## Slide 1: SA WG3 Status Report for ‘FS_CryptoPQC’
Zander Lei (Huawei)
Virendra Kumar (Qualcomm)

## Slide 2
Overall plan
‘FS_CryptoPQC’ overall plan
TUs planned
  6 TUs (total)
In SA3#123 meeting (Aug 2025)
  Agreement on Skeleton and Scope of TR 33.703.
  pCR for Assumption, Principle/Analysis, Protocol, and Threat (Key Issue)
In SA3#124 meeting (Oct 2025)
  Agreement on Template/pCR for Protocol Clause
  pCR for Assumption, Principle, Protocol, Threat, Solution
In SA3#125 meeting (Nov 2025)
  Finalizing Assumption and continue Principle/Analysis
  pCR on Protocol, Threat, Solutions/evaluation (final meeting for New Threats)
In SA3#126 meeting (Feb 2026)
  Cont. evaluating solutions, Principle/analysis, protocol profiles (final meeting for New Solutions)
In SA3#127 meeting (Apr 2026)
  Completing solution evaluation, analysis, protocol profiles and status reports for other SDOs
  Preliminary conclusions
In SA3#128 meeting (May 2026)
  Completion of TR 33.703
  Final conclusions

## Slide 3
‘‘FS_CryptoPQC” status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1080045 | Study on Transitioning to PQC | FS_CryptoPQC | Rel-20 | S3 | Jun-2026 | 15% | 50% | +35%
General
  The TR 33.703 v0.3.0 approved.
  Clauses 4-6 are nearly complete: Overview, Principles and attributes of PQC, and Protocols expected to be updated for PQC by other SDOs.
  Clause 7 “Protocols expected to be updated for PQC by 3GPP” – two key issues were identified and 17 solutions were included.
Dependencies:
  None.
Contentious Issue:
  None.
Risks:
  None identified.

## Slide 4
Pending issues
  Evaluating all solutions
  Conclusions
Dependencies:
  None
TUs consumed
  SA3#123 - 1 TU
  SA3#124 - 1.25 TU
  SA3#125 - 1 TU
TUs remaining
  2.75 TUs
TUs to be requested for the upcoming meeting
  1 TUs
Plan for completion
  Planned to close the study by SA3#128
‘‘FS_CryptoPQC” pending work and plan for completion