## Slide 1: SA WG3 Status report for ‘FS_IMSRE_SEC’
Rohini Rajendran (Samsung)

## Slide 2
TUs planned
In SA3#124 meeting:
  1 pCR agreed on scope
In SA3#125 meeting:
  Was not included in agenda as SA3 waits for CT4 to progress
In SA3#126 (upcoming) meeting:
  Request to be part of the agenda
  Open for Key issue proposals (if any) based on CT4 progress and solution
Overall plan
‘FS_IMSRE_SEC’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 | 2.5 | 0.5 | Yes | NA

## Slide 3
General
  TR 33.768 v0.1.9 currently includes only scope of the study.
Dependencies:
  Depends on CT4 progress
Contentious Issues:
  Study would progress only if there is security implications from solution(s) concluded in CT4 to resolve the number of failure scenarios at the P-CSCF.
  From current observation on solutions in TR 29.867, there seems to be no direct security implications.
Risks:
  None
‘‘FS_IMSRE_SEC‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090015 | Study on Security Aspects for IMS resiliency | ‘FS_IMSRE_SEC’ | Rel-20 | S3 | Mar-2026 | 0% | 5% | -

## Slide 4
Pending issues
  Discussion on key issues are yet to start
Dependencies:
  Depends on CT4 progress
TUs consumed
  SA3#124 - 0.25 TU
  SA3#125 - None
TUs remaining
  2.75 TUs
TUs to be requested for the upcoming meeting
  .5 TUs
Plan for completion
  Planned to close the study by SA3#127/SA3#128
‘‘FS_IMSRE_SEC‘‘ pending work and plan for completion