## Slide 1: SA WG3 Status report for ‘FS_SCAS_CP’
Markus Hanhisalo (Ericsson)

## Slide 2
TUs planned
In SA3#124 meeting:
  References, assumptions, assets, threats and test cases were approved
In SA3#125 meeting:
  1 pCR was approved to update one test case
  No agreement of the conclusion pCR.
In SA3#126 (upcoming) meeting:
  Aim is to conclude the study
  Propose and agree a WID and start the normative work (create test cases for container-based products)
Overall plan
‘FS_SCAS_CP’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 WT2 | 1 1 | 0,5 0,5 | No | NA

## Slide 3
General
  TR 33.730 v0.3.0 is only missing the conclusion of the study
Dependencies:
  None
Contentious Issues:
  Conclusion of the study and whether to create a new SCAS TS for container-based products or include test cases to TS 33.527, Security Assurance Specification (SCAS) for 3GPP virtualized network products
Risks:
  None
‘‘FS_SCAS_CP‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090021 | Study on Security Assurance Specification (SCAS) for Container-based Product | ‘FS_SCAS_CP’ | Rel-20 | S3 | Sep-2026 | 0% | 79% | -

## Slide 4
Pending issues
  whether to create a new SCAS TS for container-based products or include test cases to TS 33.527, Security Assurance Specification (SCAS) for 3GPP virtualized network products. Issue is that TS name can not be changed to include container-based products and TS would need overall many changes to incorporate container-based products SCAS.
Dependencies:
  None
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 – 0.25 TU
TUs remaining
  2.25 TUs
TUs to be requested for the upcoming meeting
  .25 TUs
Plan for completion
  SA3#126: Plan to conclude the study and propose WID
  SA3#129: plan to complete the TS
‘‘FS_SCAS_CP‘‘ pending work and plan for completion