## Slide 1: SA WG3 Status report for ‘SCAS_Femto_SeGW’
Shihan Bao (CATT)

## Slide 2
TUs planned
In SA3#124 meeting:
  TR skeleton, scope, introduction were approved.
  2 Security functional requirements on the SeGW deriving from 3GPP specifications and related test cases were approved.
  2 pCR was approved to update the product class description, critical assets and threats for SCAS_Femto_SeGW
In SA3#125 meeting:
  Security functional requirements on the SeGW deriving from 3GPP specifications and related test cases were approved.
  2 pCR was approved to update the product class description, critical assets and threats for SCAS_Femto_SeGW
In SA3#126 (upcoming) meeting:
  New test cases, test cases update and evaluations, discussion on conclusions
Overall plan
‘SCAS_Femto_SeGW’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 WT2 | 0 0 | 0.5 0.5 | No No | NA NA

## Slide 3
General
  TS 33.546 v0.2.0 contains 3 SeGW-specific test cases
Dependencies:
  None identified
Contentious Issues:
  None identified
Risks:
  None identified
‘‘SCAS_Femto_SeGW‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090026 | 5G Security Assurance Specification (SCAS) for NR Femto Security Gateway (SeGW) | ‘SCAS_Femto_SeGW’ | Rel-20 | S3 | Jun-2026 | 0% | 50% | -

## Slide 4
Pending issues
  References, assumptions, assets, threats and test cases
TUs consumed
  SA3#124 - 0.25 TU
  SA3#125 – 0.25 TU
TUs remaining
  0.5 TUs
TUs to be requested for the upcoming meeting
  SA3#126 - 0.25 TUs
  SA3#127 – 0.25 TUs
Plan for completion
  SA#112 send TS for information and approval
‘‘SCAS_Femto_SeGW‘‘ pending work and plan for completion