## Slide 1: SA WG3 Status report for ‘SCAS_NR_Femto’
Zhonghuai Xie (China Unicom)

## Slide 2
TUs planned
In SA3#124 meeting:
  TR skeleton, scope, and introduction were approved
In SA3#125 meeting:
  1 pCR was approved to update the product class description, critical assets and threats for NR Femto product
  NR Femto-specific adaptations of security functional requirements and related test cases were approved
In SA3#126 (upcoming) meeting:
  New test cases, test cases update and evaluations, discussion on conclusions
Overall plan
‘SCAS_NR_Femto’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 WT2 | 0 0 | 0.5 1 | yes yes | NA NA

## Slide 3
General
  TS 33.546 v0.2.0 contains 2 NR Femto-specific test cases
  Technical baseline was added
Dependencies:
  None identified
Contentious Issues:
  None identified
Risks:
  None identified
‘‘SCAS_NR_Femto‘‘ status after SA3#125
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090026 | Security Assurance Specification (SCAS) for NR Femto | ‘SCAS_NR_Femto’ | Rel-20 | S3 | Jun-2026 | 0% | 30% | -

## Slide 4
Pending issues
  References, assumptions, assets, threats and test cases
TUs consumed
  SA3#124 - 0.25 TU
  SA3#125 – 0.5 TU
TUs remaining
  0.75 TUs
TUs to be requested for the upcoming meeting
  SA3#126 - 0.5 TUs
  SA3#127 – 0.25 TUs
Plan for completion
  SA#112 send TS for information and approval
‘‘SCAS_NR_Femto‘‘ pending work and plan for completion