## Slide 1: Rel-19 SA5 work planning SA5#153, 29 January – 3 February, 2024
Zou Lan, 3GPP SA5 Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, 3GPP SA5 Vice-Chair, NOKIA

## Slide 2
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA5,SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Extended Stage 2 for SA5
Management requirements (SA5)
Release 19 timeline– figure with SA5 (For integrated to SA timeline)

## Slide 3: Rel-19 timeline
Key milestone timeline:
  Study items:
    for information in Jun.2024 (SA#104/SA5#156)
    for approval in Sep.2024 (SA#105/SA5#157)
  Work items
    target to finish in Jun.2025 (SA#108/SA5#161)
    latest to finish in Sep.2025 (SA#109/SA5#162)

## Slide 4: OAM TU planning and statistics
TU planning: to be proposed by moderators/rapporteurs
TU statistics: to be filled by chair based on the time consumed after each meeting

## Slide 5: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 120 TUs, implying:
  12 TUs allocated to Rel-19 SIDs / WIDs per meeting (= 120 TUs / 10 meetings)
  6 TUs allocated to each Rel-19 SID / WID in average (= 120 TUs / 20 Rel-19 SIDs/WIDs)
  0.6 TU allocated per Rel-19 SID / WID per meeting in average (= 12 TUs / 20 Rel-19 SIDs/WIDs)

## Slide 6: SA5 Rel-18 leftover TU (~Jan.2024)
 | Maintenance | R18 | R19 | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR) | 13 TU | 2 TU | 2 TU
Total= 16.5 TU | 1.5 TU | 13 TU | 2 TU | 2 TU
Assumption: Every day = 5 sessions (TUs), total TU = 18.5, total OAM TU in 1 ordinary meeting = 16.5 TU, total buffer TU = 2 TU

## Slide 7: Summary
For Rel-18 rapporteurs: Make good work plan to finalize Rel-18 work considering the time left for Rel-18.
For Rel-19 topic moderators: Propose planned TUs for SA5#153/#154/#155/#156
Rel-19 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | Jan 2024 | April 2024 | May 2024 | Aug. 2024
 |  |  |  | SA5#153 | SA5#154 | SA5#155 | SA5#156
AIML | 5.0 | 4.5 | 9.5 |  |  |  | 
MDA | 4.0 | 4.5 | 8.5 |  |  |  | 
IDM | 3.5 | 4.5 | 8.0 |  |  |  | 
CCL | 5.0 | 3.0 | 8.0 |  |  |  | 
NDT | 2.0 | 2.0 | 4.0 |  |  |  | 
CMO | 3.0 | 2.0 | 5.0 |  |  |  | 
MSEC | 1.0 | 1.0 | 2.0 |  |  |  | 
SBMA | 3.5 | 4.0 | 7.5 |  |  |  | 
PTM | 4.0 | 4.0 | 8.0 |  |  |  | 
MADCOL | 0.0 | 5.0 | 5.0 |  |  |  | 
SEPM | 2.0 | 2.0 | 4.0 |  |  |  | 
PM | 0.0 | 3.5 | 3.5 |  |  |  | 
AdNRM | 0.0 | 2.0 | 2.0 |  |  |  | 
TMQ | 0.0 | 1.0 | 1.0 |  |  |  | 
NTNM | 3.0 | 2.0 | 5.0 |  |  |  | 
IABM | 2.0 | 3.0 | 5.0 |  |  |  | 
RedcapM | 2.5 | 2.5 | 5.0 |  |  |  | 
NWDAFM | 1.50 | 2.00 | 3.5 |  |  |  | 
NSM | 1.0 | 1.0 | 2.0 |  |  |  | 
EE | 4.0 | 4.0 | 8.0 |  |  |  | 
Mexpo | 4.5 | 1.5 | 6.0 |  |  |  | 

## Slide 8: Thank you!

## Slide 9: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting = 18.5 TUs

## Slide 10: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 20 SI/WI => Average 6 TU per SI/WI (0.6/meeting). Cf. SA2: Average 6.8 TU
  => Recommended MAX no. of SI/WI = 20
  => Proposed max number of TUs allocated to any SI/WI in 1 meeting = same as in SA2 = 2

## Slide 11: Rel-19 work progress in other SA groups
  List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
950003 | Study on Integrated Sensing and Communication | FS_Sensing
1000026 | Integrated Sensing and Communication | Sensing
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse
1000028 | Mobile Metaverse Services | Metaverse
950006 | Study on Network Sharing Aspects | FS_NetShare
1000029 | Indirect Network Sharing | NetShare
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5
1000031 | FRMCS Phase 5 | FRMCS_Ph5
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3
1000024 | Satellite access Phase 3 | 5GSAT_Ph3
960017 | Study on UAV Phase 3 | FS_UAV_Ph3
1000032 | Uncrewed Aerial System Phase 3 | UAS_Ph3
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ
1000033 | Energy Efficiency as Service Criteria | EnergyServ
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT
960015 | Study on roaming value added services | FS_RVAS
990051 | Roaming Value-Added Services | RVAS
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS
990053 | Study on Interconnect of SNPN | FS_ISN
990052 | Supporting UE Mobility for XR Services | XRMobility
990050 | Edge Computing for Industrial Scenarios | EDGINDUS
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff
970044 | Multi-path relay | MultiRelay
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS
970042 | MPS for Messaging services | MPS4msg
970041 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2
980108 | Measurement Data Collection | MeasureData
1000025 | UE-to-UE multi-hop relay | UEMHopRelay
1010025 | Local traffic routing for multi-access UE | LTR_MA
1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds
1000027 | NPN security considerations | SecNPN
1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2
1010033 | Study on Integration of satellite components in the 5G architecture Phase III | FS_5GSAT_ARCH_Ph3
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg
1010005 | Study on application layer support for AI/ML services | FS_AIMLAPP
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3
1000034 | Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP
1000035 | Study on enhanced application layer support for location services | FS_eLSAPP
1000036 | Sharing of administrative configuration between interconnected MC service systems | MCShAC
1000037 | 5GMSG Service phase 3 | 5GMARCH_Ph3
1000038 | Railways specific Enhancements to Mission Critical Services | enh4FRMCS
1000039 | Enhanced Mission Critical Architecture | enhMC
1010006 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2
1010007 | Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3
1010009 | Guidelines for CAPIF Usage | CAPIF_EXT
SA1
(35)
SA2
(5)
SA3
(4)
SA6
(11)
1010010 | 5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR
1010011 | 5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) | SCAS_5G_SMSF
1010012 | Addition of 256-bit security Algorithms | 256_Algo
970002 | Lawful Interception Rel-19 | LI19
980008 Study on Diverse audio Capturing system for End-user Devices FS_DaCED
SA4(1)

## Slide 12: SA5 calendar with OAM TU (two parallel tracks on Tuesday/Wednesday)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Early Session (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
09:00 - 10:30 | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
11:00 - 12:30 | Stream#1 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
14:00 - 15:30 | Stream#1 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
16:00 - 17:30 | Stream#1 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Stream#1 (1TU) Stream#2 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
17:40 – 19:10 | Stream#1 (1TU) | Stream#1 (0.5 TU) Stream#2 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) Stream#2 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 track in ordinary meeting = 18.5 TUs
Two extra days in parallel = 9.5 sessions (TUs), total TU in 1 ordinary meeting = 28 TUs
This is practice of TU calculation, not decision for parallel tracks

## Slide 13: TU Comparison of two tracks/one track
One track:
  Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting = 18.5 TUs
Two tracks with 2 days in parallel:
  Assumption: Every day = 5 sessions (TUs), total TU in 1 track in ordinary meeting = 18.5 TUs
  Two extra day in parallel = 9.5 sessions (TUs), total TU in 1 ordinary meeting = 28 TUs
Diff: 9.5 TU* 10 meetings = 95 TU
This is practice of TU calculation, not decision for parallel tracks