## SA5#162
|  | Rel-20 |  |  | Meeting | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
[5 empty] | TU total (for planning purposes) | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5
SA5 Open plenary+ LS
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Actual
Pre-Rel-19 maintenance
|  | Planned |  |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Actual
Rel-19 maintenance + Rel-20 TEI
|  | Planned |  |  | 17 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Actual
Buffer (Overflow, other)
|  | Planned |  |  | 20 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Actual
Rel-19
|  | Planned(from the original overall plan) |  |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned(sum of individual plans)
Actual
Rel-20
|  | Planned(from the original overall plan) |  |  | 124 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12
|  | Planned(5GA) |  |  | 62 | 1 | 12 | 12 | 10 | 10 | 8 | 5 | 4 | 0 | 0
|  | Planned(6G) |  |  | 62 | 1 | 2 | 2 | 4 | 4 | 6 | 9 | 10 | 12 | 12
Planned(sum of individual plans)
Actual
Rel-21
|  | Planned |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Actual
Overall total
|  | Planned |  |  | 195 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5 | 19.5
Actual
|  | Rel-20 SID/WID detailed plan |  | TU estimates (from SID) | total TU planned by rapporteurs | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
5GA
1 | IDM |  | Study TU's planned | 4 | 4 | 1 | 1 | 1 | 1
|  | Ruiyue Xu | Study TU's used
|  | Mark Scott | Normative TU's planned | 4 | 4 |  |  |  |  | 1.5 | 1 | 1 | 0.5
Normative TU's used
2 | AIML |  | Study TU's planned | 4 | 0 | 0
|  | Hassan | Study TU's used |  | 0
|  | Jose | Normative TU's planned | 4 | 0
|  |  | Normative TU's used |  | 0
3 | NDT |  | Study TU's planned | 2 | 2 |  | 0.5 | 1 | 0.5
|  | Xian Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 |  |  |  |  | 1 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
4 | SBMA |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Kai Zhang | Study TU's used |  | 0
|  | Balazs | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
5 | EE |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.5 | 1 | 1
|  | Srilakshmi | Study TU's used |  | 0
|  | Ashutosh Kaushik | Normative TU's planned | 2.5 | 2.5 |  |  |  |  | 0.3 | 0.7 | 0.8 | 0.7
|  |  | Normative TU's used |  | 0
6 | MDA |  | Study TU's planned | 2 | 0 | 0
|  | Brendan | Study TU's used |  | 0
|  | Gang Li | Normative TU's planned | 2 | 0
|  |  | Normative TU's used |  | 0
7 | MADCOL |  | Study TU's planned | 2.75 | 2.75 | 0.7 | 0.7 | 0.65 | 0.7
|  | Sreekumar | Study TU's used |  | 0
|  | Robert Petersen | Normative TU's planned | 1.25 | 1.25 |  |  |  |  | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  |  | Normative TU's used |  | 0
8 | Mexpo |  | Study TU's planned | 2.5 | 0 | 0
|  | Winnie | Study TU's used |  | 0
|  |  | Normative TU's planned | 1.5 | 0
|  |  | Normative TU's used |  | 0
9 | CCL |  | Study TU's planned | 2 | 0 | 0
|  | Deepanshu | Study TU's used |  | 0
|  | Stephen | Normative TU's planned | 2 | 0
|  |  | Normative TU's used |  | 0
10 | AdNRM |  | Study TU's planned | 0 | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Xiaoli Shi | Normative TU's planned | 4 | 4 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.3
|  |  | Normative TU's used |  | 0
11 | PMTMQ |  | Study TU's planned | 0 | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Qiang Zu | Normative TU's planned | 5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Normative TU's used |  | 0
12 | NWDAFM |  | Study TU's planned | 0 | 0
|  | Song Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.4 | 0.4 | 0.4 |  | 0.4 | 0.4
|  |  | Normative TU's used |  | 0
13 | XRMM |  | Study TU's planned | 0 | 0
|  | pengxiang Xie | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.3 | 0.5 | 0.3 | 0.4 | 0.4 | 0.1
|  |  | Normative TU's used |  | 0
6G |  |  | Study TU's planned | 62
|  |  | TU consumed according to plan | TU planned | TU actual used
|  | Total for Rel-20 Studies |  | 87.75
|  | Total for Rel-20 Normative |  | 36.25
|  | Total for Rel-20 SID/WID |  | 124
|  | Breakout sessions bonus TU used | Total | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | total BONUS TU
1 | IDM | Intent driven management enhancement
2 | AIML | AIML management enhancement
3 | NDT | NDT enhancement
4 | SBMA | SBMA enhancement
5 | EE | Energy efficiency enhancement
6 | MDA | MDA enhancement
7 | MADCOL | Data Management enhancement
8 | Mexpo | MExpo enhancement
9 | CCL | CCL enhancement
10 | AdNRM | AdNRM
11 | PMTMQ | PM/KPI/Trace/MDT/QoE/SON enhancement
12 | NWDAFM | NWDAFM
13 | XRMM | XR management
Other
|  | Rel-20 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | leftover
1 | CAPCH |  | Study TU's planned | 1
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
2 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
3 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
4 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
5 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
6 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
7 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
8 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used