## Version history
Document version history
Date | Version | Description of Change
2010-05-30 | 48_1 | Status update for TSGs #48. Several new RFCs and new drafts approved by IESG. draft-johnston-dispatch-sip-cc-uui replaces draft-johnston-sipping-cc-uui and draft-devarapalli-pmipv6-heartbeat has been replaced by draft-ietf-netlmm-pmipv6-hearbeat.
2010-05-18 | 48_0 | Updated information on draft-ietf-sipping-config-framework, draft-dawes-dispatch-mediasec-parameter added. draft-ietf-simple-common-policy-caps was removed to reflect its removal from 24.141 in CT1 #64
2010-03-15 | 47_7 | d
2010-02-18 | 47_6 | More updates from 3GPP - IETF telco, status update of all drafts, duplicated lines for draft-ietf-dime-qos-attributes and draft-ietf-v6ops-3gpp-analysis were removed
2010-02-12 | 47_5 | Updates from 3GPP - IETF telco
2010-02-11 | 47_4 | Updated based on review comments. draft-ietf-sipping-config-framework was put back on the list for SA4 use and draft-tschofenig-dime-diameter-qos was replaced by draft-ietf-dime-qos-attributes
2010-02-04 | 47_3 | Updated version after 3GPP review on 3rd of February: draft-mmusic-ice-tcp, draft-sipcore-keep, draft-mediactrl-vxml, draft-mediactrl-sip-control-framework, draft-mediactrl-ivr-control-package, draft-mediactrl-sip-control-package, draft-sipcore-invfix, draft-sip-ipv6-abnf-fix, draft-kaplan-dispatch-session-id added, draft-dotson-sip-mutual-auth was removed and draft-dawes-sipping-debug-event and debug-id were merged into draft-dawes-sipping-debug. CT1 dependency on mikey-ticket added, several comments added and status of all drafts updated
2010-02-02 | 47_2 | Interim version while preparing for 3GPP review on the 3rd of February
2010-01-28 | 47_1 | Status update of all drafts
2010-01-04 | 47_0 | Correction to the title of draft-das-mipshop-andsf-dhcp-options
2009-12-06 | 46_5 | draft-patel-dispatch-cpc-oli-parameter replaces dead draft-mahy-iptel-cpc. Status update of all drafts
2009-11-29 | 46_4 | Editorial updates on the previous version.
2009-11-27 | 46_3 | Updated for TSG CT #46: Rel-9 dependencies are included, draft-jesske-sipping-etsi-ngn-reason was replaced with draft-jesske-dispatch-reason-in-responses and systematic status update of all drafts was made
2009-11-05 | 46_2 | Updated for IETF #76: draft-ietf-sip-xcapevent is also needed by SA4, draft-zeilenga-ldap-txn and mattson-mikey-ticket were added. Also systematic status update of all drafts
2009-10-21 | 46_1 | Updates received in the 3GPP - IETF teleconference. Mainly status information on outstanding drafts. draft-muhanna-mext-binding-revocation replaced with draft-ietf-mext-binding-revocation
2009-09-30 | 46_0 | Updated for 3GPP - IETF review: draft-ietf-dime-diameter-cmd-codes added and systematic status update done
2009-09-08 | 45_3 | Updated for TSGs #45: Status update of all items and duplicated draft-ietf-dime-qos-attributes was merged to just one line
2009-08-25 | 45_2 | Rel-5 dependencies were removed since they are all completed
2009-07-27 | 45_1 | rfc3344bis and draft-ietf-bliss-call-completion were changed from "possible" to "definite" dependencies. draft-giaretta-netlmm-mip-interactions is not referenced in 23.402 any more and therefore it was removed from the list.
2009-07-23 | 45_0 | Status update for IETF #75
2009-06-02 | 44_6 | Updates based on TSG CT #44 feedback: removed Rel-5 which is already completed and added Rel-8 to frozen releases
2009-05-25 | 44_5 | Updates for TSG #44: draft-ietf-mmusic-file-transfer re-named to draft-ietf-mmusic-file-transfer-mech and systematic status update
2009-05-04 | 44_4 | Updates from 3GPP - IETF conference call: draft-ietf-mext-nemo-v4traversal is approved by IESG, draft-das-mipshop-andsf-dhcp-options is not a MIPSHOP WG item, draft-ietf-mipshop-mos-dns-discovery was removed from the list as it is not referenced from the latest version of 24.302.
2009-04-29 | 44_3 | Systematic status update of all drafts, draft-arkko-mext-rfc2775-altcoa-check was removed, draft-ietf-mip6-bootstrapping-split (RFC 5026) is referenced from 24.302 which makes is definite dependency but that is not a problem as the document is already an RFC. draft-ietf-mipshop-mos-dhcp-options is replaced with draft-das-mipshop-andsf-dhcp-options
2009-03-30 | 44_2 | Systematic status update of all drafts, draft-ietf-sip-info-events was added and draft-ietf-mext-rfc3775bis changed to non-critical
2009-03-26 | 44_1 | Better descriptions of the new drafts, explanation of categorisation added on Statistics page
2009-03-20 | 44_0 | Updates during IETF #74: draft-montemurro-gsma-imei-urn, draft-alexeitsev-bliss-alert-info-urns, draft-ietf-mmusic-sdp-media-capabiliies, draft-garcia-mmusic-sdp-cs and draft-garcia-mmusic-sdp-misc-cap were added. draft-ietf-mmusic-sdp-capability-negotiation is also used in 24.292
2009-03-02 | 43_3 | Updates for TSGs #43: reference to draft-saklikar-communication-diversion-notification is removed and reference to draft-avasarala-sipping-comm-div-notification was added. Also systematic status update of all drafts was made
2009-02-04 | 43_2 | Updates from 3GPP - IETF telco: draft-patel-ecrit-sos-parameter added as new dependency, draft-jones-3gpp-eps-command-codes changed to critical dependency
2009-01-30 | 43_1 | Draft status update for 3GPP - IETF telco
2009-01-12 | 43_0 | draft-ietf-mip6-bootstrapping-integrated, draft-ietf-hokey-emsk-hierarchy, draft-arkko-mext-rfc3775-altcoa-check, draft-ietf-mext-rfc3775bis added
2008-11-28 | 42.2 | Status update of all drafts
2008-11-03 | 42.1 | More updates for 3GPP - IETF telco: draft-jones-3gpp-eps-command-codes and draft-ietf-avt-rtcp-non-compound added as new dependency
2008-10-30 | 42.0 | Status update for 3GPP - IETF telco: draft-ietf-bliss-call-completion is becoming critical to avoid parallel solutions, draft-saklikar-diversion-notification added and systematic status update of all drafts
2008-09-15 | 41.0.3 | Update for TSG SA #41: Status update of published RFCs
2008-09-08 | 41.0.2 | Update for TSGs #41: draft-bakker-sipping-3gpp-ims-xml-body-handling added
2008-09-08 | 41.0.1 | Update for TSGs #41: draft-muhanna-mip6-binding-revocation replaced with draft-muhanna-mext-binding-revocation, draft-dawes-sipping-debug-event, draft-dawes-sipping-debug-id and draft-arkko-eap-aka-kdf added as new drafts and systematic status update of all drafts
2008-07-24 | 41.0.0 | Update before IETF #72: draft-ietf-simple-imdn is also needed by CT3, draft-devarapalli-netlmm-pmipv6-heartbeat added, systematic status update of all drafts with several new drafts marked as approved
2008-06-03 | 40.0.6 | Still more updates for TSG SA #40. draft-ietf-mmusic-sdp-capability-negotiation, draft-ietf-sip-multiple-refer, draft-ietf-sip-uri-list-subscribe, draft-ietf-mmusic-file-transfer and draft-bliss-call-completion were added
2008-06-02 | 40.0.5 | Further updates for TSG SA #40. draft-vanelburg_sipping-served-user, draft-vanelburg-sipping-private-network-indication, draft-ietf-mmusic-sdp-capability-negotiation, draft-ietf-sip-multiple-refer, draft-ietf-sip-uri-list-subscribe, draft-ietf-mmusic-file-transfer and draft-bliss-call-completion were added
2008-06-02 | 40.0.4 | Version going to TSG SA #40 with CT comments included. Draft-ietf-mipshop-mos-dns-discovery, draft-ietf-mipshop-dhcp-options and dotson-sip-mutual-auth added as new dependencies and full status update of all drafts
2008-05-26 | 40.0.3 | Version going to TSGs #40, jesske-sipping-ngn-reason and monrad-sipping-3gpp-urn-namespace added and full status update done to all drafts
2008-05-05 | 40.0.2 | More updates based on CT rapporteurs comments, draft-johnston-sipping-cc-uui added
2008-04-21 | 40.0.1 | More updates: draft-ietf-qos-attributes added as Rel-7 dependency, draft-ietf-simple-imdn, draft-ietf-dime-qos-attributes, draft-ietf-dime-mip6-split and draft-ietf-sipping-race-examples added
2008-04-17 | 40.0.0 | Updates from March plenaries and April WG meeting round
2008-02-29 | 39.0.2 | Updates from the 3GPP - IETF conference call: mip6-ha-switch, korhonen-dime-pmip6, ietf-dime-mip6-integrated, korhonen-mip4-service, muhanna-mip6-binding-revocation, muhanna-netlmm-grekey-option and giaretta-netlmm-mip-interactions were added and a systematic status update was made on all drafts
2008-02-12 | 39.0.1 | Status update for 3GPP - IETF conference call and draft-ietf-mip6-hiopt added
2007-11-26 | 38.0.2 | Status update for TSGs #38
2007-10-26 | 38.0.1 | Outdated SAE dependencies from 23.882 are identified in this version as well as the updates from the 3GPP - IETF conference call. ietf-mip4-rfc3344bis was added based on 24.801 reference and ietf-mobike-protocol, ietf-mip4-fmipv4, giaretta-netlmm-dt-protocol, leung-mip4-proxy-mode, chowdhury-netmip6, sgundave-mip6-proxymip6, ietf-mip4-dsmipv4 were removed from the list as they were only referenced from the outdated 3GPP TR 23.882
2007-10-19 | 38.0.0 | Status update for 3GPP - IETF conference call
2007-09-07 | 37.0.0 | Status update for TSGs #37. New RFCs: P-Profile key, rosen-iptel-dialstring. IESG approved drafts in RFC editor's queue: sip-acr-code, ietf-ecrit-service-urn, sipping-gruu-reg-event, ice-option-tag, ejzak-sipping-p-em-auth, simple-presence-rules. SAE dependencies ietf-mip6-nemo-v4traversal, netlmm-proxymip6 and netlmm-pmip6-ipv4-support have become definite references from TS instead of possibly needed in TR. New dependencies to draft-ietf-mip6-bootstrapping-split, draft-ietf-netlmm-pmip6-ipv4-support, draft-ietf-netlmm-proxymip6
2007-06-18 | 36.0.4 | Status update of all drafts based on I-D tracker
2007-06-04 | 36.0.3 | draft-simon-emu-rfc2716bis added, draft-drage-sipping-service-identification and draft-rosenberg-sip-app-media-tag were added. Also full status update
2007-05-28 | 36.0.2 | Status update for TSGs #36
2007-05-23 | 36.0.1 | IETF WG added for yu-tel-dai -draft, draft-ietf-radext-filter-rules is now RFC 4849. Systematic status update of all drafts
2007-05-10 | 36.0.0 | Updated for TSGs #36: draft-ejzak-sipping-p-em-auth, allen-sipping-poc-p-answer-state-header and yu-tel-dai added
2007-03-21 | 35.3.0 | More details filled in to the new Rel-7 dependencies
2007-03-10 | 35.2.0 | Status update for TSG SA #35: all checked, no changes
2007-02-21 | 35.1.0 | Comments from 3GPP - IETF conference call, new Rel-7 dependencies added towards draft-mahy-iptel-cpc, draft-camarillo-sipping-profile-key, draft-ietf-mmusic-ice, draft-ietf-behave-rfc3489bis, draft-ietf-behave-turn, draft-ietf-sip-ice-option-tag, draft-rosen-iptel-dialstring, draft-ietf-sip-uri-list-conferencing and status update of existing dependencies. Rel-7 is considered frozen in 3GPP TSGs #35
2007-02-19 | 35.0.0 | Document version numbering aligned with 3GPP plenary meeting numbers, tschofenig-radext-qos, tschofenig-dime-diameter-qos added, draft-ietf-sip-uri-list-message moves from SIPPING to SIP, status update of all drafts
2006-12-07 | 7.0.2 | Comments removed
2006-11-22 | 7.0.1 | Status update before CT and SA #34: rosenberg-presence-processing-model removed
2006-11-22 | 7.0.0 | Status update before CT and SA #34: Rel-7 and Rel-8 dependencies are reported separately and redundant number column is removed.
2006-11-03 | 6.8.3 | Status update of all dependencies and koodli-mip4-fmipv4 replaced by draft-ietf-mip4-fmipv4, giaretta-netlmm-protocol replaced with giaretta-netlmm-dt-protocol, gundavelli-netlmm-mip6-proxy replaced with draft-sgundave-mip6-proxymip6, wood-netlmm-emp-base replaced with chowdhury-netmip6, leung-mip4-proxy-mode and ietf-mip6-nemo-v4traversal were added
2006-11-03 | 6.8.2 | Status update before IETF #67: RFC 4660, 4661 published, lehtovirta-srtp-rcc and ikev2-ocsp are approved by IESG
2006-09-27 | 6.8.1 | RFC 4555 was changed to "desirable" instead of "critical"
2006-09-22 | 6.8.1 | Also the new RFCs were updated since the previous version (sdp-new, avt-rtcp-feedback, avt-rtp-retransmission, newtype-keyid, sdp-srcfilter, simple-cipid, event-list, presence-data-model, simple-rpid, indirect-mech, cc-conferencing, conference-package, mobike-protocol) and ikev2-ocsp has proceeded to IESG evaluation
2006-09-13 | 6.8.0 | Updates for TSGs #33: simple-message-sessions, simple-xcap, srtp-rcc, gruu-reg-event are in IESG and geopriv-common-policy and ikev2-multiple-auth are in RFC editor's queue
2006-07-10 | 6.7.6 | Updates during CT1 #42bis and IETF 66: sip-outbound and geopriv-common-policy added and some status updates
2006-07-06 | 6.7.5 | Updates for IETF #66 review: No status updates on any drafts, just more questions to ADs on the status of some drafts
2006-05-24 | 6.7.4 | Also CT3 needs draft-eronen-ipsec-ikev2-multiple-auth
2006-05-11 | 6.7.3 | sipping-sos was removed from the list as it is not referenced by 3GPP any more.
2006-05-10 | 6.7.2 | draft-schulzrinne-sipping-emergency-arch is removed from the list as it is not referenced by 3GPP, draft-ietf-radext-ieee802 was replaced with draft-ietf-radext-filter-rules
2006-04-28 | 6.7.1 | Rel-8 SAE dependencies were added
2006-03-28 | 6.7.0 | The Rel-7 IETF dependencies from 3GPP TRs and draft TSs were added to this version
2006-03-19 | 6.6.3 | Updates during after the 3GPP #31 plenaries, draft-ietf-geopriv-dhcp-civil, draft-ietf-ecrit-service-urn, draft-ietf-sipping-sos and draft-ietf-sip-location-conveyance added
2006-03-02 | 6.6.2 | Updates on statistics worksheet
2006-02-27 | 6.6.1 | Updates from 3GPP - IETF conference call included
2006-02-22 | 6.6.0 | Updates for the March 3GPP plenaries, draft-arkko-map-doi removed
2006-02-21 | 6.5.7 | Updates from 3GPP - IETF conference call. draft-elwell-sipping-redirection-reason and draft-jesske-sipping-etsi-ngn-reason removed and draft-jennings-sip-voicemail-uri and draft-sip-acr-code added
2006-02-20 | 6.5.6 | Interim version during 3GPP - IETF conference call
2006-02-15 | 6.5.5 | Status update of all items from ID tracker. Updated: sdp-new, simple-presence-data-model, simple-rpid, newtype-keyid, rmt-flute-sdp, sipping-user-database and lots of new RFC numbers
2006-02-03 | 6.5.4 | Updates after December 2005 TSG meetings. RFCs 4005 and 4072 were given RFC numbers. New Rel-6 dependencies to ietf-radext-ieee802 and draft-lehtovirta-srtp-rcc added
2005-11-23 | 6.5.3 | drage-sipping-rfc3455bis added, draft-arkko-radext-multi-service-decisions removed based on CT4 CR, chargeable-user-id, ietf-simple-filter-format are in RFC editor's queue. Drafts in LC are not grouped together with those in IESG evaluation but "in progress".
2005-10-19 | 6.5.2 | arkko-radext-multi-service-decisions changed to nice to have, ietf-avt-rtp-amrwbplus and adrangi-eap-network-discovery, mmusic-srcfilter and avt-rtp-retransmission are in RFC Ed queue, eap-keying changed to non-critical, geopriv-common-policy removed as there is no direct reference to it from 3GPP
2005-10-12 | 6.5.1 | Interim version for review with IETF ADs on the 18th of October 2005
2005-09-14 | 6.5.0 | status of all dependency drafts updated, draft-jesske-sipping-etsi-ngn-reason and arkko-radext-multi-service-decisions added, rosenberg-simple-common-policy-caps replaced with simple-common-policy-caps, rosenberg-simple-pres-policy-caps replaced with simple-pres-policy-caps
2005-07-31 | 6.4.1 | avt-rtp-3gpp-timed-text and avt-rtp-retransmission were made "definite" dependencies, the reason for referencing elwell-sipping-redirection-reason was clarified
2005-07-29 | 6.4.0 | msec-newtype-keyid is the responsibility of msec, draft-ietf-simple-partial-publish changed to critical, draft-elwell-sipping-redirection-reason added, more accurate title to geopriv-pidf-lo, corrected numbering of Rel-7 items and complete IETF status update of all referenced items
2005-05-24 | 6.3.3 | Statistics formula updates
2005-05-23 | 6.3.2 | Converted the table to Excel and added the 3GPP dependency column and statistics sheet
2005-05-19 | 6.3.1 | simple-xcap-package is replaced with simple-xcap-diff. Draft-ietf-eap-keying is not a CT1 dependency any more. RFC 3890 and RFC 3960 are actually not referenced by 3GPP, so they were removed from the list. The risk level of draft-ietf-simple-event-filter-funct and draft-ietf-simple-filter-format were changed to COMPLETED as they are already in the editor’s queue. Draft-camarillo-sipping-user-database and draft-ietf-sip-history-info added as Rel-7 dependencies. Draft-ietf-tls-psk is in IESG evaluation and draft- ietf-tls-rfc2246-bis is in IETF LC.
2005-05-11 | 6.3.0 | Change of contact person from Stephen Hayes to Hannu Hietalahti, Editorial modifications of the notes, removal of the “priority” column, CN WGs changed to corresponding CT WGs, Rel-7 dependencies split out to separate table, draft-rosenberg-simple-presence-processing-model added, status update for several drafts based on the IETF ID tracker, draft-ietf-simple-partial-publish, was changed to definite need in 3GPP.
2005-05-09 | 6.2.4 | Updated status of items.

## Statistics
3GPP dependencies on IETF drafts, statistics sheet
Rel-6 |  | Rel-9
Rel-6 dependencies | 77 | Rel-9 dependencies | 4
RFC | 73 | RFC | 1
RFC Ed queue | 2 | RFC Ed queue | 0
IESG evaluation | 1 | IESG evaluation | 1
In progress | 1 | In progress | 2
Rel-7
Rel-7 dependencies | 37
RFC | 30
RFC Ed queue | 1
IESG evaluation | 1
In progress | 5
Rel-8 |  | Old releases (Rel-6, Rel-7, Rel-8)
Rel-8 dependencies | 47 | Rel-6, 7 and 8 dependencies | 161
RFC | 20 | RFC | 123
RFC Ed queue | 6 | RFC Ed queue | 9
IESG evaluation | 3 | IESG evaluation | 5
In progress | 17 | In progress | 23
Legend:
Risk: Probability of the draft NOT becoming an RFC by the end of the release
How definite: Normative references are "definite" and references in TRs and other non-normative documents are "possible"
3GPP priority: Items that are needed for certain functionality or feature are "desirable"
Items with regulatory mandate and items that break (a part of) the architecture if missing are "critical"
3GPP need: what is the 3GPP use of the draft
Consequences if not done: What goes wrong or cannot be done if the draft fails to become an RFC

## Table
3GPP dependencies on IETF drafts, detailed table format
Title | DraftBaseName | Risk | How definite? | 3GPP Priority | 3GPP Need | Consequences if not done | 3GPP WG | 3GPP dependency | 3GPP Rel | IETF WG | IETF Status | Comment
Release 6 dependencies
Diameter Network Access Server Application | ietf-aaa-diameter-nasreq | COMPLETED | Definite | Critical | WLAN charging | Cannot use Diameter for charging collection | SA2 CT4 |  | Rel 6 | AAA | RFC 4005
Diameter Extensible Authentication Protocol (EAP) Application | ietf-aaa-eap | COMPLETED | Definite | Critical | Use of EAP in WLAN environments (informational OK) | 4825 | SA2 SA3 |  | Rel 6 | AAA | RFC 4072
Extended RTP Profile fo RTCP-based Feedback (RTP/AVPF) | ietf-avt-rtcp-feedback | COMPLETED | Definite | Critical | Improved feedback mechanism for Audio Visual Profile | AV stream QoS degrades | SA4 |  | Rel 6 | AVT | RFC 4585
RTP Control Protocol Extended Reports (RTCP XR) | ietf-avt-rtcp-report-extns | COMPLETED | Definite | Critical | Improved RTCP reporting | AV stream QoS degrades | SA4 |  | Rel 6 | AVT | RFC 3611
RTP Payload format for 3GPP Timed Text | ietf-avt-rtp-3gpp-timed-text | COMPLETED | Definite | Critical | Support of timed text in streaming | Cannot provide timed text | SA4 | Codec / AVT | Rel 6 | AVT | RFC 4396
RTP Payload Format and AMRWB+ Audio Codec | ietf-avt-rtp-amrwbplus | COMPLETED | Definite. Needed in AMR-WB+ codec selected by 3GPP | Critical | Support of AMRWB+ | Cannot support AMR WB+ codec | SA4 | Codec / AVT | Rel 6 | AVT | RFC 4352
RTP Payload Formats for ETSI Standard ES 202 050, ES 202 211, and ES 202 212 Distributed Speech Recognition Encoding | ietf-avt-rtp-dsr-codecs | COMPLETED | Definite | Critical | RTP Support for DSR | Speech enabled services over IP with recommended codec not possible | SA4 |  | Rel 6 | AVT | RFC 4060
RTP payload Format for JVT Video | ietf-avt-rtp-h264 | COMPLETED | Definite | Critical | Support of H.264 codec | Cannot support H.264 codec | SA4 |  | Rel 6 | AVT | RFC 3984
RTP Retransmission Payload Format | ietf-avt-rtp-retransmission | COMPLETED | Definite | Desirable | Improved error resilience in PSS | Lower QoS in PSS | SA4 | Codec / AVT | Rel 6 | AVT | RFC 4588
MIME Type Registrations for3GPP Multimedia files | singer-avt-3gpp-mime | COMPLETED | Definite | Critical | MIME type for 3GPP AV files | 3GPP types not properly registered | SA4 |  | Rel 6 | AVT | RFC 3839
Mediating Network Discovery in the EAP | adrangi-eap-network-discovery | COMPLETED | Definite | Critical | Use EAP information for Network Discovery (Informational OK) | Cannot do WLAN roaming | CT1 SA2 SA3 | WLAN | Rel 6 | EAP | RFC 4284
EAP AKA Authentication | arkko-pppext-eap-aka | COMPLETED | Definite | Critical | AKA in EAP (Informational OK) | Use of AKA with alternate access methods (such as WLAN) | CT1 CT4 SA3 |  | Rel 6 | EAP | RFC 4187
EAP Key Management Framework | eap-keying | COMPLETED | Definite | Desirable | How to use EAP for generating, transporting keys for WLAN authentication (Informational OK) | Cannot do WLAN authentication or provide secondary keys | CT4 SA3 | WLAN | Rel 6 | EAP | RFC 5247
Extensible Authentication Protocol | eap-rfc2284bis | COMPLETED | Definite | Critical | EAP extensions to allow use in authentication over WLAN | Cannot do WLAN authentication | CT4 SA3 |  | Rel 6 | EAP | RFC 3748
EAP SIM Authentication | haverinen-pppext-eap-sim | COMPLETED | Definite | Critical | Use of EAP to carry SIM info (Informational OK) | Cannot re-use 2G security in WLAN | SA2 SA3 CT1 |  | Rel 6 | EAP | RFC 4186
Presence based location object format | ietf-geopriv-pidf-lo | COMPLETED | Definite | Critical | Carrying location info in presence | Insufficient Presence Service | CT1 |  | Rel 6 | GEOPRIV | RFC 4119
Carrying Location Objects in RADIUS | ietf-geopriv-radius-lo | COMPLETED | Definite | Critical | Collection of info about visited environment | Cannot provide location aware charging, authentication or authorization | CT4 | Other | Rel 6 | GEOPRIV | RFC 5580
Common Presence and Instant Messaging: Message Format | ietf-impp-cpim-msgfmt | COMPLETED | Definite | Critical | IMS Messaging | IMS Messaging not Available | CT1 |  | Rel 6 | IMPP | RFC 3862
CPIM Presence Information Data Format | ietf-impp-cpim-pidf | COMPLETED | Definite | Critical | Presence | Presence Service not Available | CT1 |  | Rel 6 | IMPP | RFC 3863
Common Profile for IM | ietf-impp-im | COMPLETED | Definite | Critical | IMS Messaging | Interoperability with CPIM compromised. | CT1 |  | Rel 6 | IMPP | RFC 3860
Common Profile for Presence | ietf-impp-pres | COMPLETED | Definite | Critical | Presence | Interoperability with CPIM compromised. | CT1 |  | Rel 6 | IMPP | RFC 3859
Address Resolution for IM and Presence | ietf-impp-srv | COMPLETED | Definite | Critical | Presence &IMS Messaging | Interoperability with CPIM compromised. | CT1 |  | Rel 6 | IMPP | RFC 3861
Internet Key Exchange (IKEv2) Protocol | ietf-ipsec-ikev2 | COMPLETED | Definite | Critical | Secure WLAN Interworking | Improvements to IKE needed for WLAN | SA3 |  | Rel 6 | IPSEC | RFC 4306
Cryptographic Suites for IPSec | ietf-ipsec-ui-suites | COMPLETED | Definite | Critical | Secure WLAN Interworking | IKEv2 profiles for I-WLAN | SA3 |  | Rel 6 | IPSEC | RFC 4308
Cryptographic Algorithms for use in the Internet Key Exchange Version 2 | ipsec-ikev2-algorithms | COMPLETED | Definite | Critical | Poor ikev2 interoperability | Nodes may not be able to negotiate mutual security algorithms | SA3 |  | Rel 6 | IPSEC | RFC 4307
UDP Encapsulation of IPSec ESP Packets | ipsec-udp-encaps | COMPLETED | Definite | Critical | NAT traversal | Cannot traverse NATPTs | SA3 |  | Rel 6 | IPSEC | RFC 3948
The tel URI for Telephone Numbers | ietf-iptel-rfc2806bis | COMPLETED | Definite | Critical | Define a tel URI | Cannot contact E.164 addressed users | CT1 |  | Rel 6 | IPTEL | RFC 3966
The Key ID Information Type for the General Extension Payload in MIKEY | msec-newtype-keyid | COMPLETED | Definite | Critical | Key transport in MMS | No secure streams or difficulty in distributing keys | SA3 | Other | Rel 6 | MSEC | RFC 4563
Session Description Protocol (SDP) Source Filters | ietf-mmusic-sdp-srcfilter | COMPLETED | Definite | Critical | Proved receiver with source multicast address | Source filtering not possible | SA4 | Other | Rel 6 | MMUSIC | RFC 4570
Intra-Site Automatic Tunnel Addressing Protocol (ISATAP) | ietf-ngtrans-isatap | COMPLETED | Definite | Desirable | Tunneling IPv6 sessions over IPv4 PDP contexts | IPv6 users cannot roam to networks supporting IPv4 only. | SA2 |  | Rel 6 | NGTRANS | RFC 4214
Internet X.509 Public Key Infrastructure Certificate Management Protocol | ietf-pkix-rfc2510bis | COMPLETED | Definite | Critical | Management of Certificates for Network Domain Security | Manual methods of managing Certificates must be used with admin overhead and likely security lapses. | SA3 |  | Rel 6 | PKIX | RFC 4210
The Network Access Identifier | ietf-radext-rfc2486bis | COMPLETED | Definite | Critical | NAI format for Network Selection (Informational OK) | Cannot do WLAN roaming | SA2 SA3 | WLAN | Rel 6 | RADEXT | RFC 4282
Chargeable User Identity | radext-chargeable-user-id | COMPLETED | Definite | Critical | WLAN | Must use private ID which lowers security | CT4 | WLAN | Rel 6 | RADEXT | RFC 4372
FLUTE – File Delivery over Unidirectional Transport | ietf-rmt-flute | COMPLETED | Definite | Critical | Defines unidirectional file transport protocol | Cannot do MBMS file download | SA4 |  | Rel 6 | RMT | RFC 3926
SDP Descriptors for FLUTE | mehta-rmt-flute-sdp | COMPLETED except for publication | Definite | Critical | Using the same identifier for FLUTE over UPD in both IETF and 3GPP domain | 3GPP will define its own protocol identifier for FLUTE over UPD | SA4 | Other | Rel 6 | RMT MMUSIC | RFC Ed Queue | This individual submission has been in RFC editor's queue since September 2006. MISSREF on draft-ietf-rmt-flute-revised
Contact Information in Presence Information Data Format | ietf-simple-cipid | COMPLETED | Definite | Critical | Contact Info | Insufficient Presence Service | CT1 | Presence | Rel 6 | SIMPLE | RFC 4482
Functional Description of Event Notification Filtering | ietf-simple-event-filter-funct | COMPLETED | Definite | Critical | Filtering Mechanism | insufficient Presence Service | CT1 |  | Rel 6 | SIMPLE | RFC 4660
SIP Event Notification Extension for Collections | ietf-simple-event-list | COMPLETED | Definite | Critical | To subscribe to collections of event packages | Inefficient or limited Presence service | CT1 | Presence | Rel 6 | SIMPLE | RFC 4662
An Extensible Markup Language (XML) Based Format for Event Notification Filtering | ietf-simple-filter-format | COMPLETED | Definite | Critical | Filter Data Structure | insufficient Presence Service | CT1 |  | Rel 6 | SIMPLE | RFC 4661
Is-composing Indication for Instant Messaging Using SIP | ietf-simple-iscomposing | COMPLETED | Definite | Critical | IMS Messaging | No information that user is composing a message | CT1 |  | Rel 6 | SIMPLE | RFC 3994
The Message Session Relay Protocol | ietf-simple-message-sessions | COMPLETED | Definite | Critical | IMS Messaging | No session based instant messaging (including chat) | CT1 | Messaging | Rel 6 | SIMPLE | RFC 4975
Partial Notification of Presence Information | ietf-simple-partial-notify | COMPLETED | Definite- solution to requirements in draft-ietf-simple-presinfo-deliv-reqs | Critical | Partial notification | Presence state must be completely refreshed | CT1 | Presence | Rel 6 | SIMPLE | RFC 5263
Presence Information Data Format (PIDF) Extension for Partial Presence | ietf-simple-partial-pidf-format | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-presinfo-deliv-reqs | Critical | Partial notification | Presence state must be completely refreshed | CT1 | Presence | Rel 6 | SIMPLE | RFC 5262
Partial Publication of Presence Information | ietf-simple-partial-publish | COMPLETED | Definite | Critical | Ability to only update some presence info | Inefficient presence service | CT1 | Presence | Rel 6 | SIMPLE | RFC 5264
User Agent Capability Presence Status Extension | ietf-simple-prescaps-ext | COMPLETED | Definite | Critical | UEs can indicate presence capabilities | insufficient Presence Service | CT1 | Presence | Rel 6 | SIMPLE | RFC 5196
SIP Extensions for Presence | ietf-simple-presence | COMPLETED | Definite | Critical | Presence | Presence Service not Available | CT1 CT5 |  | Rel 6 | SIMPLE | RFC 3856
A Data Model for Presence | ietf-simple-presence-data-model | COMPLETED | Definite | Critical | Required for presence server to produce consistent presence state | inconsistent presence data delivered | CT1 | Presence | Rel 6 | SIMPLE | RFC 4479
XCAP Usages for Setting Presence Authorization | ietf-simple-presence-rules | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-data-req | Critical | Protocol for presence data manipulation | User cannot manage lists and authorization | CT1 | Presence | Rel 6 | SIMPLE | RFC 5025
RPID – Rich Presence Information Data Format | ietf-simple-rpid | COMPLETED | Definite | Critical | Presence | 3GPP specific format used. Interoperability compromised. | CT1 | Presence | Rel 6 | SIMPLE | RFC 4480
An XML Based Format for Watcher Information | ietf-simple-winfo-format | COMPLETED | Definite | Critical | Presence | Presence Service not Available | CT1 |  | Rel 6 | SIMPLE | RFC 3858
A SIP Event Sub-Package for Watcher Information | ietf-simple-winfo-package | COMPLETED | Definite | Critical | Presence | Presence Service not Available | CT1 |  | Rel 6 | SIMPLE | RFC 3857
The Extensible Markup Language (XML) Configuration Access Protocol (XCAP) | ietf-simple-xcap | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-data-req | Critical | Protocol for presence data manipulation | User cannot manage lists and authorization | CT1 | Presence | Rel 6 | SIMPLE | RFC 4825
XCAP Usage for Resource Lists | ietf-simple-xcap-list-usage | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-data-req | Critical | Protocol for presence data manipulation | User cannot manage lists and authorization | CT1 |  | Rel 6 | SIMPLE | RFC 4826
A SIP Event Package for Modification Events for XCAP Documents | ietf-simple-xcap-diff | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-data-req | Critical | Protocol for presence data manipulation | User cannot manage lists and authorization | CT1 | Presence | Rel 6 | SIMPLE | RFC 5874 | New RFC in May 2010
XCAP Usage for Publishing Presence Information | ietf-simple-xcap-pidf-manipulation-usage | COMPLETED | Definite- Solution to requirements in draft-ietf-simple-data-req | Critical | Protocol for presence data manipulation | Cannot support hard state requirements | CT1 |  | Rel 6 | SIMPLE | RFC 4827
Indicating User Agent Capabilities in SIP | ietf-sip-callee-caps | COMPLETED | Definite | Critical | Conferencing and multiple terminals | Cannot indicate conferencing capabilities | SA2 CT1 |  | Rel 6 | SIP | RFC 3840
Caller Preferences and Callee Capabilities for SIP | ietf-sip-callerprefs | COMPLETED | Definite | Critical | Conferencing and multiple terminals | Cannot indicate conferencing preferences and multiple terminals | SA2 CT1 |  | Rel 6 | SIP | RFC 3841
A Mechanism for Content Indirection in SIP Messages | ietf-sip-content-indirect-mech | COMPLETED | Definite- Solution to requirements in draft-ietf-sipping-content-indirect | Desirable | Content Indirection Mechanism | All content must be carried inline | CT1 | Other | Rel 6 | SIP | RFC 4483
The SIP “Join” Header | ietf-sip-join | COMPLETED | Possible | Nice to Have | Call Monitoring, etc. | These features not easily available | CT1 |  | Rel 6 | SIP | RFC 3911
SIP Extension for Event State Publication | ietf-sip-publish | COMPLETED | Possible– One solution to requirements in draft-ietf-simple-publish reqs | Critical | Protocol for composing state information | Presence Service not Available | CT1 |  | Rel 6 | SIP | RFC 3903
The SIP Referred-By Mechanism | ietf-sip-referredby | COMPLETED | Possible | Desirable | Call Transfer, Conferencing | Less efficient call transfers and conferencing | CT1 |  | Rel 6 | SIP | RFC 3892
The SIP “Replaces” Header | ietf-sip-replaces | COMPLETED | Possible | Nice to Have | Call Transfer | Less efficient call transfers | CT1 |  | Rel 6 | SIP | RFC 3891
Session Timers in the SIP | ietf-sip-session-timer | COMPLETED | Possible | Nice to Have | Clean up lost sessions | Possible memory leaks | CT1 |  | Rel 6 | SIP | RFC 4028
SIP Call Control –Conferencing for User Agents | ietf-sipping-cc-conferencing | COMPLETED | Definite | Critical | Conferencing | Conferencing Service not Available | CT1 | Conferencing | Rel 6 | SIPPING | RFC 4579
A SIP Event Package for Conference State | ietf-sipping-conference-package | COMPLETED | Definite | Critical | Conferencing | Conferencing Service not Available | CT1, CT3 | Conferencing | Rel 6 | SIPPING | RFC 4575
A Framework for Conferencing with SIP | ietf-sipping-conferencing-framework | COMPLETED | Definite | Critical | Conferencing | Conferencing Service not Available | CT1 | Conferencing | Rel 6 | SIPPING | RFC 4353
Extensible Markup Language (XML) Configuration Access Protocol (XCAP) Diff event package | ietf-sip-xcapevent | COMPLETED except for publication | Definite | Desirable | Presence | Cannot deliver profile info to terminal | CT1 24.141 24.229 24.523 24.623 | Presence | Rel 6 | SIP | RFC 5875 | New RFC in May 2010
A Framework to configure SIP UA in SIP deployments | sipping-config-framework | High | Definite | Desirable | Retrieval of service attachment info for subscription of IMS based PSS adn MBMS user service | UE cannot be notified when the service attachment information is modified | SA4 26.237 | IMS_PSS_MBMS_US_EXT | Rel 6 | SIPCORE | IESG Evaluation | Still in IESG evaluation and expected to pass once 4 discussion points are solved
Multiple-Recipient MESSAGE Requests in the Session Initiation Protocol (SIP) | ietf-sip-uri-list-message | COMPLETED | Definite | Desirable | Delivery of Message to multiple recipients | Unclear specifications for delivery to multiple recipients | CT1 | Messaging | Rel 6 | SIP | RFC 5365
Pre-Shared Key Ciphersuites for Transport Layer Security | ietf-tls-psk | COMPLETED | Definite | Desirable | Use of pre-shared keys for TLS | pre-shared keys for TLS not available | SA3 | Other | Rel 6 | TLS | RFC 4279
The TLS Protocol Version 1.1 | ietf-tls-rfc2246-bis | COMPLETED | Definite | Desirable | More secure presence | Must use TLS 1.0 | SA3 | Presence | Rel 6 | TLS | RFC 4346
Analysis of Ipv6 Transitionin 3GPP Networks | ietf-v6ops-3gpp-analysis | COMPLETED | Definite | Desirable | Identifies 3GPP Ipv6 transition scenarios (RFC not necessary) | 3GPP operators receive poor guidance on Ipv6 implementation strategies | SA2 CT3 |  | Rel 6 | V6OPS | RFC 4215
Transition Scenarios for 3GPP Networks | ietf-v6ops-3gpp-cases | COMPLETED | Definite | Desirable | Identifies 3GPP Ipv6 transition scenarios (RFC not necessary) | 3GPP operators receive poor guidance on Ipv6 implementation scenarios | SA2 CT3 |  | Rel 6 | V6OPS | RFC 3574
Introduction of new RADIUS attributes to limit user access by filtering | ietf-radext-filter-rules | COMPLETED | Definite | Desirable | NAS filtering | No NAS filtering in auth. response | CT4 (29.234) | WLAN | Rel 6 | RADEXT | RFC 4849
Integrity transform carrying roll-over counter | lehtovirta-srtp-rcc | COMPLETED | Definite | Critical | MBMS RollOver Counter | Loss of ROC sync makes MBMS session unusable | SA3 | MBMS | Rel6 | MSEC? | RFC 4771
A Session Identifier for the Session Initiation Protocol | sipcore-invfix | medium | definite | critical | Error in the specified handling of 200 OK response |  | CT1 24.229 | IMS2 | Rel-6 | SIPCORE | In progress | Publication requested
Essential correction for IPv6 ABNF and URI comparison in RFC3261 | sip-ipv6-abnf-fix | COMPLETED except for publication | definite | critical | abnf for IPv4-mapped IPv6 address |  | CT1 24.229 | IMS2 | Rel-6 | SIPCORE | RFC Ed Queue | Approved by IESG in May
It is getting time to remove Rel-6 dependencies from the list next time? (subject to invfix passing IESG)
Release 7 dependencies
Determining how and why the call arrived at the destination | ietf-sip-history-info | COMPLETED | Definite | Critical | Indication of possible redirects | User is not aware of possible redirections of incoming request. | CT1 | SS | Rel-7 | SIP | RFC 4244
Definition of P-User-Database P-header | camarillo-sipping-user-database | COMPLETED | Definite – (the requirement is definite, this is one solution) | Nice to have | Optimisation of Cx interface procedures | Less optimized and scalable Cx interface | SA2 | Other | Rel-7 | SIPPING | RFC 4457
SIP URIs for applications such as voice mail and interactive voice response | jennings-sip-voicemail-uri | COMPLETED | Definite |  | Service URIs for SIP connections towards voice mail or interactive voice recognitions systems |  | CT1 | NGN | Rel-7 | SIP | RFC 4458
Rejecting anonymous requests in SIP | sip-acr-code | COMPLETED | Definite | Critical | Anonymous SIP call rejection | No means to offer anonymous call rejection which is regulatory requirement | CT1, CT3 | NGN, MITE | Rel-7 | SIP | RFC 5079
Update of P-header definitions for 3GPP | drage-sipping-rfc3455bis | Medium | Definite | Critical | The use of several headers is updated: P-Associated URI, P-Charging-Function-Addresses, P-Charging-Vector, P-Access-Network-Info | Unclear proxy handling of P-Associated-URI, UA in the network cannot insert P-Charging-Function-Addresses and P-Charging-Vector and P-Access-Network-Info cannot be used with WLAN | CT1 24.229 | Other, WLAN (no explicit ref. to 3455bis, but the headers are used already) | Rel-7 | SIPPING | In progress | The draft has expired, and it is still needed by 3GPP. The editor of the draft needs to provide a new version (Tracking via CT action point)
DHCP mechanism to find the current location | geopriv-dhcp-civil | COMPLETED | Definite | Critical | Location of IMS emergency calls | no DHCP mechanism to locate IMS emergency calls | SA2 (23.167) | Emergency | Rel-7 | GEOPRIV | RFC 4776
Informing the network entity of the terminal's location | ietf-sipcore-location-conveyance | Low | Possible | Critical | Location of IMS emergency calls | No way to inform the network of the terminal's location | CT1 24.229 24.503 | Emergency | Rel-7 | SIPCORE | In Progress | CT1 #61 did the update to 24.229 but 24.503 reference to old draft-ietf-sip-location-conveyance still needs to be updated. How to progress the work in IETF? -> New version has been published and is progressing.
identifying an emergency call at session setup | ietf-ecrit-service-urn | COMPLETED | Possible | Critical | Identification of emergency session (SOS) | No way for the network to know that a session establishment is due to emergency | SA1, CT1 (22.101, 24.229) | Emergency | Rel-7 | ECRIT | RFC 5031
Host Identity namespace and protocol architecture | ietf-hip-arch | COMPLETED | Possible | Nice to have | Network composition feasibility study |  | SA1 (22.980) |  | Rel-7 |  | RFC 4423
Globally Routable UA URI | ietf-sip-gruu | COMPLETED | Possible | Critical | Definition of globally routable UA URI | Need to define a 3GPP specific routable URI | SA2 (23.808) | GRUU | Rel-7 | SIP | RFC 5627
Event package for GRUU | ietf-sipping-gruu-reg-event | COMPLETED | Possible | Critical | SUBSCRIBE and NOTIFY for GRUU events | Notification of GRUU state cannot be given | SA2 (23.808) | GRUU | Rel-7 | SIPPING | RFC 5628
Identifies a TLS related MiM attack | torvinen-http-digest-aka-v2 | COMPLETED | Possible | Nice to have | Example of one particular type of security attack | None | SA3 (33.801) | SEC | Rel-7 |  | RFC 4169
OCSP extensions to IKEv2 | myers-ikev2-ocsp | COMPLETED | Definite | Desirable | Checking of revocation status of certificates | The UE may not be able to check the status of certificates in all cases | SA3 (33.234) | WLAN | Rel-7 |  | RFC 4806
IKEv2 extensions to allow multiple authentications, even using different mechanisms | eronen-ipsec-ikev2-multiple-auth | COMPLETED | Definite | Critical | Multiple authentication to support private network access over WLAN | VPN access over WLAN cannot be done | SA3, CT3 (33.234, 29.161) | WLAN | Rel-7 |  | RFC 4739
Delivering requests on the existing connections established by UA through firewall or NAT | ietf-sip-outbound | COMPLETED | Definite | Critical | Multiple access and NAT traversal | NAT traversal does not work without this | CT1 (24.229) | GRUU | Rel-7 | SIP | RFC 5626
XML document format for expressing privacy preferences | ietf-geopriv-common-policy | COMPLETED | Definite | Critical | Privacy | GRUU does not work without this | CT3 (29.163) | FBI | Rel-7 | GEOPRIV | RFC 4745
Diameter application to perform AAA on QoS reservations | tschofenig-radext-qos | High | Definite | Desirable | QoS provisioning over WLAN | WLAN services can be authenticated and authorised, but there is no means to provide QoS classes | CT4 (29.234) | WLAN | Rel-7 | RADEXT | In Progress | The draft has expired and the editor needs to provide a new version.
Diameter attribute-value pairs (AVP) for filtering and QoS handling | ietf-dime-qos-attributes | COMPLETED | Definite | Desirable | 3GPP need for this draft is twofold. In Rel-7 it is needed for I-WLAN support of QoS mechanisms. In Rel-8 SAE uses it in interfaces that are needed for definition of attribute value pairs to convey QoS information between Diameter peers for interfaces that are needed for non-3GPP access | For I-WLAN part in Rel-7 the WLAN services can be authenticated and authorised, but AN’s QoS capabilities can not be sent. For Rel-8 SAE the attribute value pairs to convey QoS information between Diameter peers remains open or have to be defined within 3GPP | CT4 (29.234) | WLAN | Rel-7 | DIME | RFC 5777
New URI parameter to represent calling party category (CPC) | patel-dispatch-cpc-oli-parameter | High | Definite | Desirable | Including CPC URI parameter in SIP URI and Tel URI | The AS cannot provide the SS7 or ISUP calling party category CPC | CT1 (24.229) | FBI | Rel-7 | DISPATCH | In Progress | this draft replaces draft-mahy-iptel-cpc. The work is expected to progress in new mini-WG spun off from DISPATCH
Definition of P-Profile-Key P-header for SIP registrars and SIP proxies. The profile key corresponds to the destination SIP URI of a request | camarillo-sipping-profile-key | COMPLETED | Definite | Desirable | SIP proxies need a pointer to the user database and if the Public Service Identity (PSI) is wildcarded, then the proxy needs to index with P-Profile-Key instead | Wildcarded PSI does not work | CT1 (24.229) |  | Rel-7 | SIPPING | RFC 5002
Interactive Connectivity Establishment protocol for NAT traversal. | ietf-mmusic-ice | COMPLETED | Definite | Desirable | NAT traversal | NAT traversal does not work without this | CT1 (24.229) | FBI | Rel-7 | MMUSIC | RFC 5245 | New RFC
Simple Traversal Underneath NATs, i.e. updated version of NAT traversal protocol | ietf-behave-rfc3489bis | COMPLETED | Definite | Desirable | NAT traversal | NAT traversal does not work without this | CT1 (24.229) | FBI | Rel-7 | BEHAVE | RFC 5389
Defines NAT traversal for UDP using STUN | ietf-behave-turn | COMPLETED except for publication | Definite | Desirable | NAT traversal | NAT traversal does not work without this | CT1 (24.229) | FBI | Rel-7 | BEHAVE | RFC 5766 | New RFC
Definition of SIP media feature tag and option tag for UA to require the support of ICE by the registrar | ietf-sip-ice-option-tag | COMPLETED except for publication | Definite | Desirable | NAT traversal | NAT traversal does not work without this | CT1 (24.229) | FBI | Rel-7 | SIP | RFC 5768 | New RFC
New value for the "dialstring" parameter to allow encoding of dial string to SIP URI (as Tel-URI cannot represent a dial string) | rosen-iptel-dialstring | COMPLETED | Definite | Desirable | Handling of dial strings in telephony and IMS emergency calls | No means to encode dial string in Tel-URI | CT1 (24.229) | MTSI, Emergency | Rel-7 |  | RFC 4967
Creation of conference using SIP URI-list contained in INVITE | ietf-sip-uri-list-conferencing | COMPLETED | Definite | Desirable | Establishment of ad hoc conferences with multple remote parties | Ad hoc conferences cannot be supported | CT1 (24.229, 24.147) | Conferencing | Rel-7 | SIP | RFC 5366
SIP extension for early media authorization | ejzak-sipping-p-em-auth | COMPLETED | Definite | Desirable | Early media authorization | Early media handling cannot be specified | CT1 (24.229) | IMSProtoc | Rel-7 | SIPPING | RFC 5009
P-Answer-State header extension to SIP for OMA push to talk | allen-sipping-poc-p-answer-state-header | COMPLETED | Definite | Desirable | PoC functionality for UE and AS roles | Not possible to specify the UE answering mode | CT1 (24.229) | IMSProtoc | Rel-7 | SIPPING | RFC 4964
Definition of EAP-TLS which includes support for certificate-based mutual authentication and key derivation | draft-simon-emu-rfc2716bis | COMPLETED | Definite | Desirable | Support of IMS emergency calls without UICC in I-WLAN | UICC-less emergency calls are not possible | SA3 (33.234) | WLAN | Rel-7 |  | RFC 5216
Definition of P-Preferred-Service and P-Asserted-Service headers for service identification | drage-sipping-service-identification | High | Definite | Critical | Indication of IMS communication services | IMS Service ID will not work | CT1 (24.229) | ServID | Rel-7 | SIPPING | IESG evaluation | What is the relationship between draft-drage-sipping-service-identification and draft-ietf-sipping-service-identification which is already in RFC editor's queue?
Definition of MIME type sub-types to identify accurately an application in the user agent | rosenberg-sip-app-media-tag | COMPLETED | Definite | Desirable | Indication of IMS communication services | feature tag usage is not defined | CT1 (24.229) | IMSProtoc | Rel-7 | SIP | RFC 5688
Namespace identifier for URN resources published by 3GPP | monrad-sipping-3gpp-urn-namespace | COMPLETED | Definite | Desirable | URN definitions for key request/response between the UE and NAF and ME - UICC | Need to define 3GPP specific URNs | SA3 33.110, 33.259 | PNM | Rel-7 | SIPPING | RFC 5279
Extensions to the REFER method so that multiple resources can be referenced in single request | ietf-sip-multiple-refer | COMPLETED | Definite | Desirable | Optionally supported if REFER supported | No multiple references in single request | CT1 24.229 | IMSProtoc | Rel-7 | SIP | RFC 5368
Subscription to list of resources in a single request | ietf-sip-uri-list-subscribe | COMPLETED | Definite | Desirable | Subscription to Resource-Contained Resource Lists in SIP | Need to subscribe to each resource individually | CT1 24.229 | IMSProtoc | Rel-7 | SIP | RFC 5367
Extension to allow SDP to capability negotiation framework that allows negotiation of multiple transport protocols or attributes. | ietf-mmusic-sdp-capability-negotiation | COMPLETED Except for publication | Definite | Desirable | SDP capability negotiation mechanism | Calls from terminals supporting Audio-Visual Profile with Feedback (AVPF) to non-AVPF terminals will be rejected | CT1 24.229 24.292 SA4 26.114 | IMSProtoc | Rel-7 | MMUSIC | RFC Ed queue | Approved by IESG in March 2010
Mechanism to negotiate the transfer of one or more files between two endpoints by using SIP offer/answer | ietf-mmusic-file-transfer-mech | COMPLETED | Definite | Desirable | Using messaging service for file transfer | No SIP/SDP mechanism to negotiate the properties of transferred file | CT1 24.247 | Messaging | Rel-7 | MMUSIC | RFC 5547
URI parameter for marking SIP registrations for emergency services | patel-ecrit-sos-parameter | High | Definite | Critical | Emergency registration | Not possible to distinguish emergency registration from normal one | CT1 24.229 | EMC1 | Rel-7 | ECRIT | In progress | I-D tracker indicates no progress since Feb 2010 (tracking via CT action point)
Release 8 dependencies
IPv4 and IPv6 tunneling for dual stack | ietf-mext-nemo-v4traversal | COMPLETED except for publication | Definite | Critical | PDN GW acts as HA for DSMIP UE | No DSMIP solution | SA2,CT1, CT4 23.402, 24.303 29.275 | SAE | Rel-8 | MEXT | RFC 5555
DAI parameter for 'tel' URI | yu-tel-dai | Medium | Definite | Desirable | Handling of cic and dai parameters in tel-URI | Preferred circuit carrier access and preferred circuit carrier selection does not work as the related BGCF and MGCF procecures cannot be specified | CT1 24.229 | PktCbl-Intw | Rel-8 | DISPATCH | In progress | New draft published in April 2010 (but the I-D tracker still indicates it as DEAD)
Proxy Mobile IPv6 | ietf-netlmm-proxymip6 | COMPLETED | Definite | Critical | PMIP6 mobility for non-3GPP access | No PMIP6 | SA2, CT1, CT4 23.402, 24.801, 29.275 | SAE | Rel-8 | NETLMM | RFC 5213
IPv4 support for proxy mobile IPv6 | ietf-netlmm-pmip6-ipv4-support | COMPLETED | Definite | Critical | IPv4 address allocation via DHCP for non-3GPP access | No PMIP6 | SA2 23.402 CT4 29.275 | SAE | Rel-8 | NETLMM | RFC 5844 | New RFC
Mobile IPv6 bootstrapping in split scenario | ietf-mip6-bootstrapping-split | COMPLETED | Definite | Desirable | IPv6 bootstrapping |  | CT1 24.302 | SAE | Rel-8 | MEXT | RFC 5026
IP mobility support for IPv4, revised | ietf-mip4-rfc3344bis | COMPLETED except for publication | Definite | Desirable | IPv4 mobility for non-3GPP access | MIP4 does not work for non-3GPP access. The whole 24.304 has been systematically written based on rfc3344bis | CT1 24.801 24.304 | SAE | Rel-8 | MIP4 | RFC Ed queue | Approved by IESG in April 2010
IPv6 autoconfiguration | ietf-ipv6-rfc2462bis | COMPLETED | Definite | Critical | Assignment of UI IPv6 address prefix | Stateless IPv6 address autoconfiguration does not work | SA2 23.401 | SAE | Rel-8 |  | RFC 4862
DHCP option for home network information discovery in MIP6 | ietf-mip6-hiopt | COMPLETED except for publication | Definite | Desirable | Home Agent discovery via DHCPv6 | Need some other mechanism for the HA discovery | CT1 24.801, 24.303 | SAE | Rel-8 | MEXT | RFC Ed queue | Approved by IESG in May 2008
Mobility header home agent switch message | ietf-mip6-ha-switch | COMPLETED | Definite | Desirable | PDN GW reallocation | Cannot preserve IP address in some handover scenarios over S2c | SA2 23.402 | SAE | Rel-8 | MEXT | RFC 5142
Support of mobility access gateway and local mobility anchor to Diameter server interaction | korhonen-dime-pmip6 | COMPLETED | Definite | Desirable | Download of mobility and access authentication related parameters at ePDG-AAA | No bearer control on untrusted non-3GPP access technologies | SA2 23.402 | SAE | Rel-8 | DIME | RFC 5779
Diameter mobile IPv6: Support for network access server to Diameter server interaction | ietf-dime-mip6-integrated | COMPLETED except for publication | Definite | Desirable | Download of mobility and access authentication related parameters at ePDG-AAA | No bearer control on untrusted non-3GPP access technologies | SA2 23.402 | SAE | Rel-8 | DIME | RFC 5447
Service selection for MIPv4 | korhonen-mip4-service | COMPLETED except for publication | Definite | Desirable | MIP4 FA CoA procedures for non-3GPP access interworking | Additional connections to another PDN does not work | SA2 23.402 CT1 24.304 | SAE | Rel-8 | MIP4 | RFC 5446
Binding revocation for IPv6 mobility | ietf-mext-binding-revocation | COMPLETED except for publication | Definite | Desirable | Termination of mobility session between UE and mobility anchor | Network initiated detach procedures for PMIP6 and DSMIP6 do not work | SA2 23.402 CT4 29.275 | SAE | Rel-8 | MEXT | RFC Ed queue
GRE key option for Proxy mobile IPv6 | muhanna-netlmm-grekey-option | COMPLETED except for publication | Definite | Desirable | Negotiation of IP version encapsulation mode and Generic Routing Encapsulation (GRE) key for marking the flows | MIP6 tunneling and GRE does not work at PMIP interfaces S2, S5 and S8 | SA2 23.402 CT4 29.275 | SAE | Rel-8 | NETLMM | RFC Ed queue
Mechanism whereby endpoints can request Instand Message Disposition Notifications (IMDN), including delivery, processing, and read-notifications for page-mode message | ietf-simple-imdn | COMPLETED except for publication | Definite | Desirable | Progress notifications on the SIP side of SIP and SMS message interworking | Interoperability still works, but the notifications cannot be given on the SIP side of the interworking | SA2 23.204 CT3 29.311 | Messaging interworking | Rel-8 | SIMPLE | RFC 5438
Interaction between the Home Agent and the Diameter Server of the Mobile Service Provider (MSP) while bootstrapping mobile IPv6 operation | ietf-dime-mip6-split | COMPLETED except for publication | Definite | Desirable | definition of Application-Id between Diameter nodes | Application-Ids need to be defined in 3GPP | CT4 29.273 | SAE | Rel-8 | DIME | RFC 5778
Example call flows of race conditions in SIP and best practices to handle them | ietf-sipping-race-examples | COMPLETED | Definite | Desirable | Describe race conditions for call clearing | Problmens in RFC 3261 related to race conditions remain open | CT4 29.231 | ExtSIPI | Rel-8 | SIPPING | RFC 5407
Transport of telephony User-User-Information in SIP messages | johnston-dispatch_sip-cc-uui | Medium | Definite | Desirable | NGN needs to support UUS during call | No means to transfer UUS data to user | CT1 24.229 | UUSIW | Rel-8 | DISPATCH | In progress | draft-johnston-dispatch-sip-cc-uui has replaced draft-johnston-sipping-cc-uui. CT1 needs to update 24.229.
The use of the reason header field in SIP responses | jesske-dispatch-reason-in-responses | Medium | Definite | Desirable | Conveying the telephony reason code in SIP (reject) message for interworking with the existing PSTN/ISDN networks | Error handling at SIP level cannot take into account all real life telephony error cases | CT1 24.229 CT3 29.163 | FBI | Rel-8 | DISPATCH | In progress | draft-jesske-sipping-etsi-ngn-reason is replaced with draft-jesske-dispatch-reason-in-responses. The editor has been requested to split out the protocol changes from the use cases more clearly
DHCP options to contain a list of domain names or IP addresses of ANDSF servers | das-mipshop-andsf-dhcp-options | Medium | Definite | Desirable | ANDSF discovery by the UE to find out the domain or IP address of the home ANDSF | Need to pre-configure the home ANDSF properties by other means | CT1 24.302 | SAE | Rel-8 | MIPSHOP | In progress | Agreed to proceed as AD sponsored draft (Jari Arkko). MIPSHOP review was requested and that has now been passed. 3GPP has documented how the draft is used.
Definition of P-Served-User P-header to convey the information on the served user identity across ISC | vanelburg-sipping-served-user | COMPLETED | Definite | Desirable | Indication of the served user in call forwarding | Call forwarding not handled properly | CT1 24.229 | IMSProtoc2 | Rel-8 | SIPPING | RFC 5502
Justification and definition of the indication of private network so that private network traffic can be distinguished from the other private networks and public network traffic | vanelburg-sipping-private-network-ind | Medium | Definite | Desirable | Indication of private network traffic to apply processing rules specific to that private network | Private network specific processing rules are not possible (or at least no indication in signalling when to apply them and when not) | CT1 24.229 | IMS_Corp | Rel-8 | DISPATCH | In progress | new draft name draft-vanelburg-dispatch-private-network-ind and the draft has expired. Does CT1 still need to write a CR to update to new draft? The authors need to drive the work in DISPATCH
Recommendations on call completion interoperability | ietf-bliss-call-completion | High | Definite | Critical | No reference yet, but likely to be needed for CCBS work. Allows calling user to be notified when the called user becomes available. | No CCBS in Rel-8 or 3GPP has to define suspend and resume procedures in 3GPP TS | CT1 24.642 | CCBS | Rel-8 | BLISS | In progress | Expired, the editor needs to provide a new version (tracking via CT action point)
Heartbeat mechanism between Mobile Access Gateway and Local Mobility Anchor to detect the failure of peer entity rapidly | netlmm-pmipv6-heartbeat | COMPLETED except for publication | Definite | Desirable | Path management procedures to see if the peer GTP entity is still alive | The heartbeat mechanism currently existing in GTP cannot be provided in PMIPv6 | CT4 29.275 | SAE | Rel-8 | NETLMM | RFC Ed queue | draft-devarapalli-netlmm-pmipv6-heartbeat was replaced by draft-ietf-netlmm-pmipv6-hearbeat which has been in RFC editors queue since April 2009
Private extension to the Session Initiation Protocol (SIP) for debugging | dawes-sipping-debug | Medium | Definite | Desirable | IMS tracing for troubleshooting and testing purposes | IMS tracing does not work | CT1 24.229 | IMS Trace | Rel-8 | SIPPING | In progress | The old two draft-dawes-sipping-debug- drafts are merged into this one and CT1 is already referencing to the new version. It was requested by Mary that this work should continue in DISPATCH
New EAP method, EAP-AKA' as a revision of EAP-AKA with binding of derived keys with the name of the access network | arkko-eap-aka-kdf | COMPLETED | Definite | Desirable | Security procedures for trusted CDMA 2000 take access network identity as one parameter for key derivation | Key derivation for trusted CDMA 2000 does not work | CT1 24.302 CT4 23.003 | SAE | Rel-8 |  | RFC 5448
Registration of new disposition-types for content-disposition header that apply to application / 3gpp-ims+xml body used in 3GPP | bakker-sipping-3gpp-ims-xml-body-handling | Medium | Definite | Desirable | Needed for IANA registration of 3gpp-alternative-service and 3gpp-service-info | IANA registration is not possible | CT1 24.229 | IMSProtoc2 | Rel-8 | SIPPING | In progress | The draft has expired, but the author intends to resubmit it (in which group?). There never was a reference from 24.229 to this draft, but the draft is needed to for IANA registration. Should the IANA registration be done via new version of the draft or via reference to 3GPP specification? This document will progress as AD sponsored document (Cullen Jennings)
Event package for subscription and notification on diversions of incoming sessions | avasarala-dispatch-comm-div-notification | High | Definite | Desirable | Additional info on diversions for the receiver of SIP call | No notification of re-direction or forwarding towards the recipient of terminating sessions | CT1 24.504, 24.604 | MAINT_R2 | Rel-8 | DISPATCH | In progress | New draft version in April 2010
New IANA Diameter command codes for vendor-specific Diameter applications for 3GPP EPS | jones-3gpp-dime-eps-command-codes | COMPLETED | Definite | Critical | Diameter command codes registered by IANA | This dependency is towards the IANA registration of the Command Codes and MME implementation is not possible without them. SAE procedures between MME and HSS cannot work without the command code definitions | CT4 29.272 | SAE | Rel-8 | DIME | RFC 5516
Reduced size RTCP packets via change of rules for creating compound packets as outlined in RFC 3550. This document updates RFC 3550, 3711, 4585 | ietf-avt-rtcp-non-compound | COMPLETED | Definite | Desirable | Reduced packet size. This Rel-8 change was also brought back to Rel-7 for compatibility reasons | No benefit from reduced packet size | SA4 26.114 | MTSI-MHI | Rel-8 |  | RFC 5506
Method of home agent information discovery for the integrated scenario where the mobility service and network access are authorized by the same server | ietf-mip6-bootstrapping-integrated | COMPLETED except for publication | Definite |  | MIP6 home agent discovery | IPv6 bootstrapping in integrated scenario needs this | CT4 29.273 | SAE | Rel-8 |  | RFC Ed queue | This draft has been in RFC editor's queue since April 2008. REF: draft-ietf-mip6-hiopt, MISSREF: draft-ietf-mip6-radius
Reserves EMSK (Extended Master Session Key) for the sole purpose of deriving root keys. Also definition of the use of the root keys and separation between root keys. | ietf-hokey-emsk-hierarchy | COMPLETED | Definite | Desirable | Mobile IP root key generation |  | SA3 33.402 | SAE | Rel-8 |  | RFC 5295
Protocol to allow nodes to remain reachable while moving in the IPv6 Internet. Binding of IPv6 node's home address with its care-of address and to route packets directly to care-of address. | mext-rfc3775bis | High | Definite | Desirable | Detection of HA binding error or unrecognised mobility header | Need to use RFC 3775 as it stands | CT1 24.303 | SAE | Rel-8 | MEXT | In progress | New draft version has been published in October 2009 to cater for the WG LC comments (Johnson, Perkins, Arkko), but no progress since then
Definition of some URNs for support of ringback tones and semantic indications without tied rendering | alexeitsev-bliss-alert-info-urns | high | Definite | Desirable | used to inform the caller and the AS (when AS does not detect network determined user busy) about the call-waiting service situation on the callee side. | The caller is unaware of the call waiting situation on the callee side, and thus degrades user experience. Caller cannot decide how to proceed with the call. | CT1 24.292 24.615 | ICS | Rel-8 | DISPATCH | In progress | New name draft-liess-dispatch-alert-info-urns, but no progress since 2009. Expired in July 2009
Extension of SDP negotiation to media types and their associated parameters | ietf-mmusic-sdp-media-capabilities | High | Definite | Desirable | extensions to SDP capability negotiation to enable ICS UE-based traminating access domain selection with audio streams over CS bearers with SIP service control | ICS UE based T-ADS will not be possible when SCC AS uses capability negotiations to allow UE to choose whether audio media is streamed over CS or PS bearers | CT1 24.292 | ICS | Rel-8 | MMUSIC | In progress | The draft has expired and it is waiting for editor to provide a new version.
Use cases, requirements and protocol extensions for using SIP offer/answer model for establishing audio media streams over CS PSTN | ietf-mmusic-sdp-cs | High | Definite | Desirable | ICS enables a session to be estabslished and controlled in SIP with audio speech media on a CS bearer | establishment of SIP sessions with audio on CS bearer will not be possible. ICS sessions with CS audio cannot be centralized and controlled in IMS. | CT1 24.292 | ICS | Rel-8 | MMUSIC | In progress | The author has received comments on the current drafts and intends to provide new version for IETF #77
Extension of SDP negotiation framework to allow E2E negotiation of media titles, connection data and media bandwidth | garcia-mmusic-sdp-misc-cap | High | Definite | Desirable | extensions to SDP capability negotiation to enable ICS UE-based traminating access domain selection with audio streams over CS bearers with SIP service control | ICS UE based T-ADS will not be possible when SCC AS uses capability negotiations to allow UE to choose whether audio media is streamed over CS or PS bearers | CT1 24.292 | ICS | Rel-8 | MMUSIC | In progress | The author has received comments on the current drafts and intends to provide new version for IETF #77. Overlap with another draft (draft-boucadair-mmusic-ccap) has been identified and the next version is expected to remove that overlap
SIP INFO method and mechanism for defining, negotiating and exchanging Info Packages that use the INFO method. This draft is intended to obsolete RFC 2976 | ietf-sipcore-info-events | High | Definite | Desirable | Application information for AoC | Got to live with the shortcomings of RFC 2976 | CT1 24.229 | ICS | Rel-8 | SIPCORE | IESG evaluation | IESG evaluation in May 2010. One discussion point still to be solved before the draft can pass IESG.
URN namespace and sub-namespaces for GSMA and IMEI and IMEISV | montemurro-gsma-imei-urn | High | Definite | Desirable | URN format for using the IMEI as unique sip.instance media feature tag value is defined | ICS and session continuity cannot work reliably | CT4 23.003 | ICS | Rel-8 |  | In Progress | The draft is indicated as dead in I-D tracker. The next version -05 has already been drafted but it needs the IMEI version indicator to allow possible IMEI syntax change in the future. Expired in April 2009
Re-direct mechanism for IKEv2 to redirect a VPN client to attach to another gateway | ietf-ipsecme-ikev2-redirect | COMPLETED | Definite | Desirable | Home Agent reallocation | No specified mechanism for HA reallocation | CT1 24.303 | SAES | Rel-8 |  | RFC 5685
Define Diameter command code value ranges for different purposes and consequently different IANA registration processes | ietf-dime-diameter-cmd-iana | COMPLETED | Definite | Critical | IANA registration process for new Diameter command codes | New command codes specified in 3GPP for Rel-8 | CT4 29.173 | SAES | Rel-8 | DIME | RFC 5719
TCP Candidates with Interactive Connectivity Establishment (ICE) | mmusic-ice-tcp | medium | definite | critical | nat traversal |  | CT1 24.229 |  | Rel-8 | MMUSIC | In progress | Expired
Indication of support for keep-alive | sipcore-keep | medium | definite | critical | nat traversal, maintain nat binding | Keepalive does not work across NAT | CT1 24.229 | IMSProtoc2 | Rel-7 | SIPCORE | In progress | New draft in May 2010
SIP Interface to VoiceXML Media Services | mediactrl-vxml | COMPLETED | definite | desirable | Media Control AS control of MRFC tones and announcements |  | CT1 24.229 | MRFC | Rel-8 MRFC | MEDIACTRL | RFC 5552
Media Control Channel Framework | mediactrl-sip-control -framework | medium | definite | desirable | Media Control AS control of MRFC tones and announcements |  | CT1 24.229 | MRFC | Rel-8 MRFC | MEDIACTRL | IESG evaluation | Revised ID is needed
An IVR Control Package for the Media Control Channel Framework | mediactrl-ivr- control-package | medium | definite | desirable | Media Control AS control of MRFC tones and announcements |  | CT1 24.229 | MRFC | Rel-8 MRFC | MEDIACTRL | IESG evaluation | Revised ID is needed
A Mixer Control Package for the Media Control Channel Framework | mediactrl-mixer- control-package | medium | definite | desirable | Media Control AS control of MRFC trancoding |  | CT1 24.229 | MRFC | Rel-8 MRFC | MEDIACTRL | IESG evaluation | Revised ID is needed
Release 9 dependencies
Mobile Internet KEY mangament (MIKEY) extension to add the concetp of tickets and centralised key distribution operating mode | mattson-mikey-ticket | high | Definite | Critical | Centralised key management in 3GPP architecture | MIKEY media security is not possible in 3GPP architecture | SA3 33.328 CT1 24.229 | MEDIASEC | Rel-9 |  | IESG evaluation | IESG evaluation in May 2010
Extension of Lightweight Directory Access Protocol (LDAP) to allow a number of update operations in single transaction | zeilenga-ldap-txn | COMPLETED | Definite | Critical | Support of transactions on Ud interface. This draft is intended to be progressed as individual submission instead of a WG item. | 3GPP has to specify Ud transactions on their own | CT4 29.335 | UDC | Rel-9 |  | RFC 5805
Session identifier for SIP | kaplan-dispatch-session-id | Medium | Definite | Desirable | Call correlation for O&M purposes, call service correlation | O&M procedures are more complicated, E2E session correlation does not work in all cases | CT1 24.229 | IMSProtoc3 | Rel-9 | DISPATCH | In progress
Extension of security mechanism negotiation to media plane | dawes-dispatch-mediasec-parameter | high | Definite | Desirable | IMS media security | Not possible to set up IMS media security | SA3 33.328 | MEDIASEC | Rel-9 | DISPATCH | In progress | New addition to the list