## Work_plan_3gpp
ID | Unique_ID | Name | Acronym | Outline Level | Release | Resource Names | Start | Finish | % Complete | Hyperlink | Status Report | WI rapporteur name | WI rapporteur e-mail | Notes | Impacted TSs and TRs | TSG approved | PCG approved | TSG stopped | PCG stopped | Created | last modif
1 | 0 | Work Plan 3GPP version June 11th 2021 |  | 1 | Rel-18 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2015-01-15 | 2015-03-05
2 | 0 | Includes the WIDs proposed by CT and SA WGs to TSG#92e |  | 1 | Rel-18 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2018-03-15 | NA
3 | 0 | Next milestones: Rel-17 St.2: June 21. St. 3: March 22. Rel-18: St.1: Dec. 2021 |  | 1 | Rel-18 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2015-08-12 | NA
4 | 0 |  |  | 1 | Rel-18 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2015-08-12
5 | 0 | --- RELEASE 18 --- | - | 1 | Rel-18 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
6 | 0 | Rel-18 normative work | - | 1 | Rel-18 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
7 | 920036 | Evolution of IMS Multimedia Telephony Service | eMMTEL | 1 | Rel-18 |  | Thu 19/09/19 | Sun 12/12/21 | 76% | SP-210519 |  | Hu Yue, China Mobile, huyueyjy@chinamobile.com |  |  | 22.261;22.173 |  |  |  |  | Fri 11/06/21 | NA
8 | 850042 | Study on evolution of IMS multimedia telephony service | FS_MMTELin5G | 2 | Rel-18 | S1 | Thu 19/09/19 | Wed 08/09/21 | 95% | SP-190836 |  | Yan Di, China Mobile, yandi@chinamobile.com |  | ; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95 | New ; 22.873 | 85 |  |  |  | Fri 13/09/19 | Fri 11/06/21
9 | 920029 | Stage 1 of Evolution of IMS Multimedia Telephony Service | eMMTEL | 2 | Rel-18 | S1 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210519 |  | Hu Yue, China Mobile, huyueyjy@chinamobile.com |  |  | 22.261;22.173 |  |  |  |  | Fri 11/06/21 | NA
10 | 920037 | AI/ML model transfer in 5GS | AMMT | 1 | Rel-18 |  | Fri 06/12/19 | Sun 12/12/21 | 71% | SP-210520 |  | Jia SHEN, OPPO, sj@oppo.com |  |  | 22.261 |  |  |  |  | Fri 11/06/21 | NA
11 | 860009 | Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS | FS_AMMT | 2 | Rel-18 | S1 | Fri 06/12/19 | Fri 11/06/21 | 95% | SP-191040 |  | Jia SHEN, Oppo . | sj@oppo.com | 28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95 | 33.852 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
12 | 920030 | Stage 1 of AMMT | AMMT | 2 | Rel-18 | S1 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210520 |  | Jia SHEN, OPPO, sj@oppo.com |  |  | 22.261 |  |  |  |  | Fri 11/06/21 | NA
13 | 920038 | 5G Networks Providing Access to Localized Services | PALS | 1 | Rel-18 |  | Wed 16/09/20 | Wed 08/09/21 | 71% | SP-210522 |  | Lola Awoniyi-Oteri, qualcomm | oawoniyi@qti.qualcomm.com |  | 22.261 |  |  |  |  | Fri 11/06/21 | NA
14 | 890023 | Study on PALS | FS_PALS | 2 | Rel-18 | S1 | Wed 16/09/20 | Fri 11/06/21 | 95% | SP-200799 |  | Jack Nasielski | jackn <at> qti.qualcomm.com | 5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95 | 22.844 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
15 | 920031 | Stage 1 of PALS | PALS | 2 | Rel-18 | S1 | Fri 11/06/21 | Wed 08/09/21 | 0% | SP-210522 |  | Lola Awoniyi-Oteri, qualcomm | oawoniyi@qti.qualcomm.com |  | 22.261 |  |  |  |  | Fri 11/06/21 | NA
16 | 920039 | Smart Energy and Infrastructure | SEI | 1 | Rel-18 |  | Thu 25/06/20 | Sun 12/12/21 | 59% | SP-210523 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn |  | 22.104;22.261 |  |  |  |  | Fri 11/06/21 | NA
17 | 880038 | Study on 5G Smart Energy and Infrastructure | FS_5GSEI | 2 | Rel-18 | S1 | Thu 25/06/20 | Fri 11/06/21 | 90% | SP-200574 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn | 28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90 | 22.867 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
18 | 920032 | Stage 1 of Smart Energy and Infrastructure | SEI | 2 | Rel-18 | S1 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210523 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn |  | 22.104;22.261 |  |  |  |  | Fri 11/06/21 | NA
19 | 910038 | Enhanced Access to and Support of Network Slice | EASNS | 1 | Rel-18 |  | Thu 25/06/20 | Sun 12/09/21 | 100% | SP-210210 |  | Chun, SungDuck, LG Electronics Inc. | sungduck.chun@lge.com |  | 22.261 |  |  |  |  | Thu 18/03/21 | NA
20 | 880035 | Study on EASNS | FS_EASNS | 2 | Rel-18 | S1 | Thu 25/06/20 | Wed 17/03/21 | 100% | SP-200571 |  | Chun, SungDuck, LG Electronics Inc | sungduck.chun@lge.com | 12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100 | 22.835 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
21 | 910032 | Stage 1 for EASNS | EASNS | 2 | Rel-18 | S1 | Thu 18/03/21 | Sun 12/09/21 | 100% | SP-210210 |  | Chun, SungDuck, LG Electronics Inc. | sungduck.chun@lge.com | ; 11/6/21: 0%->100 | 22.261 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
22 | 910039 | 5G Timing Resiliency System | 5TRS | 1 | Rel-18 |  | Thu 25/06/20 | Sun 12/09/21 | 100% | SP-210211 |  | Betsy Covell, Nokia | betsy.covell@nokia.com |  | 22.261; 22.104 |  |  |  |  | Thu 18/03/21 | NA
23 | 880037 | Study on 5TRS | FS_5TRS | 2 | Rel-18 | S1 | Thu 25/06/20 | Fri 12/03/21 | 100% | SP-200573 |  | Betsy Covell, Nokia | betsy.covell@nokia.com | 28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100 | 22.878 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
24 | 910033 | Stage 1 for 5TRS | 5TRS | 2 | Rel-18 | S1 | Thu 18/03/21 | Sun 12/09/21 | 100% | SP-210211 |  | Betsy Covell, Nokia | betsy.covell@nokia.com | ; 11/6/21: 0%->100 | 22.261; 22.104 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
25 | 910040 | Ranging-based Service | Ranging | 1 | Rel-18 |  | Thu 25/06/20 | Sat 12/06/21 | 100% | SP-210212 |  | Xiaowei jiang, Xiaomi | jiangxiaowei@xiaomi.com |  | 22.261 |  |  |  |  | Thu 18/03/21 | NA
26 | 880039 | Study on Ranging | FS_Ranging | 2 | Rel-18 | S1 | Thu 25/06/20 | Fri 11/06/21 | 100% | SP-200575 |  | Xiaowei jiang | jiangxiaowei@xiaomi.com | 28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100 | 22.855 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
27 | 910034 | Stage 1 for Ranging | Ranging | 2 | Rel-18 | S1 | Thu 18/03/21 | Sat 12/06/21 | 100% | SP-210212 |  | Xiaowei jiang, Xiaomi | jiangxiaowei@xiaomi.com | ; 11/6/21: 0%->100 | 22.261 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
28 | 910036 | Low Power High Accuracy Positioning for industrial IoT scenarios | LPHAP | 1 | Rel-18 | S1 | Thu 18/03/21 | Fri 11/06/21 | 100% | SP-210216 |  | Yuan Wang, Huawei | wangyuan5@huawei.com | ; 19/3/21: 0%->40; 11/6/21: 40%->100 | 22.104; 22.261 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
29 | 890024 | Subscriber-aware Northbound API access | SNA | 1 | Rel-18 | S1 | Tue 01/09/20 | Thu 17/09/20 | 100% | SP-200797 |  | Minokuchi, Atsushi, NTT DOCOMO | minokuchi at nttdocomo dot com |  | 22.261 | 89 | 45 |  |  | Fri 11/09/20 | NA
30 | 900028 | Support for Service Function Chaining | SFChain | 1 | Rel-18 | S1 | Fri 04/12/20 | Fri 12/03/21 | 100% | SP-201040 |  | Ellen Liao; Intel | ellen.c.liao at intel.com | 22.261; 22.101; 22.115 ; 5/12/20: 0%->100 |  | 90 |  |  |  | Fri 04/12/20 | Sat 05/12/20
31 | 910035 | Data Integrity in 5GS | DI_5G | 1 | Rel-18 | S1 | Thu 18/03/21 | Thu 25/03/21 | 100% | SP-210213 |  | Qun wei, China Unicom | Weiqun5 <at> chinaunicom.cn | ; 19/3/21: 0%->100 | 22.261 |  |  |  |  | Thu 18/03/21 | Fri 19/03/21
32 | 920033 | Signal level Enhanced Network Selection | SENSE | 1 | Rel-18 | S1 | Fri 11/06/21 | Wed 08/09/21 | 40% | SP-210525 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@magenta.at | ; 11/6/21: 0%->40 | 22.011 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
33 | 920034 | 5G system with satellite access to Support Control and/or Video Surveillance | SCVS | 1 | Rel-18 | S1 | Fri 11/06/21 | Wed 08/09/21 | 0% | SP-210527 |  | Dong Chen, Xiaomi | chendong7@xiaomi.com |  | 22.261 |  |  |  |  | Fri 11/06/21 | NA
34 | 920035 | 5G system with satellite backhaul | 5GSATB | 1 | Rel-18 | S1 | Fri 11/06/21 | Sun 20/06/21 | 100% | SP-210528 |  | Xu Hui, CATT | xuhui@catt.cn | ; 11/6/21: 0%->100 | 22.261 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
35 | 920042 | (Small) Technical Enhancements and Improvements for Rel-18 | TEI18 | 1 | Rel-18 |  | Fri 12/03/21 | Fri 10/03/23 | 0% | [7 empty] | 43 |  |  | Mon 15/06/15 | Mon 15/06/15
36 | 920003 | Lawful Interception Rel-18 | LI18 | 1 | Rel-18 | S3LI | Fri 12/03/21 | Fri 10/03/23 | 0% | SP-210300 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com |  | 33.128;33.127;33.126;33.108;33.107 |  |  |  |  | Fri 11/06/21 | NA
37 | 0 | Rel-18 Studies on Railways | - | 1 | Rel-18 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
38 | 850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 1 | Rel-18 | S1 | Thu 19/09/19 | Wed 08/09/21 | 30% | SP-190838 |  | Han, Andrew Min-gyu, Hansung University | andyhan(at)hansung(dot)ac(dot)kr | ; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30 | New ; 22.890 | 85 | 43 |  |  | Fri 13/09/19 | Fri 19/03/21
39 | 880036 | Study on Off-Network for Rail | FS_OffNetRail | 1 | Rel-18 | S1 | Thu 25/06/20 | Fri 10/12/21 | 50% | SP-200572 |  | Guillaume Gach | Ext.gach <at> uic.org | 28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50 | 22.99 | 88 | 45 |  |  | Thu 25/06/20 | Fri 19/03/21
40 | 880034 | Study of Interconnection and Migration Aspects for Railways | FS_IRail | 1 | Rel-18 | S6 | Thu 25/06/20 | Thu 16/09/21 | 30% | SP-200336 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | 13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30 | 23.700-90 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
41 | 900026 | Study on FRMCS Evolution | FS_eFRMCS | 1 | Rel-18 | S1 | Fri 04/12/20 | Fri 10/12/21 | 20% | SP-201038 |  | Guillaume Gach; UIC | Guillaume Gach; gach <at> uic.org | 22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20 |  | 90 |  |  |  | Fri 04/12/20 | Fri 19/03/21
42 | 0 | Rel-18 other Studies | - | 1 | Rel-18 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
43 | 920022 | Study on Standardising Automated Certificate Management in SBA | FS_ACM_SBA | 1 | Rel-18 | S3 | Fri 11/06/21 | Sun 12/06/22 | 0% | SP-210419 |  | BT, Niraj Rathod | Niraj.rathod@bt.com | [6 empty] | Fri 11/06/21 | NA
44 | 920014 | Study on application enablement aspects for subscriber-aware northbound API access | FS_SNAAPP | 1 | Rel-18 | S6 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210476 |  | Suzuki, Yuji, NTT DOCOMO | yuuji.suzuki.rm@nttdocomo.com | [6 empty] | Fri 11/06/21 | NA
45 | 920015 | Study on 5G-enabled fused location service capability exposure | FS_5GFLS | 1 | Rel-18 | S6 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210477 |  | Zhang, Ling, CATT | zhangling@catt.cn | [6 empty] | Fri 11/06/21 | NA
46 | 920016 | Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | 1 | Rel-18 | S6 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210478 |  | Mladin, Catalina; Convida Wireless | Mladin.Catalina@convidawireless.com | [6 empty] | Fri 11/06/21 | NA
47 | 920017 | Study on enhanced architecture for enabling Edge Applications | FS_eEDGEAPP | 1 | Rel-18 | S6 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210479 |  | Gupta, Nishant, Samsung | nishant.gup@samsung.com | [6 empty] | Fri 11/06/21 | NA
48 | 910022 | Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | 1 | Rel-18 | S6 | Thu 18/03/21 | Sat 12/03/22 | 0% | SP-210177 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | [6 empty] | Thu 18/03/21 | NA
49 | 900027 | Study on supporting tactile and multi-modality communication services | FS_TACMM | 1 | Rel-18 | S1 | Fri 04/12/20 | Fri 11/06/21 | 40% | SP-201039 |  | Wang, Shuo, China Mobile | wangshuoyjy@chinamobile.com | 10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40 | 22.847 | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
50 | 890022 | Study on vehicle-mounted relays | FS_VMR | 1 | Rel-18 | S1 | Wed 16/09/20 | Wed 08/09/21 | 85% | SP-200798 |  | Francesco Pica | fpica@qti.qualcomm.com | 5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85 | 22.839 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
51 | 880033 | Study of Gateway UE function for Mission Critical Communication | FS_MCGWUE | 1 | Rel-18 | S6 | Thu 25/06/20 | Mon 20/09/21 | 60% | SP-200335 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | 13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60 | 23.700-79 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
52 | 880040 | Study on Enhancements for Residential 5G | FS_Resident | 1 | Rel-18 | S1 | Thu 25/06/20 | Fri 11/06/21 | 85% | SP-200576 |  | Toon Norp, KPN | toon.norp@tno.nl | 28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85 | 22.858 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
53 | 880041 | Study on Personal IoT Networks | FS_PIN | 1 | Rel-18 | S1 | Thu 25/06/20 | Fri 11/06/21 | 90% | SP-200592 |  | Adrian Buckley, vivo Mobile Communications | adrian.buckley@vivo.com | 28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90 | 22.859 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
54 | 850043 | Study on sharing administrative configuration between interconnected MCX Service systems | FS_SACI_MCS | 1 | Rel-18 | S1 | Thu 19/09/19 | Fri 10/12/21 | 90% | SP-190837 |  | Toobe, Jens, BDBOS | jens.toobe at bdbos.bmi.bund.de | ; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90 | New ; 22.881 | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
55 | 860010 | Guidelines for Extra-territorial 5G Systems | FS_5GET | 1 | Rel-18 | S1 | Fri 06/12/19 | Fri 10/12/21 | 60% | SP-191042 |  | Cyril MICHEL,Thales | cyril.michel@thalesaleniaspace.com | 12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60 |  | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
56 | 0 | --- RELEASE 17 --- | - | 1 | Rel-17 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
57 | 0 | Rel-17 on Use of 5G by different sectors ("verticals") | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
58 | 840050 | Enhancements for cyber-physical control applications in vertical domains | eCAV | 1 | Rel-17 |  | Thu 07/03/19 | Thu 12/12/19 | 100% | SP-190310 |  | Bahr, Michael, Siemens AG | bahr et siemens dod com |  | 22.104; 22.261 | 84 | 43 |  |  | Fri 31/05/19 | NA
59 | 830020 | Study on eCAV | FS_eCAV | 2 | Rel-17 | S1 | Thu 07/03/19 | Thu 05/09/19 | 100% | SP-190092 | - | Michael Bahr, Siemens AG | bahr et siemens dod com | 14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Fri 26/06/20
60 | 840041 | Stage 1 of eCAV | eCAV | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-191043 |  | Bahr, Michael, Siemens AG | bahr et siemens dod com | 31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100 | 22.104; 22.261 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
61 | 840024 | Study on enhanced support of Non-Public Networks | FS_eNPN | 1 | Rel-17 | S2 | Thu 06/06/19 | Fri 12/03/21 | 100% | SP-200094 |  | Peter Hedman | peter . hedman @ ericsson . com | 8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/... | New ; 23.700-07 | 84 | 43 |  |  | Fri 31/05/19 | Fri 19/03/21
62 | 910065 | Enhanced support of Non-Public Networks | eNPN | 1 | Rel-17 |  | Thu 03/12/20 | Sat 12/03/22 | 17% | SP-200980 |  | Hedman, Peter, Ericsson | peter dot hedman at ericsson dot com |  | 23.501; 23.502; 23.503; 23.228; 23.167 | 90 |  |  |  | Thu 03/12/20 | NA
63 | 900015 | Stage 2 for eNPN | eNPN | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 20% | SP-200980 |  | Hedman, Peter, Ericsson | peter dot hedman at ericsson dot com | 19/3/21: 0%->20 | 23.501; 23.502; 23.503; 23.228; 23.167 | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
64 | 910016 | CT aspects of eNPN | eNPN | 2 | Rel-17 | ct | Thu 18/03/21 | Sat 12/03/22 | 17% | CP-210139 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 |  |  |  |  | Thu 18/03/21 | NA
65 | 910066 | CT1 aspects of eNPN | eNPN | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 20% | CP-210139 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 11/6/21: 0%->20 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
66 | 910067 | CT3 aspects of eNPN | eNPN | 3 | Rel-17 | C3 | Thu 18/03/21 | Sat 12/03/22 | 0% | CP-210139 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | [6 empty] | Thu 18/03/21 | NA
67 | 910068 | CT4 aspects of eNPN | eNPN | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 30% | CP-210139 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 11/6/21: 0%->30 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
68 | 920025 | Security Aspects of eNPN | eNPN | 2 | Rel-17 | S3 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210422 |  | Jost, Christine, Ericsson | christine.jost@ericsson.com |  | 33.501 |  |  |  |  | Fri 11/06/21 | NA
69 | 880008 | Study on enhanced security support for Non-Public Networks | FS_eNPN_SEC | 2 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 75% | SP-200353 |  | Normann, Henrik, Ericsson | henrik.normann@ericsson.com | 28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21 | 33.857 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
70 | 840045 | Audio-Visual Service Production | AVPROD | 1 | Rel-17 |  | Wed 06/06/18 | Thu 12/12/19 | 100% | SP-190304 |  | Wagdin, Ian, BBC | ian.wagdin@bbc.co.uk |  | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | NA
71 | 800014 | Study on AVPROD | FS_AVPROD | 2 | Rel-17 | S1 | Wed 06/06/18 | Wed 12/06/19 | 100% | SP-181015 |  | Roland Beutler, EBU | Roland.Beutler@swr.de | 6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100 | 22.827 | 80 | 41 |  |  | Wed 06/06/18 | Fri 13/09/19
72 | 840031 | Stage 1 of AVPROD | AVPROD | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-191041 |  | Wagdin, Ian, BBC | ian.wagdin@bbc.co.uk | 13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041 | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | Thu 12/12/19
73 | 910001 | Study on Media Production over 5G NPN | FS_NPN4AVProd | 1 | Rel-17 | S4 | Thu 18/03/21 | Fri 11/03/22 | 15% | SP-210041 |  | Lohmar, Thorsten, Ericsson | Thorsten.Lohmar@ericsson.com | ; 9/4/21: 26.805 added;; 11/6/21: 0%->15 | New 26.805 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
74 | 820025 | Study on application layer support for Factories of the Future in 5G network | FS_FFAPP | 1 | Rel-17 | S6 | Thu 07/03/19 | Fri 11/06/21 | 98% | SP-200836 |  | Shao Weixiang, ZTE Corporation | shao.weixiang@zte.com.cn | 14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F... | new | 82 | 42 |  |  | Thu 06/12/18 | Fri 11/06/21
75 | 840025 | Study on enhancement of support for 5G LAN-type service | FS_5GLAN_enh | 1 | Rel-17 | S2 | Thu 06/06/19 | Thu 12/03/20 | 0% | SP-190626 |  | Runze Zhou, Huawei | zhourunze@huawei.com | 20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added; | New ; 23.762 | 84 | 43 |  |  | Fri 31/05/19 | Tue 08/10/19
76 | 900022 | Study on Charging Aspect of 5G LAN-type Services | FS_5GLAN_CH | 1 | Rel-17 | S5 | Fri 04/12/20 | Fri 11/06/21 | 10% | SP-201081 |  | CHEN SHAN, Huawei | chenshan@huawei.com | 21/3/21: 0%->10 |  | 90 |  |  |  | Fri 04/12/20 | Sun 21/03/21
77 | 840042 | Complete Gap Analysis for Railways Mobile Communication System | MONASTERYEND | 1 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190312 |  | Gach, Guillaume, UIC | ext.gach@uic.org | 31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100 | 22.280; 22.281; 22.282; 22.179; 22.289 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
78 | 890035 | Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | 1 | Rel-17 |  | Thu 06/06/19 | Wed 08/09/21 | 78% | SP-191104 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85 | 23.280; 23.379; 23.281; 23.282; 23.283 | 84 | 43 |  |  | Fri 31/05/19 | Sun 28/06/20
79 | 840037 | Stage 2 of eMONASTERY2 | eMONASTERY2 | 2 | Rel-17 | S6 | Thu 06/06/19 | Fri 11/09/20 | 100% | SP-191104 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100 | 23.280; 23.379; 23.281; 23.282; 23.283 | 84 | 43 |  |  | Fri 31/05/19 | Sun 13/09/20
80 | 890063 | Stage 3 of eMONASTERY2 | eMONASTERY2 | 2 | Rel-17 | C1 | Wed 16/09/20 | Wed 08/09/21 | 50% | CP-202256 |  | Gkatzikis, Lazaros, Nokia(Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | ; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50 | 24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 | 89 | 45 |  |  | Fri 25/09/20 | Fri 11/06/21
81 | 840043 | Study on Future Railway Mobile Communication System3 | FS_FRMCS3 | 1 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-200578 |  | Gach, Guillaume, UIC, | ext.gach@uic.org | 31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578 | 22.989 | 84 | 43 |  |  | Fri 31/05/19 | Thu 25/06/20
82 | 850046 | Asset Tracking for 5G | ATRAC | 1 | Rel-17 |  | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-190816 |  | Thierry Berisot, NOVAMINT | tberisot@novamint.com |  | 22.261 | 85 | 43 |  |  | Fri 13/09/19 | NA
83 | 810017 | Study on ATRAC | FS_5G_ATRAC | 2 | Rel-17 | S1 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180922 |  | Thierry Berisot, NOVAMINT | tberisot@novamint.com | 4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100 | 22.836 | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
84 | 850037 | Stage 1 of ATRAC | ATRAC | 2 | Rel-17 | S1 | Thu 19/09/19 | Thu 12/12/19 | 100% | SP-190931 |  | Thierry Berisot, NOVAMINT | tberisot@novamint.com | ; 13/9/19: 0%->95; 6/12/19: 95%->100 | 22.261 | 85 | 43 |  |  | Fri 13/09/19 | Fri 06/12/19
85 | 910052 | Enhancement to the 5GC LoCation Services-Phase 2 | 5G_eLCS_ph2 | 1 | Rel-17 |  | Wed 25/03/20 | Sat 12/03/22 | 28% | SP-200082 |  | Ming Ai, CATT | aiming@catt.cn | 5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20 | 23.273 | 87 | 44 |  |  | Fri 31/05/19 | Sat 05/12/20
86 | 870001 | Stage 2 of 5G_eLCS_ph2 | 5G_eLCS_ph2 | 2 | Rel-17 | S2 | Wed 25/03/20 | Wed 08/09/21 | 70% | SP-200082 |  | Ming Ai, CATT | aiming@catt.cn | 5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21 | 23.273 | 87 | 44 |  |  | Fri 31/05/19 | Fri 11/06/21
87 | 910006 | CT aspects of 5G_eLCS_ph2 | 5G_eLCS_ph2 | 2 | Rel-17 | ct | Thu 18/03/21 | Sat 12/03/22 | 7% | CP-211090 |  | Chenxi Bao, CATT | baochenxi@catt.cn | 11/6/21: WID:CP-210075->CP-211090 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
88 | 910053 | CT1 aspects of 5G_eLCS_ph2 | 5G_eLCS_ph2 | 3 | Rel-17 | C1 | Thu 18/03/21 | Sat 12/03/22 | 0% | CP-211090 |  | Chenxi Bao, CATT | baochenxi@catt.cn |  | 24.501; 24.571; 27.007 |  |  |  |  | Thu 18/03/21 | NA
89 | 910054 | CT3 aspects of 5G_eLCS_ph2 | 5G_eLCS_ph2 | 3 | Rel-17 | C3 | Thu 18/03/21 | Sat 12/03/22 | 0% | CP-211090 |  | Chenxi Bao, CATT | baochenxi@catt.cn |  | 29.522; 29.122 |  |  |  |  | Thu 18/03/21 | NA
90 | 910055 | CT4 aspects of 5G_eLCS_ph2 | 5G_eLCS_ph2 | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 20% | CP-211090 |  | Chenxi Bao, CATT | baochenxi@catt.cn | 11/6/21: 0%->20 | 29.515; 29.572; 24.080; 29.518; 29.503; 29.571 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
91 | 900060 | RAN aspects of NR positioning enhancements | NR_pos_enh | 1 | Rel-17 |  | Thu 07/03/19 | Thu 08/09/22 | 29% | RP-210903 |  | Intel |  | follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
92 | 860034 | Study on NR positioning enhancements | FS_NR_pos_enh | 2 | Rel-17 | R1 | Thu 07/03/19 | Wed 03/06/20 | 100% | RP-202094 |  | CATT |  | affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
93 | 900160 | Core part: NR positioning enhancements | NR_pos_enh-Core | 2 | Rel-17 | R1 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210903 |  | Intel |  | follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) |  | 90 |  |  |  | Wed 06/01/21 | NA
94 | 900260 | Perf. part: NR positioning enhancements | NR_pos_enh-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Thu 08/09/22 | 0% | RP-210903 |  | Intel |  | follow-up WI of REL-17 SI FS_NR_pos_enh |  | 90 |  |  |  | Wed 06/01/21 | NA
95 | 840047 | Communication Service Requirements for Critical Medical Applications | CMED | 1 | Rel-17 |  | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-190306 |  | Lagrange, Mathieu, b<>com | mathieu.lagrange@b-com.com |  | 22.261; 22.104 | 84 | 43 |  |  | Fri 31/05/19 | NA
96 | 810016 | Study on CMED | FS_CMED | 2 | Rel-17 | S1 | Thu 06/09/18 | Fri 13/09/19 | 100% | SP-180783 |  | Mathieu Lagrange, b<>com | mathieu.lagrange@b-com.com | 4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100 | 22.826 | 81 | 41 |  |  | Thu 06/09/18 | Fri 06/12/19
97 | 840033 | Stage 1 of CMED | CMED | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190306 |  | Lagrange, Mathieu, b<>com | mathieu.lagrange@b-com.com | 13/9/19: 0%->80; 6/12/19: 80%->100 | 22.261; 22.104 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
98 | 0 | Rel-17 drone/UAS/UAV/EAV | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | 06/21: "unmanned" changed to "uncrewed" as per SA#91 discussions | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
99 | 840083 | 5G Enhancement for UAVs | EAV | 1 | Rel-17 |  | Thu 06/09/18 | Fri 13/12/19 | 100% | SP-190308 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn |  | 22.125; 22.261 | 84 | 43 |  |  | Fri 31/05/19 | NA
100 | 810019 | Study on EAV | FS_EAV | 2 | Rel-17 | S1 | Thu 06/09/18 | Fri 13/12/19 | 100% | SP-180909 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn | -; 31/5/19: 70%->90; 13/9/19: 90%->100 | 22.829 | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
101 | 840039 | Stage 1 of EAV | EAV | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190308 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn | 26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100 | 26.118; 26.247¦22.125 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
102 | 820011 | Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking | FS_ID_UAS_SA2 | 1 | Rel-17 | S2 | Thu 06/12/18 | Tue 15/12/20 | 100% | SP-200097 |  | Qualcomm Incorporated, Stefano Faccin | sfaccin@qti.qualcomm.com | 25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100 |  | 82 | 42 |  |  | Thu 06/12/18 | Sat 05/12/20
103 | 820026 | Study on application layer support for Uncrewed Aerial System (UAS) | FS_UASAPP | 1 | Rel-17 | S6 | Thu 06/12/18 | Fri 12/03/21 | 100% | SP-200111 |  | Niranth Amogh, Huawei | namogh@huawei.com | 31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100 | new 23.755 | 82 | 42 |  |  | Thu 06/12/18 | Sun 21/03/21
104 | 920045 | Application layer support for Uncrewed Aerial System (UAS) | UASAPP | 1 | Rel-17 | S6 | Fri 04/12/20 | Sat 12/03/22 | 28% | SP-200988 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 23.434 ; 21/3/21: 0%->25 |  | 90 |  |  |  | Fri 04/12/20 | Sun 21/03/21
105 | 900025 | Stage 2 of Application layer support for Uncrewed Aerial System (UAS) | UASAPP | 2 | Rel-17 | S6 | Fri 04/12/20 | Fri 11/06/21 | 100% | SP-200988 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 23.434 ; 21/3/21: 0%->25; 11/6/21: 25%->100 |  | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
106 | 920004 | CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) | UASAPP | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211111 |  | Lin Shu, Huawei, | shulin@huawei.com |  | 24.548;24.545;27.007 |  |  |  |  | Fri 11/06/21 | NA
107 | 920046 | CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) | UASAPP | 2 | Rel-17 | C3 | Fri 11/06/21 | Fri 11/03/22 | 5% | CP-211111 |  | Lin Shu, Huawei | shulin@huawei.com | ; 11/6/21: 0%->5 | 29.549 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
108 | 880007 | Study on security aspects of Uncrewed Aerial Systems (UAS) | FS_UAS_SEC | 1 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 90% | SP-200352 |  | Adrian Escott, Qualcomm Incorporated | aescott@qti.qualcomm.com | 12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21 | 33.854 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
109 | 810049 | Remote Identification of Uncrewed Aerial Systems | ID_UAS | 1 | Rel-17 |  | Thu 06/09/18 | Sat 12/03/22 | 20% | SP-180771 |  | Eddy HALL, Qualcomm incorporated | edhall@qti.qualcomm.com |  |  | 81 | 41 |  |  | Thu 06/09/18 | NA
110 | 810013 | Stage 1 of Remote Identification of Uncrewed Aerial Systems | ID_UAS | 2 | Rel-17 | S1 | Thu 06/09/18 | Fri 14/12/18 | 100% | SP-180771 |  | Eddy HALL, Qualcomm incorporated | edhall@qti.qualcomm.com | 10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16 | 22.125 | 81 | 41 |  |  | Thu 06/09/18 | Tue 04/12/18
111 | 900014 | (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | ID_UAS | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 15% | SP-200979 |  | Faccin, Stefano, Qualcomm Incorporated | sfaccin@qti.qualcomm.com | 19/3/21: 0%->15 | 23.501; 23.502; 23.503; 23.401 | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
112 | 910017 | CT aspects for ID_UAS | ID_UAS | 2 | Rel-17 | ct | Thu 18/03/21 | Sat 12/03/22 | 13% | CP-211112 |  | Sunghoon Kim, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | ; 11/6/21: WID:CP-210287->CP-211112 | 24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
113 | 910069 | CT1 aspects for ID_UAS | ID_UAS | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 20% | CP-211112 |  | Sunghoon Kim, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | ; 11/6/21: 0%->20 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
114 | 910070 | CT3 aspects for ID_UAS | ID_UAS | 3 | Rel-17 | C3 | Thu 18/03/21 | Sat 12/03/22 | 0% | CP-211112 |  | Sunghoon Kim, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | [6 empty] | Thu 18/03/21 | NA
115 | 910071 | CT4 aspects for ID_UAS | ID_UAS | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 20% | CP-211112 |  | Sunghoon Kim, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | ; 11/6/21: 0%->20 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
116 | 920028 | Security aspects of Uncrewed Aerial Systems | ID_UAS | 2 | Rel-17 | S3 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210425 |  | Escott, Adrian, Qualcomm Incorporated | aescott@qti.qualcomm.com | [6 empty] | Fri 11/06/21 | NA
117 | 0 | Rel-17 Satellite/Non-Terrestrial (NTN) related | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
118 | 890034 | Integration of satellite components in the 5G architecture | 5GSAT_ARCH | 1 | Rel-17 |  | Wed 06/06/18 | Fri 10/09/21 | 88% | SP-191335 |  | Cyril MICHEL, thales | cyril.michel@thalesaleniaspace.com |  | 23.501; 23.502; 23.503 | 86 | 44 |  |  | Fri 06/12/19 | NA
119 | 800048 | Stage 1 of 5GSAT | 5GSAT | 2 | Rel-17 | S1 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180326 |  | MICHEL, Cyril, Thales | cyril.michel@thalesaleniaspace.com | 10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17 | 22.261 | 80 | 41 |  |  | Wed 06/06/18 | Tue 04/12/18
120 | 800026 | Study on architecture aspects for using satellite access in 5G | FS_5GSAT_ARCH | 2 | Rel-17 | S2 | Wed 06/06/18 | Thu 25/06/20 | 100% | SP-181253 |  | MICHEL, Cyril | cyril.michel@thalesaleniaspace.com | 10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%-... | New | 80 | 41 |  |  | Wed 06/06/18 | Fri 26/06/20
121 | 860005 | (Stage 2 of) Integration of satellite components in the 5G architecture | 5GSAT_ARCH | 2 | Rel-17 | S2 | Fri 06/12/19 | Wed 08/09/21 | 98% | SP-191335 |  | Cyril MICHEL, thales | cyril.michel@thalesaleniaspace.com | 12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21 | 23.501; 23.502; 23.503 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
122 | 911030 | CT aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 2 | Rel-17 | ct | Wed 16/09/20 | Fri 10/09/21 | 73% | CP-210149 |  | Catovic, Amer, Qualcomm Incorporated | amerc@qti.qualcomm.com | ; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149 | 23.122; 24.501; 24.008; 24.301 | 89 | 45 |  |  | Sat 12/09/20 | Fri 11/06/21
123 | 890005 | CT1 aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 3 | Rel-17 | C1 | Wed 16/09/20 | Fri 10/09/21 | 80% | CP-210149 |  | Catovic, Amer, Qualcomm Incorporated | amerc@qti.qualcomm.com | ; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80 | 23.122; 24.501; 24.008; 24.301 | 89 | 45 |  |  | Sat 12/09/20 | Fri 11/06/21
124 | 920057 | CT3 aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 3 | Rel-17 | C3 | Wed 16/09/20 | Fri 10/09/21 | 60% | CP-210149 |  | Catovic, Amer, Qualcomm Incorporated | amerc@qti.qualcomm.com | ; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60 | 23.122; 24.501; 24.008; 24.301 | 89 | 45 |  |  | Sat 12/09/20 | Fri 11/06/21
125 | 911031 | CT4 aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 3 | Rel-17 | C4 | Wed 16/09/20 | Fri 10/09/21 | 80% | CP-210149 |  | Catovic, Amer, Qualcomm Incorporated | amerc@qti.qualcomm.com | ; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80 | 23.122; 24.501; 24.008; 24.301 | 89 | 45 |  |  | Sat 12/09/20 | Fri 11/06/21
126 | 860046 | Solutions for NR to support non-terrestrial networks (NTN) | NR_NTN_solutions | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-210908 |  | Thales |  | affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
127 | 860146 | Core part: Solutions for NR for NTN | NR_NTN_solutions-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-210908 |  | Thales |  | affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions |  | 86 | 44 |  |  | Tue 14/01/20 | NA
128 | 860246 | Perf. Part: Solutions for NR for NTN | NR_NTN_solutions-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-210908 |  | Thales |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
129 | 830025 | Study on management and orchestration aspects with integrated satellite components in a 5G network | FS_5GSAT_MO | 1 | Rel-17 | S5 | Thu 07/03/19 | Fri 12/03/21 | 100% | SP-190138 |  | Floris Drijver, TNO | floris.drijver@tno.nl | 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Sun 21/03/21
130 | 860033 | Study on NB-IoT/eMTC support for NTN | FS_LTE_NBIOT_eMTC_NTN | 1 | Rel-17 | R1 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-202689 |  | MediaTek |  | affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689 | 36.763 | 86 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
131 | 0 | Rel-17 IoT related | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
132 | 850012 | Study on enhanced support of Industrial IoT | FS_IIoT | 1 | Rel-17 | S2 | Thu 19/09/19 | Fri 12/03/21 | 100% | SP-200298 |  | Nokia, Devaki Chandramouli, | devaki.chandramouli@nokia.com | ; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/... | New ; 23.700-20 | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
133 | 880010 | Study on security for enhanced support of Industrial IoT | FS_IIoT_SEC | 1 | Rel-17 | S3 | Fri 12/06/20 | Fri 11/06/21 | 100% | SP-200355 |  | Nokia, Anja Jerichow | anja.jerichow@nokia.com | 28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100 | 33.851 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
134 | 920024 | Security for enhanced support of Industrial IoT | IIoT_SEC | 1 | Rel-17 | S3 | Fri 11/06/21 | Sun 20/06/21 | 0% | SP-210421 |  | Nokia, Anja Jerichow | anja.jerichow@nokia.com |  | 33.501 |  |  |  |  | Fri 11/06/21 | NA
135 | 910059 | Support of Enhanced Industrial IIoT | IIoT | 1 | Rel-17 |  | Thu 03/12/20 | Fri 11/03/22 | 64% | SP-200973 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com |  |  | 90 |  |  |  | Thu 03/12/20 | NA
136 | 900008 | Stage 2 for IIoT | IIoT | 2 | Rel-17 | S2 | Thu 03/12/20 | Wed 08/09/21 | 90% | SP-200973 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com | 19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21 | 23.501; 23.502; 23.503 | 90 |  |  |  | Thu 03/12/20 | Fri 11/06/21
137 | 910014 | CT aspects of support of enhanced Industrial IoT | IIoT | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 57% | CP-211114 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  | 24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 |  |  |  |  | Thu 18/03/21 | NA
138 | 910060 | CT1 aspects of support of enhanced Industrial IoT | IIoT | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 65% | CP-211114 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com | ; 11/6/21: 0%->65 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
139 | 910061 | CT3 aspects of support of enhanced Industrial IoT | IIoT | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 45% | CP-211114 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com | ; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
140 | 910062 | CT4 aspects of support of enhanced Industrial IoT | IIoT | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 60% | CP-211114 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com | ; 11/6/21: 0%->60 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
141 | 860044 | Additional enhancements for NB-IoT and LTE-MTC | NB_IOTenh4_LTE_eMTC6 | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-201306 |  | Huawei |  | affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
142 | 860144 | Core part: Additional enhancements for NB-IoT and LTE-MTC | NB_IOTenh4_LTE_eMTC6-Core | 2 | Rel-17 | R1 | Mon 21/12/20 | Tue 15/06/21 | 0% | RP-201306 |  | Huawei |  | affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC |  | 86 | 44 |  |  | Tue 14/01/20 | NA
143 | 860244 | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | NB_IOTenh4_LTE_eMTC6-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-201306 |  | Huawei |  | affects: LTE. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
144 | 860051 | NR small data transmissions in INACTIVE state | NR_SmallData_INACTIVE | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-210870 |  | ZTE |  | affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
145 | 860151 | Core part: NR small data transmissions in INACTIVE state | NR_SmallData_INACTIVE-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-210870 |  | ZTE |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
146 | 860251 | Perf. part: NR small data transmissions in INACTIVE state | NR_SmallData_INACTIVE-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-210870 |  | ZTE |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
147 | 860045 | Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | NR_IIOT_URLLC_enh | 1 | Rel-17 |  | Mon 16/12/19 | Tue 15/03/22 | 0% | RP-210854 |  | Nokia |  | affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
148 | 860145 | Core part: Enhanced IoT and URLLC support for NR | NR_IIOT_URLLC_enh-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-210854 |  | Nokia |  | affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
149 | 860245 | Perf. Part: Enhanced IoT and URLLC support for NR | NR_IIOT_URLLC_enh-Perf | 2 | Rel-17 | R4 | Mon 15/06/20 | Tue 15/03/22 | 0% | RP-210854 |  | Nokia |  |  |  | 86 |  |  |  | Fri 25/09/20 | NA
150 | 0 | Rel-17 V2V/D2D/Sidelink related | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
151 | 860042 | NR Sidelink enhancement | NR_SL_enh | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-202846 |  | LG Electronics |  | affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
152 | 860142 | Core part: NR Sidelink enhancement | NR_SL_enh-Core | 2 | Rel-17 | R1 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-202846 |  | LG Electronics |  | affects: NR. compare REL-16 WI 5G_V2X_NRSL |  | 86 | 44 |  |  | Tue 14/01/20 | NA
153 | 860242 | Perf. part: NR Sidelink enhancement | NR_SL_enh-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-202846 |  | LG Electronics |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
154 | 860038 | Study on NR Sidelink relay | FS_NR_SL_relay | 1 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/09/20 | 100% | RP-202208 |  | OPPO |  | affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
155 | 840035 | Study on enhancements to application layer support for V2X services | FS_eV2XAPP | 1 | Rel-17 | S6 | Thu 06/06/19 | Fri 12/06/20 | 95% | SP-200110 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95 | 23.764 | 84 | 43 |  |  | Fri 31/05/19 | Sun 13/09/20
156 | 910075 | Enhanced application layer support for V2X services | eV2XAPP | 1 | Rel-17 |  | Wed 16/09/20 | Fri 11/03/22 | 58% | SP-200831 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | ; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21 | 23.286; 23.434 | 89 | 45 |  |  | Fri 11/09/20 | Wed 10/02/21
157 | 890036 | Stage 2 of eV2XAPP | eV2XAPP | 2 | Rel-17 | S6 | Wed 16/09/20 | Tue 15/06/21 | 100% | SP-200831 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | ; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100 | 23.286; 23.434 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
158 | 910019 | CT aspects of eV2XAPP | eV2XAPP | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 42% | CP-211109 |  | Herrero Veron, Christian (Huawei) |  | ; 11/6/21: WID:CP-210273->CP-211109 | 24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
159 | 910076 | CT1 aspects of eV2XAPP | eV2XAPP | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 35% | CP-211109 |  | Herrero Veron, Christian (Huawei) |  | ; 11/6/21: 0%->35 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
160 | 910077 | CT3 aspects of eV2XAPP | eV2XAPP | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 50% | CP-211109 |  | Herrero Veron, Christian (Huawei) |  | ; 11/6/21: 0%->50 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
161 | 910037 | Support of advanced V2X services - Phase 2 | eV2XARC_Ph2 | 1 | Rel-17 |  | Thu 19/09/19 | Sat 12/03/22 | 37% | SP-210090 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com |  | 23.287 |  |  |  |  | Thu 18/03/21 | NA
162 | 850013 | Study on V2X services – Phase 2 | FS_eV2XARC_Ph2 | 2 | Rel-17 | S2 | Thu 19/09/19 | Fri 12/03/21 | 100% | SP-190631 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | ; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100 | New | 85 | 43 |  |  | Fri 13/09/19 | Fri 19/03/21
163 | 910021 | Stage 2 of eV2XARC_Ph2 | eV2XARC_Ph2 | 2 | Rel-17 | S2 | Thu 18/03/21 | Sat 12/06/21 | 0% | SP-210090 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com |  | 23.287 |  |  |  |  | Thu 18/03/21 | NA
164 | 920005 | CT1 aspects of eV2XARC_Ph2 | eV2XARC_Ph2 | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211116 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.588;24.587 |  |  |  |  | Fri 11/06/21 | NA
165 | 920047 | CT3 aspects of eV2XARC_Ph2 | eV2XARC_Ph2 | 2 | Rel-17 | C3 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211116 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 31.102;29.522;29.525;29.519 |  |  |  |  | Fri 11/06/21 | NA
166 | 920048 | CT6 aspects of eV2XARC_Ph2 | eV2XARC_Ph2 | 2 | Rel-17 | C6 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211116 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 31.102 |  |  |  |  | Fri 11/06/21 | NA
167 | 0 | Rel-17 NR enhancements | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
168 | 860040 | Further enhancements on MIMO for NR | NR_feMIMO | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-202024 |  | Samsung |  | affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024 |  | 86 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
169 | 860140 | Core part: Further enhancements on MIMO for NR | NR_feMIMO-Core | 2 | Rel-17 | R1 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-202024 |  | Samsung |  | affects: NR. compare REL-16 WI NR_eMIMO |  | 86 | 44 |  |  | Tue 14/01/20 | NA
170 | 860240 | Perf. part: Further enhancements on MIMO for NR | NR_feMIMO-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-202024 |  | Samsung |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
171 | 860043 | NR Dynamic spectrum sharing (DSS) | NR_DSS | 1 | Rel-17 |  | Mon 16/12/19 | Mon 15/03/21 | 0% | RP-193260 |  | Ericsson |  | affects: NR. no Perf. part |  | 86 | 44 |  |  | Tue 14/01/20 | NA
172 | 860143 | Core part: NR DSS | NR_DSS-Core | 2 | Rel-17 | R1 | Mon 16/12/19 | Mon 15/03/21 | 0% | RP-193260 |  | Ericsson |  | affects: NR. no Perf. part |  | 86 | 44 |  |  | Tue 14/01/20 | NA
173 | 860047 | UE power saving enhancements for NR | NR_UE_pow_sav_enh | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 9% | RP-200938 |  | MediaTek |  | affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
174 | 860147 | Core part: UE power saving enhancements for NR | NR_UE_pow_sav_enh-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-200938 |  | MediaTek |  | affects: NR. compare REL-16 WI NR_UE_pow_sav |  | 86 | 44 |  |  | Tue 14/01/20 | NA
175 | 860247 | Perf. part: UE power saving enhancements for NR | NR_UE_pow_sav_enh-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-200938 |  | MediaTek |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
176 | 880071 | UE Conformance Test Aspects -UE Power Saving in NR | NR_UE_pow_sav-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Mon 21/06/21 | 39% | RP-202726 |  | CATT |  | 8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
177 | 860049 | Further Multi-RAT Dual-Connectivity enhancements | LTE_NR_DC_enh2 | 1 | Rel-17 |  | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-201040 |  | Huawei |  | affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
178 | 860149 | Core part: Further Multi-RAT Dual-Connectivity enhancements | LTE_NR_DC_enh2-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-201040 |  | Huawei |  | affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh |  | 86 | 44 |  |  | Tue 14/01/20 | NA
179 | 860249 | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | LTE_NR_DC_enh2-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-201040 |  | Huawei |  | affects: LTE, NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
180 | 860050 | Enhancements to Integrated Access and Backhaul (IAB) for NR | NR_IAB_enh | 1 | Rel-17 |  | Mon 11/03/19 | Wed 15/12/21 | 34% | RP-210758 |  | Qualcomm |  | affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
181 | 860150 | Core part: Enhancements to IAB for NR | NR_IAB_enh-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-210758 |  | Qualcomm |  | affects: NR. compare REL-16 WI NR_IAB |  | 86 | 44 |  |  | Tue 14/01/20 | NA
182 | 860250 | Perf. part: Enhancements to IAB for NR | NR_IAB_enh-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/12/21 | 0% | RP-210758 |  | Qualcomm |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
183 | 830021 | Study on Security for NR_IAB | FS_NR_IAB_Sec | 2 | Rel-17 | S3 | Mon 11/03/19 | Fri 10/12/21 | 78% | SP-201016 |  | Rajavelsamy Rajadurai, Samsung, | rajvel{@]samsung.com | 31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21... | 33.824 | 83 | 42 |  |  | Thu 14/03/19 | Fri 11/06/21
184 | 860052 | Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | LTE_NR_arch_evo_enh | 1 | Rel-17 |  | Mon 16/12/19 | Tue 15/12/20 | 0% | RP-193181 |  | China Unicom |  | affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo |  | 86 | 44 |  |  | Tue 14/01/20 | NA
185 | 860152 | Core part: LTE_NR_arch_evo_enh | LTE_NR_arch_evo_enh-Core | 2 | Rel-17 | R3 | Mon 16/12/19 | Tue 15/12/20 | 0% | RP-193181 |  | China Unicom |  | affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo |  | 86 | 44 |  |  | Tue 14/01/20 | NA
186 | 890055 | Further enhancement on NR demodulation performance | NR_demod_enh2 | 1 | Rel-17 |  | Tue 15/09/20 | Fri 12/03/21 | 0% | RP-210920 |  | China Telecom |  | demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
187 | 890255 | Perf. part: NR_demod_enh2 | NR_demod_enh2-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Fri 12/03/21 | 0% | RP-210920 |  | China Telecom |  | demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part |  | 89 | 45 |  |  | Sun 11/10/20 | NA
188 | 890056 | Introduction of DL 1024QAM for NR frequency range 1 (FR1) | NR_DL1024QAM_FR1 | 1 | Rel-17 |  | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-202886 |  | Ericsson |  | ; 6/1/21: WID:RP-202044->RP-202886 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 06/01/21
189 | 890156 | Core part: Introduction of DL 1024QAM for NR FR1 | NR_DL1024QAM_FR1-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-202886 |  | Ericsson |  |  |  | 89 | 45 |  |  | Sun 11/10/20 | NA
190 | 890256 | Perf. part: Introduction of DL 1024QAM for NR FR1 | NR_DL1024QAM_FR1-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-202886 |  | Ericsson |  |  |  | 89 | 45 |  |  | Sun 11/10/20 | NA
191 | 890057 | NR RRM further enhancement | NR_RRM_enh2 | 1 | Rel-17 |  | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-202874 |  | Apple |  | LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 06/01/21
192 | 890157 | Core part: Further RRM enhancement for NR and MR-DC | NR_RRM_enh2-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-202874 |  | Apple |  | LTE impacts? |  | 89 | 45 |  |  | Sun 11/10/20 | NA
193 | 890257 | Perf. part: Further RRM enhancement for NR and MR-DC | NR_RRM_enh2-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-202874 |  | Apple |  | LTE impacts? |  | 89 | 45 |  |  | Sun 11/10/20 | NA
194 | 890058 | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | NR_HST_FR1_enh | 1 | Rel-17 |  | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210833 |  | CMCC |  | follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
195 | 890158 | Core part: Enhanced NR support for high speed train scenario for FR1 | NR_HST_FR1_enh-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-210833 |  | CMCC |  | follow-up WI of REL-16 WI NR_HST |  | 89 | 45 |  |  | Sun 11/10/20 | NA
196 | 890258 | Perf. part: Enhanced NR support for high speed train scenario for FR1 | NR_HST_FR1_enh-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210833 |  | CMCC |  | follow-up WI of REL-16 WI NR_HST |  | 89 | 45 |  |  | Sun 11/10/20 | NA
197 | 890059 | Further enhancements of NR RF requirements for frequency range 2 (FR2) | NR_RF_FR2_req_enh2 | 1 | Rel-17 |  | Tue 15/09/20 | Sat 11/12/21 | 0% | RP-210914 |  | Nokia |  | compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
198 | 890159 | Core part: NR_RF_FR2_req_enh2 | NR_RF_FR2_req_enh2-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-210914 |  | Nokia |  | compare REL-16 WI NR_RF_FR2_req_enh |  | 89 | 45 |  |  | Sun 11/10/20 | NA
199 | 890259 | Perf. part: NR_RF_FR2_req_enh2 | NR_RF_FR2_req_enh2-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 11/12/21 | 0% | RP-210914 |  | Nokia |  | compare REL-16 WI NR_RF_FR2_req_enh |  | 89 | 45 |  |  | Sun 11/10/20 | NA
200 | 890060 | NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2 | 1 | Rel-17 |  | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210800 |  | Samsung |  | follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
201 | 890160 | Core part: NR support for high speed train scenario in FR2 | NR_HST_FR2-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210800 |  | Samsung |  | follow-up WI of REL-16 WI NR_HST; TR 38.8xx |  | 89 | 45 |  |  | Sun 11/10/20 | NA
202 | 890260 | Perf. Part: NR support for high speed train scenario in FR2 | NR_HST_FR2-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210800 |  | Samsung |  | follow-up WI of REL-16 WI NR_HST |  | 89 | 45 |  |  | Sun 11/10/20 | NA
203 | 890061 | NR measurement gap enhancements | NR_MG_enh | 1 | Rel-17 |  | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210679 |  | MediaTek |  | measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
204 | 890161 | Core part: NR and MR-DC measurement gap enhancements | NR_MG_enh-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-210679 |  | MediaTek |  | measurement gaps were introduced for NR in REL-15 WI NR_newRAT |  | 89 | 45 |  |  | Sun 11/10/20 | NA
205 | 890261 | Perf. part: NR and MR-DC measurement gap enhancements | NR_MG_enh-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 12/03/22 | 0% | RP-210679 |  | MediaTek |  | measurement gaps were introduced for NR in REL-15 WI NR_newRAT |  | 89 | 45 |  |  | Sun 11/10/20 | NA
206 | 890062 | RF requirements enhancement for NR frequency range 1 (FR1) | NR_RF_FR1_enh | 1 | Rel-17 |  | Tue 15/09/20 | Sat 11/12/21 | 0% | RP-210899 |  | Huawei |  | compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899 |  | 89 | 45 |  |  | Sun 11/10/20 | Wed 07/04/21
207 | 890162 | Core part: RF requirements enhancement for NR FR1 | NR_RF_FR1_enh-Core | 2 | Rel-17 | R4 | Tue 15/09/20 | Wed 08/09/21 | 0% | RP-210899 |  | Huawei |  | compare REL-16 WI NR_RF_FR1 |  | 89 | 45 |  |  | Sun 11/10/20 | NA
208 | 890262 | Perf. part: RF requirements enhancement for NR FR1 | NR_RF_FR1_enh-Perf | 2 | Rel-17 | R4 | Tue 15/09/20 | Sat 11/12/21 | 0% | RP-210899 |  | Huawei |  | compare REL-16 WI NR_RF_FR1 |  | 89 | 45 |  |  | Sun 11/10/20 | NA
209 | 0 | Rel-17 Self-Organizing (SON)/Autonomous Networks | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
210 | 860053 | Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | NR_ENDC_SON_MDT_enh | 1 | Rel-17 |  | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-193255 |  | CMCC |  | affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes |  | 86 | 44 |  |  | Tue 14/01/20 | NA
211 | 860153 | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | NR_ENDC_SON_MDT_enh-Core | 2 | Rel-17 | R3 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-201281 |  | CMCC |  | affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
212 | 910029 | Plug and connect support for management of Network Functions | PACMAN | 1 | Rel-17 | S5 | Thu 18/03/21 | Fri 10/06/22 | 10% | SP-210260 |  | Per Elmdahl, Ericsson | Per.elmdahl@ericsson.com | ; 11/6/21: 0%->10 | 28.313 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
213 | 870028 | Enhancements of Self-Organizing Networks (SON) for 5G networks | eSON_5G | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 35% | SP-200194 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | ; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21 | 28.313; 28.552; 28.541; 28.545 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
214 | 850032 | Study on autonomous network levels | FS_ANL | 1 | Rel-17 | S5 | Thu 19/09/19 | Mon 14/09/20 | 100% | SP-190928 |  | China Mobile | caoxi@chinamobile.com | ; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17 | New ; 28.810 | 85 | 43 |  |  | Fri 13/09/19 | Sun 13/09/20
215 | 880027 | Autonomous network levels | ANL | 1 | Rel-17 | S5 | Fri 12/06/20 | Fri 11/06/21 | 70% | SP-200464 |  | Cao, Xi, China Mobile | caoxi@chinamobile.com | 28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
216 | 0 | Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC) | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
217 | 900038 | Multicast-broadcast services in 5G | 5MBS | 1 | Rel-17 |  | Thu 07/03/19 | Sat 12/03/22 | 43% | SP-201106 |  | Meng Li, Huawei | raymond.limeng@huawei.com | 23.501; 23.502; 23.503 |  | 90 |  |  |  | Thu 03/12/20 | NA
218 | 830030 | Study on Architectural enhancements for 5G multicast-broadcast services | FS_5MBS | 2 | Rel-17 | S2 | Thu 07/03/19 | Fri 12/03/21 | 100% | SP-200690 |  | Meng Li, Huawei | raymond.limeng@huawei.com | 7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID:... | 23.757 | 83 | 42 |  |  | Thu 14/03/19 | Fri 19/03/21
219 | 900009 | Stage 2 for 5MBS | 5MBS | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 10/09/21 | 20% | SP-201106 |  | Meng Li, Huawei | raymond.limeng@huawei.com | 23.501; 23.502; 23.503 ; 19/3/21: 0%->20 |  | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
220 | 920043 | CT1 aspects of the architectural enhancements for 5G multicast-broadcast services | 5MBS | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211093 |  | Gulbani, Giorgi, Huawei | giorgi.gulbani@huawei.com |  | 24.501 |  |  |  |  | Fri 11/06/21 | NA
221 | 920044 | CT3 aspects of the architectural enhancements for 5G multicast-broadcast services | 5MBS | 2 | Rel-17 | C3 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211093 |  | Gulbani, Giorgi, Huawei | giorgi.gulbani@huawei.com |  | 29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 |  |  |  |  | Fri 11/06/21 | NA
222 | 910002 | CT4 aspects of the architectural enhancements for 5G multicast-broadcast services | 5MBS | 2 | Rel-17 | C4 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211093 |  | Gulbani, Giorgi, Huawei | giorgi.gulbani@huawei.com | UID in 91xx range but presented to CT#92 | 29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 |  |  |  |  | Fri 11/06/21 | NA
223 | 920023 | Security Aspects of Enhancements for 5G Multicast-Broadcast Services | 5MBS | 2 | Rel-17 | S3 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210420 |  | Longhua Guo, Huawei Technologies | guolonghua@huawei.com |  | 33.501 |  |  |  |  | Fri 11/06/21 | NA
224 | 870014 | Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 1 | Rel-17 | S4 | Wed 25/03/20 | Fri 11/06/21 | 100% | SP-200238 |  | Peng Tan, Telus | peng.tan@telus.com | 10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100 | new | 87 | 44 |  |  | Fri 31/05/19 | Fri 11/06/21
225 | 810055 | Study on location enhancements for mission critical services | FS_enhMCLoc | 1 | Rel-17 | S6 | Fri 14/09/18 | Thu 12/03/20 | 100% | SP-190725 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100 | 23.744 | 81 | 41 |  |  | Fri 14/09/18 | Sat 05/12/20
226 | 850040 | Broadcast / Multicast requirements supporting Mission Critical Services in 5G | 5MBS_eMC | 1 | Rel-17 | S1 | Mon 02/09/19 | Thu 12/12/19 | 100% | SP-190942 |  | Toobe, Jens, BDBOS | jens.toobe at bdbos.bmi.bund.de | ; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100 | 22.261 | 85 | 43 |  |  | Fri 13/09/19 | Fri 06/12/19
227 | 880006 | Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services | FS_5MBS_SEC | 1 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 75% | SP-200351 |  | Longhua Guo, Huawei Technologies | guolonghua@huawei.com | 28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21 | 33.85 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
228 | 850035 | Study on Mission Critical services over 5G multicast-broadcast system | FS_MC5MBS | 1 | Rel-17 | S6 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190929 |  | Val Oprescu, AT&T |  | ; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100 | New ; 23.774; 33.524 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
229 | 860048 | NR multicast and broadcast services | NR_MBS | 1 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-193248 |  | Huawei |  | affects: NR. no Perf. part |  | 86 | 44 |  |  | Tue 14/01/20 | NA
230 | 860148 | Core part: NR multicast and broadcast services | NR_MBS-Core | 2 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-201038 |  | Huawei |  | affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
231 | 800023 | Study on Mission Critical services support over 5G System | FS_MCOver5GS | 1 | Rel-17 | S6 | Wed 06/06/18 | Wed 08/09/21 | 80% | SP-200837 |  | Verweij, Kees, The Police of the Netherlands | kees.verweij@politie.nl | 6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 28/6/20: 45%-... | New; 23.783 | 80 | 41 |  |  | Wed 06/06/18 | Fri 11/06/21
232 | 920051 | Mission Critical Services over 5GS | MCOver5GS | 1 | Rel-17 | S6 | Wed 16/09/20 | Sat 12/03/22 | 50% | SP-200833 |  | Wendler, Ingo, UIC | ingo.wendler@sbb.ch | 25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65 | 23.289 | 89 | 45 |  |  | Fri 11/09/20 | Sun 21/03/21
233 | 890027 | Stage 2 of MCOver5GS | MCOver5GS | 2 | Rel-17 | S6 | Wed 16/09/20 | Tue 15/06/21 | 100% | SP-200833 |  | Wendler, Ingo, UIC | ingo.wendler@sbb.ch | 25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100 | 23.289 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
234 | 920007 | CT1 aspects of MCOver5GS | MCOver5GS | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211118 |  | Gkatzikis, Lazaros, Nokia | lazaros(dot)gkatzikis(at)nokia(dot)com |  | 24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 |  |  |  |  | Fri 11/06/21 | NA
235 | 890039 | Mission Critical Data | eMCData3 | 1 | Rel-17 |  | Fri 06/12/19 | Wed 15/09/21 | 75% | SP-191106 |  | Shih, Jerry, AT&T | jerry.shih@att.com | ; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70 | 23.280; 23.282 | 86 | 44 |  |  | Fri 06/12/19 | Sun 13/09/20
236 | 860007 | Stage 2 of MCData3 | eMCData3 | 2 | Rel-17 | S6 | Fri 06/12/19 | Tue 15/06/21 | 100% | SP-191106 |  | Shih, Jerry, AT&T | jerry.shih@att.com | ; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100 | 23.280; 23.282 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
237 | 890038 | CT aspects of eMCData3 | eMCData3 | 2 | Rel-17 | C1 | Wed 17/06/20 | Wed 15/09/21 | 45% | CP-201177 |  |  |  | 5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45 |  | 89 | 45 |  |  | Fri 25/09/20 | Fri 11/06/21
238 | 880020 | Protocol enhancements for Mission Critical Services | MCProtoc17 | 1 | Rel-17 | C1 | Fri 25/09/20 | Mon 20/09/21 | 50% | CP-202193 |  | AXELL, Jörgen | jorgen.axell@ericsson.com | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
239 | 820040 | Mission Critical system migration and interconnection | MCSMI_CT | 1 | Rel-17 | C1 | Thu 13/12/18 | Thu 12/12/19 | 5% | CP-190143 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | ¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation) | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 | 82 | 42 |  |  | Fri 07/12/18 | Fri 13/09/19
240 | 890003 | CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI_CT | 1 | Rel-17 | C1 | Wed 16/09/20 | Wed 08/09/21 | 60% | eMCCI_CT |  | Mike Dolan, FirstNet | michael.dolan@firstnet.gov | 5/12/20: 0%->60 | 29.379; 29.380; 29.582 | 89 | 45 |  |  | Fri 25/09/20 | Sat 05/12/20
241 | 0 | Rel-17 Edge computing | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
242 | 880042 | Architecture for enabling Edge Applications | EDGEAPP | 1 | Rel-17 |  | Thu 07/03/19 | Fri 10/12/21 | 74% | SP-200109 |  | Gupta, Nishant, Samsung | nishant.gup@samsung.com | 25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20 | 23.222, 23.558 | 86 | 44 |  |  | Fri 06/12/19 | Thu 26/03/20
243 | 830008 | Study on Application Architecture for enabling Edge Applications | FS_EDGEAPP | 2 | Rel-17 | S6 | Thu 07/03/19 | Thu 05/12/19 | 100% | SP-190065 |  | Nishant Gupta, Samsung | nishant.gup@samsung.com | 31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Thu 26/03/20
244 | 860006 | Architecture for enabling Edge Applications | EDGEAPP | 2 | Rel-17 | S6 | Fri 06/12/19 | Tue 15/06/21 | 100% | SP-200886 |  | Gupta, Nishant, Samsung | nishant.gup@samsung.com | 25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85%... | 23.222, 23.558 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
245 | 900006 | CT aspects for Enabling Edge Applications | EDGEAPP | 2 | Rel-17 |  | Mon 07/12/20 | Fri 10/12/21 | 41% | CP-211196 |  | Narendranath Durga Tangudu | n.tangudu@samsung.com | 29.222 ; 11/6/21: WID:CP-203106->CP-211196 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
246 | 900034 | CT1 aspects for Enabling Edge Applications | EDGEAPP | 3 | Rel-17 | C1 | Mon 07/12/20 | Fri 10/09/21 | 30% | CP-211196 |  | Narendranath Durga Tangudu | n.tangudu@samsung.com | 29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
247 | 900035 | CT3 aspects for Enabling Edge Applications | EDGEAPP | 3 | Rel-17 | C3 | Mon 07/12/20 | Fri 10/12/21 | 50% | CP-211196 |  | Narendranath Durga Tangudu | n.tangudu@samsung.com | 29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
248 | 830032 | Study on enhancement of support for Edge Computing in 5GC | FS_enh_EC | 1 | Rel-17 | S2 | Thu 07/03/19 | Tue 15/12/20 | 100% | SP-200093 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Sat 05/12/20
249 | 910048 | Enhancement of support for Edge Computing in 5G Core network | eEDGE_5GC | 1 | Rel-17 |  | Thu 03/12/20 | Fri 11/03/22 | 43% | SP-201107 |  | Hui Ni, Huawei Technologies | hui.ni@huawei.com | 23.501; 23.502; 23.503 |  | 90 |  |  |  | Thu 03/12/20 | NA
250 | 900016 | Stage 2 of eEDGE_5GC | eEDGE_5GC | 2 | Rel-17 | S2 | Thu 03/12/20 | Wed 08/09/21 | 75% | SP-201107 |  | Hui Ni, Huawei Technologies | hui.ni@huawei.com | 23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21 |  | 90 |  |  |  | Thu 03/12/20 | Fri 11/06/21
251 | 910005 | CT aspects of 5G eEDGE | eEDGE_5GC | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 35% | CP-211092 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | [6 empty] | Thu 18/03/21 | NA
252 | 910049 | CT1 aspects of 5G eEDGE | eEDGE_5GC | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 40% | CP-211092 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 11/6/21: 0%->40 | 24.008; 24.501; 24.526; 27.007 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
253 | 910050 | CT3 aspects of 5G eEDGE | eEDGE_5GC | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 40% | CP-211092 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092 | 29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
254 | 910051 | CT4 aspects of 5G eEDGE | eEDGE_5GC | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 25% | CP-211092 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 11/6/21: 0%->25 | 29.244; 29.510; 29.502; 29.503; 29.505; 29.571 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
255 | 920026 | Security Aspects of Enhancements of Support for Edge Computing in 5GC | eEDGE_5GC | 2 | Rel-17 | S3 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210423 |  | Bo Zhang, Huawei Technologies | zhangbo6@huawei.com |  | 33.501 |  |  |  |  | Fri 11/06/21 | NA
256 | 920019 | Edge Computing Management | ECM | 1 | Rel-17 | S5 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210388 |  | Deepanshu Gautam, Samsung | deepanshu<dot>g<at>samsung<dot>com |  | 28.532;28.531;28.554;28.552;28.541 |  |  |  |  | Fri 11/06/21 | NA
257 | 880002 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC | FS_eEDGE_Sec | 1 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 75% | SP-200347 |  | Bo Zhang, Huawei Technologies | zhangbo6@huawei.com | 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21 | 33.839 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
258 | 880030 | Study on charging aspects of Edge Computing | FS_EDGE_CH | 1 | Rel-17 | S5 | Thu 25/06/20 | Wed 08/09/21 | 60% | SP-200467 |  | Yizhi Yao, Intel | yizhi<dot>yao<at>intel<dot>com | 5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21 | 28.815 | 88 | 45 |  |  | Fri 26/06/20 | Sun 21/03/21
259 | 870029 | Study on enhancements of edge computing management | FS_eEDGE_Mgt | 1 | Rel-17 | S5 | Wed 25/03/20 | Wed 08/09/21 | 90% | SP-200195 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21 | New | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
260 | 0 | Rel-17 Slicing | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
261 | 920058 | Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs | NBI17 | 1 | Rel-17 |  | Fri 11/06/21 | Fri 10/03/23 | 19% | CP-211197 |  | Yali Yan, Huawei | yanyali@huawei.com | [6 empty] | Fri 11/06/21 | NA
262 | 920013 | CT1 aspects of NBI17 | NBI17 | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211197 |  | Yali Yan, Huawei | yanyali@huawei.com |  | 24.558 |  |  |  |  | Fri 11/06/21 | NA
263 | 920053 | CT3 aspects of NBI17 | NBI17 | 2 | Rel-17 | C3 | Fri 11/06/21 | Fri 10/03/23 | 35% | CP-211197 |  | Yali Yan, Huawei | yanyali@huawei.com | ; 11/6/21: 0%->35 | 29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
264 | 920054 | CT4 aspects of NBI17 | NBI17 | 2 | Rel-17 | C4 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211197 |  | Yali Yan, Huawei | yanyali@huawei.com |  | 29.518;29.503;29.272;29.336;29.571 |  |  |  |  | Fri 11/06/21 | NA
265 | 920012 | Enhancement of 5G PCC related services in Rel-17 | en5GPccSer17 | 1 | Rel-17 | C3 | Fri 11/06/21 | Fri 11/03/22 | 20% | CP-211193 |  | Xiaoyun Zhou, Huawei | zhouxiaoyun8@huawei.com | ; 11/6/21: 0%->20 | 29.214;29.519;29.594;29.521;29.514;29.513;29.512 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
266 | 900032 | Enhancement of Network Slicing Phase 2 | eNS_Ph2 | 1 | Rel-17 |  | Thu 19/09/19 | Fri 11/03/22 | 48% | SP-200976 |  | ZTE, Jinguo Zhu | Zhu dot Jinguo at zte dot com dot cn | 23.501; 23.502; 23.503 |  | 90 |  |  |  | Thu 03/12/20 | NA
267 | 850010 | Study on Enhancement of Network Slicing Phase 2 | FS_eNS_Ph2 | 2 | Rel-17 | S2 | Thu 19/09/19 | Fri 12/03/21 | 100% | SP-190931 |  | So, Tricci, ZTE | tso@ztetx.com | ; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100 | New ; 23.700-40 | 85 | 43 |  |  | Fri 13/09/19 | Fri 19/03/21
268 | 900011 | Stage 2 for Enhancement of Network Slicing Phase 2 | eNS_Ph2 | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 5% | SP-200976 |  | ZTE, Jinguo Zhu | Zhu dot Jinguo at zte dot com dot cn | 23.501; 23.502; 23.503 ; 19/3/21: 0%->5 |  | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
269 | 920059 | Stage 3 for Enhancement of Network Slicing Phase 2 | eNS_Ph2 | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 30% | CP-210288 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | [6 empty] | Thu 18/03/21 | NA
270 | 910041 | CT1 aspects of eNS_Ph2 | eNS_Ph2 | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 30% | CP-210288 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | 11/6/21: 0%->30 | 24.501 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
271 | 910042 | CT3 aspects of eNS_Ph2 | eNS_Ph2 | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 30% | CP-210288 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | 11/6/21: 0%->30 | 29.522 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
272 | 910043 | CT4 aspects of eNS_Ph2 | eNS_Ph2 | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 30% | CP-210288 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | 11/6/21: 0%->30 | 29.510; 29.518; 29.502; 29.524 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
273 | 911007 | Enhancement of RAN slicing for NR | NR_slice | 1 | Rel-17 | R2 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210912 |  | CMCC |  | follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part | [5 empty] | Wed 07/04/21 | NA
274 | 911107 | Core part: Enhancement of RAN slicing for NR | NR_slice-Core | 2 | Rel-17 | R2 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210912 |  | CMCC |  | follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part | [5 empty] | Wed 07/04/21 | NA
275 | 860022 | Study on network slice management enhancement | FS_NSMEN | 1 | Rel-17 | S5 | Fri 06/12/19 | Wed 08/09/21 | 80% | SP-200766 |  | Brendan Hassett, Huawei Technologies Sweden AB, | brendan.t.hassett@huawei.com | 13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21 |  | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
276 | 900023 | Study on Charging Aspects for Network Slicing Phase 2 | FS_NETSLICE_CH_Ph2 | 1 | Rel-17 | S5 | Tue 12/01/21 | Fri 10/09/21 | 15% | SP-201082 |  | Matrixx, Gerald Görmer | Gerald dot Goermer at Matrixx dot com | 21/3/21: 0%->15 |  | 90 |  |  |  | Tue 12/01/21 | Sun 21/03/21
277 | 910023 | Study on enhanced security for network slicing Phase 2 | FS_eNS2_SEC | 1 | Rel-17 | S3 | Thu 18/03/21 | Fri 10/12/21 | 15% | SP-210106 |  | Zander Lei, Huawei | lei.zhongding@huawei.com | ; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21 | New |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
278 | 910026 | Study on network slice management capability exposure | FS_NSCE | 1 | Rel-17 | S5 | Thu 18/03/21 | Fri 10/12/21 | 5% | SP-210131 |  | Xiaobo Yu, Alibaba Group | shibo.yxb@alibaba-inc.com | ; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21 | New |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
279 | 910095 | Study on 5G NR UE full stack testing for Network Slicing | FS_NR_Slice_Test | 1 | Rel-17 | R5 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210371 |  | CMCC |  | TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) | [5 empty] | Wed 07/04/21 | NA
280 | 0 | Rel-17 Multi-(U)SIM | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
281 | 840049 | Support for Multi-USIM Devices | MUSIM | 1 | Rel-17 |  | Thu 07/03/19 | Fri 11/03/22 | 73% | SP-190309 |  | Liao, Ellen C, Intel | ellen.c.liao@intel.com |  | 22.261; 22.278; 22.101 | 84 | 43 |  |  | Fri 31/05/19 | NA
282 | 830019 | Study on MUSIM | FS_MUSIM | 2 | Rel-17 | S1 | Thu 07/03/19 | Fri 06/09/19 | 100% | SP-190091 | - | Liao, Ellen C, Intel | ellen.c.liao@intel.com | 14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Fri 06/12/19
283 | 840040 | Stage 1 of MUSIM | MUSIM | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190309 |  | Liao, Ellen C, Intel | ellen.c.liao@intel.com | 13/9/19: 0%->50; 6/12/19: 50%->100 | 22.261; 22.278; 22.101 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
284 | 820012 | Study on Stage 2 (System Enablers) for MUSIM | FS_MUSIM | 2 | Rel-17 | S2 | Thu 07/03/19 | Fri 12/03/21 | 95% | SP-200297 |  | Sašo Stojanovski, Intel | saso stojanovski intel com) | 21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2... | 23.761 | 82 | 42 |  |  | Thu 06/12/18 | Fri 19/03/21
285 | 900013 | System enablers for Multi-USIM devices | MUSIM | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 20% | SP-210091 |  | Sašo Stojanovski, Intel | saso stojanovski intel com | 23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091 |  | 90 |  |  |  | Thu 03/12/20 | Sun 13/06/21
286 | 910015 | CT aspects of Enabling Multi-USIM Devices | MUSIM | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 40% | CP-210280 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com |  | 24.501; 24.301; 27.007; 29.274 |  |  |  |  | Thu 18/03/21 | NA
287 | 910063 | CT1 aspects of Enabling Multi-USIM Devices | MUSIM | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 40% | CP-210280 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | ; 11/6/21: 0%->40 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
288 | 910064 | CT4 aspects of Enabling Multi-USIM Devices | MUSIM | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 40% | CP-210280 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | ; 11/6/21: 0%->40 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
289 | 900017 | Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) | FS_MUSIM_SEC | 2 | Rel-17 | S3 | Fri 04/12/20 | Fri 10/12/21 | 96% | SP-201018 |  | Abhijeet Kolekar, Intel Corporation | abhijeet.kolekar@intel.com | 5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21 | 33.873 | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
290 | 860063 | Support for Multi-SIM devices for LTE/NR | LTE_NR_MUSIM | 1 | Rel-17 |  | Mon 09/12/19 | Thu 17/06/21 | 0% | RP-210316 |  | Vivo |  | 28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316 |  | 86 |  |  |  | Wed 10/06/20 | Wed 07/04/21
291 | 860163 | Core part: Support for Multi-SIM devices for LTE/NR | LTE_NR_MUSIM-Core | 2 | Rel-17 | R2 | Mon 09/12/19 | Thu 17/06/21 | 0% | RP-210316 |  | Vivo |  |  |  | 86 |  |  |  | Wed 10/06/20 | Tue 28/07/20
292 | 0 | Rel-17 other cross-TSG Features | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
293 | 910007 | Start of Pause of Charging via User Plane | SPOCUP | 1 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/06/21 | 100% | CP-210076 |  | YONG, YANG, Ericsson, frank | yong.yang@ericsson.com | ; 21/3/21: 0%->85; 11/6/21: 85%->100 | 29.244; 29.060; 29.281; 29.274; 29.502 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
294 | 910030 | File Management | FIMA | 1 | Rel-17 | S5 | Thu 18/03/21 | Fri 10/12/21 | 25% | SP-210135 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | ; 11/6/21: 0%->25 | 28.537; 28.622; 28.623; 28.532 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
295 | 910024 | Enhancements of 3GPP profiles for cryptographic algorithms and security protocols | eCryptPr | 1 | Rel-17 | S3 | Thu 18/03/21 | Fri 10/12/21 | 35% | SP-210107 |  | Pinar Comak, Ericsson | pinar.comak@ericsson.com | ; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21 | 33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
296 | 920027 | AKMA TLS protocol profiles | AKMA_TLS | 1 | Rel-17 | S3 | Fri 11/06/21 | Sun 12/09/21 | 0% | SP-210424 |  | Escott, Adrian, Qualcomm Incorporated | aescott@qti.qualcomm.com |  | 33.535 |  |  |  |  | Fri 11/06/21 | NA
297 | 910025 | User Plane Integrity Protection for LTE | UPIP_SEC_LTE | 1 | Rel-17 | S3 | Thu 18/03/21 | Fri 10/12/21 | 85% | SP-210105 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | ; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21 | 33.401; 33.501 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
298 | 900002 | Restoration of PDN Connections in PGW-C/SMF Set | RPCPSET | 1 | Rel-17 | C4 | Mon 07/12/20 | Fri 18/12/20 | 100% | CP-203020 |  | LANDAIS, Bruno, Nokia | bruno.landais@nokia.com | 23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100 |  | 90 |  |  |  | Sat 05/12/20 | Sat 05/12/20
299 | 900037 | Enhancement of Inter-PLMN Roaming | EoIPR | 1 | Rel-17 | C4 | Mon 07/12/20 | Fri 10/09/21 | 35% | CP-203021 |  | Caixia Qi, Huawei | Caixia.qi@huawei.com | 29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
300 | 911037 | Reliable Data Service Serialization Indication | RDSSI | 1 | Rel-17 |  | Thu 09/05/19 | Sun 12/09/21 | 100% | SP-190446 |  | Starsinic, Michael, Convida Wireless LLC | starsinic.michael@convidawireless.com |  | 23.682; 23.501; 23.502 | 84 | 43 |  |  | Fri 31/05/19 | Thu 06/06/19
301 | 840017 | Stage 2 of RDSSI | RDSSI | 2 | Rel-17 | S2 | Thu 09/05/19 | Thu 06/06/19 | 100% | SP-190446 |  | Starsinic, Michael, Convida Wireless LLC | starsinic.michael@convidawireless.com | 6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17 | 23.682; 23.501; 23.502 | 84 | 43 |  |  | Fri 31/05/19 | Thu 06/06/19
302 | 900005 | CT aspects of RDSSI | RDSSI | 2 | Rel-17 | C1 | Mon 07/12/20 | Sun 12/09/21 | 100% | CP-203234 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 24.250; 29.122 ; 21/3/21: 0%->100 |  | 90 |  |  |  | Sat 05/12/20 | Sun 21/03/21
303 | 900021 | Management Aspects of 5G Network Sharing | MANS | 1 | Rel-17 | S5 | Fri 04/12/20 | Fri 10/09/21 | 25% | SP-201080 |  | Mingrui Sun, China Unicom | sunmr19@chinaunicom.cn | 32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25 |  | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
304 | 920018 | Study on Management Aspects of 5G Network Sharing | FS_MANS | 1 | Rel-17 | S5 | Fri 11/06/21 | Sun 12/12/21 | 0% | SP-210387 |  | Mingrui Sun, China Unicom | sunmr19@chinaunicom.cn |  | New |  |  |  |  | Fri 11/06/21 | NA
305 | 900019 | Adapting BEST for use in 5G networks | BEST_5G | 1 | Rel-17 | S3 | Fri 04/12/20 | Fri 10/12/21 | 70% | SP-201020 |  | Keesmaat, Iko, KPN | iko.keesmaat@tno.nl | 33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21 |  | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
306 | 920049 | Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | 1 | Rel-17 | S6 | Fri 04/12/20 | Sat 12/03/22 | 21% | SP-200987 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35 |  | 90 |  |  |  | Fri 04/12/20 | Sun 21/03/21
307 | 900024 | Stage 2 of eSEAL | eSEAL | 2 | Rel-17 | S6 | Fri 04/12/20 | Tue 15/06/21 | 80% | SP-200987 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80 |  | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
308 | 920006 | CT1 aspects of eSEAL | eSEAL | 2 | Rel-17 | C1 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211117 |  | Sapan Shah (Samsung Electronics) | sapan.shah@samsung.com |  | 29.549;24.548;24.547;24.546;24.545 |  |  |  |  | Fri 11/06/21 | NA
309 | 920050 | CT3 aspects of eSEAL | eSEAL | 2 | Rel-17 | C3 | Fri 11/06/21 | Sat 12/03/22 | 0% | CP-211117 |  | Sapan Shah (Samsung Electronics) | sapan.shah@samsung.com |  | 29.549 |  |  |  |  | Fri 11/06/21 | NA
310 | 900033 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | ATSSS_Ph2 | 1 | Rel-17 |  | Thu 07/03/19 | Fri 11/03/22 | 61% | SP-200977 |  | Apostolis Salkintzis, Lenovo | y1026c@lenovo.com | 23.501; 23.502; 23.503 |  | 90 |  |  |  | Thu 03/12/20 | NA
311 | 840084 | Study on ATSSS_Ph2 | FS_ATSSS_Ph2 | 2 | Rel-17 | S2 | Thu 07/03/19 | Tue 15/12/20 | 100% | SP-200095 |  | So, Tricci, ZTE | tso@ztetx.com | 25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100 | New 23.700-93 | 84 | 43 |  |  | Wed 26/06/19 | Fri 19/03/21
312 | 900012 | Stage 2 of ATSSS_Ph2 | ATSSS_Ph2 | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 55% | SP-200977 |  | Apostolis Salkintzis, Lenovo | y1026c@lenovo.com | 23.501; 23.502; 23.503 ; 19/3/21: 0%->55 |  | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
313 | 910013 | CT aspects of ATSSS_Ph2 | ATSSS_Ph2 | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 38% | CP-210136 |  | ZHOU Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | [6 empty] | Thu 18/03/21 | NA
314 | 910056 | CT1 aspects of ATSSS_Ph2 | ATSSS_Ph2 | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 60% | CP-210136 |  | ZHOU Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 11/6/21: 0%->60 | 24.193; 24.301; 24.501 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
315 | 910057 | CT3 aspects of ATSSS_Ph2 | ATSSS_Ph2 | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 50% | CP-210136 |  | ZHOU Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 11/6/21: 0%->50 | 29.512 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
316 | 910058 | CT4 aspects of ATSSS_Ph2 | ATSSS_Ph2 | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 5% | CP-210136 |  | ZHOU Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 11/6/21: 0%->5 | 29.244; 29.502; 29.518 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
317 | 900031 | Enablers for Network Automation for 5G - phase 2 | eNA_Ph2 | 1 | Rel-17 |  | Thu 06/06/19 | Fri 11/03/22 | 50% | SP-200975 |  | TBD |  | 23.501; 23.502; 23.503; 23.288 |  | 90 |  |  |  | Thu 03/12/20 | NA
318 | 840022 | Study on Enablers for Network Automation for 5G - phase 2 | FS_eNA_Ph2 | 2 | Rel-17 | S2 | Thu 06/06/19 | Tue 15/12/20 | 100% | SP-200098 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com | 8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/... | New ; 23.700-91 | 84 | 43 |  |  | Fri 31/05/19 | Fri 19/03/21
319 | 900010 | Stage 2 of eNA_Ph2 | eNA_Ph2 | 2 | Rel-17 | S2 | Thu 03/12/20 | Fri 11/06/21 | 40% | SP-200975 |  | TBD |  | 23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40 |  | 90 |  |  |  | Thu 03/12/20 | Fri 19/03/21
320 | 910012 | CT aspects of eNA_Ph2 | eNA_Ph2 | 2 | Rel-17 | ct | Fri 19/03/21 | Fri 11/03/22 | 12% | CP-211191 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | ; 11/6/21: WID:CP-210290->CP-211191 | 29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 |  |  |  |  | Fri 19/03/21 | Fri 11/06/21
321 | 910088 | CT3 aspects of eNA_Ph2 | eNA_Ph2 | 3 | Rel-17 | C3 | Fri 19/03/21 | Fri 11/03/22 | 20% | CP-211191 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | ; 11/6/21: 0%->20 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
322 | 910089 | CT4 aspects of eNA_Ph2 | eNA_Ph2 | 3 | Rel-17 | C4 | Fri 19/03/21 | Fri 11/03/22 | 5% | CP-211191 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | ; 11/6/21: 0%->5 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
323 | 890015 | Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 | FS_eNA_SEC | 2 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 50% | SP-200722 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21 | 33.866 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
324 | 900030 | Proximity based Services in 5GS | 5G_ProSe | 1 | Rel-17 |  | Thu 07/03/19 | Fri 11/03/22 | 65% | SP-200972 |  | TBD |  |  |  | 88 | 45 |  |  | Thu 03/12/20 | NA
325 | 830033 | Study on System enhancement for Proximity based Services in 5GS | FS_5G_ProSe | 2 | Rel-17 | S2 | Thu 07/03/19 | Fri 12/03/21 | 100% | SP-190443 |  | Qiang Deng, CATT | dengqiang1@catt.cn | 7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21:... | 23.752; 23.752 | 83 | 42 |  |  | Thu 14/03/19 | Fri 11/06/21
326 | 900007 | Stage 2 for Proximity based Services in 5GS | 5G_ProSe | 2 | Rel-17 | S2 | Thu 03/12/20 | Wed 08/09/21 | 85% | SP-201096 |  | Qiang Deng, CATT | dengqiang1@catt.cn | 19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21 |  | 90 |  |  |  | Thu 03/12/20 | Fri 11/06/21
327 | 910018 | CT aspects of proximity based services in 5GS | 5G_ProSe | 2 | Rel-17 | ct | Thu 18/03/21 | Fri 11/03/22 | 37% | CP-211110 |  | Yong Jiang, CATT | jiangyong@catt.cn | ; 11/6/21: WID:CP-210292->CP-211110 | 23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
328 | 910072 | CT1 aspects of 5G_ProSe | 5G_ProSe | 3 | Rel-17 | C1 | Thu 18/03/21 | Fri 11/03/22 | 50% | CP-211110 |  | Yong Jiang, CATT | jiangyong@catt.cn | ; 11/6/21: 0%->50 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
329 | 910073 | CT3 aspects of 5G_ProSe | 5G_ProSe | 3 | Rel-17 | C3 | Thu 18/03/21 | Fri 11/03/22 | 35% | CP-211110 |  | Yong Jiang, CATT | jiangyong@catt.cn | ; 11/6/21: 0%->35 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
330 | 910074 | CT4 aspects of 5G_ProSe | 5G_ProSe | 3 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 25% | CP-211110 |  | Yong Jiang, CATT | jiangyong@catt.cn | ; 11/6/21: 0%->25 | [5 empty] | Thu 18/03/21 | Fri 11/06/21
331 | 890018 | Study on charging aspects of Enhanced Proximity-based Services in 5GC | FS_5G_Prose_CH | 2 | Rel-17 | S5 | Wed 16/09/20 | Fri 11/06/21 | 40% | SP-200767 |  | Shu, Min, CATT | shumin@catt.cn | 25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40 | 32.846 | 89 | 45 |  |  | Thu 10/09/20 | Sun 21/03/21
332 | 880005 | Study on Security Aspects of Enhancement for Proximity Based Services in 5GS | FS_5G_ProSe_Sec | 2 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 75% | SP-200350 |  | Wei Zhou, CATT | zhouwei@catt.cn | 28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21 | 33.847 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
333 | 911005 | NR Sidelink Relay | NR_SL_relay | 1 | Rel-17 |  | Fri 12/03/21 | Thu 08/09/22 | 0% | RP-210904 |  | OPPO |  | follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay | [5 empty] | Wed 07/04/21 | NA
334 | 911105 | Core part: NR Sidelink Relay | NR_SL_relay-Core | 2 | Rel-17 | R2 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210904 |  | OPPO |  | follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay | [5 empty] | Wed 07/04/21 | NA
335 | 911205 | Perf. part: NR Sidelink Relay | NR_SL_relay-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Thu 08/09/22 | 0% | RP-210904 |  | OPPO |  | follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay | [5 empty] | Wed 07/04/21 | NA
336 | 890030 | Authentication and key management for applications based on 3GPP credential in 5G | AKMA | 1 | Rel-17 |  | Thu 19/09/19 | Wed 08/09/21 | 96% | SP-190711 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | ; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17 | New ; 33.535 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
337 | 850021 | SA3 aspects of AKMA | AKMA | 2 | Rel-17 | S3 | Thu 19/09/19 | Fri 12/06/20 | 98% | SP-190711 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | ; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98 | New ; 33.535 | 85 | 43 |  |  | Fri 13/09/19 | Fri 19/03/21
338 | 890008 | CT aspects of AKMA | AKMA-CT | 2 | Rel-17 | ct | Wed 16/09/20 | Wed 08/09/21 | 96% | CP-203107 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254 |  | 89 | 45 |  |  | Fri 11/09/20 | Fri 25/09/20
339 | 890031 | CT1 aspects of AKMA | AKMA-CT | 3 | Rel-17 | C1 | Wed 16/09/20 | Fri 12/03/21 | 95% | CP-203107 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 21/3/21: 0%->95 | 24.501 | 89 | 45 |  |  | Fri 11/09/20 | Sun 21/03/21
340 | 890032 | CT3 aspects of AKMA | AKMA-CT | 3 | Rel-17 | C3 | Wed 16/09/20 | Fri 12/03/21 | 97% | CP-203107 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97 | 29.522 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
341 | 890033 | CT4 aspects of AKMA | AKMA-CT | 3 | Rel-17 | C4 | Wed 16/09/20 | Wed 08/09/21 | 95% | CP-203107 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95 | 29.503; 29.510; 29.571 | 89 | 45 |  |  | Fri 11/09/20 | Sun 21/03/21
342 | 890049 | Enhancement of Private Network support for NG-RAN | NG_RAN_PRN_enh | 1 | Rel-17 | R3 | Thu 17/09/20 | Thu 17/06/21 | 0% | RP-202363 |  | China Telecom |  | follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 06/01/21
343 | 890149 | Core part: Enhancement of Private Network support for NG-RAN | NG_RAN_PRN_enh-Core | 2 | Rel-17 | R3 | Thu 17/09/20 | Thu 17/06/21 | 0% | RP-202363 |  | China Telecom |  | follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? |  | 89 | 45 |  |  | Fri 25/09/20 | NA
344 | 840046 | Multimedia Priority Service (MPS) Phase 2 | MPS2 | 1 | Rel-17 |  | Fri 15/12/17 | Fri 11/06/21 | 79% | SP-190305 |  | Singh, Ray P; Perspecta Labs | rsingh@perspectalabs.com |  | 22.953; 22.153 | 84 | 43 |  |  | Fri 31/05/19 | NA
345 | 780005 | Study on MPS2 | FS_MPS2 | 2 | Rel-17 | S1 | Fri 15/12/17 | Thu 12/09/19 | 100% | SP-190315 |  | Singh, Ray P; Vencore Labs | rsingh@vencorelabs.com | 16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100 | 22.854 | 78 | 40 |  |  | Fri 15/12/17 | Mon 17/08/20
346 | 850011 | Study on MPS2, Stage 2 | FS_MPS2_St2 | 2 | Rel-17 | S2 | Thu 19/09/19 | Fri 12/06/20 | 0% | SP-190629 |  | Don Lukacs; Perspecta Labs | dlukacs@perspectalabs.com | ; 8/10/19: 23.775 added; | New ; 23.775 | 85 | 43 |  |  | Fri 13/09/19 | Tue 08/10/19
347 | 840032 | Stage 1 of MPS2 | MPS2 | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190561 |  | Singh, Ray P; Perspecta Labs | rsingh@perspectalabs.com | 13/9/19: 0%->85; 6/12/19: 85%->100 | 22.953; 22.153 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
348 | 870002 | Stage 2 of MPS2 | MPS2 | 2 | Rel-17 | S2 | Wed 25/03/20 | Fri 11/06/21 | 99% | SP-200519 |  | Streijl, Robert, Perspecta Labs | rstreijl@perspectalabs.com | 25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99 |  | 87 | 44 |  |  | Wed 25/03/20 | Fri 11/06/21
349 | 880031 | Stage 3 of MPS2 | MPS2 | 2 | Rel-17 | ct | Thu 25/06/20 | Mon 15/03/21 | 73% | CP-201207 |  | Peter Monnes, Perspecta Labs | pmonnes@perspectalabs.com | 24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 |  | 88 | 45 |  |  | Fri 26/06/20 | NA
350 | 880050 | CT1 aspects of MPS2 | MPS2 | 3 | Rel-17 | C1 | Thu 25/06/20 | Mon 15/03/21 | 80% | CP-201207 |  | Peter Monnes, Perspecta Labs | pmonnes@perspectalabs.com | 24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80 |  | 88 | 45 |  |  | Fri 26/06/20 | Sun 21/03/21
351 | 880058 | CT3 aspects of MPS2 | MPS2 | 3 | Rel-17 | C3 | Thu 25/06/20 | Mon 15/03/21 | 70% | CP-201207 |  | Peter Monnes, Perspecta Labs | pmonnes@perspectalabs.com | 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
352 | 880051 | CT4 aspects of MPS2 | MPS2 | 3 | Rel-17 | C4 | Thu 25/06/20 | Mon 15/03/21 | 70% | CP-201207 |  | Peter Monnes, Perspecta Labs | pmonnes@perspectalabs.com | 29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
353 | 890011 | Mission critical security enhancements phase 2 | MCXSec2 | 1 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 80% | SP-200879 |  | Woodward, Tim, Motorola Solutions, Inc, | tim.woodward@motorolasolutions.com | ; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21 | 33.18 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
354 | 890070 | PAP/CHAP protocols usage in 5GS | PAP_CHAP | 1 | Rel-17 | ct | Wed 16/09/20 | Fri 10/09/21 | 99% | CP-202251 |  | Mingxue Li, China Telecom | limx36@chinatelecom.cn | 24.501; 29.561 |  | 89 | 45 |  |  | Fri 25/09/20 | NA
355 | 890071 | CT1 aspects of PAP/CHAP protocols usage in 5GS | PAP_CHAP | 2 | Rel-17 | C1 | Wed 16/09/20 | Fri 10/09/21 | 100% | CP-202251 |  | Mingxue Li, China Telecom | limx36@chinatelecom.cn | 24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100 |  | 89 | 45 |  |  | Fri 25/09/20 | Fri 11/06/21
356 | 890072 | CT3 aspects of PAP/CHAP protocols usage in 5GS | PAP_CHAP | 2 | Rel-17 | C3 | Wed 16/09/20 | Fri 12/03/21 | 100% | CP-210188 |  | Mingxue Li, China Telecom | limx36@chinatelecom.cn | 29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100 |  | 89 | 45 |  |  | Fri 25/09/20 | Fri 11/06/21
357 | 890001 | Service-based support for SMS in 5GC | SMS_SBI | 1 | Rel-17 |  | Wed 16/09/20 | Wed 08/09/21 | 23% | CP-202242 |  | HAOUARI, Wafa, Orange | wafa.haouari@orange.com | 25/9/20: WID:CP-202028->CP-202242 |  | 89 | 45 |  |  | Fri 11/09/20 | Fri 25/09/20
358 | 890028 | CT1 aspects of SMS_SBI | SMS_SBI | 2 | Rel-17 | C1 | Wed 16/09/20 | Fri 12/03/21 | 0% | CP-202242 |  | HAOUARI, Wafa, Orange | wafa.haouari@orange.com |  | 23.04 | 89 | 45 |  |  | Fri 11/09/20 | NA
359 | 890029 | CT4 aspects of SMS_SBI | SMS_SBI | 2 | Rel-17 | C4 | Wed 16/09/20 | Wed 08/09/21 | 35% | CP-202242 |  | HAOUARI, Wafa, Orange | wafa.haouari@orange.com | 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35 | 29.503; 29.540; 29.571 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
360 | 840048 | Enhanced Relays for Energy eFficiency and Extensive Coverage | REFEC | 1 | Rel-17 |  | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-190307 |  | Norp, Toon, KPN | toon.norp@tno.nl |  | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | NA
361 | 810018 | Study on REFEC | FS_REFEC | 2 | Rel-17 | S1 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180785 |  | Jose Luis Almodovar Chico, KPN | jose.almodovarchico@tno.nl | 4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100 | 22.866 | 81 | 41 |  |  | Thu 06/09/18 | Fri 06/12/19
362 | 840034 | Stage 1 of REFEC | REFEC | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-190307 |  | Norp, Toon, KPN | toon.norp@tno.nl | 13/9/19: 0%->90; 6/12/19: 90%->100 | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
363 | 840044 | Network Controlled Interactive Service | NCIS | 1 | Rel-17 |  | Wed 06/06/18 | Thu 12/12/19 | 100% | SP-190303 |  | Ning YANG, oppo | yangning@oppo.com |  | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | NA
364 | 800015 | Study on NCIS | FS_NCIS | 2 | Rel-17 | S1 | Wed 06/06/18 | Thu 14/03/19 | 100% | SP-180341 |  | YANG Ning, Oppo | yangning@oppo.com | 6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100 | 22.842 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
365 | 840030 | Stage 1 of NCIS | NCIS | 2 | Rel-17 | S1 | Thu 06/06/19 | Thu 12/12/19 | 100% | SP-191039 |  | Ning YANG, oppo | yangning@oppo.com | 13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039 | 22.261 | 84 | 43 |  |  | Fri 31/05/19 | Thu 12/12/19
366 | 840019 | 5G System Enhancement for Advanced Interactive Services | 5G_AIS | 1 | Rel-17 | S2 | Thu 06/06/19 | Fri 11/06/21 | 100% | SP-190564 |  | Lei Yixue, Tencent | yixuelei@tencent.com | 5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100 | 23.501; 23.502; 23.503 | 84 | 43 |  |  | Fri 31/05/19 | Fri 11/06/21
367 | 890009 | Points for 8K VR 360 Video over 5G | 8K_VR_5G | 1 | Rel-17 | S4 | Wed 16/09/20 | Fri 11/06/21 | 100% | SP-200667 |  | Ozgur Oyman, Company: Intel | ozgur.oyman@intel.com | ; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100 | 26.118; 26.511; 26.925 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
368 | 880043 | Multi-Device and multi-identity Enhancements (MuDE) | MuDE | 1 | Rel-17 |  | Mon 02/09/19 | Fri 11/12/20 | 100% | SP-190823 |  | Adrian.buckley@vivo.com |  | ; 13/9/19: 0%->100 | 22.173 | 85 | 43 |  |  | Fri 13/09/19 | Fri 13/09/19
369 | 850041 | Stage 1 of MuDE | MuDE | 2 | Rel-17 | S1 | Mon 02/09/19 | Thu 19/09/19 | 100% | SP-190823 |  | Adrian.buckley@vivo.com |  | ; 13/9/19: 0%->100 | 22.173 | 85 | 43 |  |  | Fri 13/09/19 | Fri 13/09/19
370 | 880018 | Stage 3 of MuDE | MuDe | 2 | Rel-17 | C1 | Thu 25/06/20 | Fri 11/12/20 | 100% | CP-201162 |  | Adrian Buckley | adrian.buckley@vivo.com | 24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
371 | 920055 | Best Practice of Packet Forwarding Control Protocol (PFCP) | BEPoP | 1 | Rel-17 | ct | Thu 25/06/20 | Wed 15/09/21 | 53% | CP-210074 |  | Song Yue, China Mobile | songyue@chinamobile.com | 29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074 | 29.82 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
372 | 920056 | CT3 aspects of BEPoP | BEPoP | 2 | Rel-17 | C3 | Thu 25/06/20 | Wed 15/09/21 | 60% | CP-210074 |  | Song Yue, China Mobile | songyue@chinamobile.com | 29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60 | 29.82 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
373 | 880014 | CT4 aspects of BEPoP | BEPoP | 2 | Rel-17 | C4 | Thu 25/06/20 | Wed 15/09/21 | 45% | CP-210074 |  | Song Yue, China Mobile | songyue@chinamobile.com | 29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45 | 29.82 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
374 | 880029 | Enhancement of Handover Optimization | E_HOO | 1 | Rel-17 | S5 | Thu 25/06/20 | Fri 11/03/22 | 30% | SP-200466 |  | Elmdahl, Per, Ericsson | per dot Elmdahl at Ericsson dot com | 28.552; 28.313; 28.541 ; 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:18/06/2021->03/22; 11/6/21: 10%->30 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
375 | 880028 | Management data collection control and discovery | MADCOL | 1 | Rel-17 | S5 | Thu 25/06/20 | Wed 22/09/21 | 30% | SP-200465 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | 28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
376 | 880026 | Management of the enhanced tenant concept | eMEMTANE | 1 | Rel-17 | S5 | Fri 26/06/20 | Wed 15/12/21 | 15% | SP-200463 |  | Zhu, Lei, Huawei | lei.zhu@huawei.com | 28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
377 | 880025 | Enhancements of 5G performance measurements and KPIs | ePM_KPI_5G | 1 | Rel-17 | S5 | Fri 12/06/20 | Fri 10/09/21 | 50% | SP-200462 |  | Yizhi Yao, Intel | yizhi<dot>yao<at>intel<dot>com | 28.552; 32.425; 28.554; 32.426; 32.450; 32.451; 32.455 ; 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->40; 11/6/21: 40%->50 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
378 | 880012 | Extension for headset interface tests of UE | HInT | 1 | Rel-17 | S4 | Thu 25/06/20 | Fri 10/09/21 | 70% | SP-200398 |  | Jan Reimes, HEAD acoustics GmbH, | jan.reimes@head-acoustics.com | 26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70 |  | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
379 | 840038 | MC services support on IOPS mode of operation | MCIOPS | 1 | Rel-17 | S6 | Thu 06/06/19 | Fri 11/09/20 | 100% | SP-190944 | Camilo Solano, Ericsson | Camilo.solano@ericsson.com | 23.280; 23.379; 23.281; 23.282 | 13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100 | 23.18 | 84 | 43 |  |  | Fri 31/05/19 | Sat 05/12/20
380 | 840016 | Supporting Flexible Local Area Data Network | FLADN | 1 | Rel-17 | S2 | Thu 06/06/19 | Fri 11/09/20 | 0% | SP-190563 |  | LG Electronics, Hyunsook Kim | hyuns.kim@lge.com |  | 23.501; 23.502 | 84 | 43 |  |  | Fri 31/05/19 | NA
381 | 820003 | Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 1 | Rel-17 | S4 | Thu 13/12/18 | Fri 11/03/22 | 75% | SP-180985 |  | Ozgur Oyman, Intel | Ozgur.Oyman@Intel.com | 7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->... | 26.114; 26.223 |  |  |  |  | Thu 14/03/19 | Fri 11/06/21
382 | 830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 1 | Rel-17 | S4 | Thu 07/03/19 | Fri 02/12/22 | 20% | SP-190040 |  | Stéphane Ragot, Orange | stephane.ragot@orange.com | 31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20 | 26.260, new | 83 | 42 |  |  | Thu 14/03/19 | Sat 05/12/20
383 | 860012 | Handsets Featuring Non-Traditional Earpieces | HaNTE | 1 | Rel-17 | S4 | Fri 06/12/19 | Wed 08/09/21 | 70% | SP-190989 |  | Schevciw, Andre, Qualcomm Incorporated | aschevci@qti.qualcomm.com | 25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11... | 26.131; 26.132; 26.801 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
384 | 920008 | 5GMS AF Event Exposure | EVEX | 1 | Rel-17 | S4 | Fri 11/06/21 | Fri 11/03/22 | 0% | SP-210374 |  | Lo, Charles, Qualcomm Inc., | clo@qti.qualcomm.com |  | 26.512;26.501 |  |  |  |  | Fri 11/06/21 | NA
385 | 920009 | Edge Extensions to the 5G Media Streaming Architecture | 5GMS_EDGE | 1 | Rel-17 | S4 | Fri 11/06/21 | Wed 08/09/21 | 0% | SP-210375 |  | Bouazizi, Imed, Qualcomm Inc. | bouazizi@qti.qualcomm.com |  | 26.501 |  |  |  |  | Fri 11/06/21 | NA
386 | 920010 | 5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions | 5MBUSA | 1 | Rel-17 | S4 | Fri 11/06/21 | Fri 10/06/22 | 0% | SP-210376 |  | TAN, PENG, TELUS | peng.tan@telus.com |  | 26.501 |  |  |  |  | Fri 11/06/21 | NA
387 | 920011 | 8K Television over 5G | 8K_TV_5G | 1 | Rel-17 | S4 | Fri 11/06/21 | Fri 11/03/22 | 0% | SP-210381 |  | Thomas Stockhammer | tsto@qti.qualcomm.com |  | 26.955;26.925;26.511;26.116 |  |  |  |  | Fri 11/06/21 | NA
388 | 830017 | Verification-modified Calling Name Display | VMOD_DISPLAY | 1 | Rel-17 | S1 | Thu 07/03/19 | Thu 21/03/19 | 100% | SP-190085 |  | Hala Mowafy, Ericsson | Hala.Mowafy@ericsson.com | 14/3/19: 0%->100 | 22.173 | 83 | 42 |  |  | Fri 15/12/17 | Thu 14/03/19
389 | 850038 | Enhanced Calling Name Service Analytics Interworking | eCNAM_An | 1 | Rel-17 | S1 | Mon 02/09/19 | Thu 19/09/19 | 100% | SP-190940 |  | Hala.Mowafy@ericsson.com |  | ; 13/9/19: 0%->100 | 22.173 | 85 | 43 |  |  | Fri 13/09/19 | Fri 13/09/19
390 | 880049 | Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode | eCPSOR_CON | 1 | Rel-17 |  | Mon 02/09/19 | Fri 18/06/21 | 20% | CP-210148 |  | Minokuchi, Atsushi, NTT DOCOMO | minokuchi at nttdocomo dot com | ; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148 | 22.261 | 85 | 43 |  |  | Fri 13/09/19 | Sun 13/06/21
391 | 850039 | Stage 1 of eCPSOR_CON | eCPSOR_CON | 2 | Rel-17 | S1 | Mon 02/09/19 | Fri 18/06/21 | 10% | SP-190941 |  | Minokuchi, Atsushi, NTT DOCOMO | minokuchi at nttdocomo dot com | ; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20 | 22.261 | 85 | 43 |  |  | Fri 13/09/19 | Sat 05/12/20
392 | 880022 | Stage 3 (CT1) of eCPSOR_CON | eCPSOR_CON | 2 | Rel-17 | C1 | Thu 25/06/20 | Fri 18/06/21 | 50% | CP-210148 |  | Al-Bakri Ban, NTT DOCOMO | ban.albakri@meadowcom.com | 23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
393 | 900036 | Stage 3 (CT4) of eCPSOR_CON | eCPSOR_CON | 2 | Rel-17 | C4 | Thu 25/06/20 | Fri 18/06/21 | 10% | CP-210148 |  | Al-Bakri Ban, NTT DOCOMO | ban.albakri@meadowcom.com | 23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10 |  | 90 |  |  |  | Fri 26/06/20 | Fri 11/06/21
394 | 910090 | Integration of Generic Bootstrapping Architecture (GBA) into 5GC | GBA_5G | 1 | Rel-17 |  | Wed 06/06/18 | Sat 12/03/22 | 20% | SP-190714 |  | Vlasios Tsiatsis, Ericsson | vlasios.tsiatsis@ericsson.com | 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20 | 33.220; 33.222; 33.223; 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Sat 05/12/20
395 | 850023 | Security aspects of Integration of GBA into 5GC | GBA_5G | 2 | Rel-17 | S3 | Thu 19/09/19 | Fri 10/12/21 | 55% | SP-190714 |  | Vlasios Tsiatsis, Ericsson | vlasios.tsiatsis@ericsson.com | 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21 | 33.220; 33.222; 33.223; 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
396 | 910004 | CT aspects of Integration of GBA into SBA | GBA_5G | 2 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/03/22 | 15% | CP-210283 |  | de Gregorio, Jesús (Ericsson) | jesus.de.gregorio@ericsson.com | ; 21/3/21: 0%->5; 11/6/21: 5%->15 | 29.503; 29.505; 29.510; 29.562; 29.571 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
397 | 910047 | Integration of Generic Bootstrapping Architecture (GBA) into 5GC | GBA_5G | 2 | Rel-17 | S3 | Wed 06/06/18 | Sat 12/03/22 | 0% | SP-190714 |  | Vlasios Tsiatsis, Ericsson | vlasios.tsiatsis@ericsson.com | 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20 | 33.220; 33.222; 33.223; 33.501 | 85 | 43 |  |  | Fri 19/03/21 | NA
398 | 770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 1 | Rel-17 | S4 | Fri 08/09/17 | Fri 10/06/22 | 27% | SP-170611 |  | Bin Wang, Huawei Technologies Co Ltd | binbin.wang@huawei.com | 15/12/17: added :26.258¦26.256¦26.255¦26.254¦26.253¦26.251¦26.252¦26.250¦26.997¦15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12... | 26.114, new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997 | 77 | 39 |  |  | Fri 08/09/17 | Sat 05/12/20
399 | 850045 | Support for Minimization of service Interruption | MINT | 1 | Rel-17 |  | Thu 07/03/19 | Fri 12/03/21 | 99% | SP-190814 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com |  | 22.011; 22.261 | 85 | 43 |  |  | Fri 13/09/19 | NA
400 | 830018 | Study on MINT | FS_MINT | 2 | Rel-17 | S1 | Thu 07/03/19 | Thu 05/09/19 | 100% | SP-190090 | - | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 31/5/19: 0%->65; 13/9/19: 65%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Fri 13/09/19
401 | 850036 | Stage 1 of MINT | MINT | 2 | Rel-17 | S1 | Fri 13/09/19 | Thu 12/12/19 | 100% | SP-190938 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 13/9/19: 0%->80; 6/12/19: 80%->100 | 22.011; 22.261 | 85 | 43 |  |  | Fri 13/09/19 | Fri 06/12/19
402 | 900004 | Study on the CT aspects of Support for Minimization of service Interruption | FS_MINT-CT | 2 | Rel-17 | C1 | Mon 07/12/20 | Fri 12/03/21 | 95% | CP-203232 |  | Sang Min Park, LG Electronics | sangmin2.park@lge.com | 21/3/21: 0%->60; 11/6/21: 60%->95 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
403 | 860008 | IMS emergency support for Stand-alone Non-Public Network (SNPN) | IESNPN | 1 | Rel-17 | S1 | Fri 06/12/19 | Fri 13/12/19 | 100% | SP-191038 |  | Wong, Curt; | curt.wong@charter.com | 6/12/19: 0%->100 | 22.101; 22.261; 22.228 | 86 | 44 |  |  | Fri 06/12/19 | Fri 06/12/19
404 | 870023 | Management of non-public networks (NPN) | OAM_NPN | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 50% | SP-200189 |  | ZHANG, Kai, Huawei | kai.zhangkai@huawei.com | ; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21 | 28.541; 28.531; 28.533; 28.552; 28.554 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
405 | 860016 | Assurance Specification for IMS | SCAS_IMS | 1 | Rel-17 | S3 | Fri 06/12/19 | Fri 11/06/21 | 90% | SP-191128 |  | Bo Zhang, Huawei Technologies | zhangbo6@huawei.com | ; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90 | 33.926 | 86 |  |  |  | Fri 06/12/19 | Fri 11/06/21
406 | 870020 | Security Assurance Specification for 5G (eSCAS_5G) | eSCAS_5G | 1 | Rel-17 | S3 | Wed 25/03/20 | Fri 10/12/21 | 62% | SP-200149 |  | Rong Wu, Huawei Technologies Co. | Raina.wu@huawei.com | 26/6/20: 0%->5 | 33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519 | 87 | 44 |  |  | Wed 25/03/20 | Fri 26/06/20
407 | 890013 | eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) | SCAS_5G_NSSAAF | 2 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 45% | SP-200720 |  | Rong Wu, Huawei Technologies Co., Ltd. | Raina.wu@huawei.com | 5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21 | 33.926; 33.326 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
408 | 870017 | eSCAS_5G for Non-3GPP InterWorking Function | SCAS_5G_N3IWF | 2 | Rel-17 | S3 | Wed 25/03/20 | Fri 10/12/21 | 20% | SP-200146 |  | Feng Gao, China Unicom | gaofeng149@chinaunicom.cn | 26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21 | 33.926; 33.520 | 87 | 44 |  |  | Wed 25/03/20 | Fri 11/06/21
409 | 870018 | eSCAS_5G for 5G NWDAF | SCAS_5G_NWDAF | 2 | Rel-17 | S3 | Wed 25/03/20 | Fri 10/12/21 | 85% | SP-200147 |  | QI Minpeng, China Mobile | qiminpeng@chinamobile.com | 26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%-> | 22.521; 33.926 | 87 | 44 |  |  | Wed 25/03/20 | Fri 11/06/21
410 | 870019 | eSCAS_5G for Service Communication Proxy | SCAS_5G_SECOP | 2 | Rel-17 | S3 | Wed 25/03/20 | Fri 10/12/21 | 70% | SP-200148 |  | Wei Lu, Nokia | wei.lu@nokia-sbell.com | 26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21 | 33.522; 33.926 | 87 | 44 |  |  | Wed 25/03/20 | Fri 11/06/21
411 | 880003 | eSCAS_5Gfor Inter PLMN UP Security | SCAS_5G_IPUPS | 2 | Rel-17 | S3 | Fri 12/06/20 | Fri 10/12/21 | 90% | SP-200348 |  | Jin PENG, ZTE Corporation | peng.jin1@zte.com.cn | 33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21 |  | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
412 | 870022 | Enhancements on EE for 5G networks | EE5GPLUS | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 55% | SP-200188 |  | Jean-Michel CORNILY, ORANGE | jeanmichel.cornily@orange.com | ; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->55; 11/6/21: FCD:Wed 08/09/->12/21 | 28.310; 28.552; 28.554; 28.541 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
413 | 870024 | Enhancement on Management Aspects of 5G Service-Level Agreement | EMA5SLA | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 65% | SP-200190 |  | SHI, Xiaonan, CMCC | shixiaonan@chinamobile.com | ; 13/9/20: 0%->5; 5/12/20: 5%->40; 21/3/21: 40%->60; 21/3/21: FCD:18/03/2021->06/21; 11/6/21: 60%->65; 11/6/21: FCD:Fri 11/06/->12/21 | 28.541; 28.531 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
414 | 870025 | Management of MDT enhancement in 5G | e_5GMDT | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 75% | SP-200191 |  | Ayani, Zhulia, Ericsson | zhulia.Ayani@ericsson.com | ; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75 | 32.421; 32.422; 32.423; 28.622; 28.623; 28.523 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
415 | 870026 | Additional NRM features | adNRM | 1 | Rel-17 | S5 | Wed 05/02/20 | Tue 15/06/21 | 30% | SP-200192 |  | Jing Ping, Nokia | jing.ping@nokia-sbell.com | ; 10/6/20: FCD:19/03/2020->06/20; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->30 | 28.540; 28.541; 28.622; 28.623 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
416 | 870027 | Enhancement of QoE Measurement Collection | eQoE | 1 | Rel-17 | S5 | Wed 25/03/20 | Thu 16/09/21 | 20% | SP-200193 |  | Petersen, Robert, Ericsson | robert <dot> petersen <at>ericsson<dot>ericsson | ; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20 | 28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
417 | 860061 | Study on NR QoE (Quality of Experience) management and optimizations for diverse services | FS_NR_QoE | 1 | Rel-17 | R3 | Mon 16/12/19 | Tue 15/09/20 | 100% | RP-193256 |  | China Unicom |  | affects: NR.; 25/9/20: 38.890 added;; 7/4/21: 0%->100 | 38.89 | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
418 | 870030 | Enhanced Closed loop SLS Assurance | eCOSLA | 1 | Rel-17 | S5 | Wed 25/03/20 | Wed 08/09/21 | 50% | SP-200196 |  | Groenendijk, Jan, Ericsson | jan.groenendijk@ericsson.com | 13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21 | 28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
419 | 870034 | Enhanced Mission Critical Push-to-talk architecture phase 3 | enh3MCPTT | 1 | Rel-17 |  | Wed 25/03/20 | Wed 08/09/21 | 77% | SP-200108 |  | Dom Lazara; Motorola Solutions | Dom.Lazara@motorolasolutions.com | ; 28/6/20: 0%->20 | 23.379; 23.280; 23.281; 23.282; 23.283 | 87 | 44 |  |  | Fri 06/12/19 | Sun 28/06/20
420 | 870016 | Stage 2 aspects of enh3MCPTT | enh3MCPTT | 2 | Rel-17 | S6 | Wed 25/03/20 | Tue 15/06/21 | 100% | SP-200108 |  | Dom Lazara; Motorola Solutions | Dom.Lazara@motorolasolutions.com | ; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100 | 23.379; 23.280; 23.281; 23.282; 23.283 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
421 | 900039 | Stage 3 aspects of enh3MCPTT | enh3MCPTT-CT | 2 | Rel-17 | C1 | Mon 14/09/20 | Wed 08/09/21 | 48% | CP-202188 |  |  |  | ; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48 | 23.379; 23.280; 23.281; 23.282; 23.283 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
422 | 840028 | IMS Charging in 5G System Architecture | 5GSIMSCH | 1 | Rel-17 | S5 | Thu 06/06/19 | Fri 12/03/21 | 60% | SP-190367 |  | Jahangir, Zeeshan, T-Mobile USA | Zeeshan.jahangir@t-mobile.com | 13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60 | 32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 | 84 | 43 |  |  | Fri 31/05/19 | Sun 21/03/21
423 | 810027 | Intent driven management service for mobile network | IDMS_MN | 1 | Rel-17 | S5 | Thu 06/09/18 | Fri 10/12/21 | 70% | SP-180899 |  | Zou Lan, Huawei | zoulan@huawei.com | 7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed... | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 11/06/21
424 | 820006 | Study on User Plane Integrity Protection | FS_UP_IP_Sec | 1 | Rel-17 | S3 | Thu 13/12/18 | Fri 12/03/21 | 100% | SP-181035 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20... |  | 82 | 42 |  |  | Thu 06/12/18 | Fri 11/06/21
425 | 890012 | Enhancements to User Plane Integrity Protection Support in 5GS | eUPIP_SEC | 1 | Rel-17 | S3 | Wed 16/09/20 | Fri 12/03/21 | 100% | SP-200719 |  | Anand Palanigounder, Qualcomm Incorporated | apg@qti.qualcomm.com | ; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100 | 33.501 | 89 | 45 |  |  | Fri 11/09/20 | Fri 19/03/21
426 | 840036 | Study on support of the 5GMSG Service | FS_5GMARCH | 1 | Rel-17 | S6 | Thu 06/06/19 | Fri 11/12/20 | 100% | SP-200835 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100 | 23.700-24 | 84 | 43 |  |  | Fri 31/05/19 | Fri 11/06/21
427 | 890026 | Application Architecture for MSGin5G Service | 5GMARCH | 1 | Rel-17 | S6 | Wed 16/09/20 | Tue 15/06/21 | 75% | SP-200832 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75 | 23.554 | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
428 | 820035 | Discovery of management services in 5G | 5GDMS | 1 | Rel-17 | S5 | Thu 13/12/18 | Wed 08/09/21 | 80% | SP-200770 |  | Brendan Hassett, Huawei Technologies Sweden AB | brendan.t.hassett@huawei.com | ¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ... | 28.533; 28.532; 28.531 | 82 | 42 |  |  | Fri 07/12/18 | Fri 11/06/21
429 | 860024 | Network policy managementfor 5G mobile networks | NPM | 1 | Rel-17 | S5 | Fri 06/12/19 | Fri 11/03/22 | 75% | SP-191211 |  | China Mobile Shasha Guo | guoshasha@chinamobile.com | ; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75 | 28.532; 28.541 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
430 | 860025 | Lawful Interception Rel-17 | LI17 | 1 | Rel-17 | S3 | Tue 10/12/19 | Fri 11/03/22 | 20% | SP-190983 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20 | 33.107; 33.108; 33.126; 33.127; 33.128 | 86 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
431 | 850047 | (Small) Technical Enhancements and Improvements for Rel-17 | TEI17 | 1 | Rel-17 |  | Wed 11/03/20 | Sat 12/03/22 | 55% | [6 empty] | 85 | 43 |  |  | Mon 15/06/15 | Mon 15/06/15
432 | 870003 | IMS Optimization for HSS Group ID in an SBA environment | TEI17_IMSGID | 2 | Rel-17 | S2 | Wed 25/03/20 | Fri 12/06/20 | 100% | SP-200452 |  | Foti, George, Ericsson | George.foti@ericsson.com | 19/3/21: 0%->100 | 23.228 | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
433 | 910044 | Same PCF Selection For AMF and SMF | TEI17_SPSFAS | 2 | Rel-17 |  | Wed 25/03/20 | Wed 08/09/21 | 94% | SP-200447 |  | Heng, Nie, China Telecom | nieheng@chinatelecom.cn |  |  | 88 | 45 |  |  | Thu 25/06/20 | NA
434 | 880016 | Stage 2 for TEI17_SPSFAS | TEI17_SPSFAS | 3 | Rel-17 | S2 | Wed 25/03/20 | Fri 12/06/20 | 100% | SP-200447 |  | Heng, Nie, China Telecom | nieheng@chinatelecom.cn | 23.501, 23.502 ; 19/3/21: 0%->100 |  | 88 | 45 |  |  | Thu 25/06/20 | Fri 19/03/21
435 | 910003 | CT aspects on TEI17_SPSFAS | TEI17_SPSFAS | 3 | Rel-17 | ct | Thu 18/03/21 | Wed 08/09/21 | 92% | CP-211184 |  | Yue Sun, China Telecom | suny20@chinatelecom.cn | [6 empty] | Thu 18/03/21 | NA
436 | 910045 | CT3 aspects on TEI17_SPSFAS | TEI17_SPSFAS | 4 | Rel-17 | C3 | Thu 18/03/21 | Wed 08/09/21 | 98% | CP-211184 |  | Yue Sun, China Telecom | suny20@chinatelecom.cn | 11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184 | 29.513 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
437 | 910046 | CT4 aspects on TEI17_SPSFAS | TEI17_SPSFAS | 4 | Rel-17 | C4 | Thu 18/03/21 | Fri 11/06/21 | 80% | CP-211184 |  | Yue Sun, China Telecom | suny20@chinatelecom.cn | 11/6/21: 0%->80 | 29.502; 29.503; 29.504 |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
438 | 880017 | System enhancement for Redundant PDU Session | TEI17_SE_RPS | 2 | Rel-17 | S2 | Wed 25/03/20 | Fri 12/06/20 | 100% | SP-200448 |  | Devaki Chandramouli | devaki.chandraouli@nokia.com | ; 11/6/21: 0%->100 | 23.501, 23.502 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
439 | 910078 | Support for Signed Attestation for Priority and Emergency Sessions | TEI17_SAPES | 2 | Rel-17 |  | Wed 25/03/20 | Sun 12/09/21 | 100% | SP-200453 |  | Foti, George, Ericsson | George.foti@ericsson.com |  |  | 87 | 44 |  |  | Wed 10/06/20 | NA
440 | 870004 | Stage 2 for TEI17_SAPES | TEI17_SAPES | 3 | Rel-17 | S2 | Wed 25/03/20 | Fri 12/06/20 | 100% | SP-200453 |  | Foti, George, Ericsson | George.foti@ericsson.com | 19/3/21: 0%->100 | 23.228; 23.167 | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
441 | 910020 | CT aspects on TEI17_SAPES | TEI17_SAPES | 3 | Rel-17 | ct | Fri 19/03/21 | Sun 12/09/21 | 100% | CP-210272 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com |  | 24.229; 29.165 |  |  |  |  | Fri 19/03/21 | NA
442 | 910079 | CT1 aspects on TEI17_SAPES | TEI17_SAPES | 4 | Rel-17 | C1 | Fri 19/03/21 | Sun 12/09/21 | 100% | CP-210272 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | ; 11/6/21: 0%->100 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
443 | 910080 | CT3 aspects on TEI17_SAPES | TEI17_SAPES | 4 | Rel-17 | C3 | Fri 19/03/21 | Sun 12/09/21 | 100% | CP-210272 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | ; 11/6/21: 0%->100 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
444 | 910081 | Dynamically Changing AM Policies in the 5GC | TEI17_DCAMP | 2 | Rel-17 |  | Wed 11/03/20 | Sat 12/03/22 | 26% | SP-200446 |  | Pancorbo, Belen (Ericsson) |  |  |  | 87 | 44 |  |  | Wed 10/06/20 | NA
445 | 870005 | Stage 2 for TEI17_DCAMP | TEI17_DCAMP | 3 | Rel-17 | S2 | Wed 11/03/20 | Thu 25/06/20 | 100% | SP-200446 |  | Pancorbo, Belen (Ericsson) |  | 19/3/21: 0%->100 | 23.501; 23.502; 23.503 | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
446 | 910009 | CT aspects on TEI17_DCAMP | TEI17_DCAMP | 3 | Rel-17 | ct | Fri 19/03/21 | Sat 12/03/22 | 15% | CP-211192 |  | Garcia Azorero, Fuencisla. Ericsson | fuencisla.garcia@ericsson.com | ; 11/6/21: WID:CP-210291->CP-211192 | 29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 |  |  |  |  | Fri 19/03/21 | Fri 11/06/21
447 | 910082 | CT3 aspects on TEI17_DCAMP | TEI17_DCAMP | 4 | Rel-17 | C3 | Fri 19/03/21 | Fri 11/03/22 | 30% | CP-211192 |  | Garcia Azorero, Fuencisla. Ericsson | fuencisla.garcia@ericsson.com | ; 11/6/21: 0%->30 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
448 | 910083 | CT4 aspects on TEI17_DCAMP | TEI17_DCAMP | 4 | Rel-17 | C4 | Fri 19/03/21 | Sat 12/03/22 | 0% | CP-211192 |  | Garcia Azorero, Fuencisla. Ericsson | fuencisla.garcia@ericsson.com | [6 empty] | Fri 19/03/21 | NA
449 | 870006 | IP address pool information from UDM | TEI17_IPU | 2 | Rel-17 | S2 | Wed 11/03/20 | Thu 25/06/20 | 100% | SP-200454 |  | Stefan Rommer | stefan . rommer @ ericsson . com | 19/3/21: 0%->100 |  | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
450 | 910084 | Dynamic management of group-based event monitoring | TEI17_GEM | 2 | Rel-17 |  | Wed 11/03/20 | Sat 12/03/22 | 28% | SP-200455 |  | Qian XB Chen, Ericsson | Qian.XB.Chen@ericsson.com |  |  | 87 | 44 |  |  | Wed 10/06/20 | NA
451 | 870007 | Stage 2 for TEI17_GEM | TEI17_GEM | 3 | Rel-17 | S2 | Wed 11/03/20 | Thu 25/06/20 | 100% | SP-200455 |  | Qian XB Chen, Ericsson | Qian.XB.Chen@ericsson.com | 11/6/21: 0%->100 | 23.682 | 87 | 44 |  |  | Wed 10/06/20 | Fri 11/06/21
452 | 910010 | CT aspects on TEI17_GEM | TEI17_GEM | 3 | Rel-17 | ct | Fri 19/03/21 | Sat 12/03/22 | 17% | CP-211195 |  | Maria Tianmei, Liang, Ericsson | maría.liang@ericsson.com | ; 11/6/21: WID:CP-210185->CP-211195 | 29.122 29.336 |  |  |  |  | Fri 19/03/21 | Fri 11/06/21
453 | 910085 | CT3 aspects on TEI17_GEM | TEI17_GEM | 4 | Rel-17 | C3 | Fri 19/03/21 | Fri 11/03/22 | 35% | CP-211195 |  | Maria Tianmei, Liang, Ericsson | maría.liang@ericsson.com | ; 11/6/21: 0%->35 | [5 empty] | Fri 19/03/21 | Fri 11/06/21
454 | 910086 | CT4 aspects on TEI17_GEM | TEI17_GEM | 4 | Rel-17 | C4 | Fri 19/03/21 | Sat 12/03/22 | 0% | CP-211195 |  | Maria Tianmei, Liang, Ericsson | maría.liang@ericsson.com | [6 empty] | Fri 19/03/21 | NA
455 | 920041 | Support of different slices over different Non 3GPP access | TEI17_N3SLICE | 2 | Rel-17 |  | Wed 11/03/20 | Sun 20/06/21 | 100% | SP-200456 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com | 19/3/21: 0%->100 | 23.501; 23.502 | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
456 | 870008 | Stage 2 for Support of different slices over different Non 3GPP access | TEI17_N3SLICE | 3 | Rel-17 | S2 | Wed 11/03/20 | Thu 25/06/20 | 100% | SP-200456 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com | 19/3/21: 0%->100 | 23.501; 23.502 | 87 | 44 |  |  | Wed 10/06/20 | Fri 19/03/21
457 | 920001 | CT aspects of Support of different slices over different Non 3GPP access | TEI17_N3SLICE | 3 | Rel-17 | C4 | Fri 11/06/21 | Sun 20/06/21 | 100% | CP-211089 |  | LANDAIS, Bruno, Nokia | bruno.landais@nokia.com | ; 11/6/21: 0%->100 | 24.501;29.571;29.510 |  |  |  |  | Fri 11/06/21 | Fri 11/06/21
458 | 910087 | N7/N40 Interfaces Enhancements to Support GERAN and UTRAN | TEI17_NIESGU | 2 | Rel-17 |  | Wed 11/03/20 | Fri 10/09/21 | 47% | SP-200457 |  | Aihua, Li, China Mobile | liaihua@ chinamobile.com |  |  | 87 | 44 |  |  | Wed 10/06/20 | NA
459 | 870009 | Stage 2 for TEI17_NIESGU | TEI17_NIESGU | 3 | Rel-17 | S2 | Wed 11/03/20 | Thu 25/06/20 | 100% | SP-200457 |  | Aihua, Li, China Mobile | liaihua@ chinamobile.com | 11/6/21: 0%->100 | 23.060; 23.401; 23.503; 23.203 | 87 | 44 |  |  | Wed 10/06/20 | Fri 11/06/21
460 | 890019 | SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN | TEI17_NIESGU | 3 | Rel-17 | S5 | Wed 16/09/20 | Wed 08/09/21 | 10% | SP-200854 |  | Dong, Jia, China Mobile | dongjia@chinamobile.com | 25/09/20: acronym: "NIESGU"->"TEI17_NIESGU"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10 | 32.240; 32.251; 32.255; 32.290; 32.291; 32.298 | 89 | 45 |  |  | Fri 11/09/20 | Sun 21/03/21
461 | 910011 | CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN | TEI17_NIESGU | 3 | Rel-17 | C3 | Fri 19/03/21 | Fri 10/09/21 | 90% | CP-211194 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | ; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194 | 29.512; 29.513 |  |  |  |  | Fri 19/03/21 | Fri 11/06/21
462 | 880019 | Stage-3 5GS NAS protocol development 17 | 5GProtoc17 | 1 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 25% | CP-201163 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 | 88 | 45 |  |  | Fri 26/06/20 | NA
463 | 880044 | Stage-3 5GS NAS protocol development 17 general aspects | 5GProtoc17 | 2 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 50% | CP-201163 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50 |  | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
464 | 880045 | Stage-3 5GS NAS protocol development 17 non-IETF aspects | 5GProtoc17-non3GPP | 2 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 0% | CP-201163 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 | 88 | 45 |  |  | Fri 26/06/20 | NA
465 | 880021 | Stage-3 SAE Protocol Development | SAES17 | 1 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 17% | CP-201165 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com |  |  | 88 | 45 |  |  | Fri 26/06/20 | NA
466 | 880046 | Stage-3 SAE Protocol Development general aspects | SAES17 | 2 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 50% | CP-201165 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
467 | 880047 | Stage-3 SAE Protocol Development CSFB aspects | SAES17-CSFB | 2 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 0% | CP-201165 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 88 | 45 |  |  | Fri 26/06/20 | NA
468 | 880048 | Stage-3 SAE Protocol Development non 3GPP aspects | SAES17-non3GPP | 2 | Rel-17 | C1 | Thu 25/06/20 | Mon 20/09/21 | 0% | CP-201165 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 88 | 45 |  |  | Fri 26/06/20 | NA
469 | 911034 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 1 | Rel-17 | C1 | Thu 25/06/20 | Fri 10/09/21 | 50% | CP-201167 |  | Gkatzikis, Lazaros(Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; | 88 | 45 |  |  | Fri 26/06/20 | Sun 21/03/21
470 | 880023 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 2 | Rel-17 | C1 | Thu 25/06/20 | Fri 10/09/21 | 40% | CP-201167 |  | Gkatzikis, Lazaros(Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 11/6/21: 20%->40 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
471 | 911035 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 2 | Rel-17 | C3 | Thu 25/06/20 | Fri 10/09/21 | 60% | CP-201167 |  | Gkatzikis, Lazaros(Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 11/6/21: 0%->60 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
472 | 880032 | Packet Flow Description (PFD) management enhancement | pfdManEnh | 1 | Rel-17 | C3 | Thu 25/06/20 | Fri 11/06/21 | 100% | CP-210183 |  | Xiaoyun Zhou, Huawei | zhouxiaoyun8@huawei.com | 13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100 | 29.251; 29.551 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
473 | 880013 | Service Based Interface Protocol Improvements Release 17 | SBIProtoc17 | 1 | Rel-17 |  | Thu 19/09/19 | Sun 12/12/21 | 62% | CP-211088 |  | Song Yue, China Mobile | songyue@chinamobile.com |  |  | 88 | 45 |  |  | Fri 26/06/20 | NA
474 | 880053 | CT3 aspects of SBIProtoc17 | SBIProtoc17 | 2 | Rel-17 | C3 | Thu 25/06/20 | Mon 20/09/21 | 65% | CP-211088 |  | Song Yue, China Mobile | songyue@chinamobile.com | 13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088 | 29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
475 | 880054 | CT4 aspects of SBIProtoc17 | SBIProtoc17 | 2 | Rel-17 | C4 | Thu 25/06/20 | Mon 20/09/21 | 50% | CP-211088 |  | Song Yue, China Mobile | songyue@chinamobile.com | 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50 | 29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
476 | 850028 | Study on enhancement of Management Data Analytics Service | FS_eMDAS | 2 | Rel-17 | S5 | Thu 19/09/19 | Fri 12/03/21 | 100% | SP-190930 |  | Yao, Yizhi, Intel | yizhi.yao@intel.com | ; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100 | New ; 28.809 | 85 | 43 |  |  | Fri 13/09/19 | Sun 21/03/21
477 | 910027 | Enhancements of Management Data Analytics Service | eMDAS | 2 | Rel-17 | S5 | Thu 18/03/21 | Sun 12/12/21 | 0% | SP-210132 |  | Yao, Yizhi, Intel | yizhi<dot>yao<at>intel<dot>com |  | 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 |  |  |  |  | Thu 18/03/21 | NA
478 | 0 | Rel-17 Other NR-only improvements | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
479 | 911008 | NR QoE magement and optimizations for diverse services | NR_QoE | 1 | Rel-17 |  | Thu 07/03/19 | Wed 02/09/20 | 0% | RP-210913 |  | China Unicom |  | follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part | [5 empty] | Fri 04/06/21 | NA
480 | 911108 | Core part: NR QoE management and optimizations for diverse services | NR_QoE-Core | 2 | Rel-17 | R3 | Thu 07/03/19 | Wed 02/09/20 | 0% | RP-210913 |  | China Unicom |  | follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part | [5 empty] | Wed 07/04/21 | NA
481 | 911009 | Rel-17 Power Class 2 UE for NR inter-band CA with or without SUL configurations with x (16>=x>2) bands DL and y (y=1, 2) bands UL | NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL | 1 | Rel-17 |  | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210543 |  | Huawei |  | basket WI; TR 38.8xx | [5 empty] | Wed 07/04/21 | NA
482 | 911109 | Core part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL | NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210543 |  | Huawei |  | basket WI; TR 38.8xx | [5 empty] | Wed 07/04/21 | NA
483 | 911209 | Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL | NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210543 |  | Huawei | [7 empty] | Wed 07/04/21 | NA
484 | 911010 | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS | 1 | Rel-17 |  | Fri 12/03/21 | Thu 08/09/22 | 0% | RP-210807 |  | Vivo |  | compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx | [5 empty] | Wed 07/04/21 | NA
485 | 911110 | Core part: NR_FR1_TRP_TRS | NR_FR1_TRP_TRS-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210807 |  | Vivo |  | compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx | [5 empty] | Wed 07/04/21 | NA
486 | 911210 | Perf. part: NR_FR1_TRP_TRS | NR_FR1_TRP_TRS-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Thu 08/09/22 | 0% | RP-210807 |  | Vivo |  | compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy | [5 empty] | Wed 07/04/21 | NA
487 | 911012 | High power UE (power class 1.5) for NR band n79 | NR_UE_PC1_5_n79 | 1 | Rel-17 |  | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210843 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
488 | 911112 | Core part: NR_UE_PC1_5_n79 | NR_UE_PC1_5_n79-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210843 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
489 | 911212 | Perf. part: NR_UE_PC1_5_n79 | NR_UE_PC1_5_n79-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210843 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
490 | 911013 | High power UE (power class 2) for NR band n34 | NR_UE_PC2_n34 | 1 | Rel-17 |  | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210844 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
491 | 911113 | Core part: NR_UE_PC2_n34 | NR_UE_PC2_n34-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210844 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
492 | 911213 | Perf. part: NR_UE_PC2_n34 | NR_UE_PC2_n34-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210844 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
493 | 911014 | High power UE (power class 2) for NR band n39 | NR_UE_PC2_n39 | 1 | Rel-17 |  | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210845 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
494 | 911114 | Core part: NR_UE_PC2_n39 | NR_UE_PC2_n39-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210845 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
495 | 911214 | Perf. part: NR_UE_PC2_n39 | NR_UE_PC2_n39-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210845 |  | CMCC | [7 empty] | Wed 07/04/21 | NA
496 | 911015 | Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 | NR_FR2_FWA_Bn259 | 1 | Rel-17 |  | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210875 |  | SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm |  | compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 | [5 empty] | Wed 07/04/21 | NA
497 | 911115 | Core part: NR_FR2_FWA_Bn259 | NR_FR2_FWA_Bn259-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210875 |  | SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm |  | compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 | [5 empty] | Wed 07/04/21 | NA
498 | 911215 | Perf. part: NR_FR2_FWA_Bn259 | NR_FR2_FWA_Bn259-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210875 |  | SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm |  | compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 | [5 empty] | Wed 07/04/21 | NA
499 | 911006 | NR Uplink Data Compression (UDC) | NR_UDC | 1 | Rel-17 |  | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210909 |  | CATT |  | no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core | [5 empty] | Wed 07/04/21 | NA
500 | 911106 | Core part: NR_UDC | NR_UDC-Core | 2 | Rel-17 | R2 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210909 |  | CATT |  | no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core | [5 empty] | Wed 07/04/21 | NA
501 | 910097 | Study on optimizations of pi/2 BPSK uplink power in NR | FS_NR_Opt_pi2BPSK | 1 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210910 |  | Huawei | [7 empty] | Wed 07/04/21 | NA
502 | 910096 | Study on band combination handling in RAN4 | FS_NR_ENDC_combo_rules | 1 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210773 |  | ZTE |  | TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC | [5 empty] | Wed 07/04/21 | NA
503 | 880078 | Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs | NR_MIMO_OTA | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-201800 |  | CAICT |  | 25/9/20: WID:RP-201302->RP-201800 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
504 | 880178 | Core part: NR_MIMO_OTA | NR_MIMO_OTA-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-201800 |  | CAICT |  | 25/9/20: 38.151 added; | 38.151 | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
505 | 880278 | Perf. Part: NR_MIMO_OTA | NR_MIMO_OTA-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-201800 |  | CAICT |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
506 | 870064 | Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | NR_FR2_FWA_Bn257_Bn258 | 1 | Rel-17 |  | Wed 25/03/20 | Mon 15/03/21 | 100% | RP-202565 |  | Softbank |  | affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565 |  | 87 | 44 |  |  | Thu 26/03/20 | Wed 06/01/21
507 | 870164 | Core part: NR_FR2_FWA_Bn257_Bn258 | NR_FR2_FWA_Bn257_Bn258-Core | 2 | Rel-17 | R4 | Wed 25/03/20 | Tue 15/09/20 | 100% | RP-202565 |  | Softbank |  | affects: NR. TR 38.8xx; 7/4/21: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
508 | 870264 | Perf. Part: NR_FR2_FWA_Bn257_Bn258 | NR_FR2_FWA_Bn257_Bn258-Perf | 2 | Rel-17 | R4 | Wed 25/03/20 | Mon 15/03/21 | 100% | RP-202565 |  | Softbank |  | affects: NR. TR 38.8xx; 7/4/21: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
509 | 880092 | Adding channel bandwidth support to existing NR bands | NR_bands_R17_BWs | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210917 |  | Ericsson |  | 25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
510 | 880192 | Core part: NR_bands_R17_BWs | NR_bands_R17_BWs-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210917 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
511 | 880093 | Introduction of channel bandwidths 35MHz and 45MHz for NR FR1 | NR_FR1_35MHz_45MHz_BW | 1 | Rel-17 |  | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210722 |  | Huawei |  | 25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
512 | 880193 | Core part: NR_FR1_35MHz_45MHz_BW | NR_FR1_35MHz_45MHz_BW-Core | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210722 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
513 | 880293 | Perf. Part: NR_FR1_35MHz_45MHz_BW | NR_FR1_35MHz_45MHz_BW-Perf | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210722 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
514 | 880097 | SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL | NR_SAR_PC2_interB_SUL_2BUL | 1 | Rel-17 |  | Thu 19/03/20 | Fri 19/03/21 | 50% | RP-201584 |  | China Telecom |  | 25/9/20: WID:RP-201337->RP-201584 |  | 88 | 45 |  |  | Tue 28/07/20 | NA
515 | 880197 | Core part: NR_SAR_PC2_interB_SUL_2BUL | NR_SAR_PC2_interB_SUL_2BUL-Core | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-201584 |  | China Telecom |  | 25/9/20: WID:RP-201337->RP-201584 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
516 | 880297 | Perf. Part: NR_SAR_PC2_interB_SUL_2BUL | NR_SAR_PC2_interB_SUL_2BUL-Perf | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 100% | RP-201584 |  | China Telecom |  | 7/4/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
517 | 900061 | NR coverage enhancements | NR_cov_enh | 1 | Rel-17 |  | Thu 07/03/19 | Thu 08/09/22 | 29% | RP-210855 |  | China Telecom |  | follow-up WI of REL-17 SI FS_NR_cov_enh ; 7/4/21: WID:RP-202928->RP-210855 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
518 | 860036 | Study on on NR coverage enhancements | FS_NR_cov_enh | 2 | Rel-17 | R1 | Thu 07/03/19 | Wed 03/06/20 | 100% | RP-200861 |  | China Telecom |  | affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
519 | 900161 | Core part: NR_cov_enh | NR_cov_enh-Core | 2 | Rel-17 | R1 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210855 |  | China Telecom |  | follow-up WI of REL-17 SI FS_NR_cov_enh |  | 90 |  |  |  | Wed 06/01/21 | NA
520 | 900261 | Perf. part: NR_cov_enh | NR_cov_enh-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Thu 08/09/22 | 0% | RP-210855 |  | China Telecom |  | follow-up WI of REL-17 SI FS_NR_cov_enh |  | 90 |  |  |  | Wed 06/01/21 | NA
521 | 900062 | Support of reduced capability NR devices | NR_redcap | 1 | Rel-17 |  | Mon 16/12/19 | Thu 08/09/22 | 14% | RP-210918 |  | Ericsson |  | follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202933->RP-210918 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
522 | 860035 | Study on support of reduced capability NR devices | FS_NR_redcap | 2 | Rel-17 | R1 | Mon 16/12/19 | Mon 15/06/20 | 100% | RP-202704 |  | Ericsson |  | affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
523 | 900162 | Core part: NR_redcap | NR_redcap-Core | 2 | Rel-17 | R1 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210918 |  | Ericsson |  | follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) |  | 90 |  |  |  | Wed 06/01/21 | NA
524 | 900262 | Perf. part: NR_redcap | NR_redcap-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Thu 08/09/22 | 0% | RP-210918 |  | Ericsson |  | follow-up WI of REL-17 SI FS_NR_redcap |  | 90 |  |  |  | Wed 06/01/21 | NA
525 | 900064 | Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 | NR_bands_UL_MIMO_PC3_R17 | 1 | Rel-17 |  | Mon 14/12/20 | Sun 12/06/22 | 0% | RP-210557 |  | Huawei |  | basket WI ; 7/4/21: WID:RP-202819->RP-210557 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
526 | 900164 | Core part: NR_bands_UL_MIMO_PC3_R17 | NR_bands_UL_MIMO_PC3_R17-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210557 |  | Huawei |  | basket WI |  | 90 |  |  |  | Wed 06/01/21 | NA
527 | 900264 | Perf. part: NR_bands_UL_MIMO_PC3_R17 | NR_bands_UL_MIMO_PC3_R17-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Sun 12/06/22 | 0% | RP-210557 |  | Huawei |  | basket WI |  | 90 |  |  |  | Wed 06/01/21 | NA
528 | 900167 | Introduction of bandwidth combination set 4 (BCS4) for NR | NR_BCS4-Core | 1 | Rel-17 | R4 | Thu 07/03/19 | Wed 03/06/20 | 0% | RP-202832 |  | Ericsson |  | no Perf. part |  | 90 |  |  |  | Wed 06/01/21 | NA
529 | 900068 | Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R17 | 1 | Rel-17 |  | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210478 |  | China Telecom |  | basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
530 | 900168 | Core part: DL_intrpt_combos_TxSW_R17 | DL_intrpt_combos_TxSW_R17-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210478 |  | China Telecom |  | basket WI; TR 37.8xx |  | 90 |  |  |  | Wed 06/01/21 | NA
531 | 900268 | Perf. part: DL_intrpt_combos_TxSW_R17 | DL_intrpt_combos_TxSW_R17-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/03/22 | 0% | RP-210478 |  | China Telecom |  | basket WI |  | 90 |  |  |  | Wed 06/01/21 | NA
532 | 900069 | High-power UE (power class 1.5) operation in NR bands n77 and n78 | HPUE_PC1_5_n77_n78 | 1 | Rel-17 |  | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-202912 |  | Qualcomm |  | no Perf. part |  | 90 |  |  |  | Wed 06/01/21 | NA
533 | 900169 | Core part: HPUE_PC1_5_n77_n78 | HPUE_PC1_5_n77_n78-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-202912 |  | Qualcomm |  | no Perf. part |  | 90 |  |  |  | Wed 06/01/21 | NA
534 | 900070 | NR repeaters | NR_repeaters | 1 | Rel-17 |  | Mon 14/12/20 | Sun 12/12/21 | 0% | RP-210818 |  | Qualcomm |  | no Perf. part ; 7/4/21: WID:RP-202927->RP-210818 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
535 | 900170 | Core part: HPUE_PC1_5_n77_n78 | NR_repeaters-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sun 12/12/21 | 0% | RP-210818 |  | Qualcomm |  | no Perf. part |  | 90 |  |  |  | Wed 06/01/21 | NA
536 | 0 | Rel-17 NR Carrier Aggregation | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
537 | 0 | Rel-17 NR intra band Carrier Aggregation (itrabCA) | - | 2 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
538 | 881005 | NR itrabCA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R17_Intra | 1 | Rel-17 |  | Thu 09/06/16 | Wed 15/09/21 | 0% | RP-210210 |  | Ericsson |  | 25/9/20: WID:RP-200663->RP-201571; 6/1/21: WID:RP-201571->RP-202187; 7/4/21: WID:RP-202187->RP-210210 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
539 | 881105 | Core part: NR_CA_R17_Intra | NR_CA_R17_Intra-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210210 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
540 | 881205 | Perf. Part: NR_CA_R17_Intra | NR_CA_R17_Intra-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210210 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
541 | 0 | Rel-17 NR inter band Carrier Aggregation (iterbCA) | - | 2 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
542 | 900063 | High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1 | NR_intra_HPUE_R17 | 1 | Rel-17 |  | Wed 10/02/21 | Thu 09/12/21 | 0% | RP-210555 |  | Huawei |  | 7/4/21: WID:RP-202818->RP-210555 |  | 90 |  |  |  | Wed 10/02/21 | Wed 07/04/21
543 | 900163 | Core part: NR_intra_HPUE_R17 | NR_intra_HPUE_R17-Core | 2 | Rel-17 | R4 | Wed 10/02/21 | Thu 09/12/21 | 0% | RP-210555 |  | Huawei |  |  |  | 90 |  |  |  | Wed 10/02/21 | NA
544 | 900263 | Perf. Part: NR_intra_HPUE_R17 | NR_intra_HPUE_R17-Perf | 2 | Rel-17 | R4 | Wed 10/02/21 | Thu 09/12/21 | 0% | RP-210555 |  | Huawei |  |  |  | 90 |  |  |  | Wed 10/02/21 | NA
545 | 881006 | NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R17_2BDL_xBUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210495 |  | ZTE |  | 25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
546 | 881106 | Core part: NR_CADC_R17_2BDL_xBUL | NR_CADC_R17_2BDL_xBUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210495 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
547 | 881206 | Perf. part: NR_CADC_R17_2BDL_xBUL | NR_CADC_R17_2BDL_xBUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210495 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
548 | 881007 | NR iterbCA for 3 bands DL with 1 band UL | NR_CA_R17_3BDL_1BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210901 |  | CATT |  | 25/9/20: WID:RP-200922->RP-201787; 6/1/21: WID:RP-201787->RP-202720; 7/4/21: WID:RP-202720->RP-210901 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
549 | 881107 | Core part: NR_CA_R17_3BDL_1BUL | NR_CA_R17_3BDL_1BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210901 |  | CATT |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
550 | 881207 | Perf. part: NR_CA_R17_3BDL_1BUL | NR_CA_R17_3BDL_1BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210901 |  | CATT |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
551 | 881008 | NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R17_3BDL_2BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210497 |  | ZTE |  | 25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
552 | 881108 | Core part: NR_CADC_R17_3BDL_2BUL | NR_CADC_R17_3BDL_2BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210497 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
553 | 881208 | Perf. part: NR_CADC_R17_3BDL_2BUL | NR_CADC_R17_3BDL_2BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210497 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
554 | 881009 | NR iterbCA for 4 bands DL with 1 band UL | NR_CA_R17_4BDL_1BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210760 |  | Ericsson |  | 25/9/20: WID:RP-200665->RP-201573; 6/1/21: WID:RP-201573->RP-202189; 7/4/21: WID:RP-202189->RP-210760 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
555 | 881109 | Core part: NR_CA_R17_4BDL_1BUL | NR_CA_R17_4BDL_1BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210760 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
556 | 881209 | Perf. part: NR_CA_R17_4BDL_1BUL | NR_CA_R17_4BDL_1BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210760 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
557 | 881010 | NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands | NR_CADC_R17_4BDL_2BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210802 |  | Samsung |  | 25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
558 | 881110 | Core part: NR_CADC_R17_4BDL_2BUL | NR_CADC_R17_4BDL_2BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210802 |  | Samsung |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
559 | 881210 | Perf. part: NR_CADC_R17_4BDL_2BUL | NR_CADC_R17_4BDL_2BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210802 |  | Samsung |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
560 | 881011 | NR iterbCA for 5 bands DL with x bands UL (x=1, 2) | NR_CADC_R17_5BDL_xBUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210561 |  | Huawei |  | 25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
561 | 881111 | Core part: NR_CADC_R17_5BDL_xBUL | NR_CADC_R17_5BDL_xBUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210561 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
562 | 881211 | Perf. part: NR_CADC_R17_5BDL_xBUL | NR_CADC_R17_5BDL_xBUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210561 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
563 | 890054 | Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) | NR_PC2_CA_R17_2BDL_2BUL | 1 | Rel-17 |  | Thu 17/09/20 | Fri 17/12/21 | 0% | RP-210476 |  | China Telecom |  | basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 6/1/21: WID:RP-202102->RP-202373; 7/4/21: WID:RP-202373->RP-210476 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 07/04/21
564 | 890154 | Core part: NR_PC2_CA_R17_2BDL_2BUL | NR_PC2_CA_R17_2BDL_2BUL-Core | 2 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/12/21 | 0% | RP-210476 |  | China Telecom |  | basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx |  | 89 | 45 |  |  | Fri 25/09/20 | NA
565 | 890254 | Perf. part: NR_PC2_CA_R17_2BDL_2BUL | NR_PC2_CA_R17_2BDL_2BUL-Perf | 2 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/12/21 | 0% | RP-210476 |  | China Telecom |  | basket WI |  | 89 | 45 |  |  | Fri 25/09/20 | NA
566 | 0 | Rel-17 NR and LTE | - | 1 | Rel-17 |  | Wed 25/03/20 | Tue 15/09/20 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
567 | 911019 | Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths | ENDC_R17_1BLTE_1BNR_MS | 1 | Rel-17 |  | Thu 25/03/21 | Fri 25/03/22 | 0% | RP-210891 |  | Huawei, HiSilicon |  | basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part | [5 empty] | Fri 09/04/21 | NA
568 | 911119 | Core part: ENDC_R17_1BLTE_1BNR_MS | ENDC_R17_1BLTE_1BNR_MSD-Core | 2 | Rel-17 |  | Thu 25/03/21 | Fri 25/03/22 | 0% | RP-210891 |  | Huawei, HiSilicon |  | basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part | [5 empty] | Fri 09/04/21 | NA
569 | 911011 | Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) | ENDC_PC2_R17_xLTE_yNR | 1 | Rel-17 |  | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210816 |  | Ericsson |  | basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx | [5 empty] | Wed 07/04/21 | NA
570 | 911111 | Core part: ENDC_PC2_R17_xLTE_yNR | ENDC_PC2_R17_xLTE_yNR-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210816 |  | Ericsson |  | basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx | [5 empty] | Wed 07/04/21 | NA
571 | 911211 | Perf. Part: ENDC_PC2_R17_xLTE_yNR | ENDC_PC2_R17_xLTE_yNR-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Wed 08/09/21 | 0% | RP-210816 |  | Ericsson |  | compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD | [5 empty] | Wed 07/04/21 | NA
572 | 911018 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC | LTE_NR_Simult_RxTx | 1 | Rel-17 |  | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210890 |  | Huawei | [7 empty] | Wed 07/04/21 | NA
573 | 911118 | Core part: LTE_NR_Simult_RxTx | LTE_NR_Simult_RxTx-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210890 |  | Huawei | [7 empty] | Wed 07/04/21 | NA
574 | 911218 | Perf. part: LTE_NR_Simult_RxTx | LTE_NR_Simult_RxTx-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210890 |  | Huawei | [7 empty] | Wed 07/04/21 | NA
575 | 890052 | Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R17_5BLTE_1BNR_6DL2UL | 1 | Rel-17 |  | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-210801 |  | Samsung |  | basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 07/04/21
576 | 890152 | Core part: DC_R17_5BLTE_1BNR_6DL2UL | DC_R17_5BLTE_1BNR_6DL2UL-Core | 2 | Rel-17 | R4 | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-210801 |  | Samsung |  | basket WI; TR 37.717-51-11 |  | 89 | 45 |  |  | Fri 25/09/20 | NA
577 | 890252 | Perf. part: DC_R17_5BLTE_1BNR_6DL2UL | DC_R17_5BLTE_1BNR_6DL2UL-Perf | 2 | Rel-17 | R4 | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-210801 |  | Samsung |  | basket WI |  | 89 | 45 |  |  | Fri 25/09/20 | NA
578 | 890053 | Rel-17 Dual Connectivity (DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) | DC_R17_xBLTE_2BNR_yDL3UL | 1 | Rel-17 |  | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-202542 |  | Samsung |  | basket WI; TR 37.717-21-22 ; 6/1/21: WID:RP-201643->RP-202542 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 06/01/21
579 | 890153 | Core part: DC_R17_xBLTE_2BNR_yDL3UL | DC_R17_xBLTE_2BNR_yDL3UL-Core | 2 | Rel-17 | R4 | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-202542 |  | Samsung |  | basket WI; TR 37.717-21-22 |  | 89 | 45 |  |  | Fri 25/09/20 | NA
580 | 890253 | Perf. part: DC_R17_xBLTE_2BNR_yDL3UL | DC_R17_xBLTE_2BNR_yDL3UL-Perf | 2 | Rel-17 | R4 | Thu 17/09/20 | Wed 08/09/21 | 0% | RP-202542 |  | Samsung |  | basket WI |  | 89 | 45 |  |  | Fri 25/09/20 | NA
581 | 880080 | Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210588 |  | CATT |  | 25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588 | 37.875 | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
582 | 880180 | Core part: NR_LTE_V2X_PC5_combos | NR_LTE_V2X_PC5_combos-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210588 |  | CATT |  | 25/9/20: 37.875 added; | 37.875 | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
583 | 880280 | Perf. part: NR_LTE_V2X_PC5_combos | NR_LTE_V2X_PC5_combos-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210588 |  | CATT |  | 25/9/20: 37.875 added; | 37.875 | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
584 | 880094 | High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band | ENDC_UE_PC2_R17_NR_TDD | 1 | Rel-17 |  | Mon 22/06/20 | Sun 12/12/21 | 0% | RP-210327 |  | China Unicom |  | 25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
585 | 880194 | Core part: ENDC_UE_PC2_R17_NR_TDD | ENDC_UE_PC2_R17_NR_TDD-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210327 |  | China Unicom |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
586 | 880294 | Perf. part: ENDC_UE_PC2_R17_NR_TDD | ENDC_UE_PC2_R17_NR_TDD-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210327 |  | China Unicom |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
587 | 911000 | UE Conformance - ENDC_UE_PC2_R17_NR_TDD | ENDC_UE_PC2_R17_NR_TDD-UEConTest | 2 | Rel-17 | R5 | Fri 12/03/21 | Sun 12/12/21 | 0% | RP-210401 |  | China Unicom |  | tested: REL-17 basket WI ENDC_UE_PC2_R17_NR_TDD-Core | [5 empty] | Wed 07/04/21 | NA
588 | 880095 | LTE/NR spectrum sharing in Band 38/n38 | DSS_LTE_B38_NR_Bn38 | 1 | Rel-17 |  | Wed 17/06/20 | Tue 15/09/20 | 100% | RP-201314 |  | Vodafone |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
589 | 880195 | Core part: DSS_LTE_B38_NR_Bn38 | DSS_LTE_B38_NR_Bn38-Core | 2 | Rel-17 | R4 | Wed 17/06/20 | Tue 15/09/20 | 100% | RP-201314 |  | Vodafone |  | 25/9/20: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
590 | 880096 | LTE/NR spectrum sharing in Band 40/n40 | DSS_LTE_B40_NR_Bn40 | 1 | Rel-17 |  | Wed 17/06/20 | Tue 15/09/20 | 100% | RP-202084 |  | Reliance Jio |  | 25/9/20: WID:RP-201362->RP-202084 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
591 | 880196 | Core part: DSS_LTE_B40_NR_Bn40 | DSS_LTE_B40_NR_Bn40-Core | 2 | Rel-17 | R4 | Wed 17/06/20 | Tue 15/09/20 | 100% | RP-202084 |  | Reliance Jio |  | 6/1/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
592 | 880296 | Perf. part: DSS_LTE_B40_NR_Bn40 | DSS_LTE_B40_NR_Bn40-Perf | 2 | Rel-17 | R4 | Wed 17/06/20 | Tue 15/09/20 | 100% | RP-202084 |  | Reliance Jio |  | 25/9/20: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
593 | 880098 | Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R17_1BLTE_1BNR_2DL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210204 |  | CHTTL |  | 25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
594 | 880198 | Core part: DC_R17_1BLTE_1BNR_2DL2UL | DC_R17_1BLTE_1BNR_2DL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210204 |  | CHTTL |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
595 | 880298 | Perf. part: DC_R17_1BLTE_1BNR_2DL2UL | DC_R17_1BLTE_1BNR_2DL2UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210204 |  | CHTTL |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
596 | 880099 | Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R17_2BLTE_1BNR_3DL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210559 |  | Huawei |  | 25/9/20: WID:RP-201369->RP-202060; 6/1/21: WID:RP-202060->RP-202613; 7/4/21: WID:RP-202613->RP-210559 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
597 | 880199 | Core part: DC_R17_2BLTE_1BNR_3DL2UL | DC_R17_2BLTE_1BNR_3DL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210559 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
598 | 890263 | Perf. part: DC_R17_2BLTE_1BNR_3DL2UL | DC_R17_2BLTE_1BNR_3DL2UL-Perf | 2 | Rel-17 | R4 | Wed 16/09/20 | Wed 15/09/21 | 0% | RP-210559 |  | Huawei |  |  |  | 89 | 45 |  |  | Sun 11/10/20 | NA
599 | 881000 | Dual Connectivity (DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R17_3BLTE_1BNR_4DL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210211 |  | Ericsson |  | 25/9/20: WID:RP-201370->RP-201572; 6/1/21: WID:RP-201572->RP-202188; 7/4/21: WID:RP-202188->RP-210211 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
600 | 881100 | Core part: DC_R17_3BLTE_1BNR_4DL2UL | DC_R17_3BLTE_1BNR_4DL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210211 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
601 | 881200 | Perf. part: DC_R17_3BLTE_1BNR_4DL2UL | DC_R17_3BLTE_1BNR_4DL2UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210211 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
602 | 881001 | Dual Connectivity (DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R17_4BLTE_1BNR_5DL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210766 |  | Nokia |  | 25/9/20: WID:RP-201371->RP-201483; 6/1/21: WID:RP-201483->RP-202590; 7/4/21: WID:RP-202590->RP-210766 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
603 | 881101 | Core part: DC_R17_4BLTE_1BNR_5DL2UL | DC_R17_4BLTE_1BNR_5DL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210766 |  | Nokia |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
604 | 881201 | Perf. part: DC_R17_4BLTE_1BNR_5DL2UL | DC_R17_4BLTE_1BNR_5DL2UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210766 |  | Nokia |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
605 | 881002 | Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R17_xBLTE_2BNR_yDL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210202 |  | LG Electronics |  | 25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
606 | 881102 | Core part: DC_R17_xBLTE_2BNR_yDL2UL | DC_R17_xBLTE_2BNR_yDL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210202 |  | LG Electronics |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
607 | 881202 | Perf. part: DC_R17_xBLTE_2BNR_yDL2UL | DC_R17_xBLTE_2BNR_yDL2UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210202 |  | LG Electronics |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
608 | 881003 | Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL) | DC_R17_xBLTE_yBNR_3DL3UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210344 |  | ZTE |  | 25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
609 | 881103 | Core part: DC_R17_xBLTE_yBNR_3DL3UL | DC_R17_xBLTE_yBNR_3DL3UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210344 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
610 | 881203 | Perf. part: DC_R17_xBLTE_yBNR_3DL3UL | DC_R17_xBLTE_yBNR_3DL3UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210344 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
611 | 881004 | Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL) | DC_R17_xBLTE_3BNR_yDL2UL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210346 |  | ZTE |  | 25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
612 | 881104 | Core part: DC_R17_xBLTE_3BNR_yDL2UL | DC_R17_xBLTE_3BNR_yDL2UL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210346 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
613 | 881204 | Perf. part: DC_R17_xBLTE_3BNR_yDL2UL | DC_R17_xBLTE_3BNR_yDL2UL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210346 |  | ZTE |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
614 | 881012 | band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R17 | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210563 |  | Huawei |  | 25/9/20: WID:RP-201026->RP-201726; 6/1/21: WID:RP-201726->RP-202611; 7/4/21: WID:RP-202611->RP-210563 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
615 | 881112 | Core part: NR_SUL_combos_R17 | NR_SUL_combos_R17-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210563 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
616 | 881212 | Perf. part: NR_SUL_combos_R17 | NR_SUL_combos_R17-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210563 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
617 | 900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | NR_CADC_NR_LTE_DC_R17-UEConTest | 1 | Rel-17 | R5 | Mon 14/12/20 | Fri 10/12/21 | 5% | RP-202568 |  | Huawei |  | tested: REL-17 basket WIs: NR_CA_R17_Intra, NR_CADC_R17_2BDL_xBUL, NR_CA_R17_3BDL_1BUL, NR_CADC_R17_3BDL_2BUL, NR_CA_R17_4BDL_1BUL, NR_CADC_R17_4BDL_2BUL, NR_CADC_R17_5BDL_xBUL, NR_SUL_combos_R17, DC_R17_1BLTE_1BNR_2DL2UL, DC_R17_2BLTE_1BNR_3DL2UL, DC_... |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
618 | 0 | Rel-17 NR new/modified bands | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
619 | 911016 | Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) | NR_RAIL_EU_900MHz | 1 | Rel-17 |  | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210878 |  | Union Internationale Chemins de Fer (UIC) |  | FDD: UL: 874.4-880MHz, DL: 919.4-925MHz | [5 empty] | Wed 07/04/21 | NA
620 | 911116 | Core part: NR_RAIL_EU_900MHz | NR_RAIL_EU_900MHz-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210878 |  | Union Internationale Chemins de Fer (UIC) |  | FDD: UL: 874.4-880MHz, DL: 919.4-925MHz | [5 empty] | Wed 07/04/21 | NA
621 | 911216 | Perf. part: NR_RAIL_EU_900MHz | NR_RAIL_EU_900MHz-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210878 |  | Union Internationale Chemins de Fer (UIC) | [7 empty] | Wed 07/04/21 | NA
622 | 911017 | Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) | NR_RAIL_EU_1900MHz_TDD | 1 | Rel-17 |  | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210879 |  | Union Internationale Chemins de Fer (UIC) |  | TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz | [5 empty] | Wed 07/04/21 | NA
623 | 911117 | Core part: NR_RAIL_EU_1900MHz_TDD | NR_RAIL_EU_1900MHz_TDD-Core | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210879 |  | Union Internationale Chemins de Fer (UIC) |  | TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz | [5 empty] | Wed 07/04/21 | NA
624 | 911217 | Perf. part: NR_RAIL_EU_1900MHz_TDD | NR_RAIL_EU_1900MHz_TDD-Perf | 2 | Rel-17 | R4 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210879 |  | Union Internationale Chemins de Fer (UIC) | [7 empty] | Wed 07/04/21 | NA
625 | 860041 | Extending current NR operation to 71GHz | NR_ext_to_71GHz | 1 | Rel-17 | R1 | Mon 16/12/19 | Wed 15/09/21 | 0% | RP-210862 |  | Qualcomm |  | affects: NR.; 25/9/20: WID:RP-193229->RP-201845; 6/1/21: WID:RP-201845->RP-202925; 7/4/21: WID:RP-202925->RP-210862 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
626 | 860141 | Core part: Extending current NR operation to 71GHz | NR_ext_to_71GHz-Core | 2 | Rel-17 | R1 | Mon 16/12/19 | Tue 15/06/21 | 0% | RP-210862 |  | Qualcomm |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
627 | 860241 | Perf. part: Extending current NR operation to 71GHz | NR_ext_to_71GHz-Perf | 2 | Rel-17 | R4 | Mon 16/12/19 | Wed 15/09/21 | 0% | RP-210862 |  | Qualcomm |  | affects: NR. |  | 86 | 44 |  |  | Tue 14/01/20 | NA
628 | 860037 | Study on supporting NR from 52.6 GHz to 71 GHz | FS_NR_52_to_71GHz | 1 | Rel-17 | R1 | Mon 16/12/19 | Mon 15/06/20 | 100% | RP-201838 |  | Intel |  | affects: NR. TR 38.8xx; 28/7/20: WID:RP-193259->RP-200902; 25/9/20: WID:RP-200902->RP-201838; 7/4/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
629 | 870060 | Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz | FS_NR_IMT_param | 1 | Rel-17 | R4 | Wed 25/03/20 | Tue 15/12/20 | 100% | RP-202276 |  | Ericsson |  | affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
630 | 870063 | Introduction of NR band n13 | NR_n13 | 1 | Rel-17 | R4 | Wed 25/03/20 | Tue 15/09/20 | 100% | RP-200480 |  | Huawei |  | affects: NR. TR 38.8xx |  | 87 | 44 |  |  | Thu 26/03/20 | NA
631 | 870163 | Core part: Introduction of NR band n13 | NR_n13-Core | 2 | Rel-17 | R4 | Wed 25/03/20 | Tue 15/09/20 | 100% | RP-200480 |  | Huawei |  | affects: NR. TR 38.8xx; 6/1/21: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
632 | 870263 | Perf. part: Introduction of NR band n13 | NR_n13-Perf | 2 | Rel-17 | R4 | Wed 25/03/20 | Tue 15/09/20 | 100% | RP-200480 |  | Huawei |  | affects: NR. TR 38.8xx; 6/1/21: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
633 | 880082 | Introduction of NR 47GHz band | NR_47GHz_band | 1 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210827 |  | Ericsson |  | 7/4/21: WID:RP-201232->RP-210827 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
634 | 880182 | Core part: Introduction of NR 47GHz band | NR_47GHz_band-Core | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210827 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
635 | 880282 | Perf. part: Introduction of NR 47GHz band | NR_47GHz_band-Perf | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-210827 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
636 | 880084 | Introduction of NR band 24 | NR_band_n24 | 1 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 50% | RP-201357 |  | Ligado Networks |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
637 | 880184 | Core part: Introduction of NR band 24 | NR_band_n24-Core | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 0% | RP-201357 |  | Ligado Networks |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
638 | 880284 | Perf. part: Introduction of NR band 24 | NR_band_n24-Perf | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 100% | RP-201357 |  | Ligado Networks |  | 7/4/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
639 | 890050 | Introduction of 6GHz NR licensed bands | NR_6GHz | 1 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/06/22 | 0% | RP-202844 |  | Huawei |  | missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 06/01/21
640 | 890150 | Core part: Introduction of 6GHz NR licensed bands | NR_6GHz-Core | 2 | Rel-17 | R4 | Thu 17/09/20 | Tue 15/03/22 | 0% | RP-202844 |  | Huawei |  | missing target dates to be updated |  | 89 | 45 |  |  | Fri 25/09/20 | NA
641 | 890250 | Perf. part: Introduction of 6GHz NR licensed bands | NR_6GHz-Perf | 2 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/06/22 | 0% | RP-202844 |  | Huawei |  | missing target dates to be updated |  | 89 | 45 |  |  | Fri 25/09/20 | NA
642 | 890051 | Introduction of lower 6GHz NR unlicensed operation for Europe | NR_6GHz_unlic_EU | 1 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/06/22 | 0% | RP-210762 |  | Nokia |  | missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 07/04/21
643 | 890151 | Core part: Introduction of lower 6GHz NR unlicensed operation for Europe | NR_6GHz_unlic_EU-Core | 2 | Rel-17 | R4 | Thu 17/09/20 | Tue 15/03/22 | 0% | RP-210762 |  | Nokia |  | missing target dates to be updated ; 10/2/21: 38.849 added; | 38.849 | 89 | 45 |  |  | Fri 25/09/20 | Wed 10/02/21
644 | 890251 | Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe | NR_6GHz_unlic_EU-Perf | 2 | Rel-17 | R4 | Thu 17/09/20 | Fri 17/06/22 | 0% | RP-210762 |  | Nokia |  | missing target dates to be updated |  | 89 | 45 |  |  | Fri 25/09/20 | NA
645 | 900065 | Introduction of NR band n67 | NR_n67 | 1 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-202829 |  | Ericsson |  |  |  | 90 |  |  |  | Wed 06/01/21 | NA
646 | 900165 | Core part: Introduction of NR band n67 | NR_n67-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-202829 |  | Ericsson |  |  |  | 90 |  |  |  | Wed 06/01/21 | NA
647 | 900265 | Perf. Part: Introduction of NR band n67 | NR_n67-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-202829 |  | Ericsson |  |  |  | 90 |  |  |  | Wed 06/01/21 | NA
648 | 900066 | Introduction of NR band n85 | NR_n85 | 1 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-210707 |  | Ericsson |  | ; 7/4/21: WID:RP-202830->RP-210707 |  | 90 |  |  |  | Wed 06/01/21 | Wed 07/04/21
649 | 900166 | Core part: Introduction of NR band n85 | NR_n85-Core | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-210707 |  | Ericsson |  |  |  | 90 |  |  |  | Wed 06/01/21 | NA
650 | 900266 | Perf. part: Introduction of NR band n85 | NR_n85-Perf | 2 | Rel-17 | R4 | Mon 14/12/20 | Sat 12/06/21 | 0% | RP-210707 |  | Ericsson |  |  |  | 90 |  |  |  | Wed 06/01/21 | NA
651 | 880083 | Introduction of 1.6 GHz NR supplemental uplink (SUL) band with same uplink frequency range of Band 24 | NR_SUL_UL_n24 | 1 | Rel-17 |  | Thu 19/03/20 | Fri 19/03/21 | 100% | RP-210341 |  | Ligado Networks |  | 7/4/21: WID:RP-201251->RP-210341 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
652 | 880183 | Core part: NR_SUL_UL_n24 | NR_SUL_UL_n24-Core | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 100% | RP-210341 |  | Ligado Networks |  | 7/4/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
653 | 880283 | Perf. part: NR_SUL_UL_n24 | NR_SUL_UL_n24-Perf | 2 | Rel-17 | R4 | Thu 19/03/20 | Fri 19/03/21 | 100% | RP-210341 |  | Ligado Networks |  | 7/4/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
654 | 880085 | Introduction of NR supplemental uplink (SUL) band 1880-1920MHz | NR_SUL_band_1880_1920MHz | 1 | Rel-17 |  | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201363 |  | CMCC |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
655 | 880185 | Core part: NR_SUL_band_1880_1920MHz | NR_SUL_band_1880_1920MHz-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201363 |  | CMCC |  | 6/1/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
656 | 880285 | Perf. part: NR_SUL_band_1880_1920MHz | NR_SUL_band_1880_1920MHz-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201363 |  | CMCC |  | 6/1/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
657 | 880086 | Introduction of NR supplemental uplink (SUL) band 2300-2400MHz | NR_SUL_band_2300_2400MHz | 1 | Rel-17 |  | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201364 |  | CMCC |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
658 | 880186 | Core part: NR_SUL_band_2300_2400MHz | NR_SUL_band_2300_2400MHz-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201364 |  | CMCC |  | 6/1/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
659 | 880286 | Perf. part: NR_SUL_band_2300_2400MHz | NR_SUL_band_2300_2400MHz-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Tue 15/12/20 | 100% | RP-201364 |  | CMCC |  | 6/1/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
660 | 900055 | UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands | NR_lic_bands_BW_R17-UEConTest | 1 | Rel-17 | R5 | Mon 14/12/20 | Fri 10/12/21 | 16% | RP-202567 |  | Huawei |  | tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
661 | 0 | Rel-17 LTE new/modified bands | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
662 | 911020 | New bands and bandwidth allocation for 5G terrestrial broadcast | LTE_terr_bcast_bands | 1 | Rel-17 | R4 | Mon 08/06/20 | Fri 11/03/22 | 0% | RP-210907 |  | EBU |  | WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part | [5 empty] | Thu 08/04/21 | NA
663 | 911120 | Core part: New bands and bandwidth allocation for 5G terrestrial broadcast | LTE_terr_bcast_bands_part1 | 2 | Rel-17 | R4 | Mon 08/06/20 | Fri 11/03/22 | 0% | RP-210907 |  | EBU |  | WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part | [5 empty] | Thu 08/04/21 | NA
664 | 880079 | Additional LTE bands for UE categories M1/M2/NB1/NB2 | LTE_bands_R17_M1_M2_NB1_NB2 | 1 | Rel-17 |  | Mon 08/06/20 | Wed 15/09/21 | 0% | RP-201646 |  | Ericsson |  | 25/9/20: WID:RP-200804->RP-201646 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
665 | 880179 | Core part: LTE_bands_R17_M1_M2_NB1_NB2 | LTE_bands_R17_M1_M2_NB1_NB2-Core | 2 | Rel-17 | R4 | Mon 08/06/20 | Wed 15/09/21 | 0% | RP-201646 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
666 | 880279 | Perf. part: LTE_bands_R17_M1_M2_NB1_NB2 | LTE_bands_R17_M1_M2_NB1_NB2-Perf | 2 | Rel-17 | R4 | Mon 08/06/20 | Wed 15/09/21 | 0% | RP-201646 |  | Ericsson |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
667 | 880081 | Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits | LTE_B24_mod | 1 | Rel-17 |  | Mon 15/06/20 | Fri 19/03/21 | 50% | RP-201356 |  | Ligado Networks |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
668 | 880181 | Core part: LTE_B24_mod | LTE_B24_mod-Core | 2 | Rel-17 | R4 | Mon 15/06/20 | Fri 19/03/21 | 0% | RP-201356 |  | Ligado Networks |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
669 | 880281 | Perf. part: LTE_B24_mod | LTE_B24_mod-Perf | 2 | Rel-17 | R4 | Mon 15/06/20 | Fri 19/03/21 | 100% | RP-201356 |  | Ligado Networks |  | 7/4/21: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
670 | 0 | Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA) | - | 1 | Rel-17 |  | Thu 09/06/16 | Thu 09/06/16 | 0% | - | - | - | - |  | 26.234; 26.247 |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
671 | 880087 | LTE iterbCA for 2 bands DL with 1 band UL | LTE_CA_R17_2BDL_1BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210227 |  | Qualcomm |  | 25/9/20: WID:RP-201248->RP-201754; 6/1/21: WID:RP-201754->RP-202573; 7/4/21: WID:RP-202573->RP-210227 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
672 | 880187 | Core part: LTE_CA_R17_2BDL_1BUL | LTE_CA_R17_2BDL_1BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210227 |  | Qualcomm |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
673 | 880287 | Perf. part: LTE_CA_R17_2BDL_1BUL | LTE_CA_R17_2BDL_1BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210227 |  | Qualcomm |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
674 | 880088 | LTE iterbCA for 3 bands DL with 1 band UL | LTE_CA_R17_3BDL_1BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 50% | RP-210540 |  | Huawei |  | 25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
675 | 880188 | Core part: LTE_CA_R17_3BDL_1BUL | LTE_CA_R17_3BDL_1BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-202615 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
676 | 880288 | Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL | LTE_CA_R17_3BDL_1BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 100% | RP-202615 |  | Huawei |  | 6/1/21: stopped at 0% |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 06/01/21
677 | 880089 | LTE iterbCA Core for x bands DL (x=4, 5, 6) with 1 band UL | LTE_CA_R17_xBDL_1BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210837 |  | Nokia |  | 25/9/20: WID:RP-201245->RP-201911; 6/1/21: WID:RP-201911->RP-202212; 7/4/21: WID:RP-202212->RP-210837 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
678 | 880189 | Core part: LTE_CA_R17_xBDL_1BUL | LTE_CA_R17_xBDL_1BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210837 |  | Nokia |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
679 | 880289 | Perf. part: LTE_CA_R17_xBDL_1BUL | LTE_CA_R17_xBDL_1BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210837 |  | Nokia |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
680 | 880090 | LTE iterbCA for 2 bands DL with 2 bands UL | LTE_CA_R17_2BDL_2BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210542 |  | Huawei |  | 25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542 |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
681 | 880190 | Core part: LTE_CA_R17_2BDL_2BUL | LTE_CA_R17_2BDL_2BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210542 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
682 | 880290 | Perf. part: LTE_CA_R17_2BDL_2BUL | LTE_CA_R17_2BDL_2BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210542 |  | Huawei |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
683 | 880091 | LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL | LTE_CA_R17_xBDL_2BUL | 1 | Rel-17 |  | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210200 |  | LG |  | 25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200 |  | 88 | 45 |  |  | Tue 28/07/20 | NA
684 | 880191 | Core part: LTE_CA_R17_xBDL_2BUL | LTE_CA_R17_xBDL_2BUL-Core | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210200 |  | LG |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | Wed 07/04/21
685 | 880291 | Perf. part: LTE_CA_R17_xBDL_2BUL | LTE_CA_R17_xBDL_2BUL-Perf | 2 | Rel-17 | R4 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-210200 |  | LG |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
686 | 0 | Release 17 other Studies | - | 1 | Rel-17 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
687 | 920020 | Study on Nchf charging services phase 2 | FS_NCHF_Ph2 | 1 | Rel-17 | S5 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210390 |  | Tornkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericsson(dot)com | [6 empty] | Fri 11/06/21 | NA
688 | 920021 | Study on 5G roaming charging architecture for wholesale and retail scenarios | FS_CHROAM | 1 | Rel-17 | S5 | Fri 11/06/21 | Sat 12/03/22 | 0% | SP-210391 |  | Tornkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericsson(dot)com | [6 empty] | Fri 11/06/21 | NA
689 | 910091 | Study on non-seamless WLAN Offload in 5GS using 3GPP credentials | FS_NSWO_5G | 1 | Rel-17 | S3 | Tue 25/05/21 | Wed 08/09/21 | 25% | SP-210262 |  | Nair, Suresh, Nokia | suresh.p.nair@nokia.com | 11/6/21: 0%->25 | [5 empty] | Tue 25/05/21 | Fri 11/06/21
690 | 840085 | Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | 1 | Rel-17 | S2 | Fri 07/06/19 | Wed 10/06/20 | 0% | SP-190562 |  | Huan Li, Huawei | ivy.lihuan@huawei.com | 26/6/19: 23.700-16 added; | 23.700-16 | 84 | 43 |  |  | Sat 03/06/17 | Wed 26/06/19
691 | 840020 | Study on enhancement of 5G UE Policy | FS_eUEPO | 1 | Rel-17 | S2 | Thu 06/06/19 | Thu 12/03/20 | 0% | SP-190449 |  | Changhong Shan, Intel | chang.hong.shan@intel.com | 26/6/19: 23.760 added; | New ; 23.760 | 84 | 43 |  |  | Fri 31/05/19 | Wed 26/06/19
692 | 840021 | Study on the Usage of User Identifiers in the 5G System | FS_UUI5 | 1 | Rel-17 | S2 | Thu 06/06/19 | Fri 12/06/20 | 0% | SP-190450 |  | Starsinic, Michael, Convida Wireless LLC | starsinic.michael@convidawireless.com | 26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; | New ; 23.700-094; | 84 | 43 |  |  | Fri 31/05/19 | Tue 08/10/19
693 | 830031 | Study on service-based support for SMS in 5GC | FS_SB_SMS | 1 | Rel-17 | S2 | Thu 07/03/19 | Thu 05/12/19 | 0% | SP-190184 |  | George Foti | George dot Foti at ericsson dot com |  | New | 83 | 42 |  |  | Thu 14/03/19 | NA
694 | 830034 | Study on UPF enhancement for control and SBA | FS_UPCAS | 1 | Rel-17 | S2 | Thu 07/03/19 | Fri 06/03/20 | 0% | SP-190187 |  | Dan Wang, China Mobile | wangdanyjy@chinamobile.com |  | New | 83 | 42 |  |  | Thu 14/03/19 | NA
695 | 890010 | Study on security aspects of the 5GMSG Service (St1 in Rel16!) | FS_SEC_5GMSG | 1 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 45% | SP-200878 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | 25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21 | 33.862 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
696 | 810032 | Study on 5G security enhancement against false base stations | FS_5GFBS | 1 | Rel-17 | S3 | Thu 06/09/18 | Fri 12/03/21 | 87% | SP-180690 |  | Ivy Guo, Apple | ivy_guo@apple.com | 7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ... | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 19/03/21
697 | 890014 | Study on the security of AMF re-allocation | FS_AMFREAL_SEC | 1 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 70% | SP-200721 |  | Tsiatsis, Vlasios, Ericsson | vlasios.tsiatsis@ericsson.com | 5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21 | 33.864 | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
698 | 900020 | Study on enhanced Security Aspects of the 5G Service Based Architecture | FS_eSBA_SEC | 1 | Rel-17 | S3 | Fri 04/12/20 | Fri 10/12/21 | 70% | SP-201021 |  | Anja Jerichow, Nokia | anja.jerichow@nokia.com | 10/2/21: 33.875 added;; 19/3/21: 0%->45; 19/3/21: FCD:11/06/2021->09/21; 11/6/21: 45%->70; 11/6/21: FCD:Wed 08/09/->12/21 | 33.875 | 90 |  |  |  | Fri 04/12/20 | Fri 11/06/21
699 | 890037 | Study on User Consent for 3GPP services | FS_UC3S | 1 | Rel-17 | S3 | Wed 16/09/20 | Fri 10/12/21 | 50% | SP-200885 |  | Rong Wu, Huawei Technologies | raina.wu@huawei.com | 5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21 | 33.867 | 89 | 45 |  |  | Fri 25/09/20 | Fri 11/06/21
700 | 880004 | Study on security aspects of the Disaggregated gNB Architecture | FS_disagg_gNB_Sec | 1 | Rel-17 | S3 | Thu 25/06/20 | Fri 12/03/21 | 100% | SP-200349 |  | Sen XU, China Telecom | xusen@chinatelecom.cn | 12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100 | 33.84 | 88 | 45 |  |  | Thu 25/06/20 | Fri 19/03/21
701 | 810037 | Study on SECAM and SCAS for 3GPP virtualized network products | FS_VNP_SECAM_SCAS | 1 | Rel-17 | S3 | Tue 02/10/18 | Fri 10/12/21 | 90% | SP-180696 |  | Minpeng Qi, China Mobile | qiminpeng@chinamobile.com | 2/10/18: Moved from Rel-17¦7/12/18: 0%->5¦20/3/19: 5%->20; 13/9/19: 20%->30; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 30%->35; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 35%->60; 5/12/20: 60%->70;... | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 11/06/21
702 | 820007 | Study on Security Impacts of Virtualisation | FS_SIV | 1 | Rel-17 | S3 | Thu 13/12/18 | Fri 10/12/21 | 55% | SP-181236 |  | Alex Leadbeater, BT Plc | alex.leadbeater@bt.com | 20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%->... |  | 82 | 42 |  |  | Thu 06/12/18 | Fri 11/06/21
703 | 820010 | Study on Long Term Key Update Process (LTKUP) Detailed solutions | FS_LTKUP_Detail | 1 | Rel-17 | S3 | Thu 13/12/18 | Thu 12/03/20 | 100% | SP-181038 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100 |  | 82 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
704 | 820009 | Study on authentication enhancements in 5GS | FS_AUTH_ENH | 1 | Rel-17 | S3 | Thu 13/12/18 | Fri 10/12/21 | 85% | SP-190713 |  | Tsiatsis, Vlasios, | vlasios.tsiatsis@ericsson.com | 07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202... | new | 82 | 42 |  |  | Thu 06/12/18 | Fri 11/06/21
705 | 880011 | Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 1 | Rel-17 | S4 | Thu 25/06/20 | Fri 10/12/21 | 65% | SP-200399 |  | Hakju Ryan Lee | hakju00.lee@samsung.com | 25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21 | 26.998 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
706 | 850004 | Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 1 | Rel-17 | S4 | Fri 13/09/19 | Fri 10/12/21 | 20% | SP-190642 |  | Igor CURCIO | igor.curcio@nokia.com | ; 8/10/19: 26.999 added;; 8/10/19: 26.119 added;; 25/3/20: 0%->10; 20/4/20: FCD:12/06/2020->12/20; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 10%->20; 11/6/21: FCD:Fri 11/06/->12/21 | New ; 26.999; 26.119 | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
707 | 900029 | Study on 5G media streaming extensions | FS_5GMS_EXT | 1 | Rel-17 | S4 | Fri 04/12/20 | Wed 08/09/21 | 40% | SP-200937 |  | Iraj Sodagar, Company, Tencent | irajs@live.com | 21/3/21: 0%->5; 11/6/21: 5%->40 |  | 90 |  |  |  | Thu 03/12/20 | Fri 11/06/21
708 | 870015 | Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 1 | Rel-17 | S4 | Wed 25/03/20 | Fri 11/06/21 | 100% | SP-200056 |  | Bouazizi, Imed, Qualcomm | bouazizi@qti.qualcomm.com | 10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100 |  | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
709 | 870013 | Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 1 | Rel-17 | S4 | Wed 25/03/20 | Wed 08/09/21 | 65% | SP-200054 |  | Thomas Stockhammer | tsto@qti.qualcomm.com | 10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65 | 26.925 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
710 | 870011 | Study on 5G Video Codec Characteristics | FS_5GVideo | 1 | Rel-17 | S4 | Wed 25/03/20 | Fri 10/12/21 | 70% | SP-200052 |  | Thomas Stockhammer | tsto@qti.qualcomm.com | 10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21 |  | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
711 | 870012 | Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 1 | Rel-17 | S4 | Wed 25/03/20 | Wed 08/09/21 | 96% | SP-200053 |  | Iraj Sodagar | irajsodagar@tencent.com | ; 10/6/20: 0%->10; 5/12/20: 10%->30; 5/12/20: FCD:11/12/2020->09/20; 21/3/21: 30%->40; 11/6/21: 40%->96 | 26.939 | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
712 | 910031 | Study on Enhancement of service-based management architecture | FS_eSBMA | 1 | Rel-17 | S5 | Thu 18/03/21 | Fri 10/12/21 | 10% | SP-210136 |  | Lan Zou, Huawei | zoulan@huawei.com | ; 11/6/21: 0%->10 | New |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
713 | 910028 | Study on Continuous integration continuous delivery support for 3GPP NFs. | FS_CICDNS | 1 | Rel-17 | S5 | Thu 18/03/21 | Fri 10/09/21 | 15% | SP-210133 |  | Vaishnavi, Ishan, Lenovo | ivaishnavi@lenovo.com | ; 11/6/21: 0%->15 | New |  |  |  |  | Thu 18/03/21 | Fri 11/06/21
714 | 890016 | Study on access control for management service | FS_MNSAC | 1 | Rel-17 | S5 | Wed 16/09/20 | Wed 08/09/21 | 80% | SP-200853 |  | Jing Ping, Nokia | jing.ping@nokia-sbell.com | 25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21 |  | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
715 | 890017 | Study on YANG PUSH | FS_YANG | 1 | Rel-17 | S5 | Wed 16/09/20 | Wed 08/09/21 | 10% | SP-200765 |  | Lengyel, Balazs, Ericsson | balazs.lengyel@ericsson.com | 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10 |  | 89 | 45 |  |  | Thu 10/09/20 | Fri 11/06/21
716 | 870021 | Study on new aspects of EE for 5G networks | FS_EE5G | 1 | Rel-17 | S5 | Wed 25/03/20 | Fri 10/12/21 | 75% | SP-200187 |  | Jean-Michel CORNILY, ORANGE | jeanmichel.cornily@orange.com | 28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21 |  | 87 | 44 |  |  | Fri 06/12/19 | Fri 11/06/21
717 | 911032 | Study on enhanced IMS to 5GC Integration Phase 2 | FS_eIMS5G2 | 1 | Rel-17 | ct | Fri 25/09/20 | Wed 08/09/21 | 17% | CP-201358 |  | Haitao Wei (Huawei) | weihaitao@huawei.com | 13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15 | 23.700-10 | 88 | 45 |  |  | Fri 26/06/20 | Sun 21/03/21
718 | 880024 | CT1 aspects of FS_eIMS5G2 | FS_eIMS5G2 | 2 | Rel-17 | C1 | Fri 25/09/20 | Wed 08/09/21 | 15% | CP-201358 |  | Haitao Wei (Huawei) | weihaitao@huawei.com | 13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15 | 23.700-10 | 88 | 45 |  |  | Fri 26/06/20 | Sun 21/03/21
719 | 911036 | CT3 aspects of FS_eIMS5G2 | FS_eIMS5G2 | 2 | Rel-17 | C3 | Fri 25/09/20 | Wed 08/09/21 | 5% | CP-201358 |  | Haitao Wei (Huawei) | weihaitao@huawei.com | 13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 0%->5 | 23.700-10 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
720 | 911033 | CT4 aspects of FS_eIMS5G2 | FS_eIMS5G2 | 2 | Rel-17 | C4 | Fri 25/09/20 | Wed 08/09/21 | 30% | CP-201358 |  | Haitao Wei (Huawei) | weihaitao@huawei.com | 13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 30%->40; 11/6/21: 40%->30 | 23.700-10 | 88 | 45 |  |  | Fri 26/06/20 | Fri 11/06/21
721 | 900001 | Study on restoration of profiles related to UDR | FS_ReP_UDR | 1 | Rel-17 | C4 | Mon 07/12/20 | Fri 10/09/21 | 40% | CP-203019 |  | Ishikawa, Hiroshi, NTT DOCOMO | hiroshi.ishikawa.ev (at) nttdocomo.com | 21/3/21: 0%->20; 11/6/21: 20%->40 |  | 90 |  |  |  | Sat 05/12/20 | Fri 11/06/21
722 | 890002 | Study on Port Number Allocation Alternatives for New 3GPP Interfaces | FS_PortAl | 1 | Rel-17 | C4 | Wed 16/09/20 | Wed 08/09/21 | 70% | CP-202243 |  | Giorgi Gulbani, Huawei | giorgi.gulbani@huawei.com | 13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70 |  | 89 | 45 |  |  | Fri 11/09/20 | Fri 11/06/21
723 | 800045 | Study on IETF QUIC Transport for Service Based Interfaces | FS_QUIC | 1 | Rel-17 | C4 | Wed 06/06/18 | Wed 08/09/21 | 80% | CP-183245 |  | Sridhar Bhaskaran (Huawei) | sridhar.bhaskaran@huawei.com | 6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: 40%->50¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21 | New; 29.893 | 80 | 41 |  |  | Wed 06/06/18 | Sun 13/09/20
724 | 880075 | Study on scenarios and requirements of in-coverage, partial coverage, and out-of-coverage NR positioning use cases | FS_NR_pos_cov | 1 | Rel-17 | RP | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-201518 |  | LG Electronics |  | 25/9/20: WID:RP-201384->RP-201518 |  | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
725 | 860062 | Study on XR (Extended Reality) evaluations for NR | FS_NR_XR_eval | 1 | Rel-17 | R1 | Mon 16/12/19 | Mon 15/03/21 | 0% | RP-210460 |  | Qualcomm |  | affects: NR.; 28/7/20: WID:RP-193241->RP-201145; 7/4/21: WID:RP-201145->RP-210460 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 07/04/21
726 | 860039 | Study on enhancement of RAN slicing for NR | FS_NR_slice | 1 | Rel-17 | R2 | Mon 16/12/19 | Tue 15/12/20 | 0% | RP-201612 |  | CMCC |  | affects: NR. TR 38.8xx; 25/9/20: WID:RP-193254->RP-201612 |  | 86 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
727 | 880076 | Study on enhancement for data collection for NR and ENDC | FS_NR_ENDC_data_collect | 1 | Rel-17 | R3 | Mon 22/06/20 | Wed 15/09/21 | 0% | RP-201620 |  | CMCC |  | 25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added; | 37.817; 38.817 | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
728 | 850071 | Study on enhanced test methods for FR2 NR UEs | FS_FR2_enhTestMethods | 1 | Rel-17 | R4 | Thu 19/09/19 | Tue 15/09/20 | 0% | RP-210633 |  | Apple |  | TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633 |  | 85 | 43 |  |  | Tue 08/10/19 | Wed 07/04/21
729 | 880077 | Study on high-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands 5 and 12 and NR band n71 | FS_LTE_NR_HPUE_FWVM | 1 | Rel-17 | R4 | Thu 19/03/20 | Thu 19/03/20 | 0% | RP-201261 |  | Nokia |  | 25/9/20: 37.880 added; | 37.88 | 88 | 45 |  |  | Tue 28/07/20 | Fri 25/09/20
730 | 900058 | Study on high power UE (power class 2) for one NR FDD band | FS_NR_PC2_UE_FDD | 1 | Rel-17 | R4 | Mon 14/12/20 | Wed 08/09/21 | 0% | RP-202870 |  | China Unicom |  | TR 38.8xx |  | 90 |  |  |  | Wed 06/01/21 | NA
731 | 900059 | Study on extended 600MHz NR band | FS_NR_600MHz_ext | 1 | Rel-17 | R4 | Mon 14/12/20 | Wed 08/09/21 | 0% | RP-202924 |  | Spark |  | TR 38.8xx |  | 90 |  |  |  | Wed 06/01/21 | NA
732 | 890040 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | FS_NR_eff_BW_util | 1 | Rel-17 | R4 | Thu 17/09/20 | Thu 17/06/21 | 0% | RP-210706 |  | Ericsson |  | TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 07/04/21
733 | 0 | --- RELEASE 16 --- | - | 1 | Rel-16 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
734 | 0 | Release 16 Features and related studies | - | 1 | Rel-16 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
735 | 0 | Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC) | - | 1 | Rel-16 |  | Fri 15/12/17 | Fri 15/12/17 | 31% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
736 | 830098 | Enhancement of URLLC support in the 5G Core network | 5G_URLLC | 1 | Rel-16 |  | Fri 15/12/17 | Fri 11/06/21 | 93% | SP-181122 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Thu 14/03/19
737 | 790008 | Study on enhancement of URLLC supporting in 5GC | FS_5G_URLLC | 2 | Rel-16 | S2 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180118 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 7/6/18: 0%->15¦6/8/18: 23.725 added;¦10/9/18: 15%->60¦7/12/18: 60%->85¦14/3/19: 85%->90; 31/5/19: 90%->95; 13/9/19: 95%->100 | 23.xyz; 23.725 | 79 | 40 |  |  | Thu 15/03/18 | Fri 13/09/19
738 | 810036 | Study on the security of URLLC for 5GS | FS_5G_URLLC_SEC | 2 | Rel-16 | S3 | Thu 06/09/18 | Wed 12/06/19 | 100% | SP-180910 |  | Rong Wu, Huawei Technologies | Raina.wu@huawei.com | 7/12/18: 0%->20¦20/3/19: FCD:019->06/19¦20/3/19: 20%->65; 31/5/19: 65%->80; 13/9/19: 80%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
739 | 820019 | Stage 2 of 5G_URLLC | 5G_URLLC | 2 | Rel-16 | S2 | Thu 13/12/18 | Thu 20/06/19 | 100% | SP-181233 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
740 | 840026 | Security of URLLC for 5GS | 5G_URLLC_SEC | 2 | Rel-16 | S3 | Thu 06/06/19 | Thu 12/03/20 | 100% | SP-190351 |  | Rong Wu, Huawei Technologies | Raina.wu@huawei.com | 13/9/19: 0%->30; 6/12/19: 30%->80; 6/12/19: FCD:12/12/2019->03/20; 9/4/21: 80%->100 | 33.501 | 84 | 43 |  |  | Fri 31/05/19 | Fri 09/04/21
741 | 840005 | CT Aspects of 5G_URLLC | 5G_URLLC | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192022 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 16/9/19: WID:CP-191063->CP-192022 |  | 84 | 43 |  |  | Fri 31/05/19 | Mon 16/09/19
742 | 870059 | CT1 Aspects of 5G_URLLC | 5G_URLLC | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192022 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100 |  | 87 | 44 |  |  | Fri 31/05/19 | Thu 26/03/20
743 | 840060 | CT3 Aspects of 5G_URLLC | 5G_URLLC | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192022 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100 | 29.512; 29.513; 29.514; 29.522; 29.508 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
744 | 840061 | CT4 Aspects of 5G_URLLC | 5G_URLLC | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192022 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 31/5/19: 0%->5; 13/9/19: 5%->20; 6/12/19: 20%->60; 26/3/20: 60%->98; 26/6/20: 98%->100 | 29.244; 29.502; 29.503; 29.510; 29.281 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
745 | 890020 | Charging enhancement for URLLC | 5G_URLLC | 2 | Rel-17 | S5 | Wed 16/09/20 | Fri 11/06/21 | 30% | SP-200769 |  | Chen, Shan, Huawei | chenshan@huawei.com | ; 5/12/20: 0%->20; 5/12/20: FCD:12/03/2021->06/20; 21/3/21: 20%->30 | 32.255; 32.291; 32.298 | 89 | 45 |  |  | Fri 11/09/20 | Sun 21/03/21
746 | 780030 | Stopped - Study on EPC support for Mobility with Low Latency Communication | FS_LLC_Mob | 2 | Rel-16 | S2 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-171069 |  | Chris PUDNEY | chris dot pudney at vodafone dot com | 16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395 | new 23.739 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
747 | 790009 | Stopped - Study on enht of systems using EPS for UR and Availability using commodity equipment | FS_EPS_URACE | 2 | Rel-16 | S2 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180119 |  | Chris Pudney | chris.pudney@vodafone.com | 7/6/18: 0%->10¦6/8/18: 23.736 added¦6/6/19: stopped at 10% as per SP-190395; 6/6/19: 10%->100 | new; 23.736 | 79 | 40 |  |  | Thu 15/03/18 | Thu 06/06/19
748 | 830074 | Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) | NR_L1enh_URLLC | 1 | Rel-16 | R1 | Fri 15/06/18 | Fri 10/06/22 | 70% | RP-191584 |  | Huawei |  | 26/6/19: WID:RP-190726->RP-191584 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
749 | 800095 | Study on physical layer enhancements for NR UR Low Latency Cases | FS_NR_L1enh_URLLC | 2 | Rel-16 | R1 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181477 |  | Huawei |  | TR 38.8xx¦26/3/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
750 | 830174 | Core part: Physical Layer Enhancements for NR URLLC | NR_L1enh_URLLC-Core | 2 | Rel-16 | R1 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-190726 |  | Huawei |  | 26/3/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
751 | 830274 | Perf. part: Physical Layer Enhancements for NR URLLC | NR_L1enh_URLLC-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Tue 15/09/20 | 100% | RP-190726 |  | Huawei |  | 7/4/21: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 07/04/21
752 | 900054 | UE Conformance Test Aspects - Physical Layer Enhancements for NR URLLC | NR_L1enh_URLLC-UEConTest | 2 | Rel-16 | R5 | Mon 14/12/20 | Fri 10/06/22 | 5% | RP-202566 |  | Huawei |  | tested: REL-16 WI NR_L1enh_URLLC-Core ; 8/4/21: 0%->5 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
753 | 830080 | Support of NR Industrial Internet of Things (IoT) | NR_IIOT | 1 | Rel-16 | R2 | Fri 15/06/18 | Wed 15/12/21 | 89% | RP-192590 |  | Nokia |  | 26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
754 | 810060 | Study on channel modeling for indoor industrial scenarios | FS_IIIOT_CM | 2 | Rel-16 | R1 | Fri 14/09/18 | Fri 13/09/19 | 100% | RP-182138 |  | Ericsson |  | 8/10/19: 0%->100 |  | 81 | 41 |  |  | Tue 25/09/18 | Tue 08/10/19
755 | 800098 | Study on NR Industrial Internet of Things (IoT) | FS_NR_IIOT | 2 | Rel-16 | R2 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181479 |  | Nokia |  | TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100 | 38.825 | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
756 | 830180 | Core part: Support of NR Industrial Internet of Things (IoT) | NR_IIOT-Core | 2 | Rel-16 | R2 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200797 |  | Nokia |  | 28/7/20: WID:RP-192590->RP-200797; 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
757 | 880067 | UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT) | NR_IioT-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 68% | RP-200757 |  | CMCC |  | 8/10/20: 0%->5; 8/4/21: 5%->68 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
758 | 820999 | 5GS Enhanced support of Vertical and LAN Services | - | 1 | Rel-16 |  | Fri 15/12/17 | Fri 15/12/17 | 31% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
759 | 750004 | Study on Communication for Automation in Vertical Domains | FS_CAV | 1 | Rel-16 | S1 | Thu 02/03/17 | Thu 15/03/18 | 100% | SP-170169 |  | Walewski, Joachim, Siemens AG | joachim.walewski@siemens.com | 7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100 | 22.804 | 75 | 38 |  |  | Thu 02/03/17 | Thu 07/06/18
760 | 800007 | Service requirements for cyber-physical control applications in vertical domains | cyberCAV | 1 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180321 |  | Joachim W. Walewski (Siemens) |  | 10/9/18: 5%->40¦4/12/18: 40%->100 | 22.261; 22.104 | 80 | 41 |  |  | Wed 06/06/18 | Tue 04/12/18
761 | 830042 | 5GS Enhanced support of Vertical and LAN Services | Vertical_LAN | 1 | Rel-16 |  | Wed 06/06/18 | Thu 12/03/20 | 99% | SP-181120 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com |  |  | 82 | 42 |  |  | Thu 06/12/18 | Thu 14/06/18
762 | 800028 | Study on 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN | 2 | Rel-16 | S2 | Wed 06/06/18 | Fri 14/12/18 | 100% | SP-180507 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com | 10/9/18: 0%->25¦7/12/18: 25%->88¦14/3/19: 88%->92; 31/5/19: 92%->100 | 23.734 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
763 | 820017 | Stage 2 of Vertical_LAN | Vertical_LAN | 2 | Rel-16 | S2 | Thu 13/12/18 | Mon 24/06/19 | 100% | SP-181120 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com | 14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Fri 06/12/19
764 | 810038 | Study on Security for 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN_SEC | 2 | Rel-16 | S3 | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-180697 |  | Jerichow, Anja (Nokia) | anja.jerichow@nokia.com | 7/12/18: 0%->10¦20/3/19: FCD:019->06/19¦20/3/19: 10%->65; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->78; 6/12/19: 78%->92; 25/3/20: 92%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Wed 25/03/20
765 | 840027 | Security for Vertical_LAN | Vertical_LAN_SEC | 2 | Rel-16 | S3 | Thu 06/06/19 | Thu 12/03/20 | 100% | SP-190352 |  | Jerichow, Anja, Nokia | anja.jerichow@nokia.com | 13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100 | 33.501 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
766 | 830010 | CT aspects of Vertical_LAN | Vertical_LAN | 2 | Rel-16 | ct | Thu 14/03/19 | Thu 12/03/20 | 99% | CP-193272 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com | 3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272 |  | 83 | 42 |  |  | Thu 06/12/18 | Mon 09/12/19
767 | 830035 | CT1 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C1 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-193272 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com | 31/5/19: 0%->20; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 20%->75; 6/12/19: 75%->90; 26/3/20: 90%->95; 26/6/20: 95%->99; 13/9/20: 99%->100 | 23.122; 24.368; 24.501; 24.526 | 83 | 42 |  |  | Thu 06/12/18 | Sun 13/09/20
768 | 830036 | CT3 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C3 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-201174 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com | 31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; ; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174 | 29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
769 | 830037 | CT4 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C4 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-193272 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com | 31/5/19: 0%->5; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 5%->50; 6/12/19: 50%->85; 26/3/20: 85%->95; 26/6/20: 95%->100 | 23.003; 23.008; 29.502; 29.503; 29.505; 29.509; 29.510; 29.518; 29.571; 29.244; 29.281 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
770 | 850048 | Service Enabler Architecture Layer for Verticals | SEAL | 1 | Rel-16 |  | Thu 07/03/19 | Fri 12/06/20 | 100% | SP-181141 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 14/3/19: 0%->60; 31/5/19: 60%->95; 8/10/19: 33.434 added;; 8/10/19: 24.548 added; | new 23.434; 33.434; 24.548; 24.547 | 85 | 42 |  |  | Thu 06/12/18 | Tue 08/10/19
771 | 820027 | Stage 2 of SEAL | SEAL | 2 | Rel-16 | S6 | Thu 07/03/19 | Thu 29/08/19 | 100% | SP-181141 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 14/3/19: 0%->60; 31/5/19: 60%->95; 13/9/19: 0%->100 | new 23.434 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
772 | 850019 | Security aspects of SEAL | SEAL | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190901 |  | Rajavelsamy Rajadurai (Samsung) | rajvel@samsung.com | ; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100 | New | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
773 | 850006 | CT aspects of SEAL | SEAL | 2 | Rel-16 | ct | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192255 |  | Sapan Shah (Samsung Electronics) | sapan.shah@samsung.com |  | New | 85 | 43 |  |  | Fri 13/09/19 | NA
774 | 850049 | CT1 aspects of SEAL | SEAL | 3 | Rel-16 | C1 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192255 |  | Sapan Shah (Samsung Electronics) | sapan.shah@samsung.com | ; 6/12/19: 0%->60; 6/12/19: 60%->60; 26/3/20: 60%->80; 26/6/20: 80%->100 | New | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
775 | 850050 | CT3 aspects of SEAL | SEAL | 3 | Rel-16 | C3 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192255 |  | Sapan Shah (Samsung Electronics) | sapan.shah@samsung.com | ; 26/3/20: 0%->75; 26/6/20: 75%->100 | New | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
776 | 820067 | NR-based access to unlicensed spectrum | NR_unlic | 1 | Rel-16 | R1 | Wed 15/03/17 | Sun 15/12/19 | 61% | RP-201834 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834 |  | 82 | 42 |  |  | Wed 16/01/19 | Fri 25/09/20
777 | 750045 | Study on NR-based access to unlicensed spectrum | FS_NR_unlic | 2 | Rel-16 | R1 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-181339 |  | Qualcomm |  | TR 38.8XX19/6/17: WID: RP-170828->RP-171416¦30/6/17: 32.889 added;¦19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%¦27/6/18: Compl:10%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦16/1/19: 40%->100 | 32.889 | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
778 | 820167 | Core part: NR-based access to unlicensed spectrum | NR_unlic-Core | 2 | Rel-16 | R1 | Sat 15/12/18 | Sun 15/12/19 | 100% | RP-201834 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706; 6/1/21: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 06/01/21
779 | 820267 | Perf. part: NR-based access to unlicensed spectrum | NR_unlic-Perf | 2 | Rel-16 | R4 | Sat 15/12/18 | Sun 15/12/19 | 0% | RP-201834 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 26/03/19
780 | 911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | NR_unlic-UEConTest | 2 | Rel-16 | R5 | Fri 12/03/21 | Sun 12/12/21 | 0% | RP-210708 |  | Qualcomm |  | tested: REL-16 WI NR_unlic-Core | [5 empty] | Wed 07/04/21 | NA
781 | 800006 | LAN support in 5G | 5GLAN | 1 | Rel-16 | S1 | Mon 05/06/17 | Fri 14/12/18 | 99% | SP-180593 |  | Almodovar Chico, Jose Luis, KPN | jose.almodovarchico@tno.nl |  | 22.261; 22.278 | 80 | 41 |  |  | Wed 06/06/18 | NA
782 | 760007 | Study on LAN Support in 5G | FS_5GLAN | 2 | Rel-16 | S1 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170456 |  | Nasielski, Jack, Qualcomm Incorporated | jackn@qti.qualcomm.com | 11/9/17: 0%->35¦15/12/17: 35%->65¦16/3/18: 65%->100 | 22.821; | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
783 | 800047 | Stage 1 of 5GLAN | 5GLAN | 2 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/12/18 | 100% | SP-180593 |  | Almodovar Chico, Jose Luis, KPN | jose.almodovarchico@tno.nl | 10/9/18: 40%->75¦10/9/18: FCD:09/18->12/18¦4/12/18: 75%->100 | 22.261; 22.278 | 80 | 41 |  |  | Wed 06/06/18 | Tue 04/12/18
784 | 830024 | Study on non-public networks management | FS_OAM_NPN | 1 | Rel-16 | S5 | Thu 07/03/19 | Fri 12/06/20 | 100% | SP-190137 |  | ZHANG, Kai, Huawei | kai.zhangkai@huawei.com | 31/5/19: 0%->2; 13/9/19: 2%->10; 26/3/20: 10%->70; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 70%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Sun 28/06/20
785 | 0 | Cellular IoT support and evolution | - | 1 | Rel-16 |  | Sat 18/06/16 | Sat 18/06/16 | 17% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
786 | 830043 | Cellular IoT support and evolution for the 5G System | 5G_CIoT | 1 | Rel-16 |  | Fri 08/09/17 | Fri 12/06/20 | 99% | SP-181118 | [5 empty] | 83 | 42 |  |  | Thu 06/12/18 | NA
787 | 770038 | Study on 5G_CIoT | FS_CIoT_5G | 2 | Rel-16 | S2 | Fri 08/09/17 | Fri 14/12/18 | 100% | SP-180614 |  | Sebastian Speicher | sspeiche@qti.qualcomm.com | 11/09/17: rapporteur change¦15/12/17: 23.724 added;¦16/3/18: 0%->20¦7/6/18: 20%->50¦15/6/18: WID:SP-170801->SP-180614¦15/6/18: FCD:09/18->12/18¦10/9/18: 50%->70¦7/12/18: 70%->95; 31/5/19: 95%->100 | New; 23.724 | 77 | 39 |  |  | Fri 08/09/17 | Fri 31/05/19
788 | 820015 | Stage 2 of 5G_CIoT | 5G_CIoT | 2 | Rel-16 | S2 | Thu 13/12/18 | Thu 20/06/19 | 98% | SP-181118 |  | Sebastian Speicher | sspeiche@qti.qualcomm.com | 14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98 | 23.501; 23.502 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
789 | 830013 | CT aspects of 5G_CIoT | 5G_CIoT | 2 | Rel-16 | ct | Thu 14/03/19 | Thu 12/03/20 | 99% | CP-200147 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 3/6/19: WID:CP-190198->CP-111158; 9/12/19: WID:CP-111237->CP-193274; 25/3/20: WID:CP-193274->CP-200147 |  | 83 | 42 |  |  | Thu 06/12/18 | Wed 25/03/20
790 | 830038 | CT1 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C1 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-200147 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 31/5/19: 0%->40; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 40%->60; 6/12/19: 60%->85; 26/3/20: 85%->92; 26/6/20: 92%->99; 13/9/20: 99%->100 | 23.122; 24.250; 24.301; 24.368; 24.501; 27.007 | 83 | 42 |  |  | Thu 06/12/18 | Sun 13/09/20
791 | 830039 | CT3 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C3 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-200147 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100 | 29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
792 | 830040 | CT4 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C4 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-200147 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 31/5/19: 0%->10; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 10%->25; 6/12/19: 25%->60; 26/3/20: 60%->90; 26/6/20: 90%->100 | 23.008; 29.274; 29.502; 29.503; 29.505; 29.518 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
793 | 830041 | CT6 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C6 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-200147 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 26/3/20: 0%->100 | TBD | 83 | 42 |  |  | Thu 06/12/18 | Thu 26/03/20
794 | 850014 | Security of 5G_CIoT | 5G_CIoT | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190897 |  | Henrik Normann, Ericsson | henrik.normann@ericsson.com | 6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100 | 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
795 | 800033 | Study on evolution of Cellular IoT security for the 5G System | FS_CIoT_sec_5G | 1 | Rel-16 | S3 | Wed 06/06/18 | Thu 12/12/19 | 100% | SP-180440 |  | Noamen Ben Henda | noamen.ben.henda@ericsson.com | 6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100 | New; 33.861 | 80 | 41 |  |  | Wed 06/06/18 | Fri 26/06/20
796 | 890021 | Study on charging aspects of 5GS CIoT | FS_5G_CIoT_CH | 1 | Rel-17 | S5 | Wed 16/09/20 | Wed 08/09/21 | 30% | SP-200771 |  | Zhu, Lei, Huawei | lei.zhu@huawei.com | 5/12/20: 0%->15; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 15%->30 |  | 89 | 45 |  |  | Thu 10/09/20 | Sun 21/03/21
797 | 760040 | Study on MBMS User Services for IoT | FS_MBMS_IoT | 1 | Rel-16 | S4 | Mon 05/06/17 | Fri 14/09/18 | 100% | SP-170592 |  | Cedric thienot, Expway | cedric (dot) thienot (at) expway (dot) com | 11/9/17: 0%->10¦15/12/17: 10%->30¦16/3/18: 30%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->90¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 90%->100 | 26.8xx | 76 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
798 | 800083 | Additional MTC enhancements for LTE | LTE_eMTC5 | 1 | Rel-16 | R1 | Fri 15/06/18 | Mon 15/06/20 | 100% | RP-192875 |  | Ericsson |  | RAN3 impact?¦16/1/19: WID:RP-181450->RP-182891¦26/3/19: WID:RP-182891->RP-190770; 26/6/19: WID:RP-190770->RP-191356; 14/1/20: WID:RP-191356->RP-192875 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
799 | 800183 | Core part: Additional MTC enhancements for LTE | LTE_eMTC5-Core | 2 | Rel-16 | R1 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192875 |  | Ericsson |  | RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
800 | 800283 | Perf. part: Additional MTC enhancements for LTE | LTE_eMTC5-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Mon 15/06/20 | 100% | RP-192875 |  | Ericsson |  | 26/3/19: WID:RP-182891->RP-190770; 6/1/21: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 06/01/21
801 | 800084 | Additional enhancements for NB-IoT | NB_IOTenh3 | 1 | Rel-16 | R1 | Fri 15/06/18 | Mon 15/06/20 | 100% | RP-200293 |  | Huawei |  | RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
802 | 800184 | Core part: Additional enhancements for NB-IoT | NB_IOTenh3-Core | 2 | Rel-16 | R1 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200293 |  | Huawei |  | RAN3 impact?¦26/3/19: WID:RP-182902->RP-190757; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
803 | 800284 | Perf. part: Additional enhancements for NB-IoT | NB_IOTenh3-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Mon 15/06/20 | 100% | RP-200293 |  | Huawei |  | 26/3/19: WID:RP-182902->RP-190757; 6/1/21: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 06/01/21
804 | 810050 | 5G message service | 5GMSG | 1 | Rel-16 | S1 | Sat 18/06/16 | Fri 14/12/18 | 100% | SP-180772 |  |  |  |  | 22.262 | 81 | 41 |  |  | Thu 06/09/18 | NA
805 | 770004 | Study on 5G message service for MIoT | FS_5GMSG | 2 | Rel-16 | S1 | Sat 18/06/16 | Fri 14/09/18 | 100% | SP-170704 |  | Zheng, Jianping, China Mobile | zhengjianping@chinamobile.com | 15/12/17: 22.824 added;¦15/12/17: 0%->25¦16/3/18: 25%->60¦10/9/18: 60%->95¦4/12/18: 95%->100 | New; 22.824 | 77 | 39 |  |  | Fri 08/09/17 | Tue 04/12/18
806 | 810014 | Message Service Within the 5G System requirements | MSGin5G | 2 | Rel-16 | S1 | Thu 06/09/18 | Fri 14/12/18 | 100% | SP-180920 |  | Zheng, Jianping, China Mobile | zhengjianping@chinamobile.com | 4/12/18: 0%->100 | 22.262; 22.261 | 81 | 41 |  |  | Thu 06/09/18 | Fri 11/06/21
807 | 0 | Advanced V2X support | - | 1 | Rel-16 |  | Mon 05/06/17 | Mon 05/06/17 | 45% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
808 | 790002 | Study on Improvement of V2X Service Handling | FS_V2XIMP | 1 | Rel-16 | S1 | Thu 15/03/18 | Thu 14/06/18 | 100% | SP-180247 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100 | 22.886 | 79 | 40 |  |  | Thu 15/03/18 | Tue 04/12/18
809 | 820024 | Improvement of V2X service Handling | V2XIMP | 1 | Rel-16 | S1 | Thu 25/10/18 | Tue 04/12/18 | 100% | SP-181013 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 4/12/18: 0%->95¦14/3/19: 95%->100 | 22.186 | 82 | 42 |  |  | Tue 04/12/18 | Thu 14/03/19
810 | 840074 | Application layer support for V2X services | V2XAPP | 1 | Rel-16 |  | Fri 15/12/17 | Thu 12/03/20 | 100% | SP-180898 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 7/12/18: 0%->25¦14/3/19: 25%->65 | New | 84 | 41 |  |  | Thu 06/09/18 | Thu 14/03/19
811 | 780025 | Study on V2XAPP | FS_V2XAPP | 2 | Rel-16 | S6 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-171071 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100 |  | 78 | 40 |  |  | Fri 15/12/17 | Fri 07/12/18
812 | 810020 | Stage 2 of V2XAPP | V2XAPP | 2 | Rel-16 | S6 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180898 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 7/12/18: 0%->25¦14/3/19: 25%->65; 31/5/19: 65%->95; 13/9/19: 95%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
813 | 840010 | CT aspects of V2XAPP | V2XAPP | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192077 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 16/9/19: WID:CP-191153->CP-192077 |  | 84 | 43 |  |  | Fri 31/05/19 | Mon 16/09/19
814 | 840075 | CT1 aspects of V2XAPP | V2XAPP | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192077 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100 | 24.386; 27.007 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
815 | 840076 | CT3 aspects of V2XAPP | V2XAPP | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192077 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 13/9/19: 0%->10; 6/12/19: 10%->60; 26/3/20: 60%->100 | 29.122; 29.116 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
816 | 840077 | CT4 aspects of V2XAPP | V2XAPP | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192077 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 26/3/20: 0%->100 | 23.003; 23.008 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
817 | 840078 | Architecture enhancements for 3GPP support of advanced V2X services | eV2XARC | 1 | Rel-16 |  | Mon 05/06/17 | Thu 12/03/20 | 99% | SP-181121 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | 14/3/19: 0%->30 | 23.501; 23.502; 23.503; 23.285 | 84 | 43 |  |  | Thu 06/12/18 | Thu 14/03/19
818 | 760043 | Study on eV2XARC | FS_eV2XARC | 2 | Rel-16 | S2 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-180733 | SP-170412 | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | 11/9/17: 0%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170379->SP 170590¦16/3/18: 20%->25¦7/6/18: 25%->35¦10/9/18: 35%->58¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP 170590->SP-180733¦7/12/18: 58%->88¦14/3/19: 88%->95; 31/5/19: 95%->100 | 23.786 | 76 | 39 |  |  | Sat 03/06/17 | Fri 31/05/19
819 | 820018 | Stage 2 of eV2XARC | eV2XARC | 2 | Rel-16 | S2 | Thu 13/12/18 | Fri 14/06/19 | 100% | SP-181121 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | 14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100 | 23.501; 23.502; 23.503; 23.285; 24.588 | 82 | 42 |  |  | Thu 06/12/18 | Wed 25/03/20
820 | 840011 | CT aspects of eV2XARC | eV2XARC | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 99% | CP-201343 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 16/9/19: WID:CP-191154->CP-192078; 25/3/20: WID:CP-192078->CP-200291; 2/7/20: WID:CP-200291->CP-201343 |  | 84 | 43 |  |  | Fri 31/05/19 | Thu 02/07/20
821 | 840079 | CT1 aspects of eV2XARC | eV2XARC | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-201343 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100 | 23.122; 24.501; 24.301; 27.007 | 84 | 43 |  |  | Fri 31/05/19 | Sun 13/09/20
822 | 840080 | CT3 aspects of eV2XARC | eV2XARC | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-201343 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 13/9/19: 0%->30; 6/12/19: 30%->80; 26/3/20: 80%->90; 26/6/20: 90%->100; 26/6/20: WID:CP-200291->CP-201199 | 29.512; 29.513; 29.514; 29.519; 29.122; 29.522 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
823 | 840081 | CT4 aspects of eV2XARC | eV2XARC | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-201343 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 26/3/20: 0%->95; 26/6/20: 95%->100 | 23.003; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
824 | 840082 | CT6 aspects of eV2XARC | eV2XARC | 3 | Rel-16 | C6 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-201343 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 26/3/20: 0%->100 | 31.102 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
825 | 860014 | Security Aspects of eV2XARC | eV2XARC | 2 | Rel-16 | S3 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191125 |  | Dongjoo Kim, LG Electronics Inc. | dongjoo7.kim@lge.com | ; 6/12/19: 0%->10; 25/3/20: 10%->70; 26/6/20: 70%->95; 12/9/20: 95%->98; 5/12/20: 98%->99; 19/3/21: 99%->100 | 33.220, TS 33.536 | 86 | 44 |  |  | Fri 06/12/19 | Fri 19/03/21
826 | 800096 | Study on NR Vehicle-to-Everything (V2X) | FS_NR_V2X | 1 | Rel-16 | R1 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-190224 |  | LG Electronics |  | TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
827 | 770029 | Study on V2X Media Handling and Interaction | FS_mV2X | 1 | Rel-16 | S4 | Fri 08/09/17 | Thu 12/09/19 | 100% | SP-170799 |  | Jung, Kyunghun, Samsung Electronics Co., Ltd | kyunghun.jung@samsung.com | 15/12/17: 26.985 added;¦15/12/17: 0%->30¦16/3/18: 30%->50¦22/3/18: FCD:09/18->12/18¦7/6/18: 50%->60. 14/06/18: Moved from Rel-15¦10/9/18: 60%->80¦13/12/18: 80%->60¦13/12/18: FCD:12/18->09/19¦12/3/19: 60%->70; 31/5/19: 70%->80; 26/6/20: 80%->100 | New; 26.985 | 77 | 39 |  |  | Fri 08/09/17 | Fri 26/06/20
828 | 830023 | Study on Security Aspects of 3GPP support for Advanced V2X Services | FS_eV2X_Sec | 1 | Rel-16 | S3 | Thu 07/03/19 | Thu 12/03/20 | 100% | SP-190108 |  | Joonwoong Kim, LG Electronics | joonwoong.kim@lge.com | 31/5/19: 0%->20; 13/9/19: 20%->60; 13/9/19: FCD:05/09/2019->12/20; 6/12/19: 60%->75; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 75%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Fri 26/06/20
829 | 830078 | 5G V2X with NR sidelink | 5G_V2X_NRSL | 1 | Rel-16 | R1 | Fri 01/03/19 | Wed 15/12/21 | 29% | RP-200129 |  | LG Electronics |  | 26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
830 | 830178 | Core part: 5G V2X with NR sidelink | 5G_V2X_NRSL-Core | 2 | Rel-16 | R1 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200129 |  | LG Electronics |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
831 | 830278 | Perf. part: 5G V2X with NR sidelink | 5G_V2X_NRSL-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Tue 15/09/20 | 0% | RP-200129 |  | LG Electronics |  |  |  | 83 | 42 |  |  | Tue 26/03/19 | NA
832 | 880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | 5G_V2X_NRSL_eV2XARC-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 11% | RP-200894 |  | Huawei |  | 8/10/20: 0%->5; 8/4/21: 5%->11 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
833 | 0 | 5G Location and Positionning Services | - | 1 | Rel-16 |  | Mon 05/06/17 | Mon 05/06/17 | 56% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
834 | 800013 | 5G positioning services | 5G_HYPOS | 1 | Rel-16 | S1 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-180329 |  | Ries, Lionel, ESA | lionel.ries at esa.int |  | 22.261 | 80 | 41 |  |  | Wed 06/06/18 | NA
835 | 760006 | Study on positioning use cases | FS_5G_HYPOS | 2 | Rel-16 | S1 | Mon 05/06/17 | Fri 15/06/18 | 100% | SP-170589 |  | Ries, Lionel, ESA | lionel.ries@esa.int | 11/9/17: 0%->10¦15/12/17: 10%->50¦15/12/17: FCD:03/18->06/18¦16/3/18: 50%->75¦7/6/18: 75%->90¦10/9/18: 90%->100 | 22.872 | 76 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
836 | 800049 | Stage 1 of 5G_HYPOS | 5G_HYPOS | 2 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/12/18 | 100% | SP-180329 |  | Ries, Lionel, ESA | lionel.ries at esa.int | 10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100 | 22.261 | 80 | 41 |  |  | Wed 06/06/18 | Tue 04/12/18
837 | 830102 | Enhancement to the 5GC LoCation Services | 5G_eLCS | 1 | Rel-16 |  | Fri 15/12/17 | Fri 12/06/20 | 98% | SP-181119 |  | Ming Ai, CATT | aiming@catt.cn |  | 23.501; 23.502 | 83 | 42 |  |  | Thu 06/12/18 | NA
838 | 780028 | Study on Enhancement to the 5GC Location Services | FS_eLCS | 2 | Rel-16 | S2 | Fri 15/12/17 | Thu 14/03/19 | 100% | SP-180734 |  | Ming Ai, CATT | aiming@catt.cn | 16/3/18: 0%->15¦7/6/18: 15%->45¦10/9/18: 45%->55¦10/9/18: FCD:12/18->03/19¦2/10/18: WID:SP-170937->SP-180734¦7/12/18: 55%->100 | new 23.731 | 78 | 40 |  |  | Fri 15/12/17 | Fri 07/12/18
839 | 810035 | Study on Security of the enhancement to the 5GC location services | FS_eLCS_Sec | 2 | Rel-16 | S3 | Thu 06/09/18 | Fri 13/12/19 | 100% | SP-180694 |  | Wei Zhou, CATT | zhouwei@catt.cn | 7/12/18: 0%->5¦20/3/19: 5%->50; 31/5/19: 50%->80; 13/9/19: 80%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
840 | 820016 | Stage 2 of 5G_eLCS | 5G_eLCS | 2 | Rel-16 | S2 | Thu 13/12/18 | Thu 20/06/19 | 100% | SP-181119 |  | Ming Ai, CATT | aiming@catt.cn | 14/3/19: 0%->45; 31/5/19: 45%->85; 26/6/19: 29.515 added;; 13/9/19: 85%->100 | 23.501; 23.502; 29.515 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
841 | 830003 | CT aspects of 5G_eLCS | 5G_eLCS | 2 | Rel-16 | ct | Thu 07/03/19 | Thu 05/12/19 | 95% | CP-192260 |  | Tingfang Tang, CATT | tangtingfang@catt.cn | 17/9/19: WID:CP-190014->CP-192260 |  | 83 | 42 |  |  | Thu 06/12/18 | Tue 17/09/19
842 | 830044 | CT1 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C1 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-192260 |  | Tingfang Tang, CATT | tangtingfang@catt.cn | 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 0%->40; 6/12/19: 40%->90; 26/6/20: 90%->99; 13/9/20: 99%->100 | 24.501; 27.007 | 83 | 42 |  |  | Thu 06/12/18 | Sun 13/09/20
843 | 830045 | CT3 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C3 | Thu 07/03/19 | Thu 05/12/19 | 85% | CP-192260 |  | Tingfang Tang, CATT | tangtingfang@catt.cn | 3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85 | 29.522; 29.122 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
844 | 830046 | CT4 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C4 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-192260 |  | Tingfang Tang, CATT | tangtingfang@catt.cn | 31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100 | 24.080; 29.518; 29.572; 29.503; 29.505 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
845 | 850017 | Security of 5G_eLCS | 5G_eLCS | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190900 |  | Wei Zhou, CATT | zhouwei@catt.cn | ; 6/12/19: 0%->75; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 75%->100 | 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
846 | 830077 | NR positioning support | NR_pos | 1 | Rel-16 | R1 | Fri 15/06/18 | Fri 10/12/21 | 51% | RP-192581 |  | Intel |  | 26/6/19: WID:RP-190752->RP-191156; 14/1/20: WID:RP-191156->RP-192581 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
847 | 800092 | Study on NR positioning support | FS_NR_pos | 2 | Rel-16 | R1 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181399 |  | Intel |  | TR 38.8xx¦26/3/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
848 | 830073 | Study on local NR positioning in NG-RAN | FS_NR_local_pos | 2 | Rel-16 | R3 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191774 |  | CMCC |  | 8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100 | 38.856 | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
849 | 830177 | Core part: NR positioning support | NR_pos-Core | 2 | Rel-16 | R1 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-192581 |  | Intel |  | 25/9/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Fri 25/09/20
850 | 830277 | Perf. part: NR positioning support | NR_pos-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Tue 15/09/20 | 0% | RP-192581 |  | Intel |  |  |  | 83 | 42 |  |  | Tue 26/03/19 | NA
851 | 900057 | UE Conformance Test Aspects - NR positioning support | NR_pos-UEConTest | 2 | Rel-16 | R5 | Mon 14/12/20 | Fri 10/12/21 | 5% | RP-202727 |  | CATT |  | tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
852 | 0 | UE radio capability signalling optimization | - | 1 | Rel-16 |  | Wed 06/06/18 | Wed 06/06/18 | 17% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
853 | 840054 | Optimisations on UE radio capability signalling | RACS | 1 | Rel-16 |  | Wed 06/06/18 | Thu 12/03/20 | 100% | RP-191460 |  | Haris Zisimopoulos | harisz@qti.qualcomm.com | 26/6/19: WID:SP-190180->RP-191460 | 23.501; 23.502; 23.401 | 84 | 43 |  |  | Thu 14/03/19 | Wed 26/06/19
854 | 800025 | Study on RACS | FS_RACS | 2 | Rel-16 | S2 | Wed 06/06/18 | Fri 14/12/18 | 100% | SP-180599 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 10/9/18: 0%->40¦7/12/18: 40%->70¦14/3/19: 70%->100 | New | 80 | 41 |  |  | Wed 06/06/18 | Thu 14/03/19
855 | 830027 | Stage 2 of RACS | RACS | 2 | Rel-16 | S2 | Thu 07/03/19 | Thu 06/06/19 | 100% | SP-190180 |  | Haris Zisimopoulos | harisz@qti.qualcomm.com | 31/5/19: 0%->90; 26/6/19: 29.673 added;; 13/9/19: 90%->100 | 23.501; 23.502; 23.401; 29.673 | 83 | 42 |  |  | Thu 14/03/19 | Fri 13/09/19
856 | 840003 | CT aspects of RACS | RACS | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-200058 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 17/9/19: WID:CP-191061->CP-192207; 25/3/20: WID:CP-192207->CP-200058 |  | 84 | 43 |  |  | Fri 31/05/19 | Wed 25/03/20
857 | 840055 | CT1 aspects of RACS | RACS | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-200058 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100 | 24.301; 24.501; 24.368; 27.007 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
858 | 840056 | CT3 aspects of RACS | RACS | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-200058 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 13/9/19: 0%->50; 6/12/19: 50%->90; 26/3/20: 90%->100 | 29.122; 29.522 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
859 | 840057 | CT4 aspects of RACS | RACS | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-200058 |  | Waqar Zia; Qualcomm Incorporated | wzia@qti.qualcomm.com | 13/9/19: 0%->20; 6/12/19: 20%->75; 26/3/20: 75%->90; 26/6/20: 90%->100 | 23.003; 23.008; 29.230; 29.274; 29.510; 29.518 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
860 | 830079 | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RACS-RAN | 1 | Rel-16 | R2 | Fri 15/06/18 | Wed 08/09/21 | 66% | RP-200164 |  | MediaTek |  | 26/3/20: WID:RP-190657->RP-200164 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
861 | 800097 | Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects | FS_RACS_RAN | 2 | Rel-16 | R2 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181459 |  | MediaTek |  | TR 37.873¦related SA2 SI FS_RACS was started at SA #80 ¦6/8/18: 37.873 added;¦26/3/19: 0%->100 | 37.873 | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
862 | 830179 | Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RACS-RAN-Core | 2 | Rel-16 | R2 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200164 |  | MediaTek |  | 26/6/19: WID:RP-190657->RP-191088; 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
863 | 880073 | UE Conformance Test Aspects - Optimisations on UE radio capability signalling - NR/E-UTRA Aspects | RACS-UEConTest | 2 | Rel-16 | R5 | Thu 19/03/20 | Wed 08/09/21 | 25% | RP-210714 |  | Qualcomm |  | 8/10/20: 0%->5; 7/4/21: WID:RP-201153->RP-210714; 8/4/21: 5%->25; 8/4/21: FCD:19/03/2021->09/21 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
864 | 800099 | Study on solutions for NR to support non-terrestrial networks (NTN) | FS_NR_NTN_solutions | 1 | Rel-16 | R3 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-190710 |  | Thales |  | TR 38.8xx¦compare REL-15 SI FS_NR_nonterr_nw¦26/3/19: WID:RP-181370->RP-190710; 14/1/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
865 | 0 | Enablers for Network Automation Architecture for 5G | - | 1 | Rel-16 |  | Mon 05/06/17 | Mon 05/06/17 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
866 | 830047 | Enablers for Network Automation for 5G | eNA | 1 | Rel-16 |  | Mon 05/06/17 | Thu 12/03/20 | 99% | SP-181123 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com |  | 23.501; 23.502; 23.503 | 83 | 42 |  |  | Thu 06/12/18 | NA
867 | 760047 | Study of enablers for Network Automation for 5G | FS_eNA | 2 | Rel-16 | S2 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-180792 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com | 16/3/18: FCD:09/18->06/18¦16/3/18: 0%->15¦7/6/18: 15%->30¦15/6/18: WID:SP-170383->SP-180613¦15/6/18: FCD:06/18->09/18¦10/9/18: 30%->50¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-180613->SP-180792¦7/12/18: 50%->90¦14/3/19: 90%->94; 31/5/19: 94%->100 | new 23.791 | 76 | 39 |  |  | Sat 03/06/17 | Fri 31/05/19
868 | 820020 | Stage 2 of eNA | eNA | 2 | Rel-16 | S2 | Thu 06/12/18 | Mon 17/06/19 | 100% | SP-181123 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com | 14/3/19: 0%->50; 31/5/19: 50%->85; 26/6/19: 29.517 added;; 13/9/19: 85%->92; 6/12/19: 92%->97; 25/3/20: 97%->100 | 23.501; 23.502; 23.503; 29.517 | 82 | 42 |  |  | Thu 06/12/18 | Wed 25/03/20
869 | 830009 | CT aspects of eNA | eNA | 2 | Rel-16 | ct | Thu 07/03/19 | Thu 12/03/20 | 99% | CP-192259 |  | Yali Yan, Huawei | yanyali@huawei.com | 3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259 |  | 83 | 42 |  |  | Thu 06/12/18 | Tue 17/09/19
870 | 830048 | CT3 aspects of eNA | eNA | 3 | Rel-16 | C3 | Thu 07/03/19 | Thu 12/03/20 | 100% | CP-192259 |  | Yali Yan, Huawei | yanyali@huawei.com | 31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->55; 6/12/19: 55%->85; 6/12/19: FCD:05/12/2019->03/20; 26/3/20: 85%->100 | 29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554 | 83 | 42 |  |  | Thu 06/12/18 | Thu 26/03/20
871 | 830049 | CT4 aspects of eNA | eNA | 3 | Rel-16 | C4 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-192259 |  | Yali Yan, Huawei | yanyali@huawei.com | 31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100 | 29.244; 29.510; 29.518; 29.503; 29.505 | 83 | 42 |  |  | Thu 06/12/18 | Thu 26/03/20
872 | 0 | Wireless and Wireline Convergence Enhancement | - | 1 | Rel-16 |  | Mon 05/06/17 | Mon 05/06/17 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
873 | 760044 | Study on the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC | 1 | Rel-16 | S2 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-170380 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com | 11/9/17: 0%->15¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 15%->25¦7/6/18: 25%->35¦10/9/18: 35%->60¦10/9/18: FCD:06/18->12/18¦7/12/18: 60%->100 | 23.716 | 76 | 39 |  |  | Sat 03/06/17 | Fri 07/12/18
874 | 800031 | Study on the security of the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC_SEC | 1 | Rel-16 | S3 | Wed 06/06/18 | Thu 12/09/19 | 100% | SP-180438 |  | He Li, Huawei Technologies | LIHE2@HUAWEI.COM | 6/8/18: 33.807 added;¦10/9/18: 0%->5¦7/12/18: 5%->30¦20/3/19: 30%->60¦20/3/19: FCD:019->09/19; 31/5/19: 60%->75; 8/10/19: 75%->100 | New; 33.807 | 80 | 41 |  |  | Wed 06/06/18 | Tue 08/10/19
875 | 830050 | Wireless and Wireline Convergence for the 5G system architecture | 5WWC | 1 | Rel-16 |  | Thu 06/12/18 | Fri 12/06/20 | 99% | SP-181117 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com |  | 23.501; 23.502; 23.503 | 83 | 42 |  |  | Thu 06/12/18 | NA
876 | 820014 | Stage 2 of 5WWC | 5WWC | 2 | Rel-16 | S2 | Thu 06/12/18 | Thu 13/06/19 | 100% | SP-181117 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com | 14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
877 | 830015 | CT aspects of 5WWC | 5WWC | 2 | Rel-16 | ct | Thu 07/03/19 | Thu 12/03/20 | 99% | CP-192079 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 3/6/19: WID:CP-190200->CP-191156. Confusion with UID (was 829910 instead of 830015); 17/9/19: WID:CP-191156->CP-192079; 9/12/19: WID:CP-192079->CP-193145; 2/7/20: WID:CP-193145->CP-192079 |  | 83 | 42 |  |  | Thu 06/12/18 | Thu 02/07/20
878 | 829911 | CT1 aspects of 5WWC | 5WWC | 3 | Rel-16 | C1 | Thu 07/03/19 | Thu 12/03/20 | 100% | CP-192079 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100 | 24.501; 24.502; 24.526 |  |  |  |  | Thu 06/12/18 | Tue 30/06/20
879 | 829912 | CT3 aspects of 5WWC | 5WWC | 3 | Rel-16 | C3 | Thu 07/03/19 | Thu 12/03/20 | 100% | CP-192079 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100 | 29.512; 29.513; 29.514; 29.507; 29.122; 29.522 |  |  |  |  | Thu 06/12/18 | Fri 26/06/20
880 | 829914 | CT4 aspects of 5WWC | 5WWC | 3 | Rel-16 | C4 | Thu 13/06/19 | Thu 12/03/20 | 100% | CP-192079 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 0%->5; 6/12/19: 5%->60; 26/3/20: 60%->95; 26/6/20: 95%->100 | 23.003; 29.518; 29.502; 29.509; 29.244; 29.503; 29.571; 29.505 |  |  |  |  | Thu 06/12/18 | Fri 26/06/20
881 | 850015 | Security of 5WWC | 5WWC | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190898 |  | He Li, Huawei Technologies | lihe2@huawei.com | 13/9/19: 0%->100; 8/10/19: 100%->0; 6/12/19: 0%->90; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 90%->95; 26/6/20: 95%->100 | 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
882 | 860019 | Charging Aspect for 5WWC | 5WWC | 2 | Rel-16 | S5 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191188 |  | ZHU, Lei, Huawei | lei.zhu@huawei.com | ; 26/3/20: 0%->35; 28/6/20: 35%->100 | 32.240; 32.255; 32.291; 32.298 | 86 | 44 |  |  | Fri 06/12/19 | Sun 28/06/20
883 | 830082 | NG interface usage for WWC | 5WWC-NG_interface | 2 | Rel-16 | R3 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-190772 |  | Huawei |  |  |  | 83 | 42 |  |  | Tue 26/03/19 | NA
884 | 830182 | Core part: NG interface usage for WWC | 5WWC-NG_interface-Core | 3 | Rel-16 | R3 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-190999 |  | Huawei |  | 26/6/19: WID:RP-190772->RP-190999; 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
885 | 0 | Mission Critical, Public Warning, Railways and Maritime | - | 1 | Rel-16 |  | Mon 19/09/16 | Mon 19/09/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
886 | 790024 | Study on MC services access aspects | FS_MCSAA | 1 | Rel-16 | S6 | Thu 15/03/18 | Wed 12/06/19 | 100% | SP-181135 |  | Joakim Åkesson, Ericsson | Joakim.akesson@ericsson.com | 19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100 | new 23.xxx; 23.778 | 79 | 40 |  |  | Thu 15/03/18 | Fri 31/05/19
887 | 800024 | Study into discreet listening and logging for mission critical services | FS_MCLOG | 1 | Rel-16 | S6 | Wed 06/06/18 | Wed 12/06/19 | 100% | SP-181138 |  | Chater-Lea, David, Motorola Solutions | david.chater-lea@motorolasolutions.com | 6/8/18: 23.784 added;¦10/9/18: 0%->10¦7/12/18: 10%->50¦7/12/18: FCD:03/19->06/19¦14/12/18: WID:SP-180384->SP-181138¦14/3/19: 50%->75; 31/5/19: 75%->100 | New; 23.784 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
888 | 800022 | Enhanced Mission Critical Push-to-talk architecture phase 2 | enh2MCPTT | 1 | Rel-16 | S6 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-190068 |  | Dom Lazara; Motorola Solutions | Dom.Lazara@motorolasolutions.com | 10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100 | 23.280; 23.379; 23.281; 23.282; 23.283 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
889 | 860026 | Stage 2 of enh2MCPTT | enh2MCPTT | 2 | Rel-16 | S6 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-190068 |  | Dom Lazara; Motorola Solutions | Dom.Lazara@motorolasolutions.com | 10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100; 1/7/20: 0%->100 | 23.280; 23.379; 23.281; 23.282; 23.283 | 80 | 41 |  |  | Wed 06/06/18 | Wed 01/07/20
890 | 860003 | CT aspects of enh2MCPTT | enh2MCPTT-CT | 2 | Rel-16 | C1 | Fri 06/12/19 | Thu 12/03/20 | 100% | CP-193148 |  | Mike Dolan, FirstNet | michael.dolan@firstnet.gov | ; 26/3/20: 0%->100 | 24.379; 24.380; 24.481; 24.482; 24.483; 24.484 | 86 | 44 |  |  | Fri 06/12/19 | Thu 26/03/20
891 | 830051 | Enhancements to Functional architecture and information flows for Mission Critical Data | eMCData2 | 1 | Rel-16 | S6 | Wed 06/06/18 | Thu 12/03/20 | 99% | SP-180378 |  | Shih, Jerry, AT&T | jerry.shih@att.com | 10/9/18: 0%->10¦7/12/18: 10%->40 |  | 83 | 42 |  |  | Wed 06/06/18 | Fri 07/12/18
892 | 800018 | Stage 2 of eMCData2 | eMCData2 | 2 | Rel-16 | S6 | Wed 06/06/18 | Fri 14/06/19 | 100% | SP-180378 |  | Shih, Jerry, AT&T | jerry.shih@att.com | 10/9/18: 0%->10¦7/12/18: 10%->40¦14/3/19: 40%->75; 31/5/19: 75%->90; 13/9/19: 90%->100 | 23.280; 23.282 | 80 | 41 |  |  | Wed 06/06/18 | Fri 13/09/19
893 | 830014 | CT aspects of eMCData2 | eMCData2 | 2 | Rel-16 | C1 | Thu 14/03/19 | Thu 12/03/20 | 100% | CP-193146 |  | Val Oprescu (AT&T) | vo4887@att.com | 31/5/19: 0%->15; 13/9/19: 15%->25; 17/9/19: WID:CP-190199->CP-192081; 6/12/19: 25%->55; 9/12/19: FCD:12/12/2019->03/20; 9/12/19: WID:CP-192081->CP-193146; 26/3/20: 55%->70; 26/6/20: 70%->100 | 24.282; 24.582; 24.483; 24.484; 24.zzz | 72 |  |  |  | Wed 06/06/18 | Fri 26/06/20
894 | 850051 | MCData File Distribution support over xMB | MC_XMB | 1 | Rel-16 |  | Thu 06/09/18 | Thu 12/03/20 | 100% | SP-180665 |  | Thiénot Cédric, Expway | cedric.thienot@expway.com | 7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100 | 26.348 | 85 | 43 |  |  | Thu 06/09/18 | Fri 31/05/19
895 | 810004 | Stage 2 of MC_XMB | MC_XMB | 2 | Rel-16 | S4 | Thu 06/09/18 | Fri 07/06/19 | 100% | SP-180665 |  | Thiénot Cédric, Expway | cedric.thienot@expway.com | 7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100 | 26.348 | 81 | 41 |  |  | Thu 06/09/18 | Fri 31/05/19
896 | 850007 | CT aspects of MC_XMB | MC_XMB-CT | 2 | Rel-16 | C3 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192253 |  | Wenliang Xu, Ericsson | wenliang.xu@ericsson.com | ; 6/12/19: 0%->90; 26/3/20: 90%->100 | 29.116 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
897 | 810011 | Protocol enhancements for Mission Critical Services | MCProtoc16 | 1 | Rel-16 | C1 | Thu 06/09/18 | Fri 20/12/19 | 100% | CP-182110 |  | AXELL, Jörgen | jorgen.axell@ericsson.com | 7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100 | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980 | 81 | 41 |  |  | Thu 06/09/18 | Thu 26/03/20
898 | 800053 | MBMS APIs for Mission Critical Services | MBMSAPI_MCS | 1 | Rel-16 | S6 | Mon 05/06/17 | Thu 14/03/19 | 100% | SP-180380 |  | Ling Zhang, TD Tech Ltd. | zhangling@td-tech.com |  | New | 80 | 41 |  |  | Wed 06/06/18 | NA
899 | 760051 | Study on MBMS APIs for MC Services | FS_MBMSAPI_MC | 2 | Rel-16 | S6 | Mon 05/06/17 | Fri 15/06/18 | 100% | SP-180237 |  | Ling Zhang, TD Tech Ltd | zhangling@td-tech.com | 12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100 | new 23.792 | 76 | 39 |  |  | Sat 03/06/17 | Thu 14/06/18
900 | 800020 | Stage 2 of MBMS APIs for MC Services | MBMSAPI_MCS | 2 | Rel-16 | S6 | Wed 06/06/18 | Thu 14/03/19 | 100% | SP-180380 |  | Ling Zhang, TD Tech Ltd. | zhangling@td-tech.com | 6/8/18: 23.479 added;¦10/9/18: 0%->15¦7/12/18: 15%->65¦14/3/19: 65%->90; 31/5/19: 90%->100 | New; 23.479 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
901 | 840013 | Enhancement of 3GPP Northbound APIs | eNAPIs | 1 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193175 |  | Yali Yan, Huawei | yanyali@huawei.com | ; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: WID:CP-192184->CP-193175 | 29.122; 29.222; 29.522; 29.116 | 84 | 43 |  |  | Fri 31/05/19 | Mon 09/12/19
902 | 850053 | CT3 aspects of eNAPIs | eNAPIs | 2 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193175 |  | Yali Yan, Huawei | yanyali@huawei.com | ; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 6/12/19: 50%->85; 6/12/19: WID:CP-192184->CP-193175; 26/3/20: 85%->100 | 29.122; 29.222; 29.522; 29.116 | 85 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
903 | 850059 | CT4 aspects of eNAPIs | eNAPIs | 2 | Rel-16 | C4 | Tue 17/09/19 | Thu 12/03/20 | 100% | CP-193175 |  | Yali Yan, Huawei | yanyali@huawei.com | ; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100 | 29.122; 29.222; 29.522; 29.116 | 85 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
904 | 800019 | Enhanced Mission Critical System Migration and Interconnection | eMCSMI | 1 | Rel-16 | S6 | Wed 06/06/18 | Wed 12/06/19 | 100% | SP-180379 |  | Chater-Lea, David; Motorola Solutions | david.chater-lea@motorolasolutions.com | 10/9/18: 0%->5¦7/12/18: 5%->10¦7/12/18: FCD:03/19->06/19¦14/3/19: 10%->50; 31/5/19: 50%->100. | 23.280; 23.379; 23.281; 23.282; 23.283 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
905 | 810054 | Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | 1 | Rel-16 |  | Wed 06/06/18 | Fri 14/06/19 | 100% |  |  | Monnes, Peter, Harris Corporation | pmonnes@harris.com |  |  | 80 | 41 |  |  | Mon 10/09/18 | NA
906 | 800021 | Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | 2 | Rel-16 | S6 | Wed 06/06/18 | Fri 14/06/19 | 100% | SP-180680 |  | Monnes, Peter, Harris Corporation | pmonnes at harris dot com | 10/9/18: 0%->5¦2/10/18: WID:SP-180381->SP-180680¦7/12/18: 5%->15¦14/3/19: 15%->40; 31/5/19: 40%->70; 13/9/19: 70%->100 | 23.283 | 80 | 41 |  |  | Wed 06/06/18 | Fri 13/09/19
907 | 800016 | Stage 3 for MC Communication Interworking with Land Mobile Radio Systems | MCCI_CT | 1 | Rel-16 | C1 | Wed 06/06/18 | Thu 12/09/19 | 100% | CP-190203 |  | Monnes, Peter, Harris Corporation | pmonnes@harris.com | 10/9/18: 5%->15¦7/12/18: 15%->45¦10/12/18: FCD:12/18->06/19¦10/12/18: WID:CP-181187->CP-183247. 06/03/19: both name and acronym changed (was MCCI3)¦14/3/19: 45%->60¦18/3/19: WID:CP-183248->CP-190203¦18/3/19: FCD:019->09/19; 31/5/19: 60%->70; 13/9/19: 7... | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 | 80 | 41 |  |  | Wed 06/06/18 | Thu 26/03/20
908 | 800032 | Mission Critical Services Security Enhancements | MCXSec | 1 | Rel-16 | S3 | Wed 06/06/18 | Thu 11/06/20 | 100% | SP-180596 |  | Woodward, Tim, Motorola Solutions, Inc |  | 10/9/18: 0%->40¦7/12/18: 40%->50¦20/3/19: FCD:019->09/19¦20/3/19: 50%->0; 31/5/19: 0%->45; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 45%->55; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 55%->75; 26/6/20: 75%->80; 12/9/20: FCD:12/03/2020->06/20; 9/4/21: 80%... | 33.18 | 80 | 41 |  |  | Wed 06/06/18 | Fri 09/04/21
909 | 780003 | Enhancements of Public Warning System | ePWS | 1 | Rel-16 |  | Mon 19/09/16 | Thu 12/03/20 | 99% | SP-170998 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 16/3/18: 0%->100 |  | 80 | 41 |  |  | Fri 15/12/17 | Fri 16/03/18
910 | 730005 | Study on enhancements of Public Warning System | FS_ePWS | 2 | Rel-16 | S1 | Mon 19/09/16 | Thu 14/09/17 | 100% | SP-160733 |  | SyncTechno Inc., Hyounhee Koo | koo at synctechno dot com | 22.xxx¦1/12/16: 0%->5¦2/3/17: 5%->45¦7/6/17: 45%->75¦30/6/17: 22.869 added;¦25/8/17: 75%->95¦15/12/17: 95%->100 | 22.869 | 73 | 37 |  |  | Mon 19/09/16 | Fri 15/12/17
911 | 800052 | Stage 1 of ePWS | ePWS | 2 | Rel-16 | S1 | Fri 15/12/17 | Fri 14/12/18 | 100% | SP-170998 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 16/3/18: 0%->100 |  | 80 | 41 |  |  | Fri 15/12/17 | Fri 16/03/18
912 | 810012 | CT aspects of enhancements of Public Warning System | ePWS | 2 | Rel-16 | ct | Thu 06/09/18 | Thu 12/03/20 | 99% | CP-191155 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 3/6/19: WID:CP-182228->CP-191155 |  | 81 | 41 |  |  | Thu 06/09/18 | Mon 03/06/19
913 | 810053 | Study on stages 2 and 3 of enhancements of ePWS | ePWS | 3 | Rel-16 | C1 | Mon 10/09/18 | Fri 14/06/19 | 100% | CP-191155 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 7/12/18: 0%->10¦21/3/19: 10%->30; 31/5/19: 30%->85; 3/6/19: WID:CP-182228->CP-191155; 13/9/19: 85%->100 | New | 81 | 41 |  |  | Mon 10/09/18 | Fri 13/09/19
914 | 810047 | CT1 aspects of ePWS | ePWS | 3 | Rel-16 | C1 | Thu 06/09/18 | Thu 12/03/20 | 100% | CP-191155 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 14/3/19: 0%->30; 3/6/19: FCD:14/06/2019->03/20; 3/6/19: WID:CP-182228->CP-191155; 20/9/19: 0%->100; 6/12/19: 100%->65; 26/3/20: 65%->95; 26/6/20: 95%->100 | 23.041 | 81 | 41 |  |  | Thu 06/09/18 | Fri 26/06/20
915 | 810048 | deleted- CT4 aspects of ePWS (Possible impacts) | ePWS | 3 | Rel-16 | C4 | Thu 06/09/18 | Fri 13/12/19 | 100% | CP-191155 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 3/6/19: WID:CP-182228->CP-191155; 16/9/19: 0%->100 | 29.168 | 81 | 41 |  |  | Thu 06/09/18 | Mon 16/09/19
916 | 760054 | Mobile Communication System for Railways 2 | MONASTERY2 | 1 | Rel-16 |  | Mon 05/06/17 | Thu 12/03/20 | 100% | SP-170451 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 15/12/17: 10%->35 | New 22.289; 22.280; 22.281; 22.282; 22.179 | 76 | 42 |  |  | Sat 03/06/17 | Fri 15/12/17
917 | 760005 | Study on MONASTERY2 | FS_FRMCS2 | 2 | Rel-16 | S1 | Mon 05/06/17 | Fri 14/06/19 | 100% | SP-170588 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 15/12/17: 35%->50¦16/3/18: 50%->80¦7/6/18: 80%->85¦10/9/18: FCD:06/18->06/19¦4/12/18: 85%->100 | New 22.889 | 76 | 39 |  |  | Sat 03/06/17 | Tue 04/12/18
918 | 790023 | Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2 | FS_FRMCS2_SA6 | 2 | Rel-16 | S6 | Thu 15/03/18 | Tue 12/03/19 | 100% | SP-181133 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 19/4/18: 0%->5¦14/6/18: 5%->15¦6/8/18: 23.796 added;¦10/9/18: 15%->20¦7/12/18: 20%->65¦7/12/18: FCD:12/18->03/19¦14/3/19: 65%->100 | 23.cde; 23.796 | 79 | 40 |  |  | Thu 15/03/18 | Thu 14/03/19
919 | 760004 | Stage 1 of MONASTERY2 | MONASTERY2 | 2 | Rel-16 | S1 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-170451 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 16/3/18: 35%->55¦7/6/18: 55%->70¦7/6/18: FCD:06/18->12/18¦10/9/18: 70%->75¦4/12/18: 75%->100 | New 22.289; 22.280; 22.281; 22.282; 22.179 | 76 | 39 |  |  | Sat 03/06/17 | Tue 04/12/18
920 | 830007 | Application Architecture for MONASTERY2 | MONASTERY2 | 2 | Rel-16 | S6 | Thu 14/03/19 | Thu 13/06/19 | 100% | SP-190064 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 31/5/19: 0%->100 | 23.280; 23.379; 23.281; 23.282 | 83 | 42 |  |  | Thu 14/03/19 | Fri 31/05/19
921 | 840009 | CT aspects of MONASTERY2 | MONASTERY2 | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193143 |  | Gkatzikis, Lazaros (Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 9/12/19: WID:CP-191152->CP-193143 |  | 84 | 43 |  |  | Fri 31/05/19 | Mon 09/12/19
922 | 840072 | CT1 aspects of MONASTERY2 | MONASTERY2 | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193143 |  | Gkatzikis, Lazaros (Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 13/9/19: 0%->10; 6/12/19: 10%->50; 26/3/20: 50%->65; 26/6/20: 65%->100 | 24.379 ; 24.281 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.581; 24.582 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
923 | 840073 | deleted: CT3 aspects of MONASTERY2 | MONASTERY2 | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193143 |  | Gkatzikis, Lazaros (Nokia) | lazaros(dot)gkatzikis(at)nokia(dot)com | 2/7/20: deleted, put at 100% (was at 0) | 29.165 | 84 | 43 |  |  | Fri 31/05/19 | NA
924 | 840092 | NR support for high speed train scenario | NR_HST | 1 | Rel-16 | R4 | Mon 17/06/19 | Fri 10/12/21 | 76% | RP-191788 |  | CMCC |  | 8/10/19: WID:RP-191512->RP-191788 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 08/10/19
925 | 840192 | Core part: NR support for high speed train scenario | NR_HST-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-191788 |  | CMCC |  | 28/7/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
926 | 840292 | Perf. part: NR support for high speed train scenario | NR_HST-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-202320 |  | CMCC |  | 6/1/21: WID:RP-191788->RP-202320; 6/1/21: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Wed 06/01/21
927 | 900050 | UE Conformance Test Aspects - NR support for high speed train scenario | NR_HST-UEConTest | 2 | Rel-16 | R5 | Mon 14/12/20 | Fri 10/12/21 | 39% | RP-210372 |  | CMCC |  | tested: REL-16 WI NR_HST-Core ; 7/4/21: WID:RP-202328->RP-210372; 8/4/21: 0%->39 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
928 | 800011 | Maritime Communication Services over 3GPP System | MARCOM | 1 | Rel-16 | S1 | Mon 19/09/16 | Thu 13/12/18 | 100% | SP-180594 |  | Hyounhee Koo, SyncTechno Inc | koo at synctechno dot com |  | 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468 | 80 | 41 |  |  | Wed 06/06/18 | NA
929 | 730007 | Study on Maritime Communication Services over 3GPP system | FS_MARCOM | 2 | Rel-16 | S1 | Mon 19/09/16 | Fri 15/06/18 | 100% | SP-170453 |  | SyncTechno Inc., Hyounhee Koo | koo at synctechno dot com | 22.xxx¦1/12/16: 0%->10¦2/3/17: 10%->15¦2/3/17: WID:SP-160556->SP-170166¦10/3/17: FCD:06/17->06/20¦21/3/17: 22.819 added;¦8/6/17: WID:SP-170166->SP-170453¦25/8/17: 15%->35¦15/12/17: 35%->55¦16/3/18: 55%->75¦7/6/18: 75%->95¦10/9/18: 95%->100 | 22.819 | 73 | 37 |  |  | Mon 19/09/16 | Mon 10/09/18
930 | 800051 | Stage 1 of MARCOM | MARCOM | 2 | Rel-16 | S1 | Wed 06/06/18 | Thu 13/12/18 | 100% | SP-180594 |  | Hyounhee Koo, SyncTechno Inc | koo at synctechno dot com | 10/9/18: 0%->70¦4/12/18: 70%->95¦14/3/19: 95%->100 | 22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468 | 80 | 41 |  |  | Wed 06/06/18 | Thu 14/03/19
931 | 0 | Streaming and TV | - | 1 | Rel-16 |  | Thu 01/12/16 | Wed 05/06/19 | 68% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
932 | 800008 | Enhancement of LTE for Efficient delivery of Streaming Service | eLSTR | 1 | Rel-16 | S1 | Thu 01/12/16 | Fri 14/09/18 | 100% | SP-180322 |  | Xia, Xu, China Telecom | xiaxu.bri@chinatelecom.cn |  | 22.278; 22.115 | 80 | 41 |  |  | Wed 06/06/18 | NA
933 | 740001 | Study on eLSTR | FS_eLESTR | 2 | Rel-16 | S1 | Thu 01/12/16 | Thu 15/03/18 | 100% | SP-160960 |  | China Telecommunications, XIA Xu | xiaxu@ctbri.com.cn | 2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100 | 22.833 | 74 | 38 |  |  | Thu 01/12/16 | Fri 16/03/18
934 | 800054 | Stage 1 of eLSTR | eLSTR | 2 | Rel-16 | S1 | Tue 08/05/18 | Fri 14/09/18 | 100% | SP-180322 |  | Xia, Xu, China Telecom | xiaxu.bri@chinatelecom.cn | 15/6/18: FCD:06/18->09/18¦10/9/18: 90%->100 | 22.278; 22.115 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
935 | 800001 | Enhancements to Framework for Live Uplink Streaming | E_FLUS | 1 | Rel-16 | S4 | Wed 06/06/18 | Fri 03/07/20 | 95% | SP-180285 |  | Lo, Charles, Qualcomm Incorporated | clo@qti.qualcomm.com | 10/9/18: 0%->20¦7/12/18: 20%->40¦7/3/19: 40%->45¦7/3/19: FCD:03/19->09/19; 31/5/19: 45%->55; 13/9/19: FCD:20/09/2019->12/20; 13/9/19: 55%->75; 6/12/19: 75%->85; 25/3/20: 85%->90; 25/3/20: FCD:12/12/2019->06/20; 10/6/20: 90%->100; 26/6/20: FCD:12/06/202... | 26.238; 26.939 | 80 | 41 |  |  | Wed 06/06/18 | Fri 26/06/20
936 | 810003 | Coverage and Handoff Enhancements for Multimedia | CHEM | 1 | Rel-16 | S4 | Thu 06/09/18 | Fri 07/06/19 | 100% | SP-180664 |  | Nikolai Leung | nleung@qti.qualcomm.com | 7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100 | 26.114 | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
937 | 770027 | Study on QoE metrics for VR | FS_QoE_VR | 1 | Rel-16 | S4 | Fri 08/09/17 | Fri 20/09/19 | 100% | SP-170614 |  | Ericsson (Gunnar Heikkilä | gunnar.heikkila@ericsson.com | 15/12/17: 26.929 added;¦15/12/17: 26.119 added;¦15/12/17: FCD:06/18->09/18¦15/12/17: 0%->10¦16/3/18: 10%->15¦7/6/18: 15%->20¦7/6/18: FCD:09/18->12/18. 14/06/18: Moved from Rel-15¦10/9/18: 20%->25¦12/3/19: 25%->55¦12/3/19: FCD:12/18->09/19; 31/5/19: 55%... | New; 26.929; 26.119 | 77 | 39 |  |  | Fri 08/09/17 | Fri 31/05/19
938 | 760039 | Study on 5G enhanced Mobile Broadband Media Distribution | FS_5GMedia_Distribution | 1 | Rel-16 | S4 | Mon 05/06/17 | Fri 14/09/18 | 100% | SP-170334 |  | Bouazizi, Imed, Samsung Electronics Co., Ltd., | i (dot) Bouazizi (at) Samsung (dot) com | 11/9/17: 0%->10¦15/12/17: FCD:03/18->06/20¦15/12/17: 10%->25¦16/3/18: 25%->60¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->75; 26/6/20: 75%->100; 25/9/20: 26.998 added; | 26.8xx; 26.998 | 76 | 39 |  |  | Sat 03/06/17 | Fri 25/09/20
939 | 820002 | Media streaming architecture | 5GMSA | 1 | Rel-16 | S4 | Thu 06/12/18 | Wed 12/06/19 | 100% | SP-180984 |  | Frédéric GABIN | Frederic.gabin@ericsson.com | ; 31/5/19: 0%->100 | 26.501; 26.233 | 82 | 42 |  |  | Fri 07/12/18 | Fri 31/05/19
940 | 840000 | VR QoE metrics | VRQoE | 1 | Rel-16 | S4 | Thu 06/06/19 | Thu 12/03/20 | 100% | SP-190331 |  | Gunnar HEIKKILÄ | gunnar.heikkila@ericsson.com | 22.280¦22.281¦22.282¦22.179¦22.289 ; 13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->100 | 22.280; 22.281; 22.282; 22.179; 22.289 | 84 | 43 |  |  | Fri 31/05/19 | Wed 25/03/20
941 | 810040 | Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | 1 | Rel-16 | S4 | Mon 05/06/17 | Thu 12/12/19 | 100% | SP-180663 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com |  | 26.114 | 81 | 41 |  |  | Thu 06/09/18 | NA
942 | 760041 | Study on Media Handling Aspects of Conversational Services in 5G Systems | FS_5G_MEDIA_MTSI | 2 | Rel-16 | S4 | Mon 05/06/17 | Sat 15/09/18 | 100% | SP-170336 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 11/9/17: 0%->5¦15/12/17: 5%->35¦16/3/18: 35%->55¦16/3/18: FCD:03/18->09/18¦7/6/18: 55%->80. 14/06/18: Moved from Rel-15¦10/9/18: 80%->100 | 26.919 | 76 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
943 | 810002 | Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | 2 | Rel-16 | S4 | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-190640 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/12/18: 0%->35¦7/3/19: 35%->50; 31/5/19: 50%->75; 13/9/19: 75%->80; 13/9/19: FCD:13/09/2019->12/20; 19/9/19: WID:SP-180663->SP-190640; 6/12/19: 80%->90; 25/3/20: 90%->100 | 26.114; 26.131; 26.132; 26.223; 26.919 | 81 | 41 |  |  | Thu 06/09/18 | Wed 25/03/20
944 | 770031 | Study on EVS Float Conformance Non Bit-Exact | FS_EVS_FCNBE | 1 | Rel-16 | S4 | Fri 08/09/17 | Fri 14/09/18 | 100% | SP-170618 |  | Fabrice Plante, Intel | fabrice.m.plante@intel.com | 15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100 | New; 26.843 | 77 | 39 |  |  | Fri 08/09/17 | Mon 10/09/18
945 | 820001 | EVS Floating-point Conformance for Non Bit-Exact | EVS_FCNBE | 1 | Rel-16 | S4 | Wed 06/06/18 | Thu 12/12/19 | 100% | SP-180983 |  | Fabrice, Plante, Intel | fabrice.m.plante@intel.om | ¦7/3/19: 0%->25¦7/3/19: 0%->25¦7/3/19: 0%->25. CANNOT CHANGE STARTING DATE… Real one: Thu 06/12/18; 31/5/19: 25%->50; 13/9/19: 50%->80; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 80%->100 | 26.444 | 82 | 42 |  |  | Wed 06/06/18 | Fri 06/12/19
946 | 800003 | Addition of HLG HDR to TV Video Profiles | HLG_HDR | 1 | Rel-16 | S4 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180287 |  | Paul Szucs, Sony Europe Limited | paul.szucs@sony.com | 10/9/18: 0%->100 | 26.116; 26.346; 26.234 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
947 | 0 | User Identities, Authentication, multi-device | - | 1 | Rel-16 |  | Fri 15/12/17 | Fri 15/12/17 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
948 | 800012 | User Identities and Authentication | UIA | 1 | Rel-16 | S1 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-180328 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at |  | 22.101; 22.115 | 80 | 41 |  |  | Wed 06/06/18 | NA
949 | 780004 | Study on a Layer for User Centric Identifiers and Authentication | FS_LUCIA | 2 | Rel-16 | S1 | Fri 15/12/17 | Thu 14/06/18 | 100% | SP-170995 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at | 16/3/18: 0%->60¦7/6/18: 60%->90¦10/9/18: 90%->100 | 22.904 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
950 | 800050 | Stage 1 of User Identities and Authentication | UIA | 2 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180328 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at | 10/9/18: 0%->100 | 22.101; 22.115 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
951 | 810044 | Multi-device and multi-identity | MuD | 1 | Rel-16 |  | Wed 06/06/18 | Mon 15/06/20 | 99% | SP-180315 |  | Peter Bleckert, Ericsson | Peter.Bleckert@ericsson.com |  |  | 80 | 41 |  |  | Wed 06/06/18 | NA
952 | 800004 | Stage 1 of Multi-device and multi-identity | MuD | 2 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180315 |  | Peter Bleckert, Ericsson | Peter.Bleckert@ericsson.com | 10/9/18: 85%->90¦4/12/18: 90%->100 | 22.173 | 80 | 41 |  |  | Wed 06/06/18 | Tue 04/12/18
953 | 810010 | CT aspects of Multi-device and multi-identity | MuD | 2 | Rel-16 | ct | Thu 06/09/18 | Mon 15/06/20 | 99% | CP-200148 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 9/12/19: WID:CP-182227->CP-193273; 25/3/20: WID:CP-193273->CP-200148 |  | 81 | 41 |  |  | Wed 06/06/18 | Wed 25/03/20
954 | 810045 | CT1 aspects of Multi-device and multi-identity | MuD | 3 | Rel-16 | C1 | Thu 06/09/18 | Mon 15/06/20 | 100% | CP-200148 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 7/12/18: 0%->10¦14/3/19: 10%->15; 31/5/19: 15%->35; 13/9/19: 35%->65; 6/12/19: 65%->85; 25/3/20: FCD:14/06/2019->03/20; 26/3/20: 85%->100; 2/7/20: FCD:25/03/2020->06/20 | 24.173; 24.229; 24.167 | 81 | 41 |  |  | Wed 06/06/18 | Thu 02/07/20
955 | 810046 | CT3 aspects of Multi-device and multi-identity | MuD | 3 | Rel-16 | C3 | Thu 06/09/18 | Mon 15/06/20 | 100% | CP-200148 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 7/12/18: 0%->5; 13/9/19: 5%->95; 6/12/19: 95%->98; 26/3/20: 98%->100; 2/7/20: FCD:25/03/2020->06/20 | 29.165 | 81 | 41 |  |  | Wed 06/06/18 | Thu 02/07/20
956 | 0 | Slicing | - | 1 | Rel-16 |  | Fri 08/09/17 | Fri 08/09/17 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
957 | 830103 | Enhancement of Network Slicing | eNS | 1 | Rel-16 |  | Thu 15/03/18 | Sun 12/12/21 | 90% | SP-181232 |  | ZTE, Tricci So | tso at ztetx dot com |  |  | 83 | 42 |  |  | Thu 06/12/18 | NA
958 | 790011 | Study on Enhancement of Network Slicing | FS_eNS | 2 | Rel-16 | S2 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180503 |  | ZTE, Tricci So | tso at ztetx dot com | 7/6/18: 0%->10¦15/6/18: WID:SP-180121->SP-180503¦6/8/18: 23.740 added;¦10/9/18: 10%->50¦7/12/18: 50%->85¦7/12/18: 85%->¦14/3/19: 85%->100 | new; 23.740 | 79 | 40 |  |  | Thu 15/03/18 | Thu 14/03/19
959 | 820023 | Stage 2 of eNS | eNS | 2 | Rel-16 | S2 | Thu 13/12/18 | Thu 20/06/19 | 100% | SP-181232 |  | ZTE, Tricci So | tso at ztetx dot com | 14/3/19: 0%->60; 31/5/19: 60%->100 |  | 82 | 42 |  |  | Thu 06/12/18 | Fri 31/05/19
960 | 830011 | CT aspects of eNS | eNS | 2 | Rel-16 | ct | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-201161 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn | 2/7/20: WID:CP-190196->CP-201161 |  | 83 | 42 |  |  | Thu 06/12/18 | Thu 02/07/20
961 | 830052 | CT1 aspects of eNS | eNS | 3 | Rel-16 | C1 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-201161 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn | 13/9/19: 0%->40; 6/12/19: 40%->85; 26/3/20: 85%->95; 26/6/20: 95%->97; 13/9/20: 97%->100 | 24.501 | 83 | 42 |  |  | Thu 06/12/18 | Sun 13/09/20
962 | 830053 | CT3 aspects of eNS | eNS | 3 | Rel-16 | C3 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-201161 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn | 6/12/19: 0%->80; 26/3/20: 80%->98; 26/6/20: 98%->100 | 29.061; 29.561 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
963 | 830054 | CT4 aspects of eNS | eNS | 3 | Rel-16 | C4 | Thu 07/03/19 | Thu 05/12/19 | 100% | CP-201161 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn | 31/5/19: 0%->30; 13/9/19: 30%->50; 6/12/19: 50%->95; 26/3/20: 95%->85 (went down); 26/6/20: 85%->100 | 29.502; 29.503; 29.505; 29.509; 29.518 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
964 | 810034 | Study on Security aspects of Enhancement of Network Slicing | FS_eNS_SEC | 2 | Rel-16 | S3 | Thu 06/09/18 | Thu 12/03/20 | 100% | SP-180692 |  |  | Suresh.p.nair@nokia.com | 7/12/18: 0%->15¦20/3/19: 15%->65¦20/3/19: FCD:019->06/19; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 26/06/20
965 | 850022 | Security aspects of Enhanced Network Slicing | eNS | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 11/06/21 | 100% | SP-190712 |  | Suresh.p.nair@nokia.com |  | ; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 30%->95; 12/9/20: 95%->97; 19/3/21: FCD:12/06/2020->06/21; 11/6/21: 97%->100 | New | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
966 | 910099 | UE Conformance Test Aspects - Enhancement of Network Slicing | eNS-UEConTest | 2 | Rel-16 | R5 | Fri 12/03/21 | Sun 12/12/21 | 0% | RP-210370 |  | CMCC |  | tested: CT1 and SA3 REL-16 WI eNS (Enhancement of Network Slicing); compare REL-17 SI FS_NR_slice; | [5 empty] | Wed 07/04/21 | NA
967 | 810051 | Business Role Models for Network Slicing | BRMNS | 1 | Rel-16 | S1 | Fri 08/09/17 | Thu 13/12/18 | 100% | SP-180773 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com |  | 22.261 | 81 | 41 |  |  | Thu 06/09/18 | NA
968 | 770005 | Study on Business Role Models for Network Slicing | FS_BMNS | 2 | Rel-16 | S1 | Fri 08/09/17 | Fri 14/09/18 | 100% | SP-180169 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com | 15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100 | New; 22.830 | 77 | 39 |  |  | Fri 08/09/17 | Tue 04/12/18
969 | 810015 | Business Role Models for Network Slicing | BRMNS | 2 | Rel-16 | S1 | Thu 06/09/18 | Thu 13/12/18 | 100% | SP-180773 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com | 10/9/18: 0%->95¦4/12/18: 95%->100 | 22.261 | 81 | 41 |  |  | Thu 06/09/18 | Tue 04/12/18
970 | 810022 | Study on tenancy concept in 5G networks and network slicing management | FS_TENANCYC | 1 | Rel-16 | S5 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180815 |  | ZHU, Lei (Huawei | Lei.zhu@huawei.com | 7/12/18: 0%->20¦14/3/19: 20%->26; 31/5/19: 26%->40; 13/9/19: 40%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
971 | 810031 | Enhancement of performance assurance for 5G networks including network slicing | 5G_SLICE_ePA | 1 | Rel-16 | S5 | Thu 06/09/18 | Thu 12/03/20 | 100% | SP-190247 |  | Xiaowei Sun (China Mobile) |  | 7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70 | 28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623 | 81 | 41 |  |  | Thu 06/09/18 | Fri 31/05/19
972 | 850055 | Overall aspects of 5G_SLICE_ePA | 5G_SLICE_ePA | 2 | Rel-16 | S5 | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-190247 |  | Xiaowei Sun (China Mobile) |  | 7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70; 13/9/19: 70%->85; 13/9/19: 85%->; 26/3/20: 85%->97; 28/6/20: 97%->100 | 28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623 | 81 | 41 |  |  | Thu 06/09/18 | Sun 28/06/20
973 | 850029 | KPI reporting | 5G_SLICE_ePA-KPI | 2 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190881 |  | ZHU, Weihong, ZTE Corporation | zhu.weihong@zte.com.cn | ; 26/3/20: 0%->100 | 28.550; 28.554; 28.622; 28.532 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
974 | 820029 | Study on Charging Aspects of Network Slicing | FS_NETSLICE_CH | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 12/12/19 | 100% | SP-181065 |  | Chen Shan, Huawei | chenshan@huawei.com | 14/3/19: 0%->30¦14/3/19: FCD:06/19->09/19; 31/5/19: 30%->45; 13/9/19: 45%->85; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 85%->100 |  | 82 | 42 |  |  | Fri 07/12/18 | Fri 06/12/19
975 | 0 | Other cross-TSG Release 16 Features | - | 1 | Rel-16 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
976 | 760003 | Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | PARLOS | 1 | Rel-16 |  | Thu 01/12/16 | Fri 13/12/19 | 100% | SP-170449 |  | Covell, Betsy Nokia | betsy.covell@nokia.com | 16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16 | 22.115; 22.101; 22.228 | 76 | 38 |  |  | Sat 03/06/17 | Wed 07/06/17
977 | 740002 | Study on Stage 1 of PARLOS | FS_PARLOS | 2 | Rel-15 | S1 | Thu 01/12/16 | Mon 10/09/18 | 100% | SP-160904 |  | Covell, Betsy | betsy.covell@nokia.com | 1/12/16: 0%->75¦2/3/17: 75%->100¦10/9/18: FCD:03/17->09/18 | 22.82 | 74 | 38 |  |  | Thu 01/12/16 | Mon 10/09/18
978 | 760046 | Study on Stage 2 for PARLOS | FS_PARLOS_SA2 | 2 | Rel-16 | S2 | Mon 05/06/17 | Fri 14/09/18 | 100% | SP-180501 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com | 11/9/17: 0%->20¦16/3/18: FCD:12/17->12/18.¦16/3/18: 20%->45¦23/3/18: WID:SP-170382->SP-180116¦23/3/18: FCD:12/18->06/18¦7/6/18: 45%->70¦15/6/18: WID:SP-180116->SP-180501¦15/6/18: FCD:06/18->09/18¦10/9/18: 70%->100 | 23.715 | 76 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
979 | 800035 | Study on Security Aspects of PARLOS | FS_PARLOS_Sec | 2 | Rel-16 | S3 | Wed 06/06/18 | Thu 12/09/19 | 100% | SP-180442 |  | Greg Schumacher, Sprint | Gregory.schumacher@sprint.com | 6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100 | New; 33.815 | 80 | 41 |  |  | Wed 06/06/18 | Fri 13/09/19
980 | 760071 | Stage 1 of PARLOS | PARLOS | 2 | Rel-16 | S1 | Wed 10/05/17 | Thu 08/06/17 | 100% | SP-170449 |  | Covell, Betsy Nokia | betsy.covell@nokia.com | 7/6/17: 0%->100 | 22.115; 22.101; 22.228 | 76 | 39 |  |  | Sat 03/06/17 | Wed 07/06/17
981 | 810008 | Stage 2 of PARLOS | PARLOS | 2 | Rel-16 | S2 | Thu 06/09/18 | Fri 15/03/19 | 100% | SP-180738 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com) | 14/3/19: 0%->95; 31/5/19: 95%->100 | 23.401; 23.203; 23.221; 23.228; 23.167 | 81 | 41 |  |  | Thu 06/09/18 | Fri 31/05/19
982 | 830012 | CT aspects of PARLOS | PARLOS | 2 | Rel-16 | ct | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com |  |  | 83 | 42 |  |  | Thu 06/09/18 | NA
983 | 830062 | CT1 aspects of PARLOS | PARLOS | 3 | Rel-16 | C1 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com | 31/5/19: 0%->80; 13/9/19: 80%->95; 6/12/19: 95%->98; 26/3/20: 98%->100 | 24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007 | 83 | 42 |  |  | Thu 06/09/18 | Thu 26/03/20
984 | 830063 | CT3 aspects of PARLOS | PARLOS | 3 | Rel-16 | C3 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com | 13/9/19: 0%->95; 26/3/20: 95%->100 | 29.212; 29.213; 29.214 | 83 | 42 |  |  | Thu 06/09/18 | Thu 26/03/20
985 | 830064 | CT4 aspects of PARLOS | PARLOS | 3 | Rel-16 | C4 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com | 6/12/19: 0%->100 | 29.228; 29.229; 29.274 | 83 | 42 |  |  | Thu 06/09/18 | Fri 06/12/19
986 | 830065 | CT6 aspects of PARLOS | PARLOS | 3 | Rel-16 | C6 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com | 31/5/19: 0%->10; 26/3/20: 10%->100 | 31.102; 31.103 | 83 | 42 |  |  | Thu 06/09/18 | Thu 26/03/20
987 | 860015 | Security Aspects of PARLOS | PARLOS | 2 | Rel-16 | S3 | Fri 06/12/19 | Fri 13/12/19 | 100% | SP-191126 |  | Schumacher, Greg, Sprint | Gregory.schumacher@sprint.com | ; 6/12/19: 0%->100 | 33.401 | 86 | 44 |  |  | Fri 06/12/19 | Fri 06/12/19
988 | 820043 | Enhancing Topology of SMF and UPF in 5G Networks | ETSUN | 1 | Rel-16 |  | Fri 08/09/17 | Thu 12/03/20 | 100% | SP-181116 | [5 empty] | 82 | 42 |  |  | Wed 05/12/18 | NA
989 | 770039 | Study on ETSUN | FS_ETSUN | 2 | Rel-16 | S2 | Fri 08/09/17 | Fri 14/12/18 | 100% | SP-180731 |  | Laurent Thiebaut (Nokia) | Laurent.thiebaut@nokia.com | 15/12/17: 23.726 added;¦16/3/18: 0%->25¦7/6/18: 25%->40¦10/9/18: 40%->65¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170743->SP-180731¦2/10/18: FCD:12/18->12/18¦7/12/18: 65%->100 | 23.726 | 77 | 39 |  |  | Fri 08/09/17 | Fri 07/12/18
990 | 820013 | Stage 2 of ETSUN | ETSUN | 2 | Rel-16 | S2 | Fri 07/12/18 | Mon 17/06/19 | 100% | SP-181116 |  |  |  | 14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100 |  | 82 | 42 |  |  | Wed 05/12/18 | Fri 13/09/19
991 | 830002 | CT aspects of ETSUN | ETSUN | 2 | Rel-16 | ct | Fri 08/03/19 | Fri 06/12/19 | 100% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 83 | 42 |  |  | Wed 05/12/18 | NA
992 | 830055 | CT3 aspects of ETSUN | ETSUN | 3 | Rel-16 | C3 | Fri 08/03/19 | Fri 06/12/19 | 100% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 13/9/19: 0%->80; 6/12/19: 80%->85; 26/3/20: 85%->100 | 29.508; 29.561 | 83 | 42 |  |  | Wed 05/12/18 | Thu 26/03/20
993 | 830056 | CT4 aspects of ETSUN | ETSUN | 3 | Rel-16 | C4 | Fri 08/03/19 | Fri 06/12/19 | 100% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 31/5/19: 0%->25; 13/9/19: 25%->95; 6/12/19: 95%->100 | 29.244; 29.502; 29.510; 29.518; 29.281 | 83 | 42 |  |  | Wed 05/12/18 | Fri 06/12/19
994 | 850024 | Charging aspects of ETSUN | ETSUN | 2 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190880 |  | Dong, Jia, China Mobile | dongjia@chinamobile.com | ; 6/12/19: 0%->70; 26/3/20: 70%->100 | 32.255; 32.291; 32.298 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
995 | 820044 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture | ATSSS | 1 | Rel-16 |  | Mon 05/06/17 | Thu 12/03/20 | 100% | SP-181124 |  | So, Tricci, ZTE | tso@ztetx.com |  | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | NA
996 | 760052 | Study on ATSSS | FS_ATSSS | 2 | Rel-16 | S2 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-180732 |  | So, Tricci, ZTE | tso@ztetx.com | 11/9/17: 0%->100¦14/9/17: 100%->10¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 10%->20¦7/6/18: 20%->40¦10/9/18: 40%->70¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170411->SP-180732¦2/10/18: FCD:12/18->12/18¦7/12/18: 70%->100 | new 23.793 | 76 | 39 |  |  | Sat 03/06/17 | Fri 07/12/18
997 | 820021 | Stage 2 of ATSSS | ATSSS | 2 | Rel-16 | S2 | Fri 14/12/18 | Fri 21/06/19 | 100% | SP-181124 |  | So, Tricci, ZTE | tso@ztetx.com | 14/3/19: 0%->45; 31/5/19: 45%->85; 13/9/19: 85%->100 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
998 | 830016 | CT aspects of ATSSS | ATSSS | 2 | Rel-16 | ct | Mon 11/03/19 | Mon 09/12/19 | 100% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn |  |  | 83 | 42 |  |  | Thu 06/12/18 | NA
999 | 830057 | CT1 aspects of ATSSS | ATSSS | 3 | Rel-16 | C1 | Mon 11/03/19 | Mon 09/12/19 | 100% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 31/5/19: 0%->25; 13/9/19: 25%->55; 6/12/19: 55%->65; 26/3/20: 65%->70; 26/6/20: 70%->100 | 24.501; 24.526; 24.502 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
1000 | 830058 | CT3 aspects of ATSSS | ATSSS | 3 | Rel-16 | C3 | Mon 11/03/19 | Mon 09/12/19 | 100% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 31/5/19: 0%->50; 13/9/19: 50%->55; 6/12/19: 55%->60; 26/3/20: 60%->100 | 29.512; 29.513 | 83 | 42 |  |  | Thu 06/12/18 | Thu 26/03/20
1001 | 830059 | CT4 aspects of ATSSS | ATSSS | 3 | Rel-16 | C4 | Mon 11/03/19 | Mon 09/12/19 | 100% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | 31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100 | 29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
1002 | 840999 | (IETF) TCP Extensions for Multipath Operation with Multiple Addresses (draft-ietf-mptcp-rfc6824bis) | ATSSS | 3 | Rel-16 | S2-IETF | Wed 26/06/19 | Mon 09/12/19 | 100% |  |  |  |  | 23/4/20: 80%->100; 9/4/21: RFC 8684 added; | RFC 8684 | 84 | 43 |  |  | Wed 26/06/19 | Fri 09/04/21
1003 | 840998 | (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters) | ATSSS | 3 | Rel-16 | S2-IETF | Wed 26/06/19 | Mon 09/12/19 | 100% |  |  |  |  | 23/4/20: 30%->90; 25/9/20: 90%->100; 9/4/21: RFC 8803 added; | RFC 8803 | 84 | 43 |  |  | Wed 26/06/19 | Fri 09/04/21
1004 | 860018 | Charging Access of ATSSS | ATSSS | 2 | Rel-16 | S5 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191187 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | ; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100 | 32.255; 32.290; 32.291; 32.298 | 86 | 44 |  |  | Fri 06/12/19 | Sun 13/09/20
1005 | 810041 | Single radio voice continuity from 5GS to 3G | 5G_SRVCC | 1 | Rel-16 |  | Thu 15/03/18 | Fri 10/09/21 | 90% | SP-180737 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn |  | 23.216; 23.501; 23.502 | 81 | 41 |  |  | Thu 06/09/18 | NA
1006 | 790010 | Study for single radio voice continuity from 5GS to 3G | FS_5G-SRVCC | 2 | Rel-16 | S2 | Thu 15/03/18 | Fri 15/06/18 | 100% | SP-180239 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 7/6/18: 0%->80¦6/8/18: 23.756 added;¦10/9/18: 80%->100 | 23.756 | 79 | 40 |  |  | Thu 15/03/18 | Mon 10/09/18
1007 | 810007 | Single radio voice continuity from 5GS to 3G | 5G_SRVCC | 2 | Rel-16 | S2 | Thu 06/09/18 | Thu 14/03/19 | 100% | SP-180897 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 14/3/19: 0%->100 | 23.216; 23.501; 23.502 | 81 | 41 |  |  | Thu 06/09/18 | Thu 14/03/19
1008 | 820008 | Security aspects of single radio voice continuity from 5GS to UTRAN | 5GS_UTRAN_SEC | 2 | Rel-16 | S3 | Thu 13/12/18 | Wed 12/06/19 | 100% | SP-190703 |  | Feng Gao, China Unicom | gaofeng149@chinaunicom.cn | 20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703 | 33.501; 33.401; 33.220 | 82 | 42 |  |  | Thu 13/12/18 | Fri 20/09/19
1009 | 820069 | RAN aspects of 5G_SRVCC | SRVCC_NR_to_UMTS | 2 | Rel-16 | R2 | Sat 15/12/18 | Sun 15/12/19 | 79% | RP-200151 |  | China Unicom |  | no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: WID:RP-190713->RP-200151 |  | 82 | 42 |  |  | Wed 16/01/19 | Thu 26/03/20
1010 | 820169 | Core part: Single Radio Voice Call Continuity from 5G to 3G | SRVCC_NR_to_UMTS-Core | 3 | Rel-16 | R2 | Sat 15/12/18 | Sun 15/12/19 | 100% | RP-200151 |  | China Unicom |  | no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Thu 26/03/20
1011 | 830270 | Perf. part: Single Radio Voice Call Continuity from 5G to 3G | SRVCC_NR_to_UMTS-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Mon 01/06/20 | 100% | RP-200151 |  | China Unicom |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1012 | 890046 | UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G | SRVCC_NR_to_UMTS-UEConTest | 3 | Rel-16 | R5 | Thu 17/09/20 | Fri 10/09/21 | 31% | RP-210400 |  | China Unicom |  | tested: REL-16 WI SRVCC_NR_to_UMTS-Core ; 7/4/21: WID:RP-201794->RP-210400; 8/4/21: 0%->31; 8/4/21: FCD:08/09/2021->09/21 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1013 | 840004 | CT aspect of 5G_SRVCC | 5G_SRVCC | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193014 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 6/12/19: WID:CP-191062->CP-193014 |  | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
1014 | 840058 | CT1 aspect of 5G_SRVCC | 5G_SRVCC | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193014 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 13/9/19: 0%->65; 6/12/19: 65%->90; 26/3/20: 90%->100 | 24.501; 24.237; 24.008; 27.007 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1015 | 860027 | CT3 aspect of 5G_SRVCC | 5G_SRVCC | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193014 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 6/12/19: created, 0%->60; 26/3/20: 60%->100 |  | 86 | 44 |  |  | Fri 31/05/19 | Thu 26/03/20
1016 | 840059 | CT4 aspect of 5G_SRVCC | 5G_SRVCC | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193014 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100 | 29.303; 29.503; 29.504; 29.505; 29.518; 29.274 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1017 | 790005 | Study on Remote Identification of Uncrewed Aerial Systems | FS_ID_UAS | 1 | Rel-16 | S1 | Thu 15/03/18 | Fri 14/09/18 | 100% | SP-180172 |  | Eddy Hall; Qualcomm Incorporated | edhall@qti.qualcomm.com | 7/6/18: 0%->60¦10/9/18: 60%->100 | 22.825 | 79 | 40 |  |  | Thu 15/03/18 | Mon 10/09/18
1018 | 800034 | Study on Security Aspects of the 5G Service Based Architecture | FS_SBA_Sec | 1 | Rel-16 | S3 | Wed 06/06/18 | Thu 12/03/20 | 100% | SP-180598 |  | Hans Christian Rudolph, Deutsche Telekom AG | hans-christian.rudolph@telekom.de | 6/8/18: 33.855 added;¦10/9/18: 65%->75¦7/12/18: 75%->76¦20/3/19: 76%->65¦20/3/19: FCD:018->09/19; 31/5/19: 65%->75; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100 | New; 33.855 | 80 | 41 |  |  | Wed 06/06/18 | Fri 26/06/20
1019 | 820045 | Enhancements to the Service-Based 5G System Architecture | 5G_eSBA | 1 | Rel-16 |  | Thu 15/03/18 | Fri 12/06/20 | 100% | SP-181125 | [5 empty] | 82 | 42 |  |  | Thu 06/12/18 | NA
1020 | 790007 | Study on Enhancements to the Service-Based 5G System Architecture | FS_eSBA | 2 | Rel-16 | S2 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180231 |  | Tao Sun (China Mobile) | suntao@chinamobile.com | 7/6/18: 0%->15¦6/8/18: 23.742 added;¦10/9/18: 15%->60¦7/12/18: 60%->100 | 23.xxx; 23.742 | 79 | 40 |  |  | Thu 15/03/18 | Fri 07/12/18
1021 | 820022 | Stage 2 of 5G_eSBA | 5G_eSBA | 2 | Rel-16 | S2 | Thu 13/12/18 | Thu 20/06/19 | 100% | SP-181125 |  | Tao Sun (China Mobile) | suntao@chinamobile.com | 14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100 | 23.501; 23.502; 23.503 | 82 | 42 |  |  | Thu 06/12/18 | Fri 13/09/19
1022 | 830001 | CT aspects of 5G_eSBA | 5G_eSBA | 2 | Rel-16 | ct | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com |  |  | 83 | 42 |  |  | Thu 06/12/18 | NA
1023 | 830060 | CT3 aspects of 5G_eSBA | 5G_eSBA | 3 | Rel-16 | C3 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com | 6/12/19: 0%->30; 26/3/20: 30%->100 | 29.507; 29.508; 29.513; 29.512; 29.514; 29.519; 29.520; 29.521; 29.523; 29.525; 29.551; 29.554 | 83 | 42 |  |  | Thu 06/12/18 | Thu 26/03/20
1024 | 830061 | CT4 aspects of 5G_eSBA | 5G_eSBA | 3 | Rel-16 | C4 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com | 31/5/19: 0%->10; 13/9/19: 10%->40; 6/12/19: 40%->70; 26/3/20: 70%->95; 26/6/20: 95%->100 | 29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.518; 29.531; 29.540; 29.571; 29.572; 29.573 | 83 | 42 |  |  | Thu 06/12/18 | Fri 26/06/20
1025 | 850016 | Security for 5G_eSBA | 5G_eSBA | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190899 |  | Nagendra Bykampadi, Nokia | nagendra.bykampadi@nokia.com | ; 6/12/19: 0%->45; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 45%->70; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 70%->95; 12/9/20: 95%->100 | 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Sat 12/09/20
1026 | 780029 | Study on Enhanced IMS to 5GC Integration | FS_eIMS5G | 1 | Rel-16 | S2 | Fri 15/12/17 | Fri 14/06/19 | 100% | SP-180736 |  | Joul, Chris, T-Mobile USA | chris <dot> joul <at> t-mobile <dot> com | 16/3/18: 0%->20¦7/6/18: 20%->40¦10/9/18: FCD:09/18->06/19¦2/10/18: WID:SP-171052->SP-180736¦14/3/19: 40%->70; 6/12/19: 70%->100 | new 23.794 | 78 | 40 |  |  | Fri 15/12/17 | Fri 06/12/19
1027 | 840062 | SBA aspects of enhanced IMS to 5GC integration | eIMS5G_SBA | 1 | Rel-16 |  | Thu 14/03/19 | Thu 13/06/19 | 100% | SP-190181 |  | T-Mobile USA, Christopher Joul |  |  | 23.501; 23.502; 23.503; 23.228 | 84 | 42 |  |  | Thu 14/03/19 | NA
1028 | 830028 | Stage 2 of eIMS5G_SBA | eIMS5G_SBA | 2 | Rel-16 | S2 | Thu 14/03/19 | Thu 13/06/19 | 100% | SP-190181 |  | T-Mobile USA, Christopher Joul |  | 31/5/19: 0%->100 | 23.501; 23.502; 23.503; 23.228 | 83 | 42 |  |  | Thu 14/03/19 | Fri 31/05/19
1029 | 840006 | CT aspects of eIMS5G_SBA | eIMS5G_SBA | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192023 |  | de Gregorio, Jesus. Ericsson | jesus.de.gregorio@ericsson.com | 16/9/19: WID:CP-191065->CP-192023 |  | 84 | 43 |  |  | Fri 31/05/19 | Mon 16/09/19
1030 | 850056 | CT1 aspects of eIMS5G_SBA | eIMS5G_SBA | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192023 |  | de Gregorio, Jesus. Ericsson | jesus.de.gregorio@ericsson.com | 6/12/19: 0%->70; 26/6/20: 70%->100 |  | 85 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
1031 | 840063 | CT3 aspects of eIMS5G_SBA | eIMS5G_SBA | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192023 |  | de Gregorio, Jesus. Ericsson | jesus.de.gregorio@ericsson.com | 13/9/19: 0%->70; 6/12/19: 70%->90; 26/3/20: 90%->100 | 29.513; 29.514 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1032 | 840064 | CT4 aspects of eIMS5G_SBA | eIMS5G_SBA | 3 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192023 |  | de Gregorio, Jesus. Ericsson | jesus.de.gregorio@ericsson.com | 13/9/19: 0%->25; 6/12/19: 25%->50; 26/3/20: 50%->90; 26/6/20: 90%->100 | 29.510; 29.571; 23.380 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
1033 | 830081 | Private Network Support for NG-RAN | NG_RAN_PRN | 1 | Rel-16 | R3 | Fri 01/03/19 | Wed 15/12/21 | 46% | RP-200122 |  | China Telecom |  | 26/3/20: WID:RP-190729->RP-200122 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
1034 | 830181 | Core part: Private Network Support for NG-RAN | NG_RAN_PRN-Core | 2 | Rel-16 | R3 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200122 |  | China Telecom |  | 26/6/19: WID:RP-190729->RP-191563; 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1035 | 880072 | UE Conformance Test Aspects - Private Network Support for NG-RAN | NG_RAN_PRN_Vertical_LAN-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 10% | RP-201152 |  | Qualcomm |  | 8/10/20: 0%->5; 8/4/21: 5%->10 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
1036 | 810039 | Media Handling Aspects of RAN Delay Budget Reporting in MTSI | E2E_DELAY | 1 | Rel-16 |  | Fri 15/12/17 | Thu 12/12/19 | 100% | SP-180662 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com |  | 26.114 | 81 | 41 |  |  | Thu 06/09/18 | NA
1037 | 780022 | Study on E2E_DELAY | FS_E2E_DELAY | 2 | Rel-16 | S4 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170837 |  | Oyman, Ozgur, Company: Intel, | ozgur.oyman@intel.com | 16/3/18: 0%->10¦7/6/18: 10%->60¦10/9/18: 60%->100 | new | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1038 | 810001 | Stage 2 of E2E_DELAY | E2E_DELAY | 2 | Rel-16 | S4 | Thu 06/09/18 | Fri 07/06/19 | 100% | SP-180662 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/12/18: 0%->75¦7/3/19: 75%->85¦7/3/19: FCD:03/19->06/19; 31/5/19: 85%->100 | 26.114 | 81 | 41 |  |  | Thu 06/09/18 | Fri 31/05/19
1039 | 830004 | CT Aspects of E2E_DELAY | E2E_DELAY | 2 | Rel-16 | ct | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com |  |  | 83 | 42 |  |  | Thu 06/09/18 | NA
1040 | 830066 | CT1 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C1 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com | 31/5/19: 0%->100; 13/9/19: 100%->100 | 24.229 | 83 | 42 |  |  | Thu 06/09/18 | Fri 13/09/19
1041 | 830067 | CT3 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C3 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com | 31/5/19: 0%->100 | 29.162 | 83 | 42 |  |  | Thu 06/09/18 | Fri 31/05/19
1042 | 830068 | CT4 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C4 | Thu 14/03/19 | Thu 12/12/19 | 100% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com | 31/5/19: 0%->100 | 23.334; 29.334; 29.238; 23.333; 29.333 | 83 | 42 |  |  | Thu 06/09/18 | Fri 31/05/19
1043 | 830069 | Enhancements for Common API Framework for 3GPP Northbound APIs | eCAPIF | 1 | Rel-16 |  | Thu 15/03/18 | Thu 12/03/20 | 100% | SP-181137 |  | Basavaraj Pattan, Samsung | basavarajjp@samsung.com | 7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137 | 23.222 | 83 | 42 |  |  | Thu 15/03/18 | Thu 13/12/18
1044 | 790022 | Stage 2 for eCAPIF | eCAPIF | 2 | Rel-16 | S6 | Thu 15/03/18 | Wed 12/06/19 | 100% | SP-181137 |  | Basavaraj Pattan, Samsung | basavarajjp@samsung.com | 7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137¦14/3/19: 45%->80; 31/5/19: 80%->100 | 23.222 | 79 | 40 |  |  | Thu 15/03/18 | Fri 31/05/19
1045 | 830022 | Security aspects of eCAPIF | eCAPIF | 2 | Rel-16 | S3 | Thu 07/03/19 | Thu 12/12/19 | 100% | SP-1901240 |  | Rajavelsamy Rajadurai, Samsung | rajvel{@]samsung.com | 31/5/19: 0%->30; 31/5/19: 0%->30; 31/5/19: 0%->30; 13/9/19: 30%->90; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 90%->100 | 33.122 | 83 | 42 |  |  | Thu 14/03/19 | Fri 06/12/19
1046 | 850008 | CT aspects of eCAPIF | eCAPIF | 2 | Rel-16 | C3 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192254 |  | Narendranath Durga, Tangudu (Samsung) | n.tangudu {@]samsung.com | ; 6/12/19: 0%->65; 26/3/20: 65%->95; 26/6/20: 95%->100 | 29.222 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
1047 | 840065 | User data interworking, Coexistence and Migration | UDICOM | 1 | Rel-16 | S2 | Thu 14/03/19 | Fri 14/06/19 | 99% | SP-190182 |  | Alessio Casati, Nokia | Alessio.casati@nokia.com |  | 23.501; 23.502; 23.228 | 84 | 42 |  |  | Thu 14/03/19 | NA
1048 | 800055 | Study on UDICOM | FS_UDICoM | 2 | Rel-16 | S2 | Fri 15/06/18 | Wed 12/06/19 | 100% | SP-190148 |  | Susana Sabater (Vodafone | susana.sabater@vodafone.com | 10/9/18: 0%->30¦2/10/18: WID:SP-180620->SP-180735¦7/12/18: 30%->80¦14/12/18: FCD:12/18->03/20¦14/3/19: 80%->100¦21/3/19: WID:SP-181110->SP-190148¦21/3/19: FCD:019->06/19; 13/9/19: 75%->100 | 23.732; new | 80 | 41 |  |  | Fri 15/06/18 | Fri 13/09/19
1049 | 830029 | Stage 2 of UDICOM | UDICOM | 2 | Rel-16 | S2 | Thu 14/03/19 | Fri 14/06/19 | 100% | SP-190182 |  | Alessio Casati, Nokia | Alessio.casati@nokia.com | 6/6/19: 0%->100; 26/6/19: 23.632 added; | 23.501; 23.502; 23.228; 23.632 | 83 | 42 |  |  | Thu 14/03/19 | Wed 26/06/19
1050 | 840007 | CT aspects of UDICOM | UDICOM | 2 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-193016 |  | Wiehe, Ulrich, Nokia | ulrich.wiehe@nokia.com | 31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->75; 9/12/19: WID:CP-191066->CP-193016; 26/3/20: 75%->90; 26/6/20: 90%->100 | 29.503; 29.505; 29.571; 29.510 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
1051 | 910008 | UICC-terminal interface testing for UEs with non-removable UICCs | nrUICC_UEConTest | 1 | Rel-16 | C6 | Thu 18/03/21 | Fri 10/12/21 | 5% | CP-210285 |  | Marquordt, Arne, COMPRION GmbH | amarquordt@comprion.com | ; 21/3/21: 0%->5 | 31.122; 31.213 |  |  |  |  | Thu 18/03/21 | Sun 21/03/21
1052 | 800036 | Study on authentication and key management for applications based on 3GPP credential in 5G | FS_AKMA | 1 | Rel-16 | S3 | Wed 06/06/18 | Thu 12/12/19 | 100% | SP-180443 |  | Jin Peng, China Mobile | pengjin@chinamobile.com | 6/8/18: 33.835 added;¦7/12/18: 5%->20¦20/3/19: 20%->60¦20/3/19: FCD:019->09/19; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->12/19; 6/12/19: 70%->95; 26/6/20: 95%->100 | New; 33.835 | 80 | 41 |  |  | Wed 06/06/18 | Fri 26/06/20
1053 | 900018 | Removal of AKMA from Rel-16 | RM_AKMA_R16 | 1 | Rel-16 | S3 | Fri 04/12/20 | Sat 12/12/20 | 100% | SP-201019 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | 33.535; 33.501; 33.220 ; 9/4/21: 0%->100 |  | 90 |  |  |  | Fri 04/12/20 | Fri 09/04/21
1054 | 0 | NR-related Release 16 Features | - | 1 | Rel-16 |  | Thu 07/03/19 | Thu 07/03/19 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1055 | 860058 | Addition of wider channel bandwidth in NR band n3 | NR_n3_BW | 1 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200305 |  | Ericsson |  | affects: NR.; 26/3/20: WID:RP-193056->RP-200305 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 26/03/20
1056 | 860158 | Core part: Addition of wider channel bandwidth in NR band n3 | NR_n3_BW-Core | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200305 |  | Ericsson |  | affects: NR.; 28/7/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1057 | 860258 | Perf. part: Addition of wider channel bandwidth in NR band n3 | NR_n3_BW-Perf | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200305 |  | Ericsson |  | affects: NR.; 28/7/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1058 | 860059 | Addition of wider channel bandwidth in NR band n65 | NR_n65_BW | 1 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200306 |  | Ericsson |  | affects: NR.; 26/3/20: WID:RP-193057->RP-200306 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 26/03/20
1059 | 860159 | Core part: Addition of wider channel bandwidth in NR band n65 | NR_n65_BW-Core | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200306 |  | Ericsson |  | affects: NR.; 28/7/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1060 | 860259 | Perf. part: Addition of wider channel bandwidth in NR band n65 | NR_n65_BW-Perf | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200306 |  | Ericsson |  | affects: NR.; 28/7/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1061 | 830075 | UE Power Saving in NR | NR_UE_pow_sav | 1 | Rel-16 | R1 | Fri 15/06/18 | Tue 15/09/20 | 100% | RP-200494 |  | CATT |  | 26/6/19: WID:RP-190727->RP-191607; 30/6/20: WID:RP-191607->RP-200494 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 30/06/20
1062 | 800094 | Study on UE power saving in NR | FS_NR_UE_pow_sav | 2 | Rel-16 | R1 | Fri 15/06/18 | Sat 15/06/19 | 100% | RP-181463 |  | CATT |  | TR 38.8xx; 26/6/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 26/06/19
1063 | 830175 | Core part: UE Power Saving in NR | NR_UE_pow_sav-Core | 2 | Rel-16 | R1 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200494 |  | CATT |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1064 | 830275 | Perf. part: UE Power Saving in NR | NR_UE_pow_sav-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Tue 15/09/20 | 100% | RP-200494 |  | CATT |  | 7/4/21: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 07/04/21
1065 | 800072 | Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16 | 1 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201018 |  | Huawei |  | basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 26/6/19: WID:RP-1907... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1066 | 800172 | Core part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16-Core | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201018 |  | Huawei |  | basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1067 | 800272 | Perf. part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201018 |  | Huawei |  | basket WI¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1068 | 800057 | NR intra-band Carrier Aggregation |  | 1 | Rel-16 |  | Fri 15/06/18 | Sun 15/12/19 | 100% | [6 empty] | 80 | 41 |  |  | Wed 27/06/18 | NA
1069 | 800073 | Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200656 |  | Ericsson |  | basket WI¦TR 38.716-01-01¦16/1/19: WID:RP-181426->RP-182256¦26/3/19: WID:RP-182256->RP-190689; 26/6/19: WID:RP-190689->RP-191194; 8/10/19: WID:RP-191194->RP-191812; 14/1/20: WID:RP-191812->RP-192445; 26/3/20: WID:RP-192445->RP-200101; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1070 | 800173 | Core part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200656 |  | Ericsson |  | basket WI¦TR 38.716-01-01¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1071 | 800273 | Perf. part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200656 |  | Ericsson |  | basket WI¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1072 | 800074 | Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201253 |  | ZTE |  | basket WI¦TR 38.716-02-00¦16/1/19: WID:RP-180817->RP-182501¦26/3/19: WID:RP-182501->RP-190494; 26/6/19: WID:RP-190494->RP-191565; 8/10/19: WID:RP-191565->RP-191822; 14/1/20: WID:RP-191822->RP-192615; 26/3/20: WID:RP-192615->RP-200168; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1073 | 800174 | Core part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201253 |  | ZTE |  | basket WI¦TR 38.716-02-00¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1074 | 800274 | Perf. part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201253 |  | ZTE |  | basket WI¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1075 | 830099 | NR inter-band Carrier Aggregation |  | 1 | Rel-16 |  | Fri 01/03/19 | Fri 11/06/21 | 66% | [6 empty] | 83 | 42 |  |  | Tue 26/03/19 | NA
1076 | 830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | NR_CADC_NR_LTE_DC_R16-UEConTest | 2 | Rel-16 | R5 | Fri 01/03/19 | Fri 11/06/21 | 6% | RP-200759 |  | CMCC |  | 8/10/19: WID:RP-190321->RP-191772; 28/7/20: WID:RP-191772->RP-200759; 8/10/20: 0%->6; 8/10/20: FCD:01/06/2020->06/21; 8/4/21: 6%->6 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 08/04/21
1077 | 830095 | Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200918 |  | CATT |  | 26/6/19: WID:RP-190692->RP-191153; 8/10/19: WID:RP-191153->RP-192245; 14/1/20: WID:RP-192245->RP-193206; 26/3/20: WID:RP-193206->RP-200238; 28/7/20: WID:RP-200238->RP-200918 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1078 | 830195 | Core part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200918 |  | CATT |  | 26/6/19: 38.716-03-01 added;; 28/7/20: 0%->100 | 38.716-03-01 | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1079 | 830295 | Perf. part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200918 |  | CATT |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1080 | 830096 | Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200673 |  | ZTE |  | 26/6/19: WID:RP-190693->RP-191566; 8/10/19: WID:RP-191566->RP-191824; 14/1/20: WID:RP-191824->RP-192617; 26/3/20: WID:RP-192617->RP-200171; 28/7/20: WID:RP-200171->RP-200673 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1081 | 830196 | Core part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200673 |  | ZTE |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1082 | 830296 | Perf. part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200673 |  | ZTE |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1083 | 831000 | New bands for New Radio |  | 1 | Rel-16 | R4 | Fri 15/06/18 | Fri 11/06/21 | 95% | RP-182258 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258 |  | 83 | 42 |  |  | Wed 27/06/18 | Wed 16/01/19
1084 | 850062 | UE Conformance Test Aspects for new Rel-16 NR bands and extension of existing NR bands | NR_bands_BW_R16-UEConTest | 2 | Rel-16 | R5 | Thu 19/09/19 | Fri 11/06/21 | 67% | RP-200633 |  | Ericsson |  | testing all new NR band(s) and NR channel bandwidth addition Wis of REL-16; 14/1/20: WID:RP-192128->RP-192893; 26/3/20: WID:RP-192893->RP-200146; 28/7/20: WID:RP-200146->RP-200633; 8/10/20: 0%->47; 8/10/20: FCD:15/06/2020->12/20; 8/4/21: 47%->67; 8/4/2... |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 08/04/21
1085 | 800077 | Band 65 for New Radio | NR_band_n65 | 2 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/12/18 | 100% | RP-190360 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258¦26/3/19: WID:RP-182258->RP-190360 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
1086 | 800177 | Core part: Band 65 for New Radio | NR_band_n65-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/12/18 | 100% | RP-190360 |  | Dish Network |  | 26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 26/06/19
1087 | 800277 | Perf. part: Band 65 for New Radio | NR_band_n65-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/12/18 | 100% | RP-190360 |  | Dish Network |  | 26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 26/06/19
1088 | 820073 | Introduction of NR band n18 | NR_n18 | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-191556 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173; 26/6/19: WID:RP-190173->RP-191556 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1089 | 820173 | Core part: Introduction of NR band n18 | NR_n18-Core | 3 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-190173 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1090 | 820273 | Perf. part: Introduction of NR band n18 | NR_n18-Perf | 3 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-190173 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1091 | 820077 | Introduction of NR band n48 | NR_n48 | 2 | Rel-16 | R4 | Thu 13/12/18 | Sat 01/06/19 | 100% | RP-190908 |  | US Cellular |  | 26/6/19: WID:RP-182865->RP-190908 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1092 | 820177 | Core part: Introduction of NR band n48 | NR_n48-Core | 3 | Rel-16 | R4 | Thu 13/12/18 | Mon 18/03/19 | 100% | RP-182865 |  | US Cellular |  | 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1093 | 830271 | Perf. part: Introduction of NR band n48 | NR_n48-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190140 |  | Nokia |  | 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1094 | 830090 | Introduction of NR band n14 | NR_n14 | 2 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190965 |  | AT&T |  | 26/6/19: WID:RP-190165->RP-190965 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1095 | 830190 | Core part: Introduction of NR band n14 | NR_n14-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190165 |  | AT&T |  | 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1096 | 830290 | Perf. part: Introduction of NR band n14 | NR_n14-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190165 |  | AT&T |  | 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1097 | 830091 | Introduction of NR band n30 | NR_n30 | 2 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190967 |  | AT&T |  | 26/6/19: WID:RP-190166->RP-190967 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1098 | 830191 | Core part: Introduction of NR band n30 | NR_n30-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190166 |  | AT&T |  | 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1099 | 830291 | Perf. part: Introduction of NR band n30 | NR_n30-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190166 |  | AT&T |  | 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1100 | 830097 | Introduction of NR band n259 | NR_n259 | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-200249 |  | Ericsson |  | 26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
1101 | 830197 | Core part: Introduction of NR band n259 | NR_n259-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191880 |  | Ericsson |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1102 | 830297 | Perf. part: Introduction of NR band n259 | NR_n259-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191880 |  | Ericsson |  | 28/7/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1103 | 850067 | Introduction of NR band n26 | NR_n26 | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192736 |  | Sprint |  | UL: 814-849MHz, DL: 859-894MHz; 14/1/20: WID:RP-192273->RP-192736 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1104 | 850167 | Core part: Introduction of NR band n26 | NR_n26-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192736 |  | Sprint |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1105 | 850267 | Perf. part: Introduction of NR band n26 | NR_n26-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192736 |  | Sprint |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1106 | 840097 | Introduction of NR supplementary DL band n29 | NR_n29 | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/09/19 | 100% | RP-192236 |  | Dish Network |  | 8/10/19: WID:RP-191474->RP-192236 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 08/10/19
1107 | 840197 | Core part: Introduction of NR supplementary DL band n29 | NR_n29-Core | 3 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/09/19 | 100% | RP-192236 |  | Dish Network |  | 8/10/19: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 08/10/19
1108 | 840297 | Perf. part: Introduction of NR supplementary DL band n29 | NR_n29-Perf | 3 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/09/19 | 100% | RP-192236 |  | Dish Network |  | 8/10/19: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 08/10/19
1109 | 850068 | Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR | NR_SUL_band_2010_2025MHz | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192584 |  | CMCC |  | 14/1/20: WID:RP-192274->RP-192584 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1110 | 850168 | Core part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR | NR_SUL_band_2010_2025MHz-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192584 |  | CMCC |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1111 | 850268 | Perf. part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR | NR_SUL_band_2010_2025MHz-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192584 |  | CMCC |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1112 | 860056 | Introduction of band n53 | NR_n53 | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-192409 |  | Globalstar |  | affects: NR. |  | 86 | 44 |  |  | Tue 18/02/20 | NA
1113 | 860156 | Core part: Introduction of band n53 | NR_n53-Core | 3 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-192409 |  | Globalstar |  | affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 26/03/20
1114 | 860256 | Perf. part: Introduction of band n53 | NR_n53-Perf | 3 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-192409 |  | Globalstar |  | affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 26/03/20
1115 | 831001 | New Radio Band-related topics |  | 1 | Rel-16 | R4 | Thu 13/12/18 | Sun 12/06/22 | 84% | RP-182258 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258 |  | 83 | 42 |  |  | Wed 27/06/18 | Wed 16/01/19
1116 | 830087 | RF requirements for NR frequency range 1 (FR1) | NR_RF_FR1 | 2 | Rel-16 | R4 | Fri 01/03/19 | Wed 15/12/21 | 75% | RP-193266 |  | Huawei |  | 26/6/19: WID:RP-190759->RP-191114; 8/10/19: WID:RP-191114->RP-192282; 14/1/20: WID:RP-192282->RP-193266 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
1117 | 830187 | Core part: RF requirements for NR FR1 | NR_RF_FR1-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-193266 |  | Huawei |  | 25/9/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Fri 25/09/20
1118 | 830287 | Perf. Part: RF requirements for NR FR1 | NR_RF_FR1-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Mon 01/06/20 | 100% | RP-193266 |  | Huawei |  | 6/1/21: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 06/01/21
1119 | 870061 | UE Conformance Test Aspects - RF requirements for NR FR1 | NR_RF_FR1-UEConTest | 3 | Rel-16 | R5 | Wed 25/03/20 | Wed 15/12/21 | 43% | RP-200094 |  | Huawei |  | affects: NR. TR 38.8xx; 8/10/20: 0%->15; 8/4/21: 15%->43 |  | 87 | 44 |  |  | Tue 14/01/20 | Thu 08/04/21
1120 | 830088 | Add support of NR DL 256QAM for frequency range 2 (FR2) | NR_DL256QAM_FR2 | 2 | Rel-16 | R4 | Fri 01/03/19 | Fri 10/06/22 | 70% | RP-200124 |  | China Telecom |  | 26/6/19: WID:RP-190760->RP-190925; 8/10/19: WID:RP-190925->RP-191891; 26/3/20: WID:RP-191891->RP-200124 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
1121 | 830188 | Core part: Add support of NR DL 256QAM for FR2 | NR_DL256QAM_FR2-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200124 |  | China Telecom |  | 8/10/19: 38.883 added;; 28/7/20: 0%->100 | 38.883 | 83 | 42 |  |  | Tue 26/03/19 | Tue 28/07/20
1122 | 830288 | Perf. part: Add support of NR DL 256QAM for FR2 | NR_DL256QAM_FR2-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Tue 15/09/20 | 100% | RP-200124 |  | China Telecom |  | 7/4/21: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 07/04/21
1123 | 900051 | UE Conformance Test Aspects - Add support of NR DL 256QAM for FR2 | NR_DL256QAM_FR2-UEConTest | 3 | Rel-16 | R5 | Mon 14/12/20 | Fri 10/06/22 | 20% | RP-202371 |  | China Telecom |  | tested: REL-16 WI NR_DL256QAM_FR2-Core ; 8/4/21: 0%->20 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
1124 | 830089 | NR RF requirement enhancements for frequency range 2 (FR2) | NR_RF_FR2_req_enh | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 12/06/22 | 54% | RP-201606 |  | Nokia |  | 26/6/19: WID:RP-190761->RP-191290; 8/10/19: WID:RP-191290->RP-192227; 14/1/20: WID:RP-192227->RP-192653; 26/3/20: WID:RP-192653->RP-200246; 28/7/20: WID:RP-200246->RP-200668; 25/9/20: WID:RP-200668->RP-201606 |  | 83 | 42 |  |  | Tue 26/03/19 | Fri 25/09/20
1125 | 830189 | Core part: NR RF requirement enhancements for FR2 | NR_RF_FR2_req_enh-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 01/03/20 | 100% | RP-200668 |  | Nokia |  | 8/10/19: 38.831 added;; 25/9/20: 0%->100 | 38.831 | 83 | 42 |  |  | Tue 26/03/19 | Fri 25/09/20
1126 | 850073 | Perf. part: NR RF requirement enhancements for FR2 | NR_RF_FR2_req_enh-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-200668 |  | Nokia |  | 25/9/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Fri 25/09/20
1127 | 910098 | UE Conformance Test Aspects - NR RF requirement enhancements for frequency range 2 (FR2) | NR_RF_FR2_req_enh-UEConTest | 3 | Rel-16 | R5 | Fri 12/03/21 | Sun 12/06/22 | 0% | RP-210363 |  | Nokia |  | tested: REL-16 WI NR_RF_FR2_req_enh-Core | [5 empty] | Wed 07/04/21 | NA
1128 | 830092 | Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5 | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-192080 |  | Huawei |  | 26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1129 | 830192 | Core part: Introduction of an NR SUL band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-192080 |  | Huawei |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1130 | 830292 | Perf. part: Introduction of an NR SUL band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-192080 |  | Huawei |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1131 | 820074 | Adding wider channel bandwidths in NR band n7 | NR_n7_BW | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/09/19 | 100% | RP-190137 |  | BT |  | no Perf. part¦26/3/19: WID:RP-182827->RP-190137 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 26/03/19
1132 | 820174 | Core part: Adding wider channel bandwidths in NR band n7 | NR_n7_BW-Core | 3 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/09/19 | 100% | RP-190137 |  | BT |  | no Perf. part¦26/3/19: WID:RP-182827->RP-190137; 8/10/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 08/10/19
1133 | 830093 | Addition of wider channel bandwidth in NR band n38 | NR_n38_BW | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191472 |  | Huawei |  | 26/6/19: WID:RP-190392->RP-191472; 14/1/20: WID:RP-191472->RP-192513; 13/6/21: WID:RP-192513->RP-191472 |  | 83 | 42 |  |  | Tue 26/03/19 | Sun 13/06/21
1134 | 830193 | Core part: Addition of wider channel bandwidth in NR band n38 | NR_n38_BW-Core | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191472 |  | Huawei |  | 14/1/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
1135 | 830293 | Perf. part: Addition of wider channel bandwidth in NR band n38 | NR_n38_BW-Perf | 3 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191472 |  | Huawei |  | 14/1/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
1136 | 850063 | Addition of further channel bandwidths in NR band 38 | NR_n38_BW2 | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192513 |  | Ericsson |  | 13/6/21: WID:RP-192215->RP-192513 |  | 85 | 43 |  |  | Tue 08/10/19 | Sun 13/06/21
1137 | 850163 | Core part: Addition of further channel bandwidths in NR band 38 | NR_n38_BW2-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192513 |  | Ericsson |  | compare REL-16 WI NR_n38_BW; 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1138 | 850263 | Perf. part: Addition of further channel bandwidths in NR band 38 | NR_n38_BW2-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192513 |  | Ericsson |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1139 | 820075 | Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW | 2 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-191681 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174; 26/6/19: WID:RP-190174->RP-191569; 8/10/19: WID:RP-191569->RP-191681 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 08/10/19
1140 | 820175 | Core part: Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW-Core | 3 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-191681 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174; 8/10/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 08/10/19
1141 | 820275 | Stopped - Perf. part: Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW-Perf | 3 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-191681 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174. 08/10/2019: stopped at 0%; 8/10/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 08/10/19
1142 | 820076 | Adding wider channel bandwidths in NR band n50 | NR_n50_BW | 2 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-182829 |  | Huawei |  | no Perf. part |  | 82 | 42 |  |  | Wed 16/01/19 | NA
1143 | 820176 | Core part: Adding wider channel bandwidths in NR band n50 | NR_n50_BW-Core | 3 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-182829 |  | Huawei |  | no Perf. part; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1144 | 850064 | Addition of wider channel bandwidths in NR band n75 | NR_n75_BW | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192216 |  | Ericsson |  |  |  | 85 | 43 |  |  | Tue 08/10/19 | NA
1145 | 850164 | Core part: Addition of wider channel bandwidths in NR band n75 | NR_n75_BW-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192216 |  | Ericsson |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1146 | 850264 | Perf. part: Addition of wider channel bandwidths in NR band n75 | NR_n75_BW-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192216 |  | Ericsson |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1147 | 850065 | Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25 | NR_n25_BW | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192401 |  | Nokia |  | 14/1/20: WID:RP-192219->RP-192401 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1148 | 850165 | Core part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25 | NR_n25_BW-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192401 |  | Nokia |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1149 | 850265 | Perf. part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25 | NR_n25_BW-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192401 |  | Nokia |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1150 | 850066 | Addition of wider channel bandwidths in NR band n28 | NR_n28_BW | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192656 |  | CBN |  | 14/1/20: WID:RP-192261->RP-192656 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1151 | 850166 | Core part: Addition of wider channel bandwidths in NR band n28 | NR_n28_BW-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192656 |  | CBN |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1152 | 850266 | Perf. part: Addition of wider channel bandwidths in NR band n28 | NR_n28_BW-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192656 |  | CBN |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1153 | 850069 | Addition of new channel bandwidth in NR band n1 | NR_n1_BW2 | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192801 |  | China Unicom |  | 8/10/19: WID:RP-192275->RP-192009. compare REL-16 WI NR_n1_BW; 14/1/20: WID:RP-192275->RP-192801 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1154 | 850169 | Core part: Addition of new channel bandwidth in NR band n1 | NR_n1_BW2-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192801 |  | China Unicom |  | 28/7/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 28/07/20
1155 | 850269 | Perf. part: Addition of new channel bandwidth in NR band n1 | NR_n1_BW2-Perf | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192801 |  | China Unicom |  | 28/7/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 28/07/20
1156 | 850070 | Addition of asymmetric channel bandwidth for NR band n66 | NR_n66_BW | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-200265 |  | Huawei |  | no Perf. Part; 14/1/20: WID:RP-192276->RP-192808; 26/3/20: WID:RP-192808->RP-200265 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1157 | 850170 | Core part: Addition of asymmetric channel bandwidth for NR band n66 | NR_n66_BW-Core | 3 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-201010 |  | Huawei |  | 28/7/20: WID:RP-200265->RP-201010; 28/7/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 28/07/20
1158 | 800085 | Enhancements on MIMO for NR | NR_eMIMO | 1 | Rel-16 | R1 | Fri 15/06/18 | Wed 15/12/21 | 76% | RP-200474 |  | Samsung |  | 16/1/19: WID:RP-181453->RP-182863; 8/10/19: WID:RP-182863->RP-192271; 26/3/20: WID:RP-192271->RP-200474 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
1159 | 800185 | Core part: Enhancements on MIMO for NR | NR_eMIMO-Core | 2 | Rel-16 | R1 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200474 |  | Samsung |  | 25/9/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Fri 25/09/20
1160 | 800285 | Perf. part: Enhancements on MIMO for NR | NR_eMIMO-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Tue 15/09/20 | 100% | RP-200474 |  | Samsung |  | 7/4/21: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 07/04/21
1161 | 880070 | UE Conformance Test Aspects - Enhancements on MIMO for NR | NR_eMIMO-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 16% | RP-200895 |  | Huawei |  | 8/10/20: 0%->1; 8/4/21: 1%->16 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
1162 | 800087 | NR mobility enhancements | NR_Mob_enh | 1 | Rel-16 | R2 | Fri 15/06/18 | Wed 15/12/21 | 78% | RP-192534 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489; 8/10/19: WID:RP-190489->RP-192277; 14/1/20: WID:RP-192277->RP-192534 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1163 | 800187 | Core part: NR mobility enhancements | NR_Mob_enh-Core | 2 | Rel-16 | R2 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192534 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1164 | 800287 | Perf. part: NR mobility enhancements | NR_Mob_enh-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192534 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489; 6/1/21: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 06/01/21
1165 | 880068 | UE Conformance Test Aspects - NR Mobility Enhancements | NR_Mob_enh-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 35% | RP-200893 |  | Huawei |  | 8/10/20: 0%->5; 8/4/21: 5%->35 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
1166 | 820068 | 2-step RACH for NR | NR_2step_RACH | 1 | Rel-16 | R1 | Sat 15/12/18 | Sun 15/12/19 | 60% | RP-200085 |  | ZTE |  | WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 8/10/19: WID:RP-190711->RP-192330; 26/3/20: WID:RP-192330->RP-200085 |  | 82 | 42 |  |  | Wed 16/01/19 | Thu 26/03/20
1167 | 820168 | Core part: 2-step RACH for NR | NR_2step_RACH-Core | 2 | Rel-16 | R1 | Sat 15/12/18 | Sun 15/12/19 | 100% | RP-200085 |  | ZTE |  | WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 28/7/20: 0%->100; 28/7/20: 100%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 28/07/20
1168 | 820268 | Perf. part: 2-step RACH for NR | NR_2step_RACH-Perf | 2 | Rel-16 | R4 | Sat 15/12/18 | Thu 20/06/19 | 100% | RP-200085 |  | ZTE |  | 26/3/19: WID:RP-182894->RP-190711; 6/1/21: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 06/01/21
1169 | 911001 | UE Conformance Test Aspects - 2-step RACH for NR | NR_2step_RACH-UEConTest | 2 | Rel-16 | R5 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210612 |  | ZTE |  | tested REL-16 WI NR_2step_RACH-Core | [5 empty] | Wed 07/04/21 | NA
1170 | 840091 | SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR | NR_SON_MDT | 1 | Rel-16 | R3 | Mon 17/06/19 | Fri 17/12/21 | 61% | RP-191594 |  | CMCC |  | no Perf. part; impact on SA2, SA5, CT4?; TR 38.314 |  | 84 | 43 |  |  | Wed 26/06/19 | NA
1171 | 840191 | Core part: SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR | NR_SON_MDT-Core | 2 | Rel-16 | R3 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-192610 |  | CMCC |  | no Perf. part; impact on SA2, SA5, CT4?; TR 38.314; 8/10/19: WID:RP-191594->RP-191776; 8/10/19: 38.314 added;; 14/1/20: WID:RP-191776->RP-192610; 28/7/20: 0%->100 | 38.314 | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1172 | 890043 | UE Conformance Test Aspects - SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR | NR_SON_MDT-UEConTest | 2 | Rel-16 | R5 | Thu 17/09/20 | Fri 17/12/21 | 37% | RP-210377 |  | CMCC |  | tested: REL-16 WI NR_SON_MDT-Core ; 7/4/21: WID:RP-201625->RP-210377; 8/4/21: 0%->37 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1173 | 810030 | Study on Self-Organizing Networks (SON) for 5G | FS_SON_5G | 1 | Rel-16 | S5 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180827 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 7/12/18: 0%->10¦14/3/19: 10%->40; 31/5/19: 40%->50; 6/12/19: 50%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 06/12/19
1174 | 850030 | Self-Organizing Networks (SON) for 5G networks | SON_5G | 1 | Rel-16 | S5 | Thu 19/09/19 | Mon 14/09/20 | 100% | SP-200763 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | ; 13/9/19: 0%->80; 8/10/19: 28.544 added;; 8/10/19: 28.313 added;; 28/6/20: 80%->75; 13/9/20: 75%->100; 13/9/20: WID:SP-190785->SP-200763; 13/9/20: FCD:12/03/2020->09/20 | 28.552; 28.545 ; 28.544; 28.313 | 85 | 43 |  |  | Fri 13/09/19 | Sun 13/09/20
1175 | 840093 | RRM requirement for CSI-RS based L3 measurement in NR | NR_CSIRS_L3meas | 1 | Rel-16 | R4 | Mon 17/06/19 | Tue 15/09/20 | 37% | RP-210590 |  | CATT |  | 8/10/19: WID:RP-191580->RP-191992; 26/3/20: WID:RP-191992->RP-200240; 28/7/20: WID:RP-200240->RP-201345; 25/9/20: WID:RP-201345->RP-201975; 6/1/21: WID:RP-201975->RP-202723; 7/4/21: WID:RP-202723->RP-210590 |  | 84 | 43 |  |  | Wed 26/06/19 | Wed 07/04/21
1176 | 840193 | Core part: RRM requirement for CSI-RS based L3 measurement in NR | NR_CSIRS_L3meas-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-210590 |  | CATT |  | 25/9/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Fri 25/09/20
1177 | 840293 | Perf. part: RRM requirement for CSI-RS based L3 measurement in NR | NR_CSIRS_L3meas-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Tue 15/09/20 | 0% | RP-210590 |  | CATT |  |  |  | 84 | 43 |  |  | Wed 26/06/19 | NA
1178 | 840094 | NR performance requirement enhancement | NR_perf_enh | 1 | Rel-16 | R4 | Mon 17/06/19 | Wed 08/09/21 | 32% | RP-200472 |  | China Telecom |  | no Core part; 8/10/19: WID:RP-191587->RP-192281; 14/1/20: WID:RP-192281->RP-192532; 26/3/20: WID:RP-192532->RP-200472 |  | 84 | 43 |  |  | Wed 26/06/19 | Thu 26/03/20
1179 | 840294 | Perf. part: NR performance requirement enhancement | NR_perf_enh-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/09/19 | 100% | RP-200472 |  | China Telecom |  | no Core part; 7/4/21: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Wed 07/04/21
1180 | 890048 | UE Conformance Test Aspects - NR performance requirement enhancement | NR_perf_enh-UEConTest | 2 | Rel-16 | R5 | Thu 17/09/20 | Wed 08/09/21 | 15% | RP-202557 |  | Qualcomm -> China Telecom |  | tested: REL-16 WI NR_perf_enh-Perf ; 6/1/21: WID:RP-201941->RP-202557; Qualcomm -> China Telecom; 8/4/21: 0%->15 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1181 | 840095 | NR RRM enhancement | NR_RRM_enh | 1 | Rel-16 | R4 | Mon 17/06/19 | Mon 15/06/20 | 100% | RP-201883 |  | Intel |  | 8/10/19: WID:RP-191601->RP-192157; 14/1/20: WID:RP-192157->RP-193211; 26/3/20: WID:RP-193211->RP-200256; 28/7/20: WID:RP-200256->RP-201112; 25/9/20: WID:RP-201112->RP-201883 |  | 84 | 43 |  |  | Wed 26/06/19 | Fri 25/09/20
1182 | 840195 | Core part: NR RRM enhancement | NR_RRM_enh-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-201883 |  | Intel |  | 25/9/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Fri 25/09/20
1183 | 840295 | Perf. part: NR RRM enhancement | NR_RRM_enh-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Mon 15/06/20 | 100% | RP-202655 |  | Intel |  | 6/1/21: WID:RP-201883->RP-202655; 7/4/21: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Wed 07/04/21
1184 | 840096 | Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL | NR_CA_R16_4BDL_1BUL | 1 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-200658 |  | Ericsson |  | basket WI; TR 38.716-04-01; 8/10/19: WID:RP-191196->RP-191814; 14/1/20: WID:RP-191814->RP-192447; 26/3/20: WID:RP-192447->RP-200103; 28/7/20: WID:RP-200103->RP-200658 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1185 | 840196 | Core part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL | NR_CA_R16_4BDL_1BUL-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-200658 |  | Ericsson |  | basket WI; TR 38.716-04-01; 28/7/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1186 | 840296 | Perf. part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL | NR_CA_R16_4BDL_1BUL-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-200658 |  | Ericsson |  | basket WI; 28/7/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1187 | 840098 | Addition of wider channel bandwidth in NR band n1 | NR_n1_BW | 1 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-192009 |  | Ericsson |  | 8/10/19: WID:RP-191595->RP-192009 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 08/10/19
1188 | 840198 | Core part: Addition of wider channel bandwidth in NR band n1 | NR_n1_BW-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-192009 |  | Ericsson |  | 26/3/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Thu 26/03/20
1189 | 840298 | Perf. part: Addition of wider channel bandwidth in NR band n1 | NR_n1_BW-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-192009 |  | Ericsson |  | 26/3/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Thu 26/03/20
1190 | 840099 | Addition of channel bandwidths in Band n77 and n78 | NR_n77_n78_BW | 1 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/12/19 | 100% | RP-191606 |  | Huawei |  | no Perf. part |  | 84 | 43 |  |  | Wed 26/06/19 | NA
1191 | 840199 | Core part: Addition of channel bandwidths in Band n77 and n78 | NR_n77_n78_BW-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/12/19 | 100% | RP-192822 |  | Huawei |  | no Perf. part; 8/10/19: WID:RP-191606->RP-192349; 14/1/20: WID:RP-192349->RP-192822; 26/3/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Thu 26/03/20
1192 | 841000 | Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL | DC_R16_LTE_NR_3DL3UL | 1 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-201254 |  | ZTE |  | max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1193 | 841100 | Core part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL | DC_R16_LTE_NR_3DL3UL-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-201254 |  | ZTE |  | max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 28/7/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1194 | 841200 | Perf. part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL | DC_R16_LTE_NR_3DL3UL-Perf | 2 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/03/20 | 100% | RP-201254 |  | ZTE |  | max. 2 NR bands for DL and UL; min. 1 NR FR2 band; 28/7/20: 0%->100 |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 28/07/20
1195 | 841001 | Introduction of NR FDD bands with variable duplex and corresponding framework | NR_FDD_bands_varduplex | 1 | Rel-16 | R4 | Mon 17/06/19 | Sun 15/12/19 | 100% | RP-192820 |  | Huawei |  | no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/... |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 14/01/20
1196 | 841101 | Core part: Introduction of NR FDD bands with variable duplex and corresponding framework | NR_FDD_bands_varduplex-Core | 2 | Rel-16 | R4 | Mon 17/06/19 | Fri 13/12/19 | 100% | RP-192820 |  | Huawei |  | no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/... |  | 84 | 43 |  |  | Wed 26/06/19 | Tue 14/01/20
1197 | 850074 | Perf. part: Introduction of NR FDD bands with variable duplex and corresponding framework | NR_FDD_bands_varduplex-Perf | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/12/19 | 100% | RP-192820 |  | Huawei |  | 14/1/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1198 | 841002 | Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | DC_Pcmax_3UL_CC | 1 | Rel-16 | R4 | Wed 31/07/19 | Thu 12/03/20 | 0% | RP-191604 |  | Huawei |  | no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI |  | 84 | 43 |  |  | Wed 31/07/19 | NA
1199 | 841102 | Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1) | DC_Pcmax_3UL_CC-Core | 2 | Rel-16 | R4 | Wed 31/07/19 | Thu 12/03/20 | 0% | RP-192093 |  | Huawei |  | no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093 |  | 84 | 43 |  |  | Wed 31/07/19 | Tue 08/10/19
1200 | 880074 | Addition of NR UE measurements to enable OTA conformance testing | NR_OTA_Uemeas | 1 | Rel-16 | R1 | Mon 22/06/20 | Tue 28/07/20 | 100% | RP-200824 |  | Keysight Technologies |  |  |  | 88 | 45 |  |  | Tue 28/07/20 | NA
1201 | 880174 | Core part: Addition of NR UE measurements to enable OTA conformance testing | NR_OTA_Uemeas-Core | 2 | Rel-16 | R1 | Mon 22/06/20 | Tue 28/07/20 | 100% | RP-200824 |  | Keysight Technologies |  | 28/7/20: 0%->100; 28/7/20: 0%->100 |  | 88 | 45 |  |  | Tue 28/07/20 | Tue 28/07/20
1202 | 0 | Release 16 Features impacting both LTE and NR | - | 1 | Rel-16 |  | Thu 07/03/19 | Thu 07/03/19 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1203 | 860054 | Over the air (OTA) base station (BS) testing TR | OTA_BS_testing | 1 | Rel-16 | R4 | Thu 07/03/19 | Wed 05/06/19 | 100% | RP-193225 |  | Huawei |  | affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16 |  | 86 | 44 |  |  | Tue 18/02/20 | NA
1204 | 860254 | Perf. Part: Over the air (OTA) base station (BS) testing TR | OTA_BS_testing-Perf | 2 | Rel-16 | R4 | Thu 07/03/19 | Wed 05/06/19 | 100% | RP-201021 |  | Huawei |  | affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16; 26/3/20: WID:RP-193225->RP-200276; 28/7/20: WID:RP-200276->RP-201021; 25/9/20: 37.941 added;; 6/1/21: 0%->100 | 37.941 | 86 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
1205 | 860055 | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | ENDC_UE_PC2_FDD_TDD | 1 | Rel-16 | R4 | Mon 16/12/19 | Fri 17/12/21 | 82% | RP-193244 |  | China Unicom |  | affects: LTE, NR. no Perf. part |  | 86 | 44 |  |  | Tue 18/02/20 | NA
1206 | 860155 | Core part: High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | ENDC_UE_PC2_FDD_TDD-Core | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-201578 |  | China Unicom |  | affects: LTE, NR. no Perf. part; 25/9/20: WID:RP-193244->RP-201578; 25/9/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
1207 | 890044 | UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | ENDC_UE_PC2_FDD_TDD-UEConTest | 2 | Rel-16 | R5 | Thu 17/09/20 | Fri 17/12/21 | 78% | RP-201776 |  | China Unicom |  | tested: REL-16 WI ENDC_UE_PC2_FDD_TDD-Core ; 8/4/21: 0%->78 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1208 | 860057 | Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | DC_R16_xBLTE_2BNR_yDL3UL | 1 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200905 |  | NTT DOCOMO |  | affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 26/3/20: WID:RP-192784->RP-200228; 28/7/20: WID:RP-200228->RP-200905 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1209 | 860157 | Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | DC_R16_xBLTE_2BNR_yDL3UL-Core | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200905 |  | NTT DOCOMO |  | affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 28/7/20: 0%->100; 25/9/20: 37.716-41-22 added; | 37.716-41-22 | 86 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
1210 | 860257 | Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | DC_R16_xBLTE_2BNR_yDL3UL-Perf | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-200905 |  | NTT DOCOMO |  | affects: LTE, NR.; 28/7/20: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Tue 28/07/20
1211 | 860060 | LTE/NR spectrum sharing in band 48/n48 frequency range | NR_n48_LTE_48_coex | 1 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-201858 |  | Apple |  | affects: LTE, NR. no Perf. part; 26/3/20: WID:RP-193213->RP-200234; 28/7/20: WID:RP-200234->RP-201359; 25/9/20: WID:RP-201359->RP-201858 |  | 86 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
1212 | 860160 | Core part: LTE/NR spectrum sharing in band 48/n48 frequency range | NR_n48_LTE_48_coex-Core | 2 | Rel-16 | R4 | Mon 16/12/19 | Sun 15/03/20 | 100% | RP-201858 |  | Apple |  | affects: LTE, NR. no Perf. part; 6/1/21: 0%->100 |  | 86 | 44 |  |  | Tue 14/01/20 | Wed 06/01/21
1213 | 800088 | LTE-NR & NR-NR Dual Connectivity and NR Carrier Aggregation enhancements | LTE_NR_DC_CA_enh | 1 | Rel-16 | R2 | Fri 15/06/18 | Sat 12/03/22 | 33% | RP-200791 |  | Ericsson |  | RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 26/6/19: WID:RP-190452->RP-191600; 8/10/19: WID:RP-191600->RP-192336; 28/7/20: WID:RP-192336->RP-200791 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1214 | 800188 | Core part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | LTE_NR_DC_CA_enh-Core | 2 | Rel-16 | R2 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200791 |  | Ericsson |  | RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 25/9/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Fri 25/09/20
1215 | 800288 | Perf. part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | LTE_NR_DC_CA_enh-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Mon 15/06/20 | 0% | RP-200791 |  | Ericsson |  | 26/3/19: WID:RP-181469->RP-190452 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
1216 | 911004 | UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | LTE_NR_DC_CA_enh-UEConTest | 2 | Rel-16 | R5 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210746 |  | Nokia |  | lested: REL-16 WI LTE_NR_DC_CA_enh-Core | [5 empty] | Wed 07/04/21 | NA
1217 | 820079 | High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD | 1 | Rel-16 | R4 | Thu 13/12/18 | Wed 18/03/20 | 99% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 26/03/19
1218 | 820061 | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | FS_ENDC_UE_PC2_FDD_TDD | 2 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-192268 |  | China Unicom |  | EN-DC = E-UTRA-NR Dual Connectivity¦TR 37.8xx¦26/3/19: WID:RP-182895->RP-190167; 8/10/19: WID:RP-190167->RP-192268; 14/1/20: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 14/01/20
1219 | 820179 | Core part: High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD-Core | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 14/01/20
1220 | 820279 | Perf. part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD-Perf | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 14/01/20
1221 | 870062 | UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD-UEConTest | 2 | Rel-16 | R5 | Thu 07/03/19 | Wed 18/03/20 | 100% | RP-202066 |  | CMCC |  | affects: NR. TR 38.8xx; 28/7/20: WID:RP-200434->RP-200761; 25/9/20: WID:RP-200761->RP-202066; 25/9/20: 0%->100 |  | 87 | 44 |  |  | Tue 14/01/20 | Fri 25/09/20
1222 | 790054 | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | LTE_NR_arch_evo | 1 | Rel-16 | R3 | Thu 15/03/18 | Fri 13/12/19 | 100% | RP-192917 |  | China Unicom |  | follow-up WI of REL-15 SI FS_LTE_arch_evo; 14/1/20: WID:RP-180531->RP-192917 |  | 79 | 40 |  |  | Tue 27/03/18 | Tue 14/01/20
1223 | 790154 | Core part: eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | LTE_NR_arch_evo-Core | 2 | Rel-16 | R3 | Thu 15/03/18 | Fri 13/12/19 | 100% | RP-192917 |  | China Unicom |  | follow-up WI of REL-15 SI FS_LTE_arch_evo¦27/6/18: Compl:0%->15%¦27/6/18: CD:Fri 15/06/18->Sun 15/12/19¦27/6/18: WID: RP-180531->RP-181375¦27/6/18: Release: Rel-15->Rel-16¦6/8/18: 37.470 to 473 and 36.470 to 473 added;; 14/1/20: 15%->100 | 37.470; 37.471; 37.472; 37.473; 36.470; 36.471; 36.472; 36.473 | 79 | 40 |  |  | Tue 27/03/18 | Tue 14/01/20
1224 | 820080 | LTE/NR spectrum sharing in Band 41/n41 frequency range | NR_n41_LTE_41_coex | 1 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-191588 |  | KDDI |  | no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: WID:RP-190175->RP-191588 |  | 82 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1225 | 820180 | Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range | NR_n41_LTE_41_coex-Core | 2 | Rel-16 | R4 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-190175 |  | KDDI |  | no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1226 | 800078 | 29 dBm UE Power Class for LTE band 41 and NR Band n41 | LTE_NR_B41_Bn41_PC29dBm | 1 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/06/19 | 100% | RP-201134 |  | Sprint |  | no Perf. part¦26/3/19: WID:RP-181655->RP-190502; 14/1/20: WID:RP-190502->RP-192738; 28/7/20: WID:RP-192738->RP-201134 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1227 | 800178 | Core part: 29 dBm UE Power Class for LTE band 41 and NR Band n41 | LTE_NR_B41_Bn41_PC29dBm-Core | 2 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/06/19 | 100% | RP-201134 |  | Sprint |  | no Perf. part¦7/3/19: WID:RP-181460->RP-181655¦26/3/19: WID:RP-181655->RP-190502; 25/9/20: 0%->100; 25/9/20: 100%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Fri 25/09/20
1228 | 800058 | Dual Connectivity (EN-DC) |  | 1 | Rel-16 |  | Fri 15/06/18 | Sun 15/12/19 | 100% | [6 empty] | 80 | 41 |  |  | Wed 27/06/18 | NA
1229 | 800066 | Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200752 |  | NTT DOCOMO |  | basket WI¦TR 37.716-01-01¦16/1/19: WID:RP-181447->RP-182567¦26/3/19: WID:RP-182567->RP-190705; 26/6/19: WID:RP-190705->RP-191568; 8/10/19: WID:RP-191568->RP-191752; 14/1/20: WID:RP-191752->RP-192742; 26/3/20: WID:RP-192742->RP-200221; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1230 | 800166 | Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Fri 13/12/19 | 100% | RP-200752 |  | NTT DOCOMO |  | basket WI¦TR 37.716-01-01¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1231 | 800266 | Perf. part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200752 |  | NTT DOCOMO |  | basket WI¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1232 | 800067 | Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201278 |  | Huawei |  | basket WI¦TR 37.716-02-01¦16/1/19: WID:RP-181357->RP-182557¦26/3/19: WID:RP-182557->RP-190379; 26/6/19: WID:RP-190379->RP-191124; 8/10/19: WID:RP-191124->RP-192087; 14/1/20: WID:RP-192087->RP-192815; 26/3/20: WID:RP-192815->RP-200271; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1233 | 800167 | Core part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201278 |  | Huawei |  | basket WI¦TR 37.716-02-01¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1234 | 800267 | Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201278 |  | Huawei |  | basket WI¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1235 | 800068 | Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200657 |  | Ericsson |  | basket WI¦TR 37.716-03-01¦16/1/19: WID:RP-181407->RP-182257¦26/3/19: WID:RP-182257->RP-190159; 26/6/19: WID:RP-190159->RP-191195; 8/10/19: WID:RP-191195->RP-191813; 14/1/20: WID:RP-191813->RP-192446; 26/3/20: WID:RP-192446->RP-200102; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1236 | 800168 | Core part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200657 |  | Ericsson |  | basket WI¦TR 37.716-03-01¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1237 | 800268 | Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200657 |  | Ericsson |  | basket WI¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1238 | 800069 | Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200648 |  | Nokia |  | basket WI¦TR 37.716-04-01¦16/1/19: WID:RP-181001->RP-182534¦26/3/19: WID:RP-182534->RP-190294; 26/6/19: WID:RP-190294->RP-191205; 8/10/19: WID:RP-191205->RP-191728; 14/1/20: WID:RP-191728->RP-192768; 26/3/20: WID:RP-192768->RP-200134; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1239 | 800169 | Core part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200648 |  | Nokia |  | basket WI¦TR 37.716-04-01¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1240 | 800269 | Perf. part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200648 |  | Nokia |  | basket WI¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1241 | 800070 | Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-180997 |  | Samsung |  | basket WI¦TR 37.716-05-01 |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1242 | 800170 | Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-180997 |  | Samsung |  | basket WI¦TR 37.716-05-01; 14/1/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1243 | 800270 | Stopped: Perf. part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-180997 |  | Samsung |  | basket WI; 14/1/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1244 | 800071 | Dual Connectivity (EN-DC) of x bands (x=1, 2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200744 |  | LG Electronics |  | basket WI¦TR 37.716-00-02¦16/1/19: WID:RP-180777->RP-182302, "x=1" added¦26/3/19: WID:RP-182302->RP-190151; 26/6/19: WID:RP-190151->RP-190949; 8/10/19: WID:RP-190949->RP-191744; 14/1/20: WID:RP-191744->RP-192592; 26/3/20: WID:RP-192592->RP-200080; 28/7... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1245 | 800171 | Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200744 |  | LG Electronics |  | basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1246 | 800271 | Perf. part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200744 |  | LG Electronics |  | basket WI¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1247 | 0 | LTE-related Release 16 Features | - | 1 | Rel-16 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1248 | 790057 | E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US | 1 | Rel-16 | R4 | Thu 15/03/18 | Tue 18/06/19 | 100% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: WID:RP-180583->RP-182405 | 36.791 | 79 | 40 |  |  | Tue 27/03/18 | Wed 16/01/19
1249 | 790157 | Core part: E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US-Core | 2 | Rel-16 | R4 | Thu 15/03/18 | Sat 15/12/18 | 100% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: 0%->100 | 36.791 | 79 | 40 |  |  | Tue 27/03/18 | Wed 16/01/19
1250 | 790257 | Perf. part: E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US-Perf | 2 | Rel-16 | R4 | Thu 15/03/18 | Sat 15/12/18 | 100% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦16/1/19: 0%->100 |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 16/01/19
1251 | 820063 | UE Conformance Test Aspects - E-UTRA 2.4 GHz TDD Band for US (Band 53) | LTE_TDD_2400_US-UEConTest | 2 | Rel-15 | R5 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-182406 |  | Globalstar |  | tested: REL-15 WI LTE_TDD_2400_US-Core; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1252 | 800059 | LTE intra-band Carrier Aggregation (CA) |  | 1 | Rel-16 |  | Fri 15/06/18 | Wed 08/09/21 | 87% | [6 empty] | 80 | 41 |  |  | Wed 27/06/18 | NA
1253 | 800060 | Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200655 |  | Ericsson |  | basket WI¦TR 36.716-01-01¦16/1/19: WID:RP-180806->SP-182255¦26/3/19: WID:RP-182255->RP-190157; 26/6/19: WID:RP-190157->RP-191193; 8/10/19: WID:RP-191193->RP-191811; 14/1/20: WID:RP-191811->RP-192444; 26/3/20: WID:RP-192444->RP-200100; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1254 | 800160 | Core part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Fri 13/12/19 | 100% | RP-200655 |  | Ericsson |  | basket WI¦TR 36.716-01-01¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1255 | 800260 | Perf. part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200655 |  | Ericsson |  | basket WI¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1256 | 800061 | Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201263 |  | Qualcomm |  | basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 8/10/19: WID:RP-191085->RP-191733; 14/1/20: WID:RP-191733->RP-192525; 26/3/20: WID:RP-192525->RP-200231; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1257 | 800161 | Core part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201263 |  | Qualcomm |  | basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1258 | 800261 | Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201263 |  | Qualcomm |  | basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1259 | 800062 | Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201012 |  | Huawei |  | basket WI¦TR 36.716-03-01¦16/1/19: WID:RP-181436->RP-182553¦26/3/19: WID:RP-182553->RP-190375; 26/6/19: WID:RP-190375->RP-191120; 8/10/19: WID:RP-191120->RP-192083; 14/1/20: WID:RP-192083->RP-192811; 26/3/20: WID:RP-192811->RP-200451; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1260 | 800162 | Core part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201012 |  | Huawei |  | basket WI¦TR 36.716-03-01¦26/3/19: WID:RP-182553->RP-190375; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1261 | 800262 | Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201012 |  | Huawei |  | basket WI¦26/3/19: WID:RP-182553->; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1262 | 800063 | Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201238 |  | Nokia |  | basket WI¦TR 36.716-04-01¦16/1/19: WID:RP-181408->RP-182330¦26/3/19: WID:RP-182330->RP-190138; 26/6/19: WID:RP-190138->RP-190906; 8/10/19: WID:RP-190906->RP-191730; 14/1/20: WID:RP-191730->RP-192423; 26/3/20: WID:RP-192423->RP-200157; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1263 | 800163 | Core part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201238 |  | Nokia |  | basket WI¦TR 36.716-04-01¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1264 | 800263 | Perf. part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201238 |  | Nokia |  | basket WI¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1265 | 800064 | Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201014 |  | Huawei |  | basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1266 | 800164 | Core part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201014 |  | Huawei |  | basket WI¦TR 36.716-02-02¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1267 | 800264 | Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Fri 13/12/19 | 100% | RP-201014 |  | Huawei |  | basket WI¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1268 | 800065 | Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200740 |  | LG Electronics |  | basket WI¦TR 36.716-00-02¦16/1/19: WID:RP-180778->RP-182301¦26/3/19: WID:RP-182301->RP-190150; 26/6/19: WID:RP-190150->RP-190946; 8/10/19: WID:RP-190946->RP-191743; 14/1/20: WID:RP-191743->RP-192586; 26/3/20: WID:RP-192586->RP-200510; 28/7/20: WID:RP-2... |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1269 | 800165 | Core part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Fri 13/12/19 | 100% | RP-200740 |  | LG Electronics |  | basket WI¦TR 36.716-00-02¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1270 | 800265 | Perf. part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200740 |  | LG Electronics |  | basket WI¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1271 | 810061 | UE Conformance Test Aspects – Rel-16 LTE CA configurations | LTE_CA_R16-UEConTest | 2 | Rel-16 | R5 | Fri 14/09/18 | Wed 08/09/21 | 7% | RP-182648 |  | Ericsson |  | 16/1/19: WID:RP-181605->RP-182648; 8/10/20: 0%->7; 8/10/20: FCD:19/06/2020->12/20; 8/4/21: 7%->7; 8/4/21: FCD:11/12/2020->09/21 |  | 81 | 41 |  |  | Tue 25/09/18 | Thu 08/04/21
1272 | 830076 | LTE-based 5G terrestrial broadcast | LTE_terr_bcast | 1 | Rel-16 | R1 | Fri 15/06/18 | Mon 01/06/20 | 100% | RP-193050 |  | Qualcomm |  | 8/10/19: WID:RP-190732->RP-191924; 8/10/19: 36.276 added;; 14/1/20: WID:RP-191924->RP-193050 | 36.276; 36.476 | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
1273 | 800091 | Study on LTE-based 5G terrestrial broadcast | FS_LTE_terr_bcast | 2 | Rel-16 | R1 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181342 |  | Qualcomm |  | TR 36.7xx¦26/3/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
1274 | 830176 | Core part: LTE-based 5G terrestrial broadcast | LTE_terr_bcast-Core | 2 | Rel-16 | R1 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-193050 |  | Qualcomm |  | 26/3/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 26/03/20
1275 | 830276 | Perf. part: LTE-based 5G terrestrial broadcast | LTE_terr_bcast-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Mon 01/06/20 | 100% | RP-193050 |  | Qualcomm |  | 25/9/20: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Fri 25/09/20
1276 | 830094 | Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72 | 1 | Rel-16 | R4 | Fri 01/03/19 | Fri 11/09/20 | 99% | RP-191285 |  | Nokia |  | 26/6/19: WID:RP-190665->RP-191285 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1277 | 830194 | Core part: Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72-Core | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-190665 |  | Nokia |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1278 | 830294 | Perf. part: Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-190665 |  | Nokia |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1279 | 860030 | UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72-UEConTest | 2 | Rel-16 | R5 | Mon 16/12/19 | Fri 11/09/20 | 100% | RP-192506 |  | Airbus |  | affects: LTE. tested: REL-16 WI LTE_PC2_B31_B72-Core; 25/9/20: 0%->100; 8/10/20: FCD:15/03/2020->09/20 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 08/10/20
1280 | 800056 | Additional LTE bands |  | 1 | Rel-16 |  | Fri 15/06/18 | Wed 08/09/21 | 83% | [6 empty] | 80 | 41 |  |  | Wed 27/06/18 | NA
1281 | 800075 | Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1 | 2 | Rel-16 | R4 | Fri 15/06/18 | Wed 08/09/21 | 85% | RP-201200 |  | Ericsson |  | basket WI¦16/1/19: WID:RP-181006->RP-182768¦26/3/19: WID:RP-182768->RP-190332; 14/1/20: WID:RP-190332->RP-192453; 26/3/20: WID:RP-192453->RP-200153; 28/7/20: WID:RP-200153->RP-201200 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1282 | 800175 | Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201200 |  | Ericsson |  | basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1283 | 800275 | Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1-Perf | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201200 |  | Ericsson |  | basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1284 | 900052 | UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1-UEConTest | 3 | Rel-16 | R5 | Mon 14/12/20 | Wed 08/09/21 | 26% | RP-202522 |  | Ericsson |  | tested: REL-16 WI LTE_bands_R16_M1_NB1-Core ; 8/4/21: 0%->26 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
1285 | 800076 | Additional LTE bands for UE category M2 and/or NB2 in Rel-16 | LTE_bands_R16_M2_NB2 | 2 | Rel-16 | R4 | Fri 15/06/18 | Wed 08/09/21 | 78% | RP-200154 |  | Ericsson |  | basket WI¦no Perf. part¦16/1/19: WID:RP-181007->RP-182769¦26/3/19: WID:RP-182769->RP-190333; 14/1/20: WID:RP-190333->RP-192454; 26/3/20: WID:RP-192454->RP-200154 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
1286 | 800176 | Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16 | LTE_bands_R16_M2_NB2-Core | 3 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-201201 |  | Ericsson |  | basket WI¦no Perf. part¦26/3/19: WID:RP-182769->RP-190333; 28/7/20: WID:RP-200154->RP-201201; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1287 | 900053 | UE Conformance Test Aspects - Additional LTE bands for UE category M2 and/or NB2 in Rel-16 | LTE_bands_R16_M2_NB2-UEConTest | 3 | Rel-16 | R5 | Mon 14/12/20 | Wed 08/09/21 | 33% | RP-202523 |  | Ericsson |  | tested: REL-16 WI LTE_bands_R16_M2_NB2-Core ; 8/4/21: 0%->33 |  | 90 |  |  |  | Wed 06/01/21 | Thu 08/04/21
1288 | 800079 | Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2 | 1 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-181482 |  | NTT DOCOMO |  |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1289 | 800179 | Core part: Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2-Core | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-181482 |  | NTT DOCOMO |  | 14/1/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1290 | 800279 | Perf. part: Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-181482 |  | NTT DOCOMO |  | 26/3/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
1291 | 800082 | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM | 1 | Rel-16 | R1 | Fri 15/06/18 | Fri 17/12/21 | 63% | RP-193190 |  | LG Electronics |  | 16/1/19: WID:RP-181431->RP-182864¦26/3/19: WID:RP-182864->RP-190700; 26/6/19: WID:RP-190700->RP-191546; 8/10/19: WID:RP-191546->RP-191997; 14/1/20: WID:RP-191997->RP-193190 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1292 | 800182 | Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM-Core | 2 | Rel-16 | R1 | Fri 15/06/18 | Sat 15/06/19 | 100% | RP-193190 |  | LG Electronics |  | 26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1293 | 800282 | Perf. part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sat 15/06/19 | 100% | RP-193190 |  | LG Electronics |  | 26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1294 | 890047 | UE Conformance Test Aspects - Cross Link Interference (CLI) handling for NR | NR_CLI-UEConTest | 2 | Rel-16 | R5 | Thu 17/09/20 | Fri 17/12/21 | 5% | RP-210716 |  | Qualcomm |  | tested: CLI part of REL-16 WI NR_CLI_RIM-Core ; 7/4/21: WID:RP-201940->RP-210716; 8/4/21: 0%->5 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1295 | 800086 | DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE | 1 | Rel-16 | R1 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192766 |  | Huawei |  | 16/1/19: WID:RP-181485->RP-182901; 14/1/20: WID:RP-182901->RP-192766 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 14/01/20
1296 | 800186 | Core part: DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE-Core | 2 | Rel-16 | R1 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192766 |  | Huawei |  | 26/3/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
1297 | 800286 | Perf. part: DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-192766 |  | Huawei |  | 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1298 | 820071 | Transfer of Iuant interface specifications from 25-series to 37-series | Iuant_transfer | 1 | Rel-16 | R3 | Thu 13/12/18 | Mon 18/03/19 | 100% | RP-190160 |  | Huawei |  | administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf.... |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 26/03/19
1299 | 820171 | Core part: Transfer of Iuant interface specifications from 25-series to 37-series | Iuant_transfer-Core | 2 | Rel-16 | R3 | Thu 13/12/18 | Mon 18/03/19 | 100% | RP-190160 |  | Huawei |  | administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf.... |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 26/03/19
1300 | 820072 | Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility | Direct_data_fw_NR | 1 | Rel-16 | R3 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-182886 |  | Ericsson |  | no Perf. part |  | 82 | 42 |  |  | Wed 16/01/19 | NA
1301 | 820172 | Core part: Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility | Direct_data_fw_NR-Core | 2 | Rel-16 | R3 | Thu 13/12/18 | Tue 18/06/19 | 100% | RP-182886 |  | Ericsson |  | no Perf. part; 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1302 | 800089 | Even further mobility enhancement in E-UTRAN | LTE_feMob | 1 | Rel-16 | R2 | Fri 15/06/18 | Wed 15/12/21 | 72% | RP-200148 |  | China Telecom |  | compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 26/6/19: WID:RP-190272->RP-190921; 26/3/20: WID:RP-190921->RP-200148 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 26/03/20
1303 | 800189 | Core part: Even further mobility enhancement in E-UTRAN | LTE_feMob-Core | 2 | Rel-16 | R2 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200148 |  | China Telecom |  | compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 28/7/20: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1304 | 800289 | Perf. part: Even further mobility enhancement in E-UTRAN | LTE_feMob-Perf | 2 | Rel-16 | R4 | Fri 15/06/18 | Sun 15/12/19 | 100% | RP-200148 |  | China Telecom |  | 26/3/19: WID:RP-181475->RP-190272; 7/4/21: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 07/04/21
1305 | 880066 | UE Conformance Test Aspects - Even further mobility enhancement in E-UTRAN | LTE_feMob-UEConTest | 2 | Rel-16 | R5 | Mon 22/06/20 | Wed 15/12/21 | 16% | RP-200731 |  | China Telecom |  | 8/10/20: 0%->5; 8/4/21: 5%->16 |  | 88 | 45 |  |  | Tue 28/07/20 | Thu 08/04/21
1306 | 820078 | 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR | 1 | Rel-16 | R4 | Thu 13/12/18 | Thu 17/12/20 | 99% | RP-191287 |  | Nokia |  | 26/6/19: WID:RP-182898->RP-191287 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1307 | 820178 | Core part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR-Core | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-182898 |  | Nokia |  | 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1308 | 820278 | Perf. part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR-Perf | 2 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-182898 |  | Nokia |  | 26/6/19: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Wed 26/06/19
1309 | 890041 | UE Conformance Test Aspects - 410-430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe (Bands 87 and 88) | LTE410_Europe_PPDR-UEConTest | 2 | Rel-16 | R5 | Thu 17/09/20 | Thu 17/12/20 | 100% | RP-201479 |  | Nokia |  | tested: REL-16 WI LTE410_Europe_PPDR-Core ; 6/1/21: 0%->100 |  | 89 | 45 |  |  | Fri 25/09/20 | Wed 06/01/21
1310 | 850072 | Support for NavIC Navigation Satellite System for LTE | LCS_NAVIC | 1 | Rel-16 | R2 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192408 |  | Reliance Jio |  | introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408 |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 14/01/20
1311 | 850172 | Core part: Support for NavIC Navigation Satellite System for LTE | LCS_NAVIC-Core | 2 | Rel-16 | R2 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192408 |  | Reliance Jio |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1312 | 850272 | Perf. part: Support for NavIC Navigation Satellite System for LTE | LCS_NAVIC-Perf | 2 | Rel-16 | R4 | Thu 19/09/19 | Sun 15/03/20 | 100% | RP-192408 |  | Reliance Jio |  | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 26/03/20
1313 | 0 | All other Release 16 Features | - | 1 | Rel-16 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1314 | 840001 | 5G Media Streaming stage 3 | 5GMS3 | 1 | Rel-16 | S4 | Thu 06/06/19 | Tue 15/09/20 | 100% | SP-190464 |  | Paul Szucs, Sony | Paul.Szucs@Sony.com | 13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->70; 25/3/20: FCD:12/03/2020->06/20; 10/6/20: 70%->85; 26/6/20: FCD:12/06/2020->09/20; 12/9/20: 85%->100. Moved to Rel-16 | 26.234; 26.247; 26.117; 26.502; 26.503; 26.504; 26.511; 26.512 | 84 | 43 |  |  | Fri 31/05/19 | Sat 12/09/20
1315 | 880009 | User Plane Integrity Protection | UPIP_SEC | 1 | Rel-16 | S3 | Fri 12/06/20 | Thu 25/06/20 | 100% | SP-200656 |  | Tim Evans, Vodafone Group | tim.evans1@vodafone.com | 33.501; 33.401 ; 26/6/20: 0%->100; 25/9/20: WID:SP-200354->SP-200656 |  | 88 | 45 |  |  | Thu 25/06/20 | Fri 25/09/20
1316 | 880001 | Removal of H.263 and MPEG-4 Visual from 3GPP Services | RM_H263_MP4V | 1 | Rel-16 | S4 | Thu 25/06/20 | Wed 16/09/20 | 100% | SP-200400 |  | Thomas Stockhammer | tsto@qti.qualcomm.com | 26.140; 26.114; 26.244; 26.346; 26.234; 26/6/20: 0%->60; 12/9/20: 60%->100 |  | 88 | 45 |  |  | Thu 25/06/20 | Sat 12/09/20
1317 | 830086 | Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | MSR_GSM_UTRA_LTE_NR | 1 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-190642 |  | Ericsson |  |  |  | 83 | 42 |  |  | Tue 26/03/19 | NA
1318 | 830186 | Core part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications | MSR_GSM_UTRA_LTE_NR-Core | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-190642 |  | Ericsson |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1319 | 830286 | Perf. Part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications | MSR_GSM_UTRA_LTE_NR-Perf | 2 | Rel-16 | R4 | Fri 01/03/19 | Sun 15/09/19 | 100% | RP-190642 |  | Ericsson |  | 8/10/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Tue 08/10/19
1320 | 840066 | Volume Based Charging Aspects for VoLTE | VBCLTE | 1 | Rel-16 |  | Thu 06/09/18 | Thu 12/03/20 | 100% | SP-180813 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 14/3/19: 0%->50 | 32.251; 32.260; 32.298; 32.299 | 84 | 43 |  |  | Thu 06/09/18 | Thu 14/03/19
1321 | 810021 | Stage 2 of VBCLTE | VBCLTE | 2 | Rel-16 | S5 | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-180813 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 14/3/19: 0%->50; 13/9/19: 50%->55; 13/9/19: FCD:14/06/2019->12/20; 6/12/19: 55%->100 | 32.251; 32.260; 32.298; 32.299 | 81 | 41 |  |  | Thu 06/09/18 | Fri 06/12/19
1322 | 840012 | CT aspects of VBCLTE | VBCLTE | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191110 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com |  |  | 84 | 43 |  |  | Fri 31/05/19 | NA
1323 | 840067 | deleted - CT1 aspects of VBCLTE | VBCLTE | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191110 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 2/7/20: 0%->100 | 24.229 | 84 | 43 |  |  | Fri 31/05/19 | Thu 02/07/20
1324 | 840068 | CT3 aspects of VBCLTE | VBCLTE | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-201206 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 6/12/19: 0%->100; 26/6/20: WID:CP-191110->CP-201206 | 29.212; 29.213; 29.214 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
1325 | 820070 | Integrated access and backhaul for NR | NR_IAB | 1 | Rel-16 |  | Wed 15/03/17 | Fri 12/06/20 | 82% | RP-210442 |  | Qualcomm |  | follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 26/6/19: WID:RP-190712->RP-191558; 8/10/19: WID:RP-191558->RP-192188; 14/1/20: WID:RP-192188->RP-193226; 26/3/20: WID:RP-193226->RP-200084; 28/7/20: WID:RP-200084->RP-200840; 25/9/2... | 38.809 | 82 | 42 |  |  | Wed 16/01/19 | Wed 07/04/21
1326 | 750047 | Study on NR_IAB | FS_NR_IAB | 2 | Rel-16 | R2 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-181349 |  | Qualcomm |  | TR 38.8XX¦30/6/17: 38.874 added;¦19/9/17: WID: RP-170831->RP-171880¦8/1/18: WID: RP-171880->RP-17229027/3/18: Compl:0%->20%¦27/6/18: Compl:20%->50%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18;¦16/1/19: 50%->100 | 38.874 | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1327 | 850009 | Architecture enhancements for the support of Integrated access and backhaul (IAB) | IABARC | 2 | Rel-16 | S2 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190627 |  | Hong Cheng, Qualcomm Incorporated | hongc@qti.qualcomm.com | 13/9/19: 0%->33 | 23.501; 23.502; 23.401 | 85 | 43 |  |  | Fri 13/09/19 | Fri 13/09/19
1328 | 850060 | Stage 2 of IABARC | IABARC | 3 | Rel-16 | S2 | Thu 19/09/19 | Thu 12/12/19 | 100% | SP-190627 |  | Hong Cheng, Qualcomm Incorporated | hongc@qti.qualcomm.com | 13/9/19: 0%->33; 6/12/19: 33%->100 | 23.501; 23.502; 23.401 | 85 | 43 |  |  | Fri 13/09/19 | Fri 06/12/19
1329 | 850002 | CT4 aspects of IABARC | IABARC | 3 | Rel-16 | C4 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP201074 |  | Chaponniere, Lena, Qualcomm Incorporated | lguellec@qti.qualcomm.com | ; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: WID:CP-193015->CP 201074 | 24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 | 85 | 43 |  |  | Fri 13/09/19 | Thu 02/07/20
1330 | 880059 | CT1 aspects of IABARC | IABARC | 3 | Rel-16 | C1 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP201074 |  | Chaponniere, Lena, Qualcomm Incorporated | lguellec@qti.qualcomm.com | ; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: 0%->100 | 24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 | 85 | 43 |  |  | Fri 13/09/19 | Thu 02/07/20
1331 | 820170 | Core part: NR_IAB | NR_IAB-Core | 2 | Rel-16 | R2 | Thu 07/03/19 | Fri 06/03/20 | 100% | RP-210442 |  | Qualcomm |  | follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; ; 8/10/19: WID:RP-190712->RP-192188; 28/7/20: WID:RP-200084->RP-200840; 25/9/20: 0%->100; 25/9/20: 38.175 added;; 25/9/20: 38.809 added; | 38.175; 38.809 | 82 | 42 |  |  | Wed 16/01/19 | Fri 25/09/20
1332 | 820270 | Perf. Part: NR_IAB | NR_IAB-Perf | 2 | Rel-16 | R4 | Thu 07/03/19 | Fri 06/03/20 | 0% | RP-210442 |  | Qualcomm |  | 26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added; | 38.809; 38.176-1; 38.176-2 | 82 | 42 |  |  | Wed 16/01/19 | Fri 09/04/21
1333 | 850020 | Security for IAB | NR_IAB | 2 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/06/20 | 100% | SP-190902 |  | Rajavelsamy Rajadurai, Samsung | rajvel{@]samsung.com | ; 6/12/19: 0%->65; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100 | 33.501 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
1334 | 860013 | User Plane Gateway Function for Inter-PLMN Security | UPGF | 1 | Rel-16 | S3 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191123 |  | Steve Kohalmi, Juniper Networks | skohalmi@juniper.net | ; 6/12/19: 0%->90; 25/3/20: 90%->100 | 33.501 | 86 | 44 |  |  | Fri 06/12/19 | Wed 25/03/20
1335 | 790003 | Enhancements to IMS for new real time communication services | enIMS | 1 | Rel-16 | S1 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180137 |  | China Mobile, Hui Cai | caihui at chinamobile dot com | 7/6/18: 0%->25¦10/9/18: 25%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100 | 22.261; 22.468; 22.228; 22.280; 22.281; 22.282; 22.179 | 79 | 40 |  |  | Thu 15/03/18 | Tue 04/12/18
1336 | 820028 | Enhancement of 5G PCC related services | en5GPccSer | 1 | Rel-16 | C3 | Thu 13/12/18 | Thu 19/12/19 | 100% | CP-183246 |  | Xiaoyun Zhou, Huawei | zhouxiaoyun8@huawei.com | ¦14/3/19: 0%->10; 31/5/19: 10%->60; 13/9/19: 60%->70; 6/12/19: 70%->90; 26/3/20: 90%->100 | 29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 | 82 | 42 |  |  | Fri 07/12/18 | Thu 26/03/20
1337 | 810023 | Energy efficiency of 5G | EE_5G | 1 | Rel-16 | S5 | Thu 06/09/18 | Thu 12/03/20 | 100% | SP-191193 |  | CORNILY, Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->45; 13/9/19: 45%->70; 12/12/19: WID:SP-180819->SP-191193; 12/12/19: FCD:13/12/2019->03/20; 26/3/20: 70%->95; 28/6/20: 95%->100 | 28.540; 28.541; 28.552; 28.554 | 81 | 41 |  |  | Thu 06/09/18 | Sun 28/06/20
1338 | 820039 | Signalling Improvements for Network Efficiency in 5GS | SINE_5G | 1 | Rel-16 | C1 | Thu 13/12/18 | Thu 12/12/19 | 100% | CP-190142 |  | Shu, Lin | shulin@huawei.com | ¦14/3/19: 0%->50¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183085->CP-190142; 31/5/19: 50%->75; 13/9/19: 75%->85; 6/12/19: 85%->95; 26/3/20: 95%->100 | 24.501; 24.301; 24.368; 27.007; 24.008 | 82 | 42 |  |  | Fri 07/12/18 | Thu 26/03/20
1339 | 790001 | New Services and Markets Technology Enablers – Phase 2 | SMARTER_Ph2 | 1 | Rel-16 | S1 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180589 |  | Li, Alice, Vodafone | alice.li@vodafone.com | 7/6/18: WID:SP-180138->SP-180313¦7/6/18: 0%->10¦10/9/18: 10%->40¦4/12/18: 40%->100 | 22.261; 22.278 | 79 | 40 |  |  | Thu 15/03/18 | Tue 04/12/18
1340 | 780055 | 5G Voice Service Continuity | 5GVSC | 1 | Rel-16 | S1 | Thu 21/12/17 | Tue 13/03/18 | 100% | SP-171077 |  | Qun Wei, China Unicom | weiqun5@chinaunico.cn | 16/3/18: 0%->100 | 22.261 | 78 | 40 |  |  | Thu 21/12/17 | Fri 16/03/18
1341 | 790015 | Security Assurance Specification for 5G | SCAS_5G | 1 | Rel-16 | S3 | Thu 15/03/18 | Fri 13/09/19 | 100% | SP-180689 |  | Marcus Wong, Huawei Technologies | mwong@huawei.com | 27/3/18: added: 33.514¦33.513¦33.511¦33.512¦33.515 ¦6/8/18: 33.511 to 515 added;¦10/9/18: 0%->10¦2/10/18: WID:SP-180238->SP-180689¦7/12/18: 10%->20¦20/3/19: 20%->60; 31/5/19: 60%->75; 13/9/19: 75%->100 | 33.216; 33.926; 33.515; 33.511; 33.512; 33.513; 33.514; 33.515 | 79 | 40 |  |  | Thu 15/03/18 | Fri 13/09/19
1342 | 840069 | 5GS Transfer of Policies for Background Data Transfer | xBDT | 1 | Rel-16 |  | Thu 07/03/19 | Thu 12/03/20 | 100% | SP-180509 |  | Takeshi Usui KDDI | ta-usui@kddi.com |  | 23.501; 23.502; 23.503 | 84 | 43 |  |  | Wed 06/06/18 | NA
1343 | 800030 | Stage 2 of xBDT | xBDT | 2 | Rel-16 | S2 | Thu 07/03/19 | Thu 12/12/19 | 100% | SP-180509 |  | Takeshi Usui KDDI | ta-usui@kddi.com | 31/5/19: 0%->100 | 23.501; 23.502; 23.503 | 80 | 41 |  |  | Wed 06/06/18 | Fri 31/05/19
1344 | 840014 | CT aspects of xBDT | xBDT | 2 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192182 |  | Yan Xiaojian, ZTE | yan.xiaojian@zte.com.cn | 17/9/19: WID:CP-191113->CP-192182 |  | 84 | 43 |  |  | Fri 31/05/19 | Tue 17/09/19
1345 | 840070 | CT1 aspects of xBDT | xBDT | 3 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192182 |  | Yan Xiaojian, ZTE | yan.xiaojian@zte.com.cn | 13/9/19: 0%->100 | 24.526 | 84 | 43 |  |  | Fri 31/05/19 | Fri 13/09/19
1346 | 840071 | CT3 aspects of xBDT | xBDT | 3 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-192182 |  | Yan Xiaojian, ZTE | yan.xiaojian@zte.com.cn | 13/9/19: 0%->70; 6/12/19: 70%->95; 26/3/20: 95%->100 | 29.519; 29.513; 29.514; 29.122; 29.522; 29.525 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1347 | 850057 | CT4 aspects of xBDT | xBDT | 3 | Rel-16 | C4 | Tue 17/09/19 | Thu 12/03/20 | 100% | CP-192182 |  | Yan Xiaojian, ZTE | yan.xiaojian@zte.com.cn | 26/3/20: 0%->100 |  | 85 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1348 | 770020 | Service Interactivity | SerInter | 1 | Rel-16 | S4 | Fri 08/09/17 | Thu 12/12/19 | 100% | SP-170796 |  | Lo, Charles, Qualcomm Incorporated | clo@qti.qualcomm.com | 15/12/17: 0%->10¦16/3/18: 10%->20¦7/6/18: 20%->40¦7/6/18: FCD:06/18->12/18. Moved from Rel-15¦10/9/18: 40%->50¦7/12/18: 50%->60¦7/3/19: 60%->70¦7/3/19: FCD:12/18->06/19; 31/5/19: FCD:14/06/2019->09/20; 31/5/19: 70%->80; 13/9/19: FCD:12/09/2019->12/20; ... | 26.346; 26.247; 26.347 | 77 | 39 |  |  | Fri 08/09/17 | Fri 06/12/19
1349 | 800002 | Alternative EVS implementation using updated fixed-point basic operators | Alt_FX_EVS | 1 | Rel-16 | S4 | Wed 06/06/18 | Fri 14/12/18 | 100% | SP-180286 |  | Pawate, Raj, Cadence Design Systems Inc | pawateb@cadence.com | 6/8/18: 26.452 added;¦10/9/18: 0%->20¦7/12/18: 20%->90¦7/3/19: 90%->100 | 26.441; 26.442; 26.444; 26.445; 26.446; 26.447; 26.449; 26.450; 26.451; 26.952; 26.452 | 80 | 41 |  |  | Wed 06/06/18 | Thu 07/03/19
1350 | 800046 | Shared Data Handling on Nudm and Nudr | Shared_Data | 1 | Rel-16 | C4 | Wed 06/06/18 | Fri 14/12/18 | 100% | CP-181136 |  | Wiehe, Ulrich, Nokia | ulrich.wiehe@nokia.com | 10/9/18: 0%->90¦10/12/18: 90%->100 | 29.503; 29.505; 29.504 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/12/18
1351 | 790019 | Usage of CAPIF for xMB API | CAPIF4xMB | 1 | Rel-16 | S4 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180031 |  | Thorsten Lohmar, Ericsson LM | Thorsten.lohmar@ericsson.com | 7/6/18: 0%->25¦6/8/18: 26.348 added;¦10/9/18: 25%->40¦7/12/18: 40%->100 | 26.346, new; 26.348 | 79 | 40 |  |  | Thu 15/03/18 | Fri 07/12/18
1352 | 800009 | Policy delivery to UE for background data transfer | PDBDT | 1 | Rel-16 | S1 | Tue 08/05/18 | Fri 15/06/18 | 100% | SP-180324 |  | Takatsugu Kito, KDDI | ta-kito at kddi dot com | 10/9/18: 90%->100 | 22.261 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
1353 | 790004 | QoS Monitoring | QoS_MON | 1 | Rel-16 | S1 | Thu 15/03/18 | Fri 14/12/18 | 100% | SP-180141 |  | Amar Deol | amar.deol@huawei.com | 7/6/18: 0%->60¦10/9/18: 60%->85¦10/9/18: FCD:06/18->12/18¦4/12/18: 85%->100 | 22.261 | 79 | 40 |  |  | Thu 15/03/18 | Tue 04/12/18
1354 | 800005 | Inter-RAT Mobility requirements for real time service | MOBRT | 1 | Rel-16 | S1 | Wed 06/06/18 | Fri 14/09/18 | 100% | SP-180592 |  | Yang Xu, Oppo | xuyang@oppo.com | 10/9/18: 70%->100 | 22.261 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
1355 | 760058 | Management of QoE measurement collection | QOED | 1 | Rel-16 | S5 | Mon 05/06/17 | Thu 12/12/19 | 100% | SP-181069 |  | Petersen, Robert, Ericsson | robert <dot> petersen <at>ericsson<dot>ericsson | 30/6/17: 28.309 added;¦30/6/17: 28.308 added;¦30/6/17: 28.307 added;¦30/6/17: 28.406 added;¦11/9/17: 0%->5¦15/12/17: 5%->15¦16/3/18: 15%->25¦7/6/18: FCD:06/18->12/18. 16/6/16: moved from Rel-15¦10/9/18: 25%->30¦7/12/18: 30%->40¦13/12/18: FCD:...; 31/5/... | 32.101; 32.103; 6 new TS; 28.309; 28.308; 28.307; 28.406; 28.405; 28.404 | 76 | 39 |  |  | Wed 07/06/17 | Sun 13/09/20
1356 | 760059 | Study on network policy management for mobile networks based on NFV scenarios | FS_NETPOL | 1 | Rel-15 | S5 | Mon 05/06/17 | Thu 14/06/18 | 100% | SP-170593 |  | China Mobile Jinglei Liu | liujinglei@chinamobile.com | 30/6/17: 32.871 added;¦11/9/17: 0%->20¦15/12/17: 20%->30¦16/3/18: 30%->35¦7/6/18: 35%->100 | new; 32.871 | 76 | 39 |  |  | Mon 05/06/17 | Thu 07/06/18
1357 | 810025 | Network policy management for mobile networks based on NFV scenarios | NETPOL | 1 | Rel-16 | S5 | Thu 06/09/18 | Thu 12/12/19 | 100% | SP-191194 |  | China Mobile Hao Zhang | zhanghao@chinamobile.com | 7/12/18: 0%->10; 13/9/19: 10%->85; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 85%->100; 12/12/19: WID:SP-180821->SP-191194 | New | 81 | 41 |  |  | Thu 06/09/18 | Thu 12/12/19
1358 | 810024 | OAM aspects of LTE and WLAN integration | OAM_LTE_WLAN | 1 | Rel-16 | S5 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180820 |  | Yizhi Yao, Intel Corporation | yizhi dot yao at intel dot com | 7/12/18: 0%->50¦14/3/19: 50%->100 | 32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659 | 81 | 41 |  |  | Thu 06/09/18 | Thu 14/03/19
1359 | 810026 | Methodology for 5G management specifications | METHOGY | 1 | Rel-16 | S5 | Thu 06/09/18 | Fri 15/03/19 | 100% | SP-180822 |  | Groenendijk, Jan, Ericsson | jan<dot>Groenendijk<at>ericsson<dot>com | 7/12/18: 0%->60¦14/3/19: 60%->85; 13/9/19: 85%->100 | New; 32.156 | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
1360 | 820030 | Nchf Online and Offline charging services | OFSBI_CH | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 19/09/19 | 100% | SP-181066 |  | Zhu Lei, Huawei | Zhulei@huawei.com | ¦14/3/19: 0%->40; 31/5/19: 40%->70; 13/9/19: 70%->100 | 32.240; 32.255; 32.290; 32.291; 32.298 | 82 | 42 |  |  | Fri 07/12/18 | Fri 13/09/19
1361 | 820031 | Charging Enhancement of 5GC interworking with EPC | 5GIEPC_CH | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 19/09/19 | 100% | SP-181067 |  | Chen Shan, Huawei | chenshan@huawei.com | ¦14/3/19: 0%->30; 31/5/19: 30%->60; 13/9/19: 60%->100 | 32.255; 32.291; 32.298 | 82 | 42 |  |  | Fri 07/12/18 | Fri 13/09/19
1362 | 820032 | NRM enhancements | eNRM | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 12/03/20 | 100% | SP-190778 |  | Jing Ping, Nokia | jing.ping@nokia-sbell.com | ¦14/3/19: 0%->10¦21/3/19: WID:SP-181068 ->SP-190140¦21/3/19: FCD:019->09/19; 31/5/19: 10%->20; 13/9/19: 20%->40; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-190140->SP-190778; 26/3/20: 40%->92; 28/6/20: 92%->98; 13/9/20: 98%->100 | 28.540; 28.541; 28.622 ; 28.623; 28.620 | 82 | 42 |  |  | Fri 07/12/18 | Sun 13/09/20
1363 | 820033 | Network Exposure Charging in 5G System Architecture | 5GS_Ph1_NEFCH | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 19/12/19 | 100% | SP-181070 |  | Tornkvist, Robert, Ericsson | robert(dot)tornkvist(at)Ericsson(dot)com | ¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100 | 32.240; 32.254; 32.290; 32.291; 32.298 | 82 | 42 |  |  | Fri 07/12/18 | Fri 06/12/19
1364 | 820034 | Charging AMF in 5G System Architecture Phase 1 | 5GS_Ph1_AMFCH | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 19/12/19 | 100% | SP-181071 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | ¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->70; 6/12/19: 70%->100 | 32.240; 32.290; 32.291; 32.298; 32.297 | 82 | 42 |  |  | Fri 07/12/18 | Fri 06/12/19
1365 | 820036 | Trace Management in the context of Services Based Management Architecture | TM_SBMA | 1 | Rel-16 | S5 | Thu 13/12/18 | Thu 12/03/20 | 100% | SP-181073 |  | Andrianov, Anatoly, Nokia | anatoly.andrianov@nokia.com | ; 31/5/19: 0%->10; 13/9/19: FCD:19/06/2019->03/20; 26/3/20: 10%->50; 28/6/20: 50%->100 | 32.421; 32.422; 28.530; 28.532; 28.533; 28.540; 28.541 | 82 | 42 |  |  | Fri 07/12/18 | Sun 28/06/20
1366 | 820005 | Lawful Interception Rel-16 | LI16 | 1 | Rel-16 | S3LI | Thu 13/12/18 | Fri 11/06/21 | 100% | SP-181210 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 31/5/19: 0%->15; 13/9/19: 15%->40; 6/12/19: 40%->55; 25/3/20: 55%->60; 25/3/20: FCD:19/12/2019->03/20; 26/6/20: FCD:13/03/2020->09/20; 26/6/20: 60%->85; 12/9/20: 85%->92; 5/12/20: 92%->97; 19/3/21: 97%->99; 19/3/21: FCD:15/09/2020->06/21; 11/6/21: 99%-... | 33.107; 33.108; 33.126; 33.127; 33.128 | 82 | 42 |  |  | Fri 07/12/18 | Fri 11/06/21
1367 | 820038 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc16 | 1 | Rel-16 | C1 | Thu 13/12/18 | Wed 25/03/20 | 100% | CP-183084 |  | Leis, Peter, Nokia | peter.leis@nokia.com | ¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 30/6/20: 99%->100 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 82 | 42 |  |  | Fri 07/12/18 | Tue 30/06/20
1368 | 870077 | CT1 aspects of IMSProtoc16 | IMSProtoc16 | 2 | Rel-16 | C1 | Thu 13/12/18 | Fri 13/12/19 | 100% | CP-183084 |  | Leis, Peter, Nokia | peter.leis@nokia.com | ¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019-> | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 87 | 44 |  |  | Fri 07/12/18 | Thu 23/04/20
1369 | 880060 | CT3 aspects of IMSProtoc16 | IMSProtoc16 | 2 | Rel-16 | C3 | Thu 13/12/18 | Fri 13/12/19 | 100% | CP-183084 |  | Leis, Peter, Nokia | peter.leis@nokia.com | ¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019-> | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 87 | 44 |  |  | Fri 07/12/18 | Thu 23/04/20
1370 | 870078 | (IETF) Location Source Parameter for the SIP Geolocation Header Field (draft-ietf-sipcore-locparam) | 5GProtoc16 | 2 | Rel-16 | C1-IETF | Thu 13/12/18 | Wed 25/03/20 | 100% | CP-200146 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 30/6/20: 90%->100; 9/4/21: RFC 8787 added; | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ; RFC 8787 | 87 | 44 |  |  | Fri 07/12/18 | Fri 09/04/21
1371 | 820041 | Stage-3 5GS NAS protocol development | 5GProtoc16 | 1 | Rel-16 | C1 | Thu 13/12/18 | Wed 25/03/20 | 100% | CP-200146 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 25/3/20: WID:CP-183087->CP-200146 | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 | 42 |  |  | Fri 07/12/18 | Wed 25/03/20
1372 | 820049 | Stage-3 5GS NAS protocol development general aspects | 5GProtoc16 | 2 | Rel-16 | C1 | Thu 13/12/18 | Wed 25/03/20 | 100% | CP-200146 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 26/6/20: 98%->100 | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 | 42 |  |  | Fri 07/12/18 | Fri 26/06/20
1373 | 820050 | Stage-3 5GS NAS protocol development for support for non-3GPP accesses | 5GProtoc16-non3GPP | 2 | Rel-16 | C1 | Thu 13/12/18 | Wed 25/03/20 | 100% | CP-200146 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ¦14/3/19: 0%->25; 31/5/19: 25%->50; 25/3/20: FCD:19/12/2019->03/20; 30/6/20: 50%->100 | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 | 42 |  |  | Fri 07/12/18 | Tue 30/06/20
1374 | 820042 | Stage-3 SAE Protocol Development for Rel16 | SAES16 | 1 | Rel-16 | C1 | Thu 13/12/18 | Thu 19/12/19 | 100% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 | 42 |  |  | Fri 07/12/18 | NA
1375 | 820046 | Stage-3 SAE Protocol Development for Rel16 general aspects | SAES16 | 2 | Rel-16 | C1 | Thu 13/12/18 | Thu 19/12/19 | 100% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 26/3/20: 90%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 | 42 |  |  | Fri 07/12/18 | Thu 26/03/20
1376 | 820047 | Stage-3 SAE Protocol Development for Rel16 for CS Fallback in EPS | SAES16-CSFB | 2 | Rel-16 | C1 | Thu 13/12/18 | Thu 19/12/19 | 100% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 | 42 |  |  | Fri 07/12/18 | Tue 30/06/20
1377 | 820048 | Stage-3 SAE Protocol Development Rel16 for support for non-3GPP accesses | SAES16-non3GPP | 2 | Rel-16 | C1 | Thu 13/12/18 | Thu 19/12/19 | 100% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 | 42 |  |  | Fri 07/12/18 | Tue 30/06/20
1378 | 840018 | S6b Optional for ePDG connected to 5GS | 5GS_S6b_Optional | 1 | Rel-16 | S2 | Thu 09/05/19 | Thu 06/06/19 | 100% | SP-190447 |  | Irfan Ali, Cisco | irfaali at cisco dot com | 6/6/19: 0%->100 | 23.501; 23.502 | 84 | 43 |  |  | Fri 31/05/19 | Thu 06/06/19
1379 | 840002 | Service Based Interface Protocol Improvements | SBIProtoc16 | 1 | Rel-16 | ct | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191060 |  | Yue Song, China Mobile | songyue (at) chinamobile (dot) com |  |  | 84 | 43 |  |  | Fri 31/05/19 | NA
1380 | 840052 | CT3 aspects of SBIProtoc16 | SBIProtoc16 | 2 | Rel-16 | C3 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191060 |  | Yue Song, China Mobile | songyue (at) chinamobile (dot) com | 13/9/19: 0%->25; 6/12/19: 25%->75; 26/3/20: 75%->100 | 29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554 | 84 | 43 |  |  | Fri 31/05/19 | Thu 26/03/20
1381 | 840053 | CT4 aspects of SBIProtoc16 | SBIProtoc16 | 2 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191060 |  | Yue Song, China Mobile | songyue (at) chinamobile (dot) com | 31/5/19: 0%->10; 6/12/19: 10%->90; 26/3/20: 90%->95; 26/6/20: 95%->100 | 29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.531; 29.540; 29.518; 29.571; 29.572; 29.573 | 84 | 43 |  |  | Fri 31/05/19 | Fri 26/06/20
1382 | 840008 | Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 | ISAT-MO-WITHDRAW | 1 | Rel-16 | C1 | Thu 06/06/19 | Thu 12/03/20 | 100% | CP-191151 |  | Dawes, Peter, Vodafone | peter(dot)dawes(at)vodafone(dot)com | ; 13/9/19: 0%->100 | 24.323 | 84 | 43 |  |  | Fri 31/05/19 | Fri 13/09/19
1383 | 840051 | Lawful Interception Report Rel-16 | LIR16 | 1 | Rel-16 | S3LI | Thu 06/06/19 | Thu 12/12/19 | 0% | SP-190342 |  | Nag Rao, Nokia | nagaraja.rao@nokia.com |  | New | 84 | 43 |  |  | Fri 31/05/19 | NA
1384 | 850003 | RTCP Verification for Real-Time Services | RTCPVer | 1 | Rel-16 | S4 | Fri 13/09/19 | Thu 12/03/20 | 100% | SP-190639 |  | Burman, Bo, Ericsson LM, | bo.burman@ericsson.com | ; 8/10/19: 26.139 added;; 6/12/19: 0%->60; 25/3/20: 60%->100 | 26.114; 24.380; 24.581; 26.281; New ; 26.139 | 85 | 43 |  |  | Fri 13/09/19 | Wed 25/03/20
1385 | 850025 | Network Slice Performance and Analytics Charging in 5G System | 5GS_NSPACH | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190780 |  | Chen Shan, Huawei | chenshan@huawei.com | 8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100 | 32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201 | 85 | 43 |  |  | Fri 13/09/19 | Sun 13/09/20
1386 | 850026 | Closed loop SLS Assurance | COSLA | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190781 |  | Groenendijk, Jan, Ericsson | jan.groenendijk@ericsson.com | ; 8/10/19: 28.536 added;; 26/3/20: 0%->55; 28/6/20: 55%->100 | 28.533; 28.540; 28.541; 28.530; 28.531; 28.545; 28.546; 28.550; 28.552; 28.553 ; 28.536; 28.535 | 85 | 43 |  |  | Fri 13/09/19 | Sun 28/06/20
1387 | 850027 | Streaming trace reporting | OAM_RTT | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190782 |  | Andrianov, Anatoly, Nokia | anatoly.andrianov@nokia.com | ; 26/3/20: 0%->25; 28/6/20: 25%->100 | 32.421; 32.422; 32.423; 28.532; 28.533 | 85 | 43 |  |  | Fri 13/09/19 | Sun 28/06/20
1388 | 850031 | Enhancement of 3GPP management system for multiple tenant environment support | MEMTANE | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190786 |  | Zhu, Lei, Huawei | lei.zhu@huawei.com | ; 26/3/20: 0%->35; 28/6/20: 35%->100 | 28.531; 28.532; 28.533; 28.541; 28.552; 28.554 | 85 | 43 |  |  | Fri 13/09/19 | Sun 28/06/20
1389 | 850033 | Network Slice Management Charging in 5G System | 5GS_NSMCH | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-190788 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | ; 8/10/19: 28.202 added;; 6/12/19: 0%->5; 28/6/20: 5%->50; 13/9/20: 50%->100 | 32.240; 32.290; 32.291; 32.298; 32.297 ; 28.202 | 85 | 43 |  |  | Fri 13/09/19 | Sun 13/09/20
1390 | 850034 | Management Aspects of 5G Service-Level Agreement | MA5SLA | 1 | Rel-16 | S5 | Thu 19/09/19 | Thu 12/03/20 | 100% | SP-200185 |  | Hu, Yushuang, CMCC | huyushuang@chinamobile.com | ; 25/3/20: WID:SP-190789->SP-200185; 26/3/20: 0%->100 | 28.540; 28.541 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
1391 | 850001 | Load and Overload Control of 5GC Service Based Interfaces | LOLC | 1 | Rel-16 |  | Wed 06/06/18 | Thu 12/03/20 | 100% | CP-200059 |  | Giorgi Gulbani (Huawei) | giorgi.gulbani@huawei.com | ; 25/3/20: WID:CP-192019->CP-200059 |  | 85 | 43 |  |  | Fri 13/09/19 | Wed 25/03/20
1392 | 800044 | Study on Load and Overload Control of 5GC Service Based Interfaces | FS_LOLC | 2 | Rel-16 | C4 | Wed 06/06/18 | Fri 14/06/19 | 100% | CP-181195 |  | Sridhar Bhaskaran (Huawei) | sridhar.bhaskaran@huawei.com | 6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100 | New; 22.943 | 80 | 41 |  |  | Wed 06/06/18 | Fri 06/12/19
1393 | 850052 | Deleted: C3 aspects of LOLC (TBD) | LOLC | 2 | Rel-16 | C3 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-200059 |  | Giorgi Gulbani (Huawei) | giorgi.gulbani@huawei.com | 2/7/20: deleted, put at 100% (was at 0) | TBD | 85 | 43 |  |  | Fri 13/09/19 | NA
1394 | 850054 | C4 aspects of LOLC | LOLC | 2 | Rel-16 | C4 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-200059 |  | Giorgi Gulbani (Huawei) | giorgi.gulbani@huawei.com | ; 26/3/20: 0%->90; 26/6/20: 90%->100 | 29.500; 29.510 | 85 | 43 |  |  | Fri 13/09/19 | Fri 26/06/20
1395 | 880056 | 5GS Enhanced support of Over the air (OTA) mechanism for UICC configuration parameter update | 5GS_OTAF | 1 | Rel-16 | C4 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192257 |  | Wiehe, Ulrich, Nokia | Ulrich.Wiehe@nokia.com | ; 6/12/19: 0%->65; 26/3/20: 65%->100 | 23.122; 29.503 ; 29.510 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
1396 | 880057 | C1 aspects of 5GS_OTAF | 5GS_OTAF | 2 | Rel-16 | C1 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192257 |  | Wiehe, Ulrich, Nokia | Ulrich.Wiehe@nokia.com | ; 6/12/19: 0%->65; 26/3/20: 65%->100 | 23.122; 29.503 ; 29.510 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
1397 | 850005 | C4 aspects of 5GS_OTAF | 5GS_OTAF | 2 | Rel-16 | C4 | Thu 19/09/19 | Thu 12/03/20 | 100% | CP-192257 |  | Wiehe, Ulrich, Nokia | Ulrich.Wiehe@nokia.com | ; 6/12/19: 0%->65; 26/3/20: 65%->100 | 23.122; 29.503 ; 29.510 | 85 | 43 |  |  | Fri 13/09/19 | Thu 26/03/20
1398 | 830026 | Integration of ONAP and 3GPP 5G management framework | ONAP3GPP | 1 | Rel-16 | S5 | Thu 07/03/19 | Thu 12/03/20 | 100% | SP-190139 |  | SMITH David K., AT&T | DS9930@att.com | 31/5/19: 0%->10; 13/9/19: 10%->25; 13/9/19: FCD:05/03/2020->03/20; 26/3/20: 25%->100 | 28.540; 28.622; 28.623; 28.532 | 83 | 42 |  |  | Thu 14/03/19 | Thu 26/03/20
1399 | 860011 | Support of Hybrid DASH/HLS over eMBMS | DAHOE | 1 | Rel-16 | S4 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-190988 |  | Thienot, Cédric, Enensys | cedric.thienot@enensys.com | 25/3/20: 0%->100 | 26.346; 26.347; 26.348 | 86 | 44 |  |  | Fri 06/12/19 | Wed 25/03/20
1400 | 860017 | 3GPP profiles for cryptographic algorithms and security protocols | CryptPr | 1 | Rel-16 | S3 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191129 |  | Christine Jost, Ericsson | christine.jost@ericsson.com | ; 25/3/20: 0%->100 | 33.210, 33.310, 33.501 | 86 | 44 |  |  | Fri 06/12/19 | Wed 25/03/20
1401 | 860020 | CHF-controlled quota management | CHFCQM | 1 | Rel-16 | S5 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191189 |  | Lagha, Naceur, Amdocs | nlagha@amdocs.com | ; 26/3/20: 0%->50; 28/6/20: 50%->100 | 32.255; 32.290; 32.291 | 86 | 44 |  |  | Fri 06/12/19 | Sun 28/06/20
1402 | 860021 | Management of MDT in 5G | 5GMDT | 1 | Rel-16 | S5 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191190 |  | Ayani, Zhulia, Ericsson | zhulia.Ayani@ericsson.com | ; 26/3/20: 0%->100 | 32.421; 32.422; 32.423; 28.532; 28.533 | 86 | 44 |  |  | Fri 06/12/19 | Thu 26/03/20
1403 | 860023 | 5G management capabilities | 5GMNC | 1 | Rel-16 | S5 | Fri 06/12/19 | Thu 12/03/20 | 100% | SP-191195 |  | CORNILY, Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | ; 26/3/20: 0%->100 | 28.532 | 86 | 44 |  |  | Fri 06/12/19 | Thu 26/03/20
1404 | 860001 | Nudsf Service Based Interface | NUDSF | 1 | Rel-16 | C4 | Fri 06/12/19 | Thu 12/03/20 | 100% | CP-193270 |  | Askerup, Anders, Hewlett Packard Enterprise, | Anders.Askerup@hpe.com. | ; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100 | 29.510; 29.500 | 86 | 44 |  |  | Fri 06/12/19 | Thu 02/07/20
1405 | 840029 | Study on Nudsf Service Based Interface | FS_NUDSF | 1 | Rel-16 | C4 | Thu 06/06/19 | Thu 12/12/19 | 100% | CP-191236 |  | Askerup, Anders, Hewlett Packard Enterprise | Anders.Askerup@hpe.com | 31/5/19: 0%->10; 6/12/19: 10%->100 | 29.808 | 84 | 43 |  |  | Fri 31/05/19 | Fri 06/12/19
1406 | 860002 | Nsoraf Service Based Interface | NSORAF | 1 | Rel-16 | C4 | Fri 06/12/19 | Thu 12/03/20 | 100% | CP-193017 |  | EL MOATAMID, Abdessamad, Orange | abdessamad.elmoatamid@orange.com. | ; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100 | 29.503; 29.510 | 86 | 44 |  |  | Fri 06/12/19 | Thu 02/07/20
1407 | 860004 | Video enhancement of IMS CAT/CRS/announcement services | eIMSVideo | 1 | Rel-16 | C1 | Fri 06/12/19 | Thu 12/03/20 | 100% | CP-193149 |  | Hongxia Hao, Huawei | haohongxia@huawei.com | ; 26/3/20: 0%->33; 26/6/20: 33%->100 | 24.182; 24.183; 24.628 | 86 | 44 |  |  | Fri 06/12/19 | Fri 26/06/20
1408 | 870010 | Ambient noise test methodology for evaluation of acoustic UE performance | ANTeM | 1 | Rel-16 | S4 | Mon 17/02/20 | Wed 25/03/20 | 100% | SP-200051 |  | Jan Reimes, HEAD acoustics GmbH, | jan.reimes@head-acoustics.de | ; 26/6/20: 0%->100 | 26.132 | 87 | 44 |  |  | Wed 25/03/20 | Fri 26/06/20
1409 | 890045 | UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR | B1C_BDS_pos_UEConTest | 1 | Rel-16 | R5 | Thu 17/09/20 | Thu 17/06/21 | 71% | RP-201777 |  | CATT |  | tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1410 | 911002 | UE Conformance Test Aspects - Support of eCall over IMS for NR | NR_EIEI-UEConTest | 1 | Rel-16 | R5 | Fri 12/03/21 | Sat 12/03/22 | 0% | RP-210704 |  | Qualcomm |  | tested: REL-16 TEI CRs of SA2/CT1/R2; compare LTE REL-14 WI EIEI-UEConTest "Evolution to and Interworking with eCall in IMS" | [5 empty] | Wed 07/04/21 | NA
1411 | 770050 | (Small) Technical Enhancements and Improvements for Rel-16 | TEI16 | 1 | Rel-16 |  | Mon 11/09/17 | Tue 30/06/20 | 0% | [6 empty] | 77 | 41 |  |  | Mon 15/06/15 | Mon 15/06/15
1412 | 800100 | (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446) | TEI16 | 2 | Rel-16 | S3-IETF | Mon 11/09/17 | Fri 14/12/18 | 100% | [6 empty] | 80 | 41 |  |  | Wed 27/06/18 | NA
1413 | 860099 | (Small) Test Technical Enhancements and Improvements for Rel-16 | TEI16_Test | 2 | Rel-16 | R5 | Thu 23/01/20 | Tue 30/06/20 | 0% | [6 empty] | 86 | 41 |  |  | Wed 27/06/18 | NA
1414 | 0 | Release 16 Studies with no corresponding Feature | - | 1 | Rel-16 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1415 | 0 | Release 16 Studies on 5G/5GS/5GC/NR | - | 1 | Rel-16 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1416 | 800029 | Study on system architecture for next generation real time communication services | FS_NG_RTC | 1 | Rel-16 | S2 | Wed 06/06/18 | Thu 14/03/19 | 0% | SP-180508 |  | Yi Jiang | jiangyi at chinamobile dot com |  | New | 80 | 41 |  |  | Wed 06/06/18 | NA
1417 | 790014 | Study on security aspects of single radio voice continuity from 5G to UTRAN | FS_5G_UTRAN_SEC | 1 | Rel-16 | S3 | Thu 15/03/18 | Fri 15/03/19 | 100% | SP-180209 |  | Feng Gao, China Unicom | gaofeng149@chinaunicom.cn | 27/3/18: 33.856 added;¦7/6/18: 0%->50¦10/9/18: 50%->79¦7/12/18: 79%->100 | 33.856 | 79 | 40 |  |  | Thu 15/03/18 | Fri 07/12/18
1418 | 780023 | Study on supporting 256-bit algorithms for 5G | FS_256_Algo | 1 | Rel-16 | S3 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-171054 |  | Evans, Tim, Vodafone Group | tim.evans1@vodafone.com | 16/3/18: 0%->30¦7/6/18: 30%->55¦10/9/18: 55%->60¦7/12/18: 60%->100 | new | 78 | 40 |  |  | Fri 15/12/17 | Fri 07/12/18
1419 | 780001 | Study on User Plane Protocol in 5GC | FS_UPPS | 1 | Rel-16 | C4 | Fri 15/12/17 | Fri 14/06/19 | 100% | CP-182052 |  | Satoru Matsushima, SoftBank Corp | satoru.matsushima@g.softbank.co.jp | 16/3/18: 0%->5¦2/10/18: WID:CP-173160->CP-182052¦2/10/18: FCD:09/18->06/19¦14/3/19: 20%->70; 31/5/19: 70%->90; 14/1/20: 90%->100 | 29.892 | 78 | 40 |  |  | Fri 15/12/17 | Tue 14/01/20
1420 | 790012 | Study on Application Awareness Interworking between LTE and NR | FS_AAI_LTE_NR | 1 | Rel-16 | S2 | Thu 15/03/18 | Thu 14/03/19 | 30% | SP-180122 |  | Biao Long, China Telecom | longb.gd@chinatelecom.cn | 7/6/18: 0%->30¦6/8/18: 23.727 added; | new; 23.727 | 79 | 40 |  |  | Thu 15/03/18 | Mon 06/08/18
1421 | 800090 | Study on NR beyond 52.6 GHz | FS_NR_beyond_52GHz | 1 | Rel-16 | RP | Fri 15/06/18 | Fri 14/09/18 | 100% | RP-181435 |  | Intel |  | 14/1/20: 0%->100 | 38.8xx | 80 | 41 |  |  | Mon 06/08/18 | Tue 14/01/20
1422 | 800093 | Study on remote interference management for NR | FS_NR_RIM | 1 | Rel-16 | R1 | Fri 15/06/18 | Sat 15/12/18 | 100% | RP-181430 |  | CMCC |  | TR 38.8xx¦see follow-up REL-16 WI NR_CLI_RIM¦16/1/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 16/01/19
1423 | 801000 | Study on RAN-centric data collection and utilization for LTE and NR | FS_LTE_NR_data_collect | 1 | Rel-16 | R3 | Fri 01/06/18 | Sat 01/06/19 | 100% | RP-181456 |  | CMCC |  | TR 37.8XX, related to SON, MDT; 26/6/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 26/06/19
1424 | 801001 | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR UEs | FS_NR_MIMO_OTA_test | 1 | Rel-16 | R4 | Fri 15/06/18 | Fri 13/12/19 | 100% | RP-201069 |  | CAICT |  | related REL-15 SI FS_NR_test_methods; 23/1/20: 0%->45; 23/1/20: WID:RP-181402->RP-182305; 28/7/20: WID:RP-182305->RP-201069; 28/7/20: 45%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 28/07/20
1425 | 801002 | Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR | FS_NR_2RX_vehUE | 1 | Rel-16 | R4 | Fri 01/06/18 | Sat 15/12/18 | 100% | RP-181467 |  | Samsung |  | TR 38.8XX¦16/1/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Wed 16/01/19
1426 | 750044 | Study of test methods for New Radio | FS_NR_test_methods | 1 | Rel-16 | R4 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-180546 |  | Intel |  | TR 38.8XX¦19/6/17: Compl:0%->10%¦19/6/17: WID: RP-170824->RP-171021¦30/6/17: 38.810 added;19/9/17: Compl:10%->15%19/9/17: WID: RP-171021->RP-171828¦8/1/18: Compl:15%->20%27/3/18: Compl:20%->45%27/3/18: CD:Thu 15/ ¦2¦16/1/19: 75%->100 | 38.81 | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1427 | 750046 | Study on Non-Orthogonal Multiple Access (NOMA) for NR | FS_NR_NOMA | 1 | Rel-16 | R1 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-181403 |  | ZTE |  | TR 38.8XX¦19/6/17: WID: RP-170829->RP-171043¦30/6/17: 32.812 added;¦27/6/18: Compl:0%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦27/6/18: WID: RP-171043->RP-181403;¦16/1/19: 40%->100 | 32.812 | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1428 | 810033 | Stopped - Study of KDF negotiation for 5G System Security | FS_5GS_KDF | 1 | Rel-16 | S3 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180691 |  | Ahmad Muhanna | ahmad.muhanna@huawei.com | 7/12/18: 0%->55¦20/3/19: 55%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Wed 20/03/19
1429 | 760053 | Study on Long Term Key Update Procedures | FS_LTKUP | 1 | Rel-16 | S3 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-170413 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 11/9/17: 0%->10¦15/12/17: 10%->70¦15/12/17: FCD:12/17->03/18¦16/3/18: 70%->90¦16/3/18: FCD:03/18->06/18¦7/6/18: FCD:06/18->12/18. 10/9/18: moved from Rel-15 as per SP-180687¦7/12/18: 90%->100 | Internal TR | 76 | 39 |  |  | Sat 03/06/17 | Fri 07/12/18
1430 | 810006 | Study on eXtended Reality (XR) in 5G | FS_5GXR | 1 | Rel-16 | S4 | Tue 02/10/18 | Thu 12/03/20 | 100% | SP-180667 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 2/10/18: Moved from Rel-17. 17/01/19: acronym corrected from FS_XR5G¦12/3/19: 0%->35; 31/5/19: 35%->45; 13/9/19: 45%->60; 13/9/19: FCD:13/12/2019->03/20; 25/3/20: 60%->100; 25/9/20: 26.998 added; | 26.9xx; 26.998 | 81 | 41 |  |  | Thu 06/09/18 | Fri 25/09/20
1431 | 820060 | Study on 7 - 24 GHz frequency range for NR | FS_7to24GHz_NR | 1 | Rel-16 | R4 | Thu 13/12/18 | Fri 13/12/19 | 100% | RP-192076 |  | Huawei |  | TR. 38.8xx¦26/3/19: WID:RP-182884->RP-190373; 8/10/19: WID:RP-190373->RP-192076; 28/7/20: 0%->100 |  | 82 | 42 |  |  | Wed 16/01/19 | Tue 28/07/20
1432 | 830006 | Study on UEs Supporting Handset Mode with Non-Traditional Earpieces | FS_HaNTE | 1 | Rel-16 | S4 | Thu 07/03/19 | Thu 05/09/19 | 100% | SP-190041 |  | Schevciw, Andre, Qualcomm Incorporated | aschevci@qti.qualcomm.com | 31/5/19: 0%->10; 13/9/19: 10%->100 | New | 83 | 42 |  |  | Thu 14/03/19 | Fri 13/09/19
1433 | 830072 | Study on enhancement for disaggregated gNB architecture | FS_enh_disagg_gNB | 1 | Rel-16 | R3 | Fri 01/03/19 | Sun 15/12/19 | 100% | RP-191975 |  | China Telecom |  | 26/6/19: WID:RP-190702->RP-191481; 8/10/19: WID:RP-191481->RP-191975; 8/10/19: 38.823 added;; 14/1/20: 0%->100 | 38.823 | 83 | 42 |  |  | Tue 26/03/19 | Tue 14/01/20
1434 | 840090 | Study on 5G NR UE Application Layer Data Throughput Performance | FS_UE_5GNR_App_Data_Perf | 1 | Rel-16 | R5 | Mon 17/06/19 | Wed 08/09/21 | 87% | RP-210710 |  | Qualcomm |  | compare: REL-11 SI FS_UE_App_Data_Perf; TR 37.9xx. 07/2019: title changed from "…UE 5G NR…"; 8/10/19: 37.901-5 added;; 14/1/20: WID:RP-191590->RP-192712; 8/10/20: 0%->87; 8/10/20: FCD:13/03/2020->12/20; 6/1/21: WID:RP-192712->RP-202849; 7/4/21: WID:RP-... | 37.901-5 | 84 | 43 |  |  | Wed 26/06/19 | Thu 08/04/21
1435 | 0 | Release 16 other Studies | - | 1 | Rel-16 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1436 | 770002 | Study on using Satellite Access in 5G | FS_5GSAT | 1 | Rel-16 | S1 | Fri 08/09/17 | Fri 15/06/18 | 100% | SP-170702 |  | MICHEL, Cyril | cyril.michel@thalesaleniaspace.com | 15/12/17: 22.822 added;¦15/12/17: 0%->30¦15/12/17: FCD:12/17->06/18¦16/3/18: 30%->70¦7/6/18: 70%->100 | New; 22.822 | 77 | 39 |  |  | Fri 08/09/17 | Thu 07/06/18
1437 | 770003 | Study on enhancements to IMS for new real time communication services | FS_enIMS | 1 | Rel-16 | S1 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170703 |  | China Mobile, Hui Cai | caihui at chinamobile dot com | 11/9/17: 0%->20¦15/12/17: 22.823 added;¦15/12/17: 20%->75¦16/3/18: 75%->100; 25/9/20: 26.998 added; | New; 22.823; 26.998 | 77 | 39 |  |  | Fri 08/09/17 | Fri 25/09/20
1438 | 800037 | Stopped - Study on protocol enhancement for real time communication | FS_PROTIMP | 1 | Rel-16 | S5 | Wed 06/06/18 | Fri 12/06/20 | 100% | SP-180597 |  | Olaf Pollakowski, Nokia | olaf.pollakowski@nokia.com | 6/8/18: 28.823 added;; 26/3/20: FCD:14/03/2019->06/20; 25/9/20: Stopped, so 0%->100 | New; 28.823 | 80 | 41 |  |  | Wed 06/06/18 | Fri 25/09/20
1439 | 800038 | Study on integration of ONAP and 3GPP configuration management services for 5G networks | FS_ONAPCINT | 1 | Rel-16 | S5 | Wed 06/06/18 | Thu 14/03/19 | 100% | SP-181075 |  | Li Gang, Ericsson | gang.g.li@ericsson.com | 10/9/18: 0%->5¦7/12/18: 5%->60¦14/12/18: WID:SP-180388->SP-181075¦14/3/19: 60%->100; 26/6/19: 28.890 added; | New; 28.890 | 80 | 41 |  |  | Wed 06/06/18 | Wed 26/06/19
1440 | 780031 | Study on integration of ONAP DCAE and 3GPP management architecture | FS_ONAPDCAE | 1 | Rel-16 | S5 | Fri 15/12/17 | Fri 15/03/19 | 100% | SP-181074 |  | ORANGE (Jean-Michel Cornily | jeanmichel.cornily@orange.com | 16/3/18: 0%->10¦27/3/18: 28.900 added;¦7/6/18: 10%->20¦7/6/18: FCD:09/18->03/19¦15/6/18: WID:SP-170948->SP-180389¦10/9/18: 20%->35¦7/12/18: 35%->80¦14/12/18: WID:SP-180389->SP-181074¦14/3/19: 80%->100 | 28.9 | 78 | 40 |  |  | Fri 15/12/17 | Thu 14/03/19
1441 | 800039 | Study on management aspects of edge computing | FS_MAN_EC | 1 | Rel-16 | S5 | Wed 06/06/18 | Thu 14/03/19 | 100% | SP-180390 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 6/8/18: 28.803 added;¦10/9/18: 0%->10¦7/12/18: 10%->20¦14/3/19: 20%->50; 31/5/19: 50%->65; 13/9/19: 65%->100 | New; 28.803 | 80 | 41 |  |  | Wed 06/06/18 | Fri 13/09/19
1442 | 750048 | Study on self-evaluation towards IMT-2020 submission | FS_5G_eval | 1 | Rel-16 | ITU-R AH,ITU-RAH | Wed 14/12/16 | Fri 14/06/19 | 100% | RP-181318 |  | Huawei |  | TR 38.9XX¦19/6/17: CD:Sat 15/09/18->Fri 15/06/18¦19/6/17: WID: RP-170832->RP-171451¦19/6/17: Release: Rel-16->Rel-15¦8/1/18: Compl:0%->15%27/3/18: Compl:15%->25%¦27/6/18: Compl:25%->35%¦27/6/18: CD:Fri 15/0; 26/6/19: 35%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 26/06/19
1443 | 780060 | Study on 6 GHz for LTE and NR | FS_6GHz_LTE_NR | 1 | Rel-16 | RP | Fri 15/12/17 | Fri 14/12/18 | 30% | RP-202798 |  | Ericsson |  | SI under RAN leadership¦TR 37.8XX27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957; 14... | 37.890; 37.107 | 78 | 40 |  |  | Mon 08/01/18 | Wed 06/01/21
1444 | 810029 | Study on management aspects of communication services | FS_CSMAN | 1 | Rel-16 | S5 | Thu 06/09/18 | Fri 14/06/19 | 100% | SP-180923 |  | Groenendijk, Jan, Ericsson | jan<dot>Groenendijk<at>ericsson<dot>com. | 7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100 | New | 81 | 41 |  |  | Thu 06/09/18 | Fri 13/09/19
1445 | 810005 | Study on Typical Traffic Characteristics of Media Services | FS_TyTrac | 1 | Rel-16 | S4 | Tue 02/10/18 | Thu 12/03/20 | 100% | SP-180666 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 2/10/18: Moved from Rel-17¦12/3/19: 0%->45; 31/5/19: 45%->50; 13/9/19: 50%->60; 13/9/19: FCD:13/12/2019->03/20; 25/3/20: 60%->100 | 26.9xx | 81 | 41 |  |  | Thu 06/09/18 | Wed 25/03/20
1446 | 820037 | Study on non-file-based trace reporting | FS_OAM_RTT | 1 | Rel-16 | S5 | Thu 06/12/18 | Wed 12/06/19 | 100% | SP-181076 |  | Andrianov, Anatoly, Nokia | anatoly.andrianov@nokia.com | 13/9/19: 0%->100 |  | 82 | 42 |  |  | Fri 07/12/18 | Fri 13/09/19
1447 | 820004 | Study on ambient noise test methodology for evaluation of acoustic UE performance | FS_ANTeM | 1 | Rel-16 | S4 | Thu 06/12/18 | Thu 12/12/19 | 100% | SP-180986 |  | Jan Reimes, HEAD acoustics GmbH | jan.reimes@head-acoustics.de | 12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100 |  | 82 | 42 |  |  | Fri 07/12/18 | Wed 25/03/20
1448 | 800027 | Stopped - Study on supporting Flexible Local Area Data Network | FS_FLADN | 1 | Rel-16 | S2 | Wed 06/06/18 | Thu 14/03/19 | 100% | SP-180506 |  | LG Electronics, | hyuns.kim@lge.com | 10/9/18: FCD:12/18->03/19¦6/6/19: stopped at 0% as per SP-190395 | New | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/09/18
1449 | 760045 | Study on encrypted traffic detection | FS_ENTRADE | 1 | Rel-16 | S2 | Mon 05/06/17 | Wed 12/06/19 | 70% | SP-181111 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | ¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170381->SP-170934¦16/3/18: 0%->20¦7/6/18: 20%->70¦14/12/18: FCD:09/18->06/19. Name changed | new 23.787 | 76 | 39 |  |  | Sat 03/06/17 | Fri 14/12/18
1450 | 850018 | Study on storage and transport of 5GC security parameters for ARPF authentication | FS_5GC_SEC_ARPF | 1 | Rel-16 | S3 | Thu 19/09/19 | Fri 12/03/21 | 100% | SP-190708 |  | Evans, Timothy, Vodafone | tim.evans1@vodafone.com | ; 8/10/19: 33.502 added;; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 30%->60; 12/9/20: 60%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->98; 11/6/21:... | New ; 33.502 | 85 | 43 |  |  | Fri 13/09/19 | Fri 11/06/21
1451 | 0 | --- RELEASE 15 --- | - | 1 | Rel-15 |  | Tue 15/03/16 | Tue 15/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1452 | 0 | Release 15 Features on 5G | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1453 | 740005 | 5G System - Phase 1 | 5GS_Ph1 | 1 | Rel-15 |  | Thu 09/06/16 | Fri 14/06/19 | 97% | SP-160958 |  | China Mobile, Tao Sun | suntao@chinamobile.com | 15/12/17: 23.503 added; |  | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1454 | 750019 | Study on Charging Aspects of 5G System Architecture Phase 1 | FS_5GS_Ph1_CH | 2 | Rel-15 | S5 | Fri 03/03/17 | Fri 15/12/17 | 100% | SP-170953 |  | Chen, Shan, Huawei | chenshan@huawei.com | 7/6/17: 0%->15¦11/9/17: 15%->60¦11/9/17: WID:SP-170128->SP-170659¦15/12/17: 60%->100¦21/12/17: WID:SP-170659->SP-170953 |  | 75 | 38 |  |  | Fri 03/03/17 | Thu 21/12/17
1455 | 720005 | (Stage 1 of 5G) New Services and Markets Technology Enablers | SMARTER | 2 | Rel-15 | S1 | Thu 09/06/16 | Wed 15/03/17 | 100% | SP-160364 |  | Li, Alice | alice.li@vodafone.com | Resulting from FS_SMARTER¦19/9/16: 0%->55¦6/10/16: 22.261 added¦1/12/16: FCD:09/16->03/20¦1/12/16: 55%->75¦2/3/17: 75%->90¦7/6/17: 90%->100 | 22.261 | 72 | 37 |  |  | Thu 09/06/16 | Wed 07/06/17
1456 | 740061 | Stage 2 of 5G System - Phase 1 | 5GS_Ph1 | 2 | Rel-15 | S2 | Thu 01/12/16 | Thu 14/12/17 | 100% | SP-160958 |  | China Mobile, Tao Sun | suntao@chinamobile.com | 3/3/17: 0%->30¦7/6/17: 30%->55¦11/9/17: 55%->75¦21/12/17: 75%->95¦11/6/18: 95%->100 | 23.401, 23.167, 23.271, 23.002; 23.228, 23.401, 23.167, 23.271, 23.502, 23.501; 23.503 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/06/18
1457 | 750016 | Security aspects of 5G System - Phase 1 | 5GS_Ph1-SEC | 2 | Rel-15 | S3 | Thu 02/03/17 | Fri 15/06/18 | 100% | SP-180693 |  | NTT DOCOMO, Alf Zugenmaier | alf.zugenmaier@hm.edu | 7/6/17: 0%->10¦11/9/17: 10%->30¦15/12/17: 30%->65¦21/12/17: WID:SP-170234->SP-170881¦16/3/18: 65%->85¦16/3/18: FCD:03/18->06/18¦7/6/18: 85%->95¦10/9/18: WID:SP-170881->100¦10/9/18: 95%->100¦2/10/18: WID:SP-170881->SP-180693 | 33.501; 33.401; 33.210; 33.310; 33.220 | 75 | 38 |  |  | Thu 02/03/17 | Tue 02/10/18
1458 | 870079 | Security aspects of 5G System - Phase 1 IETF | 5GS_Ph1-SEC | 2 | Rel-15 | S3-IETF | Thu 02/03/17 | Fri 15/06/18 | 50% | [6 empty] | 87 | 44 |  |  | Thu 02/03/17 | Tue 02/10/18
1459 | 750025 | CT aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 2 | Rel-15 | ct | Fri 03/03/17 | Thu 14/06/18 | 99% | CP-183243 |  | Song Yue (China Mobile) | songyue at chinamobile.com | 6/17: WID:CP-170204->CP-171105¦9/17: WID:CP-171105->CP-172034. Rapp changed, impacted TS clarified¦12/17: added: 24.501 ¦24.502 ¦29.520 added¦29.514¦29.513 ¦29.520a¦29.514a¦12/17: 29.519 added¦29.516 added;¦: 2.. 3/18: 29.554 added;29.59¦6/... | 24.501; 24.502; 29.520; 29.514; 29.513; ; 29.520a; 29.514a; 29.519; 29.516; 29.512; 29.508; 29.507; 29.551; 29.554; 29.522; 24.568; 29.521; 29.525; 29.524; 29.523 | 75 | 38 |  |  | Fri 03/03/17 | Mon 10/12/18
1460 | 750026 | Studies on CT1 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 |  | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 18/12/17: WID:CP-172034->CP-173161 | 23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007 | 75 | 38 |  |  | Fri 03/03/17 | Mon 18/12/17
1461 | 770042 | Study on 5G Network selection | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 10%->55¦15/12/17: 55%->80¦16/3/18: 80%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 16/03/18
1462 | 770043 | Study on 5G Mobility management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 40%->70¦15/12/17: 70%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 15/12/17
1463 | 770044 | Study on 5G Session management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 35%->75¦15/12/17: 75%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 15/12/17
1464 | 770045 | Study on 5G Non-3GPP access networks | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 15%->55¦15/12/17: 55%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 15/12/17
1465 | 770046 | Study on 5G Interworking with EPC | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 15%->45¦15/12/17: 45%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 15/12/17
1466 | 770047 | Study on 5G System core network impact on services, network functions and capabilities | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 20%->65¦15/12/17: 65%->85¦16/3/18: 85%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 16/03/18
1467 | 770048 | Study on 5G Network slicing | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail¦11/9/17: 10%->45¦15/12/17: 45%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Fri 15/12/17
1468 | 780008 | CT1 aspects of 5G System - Phase 1 (normative work) | 5GS_Ph1-CT | 3 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007 | 75 | 38 |  |  | Fri 03/03/17 | Fri 08/09/17
1469 | 780009 | 5G Network selection | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 16/3/18: 0%->60¦7/6/18: 60%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Thu 07/06/18
1470 | 780010 | 5G Mobility management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->25¦16/3/18: 25%->70¦7/6/18: 70%->95¦10/9/18: 95%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/09/18
1471 | 780011 | 5G Session management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->35¦16/3/18: 35%->85¦7/6/18: 85%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Thu 07/06/18
1472 | 780012 | 5G Non-3GPP access networks | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->95¦10/9/18: 95%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/09/18
1473 | 780013 | 5G Interworking with EPC | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Thu 07/06/18
1474 | 780014 | 5G System core network impact on services, network functions and capabilities | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->10¦16/3/18: 10%->70¦7/6/18: 70%->90¦10/9/18: 90%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/09/18
1475 | 780015 | 5G Network slicing | 5GS_Ph1-CT | 4 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100 |  | 77 | 39 |  |  | Fri 03/03/17 | Thu 07/06/18
1476 | 750027 | Study on CT3 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C3 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Fernandez, Susana (Ericsson) | Susana.Fernandez at ericsson.com | 5/6/17: 0%->20¦15/12/17: 20%->95¦22/3/18: 95%->100 | 29.213; 29.214; 29.219; 29.122 | 75 | 38 |  |  | Fri 03/03/17 | Thu 22/03/18
1477 | 790044 | CT3 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C3 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-183243 |  | Fernandez, Susana (Ericsson) | Susana.Fernandez at ericsson.com | 5/6/17: 0%->20¦15/12/17: 20%->95¦7/6/18: 35%->70¦7/6/18: 70%->100 | 29.213; 29.214; 29.219; 29.122 | 75 | 38 |  |  | Fri 03/03/17 | Thu 07/06/18
1478 | 750028 | CT4 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C4 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Landais, Bruno (Nokia) | Bruno.Landais at nokia.com | 5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦7/6/18: 50%->95¦10/9/18: 95%->99¦10/12/18: 99%->100 | 23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303 | 75 | 38 |  |  | Fri 03/03/17 | Mon 10/12/18
1479 | 870080 | (IETF) Improved Extensible Authentication Protocol Method for 3GPP Mobile Network Authentication and Key Agreement (EAP-AKA') (draft-ietf-emu-rfc5448bis) | 5GS_Ph1-CT | 3 | Rel-15 | C4-IETF | Fri 03/03/17 | Thu 14/12/17 | 80% | [6 empty] | 87 | 44 |  |  | Fri 03/03/17 | Mon 10/12/18
1480 | 750029 | Study on CT6 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C6 | Fri 03/03/17 | Thu 14/12/17 | 100% | CP-183243 |  | Amandeep Virk from Qualcomm |  | 5/6/17: 0%->10¦11/9/17: 10%->60¦15/12/17: 60%->85¦22/3/18: 85%->95¦7/6/18: 95%->100 |  | 75 | 38 |  |  | Fri 03/03/17 | Thu 07/06/18
1481 | 790043 | CT6 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C6 | Fri 16/03/18 | Thu 14/06/18 | 100% | CP-183243 |  | Landais, Bruno (Nokia) | Bruno.Landais at nokia.com | 5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦16/3/18: 0%->20¦7/6/18: 20%->90¦10/9/18: 90%->95. 10/9/18: 95->100 as per CT81 discussions¦10/12/18: 100%->95¦11/12/18: 95%->100 | 23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303 | 75 | 38 |  |  | Fri 03/03/17 | Tue 11/12/18
1482 | 800081 | UE Conformance Test Aspects – 5G System Non-3GPP Access | 5GS_Ph1-CT_n3GPPA-UEConTest | 2 | Rel-15 | R5 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-181032 |  | Motorola |  | tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100 |  | 80 |  |  |  | Wed 27/06/18 | Thu 26/03/20
1483 | 760029 | IMS impact due to 5GS IP-CAN | 5GS_Ph1-IMSo5G | 2 | Rel-15 | ct | Mon 04/09/17 | Fri 15/06/18 | 100% | CP-180094 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 8/9/17: WID:CP-171103->CP-172033¦FCD: 12/17->06/18¦19/3/18: WID:CP-172033->CP-180094 |  | 76 | 39 |  |  | Fri 02/06/17 | Mon 19/03/18
1484 | 770017 | CT1 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C1 | Mon 04/09/17 | Fri 15/06/18 | 100% | CP-180094 |  | Song Yue, China Mobile | songyue@chinamobile.com | 14/9/17: 0%->10¦15/12/17: 10%->65¦rapporteur changed¦20/3/18: 65%->75¦7/6/18: 75%->95¦10/9/18: 95%->100 | 24.229; 24.167 | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/09/18
1485 | 770018 | CT3 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C3 | Mon 04/09/17 | Fri 15/06/18 | 100% | CP-180094 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->80¦10/9/18: 80%->100 | 29.213; 29.214 | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/09/18
1486 | 770019 | CT4 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C4 | Mon 04/09/17 | Fri 15/06/18 | 100% | CP-180094 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 23.008; 29.228; 29.229; 29.328; 29.329; 23.003 | 77 | 39 |  |  | Fri 03/03/17 | Thu 07/06/18
1487 | 780034 | Service Based Interface for 5G Charging | 5GS_Ph1-SBI_CH | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170951 |  | Chen, Shan, Huawei | chenshan@huawei.com | 16/3/18: 0%->15¦7/6/18: 15%->55¦7/6/18: FCD:06/18->09/18¦10/9/18: 55%->100 | 32.240; 32.298 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1488 | 780035 | Data Charging in 5G System Architecture Phase 1 | 5GS_Ph1-DCH | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170952 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 16/3/18: 0%->10¦7/6/18: 10%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100 | 32.24 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1489 | 810028 | SMS Charging in 5G System Architecture Phase 1 | 5GS_Ph1-SMSCH | 2 | Rel-15 | S5 | Thu 06/09/18 | Fri 14/12/18 | 100% | SP-180824 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/12/18: 0%->100 | 32.240; 32.274; 32.290; 32.291; 32.299; 32.298 | 81 |  |  |  | Thu 06/09/18 | Fri 07/12/18
1490 | 800040 | Charging for IMS over 5G System Architecture Phase 1 | 5GS_Ph1_IMSCH | 2 | Rel-15 | S5 | Mon 07/05/18 | Fri 15/06/18 | 100% | SP-180391 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.240; 32.260; 32.299; 32.298 | 80 |  |  |  | Wed 06/06/18 | Thu 07/06/18
1491 | 800041 | UE Conformance Test Aspects - CT6 aspects of 5G System | 5GS_Ph1_UEConTest | 2 | Rel-15 | C6 | Thu 07/06/18 | Fri 14/06/19 | 98% | CP-183242 |  | Azem, Dania (COMPRION GmbH) | DAzem@comprion.com | 10/12/18: 0%->5¦10/12/18: 5%->¦10/12/18: WID:CP-181187->CP-183242; 31/5/19: 5%->10; 6/12/19: 10%->60; 26/3/20: 60%->85; 26/6/20: 85%->95; 13/9/20: 95%->98 | 31.121 ; 31.124 | 80 |  |  |  | Thu 02/03/17 | Sun 13/09/20
1492 | 750035 | EPC enhancements to support 5G New Radio via Dual Connectivity | EDCE5 | 1 | Rel-15 |  | Thu 02/03/17 | Thu 15/03/18 | 100% | SP-170583 |  | Chris Pudney, Vodafone Group | Chris Pudney, Vodafone Group | 9/6/17: WID:SP-170058->SP-170583 |  | 75 | 38 |  |  | Thu 02/03/17 | Fri 09/06/17
1493 | 750012 | SA2 aspects of EDCE5 | EDCE5 | 2 | Rel-15 | S2 | Thu 02/03/17 | Thu 14/09/17 | 100% | SP-170583 |  | Chris Pudney, Vodafone Group |  | 7/6/17: 0%->55¦11/9/17: 55%->90¦15/12/17: 90%->100 |  | 75 | 38 |  |  | Thu 02/03/17 | Fri 15/12/17
1494 | 750036 | SA3 aspects of EDCE5 | EDCE5 | 2 | Rel-15 | S3 | Thu 02/03/17 | Thu 14/09/17 | 100% | SP-170233 |  | Adrian Escott, Qualcomm Incorporated |  | 7/6/17: 0%->60¦11/9/17: 60%->70¦15/12/17: 70%->100 |  | 75 | 38 |  |  | Thu 02/03/17 | Fri 15/12/17
1495 | 760001 | CT aspects of EDCE5 | EDCE5-CT | 2 | Rel-15 | ct | Mon 05/06/17 | Thu 14/12/17 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 18/12/17: WID:CP-171045->CP-173038 |  | 76 | 39 |  |  | Mon 05/06/17 | Mon 18/12/17
1496 | 760068 | CT1 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C1 | Mon 05/06/17 | Thu 14/12/17 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 14/9/17: 0%->65¦15/12/17: 65%->100 | 24.301; 27.007 | 76 | 39 |  |  | Mon 05/06/17 | Fri 15/12/17
1497 | 760069 | CT3 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C3 | Mon 05/06/17 | Thu 14/12/17 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com |  | 29.212; 29.213; 29.214; 29.215; 29.201 | 76 | 39 |  |  | Mon 05/06/17 | NA
1498 | 760070 | CT4 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C4 | Mon 05/06/17 | Thu 14/12/17 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 11/9/17: 0%->50¦15/12/17: 50%->100 | 23.008; 29.272; 29.230; 29.002; 29.305; 29.274 | 76 | 39 |  |  | Mon 05/06/17 | Fri 15/12/17
1499 | 760062 | Charging aspects of EDCE5: PS Charging enhancements to support 5G New Radio via Dual Connectivity | EDCE5-CH | 2 | Rel-15 | S5 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170487 |  | Törnkvist, Robert, Ericsson | robert.tornkvist(at)ericsson.com | 15/12/17: 0%->20¦16/3/18: 20%->100 | 32.251; 32.298; 32.299 | 76 | 39 |  |  | Mon 05/06/17 | Fri 16/03/18
1500 | 750067 | New Radio Access Technology | NR_newRAT | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/06/19 | 99% | RP-190213 |  | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦30/6/17: 38.425 added;¦14/9/17: WID:RP-170855->RP-171485¦15/12/17: added: 38.305¦38.113¦37.863-04-01¦37.863-03-01¦37.863-02-01¦38.820-04-01¦38.820-03-01¦38.820-02-01¦15/12/17: 37.32... | 38.425; 38.424; 38.423; 38.422; 38.421; 38.420; 38.305; 38.113; 37.863-04-01; 37.863-03-01; 37.863-02-01; 38.820-04-01; 38.820-03-01; 38.820-02-01; 37.324; 37.872; 37.864-11-22; 37.866-00-02 | 75 | 38 |  |  | Tue 21/03/17 | Tue 26/03/19
1501 | 750167 | Core part: New Radio Access Technology | NR_newRAT-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-190213 | RP-181466 | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT¦19/6/17: Compl:0%->22%19/6/17: WID: RP-170855->RP-171485¦30/6/17 & 12/6/17: impacted specs added19/9/17: Compl:22%->50%19/9/17: WID: RP-171485->RP-172115¦15/12/17: added: 38.818¦37.865-01-01¦37.834-01-01¦37....; 2... | 37.340;37.834-01-01;37.863-05-01;37.864-41-21;37.865-01-01;38.101;38.104;38.12?;38.201/2;38.211/2;38.213to215;38.300;38.304to307;38.321to323;38.331;38.401;38.410to414;38.455;38.470to475;38.815;38.817-01-02;38.818; 38.113; 29.413; 37.864-11-22; 38.415; 38. | 75 | 38 |  |  | Tue 21/03/17 | Wed 26/06/19
1502 | 750267 | Perf. part: New Radio Access Technology | NR_newRAT-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 14/06/19 | 100% | RP-191971 |  | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦19/6/17: WID: RP-170855->RP-171485¦12/7/17: 38.133 added;¦12/7/17: 38.141 added;¦19/9/17: WID: RP-171485->RP-172115¦15/12/17: 38.101-4 added¦8/1/18: WID: RP-172115->RP-172834¦27/3/18: W...; 8/... | 38.133; 38.141; 38.101-4; 38.171 | 75 | 38 |  |  | Tue 21/03/17 | Tue 14/01/20
1503 | 750072 | LTE connectivity to 5G-CN | LTE_5GCN_connect | 1 | Rel-15 | R2 | Wed 15/03/17 | Thu 20/12/18 | 100% | RP-171432 |  | Huawei |  | no Perf. part¦14/9/17: WID:RP-170840->RP-171432 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1504 | 750172 | Core part: LTE connectivity to 5G-CN | LTE_5GCN_connect-Core | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-180860 | RP-180862 | Huawei |  | no Perf. Part19/6/17: Compl:0%->5%19/6/17: WID: RP-170840->RP-17143219/9/17: Compl:5%->10%¦8/1/18: Compl:10%->20%¦27/3/18: Compl:20%->30%¦ ¦27/6/18: Compl:30%->99%¦7/3/19: 99%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 07/03/19
1505 | 761205 | Perf. part: LTE connectivity to 5G-CN | LTE_5GCN_connect-Perf | 2 | Rel-15 | R4 | Tue 20/06/17 | Thu 20/12/18 | 100% | RP-180860 | RP-180862 | Huawei |  | 16/1/19: 0%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1506 | 760087 | UE Conformance Test Aspects - 5G system with NR and LTE | 5GS_NR_LTE-UEConTest | 1 | Rel-15 | R5 | Thu 15/06/17 | Fri 11/06/21 | 86% | RP-210423 |  | Ericsson |  | ¦19/9/17: Compl:0%->2%¦15/12/17: impacted specs add¦15/12/17: 38.508-2 added;¦ ;; 8/10/19: WID:RP-181206->RP-192123; 8/10/19: 34.229-5 added;; 24/4/20: FCD:14/12/2018->12/20; 24/4/20: 15%->69; 8/10/20: 69%->79; 8/10/20: FCD:15/12/2020->12/20; 7/4/21: W... | 38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2; 34.229-5 | 76 | 39 |  |  | Fri 16/06/17 | Thu 08/04/21
1507 | 0 | Release 15 Features on V2X | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1508 | 750003 | Enhancement of 3GPP support for V2X scenarios | eV2X | 1 | Rel-15 |  | Thu 09/06/16 | Wed 22/03/17 | 100% | SP-170158 |  | Chun, SungDuck, LG Electronics | sungduck.chun@lge.com |  |  | 75 | 38 |  |  | Thu 02/03/17 | NA
1509 | 720003 | Study on Enhancement of 3GPP support for V2X services | FS_eV2X | 2 | Rel-15 | S1 | Thu 09/06/16 | Thu 15/12/16 | 100% | SP-160370 |  | LG Electronics, SungDuck Chun | sungduck.chun@lge.com | 19/9/16: 30%->70¦6/10/16: 22.886 added¦1/12/16: 70%->95¦2/3/17: 95%->100 | 22.886 | 72 | 37 |  |  | Thu 09/06/16 | Thu 02/03/17
1510 | 750002 | Stage 1 of Enhancement of 3GPP support for V2X scenarios | eV2X | 2 | Rel-15 | S1 | Mon 09/01/17 | Wed 22/03/17 | 100% | SP-170158 |  | Chun, SungDuck, LG Electronics | sungduck.chun@lge.com | 7/6/17: 90%->100 | 22.186 | 75 | 38 |  |  | Thu 02/03/17 | Wed 07/06/17
1511 | 750075 | V2X new band combinations for LTE | LTE_V2X_CA_bands | 1 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-170752 |  | LG Electronics |  | no Perf. part¦12/7/17: 36.787 added; | 36.787 | 75 | 38 |  |  | Tue 21/03/17 | Wed 12/07/17
1512 | 750175 | Core part: V2X new band combinations for LTE | LTE_V2X_CA_bands-Core | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-180328 |  | LG Electronics |  | no Perf. part¦19/6/17: Compl:0%->20%¦19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->50%¦27/3/18: Compl:50%->70%; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1513 | 750062 | Enhancements on LTE-based V2X Services | LTE_eV2X | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/12/18 | 99% | RP-171069 |  | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦14/9/17: WID:RP-170798->RP-171069 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1514 | 750162 | Core part: V2X phase 2 based on LTE | LTE_eV2X-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-171740 | RP-180858 | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦19/6/17: Compl:0%->15%¦ 30/6/17: 36.788 added;¦19/9/17: Compl:15%->30% 8/1/18: Compl:30%->55%27/3/18: Compl:55%->75% | 36.788 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1515 | 750262 | Perf. Part: V2X phase 2 based on LTE | LTE_eV2X-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-182549 |  | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #7519/6/17: WID: RP-170798->RP-17106919/9/17: WID: RP-171069->RP-171740¦27/6/18: Compl:0%->5%¦16/1/19: 5%->100¦16/1/19: WID:RP-171740->RP-182549 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1516 | 700045 | Study on security aspects for LTE support of V2X services | FS_V2XLTE_ARC | 1 | Rel-15 | S3 | Mon 07/09/15 | Thu 15/06/17 | 100% | SP-150852 |  | Huawei, Marcus Wong | mwong@huawei.com | 11/12/15: WID:SP-150715->SP-150743. 28/01/16: typo on name corrected, WD corrected (was SP-150743)¦7/3/16: 0%->10¦19/9/16: 10%->65¦1/12/16: 65%->85¦6/3/17: 85%->90¦21/3/17: FCD shifted, moved from Rel-14¦21/3/17: FCD:09/16->06/17¦8/8/18: 90%->100 | 33.885 | 70 | 36 |  |  | Mon 07/12/15 | Wed 08/08/18
1517 | 0 | Release 15 Features on Ultra/Highly Reliable Low Latency Communication | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1518 | 770037 | EPC support for E-UTRAN Ultra Reliable Low Latency Communication | EPS_URLLC | 1 | Rel-15 | S2 | Fri 08/09/17 | Thu 15/03/18 | 100% | SP-170811 |  | Chris PUDNEY | chris dot pudney at vodafone dot com | 15/12/17: WID:SP-170797->SP-170811¦15/12/17: 0%->15¦20/3/18: 15%->100 | 23.401; 23.214; 23.203 | 77 | 39 |  |  | Fri 08/09/17 | Tue 20/03/18
1519 | 750061 | Highly Reliable Low Latency Communication for LTE | LTE_HRLLC | 1 | Rel-15 | R1 | Wed 15/03/17 | Sat 15/12/18 | 46% | RP-171489 |  | Ericsson |  | 14/9/17: WID:RP-170796->RP-171489 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1520 | 750161 | Core part: Highly Reliable Low Latency Communication for LTE | LTE_HRLLC-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-181259 | RP-180693 | Ericsson |  | ¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: Compl:0%->10%¦8/1/18: WID: RP-171489->RP-172845¦27/3/18: Compl:10%->30%¦27/6/18: Compl:30%->99%¦27/6/18: CD:Fri 15 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1521 | 750261 | Perf. part: Highly Reliable Low Latency Communication for LTE | LTE_HRLLC-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Sat 15/12/18 | 0% | RP-181259 |  | Ericsson |  | ¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: WID: RP-171489->RP-172845¦27/6/18: WID: RP-172845->RP-181259 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1522 | 0 | Release 15 Features on improvements of Mission Critical (MC) | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1523 | 720057 | Study on MC system migration and interconnect between MCPTT systems | FS_MCSMI | 1 | Rel-15 | S6 | Mon 13/06/16 | Mon 12/06/17 | 100% | SP-160880 |  | Chater-Lea, David |  | 28/7/16: 23.781 added¦19/9/16: WID:SP-160340->SP-160526¦FCD: 09/16->12/16¦19/9/16: 0%->40¦1/12/16: WID:SP-160526->SP-160880¦1/12/16: 40%->48¦9/12/16: FCD:12/16->06/17, Rel-14->Rel-15¦3/3/17: 48%->60¦7/6/17: 60%->100 | New 23.781 | 72 | 37 |  |  | Fri 16/09/16 | Wed 07/06/17
1524 | 720058 | Study on MC Communication Interworking between LTE and non-LTE Systems | FS_MCCI | 1 | Rel-15 | S6 | Mon 13/06/16 | Mon 12/06/17 | 100% | SP-160881 |  | Monnes, Peter (Harris Corp.) |  | 28/7/16: 23.782 added¦19/9/16: WID:SP-160341->SP-160527¦19/9/16: 0%->20¦1/12/16: WID:SP-160527->SP-160881¦1/12/16: 20%->22¦9/12/16: FCD:12/16->06/17, Rel-14->Rel-15¦3/3/17: 22%->50¦7/6/17: 50%->90¦11/9/17: 90%->100 | New 23.782 | 72 | 37 |  |  | Mon 13/06/16 | Mon 11/09/17
1525 | 720083 | Study on MC Security Enhancements | FS_MC_Sec | 1 | Rel-15 | S3 | Fri 17/06/16 | Thu 15/03/18 | 100% | SP-170416 |  | Haigh, Peter, CESG | peter.haigh@cesg.gsi.gov.uk | 28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17 | 33.xxx; 33.280; 39.880 | 72 | 37 |  |  | Fri 17/06/16 | Fri 16/03/18
1526 | 760050 | MC Communication Interworking between LTE and non-LTE Systems (Stage 3 in Rel16) | MCCI | 1 | Rel-15 | S6 | Mon 05/06/17 | Thu 14/12/17 | 100% | SP-170578 |  | Monnes, Peter, Harris Corporation | pmonnes at harris dot com | 11/9/17: 0%->40¦15/12/17: 40%->87¦16/3/18: 87%->100. 10/9/18: moved from Rel-15 since too late for St 3 in Rel-15 as said in CT81. 12/9/18: moved back to Rel-15, while St.3 will be Rel-16 | New 23.283; 23.280; 23.379; 23.282 | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
1527 | 780002 | Removal of 'over LTE' limitation from Mission Critical Specifications | MCOver | 1 | Rel-15 | S1 | Wed 15/11/17 | Fri 15/12/17 | 100% | SP-180354 |  | Kees Verweij ;The Police of the Netherlands | KeesdotVerweijatPolitiedotNL | 7/6/18: WID:SP-170986->SP-180354 | 22.179; 22.280; 22.281; 22.282; 22.468 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1528 | 750021 | Enhancements to MCPTT functional architecture and information flows | enhMCPTT | 1 | Rel-15 |  | Fri 03/03/17 | Fri 15/06/18 | 100% | SP-170248 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 21/3/17: impacted TS/TR added¦7/6/17: 0%->25 | 23.280 + 23.379 | 75 | 38 |  |  | Fri 03/03/17 | Wed 07/06/17
1529 | 770008 | Stage 2 of enhMCPTT | enhMCPTT | 2 | Rel-15 | S6 | Fri 03/03/17 | Thu 14/12/17 | 100% | SP-170248 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 21/3/17: impacted TS/TR added¦7/6/17: 0%->25¦11/9/17: 25%->45¦15/12/17: 45%->100 | 23.280 + 23.379 | 75 | 38 |  |  | Fri 03/03/17 | Fri 15/12/17
1530 | 770009 | Stage 3 of enhMCPTT | enhMCPTT-CT | 2 | Rel-15 | C1 | Fri 08/09/17 | Fri 15/06/18 | 100% | CP-172030 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 15/12/17: 0%->10¦7/6/18: 10%->20¦10/9/18: 20%->80¦7/12/18: 80%->85¦10/12/18: 85%->100 | 24.379; 24.380; 24.481; 24.482; 24.483; 24.484 | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/12/18
1531 | 750022 | Enhancements to MC Data Functional architecture and information flows | eMCData | 1 | Rel-15 |  | Fri 03/03/17 | Fri 15/06/18 | 100% | SP-170462 |  | David Freeman, Home Office | david@dnf-consulting.co.uk | 21/3/17: impacted TS/TR added¦7/6/17: 0%->10¦8/6/17: WID:SP-170249->SP-170462 | 23.280 + 23.282 | 75 | 38 |  |  | Fri 03/03/17 | Thu 08/06/17
1532 | 770010 | Stage 2 of eMCData | eMCData | 2 | Rel-15 | S6 | Fri 03/03/17 | Thu 14/12/17 | 100% | SP-170462 |  | David Freeman, Home Office | david@dnf-consulting.co.uk | 21/3/17: impacted TS/TR added¦7/6/17: 0%->10¦8/6/17: WID:SP-170249->SP-170462¦11/9/17: 10%->15¦15/12/17: 15%->100 | 23.280 + 23.282 | 75 | 38 |  |  | Fri 03/03/17 | Fri 15/12/17
1533 | 770011 | Stage 3 of eMCData | eMCData-CT | 2 | Rel-15 | C1 | Fri 08/09/17 | Fri 15/06/18 | 100% | CP-172146 |  | HASON, Baruh | Baruh.Hason@motorolasolutions.com | 20/3/18: 0%->30¦7/6/18: 30%->85¦10/12/18: 85%->100 | 24.282; 24.582; 24.481; 24.483; 24.484 | 77 | 39 |  |  | Fri 03/03/17 | Mon 10/12/18
1534 | 760048 | Enhancements to MC Video Functional architecture and information flows | eMCVideo | 1 | Rel-15 |  | Mon 05/06/17 | Fri 15/06/18 | 100% | SP-170401 |  | Niranth Amogh, Huawei Telecommunications (India | namogh@huawei.com | 7/6/17: 0%->10 | 23.280; 23.281 | 76 | 39 |  |  | Sat 03/06/17 | Wed 07/06/17
1535 | 770012 | Stage 2 of eMCVideo | eMCVideo | 2 | Rel-15 | S6 | Mon 05/06/17 | Thu 14/12/17 | 100% | SP-170401 |  | Niranth Amogh, Huawei Telecommunications (India | namogh@huawei.com | 7/6/17: 0%->10¦11/9/17: 10%->60¦15/12/17: 60%->100 | 23.280; 23.281 | 76 | 39 |  |  | Sat 03/06/17 | Fri 15/12/17
1536 | 770013 | Stage 3 of eMCVideo | eMCVideo-CT | 2 | Rel-15 | ct | Fri 08/09/17 | Fri 15/06/18 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 7/6/18: WID:CP-172032->CP-181084 |  | 77 | 39 |  |  | Sat 03/06/17 | Thu 07/06/18
1537 | 770014 | CT1 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C1 | Fri 08/09/17 | Fri 15/06/18 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 20/3/18: 0%->25¦7/6/18: 25%->100¦12/6/18: 100%->99¦10/9/18: 99%->100 | 24.281; 24.581; 24.481; 24.483; 24.484 | 77 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
1538 | 770015 | CT3 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C3 | Tue 05/12/17 | Fri 15/06/18 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 10/9/18: 0%->100 | 29.165; 29.213; 29.214 | 77 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
1539 | 770016 | CT6 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C6 | Tue 05/12/17 | Fri 15/06/18 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 10/9/18: 0%->100 | 31.102; 31.103 | 77 | 39 |  |  | Sat 03/06/17 | Mon 10/09/18
1540 | 760067 | MC Security Enhancements | eMCSec | 1 | Rel-15 | S3 | Mon 05/06/17 | Fri 15/06/18 | 100% | SP-170415 |  | Haigh, Peter, NCSC |  | 15/12/17: 0%->80¦15/12/17: FCD:12/17->03/18¦21/12/17: FCD:03/18->05/18. Exception in SP-171056¦16/3/18: 80%->90¦16/3/18: FCD:05/18->06/18¦7/6/18: 90%->100 | 33.18 | 76 | 39 |  |  | Wed 07/06/17 | Thu 07/06/18
1541 | 750023 | MBMS usage for MC communication services | MBMS_Mcservices | 1 | Rel-15 | S6 | Fri 03/03/17 | Thu 07/06/18 | 100% | SP-170686 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | 21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100. Problem with % complete when set as Parent Feature. Has to be left as independent item… | 23.280 + 23.281 + 23.282 + 23.379 | 75 | 38 |  |  | Fri 03/03/17 | Fri 16/03/18
1542 | 800043 | Stage 2 for MBMS_Mcservices | MBMS_Mcservices | 2 | Rel-15 | S6 | Fri 03/03/17 | Fri 15/12/17 | 100% | SP-170686 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | 21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100 | 23.280 + 23.281 + 23.282 + 23.379 | 75 | 38 |  |  | Fri 03/03/17 | Fri 16/03/18
1543 | 800017 | Stage 3 for MBMS_Mcservices | MBMS_Mcservices | 2 | Rel-15 | C1 | Mon 09/04/18 | Thu 07/06/18 | 100% | CP-183105 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 12/6/18: 10%->30¦10/9/18: 30%->70¦7/12/18: 70%->100 | 24.281; 24.282; 24.379; 24.380; 24.581; 24.380 | 80 | 41 |  |  | Wed 06/06/18 | Mon 10/12/18
1544 | 760049 | MC system migration and interconnection | MCSMI | 1 | Rel-15 | S6 | Mon 05/06/17 | Thu 14/12/17 | 100% | SP-170577 |  | Chater-Lea, David; Motorola Solutions | david.chater-lea@motorolasolutions.com | 12/7/17: WID:SP-170402->SP-170577¦11/9/17: 0%->20¦15/12/17: 20%->80¦16/3/18: 80%->100 | 23.280; 23.379; 23.281; 23.282; 24.885 | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
1545 | 770007 | Protocol enhancements for Mission Critical Services | MCProtoc15 | 1 | Rel-15 | C1 | Fri 08/09/17 | Fri 15/06/18 | 100% | CP-172145 |  | Jörgen Axell |  | 14/9/17: 0%->15¦15/12/17: 15%->40¦20/3/18: 40%->70¦7/6/18: 70%->100 |  | 77 | 39 |  |  | Fri 08/09/17 | Thu 07/06/18
1546 | 890042 | UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo | MCenhUEConTest | 1 | Rel-15 | R5 | Thu 17/09/20 | Fri 17/12/21 | 16% | RP-201487 |  | NIST |  | tested: REL-15 SA/CT WIs enhMCPTT, eMCVideo, eMCData, MBMS_Mcservices, MCSMI, MCProtoc15, MCOver ; 8/4/21: 0%->16 |  | 89 | 45 |  |  | Fri 25/09/20 | Thu 08/04/21
1547 | 0 | Release 15 Features on MTC-IoT | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1548 | 730050 | Battery Efficient Security for very low Throughput MTC Devices | BEST_MTC_Sec | 1 | Rel-15 | S3 | Mon 19/09/16 | Thu 15/03/18 | 100% | SP-160569 |  | Evans, Tim, VODAFONE Group Plc. |  | 6/10/16: 33.163 added 6/3/17: FCD:12/16->09/17¦6/3/17: 0%->20. Moved from Rel-14.¦7/6/17: 20%->95¦15/12/17: FCD:09/17->03/18¦16/3/18: 95%->100 | 33.401, 43.020, 33.220; 33.163 | 73 | 37 |  |  | Mon 19/09/16 | Fri 16/03/18
1549 | 780016 | AT Commands for CIoT-Ext | AT_CIoT-Ext | 1 | Rel-15 | C1 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-173083 |  | Bakker, John-Luc (Blackberry) | jbakker@blackberry.com | 20/3/18: 0%->20¦7/6/18: 20%->100 | 27.007 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1550 | 750059 | Even further enhanced MTC for LTE | LTE_eMTC4 | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 11/06/21 | 86% | RP-171427 |  | Ericsson |  | WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦14/9/17: WID:RP-170732->RP-171427 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1551 | 750159 | Core part: Even further enhanced MTC for LTE | LTE_eMTC4-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-172811 | RP-181213 | Ericsson |  | WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦19/6/17: Compl:0%- 19/9/ 8/1 2 ;¦16/1/19: 97%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1552 | 750259 | Perf. part: Even further enhanced MTC for LTE | LTE_eMTC4-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-172811 |  | Ericsson |  | note: RAN #75 approved WID RP-170732 with working agreement19/6/17: WID: RP-170732->RP-171427¦8/1/18: WID: RP-171427->RP-172811¦27/6/18: Compl:0%->50%¦16/1/19: 50%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1553 | 860032 | UE Conformance Test Aspects - Even further enhanced MTC for LTE | LTE_eMTC4-UEConTest | 2 | Rel-15 | R5 | Mon 16/12/19 | Fri 11/06/21 | 54% | RP-192894 |  | Ericsson |  | affects: LTE. tested: REL-15 WI LTE_eMTC4-Core; 8/10/20: 0%->47; 8/4/21: 47%->54; 8/4/21: FCD:15/12/2020->06/21 |  | 86 | 44 |  |  | Tue 14/01/20 | Thu 08/04/21
1554 | 750066 | Further NB-IoT enhancements | NB_IOTenh2 | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 11/06/21 | 92% | RP-182389 |  | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦14/9/17: WID:RP-170852->RP-171428 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1555 | 750166 | Core part: Further NB-IoT enhancements | NB_IOTenh2-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 95% | RP-182389 | RP-180851 | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1556 | 750266 | Perf. part: Further NB-IoT enhancements | NB_IOTenh2-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 14/12/18 | 100% | RP-182389 |  | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦8/1 ;¦26/3/19: 30%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 26/03/19
1557 | 860031 | UE Conformance Test Aspects - Further NB-IoT enhancements | NB_IOTenh2-UEConTest | 2 | Rel-15 | R5 | Thu 12/12/19 | Fri 11/06/21 | 79% |  |  |  |  | 8/10/20: 0%->25; 8/10/20: FCD:11/12/2020->12/20; 8/4/21: 25%->79; 8/4/21: FCD:11/12/2020->06/21 |  | 86 | 44 |  |  | Tue 18/02/20 | Thu 08/04/21
1558 | 0 | Release 15 Features related to WLAN | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1559 | 750010 | Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery | ProSe_WLAN_DD | 1 | Rel-15 |  | Tue 15/11/16 | Thu 15/03/18 | 100% | SP-160957 |  | Intel Corporation; Ana Lucia Pinheiro | ana.lucia.a.pinheiro@intel.com | 1/12/16: 0%->100 | 22.278 | 74 | 38 |  |  | Thu 01/12/16 | Thu 01/12/16
1560 | 740003 | Stage 1 of ProSe_WLAN_DD | ProSe_WLAN_DD | 2 | Rel-15 | S1 | Tue 15/11/16 | Thu 15/12/16 | 100% | SP-160957 |  | Intel Corporation; Ana Lucia Pinheiro | ana.lucia.a.pinheiro@intel.com | 1/12/16: 0%->100 | 22.278 | 74 | 38 |  |  | Thu 01/12/16 | Thu 01/12/16
1561 | 750011 | Stage 2 of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage2 | 2 | Rel-15 | S2 | Thu 02/03/17 | Thu 15/06/17 | 100% | SP-170057 |  | Intel, Sašo Stojanovski | saso.stojanovski@intel.com | 6/3/17: 0%->55¦7/6/17: 55%->100 |  | 75 | 38 |  |  | Thu 02/03/17 | Wed 07/06/17
1562 | 760026 | Stage 3 of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 2 | Rel-15 | ct | Fri 02/06/17 | Wed 06/12/17 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 18/12/17: WID:CP-171102->CP-173084 |  | 76 | 39 |  |  | Fri 02/06/17 | Mon 18/12/17
1563 | 760027 | CT1 aspects of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 3 | Rel-15 | C1 | Fri 02/06/17 | Wed 06/12/17 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 14/9/17: 0%->60¦15/12/17: 60%->100 | 24.334 | 76 | 39 |  |  | Fri 02/06/17 | Fri 15/12/17
1564 | 760028 | CT4 aspects of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 3 | Rel-15 | C4 | Fri 02/06/17 | Wed 06/12/17 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 15/12/17: 0%->100 | 29.345; 29.230; 23.008 | 76 | 39 |  |  | Fri 02/06/17 | Fri 15/12/17
1565 | 780045 | Charging of ProSe_WLAN_DD | ProSe_WLAN_DD-CH | 2 | Rel-15 | S5 | Fri 15/12/17 | Thu 15/03/18 | 100% | SP-170947 |  | Yizhi Yao, Intel Corporation | yizhi.yao@intel.com | 15/12/17: 0%->40¦16/3/18: 40%->100 | 32.277; 32.298; 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Fri 16/03/18
1566 | 760020 | Complementary Features for Voice services over WLAN | VoWLAN | 1 | Rel-15 |  | Mon 13/06/16 | Thu 14/06/18 | 100% | SP-170378 | [5 empty] | 76 | 39 |  |  | Fri 02/06/17 | NA
1567 | 720082 | Study on Complementary Features for Voice services over WLAN | FS_VoWLAN | 2 | Rel-15 | S2 | Mon 13/06/16 | Wed 15/03/17 | 100% | SP-160506 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com | 28/7/16: 23.751 added¦19/9/16: 0%->10., 7/12/16: moved from Rel-14, according to SP-160806¦6/3/17: 10%->80¦7/6/17: 80%->100 | 23.751 | 72 | 37 |  |  | Fri 17/06/16 | Wed 07/06/17
1568 | 760021 | Stage 2 of VoWLAN | VoWLAN | 2 | Rel-15 | S2 | Tue 09/05/17 | Thu 08/06/17 | 100% | SP-170378 |  | Drevon Nicolas, Nokia | nicolas.drevon@nokia.com | 15/12/17: 0%->100 | 23.402 | 76 | 39 |  |  | Fri 02/06/17 | Fri 15/12/17
1569 | 760022 | CT aspects of VoWLAN | VoWLAN-CT | 2 | Rel-15 | ct | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: WID:CP-171101->CP-181083 |  | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1570 | 760023 | CT1 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C1 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 14/9/17: 0%->70¦15/12/17: 70%->100 | 24.302 ; 24.312 ; 24.244 | 76 | 39 |  |  | Fri 02/06/17 | Fri 15/12/17
1571 | 760024 | CT4 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C4 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: 0%->100 | 29.274 | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1572 | 760025 | CT6 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C6 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: 0%->100 | 31.102 | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1573 | 0 | Release 15 Features on Virtual Reality (VR) | - | 1 | Rel-15 |  | Tue 01/03/16 | Tue 01/03/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1574 | 710014 | Study on Virtual Reality | FS_VR | 1 | Rel-15 | S4 | Tue 01/03/16 | Tue 12/09/17 | 100% | SP-160084 |  | Gilles TENIOU, Orange | gilles.teniou@orange.com | 11/6/16: 0%->10¦19/9/16: 10%->40, FCD: 12/16->03/17¦1/12/16: FCD:03/17->06/17¦1/12/16: 40%->35¦14/12/16: 35%->45¦14/12/16: FCD:06/17->09/17¦6/3/17: 45%->55¦7/6/17: 55%->70¦11/9/17: 70%->100 | 26.918 | 71 | 36 |  |  | Tue 01/03/16 | Mon 11/09/17
1575 | 770030 | Study on 3GPP codecs for VR audio | FS_CODVRA | 1 | Rel-15 | S4 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170617 |  | Toftgård, Tomas, Ericsson | tomas.toftgard@ericsson.com | 15/12/17: 0%->100¦15/12/17: FCD:09/17->12/17 | 26.918 | 77 | 39 |  |  | Fri 08/09/17 | Fri 15/12/17
1576 | 770022 | Test Methodologies for the Evaluation of Perceived Listening Quality in Immersive Audio Systems | LiQuImAS | 1 | Rel-15 | S4 | Fri 08/09/17 | Fri 14/09/18 | 100% | SP-170609 |  | Schevciw, Andre – Qualcomm Incorporated | aschevci@qti.qualcomm.com | 15/12/17: added: 26.861¦26.261¦26.260¦26.259¦15/12/17: 0%->15¦16/3/18: 15%->20¦7/6/18: 20%->35¦7/6/18: FCD:06/18->09/18¦10/9/18: 35%->100 | New; 26.861; 26.261; 26.260; 26.259 | 77 | 39 |  |  | Fri 08/09/17 | Mon 10/09/18
1577 | 770023 | Addition of HDR to TV Video Profiles | HDR | 1 | Rel-15 | S4 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170610 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 0%->100 | 26.116; 26.346; 26.234; 26.247; 26.244 | 77 | 39 |  |  | Fri 08/09/17 | Fri 15/12/17
1578 | 770025 | Virtual Reality Profiles for Streaming Media | VRStream | 1 | Rel-15 | S4 | Fri 08/09/17 | Fri 14/09/18 | 100% | SP-180893 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 26.118 added;¦15/12/17: 0%->25¦16/3/18: 25%->40¦7/6/18: 40%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170612->SP-180893 | 26.118; 26.818; 26.247; 26.346; 26.234 | 77 | 39 |  |  | Fri 08/09/17 | Tue 02/10/18
1579 | 0 | Release 15 other Features | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1580 | 790016 | Forward compatibility for 3GPP Diameter Charging Applications | FWDCA | 1 | Rel-15 | S5 | Thu 15/03/18 | Fri 15/06/18 | 100% | SP-180076 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.251; 32.277; 32.299 | 79 | 40 |  |  | Thu 15/03/18 | Thu 07/06/18
1581 | 790017 | Diameter Overload Control Mechanisms for Charging | DOCME_CH | 1 | Rel-15 | S5 | Thu 15/03/18 | Fri 14/09/18 | 100% | SP-180077 |  | Törnkvist, Robert, Ericsson | robert(dot)tornkvist(at)Ericsson(dot)com | 7/6/18: 0%->10¦7/6/18: FCD:06/18->09/18¦10/9/18: 10%->100 | 32.299 | 79 | 40 |  |  | Thu 15/03/18 | Mon 10/09/18
1582 | 790018 | Charging aspects of WLAN access in EPC | WAEPC_CH | 1 | Rel-15 | S5 | Thu 15/03/18 | Fri 15/06/18 | 100% | SP-180078 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.251; 32.260; 32.299; 32.298 | 79 | 40 |  |  | Thu 15/03/18 | Thu 07/06/18
1583 | 790020 | FEC and ROHC Activation for GCSE over MBMS | FRASE | 1 | Rel-15 | S4 | Thu 15/03/18 | Fri 14/09/18 | 100% | SP-180206 |  | Bouazizi, Imed, Samsung Electronics Co., Ltd | i.bouazizi@samsung.com. | 7/6/18: 0%->30¦7/6/18: FCD:06/18->09/18¦10/9/18: 30%->100 | 26.346, new | 79 | 40 |  |  | Thu 15/03/18 | Mon 10/09/18
1584 | 790021 | Media Handling Aspects of 5G Conversational Services | 5G_MTSI_Codecs | 1 | Rel-15 | S4 | Thu 15/03/18 | Fri 14/09/18 | 100% | SP-180650 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/6/18: 0%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-180033->SP-180650 | 26.114; 26.223 | 79 | 40 |  |  | Thu 15/03/18 | Tue 02/10/18
1585 | 790025 | SRVCC for terminating call in pre-alerting phase | bSRVCC_MT | 1 | Rel-15 |  | Thu 15/03/18 | Thu 14/06/18 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com |  |  | 79 | 40 |  |  | Fri 16/03/18 | NA
1586 | 790026 | CT1 aspects of bSRVCC_MT | bSRVCC_MT | 2 | Rel-15 | C1 | Thu 15/03/18 | Thu 14/06/18 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 16/3/18: 0%->80¦7/6/18: 80%->100 | 24.237; 24.008 | 79 | 40 |  |  | Fri 16/03/18 | Thu 07/06/18
1587 | 790027 | CT3 aspects of bSRVCC_MT | bSRVCC_MT | 2 | Rel-15 | C3 | Thu 15/03/18 | Thu 14/06/18 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 22/3/18: 0%->95¦10/9/18: 95%->100 | 29.165 | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1588 | 790035 | Increasing the number of EPS bearers | INOBEAR | 1 | Rel-15 |  | Fri 16/03/18 | Fri 15/06/18 | 100% | SP-171044 |  | Andy.Bennett, Samsung | a <dot> bennett <at> Samsung.com |  | 23.401; 23.167 | 78 | 40 |  |  | Fri 15/12/17 | NA
1589 | 780027 | Stage 2 of INOBEAR | INOBEAR | 2 | Rel-15 | S2 | Fri 16/03/18 | Fri 15/06/18 | 100% | SP-171044 |  | Andy.Bennett, Samsung | a <dot> bennett <at> Samsung.com |  | 23.401; 23.167 | 78 | 40 |  |  | Fri 15/12/17 | NA
1590 | 790036 | Stage 3 of INOBEAR | INOBEAR-CT | 2 | Rel-15 | ct | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com |  |  | 79 | 40 |  |  | Fri 15/12/17 | NA
1591 | 790037 | CT1 aspects of INOBEAR | INOBEAR-CT | 3 | Rel-15 | C1 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com | 7/6/18: 0%->100 | 24.301; 24.007 | 79 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1592 | 790038 | CT4 aspects of INOBEAR | INOBEAR-CT | 3 | Rel-15 | C4 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com | 7/6/18: 0%->100 | 29.274 | 79 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1593 | 780070 | Increased number of E-UTRAN data bearers | INOBEARRAN | 1 | Rel-15 | R2 | Fri 15/12/17 | Fri 14/09/18 | 99% | RP-172835 |  | Samsung |  |  |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1594 | 780170 | Core part: Increased number of E-UTRAN data bearers | INOBEARRAN-Core | 2 | Rel-15 | R2 | Fri 15/12/17 | Fri 14/09/18 | 99% | RP-180569 |  | Samsung |  | 27/3/18: WID: RP-172835->RP-180569¦27/6/18: Compl:0%->99%¦27/6/18: |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1595 | 780019 | Remote UE access via relay UE | REAR | 1 | Rel-15 |  | Tue 01/03/16 | Fri 15/06/18 | 100% | SP-160511 |  | Huawei, Laurence Meriau | laurence.meriau@huawei.com | Previously known as "wearable devices"¦9/6/16: 0%->100¦9/6/16: WID:SP-160231->SP-160371 | 22.278, 22.115 | 71 | 36 |  |  | Fri 11/03/16 | Thu 09/06/16
1596 | 740007 | Study on architecture enhancements to ProSe UE-to-Network Relay | FS_REAR | 2 | Rel-15 | S2 | Thu 01/12/16 | Thu 14/09/17 | 100% | SP-160961 |  | Dario Serafino Tonesi, Huawei | dario.tonesi@huawei.com | 1/12/16: 0%->5. Study on Stage 2 for REAR. When normative work completed, Stage 1 and Stage 2 shall be in the same release¦6/3/17: 5%->30¦7/6/17: 30%->60¦11/9/17: 60%->95¦15/12/17: 95%->100 | 23.733 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1597 | 750017 | Study on security aspects of enhancements to ProSe UE-to-Network Relay | FS_REAR_Sec | 2 | Rel-15 | S3 | Thu 02/03/17 | Fri 15/06/18 | 100% | SP-170270 |  |  | lihe2@huawei.com | 7/6/17: 0%->15¦11/9/17: 15%->50¦15/12/17: 50%->79¦16/3/18: 79%->99¦16/3/18: FCD:03/18->06/18¦7/6/18: 99%->100 |  | 75 | 38 |  |  | Thu 02/03/17 | Thu 07/06/18
1598 | 710047 | Stage 1 for REAR | REAR | 2 | Rel-15 | S1 | Tue 01/03/16 | Wed 15/06/16 | 100% | SP-160511 |  | Huawei, Laurence Meriau | laurence.meriau@huawei.com | Previously known as "wearable devices"¦9/6/16: 0%->100¦9/6/16: WID:SP-160231->SP-160371¦15/12/17: moved Rel-14->Rel-15 | 22.278, 22.115 | 71 | 36 |  |  | Fri 11/03/16 | Fri 15/12/17
1599 | 780046 | Enhanced VoLTE performance | eVoLP | 1 | Rel-15 |  | Thu 01/12/16 | Fri 15/06/18 | 100% | [6 empty] | 78 | 40 |  |  | Fri 15/12/17 | NA
1600 | 780026 | Stage 2 of eVoLP | eVoLP | 2 | Rel-15 | S2 | Thu 12/10/17 | Fri 15/12/17 | 100% | SP-170935 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com |  | 23.401; 23.203 | 78 | 40 |  |  | Fri 15/12/17 | NA
1601 | 780044 | CT aspects on enhanced VoLTE performance | eVoLP-CT | 2 | Rel-15 |  | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com |  |  | 78 | 40 |  |  | Fri 15/12/17 | NA
1602 | 780042 | CT3 aspects of EvoLP | eVoLP-CT | 3 | Rel-15 | C3 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com | 16/3/18: 0%->100 | 29.212; 29.213 | 78 | 40 |  |  | Fri 15/12/17 | Fri 16/03/18
1603 | 780043 | CT4 aspects of EvoLP | eVoLP-CT | 3 | Rel-15 | C4 | Fri 15/12/17 | Thu 14/06/18 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com | 7/6/18: 0%->100 | 29.274 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1604 | 770051 | Study on enhanced VoLTE performance | FS_eVoLP | 2 | Rel-15 |  | Thu 01/12/16 | Fri 15/06/18 | 100% | SP-160833 |  | Fabrice Plante, Intel | fabrice.m.plante@intel.com | 1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100 | 23.759 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/09/17
1605 | 740006 | S2 aspects of FS_eVoLP | FS_eVoLP | 3 | Rel-15 | S2 | Thu 01/12/16 | Thu 14/09/17 | 100% | SP-160833 |  | Xiaobo Wu |  | 1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100¦15/12/17: rapporteur changed | 23.759 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1606 | 770052 | S4 aspects of FS_eVoLP | FS_eVoLP | 3 | Rel-15 | S4 | Thu 14/09/17 | Fri 15/06/18 | 100% | SP-170615 |  | Venkatraman, Atti, Qualcomm Incorporated | vatti@qti.qualcomm.com | 15/12/17: 26.959 added;¦15/12/17: 0%->50¦16/3/18: 50%->75¦16/3/18: FCD:03/18->06/18¦7/6/18: 75%->100 | 26.959 | 77 | 39 |  |  | Thu 14/09/17 | Thu 07/06/18
1607 | 710006 | Unlicensed Spectrum Offloading System | USOS | 1 | Rel-15 |  | Mon 01/02/16 | Thu 15/03/18 | 100% | SP-160117 | SP-170526 | Edward Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com | 08/09/17: Moved from Rel-14 |  | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
1608 | 740008 | Study on unlicensed spectrum offloading system enhancements | FS_USOS | 2 | Rel-15 | S2 | Thu 01/12/16 | Thu 15/06/17 | 100% | SP-160835 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100 | 23.729 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/09/17
1609 | 770006 | Stage 1 of USOS | USOS | 2 | Rel-15 | S1 | Mon 01/02/16 | Tue 01/03/16 | 100% | SP-160117 | SP-170526 | Edward Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com |  | 22.101, 22.115 | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
1610 | 770036 | Stage 2 of USOS | USOS | 2 | Rel-15 | S2 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170740 |  | Haris Zisimopoulos | harisz@qti.qualcomm.com | 15/12/17: 0%->100 | 23.401; 23.203 | 77 | 39 |  |  | Fri 08/09/17 | Fri 15/12/17
1611 | 770001 | Stage 3 of USOS | USOS-CT | 2 | Rel-15 | C4 | Fri 08/09/17 | Thu 15/03/18 | 100% | CP-172028 |  | Lena Chaponniere, Qualcomm Incorporated | lguellec@qti.qualcomm.com | 15/12/17: acronym corrected to USOS-CT as per the approved WID¦18/12/17: 0%->60¦16/3/18: 60%->100 | 23.008; 29.272; 29.230; 29.002; 29.305; 29.274 | 77 | 39 |  |  | Tue 01/03/16 | Fri 16/03/18
1612 | 750007 | Mobile Communication System for Railways | MONASTERY | 1 | Rel-15 |  | Thu 09/06/16 | Fri 15/06/18 | 100% | SP-170163 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com |  |  | 75 | 38 |  |  | Thu 02/03/17 | NA
1613 | 720004 | Study on Future Railway Mobile Communication System | FS_FRMCS | 2 | Rel-15 | S1 | Thu 09/06/16 | Thu 15/06/17 | 100% | SP-170166 |  | Merkel, Juergen | Merkel, Juergen - Nokia Networks | 19/9/16: 0%->25¦6/10/16: 22.989 added¦1/12/16: 25%->40¦1/12/16: WID:SP-160371->SP-160903¦9/12/16: FCD:12/16->3/201. WID was in SP-160903¦2/3/17: 40%->80¦2/3/17: FCD:03/17->06/17¦7/6/17: 80%->100 | 22.989 | 72 | 37 |  |  | Thu 09/06/16 | Wed 07/06/17
1614 | 750024 | Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) | FS_FRMCS_ARCH | 2 | Rel-15 | S6 | Fri 03/03/17 | Thu 14/12/17 | 100% | SP-170269 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 21/3/17: added impacted TR¦7/6/17: 0%->10¦11/9/17: 10%->50¦15/12/17: 50%->100 | new 23.790 | 75 | 38 |  |  | Fri 03/03/17 | Fri 15/12/17
1615 | 750006 | Stage 1 of MONASTERY | MONASTERY | 2 | Rel-15 | S1 | Thu 02/03/17 | Thu 15/06/17 | 100% | SP-170697 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 7/6/17: 0%->10¦8/9/17: WID:SP-170163->SP-170697¦11/9/17: 10%->100 | 22.280; 22.179 | 75 | 38 |  |  | Thu 02/03/17 | Mon 11/09/17
1616 | 770040 | Stage 2 of MONASTERY | MONASTERY | 2 | Rel-15 | S6 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170756 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 14/9/17: SA6 and not SA2¦15/12/17: 0%->100 | 23.280; 23.379 | 77 | 39 |  |  | Fri 08/09/17 | Fri 15/12/17
1617 | 790031 | Stage 3 of MONASTERY | MONASTERY | 2 | Rel-15 | ct | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: WID:CP-180097->CP-182202 |  | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1618 | 790032 | CT1 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C1 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 16/3/18: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100 | 24.379; 24.380; 24.481; 24.483; 24.484 | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1619 | 790033 | CT3 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C3 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: 0%->100 | 29.165 | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1620 | 790034 | DELETED - CT6 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C6 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: 0%->100 | 31.102; 31.103 | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1621 | 790013 | Security Architecture of MONASTERY | MONASTERY_SEC | 2 | Rel-15 | S3 | Thu 11/01/18 | Fri 16/03/18 | 100% | SP-180052 |  | Woodward, Tim, Motorola Solutions |  | 16/3/18: 0%->100 | 33.18 | 79 | 40 |  |  | Thu 15/03/18 | Fri 16/03/18
1622 | 760030 | PS Data Off Phase 2 | PS_DATA_OFF2 | 1 | Rel-15 |  | Thu 02/03/17 | Thu 14/06/18 | 100% | SP-170246 |  | Murhammer, Leopold, Deutsche Telekom AG | leopold.murhammer@t-mobile.at |  |  | 75 | 38 |  |  | Thu 02/03/17 | NA
1623 | 750008 | Stage 2 of PS Data Off Phase 2 | PS_DATA_OFF2 | 2 | Rel-15 | S2 | Thu 02/03/17 | Fri 15/12/17 | 100% | SP-170246 |  | Murhammer, Leopold, Deutsche Telekom AG | leopold.murhammer@t-mobile.at | 7/6/17: 0%->10¦11/9/17: 10%->85¦15/12/17: 85%->100¦15/12/17: FCD:09/17->12/17 |  | 75 | 38 |  |  | Thu 02/03/17 | Fri 15/12/17
1624 | 760031 | Stage 3 of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 2 | Rel-15 | ct | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 18/12/17: WID:CP-171104->CP-173162¦7/6/18: WID:CP-173162->CP-181082 |  | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1625 | 760032 | CT1 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C1 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 24.008; 24.301; 27.007; 24.229; 24.368; 24.167; 24.173; 24.275; 24.341; 24.390; 24.391 | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1626 | 760033 | CT4 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C4 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->100 | 29.272; 29.274; 29.328; 29.329; 29.228; 29.229; 23.008 | 76 | 39 |  |  | Fri 02/06/17 | Fri 15/12/17
1627 | 760034 | CT6 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C6 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 31.102; 31.103; 31.111 | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1628 | 760035 | Northbound APIs for SCEF – SCS/AS Interworking | NAPS | 1 | Rel-15 |  | Thu 02/03/17 | Fri 15/06/18 | 100% | SP-170240 |  | Vaidya, Maulik, Huawei | Maulik.vaidya@huawei.com | 6/3/17: 0%->10 |  | 75 | 38 |  |  | Thu 02/03/17 | Mon 06/03/17
1629 | 750009 | Stage 2 of NAPS | NAPS | 2 | Rel-15 | S2 | Thu 02/03/17 | Fri 15/09/17 | 100% | SP-170240 |  | Zhu Fenqin, Huawei | zhufenqin@huawei.com | 6/3/17: 0%->10¦7/6/17: 10%->85¦30/6/17: 29.122 added;¦11/9/17: 85%->100¦15/12/17: rapoprteur changed | 29.122 | 75 | 38 |  |  | Thu 02/03/17 | Fri 15/12/17
1630 | 780006 | Stage 3 of NAPS | NAPS-CT | 2 | Rel-15 | C3 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90. 18/12/17: WID corrected¦18/12/17: WID:CP-171143 ->CP-173112 | 29.336; 29.128; 29.230 | 78 | 40 |  |  | Fri 02/06/17 | Mon 18/12/17
1631 | 760036 | CT3 aspects of NAPS | NAPS-CT | 3 | Rel-15 | C3 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90¦15/12/17: 90%->65. 18/12/17: WID corrected¦16/3/18: 65%->72¦7/6/18: 72%->85¦7/6/18: 85%->95¦10/9/18: 95%->100 | 29.336; 29.128; 29.230 | 76 | 39 |  |  | Fri 02/06/17 | Mon 10/09/18
1632 | 780007 | CT4 aspects of NAPS | NAPS-CT | 3 | Rel-15 | C4 | Fri 02/06/17 | Thu 14/06/18 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 7/6/18: 95%->100 |  | 78 | 40 |  |  | Fri 02/06/17 | Thu 07/06/18
1633 | 770032 | Security aspects of NAPS | NAPS-Sec | 2 | Rel-15 | S3 | Fri 08/09/17 | Fri 16/03/18 | 100% | SP-170635 |  | Zhao, Xuwen, Huawei | zhaoxuwen@huawei.com | 15/12/17: 0%->60¦16/3/18: 60%->100 | 33.187 | 77 | 39 |  |  | Fri 08/09/17 | Fri 16/03/18
1634 | 760063 | Carging aspects of NAPS | NAPS-CH | 2 | Rel-15 | S5 | Fri 08/09/17 | Fri 15/06/18 | 100% | SP-170488 |  | Chen, Shan, Huawei | chenshan@huawei.com | 30/6/17: 32.254 added;¦11/9/17: 0%->10¦15/12/17: 10%->20¦16/3/18: 20%->50¦7/6/18: 50%->100 | New TS; impact 32.240; 32.298; 32.299; 32.254 | 76 | 39 |  |  | Mon 05/06/17 | Thu 07/06/18
1635 | 770049 | Common API Framework for 3GPP Northbound APIs | CAPIF | 1 | Rel-15 |  | Fri 10/03/17 | Fri 15/06/18 | 100% | SP-170798 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 15/12/17: 23.222 added; | New; 23.222 | 77 | 39 |  |  | Fri 08/09/17 | Fri 15/12/17
1636 | 750031 | Study on CAPIF | FS_CAPIF | 2 | Rel-15 | S6 | Fri 10/03/17 | Thu 14/09/17 | 100% | SP-170405 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 21/3/17: added impacted TR¦7/6/17: 0%->35¦8/6/17: WID:SP-170279->SP-170405¦11/9/17: 35%->70¦15/12/17: 70%->100 | new 23.722 | 75 | 38 |  |  | Fri 10/03/17 | Fri 15/12/17
1637 | 770041 | Stage 2 of CAPIF | CAPIF | 2 | Rel-15 | S6 | Fri 08/09/17 | Fri 15/12/17 | 100% | SP-170798 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 15/12/17: 0%->95¦16/3/18: 95%->100 | New | 77 | 39 |  |  | Fri 08/09/17 | Fri 16/03/18
1638 | 790042 | Stage 3 of CAPIF | CAPIF-CT | 2 | Rel-15 | C3 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180151 |  | Nishant Gupta, Samsung | nishant.gup@samsung.com | 16/3/18: 0%->10¦27/3/18: 29.222 added¦19/4/18: CAPIF->CAPIF-CT¦7/6/18: 10%->35¦7/6/18: 35%->85¦10/9/18: 85%->100 | 29.122; 29.116; 29.222 | 79 | 40 |  |  | Fri 16/03/18 | Mon 10/09/18
1639 | 780024 | Security aspects of CAPIF | CAPIF-Sec | 2 | Rel-15 | S3 | Fri 15/12/17 | Thu 14/06/18 | 100% | SP-171051 |  | Rajavelsamy Rajadurai, Samsung | rajvel{@]samsung.com | 16/3/18: 0%->40¦7/6/18: 40%->100 |  | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1640 | 760066 | Management and orchestration of 5G networks and network slicing | NETSLICE | 1 | Rel-15 | S5 | Mon 13/06/16 | Fri 14/09/18 | 100% | SP-180816 |  | Jan Groenendijk, Ericsson | jan<dot>groenendijk<at>ericsson<dot>com | 21/12/17: WID:SP-170586->SP-170960. Name changed from "Management of Network Slicing in Mobile Networks, Concepts, Use cases and Requirements"¦27/3/18: 32.159 added;¦6/8/18: 32.159 added;¦8/8/18: WID:SP-170960->SP 180124¦2/10/18: WID:SP 180124->SP-... | 32.101; 32.103; new; 32.159; 32.159 | 76 | 39 |  |  | Mon 05/06/17 | Tue 02/10/18
1641 | 780056 | General aspects of NETSLICE | NETSLICE | 2 | Rel-15 | S5 | Mon 13/06/16 | Fri 14/09/18 | 100% | SP-180816 |  | Jan Groenendijk, Ericsson | jan<dot>groenendijk<at>ericsson<dot>com | 21/12/17: created from the Feature level, since SP-170960 contains its own specs and completions¦16/3/18: 46%->60¦7/6/18: 60%->85¦7/6/18: FCD:06/18->09/18¦8/8/18: WID:SP-170960->SP 180124¦10/9/18: 85%->100 | 32.101; 32.103; 28.530 | 76 | 39 |  |  | Mon 05/06/17 | Mon 10/09/18
1642 | 720048 | Study on management and orchestration of network slicing for next generation network | FS_MONETS | 2 | Rel-15 | S5 | Mon 13/06/16 | Tue 12/09/17 | 100% | SP-160394 |  | Ericsson , Robert Petersen |  | 28/7/16: 28.801 added¦19/9/16: 0%->10¦1/12/16: 10%->25¦6/3/17: FCD:03/17->06/17¦6/3/17: 25%->60¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->09/17¦7/6/17: 60%->90¦11/9/17: 90%->100 | 32.8xx; 28.801 | 72 | 37 |  |  | Mon 13/06/16 | Mon 11/09/17
1643 | 770033 | Study on security aspect of 5G Network Slicing Provisioning | FS_NETSLICE_MGT_Sec | 2 | Rel-15 | S3 | Fri 08/09/17 | Fri 15/06/18 | 100% | SP-170636 |  | SA3: Huawei | lei.zhongding@huawei.com | 11/9/17: 0%->5¦15/12/17: 33.811 added;¦15/12/17: 5%->20. Acronym corrected.¦16/3/18: 20%->30¦7/6/18: 30%->100 | 33.811 | 77 | 39 |  |  | Fri 08/09/17 | Thu 07/06/18
1644 | 760065 | Provisioning of network slicing for 5G networks and services | NETSLICE-PRO_NS | 2 | Rel-15 | S5 | Mon 05/06/17 | Fri 14/09/18 | 100% | SP-180818 |  | Zhang Kai, Huawei | kai.zhangkai@huawei.com | 15/12/17: 0%->15¦21/12/17: WID:SP-170580->SP-170955¦16/3/18: 15%->40¦27/3/18: 28.532 added;¦7/6/18: 40%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100¦2/10/18: WID:SP-170955->SP-180818 | 28.531 | 76 | 39 |  |  | Mon 05/06/17 | Tue 02/10/18
1645 | 780037 | Network Resource Model (NRM) for 5G networks and network slicing | NETSLICE-5GNRM | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-180812 |  | Nokia (Jing Ping | jing.ping@nokia-sbell.com | 16/3/18: 0%->25¦7/6/18: 25%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170956->SP-180812 | 28.657; 28.658; 28.659; 28.707; 28.708; 28.709 | 78 | 40 |  |  | Fri 15/12/17 | Tue 02/10/18
1646 | 780038 | Performance Assurance for 5G networks including network slicing | NETSLICE-ADPM5G | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-180814 |  | Yizhi Yao, Intel Corporation | yizhi dot yao at intel dot com | 16/3/18: 0%->10¦7/6/18: 10%->50¦7/6/18: FCD:06/18->09/18¦10/9/18: 50%->100¦2/10/18: WID:SP-170957->SP-180814 | 32.404 | 78 | 40 |  |  | Fri 15/12/17 | Tue 02/10/18
1647 | 780039 | Management and virtualization aspects of 5G networks | NETSLICE-MNFV5G | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170958 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 16/3/18: 0%->25¦7/6/18: 25%->75¦7/6/18: FCD:06/18->09/18¦10/9/18: 75%->100 | 28.500; 28.510; 28.511; 28.512; 28.513; 28.515; 28.516; 28.517; 28.518; 28.520; 28.521; 28.522; 28.523; 28.525; 28.526; 28.527; 28.528 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1648 | 780040 | 5G Trace management | NETSLICE-5GTRACE | 2 | Rel-15 | S5 | Fri 15/12/17 | Thu 07/06/18 | 100% | SP-170959 |  | Nokia (Anatoly Andrianov | anatoly.andrianov@nokia.com | 7/6/18: 0%->100 | 32.421; 32.422; 32.423; 32.441; 32.442; 32.446 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1649 | 810009 | CT aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 2 | Rel-15 | ct | Thu 06/09/18 | Thu 06/09/18 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 81 | 41 |  |  | Thu 06/09/18 | NA
1650 | 810042 | CT3 aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 3 | Rel-15 | C3 | Thu 06/09/18 | Thu 06/09/18 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 10/9/18: 0%->100 | 29.507; 29.512 | 81 | 41 |  |  | Thu 06/09/18 | Mon 10/09/18
1651 | 810043 | CT4 aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 3 | Rel-15 | C4 | Thu 06/09/18 | Thu 06/09/18 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 10/9/18: 0%->100 | 29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274 | 81 | 41 |  |  | Thu 06/09/18 | Mon 10/09/18
1652 | 780041 | Fault Supervision for 5G networks and network slicing | NETSLICE-FS5G | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-180817 |  | Zhu Weihong, ZTE | zhu.weihong@zte.com.cn | 16/3/18: 0%->20¦7/6/18: 20%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170961->SP-180817 | 28.545 | 78 | 40 |  |  | Fri 15/12/17 | Tue 02/10/18
1653 | 790039 | Policy and Charging for Volume Based Charging | PC_VBC | 1 | Rel-15 |  | Thu 01/12/16 | Fri 15/06/18 | 100% | [6 empty] | 78 | 40 |  |  | Fri 16/03/18 | NA
1654 | 780017 | Study on Policy and Charging for Volume Based Charging | FS_PC_VBC | 2 | Rel-15 | C3 | Thu 01/12/16 | Fri 15/12/17 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 6/3/17: 0%->30¦21/3/17: 29.827 added;¦5/6/17: 30%->60¦8/9/17: WID:CP-160822->CP-172058¦11/9/17: FCD:06/17->12/17 | 29.827 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/09/17
1655 | 740057 | CT3 aspects of FS_PC_VBC | FS_PC_VBC | 3 | Rel-15 | C3 | Thu 01/12/16 | Fri 15/12/17 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 6/3/17: 0%->30¦21/3/17: 29.827 added;¦5/6/17: 30%->60¦8/9/17: WID:CP-160822->CP-172058¦11/9/17: FCD:06/17->12/17¦15/12/17: 60%->61¦15/12/17: 61%->100 | 29.827 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1656 | 780018 | CT1 aspects of FS_PC_VBC | FS_PC_VBC | 3 | Rel-15 | C1 | Thu 01/12/16 | Fri 15/12/17 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 15/12/17: 0%->100 | 29.827 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1657 | 790040 | CT1 aspects of PV_VBC | PC_VBC | 2 | Rel-15 | C1 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180051 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 7/6/18: 0%->100 | 24.605; 24.147 | 79 | 40 |  |  | Fri 16/03/18 | Thu 07/06/18
1658 | 790041 | CT3 aspects of PV_VBC | PC_VBC | 2 | Rel-15 | C3 | Fri 16/03/18 | Fri 15/06/18 | 100% | CP-180051 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 7/6/18: 0%->100 | 29.212; 29.213; 29.214 | 79 | 40 |  |  | Fri 16/03/18 | Thu 07/06/18
1659 | 760037 | Framework for Live Uplink Streaming | FLUS | 1 | Rel-15 | S4 | Mon 05/06/17 | Thu 14/06/18 | 100% | SP-170824 |  | Park, Kyungmo, SK Telecom | kyungmo.park@sk.com | 30/6/17: 26.238 added;¦11/9/17: 0%->10¦15/12/17: 10%->85¦15/12/17: FCD:12/17->06/18¦21/12/17: WID:SP-170576->SP-170824¦16/3/18: 85%->90¦7/6/18: 90%->100 | New TS; 26.238 | 76 | 39 |  |  | Sat 03/06/17 | Thu 07/06/18
1660 | 770034 | Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management | OAM_SON_AAS | 1 | Rel-15 | S5 | Fri 08/09/17 | Fri 15/06/18 | 100% | SP-170658 |  | Nokia (Weixing Wang) | weixing.wang@nokia-sbell.com | 15/12/17: 0%->80¦10/9/18: 80%->100 | 28.627; 28.628; 28.629; 28.658; 28.659 | 77 | 39 |  |  | Fri 08/09/17 | Mon 10/09/18
1661 | 740011 | Server and Network Assisted DASH for 3GPP Multimedia Services | SAND | 1 | Rel-15 | S4 | Thu 01/12/16 | Thu 14/09/17 | 100% | SP-170031 | SP-170687 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 3/3/17: WID:SP-160779->SP-170031¦6/3/17: 0%->15¦7/6/17: 15%->60¦11/9/17: 60%->100 | 26.247, 26.233 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/09/17
1662 | 770021 | SAND for MBMS | SAND4M | 1 | Rel-15 | S4 | Fri 08/09/17 | Fri 15/06/18 | 100% | SP-170827 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 0%->50¦15/12/17: FCD:12/17->03/18¦21/12/17: WID:SP-170608->SP-170827¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->100 | 26.247; 26.346; 26.347; TR26.946 | 77 | 39 |  |  | Fri 08/09/17 | Thu 07/06/18
1663 | 780036 | Management Enhancement for EPC CUPS | ME_CUPS | 1 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170954 |  | Huawei (ZHU, Lei | lei.zhu@huawei.com | ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14¦16/3/18: 0%->5¦7/6/18: 5%->60¦10/9/18: 60%->100 | 32.426; 32.455; 28.658; 28.707; 28.708; 28.709 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1664 | 760038 | Enhanced QoE Reporting for MTSI | EQoE_MTSI | 1 | Rel-15 | S4 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170333 |  | Gunnar Heikkilä, Ericsson LM | gunnar.heikkila@ericsson.com | 11/9/17: 0%->10¦15/12/17: 10%->80¦16/3/18: 80%->100 | 26.114 | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
1665 | 760012 | Enhanced Calling Name Service | eCNAM | 1 | Rel-15 |  | Thu 15/09/16 | Wed 14/03/18 | 100% | SP-160548 |  | Hala Mowafy, Ericsson |  | 1/12/16: 0%->100 | 22.173 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
1666 | 730006 | Stage 1 of eCNAM | eCNAM | 2 | Rel-15 | S1 | Thu 15/09/16 | Thu 15/12/16 | 100% | SP-160548 |  | Hala Mowafy, Ericsson |  | 1/12/16: 0%->100¦30/6/17: 24.196 added; | 22.173; 24.196 | 73 | 37 |  |  | Mon 19/09/16 | Fri 30/06/17
1667 | 760013 | CT aspects of eCNAM | eCNAM-CT | 2 | Rel-15 | ct | Fri 02/06/17 | Wed 14/03/18 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com |  |  | 76 | 39 |  |  | Fri 02/06/17 | NA
1668 | 760014 | CT1 aspects of eCNAM | eCNAM-CT | 3 | Rel-15 | C1 | Fri 02/06/17 | Wed 14/03/18 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com | 14/9/17: 0%->40¦15/12/17: 40%->85¦20/3/18: 85%->100 | 24.259; 24.604; 24.606; 24.607; 24.608; 24.610; 24.611; 24.615; 24.616; 24.629; 24.642; 24.647; 24.654 | 76 | 39 |  |  | Fri 02/06/17 | Tue 20/03/18
1669 | 760015 | CT3 aspects of eCNAM | eCNAM-CT | 3 | Rel-15 | C3 | Fri 02/06/17 | Wed 14/03/18 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com | 7/6/18: 0%->100 | 29.165 | 76 | 39 |  |  | Fri 02/06/17 | Thu 07/06/18
1670 | 750001 | Enhancement of background data transfer | eBT | 1 | Rel-15 | S1 | Mon 16/01/17 | Wed 08/03/17 | 100% | SP-170161 |  | Atsushi Minokuchi, NTT DOCOMO | minokuchi at nttdocomo dot com |  | 22.101 | 75 | 38 |  |  | Thu 02/03/17 | NA
1671 | 760016 | Stage-3 SAE Protocol Development - Phase 6 | SAES6 | 1 | Rel-15 | C1 | Fri 02/06/17 | Mon 18/06/18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | Wed 02/03/16 | NA
1672 | 760017 | SAES6 CS Fallback in EPS | SAES6-CSFB | 2 | Rel-15 | C1 | Fri 02/06/17 | Mon 18/06/18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | Wed 02/03/16 | Thu 07/06/18
1673 | 760018 | SAES6 for support for non-3GPP accesses | SAES6-non3GPP | 2 | Rel-15 | C1 | Fri 02/06/17 | Mon 18/06/18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | Wed 02/03/16 | Thu 07/06/18
1674 | 760019 | SAE Protocol Development (Stage 3) - Phase 6 | SAES6 | 2 | Rel-15 | C1 | Fri 02/06/17 | Mon 18/06/18 | 100% | CP-171100 |  |  |  | 14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100 |  | 72 | 37 |  |  | Tue 24/03/15 | Thu 07/06/18
1675 | 730051 | Security Assurance Specification for eNB network product class | SCAS_eNB | 1 | Rel-15 | S3 | Mon 19/09/16 | Tue 12/12/17 | 100% | SP-160570 |  | Marcus Wong, Huawei Technologies | mwong@huawei.com | 6/10/16: 33.216 added¦1/12/16: 0%->5¦6/3/17: 5%->25. Moved from Rel-14.¦7/6/17: FCD:06/17->12/17¦7/6/17: 25%->75¦11/9/17: 75%->100 | 33.117, 33.926; 33.216 | 73 | 37 |  |  | Mon 19/09/16 | Mon 11/09/17
1676 | 720075 | Security Assurance Specification for PGW network product class | SCAS_PGW | 1 | Rel-15 | S3 | Fri 17/06/16 | Tue 12/12/17 | 100% | SP-160481 |  | Peng Jin, China Mobile | pengjin@chinamobile.com | 28/7/16: 33.250 added¦19/9/16: 0%->10¦6/10/16: 33.216 added¦1/12/16: 10%->40. 06/03/17: moved from Rel-14.¦6/3/17: 40%->80¦7/6/17: FCD:06/17->12/17¦7/6/17: 80%->95¦11/9/17: 95%->100 | 33.250; 33.216 | 72 | 37 |  |  | Fri 17/06/16 | Mon 11/09/17
1677 | 750005 | HPLMN Radio Access Technology deployment Optimisation in Network Selection | HORNS | 1 | Rel-15 | S1 | Thu 02/03/17 | Thu 15/06/17 | 100% | SP-170277 |  | Eddy Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com | 7/6/17: 75%->100 |  | 75 | 38 |  |  | Thu 02/03/17 | Wed 07/06/17
1678 | 760008 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 1 | Rel-15 | ct | Fri 02/06/17 | Thu 23/04/20 | 95% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com |  |  | 76 | 39 |  |  | Sat 11/06/16 | NA
1679 | 760009 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C1 | Fri 02/06/17 | Wed 13/06/18 | 100% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com | 14/9/17: 0%->40¦15/12/17: 40%->60¦16/3/18: 60%->80¦7/6/18: 80%->100 | 23.218; 24.229; 24.930 | 76 | 39 |  |  | Thu 04/12/14 | Thu 07/06/18
1680 | 760010 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C1-IETF | Fri 02/06/17 | Thu 23/04/20 | 91% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com |  |  | 76 | 39 |  |  | Thu 04/12/14 | NA
1681 | 780047 | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | IMSProtoc9 | 3 | Rel-15 | C1-IETF | Fri 02/06/17 | Fri 15/06/18 | 100% |  |  | Christer Holmberg | christer.holmberg@ericsson.com | 22/3/18: 0%->100; 9/4/21: RFC 8262 added; | RFC 8262 | 78 | 40 |  |  | Mon 18/12/17 | Fri 09/04/21
1682 | 780048 | (IETF) P-Visited-Network header updated (was: draft-jesske-update-p-visited-network ) | IMSProtoc9 | 3 | Rel-15 | C1-IETF | Fri 02/06/17 | Fri 15/06/18 | 100% |  |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 27/6/18: 0%->100 |  | 78 | 40 |  |  | Mon 18/12/17 | Wed 27/06/18
1683 | 870065 | (IETF) Update to Private Header Field P-Visited-Network-ID in Session Initiation Protocol (SIP) Requests and Responses (draft-jesske-update-p-visited-network) | IMSProtoc8 | 3 | Rel-15 | C1-IETF | Wed 08/01/20 | Thu 23/04/20 | 25% |  |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de |  |  | 87 | 44 |  |  | Thu 23/04/20 | NA
1684 | 760011 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C3 | Fri 02/06/17 | Wed 13/06/18 | 100% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com | 15/12/17: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100 | 29.163; 29.165; 29.949 | 76 | 39 |  |  | Thu 02/04/15 | Mon 10/09/18
1685 | 750014 | Lawful Interception Rel-15 | LI15 | 1 | Rel-15 |  | Thu 02/03/17 | Tue 12/03/19 | 100% | SP-170839 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 21/12/17: WID:SP-170039->SP-170839¦16/3/18: 10%->20 |  | 75 | 38 |  |  | Wed 27/07/16 | Fri 16/03/18
1686 | 750015 | Deleted - Study on R15 Lawful Interception Service | FS_15LIS | 2 | Rel-15 | S3LI | Thu 02/03/17 | Fri 14/09/18 | 100% | SP-170040 |  | Gerry McQuaid, Vodafone | Gerald.McQuaid@vodafone.com | 12/7/17: 0%->5¦11/9/17: 5%->10¦16/3/18: 24%->35¦7/6/18: 35%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->85. 17/01/19: deleted as per Alex's e-mail 13 Nov. Was at 85% |  | 75 | 38 | 82 |  | Wed 27/07/16 | Mon 10/09/18
1687 | 750013 | Normative work on Lawful Interception Rel-15 | LI15 | 2 | Rel-15 | S3LI | Thu 02/03/17 | Tue 12/03/19 | 100% | SP-170839 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 12/7/17: 0%->5¦15/12/17: 5%->10¦10/9/18: 17%->40¦7/12/18: FCD:12/18->03/19¦7/12/18: 40%->75¦20/3/19: 75%->80; 31/5/19: 80%->100 |  | 75 | 38 |  |  | Wed 27/07/16 | Fri 31/05/19
1688 | 750068 | DL interference mitigation for UMTS | UTRA_DL_IM | 1 | Rel-15 | R2 | Wed 15/03/17 | Thu 15/06/17 | 100% | RP-170703 |  | Qualcomm |  | no Perf. part |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1689 | 750168 | Core part: DL interference mitigation for UMTS | UTRA_DL_IM-Core | 2 | Rel-14 | R2 | Wed 15/03/17 | Thu 15/06/17 | 100% | RP-171136 | RP-171135 | Qualcomm |  | no Perf. part19/6/17: Compl:0%->100% |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 19/06/17
1690 | 760055 | Control and monitoring of Power, Energy and Environmental (PEE) parameters in Radio Access Networks (RAN) | PEE_CMON | 1 | Rel-15 | S5 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170479 |  | Jean-Michel CORNILY, ORANGE |  | 30/6/17: 28.306 added;¦30/6/17: 28.305 added;¦30/6/17: 28.304 added;¦11/9/17: 0%->20¦15/12/17: 20%->80¦16/3/18: 80%->100 | New TSs, 52.402; 32.405; 32.425; 32.101; 32.103; 28.306; 28.305; 28.304 | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
1691 | 760082 | Simplified HS-SCCH for UMTS | UTRA_simple_HSSCCH | 1 | Rel-15 | R6 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-171443 |  | Ericsson |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1692 | 750077 | Study on a simplified HS-SCCH for UMTS | FS_UTRA_simple_HSSCCH | 2 | Rel-15 | R1 | Wed 15/03/17 | Thu 15/06/17 | 100% | RP-171477 |  | gerardo.agni.medina.acosta@ericsson.com | gerardo.agni.medina.acosta@ericsson.com | 19/6/17: Compl:0%->100%¦30/6/17: 25.709 added; | 25.709 | 75 | 38 |  |  | Tue 21/03/17 | Fri 30/06/17
1693 | 760182 | Core part: Simplified HS-SCCH for UMTS | UTRA_simple_HSSCCH-Core | 2 | Rel-15 | R6 | Thu 15/06/17 | Fri 15/12/17 | 100% | RP-172720 | RP-172306 | Ericsson |  | 11/9/17: 0%->85¦15/12/17: 85%->100¦8/1/18: WID: RP-171443->RP-172720¦ |  | 76 | 39 |  |  | Fri 16/06/17 | Mon 08/01/18
1694 | 760057 | Charging for enhancement to Flexible Mobile Service Steering (eFMSS) | eFMSS_CH | 1 | Rel-15 | S5 | Mon 05/06/17 | Thu 14/12/17 | 100% | SP-170482 |  | Long,Biao, China Telecom | longb.gd@chinatelecom.cn. | 11/9/17: 0%->70¦15/12/17: 70%->100 | 32.251; 32.298; 32.299 | 76 | 39 |  |  | Sat 03/06/17 | Fri 15/12/17
1695 | 780020 | Receive acoustic output test in the presence of background noise | RAOT | 1 | Rel-15 | S4 | Fri 15/12/17 | Fri 15/06/18 | 100% | SP-170835 |  | ISBERG, Peter, Sony Mobile Communications | peter.isberg [at] sony.com | 16/3/18: 0%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->100 | 26.131; 26.132 | 78 | 40 |  |  | Fri 15/12/17 | Thu 07/06/18
1696 | 780021 | Speech quality in the presence of ambient noise for super-wideband and fullband modes | SPAN | 1 | Rel-15 | S4 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170836 |  | Reimes, Jan – HEAD acoustics GmbH | jan.reimes@head-acoustics.de | 16/3/18: 0%->50¦7/6/18: 50%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100 | 26.131 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1697 | 780032 | REST Solution Sets | REST_SS | 1 | Rel-15 |  | Mon 19/09/16 | Mon 16/09/19 | 27% | SP-170950 | [5 empty] | 78 | 41 |  |  | Fri 15/12/17 | NA
1698 | 730057 | Study on a RESTful HTTP-based Solution Set | FS_OAM_RESTFUL | 2 | Rel-15 | S5 | Mon 19/09/16 | Tue 12/12/17 | 100% | SP-160613 |  | Nokia: Pollakowski, Olaf | olaf.pollakowski@nokia.com | 6/10/16: 32.866 added¦1/12/16: 0%->5¦7/6/17: 5%->45¦7/6/17: FCD:06/17->12/17¦11/9/17: 45%->80¦15/12/17: 80%->100 | 32.866 | 73 | 37 |  |  | Mon 19/09/16 | Fri 15/12/17
1699 | 780033 | REST Solution Sets (normative work) | REST_SS | 2 | Rel-15 | S5 | Fri 15/12/17 | Fri 14/09/18 | 100% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | 16/3/18: 0%->20¦7/6/18: 20%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->100 | 32.101 | 78 | 40 |  |  | Fri 15/12/17 | Mon 10/09/18
1700 | 800114 | (IETF) JSON Schema: A Media Type for Describing JSON Documents (draft-handrews-json-schema) | REST_SS | 2 | Rel-15 | S5-IETF | Fri 15/12/17 | Mon 16/09/19 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | Tue 10/07/18 | NA
1701 | 800115 | (IETF) JSON Schema Validation: A Vocabulary for Structural Validation of JSON (draft-handrews-json-schema-validation) | REST_SS | 2 | Rel-15 | S5-IETF | Fri 15/12/17 | Mon 16/09/19 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | Tue 10/07/18 | NA
1702 | 800116 | (IETF) JSON Hyper-Schema: A Vocabulary for Hypermedia Annotation of JSON (draft-handrews-json-schema-hyperschema) | REST_SS | 2 | Rel-15 | S5-IETF | Fri 15/12/17 | Mon 16/09/19 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | Tue 10/07/18 | NA
1703 | 790028 | Enhancements to Call spoofing functionality | eSPECTRE | 1 | Rel-15 | C1 | Thu 15/03/18 | Thu 07/03/19 | 99% | CP-180096 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com |  |  | 79 | 41 |  |  | Fri 16/03/18 | NA
1704 | 790029 | CT1 aspects of eSPECTRE | eSPECTRE | 2 | Rel-15 | C1 | Thu 15/03/18 | Thu 14/06/18 | 100% | CP-180096 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 16/3/18: 0%->5; 7/6/18: 5%->50; 10/9/18: 50%->100 | 24.229 | 79 |  |  |  | Fri 16/03/18 | Mon 10/09/18
1705 | 800101 | (IETF) PASSporT SHAKEN Extension (draft-ietf-stir-passport-shaken)--> RFC 8588 | eSPECTRE | 2 | Rel-15 | C1-IETF | Thu 14/06/18 | Fri 14/09/18 | 100% |  |  | Axell, Jörgen, Ericsson |  | 23/4/20: 25%->100 | [5 empty] | Wed 27/06/18 | Thu 23/04/20
1706 | 870073 | (IETF) PASSporT Extension for Diverted Calls (draft-ietf-stir-passport-divert) | eSPECTRE | 2 | Rel-15 | C1-IETF | Thu 07/03/19 | Thu 07/03/19 | 80% |  |  |  |  | 9/4/21: RFC 8946 added; | RFC 8946 | 87 | 44 |  |  | Thu 23/04/20 | Fri 09/04/21
1707 | 790030 | CT3 aspects of eSPECTRE | eSPECTRE | 2 | Rel-15 | C3 | Thu 15/03/18 | Thu 14/06/18 | 100% | CP-180096 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 10/9/18: 0%->100 | 29.163; 29.165 | 79 |  |  |  | Fri 16/03/18 | Mon 10/09/18
1708 | 750033 | (Small) Technical Enhancements and Improvements for Rel-15 | TEI15 | 1 | Rel-15 |  | Fri 17/03/17 | Fri 15/06/18 | 100% | [6 empty] | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1709 | 800102 | (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (draft-ietf-tls-tls13) | TEI15 | 2 | Rel-15 | S3-IETF | Fri 17/03/17 | Fri 15/06/18 | 100% |  |  |  |  | 26/6/19: 25%->100; 9/4/21: RFC 8446 added; | RFC 8446 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
1710 | 750034 | (Small) Test Technical Enhancements and Improvements for Rel-15 | TEI15_Test | 1 | Rel-15 |  | Fri 17/03/17 | Fri 15/12/17 | 100% | - |  | - | - | Created upon demand of RAN5 | - | 75 | 38 |  |  | Mon 12/01/15 | Wed 24/02/16
1711 | 0 | Release 15 Features on LTE improvements | - | 1 | Rel-15 |  | Sat 01/01/00 | Sat 01/01/00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1712 | 770067 | UL data compression in LTE | LTE_UDC | 1 | Rel-15 | R2 | Mon 03/01/00 | Fri 15/03/19 | 99% | RP-172076 |  | CATT |  |  |  | 77 | 39 |  |  | Tue 19/09/17 | NA
1713 | 770167 | Core part: UL data compression in LTE | LTE_UDC-Core | 2 | Rel-15 | R2 | Mon 03/01/00 | Fri 14/09/18 | 99% | RP-180914 | RP-180912 | CATT |  | ¦8/1/18: Compl:0%->70%¦8/1/18: CD:Mon 03/01/00->Thu 15/03/18¦27/3/18: Compl:70%->99%27/3/1 ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18; |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 27/06/18
1714 | 800080 | UE Conformance Test Aspects - UL Data Compression in LTE | LTE_UDC-UEConTest | 2 | Rel-15 | R5 | Fri 15/06/18 | Fri 15/03/19 | 100% | RP-190311 |  | CATT |  | tested: REL-15 WI LTE_UDC-Core¦26/3/19: WID:RP-180918->RP-190311¦26/3/19: 0%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Tue 26/03/19
1715 | 770068 | LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42 | 1 | Rel-15 | R4 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-172030 |  | KDDI |  |  |  | 77 | 39 |  |  | Tue 19/09/17 | NA
1716 | 770168 | Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42-Core | 2 | Rel-15 | R4 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180151 |  | KDDI |  | 15/12/17: 36.715-04 added;¦8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%; | 36.715-04 | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1717 | 770268 | Perf. part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42-Perf | 2 | Rel-15 | R4 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180151 |  | KDDI |  | ¦27/3/18: Compl:0%->100%; |  | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1718 | 770069 | Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1 | 1 | Rel-15 | R4 | Fri 15/09/17 | Fri 15/06/18 | 100% | RP-172077 |  | Ericsson |  |  |  | 77 | 39 |  |  | Tue 19/09/17 | NA
1719 | 770169 | Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-Core | 2 | Rel-15 | R4 | Fri 15/09/17 | Fri 15/06/18 | 100% | RP-180262 |  | Ericsson |  | ¦8/1/18: Compl:0%->99%27/3/18: WID: RP-172077->RP-180262¦27/6/18: Compl:99%->100% |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 27/06/18
1720 | 770269 | Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-Perf | 2 | Rel-15 | R4 | Fri 15/09/17 | Fri 15/06/18 | 100% | RP-180262 |  | Ericsson |  | ¦27/3/18: Compl:0%->99% ¦27/6/18: Compl:99%->100% |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 27/06/18
1721 | 780066 | UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-UEConTest | 2 | Rel-15 | R5 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-172713 |  | Ericsson |  | tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ; |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1722 | 770070 | Additional LTE bands for UE category M2 and/or NB2 in Rel-15 | LTE_bands_R15_M2_NB2 | 1 | Rel-15 | R4 | Fri 15/09/17 | Fri 14/12/18 | 100% | RP-172078 |  | Ericsson |  |  |  | 77 | 39 |  |  | Tue 19/09/17 | NA
1723 | 770071 | Extended-Band12 new E-UTRA Band | Ext_B12_LTE | 1 | Rel-15 | R4 | Fri 15/09/17 | Sat 01/06/19 | 100% | RP-172111 |  | Ericsson |  |  |  | 77 | 39 |  |  | Tue 19/09/17 | NA
1724 | 770171 | Core part: Extended-Band12 new E-UTRA Band | Ext_B12_LTE-Core | 2 | Rel-15 | R4 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180159 |  | Ericsson |  | 15/12/17: 37.761 added;¦8/1/18: Compl:0%->25%¦27/3/18: Compl:25%->100%; | 37.761 | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1725 | 770271 | Perf. part: Extended-Band12 new E-UTRA Band | Ext_B12_LTE-Perf | 2 | Rel-15 | R4 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180159 |  | Ericsson |  | ¦8/1/18: WID: RP-172111->RP-17262527/3/18: Compl:0%->100% |  | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1726 | 830084 | UE Conformance Test Aspects - Extended-Band12 new E-UTRA Band (Band 85) | Ext_B12_LTE-UEConTest | 2 | Rel-15 | R5 | Fri 01/03/19 | Sat 01/06/19 | 100% | RP-190937 |  | Ericsson |  | 26/6/19: WID:RP-190510->RP-190937; 26/6/19: 0%->100 |  | 83 | 42 |  |  | Tue 26/03/19 | Wed 26/06/19
1727 | 710073 | Stopped - Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON | 1 | Rel-15 |  | Tue 15/03/16 | Thu 15/03/18 | 100% | RP-171459 |  | Huawei |  | no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459 |  | 71 | 36 |  |  | Tue 22/03/16 | Thu 14/09/17
1728 | 710173 | Stopped - Core part: Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON-Core | 2 | Rel-15 | R2 | Tue 15/03/16 | Thu 15/03/18 | 100% | RP-171459 |  | Huawei |  | no Perf. part¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/12/16->Wed 15/03/17¦1/7/16: WID: RP-160540->RP-16093726/9/16: Compl:10%->30%¦20/12/16: Compl:30%->75%¦20/12/16: Stat Rep: --> 21/3/17: Compl:75%->79% 21/3/17: CD:W ¦27/6/ |  | 71 | 36 |  |  | Tue 22/03/16 | Wed 27/06/18
1729 | 750032 | Stopped - Study on Stage 2 of LTE_LIGHT_CON | FS_LTE_LIGHT_CON | 2 | Rel-15 | S2 | Fri 10/03/17 | Thu 15/06/17 | 100% | SP-170280 |  | Sašo Stojanovski , intel | saso.stojanovski@intel.com | 21/3/17: 23.723 added;¦7/6/17: 0%->55. Stopped at 55%, set at 100% artificially | 23.723 | 75 | 38 |  |  | Fri 10/03/17 | Wed 07/06/17
1730 | 740045 | Stopped - Stage 3 of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 2 | Rel-15 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
1731 | 740046 | Stopped - CT1 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->25¦11/9/17: 25%->0 | 24.008, 24.301, 29.118, 24.368, 27.007 | 74 | 38 |  |  | Thu 01/12/16 | Mon 11/09/17
1732 | 740047 | Stopped - CT4 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C4 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 29.274, 29.272 | 74 | 38 |  |  | Thu 01/12/16 | NA
1733 | 740048 | Stopped - CT6 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C6 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/3/17: 0%->100 | 31.102 | 74 | 38 |  |  | Thu 01/12/16 | Tue 07/03/17
1734 | 710074 | Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA | 1 | Rel-15 |  | Tue 15/03/16 | Fri 14/09/18 | 71% | RP-161668 |  | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA¦14/9/17: WID:RP-160548->RP-161668 | 37.843 | 71 | 36 |  |  | Tue 22/03/16 | Thu 14/09/17
1735 | 710174 | Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Core | 2 | Rel-15 | R4 | Tue 15/03/16 | Fri 15/12/17 | 100% | RP-171745 | RP-172345 | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/1726/9/16: Compl:5%->10% 20/12/16: Compl:10%->20%21/3/17: Compl:20%->40% ; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
1736 | 710274 | Perf. part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Perf | 2 | Rel-15 | R4 | Tue 15/03/16 | Fri 14/09/18 | 50% | RP-181297 |  | Huawei |  | 1/7/16: WID: RP-160548->RP-1609401/7/16: Release: Rel-15->Rel-14¦26/9/16: WID: RP-160940->RP-161668 20/12/16: Stat Rep: -->¦21/3/17: Compl:0%->10%; |  | 71 | 36 |  |  | Tue 22/03/16 | Wed 27/06/18
1737 | 720091 | Shortened TTI and processing time for LTE | LTE_sTTIandPT | 1 | Rel-15 |  | Wed 15/06/16 | Sat 12/12/20 | 99% | RP-161299 |  | Ericsson |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1738 | 720191 | Core part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Core | 2 | Rel-15 | R1 | Wed 15/06/16 | Fri 14/09/18 | 99% | RP-171468 | RP-181008 | Ericsson |  | 26/9/16: Compl:0%->5%¦20/12/16: Compl:5%->10%21/3/17: Compl:10%->30%19/6/17: Compl:30%->65%19/6/17: CD: 19/9/17: Compl:65%->75%¦8/1/18: Compl:75%->99%¦8/1/18: CD:Fri 15/12/17->F ¦27/6/18: CD:Fri 15/06/1 |  | 72 | 37 |  |  | Fri 01/07/16 | Wed 27/06/18
1739 | 720291 | Perf. part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Perf | 2 | Rel-15 | R4 | Wed 14/09/16 | Fri 14/09/18 | 100% | RP-171468 |  | Ericsson |  | ¦26/9/16: WID: RP-161299->RP-161922¦20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113¦19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%¦27/6/18: Compl:33%->60%¦26/3/19: 60%->100 |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 26/03/19
1740 | 820064 | UE Conformance Test Aspects - Shortened TTI and processing time for LTE | LTE_sTTIandPT-UEConTest | 2 | Rel-15 | R5 | Sat 15/12/18 | Sat 12/12/20 | 100% | RP-191003 |  | Huawei |  | tested: REL-15 WI LTE_sTTIandPT-Core; 26/6/19: WID:RP-182429->RP-191003; 8/10/20: 0%->90; 8/10/20: 0%->90; 8/10/20: FCD:20/06/2019->12/20; 7/4/21: 0%->100; 8/4/21: 100%->100 | [5 empty] | Wed 16/01/19 | Thu 08/04/21
1741 | 740072 | 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR | 1 | Rel-15 |  | Thu 15/12/16 | Thu 15/03/18 | 100% | RP-162514 |  | Airbus |  | 21/3/17: 36.748 added; | 36.748 | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
1742 | 740172 | Core part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-162514 |  | Airbus |  | 21/3/17: Compl:0%->10%¦19/6/17: Compl:10%->75%¦19/9/17: Compl:75%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1743 | 740272 | Perf. part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR-Perf | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-162514 |  | Airbus |  | 19/6/17: Compl:0%->50%19/9/17: Compl:50%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1744 | 770065 | UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72) | LTE450_Europe_PPDR-UEConTest | 2 | Rel-15 | R5 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180528 |  | Airbus |  | ¦8/1/18: Compl:0%->77%¦27/3/18: Compl:77%->100%; |  | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1745 | 740074 | E-UTRA 700MHz in Europe for Broadband-PPDR (Public Protection and Disaster Relief) | LTE700_Europe_PPDR | 1 | Rel-15 |  | Thu 15/12/16 | Thu 15/03/18 | 83% | RP-162534 |  | Airbus |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
1746 | 740174 | Core part: E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-170212 |  | Airbus |  | 21/3/17: Compl:0%->25%¦19/6/17: Compl:25%->80%¦19/9/17: Compl:80%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1747 | 740274 | Perf. part: E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-Perf | 2 | Rel-15 | R4 | Thu 15/12/16 | Wed 15/03/17 | 0% | RP-170212 |  | Airbus |  | 21/3/17: CD:Thu 15/06/17->Wed 15/03/17 |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
1748 | 770066 | UE Conformance Test Aspects - E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-UEConTest | 2 | Rel-15 | R5 | Fri 15/09/17 | Thu 15/03/18 | 100% | RP-180529 |  | Airbus |  | ¦8/1/18: Compl:0%->64%27/3/18: Compl:64%->100%; |  | 77 | 39 |  |  | Tue 19/09/17 | Tue 27/03/18
1749 | 740075 | FDD operating band in the L-band for LTE | LTE_FDD_L_Band | 1 | Rel-15 |  | Thu 15/12/16 | Fri 14/09/18 | 100% | RP-162536 |  | NTT DOCOMO |  | 21/3/17: 36.751 added; | 36.751 | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
1750 | 740175 | Core part: FDD operating band in the L-band for LTE | LTE_FDD_L_Band-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-171403 |  | NTT DOCOMO |  | 21/3/17: Compl:0%->50%¦19/6/17: Compl:50%->99%¦19/9/17: Compl:99%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1751 | 740275 | Perf. part: FDD operating band in the L-band for LTE | LTE_FDD_L_Band-Perf | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-171403 |  | NTT DOCOMO |  | 19/6/17: Compl:0%->99%19/6/17: CD:Thu 15/06/19/9/17: Compl:99%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1752 | 780062 | UE Conformance Test Aspects - FDD operating band in the L-band for LTE | LTE_FDD_L_band-UEConTest | 2 | Rel-15 | R5 | Fri 15/12/17 | Fri 14/09/18 | 100% | RP-180145 |  | NTT DOCOMO |  | tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ;; 11/10/20: 60%->100 |  | 78 | 40 |  |  | Mon 08/01/18 | Sun 11/10/20
1753 | 740076 | LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext | 1 | Rel-15 |  | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-162556 |  | Qualcomm |  | 21/3/17: 36.934 added;¦21/3/17: 36.753 added; | 36.934; 36.753 | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
1754 | 740176 | Core part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-171389 |  | Qualcomm |  | 21/3/17: Compl:0%->20%19/6/17: Compl:20%->50%;19/9/17: Compl:50%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1755 | 740276 | Perf. part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext-Perf | 2 | Rel-15 | R4 | Fri 17/03/17 | Fri 15/09/17 | 100% | RP-171389 |  | Qualcomm |  | ¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17 19/9/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1756 | 740077 | Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2 | 1 | Rel-15 |  | Thu 15/12/16 | Fri 14/12/18 | 100% | RP-162571 |  | Sprint |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
1757 | 740177 | Core part: Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/12/17 | 100% | RP-172295 |  | Sprint |  | 21/3/17: Compl:0%->5%¦19/6/17: Compl:5%->50%¦19/9/17: Compl:50%->90%¦8/1/18: Compl:90%->100%; |  | 74 | 38 |  |  | Tue 20/12/16 | Mon 08/01/18
1758 | 780065 | UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2-UEConTest | 2 | Rel-15 | R5 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-172698 |  | Sprint |  | tested: REL-15 WI LTE_CA_C_B41_PC2-Core¦27/3/18: Co ;; 28/7/20: 5%->100 |  | 78 | 40 |  |  | Mon 08/01/18 | Tue 28/07/20
1759 | 730081 | Addition of Power Class 1 UE to bands B3/B20/B28 for LTE | LTE_HPUE_B3_B20_B28 | 1 | Rel-15 |  | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-161871 |  | Motorola Solutions |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1760 | 730181 | Core part: Addition of Power Class 1 UE to bands B3/B20/B28 for LTE | LTE_HPUE_B3_B20_B28-Core | 2 | Rel-15 | R4 | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-171757 |  | Motorola Solutions |  | ¦20/12/16: Compl:0%->15%¦20/12/16: CD:Wed 15/03/17->Thu 15/06/1721/3/17: Compl:15%->70%19/6/17: Compl:70%->99%19/9/17: Compl:99%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 19/09/17
1761 | 740080 | TDD operating band in the L-band for LTE | LTE_TDD_L_Band | 1 | Rel-15 |  | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-170304 |  | Huawei |  | 21/3/17: 36.753 added;¦14/9/17: WID:RP-162557->RP-170304 | 36.753 | 74 | 38 |  |  | Tue 20/12/16 | Thu 14/09/17
1762 | 740180 | Core part: TDD operating band in the L-band for LTE | LTE_TDD_L_Band-Core | 2 | Rel-15 | R4 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-170304 |  | Huawei |  | 21/3/17: Compl:0%->15%¦19/6/17: Compl:15%->70%¦ 19/9/17: Compl:70%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1763 | 740280 | Perf. part: TDD operating band in the L-band for LTE | LTE_TDD_L_Band-Perf | 2 | Rel-15 | R4 | Fri 17/03/17 | Fri 15/09/17 | 100% | RP-170304 |  | Huawei |  | 21/3/17: WID: RP-162557->RP-170304¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17¦19/9/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1764 | 750060 | Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-171031 |  | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦14/9/17: WID:RP-170750->RP-171031 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1765 | 750160 | Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-180584 | RP-180318 | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦19/6/17: Compl:0%->70%¦19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%¦27/3/18: Compl:90%->99%¦27/3/18: CD:Thu 15/03/18->Fri ¦27/6/18: CD:Fri |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1766 | 750260 | Perf. part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-180584 |  | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #7519/6/17: WID: RP-170750->RP-171031¦8/1/18: Compl:0%->65%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:65%->80%27/3/ ¦27/6/18: Compl:80%->100% |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1767 | 750063 | UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh | 1 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-171508 |  | Nokia |  | 14/9/17: WID:RP-170813->RP-171508 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1768 | 750163 | Core part: UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh-Core | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-181298 | RP-180947 | Nokia |  | ¦19/6/17: Compl:0%->10%¦19/6/17: CD:Fri 15/12/17->Fri 15/06/18 19/9/17: Compl:10%->20%¦8/1/18: Compl:20%->40%¦8/1/18: WID: RP-171508->RP-17231327/3/18: Compl:40%->50%¦27/6/18: Compl:50%->99%;; 24/4/20: 99%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Fri 24/04/20
1769 | 750263 | Perf. part: UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-181298 |  | Nokia |  | ¦19/6/17: WID: RP-170813->RP-171508¦8/1/18: Compl:0%->30%¦8/1/18: WID: RP-171508->RP-172313¦27/6/18: Compl:30%->100%¦27/6/18: WID: RP-17231 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1770 | 750064 | Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL | 1 | Rel-15 | R1 | Wed 14/09/16 | Fri 14/12/18 | 99% | RP-171067 |  | Huawei |  | 14/9/17: WID:RP-170838->RP-171067 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1771 | 750164 | Core part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-171740 | RP-180854 | Huawei |  | ¦19/6/17: Compl:0%->20%¦19/6/17: CD:Sat 15/12/18->Thu 15/03/18 19/6/17: FCD:03/18->06/18¦12/7/17: 36.783 added;19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->85%27/3/18: Compl:85%->99% | 36.783 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1772 | 750264 | Perf. part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL-Perf | 2 | Rel-15 | R4 | Wed 14/09/16 | Fri 14/12/18 | 100% | RP-171740 |  | Huawei |  | ¦19/6/17: CD:Sat 15/12/18->Fri 15/06/18¦19/6/17: WID: RP-170838->RP-171067 19/9/17: WID: RP-171067->RP-17173827/3/18: Compl:0%->25%¦27/6/18: Compl:25%->50%¦16/1/19: 50%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1773 | 750065 | Enhancements to LTE operation in unlicensed spectrum | LTE_unlic | 1 | Rel-15 | R1 | Wed 15/03/17 | Sat 15/12/18 | 99% | RP-180402 |  | Nokia |  | note: The is actually a further LAA enhancement |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1774 | 750165 | Core part: Enhancements to LTE operation in unlicensed spectrum | LTE_unlic-Core | 2 | Rel-15 | R1 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-180402 | RP-180948 | Nokia |  | note: The is actually a further LAA enhancement¦19/6/17: Compl:0%->15%¦19/6/17: CD:Fri 15 19/9/17: Compl:15%->30%¦8/1/18: Compl:30%->65%¦ 27/3/18: Compl:65%->85% 27/3/18: 37.107 added;; | 37.107; 37.106 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1775 | 750265 | Perf. part: Enhancements to LTE operation in unlicensed spectrum | LTE_unlic-Perf | 2 | Rel-15 | R4 | Thu 14/12/17 | Sat 15/12/18 | 100% | RP-180402 |  | Nokia |  | 19/6/17: CD:Thu 15/03/18->Sat 15/12/18¦8/1/18: WID: RP-170848->RP-17284127/3/18: WID: RP-172841->RP-180402¦16/1/19: 0%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 16/01/19
1776 | 750069 | Further video enhancements for LTE | LTE_ViLTE_enh2 | 1 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-170781 |  | CMCC |  | no Perf. part¦compare REL-14 WI LTE_VoLTE_ViLTE_enh |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1777 | 750169 | Core part: Further video enhancements for LTE | LTE_ViLTE_enh2-Core | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-172726 | RP-172381 | CMCC |  | no Perf. part¦compare REL-14 WI LTE_VoLTE_ViLTE_enh19/6/17: Compl:0%->15%19/6/17: W 19/9/17: Compl:15%->35%¦8/1/18: Compl:35%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1778 | 750070 | Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming | 1 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/12/18 | 99% | RP-170786 |  | China Unicom |  | compare REL-14 WI UMTS_QMC_Streaming-Core |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1779 | 750170 | Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming-Core | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 99% | RP-170956 | RP-172192 | China Unicom |  | compare REL-14 WI UMTS_QMC_Streaming-Core¦19/6/17: Compl:0%->25%¦19/6/17: WID: RP- 19/9/17: Compl:25%->45%¦8/1/18: Compl:45%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18 |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1780 | 790051 | UE Conformance Test Aspects - Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming-UEConTest | 2 | Rel-15 | R5 | Thu 15/03/18 | Fri 14/12/18 | 100% | RP-180215 |  | China Unicom |  | tested: REL-15 WI LTE_QMC_Streaming-Core¦WI code to be used: LTE_QMC_Streaming-UEConTest;; 26/6/19: 5%->100 |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 26/06/19
1781 | 750071 | Enhancing LTE CA Utilization | LTE_euCA | 1 | Rel-15 | R2 | Wed 15/03/17 | Wed 08/09/21 | 48% | RP-170805 |  | Nokia |  |  |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1782 | 750171 | Core part: Enhancing LTE CA Utilization | LTE_euCA-Core | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 14/09/18 | 90% | RP-180561 | RP-181069 | Nokia |  | 19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1783 | 750271 | Perf. part: Enhancing LTE CA Utilization | LTE_euCA-Perf | 2 | Rel-15 | R4 | Wed 13/09/17 | Fri 14/12/18 | 100% | RP-180561 |  | Nokia |  | 16/3/18: FCD:12/17->12/18¦27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:0%->20%¦26/3/19: 20%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 26/03/19
1784 | 820066 | UE Conformance Test Aspects - Enhancing LTE CA Utilization | LTE_euCA-UEConTest | 2 | Rel-15 | R5 | Sat 15/12/18 | Wed 08/09/21 | 0% | RP-182619 |  | Nokia |  | tested: REL-15 WI LTE_euCA-Core; 8/10/20: 0%->35; 8/10/20: FCD:15/12/2019->12/20; 8/4/21: 0%->56; 8/4/21: FCD:12/12/2020->09/20 | [5 empty] | Wed 16/01/19 | Thu 08/04/21
1785 | 750073 | 450 MHz Band for LTE in Region 3 | LTE450_Reg3 | 1 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/03/19 | 99% | RP-170952 |  | China Unicom |  | 14/9/17: WID:RP-170159->RP-170952 |  | 75 | 38 |  |  | Tue 21/03/17 | Thu 14/09/17
1786 | 750173 | Core part: 450 MHz Band for LTE in Region 3 | LTE450_Reg3-Core | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-170952 |  | China Unicom |  | ¦19/6/17: Compl:0%->30%¦19 12/7/17: 36.759 added;¦19/9/17: Compl:30%->80%¦8/1/18: Compl:80%->100% | 36.759 | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1787 | 750273 | Perf. part: 450 MHz Band for LTE in Region 3 | LTE450_Reg3-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-170952 |  | China Unicom |  | ¦19/6/17: WID: RP-170159->RP-170952¦8/1/18: Compl:0%->100% |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1788 | 790058 | UE Conformance Test Aspects - 450 MHz Band for LTE in Region 3 | LTE450_Reg3-UEConTest | 2 | Rel-15 | R5 | Thu 15/03/18 | Fri 15/03/19 | 100% | RP-181040 |  | China Unicom, Shi Yu |  | ¦27/6/18: Compl:0%->5%;; 14/1/20: 5%->100 | 34.121-1; 36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1; 36.905 | 79 | 40 |  |  | Thu 19/04/18 | Tue 14/01/20
1789 | 750074 | US 600 MHz Band for LTE | LTE600_US | 1 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-170740 |  | Ericsson |  |  |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 21/03/17
1790 | 750174 | Core part: US 600 MHz Band for LTE | LTE600_US-Core | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/09/17 | 100% | RP-171142 |  | Ericsson |  | ¦19/6/17: Compl:0%->95%¦19 12/7/17: 36.755 added;19/9/17: Compl:95%->100% | 36.755 | 75 | 38 |  |  | Tue 21/03/17 | Tue 19/09/17
1791 | 750274 | Perf. part: US 600 MHz Band for LTE | LTE600_US-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/09/17 | 100% | RP-171142 |  | Ericsson |  | ¦19/6/17: Compl:0%->95%¦19 19/9/17: Compl:95%->100% |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 19/09/17
1792 | 770060 | UE Conformance Test Aspects - US 600 MHz Band for LTE (Band 71) | LTE600_US-UEConTest | 2 | Rel-15 | R5 | Fri 15/09/17 | Fri 15/12/17 | 100% | RP-172195 |  | Dish Network |  | ¦8/1/18: Compl:0%->100%¦ |  | 77 | 39 |  |  | Tue 19/09/17 | Mon 08/01/18
1793 | 750076 | LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA | 1 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-170804 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2 Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA" |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 19/06/17
1794 | 750176 | Core part: LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA-Core | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-172626 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2;19/6/17: Com¦Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA-Core"¦12/7/17: 36.790 added;; | 36.79 | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1795 | 750276 | Perf. part: LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA-Perf | 2 | Rel-15 | R4 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-172626 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2¦19/6/17: C Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA-Perf"; |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1796 | 760097 | Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15 | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171131 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1797 | 760197 | Core part: Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180073 |  | Huawei |  | 19/9/17: Compl:0%->99%¦8/1/18: WID: RP-171131->RP-17234727/3/18: Compl:99%->90% ¦27/6/18: Compl:90%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1798 | 760297 | Perf. part: Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180073 |  | Huawei |  | ¦8/1/18: WID: RP-171131->RP-172347¦27/3/18: WID: RP-172347->RP-180073¦27/6/18: Compl:0%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1799 | 760098 | Addition of band 28 and 40 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B28_B40 | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/09/17 | 100% | RP-171132 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1800 | 760198 | Core part: Addition of band 28 and 40 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B28_B40-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/09/17 | 100% | RP-171132 |  | Huawei |  | 19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 19/09/17
1801 | 760099 | LTE Advanced high power TDD UE (power class 2) for Rel-15 | LTE_TDD_HPUE_R15 | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 11/06/21 | 99% | RP-171492 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1802 | 760199 | Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15 | LTE_TDD_HPUE_R15-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171755 |  | Huawei |  | 19/9/17: Compl:0%->10%¦ 15/12/17: 36.760 added;¦8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%¦27/6/18: Comp | 36.76 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1803 | 850061 | UE Conformance Test Aspects – LTE Advanced high power TDD UE (power class 2) for Rel-15 | LTE_TDD_HPUE_R15-UEConTest | 2 | Rel-15 | R5 | Thu 19/09/19 | Fri 11/06/21 | 98% | RP-192116 |  | Huawei |  | 8/10/20: 0%->50; 8/10/20: FCD:15/09/2020->12/20; 8/4/21: 50%->98; 8/4/21: FCD:11/12/2020->06/21 |  | 85 | 43 |  |  | Tue 08/10/19 | Thu 08/04/21
1804 | 761000 | New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa | 1 | Rel-15 | R4 | Thu 15/06/17 | Thu 15/03/18 | 100% | RP-171506 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1805 | 761100 | Core part: New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Thu 15/03/18 | 100% | RP-180247 |  | Huawei |  | 12/7/17: 36.758 added;19/9/17: Compl:0%->10%¦ 8/1/18: Compl:10%->70%27/3/18: Compl:70%->100%; | 36.758 | 76 | 39 |  |  | Fri 16/06/17 | Tue 27/03/18
1806 | 761200 | Perf. part: New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Thu 15/03/18 | 100% | RP-180247 |  | Huawei |  | ¦19/9/17: WID: RP-171506->RP-171759¦27/3/18: Compl:0%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 27/03/18
1807 | 761001 | UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM | 1 | Rel-15 | R4 | Thu 15/06/17 | Sat 15/12/18 | 93% | RP-171408 |  | Ericsson |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1808 | 761101 | Core part: UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 14/09/18 | 85% | RP-181315 |  | Ericsson |  | ¦19/9/17: Compl:0%->15%¦8/1/18: Compl:15%->50%27/3/18: Compl:50%->70%¦27/6/18: Compl:70%->85% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1809 | 761201 | Perf. part: UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Sat 15/12/18 | 100% | RP-181315 |  | Ericsson |  | ¦27/6/18: WID: RP-171408->RP-181315¦16/1/19: 0%->100 |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 16/01/19
1810 | 780068 | Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN | 1 | Rel-15 | R2 | Fri 15/12/17 | Sun 15/12/19 | 98% | RP-172820 |  | CMCC |  | MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1811 | 780168 | Core part: Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN-Core | 2 | Rel-15 | R2 | Fri 15/12/17 | Fri 14/09/18 | 95% | RP-180306 | RP-180867 | CMCC |  | MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact27/3/18: Compl:0%->30%2 ¦27/6/18: Compl:30%->95% |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1812 | 820065 | UE Conformance Test Aspects - Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN-UEConTest | 2 | Rel-15 | R5 | Sat 15/12/18 | Sun 15/12/19 | 100% | RP-182509 |  | CMCC |  | tested: REL-15 WI LTE_MDT_BT_WLAN-Core; 14/1/20: 0%->100; 14/1/20: 100%->100 | [5 empty] | Wed 16/01/19 | Tue 14/01/20
1813 | 780069 | Enhanced LTE Support for Aerial Vehicles | LTE_Aerial | 1 | Rel-15 | R2 | Wed 15/03/17 | Wed 19/06/19 | 99% | RP-172826 |  | Ericsson |  | follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1814 | 750042 | Study on enhanced LTE Support for Aerial Vehicles | FS_LTE_Aerial | 2 | Rel-15 | R2 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-171050 |  | NTT DOCOMO |  | TR 36.7XX19/6/17: Compl:0%->15%¦30/6/17: 36.777 added;¦19/9/17: Compl:15%->30%¦8/1/18: Compl:30%->100% | 36.777 | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1815 | 780169 | Core part: Enhanced LTE Support for Aerial Vehicles | LTE_Aerial-Core | 2 | Rel-15 | R2 | Fri 15/12/17 | Fri 14/09/18 | 99% | RP-181310 | RP-181045 | Ericsson |  | follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part¦27/3/18: Compl:0%->15%¦27/6/18: Compl:15%->99%; |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1816 | 820062 | UE Conformance Test Aspects - Enhanced LTE Support for Aerial Vehicles | LTE_Aerial-UEConTest | 2 | Rel-15 | R5 | Sat 15/12/18 | Wed 19/06/19 | 100% | RP-192747 |  | NTT DOCOMO |  | tested: REL-15 WI LTE_Aerial-Core; 8/10/19: WID:RP-182324->RP-191747; 14/1/20: WID:RP-191747->RP-192747; 14/1/20: 0%->100 | [5 empty] | Wed 16/01/19 | Tue 14/01/20
1817 | 780071 | Separation of CP and UP for Split Option 2 of NR | NR_CPUP_Split | 1 | Rel-15 | R3 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-172831 |  | Ericsson |  | follow-up WI of REL-15 SI FS_NR_CPUP_Split¦introduction of E1 interface |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1818 | 780171 | Core part: Separation of CP and UP for Split Option 2 of NR | NR_CPUP_Split-Core | 2 | Rel-15 | R3 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-180326 | RP-181149 | Ericsson |  | follow-up WI of REL-15 SI FS_NR_CPUP_Split¦introduction of E1 interface. 30/1/18: acronym updated27/3/18: Compl:0%->30%27/3/18: WID: RP-172831->RP-180326¦27/6/18: Compl:30%->100%¦27/6/18: Stat Rep: ->RP-181149 |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1819 | 780072 | UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL | 1 | Rel-15 | R4 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-172842 |  | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1820 | 780172 | Core part: UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL-Core | 2 | Rel-15 | R4 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-180960 | RP-180959 | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL27/3/18: Compl:0%->40%¦27/6/18: Compl:40%->100% |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1821 | 780272 | Perf. part: UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL-Perf | 2 | Rel-15 | R4 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-180960 |  | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL¦27/6/18: Compl:0%->30%¦26/3/19: 30%->100 |  | 78 | 40 |  |  | Mon 08/01/18 | Tue 26/03/19
1822 | 780073 | ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe | 1 | Rel-15 | R4 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-182441 |  | Airbus |  | This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78¦compare REL-15 WI LTE450_Europe_PPDR-Core¦16/1/19: WID:RP-172568->RP-182441 |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 16/01/19
1823 | 780173 | Core part: ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe-Core | 2 | Rel-15 | R4 | Fri 15/12/17 | Fri 15/12/17 | 100% | RP-182441 |  | Airbus |  | This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78¦compare REL-15 WI LTE450_Europe_PPDR-Core; |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1824 | 810063 | UE Conformance Test Aspects - ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe-UEConTest | 2 | Rel-15 | R5 | Fri 14/09/18 | Fri 14/12/18 | 100% | RP-181630 |  | Airbus |  | 16/1/19: 0%->100 |  | 81 | 41 |  |  | Tue 25/09/18 | Wed 16/01/19
1825 | 780074 | LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL | 1 | Rel-15 | R4 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-172839 |  | Qualcomm |  | basket CA WI¦TR 36.715-00-01 |  | 78 | 40 |  |  | Mon 08/01/18 | Mon 08/01/18
1826 | 780174 | Core part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL-Core | 2 | Rel-15 | R4 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-181442 |  | Qualcomm |  | basket CA WI¦TR 36.715-00-01¦27/3/18: Compl:0%->10%¦27/3/18: 36.715-00-01 added;¦27/6/18: Compl:10%->100%; | 36.715-00-01 | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1827 | 780274 | Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL-Perf | 2 | Rel-15 | R4 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-181442 |  | Qualcomm |  | basket CA WI27/3/18: CD:Sat 15/12/18->Fri 15/06/18 ¦27/6/18: Compl:0%->50%;¦16/1/19: 50%->100 |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 16/01/19
1828 | 761002 | Performance requirements of interference cancellation receiver for LTE BS | LTE_IC_BS | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/09/17 | 100% | RP-171411 |  | China Telecom |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1829 | 761202 | Perf. part: Performance requirements of interference cancellation receiver for LTE BS | LTE_IC_BS-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/09/17 | 100% | RP-171411 |  | China Telecom |  | ¦19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 19/09/17
1830 | 761003 | LTE CRS-Interference Mitigation performance requirements for single RX chain UEs | LTE_1RX_CRS_IM | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171465 |  | Intel |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1831 | 761203 | Perf. part: LTE CRS-Interference Mitigation performance requirements for single RX chain UEs | LTE_1RX_CRS_IM-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-N1122 |  | Intel |  | ¦19/9/17: Compl:0%->20%¦19/9/17: WID: RP-171465->RP-171831¦8/1/18: Compl:20%->60%¦27/3/18: Compl:60%->85%¦27/6/18: Compl:85%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1832 | 760090 | LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-170962 |  | Ericsson |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1833 | 760190 | Core part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180800 |  | Ericsson |  | 12/7/17: 36.715-00-00 added;¦19/9/17: Compl:0%->25% 8/1/18: Compl:25%->70%;27/3/18: Compl:70%->67%¦ ¦27/6/18: Compl:67%->100%; | 36.715-00-00 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1834 | 760290 | Perf. part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180800 |  | Ericsson |  | 19/9/17: Compl:0%->25%¦ 8/1/18: Compl:25%->70%¦8/1/18:27/3/18: Compl:70%->67%¦ ¦27/6/18: Compl:67%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1835 | 760091 | LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171026 |  | Qualcomm |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1836 | 760191 | Core part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-181013 |  | Qualcomm |  | 12/7/17: 36.715-02-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->30%¦27/3/18: Compl:30%->40%¦ ¦27/6/18: Compl:40%->100%; | 36.715-02-01 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1837 | 760291 | Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-181013 |  | Qualcomm |  | ¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->30%;27/3/18: Compl:30%->40% ¦27/6/18: Compl:40%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1838 | 760092 | LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171126 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1839 | 760192 | Core part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180955 |  | Huawei |  | 12/7/17: 36.715-03-01 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%¦27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%; | 36.715-03-01 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1840 | 760292 | Perf. part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180955 |  | Huawei |  | ¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1841 | 760093 | LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-170963 |  | Ericsson |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1842 | 760193 | Core part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180801 |  | Ericsson |  | 12/7/17: 36.715-04-01 added;¦19/9/17: Compl:0%->54% 8/1/18: Compl:54%->65%;27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%; | 36.715-04-01 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1843 | 760293 | Perf. part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180801 |  | Ericsson |  | 19/9/17: Compl:0%->54%¦ 8/1/18: Compl:54%->65%¦27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1844 | 760094 | LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171466 |  | Nokia |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1845 | 760194 | Core part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180743 |  | Nokia |  | 12/7/17: 36.715-05-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->50%;27/3/18: Compl:50%->75% ¦27/6/18: Compl:75%->100%; | 36.715-05-01 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1846 | 760294 | Perf. part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180743 |  | Nokia |  | ¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->75%¦ ¦27/6/18: Compl:75%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1847 | 760095 | LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-171127 |  | Huawei |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1848 | 760195 | Core part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180957 |  | Huawei |  | 12/7/17: 36.715-02-02 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60% | 36.715-02-02 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1849 | 760295 | Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180957 |  | Huawei |  | ¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1850 | 760096 | LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-170946 |  | LG Electronics |  |  |  | 76 | 39 |  |  | Mon 19/06/17 | NA
1851 | 760196 | Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL-Core | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180770 |  | LG Electronics |  | 12/7/17: 36.715-00-02 added;¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->80%¦ ¦27/6/18: | 36.715-00-02 | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1852 | 760296 | Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL-Perf | 2 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/06/18 | 100% | RP-180770 |  | LG Electronics |  | 19/9/17: CD:Sat 15/09/18->Fri 15/06/18¦ 8/1/18: Compl:0%->50%¦27/3/18: Compl:50%->80% ¦27/6/18: Compl:80%->100%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1853 | 770064 | UE Conformance Test Aspects – Rel-15 CA configurations | LTE_CA_R15-UEConTest | 1 | Rel-15 | R5 | Fri 15/09/17 | Wed 08/09/21 | 22% | RP-181202 |  | Ericsson |  | ¦8/1/18: Compl:0%->7%¦27/3/18: Compl:7%->8% ;; 8/10/20: 9%->22; 8/10/20: FCD:14/06/2019->12/20; 8/4/21: FCD:11/12/2020->09/21; 8/4/21: 22%->22 |  | 77 | 39 |  |  | Tue 19/09/17 | Thu 08/04/21
1854 | 580037 | Stopped - LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS | 1 | Rel-15 |  | Sat 15/12/12 | Fri 15/12/17 | 82% | RP-130703 | - | Nokia | petri.j.vasenkari@nokia.com | Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022 | UTRA, LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 15/09/14
1855 | 580137 | Stopped - Core part: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS-Core | 2 | Rel-15 | R4 | Sat 15/12/12 | Fri 15/12/17 | 85% | RP-172035 |  | Nokia | petri.j.vasenkari@nokia.com | ¦CD:Wed 18/03/15->Sun 15/03/15¦Rel-12->Rel-13¦Stat Rep: RP-141158->RP-141973 1st Apr 15: Compl:35%->40% 1st Apr 15: Stat Rep: RP-141973->RP-150104 03/07/15: Stat Rep: RP-150104->RP-150615 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150615->RP-15 | 25.144, New 37.144 | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/01/18
1856 | 630011 | Stopped - Test part: LTE UE TRP and TRS and UTRA Hand Phantom | LTE_UTRA_TRP_TRS-UEConTest | 2 | Rel-15 | R5 | Sat 15/03/14 | Fri 15/12/17 | 78% | RP-150070 |  | ZTE | TAYLOR Carolyn (carolyn.tayl@zte.com.cn) | Stat Rep: RP-141132->RP-141848¦Rel 12->Rel13 1st Apr 15: Compl:15%->20% 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: WID: RP-140090->RP-150070 1st Apr 15: Stat Rep: RP-141848->RP-150069 03/07/15: Compl:20%->25% 03/07/15: Stat Rep: RP-150069-> | New 37.544 | 63 | 32 |  |  | Tue 04/03/14 | Mon 08/01/18
1857 | 790053 | Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh | 1 | Rel-15 | R6 | Thu 15/03/18 | Sat 15/09/18 | 90% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh |  | 79 | 40 |  |  | Tue 27/03/18 | NA
1858 | 790153 | Core part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh-Core | 2 | Rel-15 | R6 | Thu 15/03/18 | Fri 14/09/18 | 80% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%; |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 27/06/18
1859 | 790253 | Perf. part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh-Perf | 2 | Rel-15 | R6 | Thu 15/03/18 | Sat 15/09/18 | 100% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;¦10/9/18: 80%->100 |  | 79 | 40 |  |  | Tue 27/03/18 | Mon 10/09/18
1860 | 790056 | LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL | 1 | Rel-15 | R4 | Thu 15/03/18 | Fri 15/06/18 | 100% | RP-180573 |  | KDDI |  | basket CA WI¦no Perf. part |  | 79 | 40 |  |  | Tue 27/03/18 | NA
1861 | 790156 | Core part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL-Core | 2 | Rel-15 | R4 | Thu 15/03/18 | Fri 15/06/18 | 100% | RP-181311 |  | KDDI |  | basket CA WI¦no Perf. part¦27/6/18: Compl:0%->100%¦… |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 27/06/18
1862 | 801203 | Perf. Part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL-Perf | 2 | Rel-15 | R4 | Tue 15/05/18 | Fri 15/06/18 | 100% | RP-181311 |  | KDDI |  | Perf. Part was introduced and completed at RAN #80 |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1863 | 790055 | Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72 | 1 | Rel-15 | R4 | Thu 15/03/18 | Fri 14/12/18 | 100% | RP-180178 |  | Airbus |  | to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72; |  | 79 | 40 |  |  | Tue 27/03/18 | NA
1864 | 790155 | Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72-Core | 2 | Rel-15 | R4 | Thu 15/03/18 | Fri 15/06/18 | 100% | RP-180688 |  | Airbus |  | to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16 |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 27/06/18
1865 | 810062 | UE Conformance Test Aspects - Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72-UEConTest | 2 | Rel-15 | R5 | Fri 14/09/18 | Fri 14/12/18 | 100% | RP-181629 |  | Airbus |  | 16/1/19: 0%->100 | [5 empty] | Tue 25/09/18 | Wed 16/01/19
1866 | 0 | Release 15 Studies | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1867 | 0 | Release 15 Studies on 5G | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1868 | 730056 | Study on management aspects of virtualized network functions that are part of the NR | FS_MA_RNVNF | 1 | Rel-15 | S5 | Mon 19/09/16 | Fri 15/12/17 | 100% | SP-160703 |  | Intel (Joey Chou | joey.chou@intel.com | 6/10/16: Acronym FS_MA_RVNF ->FS_MA_RNVNF ¦6/10/16: 32.864 added¦1/12/16: 0%->5¦6/3/17: 5%->10¦7/6/17: 10%->40¦11/9/17: 40%->70¦15/12/17: 70%->100¦15/12/17: FCD:09/17->12/17 | 32.864 | 73 | 37 |  |  | Mon 19/09/16 | Fri 15/12/17
1869 | 750043 | Study on CU-DU lower layer split for New Radio | FS_NR_CU_DU_LLS | 1 | Rel-15 | R3 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-180684 |  | NTT DOCOMO |  | CU = central unit, DU = distributed unit¦results will be captured in existing TR 38.801¦19/9/17: Compl:0%->30%¦19/9/17: WID: RP-170818->RP-171717¦15/12/17: 38.816 added;¦8/1/18: Compl:30%->95%¦8/1/18: CD:Fr ¦27/6/18 | 38.816 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1870 | 750040 | Study on NR to support non-terrestrial networks | FS_NR_nonterr_nw | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-171450 |  | Thales |  | TR 38.8XX19/6/17: Compl:0%->25%19/6/17: CD:Fri 15/12/17->Thu 15/03/1819/6/17: WID: RP-170717->RP-171450¦30/6/17: 38.811 added;¦19/9/17: Compl:25%->40%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/18¦27/3/18: Compl:40%->45%¦27/6/18: Compl:4 | 38.811 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1871 | 710045 | STOPPED AT SA#77 - SA3 aspects on Study on Architecture and Security for Next Generation System | FS_NSA | 1 | Rel-15 | S3 | Tue 01/03/16 | Tue 12/12/17 | 100% | SP-160727 |  | Vesa Torvinen, Ericsson | vesa.torvinen@ericsson.com | 19/9/16: 0%->25¦22/9/16: WID:SP-160227->SP-160727¦22/9/16: FCD:12/16->03/17¦1/12/16: 25%->45¦6/3/17: 45%->60¦7/6/17: FCD:03/17->12/17 so Rel-14->Rel-15¦7/6/17: 60%->65¦11/9/17: 65%->100 | 33.899 | 71 | 36 |  |  | Tue 01/03/16 | Mon 11/09/17
1872 | 760080 | Study on separation of CP and UP for split option 2 of NR | FS_NR_CPUP_Split | 1 | Rel-15 | R3 | Thu 15/06/17 | Fri 15/12/17 | 100% | RP-171905 |  | Ericsson |  | 19/9/17: Compl:0%->45%19/9/17: WID: RP-171421->RP-171905¦15/12/17: 38.806 added;¦8/1/18: Compl:45%->100% | 38.806 | 76 | 39 |  |  | Fri 16/06/17 | Mon 08/01/18
1873 | 0 | Release 15 Studies on 4G/LTE | - | 1 | Rel-15 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1874 | 710064 | Stopped - Study on LTE bandwidth flexibility enhancements | FS_LTE_BW_flex | 1 | Rel-15 | R4 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-161670 |  | Huawei |  | 1/7/16: Compl:0%->50%¦28/7/16: 36.740 added¦26/9/16: WID: RP-161328->RP-161670¦20/12/16: CD:Thu 15/0;21/3/17: CD:Fri 15 12/7/17: 50%->100 since declared as stopped | 36.74 | 71 | 36 |  |  | Tue 22/03/16 | Wed 12/07/17
1875 | 730070 | Study on interference cancellation receiver for LTE BS | FS_LTE_IC_BS | 1 | Rel-15 | R4 | Thu 15/09/16 | Thu 15/06/17 | 100% | RP-161485 |  | China Telecom |  | 6/10/16: 36.766 added¦20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%¦19/6/17: Compl:65%->100% | 36.766 | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1876 | 740066 | Study on uplink data compression in LTE | FS_LTE_UDC | 1 | Rel-15 | R2 | Thu 15/12/16 | Fri 15/09/17 | 100% | RP-170403 |  | CATT |  | ¦21/3/17: WID: RP-162541->RP-170403¦21/3/17: 36.754 added;19/6/17: Compl:0%->90%¦19/9/17: Compl:90%->100 | 36.754 | 74 | 38 |  |  | Tue 20/12/16 | Tue 19/09/17
1877 | 760081 | Study on LTE DL 8Rx antenna ports | FS_LTE_8Rx_AP_DL | 1 | Rel-15 | R4 | Thu 15/06/17 | Fri 15/12/17 | 100% | RP-171753 |  | Huawei |  | 12/7/17: 36.757 added;¦19/9/17: Compl:0%->35%¦ 8/1/18: Compl:35%->100% | 36.757 | 76 | 39 |  |  | Fri 16/06/17 | Mon 08/01/18
1878 | 0 | Other Release 15 Studies | - | 1 | Rel-15 |  | Fri 08/09/17 | Fri 16/03/18 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1879 | 770026 | Study on Update to fixed-point basic operators | FS_BASOP | 1 | Rel-15 | S4 | Fri 08/09/17 | Thu 15/03/18 | 100% | SP-170613 |  | Jelinek, Milan, VoiceAge Corporation | Milan.Jelinek@USherbrooke.ca | 15/12/17: 26.973 added;¦15/12/17: 0%->80¦16/3/18: 80%->100 | New; 26.973 | 77 | 39 |  |  | Fri 08/09/17 | Fri 16/03/18
1880 | 710063 | Study on further enhancements to LTE Device to Device (D2D), UE to network relays for IoT (Internet of Things) and wearables | FS_feD2D_IoT_relay_wearable | 1 | Rel-15 | R2 | Tue 15/03/16 | Fri 15/12/17 | 100% | RP-170295 |  | Qualcomm |  | 1/7/16: Compl:0%->2%;26/9/16: Compl:2%->5%¦6/10/16: 36.746 added¦20/12/16: Compl:5%->15%;21/3/17: Compl:15%->35%…19/6/17: ; | 36.746 | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
1881 | 710049 | Study on Energy Efficiency Aspects of 3GPP Standards | FS_ENEFF | 1 | Rel-15 | SP | Fri 11/03/16 | Fri 09/06/17 | 100% | SP-160224 | _SP-170533 | Orange, Xiaobao Chen | xiaobao.chen@orange.com | 28/7/16: 21.866 added;¦9/6/17: FCD:12/16->9/6/17 (Rel-14->Rel-15)¦0%->100 | 21.866 | 71 | 36 |  |  | Fri 11/03/16 | Fri 09/06/17
1882 | 750049 | Study on evaluation methodology of new V2X use cases for LTE and NR | FS_LTE_NR_V2X_eval | 1 | Rel-15 | R1 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-171093 |  | LG Electronics |  | TR 38.8XX19/6/17: WID: RP-170837->RP-171093¦12/7/17: 37.885 added;19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->10%¦8/1/18: CD:Fri 15/12/17->Thu 15/03/18¦27/3/18: Compl:10%->30%¦27/3/18: CD:Thu 15/03/18->Fri 15/06/18¦27/ | 37.885 | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1883 | 760042 | Study on FEC for MC Services | FS_FEC_MCS | 1 | Rel-15 | S4 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170337 |  | Lambrou, John - Motorola Solutions | john (dot) lambrou (at) motorolasolutions (dot) com | 11/9/17: 0%->15¦15/12/17: 15%->60¦15/12/17: FCD:12/17->03/18¦16/3/18: 60%->100 | 26.881 | 76 | 39 |  |  | Sat 03/06/17 | Fri 16/03/18
1884 | 710032 | Study on Enhanced Isolated E-UTRAN Operation for Public Safety | FS_IOPS_LB | 1 | Rel-15 | S2 | Mon 07/03/16 | Thu 15/12/16 | 100% | SP-160171 |  | Antoine Mouquet, Orange | antoine.mouquet@orange.com | 9/6/16: 0%->6¦28/7/16: 23.798 added¦1/12/16: FCD:09/16->12/16¦1/12/16: 6%->15. 7/12/16: Moved from Rel-14 according to SP-160806.¦6/3/17: 15%->50¦7/6/17: 50%->100 | 23.798 | 71 | 36 |  |  | Mon 07/03/16 | Wed 07/06/17
1885 | 740016 | Study on Management Enhancement of CUPS of EPC Nodes | FS_MECUPS | 1 | Rel-15 | S5 | Thu 01/12/16 | Tue 12/12/17 | 100% | SP-160925 |  | Huawei; Jiang, Junyi | jiangjunyi@huawei.com | 6/3/17: 0%->5¦7/6/17: 5%->40¦7/6/17: FCD:09/17->12/17¦11/9/17: 40%->50¦15/12/17: 50%->100 | 32.867 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1886 | 720041 | Study on Technical Requirements for a new secure platform for 3GPP applications | FS_NG_SP | 1 | Rel-15 | C6 | Mon 13/06/16 | Tue 12/09/17 | 100% | CP-160371 |  | Heiko Kruse | heiko.kruse@safrangroup.com | 16/9/16: 0%->15. ¦5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet)¦5/6/17: FCD:12/16->09/20¦15/12/17: 70%->100 | 31.801 | 72 | 37 |  |  | Mon 13/06/16 | Fri 15/12/17
1887 | 750030 | Study on technical requirements for a new secure platform for 3GPP applications | FS_NG_SP2 | 1 | Rel-15 | C6 | Fri 03/03/17 | Thu 14/09/17 | 100% | CP-170183 |  | Heiko Kruse | heiko.kruse@safrangroup.com | 21/3/17: 31.801 added;¦11/9/17: 0%->70¦15/12/17: 70%->100 | 31.801 | 75 | 38 |  |  | Fri 03/03/17 | Fri 15/12/17
1888 | 750041 | Study on scheduling enhancements with CA for UMTS | FS_UTRA_CA_sched_enh | 1 | Rel-15 | R1 | Wed 15/03/17 | Thu 15/06/17 | 100% | RP-171065 |  | Huawei |  | TR 25.7XX¦19/6/17: Compl:0%->100%¦ 12/7/17: 25.708 added; | 25.708 | 75 | 38 |  |  | Tue 21/03/17 | Wed 12/07/17
1889 | 750050 | Study on Architecture Evolution for E-UTRAN | FS_LTE_arch_evo | 1 | Rel-15 | R3 | Wed 15/03/17 | Thu 15/03/18 | 100% | RP-172707 |  | China Unicom |  | TR 36.8XX¦12/7/17: 36.756 added;19/9/17: Compl:0%->40%¦15/12/17: 37.876 added;¦8/1/18: Compl:40%->827/3/18: Compl:85%->100% | 36.756; 37.876 | 75 | 38 |  |  | Tue 21/03/17 | Tue 27/03/18
1890 | 590045 | Study on Enhanced Acoustic Test Specifications | FS_SEATS | 1 | Rel-15 | S4 | Mon 18/03/13 | Tue 12/12/17 | 100% | SP-130028 | - | Knowles, Intel | Scott Isabelle (Knowles), David Isherwood (Intel) | SP#65 completion 09/14=>12/14. Moved to Rel-13. Dec.14: 30->35%, CD 12/14->03/15. Mar.15: CD: 06/16. 40%¦June2015: Compl:40%->45. . 15/4/16: moved from R 21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: FCD:06/17->12/17¦11/9/17: 80%->8 | 26.931 | 59 | 30 |  |  | Wed 20/02/13 | Fri 15/12/17
1891 | 720025 | Study on User Services Enhancements in 3GPP for TV Services | FS_USE_3GPP_4_TV | 1 | Rel-15 | S4 | Mon 13/06/16 | Tue 12/09/17 | 100% | SP-160273 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 19/9/16: 0%->30¦6/10/16: 26.917 added¦1/12/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: 60%->75¦6/3/17: FCD:03/17->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: 75%->80¦7/6/17: FCD:06/17->09/17¦11/9/17: 80%->100 | 26.9xx; 26.917 | 72 | 37 |  |  | Sat 11/06/16 | Mon 11/09/17
1892 | 700047 | Study on OAM support for assessment of energy efficiency in mobile access networks | FS_OAM_EE | 1 | Rel-15 | S5 | Mon 02/11/15 | Fri 09/06/17 | 100% | SP-160430 |  | Cornily,Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 13/6/16: WID:SP-150674->SP-160430¦13/6/16: 0%->55¦1/12/16: 55%->80¦6/3/17: FCD:03/17->06/17¦6/3/17: 80%->90¦21/3/17: moved from rel-14¦7/6/17: 90%->100 | 32.856 | 70 | 36 |  |  | Mon 07/12/15 | Wed 07/06/17
1893 | 730055 | Study on Management aspects of selected IoT-related features | FS_OAM_IOT | 1 | Rel-15 | S5 | Mon 19/09/16 | Tue 12/12/17 | 100% | SP-160611 |  | Cisco Systems / Yanover, Vladimir |  | 6/10/16: 32.857 added¦1/12/16: 0%->5¦21/3/17: moved from Rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 5%->20¦11/9/17: 20%->30¦15/12/17: 30%->45¦16/3/18: 45%->100 | 32.857 | 73 | 37 |  |  | Mon 19/09/16 | Fri 16/03/18
1894 | 700048 | Study on OAM aspects of SON for AAS-based deployments | FS_OAM_SON_AAS | 1 | Rel-15 | S5 | Mon 02/11/15 | Fri 09/06/17 | 100% | SP-150677 |  | Nokia Networks (Yizhi Yao) | Yizhi.yao@nokia.com | 13/6/16: 0%->40¦19/9/16: FCD:09/16->12/16¦19/9/16: 40%->60¦1/12/16: FCD:12/16->03/17¦1/12/16: 60%->70¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: 70%->100 | (new) | 70 | 36 |  |  | Mon 07/12/15 | Wed 07/06/17
1895 | 760056 | Study on OAM aspects of LTE and WLAN integration | FS_OAM_LWI | 1 | Rel-15 | S5 | Mon 05/06/17 | Thu 15/03/18 | 100% | SP-170480 |  | Yizhi Yao, Intel Corporation | yizhi.yao@intel.com | 30/6/17: 32.868 added;¦11/9/17: 0%->10¦15/12/17: 10%->50¦16/3/18: 50%->90¦7/6/18: 90%->100 | new; 32.868 | 76 | 39 |  |  | Sat 03/06/17 | Thu 07/06/18
1896 | 680054 | Study on Overload Control for Diameter Charging Applications | FS_DOCME_CH | 1 | Rel-15 | S5 | Thu 18/06/15 | Fri 15/12/17 | 100% | SP-170481 |  | GUO Wenjie, ZTE | guo.wenjie1@zte.com.cn | Aug2015: moved to Rel-14 (email CT and EG)¦07/09/15: 0%->5¦7/3/16: 5%->10¦13/6/16: FCD:03/16->09/16¦19/9/16: FCD: 09/16->06/17¦6/3/17: FCD:03/17->12/17¦21/3/17: moved from rel-14¦7/6/17: 10%->25¦8/6/17: WID:SP-150310->SP-170481¦11/9/17: 25%->3 | New 32.869 | 68 | 35 |  |  | Fri 26/06/15 | Fri 15/12/17
1897 | 730053 | Study on forward compatibility for 3GPP Diameter Charging Applications | FS_FWDCA | 1 | Rel-15 | S5 | Mon 19/09/16 | Thu 15/06/17 | 100% | SP-160608 |  | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | 6/10/16: 32.870 added¦1/12/16: 0%->10¦21/3/17: moved from rel-14¦11/9/17: 10%->40¦15/12/17: 40%->100 | 32.87 | 73 | 37 |  |  | Mon 19/09/16 | Fri 15/12/17
1898 | 710007 | Study on Implementation for the Partitioning of Itf-N | FS_IMP_ITFN | 1 | Rel-15 | S5 | Tue 01/03/16 | Thu 15/03/18 | 100% | SP-160020 |  | Hu, Yaxi, China Mobile | huyaxi@cmdi.chinamobile.com | 13/6/16: 0%->10¦19/9/16: 10%->35¦1/12/16: 35%->40¦6/3/17: FCD:03/17->03/18¦21/3/17: moved from rel-14¦7/6/17: 40%->60¦11/9/17: 60%->80¦15/12/17: 80%->100 | New 32.880 | 71 | 36 |  |  | Tue 01/03/16 | Fri 15/12/17
1899 | 720046 | Study on Management Aspects of Next Generation Network architecture and features | FS_MAN_NGNAF | 1 | Rel-15 | S5 | Mon 13/06/16 | Tue 12/12/17 | 100% | SP-160399 |  | Nokia Networks, Yizhi Yao | Yizhi.yao@nokia.com | 28/7/16: 28.802 added¦19/9/16: 0%->5¦1/12/16: 5%->10¦6/3/17: FCD:03/17->06/17¦6/3/17: 10%->40¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 40%->60¦11/9/17: 60%->70¦15/12/17: 70%->100 | (new); 28.802 | 72 | 37 |  |  | Mon 13/06/16 | Fri 15/12/17
1900 | 720047 | Study on Management and Orchestration Architecture of Next Generation Network and Service | FS_NGNS_MOA | 1 | Rel-15 | S5 | Mon 13/06/16 | Tue 12/12/17 | 100% | SP-160400 |  | Huawei Technologies, Zou Lan | zoulan@huawei.com | 28/7/16: 28.800 added¦19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 10%->25¦11/9/17: 25%->30¦15/12/17: 30%->100 | xy.abc; 28.800 | 72 | 37 |  |  | Mon 13/06/16 | Fri 15/12/17
1901 | 720063 | Study on SON for eCoMP for LTE | FS_LTE_SON_eCOMP | 1 | Rel-15 | R3 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-161181 |  | Nokia |  | 26/9/16: Compl:0%->10%. ¦20/12/16: Compl:10%->40%21/3/17: Compl:40%->60%¦19/6/17: Compl:60%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
1902 | 650036 | Stopped - Study on IMS Enhanced Spoofed Call Prevention and Detection | FS_ESCAPADES | 1 | Rel-15 | S3 | Fri 19/09/14 | Fri 15/12/17 | 100% | SP-140611 | - | Sprint | Gregory.schumacher@sprint.com | Dec.14: TR number added. 3/3/15: 0->5%¦June2015: Compl:5%->25¦9/12/15: 25%->30¦21/3/17: moved from Rel-13¦21/3/17: FCD:09/15->12/17¦7/6/17: Stopped (30%->100%) | 33.832 | 64 | 33 |  |  | Thu 04/09/14 | Wed 07/06/17
1903 | 760060 | Study on Volume Based Charging Aspects for VoLTE | FS_VBCLTE | 1 | Rel-15 | S5 | Mon 05/06/17 | Thu 14/06/18 | 100% | SP-170594 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 30/6/17: 32.848 added;¦11/9/17: 0%->5¦15/12/17: 5%->35¦16/3/18: 35%->45¦7/6/18: 45%->100 | new; 32.848 | 76 | 39 |  |  | Mon 05/06/17 | Thu 07/06/18
1904 | 710015 | STOPPED - Study on UE characteristics and performance for Video | FS_UE_VTPerf | 1 | Rel-15 | S4 | Tue 01/03/16 | Thu 15/06/17 | 100% | SP-160085 |  | Stéphane PROUST, Orange | stephane.proust@orange.com | 11/6/16: 0%->10¦19/9/16: 10%->30, FCD: 12/16->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: Stopped, so 30%->100 | 26.932 | 71 | 36 |  |  | Tue 01/03/16 | Wed 07/06/17
1905 | 780061 | Study on UE Application Layer Data Throughput Performance Expansion for CA | FS_UE_App_Data_Perf_CA | 1 | Rel-15 | R5 | Fri 15/12/17 | Fri 15/06/18 | 100% | RP-180203 |  | PCTEST Engineering Lab |  | compare REL-11 SI FS_UE_App_Data_Perf¦note: SI FS_UE_App_Data_Perf_CA is addressing 2DL/1UL involving also an unlicensed carrier of REL-13 LTE_LAA¦instead of a new TR, the TR 37.901 will be updated for REL-15¦ ; |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1906 | 760064 | Study on system and functional aspects of Energy Efficiency in 5G networks | FS_EE_5G | 1 | Rel-15 | S5 | Mon 05/06/17 | Fri 14/12/18 | 100% | SP-170489 |  | CORNILY, Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 30/6/17: 32.872 added;¦11/9/17: 0%->5¦15/12/17: 32.972 added;¦15/12/17: 5%->40¦16/3/18: 40%->60¦7/6/18: 60%->65¦7/6/18: FCD:06/18->12/18¦10/9/18: 65%->85¦7/12/18: 85%->100 | new; 32.872; 32.972 | 76 | 39 |  |  | Mon 05/06/17 | Fri 07/12/18
1907 | 0 | --- RELEASE 14 --- | - | 1 | Rel-14 |  | Fri 12/12/14 | Fri 12/12/14 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1908 | 0 | Release 14 on Mission Critical | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1909 | 700027 | Mission Critical Improvements | MCImp | 1 | Rel-14 |  | Tue 14/04/15 | Fri 13/12/19 | 100% |  |  |  |  | Umbrella Feature |  | 70 | 36 |  |  | Mon 07/12/15 | Fri 11/12/15
1910 | 700029 | Mission Critical Push to Talk over LTE Realignment | MCImp-MCPTTR | 2 | Rel-14 | S1 | Mon 07/12/15 | Wed 15/06/16 | 100% | SP-150821 | SP-170406 | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160102¦0->75%¦9/6/16: 75%->100 | 22.179 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1911 | 740022 | Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT | 2 | Rel-14 |  | Mon 13/06/16 | Wed 14/06/17 | 100% | SP-160490 |  | Lazara, Dom | dom.lazara@motorolasolutions.com | 28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100 | 23.379, 23.280, 23.281, 23.282; 23.379 | 72 | 37 |  |  | Mon 13/06/16 | Thu 01/12/16
1912 | 720056 | Stage 2 of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT | 3 | Rel-14 | S6 | Mon 13/06/16 | Thu 15/12/16 | 100% | SP-160490 |  | Lazara, Dom | dom.lazara@motorolasolutions.com | 28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100 | 23.379, 23.280, 23.281, 23.282; 23.379 | 72 | 37 |  |  | Mon 13/06/16 | Thu 01/12/16
1913 | 740023 | Stage 3 of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 3 | Rel-14 | ct | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
1914 | 740024 | CT1 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C1 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 6/3/17: 0%->20¦5/6/17: 20%->95¦14/9/17: 95%->97¦15/12/17: 97%->100 | 24.379, 24.380, 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1915 | 740025 | CT3 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C3 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1916 | 740026 | CT4 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C4 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 6/3/17: 0%->100 | 23.003, 29.228, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1917 | 740027 | CT6 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C6 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 5/6/17: 0%->100. No work identified for CT6. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1918 | 700028 | Mission Critical Services Common Requirements | MCImp-MCCoRe | 2 | Rel-14 | S1 | Mon 07/12/15 | Wed 15/06/16 | 100% | SP-150822 | SP-170407 | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160104¦0->75%¦9/6/16: 75%->100 | New 22.280 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1919 | 720055 | Common functional architecture to support mission critical services | MCImp-MC_ARCH | 2 | Rel-14 | S6 | Mon 13/06/16 | Thu 15/12/16 | 100% | SP-160489 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.280 added¦19/9/16: 0%->40¦1/12/16: 40%->95¦3/3/17: 95%->100 | 23.280, 23.379, 23.281, 23.282; 23.280 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
1920 | 720053 | Mission Critical Video over LTE | MCImp-MCVideo | 2 | Rel-14 |  | Tue 14/04/15 | Wed 14/06/17 | 100% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106¦0->80%¦9/6/16: 80%->100 |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1921 | 670006 | Study on Mission Critical Video over LTE | FS_MCVideo | 3 | Rel-14 | S1 | Tue 14/04/15 | Tue 15/12/15 | 100% | SP-150048 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added¦June2015: Compl:0%->50¦07/09/15: 50%->70¦7/12/15: 70%->100 | New 22.879 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
1922 | 700030 | Stage 1 of MCVideo | MCImp-MCVideo | 3 | Rel-14 | S1 | Mon 07/12/15 | Wed 15/06/16 | 100% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106¦0->80%¦9/6/16: 80%->100 | New 22.281 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1923 | 720051 | Stage 2 for MCVideo | MCImp-MCVideo | 3 | Rel-14 | S6 | Mon 13/06/16 | Thu 15/12/16 | 100% | SP-160491 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.281 added¦19/9/16: 0%->25¦1/12/16: 25%->95¦3/3/17: 95%->100 | 23.281, 23.280, 23.379, 23.282; 23.281 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
1924 | 750018 | MCVideo codecs and media handling | MCImp-MCVideo | 3 | Rel-14 | S4 | Wed 11/01/17 | Thu 16/03/17 | 100% | SP-170244 |  | John Lambrou (Motorola Solutions) | john (dot) lambrou (at) motorolasolutions (dot) com | 6/3/17: 0%->100 | 26.281 | 75 | 38 |  |  | Fri 03/03/17 | Mon 06/03/17
1925 | 740033 | Stage 3 of MCVideo | MCImp-MCVIDEO-CT | 3 | Rel-14 | ct | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com |  | 24.581, 24.281 | 74 | 38 |  |  | Thu 01/12/16 | NA
1926 | 740034 | CT1 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C1 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 6/3/17: 0%->25¦5/6/17: 25%->90¦14/9/17: 90%->100 | 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Thu 14/09/17
1927 | 740035 | CT3 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C3 | Thu 01/12/16 | Wed 15/03/17 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1928 | 740036 | CT4 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C4 | Thu 01/12/16 | Wed 15/03/17 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 6/3/17: 0%->100 | 23.003, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1929 | 740037 | CT6 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C6 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 5/6/17: 0%->100. No work identified for CT6. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1930 | 720054 | Mission Critical Data over LTE | MCImp-MCData | 2 | Rel-14 |  | Tue 14/04/15 | Wed 14/06/17 | 100% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100 |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 28/07/16
1931 | 670007 | Study on Mission Critical Data Communications | FS_MCDATA | 3 | Rel-14 | S1 | Tue 14/04/15 | Tue 15/12/15 | 100% | SP-150049 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added¦June2015: Compl:0%->20¦07/09/15: 20%->90¦7/12/15: 90%->100 | New 22.880 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
1932 | 700031 | Stage 1 of MCData | MCImp-MCData | 3 | Rel-14 | S1 | Mon 07/12/15 | Wed 15/06/16 | 100% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100 | New 22.282 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1933 | 720052 | Stage 2 for MCData | MCImp-MCData | 3 | Rel-14 | S6 | Mon 13/06/16 | Thu 15/12/16 | 100% | SP-160492 |  | David Freeman (UK Home Office) | david@dnf-consulting.co.uk | 28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100 | 23.282 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
1934 | 740028 | Stage 3 of MCData | MCImp-MCDATA-CT | 3 | Rel-14 | ct | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com |  | 24.582, 24.282 | 74 | 38 |  |  | Thu 01/12/16 | Wed 14/06/17
1935 | 740029 | CT1 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C1 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 6/3/17: 0%->10¦5/6/17: 10%->65¦5/6/17: 65%->90¦14/9/17: 90%->96¦15/12/17: 96%->100 | 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
1936 | 740030 | CT3 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C3 | Thu 01/12/16 | Wed 15/03/17 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1937 | 740031 | CT4 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C4 | Thu 01/12/16 | Wed 15/03/17 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 6/3/17: 0%->100 | 23.003, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1938 | 740032 | CT6 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C6 | Thu 01/12/16 | Wed 14/06/17 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | No work identified. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1939 | 730047 | Security of the Mission Critical Service | MCSec | 2 | Rel-14 | S3 | Mon 19/09/16 | Thu 15/06/17 | 100% | SP-160566 |  | Haigh, Peter, CESG | peter.haigh@cesg.gsi.gov.uk | 6/10/16: 33.180 added¦1/12/16: 0%->25¦6/3/17: 25%->60¦7/6/17: 60%->85¦11/9/17: 85%->100 | 33.18 | 73 | 37 |  |  | Mon 19/09/16 | Mon 11/09/17
1940 | 790052 | UE Conformance Test Aspects - Mission Critical Improvements | MCImp-UEConTest | 2 | Rel-14 | R5 | Thu 15/03/18 | Fri 13/12/19 | 100% | RP-180527 |  | NIST |  | tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements)¦to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).;; 25/9/20: 5%->100 |  | 79 | 40 |  |  | Tue 27/03/18 | Fri 25/09/20
1941 | 730008 | Protocol enhancements for MCPTT over LTE | MCPTTProtoc1 | 1 | Rel-14 | ct | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | This Feature is a stage-3 only feature that fixes/enhances MCPTT protocol level (not visible from stage2). Not to be confused with Rel-14 MCPTT Stage 3. |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1942 | 730009 | CT1 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C1 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 6/3/17: 5%->100 | 24.229, 24.379, 24.380, 24.381, 24.382, 24.383, 24.384, 24.980 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1943 | 730010 | CT3 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C3 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 2/12/16: 0%->20¦6/3/17: 20%->100 | 29.165, 29.212, 29.213, 29.214 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1944 | 730011 | CT4 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C4 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 6/3/17: 0%->100 | 23.003, 23.008, 29.283 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1945 | 730012 | CT6 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C6 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 5/6/17: 0%->100. No more work identified. | 31.102 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1946 | 0 | Release 14 on V2X | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1947 | 720030 | LTE support for V2X services | V2XLTE | 1 | Rel-14 |  | Mon 09/02/15 | Fri 14/12/18 | 100% | SP-150573 |  |  |  | 7/12/15: 0%->5¦28/1/16: 22.185 added¦2/3/16: 5%->90¦9/6/16: 90%->100 | 22.278; 22.185 | 68 | 35 |  |  | Wed 09/09/15 | Thu 09/06/16
1948 | 690035 | Stage 1 for LTE support for V2X services | V2XLTE | 2 | Rel-14 | S1 | Wed 09/09/15 | Thu 17/03/16 | 100% | SP-150573 |  |  |  | 7/12/15: 0%->5¦28/1/16: 22.185 added¦2/3/16: 5%->90¦9/6/16: 90%->100 | 22.278; 22.185 | 68 | 35 |  |  | Wed 09/09/15 | Thu 09/06/16
1949 | 720011 | Architecture enhancements for LTE support of V2X services | V2XARC | 2 | Rel-14 | S2 | Thu 09/06/16 | Thu 15/12/16 | 100% | SP-160317 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 28/7/16: 23.285 added¦19/9/16: 0%->85¦1/12/16: FCD:09/16->12/16¦1/12/16: 85%->100 | 23.285 | 72 | 37 |  |  | Thu 09/06/16 | Thu 01/12/16
1950 | 740009 | Security aspect of LTE support of V2X services | V2XLTE-Sec | 2 | Rel-14 | S3 | Thu 01/12/16 | Thu 15/06/17 | 100% | SP-160955 |  | Huawei, Marcus Wong | mwong@huawei.com | 6/3/17: 0%->75¦7/6/17: 75%->100 | 33.185 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
1951 | 720090 | RAN aspects of LTE-based V2X Services | LTE_V2X | 2 | Rel-14 |  | Wed 15/06/16 | Fri 14/12/18 | 100% | RP-161298 |  | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1952 | 720190 | Core part: LTE-based V2X Services | LTE_V2X-Core | 3 | Rel-14 | R1 | Wed 15/06/16 | Wed 15/03/17 | 100% | RP-162519 | RP-170237 | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X26/9/16: Compl:0%->15%26/9/16: WID: RP-161298->RP-161894¦6/10/16: 36.786 added¦6/10/16: added¦20/12/16: Compl:15%->75% 21/3/17: Compl:75%->100% | 36.786; | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
1953 | 720290 | Perf. part: LTE-based V2X Services | LTE_V2X-Perf | 3 | Rel-14 | R4 | Wed 15/06/16 | Fri 15/09/17 | 100% | RP-162519 |  | LG Electronics |  | ¦26/9/16: WID: RP-161298->RP-161894¦20/12/16: WID: RP-161894->RP-162519¦20/12/16: Stat Rep: ->RP-162519¦19/6/17: Compl:0%->75%¦19/9/17: Compl:75%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 19/09/17
1954 | 760086 | UE Conformance Test Aspects - Support for LTE-based V2X Services | LTE_V2X-UEConTest | 3 | Rel-14 | R5 | Thu 15/06/17 | Fri 14/12/18 | 100% | RP-192556 |  | Huawei |  | ¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->40%¦ 27/3/18: Compl:40%->55%; 14/1/20: WID:RP-172356->RP-192556; 14/1/20: 65%->100 |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 14/01/20
1955 | 730026 | CT aspects of V2X Services | V2X-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1956 | 730027 | CT1 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C1 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 24.385 added¦6/10/16: 24.386 added¦2/12/16: 0%->65¦6/3/17: 65%->100 | 23.122, 24.301, 24.334; 24.385; 24.386 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1957 | 730028 | CT3 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C3 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 29.387 added¦2/12/16: 0%->40¦6/3/17: 40%->60¦5/6/17: 60%->100 | 29.212, 29.468; 29.387 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1958 | 730029 | CT4 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 29.388 added¦6/10/16: 29.389 added¦2/12/16: 0%->80¦6/3/17: 80%->100 | 23.003, 23.007, 23.008, 29.272; 29.388; 29.389 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1959 | 730030 | CT6 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C6 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 7/3/17: 0%->100 | 31.102, 31.111 | 73 | 37 |  |  | Fri 16/09/16 | Tue 07/03/17
1960 | 700019 | Study on LTE support for V2X services | FS_V2XLTE | 2 | Rel-14 |  | Mon 09/02/15 | Fri 17/06/16 | 100% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75 | New 22.885 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
1961 | 670009 | Study on Stage 1 of LTE support for V2X services | FS_V2XLTE_S1 | 3 | Rel-14 | S1 | Mon 09/02/15 | Mon 09/02/15 | 100% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75¦7/12/15: 75%->100 | New 22.885 | 67 | 34 |  |  | Mon 07/12/15 | Mon 07/12/15
1962 | 700050 | Study on Stage 2 of LTE support for V2X services | FS_V2XARC | 3 | Rel-14 | S2 | Mon 07/09/15 | Fri 17/06/16 | 100% | SP-150852 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 11/12/15: WID:SP-150625->SP-150743¦7/3/16: 10%->22¦7/3/16: WID:SP-150743->SP-150852¦9/6/16: 22%->80¦19/9/16: 80%->100 | 23.785 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
1963 | 760072 | Study on Security of LTE support for V2X services | FS_V2XARC_S3 | 3 | Rel-14 | S3 | Mon 07/09/15 | Fri 17/06/16 | 100% | SP-150852 |  |  |  | Introduced at 100% completion, as per SA3 report to SA#76 | 33.885 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
1964 | 680058 | RAN1 Study on LTE-based V2X Services | FS_LTE_V2X | 3 | Rel-14 | R1 | Mon 15/06/15 | Wed 15/06/16 | 100% | RP-161263 |  | LG Electronics |  | 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ¦28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15¦ | 33.885 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
1965 | 700061 | Support for V2V services based on LTE sidelink | LTE_SL_V2V | 1 | Rel-14 |  | Tue 15/12/15 | Fri 14/09/18 | 100% | RP-152293 |  | LG Electronics |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1966 | 700161 | Core part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Core | 2 | Rel-14 | R1 | Tue 15/12/15 | Thu 15/09/16 | 100% | RP-161603 |  | LG Electronics |  | 22/3/16: Compl:0%->15%22/3/16: WID: RP-152293->RP-1606491/7/16: Compl:15%->60%1/7/16: WID: RP-160649->RP-161272¦28/7/16: 36.785 added¦26/9/16: Compl:60%->100%¦26/9/16: WID: RP-161272->RP-161603 | 36.785 | 70 | 36 |  |  | Fri 01/01/16 | Mon 26/09/16
1967 | 700261 | Perf. part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 100% | RP-161603 |  | LG Electronics |  | 22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-16127226/9/16: WID: RP-161272->RP-161603¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:80%->100% |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 19/06/17
1968 | 730073 | UE Conformance Test Aspects - Support for V2V services based on LTE sidelink | LTE_SL_V2V-UEConTest | 2 | Rel-14 | R5 | Thu 15/09/16 | Fri 14/09/18 | 100% | RP-172358 |  | Huawei |  | ¦20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ;; 11/10/20: 98%->100 |  | 73 | 37 |  |  | Mon 26/09/16 | Sun 11/10/20
1969 | 0 | Release 14 on CIoT | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1970 | 710023 | Non-IP for Cellular Internet of Things (CIoT) for 2G/3G-GPRS(EC-EGPRS) | NonIP_GPRS | 1 | Rel-14 |  | Wed 02/03/16 | Thu 15/09/16 | 100% | SP-160196 | [5 empty] | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
1971 | 710024 | Non-IP for Cellular IoT for EC-EGPRS | NonIP_GPRS | 2 | Rel-14 | S2 | Wed 02/03/16 | Wed 15/06/16 | 100% | SP-160196 |  | Hans Ronneke, Ericsson | hans . Ronneke (a) ericsson . Com | 9/6/16: 0%->50¦19/9/16: 50%->100 | 23.060, 23.682, 23.401? | 71 | 36 |  |  | Wed 02/03/16 | Mon 19/09/16
1972 | 710025 | CT aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 2 | Rel-14 |  | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293 |  | 71 | 36 |  |  | Wed 02/03/16 | Sat 11/06/16
1973 | 710026 | CT1 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C1 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: 0%->50¦11/6/16: WID:CP-160161->CP-160293¦16/9/16: 50%->65¦2/12/16: 65%->100 | 24.008 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
1974 | 720069 | CT3 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C3 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦20/9/16: 0%->100 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | 72 | 37 |  |  | Wed 02/03/16 | Tue 20/09/16
1975 | 710027 | CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C4 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦2/12/16: 65%->100 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
1976 | 720092 | Further enhanced MTC for LTE | LTE_feMTC | 1 | Rel-14 |  | Wed 15/06/16 | Fri 14/09/18 | 100% | RP-161321 |  | Ericsson |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1977 | 720192 | Core part: Further enhanced MTC for LTE | LTE_feMTC-Core | 2 | Rel-14 | R1 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-170532 | RP-171441 | Ericsson |  | 26/9/16: Compl:0%->12%26/9/16: WID: RP-161321->RP-161464¦20/12/16: Compl:12%->70%¦20/12/16: WID: RP-161464->RP-16252021/3/17: Compl:70%->95% ¦21/3/17: CD19/6/17: Compl:95%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
1978 | 720292 | Perf. part: Further enhanced MTC for LTE | LTE_feMTC-Perf | 2 | Rel-14 | R4 | Wed 15/06/16 | Fri 15/12/17 | 100% | RP-170532 |  | Ericsson |  | ¦26/9/16: WID: RP-161321->RP-161464¦20/12/16: WID: RP-161464->RP-162520¦20/12/16: Stat Rep: ->RP-16252021/3/17: CD:Fri 15/09/17->Fri 15/12/1721/3/17 19/6/17: Compl:0%->35%19/9/17: Compl:35%->60%¦8/1/18: Compl:60%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 08/01/18
1979 | 770063 | UE Conformance Test Aspects - Further enhanced MTC for LTE | LTE_feMTC-UEConTest | 2 | Rel-14 | R5 | Fri 15/09/17 | Fri 14/09/18 | 100% | RP-192886 |  | Ericsson |  | ¦8/1/18: Compl:0%->6%¦27/3/18: Compl:6%->21%¦ ¦2¦26/3/19: WID:RP-180414->RP-190514; 26/6/19: WID:RP-190514->RP-190935; 14/1/20: WID:RP-190935->RP-192886; 26/3/20: 26%->100 |  | 77 | 39 |  |  | Tue 19/09/17 | Thu 26/03/20
1980 | 720093 | Enhancements of NB-IoT | NB_IOTenh | 1 | Rel-14 |  | Wed 15/06/16 | Fri 14/12/18 | 100% | RP-161324 |  | Huawei |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1981 | 720193 | Core part: Enhancements of NB-IoT | NB_IOTenh-Core | 2 | Rel-14 | R1 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-171060 | RP-171061 | Huawei |  | 26/9/16: Compl:0%->13%26/9/16: WID: RP-161324->RP-161901¦20/12/16: Compl:13%->70%¦21/3/17: Compl:70%->95%¦21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:95%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
1982 | 720293 | Perf. part: Enhancements of NB-IoT | NB_IOTenh-Perf | 2 | Rel-14 | R4 | Wed 15/06/16 | Fri 15/12/17 | 100% | RP-171060 |  | Huawei |  | 26/9/16: WID: RP-161324->RP-16190121/3/17: CD:Fri 15/09/17->Fri 15/12/17¦19/6/17: Compl:0%->50%¦19/6/17: WID: RP-161901->RP-171060¦19/9/17: Compl:50%->60%¦8/1/18: Compl:60%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 08/01/18
1983 | 770061 | UE Conformance Test Aspects - Enhancements of NB-IoT | NB_IOTenh-UEConTest | 2 | Rel-14 | R5 | Fri 15/09/17 | Fri 14/12/18 | 100% | RP-171781 |  | Huawei |  | ¦8/1/18: Compl:0%->5%27/3/18: Compl:5%->30%¦27/6/18: C; 11/10/20: 60%->100 |  | 77 | 39 |  |  | Tue 19/09/17 | Sun 11/10/20
1984 | 730021 | AT Commands for CIoT | AT_CIoT | 1 | Rel-14 | C1 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160477 |  | John-Luc Bakker |  | 2/12/16: 10%->95¦6/3/17: 95%->100 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1985 | 730359 | Extended architecture support for Cellular Internet of Things | CIoT_Ext | 1 | Rel-14 |  | Fri 17/06/16 | Tue 14/03/17 | 100% | SP-160732 |  | Intel : Puneet Jain | puneet.jain@intel.com |  | 23.401, 23.682, 23.060 | 73 | 37 |  |  | Mon 19/09/16 | Mon 19/09/16
1986 | 720081 | Study on extended architecture support for Cellular Internet of Things | FS_CIoT_Ext | 2 | Rel-14 | S2 | Fri 17/06/16 | Thu 15/12/16 | 100% | SP-160505 |  | Intel : Puneet Jain | puneet.jain@intel.com | 28/7/16: 23.730 added¦19/9/16: 0%->70¦1/12/16: FCD:03/17->12/16¦1/12/16: 70%->100 | 23.73 | 72 | 37 |  |  | Fri 17/06/16 | Thu 01/12/16
1987 | 730059 | Stage 2 of Extended architecture support for Cellular Internet of Things | CIoT_Ext | 2 | Rel-14 | S2 | Thu 15/09/16 | Fri 16/12/16 | 100% | SP-160830 |  | Intel : Puneet Jain | puneet.jain@intel.com | 1/12/16: 0%->100¦1/12/16: WID:SP-160732->SP-160830 | 23.401, 23.682, 23.060, 23.271 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
1988 | 740038 | Stage 3 of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 2 | Rel-14 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 21/3/17: 24.250 added; | 24.25 | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
1989 | 740039 | CT1 aspects of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 3 | Rel-14 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 6/3/17: 0%->50¦5/6/17: 50%->100 | 24.301, 24.008 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1990 | 740040 | CT4 aspects of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 3 | Rel-14 | C4 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 6/3/17: 0%->90¦5/6/17: 90%->100 | 23.008, 29.272, 29.002, 29.336, 29.128, 29.171, 29.172, 29.173 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1991 | 730077 | Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh | 1 | Rel-14 | R6 | Thu 15/09/16 | Fri 15/06/18 | 99% | RP-161806 |  | Nokia |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1992 | 730177 | Core part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh-Core | 2 | Rel-14 | R6 | Thu 15/09/16 | Thu 15/06/17 | 100% | RP-161806 | RP-171321 | Nokia |  | ¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80%19/6/17: Compl:80%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1993 | 730277 | Perf. part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh-Perf | 2 | Rel-14 | R6 | Thu 15/03/18 | Fri 15/06/18 | 100% | RP-161806 |  | Nokia |  | ¦20/12/16: Compl:0%->20% ¦21/3/17: Compl:20%->80%¦ 19/6/17: Compl:80%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1994 | 730083 | New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands | 1 | Rel-14 | R4 | Thu 15/09/16 | Fri 15/09/17 | 99% | RP-161890 |  | Ericsson |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1995 | 730183 | Core part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands-Core | 2 | Rel-14 | R4 | Thu 15/09/16 | Thu 15/06/17 | 100% | RP-170139 | RP-170970 | Ericsson |  | ¦20/12/16: Compl:0%->99% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17;19/6/17: Compl:99%->100%19/6/17: Stat Rep: ->RP-170970 |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1996 | 730283 | Perf. part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands-Perf | 2 | Rel-14 | R4 | Thu 15/09/16 | Thu 15/06/17 | 100% | RP-170139 |  | Ericsson |  | ¦20/12/16: Compl:0%->99% 21/3/17: Compl:99%->70% 19/6/17: Compl:70%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1997 | 750057 | UE Conformance Test Aspects - New band support for Rel-14 NB-IoT | NB_IOT_R14_bands-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Fri 15/09/17 | 100% | RP-170495 |  | Ericsson |  | tested: REL-14 NB_IOT_R14_bands-Core (which got an exception at RAN #75 to still complete in REL-14 by RAN #76); |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 19/09/17
1998 | 720006 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 1 | Rel-14 |  | Thu 17/09/15 | Fri 15/12/17 | 99% | SP-160310 | SP-170537 | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95 | 23.711 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
1999 | 690051 | Study on Enhancements of Dedicated Core Networks selection mechanism | FS_eDecor | 2 | Rel-14 | S2 | Thu 17/09/15 | Fri 18/03/16 | 100% | SP-150518 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95¦19/9/16: 95%->100 | 23.711 | 69 | 35 |  |  | Thu 17/09/15 | Mon 19/09/16
2000 | 720007 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 2 | Rel-14 | S2 | Thu 09/06/16 | Thu 15/09/16 | 100% | SP-160310 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 19/9/16: 70%->100 | 23.401, 23.060, 23.251 | 72 | 37 |  |  | Thu 17/09/15 | Mon 19/09/16
2001 | 730013 | CT aspects of eDecor | eDecor-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2002 | 730014 | CT1 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C1 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100 | 24.301, 24.008, 24.368 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2003 | 730015 | CT4 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 2/12/16: 0%->10¦6/3/17: 10%->100 | 29.303, 23.003, 23.008 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
2004 | 730016 | CT6 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C6 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100 | 31.102, 31.111 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2005 | 740067 | RAN aspects of eDECOR for UMTS and LTE | eDECOR-UTRA_LTE | 2 | Rel-14 | R3 | Thu 15/12/16 | Fri 15/12/17 | 99% | RP-162543 |  | Ericsson |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
2006 | 740167 | Core part: RAN aspects of eDECOR for UMTS and LTE | eDECOR-UTRA_LTE-Core | 3 | Rel-14 | R3 | Thu 15/12/16 | Wed 15/03/17 | 100% | RP-162543 | RP-170547 | Ericsson |  | 21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547 |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
2007 | 760088 | UE Conformance Test Aspects - Enhancements of Dedicated Core Networks for UTRA and LTE | eDECOR-UTRA_LTE-UEConTest | 3 | Rel-14 | R5 | Thu 15/06/17 | Fri 15/12/17 | 100% | RP-171899 |  | Ericsson |  | ¦19/9/17: Compl:0%->50%¦ 8/1/18: Compl:50%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Mon 08/01/18
2008 | 760002 | Deleted - GSM aspects of eDECOR | eDecor | 2 | Rel-14 | R6 | Tue 04/04/17 | Thu 15/06/17 | 100% | SP-160310 |  | Ericsson |  | Verbal addition by Paolo U. 21/09/17: verbal deletion by Paolo | 44.060, 44.018, 48.018 | 76 | 39 |  |  | Mon 29/05/17 | NA
2009 | 740078 | Addition of band 25 and 26 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B25_B26 | 1 | Rel-14 | R4 | Thu 15/12/16 | Wed 15/03/17 | 100% | RP-162572 |  | Sprint |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
2010 | 740178 | Core part: Addition of band 25 and 26 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B25_B26-Core | 2 | Rel-14 | R4 | Thu 15/12/16 | Wed 15/03/17 | 100% | RP-162572 |  | Sprint |  | ¦21/3/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
2011 | 740179 | Addition of bands 25 and 40 to LTE MTC cat.1 | LTE_MTCe2_L1_cat1_B25_B40-Core | 1 | Rel-14 | R4 | Thu 15/12/16 | Wed 15/03/17 | 100% | RP-162573 |  | Sprint |  | ¦21/3/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
2012 | 0 | Release 14 on WLAN | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
2013 | 720031 | EIR check for WLAN access to EPC | EWE | 1 | Rel-14 |  | Mon 02/11/15 | Thu 15/09/16 | 100% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60¦9/6/16: 60%->100 | 23.002, 23.402 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2014 | 700039 | Stage 2 of EWE | EWE | 2 | Rel-14 | S2 | Mon 02/11/15 | Fri 17/06/16 | 100% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60¦9/6/16: 60%->100 | 23.002, 23.402 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2015 | 720002 | CT aspects of EWE | EWE-CT | 2 | Rel-14 | ct | Mon 13/06/16 | Thu 15/09/16 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com |  |  | 72 | 37 |  |  | Mon 13/06/16 | NA
2016 | 720032 | CT1 aspects of EWE | EWE-CT | 3 | Rel-14 | C1 | Mon 13/06/16 | Thu 15/09/16 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com | 16/9/16: 0%->100 | 24.302 | 72 | 37 |  |  | Mon 13/06/16 | Fri 16/09/16
2017 | 720033 | CT4 aspects of EWE | EWE-CT | 3 | Rel-14 | C4 | Mon 13/06/16 | Thu 15/09/16 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com | 2/12/16: 0%->100 | 29.273 | 72 | 37 |  |  | Mon 13/06/16 | Fri 02/12/16
2018 | 730048 | Support of EAP Re-authentication Protocol for WLAN Interworking | ERP | 1 | Rel-14 |  | Fri 16/09/16 | Thu 16/03/17 | 100% | SP-160568 |  | ORANGE, Todor Gamishev | Todor dot Gamishev at Orange dot com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2019 | 730049 | Support of EAP Re-authentication Protocol for WLAN Interworking | ERP | 2 | Rel-14 | S3 | Fri 16/09/16 | Wed 15/03/17 | 100% | SP-160568 |  | ORANGE, Todor Gamishev | Todor dot Gamishev at Orange dot com | 1/12/16: 0%->90¦6/3/17: 90%->100 | 33.402 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
2020 | 730003 | CT aspects of ERP | ERP-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Thu 16/03/17 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2021 | 730045 | CT1 aspects of ERP | ERP-CT | 3 | Rel-14 | C1 | Fri 16/09/16 | Thu 16/03/17 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com | 2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100 | 24.302 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2022 | 730046 | CT4 aspects of ERP | ERP-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Thu 16/03/17 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com | 2/12/16: 0%->50¦6/3/17: 50%->95¦5/6/17: 95%->100 | 29.273, 23.008, 23.003 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2023 | 720019 | Phase 2 of the Support of Emergency services over WLAN | SEW2 | 1 | Rel-14 |  | Tue 01/09/15 | Wed 15/03/17 | 100% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com |  | new 23.771, 23.402, 23.167 | 72 | 37 |  |  | Wed 01/04/15 | Thu 09/06/16
2024 | 690033 | Study on Phase 2 of the Support of Emergency services over WLAN | FS_SEW2 | 2 | Rel-14 | S2 | Tue 01/09/15 | Thu 16/06/16 | 100% | SP-160173 |  | Laurent Thiebaut, Alcatel Lucent | Laurent.thiebaut@alcatel-lucent.com | June2015: Compl:0%->100, SP-150151->SP-150251¦7/12/15: 0%->30, FCD: 12/15->06/16¦7/3/16: 30%->75¦7/3/16: WID:SP-150251->SP-160173¦9/6/16: 75%->100 | new 23.771 | 67 | 34 |  |  | Wed 01/04/15 | Thu 09/06/16
2025 | 720018 | Support of Emergency services over WLAN - phase 2 | SEW2 | 2 | Rel-14 | S2 | Mon 13/06/16 | Thu 15/09/16 | 100% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com | 11/6/16: 0%->45¦19/9/16: 45%->100 | 23.402, 23.167 | 72 | 37 |  |  | Wed 01/04/15 | Mon 19/09/16
2026 | 730017 | CT aspects of SEW2 | SEW2-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 5/12/16: WID:CP-160476->CP-160694 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/12/16
2027 | 730018 | CT1 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C1 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 2/12/16: 20%->95¦5/6/17: 95%->100 | 24.302, 24.312, 24.301, 24.244, 24.229, 24.237 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2028 | 730019 | CT4 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 2/12/16: 0%->100 | 23.003, 29.272, 29.273, 29.274, 29.328 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
2029 | 730020 | Deleted - CT6 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C6 | Wed 14/12/16 | Wed 14/12/16 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | Deleted at CT6#82 | 31.102 | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2030 | 720076 | T-ADS supporting WLAN Access | TADS_WLAN | 1 | Rel-14 | S2 | Tue 15/03/16 | Thu 15/09/16 | 100% | SP-160488 | SP-170519 | Jiang Yi | jiangyi (at) chinamobile (dot) com | 19/9/16: 0%->100 | 23.292, 23.221, 23.402 | 72 | 37 |  |  | Fri 17/06/16 | Mon 19/09/16
2031 | 710075 | Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr | 1 | Rel-14 | R2 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-160600 |  | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2032 | 710175 | Core part: Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr-Core | 2 | Rel-14 | R2 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-160923 | RP-170330 | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923¦26/9/16: Compl:25%->45%¦20/12/16: Compl:45%->75%¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:75%->100% ¦21/3/17 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2033 | 0 | Release 14 on IMS | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
2034 | 700020 | Evolution to and Interworking with eCall in IMS | EIEI | 1 | Rel-14 |  | Mon 11/05/15 | Thu 15/03/18 | 100% | SP-150275 | SP-170538 | Kurt Bischinger |  | 12/15: created by MCC to distinguish Stage 1 from Stage 2 | 22.101 | 68 | 35 |  |  | Mon 07/12/15 | Tue 09/06/15
2035 | 680004 | Stage 1 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S1 | Mon 11/05/15 | Fri 19/06/15 | 100% | SP-150275 |  | Kurt Bischinger |  |  | 22.101 | 68 | 35 |  |  | Tue 09/06/15 | Tue 09/06/15
2036 | 700021 | Stage 2 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S2 | Fri 11/12/15 | Fri 10/06/16 | 100% | SP-150623 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 7/3/16: 0%->20¦9/6/16: 20%->100. FCD: 03/16->06/16 | 23.167, 23.401 | 68 | 35 |  |  | Mon 07/12/15 | Thu 09/06/16
2037 | 710020 | CT aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 2 | Rel-14 |  | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  |  | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
2038 | 710021 | CT1 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C1 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 11/6/16: 0%->35¦16/9/16: 35%->85¦2/12/16: 85%->100 | 24.229, 24.301 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
2039 | 720068 | (IETF) Next-Generation Pan-European eCall (draft-ietf-ecrit-ecall) | EIEI-CT | 3 | Rel-14 | C1-IETF | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160053 |  |  |  | 18/12/17: 30%->100; 9/4/21: RFC 8147 added; | draft-ietf-ecrit-ecall; RFC 8147 | 72 | 37 |  |  | Wed 02/03/16 | Fri 09/04/21
2040 | 710022 | CT6 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C6 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 16/9/16: 0%->100 | 31.102 | 71 | 36 |  |  | Wed 02/03/16 | Fri 16/09/16
2041 | 760084 | UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI) | EIEI-UEConTest | 2 | Rel-14 | R5 | Thu 15/06/17 | Thu 15/03/18 | 100% | RP-171057 |  | Qualcomm |  | ¦19/9/17: Compl:0%->45%¦8/1/18: Compl:45%->80%¦27/3/18: Compl:80%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 27/03/18
2042 | 720074 | Password based service activation for IMS Multimedia Telephony service | PWDIMS | 1 | Rel-14 |  | Wed 11/03/15 | Thu 15/12/16 | 100% | SP-150041 | SP-170536 | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | 67 | 34 |  |  | Wed 04/03/15 | Fri 31/07/15
2043 | 670012 | Stage 1 for PWDIMS | PWDIMS | 2 | Rel-14 | S1 | Wed 11/03/15 | Fri 13/03/15 | 100% | SP-150041 |  | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | 67 | 34 |  |  | Wed 04/03/15 | Fri 31/07/15
2044 | 720034 | CT aspects for PWDIMS | PWDIMS-CT | 2 | Rel-14 | ct | Mon 13/06/16 | Thu 15/12/16 | 100% | CP-160295 |  | Axell, Jörgen |  |  |  | 72 | 37 |  |  | Sat 11/06/16 | NA
2045 | 720035 | CT1 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C1 | Mon 13/06/16 | Thu 15/12/16 | 100% | CP-160295 |  | Axell, Jörgen |  | 2/12/16: 0%->15¦6/3/17: 15%->100 | 24.623, 24.611 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
2046 | 720036 | CT3 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C3 | Mon 13/06/16 | Thu 15/12/16 | 100% | CP-160295 |  | Axell, Jörgen |  | 5/6/17: 0%->100 | 29.292 | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
2047 | 630007 | IMS Signalling Activated Trace | ISAT | 1 | Rel-14 |  | Wed 05/03/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | Mar 15: WID: CP-140195->CP-150091. ES in CP-150637. 8/3/16: Moved from Rel-13 at CT#71 | - | 63 | 32 |  |  | Wed 29/01/14 | Tue 08/03/16
2048 | 630107 | CT1 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C1 | Mon 10/03/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728¦5/6/17: 0%->100 | 24.229, 24.323 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
2049 | 651003 | (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497 | ISAT | 2 | Rel-14 | C1-IETF | Fri 12/09/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦13/6/16: 25%->28; 26/6/19: 28%->100 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Wed 26/06/19
2050 | 651103 | (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497 | ISAT | 2 | Rel-14 | C3-IETF | Fri 12/09/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637; 26/6/19: 25%->100 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Wed 26/06/19
2051 | 651203 | (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497 | ISAT | 2 | Rel-14 | C4-IETF | Fri 12/09/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 25%->70; 26/6/19: 70%->100 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Wed 26/06/19
2052 | 630207 | CT3 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C3 | Mon 10/03/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 0%->100 | 29.165 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
2053 | 630307 | CT4 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C4 | Wed 05/03/14 | Fri 11/03/16 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar.15: 90%. ES in CP-150615. 7/3/16: Rel-13->Rel-14¦5/6/17: 90%->100 | 23.008, 29.228, 29.229, 29.328, 29.329 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
2054 | 0 | Other Release 14 | - | 1 | Rel-14 |  | Thu 09/06/16 | Thu 09/06/16 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
2055 | 740017 | User Controlled Spoofed Call Treatment | SPECTRE | 1 | Rel-14 |  | Tue 23/08/16 | Fri 15/06/18 | 100% | SP-160898 |  | Greg Schumacher, Sprint |  | 1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898 |  | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
2056 | 730004 | Stage 1 of User Controlled Spoofed Call Treatment | SPECTRE | 2 | Rel-14 | S1 | Tue 23/08/16 | Mon 19/09/16 | 100% | SP-160898 |  | Greg Schumacher, Sprint |  | 1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898 | 22.228, 22.173 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
2057 | 740018 | Stage 3 of User Controlled Spoofed Call Treatment | SPECTRE-CT | 2 | Rel-14 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160696 |  | Dolly, Martin | md3135@att.com | 2/12/16: 0%->25¦6/3/17: 25%->100 | 24.229, 29.165 | 74 | 38 |  |  | Mon 19/09/16 | Mon 06/03/17
2058 | 750037 | (IETF) A SIP Response Code for Unwanted Calls (draft-ietf-sipcore-status-unwanted) | SPECTRE-CT_IETF | 2 | Rel-14 | C1-IETF | Tue 14/03/17 | Tue 14/03/17 | 100% |  |  | Ericsson |  | 18/12/17: 20%->100; 9/4/21: RFC 8197 added; | RFC 8197 | 75 | 38 |  |  | Tue 21/03/17 | Fri 09/04/21
2059 | 780049 | (IETF) Authenticated Identity Management in SIP (draft-ietf-stir-rfc4474bis) | SPECTRE-CT_IETF2 | 2 | Rel-14 | C1-IETF | Thu 15/06/17 | Fri 15/06/18 | 100% |  |  | Christer Holmberg | christer.holmberg@ericsson.com | 22/3/18: 0%->100; 9/4/21: RFC 8224 added; | RFC 8224 | 78 | 40 |  |  | Mon 18/12/17 | Fri 09/04/21
2060 | 700032 | Enhancement for TV service | EnTV | 1 | Rel-14 |  | Tue 14/04/15 | Fri 09/06/17 | 100% | SP-150756 | SP-170532 | Zhiming Li | Lizhiming@huawei.com | 2/3/16: 0%->100 | 22.101 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
2061 | 670010 | Study on 3GPP Enhancement for TV Video service | FS_EnTV | 2 | Rel-14 | S1 | Tue 14/04/15 | Tue 15/12/15 | 100% | SP-150052 |  | Zhiming Li (Huawei) | lizhiming@huawei.com | 1/4/15:TR number added¦June2015: Compl:0%->20¦07/09/15: 20%->75¦7/12/15: 75%->100 | 22.816 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
2062 | 720015 | System Architecture Enhancements to eMBMS for TV Video Service | AE_enTV | 2 | Rel-14 |  | Fri 11/03/16 | Thu 15/12/16 | 100% | SP-160730 | [5 empty] | 71 | 36 |  |  | Fri 11/03/16 | Thu 09/06/16
2063 | 710046 | Study on System Architecture Enhancements to eMBMS for TV Video Service | FS_AE_enTV | 3 | Rel-14 | S2 | Fri 11/03/16 | Thu 15/09/16 | 100% | SP-160225 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | 9/6/16: 0%->70¦28/7/16: 23.746 added¦19/9/16: 70%->100 | 23.746 | 71 | 36 |  |  | Fri 11/03/16 | Mon 19/09/16
2064 | 730058 | System Architecture Enhancements for TV service | AE_enTV | 3 | Rel-14 | S2 | Thu 25/08/16 | Thu 15/12/16 | 100% | SP-160730 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | 19/9/16: 0%->85¦1/12/16: FCD:09/16->12/16¦1/12/16: 85%->100 | 23.246 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
2065 | 730052 | Mobile Network Interface for MBMS Delivery of Media and TV services | AE_enTV-MI_MTV | 2 | Rel-14 | S4 | Mon 22/08/16 | Fri 09/12/16 | 100% | SP-160731 |  | Thorsten Lohmar | Thorsten.lohmar@ericsson.com | 06/10/16: Acronym: SA_enTV-MI_MTV -> AE_enTV-MI_MTV¦1/12/16: FCD:09/16->2/16¦1/12/16: 0%->50¦8/12/16: 50%->100 | 26.346 | 73 | 37 |  |  | Mon 19/09/16 | Thu 08/12/16
2066 | 740060 | Codec aspects for eMBMS Delivery of Media and TV Services | AE_enTV-S4 | 2 | Rel-14 | S4 | Thu 08/12/16 | Fri 09/06/17 | 100% | SP-160956 |  | Imed Bouazizi | i.bouazizi@samsung.com | 6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100 | 26.347, 26.346 | 74 | 38 |  |  | Thu 08/12/16 | Wed 07/06/17
2067 | 740049 | Stage 3 of system architecture enhancements for TV service | AE_enTV-CT | 2 | Rel-14 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 21/3/17: 29.116 added; | 24.116, 24.117; 29.116 | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
2068 | 740050 | CT1 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100 | 24.008 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
2069 | 740051 | CT3 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C3 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 6/3/17: 0%->80¦6/3/17: 80%->100 | 29.061 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
2070 | 740052 | CT4 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C4 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 5/6/17: 0%->100 | 29.274, 23.003 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
2071 | 740053 | CT6 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C6 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 7/3/17: 0%->100 | 31.102 | 74 | 38 |  |  | Thu 01/12/16 | Tue 07/03/17
2072 | 700054 | MBMS Transport Protocol and APIs | TRAPI | 1 | Rel-14 | S4 | Fri 11/12/15 | Wed 15/03/17 | 100% | SP-150851 |  | Samsung, Imed Bouazizi | i.bouazizi@samsung.com | 28/1/16: 26.347 added¦7/3/16: 0%->20¦11/6/16: 20%->35¦19/9/16: 35%->60. FCD: 09/16->03/17¦1/12/16: 60%->70¦6/3/17: 70%->100 | 26.346, 26.852, New TS; 26.347 | 70 | 36 |  |  | Fri 11/12/15 | Mon 06/03/17
2073 | 670003 | Multimedia Priority Service Modifications | MPS_Mods | 1 | Rel-14 | S1 | Wed 11/03/15 | Wed 15/06/16 | 100% | SP-150043 |  | Ray P. Singh (Applied Communications Science) | rsingh@appcomsci.com | 1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%¦07/09/15: 25%->40¦7/12/15: 40%->70¦2/3/16: 70%->80¦9/6/16: 80%->100 | 22.153 | 67 | 34 |  |  | Wed 04/03/15 | Thu 09/06/16
2074 | 721004 | Lawful Interception Rel-14 | LI14 | 1 | Rel-14 | S3LI | Wed 15/06/16 | Fri 15/12/17 | 100% | SP-170038 |  | Koen JASPERS, PIDS |  | 1/12/16: 0%->10¦2/3/17: WID:SP-160375->SP-1570038¦3/3/17: 8%->15¦6/3/17: 15%->20¦9/3/17: WID:SP-1570038->SP-170038¦7/6/17: 20%->50¦11/9/17: 50%->80¦15/12/17: 80%->100 |  | 72 | 37 |  |  | Wed 27/07/16 | Fri 15/12/17
2075 | 730031 | SIP Reason header extension | REAS_EXT | 1 | Rel-14 | ct | Fri 16/09/16 | Thu 14/06/18 | 99% | CP-160481 | CP-171175 | Mohali, Marianne | marianne.mohali@orange.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2076 | 730032 | CT1 aspects of SIP Reason header extension | REAS_EXT | 2 | Rel-14 | C1 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160481 |  | Mohali, Marianne | marianne.mohali@orange.com | 2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100 | 24.229 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2077 | 780050 | (IETF) ISUP Cause Location Parameter for the SIP Reason Header Field (draft-ietf-sipcore-reason-q850-loc) --> RFC 8606 | REAS_EXT | 2 | Rel-14 | C1-IETF | Thu 15/06/17 | Thu 14/06/18 | 100% |  |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 23/4/20: 50%->100 |  | 78 | 40 |  |  | Mon 18/12/17 | Thu 23/04/20
2078 | 730033 | CT3 aspects of SIP Reason header extension | REAS_EXT | 2 | Rel-14 | C3 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160481 |  | Mohali, Marianne | marianne.mohali@orange.com | 5/6/17: 0%->100 | 29.163, 29.292 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2079 | 690034 | Enhancements to User Location Reporting Support | eULRS | 1 | Rel-14 | S1 | Wed 09/09/15 | Fri 18/12/15 | 100% | SP-150540 |  |  |  | 2/3/16: 0%->100 |  | 68 | 35 |  |  | Wed 09/09/15 | Wed 02/03/16
2080 | 730002 | Diameter Load Control Mechanism | DLoCMe | 1 | Rel-14 | ct | Wed 03/12/14 | Wed 15/03/17 | 98% | CP-160645 | CP-171049 | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 5/12/16: WID:CP-160412->CP-160645 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/12/16
2081 | 730041 | CT3 aspects of Diameter Load Control Mechanism | DLoCMe | 2 | Rel-14 | C3 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160645 |  | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 2/12/16: 0%->100 | 29.272, 29.273, 29.228, 29.229, 29.328, 29.329, 29.336, 29.344, 29.345, 29.128, 29.283 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
2082 | 730042 | CT4 aspects of Diameter Load Control Mechanism | DLoCMe | 2 | Rel-14 | C4 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160645 |  | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 2/12/16: 0%->100 | 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
2083 | 740058 | (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583 | DLoCMe | 2 | Rel-14 | C4-IETF | Fri 02/12/16 | Wed 15/03/17 | 90% | CP-160645 |  |  |  | 2/12/16: 0%->90 |  | 74 | 38 |  |  | Fri 02/12/16 | Fri 02/12/16
2084 | 660025 | Study on Diameter Load Control Mechanisms | FS_DLoCME | 2 | Rel-13 | C4 | Wed 03/12/14 | Fri 11/09/15 | 100% | CP-140996 |  | Alcatel-Lucent |  | 0->5%. Mar. 15: 10%¦7/12/15: 10%->40¦13/6/16: 40%->100 | New 29.810 | 66 | 34 |  |  | Thu 04/12/14 | Mon 13/06/16
2085 | 740012 | Diameter Base Protocol Specification Update | DBPU | 1 | Rel-14 |  | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
2086 | 740054 | CT aspects of Diameter Base Protocol Specification Update | DBPU | 2 | Rel-14 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
2087 | 740055 | CT3 aspects of Diameter Base Protocol Specification Update | DBPU | 3 | Rel-14 | C3 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com | 6/3/17: 0%->100 | 29.061, 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.368, 29.468, 29.213, 29.155, 29.201 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
2088 | 740056 | CT4 aspects of Diameter Base Protocol Specification Update | DBPU | 3 | Rel-14 | C4 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com | 2/12/16: 0%->10¦6/3/17: 10%->100 | 29.109, 29.128, 29.172, 29.173, 29.228, 29.229, 29.272, 29.273, 29.283, 29.328, 29.329, 29.336, 29.337, 29.338, 29.343, 29.344, 29.345 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
2089 | 740013 | Charging aspects for Diameter Base Protocol Specification Update | DBPU-CH | 2 | Rel-14 | S5 | Thu 01/12/16 | Fri 10/03/17 | 100% | SP-160837 |  | Nokia | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | 6/3/17: 0%->100 | 32.240, 32.251, 32.260, 32.270, 32.271, 32.272, 32.273, 32.274, 32.275, 32.278, 32.280, 32.295, 32.296, 32.297, 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
2090 | 720060 | Enhancements to Multi-stream Multiparty Conferencing Media Handling | MMCMH_Enh | 1 | Rel-14 |  | Wed 02/03/16 | Tue 21/03/17 | 99% | SP-160272 | SP-170528 | Nikolai Leung | nleung@qti.qualcomm.com |  | 26.114 | 72 | 37 |  |  | Sat 11/06/16 | NA
2091 | 720029 | Overall aspects of MMCMH_Enh | MMCMH_Enh | 2 | Rel-14 | S4 | Mon 13/06/16 | Fri 10/03/17 | 100% | SP-160596 |  | Nikolai Leung | nleung@qti.qualcomm.com | 19/9/16: WID:SP-160272->SP-160785¦19/9/16: 0%->50¦1/12/16: 50%->80¦1/12/16: FCD:12/16->03/17¦6/3/17: 80%->100 | 26.114, 26.980 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
2092 | 720064 | CT aspects of MMCMH_Enh | MMCMH_Enh-CT | 2 | Rel-14 | ct | Wed 02/03/16 | Tue 21/03/17 | 99% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | To be checked at SA4 if a part can stay in Rel-13 (now Stages 1 and 2 by SA4 in UID660050), while the CT aspects are in Rel-14. 06/16: Name changed from "CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream". Acronym changed from "MMCMH- |  | 72 | 37 |  |  | Wed 02/03/16 | Mon 13/06/16
2093 | 720065 | CT1 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C1 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Name changed from "CT1 aspects of MTSI Extension on Multi-stream". Acronym changed from "MMCMH-CT"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦2/12/16: 0%->95¦6/3/17: 95%->100 | 24.229 | 72 | 37 |  |  | Wed 02/03/16 | Mon 06/03/17
2094 | 720066 | CT3 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C3 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Acronym changed from "MMCMH-CT"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦6/3/17: 0%->100 | 29.162, 29.213, 29.214, 29.165 | 72 | 37 |  |  | Wed 02/03/16 | Mon 06/03/17
2095 | 720067 | CT4 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C4 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | 3/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦2/12/16: 0%->35¦6/3/17: 35%->75¦5/6/17: 75%->100 | 23.333, 29.333, 23.334, 29.334, 29.238 | 72 | 37 |  |  | Wed 02/03/16 | Mon 05/06/17
2096 | 750038 | (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast) | MMCMH_Enh-CT | 3 | Rel-14 | C1-IETF | Tue 21/03/17 | Tue 21/03/17 | 90% |  |  | Ericsson | tomas.frankkila@ericsson.com | 23/4/20: 50%->90; 9/4/21: RFC 8853 added; | RFC 8853 | 75 | 38 |  |  | Tue 21/03/17 | Fri 09/04/21
2097 | 750039 | (IETF) RTP Payload Format Restrictions (draft-ietf-mmusic-rid) | MMCMH_Enh-CT | 3 | Rel-14 | C1-IETF | Tue 21/03/17 | Tue 21/03/17 | 90% |  |  | Ericsson |  | 23/4/20: 20%->90; 9/4/21: RFC 8851 added; | RFC 8851 | 75 | 38 |  |  | Tue 21/03/17 | Fri 09/04/21
2098 | 710002 | Deleted - CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream | MMCMH-CT | 1 | Rel-14 | ct | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT |  | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
2099 | 710028 | deleted -CT1 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C1 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 24.229 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
2100 | 710029 | deleted -CT3 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C3 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 29.162, 29.213, 29.214, 29.165 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
2101 | 710030 | deleted -CT4 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C4 | Wed 02/03/16 | Thu 15/09/16 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 23.333, 29.333, 23.334, 29.334, 29.238 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
2102 | 720008 | Control and User Plane Separation of EPC nodes | CUPS | 1 | Rel-14 |  | Thu 17/09/15 | Wed 15/03/17 | 100% | SP-160316 | SP-170520 | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20¦7/3/16: 20%->40¦9/6/16: 40%->100¦28/7/16: 23.214 added; | 23.714; 23.214 | 69 | 35 |  |  | Thu 17/09/15 | Thu 28/07/16
2103 | 690052 | Study on Control and User Plane Separation of EPC nodes | FS_CUPS | 2 | Rel-14 | S2 | Thu 17/09/15 | Fri 17/06/16 | 100% | SP-150519 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20¦7/3/16: 20%->40¦9/6/16: 40%->100 | 23.714 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
2104 | 720009 | Control and User Plane Separation of EPC nodes | CUPS | 2 | Rel-14 | S2 | Thu 09/06/16 | Thu 15/09/16 | 100% | SP-160316 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 19/9/16: 0%->80¦1/12/16: 80%->100 | 23.214, 23.002, 23.203, 23.401, 23.402 | 72 | 37 |  |  | Thu 17/09/15 | Thu 01/12/16
2105 | 730001 | CT aspects for CUPS | CUPS-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2106 | 730039 | CT3 aspects for CUPS | CUPS-CT | 3 | Rel-14 | C3 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com | 8/6/17: 0%->100 | 29.212, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Thu 08/06/17
2107 | 730040 | CT4 aspects for CUPS | CUPS-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Wed 15/03/17 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com | 2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100 | 23.007, 29.274, 29.281, 29.303, 23.008 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2108 | 690048 | OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM14 | 1 | Rel-14 | S5 | Thu 12/03/15 | Tue 12/12/17 | 100% | [6 empty] | 68 | 35 |  |  | Wed 16/09/15 | Wed 16/09/15
2109 | 680035 | Management of mobile networks that include virtualized network functions | OAM14-MAMO_VNF | 2 | Rel-14 | S5 | Mon 15/06/15 | Tue 12/12/17 | 100% | SP-150362 |  | Jinglei Liu, China Mobile | liujinglei@chinamobile.com | June2015: WID:SP-150308->SP-150362 |  | 68 | 35 |  |  | Mon 15/06/15 | Thu 18/06/15
2110 | 680036 | Management concept, architecture and requirements for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-MCAR | 3 | Rel-14 | S5 | Mon 15/06/15 | Thu 15/12/16 | 100% | SP-160023 |  | Jinglei Liu, China Mobile (liujinglei@chinamobile.com) | liujinglei@chinamobile.com | June2015: WID:SP-150309->SP-150363. Aug2015: FCD: Mar 2016¦07/09/15: 0%->20. 15/09/15: FCD: Mar 16->Dec 16, moved to Rel-14¦7/12/15: 20%->40¦7/3/16: 40%->50¦7/3/16: WID:SP-150363->SP-160023 ( FCD: Dec16->Sep16)¦13/6/16: 50%->70¦19/9/16: FCD:09/16 | 28.xyz, 32.101 | 68 | 35 |  |  | Mon 15/06/15 | Wed 22/03/17
2111 | 690039 | Configuration Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-CM | 3 | Rel-14 | S5 | Wed 16/09/15 | Fri 09/06/17 | 100% | SP-160401 |  | ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn) | zhu.weihong@zte.com.cn | 5/10/15: 28.513¦28.512¦28.511¦28.510 added¦7/12/15: 0%->15¦7/3/16: 15%->20¦13/6/16: 20%->30¦19/9/16: 30%->50¦1/12/16: 50%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100 | 28.513; 28.512; 28.511; 28.510; 28.621, 28.622, 28.623, 28.704, 28.707 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
2112 | 690040 | Fault Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-FM | 3 | Rel-14 | S5 | Wed 16/09/15 | Fri 09/06/17 | 100% | SP-160403 |  | Huawei (Kai ZHANG, kai.zhangkai@huawei.com) | kai.zhangkai@huawei.com | 5/10/15: 28.518¦28.517¦28.516¦28.515 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->50¦13/6/16: WID:SP-150404->SP-160403¦19/9/16: 50%->75¦1/12/16: 75%->80¦1/12/16: 80%->¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 80%-> | 28.515, 28.516, 28.517, 28.518, 32.111-1, 32.111-2, 32.111-6 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
2113 | 690041 | Performance management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-PM | 3 | Rel-14 | S5 | Wed 16/09/15 | Tue 12/12/17 | 100% | SP-160402 |  | Intel (Joey Chou, joey.chou@intel.com) | joey.chou@intel.com | 5/10/15: 28.523¦28.522¦28.521¦28.520 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->30¦13/6/16: WID:SP-150401->SP-160402¦19/9/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->75¦7/6/17: 75%->90¦7/6/17: FCD:0 | 28.523; 28.522; 28.521; 28.520; 32.426, 32.409, 32.401 | 69 | 35 |  |  | Mon 15/06/15 | Mon 11/09/17
2114 | 690042 | Lifecycle management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-LCM | 3 | Rel-14 | S5 | Wed 16/09/15 | Fri 09/06/17 | 100% | SP-160427 |  | Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks | anatoly.andrianov@nokia.com | 5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%- | 28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
2115 | 710009 | Filtering of PM measurements and data volume | OAM14-FILMEAS | 2 | Rel-14 | S5 | Tue 01/03/16 | Thu 01/12/16 | 100% | SP-160610 |  | Ericsson: Robert Petersen | robert.petersen@ericsson.com | 13/6/16: 0%->15¦19/9/16: WID:SP-160022->SP-160610¦19/9/16: 15%->60¦1/12/16: 60%->95¦6/3/17: 95%->100 | New 32.817, 32.425, 32.412, 32.416, 32.130 | 71 | 36 |  |  | Tue 01/03/16 | Mon 06/03/17
2116 | 670028 | Study on OAM support for Licensed Shared Access (LSA) | FS_OAM_LSA | 2 | Rel-14 | S5 | Thu 12/03/15 | Fri 11/03/16 | 100% | SP-150056 |  | Nokia Networks, Anatoly Andrianov | anatoly<dot>andrianov<at>nokia<dot>com | June2015: Compl:0%->15¦07/09/15: 15%->70¦7/12/15: 70%->75¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14¦28/7/16: 28.303 added¦28/7/16: 28.302 added¦28/7/16: 28.301 added¦28/7/16: 33.250 added¦28/7/16: added; | 28.303; 28.302; 28.301; | 67 | 34 |  |  | Thu 12/03/15 | Thu 28/07/16
2117 | 720044 | OAM support for Licensed Shared Access (LSA) | OAM14-LSA | 2 | Rel-14 | S5 | Mon 13/06/16 | Mon 12/06/17 | 100% | SP-160397 |  | Nokia: Olaf Pollakowski |  | 28/7/16: 28.303 added¦28/7/16: 28.302 added¦28/7/16: 28.301 added¦19/9/16: 0%->20¦1/12/16: 20%->30¦6/3/17: 30%->40¦7/6/17: 40%->100 | 32.101; 28.303; 28.302; 28.301 | 72 | 37 |  |  | Thu 12/03/15 | Wed 07/06/17
2118 | 680050 | Development of super-wideband and fullband P.835 | DESUDAPS | 1 | Rel-14 | S4 | Tue 16/06/15 | Thu 15/06/17 | 100% | SP-150215 | SP-170346 | Scott Isabelle (Knowles, Inc.) | sisabelle@audience.com | 06/15: FCD corrected to Dec.15¦Aug2015: 0%->5¦07/09/15: 5%->20, FCD: 12/15->06.16¦7/12/15: 20%->40, MOVED TO REL-14¦7/3/16: 40%->50. 15/4/16: 6/16->12/16¦11/6/16: 50%->60¦19/9/16: 60%->70, fcd: 12/16->06/17¦1/12/16: 70%->75¦6/3/17: 75%->80¦7/6 | 26.131, 26.132 | 68 | 35 |  |  | Thu 18/06/15 | Wed 07/06/17
2119 | 670004 | Enhancing Location Capabilities for Indoor and Outdoor Emergency Communications | ELIOT | 1 | Rel-14 | S1 | Wed 11/03/15 | Tue 15/12/15 | 100% | SP-150044 | SP-170553 | Greg Schumacher | Gregory.schumacher@sprint.com | 1/4/15: rapporteur added, Impacted TS added¦June2015: Compl:0%->25¦07/09/15: 25%->80¦2/3/16: 80%->100 | 22.101, 22.071 | 67 | 34 |  |  | Wed 04/03/15 | Wed 02/03/16
2120 | 670005 | Enhancements to Domain Selection between VoLTE and CDMA CS | eDSVCC | 1 | Rel-14 | S1 | Wed 11/03/15 | Mon 15/06/15 | 100% | SP-150045 |  | China Telecom, Hongmei Zhu | zhuhongmei@gsta.com | 1/4/15: rapporteur added, Impacted TS added¦June2015: Compl:0%->100 | 22.101 | 67 | 34 |  |  | Wed 04/03/15 | Mon 15/06/15
2121 | 680002 | Control of Applications when Third party Servers encounter difficulties | CATS | 1 | Rel-14 | S1 | Mon 11/05/15 | Wed 16/09/15 | 100% | SP-150273 | SP-170338 | Eriko Yoshida, KDDI | er-yoshida (at) kddi (dot) com | 07/09/15: 0%->100 | 22.011 | 68 | 35 |  |  | Tue 09/06/15 | Mon 07/09/15
2122 | 720080 | PS Data Off Services | PS_Data_Off | 1 | Rel-14 |  | Mon 09/11/15 | Fri 09/06/17 | 100% | SP-150823 | SP-170708 | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.03 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
2123 | 700033 | PS Data Off Services | PS_Data_Off | 2 | Rel-14 | S1 | Mon 09/11/15 | Tue 15/03/16 | 100% | SP-150823 |  | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.03 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
2124 | 720079 | Study on Stage 2 of PS Data off function | FS_PS_DATA_OFF | 2 | Rel-14 | S2 | Fri 17/06/16 | Thu 15/12/16 | 100% | SP-160318 |  | Orange, david <dot> cailliere <at> orange <dot> com | david <dot> cailliere <at> orange <dot> com | 28/7/16: 23.702 added¦19/9/16: 0%->60¦1/12/16: FCD:09/16->12/16¦1/12/16: 60%->100 | 23.702 | 72 | 37 |  |  | Fri 17/06/16 | Thu 01/12/16
2125 | 740004 | Stage 2 of PS Data Off | PS_DATA_OFF | 2 | Rel-14 | S2 | Thu 17/11/16 | Thu 15/12/16 | 100% | SP-160831 |  | Christophe Petit (Orange) | kris (dot) petit (at) orange (dot) com | 1/12/16: 0%->100 | 23.401, 23.203, 23.060, 23.228, 23.292, 23.221 | 74 | 38 |  |  | Thu 01/12/16 | Thu 01/12/16
2126 | 740041 | Stage 3 of PS Data Off | PS_DATA_OFF-CT | 2 | Rel-14 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
2127 | 740042 | CT1 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->95¦5/6/17: 95%->100 | 24.008, 24.301, 27.007, 24.229, 24.368, 24.167 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
2128 | 740043 | CT3 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C3 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->60¦8/6/17: 60%->100 | 29.212, 29.213 | 74 | 38 |  |  | Thu 01/12/16 | Thu 08/06/17
2129 | 740044 | CT6 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C6 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/3/17: 0%->100 | 31.102, 31.103, 31.111 | 74 | 38 |  |  | Thu 01/12/16 | Tue 07/03/17
2130 | 740014 | Charging Aspect for 3GPP PS Data off Function | PS_DATA_OFF-CH | 2 | Rel-14 | S5 | Thu 01/12/16 | Fri 09/06/17 | 100% | SP-160839 |  | Huawei， Chen, Shan | chenshan@huawei.com | 6/3/17: 0%->70¦6/3/17: FCD:03/17->06/17¦7/6/17: 70%->100 | 32.251, 32.298, 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
2131 | 710003 | SCC AS Restoration | SCCAS_RES | 1 | Rel-14 | C4 | Wed 02/03/16 | Thu 15/12/16 | 100% | CP-160118 |  | China Mobile, Hao Zhang, | zhanghao@chinamobile.com | 13/6/16: 0%->100 | 23.38 | 71 | 36 |  |  | Wed 02/03/16 | Mon 13/06/16
2132 | 710004 | Paging Policy Enhancements and Procedure | PPEPO_LTE | 1 | Rel-14 | S1 | Mon 01/02/16 | Tue 01/03/16 | 100% | SP-160113 | SP-170549 | China Unicom, Zhuoyun Zhang | zhangzy910@chinaunicom.cn |  | 22.101 | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
2133 | 720077 | Enhancement to Flexible Mobile Service Steering | eFMSS | 1 | Rel-14 |  | Mon 11/05/15 | Thu 15/09/16 | 100% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | 72 | 37 |  |  | Tue 01/03/16 | Tue 01/03/16
2134 | 680003 | Study on enhancement to FMSS for Rel 14 | FS_eFMSS | 2 | Rel-14 | S1 | Mon 11/05/15 | Wed 16/12/15 | 100% | SP-150280 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 7/12/15: 70%->100 | 22.808 | 68 | 35 |  |  | Tue 09/06/15 | Mon 07/12/15
2135 | 710005 | Stage 1 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S1 | Mon 01/02/16 | Tue 01/03/16 | 100% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
2136 | 720078 | Stage 2 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S2 | Fri 17/06/16 | Thu 15/09/16 | 100% | SP-160314 |  | ZTE, Tricci So |  | 19/9/16: 0%->100 | 23.203 | 72 | 37 |  |  | Tue 01/03/16 | Mon 19/09/16
2137 | 710010 | Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 1 | Rel-14 |  | Tue 01/03/16 | Thu 01/12/16 | 92% | SP-160081 | SP-170515 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10 | 26.223 | 71 | 36 |  |  | Tue 01/03/16 | Sat 11/06/16
2138 | 721005 | S4 aspects of Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 2 | Rel-14 | S4 | Tue 01/03/16 | Thu 01/12/16 | 100% | SP-160081 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100 | 26.223 | 72 | 37 |  |  | Tue 01/03/16 | Thu 01/12/16
2139 | 720061 | (IETF) Other IETF aspects of IMS_TELEP_EXT | IMS_TELEP_EXT | 2 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 91% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  | draft-ietf-payload-rtp-h265, -flexible-fec-scheme , draft-ietf-clue-framework , -datachannel, -signalling, -data-model-schema, -protocol, -rtp-mapping, draft-ietf-mmusic-sctp-sdp, -data-channel-sdpneg, draft-ietf-tsvwg-sctp-dtls-encaps | 72 | 37 |  |  | Tue 01/03/16 | NA
2140 | 800103 | (IETF) RTP Payload Format for Flexible Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627 | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 100% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 23/04/20
2141 | 800104 | (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8845 added; | RFC 8845 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2142 | 800105 | (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8850 added; | RFC 8850 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2143 | 800106 | (IETF) Session Signaling for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-signaling) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8848 added; | RFC 8848 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2144 | 800107 | (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8846 added; | RFC 8846 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2145 | 800108 | (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8847 added; | RFC 8847 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2146 | 800109 | (IETF) Mapping RTP streams to CLUE Media Captures (draft-ietf-clue-rtp-mapping) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8849 added; | RFC 8849 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2147 | 800110 | (IETF) Session Description Protocol (SDP) Offer/Answer Procedures For Stream Control Transmission Protocol (SCTP) over Datagram Transport Layer Security (DTLS) Transport. (draft-ietf-mmusic-sctp-sdp) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8841 added; | RFC 8841 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2148 | 800111 | (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | Tue 01/03/16 | Thu 01/12/16 | 90% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 23/4/20: 25%->90; 9/4/21: RFC 8864 added; | RFC 8864 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2149 | 710011 | Improved Streaming QoE Reporting in 3GPP | IQoE | 1 | Rel-14 | S4 | Tue 01/03/16 | Wed 15/03/17 | 100% | SP-160082 | SP-170521 | Zhiming Li, Huawei | Lizhiming@huawei.com | 11/6/16: 0%->10¦19/9/16: 10%->55. FDC: 12/16->03/17¦1/12/16: 55%->65¦6/3/17: 65%->100 | New 26.909, 26.247, 26.346 | 71 | 36 |  |  | Tue 01/03/16 | Mon 06/03/17
2150 | 710085 | New GPRS algorithms for EASE | EASE_ALGOs_SA3 | 1 | Rel-14 | S3 | Tue 15/03/16 | Wed 15/06/16 | 100% | SP-160203 |  | Tim Evans, Vodafone |  | Discussion whether it should be Rel-13. To be concluded at SA#72.¦13/6/16: 0%->60¦1/12/16: 60%->70¦6/3/17: 70%->100 | 55.241, 55.242, 55.243, 55.251, 55.252, 55.253 | 71 | 36 |  |  | Tue 22/03/16 | Mon 06/03/17
2151 | 710048 | S8 Home Routing Architecture for VoLTE | V8 | 1 | Rel-14 |  | Thu 18/06/15 | Fri 09/06/17 | 100% | SP-160315 | SP-170522 |  |  | Umbrella, created by MCC to group SA2 and SA3 activities |  | 71 | 36 |  |  | Fri 11/03/16 | Fri 11/03/16
2152 | 680053 | Study on S8 Home Routing Architecture | FS_V8 | 2 | Rel-14 | S2 | Thu 18/06/15 | Thu 10/03/16 | 100% | SP-150255 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 07/09/15: 0%->10¦07/09/15: 10%->100¦7/12/15: 100%->10% (mistake?) then 10%->70, FCD: 12/15-?03/16¦7/3/16: 70%->80¦9/6/16: 80%->100 | New 23.xxx | 68 | 35 |  |  | Thu 18/06/15 | Thu 09/06/16
2153 | 690049 | Study on LI in S8 Home Routing Architecture for VoLTE | FS_LIV8 | 2 | Rel-14 | S3 | Thu 17/09/15 | Fri 17/06/16 | 100% | SP-150461 |  | Greg Schumacher (SPRINT) Gregory | Schumacher@sprint.com | 7/12/15: 0%->45¦28/1/16: 33.827 added¦7/3/16: 45%->55¦19/9/16: 55%->65¦15/12/17: 65%->100 | 33.827 | 69 | 35 |  |  | Thu 17/09/15 | Fri 15/12/17
2154 | 720017 | S8 Home Routing Architecture for VoLTE | V8 | 2 | Rel-14 | S2 | Mon 13/06/16 | Thu 15/12/16 | 100% | SP-160315 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 11/6/16: 0%->60¦19/9/16: 60%->95¦1/12/16: FCD:09/16->12/16¦1/12/16: 95%->100 | 23.228, 23.167, 23.203 | 72 | 37 |  |  | Thu 18/06/15 | Thu 01/12/16
2155 | 730023 | CT Aspects of V8 | V8-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2156 | 730024 | CT1 Aspects of V8 | V8-CT | 3 | Rel-14 | C1 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com | 2/12/16: 40%->100 | 24.229 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
2157 | 730025 | CT3 Aspects of V8 | V8-CT | 3 | Rel-14 | C3 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com | 2/12/16: 40%->100 | 29.212, 29.213, 29.214 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
2158 | 720050 | Charging Aspects of S8 Home Routing Architecture for VoLTE | CH14-V8 | 2 | Rel-14 | S5 | Mon 13/06/16 | Fri 09/06/17 | 100% | SP-160838 |  | Chen, Ai (China Mobile) | chenai(at) chinamobile (dot) com | 19/9/16: 0%->15¦1/12/16: FCD:12/16->03/17¦1/12/16: 15%->60¦1/12/16: WID:SP-160429->SP-160838¦6/3/17: FCD:03/17->06/17¦7/6/17: 60%->100 | 32.240, 32.251, 32.260 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
2159 | 720020 | Improvements of awareness of user location change | AULC | 1 | Rel-14 |  | Thu 17/09/15 | Fri 09/06/17 | 100% | SP-160308 | SP-170524 | Yang Xu | xuyang49@chinaunicom.cn |  |  | 72 | 37 |  |  | Thu 17/09/15 | Thu 09/06/16
2160 | 690050 | Study on improvement of awareness of user location change | FS_AULC | 2 | Rel-14 | S2 | Thu 17/09/15 | Fri 17/06/16 | 100% | SP-150517 |  | Yang Xu | xuyang49@chinaunicom.cn | 7/12/15: 0%->40¦7/3/16: 40%->70¦9/6/16: 70%->100 | 23.71 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
2161 | 720021 | Improvements of awareness of user location change | AULC | 2 | Rel-14 | S2 | Mon 06/06/16 | Thu 15/09/16 | 100% | SP-160308 |  | Yang Xu | xuyang49@chinaunicom.cn | 11/6/16: 0%->10¦19/9/16: 10%->100 | 23.401, 23.203, 23.060 | 72 | 37 |  |  | Thu 17/09/15 | Mon 19/09/16
2162 | 730034 | CT Aspect of AULC | AULC-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
2163 | 730035 | CT3 Aspect of AULC | AULC-CT | 3 | Rel-14 | C3 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com | 2/12/16: 0%->10¦6/3/17: 10%->100 | 29.212, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
2164 | 730036 | CT4 Aspect of AULC | AULC-CT | 3 | Rel-14 | C4 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com | 2/12/16: 0%->95¦6/3/17: 95%->100 | 29.274 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
2165 | 730054 | Charging Aspects of Improvements of AULC | AULC-CH | 2 | Rel-14 | S5 | Mon 19/09/16 | Fri 09/06/17 | 100% | SP-160609 |  | Huawei， Chen, Shan | chenshan@huawei.com | 1/12/16: 0%->40¦6/3/17: 40%->80¦6/3/17: FCD:03/17->06/17¦7/6/17: 80%->100 | TS32.251, TS32.298, TS32.299 | 73 | 37 |  |  | Mon 19/09/16 | Wed 07/06/17
2166 | 720022 | Service Domain Centralization | SeDoC | 1 | Rel-14 | S2 | Mon 02/11/15 | Mon 19/09/16 | 100% | SP-160675 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com |  |  | 72 | 37 |  |  | Mon 07/12/15 | Thu 09/06/16
2167 | 700040 | Study on Service Domain Centralization | FS_SeDoC | 2 | Rel-14 | S2 | Mon 02/11/15 | Thu 15/09/16 | 100% | SP-160306 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com | Comes back from previous release¦28/1/16: 23.719 added¦7/3/16: 0%->30¦7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70¦11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16¦1/12/16: 70%->100 | 23.719 | 70 | 36 |  |  | Mon 07/12/15 | Thu 01/12/16
2168 | 730044 | Service Domain Centralization | SeDoC | 2 | Rel-14 | S2 | Tue 16/08/16 | Mon 19/09/16 | 100% | SP-160675 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com | 19/9/16: 0%->100 | 23.292, 23.167 | 73 | 37 |  |  | Mon 19/09/16 | Mon 19/09/16
2169 | 720014 | Sponsored data connectivity improvements | SDCI | 1 | Rel-14 |  | Mon 02/11/15 | Thu 15/12/16 | 100% | SP-160309 | SP-170523 | Yang Xu | xuyang49@chinaunicom.cn |  |  | 72 | 37 |  |  | Mon 07/12/15 | Thu 09/06/16
2170 | 700041 | Study on sponsored data connectivity improvements | FS_SDCI | 2 | Rel-14 | S2 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150627 |  | Yang Xu | xuyang49@chinaunicom.cn | 28/1/16: 23.721 added¦7/3/16: 10%->40¦9/6/16: 40%->100 | 23.721 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2171 | 720024 | Sponsored data connectivity improvements | SDCI | 2 | Rel-14 | S2 | Mon 13/06/16 | Thu 15/09/16 | 100% | SP-160309 |  | Yang Xu | xuyang49@chinaunicom.cn | 19/9/16: 0%->100 | 23.203, 23.682 | 72 | 37 |  |  | Mon 07/12/15 | Mon 19/09/16
2172 | 730037 | CT Aspects of SDCI | SDCI-CT | 2 | Rel-14 | ct | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160580 |  | China Unicom, Xu, Yang | xuyang49@chinaunicom.cn | 6/10/16: 29.251 added; | 29.251 | 73 | 37 |  |  | Fri 16/09/16 | Thu 06/10/16
2173 | 730038 | CT3 Aspects of SDCI | SDCI-CT | 3 | Rel-14 | C3 | Fri 16/09/16 | Thu 15/12/16 | 100% | CP-160580 |  | China Unicom, Xu, Yang | xuyang49@chinaunicom.cn | 6/10/16: 29.250 added¦2/12/16: 10%->30¦6/3/17: 30%->80¦5/6/17: 80%->100 | 29.212, 29.213, 29.214, 29.201, 29.250 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
2174 | 710017 | Stage-3 SAE Protocol Development - Phase 5 | SAES5 | 1 | Rel-14 | C1 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com |  | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
2175 | 710018 | SAES5 CS Fallback in EPS | SAES5-CSFB | 2 | Rel-14 | C1 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->5¦16/9/16: 5%->20¦2/12/16: 20%->70¦6/3/17: 70%->100 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Mon 06/03/17
2176 | 710019 | SAES5 for support for non-3GPP accesses | SAES5-non3GPP | 2 | Rel-14 | C1 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->15¦16/9/16: 15%->20¦2/12/16: 20%->85¦6/3/17: 85%->100 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Mon 06/03/17
2177 | 720073 | SAE Protocol Development (Stage 3) - Phase 5 | SAES5 | 2 | Rel-14 | C1 | Wed 02/03/16 | Wed 15/03/17 | 100% | CP-160052 |  |  |  | Added following CT1's chair e-mail 14/06/16¦16/9/16: 0%->20¦2/12/16: 20%->85¦6/3/17: 85%->100 |  | 72 | 37 |  |  | Tue 24/03/15 | Mon 06/03/17
2178 | 720012 | Group based enhancements in the network capability exposure functions | GENCEF | 1 | Rel-14 | S2 | Mon 02/11/15 | Fri 16/12/16 | 100% | SP-160311 | SP-170517 | Samsung, Sung Hwan Won | sunghwan.won@samsung.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2179 | 700043 | Study on group based enhancements in the network capability exposure functions | FS_GENCEF | 2 | Rel-14 | S2 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-160311 |  | Samsung, Sung Hwan Won | sunghwan.won@samsung.com | 28/1/16: 23.773 added¦28/1/16: 23.742 added¦7/3/16: 0%->10¦9/6/16: 10%->100 | 23.xyz; 23.773; 23.742 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2180 | 720013 | Group based enhancements in the network capability exposure functions | GENCEF | 2 | Rel-14 | S2 | Thu 09/06/16 | Fri 16/12/16 | 100% | SP-160311 |  | Samsung, Sunghoon Kim | s.hun.kim@samsung.com | 19/9/16: 0%->90¦1/12/16: FCD:09/16->12/16¦1/12/16: 90%->100 | 23.682 | 72 | 37 |  |  | Mon 07/12/15 | Thu 01/12/16
2181 | 720084 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 1 | Rel-14 |  | Mon 02/11/15 | Fri 14/09/18 | 99% | SP-160312 | [5 empty] | 72 | 37 |  |  | Mon 07/12/15 | NA
2182 | 700044 | Study on Robust Call Setup for VoLTE subscriber in LTE | FS_RobVoLTE | 2 | Rel-14 | S2 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150632 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com | 28/1/16: 23.750 added¦7/3/16: 0%->20¦9/6/16: 20%->100 | 23.8xx; 23.750 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2183 | 720301 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 2 | Rel-14 | S2 | Fri 17/06/16 | Thu 15/09/16 | 100% | SP-160312 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com | 19/9/16: 0%->100. 1/12/16: UID changed: 720085 -> 720301 (720085 was also used for RP-161181) | 23.228, 23.237 | 72 |  |  |  | Mon 07/12/15 | Thu 01/12/16
2184 | 730022 | CT Aspects of RobVoLTE | RobVoLTE-CT | 2 | Rel-14 | C1 | Fri 16/09/16 | Thu 16/03/17 | 100% | CP-160478 |  | PATEL, Milan | Milan.Patel@huawei.com | 2/12/16: 0%->80¦6/3/17: 80%->100 | 24.229, 24.292 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
2185 | 730078 | Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh | 2 | Rel-14 | R2 | Thu 15/09/16 | Fri 14/09/18 | 99% | RP-161856 |  | CMCC |  |  |  | 73 | 37 |  |  | Wed 14/12/16 | Mon 26/09/16
2186 | 730178 | Core part: Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh-Core | 3 | Rel-14 | R2 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161856 | RP-170323 | CMCC |  | ¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170323 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
2187 | 760089 | UE Conformance Test Aspects –Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh-UEConTest | 3 | Rel-14 | R5 | Thu 15/06/17 | Fri 14/09/18 | 100% | RP-171385 |  | CATT |  | ¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->60%¦ 27/3/18: Compl:60 ;; 11/10/20: 95%->100 |  | 76 | 39 |  |  | Fri 16/06/17 | Sun 11/10/20
2188 | 740010 | RAN-Assisted Codec Adaptation in MTSI | LTE_VoLTE_ViLTE_enh-S4 | 2 | Rel-14 | S4 | Thu 01/12/16 | Fri 09/06/17 | 100% | SP-160778 | SP-170516 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 6/3/17: 0%->65¦6/3/17: FCD:03/17->06/17¦7/6/17: 65%->100 |  | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
2189 | 720028 | Extension of UE Delay test methods and requirements | EXT_UED | 1 | Rel-14 | S4 | Mon 13/06/16 | Fri 09/06/17 | 100% | SP-160600 | SP-170345 | Stéphane Ragot, ORANGE | stephane.ragot@orange.com | 19/9/16: WID:SP-160271->SP-160600¦19/9/16: 0%->20¦1/12/16: 20%->30¦14/12/16: 30%->50¦6/3/17: 50%->60¦6/3/17: FCD:03/17->06/17¦7/6/17: 60%->100 | 26.954, 26.131, 26.132 | 72 | 37 |  |  | Sat 11/06/16 | Wed 07/06/17
2190 | 720037 | Improved operator control using new UE configuration parameters | IOC_UE_conf | 1 | Rel-14 |  | Mon 13/06/16 | Wed 15/03/17 | 100% | CP-160828 | CP-171176 | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10¦17/10/16: WID:CP-160296->CP-160374¦5/12/16: WID:CP-160374->CP-160828 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.XXX, 24.YYY | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/12/16
2191 | 720038 | CT1 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C1 | Mon 13/06/16 | Wed 15/03/17 | 100% | CP-160828 |  | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10¦16/9/16: 10%->20¦17/10/16: WID:CP-160296->CP-160374¦2/12/16: 20%->75¦6/3/17: 75%->100 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.275 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
2192 | 720039 | CT6 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C6 | Mon 13/06/16 | Wed 15/03/17 | 100% | CP-160828 |  | Adrian Buckley | abuckley@blackberry.com | 11/6/16: 0%->10¦14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100 | 31.102, 31.103 | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
2193 | 720001 | Shared Subscription Data Update | eSDU | 1 | Rel-14 | C4 | Mon 13/06/16 | Thu 15/12/16 | 100% | CP-160644 | CP-171050 | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 13/6/16: 0%->25¦2/12/16: 25%->100¦5/12/16: WID:CP-160243->CP-160644 | 29.272, 29.002, 29.305, 29.230 | 72 | 37 |  |  | Mon 13/06/16 | Mon 05/12/16
2194 | 710012 | Rel-14 Charging | CH14 | 1 | Rel-14 | S5 | Tue 01/03/16 | Fri 09/06/17 | 100% | SP-160021 |  |  |  | Umbrella Feature |  | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
2195 | 710008 | Resource Optimization for PS Domain Online | CH14-ROPOCH | 2 | Rel-14 | S5 | Tue 01/03/16 | Fri 09/06/17 | 100% | SP-160021 |  | Shrader, David(Ericsson) | david.shrader@ericsson.com | 13/6/16: 0%->10. FCD:09/16->03/17¦19/9/16: FCD: 09/16->03/17¦19/9/16: 10%->20¦1/12/16: 20%->50¦6/3/17: 50%->80¦6/3/17: FCD:03/17->06/20¦7/6/17: 80%->100 | 32.251, 32.299 | 71 | 36 |  |  | Tue 01/03/16 | Wed 07/06/17
2196 | 740015 | Charging for SMS via T4 | CH14-SMST4 | 2 | Rel-14 | S5 | Thu 01/12/16 | Fri 09/06/17 | 100% | SP-160840 |  | Nokia | Maryse <dot> Gardella <at> Nokia <dot> com | 6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100 | 32.274, 32.250 , 32.298, 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
2197 | 720049 | Charging Aspects of Enhanced Proximity-based Services | CH14-ProSe | 2 | Rel-14 | S5 | Mon 13/06/16 | Fri 09/06/17 | 100% | SP-160428 | SP-170408 | Chen, Shan | chenshan@huawei.com | 19/9/16: 0%->40¦1/12/16: 40%->60¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100 | 32.240, 32.251, 32.277, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
2198 | 740019 | Determination of Completeness of Charging Information in IMS | CH14-DCCII | 1 | Rel-14 | S5 | Mon 13/06/16 | Fri 09/06/17 | 100% | SP-160398 |  | Jesske, Roland (Deutsche Telekom) |  | 19/9/16: 0%->10 | 32.240, 32.260, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Mon 19/09/16
2199 | 720045 | Determination of Completeness of Charging Information in IMS | CH14-DCCII | 2 | Rel-14 | S5 | Mon 13/06/16 | Fri 09/06/17 | 100% | SP-160398 | SP-170344 | Jesske, Roland (Deutsche Telekom) |  | 19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦7/6/17: 10%->100 | 32.240, 32.260, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
2200 | 740059 | CT Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 2 | Rel-14 | ct | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160697 | CP-171048 | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de |  |  | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
2201 | 740020 | CT1 Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 3 | Rel-14 | C1 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160697 |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 2/12/16: 0%->10¦6/3/17: 10%->35¦5/6/17: 35%->100 | 24.229 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
2202 | 740021 | CT3 Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 3 | Rel-14 | C3 | Thu 01/12/16 | Tue 14/03/17 | 100% | CP-160697 |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 8/6/17: 0%->100 | 29.165 | 74 | 38 |  |  | Thu 01/12/16 | Thu 08/06/17
2203 | 700060 | Enhanced LAA for LTE | LTE_eLAA | 1 | Rel-14 |  | Tue 15/12/15 | Fri 14/09/18 | 100% | RP-152272 |  | Ericsson |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2204 | 700160 | Core part: Enhanced LAA for LTE | LTE_eLAA-Core | 2 | Rel-14 | R1 | Tue 15/12/15 | Wed 15/03/17 | 100% | RP-162235 | RP-170269 | Ericsson |  | 22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881¦26/9/16: Compl:60%->92%¦26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: WID: ¦20/12/16: Compl:92%->97%¦20/12/16:21/3/17: Compl: |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 21/03/17
2205 | 700260 | Perf. part: Enhanced LAA for LTE | LTE_eLAA-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Fri 15/09/17 | 100% | RP-162235 |  | Ericsson |  | 22/3/16: WID: RP-152272->RP-160407¦1/7/16: WID: RP-160407->RP-16088126/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160881->RP-161832¦20/12/16: WID: RP-161832->RP-162235;21/3/17: Compl:0%->33%¦19/6/17: Compl:33%->50%¦ ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
2206 | 730075 | UE Conformance Test Aspects - Enhanced LAA for LTE | LTE_eLAA-UEConTest | 2 | Rel-14 | R5 | Thu 15/09/16 | Fri 14/09/18 | 100% | RP-171577 |  | Intel |  | ¦21/3/17: Compl:0%->5% ;19/6/17: Compl:5%->6%¦19/9/17: Compl 8/1/18: C2 ;; 11/10/20: 85%->100 |  | 73 | 37 |  |  | Mon 26/09/16 | Sun 11/10/20
2207 | 700062 | RRC optimization for UMTS | UTRA_RRCopt | 1 | Rel-14 | R2 | Tue 15/12/15 | Thu 15/09/16 | 100% | RP-152267 |  | Ericsson |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2208 | 700162 | Core part: RRC optimization for UMTS | UTRA_RRCopt-Core | 2 | Rel-14 | R2 | Tue 15/12/15 | Thu 15/09/16 | 100% | RP-160287 | RP-172758 | Ericsson |  | 22/3/16: Compl:0%->8%¦ 1/7/16: Compl:8%->70%26/9/16: Compl:70%->100%¦8/1/18: Stat Rep: ->RP-172758 |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 08/01/18
2209 | 700063 | DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX | 1 | Rel-14 | R2 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-152286 |  | Huawei |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2210 | 700163 | Core part: DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX-Core | 2 | Rel-14 | R2 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-162513 | RP-162132 | Huawei |  | 22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->50%26/9/16: Compl:50%->65%¦20/12/16: Compl:65%->100%¦ |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2211 | 700077 | AWS-3/4 Band for LTE | LTE_AWS_3_4 | 1 | Rel-14 |  | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-151731 |  | Dish Network |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2212 | 700177 | Core part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Core | 2 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/06/16 | 100% | RP-160783 |  | Dish Network |  | ¦22/3/16: Compl:0%->60%¦1/7/16: Compl:60%->100%¦1/7/16: CD:Th | 36.749 | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
2213 | 700277 | Perf. part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/06/16 | 100% | RP-160783 |  | Dish Network |  | 1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06 |  | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
2214 | 730072 | UE Conformance Test Aspects – AWS-3/4 Band for LTE (Band 70) | LTE_AWS_3_4-UEConTest | 2 | Rel-14 | R5 | Thu 15/09/16 | Thu 15/12/16 | 100% | RP-162009 |  | Dish Network |  | ¦20/12/16: Compl:0%->100%¦ |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 20/12/16
2215 | 700078 | LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3 | 1 | Rel-14 | R4 | Tue 15/12/15 | Tue 15/12/15 | 0% | RP-152238 |  | KT Corp. |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2216 | 700178 | Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3-Core | 2 | Rel-14 | R4 | Tue 15/12/15 | Tue 15/12/15 | 0% | RP-152238 |  | KT Corp. |  |  |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 22/12/15
2217 | 740073 | Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs | 1 | Rel-14 | R4 | Thu 15/12/16 | Fri 15/09/17 | 99% | RP-162515 |  | Hughes Network Systems |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
2218 | 740173 | Core part: Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs-Core | 2 | Rel-14 | R4 | Thu 15/12/16 | Wed 15/03/17 | 100% | RP-170235 |  | Hughes Network Systems |  | ¦21/3/17: Compl:0%->100% ¦2 |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
2219 | 760083 | UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs-UEConTest | 2 | Rel-14 | R5 | Thu 15/06/17 | Fri 15/09/17 | 100% | RP-170931 |  | Dish Network |  | ¦19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 19/09/17
2220 | 700079 | LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3 | 1 | Rel-14 | R4 | Tue 15/12/15 | Fri 15/12/17 | 99% | RP-152253 |  | Orange |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2221 | 700179 | Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Core | 2 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/06/16 | 100% | RP-161200 |  | Orange |  | 28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378¦1/7/16: Compl:40%->100%; | 36.858 | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
2222 | 700279 | Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/06/16 | 100% | RP-161200 |  | Orange |  | ¦22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16 |  | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
2223 | 750052 | UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69) | LTE_FDD_2600_CA_B3-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-172257 |  | Bureau Veritas |  | ¦19/9/17: Compl:43%->96%¦8/1/18: Compl:96%->100%¦ | [5 empty] | Mon 19/06/17 | Mon 08/01/18
2224 | 700080 | Multi-Band Base Station testing with three or more bands | MB_BS_test_3B | 1 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-152205 |  | Alcatel-Lucent |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2225 | 700180 | Core part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Core | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-162442 | RP-162032 | Alcatel-Lucent |  | 22/3/16: Compl:0%->50%22/3/16: WID: RP-152205->RP-1600631/7/16: Compl:50%->90%¦26/9/16: Compl:90%->95%¦26/9/16¦20/12/16: Compl:95%->100%¦ | 37.871 | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2226 | 700280 | Perf. part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-162442 |  | Alcatel-Lucent |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152205->RP-160063¦1/7/16: Compl:5%->30%26/9/16: Compl:30%->60%26/¦20/12/16: Compl:60%->100%¦ |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2227 | 700081 | Performance enhancements for high speed scenario in LTE | LTE_high_speed | 1 | Rel-14 | R4 | Tue 15/12/15 | Fri 14/09/18 | 99% | RP-152263 |  | NTT DOCOMO |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
2228 | 700181 | Core part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Core | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-160172 | RP-162222 | NTT DOCOMO |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152263->RP-160172¦1/7/16: Compl:5%->25%26/9/16: Compl:25%->45%20/12/16: Compl:45%->100%20/12/16: Stat Rep: ->RP-162222 |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2229 | 700282 | Perf. part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Perf | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 100% | RP-171039 |  | NTT DOCOMO |  | 22/3/16: WID: RP-152263->RP-1601721/7/16: Compl:0%->20%¦26/9/16: Compl:20%->25%¦20/12/16: Compl:25%->35% ¦21/3/17: Compl:35%->70%¦19/6/17: Compl:70%->100%¦19/6/17: WID: RP-160172->RP-171039 |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 19/06/17
2230 | 750056 | UE Conformance Test Aspects - Performance enhancements for high speed scenario in LTE | LTE_high_speed-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-170367 |  | CMCC |  | tested: REL-14 LTE_high_speed-Core;¦19/6/17: Compl: 1 8/1/18:27/3/ ;; 11/10/20: 95%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Sun 11/10/20
2231 | 710072 | Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2 | 1 | Rel-14 | R2 | Tue 15/03/16 | Fri 15/12/17 | 99% | RP-160538 |  | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2232 | 710172 | Core part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Core | 2 | Rel-14 | R2 | Tue 15/03/16 | Thu 15/12/16 | 100% | RP-162026 | RP-162506 | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->60%¦26/9/16: WID:¦20/12/16: Compl:60%->100%¦ |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
2233 | 710272 | Perf. part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-162026 |  | Huawei |  | 26/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160538->RP-161850¦20/12/16: Compl:0%->30%¦20/12/16: WI21/3/17: Compl:30%->50%19/6/17: Compl:50%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
2234 | 750053 | UE Conformance Test Aspects - RAT Independent Further Indoor Positioning Enhancements for LTE | LTE_iPos_enh2_RI-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Fri 15/12/17 | 100% | RP-172317 |  | NextNav |  | tested: REL-14 UTRA_LTE_iPos_enh2-Core (but only RAT independent aspects for LTE);¦ ; |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
2235 | 710076 | Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA | 1 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/03/18 | 99% | RP-160603 |  | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2236 | 710176 | Core part: Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA-Core | 2 | Rel-14 | R4 | Tue 15/03/16 | Fri 15/09/17 | 100% | RP-170278 |  | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part1/7/16: Compl:0%->10%1/7/16: WID: RP-160603->RP-16091426/9/16: Compl:10%->15%¦20/12/16: Compl:15%->25%¦20/12/16: WID: RP-160914->RP-162306;21/3/17: Compl:25%->33%;1 ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
2237 | 730071 | UE Conformance Test Aspects - Radiated Performance of Multiple-antenna Receivers in the LTE UE | LTE_MIMO_OTA-UEConTest | 2 | Rel-14 | R5 | Thu 15/09/16 | Thu 15/03/18 | 100% | RP-171615 |  | Intel |  | ¦20/12/16: Compl:0%->5%21/3/17: Compl:5%->20%19/6/17: Compl:20% 1 8/1/18: C27/3/ |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 27/03/18
2238 | 710077 | Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO | 1 | Rel-14 | R1 | Tue 15/03/16 | Fri 11/06/21 | 57% | RP-160623 |  | Samsung |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2239 | 710177 | Core part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Core | 2 | Rel-14 | R1 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-160623 | RP-170173 | Samsung |  | ¦1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->80%¦20/12/16: Stat Rep: -->¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170173 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2240 | 710277 | Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Fri 15/12/17 | 100% | RP-160623 |  | Samsung |  | ¦20/12/16: Stat Rep: -->¦19/6/17: Compl:0%->50%19/9/17: Compl:50%->70%19/9/17: CD:Fri 15/09/17->Fri 15/12/17¦8/1/18: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
2241 | 830085 | UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-UEConTest | 2 | Rel-14 | R5 | Fri 01/03/19 | Fri 11/06/21 | 5% | RP-190650 |  | Ericsson |  | 08/10/20: UID corrected (was 830185); 8/10/20: 0%->5; 8/10/20: FCD:13/09/2019->12/20; 8/4/21: FCD:11/12/2020->06/21 |  | 83 | 42 |  |  | Tue 26/03/19 | Thu 08/04/21
2242 | 710078 | Further mobility enhancements in LTE | LTE_eMob | 1 | Rel-14 | R2 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160636 |  | ZTE |  | no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2243 | 710178 | Core part: Further mobility enhancements in LTE | LTE_eMob-Core | 2 | Rel-14 | R2 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-162503 | RP-170369 | ZTE |  | no Perf. part¦1/7/16: Compl:0%->25%¦1/7/16: WID: RP-160636->RP-160921¦26/9/16: Compl:25%->50%¦20/12/16: Compl:50%->90%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/1721/3/17: Compl:90%->100%¦21/3/17: St |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2244 | 740265 | Perf. Part: Further mobility enhancements in LTE | LTE_eMob-Perf | 2 | Rel-14 | R4 | Thu 15/12/16 | Thu 15/06/17 | 100% | RP-162503 |  | ZTE | [7 empty] | Mon 19/06/17 | NA
2245 | 710079 | Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh | 1 | Rel-14 | R1 | Tue 15/03/16 | Fri 14/12/18 | 99% | RP-160664 |  | Ericsson |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2246 | 710179 | Core part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Core | 2 | Rel-14 | R1 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-162488 | RP-170115 | Ericsson |  | 1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->85%¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->21/3/17: Compl:85%->100%21/3/17: Stat Rep: ->RP-170115 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2247 | 710279 | Perf. part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Fri 15/09/17 | 100% | RP-162488 |  | Ericsson |  | ¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->;21/3/17: Compl:0%->20%19/6/17: Compl:20%->75%¦19/9/17: Compl:75%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
2248 | 780063 | UE Conformance Test Aspects - Uplink capacity enhancements for LTE | LTE_UL_CAP_enh-UEConTest | 2 | Rel-14 | R5 | Fri 15/12/17 | Fri 14/12/18 | 100% | RP-172639 |  | Ericsson |  | tested: REL-14 WI LTE_UL_CAP_enh-Core¦related to UL 256 QAM27/3 ;¦26/3/19: 35%->100 |  | 78 | 40 |  |  | Mon 08/01/18 | Tue 26/03/19
2249 | 710080 | L2 latency reduction techniques for LTE | LTE_LATRED_L2 | 1 | Rel-14 | R2 | Tue 15/03/16 | Thu 15/03/18 | 99% | RP-160667 |  | Ericsson |  | no Perf. part¦follow-up WI of SI FS_LTE_LATRED |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2250 | 710180 | Core part: L2 latency reduction techniques for LTE | LTE_LATRED_L2-Core | 2 | Rel-14 | R2 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-160667 | RP-172559 | Ericsson |  | no Perf. part¦follow-up WI of SI FS_LTE_LATRED¦1/7/16: Compl:0%->80%¦26/9/16: Compl:80%->100%8/1/18: Stat Rep: -->RP-172559 |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
2251 | 780064 | UE Conformance Test Aspects - L2 latency reduction techniques for LTE | LTE_LATRED_L2-UEConTest | 2 | Rel-14 | R5 | Fri 15/12/17 | Thu 15/03/18 | 100% | RP-180530 |  | Ericsson |  | tested: REL-14 WI LTE_LATRED_L2-Core27/3/18: Compl:0%->100%; |  | 78 | 40 |  |  | Mon 08/01/18 | Tue 27/03/18
2252 | 710081 | eMBMS enhancements for LTE | MBMS_LTE_enh2 | 1 | Rel-14 | R1 | Tue 15/03/16 | Fri 15/09/17 | 99% | RP-160675 | RP-171628 | Ericsson |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2253 | 710181 | Core part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Core | 2 | Rel-14 | R1 | Tue 15/03/16 | Fri 15/09/17 | 100% | RP-170199 |  | Ericsson |  | 1/7/16: Compl:0%->10%1/7/16: CD:Tue 15/03/16->Wed 15/03/171/7/16: WID: RP-160675->RP-16129726/9/16: Compl:10%->55%¦20/12/16: Compl:55%->80%¦20/12/16: WID: RP-161297->RP-162231 ¦21/3/17: Compl:80%->90% ¦19/6/17: Compl:90 ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
2254 | 710281 | Perf. part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Fri 15/09/17 | 100% | RP-170199 |  | Ericsson |  | ¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
2255 | 710082 | SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch | 1 | Rel-14 | R1 | Tue 15/03/16 | Fri 15/06/18 | 99% | RP-160676 |  | Huawei |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2256 | 710182 | Core part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Core | 2 | Rel-14 | R1 | Tue 15/03/16 | Thu 15/12/16 | 100% | RP-160935 | RP-162137 | Huawei |  | 1/7/16: Compl:0%->35%1/7/16: WID: RP-160676->RP-160935¦26/9/16: Compl:35%->55%¦20/12/16: Compl:55%->100%¦20/12/16: Stat Rep: -->RP-162137 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
2257 | 710282 | Perf. part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160935 |  | Huawei |  | 1/7/16: WID: RP-160676->RP-160935¦20/12/16: Stat Rep: --> 21/3/17: Compl:0%->25% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17¦19/6/17: Compl:25%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
2258 | 750054 | UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Fri 15/06/18 | 100% | RP-180848 |  | Huawei |  | tested: REL-14 LTE_SRS_switch-Core;¦19/6/17: Compl:0%->5%¦8/1/18: Compl:27/3/ ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
2259 | 710084 | Downlink Multiuser Superposition Transmission for LTE | LTE_MUST | 1 | Rel-14 | R1 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160680 |  | MediaTek |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
2260 | 710184 | Core part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Core | 2 | Rel-14 | R1 | Tue 15/03/16 | Thu 15/12/16 | 100% | RP-161019 | RP-162504 | MediaTek |  | ¦1/7/16: Compl:0%->40%¦1/7/16: WID: RP-160680->RP-16101926/9/16: Compl:40%->60%¦20/12/16: Compl:60%->100%¦20/12/16: Stat Rep: -->RP-162504 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
2261 | 710284 | Perf. part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-161019 |  | MediaTek |  | 1/7/16: WID: RP-160680->RP-161019¦26/9/16: CD:Fri 15/09/17->Thu 15/06/17¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:0%->25%19/6/17: Compl:25%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
2262 | 720040 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 1 | Rel-14 | C1 | Tue 14/06/16 | Wed 15/03/17 | 98% | CP-160294 |  |  |  | 11/6/16: 0%->15¦5/6/17: 67%->100 |  | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
2263 | 720070 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C1 | Tue 14/06/16 | Wed 15/03/17 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100¦16/9/16: 0%->30¦2/12/16: 30%->75¦6/3/17: 75%->100 |  | 72 | 37 |  |  | Thu 04/12/14 | Mon 06/03/17
2264 | 720071 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C1-IETF | Tue 14/06/16 | Wed 15/03/17 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage |  | draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update (became RFC 8122) | 72 | 37 |  |  | Thu 04/12/14 | Mon 07/12/15
2265 | 800112 | (IETF) Session Description Protocol (SDP) Offer/Answer Considerations for Datagram Transport Layer Security (DTLS) and Transport Layer Security (TLS) (draft-ietf-mmusic-dtls-sdp) | IMSProtoc8 | 2 | Rel-14 | C1-IETF | Tue 14/06/16 | Wed 15/03/17 | 90% | CP-160294 |  | Alcatel-Lucent | Keith Drage | 23/4/20: 25%->90; 9/4/21: RFC 8842 added; | RFC 8842 | 80 | 41 |  |  | Wed 27/06/18 | Fri 09/04/21
2266 | 720072 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C3 | Tue 14/06/16 | Wed 15/03/17 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage | 2/4/15: added, following CT3 chair's info that the WID also has a CT3 part¦June2015: Compl:0%->20¦07/09/15: 20%->40¦7/12/15: 40%->100¦20/9/16: 0%->10¦2/12/16: 10%->30¦6/3/17: 30%->100 |  | 72 | 37 |  |  | Thu 02/04/15 | Mon 06/03/17
2267 | 720094 | Multi-Carrier Enhancements for UMTS | UTRA_MCe | 1 | Rel-14 | R2 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-161259 |  | Huawei, HiSilicon |  | no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
2268 | 700059 | Study on Multi-Carrier Enhancements for UMTS | FS_UTRA_MCe | 2 | Rel-14 | R1 | Tue 15/12/15 | Wed 15/06/16 | 100% | RP-152290 |  | Huawei |  | 22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->100%¦28/7/16: 25.707 added; | 25.707 | 70 | 36 |  |  | Fri 01/01/16 | Thu 28/07/16
2269 | 720194 | Core part: Multi-Carrier Enhancements for UMTS | UTRA_MCe-Core | 2 | Rel-14 | R2 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-162453 | RP-162129 | Huawei, HiSilicon |  | no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe¦26/9/16: Compl:0%->35%¦20/12/16: Compl:35%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2270 | 720095 | Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US | 1 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-161219 |  | Nokia |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
2271 | 720195 | Core part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Core | 2 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-162007 |  | Nokia |  | 26/9/16: Compl:0%->70%¦6/10/16: 36.744 added¦20/12/16: Compl:70%->100%¦ | 36.744 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2272 | 720295 | Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Perf | 2 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-162007 |  | Nokia |  | ¦20/12/16: Compl:0%->100%¦ |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2273 | 740069 | UE Conformance Test Aspects – Citizens Broadband Radio Service (CBRS) 3.5GHz Band for LTE in the United States (Band 48) | LTE_TDD_3550_CBRS_US-UEConTest | 2 | Rel-14 | R5 | Thu 15/12/16 | Thu 15/06/17 | 100% | RP-162254 |  | Nokia |  | 21/3/17: Compl:0%->60% ¦ 19/6/17: Compl:60%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Mon 19/06/17
2274 | 720096 | LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2 | 1 | Rel-14 | R4 | Wed 15/06/16 | Wed 15/03/17 | 100% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
2275 | 720196 | Core part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Core | 2 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE¦26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2276 | 720296 | Perf. part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Perf | 2 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-161221 |  | Sprint |  | 26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2277 | 730076 | UE Conformance Test Aspects – LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-UEConTest | 2 | Rel-14 | R5 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161789 |  | Sprint |  | ¦20/12/16: Compl:0%->65% 21/3/17: Compl:65%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
2278 | 721002 | Dedicated Core Networks for GERAN | DECOR_GERAN | 1 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/09/16 | 100% | RP-161029 |  | Ericsson |  | no Perf. part¦DECOR was a REL-13 SA2 feature |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
2279 | 721102 | Core part: Dedicated Core Networks for GERAN | DECOR_GERAN-Core | 2 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/09/16 | 100% | RP-161029 | RP-170194 | Ericsson |  | no Perf. part¦DECOR was a REL-13 SA2 feature¦26/9/16: Compl:0%->100%21/3/17: Stat Rep: ->RP-170194 |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
2280 | 721003 | Positioning Enhancements for GERAN | ePOS_GERAN | 1 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-161260 |  | Ericsson |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
2281 | 721103 | Core part: Positioning Enhancements for GERAN | ePOS_GERAN-Core | 2 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-171052 | RP-170920 | Ericsson |  | 26/9/16: Compl:0%->30%¦20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ¦19/6/17: Compl:80%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
2282 | 721203 | Perf. part: Positioning Enhancements for GERAN | ePOS_GERAN-Perf | 2 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-171052 |  | Ericsson |  | ¦20/12/16: Compl:0%->50% ¦21/3/17: Compl:50%->80%¦19/6/17: Compl:80%->100%¦ |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
2283 | 730079 | Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming | 1 | Rel-14 | R2 | Wed 03/12/14 | Thu 15/03/18 | 99% | RP-161917 |  | China Unicom |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2284 | 660037 | Study on KQIs for Service Experience | FS_KQISE | 2 | Rel-14 | S5 | Wed 03/12/14 | Fri 11/03/16 | 100% | SP-150676 |  | Li, Hui (hui.li(at)huawei.com) | hui.li(at)huawei.com | Mar 15: 0->5%¦June2015: Compl:0%->40¦07/09/15: 40%->50¦14/09/15: WID:SP-140784->SP-150405¦7/12/15: 50%->75¦7/12/15: WID:SP-150405->SP-150676 ¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14 | 32.8xy | 66 | 34 |  |  | Thu 04/12/14 | Tue 22/03/16
2285 | 730179 | Core part:Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming-Core | 2 | Rel-14 | R2 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161917 | RP-170259 | China Unicom |  | ¦20/12/16: Compl:0%->60% ¦21/3/17: Compl:60%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
2286 | 750055 | UE Conformance Test Aspects -Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming-UEConTest | 2 | Rel-14 | R5 | Wed 15/03/17 | Thu 15/03/18 | 100% | RP-180559 |  | Huawei |  | tested: REL-14 UMTS_QMC_Streaming-Core;19/6/17: Comp 19/ 8/1/18: 27/3/ |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 27/03/18
2287 | 730080 | Flexible eNB-ID and Cell-ID in E-UTRAN | LTE_FNBID | 1 | Rel-14 | R3 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-161896 |  | China Telecom |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2288 | 710056 | Study on flexible eNB-ID and Cell-ID in E-UTRAN | FS_LTE_FNBID | 2 | Rel-14 | R3 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-160534 | - | China Telecom |  | 1/7/16: Compl:0%->60%26/9/16: Compl:60%->100% | New 36.896 | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2289 | 730180 | Core part: Flexible eNB-ID and Cell-ID in E-UTRAN | LTE_FNBID-Core | 2 | Rel-14 | R3 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161896 | RP-170478 | China Telecom |  | ¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
2290 | 730084 | 4 receiver (4Rx) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL) | LTE_4Rx_AP_DL_CA | 1 | Rel-14 | R4 | Thu 15/09/16 | Fri 14/09/18 | 99% | RP-161897 |  | Ericsson |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2291 | 730184 | Core part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL) | LTE_4Rx_AP_DL_CA-Core | 2 | Rel-14 | R4 | Thu 15/09/16 | Thu 15/12/16 | 100% | RP-161897 | RP-162059 | Ericsson |  | ¦20/12/16: Compl:0%->100%¦20/12/16: Stat Rep: ->RP-162059 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 20/12/16
2292 | 730284 | Perf. part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL) | LTE_4Rx_AP_DL_CA-Perf | 2 | Rel-14 | R4 | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-161897 |  | Ericsson |  | ¦20/12/16: Compl:0%->30%;21/3/17: Compl:30%->50%19/6/17: Compl:50%->90%¦19/9/17: Compl:90%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 19/09/17
2293 | 740071 | Introduction of new band support for 4Rx antenna ports for LTE | LTE_4Rx_AP_DL_bands | 2 | Rel-14 | R4 | Thu 15/12/16 | Fri 14/09/18 | 99% | RP-162496 |  | Huawei |  | Pending acronym |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
2294 | 740171 | Core part: Introduction of new band support for 4Rx antenna ports for LTE | LTE_4Rx_AP_DL_bands-Core | 3 | Rel-14 | R4 | Thu 15/12/16 | Thu 15/06/17 | 100% | RP-170307 |  | Huawei |  | ¦21/3/17: Compl:0%->80% ¦2119/6/17: Compl:80%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Mon 19/06/17
2295 | 750058 | UE Conformance Test Aspects - 4 Rx antenna ports with CA for LTE DL | LTE_4Rx_AP_DL_CA-UEConTest | 3 | Rel-14 | R5 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-170704 |  | Ericsson |  | tested: REL-14 LTE_4Rx_AP_DL_CA-Core¦19/6/17: C 1 8/1/18: C 27/3/ ;¦26/3/19: 90%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 26/03/19
2296 | 730085 | Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX | 1 | Rel-14 | R4 | Thu 15/09/16 | Fri 14/09/18 | 99% | RP-161898 |  | Qualcomm |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2297 | 730185 | Core part: Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX-Core | 2 | Rel-14 | R4 | Thu 15/09/16 | Thu 15/06/17 | 100% | RP-171149 | RP-171317 | Qualcomm |  | ¦20/12/16: Compl:0%->70%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17 ¦21/3/17: Compl:70%->95% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1 19/6/17: Compl:95%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
2298 | 730285 | Perf. part: Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX-Perf | 2 | Rel-14 | R4 | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-171149 |  | Qualcomm |  | ¦20/12/16: Compl:0%->20%¦20/12/16: CD:Thu 15/06/17->Fri 15/09/17 21/3/17: Compl:20%->70% ¦21/3/17: WID: RP-162570->RP-17079119/6/17: Compl:70%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
2299 | 760085 | UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE | LTE_UE_cat_1RX-UEConTest | 2 | Rel-14 | R5 | Thu 15/06/17 | Fri 14/09/18 | 100% | RP-180263 |  | Qualcomm |  | ¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100 |  | 76 | 39 |  |  | Fri 16/06/17 | Sun 11/10/20
2300 | 730086 | Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP) | LTE_WLAN_eLWIP | 1 | Rel-14 | R3 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161929 |  | Nokia |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2301 | 730186 | Core part: Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP) | LTE_WLAN_eLWIP-Core | 2 | Rel-14 | R3 | Thu 15/09/16 | Wed 15/03/17 | 100% | RP-161929 | RP-170706 | Nokia |  | ¦20/12/16: Compl:0%->60% 21/3/17: Compl:60%->100% 21/3/17: Stat Rep: ->RP-170706 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
2302 | 710083 | LTE Measurement Gap Enhancement | LTE_meas_gap_enh | 1 | Rel-14 |  | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160678 |  | Intel |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2303 | 710183 | Core part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Core | 2 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160912 | RP-171330 | Intel |  | ¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
2304 | 710283 | Perf. part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Perf | 2 | Rel-14 | R4 | Tue 15/03/16 | Thu 15/06/17 | 100% | RP-160912 |  | Intel |  | 1/7/16: WID: RP-160678->RP-1609121/7/16: Release: Rel-15->Rel-14¦20/12/16: Stat Rep: -->¦20/12/16: Release: Rel-15->Rel-14 21/3/17: Compl:0%->20% 21/3/17: Release: Rel19/6/17: Compl:20%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
2305 | 730082 | Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE | LTE_eCRSIM_eSUMIMO | 1 | Rel-14 |  | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-161877 |  | Intel |  |  | 39.747 | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
2306 | 730282 | Perf. part: Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE | LTE_eCRSIM_eSUMIMO-Perf | 2 | Rel-14 | R4 | Thu 15/09/16 | Fri 15/09/17 | 100% | RP-162303 |  | Intel |  | 6/10/16: 36.176 added¦20/12/16: Compl:0%->30%21/3/17: Compl:30%->50% ¦21/3/17: Release: Rel-15->Rel-14¦19/6/17: Compl:50%->85%19/9/17: Compl:85%->100% | 36.176 | 73 | 37 |  |  | Mon 26/09/16 | Tue 19/09/17
2307 | 780051 | Miscellaneous IETF dependencies | TEI14_IETF | 1 | Rel-14 |  | Wed 15/03/17 | Fri 05/06/20 | 75% |  |  |  |  | Created upon demand of RAN5 |  | 78 | 40 |  |  | Mon 18/12/17 | NA
2308 | 870066 | (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel) | TEI14_IETF | 2 | Rel-14 | CT1-IETF | Thu 06/02/20 | Fri 05/06/20 | 80% |  |  |  |  | 9/4/21: RFC 8865 added; | RFC 8865 | 78 | 40 |  |  | Mon 18/12/17 | Fri 09/04/21
2309 | 780052 | (IETF) SDP Offer/Answer Clarifications for RTP/RTCP Multiplexing [RFC 5761 (was draft-ietf-avtcore-5761-update)] | TEI14_IETF | 2 | Rel-14 | CT1-IETF | Wed 15/03/17 | Fri 15/09/17 | 100% | [6 empty] | 78 | 40 |  |  | Mon 18/12/17 | NA
2310 | 780053 | (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel) | TEI14_IETF | 2 | Rel-14 | CT1-IETF | Wed 15/03/17 | Thu 14/12/17 | 25% |  |  |  |  | was (IETF) T.140 Text Conversation over Data Channels (draft-schwarz-mmusic-t140-usage-data-channel); 9/4/21: RFC 8865 added; | RFC 8865 | 78 | 40 |  |  | Mon 18/12/17 | Fri 09/04/21
2311 | 780054 | (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel) | TEI14_IETF | 2 | Rel-14 | CT1-IETF | Wed 15/03/17 | Thu 14/12/17 | 100% |  |  |  |  | 22/3/18: 25%->100. was (IETF) BFCP floor control signalling over Data Channels (draft-schwarz-mmusic-bfcp-usage-data-channel). ; 9/4/21: RFC 8865 added; | RFC 8865 | 78 | 40 |  |  | Mon 18/12/17 | Fri 09/04/21
2312 | 870068 | (IETF) Negotiating Media Multiplexing Using the Session Description Protocol (SDP) (draft-ietf-mmusic-sdp-bundle-negotiation) | TEI14_IETF | 2 | Rel-14 | C1-IETF | Mon 23/03/20 | Thu 23/04/20 | 90% |  |  |  |  | 9/4/21: RFC 8843 added; | RFC 8843 | 87 | 44 |  |  | Thu 23/04/20 | Fri 09/04/21
2313 | 870069 | (IETF) Indicating Exclusive Support of RTP/RTCP Multiplexing using SDP (draft-ietf-mmusic-mux-exclusive) | TEI14_IETF | 2 | Rel-14 | C1-IETF | Mon 23/03/20 | Thu 23/04/20 | 90% |  |  |  |  | 9/4/21: RFC 8858 added; | RFC 8858 | 87 | 44 |  |  | Thu 23/04/20 | Fri 09/04/21
2314 | 870082 | (IETF) IP Mobility Support for IPv4, Revised (draft-ietf-mip4-rfc3344bis) --> RFC 5944 | TEI14_IETF | 2 | Rel-14 | C1-IETF | Mon 23/03/20 | Thu 23/04/20 | 100% | [6 empty] | 87 | 44 |  |  | Thu 23/04/20 | NA
2315 | 620062 | Security Assurance Specification for 3GPP network products | SCAS | 1 | Rel-14 | S3 | Mon 09/12/13 | Thu 15/06/17 | 100% | SP-150292 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | Triggered by Rel-12 TR 33.805 Study on Security Assurance Methodology for 3GPP Network Elements (FS_SECAM)¦June2015: WID:SP-130718->SP-150292. Aug 15: TR numb added¦28/1/16: 33.926 added¦28/7/16: 33.250 added;06/10/16: moved to Rel-14 as per John/M... | 33.199; 33.926, 33.117; 33.250; 33.515 | 62 | 32 |  |  | Fri 22/11/13 | Mon 06/08/18
2316 | 620162 | STOPPED - TR on Pilot development of Security Assurance Specification for MME network product class | SCAS-SA3Pil_TR | 2 | Rel-14 | S3 | Mon 09/12/13 | Fri 12/12/14 | 100% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR collects input for the new TS 33.116. Dec.14: 55->70%. 3/3/15: 70->55%. 10/03/15: 55->75%¦June2015: Compl:75%->80¦7/12/15: STOPPED AT 80% (marked as 100% here since no more work expected) | New 33.806 | 62 | 32 |  |  | Fri 22/11/13 | Mon 07/12/15
2317 | 620362 | TR on Security Assurance scheme for 3GPP network products | SCAS-SA3TR | 2 | Rel-14 | S3 | Mon 09/12/13 | Thu 15/12/16 | 100% | SP-150716 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR contains results of the second WID objective. Dec.14: 75->85%¦June2015: Compl:85%->90¦7/12/15: 90%->92¦10/12/15: WID:SP-130718->SP-150716¦19/9/16: 92%->98. FCD set to 12.16 (was 03/16)¦6/10/16: 33.216 added¦1/12/16: 81%->100 | New 33.916; 33.216 | 62 | 32 |  |  | Fri 22/11/13 | Thu 01/12/16
2318 | 620262 | Security Assurance Specification for 3GPP network product classes | SCAS-SA3 | 2 | Rel-14 | S3 | Fri 13/12/13 | Thu 15/06/17 | 100% | SP-150716 | - | China Mobile | Judy Zhu (zhuhongru@chinamobile.com) | June2015: 0%->5¦7/12/15: 5%->72.¦10/12/15: WID:SP-130718->SP-150716¦7/3/16: 72%->75¦28/7/16: 33.250 added¦19/9/16: 75%->90. FCD set to 12.16 (was 03/16). 6/3/17: moved from Rel-14.¦15/2/18: moved back to Rel-14¦6/8/18: 33.515 added; | New 33.116, 33.117; 33.250; 22.511; 22.512; 22.513; 22.514; 33.515 | 62 | 32 |  |  | Fri 22/11/13 | Mon 06/08/18
2319 | 680099 | (Small) Technical Enhancements and Improvements for Rel-14 | TEI14 | 1 | Rel-14 | SP,CP,RP,R4 | Mon 11/05/15 | Thu 18/06/15 | 100% | [6 empty] | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
2320 | 689999 | (Small) Test Technical Enhancements and Improvements for Rel-14 | TEI14_Test | 1 | Rel-14 | SP,CP,RP,GP | Tue 13/09/16 | Thu 20/12/18 | 100% | - |  | - | - | Created upon demand of RAN5 | - |  |  |  |  | Mon 12/01/15 | Wed 24/02/16
2321 | 709998 | Rel-14 LTE Carrier Aggregation | LTE_CA_Rel14 | 1 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
2322 | 690086 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12 | 2 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
2323 | 690186 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Core | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2324 | 690286 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Perf | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2325 | 690087 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12 | 2 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
2326 | 690187 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Core | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2327 | 690287 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Perf | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2328 | 690088 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12 | 2 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
2329 | 690188 | Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Core | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2330 | 690288 | Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Perf | 3 | Rel-14 | R4 | Tue 15/09/15 | Tue 15/03/16 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
2331 | 709999 | Rel-14LTE Advanced inter-band Carrier Aggregation | LTE_AIBCA_Rel14 | 1 | Rel-14 | R4 | Tue 15/12/15 | Fri 11/06/21 | 76% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
2332 | 700069 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-151671 |  | Nokia Networks |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2333 | 700169 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-170143 |  | Nokia Networks |  | 28/1/16: 36.714-05-01 added¦22/3/16: Compl:0%->15%¦22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%¦26/9/16: Compl:40%->60%¦20/12/16: Compl ¦21/3/17 | 36.714-05-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2334 | 700269 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-170143 |  | Nokia Networks |  | 22/3/16: WID: RP-151671->RP-1606151/7/16: WID: RP-160615->RP-16105226/9/16: WID: RP-161052->RP-161496¦20/12/16: Compl:0%->90% ¦21/3/17: Compl:90%->95%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2335 | 700070 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 80% | RP-152196 |  | Qualcomm |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2336 | 700170 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 80% | RP-170123 |  | Qualcomm |  | 28/1/16: 36.714-02-01 added¦22/3/16: Compl:0%->20%¦22/3/16: WID: RP-152196->RP-160616¦1/7/16: Compl:20%->30%¦1/7/16: WI26/9/16: Compl:30%->50%¦20/12/16: Com 21/3/17: | 36.714-02-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2337 | 700270 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 80% | RP-170123 |  | Qualcomm |  | 22/3/16: WID: RP-152196->RP-1606161/7/16: Compl:0%->30%1/7/16: WID: RP-160616->RP-161202¦26/9/16: Compl:30%->50% 20/12/16: Compl:50%->75% 21/3/17: Compl:75%->80%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2338 | 700071 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-152237 |  | Huawei |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2339 | 700171 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-170312 |  | Huawei |  | 28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192¦1/7/16: Compl:20%->40%¦26/9/16: Compl:40%->60%¦20/12/16: C ¦21/3/17: | 36.714-02-02 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2340 | 700271 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-170312 |  | Huawei |  | ¦22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-16094726/9/16: WID: RP-160947->RP-161676¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->90 |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2341 | 700072 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/03/17 | 100% | RP-152241 |  | Nokia Networks |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2342 | 700172 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/03/17 | 100% | RP-152241 |  | Nokia Networks |  | 28/1/16: 36.714-03-03 added;22/3/16: Compl:0%->1%1/7/16: Compl:1%->15%¦21/3/17: Compl:15%->100% | 36.714-03-03 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2343 | 700272 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Wed 15/03/17 | 100% | RP-152241 |  | Nokia Networks |  | ¦1/7/16: Compl:0%->15%21/3/17: Compl:15%->100% |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2344 | 700073 | LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 48% | RP-152246 |  | LG Electronics |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2345 | 700173 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-170128 |  | LG Electronics |  | 28/1/16: 36.714-00-02 added¦22/3/16: Compl:0%->10%¦22/3/16: WID: RP-152246->RP-160148¦1/7/16: Compl:10%->40%¦26/9/16: Compl:40%->70%¦20/¦21/3/17: | 36.714-00-02 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2346 | 700273 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 0% | RP-170128 |  | LG Electronics |  | 22/3/16: WID: RP-152246->RP-1601481/7/16: WID: RP-160148->RP-160748¦26/9/16: WID: RP-160748->RP-161487¦20/12/16: WID: RP-161487->RP-16203621/3/17: |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2347 | 700074 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-152249 |  | Ericsson |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2348 | 700174 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-170189 |  | Ericsson |  | 28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%¦26/9/16: Compl:38%->74%¦20/12/16: Compl:74%->9521/3/1 | 36.714-04-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2349 | 700274 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 95% | RP-170189 |  | Ericsson |  | ¦22/3/16: WID: RP-152249->RP-160614¦1/7/16: Compl:0%->38%¦1/7/16: WID: RP-160614->RP-16082126/9/16: Compl:38%->0%¦20/12/16: Compl:0%->95% ¦21/3/17: CD:Wed 1 |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2350 | 700075 | LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 82% | RP-152250 |  | Ericsson |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2351 | 700175 | Core part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 82% | RP-170188 |  | Ericsson |  | 28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613¦1/7/16: Compl:60%->50%¦1/7/16: WID: RP-160613¦26/9/16: Compl:50%->44%¦20/12/16:21/3/1 | 36.714-00-00 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2352 | 700275 | Perf. part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 82% | RP-170188 |  | Ericsson |  | ¦22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-16082226/9/16: WID: RP-160822->RP-161473¦20/12/16: Compl:50%->64% 21/3/17: Compl:64%-> |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2353 | 700076 | LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL | 2 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-152278 |  | Huawei |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
2354 | 700176 | Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Core | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-170309 |  | Huawei |  | 28/1/16: 36.714-03-01 added;22/3/16: Compl:0%->15%22/3/16: WID: RP-152278->RP-1605821/7/16: Compl:15%->40%1/7/1626/9/16: Compl:40%->60%¦20/12/16: Compl:60%->80 21/3/1 | 36.714-03-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2355 | 700276 | Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Perf | 3 | Rel-14 | R4 | Tue 15/12/15 | Thu 15/06/17 | 90% | RP-170309 |  | Huawei |  | 22/3/16: WID: RP-152278->RP-160582¦1/7/16: WID: RP-160582->RP-160945¦26/9/16: WID: RP-160945->RP-161674¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->90%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
2356 | 720098 | UE Conformance Test Aspects – Rel-14 CA configurations | LTE_CA_R14-UEConTest | 2 | Rel-14 | R5 | Wed 15/06/16 | Fri 11/06/21 | 38% | RP-161528 |  | Ericsson |  | testing REL-14 CA basket WIs: LTE_CA_R14_intra-Core, LTE_CA_R14_2DL1UL-Core, LTE_CA_R14_3DL1UL-Core, LTE_CA_R14_4DL1UL-Core, LTE_CA_R14_5DL1UL-Core, LTE_CA_R14_2DL2UL-Core, LTE_CA_R14_xDL2UL-Core, LTE_CA_R14_3DL3UL-Core ;; 8/10/20: 20%->38; 8/10/20: F... |  | TSG#72 | PCG-37 |  |  | Fri 01/07/16 | Thu 08/04/21
2357 | 0 | Release 14 Studies | - | 1 | Rel-14 | SP,RP,CP,GP | Wed 17/09/14 | Fri 11/12/15 | 100% | - | - |  | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
2358 | 690060 | Study on channel model for frequency spectrum above 6 GHz | FS_6GHz_CH_model | 1 | Rel-14 | R1 | Tue 15/09/15 | Wed 15/06/16 | 100% | RP-160210 |  | Samsung |  | will start only in RAN in Q4/15¦28/1/16: 38.900 added¦22/3/16: Compl:10%->20%¦22/3/16: WID: RP-151606->RP-160210¦1/7/16: Compl:20%->100%. 2/12/16: Moved to Rel-15 according JMM email to move all 38.xxx related WIDs to Rel-15¦21/3/17: Stat Rep: --> | 38.9 | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
2359 | 700058 | Study on Scenarios and Requirements for Next Generation Access Technologies | FS_NG_SReq | 1 | Rel-14 | RP | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-160811 |  | CMCC |  | 22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%¦14/12/16: FCD:09/16->12/16¦14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re | 38.xxx | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2360 | 720086 | Study on NB-IoT RF requirement for coexistence with CDMA | FS_NB_IOT_CDMA_coex | 1 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-161187 |  | China Telecom |  | ¦26/9/16: Compl:0%->35%¦6/10/16: 36.752 added¦20/12/16: Compl:35%->100% | 36.752 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2361 | 610032 | Study on need for Multiple Access Point Names | FS_MAPN | 1 | Rel-14 | S1 | Thu 12/09/13 | Fri 19/06/15 | 100% | SP-130416 |  | Giesecke & Devrient | Ilario.macchi@gi-de.com | SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%¦June2015: Compl:90%->100 | 22.802 | 61 | 31 |  |  | Mon 26/08/13 | Mon 15/06/15
2362 | 620071 | Study on Multimedia Broadcast Supplement for Public Warning System | FS_MBSP | 1 | Rel-14 | S1 | Wed 11/12/13 | Fri 12/12/14 | 100% | SP-130599 |  | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100% | 22.815 | 62 | 32 |  |  | Tue 26/11/13 | Wed 03/12/14
2363 | 630018 | Study on service aspects for dealing with User Control over spoofed calls | FS_UC_SPOOF | 1 | Rel-14 | S1 | Fri 07/03/14 | Fri 20/03/15 | 100% | SP-140074 |  | Sprint | Gregory.schumacher@sprint.com | SP#65 moved to Rel-14. Linked to SA3 Rel-11 TR 33.838 PUCI and Rel-12 ongoing study TR 33.831 (FS_SPOOF). Dec.14: 70->90, CD: 12/14->03/15. Mar.15: 100% | 22.898 | 63 | 32 |  |  | Wed 05/02/14 | Wed 04/03/15
2364 | 640060 | Study on User Location Reporting Support enhancements | FS_eULRS | 1 | Rel-14 | S1 | Thu 19/06/14 | Wed 17/06/15 | 100% | SP-140402 |  | China Unicom | Zhuoyun Zhang ( zhangzy910@chinaunicom.cn) | SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%¦June2015: Compl:90%->100 | 22.899 | 64 | 33 |  |  | Thu 29/05/14 | Mon 15/06/15
2365 | 640061 | Study on Control of Applications when Third party Servers encounter difficulties | FS_CATS | 1 | Rel-14 | S1 | Thu 19/06/14 | Mon 15/06/15 | 100% | SP-140758 |  | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 completion 12/14=>03/15. Moved to Rel-14. Linked to Rel-13 Feature SEES and Rel-13 TR 22.806 (FS_ACDC). Dec.14: 30->60%, WID SP-140246->SP-140758, CD: 12/14->03/15. Mar.15: CD: 03/13->06/15. 60->90%¦June2015: Compl:90%->100 | 22.818 | 64 | 33 |  |  | Thu 29/05/14 | Mon 15/06/15
2366 | 670011 | Study on Paging Policy Enhancements and Procedure Optimizations in LTE | FS_PPEPO_LTE | 1 | Rel-14 | S1 | Tue 14/04/15 | Tue 15/12/15 | 100% | SP-150053 |  | Zhuoyun Zhang (China Unicom) | zhangzy910@chinaunicom.cn | 1/4/15:TR number added¦June2015: Compl:0%->40¦07/09/15: 40%->60¦7/12/15: 60%->100 | New 22.838 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
2367 | 670041 | Study on Latency reduction techniques for LTE | FS_LTE_LATRED | 1 | Rel-14 | R2 | Mon 16/03/15 | Wed 15/06/16 | 100% | RP-150465 |  | Ericsson |  | 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%; | 36.881 | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
2368 | 680057 | Study on High Power LTE UE for Band 41 | FS_LTE_B41_HPUE | 1 | Rel-14 | R4 | Mon 15/06/15 | Wed 15/06/16 | 100% | RP-160092 |  | Sprint |  | 7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ¦22/3/16: Compl:10%->40%¦22/3/16: WID: RP-151104->RP-1600921/7/16: Compl | 36.886 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
2369 | 680049 | Study on Media and Quality Aspects of SRVCC Enhancements | FS_SETA_S4 | 1 | Rel-14 | S4 | Thu 18/06/15 | Fri 11/03/16 | 100% | SP-150361 |  | Frédéric Gabin, Ericsson LM | frederic . gabin @ ericsson . com | Aug2015: 0%->25¦07/09/15: 25%->30¦7/12/15: 30%->80, FCD: 12/15->03/16, MOVED TO REL-14¦7/3/16: 80%->100 | New 26.916, 26.114 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/03/16
2370 | 720085 | Deleted - Study on SON for eCoMP for LTE | delFS_LTE_SON_eCOMP | 1 | Rel-14 | R3 | Tue 14/06/16 | Thu 16/06/16 | 100% | RP-161181 |  | Nokia |  | 26/9/16: Compl:0%->10%. 1/12/16: Deleted: 720085 was allocated twice: to FS_LTE_SON-ECOMP (now in 720063) and to ROBVOLTE (now in 720301) | 23.228, 23.237 | 72 | 37 |  |  | Mon 07/12/15 | Mon 26/09/16
2371 | 700036 | Study on UICC power optimization for MTC | FS_UICC_MTC_OPT | 1 | Rel-14 | C6 | Wed 15/06/16 | Thu 15/12/16 | 100% | CP-150875 |  | Berionne, Michele | micheleb [at] qti [dot] qualcomm [dot] com | 7/3/16: 0%->100¦5/6/17: 71%->100 | 31.97 | 70 | 36 |  |  | Mon 07/12/15 | Mon 05/06/17
2372 | 710013 | Study on Server and Network Assisted DASH for 3GPP | FS_SAND | 1 | Rel-14 | S4 | Tue 01/03/16 | Thu 15/12/16 | 100% | SP-160083 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100 | TR26.957 | 71 | 36 |  |  | Tue 01/03/16 | Thu 01/12/16
2373 | 710016 | Study on MBMS usage for mission critical communication services | FS_MBMS_MCservices | 1 | Rel-14 | C1 | Tue 01/03/16 | Tue 01/03/16 | 99% | SP-160728 |  | Magnus Tränk, Ericsson LM | magnus.trank@ericsson.com | 11/6/16: 0%->35. Name corrected¦19/9/16: WID:SP-160201->SP-160525¦FCD: 09/16->12/16¦19/9/16: 35%->60¦23/9/16: WID:SP-160525->SP-160728¦1/12/16: 60%->95¦3/3/17: 95%->100 | 23.78 | 71 | 36 |  |  | Tue 01/03/16 | Fri 03/03/17
2374 | 710057 | Study on enhancement of VoLTE | FS_LTE_eVoLTE | 1 | Rel-14 | R2 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-160902 | - | CMCC |  | 1/7/16: Compl:0%->75%1/7/16: WI¦28/7/16: 36.750 added¦26/9/16: Compl:75%->100% | 36.75 | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2375 | 710058 | Study on HSPA and LTE Joint Operation | FS_UTRA_LTE_JOP | 1 | Rel-14 | R3 | Tue 15/03/16 | Thu 15/12/16 | 100% | RP-160571 |  | China Unicom |  | ¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦ | New 37.805 | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
2376 | 710059 | Study on LTE Advanced Carrier Aggregation of Band 3 and Band 39 | FS_LTE_CA_B3_B39 | 1 | Rel-14 | R4 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-161704 |  | ZTE |  | intention to capture results in existing TR 36.714-02-01 ¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->50%¦20/12/16: Compl ¦21/3/17: Compl:8 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2377 | 710060 | Study on Context Aware Service Delivery in RAN for LTE | FS_LTE_context | 1 | Rel-14 | R3 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-160906 |  | CMCC |  | 1/7/16: Compl:0%->25%1/26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->70% ¦21/3/17: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2378 | 710061 | Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | FS_feCOMP_LTE | 1 | Rel-14 | R1 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-160954 |  | Intel |  | ¦1/7/16: Compl:0%->15%¦26/9/16: Compl:15%->30%¦20/12/16: Compl:30%->80%21/3/17: Compl:80%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2379 | 670015 | Study on Determination of Completeness of Charging Information in IMS | FS_DCCHII | 1 | Rel-14 | S5 | Thu 05/03/15 | Fri 11/03/16 | 100% | SP-150106 |  | Jesske, Roland | r.jesske@telekom.de | 11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request¦June2015: Compl:0%->7¦07/09/15: 7%->15¦7/12/15: 15%->60, FCD: 09/15->03/16¦7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14 | 32.xyz | 67 | 34 |  |  | Thu 05/03/15 | Tue 22/03/16
2380 | 660058 | Study on Interactivity Support for 3GPP-based Streaming and Download Services | FS_IS3 | 1 | Rel-14 | S4 | Fri 12/12/14 | Fri 10/03/17 | 100% | SP-140742 |  | Lo, Charles, Qualcomm | clo@qti.qualcomm.com | TR number added. Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->30, FCD: 12/15->03/16¦7/3/16: 30%->40. 15/4/16: moved from Rel-13. FCD: 11/3/16->23/9/16¦11/6/16: 40%->50¦19/9/16: 50%->70, FCD:09/16->12/16¦1/12/16: 70%->80; | 26.953 | 66 | 34 |  |  | Fri 12/12/14 | Mon 06/03/17
2381 | 720026 | Study on MBMS usage and codecs for MCPTT call and MC Video Service | FS_MCP_V | 1 | Rel-14 | S4 | Mon 13/06/16 | Wed 15/03/17 | 100% | SP-160274 |  | Zhiming Li, Huawei | lizhiming@huawei.com | 28/7/16: 26.880 added¦19/9/16: 0%->30, FCD: 12/16->03/17¦1/12/16: 30%->60¦6/3/17: 60%->100 | 26.88 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
2382 | 720027 | Study on MBMS Extensions for Provisioning and Content Ingestion | FS_xMBMS | 1 | Rel-14 | S4 | Mon 13/06/16 | Fri 10/03/17 | 100% | SP-160275 |  | Kyungmo Park, sk telecom | kyungmo.park@sk.com | 28/7/16: 26.981 added¦19/9/16: 0%->30¦1/12/16: 30%->50¦1/12/16: FCD:12/16->03/17¦6/3/17: 50%->100 | 26.981 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
2383 | 720088 | Study on global application of LTE Band 11 and of LTE Band 21 UEs | FS_LTE_B11_B21_global | 1 | Rel-14 | R4 | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-161220 |  | SoftBank |  | 26/9/16: Compl:0%->30%¦6/10/16: 36.745 added¦20/12/16: Compl:30%->100% | 36.745 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
2384 | 720089 | Study on Downlink MIMO for GERAN | FS_DOMIMO_RAN6 | 1 | Rel-14 | R6 | Wed 15/06/16 | Thu 15/09/16 | 100% | RP-161261 |  | Nokia, Alcatel-Lucent Shanghai Bell |  | continuation of GERAN SI UID 590034, DOMIMO under RAN626/9/16: Compl:0%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
2385 | 700018 | Release 14 studies on 5G MObile Network for Advanced communications |  | 1 | Rel-14 | S1 | Mon 02/02/15 | Thu 15/12/16 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 11/3: WID: SP-150050->150142¦June2015: Compl:0%->20¦07/09/15: 20%->60. 07/12/15: Created by MCC as BB to dissociate SA1 versus SA2 aspects | New 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
2386 | 700022 | Study on Stage 1 for New Services and Markets Technology Enablers | FS_SMARTER | 1 | Rel-14 | S1 | Mon 02/02/15 | Fri 10/06/16 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com |  | New 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
2387 | 670008 | General aspects of FS_SMARTER SA1 | FS_SMARTER | 2 | Rel-14 | S1 | Mon 02/02/15 | Fri 12/02/16 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 7/12/15: 60%->85¦2/3/16: 85%->95¦7/6/17: 95%->100 | New 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Wed 07/06/17
2388 | 700023 | FS_SMARTER – massive Internet of Things | FS_SMARTER-mIoT | 2 | Rel-14 | S1 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150817 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 2/3/16: 35%->65¦9/6/16: 65%->100 | New 22.861 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2389 | 700024 | FS_SMARTER – Critical Communications | FS_SMARTER-CRIC | 2 | Rel-14 | S1 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150818 |  | Kanerva, Mikko | mikko.kanerva@nokia.com | 2/3/16: 15%->60¦9/6/16: 60%->95¦7/6/17: 95%->100 | New 22.862 | 70 | 36 |  |  | Mon 07/12/15 | Wed 07/06/17
2390 | 700025 | FS_SMARTER – enhanced Mobile Broadband | FS_SMARTER-eMBB | 2 | Rel-14 | S1 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150819 |  | Laurence Meriau | laurence.meriau@huawei.com | 2/3/16: 40%->75¦9/6/16: 75%->100 | New 22.863 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
2391 | 700026 | FS_SMARTER – Network Operation | FS_SMARTER-NEO | 2 | Rel-14 | S1 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150820 |  | Lu Lu | lulu@chinamobile.com | 2/3/16: 30%->60¦19/9/16: 60%->100 | New 22.864 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
2392 | 700017 | SA2 aspects on Study on Architecture and Security for next Generation System | FS_NextGen | 1 | Rel-14 | S2 | Mon 07/12/15 | Thu 15/12/16 | 100% | SP-160727 |  | suntao@chinamobile.com, devaki.chandramouli@nokia.com | suntao@chinamobile.com, devaki.chandramouli@nokia.com | 28/1/16: 23.799 added¦Acronym corrected ("NexGen"->"NextGen")¦7/3/16: 5%->15¦10/3/16: WID:SP-150853->SP-160200. Name changed from "Study on Architecture for next Generation System"¦9/6/16: 15%->35¦19/9/16: 35%->64¦22/9/16: WID:SP-160227->SP-16072 | 23.799 | 70 | 36 |  |  | Mon 07/12/15 | Thu 01/12/16
2393 | 710062 | Study on New Radio (NR) Access Technology | FS_NR_newRAT | 1 | Rel-14 | R1 | Tue 15/03/16 | Wed 15/03/17 | 100% | RP-170379 |  | NTT DOCOMO |  | includes RAN TR 38.801¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160671->RP-161214¦1/7/16: Release: Rel-15->Rel-14¦28/7/16: 38.802 added¦26/9/16: Compl:10%->20%¦26/9/16: WID: RP-161214->RP-161596. 2/12/16: Moved | 38.801, 38.912; 38.802; 38.901; 38.805 | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
2394 | 0 | --- RELEASE 13 --- | - | 1 | Rel-13 | SP,RP,CP,GP | Wed 11/12/13 | Tue 25/11/14 | 100% | - | - |  |  | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
2395 | 620064 | Mission Critical Push To Talk over LTE (MCPTT) | MCPTT | 1 | Rel-13 |  | Wed 11/12/13 | Fri 15/06/18 | 98% | SP-150356 | - | NIST | david.cypher@nist.gov | SP#65 updated WID SP-140276=>SP-140435. Mar 15: WID: SP-140879->SP-150164. 4/15: S4 added. 6/15: WID updated | Stage 1/2; | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/07/16
2396 | 640142 | Study on Application Architecture to support MCPTT | MCPTT | 2 | Rel-13 | S6 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-150356 | - | Yannick Lair | yannick.lair@lge.com | SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435. Dec.14: 2->20%. Mar 15: WID: SP-140879->SP-150095. Mar15: 30%. Transferred to SA6. June 15: FCD shifted to Sept,WID updated¦June2015: Compl:24%->50¦June2015: Compl:50%->70. 3/8/15: Rapp | New 23.779 | 64 | 33 |  |  | Wed 04/06/14 | Mon 07/09/15
2397 | 670030 | SA2 Study on Architecture Enhancements at the EPS and IMS Level to Support MCPTT | MCPTT | 2 | Rel-13 | S2 | Fri 13/03/15 | Wed 17/06/15 | 100% | SP-150356 |  | Randy Bloomfield (randy@its.bldrdoc.gov) | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: WID: SP-140879->SP-150164.¦June2015: Compl:0%->30, WID updated¦07/09/15: 30%->100, "To be confirmed" deleted, since SA2 has completed it. |  | 67 | 34 |  |  | Fri 13/03/15 | Mon 07/09/15
2398 | 670032 | Study on Security Enhancements for MCPTT | MCPTT | 2 | Rel-13 | S3 | Fri 13/03/15 | Fri 11/03/16 | 100% | SP-150356 |  | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated¦7/12/15: 0%->75¦10/12/15: FCD->March, ES in SP-150729¦7/3/16: 75%->80¦28/7/16: 33.280 added¦28/7/16: 39.880 added¦1/12/16: 80%->100 | 33.879; 33.280; 39.880 | 67 | 34 |  |  | Fri 13/03/15 | Thu 01/12/16
2399 | 670022 | Study on media, codecs and MBMS enhancements for MCPTT | MCPTT | 2 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/03/16 | 100% | SP-150356 |  | Zhiming Li (lizhiming@huawei.com) | Zhiming Li (lizhiming@huawei.com) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. 5/5/15: TR number added¦June2015: Compl:0%->5, WID updated¦Aug2015: 5%->15¦07/09/15: 15%->40¦7/12/15: 40%->80, FCD: 12/15->03/16¦7/3/16: 80%->85; 26/6/20: 85%->100 | New 26.879 | 67 | 34 |  |  | Thu 05/03/15 | Fri 26/06/20
2400 | 620164 | Stage 1 for MCPTT | MCPTT | 2 | Rel-13 | S1 | Wed 11/12/13 | Fri 12/12/14 | 100% | SP-150356 | SP-140502 | NIST | david.cypher@nist.gov | SP#65 completion 09/14=>12/14. Exception in SP-140502. TS 22.179v100 for Information. Completed. Mar 15: WID: SP-140879->SP-150164. 6/15: WID updated | New 22.179 | 62 | 32 |  |  | Tue 26/11/13 | Thu 18/06/15
2401 | 640143 | Functional architecture and information flows to support MCPTT | MCPTT | 2 | Rel-13 | S6 | Thu 18/06/15 | Fri 11/12/15 | 100% | SP-150356 | - | Yannick Lair | yannick.lair@lge.com | June2015: added as per SP-150356¦June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID¦07/09/15: 15%->50¦07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15¦7/3/16: 85%->100 | New 23.179 | 64 | 33 |  |  | Wed 04/06/14 | Mon 07/03/16
2402 | 660053 | Security of MCPTT | MCPTT | 2 | Rel-13 | S3 | Fri 12/12/14 | Fri 11/03/16 | 100% | SP-150356 |  | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015¦June2015: Compl:5%->15, WID updated. 7/9/15: TS number added¦7/12/15: 15%->60. FCD -> 03/16, ES in SP-150729¦7/3/16: 60%->85¦1/12/16: 85%->98¦6/3/17: 98%->100 | 33.179 | 66 | 34 |  |  | Fri 12/12/14 | Mon 06/03/17
2403 | 670023 | MCPTT Codecs and media handling | MCPTT | 2 | Rel-13 | S4 | Thu 05/03/15 | Fri 11/03/16 | 100% | SP-150356 |  | Zhiming Li (lizhiming@huawei.com) | Zhiming Li (lizhiming@huawei.com) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015¦June2015: Compl:0%->5, WID updated¦Aug2015: 5%->15¦07/09/15: 15%->40. ES in SP-150663¦7/3/16: 40%->85; 26/6/20: 85%->100 | 26.346, new 26.179 | 67 | 34 |  |  | Thu 05/03/15 | Fri 26/06/20
2404 | 690011 | MCPTT protocol aspects | MCPTT-CT | 2 | Rel-13 | ct | Mon 07/09/15 | Thu 30/06/16 | 96% | CP-150793 |  | Keith Drage, Alcatel-Lucent |  | 7/12/15: WID:CP-150587->CP-150793¦28/1/16: 24.384 added; |  | 69 | 35 |  |  | Mon 07/09/15 | Thu 28/01/16
2405 | 690017 | CT1 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | 7/12/15: WID:CP-150587->CP-150793¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.379, 24.380 24.38, 24.382, 24.383, 24.384, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
2406 | 690096 | Call Control – On Network | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->50¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 50%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.379 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2407 | 690097 | Call Control – Off Network | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.379 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2408 | 690098 | Floor Control – On Network | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->80¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 80%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.38 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2409 | 690099 | Floor Control – Off Network | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->85¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 85%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.38 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2410 | 691000 | Broadcast – Call Control and Floor Control | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->50¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 50%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.379, 24.380 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2411 | 691001 | Group management | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.381 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2412 | 691002 | Identity management | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.382 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2413 | 691003 | Management Object | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->10¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 10%->100. Name changed from "Configuration management"¦7/3/16: WID:CP-150863->CP-160160¦5/12/1 | 24.383 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
2414 | 710033 | Configuration management | MCPTT-CT | 4 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Introduced from CT1 WP update in 03/16¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 24.384 | 71 | 36 |  |  | Mon 07/03/16 | Mon 05/12/16
2415 | 690028 | CT3 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C3 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: 0%->70¦7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150643¦7/3/16: 70%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 29.165 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
2416 | 690018 | CT4 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C4 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150864¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 23.003, 23.008, 29.283 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
2417 | 700049 | CT6 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C6 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150866¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817 | 31.102, 31.103 | 70 | 36 |  |  | Mon 07/09/15 | Mon 05/12/16
2418 | 710034 | (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT | MCPTT-CT | 3 | Rel-13 | C1-IETF | Wed 10/02/16 | Thu 30/06/16 | 25% | CP-160817 |  | Ericsson | christer.holmberg@ericsson.com | 5/12/16: WID:CP-160160->CP-160817 | draft-holmberg-dispatch-mcptt-rp-namespace | 71 | 36 |  |  | Mon 07/03/16 | Mon 05/12/16
2419 | 870072 | (IETF) OAuth 2.0 Token Exchange (draft-ietf-oauth-token-exchange) --> RFC 8693 | MCPTT-CT | 3 | Rel-13 | C1-IETF | Wed 10/02/16 | Thu 30/06/16 | 100% | CP-160817 | [5 empty] | 87 | 44 |  |  | Mon 07/03/16 | Mon 05/12/16
2420 | 690019 | IMS Profile to support MCPTT | MCPTT-Prof | 2 | Rel-13 | C1 | Mon 14/09/15 | Fri 11/03/16 | 100% | CP-150794 |  | Huawei, PATEL Milan | Milan.Patel@huawei.com | 12/15: TR # added¦7/12/15: 0%->60¦7/12/15: WID:CP-150500->CP-150794. FCD -> 03/16, ES in CP-150722¦7/3/16: 60%->100 | 24.98 | 69 | 35 |  |  | Wed 09/09/15 | Mon 07/03/16
2421 | 740070 | UE Conformance Test Aspects - Support for Mission Critical Push To Talk over LTE (MCPTT) | MCPTT-ConTest | 2 | Rel-13 | R5 | Thu 15/12/16 | Fri 15/06/18 | 100% | RP-180132 |  | US Department of Commerce |  | 6/1/17: acronym changed from "MCPTT-UEConTest" ¦21/3/17: Compl:0%->5%¦21/3/17: 36.579-5 added; | 36.579-5 | 74 | 38 |  |  | Tue 20/12/16 | Wed 27/06/18
2422 | 640062 | Deleted: SA2 aspects for MCPTT | MCPTT | 2 | Rel-13 | S2 | Fri 13/03/15 | Fri 13/03/15 | 100% | SP-150356 | - | Randy Bloomfield (randy@its.bldrdoc.gov) | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: transferred to SA6. Was 06/14 to 06/15. 6/15: WID updated | New 23.179 | 64 | 33 | SP-69 |  | Wed 04/06/14 | Thu 18/06/15
2423 | 670031 | Deleted (duplicated): Application Architecture to support MCPTT | MCPTT | 2 | Rel-13 | S6 | Fri 13/03/15 | Fri 13/03/15 | 100% | SP-150356 |  | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated. 7/15: removed since duplicates 640143 and 660054 (only 640143 is kept) |  | 67 | 34 | SP-69 |  | Fri 13/03/15 | Fri 31/07/15
2424 | 660054 | Deleted (duplicated): SA6 aspects for MCPTT | MCPTT | 2 | Rel-13 | S6 | Fri 12/12/14 | Fri 11/12/15 | 100% | SP-150356 |  | David Cypher (david.cypher at nist.gov) | David Cypher (david.cypher at nist.gov) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. 6/15: WID updated. 31 July: deleted since duplicates 640143 and 670031 (only 640143 is kept) |  | 66 | 34 | SP-69 |  | Fri 12/12/14 | Thu 18/06/15
2425 | 670024 | MBMS Extensions and Profiling | MEPRO | 1 | Rel-13 | S4 | Thu 05/03/15 | Fri 11/12/15 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 1/4/15: TS number added¦14/09/15: WID:SP-150099->SP-150439 | 26.346, new 26.852 | 67 | 34 |  |  | Thu 05/03/15 | Mon 14/09/15
2426 | 670090 | TR on Profiling and Extensions of MBMS | MEPRO | 2 | Rel-13 | S4 | Thu 05/03/15 | Fri 11/12/15 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100 | new 26.852 | 67 | 34 |  |  | Wed 08/04/15 | Mon 07/12/15
2427 | 670091 | Specification of MBMS Extensions and Profiling | MEPRO | 2 | Rel-13 | S4 | Thu 05/03/15 | Fri 11/12/15 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100 | 26.346 | 67 | 34 |  |  | Wed 08/04/15 | Mon 07/12/15
2428 | 630015 | Isolated E-UTRAN Operation for Public Safety | IOPS | 1 | Rel-13 | S1 | Fri 07/03/14 | Fri 11/03/16 | 100% | SP-150463 | S1-143304 | General Dynamics | paul.piggin@gd-broadband.com | SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463 | New 22.346 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
2429 | 680047 | Stage 1 fo Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S1 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-150463 | S1-143304 | General Dynamics | paul.piggin@gd-broadband.com | SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463 | New 22.346 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
2430 | 680048 | Stage 2 for Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S2 | Thu 18/06/15 | Wed 30/12/15 | 100% | SP-150463 |  | Phil Young | phil.young@gd-broadband.com | 07/09/15: 0%->100¦14/09/15: WID:SP 150358->SP-150463 | 23.401 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
2431 | 690047 | Security aspects for Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S3 | Wed 16/09/15 | Wed 30/12/15 | 100% | SP-150463 |  | General Dynamics | paul.piggin@gd-ms.uk | 07/09/15: 0%->100¦11/12/15: 0%->100 | 33.401 | 63 | 32 |  |  | Wed 05/02/14 | Fri 11/12/15
2432 | 700037 | CT aspects for IOPS | IOPS-CT | 2 | Rel-13 | C6 | Mon 02/11/15 | Fri 11/03/16 | 100% | CP-150876 |  | Heiko Kruse, Morpho Cards GmbH | heiko.kruse@mrpho.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/12/15
2433 | 700038 | CT6 aspects for IOPS | IOPS-CT | 3 | Rel-13 | C6 | Mon 02/11/15 | Fri 11/03/16 | 100% | CP-150876 |  | Heiko Kruse, Morpho Cards GmbH | heiko.kruse@mrpho.com | ES in CP-150837¦7/3/16: 0%->100 | 31.102 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
2434 | 640042 | Service Requirements Maintenance for Group Communication System Enablers for LTE | SRM_GCSE_LTE | 1 | Rel-13 | S1 | Wed 18/06/14 | Wed 17/09/14 | 100% | SP-140228 | S1-143307 | Nokia Networks | Juergen.Merkel@nsn.com | SP#65 completed. Some Rel-12 service reqs have no Stage 2/3 implementation | 22.468 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/09/14
2435 | 650018 | Enhanced Calling Information Presentation | ECIP | 1 | Rel-13 | S1 | Mon 15/09/14 | Wed 16/12/15 | 100% | SP-140513 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 approved WID & completed. Triggered by Rel-13 TR 22.810. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067. 31/07/15: 100% | 22.182 (CAT), 22.183 (CRS) | 62 | 32 |  |  | Tue 26/11/13 | Fri 31/07/15
2436 | 650019 | Flexible Mobile Service Steering | FMSS | 1 | Rel-13 | S1,S2 | Mon 15/09/14 | Fri 11/03/16 | 100% | SP-140638 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS) | 22.101 | 65 | 33 |  |  | Tue 26/11/13 | Thu 28/08/14
2437 | 650055 | Stage 1 for Flexible Mobile Service Steering | FMSS-ST1 | 2 | Rel-13 | S1 | Mon 15/09/14 | Wed 17/09/14 | 100% | SP-140638 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS). Dec.14: moved from Feature to S1 BB | 22.101 | 65 | 33 |  |  | Tue 26/11/13 | Wed 03/12/14
2438 | 660002 | Flexible Mobile Service Steering TR Phase | FMSS-SA2TR | 2 | Rel-13 | S2 | Fri 12/12/14 | Wed 17/06/15 | 100% | SP-140703 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 3/3: TR number added.Mar15: 15->20%¦June2015: Compl:20%->85¦07/09/15: 85%->100 | 23.718 | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
2439 | 660003 | Flexible Mobile Service Steering - Stage 2 | FMSS-SA2 | 2 | Rel-13 | S2 | Fri 12/12/14 | Wed 17/06/15 | 100% | SP-140703 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 07/09/15: 0%->90¦07/09/15: 90%->100 |  | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
2440 | 690024 | CT3 Aspect of Flexible Mobile Service Steering | FMSS-CT | 2 | Rel-13 | C3 | Wed 09/09/15 | Fri 11/03/16 | 100% | CP-150799 |  | ZTE,Zhou Xiaoyun | zhou.xiaoyun@zte.com.cn | 07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100 | 29.abc, 29.212, 29.213 | 69 | 35 |  |  | Wed 09/09/15 | Mon 07/03/16
2441 | 650020 | GERAN UTRAN Sharing Enhancements | GUSH | 1 | Rel-13 | S1 | Fri 19/09/14 | Fri 12/12/14 | 100% | SP-140637 | SP-140515 | Telefónica | chris.friel@telefonica.com | SP#65 exception in SP-140515. Triggered by TR 22.852 (FS_RSE and FS_GUSH). Completed. | 22.101 | 65 | 33 |  |  | Wed 13/08/14 | Wed 03/12/14
2442 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1,C1 | Wed 18/06/14 | Fri 11/03/16 | 100% | SP-140234 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. Triggered by Rel-13 Study TR 22.806 | 22.011 | 64 | 33 |  |  | Tue 27/05/14 | Fri 29/08/14
2443 | 660013 | Stage 1 for Application specific Congestion control for Data Communication | ACDC-ST1 | 2 | Rel-13 | S1 | Wed 18/06/14 | Wed 17/09/14 | 100% | SP-140234 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | Results from MCC Split of the SA1 feature into F+BB for stage 1 | 22.011 | 64 | 33 |  |  | Tue 27/05/14 | Fri 29/08/14
2444 | 660039 | Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 2 | Rel-13 | C1 | Thu 04/12/14 | Fri 11/03/16 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282 | 24.105, 24.301, 24.008, 27.007, 31.102 | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
2445 | 660139 | CT1 part of Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 3 | Rel-13 | C1 | Thu 04/12/14 | Wed 16/12/15 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66¦June2015: Compl:0%->10. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282¦07/09/15: 5%->70¦7/12/15: 70%->100 | 24.105, 24.301, 24.008, 27.007, 23.122 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/12/15
2446 | 660239 | CT6 part of Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 3 | Rel-13 | C6 | Thu 04/12/14 | Fri 11/03/16 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282. 12/15: FCD -> 03/16, ES in CP-150838¦7/3/16: 0%->100 | 31.102 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/03/16
2447 | 670059 | RAN aspects of Application specific Congestion control for Data Communication | ACDC-RAN | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150512 |  | LG Electronics |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2448 | 670159 | Core part: RAN aspects of Application specific Congestion control for Data Communication | ACDC-RAN-Core | 3 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150662 | RP-151275 | LG Electronics |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150512->RP-150662 03/07/15: Stat Rep: ->RP-150661 29/09/15: Compl:25%->70% 29/09/15: Stat Rep: RP-150661->RP-151275¦1/1/16: Compl:70%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2449 | 570029 | User Plane Congestion management | UPCON | 1 | Rel-13 | S1,S2,C3,C4 | Wed 12/09/12 | Wed 18/03/15 | 100% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON) | Stage 1/2/3 | 57 | 29 |  |  | Mon 06/08/12 | Tue 16/09/14
2450 | 570129 | Stage 1 for User Plane Congestion management | UPCON-ST1 | 2 | Rel-13 | S1 | Wed 12/09/12 | Wed 06/03/13 | 100% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101. 3/3/15: start date corrected (was Mar 12) | 22.101 | 57 | 29 |  |  | Mon 06/08/12 | Tue 03/03/15
2451 | 580057 | TR on Stage 2 for User Plane Congestion management | UPCON-SA2TR | 2 | Rel-13 | S2 | Wed 12/12/12 | Wed 18/03/15 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. TR 23.705v100 for Information. Dec.14: 87->98%. Mar15: 100% | new 23.705 | 58 | 30 |  |  | Tue 13/11/12 | Thu 05/03/15
2452 | 580058 | Deleted - Stage 2 for User Plane Congestion management | UPCON-SA2Del | 2 | Rel-13 | S2 | Wed 19/12/12 | Wed 11/12/13 | 100% | SP-140631 | - | NEC | andreas.maeder@neclab.eu | SP#62 stopped at 0% completion | TBD | 58 | 30 | SP-62 | PCG-32 | Tue 13/11/12 | Tue 16/09/14
2453 | 630019 | BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON | 2 | Rel-13 | S2 | Fri 07/03/14 | Fri 13/03/15 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control | - | 63 | 32 |  |  | Tue 04/03/14 | Tue 16/09/14
2454 | 630119 | Stage 2 for RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON-SA2 | 3 | Rel-13 | S2 | Fri 07/03/14 | Fri 12/12/14 | 100% | SP-140434 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>S2-142850 (added impacted specs). Dec.14: 70->100% only if RAN agrees to standardize the FPI | 23.060, 23.203, 23.401 | 63 | 32 |  |  | Tue 04/03/14 | Wed 03/12/14
2455 | 650007 | CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 3 | Rel-13 | C3 | Tue 18/03/14 | Fri 13/03/15 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Stage 3¦WID: CP-140734->CP-140929. June 2015: WID: CP-140929-> CP-150365. | Stage 3 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
2456 | 650107 | CT3 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C3 | Tue 18/03/14 | Fri 13/03/15 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Dec.14: 0->60¦WID: CP-140734->CP-140929. Mar.15: 60->95%¦June2015: Compl:95%->100. WID: CP-140929-> CP-150365. | 29.201, 29.212, 29.213, 29.214, 29.215, 29.219, New 29.217 (PCC over Np) | 65 | 33 |  |  | Tue 29/07/14 | Mon 15/06/15
2457 | 650207 | CT4 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C4 | Tue 18/03/14 | Fri 13/03/15 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Dec.14: 0->20¦WID: CP-140734->CP-140929. Mar. 15: 50%¦June2015: Compl:50%->90. WID: CP-140929-> CP-150365.¦07/09/15: 90%->100 | 23.003, 29.303, New 29.405 (UPCON over Nq) | 65 | 33 |  |  | Tue 29/07/14 | Mon 07/09/15
2458 | 630020 | Deleted - BB2: Application and Content Prioritization | UPCON-CONDEL | 2 | Rel-13 | S2 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Content specific UP prioritization (Video), Application specific UP prioritization | TBD | 63 | 32 | SP-65 | PCG-33 | Tue 04/03/14 | Tue 16/09/14
2459 | 630021 | Deleted - BB3: Uplink traffic and attended/unattended traffic | UPCON-TRAFDEL | 2 | Rel-13 | S2 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Uplink Congestion Management, Un/Attended UE Information | TBD | 63 | 32 | SP-65 | PCG-33 | Tue 04/03/14 | Tue 16/09/14
2460 | 650028 | Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 1 | Rel-13 |  | Tue 09/09/14 | Wed 15/03/17 | 95% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Can be seen as an "enhancement" of Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042. Mar. 15: 20% | - | 65 | 33 |  |  | Fri 05/09/14 | Thu 05/03/15
2461 | 650128 | TR on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | Tue 09/09/14 | Wed 16/09/15 | 100% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100 | New 26.9xy | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
2462 | 650228 | Specification on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | Tue 09/09/14 | Wed 16/12/15 | 100% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦07/09/15: 30%->60¦7/12/15: 60%->100 | New 26.1xy | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
2463 | 710035 | (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | Thu 10/12/15 | Wed 15/03/17 | 90% |  |  | Intel | ozgur.oyman@intel.com | 23/4/20: 60%->90. was (IETF) CLUE Protocol (draft-ietf-clue-protocol); 9/4/21: RFC 8847 added; | 26.22; RFC 8847 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2464 | 710036 | (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | Thu 10/12/15 | Wed 15/03/17 | 90% |  |  | Intel | ozgur.oyman@intel.com | 23/4/20: 60%->90; 9/4/21: RFC 8849 added; | 26.22; RFC 8849 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2465 | 710037 | Deleted - (IETF) DTLS Encapsulation of SCTP Packets (draft-ietf-tsvwg-sctp-dtls-encaps) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | Thu 10/12/15 | Wed 15/03/17 | 100% |  |  | Intel | ozgur.oyman@intel.com | 22/3/18: 95%->100. 07/06/18: deleted as per SP-180260; 9/4/21: RFC 8261 added; | 26.22; RFC 8261 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2466 | 710038 | (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | Thu 10/12/15 | Wed 15/03/17 | 90% |  |  | Ericsson | tomas.frankkila@ericsson.com | 23/4/20: 60%->90; 9/4/21: RFC 8853 added; | 26.114, 26.223; RFC 8853 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2467 | 600045 | RAN Sharing Enhancements | RSE | 1 | Rel-13 | S1,R3 | Wed 19/06/13 | Tue 15/12/15 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | - | 60 | 31 |  |  | Mon 03/06/13 | Tue 26/11/13
2468 | 600145 | Stage 1 for RAN Sharing Enhancements | RSE-SA1 | 2 | Rel-13 | S1 | Wed 19/06/13 | Wed 11/12/13 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | SP#62 completed | 22.101 | 60 | 31 |  |  | Mon 03/06/13 | Tue 26/11/13
2469 | 650021 | RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE | 2 | Rel-13 | R3 | Fri 12/09/14 | Tue 15/12/15 | 100% | RP-141671 | - | NEC | Siva.Vakeesar@emea.nec.com | Triggered by TR 36.856 Study on RAN aspects of RAN Sharing Enhancements for LTE (FS_RSE-RAN_LTE) & SA1 22.101 Stage 1 | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
2470 | 650121 | Core part: RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE-Core | 3 | Rel-13 | R3 | Fri 12/09/14 | Tue 15/12/15 | 100% | RP-151827 | RP-151295 | NEC | Siva.Vakeesar@emea.nec.com | ¦CD:Mon 15/06/15->Tue 15/09/15¦Stat Rep: -->RP-141891 1st Apr 15: Compl:15%->20% 1st Apr 15: Stat Rep: RP-141891->RP-150289 03/07/15: Compl:20%->75% 03/07/15: Stat Rep: RP-150289->RP-150875 29/09/15: Compl:75%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/1 | 36.300, 36.413, 36.423 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2471 | 630014 | Enhancements to WEBRTC interoperability | eWebRTCi | 1 | Rel-13 | S1,S2,S3 | Fri 07/03/14 | Thu 16/06/16 | 99% | SP-140630 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part, SA1 change). Add enhanced interoperability support for WebRTC to Rel-12 Web Real Time Communication (WebRTC) Access to IMS. | Stage 1/2 | 63 | 32 |  |  | Wed 05/02/14 | Tue 16/09/14
2472 | 630114 | Stage 1 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S1 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140630 | S1-143303 | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 completed. Updated WID SP-140286=>SP-140630 | 22.228 | 63 | 32 |  |  | Wed 05/02/14 | Tue 16/09/14
2473 | 640138 | TR on Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | Thu 19/06/14 | Wed 18/03/15 | 100% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 9->55%¦June2015: Compl:55%->85¦07/09/15: 85%->100 | New 23.706 | 64 | 33 |  |  | Thu 12/06/14 | Mon 07/09/15
2474 | 640038 | Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 17/06/15 | 100% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part)¦June2015: Compl:0%->85¦07/09/15: 85%->100 | 23.228 | 64 | 33 |  |  | Thu 12/06/14 | Mon 07/09/15
2475 | 650122 | TR on Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | Wed 17/09/14 | Wed 30/09/15 | 100% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%, TR number added. 3/3/15: 30%.¦June2015: Compl:30%->75¦11/12/15: 54%->100¦11/12/15: 100%->100 | New 33.872 | 65 | 33 |  |  | Thu 04/09/14 | Fri 11/12/15
2476 | 650022 | Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | Wed 17/09/14 | Wed 30/09/15 | 100% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%¦11/12/15: 15%->100 | 33.203, 33.328 | 65 | 33 |  |  | Thu 04/09/14 | Fri 11/12/15
2477 | 690037 | (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third Party Authorization (draft-ietf-tram-turn-third-party-authz) | eWebRTCi | 2 | Rel-13 | S3-IET | Wed 17/09/14 | Wed 12/08/15 | 100% | SP-150474 | - | Alcatel-Lucent |  | TS 33.203 CR0235 draft-ietf-tram-turn-third-party-authz¦7/3/16: 10%->100; 9/4/21: RFC 7635 added; | 33.203, RRC 7635 (was draft-ietf-tram-turn-third-party-authz); RFC 7635 | 69 | 35 |  |  | Thu 04/09/14 | Fri 09/04/21
2478 | 690012 | Stage 3 for Enhancements to WebRTC interoperability | eWebRTCi-CT | 2 | Rel-13 | ct | Mon 07/09/15 | Thu 16/06/16 | 97% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2479 | 690015 | CT1 aspects 3 for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C1 | Mon 07/09/15 | Fri 18/12/15 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: 0%->100¦7/12/15: WID:CP-150498->CP-150790->CP-150767 | 24.371, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2480 | 690029 | CT3 aspects for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C3 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150644¦7/3/16: 0%->100 | 29.214 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2481 | 690016 | CT4 aspects for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C4 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150623¦7/3/16: 0%->100 | 29.228, 23.334, 29.334, 23.008 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2482 | 710039 | (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg) | eWebRTCi-CT | 3 | Rel-13 | C1-IETF,SA4-IETF | Tue 08/12/15 | Fri 11/03/16 | 90% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates; 23/4/20: 75%->90; 9/4/21: RFC 8864 added; | 24.371, 24.229; RFC 8864 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2483 | 710040 | (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel) | eWebRTCi-CT | 3 | Rel-13 | C1-IETF | Tue 08/12/15 | Fri 11/03/16 | 75% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates | 24.371, 24.229, 26.223 | 71 | 36 |  |  | Mon 07/03/16 | Mon 07/03/16
2484 | 710041 | (IETF) A Language for Rules Describing JSON Content (draft-newton-json-content-rules) | eWebRTCi-CT | 3 | Rel-13 | C3-IETF | Tue 08/12/15 | Fri 11/03/16 | 100% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates. This individual draft will not further progress in IETF but is kept as reference in version -09; 23/4/20: 25%->100 | 24.371, 24.229, 26.223 | 71 | 36 |  |  | Mon 07/03/16 | Thu 23/04/20
2485 | 870074 | Deleted - (IETF) Oauth 2.0 Proof-of-Possession (PoP) Security Architecture (draft-ietf-oauth-pop-architecture) | eWebRTCi-CT | 3 | Rel-13 | S3-IETF | Tue 08/12/15 | Thu 16/06/16 | 100% |  |  |  |  | 9/4/21: 25%->100 |  | 87 | 44 |  |  | Mon 07/03/16 | Fri 09/04/21
2486 | 870076 | (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third-Party Authorization (draft-ietf-tram-turn-third-party-authz) --> RFC 7635 | eWebRTCi-CT | 3 | Rel-13 | S3-IETF | Tue 08/12/15 | Thu 16/06/16 | 100% | [6 empty] | 87 | 44 |  |  | Mon 07/03/16 | Thu 23/04/20
2487 | 630016 | Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 1 | Rel-13 | S2 | Fri 07/03/14 | Thu 12/05/16 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios | Stage 2 | 63 | 32 |  |  | Wed 05/02/14 | Tue 04/03/14
2488 | 630116 | TR on Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord-SA2TR | 2 | Rel-13 | S2 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | SP#65 completed. TR 23.704v200 for Approval | New 23.704 | 63 | 32 |  |  | Wed 05/02/14 | Mon 04/08/14
2489 | 630216 | Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord-SA2 | 2 | Rel-13 | S2 | Wed 12/03/14 | Fri 12/12/14 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Dec.14: 0->100% | 23.216, 23.251, 23.272 | 63 | 32 |  |  | Wed 05/02/14 | Wed 03/12/14
2490 | 650100 | RAN aspects for improvements to CS/PS coordination in GERAN Shared Networks | CSPS_Coord_GERAN | 2 | Rel-13 | G2 | Wed 11/03/15 | Thu 12/05/16 | 100% | GP-150225 |  | Nicklas Johansson, Ericsson LM | Nicklas.Johansson@Ericsson.com | June2015: Compl:0%->35¦07/09/15: 35%->50, FCD:08/15->11/15¦7/12/15: 50%->95, FCD: 12/15->02/16. 02/03/16: FCD: 02/16->05/16¦13/6/16: 95%->100 | 48.008, 48.018 | 65 |  |  |  | Thu 07/05/15 | Mon 13/06/16
2491 | 640040 | Enhancements to Proximity-based Services | eProSe | 1 | Rel-13 | S1,S2,S3 | Mon 18/03/13 | Fri 11/03/16 | 100% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | - | Stage 1/2 | 64 | 33 |  |  | Tue 27/05/14 | Fri 05/09/14
2492 | 640140 | Stage 1 for Enhancements to Proximity-based Services | eProSe-SA1 | 2 | Rel-13 | S1 | Thu 19/06/14 | Wed 17/09/14 | 100% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced. | 22.115, 22.278 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/09/14
2493 | 640041 | Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA2 | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-150028 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:0%->30. FCD: June->Sept. 07/09/15: 24->70%¦07/09/15: 70%->90¦7/12/15: 90%->100 | 23.303, TBD | 64 | 33 |  |  | Tue 17/06/14 | Mon 07/12/15
2494 | 640141 | TR on Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA2TR | 2 | Rel-13 | S2 | Wed 18/06/14 | Fri 13/03/15 | 100% | SP-150028 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:60%->90¦07/09/15: 90%->95¦07/09/15: 95%->100 | New 23.713 | 64 | 33 |  |  | Tue 17/06/14 | Mon 07/09/15
2495 | 650023 | Security for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA3 | 2 | Rel-13 | S3 | Fri 19/09/14 | Fri 11/03/16 | 100% | SP-150028 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA3t->eProSe-Ext-SA3. Mar15: WID: SP-140573 ->SP-150028¦7/12/15: 0%->75¦10/12/15: FCD ->03/16, ES in SP-150714¦7/3/16: 75%->100 | 33.303 | 65 | 33 |  |  | Thu 04/09/14 | Mon 07/03/16
2496 | 680006 | CT aspects of enhancements to Proximity-based | eProSe-Ext-CT | 2 | Rel-13 | C1 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  | 23.122, 24.301, 24.333, 24.334 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
2497 | 680007 | CT1 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C1 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->40¦7/12/15: 40%->90. FCD -> 03/16, ES in CP-150724¦7/3/16: 90%->100 | 29.343 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2498 | 680008 | CT3 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->60¦8/3/16: 60%->100 | 23.003, 23.008, 29.272, 29.344, 29.345 | 68 | 35 |  |  | Mon 15/06/15 | Tue 08/03/16
2499 | 680009 | CT4 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->10¦7/12/15: 10%->80. FCD->03/16. ES in CP-150616¦7/3/16: 80%->100 | 31.102, 31.111 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2500 | 680010 | CT6 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C6 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 7/12/15: FCD -> 03/16, ES in CP-150839. FCD->03/16. ES in CP-150616¦7/3/16: 0%->95¦8/3/16: 95%->100 | 31.102, 31.111 | 68 | 35 |  |  | Mon 15/06/15 | Tue 08/03/16
2501 | 590035 | Study on Security for Proximity-based Services | FS_ProSe_Sec | 2 | Rel-13 | S3 | Mon 18/03/13 | Wed 17/06/15 | 100% | SP-140629 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information. 4/3/15: 95%->70% (more topics to be included)¦June2015: Compl:70%->75¦7/12/15: 75%->95¦7/3/1 | 33.833 | 59 | 30 |  |  | Wed 20/02/13 | Thu 01/12/16
2502 | 729999 | Note: Charging Aspects done in Rel-14 under CH14-Prose (UID 720049) | eProSe | 2 | Rel-13 | S5 | Wed 17/06/15 | Wed 17/06/15 | 100% | [10 empty] | Mon 13/06/16 | Thu 01/12/16
2503 | 640045 | voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 1 | Rel-13 | S1,S2,C4,C1,C3 | Mon 16/06/14 | Fri 12/12/14 | 100% | SP-140394 | - | Alcatel-Lucent | (betsy.covell@alcatel-lucent.com) | - | Stage 1/2 | 64 | 33 |  |  | Thu 29/05/14 | Wed 11/06/14
2504 | 640145 | Stage 1 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRA-N_PPD-SA1 | 2 | Rel-13 | S1 | Mon 16/06/14 | Wed 18/06/14 | 100% | SP-140394 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 approved WID & completed | 22.228, 22.278 | 64 | 33 |  |  | Thu 29/05/14 | Wed 11/06/14
2505 | 640245 | Stage 2 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-SA2 | 2 | Rel-13 | S2 | Wed 18/06/14 | Fri 12/12/14 | 100% | SP-140394 | - | Alcatel-Lucent | laurent.thiebaut@alcatel-lucent.com | Architectural enhancements allowing a differentiated paging policy for IMS voice calls over E-UTRAN. Dec.14: 25->100% | 23.228, 23.401 | 64 | 33 |  |  | Wed 11/06/14 | Wed 03/12/14
2506 | 650003 | CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 2 | Rel-13 | C4,C1,C3 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Stage 3 | Stage 3 | 65 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
2507 | 650103 | CT4 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C4 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Mar.15: 0->100% | 29.274, 29.281 | 65 | 33 |  |  | Tue 29/07/14 | Wed 04/03/15
2508 | 650203 | CT1 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C1 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Dec.14: 0->50%¦07/09/15: 50%->50¦7/12/15: 50%->100 | 24.229 | 65 | 33 |  |  | Tue 29/07/14 | Mon 07/12/15
2509 | 650303 | CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C3 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Mar.15: 0->100% | 29.061 | 65 | 33 |  |  | Tue 29/07/14 | Wed 04/03/15
2510 | 640047 | IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 1 | Rel-13 | S2 | Wed 18/06/14 | Wed 15/06/16 | 100% | SP-150250 | - | Tricci So, ZTE | tso@zte.com.cn | 06/15: WID: SP-140279->SP-150250 | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
2511 | 640147 | TR for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-SA2TR | 2 | Rel-13 | S2 | Wed 18/06/14 | Fri 13/03/15 | 100% | SP-140279 | - | Tricci So, ZTE | tso@zte.com.cn | Revived the Rel-12 DRAFT TR 23.861 stopped at SP#59 (at 40% completion). Dec.14: 20->60%¦June2015: Compl:60%->90, WID: SP-140279->SP-150250 | New 23.861 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
2512 | 640247 | Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-SA2 | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-150250 |  | Tricci So, ZTE | tso@zte.com.cn | June2015: Compl:0%->65, WID: SP-140279->SP-150250¦07/09/15: 52%->100 | 23.402, New 23.203 | 64 |  |  |  | Fri 30/05/14 | Mon 07/09/15
2513 | 690043 | Charging Aspects of IP Flow Mobility support for S2a and S2b Interfaces (NBIFOM) | NBIFOM-CH | 2 | Rel-13 | S5 | Wed 16/09/15 | Wed 15/06/16 | 100% | SP-150406 |  | GUO Wenjie, ZTE | guo.wenjie1@zte.com.cn | 7/12/15: 0%->50. ES in SP-150710 (wrong UID mentioned in the ES)¦7/3/16: 50%->85%, FCD:03/16->06/16¦13/6/16: 85%->100 | 32.251, 32.298, 32.299 | 69 | 35 |  |  | Fri 30/05/14 | Mon 13/06/16
2514 | 680019 | CT aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 2 | Rel-13 | C1 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation | zhou.xingyue@zte.com.cn | 14/09/15: WID:CP-150285->CP-150497¦7/12/15: WID:CP-150497->CP-150791->874 | 24.161 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2515 | 680020 | CT1 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C1 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation. ES in 641 | zhou.xingyue@zte.com.cn | 07/09/15: 0%->25¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 25%->75¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 75%->100 | 24.301, 24.302, 24.244, 24.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2516 | 680021 | CT3 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150874 |  | 680001Xingyue(Joy) Zhou, ZTECorporation. ES in 641 | zhou.xingyue@zte.com.cn | 07/09/15: 0%->40¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 40%->95¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 95%->100 | 29.212, 29.213, 29.214, 29.215 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2517 | 680022 | CT4 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation | zhou.xingyue@zte.com.cn | 07/09/15: 0%->20¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 20%->100¦7/12/15: WID:CP-150497->CP-150791->874 | 29.274, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2518 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | Fri 14/03/14 | Fri 13/03/15 | 100% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Wed 11/06/14
2519 | 640153 | Stage 2 for Double Resource Reuse for Multiple Media Sessions | DRuMS-SA2 | 2 | Rel-13 | S2 | Fri 14/03/14 | Fri 13/03/15 | 100% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | Dec.14: 49->95%. Mar15: 100% | 23.203, 23.228 | 64 | 33 |  |  | Fri 30/05/14 | Thu 05/03/15
2520 | 660019 | CT aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 2 | Rel-13 | C3 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140926 |  | Ericsson |  |  | 24.229, 24.615, 24.610, 24.605, 29.212, 29.213, 29.214, 29.215 | 66 | 34 |  |  | Thu 04/12/14 | Thu 04/12/14
2521 | 660047 | CT1 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 3 | Rel-13 | C1 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140926 |  | Ericsson |  | 5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100 | 24.229, 24.615, 24.610, 24.605 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/09/15
2522 | 660048 | CT3 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 3 | Rel-13 | C3 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140926 |  | Ericsson | Jan Holm | Mar.15: 65->95%¦June2015: Compl:95%->100 | 29.212, 29.213, 29.214, 29.215 | 66 | 34 |  |  | Tue 09/12/14 | Mon 15/06/15
2523 | 640056 | Lawful Interception in the 3GPP Rel-13 | LI13 | 1 | Rel-13 | S3 | Wed 18/06/14 | Thu 15/12/16 | 100% | SP-160043 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | SP#65 updated WID SP-140400=>SP-140578. 2/4/15: WID SP-140815->SP-150111¦June2015: Compl:0%->10. WID: SP-150111->SP-150290¦14/09/15: WID:SP-150290->SP-150460¦7/12/15: 10%->15¦7/3/16: 13%->20¦7/3/16: WID:SP-150460->SP-160043¦19/9/16: 20%->60. FCD | 33.106, 33.107, 33.108 | 64 | 33 |  |  | Wed 11/06/14 | Thu 01/12/16
2524 | 640055 | STOPPED - Study on Lawful Interception Service Evolution | FS_LISE | 1 | Rel-13 | S3 | Mon 23/06/14 | Wed 09/12/15 | 100% | SP-140303 | - | Alcatel-Lucent | terry.jacobson@alcatel-lucent.com | Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points. 3/3/15: 0->5%¦7/12/15: 5%->10. Stoppped at 10% in March 2017.¦6/3/17: 10%->100 | 33.826 | 64 | 33 |  |  | Wed 11/06/14 | Mon 06/03/17
2525 | 640058 | Video enhancements by Region-Of-Interest information signalling | ROI | 1 | Rel-13 | S4 | Wed 18/06/14 | Wed 16/12/15 | 100% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Dec.14: 5->20%. Mar.15: 40%¦07/09/15: 43%->100 | 26.114 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/09/15
2526 | 680031 | SA4 aspects of Video enhancements by Region-Of-Interest information signalling | ROI | 2 | Rel-13 | S4 | Wed 18/06/14 | Wed 16/09/15 | 100% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Created by MCC as the structure of the Feature get expanded to include CT aspects¦June2015: Compl:40%->90, FCD: 06/15->09/15¦Aug2015: Compl:90%->95 | 26.114 | 64 | 33 |  |  | Mon 15/06/15 | Wed 12/08/15
2527 | 680017 | CT Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 2 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 14/09/15: WID:CP-150241->CP-150425 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
2528 | 680032 | CT1 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C1 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->50¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 50%->100 | 24.229 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2529 | 680033 | CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->10¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 10%->100 | 29.162 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2530 | 680034 | CT4 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->5¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 5%->100 | 23.334, 29.334, 29.238 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2531 | 650026 | TV video profile | TVProf | 1 | Rel-13 | S4 | Tue 09/09/14 | Fri 11/03/16 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Mar. 15: 5->15% | - | 65 | 33 |  |  | Fri 05/09/14 | Thu 05/03/15
2532 | 650126 | TR on TV video profile | TVProf-SA4TR | 2 | Rel-13 | S4 | Tue 09/09/14 | Fri 11/03/16 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16¦7/3/16: 85%->100 | New 26.9xy. ES in SP-150650 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
2533 | 650226 | Specification on TV video profile | TVProf-SA4 | 2 | Rel-13 | S4 | Tue 09/09/14 | Fri 11/03/16 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16. ES in SP-150650¦7/3/16: 85%->100 | 26.234, 26.244, 26.346, 26.247, New 26.xyz. ES in SP-150650 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
2534 | 650027 | Enhanced LTE UE Delay test methods and requirements | E_LTE_UED | 1 | Rel-13 | S4 | Tue 09/09/14 | Wed 15/06/16 | 100% | SP-140482 | - | Orange | stephane.ragot@orange.com | Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->50¦7/12/15: 50%->80, FCD: 12/15->03/16. ES in SP-150652¦7/3/16: FCD: 03/16->06/16¦11/6/16: 80%->100 | 26.131, 26.132 | 65 | 33 |  |  | Fri 05/09/14 | Sat 11/06/16
2535 | 650029 | HTML5 Presentation Layer | HTML5 | 1 | Rel-13 | S4 | Tue 09/09/14 | Wed 16/12/15 | 100% | SP-140484 | - | Samsung | Imed Bouazizi (i.bouazizi@samsung.com) | Triggered by Rel-12 TR 26.907 (Study of HTML5 and 3GPP User Services). Dec.14: 0->5%. Mar. 15: 10%¦June2015: Compl:10%->20¦Aug2015: 20%->40¦07/09/15: 40%->70¦7/12/15: 70%->100 | 26.140, 26.234, 26.247, 26.346, New 26.xyz | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
2536 | 650030 | Support of EVS in 3G Circuit-Switched networks | EVSoCS | 1 | Rel-13 | S4,C4,C1,C3,R1,R2,R3 | Tue 09/09/14 | Fri 11/03/16 | 100% | SP-140485 | - | Qualcomm | Imre Varga (ivarga@qti.qualcomm.com) | Provide CS support of EVS to enhance voice quality in CS services over UTRAN (3G WCDMA). Dec.14: 0->5%¦28/1/16: 26.454 added¦28/1/16: 26.453 added; | 26.103, 28.062, New 26.454; New 26.453 | 65 | 33 |  |  | Fri 05/09/14 | Thu 28/01/16
2537 | 670016 | SA4 aspects of EVS in 3G Circuit-Switched networks | EVSoCS-S4 | 2 | Rel-13 | S4 | Tue 09/09/14 | Fri 11/03/16 | 100% | SP-140485 | - | Qualcomm | Imre Varga (ivarga@qti.qualcomm.com) | Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%¦Aug2015: 10%->20¦07/09/15: 20%->40¦7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655¦28/1/16: 26.454 added¦28/1/16: 26.453 added; | 26.103, 28.062, New 26.454; New 26.453 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
2538 | 670002 | CT aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 2 | Rel-13 | C4,C1,C3 | Wed 04/03/15 | Fri 11/03/16 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com |  |  | 67 | 34 |  |  | Wed 04/03/15 | Mon 09/03/15
2539 | 670017 | CT1 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C1 | Wed 04/03/15 | Fri 11/12/15 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->90¦7/12/15: 90%->100 | 24.008 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
2540 | 670018 | CT3 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C3 | Wed 04/03/15 | Fri 11/03/16 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | June2015: Compl:0%->10¦07/09/15: 10%->15¦7/12/15: 15%->90. FCD -> 03/16, ES in CP-150638¦7/3/16: 90%->100 | 29.163, 29.414, 29.415 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
2541 | 670019 | CT4 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C4 | Wed 04/03/15 | Fri 11/03/16 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | June2015: Compl:0%->95. FCD -> 03/16, ES in CP-150618¦7/3/16: 95%->100 | 23.153, 23.334, 29.002, 29.231, 29.232, 29.332, 29.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
2542 | 660073 | Support of EVS over UTRAN CS | EVSoCS_UTRAN | 2 | Rel-13 | R2,R1,R3 | Tue 16/06/15 | Tue 15/12/15 | 100% | RP-142282 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
2543 | 660173 | Core part: Support of EVS over UTRAN CS | EVSoCS_UTRAN-Core | 3 | Rel-13 | R2,R1,R3 | Tue 16/06/15 | Tue 15/12/15 | 100% | RP-142282 | RP-151282 | Francesco Pica - Qualcomm Incorporated | fpica@qti.qualcomm.com | Rapporteur details and involved WGs updated 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150128. 5/5/15: 0->10% 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150128->RP-150759 29/09/15: Compl:25%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2544 | 650031 | Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP) | eDASH | 1 | Rel-13 | S4 | Tue 09/09/14 | Wed 16/12/15 | 100% | SP-150448 | - | Qualcomm, Huawei | Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com) | Triggered by Rel-12 Dec.14: 0->10%. Mar. 15: 15%¦June2015: Compl:15%->25. WID updated¦Aug2015: 25%->30¦07/09/15: 30%->60¦14/09/15: WID:SP-150211->SP-150448¦7/12/15: 60%->100 | 26.233, 26.234, 26.244, 26.247, 26.938, 26.346, 26.946 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
2545 | 650032 | QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 1 | Rel-13 | S4,C3,C1,C4 | Wed 06/03/13 | Fri 11/03/16 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | - | 59 | 30 |  |  | Wed 20/02/13 | Sat 20/09/14
2546 | 620068 | TR on improved end-to-end QoS handling for MTSI | QOSE2EMTSI | 2 | Rel-13 | S4 | Wed 11/12/13 | Fri 11/03/16 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel12 incl. new TR to Rel-13). Completion 03/15=>06/15. Mar15: 26.924 for info. 8/4/15: 50%¦Aug2015: 50%->60¦7/12/15: 75%->90, FCD: 06/15->03/16¦7/3/16: 90%->100 | new 26.924 | 62 | 32 |  |  | Fri 29/11/13 | Mon 07/03/16
2547 | 650132 | SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 2 | Rel-13 | S4 | Wed 06/03/13 | Fri 11/03/16 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65: WID SP-130670=>SP-140601 (moved from Rel12 incl. new TR to Rel-13). FCD 03/15=>06/15. St1 in TS 22.173. 12/14: 70->40%, CD: 06/15->09/15. 03/15: 50%. June 15: FCD: 09/15->12/15¦08/15: 60%¦09/15: 75%¦7/12. ES in SP-150658¦7/3/16: 90%->100 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Mon 07/03/16
2548 | 660043 | CT Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 2 | Rel-13 | C3,C1,C4 | Wed 05/11/14 | Fri 11/03/16 | 100% | CP-140925 |  | Ericsson |  |  |  | 66 | 34 |  |  | Tue 09/12/14 | Tue 09/12/14
2549 | 660044 | CT3 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C3 | Wed 05/11/14 | Fri 11/03/16 | 100% | CP-140925 |  | Ericsson |  | 7/12/15: 0%->70. FCD -> 03/16, ES in CP-150636¦7/3/16: 70%->100 | 29.162, 29.163, 29.213, 29.214 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
2550 | 660045 | CT1 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C1 | Wed 05/11/14 | Fri 11/03/16 | 100% | CP-140925 |  | Ericsson |  | FCD -> 03/16, ES in CP-150726¦7/3/16: 0%->100 | 24.229 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
2551 | 660046 | CT4 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C4 | Wed 05/11/14 | Fri 11/03/16 | 100% | CP-140925 |  | Ericsson |  | FCD -> 03/16, ES in CP-150620¦7/3/16: 0%->100 | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
2552 | 660050 | MTSI Extension on Multi-stream Multiparty | MMCMH | 1 | Rel-13 |  | Fri 12/12/14 | Mon 07/03/16 | 98% | SP-150660 |  | Tomas Frankkila, Ericsson LM | tomas.frankkila@ericsson.com | Mar. 15: 0->10%. WID: SP-140738->SP-150097¦June2015: Compl:10%->30¦Aug2015: 30%->50, FCD: sep->Dec 2015¦07/09/15: 50%->60¦7/12/15: 60%->100¦10/12/15: WID:SP-150097->SP-150660. Might be moved to Rel-14 (see note in UID710002) | 26.114, New 26.980 | 66 | 34 |  |  | Fri 12/12/14 | Thu 10/12/15
2553 | 710042 | Codec aspects for MMCMH | MMCMH | 2 | Rel-13 | S4 | Fri 12/12/14 | Thu 17/12/15 | 100% | SP-150660 |  | Tomas Frankkila, Ericsson LM | tomas.frankkila@ericsson.com | Introduced by MCC to dissociate S4 from IeTF aspects | 26.114, New 26.980 | 66 | 34 |  |  | Fri 12/12/14 | Thu 10/12/15
2554 | 710043 | (IETF) RTP Stream Pause and Resume (RFC 7728) | MMCMH | 2 | Rel-13 | S4-IETF | Mon 07/12/15 | Mon 07/03/16 | 100% | SP-150660 |  | Ericsson | tomas.frankkila@ericsson.com | 02/2016: published as RFC 7728 | (IETF) RTP Stream Pause and Resume (RFC 7728) | 71 | 36 |  |  | Fri 12/12/14 | Mon 07/03/16
2555 | 720062 | (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast) | MMCMH | 2 | Rel-13 | S4-IETF | Mon 07/12/15 | Mon 07/03/16 | 90% |  |  |  |  | Was (IETF) (draft-ietf-mmusic-sdp-simulcast); 23/4/20: 0%->90; 9/4/21: RFC 8853 added; | RFC 8853 | 72 | 37 |  |  | Mon 13/06/16 | Fri 09/04/21
2556 | 660051 | Video Telephony Robustness Improvements Extensions | VTRI_EXT | 1 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/09/15 | 100% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | New TR added. 3/3/15: "extensions" added in the title. Mar. 15: 0->10% | 26.922 (new), 26.114 | 66 | 34 |  |  | Fri 12/12/14 | Thu 05/03/15
2557 | 660151 | TR on Video Telephony Robustness Improvements | VTRI_EXT | 2 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/09/15 | 100% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 3/3/15: created to distinguish TR and TS tasks¦June2015: Compl:10%->40¦Aug2015: 40%->95¦07/09/15: 95%->100 | 26.922 (new), 26.114 | 66 | 34 |  |  | Tue 03/03/15 | Mon 07/09/15
2558 | 660251 | Specification on Video Telephony Robustness Improvements | VTRI_EXT | 2 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/09/15 | 100% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 3/3/15: created to distinguish TR and TS tasks¦June2015: Compl:10%->40¦Aug2015: 40%->95¦07/09/15: 95%->100 | 26.922 (new), 26.114 | 66 | 34 |  |  | Tue 03/03/15 | Mon 07/09/15
2559 | 690038 | (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627 | VTRI_EXT | 2 | Rel-13 | S4-IETF | Fri 12/12/14 | Fri 11/09/15 | 100% | SP-15047 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added; 23/4/20: 10%->100 | 26.114, draft-ietf-payload-flexible-fec-scheme | 69 | 35 |  |  | Tue 03/03/15 | Thu 23/04/20
2560 | 660052 | Acoustic Test methods and Performance Objectives for Speakerphone Performance in Noisy Environments | ATeMPO_SPINE | 1 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/03/16 | 100% | SP-140740 |  | Andre Schevciw, Qualcomm Incorporated; Scott Isabelle, Audience Inc. | aschevci@qti.qualcomm.com; sisabelle@audience.com | June2015: Compl:0%->10. Aug: FCD: Jun->Sep15¦07/09/15: 10%->30, FCD:09/15->12/15¦7/12/15: 40%->80, FCD: 12/15->03/16. ES in SP-150642¦7/3/16: 80%->100 | 26.131, 26.132 | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/03/16
2561 | 630010 | Rel-13 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM13 | 1 | Rel-13 | S5 | Wed 20/06/12 | Fri 11/03/16 | 100% | SP-150305 | - | - | - | OAM13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150305¦5/10/15: 28.683 added; | 28.683 | 63 | 32 |  |  | Thu 27/02/14 | Mon 05/10/15
2562 | 560132 | Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | SON-NM-CCO | 2 | Rel-13 | S5 | Fri 19/09/14 | Fri 11/12/15 | 100% | SP-140060 | - | Ericsson | robert.petersen@ericsson.com | SP#64 work not started. Dec.14: 0->20, cd: 06/15->12/15. Mar 15: 20->30%¦June2015: Compl:30%->50¦07/09/15: 50%->60¦7/12/15: 60%->100 | 28.627, 28.628, 32.103, 32.422, 32.425, 32.442 | 56 | 29 |  |  | Wed 18/04/12 | Mon 07/12/15
2563 | 560034 | Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 2 | Rel-13 | S5 | Wed 20/06/12 | Wed 18/03/15 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0 | - | 56 | 29 |  |  | Mon 14/05/12 | Mon 01/09/14
2564 | 560134 | TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | Wed 20/06/12 | Wed 18/03/15 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13.. Dec.14: 72->78. Mar 15: 80%¦June2015: Compl:80%->85¦07/09/15: 85%->90¦7/12/15: 90%->100 | New 32.838 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
2565 | 560234 | TS work on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | Mon 25/06/12 | Wed 18/03/15 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13¦7/12/15: 50%->100 | 32.101/2/3,32.111-1,32.111-2,32.111-6,32.15x,32.401,32.411,32.412,32.421,32.422,32.423,32.431,32.432,32.436,32.441,32.442,32.446,32.500,32.501,32.502,32.506,32.521,32.522,32.526,32.531,32.532,32.536,32.551,32.691,32.692,32.696,32.762 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
2566 | 560235 | Converged management Performance Management Interface Definitions | OAM-PMID | 2 | Rel-13 | S5 | Wed 20/06/12 | Fri 11/12/15 | 100% | SP-150678 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678 | new TSs 32.863 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
2567 | 560036 | WLAN Management | WLAN-OAM | 2 | Rel-13 | S5 | Wed 27/06/12 | Wed 17/06/15 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 moved to Rel-13. Updated WID SP-130042=>SP-140535 (split into Rel-12 Study & Rel-13 normative WI). TR 32.841 was completed as a Rel-12 Study and has triggered this normative work | - | 56 | 29 |  |  | Tue 12/06/12 | Wed 10/09/14
2568 | 560136 | WLAN Network Resource Model for Type-2 interface | WLAN-OAM-SA5 | 3 | Rel-13 | S5 | Wed 27/06/12 | Wed 17/06/15 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. Dec.14: 10->20¦June2015: Compl:20%->70¦07/09/15: 70%->80¦7/12/15: 80%->100 | new (28.680, 28.682), 28.681 | 56 | 29 |  |  | Tue 12/06/12 | Mon 07/12/15
2569 | 560236 | WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface | WLAN-OAM-SA5ietf | 3 | Rel-13 | S5 | Wed 27/06/12 | Wed 17/06/15 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified¦June2015: Compl:5%->20¦07/09/15: 20%->60¦7/12/15: 60%->100 | new 28.403 | 56 | 29 |  |  | Tue 12/06/12 | Mon 07/12/15
2570 | 600044 | Energy Efficiency related Performance Measurements | OAM-PM_EE | 2 | Rel-13 | S5 | Fri 21/06/13 | Fri 11/03/16 | 100% | SP-140612 | - | Nokia Networks | Yizhi.yao@nsn.com | SP#65 updated WID SP-130263=>SP-140612. Completion 09/14=>06/15. Moved to Rel-13¦June2015: Compl:25%->40¦07/09/15: 40%->50. ES in SP-150708¦7/3/16: 50%->100 | 32.425 | 60 | 31 |  |  | Sun 02/06/13 | Mon 07/03/16
2571 | 660055 | Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement | MBSFN_MDT | 2 | Rel-13 | S5 | Fri 12/12/14 | Fri 12/12/14 | 100% | SP-140786 |  | Padma Sudarsan (Alcatel-Lucent) | padma.sudarsan<AT>alcatel-lucent<DOT>com | Mar 15: 0->15%¦June2015: Compl:15%->100 | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 66 | 34 |  |  | Fri 12/12/14 | Mon 15/06/15
2572 | 641000 | Rel-13 Charging | CH13 | 1 | Rel-13 | S5 | Thu 19/06/14 | Wed 16/12/15 | 100% | SP-150307 | - | - | - | CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150307 | - | 64 | 33 |  |  | Fri 06/06/14 | Thu 18/06/15
2573 | 640059 | Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 2 | Rel-13 | S5 | Thu 19/06/14 | Wed 16/12/15 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations | Stage 2/3 | 64 | 33 |  |  | Fri 06/06/14 | Fri 06/06/14
2574 | 640159 | TR on Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | Thu 19/06/14 | Wed 17/06/15 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Dec.14: 10->25%. Mar15: 20->60%. 06/15: 100%¦7/12/15: 100%->100 | New 32.843 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/12/15
2575 | 640259 | Specification of Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | Mon 23/06/14 | Wed 16/12/15 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | 07/09/15: 0%->80¦7/12/15: 80%->100 | 32.251, 32.299 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/12/15
2576 | 660056 | ULI and release causes for charging enhancement for VoLTE | ULRELC-CH | 2 | Rel-13 | S5 | Fri 12/12/14 | Mon 07/12/15 | 100% | SP-140785 |  | Alcatel-Lucent, Maryse Gardella | Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com | Acronym changed to ULRELC-CH. Mar15: 0->5%. CD: 12/14->09/15. 06/15: 20%¦07/09/15: 20%->40¦7/12/15: 40%->100, FCD: 09/15->12/15 | 32.251, 32.260, 32.299, 32.298, | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/12/15
2577 | 670025 | Charging on enhancements for IMS Service Continuity | CHeISC | 2 | Rel-13 | S5 | Thu 05/03/15 | Wed 09/09/15 | 100% | SP-150055 |  | Gerald Goermer | Gerald <dot> Goermer <at> nsn <dot> com | 06/15: 0->50%¦07/09/15: 50%->100. FCD: 12/15->09/15 | 32.260, 32.299, 32.298 | 67 | 34 |  |  | Thu 05/03/15 | Mon 07/09/15
2578 | 680037 | Announcements for IMS Online Charging | ANIMO | 2 | Rel-13 | S5 | Mon 15/06/15 | Mon 14/12/15 | 100% | SP-150675 |  | Amdocs, Naceur <dot> Lagha <at> Amdocs <dot> com |  | 07/09/15: 0%->30¦7/12/15: 30%->100¦7/12/15: WID:SP-150307->SP-150675 | 32.260, 32.275, 32.299, 32.240, 32.281 | 68 | 35 |  |  | Sun 14/06/15 | Mon 07/12/15
2579 | 680038 | Enhanced S2a Mobility Over Trusted WLAN access to EPC - Charging | eSaMOG-CH | 2 | Rel-13 | S5 | Mon 15/06/15 | Thu 17/09/15 | 100% | SP-150344 |  | Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com |  | 07/09/15: 0%->30¦7/12/15: 30%->100 | 32.240, 32.251, 32.299, 32.298 | 68 | 35 |  |  | Sun 14/06/15 | Mon 07/12/15
2580 | 610005 | Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS | RTCP_MUX | 1 | Rel-13 | C4,C1,C3 | Mon 09/09/13 | Fri 11/12/15 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Stage 2/3 | Stage 2/3 | 61 | 31 |  |  | Sat 10/08/13 | Wed 03/09/14
2581 | 610105 | CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C4 | Mon 09/09/13 | Fri 11/12/15 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15. Dec.14: 10->100 | 23.334, 29.334 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2582 | 610205 | CT1 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C1 | Fri 13/09/13 | Fri 11/12/15 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15¦7/12/15: 0%->100 | 24.229 | 61 | 31 |  |  | Sat 10/08/13 | Mon 07/12/15
2583 | 610305 | CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C3 | Fri 13/09/13 | Fri 11/12/15 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15¦8/12/15: 0%->100 | 29.213, 29.214 | 61 | 31 |  |  | Sat 10/08/13 | Tue 08/12/15
2584 | 550017 | LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US | 1 | Rel-13 | R4,R2,R3 | Mon 05/03/12 | Tue 09/06/15 | 8% | RP-121397 | - | LightSquared | masoud.olfat@lightsquared.com | RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
2585 | 550117 | Core part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Core | 2 | Rel-13 | R4,R2,R3 | Tue 06/08/13 | Tue 10/03/15 | 15% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 03/15=>06/15. On hold till 12/2014 | 25.101, 25.104, 25.113, 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, new 36.832 | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
2586 | 550217 | Perf. Part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Perf | 2 | Rel-13 | R4 | Mon 05/03/12 | Tue 09/06/15 | 5% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 06/15=>09/15. . On hold till 12/2014 | 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.113, 36.124, 36.133, 36.141, 36.307 | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
2587 | 640019 | Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig | 1 | Rel-13 | R3 | Wed 18/06/14 | Tue 15/09/15 | 100% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015) | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 23/06/14
2588 | 640119 | Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig-Core | 2 | Rel-13 | R3 | Wed 18/06/14 | Tue 15/09/15 | 100% | RP-141032 | RP-151213 | Samsung | sunghwan.won@samsung.com | CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141805 1st Apr 15: Compl:15%->30% 1st Apr 15: Stat Rep: RP-141805->RP-150162 03/07/15: Compl:30%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150162->RP-150846 29/09/1 | 36.300, 36.423 | 64 | 33 |  |  | Mon 16/06/14 | Tue 29/09/15
2589 | 640036 | 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1 | 1 | Rel-13 | R4 | Tue 17/06/14 | Thu 15/09/16 | 100% | RP-141710 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | Triggered by TR 37.846 Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) FS_UTRA_LTE_1980_2170_REG1 | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2590 | 640136 | Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Core | 2 | Rel-13 | R4 | Tue 17/06/14 | Tue 15/12/15 | 100% | RP-151732 | RP-151299 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:5%->15%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03 | 36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL), New 36.862 (Technical Report for 2 GHz Band in Region 1) | 64 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2591 | 640236 | Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Perf | 2 | Rel-13 | R4 | Wed 18/06/14 | Tue 15/12/15 | 100% | RP-151732 | RP-151299 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150106->RP-150705 29/09/15: Stat | 36.101, 36.104, 36.133, 36.141, 36.307, 36.862 | 64 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2592 | 710066 | UE Conformance Test Aspects - FDD LTE band 1980-2010 MHz and 2170-2200MHz (band 65) in Region1 and Region 3 | LTE_1980_2170_REG1_REG3-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-160774 | - | Dish Network |  | testing REL-13 LTE_1980_2170_REG1-Core and LTE_1980_2170_REG3-Core¦ |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2593 | 650034 | Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS | 1 | Rel-13 | R3,G2 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-141624 | - | Nokia Networks | krzysztof.kordybach@nsn.com | Triggered by TR 37.822 Study on Next-Generation SON for UTRA and LTE (FS_UTRA_LTE_NG_SON) | LTE | 65 | 33 |  |  | Mon 16/06/14 | Tue 16/09/14
2594 | 650134 | Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS-Core | 2 | Rel-13 | R3 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-141624 | RP-150727 | Nokia Networks | krzysztof.kordybach@nsn.com | CD:Tue 16/06/15->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141854 1st Apr 15: Compl:15%->25% 1st Apr 15: Stat Rep: RP-141854->RP-150110 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150110->RP-150727 | 36.300, 36.423, 36.413, 25.413 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2595 | 660001 | Usage Monitoring Control PCC Extension | eUMONC | 1 | Rel-13 | S2 | Wed 03/12/14 | Tue 16/06/15 | 100% | SP-140709 |  | CTBRI |  |  |  | 66 | 34 |  |  | Wed 03/12/14 | Wed 03/12/14
2596 | 660022 | Stage 2 of Usage Monitoring Control PCC Extension | eUMONC-SA2 | 2 | Rel-13 | S2 | Wed 03/12/14 | Tue 16/06/15 | 100% | SP-140709 |  | China Telecom, Jinyan Li | lijy@ctbri.com.cn | June2015: Compl:6%->100. Verbal indication from SA2 chair | 23.203 | 66 | 34 |  |  | Wed 03/12/14 | Mon 15/06/15
2597 | 660020 | CT3 Aspect of Usage Monitoring Control extension | eUMONC-CT3 | 2 | Rel-13 | C3 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140927 |  | ZTE |  | Mar.15: 10->100% | 29.212, 29.215 | 66 | 34 |  |  | Thu 04/12/14 | Wed 04/03/15
2598 | 660030 | Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 1 | Rel-13 | C1 | Mon 06/10/14 | Fri 13/03/15 | 100% | CP-140813 |  | Ericsson |  |  |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
2599 | 660014 | CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140813 |  | Ericsson |  | . 12/12:0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN | 24.229, 24.302 | 66 | 34 |  |  | Thu 04/12/14 | Tue 05/05/15
2600 | 660023 | CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 2 | Rel-13 | C4 | Mon 06/10/14 | Fri 13/03/15 | 100% | CP-140813 |  | Ericsson |  | Mar.15: 0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN | 29.274, 29.275 | 66 | 34 |  |  | Thu 04/12/14 | Tue 05/05/15
2601 | 660028 | P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 1 | Rel-13 | C4 | Wed 03/12/14 | Mon 14/12/15 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | WID added, acronym. June 2015: WID: CP-140995-> CP-150275 |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
2602 | 660041 | CT1 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 2 | Rel-13 | C1 | Wed 03/12/14 | Mon 14/12/15 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CT4->CT1. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:0%->10. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 10%->70¦7/12/15: 70%->100 | 24.302, 24.229, 24.244, 24.008 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/12/15
2603 | 660040 | CT4 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 2 | Rel-13 | C4 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | Dec.14: 0->5%. Mar.15: 5->100%. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:100%->75. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 75%->85¦7/12/15: 85%->100 | New 29.8xy, 23.380, 29.273, 29.274, 29.275, 23.008 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/12/15
2604 | 680012 | Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 1 | Rel-13 | C4 | Mon 15/06/15 | Thu 17/09/15 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com |  | 24.244, 24.302, 29.273, 29.274, 29.275, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
2605 | 680039 | CT1 aspects of Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 2 | Rel-13 | C1 | Mon 15/06/15 | Thu 17/09/15 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com | 07/09/15: 0%->80¦7/12/15: 80%->100 | 24.244, 24.302 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2606 | 680040 | CT4 aspects of Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 2 | Rel-13 | C4 | Mon 15/06/15 | Thu 17/09/15 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com | 07/09/15: 0%->90¦7/12/15: 90%->100 | 29.273, 29.274, 29.275, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2607 | 680041 | Authentication Signalling Improvements for WLAN | ASI_WLAN | 1 | Rel-13 | C1 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150330 |  | Youyang Yu | yuyouyang@huawei.com | 07/09/15: 0%->40¦7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727¦7/3/16: 95%->100 | 24.302, 24.244 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2608 | 660016 | Stage-3 SAE Protocol Development - Phase 4 | SAES4 | 1 | Rel-13 | C1 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms | 23.12, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 66 | 34 |  |  | Thu 04/12/14 | Tue 24/03/15
2609 | 670037 | SAE Protocol Development (Stage 3) - Phase 4 | SAES4 | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms. 5/5/15: acronym changed from "SAES4-CT1"¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
2610 | 670038 | CS Fallback in EPS - Phase 4 | SAES4-CSFB | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
2611 | 670039 | SAE for support for non-3GPP accesses - Phase 4 | SAES4-non3GPP | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->50¦7/12/15: 50%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
2612 | 660034 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 1 | Rel-13 | C1,C3 | Wed 03/12/14 | Fri 13/03/15 | 74% | CP-140928 |  | Orange |  |  |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
2613 | 660134 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 13/03/15 | 100% |  |  | Orange |  | 5/5/15: created¦June2015: Compl:0%->70¦07/09/15: 70%->100 | 24.229 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/09/15
2614 | 660036 | (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C1-IETF | Wed 03/12/14 | Tue 10/03/15 | 0% | CP-140928 |  | Orange |  | Mar15: resp WG:C1->C1-IETF. WID changed from INNB_IW-CT1 | draft-mohali-dispatch-cause-for-service-number | 66 | 34 |  |  | Thu 04/12/14 | Wed 18/03/15
2615 | 660021 | CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C3 | Wed 03/12/14 | Fri 13/03/15 | 100% | CP-140928 |  | Orange |  | Mar.15: 80->90%. WID changed from INNB_IW-CT3¦June2015: Compl:0%->98¦07/09/15: 98%->99¦7/12/15: 99%->100 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2616 | 660042 | Warning Status Report in EPS | WSR_EPS | 1 | Rel-13 | C4 | Wed 03/12/14 | Mon 14/09/15 | 100% | CP-150792 |  | one2many |  | 5/5/15: acronym changed from "WSR_EP"¦7/12/15: WID:CP-140998->CP-150792 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2617 | 660015 | CT1 aspects of Warning Status Report in EPS | WSR_EPS | 2 | Rel-13 | C1 | Wed 03/12/14 | Mon 14/09/15 | 100% | CP-150792 |  | one2many |  | 2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from "WSR_EP"¦07/09/15: 0%->25¦7/12/15: 25%->100¦7/12/15: WID:CP-140998->CP-150792 | New 23.712 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2618 | 660029 | CT4 aspects of Warning Status Report in EPS | WSR_EPS | 2 | Rel-13 | C4 | Wed 03/12/14 | Mon 14/09/15 | 100% | CP-150792 |  | one2many |  | 2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from "WSR_EP"¦7/12/15: 0%->100¦7/12/15: WID:CP-140998->CP-150792 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2619 | 660026 | Shared Data Update for Multiple Subscriber | SHARED_SubData_UPD | 1 | Rel-13 | C4 | Wed 03/12/14 | Wed 03/12/14 | 100% | CP-150013 |  | Huawei, Susan Shi | susan.shishufeng@huawei.com | Mar.15: 0->50%, WID: CP-140804->CP-150013¦June2015: Compl:50%->95¦07/09/15: 95%->100 | 29.328, 29.364 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/09/15
2620 | 660017 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 1 | Rel-13 | C1 | Wed 03/12/14 | Tue 20/06/17 | 70% | CP-140815 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10% | 23.218, 24.998, 24.930 | 66 | 34 |  |  | Thu 04/12/14 | Wed 04/03/15
2621 | 670096 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C1 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140815 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2622 | 720059 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C1 | Mon 13/06/16 | Tue 20/06/17 | 10% | CP-140815 |  | Alcatel-Lucent | Keith Drage |  | draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2623 | 670097 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C3 | Wed 03/12/14 | Fri 11/12/15 | 100% | CP-140815 |  | Alcatel-Lucent | Keith Drage | 2/4/15: added, following CT3 chair's info that the WID also has a CT3 part¦June2015: Compl:0%->20¦07/09/15: 20%->40¦7/12/15: 40%->100 |  | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/12/15
2624 | 670013 | Retry restriction for Improving System Efficiency | RISE | 1 | Rel-13 | C1 | Wed 04/03/15 | Tue 15/12/15 | 100% | CP-150495 |  | Huawei, Lin Shu | shulin@huawei.com | Continuation of Rel-12 SINE UID 620006. 5/5/15: acronym changed from "RISE"¦June2015: Compl:0%->10¦07/09/15: 10%->70¦14/09/15: WID:CP-150092->CP-150495¦7/12/15: 70%->100 |  | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
2625 | 670020 | H.248 Aspects of WebRTC Data Channel on IMS Access Gateway | WebRTCH248DC | 1 | Rel-13 | C4 | Wed 04/03/15 | Fri 11/03/16 | 100% | CP-150185 |  | China Mobile, Xiaoning Du | duxiaoning@chinamobile.com |  | 23.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 09/03/15
2626 | 670001 | CT4 Aspect of H.248 Aspects of WebRTC Data Channel on IMS Access Gateway | WebRTCH248DC | 2 | Rel-13 | C4 | Wed 04/03/15 | Fri 11/03/16 | 100% | CP-150185 |  | China Mobile, Xiaoning Du. ES in 639 | duxiaoning@chinamobile.com | June2015: Compl:0%->10¦07/09/15: 10%->20¦7/12/15: 20%->90¦7/3/16: 90%->100 | 23.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
2627 | 670021 | Continuation of the Overload Control for PCC based Diameter applications | cDOCME_PCC | 1 | Rel-13 | C3 | Wed 04/03/15 | Fri 11/12/15 | 100% | CP-150194 |  | ZTE, Zhou Xiaoyun | zhou.xiaoyun@zte.com.cn | Relates to UID 580026 (Study on Diameter overload control mechanism)¦June2015: Compl:0%->100 | 29.212, 29.215, 29.219, 29.217 | 67 | 34 |  |  | Wed 04/03/15 | Mon 15/06/15
2628 | 670026 | Review of dedicated 3GPP UICC features | Red_UCe | 1 | Rel-13 | C6 | Mon 09/03/15 | Fri 11/12/15 | 100% | CP-150152 |  | Blackberry, Adrian Buckley | abuckley@blackberry.com | Results from the homonymous Study¦June2015: Compl:0%->60¦07/09/15: 60%->75¦7/3/16: 75%->100 | 31.102, 31.111, 31.121, 31.124 | 67 | 34 |  |  | Mon 09/03/15 | Mon 07/03/16
2629 | 680014 | Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 1 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com |  | 23.334, 29.334, 29.162, 29.238, 23.333, 29.333, 29.163, 29.332, 29.292, 29.232, 29.235 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
2630 | 680042 | CT3 aspects of Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 2 | Rel-13 | C3 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com | 7/12/15: 0%->90. FCD->03/16. ES in CP-150614¦7/3/16: 90%->100 | 29.162, 29.163, 29.292, 29.235 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2631 | 680043 | CT4 aspects of Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 2 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com | 07/09/15: 0%->5¦7/12/15: 5%->70. FCD->03/16. ES in CP-150614¦7/3/16: 70%->100 | 23.334, 29.334, 29.238, 23.333, 29.333, 29.332, 29.232 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2632 | 640044 | (SA66: on hold) Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | Wed 18/06/14 | Tue 16/09/14 | 100% | SP-140509 | S1-143306 | Intel | Eric.siow@intel.com | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO) | 22.101 | 64 | 33 |  |  | Tue 27/05/14 | Fri 12/12/14
2633 | 660012 | Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO-ST1 | 2 | Rel-13 | S1 | Wed 18/06/14 | Tue 16/09/14 | 100% | SP-140509 | S1-143306 | Intel | Eric.siow@intel.com | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO). Dec.14: former S1-only feature split | 22.101 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/12/14
2634 | 640051 | Enhanced CS Fallback (CSFB) | eCSFB | 1 | Rel-13 | S2,S3 | Wed 18/06/14 | Fri 13/03/15 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB) | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
2635 | 640151 | TR for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | Wed 18/06/14 | Fri 12/12/14 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Dec.14: 35->85%¦14/09/15: 85%->100. SA#69: decision not to continue the work on this. No normative work. | New 23.772 | 64 | 33 |  |  | Wed 11/06/14 | Mon 14/09/15
2636 | 640251 | Deleted - Stage 2 for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | Fri 13/03/15 | Fri 13/03/15 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part) | 23.272 | 64 | 33 | SP-69 |  | Wed 11/06/14 | Wed 11/06/14
2637 | 650024 | Deleted - Security for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S3 | Thu 18/09/14 | Thu 18/09/14 | 100% | SP-140579 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579¦14/09/15: 0%->100. SA#69: deleted, since SA2 has stopped the work. |  | 65 | 33 | SP-69 |  | Mon 15/09/14 | Mon 14/09/15
2638 | 650025 | SRVCC Enhancements for Transcoding Avoidance | SETA | 1 | Rel-13 | S2 | Fri 19/09/14 | Wed 17/06/15 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | Enhance chances for end-to-end transcoder free operation (TrFo) where possible/ ensure proper CS radio resources are reserved for optimal RAN codec. Address TrFo of EVS codecs during SRVCC that are not covered by Rel-12 | Stage 2 | 65 | 33 |  |  | Tue 05/08/14 | Fri 12/12/14
2639 | 650125 | TR for SRVCC Enhancements for Transcoding Avoidance | SETA-SA2TR | 2 | Rel-13 | S2 | Fri 19/09/14 | Fri 13/03/15 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | Dec.14: 0->70%¦14/09/15: 70%->100. Stopped without conclusion, no intention to continue the study nor to do any mormative work. | New 23.7xy | 65 | 33 |  |  | Tue 05/08/14 | Mon 14/09/15
2640 | 650225 | Deleted - Stage 2 for SRVCC Enhancements for Transcoding Avoidance | SETA-SA2 | 2 | Rel-13 | S2 | Wed 17/06/15 | Wed 17/06/15 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | SA#69: stop the work on this. | 23.216, 23.237 | 65 | 33 | SP-69 |  | Tue 05/08/14 | Wed 16/09/15
2641 | 590030 | Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA | 1 | Rel-13 | R4 | Mon 04/03/13 | Thu 15/09/16 | 100% | RP-130373 | - | Huawei | ronnie.zhang@huawei.com | Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA) | UTRA, LTE, GERAN | 59 | 30 |  |  | Tue 26/02/13 | Mon 15/09/14
2642 | 590130 | Core part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Core | 2 | Rel-13 | R4 | Mon 04/03/13 | Tue 15/03/16 | 100% | RP-160188 | RP-151241 | Huawei | ronnie.zhang@huawei.com | ¦CD:Thu 11/12/14->Tue 15/12/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241¦ | New 37.142 (AAS BS Tx & Rx), New 37.842, 37.114, 37.145-1, 37.145-2 | 59 | 30 |  |  | Tue 26/02/13 | Tue 22/03/16
2643 | 590230 | Perf. part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Perf | 2 | Rel-13 | R4 | Fri 15/03/13 | Thu 15/09/16 | 100% | RP-160188 | RP-151241 | Huawei | ronnie.zhang@huawei.com | ¦CD:Sat 18/06/16->Wed 15/06/16¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Stat Rep: RP-150687->RP-151241 22/3/16: Compl:2 26/9/16: Compl:95%->100% | New 37.1xy (AAS BS conformance testing) | 59 | 30 |  |  | Tue 26/02/13 | Mon 26/09/16
2644 | 660074 | Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox | 1 | Rel-13 | R2 | Mon 15/12/14 | Thu 15/09/16 | 100% | RP-142311 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
2645 | 660174 | Core part: Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox-Core | 2 | Rel-13 | R2,R1,R3 | Fri 14/08/15 | Tue 15/03/16 | 100% | RP-150441 | RP-151337 | Qualcomm Incorporated, Shailesh Patil | patil@qti.qualcomm.com | Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2646 | 660274 | Perf. part: Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox-Perf | 2 | Rel-13 | R4 | Mon 15/12/14 | Thu 15/09/16 | 100% | RP-150441 | RP-151337 | Qualcomm | Qualcomm | 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Stat Rep: RP-150795->RP-151337¦1/1/16: CD¦22/3/16: Compl:0%->10%;26/9/16: Compl:85%->100% |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 26/09/16
2647 | 660076 | Radiated requirements for the verification of multi-antenna reception performance of UEs | UTRA_LTE_MIMO_OTA | 1 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142221 | RP-171826 | Intel | Intel |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
2648 | 660176 | Core part: Radiated requirements for the verification of multi-antenna reception performance of UEs | UTRA_LTE_MIMO_OTA-Core | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-160344 | RP-151573 | Intel | Intel | 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142221->RP-150261 1st Apr 15: Stat Rep: ->RP-150260 03/07/15: Compl:5%->15% 03/07/15: Stat Rep: RP-150260->RP-150746 29/09/15: Compl:15%->25% 29/09/15: WID: RP-150261->RP-151574 29/09/15: Stat Rep: RP-15074 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2649 | 660077 | UE core requirements for uplink 64 QAM | LTE_UL64QAM | 1 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-142222 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
2650 | 660177 | Core part: UE core requirements for uplink 64 QAM | LTE_UL64QAM-Core | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150691 | RP-151244 | Huawei | Huawei | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150232 03/07/15: Compl:10%->90% 03/07/15: WID: RP-142222->RP-150691 03/07/15: Stat Rep: RP-150232->RP-150688 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150688->RP-151244 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2651 | 680069 | UE Conformance Test Aspects - Core Requirements for Uplink 64QAM for E-UTRA | LTE_UL64QAM-UEConTest | 1 | Rel-13 | R5 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150812 | RP-151174 | CMCC |  | tested Core part: LTE_UL64QAM-Core which is not yet completed 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151174 1/1/16: Compl:5%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2652 | 660078 | Performance requirements of MMSE-IRC receiver for LTE BS | LTE_MMSE_IRC_BS | 1 | Rel-13 | R4 | Mon 15/12/14 | Wed 15/06/16 | 100% | RP-142223 |  | China Telecom | China Telecom |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
2653 | 660278 | Perf. part: Performance requirements of MMSE-IRC receiver for LTE BS | LTE_MMSE_IRC_BS-Perf | 2 | Rel-13 | R4 | Mon 15/12/14 | Wed 15/06/16 | 100% | RP-150206 | RP-151215 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142223->RP-150206 1st Apr 15: Stat Rep: ->RP-150204 03/07/15: Compl:10%->35% 03/07/15: Stat Rep: RP-150204->RP-150630 29/09/15: Compl:35%->50% 29/09/15: Stat Rep: RP-150630->RP-151215¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/07/16
2654 | 660079 | CRS Interference Mitigation for LTE Homogenous Deployments | LTE_CRSIM | 1 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142263 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
2655 | 660279 | Perf. part: CRS Interference Mitigation for LTE Homogenous Deployments | LTE_CRSIM-Perf | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142263 | RP-151171 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Mon 15/06/15->Tue 15/03/16 1st Apr 15: Stat Rep: ->RP-150061 03/07/15: Compl:10%->20% 03/07/15: Stat Rep: RP-150061->RP-150584 29/09/15: Compl:20%->30% 29/09/15: Stat Rep: RP-150584->RP-151171 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2656 | 670055 | Dual Connectivity enhancements for LTE | LTE_dualC_enh | 1 | Rel-13 | R2 | Mon 16/03/15 | Wed 15/06/16 | 100% | RP-150490 |  | NTT DOCOMO |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2657 | 670155 | Core part: Dual Connectivity enhancements for LTE | LTE_dualC_enh-Core | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151739 | RP-151330 | NTT DOCOMO |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150744 29/09/15: Compl:25%->55% 29/09/15: Stat Rep: RP-150744->RP-151330 1/1/16: Compl:55%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2658 | 670255 | Perf. part: Dual Connectivity enhancements for LTE | LTE_dualC_enh-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Wed 15/06/16 | 100% | RP-151739 | RP-151330 | NTT DOCOMO |  | 03/07/15: Stat Rep: ->RP-150744 29/09/15: Stat Rep: RP-150744->RP-151330 ¦1/1/16: WID: RP-150490->RP-15173922/3/16: Compl:0%->50%; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
2659 | 670056 | Multicarrier Load Distribution of UEs in LTE | LTE_MC_load | 1 | Rel-13 | R2 | Mon 16/03/15 | Thu 15/09/16 | 100% | RP-150491 |  | ZTE |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2660 | 670156 | Core part: Multicarrier Load Distribution of UEs in LTE | LTE_MC_load-Core | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-152181 | RP-151190 | ZTE |  | 03/07/15: Compl:0%->40% 03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: Compl:40%->55% 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-151190 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2661 | 670256 | Perf. part: Multicarrier Load Distribution of UEs in LTE | LTE_MC_load-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Thu 15/09/16 | 100% | RP-161699 | RP-151190 | ZTE |  | 03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-1511901/1/16:22/3/16: Compl:70%->75%¦26/9/16: Compl:90%->100%¦26/9/16: WID: RP-152181 |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 26/09/16
2662 | 670058 | LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio | 1 | Rel-13 | R2 | Mon 16/03/15 | Fri 14/09/18 | 99% | RP-150510 |  | Intel |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2663 | 670158 | Core part: LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio-Core | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-160521 | RP-151563 | Intel |  | 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081, 07/08/15: impacted TSs added 29/09/15: Compl:30%->35% 29/09/15: Stat Rep: RP-151081->RP-151563; | 36.461, 36.462, 36.463, 36.464, 36.465, 36.622, 36.623, 36.624, 36.625, 36.360 | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
2664 | 670258 | Perf. part: LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-160521 | RP-151563 | Intel |  | 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081 29/09/15: Stat Rep: RP-151081->RP-1515631/1/16: Compl:0%->10% ¦22/3/16: Compl:10%->100%¦ |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
2665 | 710070 | UE Conformance Test Aspects - WLAN/3GPP Radio Level Integration and Interworking Enhancement Interworking | LTE_WLAN_radio-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Fri 14/09/18 | 100% | RP-180942 |  | Intel |  | testing REL-13 LTE_WLAN_radio-Core¦1/7/16: Compl:0%->5%¦20/21/3/17: Compl:20 ;27/3/18: ;¦26/3/19: 58%->100 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 26/03/19
2666 | 670060 | RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network | CSPS_Coord-UTRA | 1 | Rel-13 | R3 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150500 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2667 | 670160 | Core part: RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network | CSPS_Coord-UTRA-Core | 2 | Rel-13 | R3 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150500 | RP-151289 | Ericsson |  | 03/07/15: Compl:0%->45% 03/07/15: Stat Rep: ->RP-150842 29/09/15: Compl:45%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150842->RP-1512891/1/16: Compl:80%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2668 | 670061 | LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL | 1 | Rel-13 | R4 | Mon 03/01/00 | Fri 15/09/17 | 99% | RP-150427 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2669 | 670161 | Core part: LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-Core | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150427 | RP-151265 | Ericsson |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150803->RP-151265¦1/1/16: Compl:50%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2670 | 670261 | Perf. part: LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-Perf | 2 | Rel-13 | R4 | Mon 03/01/00 | Thu 15/09/16 | 100% | RP-161237 | RP-151265 | Ericsson |  | 03/07/15: Compl:0%->15% 03/07/15: CD:Mon 02/10/00->Wed 15/06/16 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:15%->35% 29/09/15: Stat Rep: RP-150803->RP-15126522/3/16: Compl:60%-;26/9/16: Compl:90%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 26/09/16
2671 | 700066 | UE Conformance Test Aspects - LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-UEConTest | 2 | Rel-13 | R5 | Tue 15/12/15 | Fri 15/09/17 | 100% | RP-160078 |  | Ericsson |  | ¦22/3/16: Compl:0%->10%¦1/7/16: Compl:10%->25%¦ 26/9/16: 21/3/17: Compl:60%->70 ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
2672 | 670062 | AWS-Extension Band for LTE | LTE_AWS_EXT | 1 | Rel-13 | R4 | Mon 16/03/15 | Thu 15/09/16 | 100% | RP-150428 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2673 | 670162 | Core part: AWS-Extension Band for LTE | LTE_AWS_EXT-Core | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150800 | RP-151343 | Ericsson |  | 03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2674 | 670262 | Perf. part: AWS-Extension Band for LTE | LTE_AWS_EXT-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150800 | RP-151343 | Ericsson |  | 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Stat Rep: RP-150796->RP-151343¦ |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2675 | 700068 | UE Conformance Test Aspects - AWS-Extension Band for LTE (Band 66) | LTE_AWS_EXT-UEConTest | 2 | Rel-13 | R5 | Tue 15/12/15 | Thu 15/09/16 | 100% | RP-161524 |  | Ericsson |  | ¦22/3/16: Compl:0%->10%1/7/16: Compl:10%->65%26/9/16: Comp |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 26/09/16
2676 | 670063 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7_BWset | 1 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150171 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2677 | 670163 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7_BWset-Core | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150602 | RP-150536 | Nokia Networks |  | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
2678 | 670263 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7_BWset-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150602 | RP-150536 | Nokia Networks |  | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
2679 | 670064 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5_BWset | 1 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150425 |  | Samsung |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2680 | 670164 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5_BWset-Core | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150425 | RP-150536 | Samsung |  | 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
2681 | 670264 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5_BWset-Perf | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150425 | RP-150536 | Samsung |  | 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
2682 | 670054 | Multiflow Enhancements for UTRA | HSDPA_MFTX_enh | 1 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/09/15 | 100% | RP-150288 |  | Nokia | alexander.sayenko@nokia.com |  |  | 67 | 34 |  |  | Tue 05/05/15 | Tue 05/05/15
2683 | 670154 | Core part: Multiflow Enhancements for UTRA | HSDPA_MFTX_enh-Core | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/09/15 | 100% | RP-151021 | RP-151302 | Nokia | alexander.sayenko@nokia.com | 03/07/15: Compl:0%->80% 03/07/15: WID: RP-150288->RP-151021 03/07/15: Stat Rep: ->RP-150827 29/09/15: Compl:80%->100% 29/09/15: Stat Rep: RP-150827->RP-151302 |  | 67 | 34 |  |  | Tue 05/05/15 | Tue 29/09/15
2684 | 680044 | Message interworking during PS to CS SRVCC | mSRVCC | 1 | Rel-13 | C1 | Mon 15/06/15 | Wed 16/09/15 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com |  |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
2685 | 680045 | CT1 aspects of Message interworking during PS to CS SRVCC | mSRVCC | 2 | Rel-13 | C1 | Mon 15/06/15 | Wed 16/09/15 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com | 07/09/15: 0%->25¦7/12/15: 25%->100 | 24.237, 24.292 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2686 | 680046 | CT3 aspects of Message interworking during PS to CS SRVCC | mSRVCC | 2 | Rel-13 | C3 | Mon 15/06/15 | Wed 16/09/15 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com | 07/09/15: 0%->70¦7/12/15: 70%->100 | 29.292 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2687 | 690008 | Support of Emergency services over WLAN – phase 1 | SEW1 | 1 | Rel-13 | S2 | Thu 18/06/15 | Fri 11/03/16 | 100% | SP-150253 |  | Laurent thiebaut | Laurent.thiebaut@alcatel-lucent.com | 07/09/15: 0%->100 | 23.402, 23.167, 23.271, 23.203, 23.228 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/09/15
2688 | 680051 | Stage 2 of Support of Emergency services over WLAN - phase 1 | SEW1 | 2 | Rel-13 | S2 | Thu 18/06/15 | Wed 16/09/15 | 100% | SP-150253 |  | Laurent thiebaut | Laurent.thiebaut@alcatel-lucent.com | 07/09/15: 0%->100 | 23.402, 23.167, 23.271, 23.203, 23.228 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/09/15
2689 | 690009 | CT aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 2 | Rel-13 | ct | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
2690 | 690022 | CT1 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 60%->95. FCD -> 03/16, ES in CP-150729¦7/3/16: 95%->100 | 24.302, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2691 | 690025 | CT3 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C3 | Mon 07/09/15 | Fri 11/12/15 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 0%->100 | 29.212, 29.214 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2692 | 690023 | CT4 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C4 | Mon 07/09/15 | Fri 11/12/15 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 0%->100 | 23.003, 23.008, 29.273, 29.274 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2693 | 690036 | CT6 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C6 | Mon 07/09/15 | Fri 11/12/15 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/3/16: 0%->100 | 31.102 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2694 | 660009 | MBMS Enhancements | MBMS_enh | 1 | Rel-13 | S2 | Wed 03/12/14 | Mon 07/12/15 | 100% | SP-150516 |  | Nokia Networks, Curt Wong |  | . 3/3: WID tdoc number updated¦14/09/15: WID:SP-140883->SP-150516 |  | 66 | 34 |  |  | Wed 03/12/14 | Mon 14/09/15
2695 | 660010 | MBMS Enhancements TR Phase | FS_MBMS_enh_TR | 2 | Rel-13 | S2 | Wed 03/12/14 | Mon 14/09/15 | 100% | SP-150516 |  | Nokia Networks, Curt Wong |  | Acronym changed from "MBMS_enh-SA2TR". Mar15: 0->10%¦June2015: Compl:10%->50¦07/09/15: 50%->70. acronym changed from "MBMS_enh" to "MBMS_enh_TR"¦07/09/15: 70%->100¦14/09/15: WID:SP-140883->SP-150516 | 23.8xy | 66 | 34 |  |  | Wed 03/12/14 | Mon 14/09/15
2696 | 690046 | MBMS Enhancements | MBMS_enh_St2 | 2 | Rel-13 | S2 | Mon 10/08/15 | Wed 16/09/15 | 100% | SP-150520 |  | Nokia Networks, Curt Wong |  | SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_ | 23.246, 23.468 | 69 | 35 |  |  | Wed 16/09/15 | Wed 14/10/15
2697 | 700006 | CT aspects of MBMS Enhancements | MBMS_enh-CT | 2 | Rel-13 | C3 | Mon 09/11/15 | Mon 07/12/15 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  |  |  | 70 | 36 |  |  | Mon 07/12/15 | NA
2698 | 700035 | CT3 aspects of MBMS enhancements | MBMS_enh-CT | 3 | Rel-13 | C3 | Mon 09/11/15 | Mon 07/12/15 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  | 8/12/15: 0%->100 | 29.061, 29.468 | 70 | 36 |  |  | Mon 07/12/15 | Tue 08/12/15
2699 | 700007 | CT4 aspects of MBMS enhancements | MBMS_enh-CT | 3 | Rel-13 | C4 | Mon 09/11/15 | Mon 07/12/15 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  |  | 29.274, 23.008, 29.230 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/12/15
2700 | 660011 | Deleted (not approved) - MBMS Enhancements - Stage 2 | MBMS_enh_TS | 2 | Rel-13 | S2 | Fri 13/03/15 | Fri 13/03/15 | 100% | SP-140883 |  | Rainer Liebhart |  | Commented during RAN#67 that it should have never beeen here. 07/09/15: "undeleted", acronym changed from "MBMS_enh-del" to "MBMS_enh_TS". 14/10/15: SP-140883 was never approved so this line should have never appeared in the WP. | 23.246, 23.468 | 66 | 34 | SP-69 |  | Wed 03/12/14 | Wed 16/09/15
2701 | 690002 | EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 1 | Rel-13 | C4 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
2702 | 690026 | CT3 aspects for EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 2 | Rel-13 | C3 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM | 7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100 | 29.212, 29.213 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/12/15
2703 | 690027 | CT4 aspects for EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 2 | Rel-13 | C4 | Mon 07/09/15 | Fri 18/12/15 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM | 7/12/15: 95%->100 | 29.274, 29.274, 29.275, 29.282, 29.273, 29.230, 23.008, 29.273 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2704 | 700008 | Diameter Message Priority | DiaPri | 1 | Rel-13 | C4 | Mon 02/11/15 | Thu 16/06/16 | 100% | CP-150613 |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | NA
2705 | 700009 | CT3 aspects of DiaPri | DiaPri | 2 | Rel-13 | C3 | Mon 02/11/15 | Fri 11/03/16 | 100% | CP-150613 |  | Intel, Vivek Gupta |  | ES in CP-150645¦7/3/16: 65%->100 | 29.153, 29.154, 29.201, 29.212, 29.213, 29.214, 29.215, 29.217, 29.219 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
2706 | 700010 | CT4 aspects of DiaPri | DiaPri | 2 | Rel-13 | C4 | Mon 02/11/15 | Fri 11/03/16 | 100% | CP-150613 |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com | ES in CP-150622¦7/3/16: 70%->100 | 29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.338, 29.344, 29.345 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
2707 | 710044 | (IETF) Diameter Routing Message Priority (draft-ietf-dime-drmp) | DiaPri | 2 | Rel-13 | C4-IETF | Tue 08/12/15 | Thu 16/06/16 | 100% | 7/3/16:introducedbyIETFinputs |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com | 02/2016: publication requested¦2/12/16: 85%->100; 9/4/21: RFC 7944 added; | 29.227, 29.272, 29.273, 29.229; RFC 7944 | 71 | 36 |  |  | Mon 07/03/16 | Fri 09/04/21
2708 | 680059 | Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC | 1 | Rel-13 | R1 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151044 | - | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2709 | 680159 | Core part: Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC-Core | 2 | Rel-13 | R1,R2,R3 | Thu 15/10/15 | Tue 15/12/15 | 100% | RP-151880 | RP-151564 | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2710 | 680259 | Perf. part: Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151880 | RP-151564 | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Stat Rep: -->RP-151564¦1/1/16: Compl:0%->80%¦1/1/16: WID: RP-151044->RP-151880 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2711 | 680060 | Licensed-Assisted Access using LTE | LTE_LAA | 1 | Rel-13 | R1 | Mon 15/06/15 | Fri 15/09/17 | 99% | RP-151045 | - | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2712 | 680160 | Core part: Licensed-Assisted Access using LTE | LTE_LAA-Core | 2 | Rel-13 | R1 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151045 | RP-151390 | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-1513901/1/16: Compl:25%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2713 | 680260 | Perf. part: Licensed-Assisted Access using LTE | LTE_LAA-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Thu 15/12/16 | 100% | RP-151045 |  | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Stat Rep: -->RP-15139022/3/16: Compl:0%->33%¦1/7/16: Compl:3¦26/9/16: Compl:50%->90%¦20/12/16: Compl:90%->100%¦20/12/16: Stat Rep: RP-151390-> |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 20/12/16
2714 | 700067 | UE Conformance Test Aspects - Licensed-Assisted Access using LTE | LTE_LAA-UEConTest | 2 | Rel-13 | R5 | Tue 15/12/15 | Fri 15/09/17 | 100% | RP-162376 |  | Motorola Mobility |  | ¦22/3/16: Compl:0%->5%1/7/16: Compl:5%->8%26/9/16: Compl:8%->15%¦20/21/3/17: Com ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
2715 | 680061 | Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO | 1 | Rel-13 | R1 | Mon 15/06/15 | Fri 14/12/18 | 99% | RP-151085 | - | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2716 | 680161 | Core part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO-Core | 2 | Rel-13 | R1 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151085 | RP-151565 | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-151565 1/1/16: Compl:25%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2717 | 680261 | Perf. part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Thu 15/09/16 | 100% | RP-151085 | RP-151565 | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Stat Rep: -->RP-151565 ¦1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->35%;26/9/16: Compl:70%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Mon 26/09/16
2718 | 770062 | UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE | LTE_EBF_FDMIMO-UEConTest | 2 | Rel-13 | R5 | Fri 15/09/17 | Fri 14/12/18 | 100% | RP-172651 |  | Ericsson |  | ¦8/1/18: Compl:0%->5%¦27/3/18: Compl:5%->10%¦27/6/18: CD:Fri 15/06/18-; 26/3/20: 10%->100 |  | 77 | 39 |  |  | Tue 19/09/17 | Thu 26/03/20
2719 | 680062 | L2/L3 Downlink enhancements for UMTS | UTRA_EDL_L23 | 1 | Rel-13 | R2 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151043 | - | Huawei |  | no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2720 | 680162 | Core part: L2/L3 Downlink enhancements for UMTS | UTRA_EDL_L23-Core | 2 | Rel-13 | R2 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-152184 | RP-151238 | Huawei |  | no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ¦ |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2721 | 680064 | Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM | 1 | Rel-13 | R2 | Mon 15/06/15 | Thu 15/09/16 | 100% | RP-151110 | - | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2722 | 680164 | Core part: Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-Core | 2 | Rel-13 | R2 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151110 | RP-151237 | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151237 1/1/16: Compl:30%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2723 | 680264 | Perf. part: Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151110 | RP-151237 | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Stat Rep: -->RP-1512371/1/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2724 | 710069 | UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-161681 | - | Huawei |  | testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16 |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2725 | 680065 | Extension of Dual Connectivity in E-UTRAN | LTE_dualC_ext | 1 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151008 | - | Samsung |  | no Perf. part¦follow-up WI of REL-13 SI FS_LTE_dualC_ext; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2726 | 680165 | Core part: Extension of Dual Connectivity in E-UTRAN | LTE_dualC_ext-Core | 2 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151798 | RP-151214 | Samsung |  | no Perf. part¦follow-up WI of REL-13 SI FS_LTE_dualC_ext¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151214¦1/1/16: Compl:3 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2727 | 680067 | RAN sharing enhancements for UMTS | RSE_UTRA_GUSH | 1 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151086 | - | Huawei |  | no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2728 | 680167 | Core part: RAN sharing enhancements for UMTS | RSE_UTRA_GUSH-Core | 2 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151251 | RP-151239 | Huawei |  | no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE¦29/09/15: Compl:0%->30% 29/09/15: WID: RP-151086->RP-151251 29/09/15: Stat Rep: -->RP-151239 ¦ |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2729 | 680071 | Interference mitigation for downlink control channels of LTE | LTE_IM_DLCCH | 1 | Rel-13 | R4 | Mon 15/06/15 | Fri 14/09/18 | 99% | RP-151107 | - | Intel |  | only Perf. part, no Core part; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2730 | 680271 | Perf. part: Interference mitigation for downlink control channels of LTE | LTE_IM_DLCCH-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Wed 15/06/16 | 100% | RP-160908 | RP-151301 | Intel |  | only Perf. part, no Core part¦29/09/15: CD:Tue 15/03/16->Wed 15/06/16 29/09/15: Stat Rep: -->RP-1513011/1/16: Compl:0%->40%22/3/16: Compl:40%->70% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
2731 | 750051 | UE Conformance Test Aspects - Interference Mitigation for Downlink Control Channels of LTE | LTE_IM_DLCCH-UEConTest | 2 | Rel-13 | R5 | Wed 15/03/17 | Fri 14/09/18 | 100% | RP-180176 |  | Intel |  | tested: REL-13 LTE_IM_DLCCH-Perf (note: WI had no Core part);19/6/171 8/1/18: C 27/3/18 ;¦26/3/19: 84%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 26/03/19
2732 | 690062 | Network-Assisted Interference Cancellation and Suppression for UMTS | UTRA_NAICS | 1 | Rel-13 | R1 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151577 | - | Huawei |  | no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2733 | 690162 | Core part: Network-Assisted Interference Cancellation and Suppression for UMTS | UTRA_NAICS-Core | 2 | Rel-13 | R1 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151879 | - | Huawei |  | no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS ¦1/1/16: Compl:0%->100% ¦1/1/16: WID: RP-151577->RP-151879 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2734 | 690064 | Dual Carrier HSUPA Enhancements for UTRAN CS | DC_HSUPA_CS | 1 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151607 | - | Nokia Networks |  | no Perf. part¦compare REL-13 WI HSUPA_DB_MC |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2735 | 690164 | Core part: Dual Carrier HSUPA Enhancements for UTRAN CS | DC_HSUPA_CS-Core | 2 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151780 | - | Nokia Networks |  | no Perf. part¦compare REL-13 WI HSUPA_DB_MC 1/1/16: Compl:0%->100% 1/1/16: WID: RP-151607->RP-151780 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2736 | 690065 | Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2 | 1 | Rel-13 | R2 | Mon 16/03/15 | Wed 15/03/17 | 100% | RP-151611 | - | CMCC |  | no Perf. part¦follow-up WI of REL-13 SI FS_LTE_eMDT2 |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2737 | 670042 | Study on further Enhancements of Minimization of Drive Tests for E-UTRAN | FS_LTE_eMDT2 | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/09/15 | 100% | RP-150472 | RP-151181 | CMCC |  | 03/07/15: Compl:0%->70% 03/07/15: Stat Rep: -->RP-150806 29/09/15: Compl:70%->100% 29/09/15: Stat Rep: RP-150806->RP-151181 | 36.88 | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
2738 | 690165 | Core part: Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2-Core | 2 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151611 | - | CMCC |  | no Perf. part¦follow-up WI of REL-13 SI FS_LTE_eMDT2¦1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2739 | 721000 | UE Conformance Test Aspects – Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2-UEConTest | 2 | Rel-13 | R5 | Wed 15/06/16 | Wed 15/03/17 | 100% | RP-161071 |  | Intel |  | tested REL-13 WI: LTE_eMDT2-Core26/9/16: Com;21/3/17: Compl:5%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
2740 | 690066 | LTE-WLAN RAN Level Integration supporting legacy WLAN | LTE_WLAN_radio_legacy | 1 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151615 | - | Alcatel-Lucent |  | no Perf. part¦compare REL-13 WI LTE_WLAN_radio |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2741 | 690166 | Core part: LTE-WLAN RAN Level Integration supporting legacy WLAN | LTE_WLAN_radio_legacy-Core | 2 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-160608 | - | Alcatel-Lucent |  | no Perf. part¦compare REL-13 WI LTE_WLAN_radio1/1/16: Compl:0%->95% 22/3/16: Compl:95%->100%¦28/7/16: 36.361 added; | 36.361 | 69 | 35 |  |  | Tue 29/09/15 | Thu 28/07/16
2742 | 690067 | Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh | 1 | Rel-13 | R2 | Tue 15/09/15 | Wed 15/03/17 | 100% | RP-151624 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2743 | 690167 | Core part: Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh-Core | 2 | Rel-13 | R2 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-160332 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh1/1/16: Compl:0%->100%1/1/16: WID: RP-151624->RP-15225122/3/16: WID: RP-152251->RP-160332 |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2744 | 690267 | Perf. part: Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh-Perf | 2 | Rel-13 | R4 | Tue 15/09/15 | Wed 15/06/16 | 100% | RP-160332 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh 1/1/16: Compl:0%->10% 1/1/16: WID: RP-151624->RP-152251¦22/3/16: Compl:10%->20%¦22/3/16: WID: RP-152251->RP-160332 28/7/16: 37.171 added¦28/7/16: 37.958 added; | 37.171; 37.958 | 69 | 35 |  |  | Tue 29/09/15 | Thu 28/07/16
2745 | 700011 | CT aspects of Indoor Positionning | UTRA_LTE_iPos_enh-CT | 2 | Rel-13 | C4 | Mon 12/10/15 | Mon 07/12/15 | 100% | CP-150612 |  | Ericsson, Jesús de Gregorio | jesus.de.gregorio@ericsson.com |  | 29.171, 29.172, 29.230, 29.002 | 70 | 36 |  |  | Mon 07/12/15 | NA
2746 | 700053 | CT4 aspects of Indoor Positionning | UTRA_LTE_iPos_enh-CT | 3 | Rel-13 | C4 | Mon 12/10/15 | Mon 07/12/15 | 100% | CP-150612 |  | Ericsson, Jesús de Gregorio | jesus.de.gregorio@ericsson.com | 8/12/15: 0%->100 | 29.171, 29.172, 29.230, 29.002 | 70 | 36 |  |  | Mon 07/12/15 | Tue 08/12/15
2747 | 720099 | UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS | UTRA_LTE_iPos_enh-UEConTest | 2 | Rel-13 | R5 | Wed 15/06/16 | Wed 15/03/17 | 100% | RP-170233 |  | NextNav |  | tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl: |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
2748 | 680063 | Power saving enhancements for UMTS | UTRA_SDATA_POWSAV | 1 | Rel-13 | R2 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151092 | - | Ericsson |  | no Perf. part¦follow-up WI of SI FS_UTRA_SDATA |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2749 | 680163 | Core part: Power saving enhancements for UMTS | UTRA_SDATA_POWSAV-Core | 2 | Rel-13 | R2 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151998 | RP-151291 | Ericsson |  | no Perf. part¦follow-up WI of SI FS_UTRA_SDATA 29/09/15: Compl:0%->25% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-151092->RP-151292 29/09/15: Stat Rep: -->RP-151291 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2750 | 700256 | Perf. Part: Power saving enhancements for UMTS | UTRA_SDATA_POWSAV-Perf | 2 | Rel-13 | R4 | Tue 15/12/15 | Tue 15/03/16 | 100% | RP-151998 |  | Ericsson |  | ¦22/3/16: Compl:0%->100% |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 22/03/16
2751 | 680073 | 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB | 1 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151042 | - | Etisalat |  | REL-independent from REL-9 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2752 | 680173 | Core part: 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB-Core | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151042 | RP-151207 | Etisalat |  | REL-independent from REL-9. Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13; | 36.893 | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2753 | 680273 | Perf. part: 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151042 | RP-151207 | Etisalat |  | REL-independent from REL-9 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2754 | 680075 | European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20 | LTE_CA_700EU_B20 | 1 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150861 | - | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2755 | 680175 | Core part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20 | LTE_CA_700EU_B20-Core | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151228 | RP-151232 | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it. Aug 15: TR numb added 29/09/15: Compl:0%->80% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13 | 36.895 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2756 | 680275 | Perf. part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20 | LTE_CA_700EU_B20-Perf | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151228 | RP-151232 | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2757 | 0 | Release 13 Features on Internet of Things (IoT) | - | 1 | Rel-13 | SP,RP,CP,GP | Thu 12/09/13 | Tue 12/05/15 | 100% | - | - |  |  | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
2758 | 620063 | Service Requirements Maintenance for Machine-Type Communications (MTC) | SRMMTC | 1 | Rel-13 | S1 | Tue 15/09/15 | Fri 10/06/16 | 100% | SP-130600 | - | KPN | toon.norp@tno.nl | SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13. | 22.368 | 62 | 32 |  |  | Tue 26/11/13 | Wed 03/09/14
2759 | 700012 | Cellular (Narrowband) Internet of Things | CIoT | 1 | Rel-13 |  | Tue 15/09/15 | Fri 15/12/17 | 100% | [6 empty] | 70 | 36 |  |  | Mon 07/12/15 | NA
2760 | 700016 | Stage 2 of CIoT | CIoT | 2 | Rel-13 | S2 | Mon 05/10/15 | Mon 05/10/15 | 100% | SP-150844 |  | Intel, Puneet Jain | puneet.jain@intel.com | 7/3/16: 0%->95 | 23.401, 23.682, 23.251 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
2761 | 700046 | Security Aspects of CIoT (aka NB-IoT) | CIoT | 2 | Rel-13 | S3 | Mon 02/11/15 | Fri 10/06/16 | 100% | SP-150844 |  | Tim Evans, Vodafone |  | 7/3/16: 0%->39¦19/9/16: 39%->100 | 33.401 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
2762 | 700013 | CT aspects of CIoT | CIoT-CT | 2 | Rel-13 | C1 | Mon 07/12/15 | Wed 15/06/16 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 11/6/16: WID:CP-150795->CP-160292 |  | 70 | 36 |  |  | Mon 07/12/15 | Sat 11/06/16
2763 | 700014 | CT1 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C1 | Mon 07/12/15 | Fri 11/03/16 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->35¦11/6/16: 35%->100¦11/6/16: WID:CP-150795->CP-160292 | 24.301, 24.008, 23.122 | 70 | 36 |  |  | Mon 07/12/15 | Sat 11/06/16
2764 | 700051 | CT3 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C3 | Mon 07/12/15 | Wed 15/06/16 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->90¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 90%->100 | 29.061, 29.212 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
2765 | 700015 | CT4 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C4 | Mon 07/12/15 | Wed 15/06/16 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->65¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 65%->100 | 29.272, 29.274, 23.008, 23.007, 29.128, 29.275, 29.230, 29.336, 29.281, 29.002, 29.303 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
2766 | 700052 | CT6 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C6 | Mon 07/12/15 | Wed 15/06/16 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 11/6/16: WID:CP-150795->CP-160292¦13/6/16: 0%->100 | 31.102 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
2767 | 720042 | Charging Aspects of CIoT | CIoT-CH | 2 | Rel-13 | S5 | Thu 12/05/16 | Mon 13/06/16 | 100% | SP-160395 |  | Gardella, Maryse (Nokia) | Gardella, Maryse (Nokia) | 32.25x¦13/6/16: 0%->100 | 32.25x, 32.240, 32.251, 32.274, 32.299, 32.298, 32.297 | 72 | 37 |  |  | Mon 13/06/16 | Mon 13/06/16
2768 | 690063 | RAN aspects of CIoT aka Narrowband Internet of Things (IOT) | NB_IOT | 2 | Rel-13 | R1 | Tue 15/09/15 | Thu 15/12/16 | 100% | RP-151621 | - | Vodafone |  | no Perf. part¦note: WI only stays in REL-13 because of PCG decision |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2769 | 690163 | Core part: Narrowband Internet of Things (IOT) | NB_IOT-Core | 3 | Rel-13 | R1 | Tue 15/09/15 | Wed 15/06/16 | 100% | RP-160933 | - | Vodafone |  | no Perf. part¦note: WI only stays in REL-13 because of PCG decision1/1/16: Compl:0%->25% 22/3/16: Compl:25%->75%;1/7/16: Com | 36.802 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/07/16
2770 | 700257 | Perf. part: Narrowband Internet of Things (IOT) | NB_IOT-Perf | 3 | Rel-13 | R4 | Tue 15/12/15 | Thu 15/12/16 | 100% | RP-162134 |  | Vodafone |  | 22/3/16: WID: RP-152284->RP-160656¦1/7/16: WID: RP-160656->RP-16093326/9/16: Compl:0%->60%26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦20/12/16: Compl:60%->100%¦20/12/16: WID: RP-160933->RP-162134 |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
2771 | 720043 | Management for NB-IoT | NB_IOT-OAM | 2 | Rel-13 | S5 | Thu 12/05/16 | Wed 15/06/16 | 100% | SP-160396 |  | Huawei, Kai ZHANG | kai.zhangkai@huawei.com | 13/6/16: 0%->100 | 28.657, 28.658, 28.659, 32.425 | 72 | 37 |  |  | Mon 13/06/16 | Mon 13/06/16
2772 | 710065 | UE Conformance Test Aspects - Narrowband Internet of Things (NB-IOT) | NB_IOT-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Fri 15/12/17 | 100% | RP-160047 |  | CMCC |  | testing REL-13 NB_IOT-Core1/7/16: Compl:0%->5%¦26/9¦20/12/1¦21/3/17: Compl: ; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
2773 | 690006 | Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM | 1 | Rel-13 | G1,G2 | Fri 25/09/15 | Thu 15/09/16 | 69% | GP-151039 |  | Marteen Sunberg, Ericsson | Marteen.Sunberg@Ericsson.com | 7/12/15: 0%->60 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2774 | 700003 | Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things Core part | CIoT_EC_GSM-Core | 2 | Rel-13 | G1,G2 | Fri 25/09/15 | Thu 12/05/16 | 100% | GP-151039 |  | Marteen Sunberg, Ericsson | Marteen.Sunberg@Ericsson.com | 7/12/15:created by MCC to distinguish core versus test parts. 2/3/16: FCD: 11/15->05/16, 40->90%¦13/6/16: 90%->100 |  | 70 | 36 |  |  | Mon 07/09/15 | Mon 13/06/16
2775 | 700004 | Test for CIoT_EC_GSM | CIoT_EC_GSM_GERAN3new | 2 | Rel-13 | G3 | Wed 11/11/15 | Thu 12/05/16 | 0% | GP-151149 |  | Sierra Wireless S.A | Marteen.Sunberg@Ericsson.com | 7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new |  | 70 | 36 |  |  | Mon 07/09/15 | Wed 02/03/16
2776 | 721201 | Perf. Part: Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM-Perf | 2 | Rel-13 | R6 | Wed 15/06/16 | Thu 15/09/16 | 100% | RP-160929 |  | Ericsson |  | related to GERAN REL-13 WI CIoT_EC_GSM-Core26/9/16: Compl:0%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
2777 | 720097 | MS Conformance Test Aspects - Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM-MSConTest | 2 | Rel-13 | R5 | Wed 15/06/16 | Thu 15/09/16 | 100% | RP-160753 |  | Ericsson |  | tested REL-13 WI: CIoT_EC_GSM-Core26/9/16: Compl |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
2778 | 690005 | Extended DRX cycle for Power Consumption | eDRX | 1 | Rel-13 | S2,R2,G2 | Wed 03/12/14 | Thu 15/09/16 | 93% | SP-150369 |  | Miguel Griot | mgriot@qti.qualcomm.com | June2015: WID:SP-150254->SP-150369 | 23.401, 23.060, 23.682, 23.271, 23.272 | 68 | 35 |  |  | Thu 18/06/15 | Thu 18/06/15
2779 | 660008 | Study on Extended DRX cycle for Power Consumption Optimization | FS_eDRX | 2 | Rel-13 | S2 | Wed 03/12/14 | Fri 11/12/15 | 100% | SP-140881 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | No Ran aspects yet. GERAN in FS_uPoD.29/1: TS number added Mar15: 0->30%¦June2015: Compl:30%->95, Exc S granted in SP-150352¦07/09/15: 95%->100 | 23.77 | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
2780 | 680052 | Stage 2 for Extended DRX cycle for Power Consumption | eDRX | 2 | Rel-13 | S2 | Mon 15/06/15 | Wed 16/12/15 | 100% | SP-150369 |  | Miguel Griot | mgriot@qti.qualcomm.com | June2015: WID:SP-150254->SP-150369¦07/09/15: 0%->95¦7/12/15: 95%->99 | 23.401, 23.060, 23.682, 23.271, 23.272 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/12/15
2781 | 690010 | CT aspects of extended DRX cycle | eDRX-CT | 2 | Rel-13 | ct | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
2782 | 690020 | CT1 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C1 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100 | 24.301, 24.008, 29.118 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2783 | 690030 | CT3 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C3 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541. FCD ->03/16. ES in CP-150723¦8/12/15: 0%->100 | 29.338, 23.007, 29.274, 29.060, 29.172 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/12/15
2784 | 690021 | CT4 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C4 | Mon 07/09/15 | Thu 17/12/15 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541¦7/12/15: 40%->100¦8/12/15: 100%->95¦8/3/16: 95%->100 | 29.212 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/03/16
2785 | 700034 | CT6 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C6 | Mon 07/09/15 | Fri 11/03/16 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100 |  | 70 | 36 |  |  | Mon 07/09/15 | Tue 08/03/16
2786 | 670057 | RAN enhancements for extended DRX in LTE | LTE_extDRX | 2 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150493 |  | Qualcomm |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
2787 | 670157 | Core part: RAN enhancements for extended DRX in LTE | LTE_extDRX-Core | 3 | Rel-13 | R2 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-151339 | RP-151338 | Qualcomm |  | 03/07/15: Compl:0%->15% 03/07/15: Stat Rep: ->RP-150798 29/09/15: Compl:15%->35% 29/09/15: WID: RP-150493->RP-151339 29/09/15: Stat Rep: RP-150798->RP-151338 ¦22/3/16: Compl:95%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
2788 | 710071 | UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE | LTE_extDRX-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-160602 | - | Qualcomm |  | testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2789 | 690001 | Extended DRX (eDRX) for GSM | eDRX_GSM | 2 | Rel-13 | G2,G1 | Fri 28/08/15 | Thu 12/05/16 | 44% | GPC150624 |  | John Diachina, Ericsson LM | John.Diachina@Ericsson.com | 07/09/15: 0%->40¦7/12/15: 40%->100 | 43.064, 44.018, 44.060, 45.008, 48.018, 43.022 | 69 | 35 |  |  | Wed 12/08/15 | Mon 07/12/15
2790 | 700001 | Core Part: Extended DRX (eDRX) for GSM | eDRX_GSM-Core | 3 | Rel-13 | G2,G1 | Fri 28/08/15 | Fri 20/11/15 | 100% | GPC150624 |  | John Diachina, Ericsson LM | John.Diachina@Ericsson.com | 7/12/15: created by MCC to distinguish Core versus test parts | 43.064, 44.018, 44.060, 45.008, 48.018, 43.022 | 70 | 36 |  |  | Wed 12/08/15 | Mon 07/12/15
2791 | 700002 | MS test: Extended DRX (eDRX) for GSM | eDRX_GSM_GERAN3new | 3 | Rel-13 | G3 | Mon 07/12/15 | Thu 12/05/16 | 15% | GP-151148 |  | Sierra Wireless S.A | John.Diachina@Ericsson.com | 7/12/15: created by GERAN. 2/3/16: G1,G2->G3. Acronym: eDRX_GSM-Test -> eDRX_GSM_GERAN3new (to conform to WID)¦0->15% |  | 70 | 36 |  |  | Wed 12/08/15 | Wed 02/03/16
2792 | 670027 | Optimizations to Support High Latency Communications | HLcom | 1 | Rel-13 | S2 | Fri 19/09/14 | Wed 16/12/15 | 100% | SP-150030 |  | Ericsson, Hans Rönneke | hans.ronneke(at)ericsson.com |  | 23.401, 23.060, 23.682 | 67 | 34 |  |  | Thu 05/03/15 | Thu 05/03/15
2793 | 650035 | Study on Optimizations to support High Latency communications | FS_HLcom | 2 | Rel-13 | S2 | Fri 19/09/14 | Wed 17/06/15 | 100% | SP-140635 | - | Ericsson | hans.ronneke@ericsson.com | Dec.14: 0->30%. Mar15: 70%¦June2015: Compl:70%->100 | New 23.709 | 65 | 33 |  |  | Tue 05/08/14 | Mon 15/06/15
2794 | 680005 | Optimizations to Support High Latency Communications | HLcom | 2 | Rel-13 | S2 | Thu 05/03/15 | Mon 15/06/15 | 100% | SP-150252 |  | Ericsson, Hans Rönneke | hans.ronneke(at)ericsson.com | June 2015: created by MCC as a result of the split of the one-line Feature into a several-lines Feature (now Stage 2 and Stage 3 aspects)¦June2015: Compl:0%->100. WID: SP-150030->SP-150252 | 23.401, 23.060, 23.682 | 67 | 34 |  |  | Mon 15/06/15 | Thu 18/06/15
2795 | 680015 | CT aspects of Optimizations to Support High Latency | HLcom-CT | 2 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150399 |  | Yong Yang, Ericsson | frank.yong.yang@ericsson.com | 07/09/15: 0%->80¦7/12/15: 80%->100 | 29.274, 29.060, 29.281, 23.008, 29.272, 29.230, 29.002, 29.336, 29.xyz | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2796 | 650033 | Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1 | 1 | Rel-13 | R1,R4,R2 | Fri 12/09/14 | Fri 15/09/17 | 99% | RP-141660 | - | Ericsson | johan.bergman@ericsson.com | Triggered by Rel-12 TR 36.888 Study on Provision of low-cost MTC UEs based on LTE (FS_LC_MTC_LTE) and Low cost & enhanced coverage MTC UE for LTE (LC_MTC_UE) | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
2797 | 650133 | Core part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Core | 2 | Rel-13 | R1,R2,R4 | Fri 12/09/14 | Tue 15/03/16 | 100% | RP-150492 | RP-151186 | Ericsson | johan.bergman@ericsson.com | 3/3/15: WID: RP-141865¦Stat Rep: -->RP-141785 1st Apr 15: Compl:10%->25% 1st Apr 15: WID: RP-141865->RP-150492 1st Apr 15: Stat Rep: RP-141785->RP-150495 03/07/15: Compl:25%->45% 03/07/15: Stat Rep: RP-150495->RP-150583 29/09/15: Compl:45%->65% 29/09/ | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.302, 36.306, 36.321, 36.331 | 65 | 33 |  |  | Mon 16/06/14 | Tue 22/03/16
2798 | 650233 | Perf. Part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Perf | 2 | Rel-13 | R4 | Fri 12/09/14 | Thu 15/12/16 | 100% | RP-150492 |  | Ericsson | johan.bergman@ericsson.com | ¦WID: RP-142043->RP-141865¦Stat Rep: -->RP-141785 1st Apr 15: WID: RP-141865->RP-150492 1st Apr 15: Stat Rep: RP-141785->RP-150495 03/07/15: Stat Rep: RP-150495->RP-150583 29/09/15: Stat Rep: RP-150583->RP-151186 ;26/9/16: Compl:70%-¦ | 36.101, 36.104, 36.133 | 65 | 33 |  |  | Mon 16/06/14 | Tue 20/12/16
2799 | 710067 | UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-UEConTest | 2 | Rel-13 | R5 | Tue 15/03/16 | Fri 15/09/17 | 100% | RP-171156 |  | Ericsson |  | testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
2800 | 690045 | EGPRS Access Security Enhancements in relation to Cellular IoT | EASE_EC_GSM | 1 | Rel-13 | S3 | Wed 16/09/15 | Fri 11/03/16 | 100% | SP-150462 |  | Vesa Torvinen, Ericsson |  | 7/12/15: 0%->5¦28/1/16: 33.420 added¦7/3/16: 5%->80¦11/6/16: 80%->98¦19/9/16: 98%->99¦21/3/17: 99%->100->99%¦7/6/17: 99%->100 | New 33.420 | 69 | 35 |  |  | Wed 16/09/15 | Wed 07/06/17
2801 | 640050 | Group based Enhancements | GROUPE | 1 | Rel-13 | S2,S3 | Wed 18/06/14 | Wed 16/12/15 | 100% | SP-140706 | - | Huawei | ZhangWanqiang@huawei.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
2802 | 640150 | TR for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | Wed 18/06/14 | Wed 18/03/15 | 100% | SP-140706 | - | Huawei, Wanqiang Zhang | ZhangWanqiang@huawei.com | Dec.14: 20->70%. Mar15: 90%¦June2015: Compl:90%->100 | New 23.769 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
2803 | 640250 | Stage 2 for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 17/06/15 | 100% | SP-140706 | - | Huawei | ZhangWanqiang@huawei.com | Mar15: 0->20%¦June2015: Compl:20%->100 | 23.682, TBD | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
2804 | 640350 | TR on Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | Wed 18/06/14 | Fri 12/06/15 | 100% | SP-140706 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. 3/3/15: 5->10%.¦June2015: Compl:10%->60¦11/12/15: 60%->100 | New 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2805 | 640450 | Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-140706 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -¦11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2806 | 680016 | CT aspects of Group based Enhancements | GROUPE-CT | 2 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 7/12/15: WID:CP-150240->CP-150816 | 24.008, 24.301, 29.468, 29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2807 | 680028 | CT1 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C1 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 07/09/15: 0%->15¦7/12/15: 15%->100¦7/12/15: WID:CP-150240->CP-150816 | 24.008, 24.301 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2808 | 680029 | DELETED: CT3 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 7/12/15: WID:CP-150240->CP-150816. CT3 task removed | 29.468 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2809 | 680030 | CT4 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 07/09/15: 0%->80¦7/12/15: 80%->100¦7/12/15: WID:CP-150240->CP-150816 | 29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2810 | 640049 | Monitoring Enhancements | MONTE | 1 | Rel-13 | S2,S3 | Wed 18/06/14 | Fri 11/03/16 | 100% | SP-140705 | - | Intel | puneet.jain@intel.com | Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added; | 32.278 | 64 | 33 |  |  | Fri 30/05/14 | Mon 05/10/15
2811 | 640149 | TR for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | Wed 17/09/14 | Wed 17/06/15 | 100% | SP-140705 | - | Intel, Puneet Jain | puneet.jain@intel.com | Dec.14: 25->85%. Mar15: 100% | New 23.789 | 64 | 33 |  |  | Fri 30/05/14 | Mon 05/10/15
2812 | 640249 | Stage 2 for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 17/06/15 | 100% | SP-140705 | - | Intel, Puneet Jain | puneet.jain@intel.com | -¦June2015: Compl:0%->100 | 23.682, TBD | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
2813 | 640349 | TR on Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | Wed 18/06/14 | Fri 12/06/15 | 100% | SP-140705 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs.3/3/15: 5->10%.¦June2015: Compl:10%->15¦11/12/15: 15%->100 | New 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2814 | 640449 | Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-140705 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -¦11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2815 | 690044 | Charging aspects of MONTE | MONTE-CH | 2 | Rel-13 | S5 | Wed 16/09/15 | Fri 11/03/16 | 100% | SP-150571 | - | Huawei(Li Li, jasmine.li@huawei.com) | jasmine.li@huawei.com | 7/10/15: acronym changed from "MONTE" to "MONTE-CH"¦7/12/15: 0%->50. ES in SP-150709 (wrong UID in the ES)¦7/3/16: 25%->100 | 32.27x, 32.240, 32.299, 32.298 | 69 | 35 |  |  | Fri 30/05/14 | Mon 07/03/16
2816 | 680011 | Monitoring Enhancements CT aspects | MONTE-CT | 2 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 14/09/15: WID:CP-150396->CP-150422 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
2817 | 680025 | CT1 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C1 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 07/09/15: 0%->95¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 95%->100 | 24.301, 24.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2818 | 680026 | CT3 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 07/09/15: 0%->100¦14/09/15: WID:CP-150396->CP-150422 | 29.214, 29.213, 29.201 | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
2819 | 680027 | CT4 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 61907/09/15: 0%->50¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 50%->85. FCD -> 03/16, ES in CP-150619¦7/3/16: 85%->100 | New 29.128, 29.272, 29.002, 29.336, 29.230, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2820 | 640046 | Dedicated Core Networks | DECOR | 1 | Rel-13 | S2 | Wed 18/06/14 | Fri 11/03/16 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | 06/15: WID: SP-140707-> SP-150249 | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
2821 | 640146 | TR for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | Wed 18/06/14 | Fri 12/12/14 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Dec.14: 30->100%. 06/15: WID: SP-140707-> SP-150249 | New 23.707 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
2822 | 640246 | Stage 2 for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 18/03/15 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Mar15: 0->70%¦June2015: Compl:70%->100, WID: SP-140707-> SP-150249 | 23.060, 23.401, 23.236 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
2823 | 690004 | CT aspects of Dedicated Core Networks | DECOR-CT | 2 | Rel-13 | ct | Thu 25/06/15 | Fri 11/03/16 | 100% | CP-150423 |  | Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com) | Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com) |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
2824 | 690014 | CT1 aspects for Dedicated Core Networks CT aspects | DECOR-CT | 3 | Rel-13 | C1 | Mon 07/09/15 | Thu 17/12/15 | 100% | CP-150423 |  | Huawei |  | 7/12/15: 0%->100 | 24.301, 24.008 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
2825 | 690013 | CT4 aspects for Dedicated Core Networks CT aspects | DECOR-CT | 3 | Rel-13 | C4 | Thu 25/06/15 | Fri 11/03/16 | 100% | CP-150423 |  |  |  | 7/12/15: 70%->90. FCD -> 03/16, ES CP-150617¦7/3/16: 90%->100 | 29.274, 29.060, 23.003, 29.272, 29.002, 29.305, 23.008, 29.230, 29.303, 23.007 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
2826 | 680066 | Dedicated Core Networks RAN Aspects | DECOR-UTRA_LTE | 2 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151048 | - | Ericsson |  | no Perf. part¦note: DECOR is a REL-13 SA2 WI; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2827 | 680166 | Core part: Dedicated Core Networks | DECOR-UTRA_LTE-Core | 3 | Rel-13 | R3 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151048 | RP-151290 | Ericsson |  | no Perf. part¦note: DECOR is a REL-13 SA2 WI¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-1512901/1/16: Compl:30%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2828 | 610030 | Service Exposure and Enablement Support | SEES | 1 | Rel-13 | S1 | Thu 12/09/13 | Wed 17/09/14 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#62 completion 06/14=>09/14. Linked to Rel-12 Study TR 22.888 (FS_MTCe) and to Features Rel-11 SIMTC & Rel-12 MTCe and MOSAP | Stage 1 | 61 | 31 |  |  | Mon 26/08/13 | Tue 26/11/13
2829 | 610130 | TR on Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | Thu 12/09/13 | Wed 18/06/14 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements) | New 22.853 | 61 | 31 |  |  | Mon 26/08/13 | Tue 27/05/14
2830 | 610230 | Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | Thu 12/09/13 | Wed 17/09/14 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#65 completed | 22.101, 22.115, 22.368, TBD | 61 | 31 |  |  | Mon 26/08/13 | Thu 28/08/14
2831 | 640048 | Architecture Enhancements for Service capability Exposure | AESE | 1 | Rel-13 | S2,S3 | Wed 18/06/14 | Fri 11/03/16 | 100% | SP-140704 | - | Intel | puneet.jain@intel.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
2832 | 640148 | TR for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | Wed 18/06/14 | Wed 18/03/15 | 100% | SP-140704 | - | Intel, Puneet Jain | puneet.jain@intel.com | Dec.14: 30->65%. Mar15: 75%¦June2015: Compl:75%->100 | New 23.708 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
2833 | 640248 | Stage 2 for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | Mon 23/06/14 | Wed 17/06/15 | 100% | SP-140704 | - | Intel, Puneet Jain | puneet.jain@intel.com | -¦June2015: Compl:0%->100 | 23.682, 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
2834 | 640348 | TR on Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | Mon 23/06/14 | Wed 17/06/15 | 100% | SP-140704 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. Dec.14: 0->40%. 3/3/15: 45%.¦June2015: Compl:45%->60¦11/12/15: 60%->100 | New 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2835 | 640448 | Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | Mon 23/06/14 | Wed 16/09/15 | 100% | SP-140704 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -¦11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
2836 | 680001 | CT aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 2 | Rel-13 | C3 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150576 |  | Yizhuang Wu, Huawei | wuyizhuang@huawei.com | 14/09/15: WID:CP-150402->CP-150487->CP-150576 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
2837 | 680023 | CT3 aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 3 | Rel-13 | C3 | Mon 15/06/15 | Fri 11/03/16 | 100% | CP-150576 |  | Yizhuang Wu, Huawei. FCD+3, ES in 642 | wuyizhuang@huawei.com | 07/09/15: 0%->35¦14/09/15: WID:CP-150402->CP-150487->CP-150576¦7/12/15: 35%->90¦7/3/16: 90%->100 | 29.154 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
2838 | 680024 | CT4 aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 3 | Rel-13 | C4 | Mon 15/06/15 | Wed 16/12/15 | 100% | CP-150576 |  | Yizhuang Wu, Huawei | wuyizhuang@huawei.com | 07/09/15: 0%->40¦14/09/15: WID:CP-150402->CP-150487->CP-150576¦7/12/15: 40%->100 | 29.201, 29.336, 29.230, 29.272, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2839 | 621000 | Rel-13 LTE Carrier Aggregation | LTE_CA_Rel13 | 1 | Rel-13 | R4 | Mon 09/12/13 | Fri 14/12/18 | 95% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
2840 | 690080 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2841 | 690180 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2842 | 690280 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2843 | 690081 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2844 | 690181 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2845 | 690281 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
2846 | 620023 | LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27 | 2 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 30% | RP-140120 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
2847 | 620123 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Core | 3 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 30% | RP-140120 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
2848 | 620223 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Perf | 3 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 30% | RP-140120 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
2849 | 620032 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27 | 2 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 25% | RP-131754 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
2850 | 620132 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Core | 3 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 25% | RP-131754 | RP-151131 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 18/06/15->Mon 15/06/15¦Compl:25%->25%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
2851 | 620232 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Perf | 3 | Rel-13 | R4 | Mon 09/12/13 | Tue 15/12/15 | 25% | RP-131754 | RP-151131 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 18/06/15->Mon 15/06/15¦Compl:25%->25%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
2852 | 630033 | LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22 | 2 | Rel-13 | R4 | Thu 06/03/14 | Mon 15/06/15 | 100% | RP-140094 | - | Orange, Ericsson | erika.tejedor@ericsson.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2853 | 630133 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Core | 3 | Rel-13 | R4 | Thu 06/03/14 | Mon 15/06/15 | 100% | RP-140094 | RP-150536 | Orange, Ericsson | erika.tejedor@ericsson.com | CD:Thu 11/12/14->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 03/07/15: Compl:10%->100% 03/07/15: Stat Rep: RP-141732->RP-150536 | 36.101, 36.104, 36.133, generic 36.851 (2 Band CA with 1UL), | 63 | 32 |  |  | Mon 10/03/14 | Thu 18/06/15
2854 | 630233 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Perf | 3 | Rel-13 | R4 | Tue 11/03/14 | Mon 15/06/15 | 100% | RP-140094 | RP-150536 | Orange, Ericsson | erika.tejedor@ericsson.com | CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-141732->RP-150536 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Thu 18/06/15
2855 | 640022 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12 | 2 | Rel-13 | R4 | Wed 18/06/14 | Mon 15/06/15 | 100% | RP-141232 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Sun 21/09/14
2856 | 640122 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Core | 3 | Rel-13 | R4 | Wed 18/06/14 | Mon 15/06/15 | 100% | RP-141232 | RP-150536 | U.S. Cellular | sebastian.thalanany@uscellular.com | CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->40%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:40%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, 36.141, 36.307, generic new Rel-13 TR36.8xy [similar to Rel-12 36.853 (3 Band CA with 1UL)] | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2857 | 640222 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Perf | 3 | Rel-13 | R4 | Wed 18/06/14 | Mon 15/06/15 | 100% | RP-141232 | RP-150536 | U.S. Cellular | sebastian.thalanany@uscellular.com | CD:Thu 18/06/15->Mon 15/06/15¦Compl:0%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2858 | 640025 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8 | 2 | Rel-13 | R4 | Mon 16/06/14 | Mon 15/06/15 | 100% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2859 | 640125 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Core | 3 | Rel-13 | R4 | Mon 16/06/14 | Mon 15/06/15 | 100% | RP-150874 | RP-150536 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | ¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:60%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2860 | 640225 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Perf | 3 | Rel-13 | R4 | Wed 18/06/14 | Mon 15/06/15 | 100% | RP-150874 | RP-150536 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | ¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2861 | 640032 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42 | 2 | Rel-13 | R4 | Mon 16/06/14 | Mon 15/06/15 | 100% | RP-140974 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2862 | 640132 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Core | 3 | Rel-13 | R4 | Mon 16/06/14 | Mon 15/06/15 | 100% | RP-140974 | RP-150536 | Huawei | leo.liuye@huawei.com | CD:Thu 11/12/14->Sun 15/03/15¦Compl:30%->50%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:50%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-15 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2863 | 640232 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Perf | 3 | Rel-13 | R4 | Wed 18/06/14 | Mon 15/06/15 | 100% | RP-140974 | RP-150536 | Huawei | leo.liuye@huawei.com | CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2864 | 650037 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141129 | - | Nokia Networks | iwajlo.angelow@nsn.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2865 | 650137 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150717 | RP-150536 | Nokia Networks | iwajlo.angelow@nsn.com | CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->90%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141129->RP-150717 03/07/15: Stat Rep: RP-150013->RP-15 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2866 | 650237 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150717 | RP-150536 | Nokia Networks | iwajlo.angelow@nsn.com | CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->90%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141129->RP-150717 03/07/15: Stat Rep: RP-150013->RP-15 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2867 | 650038 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141145 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2868 | 650138 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141145 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2869 | 650238 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141145 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2870 | 650039 | LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141146 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2871 | 650139 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141146 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->35%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2872 | 650239 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141146 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2873 | 650040 | LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40 | 2 | Rel-13 | R4 | Fri 12/09/14 | Tue 15/12/15 | 100% | RP-141168 | - | Ericsson | imadur.rahman@ericsson.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2874 | 650140 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40-Core | 3 | Rel-13 | R4 | Fri 12/09/14 | Tue 15/12/15 | 100% | RP-141168 | RP-151131 | Ericsson | imadur.rahman@ericsson.com | CD:Wed 11/03/15->Sun 15/03/15¦Compl:0%->30%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:30%->70% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013-> | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2875 | 650240 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Tue 15/12/15 | 100% | RP-141168 | RP-151131 | Ericsson | imadur.rahman@ericsson.com | CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-1 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2876 | 650041 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40 | 2 | Rel-13 | R4 | Mon 15/09/14 | Tue 15/12/15 | 100% | RP-141312 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2877 | 650141 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Tue 15/12/15 | 100% | RP-141312 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2878 | 650241 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Tue 15/12/15 | 100% | RP-141312 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
2879 | 650042 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141674 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2880 | 650142 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150832 | RP-150536 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2881 | 650242 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150832 | RP-150536 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2882 | 650043 | LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141336 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2883 | 650143 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-142007 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | ¦WID: RP-142043->RP-142007¦Stat Rep: -->RP-141732 1st Apr 15: Compl:75%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2884 | 650243 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-142007 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | ¦WID: RP-142043->RP-142007¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2885 | 650044 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141337 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2886 | 650144 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150318 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->75% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:75%->100% 03/07/1 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2887 | 650244 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150318 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2888 | 650045 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40 | 2 | Rel-13 | R4 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-141675 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2889 | 650145 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40-Core | 3 | Rel-13 | R4 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-150285 | RP-150536 | SK Telecom | haesung.park@sk.com | ¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2890 | 650245 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-150285 | RP-150536 | SK Telecom | haesung.park@sk.com | ¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2891 | 650047 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141677 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 3DL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2892 | 650147 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-151027 | RP-150536 | CATT | Yuexia Song (songyuexia@catt.cn) | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Sta | 36.101, 36.104, 36.133, New 36.833-5-42 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2893 | 650247 | Perf. Part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-151027 | RP-150536 | CATT | Yuexia Song (songyuexia@catt.cn) | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Stat | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2894 | 650049 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41 | 2 | Rel-13 | R4 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-141290 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2895 | 650149 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141845 | RP-150536 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2896 | 650249 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Perf | 3 | Rel-13 | R4 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-141845 | RP-150536 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2897 | 650051 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141655 | - | Samsung | xutao.zhou@samsung.com | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2898 | 650151 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141655 | RP-150536 | Samsung | xutao.zhou@samsung.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2899 | 650251 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141655 | RP-150536 | Samsung | xutao.zhou@samsung.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2900 | 650053 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29 | 2 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141667 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2901 | 650153 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Core | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141667 | RP-150536 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New 36.8xy (inter-band CA 2DL/1UL (introduce CA_B5-B29), New 36.8xz (inter-band CA 3DL/1UL) | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2902 | 650253 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Perf | 3 | Rel-13 | R4 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141667 | RP-150536 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
2903 | 660072 | LTE Carrier Aggregation Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C | 2 | Rel-13 |  | Mon 15/12/14 | Fri 14/09/18 | 100% | RP-142286 |  | Nokia Networks | Nokia | FCD: 06/16->12/15, Rel-14?->Rel-13 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
2904 | 660172 | Core part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C-Core | 3 | Rel-13 | R1 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151984 | RP-151285 | Nokia Networks | Nokia | FCD: 06/16->12/15, Rel-14?->Rel-13 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: Compl:10%->40% 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Compl:4 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2905 | 660272 | Perf. part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Wed 15/06/16 | 100% | RP-151984 | RP-151285 | Nokia Networks | Nokia | 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Stat Rep: RP-150769->RP-151285¦22/3/16: ; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/07/16
2906 | 730074 | UE Conformance Test Aspects - LTE Carrier Aggregation Enhancement Beyond 5 Carriers: PUCCH on Scell | LTE_CA_enh_b5C_PUCCH-UEConTest | 3 | Rel-13 | R5 | Thu 15/09/16 | Fri 14/09/18 | 100% | RP-192558 |  | Huawei |  | ¦20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%¦19/9/17: Compl:8%->15%¦8/1/18: 27/3/18; 14/1/20: WID:RP-171764->RP-192558; 14/1/20: 20%->100 |  | 66 |  |  |  | Mon 26/09/16 | Tue 14/01/20
2907 | 660080 | HSPA Dual-Band UL carrier aggregation | HSUPA_DB_MC | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142237 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
2908 | 660180 | Core part: HSPA Dual-Band UL carrier aggregation | HSUPA_DB_MC-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151852 | RP-151281 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Compl:10%->40% 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150761->RP-151281¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2909 | 660280 | Perf. part: HSPA Dual-Band UL carrier aggregation | HSUPA_DB_MC-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-151852 | RP-151281 | Qualcomm | Qualcomm | 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Stat Rep: RP-150761->RP-1512811/1/16: Compl:0%->90% ¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2910 | 660081 | LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26 | LTE_CA_B25_B26 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142020 |  | Sprint | Sprint |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2911 | 660181 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26 | LTE_CA_B25_B26-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150115 | RP-150536 | Sprint | Sprint | 1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2912 | 660281 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26 | LTE_CA_B25_B26-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150115 | RP-150536 | Sprint | Sprint | 1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2913 | 660082 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41 | LTE_CA_B3_B41 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142239 |  | China Telecom | China Telecom |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2914 | 660182 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41 | LTE_CA_B3_B41-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151446 | RP-151131 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2915 | 660282 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41 | LTE_CA_B3_B41-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151446 | RP-151131 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2916 | 660083 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-141777 |  | China Unicom | China Unicom |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2917 | 660183 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-141777 | RP-151131 | China Unicom | China Unicom | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2918 | 660283 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-141777 | RP-151131 | China Unicom | China Unicom | 03/07/15: Compl:0%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2919 | 660084 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-141791 |  | NTT DOCOMO | NTT DOCOMO |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2920 | 660184 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150639 | RP-151131 | NTT DOCOMO | NTT DOCOMO | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2921 | 660284 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150639 | RP-151131 | NTT DOCOMO | NTT DOCOMO | 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2922 | 660085 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141792 |  | NTT DOCOMO | NTT DOCOMO |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2923 | 660185 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150640 | RP-150536 | NTT DOCOMO | NTT DOCOMO | 1st Apr 15: Compl:0%->90% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2924 | 660285 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150640 | RP-150536 | NTT DOCOMO | NTT DOCOMO | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2925 | 660086 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-141802 |  | ZTE | ZTE |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2926 | 660186 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150614 | RP-151131 | ZTE | ZTE | 1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2927 | 660286 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150614 | RP-151131 | ZTE | ZTE | 1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2928 | 660087 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-141826 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2929 | 660187 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-150447 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2930 | 660287 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-150447 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2931 | 660088 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_Bwset | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141881 |  | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7 |  | 66 | 34 |  |  | Mon 12/01/15 | Wed 18/03/15
2932 | 660188 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_Bwset-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141881 | RP-150536 | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7-Core 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2933 | 660288 | Perf. Part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_BWset-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141881 | RP-150536 | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7-Perf 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2934 | 660089 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141882 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2935 | 660189 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141882 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2936 | 660289 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-141882 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2937 | 660090 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-141946 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2938 | 660190 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151258 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2939 | 660290 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151258 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2940 | 660091 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-141947 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2941 | 660191 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151259 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2942 | 660291 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151259 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2943 | 660092 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-141949 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2944 | 660192 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151261 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->95% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2945 | 660292 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-151261 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->90% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2946 | 660093 | LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142013 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2947 | 660193 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142013 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->95% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2948 | 660293 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142013 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2949 | 660094 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142038 |  | Nokia Networks | Nokia Networks |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2950 | 660194 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150719 | RP-150536 | Nokia Networks | Nokia Networks | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2951 | 660294 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150719 | RP-150536 | Nokia Networks | Nokia Networks | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2952 | 660095 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-142193 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2953 | 660195 | Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-142193 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2954 | 660295 | Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 40% | RP-142193 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2955 | 660096 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142194 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2956 | 660196 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142194 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/ |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2957 | 660296 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-142194 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2958 | 660097 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142206 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2959 | 660197 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150676 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->60% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2960 | 660297 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150676 | RP-151131 | Huawei | Huawei | 1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2961 | 660098 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142207 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2962 | 660198 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-151071 | RP-150536 | Huawei | Huawei | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2963 | 660298 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-151071 | RP-150536 | Huawei | Huawei | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2964 | 660099 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142208 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2965 | 660199 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150234 | RP-150536 | Huawei | Huawei | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2966 | 660299 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150234 | RP-150536 | Huawei | Huawei | 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2967 | 661000 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142209 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2968 | 661100 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142209 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:40%->50% 29/09/15: CD:Tue 1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2969 | 661200 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142209 | RP-151131 | Huawei | Huawei | 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2970 | 661001 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142238 |  | Intel | Intel |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2971 | 661101 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142238 | RP-150536 | Intel | Intel | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2972 | 661201 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142238 | RP-150536 | Intel | Intel | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2973 | 661002 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28 | 2 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142244 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2974 | 661102 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142244 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2975 | 661202 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-142244 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2976 | 661003 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142198 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2977 | 661103 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150449 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2978 | 661203 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150449 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2979 | 661004 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142199 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2980 | 661104 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150448 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2981 | 661204 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150448 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2982 | 661005 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142200 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2983 | 661105 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150450 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2984 | 661205 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150450 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2985 | 661006 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142201 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2986 | 661106 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150452 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2987 | 661206 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150452 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2988 | 661007 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142202 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2989 | 661107 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150451 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2990 | 661207 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150451 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2991 | 661008 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142203 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2992 | 661108 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150453 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2993 | 661208 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150453 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2994 | 661009 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142204 |  | Alcatel-Lucent | Alcatel-Lucent |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2995 | 661109 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142204 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2996 | 661209 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142204 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->25% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->75% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2997 | 661010 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13 | LTE_CA_2UL_R13-A1 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-141935 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
2998 | 661110 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13 | LTE_CA_2UL_R13-A1-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150678 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2999 | 661210 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13 | LTE_CA_2UL_R13-A1-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150678 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3000 | 661011 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13 | LTE_CA_2UL_R13-A2 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-141975 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
3001 | 661111 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13 | LTE_CA_2UL_R13-A2-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150408 | RP-151131 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3002 | 661211 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13 | LTE_CA_2UL_R13-A2-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150408 | RP-151131 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3003 | 661012 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13 | LTE_CA_2UL_R13-A3 | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142010 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
3004 | 661112 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13 | LTE_CA_2UL_R13-A3-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150409 | RP-151131 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3005 | 661212 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13 | LTE_CA_2UL_R13-A3-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150409 | RP-151131 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131¦ |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3006 | 661013 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL | LTE_CA_NC_B41_4DL | 2 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142022 |  | Alcatel-Lucent | Alcatel-Lucent |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
3007 | 661113 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL | LTE_CA_NC_B41_4DL-Core | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142022 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 15/03/16->Tue 15/12/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3008 | 661213 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL | LTE_CA_NC_B41_4DL-Perf | 3 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-142022 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 18/12/18->Tue 15/12/15 1st Apr 15: Stat Rep: -->RP-150013 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150536->RP-151131 ¦ |  | 66 | 31 |  |  | Sat 14/09/13 | Fri 01/01/16
3009 | 670065 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42 | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150121 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3010 | 670165 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150641 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3011 | 670265 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150641 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3012 | 670066 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42 | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150122 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3013 | 670166 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150642 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3014 | 670266 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150642 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3015 | 670067 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42 | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150123 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3016 | 670167 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150643 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3017 | 670267 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150643 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3018 | 670068 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42 | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150124 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3019 | 670168 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150644 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3020 | 670268 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150644 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3021 | 670069 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42 | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150125 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3022 | 670169 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150645 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3023 | 670269 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150645 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3024 | 670070 | Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150429 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3025 | 670170 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150429 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3026 | 670270 | Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150429 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3027 | 670071 | Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150430 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3028 | 670171 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150430 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3029 | 670271 | Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150430 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3030 | 670072 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150431 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3031 | 670172 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150431 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ¦1/122/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3032 | 670272 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150431 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 122/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3033 | 670073 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150432 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3034 | 670173 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150432 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-1511311/1/16:22/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3035 | 670273 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150432 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 1/1/1¦22/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3036 | 670074 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150433 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3037 | 670174 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150433 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3038 | 670274 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150433 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3039 | 670075 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150073 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3040 | 670175 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150660 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3041 | 670275 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150660 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3042 | 670076 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150074 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3043 | 670176 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150659 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3044 | 670276 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150659 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3045 | 670077 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150075 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3046 | 670177 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150658 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3047 | 670277 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150658 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3048 | 670078 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150434 |  | SK Telecom |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3049 | 670178 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151216 | RP-151131 | SK Telecom |  | 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3050 | 670278 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151216 | RP-151131 | SK Telecom |  | 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3051 | 670079 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150435 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3052 | 670179 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150435 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3053 | 670279 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150435 | RP-151131 | Nokia Networks |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3054 | 670080 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150436 |  | Huawei |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3055 | 670180 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150436 | RP-151131 | Huawei |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3056 | 670280 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150436 | RP-151131 | Huawei |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3057 | 670081 | LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD | LTE_CA_2UL_FDD_TDD | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150064 |  | KDDI |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3058 | 670181 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD | LTE_CA_2UL_FDD_TDD-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150064 | RP-151131 | KDDI |  | 03/07/15: Compl:0%->70% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:70%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3059 | 670281 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD | LTE_CA_2UL_FDD_TDD-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150064 | RP-151131 | KDDI |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3060 | 670082 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL_R13-A4 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150410 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3061 | 670182 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13 | LTE_CA_2UL_R13-A4-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150616 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3062 | 670282 | Perf. Part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13 | LTE_CA_2UL_R13-A4-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150616 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3063 | 670083 | LTE Advanced 3DL/2UL inter-band Carrier Aggregation | LTE_CA_3DL_2UL | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150479 |  | Nokia Corporation |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3064 | 670183 | Core part:LTE Advanced 3DL/2UL inter-band Carrier Aggregation | LTE_CA_3DL_2UL-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151230 | RP-151131 | Nokia Corporation |  | 03/07/15: Compl:0%->25% 03/07/15: CD:Tue 15/03/16->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3065 | 670283 | Perf. part:LTE Advanced 3DL/2UL inter-band Carrier Aggregation | LTE_CA_3DL_2UL-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151230 | RP-151131 | Nokia Corporation |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3066 | 670084 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_NC_B42_3DL | 2 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150246 |  | Huawei |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3067 | 670184 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_NC_B42_3DL-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150246 | RP-150536 | Huawei |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3068 | 670284 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_NC_B42_3DL-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Mon 15/06/15 | 100% | RP-150246 | RP-150536 | Huawei |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3069 | 670085 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 8 | LTE_CA_C_B8 | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150437 |  | CMCC |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3070 | 670185 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8 | LTE_CA_C_B8-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151177 | RP-151131 | CMCC |  | 03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3071 | 670285 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8 | LTE_CA_C_B8-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151177 | RP-151131 | CMCC |  | 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131¦ |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3072 | 670086 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_C_B42_4DL | 2 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150438 |  | CATT |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
3073 | 670186 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_C_B42_4DL-Core | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150438 | RP-151131 | CATT |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3074 | 670286 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_C_B42_4DL-Perf | 3 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150438 | RP-151131 | CATT |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3075 | 680077 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150609 | - | Softbank Mobile |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3076 | 680177 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150609 | RP-151131 | Softbank Mobile |  | 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3077 | 680277 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150609 | RP-151131 | Softbank Mobile |  | 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3078 | 680078 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 90% | RP-150864 | - | Ericsson |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3079 | 680178 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32-Core | 3 | Rel-14 | R4 | Mon 15/06/15 | Tue 15/03/16 | 90% | RP-150864 | RP-151131 | Ericsson |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-1511311/22/3/16: Compl:50%->90% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3080 | 680278 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32-Perf | 3 | Rel-14 | R4 | Mon 15/06/15 | Tue 15/03/16 | 90% | RP-150864 | RP-151131 | Ericsson |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->90% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3081 | 680079 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151012 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3082 | 680179 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151012 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3083 | 680279 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151012 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3084 | 680080 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151013 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3085 | 680180 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151013 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3086 | 680280 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151013 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3087 | 680081 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151014 | - | Nokia Networks |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3088 | 680181 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151014 | RP-151131 | Nokia Networks |  | 29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-1511311/1/16: Compl: |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3089 | 680281 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151014 | RP-151131 | Nokia Networks |  | 29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-151131¦1/1/16: Comp |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3090 | 680082 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151111 | - | KDDI |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3091 | 680182 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151111 | RP-151131 | KDDI |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3092 | 680282 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151111 | RP-151131 | KDDI |  | 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3093 | 680083 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151112 | - | KDDI |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3094 | 680183 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151158 | RP-151131 | KDDI |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3095 | 680283 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151158 | RP-151131 | KDDI |  | 29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131¦ |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3096 | 680085 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-150628 | - | Rogers Communications |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3097 | 680185 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-150628 | RP-151131 | Rogers Communications |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3098 | 680285 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-150628 | RP-151131 | Rogers Communications |  | 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3099 | 680086 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150632 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3100 | 680186 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150632 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3101 | 680286 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150632 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3102 | 680087 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150633 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3103 | 680187 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150633 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3104 | 680287 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150633 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3105 | 680088 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150634 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3106 | 680188 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150634 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3107 | 680288 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150634 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3108 | 680089 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150635 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3109 | 680189 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150635 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3110 | 680289 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150635 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3111 | 680090 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150636 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3112 | 680190 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150636 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3113 | 680290 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150636 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3114 | 680091 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150637 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3115 | 680191 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150637 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3116 | 680291 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150637 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3117 | 680092 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150638 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3118 | 680192 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150638 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3119 | 680292 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150638 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3120 | 680093 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150728 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3121 | 680193 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150728 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3122 | 680293 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150728 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3123 | 680094 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150731 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3124 | 680194 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150731 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3125 | 680294 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150731 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3126 | 680095 | LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150732 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3127 | 680195 | Core part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150732 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3128 | 680295 | Perf. part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150732 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3129 | 680096 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151015 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3130 | 680196 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151015 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3131 | 680296 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151015 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3132 | 680097 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151016 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3133 | 680197 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151016 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3134 | 680297 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151016 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3135 | 680098 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151017 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3136 | 680198 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151017 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3137 | 680298 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/03/16 | 100% | RP-151017 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
3138 | 681000 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151018 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3139 | 681100 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151018 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3140 | 681200 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151018 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3141 | 681001 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151019 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3142 | 681101 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151019 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3143 | 681201 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151019 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3144 | 681002 | LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation | LTE_CA_3DL_2UL_inter_intra | 2 | Rel-14 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150817 | - | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL whi |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3145 | 681102 | Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation | LTE_CA_3DL_2UL_inter_intra-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP151576 | RP-151131 | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3146 | 681202 | Perf. part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation | LTE_CA_3DL_2UL_inter_intra-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP151576 | RP-151131 | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3147 | 681003 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 5 | LTE_CA_C_B5 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151035 | - | Intel |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3148 | 681103 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5 | LTE_CA_C_B5-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151035 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3149 | 681203 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5 | LTE_CA_C_B5-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151035 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3150 | 681004 | Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4_BWset | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151034 | - | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3151 | 681104 | Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4_BWset-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151034 | RP-151131 | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3152 | 681204 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4_BWset-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-151034 | RP-151131 | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3153 | 681005 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5 | LTE_CA_NC_B5 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151036 | - | Intel |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3154 | 681105 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5 | LTE_CA_NC_B5-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151036 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3155 | 681205 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5 | LTE_CA_NC_B5-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151036 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3156 | 681006 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_NC_B42_4DL | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151102 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
3157 | 681106 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_NC_B42_4DL-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151102 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3158 | 681206 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL | LTE_CA_NC_B42_4DL-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151102 | RP-151131 | Huawei |  | 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3159 | 680074 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12_BWset | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150585 | - | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
3160 | 680174 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12_BWset-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150585 | RP-151131 | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3161 | 680274 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12_BWset-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150585 | RP-151131 | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3162 | 680076 | Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150947 | - | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
3163 | 680176 | Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150947 | RP-151131 | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3164 | 680276 | Perf. part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/09/15 | 100% | RP-150947 | RP-151131 | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
3165 | 680072 | Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China | 2 | Rel-13 | R4 | Mon 15/06/15 | Thu 15/09/16 | 100% | RP-151037 | - | Huawei |  | Aug 15: TR numb added |  | 68 | 35 |  |  | Wed 12/08/15 | Wed 12/08/15
3166 | 680172 | Core part: Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151037 | RP-151242 | Huawei |  | Aug 15: TR numb added 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151242 | 36.892 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3167 | 680272 | Perf. part: Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151037 | RP-151242 | Huawei |  | 29/09/15: Stat Rep: -->RP-151242 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3168 | 710068 | UE Conformance Test Aspects - Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-UEConTest | 3 | Rel-13 | R5 | Tue 15/03/16 | Thu 15/09/16 | 100% | RP-161679 | - | Huawei |  | testing REL-13 LTE_TDD_1447MHz_China-Core¦1/7/16: C¦ |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
3169 | 680084 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42 | 2 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-150627 |  | ZTE |  |  |  | 68 | 35 |  |  | Wed 12/08/15 | Wed 12/08/15
3170 | 680184 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42-Core | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151562 | RP-151131 | ZTE |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 01/01/16
3171 | 680284 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42-Perf | 3 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151562 | RP-151131 | ZTE |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 01/01/16
3172 | 690073 | LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38 | LTE_CA_B5_B38 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151367 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3173 | 690173 | Core part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38 | LTE_CA_B5_B38-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151367 | - | Huawei |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3174 | 690273 | Perf. part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38 | LTE_CA_B5_B38-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151367 | - | Huawei |  | ¦1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3175 | 690074 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151156 | - | KDDI |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3176 | 690174 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151156 | - | KDDI |  | ¦1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3177 | 690274 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151156 | - | KDDI |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3178 | 690075 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151200 | - | ZTE |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3179 | 690175 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151200 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3180 | 690275 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151200 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3181 | 690076 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151365 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3182 | 690176 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151365 | - | Huawei |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3183 | 690276 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151365 | - | Huawei |  | ¦1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3184 | 690077 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151448 | - | ZTE |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3185 | 690177 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151448 | - | ZTE |  | ¦1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3186 | 690277 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151448 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3187 | 690078 | LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3188 | 690178 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3189 | 690278 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3190 | 690079 | LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3191 | 690179 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3192 | 690279 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3193 | 690082 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151262 | - | KT |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3194 | 690182 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151262 | - | KT |  | ¦1/1 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3195 | 690282 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151262 | - | KT |  | 1 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3196 | 690083 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3197 | 690183 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3198 | 690283 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3199 | 690084 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3200 | 690184 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3201 | 690284 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3202 | 690085 | LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3203 | 690185 | Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3204 | 690285 | Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3205 | 690089 | LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | NA
3206 | 690189 | Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3207 | 690289 | Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3208 | 690090 | LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3209 | 690190 | Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3210 | 690290 | Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3211 | 690091 | LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151512 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3212 | 690191 | Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-160141 | - | Telstra |  | ¦22/3/16: Compl:95%->100%; |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
3213 | 690291 | Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-160141 | - | Telstra |  | 22/3/16: Compl:95%->100%; |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
3214 | 690092 | LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151513 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3215 | 690192 | Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151513 | - | Telstra |  | 22/3/16: Compl:95%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
3216 | 690292 | Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151513 | - | Telstra |  | ¦22/3/16: Compl:95%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
3217 | 690093 | LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3218 | 690193 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3219 | 690293 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3220 | 690094 | LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41 | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151403 | - | CATT |  | TDD case¦5/10/15: 36.899-13 added; | 36.899-13 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/10/15
3221 | 690194 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151403 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3222 | 690294 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151403 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3223 | 690095 | Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7_BWset | 2 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 |  | 69 | 35 |  |  | Tue 29/09/15 | NA
3224 | 690195 | Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7_BWset-Core | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 ¦ |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3225 | 690295 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7_BWset-Perf | 3 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 ¦ |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3226 | 700065 | UE Conformance Test Aspects - Rel-13 LTE CA configurations | LTE_CA_Rel13-UEConTest | 2 | Rel-13 | R5 | Tue 15/12/15 | Fri 14/12/18 | 100% | RP-161553 |  | Ericsson |  | ¦22/3/16: Compl:0%->5%;1/7/16: Compl:5%->22%26/9/16: Compl:22%->¦2 21/3/17: Compl:39% ;; 14/1/20: 62%->100 |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 14/01/20
3227 | 610034 | (Small) Technical Enhancements and Improvements for Rel-13 | TEI13 | 1 | Rel-13 | SP,CP,RP,GP | Wed 18/09/13 | Mon 21/12/15 | 100% | - | PCG-31 | - | - | - | - | 61 | 31 |  |  | Mon 12/01/15 | Sat 14/09/13
3228 | 710001 | (Small) Test Technical Enhancements and Improvements for Rel-13 | TEI13_Test | 1 | Rel-13 | SP,CP,RP,GP | Wed 18/09/13 | Mon 21/12/15 | 100% | - | PCG-31 | - | - | Created upon demand of RAN5 | - | 61 | 31 |  |  | Mon 12/01/15 | Wed 24/02/16
3229 | 699999 | Awaiting formal work item | DUMMY | 1 | Rel-13 | SP,CP,RP,GP | Wed 18/09/13 | Mon 21/12/15 | 100% | [6 empty] | 69 | 35 |  |  | Mon 07/09/15 | NA
3230 | 690007 | (Small) Security Enhancements and Improvements for Rel-13 | SEC13 | 1 | Rel-13 | S3 | Tue 12/12/06 | Mon 21/12/15 | 100% | - | PCG-31 | - | - | - | - | 61 | 31 |  |  | Mon 12/01/15 | Sat 14/09/13
3231 | 0 | Release 13 IoT related Studies | - | 1 | Rel-13 | SP,R2 | Thu 12/09/13 | Fri 25/12/15 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
3232 | 620012 | Study on Power saving for Machine-Type Communications (MTC) devices | FS_uPoD | 1 | Rel-13 | G2,G1 | Tue 12/08/14 | Fri 14/08/15 | 100% | GP-131136 | - | China Mobile | Jing Han (hanjing@chinamobile.com) | GP#65 completion 02/15=>05/15. GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP). Dec.14: 30->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100 | 43.869 | 60 | 32 |  |  | Fri 22/11/13 | Wed 30/09/15
3233 | 640001 | Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things | FS_IoT_LC | 1 | Rel-13 | G1,G2 | Fri 30/05/14 | Fri 28/08/15 | 100% | GP-150354 | - | Vodafone | chris.pudney@vodafone.com | GP#62 approved WID. Dec.14: 15->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100¦14/09/15: WID:GP-140421->GP-150354 | 45.8xy | 66 | 33 |  |  | Fri 30/05/14 | Mon 14/09/15
3234 | 670029 | Study on architecture enhancements of cellular systems for ultra low complexity and low throughput Internet of Things | FS_AE_CIoT | 1 | Rel-13 | S2 | Fri 13/03/15 | Fri 11/12/15 | 100% | SP-150167 |  | puneet.jain@intel.com | puneet.jain@intel.com | 07/09/15: 0%->20¦07/09/15: 20%->65¦7/12/15: 65%->95¦7/3/16: 95%->100 | New 23.8xx | 67 | 34 |  |  | Fri 13/03/15 | Mon 07/03/16
3235 | 670036 | Study on Battery Efficient Security for very low Throughput Machine Type Communication Devices | FS_BEST_MTC_Sec | 1 | Rel-13 | S3 | Fri 13/03/15 | Fri 11/12/15 | 100% | SP-150171 |  | Barry, Aguibou, VODAFONE Group Plc | Barry, Aguibou, VODAFONE Group Plc | TR number added¦June2015: Compl:0%->10¦7/12/15: 10%->50¦11/12/15: 50%->75¦7/3/16: 75%->95¦19/9/16: 95%->100¦6/10/16: 33.163 added; | 32.863; 33.163 | 67 | 34 |  |  | Fri 13/03/15 | Thu 06/10/16
3236 | 650013 | Study on Small data transmission enhancements for UMTS | FS_UTRA_SDATA | 1 | Rel-13 | R1,R3 | Tue 16/09/14 | Mon 15/06/15 | 100% | RP-141861 | RP-150843 | Ericsson | gerardo.agni.medina.acosta@ericsson.com | 3/3/15: WID: RP-141861¦Stat Rep: -->RP-141859. Impacted TR number added. 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141859->RP-150196 03/07/15: Compl:55%->100% 03/07/15: Stat Rep: RP-150196->RP-150843 | 25.705 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
3237 | 570034 | Study on Application specific Congestion control for Data Communication | FS_ACDC | 1 | Rel-13 | S1 | Mon 17/09/12 | Wed 17/09/14 | 100% | SP-130415 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion) | 22.806 | 57 | 29 |  |  | Fri 31/08/12 | Fri 29/08/14
3238 | 610031 | Study on enhancements for Infrastructure based data Communication Between Devices | FS_eICBD | 1 | Rel-13 | S1 | Sat 14/09/13 | Wed 17/09/14 | 100% | SP-130418 | S1-143309 | KPN | toon.norp@tno.nl | SP#65 completed. TR 22.807v200 for Approval | 22.807 | 61 | 31 |  |  | Mon 26/08/13 | Thu 28/08/14
3239 | 0 | Release 13 other Studies | - | 1 | Rel-13 | SP,R2 | Thu 12/09/13 | Fri 25/12/15 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
3240 | 600046 | Study on Isolated E-UTRAN Operation for Public Safety | FS_IOPS | 1 | Rel-13 | S1 | Tue 25/06/13 | Wed 18/06/14 | 100% | SP-130596 | - | General Dynamics | paul.piggin@gd-broadband.com | SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and FeaturES in CP-150ProSe, GCSE_LTE | 22.897 | 60 | 31 |  |  | Thu 30/05/13 | Tue 27/05/14
3241 | 660059 | Study on architecture enhancements for Public Safety | FS_IOPS_St2 | 1 | Rel-13 | S2 | Fri 12/12/14 | Fri 12/06/15 | 100% | SP-140714 |  |  | phil.young@gd-broadband.com | June2015: Compl:0%->100 |  | 66 | 34 |  |  | Fri 12/12/14 | Mon 15/06/15
3242 | 670095 | Study on Security Aspects of Isolated E-UTRAN Operation for Public Safety | FS_IOPS_Sec | 1 | Rel-13 | S3 | Thu 12/03/15 | Fri 18/09/15 | 100% | SP-150074 |  | Paul Piggin, General Dynamics UK | paul.piggin@gd-broadband.com | TR added¦June2015: Compl:0%->30¦7/12/15: 30%->100 | New 33.897 | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/12/15
3243 | 610033 | (SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO | FS_CSIPTO | 1 | Rel-13 | S1 | Fri 13/09/13 | Wed 18/06/14 | 100% | SP-130417 | - | Intel | Eric.siow@intel.com | SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET | 22.828 | 61 | 31 |  |  | Mon 26/08/13 | Fri 12/12/14
3244 | 620069 | Study on Flexible Mobile Service Steering | FS_FMSS | 1 | Rel-13 | S1 | Fri 13/12/13 | Wed 17/09/14 | 100% | SP-130597 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 completed. TR 22.808v200 for Approval. Study supporting traffic classification and service chain selection capabilities per operator’s policy in order to realize efficient and flexible mobile service steering in the Gi-LAN network | 22.808 | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/08/14
3245 | 620070 | Study on Enhanced Calling Information Presentation | FS_ECIP | 1 | Rel-13 | S1 | Fri 13/12/13 | Wed 17/09/14 | 100% | SP-130598 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 completed. TR 22.810v200 for Approval. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067 | 22.81 | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/08/14
3246 | 630017 | Study on RAN Sharing Enhancements on GERAN and UTRAN | FS_GUSH | 1 | Rel-13 | S1 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140073 | - | Telefónica | chris.friel@telefonica.com | SP#65 completed. Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | 22.852 updates | 63 | 32 |  |  | Wed 05/02/14 | Fri 29/08/14
3247 | 520035 | Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group | FS_UMONC_sas | 1 | Rel-13 | S2 | Wed 08/06/11 | Fri 12/12/14 | 100% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Added to the Title "for Service, Application and Subscriber Group", Changed Acronym: FS_UMONC=>FS_UMONC_sas | 23.858 | 52 | 27 |  |  | Thu 19/05/11 | Thu 19/06/14
3248 | 520335 | Deleted - SA1 part of Study on Usage Monitoring Control PCC Enhancement | - | 2 | - | S1 | Wed 08/06/11 | Wed 20/06/12 | 100% | SP-120554 | - | ZTE | Li.Mian@zte.com.cn | SP#56 completed | 23.858 | 52 | 27 | SP-58 | PCG-31 | Thu 19/05/11 | Mon 09/09/13
3249 | 520135 | SA2 part of Study on Usage Monitoring Control PCC Enhancement | FS_UMONC_sas | 2 | Rel-13 | S2 | Fri 14/06/13 | Fri 12/12/14 | 100% | SP-150029 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Updated WID SP-120554=>SP-140403. Changed Justification/objectives/Rapporteut ZTE=>China Unciom. SP#58 SA2 stopped (at 70% completion). Dec.14: 80->100%. Mar 15: WID SP-140403->SP-150029 | 23.858 | 52 | 27 |  |  | Thu 19/05/11 | Thu 05/03/15
3250 | 520235 | Deleted - SA5 part of Study on Usage Monitoring Control enhancement | - | 2 | - | S5 | Fri 02/03/12 | Wed 12/09/12 | 100% | SP-120554 | - | Huawei | Hui Cai (Sarah.Cai@huawei.com) | SP#57 stopped | 32.858 | 52 | 27 | SP-57 | PCG-29 | Thu 19/05/11 | Thu 30/08/12
3251 | 500034 | Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int_Sec | 1 | Rel-13 | S3 | Tue 28/12/10 | Fri 12/06/15 | 100% | SP-150368 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%¦June2015: Compl:65%->100¦June2015: WID:SP-140576->SP-150368 | 33.895 | 50 | 26 |  |  | Thu 25/11/10 | Thu 18/06/15
3252 | 610043 | Study on Subscriber Privacy Impact in 3GPP | FS_SPI | 1 | Rel-13 | S3 | Tue 17/09/13 | Wed 16/12/15 | 100% | SP-130399 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 moved to Rel-13. Completion 09/14=>12/15. Related to SA1 TR 22.949 Rel-6 Study on Privacy Capability (PrivCap) UID_31030 studied generalized privacy capability (protection of personal data and non-disclosure of identity). Dec.14: 80->85¦June2015 | 33.849 | 61 | 31 |  |  | Tue 03/09/13 | Mon 07/03/16
3253 | 610045 | Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function | FS_D_MLB_SON_OAM | 1 | Rel-13 | S5 | Mon 15/09/14 | Mon 13/06/16 | 100% | SP-130430 | - | Cisco | Vladimir Yanover (vyanover@cisco.com) | SP#64 completion 06/14=>12/14. Dec.14: 20->25%, CD: 12/14->06/15¦June2015: Compl:25%->30¦7/12/15: 30%->45¦7/3/16: 45%->50¦13/6/16: 50%->100 | 32.86 | 61 | 31 |  |  | Mon 09/09/13 | Mon 13/06/16
3254 | 620059 | Study on Application and Partitioning of Itf-N | FS_OAM_AP_Itf-N | 1 | Rel-13 | S5 | Tue 17/12/13 | Fri 11/09/15 | 100% | SP-130681 | - | China Mobile | Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com) | -Dec.14: 15->30%, CD: 12/14->09/15¦June2015: Compl:30%->60¦07/09/15: 60%->100 | 32.861 | 62 | 32 |  |  | Thu 28/11/13 | Mon 07/09/15
3255 | 620060 | Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks | FS_REVOLTE_IMS_CH | 1 | Rel-13 | S5 | Tue 17/12/13 | Fri 12/06/15 | 100% | SP-130609 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | SP#64 moved to Rel-13. Completion 06/14=>12/14. Dec.14: 35->55, CD: 12/14->06/15. Mar 15: 55->75%¦June2015: Compl:75%->100 | 32.849 | 62 | 32 |  |  | Thu 28/11/13 | Mon 15/06/15
3256 | 640054 | Study on Network Management of Virtualized Networks | FS_OAM_VIRNET | 1 | Rel-13 | S5 | Wed 11/06/14 | Wed 17/06/15 | 100% | SP-140398 | - | China Mobile, Huawei | Liu Jinglei (liujinglei@chinamobile.com), zoulan@huawei.com | Dec.14: 10->25%. Mar 15: 25->60%¦June2015: Compl:60%->85¦07/09/15: 85%->100 | 32.842 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/09/15
3257 | 590010 | Study on Review of dedicated 3GPP UICC features | FS_Red_UCe | 1 | Rel-13 | C6 | Wed 13/03/13 | Wed 16/12/15 | 100% | CP-130168 | - | BlackBerry | Adrian Buckley (abuckley@blackberry.com) | CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100% | 31.901 | 59 | 30 |  |  | Wed 20/02/13 | Wed 03/12/14
3258 | 490006 | Study on Solutions for GSM/EDGE BTS Energy Saving | FS_Energy_BTS | 1 | Rel-13 | G1,G2 | Tue 30/08/11 | Fri 20/11/15 | 100% | GP-101638 | - | Nokia Networks | juergen.hofmann@nokia.com | GP#63 moved to Rel-13. Completion 08/14=>11/14. GP#55 TR 45.926v100 for Information. GP#47 approved WID. Dec.14: 90->95%. 3/3/15: start date corrected (was 03/09). 7/9/15: FCD: 8/15->11/15¦7/12/15: 95%->100 | 45.926 | 47 | 25 |  |  | Sun 05/09/10 | Mon 07/12/15
3259 | 590034 | Study on Downlink MIMO | FS_DOMIMO | 1 | Rel-13 | G1,G2 | Thu 14/08/14 | Thu 12/05/16 | 100% | GP-130288 | - | Nokia Networks | juergen.hofmann@nokia.com | GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID. Dec.14: 50->65%, CD: 02/15->05/15. 7/9/15: FCD: 11/15->02/16¦2/3/16: 65%->75, FCD: 02/16->05/16¦11/9/17: 75%->100 | 45.8xy | 57 | 30 |  |  | Mon 04/03/13 | Mon 11/09/17
3260 | 640017 | Study on MIMO OTA antenna test function for LTE | FS_LTE_MIMO_OTA_ATF | 1 | Rel-13 | R4 | Mon 18/03/13 | Mon 15/12/14 | 100% | RP-141325 | RP-142045 | Keysight | Moray_Rumney@keysight.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:60%->100%¦Stat Rep: RP-141124->RP-142045 | 36.509, new 37.978 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
3261 | 620013 | Stopped at 20% - Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO) | FS_UL_MU_MIMO | 1 | Rel-13 | G1,G2 | Thu 17/04/14 | Fri 19/02/16 | 100% | GP-131131 | - | Huawei | Chao Luo (chluo@huawei.com) | GP#62 completion 11/14=>02/15. GP#60 approved WID. Dec.14: 02/15->05/15. 02/03/16: stopped at 20% | 45.876 | 60 | 32 | SP#71 |  | Fri 22/11/13 | Wed 03/12/14
3262 | 570022 | Study on LTE FDD in the bands 1980-2010 MHz and 2170-2200 MHz | FS_LTE_1980_2170_Korea | 1 | Rel-13 | R4 | Tue 11/09/12 | Tue 15/12/15 | 100% | RP-151855 | RP-151274 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 11/12/14->Sun 15/03/15¦Compl:85%->90%¦Stat Rep: RP-141153->RP-141851 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141154->RP-150119 1st Apr 15: Stat Rep: RP-141851->RP-150120 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: S | LTE 36.861 | 57 | 29 |  |  | Mon 03/09/12 | Fri 01/01/16
3263 | 600020 | Study on Positioning enhancements for E-UTRA | FS_LCSenh_LTE | 1 | Rel-13 | R4 | Tue 01/05/12 | Mon 15/12/14 | 100% | RP-130680 | RP-142224 | Huawei | Jie Cui (cuijie@huawei.com) | WID: RP-140667->RP-130680¦Stat Rep: RP-140639->RP-142224. 3/3/15: R1 removed as 2nd responsible WG | LTE 36.855 | 60 | 31 |  |  | Mon 17/06/13 | Tue 03/03/15
3264 | 620045 | Study on Multi-RAT joint coordination | FS_MultiRAT_JC | 1 | Rel-13 | R4 | Fri 06/12/13 | Mon 15/06/15 | 100% | RP-150417 | RP-150807 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | ¦WID: RP-142043->RP-132086¦Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807 | UTRA, LTE 37.870 | 62 | 32 |  |  | Wed 27/11/13 | Thu 18/06/15
3265 | 640016 | Study on Advanced Wireless Services (AWS) - Extension band for LTE | FS_LTE_AWS_EXT | 1 | Rel-13 | R4 | Mon 16/12/13 | Mon 15/12/14 | 100% | RP-141037 | RP-141968 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | CD:Thu 11/12/14->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141429->RP-141968. 5/5/15: 2nd TR number added (to be clarified why two TR for a same topic) | 36.849, 36.869 | 64 | 33 |  |  | Mon 16/06/14 | Tue 05/05/15
3266 | 640018 | Study on Indoor Positioning Enhancements for UTRA and LTE | FS_UTRA_LTE_iPos_enh | 1 | Rel-13 | R1,R4 | Wed 18/06/14 | Tue 15/09/15 | 100% | RP-141102 | RP-151178 | NextNav | Vogedes Jerome (jvogedes@NextNav.com) | CD:Thu 17/09/15->Tue 15/09/15¦Compl:0%->8%¦Stat Rep: RP-141101->RP-141818 1st Apr 15: Compl:8%->30% 1st Apr 15: Stat Rep: RP-141818->RP-150080 03/07/15: Compl:30%->75% 03/07/15: Stat Rep: RP-150080->RP-150595 29/09/15: Compl:75%->100% 29/09/15: Stat | UTRA, LTE 37.857 | 64 | 33 |  |  | Mon 16/06/14 | Tue 29/09/15
3267 | 650014 | Study on Downlink enhancements for UMTS | FS_UTRA_EDL | 1 | Rel-13 | R2,R1 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-150224 | RP-150681 | Huawei | jun.chen@huawei.com | WID: RP-141901¦Stat Rep: -->RP-142233 1st Apr 15: Compl:40%->80% 1st Apr 15: WID: RP-141901->RP-150224 1st Apr 15: Stat Rep: RP-142233->RP-150223. 5/5/15: R4 replaced by R1 (correction mistake) 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150223-> | UTRA 25.706 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
3268 | 650015 | Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | FS_LTE_EBF_FDMIMO | 1 | Rel-13 | R1 | Fri 12/09/14 | Mon 15/06/15 | 100% | RP-150930 | RP-150734 | Nokia Networks (DL), Samsung (UL) | bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com | 3/3/15: WID: RP-141831¦Stat Rep: -->RP-141822, impacted TR number added. 1st Apr 15: Compl:30%->45% 1st Apr 15: Stat Rep: RP-141822->RP-150346. 5/5/15: "R4" replaced by "R1" (correction mistake) 03/07/15: Compl:45%->100% 03/07/15: WID: RP-141831->RP-1 | 36.897 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
3269 | 650016 | Study on Licensed-Assisted Access using LTE | FS_LTE_LAA | 1 | Rel-13 | R1,R2,R4 | Tue 16/09/14 | Mon 15/06/15 | 100% | RP-141817 | RP-150624 | Ericsson, Huawei | havish.koorapaty@ericsson.com, david.mazzarese@huawei.com | 3/3/15: WID: RP-141817¦Stat Rep: -->RP-141816. Impacted TR number added. 1st Apr 15: Compl:30%->40% 1st Apr 15: Stat Rep: RP-141816->RP-150414 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150414->RP-150624 | 36.889 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
3270 | 660027 | Study on EPC Signalling Improvement for Race Scenarios | FS_EPC_SIG_RACE | 1 | Rel-13 | C4 | Wed 03/12/14 | Fri 11/09/15 | 100% | CP-140997 |  | Huawei |  | Mar15: 0->20%¦June2015: Compl:20%->80¦07/09/15: 80%->95¦7/12/15: 95%->100 | New 29.811 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
3271 | 660057 | Study on Video Enhancements in 3GPP Multimedia Services | FS_VE_3MS | 1 | Rel-13 | S4 | Fri 12/12/14 | Fri 11/12/15 | 100% | SP-140741 |  | Ye-Kui Wang, Qualcomm Incorporated | yekuiw@qti.qualcomm.com | Mar. 15: 0->20%¦June2015: Compl:20%->40¦07/09/15: 40%->80¦7/12/15: 80%->100 |  | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/12/15
3272 | 660063 | Study on possible additional configuration for LTE TDD | FS_LTE_TDD_add_config | 1 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150652 | RP-151283 | NTT DOCOMO, Hideaki Takahashi | NTT DOCOMO | TR 36.825 rapporteur: CATT. TR number added. 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150151 03/07/15: Compl:5%->35% 03/07/15: WID: RP-142248->RP-150652 03/07/15: Stat Rep: RP-150151->RP-150805 29/09/15: Compl:35%->100% 29/09/15: Stat Rep: R | 36.825 | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
3273 | 660064 | Study on Network-Assisted Interference Cancellation and Suppression for UMTS | FS_UTRA_NAICS | 1 | Rel-13 | R1 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-150174 | RP-151235 | Huawei | Huawei | TS number added 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-142250->RP-150174 1st Apr 15: Stat Rep: ->RP-150175. 5/5/15: "R4" replaced by "R1" (correction mistake) 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150175->RP-150679 29/09/15: Compl:65%- | 25.766 | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
3274 | 660065 | Study on Enhanced Multiuser Transmissions and Network Assisted Interference Cancellation for LTE | FS_LTE_MUTX_NAIC | 1 | Rel-13 | R1 | Mon 15/12/14 | Sun 15/03/15 | 0% | RP-142315 | RP-150213 | MediaTek | MediaTek | 1st Apr 15: CD:Tue 15/12/15->Sun 15/03/15 1st Apr 15: Stat Rep: ->RP-150213. 5/5/15: "R4" replaced by "R1" (correction mistake) |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 05/05/15
3275 | 660066 | Study on Support of single-cell point-to-multipoint transmission in LTE | FS_LTE_SC_PTM | 1 | Rel-13 | R4 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150177 | RP-150695 | Jeff GAO | gaoyongqiang@huawei.com | deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695 | 36.89 | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
3276 | 660067 | Study on Extension of Dual Connectivity in E-UTRAN | FS_LTE_dualC_ext | 1 | Rel-13 | R3 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150170 | RP-150849 | Samsung | Samsung | 1st Apr 15: WID: RP-142257->RP-150170 1st Apr 15: Stat Rep: ->RP-150163 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150163->RP-150849. 7/10/15: responsible group corrected (R4->R3) | 36.875 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
3277 | 660068 | Study on further enhancements of small cell higher layer aspects for LTE | FS_LTE_SC_enh2_hilayer | 1 | Rel-13 | R3 | Mon 15/12/14 | Tue 15/09/15 | 100% | RP-142283 | RP-151243 | Huawei | Huawei | 03/07/15: Compl:10%->30% 03/07/15: Stat Rep: RP-150226->RP-150683 29/09/15: Compl:30%->100% 29/09/15: Stat Rep: RP-150683->RP-151243. 7/10/15: responsible group corrected (R4->R3) and TS (37.876->36.876) | 36.876 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
3278 | 660069 | Study on RAN sharing enhancements for UMTS | FS_RSE_UTRA_GUSH | 1 | Rel-13 | R3 | Mon 15/12/14 | Mon 15/06/15 | 100% | RP-150686 | RP-150684 | Huawei | Huawei | 03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3) | 25.756 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
3279 | 660070 | Study on LTE DL 4 Rx antenna ports | FS_LTE_4Rx_AP_DL | 1 | Rel-13 | R4 | Mon 15/12/14 | Fri 13/03/15 | 100% | RP-150457 | RP-150138 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->100% 1st Apr 15: WID: RP-142299->RP-150457 1st Apr 15: Stat Rep: ->RP-150138 |  | 66 | 34 |  |  | Mon 12/01/15 | Wed 01/04/15
3280 | 660071 | Study on performance enhancements for high speed scenario in LTE | FS_LTE_high_speed | 1 | Rel-13 | R4 | Mon 15/12/14 | Tue 15/12/15 | 100% | RP-150159 | RP-151313 | NTTDoCoMo | NTTDoCoMo | TR Rapporteur is Huawei 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142307->RP-150159 1st Apr 15: Stat Rep: ->RP-150517 03/07/15: Compl:5%->40% 03/07/15: Stat Rep: RP-150517->RP-150793 29/09/15: Compl:40%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
3281 | 660061 | Study on Enhanced Multiuser Transmissions and Network | FS_MUIC_LTE | 1 | Rel-13 | R1 | Fri 12/12/14 | Fri 11/12/15 | 0% | RP-142315 |  | Pei-Kai Liao | pk.liao@mediatek.com | TR added | 36.891 | 67 | 34 |  |  | Fri 12/12/14 | Thu 29/01/15
3282 | 670040 | Study on regulatory aspects for flexible duplex for E-UTRAN | FS_LTE_flex_duplex_reg | 1 | Rel-13 | RP | Wed 15/06/16 | Thu 15/12/16 | 100% | RP-150470 | RP-151307 | LG Electronics Inc. |  | TR added 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: -->RP-150770 29/09/15: Compl:5%->100% 29/09/15: Stat Rep: RP-150770->RP-151307 | 36.882 | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
3283 | 670043 | Study on Downlink Multiuser Superposition Transmission for LTE | FS_LTE_MUST | 1 | Rel-13 | R1 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151100 | RP-151345 | Mediatek |  | TR added 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150496->RP-151100 03/07/15: Stat Rep: -->RP-150857 29/09/15: Compl:30%->50% 29/09/15: Stat Rep: RP-150857->RP-151345 | 36.859 | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3284 | 670044 | Study on Measurement gap enhancement for LTE | FS_LTE_meas_gap | 1 | Rel-13 | R4 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150515 | RP-151317 |  |  | 03/07/15: Compl:0%->15% 03/07/15: CD:Thu 10/12/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150754 03/07/15: Release: REL-13->Rel-13. Aug 15: TR numb added 29/09/15: Compl:15%->65% 29/09/15: Stat Rep: RP-150754->RP-151317 | 36.894 | 67 |  |  |  | Mon 11/05/15 | Fri 01/01/16
3285 | 670087 | Study on Phase 1 of the Support of Emergency services over WLAN | FS_SEW | 1 | Rel-13 | S2 | Thu 12/03/15 | Thu 18/06/15 | 100% | SP-150251 |  | Laurent Thiebaut, Alcatel Lucent | Laurent.thiebaut@alcatel-lucent.com | June2015: Compl:0%->100, SP-150151->SP-150251 | new 23.771 | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
3286 | 670093 | Study on EGPRS Access Security Enhancements with relation to cellular IoT | FS_EASE_IoT | 1 | Rel-13 | S3 | Thu 12/03/15 | Fri 11/12/15 | 100% | SP-150145 |  | Vesa Torvinen, Ericsson |  | TR added¦June2015: Compl:0%->25¦7/12/15: 25%->70¦28/1/16: 33.420 added¦7/3/16: 70%->100 | New 33.860; 33.420 | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/03/16
3287 | 680013 | Study on SCC AS Restoration | FS_SCCAS_RES | 1 | Rel-13 | C4 | Mon 15/06/15 | Mon 15/06/15 | 100% | CP-150398 |  | Hao Zhang,, China Mobile | zhanghao@chinamobile.com | 07/09/15: 5%->20¦7/12/15: 20%->100 | New 29.812 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
3288 | 680018 | Study on S6a/S6d Shared Data Update | FS_eSDU | 1 | Rel-13 | C4 | Mon 15/06/15 | Fri 11/12/15 | 100% | CP-150400 |  | Ulrich Wiehe, Nokia Networks | ulrich.wiehe@nokia.com | 07/09/15: 0%->20¦7/12/15: 20%->100 | New 29.813 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
3289 | 680055 | Study on Network Assistance for Network Synchronization in LTE | FS_LTE_NW_SYNC | 1 | Rel-14 | R3 | Mon 15/06/15 | Thu 15/12/16 | 100% | RP-151252 |  | Huawei |  | Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: WID: RP-151084->RP-151252 29/09/15: Stat Rep: -->RP-151240 22/3/16: Compl:60%->80%¦22/3/16: CD:Tue 15/03/16->Wed 15/06/16¦ ¦ | New 36.898 | 68 | 35 |  |  | Fri 03/07/15 | Tue 20/12/16
3290 | 680056 | Study onLTE Advanced inter-band Carrier Aggregation of Band 20 and Band 28 | FS_LTE_CA_B20_B28 | 1 | Rel-13 | R4 | Mon 15/06/15 | Tue 15/12/15 | 100% | RP-151515 | RP-151231 | TeliaSonera |  | 29/09/15: Compl:0%->20% 29/09/15: WID: RP-151101->RP-151515 29/09/15: Stat Rep: -->RP-151231 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
3291 | 690003 | Study on Impacts of the Diameter Base Protocol Specification Update | FS_DBPU | 1 | Rel-13 | C4 | Mon 07/09/15 | Fri 18/12/15 | 100% | CP-150575 |  | Huawei, Peter Schmitt |  | 7/3/16: 0%->79¦13/6/16: 79%->99¦2/12/16: 99%->100 | 29.274, 29.060, 23.003, 29.272, 29.002, 29.305, 23.008, 29.230, 29.303, 23.007, 24.301, 24.008 | 69 | 35 |  |  | Mon 07/09/15 | Fri 02/12/16
3292 | 690061 | Study on new AWS-3/4 Band for LTE | FS_LTE_AWS_3_4 | 1 | Rel-13 | R4 | Tue 15/09/15 | Tue 15/12/15 | 100% | RP-151626 | - | Dish Network |  |  | 36.87 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
3293 | 720087 | Study on multi-node testing for LAA | FS_LTE_LAA_multinode_test | 1 | Rel-13 | R4 | Wed 15/06/16 | Thu 15/06/17 | 100% | RP-162144 |  | Huawei |  | coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672¦20/12/16: Compl:10%->30%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17¦20/12/16: WID: RP-161672->RP-162144¦21/3/17: CD:Wed 15/03/17->Thu 15/06/17; |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
3294 | 560435 | Stopped - Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR | FS_OAM_NGMN_NGCOR | 1 | Rel-13 | S5 | Tue 26/06/12 | Fri 15/12/17 | 100% | SP-140787 | - | Huawei | zoulan@huawei.com | SP#65 updated WID SP-140349=>SP-140539. Dec.14: 35->45, 12/14: 28.821 added. Mar 15: 45->50%¦June2015: Compl:50%->60. 07/09/15: FCD: 09/15->12/15¦7/12/15: FCD:12/15->03/16¦21/3/17:marked as stopped, was 60% | 32.837, 28.821 | 56 | 29 |  |  | Mon 14/05/12 | Tue 21/03/17
3295 | 0 | --- RELEASE 12 --- | - | 1 | Rel-12 | SP,CP,RP,GP | Mon 14/10/13 | Fri 12/12/14 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/09/11 | Wed 17/09/14
3296 | 0 | Stage 1 - ONLY Features | - | 1 | Rel-12 | SP,CP | Tue 27/09/11 | Wed 05/03/14 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
3297 | 490030 | SIPTO Service Continuity of IP Data Session | SIPTO_SC | 1 | Rel-12 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12 (Reason: Stage 2 for requirements in TS 22.101 clause 4.3.5 have not been implemented in Rel-11). Linked to Rel-10 Local IP Access and Selected Internet IP Traffic Offload (LIPA_SIPTO) | Stage 1 | 49 | 25 |  |  | Wed 01/09/10 | Thu 30/08/12
3298 | 490130 | Stage 1 for SIPTO Service Continuity of IP Data Session | SIPTO_SC-SA1 | 2 | Rel-12 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12. SP#53 completed | 22.101, 22.220 | 49 | 25 |  |  | Wed 01/09/10 | Thu 30/08/12
3299 | 500031 | Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers | MOSAP | 1 | Rel-12 | S1,S2 | Thu 16/12/10 | Wed 11/12/13 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#58 Stage 2 stopped (TR only, no normative work done) | Stage 1 | 50 | 26 |  |  | Mon 29/11/10 | Thu 22/11/12
3300 | 500131 | Stage 1 for MOSAP | MOSAP-SA1 | 2 | Rel-12 | S1 | Thu 16/12/10 | Wed 21/09/11 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#53 completed | 22.278 | 50 | 26 |  |  | Mon 29/11/10 | Sat 09/06/12
3301 | 520025 | TR on Stage 2 for MOSAP | MOSAP-SA2TR | 2 | Rel-12 | S2 | Mon 06/06/11 | Wed 11/12/13 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#62 completed. TR 23.862v200 for Approval. SP#58 frozen as v100. | new 23.862 | 52 | 27 |  |  | Thu 26/05/11 | Thu 22/11/12
3302 | 520026 | Deleted - Stage 2 for MOSAP | MOSAP-SA2Del | 2 | Rel-12 | S2 | Tue 14/06/11 | Wed 12/12/12 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#58 stopped (no normative work done) | TBD | 52 | 27 | SP-58 | PCG-30 | Thu 26/05/11 | Thu 22/11/12
3303 | 520027 | IMS Network-Independent Public User Identities | INIPUI | 1 | Rel-12 | S1 | Wed 08/06/11 | Wed 20/06/12 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | Triggered by Rel-11 TR 22.894 (FS_INIPUI) | Stage 1 | 52 | 27 |  |  | Thu 19/05/11 | Tue 19/06/12
3304 | 520127 | Stage 1 for IMS Network-Independent Public User Identities | INIPUI-SA1 | 2 | Rel-12 | S1 | Wed 08/06/11 | Wed 20/06/12 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 re-completed. Updated WID SP-110381=>SP-120425 (Re-opened & moved to Rel-12 by adding new reqs & removing reqs from Rel-11). SP#53 Rel-11 Stage 1 completed | 22.115, 22.228 | 52 | 27 |  |  | Thu 19/05/11 | Tue 19/06/12
3305 | 530043 | Service and Media Reachability for Users over Restrictive Firewalls | SMURFs | 1 | Rel-12 | S1 | Wed 21/09/11 | Wed 20/06/12 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 Stage 1 completed | Stage 1 | 53 | 27 |  |  | Tue 19/07/11 | Thu 15/09/11
3306 | 530143 | Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls | SMURFs-SA1 | 2 | Rel-12 | S1 | Wed 21/09/11 | Wed 20/06/12 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 completed | 22.278 | 53 | 27 |  |  | Tue 19/07/11 | Fri 08/06/12
3307 | 550024 | Advanced IP Interconnection of Services (IPXS) for national interconnect | IPXSNAT | 1 | Rel-12 | S1 | Tue 06/03/12 | Wed 12/09/12 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051. | Stage 1 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
3308 | 550124 | Stage 1 for Advanced IP Interconnection of Services (IPXS) for national interconnect | IPXSNAT-SA1 | 2 | Rel-12 | S1 | Tue 06/03/12 | Wed 12/09/12 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 completed | 22.228 CR#0161 | 55 | 28 |  |  | Wed 22/02/12 | Mon 14/01/13
3309 | 550025 | Integration of Single Sign-On (SSO) frameworks with 3GPP networks | SSO_Int | 1 | Rel-12 | S1 | Thu 08/03/12 | Wed 12/09/12 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 Stage 1 completed. Triggered by Rel-12 TR 22.895. Linked to SA3 33.8xy (Study on Security aspects of SSO_Int), 33.914 (SSO application security for common IMS based on SIP Digest), 33.924 (i/w GBA and OpenID), 33.980 (i/w GBA and Liberty Alliance) | Stage 1 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
3310 | 550125 | Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks | SSO_Int-SA1 | 2 | Rel-12 | S1 | Thu 08/03/12 | Wed 12/09/12 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 completed | 22.101 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
3311 | 560019 | Explicit Communication Transfer Blind (ECT Blind) service interactions | ECTB | 1 | Rel-12 | S1 | Mon 18/06/12 | Wed 20/06/12 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 WID approved & Stage 1 completed | Stage 1 | 56 | 29 |  |  | Mon 14/05/12 | Fri 08/06/12
3312 | 560119 | Stage 1 for Explicit Communication Transfer Blind (ECT Blind) service interactions | ECTB-SA1 | 2 | Rel-12 | S1 | Mon 18/06/12 | Wed 20/06/12 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 new WID approved & work completed. Clarify the service interactions between ECT Blind and other MMTEL Supplementary Services | 22.173 | 56 | 29 |  |  | Mon 14/05/12 | Fri 08/06/12
3313 | 570027 | IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2) | IMSSat | 1 | Rel-12 | S1 | Thu 02/02/12 | Wed 12/09/12 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS | Stage 1 | 57 | 29 |  |  | Mon 06/08/12 | Wed 08/08/12
3314 | 570127 | Stage 1 for IMS access via DVB-RCS2 | IMSSat-SA1 | 2 | Rel-12 | S1 | Thu 02/02/12 | Wed 12/09/12 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 completed. Definition of DVB-RCS2 as a non-3GPP IP Connectivity Access Network for IMS | 22.228 | 57 | 29 |  |  | Mon 06/08/12 | Wed 08/08/12
3315 | 580060 | Sequential Flexible Alerting | SEQ_FA | 1 | Rel-12 | S1 | Mon 10/12/12 | Wed 12/12/12 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. 22/01: acronym modified | Stage 1 | 58 | 30 |  |  | Fri 16/11/12 | Thu 22/01/15
3316 | 580160 | Stage 1 for Sequential Flexible Alerting | SEQ_FA | 2 | Rel-12 | S1 | Mon 10/12/12 | Wed 12/12/12 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed | 22.173 | 58 | 30 |  |  | Fri 16/11/12 | Wed 21/11/12
3317 | 580061 | Language and Modality Information for communications | LangInfo | 1 | Rel-12 | S1 | Tue 11/12/12 | Wed 06/03/13 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 Stage 1 completed. Triggered by Rel-11 Study on Non Voice Emergency Services (FS_NOVES) TR 22.871 use case 10 | Stage 1 | 58 | 30 |  |  | Fri 16/11/12 | Tue 19/02/13
3318 | 580161 | Stage 1 for Language and Modality Information for communications | LangInfo-SA1 | 2 | Rel-12 | S1 | Tue 11/12/12 | Wed 06/03/13 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 completed. Updated WID SP-120937=>SP-130108 | 22.228 | 58 | 30 |  |  | Fri 16/11/12 | Tue 19/02/13
3319 | 590040 | Emergency Session Identification | ESID | 1 | Rel-12 | S1 | Mon 04/03/13 | Wed 06/03/13 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 Stage 1 completed. | Stage 1 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
3320 | 590140 | Stage 1 for Emergency Session Identification | ESID-SA1 | 2 | Rel-12 | S1 | Mon 04/03/13 | Wed 06/03/13 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 completed (22.101 CR#0445) | 22.101 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
3321 | 590041 | Deleted - Application and Service Access Control | ASAC | 1 | Rel-12 | S1 | Wed 06/03/13 | Wed 19/06/13 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC continues. Triggered by TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) UID_570034 | Stage 1 | 59 | 30 | SP-60 | PCG-31 | Tue 19/02/13 | Tue 19/02/13
3322 | 590141 | Deleted - Stage 1 for Application and Service Access Control | ASAC-SA1del | 2 | Rel-12 | S1 | Wed 06/03/13 | Wed 19/06/13 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster) | 22.011 | 59 | 30 | SP-60 | PCG-31 | Tue 19/02/13 | Tue 19/02/13
3323 | 590042 | Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | PMOC | 1 | Rel-12 | S1 | Mon 04/03/13 | Wed 06/03/13 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 Stage 1 completed | Stage 1 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
3324 | 590142 | Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | PMOC-SA1 | 2 | Rel-12 | S1 | Mon 04/03/13 | Wed 06/03/13 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 completed | 22.011 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
3325 | 0 | SA1/SA2 Features | - | 1 | Rel-12 | SP,CP,RP | Fri 17/05/13 | Fri 07/03/14 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
3326 | 500028 | LIPA Mobility and SIPTO at the Local Network | LIMONET | 1 | Rel-12 | S2,C4,C1,R3 | Fri 15/10/10 | Thu 06/03/14 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | CP#63 completed. SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility). Linked to UID_450035 Local IP Access and Selected IP Traffic Offload (LIPA_SIPTO) | Stage 2/3 | 50 | 26 |  |  | Fri 26/11/10 | Wed 27/02/13
3327 | 500128 | TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network | LIMONET-SA3 | 2 | Rel-12 | S2 | Fri 15/10/10 | Wed 06/03/13 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#59 completed. TR 23.859 v100 for Information and Approval | new 23.859 | 50 | 26 |  |  | Fri 26/11/10 | Wed 27/02/13
3328 | 500328 | BB1: SIPTO at the Local Network | LIMONET-SIPTO | 2 | Rel-12 | S2 | Fri 22/10/10 | Wed 05/03/14 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Thu 06/06/13
3329 | 501328 | Stage 2 for SIPTO at the Local Network | LIMONET-SIPTO-SA2 | 3 | Rel-12 | S2 | Fri 22/10/10 | Wed 19/06/13 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Thu 06/06/13
3330 | 530015 | Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO | 3 | Rel-12 | C4,C1 | Sat 24/09/11 | Wed 05/03/14 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | Stage 3 | 53 | 27 |  |  | Sat 27/08/11 | Wed 29/01/14
3331 | 530115 | CT4 part of Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO-CT4 | 4 | Rel-12 | C4 | Sat 24/09/11 | Fri 06/09/13 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#61 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.303 | 53 | 27 |  |  | Sat 27/08/11 | Sat 10/08/13
3332 | 530215 | CT1 part of Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO-CT1 | 4 | Rel-12 | C1 | Sat 24/09/11 | Wed 05/03/14 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | 24.008, 24.301 | 53 | 27 |  |  | Sat 27/08/11 | Wed 29/01/14
3333 | 590020 | RAN aspects for SIPTO at the Local Network | LIMONET-RAN | 2 | Rel-12 | R3 | Mon 04/03/13 | Thu 06/03/14 | 100% | RP-130372 | - | Huawei | zheng.zhou@huawei.com | - | UTRA, LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3334 | 590120 | Core part: RAN aspects for SIPTO at the Local Network | LIMONET-RAN-Core | 3 | Rel-12 | R3 | Mon 04/03/13 | Thu 06/03/14 | 100% | RP-130372 | RP-131512 | Huawei | zheng.zhou@huawei.com | RP#62 completed | 25.401, 25.413, 25.423, 25.467, 25.469, 36.300, 36.413, 36.423 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
3335 | 501228 | Deleted - BB2: Stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | LIMONET-LIPA | 2 | Rel-12 | S2 | Fri 22/10/10 | Wed 12/12/12 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | 50 | 26 | SP-58 | PCG-30 | Fri 26/11/10 | Wed 27/02/13
3336 | 500228 | Deleted - Stage 2 for stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | LIMONET-LIPA-del1 | 3 | Rel-12 | S2 | Fri 22/10/10 | Wed 12/12/12 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | 50 | 26 | SP-58 | PCG-30 | Fri 26/11/10 | Wed 27/02/13
3337 | 530016 | Deleted - Stage 3 CN aspects of LIPA Mobility | LIMONET-LIPA-del2 | 3 | Rel-12 | C1,C4 | Sat 24/09/11 | Wed 12/12/12 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | Stage 3 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Wed 06/06/12
3338 | 530116 | Deleted - CT1 part of CN aspects of LIPA Mobility | LIMONET-LIPA-del3 | 4 | Rel-12 | C1 | Sat 24/09/11 | Wed 12/12/12 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 24.008, 24.301 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Wed 06/06/12
3339 | 530216 | Deleted - CT4 part of CN aspects of LIPA Mobility | LIMONET-LIPA-del4 | 4 | Rel-12 | C4 | Sat 24/09/11 | Wed 12/12/12 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 29.060, 29.274, 29.281, 29.303, 29.002, 29.272, 29.275, 29.282, 29.305 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Mon 18/02/13
3340 | 510049 | Operator Policies for IP Interface Selection | OPIIS | 1 | Rel-12 | S2,C1 | Wed 23/03/11 | Fri 06/12/13 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network) | Stage 2/3 | 51 | 26 |  |  | Mon 21/02/11 | Wed 27/02/13
3341 | 510149 | TR on Stage 2 for Operator Policies for IP Interface Selection | OPIIS | 2 | Rel-12 | S2 | Wed 23/03/11 | Wed 12/12/12 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#58 completed | new 23.853 | 51 | 26 |  |  | Mon 21/02/11 | Mon 10/12/12
3342 | 510249 | Stage 2 for Operator Policies for IP Interface Selection | OPIIS | 2 | Rel-12 | S2 | Mon 04/04/11 | Wed 06/03/13 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#59 completed (23.402 CR#152: Introduction of Inter-APN Routing Policies) | 23.402 | 51 | 26 |  |  | Mon 21/02/11 | Wed 27/02/13
3343 | 600047 | Stage 3 for Operator Policies for IP Interface Selection | OPIIS-CT | 2 | Rel-12 | C1 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130215 | - | LG Electronics | Jaehyun Kim (jaehyun7.kim@lge.com) | CP#62 completed. Specify Inter-APN Routing Policies for selecting an IP interface to route IP flows among a choice of available interfacES in CP-150both 3GPP and non-3GPP accesses | 24.302, 24.312 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
3344 | 520029 | Short Message Service (SMS) submit and delivery without MSISDN in IMS | SMSMI | 1 | Rel-12 | S2,C1,C4 | Wed 08/06/11 | Fri 06/12/13 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | Linked to Rel-7 SMSIP (Support of SMS over generic 3GPP IP access), Rel-11 SIMTC, Rel-12 TR 22.988 SA1 Study on alternatives to E.164 for MTC | Stage 2/3 | 52 | 27 |  |  | Thu 26/05/11 | Mon 18/11/13
3345 | 520129 | TR on Stage 2 for SMS submit and delivery without MSISDN in IMS | SMSMI-SA2TR | 2 | Rel-12 | S2 | Wed 08/06/11 | Wed 12/12/12 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | new 23.863 | 52 | 27 |  |  | Thu 26/05/11 | Thu 22/11/12
3346 | 520229 | Stage 2 for SMS submit and delivery without MSISDN in IMS | SMSMI-SA2 | 2 | Rel-12 | S2 | Mon 13/06/11 | Wed 12/12/12 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | 23.204, 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Sat 09/06/12
3347 | 590013 | Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 2 | Rel-12 | C1,C4 | Fri 01/03/13 | Fri 06/12/13 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS | Stage 3 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
3348 | 590113 | CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 3 | Rel-12 | C1 | Fri 01/03/13 | Fri 06/12/13 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed | 23.040, 24.341 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
3349 | 590213 | CT4 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 3 | Rel-12 | C4 | Fri 01/03/13 | Fri 06/09/13 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#61 completed | 23.008, 29.002, 29.305, 29.328, 29.338 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
3350 | 530042 | IMS-based Telepresence | IMS_TELEP | 1 | Rel-12 | S1,C1,C3,C4,IETF | Mon 22/03/10 | Tue 09/12/14 | 93% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified | Stage 1/2/3 | 53 | 27 |  |  | Tue 19/07/11 | Fri 08/06/12
3351 | 530142 | Stage 1 for IMS-based Telepresence | IMS_TELEP | 2 | Rel-12 | S1 | Thu 22/09/11 | Wed 20/06/12 | 100% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#56 completed. 2/4/15: acronym changed to IMS_TELEP | 22.228 | 53 | 27 |  |  | Tue 19/07/11 | Thu 02/04/15
3352 | 580001 | CT part for IMS Telepresence (Stage 2/3) | IMS_TELEP | 2 | Rel-12 | C1,C3,C4,IETF | Mon 22/03/10 | Tue 09/12/14 | 93% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 updated WID CP-140196=>CP-140624. 2/4/15: acronym changed to IMS_TELEP | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3353 | 580002 | TR on CT part of IMS Telepresence (Stage 2/3) | IMS_TELEP | 3 | Rel-12 | C1 | Fri 07/12/12 | Fri 13/06/14 | 100% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#64 completed. 2/4/15: acronym changed to IMS_TELEP | New 24.803 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3354 | 580003 | CT1 part of IMS Telepresence (Stage 3) | IMS_TELEP | 3 | Rel-12 | C1 | Fri 07/12/12 | Tue 09/12/14 | 100% | CP-140624 | CP-140616 | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 TS 24.103v100 for Information. Updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140616. Dec.14: 90->100%. 2/4/15: acronym changed to IMS_TELEP | 24.147, 24.166, 24.229, New 24.103 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3355 | 641001 | (IETF) Session Description Protocol (SDP) Offer/Answer Procedures For Stream Control Transmission Protocol (SCTP) over Datagram Transport Layer Security (DTLS) | IMS_TELEP | 3 | Rel-12 | C1-IETF | Mon 22/03/10 | Fri 05/12/14 | 90% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-mmusic-sctp-sdp).; 23/4/20: 50%->90; 9/4/21: RFC 8842 added; | draft-ietf-mmusic-sctp-sdp; RFC 8842 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3356 | 641002 | (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) | IMS_TELEP | 3 | Rel-12 | C1-IETF | Mon 22/03/10 | Fri 05/12/14 | 90% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-framework ); 9/4/21: RFC 8845 added; | draft-ietf-clue-framework; RFC 8845 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3357 | 641003 | (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) | IMS_TELEP | 3 | Rel-12 | C1-IETF | Mon 22/03/10 | Fri 05/12/14 | 90% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-datachannel); 9/4/21: RFC 8850 added; | draft-ietf-clue-datachannel; RFC 8850 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3358 | 641004 | (IETF) Session Signaling for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-signaling) | IMS_TELEP | 3 | Rel-12 | C1-IETF | Mon 22/03/10 | Fri 05/12/14 | 90% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-signaling); 9/4/21: RFC 8848 added; | draft-ietf-clue-signaling; RFC 8848 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3359 | 641005 | (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) | IMS_TELEP | 3 | Rel-12 | C1-IETF | Mon 22/03/10 | Fri 05/12/14 | 90% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-data-model-schema); 9/4/21: RFC 8846 added; | draft-ietf-clue-data-model-schema; RFC 8846 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3360 | 580004 | CT3 part of IMS Telepresence (Stage 3) | IMS_TELEP | 3 | Rel-12 | C3 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 completed. 2/4/15: acronym changed to IMS_TELEP | 29.165 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3361 | 610011 | CT4 part of IMS Telepresence (Stage 2/3) | IMS_TELEP | 3 | Rel-12 | C4 | Fri 13/09/13 | Tue 09/12/14 | 100% | CP-140624 | CP-140477 | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140477. Mar.15: 0->100%. 2/4/15: acronym changed to IMS_TELEP | 23.333, 29.333 | 61 | 31 |  |  | Sun 11/08/13 | Thu 02/04/15
3362 | 560020 | Group Communication System Enablers for LTE | GCSE_LTE | 1 | Rel-12 | S1,S2,S3,C3,C4,R3,C1 | Mon 18/06/12 | Fri 13/03/15 | 100% | SP-140433 | - | Nokia Networks | Juergen.Merkel@nsn.com | Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety | Stage 1/2/3 | 56 | 29 |  |  | Mon 14/05/12 | Sun 07/09/14
3363 | 560120 | Stage 1 for Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S1 | Mon 18/06/12 | Wed 19/06/13 | 100% | SP-140433 | - | Nokia Networks | Juergen.Merkel@nsn.com | SP#60 completed. TS 22.468 v100 for 1-step Approval | New 22.468 | 56 | 29 |  |  | Mon 14/05/12 | Sun 07/09/14
3364 | 590037 | TR on Architecture enhancements to support Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S2 | Thu 07/03/13 | Fri 07/03/14 | 100% | SP-140433 | - | Nokia Networks | rainer.liebhart@nsn.com | SP#63 completed. TR 23.768v200 for Approval | New 23.768 | 59 | 30 |  |  | Thu 21/02/13 | Sun 07/09/14
3365 | 590038 | Stage 2 for Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S2 | Tue 12/03/13 | Tue 16/09/14 | 100% | SP-140433 | - | Nokia Networks | rainer.liebhart@nsn.com | SP#65 completed. Updated WID SP-140113=>SP-140433. SP#63 TS 23.468v100 for 1-step Approval | New 23.468 | 59 | 30 |  |  | Thu 21/02/13 | Mon 15/09/14
3366 | 610135 | TR on Security for Group Communication System Enablers for LTE (Stage 2) | GCSE_LTE | 2 | Rel-12 | S3 | Thu 12/09/13 | Wed 18/06/14 | 100% | SP-140433 | - | Nokia Networks | anja.jerichow@nsn.com | SP#64 completed. TR 33.888v100 for 1-step Approval | New 33.888 | 61 | 31 |  |  | Tue 03/09/13 | Sun 07/09/14
3367 | 610035 | Security for Group Communication System Enablers for LTE (Stage 2) | GCSE_LTE | 2 | Rel-12 | S3 | Fri 13/09/13 | Wed 18/06/14 | 100% | SP-140433 | - | Nokia Networks | anja.jerichow@nsn.com | SP#64 completed | 33.246 | 61 | 31 |  |  | Tue 03/09/13 | Sun 07/09/14
3368 | 640010 | CT aspects of Group Communication System Enablers for LTE | GCSE_LTE-CT | 2 | Rel-12 | C3,C4,C1 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140559 | - | Nokia Networks | thomas.belling@nsn.com | CP#65 updated WID CP-140452=>C3-143199 (added CT1 part) | Stage 3 | 64 | 33 |  |  | Tue 10/06/14 | Sat 06/09/14
3369 | 640110 | CT3 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C3 | Fri 13/06/14 | Thu 11/09/14 | 100% | CP-140559 | - | Nokia Networks | thomas.belling@nsn.com | CP#65 completed. TS 29.468v200 for Approval | 29.212, 29.213, 29.214, 29.274, New 29.468 | 64 | 33 |  |  | Tue 10/06/14 | Sat 06/09/14
3370 | 640210 | CT4 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C4 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140559 | CP-140725 | Nokia Networks | thomas.belling@nsn.com | CP#65 completion 09/14=>12/14. Exception in CP-140725. Dec.14: 35->100 | 23.007, 23.008 | 64 | 33 |  |  | Tue 10/06/14 | Thu 04/12/14
3371 | 650008 | CT1 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C1 | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-140559 | CP-140614 | Nokia Networks | thomas.belling@nsn.com | CP#65 updated WID CP-140452=>CP-140559 (added CT1 part). Exception in CP-140614. Dec.14: 90->100% | 24.301 | 65 | 33 |  |  | Wed 30/07/14 | Thu 04/12/14
3372 | 640037 | Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM | 2 | Rel-12 | R3 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141035 | - | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | - | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
3373 | 640137 | Core part: Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM-Core | 3 | Rel-12 | R3 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141035 | RP-150081 | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | CD:Thu 11/12/14->Sun 15/03/15¦Compl:25%->80%¦Stat Rep: RP-141327->RP-141863 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141863->RP-150081 | 36.413 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
3374 | 560022 | Machine-Type and other mobile data applications Communications enhancements | MTCe | 1 | Rel-12 |  | Thu 10/12/09 | Thu 12/05/16 | 98% | SP-130327 | - | Intel | puneet.jain@intel.com | - | Stage 1/2/3 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3375 | 560021 | Stage 1 for Support for Interworking with M2M Service Enablement | MTCe-SIMSE | 2 | Rel-12 | S1 | Mon 18/06/12 | Wed 06/03/13 | 100% | SP-120436 | - | KPN | toon.norp@tno.nl | SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer) | 22.368 | 56 | 29 |  |  | Mon 14/05/12 | Tue 19/02/13
3376 | 570030 | Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance | MTCe-SRM | 2 | Rel-12 | S1 | Thu 13/09/12 | Wed 06/03/13 | 100% | SP-130105 | - | KPN | toon.norp@tno.nl | SP#59 completed. Updated WID SP-120541=>SP-130105 | 22.101, 22.368 | 57 | 29 |  |  | Mon 06/08/12 | Tue 19/02/13
3377 | 560722 | TR on Security aspects of Machine-Type Communications | MTCe-SA3TR | 2 | Rel-12 | S3 | Thu 10/12/09 | Fri 07/03/14 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TR 33.868v100 for 1-step Approval. Was Rel-10 UID_460023 (Security for NIMTC). Was Rel-11 UID_490028 (TR on Security aspects of MTC). SP#56 activity transferred to Rel-12 Feature MTCe | New 33.868 | 56 | 29 |  |  | Thu 16/08/12 | Thu 27/02/14
3378 | 560522 | Security and Privacy aspects for Machine-Type and other mobile data applications Communications enhancements (Stage 2) | MTCe-SA3 | 2 | Rel-12 | S3 | Fri 22/06/12 | Fri 07/03/14 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TS 33.187v100 for 1-step Approval | New 33.187 | 56 | 29 |  |  | Sat 02/06/12 | Thu 27/02/14
3379 | 560122 | BB1: Small Data and Device Triggering Enhancements (SDDTE) | MTCe-SDDTE | 2 | Rel-12 | S2,C4,C3 | Mon 18/06/12 | Thu 11/09/14 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | - | - | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3380 | 560622 | TR on Stage 2 BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE | 3 | Rel-12 | S2 | Mon 18/06/12 | Wed 11/12/13 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed. TR 23.887v200 for Approval | New 23.887 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3381 | 562122 | Stage 2 for BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE | 3 | Rel-12 | S2 | Tue 26/06/12 | Wed 11/12/13 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed | 23.682 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3382 | 630001 | Stage 3 for BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE-CT | 3 | Rel-12 | C4,C3 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#65 updated WID CP-140272=>CP-140489 | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
3383 | 630101 | CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | MTCe-SDDTE-CT | 4 | Rel-12 | C4 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#65 completed. Updated WID CP-140272=>CP-140489 | 29.002, 29.336, 23.008, 29.337, 29.338, 29.230 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
3384 | 630201 | CT3 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | MTCe-SDDTE-CT | 4 | Rel-12 | C3 | Wed 05/03/14 | Fri 13/06/14 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#64 completed | 29.368 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
3385 | 560222 | Deleted - BB2: Monitoring Enhancements (MONTE) | MTCe-MONTE | 2 | Rel-12 | S2 | Mon 18/06/12 | Wed 12/12/12 | 100% | SP-120438 | - | Intel | puneet.jain@intel.com | SP#58 stopped (at 20% completion) | 23.682 | 56 | 29 | SP-58 | PCG-30 | Fri 13/04/12 | Fri 14/12/12
3386 | 560322 | BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 2 | Rel-12 |  | Mon 18/06/12 | Thu 12/05/16 | 93% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | - | - | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3387 | 561622 | TR on Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 3 | Rel-12 | S2 | Mon 18/06/12 | Wed 11/12/13 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed. TR 23.887v200 for Approval | New 23.887 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3388 | 562322 | Stage 2 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 3 | Rel-12 | S2 | Tue 26/06/12 | Wed 11/12/13 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed | 23.060, 23.401, 23.682 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
3389 | 620007 | Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT | 3 | Rel-12 |  | Fri 06/12/13 | Tue 15/03/16 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | - | Stage 3 | 62 | 32 |  |  | Mon 18/11/13 | Mon 18/11/13
3390 | 620107 | CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT1 | 4 | Rel-12 | C1 | Fri 06/12/13 | Thu 11/09/14 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#65 completed | 24.008, 24.301 | 62 | 32 |  |  | Mon 18/11/13 | Mon 28/07/14
3391 | 620207 | Deleted - CT4 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT4 | 4 | Rel-12 | C4 | Mon 09/12/13 | Thu 11/09/14 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#65 stopped (no inpact on CT4) | 29.274, 29.060, 23.008 | 62 | 32 | CP-65 | PCG-33 | Mon 18/11/13 | Sun 25/05/14
3392 | 620307 | CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT6 | 4 | Rel-12 | C6 | Mon 09/12/13 | Tue 09/12/14 | 100% | CP-130714 | CP-140697 | Ericsson | mikael.wass@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140697¦June2015: Compl:90%->100 | 31.101, 31.102, 31.111 | 62 | 32 |  |  | Mon 18/11/13 | Mon 15/06/15
3393 | 690068 | UE Conformance Test Aspects - UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-UEConTest | 4 | Rel-12 | R5 | Tue 15/09/15 | Tue 15/03/16 | 100% | RP-151161 | - | Ericsson |  | tested: MTCe-UEPCOP was a REL-12 SA2 WI¦NAS over LTE and UTRA;1/1/16: Compl:0%->25%22/3/16: C |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
3394 | 650009 | Support of Power Saving Mode in GERAN | MTCe-UEPCOP-GERAN | 3 | Rel-12 | G1 | Mon 25/08/14 | Fri 29/08/14 | 100% | GP-140628 |  | Ericsson | sajal.kumar.das@ericsson.com | GP#63 approved WID and completed | 43.022 | 63 | 33 |  |  | Fri 29/08/14 | Fri 29/08/14
3395 | 700005 | Testing of Support of Power Saving Mode in GERAN | MTCe-UEPCOP_GERAN3new | 3 | Rel-12 | G3 | Wed 11/11/15 | Thu 12/05/16 | 10% | GP-151186 |  | Ericsson | sajal.kumar.das@ericsson.com | 7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new¦2/3/16: 0%->10 |  | 70 | 36 |  |  | Fri 29/08/14 | Wed 02/03/16
3396 | 560422 | Deleted - BB4: Group based MTC feature (GROUP) | MTCe-GROUP | 2 | Rel-12 | S2 | Wed 20/06/12 | Wed 12/12/12 | 100% | SP-120267 | - | KPN | Annemieke Kips | SP#58 stopped (at 25% completion) | 23.682 | 56 | 29 | SP-58 | PCG-30 | Fri 13/04/12 | Fri 14/12/12
3397 | 620043 | RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN | 2 | Rel-12 | R2,R3 | Mon 03/02/14 | Fri 12/09/14 | 100% | RP-140752 | - | ZTE | sergio.parolari@zte.com.cn | Triggered by TR 23.887 Machine Type and other mobile data applications Communications Enhancements (MTCe), TR 37.869 Study on Enhancements MTC and other Mobile Data Applications¦RAN aspects (FS_MTCe_RAN), Rel-11 TR 23.888 SIMTC | UTRA, LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
3398 | 620143 | Core part: RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN-Core | 3 | Rel-12 | R2,R3 | Mon 03/02/14 | Fri 12/09/14 | 100% | RP-140752 | RP-141096 | ZTE | sergio.parolari@zte.com.cn | RP#65 completed | 25.300, 25.304, 25.413, 36.300, 36.304, 36.413, 36.423 | 62 | 32 |  |  | Sat 07/12/13 | Mon 15/09/14
3399 | 600012 | Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | Sat 15/06/13 | Thu 15/12/16 | 100% | RP-130848 | - | Vodafone | eric.bouton@vodafone.com | Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE) | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
3400 | 600112 | Core part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Core | 2 | Rel-12 | R1,R2,R4 | Sat 15/06/13 | Mon 15/12/14 | 100% | RP-140522 | RP-142024 | Vodafone | eric.bouton@vodafone.com | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141221->RP-142024 | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3401 | 600212 | Perf. part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Perf | 2 | Rel-12 | R4 | Sat 15/06/13 | Mon 15/06/15 | 100% | RP-150940 | RP-150915 | Vodafone | eric.bouton@vodafone.com | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141221->RP-142024 1st Apr 15: Compl:65%->90% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-142024->RP-150149 03/07/15: Compl:90%->100% 03/07/15: WID: RP-14052 | 36.101, 36.104, 36.133 | 60 | 31 |  |  | Mon 17/06/13 | Thu 18/06/15
3402 | 670048 | UE Conformance Test Aspects - Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Thu 15/12/16 | 100% | RP-160069 |  | Ericsson |  | 03/07/15: Compl:0%->13% 03/07/15: WID: RP-150135->RP-150838 03/07/15: Stat Rep: ->RP-150833 29/09/15: Compl:13%->25% 29/09/15: Stat Rep: RP-150833->RP-151165 ¦1/1/16: Compl:25%->70% ¦1/1/16: CD:Tue 15/12/15->Tue 15/03/16 |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 20/12/16
3403 | 560024 | Policy and Charging Control for supporting fixed broadband access networks | P4C | 1 | Rel-12 | S2,S1,S5,C3,C1,C4 | Wed 20/06/12 | Fri 12/12/14 | 100% | SP-120443 | - | Huawei | marco.spini@huawei.com | Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work | Stage 1/2/3 | 56 | 29 |  |  | Fri 13/04/12 | Tue 08/01/13
3404 | 570031 | Stage 1 for Policy and Charging Support for Fixed Mobile Convergence | P4C-FMC | 2 | Rel-12 | S1 | Mon 10/09/12 | Wed 12/09/12 | 100% | SP-120542 | - | Huawei | amar.deol@huawei.com | SP#57 completed | 22.278 | 57 | 29 |  |  | Mon 06/08/12 | Tue 08/01/13
3405 | 560124 | BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F | 2 | Rel-12 | S2,S5,C3,C1,C4 | Wed 20/06/12 | Fri 12/12/14 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | - | - | 56 | 29 |  |  | Mon 04/06/12 | Tue 08/01/13
3406 | 560724 | TR on Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F-SA2TR | 3 | Rel-12 | S2 | Wed 20/06/12 | Fri 12/12/14 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#64 TR 23.896 was never sent for approval due to incomplete P4C BBs. SP#61 TR 23.896v100 for Information. Dec.14: 90->100%. Mar15: 23.896 for approval. | new 23.896 | 56 | 29 |  |  | Mon 04/06/12 | Fri 13/03/15
3407 | 562124 | Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F-SA2 | 3 | Rel-12 | S2 | Wed 20/06/12 | Wed 11/12/13 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#62 completed | 23.139, 23.203 | 56 | 29 |  |  | Mon 04/06/12 | Thu 28/11/13
3408 | 610012 | Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 3 | Rel-12 | C3,C1,C4 | Fri 06/09/13 | Fri 13/06/14 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | Stage 3 | 61 | 31 |  |  | Mon 12/08/13 | Wed 16/04/14
3409 | 610112 | CT3 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C3 | Fri 06/09/13 | Fri 13/06/14 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.212, 29.213, 29.215, 29.219 | 61 | 31 |  |  | Mon 12/08/13 | Wed 16/04/14
3410 | 620009 | CT1 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C1 | Fri 06/12/13 | Wed 05/03/14 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#63 completed | 24.302 | 62 | 32 |  |  | Tue 19/11/13 | Wed 29/01/14
3411 | 620010 | CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C4 | Fri 06/12/13 | Fri 13/06/14 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.273 | 62 | 32 |  |  | Tue 19/11/13 | Wed 16/04/14
3412 | 600042 | Policy and Charging Enforcement Function (PCEF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_P | 3 | Rel-12 | S5 | Fri 21/06/13 | Wed 17/09/14 | 100% | SP-130261 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#65 completed. Introduce Charging Characteristics in Convergent scenario, Include missing fixed user location information for NSWO | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | 60 | 31 |  |  | Sun 02/06/13 | Tue 26/08/14
3413 | 600043 | Traffic Detection Function (TDF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_T | 3 | Rel-12 | S5 | Mon 24/06/13 | Wed 18/06/14 | 100% | SP-130262 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | 60 | 31 |  |  | Sun 02/06/13 | Tue 10/06/14
3414 | 560224 | BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI | 2 | Rel-12 | S2 | Wed 20/06/12 | Wed 19/06/13 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | - | - | 56 | 29 |  |  | Mon 04/06/12 | Tue 08/01/13
3415 | 560824 | TR on Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI-SA2TR | 3 | Rel-12 | S2 | Wed 20/06/12 | Wed 19/06/13 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | new 23.839 | 56 | 29 |  |  | Mon 04/06/12 | Mon 17/06/13
3416 | 562224 | Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI-SA2 | 3 | Rel-12 | S2 | Wed 20/06/12 | Wed 19/06/13 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | 23.139, 23.203 | 56 | 29 |  |  | Mon 04/06/12 | Thu 06/06/13
3417 | 560324 | Deleted - BB3: Policy and Charging Control for 3GPP UEs connected to fixed broadband access network via S2b and S2c reference points for EPC routed traffic (P4C-S2bc) | P4C-S2bc | 2 | Rel-12 | S2 | Thu 21/06/12 | Wed 12/12/12 | 100% | SP-120445 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 0% completion) | 23.139, 23.203, new 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
3418 | 560424 | Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB) | P4C-HeNB | 2 | Rel-12 | S2 | Thu 21/06/12 | Wed 12/12/12 | 100% | SP-120278 | - | NEC | Stefan.Schmid@neclab.eu | SP#58 stopped (at 0% completion) | 23.139, 23.203, new 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
3419 | 560524 | Deleted - BB5: Policy and Charging Control for supporting Layer 2 traffic in fixed broadband access network (P4C-FL2) | P4C-FL2 | 2 | Rel-12 | S2 | Thu 21/06/12 | Wed 12/12/12 | 100% | SP-120279 | - | Huawei | marco.spini@huawei.com | SP#58 stopped (at 0% completion) | 23.139, 23.203, new 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
3420 | 560624 | Deleted - BB6: Policy and Charging Control for 3GPP UEs connected to fixed broadband access networks via S2a reference point for EPC routed traffic in convergence (P4C-TC) | P4C-TC | 2 | Rel-12 | S2 | Wed 20/06/12 | Wed 12/12/12 | 100% | SP-120280 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 30% completion) | 23.139, 23.203, new 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
3421 | 560025 | IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI | 1 | Rel-12 | S2,S1,C1,C3 | Wed 28/09/11 | Tue 09/12/14 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | Linked to Rel-11 IPXS Feature UID_470051 Advanced IP Interconnection of Services. This WI defines a generic framework for interconnecting with any type of IMS based network including IP-PBXs. | Stage 1/2/3 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
3422 | 560325 | Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SA1 | 2 | Rel-12 | S1 | Wed 28/09/11 | Wed 12/09/12 | 100% | SP-120862 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#57 completed. 22.228CR#0171 | 22.228 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
3423 | 560125 | TR on IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SATR | 2 | Rel-12 | S2,S1 | Mon 18/06/12 | Wed 19/06/13 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | new 23.897 | 56 | 29 |  |  | Fri 11/05/12 | Thu 06/06/13
3424 | 560225 | Stage 2 for IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SA2 | 2 | Rel-12 | S2 | Mon 25/06/12 | Wed 19/06/13 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | 23.228 | 56 | 29 |  |  | Fri 11/05/12 | Thu 06/06/13
3425 | 610007 | CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 2 | Rel-12 | C1,C3 | Fri 06/09/13 | Tue 09/12/14 | 100% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | - | Stage 3 | 61 | 31 |  |  | Sat 10/08/13 | Mon 03/03/14
3426 | 610107 | CT1 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 3 | Rel-12 | C1 | Fri 06/09/13 | Tue 09/12/14 | 100% | CP-140197 | CP-140607 | Deutsche Telekom | michael.kreipl@telekom.de | CP#65 completion 09/14=>12/14. Exception in CP-140607. Dec.14: 85->100% | 23.218, 24.229, 24.525 (transfer of ETSI 182 025) | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3427 | 610207 | CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 3 | Rel-12 | C3 | Fri 06/09/13 | Wed 11/06/14 | 100% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | CP#64 completed | 29.165 | 61 | 31 |  |  | Sat 10/08/13 | Wed 16/04/14
3428 | 560026 | WLAN Network Selection for 3GPP Terminals | WLAN_NS | 1 | Rel-12 | S2,S1,S3,C1 | Mon 18/06/12 | Tue 09/12/14 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | Evaluate and if needed enhance existing 3GPP solutions for WLAN network selection taking into account WFA Hotspot 2.0 solutions | Stage 1/2/3 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
3429 | 560126 | TR on Stage 2 for WLAN Network Selection for 3GPP Terminals | WLAN_NS-SATR | 2 | Rel-12 | S2,S1 | Mon 18/06/12 | Wed 11/12/13 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | New 23.865 | 56 | 29 |  |  | Fri 11/05/12 | Thu 28/11/13
3430 | 560226 | Stage 2 for WLAN Network Selection for 3GPP Terminals | WLAN_NS-SA2 | 2 | Rel-12 | S2 | Fri 22/06/12 | Wed 11/12/13 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | 23.402, 23.865 | 56 | 29 |  |  | Thu 22/11/12 | Thu 28/11/13
3431 | 580055 | Deleted - TR on Security Aspects of WLAN Network Selection for 3GPP Terminals | WLAN_Nsdel | 2 | Rel-12 | S3 | Thu 13/12/12 | Fri 07/03/14 | 100% | SP-120847 | - | Huawei | Lydia Xu (xuyixian@huawei.com) | SP#63 stopped (84% complete) | New 33.865 | 58 | 30 | CP-63 | PCG-32 | Fri 02/11/12 | Tue 04/03/14
3432 | 620005 | CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3) | WLAN_NS-CT | 2 | Rel-12 | C1 | Fri 06/12/13 | Tue 09/12/14 | 100% | CP-130712 | CP-140622 | Qualcomm | Amer Catovic, amerc@qualcomm.com | CP#65 completion 09/14=>12/14. CP#65 exception CP-140622. Dec.14: 95->100% | 24.302, 24.312 | 62 | 32 |  |  | Tue 19/11/13 | Thu 04/12/14
3433 | 570028 | Deleted - IMS Registration Control | IMS_RegCon | 1 | Rel-12 | S1,S2,C1,C4 | Tue 31/01/12 | Wed 11/12/13 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information) | Stage 1/2/3 | 57 | 29 | SP-62 | PCG-32 | Mon 06/08/12 | Tue 10/12/13
3434 | 570128 | Deleted - Stage 1 for IMS Registration Control | IMS_RegCon-del1 | 2 | Rel-12 | S1 | Tue 31/01/12 | Wed 12/09/12 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#57 completed | 22.228 | 57 | 29 | SP-62 | PCG-32 | Mon 06/08/12 | Tue 10/12/13
3435 | 580056 | Deleted - Stage 2 for IMS Registration Control | IMS_RegCon-del2 | 2 | Rel-12 | S2 | Thu 13/12/12 | Wed 11/12/13 | 100% | SP-120735 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 stopped at 50% completion | 23.228 | 58 | 30 | SP-62 | PCG-32 | Tue 13/11/12 | Tue 10/12/13
3436 | 600016 | Deleted - CT aspects of IMS registration control | IMS_RegCon-CT | 2 | Rel-12 | C1,C4 | Wed 19/06/13 | Wed 11/12/13 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | Stage 2/3 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
3437 | 600116 | Deleted - CT1 aspects of CT aspects of IMS registration control (Stage 2/3) | IMS_RegCon-CT1 | 3 | Rel-12 | C1 | Wed 19/06/13 | Wed 11/12/13 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 23.218, 24.229 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
3438 | 600216 | Deleted - CT4 aspects of CT aspects of IMS registration control (Stage 3) | IMS_RegCon-CT4 | 3 | Rel-12 | C4 | Wed 19/06/13 | Wed 11/12/13 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 29.228, 29.229, 23.008 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
3439 | 580059 | Proximity-based Services | ProSe | 1 | Rel-12 |  | Thu 13/12/12 | Thu 15/06/17 | 100% | SP-140574 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044 | Stage 1/2 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
3440 | 580159 | Stage 1 for Proximity-based Services | ProSe-SA1 | 2 | Rel-12 | S1 | Thu 13/12/12 | Wed 19/06/13 | 100% | SP-140574 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#60 completed | 22.115, 22.278 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
3441 | 580259 | TR on Stage 2 for Proximity-based Services | ProSe-SA2TR | 2 | Rel-12 | S2 | Thu 13/12/12 | Fri 07/03/14 | 100% | SP-140574 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#63 completed. TR 23.703v200 for Approval | New 23.703 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
3442 | 580359 | Stage 2 for Proximity-based Services | ProSe-SA2 | 2 | Rel-12 | S2 | Wed 19/12/12 | Wed 18/06/14 | 100% | SP-140574 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval | New 23.303 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
3443 | 590036 | Security for Proximity-based Services | ProSe-SA3 | 2 | Rel-12 | S3 | Wed 13/03/13 | Fri 12/12/14 | 100% | SP-140574 | SP-140584 | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 re-opened. Completion 06/14=>12/14. Exception in SP-140584. Updated WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). SP#64 completed. TS 33.303 v100 for 1-step Approval¦Aug2015: 90%->100 | 33.220, New 33.303 | 59 | 30 |  |  | Wed 20/02/13 | Fri 14/08/15
3444 | 651104 | (IETF) Security for Proximity-based Services (ietf-avtcore-srtp-aes-gcm) | ProSe | 2 | Rel-12 | S3-IETF | Fri 12/09/14 | Tue 09/12/14 | 100% | SP-140574 | - | Atle Monrad | atle.monrad@ericsson.com | Submitted to IESG for publication¦7/3/16: 75%->100; 9/4/21: RFC 7714 added; | RFC 7714 (was ietf-avtcore-srtp-aes-gcm); RFC 7714 | 65 | 33 |  |  | Mon 15/09/14 | Fri 09/04/21
3445 | 640039 | Charging Aspects of Proximity-based Services | ProSe-CH | 2 | Rel-12 | S5 | Thu 19/06/14 | Fri 13/03/15 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 exception in SP-140543. Mar15: 85->100% | Stage 2/3 | 64 | 33 |  |  | Fri 06/06/14 | Thu 05/03/15
3446 | 640139 | Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use | ProSe-CH-SA5TR | 3 | Rel-12 | S5 | Thu 19/06/14 | Fri 12/12/14 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100% | New 32.844 | 64 | 33 |  |  | Fri 06/06/14 | Fri 12/12/14
3447 | 640239 | Specification of Charging Aspects of Proximity-based Services | ProSe-CH-SA5 | 3 | Rel-12 | S5 | Thu 19/06/14 | Fri 13/03/15 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140543. SP#65 TR 32.277v100 for Information. Dec.14: CD: 09/14->03/15, 40->75%. Mar15: 75->100% | 32.240, 32.297, 32.298, 32.299, New 32.277 | 64 | 33 |  |  | Fri 06/06/14 | Thu 05/03/15
3448 | 630006 | CT aspects of Proximity-based Services (Stage 3) | ProSe-CT | 2 | Rel-12 |  | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#64 updated WID CP-140194=>CP-140290 | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Mon 03/03/14
3449 | 630106 | CT1 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C1 | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140290 | CP-140615 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100% | 24.301, 23.122, New TSs (24.333, 24.334) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3450 | 630206 | CT3 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C3 | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140290 | CP-140568 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. TS 29.343v100 for 1-step Approval. Exception in CP-140568. Dec.14: 90->100 | New 29.343 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3451 | 630306 | CT4 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C4 | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140290 | CP-140484 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. TS 29.344/5v100 for 1-step Approval. Exception in CP-140484. Dec.14: 90->100 | 29.272, 23.008, 23.003, New TSs (29.344, 29.345) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3452 | 630406 | CT6 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C6 | Thu 06/03/14 | Tue 09/12/14 | 100% | CP-140290 | CP-140695 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. Exception in CP-140695. Dec.14: 60->100% | 31.102 | 63 | 32 |  |  | Wed 29/01/14 | Wed 03/12/14
3453 | 630030 | LTE Device to Device Proximity Services | LTE_D2D_Prox | 2 | Rel-12 |  | Tue 11/03/14 | Thu 15/06/17 | 100% | RP-140955 | - | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | follow-up of TR 36.843 FS_LTE_D2D_Prox | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
3454 | 630130 | Core part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Core | 3 | Rel-12 | R1,R2,R4 | Sat 15/03/14 | Fri 13/03/15 | 100% | RP-142043 | RP-150094 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | ¦CD:Sat 15/03/14->Sun 15/03/15Compl:0%->95%¦CD:Fri 13/03/15->Sun 15/03/15¦Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:95%->100% 1st Apr 15: Stat Rep: RP-141894->RP-150094 | 36.101, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.306, 36.321, 36.322, 36.323, 36.331, 36.413, 36.423, New 36.877 | 63 | 32 |  |  | Mon 10/03/14 | Wed 01/04/15
3455 | 630230 | Perf. part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Perf | 3 | Rel-12 | R4 | Tue 11/03/14 | Tue 15/12/15 | 100% | RP-142043 | RP-151276 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | ¦CD:Sat 15/03/14->Sun 15/03/15¦Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:10%->25% 1st Apr 15: Stat Rep: RP-141894->RP-150094 03/07/15: Compl:25%->70% 03/07/15: Stat Rep: RP-150094->RP-150760 29/09/15: Compl:70%->95% 29/09/15: CD:Tue 15/09/15-> | 36.101, 36.133 | 63 | 32 |  |  | Mon 10/03/14 | Fri 01/01/16
3456 | 670046 | UE Conformance Test Aspects – LTE Device-to-Device Proximity Services | LTE_D2D_Prox-UEConTest | 3 | Rel-12 | R5 | Mon 16/03/15 | Thu 15/06/17 | 100% | RP-160382 |  | Qualcomm | svora@qti.qualcomm.com | rapporteur e-mail added 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150765 29/09/15: Compl:10%->30% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150765->RP-151280 1/1/16: Compl:30%->45% 1/1/16: WID: RP-1¦ ; |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 19/06/17
3457 | 580062 | Web Real Time Communication access to IMS | IMS_WebRTC | 1 | Rel-12 | S1,S2,S3 | Fri 14/12/12 | Thu 07/03/19 | 96% | SP-130707 | - | China Mobile | lulu@chinamobile.com | IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed. | Stage 1/2 | 58 | 30 |  |  | Fri 16/11/12 | Mon 09/09/13
3458 | 580162 | Stage 1 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S1 | Fri 14/12/12 | Wed 19/06/13 | 100% | SP-130707 | - | China Mobile | lulu@chinamobile.com | SP#60 completed | 22.101, 22.228 | 58 | 30 |  |  | Fri 16/11/12 | Mon 09/09/13
3459 | 600040 | TR on Stage 2 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S2 | Wed 19/06/13 | Wed 11/12/13 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#62 completed. TR 23.701v100 for Information & Approval | New 23.701 | 60 | 31 |  |  | Thu 06/06/13 | Mon 09/09/13
3460 | 600041 | Stage 2 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S2 | Wed 19/06/13 | Fri 07/03/14 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#63 completed | 23.228 | 60 | 31 |  |  | Thu 06/06/13 | Tue 04/02/14
3461 | 631001 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-overview) | IMS_WebRTC | 2 | Rel-12 | C1-IETF | Tue 25/06/13 | Fri 12/12/14 | 90% | SP-130707 | - | Uwe Rauschenbach | Uwe Rauschenbach | In WGLC. Mar15: responsible WG changed from S2-IETF; 23/4/20: 50%->90; 9/4/21: RFC 8825 added; | draft-ietf-rtcweb-overview; RFC 8825 | 63 | 32 |  |  | Mon 10/02/14 | Fri 09/04/21
3462 | 880055 | (IETF) WebRTC Data Channel Establishment Protocol (draft-ietf-rtcweb-data-protocol) | IMS_WebRTC | 2 | Rel-12 | C1-IETF | Tue 25/06/13 | Fri 12/12/14 | 90% | CP-140192 |  |  |  | 9/4/21: RFC 8832 added; | RFC 8832 | 88 | 45 |  |  | Fri 26/06/20 | Fri 09/04/21
3463 | 620067 | TR on Security for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S3 | Wed 11/12/13 | Wed 17/09/14 | 100% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#65 completed. TR 33.871v200 for Approval | New 33.871 | 62 | 32 |  |  | Thu 05/12/13 | Thu 04/09/14
3464 | 610036 | Security for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S3 | Thu 12/09/13 | Wed 18/06/14 | 100% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#64 completed | 33.203, 33.328 | 61 | 31 |  |  | Tue 03/09/13 | Mon 09/06/14
3465 | 630003 | CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 2 | Rel-12 | C1,C4,IETF | Wed 05/03/14 | Thu 07/03/19 | 97% | CP-140192 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | - | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Sat 06/09/14
3466 | 870070 | (IETF) Trickle ICE: Incremental Provisioning of Candidates for the Interactive Connectivity Establishment (ICE) Protocol (draft-ietf-ice-trickle) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | Thu 07/03/19 | Thu 07/03/19 | 90% |  |  |  |  | 9/4/21: RFC 8838 added; | RFC 8838 | 87 | 44 |  |  | Thu 23/04/20 | Fri 09/04/21
3467 | 870071 | (IETF) Trickle ICE: Incremental Provisioning of Candidates for the Interactive Connectivity Establishment (ICE) Protocol (draft-ietf-ice-trickle) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | Thu 07/03/19 | Thu 07/03/19 | 90% |  |  |  |  | 9/4/21: RFC 8838 added; | RFC 8838 | 87 | 44 |  |  | Thu 23/04/20 | Fri 09/04/21
3468 | 630103 | CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT1 | 3 | Rel-12 | C1 | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140192 | CP-140621 | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. Dec.14: 70->90%. 3/3/15: 100% cpltd. | 24.229, New 24.371 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/03/15
3469 | 641006 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-data-channel) | IMS_WebRTC-data | 3 | Rel-12 | C1-IETF | Thu 06/03/14 | Tue 09/12/14 | 90% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for publication. Mar15: In RFC-Editors queue; 9/4/21: RFC 8831 added; | draft-ietf-rtcweb-data-channel; RFC 8831 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3470 | 641007 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-stun-consent-freshness) | IMS_WebRTC-stun | 3 | Rel-12 | C1-IETF | Thu 06/03/14 | Tue 09/12/14 | 100% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Mar15: Publication requested¦7/3/16: 50%->100; 9/4/21: RFC 7675 added; | draft-ietf-rtcweb-stun-consent-freshness; RFC 7675 | 64 | 33 |  |  | Fri 06/06/14 | Fri 09/04/21
3471 | 651001 | Deleted - (IETF) Web Real Time Communication access to IMS (draft-ietf-sipcore-sip-authn) | IMS_WebRTC-yusef | 3 | Rel-12 | C1-IETF | Fri 12/09/14 | Fri 05/12/14 | 100% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress; 23/4/20: 25%->100 | draft-yusef-sipcore-sip-oaut. Replaced by replaced by draft-ietf-sipcore-sip-token-authnz | 65 | 33 |  |  | Tue 02/09/14 | Thu 23/04/20
3472 | 870067 | (IETF) Third-Party Token-based Authentication and Authorization for Session Initiation Protocol (SIP) (draft-ietf-sipcore-sip-token-authnz) | IMS_WebRTC-yusef | 3 | Rel-12 | C1-IETF | Fri 12/09/14 | Fri 05/12/14 | 80% |  |  |  |  | 9/4/21: RFC 8898 added; | RFC 8898 | 87 | 44 |  |  | Tue 02/09/14 | Fri 09/04/21
3473 | 660031 | Deleted - (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id) | IMS_WebRTC-holmb | 3 | Rel-12 | C1-IETF | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-140192 |  | christer.holmberg@ericsson.com |  | 7/3/16: 25%->100 since deleted (draft no longer needed). | draft-holmberg-sipcore-auth-id | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/03/16
3474 | 630203 | CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT4 | 3 | Rel-12 | C4 | Wed 05/03/14 | Tue 09/12/14 | 100% | CP-140192 | CP-140732 | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | CP#65 completion 09/14=>12/14. Exception in CP-140732. Dec.14: 30->80%. Mar. 15: 100% | 23.334, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Wed 04/03/15
3475 | 580063 | Usage Monitoring Control PCC enhancement | UMONC | 1 | Rel-12 | S2,C3 | Thu 13/12/12 | Fri 06/09/13 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 Stage 2 completed. Triggered by Rel-12 TR 23.858 Study on Usage Monitoring Control enhancement (UID_520035) | Stage 2/3 | 58 | 30 |  |  | Sun 18/11/12 | Wed 27/02/13
3476 | 580163 | Stage 2 for Usage Monitoring Control PCC enhancement | UMONC | 2 | Rel-12 | S2 | Thu 13/12/12 | Wed 06/03/13 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System) | 23.203 | 58 | 30 |  |  | Sun 18/11/12 | Wed 27/02/13
3477 | 600048 | CT3 aspects of Usage Monitoring Control PCC enhancement (Stage 3) | UMONC-CT3 | 2 | Rel-12 | C3 | Fri 14/06/13 | Fri 06/09/13 | 100% | CP-130396 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#61 completed. 2/4/15: acronym changed to "UMONC-CT3" | 29.212, 29.214, 29.215 | 60 | 31 |  |  | Wed 29/05/13 | Thu 02/04/15
3478 | 590039 | Application Based Charging | ABC | 1 | Rel-12 | S2,S5,C3 | Thu 07/03/13 | Wed 18/06/14 | 100% | SP-130328 | - | Allot | Alla Goldner (agoldner@allot.com) | Triggered by TR 23.800 Study on Application Based Charging (FS_ABC) UID_560038 | Stage 2/3 | 59 | 30 |  |  | Thu 21/02/13 | Thu 06/06/13
3479 | 590139 | Stage 2 for Application Based Charging | ABC-SA2 | 2 | Rel-12 | S2 | Thu 07/03/13 | Wed 19/06/13 | 100% | SP-130328 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#60 completed | 23.203 | 59 | 30 |  |  | Thu 21/02/13 | Thu 25/07/13
3480 | 600011 | Charging for Application Based Charging | ABC-CT5 | 2 | Rel-12 | S5 | Wed 19/06/13 | Wed 18/06/14 | 100% | SP-130328 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | 32.240, 32.251, 32.296, 32.298, 32.299 | 60 | 31 |  |  | Wed 29/05/13 | Tue 10/06/14
3481 | 600049 | CT3 aspects of Application Based Charging (Stage 3) | ABC-CT3 | 2 | Rel-12 | C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130353 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#62 completed | 29.212, 29.213, 29.214, 29.215, 29.219 | 60 | 31 |  |  | Wed 29/05/13 | Mon 21/10/13
3482 | 610038 | Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG | 1 | Rel-12 | S2,C1,C4 | Mon 09/09/13 | Tue 09/12/14 | 100% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | - | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
3483 | 610138 | Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-SA2 | 2 | Rel-12 | S2 | Wed 11/09/13 | Fri 07/03/14 | 100% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | SP#63 completed | 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Tue 04/02/14
3484 | 610009 | Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 2 | Rel-12 | C1,C4 | Mon 09/09/13 | Tue 09/12/14 | 100% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#62 updated WID CP-130580=>CP-130715 | Stage 3 | 61 | 31 |  |  | Sat 10/08/13 | Thu 28/11/13
3485 | 610109 | CT1 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 3 | Rel-12 | C1 | Mon 09/09/13 | Tue 09/12/14 | 100% | CP-130715 | CP-140608 | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#65 completion 09/14=>12/14. Exception in CP-140608. TS 24.244 v200 for Approval. Dec.14: 95->100% | 24.302, New 24.244 (WLAN control plane protocol for trusted WLAN access to EPC) | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3486 | 610209 | CT4 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 3 | Rel-12 | C4 | Mon 09/09/13 | Thu 11/09/14 | 100% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#65 completed | 29.273, 29.274, 29.275 | 61 | 31 |  |  | Sat 10/08/13 | Mon 28/07/14
3487 | 610039 | Optimized Offloading to WLAN in 3GPP-RAT Mobility | WORM | 1 | Rel-12 | S2,C1 | Thu 12/09/13 | Fri 13/06/14 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB) | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
3488 | 610139 | Stage 2 for Optimized Offloading to WLAN in 3GPP-RAT Mobility | WORM-SA2 | 2 | Rel-12 | S2 | Thu 12/09/13 | Wed 11/12/13 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#62 completed | 23.272, 23.401, 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Thu 28/11/13
3489 | 620003 | CT aspects of Optimized Offloading to WLAN in 3GPP-RAT Mobility (Stage 3) | WORM-CT | 2 | Rel-12 | C1 | Fri 06/12/13 | Fri 13/06/14 | 100% | CP-140109 |  | Intel | Chen-ho Chin (chen-hox.chin@intel.com) | CP#64 completed. Stage 3 enabling differentiation/prioritization of 3GPP RATs relative to WLAN for traffic flow routing based on Inter-System Routing Policies | 24.302, 24.312 | 62 | 32 |  |  | Mon 18/11/13 | Mon 26/05/14
3490 | 610040 | Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN | 1 | Rel-12 | S2,C3,C1,C4 | Thu 12/09/13 | Thu 11/09/14 | 100% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
3491 | 610140 | Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-SA2 | 2 | Rel-12 | S2 | Thu 12/09/13 | Fri 07/03/14 | 100% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | SP#63 completed | 23.203, 23.228, 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Tue 04/02/14
3492 | 620008 | CT aspects of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case (Stage 3) | NETLOC_TWAN-CT | 2 | Rel-12 | C3,C1,C4 | Fri 06/12/13 | Thu 11/09/14 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | - | Stage 3 | 62 | 32 |  |  | Tue 19/11/13 | Tue 19/11/13
3493 | 620108 | CT3 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C3 | Fri 06/12/13 | Fri 13/06/14 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#64 completed | 29.212, 29.214 | 62 | 32 |  |  | Tue 19/11/13 | Wed 16/04/14
3494 | 620208 | CT1 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C1 | Mon 09/12/13 | Thu 11/09/14 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#65 completed | 24.229 | 62 | 32 |  |  | Tue 19/11/13 | Mon 28/07/14
3495 | 620308 | CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C4 | Fri 06/12/13 | Thu 11/09/14 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#65 completed | 29.273, 29.274, 29.275, 29.328, 29.329 | 62 | 32 |  |  | Tue 19/11/13 | Mon 28/07/14
3496 | 620061 | Core Network Overload - User Location Information reporting improvement | CNO_ULI | 1 | Rel-12 | S2,C3,C4,S5 | Wed 11/12/13 | Wed 17/09/14 | 100% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | - | Stage 2/3 | 62 | 32 |  |  | Thu 28/11/13 | Sun 28/09/14
3497 | 620161 | Stage 2 for Core Network Overload - User Location Information reporting improvement | CNO_ULI-SA2 | 2 | Rel-12 | S2 | Wed 11/12/13 | Fri 07/03/14 | 100% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#63 completed | 23.060, 23.203, 23.401 | 62 | 32 |  |  | Thu 28/11/13 | Tue 04/02/14
3498 | 650017 | Charging aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CH | 2 | Rel-12 | S5 | Mon 15/09/14 | Wed 17/09/14 | 100% | SP-140541 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#65 New WID approved & completed. Introduction of Presence Reporting Areas for Charging | 32.251, 32.298, 32.299 | 65 | 33 |  |  | Sun 24/08/14 | Wed 10/09/14
3499 | 630004 | CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 2 | Rel-12 | C3,C4 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | Specify Stage 3 procedures to support the ULI signalling optimizations | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Wed 29/01/14
3500 | 630104 | CT3 part of CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 3 | Rel-12 | C3 | Wed 05/03/14 | Fri 13/06/14 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#64 completed | 29.212, 29.213 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
3501 | 630204 | CT4 part of CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 3 | Rel-12 | C4 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#65 completed | 23.008, 29.060, 29.274 | 63 | 32 |  |  | Wed 29/01/14 | Mon 28/07/14
3502 | 560028 | Rel-12 Security small Enhancements | SEC12 | 1 | Rel-12 | S3 | Wed 23/03/11 | Wed 17/09/14 | 100% | - | - | - | - | SEC12 is an umbrella Feature for Security related TEI12 type of changes that are not part of any other dedicated feature | Stage 2/3 | 56 | 29 |  |  | Sat 02/06/12 | Thu 04/09/14
3503 | 510054 | Security aspects of Public Warning System | PWS_Sec | 1 | Rel-12 | S3,S1 | Wed 23/03/11 | Wed 17/09/14 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | - | - | 51 | 26 |  |  | Sat 02/06/12 | Mon 09/06/14
3504 | 560029 | Stage 1 for Protection against false PWS Warning Notifications | PWS_Sec-SA1 | 2 | Rel-12 | S1 | Fri 15/06/12 | Wed 12/09/12 | 100% | SP-120433 | - | Vodafone | adrian.neal@vodafone.com | SP#57 completed. Specify reqs to protect against false PWS Warning Notifications (Optional as not all regions/countries require this functionality). WID covers all objectivES in CP-150SA3 PWS_Sec Feature-level WID replacing the original Stage 1 UID_510154 | 22.268 | 56 | 29 |  |  | Thu 07/06/12 | Tue 07/08/12
3505 | 510354 | TR on SA3 part for Security aspects of Public Warning System | PWS_Sec-SA3TR | 2 | Rel-12 | S3 | Wed 23/03/11 | Wed 17/09/14 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#65 completed. TR 33.969v100 for 1-step Approval. Former TR 33.869 changed to 33.969. | New 33.869 changed to 33.969 | 51 | 26 |  |  | Sat 02/06/12 | Thu 04/09/14
3506 | 511354 | Deleted - SA3 part for Security aspects of Public Warning System | PWS_Sec-del1 | 2 | Rel-12 | S3 | Wed 30/03/11 | Wed 18/06/14 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#64 stopped | New 33.269 | 51 | 26 | SP-64 | PCG-33 | Sat 02/06/12 | Mon 09/06/14
3507 | 510154 | Deleted - Stage 1 for Security aspects of Public Warning System | PWS_Sec-del2 | 2 | Rel-12 | S1 | Wed 23/03/11 | Wed 20/06/12 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. | 22.268 | 51 | 26 | SP-56 | PCG-29 | Sat 02/06/12 | Tue 26/06/12
3508 | 510254 | Deleted - Stage 2 for Security aspects of Public Warning System | PWS_Sec-del3 | 2 | Rel-12 | S2 | Wed 23/03/11 | Wed 21/09/11 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#53 work stopped as already done in previous releases | 23.401 | 51 | 26 | SP-53 | PCG-27 | Sat 02/06/12 | Mon 20/02/12
3509 | 510454 | Deleted - CT1 part for Security aspects of Public Warning System | PWS_Sec-del4 | 2 | Rel-12 | C1 | Fri 25/03/11 | Wed 20/06/12 | 100% | SP-120434 | - | ST-Ericsson | mikael.wass@ericsson.com | TSG#56 work stopped. SP#56 updated WID SP-110223=>SP-120334 (removed all but SA3 impacted specs) | 23.041 | 51 | 26 | SP-56 | PCG-29 | Sat 02/06/12 | Fri 08/06/12
3510 | 510554 | Deleted - RAN2 part for Security aspects of Public Warning System | PWS_Sec-del5 | 2 | Rel-12 | R2 | Fri 25/03/11 | Fri 16/09/11 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | RP#53 work stopped as no WI in RAN | 36.331 | 51 | 26 | RP-53 | PCG-27 | Sat 02/06/12 | Mon 20/02/12
3511 | 520031 | Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2) | Web_GBA | 1 | Rel-12 | S3 | Wed 08/06/11 | Thu 20/06/13 | 100% | SP-120890 | - | Nokia | Silke.Holtmanns@nokia.com | SP#60 completed | 33.220, 33.222, New 33.823 | 52 | 27 |  |  | Tue 17/05/11 | Mon 01/07/13
3512 | 560030 | Extended IMS media plane security features | eMEDIASEC | 1 | Rel-12 | S3,C4,C1,C3,IETF | Wed 20/06/12 | Tue 09/12/14 | 97% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC) | Stage 2/3 | 56 | 29 |  |  | Sat 02/06/12 | Tue 19/02/13
3513 | 560130 | SA3 part of Extended IMS media plane security features (Stage 2) | eMEDIASEC-SA3 | 2 | Rel-12 | S3 | Wed 20/06/12 | Wed 18/06/14 | 100% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#64 completed | 33.328 | 56 | 29 |  |  | Sat 02/06/12 | Tue 10/06/14
3514 | 611003 | (IETF) SA3 part of Extended IMS media plane security features (RFC 7345) | eMEDIASECSA3IETF | 2 | Rel-12 | S3-IETF | Wed 20/06/12 | Fri 12/09/14 | 100% | SP-120447 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | SP#65 completed | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 61 | 31 |  |  | Mon 23/09/13 | Tue 02/09/14
3515 | 580005 | CT aspects of Extended IMS media plane security features (Stage 2/3) | eMEDIASEC-CT | 2 | Rel-12 | C4,C1,C3,IETF | Thu 13/12/12 | Tue 09/12/14 | 95% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | Stage 2/3 | 58 | 30 |  |  | Wed 14/11/12 | Tue 19/11/13
3516 | 600051 | TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects | eMEDIASEC-CT | 3 | Rel-12 | C4 | Thu 13/12/12 | Thu 11/09/14 | 100% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed. TR 29.828v200 for Approval. 2/4/15: acronym changed to eMEDIASEC-CT | New 29.828 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
3517 | 580006 | CT4 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C4 | Wed 19/12/12 | Tue 09/12/14 | 100% | CP-130597 | CP-140479 | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completion 09/14=>12/14. Exception in CP-140479. Dec.14: 90->100. 2/4/15: acronym changed to eMEDIASEC-CT | 23.334, 29.334, 29.238, 23.333, 29.333 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
3518 | 621001 | (IETF) CT4 part of Extended IMS media plane security features (RFC 7345) | eMEDIASEC-CT | 3 | Rel-12 | C4-IETF | Tue 18/12/12 | Thu 11/09/14 | 100% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 62 | 32 |  |  | Wed 27/11/13 | Thu 02/04/15
3519 | 641009 | (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-mmusic-sdp-for-gw) | eMEDIASEC-CT | 3 | Rel-12 | C4-IETF | Thu 12/06/14 | Tue 09/12/14 | 0% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Work in progress. 2/4/15: acronym changed to eMEDIASEC-CT¦22/3/18: 100%->0 | draft-schwarz-mmusic-sdp-for-gw | 64 | 33 |  |  | Thu 12/06/14 | Thu 22/03/18
3520 | 580007 | CT1 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C1 | Thu 13/12/12 | Thu 11/09/14 | 100% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | 23.218, 24.147, 24.229, 24.247 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
3521 | 621002 | (IETF) CT1 part of Extended IMS media plane security features (RFC 7345) | eMEDIASEC-CT | 3 | Rel-12 | C1-IETF | Thu 06/03/14 | Thu 11/09/14 | 100% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 62 | 32 |  |  | Wed 27/11/13 | Thu 02/04/15
3522 | 580008 | CT3 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C3 | Wed 19/12/12 | Tue 09/12/14 | 100% | CP-130597 | CP-140569 | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completion 06/14=>12/14. Level 100%=>80%. Exception in CP-140569. CP#64 completed. Dec.14: 80->100. 2/4/15: acronym changed to eMEDIASEC-CT | 29.162 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
3523 | 570032 | Lawful Interception in the 3GPP Rel-12 | LI12 | 1 | Rel-12 | S3 | Mon 17/09/12 | Fri 12/12/14 | 100% | SP-130650 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | 3/3/15: 75->100% | 33.106, 33.107, 33.108 | 57 | 29 |  |  | Fri 31/08/12 | Tue 03/03/15
3524 | 580064 | Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | TURAN | 1 | Rel-12 | S3,C1 | Thu 13/12/12 | Wed 18/06/14 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | Linked to Rel-12 SMURFs. Related to TS 22.278 (EPS) cl.7.1.8 Service Reachability (Firewall traversal for IP based services for non-3GPP access), TS 22.228 (IMS) cl.5 (support Firewall traversal), TR 33.830 (Study on Firewall traversal) | Stage 2/3 | 58 | 30 |  |  | Mon 12/11/12 | Wed 20/02/13
3525 | 580164 | SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | TURAN-SA3 | 2 | Rel-12 | S3 | Thu 13/12/12 | Wed 18/06/14 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#64 completed | 33.203, 33.402 | 58 | 30 |  |  | Mon 12/11/12 | Mon 09/06/14
3526 | 600050 | CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3) | TURAN-CT | 2 | Rel-12 | C1 | Fri 14/06/13 | Fri 13/06/14 | 100% | CP-130716 | - | Huawei | Haitao Wei (weihaitao@huawei.com) | CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs | 24.229, 24.302, New 24.322 | 60 | 31 |  |  | Tue 28/05/13 | Mon 26/05/14
3527 | 620065 | Specification of the TUAK Algorithm Set | STAS | 1 | Rel-12 | S3 | Mon 09/12/13 | Wed 18/06/14 | 100% | SP-140814 | - | Vodafone | aguibou.barry@vodafone.com | SP#64 completed. Triggered by SP-130602 LS from ETSI SAGE (TUAK as alternative to Milenage). 12/14: new TS added | New TSs: 35.231, 35.232, 35.233, 35.9nn, 35.9nn, 35.9nn | 62 | 32 |  |  | Fri 22/11/13 | Fri 12/12/14
3528 | 470030 | Codec for Enhanced Voice Services | EVS_codec | 1 | Rel-12 | S4,S1,C4,C1,C3 | Thu 25/03/10 | Tue 15/03/16 | 100% | SP-140151 | - | Huawei | lei.miao@huawei.com | Triggered by UID_370045 Study on enhanced voice service requirements for EPS (TR 22.813) | - | 47 | 24 |  |  | Wed 10/03/10 | Thu 27/02/14
3529 | 470031 | Stage 1 for Codec for Enhanced Voice Services | EVS_codec-SA1 | 2 | Rel-12 | S1 | Thu 25/03/10 | Thu 25/03/10 | 100% | SP-140007 | - | Huawei | lei.miao@huawei.com | SP#47 completed | 22.173 | 47 | 24 |  |  | Wed 10/03/10 | Mon 22/03/10
3530 | 470032 | Stage 2/3 for Codec for Enhanced Voice Services | EVS_codec-SA4 | 2 | Rel-12 | S4 | Thu 25/03/10 | Fri 12/12/14 | 100% | SP-140151 | SP-140467 | Huawei | lei.miao@huawei.com | SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). Dec.14: 90->95 | 26.114, New (26.441, 26.442, 26.443, 26.444, 26.445, 26.446, 26.447, 26.448, 26.449, 26.450, 26.451) | 47 | 24 |  |  | Wed 10/03/10 | Fri 26/06/15
3531 | 470132 | TR on Performance characterization of Codec for Enhanced Voice Services | EVS_codec-SA4TR | 2 | Rel-12 | S4 | Thu 25/03/10 | Fri 12/12/14 | 100% | SP-140151 | SP-140467 | Huawei | lei.miao@huawei.com | SP#65 completion 09/14=>12/14. Ongoing TR 26.952 EVS Codec Performance Characterization. Exception in SP-140467 | New 26.952 | 47 | 24 |  |  | Wed 10/03/10 | Fri 26/06/15
3532 | 650005 | CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 2 | Rel-12 | C4,C1,C3 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140800 | - | Nokia Networks | Jan.Kall@nsn.com | Stage 3¦WID: CP-140492-> CP-140800 |  | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
3533 | 650105 | CT4 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C4 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140800 | CP-140478 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140478. Dec.14: 0->100¦WID: CP-140492-> CP-140800 | 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
3534 | 650205 | CT1 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C1 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140800 | CP-140618 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140618. Dec.14: 0->100%¦WID: CP-140492-> CP-140800 | 24.229 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
3535 | 650305 | CT3 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C3 | Tue 16/09/14 | Tue 09/12/14 | 100% | CP-140800 | CP-140560 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800 | 29.163, 29.292 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
3536 | 670050 | UE Conformance Test Aspects - Codec for Enhanced Voice Services (EVS) | EVS_codec-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150836 | RP-151164 | Ericsson |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150137->RP-150836 03/07/15: Stat Rep: ->RP-150831 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150831->RP-1511641/1/16: Compl:75%->95%1/1/16: CD:Tue 15/12/15->Tue 15/03/16; |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3537 | 560040 | Coordination of Video Orientation | CVO | 1 | Rel-12 | S4,C4,C1,C3 | Thu 07/06/12 | Fri 06/12/13 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | CP#62 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | - | 56 | 29 |  |  | Thu 07/06/12 | Tue 19/11/13
3538 | 560140 | SA4 part of Coordination of Video Orientation | CVO-SA4 | 2 | Rel-12 | S4 | Thu 07/06/12 | Wed 06/03/13 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | 26.114, 26.141, 26.234, 26.346 | 56 | 29 |  |  | Thu 07/06/12 | Sat 16/02/13
3539 | 600006 | CT aspects of Coordination of Video Orientation | CVO-CT | 2 | Rel-12 | C4,C1,C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | Complete CVO support (both, basic 2 bit orientation and additional option for extra 6 bit granularity) within CN protocols/procedures for IMS nodes, e.g. IMS ALG/AGW,IBCF/TrGW,MRFC/MRFP & add support of CVO-related SDP attributes to be negotiated by UE | Stage 2/3 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3540 | 600106 | CT4 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C4 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Tue 28/05/13 | Wed 29/01/14
3541 | 600206 | CT1 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C1 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
3542 | 600306 | CT3 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
3543 | 570033 | High Efficiency Video Coding | HEVC | 1 | Rel-12 | S4,IETF | Wed 12/09/12 | Fri 05/12/14 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | Specify the support of HEVC in 3GPP services (PSS, DASH, MTSI, MMS, MBMS, IMS Messaging and Presence) | - | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
3544 | 570133 | TR on Evaluation of High Efficiency Video Coding for 3GPP Services | HEVC-SA4TR | 2 | Rel-12 | S4 | Wed 12/09/12 | Thu 19/06/14 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed. TR 26.906v200 for Approval | New 26.906 | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
3545 | 570233 | High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI, IMS Messaging and Presence | HEVC-SA4 | 2 | Rel-12 | S4 | Mon 17/09/12 | Wed 18/06/14 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed | 26.114, 26.140, 26.141, 26.234, 26.244, 26.247, 26.346 | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
3546 | 631002 | (IETF) High Efficiency Video Coding | HEVC-SA4IETF | 2 | Rel-12 | S4-IETF | Mon 17/09/12 | Fri 05/12/14 | 100% | SP-130569 | - | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | Submitted to IESG for publication. 7/10/15: Rapporteur added¦7/3/16: 50%->95¦13/6/16: 95%->100 | draft-ietf-payload-rtp-h265=>RFC7798 | 63 | 32 |  |  | Mon 10/02/14 | Mon 13/06/16
3547 | 580065 | Mobile stereoscopic 3D services extensions | M3DV_Ext | 1 | Rel-12 | S4 | Wed 12/12/12 | Wed 11/09/13 | 100% | SP-120768 | - | Huawei | lukasz.kondrad@huawei.com | SP#61 completed. Related to Rel-11 Study On Mobile 3D Video Coding (FS_M3DVC) TR 26.905 and Rel-11 Mobile 3D Video Coding (M3DVC) | 26.114, 26.245, 26.247, 26.430 | 58 | 30 |  |  | Mon 12/11/12 | Wed 24/07/13
3548 | 580066 | IMS-based Streaming and Download Delivery Enhancements | IMS_SDE | 1 | Rel-12 | S4 | Wed 12/12/12 | Fri 07/03/14 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | Provide an extension of IMS based PSS and MBMS user services | - | 58 | 30 |  |  | Mon 12/11/12 | Fri 19/04/13
3549 | 580166 | TR on IMS-based Streaming and Download Delivery Enhancements | IMS_SDE-SA4TR | 2 | Rel-12 | S4 | Wed 12/12/12 | Fri 07/03/14 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Identify use cases and requirements based on Rel-10/11 PSS and MBMS functionality to be addressed for IMS-based streaming and download enhancements | new 26.827 | 58 | 30 |  |  | Mon 12/11/12 | Wed 29/01/14
3550 | 580266 | Specification on IMS-based Streaming and Download Delivery Enhancements | IMS_SDE-SA4 | 2 | Rel-12 | S4 | Thu 13/12/12 | Fri 07/03/14 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Develop procedures towards enabling the IMS-based extensions of the identified use casES in CP-150TS 26.237. Refine existing MBMS download procedures to enable IMS-based MBMS file repair with the use of conventional HTTP web servers. | 26.237 | 58 | 30 |  |  | Mon 12/11/12 | Wed 29/01/14
3551 | 580067 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE | ART_LTE | 1 | Rel-12 | S4 | Wed 12/12/12 | Fri 12/12/14 | 100% | SP-120769 | - | Qualcomm | Andre Schevciw (aschevci@qualcomm.com) | Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods | Stage 3 | 58 | 30 |  |  | Mon 12/11/12 | Fri 19/04/13
3552 | 580167 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects | ART_LTE-NBWB | 2 | Rel-12 | S4 | Wed 12/12/12 | Wed 11/12/13 | 100% | SP-120771 | - | Sony Mobile Communications | Peter.Isberg@sony.com | SP#62 completed | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Mon 18/11/13
3553 | 580267 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects | ART_LTE-UED | 2 | Rel-12 | S4 | Wed 12/12/12 | Wed 17/09/14 | 100% | SP-120770 | - | AT&T, Orange | luisa.marchetto@att.com, stephane.ragot@orange.com | SP#65 completed | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Wed 13/08/14
3554 | 580367 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - Super wideband and fullband aspects | ART_LTE-SUPER | 2 | Rel-12 | S4 | Wed 12/12/12 | Fri 12/12/14 | 100% | SP-120772 | SP-140470 | Sony Mobile Communications | peter.isberg@sonymobile.com | SP#65 completion 09/14=>12/14. Exception in SP-140470. Dec.14: 65->100 | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Wed 03/12/14
3555 | 590043 | MBMS Improvements | MI | 1 | Rel-12 | S4 | Wed 06/03/13 | Fri 12/12/14 | 100% | SP-130024 | SP-140471 | Ericsson | eric.turcotte@ericsson.com | Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description |  | 59 | 30 |  |  | Wed 20/02/13 | Fri 05/09/14
3556 | 590343 | TR on Enhanced MBMS Operation | MI-EMOTR | 2 | Rel-12 | S4 | Wed 06/03/13 | Fri 12/12/14 | 100% | SP-140212 | SP-140471 | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.848v100 for Information. Dec.14: 85->100. | New 26.848 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
3557 | 590143 | Enhanced MBMS Operation | MI-EMO | 2 | Rel-12 | S4 | Wed 06/03/13 | Fri 12/12/14 | 100% | SP-140212 | SP-140471 | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 85->100 | 26.247, 26.346 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
3558 | 590443 | TR on MBMS operation on Demand | MI-MooDTR | 2 | Rel-12 | S4 | Wed 06/03/13 | Fri 12/12/14 | 100% | SP-130026 | SP-140471 | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.849v100 for Information. Dec.14: 75->100 | New 26.849 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
3559 | 590243 | MBMS operation on Demand | MI-MooD | 2 | Rel-12 | S4 | Wed 06/03/13 | Fri 12/12/14 | 100% | SP-130026 | SP-140471 | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 75->100 | 26.346 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
3560 | 590044 | End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI | 1 | Rel-12 | S4 | Wed 06/03/13 | Mon 14/09/15 | 100% | SP-140600 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Tue 09/09/14
3561 | 670098 | S4 aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI | 2 | Rel-12 | S4 | Wed 06/03/13 | Tue 16/09/14 | 100% | SP-140600 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Tue 09/09/14
3562 | 600007 | CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 2 | Rel-12 | C3,C1,C4 | Fri 21/06/13 | Mon 14/09/15 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Stage 2/3. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | Stage 2/3 | 60 | 31 |  |  | Wed 20/02/13 | Tue 05/05/15
3563 | 600107 | CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C3 | Fri 21/06/13 | Mon 14/09/15 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Dec.14: CD: 09/14->09/15. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 29.162, 29.163, 29.213, 29.214 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
3564 | 600207 | CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C1 | Fri 21/06/13 | Fri 12/09/14 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 24.229 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
3565 | 600307 | CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C4 | Fri 21/06/13 | Fri 12/09/14 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
3566 | 620066 | Video Coding Enhancements in IMS Messaging and Presence | VCEIMP | 1 | Rel-12 | S4 | Wed 11/12/13 | Fri 07/03/14 | 100% | SP-130579 | - | Ericsson | frederic.gabin@ericsson.com | SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141 | 26.141 | 62 | 32 |  |  | Fri 29/11/13 | Wed 29/01/14
3567 | 640057 | Video Telephony Robustness Improvements | VTRI | 1 | Rel-12 | S4 | Wed 18/06/14 | Tue 16/09/14 | 100% | SP-140218 | - | Qualcomm | Muhammed Coban (mcoban@qti.qualcomm.com) | SP#65 completed. Linked to E2EMTSI (End-to-End Multimedia Telephony Service for IMS extensions). Add Reqs&guidelines for video telephony robustness to improve service perf. for PLI, Generic NACK, and FIR messages within overall bitrate limit | 26.114 | 64 | 33 |  |  | Fri 06/06/14 | Wed 13/08/14
3568 | 560031 | Rel-12 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM12 | 1 | Rel-12 | S5 | Wed 21/09/11 | Fri 12/12/14 | 100% | - | - | - | - | OAM12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | - | 56 | 29 |  |  | Wed 18/04/12 | Wed 18/04/12
3569 | 560131 | Rel-12 Self-Organizing Networks (SON) - OAM aspects | OAM12-SON | 2 | Rel-12 | S5 | Wed 21/09/11 | Wed 11/12/13 | 100% | - | - | - | - | OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI | - | 56 | 29 |  |  | Wed 18/04/12 | Mon 19/11/12
3570 | 560033 | Multi-vendor Plug and Play eNB connection to the network | SON-NM-MUPPET | 3 | Rel-12 | S5 | Wed 21/09/11 | Wed 11/12/13 | 100% | SP-120777 | - | NSN | anatoly.andrianov@nsn.com | SP#62 completed. TS 32.508v200 for Approval, TS 32.509v100 for 1-step Approval | 32.501, New TSs (32.508, 32.509) | 56 | 29 |  |  | Wed 18/04/12 | Wed 27/11/13
3571 | 560035 | Compliance of 3GPP SA5 specifications to the NGMN Next Generation Converged Operations Requirements (NGCOR) | OAM-NGMN_NGCOR | 2 | Rel-12 | S5 | Wed 20/06/12 | Wed 17/09/14 | 100% | SP-140321 | - | Huawei | christian.toche@huawei.com | SP#65 moved to Rel-13 OAM-PMID (Converged management Performance Management Interface Definition) UID_560235 | - | 56 | 29 |  |  | Mon 14/05/12 | Mon 25/08/14
3572 | 560135 | Converged Management Model Alignment (Phase 2) | OAM-MODAL | 3 | Rel-12 | S5 | Wed 20/06/12 | Wed 17/09/14 | 100% | SP-140322 | - | NSN | olaf.pollakowski@nsn.com | SP#65 completed. TR 28.280v100 for 1-step Approval | 32.156, new 28.820 | 56 | 29 |  |  | Mon 14/05/12 | Mon 25/08/14
3573 | 560335 | 3GPP Fault Management Solution Profile for NGMN NGCOR | OAM-FMSP | 3 | Rel-12 | S5 | Wed 20/06/12 | Wed 19/06/13 | 100% | SP-120778 | - | Ericsson | thomas.tovinger@ericsson.com | SP#60 completed. TS 28.390v200 for Approval | new 28.390 | 56 | 29 |  |  | Wed 23/05/12 | Thu 13/06/13
3574 | 530050 | Network Management for 3GPP Interworking WLAN | OAM-IWLAN | 2 | Rel-12 | S5 | Wed 21/09/11 | Wed 17/09/14 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 updated WID SP-120779=>SP-140542 (removed parts on CN and non-3GPP access). Discontinue I-WLAN spec. | - | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
3575 | 530150 | Performance measurements part Network Management for 3GPP Interworking WLAN | OAM-IWLAN-SA5P | 3 | Rel-12 | S5 | Thu 22/09/11 | Wed 17/09/14 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 completed. TS 28.402v100 for 1-step Approval, withdraw New TS 28.401 (CN and non-3GPP access i/w PMs). Moved PMs for EPC and non-3GPP access i/w from 28.401=>28.402 | new 28.401, withdrawn new 28.402 | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
3576 | 530250 | NIM part Network Management for 3GPP Interworking WLAN | OAM-IWLAN-SA5NM | 3 | Rel-12 | S5 | Wed 21/09/11 | Wed 11/12/13 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 discontinue I-WLAN specs: Move parts (e.g. IOCs) applicable for EPC and non-3GPP access interworking NRMs from 28.601/2/6 to 28.611/2/6. Withdraw 28.601/2/6 (CN and non-3GPP access i/w NRMs). SP#62 completed. TSs 28.601/2/6/11/12/16 for Approval | 32.632, 32.636, 32.752, 32.756, new (28.611, 28.612, 28.616, withdrawn 28.601, 28.602, 28.606) | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
3577 | 580053 | Rel-12 Network Infrastructure Management | OAM12-NIM | 2 | Rel-12 | S5 | Wed 11/12/13 | Fri 12/12/14 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Thu 15/11/12 | Mon 19/11/12
3578 | 620056 | Alarm quality improvements | OAM-AMI-SA5 | 3 | Rel-12 | S5 | Wed 11/12/13 | Fri 12/12/14 | 100% | SP-130611 | SP-140544 | TeliaSonera | tommy.berggren@teliasonera.com | SP#65 completion 09/14=>12/14. Exception in SP-140544. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) . Dec.14: 50->100 | 32.111-1, 32.111-2, 32.111-6 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
3579 | 630012 | Radio Planning Tool (RPT) interface | OAM-RPTi-SA5 | 3 | Rel-12 | S5 | Fri 07/03/14 | Fri 12/12/14 | 100% | SP-140026 | SP-140546 | Nokia Networks | olaf.pollakowski@nsn.com | SP#65 completion 09/14=>12/14. Exception in SP-140546. SP#65 v100 TS 28.667/8 for Information. Dec.14: 60->100 | 32.101, New TSs (28.667, 28.668, 28.669) | 63 | 32 |  |  | Thu 27/02/14 | Thu 04/12/14
3580 | 580054 | Deleted - Rel-12 Performance Management | OAM12-PM | 2 | Rel-12 | S5 | Fri 21/06/13 | Tue 16/09/14 | 100% | - | - | - | - | OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI | - | 58 | 30 | SP-69 |  | Thu 15/11/12 | Tue 19/08/14
3581 | 620057 | OAM aspects of Network Sharing | OAM-SHARE | 2 | Rel-12 | S5 | Wed 11/12/13 | Fri 12/12/14 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. Triggered by Rel-12 TR 32.851 Study on OAM aspects of Network Sharing (FS_OAM_SHARE), Rel-6 Network Sharing (NTShar) UID_31018 | Stage 1/2/3 | 62 | 32 |  |  | Thu 28/11/13 | Wed 10/09/14
3582 | 620157 | OAM aspects of Network Sharing - Concepts and high-level requirements | OAM-SHARE-SA5c | 3 | Rel-12 | S5 | Wed 11/12/13 | Fri 12/12/14 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. LM 80->100 | new 32.130 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
3583 | 620257 | OAM aspects of Network Sharing - Impacts on existing specifications | OAM-SHARE-SA5imp | 3 | Rel-12 | S5 | Thu 12/12/13 | Fri 12/12/14 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. Dec.14: 60->100 | 28.401,28.621/2/3,28.651/2/3,28.654/5/6,28.657/8/9,28.701/2/3,28.731/2/3,28.734/5/6,32.101/2,32.111-1/2/3/6,32.121/2/6,32.155,32.171/2/6,32.300/1/2/6,32.311/2/6,32.321/2/6,32.331/2/6,32.341/2/6,32.351/352/6,32.361/2/6,32.381/2/6,32.405/6/7/8/9/10/11/12/41 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
3584 | 570037 | Rel-12 Charging | CH12 | 1 | Rel-12 | S5 | Wed 12/12/12 | Wed 18/06/14 | 100% | - | - | - | - | CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | - | 57 | 29 |  |  | Wed 19/09/12 | Wed 19/09/12
3585 | 580051 | Short Message Service - Service Center (SMS-SC) Offline Charging | SMS-SC-CH | 2 | Rel-12 | S5 | Wed 12/12/12 | Mon 10/03/14 | 100% | SP-140027 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027 | 32.240, 32.274, 32.297, 32.298, 32.299 | 58 | 30 |  |  | Tue 20/11/12 | Thu 27/02/14
3586 | 610041 | Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3) | CHIPS | 2 | Rel-12 | S5 | Thu 12/09/13 | Wed 18/06/14 | 100% | SP-130642 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS | 32.251, 32.298, 32.299 | 61 | 31 |  |  | Wed 04/09/13 | Mon 07/12/15
3587 | 610042 | Charging using an Alternative Roaming Provider (Stage 2/3) | CHARP | 2 | Rel-12 | S5 | Thu 12/09/13 | Wed 18/06/14 | 100% | SP-130428 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed. TS 32.276v200 for Approval, 32.293v100 for 1-step Approval | 32.240, 32.299, New TSs [32.276 (Voice Call Service Charging), 32.293 (Proxy Function)] | 61 | 31 |  |  | Wed 04/09/13 | Tue 10/06/14
3588 | 620058 | Charging for IMS centralized service (ICS) control (Stage 2/3) | CHICS | 2 | Rel-12 | S5 | Wed 11/12/13 | Wed 18/06/14 | 100% | SP-130610 | - | NSN | Gerald.Goermer@nsn.com | SP#64 completed. Align SA5 Charging specifications with Rel-8 Feature IMS Centralized Service control (ICSRA) and subsequent enhancements under TEIx (SA2 23.292 ICSRA Stage 2, CT3 29.292, CT1 24.607, 24.611) | 32.250, 32.298 | 62 | 32 |  |  | Fri 06/12/13 | Tue 10/06/14
3589 | 530018 | IMS Emergency PSAP Callback (Stage 3) | EMC_PC | 1 | Rel-12 | C1,C3,IETF | Wed 21/09/11 | Fri 13/06/14 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls | Stage 3 | 53 | 27 |  |  | Sat 27/08/11 | Mon 18/11/13
3590 | 530118 | CT1 part of IMS Emergency PSAP Callback | EMC_PC | 2 | Rel-12 | C1 | Thu 22/09/11 | Fri 13/06/14 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | 24.229, tied to completion of IETF dependencies: 24.604, 24.605, 24.610, 24.611, 24.629 | 53 | 27 |  |  | Sat 27/08/11 | Thu 02/04/15
3591 | 531004 | (IETF) CT1 part of IMS Emergency PSAP Callback (RFC 7090) | EMC_PC | 2 | Rel-12 | C1-IETF | Wed 21/09/11 | Fri 13/06/14 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | RFC 7090 (was draft-ietf-ecrit-psap-callback | 53 | 27 |  |  | Sun 28/08/11 | Thu 02/04/15
3592 | 530218 | CT3 part of IMS Emergency PSAP Callback | EMC_PC | 2 | Rel-12 | C3 | Sat 24/09/11 | Fri 06/09/13 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#61 completed. 2/4/15: acronym changed to EMC_PC | 29.163, 29.165 | 53 | 27 |  |  | Sat 27/08/11 | Thu 02/04/15
3593 | 601001 | (IETF) CT3 part of IMS Emergency PSAP Callback (RFC 7090) | EMC_PC | 2 | Rel-12 | C3-IETF | Wed 21/09/11 | Fri 13/06/14 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | RFC 7090 (was draft-ietf-ecrit-psap-callback) | 60 | 31 |  |  | Mon 10/06/13 | Thu 02/04/15
3594 | 570008 | Interworking between a PLMN with WLAN to access the EPC and a PDN (Stage 3) | SAES_WLAN_EPC_intwk | 1 | Rel-12 | C3 | Mon 10/09/12 | Fri 06/09/13 | 100% | CP-130395 | - | Huawei | Christian.Herrero@huawei.com | CP#61 completed. Linked to Rel-8 Feature SAES in CP-150System Architecture Evolution specification - Evolved Packet System (non RAN aspects) UID_320005 | 29.061 | 57 | 29 |  |  | Mon 13/08/12 | Mon 12/08/13
3595 | 580009 | Reporting Enhancements in Warning Message Delivery (Stage 2/3) | REP_WMD | 1 | Rel-12 | C1,C4,R3 | Fri 07/12/12 | Fri 13/06/14 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality. | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Wed 04/09/13
3596 | 580010 | CT1 part of Reporting Enhancements in Warning Message Delivery (Stage 2) | REP_WMD-CT1 | 2 | Rel-12 | C1 | Fri 07/12/12 | Tue 04/03/14 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#63 completed | 23.041 | 58 | 30 |  |  | Mon 19/11/12 | Mon 03/03/14
3597 | 580011 | CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3) | REP_WMD-CT4 | 2 | Rel-12 | C4 | Mon 10/12/12 | Fri 13/06/14 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#64 completed | 23.007, 29.168 | 58 | 30 |  |  | Mon 19/11/12 | Sun 25/05/14
3598 | 590021 | Public Warning System - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS | 2 | Rel-12 | R3 | Mon 04/03/13 | Fri 13/06/14 | 100% | RP-130398 | - | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | - | LTE | 59 | 30 |  |  | Tue 26/02/13 | Fri 01/03/13
3599 | 590121 | Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS-Core | 3 | Rel-12 | R3 | Mon 04/03/13 | Fri 13/06/14 | 100% | RP-130398 | RP-140637 | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | RP#64 completed | 36.413 | 59 | 30 |  |  | Tue 26/02/13 | Tue 04/03/14
3600 | 580012 | Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3) | bSRVCC | 1 | Rel-12 | C1,C3,R5 | Fri 07/12/12 | Thu 06/03/14 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12 | GERAN, UTRA, LTE | 58 | 30 |  |  | Mon 19/11/12 | Mon 10/06/13
3601 | 580112 | CT1 part of Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC | 2 | Rel-12 | C1 | Fri 07/12/12 | Fri 14/06/13 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completed. 2/4/15: acronym changed to bSRVCC | 24.008, 24.237 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3602 | 600008 | CT3 part of Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC | 2 | Rel-12 | C3 | Wed 12/06/13 | Fri 14/06/13 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completedbSRVCC | 29.165 | 60 | 31 |  |  | Tue 28/05/13 | Thu 02/04/15
3603 | 620017 | Test part: Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC-UEConTest | 2 | Rel-12 | R5 | Fri 06/12/13 | Thu 06/03/14 | 100% | RP-131919 | RP-140422 | NTT DOCOMO | Masahiro.Tamaoki.eu@nttdocomo.com | RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3) | 34.229-1, 34.229-2, 36.523-1, 36.523-2 | 62 | 32 |  |  | Mon 25/11/13 | Sat 14/12/13
3604 | 580013 | IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 1 | Rel-12 | C1,C3,IETF | Fri 07/12/12 | Tue 09/12/14 | 99% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | - | Stage 3 | 58 | 30 |  |  | Mon 19/11/12 | Thu 06/12/12
3605 | 580014 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 2 | Rel-12 | C1 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#65 completed. 4/2/15: acronym changed to IMSProtoc6 | 23.218, 24.229, 24.930 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3606 | 601002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | Tue 21/05/13 | Tue 09/12/14 | 100% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100 | draft-holmberg-sipcore-received-realm | 60 | 31 |  |  | Mon 10/06/13 | Tue 21/03/17
3607 | 651002 | Deleted - (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-jesske-sipcore-sip-tree-cap-indicators) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | Fri 12/09/14 | Fri 05/12/14 | 100% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 9/4/21: 25%->100 | draft-allen-sipcore-sip-tree-cap-indicators | 65 | 33 |  |  | Tue 02/09/14 | Fri 09/04/21
3608 | 660038 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-120905 |  | christer.holmberg@ericsson.com |  | work in progress. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 25%->100; 9/4/21: RFC 7989 added; | draft-ietf-insipid-session-id; RFC 7989 | 65 | 34 |  |  | Thu 04/12/14 | Fri 09/04/21
3609 | 580015 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 2 | Rel-12 | C3 | Fri 06/06/14 | Thu 11/09/14 | 100% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#65 completed. 4/2/15: acronym changed to IMSProtoc6 | 29.163, 29.165 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
3610 | 611001 | (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C3-IETF | Fri 06/09/13 | Fri 05/12/14 | 100% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100 | draft-holmberg-sipcore-received-realm | 61 | 31 |  |  | Fri 23/08/13 | Tue 21/03/17
3611 | 580016 | SAE Protocol Development - Phase 3 | SAES3 | 1 | Rel-12 | C1 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Sat 16/02/13
3612 | 580017 | SAE Protocol Development (Stage 3) - Phase 3 | SAES3-CT1 | 2 | Rel-12 | C1 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
3613 | 580018 | CS Fallback in EPS - Phase 3 | SAES3-CSFB | 2 | Rel-12 | C1 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
3614 | 580019 | SAE for support for non-3GPP accesses - Phase 3 | SAES3-non3GPP | 2 | Rel-12 | C1 | Fri 07/12/12 | Thu 11/09/14 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
3615 | 580020 | IM-SSF Application Server Service Data Descriptions (Stage 2/3) | IMS_SSFDD | 1 | Rel-12 | C4,C1 | Fri 07/12/12 | Fri 14/06/13 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Wed 29/05/13
3616 | 580021 | Stage 2 for IM-SSF Application Server Service Data Descriptions | IMS_SSFDD | 2 | Rel-12 | C1 | Fri 07/12/12 | Fri 01/03/13 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#59 completed | 23.218 | 58 | 30 |  |  | Mon 19/11/12 | Sat 16/02/13
3617 | 580022 | Stage 3 for IM-SSF Application Server Service Data Descriptions | IMS_SSFDD | 2 | Rel-12 | C4 | Mon 10/12/12 | Fri 14/06/13 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | 29.328, 29.329, 29.364 | 58 | 30 |  |  | Mon 19/11/12 | Wed 29/05/13
3618 | 580023 | Diameter based interface between SGSN and SMS central functions (Stage 2/3) | Dia_SGSN_SMS | 1 | Rel-12 | C4,C1 | Mon 10/12/12 | Fri 06/12/13 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | Stage 2/3 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
3619 | 590015 | Stage 2 for Diameter based interface between SGSN and SMS central functions | Dia_SGSN_SMS | 2 | Rel-12 | C1 | Thu 07/03/13 | Fri 06/12/13 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 23.04 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
3620 | 580123 | Stage 3 for Diameter based interface between SGSN and SMS central functions | Dia_SGSN_SMS | 2 | Rel-12 | C4 | Mon 10/12/12 | Fri 06/12/13 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 29.002, 29.230, 29.272, 29.305, 29.336, 29.337, 29.338 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
3621 | 580024 | Diameter based interface between SGSN-GMLC (Stage 3) | Dia_SGSN_GMLC | 1 | Rel-12 | C4 | Mon 10/12/12 | Fri 06/12/13 | 100% | CP-130598 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol) | 29.002, 29.172, 29.173, 29.230, 29.272 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
3622 | 590009 | IMS impacts on UICC Application Aspects (Stage 3) | IMS_UApAs | 1 | Rel-12 | C6 | Mon 04/03/13 | Tue 09/12/14 | 100% | CP-130169 | CP-140696 | Giesecke & Devrient | sergi.espi@gi-de.com | CP#65 completion 09/14=>12/14. Exception in CP-140696. Dec.14: 85->100% | 31.102, 31.103, 31.111, 31.130 | 59 | 30 |  |  | Wed 20/02/13 | Wed 03/12/14
3623 | 590012 | eMBMS restoration procedures | eMBMS_Rest | 1 | Rel-12 | C4,C3 | Fri 01/03/13 | Thu 11/09/14 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed. Linked to Rel-9 MBMS support in EPS (MBMS_EPS). Rel-10 CT Features EPC Node Restoration with/out Idle mode Signalling Reduction (ISR) activated (EPC_NR/EPC_NR_ISR) | Stage 3 | 59 | 30 |  |  | Thu 07/03/13 | Mon 18/11/13
3624 | 590112 | CT4 part of eMBMS restoration procedures | eMBMS_Rest | 2 | Rel-12 | C4 | Fri 01/03/13 | Fri 06/12/13 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed | 23.007, 23.008, 29.274 | 59 | 30 |  |  | Thu 07/03/13 | Mon 18/11/13
3625 | 610006 | CT3 part of eMBMS restoration procedures | eMBMS_Rest | 2 | Rel-12 | C3 | Wed 04/09/13 | Thu 11/09/14 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed | 29.061 | 61 | 31 |  |  | Thu 07/03/13 | Fri 01/08/14
3626 | 590014 | Dual Radio VCC enhancements (Stage 2/3) | eDRVCC | 1 | Rel-12 | C1,C3.S2 | Wed 19/09/12 | Fri 06/12/13 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed. Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). Stage 3 linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056 (Stage 2 in TS 23.237). 2/4/15: acronym changed to eDRVCC | Stage 2/3 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
3627 | 590114 | Stage 2 for Dual Radio VCC enhancements | eDRVCC | 2 | Rel-12 | S2 | Wed 19/09/12 | Fri 01/03/13 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). 2/4/15: acronym changed to eDRVCC | 23.237 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
3628 | 590214 | Stage 3 for Dual Radio VCC enhancements | eDRVCC | 2 | Rel-12 | C1,C3 | Fri 01/03/13 | Fri 06/12/13 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed | Stage 3 | 59 | 30 |  |  | Tue 19/02/13 | Mon 18/11/13
3629 | 590314 | CT1 part of Stage 3 for Dual Radio VCC enhancements | eDRVCC | 3 | Rel-12 | C1 | Fri 01/03/13 | Fri 06/12/13 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed. 2/4/15: acronym changed to eDRVCC | 24.237, 24.292 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
3630 | 590414 | CT3 part of Stage 3 for Dual Radio VCC enhancements | eDRVCC | 3 | Rel-12 | C3 | Fri 01/03/13 | Fri 06/09/13 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#61 completed. 2/4/15: acronym changed to eDRVCC | 29.165 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
3631 | 600009 | CT aspects of Signalling of Image Size (Stage 2/3) | SIS_CT | 1 | Rel-12 | C4,C1,C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included | Stage 2/3 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3632 | 600109 | CT4 part of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C4 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3633 | 600209 | CT1 part of CT Aspects of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C1 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3634 | 600309 | CT3 part of CT Aspects of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3635 | 600010 | IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S) | ICS_IWE | 1 | Rel-12 | C3 | Fri 14/06/13 | Fri 06/12/13 | 100% | CP-130352 | - | Orange | marianne.mohali@orange.com | CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS) | 29.292 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
3636 | 610002 | GPRS Tunnelling Protocol for the Control plane (GTP-C) Overload Control Mechanisms | GOCMe | 1 | Rel-12 | C4 | Fri 06/09/13 | Thu 11/09/14 | 100% | CP-140488 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#65 completed. Updated WID CP-130433=>CP-140488 | 23.008, 29.230, 29.273, 29.274, 29.303, New 29.807 | 61 | 31 |  |  | Sat 10/08/13 | Mon 28/07/14
3637 | 610004 | Proxy Call Session Control Function (P-CSCF) restoration enhancements (Stage 2/3) | PCSCF_RES | 1 | Rel-12 | C4,C3,C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 updated WID CP-140443=>CP-140490. Based TR 29.806, solutions B and D are selected for standardization. Dec.14: 95->100 | Stage 2/3 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3638 | 610104 | TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements | PCSCF_RES | 2 | Rel-12 | C4 | Fri 06/09/13 | Thu 11/09/14 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completed. TR 29.806v200 for Approval | New 29.806 | 61 | 31 |  |  | Sat 10/08/13 | Sat 06/09/14
3639 | 640999 | Common for HSS & PCRF solutions | PCSCF_RES | 2 | Rel-12 | C4,C3,C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
3640 | 610204 | CT4 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C4 | Fri 06/09/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140481 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140481. Dec.14: 90->100 | 23.380, 29.060, 29.274 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3641 | 640014 | CT1 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C1 | Wed 03/04/13 | Fri 05/12/14 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completed | 24.008 | 64 | 33 |  |  | Sat 10/08/13 | Sat 06/09/14
3642 | 650002 | CT3 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C3 | Fri 03/05/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140687 | Huawei | susan.shishufeng@huawei.com | CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687 | 29.061, 29.165 | 65 | 33 |  |  | Sat 10/08/13 | Tue 03/06/14
3643 | 640998 | HSS based solution | PCSCF_RES | 2 | Rel-12 | C4,C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
3644 | 610210 | CT4 part of HSS based solution | PCSCF_RES | 3 | Rel-12 | C4 | Fri 06/09/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140481 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140481. Dec.14: 90->100 | 29.002, 29.228, 29.229, 29.272, 29.305 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3645 | 640114 | CT1 part of HSS based solution | PCSCF_RES | 3 | Rel-12 | C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140605 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100% | 24.229 | 64 | 33 |  |  | Sat 10/08/13 | Thu 04/12/14
3646 | 640997 | PCRF based solution | PCSCF_RES | 2 | Rel-12 | C3,C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | - | Huawei | susan.shishufeng@huawei.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
3647 | 640015 | CT3 part of PCRF based solution | PCSCF_RES | 3 | Rel-12 | C3 | Fri 03/05/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140687 | Huawei | susan.shishufeng@huawei.com | CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687 | 29.212, 29.213, 29.214, 29.215 | 64 | 33 |  |  | Sat 10/08/13 | Tue 03/06/14
3648 | 640214 | CT1 part of PCRF based solution | PCSCF_RES | 3 | Rel-12 | C1 | Wed 03/04/13 | Tue 09/12/14 | 100% | CP-140490 | CP-140605 | Huawei | susan.shishufeng@huawei.com | CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100 | 24.229 | 64 | 33 |  |  | Sat 10/08/13 | Thu 04/12/14
3649 | 610008 | Updating IMS to conform to RFC 6665 (Stage 3) | UP6665 | 1 | Rel-12 | C1,C3 | Mon 09/09/13 | Fri 13/03/15 | 100% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes | Stage 3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
3650 | 610108 | CT1 part of Updating IMS to conform to RFC 6665 | UP6665 | 2 | Rel-12 | C1 | Mon 09/09/13 | Tue 09/12/14 | 100% | CP-130717 | CP-140620 | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#65 completion 09/14=>12/14. Exception in CP-140620. 3/3/15: 100% cpltd. | 23.218, 24.141, 24.147, 24.229, 24.237, 24.292, 24.337, 24.341, 24.604, 24.606, 24.623, 24.628, 24.629, 24.642 | 61 | 31 |  |  | Thu 25/07/13 | Tue 03/03/15
3651 | 610208 | CT3 part of Updating IMS to conform to RFC 6665 | UP6665 | 2 | Rel-12 | C3 | Mon 09/09/13 | Fri 06/12/13 | 100% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#62 completed | 29.163, 29.165 | 61 | 31 |  |  | Thu 25/07/13 | Tue 19/11/13
3652 | 670033 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-clarifications) | UP6665 | 2 | Rel-12 | C1-IETF | Fri 13/03/15 | Fri 13/03/15 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date; 9/4/21: RFC 7647 added; | draft-ietf-sipcore-refer-clarification; RFC 7647 | 67 | 34 |  |  | Fri 13/03/15 | Fri 09/04/21
3653 | 670034 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-explicit-subscription) | UP6665 | 2 | Rel-12 | C1-IETF | Fri 13/03/15 | Fri 13/03/15 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100; 9/4/21: RFC 7614 added; | draft-ietf-sipcore-refer-explicit-subscription; RFC 7614 | 67 | 34 |  |  | Fri 13/03/15 | Fri 09/04/21
3654 | 670035 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-roach-sipcore-6665-clarifications) | UP6665 | 2 | Rel-12 | C1-IETF | Fri 13/03/15 | Fri 13/03/15 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100 | draft-roach-sipcore-6665-clarification | 67 | 34 |  |  | Fri 13/03/15 | Mon 14/09/15
3655 | 620004 | IMS Operator Determined Call Barring enhancements (Stage 3) | eIODB | 1 | Rel-12 | C1,C3 | Fri 06/12/13 | Thu 11/09/14 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision | Stage 3 | 62 | 32 |  |  | Mon 18/11/13 | Mon 18/11/13
3656 | 620104 | CT1 part of IMS Operator Determined Call Barring enhancements | eIODB | 2 | Rel-12 | C1 | Fri 06/12/13 | Fri 13/06/14 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#64 completed | 24.229, 24.315 | 62 | 32 |  |  | Mon 18/11/13 | Mon 26/05/14
3657 | 620204 | CT3 part of IMS Operator Determined Call Barring enhancements | eIODB | 2 | Rel-12 | C3 | Mon 09/12/13 | Thu 11/09/14 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#65 completed | 29.165 | 62 | 32 |  |  | Mon 18/11/13 | Fri 01/08/14
3658 | 620006 | Signalling Improvements for Network Efficiency (Stage 3) | SINE | 1 | Rel-12 | C1 | Fri 06/12/13 | Tue 09/12/14 | 100% | CP-130713 | CP-140617 | Huawei | Lin Shu (shulin@huawei.com) | CP#65 completion 09/14=>12/14. Exception in CP-140617.Dec.14: 80->85%. 3/3/15: 100% cpltd. | 24.008, 24.301 | 62 | 32 |  |  | Mon 18/11/13 | Tue 03/03/15
3659 | 630002 | Interactive Connectivity Establishment (ICE, IETF RFC 5245) impacts on IMS H.248 profiles | ICEH248 | 1 | Rel-12 | C4,C3 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | Add optional ICE support as defined in Rel-8 TS (23.228, 24.229) to Iq, Ix, Mn, Mp, Mc interfaces. SA2 Rel-12 TS 23.228 requires support for ICE in eP-CSCF, eIMS-AGW for WebRTC | Stage 2/3 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
3660 | 630102 | CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3) | ICEH248 | 2 | Rel-12 | C4 | Wed 05/03/14 | Thu 11/09/14 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#65 completed | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Mon 28/07/14
3661 | 630202 | CT3 part of ICE impacts on IMS H.248 profiles (Stage 2) | ICEH248 | 2 | Rel-12 | C3 | Wed 05/03/14 | Fri 13/06/14 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#64 completed | 29.162, 29.163, 29.292 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
3662 | 630005 | Transfer of ETSI business trunking specifications | IMS_Corp2 | 1 | Rel-12 | C1,S1 | Wed 05/03/14 | Tue 09/12/14 | 100% | SP-140170 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060 | - | 63 | 32 |  |  | Wed 29/01/14 | Fri 07/03/14
3663 | 630105 | SA1 part of Transfer of ETSI business trunking specifications | IMS_Corp2 | 2 | Rel-12 | S1 | Wed 05/03/14 | Wed 17/09/14 | 100% | SP-140170 | S1-143300 | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 completed. TS 22.519v200 for Approval | New 22.519 (ETSI 181 019) | 63 | 32 |  |  | Thu 06/03/14 | Wed 03/09/14
3664 | 630205 | CT1 part of Transfer of ETSI business trunking specifications | IMS_Corp2 | 2 | Rel-12 | C1 | Wed 05/03/14 | Tue 09/12/14 | 100% | SP-140170 | CP-140619 | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | CP#65 TS 24.525v200 for Approval. TR 24.969v100 for Information. Completion 09/14=>12/14. Exception in CP-140619. Dec.14: 90->100 | New TSs [24.523 (182 023), 24.524 (182 024), 24.525 (182 025)], New 24.969 (183 069) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3665 | 630008 | Support of ALT-C attribute | ALTC | 1 | Rel-12 | C4,C1,C3 | Mon 10/03/14 | Tue 09/12/14 | 100% | CP-140191 | - | Orange | lionel.morand@orange.com | SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network. | - | 63 | 32 |  |  | Wed 29/01/14 | Mon 03/03/14
3666 | 630108 | CT4 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C4 | Mon 10/03/14 | Tue 09/12/14 | 100% | CP-140191 | CP-140485 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140485. Dec.14: 0->100 | 23.334, 29.238, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3667 | 630208 | CT1 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C1 | Mon 10/03/14 | Tue 09/12/14 | 100% | CP-140191 | CP-140611 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140611. Dec.14: 0->100 | 24.229 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3668 | 630308 | CT3 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C3 | Mon 10/03/14 | Tue 09/12/14 | 100% | CP-140191 | CP-140563 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140563. Dec.14: 0->100 | 29.162 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
3669 | 640003 | Diameter Overload Control Mechanisms | DOCME | 1 | Rel-12 | C4,IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140273 | - | Orange | lionel.morand@orange.com | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | - | 64 | 33 |  |  | Sun 25/05/14 | Mon 16/06/14
3670 | 640103 | CT4 part of Diameter Overload Control Mechanisms | DOCME | 2 | Rel-12 | C4 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140273 | CP-140486 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140486. Dec.14: 70->100 | 29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.344, 29.345 | 64 | 33 |  |  | Sun 25/05/14 | Thu 04/12/14
3671 | 641010 | (IETF) Diameter Overload Control Mechanisms (draft-ietf-dime-ovli) | DOCME | 2 | Rel-12 | C4-IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140273 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Mar15: In WGLC¦7/3/16: 50%->100; 9/4/21: RFC 7683 added; | draft-ietf-dime-ovli; RFC 7683 | 64 | 33 |  |  | Sun 25/05/14 | Fri 09/04/21
3672 | 640004 | Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 1 | Rel-12 | C1,C3 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases. | - | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
3673 | 640104 | CT1 part of Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 2 | Rel-12 | C1 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140285 | CP-140609 | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completion 09/14=>12/14. Exception in CP-140609. Dec.14: 85->100 | 24.229, 24.259, 24.604 | 64 | 33 |  |  | Mon 07/04/14 | Thu 04/12/14
3674 | 640204 | CT3 part of Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 2 | Rel-12 | C3 | Fri 13/06/14 | Thu 11/09/14 | 100% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completed | 29.163, 29.165, 29.292 | 64 | 33 |  |  | Mon 07/04/14 | Thu 31/07/14
3675 | 640007 | Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 1 | Rel-12 | C1,C3,IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025 | - | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
3676 | 640107 | CT1 part of Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 2 | Rel-12 | C1 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140288 | CP-140613 | Ericsson | Jan.Holm@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140613. Dec.14: 95->100 | 24.229 | 64 | 33 |  |  | Mon 07/04/14 | Thu 04/12/14
3677 | 641008 | (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (draft-holmberg-dispatch-iotl) | NNI_RS | 2 | Rel-12 | C1-IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140288 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Publication requested¦7/3/16: 50%->100 | draft-holmberg-dispatch-iotl | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/03/16
3678 | 640207 | CT3 part of Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 2 | Rel-12 | C3 | Fri 13/06/14 | Thu 11/09/14 | 100% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | CP#65 completed | 29.079, 29.165 | 64 | 33 |  |  | Mon 07/04/14 | Thu 31/07/14
3679 | 640008 | Unstructured Supplementary Service Data (USSD) method selection (Stage 3) | USSD_MS | 1 | Rel-12 | C1 | Wed 11/06/14 | Fri 13/06/14 | 100% | CP-140450 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain) | 24.173, 24.390, New 24.391 | 64 | 33 |  |  | Mon 07/04/14 | Thu 12/06/14
3680 | 640009 | Representational State Transfer (REST) reference point between Application Function (AF) and Protocol Converter (PC) | REST_AF_PC | 1 | Rel-12 | C3 | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140451 | CP-140561 | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#65 completion 09/14=>12/14. TS 29.201v200 for Approval. Exception in CP-140561. Dec.14: 80->100 | 29.213, 29.214, new 29.201 | 64 | 33 |  |  | Tue 10/06/14 | Thu 04/12/14
3681 | 640011 | Overload Control for PCC based Diameter applications | DOCME-PCC | 1 | Rel-12 | C3,IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | - | 64 | 33 |  |  | Tue 10/06/14 | Mon 16/06/14
3682 | 640111 | CT3 part of Overload Control for PCC based Diameter applications | DOCME-PCC | 2 | Rel-12 | C3 | Fri 13/06/14 | Thu 11/09/14 | 100% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#65 completed | 29.212, 29.213, 29.214 | 64 | 33 |  |  | Tue 10/06/14 | Thu 31/07/14
3683 | 641011 | (IETF) Overload Control for PCC based Diameter applications | DOCME-PCC | 2 | Rel-12 | C3-IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140405 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress¦7/3/16: 50%->100 | draft-ietf-dime-ovli | 64 | 33 |  |  | Tue 10/06/14 | Mon 07/03/16
3684 | 650004 | Network Initiated USSD Simulation Services in IMS | USSI-NET | 1 | Rel-12 | C1 | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-140625 | CP-140610 | AT&T | Martin Dolly (md3135@att.com) | CP#65 exception in CP-140610. Dec.14: 75->100 | 24.39 | 65 | 33 |  |  | Mon 28/07/14 | Thu 04/12/14
3685 | 530002 | Introduction of ER-GSM band for GSM-R | RT_ERGSM | 1 | Rel-12 | G1,C1,G3new | Fri 16/09/11 | Fri 28/02/14 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios. | GERAN | 51 | 27 |  |  | Tue 06/09/11 | Fri 07/03/14
3686 | 530102 | GERAN1 part of Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | G1 | Fri 16/09/11 | Fri 28/02/14 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed. GP#51 approved WID | 45.001, 45.005, 45.008, 45.050 | 51 | 27 |  |  | Tue 06/09/11 | Fri 07/03/14
3687 | 610016 | Test part: Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | G3new | Mon 02/09/13 | Fri 28/02/14 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed | 51.010, 51.021 | 59 | 31 |  |  | Wed 04/09/13 | Fri 07/03/14
3688 | 530202 | CT1 part of Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | C1 | Wed 28/09/11 | Fri 06/12/13 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | CP#62 completed. Added ERGSM capability indication (24.008 CR#2469R1) | 24.008 | 53 | 27 |  |  | Tue 06/09/11 | Tue 19/11/13
3689 | 570002 | Downlink Multi Carrier GERAN | DMCG | 1 | Rel-12 | G2,G1,C1,G3new | Mon 10/09/12 | Fri 13/03/15 | 91% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2 | GERAN | 55 | 29 |  |  | Mon 03/09/12 | Sat 01/03/14
3690 | 570102 | Core part: Downlink Multi Carrier GERAN | DMCG | 2 | Rel-12 | G2,G1 | Mon 22/07/13 | Fri 30/05/14 | 100% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#62 completed. GP#55 approved WID | 43.064, 44.004, 44.018, 44.060, 45.002, 45.003, 45.005, 45.008, 48.018 | 55 | 29 |  |  | Mon 03/09/12 | Fri 30/05/14
3691 | 570202 | CT part: Downlink Multi Carrier GERAN | DMCG | 2 | Rel-12 | C1 | Mon 10/09/12 | Thu 11/09/14 | 100% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | CP#65 completed | 24.008 | 55 | 29 |  |  | Mon 03/09/12 | Mon 28/07/14
3692 | 570302 | Test part: Downlink Multi Carrier GERAN | DMCG-MStest | 2 | Rel-12 | G3new | Mon 10/09/12 | Fri 13/03/15 | 80% | GP-120930 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#63 completion 08/14=>11/14. Dec.14: 35->80%, CD:11/14->03/15 | 51.010-1, 51.010-2 | 55 | 29 |  |  | Mon 03/09/12 | Wed 03/12/14
3693 | 590033 | Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS) | MSRD_VAMOS | 1 | Rel-12 | G1,G2,C1,G3new | Fri 01/03/13 | Fri 21/11/14 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002 | GERAN | 57 | 30 |  |  | Mon 04/03/13 | Fri 29/08/14
3694 | 590333 | CT1 introduction of MS capability support for MS supporting MSRD for VAMOS | MSRD_VAMOS | 2 | Rel-12 | C1 | Fri 01/03/13 | Fri 06/12/13 | 100% | GP-130849 | - | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | CP#62 completed | 24.008 | 57 | 30 |  |  | Mon 04/03/13 | Fri 29/08/14
3695 | 590133 | MSRD for VAMOS - Performance Requirements | MSRD_VAMOS-PerfReq | 2 | Rel-12 | G1,G2 | Thu 28/11/13 | Fri 21/11/14 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 95->100 | 44.018, 45.001, 45.002, 45.005, 45.008, 45.009 | 57 | 30 |  |  | Mon 04/03/13 | Wed 03/12/14
3696 | 590233 | MSRD for VAMOS - MS Conformance Test | MSRD_VAMOS-Test | 2 | Rel-12 | G3new | Wed 06/03/13 | Fri 21/11/14 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 85->100 | 51.010-1, 51.010-2 | 57 | 30 |  |  | Mon 04/03/13 | Wed 03/12/14
3697 | 620014 | New Training Sequence Codes (TSC) for GERAN | NewToN | 1 | Rel-12 | G1,G2,C1 | Fri 22/11/13 | Tue 09/12/14 | 93% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002 | GERAN | 60 | 32 |  |  | Fri 22/11/13 | Tue 27/05/14
3698 | 620114 | GERAN1 part of New Training Sequence Codes (TSC) for GERAN | NewToN | 2 | Rel-12 | G1 | Fri 22/11/13 | Fri 21/11/14 | 100% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. Dec.14: 80->100% | 45.001, 45.002, 45.008, 45.009, 45.050 | 60 | 32 |  |  | Fri 22/11/13 | Wed 03/12/14
3699 | 620214 | GERAN2 part of New Training Sequence Codes (TSC) for GERAN | NewToN | 2 | Rel-12 | G2 | Fri 22/11/13 | Wed 19/11/14 | 80% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. | 44.018, 44.060 | 60 | 32 |  |  | Fri 22/11/13 | Fri 30/05/14
3700 | 620314 | CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3) | NewToN | 2 | Rel-12 | C1 | Fri 22/11/13 | Tue 09/12/14 | 100% | GP-131139 | CP-140604 | Ericsson | Mårten Sundberg | CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604. 3/3/15: 100% cpltd. | 24.008 | 60 | 32 |  |  | Fri 22/11/13 | Tue 03/03/15
3701 | 550016 | Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO | 1 | Rel-12 | R4 | Mon 05/03/12 | Fri 06/12/13 | 100% | RP-120368 | - | Vodafone | Luis Anaya | RP#59 moved to Rel-12. Triggered by FS_HSPA_LTE_measRP_MIMO_multi-antenna. Core functionality exists since Rel-6 & Rel-7 (MIMO). Adds a very generic test method to test UEs with 2 or more Rx antennas | UTRA, LTE | 55 | 28 |  |  | Thu 23/02/12 | Thu 14/03/13
3702 | 550116 | Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO-Perf | 2 | Rel-12 | R4 | Mon 05/03/12 | Fri 06/12/13 | 100% | RP-120368 | RP-131507 | Vodafone | luis.anaya@vodafone.com | RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI) | new 37.977 | 55 | 28 |  |  | Thu 23/02/12 | Fri 30/08/13
3703 | 570021 | Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3) | EHNB_enh3 | 1 | Rel-12 | R3,R2 | Wed 12/09/12 | Fri 06/12/13 | 100% | RP-130741 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Triggered by FS_EHNB_enh (TR 37.803) | UTRA, LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
3704 | 570121 | Core part: Further enhancements to H(e)NB mobility - Part 3 | EHNB_enh3-Core | 2 | Rel-12 | R3,R2 | Wed 12/09/12 | Fri 06/12/13 | 100% | RP-130741 | RP-131508 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | 25.304, 25.331, 25.367, 25.467, 25.469, 36.300, 36.331 | 57 | 29 |  |  | Tue 04/09/12 | Fri 29/11/13
3705 | 590019 | Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE | LCS_BDS | 1 | Rel-12 | R2,R3,R4,R5 | Mon 04/03/13 | Mon 15/06/15 | 100% | RP-130416 | - | CATR | Ying Du (duying1@catr.cn) | BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2 | UTRA, LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 05/03/13
3706 | 590119 | Core part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Core | 2 | Rel-12 | R2,R3 | Sun 02/06/13 | Thu 06/03/14 | 100% | RP-130416 | RP-131500 | ZTE | Huang He (huang.he4@zte.com.cn) | RP#62 completed | 25.305, 25.306, 25.331, 25.453, 25.413, 25.423, 25.433 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
3707 | 590219 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Perf | 2 | Rel-12 | R4 | Thu 07/03/13 | Fri 13/06/14 | 100% | RP-130416 | RP-140714 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed. TS 25.173v100 for 1-step Approval | 25.172 (FDD), new 25.173 (TDD) | 59 | 30 |  |  | Tue 26/02/13 | Wed 11/06/14
3708 | 590319 | Core part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Core | 2 | Rel-12 | R2 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-130416 | RP-131525 | CATR | Ying Du (duying1@catr.cn) | RP#62 completed | 36.305, 36.355 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
3709 | 590419 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Perf | 2 | Rel-12 | R4 | Thu 07/03/13 | Fri 13/06/14 | 100% | RP-130416 | RP-140713 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed | 36.171 | 59 | 30 |  |  | Tue 26/02/13 | Thu 12/06/14
3710 | 640013 | Test part: BeiDou Navigation Satellite System (BDS) Positioning Support for LTE and UMTS | LCS_BDS-UEConTest | 2 | Rel-12 | R5 | Sun 15/06/14 | Mon 15/06/15 | 100% | RP-140730 | RP-150656 | CATT | Chen Xiaiozhong (chenxiaozhong@catt.cn) | ¦Stat Rep: RP-141350->RP-141950 1st Apr 15: Compl:80%->90% 1st Apr 15: Stat Rep: RP-141950->RP-150357 03/07/15: Compl:90%->100% 03/07/15: Stat Rep: RP-150357->RP-150656 | 34.108, 36.508, 37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5 | 64 | 33 |  |  | Tue 10/06/14 | Thu 18/06/15
3711 | 620011 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 1 | Rel-12 | G2,G1,G3new | Fri 22/11/13 | Fri 13/03/15 | 93% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001 | GERAN | 60 | 32 |  |  | Fri 22/11/13 | Sat 01/03/14
3712 | 620111 | GERAN2 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 2 | Rel-12 | G2 | Fri 22/11/13 | Fri 29/08/14 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#63 completed | 44.031, 49.031, 44.071, 48.031 | 60 | 32 |  |  | Fri 22/11/13 | Fri 29/08/14
3713 | 620211 | GERAN1 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 2 | Rel-12 | G1 | Fri 22/11/13 | Fri 29/08/14 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#63 completed | 43.059, 45.005 | 60 | 32 |  |  | Fri 22/11/13 | Fri 29/08/14
3714 | 630009 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new | LCS_BDS_GERAN-GERAN3new | 2 | Rel-12 | G3new | Sat 01/03/14 | Fri 13/03/15 | 80% | GP-140244 |  | CATR | Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn | Dec.14: 25->80%, CD: 11/14->03/15 | 51010-1, 51.010-2, 51.010-7 | 61 | 32 |  |  | Sat 01/03/14 | Fri 29/08/14
3715 | 620311 | Deleted - Test part: Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN-MStest | 2 | Rel-12 | G3new | Fri 22/11/13 | Fri 28/02/14 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#61 stopped | 51.010-1 | 60 | 32 | GP-61 | PCG-32 | Fri 22/11/13 | Sat 01/03/14
3716 | 600019 | Deleted - New Base Station specification structure | BSspec_struc | 1 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-130851 | - | Ericsson | johan.skold@ericsson.com | Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc) | UTRA, LTE, MSR | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Mon 17/06/13
3717 | 600119 | Deleted - Core part: New Base Station specification structure | BSspec_struc-Core | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-130851 | RP-131513 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 20% completion) | 25.104, 25.105, 36.104, 37.104, 37.810, New 37.811 (New BS specification structure), New 37.xya (New RF core specification) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Fri 29/11/13
3718 | 600219 | Deleted - Perf. part: New Base Station specification structure | BSspec_struc-Perf | 2 | Rel-12 | R4 | Thu 20/06/13 | Fri 06/12/13 | 100% | RP-130851 | RP-131514 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 0% completion) | 25.113, 25.141, 25.142, 36.113, 36.141, 37.113, 37.141, 37.810, New 37.xyz (New RF test specification, New 37.xyw (ew EMC specification) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Fri 29/11/13
3719 | 600021 | L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL | 1 | Rel-12 | R4,R2,R3 | Mon 17/06/13 | Tue 15/12/15 | 100% | RP-140092 | - | Orange | olfa.benhaddada@orange.com | ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1 | UTRA, LTE | 60 | 31 |  |  | Mon 17/06/13 | Sat 07/12/13
3720 | 600121 | Core part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Core | 2 | Rel-12 | R4,R2,R3 | Thu 13/02/14 | Fri 13/06/14 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed. RP#65 forgotten TR 37.814 v100 for 1-step Approval | 25.101, 25.104, 25.113, 25.133, 25.307, 25.327, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, 37.104, 37.113, new 37.814 | 60 | 31 |  |  | Mon 17/06/13 | Mon 15/09/14
3721 | 600221 | Perf. part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Perf | 2 | Rel-12 | R4 | Mon 17/06/13 | Fri 13/06/14 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed | 25.133, 25.141, 25.307, 25.327, 36.133, 36.141, 36.307, 37.141 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
3722 | 670047 | UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-150835 | RP-151163 | Ericsson |  | 03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163¦1/1/16 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3723 | 600027 | LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON | 1 | Rel-12 | R3,S2,C4,G2 | Tue 18/06/13 | Fri 13/06/14 | 100% | RP-130831 | - | China Telecom | Jinlian_wu@189.cn | Triggered by Rel-12 TR 37.813 (FS_LTE_HRPD_SON). SA2 should verify the architecture solution in TR 37.813 for inter-RAT load balancing between LTE-HRPD. CT4 should specify the RIM extension to support the feature. | UTRA, LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
3724 | 610103 | Stage 2 for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON | 2 | Rel-12 | S2 | Wed 11/09/13 | Wed 11/12/13 | 100% | - | - | Huawei | Huan Li (ivy.lihuan@huawei.com) | SP#62 completed | 23.402 | 61 | 31 |  |  | Thu 15/08/13 | Thu 28/11/13
3725 | 600127 | Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON-Core | 2 | Rel-12 | R3 | Tue 18/06/13 | Fri 13/06/14 | 100% | RP-130831 | RP-140745 | China Telecom | Jinlian_wu@189.cn | RP#64 completed | 36.300, 36.413 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
3726 | 610003 | CT aspects for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON (Stage 3) | LTE_HRPD_SON-CT | 2 | Rel-12 | C4 | Wed 04/09/13 | Fri 06/09/13 | 100% | CP-130434 | - | Huawei | Xiaoyan SHI (sean.shixiaoyan@huawei.com | CP#61 WID approved & Completed | 29.274, 29.276, 29.280 | 61 | 31 |  |  | Sun 11/08/13 | Tue 13/08/13
3727 | 610015 | GERAN aspects for LTE-HRPD inter-RAT SON, RAN Information Management (RIM) - Stage 3 | LTE_HRPD_SON-RIM | 2 | Rel-12 | G2 | Mon 26/08/13 | Fri 30/08/13 | 100% | GP-130817 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#59 WID approved & Completed | 48.018 | 59 | 31 |  |  | Sun 11/08/13 | Tue 01/10/13
3728 | 620042 | Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon | 1 | Rel-12 | R4,R2 | Sun 15/12/13 | Fri 14/09/18 | 99% | RP-132061 | - | Ericsson | christopher.callender@ericsson.com | - | UTRA, LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
3729 | 620142 | Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Core | 2 | Rel-12 | R4,R2 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-132061 | RP-141787 | Ericsson | christopher.callender@ericsson.com | ¦CD:Thu 18/12/14->Mon 15/12/14¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787 | 25.133, 25.331, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
3730 | 620242 | Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/06/15 | 100% | RP-132061 | RP-150596 | Ericsson | christopher.callender@ericsson.com | ¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787 1st Apr 15: Compl:5%->40% 1st Apr 15: Stat Rep: RP-141787->RP-150063 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150063->RP-150596 | 25.133, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Thu 18/06/15
3731 | 700064 | UE Conformance Test Aspects - Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-UEConTest | 2 | Rel-12 | R5 | Tue 15/12/15 | Fri 14/09/18 | 100% | RP-171889 |  | Ericsson |  | 22/3/16: Compl:0%->4%1/7/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: Com 21/3/17: Compl ¦2 ;; 11/10/20: 35%->100 |  | 70 | 36 |  |  | Fri 01/01/16 | Sun 11/10/20
3732 | 620048 | WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2,S2,C1,C4 | Fri 06/12/13 | Tue 09/12/14 | 100% | RP-140981 | - | Intel | sasha.sirotkin@intel.com | Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw) | UTRA, LTE | 62 | 32 |  |  | Mon 09/12/13 | Mon 09/12/13
3733 | 620148 | Core part: WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-Core | 2 | Rel-12 | R2 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-140981 | RP-141310 | Intel | sasha.sirotkin@intel.com | SP#65 completed | 25.304, 25.306, 25.331, 36.304, 36.306, 36.331 | 62 | 32 |  |  | Mon 09/12/13 | Tue 09/09/14
3734 | 630013 | SA2 aspects of WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-SA2 | 2 | Rel-12 | S2 | Fri 07/03/14 | Wed 17/09/14 | 100% | SP-140169 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#65 completed | 23.402, 23.401, 23.060, 23.251 | 63 | 32 |  |  | Fri 07/03/14 | Mon 15/09/14
3735 | 640006 | CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3) | UTRA_LTE_WLAN_interw-CT | 2 | Rel-12 | C1,C4 | Tue 09/09/14 | Tue 09/12/14 | 100% | CP-140623 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 revised WID CP-140287=>CP-140623 (added CT4 part) | Stage 2/3 | 64 | 33 |  |  | Mon 07/04/14 | Tue 09/09/14
3736 | 640106 | CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3) | UTRA_LTE_WLAN_interw-CT | 3 | Rel-12 | C1 | Tue 09/09/14 | Tue 09/12/14 | 100% | CP-140623 | CP-140720 | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd. | 24.008, 24.301, 24.302, 24.312 | 64 | 33 |  |  | Mon 07/04/14 | Tue 03/03/15
3737 | 650001 | CT4 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3) | UTRA_LTE_WLAN_interw-CT | 3 | Rel-12 | C4 | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-140623 | CP-140482 | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 revised WID CP-140287=>CP-140623 (added CT4 part). Exception in CP-140482. Dec.14: 50->100 | 23.008, 29.002, 29.272, 29.274, 29.305 | 65 | 33 |  |  | Mon 28/07/14 | Thu 04/12/14
3738 | 660075 | UE Conformance Test Aspects – WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-UEConTest | 1 | Rel-12 | R5 | Mon 15/12/14 | Tue 15/03/16 | 100% | RP-151270 | RP-151264 | Intel | Intel | Rel13->Rel-12¦Moved at appropriate place 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150098 03/07/15: Compl:5%->20% 03/07/15: Stat Rep: RP-150098->RP-150929 29/09/15: Compl:20%->60% 29/09/15: WID: RP-141879->RP-151270 29/09/15: Stat Rep: RP-15 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
3739 | 551000 | Rel-12 LTE Carrier Aggregation | LTE_CA_Rel-12 | 1 | Rel-12 | R4 | Mon 19/09/11 | Thu 15/12/16 | 100% | - | - | - | - | LTE_CA_Rel-12 | LTE | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
3740 | 530025 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7 | 2 | Rel-12 | R4 | Mon 19/09/11 | Fri 12/09/14 | 100% | RP-141487 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2DL | LTE | 53 | 27 |  |  | Thu 15/09/11 | Sat 07/12/13
3741 | 530125 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7-Core | 3 | Rel-12 | R4 | Mon 19/09/11 | Fri 12/09/14 | 100% | RP-141487 | RP-141084 | Ericsson | christian.bergljung@ericsson.com | RP#65 completed. Updated WID RP-132042=>RP-141487 | 36.101, 36.104, new generic 36.851 | 53 | 27 |  |  | Thu 15/09/11 | Sat 20/09/14
3742 | 530225 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7 | LTE_CA_B1_B7-Perf | 3 | Rel-12 | R4 | Mon 03/10/11 | Fri 12/09/14 | 100% | RP-141487 | RP-141084 | Ericsson | christian.bergljung@ericsson.com | RP#65 completed | 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Mon 08/09/14
3743 | 530029 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25 | 2 | Rel-12 | R4 | Mon 19/09/11 | Fri 14/06/13 | 100% | RP-130179 | - | Sprint | George.Cummings@sprint.com | Intra-band NC | LTE | 53 | 27 |  |  | Thu 15/09/11 | Fri 07/06/13
3744 | 530129 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25-Core | 3 | Rel-12 | R4 | Mon 19/09/11 | Fri 14/06/13 | 100% | RP-130179 | RP-130563 | Sprint | George.Cummings@sprint.com | RP#60 completed. TR 36.841 for 1-step Approval | 36.101, 36.104, 36.133, new 36.833-2-25 | 53 | 27 |  |  | Thu 15/09/11 | Fri 07/06/13
3745 | 530229 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25-Perf | 3 | Rel-12 | R4 | Mon 19/09/11 | Fri 14/06/13 | 100% | RP-130179 | RP-130759 | Sprint | George.Cummings@sprint.com | RP#60 completed | 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Mon 10/06/13
3746 | 550010 | Deleted -LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL | 2 | Rel-12 | R4 | Mon 05/03/12 | Fri 01/03/13 | 100% | RP-120867 | - | SK Telecom | Seungpyo Hong | Inter-band 2UL | LTE | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
3747 | 550110 | Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Core | 3 | Rel-12 | R4 | Mon 05/03/12 | Fri 01/03/13 | 100% | RP-120867 | RP-130098 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.101, 36.104, 36.133, 36.307, new generic 36.851 | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
3748 | 550210 | Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Perf | 3 | Rel-12 | R4 | Mon 12/03/12 | Fri 01/03/13 | 100% | RP-120867 | RP-130099 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.133, 36.141 | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
3749 | 670049 | UE Conformance Test Aspects - Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 2UL | LTE_CA_Rel12_2UL-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Thu 15/12/16 | 100% | RP-160071 |  | Ericsson | NA | 03/07/15: Compl:0%->29% 03/07/15: Stat Rep: ->RP-150834 29/09/15: Compl:29%->55% 29/09/15: Stat Rep: RP-150834->RP-151166 1/1/16: Compl:55%->70% 1/1/16: CD:Tue 15/12/15->Tue 15/03/16 1/1/16: WID: RP-1¦ |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 20/12/16
3750 | 550011 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3 | 2 | Rel-12 | R4 | Mon 05/03/12 | Fri 06/12/13 | 100% | RP-131359 | - | SK Telecom | haesung.park@sk.com | Intra-band NC | LTE | 55 | 28 |  |  | Thu 23/02/12 | Thu 23/02/12
3751 | 550111 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3-Core | 3 | Rel-12 | R4 | Mon 05/03/12 | Fri 06/12/13 | 100% | RP-131359 | RP-131573 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, new 36.833-2-03 | 55 | 28 |  |  | Thu 23/02/12 | Mon 02/12/13
3752 | 550211 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3 | LTE_CA_NC_B3-Perf | 3 | Rel-12 | R4 | Thu 15/03/12 | Fri 06/12/13 | 100% | RP-131359 | RP-131574 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 55 | 28 |  |  | Thu 23/02/12 | Mon 02/12/13
3753 | 560015 | Deleted - LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1 | 2 | Rel-12 | R4 | Mon 18/06/12 | Fri 14/06/13 | 100% | RP-130298 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Intra-band C | LTE | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
3754 | 560115 | Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1-Core | 3 | Rel-12 | R4 | Mon 18/06/12 | Fri 14/06/13 | 100% | RP-120826 | RP-130549 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 10% completion (rationale in RP-130670) | 36.101, 36.104, 36.133, 36.141, 36.307, new 36.835 | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
3755 | 560215 | Deleted - Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1 | LTE_CA_C_B1-Perf | 3 | Rel-12 | R4 | Fri 22/06/12 | Fri 14/06/13 | 100% | RP-120826 | RP-130550 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
3756 | 560016 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4 | 2 | Rel-12 | R4 | Mon 18/06/12 | Fri 06/09/13 | 100% | RP-131135 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band NC | LTE | 56 | 29 |  |  | Wed 13/06/12 | Wed 12/06/13
3757 | 560116 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4-Core | 3 | Rel-12 | R4 | Mon 18/06/12 | Fri 06/09/13 | 100% | RP-131135 | RP-131039 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, new 36.833-2-04 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
3758 | 560216 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 | LTE_CA_NC_B4-Perf | 3 | Rel-12 | R4 | Fri 22/06/12 | Fri 06/09/13 | 100% | RP-131135 | RP-131040 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
3759 | 560017 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4 | 2 | Rel-12 | R4 | Mon 18/06/12 | Fri 06/09/13 | 100% | RP-130175 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 1 UL | LTE | 56 | 29 |  |  | Wed 13/06/12 | Fri 07/09/12
3760 | 560117 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4-Core | 3 | Rel-12 | R4 | Mon 18/06/12 | Fri 06/09/13 | 100% | RP-130175 | RP-131007 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, new generic 36.851 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
3761 | 560217 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4-Perf | 3 | Rel-12 | R4 | Fri 22/06/12 | Fri 06/09/13 | 100% | RP-130175 | RP-131376 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
3762 | 570012 | LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29 | 2 | Rel-12 | R4 | Wed 12/09/12 | Fri 14/06/13 | 100% | RP-130170 | - | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Mon 03/09/12
3763 | 570112 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29-Core | 3 | Rel-12 | R4 | Wed 12/09/12 | Fri 14/06/13 | 100% | RP-130170 | RP-130535 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.101, 36.104, 36.133, new generic 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
3764 | 570212 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29 | LTE_CA_B23_B29-Perf | 3 | Rel-12 | R4 | Wed 12/09/12 | Fri 14/06/13 | 100% | RP-130170 | RP-130536 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
3765 | 570013 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26 | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130658 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
3766 | 570113 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26-Core | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130658 | RP-130527 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.307, new generic 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
3767 | 570213 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26 | LTE_CA_B3_B26-Perf | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130658 | RP-130528 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
3768 | 570014 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19 | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130198 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
3769 | 570114 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19-Core | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130198 | RP-130525 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Sat 08/06/13
3770 | 570214 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19 | LTE_CA_B3_B19-Perf | 3 | Rel-12 | R4 | Thu 13/09/12 | Fri 14/06/13 | 100% | RP-130198 | RP-130526 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Sat 08/06/13
3771 | 570015 | Deleted -LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39 | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 07/12/12 | 100% | RP-121178 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 1 UL | LTE | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
3772 | 570115 | Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39-Core | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 07/12/12 | 100% | RP-121178 | RP-121624 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 10% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.101, 36.104, 36.307, new generic 36.851 | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
3773 | 570215 | Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 | LTE_CA_B38_B39-Perf | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 07/12/12 | 100% | RP-121178 | RP-121625 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 0% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.133, 36.141 | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
3774 | 570016 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3 | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-131184 | - | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | Intra-band NC | LTE | 57 | 29 |  |  | Mon 03/09/12 | Thu 29/08/13
3775 | 570116 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3-Core | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-131184 | RP-131029 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs) | 36.101, 36.104, 36.133, new 36.833-1-03 | 57 | 29 |  |  | Mon 03/09/12 | Wed 04/09/13
3776 | 570216 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3 | LTE_CA_C_B3-Perf | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-131184 | RP-131030 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Wed 04/09/13
3777 | 570018 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8 | 2 | Rel-12 | R4 | Thu 02/02/12 | Fri 14/06/13 | 100% | RP-130181 | - | Softbank Mobile | Kenichi Kihara | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Wed 28/11/12
3778 | 570118 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8-Core | 3 | Rel-12 | R4 | Thu 02/02/12 | Fri 14/06/13 | 100% | RP-130181 | RP-130515 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.101, 36.104, new generic 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
3779 | 570218 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8 | LTE_CA_B1_B8-Perf | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130181 | RP-130516 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
3780 | 570026 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28 | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130189 | - | eAccess | FukumotoShiro@eaccess.net | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
3781 | 570126 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28-Core | 3 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-130189 | RP-130529 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.101, 36.104, new generic 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
3782 | 570226 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28 | LTE_CA_B3_B28-Perf | 3 | Rel-12 | R4 | Wed 12/09/12 | Fri 14/06/13 | 100% | RP-130189 | RP-130530 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
3783 | 580032 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26 | 2 | Rel-12 | R4 | Fri 07/12/12 | Fri 06/09/13 | 100% | RP-130668 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
3784 | 580132 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26-Core | 3 | Rel-12 | R4 | Fri 07/12/12 | Fri 06/09/13 | 100% | RP-130668 | RP-131005 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, 36.104, 36.133, new generic 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Wed 28/08/13
3785 | 580232 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26 | LTE_CA_B1_B26-Perf | 3 | Rel-12 | R4 | Fri 07/12/12 | Fri 06/09/13 | 100% | RP-130668 | RP-131006 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Wed 28/08/13
3786 | 580033 | LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41 | 2 | Rel-12 | R4 | Mon 10/12/12 | Thu 06/03/14 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
3787 | 580133 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41-Core | 3 | Rel-12 | R4 | Mon 10/12/12 | Thu 06/03/14 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed. Replaces the Stopped WI - LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 (LTE_CA_B38_B39) UID_570015 | 36.101, 36.104, 36.307, new generic 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
3788 | 580233 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41 | LTE_CA_B39_B41-Perf | 3 | Rel-12 | R4 | Fri 14/12/12 | Thu 06/03/14 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed | 36.133, 36.141 | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
3789 | 580034 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12 | 2 | Rel-12 | R4 | Mon 10/12/12 | Fri 12/09/14 | 100% | RP-140474 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/09/14
3790 | 580134 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12-Core | 3 | Rel-12 | R4 | Mon 10/12/12 | Fri 12/09/14 | 100% | RP-140474 | RP-141084 | US Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/09/14
3791 | 580234 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12 | LTE_CA_B2_B12-Perf | 3 | Rel-12 | R4 | Fri 14/12/12 | Thu 06/03/14 | 100% | RP-140474 | RP-140428 | US Cellular | sebastian.thalanany@uscellular.com | RP#63 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Tue 04/03/14
3792 | 580035 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7 | 2 | Rel-12 | R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-130813 | - | Ericsson | christian.bergljung@ericsson.com | Intra-band NC | LTE | 58 | 30 |  |  | Mon 10/12/12 | Thu 28/02/13
3793 | 580135 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7-Core | 3 | Rel-12 | R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-130813 | RP-131575 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.101, 36.104, 36.133, new 36.833-2-07 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
3794 | 580235 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7 | LTE_CA_NC_B7-Perf | 3 | Rel-12 | R4 | Fri 14/12/12 | Fri 06/12/13 | 100% | RP-130813 | RP-131576 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
3795 | 580036 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27 | 2 | Rel-12 | R4 | Mon 10/12/12 | Fri 13/06/14 | 100% | RP-131679 | - | NII Holdings | bill.shvodian@nii.com | Intra-band contig. CA 2DL/1UL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Thu 19/12/13
3796 | 580136 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27-Core | 3 | Rel-12 | R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-131679 | RP-131567 | NII Holdings | bill.shvodian@nii.com | RP#62 completed | 36.101, 36.104, new 36.833-1-27 | 58 | 30 |  |  | Mon 10/12/12 | Fri 06/12/13
3797 | 580236 | Perf part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27 | LTE_CA_C_B27-Perf | 3 | Rel-12 | R4 | Fri 14/12/12 | Fri 13/06/14 | 100% | RP-131679 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed. TR 36.833-1-27v200 for Approval | 36.101, 36.133, 36.141, 36.307, new 36.833-1-27 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
3798 | 590022 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13 | 2 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130196 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band 1 UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3799 | 590122 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130196 | RP-130523 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, new generic 36.851 | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3800 | 590222 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13 | LTE_CA_B2_B13-Perf | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130196 | RP-130524 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3801 | 590024 | LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21 | 2 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130197 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3802 | 590124 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130197 | RP-130533 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic 36.851 | 59 | 30 |  |  | Tue 26/02/13 | Sat 08/06/13
3803 | 590224 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21 | LTE_CA_B19_B21-Perf | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130197 | RP-130534 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Sat 08/06/13
3804 | 590025 | Deleted -LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26 | 2 | Rel-12 | R4 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-130201 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Tue 26/02/13
3805 | 590125 | Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-130201 | RP-131549 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.101, 36.104, 36.133, new generic 36.851 | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Mon 02/12/13
3806 | 590225 | Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26 | LTE_CA_B8_B26-Perf | 3 | Rel-12 | R4 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-130201 | RP-131550 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.141, 36.307 | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Mon 02/12/13
3807 | 590029 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1 | 2 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-140475 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
3808 | 590129 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-141941 | RP-141732 | Huawei | Liu Ye (leo.liuye@huawei.com) | ¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, New generic 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3809 | 590229 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Perf | 3 | Rel-12 | R4 | Wed 13/03/13 | Mon 15/12/14 | 100% | RP-141941 | RP-141732 | Huawei | Liu Ye (leo.liuye@huawei.com) | ¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732 | 36.133 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3810 | 590028 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2 | 2 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-130327 | - | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
3811 | 590128 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-130327 | RP-141732 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | ¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3812 | 590228 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Perf | 3 | Rel-12 | R4 | Wed 13/03/13 | Mon 15/12/14 | 100% | RP-130327 | RP-141732 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | ¦Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3813 | 590023 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3 | 2 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-140853 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
3814 | 590123 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-140853 | RP-141732 | Ericsson | christian.bergljung@ericsson.com | ¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3815 | 590223 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Perf | 3 | Rel-12 | R4 | Wed 13/03/13 | Mon 15/12/14 | 100% | RP-140853 | RP-141732 | Ericsson | christian.bergljung@ericsson.com | ¦Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3816 | 590031 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4 | 2 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-141160 | - | Nokia | petri.j.vasenkari@nokia.com | Inter-band CA 2UL. RP#65 updated WID RP-140476=>RP-141160. | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
3817 | 590131 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-141967 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3818 | 590231 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Perf | 3 | Rel-12 | R4 | Wed 13/03/13 | Mon 15/12/14 | 100% | RP-141967 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3819 | 590026 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5 | 2 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-141195 | - | NTT DOCOMO | kei.andou.ye@nttdocomo.com | Inter-band CA 2UL. RP#65 updated WID RP-131146=>RP-141195. Changed Rapp Renesas=>Broadcom=>NTT DOCOMO | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
3820 | 590126 | Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Mon 15/12/14 | 100% | RP-141195 | RP-141732 | NTT DOCOMO | kei.andou.ye@nttdocomo.com | ¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3821 | 590226 | Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Perf | 3 | Rel-12 | R4 | Wed 13/03/13 | Mon 15/12/14 | 100% | RP-141195 | RP-141732 | NTT DOCOMO | kei.andou.ye@nttdocomo.com | ¦Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3822 | 590027 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39 | 2 | Rel-12 | R4 | Mon 04/03/13 | Thu 06/03/14 | 100% | RP-131171 | - | China Mobile | Li Nan (linan@chinamobile.com) | Intra-band C 2DL/2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
3823 | 590127 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39-Core | 3 | Rel-12 | R4 | Mon 04/03/13 | Thu 06/03/14 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.101, 36.104, 36.133, New 36.833-1-39 [instead of 36.845] | 59 | 30 |  |  | Tue 26/02/13 | Wed 05/03/14
3824 | 590227 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39 | LTE_CA_C_B39-Perf | 3 | Rel-12 | R4 | Thu 07/03/13 | Thu 06/03/14 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Wed 05/03/14
3825 | 600022 | LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL | 2 | Rel-12 | R4 | Tue 18/06/13 | Mon 15/12/14 | 100% | RP-140267 | - | Nokia | petri.j.vasenkari@nokia.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
3826 | 600122 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Mon 15/12/14 | 100% | RP-141962 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ¦WID: RP-142043->RP-141962¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.306, 36.331, New 36.833-4 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3827 | 600023 | Deleted -LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL | 2 | Rel-12 | R4 | Wed 19/06/13 | Thu 06/03/14 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | Intra-band NC 2UL | LTE | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3828 | 600123 | Deleted - Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Core | 3 | Rel-12 | R4 | Wed 19/06/13 | Thu 06/03/14 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (5% complete). Reason: Market conditions have eliminated the need for this feature, at least for the foreseeable future | 36.101, 36.104, 36.133, new 36.833-3-41 | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3829 | 600223 | Deleted - Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Perf | 3 | Rel-12 | R4 | Thu 20/06/13 | Thu 06/03/14 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (0% complete). | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3830 | 600024 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL | 2 | Rel-12 | R4 | Wed 19/06/13 | Mon 15/12/14 | 100% | RP-131136 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
3831 | 600124 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Core | 3 | Rel-12 | R4 | Wed 19/06/13 | Mon 15/12/14 | 100% | RP-141784 | RP-141732 | T-Mobile USA | nelson.ueng@t-mobile.com | ¦WID: RP-142043->RP-141784¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, new 36.833-4-04 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3832 | 600224 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Perf | 3 | Rel-12 | R4 | Tue 25/06/13 | Mon 15/12/14 | 100% | RP-141784 | RP-141732 | T-Mobile USA | nelson.ueng@t-mobile.com | ¦WID: RP-142043->RP-141784¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3833 | 600025 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131265 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band C CA | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
3834 | 600125 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131265 | RP-131565 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new 36.833-1-23 [instead of 36.864] | 60 | 31 |  |  | Mon 17/06/13 | Mon 02/12/13
3835 | 600225 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23 | LTE_CA_C_B23-Perf | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131265 | RP-131566 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 02/12/13
3836 | 600026 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 13/06/14 | 100% | RP-131700 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Thu 19/12/13
3837 | 600126 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131700 | RP-131577 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new 36.833-2-23 | 60 | 31 |  |  | Mon 17/06/13 | Thu 19/12/13
3838 | 600226 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23 | LTE_CA_NC_B23-Perf | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 13/06/14 | 100% | RP-131700 | RP-140569 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#64 completed. TR 36.833-2-23v200 for Approval | 36.101, 36.133, 36.141, 36.307, new 36.833-2-23 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
3839 | 600028 | LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131159 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
3840 | 600128 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131159 | RP-131705 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic 36.851 | 60 | 31 |  |  | Wed 05/06/13 | Mon 02/12/13
3841 | 600228 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25 | LTE_CA_B12_B25-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 06/12/13 | 100% | RP-131159 | RP-131706 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Mon 02/12/13
3842 | 600029 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130669 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
3843 | 600129 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130669 | RP-131003 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, new generic 36.851 | 60 | 31 |  |  | Wed 05/06/13 | Wed 28/08/13
3844 | 600229 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Perf | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130669 | RP-131004 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Wed 28/08/13
3845 | 600030 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130675 | - | AT&T | marc.grant@att.com | Inter-band 2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
3846 | 600130 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130675 | RP-131009 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Fri 30/08/13
3847 | 600230 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5-Perf | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/09/13 | 100% | RP-130675 | RP-131010 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Fri 30/08/13
3848 | 600031 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-131696 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3849 | 600131 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-131696 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. TR 36.853v200 for Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3850 | 600231 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Perf | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-131696 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3851 | 600032 | Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131130 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3852 | 600132 | Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131130 | RP-131590 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3853 | 600232 | Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 06/12/13 | 100% | RP-131130 | RP-131591 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3854 | 600033 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30 | 2 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141212 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3855 | 600133 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Core | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141212 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131697=>RP-141212 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3856 | 600233 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141212 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3857 | 600034 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30 | 2 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141213 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3858 | 600134 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Core | 3 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141213 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131698=>RP-141213 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3859 | 600234 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141213 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3860 | 600035 | Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131133 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Mon 17/06/13
3861 | 600135 | Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-131133 | RP-131598 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3862 | 600235 | Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 06/12/13 | 100% | RP-131133 | RP-131599 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
3863 | 600036 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30 | 2 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141215 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3864 | 600136 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Core | 3 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141215 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131699=>RP- 141215 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3865 | 600236 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141215 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
3866 | 600037 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13 | 2 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141434 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3867 | 600137 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Core | 3 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141434 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated RP-131684=>RP-141434 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3868 | 600237 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141434 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3869 | 600038 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13 | 2 | Rel-12 | R4 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-141435 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3870 | 600138 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Core | 3 | Rel-12 | R4 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-141435 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated WID RP-131682=>RP-141435 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3871 | 600238 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Perf | 3 | Rel-12 | R4 | Wed 19/06/13 | Fri 12/09/14 | 100% | RP-141435 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3872 | 600039 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13 | 2 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141433 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3873 | 600139 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Core | 3 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141433 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated WID RP-131683=>RP-141433 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3874 | 600239 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Perf | 3 | Rel-12 | R4 | Fri 14/06/13 | Fri 12/09/14 | 100% | RP-141433 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
3875 | 610017 | LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28 | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131307 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3876 | 610117 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131307 | RP-131545 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.101, 36.104, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
3877 | 610217 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28 | LTE_CA_B7_B28-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131307 | RP-131546 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.141 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3878 | 610018 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25 | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131343 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3879 | 610118 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131343 | RP-131543 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3880 | 610218 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25 | LTE_CA_B5_B25-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131343 | RP-131705 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3881 | 610019 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11 | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-131354 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3882 | 610119 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.101, 36.104, new generic 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Fri 20/06/14
3883 | 610219 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11 | LTE_CA_B1_B11-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Fri 20/06/14
3884 | 610020 | LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11 | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 12/09/14 | 100% | RP-131355 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
3885 | 610120 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 12/09/14 | 100% | RP-131355 | RP-141084 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#65 completed | 36.101, 36.104, new generic 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
3886 | 610220 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11 | LTE_CA_B8_B11-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 12/09/14 | 100% | RP-131355 | RP-141084 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#65 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
3887 | 610021 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7 | 2 | Rel-12 | R4 | Mon 09/09/13 | Mon 02/12/13 | 100% | RP-131365 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3888 | 610121 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Mon 02/12/13 | 100% | RP-131365 | RP-131541 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.101, 36.104, 36.133, new generic 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3889 | 610221 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7 | LTE_CA_B5_B7-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Mon 02/12/13 | 100% | RP-131365 | RP-131542 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
3890 | 610022 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/03/15 | 100% | RP-140100 | - | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band contig. CA 3DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
3891 | 610122 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 12/09/14 | 100% | RP-140100 | RP-141084 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#65 completed | 36.101, 36.104, 36.133, 36.307, New 36.833-5-41 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
3892 | 610222 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL-Perf | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/03/15 | 100% | RP-142017 | RP-150013 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | ¦WID: RP-142043->RP-142017¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141 | 61 | 31 |  |  | Sat 07/09/13 | Wed 01/04/15
3893 | 610023 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2 | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-131366 | - | Ericsson | imadur.rahman@ericsson.com | Intra-band non-contig. CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
3894 | 610123 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2-Core | 3 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed. TR 36.833-2-02v100 for 1-step Approval | 36.101, 36.104, 36.133, New 36.833-2-02 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
3895 | 610223 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2 | LTE_CA_NC_B2-Perf | 3 | Rel-12 | R4 | Tue 10/09/13 | Fri 13/06/14 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
3896 | 620018 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-132022 | - | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
3897 | 620118 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-132022 | RP-141084 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | RP#65 completed | 36.101, 36.104, 36.133, new generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3898 | 620218 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3 | LTE_CA_B1_B3-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-132022 | RP-141084 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3899 | 620019 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28 | 2 | Rel-12 | R4 | Mon 09/12/13 | Mon 15/12/14 | 100% | RP-132028 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
3900 | 620119 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Mon 15/12/14 | 100% | RP-141803 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.307, new generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
3901 | 620219 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Perf | 3 | Rel-12 | R4 | Thu 12/12/13 | Mon 15/12/14 | 100% | RP-141803 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732 | 36.133, 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
3902 | 620020 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset | 2 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-131656 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
3903 | 620120 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.101, new generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
3904 | 620220 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
3905 | 620021 | LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140142 | - | NII Holdings | bill.shvodian@nii.com | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
3906 | 620121 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.101, 36.104, 36.133, new generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
3907 | 620221 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27 | LTE_CA_B4_B27-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
3908 | 620022 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27 | 2 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
3909 | 620122 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.307, New generic 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
3910 | 620222 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27 | LTE_CA_B3_B27-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
3911 | 620072 | LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW | 2 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | Inter-band 2DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
3912 | 620172 | Core part:LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.101, 36.104, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
3913 | 620272 | Perf. part:LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 06/03/14 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.141 | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
3914 | 620024 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141654 | - | KT | Ilwhan Kim (ilwhan.kim@kt.com) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3915 | 620124 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141654 | RP-141084 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | RP#65 completed. Updated WID RP-131753=>RP-141654 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3916 | 620224 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141654 | RP-141084 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3917 | 620025 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141462 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3918 | 620125 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141462 | RP-141084 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#65 completed. Updated WID RP-140209=>RP-141462 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3919 | 620225 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141462 | RP-141084 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
3920 | 620026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140186 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3921 | 620126 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140186 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3922 | 620226 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140186 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3923 | 620027 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12 | 2 | Rel-12 | R4 | Mon 09/12/13 | Thu 11/12/14 | 100% | RP-140189 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
3924 | 620127 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140189 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Tue 30/09/14
3925 | 620227 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 11/12/14 | 100% | RP-140189 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completion 09/14=>12/14 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 12/09/14
3926 | 620028 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140190 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3927 | 620128 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140190 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3928 | 620228 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Perf | 3 | Rel-12 | R4 | Tue 10/12/13 | Fri 12/09/14 | 100% | RP-140190 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3929 | 620029 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131654 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3930 | 620129 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131654 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3931 | 620229 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131654 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3932 | 620030 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141211 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3933 | 620130 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141211 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131652=>RP-141211. | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3934 | 620230 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141211 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3935 | 620031 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141224 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
3936 | 620131 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141224 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-140244=>RP-141224 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
3937 | 620231 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Perf | 3 | Rel-12 | R4 | Tue 10/12/13 | Fri 12/09/14 | 100% | RP-141224 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
3938 | 620033 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140191 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3939 | 620133 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140191 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3940 | 620233 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140191 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3941 | 620034 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131655 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3942 | 620134 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131655 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3943 | 620234 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-131655 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3944 | 620035 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141214 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3945 | 620135 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141214 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131653=>RP-141214 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3946 | 620235 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141214 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3947 | 620037 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140728 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 2DL/2UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
3948 | 620137 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.101, 36.104, 36.133, new 36.833-1-42 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
3949 | 620237 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 | LTE_CA_C_B42-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
3950 | 620036 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-131810 | - | Orange | Olfa BEN HADDADA | Intra-band contig. CA 2DL/2UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
3951 | 620136 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.101, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
3952 | 620236 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
3953 | 620038 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/03/15 | 100% | RP-140101 | - | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band non-contig. CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3954 | 620138 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Thu 11/09/14 | 100% | RP-140101 | RP-141084 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#65 completed | 36.101, 36.104, 36.133, 36.307, new 36.833-6-xy | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
3955 | 620238 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/03/15 | 100% | RP-140101 | RP-150013 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | CD:Thu 12/03/15->Sun 15/03/15¦Compl:60%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Wed 01/04/15
3956 | 620039 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140671 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
3957 | 620139 | Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed. Updated WID RP-140404=>RP-140671. TR 36.833-2-42v100 for 1-step Approval | 36.101, 36.104, 36.133, new 36.833-2-42 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
3958 | 620239 | Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 | LTE_CA_NC_B42-Perf | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
3959 | 620050 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5 | 2 | Rel-12 | R4 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-141454 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3960 | 620150 | Core part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Core | 3 | Rel-12 | R4 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-141454 | RP-141084 | SK Telecom | haesung.park@sk.com | RP#65 completed. Updated WID RP-132121=>RP-141454 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3961 | 620250 | Perf. part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Perf | 3 | Rel-12 | R4 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-141454 | RP-141084 | SK Telecom | haesung.park@sk.com | RP#65 completed. Updated WID RP-132121=>RP-141454 | 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3962 | 620051 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141222 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3963 | 620151 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141222 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-141017=>RP-141222 | 36.101, 36.104, 36.133, new generic 36.851 (2 Band CA with 1UL), 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3964 | 620251 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Perf | 3 | Rel-12 | R4 | Tue 10/12/13 | Fri 12/09/14 | 100% | RP-141222 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3965 | 620052 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20 | 2 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141223 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3966 | 620152 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-141223 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-140243=>RP-141223 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3967 | 620252 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Perf | 3 | Rel-12 | R4 | Tue 10/12/13 | Fri 12/09/14 | 100% | RP-141223 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
3968 | 620053 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20 | 2 | Rel-12 | R4 | Mon 09/12/13 | Mon 15/12/14 | 100% | RP-132080 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Tue 09/09/14
3969 | 620153 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Core | 3 | Rel-12 | R4 | Mon 09/12/13 | Mon 15/12/14 | 100% | RP-132080 | RP-141732 | Vodafone | luis.anaya@vodafone.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3970 | 620253 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Perf | 3 | Rel-12 | R4 | Thu 12/12/13 | Mon 15/12/14 | 100% | RP-132080 | RP-141732 | Vodafone | luis.anaya@vodafone.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3971 | 630022 | Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_Bwset | 2 | Rel-12 | R4 | Mon 03/03/14 | Thu 06/03/14 | 100% | RP-140084 | - | AT&T | marc.grant@att.com | Inter-band 2DL/1UL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Wed 12/03/14
3972 | 630122 | Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_BWset-Core | 3 | Rel-12 | R4 | Mon 03/03/14 | Thu 06/03/14 | 100% | RP-140084 | RP-140428 | AT&T | marc.grant@att.com | RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected | 36.101, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Wed 12/03/14
3973 | 630023 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20_BWset | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140447 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3974 | 630123 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20_BWset-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140447 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
3975 | 630024 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20_BWset | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140448 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3976 | 630124 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20_BWset-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140448 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
3977 | 630025 | Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback | LTE_CA_3DL_FB_BW | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140454 | - | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3978 | 630125 | Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback | LTE_CA_3DL_FB_BW-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140454 | RP-140569 | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | RP#64 completed, Additional BW combinations added for 6 Wis: 3 open Rel-12 Wis (B1_B5_B7, B2_B29_B30, B4_B29_B30) and 3 completed Rel-11 Wis (B3_B5, B4_B5, B4_B12) | 36.101, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
3979 | 630026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141196 | - | Nokia Networks | iwajlo.angelow@nsn.com | Inter-band CA 3DL. Mar15: acronym reverted to LTE_CA_B3_B7_B7_ | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
3980 | 630126 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141196 | RP-141084 | Nokia Networks | iwajlo.angelow@nsn.com | RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_ | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
3981 | 630226 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141196 | RP-141084 | Nokia Networks | iwajlo.angelow@nsn.com | RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_ | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
3982 | 630027 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141193 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3983 | 630127 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141193 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed. Updated WID RP-140106=>RP-141193 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3984 | 630227 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141193 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed. Updated WID RP-140106=>RP-141193 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3985 | 630028 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141126 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3986 | 630128 | Core part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141126 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated RP-140390=>RP-141126 | 36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3987 | 630228 | Perf. part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141126 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated RP-140390=>RP-141126 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3988 | 630029 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140948 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Intra-band contig. CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3989 | 630129 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.101, 36.104, 36.133, New 36.833-5-40 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
3990 | 630229 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/06/14 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
3991 | 630035 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset | 2 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-141235 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3992 | 630135 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Core | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-141235 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed. Updated WID RP-140987=>RP-141235 (removed Perf. Part) | 36.101, generic 36.850 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3993 | 630235 | Deleted - Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Perf | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-141235 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 stopped. Updated WID RP-140987=>RP-141235 (removed Perf. Part) | 36.307 | 63 | 32 | RP-65 | PCG-33 | Mon 10/03/14 | Sun 21/09/14
3994 | 630036 | LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-140450 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3995 | 630136 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-140450 | RP-141084 | Huawei | leo.liuye@huawei.com | RP#65 completed | 36.101, 36.104, 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3996 | 630236 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42 | LTE_CA_B41_B42-Perf | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-140450 | RP-141084 | Huawei | leo.liuye@huawei.com | RP#65 completed | 36.141 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
3997 | 630037 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141709 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
3998 | 630137 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141709 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed. Updated WID RP-140116=>RP-141709 | 36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
3999 | 630237 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Perf | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-141709 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
4000 | 630038 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4 | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141236 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
4001 | 630138 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-141236 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | RP#65 completed. Updated WID RP-140117=>RP-141236 | 36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
4002 | 630238 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Perf | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-141236 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
4003 | 630045 | Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-140452 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
4004 | 630145 | Core part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-140452 | RP-141084 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#65 completed | 36.101, 36.307, 36.833-2-25 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
4005 | 630245 | Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25 | LTE_CA_NC_B25_BWset-Perf | 3 | Rel-12 | R4 | Fri 07/03/14 | Fri 12/09/14 | 100% | RP-140452 | RP-141084 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#65 completed | 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
4006 | 640020 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4_Bwset2 | 2 | Rel-12 | R4 | Sun 15/06/14 | Fri 12/09/14 | 100% | RP-140599 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | Inter-band CA 2DL. Mar 15: acronym changed from LTE_CA_B2_B4_Bwset_ | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 10/03/15
4007 | 640120 | Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 | LTE_CA_B2_B4_BWset2-Core | 3 | Rel-12 | R4 | Sun 15/06/14 | Fri 12/09/14 | 100% | RP-140599 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | Dec 14: Prev CD:Fri 12/09/14¦Prev %:100%, title changed. Mar 15: Acronym changed to LTE_CA_B2_B4_BWset2-Core_ | 36.101, 36.851 | 64 | 33 |  |  | Mon 16/06/14 | Tue 10/03/15
4008 | 640021 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_BWset | 2 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140642 | - | AT&T | marc.grant@att.com | 2DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4009 | 640121 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_Bwset-Core | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140642 | RP-141732 | AT&T | marc.grant@att.com | ¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732 | 36.101, 36.851 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4010 | 640221 | Perf. Part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_BWset-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140642 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 | 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4011 | 640027 | E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141304 | - | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | LTE | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4012 | 640127 | Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult-Perf | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141304 | RP-150188 | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | CD:Thu 12/03/15->Sun 15/03/15¦Compl:10%->90%¦Stat Rep: RP-141303->RP-141839 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141839->RP-150188 | 36.101 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
4013 | 640028 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19 | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141004 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4014 | 640128 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141004 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4015 | 640228 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Perf | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141004 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4016 | 640029 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42 | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141007 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4017 | 640129 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141007 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4018 | 640229 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Perf | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141007 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4019 | 640030 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42 | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141005 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4020 | 640130 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141005 | RP-150013 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | CD:Thu 11/12/14->Sun 15/03/15¦Compl:50%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
4021 | 640230 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Perf | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 13/03/15 | 100% | RP-141005 | RP-150013 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | CD:Thu 11/12/14->Tue 15/03/16¦Compl:50%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: CD:Tue 15/03/16->Sun 15/03/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
4022 | 640031 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42 | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141006 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4023 | 640131 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141006 | RP-141084 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | RP#65 completed | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4024 | 640231 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Perf | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141006 | RP-141084 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4025 | 640035 | Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW | 2 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141127 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4026 | 640135 | Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Fri 12/09/14 | 100% | RP-141127 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated WID RP-140950=>RP-141127 | 36.101 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
4027 | 650054 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW-Perf | 3 | Rel-12 | R4 | Mon 08/09/14 | Fri 12/09/14 | 100% | RP-141127 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 updated WID RP-140950=>RP-141127 (added Perf. Part). Completed. | 36.307 | 65 | 33 |  |  | Sun 21/09/14 | Sun 05/10/14
4028 | 650010 | LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28 | LTE_CA_B18_B28 | 2 | Rel-12 | R4 | Wed 10/09/14 | Fri 12/09/14 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 2DL | LTE | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
4029 | 650110 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28 | LTE_CA_B18_B28-Core | 3 | Rel-12 | R4 | Wed 10/09/14 | Fri 12/09/14 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#65 WID approved & completed. Triggered by revised Rel-13 WID RP-140451=>RP-141610 (take out B18_B28 for Rel-12 from the Rel-13 B1_B18_B28) | 36.101, 36.104, 36.133 | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
4030 | 650210 | Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28 | LTE_CA_B18_B28-Perf | 3 | Rel-12 | R4 | Wed 10/09/14 | Fri 12/09/14 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307 | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
4031 | 630034 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140169 | - | Intel | xinrong.wang@intel.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4032 | 630134 | Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140169 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.851 (2 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4033 | 630234 | Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140169 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4034 | 630039 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140165 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4035 | 630139 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140165 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4036 | 630239 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140165 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4037 | 630040 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140166 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4038 | 630140 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140166 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4039 | 630240 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140166 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4040 | 630041 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140167 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4041 | 630141 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140167 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4042 | 630241 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140167 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4043 | 630042 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140168 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4044 | 630142 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140168 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4045 | 630242 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140168 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4046 | 630043 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140194 | - | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4047 | 630143 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140194 | RP-141732 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | CD:Thu 11/12/14->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4048 | 630243 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Perf | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-140194 | RP-141732 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | CD:Thu 11/12/14->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4049 | 630044 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28 | 2 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-141610 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4050 | 630144 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Core | 3 | Rel-12 | R4 | Thu 06/03/14 | Mon 15/12/14 | 100% | RP-141788 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-141788¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4051 | 630244 | Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Perf | 3 | Rel-12 | R4 | Tue 11/03/14 | Mon 15/12/14 | 100% | RP-141788 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-141788¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4052 | 640023 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12 | 2 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4053 | 640123 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Core | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140661 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, 36.307, generic 36.851 (2 Band CA with 1UL), generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4054 | 640223 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140661 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.133, 36.141 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4055 | 640024 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7 | 2 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4056 | 640124 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Core | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140662 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, 36.307, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4057 | 640224 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140662 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.133, 36.141 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4058 | 640026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41 | 2 | Rel-12 | R4 | Mon 16/06/14 | Mon 15/12/14 | 100% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4059 | 640126 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Core | 3 | Rel-12 | R4 | Mon 16/06/14 | Mon 15/12/14 | 100% | RP-142301 | RP-141732 | China Mobile | PAN Qun (panqun@chinamobile.com) | ¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4060 | 640226 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-142301 | RP-141732 | China Mobile | PAN Qun (panqun@chinamobile.com) | ¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4061 | 640033 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41 | 2 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4062 | 640133 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Core | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-142297 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4063 | 640233 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-142297 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | Compl:100%->0%¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4064 | 640034 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41 | 2 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
4065 | 640134 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Core | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-142298 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4066 | 640234 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Perf | 3 | Rel-12 | R4 | Wed 18/06/14 | Mon 15/12/14 | 100% | RP-142298 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | Compl:100%->0%¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4067 | 650046 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41 | 2 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141673 | - | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
4068 | 650146 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Core | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-142018 | RP-141732 | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | ¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.307, New 36.833-x-yz | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4069 | 650246 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Perf | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-142018 | RP-141732 | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | ¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.141 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4070 | 650048 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41 | 2 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141288 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
4071 | 650148 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Core | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-142302 | RP-141732 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4072 | 650248 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Perf | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-142302 | RP-141732 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4073 | 650050 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29 | 2 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141448 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
4074 | 650150 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Core | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141448 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4075 | 650250 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Perf | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141448 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4076 | 650052 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29 | 2 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141668 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
4077 | 650152 | Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Core | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141668 | RP-141732 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 11/12/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4078 | 650252 | Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Perf | 3 | Rel-12 | R4 | Mon 15/09/14 | Mon 15/12/14 | 100% | RP-141668 | RP-141732 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
4079 | 610013 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation | LTE_CA_Rel12-UEConTest | 1 | Rel-12 | R5 | Sun 15/09/13 | Fri 13/03/15 | 100% | RP-150077 | RP-150076 | Microsoft | jussi.kuusisto@microsoft.com | ¦Stat Rep: RP-141444->RP-141774 1st Apr 15: Compl:75%->100% 1st Apr 15: WID: RP-140621->RP-150077 1st Apr 15: Stat Rep: RP-141774->RP-150076 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 61 | 31 |  |  | Fri 30/08/13 | Wed 01/04/15
4080 | 650011 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 3DL | LTE_CA_Rel12_3DL-UEConTest | 1 | Rel-12 | R5 | Mon 15/09/14 | Tue 15/03/16 | 100% | RP-151821 | RP-151464 | Microsoft | jussi.kuusisto@microsoft.com | ¦Stat Rep: -->RP-141775 1st Apr 15: Compl:6%->12% 1st Apr 15: CD:Tue 15/09/15->Tue 15/12/15 1st Apr 15: WID: RP-142231->RP-150079 1st Apr 15: Stat Rep: RP-141775->RP-150078 03/07/15: Compl:12%->35% 03/07/15: WID: RP-150079->RP-150594 03/07/15: Stat Re | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 65 | 33 |  |  | Tue 09/09/14 | Tue 22/03/16
4081 | 510033 | Deleted - Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC | 1 | Rel-12 | R3,R1,R2 | Fri 18/03/11 | Fri 14/06/13 | 100% | RP-121198 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped. RP#58 on hold til June 2013 | LTE | 51 | 26 | RP-60 | PCG-31 | Mon 14/03/11 | Wed 12/06/13
4082 | 510133 | Deleted - Core part: Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC-Core | 2 | Rel-12 | R3,R1,R2 | Fri 18/03/11 | Fri 14/06/13 | 100% | RP-121198 | RP-130500 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped at 40% completion. RP#58 on hold til June 2013 | 36.300, 36.413, 36.420, 36.423 | 51 | 26 | RP-60 | PCG-31 | Mon 14/03/11 | Wed 12/06/13
4083 | 570017 | LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band | 1 | Rel-12 | R4,R2,R5 | Wed 12/09/12 | Mon 15/12/14 | 100% | RP-130843 | - | AT&T | marc.grant@att.com | RP#58 RP-121701 work can start based on FCC Order (FCC-12-130) http://hraunfoss.fcc.gov/edocs_public/attachmatch/FCC-12-130A1.pdf | LTE | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
4084 | 570117 | Core part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Core | 2 | Rel-12 | R4,R2 | Wed 12/09/12 | Fri 14/06/13 | 100% | RP-130843 | RP-130569 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, new 36.846 | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
4085 | 570217 | Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Perf | 2 | Rel-12 | R4 | Thu 13/09/12 | Fri 14/06/13 | 100% | RP-130843 | RP-130570 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.133, 36.141 | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
4086 | 640002 | Test Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-UEConTest | 2 | Rel-12 | R5 | Sun 15/06/14 | Mon 15/12/14 | 100% | RP-140643 | RP-141773 | Ericsson | fredrik.sundstrom@ericsson.com | ¦Stat Rep: RP-141166->RP-141773 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 64 | 33 |  |  | Wed 28/05/14 | Mon 12/01/15
4087 | 570019 | Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil | 1 | Rel-12 | R4,R5 | Tue 11/09/12 | Fri 06/12/13 | 100% | RP-121414 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | - | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
4088 | 570119 | Core part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Core | 2 | Rel-12 | R4 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-121414 | RP-130567 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#60 completed. TR 36.840 v100 for 1-step Approval | 36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new 36.840 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
4089 | 570219 | Perf. part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Perf | 2 | Rel-12 | R4 | Thu 13/09/12 | Fri 06/09/13 | 100% | RP-121414 | RP-131070 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#61 completed | 36.133, 36.141, 37.141 | 57 | 29 |  |  | Mon 03/09/12 | Fri 30/08/13
4090 | 600005 | Test part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-UEConTest | 2 | Rel-12 | R5 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-130646 | RP-131457 | Huawei | Xiang Li (tricia.li@huawei.com) | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3 | 60 | 31 |  |  | Thu 30/05/13 | Fri 29/11/13
4091 | 570020 | Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh | 1 | Rel-12 | R1,R4 | Tue 11/09/12 | Tue 15/03/16 | 100% | RP-121416 | - | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | Stage 3 | LTE | 57 | 29 |  |  | Mon 03/09/12 | Thu 06/12/12
4092 | 570120 | Core part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Core | 2 | Rel-12 | R1 | Tue 11/09/12 | Fri 13/06/14 | 100% | RP-121416 | RP-140652 | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | RP#64 completed | 36.211, 36.212, 36.213, 36.331 | 57 | 29 |  |  | Mon 03/09/12 | Sun 06/07/14
4093 | 570220 | Perf. part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Perf | 2 | Rel-12 | R4 | Sat 15/09/12 | Mon 15/12/14 | 100% | RP-121416 | RP-142042 | Alcatel-Lucent | ren.da@alcatel-lucent.com | ¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141378->RP-142042 | 36.101 | 57 | 29 |  |  | Mon 03/09/12 | Mon 12/01/15
4094 | 670045 | UE Conformance Test Aspects - Further DL MIMO Enhancement for LTE-Advanced | LTE_eDL_MIMO_enh-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Tue 15/03/16 | 100% | RP-150071 | RP-151189 | ZTE |  | 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150606 29/09/15: Compl:10%->70% 29/09/15: Stat Rep: RP-150606->RP-1511891/1/16: Compl:70%->75% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
4095 | 570025 | Deleted - New Carrier Type for LTE | LTE_NCT | 1 | Rel-12 | R1,R2,R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-122028 | - | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped. Continue discussion on use cases and requirements for a NCT in LTE beyond Rel-12. Action: Ericsson to provide at RP#62 a summary of work done so far | LTE | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
4096 | 570125 | Deleted - Core part: New Carrier Type for LTE | LTE_NCT-Core | 2 | Rel-12 | R1,R2,R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-122028 | RP-130984 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 20% completion | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.321, 36.331 | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
4097 | 570225 | Deleted - Perf. part: New Carrier Type for LTE | LTE_NCT-Perf | 2 | Rel-12 | R4 | Mon 17/09/12 | Fri 06/09/13 | 100% | RP-122028 | RP-130985 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141 | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
4098 | 580027 | Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA | 1 | Rel-12 | R1,R2,R3,R4 | Fri 07/12/12 | Thu 15/03/18 | 99% | RP-121772 | - | CATT | Zukang Shen (shenzukang@catt.cn) | Stage 3. Triggered by Rel-11 TR 36.828 Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation (FS_LTE_TDD_eIMTA) UID_510039 | LTE | 58 | 30 |  |  | Mon 03/09/12 | Mon 10/12/12
4099 | 580127 | Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Core | 2 | Rel-12 | R1,R2,R3,R4 | Fri 07/12/12 | Fri 13/06/14 | 100% | RP-121772 | RP-140724 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#64 completed | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423 | 58 | 30 |  |  | Mon 03/09/12 | Sun 06/07/14
4100 | 580227 | Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Perf | 2 | Rel-12 | R4 | Sat 15/12/12 | Tue 15/09/15 | 100% | RP-121772 | RP-151447 | CATT | Zukang Shen (shenzukang@catt.cn) | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141342->RP-141948 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141948->RP-150154 03/07/15: Compl:55%->95% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150 | 36.101, 36.104, 36.133, 36.141 | 58 | 30 |  |  | Mon 03/09/12 | Tue 29/09/15
4101 | 690072 | UE Conformance Test Aspects - Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-UEConTest | 2 | Rel-12 | R5 | Tue 15/09/15 | Thu 15/03/18 | 100% | RP-151398 |  | CATT |  | tested: REL-12 WI LTE_TDD_eIMTA-Core;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15% 21/3/ 19 827/3/ |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 27/03/18
4102 | 580029 | HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE | 1 | Rel-12 | R2,R4 | Fri 13/04/12 | Fri 12/09/14 | 100% | RP-122007 | - | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | Stage 3. Triggered by Rel-11 TR 36.839 Study on HetNet mobility enhancements for LTE (FS_HetNet_eMOB_LTE) | LTE | 58 | 30 |  |  | Mon 10/12/12 | Tue 09/09/14
4103 | 580129 | Core part: HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE-Core | 2 | Rel-12 | R2,R4 | Fri 13/04/12 | Fri 12/09/14 | 100% | RP-122007 | RP-141413 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | SP#65 completed | 36.133, 36.304, 36.331 | 58 | 30 |  |  | Mon 10/12/12 | Tue 09/09/14
4104 | 580030 | Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW | 1 | Rel-12 | R3 | Mon 10/12/12 | Fri 13/06/14 | 100% | RP-122006 | - | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11¦remaining work including solution definition is Rel-12 | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
4105 | 580130 | Core part: Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW-Core | 2 | Rel-12 | R3 | Mon 10/12/12 | Fri 13/06/14 | 100% | RP-122006 | RP-140592 | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | RP#64 completed | 36.300, 36.413, 36.423 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
4106 | 580031 | 8 Rx Antennas for LTE UL | LTE_UL_8Rx | 1 | Rel-12 | R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-121709 | - | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | WI has perf. part only (as change from 4Rx to 8Rx has no Core spec impact) | LTE | 58 | 30 |  |  | Mon 03/09/12 | Mon 10/12/12
4107 | 580231 | Perf. part: 8 Rx Antennas for LTE UL | LTE_UL_8Rx-Perf | 2 | Rel-12 | R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-121709 | RP-131523 | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | RP#62 completed | 36.104, 36.141 | 58 | 30 |  |  | Mon 03/09/12 | Fri 29/11/13
4108 | 600013 | LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD | 1 | Rel-12 | R1,R2,R4 | Fri 12/04/13 | Mon 15/12/14 | 100% | RP-140465 | - | Nokia | lars.e.lindh@nokia.com | - | LTE | 60 | 31 |  |  | Mon 17/06/13 | Thu 13/03/14
4109 | 600113 | Core part: LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD-Core | 2 | Rel-12 | R1,R2,R4 | Fri 12/04/13 | Fri 13/06/14 | 100% | RP-140465 | RP-140982 | Nokia, China Mobile (for TR) | lars.e.lindh@nokia.com, Xiaodong Shen (shenxiaodong@chinamobile.com) | RP#64 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.331, new 36.847 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
4110 | 600213 | Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD-Perf | 2 | Rel-12 | R4 | Sat 15/06/13 | Mon 15/12/14 | 100% | RP-140465 | RP-141972 | Nokia | lars.e.lindh@nokia.com | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141374->RP-141972 | 36.101, 36.104, 36.133 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
4111 | 600014 | LTE Coverage Enhancements | Cov_Enh_LTE | 1 | Rel-12 | R1,R2,R4,R5 | Fri 01/03/13 | Mon 15/06/15 | 100% | RP-130833 | - | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | Triggered by Rel-11 TR 36.824 (FS_Cov_Enh_LTE) | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
4112 | 600114 | Core part: LTE Coverage Enhancements | Cov_Enh_LTE-Core | 2 | Rel-12 | R1,R2,R4 | Fri 01/03/13 | Fri 13/06/14 | 100% | RP-130833 | RP-140683 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | RP#64 completed | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.321, 36.331 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
4113 | 600214 | Perf. part: LTE Coverage Enhancements | Cov_Enh_LTE-Perf | 2 | Rel-12 | R4 | Sat 15/06/13 | Mon 15/12/14 | 100% | RP-130833 | RP-141833 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141149->RP-141833 | 36.101, 36.104, 36.133, 36.141 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
4114 | 650012 | Test part: LTE Coverage Enhancements | Cov_Enh_LTE-UEConTest | 2 | Rel-12 | R5 | Mon 15/09/14 | Mon 15/06/15 | 100% | RP-141150 | RP-150631 | China Telecom | YANG Shan (yangshan@ctbri.com.cn) | ¦Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631 | 36.508, 36.523-1, 36.523-2, 36.523-3 | 65 | 33 |  |  | Tue 09/09/14 | Thu 18/06/15
4115 | 610024 | Further MBMS operations support for E-UTRAN | MBMS_LTE_OS | 1 | Rel-12 | R2,R1,R3,R4 | Sun 15/09/13 | Mon 15/12/14 | 100% | RP-140282 | - | Verizon | yeesin.chan@verizonwireless.com | Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS. | LTE | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
4116 | 610124 | Core part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Core | 2 | Rel-12 | R2,R1,R3,R4 | Sun 15/09/13 | Mon 15/12/14 | 100% | RP-140282 | RP-141821 | Verizon | yeesin.chan@verizonwireless.com | ¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821 | 36.133, 36.214, 36.300, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320 | 61 | 31 |  |  | Sat 07/09/13 | Mon 12/01/15
4117 | 620073 | Perf. part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-140282 | RP-141821 | Verizon | yeesin.chan@verizonwireless.com | ¦CD:Wed 17/12/14->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821 | 36.133 | 62 | 32 |  |  | Wed 18/12/13 | Mon 12/01/15
4118 | 620040 | Dual connectivity for LTE | LTE_SC_enh_dualC | 1 | Rel-12 | R2,R1,R3,R4,S2,C4 | Sun 15/12/13 | Fri 15/09/17 | 99% | RP-141266 | - | NTT DOCOMO | tooru.uchino.fv@nttdocomo.com | Triggered by TR 36.842 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects (UID_580044) | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 15/09/14
4119 | 620140 | Core part: Dual connectivity for LTE | LTE_SC_enh_dualC-Core | 2 | Rel-12 | R2,R1,R3,R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-141797 | RP-141796 | NTT DOCOMO, NEC | RAN1/2/4 tooru.uchino.fv@nttdocomo.com, RAN3 Chenghock Ng (ngcheng@da.jp.nec.com) | ¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141264->RP-141796 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.322, 36.323, 36.331, 36.410, 36.413, 36.420, 36.423, new RAN3 36.425 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
4120 | 620240 | Perf. part: Dual Connectivity for LTE | LTE_SC_enh_dualC-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/06/15 | 100% | RP-141797 | RP-150791 | NTT DOCOMO | kunihiko.teshima.hg@nttdocomo.com | ¦Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791 | 36.101, 36.104, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Thu 18/06/15
4121 | 631000 | SA2 part of Dual connectivity for LTE | LTE_SC_enh_dualC-S2 | 2 | Rel-12 | S2 | Wed 19/03/14 | Wed 17/09/14 | 100% | - | - | - | - | SP#64 Three CRs agreed in SP-140262 (23.251CR0099, 23.401CR2658&CR2707). Dec.14:99->100% | 23.251, 23.401 | 63 | 32 |  |  | Thu 19/06/14 | Wed 03/12/14
4122 | 650006 | CT aspects of Dual connectivity for LTE | LTE_SC_enh_dualC-CT | 2 | Rel-12 | C4 | Fri 12/09/14 | Tue 09/12/14 | 100% | CP-140493 | CP-140487 | Huawei | Xiaoyan SHI (sean.shixiaoyan@huawei.com) | Stage 2/3. CP#65 exception in CP-140487. LM70->100 | 23.007, 23.008, 29.274, 29.281 | 65 | 33 |  |  | Tue 29/07/14 | Thu 04/12/14
4123 | 680070 | UE Conformance Test Aspects - Dual connectivity for LTE | LTE_SC_enh_dualC-UEConTest | 2 | Rel-12 | R5 | Mon 15/06/15 | Fri 15/09/17 | 100% | RP-150840 |  | Ericsson |  | tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16¦ ; |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 19/09/17
4124 | 620041 | E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | Sun 15/12/13 | Thu 15/06/17 | 100% | RP-141459 | - | Huawei | Elean FAN (fanxiaoan@huawei.com) | Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041) | LTE | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4125 | 620141 | Core part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Core | 2 | Rel-12 | R1,R2,R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-141459 | RP-141899 | Huawei | Elean FAN (fanxiaoan@huawei.com) | ¦CD:Tue 12/05/15->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.413, 36.423, 36.443 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
4126 | 620241 | Perf. part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/06/15 | 100% | RP-141459 | RP-150690 | Huawei | Elean FAN (fanxiaoan@huawei.com) | ¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP- | 36.101, 36.104, 36.133, 36.141 | 62 | 32 |  |  | Mon 09/12/13 | Thu 18/06/15
4127 | 680068 | UE Conformance Test Aspects - E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-UEConTest | 2 | Rel-12 | R5 | Mon 15/06/15 | Thu 15/06/17 | 100% | RP-160414 |  | Huawei |  | tested Core part: LTE_SC_enh_L1-Core 29/09/15: Compl:0%->10% 29/09/15: CD:Wed 15/06/16->Thu 15/12/16 29/09/15: Stat Rep: -->RP-151247¦1/1/16: Compl:10%->40%¦ |  | 68 | 35 |  |  | Fri 03/07/15 | Mon 19/06/17
4128 | 620047 | Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB | 1 | Rel-12 | R3,R1 | Sun 15/12/13 | Fri 12/12/14 | 100% | RP-140983 | - | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation). | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
4129 | 620147 | Core part: Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB-Core | 2 | Rel-12 | R3,R1 | Sun 15/12/13 | Fri 12/12/14 | 100% | RP-140983 | RP-141804 | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-140597->RP-141804 | 36.300, 36.423 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
4130 | 630031 | Smart Congestion Mitigation in E-UTRAN | SCM_LTE | 1 | Rel-12 | R2,S1,C1 | Wed 05/03/14 | Tue 15/09/15 | 100% | RP-140434 | - | LG Electronics | youngdae.lee@lge.com | follow-up of TR 36.848 FS_SCM_LTE | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
4131 | 630131 | Core part: Smart Congestion Mitigation in E-UTRAN | SCM_LTE-Core | 2 | Rel-12 | R2 | Thu 06/03/14 | Fri 12/09/14 | 100% | RP-140434 | RP-141292 | LG Electronics | youngdae.lee@lge.com | RP#65 completed | 36.331 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
4132 | 640105 | Stage 1 Prioritization of Multimedia Telephony (MMTel) and Mobile Originating-SMS for Access Class Barring (ACB) | - | 2 | Rel-12 | S1 | Wed 05/03/14 | Fri 07/03/14 | 100% | CP-140286 | - | - | - | SP#63 SP-140065 CR under TEI12 | 22.011 | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
4133 | 640005 | CT aspects of Smart Congestion Mitigation in E-UTRAN (Stage 3) | SCM_LTE-CT | 2 | Rel-12 | C1 | Fri 13/06/14 | Thu 11/09/14 | 100% | CP-140286 | - | LG Electronics | Kim, Jaehyun (jaehyun7.kim@lge.com) | CP#65 completed | 24.173, 24.301, 24.341, 27.007 | 64 | 33 |  |  | Mon 07/04/14 | Mon 28/07/14
4134 | 670051 | UE Conformance Test Aspects - Smart Congestion Mitigation in E-UTRAN | SCM_LTE-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Tue 15/09/15 | 100% | RP-150797 | RP-151445 | NTT DOCOMO |  | 03/07/15: Compl:0%->60% 03/07/15: WID: RP-150202->RP-150797 03/07/15: Stat Rep: ->RP-150794 29/09/15: Compl:60%->100% 29/09/15: Stat Rep: RP-150794->RP-151445 |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
4135 | 630032 | Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT | 1 | Rel-12 | R3,R2 | Fri 25/04/14 | Fri 13/06/14 | 100% | RP-140177 | - | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | follow-up of TR 36.809 FS_LCS_LTE_RFPMT | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
4136 | 630132 | Core part: Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT-Core | 2 | Rel-12 | R3,R2 | Fri 25/04/14 | Fri 13/06/14 | 100% | RP-140177 | RP-140591 | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | RP#64 completed | 36.305, 36.455 | 63 | 32 |  |  | Mon 10/03/14 | Thu 12/06/14
4137 | 630046 | Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS | 1 | Rel-12 | R1,R2,R4,R3 | Tue 11/03/14 | Wed 15/03/17 | 100% | RP-141634 | - | MediaTek | Craig.Burnet@mediatek.com | follow-up of TR 36.866 FS_LTE_NAICS | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
4138 | 630146 | Core part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Core | 2 | Rel-12 | R1,R2,R4,R3 | Fri 11/07/14 | Mon 15/12/14 | 100% | RP-141634 | RP-141866 | MediaTek | Craig.Burnet@mediatek.com | CD:Mon 08/12/14->Mon 15/12/14¦Compl:95%->100%¦Stat Rep: RP-141621->RP-141866 | 36.211, 36.213, 36.300, 36.331, 36.423 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
4139 | 630246 | Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Perf | 2 | Rel-12 | R4 | Tue 11/03/14 | Tue 15/09/15 | 100% | RP-151297 | RP-151296 | MediaTek | Craig.Burnet@mediatek.com | CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->25%¦Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862 | 36.101 | 63 | 32 |  |  | Mon 10/03/14 | Tue 29/09/15
4140 | 690070 | UE Conformance Test Aspects: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-UEConTest | 2 | Rel-12 | R5 | Tue 15/09/15 | Wed 15/03/17 | 100% | RP-160265 |  | Mediatek |  | tested: LTE_NAICS was a REL-12 RAN1 WI¦1/1/16: Compl:0%->35%¦1/1/16: WID: RP-151298->RP-151945¦ |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
4141 | 630047 | Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX | 1 | Rel-12 | R4 | Thu 06/03/14 | Tue 15/12/15 | 100% | RP-140520 | - | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | no Core part | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
4142 | 630147 | Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX-Perf | 2 | Rel-12 | R4 | Thu 06/03/14 | Fri 13/03/15 | 100% | RP-140520 | RP-150229 | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | CD:Fri 13/03/15->Sun 15/03/15¦Compl:50%->80%¦Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229 | 36.101 | 63 | 32 |  |  | Mon 10/03/14 | Wed 01/04/15
4143 | 670052 | UE Conformance Test Aspects - Performance Requirements of Interference Cancellation and Suppression Receiver for SU-MIMO for E-UTRA | LTE_SUMIMO_RX-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Tue 15/12/15 | 100% | RP-151819 | RP-151245 | Huawei |  | 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: ->RP-150692 29/09/15: Compl:5%->55% 29/09/15: WID: RP-150245->RP-151463 29/09/15: Stat Rep: RP-150692->RP-1512451/1/16: Compl:55%->100%1/1/16: CD:Tue 15/03/16->Tue 15/1 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
4144 | 580028 | HSPA signalling enhancements for more efficient resource usage for LCR | LCR_TDD_HSPA_sign_enh | 1 | Rel-12 | R1,R2,R3,R4 | Tue 11/12/12 | Fri 20/12/13 | 100% | RP-121984 | - | CATT | Yanping Xing (xingyanping@catt.cn) | Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026 | UTRA | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
4145 | 580128 | Core part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Core | 2 | Rel-12 | R1,R2,R3 | Sat 15/12/12 | Fri 20/12/13 | 100% | RP-121984 | RP-131499 | CATT | Yanping Xing (xingyanping@catt.cn) | Prev CD:Fri 06/12/13¦Prev %:100% | 25.222, 25.224, 25.331, 25.423, 25.433 | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/12/14
4146 | 580228 | Perf. part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Perf | 2 | Rel-12 | R4 | Tue 11/12/12 | Fri 06/09/13 | 100% | RP-121984 | RP-130968 | CATT | Yanping Xing (xingyanping@catt.cn) | RP#61 completed | 25.102 | 58 | 30 |  |  | Mon 10/12/12 | Fri 30/08/13
4147 | 600017 | HNB Positioning for UTRA | UTRA_HNB_Pos | 1 | Rel-12 | R3 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-132037 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | UTRA | 60 | 31 |  |  | Mon 17/06/13 | Mon 09/12/13
4148 | 600117 | Core part: HNB Positioning for UTRA | UTRA_HNB_Pos-Core | 2 | Rel-12 | R3 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-132037 | RP-131974 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID) | 25.305, 25.467, new 25.470 | 60 | 31 |  |  | Mon 17/06/13 | Mon 09/12/13
4149 | 610025 | Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh | 1 | Rel-12 | R1,R2,R3,R4 | Sun 15/09/13 | Wed 15/06/16 | 100% | RP-140771 | - | Qualcomm | arjunb@qti.qualcomm.com | Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3 | UTRA | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
4150 | 610125 | Core part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Core | 2 | Rel-12 | R1,R2,R3,R4 | Mon 18/11/13 | Fri 12/09/14 | 100% | RP-140771 | RP-141137 | Qualcomm | arjunb@qti.qualcomm.com | RP#65 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
4151 | 610225 | Perf. part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Perf | 2 | Rel-12 | R4 | Sun 15/09/13 | Mon 15/12/14 | 100% | RP-140771 | RP-141970 | Qualcomm | arjunb@qti.qualcomm.com | ¦Stat Rep: RP-141137->RP-141970 | 25.101, 25.104, 25.133 | 61 | 31 |  |  | Sat 07/09/13 | Mon 12/01/15
4152 | 670053 | UE Conformance Test Aspects - DCH Enhancements for UMTS | UTRA_DCHenh-UEConTest | 2 | Rel-12 | R5 | Mon 16/03/15 | Wed 15/06/16 | 100% | RP-160384 | RP-151279 | Qualcomm | NA | 03/07/15: Compl:0%->15% 03/07/15: Stat Rep: ->RP-150764 29/09/15: Compl:15%->50% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150764->RP-1512791/1/16: Compl:50%->65%; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
4153 | 610026 | UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob | 1 | Rel-12 | R2,R3,R4 | Tue 23/07/13 | Fri 13/06/14 | 100% | RP-132039 | - | Huawei | Xudong Yang (yangxudong@huawei.com) | Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3 | UTRA | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
4154 | 610126 | Core part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Core | 2 | Rel-12 | R2,R3,R4 | Tue 23/07/13 | Fri 13/06/14 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed. TS 25.300v100 for 1-step Approval | 25.101, 25.104, 25.133, 25.141, 25.304, 25.306, 25.331, 25.433, new 25.300 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
4155 | 610226 | Perf. part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Perf | 2 | Rel-12 | R4 | Mon 09/09/13 | Fri 13/06/14 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed | 25.101, 25.104, 25.133, 25.141 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
4156 | 620054 | UMTS Heterogeneous Networks enhancements | UTRA_HetNet_enh | 1 | Rel-12 | R1,R2,R3,R4 | Fri 06/12/13 | Mon 15/12/14 | 100% | RP-141701 | - | Huawei | carmela.cozzo@huawei.com | Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet)¦the 1st part is addressed by UTRA_HetNet_mob UID_610026 | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4157 | 620154 | Core part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Core | 2 | Rel-12 | R1 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-141701 | RP-141702 | Huawei | carmela.cozzo@huawei.com | RP#65 completed. Updated WID RP-140463=>RP-141701 | 25.101, 25.211, 25.212, 25.213, 25.214, 25.300, 25.302, 25.306, 25.308, 25.319, 25.331, 25.423, 25.433 | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4158 | 620254 | Perf. part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-141701 | RP-141898 | Huawei | carmela.cozzo@huawei.com | ¦Stat Rep: RP-141702->RP-141898 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
4159 | 620055 | Enhanced Broadcast of System Information | UTRA_SIBenh | 1 | Rel-12 | R2,R1,R3,R4 | Fri 06/12/13 | Mon 15/12/14 | 100% | RP-140131 | - | Ericsson | martin.van.der.zee@ericsson.com | Triggered by Rel-12 UTRA TR 25.704 Study on Enhanced Broadcast of System Information (FS_UTRA_SIBenh) | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4160 | 620155 | Core part: Enhanced Broadcast of System Information | UTRA_SIBenh-Core | 2 | Rel-12 | R2,R1,R3,R4 | Fri 06/12/13 | Fri 12/09/14 | 100% | RP-140131 | RP-141230 | Ericsson | martin.van.der.zee@ericsson.com | RP#65 completed | 25.211, 25.212 , 25.213, 25.214, 25.301, 25.302, 25.304, 25.306, 25.321, 25.331, 25.433 | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4161 | 620255 | Perf. part: Enhanced Broadcast of System Information | UTRA_SIBenh-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-140131 | RP-142080 | Ericsson | martin.van.der.zee@ericsson.com | ¦Stat Rep: RP-141230->RP-142080 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
4162 | 620049 | Further Enhanced Uplink (EUL) enhancements | EDCH_enh | 1 | Rel-12 | R2 | Sun 15/12/13 | Fri 13/03/15 | 100% | RP-140127 | - | Ericsson | mark.curran@ericsson.com | Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh) | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
4163 | 620149 | Core part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Core | 2 | Rel-12 | R2,R1,R3,R4 | Sun 15/12/13 | Mon 15/12/14 | 100% | RP-140127 | RP-141860 | Ericsson | mark.curran@ericsson.com | ¦Stat Rep: RP-141684->RP-141860 | 25.211, 25.212, 25.214, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.425, 25.433, 25.435 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
4164 | 620249 | Perf. part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Perf | 2 | Rel-12 | R4 | Sun 15/12/13 | Fri 13/03/15 | 100% | RP-140127 | RP-150062 | Ericsson | mark.curran@ericsson.com | ¦CD:Wed 18/03/15->Sun 15/03/15¦Stat Rep: RP-141684->RP-141860 1st Apr 15: Compl:75%->100% 1st Apr 15: Stat Rep: RP-141860->RP-150062 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Wed 01/04/15
4165 | 560018 | (Small) Technical Enhancements and Improvements for Rel-12 | TEI12 | 1 | Rel-12 | SP,CP,RP,GP | Tue 25/12/12 | Tue 16/09/14 | 100% | - | - | - | - | - | - | 56 | 29 |  |  | Fri 13/07/12 | Fri 06/12/13
4166 | 660032 | (IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id) | TEI12_IETF | 1 | Rel-12 | C1-IETF | Fri 13/06/14 | Tue 09/12/14 | 100% | CP-140815 |  | Alcatel-Lucent |  | Mar15: In WGLC¦21/3/17: 50%->100; 9/4/21: RFC 7989 added; | draft-ietf-insipid-session-id; RFC 7989 | 66 | 34 |  |  | Thu 04/12/14 | Fri 09/04/21
4167 | 610001 | Test - (Small) Technical Enhancements and Improvements for Rel-12 | TEI12_Test | 1 | Rel-12 | R5,G3new | Fri 24/10/14 | Fri 11/12/15 | 100% | - | - | - | - | - | - | 61 | 31 |  |  | Mon 29/07/13 | Mon 29/07/13
4168 | 0 | Release 12 Studies | - | 1 | Rel-12 | SP,CP,GP,RP | Mon 05/08/13 | Tue 16/09/14 | 80% | - | - | - | - | - | - | - | - |  |  | Thu 08/09/11 | Thu 15/09/11
4169 | 470020 | Study on Alternatives to E.164 for Machine-Type Communications | FS_AMTC | 1 | Rel-12 | S1 | Thu 25/03/10 | Wed 07/03/12 | 100% | SP-100198 | - | T-Mobile USA | gary.jones@T-Mobile.com | SP#55 completed. Determine an alternative to E.164 for identifying individual devices and route messages between those devices | 22.988 | 47 | 24 |  |  | Tue 23/03/10 | Wed 22/02/12
4170 | 480032 | Study on enhancements for Machine-Type Communications (MTC) | FS_MTCe | 1 | Rel-12 | S1 | Thu 10/06/10 | Wed 06/03/13 | 100% | SP-100448 | - | Huawei | laurence.meriau@huawei.com | SP#59 completed. TR 22.888 v100 for Information & Approval. Study addition of new MTC-related use cases and functionality and improvements to existing requirements in TS 22.368 | 22.888 | 48 | 25 |  |  | Fri 28/05/10 | Tue 19/02/13
4171 | 490035 | Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int | 1 | Rel-12 | S1 | Thu 23/09/10 | Wed 07/03/12 | 100% | SP-100640 | - | InterDigital | christopher.wallace@interdigital.com | SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec) | 22.895 | 49 | 25 |  |  | Tue 31/08/10 | Wed 22/02/12
4172 | 500035 | Study on Continuity of Data Sessions to Local Networks | FS_CSN | 1 | Rel-12 | S1 | Thu 16/12/10 | Wed 14/12/11 | 100% | SP-100885 | - | NEC | joerg.swetina@neclab.eu | SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC) | 22.896 | 50 | 26 |  |  | Thu 25/11/10 | Tue 29/11/11
4173 | 500036 | Study on non-MTC Mobile Data Applications Impacts | FS_MODAI | 1 | Rel-12 | S1 | Thu 16/12/10 | Wed 14/12/11 | 100% | SP-100889 | - | Huawei, China Mobile | Amar Deol (adeol@huawei.com), Gang Li | SP#54 completed. Linked to UID_490036 SA2 Rel-11 TR 23.843 Study on Core Network Overload solutions (FS_CNO) | 22.801 | 50 | 26 |  |  | Thu 25/11/10 | Tue 29/11/11
4174 | 530044 | Study on Proximity-based Services | FS_ProSe | 1 | Rel-12 | S1 | Thu 22/09/11 | Tue 05/03/13 | 100% | SP-110638 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#59 completed | 22.803 | 53 | 27 |  |  | Thu 08/09/11 | Tue 19/02/13
4175 | 540027 | Study on User Plane Congestion management | FS_UPCON | 1 | Rel-12 | S1 | Wed 14/12/11 | Wed 12/09/12 | 100% | SP-110819 | - | KDDI | John Visser (jvisser@rogers.com) | SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits) | 22.805 | 54 | 28 |  |  | Tue 29/11/11 | Tue 07/08/12
4176 | 540028 | Study on RAN Sharing Enhancements | FS_RSE | 1 | Rel-12 | S1 | Wed 14/12/11 | Wed 19/06/13 | 100% | SP-110820 | - | NEC | joerg.swetina@neclab.eu | SP#60 completed. Extend Rel-6 Network Sharing UID_31018 (basic scenarios of network/RAN sharing) to cover more complex scenarios that arise due to recent needs for more dynamic co-operation among operators | 22.852 | 54 | 28 |  |  | Tue 29/11/11 | Tue 18/06/13
4177 | 460025 | Deleted - Study on UICC/USIM enhancements | FS_U2e | 1 | Rel-12 | S1 | Thu 10/12/09 | Wed 07/03/12 | 100% | SP-090903 | - | Giesecke & Devrient | ilario.macchi@gi-de.com | SP#55 work stopped. Triggered by GSMA Smart SIM and 3GNBK projects, and to evolve from traditional USAT to multimedia USIM toolkit support, particularly to Smart Card Web Server | 22.817 | 46 | 24 | SP-55 | PCG-28 | Sun 06/12/09 | Sun 04/03/12
4178 | 490034 | Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 1 | Rel-12 | S2,S1,S3 | Thu 23/09/10 | Wed 12/12/12 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | Triggered by TR 22.906 SA1 Study on IMS based Peer-to-Peer Content Distribution Services UID_450047 | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Thu 22/11/12
4179 | 490134 | SA1 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#53 completed | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Fri 08/06/12
4180 | 490234 | SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S2 | Thu 23/09/10 | Wed 20/06/12 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#56 completed. TR 23.844v100 for Information and Approval | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Thu 14/06/12
4181 | 570036 | SA3 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S3 | Wed 12/09/12 | Wed 12/12/12 | 100% | SP-120622 | - | China Mobile | Zhu Judy(zhuhongru@chinamobile.com) | SP#58 completed. TR 33.844 v100 for Information and Approval | 33.844 | 57 | 29 |  |  | Tue 11/09/12 | Fri 02/11/12
4182 | 490036 | Study on Core Network Overload solutions | FS_CNO | 1 | Rel-12 | S2 | Thu 23/09/10 | Wed 11/12/13 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014) | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 28/11/13
4183 | 490136 | Study on Core Network Overload solutions (Phase 1) | FS_CNO | 2 | Rel-12 | S2 | Thu 23/09/10 | Wed 12/12/12 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | Phase 1: complete study of overload control related to MAP /Diameter signalling, other 3GPP Core Network signalling optimization | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 30/08/12
4184 | 490236 | Study on Core Network Overload solutions (Phase 2) | FS_CNO | 2 | Rel-12 | S2 | Thu 23/09/10 | Wed 11/12/13 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 28/11/13
4185 | 500037 | Study on System Enhancements for Energy Efficiency | FS_SEEE | 1 | Rel-12 | S2 | Thu 16/12/10 | Wed 20/06/12 | 100% | SP-100888 | - | Huawei | frank.mademann@huawei.com | SP#56 completed | 23.866 | 50 | 26 |  |  | Thu 25/11/10 | Tue 19/06/12
4186 | 510061 | Study on S2a Mobility based On GTP and WLAN access to EPC | FS_SaMOG | 1 | Rel-12 | S2 | Wed 23/03/11 | Wed 11/09/13 | 100% | SP-120426 | - | ZTE | Tricci So (tso@zteusa.com) | SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI | 23.852 | 51 | 26 |  |  | Mon 21/02/11 | Thu 25/07/13
4187 | 560037 | Study on Optimized Offloading to WLAN in 3GPP-RAT Mobility | FS_WORM | 1 | Rel-12 | S2 | Mon 18/06/12 | Wed 11/09/13 | 100% | SP-120261 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#61 completed. Linked to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP), UID_410043 MAPIM, UID_450041 IFOM, UID_530046 SaMOG | 23.89 | 56 | 29 |  |  | Fri 11/05/12 | Thu 25/07/13
4188 | 560038 | Study on Application Based Charging | FS_ABC | 1 | Rel-12 | S2 | Mon 18/06/12 | Wed 06/03/13 | 100% | SP-120271 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#59 completed. Linked to Rel-11 Feature UID_500032 Service Awareness and Privacy Policies (SAPP) | 23.8 | 56 | 29 |  |  | Mon 04/06/12 | Wed 27/02/13
4189 | 410043 | Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 1 | Rel-12 | S2,S1 | Fri 08/08/08 | Wed 12/12/12 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM) | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
4190 | 410143 | SA1 part of Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 2 | Rel-12 | S1 | Fri 08/08/08 | Wed 21/09/11 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#53 completed | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
4191 | 410243 | SA2 part of Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 2 | Rel-12 | S2 | Thu 18/09/08 | Wed 12/12/12 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#43 TR 23.861v100 for Information. SP#56 Rel-9 TR 23.861v130 renamed & progressed under new Study FS_NBIFOM. SP#58 completed the FS_MAPIM part of TR 23.861 (TR continued under FS_NBIFOM). | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
4192 | 560039 | Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces | FS_NBIFOM | 1 | Rel-12 | S2 | Mon 18/06/12 | Wed 06/03/13 | 100% | SP-120742 | - | ZTE | Tricci So (tso@zteusa.com) | SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility) | 23.861 | 56 | 29 | SP-59 | PCG-30 | Mon 04/06/12 | Wed 27/02/13
4193 | 480043 | Study on Extended IMS Media Plane Security features | FS_eMEDIASEC | 1 | Rel-12 | S3 | Thu 10/06/10 | Wed 06/03/13 | 100% | SP-100256 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#59 completed. Continuation of Rel-9 Feature UID_430036 IMS Media Plane Security (MEDIASEC). Study solutions and extensions to features and functionality described in TR 33.828 and TS 33.328 | 33.829 | 48 | 25 |  |  | Wed 05/05/10 | Tue 19/02/13
4194 | 530047 | Deleted - Study on Firewall traversal (Stage 2) | FS_Fire | 1 | Rel-12 | S3 | Fri 17/06/11 | Wed 17/09/14 | 100% | SP-120849 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#65 stopped. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043 | 33.83 | 53 | 27 | SP-65 | PCG-33 | Tue 19/07/11 | Wed 21/05/14
4195 | 550026 | Study on Security on spoofed call detection and prevention (Stage 2) | FS_SPOOF | 1 | Rel-12 | S3 | Wed 07/03/12 | Wed 17/09/14 | 100% | SP-120030 | - | China Mobile | lixiangjun@chinamobile.com | SP#65 completed. TR 33.831v100 for 1-step Approval. Linked to Rel-11 SPUCI TR 33.838 | 33.831 | 55 | 28 |  |  | Mon 20/02/12 | Wed 03/09/14
4196 | 570035 | Study on Security Assurance Methodology for 3GPP Network Elements | FS_SECAM | 1 | Rel-12 | S3 | Thu 13/09/12 | Wed 18/06/14 | 100% | SP-120654 | - | Orange | loic.habermacher@orange.com | SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible) | 33.805 | 57 | 29 |  |  | Fri 31/08/12 | Wed 21/05/14
4197 | 540033 | Study on Improved Support for Dynamic Adaptive Streaming over HTTP in 3GPP | FS_IS_DASH | 1 | Rel-12 | S4 | Wed 14/12/11 | Tue 16/09/14 | 100% | SP-140486 | - | Qualcomm | c_tstock@qualcomm.com | SP#65 completed. TR 26.938v200 for Approval. SP#60 TR 26.938v100 for Information. Linked to Feature UID_470034 HTTP-based Streaming and Download Services | 26.938 | 54 | 28 |  |  | Wed 14/12/11 | Fri 05/09/14
4198 | 610044 | Study on HTML5 for a new presentation layer in 3GPP services | FS_HTML5 | 1 | Rel-12 | S4 | Thu 12/09/13 | Tue 16/09/14 | 100% | SP-130357 | - | Samsung | Imed Bouazizi (i.bouazizi@sta.samsung.com) | SP#65 completed. TR 26.907v200 for Approval. SP#64 TR 26.907v100 for Information. | 26.907 | 61 | 31 |  |  | Mon 09/09/13 | Fri 05/09/14
4199 | 470050 | Study on version handling | FS_OAM_VH | 1 | Rel-12 | S5 | Thu 25/03/10 | Wed 12/12/12 | 100% | SP-100082 | - | Ericsson | thomas.tovinger@ericsson.com | SP#58 completed | 32.83 | 47 | 24 |  |  | Fri 12/02/10 | Wed 21/11/12
4200 | 510046 | Study on management of Heterogeneous Networks | FS_OAM_HetNet | 1 | Rel-12 | S5 | Wed 23/03/11 | Wed 18/06/14 | 100% | SP-130046 | - | Ericsson | ulf.hubinette@ericsson.com | SP#64 completed | 32.835 | 51 | 26 |  |  | Sat 02/06/12 | Tue 27/05/14
4201 | 540032 | Study on OAM aspects of Network Sharing | FS_OAM_SHARE | 1 | Rel-12 | S5 | Wed 07/12/11 | Wed 11/09/13 | 100% | SP-130044 | - | Alcatel-Lucent, Huawei | Padma.Sudarsan@alcatel-lucent.com, zoulan@huawei.com | SP#61 completed. Linked to Network Sharing UID_31018, SA1 22.951 (Service aspects and requirements for network sharing), SA2 23.251 (Network Sharing¦Architecture) | 32.851 | 54 | 28 |  |  | Sat 02/06/12 | Wed 04/09/13
4202 | 560032 | Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | FS_SON_NM_CCO | 1 | Rel-12 | S5 | Wed 21/09/11 | Wed 17/09/14 | 100% | SP-140028 | - | Ericsson | robert.petersen@ericsson.com | SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060) | 32.836 | 56 | 29 |  |  | Wed 18/04/12 | Mon 25/08/14
4203 | 560336 | Study on WLAN management | FS_WLAN_OAM | 1 | Rel-12 | S5 | Wed 21/09/11 | Wed 17/09/14 | 100% | SP-150408 | - | Intel | joey.chou@intel.com | SP#65 revised WID SP-130042=>SP-140536 (split into Rel-12 Study & Rel-13 normative WI). Changed Title from "TR on WLAN impacts to Type-2 management interface to the 3GPP Network Manager". TR 32.841v200 for Approval. Completed¦14/09/15: WID:SP-140536-> | 28.680, 28.681, 28.682, 28.683, 28.403 | 56 | 29 |  |  | Tue 12/06/12 | Mon 14/09/15
4204 | 580052 | Study on Alarm Management | FS_OAM_AM | 1 | Rel-12 | S5 | Fri 07/12/12 | Wed 11/09/13 | 100% | SP-120774 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#61 completed | 32.859 | 58 | 30 |  |  | Wed 21/11/12 | Wed 04/09/13
4205 | 580025 | Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests | FS_NNI_RS | 1 | Rel-12 | C3 | Mon 10/12/12 | Fri 13/06/14 | 100% | CP-130166 | - | Ericsson | Jan.Holm@ericsson.com | CP#64 completed | 24.802 | 58 | 30 |  |  | Tue 20/11/12 | Wed 18/06/14
4206 | 580026 | Study on Diameter Overload Control Mechanisms | FS_DOCME | 1 | Rel-12 | C4 | Thu 05/01/12 | Thu 11/09/14 | 100% | CP-120917 | - | Orange | lionel.morand@orange.com | CP#65 completed. TR 29.809 v200 for Approval. Triggered by SA2 Rel-12 TR 23.843 Study on Core Network Overload solutions (FS_CNO) UID_490036. Coordinate with CT3, SA5 | 29.809 | 58 | 30 |  |  | Tue 20/11/12 | Mon 28/07/14
4207 | 590011 | Study on XML based access of AF to the PCRF | FS_XML_AF_PCRF | 1 | Rel-12 | C3 | Fri 01/03/13 | Wed 04/12/13 | 100% | CP-130167 | - | Alcatel-Lucent | horst.brinkman@alcatel-lucent.com | CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications | 29.817 | 59 | 30 |  |  | Sat 16/02/13 | Thu 19/06/14
4208 | 610010 | Study on Technical aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks | FS_REVOLTE_IMS | 1 | Rel-12 | C3 | Mon 09/09/13 | Tue 09/12/14 | 100% | CP-130774 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completion 09/14=>12/14. CP#64 TR 29.949v100 for Information.Dec.14:95->100 | 29.949 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
4209 | 620001 | Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME | FS_ISIM_CR | 1 | Rel-12 | C6 | Mon 09/12/13 | Tue 09/12/14 | 100% | CP-130812 | - | Gemalto | ly-thanh.phan@gemalto.com | CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage¦June2015: Compl:30%->100 | 31.829 | 62 | 32 |  |  | Fri 22/11/13 | Mon 15/06/15
4210 | 620002 | Study on Shared Data Update for Multiple Subscribers | FS_SHARED_SubData_UPD | 1 | Rel-12 | C4 | Fri 06/12/13 | Tue 09/12/14 | 100% | CP-130809 | - | Huawei | Susan Shi (susan.shishufeng@huawei.com) | CP#65 TR 29.854v200 for Approval. Completion 09/14=>12/14. Dec.14: 80->85%. Mar.15: 100% | 29.854 | 62 | 32 |  |  | Tue 19/11/13 | Wed 04/03/15
4211 | 460001 | Study on GERAN improvements for Machine-Type Communications | FS_NIMTC_GERAN | 1 | Rel-12 | G1,G2 | Mon 24/05/10 | Fri 23/11/12 | 100% | GP-092418 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#56 completed. GP#44 approved WID | 43.868 | 44 | 24 |  |  | Fri 20/11/09 | Fri 23/11/12
4212 | 520001 | Study on Voice services over Adaptive Multi-user channels on One Slot (VAMOS) enhancements | FS_eVAMOS | 1 | Rel-12 | GP,G2,G1 | Wed 27/10/10 | Fri 30/05/14 | 100% | GP-110991 | - | China Mobile, Huawei | Chao Luo (chluo@huawei.com), dengjuan@chinamobile.com | GP#62 completed. TR 43.801v100 for 1-step Approval. GP#50 approved WID. Triggered by Rel-8 TR 45.914 Study Multi-User-Reusing One Timeslot (MUROS) UID_50590 and Rel-9 VAMOS UID_420002 | 43.801 | 50 | 27 |  |  | Sat 21/05/11 | Fri 30/05/14
4213 | 520002 | Study on GERAN enhancements for Mobile Data Applications | FS_GERAN_eMDA | 1 | Rel-12 | G2,G1 | Mon 04/04/11 | Fri 29/08/14 | 100% | GP-110999 | - | Huawei | ming.fang@huawei.com | GP#63 completed. TR 43.802v200 for Approval. GP#50 approved WID (mobile coucou). Triggered by RAN#51 (Mar 2011) WID in RP-110454 (LTE RAN Enhancements for Diverse Data Applications) UID_510031 | 43.802 | 50 | 27 |  |  | Sat 21/05/11 | Fri 29/08/14
4214 | 500016 | Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN | FS_LCS_LTE_RFPMT | 1 | Rel-12 | R4 | Fri 10/12/10 | Fri 06/09/13 | 100% | RP-120885 | RP-131082 | Polaris Wireless | Scot Gordon (sgordon@polariswireless.com) | RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005 | LTE 36.809 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/08/13
4215 | 530052 | Study on Provision of low-cost MTC UEs based on LTE | FS_LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | Mon 19/09/11 | Fri 14/06/13 | 100% | RP-121441 | RP-130583 | Vodafone | prakash.bhat@vodafone.com | RP#60 completed | LTE 36.888 | 53 | 27 |  |  | Mon 19/09/11 | Fri 07/06/13
4216 | 530054 | Deleted - Study on Mobile Relay for E-UTRA | FS_LTE_mobRelay | 1 | Rel-12 | R3,R1 | Thu 19/05/05 | Mon 23/06/14 | 100% | RP-131375 | RP-140726 | CATT | Haijing Hu (huhaijing@catt.cn) | RP#64 stopped at 80% completion | LTE 36.836 | 53 | 27 | RP-64 | PCG-33 | Mon 19/09/11 | Mon 23/06/14
4217 | 570023 | Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN | FS_LTE_SC_enh_req | 1 | Rel-12 | RP | Tue 11/09/12 | Fri 07/12/12 | 100% | RP-121418 | RP-121651 | China Mobile | Hai TANG (tanghai@chinamobile.com) | RP#58 completed. TR 36.932 v100 for Information and Approval | LTE 36.932 | 57 | 29 |  |  | Mon 03/09/12 | Thu 06/12/12
4218 | 580041 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects | FS_LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | Tue 11/09/12 | Fri 06/09/13 | 100% | RP-122032 | RP-131618 | Huawei | Elean Fan (fanxiaoan@huawei.com) | RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.872 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
4219 | 580044 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects | FS_LTE_SC_enh_hilayer | 1 | Rel-12 | R2,R3 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-122033 | RP-131619 | NTT DOCOMO | Hideaki Takahashi (h-takahashi@nttdocomo.co.jp) | RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.842 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
4220 | 580038 | Study on LTE Device-to-Device Proximity Services - Radio Aspects | FS_LTE_D2D_Prox | 1 | Rel-12 | R1,R2,R3,R4 | Mon 17/12/12 | Thu 06/03/14 | 100% | RP-122009 | RP-140416 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | RP#63 completed. TR 36.843 for 1-step approval (90% complete). Started normative work. Linked to Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) and Feature ProSe | LTE 36.843 | 58 | 30 |  |  | Mon 10/12/12 | Fri 14/03/14
4221 | 580042 | Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE | FS_LTE_3D_channel | 1 | Rel-12 | R1 | Mon 10/12/12 | Fri 12/09/14 | 100% | RP-141237 | RP-141206 | Nokia Networks | bishwarup.mondal@nsn.com | RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network | LTE 36.873 | 58 | 30 |  |  | Mon 10/12/12 | Sun 21/09/14
4222 | 580046 | Study on Energy Saving Enhancement for E-UTRAN | FS_Netw_Energy_enh_LTE | 1 | Rel-12 | R3 | Mon 10/12/12 | Fri 13/06/14 | 100% | RP-122035 | RP-140604 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | RP#64 completed. Identify potential solutions for energy saving in E-UTRAN non-overlapping scenario. Evaluate possible enhancements in overlapping scenario, so that a subset can be used for further investigation/standardization | LTE 36.887 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
4223 | 590016 | Study on Expansion of LTE_FDD_1670_US to include 1670-1680MHz Band for LTE in the US | FS_LTE_FDD_1670_US | 1 | Rel-13 | R4 | Fri 01/03/13 | Mon 15/12/14 | 100% | RP-130202 | RP-141815 | LightSquared | masoud.olfat@lightsquared.com | CD:Thu 11/12/14->Mon 15/12/14¦Compl:80%->100%¦Stat Rep: RP-141453->RP-141815 | LTE 36.844 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
4224 | 590017 | Study on Cell-specific Reference Signals (CRS) Interference Mitigation for homogenous deployments for LTE | FS_LTE_CRSIC | 1 | Rel-12 | R4 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-131840 | RP-131623 | Ericsson | shaohua.li@ericsson.com | RP#62 completed. Updated WID RP-130393=>RP-131840 | LTE 36.863 | 59 | 30 |  |  | Tue 26/02/13 | Thu 19/12/13
4225 | 590018 | Study on Network-Assisted Interference Cancellation and Suppression for LTE | FS_LTE_NAICS | 1 | Rel-12 | R1,R4 | Fri 08/03/13 | Thu 06/03/14 | 100% | RP-130404 | RP-132108 | MediaTek | jeff.zhuang@mediatek.com | RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work | LTE 36.866 | 59 | 30 |  |  | Tue 26/02/13 | Fri 14/03/14
4226 | 600015 | Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul | FS_COMP_LTE_nibackhaul | 1 | Rel-12 | R1 | Tue 18/06/13 | Fri 06/12/13 | 100% | RP-130847 | RP-131626 | Samsung | Hyojin Lee (hyojin257.lee@samsung.com) | RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332) | LTE 36.874 | 60 | 31 |  |  | Mon 17/06/13 | Tue 03/12/13
4227 | 610028 | Study on Group Communication for LTE | FS_LTE_GC | 1 | Rel-12 | R2,R3 | Tue 10/09/13 | Thu 06/03/14 | 100% | RP-131382 | RP-140182 | Alcatel-Lucent | chandrika.worrall@alcatel-lucent.com | RP#63 completed. Evaluate ability of LTE to meet public safety requirements agreed in SA for GC (GC is a key functionality of Land Mobile Radio/Private Mobile Radio and public safety systems) | LTE 36.868 | 61 | 31 |  |  | Sat 07/09/13 | Fri 14/03/14
4228 | 610029 | Study on Smart Congestion Mitigation in E-UTRAN | FS_SCM_LTE | 1 | Rel-12 | R2 | Mon 09/09/13 | Thu 06/03/14 | 100% | RP-132092 | RP-140102 | LG Electronics | youngdae.lee@lge.com | RP#63 completed | LTE 36.848 | 61 | 31 |  |  | Sat 07/09/13 | Fri 14/03/14
4229 | 620044 | Study on RAN aspects of RAN Sharing Enhancements for LTE | FS_RSE-RAN_LTE | 1 | Rel-12 | R3 | Fri 06/12/13 | Fri 13/06/14 | 100% | RP-132116 | RP-140746 | NEC | Siva.Vakeesar@emea.nec.com | RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1) | LTE 36.856 | 62 | 32 |  |  | Wed 27/11/13 | Thu 12/06/14
4230 | 530056 | Study on RF and EMC requirements for active Antenna Array System (AAS) Base Station | FS_AAS_BS_LTE_UTRA | 1 | Rel-12 | R4,R1 | Mon 19/09/11 | Fri 01/03/13 | 100% | RP-111349 | RP-130124 | Huawei | Ronnie.zhang@huawei.com | RP#59 completed | UTRA, LTE 37.840 | 53 | 27 |  |  | Mon 19/09/11 | Thu 28/02/13
4231 | 550020 | Study on LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | FS_LTE_HRPD_SON | 1 | Rel-12 | R3 | Fri 02/03/12 | Fri 14/06/13 | 100% | RP-121982 | RP-130585 | China Telecom | Wu Jinlian (wujl@gsta.com) | RP#60 completed | UTRA, LTE 37.813 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/06/13
4232 | 550021 | Study on Passive InterModulation (PIM) handling for UTRA and LTE Base Stations | FS_BS_PIM | 1 | Rel-12 | R4,G1 | Mon 05/03/12 | Fri 06/09/13 | 100% | RP-120268 | RP-131076 | Ericsson | johan.skold@ericsson.com | RP#61 completed (Conclusion: no spin-off WI). Linked to Rel-10 WI on Multi-standard radio Base Station RF requirements for non-contiguous spectrum deployments (MSR_NC) UID_480025 | UTRA, LTE 37.808 | 55 | 28 |  |  | Thu 23/02/12 | Fri 30/08/13
4233 | 580045 | Study on WLAN/3GPP Radio Interworking | FS_UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-122038 | RP-131611 | Intel | sasha.sirotkin@intel.com | RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized¦User experience suboptimal when UE connects to overloaded WLAN. | UTRA, LTE 37.834 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
4234 | 580047 | Study on RAN Enhancements for UMTS/HSPA and LTE Interworking | FS_HSPA_LTE_interworking | 1 | Rel-12 | R3 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-122036 | RP-131612 | China Unicom | Meng Zhang (zhangmeng68@chinaunicom.cn) | RP#62 completed. TR 37.852v100 for Information & Approval | UTRA, LTE 37.852 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
4235 | 580048 | Study on Next-Generation SON for UTRA and LTE | FS_UTRA_LTE_NG_SON | 1 | Rel-12 | R3 | Mon 10/12/12 | Fri 13/06/14 | 100% | RP-122037 | RP-140747 | NSN | krzysztof.kordybach@nsn.com | RP#64 completed. The study of SON features for small cell functionality covered by the Rel-12 small cell enhancement SIs (e.g. dual connectivity) is not in the scope of this study item | UTRA, LTE 37.822 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
4236 | 580049 | Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | FS_UTRA_LTE_1980_2170_REG1 | 1 | Rel-12 | R4 | Tue 11/12/12 | Fri 12/09/14 | 100% | RP-140505 | RP-141099 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1 | UTRA, LTE 37.846 | 58 | 30 |  |  | Mon 10/12/12 | Mon 22/09/14
4237 | 580050 | Study on Base Station specification structure | FS_BSspec_struc | 1 | Rel-12 | R4 | Mon 10/12/12 | Fri 14/06/13 | 100% | RP-122039 | RP-130580 | Ericsson | johan.skold@ericsson.com | RP#60 completed (1-step approval). Study new BS spec structure to avoid duplicate work for new RF features (in case of identical features among different RATs)¦avoid future discussions on how to implement new featurES in CP-150single-RAT/multi-RAT specs | UTRA, LTE, MSR 37.810 | 58 | 30 |  |  | Mon 10/12/12 | Fri 07/06/13
4238 | 590032 | Study on RAN aspects of Machine Type and other mobile data applications Communications enhancements | FS_MTCe_RAN | 1 | Rel-12 | R2 | Fri 01/03/13 | Fri 06/09/13 | 100% | RP-130396 | RP-131081 | ZTE | sergio.parolari@zteitaly.com | RP#61 completed | UTRA, LTE 37.869 | 59 | 30 |  |  | Tue 26/02/13 | Fri 30/08/13
4239 | 570024 | Study on UMTS heterogeneous networks | FS_UTRA_HetNet | 1 | Rel-12 | R1,R2,R3 | Tue 12/06/12 | Fri 06/09/13 | 100% | RP-121436 | RP-131606 | Huawei | carmela.cozzo@huawei.com | RP#62 completed | UTRA 25.800 | 57 | 29 |  |  | Mon 03/09/12 | Mon 02/12/13
4240 | 580039 | Study on Scalable UMTS FDD bandwidth | FS_UTRA_SCAL | 1 | Rel-12 | R1,R4 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-130221 | RP-132035 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#62 completed. TR 25.701v200 for Approval | UTRA 25.701 | 58 | 30 |  |  | Mon 10/12/12 | Wed 18/12/13
4241 | 620046 | Deleted - Study on Scalable UMTS FDD bandwidth by Filtering | FS_UTRA_SCAL_FILT | 1 | Rel-12 | R1 | Mon 09/12/13 | Fri 13/06/14 | 100% | RP-132122 | RP-140988 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#64 stopped at 85% completion. Follow-up of Rel-12 Study on scalable UMTS FDD bandwidth (FS_UTRA_SCAL). The result is captured in the same TR 25.701 | UTRA 25.701 | 62 | 32 | RP-64 | PCG-33 | Wed 27/11/13 | Thu 12/06/14
4242 | 580040 | Study on Dedicated Channel (DCH) enhancements for UMTS | FS_UTRA_DCHenh | 1 | Rel-12 | R1 | Mon 10/12/12 | Fri 06/09/13 | 100% | RP-130216 | RP-131073 | Qualcomm | Arjun Bharadwaj (arjunb@qti.qualcomm.com) | RP#61 completed | UTRA 25.702 | 58 | 30 |  |  | Mon 10/12/12 | Fri 07/06/13
4243 | 580043 | Study on Further Enhanced Uplink (EUL) enhancements | FS_EDCH_enh | 1 | Rel-12 | R2,R1,R3 | Mon 10/12/12 | Fri 06/12/13 | 100% | RP-130347 | RP-131608 | Ericsson | alessandro.caverni@ericsson.com | RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.) | UTRA 25.700 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
4244 | 600018 | Study on HNB Emergency Warning Area for UTRA | FS_HNB_warn_area | 1 | Rel-12 | R3 | Tue 18/06/13 | Thu 06/03/14 | 100% | RP-131258 | RP-140129 | Alcatel-Lucent, Ip.access | Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com | RP#63 completed. TR 25.703 v100 for 1-step approval | UTRA 25.703 | 60 | 31 |  |  | Mon 17/06/13 | Wed 26/02/14
4245 | 610027 | Study on Enhanced Broadcast of System Information | FS_UTRA_SIBenh | 1 | Rel-12 | R2,R1 | Mon 09/09/13 | Fri 06/12/13 | 100% | RP-131386 | RP-131610 | Ericsson | martin.van.der.zee@ericsson.com | RP#62 completed. TR 25.704v100 for Information & Approval. Study need to add capacity to present SI Broadcast mechanism unchanged since R99 | UTRA 25.704 | 61 | 31 |  |  | Sat 07/09/13 | Tue 03/12/13
4246 | 0 | --- RELEASE 11 --- | - | 1 | Rel-11 | SP,CP,GP,RP | Sun 02/06/13 | Tue 16/09/14 | 100% | - | - | - | - | - | - | - | - |  |  | Wed 31/05/06 | Tue 18/02/14
4247 | 470051 | Advanced IP Interconnection of Services | IPXS | 1 | Rel-11 | S1,S2,C1,C3 | Thu 25/03/10 | Wed 12/09/12 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS) | - | 47 | 24 |  |  | Tue 05/03/02 | Mon 19/11/12
4248 | 470052 | Stage 1 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | S1 | Thu 25/03/10 | Wed 21/09/11 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | SP#53 completed | 22.101, 22.228 | 47 | 24 |  |  | Tue 05/03/02 | Wed 24/08/11
4249 | 500025 | Stage 2 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | S2 | Thu 16/12/10 | Wed 14/12/11 | 100% | SP-100876 | - | Ericsson | fredrik.lindholm@ericsson.com | SP#54 completed | 23.228 | 50 | 26 |  |  | Wed 01/12/10 | Mon 28/11/11
4250 | 530004 | Stage 3 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | C1,C3 | Tue 13/09/11 | Wed 12/09/12 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Mon 29/08/11
4251 | 530104 | CT1 part of Stage 3 for Advanced IP Interconnection of Services | IPXS | 3 | Rel-11 | C1 | Fri 16/09/11 | Wed 12/09/12 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | 24.229 | 53 | 27 |  |  | Mon 29/08/11 | Mon 19/11/12
4252 | 530204 | CT3 part of Stage 3 for Advanced IP Interconnection of Services | IPXS | 3 | Rel-11 | C3 | Tue 13/09/11 | Fri 07/09/12 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#57 completed | 29.165 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
4253 | 480030 | System Improvements to Machine-Type Communications | SIMTC | 1 | Rel-11 | S1,S2,S5,C1,C3,C4,C6,R2,R3,R5 | Thu 10/12/09 | Thu 06/03/14 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#58 completed. Updated WID SP-110877=>SP-120848. Enhancements to Rel-10 Feature UID_410031 (NIMTC) based on Rel-11 Study on enhancements to MTC | - | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
4254 | 480130 | Stage 1 for SIMTC | SIMTC | 2 | Rel-11 | S1 | Thu 10/06/10 | Wed 21/09/11 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#53 completed. SP#57 added MTC definitions in 21.905 | 22.368, 21.905 (MTC definitions) | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
4255 | 480230 | TR on Stage 2 for SIMTC | SIMTC | 2 | Rel-11 | S2 | Thu 10/06/10 | Wed 12/09/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#57 completed. TR 23.888v200 for Approval. Was Rel-10 UID_450028 (TR on Stage 2 for NIMTC) | New 23.888 | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
4256 | 520021 | BB1: Stage 2 Reachability Aspects of SIMTC | SIMTC-Reach | 2 | Rel-11 | S2 | Thu 09/06/11 | Wed 20/06/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682) | 23.221, New 23.368 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
4257 | 520121 | Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7) | SIMTC-Reach | 3 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | - | 52 | 27 | SP-54 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4258 | 520221 | On-line device trigger | SIMTC-Reach | 3 | Rel-11 | S2 | Thu 09/06/11 | Wed 20/06/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
4259 | 520321 | MTC Addressing | SIMTC-Reach | 3 | Rel-11 | S2 | Thu 09/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 completed | 23.221, New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
4260 | 520421 | Identifiers – especially removal of MSISDN dependencies in the architecture | SIMTC-Reach | 3 | Rel-11 | S2 | Thu 09/06/11 | Wed 20/06/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
4261 | 520521 | MSISDN-less / PS-Only | SIMTC-Reach | 3 | Rel-11 | S2 | Mon 13/06/11 | Wed 07/03/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | 23.060, 23.272, New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
4262 | 540014 | MTC related interfaces and functional entities to support above features (MTCsp, etc.) | SIMTC-Reach | 3 | Rel-11 | S2 | Wed 14/12/11 | Wed 07/03/12 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | New 23.682 | 54 | 28 |  |  | Fri 25/11/11 | Mon 12/11/12
4263 | 530006 | BB1: Stage 3 (CS+PS) Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 2 | Rel-11 | C1,C3,C4,C6 | Mon 19/09/11 | Fri 07/12/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
4264 | 530106 | CT1 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C1 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 23.040, 24.008, 24.301, 24.341, 24.368 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
4265 | 530206 | CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C3 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 29.061, New 29.368 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
4266 | 530306 | CT4 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C4 | Mon 19/09/11 | Fri 07/12/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 23.003, 23.008, 29.002, 29.060, 29.230, New (29.336, 29.337) | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
4267 | 530406 | CT6 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C6 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | 22/01: acronym modified | 31.102 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
4268 | 530005 | Stage 2/3 for CS aspects for SIMTC | SIMTC-CS | 2 | Rel-11 | C4,C1,C6 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 2/3 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
4269 | 530105 | Deleted - Stage 2 CS aspects for SIMTC | SIMTC-CS | 3 | Rel-11 | C4 | Fri 16/09/11 | Thu 06/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 23.012 | 53 | 27 | CP-57 | PCG-29 | Mon 29/08/11 | Mon 13/08/12
4270 | 530205 | Stage 3 CS aspects for SIMTC | SIMTC-CS | 3 | Rel-11 | C1,C6 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Fri 15/06/12 | Mon 13/08/12
4271 | 530305 | CT1 part of Stage 3 CS aspects for SIMTC | SIMTC-CS | 4 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 24.008, 24.301 | 53 | 27 |  |  | Fri 15/06/12 | Mon 13/08/12
4272 | 530405 | Deleted - CT6 part of Stage 3 CS aspects for SIMTC | SIMTC-CS | 4 | Rel-11 | C6 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 31.102 | 53 | 27 | CP-57 | PCG-29 | Fri 15/06/12 | Mon 13/08/12
4273 | 560002 | Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 2 | Rel-11 | C1,C4 | Fri 15/06/12 | Fri 07/12/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed | Stage 2/3 | 56 | 29 |  |  | Mon 23/04/12 | Sat 17/11/12
4274 | 560102 | CT1 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 3 | Rel-11 | C1 | Fri 15/06/12 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 23.040, 24.008, 24.011, 24.301, 29.018, 29.118 | 56 | 29 |  |  | Mon 23/04/12 | Tue 14/08/12
4275 | 560202 | CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 3 | Rel-11 | C4 | Fri 15/06/12 | Fri 07/12/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed. TS 29.338 v200 for Approval | 23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New 29.338 | 56 | 29 |  |  | Mon 23/04/12 | Wed 28/11/12
4276 | 530009 | RAN overload control for Machine-Type Communications | SIMTC-RAN_OC | 2 | Rel-11 | R2,R3,C1,C6 | Fri 16/09/11 | Fri 07/09/12 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | Stage 2,3. TSG#57 completed | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
4277 | 530109 | Core part: RAN overload control for Machine-Type Communications | SIMTC-RAN_OC-Core | 3 | Rel-11 | R2,R3 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | RP#57 completed | 25.304, 25.331, 25.413, 36.304, 36.331, 36.413 | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
4278 | 530209 | Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 3 | Rel-11 | C1,C6 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Fri 24/08/12
4279 | 530309 | CT1 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 4 | Rel-11 | C1 | Fri 16/09/11 | Fri 15/06/12 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#56 completed | 23.122, 24.008, 24.301 | 53 | 27 |  |  | Mon 29/08/11 | Fri 01/06/12
4280 | 530409 | CT6 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 4 | Rel-11 | C6 | Tue 20/09/11 | Fri 07/09/12 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | CP#57 completed | 31.102 | 53 | 27 |  |  | Mon 29/08/11 | Fri 24/08/12
4281 | 610014 | Test part: System Improvements for Machine-Type Communications | SIMTC-UEConTest | 2 | Rel-11 | R5 | Mon 09/09/13 | Thu 06/03/14 | 100% | RP-140077 | RP-140075 | Ericsson | calle.hagenfeldt@ericsson.com | RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC | 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 61 | 31 |  |  | Tue 03/09/13 | Mon 03/03/14
4282 | 540019 | BB5: Charging of SIMTC (Stage 2/3) | SIMTC-CH | 2 | Rel-11 | S5 | Wed 07/12/11 | Wed 12/12/12 | 100% | SP-120848 | - | Ericsson | patrik.teppo@ericsson.com | SP#58 completed | 32.240, 32.251, 32.298, 32.299 | 54 | 28 |  |  | Mon 24/10/11 | Mon 19/11/12
4283 | 520022 | Deleted - BB2: Stage 2 Signalling Optimizations of SIMTC | SIMTC-Sig | 2 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped. SP#58 updated WID SP-110877=>SP-120848 | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4284 | 520122 | Deleted - Effectively maintain connectivity for a large number of MTC Devices (TS 22.368, 7.1.1) | SIMTC-Sig | 3 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4285 | 520222 | Deleted - Small Data Transmissions (TS 22.368, 7.2.5) | SIMTC-Sig | 3 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4286 | 530107 | Deleted - Stage 3 (CS+PS) Signalling Optimizations of SIMTC | SIMTC-Sig | 3 | Rel-11 | C1,C6 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 13/12/11
4287 | 530207 | Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC | SIMTC-Sig | 4 | Rel-11 | C1 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
4288 | 530307 | Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC | SIMTC-Sig | 4 | Rel-11 | C6 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.102 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
4289 | 520023 | Deleted - BB3: Stage 2 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 2 | Rel-11 | S2 | Wed 08/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4290 | 520123 | Deleted - Charging Requirements (TS 22.368, 7.1.5) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4291 | 520223 | Deleted - Lower Power Consumption (TS 22.368, 7.1.1) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | Fri 10/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4292 | 520323 | Deleted - MTC Monitoring (TS 22.368, 7.2.8) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | Wed 08/06/11 | Wed 14/12/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
4293 | 530008 | Deleted - Stage 3 (CS+PS) CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 3 | Rel-11 | C1,C6 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 13/12/11
4294 | 530108 | Deleted - CT1 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 4 | Rel-11 | C1 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
4295 | 530208 | Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 4 | Rel-11 | C6 | Fri 16/09/11 | Fri 09/12/11 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.101, 31.102 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
4296 | 490028 | Deleted - TR on Security aspects of Machine-Type Communications | - | 2 | Rel-11 | S3 | Thu 10/12/09 | Wed 20/06/12 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | Was Rel-10 UID_460023 (Security for NIMTC). SP#56 stopped (activity transferred to Rel-12 Feature MTCe under UID_560722). | New 33.868 | 49 | 25 | SP-56 | PCG-29 | Sat 18/09/10 | Mon 12/11/12
4297 | 540119 | Deleted - BB4: Secure Connection and Privacy of SIMTC | SIMTC-Sec | 2 | Rel-11 | S3 | Wed 08/06/11 | Wed 12/09/12 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe under UID_560522) | TBD | 52 | 27 | CP-57 | PCG-29 | Thu 26/05/11 | Mon 12/11/12
4298 | 520124 | Deleted - Secure Connection MTC Feature (TS 22.368, 7.2.10) | SIMTC-Sec | 3 | Rel-11 | S3 | Wed 08/06/11 | Wed 12/09/12 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | 52 | 27 | CP-57 | PCG-29 | Thu 26/05/11 | Mon 12/11/12
4299 | 530058 | Deleted - MTC Location Privacy | SIMTC-Priv | 3 | Rel-11 | S3 | Mon 19/09/11 | Wed 12/09/12 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | 53 | 27 | CP-57 | PCG-29 | Tue 13/09/11 | Mon 12/11/12
4300 | 480330 | Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications | SIMTC | 2 | Rel-11 | S2 | Thu 10/06/10 | Wed 08/06/11 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#52 stopped | TBD | 48 | 25 | SP-52 | PCG-27 | Fri 28/05/10 | Mon 12/11/12
4301 | 480430 | Deleted - Stage 2 on Security part for System Improvements to Machine-Type Communications | SIMTC | 2 | Rel-11 | S3 | Thu 10/06/10 | Wed 08/06/11 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#52 stopped | TBD | 48 | 25 | SP-52 | PCG-27 | Fri 28/05/10 | Mon 12/11/12
4302 | 480031 | Unstructured Supplementary Service Data (USSD) simulation service in IMS | USSI | 1 | Rel-11 | S1,C1,C3 | Thu 10/06/10 | Fri 07/12/12 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | CP#58 completed | - | 48 | 25 |  |  | Sun 06/06/10 | Mon 19/11/12
4303 | 480131 | Stage 1 for USSD simulation service in IMS | USSI | 2 | Rel-11 | S1 | Thu 10/06/10 | Thu 10/06/10 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#48 completed. Specify a CS domain USSD like service over IMS (see GSM Mobile User Initiated USSD) | 22.173 | 48 | 25 |  |  | Sun 06/06/10 | Wed 24/08/11
4304 | 520003 | Stage 3 for USSD simulation service in IMS | USSI | 2 | Rel-11 | C1,C3 | Fri 03/06/11 | Fri 07/12/12 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228 | - | 52 | 27 |  |  | Wed 18/05/11 | Mon 19/11/12
4305 | 520103 | CT1 part of Stage 3 for USSD simulation service in IMS | USSI | 3 | Rel-11 | C1 | Fri 03/06/11 | Fri 07/12/12 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at, TS 24.390 Rapp: lili.yang@huawei.com | CP#58 completed | 24.173, 24.229, new 24.390 | 52 | 27 |  |  | Wed 18/05/11 | Mon 19/11/12
4306 | 520203 | CT3 part of Stage 3 for USSD simulation service in IMS | USSI | 3 | Rel-11 | C3 | Tue 07/06/11 | Fri 07/09/12 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#57 completed | 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Mon 13/08/12
4307 | 490031 | QoS Control Based on Subscriber Spending Limits | QoS_SSL | 1 | Rel-11 | S1,S2,S5,C3 | Thu 23/09/10 | Wed 20/06/12 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | TSG#56 completed | - | 49 | 25 |  |  | Thu 02/09/10 | Thu 14/06/12
4308 | 490131 | Stage 1 for QoS Control Based on Subscriber Spending Limits | QoS_SSL | 2 | Rel-11 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed. Use cases & service requirements to allow: 1) modification of QoS based on subscriber’s spending limits 2) enforcing of spending limits for roaming subscribers without having dedicated support in the visited network | 22.115 | 49 | 25 |  |  | Thu 02/09/10 | Wed 24/08/11
4309 | 510043 | Stage 2 for QoS Control Based on Subscriber Spending Limits | QoS_SSL | 2 | Rel-11 | S2 | Wed 23/03/11 | Wed 21/09/11 | 100% | SP-110519 | - | Huawei | Xu Xia (xiatony@huawei.com) | SP#53 completed | 23.203 | 51 | 26 |  |  | Thu 10/03/11 | Fri 12/08/11
4310 | 500029 | Charging for QoS Control Based on Subscriber Spending Limits (Stage 2) | QoS_SSL | 2 | Rel-11 | S5 | Thu 16/12/10 | Wed 20/06/12 | 100% | SP-110519 | - | Nokia Siemens Networks, Huawei | Gerald.Goermer@nsn.com, shan.mingjun@huawei.com | SP#56 completed | 32.240, 32.296 | 50 | 26 |  |  | Sat 27/11/10 | Mon 02/04/12
4311 | 520004 | CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3) | QoS_SSL-CT3 | 2 | Rel-11 | C3 | Fri 03/06/11 | Fri 15/06/12 | 100% | CP-120203 | - | Huawei | QiaoWeihua@huawei.com | CP#56 completed | 29.212, 29.213, 29.214, 29.215, new 29.219 | 52 | 27 |  |  | Wed 18/05/11 | Fri 20/04/12
4312 | 490032 | Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 1 | Rel-11 | S1,S2 | Thu 23/09/10 | Wed 07/03/12 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#55 completed (Stage 2/3 specified under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021. Triggered by S1-102236/GSMA RILTE 10_007r1 (IREG LS_038 to 3GPP on Optimal Media Routing drawbacks) | - | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
4313 | 490132 | TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S2 | Thu 23/09/10 | Wed 07/03/12 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 completed | new 23.849 | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
4314 | 490232 | Stage 1 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed | 22.115, 22.173, 22.228 | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
4315 | 490332 | Deleted - Stage 2 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S2 | Tue 28/09/10 | Wed 07/03/12 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 no normative work in SA2. Stage 2/3 to be done in under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021 | None | 49 | 25 | SP-55 | PCG-28 | Tue 31/08/10 | Mon 05/03/12
4316 | 530021 | Inclusion of Media Resource Broker (Stage 2/3) | MRB | 1 | Rel-11 | C1,C3,IETF | Fri 16/09/11 | Fri 14/06/13 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032 | Stage 2/3 | 53 | 27 |  |  | Thu 25/08/11 | Wed 06/06/12
4317 | 530121 | Stage 2 for Inclusion of Media Resource Broker | MRB | 2 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 23.218 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4318 | 530221 | Stage 3 for Inclusion of Media Resource Broker | MRB | 2 | Rel-11 | C1,C3,IETF | Fri 16/09/11 | Fri 14/06/13 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#60 completed | - | 53 | 27 |  |  | Thu 25/08/11 | Wed 06/06/12
4319 | 530321 | CT1 part of Stage 3 for Inclusion of Media Resource Broker | MRB | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 24.229, 29.165 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4320 | 531005 | (IETF) Inclusion of Media Resource Broker [RFC 6917 (was draft-ietf-mediactrl-mrb)] | MRB | 3 | Rel-11 | C1-IETF | Fri 16/09/11 | Fri 14/06/13 | 100% | CP-120277 | - | Keith Drage | - | CP#60 completed | RFC 6917 (was draft-ietf-mediactrl-mrb) | 53 | 27 |  |  | Thu 25/08/11 | Mon 10/06/13
4321 | 560003 | CT3 part of Stage 3 for Inclusion of Media Resource Broker | MRB | 3 | Rel-11 | C3 | Fri 15/06/12 | Fri 07/09/12 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 29.165 | 56 | 29 |  |  | Fri 01/06/12 | Mon 13/08/12
4322 | 500030 | Non Voice Emergency Services | NOVES | 1 | Rel-11 | S1,S2 | Thu 16/12/10 | Wed 07/03/12 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES) | - | 50 | 26 |  |  | Mon 29/11/10 | Fri 16/03/12
4323 | 500130 | Stage 1 for Non Voice Emergency Services | NOVES | 2 | Rel-11 | S1 | Thu 16/12/10 | Wed 21/09/11 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed | 22.101 | 50 | 26 |  |  | Mon 29/11/10 | Wed 24/08/11
4324 | 530045 | Stage 2 for Non Voice Emergency Services (Support of IMS Emergency Sessions with Other Media on UTRAN and E-UTRAN) | NOVES-IMSESOM | 2 | Rel-11 | S2 | Thu 22/09/11 | Wed 07/03/12 | 100% | SP-110644 | - | Alcatel-Lucent | Deb.Barclay@alcatel-lucent.com | SP#55 completed | 23.060, 23.167, 23.203, 23.401 | 53 | 27 |  |  | Fri 12/08/11 | Mon 20/02/12
4325 | 510047 | Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE | 1 | Rel-11 | S1,C1 | Wed 23/03/11 | Fri 01/03/13 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 Stage 1 completed. CP#59 completed. Triggered by Rel-11 TR 22.809 Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX (FS_VINE) UID_480033 | - | 51 | 26 |  |  | Mon 21/02/11 | Sat 16/02/13
4326 | 510147 | Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE | 2 | Rel-11 | S1 | Wed 23/03/11 | Wed 21/09/11 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 completed | 22.228 | 51 | 26 |  |  | Mon 21/02/11 | Wed 24/08/11
4327 | 530010 | Stage 2/3 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE-CT1 | 2 | Rel-11 | C1 | Tue 20/09/11 | Fri 01/03/13 | 100% | CP-110641 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#59 completed | 23.218, 24.229 | 53 | 27 |  |  | Thu 25/08/11 | Sat 16/02/13
4328 | 520028 | Anonymous Call Rejection in the CS domain | ACR_CS | 1 | Rel-11 | S1,C4,C3 | Tue 07/06/11 | Fri 02/12/11 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | CP#54 completed | - | 52 | 27 |  |  | Thu 19/05/11 | Wed 23/11/11
4329 | 520128 | Stage 1 for Anonymous Call Rejection in the CS domain | ACR_CS | 2 | Rel-11 | S1 | Tue 07/06/11 | Wed 08/06/11 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013) | 22.004, 22.081, 22.082, 22.085, 22.088 | 52 | 27 |  |  | Thu 19/05/11 | Mon 19/09/11
4330 | 530011 | Core Network aspects of Anonymous Call Rejection in the CS domain | ACR_CS-CN | 2 | Rel-11 | C4,C3 | Wed 14/09/11 | Fri 02/12/11 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | Stage 2/3 | 53 | 27 |  |  | Sat 27/08/11 | Sat 27/08/11
4331 | 530111 | CT4 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 2/3) | ACR_CS-CN | 3 | Rel-11 | C4 | Wed 14/09/11 | Fri 02/12/11 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | 23.018, 23.081, 23.082, 23.085, 23.088, 23.205, 23.231, 24.088, 29.002, 29.011 | 53 | 27 |  |  | Sat 27/08/11 | Wed 23/11/11
4332 | 530211 | CT3 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 3) | ACR_CS-CN | 3 | Rel-11 | C3 | Wed 14/09/11 | Fri 16/09/11 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#53 completed | 29.163, 29.292 | 53 | 27 |  |  | Sat 27/08/11 | Mon 29/08/11
4333 | 460026 | Support for BroadBand Forum Accesses Interworking | BBAI | 1 | Rel-11 | S2,S1,C1,C3,C4,IETF | Thu 10/12/09 | Wed 12/12/12 | 100% | SP-120539 | - | Ericsson | peter.bleckert@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses) | - | 46 | 24 |  |  | Sun 06/12/09 | Thu 30/08/12
4334 | 460126 | Stage 1 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S1 | Thu 10/12/09 | Thu 25/03/10 | 100% | SP-120539 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#47 completed. Provide service requirements for supporting interworking between 3GPP EPS and the fixed broadband accesses defined by BBF | 22.278 CR#0058 | 46 | 24 |  |  | Sun 06/12/09 | Thu 30/08/12
4335 | 470022 | TR on Stage 2 for BBAI | BBAI | 2 | Rel-11 | S2 | Fri 26/03/10 | Wed 20/06/12 | 100% | SP-120539 | - | Ericsson | marco.spini@huawei.com | TR 23.839 not Approved in Rel-11¦progressed in Rel-12 under P4C-TI (UID_560824) | new 23.839 | 47 | 24 |  |  | Fri 13/04/12 | Mon 15/04/13
4336 | 470023 | Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S2 | Fri 26/03/10 | Wed 20/06/12 | 100% | SP-120539 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed | 23.203, new 23.139 | 47 | 24 |  |  | Sun 06/12/09 | Sat 09/06/12
4337 | 541001 | (IETF) Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S2-IETF | Mon 12/12/11 | Wed 12/12/12 | 100% | SP-120539 | - | Lionel Morand | Lionel Morand | Solved by IANA-registration. No RFC needed | - | 54 | 28 |  |  | Tue 06/12/11 | Thu 22/11/12
4338 | 530012 | Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 2 | Rel-11 | C1,C3,C4 | Fri 16/09/11 | Fri 07/12/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Sat 17/11/12
4339 | 530112 | TR on Stage 3 BB I for BBAI; UE to network protocols | BBAI_BBI-CT | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 15/06/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed. Identify additional FMC specific procedurES in CP-150addition to those in 24.302 (on access authentication & authorization and tunnel management¦IP mobility mode selection¦security aspects) | new 24.820 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
4340 | 550005 | TR on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | BBAI_BBI-CT | 3 | Rel-11 | C4 | Fri 02/03/12 | Fri 15/06/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed | new 29.839 | 55 | 28 |  |  | Mon 20/02/12 | Thu 14/06/12
4341 | 551002 | Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | BBAI_BBI-CT | 3 | Rel-11 | C4-IETF | Fri 02/03/12 | Fri 15/06/12 | 100% | CP-120419 | - | Lionel Morand | - | Draft removed from 3GPP documentation | draft-so-ipsecme-ikev2-cpext | 55 | 28 | CP-56 | PCG-29 | Mon 05/03/12 | Thu 14/06/12
4342 | 530212 | CT1 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 24.229, new 24.139 | 53 | 27 |  |  | Mon 29/08/11 | Wed 05/09/12
4343 | 530312 | CT3 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C3 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
4344 | 530412 | CT4 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C4 | Fri 16/09/11 | Fri 07/12/12 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | 23.008, 29.273, 29.274, new 29.139 | 53 | 27 |  |  | Mon 29/08/11 | Wed 28/11/12
4345 | 490026 | Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CTofldS1 | 2 | Rel-11 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-120419 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#53 completed. 22/01: acronym modified | 22.278 | 49 | 25 |  |  | Wed 01/09/10 | Thu 22/01/15
4346 | 470024 | Stage 2 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CTofldS2 | 2 | Rel-11 | S2 | Tue 28/09/10 | Wed 20/06/12 | 100% | SP-120419 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed. 22/01: acronym modified | 23.203, 23.401, 23.402, 23.139 | 47 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
4347 | 530013 | Stage 3 BB II - Core Network impacts: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 2 | Rel-11 | C3,C1,C4 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
4348 | 530113 | TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | BBAI_BBII-CT | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 15/06/12 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#56 completed | 24.82 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
4349 | 530213 | CT1 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | new 24.320 | 53 | 27 |  |  | Mon 29/08/11 | Tue 14/08/12
4350 | 530313 | CT3 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C3 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
4351 | 530413 | CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C4 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#55 completed | 23.008, 29.273 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
4352 | 490027 | Deleted - Stage 1 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S1 | Thu 23/09/10 | Wed 21/09/11 | 100% | SP-120539 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#57 stopped. Updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#53 completed | 22.278 | 49 | 25 | SP-57 | PCG-29 | Wed 01/09/10 | Sat 09/06/12
4353 | 470025 | Deleted - Stage 2 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S2 | Tue 28/09/10 | Wed 07/03/12 | 100% | SP-120539 | - | Huawei | marco.spini@huawei.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#55 stopped | 23.203, 23.401, 23.402, 23.139 | 47 | 24 | SP-55 | PCG-28 | Sun 06/12/09 | Thu 30/08/12
4354 | 530014 | Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility | - | 2 | Rel-11 | C3,C1,C4 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 06/03/12
4355 | 530114 | Deleted - TR on Stage 3 BB III for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | - | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | new 24.820 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
4356 | 530214 | Deleted - CT1 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | TBD | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
4357 | 530314 | Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C3 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 29.212, 29.213, 29.215 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
4358 | 530414 | Deleted - CT4 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C4 | Fri 16/09/11 | Fri 02/03/12 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 23.008, 29.273 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
4359 | 480035 | Single Radio Voice Call Continuity (SRVCC) aspect of enhancements for Multimedia Priority Service | eMPS_SRVCC | 1 | Rel-11 | S2 | Thu 10/06/10 | Wed 14/12/11 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed. Analyze and if needed specify mechanisms for the priority handling of SRVCC with regard to LTE/EPC | Stage 2 | 48 | 25 |  |  | Sun 06/06/10 | Fri 12/08/11
4360 | 480135 | TR on SRVCC for eMPS | eMPS_SRVCC | 2 | Rel-11 | S2 | Thu 10/06/10 | Wed 08/06/11 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#52 completed | new 23.854 | 48 | 25 |  |  | Sun 06/06/10 | Fri 12/08/11
4361 | 480235 | Stage 2 on SRVCC for eMPS | eMPS_SRVCC | 2 | Rel-11 | S2 | Thu 10/06/10 | Wed 14/12/11 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed | 23.216, 23.237 | 48 | 25 |  |  | Sun 06/06/10 | Sun 04/03/12
4362 | 500026 | Single Radio Video Call Continuity for 3G-CS | vSRVCC | 1 | Rel-11 | S2,C1,C3,C4 | Fri 15/10/10 | Fri 15/06/12 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | CP#56 completed. Provide Single Radio VIDEO Call Continuity from E-UTRAN to UTRAN-CS based on the agreed architecture alternative in TR 23.886 | - | 50 | 26 |  |  | Fri 26/11/10 | Mon 18/06/12
4363 | 500126 | Stage 2 for Single Radio Video Call Continuity for 3G-CS | vSRVCC | 2 | Rel-11 | S2 | Fri 15/10/10 | Wed 21/09/11 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | SP#53 completed. Triggered by Feasibility Study on video call handover capability in TR 23.886 UID_470048 Study on Single Radio Video Call Continuity for 3G-CS (FS_vSRVCC) | 23.203, 23.216, 23.237 | 50 | 26 |  |  | Fri 26/11/10 | Mon 18/06/12
4364 | 520005 | CN aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | Fri 03/06/11 | Fri 15/06/12 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | Stage 3. CP#56 completed | - | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
4365 | 520105 | CT1 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C1 | Fri 03/06/11 | Fri 15/06/12 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#56 completed | 24.008, 24.237, 24.301 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
4366 | 520205 | CT3 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C3 | Fri 03/06/11 | Fri 02/12/11 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.211, 29.212, 29.213, 29.215 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
4367 | 520305 | CT4 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C4 | Fri 03/06/11 | Fri 02/12/11 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.28 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
4368 | 480038 | Network-provided Location information for IMS (NETLOC) | NWK-PL2IMS | 1 | Rel-11 | S2,S1,S5,C3,C4,C1 | Thu 10/06/10 | Fri 01/03/13 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging. | - | 48 | 25 |  |  | Sun 06/06/10 | Tue 13/11/12
4369 | 500027 | Stage 1 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S1 | Wed 15/12/10 | Wed 21/09/11 | 100% | - | - | n/a | n/a | SP#53 completed | 22.115 | 50 | 26 |  |  | Mon 13/12/10 | Wed 21/09/11
4370 | 480138 | TR on Stage 2 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S2 | Thu 10/06/10 | Wed 14/12/11 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#54 completed | new 23.842 | 48 | 25 |  |  | Sun 06/06/10 | Tue 06/12/11
4371 | 480238 | Stage 2 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S2 | Tue 15/06/10 | Wed 07/03/12 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#55 completed | 23.060, 23.203, 23.228, 23.401 | 48 | 25 |  |  | Sun 06/06/10 | Mon 20/02/12
4372 | 490029 | Charging for Network-provided Location information for IMS | NWK-PL2IMS_CH | 2 | Rel-11 | S5 | Thu 23/09/10 | Wed 12/09/12 | 100% | SP-110700 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#57 completed | Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299) | 49 | 25 |  |  | Fri 03/09/10 | Wed 05/09/12
4373 | 550008 | CT aspects of Network-provided Location information for IMS (Stage 3) | NWK-PL2IMS-CT | 2 | Rel-11 | C3,C4,C1 | Fri 02/03/12 | Fri 01/03/13 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | Stage 3. 3/3: Acronym changed from "NWK-PL2IMS_CT" | - | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
4374 | 550108 | CT3 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C3 | Fri 02/03/12 | Fri 07/09/12 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 29.212, 29.214, 29.215 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
4375 | 550208 | CT4 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C4 | Fri 02/03/12 | Fri 15/06/12 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.305, 29.328, 29.329 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
4376 | 550308 | CT1 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C1 | Fri 02/03/12 | Fri 01/03/13 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 24.229, 24.292 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
4377 | 500032 | Service Awareness and Privacy Policies | SAPP | 1 | Rel-11 | S2,S1,C3 | Tue 12/10/10 | Fri 02/12/11 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047 | - | 50 | 26 |  |  | Fri 26/11/10 | Fri 12/08/11
4378 | 500132 | Stage 1 for Service Awareness and Privacy Policies | SAPP | 2 | Rel-11 | S1 | Tue 12/10/10 | Wed 15/12/10 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | For deep packet inspection (i.e. Traffic Detection Functionality) SA1 indicated that no new requirements are needed (see Objective of FS_PP SA1,SA2 Rel-10 Study on Policy solutions and enhancements UID_440047 TR 23.813) | - | 50 | 26 |  |  | Fri 26/11/10 | Thu 02/12/10
4379 | 500232 | Stage 2 for Service Awareness and Privacy Policies | SAPP | 2 | Rel-11 | S2 | Fri 15/10/10 | Wed 21/09/11 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#53 completed | 23.203 | 50 | 26 |  |  | Fri 26/11/10 | Fri 12/08/11
4380 | 510003 | CT3 part of Service Awareness and Privacy Policies | SAPP-CT3 | 2 | Rel-11 | C3 | Fri 18/03/11 | Fri 02/12/11 | 100% | CP-110136 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#54 completed. Stage 3 to support Application Detection and Control Functionality. Update Gx / introduce Sd reference points and procedures. Update S9 reference point in roaming scenarios | 29.212, 29.213, 29.214, 29.215 | 51 | 26 |  |  | Wed 02/03/11 | Thu 24/11/11
4381 | 500033 | VPLMN Autonomous CSG Roaming | VCSG | 1 | Rel-11 | S2,C4 | Fri 15/10/10 | Wed 14/12/11 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#56 completed. Linked to Rel-10 UID_450053 Enhanced Home NodeB / eNodeB (EHNB). Implements Rel-9 requirements for CSG support in SA1 TS 22.220 | - | 50 | 26 |  |  | Fri 26/11/10 | Mon 13/08/12
4382 | 500133 | Stage 2 for VPLMN Autonomous CSG Roaming | VCSG | 2 | Rel-11 | S2 | Fri 15/10/10 | Wed 14/12/11 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#54 completed | 23.002, 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Mon 28/11/11
4383 | 530017 | CT aspects of VPLMN Autonomous CSG Roaming | VCSG-St3 | 2 | Rel-11 | C4 | Wed 07/12/11 | Wed 07/12/11 | 100% | CP-120196 | - | ZTE | Fei Lu (lu.fei1@zte.com.cn) | CP#57 completed | 23.003, 23.007, 23.008, 23.012, 29.002, 29.230, 29.272 | 53 | 27 |  |  | Sat 27/08/11 | Mon 13/08/12
4384 | 510048 | Data Identification in Access Network Discovery and Selection Function (ANDSF) | DIDA | 1 | Rel-11 | S2,C1 | Wed 23/03/11 | Fri 07/12/12 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions | Stage 2/3 | 51 | 26 |  |  | Mon 21/02/11 | Mon 19/11/12
4385 | 510148 | TR on Stage 2 for Data Identification in ANDSF | DIDA | 2 | Rel-11 | S2 | Wed 23/03/11 | Wed 14/12/11 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#54 completed | New 23.855 | 51 | 26 |  |  | Mon 21/02/11 | Mon 28/11/11
4386 | 510248 | Stage 2 for Data Identification in ANDSF | DIDA | 2 | Rel-11 | S2 | Thu 24/03/11 | Wed 07/03/12 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#55 completed | 23.402 | 51 | 26 |  |  | Mon 21/02/11 | Mon 20/02/12
4387 | 550003 | CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3 | DIDA-CT | 2 | Rel-11 | C1 | Fri 02/03/12 | Fri 07/12/12 | 100% | CP-120089 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#58 completed | 24.302, 24.312 | 55 | 28 |  |  | Mon 20/02/12 | Mon 21/01/13
4388 | 510050 | LOcation-Based Selection of gaTEways foR WLAN | LOBSTER | 1 | Rel-11 | S2,C4 | Wed 23/03/11 | Fri 15/06/12 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | CP#56 completed. Related to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP). Enhancements to ePDG and PDN GW selection functions for S2b and S2c based on UE location | - | 51 | 26 |  |  | Fri 18/03/11 | Fri 01/06/12
4389 | 510150 | Stage 2 for LOcation-Based Selection of gaTEways foR WLAN | LOBSTER | 2 | Rel-11 | S2 | Wed 23/03/11 | Wed 14/12/11 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | SP#54 completed | 23.402 | 51 | 26 |  |  | Fri 18/03/11 | Sun 04/03/12
4390 | 540010 | CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 2 | Rel-11 | C4 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | Stage 3. CP#56 completed | Stage 3 | 54 | 28 |  |  | Wed 23/11/11 | Mon 24/09/12
4391 | 540110 | CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 3 | Rel-11 | C4 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 completed | 29.273 | 54 | 28 |  |  | Wed 23/11/11 | Mon 24/09/12
4392 | 540210 | Deleted - CT1 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 3 | Rel-11 | C1 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 stopped | 24.302 | 54 | 28 | CP-56 | PCG-29 | Wed 23/11/11 | Mon 24/09/12
4393 | 530001 | Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 1 | Rel-11 | S2,C1,C3,C4,G2,R2,R3,R5 | Mon 12/09/11 | Fri 13/03/15 | 100% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | Stage 1 in Rel-8 TS 22.278 clause 7.1.4.2. Triggered by Rel-11 TR 23.885 Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (FS_rSRVCC) UID_460030 | - | 53 | 27 |  |  | Fri 12/08/11 | Tue 20/09/11
4394 | 530101 | Stage 2 for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 2 | Rel-11 | S2 | Thu 22/09/11 | Wed 20/06/12 | 100% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#56 completed | 23.216, 23.237 | 53 | 27 |  |  | Fri 12/08/11 | Mon 18/06/12
4395 | 530201 | CT aspects for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4396 | 530301 | CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.009, 24.008, 24.229, 24.237, 24.292, 24.301 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4397 | 530401 | CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C3 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 29.165, 29.292 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4398 | 530501 | CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C4 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.280, 29.303, 29.305, 29.328 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
4399 | 530601 | GERAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-GERAN | 2 | Rel-11 | G2 | Mon 12/09/11 | Fri 28/06/13 | 100% | GP-111290 | - | ZTE | li.jing4@zte.com.cn | GP#60 completed. GP#51 approved WID | 44.018, 48.008 | 51 | 27 |  |  | Thu 25/08/11 | Wed 04/09/13
4400 | 530701 | UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA | 2 | Rel-11 | R3,R2 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111334 | - | Huawei | liwei.qiu@huawei.com | RP#58 completed | UTRA | 53 | 27 |  |  | Thu 25/08/11 | Thu 25/08/11
4401 | 530801 | Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA-Core | 3 | Rel-11 | R3,R2 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111334 | RP-121553 | Huawei | liwei.qiu@huawei.com | RP#58 completed | 25.331, 25.401, 25.413 | 53 | 27 |  |  | Thu 25/08/11 | Tue 27/11/12
4402 | 640012 | Test part: Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-UEConTest | 2 | Rel-11 | R5 | Sun 15/06/14 | Fri 13/03/15 | 100% | RP-141786 | RP-150133 | Ericsson | calle.hagenfeldt@ericsson.com | ¦Stat Rep: RP-141167->RP-141771 1st Apr 15: Compl:40%->100% 1st Apr 15: Stat Rep: RP-141771->RP-150133 | 36.508, 36.523-1, 36.523-2, 36.523-3 | 64 | 33 |  |  | Tue 10/06/14 | Wed 01/04/15
4403 | 530046 | S2a Mobility based On GTP and WLAN access to EPC | SaMOG_WLAN | 1 | Rel-11 | S2,C4,C1,C3,IETF | Thu 22/09/11 | Wed 05/03/14 | 100% | SP-110642 | - | ZTE | Chunhui Zhu (zhu.chunhui@zte.com.cn) | Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a) | Stage 2/3 | 53 | 27 |  |  | Fri 12/08/11 | Wed 19/02/14
4404 | 530146 | Stage 2 for S2a Mobility based On GTP and WLAN access to EPC | SaMOG_WLAN | 2 | Rel-11 | S2 | Thu 22/09/11 | Wed 07/03/12 | 100% | SP-110642 | - | ZTE | zhu.chunhui@zte.com.cn | SP#55 completed | 23.002, 23.203, 23.402 | 53 | 27 |  |  | Fri 12/08/11 | Mon 20/02/12
4405 | 540011 | CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 2 | Rel-11 | C4,C1,C3,IETF | Fri 02/12/11 | Wed 05/03/14 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | Stage 3 | 54 | 28 |  |  | Wed 26/10/11 | Wed 23/11/11
4406 | 540111 | CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C4 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#57 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4407 | 561010 | Deleted - (IETF) CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C4-IETF | Mon 23/04/12 | Wed 05/03/14 | 100% | CP-110802 | - | Lionel Morand | - | CP#63 Draft removed from 3GPP documentation | draft-ietf-radext-ieee802ext | 56 | 29 | CP-53 | PCG-32 | Fri 20/04/12 | Wed 19/02/14
4408 | 540211 | Deleted - CT1 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C1 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 stopped (no CT1 impact) | 24.302 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Fri 01/06/12
4409 | 540311 | CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C3 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 completed | 29.212, 29.213, 29.215 | 54 | 28 |  |  | Wed 26/10/11 | Fri 01/06/12
4410 | 540029 | Roaming Architecture for Voice over IMS with Local Breakout | RAVEL | 1 | Rel-11 | S2,S5,C1,C3 | Mon 28/11/11 | Fri 07/12/12 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | CP#58 completed. Triggered by Rel-11 TR 23.850 Study on Roaming Architecture for Voice over IMS with Local Breakout (FS_RAVEL). GSMA CPWP LS_in S5-102806 asked 3GPP SA5 to check if CS voice charging principles also apply to voice over IMS | Stage 2/3 | 54 | 28 |  |  | Tue 25/10/11 | Tue 20/11/12
4411 | 540129 | Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout | RAVEL | 2 | Rel-11 | S2 | Mon 28/11/11 | Wed 14/12/11 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed | 23.002, 23.228 | 54 | 28 |  |  | Tue 25/10/11 | Mon 28/11/11
4412 | 540030 | Charging for Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CH | 2 | Rel-11 | S5 | Wed 14/12/11 | Wed 12/09/12 | 100% | SP-110886 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | Stage 2/3. SP#57 completed | 32.240, 32.260, 32.298, 32.299 | 54 | 28 |  |  | Thu 08/12/11 | Wed 05/09/12
4413 | 550004 | CT aspects of Roaming Architecture for Voice over IMS with Local Breakout (Stage 3) | RAVEL-CT | 2 | Rel-11 | C1,C3 | Fri 02/03/12 | Fri 07/12/12 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | Stage 3 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
4414 | 550104 | CT1 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CT | 3 | Rel-11 | C1 | Fri 02/03/12 | Fri 07/12/12 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 24.229, 24.292, 24.237 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
4415 | 550204 | CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CT | 3 | Rel-11 | C3 | Fri 02/03/12 | Fri 07/12/12 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 29.165, 29.162, 29.079 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
4416 | 560027 | IMS Overload Control | IOC | 1 | Rel-11 | S2,C1,C3,IETF | Mon 18/06/12 | Tue 09/12/14 | 100% | SP-120273 | - | Orange, China Mobile | Antoine MOUQUET, YU Qing | SP#57 Stage 2 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. Linked to UID_410041 Study on IMS Evolution (TR 23.812). Solutions from IETF SOC WG and existing 3GPP procedures to be re-used if possible & backward compatibility ensured | Stage 2/3 | 56 | 29 |  |  | Fri 11/05/12 | Tue 24/07/12
4417 | 560127 | Stage 2 for IMS Overload Control | IOC | 2 | Rel-11 | S2 | Mon 18/06/12 | Wed 12/09/12 | 100% | SP-120273 | - | Orange, China Mobile | antoine.mouquet@orange-ftgroup.com, YU Qing | SP#57 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. | 23.228 | 56 | 29 |  |  | Fri 11/05/12 | Tue 24/07/12
4418 | 570007 | Stage 3 for IMS Overload Control | IOC | 2 | Rel-11 | C1,C3,IETF | Wed 05/09/12 | Tue 09/12/14 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | - | - | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4419 | 570107 | CT1 part of Stage 3 for IMS Overload Control | IOC | 3 | Rel-11 | C1 | Wed 05/09/12 | Fri 07/12/12 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 24.229 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4420 | 570207 | CT3 part of Stage 3 for IMS Overload Control | IOC | 3 | Rel-11 | C3 | Wed 05/09/12 | Fri 07/12/12 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 29.165 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4421 | 571001 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | Mon 29/07/13 | Tue 09/12/14 | 100% | CP-120561 | - | Keith Drage | Keith Drage | in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control) | RFC 7339 | 57 | 29 |  |  | Mon 03/09/12 | Tue 10/03/15
4422 | 571002 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | Mon 29/07/13 | Tue 09/12/14 | 100% | CP-120561 | - | Keith Drage | Keith Drage | Submitted to IESG for publication. Dec14: 50->90%. Mar15: 100%. Impacted RFC updated (was draft-ietf-soc-overload-rate-control). Jun 15: RFC 7415 (was draft-ietf-soc-overload-rate-control) | RFC 7415 | 57 | 29 |  |  | Mon 03/09/12 | Tue 10/03/15
4423 | 571003 | (IETF) CT part of Stage 3 for IMS Overload Control (RFC 7200) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | Mon 29/07/13 | Fri 13/06/14 | 100% | CP-120561 | - | Keith Drage | Keith Drage | CP#64 completed | RFC 7200 (was draft-ietf-soc-load-control-event-package) | 57 | 29 |  |  | Mon 13/08/12 | Fri 06/06/14
4424 | 520030 | Rel-11 Security small Enhancements | SEC11 | 1 | Rel-11 | S3 | Wed 08/06/11 | Wed 12/09/12 | 100% | - | - | - | - | SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature | - | 52 | 27 |  |  | Tue 19/04/11 | Thu 16/08/12
4425 | 520032 | Lawful Interception in the 3GPP Rel-11 | LI11 | 1 | Rel-11 | S3 | Fri 10/06/11 | Wed 20/06/12 | 100% | SP-110424 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | Stage 1/2/3. SP#56 completed | 33.106, 33.107, 33.108 | 52 | 27 |  |  | Tue 17/05/11 | Fri 08/06/12
4426 | 440055 | ZUC EEA3 and EIA3 (new Encryption & Integrity EPS security Algorithms) | EEA3_EIA3 | 1 | Rel-11 | S3,R5 | Thu 04/06/09 | Fri 07/09/12 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | RP#57 completed testing | - | 44 | 23 |  |  | Mon 18/05/09 | Tue 04/09/12
4427 | 440155 | ZUC EEA3 and EIA3 | EEA3_EIA3 | 2 | Rel-11 | S3 | Thu 04/06/09 | Wed 14/12/11 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | SP#53 completed new EPS algorithms e.g. for China | 33.401, New (35.221, 35.222, 35.223, 35.924) | 44 | 23 |  |  | Mon 18/05/09 | Mon 12/12/11
4428 | 560009 | Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms) | EEA3_EIA3_UEConTest | 2 | Rel-11 | R5 | Mon 18/06/12 | Fri 07/09/12 | 100% | RP-120631 | RP-120968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223) | 36.523-1, 36.523-2, 36.523-3 | 56 | 29 |  |  | Mon 04/06/12 | Tue 04/09/12
4429 | 480039 | Specification of Protection against Unsolicited Communication for IMS (produced TR-only) | SPUCI | 1 | Rel-11 | S3 | Thu 10/06/10 | Wed 07/03/12 | 100% | SP-100428 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#55 completed (No normative work). TR 33.838v200 for Approval & abandoned new TS 33.237. Continuation of Rel-9 UID_410027/410029. Builds on TR 33.937 Study of Mechanisms for PUCI | New 33.838, abandoned New 33.237 | 48 | 25 |  |  | Wed 05/05/10 | Mon 05/03/12
4430 | 510053 | H(e)NB security features for UE mobility scenarios (Stage 2) | HNB_mob_Sec | 1 | Rel-11 | S3 | Wed 23/03/11 | Wed 07/03/12 | 100% | SP-110025 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#55 completed. Add HeNB Security extensions to Extended H(e)NB Features (EHNBF) UID_450053 | 33.32 | 51 | 26 |  |  | Mon 14/02/11 | Mon 20/02/12
4431 | 540012 | Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials | GBA-ext | 1 | Rel-11 | S3,C4,C1 | Fri 02/12/11 | Fri 07/09/12 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | Stage 2/3. CP#57 completed | - | 54 | 28 |  |  | Mon 28/11/11 | Tue 14/08/12
4432 | 540112 | Stage 2 for GBA extensions for re-use of SIP Digest credentials | GBA-ext | 2 | Rel-11 | S3 | Wed 14/12/11 | Wed 07/03/12 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | SP#55 completed | 33.22 | 54 | 28 |  |  | Mon 28/11/11 | Mon 20/02/12
4433 | 540212 | Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 2 | Rel-11 | C4,C1 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | Stage 3 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
4434 | 540312 | CT4 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 3 | Rel-11 | C4 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.109 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
4435 | 540412 | CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 3 | Rel-11 | C1 | Mon 05/12/11 | Fri 07/09/12 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 24.109 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
4436 | 520033 | Extensions of Acoustic Test Specifications in TS 26.131 and TS 26.132 | Ext_ATS | 1 | Rel-11 | S4 | Wed 08/06/11 | Wed 12/09/12 | 100% | SP-110309 | - | Orange, Qualcomm | stephane.ragot@orange-ftgroup.com, Andre Schevciw (aschevci@qualcomm.com) | SP#57 completed | 26.131, 26.132 | 52 | 27 |  |  | Thu 26/05/11 | Mon 20/08/12
4437 | 530048 | Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements | EMM | 1 | Rel-11 | S4 | Wed 07/09/11 | Wed 06/03/13 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | Stage 3. SP#59 completed | 26.140, 26.234, 26.247, New 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Sat 16/02/13
4438 | 530148 | Enhancement to FEC for MBMS | EMM-EFEC | 2 | Rel-11 | S4 | Wed 21/09/11 | Wed 06/03/13 | 100% | SP-120182 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#59 completed | 26.346, new 26.947 | 53 | 27 |  |  | Wed 07/09/11 | Sat 16/02/13
4439 | 530248 | Download Delivery Enhancements for MBMS | EMM-DDE | 2 | Rel-11 | S4 | Wed 21/09/11 | Wed 12/12/12 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | SP#58 completed | 26.346, new 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Tue 11/12/12
4440 | 530348 | IMS-based PSS and MBMS Streaming Synchronization Enhancements | EMM-IPME | 2 | Rel-11 | S4 | Wed 07/09/11 | Wed 12/09/12 | 100% | SP-120025 | - | InterDigital Communications | hang.liu@interdigital.com | SP#58 completed | 26.237, new 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Tue 11/12/12
4441 | 560041 | Mobile 3D Video Coding | M3DV | 1 | Rel-11 | S4 | Thu 07/06/12 | Wed 12/09/12 | 100% | SP-120229 | - | Orange | gilles.teniou@orange.com | SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905. | 26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905 | 56 | 29 |  |  | Thu 07/06/12 | Mon 20/08/12
4442 | 510051 | Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM11 | 1 | Rel-11 | S5 | Wed 23/03/11 | Thu 07/03/13 | 100% | - | - | - | - | OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
4443 | 510151 | Rel-11 Network Infrastructure Management | OAM11-NIM | 2 | Rel-11 | S5 | Wed 23/03/11 | Thu 07/03/13 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
4444 | 510056 | IRP framework enhancements to support Management of Converged Networks | OAM-FMC-IRP | 3 | Rel-11 | S5 | Wed 23/03/11 | Thu 07/03/13 | 100% | SP-120652 | - | Nokia Siemens Networks, Ericsson | thomas.tovinger@ericsson.com, olaf.pollakowski@nsn.com | SP#59 completed. Triggered by SA5 Studies TR 32.833, 32.828, 32.831 | 32.101/103/150, new (28.620/621/622/623/624/625/626/627/628/629/631/632/633/651/652/653/654/655/656/657/658/659/661/662/663/671/672/673/674/675/676/701/702/703/704/705/706/707/708/709/731/732/733/734/735/736/751/752/753, 32.107/156/157/853/854 | 51 | 26 |  |  | Wed 09/03/11 | Wed 05/12/12
4445 | 510251 | Rel-11 Performance Management | OAM11-PM | 2 | Rel-11 | S5 | Wed 23/03/11 | Wed 12/12/12 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Mon 19/11/12
4446 | 510057 | IMS Performance Management enhancements | OAM-ePM-IMS | 3 | Rel-11 | S5 | Wed 23/03/11 | Wed 07/03/12 | 100% | SP-110134 | - | ZTE | guo.wenjie1@zte.com.cn | SP#55 completed | 32.409 | 51 | 26 |  |  | Tue 22/02/11 | Mon 05/03/12
4447 | 510058 | Enhanced Management of UE based network performance measurements | OAM-ePM-UE | 3 | Rel-11 | S5 | Wed 23/03/11 | Wed 12/12/12 | 100% | SP-110135 | - | Huawei, Ericsson, Nokia Siemens Networks | Zou Lan (zlan@huawei.com), ulf.hubinette@ericsson.com, gyula.bodog@nsn.com | SP#58 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 51 | 26 |  |  | Tue 22/02/11 | Wed 21/11/12
4448 | 520034 | CN performance measurements enhancement | OAM-ePM-CN | 3 | Rel-11 | S5 | Wed 08/06/11 | Wed 12/09/12 | 100% | SP-110275 | - | China Mobile | Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com), Li Jian (lijian@chinamobile.com) | SP#57 completed | 32.406, 32.407, 32.426 | 52 | 27 |  |  | Thu 19/05/11 | Fri 31/08/12
4449 | 530049 | Management of Carrier Aggregation for LTE | OAM-CA | 3 | Rel-11 | S5 | Wed 21/09/11 | Wed 12/12/12 | 100% | SP-120776 | - | Nokia Siemens Networks, Ericsson | yizhi.yao@nsn.com, per.elmdahl@ericsson.com | SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA) | 32.425 | 53 | 27 |  |  | Sat 27/08/11 | Tue 20/11/12
4450 | 510351 | Rel-11 Self-Organizing Networks (SON) - OAM aspects | OAM11-SON | 2 | Rel-11 | S5 | Wed 23/03/11 | Wed 06/03/13 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
4451 | 510059 | UTRAN Self-Organizing Networks (SON) management | OAM-SON-UTRAN | 3 | Rel-11 | S5 | Wed 23/03/11 | Wed 12/09/12 | 100% | SP-120552 | - | Huawei | kai.zhangkai@huawei.com | SP#57 completed. Updated WID SP-110518=>SP-120552 | UTRA 32.405, 32.500, 32.511, 32.521, 32.522, 32.526, 32.642, 32.646 | 51 | 26 |  |  | Tue 22/02/11 | Fri 31/08/12
4452 | 530051 | LTE Self-Organizing Networks (SON) coordination management | OAM-SON-LTE_COORD | 3 | Rel-11 | S5 | Wed 21/09/11 | Wed 06/03/13 | 100% | SP-110637 | - | Huawei, Nokia Siemens Networks | kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com | SP#59 completed | LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766 | 53 | 27 |  |  | Sat 27/08/11 | Sat 16/02/13
4453 | 540031 | Inter-RAT Energy Saving Management | OAM-IRAT-ESM | 3 | Rel-11 | S5 | Wed 07/12/11 | Wed 12/12/12 | 100% | SP-110701 | - | Nokia Siemens Networks, Huawei | clemens.suerbaum@nsn.com, xiahaitao@huawei.com | SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs | 32.405, 32.551, 32.522, 32.526, 32.642, 32.646, 32.762, 32.766 | 54 | 28 |  |  | Tue 22/11/11 | Mon 19/11/12
4454 | 510052 | Rel-11 Charging Management small Enhancements | CH11 | 1 | Rel-11 | S5 | Thu 25/03/10 | Wed 12/12/12 | 100% | - | - | - | - | CH11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | 30.821 | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
4455 | 470045 | Add solutions for Rc - reference point within the Online Charging System (OCS) | CH-Rc | 2 | Rel-11 | S5 | Thu 25/03/10 | Wed 21/09/11 | 100% | SP-110129 | - | Huawei | shan.mingjun@huawei.com | SP#53 completed. Stage 3 (Stage 1 in 22.115). Triggered by Rel-10 TR 32.825 SA5 Study on Rc Reference Point Functionalities and Message Flows (UID_410044) | 32.296, 32.299 | 47 | 24 |  |  | Fri 12/02/10 | Fri 26/08/11
4456 | 510060 | Charging for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Data Bases | PEST-CH | 2 | Rel-11 | S5 | Mon 21/03/11 | Wed 21/09/11 | 100% | SP-110126 | - | Ericsson | patrik.teppo@@ericsson.com | SP#53 completed. Stage 3 | 32.251, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Fri 26/08/11
4457 | 550019 | Unification of Charging session from SIP AS and SRVCC functions in IMS | UCHIMS_AS-SRVCC | 2 | Rel-11 | S5 | Wed 07/03/12 | Wed 12/12/12 | 100% | SP-120042 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#58 completed | 32.260, 32.275, 32.298, 32.299 | 55 | 28 |  |  | Wed 22/02/12 | Wed 05/12/12
4458 | 510029 | Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 1 | Rel-11 | S5,S1,C1 | Wed 27/10/10 | Fri 15/06/12 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115 | - | 51 | 26 |  |  | Tue 22/02/11 | Fri 01/06/12
4459 | 510129 | Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | S1 | Wed 27/10/10 | Wed 21/09/11 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#53 completed under IPXS | 22.115 | 51 | 26 |  |  | Tue 22/02/11 | Fri 07/10/11
4460 | 510229 | Stage 2/3 SA5 part of Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | S5 | Wed 27/10/10 | Wed 07/12/11 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#54 completed | 32.240, 32.260, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Mon 24/10/11
4461 | 520006 | Stage 3 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | C1 | Tue 07/06/11 | Fri 15/06/12 | 100% | CP-110440 | - | Deutsche Telekom | martin.huelsemann@telekom.de] | CP#56 completed | 24.229 | 52 | 27 |  |  | Mon 23/05/11 | Fri 01/06/12
4462 | 480011 | User Data Convergence - Data Model | UDC_DM | 1 | Rel-11 | C4,S1 | Thu 25/03/10 | Fri 07/09/12 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed. SP#48 Stage 1 completed as Rel-10 | - | 48 | 25 |  |  | Wed 26/05/10 | Mon 13/08/12
4463 | 480036 | Stage 1 for UDC Data Model | UDC_DM | 2 | Rel-11 | S1 | Thu 25/03/10 | Wed 21/09/11 | 100% | - | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | SP#53 completed under Rel-10 UDC | 22.101 | 48 | 25 |  |  | Wed 26/05/10 | Mon 19/09/11
4464 | 480111 | TR on User Data Convergence (UDC) Data Model | UDC_DM | 2 | Rel-11 | C4 | Fri 04/06/10 | Fri 07/09/12 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | new 29.935 | 48 | 25 |  |  | Wed 26/05/10 | Tue 25/09/12
4465 | 480211 | User Data Convergence (UDC) Data Model | UDC_DM | 2 | Rel-11 | C4 | Fri 04/06/10 | Fri 07/09/12 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | 29.335 | 48 | 25 |  |  | Wed 26/05/10 | Mon 13/08/12
4466 | 510004 | Definition of the UICC Application for Hosting Party Module | HPM_UICC | 1 | Rel-11 | C6 | Fri 18/03/11 | Fri 15/06/12 | 100% | CP-110289 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#56 completed | 31.102, New 31.104 | 51 | 26 |  |  | Thu 03/03/11 | Tue 25/09/12
4467 | 520007 | Usability improvement of Inter-IMS Network to Network Interface (II-NNI) specification for inter-connection by means of Option Item list | NNI_OI | 1 | Rel-11 | C3 | Tue 07/06/11 | Fri 15/06/12 | 100% | CP-110533 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#56 completed. Stage 3 (No architectural change, specify the list of selectable items related to control plane signalling directly for the same architecture) | 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Fri 01/06/12
4468 | 520008 | enhanced Nodes Restoration for EPC (Stage 2/3) | eNR_EPC | 1 | Rel-11 | C4,C1,C3,IETF | Fri 03/06/11 | Fri 06/12/13 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration UID_490014 | - | 52 | 27 |  |  | Wed 18/05/11 | Thu 28/11/13
4469 | 520108 | CT4 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C4 | Fri 03/06/11 | Fri 07/12/12 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 23.007, 23.008, 23.018, 29.274, 29.275 | 52 | 27 |  |  | Wed 18/05/11 | Tue 20/11/12
4470 | 581001 | (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077) | eNR_EPC | 2 | Rel-11 | C4-IETF | Fri 07/12/12 | Fri 06/12/13 | 100% | CP-120449 | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications) | 58 | 30 |  |  | Sat 24/11/12 | Thu 28/11/13
4471 | 540013 | CT1 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C1 | Fri 02/12/11 | Fri 02/03/12 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#55 completed | 29.118 | 54 | 28 |  |  | Wed 23/11/11 | Wed 05/09/12
4472 | 570009 | CT3 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C3 | Mon 10/09/12 | Fri 07/12/12 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 29.212 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4473 | 520009 | Reference Location Information (Stage 3) | RLI | 1 | Rel-11 | C4,C1 | Fri 03/06/11 | Fri 16/09/11 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11) | - | 52 | 27 |  |  | Wed 18/05/11 | Wed 01/06/11
4474 | 520109 | CT4 part of Reference Location Information (Stage 3) | RLI | 2 | Rel-11 | C4 | Fri 03/06/11 | Fri 03/06/11 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#52 completed | 23.008, 29.228, 29.328, 29.329 | 52 | 27 |  |  | Wed 18/05/11 | Thu 02/06/11
4475 | 520209 | CT1 part of Reference Location Information (Stage 3) | RLI | 2 | Rel-11 | C1 | Fri 03/06/11 | Fri 16/09/11 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed | 24.229 | 52 | 27 |  |  | Wed 18/05/11 | Wed 01/06/11
4476 | 520010 | IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 1 | Rel-11 | C1,C3,IETF | Tue 07/06/11 | Fri 12/09/14 | 99% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | - | 52 | 27 |  |  | Wed 18/05/11 | Thu 28/02/13
4477 | 520110 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 2 | Rel-11 | C1 | Tue 07/06/11 | Fri 07/09/12 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 23.218, 24.229, 24.930 | 52 | 27 |  |  | Wed 18/05/11 | Tue 14/08/12
4478 | 591001 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7315) | IMSProtoc5 | 2 | Rel-11 | C1-IETF | Fri 01/03/13 | Fri 12/09/14 | 100% | CP-110437 | - | Roland Jesske | Roland Jesske | CP#65 completed | RFC 7315 (was draft-drage-sipping-rfc3455bis), draft-mohali-dispatch-originating-cdiv-parameter | 59 | 30 |  |  | Thu 21/02/13 | Tue 02/09/14
4479 | 800113 | (IETF) A P-Served-User Header Field Parameter for Originating CDIV session case in SIP (draft-ietf-sipcore-originating-cdiv-parameter) --> RFC 8498 | IMSProtoc5 | 2 | Rel-11 | C1-IETF | Fri 01/03/13 | Fri 12/09/14 | 100% | CP-110437 |  | Roland Jesske | Roland Jesske | 26/6/19: 25%->100; 23/4/20: 100%->100 |  | 80 | 41 |  |  | Wed 27/06/18 | Thu 23/04/20
4480 | 611002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135) | IMSProtoc5 | 2 | Rel-11 | C1-IETF | Fri 06/09/13 | Fri 13/06/14 | 100% | CP-110437 | - | Roland Jesske | Roland Jesske | CP#64 completed | RFC 7135 (was draft-polk-local-emergency-rph-namespace) | 61 | 31 |  |  | Fri 23/08/13 | Fri 06/06/14
4481 | 520210 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 2 | Rel-11 | C3 | Tue 07/06/11 | Fri 07/09/12 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 29.163, 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Tue 14/08/12
4482 | 581002 | Deleted - (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (avasarala-dispatch-comm-div-notification) | IMSProtoc5 | 2 | Rel-11 | C3-IETF | Fri 07/12/12 | Fri 12/09/14 | 100% | CP-110437 | - | Andrew Allen | Andrew Allen | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 58 | 30 | CP-65 | PCG-33 | Wed 18/05/11 | Tue 02/09/14
4483 | 530003 | Service Identification for RRC Improvements in GERAN (Stage 2/3) | SIRIG | 1 | Rel-11 | S2,C4,C3,G2 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | TSG#57, GP#55 completed. CT defined a generic solution (not only for GERAN) | GERAN | 51 | 27 |  |  | Tue 06/09/11 | Thu 06/09/12
4484 | 560008 | Stage 2 for Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | S2 | Mon 18/06/12 | Fri 07/09/12 | 100% | - | - | - | - | SP#57 completed | 23.060, 23.251 | 56 | 29 |  |  | Mon 18/06/12 | Fri 31/08/12
4485 | 540018 | CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | C4,C3 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | - | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4486 | 540118 | CT4 part of CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 3 | Rel-11 | C4 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | 29.281 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4487 | 550009 | Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 3 | Rel-11 | C3 | Fri 02/03/12 | Fri 15/06/12 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#56 stopped (SA2 decided NO CT3 impact) | 29.212 | 55 | 28 | CP-56 | PCG-29 | Mon 20/02/12 | Fri 20/04/12
4488 | 530103 | GERAN2 part of Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | G2 | Mon 19/09/11 | Fri 31/08/12 | 100% | GP-111876 | - | China Mobile, Huawei | Juan Deng, Yang Zhao | GP#55 completed. GP#51 approved WID | 48.018 | 51 | 27 |  |  | Tue 06/09/11 | Fri 31/08/12
4489 | 530019 | SAE Protocol Development - Phase 2 | SAES2 | 1 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | - | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
4490 | 530119 | SAE Protocol Development (Stage 3) - Phase 2 | SAES2 | 2 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 53 | 27 |  |  | Thu 08/09/11 | Tue 14/08/12
4491 | 530219 | CS Fallback in EPS - Phase 2 | SAES2-CSFB | 2 | Rel-11 | C1 | Fri 16/09/11 | Fri 07/09/12 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 53 | 27 |  |  | Thu 08/09/11 | Tue 14/08/12
4492 | 530020 | GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3) | RT_VGCS_Red | 1 | Rel-11 | C1 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069) | Stage 2/3 | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
4493 | 530120 | CT1 part of GCSMSC and GCR Redundancy for VGCS/VBS | RT_VGCS_Red | 2 | Rel-11 | C1 | Mon 19/09/11 | Fri 07/09/12 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 43.068, 43.069 | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
4494 | 530220 | Deleted - CT4 part of GCSMSC and GCR Redundancy for VGCS/VBS | RT_VGCS_Red | 2 | Rel-11 | C4 | Mon 19/09/11 | Fri 15/06/12 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#56 stopped (no CT4 impact) | 29.002 | 53 | 27 | CP-56 | PCG-29 | Sat 27/08/11 | Tue 25/09/12
4495 | 540015 | Support of RFC 6140 in IMS | GINI | 1 | Rel-11 | C1 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110760 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#57 completed. Stage 3. Support procedures and protocol extensions in RFC6140 "Registration for Multiple Phone Numbers in SIP" to IMS for complex UEs. Ensure co-existence with NGCN IP-PBX registration procedures already defined in IMS. | 24.229 | 54 | 28 |  |  | Tue 22/11/11 | Tue 14/08/12
4496 | 540017 | Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 1 | Rel-11 | C4,C3 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI. | Stage 3 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4497 | 540117 | CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 2 | Rel-11 | C4 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4498 | 540217 | CT3 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 2 | Rel-11 | C3 | Fri 02/12/11 | Fri 07/09/12 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 29.162, 29.163, 29.292 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
4499 | 550007 | Inter-IMS Network to Network Interface (II-NNI) enhancements: SIP timers applicability (Stage 3) | NNI_timers | 1 | Rel-11 | C3 | Fri 02/03/12 | Fri 07/09/12 | 100% | CP-120082 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#57 completed | 29.165 | 55 | 28 |  |  | Wed 22/02/12 | Mon 13/08/12
4500 | 560005 | AT commands for Universal Resource Identifier (URI) support | ATURI | 1 | Rel-11 | C1 | Fri 15/06/12 | Fri 01/03/13 | 100% | CP-120275 | - | Intel | frank.kowalewski@intel.com | CP#59 completed. Define new AT cmd for URI addresses for IMS services (eg VoLTE). 27.007(AT cmd to control MT functions and GSM/UMTS/LTE network services from TE), 27.005(AT commands for SMS). Currently address types for AT cmd based on dialling# | 27.005, 27.007 | 56 | 29 |  |  | Sat 02/06/12 | Sat 16/02/13
4501 | 560006 | PS Additional Number (Stage 3) | PSAN | 1 | Rel-11 | C4 | Fri 15/06/12 | Fri 07/09/12 | 100% | CP-120253 | - | Deutsche Telekom | Yvette.koza@t-mobile.at | CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact) | 23.003, 23.008, 29.002, 29.272, 29.230 | 56 | 29 |  |  | Mon 23/04/12 | Mon 13/08/12
4502 | 560007 | Generic IMS User Group Over Sh | GenUG_Sh | 1 | Rel-11 | C4 | Fri 15/06/12 | Fri 07/09/12 | 100% | CP-120254 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.364 | 56 | 29 |  |  | Sat 02/06/12 | Mon 13/08/12
4503 | 570010 | IMS Operator Determined Call Barring | IODB | 1 | Rel-11 | C1,C4 | Fri 07/09/12 | Fri 14/06/13 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | LS_in C4-121615 GSMA IREG RILTE concluded that TS 22.041 clause 5.4 Stage 1 requirements are not covered by stage 3 specifications | - | 57 | 29 |  |  | Mon 13/08/12 | Thu 06/09/12
4504 | 570110 | CT1 part of IMS Operator Determined Call Barring | IODB | 2 | Rel-11 | C1 | Mon 10/09/12 | Fri 14/06/13 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#60 completed. Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CT decision. | New 24.315 | 57 | 29 |  |  | Mon 13/08/12 | Thu 13/06/13
4505 | 570210 | CT4 part of IMS Operator Determined Call Barring | IODB | 2 | Rel-11 | C4 | Fri 07/09/12 | Tue 12/03/13 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#58 completed | 23.008 , 23.015 , 29.328 , 29.329 , 29.364 | 57 | 29 |  |  | Mon 13/08/12 | Sat 17/11/12
4506 | 570011 | Enhanced T.38 FAX support (Stage 3) | MMTel_T.38_FAX | 1 | Rel-11 | C3,C1,C4 | Thu 06/09/12 | Fri 07/12/12 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed. Linked to Rel-8 Feature: IMS Multimedia Telephony Service (IMS-MMTel) UID_7038. SA1 added FAX stage 1 requirement only in Rel-10 under TEI10 to TS 22.173 (CR#0064) | - | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4507 | 570111 | CT3 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C3 | Fri 07/09/12 | Fri 07/12/12 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 29.163 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4508 | 570211 | CT1 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C1 | Fri 07/09/12 | Fri 07/12/12 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 24.229 | 57 | 29 |  |  | Mon 13/08/12 | Mon 19/11/12
4509 | 570311 | CT4 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C4 | Thu 06/09/12 | Fri 07/09/12 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#57 completed | 29.332 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
4510 | 540016 | Deleted - Enhancement of the Protocols for SMS over SGs (Stage 3) | PROTOC_SMS_SGs | 1 | Rel-11 | C4,C1 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped. Reason: Protocols for SMS over SGs is replaced by the SIMTC SMS in MME solution (as solution not only for MTC user but for general subscribers) | Stage 3 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
4511 | 540116 | Deleted - TR Study on enhancement of protocols for SMS service over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C4 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TR 29.818) | new 29.818 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
4512 | 540216 | Deleted - CT4 part of Enhancement of the Protocols for SMS over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C4 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TS 29.218 Diameter based protocols for SMS service over SGs) | 29.305, new 29.218 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
4513 | 540316 | Deleted - CT1 part of Enhancement of the Protocols for SMS over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C1 | Fri 02/12/11 | Fri 15/06/12 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped | 23.040, 24.011, 43.068 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Wed 13/06/12
4514 | 510001 | Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 1 | Rel-11 | G2,S2,C1 | Fri 04/03/11 | Fri 17/05/13 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001 | GERAN | 49 | 26 |  |  | Fri 04/03/11 | Fri 17/05/13
4515 | 510101 | GERAN part of Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | G2 | Fri 04/03/11 | Fri 17/05/13 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID | 44.018, 44.060, 45.002, 45.008, 48.008, 48.018 | 49 | 26 |  |  | Fri 04/03/11 | Fri 17/05/13
4516 | 510201 | Stage 2 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | S2 | Wed 08/06/11 | Wed 07/03/12 | 100% | SP-110390 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#55 completed | 23.251, 23.272 | 49 | 26 |  |  | Fri 04/03/11 | Tue 06/12/11
4517 | 510301 | CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | C1,C4 | Fri 03/06/11 | Fri 07/12/12 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | - | 49 | 26 |  |  | Sat 02/06/12 | Mon 19/11/12
4518 | 510401 | CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 3 | Rel-11 | C1 | Fri 03/06/11 | Fri 07/12/12 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | 24.008 | 49 | 26 |  |  | Fri 04/03/11 | Mon 19/11/12
4519 | 560004 | CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 3 | Rel-11 | C4 | Wed 13/06/12 | Fri 07/09/12 | 100% | CP-120563 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#57 completed | 23.003 | 54 | 29 |  |  | Sat 02/06/12 | Mon 19/11/12
4520 | 560042 | Stage 2 for Gateway Core Network Sharing for GERAN | Full_MOCN-GERAN-GWCN | 2 | Rel-11 | S2 | Mon 18/06/12 | Wed 06/03/13 | 100% | SP-120268 | - | Vodafone | chris.pudney@vodafone.com | SP#59 completed. (23.251CR0062R2 as TEI11. TS 23.251 specifies both MOCN and GWCN for E-UTRAN and UTRAN, but GWCN is not yet supported on GERAN. Extend Full_MOCN-GERAN to also cover GWCN GERAN | 23.251 | 56 | 29 |  |  | Mon 04/06/12 | Thu 22/11/12
4521 | 540003 | Medium range/local area requirements for multicarrier BTS | MRLA | 1 | Rel-11 | G1 | Fri 25/11/11 | Fri 23/11/12 | 100% | GP-111780 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | GERAN | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
4522 | 540103 | Core part: Medium range/local area requirements for multicarrier BTS | MRLA-Core | 2 | Rel-11 | G1 | Fri 25/11/11 | Fri 23/11/12 | 100% | GP-111899 | - | Ericsson | Eric Nordström | Stage 3. GP#56 completed. GP#52 approved WID | 45.005 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
4523 | 540203 | Perf. part: Medium range/local area requirements for multicarrier BTS | MRLA-Perf | 2 | Rel-11 | G1 | Mon 28/11/11 | Fri 23/11/12 | 100% | GP-111782 | - | Ericsson | Eric Nordström | Test spec. GP#56 completed. GP#52 approved WID | 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
4524 | 550023 | Domain Specific Access Control in GERAN | GDSAC | 1 | Rel-11 | G2 | Mon 05/03/12 | Fri 31/08/12 | 100% | GP-120452 | - | Vodafone | chris.pudney@vodafone.com | GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001) | GERAN 44.018 | 53 | 28 |  |  | Wed 18/04/12 | Fri 31/08/12
4525 | 500020 | Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB | 1 | Rel-11 | R4,R2,R3,R5 | Fri 10/12/10 | Fri 01/03/13 | 100% | RP-111396 | - | Sprint | John.J.Humbert@Sprint.com | Stage 3. Triggered by R4 Rel-10 LTE TR 37.806 Study on Extending 850 MHz (UID_440016) | UTRA, LTE | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
4526 | 500120 | Core part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Core | 2 | Rel-11 | R4,R2,R3 | Fri 10/12/10 | Fri 02/03/12 | 100% | RP-111396 | RP-120075 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141 | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
4527 | 500220 | Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Perf | 2 | Rel-11 | R4 | Fri 10/12/10 | Fri 02/03/12 | 100% | RP-111396 | RP-120076 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141 | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
4528 | 510016 | Test part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-UEConTest | 2 | Rel-11 | R5 | Fri 18/03/11 | Fri 01/03/13 | 100% | RP-110377 | RP-130043 | Sprint | John.J.Humbert@Sprint.com | RP#59 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 51 | 26 |  |  | Thu 10/03/11 | Wed 27/02/13
4529 | 530030 | Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA | 1 | Rel-11 | R3,R2 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-120314 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | Stage 1/2/3 | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4530 | 530130 | Core part: Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA-Core | 2 | Rel-11 | R3,R2 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-120314 | RP-121557 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#58 completed | 25.331, 25.401, 25.410, 25.413, 25.423, 25.433, 36.300, 36.331, 36.413, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4531 | 530033 | Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE | 1 | Rel-11 | R2,R1,R3,R4,R5 | Mon 19/09/11 | Fri 06/12/13 | 100% | RP-121204 | - | MediaTek | Johan Johansson | Stage 2/3 | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4532 | 530133 | Core part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-Core | 2 | Rel-11 | R2,R1,R3,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-121204 | RP-121556 | MediaTek | Johan Johansson | RP#58 completed | 25.133, 25.123, 25.304, 25.331, 25.413, 25.423, 36.133, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320, 36.300 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4533 | 590001 | Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 06/12/13 | 100% | RP-130172 | RP-131447 | NTT DoCoMo | masahiro.tamaoki.eu@nttdocomo.com | RP#62 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 13/08/13
4534 | 530036 | Network Energy Saving for E-UTRAN | Netw_Energy_LTE | 1 | Rel-11 | R3,GP | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120620 | - | China Mobile | yangning@chinamobile.com | Stage 2/3 | LTE, GERAN | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
4535 | 530136 | Core part: Network Energy Saving for E-UTRAN | Netw_Energy_LTE-Core | 2 | Rel-11 | R3 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120620 | RP-121016 | China Mobile | yangning@chinamobile.com | RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well | 25.413, 36.300, 36.413, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
4536 | 570001 | GERAN part: Network Energy Saving for E-UTRAN | - | 2 | Rel-11 | GP | Mon 27/08/12 | Fri 31/08/12 | 100% | GP-121178 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#55 approved WID and completed. Stage 3. ChangES in CP-150RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature | 48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)] | 55 | 29 |  |  | Sat 01/09/12 | Sat 01/09/12
4537 | 530037 | E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR | 1 | Rel-11 | R4,G1 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111383 | - | Ericsson | johan.skold@ericsson.com | Stage 3. GERAN BS RF requirements specs need aligned with RAN4 ongoing Rel-11 Feature UID_530037 E-UTRA medium range and MSR medium range/local area BS class requirements (medBS_class_LTE_MSR) | UTRA, LTE, GERAN | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
4538 | 530137 | Core part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Core | 2 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111383 | RP-121558 | Ericsson | johan.skold@ericsson.com | RP#58 completed. TR 37.809 v200 for Approval | 25.104, 36.104, 37.104, new 37.809 | 53 | 27 |  |  | Thu 15/09/11 | Wed 05/12/12
4539 | 530237 | Perf. part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Perf | 2 | Rel-11 | R4 | Fri 23/09/11 | Fri 07/12/12 | 100% | RP-111383 | RP-121559 | Ericsson | johan.skold@ericsson.com | RP#58 completed | 25.141, 36.141, 37.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4540 | 540002 | GERAN part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-GERAN | 2 | Rel-11 | G1 | Mon 28/11/11 | Fri 23/11/12 | 100% | GP-111779 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | 45.005, 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
4541 | 550015 | RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF | 1 | Rel-11 | R4,G1 | Mon 06/02/12 | Thu 06/03/14 | 100% | RP-120857 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | - | UTRA, LTE, GERAN | 55 | 28 |  |  | Thu 23/02/12 | Tue 04/09/12
4542 | 550115 | Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Core | 2 | Rel-11 | R4,G1 | Mon 06/02/12 | Fri 07/12/12 | 100% | RP-120857 | RP-121985 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#58 completed | 25.104, 25.105, 36.104, 37.104, new 37.812 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/12/12
4543 | 550215 | Perf. part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Perf | 2 | Rel-11 | R4,G1 | Thu 08/03/12 | Thu 06/03/14 | 100% | RP-120857 | RP-140064 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#63 completed | 25.141, 25.142, 36.141, 37.141 | 55 | 28 |  |  | Thu 23/02/12 | Mon 03/03/14
4544 | 560013 | Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1 | 1 | Rel-11 | R3,R2 | Fri 15/06/12 | Fri 07/12/12 | 100% | RP-121427 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2). Compare also Rel-10 WI HNB_HENB_mob_enh RP-110183 | UTRA, LTE | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
4545 | 560113 | Core part: Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1-Core | 2 | Rel-11 | R3,R2 | Fri 15/06/12 | Fri 07/12/12 | 100% | RP-121427 | RP-121563 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423 | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
4546 | 560014 | Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2 | 1 | Rel-11 | R3,R2 | Tue 19/06/12 | Fri 07/12/12 | 100% | RP-121712 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2) | UTRA, LTE | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
4547 | 560114 | Core part: Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2-Core | 2 | Rel-11 | R3,R2 | Tue 19/06/12 | Fri 07/12/12 | 100% | RP-121712 | RP-121564 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Updated WID RP-121147=>RP-121712 | 25.413, 25.467, 25.469, 25.471 | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
4548 | 430011 | Network-Based Positioning Support for LTE | LCS_LTE-NBPS | 1 | Rel-11 | R2,R1,R3,R4 | Thu 05/03/09 | Fri 13/06/14 | 100% | RP-131259 | - | TruePosition | terri.brooks@trueposition.com | - | LTE | 43 | 22 |  |  | Fri 06/03/09 | Tue 04/09/12
4549 | 430111 | Core part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Core | 2 | Rel-11 | R2,R1,R3,R4 | Thu 05/03/09 | Wed 12/06/13 | 100% | RP-131259 | RP-130483 | TruePosition | terri.brooks@trueposition.com | RP#60 completed | 36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new (36.111, 36.456, 36.457, 36.458, 36.459) | 43 | 22 |  |  | Fri 06/03/09 | Thu 29/08/13
4550 | 430211 | Perf. part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Perf | 2 | Rel-11 | R4 | Tue 24/03/09 | Fri 13/06/14 | 100% | RP-131259 | RP-140626 | TruePosition | terri.brooks@trueposition.com | RP#64 completed. TS 36.112v100 for 1-step Approval | 36.111, new 36.112 | 43 | 22 |  |  | Fri 06/03/09 | Wed 11/06/14
4551 | 480026 | Service continuity improvements for MBMS for LTE | MBMS_LTE_SC | 1 | Rel-11 | R2,R3,R5 | Fri 04/06/10 | Thu 06/03/14 | 100% | RP-120258 | - | Huawei | David.Lecompte@huawei.com | - | LTE | 48 | 25 |  |  | Fri 04/06/10 | Fri 13/07/12
4552 | 480126 | Core part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-Core | 2 | Rel-11 | R2,R3 | Fri 04/06/10 | Fri 07/09/12 | 100% | RP-120258 | RP-121001 | Huawei | David.Lecompte@huawei.com | RP#57 completed | 25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445 | 48 | 25 |  |  | Fri 04/06/10 | Thu 06/09/12
4553 | 590002 | Test part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Thu 06/03/14 | 100% | RP-130296 | RP-140074 | Ericsson | leif.mattisson@ericsson.com | RP#63 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Mon 03/03/14
4554 | 510021 | Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | Tue 22/03/11 | Mon 15/12/14 | 100% | RP-120860 | - | China Mobile | ShenXiaodong@chinamobile.com | - | LTE | 51 | 26 |  |  | Mon 14/03/11 | Wed 05/12/12
4555 | 510121 | Core part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Core | 2 | Rel-11 | R1,R2,R3,R4 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-120860 | RP-121986 | China Mobile | ShenXiaodong@chinamobile.com | RP#58 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.321, 36.331, 36.413, 36.423 | 51 | 26 |  |  | Mon 14/03/11 | Wed 05/12/12
4556 | 510221 | Perf. part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Perf | 2 | Rel-11 | R4 | Wed 23/03/11 | Fri 06/12/13 | 100% | RP-120860 | RP-131463 | China Mobile | ShenXiaodong@chinamobile.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Fri 29/11/13
4557 | 600001 | Test part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-UEConTest | 2 | Rel-11 | R5 | Sat 15/06/13 | Mon 15/12/14 | 100% | RP-130649 | RP-141847 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | ¦Stat Rep: RP-141131->RP-141847 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Mon 12/01/15
4558 | 510028 | New Band LTE Downlink FDD 716-728 MHz (Band 29, Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29) | LTE_DL_FDD700 | 1 | Rel-11 | R4 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-110435 | - | AT&T | marc.grant@att.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4559 | 510128 | Core part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Core | 2 | Rel-11 | R4 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-110710 | RP-121604 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4560 | 510228 | Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Perf | 2 | Rel-11 | R4 | Tue 29/03/11 | Fri 07/12/12 | 100% | RP-110435 | RP-121605 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4561 | 510031 | LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA | 1 | Rel-11 | R2,R5 | Fri 18/03/11 | Fri 06/09/13 | 100% | RP-120256 | - | BlackBerry | Gordon Young (gyoung@rim.com) | Stage 2/3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Wed 28/08/13
4562 | 510131 | Core part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-Core | 2 | Rel-11 | R2 | Fri 18/03/11 | Fri 07/12/12 | 100% | RP-120256 | RP-121571 | BlackBerry | Gordon Young (gyoung@rim.com) | RP#58 completed | 36.300, 36.321, 36.331, new 36.822 | 51 | 26 |  |  | Mon 14/03/11 | Thu 29/11/12
4563 | 590003 | Test part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 06/09/13 | 100% | RP-130338 | RP-130946 | BlackBerry | Enikő Sokondár (esokondar@rim.com) | RP#61 completed | 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Wed 28/08/13
4564 | 510032 | LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB | 1 | Rel-11 | R1,R2,R4,R5 | Wed 23/03/11 | Fri 01/03/13 | 100% | RP-120602 | - | NII Holdings | bill.shvodian@nii.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
4565 | 510132 | Core part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Core | 2 | Rel-11 | R1,R2,R4 | Wed 15/06/11 | Fri 07/09/12 | 100% | RP-120602 | RP-120570 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.101, 25.104, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.307, 37.104, 37.113 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
4566 | 510232 | Perf. part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Perf | 2 | Rel-11 | R4 | Wed 23/03/11 | Fri 15/06/12 | 100% | RP-120602 | RP-120571 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.123, 25.133, 25.141, 36.133, 36.141, 37.141 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
4567 | 560010 | Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-UEConTest | 2 | Rel-11 | R5 | Mon 18/06/12 | Fri 01/03/13 | 100% | RP-120603 | RP-130045 | NII Holdings | bill.shvodian@nii.com | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 56 | 29 |  |  | Wed 06/06/12 | Wed 27/02/13
4568 | 520017 | LTE for 700 MHz Digital Dividend | LTE_APAC700 | 1 | Rel-11 | R4,R2,R3,R5 | Tue 07/06/11 | Fri 14/06/13 | 100% | RP-110875 | - | Ericsson | olav.queseth@ericsson.com | Stage 3. Asian Pacific American Caucus (APAC) Asia-Pacific Telecommunity (APT) Wireless Forum | LTE | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
4569 | 520117 | Core part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Core | 2 | Rel-11 | R4,R2,R3 | Tue 07/06/11 | Fri 15/06/12 | 100% | RP-110875 | RP-120572 | Ericsson | olav.queseth@ericsson.com | RP#56 completed. TR 36.820 v100 for Information and Approval | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.113, new 36.820 | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
4570 | 520217 | Perf. part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Perf | 2 | Rel-11 | R4 | Thu 09/06/11 | Fri 15/06/12 | 100% | RP-110875 | RP-120573 | Ericsson | olav.queseth@ericsson.com | RP#56 completed | 36.133, 36.141, 37.141 | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
4571 | 560011 | Test part: LTE for 700 MHz Digital Dividend | LTE_APAC700-UEConTest | 2 | Rel-11 | R5 | Mon 18/06/12 | Fri 14/06/13 | 100% | RP-120600 | RP-130467 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 56 | 29 |  |  | Wed 06/06/12 | Mon 03/06/13
4572 | 520019 | Relays for LTE (part 2) | LTE_Relay2 | 1 | Rel-11 | R4 | Fri 04/12/09 | Fri 14/06/13 | 100% | RP-110914 | - | Ericsson | christian.hoymann@ericsson.com | Continuation of Rel-10 (open RAN4 Core & Perf parts) | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 06/06/11
4573 | 520119 | Core part: Relays for LTE (part 2) | LTE_Relay2-Core | 2 | Rel-11 | R4 | Tue 07/06/11 | Fri 07/09/12 | 100% | RP-110914 | RP-121008 | Ericsson | christian.hoymann@ericsson.com | RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10 | 36.133, new RAN4 (36.116, 36.826) | 52 | 27 |  |  | Fri 03/06/11 | Tue 04/09/12
4574 | 520219 | Perf. part: Relays for LTE (part 2) | LTE_Relay2-Perf | 2 | Rel-11 | R4 | Fri 04/12/09 | Fri 14/06/13 | 100% | RP-110914 | RP-130487 | Ericsson | christian.hoymann@ericsson.com | RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213 | 36.133, new 36.117 (E-UTRA Relay conformance testing) | 46 | 24 |  |  | Mon 30/11/09 | Tue 04/06/13
4575 | 530031 | Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE | 1 | Rel-11 | R2,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111355 | - | China Mobile | Zhenping HU | Stage 2/3 | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4576 | 530131 | Core part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Core | 2 | Rel-11 | R2,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111355 | RP-121573 | China Mobile | Zhenping HU | RP#58 completed | 36.133, 36.300, 36.306, 36.321, 36.331 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4577 | 530231 | Perf. part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Perf | 2 | Rel-11 | R4 | Tue 20/09/11 | Fri 07/12/12 | 100% | RP-111356 | RP-121574 | China Mobile | Zhenping HU | RP#58 completed | 36.133 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4578 | 530032 | Coordinated Multi-Point Operation for LTE | COMP_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | Mon 19/09/11 | Mon 15/12/14 | 100% | RP-111365 | - | Huawei, Samsung | Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com | Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE) | LTE | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
4579 | 530132 | Core part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Core | 2 | Rel-11 | R1,R2,R3,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111365 | RP-121575 | Huawei | david.mazzarese@huawei.com | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4580 | 530232 | Perf. part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Perf | 2 | Rel-11 | R4 | Fri 23/09/11 | Fri 07/12/12 | 100% | RP-111365 | RP-121576 | Huawei | Xinwei Zhi (zhixinwei@huawei.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4581 | 530332 | Core part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Core | 2 | Rel-11 | R1,R2,R3,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111365 | RP-121577 | Samsung | Juho Lee (juho95.lee@samsung.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4582 | 530432 | Perf. part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Perf | 2 | Rel-11 | R4 | Fri 23/09/11 | Fri 06/12/13 | 100% | RP-111365 | RP-131465 | Samsung | xutao.zhou@samsung.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Fri 29/11/13
4583 | 590004 | Test part: Coordinated Multi-Point Operation for LTE | COMP_LTE-UEConTest | 2 | Rel-11 | R5 | Fri 15/03/13 | Mon 15/12/14 | 100% | RP-130376 | RP-141782 | Samsung | Stoyan.Baev@partner.samsung.com |  | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Mon 12/01/15
4584 | 540025 | Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl | 1 | Rel-11 | R1,R2,R4,R5 | Fri 09/12/11 | Fri 12/09/14 | 100% | RP-120871 | - | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | Stage 3. RP#58 Core completed. Triggered by UID_510037 Rel-11 TR 36.871 Study on further Downlink MIMO enhancements for LTE-Advanced (FS_LTE_eDL_MIMO_enh) | LTE | 54 | 28 |  |  | Wed 07/12/11 | Wed 28/11/12
4585 | 540125 | Core part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Core | 2 | Rel-11 | R1,R2,R4 | Fri 09/12/11 | Fri 07/12/12 | 100% | RP-120871 | RP-121579 | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | RP#58 completed | 36.101, 36.211, 36.212, 36.213, 36.331 | 54 | 28 |  |  | Wed 07/12/11 | Wed 28/11/12
4586 | 540225 | Perf. part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Perf | 2 | Rel-11 | R4 | Fri 16/12/11 | Fri 13/06/14 | 100% | RP-120871 | RP-140651 | Alcatel-Lucent | teck.hu@alcatel-lucent.com | RP#64 completed | 36.101, 36.104, 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Wed 11/06/14
4587 | 590005 | Test part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 12/09/14 | 100% | RP-130304 | RP-141256 | Huawei | Xu Kai (xk.xukai@huawei.com) | RP#65 completed | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 09/09/14
4588 | 550012 | Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE | 1 | Rel-11 | R4,R5 | Mon 05/03/12 | Fri 06/09/13 | 100% | RP-120362 | - | Motorola Solutions | xiaowei.jin@motorolasolutions.com | Stage 3 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4589 | 550112 | Core part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-Core | 2 | Rel-11 | R4 | Mon 05/03/12 | Fri 07/12/12 | 100% | RP-120362 | RP-121581 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#58 completed. TR 36.837 v100 for Information and Approval | 36.101, new 36.837 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/12/12
4590 | 590006 | Test part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 06/09/13 | 100% | RP-130169 | RP-130949 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#61 completed | 36.521-1, 36.521-2 | 59 | 30 |  |  | Tue 26/02/13 | Thu 29/08/13
4591 | 550013 | Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej | 1 | Rel-11 | R4,R5 | Mon 05/03/12 | Fri 12/09/14 | 100% | RP-120382 | - | Renesas Mobile | Timo Roman | RP#58 completed. Triggered by FS_enh_perf_UE_LTE. Adds Perf. requirements for demodulation of the already specified PDSCH with the transmission modes defined in Rel-8 to Rel-10 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4592 | 550113 | Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-Perf | 2 | Rel-11 | R4 | Mon 05/03/12 | Fri 07/12/12 | 100% | RP-120382 | RP-121582 | Renesas Mobile | Timo Roman | RP#58 completed | 36.101 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4593 | 600002 | Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-UEConTest | 2 | Rel-11 | R5 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-140491 | RP-141602 | Broadcom | jarkko.hellsten@kolumbus.fi | RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101 | 36.508, 36.521-1, 36.521-2, New 36.904 | 60 | 31 |  |  | Wed 22/05/13 | Sun 07/09/14
4594 | 550014 | Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe | 1 | Rel-11 | R4,R2,R3,R5 | Mon 05/03/12 | Fri 14/06/13 | 100% | RP-120384 | - | China Mobile | Xiaodong Shen | Stage 3. Exists already for 1UL a WI LTE_CA_B3_B5 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 28/02/12
4595 | 550114 | Core part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-Core | 2 | Rel-11 | R4,R2,R3 | Mon 05/03/12 | Fri 07/09/12 | 100% | RP-120384 | RP-121019 | China Mobile | Xiaodong Shen | RP#57 completed | 36.211, 36.213, 36.331, 36.423 | 55 | 28 |  |  | Thu 23/02/12 | Thu 06/09/12
4596 | 590007 | Test part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 14/06/13 | 100% | RP-130305 | RP-130475 | Huawei | Li Xiang (tricia.li@huawei.com) | RP#60 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Tue 04/06/13
4597 | 580158 | Rel-11 LTE Carrier Aggregation | LTE_CA_Rel-11 | 1 | Rel-11 | R1,R2,R3,R4,R5 | Fri 10/12/10 | Fri 12/12/14 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
4598 | 510030 | LTE Carrier Aggregation Enhancements | LTE_CA_enh | 2 | Rel-11 | R1,R2,R3,R4,R5 | Tue 15/03/11 | Fri 12/12/14 | 100% | RP-121999 | - | Nokia | lars.e.lindh@nokia.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
4599 | 510130 | Core part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Core | 3 | Rel-11 | R1,R2,R4,R3 | Tue 22/03/11 | Tue 27/08/13 | 100% | RP-121999 | RP-130059 | Nokia | lars.e.lindh@nokia.com | RP#59 completed. New TR 36.823 v100 for Information and Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new 36.823 | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
4600 | 510230 | Perf. part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Perf | 3 | Rel-11 | R4 | Tue 15/03/11 | Fri 12/12/14 | 100% | RP-121999 | RP-141969 | Nokia | lars.e.lindh@nokia.com | ¦Stat Rep: RP-141377->RP-141969 | 36.101, 36.104, 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Mon 12/01/15
4601 | 600003 | Test part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-UEConTest | 3 | Rel-11 | R5 | Tue 18/06/13 | Fri 12/09/14 | 100% | RP-140619 | RP-141443 | Microsoft | jussi.kuusisto@microsoft.com | SP#65 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Tue 09/09/14
4602 | 570006 | UE Conformance Test Aspects – LTE Advanced Carrier Aggregation of Intra-band contiguous and Inter-band configurations | LTE_CA_intraC_inter_UEConTest | 2 | Rel-11 | R5 | Tue 11/09/12 | Fri 06/12/13 | 100% | RP-121814 | RP-131446 | Nokia | jussi.kuusisto@nokia.com | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1 | 57 | 29 |  |  | Wed 05/09/12 | Fri 07/06/13
4603 | 580258 | Rel-11 inter-band Carrier Aggregation | - | 2 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/12/12 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
4604 | 480023 | LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7 | 3 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/12/12 | 100% | RP-120830 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. In Europe Band 3,7,20 are interesting for LTE and LTE-Advanced deployment. Different CA combinations for these bands are of high priority for Region 1 | LTE | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
4605 | 480123 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7-Core | 4 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/09/12 | 100% | RP-120830 | RP-121022 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
4606 | 480223 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 7 | LTE_CA_B3_B7-Perf | 4 | Rel-11 | R4 | Fri 17/12/10 | Fri 07/12/12 | 100% | RP-120830 | RP-121023 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed | 36.133, 36.141 | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
4607 | 500017 | LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17 | 3 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/12/12 | 100% | RP-121458 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 50 | 26 |  |  | Fri 10/12/10 | Mon 26/11/12
4608 | 500117 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17-Core | 4 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/09/12 | 100% | RP-121458 | RP-121024 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
4609 | 500217 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17 | LTE_CA_B4_B17-Perf | 4 | Rel-11 | R4 | Fri 17/12/10 | Fri 07/12/12 | 100% | RP-121458 | RP-121595 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 50 | 26 |  |  | Fri 10/12/10 | Mon 26/11/12
4610 | 500018 | LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13 | 3 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/12/12 | 100% | RP-120905 | - | Ericsson | christian.bergljung@ericsson.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 50 | 26 |  |  | Fri 10/12/10 | Tue 27/11/12
4611 | 500118 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13-Core | 4 | Rel-11 | R4 | Fri 10/12/10 | Fri 07/09/12 | 100% | RP-120905 | RP-121026 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
4612 | 500218 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 13 | LTE_CA_B4_B13-Perf | 4 | Rel-11 | R4 | Tue 21/12/10 | Fri 07/12/12 | 100% | RP-120905 | RP-121594 | Ericsson | christian.bergljung@ericsson.com | RP#58 completed | 36.101, 36.133, 36.141 | 50 | 26 |  |  | Fri 10/12/10 | Tue 27/11/12
4613 | 510022 | LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12 | 3 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-120877 | - | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4614 | 510122 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12-Core | 4 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-120877 | RP-121592 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4615 | 510222 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 12 | LTE_CA_B4_B12-Perf | 4 | Rel-11 | R4 | Tue 29/03/11 | Fri 07/12/12 | 100% | RP-120877 | RP-121593 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed | 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4616 | 510023 | LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12 | 3 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-120221 | - | US Cellular | sebastian.thalanany@uscellular.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4617 | 510123 | Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12-Core | 4 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 07/12/12 | 100% | RP-120221 | RP-121596 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4618 | 510223 | Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 12 | LTE_CA_B5_B12-Perf | 4 | Rel-11 | R4 | Fri 25/03/11 | Fri 07/12/12 | 100% | RP-120221 | RP-121597 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4619 | 510024 | LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20 | 3 | Rel-11 | R4 | Tue 22/03/11 | Fri 07/09/12 | 100% | RP-120889 | - | Huawei | Steven Chen | Stage 3. RP#57 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
4620 | 510124 | Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20-Core | 4 | Rel-11 | R4 | Tue 22/03/11 | Fri 07/09/12 | 100% | RP-120889 | RP-121032 | Huawei | Steven Chen | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
4621 | 510224 | Perf. part: LTE Advanced Carrier Aggregation of Band 7 and Band 20 | LTE_CA_B7_B20-Perf | 4 | Rel-11 | R4 | Fri 25/03/11 | Fri 07/09/12 | 100% | RP-120889 | RP-121033 | Huawei | Steven Chen | RP#57 completed | 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
4622 | 510025 | LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17 | 3 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/12/12 | 100% | RP-110432 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4623 | 510125 | Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17-Core | 4 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/09/12 | 100% | RP-110432 | RP-121034 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
4624 | 510225 | Perf. part: LTE Advanced Carrier Aggregation of Band 2 and Band 17 | LTE_CA_B2_B17-Perf | 4 | Rel-11 | R4 | Fri 25/03/11 | Fri 07/12/12 | 100% | RP-110432 | RP-121585 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4625 | 510026 | LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5 | 3 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/12/12 | 100% | RP-110433 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4626 | 510126 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5-Core | 4 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/12/12 | 100% | RP-110433 | RP-121757 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Wed 28/11/12
4627 | 510226 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5 | LTE_CA_B4_B5-Perf | 4 | Rel-11 | R4 | Fri 25/03/11 | Fri 07/12/12 | 100% | RP-110433 | RP-121589 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4628 | 510027 | LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17 | 3 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/12/12 | 100% | RP-110434 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4629 | 510127 | Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17-Core | 4 | Rel-11 | R4 | Wed 23/03/11 | Fri 07/12/12 | 100% | RP-110434 | RP-121598 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4630 | 510227 | Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 17 | LTE_CA_B5_B17-Perf | 4 | Rel-11 | R4 | Fri 25/03/11 | Fri 07/12/12 | 100% | RP-110434 | RP-121599 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
4631 | 530023 | LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20 | 3 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120887 | - | Vodafone | tim.frost@vodafone.com | Stage 3. RP#57 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4632 | 530123 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20-Core | 4 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120887 | RP-121046 | Vodafone | tim.frost@vodafone.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4633 | 530223 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 20 | LTE_CA_B3_B20-Perf | 4 | Rel-11 | R4 | Tue 20/09/11 | Fri 07/09/12 | 100% | RP-120887 | RP-121047 | Vodafone | tim.frost@vodafone.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4634 | 530024 | LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20 | 3 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-120888 | - | Vodafone | Luis.Anaya@vodafone.com | Stage 3. RP#58 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4635 | 530124 | Core part: LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20-Core | 4 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-120888 | RP-121600 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4636 | 530224 | Perf. part: LTE Advanced Carrier Aggregation of Band 8 and Band 20 | LTE_CA_B8_B20-Perf | 4 | Rel-11 | R4 | Fri 23/09/11 | Fri 07/12/12 | 100% | RP-120888 | RP-121601 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4637 | 530026 | LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5 | 3 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120899 | - | SK Telecom | Haesung Park | Stage 3. RP#57 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4638 | 530126 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5-Core | 4 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120899 | RP-121042 | SK Telecom | Haesung Park | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4639 | 530226 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 5 | LTE_CA_B3_B5-Perf | 4 | Rel-11 | R4 | Wed 21/09/11 | Fri 07/09/12 | 100% | RP-120899 | RP-121043 | SK Telecom | Haesung Park | RP#57 completed | 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4640 | 530027 | LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7 | 3 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-121152 | - | Rogers Wireless | takwing.wan@rci.rogers.com | Stage 3. RP#58 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4641 | 530127 | Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7-Core | 4 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-121152 | RP-121590 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new generic 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4642 | 530227 | Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 7 | LTE_CA_B4_B7-Perf | 4 | Rel-11 | R4 | Fri 23/09/11 | Fri 07/12/12 | 100% | RP-121152 | RP-121591 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4643 | 540020 | LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18 | 3 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/12/12 | 100% | RP-120898 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#58 completed | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
4644 | 540120 | Core part: LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18-Core | 4 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/12/12 | 100% | RP-120898 | RP-121602 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
4645 | 540220 | Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18 | LTE_CA_B11_B18-Perf | 4 | Rel-11 | R4 | Thu 15/12/11 | Fri 07/12/12 | 100% | RP-120898 | RP-121603 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed | 36.133 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
4646 | 540021 | LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18 | 3 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-120892 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#57 completed | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4647 | 540121 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18-Core | 4 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-120892 | RP-121052 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4648 | 540221 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 18 | LTE_CA_B1_B18-Perf | 4 | Rel-11 | R4 | Tue 13/12/11 | Fri 07/09/12 | 100% | RP-120892 | RP-121053 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4649 | 540022 | LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19 | 3 | Rel-11 | R4,R2 | Mon 12/12/11 | Fri 07/09/12 | 100% | RP-120866 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#56 completed. Updated WID RP-111765=>RP-120866 | LTE | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
4650 | 540122 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19-Core | 4 | Rel-11 | R4,R2 | Mon 05/03/12 | Fri 07/09/12 | 100% | RP-120866 | RP-120552 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
4651 | 540222 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 19 | LTE_CA_B1_B19-Perf | 4 | Rel-11 | R4 | Mon 12/12/11 | Fri 15/06/12 | 100% | RP-120866 | RP-120553 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
4652 | 540023 | LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21 | 3 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/12/12 | 100% | RP-121173 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#57 completed. Updated WID RP-111764=>RP-121173 | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4653 | 540123 | Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21-Core | 4 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-121173 | RP-121054 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4654 | 540223 | Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21 | LTE_CA_B1_B21-Perf | 4 | Rel-11 | R4 | Tue 13/12/11 | Fri 07/12/12 | 100% | RP-121173 | RP-121055 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4655 | 550018 | LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8 | 3 | Rel-11 | R4 | Mon 05/03/12 | Fri 07/12/12 | 100% | RP-121162 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Stage 3. RP#58 completed | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4656 | 550118 | Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8-Core | 4 | Rel-11 | R4 | Mon 05/03/12 | Fri 07/12/12 | 100% | RP-121162 | RP-121586 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic 36.850 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4657 | 550218 | Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8 | LTE_CA_B3_B8-Perf | 4 | Rel-11 | R4 | Tue 06/03/12 | Fri 07/12/12 | 100% | RP-121162 | RP-121587 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed | 36.133, 36.141 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
4658 | 580358 | Rel-11 intra-band Carrier Aggregation | - | 2 | Rel-11 | RP | Tue 07/06/11 | Fri 07/09/12 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
4659 | 520015 | LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38 | 3 | Rel-11 | R4 | Tue 07/06/11 | Fri 07/09/12 | 100% | RP-110862 | - | Huawei | ronnie.zhang@huawei.com | Stage 3. RP#57 completed. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
4660 | 520115 | Core part: LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38-Core | 4 | Rel-11 | R4 | Tue 07/06/11 | Fri 07/09/12 | 100% | RP-110862 | RP-121060 | Huawei | ronnie.zhang@huawei.com | RP#57 completed. TR 36.830 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-38 [instead of 36.830] | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
4661 | 520215 | Perf. part: LTE Advanced Carrier Aggregation in Band 38 | LTE_CA_B38-Perf | 4 | Rel-11 | R4 | Wed 08/06/11 | Fri 07/09/12 | 100% | RP-110862 | RP-121061 | Huawei | ronnie.zhang@huawei.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
4662 | 520016 | LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41 | 3 | Rel-11 | R4 | Tue 07/06/11 | Fri 02/03/12 | 100% | RP-120249 | - | Clearwire | michael.hart@clearwire.com | RP#55 completed. WI only covers intra-band contiguous and not non-contiguous aspects. | LTE | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
4663 | 520116 | Core part: LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41-Core | 4 | Rel-11 | R4 | Tue 07/06/11 | Fri 02/03/12 | 100% | RP-120249 | RP-120126 | Clearwire | michael.hart@clearwire.com | RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new 36.833-1-41 [instead of 36.827] | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
4664 | 520216 | Perf. part: LTE Advanced Carrier Aggregation in Band 41 | LTE_CA_B41-Perf | 4 | Rel-11 | R4 | Tue 07/06/11 | Fri 02/03/12 | 100% | RP-120249 | RP-120127 | Clearwire | michael.hart@clearwire.com | RP#55 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
4665 | 530028 | LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7 | 3 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-121193 | - | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | Stage 3. RP#57 completed. Updated WID RP-111356=>RP-121193. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4666 | 530128 | Core part: LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7-Core | 4 | Rel-11 | R4 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-121193 | RP-121062 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed. TR 36.831 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-07 [instead of 36.831] | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4667 | 530228 | Perf. part: LTE Advanced Carrier Aggregation in Band 7 | LTE_CA_B7-Perf | 4 | Rel-11 | R4 | Tue 20/09/11 | Fri 07/09/12 | 100% | RP-121193 | RP-121063 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
4668 | 450016 | UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest | 1 | Rel-11 | R4,R5 | Fri 18/09/09 | Thu 15/09/16 | 100% | RP-111381 | - | CATR | Guo Lin (guolin@emcite.com) | - | UTRA | 45 | 23 |  |  | Tue 15/09/09 | Sat 17/09/11
4669 | 450116 | Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-Core | 2 | Rel-11 | R4 | Fri 18/09/09 | Fri 09/12/11 | 100% | RP-111381 | RP-111456 | CATR | Guo Lin (guolin@emcite.com) | RP#54 completed | 25.144, 25.914, 34.114 | 45 | 23 |  |  | Tue 15/09/09 | Tue 29/11/11
4670 | 520011 | Test part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-UEConTest | 2 | Rel-11 | R5 | Wed 15/06/11 | Thu 15/09/16 | 100% | RP-110629 | RP-151187 | ZTE | carolyn.tayl@zte.com.cn | 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: Stat Rep: RP-141846->RP-150068 03/07/15: Stat Rep: RP-150068->RP-150603 29/09/15: Stat Rep: RP-150603->RP-151187 | 34.114 | 52 | 27 |  |  | Mon 23/05/11 | Mon 26/09/16
4671 | 500019 | Eight carrier HSDPA | 8C_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | Wed 15/09/10 | Fri 07/12/12 | 100% | RP-101419 | - | Ericsson | johan.hultell@ericsson.com | Stage 3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
4672 | 500119 | Core part: Eight carrier HSDPA | 8C_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | Wed 15/09/10 | Fri 15/06/12 | 100% | RP-101419 | RP-120971 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
4673 | 500219 | Perf. part: Eight carrier HSDPA | 8C_HSDPA-Perf | 2 | Rel-11 | R4 | Wed 15/12/10 | Fri 07/12/12 | 100% | RP-101419 | RP-120972 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.141 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
4674 | 500021 | UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc | 1 | Rel-11 | R4,R5 | Fri 10/12/10 | Fri 02/03/12 | 100% | RP-111244 | - | China Mobile | Li Nan (linan@chinamobile.com) | Stage 3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Mon 12/09/11
4675 | 500121 | Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-Perf | 2 | Rel-11 | R4 | Fri 10/12/10 | Fri 16/09/11 | 100% | RP-111244 | RP-110996 | China Mobile | Li Nan (linan@chinamobile.com) | RP#53 completed. TR 25.873v100 for Approval | 25.102, new 25.873 | 50 | 26 |  |  | Fri 10/12/10 | Mon 12/09/11
4676 | 530038 | Test part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-UEConTest | 2 | Rel-11 | R5 | Mon 19/09/11 | Fri 02/03/12 | 100% | RP-111181 | RP-120052 | China Mobile | Ma Shuai (mashuai@chinamobile.com) | RP#55 completed | 34.108, 34.122 | 53 | 27 |  |  | Tue 06/09/11 | Thu 23/02/12
4677 | 500022 | Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv | 1 | Rel-11 | R1,R4,R2,R3,R5 | Fri 10/12/10 | Fri 13/06/14 | 100% | RP-120367 | - | Huawei | zongjie.wang@huawei.com | Stage 2/3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Tue 28/02/12
4678 | 500122 | Core part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Core | 2 | Rel-11 | R1,R4,R2,R3 | Fri 10/12/10 | Fri 07/12/12 | 100% | RP-120367 | RP-121542 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
4679 | 500222 | Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Perf | 2 | Rel-11 | R4 | Tue 14/12/10 | Fri 06/09/13 | 100% | RP-120367 | RP-130477 | Huawei | zongjie.wang@huawei.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 50 | 26 |  |  | Fri 10/12/10 | Fri 30/08/13
4680 | 500322 | Core part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Core | 2 | Rel-11 | R4,R1,R2,R3 | Fri 10/12/10 | Fri 07/12/12 | 100% | RP-120367 | RP-121544 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
4681 | 500422 | Perf. part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Perf | 2 | Rel-11 | R4 | Tue 14/12/10 | Fri 07/12/12 | 100% | RP-120367 | RP-121545 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
4682 | 590008 | Test part: Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv-UEConTest | 2 | Rel-11 | R5 | Mon 04/03/13 | Fri 13/06/14 | 100% | RP-130351 | RP-140767 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | RP#64 completed | 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 10/06/14
4683 | 510018 | Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config | 1 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 15/06/12 | 100% | RP-110308 | - | Telus Communications | jorge.delrio@telus.com | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Wed 01/06/11
4684 | 510118 | Core part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Core | 2 | Rel-11 | R4,R2 | Tue 22/03/11 | Fri 09/12/11 | 100% | RP-110308 | RP-111463 | Telus Communications | jorge.delrio@telus.com | RP#54 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new 25.327 | 51 | 26 |  |  | Mon 14/03/11 | Wed 07/12/11
4685 | 510218 | Perf. part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Perf | 2 | Rel-11 | R4 | Thu 24/03/11 | Fri 15/06/12 | 100% | RP-110308 | RP-120475 | Telus Communications | jorge.delrio@telus.com | RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new 25.327 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
4686 | 510019 | Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA | 1 | Rel-11 | R4,R2,R3 | Wed 23/03/11 | Fri 01/03/13 | 100% | RP-110416 | - | Ericsson | muhammad.kazmi@ericsson.com | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
4687 | 510119 | Core part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Core | 2 | Rel-11 | R4,R2,R3 | Wed 15/06/11 | Fri 07/09/12 | 100% | RP-110416 | RP-120842 | Ericsson | muhammad.kazmi@ericsson.com | RP#56 completed | 25.101, 25.104, 25.133, 25.331, 25.423, 25.433 | 51 | 26 |  |  | Mon 14/03/11 | Sat 16/06/12
4688 | 510219 | Perf. part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Perf | 2 | Rel-11 | R4 | Wed 23/03/11 | Fri 01/03/13 | 100% | RP-110416 | RP-130049 | Ericsson | muhammad.kazmi@ericsson.com | RP#59 completed | 25.101, 25.104, 25.133, 25.141 | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
4689 | 510020 | Further Enhancements to CELL_FACH | Cell_FACH_enh | 1 | Rel-11 | R1,R2,R3,R4,R5 | Fri 18/03/11 | Fri 13/03/15 | 100% | RP-111321 | - | Qualcomm | Ravi Agarwal | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Fri 16/09/11
4690 | 510120 | Core part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Core | 2 | Rel-11 | R2,R1,R3,R4 | Fri 18/03/11 | Fri 07/12/12 | 100% | RP-111321 | RP-121547 | Qualcomm | Ravi Agarwal | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.433 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
4691 | 510220 | Perf. part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Perf | 2 | Rel-11 | R4 | Thu 24/03/11 | Fri 06/12/13 | 100% | RP-111321 | RP-131459 | Qualcomm | Heechoon Lee (heechoon@qti.qualcomm.com) | RP#62 completed | 25.101, 25.104, 25.133, 25.141 | 51 | 26 |  |  | Mon 14/03/11 | Fri 29/11/13
4692 | 600004 | Test part: Further Enhancements to CELL_FACH | Cell_FACH_enh-UEConTest | 2 | Rel-11 | R5 | Sat 15/06/13 | Fri 13/03/15 | 100% | RP-130644 | RP-150132 | Ericsson | leif.mattisson@ericsson.com | ¦Stat Rep: RP-141164->RP-141770 1st Apr 15: Compl:92%->100% 1st Apr 15: Stat Rep: RP-141770->RP-150132 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Wed 01/04/15
4693 | 530034 | HSDPA Multiflow Data Transmission | HSDPA_MFTX | 1 | Rel-11 | R2,R1,R3,R4,R5 | Mon 19/09/11 | Fri 13/03/15 | 100% | RP-111375 | - | Nokia Siemens Networks | Alexander Sayenko | Stage 2,3 | UTRA | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
4694 | 530134 | Core part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Core | 2 | Rel-11 | R2,R1,R3,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111375 | RP-121551 | Nokia Siemens Networks | Alexander Sayenko | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.214, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4695 | 530234 | Perf. part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Perf | 2 | Rel-11 | R4 | Tue 20/09/11 | Fri 06/09/13 | 100% | RP-111375 | RP-130959 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 53 | 27 |  |  | Thu 15/09/11 | Thu 29/08/13
4696 | 620016 | Test part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-UEConTest | 2 | Rel-11 | R5 | Sun 15/12/13 | Fri 13/03/15 | 100% | RP-131692 | RP-150126 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | ¦Stat Rep: RP-141136->RP-141961 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141961->RP-150126 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 62 | 32 |  |  | Mon 25/11/13 | Wed 01/04/15
4697 | 530035 | Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | Mon 19/09/11 | Fri 06/12/13 | 100% | RP-111393 | - | Ericsson | johan.hultell@ericsson.com | Stage 3 | UTRA | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4698 | 530135 | Core part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-111393 | RP-121549 | Ericsson | johan.hultell@ericsson.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
4699 | 530235 | Perf. part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Perf | 2 | Rel-11 | R4 | Wed 21/09/11 | Fri 06/12/13 | 100% | RP-111393 | RP-131460 | Ericsson | johan.hultell@ericsson.com | RP#62 completed | 25.101, 25.104, 25.133, 25.141 | 53 | 27 |  |  | Thu 15/09/11 | Fri 29/11/13
4700 | 540009 | MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA | 1 | Rel-11 | R1,R2,R3,R4 | Fri 09/12/11 | Fri 06/09/13 | 100% | RP-121794 | - | Nokia Siemens Networks | Karri Ranta-aho | Specified UE and BS performance requirements for uplink MIMO together with QPSK and 16QAM modulations for E-DCH/HSUPA. 64QAM is for future releases | UTRA | 54 | 28 |  |  | Wed 07/12/11 | Wed 27/02/13
4701 | 540109 | Core part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | Fri 09/12/11 | Fri 07/12/12 | 100% | RP-121794 | RP-121554 | Nokia Siemens Networks | Karri Ranta-aho | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 25.423, 25.433, 26.306 | 54 | 28 |  |  | Wed 07/12/11 | Wed 27/02/13
4702 | 540209 | Perf. part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Perf | 2 | Rel-11 | R4 | Tue 13/12/11 | Fri 06/09/13 | 100% | RP-121794 | RP-130960 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 54 | 28 |  |  | Wed 07/12/11 | Thu 29/08/13
4703 | 540024 | HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC | 1 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-111746 | - | Ericsson | muhammad.kazmi@ericsson.com | Stage 3 | UTRA | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4704 | 540124 | Core part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Core | 2 | Rel-11 | R4,R2 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-111746 | RP-120987 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new 25.327 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4705 | 540224 | Perf. part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Perf | 2 | Rel-11 | R4 | Fri 09/12/11 | Fri 07/09/12 | 100% | RP-111746 | RP-120988 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed | 25.101, 25.104, 25.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
4706 | 620015 | Split TTCN Test Models for IMS testing in TS 34.229-3 | IMS-CCR_Test2 | 1 | Rel-11 | R5 | Mon 09/12/13 | Fri 12/09/14 | 100% | RP-140440 | RP-141155 | Spirent | richard.catmur@spirent.com | SP#65 completed. TS 34.229-4 for Approval. Split out of old TS 34.229-3 a new TS 34.229-4 | 34.229-3, New 34.229-4 | 62 | 32 |  |  | Mon 25/11/13 | Tue 09/09/14
4707 | 480004 | (Small) Technical Enhancements and Improvements for Rel-11 | TEI11 | 1 | Rel-11 | SP,CP,RP,GP | Fri 18/06/10 | Thu 20/09/12 | 100% | - | - | - | - | SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs# | - | 48 | 25 |  |  | Tue 02/06/09 | Mon 13/12/10
4708 | 560001 | Test - (Small) Technical Enhancements and Improvements for Rel-11 | TEI11_Test | 1 | Rel-11 | R5,G3new | Fri 15/06/12 | Wed 11/12/13 | 100% | - | - | - | - | - | - | 56 | 29 |  |  | Wed 13/06/12 | Wed 13/06/12
4709 | 571004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-11 (RFC 7077) | TEI11_IETF | 1 | Rel-11 | C4-IETF | Fri 07/09/12 | Fri 06/12/13 | 100% | - | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications) | 57 | 29 | - |  | Mon 03/09/12 | Thu 28/11/13
4710 | 0 | Release 11 Studies | - | 1 | Rel-11 | SP,CP,GP,RP | Thu 10/12/09 | Thu 10/12/09 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 03/04/12
4711 | 450047 | Study on IMS based Peer-to-Peer Content Distribution Services | FS_IMS_P2P | 1 | Rel-11 | S1,S2 | Fri 11/09/09 | Thu 10/06/10 | 100% | SP-090491 | - | China Mobile | Li Gang (ligangyf@chinamobile.com) | SP#48 completed. 3/3/15: start date corrected (was 05/09) | 22.906 | 45 | 23 |  |  | Mon 21/09/09 | Tue 03/03/15
4712 | 460024 | Study on Non Voice Emergency Services | FS_NOVES | 1 | Rel-11 | S1 | Thu 10/12/09 | Wed 21/09/11 | 100% | SP-090897 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed. Spin-off Feature UID_500030 Non Voice Emergency Services (NOVES) | 22.871 | 46 | 24 |  |  | Sun 06/12/09 | Wed 24/08/11
4713 | 480033 | Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX | FS_VINE | 1 | Rel-11 | S1,S2 | Thu 23/09/10 | Wed 23/03/11 | 100% | SP-100411 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices | 22.809 | 48 | 25 |  |  | Sun 06/06/10 | Mon 06/06/11
4714 | 490033 | Study on IMS Network-Independent Public User Identities | FS_INIPUI | 1 | Rel-11 | S1 | Thu 23/09/10 | Wed 08/06/11 | 100% | SP-100652 | - | Vodafone | mona.mustapha@vodafone.com | SP#52 completed | 22.894 | 49 | 25 |  |  | Tue 21/09/10 | Wed 18/05/11
4715 | 410041 | Study on IMS Evolution | FS_eIMS | 1 | Rel-11 | S2 | Thu 18/09/08 | Wed 14/12/11 | 100% | SP-100360 | - | China Mobile | Li Gang (ligangyf@chinamobile.com), Yu Qing (yuqing@chinamobile.com) | SP#54 completed | 23.812 | 41 | 21 |  |  | Mon 15/09/08 | Mon 28/11/11
4716 | 440047 | Study on Policy solutions and enhancements | FS_PP | 1 | Rel-11 | S2,S1 | Fri 12/06/09 | Fri 10/06/11 | 100% | SP-090895 | - | AT&T | farooq.bari@att.com | SP#52 completed. 3/3/15: start and finish dates corrected (was start on Jan-00, ends on Jan-02) | 23.813 | 44 | 23 |  |  | Sun 31/05/09 | Tue 03/03/15
4717 | 440048 | Study on IPv6 Migration | FS_IP6M | 1 | Rel-11 | S2 | Thu 04/06/09 | Wed 08/06/11 | 100% | SP-090362 | - | China Mobile | Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com) | SP#52 completed | 23.975 | 44 | 23 |  |  | Sun 31/05/09 | Thu 26/05/11
4718 | 460030 | Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | FS_rSRVCC | 1 | Rel-11 | S2 | Thu 10/12/09 | Wed 14/12/11 | 100% | SP-090806 | - | Orange | delphin.barankanira@orange-ftgroup.com | SP#54 completed. Study on "reverse direction" from UTRAN/GERAN to E-UTRAN/HSPA (Rel-8 SRVCC was in the other direction E-UTRAN/HSPA to GERAN/UTRAN) | 23.885 | 46 | 24 |  |  | Sun 06/12/09 | Sun 04/03/12
4719 | 510044 | Study on Roaming Architecture for Voice over IMS with Local Breakout | FS_RAVEL | 1 | Rel-11 | S2 | Wed 23/03/11 | Wed 14/12/11 | 100% | SP-110087 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed. Linked to Rel-11 OSCAR (Optimized Service Charging and Allocation of ResourcES in CP-150IMS whilst Roaming) UID_490032. Related to LBO/home routing decision | 23.85 | 51 | 26 |  |  | Mon 21/02/11 | Mon 28/11/11
4720 | 380084 | Study on UTRAN key management enhancements | FS_UKM | 1 | Rel-11 | S3 | Thu 20/12/07 | Wed 07/03/12 | 100% | SP-090283 | - | Ericsson | karl.norrman@ericsson.com | SP#55 completed | 33.859 | 38 | 21 |  |  | Thu 20/12/07 | Tue 20/11/12
4721 | 480048 | Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest | FS_SSO_APS | 1 | Rel-11 | S3 | Thu 10/06/10 | Wed 20/06/12 | 100% | SP-100639 | - | Nokia | Silke.Holtmanns@nokia.com | SP#56 completed. SP#55 TR 33.914v200 approved (converted 33.804). Study reuse of non-UICC credentials (in particular SIP Digest) to provide security for access to applications. Provide reference material for IMS based non-UICC based SSO to applications | 33.914 converted to 33.804 | 48 | 25 |  |  | Mon 07/06/10 | Wed 13/06/12
4722 | 520036 | Study on Mobile 3D Video Coding | FS_M3DVC | 1 | Rel-11 | S4 | Wed 08/06/11 | Wed 20/06/12 | 100% | SP-110310 | - | Orange | gilles.teniou@orange-ftgroup.com | SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS | 26.905 | 52 | 27 |  |  | Thu 26/05/11 | Mon 20/08/12
4723 | 480047 | Study on Management of Converged Networks | FS_ManCon | 1 | Rel-11 | S5 | Thu 10/06/10 | Wed 12/09/12 | 100% | SP-100377 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@nsn.com) | SP#57 completed. TR 32.833v200 for Approval | 32.833 | 48 | 25 |  |  | Wed 26/05/10 | Thu 30/08/12
4724 | 490039 | Study on User Data Convergence (UDC) information model handling and provisioning: Example Use Cases | FS_UDC_AppUseCase | 1 | Rel-11 | S5 | Thu 23/09/10 | Wed 14/12/11 | 100% | SP-110127 | - | Alcatel-Lucent | Nick Mazzarella (njmazzarella@alcatel-lucent.com) | SP#54 completed | 32.901 | 49 | 25 |  |  | Fri 03/09/10 | Mon 02/04/12
4725 | 510045 | Study on OAM aspects of inter-RAT Energy Saving | FS_OAM_ES_iRAT | 1 | Rel-11 | S5 | Wed 23/03/11 | Wed 14/12/11 | 100% | SP-110138 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES) | 32.834 | 51 | 26 |  |  | Wed 09/03/11 | Mon 02/04/12
4726 | 480015 | Study on impacts on UE-Core Network signalling from Energy Saving | FS_UE-CN_ES | 1 | Rel-11 | C1 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-100330 | - | NEC | gottfried.punz@nw.neclab.eu | CP#52 completed. Linked to SA5 UID_430044 (FS_OAM-ESM) & UID_470037 (OAM-ES), RAN3 UID_470015 (FS_Energy_LTE), RAN1 UID_460016 (FS_Energy_UMTS) | 24.826 | 48 | 25 |  |  | Sat 29/05/10 | Mon 23/05/11
4727 | 490014 | Study on EPC Nodes Restoration | FS_EPC_NR | 1 | Rel-11 | C4 | Fri 17/09/10 | Fri 07/12/12 | 100% | CP-100700 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed. Continue work in Rel-11 especially to cover handling of Idle mode Signalling Reduction (ISR). Linked to SA2 UID_490036 Study on Core Network Overload solutions | 23.857 | 49 | 25 |  |  | Wed 01/09/10 | Wed 14/11/12
4728 | 480003 | Study on Signal Precoding enhancements for EGPRS2 DL | FS_SPEED | 1 | Rel-11 | G1,G2 | Fri 03/09/10 | Fri 02/03/12 | 100% | GP-111281 | - | Ericsson | marten.sundberg@ericsson.com | GP#53 completed (03/12). GP#46 approved WID. | GERAN 45.860 | 46 | 25 |  |  | Thu 27/05/10 | Fri 02/03/12
4729 | 470014 | Study on Coordinated Multi-Point operation for LTE | FS_CoMP_LTE | 1 | Rel-11 | R1,R2,R3 | Fri 10/12/10 | Fri 16/09/11 | 100% | RP-101425 | RP-111343 | Samsung | bruno.clerckx@samsung.com | RP#53 completed | LTE 36.819 | 47 | 24 |  |  | Fri 19/03/10 | Fri 27/05/11
4730 | 480028 | Study on Signalling and procedure for interference avoidance for in-device coexistence | FS_SPIA_IDC | 1 | Rel-11 | R2,R4 | Fri 04/06/10 | Fri 16/09/11 | 100% | RP-100671 | RP-111057 | China Mobile | Zhenping Hu (huzhenping@chinamobile.com) | RP#53 completed. Studied coexistence scenario of LTE and Industrial, Scientific and Medical (ISM) Radio within the same device working in adjacent frequencies | LTE 36.816 | 48 | 25 |  |  | Tue 01/06/10 | Mon 12/09/11
4731 | 510034 | Study on HetNet mobility enhancements for LTE | FS_HetNet_eMOB_LTE | 1 | Rel-11 | R2,R1,R3,R4 | Fri 18/03/11 | Fri 07/09/12 | 100% | RP-110709 | RP-121085 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | RP#57 completed. TR 36.839 v100 for Information & Approval | LTE 36.839 | 51 | 26 |  |  | Mon 21/03/11 | Mon 03/09/12
4732 | 510037 | Study on further Downlink MIMO enhancements for LTE-Advanced | FS_LTE_eDL_MIMO_enh | 1 | Rel-11 | R1 | Fri 18/03/11 | Fri 09/12/11 | 100% | RP-111366 | RP-111550 | Alcatel-Lucent | federico.boccardi@alcatel-lucent.com | RP#54 completed | LTE 36.871 | 51 | 26 |  |  | Mon 21/03/11 | Thu 08/12/11
4733 | 510039 | Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | FS_LTE_TDD_eIMTA | 1 | Rel-11 | R1,R4 | Tue 22/03/11 | Fri 15/06/12 | 100% | RP-110450 | RP-120587 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#56 completed. TR 36.828 for Information and Approval | LTE 36.828 | 51 | 26 |  |  | Mon 21/03/11 | Sat 09/06/12
4734 | 530053 | Study on LTE Coverage Enhancements | FS_Cov_Enh_LTE | 1 | Rel-11 | R1,R2 | Mon 19/09/11 | Fri 15/06/12 | 100% | RP-120225 | RP-120589 | China Telecom | Peng Chen (chenpeng@ctbri.com.cn) | RP#56 completed. TR 36.824 v200 for Approval | LTE 36.824 | 53 | 27 |  |  | Mon 19/09/11 | Sat 09/06/12
4735 | 530055 | Study on Enhanced performance requirement for LTE UE | FS_enh_perf_UE_LTE | 1 | Rel-11 | R4,R1 | Mon 19/09/11 | Fri 02/03/12 | 100% | RP-111378 | RP-120167 | NTT DoCoMo | Yuta Sagae | RP#55 completed. TR 36.829 v100 for Information + Approval | LTE 36.829 | 53 | 27 |  |  | Mon 19/09/11 | Mon 27/02/12
4736 | 550022 | Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology | FS_LTE_OTA | 1 | Rel-11 | R4 | Mon 05/03/12 | Fri 07/09/12 | 100% | RP-120412 | RP-121083 | CATR | Xudong An (anxudong@emcite.com) | RP#57 completed | LTE 25.914, New 37.902 | 55 | 28 |  |  | Thu 23/02/12 | Mon 03/09/12
4737 | 430020 | Study on Measurement of Radiated Performance for MIMO and multi-antenna reception for HSPA and LTE terminals | FS_HSPA_LTE_measRP_MIMO_multi-antenna | 1 | Rel-11 | R4 | Fri 06/03/09 | Fri 02/03/12 | 100% | RP-111754 | RP-120154 | Vodafone | Tim.frost@vodafone.com | RP#55 completed. TR 37.976 v200 for Approval | UTRA, LTE 37.976 | 43 | 22 |  |  | Fri 06/03/09 | Thu 23/02/12
4738 | 440016 | Study on Extending 850 MHz | FS_e850 | 1 | Rel-11 | R4 | Sat 30/05/09 | Fri 07/09/12 | 100% | RP-090666 | RP-121080 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed. TR 37.806 v200 for Approval | UTRA, LTE 37.806 | 44 | 23 |  |  | Tue 26/05/09 | Tue 04/09/12
4739 | 450015 | Study on RAN improvements for Machine-Type Communications | FS_NIMTC_RAN | 1 | Rel-11 | R2,R1,R3,R4 | Fri 18/09/09 | Fri 16/09/11 | 100% | RP-100330 | RP-111052 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#53 completed. TR 37.868v100 for Approval (No WID change: RAN overload only). Triggered by TR 22.868 Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) UID_7027 and Rel-10 NIMTC UID_410030 | UTRA, LTE 37.868 | 45 | 23 |  |  | Tue 15/09/09 | Tue 06/09/11
4740 | 500002 | Study on UE Application Layer Data Throughput Performance | FS_UE_App_Data_Perf | 1 | Rel-11 | R5,R4 | Thu 16/09/10 | Fri 16/09/11 | 100% | RP-101422 | RP-111543 | Spirent | ron.borsato@spirent.com | RP#54 completed | UTRA, LTE 37.901 | 50 | 26 |  |  | Wed 08/12/10 | Tue 29/11/11
4741 | 510036 | Study on further enhancements for HNB and HeNB | FS_EHNB_enh | 1 | Rel-11 | R3,R2 | Fri 18/03/11 | Fri 15/06/12 | 100% | RP-120373 | RP-120579 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#56 completed. TR 37.803 v200 for Approval | UTRA, LTE 37.803 | 51 | 26 |  |  | Mon 21/03/11 | Sat 09/06/12
4742 | 510038 | Study on Interference analysis between 800~900 MHz bands | FS_B800_B900_Interf_LTE | 1 | Rel-11 | R4 | Wed 23/03/11 | Fri 15/06/12 | 100% | RP-111752 | RP-120586 | LG Uplus | Koo Yeon Sang (yskoo@lguplus.co.kr) | RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 | UTRA, LTE impac37.804 | 51 | 26 |  |  | Mon 21/03/11 | Wed 06/06/12
4743 | 520018 | Study on UMTS/LTE in 900 MHz band (Japan, Korea) | FS_UTRA_LTE_900MHz | 1 | Rel-11 | R4 | Tue 07/06/11 | Fri 15/06/12 | 100% | RP-120617 | RP-120580 | NTT DoCoMo | Masahiro Fujii (fujiima@nttdocomo.co.jp) | RP#56 completed. Updated WID RP-111751=>RP-120617. TR 37.804 v100 for Information and Approval. Linked to Study on Interference analysis between 800~900 MHz bands UID_510038 | UTRA, LTE 37.804 | 52 | 27 |  |  | Fri 27/05/11 | Wed 06/06/12
4744 | 500014 | Study on Uplink MIMO | FS_UTRA_UL_MIMO | 1 | Rel-11 | R1 | Fri 10/12/10 | Fri 16/09/11 | 100% | RP-101432 | RP-111048 | Qualcomm | Sharad Sambhwani | RP#53 completed (1-step Approval) | UTRA 25.871 | 50 | 26 |  |  | Wed 08/12/10 | Fri 02/09/11
4745 | 500015 | Study on HSDPA Multipoint Transmission | FS_HSDPA_MP_TX | 1 | Rel-11 | R1,R2,R3 | Fri 10/12/10 | Fri 16/09/11 | 100% | RP-101439 | RP-111049 | Nokia Siemens Networks | karri.ranta-aho@nsn.com | RP#53 completed | UTRA 25.872 | 50 | 26 |  |  | Wed 08/12/10 | Fri 09/09/11
4746 | 530057 | Study on UE Over The Air (OTA) test method with Head and Hand Phantoms | FS_OTA_phantoms_UTRA | 1 | Rel-11 | R4,R5 | Mon 19/09/11 | Fri 07/09/12 | 100% | RP-120208 | RP-121078 | Nokia | petri.j.vasenkari@nokia.com | RP#57 completed | UTRA 25.914 | 53 | 27 |  |  | Mon 19/09/11 | Thu 06/09/12
4747 | 540026 | Study on HSPA feedback and signalling efficiency enhancements for LCR TDD | FS_LCRTDD_HSPAenh | 1 | Rel-11 | R1 | Wed 07/12/11 | Fri 07/09/12 | 100% | RP-111766 | RP-121079 | TD Tech | limei.wei@td-tech.com | RP#57 completed. TR 25.874 v100 for Information & Approval | UTRA 25.874 | 54 | 28 |  |  | Wed 07/12/11 | Sat 09/06/12
4748 | 510035 | Deleted - Study on Enhanced Uplink Transmission for LTE | FS_eUL_TX_LTE | 1 | Rel-11 | R1 | Tue 22/03/11 | Fri 15/06/12 | 100% | RP-120259 | RP-120585 | Huawei | Yongxing Zhou | RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it | LTE 36.8xy | 51 | 26 | RP-56 | PCG-29 | Mon 21/03/11 | Mon 18/06/12
4749 | 0 | --- RELEASE 10 --- | - | 1 | Rel-10 | CP,GP,RP,SP | Thu 11/12/08 | Wed 21/09/11 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
4750 | 390073 | Enhancements for Multimedia Priority Service | eMPS | 1 | Rel-10 | S1,S2,C4,C3,C1 | Mon 13/03/06 | Fri 18/03/11 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044) | - | 39 | 21 |  |  | Fri 28/03/03 | Tue 01/03/11
4751 | 390074 | Stage 1 on enhancements for Multimedia Priority Service | ePRIOR-St1 | 2 | Rel-10 | S1 | Mon 13/03/06 | Thu 05/06/08 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | 22/01: acronym modified | 22.153, 22.278 | 39 | 21 |  |  | Fri 28/03/03 | Thu 22/01/15
4752 | 460029 | Stage 2 on enhancements for Multimedia Priority Service | ePRIOR-St2 | 2 | Rel-10 | S2 | Thu 10/12/09 | Thu 23/09/10 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | - | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
4753 | 460329 | Stage 2 on eMPS for CSFB | ePRIOR-St2 | 3 | Rel-10 | S2 | Thu 10/12/09 | Thu 23/09/10 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
4754 | 460429 | Stage 2 on eMPS for EPS Bearer Service | ePRIOR-St2 | 3 | Rel-10 | S2 | Thu 10/12/09 | Thu 23/09/10 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
4755 | 460529 | Stage 2 on eMPS for IMS Aspects | ePRIOR-St2 | 3 | Rel-10 | S2 | Thu 10/12/09 | Thu 23/09/10 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
4756 | 460229 | Deleted - TR 23.854 on Stage 2 on enhancements for Multimedia Priority Service | - | 2 | Rel-10 | S2 | Thu 10/12/09 | Thu 16/12/10 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 TR 23.854 v100 for Information. SP#50 moved to Rel-11 SRVCC aspect of enhancements for Multimedia Priority Service UID_480135 (place holder for solution alternatives and agreed functions to be reflected in affected existing TS) | new 23.854 | 46 | 24 | SP-50 | PCG-27 | Sun 06/12/09 | Tue 30/11/10
4757 | 490008 | Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 2 | Rel-10 | C4,C3,C1 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | Stage 3 | 49 | 25 |  |  | Wed 01/09/10 | Thu 09/12/10
4758 | 490108 | CT4 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C4 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 23.008, 29.002, 29.228, 29.229, 29.272, 29.274, 29.277, 29.328, 29.329 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
4759 | 490208 | CT3 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C3 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 29.212, 29.213, 29.214 | 49 | 25 |  |  | Wed 01/09/10 | Tue 01/03/11
4760 | 490308 | CT1 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C1 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 24.008, 24.229, 24.301 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
4761 | 410030 | Network Improvements for Machine-Type Communications | NIMTC | 1 | Rel-10 | S1,S2,S5,C1,C4,C6,G2,R2,R3,R5,G3new | Thu 18/09/08 | Fri 22/11/13 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | Triggered by Rel-8 UID_7027 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) TR 22.868 | - | 41 | 21 |  |  | Mon 15/09/08 | Mon 28/02/11
4762 | 410031 | Stage 1 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S1 | Thu 18/09/08 | Thu 25/03/10 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | SP#47 completed | 22.011, New 22.368 | 41 | 21 |  |  | Mon 15/09/08 | Tue 09/03/10
4763 | 450028 | Deleted - TR on Stage 2 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S2 | Thu 24/09/09 | Thu 16/12/10 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#50 updated WID SP-090832=>SP-100863 (TR 23.888 not submitted for approval to conclude Rel-10 NIMTC as it will continue to serve as basis for Rel-11 SIMTC work item) | New 23.888 | 45 | 23 | SP-50 | PCG-26 | Mon 21/09/09 | Wed 01/12/10
4764 | 490037 | Stage 2 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S2 | Mon 30/08/10 | Thu 23/09/10 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#49 completed | 23.060, 23.236, 23.401 | 45 | 23 |  |  | Mon 21/09/09 | Mon 13/12/10
4765 | 460023 | Deleted - Security for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S3 | Thu 10/12/09 | Thu 23/09/10 | 100% | SP-100863 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#49 stopped (activity transferred to Rel-11 Feature SIMTC under UID_490028 "TR on Security aspects of Machine-Type Communications". | New 33.868 | 46 | 24 | SP-49 | PCG-25 | Mon 21/09/09 | Mon 27/09/10
4766 | 510040 | Charging for Network Improvements for Machine-Type Communication | NIMTC-CH | 2 | Rel-10 | S5 | Mon 21/03/11 | Wed 23/03/11 | 100% | SP-110136 | - | Ericsson | patrik.teppo@@ericsson.com | SP#51 completed | 32.251, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/03/11
4767 | 480005 | CN part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 2 | Rel-10 | C1,C4,C6 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | Stage 3 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
4768 | 480105 | CT1 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C1 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.122, 24.008, 24.301, New 24.368 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
4769 | 480205 | Deleted - CT3 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C3 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 stopped (SA2 decided to move impact from CT3 to CT4). Updated WID CP-110147=>CP-110442 (no CT3 impact) | 29.212, 29.213, 29.215 | 48 | 25 | CP-52 | PCG-27 | Wed 26/05/10 | Wed 01/06/11
4770 | 480305 | CT4 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C4 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.275, 29.282 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
4771 | 510005 | CT6 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C6 | Fri 18/03/11 | Fri 03/06/11 | 100% | - | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#52 completed | 31.102 | 51 | 26 |  |  | Thu 10/03/11 | Wed 18/05/11
4772 | 490003 | GERAN part of Network Improvements for Machine-Type Communications (Stage 3) | NIMTC | 2 | Rel-10 | G2 | Fri 03/09/10 | Fri 02/09/11 | 100% | GP-101647 | - | Vodafone, Ericsson | leo.patanapongpibul@vodafone.com, john.diachina@ericsson.com | GP#51 completed. GP#47 approved WID | 44.018, 44.060 | 47 | 25 |  |  | Sun 05/09/10 | Mon 05/09/11
4773 | 570003 | MS Conformance Test Aspects for GERAN - Network Improvements for Machine-Type Communications | NIMTC_GERAN-MSTest | 2 | Rel-10 | G3new | Mon 27/08/12 | Fri 22/11/13 | 100% | GP-121141 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#60 completed. GP#55 approved WID. Testing for CT1 part of Stage 3 for NIMTC UID_480105, GERAN part of NIMTC (Stage 3) UID_490003 | 51.010-1, 51.010-2 | 55 | 29 |  |  | Thu 23/08/12 | Fri 22/11/13
4774 | 490024 | RAN mechanisms to avoid CN overload due to Machine-Type Communications | NIMTC-RAN_overload | 2 | Rel-10 | R2,R3 | Fri 17/09/10 | Fri 18/03/11 | 100% | RP-101026 | RP-110063 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#51 completed | UTRA, LTE 25.331, 25.413, 36.331, 36.413 | 49 | 25 |  |  | Mon 20/09/10 | Mon 14/03/11
4775 | 570004 | UE Conformance Test Aspects - Network Improvements for Machine-Type Communications | NIMTC-UEConTest | 2 | Rel-10 | R5 | Tue 11/09/12 | Fri 14/06/13 | 100% | RP-121124 | RP-130465 | Ericsson | calle.hagenfeldt@ericsson.com | RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024 | 34.123-1, 34.123-2, 34.123-3, 36.523-1, 36.523-2, 36.523-3 | 57 | 29 |  |  | Wed 05/09/12 | Mon 03/06/13
4776 | 430035 | Multi Access PDN Connectivity | MAPCON | 1 | Rel-10 | S2,C4,C1,C3 | Fri 13/03/09 | Fri 18/03/11 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | CP#51 completed. SP#49 Stage 2 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | - | 43 | 22 |  |  | Thu 05/03/09 | Tue 08/02/11
4777 | 430135 | Stage 2 for Multi Access PDN Connectivity | MAPCON | 2 | Rel-10 | S2 | Fri 13/03/09 | Thu 23/09/10 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | 23.237, 23.401, 23.402 | 43 |  |  |  | Mon 25/10/10 | Mon 25/10/10
4778 | 500004 | CT aspects of Multi Access PDN Connectivity | MAPCON-St3 | 2 | Rel-10 | C4,C1,C3 | Mon 15/11/10 | Fri 18/03/11 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | - | 50 | 26 |  |  | Mon 25/10/10 | Thu 09/12/10
4779 | 500104 | CT4 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C4 | Mon 15/11/10 | Fri 10/12/10 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#50 completed | 29.273, 29.272, 29.002, 23.008 | 50 | 26 |  |  | Mon 25/10/10 | Thu 09/12/10
4780 | 500204 | CT1 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C1 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 24.302, 24.312 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
4781 | 500304 | CT3 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C3 | Mon 15/11/10 | Fri 18/03/11 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 29.215 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
4782 | 440052 | IMS Service Continuity – Inter Device Transfer enhancements | IMS_SC_eIDT | 1 | Rel-10 | S1,S2,C1,IETF | Thu 04/06/09 | Fri 07/12/12 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements | - | 44 | 23 |  |  | Mon 25/05/09 | Tue 09/03/10
4783 | 440152 | Stage 1 - IMS Service Continuity – Inter Device Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | S1 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#47 completed | 22.228 | 44 | 23 |  |  | Mon 25/05/09 | Tue 09/03/10
4784 | 450029 | Stage 2 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | S2 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-100167 | - | Huawei | Lee Valerius (lvalerius@huawei.com) | SP#49 completed | 23.237, 23.292, new 23.831 | 45 | 23 |  |  | Mon 21/09/09 | Mon 06/09/10
4785 | 470001 | Stage 3 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | C1 | Fri 19/03/10 | Fri 18/03/11 | 100% | CP-110285 | - | Huawei | georg.mayer@huawei.com | CP#51 completed. WID updated CP-100334=>CP-110285 | 24.216, 24.229, 24.237, new (24.837, 24.337) | 47 | 24 |  |  | Wed 17/03/10 | Thu 17/03/11
4786 | 521001 | (IETF) Stage 3 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | C1-IETF | Fri 19/03/10 | Fri 07/12/12 | 100% | CP-110285 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 52 | 27 |  |  | Mon 20/06/11 | Tue 04/12/12
4787 | 450030 | IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | CPM-SMS | 1 | Rel-10 | S1,S2,C3 | Thu 24/09/09 | Fri 17/09/10 | 100% | SP-090615 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM | - | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
4788 | 450031 | Stage 1 for CPM-SMS | CPM-SMS | 2 | Rel-10 | S1 | Thu 24/09/09 | Thu 25/03/10 | 100% | SP-090615 | - | China Mobile | Qing Huang | SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C) | 22.34 | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
4789 | 450032 | Stage 2 for CPM-SMS | CPM-SMS | 2 | Rel-10 | S2 | Thu 24/09/09 | Thu 25/03/10 | 100% | SP-090615 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#47 completed | 23.204, new 23.824 | 45 | 23 |  |  | Tue 08/09/09 | Fri 26/02/10
4790 | 460017 | Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | CPM-SMS | 2 | Rel-10 | C3 | Fri 04/12/09 | Fri 17/09/10 | 100% | CP-090859 | - | Ericsson | Jan Holm | CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204 | 29.311 | 46 | 24 |  |  | Mon 30/11/09 | Wed 01/09/10
4791 | 450033 | Completion of Communications on Not Logged-in | CCNL | 1 | Rel-10 | S1,C1,C3 | Thu 24/09/09 | Fri 18/03/11 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | CP#51 completed. SP#45 Stage 1 completed | - | 45 | 23 |  |  | Tue 08/09/09 | Tue 08/09/09
4792 | 450034 | Stage 1 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | S1 | Thu 24/09/09 | Thu 24/09/09 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | SP#45 completed | 22.173 CR#0056r1 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
4793 | 470002 | CT1 part of Stage 3 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | C1 | Fri 19/03/10 | Fri 18/03/11 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#51 completed | 24.173, 24.642 | 47 | 24 |  |  | Wed 17/03/10 | Mon 14/02/11
4794 | 480006 | CT3 part of Stage 3 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | C3 | Fri 04/06/10 | Fri 17/09/10 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#49 completed | 29.165 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/09/10
4795 | 450035 | Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 1 | Rel-10 | S2,S1,S3,S5,C4,C1 | Thu 24/09/09 | Wed 23/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | TSG#51 completed. Updated WID SP-100696=>SP-110131. SP#49 Stage 2 & Security completed. UID_400035 Enhanced Home NodeB/eNodeB (EHNB) formerly covered Local IP Access to Internet and Local access to Home Network from the Home NodeB/eNodeB | - | 45 | 23 |  |  | Tue 08/09/09 | Mon 13/12/10
4796 | 450037 | Stage 1 for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S1 | Thu 24/09/09 | Thu 25/03/10 | 100% | SP-110131 | - | Huawei, China Mobile | Amar Deol (adeolf@huawei.com), Gang Li (ligangyf@chinamobile.com) | SP#47 completed | 22.101, 22.220 | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
4797 | 450036 | TR on Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S2 | Thu 24/09/09 | Fri 18/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#51 completed. TR 23.829 for Approval | New 23.829 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
4798 | 450039 | Security for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S3 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-110131 | - | Huawei, Qualcomm | Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com) | SP#49 completed | 33.102, 33.107, 33.108, 33.320, 33.401 | 45 | 23 |  |  | Tue 08/09/09 | Fri 23/07/10
4799 | 450040 | OAM&P for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S5 | Thu 24/09/09 | Wed 23/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | Zou Lan (zlan@huawei.com), Chen Gang (chengang@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.581, 32.582, 32.584, 32.591, 32.592, 32.642, 32.646, 32.772, 32.782 | 45 | 23 |  |  | Tue 08/09/09 | Thu 17/03/11
4800 | 460039 | Charging for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S5 | Thu 10/12/09 | Wed 23/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | shan.mingjun@huawei.com, Ai Chen (chenai@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.251 | 46 | 24 |  |  | Tue 08/09/09 | Thu 17/03/11
4801 | 450238 | Stage 2/3 for Local IP Access | LIPA | 2 | Rel-10 | S2,C4,C1 | Thu 24/09/09 | Fri 18/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | 45 | 23 |  |  | Tue 08/09/09 | Mon 06/09/10
4802 | 450338 | Stage 2 for Local IP Access | LIPA | 3 | Rel-10 | S2 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (has impacts to RAN) | 23.060, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Mon 06/09/10
4803 | 480008 | Stage 3 for Local IP Access | LIPA | 3 | Rel-10 | C4,C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | - | 48 | 25 |  |  | Wed 26/05/10 | Wed 26/05/10
4804 | 480108 | CT4 part of Stage 3 for Local IP Access | LIPA | 4 | Rel-10 | C4 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 23.008, 23.015, 29.002, 29.060, 29.272, 29.274, 29.281, 29.303 | 48 | 25 |  |  | Wed 26/05/10 | Tue 30/11/10
4805 | 480208 | CT1 part of Stage 3 for Local IP Access | LIPA | 4 | Rel-10 | C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 24.008, 24.301 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
4806 | 450038 | Stage 2/3 for SIPTO for macro networks | SIPTO | 2 | Rel-10 | S2,C4,C1 | Thu 24/09/09 | Fri 18/03/11 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
4807 | 450138 | Stage 2 for SIPTO for macro networks | SIPTO | 3 | Rel-10 | S2 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (SIPTO GW selection for wild card APN and for GERAN. Serving-GW selection for SIPTO. Corrections and Clarifications of the SIPTO procedure) | 23.060, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
4808 | 480007 | Stage 3 for SIPTO for macro networks | SIPTO | 3 | Rel-10 | C4,C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | - | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
4809 | 480107 | CT4 part of Stage 3 for SIPTO for macro networks | SIPTO | 4 | Rel-10 | C4 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | 23.003, 23.008, 29.002, 29.272, 29.303 | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
4810 | 480207 | CT1 part of Stage 3 for SIPTO for macro networks | SIPTO | 4 | Rel-10 | C1 | Fri 04/06/10 | Fri 10/12/10 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#50 completed | 24.008, 24.301 | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
4811 | 450041 | IP Flow Mobility and seamless WLAN offload | IFOM | 1 | Rel-10 | S2,S1,S5,C1,C3 | Thu 24/09/09 | Wed 23/03/11 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#51 completed. Triggered by Rel-10 TR 23.861 (UID_410043 Study on Multi Access PDN connectivity and IP flow mobility - MAPIM) | - | 45 | 23 |  |  | Tue 08/09/09 | Thu 10/03/11
4812 | 450042 | Stage 1 for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S1 | Thu 24/09/09 | Thu 10/12/09 | 100% | SP-100089 | - | Qualcomm | David Williams (dwilliam@qualcomm.com) | SP#46 completed | 22.278 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
4813 | 450043 | Stage 2 for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S2 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#49 completed | 23.203, 23.402, new 23.261 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
4814 | 470021 | Charging for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100089 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#51 completed | 32.240, 32.251, 32.252, 32.298, 32.299 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
4815 | 480009 | Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 2 | Rel-10 | C1,C3 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | Stage 3 | 48 | 25 |  |  | Wed 26/05/10 | Thu 09/12/10
4816 | 480109 | CT1 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 3 | Rel-10 | C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 24.008, 24.301, 24.302, 24.303, 24.312, 24.327 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
4817 | 480209 | CT3 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 3 | Rel-10 | C3 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 29.212, 29.213, 29.214, 29.215 | 48 | 25 |  |  | Wed 26/05/10 | Tue 01/03/11
4818 | 450044 | Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 1 | Rel-10 | S2,S4,C4,C3,C1,IETF | Wed 15/07/09 | Fri 07/09/12 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#52 completed. Triggered by Rel-9 UID_440013 Vocoder rate adaptation for LTE | UTRA, LTE | 45 | 23 |  |  | Tue 08/09/09 | Mon 23/05/11
4819 | 450045 | TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S2,S4 | Thu 07/01/10 | Thu 23/09/10 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#48 completed | new 23.860 | 45 | 23 |  |  | Tue 08/09/09 | Wed 26/05/10
4820 | 450145 | SA4 review of TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S4 | Thu 24/09/09 | Wed 15/12/10 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#50 completed | new 23.860 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
4821 | 450046 | Stage 2 for Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S2 | Thu 24/09/09 | Thu 23/09/10 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#49 completed | 23.060, 23.203, 23.228, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Tue 14/09/10
4822 | 490038 | SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S4 | Thu 23/09/10 | Wed 23/03/11 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 completed | 26.114 | 49 | 25 |  |  | Tue 14/09/10 | Fri 18/02/11
4823 | 490007 | CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 2 | Rel-10 | C4,C3,C1 | Wed 15/07/09 | Fri 07/09/12 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | Stage 2/3 | 49 | 25 |  |  | Wed 01/09/10 | Wed 09/03/11
4824 | 490107 | CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C4 | Fri 17/09/10 | Fri 03/06/11 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 23.334, 29.334, 29.238, 23.333, 29.333, 29.232, 29.332 | 49 | 25 |  |  | Wed 01/09/10 | Tue 17/05/11
4825 | 531006 | (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C3-IETF,C4-IETF | Wed 15/07/09 | Fri 07/09/12 | 100% | CP-100702 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 53 | 27 |  |  | Wed 31/08/11 | Mon 03/09/12
4826 | 490207 | CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C3 | Fri 17/09/10 | Fri 03/06/11 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 29.162, 29.163, 29.213, 29.235, 29.292 | 49 | 25 |  |  | Wed 01/09/10 | Tue 17/05/11
4827 | 490307 | CT1 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C1 | Fri 17/09/10 | Fri 03/06/11 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 24.229 | 49 | 25 |  |  | Wed 01/09/10 | Mon 23/05/11
4828 | 450053 | Extended H(e)NB features | EHNBF | 1 | Rel-10 | S1,S2,S3 | Thu 11/12/08 | Thu 23/09/10 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#49 completed. Adds extensions to Rel-9 functionality in UID_400035 Enhanced Home NodeB / eNodeB (EHNB) | UTRA, LTE | 45 | 23 |  |  | Tue 08/09/09 | Fri 23/07/10
4829 | 450153 | Stage 1 of Extended H(e)NB features | EHNBF | 2 | Rel-10 | S1 | Thu 24/09/09 | Thu 25/03/10 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#47 completed | 22.22 | 45 | 23 |  |  | Tue 08/09/09 | Tue 08/06/10
4830 | 420034 | IMS aspects of Architecture for Home NodeB | EHNB-IMS | 2 | Rel-10 | S2 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-080799 | - | Alcatel-Lucent | Nicolas Drevon | SP#47 completed. Chosen solution has no normative impacts | New 23.832 | 42 | 22 |  |  | Tue 09/12/08 | Fri 26/02/10
4831 | 480034 | Extended H(e)NB Security features (Stage 2) | EHNBF-Sec | 2 | Rel-10 | S3 | Thu 10/06/10 | Thu 23/09/10 | 100% | SP-100257 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#49 completed | 33.32 | 48 | 25 |  |  | Wed 05/05/10 | Fri 23/07/10
4832 | 460028 | Optimal Media Routing | OMR | 1 | Rel-10 | S2,S5,C3,C1 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | CP#52 completed. SP#47 Stage 2 completed. Triggered by TR 23.894 (UID_370050 Study on System enhancements for the use of IMS servicES in CP-150local breakout) | - | 46 | 24 |  |  | Sun 06/12/09 | Tue 17/05/11
4833 | 460128 | Stage 2 for Optimal Media Routing | OMR | 2 | Rel-10 | S2 | Thu 25/03/10 | Thu 25/03/10 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#47 completed | 23.228 | 46 | 24 |  |  | Sun 06/12/09 | Fri 26/02/10
4834 | 480010 | Stage 3 for Optimal Media Routing | OMR | 2 | Rel-10 | C3,C1,C4 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134 | - | 48 | 25 |  |  | Wed 26/05/10 | Thu 10/03/11
4835 | 480110 | CT3 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C3 | Fri 04/06/10 | Fri 03/06/11 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#52 completed | 29.162, 29.163, 29.165, 29.235, new 29.079 | 48 | 25 |  |  | Wed 26/05/10 | Tue 17/05/11
4836 | 480210 | CT1 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completed. WID updated CP-100327=>CP-110134 | 24.229 | 48 | 25 |  |  | Wed 26/05/10 | Thu 10/03/11
4837 | 480310 | Deleted - CT4 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C4 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134 | - | 48 | 25 | CP-51 | PCG-26 | Wed 26/05/10 | Thu 10/03/11
4838 | 500013 | Charging for Optimal Media Routing | OMR | 2 | Rel-10 | S5 | Thu 16/12/10 | Wed 08/06/11 | 100% | SP-100772 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#52 completed. Stage 3: Linked to CT3 TS 29.079 OMR within the IMS¦Stage 3 (UID_480110) | 32.260, 32.298, 32.299 | 50 | 26 |  |  | Sat 27/11/10 | Mon 16/05/11
4839 | 470026 | IMS Emergency Session Enhancements | IESE | 1 | Rel-10 | S1,S2,C1 | Thu 25/03/10 | Fri 03/06/11 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | CP#52 completed. SP#49 completed. Source of external requirements: ETSI TISPAN TS 181.019 (Business Communication Requirements) | - | 47 | 24 |  |  | Wed 10/03/10 | Mon 23/05/11
4840 | 470027 | Stage 1 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | S1 | Thu 25/03/10 | Thu 25/03/10 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | Kurt Bischinger | SP#47 completed | 22.101 CR#0343 | 47 | 24 |  |  | Wed 10/03/10 | Tue 23/03/10
4841 | 470028 | Stage 2 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | S2 | Thu 25/03/10 | Thu 23/09/10 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | SP#49 completed | 23.167 | 47 | 24 |  |  | Wed 10/03/10 | Mon 06/09/10
4842 | 500005 | Stage 3 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | C1 | Fri 10/12/10 | Fri 03/06/11 | 100% | CP-100880 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed | 24.229 | 50 | 26 |  |  | Mon 25/10/10 | Mon 23/05/11
4843 | 480037 | S2b Mobility based on GTP | SMOG | 1 | Rel-10 | S2,C4,C3,C1 | Thu 10/06/10 | Fri 18/03/11 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. SP#49 Stage 2 completed. Related to Rel-10 UID_470049 Study on S2b mobility based on GTP (TR23.834), UID_350027 SAE for support for non-3GPP accesses. Stage1 in Rel-8 UID_320022 Reqs for evolution of 3GPP system architecture (AIPN-SAE) | - | 48 | 25 |  |  | Sun 06/06/10 | Fri 18/03/11
4844 | 480137 | Stage 2 for S2b Mobility based on GTP | SMOG | 2 | Rel-10 | S2 | Thu 10/06/10 | Thu 23/09/10 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#49 completed | 23.002, 23.203, 23.402 | 48 | 25 |  |  | Sun 06/06/10 | Mon 06/09/10
4845 | 490009 | Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 2 | Rel-10 | C4,C3,C1 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 Stage 3 completed | - | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
4846 | 490109 | CT4 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C4 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
4847 | 490209 | CT3 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C3 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 29.212, 29.213, 29.215 | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
4848 | 490309 | CT1 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C1 | Fri 17/09/10 | Fri 10/12/10 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#50 completed | 24.302 | 49 | 25 |  |  | Wed 01/09/10 | Thu 25/11/10
4849 | 500006 | Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST | 1 | Rel-10 | S2,C3 | Tue 12/10/10 | Fri 18/03/11 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user | - | 50 | 26 |  |  | Fri 26/11/10 | Sat 19/03/11
4850 | 500106 | Stage 2 for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST | 2 | Rel-10 | S2 | Tue 12/10/10 | Tue 12/10/10 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 updated WID SP-100702=>SP-110196. SP#49 work completed as SA2 CRs approved under TEI10 (SP-10557) | 23.002, 23.203 | 50 | 26 |  |  | Fri 26/11/10 | Sat 19/03/11
4851 | 500206 | CT3 aspects of Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST-CT3 | 2 | Rel-10 | C3 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100860 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#51 completed | 29.212, 29.213, 29.214, 29.215 | 50 | 26 |  |  | Fri 26/11/10 | Tue 01/03/11
4852 | 470029 | Lawful Interception in the 3GPP Rel-10 | LI10 | 1 | Rel-10 | S3 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106 (LI requirements), 33.107 (LI architecture and functions), 33.108 (Handover interface for LI) | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4853 | 470129 | LI for CAT (Customer Alerting Tones) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4854 | 470229 | LI for CRS (Customized Ringing Signal) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4855 | 470329 | LI for EPS enhancements | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4856 | 470429 | LI for VCC (Voice Call Continuity) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4857 | 470529 | LI for MEDIASEC (IMS Media security) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4858 | 470629 | LI for H(e)NB also with Local IP Access and Selected IP Traffic Offload (LIPA, SIPTO) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4859 | 470729 | LI for MBMS enhancements | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4860 | 470829 | LI for LCLS (Local Call Local Switch) | LI10 | 2 | Rel-10 | S3 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
4861 | 470033 | Optimization of IMS based PSS and MBMS User Service | OPT_IMS_PSS_MBMS_US | 1 | Rel-10 | S4 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100031 | - | Ericsson | markus.kampmann@ericsson.com | SP#51 completed. Work to enhance UID_430046 Rel-9 IMS_PSS_MBMS_US_EXT | 26.237 | 47 | 24 |  |  | Wed 10/03/10 | Wed 02/03/11
4862 | 470034 | HTTP-based Streaming and Download Services | HTTP_SDS | 1 | Rel-10 | S4,IETF | Thu 25/03/10 | Wed 21/09/11 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed. Work to enhance UID_430038 Rel-9 PSS and MBMS extensions | - | 47 | 24 |  |  | Wed 10/03/10 | Thu 26/05/11
4863 | 470134 | HTTP-based Streaming and Download Services in 3GPP | HTTP_SDS | 2 | Rel-10 | S4 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed | 26.234, 26.244, 26.346, new 26.247 | 47 | 24 |  |  | Wed 10/03/10 | Thu 26/05/11
4864 | 521002 | (IETF) HTTP-based Streaming and Download Services in 3GPP | HTTP_SDS | 2 | Rel-10 | S4-IETF | Thu 25/03/10 | Wed 21/09/11 | 100% | SP-100032 | - | - | - | SP#53/IETF#81: Draft not included in 3GPP documentation. Dec.14: IETF RFC added | RFC 6381 (was draft-gellens-mime-bucket-bis) | 52 | 27 |  |  | Mon 20/06/11 | Thu 04/12/14
4865 | 480040 | PSS and MBMS enhancements | MBS_Enh | 1 | Rel-10 | S4 | Thu 10/06/10 | Wed 23/03/11 | 100% | SP-100305 | - | Ericsson | Markus.Kampmann@ericsson.com | SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). | 26.234, 26.346 | 48 | 25 |  |  | Fri 28/05/10 | Wed 02/03/11
4866 | 480041 | Enhancements and Addition of Audio Tests to 26.131 and 26.132 | EAAT | 1 | Rel-10 | S4 | Thu 10/06/10 | Wed 08/06/11 | 100% | SP-100306 | - | Vodafone | ramin.afchar@vodafone.com | SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec | 26.131, 26.132 | 48 | 25 |  |  | Fri 28/05/10 | Tue 17/05/11
4867 | 510055 | Video Coding Enhancements in MTSI | VCEM | 1 | Rel-10 | S4 | Mon 21/03/11 | Wed 23/03/11 | 100% | SP-110050 | - | Ericsson | frederic.gabin@ericsson.com | SP#51 completed. Linked to Rel-7 UID_7040 Multimedia Telephony Service for IMS - Media handling and interaction in MTSI (MTSI-MHI) | 26.114 | 51 | 26 |  |  | Thu 10/03/11 | Wed 23/03/11
4868 | 460031 | Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM10 | 1 | Rel-10 | S5,C4 | Thu 10/12/09 | Wed 21/09/11 | 100% | - | - | - | - | OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | 30.82 | 46 | 24 |  |  | Tue 01/12/09 | Fri 26/08/11
4869 | 460032 | Rel-10 Network Infrastructure Management | OAM10-NIM | 2 | Rel-10 | S5 | Thu 10/12/09 | Wed 21/09/11 | 100% | - | - | - | - | umbrella BB | - | 46 | 24 |  |  | Tue 01/12/09 | Sat 12/12/09
4870 | 460033 | Common RAT Network Resource Model (NRM) | RAT_NRM_common | 3 | Rel-10 | S5 | Thu 10/12/09 | Wed 08/06/11 | 100% | SP-100293 | - | Ericsson | robert.petersen@ericsson.com | SP#52 completed. Share equipment btw several RATs (RET,TMA,repeaters) to reduce costs. With existing modelling is difficult to see that several cells are affected when an antenna tilt is changed etc | 32.616, 32.642, 32.646, 32.652, 32.656, 32.762, 32.766 new (32.791, 32.792, 32.796) | 46 | 24 |  |  | Tue 01/12/09 | Mon 16/05/11
4871 | 470035 | IRP Solution Set specification organisation improvements | OAM-IRP-SS | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100774 | - | Nokia Siemens Networks, Huawei | Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) | SP#51 completed | 32.153, new (32.111-6,32.126,32.176,32.306,32.316,32.326,32.336,32.346,32.356,32.366,32.376,32.386,32.396,32.416,32.446,32.506/26/36,32.606,32.616,32.626,32.636,32.646,32.656,32.666,32.676,32.696,32.716,32.726,32.736,32.746,32.756,32.766,32.776,32.786) | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
4872 | 470036 | Deleted - Service Oriented Architecture (SOA) for IRP continuation from Rel-9 | OAM-SOA-IRP | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100076 | - | Nokia Siemens Networks, Ericsson | Jörg Schmidt (J.Schmidt@NSN.com), edwin.tse@ericsson.com | SP#51 work stopped (Reason: lack of progress). Continuation of Rel-9 UID_440065 SOA for IRP (covering SOA Architecture & SOA-supporting Solution Set) to address SOA conforming Registration & Discovery capabilities | 32.101, 32.150 | 47 | 24 | SP-51 | PCG-26 | Mon 08/03/10 | Wed 09/03/11
4873 | 480042 | IRP Overview, Profiles & Usage Guide | OAM-NIM-IRP_OPU | 3 | Rel-10 | S5 | Thu 10/06/10 | Wed 08/06/11 | 100% | SP-110277 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@NSN.com) | SP#52 completed. Updated WID SP-100777=>SP-110277 | new 32.103 | 48 | 25 |  |  | Wed 26/05/10 | Mon 06/06/11
4874 | 510041 | Alarm Correlation and Root Cause Analysis | OAM-AC-RCA | 3 | Rel-10 | S5 | Wed 23/03/11 | Wed 21/09/11 | 100% | SP-110137 | - | Ericsson | brendan.hassett@ericsson.com | SP#53 completed. Triggered by Rel-10 TR 32.832 Study on Alarm Correlation and Alarm Root Cause Analysis UID_480045 & TR 32.829 Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program Fault Management UID_460038 | 32.111-1, 32.111-2, 32.111-6 | 51 | 26 |  |  | Wed 09/03/11 | Fri 26/08/11
4875 | 510042 | Inventory Management Network Resource Model enhancements | OAM-IM-NMR | 3 | Rel-10 | S5 | Wed 23/03/11 | Wed 08/06/11 | 100% | SP-110141 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items | 32.690, 32.691, 32.692, 32.696 | 51 | 26 |  |  | Wed 09/03/11 | Mon 16/05/11
4876 | 460034 | Rel-10 Self-Organizing Networks (SON) - OAM aspects | OAM10-SON | 2 | Rel-10 | S5 | Thu 10/12/09 | Wed 08/06/11 | 100% | - | - | - | - | umbrella BB | - | 46 | 24 |  |  | Tue 01/12/09 | Sat 12/12/09
4877 | 460035 | SON Self-optimization management continuation | LTE-SON-OAM_SO | 3 | Rel-10 | S5 | Thu 10/12/09 | Wed 08/06/11 | 100% | SP-110130 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#52 completed. Cont'd Rel-9 SON self-optimization management UID_390007 | 32.425, 32.521, 32.522, 32.526, 32.762, 32.766 | 46 | 24 |  |  | Tue 01/12/09 | Fri 13/05/11
4878 | 460036 | SON Self-healing management | LTE-SON-OAM_SH | 3 | Rel-10 | S5 | Thu 10/12/09 | Wed 23/03/11 | 100% | SP-110150 | - | ZTE | zhu.weihong@zte.com.cn | SP#51 completed. WID updated SP-100776=>SP-110150. Work moved to Rel-10 after split of the Rel-9 UID_390007 SON self-optimization (removed Self-Healing handling) | 32.522, 32.526, 32.762, 32.766, new 32.541 | 46 | 24 |  |  | Tue 01/12/09 | Tue 22/03/11
4879 | 470037 | OAM aspects of Energy Saving in Radio Networks | OAM-ES | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-110128 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management¦Energy Savings Management (FS_OAM_ESM) UID_430044 | 32.425, 32.522, 32.526, 32.626, 32.762, 32.766, new 32.551 | 47 | 24 |  |  | Fri 12/02/10 | Thu 17/03/11
4880 | 470038 | Rel-10 Subscription Management (SuM) evolution | OAM10-SuM | 2 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100086 | - | Ericsson | leo.yang@ericsson.com | SP#51 completed | 32.172, 32.175, 32.176 | 47 | 24 |  |  | Tue 23/03/10 | Wed 09/03/11
4881 | 470039 | Rel-10 Performance Management | - | 2 | Rel-10 | S5,C4 | Thu 25/03/10 | Wed 08/06/11 | 100% | - | - | - | - | umbrella BB | - | 47 | 24 |  |  | Fri 12/02/10 | Fri 12/02/10
4882 | 470040 | Key Performance Indicators (KPIs) for IMS | OAM-PM-KPI_IMS | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100083 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.454 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
4883 | 470041 | Key Performance Indicators (KPIs) for EPC | OAM-PM-KPI_EPC | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100084 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.455 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
4884 | 470042 | Management of UE based network performance measurements | OAM-PM-UE | 3 | Rel-10 | S5,C4 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE) | - | 47 | 24 |  |  | Fri 12/02/10 | Tue 22/03/11
4885 | 470142 | SA5 aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | S5 | Thu 25/03/10 | Wed 08/06/11 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 47 | 24 |  |  | Fri 12/02/10 | Mon 16/05/11
4886 | 510006 | CN aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | C4 | Mon 21/02/11 | Fri 18/03/11 | 100% | - | - | Nokia Siemens Networks | ulrich.wiehe@nsn.com | CP#51 completed under the SA5 WI code | 23.008 (CR#0330), 29.002 (CR#1007), 29.230 (CR#0207), 29.272 (CR#0329) | 51 | 26 |  |  | Mon 28/02/11 | Mon 28/02/11
4887 | 470043 | 3G HNB and LTE HeNB Subsystem performance measurements | OAM-PM-HeNS | 3 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100081 | - | China Mobile | Chen Gang (chengang@chinamobile.com) | SP#51 completed | 32.582, 32.592, new (32.452, 32.453) | 47 | 24 |  |  | Mon 08/03/10 | Wed 09/03/11
4888 | 470044 | Rel-10 Charging Management small Enhancements | CH10 | 1 | Rel-10 | S5 | Thu 04/06/09 | Wed 23/03/11 | 100% | - | - | - | - | CH10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | 30.82 | 47 | 24 |  |  | Fri 12/02/10 | Fri 12/02/10
4889 | 440063 | IWLAN mobility charging | eIWLAN_Mob | 2 | Rel-10 | S5 | Thu 04/06/09 | Wed 23/03/11 | 100% | SP-100090 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#51 completed. RAT differentiation for charging. Completes Rel-8 Feature IWLAN_Mob UID_370049 Mobility between 3GPP-WLAN Interworking and 3GPP Systems. Cooperation with CT1,CT3 on affected protocols | 32.240, 32.252, 32.298, 32.299 | 44 | 23 |  |  | Tue 19/05/09 | Fri 28/01/11
4890 | 470046 | Advice of Charge (AoC) service support enhancements | eAoC | 1 | Rel-10 | S5,C1 | Thu 25/03/10 | Fri 03/06/11 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work | - | 47 | 24 |  |  | Tue 23/03/10 | Mon 23/05/11
4891 | 470047 | SA5 part - AoC enhancements | eAoC | 2 | Rel-10 | S5 | Thu 25/03/10 | Wed 23/03/11 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#51 completed. SA1 Stage 1 in 22.115 | 32.275, 32.280, 32.298, 32.299 | 47 | 24 |  |  | Tue 23/03/10 | Fri 28/01/11
4892 | 490010 | CT1 part - AoC enhancements (Stage 3) | eAoC | 2 | Rel-10 | C1 | Fri 17/09/10 | Fri 03/06/11 | 100% | CP-100645 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed. SA1 Stage 1 in 22.115, 22.173, 22.024. Add mobile-specific CAI format and volume charging elements. Extensions to existing AoC XML | 24.647 | 49 | 25 |  |  | Tue 07/09/10 | Mon 23/05/11
4893 | 470003 | IMS Stage 3 IETF Protocol Alignment - phase 4 | IMSProtoc4 | 1 | Rel-10 | C1 | Fri 19/03/10 | Fri 18/03/11 | 100% | CP-100099 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not | 23.218, 24.229, 24.930 | 47 | 24 |  |  | Wed 17/03/10 | Mon 28/02/11
4894 | 480012 | Enhanced User Data Convergence (UDC) Model | eUDC | 1 | Rel-10 | C4 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100295 | - | China Mobile | Lan Sizhong (lansizhong@chinamobile.com) | CP#51 completed. Specify CRUD (Create/Read/Update/Delete) operations based on SOAP protocol, which may be used by the applications having no high real-time requirement to the data access operations | 29.335 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
4895 | 480014 | Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications | II-NNI2 | 1 | Rel-10 | C3 | Fri 04/06/10 | Fri 01/03/13 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI) | - | 48 | 25 |  |  | Wed 26/05/10 | Thu 21/02/13
4896 | 480114 | Further improvements of II-NNI Stage 3 | II-NNI2 | 2 | Rel-10 | C3 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | CP#51 completed | 29.165 | 48 | 25 |  |  | Fri 20/04/12 | Fri 20/04/12
4897 | 561001 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6794) | II-NNI2 | 2 | Rel-10 | C3-IETF | Fri 20/04/12 | Fri 01/03/13 | 100% | CP-100326 | - | Lionel Morand | Lionel Morand | CP#59 completed AUTH 48 RFC-to-be-6794 | RFC 6794 (was draft-ietf-sip-session-policy-framework) | 56 | 29 |  |  | Fri 20/04/12 | Thu 21/02/13
4898 | 561002 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6809) | II-NNI2 | 2 | Rel-10 | C3-IETF | Fri 20/04/12 | Fri 07/12/12 | 100% | CP-100326 | - | christer.holmberg@ericsson.com | Christer Holmberg | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 56 | 29 |  |  | Fri 20/04/12 | Tue 04/12/12
4899 | 480013 | AT Commands for IMS-configuration | AT_IMS | 1 | Rel-10 | C1 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100376 | - | Ericsson | atle.monrad@ericsson.com | CP#51 completed. Specify 1) IMS-related AT-commands to configure MT and 2) IMS-related unsolicited response codes from MT to present to end-user | 27.007 | 48 | 25 |  |  | Sat 29/05/10 | Mon 14/02/11
4900 | 490011 | AT Commands for USIM Application Toolkit (USAT) | AT_UICC | 1 | Rel-10 | C1 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100646 | - | ST-Ericsson | magnus.mk.karlsson@stericsson.com | CP#51 completed | 27.007 | 49 | 25 |  |  | Sat 29/05/10 | Mon 14/02/11
4901 | 490012 | Communication Control for IMS by USIM (Stage 3) | CC_IMS_USIM | 1 | Rel-10 | C6 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100647 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed. Stage 1 in TS 22.038 USAT service description. Linked to CT6's UID_1273 Rel-5 BB Provisioning of IP-based multimedia services (24.229, 31.103) and UID_390021 Rel-8 BB CT6 aspects of SAE (31.102, 31.111) | 31.102, 31.103, 31.111 | 49 | 25 |  |  | Mon 06/09/10 | Thu 03/03/11
4902 | 500003 | Dynamic view of SIP message for Inter-IMS Network to Network Interface (II-NNI) (Stage 3) | NNI_DV | 1 | Rel-10 | C3 | Fri 10/12/10 | Fri 03/06/11 | 100% | CP-100795 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#52 completed. Linked to CT3 Rel-10 Feature UID_480014 Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications (II-NNI2) | 29.165 | 50 | 26 |  |  | Fri 26/11/10 | Tue 17/05/11
4903 | 500007 | Introduction of Smart Card Web Server launch functionality | SCWS_L | 1 | Rel-10 | C6 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100883 | - | Telecom Italia | davide.pratone@telecomitalia.it | CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server servicES in CP-150an easy and simple manner | 31.102 | 50 | 26 |  |  | Sun 28/11/10 | Thu 03/03/11
4904 | 500008 | USAT using AT Commands | USAT_AT | 1 | Rel-10 | C6 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100884 | - | Giesecke & Devrient | enric.fort@gi-de.com | CP#51 completed. Stage 3 based on SA1 22.038CR#37r1 (Make USAT proactive capability reqs applicable to ME as a whole without regard to any particular configuration¦e.g. a modem connected to an external display) | Stage 3 31.102, 31.111 | 50 | 26 |  |  | Sun 28/11/10 | Thu 03/03/11
4905 | 500010 | Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3) | eSRVCC | 1 | Rel-10 | C1,C4,IETF | Fri 10/12/10 | Fri 07/12/12 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049 | - | 50 | 26 |  |  | Mon 25/10/10 | Thu 21/02/13
4906 | 500110 | CT1 part of Stage 3 for SRVCC enhancements | eSRVCC | 2 | Rel-10 | C1 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 24.229, 24.237 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
4907 | 500210 | CT4 part of Stage 3 for SRVCC enhancements | eSRVCC | 2 | Rel-10 | C4 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.305, 29.328, 29.329 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
4908 | 521003 | (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809) | eSRVCC | 2 | Rel-10 | C1-IETF | Fri 10/12/10 | Fri 07/12/12 | 100% | CP-100881 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 52 | 27 |  |  | Mon 20/06/11 | Thu 21/02/13
4909 | 500011 | Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | aSRVCC | 1 | Rel-10 | C1,R5 | Fri 10/12/10 | Fri 01/03/13 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | Builds on Rel-8 UID_390057 (IMS-Cont) TS 23.216 Stage 2. Provide Stage 3 for SRVCC PS-CS transfer of a call in alerting phase. Stage 2 TEI10 in TS 23.237 (6.3.2.1.4c/d, 6.3.2.1.7a/b) | - | 50 | 26 |  |  | Wed 16/03/11 | Mon 23/05/11
4910 | 500111 | CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | aSRVCC | 2 | Rel-10 | C1 | Fri 10/12/10 | Fri 03/06/11 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed | 24.008, 24.237 | 50 | 26 |  |  | Wed 16/03/11 | Mon 23/05/11
4911 | 570005 | Conformance test aspects SRVCC in alerting phase | aSRVCC-UEConTest | 2 | Rel-10 | R5 | Tue 11/09/12 | Fri 01/03/13 | 100% | RP-121700 | RP-130042 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#59 completed | 36.523-1, 36.523-2, 36.523-3, 34.229-1, 34.229-2, 34.229-3 | 57 | 29 |  |  | Wed 05/09/12 | Wed 27/02/13
4912 | 500012 | PCRF failure and restoration | PCRF_FR | 1 | Rel-10 | C4,C3 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed. Triggered by CT3 TR 29.816 Study on Policy and Charging Rules Function (PCRF) failure and restoration (FS_PCRF-FR) UID_450013 | Stage 2/3 work | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
4913 | 500112 | CT4 part of PCRF failure and restoration | PCRF_FR | 2 | Rel-10 | C4 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 2 23.007, Stage 3 29.230 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
4914 | 500212 | CT3 part of PCRF failure and restoration | PCRF_FR | 2 | Rel-10 | C3 | Fri 10/12/10 | Fri 18/03/11 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 3 29.212, 29.213, 29.214, 29.215 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
4915 | 510002 | Formalization of WLAN Files | FoWF | 1 | Rel-10 | C1 | Wed 23/02/11 | Wed 23/02/11 | 100% | CP-110288 | - | Deutsche Telekom | dieter.jacobsohn@telekom.de | CP#51 completed. TS 24.235 for Info+Approval. Define the ME files as specified in 24.234 in OMA Device Management structure | Stage 3: 24.234, New 24.235 | 51 | 26 |  |  | Thu 03/03/11 | Thu 17/03/11
4916 | 510007 | CS and IMS Interworking for CAT service - Early Session model | CIIC_ES | 1 | Rel-10 | C3 | Wed 16/03/11 | Fri 03/06/11 | 100% | CP-110283 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed. Stage 1 in Rel-8 TS 22.182 Customized Alerting Tones (CAT) service. Stage 3 TS 24.182 defines 3 impl models: Gateway, Forking, Early Session. Specify missing CAT service interworking procedures btw CS & IMS networks | Stage 3 29.163, 29.235, 29.292 | 51 | 26 |  |  | Wed 02/03/11 | Thu 10/03/11
4917 | 510008 | EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated | EPC_NR | 1 | Rel-10 | C4 | Wed 16/03/11 | Fri 18/03/11 | 100% | CP-110092 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274 | 51 | 26 |  |  | Tue 22/02/11 | Fri 18/03/11
4918 | 510108 | EPC Node Restoration with Idle mode Signalling Reduction (ISR) activated | EPC_NR_ISR | 1 | Rel-10 | C4 | Wed 16/03/11 | Fri 03/06/11 | 100% | CP-110287 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#52 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274 | 51 | 26 |  |  | Tue 22/02/11 | Tue 17/05/11
4919 | 510009 | Mobile Terminating Roaming Forwarding with pre-paging | MTRF | 1 | Rel-10 | C4 | Wed 16/03/11 | Fri 03/06/11 | 100% | CP-110093 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed. Provides Stage 2/3 alternative solution to Mobile Terminating Roaming Retry to solve roaming events during paging, in particular to support CSFB. Hence, no new Stage 1 requirements exist | Stage 2/3: 23.012, 23.018, 23.116, 29.002 | 51 | 26 |  |  | Tue 22/02/11 | Tue 08/03/11
4920 | 510010 | UICC access to IMS Specification | IMS-UICC-S | 1 | Rel-10 | C6,C1 | Wed 16/03/11 | Fri 03/06/11 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC | - | 51 | 26 |  |  | Thu 03/03/11 | Wed 18/05/11
4921 | 510110 | CT6 part of UICC access to IMS Specification | IMS-UICC-S | 2 | Rel-10 | C6 | Wed 16/03/11 | Fri 18/03/11 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.102, 31.103, 31.111 | 51 | 26 |  |  | Thu 03/03/11 | Thu 10/03/11
4922 | 510210 | CT1 part of UICC access to IMS Specification | IMS-UICC-S | 2 | Rel-10 | C1 | Wed 16/03/11 | Fri 03/06/11 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed | 24.229 | 51 | 26 |  |  | Thu 03/03/11 | Wed 18/05/11
4923 | 550006 | Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features | USIM_R10_Test | 1 | Rel-10 | C6 | Mon 05/03/12 | Tue 03/12/13 | 100% | CP-120396 | - | Gemalto | Denis.Praca@gemalto.com | CP#62 stopped (at 70% completion 06/13). Testing for New featurES in CP-150Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111 | 31.121, 31.124, New 31.ABC (Conformance Testing of specific features) | 55 | 28 | CP-62 | PCG-32 | Wed 22/02/12 | Thu 06/06/13
4924 | 440021 | CN aspects of Local Call Local Switch | LCLS-CN | 1 | Rel-10 | C4 | Fri 29/05/09 | Fri 18/03/11 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | GERAN Stage 2/3 | 44 | 23 |  |  | Wed 13/05/09 | Thu 09/12/10
4925 | 440022 | TR on CN aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C4 | Fri 29/05/09 | Thu 16/09/10 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#49 completed | new 23.889 | 44 | 23 |  |  | Wed 13/05/09 | Thu 09/12/10
4926 | 490013 | Stage 2/3 for CN aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C4 | Fri 17/09/10 | Fri 18/03/11 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.009, 23.205, 23.231, 29.002, 29.205, 29.232, new 23.284 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
4927 | 440023 | Deleted - CT3 aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C3 | Fri 29/05/09 | Thu 16/09/10 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT3 specification impact | - | 44 | 23 | CP-49 | PCG-25 | Wed 13/05/09 | Wed 01/09/10
4928 | 440024 | Deleted - CT1 aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C1 | Fri 29/05/09 | Thu 16/09/10 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT1 specification impact | - | 44 | 23 | CP-49 | PCG-25 | Wed 13/05/09 | Wed 01/09/10
4929 | 430001 | Local Call Local Switch | LCLS | 1 | Rel-10 | GP,G2 | Mon 07/05/07 | Mon 07/05/07 | 100% | GP-101989 | - | Huawei | wang_zhixi@huawei.com | GP#50 completed. GP#41 WID approved | GERAN Stage 3: 48.008, 48.103 | 41 | 22 |  |  | Fri 20/02/09 | Sat 21/05/11
4930 | 480002 | Tightened Link Level Performance Requirements for Single Antenna MS | TIGHTER | 1 | Rel-10 | G1,G2,C1,G3new | Fri 03/09/10 | Fri 01/03/13 | 100% | GP-101083 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#46 approved WID | GERAN | 46 | 25 |  |  | Thu 27/05/10 | Sat 16/03/13
4931 | 480102 | CT1 part for TIGHTER | TIGHTER | 2 | Rel-10 | C1 | Fri 03/09/10 | Fri 03/06/11 | 100% | GP-101083 | - | Renesas Mobile | marko.niemi@renesasmobile.com | CP#52 completed | 24.008 | 46 | 25 |  |  | Thu 27/05/10 | Mon 23/05/11
4932 | 480202 | TIGHTER Performance Requirements | TIGHTER | 2 | Rel-10 | G1,G2 | Fri 03/09/10 | Fri 20/05/11 | 100% | GP-101084 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#50 completed | 45.005, 45.015 | 46 | 25 |  |  | Thu 27/05/10 | Sat 21/05/11
4933 | 480302 | TIGHTER Testing | TIGHTER | 2 | Rel-10 | G3new | Wed 08/09/10 | Fri 01/03/13 | 100% | GP-101085 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#57 completed | 51.01 | 46 | 25 |  |  | Thu 27/05/10 | Mon 04/03/13
4934 | 490001 | Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 1 | Rel-10 | G2,S2,C1 | Fri 21/05/10 | Fri 04/03/11 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method | GERAN | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
4935 | 490101 | Stage 2 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | S2 | Fri 21/05/10 | Thu 16/12/10 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | SP#50 completed | 23.251 | 47 | 25 |  |  | Thu 27/05/10 | Tue 30/11/10
4936 | 490201 | CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | C1 | Fri 21/05/10 | Fri 10/12/10 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#50 completed | 24.008 CR#1644 | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
4937 | 490301 | GERAN2 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | G2 | Mon 30/08/10 | Fri 04/03/11 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#49 completed | 48.008 CR#0325, 48.018 CR#0303 | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
4938 | 490002 | Enhancements of Iur-g interface | eIurg | 1 | Rel-10 | G2,R3 | Fri 03/09/10 | Fri 03/06/11 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#47 approved WID | GERAN,UTRA | 47 | 25 |  |  | Sun 05/09/10 | Thu 26/05/11
4939 | 490102 | GERAN part for Enhancements of Iur-g interface (Stage 2/3) | eIurg-GERAN | 2 | Rel-10 | G2 | Fri 03/09/10 | Fri 04/03/11 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#49 completed. GP#48 updated WID GP-101659=>GP-101758 (restricting the scope to GERAN BSC and TD-SCDMA RNC only). GP#47 approved WID | 43.130, 48.008 | 47 | 25 |  |  | Sun 05/09/10 | Fri 04/03/11
4940 | 490021 | Core part: Enhancements of Iur-g interface (Stage 2/3) | eIurg-RAN | 2 | Rel-10 | R3 | Fri 03/09/10 | Fri 03/06/11 | 100% | RP-101232 | RP-110526 | ZTE | Liu Junqiang (liu.junqiang@zte.com.cn) | RP#52 completed | UTRA Stage 2 (25.401, 25.420), Stage 3 (25.423) | 49 | 25 |  |  | Sun 05/09/10 | Thu 26/05/11
4941 | 380077 | 1.28 Mcps TDD Repeater | RANimp-Repeaters1.28TDD | 1 | Rel-10 | R4 | Tue 04/12/07 | Fri 19/03/10 | 100% | RP-071003 | RP-100039 | RITT | qinyan@chinattl.com | RP#47 completed | UTRA 25.113, New 25.116, 25.153 (testing) | 38 | 21 |  |  | Mon 17/12/07 | Tue 09/03/10
4942 | 450019 | 1.28 Mcps TDD Multi-carrier HSUPA | TDD_MC_HSUPA | 1 | Rel-10 | R1,R2,R3,R4 | Fri 18/09/09 | Fri 10/12/10 | 100% | RP-090990 | RP-101079 | CATR | Aihui Song (songaihui@mail.ritt.com.cn) | RP#50 completed | UTRA 25.102, 25.105, 25.123, 25.221, 25.222, 25.223, 25.224, 25.225, 25.306, 25.319, 25.321, 25.331, 25.423, 25.427, 25.433 | 45 | 23 |  |  | Tue 15/09/09 | Fri 03/12/10
4943 | 460014 | 1.28 Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF | 1 | Rel-10 | R4 | Fri 04/12/09 | Fri 10/12/10 | 100% | RP-100607 | - | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866) | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Fri 03/12/10
4944 | 460114 | Core part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Core | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 04/06/10 | 100% | RP-100607 | RP-100446 | TD Tech | Li Rong (lirong@td-tech.com) | RP#48 completed | 25.105 | 46 | 24 |  |  | Mon 30/11/09 | Wed 02/06/10
4945 | 460214 | Perf. part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 10/12/10 | 100% | RP-100607 | RP-101081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. TR 25.968 v100 for Approval | 25.142, new 25.968 | 46 | 24 |  |  | Mon 30/11/09 | Fri 03/12/10
4946 | 470012 | Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD | MUMIMO_LCR_TDD | 1 | Rel-10 | R1,R2,R3,R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-100347 | - | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#52 completed | UTRA | 47 | 24 |  |  | Fri 19/03/10 | Tue 23/03/10
4947 | 470112 | Core part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Core | 2 | Rel-10 | R1,R2,R3 | Fri 19/03/10 | Fri 10/12/10 | 100% | RP-100347 | RP-101085 | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#50 completed | 25.221, 25.222, 25.224, 25.306, 25.308, 25.319, 25.331, 25.423, 25.425, 25.433, 25.435 | 47 | 24 |  |  | Fri 19/03/10 | Fri 03/12/10
4948 | 470212 | Perf. part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-100347 | RP-110520 | CATT | Sanjun Feng (fengsanjun@datangmobile.cn) | RP#52 completed | 25.102, 25.105, 25.142 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
4949 | 450027 | AGNSS Minimum Performance for UTRAN | AGNSSPerf_UTRAN | 1 | Rel-10 | R4,R5 | Fri 18/09/09 | Fri 16/09/11 | 100% | RP-100363 | - | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures) | UTRA | 45 | 23 |  |  | Tue 15/09/09 | Wed 08/12/10
4950 | 450127 | AGNSS Minimum Performance Specification Development | AGNSSPerf_UTRAN | 2 | Rel-10 | R4 | Fri 18/09/09 | Fri 10/12/10 | 100% | RP-100363 | RP-101078 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#50 completed | new 25.172 | 45 | 23 |  |  | Tue 15/09/09 | Wed 08/12/10
4951 | 480018 | AGNSS test case development for UMTS | AGNSSPerf_UTRAN | 2 | Rel-10 | R5 | Fri 04/06/10 | Fri 16/09/11 | 100% | RP-101405 | RP-110979 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.37.571-5, new 34.172 | 48 | 25 |  |  | Tue 01/06/10 | Tue 06/09/11
4952 | 460005 | Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT | 1 | Rel-10 | R2,R3 | Fri 04/12/09 | Fri 18/03/11 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907) | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Fri 11/03/11
4953 | 460105 | Core part: Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT-Core | 2 | Rel-10 | R2,R3 | Fri 04/12/09 | Fri 18/03/11 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed | 25.305, 25.453 | 46 | 24 |  |  | Mon 30/11/09 | Fri 11/03/11
4954 | 460015 | Four carrier HSDPA | 4C_HSDPA | 1 | Rel-10 | R1,R2,R3,R4,R5 | Fri 04/12/09 | Fri 06/09/13 | 100% | RP-100991 | - | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
4955 | 460115 | Core part: Four carrier HSDPA | 4C_HSDPA-Core | 2 | Rel-10 | R1,R2,R3,R4 | Fri 04/12/09 | Fri 18/03/11 | 100% | RP-100991 | RP-110046 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#51 completed. RP#52 TR 25.864 v200 for Approval | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306, new 25.864 | 46 | 24 |  |  | Mon 30/11/09 | Fri 27/05/11
4956 | 460215 | Perf. part: Four carrier HSDPA | 4C_HSDPA-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 16/09/11 | 100% | RP-100991 | RP-110986 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | 25.101, 25.104, 25.133, 25.141 | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
4957 | 540006 | Test part: Four carrier HSDPA | 4C_HSDPA-UEConTest | 2 | Rel-10 | R5 | Fri 02/12/11 | Fri 06/09/13 | 100% | RP-111565 | RP-130940 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#61 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 54 | 28 |  |  | Thu 24/11/11 | Thu 29/08/13
4958 | 470013 | Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD | 1 | Rel-10 | R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-100168 | - | TD Tech | dafei.wang@td-tech.com | Stage 3. RP#52 completed | UTRA | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
4959 | 470113 | Core part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Core | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 04/06/10 | 100% | RP-100168 | RP-100454 | TD Tech | dafei.wang@td-tech.com | RP#48 completed | 25.102 | 47 | 24 |  |  | Fri 19/03/10 | Tue 01/06/10
4960 | 470213 | Perf. part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-100168 | RP-110521 | TD Tech | dafei.wang@td-tech.com | RP#52 completed | 25.102 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
4961 | 480020 | Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN | 1 | Rel-10 | R3,R2,R5 | Fri 04/06/10 | Fri 07/12/12 | 100% | RP-100688 | - | ZTE | Zhai.hengxing@zte.com.cn | RP#52 Core completed. Automatic Neighbour Relation (ANR) function for UTRAN relieves operators from the burden of manually managing the Neighbour cell Relations (NRs) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Mon 15/04/13
4962 | 480120 | Core part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-Core | 2 | Rel-10 | R3,R2 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100688 | RP-110522 | ZTE | Zhai.hengxing@zte.com.cn | RP#52 completed | 25.331, 25.413, 25.423, new 25.484 (Stage 2) | 48 | 25 |  |  | Thu 03/06/10 | Tue 31/05/11
4963 | 530039 | Test part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-UEConTest | 2 | Rel-10 | R5 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-120599 | RP-121529 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 | 53 | 27 |  |  | Fri 09/09/11 | Wed 28/11/12
4964 | 480021 | Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA | 1 | Rel-10 | R4,R2 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100657 | - | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. Rel-9 Dual-Band Dual-Cell HSDPA (UID_430015 Support for different bands for Dual-Cell HSDPA) has one combination per region in principle. This work adds additional combinations: Band I and XI (Region 3) and Band II and V (Region 2) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Tue 24/05/11
4965 | 480121 | Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Core | 2 | Rel-10 | R4,R2 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100657 | RP-110523 | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new 25.327 | 48 | 25 |  |  | Thu 03/06/10 | Tue 24/05/11
4966 | 480221 | Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Perf | 2 | Rel-10 | R4,R2 | Fri 04/06/10 | Fri 17/09/10 | 100% | RP-100657 | RP-100759 | AT&T | Vince Spatafora (vs5785@att.com) | RP#49 stopped (Reason: no need for Performance work) | 25.101, 25.104, 25.141, 25.317 | 48 | 25 | RP-49 | PCG-25 | Thu 03/06/10 | Thu 09/09/10
4967 | 480022 | MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA | 1 | Rel-10 | R4,R5 | Fri 04/06/10 | Fri 02/03/12 | 100% | RP-100993 | - | Qualcomm | Heechoon Lee | RP#52 completed. RP#49 updated WID RP-100687=>RP-100993 (changed Title: MIMO Testing in HSDPA => MIMO operation with non-MIMO coexistence in HSDPA) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Mon 14/03/11
4968 | 490023 | Core part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Core | 2 | Rel-10 | R4 | Fri 17/09/10 | Fri 03/06/11 | 100% | RP-100993 | RP-110524 | Qualcomm | Heechoon Lee | RP#52 completed | 25.104 | 49 | 25 |  |  | Fri 10/09/10 | Fri 27/05/11
4969 | 480122 | Perf. part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Perf | 2 | Rel-10 | R4 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100993 | RP-110525 | Qualcomm | Heechoon Lee | RP#52 completed | 25.101, 25.141 | 48 | 25 |  |  | Thu 03/06/10 | Fri 27/05/11
4970 | 510017 | Test part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-UEConTest | 2 | Rel-10 | R5 | Fri 18/03/11 | Fri 02/03/12 | 100% | RP-110244 | RP-120042 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#55 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Thu 23/02/12
4971 | 490022 | Interfrequency detected set measurements for UMTS | Interf_dset_meas_UMTS | 1 | Rel-10 | R2,R4 | Fri 17/09/10 | Fri 10/12/10 | 100% | RP-101015 | RP-101093 | Nokia | Chris.callender@nokia.com | RP#50 completed | UTRA 25.133, 25.331 | 49 | 25 |  |  | Sat 11/09/10 | Wed 08/12/10
4972 | 460007 | Carrier Aggregation for LTE | LTE_CA | 1 | Rel-10 | R1,R2,R3,R4,R5 | Fri 04/12/09 | Fri 07/12/12 | 100% | RP-100661 | - | Nokia | Asbjorn.grovlen@nokia.com | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 14/03/11
4973 | 460107 | Core part: Carrier Aggregation for LTE | LTE_CA-Core | 2 | Rel-10 | R1,R2,R3,R4 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-100661 | RP-110535 | Nokia | lars.e.lindh@nokia.com | RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, 37.104, new RAN4 (36.807, 36.808) | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
4974 | 460207 | Perf. part: Carrier Aggregation for LTE | LTE_CA-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 09/12/11 | 100% | RP-100661 | RP-111452 | Nokia | lars.e.lindh@nokia.com | RP#54 completed | 36.101, 36.104, 36.133, 36.141, 37.141 | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
4975 | 530040 | Test part: Carrier Aggregation for LTE | LTE_CA-UEConTest | 2 | Rel-10 | R5 | Mon 19/09/11 | Fri 07/12/12 | 100% | RP-121246 | RP-121528 | Nokia | jussi.kuusisto@nokia.com | RP#58 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 53 | 27 |  |  | Tue 06/09/11 | Tue 04/12/12
4976 | 460008 | Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | Fri 04/12/09 | Fri 14/06/13 | 100% | RP-100196 | - | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Fri 19/03/10
4977 | 460108 | Core part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | Fri 04/12/09 | Fri 18/03/11 | 100% | RP-100196 | RP-110067 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 36.807 | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
4978 | 460208 | Perf. part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 02/03/12 | 100% | RP-091429 | RP-120053 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#55 completed | 36.101, 36.104, 36.133, 36.141 | 46 | 24 |  |  | Mon 30/11/09 | Thu 23/02/12
4979 | 560012 | Test part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-UEConTest | 2 | Rel-10 | R5 | Mon 18/06/12 | Fri 14/06/13 | 100% | RP-120612 | RP-130464 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | RP#60 completed. Testing for 36.101, 36.133 | 36.508, 36.521-1, 36.521-2 | 56 | 29 |  |  | Wed 06/06/12 | Tue 04/06/13
4980 | 460009 | Uplink Multiple Antenna Transmission for LTE | LTE_UL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | Mon 03/01/00 | Fri 01/03/13 | 100% | RP-100959 | - | Huawei | Mattias.wennstrom@huawei.com | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
4981 | 460109 | Core part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | Mon 03/01/00 | Fri 29/06/01 | 100% | RP-100959 | RP-110537 | Huawei | Mattias.wennstrom@huawei.com | RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 (36.807, 36.817) | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
4982 | 460209 | Perf. part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 16/09/11 | 100% | RP-100959 | RP-110992 | Huawei | Mattias.wennstrom@huawei.com | RP#53 completed | 36.101, 36.104, 36.133, 36.141, 36.817 | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
4983 | 540007 | Test part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-UEConTest | 2 | Rel-10 | R5 | Fri 02/12/11 | Fri 01/03/13 | 100% | RP-111614 | RP-130038 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Wed 27/02/13
4984 | 460013 | Relays for LTE | LTE_Relay | 1 | Rel-10 | R1,R2,R4,S2,S3,C4,C6 | Fri 04/12/09 | Wed 08/06/11 | 100% | RP-110911 | - | Ericsson | christian.hoymann@ericsson.com | RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11) | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 14/02/11
4985 | 460113 | Core part: Relays for LTE | LTE_Relay-Core | 2 | Rel-10 | R1,R2,R4 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-110911 | RP-110540 | Ericsson | christian.hoymann@ericsson.com | RP#52 completed. Updated WID RP-101417=>RP-101911 (contains only Core part completed in Rel-10). Open RAN4 Core & Perf parts moved to new Rel-11 | 36.201, 36.211, 36.212, 36.213, 36.300, 36.321, 36.323, 36.331, New RAN1 36.216 | 46 | 24 |  |  | Mon 30/11/09 | Thu 14/06/12
4986 | 460213 | Deleted - Perf. part: Relays for LTE | LTE_Relay-Perf | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-101417 | RP-110541 | Ericsson | christian.hoymann@ericsson.com | RP#52 stopped at 30% (no CRs so far) . Transferred completely to Rel-11 together with remaining core part | 36.133, New 36.117 (E-UTRA Relay conformance testing) | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Mon 06/06/11
4987 | 520020 | Stage 2 for Relays for LTE | LTE_Relay | 2 | Rel-10 | S2 | Mon 06/06/11 | Wed 08/06/11 | 100% | - | - | Vodafone | chris.pudney@vodafone.com | SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview | 23.401 | 52 | 27 |  |  | Mon 06/06/11 | Mon 06/06/11
4988 | 500038 | LTE Relay Nodes Security | LTE_Relay-Sec | 2 | Rel-10 | S3,C6 | Thu 16/12/10 | Tue 22/03/11 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | - | - | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
4989 | 500238 | TR on LTE Relay Nodes Security | LTE_Relay-Sec | 3 | Rel-10 | S3 | Thu 16/12/10 | Tue 22/03/11 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed | 33.816 | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
4990 | 500138 | Security for LTE Relay Nodes (Stage 2) | LTE_Relay-Sec | 3 | Rel-10 | S3 | Thu 16/12/10 | Tue 22/03/11 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed (impacting Stage 3 in CT and RAN) | 33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413 | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
4991 | 510011 | CT6 aspects of LTE Relay Node Security | LTE_Relay-Sec | 3 | Rel-10 | C6 | Wed 16/03/11 | Fri 18/03/11 | 100% | - | - | n/a | n/a | CP#51 completed | 31.101, 31.102 | 51 | 26 |  |  | Thu 03/03/11 | Thu 03/03/11
4992 | 510012 | Core Network Impacts for Relay Nodes | LTE_Relay-CN | 2 | Rel-10 | C4 | Wed 16/03/11 | Fri 18/03/11 | 100% | CP-110094 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.008, 29.303, 29.230, 29.272 | 51 | 26 |  |  | Mon 28/02/11 | Tue 08/03/11
4993 | 470007 | Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE | 1 | Rel-10 | R1,R2,R3,R4,R5 | Fri 19/03/10 | Fri 13/06/14 | 100% | RP-100383 | - | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Mon 14/03/11
4994 | 470107 | Core part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-Core | 2 | Rel-10 | R1,R2,R3,R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-100383 | RP-110543 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#52 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423 | 47 | 24 |  |  | Fri 19/03/10 | Fri 27/05/11
4995 | 470207 | Perf. part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 15/06/12 | 100% | RP-100383 | RP-120461 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | 36.101, 36.133 | 47 | 24 |  |  | Fri 19/03/10 | Tue 05/06/12
4996 | 550001 | Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE-UEConTest | 2 | Rel-10 | R5 | Mon 05/03/12 | Fri 13/06/14 | 100% | RP-120217 | RP-140766 | Qualcomm | Anjali Mishra (ajha@qualcomm.com) | RP#64 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 55 | 28 |  |  | Thu 23/02/12 | Tue 10/06/14
4997 | 470008 | LTE TDD in 2600MHz for US | LTE_TDD_2600_US | 1 | Rel-10 | R4,R2,R3,R5 | Fri 19/03/10 | Fri 10/12/10 | 100% | RP-101003 | - | Clearwire | michael.hart@clearwire.com | RP#50 Testing completed. RP#49 Core+Perf completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Fri 03/12/10
4998 | 470108 | Core part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Core | 2 | Rel-10 | R4,R2,R3 | Fri 19/03/10 | Wed 15/09/10 | 100% | RP-101003 | RP-100782 | Clearwire | michael.hart@clearwire.com | RP#49 completed 1st Apr 15: CD:Fri 17/09/10->Wed 15/09/10 | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141, new 36.812 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/04/15
4999 | 470208 | Perf. part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 17/09/10 | 100% | RP-101003 | RP-100783 | Clearwire | michael.hart@clearwire.com | RP#49 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.812 | 47 | 24 |  |  | Fri 19/03/10 | Thu 16/09/10
5000 | 480019 | UE conformance test part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-UEConTest | 2 | Rel-10 | R5 | Fri 04/06/10 | Fri 10/12/10 | 100% | RP-100615 | RP-101071 | Clearwire | michael.hart@clearwire.com | RP#50 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 48 | 25 |  |  | Tue 01/06/10 | Fri 03/12/10
5001 | 470009 | Adding 2 GHz band LTE FDD (Band 23) for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | S_Band_LTE_ATC_MSS | 1 | Rel-10 | R2,R4,R5 | Fri 19/03/10 | Fri 09/12/11 | 100% | RP-110775 | - | DBSD | Mariam.Sorond@ico.com | RP#52 completed. Updated WID RP-101401=>RP-110775 (changed in Title "LTE" to "LTE FDD (Band 23)" | LTE | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
5002 | 470109 | Core part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-110775 | RP-110545 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new 36.811 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
5003 | 470209 | Perf. part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-110775 | RP-110546 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.811 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
5004 | 520012 | Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | Tue 07/06/11 | Fri 09/12/11 | 100% | RP-110623 | RP-111444 | DBSD | Mariam.Sorond@ico.com | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 29/11/11
5005 | 470010 | Adding L-Band (Band 24) LTE for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | L_Band_LTE_ATC_MSS | 1 | Rel-10 | R4,R2,R5 | Fri 11/12/09 | Fri 16/09/11 | 100% | RP-101284 | - | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#53 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Tue 06/09/11
5006 | 470110 | Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | Fri 11/12/09 | Fri 10/12/10 | 100% | RP-101284 | RP-101117 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#51 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new RAN4 36.813 | 47 | 24 |  |  | Fri 19/03/10 | Thu 17/03/11
5007 | 470210 | Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-101284 | RP-110548 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#52 completed | 34.121-1, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.521-1, 36.813 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
5008 | 510015 | Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | Fri 18/03/11 | Fri 16/09/11 | 100% | RP-110777 | RP-110980 | LightSquared | masoud.olfat@lightsquared.com | RP#53 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2 | 51 | 26 |  |  | Thu 10/03/11 | Tue 06/09/11
5009 | 470011 | LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE | 1 | Rel-10 | R3,R2,R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-101004 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
5010 | 470111 | Core part: LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE-Core | 2 | Rel-10 | R3,R2,R4 | Fri 19/03/10 | Fri 03/06/11 | 100% | RP-101004 | RP-110547 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed (Stage 1,2,3) | 36.300, 36.331, 36.413, 36.423 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
5011 | 480027 | Further enhancements to MBMS for LTE | MBMS_LTE_enh | 1 | Rel-10 | R2,R3,R5 | Fri 04/06/10 | Fri 02/03/12 | 100% | RP-101244 | - | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives | LTE | 48 | 25 |  |  | Fri 04/06/10 | Mon 14/03/11
5012 | 480127 | Core part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-Core | 2 | Rel-10 | R2,R3 | Fri 04/06/10 | Fri 18/03/11 | 100% | RP-101244 | RP-110083 | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed | 25.446, 36.300, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445 | 48 | 25 |  |  | Fri 04/06/10 | Mon 14/03/11
5013 | 540008 | Test part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-UEConTest | 2 | Rel-10 | R5 | Fri 02/12/11 | Fri 02/03/12 | 100% | RP-111615 | RP-120049 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#55 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Thu 23/02/12
5014 | 380173 | UMTS/LTE 3500 MHz | RInImp8-UMTSLTE3500 | 1 | Rel-10 | R4,R2,R3,R5 | Fri 30/11/07 | Fri 14/06/13 | 100% | RP-091380 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE | 38 | 21 |  |  | Mon 17/12/07 | Mon 03/06/13
5015 | 380073 | Core part: UMTS/LTE 3500 MHz | RInImp8-UMTSLTE3500 | 2 | Rel-10 | R4,R2,R3 | Fri 30/11/07 | Fri 16/09/11 | 100% | RP-091380 | RP-110987 | Ericsson | johan.skold@ericsson.com | RP#53 completed. TR 37.801v200 for Approval | 25.101, 25.104, 25.113, 25.133, 25.141, 25.307, 25.307, 25.331, 25.461, 25.463, 34.124, 36.101, 36.104, 36.113, 36.141, 36.331, new 37.801 | 38 | 21 |  |  | Mon 17/12/07 | Fri 09/09/11
5016 | 420013 | Conformance Test Aspects – LTE 3500 | LTE-UEConTest_LTE3500 | 2 | Rel-10 | R5 | Fri 05/12/08 | Fri 14/06/13 | 100% | RP-080859 | RP-130461 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3 | 42 | 22 |  |  | Thu 27/11/08 | Mon 03/06/13
5017 | 420014 | Conformance Test Aspects – UMTS 3500 | RInImp-UEConTest_UMTS3500 | 2 | Rel-10 | R5 | Fri 05/12/08 | Fri 15/06/12 | 100% | RP-110386 | RP-120450 | Ericsson | fredrik.sundstrom@ericsson.com | RP#56 completed | 34.108, 34.121-1, 34.121-2 | 42 | 22 |  |  | Thu 27/11/08 | Tue 05/06/12
5018 | 460003 | Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE | 1 | Rel-10 | R2,R4,R3,R5 | Fri 04/12/09 | Fri 01/03/13 | 100% | RP-100360 | - | Nokia Siemens Networks | malgorzata.tomala@nsn.com | Triggered by UID_430021 TR 36.805 (Study on Minimization of drive-tests in NGN) | UTRA, LTE | 46 | 24 |  |  | Mon 30/11/09 | Wed 27/02/13
5019 | 460103 | Core part: Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE-Core | 2 | Rel-10 | R2,R4,R3 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-100360 | RP-110528 | Nokia Siemens Networks | malgorzata.tomala@nsn.com | RP#52 completed | 25.133, 25.215, 25.304, 25.331, 25.423, 36.133, 36.214, 36.300, 36.304, 36.331, 36.413, 36.423, new 37.320 (Stage 2) | 46 | 24 |  |  | Mon 30/11/09 | Tue 24/05/11
5020 | 530041 | Test part: Minimization of Drive Tests for E-UTRAN | MDT_UMTSLTE-UEConTest | 2 | Rel-10 | R5 | Mon 19/09/11 | Fri 01/03/13 | 100% | RP-120598 | RP-130036 | Ericsson | leif.mattisson@ericsson.com | RP#59 completed. Testing for LTE only | LTE 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 | 53 | 27 |  |  | Tue 06/09/11 | Wed 27/02/13
5021 | 470005 | HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh | 1 | Rel-10 | R3,R2,R5 | Fri 19/03/10 | Fri 07/12/12 | 100% | RP-110183 | - | Alcatel-Lucent | Martin,Warner@alcatel-lucent.com | - | UTRA, LTE | 47 | 24 |  |  | Fri 19/03/10 | Fri 08/04/11
5022 | 470105 | Core part: HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh-Core | 2 | Rel-10 | R3,R2 | Fri 19/03/10 | Fri 18/03/11 | 100% | RP-110183 | RP-110058 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#51 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423, new 25.471 | 47 | 24 |  |  | Fri 19/03/10 | Fri 11/03/11
5023 | 550002 | Test part: HeNB Mobility Enhancements | HNB_HENB_mob_enh-UEConTest_LTE | 2 | Rel-10 | R5 | Mon 05/03/12 | Fri 07/12/12 | 100% | RP-120218 | RP-121533 | Qualcomm | Anjali Mishra (ajha@qualcom.com) | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 55 | 28 |  |  | Thu 23/02/12 | Tue 04/09/12
5024 | 480024 | Expanded 1900 MHz Band for UTRA and LTE | E1900 | 1 | Rel-10 | R4,R2,R5 | Fri 04/06/10 | Fri 07/09/12 | 100% | RP-100676 | - | Sprint | nick.j.baustert@sprint.com | Expand UTRA and E-UTRA band 2 to include frequencies between 1910 – 1915 MHz and 1990-1995 MHz (US FCC allocation) | UTRA, LTE | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
5025 | 480124 | Core part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Core | 2 | Rel-10 | R4,R2 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100676 | RP-110529 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new 36.818 | 48 | 25 |  |  | Fri 04/06/10 | Tue 24/05/11
5026 | 480224 | Perf. part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Perf | 2 | Rel-10 | R4,R2 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-100676 | RP-110530 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new 36.818 | 48 | 25 |  |  | Fri 04/06/10 | Tue 24/05/11
5027 | 520013 | Test part: Expanded 1900 MHz Band for UTRA and LTE | E1900-UEConTest | 2 | Rel-10 | R5 | Tue 07/06/11 | Fri 07/09/12 | 100% | RP-110712 | RP-120957 | Sprint | nick.j.baustert@sprint.com | RP#57 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 04/09/12
5028 | 480025 | Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments | MSR_NC | 1 | Rel-10 | R4,G1 | Fri 04/06/10 | Fri 25/11/11 | 100% | RP-101402 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE, GERAN | 48 | 25 |  |  | Fri 04/06/10 | Mon 12/09/11
5029 | 480125 | Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Core | 2 | Rel-10 | R4 | Fri 04/06/10 | Fri 03/06/11 | 100% | RP-101402 | RP-110531 | Ericsson | johan.skold@ericsson.com | RP#52 completed | 25.104, 36.104, 37.104, new 37.802 | 48 | 25 |  |  | Fri 04/06/10 | Wed 01/06/11
5030 | 480225 | Perf. part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Perf | 2 | Rel-10 | R4 | Fri 04/06/10 | Fri 16/09/11 | 100% | RP-101402 | RP-110988 | Ericsson | johan.skold@ericsson.com | RP#53 completed | 25.141, 36.141, 37.141, 37.802 | 48 | 25 |  |  | Fri 04/06/10 | Mon 12/09/11
5031 | 490004 | GERAN part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 2 | Rel-10 | G1 | Fri 03/09/10 | Fri 25/11/11 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | - | - | 47 | 25 |  |  | Sun 05/09/10 | Sat 21/05/11
5032 | 490104 | GERAN Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 3 | Rel-10 | G1 | Fri 03/09/10 | Fri 02/09/11 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#51 completed. GP#47 approved WID | 45.005 | 47 | 25 |  |  | Sun 05/09/10 | Sat 21/05/11
5033 | 540001 | GERAN BS Test part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 3 | Rel-10 | G1 | Fri 02/09/11 | Fri 25/11/11 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#52 completed | 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 25/11/11
5034 | 440044 | (Small) Technical Enhancements and Improvements for Rel-10 | TEI10 | 1 | Rel-10 | SP,CP,RP,GP | Thu 04/06/09 | Wed 23/03/11 | 100% | - | - | - | - | - | - | 44 | 23 |  |  | Tue 02/06/09 | Mon 07/03/11
5035 | 521004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464 | TEI10_IETF | 1 | Rel-10 | C1-IETF | Thu 04/06/09 | Thu 04/12/14 | 100% | - | - | Andrew Allen | Andrew Allen | Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100 | draft-atarius-dispatch-meid-urn | 52 | 27 |  |  | Mon 20/06/11 | Thu 23/04/20
5036 | 531001 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (RFC6275) | TEI10_IETF1 | 1 | Rel-10 | C1-IETF | Thu 04/06/09 | Fri 29/07/11 | 100% | - | - | - | - | SP#53/IETF#81: RFC 6275 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis) | 53 | 27 |  |  | Fri 29/07/11 | Wed 31/08/11
5037 | 540004 | Test - (Small) Technical Enhancements and Improvements for Rel-10 | TEI10_Test | 1 | Rel-10 | R5,G3new | Thu 01/12/11 | Fri 07/12/12 | 100% | - | - | n/a | - | - | - | 54 | 28 |  |  | Wed 30/11/11 | Thu 06/09/12
5038 | 350014 | Deleted - Registration in Densely-populated area (RED) | RED | 1 | Rel-10 | S1 | Mon 12/03/07 | Thu 24/09/09 | 100% | SP-070133 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned | - | 35 | - | SP-46 | PCG-24 | Thu 29/03/07 | Mon 07/12/09
5039 | 370030 | Deleted - Stage 1 for RED | RED | 2 | Rel-10 | S1 | Mon 12/03/07 | Thu 15/03/07 | 100% | SP-070133 | - | NTT DoCoMo | takakurat@s1.nttdocomo.co.jp | SP#35 completed. SP#46 work stopped/abandoned | 22.101 CR#0207 | 35 |  | SP-46 | PCG-24 | Thu 29/03/07 | Mon 07/12/09
5040 | 370031 | Deleted - Stage 2 for RED | RED | 2 | Rel-10 | S2 | Tue 25/09/07 | Thu 24/09/09 | 100% | SP-070694 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#45 Stage 2 work stopped | draft 23.880 withdrawn, 23.002, 23.060, 23.221, 23.236 | 37 |  | SP-45 | PCG-23 | Tue 25/09/07 | Tue 08/09/09
5041 | 380062 | Deleted - Network Selection for non-3GPP Access | N3GtoNSP | 1 | Rel-10 | S1,C6 | Fri 07/12/07 | Thu 24/09/09 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | - | 38 | 21 | SP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
5042 | 380162 | Deleted - Stage 1 for N3GtoNSP | N3GtoNSP | 2 | Rel-10 | S1 | Fri 07/12/07 | Thu 24/09/09 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 22.011 | 38 | 21 | SP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
5043 | 380262 | Deleted - CT6 issues for N3GtoNSP | N3GtoNSP | 2 | Rel-10 | C6 | Fri 07/12/07 | Thu 24/09/09 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 36.3 | 38 | 21 | CP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
5044 | 420025 | Deleted - GTP-based S8 chaining | GTPchaining | 1 | Rel-10 | S2 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped (depending on ongoing related CT4 work). Stage 1 in UID_320022 Rel-8 Requirements for evolution of the 3GPP system architecture (AIPN-SAE): 22.278, 22.011, 22.246 | - | 42 | 22 | SP-47 | PCG-24 | Fri 05/12/08 | Sun 07/03/10
5045 | 420026 | Deleted - Stage 2 for GTPchaining | GTPchaining | 2 | Rel-10 | S2 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped | 23.402 | 42 | 22 | SP-47 | PCG-24 | Fri 05/12/08 | Sun 07/03/10
5046 | 430017 | Deleted - UTRAN 2 ms TTI uplink range improvement | RANimp-2mTTI_ULimp | 1 | Rel-10 | R1,R2,R3,R4 | Fri 06/03/09 | Fri 19/03/10 | 100% | RP-090333 | RP-100040 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 work stopped/abandoned (no CR approved). Cell sets the TTI (Transmission Time Interval) to 2 ms | 25.133, 25.212, 25.214, 25.321, 25.331 | 43 | 22 | RP-47 | PCG-24 | Wed 07/10/09 | Tue 16/03/10
5047 | 440043 | Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9 | eEHNB | 1 | Rel-10 | S2 | Thu 11/12/08 | Thu 25/03/10 | 100% | - | - | Alcatel-Lucent | Nicolas Drevon | SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB) | - | 44 | 23 | SP-47 | PCG-24 | Thu 13/12/07 | Mon 01/06/09
5048 | 460010 | Deleted - Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF | 1 | Rel-10 | R4,R5 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-091432 | - | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions). Add new power classES in CP-150E-UTRAN UL to allow CPE type applications to be operated at higher max output power | LTE | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Fri 27/05/11
5049 | 460110 | Deleted - Core part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-Core | 2 | Rel-10 | R4 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-091432 | RP-110539 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped at 55% (lack of contributions) | 36.101 | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Wed 16/03/11
5050 | 460210 | Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-UEConTest | 2 | Rel-10 | R5 | Fri 04/12/09 | Fri 03/06/11 | 100% | RP-091432 | RP-110504 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions) | 36.521-1 | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Fri 27/05/11
5051 | 460012 | Deleted - Latency reductions for LTE | LTE_LATRED | 1 | Rel-10 | R2,R1 | Fri 04/12/09 | Fri 10/12/10 | 100% | RP-091449 | - | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | LTE | 46 | 24 | RP-50 | PCG-26 | Mon 30/11/09 | Wed 08/12/10
5052 | 460112 | Deleted - Core part: Latency reductions for LTE | LTE_LATRED-Core | 2 | Rel-10 | R2,R1 | Fri 04/12/09 | Fri 10/12/10 | 100% | RP-091449 | RP-101112 | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | 36.213, 36.300, 36.306, 36.321, 36.331 | 46 | 24 | RP-50 | PCG-26 | Mon 30/11/09 | Wed 08/12/10
5053 | 470006 | Deleted - Enhanced Interference Management for Home NodeBs | HNB_IM | 1 | Rel-10 | R3 | Fri 19/03/10 | Fri 17/09/10 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs | UTRA | 47 | 24 | RP-49 | PCG-25 | Fri 19/03/10 | Thu 09/09/10
5054 | 470106 | Deleted - Core part: Enhanced Interference Management for Home NodeBs | HNB_IM-Core | 2 | Rel-10 | R3 | Fri 19/03/10 | Fri 17/09/10 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed) | 25.413, 25.467, 25.469 | 47 | 24 | RP-49 | PCG-25 | Fri 19/03/10 | Thu 09/09/10
5055 | 0 | Release 10 Studies | - | 1 | Rel-10 | CP,GP,RP,SP | Thu 12/03/09 | Thu 12/03/09 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
5056 | 370045 | Study on enhanced voice service requirements for the Evolved Packet System (EPS) | FS_EV_EPS | 1 | Rel-10 | S1,S4 | Mon 03/09/07 | Thu 25/03/10 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval. Spin-off Feature UID_470030 Codec for Enhanced Voice Services | 22.813 | 37 |  |  |  | Tue 02/10/07 | Tue 31/08/10
5057 | 370047 | Use cases definition and service and system requirements | FS_EV_EPS-S1 | 2 | Rel-10 | S1 | Mon 03/09/07 | Thu 11/12/08 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval | 22.813 | 37 |  |  |  | Thu 04/10/07 | Tue 31/08/10
5058 | 370048 | Codec specific part of FS_EV_EPS | FS_EV_EPS-S4 | 2 | Rel-10 | S4 | Mon 03/09/07 | Thu 25/03/10 | 100% | SP-070698 | - | Ericsson | stefan.bruhn@ericson.com | SP#47 completed. TR 22.813-100 for Approval | 22.813 | 37 |  |  |  | Thu 04/10/07 | Mon 01/02/10
5059 | 380083 | Study on advanced requirements for IP interconnect | FS_IPXS | 1 | Rel-10 | S1 | Tue 04/12/07 | Thu 10/12/09 | 100% | SP-070878 | - | Telefónica O2 | chris.friel@O2.com | SP#46 completed. Linked to Rel-8 Feature UID_380060 IP Interconnection of Services (IPinterc). Spin-off Feature Rel-11 UID_470051 Advanced IP Interconnection of Services | 22.893 | 38 | 21 |  |  | Thu 20/12/07 | Wed 11/08/10
5060 | 410039 | Study on Personal Broadcast Service | FS_PBS | 1 | Rel-10 | S1 | Thu 18/09/08 | Thu 25/03/10 | 100% | SP-080504 | - | ETRI | Jaihyung Cho | SP#47 completed | 22.947 | 41 | 21 |  |  | Mon 15/09/08 | Tue 09/03/10
5061 | 410040 | Study on LCS support in SAE for non-3GPP accesses | FS_LCS_n3GPP | 1 | Rel-10 | S1 | Thu 18/09/08 | Thu 25/03/10 | 100% | SP-080648 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed | 22.814 | 41 | 21 |  |  | Mon 15/09/08 | Wed 11/08/10
5062 | 430030 | Study on Haptic Services | FS_Haptics | 1 | Rel-10 | S1 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090664 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses | 22.987 | 43 | 22 |  |  | Thu 12/02/09 | Wed 11/08/10
5063 | 370050 | Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media | FS_IMS_LBO_ORM | 1 | Rel-10 | S2 | Mon 01/10/07 | Thu 10/12/09 | 100% | SP-080556 | - | Telecom Italia, BT | mario.madella@telecomitalia.it, victor.kueh@bt.com | SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011 | 23.894 | 37 |  |  |  | Tue 02/10/07 | Wed 25/11/09
5064 | 390055 | Study on Intra Domain Connection of RAN Nodes to Multiple CN Nodes | FS_IDC | 1 | Rel-10 | S2 | Wed 12/03/08 | Thu 25/03/10 | 100% | SP-080094 | - | China Mobile | LIU HONG (liuhongyfw@chinamobile.com) | SP#47 completed. Concluded no further normative work expected. Linked to 23.236 | 23.924 (was 23.823) | 39 | 21 |  |  | Thu 20/12/07 | Tue 23/03/10
5065 | 440049 | Study on Single Radio Voice Call Continuity enhancements | FS_eSRVCC | 1 | Rel-10 | S2 | Thu 04/06/09 | Thu 23/09/10 | 100% | SP-090363 | - | China Mobile | Hou zhiqiang (houzhiqiang@chinamobile.com), Jiang Yi (jiangyi@chinamobile.com) | SP#49 completed (Conclusion: select the SIP anchoring based solution for normative work CR (TEI10) introducing and completing stage-2). Analyzed performance of Rel-8 SRVCC solution from E-UTRAN/HSPA to UTRAN/GERAN | 23.856 | 44 | 23 |  |  | Sun 31/05/09 | Mon 06/09/10
5066 | 470048 | Study on Single Radio Video Call Continuity for 3G-CS | FS_vSRVCC | 1 | Rel-10 | S2 | Thu 25/03/10 | Thu 23/09/10 | 100% | SP-100168 | - | Samsung | Haris Zisimopoulos (haris.z@samsung.com) | SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user | 23.886 | 47 | 24 |  |  | Wed 10/03/10 | Wed 15/09/10
5067 | 470049 | Study on S2b Mobility based on GTP | FS_SMOG | 1 | Rel-10 | S2 | Thu 25/03/10 | Thu 10/06/10 | 100% | SP-100169 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101 | 23.834 | 47 | 24 |  |  | Wed 10/03/10 | Mon 07/06/10
5068 | 430040 | Study on Surround Sound codec extension for PSS and MBMS | FS_SS_PSS_MBMS | 1 | Rel-10 | S4 | Thu 12/03/09 | Wed 23/03/11 | 100% | SP-090019 | - | Fraunhofer Gesellschaft | jan.plogsties@iis.franhofer.de | SP#51 completed. Extend Rel-8 UID_34043 (Extending PSS and MBMS User Services for optimized Mobile TV) | 26.95 | 43 | 22 |  |  | Mon 02/02/09 | Mon 14/02/11
5069 | 480044 | Study on Improved Video Coding Support | FS_IVCS | 1 | Rel-10 | S4 | Thu 10/06/10 | Wed 23/03/11 | 100% | SP-100304 | - | Nokia, ETRI | imed.bouazizi@nokia.com, jaihyung@etri.re.kr | SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039) | 26.904 | 48 | 25 |  |  | Fri 28/05/10 | Fri 18/02/11
5070 | 410044 | Study on Rc Reference Point Functionalities and Message Flows | FS_OAM_Rc | 1 | Rel-10 | S5 | Thu 18/09/08 | Thu 25/03/10 | 100% | SP-080464 | - | Huawei | shan.mingjun@huawei.com | SP#47 completed | 32.825 | 41 | 21 |  |  | Mon 15/09/08 | Tue 23/03/10
5071 | 430044 | Study on Telecommunication Management; Energy Savings Management | FS_OAM_ESM | 1 | Rel-10 | S5 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090048 | - | Orange, Vodafone | Jean-Michel Cornilly (Orange) | SP#47 completed. Study result might impact Feature UID_420011 Self Organising Networks (SON) | 32.826 | 43 | 22 |  |  | Mon 23/02/09 | Mon 08/03/10
5072 | 440069 | Study on Integration of Device Management Information with Itf-N | FS_IDMI_Itf-N | 1 | Rel-10 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-100088 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#47 completed | 32.827 | 44 | 23 |  |  | Mon 18/05/09 | Tue 23/03/10
5073 | 460037 | Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model | FS_3GNRM_TMFSID | 1 | Rel-10 | S5 | Thu 10/12/09 | Wed 23/03/11 | 100% | SP-090759 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#51 completed | 32.828 | 46 | 24 |  |  | Tue 01/12/09 | Wed 09/03/11
5074 | 460038 | Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program (TIP) Fault Management | FS_3G_TMF_FM | 1 | Rel-10 | S5 | Thu 10/12/09 | Wed 23/03/11 | 100% | SP-090760 | - | Nokia Siemens Networks, Alcatel-Lucent | olaf.pollakowski@nsn.com, Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.829 | 46 | 24 |  |  | Tue 01/12/09 | Tue 22/03/11
5075 | 480045 | Study on Alarm Correlation and Alarm Root Cause Analysis | FS_AC_ARCA | 1 | Rel-10 | S5 | Thu 10/06/10 | Wed 23/03/11 | 100% | SP-100775 | - | Ericsson | edwin.tse@ericsson.com | SP#51 completed | 32.832 | 48 | 25 |  |  | Wed 26/05/10 | Wed 09/03/11
5076 | 480046 | Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM | FS_3G_TMF_PM | 1 | Rel-10 | S5 | Thu 10/06/10 | Wed 23/03/11 | 100% | SP-100291 | - | Alcatel-Lucent | Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.831 | 48 | 25 |  |  | Wed 26/05/10 | Tue 22/03/11
5077 | 450013 | Study on Policy and Charging Rules Function (PCRF) failure and restoration | FS_PCRF-FR | 1 | Rel-10 | C3 | Tue 18/08/09 | Fri 17/09/10 | 100% | CP-090861 | - | NEC | gottfried.punz@nw.neclab.eu | CP#49 completed | 29.816 | 45 | 23 |  |  | Tue 08/09/09 | Fri 17/09/10
5078 | 480016 | Study on User Data Convergence (UDC) evolution | FS_UDCe | 1 | Rel-10 | C4 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100296 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model | 23.845 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
5079 | 480017 | Study on UICC access to IMS | FS_IMS-UICC | 1 | Rel-10 | C6 | Fri 04/06/10 | Fri 18/03/11 | 100% | CP-100424 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.828 | 48 | 25 |  |  | Wed 26/05/10 | Thu 03/03/11
5080 | 450014 | Study on Uplink Tx Diversity for HSPA | FS_UL-TxDiv-HSPA | 1 | Rel-10 | R4 | Tue 18/08/09 | Fri 04/06/10 | 100% | RP-090987 | RP-100499 | Qualcomm | Heechoon Lee (heechoon@qualcomm.com) | RP#48 completed | UTRA 25.863 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
5081 | 460016 | Study on Solutions for Energy Saving within UTRA Node B | FS_Energy_UMTS | 1 | Rel-10 | R1,R3 | Fri 04/12/09 | Fri 17/09/10 | 100% | RP-091439 | RP-100796 | Vodafone | Prakash.bhat@vodafone.com | RP#49 completed. Based on ETSI EE TS 102 706. | UTRA 25.927 | 46 | 24 |  |  | Mon 30/11/09 | Thu 09/09/10
5082 | 470015 | Study on Potential solutions for energy saving for E-UTRAN | FS_Energy_LTE | 1 | Rel-10 | R3,R2 | Tue 02/02/10 | Fri 03/06/11 | 100% | RP-100674 | RP-110597 | China Mobile | Yang Ning (yangning@chinamobile.com) | RP#52 completed | LTE 36.927 | 47 | 24 |  |  | Fri 19/03/10 | Thu 02/06/11
5083 | 470016 | Study on Improvements of distributed antenna for 1.28Mcps TDD | FS_distr_ant_LCR_TDD | 1 | Rel-10 | R1,R2,R3 | Fri 05/03/10 | Fri 10/12/10 | 100% | RP-100178 | RP-101287 | ZTE | huang.he4@zte.com.cn | RP#50 completed. TR 25.865 v101 for Approval | UTRA 25.865 | 47 | 24 |  |  | Fri 19/03/10 | Tue 07/12/10
5084 | 400037 | Deleted - Study on Unauthenticated PS Emergency Calls | FS_UAPSEC | 1 | Rel-10 | S1 | Thu 05/06/08 | Thu 25/03/10 | 100% | SP-080320 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#47 work stopped/abandoned | 22.984 | 40 | 21 | SP-47 | PCG-24 | Thu 13/12/07 | Tue 09/03/10
5085 | 410042 | Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services | FS_eIMS_IBCF | 1 | Rel-10 | S2 | Thu 18/09/08 | Wed 15/12/10 | 100% | SP-090809 | - | Starent Networks | Rajat Ghai (rghai@starentnetworks.com) | SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS) | 23.848 | 41 | 21 | SP-50 | PCG-26 | Mon 15/09/08 | Mon 13/12/10
5086 | 440050 | Deleted - Study on EPC Charging enhancement | FS_EPCcharg | 1 | Rel-10 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090318 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#47 work stopped. Issue covered by Rel-10 UID_460039 Charging for LIPA_SIPTO and UID_4700xy Charging for IFOM | - | 44 | 23 | SP-47 | PCG-24 | Mon 18/05/09 | Mon 06/07/09
5087 | 450012 | Deleted - Study on Interworking Proxy between GTP based and PMIP based interfaces | FS_GTP-MIP-IW | 1 | Rel-10 | C4 | Fri 18/09/09 | Fri 04/06/10 | 100% | CP-090517 | - | NTT DoCoMo | takaaki.matsuura.sp@s1.nttdocomo.com | CP#48 work stopped/abandoned | 29.875 | 45 | 23 | CP-48 | PCG-25 | Tue 08/09/09 | Wed 26/05/10
5088 | 0 | --- RELEASE 9 --- | - | 1 | Rel-9 | CP,GP,RP,SP | Sat 01/01/00 | Sat 01/01/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
5089 | 400035 | Enhanced Home NodeB / eNodeB | EHNB | 1 | Rel-9 | S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP | Thu 05/06/08 | Fri 09/12/11 | 100% | SP-090214 | - | T-Mobile | michael.kurz@t-mobile.at | RP#54 Testing completed | UTRA, LTE | 40 | 21 |  |  | Thu 13/12/07 | Tue 29/11/11
5090 | 400047 | Stage 1 for EHNB | EHNB | 2 | Rel-9 | S1 | Thu 05/06/08 | Thu 04/06/09 | 100% | SP-080791 | - | T-Mobile | michael.kurz@t-mobile.at | CP#49 the SA1-reqs are moving. CT1 will align when the work in SA1 is clear. (was SP#44 completed.) | 22.220, 22.011 | 40 | 21 |  |  | Thu 13/12/07 | Mon 06/09/10
5091 | 410026 | Architecture aspects of EHNB | EHNB | 2 | Rel-9 | S2 | Thu 18/09/08 | Thu 24/09/09 | 100% | SP-080636 | - | T-Mobile | sebastian.speicher@telekom.de | SP#45 completed | 23.401, 23.402, 23.060, New 23.830 | 41 | 21 |  |  | Mon 15/09/08 | Wed 14/10/09
5092 | 420035 | Security aspects of Enhanced Home NodeB / eNodeB | EHNB-Sec | 2 | Rel-9 | S3 | Thu 11/12/08 | Thu 10/12/09 | 100% | SP-080879 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#46 completed | New 33.320 | 42 | 22 |  |  | Tue 09/12/08 | Mon 07/12/09
5093 | 450003 | CT1 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT1 | 2 | Rel-9 | C1 | Fri 18/09/09 | Fri 10/12/10 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#50 completed (Roaming aspects for manual CSG selection, Support of temporary users and CSG membership changes, Support of user controlled and operator controlled lists) | 23.122, 24.008, 24.285, 24.301 | 45 | 23 |  |  | Thu 09/07/09 | Thu 25/11/10
5094 | 450004 | CT6 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT6 | 2 | Rel-9 | C6 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#47 completed. Storing of CSG related data items on the USIM | 31.102 | 45 | 23 |  |  | Thu 09/07/09 | Tue 16/03/10
5095 | 420036 | 3G HNB Gateway and LTE HeNB Gateway OAM&P | HNB-OAM_GW | 2 | Rel-9 | S5 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-100087 | - | China Mobile | GangChen (chengang@chinamobile.com) | SP#47 completed | 32.632, 32.633, 32.635, New (32.771, 32.772, 32.773, 32.775, 32.781, 32.782, 32.783, 32.785) | 42 | 22 |  |  | Wed 03/12/08 | Mon 22/03/10
5096 | 430012 | 3G HNB and LTE HeNB OAM&P Type 1 Interface | HNB_eHNB-OAM_Type1 | 2 | Rel-9 | S5 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090208 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#47 completed | 32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594) | 43 | 22 |  |  | Mon 09/03/09 | Mon 08/03/10
5097 | 440066 | 3G HNB and LTE HeNB OAM&P Type 2 Interface | HNB_eHNB-OAM_Type2 | 2 | Rel-9 | S5 | Fri 15/05/09 | Thu 25/03/10 | 100% | SP-090315 | - | Ericsson | edwin.tse@ericsson.com | SP#47 completed | New (32.571, 32.572) | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
5098 | 420008 | LTE FDD Home eNodeB RF Requirements | HeNB-RF_FDD | 2 | Rel-9 | R4 | Fri 05/12/08 | Fri 19/03/10 | 100% | RP-091300 | RP-100035 | Motorola | Ying Cai (yingcai@motorola.com) | RP#47 completed | 36.104, 36.141, New 36.921 | 42 | 22 |  |  | Thu 04/12/08 | Tue 16/03/10
5099 | 430005 | LTE TDD Home eNodeB RF Requirements | HeNB-RF_TDD | 2 | Rel-9 | R4 | Fri 06/03/09 | Fri 19/03/10 | 100% | RP-091386 | RP-100036 | China Mobile | Nan Li (linan@chinamobile.com) | RP#47 completed | 36.104, 36.141, 36.300, 36.331, 36.413, New 36.922 | 43 | 22 |  |  | Tue 03/03/09 | Tue 16/03/10
5100 | 430025 | Home NB and Home eNB enhancements - RAN3 aspects | EHNB-RAN3 | 2 | Rel-9 | R3 | Fri 06/03/09 | Fri 04/12/09 | 100% | RP-090349 | RP-091050 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#46 completed (based on high priority items specified in RP-090995) | 25.413, 25.467, 25.467, 25.468, 25.469, 25.469, 36.401, 36.413, New 25.444 | 43 | 22 |  |  | Tue 10/03/09 | Fri 27/11/09
5101 | 430026 | Home NB and Home eNB enhancements - RAN2 aspects | EHNB-RAN2 | 2 | Rel-9 | R2 | Fri 06/03/09 | Fri 19/03/10 | 100% | RP-091392 | RP-100037 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#47 completed | 25.304, 25.331, 25.367, 36.300, 36.304, 36.331 | 43 | 22 |  |  | Tue 10/03/09 | Tue 16/03/10
5102 | 490020 | Conformance Test Aspects – Home NB enhancements for FDD | EHNB-UTRA_FDD_UEConTest | 2 | Rel-9 | R5 | Fri 17/09/10 | Fri 09/12/11 | 100% | RP-111315 | RP-111679 | Huawei | trica_li@huawei.com | UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367) | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Thu 09/09/10 | Wed 07/12/11
5103 | 500023 | Conformance Test Aspects – Home eNB enhancements | EHNB-LTE_UEConTest | 2 | Rel-9 | R5 | Fri 10/12/10 | Fri 16/09/11 | 100% | RP-101191 | RP-110972 | Qualcomm | Mrs Lena Chaponniere (lchaponn@qualcomm.com) | RP#53 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 50 | 26 |  |  | Fri 10/12/10 | Tue 06/09/11
5104 | 440001 | Home NB and Home eNB enhancements - GERAN aspects | EHNB-GERAN | 2 | Rel-9 | GP | Mon 18/05/09 | Fri 03/09/10 | 100% | GP-090975 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#47 completed. GP#42 WID approved | 43.055, 43.129, 44.018, 44.060, 45.008, 48.008, 48.018 | 42 | 23 |  |  | Mon 18/05/09 | Sat 04/09/10
5105 | 370026 | Value-Added Services for Short Message Service | VAS4SMS | 1 | Rel-9 | S1,C4,C1 | Mon 10/09/07 | Fri 04/12/09 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | - | 37 |  |  |  | Tue 02/10/07 | Mon 16/11/09
5106 | 370126 | Stage 1 for VAS4SMS | VAS4SMS | 2 | Rel-9 | S1 | Mon 10/09/07 | Wed 12/03/08 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | SP#39 completed. SP#43 Feature moved to Rel-9 | new 22.142 | 37 |  |  |  | Tue 02/10/07 | Wed 04/03/09
5107 | 410011 | CT4 aspects of VAS4SMS Interface and Signalling Flow | VAS4SMS | 2 | Rel-9 | C4 | Fri 12/09/08 | Fri 04/12/09 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | new 23.142 | 41 | 21 |  |  | Thu 11/09/08 | Wed 02/12/09
5108 | 410014 | CT1 aspects of VAS4SMS Interface and Signalling Flow | VAS4SMS | 2 | Rel-9 | C1 | Tue 09/09/08 | Fri 04/12/09 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | 23.04 | 41 | 21 |  |  | Thu 11/09/08 | Wed 02/12/09
5109 | 370027 | Definition of End-User Identity | EUI | 1 | Rel-9 | S1 | Mon 03/09/07 | Thu 11/12/08 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | - | 38 |  |  |  | Tue 02/10/07 | Thu 05/08/10
5110 | 410024 | Stage 1 for Definition of End-User Identity | EUI | 2 | Rel-9 | S1 | Mon 03/09/07 | Thu 11/12/08 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | 21.905 | 38 | 21 |  |  | Tue 02/10/07 | Thu 11/06/09
5111 | 380067 | Customized Ringing Signal | CRS | 1 | Rel-9 | S1,C1 | Thu 06/12/07 | Thu 03/12/09 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | CP#48 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Fri 28/05/10
5112 | 410025 | Stage 1 for Customized Ringing Signal | CRS | 2 | Rel-9 | S1 | Thu 06/12/07 | Thu 11/12/08 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | SP#42 completed. | 22.173, new 22.183 | 38 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
5113 | 440041 | Stage 3 for IMS Customized Ringing Signal (CRS) Service | CRS | 2 | Rel-9 | C1 | Fri 29/05/09 | Thu 03/12/09 | 100% | CP-090444 | - | China Mobile | wangzhao | CP#48 completed | 24.173, new 24.183 | 44 | 23 |  |  | Wed 13/05/09 | Fri 28/05/10
5114 | 380057 | Public Warning System | PWS | 1 | Rel-9 | S1,C1,C4,R2,R3,R5 | Thu 06/12/07 | Fri 07/12/12 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | TSG#46 completed. Larger scope than Rel-8 Feature UID_370051 (ETWS). Triggered by TR 22.968 Study UID_320025 (FS_PWS) | LTE | 38 | 21 |  |  | Thu 13/12/07 | Thu 03/12/09
5115 | 380058 | Stage 1 for Public Warning System | PWS | 2 | Rel-9 | S1 | Thu 06/12/07 | Thu 11/12/08 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | SP#42 completed | 22.268 | 38 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
5116 | 440029 | Stage 3 for Public Warning System | PWS-St3 | 2 | Rel-9 | C1,C4 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | RP#46 completed | - | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
5117 | 440030 | CT1 aspects of Stage 3 for Public Warning System | PWS-St3 | 3 | Rel-9 | C1 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 23.041 | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
5118 | 440031 | CT4 aspects of Stage 3 for Public Warning System | PWS-St3 | 3 | Rel-9 | C4 | Sat 30/05/09 | Fri 04/12/09 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 29.168 | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
5119 | 440005 | Public Warning System (PWS) – RAN aspects | PWS-RAN | 2 | Rel-9 | R2,R3 | Sat 30/05/09 | Fri 04/12/09 | 100% | RP-090649 | RP-091052 | AT&T | don.zelmer@att.com | RP#46 completed | LTE 36.300, 36.302, 36.331, 36.413 | 44 | 23 |  |  | Wed 20/05/09 | Thu 03/12/09
5120 | 540005 | Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE | PWS-RAN_UEConTest | 2 | Rel-9 | R5 | Fri 02/12/11 | Fri 07/12/12 | 100% | RP-111564 | RP-121525 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#58 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Tue 04/12/12
5121 | 400031 | Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 1 | Rel-9 | S1,C1 | Thu 05/06/08 | Fri 04/06/10 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | CP#48 completed | - | 40 | 21 |  |  | Thu 13/12/07 | Fri 28/05/10
5122 | 400043 | Stage 1 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | S1 | Thu 05/06/08 | Thu 05/06/08 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | SP#40 completed | 22.259 | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
5123 | 430002 | Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | C1 | Fri 06/03/09 | Fri 04/12/09 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#46 completed | 23.259 | 43 | 22 |  |  | Thu 05/03/09 | Mon 16/11/09
5124 | 430102 | Stage 3 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | C1 | Mon 09/03/09 | Fri 04/06/10 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#48 completed | 24.259 | 43 | 22 |  |  | Thu 05/03/09 | Fri 28/05/10
5125 | 400032 | Multi-Media Telephony Service enhancements | eMMTel | 1 | Rel-9 | S1,S5,C1 | Thu 05/06/08 | Thu 25/03/10 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed | - | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
5126 | 400044 | Stage 1 for eMMTel | eMMTel | 2 | Rel-9 | S1 | Thu 05/06/08 | Thu 11/12/08 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#42 completed | 22.173 | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
5127 | 430031 | Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services) | eMMTel-SS-CH | 2 | Rel-9 | S5 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090196 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#47 completed | 32.275, 32.298, 32.299 | 43 | 22 |  |  | Thu 26/02/09 | Mon 08/03/10
5128 | 430032 | Support of Real-time Transfer of Tariff Information (RTTI) in IMS charging | IMSTSS-RTTI-CH | 2 | Rel-9 | S5 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090306 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#47 completed. Linked to SA5 Rel-8 UID_380042 AoC support in IMS Charging (IMSTSS) | 32.240, 32.280, 32.298, 32.299 | 43 | 22 |  |  | Thu 26/02/09 | Mon 08/03/10
5129 | 440032 | Stage 3 - Enhancements for Completion of Communications Supplementary service | eMMTel-CC | 2 | Rel-9 | C1 | Sat 30/05/09 | Fri 04/12/09 | 100% | CP-090490 | - | France Telecom | Youssef.chadli@orange-ftgroup.com | CP#46 completed | 24.642 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
5130 | 400034 | User Data Convergence (UDC) | UDC | 1 | Rel-9 | S1,S5,C4 | Thu 05/06/08 | Thu 10/06/10 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808 | - | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
5131 | 400046 | Stage 1 for User Data Convergence (UDC) | UDC | 2 | Rel-9 | S1 | Thu 05/06/08 | Thu 11/12/08 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#42 completed | 22.101, new 22.985 | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
5132 | 430103 | Stage 2/3 for User Data Convergence (UDC) Technical Realization | UDC-CN | 2 | Rel-9 | C4 | Fri 06/03/09 | Fri 19/03/10 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | - | - | 43 | 22 |  |  | Wed 04/03/09 | Tue 09/03/10
5133 | 430003 | User Data Convergence (UDC) Technical Realization (Stage 2) | UDC-CN | 3 | Rel-9 | C4 | Fri 06/03/09 | Fri 19/03/10 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | CP#47 completed | new 23.335 | 43 | 22 |  |  | Wed 04/03/09 | Tue 09/03/10
5134 | 450002 | User Data Convergence (UDC) Protocol Description | UDC-CN | 3 | Rel-9 | C4 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090516 | - | China Mobile, Ericsson | Lan Si Zhong (lansizhong@chinamobile.com), emiliano.merino@ericsson.com | CP#47 completed | new 29.335 | 45 | 23 |  |  | Wed 04/03/09 | Tue 09/03/10
5135 | 440060 | User Data Convergence (UDC) Modelling and Management | UDC-MMAN | 2 | Rel-9 | S5 | Thu 04/06/09 | Thu 10/06/10 | 100% | SP-090309 | - | T-Mobile, China Mobile, Ericsson | istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com | SP#48 completed | - | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
5136 | 440062 | UDC – Framework for Model Handling and Management | UDC-MMAN-MFRM | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 10/06/10 | 100% | SP-090311 | - | T-Mobile | istvan.aba@t-mobile.at | SP#48 completed | 32.172, new 32.181 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
5137 | 440061 | UDC – Common Baseline Information Model | UDC-MMAN-CBIM | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090310 | - | China Mobile, Ericsson | Lan Si Zhong, Miguel Garcia | SP#47 completed | 32.172, new 32.182 | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
5138 | 410032 | IMS Services Centralization and Continuity | IMS_SCC | 1 | Rel-9 | S1,S2,C1 | Thu 18/09/08 | Fri 19/03/10 | 100% | SP-080633 | - | NEC | joerg.swetina@neclab.eu | CP#47 completed | - | 41 | 21 |  |  | Mon 15/09/08 | Thu 04/03/10
5139 | 410033 | Stage 1 - Inter-Device Transfer – Requirements | IMS_SCC-IDT | 2 | Rel-9 | S1 | Thu 18/09/08 | Thu 11/12/08 | 100% | SP-080507 | - | NEC | joerg.swetina@neclab.eu | SP#42 completed | 22.101, 22.228 | 41 | 21 |  |  | Mon 15/09/08 | Fri 05/12/08
5140 | 410134 | Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions | IMS_SCC-SPI | 2 | Rel-9 | S2,C1 | Thu 18/09/08 | Fri 19/03/10 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | - | - | 41 | 21 |  |  | Mon 15/09/08 | Fri 20/07/12
5141 | 410034 | Stage 2 for IMS Service Continuity Enhancements: Service, Policy and Interactions | IMS_SCC-SPI | 3 | Rel-9 | S2 | Thu 18/09/08 | Thu 04/06/09 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | SP#57 Removal of the MSC server assisted mid-call feature from Rel-9 by 23.237CR#0433 (CT1 proposed moving this feature to Rel-10). SP#44 completed. TR 23.838 for Approval | 23.237, 23.292, 23.216, new 23.838 | 41 | 21 |  |  | Mon 15/09/08 | Fri 20/07/12
5142 | 440034 | Stage 3 for IMS Service Continuity Enhancements: Service, Policy, Interactions and Inter UE Transfer | IMS_SCC-SPI | 3 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090440 | - | Qualcomm | Roozbeh Atarius (ratarius@qualcomm.com) | CP#47 completed | 24.216, 24.229, 24.237 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5143 | 410135 | Stage 2/3 for IMS Centralized Services | IMS_SCC-ICS | 2 | Rel-9 | S2,C1 | Thu 18/09/08 | Fri 19/03/10 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | - | 41 | 21 |  |  | Mon 15/09/08 | Tue 02/06/09
5144 | 410035 | Stage 2 for IMS Centralized Services | IMS_SCC-ICS | 3 | Rel-9 | S2 | Thu 18/09/08 | Thu 04/06/09 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#44 completed. TR 23.883 for Information + Approval | 23.292, new 23.883 | 41 | 21 |  |  | Mon 15/09/08 | Tue 02/06/09
5145 | 440033 | Stage 3 for Enhancements to IMS Centralized Services | IMS_SCC-ICS | 3 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090883 | - | Nokia Siemens Networks | Peter.Leis@nsn.com | CP#47 completed | 24.292, 24.604, 24.607, 24.608, 24.611, 24.623 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5146 | 430004 | Stage 3 - IMS Centralized Services support via I1 interface | IMS_SCC-ICS_I1 | 2 | Rel-9 | C1 | Fri 06/03/09 | Fri 19/03/10 | 100% | CP-090640 | - | Huawei | Lili Yang(kadyyang@huawei.com) | CP#47 completed | 24.237, 24.292, new 24.294 | 43 | 22 |  |  | Thu 05/03/09 | Tue 02/03/10
5147 | 420020 | Service Specific Access Control in EPS | SSAC | 1 | Rel-9 | S1,C1,R5 | Thu 11/12/08 | Fri 15/06/12 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | CP#47 completed. Triggered by TR 22.986 Study on Service Specific Access Control in EPS. As EPS is a PS-Domain only system, Domain Specific Access Control (DSAC) doesn't apply, hence SSAC allows restriction of voice and non-voice calls separately | - | 42 | 22 |  |  | Fri 05/12/08 | Thu 04/03/10
5148 | 420021 | Stage 1 for Service Specific Access Control in EPS | SSAC | 2 | Rel-9 | S1 | Thu 11/12/08 | Thu 11/12/08 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | SP#42 completed. If UE supports E-UTRA and IMS, SSAC is a mandatory Rel-9 function (during congestion in emergency case earthquake/tsunami improves mobile communications). | 22.011 CR0136 | 42 | 22 |  |  | Fri 05/12/08 | Tue 09/02/10
5149 | 440040 | Stage 3 for Service Specific Access Control in EPS | SSAC | 2 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090885 | - | NTT DoCoMo | Hideyuki Yamashita (yamashitahi@s1.nttdocomo.co.jp) | CP#47 completed | 24.173, 27.007 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5150 | 520014 | Conformance Test Aspects - Service Specific Access Control | SSAC_UEConTest | 2 | Rel-9 | R5 | Tue 07/06/11 | Fri 15/06/12 | 100% | RP-110765 | RP-120447 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#56 completed. Testing for Stage 3 for Service Specific Access Control in EPS (24.173, 27.007) UID_440040 | 34.229-1, 34.229-2, 34.229-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 05/06/12
5151 | 380064 | Support for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 1 | Rel-9 | S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF | Mon 03/01/00 | Fri 13/06/14 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | RP#56 completed testing. CP#47 completed. SP#48 completed | GERAN, LTE | 38 | 21 |  |  | Tue 02/10/07 | Tue 05/06/12
5152 | 410036 | Stage 1 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | S1 | Mon 14/01/08 | Thu 11/12/08 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#42 completed | 22.101 | 38 | 21 |  |  | Mon 15/09/08 | Tue 09/12/08
5153 | 410037 | Stage 2 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | S2 | Mon 14/01/08 | Thu 04/06/09 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#44 completed | 23.869, 23.060, 23.167, 23.203, 23.221, 23.228, 23.271, 23.401, 23.402 | 38 | 21 |  |  | Mon 15/09/08 | Mon 01/06/09
5154 | 420022 | Security aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS-Sec | 2 | Rel-9 | S3 | Fri 12/12/08 | Thu 10/06/10 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#48 completed | 33.401, 33.402 | 42 | 22 |  |  | Tue 09/12/08 | Wed 05/05/10
5155 | 440035 | Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | C1,C3,C4,R5 | Fri 29/05/09 | Fri 15/06/12 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | RP#56 completed testing. CP#47 completed | GERAN, LTE | 44 | 23 |  |  | Wed 13/05/09 | Tue 05/06/12
5156 | 440036 | CT1 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC1 | 3 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#47 completed | 23.122, 24.008, 24.229, 24.301, 24.302 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5157 | 480029 | Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS_UEConTest | 3 | Rel-9 | R5 | Fri 04/06/10 | Fri 15/06/12 | 100% | RP-100567 | RP-120445 | Samsung | stoyan.baev@partner.samsung.com | RP#56 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2, 34.229-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 48 | 25 |  |  | Fri 04/06/10 | Tue 05/06/12
5158 | 440037 | CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC3 | 3 | Rel-9 | C3 | Fri 29/05/09 | Fri 18/09/09 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#45 completed | 29.212, 29.213, 29.214, 29.215 | 44 | 23 |  |  | Wed 13/05/09 | Wed 09/09/09
5159 | 440038 | CT4 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC4 | 3 | Rel-9 | C4 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#46 completed | 23.003, 23.008, 29.060, 29.272, 29.273, 29.274, 29.275, 29.276 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
5160 | 420041 | Support for IMS Emergency Calls over LTE | IMS_EMER_LTE | 2 | Rel-9 | R2,R3 | Mon 03/01/00 | Mon 16/10/00 | 100% | RP-081140 | RP-090698 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.331, 36.413 | 42 | 22 |  |  | Wed 18/02/09 | Wed 09/05/12
5161 | 470017 | Conformance Test Aspects – Support for IMS Emergency Calls over LTE | IMS_EMER_LTE_UEConTest | 2 | Rel-9 | R5 | Thu 25/03/10 | Fri 10/12/10 | 100% | RP-100118 | RP-101068 | Ericsson | leif.mattisson@ericsson.com | RP#50 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 47 | 24 |  |  | Wed 10/03/10 | Wed 08/12/10
5162 | 410038 | Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 2 | Rel-9 | S2,C1,C4,C3,IETF | Thu 18/09/08 | Fri 13/06/14 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | CP#56 added IETF dependency | - | 41 | 21 |  |  | Mon 15/09/08 | Thu 05/03/09
5163 | 410138 | SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 3 | Rel-9 | S2 | Thu 18/09/08 | Thu 10/12/09 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | SP#46 completed | 23.870, 23.216, 23.237 | 41 | 21 |  |  | Mon 15/09/08 | Wed 25/11/09
5164 | 460018 | CT aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 3 | Rel-9 | C1,C4,C3,IETF | Fri 29/05/09 | Fri 13/06/14 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | - | 46 | 24 |  |  | Wed 13/05/09 | Wed 02/12/09
5165 | 440027 | CT1 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C1 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 24.229, 24.237 | 44 | 23 |  |  | Wed 13/05/09 | Wed 02/12/09
5166 | 440028 | CT4 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C4 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.205, 29.280 | 44 | 23 |  |  | Wed 13/05/09 | Wed 02/12/09
5167 | 460019 | CT3 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C3 | Fri 04/12/09 | Fri 04/12/09 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.163 | 46 | 24 |  |  | Wed 13/05/09 | Wed 02/12/09
5168 | 561003 | (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254) | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C3-IETF | Fri 20/04/12 | Fri 13/06/14 | 100% | CP-090882 | - | Andrew Allen | Andrew Allen | CP#64 completed | RFC 7254 (was draft-montemurro-gsma-imei-urn) | 56 | 29 |  |  | Fri 20/04/12 | Fri 06/06/14
5169 | 430006 | LCS for LTE and EPS | LCS_LTE_EPS | 1 | Rel-9 | S2,C1,C4,R2,R1,R3,R4,R5 | Thu 05/06/08 | Fri 02/03/12 | 100% | - | - | - | - | - | LTE | 43 | 22 |  |  | Wed 18/02/09 | Tue 16/03/10
5170 | 400038 | LCS Control Plane Solution for EPS | LCS_EPS-CPS | 2 | Rel-9 | S2,C4,C1 | Thu 05/06/08 | Fri 19/03/10 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | Triggered by abandoned Study UID_380068 (FS_LCS_EPS). Linked to Feature UID_380064 Support for IMS Emergency Calls over GPRS and EPS | - | 40 | 21 |  |  | Thu 13/12/07 | Sat 22/11/08
5171 | 400048 | Stage 2 for LCS Control Plane Solution for EPS | LCS_EPS-CPS | 3 | Rel-9 | S2 | Thu 05/06/08 | Thu 04/06/09 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | SP#44 completed | 23.891, 23.271, 23.401, 23.402 | 40 | 21 |  |  | Thu 13/12/07 | Mon 01/06/09
5172 | 440020 | CT4 aspects of Control Plane LCS in the EPC | LCS_EPS-CPS | 3 | Rel-9 | C4 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed (IANA registrations outstanding). Stage 3 SLs and SLg interfaces & transport of positioning messages between E-SMLC and MME in the scope of UID_420006 (Positioning Support for LTE) | 24.080, 29.002, 29.272, 29.230, new 24.171, 29.171, 29.172, 29.173 | 44 | 23 |  |  | Wed 13/05/09 | Tue 09/03/10
5173 | 440120 | CT1 aspects of Control Plane LCS in the EPC | LCS_EPS-CPS | 3 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed | 24.301 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5174 | 420006 | Positioning Support for LTE | LCS_LTE | 2 | Rel-9 | R2,R1,R3,R4 | Fri 05/12/08 | Fri 05/12/08 | 100% | RP-091389 | RP-100442 | Qualcomm | Nathan Tenny (ntenny@qualcomm.com) | RP#48 completed. UID_400038 (LCS Control Plane Solution for EPS) depends on this WI | 34.213, 36.133, 36.211, 36.214, 36.300, 36.305, 36.331, 36.355, 36.410, 36.413, 36.455, new 36.171 | 42 | 22 |  |  | Wed 03/12/08 | Tue 01/06/10
5175 | 470018 | Conformance Test Aspects – Positioning Support for LTE | LCS_LTE_UEConTest | 2 | Rel-9 | R5 | Fri 19/03/10 | Fri 02/03/12 | 100% | RP-111209 | RP-120034 | Qualcomm | Shubhang Vora (svoral@qualcomm.com) | RP#55 completed. RP#56 TS 37.571-4 v200 for Approval | 36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5) | 47 | 24 |  |  | Wed 17/03/10 | Wed 06/06/12
5176 | 400039 | MBMS support in EPS | MBMS_EPS | 1 | Rel-9 | S2,S3,S5,C3,C4,R2,R3,R4,R5 | Thu 05/06/08 | Fri 09/12/11 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | RP#47 completed. SP#46, CP#46 completed | LTE | 40 | 21 |  |  | Thu 13/12/07 | Tue 16/03/10
5177 | 400040 | Stage 2 for MBMS support in EPS | MBMS_EPS | 2 | Rel-9 | S2 | Thu 05/06/08 | Thu 04/06/09 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#44 completed | 23.246 | 40 | 21 |  |  | Thu 13/12/07 | Mon 01/06/09
5178 | 420023 | Security for MBMS support in EPS | MBMS_EPS | 2 | Rel-9 | S3 | Thu 11/12/08 | Thu 10/12/09 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#46 completed | 33.246 | 42 | 22 |  |  | Tue 09/12/08 | Wed 09/12/09
5179 | 430033 | MBMS Charging in EPS | MBMS_EPS | 2 | Rel-9 | S5 | Fri 06/03/09 | Thu 10/12/09 | 100% | SP-090052 | - | ZTE | guo.wenjie1@zte.com.cn | SP#46 completed | 32.273, 32.251, 32.298, 32.299 | 43 | 22 |  |  | Mon 23/02/09 | Tue 01/12/09
5180 | 440025 | CT4 aspects of MBMS support in EPS (Stage 3) | MBMS_EPS | 2 | Rel-9 | C4 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090325 | - | China Mobile, ZTE | wangjingyf@chinamobile.com, lu.fei1@zte.com.cn | CP#46 completed | 29.274, 29.281, 23.007, 23.008 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
5181 | 440026 | CT3 aspects of MBMS support in EPS (Stage 3) | MBMS_EPS | 2 | Rel-9 | C3 | Fri 29/05/09 | Fri 04/12/09 | 100% | CP-090330 | - | ZTE, China Mobile | zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com | CP#46 completed | 29.061 | 44 | 23 |  |  | Wed 13/05/09 | Wed 25/11/09
5182 | 430007 | MBMS support in LTE | MBMS_LTE | 2 | Rel-9 | R2,R3,R4 | Fri 06/03/09 | Fri 19/03/10 | 100% | RP-091457 | RP-100033 | Huawei | arnaud.meylan@huawei.com | RP#47 completed | 25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445 | 43 | 22 |  |  | Tue 10/03/09 | Tue 16/03/10
5183 | 500024 | Conformance Test Aspects – MBMS support in LTE | MBMS_LTE-UEConTest | 2 | Rel-9 | R5 | Fri 10/12/10 | Fri 09/12/11 | 100% | RP-101245 | RP-111437 | Huawei | Zhang Xin (zhangxin0208@huawei.com) | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 50 | 26 |  |  | Fri 10/12/10 | Tue 29/11/11
5184 | 420024 | Access Network Discovery and Selection Function enhancements | eANDSF | 1 | Rel-9 | S2,C1 | Thu 11/12/08 | Fri 19/03/10 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8 | 22.278, SA3 33.402 CR#0055 | 42 | 22 |  |  | Fri 05/12/08 | Thu 04/03/10
5185 | 420040 | Stage 2 for Access Network Discovery and Selection Function enhancements | eANDSF | 2 | Rel-9 | S2 | Thu 11/12/08 | Thu 04/06/09 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | SP#44 completed | 23.402, 23.002 | 42 | 22 |  |  | Fri 05/12/08 | Mon 01/06/09
5186 | 450006 | CT1 aspects of Access Network Discovery and Selection Function enhancements | eANDSF | 2 | Rel-9 | C1 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090742 | - | Panasonic | benjamin.limck@sg.panasonic.com | CP#47 completed | 24.302, 24.312 | 45 | 23 |  |  | Tue 08/09/09 | Tue 02/03/10
5187 | 430034 | Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 1 | Rel-9 | S2,C4,C1 | Fri 13/03/09 | Fri 19/03/10 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | CP#47 completed. Continues Rel-8 SAES Stage 2 UID_320005. Stage 1 in 22.278 (EPS Service requirements) | - | 43 | 22 |  |  | Thu 05/03/09 | Thu 04/03/10
5188 | 430134 | Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | S2 | Fri 13/03/09 | Thu 04/06/09 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | SP#44 completed | 23.060, 23.203, 23.401, 23.402 | 43 | 22 |  |  | Thu 05/03/09 | Tue 08/09/09
5189 | 450007 | CT4 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | C4 | Fri 18/09/09 | Fri 04/12/09 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#46 completed | 29.275, 23.008, 29.282 | 45 | 23 |  |  | Thu 05/03/09 | Mon 16/11/09
5190 | 450008 | CT1 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | C1 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#47 completed | 24.302 | 45 | 23 |  |  | Thu 05/03/09 | Tue 02/03/10
5191 | 450049 | System aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 1 | Rel-9 | S2,S4,C1,C3,R2,IETF | Mon 07/05/07 | Wed 12/09/12 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE | LTE | 45 | 23 |  |  | Thu 28/05/09 | Mon 03/09/12
5192 | 450050 | SA2 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S2 | Thu 04/06/09 | Thu 24/09/09 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#45 completed (CR adding support for Explicit Congestion Notification) | 23.401 CR#1103r3 | 45 | 23 |  |  | Thu 28/05/09 | Mon 21/09/09
5193 | 450051 | SA4 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S4 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090653 | - | Qualcomm | Nikolai Leung | SP#46 completed | 26.114 | 45 | 23 |  |  | Thu 28/05/09 | Mon 07/12/09
5194 | 440013 | Vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | R2 | Sat 30/05/09 | Fri 18/09/09 | 100% | RP-090978 | RP-090704 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.300 CR#0114 | 44 | 23 |  |  | Thu 28/05/09 | Sat 24/10/09
5195 | 521005 | (IETF) SA4 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S4-IETF | Thu 04/06/09 | Wed 12/09/12 | 100% | SP-090653 | - | Lionel Morand | - | SP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
5196 | 521006 | (IETF) CT aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | C1-IETF,C3-IETF,C4-IETF | Mon 07/05/07 | Fri 07/09/12 | 100% | SP-090653 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
5197 | 33025 | Access Security Enhancements | ACCSEC2 | 1 | Rel-9 | S3 | Mon 02/07/07 | Thu 04/06/09 | 100% | SP-040865 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security) | 33.102, 43.020 | 26 |  |  |  | Thu 24/03/05 | Fri 06/08/10
5198 | 410027 | Protection against Unsolicited Communication for IMS (PUCI) | PUCI | 1 | Rel-9 | S3,S1 | Thu 18/09/08 | Thu 10/12/09 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 TR 33.937 completed but no specification work done in Rel-9. Related work in OMA Categorization Based Content Screening | - | 41 | 21 |  |  | Mon 15/09/08 | Mon 07/12/09
5199 | 410028 | Stage 1 for PUCI | PUCI | 2 | Rel-9 | S1 | Thu 18/09/08 | Thu 11/12/08 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#42 completed | 22.228 | 41 | 21 |  |  | Mon 15/09/08 | Fri 05/12/08
5200 | 410029 | SA3 work on PUCI | PUCI | 2 | Rel-9 | S3 | Thu 18/09/08 | Thu 10/12/09 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 completed. No normative work done in Rel-9 | New 33.937 | 41 | 21 |  |  | Mon 15/09/08 | Mon 07/12/09
5201 | 430036 | IMS Media Plane Security | MEDIASEC | 1 | Rel-9 | S3,C1,C4,C3,IETF | Fri 01/03/02 | Fri 14/09/12 | 94% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | - | - | 43 | 22 |  |  | Wed 11/02/09 | Mon 03/09/12
5202 | 430136 | SA3 aspects of IMS Media Plane Security | MEDIASEC | 2 | Rel-9 | S3 | Fri 13/03/09 | Thu 25/03/10 | 100% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | New 33.828, 33.328 | 43 | 22 |  |  | Wed 11/02/09 | Mon 01/03/10
5203 | 521007 | (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security | MEDIASEC | 2 | Rel-9 | S3-IETF,C1-IETF,C3-IETF | Wed 18/03/09 | Fri 14/09/12 | 100% | SP-090128 | - | Peter Dawes | - | CP#57 completed, ietf-draft discontinued, documented within 3GPP | draft-dawes-dispatch-mediasec-parameter | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
5204 | 870075 | (IETF) Security Considerations for WebRTC (draft-ietf-rtcweb-security) | MEDIASEC | 2 | Rel-9 | S3-IETF | Fri 01/03/02 | Fri 14/09/12 | 90% |  |  |  |  | 9/4/21: RFC 8826 added; | RFC 8826 | 87 | 44 |  |  | Mon 20/06/11 | Fri 09/04/21
5205 | 460020 | CN aspects of IMS Media Plane Security | MEDIASEC_CORE | 2 | Rel-9 | C1,C4,C3 | Fri 18/09/09 | Fri 04/06/10 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | - | 45 | 23 |  |  | Wed 11/02/09 | Wed 02/12/09
5206 | 450010 | CT1 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C1 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 23.218, 24.229 | 45 | 23 |  |  | Wed 11/02/09 | Tue 02/03/10
5207 | 450021 | CT4 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C4 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 29.238, 23.334, 29.334 | 45 | 23 |  |  | Wed 11/02/09 | Tue 09/03/10
5208 | 460021 | CT3 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C3 | Fri 04/12/09 | Fri 04/06/10 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | 29.162 | 46 | 24 |  |  | Wed 02/12/09 | Thu 27/05/10
5209 | 440053 | GBAPush enhancements (Generic push layer) | eGBAPush | 1 | Rel-9 | S3 | Wed 12/03/08 | Thu 25/03/10 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed | New 33.224 | 44 | 23 |  |  | Wed 11/02/09 | Mon 21/09/09
5210 | 420039 | SA3 part of eGBAPush (Generic push layer) | eGBAPush | 2 | Rel-9 | S3 | Wed 12/03/08 | Thu 25/03/10 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#47 completed | New 33.224 | 39 | 21 |  |  | Sat 22/03/08 | Tue 23/02/10
5211 | 440054 | Extended Identity Management | GBA-IdM | 1 | Rel-9 | S3 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090284 | - | Nokia | Silke.Holtmanns@nokia.com | SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous) | New 33.924, CT4 29.109 (added service code) | 44 | 23 |  |  | Mon 18/05/09 | Tue 23/02/10
5212 | 440056 | Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 1 | Rel-9 | S3,IETF | Thu 04/06/09 | Fri 07/12/12 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | Continuation of Rel-8 UID_390044 SAE security architecture. Covers gaps in backhaul security in SAE (also applicable to UTRAN and GERAN backhaul) | - | 44 | 23 |  |  | Mon 18/05/09 | Sat 24/11/12
5213 | 440156 | SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | S3 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | 33.102, 33.210, 33.310, 33.401, 33.402 | 44 | 23 |  |  | Mon 18/05/09 | Mon 01/03/10
5214 | 521008 | (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | S3-IETF | Thu 04/06/09 | Fri 07/12/12 | 100% | SP-090286 | - | Bengt Sahlin | - | CP#58 completed | RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols) | 52 | 27 |  |  | Mon 20/06/11 | Sat 24/11/12
5215 | 440256 | Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | C4 | Thu 04/06/09 | Fri 04/12/09 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | CP#46 completed. No impact on CT4 specs | - | 44 | 23 | CP-46 | PCG-24 | Mon 18/05/09 | Wed 25/11/09
5216 | 440057 | 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 1 | Rel-9 | S3,C1,C4,G2,G3new | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090287 | - | Ericsson | Karl Norrman | Allow 128 as an alternative to 64 bit keys (Stage 2/3 + Test spec) | - | 44 | 23 |  |  | Mon 18/05/09 | Wed 25/11/09
5217 | 440157 | SA3 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | S3 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#46 completed | 33.102,43.020, New 55.226 | 44 | 23 |  |  | Mon 18/05/09 | Mon 01/03/10
5218 | 440357 | CT1 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | C1 | Thu 04/06/09 | Fri 18/09/09 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#45 completed | 24.008,44.064 | 44 | 23 |  |  | Mon 18/05/09 | Tue 08/09/09
5219 | 440457 | CT4 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | C4 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060 | - | 44 | 23 |  |  | Mon 18/05/09 | Mon 16/11/09
5220 | 440557 | GERAN2 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | G2 | Thu 04/06/09 | Fri 04/09/09 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#43 WID approved + completed | 44.018,48.008,48.018,48.058 | 44 | 23 |  |  | Mon 18/05/09 | Wed 06/01/10
5221 | 440657 | GERAN3new (testing) part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | G3new | Thu 04/06/09 | Fri 20/11/09 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#44 completed. GP#43 WID approved | 51.01 | 44 | 23 |  |  | Mon 18/05/09 | Fri 20/11/09
5222 | 440257 | Deleted - SA2 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | S2 | Thu 04/06/09 | Thu 24/09/09 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#45 work stopped/abandoned | 23.06 | 44 | 23 | SP-45 | PCG-23 | Mon 18/05/09 | Mon 07/09/09
5223 | 420027 | Timed Graphics | TG | 1 | Rel-9 | S4 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-080683 | - | Ericsson | clinton.priddle@ericsson.com | SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142) | 26.114, 26.140, 26.234, 26.244, 26.245, 26.346, New 26.430 | 42 | 22 |  |  | Sun 23/11/08 | Mon 01/02/10
5224 | 430037 | Managing MTSI Media Adaptation | M3A | 1 | Rel-9 | S4 | Thu 12/03/09 | Thu 10/12/09 | 100% | SP-090021 | - | Samsung | kyunghun.jung@samsung.com | SP#46 completed. Work extending Rel-8 UID_34041 MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size. Update speech/video adaptation algorithms used by network to control MTSI client terminal in congestion or poor transmission conditions. | 26.114 | 43 | 22 |  |  | Mon 02/02/09 | Mon 07/12/09
5225 | 440046 | PSS and MBMS Aspects | PMA | 1 | Rel-9 | S4 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090261 | - | Ericsson, Nokia | Clinton.Priddle@ericsson.com, imed.bouazizi@nokia.com | Umbrella WI | - | 44 | 23 |  |  | Sun 31/05/09 | Mon 08/03/10
5226 | 430038 | PSS and MBMS extensions | PMA-MBS_Ext | 2 | Rel-9 | S4 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090262 | - | Ericsson | Clinton.Priddle@ericsson.com | SP#47 completed. Extends Rel-8 UID_34043 (PSS_MBMS_OMTV) & ensures compatibility with UID_34046 (IMS_PSS_MBMS_US) | 26.234, 26.346 | 43 | 22 |  |  | Mon 02/02/09 | Mon 08/03/10
5227 | 430039 | Improved Video Support for PSS and MBMS | PMA-IVS | 2 | Rel-9 | S4 | Thu 12/03/09 | Thu 25/03/10 | 100% | SP-090263 | - | Nokia | imed.bouazizi@nokia.com | SP#47 completed | 26.234, 26.244, 26.346, new 26.903 | 43 | 22 |  |  | Mon 02/02/09 | Mon 08/03/10
5228 | 430046 | IMS based PSS and MBMS User Service extensions | IMS_PSS_MBMS_US_EXT | 1 | Rel-9 | S4 | Thu 12/03/09 | Thu 10/12/09 | 100% | SP-090225 | - | Ericsson | Markus Kampmann | SP#46 completed. Work extending Rel-8 UID_34046 (IMS_PSS_MBMS_US), SA2 UID_410034 IMSSCC-SPI (IMS Service Continuity Enhancements: Service, Policy and Interactions) | 26.237 | 43 | 22 |  |  | Mon 02/02/09 | Mon 07/12/09
5229 | 440051 | Syndicated Feed Reception within 3GPP environments | SFR | 1 | Rel-9 | S4 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090260 | - | Ericsson | Thorsten.Lohmar@ericsson.com | SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD. | New 26.150 | 44 | 23 |  |  | Sun 31/05/09 | Mon 07/12/09
5230 | 450048 | Distortion Measurement Test Methods and Requirements | DTMR | 1 | Rel-9 | S4 | Thu 24/09/09 | Thu 25/03/10 | 100% | SP-090575 | - | Motorola | Stephen Kendall (wcsk01@motorola.com) | SP#47 completed | 26.131, 26.132 | 45 | 23 |  |  | Mon 21/09/09 | Wed 02/12/09
5231 | 420029 | Rel-9 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM9 | 1 | Rel-9 | S5 | Fri 22/02/08 | Thu 10/06/10 | 100% | - | - | - | - | OAM9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | 30.819 | 42 | 22 |  |  | Tue 25/11/08 | Tue 09/02/10
5232 | 420030 | Rel-9 Network Infrastructure Management | OAM9-NIM | 2 | Rel-9 | S5 | Thu 11/12/08 | Thu 25/03/10 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | - | 42 | 22 |  |  | Tue 25/11/08 | Mon 01/12/08
5233 | 420031 | Software Management for Network Elements | OAM9-NE_SWM | 3 | Rel-9 | S5 | Thu 11/12/08 | Thu 25/03/10 | 100% | SP-080756 | - | Huawei, Nokia Siemens Networks | Bidipta Das (bidipta@huawei.com), Clemens Suerbaum (clemens.suerbaum@nsn.com) | SP#47 completed | 32.531, 32.532, 32.533, new 32.537 | 42 | 22 |  |  | Wed 03/12/08 | Mon 08/03/10
5234 | 440064 | Service Oriented Architecture (SOA) for IRP | - | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090313 | - | Ericsson, Nokia Siemens Networks | edwin.tse@ericsson.com, Jörg Schmidt (joerg@cox.net) | SP#47 completed (covering SOA Architecture & SOA-supporting Solution Set). Triggered by UID_400029 Study on Service Oriented Architecture (SOA) for IRP (TR 32.824) | 32.101, 32.102, 32.150 | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
5235 | 440065 | IRP SOAP Solution Sets continuation from Rel-8 | - | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090314 | - | Ericsson | John Power | SP#47 completed. Continuation of Rel-8 UID_400030 IRP SOAP Solution Sets | New (32.127/ 327/ 337/ 357/ 387/ 397/ 447/ 397/ 447/ 507/ 537), 32.121,32.122,32.123,32,32.321,32.322,32.323,32.325,32.331,32.332,32.333,32.335,32.351,32.352,32.353,32.381,32.382,32.383,32.385,32.391,32.392,32.393,32.395,32.441,32.442,32.443 | 44 | 23 |  |  | Mon 18/05/09 | Mon 22/03/10
5236 | 420032 | Rel-9 Performance Management | OAM9-PM | 2 | Rel-9 | S5 | Thu 12/03/09 | Thu 10/06/10 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | - | 42 | 22 |  |  | Tue 25/11/08 | Mon 01/12/08
5237 | 440059 | Enhancement of UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 10/12/09 | 100% | SP-090308 | - | China Mobile | liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao | SP#46 completed | 32.405 | 44 | 23 |  |  | Mon 18/05/09 | Tue 01/12/09
5238 | 430041 | Enhancement of E-UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | Thu 12/03/09 | Thu 10/06/10 | 100% | SP-090053 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425 | 43 | 22 |  |  | Mon 23/02/09 | Wed 26/05/10
5239 | 430042 | Enhancement of EPC Performance Measurements | - | 3 | Rel-9 | S5 | Thu 12/03/09 | Thu 10/12/09 | 100% | SP-090049 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#46 completed | 32.426 | 43 | 22 |  |  | Wed 25/02/09 | Tue 09/02/10
5240 | 430043 | Rel-9 Self-Organizing Networks (SON) - OAM aspects | OAM9-SON | 2 | Rel-9 | S5 | Fri 22/02/08 | Thu 10/06/10 | 100% | - | - | - | - | SP#43 umbrella BB created to host OAM WIs | - | 43 | 22 |  |  | Mon 09/03/09 | Tue 09/02/10
5241 | 390007 | SON self-optimization management (moved from Rel-8 LTE_SON-OAM) | - | 3 | Rel-9 | S5 | Fri 22/02/08 | Thu 10/06/10 | 100% | SP-100091 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425, new (32.521, 32.522, 32.523, 32.525) | 39 | 21 |  |  | Fri 17/06/05 | Wed 26/05/10
5242 | 440067 | Automatic Radio Network Configuration Data Preparation | - | 3 | Rel-9 | S5 | Thu 04/06/09 | Thu 10/06/10 | 100% | SP-090869 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#48 completed | 32.501, 32.502, 32.503, 32.505, new 32.507 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
5243 | 440058 | Rel-9 Subscription Management (SuM) evolution | OAM9-SuM | 2 | Rel-9 | S5 | Thu 04/06/09 | Thu 10/06/10 | 100% | SP-090307 | - | Ericsson | frode.nergard@ericsson.com | SP#48 completed | 32.140, 32.141, 32.152, 32.172, 32.175 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
5244 | 420033 | Deleted - Rel-9 Trace | OAM9-Trace | 2 | Rel-9 | S5 | Fri 13/03/09 | Thu 10/12/09 | 100% | - | - | - | - | SP#46 stopped (no work in Rel-9) | - | 42 | 22 | SP-46 | PCG-24 | Tue 25/11/08 | Tue 01/12/09
5245 | 440068 | Rel-9 Charging Management small Enhancements | CH9 | 1 | Rel-9 | S5 | Thu 04/06/09 | Thu 25/03/10 | 100% | - | - | - | - | CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | 30.819 | 44 | 23 |  |  | Tue 19/05/09 | Mon 08/03/10
5246 | 400008 | CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 1 | Rel-9 | C3,C4 | Fri 30/05/08 | Fri 19/03/10 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed. Rel-8 UID_380061 (Ipinterc) covers Stage 1 in SA1 22.101, 22.228 | - | 40 | 21 |  |  | Wed 05/09/07 | Tue 02/03/10
5247 | 400109 | CT3 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 2 | Rel-9 | C3 | Fri 30/05/08 | Fri 19/03/10 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed | 29.235 | 40 | 21 |  |  | Wed 05/09/07 | Tue 02/03/10
5248 | 400010 | CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 2 | Rel-9 | C4 | Fri 30/05/08 | Fri 04/12/09 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#46 completed | 23.231, 29.232, new 29.238 | 40 | 21 |  |  | Wed 05/09/07 | Wed 25/11/09
5249 | 410008 | IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 1 | Rel-9 | C4,C3 | Fri 12/09/08 | Fri 04/12/09 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | - | 41 | 21 |  |  | Wed 05/09/07 | Wed 29/07/09
5250 | 410108 | CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 2 | Rel-9 | C4 | Fri 12/09/08 | Fri 04/12/09 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | new 29.238 | 41 | 21 |  |  | Wed 05/09/07 | Mon 16/11/09
5251 | 410208 | CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 2 | Rel-9 | C3 | Fri 12/09/08 | Fri 04/12/09 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | 29.162, 29.235 | 41 | 21 |  |  | Wed 05/09/07 | Wed 25/11/09
5252 | 410009 | IMS Application Level Gateway Control Function (ALGCF) – IMS Access Media Gateway (IMA-MGW); Iq Interface; Stage 2 and Stage 3 | IMS_AGCF | 1 | Rel-9 | C4 | Fri 12/09/08 | Fri 04/12/09 | 100% | CP-090020 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | New 23.334, 29.334 | 41 | 21 |  |  | Wed 05/09/07 | Mon 16/11/09
5253 | 420016 | Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT | 1 | Rel-9 | C1 | Fri 05/12/08 | Fri 04/06/10 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed. Stage 1 in 22.182 | - | 42 | 22 |  |  | Thu 04/12/08 | Mon 16/11/09
5254 | 420017 | Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT-SS | 2 | Rel-9 | C1 | Fri 05/12/08 | Fri 04/06/10 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed | 24.182 | 42 | 22 |  |  | Thu 04/12/08 | Fri 28/05/10
5255 | 440017 | Completion of IMS Restoration Procedures | eIMS_RP | 1 | Rel-9 | C3,C4,C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed. Continuation of Rel-8 Feature UID_400012 IMS Restoration Procedures | - | 44 | 23 |  |  | Wed 13/05/09 | Thu 01/04/10
5256 | 440018 | CT4 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C4 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 23.380, 23.820 | 44 | 23 |  |  | Wed 13/05/09 | Tue 09/03/10
5257 | 440019 | CT1 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 24.229 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5258 | 460022 | CT3 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C3 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 29.061, 29.212, 29.213, 29.214, 29.215 | 46 | 24 |  |  | Wed 13/05/09 | Tue 02/03/10
5259 | 440039 | IMS Stage 3 IETF Protocol Alignment - phase 3 | IMSProtoc3 | 1 | Rel-9 | C1,IETF | Fri 29/05/09 | Fri 05/12/14 | 100% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | - | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5260 | 440139 | CT1 aspects of IMS Stage 3 - IETF Protocol Alignment - phase 3 | IMSProtoc3 | 2 | Rel-9 | C1 | Fri 29/05/09 | Fri 19/03/10 | 100% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 23.218, 24.229, 24.930 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
5261 | 521009 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7329) | IMSProtoc3 | 2 | Rel-9 | C1-IETF | Fri 29/05/09 | Fri 05/12/14 | 100% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed | RFC 7329 (was draft-kaplan-insipid-session-id) | 52 | 27 |  |  | Mon 20/06/11 | Wed 03/09/14
5262 | 531007 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7044) | IMSProtoc3 | 2 | Rel-9 | C1-IETF | Tue 13/09/11 | Fri 07/03/14 | 100% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#63 completed | RFC 7044 (was draft-ietf-sipcore-rfc4244bis) | 53 | 27 |  |  | Tue 13/09/11 | Wed 27/11/13
5263 | 440070 | Operational description of the Inter-IMS Network to Network Interface (II-NNI) | II-NNI | 1 | Rel-9 | C3,IETF | Fri 29/05/09 | Tue 09/12/14 | 100% | CP-090331 | - | Orange | sebastien.daudet@orange-ftgroup.com | - | - | 44 | 23 |  |  | Fri 29/05/09 | Thu 28/02/13
5264 | 440170 | Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3 | Fri 29/05/09 | Fri 04/06/10 | 100% | CP-090331 | - | Orange | - | CP#48 completed | 29.165 | 44 | 23 |  |  | Fri 20/04/12 | Thu 27/05/10
5265 | 561004 | (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7329) | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Fri 12/09/14 | 100% | CP-090331 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 complete | RFC 7329 (was draft-kaplan-insipid-session-id) | 56 | 29 |  |  | Fri 20/04/12 | Wed 03/09/14
5266 | 561005 | (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7316) | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Fri 12/09/14 | 100% | CP-090331 | - | Keith Drage | Keith Drage | CP#65 complete | RFC 7316 (was draft-vanelburg-dispatch-private-network-ind) | 56 | 29 |  |  | Fri 20/04/12 | Wed 03/09/14
5267 | 561006 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Tue 09/12/14 | 100% | CP-090331 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100 | draft-ietf-salud-alert-info-urns | 56 | 29 |  |  | Fri 20/04/12 | Mon 07/03/16
5268 | 561007 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Tue 09/12/14 | 100% | CP-090331 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). Jun 15: RFC 7433 (was draft-ietf-cuss-sip-uui) | RFC 7433 | 56 | 29 |  |  | Fri 20/04/12 | Tue 10/03/15
5269 | 561008 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Tue 09/12/14 | 100% | CP-090331 | - | Keith Drage | Keith Drage | In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdni). June 15: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn) | RFC 7434 | 56 | 29 |  |  | Fri 20/04/12 | Thu 04/12/14
5270 | 561009 | Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | Fri 20/04/12 | Fri 06/12/13 | 100% | CP-090331 | - | Peter Dawes | peter.dawes@vodafone.com | CP#62 removed from Rel-8 to Rel-11. Not completed internet-draft | Rel-12 remains draft-dawes-sipping-debug | 56 | 29 | SP-69 |  | Fri 20/04/12 | Wed 27/11/13
5271 | 591002 | Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface (avasarala-dispatch-comm-div-notification) | II-NNI | 2 | Rel-9 | C3-IETF | Fri 01/03/13 | Fri 13/06/14 | 100% | CP-090331 | - | Andrew Allen | Andrew Allen | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 59 | 30 | SP-69 |  | Thu 21/02/13 | Fri 06/06/14
5272 | 450005 | Definition of Ml interface for Control Plane LCS (Stage 3) | EMC2 | 1 | Rel-9 | C1 | Fri 18/09/09 | Fri 19/03/10 | 100% | CP-090746 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed [Stage 3 for Rel-7 Emergency Calls (EMC1)]. Related to Rel-9 UID_400038 LCS Control Plane Solution for EPS. Stage 2 in Rel-9 UID_400038 (23.271), UID_410037 (23.167) | 24.229 | 45 | 23 |  |  | Thu 17/09/09 | Tue 02/03/10
5273 | 450009 | PCC enhancements | PCC-Enh | 1 | Rel-9 | C3 | Fri 18/09/09 | Fri 04/12/09 | 100% | CP-090744 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#46 completed | 29.212, 29.213, 29.215 | 45 | 23 |  |  | Thu 05/03/09 | Thu 17/09/09
5274 | 460004 | 3GPP IMS Conferencing Management Object (MO) | IMS_ConfMO | 1 | Rel-9 | C1 | Thu 03/12/09 | Fri 04/12/09 | 100% | - | - | - | - | CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2) | New 24.166 | 46 | 24 |  |  | Tue 08/12/09 | Tue 09/02/10
5275 | 470004 | In Case of Emergency (ICE) Graphics | ICE_Graphics | 1 | Rel-9 | C6 | Wed 17/03/10 | Fri 19/03/10 | 100% | CP-100178 | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#47 approved WID and completed. Added capability to store ICE graphical information (picture). Linked to CT6 Rel-8 ICE Feature UID_380059 In Case of Emergency numbers storage and easy access on UICC | 31.102 CR#0433 | 47 | 24 |  |  | Tue 09/03/10 | Wed 17/03/10
5276 | 410023 | Rel-9 Improvements of the Radio Interface | RInImp9 | 1 | Rel-9 | RP,GP | Fri 12/09/08 | Fri 19/03/10 | 100% | - | - | - | - | RP#41 umbrella Feature created to host Rel-9 WIs | GERAN, UTRA, LTE | 41 | 21 |  |  | Tue 04/01/05 | Tue 16/03/10
5277 | 410017 | LCR TDD UE OTA Performance Requirements | RInImp9-RFLCROTA | 2 | Rel-9 | R4 | Fri 12/09/08 | Fri 29/05/09 | 100% | RP-080744 | RP-090389 | RITT | Wu Xiang (wuxiang@chinattl.com) | RP#44 completed technical work (RAN4 internal TR abandoned) | UTRA (no 25.8xy produced) | 41 | 21 |  |  | Thu 11/09/08 | Wed 09/09/09
5278 | 410019 | RF requirements for Multicarrier and Multi-RAT BS | RInImp9-RFmulti | 2 | Rel-9 | R4,G1 | Fri 21/11/08 | Fri 19/03/10 | 100% | RP-091381 | - | Ericsson | Johan.skold@ericsson.com | RP#47 completed. RF requirements specification applicable to Multi-Standard Radio (MSR) Base Station with multiple carriers and/or multiple 3GPP Radio Access Technologies (RAT) | GERAN, UTRA, LTE | 41 | 21 |  |  | Thu 11/09/08 | Tue 16/03/10
5279 | 420009 | RAN4 part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-Rfmulti | 3 | Rel-9 | R4 | Fri 05/12/08 | Fri 19/03/10 | 100% | RP-091381 | RP-100027 | Ericsson | johan.skold@ericsson.com | RP#48 completed | UTRA, LTE 25.104, 25.105, 36.104, new 37.104, 37.113, 37.141, 37.900 | 42 | 22 |  |  | Sun 23/11/08 | Tue 01/06/10
5280 | 420001 | GERAN part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-RFmulti-GERAN | 3 | Rel-9 | G1 | Fri 21/11/08 | Fri 20/11/09 | 100% | GP-081945 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#44 Core spec completed. GP#40 WID approved | GERAN 45.005, 51.021 | 40 | 22 |  |  | Sun 23/11/08 | Fri 20/11/09
5281 | 420010 | Extended UMTS/LTE 800 MHz | RInImp9-UMTSLTE800 | 2 | Rel-9 | R4,R2,R3 | Fri 05/12/08 | Fri 05/12/08 | 100% | RP-080884 | RP-090687 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#45 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466, new 36.800 | 42 | 22 |  |  | Thu 04/12/08 | Wed 07/10/09
5282 | 430009 | UMTS/LTE 800 MHz for Europe | RInImp9-UMTSLTE800EU | 2 | Rel-9 | R4,R2,R3 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090156 | RP-100028 | Ericsson | olav.queseth@ericsson.com | RP#47 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, new 36.810, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466 | 43 | 22 |  |  | Thu 26/02/09 | Tue 16/03/10
5283 | 430010 | Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350 | 2 | Rel-9 | R4 | Fri 06/03/09 | Fri 04/12/09 | 100% | RP-090258 | RP-091035 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#46 completed | UTRA 25.102, 25.105, 25.142 | 43 | 22 |  |  | Fri 27/02/09 | Wed 02/12/09
5284 | 440004 | Extended UMTS/LTE 1500 MHz | UMTSLTE1500 | 2 | Rel-9 | R4,R2,R3 | Sat 30/05/09 | Sat 30/05/09 | 100% | RP-090470 | RP-100029 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#47 completed. For potential deployment in Japan | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.331, new (36.821, 36.307) | 44 | 23 |  |  | Fri 22/05/09 | Tue 16/03/10
5285 | 440006 | Rel-9 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-9 | R5 | Tue 19/05/09 | Fri 17/09/10 | 100% | - | - | - | - | - | UTRA, LTE | 44 | 23 |  |  | Mon 18/05/09 | Thu 28/05/09
5286 | 440007 | Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe | RInImp-UEConTest-UMTSLTE800EU | 2 | Rel-9 | R5 | Tue 19/05/09 | Fri 17/09/10 | 100% | RP-090485 | RP-100736 | Ericsson | fredrik.sundstrom@ericsson.com | RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe | UTRA, LTE 34.108, 34.121-1, 34.121-2, 36.508, 36.521-1, 36.521-2, 36.521-3 | 44 | 23 |  |  | Mon 18/05/09 | Wed 08/09/10
5287 | 450017 | Conformance Test Aspects – Extended UMTS/LTE 1500 MHz | UMTSLTE1500_UEConTest | 2 | Rel-9 | R5 | Fri 18/09/09 | Fri 04/06/10 | 100% | RP-091366 | RP-100487 | NTT DoCoMo | Nguyen Dung Dao (dao@nttdocomo.co.jp) | RP#48 completed | UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
5288 | 440012 | TDD UE Over The Air (Antenna) conformance testing methodology | UEAnt_TDDTest | 2 | Rel-9 | R5 | Sat 30/05/09 | Fri 18/09/09 | 100% | RP-090621 | RP-090727 | CATR | Qu Yan (quyan@emcite.com) | RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head) | UTRA 34.114 | 44 | 23 |  |  | Wed 20/05/09 | Thu 10/09/09
5289 | 470019 | Conformance Test Aspects – Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350_UEConTest | 2 | Rel-9 | R5 | Fri 19/03/10 | Fri 04/06/10 | 100% | RP-100167 | RP-100496 | CATT | Xiaozhong Chen (chexiaozhong@datangmobile.cn) | RP#48 completed. Testing for UID_430010 Performance requirement for LCR TDD with UE speeds up to 350 km/h | UTRA 34.122 | 47 | 24 |  |  | Wed 17/03/10 | Tue 01/06/10
5290 | 450018 | Conformance Test Aspects – SMS over IMS in E-UTRAN | SMSoverIMS_UEConTest | 1 | Rel-9 | R5 | Fri 18/09/09 | Fri 19/03/10 | 100% | RP-090959 | RP-100072 | Alcatel-Lucent | Nidal Khrais (khrais@alcatel-lucent.com) | RP#47 completed | LTE 34.229-1, 34.229-2, 34.229-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 16/03/10
5291 | 430013 | Rel-9 RAN improvements | - | 1 | Rel-9 | RP | Fri 06/03/09 | Wed 08/09/10 | 100% | - | - | - | - | RP#47 completed | UTRA | 43 | 22 |  |  | Fri 06/03/09 | Wed 08/09/10
5292 | 430014 | Dual-Cell HSUPA | RANimp-DC_HSUPA | 2 | Rel-9 | R1,R2,R3,R4 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090014 | RP-100030 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.319, 25.306, 25.321, 25.331, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Tue 16/03/10
5293 | 430015 | Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA | 2 | Rel-9 | R4,R2,R3 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090973 | RP-091038 | Nokia Siemens Networks | Tuomo Säynäjäkangas (tuomo.saynajakangas@nsn.com) | RP#46 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.133, 25.306, 25.308, 25.331, 25.423, 25.433, new 25.317 replaced by new 25.327 | 43 | 22 |  |  | Fri 06/03/09 | Thu 26/11/09
5294 | 430016 | Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO | 2 | Rel-9 | R1,R2,R3,R4 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090332 | RP-091039 | Ericsson | johan.bergman@ericsson.com | RP#46 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 26.306, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Fri 27/11/09
5295 | 430018 | Transmit Antenna Array (TxAA) extension for non-MIMO UEs | RANimp-TxAA_nonMIMO | 2 | Rel-9 | R1,R2,R3,R4 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090013 | RP-091040 | Nokia | Arto Lehti (arto.lehti@nokia.com) | RP#46 completed | 25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Thu 26/11/09
5296 | 440014 | Cell Portion for 1.28 Mcps TDD | CP_LCRTDD | 2 | Rel-9 | R3,R1,R4 | Fri 06/03/09 | Wed 08/09/10 | 100% | RP-090659 | RP-091041 | CATT | Ying Zhang (zhangying2@datangmobile.cn) | RP#46 completed | 25.102, 25.105, 25.123, 25.225, 25.423, 25.433 | 44 | 23 |  |  | Thu 28/05/09 | Thu 26/11/09
5297 | 490025 | Rel-9 RAN improvements - UE Conformance Testing | - | 1 | Rel-9 | R5 | Fri 17/09/10 | Fri 07/12/12 | 100% | - | - | - | - | - | - | 49 | 25 |  |  | Wed 08/09/10 | Mon 20/09/10
5298 | 490019 | Conformance Test Aspects – Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO_UEConTest | 2 | Rel-9 | R5 | Fri 17/09/10 | Fri 03/06/11 | 100% | RP-101001 | RP-110510 | Ericsson | leif.mattisson@ericsson.com | UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Wed 08/09/10 | Wed 18/05/11
5299 | 510014 | Conformance Test Aspects – Dual-Cell HSUPA | RANimp-DC_HSUPA_UEConTest | 2 | Rel-9 | R5 | Fri 18/03/11 | Fri 07/12/12 | 100% | RP-110116 | RP-121524 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Wed 28/11/12
5300 | 510013 | Conformance Test Aspects – Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA_UEConTest | 2 | Rel-9 | R5 | Fri 18/03/11 | Fri 02/03/12 | 100% | RP-110115 | RP-120036 | Ericsson | leif.mattisson@ericsson.com | RP#55 completed. Testing for Rel-9 UID_430015 Support for different bands for Dual-Cell HSDPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Thu 23/02/12
5301 | 420007 | LTE improvements | LTEimp | 1 | Rel-9 | R1,R2,R4,R5 | Fri 06/03/09 | Fri 03/06/11 | 100% | - | - | - | - | - | LTE | 42 | 22 |  |  | Tue 02/12/08 | Wed 21/01/09
5302 | 430019 | LTE Pico NodeB RF Requirements | LTEimp-Pico_eNB-RF | 2 | Rel-9 | R4 | Fri 06/03/09 | Fri 04/12/09 | 100% | RP-091155 | RP-091045 | Huawei | Liyan Yin (yinliyan@huawei.com) | RP#46 completed | 36.104, 36.141, new 36.931 | 43 | 22 |  |  | Fri 27/02/09 | Mon 08/02/10
5303 | 430029 | Enhanced Dual-Layer transmission for LTE | LTEimp-eDL | 2 | Rel-9 | R1,R2,R4 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-091385 | RP-100034 | China Mobile | Xu Xiaodong (xuxiaodong@chinamobile.com) | RP#47 completed | 36.101, 36.211, 36.212, 36.213, 36.331 | 43 | 22 |  |  | Tue 10/03/09 | Tue 01/06/10
5304 | 490018 | UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD | LTEimp-eDL_UEConTest | 2 | Rel-9 | R5 | Fri 17/09/10 | Fri 03/06/11 | 100% | RP-100868 | RP-110509 | China Mobile | Shanpeng Xiao (xiaoshanpeng@chinamobile.com) | RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE) | 36.508, 36.521-1, 36.521-2 | 49 | 25 |  |  | Thu 09/09/10 | Wed 18/05/11
5305 | 420011 | Rel-9 Self-Organizing Networks (SON) | SON | 1 | Rel-9 | R3,R2 | Fri 06/03/09 | Fri 06/03/09 | 100% | RP-090162 | RP-100038 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#47 completed | LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902 | 42 | 22 |  |  | Fri 05/12/08 | Wed 10/03/10
5306 | 38002 | AGNSS Performances and Testing Procedures | AGNSSPTP | 1 | Rel-9 | G1,G3new | Fri 16/05/08 | Fri 20/05/11 | 100% | GP-092342 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#46 still ongoing MS testing. Linked to Rel-10 RAN4 UID_450027 (AGNSS Minimum Performance for UTRAN) | - |  |  |  |  | Mon 19/05/08 | Fri 12/02/10
5307 | 38003 | AGNSS Minimum Performances | AGNSSPTP-Perfreq | 2 | Rel-9 | G1 | Fri 16/05/08 | Fri 05/03/10 | 100% | GP-081786 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#45 completed (open performance requirements alignment GPS/Galileo) | 45.005 |  |  |  |  | Mon 19/05/08 | Wed 10/03/10
5308 | 38004 | AGNSS Testing Procedures | AGNSSPTP-MStest | 2 | Rel-9 | G3new | Fri 16/05/08 | Fri 20/05/11 | 100% | GP-092343 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#50 completed | 51.010-1, new 51.010-7 |  |  |  |  | Mon 19/05/08 | Sat 21/05/11
5309 | 420002 | Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 1 | Rel-9 | GP,G1,G2,G3new | Fri 21/11/08 | Fri 02/03/12 | 100% | GP-081949 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | Triggered by UID_50590 (MUROS) Study on Multi-User Reusing-One-Slot | - | 42 | 22 |  |  | Sun 23/11/08 | Thu 27/05/10
5310 | 420003 | Stage 2 for Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 2 | Rel-9 | GP,G1,G2 | Fri 21/11/08 | Fri 21/05/10 | 100% | GP-081964 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#46 completed. GP#40 WID approved | 45.001 | 40 | 22 |  |  | Sun 23/11/08 | Thu 27/05/10
5311 | 420004 | Stage 3 for Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 2 | Rel-9 | GP,G1,G2 | Mon 24/11/08 | Fri 04/03/11 | 100% | GP-081965 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#49 completed. GP#40 WID approved | 24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058 | 40 | 22 |  |  | Sun 23/11/08 | Fri 04/03/11
5312 | 420005 | VAMOS Radio Performance Requirements | VAMOS | 2 | Rel-9 | GP,G1,G2 | Mon 24/11/08 | Fri 20/05/11 | 100% | GP-081966 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#50 completed. GP#40 WID approved | 45.005 | 40 | 22 |  |  | Sun 23/11/08 | Sat 21/05/11
5313 | 490005 | VAMOS - MS conformance testing | VAMOS_MStest | 2 | Rel-9 | G3new | Fri 03/09/10 | Fri 02/03/12 | 100% | GP-101604 | - | BlackBerry | Raveendra Seetharam (rseetharam@rim.com) | GP#53 completed. GP#47 WID approved | 51.010-1, 51.010-2 | 47 | 25 |  |  | Sat 04/09/10 | Fri 02/03/12
5314 | 500001 | VAMOS - BTS conformance testing | VAMOS_BTStest | 2 | Rel-9 | G1 | Fri 26/11/10 | Fri 02/09/11 | 100% | GP-102005 | - | Nokia Siemens Networks | eddie.riddington@nsn.com | GP#51 completed. GP#48 WID approved | 51.021 | 48 | 26 |  |  | Sat 27/11/10 | Sat 21/05/11
5315 | 440002 | Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC) | CEBRO | 1 | Rel-9 | GP,C1 | Fri 15/05/09 | Fri 19/03/10 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed. GP#45 completed. GP#42 WID approved | - | 42 | 23 |  |  | Mon 18/05/09 | Fri 05/03/10
5316 | 440102 | GERAN part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | CEBRO | 2 | Rel-9 | GP | Fri 15/05/09 | Fri 05/03/10 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | GP#45 completed. GP#42 WID approved | new 48.049 | 42 | 23 |  |  | Mon 18/05/09 | Fri 05/03/10
5317 | 440202 | CT1 part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | CEBRO | 2 | Rel-9 | C1 | Fri 15/05/09 | Fri 19/03/10 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed | 23.041 | 42 | 23 |  |  | Mon 18/05/09 | Tue 02/03/10
5318 | 440003 | Hybrid Location | HILT | 1 | Rel-9 | GP | Mon 18/05/09 | Fri 20/11/09 | 100% | GP-091075 | - | TruePosition | Matt Ward (mward@trueposition.com) | GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT) | 43.059, 48.071 | 42 | 23 |  |  | Mon 18/05/09 | Mon 07/09/09
5319 | 420099 | (Small) Technical Enhancements and Improvements for Rel-9 | TEI9 | 1 | Rel-9 | SP,CP,RP,GP | Mon 15/09/08 | Thu 10/12/09 | 100% | - | - | - | - | SP#46 completed | - | 42 | 22 |  |  | Fri 04/11/05 | Wed 25/11/09
5320 | 460002 | Test - (Small) Technical Enhancements and Improvements for Rel-9 | TEI9_Test | 1 | Rel-9 | R5,G3new | Fri 20/11/09 | Fri 24/12/10 | 100% | - | - | - | - | GP#44 created | - | 44 | 24 |  |  | Wed 25/11/09 | Sun 05/09/10
5321 | 330017 | Deleted - Services Alignment and Migration | ServAl | 1 | Rel-9 | S1 | Wed 06/12/06 | Thu 18/09/08 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work¦no CR against TR 22.983). Triggered by Study UID_370086 (FSServAl) | - | 33 |  | SP-41 | PCG-21 | Fri 06/10/06 | Thu 05/08/10
5322 | 410001 | Deleted - Stage 1 for ServAl | - | 2 | Rel-9 | S1 | Wed 06/12/06 | Thu 18/09/08 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work¦no CR against TR 22.983) | 22.983 | 33 | 21 | SP-41 | PCG-21 | Fri 06/10/06 | Thu 05/08/10
5323 | 380071 | Deleted - Harmonization of Gq'/Rx for Common IMS | IMS_Comm_GqRx_Harm | 1 | Rel-9 | S2 | Mon 14/01/08 | Thu 12/03/09 | 100% | SP-070822 | - | Alcatel-Lucent | geoffrey.cristallo@alcatel-lucent.be | SP#43 stopped. LS_out to TISPAN informs about stopping this activity | 23.822, 23.203 | 38 | 21 | SP-43 | PCG-22 | Tue 02/10/07 | Tue 24/03/09
5324 | 380081 | Deleted - Support of WiMAX - LTE Mobility | WiMAX_LTE_Mobility | 1 | Rel-9 | R2 | Fri 06/06/08 | Fri 25/12/09 | 100% | RP-070511 | - | Samsung | - | RP#39: No agreed WID | 36.306, 36.331, 36.413, 36.300, 36.214, 36.133, 36.304 | 38 | 21 | SP-39 | PCG-21 | Mon 17/12/07 | Tue 24/03/09
5325 | 380082 | Deleted - Support of WiMAX - UMTS Mobility | WiMAX_UMTS_Mobility | 1 | Rel-9 | R2 | Fri 06/06/08 | Fri 25/12/09 | 100% | RP-070511 | - | Intel | - | RP#39: No agreed WID | 25.306, 25.331, 25.413 | 38 | 21 | SP-39 | PCG-21 | Mon 17/12/07 | Tue 24/03/09
5326 | 380086 | Deleted - Definition of 3GPP UICC services over the new high-speed interface | UICCHS | 1 | Rel-9 | C6 | Fri 19/03/10 | Fri 19/03/10 | 100% | CP-070837 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#47 work stopped/abandoned | 31.xyz | 38 | 21 | CP-47 | PCG-24 | Thu 31/01/08 | Wed 25/11/09
5327 | 390040 | Deleted - SAES Enhancements (non RAN aspects) | SAES_Ph2 | 1 | Rel-9 | S2 | Mon 25/06/07 | Mon 08/12/08 | 100% | - | - | Nokia Siemens Networks | - | SP#39 created to host Rel-9 Wis. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Mon 31/01/05 | Tue 24/03/09
5328 | 350028 | Deleted - Functions and procedures for SAE to support LTE MBMS | SAES_Ph2 | 2 | Rel-9 | S2 | Mon 25/06/07 | Mon 08/12/08 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. WID returned to SA2 for re-consideration & remove MBMS for EPS from Rel 8 | - | 35 |  | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
5329 | 390041 | Deleted - CS over EPS | SAES_Ph2 | 2 | Rel-9 | S2 | Wed 12/03/08 | Mon 08/12/08 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
5330 | 390042 | Deleted - SAE for generic support for non-3GPP accesses | SAES_Ph2 | 2 | Rel-9 | S2 | Mon 25/06/07 | Mon 09/06/08 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
5331 | 390043 | Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX | SAES_Ph2 | 3 | Rel-9 | S2 | Mon 25/06/07 | Mon 09/06/08 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 26/04/07 | Tue 24/03/09
5332 | 440071 | Deleted - Lawful Interception in the 3GPP Rel-9 | LI9 | 1 | Rel-9 | S3 | Thu 04/06/09 | Thu 25/03/10 | 100% | SP-090831 | - | PIDS, Nortel | Koen Jaspers, Ronald Ryan | SP#47 stopped. WI + new topics moved to Rel-10 | 33.106, 33.107, 33.108 | 44 | 23 | SP-47 | PCG-24 | Tue 02/06/09 | Mon 01/03/10
5333 | 0 | Release 9 Studies | - | 1 | Rel-9 | CP,RP,SP | Thu 05/06/08 | Thu 05/06/08 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
5334 | 400036 | Study on Service Specific Access Control in EPS | FS_SSAC | 1 | Rel-9 | S1 | Thu 05/06/08 | Thu 11/12/08 | 100% | SP-080319 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | SP#42 completed. Spin-off Feature UID_420020 (SSAC) | 22.986 | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
5335 | 350052 | Study on CS Domain Services over EPS access | FS_CSoPS | 1 | Rel-9 | S2 | Wed 25/04/07 | Thu 12/03/09 | 100% | SP-080800 | - | T-Mobile | Karl-Heinz.Nenner@T-Mobile.net | SP#43 completed. Linked to Combinational Services UID_31064, Services Alignment and Migration (ServAl) UID_330017 and 3GPP System Architecture Evolution (SAES) UID_3208 | 23.879 | 35 |  |  |  | Thu 29/03/07 | Mon 09/08/10
5336 | 370043 | Study on Extended Support of IMS Emergency Calls | FS_IMS-eCall | 1 | Rel-9 | S2 | Mon 24/09/07 | Thu 11/12/08 | 100% | SP-070547 | - | Qualcomm | Stephen Edge | SP#42 completed | 23.868 | 37 |  |  |  | Wed 19/07/06 | Sat 22/11/08
5337 | 320031 | Study on Service Continuity for Emergency Voice Calls | FS_VCCEm | 1 | Rel-9 | S2 | Thu 08/06/06 | Thu 12/03/09 | 100% | SP-080555 | - | Nortel | Ricky Kaura (rkaura@nortel.com) | SP#43 completed | 23.826 | 32 |  |  |  | Wed 19/07/06 | Tue 24/02/09
5338 | 370053 | Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M Equipment | FS_UM2M | 1 | Rel-9 | S3,C6 | Tue 06/04/04 | Thu 10/12/09 | 100% | SP-070702 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#46 completed. Triggered by the SA1 Rel-8 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) UID_7027 in TR 22.868. | 33.812 | 37 |  |  |  | Mon 19/11/07 | Tue 08/12/09
5339 | 360006 | Study on System Maintenance over Itf-N | FS_OAM-Maint-Itf-N | 1 | Rel-9 | S5 | Thu 07/06/07 | Thu 24/09/09 | 100% | SP-070306 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#45 completed | 32.822 | 36 |  |  |  | Mon 28/05/07 | Mon 07/09/09
5340 | 360007 | Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB | FS_OAM-SON-HNB | 1 | Rel-9 | S5 | Thu 07/06/07 | Thu 04/06/09 | 100% | SP-080461 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.821 | 36 |  |  |  | Mon 28/05/07 | Mon 18/05/09
5341 | 390017 | Study on Self-healing of Self-Organizing Networks (SON) | FS_OAM-SON-SH | 1 | Rel-9 | S5 | Fri 22/02/08 | Thu 24/09/09 | 100% | SP-080076 | - | ZTE | zhu.weihong@zte.com.cn | SP#45 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.823 | 39 | 21 |  |  | Mon 28/05/07 | Mon 07/09/09
5342 | 400029 | Study on Service Oriented Architecture (SOA) for IRP | FS_OAM_SOA_IRP | 1 | Rel-9 | S5 | Thu 05/06/08 | Thu 04/06/09 | 100% | SP-080281 | - | Ericsson | edwin.tse@ericsson.com | SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP | 32.824 | 40 | 21 |  |  | Mon 28/05/07 | Tue 02/06/09
5343 | 380079 | Study on Evaluation of the inclusion of Path Loss Based Technology in the UTRAN | FS_RAN-Pathloss | 1 | Rel-9 | R4 | Mon 17/12/07 | Fri 04/12/09 | 100% | RP-071050 | RP-091080 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#46 completed | 25.907 | 38 | 21 |  |  | Mon 17/12/07 | Thu 26/11/09
5344 | 390031 | Study on LTE-Advanced | FS_RAN_LTEA | 1 | Rel-9 | R1,R2,R3,R4 | Fri 21/03/08 | Fri 19/03/10 | 100% | RP-091360 | RP-100080 | NTT DoCoMo | Tetsushi Abe | RP#47 completed | 36.913 , New 36.814, 36.912, R2 36.806 (Relay architectures for E-UTRA), R4 36.815 (LTE-Advanced feasibility studies in RAN4) | 39 | 21 |  |  | Mon 17/12/07 | Tue 16/03/10
5345 | 410016 | Study on 1.28 Mcps TDD Home NodeB | FS_RAN-HNBLCRTDD | 1 | Rel-9 | R4 | Wed 20/02/08 | Fri 04/12/09 | 100% | RP-080767 | RP-091081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#46 completed | 25.866 | 41 | 21 |  |  | Mon 17/12/07 | Thu 03/12/09
5346 | 420012 | Study on E-UTRAN Mobility Evaluation and Enhancement | FS_EUTRAN_mob | 1 | Rel-9 | R1 | Fri 05/12/08 | Fri 29/05/09 | 100% | RP-081137 | RP-090426 | Qualcomm | Rajat Prakash (rprakash@qualcomm.com) | RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed) | none | 42 | 22 |  |  | Thu 04/12/08 | Wed 20/05/09
5347 | 430021 | Study on Minimization of drive-tests in Next Generation Networks | FS_NGN_min_drive-tests | 1 | Rel-9 | R2 | Fri 06/03/09 | Fri 04/12/09 | 100% | RP-090341 | RP-091084 | Qualcomm | Masato Kitazoe (mkitazoe@qualcomm.com) | RP#46 completed | 36.805 | 43 | 22 |  |  | Fri 06/03/09 | Fri 27/11/09
5348 | 430027 | Study on Enhanced Interference Management for HNBs | FS_eInterfMgmt_HNB | 1 | Rel-9 | R4 | Fri 06/03/09 | Fri 29/05/09 | 100% | RP-090361 | RP-090429 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#44 completed. Linked to UID_420008 LTE FDD Home eNodeB RF Requirements. Spin-off RAN3 UID_440015 Study on Enhanced Interference Management Mechanisms for HNBs | 25.967 | 43 | 22 |  |  | Tue 10/03/09 | Thu 25/06/09
5349 | 440015 | Study on Enhanced Interference Management Mechanisms for HNBs | FS_eInterfMgmtMchsm_HNB | 1 | Rel-9 | R3 | Sat 30/05/09 | Fri 18/09/09 | 100% | RP-090667 | RP-090733 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#45 completed. Triggered by RAN4 UID_430027 Study on Enhanced Interference Management for HNBs | 25.967 | 44 | 23 |  |  | Tue 26/05/09 | Tue 15/09/09
5350 | 320026 | Deleted - Study on Protection against SMS and MMS spam | FS_CPSMal | 1 | Rel-9 | S3 | Thu 08/06/06 | Thu 24/09/09 | 100% | SP-060446 | - | Orange | eric.gauthier@orange.ch | SP#45 work stopped/abandoned | 33.9xx | 32 |  | SP-45 | PCG-23 | Fri 23/06/06 | Mon 21/09/09
5351 | 0 | --- RELEASE 8 --- | - | 1 | Rel-8 | CP,GP,RP,SP | Tue 19/09/06 | Fri 19/03/10 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
5352 | 320005 | 3GPP System Architecture Evolution Specification - Evolved Packet System (non RAN aspects) | SAES | 1 | Rel-8 | S1,S2,S3,S5,C1,C3,C4,C6,IETF | Wed 12/04/06 | Fri 15/06/12 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | Role model for SAE/LTE system wide project management by SA2 in SP-060166 | - | 32 |  |  |  | Mon 31/01/05 | Tue 08/12/09
5353 | 320022 | Requirements for evolution of the 3GPP system architecture | AIPN-SAE | 2 | Rel-8 | S1 | Thu 08/06/06 | Wed 12/12/07 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | SP#38 completed | 22.011, 22.246, New 22.278 | 32 |  |  |  | Fri 23/06/06 | Wed 28/07/10
5354 | 370005 | High level and common (for all accesses) functions | EPS-ComF | 2 | Rel-8 | S2,S3,C1,C3,C4 | Tue 02/01/07 | Fri 29/05/09 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#44 completed | - | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5355 | 350024 | Stage 2 for High level functions | SAES-SA-HLF | 3 | Rel-8 | S2 | Tue 02/01/07 | Mon 02/06/08 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | New 23.402 | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
5356 | 390044 | Stage 2 Security Architecture | SAES | 3 | Rel-8 | S3 | Wed 12/03/08 | Thu 11/12/08 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.210, 33.310, New 33.401 | 39 | 21 |  |  | Wed 19/03/08 | Wed 28/07/10
5357 | 340051 | Stage 3 (CT1) for SAE impact on services, network functions and capabilities | SAES | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.229, 27.007, New 24.305 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5358 | 340054 | Stage 3 SAE impact on existing capabilities | SAES | 3 | Rel-8 | C3 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#42 completed | 29.061 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5359 | 340062 | Stage 3 (CT4) of SAE impact on existing capabilities | SAES | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | New (29.274, 29.275) | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5360 | 340049 | Stage 2/3 for Network selection procedures | SAES | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 23.122, New 24.302 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5361 | 340023 | Stage 3 EPC interworking with external PDNs (SGi) | SAES-St3-intwk | 3 | Rel-8 | C3 | Mon 05/02/07 | Fri 29/05/09 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#44 completed | 29.061 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5362 | 340022 | Stage 3 PCC within SAE | SAES-St3-PCC | 3 | Rel-8 | C3 | Mon 05/02/07 | Fri 29/05/09 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#44 completed | 29.212, 29.213, 29.214, New 29.215 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5363 | 340028 | Stage 3 for SAE / LTE identities | SAES | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 23.003 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5364 | 370017 | Unified guidelines for Diameter usage within 3GPP | SAES-DIAM | 3 | Rel-8 | C3 | Fri 21/09/07 | Fri 05/12/08 | 100% | CP-080055 | - | Huawei | Javier Gonzalez Gallego | CP#42 completed | New 29.909 | 37 |  |  |  | Tue 25/09/07 | Wed 28/07/10
5365 | 350025 | SAE for LTE access | SAES-LTE | 2 | Rel-8 | S2,C1,C3,C4 | Tue 02/01/07 | Fri 06/03/09 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
5366 | 340060 | CT4 Stage 3 for protocol between EPCs | SAES-LTE | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5367 | 350042 | SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP | 3 | Rel-8 | S2,C4 | Tue 02/01/07 | Fri 06/03/09 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | - | 35 |  |  |  | Thu 26/04/07 | Wed 28/07/10
5368 | 370006 | Stage 2 for SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP-St2 | 4 | Rel-8 | S2 | Tue 02/01/07 | Thu 05/06/08 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | 23.401, 23.060, 23.002, 23.246, 23.203, 23.107, 23.234, 23.271 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5369 | 340055 | CT4 Stage 3 for GTP v2 protocol | SAES-SA-FP_LTE-GTP | 4 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5370 | 350043 | SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF | 3 | Rel-8 | S2,C4 | Tue 02/01/07 | Fri 06/03/09 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | - | 34 |  |  |  | Thu 26/04/07 | Wed 28/07/10
5371 | 370007 | Stage 2 for SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF-St2 | 4 | Rel-8 | S2 | Tue 02/01/07 | Thu 05/06/08 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5372 | 370018 | CT4 Stage 3 for PMIP protocol within EPC | SAES-SA-FP_LTE-IETF | 4 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.275, 29.282 | 37 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5373 | 410004 | Mobile IPv4 (MIPv4) based Mobility protocols | SAES-SA-FP_LTE-IETF | 4 | Rel-8 | C4 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-090247 | - | Motorola | Lewis Milton | CP#42 completed | 29.279 | 41 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5374 | 340020 | Stage 3 for UE Non-Access-Stratum (NAS) mobility procedures in idle and active mode | SAES-LTE | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5375 | 340050 | Stage 3 for Session management, bearer control and QoS aspects | SAES-LTE | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5376 | 340053 | Stage 3 for security aspects of LTE Access | SAES-LTE | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5377 | 340025 | Stage 3 for QoS mechanisms | SAES-LTE | 3 | Rel-8 | C3 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#42 completed | 29.213 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5378 | 340026 | Stage 3 for EPC - HSS interface | SAES-LTE | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5379 | 350026 | SAE for Interoperation between LTE and legacy cellular PS accesses | SAES-SA-FP_3GPP | 2 | Rel-8 | S2,C1,C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
5380 | 370008 | Stage 2 for Interoperation between LTE and 2G/3G | EPSto2_3G | 3 | Rel-8 | S2 | Mon 05/02/07 | Thu 18/09/08 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.401, 23.402 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5381 | 380031 | Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G | SAES-SA-FP_3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 38 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
5382 | 340018 | Stage 2 GPRS enhancements for LTE access | SAES-GPRS_LTE | 3 | Rel-8 | S2 | Tue 04/09/07 | Thu 18/09/08 | 100% | SP-080132 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.401 | 34 |  |  |  | Fri 23/06/06 | Wed 28/07/10
5383 | 390008 | Stage 2 GPRS for EPC (23.060, etc.) | SAES-SA-FP_3GPP | 3 | Rel-8 | S2 | Mon 14/01/08 | Thu 18/09/08 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#41 completed | 23.06 | 39 | 21 |  |  | Wed 19/09/07 | Wed 28/07/10
5384 | 340056 | Stage 3 for EPC - GPRS | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5385 | 380032 | Stage 3 for EPC to UTRAN | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281 | 38 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5386 | 380033 | Stage 3 for EPC to 3GPP2 | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.277, 29.276 | 38 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5387 | 370009 | Stage 2 for Interoperation between LTE and CDMA2000 | EPStoC2k | 3 | Rel-8 | S2 | Mon 18/06/07 | Thu 18/09/08 | 100% | SP-080132 | - | Motorola, Vodafone | Irfan.Ali@motorola.com, chris.pudney@vodafone.com | SP#41 completed (except: Handover of multiple PDNs=>Rel-9) | 23.401, 23.402 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5388 | 360023 | Stage 3 for Inter-system mobility between E-UTRAN and CDMA2000 | SAES-SA-FP_3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.301, 24.302 |  |  |  |  | Wed 12/09/07 | Wed 28/07/10
5389 | 340061 | Stage 3 for MME - SGSN signalling free protocol | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272, 29.274 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5390 | 350027 | SAE for support for non-3GPP accesses | SAES-SA-FP_n3GPP | 2 | Rel-8 | S2,S3,C1,C4,IETF | Tue 02/01/07 | Fri 15/06/12 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037 | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
5391 | 350044 | Stage 2 for Host-based Mobility aspects | SAES-SA-FP_n3GPP-HBMob | 3 | Rel-8 | S2 | Tue 02/01/07 | Thu 05/06/08 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402 |  |  |  |  | Thu 26/04/07 | Wed 28/07/10
5392 | 350045 | Stage 2 for Network-based Mobility aspects | SAES-SA-FP_n3GPP-NBMob | 3 | Rel-8 | S2 | Tue 02/01/07 | Thu 18/09/08 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.402 |  |  |  |  | Thu 26/04/07 | Wed 28/07/10
5393 | 360022 | Stage 3 for Mobility management based on DSMIPv6 | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303 |  |  |  |  | Wed 12/09/07 | Wed 28/07/10
5394 | 521011 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt) | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1-IETF | Mon 05/02/07 | Fri 15/06/12 | 100% | CP-080493 | - | Mark Jones | - | CP#56 completed; 9/4/21: RFC 6610 added; | RFC 6610 (was draft-ietf-mip6-hiopt); RFC 6610 | 52 | 27 |  |  | Mon 20/06/11 | Fri 09/04/21
5395 | 521012 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (RFC6275) | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1-IETF | Mon 05/02/07 | Fri 29/07/11 | 100% | CP-080493 | - | - | - | SP#53/IETF#81 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis) | 52 | 27 |  |  | Mon 20/06/11 | Wed 31/08/11
5396 | 390009 | Stage 3 for Mobility management based on MIP v4 | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304 | 39 | 21 |  |  | Mon 03/03/08 | Wed 28/07/10
5397 | 380030 | Stage 3 for Inter-system mobility between E-UTRAN and non 3GPP accesses | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 38 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
5398 | 360019 | Stage 2 for Optimized Dual-Radio Handover with WiMAX | SAES-SA-FP_n3GPP-OptWIMAX | 3 | Rel-8 | S2 | Mon 25/06/07 | Thu 05/06/08 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402 |  |  |  |  | Thu 26/04/07 | Wed 28/07/10
5399 | 390045 | Stage 2 Security aspects for non-3GPP Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | S3 | Wed 12/03/08 | Thu 11/12/08 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.402, 33.210, 33.310 | 39 | 21 |  |  | Wed 19/03/08 | Wed 28/07/10
5400 | 370010 | Stage 3 security aspects for DSMIPv6 Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303 | 37 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5401 | 390172 | Stage 3 security aspects for MIPv4 Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5402 | 360021 | Stage 3 for Access to the EPC via non-3GPP access networks | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.302, 24.312 |  |  |  |  | Wed 12/09/07 | Wed 28/07/10
5403 | 370011 | Stage 3 for interfaces within EPC | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | Wed 19/09/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.281 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
5404 | 340057 | Stage 3 for Interfaces EPC - non-3GPP IP access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 06/03/09 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.273, 29.275 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5405 | 521013 | (IETF) Stage 3 for Interfaces EPC - non-3GPP IP access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4-IETF | Mon 05/02/07 | Fri 15/06/12 | 100% | CP-090247 | - | Lionel Morand | - | CP#56 completed | RFC 6611 (was draft-ietf-mip6-bootstrapping-integrated) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
5406 | 340058 | Stage 3 for AAA/HSS related | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5407 | 340059 | Stage 3 for EPC - AAA interface | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | Mon 05/02/07 | Fri 05/12/08 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
5408 | 360018 | Deleted (already covered) SAES-SA-FP_n3GPP Optimized Handover with CDMA | SAES-SA-FP_n3GPP-OptCDMA | 3 | Rel-8 | S2 | Mon 25/06/07 | Mon 25/06/07 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - |  |  | SP-37 |  | Thu 26/04/07 | Tue 24/03/09
5409 | 350030 | Single Radio Voice Call Continuity for 3GPP (SRVCC) | SAES-SRVCC | 2 | Rel-8 | S2,C1,C4 | Tue 02/01/07 | Fri 06/03/09 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | CP#43 completed. SP#38 WID approved (extract from SAE WID SP-070817). | - |  |  |  |  | Thu 29/03/07 | Wed 28/07/10
5410 | 350130 | Stage 2 for 2G/3G SRVCC | SAES-SRVCC | 3 | Rel-8 | S2 | Tue 02/01/07 | Thu 18/09/08 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | SP#41 completed. SP#38 WID approved | New 23.216 |  |  |  |  | Thu 29/03/07 | Wed 28/07/10
5411 | 410005 | Stage 3 for SRVCC in EPS | SAES-SRVCC | 3 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080793 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 23.009, 24.008, New 24.301 | 41 | 21 |  |  | Wed 03/09/08 | Wed 28/07/10
5412 | 410006 | MME to MSC interface for SRVCC | SAES-SRVCC | 3 | Rel-8 | C4 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080793 | - | Nokia Siemens Networks | Giorgi Gulbani | CP#43 completed | 23.003, 23.008, New (29.274, 29.277, 29.280) | 41 | 21 |  |  | Mon 01/09/08 | Wed 28/07/10
5413 | 360020 | Voice Call Continuity for CDMA2000 1X | SAES-VCC_1X | 2 | Rel-8 | S2 | Mon 25/06/07 | Thu 05/06/08 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - |  |  |  |  | Thu 29/03/07 | Wed 28/07/10
5414 | 350031 | SAE impacts on IMS | SAES-SA_IMS | 2 | Rel-8 | S2 | Tue 02/01/07 | Thu 05/06/08 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - |  |  |  |  | Thu 29/03/07 | Wed 28/07/10
5415 | 390036 | CS Fallback in EPS | SAES-CSFB | 2 | Rel-8 | S2,C1,C4 | Wed 12/03/08 | Fri 06/03/09 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | CP#43 completed | - | 39 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
5416 | 400001 | Stage 2 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | S2 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | SP#40 completed | New (23.272, 23.401) | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
5417 | 400102 | CT1 part of Stage 3 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#43 completed | 24.007, 24.008, 24.011, 29.018, New (24.301, 24.801, 29.118) | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
5418 | 400003 | CT4 part of Stage 3 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | C4 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#42 completed | 23.007, 23.008, 29.274, New 29.277 | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
5419 | 390039 | System enhancements for the use of IMS services in local breakout | SAES-IMS_LBO | 2 | Rel-8 | S2 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080090 | - | Telecom Italia | mario.madella@telecomitalia.it | SP#40 completed | 23.228, 23.221, 23.203 | 39 | 21 |  |  | Tue 02/10/07 | Wed 28/07/10
5420 | 390010 | EPC Data Definitions | EPC-OAM | 2 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | - | - | - | - | SP#43 completed | - | 39 | 21 |  |  | Fri 17/06/05 | Wed 28/07/10
5421 | 380037 | EPC Network Resource Model (NRM) Integration Reference Point (IRP) | EPC-OAM | 3 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | SP-070737 | - | Huawei | WANG, Xuelong | SP#43 completed | New (32.751, 32.752, 32.753, 32.755) | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
5422 | 390011 | Performance measurements for EPC | EPC-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 12/03/09 | 100% | SP-080061 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | New 32.426 | 39 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
5423 | 380038 | EPC Charging | EPC-CH | 2 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | SP-070736 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.296, 32.251, 32.252, 32.298, 32.299 | 38 | 21 |  |  | Fri 17/06/05 | Wed 28/07/10
5424 | 400104 | Domain Name System Procedures for Evolved Packet System (DEPS) | SAES-DEPS | 2 | Rel-8 | C4 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080280 | - | TeliaSonera | jouni.korhonen@teliasonera.com | CP#43 completed | 23.003, New 29.303 | 40 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5425 | 410007 | InterWorking Function (IWF) between MAP based and Diameter based interfaces | SAES-MAP2Diam | 2 | Rel-8 | C4 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080644 | - | Huawei | liming49985@huawei.com | CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam) | New 29.305 | 41 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
5426 | 390021 | CT6 aspects of SAE | SAES | 2 | Rel-8 | C6 | Fri 07/03/08 | Fri 03/06/11 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed core specification | - | 39 | 21 |  |  | Wed 12/03/08 | Wed 28/07/10
5427 | 390121 | Core specification for CT6 aspects of SAE | SAES | 3 | Rel-8 | C6 | Fri 07/03/08 | Fri 29/05/09 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed (specified Network Measurement Results collection via USAT) | 31.102, 31.111 | 39 | 21 |  |  | Wed 12/03/08 | Wed 28/07/10
5428 | 420018 | Test interworking of LTE Terminals with the USIM | SAES-USIM_LTE-Test | 3 | Rel-8 | C6 | Fri 05/12/08 | Fri 10/12/10 | 100% | CP-100598 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#50 completed. Steering of Roaming test cases have been introduced. Remaining issues CSG display testing (Provide Local Information, Call Control for EPS/PDN, Event Download (Access Technology Change - Multiple Access Technologies) | 31.121, 31.124 | 42 | 22 |  |  | Wed 03/12/08 | Sun 28/11/10
5429 | 490015 | Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS) | SAES-ISIM_IMS_Test | 3 | Rel-8 | C6 | Fri 17/09/10 | Fri 03/06/11 | 100% | CP-100602 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229). | 31.121, 31.124, New 31.134 | 49 | 25 |  |  | Mon 06/09/10 | Wed 18/05/11
5430 | 390018 | Issues for CT1 TR 24.801 | SAES | 2 | Rel-8 | C1 | Thu 04/01/07 | Fri 05/12/08 | 100% | CP-080068 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.801 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5431 | 390019 | Issues for CT3 TR 29.804 | SAES | 2 | Rel-8 | C3 | Mon 05/02/07 | Fri 12/09/08 | 100% | CP-080068 | - | Ericsson | j.javier.pastor@ericsson.com | CP#41 completed | 29.804 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
5432 | 390020 | Deleted - Issues for CT4 TR 29.803 | SAES | 2 | Rel-8 | C4 | Thu 04/01/07 | Fri 12/09/08 | 100% | CP-080068 | - | Huawei | - | CP#41 Work stopped and continued in Normative specifications | 29.803 | 39 | 21 | CP-41 | PCG-21 | Wed 19/07/06 | Tue 24/03/09
5433 | 350029 | Deleted (covered by 380068): Functions and procedures for SAE to support LCS | SAES-SA-FP_LCS | 2 | Rel-8 | S2 | Mon 03/03/08 | Mon 03/03/08 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - |  |  | SP-37 |  | Thu 29/03/07 | Tue 24/03/09
5434 | 350032 | Deleted (covered by 380064): SAE aspects of Emergency Calls | SAES-SA-EmCall | 2 | Rel-8 | S2 | Mon 03/03/08 | Mon 03/03/08 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - |  |  | SP-37 |  | Thu 29/03/07 | Tue 24/03/09
5435 | 340019 | Deleted - CT aspects of SAES | SAES-St3 | 2 | Rel-8 | C3,C1,C4 | Tue 04/09/07 | Fri 14/03/08 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5436 | 350019 | Deleted - CT1 aspects of SAES | SAES-St3 | 3 | Rel-8 | C1 | Tue 04/09/07 | Tue 04/09/07 | 100% | CP-060674 | - | - | - | SP#37 stopped | - |  |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5437 | 340052 | Deleted - Interoperability | SAES-St3-interop | 3 | Rel-8 | C1 | Fri 14/03/08 | Fri 14/03/08 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5438 | 350020 | Deleted - CT3 aspects of SAES | SAES | 3 | Rel-8 | C3 | Tue 04/09/07 | Tue 04/09/07 | 100% | CP-060675 | - | - | - | SP#37 stopped | - |  |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5439 | 350021 | Deleted - CT4 aspects of SAES | SAES | 3 | Rel-8 | C4 | Tue 04/09/07 | Tue 04/09/07 | 100% | CP-060676 | - | - | - | SP#37 stopped | 29.803 |  |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5440 | 340021 | Deleted - UE to EPC NAS signalling (incl. MBMS and QoS aspects) | SAES-St3-sig | 3 | Rel-8 | C1 | Fri 14/03/08 | Fri 14/03/08 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5441 | 340027 | Deleted - User and Control plane protocols | SAES-St3-prot | 3 | Rel-8 | C4 | Fri 21/09/07 | Fri 21/09/07 | 100% | CP-060676 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
5442 | 340037 | Deleted - Architecture enhancements for non-3GPP accesses | SAES-non_3GPP | 2 | Rel-8 | S2 | Tue 04/09/07 | Tue 04/09/07 | 100% | SP-060926 | - | Motorola | Irfan.Ali@motorola.com | SP#34 stopped. Replaced by UID_350027 and its children | 23.402 | 34 |  | SP-34 |  | Fri 23/06/06 | Tue 24/03/09
5443 | 320030 | Deleted - Stage 2 of architecture for the 3GPP System Architecture Evolution | SAES-St2 | 2 | Rel-8 | S2 | Tue 02/10/07 | Tue 02/10/07 | 100% | SP-060926 | - | Vodafone | chris.pudney@vodafone.com | SP#34 stopped. Replaced by UIDs 340018 and 340037. (SP#34 report discussion of SP-060917.) | 23.002, 23.060, 23.107, 23.203, 23.228, 23.234, 23.246, 23.271, 23.279 |  |  | SP-34 |  | Wed 19/07/06 | Tue 24/03/09
5444 | 350023 | Deleted - SA aspects of System Architecture Evolution | SAES-SA | 2 | Rel-8 | S2 | Wed 12/04/06 | Mon 01/10/07 | 100% | - | - | - | - | SP#34 stopped | - |  |  | SP-34 |  | Thu 29/03/07 | Tue 24/03/09
5445 | 450022 | Conformance Test Aspects – Mobility management based on DSMIPv6 (Dual-Stack Mobile IPv6) | DSMIPv6_UEConTest | 1 | Rel-8 | R5 | Fri 18/09/09 | Fri 17/09/10 | 100% | RP-090754 | RP-100738 | Qualcomm | Lena Chaponniere (lchaponn@qualcomm.com) | RP#49 completed. Testing for CT1's UID_360022 (24.303) under Rel-8 Feature SAES | 36.508, 36.523-1, 36.523-2, 36.523-3 | 45 | 23 |  |  | Tue 15/09/09 | Thu 09/09/10
5446 | 370025 | IMS Centralized Service control | ICSRA | 1 | Rel-8 | S1,S2,C1,C3,C4,IETF | Tue 01/11/05 | Tue 09/12/14 | 100% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | CP#46 completed | - | 37 |  |  |  | Tue 02/10/07 | Wed 02/12/09
5447 | 380039 | Stage 1 for ICS Requirement and Architecture | ICSRA | 2 | Rel-8 | S1 | Mon 03/09/07 | Wed 12/03/08 | 100% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | SP#39 completed | 22.101 | 38 | 21 |  |  | Tue 02/10/07 | Wed 23/07/08
5448 | 380040 | Stage 2 for ICS Requirement and Architecture | ICSRA-St2 | 2 | Rel-8 | S2 | Fri 14/12/07 | Thu 05/06/08 | 100% | SP-070924 | - | Alcatel-Lucent | - | SP#40 completed | 23.292, 23.206 | 38 | 21 |  |  | Mon 03/03/08 | Wed 23/07/08
5449 | 400205 | Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data | ICSRA | 2 | Rel-8 | C1,C3,C4,IETF | Tue 01/11/05 | Tue 09/12/14 | 100% | CP-091046 | - | Ericsson | sean.schneyer@ericsson.com | CP#46 completed | - | - | - |  |  | Wed 02/12/09 | Mon 07/12/09
5450 | 400005 | CT1 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#46 completed | 24.229, new (24.292, 24.286) | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
5451 | 521014 | (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns) | ICSRA | 3 | Rel-8 | C1-IETF | Fri 30/05/08 | Tue 09/12/14 | 100% | CP-091046 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added; | draft-ietf-salud-alert-info-urns; RFC 7462 | 52 | 27 |  |  | Mon 20/06/11 | Fri 09/04/21
5452 | 521015 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 6871) | ICSRA | 3 | Rel-8 | C1-IETF | Fri 30/05/08 | Fri 01/03/13 | 100% | CP-091046 | - | Andrew Allen | - | CP#59 completed | RFC 6871 (was draft-ietf-mmusic-sdp-media-capabilities) | 52 | 27 |  |  | Mon 20/06/11 | Thu 28/02/13
5453 | 521016 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7195) | ICSRA | 3 | Rel-8 | C1-IETF | Fri 30/05/08 | Fri 13/06/14 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7195 (was draft-ietf-mmusic-sdp-cs) | 52 | 27 |  |  | Mon 20/06/11 | Fri 06/06/14
5454 | 521017 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7006) | ICSRA | 3 | Rel-8 | C1-IETF | Tue 03/06/08 | Fri 06/12/13 | 100% | CP-091046 | - | Andrew Allen | - | CP#62 completed | RFC7006 (was draft-ietf-mmusic-sdp-miscellaneous-caps) | 52 | 27 |  |  | Mon 20/06/11 | Wed 27/11/13
5455 | 400006 | CT3 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C3 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-091046 | - | Mavenir | Brett Wallis ( brett@mavenir.com) | CP#43 completed | new 29.292 | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
5456 | 400007 | CT4 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C4 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#42 completed | 23.003, 29.232, 23.018, 29.002 | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
5457 | 521018 | (IETF) CT4 aspects - Stage 3 for ICSRA (RFC 7254) | ICSRA | 3 | Rel-8 | C4-IETF | Tue 01/11/05 | Fri 13/06/14 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7254 (was draft-montemurro-gsma-imei-urn) | 52 | 27 |  |  | Mon 20/06/11 | Fri 06/06/14
5458 | 400105 | Deleted - Stage 3 for ICSRA – I1 interface | ICSRA | 3 | Rel-8 | C1 | Fri 30/05/08 | Fri 12/09/08 | 100% | CP-080492 | - | Huawei | xupeili@huawei.com | CP#41 work stopped | 24.293 | 40 | 21 | CP-41 | PCG-21 | Mon 03/03/08 | Wed 02/12/09
5459 | 370059 | IMS Multimedia Telephony and Supplementary Services | IMSTSS | 1 | Rel-8 | S1,S5,C1,C3,C4,IETF | Wed 02/05/07 | Tue 09/12/14 | 100% | - | - | - | - | SP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
5460 | 370060 | General aspects of IMS Sup Services | IMSSS-Gal | 2 | Rel-8 | S1,C1,C3,C4 | Mon 03/09/07 | Fri 06/03/09 | 100% | SP-070691 | - | Ericsson | Susana Sabater | CP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
5461 | 370023 | Service and Capability for Core IMS - inclusion of TISPAN requirements | TISCAPR8 | 3 | Rel-8 | S1 | Mon 03/09/07 | Fri 14/12/07 | 100% | SP-070691 | - | Ericsson | Susana Sabater | SP#39 completed | 22.228, 22.115, 22.101 | 37 |  |  |  | Tue 02/10/07 | Thu 20/03/08
5462 | 380001 | Documentation of TISPAN R1 and R2 in CT1 | REDOC_TIS-C1 | 3 | Rel-8 | C1 | Wed 28/11/07 | Fri 12/09/08 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 24.141, 24.147, 24.173, 24.229, 24.247, 24.341, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.616, 24.623, 24.628, 24.629, 24.647, 24.654 | 38 | 21 |  |  | Wed 28/11/07 | Fri 01/08/08
5463 | 380002 | Documentation of TISPAN R1 and R2 in CT3 | REDOC_TIS-C3 | 3 | Rel-8 | C3 | Wed 28/11/07 | Fri 06/03/09 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#43 completed | 29.162, 29.163, 29.658 | 38 | 21 |  |  | Wed 28/11/07 | Mon 07/12/09
5464 | 380003 | Documentation of TISPAN R1 and R2 in CT4 | REDOC_TIS-C4 | 3 | Rel-8 | C4 | Wed 28/11/07 | Fri 12/09/08 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 29.228, 29.229 | 38 | 21 |  |  | Wed 28/11/07 | Mon 01/09/08
5465 | 370062 | IMS Multimedia Telephony Service | IMS-MMTel | 2 | Rel-8 | S1,S5 | Mon 10/09/07 | Thu 12/03/09 | 100% | - | - | - | - | SP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
5466 | 370024 | Merging TISPAN MMTel [requirements] for Common IMS | TMMTEL | 3 | Rel-8 | S1 | Mon 10/09/07 | Fri 07/12/07 | 100% | SP-070569 | - | Nokia Siemens Networks | - | SP#38 completed | 22.173 | 37 |  |  |  | Tue 02/10/07 | Mon 19/11/07
5467 | 380041 | Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging | MMTel-CH | 3 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | SP-080848 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | CP#43 completed | 32.275, 32.298/299 | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
5468 | 380006 | Call Completion on Busy Subscriber (CCBS)/Call Completion on Non-Reachable (CCNR) on IMS | CCBS_CCNR | 2 | Rel-8 | C1,C3,IETF | Wed 02/05/07 | Fri 14/06/13 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Wed 14/11/07 | Thu 29/11/07
5469 | 380007 | CT1 part of Stage 3 CCBS_CCNR | CCBS_CCNR | 3 | Rel-8 | C1 | Wed 02/05/07 | Fri 06/03/09 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.642, 24.229, 24.173 | 38 | 21 |  |  | Wed 14/11/07 | Wed 11/01/12
5470 | 380008 | CT3 part of Stage 3 CCBS_CCNR | CCBS_CCNR | 3 | Rel-8 | C3 | Wed 02/05/07 | Fri 05/12/08 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163 | 38 | 21 |  |  | Wed 14/11/07 | Wed 11/01/12
5471 | 521019 | (IETF) Stage 3 CCBS_CCNR [RFC 6910 (was draft-ietf-bliss-call-completion)] | CCBS_CCNR | 3 | Rel-8 | C1-IETF,C3-IETF | Wed 02/05/07 | Fri 14/06/13 | 100% | CP-080215 | - | Roland Jesske | - | CP#60 completed | RFC 6910 (was draft-ietf-bliss-call-completion) | 52 | 27 |  |  | Mon 20/06/11 | Mon 10/06/13
5472 | 390058 | Flexible Alerting | FA | 2 | Rel-8 | S1,C1 | Wed 30/01/08 | Fri 06/03/09 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | - | 39 | 21 |  |  | Mon 03/03/08 | Tue 15/04/08
5473 | 390059 | Stage 1 FA | FA | 3 | Rel-8 | S1 | Wed 30/01/08 | Thu 05/06/08 | 100% | - | - | Telecom Italia | - | SP#40 completed | 22.173 | 39 | 21 |  |  | Mon 03/03/08 | Thu 18/09/08
5474 | 390015 | Stage 3 FA | FA | 3 | Rel-8 | C1 | Wed 30/01/08 | Fri 06/03/09 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | 24.239, 24.173 | 39 | 21 |  |  | Mon 03/03/08 | Fri 20/02/09
5475 | 380009 | Communication Wait on IMS | CW_IMS | 2 | Rel-8 | C1,C3,IETF | Fri 22/06/07 | Tue 09/12/14 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Wed 14/11/07 | Tue 15/04/08
5476 | 380010 | CT1 part of Stage 3 CW-IMS | CW_IMS | 3 | Rel-8 | C1 | Fri 30/11/07 | Fri 06/03/09 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.615, 24.229, 24.173 | 38 | 21 |  |  | Wed 14/11/07 | Fri 20/02/09
5477 | 521020 | (IETF) Stage 3 CW-IMS (salud-alert-info-urns) | CW_IMS | 3 | Rel-8 | C1-IETF | Fri 22/06/07 | Tue 09/12/14 | 100% | CP-080214 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added; | draft-ietf-salud-alert-info-urns; RFC 7462 | 52 | 27 |  |  | Mon 20/06/11 | Fri 09/04/21
5478 | 380011 | CT3 part of Stage 3 CW-IMS | CW_IMS | 3 | Rel-8 | C3 | Fri 30/11/07 | Thu 04/12/08 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163 | 38 | 21 |  |  | Wed 14/11/07 | Fri 21/11/08
5479 | 370103 | IMS Charging | CH8_IMS | 2 | Rel-8 | S5 | Mon 17/09/07 | Thu 12/03/09 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298 | 37 |  |  |  | Sat 15/09/07 | Sun 23/03/08
5480 | 370003 | Add Interconnection Border Control Function (IBCF) to IMS Charging | CH8_IMS | 3 | Rel-8 | S5 | Mon 17/09/07 | Wed 12/03/08 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298 | 37 |  |  |  | Sat 15/09/07 | Sun 23/03/08
5481 | 380042 | Advice of Charge (AoC) support in IMS Charging | CH8_IMS | 3 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | SP-070739 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.260, 32.296, 32.298, 32.299, new 32.280 | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
5482 | 390035 | 3GPP2 Input to Common IMS | CIMS_3GPP2 | 1 | Rel-8 | S1,S2,S3,C1,C3,C4 | Fri 07/03/08 | Thu 11/12/08 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | TSG#42 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | - | 39 | 21 |  |  | Tue 02/10/07 | Tue 24/03/15
5483 | 390050 | Stage 1 CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S1 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | 22.228, 22.173, 22.101, 22.153 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
5484 | 390051 | Stage 2 CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S2 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | 23.002, 23.141, 23.203, 23.167, 23.228 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
5485 | 390052 | Security CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S3 | Wed 12/03/08 | Thu 11/12/08 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#42 completed [issues addressed under UID_370078 (IMS-Sec)]. Acronym changed from "CIMS_3GPP2, IMS_Common" | 33.141, 33.203, 33.210 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
5486 | 390113 | Stage 3 CIMS_3GPP2 | REDOC_3GPP2 | 2 | Rel-8 | C1,C3,C4 | Fri 07/03/08 | Thu 11/12/08 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | - | - | 39 | 21 |  |  | Mon 03/03/08 | Thu 04/12/08
5487 | 390013 | Stage 3 CIMS_3GPP2 (CT1) | REDOC_3GPP2 | 3 | Rel-8 | C1 | Fri 07/03/08 | Fri 05/12/08 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 23.218, 24.141, 24.147, 24.173, 24.229, 24.238, 24.247, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.629, 24.930 | 39 | 21 |  |  | Mon 03/03/08 | Thu 04/12/08
5488 | 390026 | Stage 3 CIMS_3GPP2 (CT3) | REDOC_3GPP2 | 3 | Rel-8 | C3 | Fri 07/03/08 | Fri 05/12/08 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.163, 29.212, 29.213, 29.214 | 39 | 21 |  |  | Mon 03/03/08 | Thu 26/03/09
5489 | 390027 | Stage 3 CIMS_3GPP2 (CT4) | REDOC_3GPP2 | 3 | Rel-8 | C4 | Fri 07/03/08 | Thu 11/12/08 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.228, 29.229, 29.328, 29.329 | 39 | 21 |  |  | Mon 03/03/08 | Thu 26/03/09
5490 | 350005 | IMS Enhancements for support of Packet Cable access | PktCbl | 1 | Rel-8 | S2,S3,C1,C3,C4 | Wed 06/12/06 | Fri 30/05/08 | 100% | - | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | - | 35 |  |  |  | Thu 29/03/07 | Thu 29/03/07
5491 | 350008 | IMS Enhancements for Cable Client Types and Deployment Models | PktCbl-Deploy | 2 | Rel-8 | S2,C1 | Mon 05/02/07 | Fri 30/05/08 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | - |  |  |  |  | Thu 29/03/07 | Thu 29/03/07
5492 | 350009 | Architecture aspects of PktCbl-Deploy | PktCbl-Deploy | 3 | Rel-8 | S2 | Mon 05/02/07 | Thu 06/12/07 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | SP#38 completed | 23.228 |  |  |  |  | Thu 29/03/07 | Tue 27/05/08
5493 | 350010 | CT1 aspects of PktCbl-Deploy | PktCbl-Deploy | 3 | Rel-8 | C1 | Mon 26/03/07 | Fri 30/05/08 | 100% | CP-070122 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | - |  |  |  |  | Thu 29/03/07 | Tue 13/05/08
5494 | 350011 | IMS Inter-working aspects in Support of Cable Regulatory requirements | PktCbl-Intw | 2 | Rel-8 | S2,C1,C3 | Mon 05/02/07 | Fri 14/03/08 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | CP#39 completed | - |  |  |  |  | Thu 29/03/07 | Thu 29/03/07
5495 | 350012 | Architecture aspects of PktCbl-Interwork | PktCbl-Intw | 3 | Rel-8 | S2 | Mon 05/02/07 | Fri 14/09/07 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | SP#37 completed | 23.228 |  |  |  |  | Thu 29/03/07 | Tue 29/05/07
5496 | 350013 | CT1,CT3 aspects of PktCbl-Interwork | PktCbl-Intw | 3 | Rel-8 | C1,C3 | Mon 26/03/07 | Fri 14/03/08 | 100% | CP-070575 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 24.229 |  |  |  |  | Thu 29/03/07 | Mon 03/03/08
5497 | 340008 | IMS Enhancements for Security Requirements in Support of Cable Deployments | PktCbl-Sec | 2 | Rel-8 | S3,C1,C3,C4 | Wed 06/12/06 | Fri 30/05/08 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | CP#40 completed | - | 34 |  |  |  | Fri 04/11/05 | Tue 29/05/07
5498 | 350033 | SA3 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | S3 | Wed 06/12/06 | Wed 12/03/08 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | SP#39 completed | 33.203, 33.210, 33.220 |  |  |  |  | Fri 04/11/05 | Sun 23/03/08
5499 | 350006 | CT1 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C1 | Mon 26/03/07 | Fri 30/05/08 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | 24.229 |  |  |  |  | Thu 29/03/07 | Tue 27/05/08
5500 | 380029 | CT3 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C3 | Mon 26/03/07 | Fri 30/11/07 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#38 completed | 29.163 | 38 | 21 |  |  | Thu 29/03/07 | Fri 07/03/08
5501 | 350007 | CT4 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C4 | Mon 26/03/07 | Fri 14/03/08 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 29.228, 29.229, 23.008 |  |  |  |  | Thu 29/03/07 | Tue 27/05/08
5502 | 360012 | IMS System enhancements for corporate network access | IMS_Corp | 1 | Rel-8 | S2,S1,C1,C4,IETF | Fri 22/06/07 | Fri 12/09/14 | 100% | SP-080095 | - | Orange | Delphin Barankanira | CP#47 completed | - |  |  |  |  | Fri 22/06/07 | Thu 29/07/10
5503 | 390049 | SA1 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | S1 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080095 | - | Telecom Italia | - | SP#40 completed | - | 39 | 21 |  |  | Fri 22/06/07 | Mon 19/05/08
5504 | 360014 | SA2 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | S2 | Fri 22/06/07 | Thu 18/09/08 | 100% | SP-080095 | - | Orange | Delphin Barankanira | no Stage 2 impacts | 23.228 |  |  |  |  | Fri 22/06/07 | Thu 29/07/10
5505 | 390022 | CT1 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | C1 | Fri 07/03/08 | Fri 19/03/10 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 24.229, 24.503 | 39 | 21 |  |  | Fri 07/03/08 | Wed 03/03/10
5506 | 531002 | (IETF) CT1 aspects of IMS_Corp (RFC 7316) | IMS_Corp | 2 | Rel-8 | C1-IETF | Wed 29/06/11 | Fri 12/09/14 | 100% | CP-080220 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | CP#65 completed | RFC 7316 (was draft-vanelburg-dispatch-private-network-ind) | 53 | 27 |  |  | Fri 29/07/11 | Wed 03/09/14
5507 | 390023 | CT4 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | C4 | Tue 26/02/08 | Fri 05/12/08 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#42 completed | 29.228, 29.229, 23.003, 23.008, 29.433 | 39 | 21 |  |  | Fri 07/03/08 | Sat 22/11/08
5508 | 380069 | Maintenance of TISPAN documentation | MAINTISP | 1 | Rel-8 | S2,C1,C3,C4,IETF | Mon 02/07/07 | Fri 13/06/14 | 100% | - | - | - | - | SP#40 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Thu 29/07/10
5509 | 380005 | Maintenance of TISPAN R2 | MAINT_R2 | 2 | Rel-8 | C1,C3,C4 | Fri 09/11/07 | Fri 07/03/08 | 100% | CP-080229 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.406, 24.407, 24.410, 24.411, 24.423, 24.430, 24.447, 24.451, 24.454, 24.503, 24.505, 24.508, 24.516, 24.528, 24.529, 29.412, 29.421, 29.433, 29.458, 29.527, 29.624 | 38 | 21 |  |  | Mon 19/11/07 | Mon 07/12/09
5510 | 521021 | Deleted - (IETF) Maintenance of TISPAN R2 (avasarala-dispatch-comm-div-notification) | MAINT_R2_IETF | 2 | Rel-8 | C1-IETF | Fri 09/11/07 | Fri 13/06/14 | 100% | CP-080229 | - | Andrew Allen | - | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 52 | 27 | SP-69 |  | Mon 20/06/11 | Fri 06/06/14
5511 | 380043 | Documentation of TISPAN NGN R1 and R2 in 3GPP SA2 | IMS_Comm_Doc | 2 | Rel-8 | S2 | Mon 14/01/08 | Thu 05/06/08 | 100% | SP-070823 | - | Nokia Siemens Networks | jozsef.varga@nsn.com | SP#40 completed | 23.228, 23.204, 23.167 | 38 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
5512 | 380044 | Maintenance of TISPAN release 2 common IMS | IMS_Comm_Mtce8 | 2 | Rel-8 | S2 | Mon 02/07/07 | Thu 06/12/07 | 100% | SP-070916 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | SP#38 completed | 23.506, 23.507,23.517, 23.521 | 38 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
5513 | 390056 | IMS Service Continuity | IMS-Cont | 1 | Rel-8 | S2,S1,C1 | Wed 12/03/08 | Fri 29/05/09 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | CP#44 completed | - | 39 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
5514 | 390072 | Stage 1 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | S1 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | - | 39 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
5515 | 390057 | Stage 2 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | S2 | Wed 12/03/08 | Thu 05/06/08 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | 23.237, 23.292 | 39 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
5516 | 400011 | Stage 3 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 29/05/09 | 100% | CP-080491 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#44 completed | 24.237, 24.229, 24.216 | 40 | 21 |  |  | Tue 02/10/07 | Wed 13/05/09
5517 | 370078 | Security Enhancements for IMS | IMS-Sec | 1 | Rel-8 | S3,C1,C4 | Tue 19/09/06 | Fri 06/03/09 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | CP#43 completed | - | 37 |  |  |  | Fri 04/11/05 | Fri 20/02/09
5518 | 360017 | Stage 2 for IMS-Sec | IMS-Sec | 2 | Rel-8 | S3 | Thu 01/03/07 | Thu 11/12/08 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards | 33.203, 33.141, 33.803 |  |  |  |  | Wed 21/11/07 | Mon 06/04/09
5519 | 390054 | CT1 part of Stage 3 for IMS-Sec | IMS-Sec | 2 | Rel-8 | C1 | Tue 19/09/06 | Fri 05/12/08 | 100% | - | - | Ericsson | - | CP#42 completed | - | 39 | 21 |  |  | Wed 21/11/07 | Thu 04/12/08
5520 | 390154 | CT4 part of Stage 3 for IMS-Sec | IMS-Sec | 2 | Rel-8 | C4 | Thu 07/06/07 | Fri 06/03/09 | 100% | - | - | Ericsson | - | CP#43 completed | - | 39 | 21 |  |  | Wed 21/11/07 | Fri 20/02/09
5521 | 380012 | CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA | 2 | Rel-8 | C1 | Wed 14/11/07 | Fri 06/03/09 | 100% | CP-070781 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 24.229 | 39 | 21 |  |  | Mon 19/11/07 | Fri 20/02/09
5522 | 380013 | CT4 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA-CT4 | 2 | Rel-8 | C4 | Wed 14/11/07 | Fri 30/05/08 | 100% | CP-070781 | - | Alcatel-Lucent | - | CP#40 completed | 29.229, 29.228, 23.008 | 39 | 21 |  |  | Mon 19/11/07 | Wed 14/05/08
5523 | 34046 | IMS initiated and controlled PSS and MBMS User Service | IMS_PSS_MBMS_US | 1 | Rel-8 | S4,S3,IETF | Wed 12/03/08 | Wed 21/09/11 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#39 WID approved | - |  |  |  |  | Tue 18/03/08 | Thu 30/06/11
5524 | 34146 | SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service | IMS_PSS_MBMS_US | 2 | Rel-8 | S4,S3 | Wed 12/03/08 | Wed 12/03/08 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#43 completed | 26.234, 26.346, 33.246, New 26.237 |  |  |  |  | Tue 18/03/08 | Thu 30/06/11
5525 | 521022 | (IETF) IMS initiated and controlled PSS and MBMS User Service (RFC 6080) | IMS_PSS_MBMS_US | 2 | Rel-8 | S4-IETF | Wed 12/03/08 | Wed 21/09/11 | 100% | SP-080201 | - | Ericsson | - | SP#53/IETF#81 completed | RFC 6080 (was draft-ietf-sipping-config-framework) | 52 | 27 |  |  | Mon 20/06/11 | Fri 23/08/13
5526 | 713024 | Multimedia interworking between IMS and CS networks | MIW-IMS | 1 | Rel-8 | C3,C4 | Fri 23/09/05 | Fri 05/12/08 | 100% | CP-070729 | - | Vodafone | nico.gabriele@vodafone.com | CP#42 completed | - | 71 | 36 |  |  | Mon 03/10/05 | Wed 10/12/08
5527 | 7013 | Stage 1 and 2 defined in earlier Releases | MIW-IMS | 2 | Rel-8 | S2 | Fri 23/09/05 | Wed 30/11/05 | 100% | - | - | Vodafone | nico.gabriele@vodafone.com | SP#31 Moved from FS section Feb 2006 | - |  |  |  |  | Thu 16/02/06 | Fri 30/07/10
5528 | 7014 | Stage 3 of MW-IMS | MIW-IMS-St3C3 | 2 | Rel-8 | C3 | Fri 23/09/05 | Fri 30/11/07 | 100% | CP-070096 | - | Vodafone | nico.gabriele@vodafone.com | Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021 | 29.863, 29.163 |  |  |  |  | Thu 16/02/06 | Tue 05/08/08
5529 | 380021 | Stage 3 for MW-IMS, MONA extension | MIW-IMS-St3C3_MONA | 2 | Rel-8 | C3 | Mon 05/11/07 | Fri 05/12/08 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.863, 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Mon 01/09/08
5530 | 380022 | Mn interface (MGCF – IM MGW) | MIW-IMS-St3C4 | 2 | Rel-8 | C4 | Wed 21/11/07 | Fri 05/12/08 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.332 | 38 | 21 |  |  | Wed 21/11/07 | Sat 22/11/08
5531 | 360029 | IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 1 | Rel-8 | C1,IETF | Fri 22/06/07 | Tue 09/12/14 | 100% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | - |  |  |  |  | Wed 05/09/07 | Fri 20/02/09
5532 | 360129 | CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 2 | Rel-8 | C1 | Fri 22/06/07 | Fri 06/03/09 | 100% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.218, 24.229, 24.930 |  |  |  |  | Wed 05/09/07 | Fri 20/02/09
5533 | 521023 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-bakker-sipping-3gpp-ims-xml-body-handling) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | Fri 22/06/07 | Fri 07/12/12 | 100% | CP-080794 | - | Andrew Allen | - | CP#58 completed. ietf-draft discontinued. Documented within 3GPP | draft-bakker-sipping-3gpp-ims-xml-body-handling | 52 | 27 |  |  | Mon 20/06/11 | Sat 24/11/12
5534 | 521024 | (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | Fri 22/06/07 | Fri 15/06/12 | 100% | CP-080794 | - | Keith Drage | - | CP#56 completed | RFC 6544 (was draft-ietf-mmusic-ice-tcp) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
5535 | 521025 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | Fri 22/06/07 | Tue 09/12/14 | 100% | CP-080794 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added; | draft-ietf-salud-alert-info-urns; RFC 7462 | 52 | 27 |  |  | Mon 20/06/11 | Fri 09/04/21
5536 | 380014 | Interworking between User-to-User Signalling (UUS) and SIP | UUSIW | 1 | Rel-8 | C1,C3,IETF | Fri 30/11/07 | Tue 09/12/14 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | - | 38 | 21 |  |  | Tue 13/11/07 | Wed 11/03/09
5537 | 380015 | CT1 part of Stage 3 MGCF UUSIW | UUSIW | 2 | Rel-8 | C1 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#42 completed | 24.279, 24.229 | 38 | 21 |  |  | Tue 13/11/07 | Fri 21/11/08
5538 | 521026 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui) | UUSIW | 2 | Rel-8 | C1-IETF,C3-IETF | Fri 30/11/07 | Tue 09/12/14 | 100% | CP-070782 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui) | RFC 7433 | 52 | 27 |  |  | Mon 20/06/11 | Tue 10/03/15
5539 | 551001 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn) | UUSIW | 2 | Rel-8 | C1-IETF,C3-IETF | Thu 17/03/11 | Tue 09/12/14 | 100% | CP-070782 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdn). June 2015: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn) | RFC 7434 | 55 | 28 |  |  | Sat 03/03/12 | Tue 10/03/15
5540 | 380016 | CT3 part of Stage 3 MGCF UUSIW | UUSIW | 2 | Rel-8 | C3 | Fri 30/11/07 | Thu 12/03/09 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Thu 19/02/09
5541 | 380018 | Support of Overlap signalling | Overlap | 1 | Rel-8 | C3,C1,C4 | Fri 30/11/07 | Fri 06/03/09 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Tue 13/11/07 | Fri 20/02/09
5542 | 380019 | Stage 3 Overlap (CT1) | Overlap | 2 | Rel-8 | C1 | Fri 30/11/07 | Fri 06/03/09 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 24.229 | 38 | 21 |  |  | Tue 13/11/07 | Fri 20/02/09
5543 | 380020 | Stage 3 Overlap (CT3) | Overlap | 2 | Rel-8 | C3 | Fri 30/11/07 | Fri 06/03/09 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Tue 25/11/08
5544 | 380120 | Stage 3 Overlap (CT4) | Overlap | 2 | Rel-8 | C4 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#42 completed | 29.228, 29.229 | 38 | 21 |  |  | Tue 13/11/07 | Sat 22/11/08
5545 | 380035 | AS/MRFC Stage 2 and 3 | MRFC_TS | 1 | Rel-8 | C1,IETF | Wed 14/11/07 | Fri 15/06/12 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | Triggered by Study UID_7048 (MRFC) | - | 38 | 21 |  |  | Wed 14/11/07 | Fri 30/07/10
5546 | 380135 | AS/MRFC Stage 2 | MRFC_TS | 2 | Rel-8 | C1 | Wed 14/11/07 | Fri 05/12/08 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 23.218 | 38 | 21 |  |  | Wed 14/11/07 | Tue 10/01/12
5547 | 380235 | AS/MRFC Stage 3 | MRFC_TS | 2 | Rel-8 | C1 | Wed 14/11/07 | Fri 05/12/08 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 24.229, 24.147, 24.247 | 38 | 21 |  |  | Wed 14/11/07 | Tue 10/01/12
5548 | 521027 | (IETF) AS/MRFC Stage 2 and 3 (RFC 6505) | MRFC_TS | 2 | Rel-8 | C1-IETF | Wed 14/11/07 | Fri 15/06/12 | 100% | CP-070784 | - | Keith Drage | - | CP#56 completed | RFC 6505 (was draft-ietf-mediactrl-mixer-control-package) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
5549 | 400012 | IMS Restoration Procedures | IMS_RP | 1 | Rel-8 | C4,C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 | - | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
5550 | 400026 | IMS Restoration Procedures (CT4) | IMS_RP | 2 | Rel-8 | C4 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 23.380, 29.228, 29.229, 29.230, 23.008 | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
5551 | 400027 | IMS Restoration Procedures (CT1) | IMS_RP | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 24.229 | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
5552 | 410003 | IMS Application Server Service Data Descriptions for AS interoperability | IMS_ASIO | 1 | Rel-8 | C4 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080451 | - | Alcatel-Lucent | nhberry@alcatel-lucent.com | CP#43 completed. Triggered by UID_360030 (FS_IMS_ASIO) | 29.328, 29.329, 29.364 | 41 | 21 |  |  | Wed 05/09/07 | Fri 20/02/09
5553 | 340030 | I-WLAN Network Selection Principle (NSP) | IWLANNSP | 1 | Rel-8 | S1,C1,C6 | Thu 14/06/07 | Fri 06/03/09 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | CP#43 completed | - | 34 |  |  |  | Fri 04/11/05 | Wed 25/02/09
5554 | 390024 | Stage 1 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | S1 | Thu 14/06/07 | Thu 14/06/07 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | SP#36 completed | 22.234 | 39 | 21 |  |  | Fri 04/11/05 | Tue 25/03/08
5555 | 390025 | CT1 part of Stage 3 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | C1 | Fri 07/03/08 | Fri 06/03/09 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#43 completed | 24.234 | 39 | 21 |  |  | Fri 07/03/08 | Wed 25/03/09
5556 | 390125 | CT6 part of Stage 3 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | C6 | Fri 07/03/08 | Thu 11/12/08 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#42 completed | 31.102, 31.111 | 39 | 21 |  |  | Fri 07/03/08 | Wed 25/02/09
5557 | 370049 | Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 1 | Rel-8 | S2,C1 | Fri 14/09/07 | Fri 06/03/09 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | CP#43 completed | - | 37 |  |  |  | Fri 04/11/05 | Tue 27/05/08
5558 | 380045 | Stage 2 for Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 2 | Rel-8 | S2 | Fri 14/09/07 | Thu 05/06/08 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | SP#40 completed | new 23.327 | 38 | 21 |  |  | Wed 21/11/07 | Fri 30/07/10
5559 | 400013 | CT1 aspects of Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080320 | - | Orange | reina.nader@orange-ftgroup.com | CP#43 completed | 24.303, new 24.327 | 40 | 21 |  |  | Wed 21/11/07 | Fri 30/07/10
5560 | 460006 | Conformance Test Aspects – Mobility between 3GPP WLAN Interworking and 3GPP Systems | IWLAN_Mob_UEConTest | 1 | Rel-8 | R5 | Fri 04/12/09 | Fri 17/09/10 | 100% | RP-091349 | RP-100740 | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | RP#49 completed. Testing for Rel-8 UID_400013 CT1 aspects of mobility between 3GPP WLAN Interworking and 3GPP Systems (24.327) | 34.108, 34.123-1, 34.123-2, 34.123-3 | 46 | 24 |  |  | Mon 30/11/09 | Thu 09/09/10
5561 | 7042 | Enhancements for Voice Group Call Service (VGCS) Applications (EVA) | EVA | 1 | Rel-8 | S1,C1,C4,G2 | Wed 15/03/06 | Fri 18/09/09 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | CP#45 completed | - |  |  |  |  | Tue 21/03/06 | Fri 30/07/10
5562 | 320021 | SA1 aspects of EVA | EVA | 2 | Rel-8 | S1 | Wed 15/03/06 | Wed 06/12/06 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#38 completed | 42.068 |  |  |  |  | Tue 21/03/06 | Fri 16/05/08
5563 | 370019 | VGCS/VBS and GPRS Interactions | EVA | 2 | Rel-8 | S1 | Mon 03/09/07 | Fri 21/03/08 | 100% | SP-070653 | - | Huawei | Ling Liu | SP#39 completed | 42.068, 42.069 | 37 |  |  |  | Tue 02/10/07 | Fri 16/05/08
5564 | 320019 | CT1 aspects of EVA | EVA | 2 | Rel-8 | C1 | Fri 02/06/06 | Fri 18/09/09 | 100% | CP-060260 | - | Nortel | milanpa@nortel.com | CP#45 completed | 43.068, 44.068 |  |  |  |  | Wed 21/06/06 | Wed 09/09/09
5565 | 320020 | CT4 aspects of EVA | EVA | 2 | Rel-8 | C4 | Fri 02/06/06 | Fri 30/11/07 | 100% | CP-060260 | - | Nortel | - | CP#38 completed | 29.002 |  |  |  |  | Wed 21/06/06 | Fri 16/05/08
5566 | 52148 | GERAN2 aspects of EVA | EVA | 2 | Rel-8 | G2 | Fri 30/06/06 | Fri 22/02/08 | 100% | GP-071855 | - | Nortel | frank.billenkamp@nortel.com | GP#37 completed | 44.018, 48.008 |  |  |  |  | Wed 05/07/06 | Fri 16/05/08
5567 | 31081 | Personal Network Management | PNM | 1 | Rel-8 | S1,C1,S3 | Mon 11/07/05 | Fri 06/03/09 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed | - |  |  |  |  | Thu 21/04/05 | Tue 24/03/09
5568 | 7012 | Stage 1 for PNM | PNM | 2 | Rel-8 | S1 | Mon 11/07/05 | Mon 31/07/06 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | SP#31 completed | 22.259 |  |  |  |  | Thu 16/02/06 | Wed 04/06/08
5569 | 350050 | Stage 2 for PNM | PNM | 2 | Rel-8 | C1 | Mon 26/03/07 | Fri 05/12/08 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 completed | 23.259 |  |  |  |  | Fri 04/05/07 | Fri 21/11/08
5570 | 350041 | Stage 3 for PNM | PNM | 2 | Rel-8 | C1,C4 | Mon 26/03/07 | Fri 06/03/09 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | - |  |  |  |  | Thu 16/02/06 | Mon 19/11/07
5571 | 350001 | CT1 aspects of Stage 3 PNM | PNM | 3 | Rel-8 | C1 | Mon 26/03/07 | Fri 06/03/09 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | 24.259, 24.229 |  |  |  |  | Thu 29/03/07 | Fri 20/02/09
5572 | 350002 | Deleted - CT4 aspects of Stage 3 PNM | PNM | 3 | Rel-8 | C4 | Mon 26/03/07 | Fri 05/12/08 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 no impact on CT4 specs | - |  |  | CP-42 |  | Thu 29/03/07 | Fri 30/07/10
5573 | 340010 | Key establishment between a UICC hosting device and a remote device | PNM | 2 | Rel-8 | S3 | Wed 06/12/06 | Tue 30/10/07 | 100% | SP-060839 | - | Ericsson | Vesa.Lehtovirta@ericsson.com | SP#37 completed | 33.259 |  |  |  |  | Thu 16/02/06 | Thu 26/03/09
5574 | 350049 | Deleted - Actual Requirements of PNM | PNM | 2 | Rel-8 | C1 | Mon 26/03/07 | Mon 26/03/07 | 100% | - | - | Ericsson | - | SP#37 stopped | - |  |  | SP-37 |  | Fri 04/05/07 | Tue 24/03/09
5575 | 330005 | eCall Data Transfer | EData | 1 | Rel-8 | S1,C1 | Thu 28/09/06 | Fri 06/03/09 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2) | - |  |  |  |  | Fri 06/10/06 | Mon 02/08/10
5576 | 370081 | eData Requirements | EData | 2 | Rel-8 | S1 | Thu 28/09/06 | Wed 12/03/08 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed | 22.101, 22.105 | 37 |  |  |  | Fri 06/10/06 | Mon 02/08/10
5577 | 400014 | Transfer of data during an emergency call | EData | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080316 | - | T-Mobile | Dieter Jacobsohn | CP#43 completed | 24.008 | 40 | 21 |  |  | Fri 06/10/06 | Mon 02/08/10
5578 | 34042 | eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution | eCall_Phase2 | 1 | Rel-8 | S4 | Thu 06/12/07 | Thu 24/09/09 | 100% | SP-070756 | - | Airbiquity | lhong@airbiquity.com & rrobinson@airbiquity.com | SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData) | 26.267, 26.268, 26.269, 26.967, 26.969 |  |  |  |  | Sun 09/12/07 | Mon 02/08/10
5579 | 450001 | eCall Conformance Testing | eCall_MSTest | 1 | Rel-8 | G3new | Fri 04/09/09 | Fri 03/09/10 | 100% | GP-091098 | - | Ericsson, Qualcomm | Vikrant Jain (vikrantj@qualcomm.com) | GP#47 completed. GP#43 WID approved. Testing for Rel-8 eCall_Phase2 (UID_34042) and EData (UID_330005) | 51.010-1, 51.010-2 | 45 | 23 |  |  | Mon 07/09/09 | Sat 04/09/10
5580 | 450023 | Conformance Test Aspects – non-modem procedures of eCall sessions in UTRA | UMTS_eCall_UEConTest | 1 | Rel-8 | R5 | Fri 18/09/09 | Fri 04/06/10 | 100% | RP-090952 | RP-100489 | Ericsson, Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for Rel-8 eCall_Phase2 (UID_34042) and Edata (UID_330005) | 34.108, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
5581 | 380060 | IP Interconnection of Services | IPinterc | 1 | Rel-8 | S1,S2,S5,C3 | Wed 16/08/06 | Fri 06/03/09 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#43 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
5582 | 380061 | Stage 1 for IPinterc | IPinterc | 2 | Rel-8 | S1 | Thu 06/12/07 | Wed 12/03/08 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. | 22.101, 22.228 | 38 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
5583 | 7005 | System enhancements for interconnection interfaces between two IMSs | IMS_NNI | 2 | Rel-8 | S2,S5,C3 | Wed 16/08/06 | Fri 06/03/09 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | CP#43 completed | - |  |  |  |  | Thu 16/02/06 | Mon 02/08/10
5584 | 360024 | Stage 2 for IMS_NNI | IMS_NNI | 3 | Rel-8 | S2 | Fri 22/06/07 | Thu 06/12/07 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | SP#38 completed | 23.002, 23.228 |  |  |  |  | Fri 22/06/07 | Mon 02/08/10
5585 | 360011 | IMS inter-operator service interconnection interface | FBI2-IOPSI | 3 | Rel-8 | C3 | Fri 01/06/07 | Fri 06/03/09 | 100% | CP-080578 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#43 completed | 29.865, 29.165 |  |  |  |  | Wed 20/06/07 | Mon 02/08/10
5586 | 330011 | Charging harmonization for NGN between 3GPP and ATIS-TMOC | FBI2-TISP2-CH | 3 | Rel-8 | S5 | Thu 28/09/06 | Thu 07/12/06 | 100% | SP-060545 | - | Amdocs | yishai.brown@amdocs.com | SP#34 completed | 32.297 |  |  |  |  | Mon 09/10/06 | Mon 03/03/08
5587 | 7007 | Deleted - Protocol impact of FBI for TISPAN R2 | FBI2-TISP2-c1 | 3 | Rel-8 | C1 | Wed 16/08/06 | Thu 15/03/07 | 100% | - | - | Ericsson | - | SP#38 stopped | - |  |  | SP-38 |  | Thu 16/02/06 | Tue 24/03/09
5588 | 7006 | Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8 | FBI2-TISP2-s2 | 3 | Rel-8 | S2 | Fri 30/11/07 | Fri 30/11/07 | 100% | - | - | Nokia Siemens Networks | - | SP#36 stopped | - |  |  | SP-36 |  | Thu 16/02/06 | Tue 24/03/09
5589 | 360025 | Support of (G)MSC-S – (G)MSC-S Nc Interface based on the SIP-I protocol | SIP_Nc | 1 | Rel-8 | C4,C3 | Fri 14/09/07 | Fri 06/03/09 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#43 completed. Stage 1 in Feature UID_380060 (IPinterc). CP#40 updated WID CP-070517=>CP-080282 | - |  |  |  |  | Wed 05/09/07 | Wed 28/05/08
5590 | 410002 | Stage 1 for SIP_Nc (covered by Feature IPinterc) | SIP_Nc | 2 | Rel-8 | S1 | Thu 06/12/07 | Wed 12/03/08 | 100% | SP-070871 | - | Telefónica O2 | chris.friel@O2.com | 22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc) | 22.101, 22.228 | 41 | 21 |  |  | Thu 13/12/07 | Thu 20/03/08
5591 | 360026 | SIP-I based circuit-switched core network; Stage 2 | SIP_Nc-St2 | 2 | Rel-8 | C4 | Fri 14/09/07 | Fri 05/12/08 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 23.231, 23.153, 23.205 |  |  |  |  | Wed 05/09/07 | Sat 22/11/08
5592 | 360027 | Application of SIP-I Protocols to Circuit Switched (CS) core network architecture; Stage 3 | SIP_Nc-St3C4 | 2 | Rel-8 | C4 | Fri 14/09/07 | Fri 05/12/08 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 29.231, 29.232, 29.332 |  |  |  |  | Wed 05/09/07 | Sat 22/11/08
5593 | 360028 | Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks | SIP_Nc-St3C3 | 2 | Rel-8 | C3 | Fri 14/09/07 | Fri 06/03/09 | 100% | CP-080282 | - | Nokia Siemens Networks | Thomas.Belling@nsn.com | CP#43 completed. CP#42 target 12/08=>03/09 | 29.235, 23.172, 23.202, 29.007, 29.163, 29.414 |  |  |  |  | Wed 05/09/07 | Thu 19/02/09
5594 | 370051 | Earthquake and Tsunami Warning System | ETWS | 1 | Rel-8 | S1,S2,C1,C4,G2 | Mon 10/09/07 | Fri 15/05/09 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#43 Larger scope Feature UID_380057 (PWS) moved to Rel-9 | - | 37 |  |  |  | Mon 19/11/07 | Mon 02/08/10
5595 | 370052 | Stage 1 for ETWS | ETWS | 2 | Rel-8 | S1 | Mon 10/09/07 | Wed 12/03/08 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#39 completed | 22.168 | 37 |  |  |  | Mon 19/11/07 | Thu 20/03/08
5596 | 380056 | SA2 aspects of ETWS | ETWS | 2 | Rel-8 | S2 | Mon 14/01/08 | Thu 18/09/08 | 100% | SP-070815 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#41 completed | 23.828, 23.401 | 38 | 21 |  |  | Thu 13/12/07 | Sun 14/09/08
5597 | 400015 | CT1 aspects of ETWS | ETWS | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 23.041 | 40 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
5598 | 410021 | CT4 aspects of ETWS | ETWS | 2 | Rel-8 | C4 | Fri 26/09/08 | Fri 05/12/08 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 29.168 | 40 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
5599 | 430045 | ETWS primary notification message definition in GERAN | ETWS | 2 | Rel-8 | G2 | Thu 12/03/09 | Fri 15/05/09 | 100% | SP-090154 | - | Ericsson | claes-goran.persson@ericsson.com | SP#44 completed with CT1 help (GERAN2 LS_in SP-090154) | 44.018, 44.060 | 43 | 22 |  |  | Tue 10/03/09 | Sat 30/05/09
5600 | 440011 | Conformance Test Aspects – UMTS Earthquake and Tsunami Warning System (ETWS) FDD | ETWS_UMTS_UEConTestFDD | 1 | Rel-8 | R5 | Fri 29/05/09 | Fri 12/03/10 | 100% | RP-090467 | RP-100068 | NTT DoCoMo | Makoto Ito (itohm@nttdocomo.co.jp) | RP#47 completed. Testing for Rel-8 ETWS UID_370051 | 34.108, 34.123-1, 34.123-2 | 44 | 23 |  |  | Thu 28/05/09 | Mon 08/03/10
5601 | 380059 | In Case of Emergency numbers storage and easy access on UICC | ICE | 1 | Rel-8 | S1,C6 | Tue 13/03/07 | Fri 06/03/09 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not included in Rel-8) | - | 38 | 21 |  |  | Thu 13/12/07 | Wed 04/03/09
5602 | 380159 | Stage 1 for ICE | ICE | 2 | Rel-8 | S1 | Tue 13/03/07 | Wed 12/03/08 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | SP#39 Stage 1 completed | 22.030, 22.101 | 38 | 21 |  |  | Thu 13/12/07 | Tue 17/06/08
5603 | 380259 | CT6 aspects of ICE | ICE | 2 | Rel-8 | C6 | Tue 13/03/07 | Fri 06/03/09 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not in Rel-8 / not explicitly in SA1 WID either) | 31.102 | 38 | 21 |  |  | Thu 13/12/07 | Mon 06/09/10
5604 | 330006 | Local Charging Zone Requirements | LCZR | 1 | Rel-8 | S1 | Thu 28/09/06 | Wed 12/03/08 | 100% | SP-060482 | - | China Mobile | liuhongyfw@chinamobile.com | SP#39 Stage 1 completed | 22.115 |  |  |  |  | Fri 06/10/06 | Tue 25/03/08
5605 | 340029 | Customized Alerting Tone (CAT) service | CAT | 1 | Rel-8 | S1,C1,C3,C4 | Wed 06/12/06 | Fri 18/09/09 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | CP#45 completed | - | 34 |  |  |  | Fri 04/11/05 | Mon 02/08/10
5606 | 370028 | Stage 1 for CAT | CAT | 2 | Rel-8 | S1 | Wed 06/12/06 | Thu 20/09/07 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | - | 22.182 | 37 |  |  |  | Tue 02/10/07 | Wed 10/09/08
5607 | 370029 | TISPAN requirements for customized multimedia information services | TISCMI | 2 | Rel-8 | S1 | Mon 03/09/07 | Mon 10/12/07 | 100% | SP-070880 | - | China Mobile | fenglingjuan@chinamobile.com | SP#38 completed | 22.182 | 37 |  |  |  | Tue 02/10/07 | Thu 24/07/08
5608 | 390014 | IMS CAT Supplementary Service | CAT-SS | 2 | Rel-8 | C1,C3 | Wed 12/03/08 | Fri 18/09/09 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | - | - | 39 | 21 |  |  | Mon 03/03/08 | Fri 21/11/08
5609 | 390114 | IMS CAT SS | CAT-SS | 3 | Rel-8 | C1 | Mon 21/04/08 | Thu 04/12/08 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#42 completed | 24.182 | 39 | 21 |  |  | Mon 03/03/08 | Fri 21/11/08
5610 | 390071 | CAT solution for voice and video call in CS domain | CAT-SS | 3 | Rel-8 | C3 | Wed 12/03/08 | Fri 18/09/09 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#45 completed. Triggered by Study UID_360031 (TR 29.882) | 29.163 | 39 | 21 |  |  | Mon 03/03/08 | Mon 02/08/10
5611 | 410010 | CAT Service in 3GPP CS domain | CAT-3G_CS | 2 | Rel-8 | C4,C1 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 23.205, 23.231, 29.002 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
5612 | 410110 | CT4 part of CAT Service in 3GPP CS domain | CAT-3G_CS | 3 | Rel-8 | C4 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#43 completed. Triggered by Study UID_360031 (TR 29.882) | 23.205, 23.231, 29.002 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
5613 | 410015 | CT1 part of CAT Service in 3GPP CS domain | CAT-3G_CS | 3 | Rel-8 | C1 | Fri 12/09/08 | Fri 05/12/08 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#42 completed. Triggered by Study UID_360031 (TR 29.882) | 24.008, 23.014 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
5614 | 340031 | Service-Level Interworking for Messaging Services | MESSIW | 1 | Rel-8 | S1,S2,C3,C1 | Mon 26/03/07 | Fri 06/03/09 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com; duanxiaoqin@huawei.com | CP#43 completed | - | 34 |  |  |  | Fri 04/11/05 | Mon 02/08/10
5615 | 350047 | Stage 1 for MESSIW | MESSIW | 2 | Rel-8 | S1 | Mon 26/03/07 | Mon 26/03/07 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com | SP#35 completed | 22.105, 22.340 |  |  |  |  | Fri 04/11/05 | Sat 22/03/08
5616 | 350048 | Stage 2 for MESSIW | MESSIW | 2 | Rel-8 | S2 | Thu 26/04/07 | Fri 07/03/08 | 100% | SP-070816 | - | Huawei | patrice.hede@huawei.com | SP#39 completed | 23.811, 23.204 |  |  |  |  | Fri 04/11/05 | Sat 22/03/08
5617 | 400016 | CT3 part of Stage 3 for MESSIW | MESSIW | 2 | Rel-8 | C3 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#43 completed | 29.311 | 40 | 21 |  |  | Wed 19/07/06 | Thu 19/02/09
5618 | 400017 | CT1 part of Stage 3 for MESSIW | MESSIW | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#42 completed | 24.229 | 40 | 21 |  |  | Wed 19/07/06 | Mon 02/08/10
5619 | 340044 | Multimedia Priority Service | PRIOR_EMR | 1 | Rel-8 | S1,C1,C3,C4 | Thu 08/06/06 | Fri 18/09/09 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | CP#45 completed | - | 34 |  |  |  | Fri 28/03/03 | Wed 09/09/09
5620 | 320023 | Service Requirements for PRIOR | PRIOR_EMR | 2 | Rel-8 | S1 | Thu 08/06/06 | Thu 06/12/07 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | SP#38 completed | New 22.153 | 32 |  |  |  | Fri 28/03/03 | Tue 03/06/08
5621 | 340012 | CT1 part of Stage 3 for PRIOR | PRIOR_EMR | 2 | Rel-8 | C1 | Fri 01/12/06 | Fri 18/09/09 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#45 completed | 24.229 | 34 |  |  |  | Mon 18/12/06 | Wed 09/09/09
5622 | 370021 | CT4 part of Stage 3 for PRIOR | PRIOR_EMR | 2 | Rel-8 | C4 | Fri 21/09/07 | Fri 06/03/09 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.008, 29.228, 29.229 | 37 |  |  |  | Tue 25/09/07 | Wed 11/03/09
5623 | 370020 | Deleted - Stage 3 for PRIOR | PRIOR-EMR | 2 | Rel-8 | C3 | Fri 21/09/07 | Fri 29/05/09 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2) | 29.212, 29.213, 29.214, 29.163 | 37 |  | CP-44 | PCG-23 | Tue 25/09/07 | Fri 29/05/09
5624 | 360010 | Open Service Access (OSA) Rel-8 | OSA8 | 1 | Rel-8 | S1,C5 | Thu 23/08/07 | Fri 30/05/08 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | - |  |  |  |  | Tue 22/03/05 | Mon 30/08/10
5625 | 360004 | OSA Stage 1 - Service Requirements | OSA8 | 2 | Rel-8 | S1 | Thu 23/08/07 | Wed 12/03/08 | 100% | - | - | Orange, AePONA | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | 22.127 |  |  |  |  | Tue 22/03/05 | Mon 30/08/10
5626 | 370034 | OSA Stage 1 - NGN Service Requirement | OSA8-IMSReq | 2 | Rel-8 | S1 | Mon 03/09/07 | Fri 14/03/08 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA | 22.127 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
5627 | 360005 | Rel-8 OSA Stage 2/3 enhancements | OSA8-IMS | 2 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | SP#40 maintenance & new OSA work moved to OMA | 23.198, 29.198, 29.199 |  |  |  |  | Wed 14/12/05 | Mon 02/08/10
5628 | 370012 | Deleted - Ensure Parlay-X composable with identity management frameworks, in particular Liberty Alliance | - | 3 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy | 37 | 21 | CP-40 | PCG-21 | Thu 13/09/07 | Tue 24/03/09
5629 | 370013 | Parlay-X Content Management web service (store/manage meta-data) | OSA8-IMS | 3 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-21 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
5630 | 370014 | Parlay-X Policy web service | OSA8-IMS | 3 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-22 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
5631 | 370015 | Parlay-X Terminal status web service | OSA8-IMS | 3 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-08 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
5632 | 370016 | Deleted - Identify communication format used by a particular application | - | 3 | Rel-8 | C5 | Thu 25/10/07 | Fri 30/05/08 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy | 37 | 21 | CP-40 | PCG-21 | Thu 13/09/07 | Tue 24/03/09
5633 | 380047 | Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5634 | 380048 | Deleted - Privacy on Subscriber Identity (Liberty Alliance, OASIS) (22.127 CR 0085 S1-071835) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5635 | 380049 | Deleted - Topology Hiding (22.127 CR 0086 S1-071838) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5636 | 380050 | Deleted - Subscriber event notification (22.127 CR 0087 S1-071836) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5637 | 380051 | Deleted - Event notification (22.127 CR 0088 S1-071762) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5638 | 380052 | Deleted - Access policy (22.127 CR 0089 S1-071763) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5639 | 380053 | Deleted - API usage accounting (22.127 CR 0090 S1-071792) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5640 | 380054 | Presence alignment with OMA and IETF (22.127 CR 0092 S1-071764) | OSA8-IMS | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-14/13 | 38 | 21 |  |  | Wed 05/12/07 | Mon 19/01/09
5641 | 380055 | Deleted - Service identification (22.127 CR 0095 S1-071837) | - | 3 | Rel-8 | C5 | Wed 05/12/07 | Fri 30/05/08 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | existing 29.199-xy | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
5642 | 390067 | Framework Enterprise Operator (Service Subscription function) | OSA8-IMS | 3 | Rel-8 | C5 | Thu 10/01/08 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-03 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
5643 | 390068 | Mobility Emergency Location | OSA8-IMS | 3 | Rel-8 | C5 | Thu 10/01/08 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-06 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
5644 | 390069 | Connectivity Manager SCF | OSA8-IMS | 3 | Rel-8 | C5 | Thu 10/01/08 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-10 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
5645 | 390070 | PAM Presence Agent | OSA8-IMS | 3 | Rel-8 | C5 | Thu 10/01/08 | Fri 30/05/08 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-14 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
5646 | 360032 | Paging Permission with Access Control (PPACR) | PPACR | 1 | Rel-8 | S1,C1 | Tue 12/06/07 | Fri 05/12/08 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | CP#42 completed. Triggered by Study UID_330016 (PPAC). | - |  |  |  |  | Tue 16/10/07 | Wed 10/12/08
5647 | 370084 | Stage 1 for PPACR | PPACR-S1 | 2 | Rel-8 | S1 | Tue 12/06/07 | Fri 14/09/07 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | SP#37 completed | 22.011 | 37 |  |  |  | Tue 16/10/07 | Fri 16/05/08
5648 | 380017 | Stage 3 for PPACR (CT1) | PPACR-CT1 | 2 | Rel-8 | C1 | Wed 14/11/07 | Fri 05/12/08 | 100% | CP-070783 | - | NTT DoCoMo | - | CP#42 completed | 24.008, 23.122, 24.301 | 38 | 21 |  |  | Wed 14/11/07 | Fri 21/11/08
5649 | 490017 | Conformance Test Aspects – Paging Permission with Access Control (PPAC) | PPAC_UEConTest | 1 | Rel-8 | R5 | Fri 17/09/10 | Fri 10/12/10 | 100% | RP-100806 | RP-101074 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#50 completed | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Fri 10/09/10 | Wed 08/12/10
5650 | 380063 | Charging for multi-phases services | CHRGMPH | 1 | Rel-8 | S1 | Thu 06/12/07 | Wed 12/03/08 | 99% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 Stage 1 completed | 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Wed 10/12/08
5651 | 380070 | Stage 1 for CHRGMPH | CHRGMPH-s1 | 2 | Rel-8 | S1 | Thu 06/12/07 | Wed 12/03/08 | 100% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 completed | 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Thu 20/03/08
5652 | 380065 | Home NodeB / eNodeB | HomeNB | 1 | Rel-8 | S1,C1,C4 | Thu 06/12/07 | Fri 06/03/09 | 100% | SP-070952 | - | Vodafone | John Watson | CP#43 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Wed 11/03/09
5653 | 380066 | Stage 1 for Home NodeB / eNodeB | HomeNB-S1 | 2 | Rel-8 | S1 | Thu 06/12/07 | Wed 12/03/08 | 100% | SP-070952 | - | Vodafone | John Watson | SP#39 completed | 22.011, 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Thu 24/07/08
5654 | 420019 | Support of Closed Subscriber Group (CSG) | - | 2 | Rel-8 | C4 | Fri 05/12/08 | Fri 06/03/09 | 100% | - | - | CT#42 | Hannu Hietalahti | CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG | 29.002, 29.272, 23.008, 23.003 | 42 | 22 |  |  | Thu 04/12/08 | Mon 23/02/09
5655 | 410012 | CSG and Idle Mode Mobility for LTE Home eNodeB | HomeNB-LTE | 2 | Rel-8 | C1 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080498 | - | Huawei | zhang.peng@huawei.com | CP#43 completed | 23.122, new (24.285, 24.301, 24.801) | 41 | 21 |  |  | Wed 03/09/08 | Wed 11/03/09
5656 | 410013 | CSG and Idle Mode Mobility for 3G Home NodeB | HomeNB-3G | 2 | Rel-8 | C1 | Fri 12/09/08 | Fri 06/03/09 | 100% | CP-080792 | - | Qualcomm | Osok Song | CP#43 completed | 23.122, 24.008, new 24.285 | 41 | 21 |  |  | Wed 03/09/08 | Wed 11/03/09
5657 | 390033 | UTRA HNB | HNB | 1 | Rel-8 | RP,S5 | Fri 07/03/08 | Thu 04/06/09 | 100% | - | - | - | - | SP#44 completed | - | 39 | 21 |  |  | Tue 04/01/05 | Tue 03/06/08
5658 | 400053 | Support of UTRA HNB | HNB-supp | 2 | Rel-8 | R2 | Fri 30/05/08 | Fri 06/03/09 | 100% | RP-080752 | RP-090040 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#43 completed | 25.304, 25.306, 25.331, new 25.367 | 40 | 21 |  |  | Tue 03/06/08 | Fri 27/02/09
5659 | 400054 | UTRAN Architecture for 3G HNB | HNB-arch | 2 | Rel-8 | R3 | Fri 30/05/08 | Fri 05/12/08 | 100% | RP-080487 | RP-090042 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#42 completed | 25.401, 25.410, 25.412, 25.413, 25.414, 25.415, new (25.467, 25.468, 25.469) | 40 | 21 |  |  | Tue 03/06/08 | Fri 06/03/09
5660 | 390034 | FDD Home NodeB RF requirements | HNB-RF | 2 | Rel-8 | R4 | Fri 07/03/08 | Fri 06/03/09 | 100% | RP-080971 | RP-090041 | Motorola | Ying Cai (yingcai@motorola.com) | RP#43 completed | 25.104, 25.141, new 25.967 | 39 | 21 |  |  | Mon 27/09/04 | Fri 27/02/09
5661 | 420037 | 3G Home NodeB OAM&P Type 1 Management Interface | HNB-3G_OAM | 2 | Rel-8 | S5 | Thu 11/12/08 | Thu 04/06/09 | 100% | SP-080708 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Complements work in BroadBand Forum | new (32.581, 32.582, 32.583, 32.584) | 42 | 22 |  |  | Wed 03/12/08 | Mon 18/05/09
5662 | 430022 | UTRA HNB – UE Conformance Testing | HNB-UEConTest | 1 | Rel-8 | R5 | Fri 06/03/09 | Fri 04/06/10 | 100% | - | - | - | - | RP#48 FDD completed. Testing for Feature UID_390033 UTRA HNB | - | 43 | 22 |  |  | Fri 27/02/09 | Tue 01/06/10
5663 | 430023 | Conformance Test Aspects – UTRA HNB (FDD) | HNB-UEConTestFDD | 2 | Rel-8 | R5 | Fri 06/03/09 | Fri 04/06/10 | 100% | RP-090023 | RP-100482 | Huawei | Trica Li (trica_li@huawei.com) | RP#48 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 | 43 | 22 |  |  | Fri 27/02/09 | Tue 01/06/10
5664 | 350015 | Lawful Interception in the 3GPP Rel-8 | LI8 | 1 | Rel-8 | S3 | Mon 12/03/07 | Thu 12/03/09 | 100% | SP-070238 | - | BMWI, Verizon | berthold.wilhelm@bnetza.de, ron_ryan@verizon.net | SP#43 completed | 33.106, 33.107, 33.108 |  |  |  |  | Thu 29/03/07 | Wed 11/03/09
5665 | 390046 | Generic Bootstrapping Architecture Push Function | GBAPush | 1 | Rel-8 | S3,C1,C4 | Wed 12/03/08 | Fri 06/03/09 | 100% | SP-080133 | - | Ericsson | Rolf Blom | CP#43 completed | - | 39 | 21 |  |  | Sat 22/03/08 | Fri 20/02/09
5666 | 390146 | SA3 part of GBAPush (33.223) | GBAPush | 2 | Rel-8 | S3 | Wed 12/03/08 | Fri 05/12/08 | 100% | SP-080133 | - | Ericsson | Rolf Blom | SP#42 completed 33.223 as Rel-8. TS 33.224 moved to Rel-9 under new UID_420039 | 33.223 | 39 | 21 |  |  | Sat 22/03/08 | Mon 09/03/09
5667 | 390246 | CT1 part of GBAPush | GBAPush | 2 | Rel-8 | C1 | Wed 12/03/08 | Fri 06/03/09 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 24.109 | 39 | 21 |  |  | Sat 22/03/08 | Wed 04/03/09
5668 | 390346 | CT4 part of GBAPush | GBAPush | 2 | Rel-8 | C4 | Wed 12/03/08 | Fri 06/03/09 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 29.109 | 39 | 21 |  |  | Sat 22/03/08 | Wed 04/03/09
5669 | 34045 | Requirements and Test methods for Wideband Terminals | RETEM_WB_T | 1 | Rel-8 | S4 | Wed 12/03/08 | Thu 11/12/08 | 100% | SP-080004 | - | FT, Ericsson | stephane.ragot@orange-ftgroup.com, wanqing.shi@sonyericsson.com | SP#42 completed. SP#39 WID approved. | 26.131, 26.132 |  |  |  |  | Tue 18/03/08 | Fri 21/11/08
5670 | 34043 | Extending PSS and MBMS User Services for optimized Mobile TV | PSS_MBMS_OMTV | 1 | Rel-8 | S4 | Thu 06/12/07 | Thu 11/12/08 | 100% | SP-070757 | - | Ericsson | thorsten.lohmar@ericsson.com | SP#42 completed. SP#38 WID approved. | 26.234, 26.346, 26.946 |  |  |  |  | Sun 09/12/07 | Fri 21/11/08
5671 | 400028 | Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI | MTSI_eMHI | 1 | Rel-8 | S4,C3,C4 | Thu 06/12/07 | Thu 12/03/09 | 100% | SP-080443 | - | Ericsson, Qualcomm | olle.franceschi@ericsson.com, nleung@qualcomm.com | TSG#43 completed | - | 40 | 21 |  |  | Sun 09/12/07 | Sat 21/02/09
5672 | 34041 | MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size | MTSI_eMHI-DRASIS | 2 | Rel-8 | S4 | Thu 06/12/07 | Thu 12/03/09 | 100% | SP-080246 | - | Qualcomm, Samsung | nleung@qualcomm.com & kyunghun.jung@samsung.com | SP#43 completed | 26.114 |  |  |  |  | Sun 09/12/07 | Mon 02/08/10
5673 | 400018 | CT3 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C3 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.163 | 40 | 21 |  |  | Sun 09/12/07 | Fri 20/02/09
5674 | 400020 | CT4 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C4 | Fri 30/05/08 | Fri 06/03/09 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.332 | 40 | 21 |  |  | Sun 09/12/07 | Fri 20/02/09
5675 | 400019 | Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C1 | Fri 30/05/08 | Fri 12/12/08 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774 | - | 40 | 21 | CP-42 |  | Sun 09/12/07 | Mon 02/08/10
5676 | 340063 | Rel-8 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM8 | 1 | Rel-8 | S5,C1,C4,IETF | Thu 07/06/07 | Fri 07/12/12 | 100% | - | - | - | - | OAM8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | 30.818 | 34 |  |  |  | Thu 08/03/07 | Mon 02/08/10
5677 | 340064 | Rel-8 Network Infrastructure Management | OAM8-NIM | 2 | Rel-8 | S5 | Thu 07/06/07 | Fri 04/12/09 | 100% | - | - | - | - | - | - | 34 |  |  |  | Fri 13/07/07 | Tue 24/03/09
5678 | 35051 | Telecom Management Methodology | OAM8-NIM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/03/09 | 100% | SP-070296 | - | Ericsson | thomas.tovinger@ericsson.com | SP#43 completed | 32.155, 32.153 |  |  |  |  | Fri 17/06/05 | Mon 23/02/09
5679 | 35053 | Advanced Alarming on Itf-N | OAM8-NIM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/06/08 | 100% | SP-070492 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#40 completed | 32.121, 32.122, 32.123 |  |  |  |  | Fri 17/06/05 | Wed 04/06/08
5680 | 35056 | CN CS Bearer Transport Network (BTN) relative NRM | OAM8-NIM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/06/08 | 100% | SP-070300 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed | 32.632, 32.633, 32.635 |  |  |  |  | Fri 17/06/05 | Mon 28/04/08
5681 | 390016 | Alignment with eTOM and M.3060 architectural concepts | OAM8-NIM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 11/12/08 | 100% | SP-080068 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#42 completed | 32.101/2, 32-series | 39 | 21 |  |  | Sat 15/09/07 | Tue 25/11/08
5682 | 400030 | IRP SOAP Solution Sets | OAM8-NIM | 3 | Rel-8 | S5 | Thu 05/06/08 | Thu 12/03/09 | 100% | SP-090148 | - | Ericsson | edwin.tse@ericsson.com | SP#43 completed | 32.111-7, 32.617, 32.417, 32.367, 32.347, 32.111-1, 32.111-2, 32.111-3, 32.111-5, 32.307, 32.317, 32.341, 32.342, 32.343, 32.345, 32.361, 32.362, 32.363, 32.365, 32.411, 32.412, 32.413, 32.415, 32.611, 32.612, 32.613, 32.615, 32.625 | 40 | 21 |  |  | Sat 15/09/07 | Tue 11/08/09
5683 | 450052 | Create missing specifications for IRP XML definitions | OAM8-NIM | 3 | Rel-8 | S5 | Thu 24/09/09 | Fri 04/12/09 | 100% | SP-090553 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x) | new (32.125, 32.355, 32.505, 32.535), 32.150, 32.153, 32.335 | 45 | 23 |  |  | Fri 11/09/09 | Tue 01/12/09
5684 | 370002 | Deleted - End point modelling for reference point | OAM8-NIM | 3 | Rel-8 | S5 | Mon 17/09/07 | Thu 11/12/08 | 100% | SP-070618 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#41 Work stopped. Contributions related to E-UTRAN/EPC to be submitted to UID_380036 E-UTRAN NRM IRP/ UID_380037 EPC NRM IRP | 32.152, 32.62/3/4x, 32.73x | 37 |  | SP-41 | PCG-21 | Sat 15/09/07 | Tue 24/03/09
5685 | 340065 | Rel-8 Performance Management | OAM8-PM | 2 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/03/09 | 100% | - | - | - | Li Jian (lijian@chinamobile.com) | - | - | 34 |  |  |  | Fri 13/07/07 | Thu 26/06/08
5686 | 35061 | IP bearer network Performance measurement definitions | OAM8-PM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 11/12/08 | 100% | SP-070301 | - | China Mobile | lilianyuan@chinamobile.com | SP#42 completed | 32.321, 32.322, 32.323, 32.325 |  |  |  |  | Fri 17/06/05 | Mon 02/08/10
5687 | 360001 | HSUPA performance measurements | OAM8-PM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 11/12/08 | 100% | SP-070835 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#42 completed | 32.405 |  |  |  |  | Mon 28/05/07 | Tue 25/11/08
5688 | 360002 | Key Performance Indicators (KPIs) for UMTS and GSM | OAM8-PM | 3 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/03/09 | 100% | SP-070299 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | 32.41 |  |  |  |  | Mon 28/05/07 | Mon 23/02/09
5689 | 340066 | Rel-8 Trace Management | OAM8-Trace | 2 | Rel-8 | C1,C4,IETF | Fri 07/03/08 | Fri 07/12/12 | 100% | - | - | - | - | - | - | 34 |  |  |  | Fri 22/06/07 | Wed 10/12/08
5690 | 11067 | CT1 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C1 | Fri 07/03/08 | Fri 05/12/08 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 24.323, 24.229 |  |  |  |  | Mon 17/03/08 | Mon 02/08/10
5691 | 521028 | (IETF) Service Level Tracing in IMS (draft-ietf-insipid-logme-marking) --> RFC 8497 | OAM8-Trace | 3 | Rel-8 | C1-IETF | Fri 07/03/08 | Fri 07/12/12 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#58 Removed from Rel-8, Rel-9 and Rel-10 (Not completed internet-draft); 26/6/19: 100%->100 | Rel-11 remains draft-dawes-dispatch-debug | 52 | 27 |  |  | Mon 20/06/11 | Wed 26/06/19
5692 | 531003 | Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event) | OAM8-Trace | 3 | Rel-8 | C1-IETF | Fri 07/03/08 | Fri 09/12/11 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100 | draft-dawes-sipping-debug-event | 53 | 27 |  |  | Fri 29/07/11 | Fri 09/04/21
5693 | 400022 | CT4 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C4 | Fri 07/03/08 | Fri 05/12/08 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 29.228, 29.229 | 40 | 21 |  |  | Mon 17/03/08 | Mon 02/08/10
5694 | 400021 | Deleted - CT3 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C3 | Fri 07/03/08 | Fri 05/12/08 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 stopped (No CT3-impact) | - | 40 | 21 | CP-42 | PCG-22 | Mon 17/03/08 | Mon 02/08/10
5695 | 870081 | (IETF) A Two-Way Active Measurement Protocol (TWAMP) (draft-ietf-ippm-twamp) --> RFC 5357 | OAM8 | 2 | Rel-8 | S5-IETF | Fri 07/03/08 | Mon 06/09/10 | 100% | - | - | - | - | - | - | 34 |  |  |  | Fri 13/07/07 | Tue 24/03/09
5696 | 350016 | Rel-8 Charging Management small Enhancements | CH8 | 1 | Rel-8 | S5 | Thu 16/03/06 | Thu 11/12/08 | 100% | - | - | - | - | CH8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | 30.818 |  |  |  |  | Mon 22/05/06 | Tue 24/03/09
5697 | 350038 | Online charging correlation | CH8 | 2 | Rel-8 | S5 | Thu 16/03/06 | Fri 14/12/07 | 100% | SP-070077 | - | Orange | Chahine, Rony | SP#38 completed | 32.296 |  |  |  |  | Mon 17/03/08 | Mon 17/03/08
5698 | 360003 | SMS online charging | CH8 | 2 | Rel-8 | S5 | Thu 07/06/07 | Fri 14/12/07 | 100% | SP-070293 | - | Vodafone | Gavin.Wong@vodafone.com | SP#38 completed | 32.240, 32.299, new 32.274 |  |  |  |  | Tue 29/05/07 | Mon 17/03/08
5699 | 410045 | Introduce Online Charging from SMS-SC into the SMS Charging Specifications | CH8 | 2 | Rel-8 | S5 | Thu 18/09/08 | Thu 11/12/08 | 100% | SP-080463 | - | Acision | erik.gebler@acision.com | SP#42 completed. Linked to SA2 UID 32081 (Support of SMS over IP networks) and CT4 UID 340016 (Routeing of MT-SMS via the HPLMN). | 32.274, 32.299 | 41 | 21 |  |  | Mon 15/09/08 | Tue 25/11/08
5700 | 380046 | Deleted - WLAN Offline Charging | CH8 | 2 | Rel-8 | S5 | Mon 07/01/08 | Thu 11/12/08 | 100% | SP-070750 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#42 stopped | 32.252, 32.298, 32.299 | 38 | 21 | SP-42 | PCG-22 | Fri 17/06/05 | Tue 24/03/09
5701 | 380024 | Conferencing enhancements for Mp interface | eMp | 1 | Rel-8 | C4 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | - |  | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
5702 | 380025 | Stage 2 for eMp | eMp | 2 | Rel-8 | C4 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 23.333 | 38 | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
5703 | 380026 | Stage 3 for eMp | eMp | 2 | Rel-8 | C4 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 29.333 | 38 | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
5704 | 320014 | Contact Manager for 3GPP UICC applications | eUPHBOOK | 1 | Rel-8 | C6 | Thu 22/06/06 | Fri 05/12/08 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed. CP#40: WID updated CP-070622=>CP-080382. aka Enhanced USIM phonebook | - |  |  |  |  | Tue 24/01/06 | Tue 24/03/09
5705 | 320015 | Requirements for Contact Manager | eUPHBOOK-St1 | 2 | Rel-8 | C6 | Thu 22/06/06 | Fri 21/12/07 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#38 completed | 21.111 |  |  |  |  | Tue 24/01/06 | Thu 29/05/08
5706 | 350046 | External interface for eUPHBOOK | eUPHBOOK-Ext_Spec | 2 | Rel-8 | C6 | Mon 07/05/07 | Fri 07/03/08 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#39 completed | new 31.220 |  |  |  |  | Tue 24/01/06 | Thu 29/05/08
5707 | 370004 | Internal interface for eUPHBOOK | eUPHBOOK-Int_Spec | 2 | Rel-8 | C6 | Mon 07/05/07 | Fri 05/12/08 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed | new 31.221 | 37 |  |  |  | Tue 24/01/06 | Tue 25/11/08
5708 | 320016 | Deleted - Implementation of eUPHBOOK | eUPHBOOK-St23 | 2 | Rel-8 | C6 | Thu 21/06/07 | Thu 21/06/07 | 100% | CP-060355 | - | Giesecke & Devrient | Claus Dietze | SP#33 stopped | 31.102 |  |  | SP-33 |  | Tue 24/01/06 | Tue 24/03/09
5709 | 20068 | Rel-8 LTE – 3G Long Term Evolution - Evolved Packet System RAN part | LTE | 1 | Rel-8 | RP,S5 | Mon 25/09/06 | Thu 12/03/09 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#43 completed. Role model for SAE/LTE system wide project management by SA2 in SP-060166 | LTE 36.300, 36.938 |  |  |  |  | Wed 21/06/06 | Fri 18/12/09
5710 | 330018 | LTE – Physical Layer | LTE-Phys | 2 | Rel-8 | R1 | Mon 25/09/06 | Fri 07/03/08 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Sadayuki Abeta | RP#39 completed | 36.201, 36.211, 36.212, 36.213, 36.214, 25.215, 25.225 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
5711 | 330019 | LTE – Radio Interface Layer 2 and 3 Protocol Aspect | LTE-L23 | 2 | Rel-8 | R2 | Mon 25/09/06 | Fri 05/12/08 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | benoist.sebire@nokia.com | RP#42 completed | 36.302, 36.304, 36.306, 36.314, 36.321, 36.322, 36.323, 36.331, 25.302, 25.304, 25.331 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
5712 | 330020 | LTE – eUTRAN Interfaces | LTE-interfaces | 2 | Rel-8 | R3 | Mon 25/09/06 | Fri 05/12/08 | 100% | RP-080747 | RP-080741 | Ericsson | Martin Israelsson | RP#42 completed | 36.401, 36.410, 36.411, 36.412, 36.413, 36.414, 36.420, 36.421, 36.422, 36.423, 36.424, 25.413 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
5713 | 330021 | LTE – Evolved UTRA and UTRAN RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | LTE-RF | 2 | Rel-8 | R4 | Mon 25/09/06 | Fri 05/12/08 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | Tuomo Saynajakangas | RP#42 completed. RP#47 abandoned draft 36.801, 36.803, 36.804 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.942, 25.123, 25.133 |  |  |  |  | Tue 21/03/06 | Tue 16/03/10
5714 | 370046 | LTE – FDD repeaters | LTE-Repeaters | 2 | Rel-8 | R4 | Fri 14/09/07 | Fri 06/03/09 | 100% | RP-070749 | RP-090037 | Powerwave Technologies, Andrew Wireless | ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com | RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report) | 36.106, 36.143, 25.113 | 37 |  |  |  | Mon 01/10/07 | Tue 16/03/10
5715 | 390001 | E-UTRAN Data Definitions | E-UTRAN-OAM | 2 | Rel-8 | S5 | Mon 17/09/07 | Thu 12/03/09 | 100% | - | - | - | - | SP#43 completed | - | 39 | 21 |  |  | Fri 17/06/05 | Mon 03/03/08
5716 | 370001 | Subscriber and Equipment Trace for E-UTRAN and EPC | E-UTRAN-OAM | 3 | Rel-8 | S5 | Mon 17/09/07 | Thu 12/03/09 | 100% | SP-070617 | - | Ericsson | robert.petersen@ericsson.com | SP#43 completed | 32.421, 2.422, 32.423, 2.441, 32.442, 32.443, 32.445 | 37 |  |  |  | Sat 15/09/07 | Thu 29/07/10
5717 | 380036 | E-UTRAN Network Resource Model (NRM) Integration Reference Point (IRP) | E-UTRAN-OAM | 3 | Rel-8 | S5 | Mon 07/01/08 | Thu 12/03/09 | 100% | SP-070738 | - | Ericsson | ELMDAHL, Per | SP#43 completed | new (32.761, 32.762, 32.763, 32.765) | 38 | 21 |  |  | Fri 17/06/05 | Thu 29/07/10
5718 | 390002 | Performance measurements for E-UTRAN | E-UTRAN-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 12/03/09 | 100% | SP-080062 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com) | SP#43 completed | new 32.425 | 39 | 21 |  |  | Fri 17/06/05 | Thu 29/07/10
5719 | 390003 | Key Performance Indicators (KPIs) for E-UTRAN | E-UTRAN-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 12/03/09 | 100% | SP-080063 | - | Ericsson | ulf.hubinette@ericsson.com | SP#43 completed | new (32.450, 32.451) | 39 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
5720 | 390004 | Self-Organizing Networks (SON) | LTE_SON-OAM | 2 | Rel-8 | S5 | Fri 22/02/08 | Thu 11/12/08 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed (WT UID_390007 moved to Rel-9) | - | 39 | 21 |  |  | Fri 17/06/05 | Mon 01/12/08
5721 | 390104 | SON Concepts and requirements | LTE_SON-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 11/12/08 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed | new 32.500 | 39 | 21 |  |  | Fri 17/06/05 | Tue 25/11/08
5722 | 390005 | Self-Establishment of eNBs, including automated Software Management | LTE_SON-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 11/12/08 | 100% | SP-080849 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#42 completed | new (32.501, 32.502, 32.503, 32.531, 32.532, 32.533) | 39 | 21 |  |  | Fri 17/06/05 | Mon 22/03/10
5723 | 390006 | SON Automatic Neighbour Relations (ANR) List Management | LTE_SON-OAM | 3 | Rel-8 | S5 | Fri 22/02/08 | Thu 11/12/08 | 100% | SP-080066 | - | Ericsson | edwin.tse@ericsson.com | SP#42 completed | 32.761, 32.762, 32.763, 32.765, new 32.511 | 39 | 21 |  |  | Fri 17/06/05 | Mon 01/12/08
5724 | 25029 | Rel-8 LTE – Terminal Conformance Test Specification | LTE-UEConTest | 1 | Rel-8 | R5 | Fri 01/06/07 | Fri 04/12/09 | 100% | - | - | - | - | Testing for Feature UID_20068 (LTE) | - |  |  |  |  | Tue 21/03/06 | Sun 01/06/08
5725 | 25041 | 3G LTE – Terminal Protocol Conformance Test Specifications | LTE-UEConTest_SIG | 2 | Rel-8 | R5 | Fri 01/06/07 | Fri 04/12/09 | 100% | RP-080647 | RP-091060 | NEC, Motorola | david.lecompte@nectech.fr, Jacob.John@motorola.com | RP#46 completed | 36.521-1, 36.521-2, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 |  |  |  |  | Tue 21/03/06 | Fri 27/11/09
5726 | 25042 | LTE – Terminal Radio Transmission and Reception Conformance Test Specifications | LTE-UEConTest_RF | 2 | Rel-8 | R5 | Fri 01/06/07 | Fri 04/12/09 | 100% | RP-080601 | RP-091059 | Agilent | andrea_leonardi@agilent.com | RP#46 completed. RP#50 TR 36.903 v100 for Approval | 36.521-1, 36.521-2, 36.521-3, new 36.903 |  |  |  |  | Tue 02/06/09 | Fri 10/12/10
5727 | 350040 | Rel-8 Improvements of the Radio Interface | RInImp8 | 1 | Rel-8 | RP | Mon 05/03/07 | Fri 06/03/09 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 04/01/05 | Tue 24/03/09
5728 | 350034 | UMTS 1500 MHz | RInImp8-UMTS1500 | 2 | Rel-8 | R4 | Mon 05/03/07 | Fri 14/09/07 | 100% | RP-070078 | RP-070526 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#37 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Mon 27/09/04 | Thu 09/07/09
5729 | 350035 | UMTS 700 MHz FDD | RInImp8-UMTS700 | 2 | Rel-8 | R4 | Mon 05/03/07 | Fri 30/05/08 | 100% | RP-070127 | RP-080260 | Nokia | Tuomo Saynajakangas | RP#40 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Mon 27/09/04 | Tue 16/03/10
5730 | 410018 | UMTS 1880 MHz TDD | RInImp9-UMTS1880TDD | 2 | Rel-8 | R4 | Fri 12/09/08 | Fri 06/03/09 | 100% | RP-080757 | RP-090044 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#43 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307 | 41 | 21 |  |  | Thu 11/09/08 | Tue 10/03/09
5731 | 380074 | UMTS 2300 MHz TDD LCR | RInImp8-UMTS2300TDD | 2 | Rel-8 | R4 | Mon 17/12/07 | Fri 12/09/08 | 100% | RP-071016 | RP-080517 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#41 completed. RP#47 abandoned draft 25.828 | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.306, 25.331, 34.122 | 38 | 21 |  |  | Mon 17/12/07 | Mon 02/08/10
5732 | 350037 | Further Improved Minimum Performance Requirements for HSDPA UE (FDD) - Two-Branch Interference Cancellation | RInImp8-2BIC | 2 | Rel-8 | R4 | Mon 05/03/07 | Fri 07/03/08 | 100% | RP-070254 | RP-080041 | AT&T | Marc Grant | RP#39 completed | 25.101 |  |  |  |  | Thu 15/12/05 | Mon 02/08/10
5733 | 370032 | CS Voice Service over HSPA | RInImp8-CsHspa | 2 | Rel-8 | R2 | Thu 19/07/07 | Fri 07/03/08 | 100% | RP-070765 | RP-080042 | Nokia Siemens Networks | woonhee.hwang@nsn.com | RP#39 completed | 25.323, 25.331, 25.322 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
5734 | 370033 | Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-Hsdpa15codes | 2 | Rel-8 | R4 | Mon 11/06/07 | Fri 07/03/08 | 100% | RP-070745 | RP-080043 | Vodafone | tim.frost@vodafone.com | RP#39 completed | 25.101 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
5735 | 350036 | Deleted - UMTS 2300 MHz FDD/TDD | RInImp8-UMTS2300 | 2 | Rel-8 | R4 | Mon 05/03/07 | Fri 12/09/08 | 100% | RP-070128 | RP-080515 | AT&T | Marc Grant | RP#41 stopped | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  | RP-41 | PCG-21 | Mon 27/09/04 | Mon 02/08/10
5736 | 25125 | Rel-8 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-8 | R5 | Fri 01/06/07 | Fri 05/12/08 | 100% | - | - | - | - | 05/08: Linked to Feature UID_20028 (RInImp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
5737 | 25050 | Conformance Test Aspects – CS Voice Service over HSPA | RInImp8-CsHspa_UEConTest | 2 | Rel-8 | R5 | Fri 01/06/07 | Fri 12/09/08 | 100% | RP-080160 | RP-080542 | Huawei | baoyi@huawei.com | RP#41 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 11/03/08 | Tue 09/09/08
5738 | 400055 | Conformance Test Aspects – Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-UEConTest_Hsdpa15codes | 2 | Rel-8 | R5 | Fri 07/03/08 | Fri 05/12/08 | 100% | RP-080311 | RP-080818 | Ericsson | Mikael.Ziren@Ericsson.com | RP#42 completed | 34.121-1, 34.121-2 | 40 | 21 |  |  | Tue 03/06/08 | Tue 09/12/08
5739 | 370035 | Rel-8 RAN improvements | - | 1 | Rel-8 | RP | Mon 04/06/07 | Fri 29/05/09 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/10/07 | Tue 09/02/10
5740 | 360013 | Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-64QamMimoHsdpa | 2 | Rel-8 | R1 | Mon 04/06/07 | Fri 12/09/08 | 100% | RP-070500 | RP-080518 | Ericsson | Johan.Bergman@ericsson.com | RP#41 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141 |  |  |  |  | Thu 21/06/07 | Tue 03/08/10
5741 | 370036 | Improved L2 for uplink | RANimp-UplinkL2dataRates | 2 | Rel-8 | R2 | Fri 14/09/07 | Fri 30/05/08 | 100% | RP-070717 | RP-080265 | Ericsson | Janne.Peisa@ericsson.com | RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD | 25.319, 25.301, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, 25.427 | 37 |  |  |  | Tue 02/10/07 | Tue 03/08/10
5742 | 370037 | Enhanced Uplink for CELL_FACH State in FDD | RANimp-UplinkEnhState | 2 | Rel-8 | R2 | Fri 14/09/07 | Fri 05/12/08 | 100% | RP-070677 | RP-080804 | Nokia Siemens Networks | markus.wimmer@nsn.com | RP#42 completed. Linked to UID_370036 Improved L2 for uplink | 25.309, 25.211, 25.214, 25.321, 25.331, 25.423, 25.433 | 37 |  |  |  | Tue 02/10/07 | Tue 03/08/10
5743 | 370038 | Enhanced UE Discontinuous Reception (DRX) for FDD | RANimp-DRX | 2 | Rel-8 | R2 | Fri 14/09/07 | Fri 12/09/08 | 100% | RP-070679 | RP-080520 | Nokia | luis.barreto@nokia.com | RP#41 completed. Continuation of Rel-7 work item "Continuous connectivity for packet data users" UID_20046. | 25.306, 25.308, 25.321, 25.331, 25.423 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
5744 | 370039 | Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure | RANimp-SrnsReloc | 2 | Rel-8 | R3 | Fri 14/09/07 | Fri 12/09/08 | 100% | RP-070759 | RP-080521 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution | 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.214, 25.133 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
5745 | 370040 | Enhancements for FDD HSPA Evolution | RANimp-HSPAEvo | 2 | Rel-8 | R3,R2 | Fri 14/09/07 | Fri 05/12/08 | 100% | RP-080830 | RP-080805 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#42 completed. Triggered by Rel-7 Study on Scope of future FDD HSPA Evolution (UID_20065) TR 25.999 | 25.401, 25.413, 25.420, 25.423, 25.427, 25.433, 25.446, 25.301, 25.346 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
5746 | 380075 | 64QAM for 1.28 Mcps TDD HSDPA | RANimp-64Qam1.28TDD | 2 | Rel-8 | R1 | Tue 04/12/07 | Fri 05/12/08 | 100% | RP-070924 | RP-080806 | ZTE | zfmail@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.102, 25.105, 25.123, 25.142, 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 38 | 21 |  |  | Mon 17/12/07 | Tue 03/08/10
5747 | 380076 | Enhanced CELL_FACH state in 1.28 Mcps TDD | RANimp-EnhState1.28TDD | 2 | Rel-8 | R2 | Tue 04/12/07 | Fri 05/12/08 | 100% | RP-071038 | RP-080807 | ZTE | zhang.yincheng@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.123, 25.221, 25.222, 25.224, 25.301, 25.302, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.401, 25.423, 25.425, 25.433, 25.435 | 38 | 21 |  |  | Mon 17/12/07 | Tue 03/08/10
5748 | 390028 | Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-LCRCPC | 2 | Rel-8 | R1 | Fri 07/03/08 | Fri 29/05/09 | 100% | RP-080085 | RP-090394 | TD Tech | chenying@td-tech.com | RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.929, 25.308, 25.319 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
5749 | 390029 | HSPA VoIP to WCDMA/GSM CS continuity | RANimp-HSPAVoIP | 2 | Rel-8 | R2 | Fri 07/03/08 | Fri 06/03/09 | 100% | RP-080749 | RP-090050 | Nokia | Simone.Provvedi@nokia.com | RP#43 completed | 25.331, 25.413 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
5750 | 390030 | HS-DSCH Serving Cell Change Enhancements | RANimp-HSDSCH | 2 | Rel-8 | R2 | Fri 07/03/08 | Fri 05/12/08 | 100% | RP-080227 | RP-080811 | Ericsson | henrik.enbuske@ericsson.com | RP#42 completed | 25.101, 25.104, 25.133, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
5751 | 400050 | MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | RANimp-MIMOLCR | 2 | Rel-8 | R1,R4 | Thu 24/01/08 | Fri 29/05/09 | 100% | RP-080485 | RP-090313 | CATT | wangke@datangmobile.cn | RP#43 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.102, 25.105, 25.142 | 40 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
5752 | 400052 | Dual-Cell HSDPA operation on adjacent carriers | RANimp-DCHSDPA | 2 | Rel-8 | R1,R4 | Mon 17/11/08 | Fri 29/05/09 | 100% | RP-080490 | RP-080814 | Ericsson | johan.bergman@ericsson.com | RP#42 completed. Triggered by UID_390032 Study on Dual-Cell HSDPA (withdrawn TR 25.825 v100). | 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 40 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
5753 | 25126 | Rel-8 RAN improvements - UE Conformance Testing | - | 1 | Rel-8 | R5 | Fri 30/05/08 | Fri 17/09/10 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
5754 | 410020 | Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-UEConTest_64QamMimoHsdpa | 2 | Rel-8 | R5 | Fri 12/09/08 | Fri 04/12/09 | 100% | RP-080759 | RP-091058 | Ericsson | leif.mattisson@ericsson.com | RP#46 completed. Testing for UID_360013 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2 | 41 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
5755 | 400056 | Conformance Test Aspects – Improved L2 for uplink | RANimp-UEConTest_UplinkL2dataRates | 2 | Rel-8 | R5 | Fri 30/05/08 | Fri 18/09/09 | 100% | RP-080606 | RP-090712 | Ericsson | leif.mattisson@ericsson.com | RP#45 completed. Testing for UID_370036 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
5756 | 440010 | Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates | RANimp-UEConTest_ImprovedL2LCRTDD | 2 | Rel-8 | R5 | Fri 29/05/09 | Fri 17/09/10 | 100% | RP-090491 | RP-100737 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink | 34.108, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Wed 20/05/09 | Thu 09/09/10
5757 | 400057 | Conformance Test Aspects – 64QAM for 1.28 Mcps TDD HSDPA | RANimp-UEConTest_64Qam1.28TDD | 2 | Rel-8 | R5 | Fri 30/05/08 | Fri 29/05/09 | 100% | RP-080334 | RP-090415 | ZTE | ma.zijiang@zte.com.cn | RP#44 completed. Testing for UID_380075 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
5758 | 420015 | Conformance Test Aspects – Dual-Cell HSDPA operation on adjacent carriers | RANimp-UEConTest_DCHSDPA | 2 | Rel-8 | R5 | Fri 05/12/08 | Fri 04/06/10 | 100% | RP-080996 | RP-100479 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for UID_400052 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 42 | 22 |  |  | Thu 04/12/08 | Tue 03/08/10
5759 | 430024 | Conformance Test Aspects – Enhanced Uplink for CELL_FACH State in FDD | RANimp-UEConTest_EnhancedRACHCellFACHState | 2 | Rel-8 | R5 | Fri 06/03/09 | Fri 04/06/10 | 100% | RP-090152 | RP-100483 | Nokia | jarkko.hellsten@nokia.com | RP#48 completed. Testing for UID_370037 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 43 | 22 |  |  | Fri 27/02/09 | Tue 03/08/10
5760 | 430028 | Conformance Test Aspects – Receiver Type3i | RANimp-UEConTest_ReceiverType3i | 2 | Rel-8 | R5 | Fri 06/03/09 | Fri 04/12/09 | 100% | RP-090010 | RP-091066 | Qualcomm | Ashok Kumar Narayanaswamy (anarayan@qualcomm.com) | RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD | 34.108, 34.121-1, 34.121-2 | 43 | 22 |  |  | Tue 10/03/09 | Tue 03/08/10
5761 | 440009 | Conformance Test Aspects – Enhanced CELL_FACH State in LCR TDD | RANimp-UEConTest_EnhancedCellFACHStateLCRTDD | 2 | Rel-8 | R5 | Sat 30/05/09 | Fri 17/09/10 | 100% | RP-090490 | RP-100735 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for UID_380076 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Wed 20/05/09 | Thu 09/09/10
5762 | 450024 | Conformance Test Aspects – Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-UEConTest_CPCLCRTDD | 2 | Rel-8 | R5 | Fri 18/09/09 | Fri 17/09/10 | 100% | RP-090751 | RP-100739 | ZTE | huang.he4@zte.com.cn | RP#49 completed. Testing for UID_390028 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Thu 09/09/10
5763 | 450025 | Conformance Test Aspects – MIMO for 1.28 Mcps TDD | RANimp-UEConTest_MIMOLCRTDD | 2 | Rel-8 | R5 | Fri 18/09/09 | Fri 04/06/10 | 100% | RP-100120 | RP-100660 | ZTE | huang.chun2@zte.com.cn | PR#48 completed. Testing for UID_400050 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 03/08/10
5764 | 450026 | Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements | HSDSCH_UEConTest | 2 | Rel-8 | R5 | Fri 18/09/09 | Fri 19/03/10 | 100% | RP-090756 | RP-100077 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#47 completed. Testing for UID_390030 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 03/08/10
5765 | 360008 | 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN-DOB | 1 | Rel-8 | R1 | Mon 04/06/07 | Fri 05/12/08 | 100% | RP-081124 | RP-080218 | Ericsson | Lars.Lindbom@ericsson.com | RP#42 completed. WID updated RP-070493=>RP-081124 (changed WI title "MBSFN Downlink Optimized Broadcast (DOB) 3.84 Mcps TDD" => "3.84Mcps TDD MBSFN Integrated Mobile Broadcast"). | 25.102, 25.105, 25.123, 25.201, 25.221, 25.222, 25.223, 25.224, 25.304, 25.306, 25.331, 25.346, 25.402, 25.433 |  |  |  |  | Thu 21/06/07 | Tue 09/12/08
5766 | 440008 | Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN_IMB_UEConTest | 1 | Rel-8 | R5 | Sat 30/05/09 | Fri 19/03/10 | 100% | RP-090583 | RP-100070 | IPwireless | Phil Young (pyoung@ipwireless.com) | RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Thu 21/05/09 | Tue 16/03/10
5767 | 50583 | GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 1 | Rel-8 | GP,G1,C1,G3new | Fri 08/09/06 | Fri 25/11/11 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed. GP#52 completed MS conformance testing | 44.018, 44.060, 45.002, 45.008, 45.010, 48.008, 48.018, 51.010 |  |  |  |  | Wed 13/09/06 | Fri 25/11/11
5768 | 51583 | G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G1 | Fri 08/09/06 | Fri 20/02/09 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 43.055, 43.129, 43.246, 45.002, 45.008, 45.010 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
5769 | 52583 | G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G2 | Fri 08/09/06 | Fri 20/02/09 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 44.018, 44.060, 48.008, 48.018 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
5770 | 53583 | CT1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | C1 | Fri 08/09/06 | Fri 20/02/09 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | - | 24.008 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
5771 | 54583 | Testing for GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G3new | Fri 08/09/06 | Fri 25/11/11 | 100% | GP-061757 | - | Renesas Mobile | deepa.kamath@renesasmobile.com | GP#52 completed | 51.01 |  |  |  |  | Wed 13/09/06 | Fri 25/11/11
5772 | 55586 | U-TDOA Enhancement | GUTEN | 1 | Rel-8 | GP | Fri 18/05/07 | Fri 16/11/07 | 100% | GP-070865 | - | TruePosition | Terry Brooks (terri.brooks@trueposition.com) | GP#36 completed U-TDOA (Uplink Time Difference of Arrival) | 43.059, 45.008, 48.071 |  |  |  |  | Mon 21/05/07 | Sat 30/05/09
5773 | 50587 | GAN Enhancements | GANENH | 1 | Rel-8 | GP | Tue 15/05/07 | Fri 04/09/09 | 100% | GP-071484 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed. GP#43 completed Testing | - |  |  |  |  | Thu 06/09/07 | Mon 28/09/09
5774 | 50588 | Update to GAN specifications | GANENH-SPEC | 2 | Rel-8 | GP | Fri 31/08/07 | Fri 22/02/08 | 100% | GP-071560 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed | 43.318, 44.318 |  |  |  |  | Thu 06/09/07 | Mon 19/05/08
5775 | 53089 | Update TS 51.010 Mobile Station (MS) Conformance Specification for GAN Enhancements | GANENH-MStest | 2 | Rel-8 | G3new | Tue 15/05/07 | Fri 04/09/09 | 100% | GP-071563 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#43 completed | 51.01 |  |  |  |  | Thu 06/09/07 | Mon 07/09/09
5776 | 50591 | AoIP (A-interface over IP) | AoIP | 1 | Rel-8 | GP,S4,C4,C1,C3 | Mon 03/01/00 | Thu 11/12/08 | 100% | GP-081361 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40/TSG#42 completed . Triggered by TR 43.903 Study on A-interface over IP (AINTIP) UID_50589. | - |  | 21 |  |  | Tue 26/02/08 | Wed 03/12/08
5777 | 400041 | GERAN aspects of AoIP | AoIP | 2 | Rel-8 | GP | Mon 03/01/00 | Fri 21/11/08 | 100% | GP-081362 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40 completed. GP#39 updated WID GP-080901=>GP-081362. | 48.001, 48.002, 48.008, 48.020, 49.008, 48.103 | 40 | 21 |  |  | Wed 28/05/08 | Wed 03/12/08
5778 | 400042 | Media Requirements for CS over IP based User Plane | AoIP-CSoIP | 2 | Rel-8 | S4 | Wed 05/12/07 | Thu 11/12/08 | 100% | SP-080444 | - | China Mobile, Ericsson | Karl.Hellwig@Ericsson.com | SP#42 completed | 26.102, 26.103, 26.202 | 40 | 21 |  |  | Sun 09/12/07 | Fri 21/11/08
5779 | 400024 | Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 2 | Rel-8 | C4,C1,C3 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | - | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
5780 | 400324 | CT4 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C4 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.205, 23.153, 23.231, 29.232 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
5781 | 400124 | CT1 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C1 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.009 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
5782 | 400224 | CT3 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C3 | Fri 30/05/08 | Fri 05/12/08 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 29.007 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
5783 | 51147 | New multicarrier BTS class | MCBTS | 1 | Rel-8 | G1 | Fri 31/08/07 | Fri 29/08/08 | 100% | GP-071542 | - | Alcatel-Lucent | thomas.bitzer@alcatel-lucent.de | GP#39 completed | 45.005, 45.050, 51.021 |  |  |  |  | Thu 06/09/07 | Sun 31/08/08
5784 | 38001 | Support for Additional Navigation Satellite Systems (ANSS) for LCS | ANSS | 1 | Rel-8 | S1,G2,R2 | Fri 16/05/08 | Thu 11/12/08 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | - |  |  |  |  | Mon 19/05/08 | Thu 19/02/09
5785 | 420038 | Stage 1 for ANSS for LCS | ANSS | 2 | Rel-8 | S1 | Thu 11/12/08 | Thu 11/12/08 | 100% | - | - | - | - | SP#42 completed by 22.071 CR0077 | 22.071 | 42 | 22 |  |  | Mon 08/12/08 | Tue 09/02/10
5786 | 38101 | GERAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | ANSS | 2 | Rel-8 | G2 | Fri 16/05/08 | Fri 21/11/08 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | 43.059, 44.031, 49.031, 44.071, 48.031, 51.010 |  |  |  |  | Mon 19/05/08 | Wed 03/12/08
5787 | 400051 | RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | RANimp-ANSS | 2 | Rel-8 | R2 | Fri 30/05/08 | Fri 05/12/08 | 100% | RP-080346 | RP-080813 | Qualcomm | Etienne Chaponniere (echaponn@qualcomm.com) | RP#42 WI closed at 95%. Considers Rel-9 performance requirements | 25.305, 25.306, 25.331, 25.413, 25.423, 25.433, 25.453 | 40 | 21 |  |  | Mon 17/03/08 | Thu 04/12/08
5788 | 51149 | Conformance testing for the Latency Reductions feature | CTLATRED | 1 | Rel-8 | G1,G3new | Fri 22/02/08 | Fri 05/03/10 | 100% | GP-080367 | - | Ericsson | mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com | GP#45 completed | - |  | 21 |  |  | Tue 26/02/08 | Fri 05/03/10
5789 | 53090 | MS conformance testing for the Latency Reductions feature | CTLATRED-MStest | 2 | Rel-8 | G3new | Fri 22/02/08 | Fri 05/03/10 | 100% | GP-080368 | - | Ericsson | hakan.e.grunditz@ericsson.com | GP#45 completed | 51.01 |  | 21 |  |  | Tue 26/02/08 | Fri 05/03/10
5790 | 51150 | BTS conformance testing for the Latency Reductions feature | CTLATRED-BTStest | 2 | Rel-8 | G1 | Fri 22/02/08 | Fri 20/02/09 | 100% | GP-080369 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#41 completed | 51.021 |  | 21 |  |  | Tue 26/02/08 | Fri 20/02/09
5791 | 53091 | MS conformance testing of changes introduced by WI "Support of Packet-switched Handover for GERAN A/Gb mode" | PSHCT-MStest | 1 | Rel-8 | G3new | Fri 22/02/08 | Fri 21/11/08 | 100% | GP-080411 | - | Rohde & Schwarz | Franz.Segerer@ROHDE-SCHWARZ.COM | GP#40 completed | 51.01 |  | 21 |  |  | Tue 26/02/08 | Sat 22/11/08
5792 | 320001 | (Small) Technical Enhancements and Improvements for Rel-8 | TEI8 | 1 | Rel-8 | SP,CP,RP,GP | Mon 01/01/07 | Thu 11/12/08 | 100% | - | - | - | - | SP#42 completed | - |  |  |  |  | Fri 04/11/05 | Fri 20/02/09
5793 | 521029 | (IETF) (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_IETF | 1 | Rel-8 | C1-IETF | Mon 01/01/07 | Fri 07/09/12 | 100% | - | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#57 completed | RFC 6714 (was draft-ietf-simple-msrp-cema) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
5794 | 400025 | Test - (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_Test | 1 | Rel-8 | R5,G3new | Wed 07/03/07 | Fri 24/12/10 | 100% | - | - | - | - | - | - | 40 | 21 |  |  | Fri 04/11/05 | Tue 07/12/10
5795 | 31067 | Deleted - All-IP Network | AIPN | 1 | Rel-8 | S1 | Mon 28/06/04 | Wed 15/03/06 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | SP#38 stopped. 25/07/08 Moved UID_31059 Study on All-IP Network (FS_AIPN/was AIPFS) to Rel-7 out of the stopped Rel-8 Feature UID_31067 Deleted - All-IP Network (AIPN) | - |  |  | SP-38 |  | Mon 30/08/04 | Tue 24/03/09
5796 | 31068 | Deleted - Stage 1 | AIPN | 2 | Rel-8 | S1 | Mon 28/06/04 | Wed 15/03/06 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | 22.258 withdrawn, superseded by 22.278 (UID 320022). SP#38 stopped | 22.258 |  |  | SP-38 |  | Mon 30/08/04 | Tue 24/03/09
5797 | 340032 | Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN | LCS4_IWLAN | 1 | Rel-8 | S2 | Fri 28/09/07 | Fri 28/09/07 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com | SP#35 stopped | 23.234, 23.271, 23.167 | 34 |  | SP-35 |  | Wed 22/03/06 | Tue 24/03/09
5798 | 330010 | Deleted - never approved- FBI Phase 2 | FBI2 | 1 | Rel-8 | S2 | Fri 28/09/07 | Fri 28/09/07 | 100% | - | - | Nokia Siemens Networks | - | SP#38 stopped | - |  |  | SP-38 |  | Mon 09/06/03 | Tue 24/03/09
5799 | 330007 | Deleted -Enhancements to BS30 Bearer service for Videotelephony | BS30 | 1 | Rel-8 | S1 | Thu 15/03/07 | Thu 15/03/07 | 100% | SP-060484 | - | 3 | andre.jarvis@three.co.uk | SP#38 stopped (no support) | 22.002, 22.004, 22.101, 22.105, 24.008 |  |  | SP-38 |  | Fri 06/10/06 | Tue 24/03/09
5800 | 370055 | Deleted - IMS Enhancements Rel-8 | IMS8 | 1 | Rel-8 | S1 | Mon 03/09/07 | Fri 14/12/07 | 100% | - | - | Telecom Italia | - | SP#38 stopped | - | 37 |  | SP-38 |  | Tue 30/10/07 | Tue 24/03/09
5801 | 400023 | Deleted - Contact Manager Conformance Test specifications | eUPHBOOK-Test | 1 | Rel-8 | C6 | Mon 02/06/08 | Fri 19/03/10 | 100% | CP-080430 | - | Comprion, Gemalto | Udo Willenbrink, Jacques Seif | CP#47 work stopped/abandoned | - | 40 | 21 | CP-47 | PCG-24 | Tue 24/01/06 | Tue 09/03/10
5802 | 400123 | Deleted - Contact Manager for 3GPP UICC applications test specifications | eUPHBOOK-Test | 2 | Rel-8 | C6 | Mon 02/06/08 | Fri 19/03/10 | 100% | CP-080430 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#47 work stopped/abandoned | 31.320 (external interface for communication with the ME) | 40 | 21 | CP-47 | PCG-24 | Mon 24/11/08 | Mon 06/09/10
5803 | 400223 | Deleted - Contact Manager API for Java™ Card test specification | eUPHBOOK-Test | 2 | Rel-8 | C6 | Mon 02/06/08 | Fri 19/03/10 | 100% | CP-080430 | - | Gemalto | jacques.seif@gemalto.com | CP#47 work stopped/abandoned | 31.321 (internal interface (API)) | 40 | 21 | CP-47 | PCG-24 | Mon 24/11/08 | Tue 09/03/10
5804 | 53092 | Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain | SCSAGBCT-MStest | 1 | Rel-8 | G3new | Mon 25/02/08 | Fri 04/09/09 | 100% | GP-080330 | - | Nokia | arsi.heino@nokia.com | GP#43 work stopped/abandoned (completion 0%) | 51.01 |  | 21 | GP-43 | PCG-23 | Tue 26/02/08 | Mon 07/09/09
5805 | 0 | Release 8 Studies | - | 1 | Rel-8 | CP,GP,RP,SP | Fri 07/10/05 | Fri 07/10/05 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
5806 | 7026 | Study on Customised Alerting Tone (CAT) Requirements | FS_CAT | 1 | Rel-8 | S1 | Fri 07/10/05 | Thu 14/09/06 | 100% | SP-060474 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | Spin-off Rel-8 Feature Customized Alerting Tone (CAT) Service UID_340029 | 22.982 |  |  |  |  | Fri 04/11/05 | Tue 31/08/10
5807 | 7027 | Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) | FS_M2M | 1 | Rel-8 | S1 | Fri 04/11/05 | Thu 08/03/07 | 100% | SP-050527 | - | Siemens | Juergen Merkel | SP#35 completed. Spin-off SA3 Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M (UID_370053). SP#40 Spin-off new Feature UID_410030 (NIMTC) | 22.868 |  |  |  |  | Fri 04/11/05 | Mon 24/03/08
5808 | 31089 | Study on Network Composition | FS_NetComp | 1 | Rel-8 | S1 | Wed 07/12/05 | Wed 12/12/07 | 100% | SP-060478 | - | Nokia Siemens Networks | joerg.swetina@neclab.eu | SP#38 completed | 22.98 |  |  |  |  | Mon 12/12/05 | Mon 24/03/08
5809 | 320024 | Study on Requirements of IMS Multimedia Conferencing | FS_IMSconf | 1 | Rel-8 | S1 | Thu 08/06/06 | Wed 12/09/07 | 100% | SP-060479 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#37 completed. Spin-off New Feature UID_370026 Value-Added Services for Short Message Service (VAS4SMS) | 22.948 |  |  |  |  | Fri 23/06/06 | Tue 31/08/10
5810 | 320025 | Study on support of a Public Warning System | FS_PWS | 1 | Rel-8 | S1 | Mon 03/09/07 | Fri 14/03/08 | 100% | SP-080054 | - | T-Mobile | mark.younge@t-mobile.com | SP#39 completed. Spin-off Rel-9 Feature UID_380057 (PWS) | 22.968 |  |  |  |  | Fri 23/06/06 | Thu 20/03/08
5811 | 330016 | Study on Paging Permission with Access Control | FS_PPAC | 1 | Rel-8 | S1 | Thu 28/09/06 | Thu 20/09/07 | 100% | SP-060785 | - | NTT DoCoMo | Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp) | SP#37 completed. Spin-off new Feature UID_370084 (PPACR) | 22.908 |  |  |  |  | Fri 06/10/06 | Tue 31/08/10
5812 | 340033 | Study on Non-3GPP access Network Selection Principles (NSP) | FS_N3GtoNSP | 1 | Rel-8 | S1 | Wed 06/12/06 | Thu 05/06/08 | 100% | SP-080318 | - | Telefónica O2 | chris.friel@O2.com | SP#38 completed. Spin-off New Feature UID_380062 (N3GTONSP). SP#40 WID updated SP-060930=>SP-080318. TR re-approved with new # 22.812=>22.912 | 22.912 | 34 |  |  |  | Fri 06/10/06 | Tue 03/06/08
5813 | 340034 | Study on Value Added Services for Short Message Service | FS_VAS4SMS | 1 | Rel-8 | S1 | Wed 06/12/06 | Fri 07/12/07 | 100% | SP-060786 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#38 completed. Spin-off New Feature UID_370026 (VAS4SM) | 22.942 | 34 |  |  |  | Fri 06/10/06 | Tue 31/08/10
5814 | 340035 | Study on Service continuity between mobile and WLAN networks | FS_SMLSWLAN | 1 | Rel-8 | S1 | Wed 06/12/06 | Thu 06/12/07 | 100% | SP-060936 | - | NEC | joerg.swetina@neclab.eu | SP#38 completed | 22.937 | 34 |  |  |  | Fri 06/10/06 | Tue 31/08/10
5815 | 370086 | Study on Services Alignment and Migration | FS_ServAl | 1 | Rel-8 | S1 | Wed 06/12/06 | Wed 12/03/08 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. Spin-off Rel-9 Feature UID_330017 Services Alignment and Migration (ServAl) | 22.983 | 37 |  |  |  | Fri 06/10/06 | Thu 05/08/10
5816 | 32085 | Study on 3GPP System Architecture Evolution | FS_SAE | 1 | Rel-8 | S2,S3 | Fri 03/12/04 | Thu 12/03/09 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#43 completed | - |  |  |  |  | Mon 31/01/05 | Fri 20/02/09
5817 | 32086 | Stage 2 Interim conclusion for RAN Work to start | FS_SAE | 2 | Rel-8 | S2 | Fri 03/12/04 | Thu 18/09/08 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882 |  |  |  |  | Mon 31/01/05 | Sun 14/09/08
5818 | 32087 | Stage 2 study on 3GPP architectural development | FS_SAE | 2 | Rel-8 | S2 | Mon 09/01/06 | Thu 18/09/08 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882 |  |  |  |  | Mon 31/01/05 | Sun 14/09/08
5819 | 7024 | Security study for Inter-access mobility between non-3GPP and 3GPP system | FS_SAE | 2 | Rel-8 | S3 | Mon 03/09/07 | Thu 12/03/09 | 100% | SP-070163 | - | Nokia | dajiang.zhang@nokia.com | SP#43 completed | 33.821, 33.822 |  |  |  |  | Tue 21/02/06 | Fri 20/02/09
5820 | 320028 | Study on Stage 2 aspects of IMS Service Brokering | FS_ISB_ST2 | 1 | Rel-8 | S2 | Mon 19/06/06 | Thu 18/09/08 | 100% | SP-060443 | - | Telcordia | raquel@research.telcordia.com | SP#41 completed. No spin-off activity proposed. [Note: IMS Service Brokering enhancements UID_31088 moved back from R8 to R7 to give a home to 22228CR0036_(Rel-7)_S1-051232. Hence, Rel-7 ISB has Stage 1 only (and is misaligned with Rel-7 Stages 2/3.] | 23.81 |  |  |  |  | Mon 17/07/06 | Sun 14/09/08
5821 | 7049 | Study on IMS utilizing multicast bearer services | FS_MLTICAST-IMS | 1 | Rel-8 | S2 | Wed 22/03/06 | Thu 06/12/07 | 100% | SP-060148 | - | Nokia Siemens Networks | - | SP#38 completed | 23.847 |  |  |  |  | Wed 22/03/06 | Mon 24/03/08
5822 | 350051 | Study on Multimedia Session Continuity | FS_MMSC | 1 | Rel-8 | S2 | Thu 26/04/07 | Thu 05/06/08 | 100% | SP-070818 | - | LG Electronics | - | SP#40 completed | 23.893 |  |  |  |  | Thu 29/03/07 | Mon 24/03/08
5823 | 380034 | Study on centralized IMS service control | FS_ICS | 1 | Rel-8 | S2,S1 | Mon 23/10/06 | Wed 12/03/08 | 100% | SP-070494 | - | Ericsson | peter.bleckert@ericsson.com | SP#39 completed | - | 38 | 21 |  |  | Wed 31/10/07 | Thu 20/03/08
5824 | 370087 | Study on centralized IMS services requirements | FS_ICS-S1 | 2 | Rel-8 | S1 | Mon 05/03/07 | Wed 12/03/08 | 100% | SP-070494 | - | NEC | joerg.swetina@neclab.eu | SP#39 completed | 22.892 | 37 |  |  |  | Wed 21/11/07 | Tue 31/08/10
5825 | 330012 | Study on centralized IMS services control | FS_IMS_CSC | 2 | Rel-8 | S2 | Mon 23/10/06 | Wed 12/03/08 | 100% | SP-070494 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#39 completed | 23.892 |  |  |  |  | Thu 16/02/06 | Sat 22/03/08
5826 | 380078 | Study on Architecture of IMS based Customized Alerting Tone (CAT) | FS_CAT-St2 | 1 | Rel-8 | S2 | Tue 04/12/07 | Thu 18/09/08 | 100% | SP-070905 | - | China Mobile | WANG, Jing (wangjing@chinamobilecom) | SP#41 completed as Rel-8 | 23.872 | 38 | 21 |  |  | Thu 20/12/07 | Tue 23/09/08
5827 | 380085 | Study on Home (e)NodeB Security | FS_HNB_Sec | 1 | Rel-8 | S3 | Thu 20/12/07 | Thu 12/03/09 | 100% | SP-070783 | - | Huawei | yangyanmei@huawei.com | SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007) | 33.82 | 38 | 21 |  |  | Thu 20/12/07 | Wed 11/03/09
5828 | 360015 | Study on Transferring of emergency call data – in-band modem solution | eCALLIBMS | 1 | Rel-8 | S4 | Thu 07/12/06 | Wed 12/12/07 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2) | 26.967 |  |  |  |  | Sun 10/12/06 | Fri 16/05/08
5829 | 35065 | Study on Element Operations Systems Function (EOSF) definition | OAM7-NIM-EOSF | 1 | Rel-8 | S5 | Thu 07/06/07 | Thu 12/06/08 | 100% | SP-070307 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed. WID updated SP-050608=>SP-070307 | 32.819 |  |  |  |  | Fri 16/09/05 | Mon 28/04/08
5830 | 35074 | Study on SA5 MTOSI XML Harmonization | OAM8-NIM-XML | 1 | Rel-8 | S5 | Wed 10/05/06 | Wed 12/09/07 | 100% | SP-070305 | - | Nortel | jduguay@nortel.com | SP#37 completed. WID updated SP-050295=>SP-070305 | 32.818 |  |  |  |  | Thu 24/11/05 | Thu 15/10/09
5831 | 320006 | Study on Common Profile Storage (CPS) Framework of User Data for network services and management | OAM7-CPS | 1 | Rel-8 | S5 | Mon 03/07/06 | Thu 07/06/07 | 100% | SP-060263 | - | T-Mobile | istvan.aba@t-mobile.at | SP#36 completed. Spin-off New Feature UID_400034 User Data Convergence (UDC) | 32.808 |  |  |  |  | Mon 22/05/06 | Mon 17/03/08
5832 | 340036 | Study on Management for LTE and SAE | FS_OAM_LTE_SAE | 1 | Rel-8 | S5 | Thu 07/12/06 | Thu 11/12/08 | 100% | SP-060753 | - | Ericsson | robert.petersen@ericsson.com | SP#42 completed | 32.816 | 34 |  |  |  | Fri 15/12/06 | Tue 25/11/08
5833 | 350004 | Study on Charging Aspects of 3GPP System Evolution | FS_SAEcharg | 1 | Rel-8 | S5 | Mon 02/04/07 | Thu 06/12/07 | 100% | SP-070174 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#38 completed | 32.82 |  |  |  |  | Thu 24/11/05 | Mon 17/03/08
5834 | 7048 | Study on AS-MRFC media server control protocol | MRFC | 1 | Rel-8 | C1 | Wed 22/03/06 | Fri 13/06/08 | 100% | CP-060180 | - | Hewlett-Packard | mark.syrett@hp.com | CP#40 completed. Spin-off New Feature UID_380035 (MRFC_TS) | 24.88 |  |  |  |  | Wed 22/03/06 | Tue 13/05/08
5835 | 350018 | Study on IMS Restoration Procedures | FS_IMS_RP | 1 | Rel-8 | C4 | Mon 26/03/07 | Fri 30/05/08 | 100% | CP-070031 | - | Ericsson | german.blanco@ericsson.com | CP#40 completed. Spin-off WID UID_400012 (IMS_RP) | 23.82 |  |  |  |  | Thu 29/03/07 | Thu 29/05/08
5836 | 360030 | Study on IMS Application Server Service Data Descriptions for AS interoperability | FS_IMS_ASIO | 1 | Rel-8 | C4 | Fri 14/09/07 | Fri 12/09/08 | 100% | CP-070685 | - | Alcatel-Lucent | Jean-Jacques Trottin | CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO) | 29.864 |  |  |  |  | Wed 05/09/07 | Thu 11/09/08
5837 | 360031 | Study on Customized Alerting Tone (CAT) solution for voice and video call in CS domain | FS_CAT_VVC_CS | 1 | Rel-8 | C4 | Fri 14/09/07 | Fri 12/09/08 | 100% | CP-070518 | - | China Mobile | zhanghao@chinamobile.com | CP#41 completed. Spin-off WID under Feature CAT UID_340029 | 29.882 |  |  |  |  | Wed 05/09/07 | Mon 01/09/08
5838 | 380023 | Study on InterWorking Function between MAP based and Diameter based interfaces | FS_MAP2Diam | 1 | Rel-8 | C4 | Fri 30/11/07 | Fri 05/12/08 | 100% | CP-070760 | - | Huawei | liming49985@huawei.com | CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005 | 29.805 | 38 | 21 |  |  | Mon 19/11/07 | Sat 22/11/08
5839 | 370041 | Study on Scope of future HSPA Evolution for 1.28 Mcps TDD | FS_RAN-LCRTDDHSPAEvo | 1 | Rel-8 | R1 | Fri 14/09/07 | Fri 30/05/08 | 100% | RP-070748 | RP-080290 | RITT | Xu Fei | RP#40 completed | 25.824 | 37 |  |  |  | Thu 21/06/07 | Thu 12/06/08
5840 | 370042 | Study on Synchronized E-DCH for UTRA FDD | FS_RAN-UplinkSync | 1 | Rel-8 | R1 | Fri 14/09/07 | Fri 07/03/08 | 100% | RP-070678 | RP-080068 | Nokia Siemens Networks | Karri.Ranta-aho@nsn.com | RP#39 completed | 25.823 | 37 |  |  |  | Thu 21/06/07 | Thu 26/06/08
5841 | 360016 | Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies | FS_RAN-LTEmob | 1 | Rel-8 | R4 | Mon 04/06/07 | Mon 03/12/07 | 100% | RP-070511 | RP-070827 | Motorola | hao.bi@Motorola.com | RP#38 completed | 36.938 |  |  |  |  | Thu 21/06/07 | Thu 26/06/08
5842 | 350039 | Study on 3G Home NodeB/eNodeB | FS_RAN-HNBeNB | 1 | Rel-8 | R4 | Mon 05/03/07 | Fri 30/05/08 | 100% | RP-070257 | RP-080289 | Motorola | howard.thomas@motorola.com | RP#40 completed | 25.82 |  |  |  |  | Thu 29/03/07 | Thu 26/06/08
5843 | 50589 | Study on A-interface over IP | AINTIP | 1 | Rel-8 | GP | Fri 31/08/07 | Fri 22/02/08 | 100% | GP-071562 | - | China Mobile, Ericsson | paul.schliwa-bertling@ericsson.com | GP#37 completed. Spin-off implementation Feature AoIP (A-interface over IP) UID_50591 | 43.903 |  |  |  |  | Sat 03/11/07 | Mon 03/03/08
5844 | 50590 | Study on Multi-User Reusing-One-Slot | MUROS | 1 | Rel-8 | GP | Fri 16/11/07 | Fri 12/11/10 | 100% | GP-072033 | - | Nokia Siemens Networks | juergen.hofmann@nsn.com | GP#48 completed as Rel-8. Spin-off implementation WI UID_420002 VAMOS (Voice services over Adaptive Multi-user channels on One Slot) | 45.914 |  |  |  |  | Mon 19/11/07 | Tue 30/11/10
5845 | 51148 | Study on Optimized Transmit Pulse Shape for Downlink EGPRS2-B | WIDER | 1 | Rel-8 | G1 | Fri 16/11/07 | Fri 21/05/10 | 100% | GP-072026 | - | Research In Motion, Nokia Siemens Networks | jdwyer@RIM.COM and eddie.riddington@nsn.com | GP#46 completed | 45.913 |  |  |  |  | Tue 26/02/08 | Thu 27/05/10
5846 | 350017 | Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems | FS_SM3GWLAN | 1 | Rel-8 | S2 | Tue 20/03/07 | Thu 18/09/08 | 100% | SP-070106 | - | Orange | - | SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327. | withdrawn 23.827 |  |  | SP-41 | PCG-21 | Thu 29/03/07 | Wed 17/09/08
5847 | 370044 | Deleted - equals 340035 -FS on Service continuity between mobile and WLAN networks | FSSCMobToW | 1 | Rel-8 | S1 | Mon 03/09/07 | Fri 14/12/07 | 100% | SP-070557 | - | BT | mike.meyerstein@bt.com | SP#39 stopped | 22.937 | 37 |  | SP-39 | PCG-21 | Tue 02/10/07 | Tue 24/03/09
5848 | 380068 | Deleted - Study on Evaluation of LCS Control Plane Solution for EPS | FS_LCS_EPS | 1 | Rel-8 | S2 | Mon 14/01/08 | Fri 30/05/08 | 100% | SP-070819 | - | SiRF | - | SP#40 spin-off Feature UID_400038 (LCS_CPS_EPS). SP#40 FS stopped | 23.891 | 38 |  | SP-40 | PCG-21 | Tue 02/10/07 | Tue 24/03/09
5849 | 380080 | Deleted - Study on HS-PDSCH serving cell change enhancements | FS_RAN-HSPDSCH | 1 | Rel-8 | R4 | Mon 17/12/07 | Fri 07/03/08 | 100% | RP-071044 | RP-080070 | Qualcomm | - | RP#39 stopped (no TR produced). Spin-off HS-DSCH Serving Cell Change Enhancements (UID_39003) | none | 38 | 21 | RP-39 | PCG-21 | Mon 17/12/07 | Thu 26/06/08
5850 | 390032 | Deleted - Study on Dual-Cell HSDPA operation | FS_RAN-DCHS | 1 | Rel-8 | R1 | Wed 15/08/07 | Fri 06/03/09 | 100% | RP-080228 | RP-090066 | Qualcomm | Josef Blanz | RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052) | withdrawn 25.825 v100 | 39 | 21 | RP-43 | PCG-22 | Mon 17/12/07 | Tue 17/03/09
5851 | 0 | --- RELEASE 7 --- | - | 1 | Rel-7 | CP,GP,RP,SP | Mon 02/05/05 | Thu 06/12/07 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
5852 | 732097 | Identification of Communication Services in IMS | ServID | 1 | Rel-7 | S2,S1,C1,S5 | Mon 02/05/05 | Fri 14/09/07 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | WID approved SP#28. WID updated SP#32 | - |  |  |  |  | Wed 22/06/05 | Tue 01/07/08
5853 | 32106 | TR on ServID | ServID | 2 | Rel-7 | S2 | Mon 02/05/05 | Tue 21/03/06 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 23.816 |  |  |  |  | Fri 01/07/05 | Tue 01/07/08
5854 | 32107 | Stage 1,2 of ServID | ServID | 2 | Rel-7 | S1,S2 | Fri 11/11/05 | Wed 31/05/06 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 22.228, 23.228, 23.203 |  |  |  |  | Fri 01/07/05 | Tue 01/07/08
5855 | 320010 | Stage 3 of ServID | ServID | 2 | Rel-7 | C1 | Fri 31/03/06 | Thu 15/03/07 | 100% | CP-060259 | - | Ericsson | christer.holmberg@ericsson.com | CP#32 approved WID | 23.218, 24.229 |  |  |  |  | Mon 20/03/06 | Tue 01/07/08
5856 | 7035 | Charging of ServID | ServID | 2 | Rel-7 | S5 | Fri 31/03/06 | Fri 14/09/07 | 100% | SP-060293 | - | Orange | alain.bibas@orange-ft.com | - | 32.260, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Tue 01/07/08
5857 | 32116 | Supporting Globally Routable User Agent URIs in IMS | GRUU | 1 | Rel-7 | S2,S1,C1 | Mon 14/11/05 | Fri 15/06/07 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | - |  |  |  |  | Fri 28/03/03 | Tue 01/07/08
5858 | 7009 | Deleted - TR on GRUU | GRUU | 2 | Rel-7 | S2 | Mon 14/11/05 | Thu 14/09/06 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | Abandoned | - |  |  | SP-32 |  | Thu 16/02/06 | Tue 01/07/08
5859 | 7010 | Stage 1,2 of GRUU | GRUU | 2 | Rel-7 | S1,S2 | Mon 03/07/06 | Fri 29/09/06 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | 22.228, 23.228, 23.218, 24.229 |  |  |  |  | Thu 16/02/06 | Tue 01/07/08
5860 | 320011 | Stage 3 of GRUU | GRUU | 2 | Rel-7 | C1 | Fri 02/06/06 | Fri 15/06/07 | 100% | CP-060358 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#32 approved WID | 24.229 |  |  |  |  | Thu 16/02/06 | Tue 01/07/08
5861 | 7038 | Multimedia Telephony Service for IMS | MTSI | 1 | Rel-7 | S1,C1,S4 | Wed 01/02/06 | Wed 15/03/17 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | - | 69 | 35 |  |  | Thu 02/03/06 | Wed 25/06/08
5862 | 7039 | Stage 1 of MTSI | MTSI-REQ | 2 | Rel-7 | S1 | Wed 01/02/06 | Fri 29/09/06 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173 |  |  |  |  | Tue 21/03/06 | Wed 25/06/08
5863 | 7037 | Stage 3 of MTSI | MTSI | 2 | Rel-7 | C1 | Fri 10/03/06 | Thu 14/06/07 | 100% | CP-060257 | - | Ericsson | christer.holmberg@ericsson.com | - | 24.173 |  |  |  |  | Wed 22/03/06 | Wed 25/06/08
5864 | 7040 | Media handling and interaction in MTSI | MTSI-MHI | 2 | Rel-7 | S4 | Wed 15/03/06 | Thu 15/03/07 | 100% | SP-060225 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.114 |  |  |  |  | Tue 21/03/06 | Wed 25/06/08
5865 | 690069 | UE Conformance Test Aspects - Multimedia Telephony Services for IMS (MTSI) over fixed access | MTSI_FIXED_ACCESS-UEConTest | 2 | Rel-7 | R5 | Tue 15/09/15 | Wed 15/03/17 | 100% | RP-151257 |  | Telecom Italia |  | tested: REL-7 SA/CT WI MTSI;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15%1/7/16: Compl:15%->30% ¦21/ |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
5866 | 690071 | UE Conformance Test Aspects – Multimedia Telephony Services for IMS (MTSI) over WLAN | MTSI_WLAN-UEConTest | 2 | Rel-7 | R5 | Tue 15/09/15 | Thu 15/12/16 | 100% | RP-151770 |  | Ericsson |  | tested: REL-7 WI MTSI¦1/1/16: Compl:0%->5%1/1/16: WID: RP-151334->RP-15177022/3/16: Compl:5%->10% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 20/12/16
5867 | 7023 | Deleted - duplicates UID7039 - IMS Multimedia Telephony Service | MMTEL | 2 | Rel-7 | S1 | Fri 15/06/07 | Fri 15/06/07 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173 |  |  | SP-32 |  | Thu 02/03/06 | Wed 25/06/08
5868 | 350147 | Multimedia Telephony Service for IMS (MTSI) - UE Conformance Testing | MTSI-UEConTest | 1 | Rel-7 | R5 | Wed 19/09/07 | Thu 12/03/09 | 100% | RP-080605 | RP-090056 | Ericsson, Motorola | Leif.Mattisson@ericsson.com, Jacob.John@motorola.com | RP#43 completed. Linked UID_7038 (MTSI) | 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2 |  |  |  |  | Tue 21/03/06 | Tue 24/02/09
5869 | 377001 | TISPAN requirements for Multimedia Telephony with PSTN/ISDN simulation services | TMMTEL7 | 1 | Rel-7 | S1 | Tue 18/09/07 | Thu 06/12/07 | 100% | SP-070568 | - | - | - | - | 22.273 (EI 181 002 maintenance) | 37 |  |  |  | Thu 10/01/08 | Thu 10/01/08
5870 | 387001 | Maintenance of TISPAN release 1 common IMS | MCIMSTR1 | 1 | Rel-7 | S2 | Mon 02/07/07 | Fri 07/03/08 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | http://www.3gpp.org/specs/TISPAN-IMS-ansfer.htm | 38 | 21 |  |  | Thu 10/01/08 | Mon 21/07/08
5871 | 387002 | SA1 aspects of MCIMSTR1 | MCIMSTR1-S1 | 2 | Rel-7 | S1 | Tue 18/09/07 | Thu 06/12/07 | 100% | SP-070915 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | - | 22.173, 22.273 | 38 | 21 |  |  | Thu 10/01/08 | Tue 04/11/08
5872 | 387003 | SA2 aspects of MCIMSTR1 | MCIMSTR1-S2 | 2 | Rel-7 | S2 | Tue 18/09/07 | Thu 06/12/07 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | 23.406, 23.417, 23.508,23.509, 23.511 | 38 | 21 |  |  | Thu 10/01/08 | Mon 21/07/08
5873 | 380072 | SA1,SA2 part of Maintenance of TISPAN release 1 common IMS | IMS_Comm_Mtce7 | 2 | Rel-7 | S2,S1 | Mon 02/07/07 | Thu 06/12/07 | 100% | SP-080501 | - | BT, Ericsson | Dick Knight, Raymond Forbes | SP#38 completed | 22.173, 22.273, 22.401, 23.406, 23.417, 23.508, 23.509, 23.511 | 38 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
5874 | 380004 | Maintenance of TISPAN R1 | MAINT_R1 | 2 | Rel-7 | C1,C3,C4 | Fri 09/11/07 | Fri 07/03/08 | 100% | CP-080211 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.404, 24.405, 24.406, 24.407, 24.408, 24.410, 24.411, 24.416, 29.421, 24.423, 24.428, 24.429, 29.433, 24.441, 24.403, 29.427, 24.430, 29.412 | 38 | 21 |  |  | Mon 19/11/07 | Tue 15/04/08
5875 | 32045 | PS domain and IMS impacts for supporting IMS Emergency calls (EMC1) | EMC1 | 1 | Rel-7 | S2,S1,C1,C4,IETF | Mon 18/09/00 | Fri 09/12/11 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | EMC1 |  |  |  |  | Thu 27/03/03 | Fri 28/03/03
5876 | 1314 | Service Requirements for IP-based emergency calls | EMC1 | 2 | Rel-7 | S1 | Mon 18/09/00 | Fri 25/06/04 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 22.101 |  |  |  |  | Wed 19/04/00 | Tue 08/06/04
5877 | 32046 | Study on Stage 2 for IMS-level solution | EMC1 | 2 | Rel-7 | S2 | Wed 26/02/03 | Fri 16/09/05 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 |  |  |  |  | Thu 27/03/03 | Thu 22/12/05
5878 | 32080 | Study on Stage 2 for GPRS-level solution | EMC1 | 2 | Rel-7 | S2 | Thu 14/10/04 | Thu 08/12/05 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 |  |  |  |  | Thu 14/10/04 | Thu 22/12/05
5879 | 32100 | Stage 2 Specification Phase - IMS-level | EMC1 | 2 | Rel-7 | S2 | Mon 05/09/05 | Fri 09/06/06 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.060, 23.167, 23.203, 23.221, 23.228, 23.234, 23.271, 23.406 |  |  |  |  | Thu 14/10/04 | Tue 19/09/06
5880 | 32101 | Deleted - Stage 2 Specification Phase - GPRS-level | EMC1 | 2 | Rel-7 | S2 | Fri 02/03/07 | Fri 02/03/07 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | - |  |  | SP-32 |  | Thu 14/10/04 | Fri 22/06/07
5881 | 1653 | Emergency Call Enhancements for IP& PS Based Calls – stage 3 | EMC1 | 2 | Rel-7 | C1,C4,IETF | Mon 09/01/06 | Fri 09/12/11 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | - |  |  |  |  | Tue 08/08/00 | Thu 22/12/05
5882 | 1315 | CT1 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1 | Mon 09/01/06 | Fri 15/06/07 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.229 |  |  |  |  | Wed 19/04/00 | Wed 12/09/07
5883 | 521030 | (IETF) CT1 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1-IETF | Mon 09/01/06 | Fri 09/12/11 | 100% | CP-050529 | - | Keith Drage | - | CP#54 completed | RFC 6442 (was draft-ietf-sipcore-location-conveyance) | 52 | 27 |  |  | Mon 20/06/11 | Tue 13/12/11
5884 | 13028 | Deleted - CT3 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C3 | Mon 08/05/06 | Fri 15/09/06 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.163 |  |  | CP-33 |  | Wed 19/04/00 | Tue 01/07/08
5885 | 13031 | Deleted - CT3 PS domain aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C3 | Mon 08/05/06 | Fri 15/09/06 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.061 |  |  | CP-33 |  | Tue 08/08/00 | Tue 01/07/08
5886 | 1646 | CT1 PS domain aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1 | Mon 09/01/06 | Fri 15/06/07 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.008, 24.234 |  |  |  |  | Tue 08/08/00 | Wed 12/09/07
5887 | 14026 | CT4 PS domain aspects to support IMS Emergency sessions | EMC1-GPRSc4 | 3 | Rel-7 | C4 | Mon 09/01/06 | Fri 01/06/07 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 29.06 |  |  |  |  | Tue 08/08/00 | Tue 29/05/07
5888 | 11065 | IMS Support of Conferencing | IMSconf | 1 | Rel-7 | C1 | Fri 04/11/05 | Thu 15/03/07 | 100% | CP-070120 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#35 revised WID | 24.147, 24.229 |  |  |  |  | Thu 22/12/05 | Tue 01/07/08
5889 | 34033 | Performance Characterization of VoIMS over HSDPA\EUL channels | VoIMS-PCVoIMS | 1 | Rel-7 | S4 | Tue 15/03/05 | Thu 06/12/07 | 100% | SP-050089 | - | Alcatel-Lucent | mcgowan@alcatel-lucent.com | - | 26.935 |  |  |  |  | Mon 21/03/05 | Thu 10/01/08
5890 | 31062 | WLAN-UMTS Interworking Phase 2 | WLAN2 | 1 | Rel-7 | S1,S2 | Mon 05/01/04 | Tue 07/06/05 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | Created at SP#27 because of WLAN items belonging to Rel-7. Acronym changed from "WLAN2, WLAN-SC" | 33.234 (SP-36 SA3 CRs approved) |  |  |  |  | Wed 09/03/05 | Tue 24/03/15
5891 | 31057 | Stage 1 on Session Continuity | WLAN2 | 2 | Rel-7 | S1 | Mon 05/01/04 | Fri 11/06/04 | 100% | - | - | - | - | Acronym changed from "WLAN2, WLAN-SC" | 22.234 |  |  |  |  | Thu 17/06/04 | Tue 24/03/15
5892 | 32096 | Stage 2 on Session Continuity: covered by SAE | WLAN2 | 2 | Rel-7 | S2 | Tue 07/06/05 | Tue 07/06/05 | 100% | - | - | - | - | Acronym changed from "WLAN2, WLAN-SC" | - |  |  |  |  | Tue 07/06/05 | Tue 24/03/15
5893 | 32110 | WLAN Interworking – Private Network access from WLAN 3GPP IP Access | WLANPNA | 1 | Rel-7 | S2,C1,C3,C4 | Mon 10/10/05 | Tue 26/09/06 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | - |  |  |  |  | Fri 28/03/03 | Fri 07/10/05
5894 | 32111 | WLAN-PNA - Stage 2 | WLANPNA-st2 | 2 | Rel-7 | S2 | Mon 10/10/05 | Fri 23/06/06 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Approved at SP#29 | 23.234, 33.234 |  |  |  |  | Tue 20/12/05 | Wed 31/05/06
5895 | 11059 | WLAN-PNA - Stage 3 | WLANPNA-st3 | 2 | Rel-7 | C1,C3,C4 | Wed 01/02/06 | Tue 26/09/06 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | - |  |  |  |  | Tue 22/03/05 | Fri 23/06/06
5896 | 11064 | CT1 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C1 | Wed 01/02/06 | Tue 26/09/06 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 24.234 |  |  |  |  | Thu 22/12/05 | Wed 31/05/06
5897 | 13027 | CT3 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C3 | Wed 01/02/06 | Tue 26/09/06 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 29.161 |  |  |  |  | Thu 22/12/05 | Fri 23/06/06
5898 | 14024 | Deleted - CT4 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C4 | Wed 01/02/06 | Tue 26/09/06 | 100% | CP-060256 | - | NEC | - | CT4#31¦no impacts identified, therefore completed. CP-32 stopped | 29.234 |  |  | CP-32 |  | Thu 22/12/05 | Thu 08/03/07
5899 | 32092 | Enhancements to support QoS provisioning over 3GPP/WLAN Interworking | WLANQOS | 1 | Rel-7 | S2,C4,C1 | Mon 14/03/05 | Fri 09/03/07 | 100% | SP-050682 | - | Samsung | - | Moved from FS section Feb 06. SP-30 updated WID | - |  |  |  |  | Tue 07/06/05 | Fri 18/07/08
5900 | 7015 | Deleted - TR on support of QoS on WLAN | WLANQOS | 2 | Rel-7 | S2 | Mon 14/03/05 | Tue 31/01/06 | 100% | SP-050682 | - | Samsung | - | SP#32 stopped | 23.836 |  |  | SP-32 |  | Thu 16/02/06 | Fri 18/07/08
5901 | 7016 | Stage 2 on support of QoS over 3GPP/WLAN interworking | WLANQOS | 2 | Rel-7 | S2 | Wed 01/02/06 | Fri 30/06/06 | 100% | SP-050682 | - | Samsung | - | SP#30 updated WID | 23.234 |  |  |  |  | Thu 16/02/06 | Fri 18/07/08
5902 | 14028 | Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking | WLANQOS | 2 | Rel-7 | C4 | Fri 22/09/06 | Fri 09/03/07 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 29.234, 23.008 |  |  |  |  | Wed 11/10/06 | Fri 18/07/08
5903 | 340005 | Stage 3 CT1 on support of QoS over 3GPP/WLAN Interworking | WLANQOS | 2 | Rel-7 | C1 | Mon 04/09/06 | Thu 30/11/06 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 24.234 | 34 |  |  |  | Wed 29/11/06 | Fri 18/07/08
5904 | 32079 | Location Services enhancements | LCS3 | 1 | Rel-7 | S1,S2,GP,C4,R2 | Mon 28/06/04 | Mon 17/12/07 | 100% | SP-040682 | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Wed 02/07/08
5905 | 32093 | Stage 2 for LCS3 (including IMS emergency location aspects) | LCS3 | 2 | Rel-7 | S2 | Fri 31/12/04 | Fri 15/09/06 | 100% | SP-050119 | - | SiRF | brodilitz@sirf.com | SP#27 approved WID | 23.271 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
5906 | 50558 | LCS Enhancements related to Location-Based Services | LCS3-LBS | 2 | Rel-7 | GP | Mon 03/01/05 | Fri 31/08/07 | 100% | GP-050265 | - | SiRF | kjudge@sirf.com | - | 43.059, 44.031, 48.008, 49.031 |  |  |  |  | Tue 01/02/05 | Wed 02/07/08
5907 | 14025 | CT4 aspects for LCS UEPos-LBS | LCS3-UEPos-LBS | 2 | Rel-7 | C4 | Mon 02/01/06 | Fri 01/12/06 | 100% | CP-050240 | - | SiRF | brodilitz@sirf.com | - | 24.030, 24.080, 29.002 |  |  |  |  | Mon 20/06/05 | Wed 02/07/08
5908 | 20042 | UE positioning - Velocity | LCS3-UEPos-Velocity | 2 | Rel-7 | R2 | Tue 15/03/05 | Fri 15/09/06 | 100% | RP-050300 | RP-060459 | SiRF | BRodilitz@SiRF.com | - | 25.305, 25.331, 25.410, 25.413, 25.453 |  |  |  |  | Mon 20/06/05 | Wed 02/07/08
5909 | 20012 | Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications | LCS3-UEPos-UTDOA | 2 | Rel-7 | R2 | Wed 15/09/04 | Mon 17/12/07 | 100% | RP-040387 | RP-070797 | TruePosition | Robert Gross (rgross@polariswireless.com) | - | 25.305, 25.453, new 25.111 |  |  |  |  | Mon 27/09/04 | Wed 02/07/08
5910 | 31052 | LCS for 3GPP Interworking WLAN | LCS3-IWLAN | 2 | Rel-7 | S1,S2 | Mon 28/06/04 | Fri 02/03/07 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | - |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
5911 | 32077 | FS on 3GPP system to WLAN Interworking with LCS | LCS3-IWLAN-FSs1 | 3 | Rel-7 | S1 | Mon 28/06/04 | Fri 30/06/06 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | new 22.935 |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
5912 | 32108 | Deleted - Study of work on an LCS architecture for I-WLAN. | LCS3-IWLAN-FSs2 | 3 | Rel-7 | S2 | Mon 26/06/06 | Fri 02/03/07 | 100% | SP-060291 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | SP#41 TR withdrawn. All work transferred to specs | 23.837 |  |  | SP-35 |  | Thu 16/02/06 | Wed 02/07/08
5913 | 340007 | Stage 2 for LCS architecture for I-WLAN | LCS3-IWLAN | 3 | Rel-7 | S2 | Mon 23/10/06 | Fri 02/03/07 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | - | 23.234, 23.271, 23.167 | 34 |  |  |  | Thu 16/02/06 | Mon 15/08/11
5914 | 20030 | Deleted - UE positioning Rel-7 | LCS3-UEpos | 2 | Rel-7 | RP | Wed 15/09/04 | Mon 17/12/07 | 100% | - | - | - | - | - | - |  |  | RP-38 |  | Tue 04/01/05 | Wed 25/06/08
5915 | 31084 | MBMS Enhancements | MBMSE | 1 | Rel-7 | S1,R1,C3 | Mon 11/07/05 | Fri 30/11/07 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | - |  |  |  |  | Mon 20/06/05 | Wed 25/06/08
5916 | 340041 | Stage 1 of MBMSE | MBMSE | 2 | Rel-7 | S1 | Mon 11/07/05 | Thu 08/12/05 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | 22.146, 22.246, 22.228 | 34 |  |  |  | Mon 20/06/05 | Tue 15/04/08
5917 | 340042 | MBMS FDD Physical layer Enhancements | MBMSE-RANPhysFDD | 2 | Rel-7 | R1 | Fri 15/12/06 | Mon 04/06/07 | 100% | RP-070226 | RP-070290 | Ericsson | Lars.Lindbom@ericsson.com | - | 25.211, 25.212, 25.213, 25.101, 25.104, 25.331, 25.433, 25.346, 25.306 | 34 |  |  |  | Mon 21/11/05 | Wed 25/06/08
5918 | 340043 | MBMS TDD Physical layer Enhancements | MBMSE-RANPhysTDD | 2 | Rel-7 | R1 | Fri 15/12/06 | Mon 04/06/07 | 100% | RP-070241 | RP-070291 | IPWireless | Nicholas Anderson | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123 | 34 |  |  |  | Mon 21/11/05 | Wed 25/06/08
5919 | 350022 | MBMS Low Chip Rate TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD | 2 | Rel-7 | R1 | Fri 16/03/07 | Mon 10/09/07 | 100% | RP-070253 | RP-070292 | RITT | Lin Hui | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123 |  |  |  |  | Mon 02/04/07 | Wed 25/06/08
5920 | 340046 | MBMS Mz interface | MBMSMz | 2 | Rel-7 | C3 | Mon 04/12/06 | Fri 30/11/07 | 100% | CP-070109 | - | Huawei | Deng Tingting (ttdeng@huawei.com) | - | 29.061 | 34 |  |  |  | Thu 08/03/07 | Mon 21/07/08
5921 | 400058 | MBMS - UE Conformance Testing | MBMSE_UEConTest | 1 | Rel-7 | R5 | Fri 01/06/07 | Fri 04/12/09 | 100% | - | - | - | - | Linked to Rel-7 Feature UID_31084 (MBMSE) | - | 40 | 21 |  |  | Tue 11/03/08 | Wed 01/04/09
5922 | 25049 | Conformance Test Aspects – MBMS TDD Physical layer Enhancements – MBSFN for HCR and VHCR TDD | MBMSE-RANPhysTDD_UEConTest | 2 | Rel-7 | R5 | Fri 01/06/07 | Fri 12/09/08 | 100% | RP-080155 | RP-080541 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1/2/3 |  |  |  |  | Tue 11/03/08 | Tue 09/09/08
5923 | 400059 | Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD_UEConTest | 2 | Rel-7 | R5 | Fri 30/05/08 | Fri 18/09/09 | 100% | RP-080318 | RP-090715 | CATT | chenxiaozhong@datangmobile.cn | RP#45 completed | 34.108, 34.123-1 | 40 | 21 |  |  | Tue 03/06/08 | Fri 11/09/09
5924 | 400060 | Conformance Test Aspects – MBSFN for FDD | MBMSE-UEConTest_RANPhysFDD | 2 | Rel-7 | R5 | Fri 30/05/08 | Fri 04/12/09 | 100% | RP-080336 | RP-091214 | Huawei | Xiang Li (trica_li@huawei.com) | RP#46 completed | 34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Thu 26/11/09
5925 | 34038 | MBMS User Service Extensions | MBMSUSE | 1 | Rel-7 | S4 | Wed 07/12/05 | Thu 07/06/07 | 100% | SP-050838 | - | Ericsson | Thorsten.Lohmar@ericsson.com | - | 26.346, 26.946 |  |  |  |  | Tue 13/12/05 | Tue 29/05/07
5926 | 31051 | Advanced Global Navigation Satellite System (AGNSS) concept | LCS3-AGNSS | 1 | Rel-7 | S1,S2,GP,R2 | Mon 28/06/04 | Fri 31/08/07 | 100% | SP-040681 | - | Alcatel | Michel.monnerat@thalesaleniaspace.com | - | - |  |  |  |  | Mon 30/08/04 | Wed 25/06/08
5927 | 50551 | Stage 1/2 for Towards AGNSS Concept | AGNSS | 2 | Rel-7 | S1,S2 | Fri 16/02/07 | Fri 16/02/07 | 100% | SP-040681 | - | Alcatel | richard.couty@space.alcatel.fr | - | 22.071, 23.271 |  |  |  |  | Mon 21/05/12 | Mon 21/05/12
5928 | 50548 | Towards AGNSS Concept | AGNSS-GP | 2 | Rel-7 | GP | Mon 28/06/04 | Fri 31/08/07 | 100% | GP-042677 | - | Alcatel | richard.couty@space.alcatel.fr | GP#36 completed | 43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031 |  |  |  |  | Mon 30/08/04 | Mon 21/05/12
5929 | 20050 | Global Navigation Satellite System (GNSS) in UTRAN | LCS3-GNSS-UTRAN | 2 | Rel-7 | R2 | Thu 15/12/05 | Mon 04/06/07 | 100% | RP-060211 | RP-070482 | France Telecom | alain.abinakhoul@francetelecom.com | - | 25.305, 25.331, 25.306, 25.413, 25.423, 25.433, 25.453, 25.302, 25.215, 25.401, 25.402, 25.450, 25.452 |  |  |  |  | Thu 15/12/05 | Wed 25/06/08
5930 | 50581 | A-GPS Minimum Performance | GAGR | 1 | Rel-7 | G1,G3 | Fri 28/04/06 | Fri 31/08/07 | 100% | GP-060834 | - | Spirent | richard.catmur@spirentcom.com | - | 45.005, 51.010 |  |  |  |  | Wed 03/05/06 | Wed 12/09/07
5931 | 31048 | Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM | USSD-USIM | 1 | Rel-7 | S1,C6 | Fri 05/03/04 | Fri 12/08/05 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | - |  |  |  |  | Tue 08/06/04 | Wed 10/09/08
5932 | 31060 | Stage 1 for USSD message delivery and transfer to USIM | USSD-USIM | 2 | Rel-7 | S1 | Thu 18/03/04 | Fri 15/10/04 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 22.09 |  |  |  |  | Tue 08/06/04 | Wed 10/09/08
5933 | 43008 | Alignment with requirements regarding USSD usage | USSD-USIM | 2 | Rel-7 | C6 | Fri 05/03/04 | Fri 12/08/05 | 100% | TP-040069 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 31.111, 31.115, 31.130 |  |  |  |  | Thu 02/09/04 | Thu 01/09/11
5934 | 31063 | Combinational Services | CSICS | 1 | Rel-7 | S1,S2,C1,S4 | Mon 17/01/05 | Mon 06/03/06 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | - |  |  |  |  | Fri 17/12/04 | Wed 02/07/08
5935 | 31064 | Stage 1 for CSICS | CSICS | 2 | Rel-7 | S1 | Mon 17/01/05 | Thu 09/06/05 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 22.279 |  |  |  |  | Mon 28/02/05 | Wed 02/07/08
5936 | 32084 | Stage 2 for CSICS | CSICS | 2 | Rel-7 | S2 | Mon 17/01/05 | Fri 15/07/05 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 23.279 |  |  |  |  | Tue 07/06/05 | Wed 02/07/08
5937 | 11054 | Stage 3 for CSICS CN aspects | CSICS | 2 | Rel-7 | C1 | Mon 02/05/05 | Mon 06/03/06 | 100% | CP-060105 | - | Vodafone | peter.dawes@vodafone.com | - | 24.879, 24.279, 24.229, 24.008 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
5938 | 34031 | Stage 3 for codec aspects | CSICS-Codec | 2 | Rel-7 | S4 | Tue 15/03/05 | Wed 07/12/05 | 100% | SP-050091 | - | Ericsson | Per.Frojdh@ericsson.com | - | 26.141, 26.235 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
5939 | 31065 | CAMEL Trunk Triggers | TTCAMEL | 1 | Rel-7 | S1,C4 | Fri 17/12/04 | Mon 05/12/05 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | - |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
5940 | 31066 | Stage 1 for CAMEL Trunk Triggers | TTCAMEL | 2 | Rel-7 | S1 | Fri 17/12/04 | Mon 05/12/05 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | 22.078 |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
5941 | 14017 | CAMEL Trunk Originated Trigger Detection Points | CamelR7 | 2 | Rel-7 | C4 | Fri 17/12/04 | Mon 05/12/05 | 100% | NP-040550 | - | Nortel | David Hutton (dhutton@nortel.com) | - | - |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
5942 | 31088 | IMS Service Brokering enhancements | ISB | 1 | Rel-7 | S1 | Wed 07/12/05 | Mon 13/03/06 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No CR submitted in rel-8 (according to CR database). | 22.228 |  |  |  |  | Fri 04/11/05 | Tue 25/03/08
5943 | 320027 | Stage 1 for ISB | ISB-s1 | 2 | Rel-7 | S1 | Wed 07/12/05 | Mon 13/03/06 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No Rel-8 changes | 22.228 |  |  |  |  | Fri 04/11/05 | Tue 25/03/08
5944 | 11045 | Enhancements of VGCS for public authority officials | EVGCS | 1 | Rel-7 | S1,C1,C4,G2 | Fri 27/08/04 | Fri 15/06/07 | 100% | SP-040304 | - | - | - | Moved from Rel-6 UID_50563 Enhancements of VGCS in public networks for communication of public authority officials | 43.068, 44.068, 24.008, 29.002 | 75 | 38 |  |  | Fri 03/09/04 | Mon 17/07/06
5945 | 31061 | Stage 1 for Enhancements of VGCS for public authority officials | EVGCS | 2 | Rel-7 | S1 | Fri 27/08/04 | Fri 27/08/04 | 100% | SP-040304 | - | Siemens | joerg.swetina@neclab.eu | Voice Group Call Service | 42.068, 43.068 |  |  |  |  | Mon 30/08/04 | Tue 19/09/06
5946 | 11056 | Architecture and protocol aspects | EVGCS | 2 | Rel-7 | C1,C4 | Fri 27/08/04 | Fri 15/06/07 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068 |  |  |  |  | Wed 14/09/05 | Thu 09/03/06
5947 | 11062 | CT1 aspects of EVGCS | EVGCS | 3 | Rel-7 | C1 | Fri 27/08/04 | Fri 15/06/07 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068, 24.008 |  |  |  |  | Wed 14/09/05 | Wed 12/09/07
5948 | 14022 | CT4 aspects of EVGCS | EVGCS | 3 | Rel-7 | C4 | Fri 27/08/04 | Fri 10/03/06 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 29.002 |  |  |  |  | Wed 14/09/05 | Thu 08/03/07
5949 | 752076 | GERAN2 aspects of EVGCS | EVGCS | 2 | Rel-7 | G2 | Fri 27/08/04 | Fri 16/02/07 | 100% | GP-071855 | - | Siemens | kenneth.isaacs@roke.co.uk | - | - | 75 | 38 |  |  | Fri 15/10/04 | Thu 08/03/07
5950 | 11055 | Improvements of VGCS for parallel use of services | IVGCS | 1 | Rel-7 | S1 | Tue 15/03/05 | Thu 15/03/07 | 100% | SP-070167 | - | - | - | Voice Group Call Service | - |  |  |  |  | Wed 02/03/05 | Mon 26/03/07
5951 | 31070 | Service Requirements for VGCS improvements | IVGCS | 2 | Rel-7 | S1 | Tue 15/03/05 | Wed 08/06/05 | 100% | SP-070167 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 42.068 |  |  |  |  | Tue 22/03/05 | Thu 29/03/07
5952 | 32090 | Stage 2 modifications for VGCS improvements | IVGCS | 2 | Rel-7 | C1 | Thu 01/12/05 | Wed 14/03/07 | 100% | NP-050141 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 43.068 |  |  |  |  | Tue 22/03/05 | Thu 08/03/07
5953 | 11057 | Protocol aspects | IVGCS | 2 | Rel-7 | C1 | Thu 01/12/05 | Thu 15/03/07 | 100% | NP-050141 | - | T-Mobile | Dieter Jacobsohn | Previous name (before CT32) was Architecture and protocol aspects | 44.068 |  |  |  |  | Wed 14/09/05 | Wed 31/05/06
5954 | 11063 | CT1 aspects of IVGCS | IVGCS | 3 | Rel-7 | C1 | Thu 01/12/05 | Thu 15/03/07 | 100% | CP-070118 | - | T-Mobile | - | - | 43.068, 44.068 |  |  |  |  | Wed 14/09/05 | Wed 12/09/07
5955 | 14023 | Deleted - CT4 aspects of IVGCS | IVGCS-St3-c4 | 3 | Rel-7 | C4 | Fri 09/03/07 | Fri 09/03/07 | 100% | NP-050141 | - | T-mobile | - | CT4#33 stage 2 solution is still open. | 29.002 |  |  | CP-35 |  | Wed 14/09/05 | Thu 29/03/07
5956 | 31071 | Open Service Access (OSA) Rel-7 | OSA7 | 1 | Rel-7 | S1,C5 | Tue 15/03/05 | Fri 08/06/07 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | - |  |  |  |  | Tue 22/03/05 | Thu 15/09/05
5957 | 31172 | OSA Service Broker | OSA7-SB | 2 | Rel-7 | S1,C5 | Tue 15/03/05 | Fri 01/12/06 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | - |  |  |  |  | Tue 22/03/05 | Thu 16/02/06
5958 | 31072 | Service Requirements for OSA Service Broker | OSA7 | 3 | Rel-7 | S1 | Tue 15/03/05 | Wed 08/06/05 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | 22.127 |  |  |  |  | Tue 22/03/05 | Thu 16/02/06
5959 | 43011 | Stage 2 OSA API Service Brokering | OSA7 | 3 | Rel-7 | C5 | Fri 28/04/06 | Fri 01/12/06 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 23.198 |  |  |  |  | Tue 22/03/05 | Thu 26/07/12
5960 | 7017 | Stage 3 OSA API Service Brokering | OSA7 | 3 | Rel-7 | C5 | Fri 28/04/06 | Fri 01/12/06 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 29.198-16 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
5961 | 15039 | Rel-7 OSA Stage 2/3 enhancements | OSA7 | 2 | Rel-7 | C5 | Fri 28/04/06 | Fri 08/06/07 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | CP#34 updated WID CP-060607=>CP-070200 | 29.198/9, 23.198 |  |  |  |  | Wed 14/12/05 | Thu 26/07/12
5962 | 7018 | Parlay X Message Broadcast Web Service | OSA7 | 3 | Rel-7 | C5 | Fri 28/04/06 | Fri 01/12/06 | 100% | CP-070200 | - | ETRI | - | - | 29.199-15, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
5963 | 7019 | Parlay X Geocoding Web Service | OSA7 | 3 | Rel-7 | C5 | Fri 28/04/06 | Fri 01/12/06 | 100% | CP-070200 | - | ETRI | - | - | 29.199-16, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
5964 | 7020 | Parlay X Application driven QoS Web Service | OSA7 | 3 | Rel-7 | C5 | Fri 28/04/06 | Fri 09/03/07 | 100% | CP-070200 | - | BT | - | - | 29.199-17, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
5965 | 340001 | Parlay-X Device Capabilities and Configuration | OSA7 | 3 | Rel-7 | C5 | Thu 26/10/06 | Fri 08/06/07 | 100% | CP-070200 | - | Telenor | - | - | 29.199-18, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
5966 | 340002 | Parlay-X Multimedia Streaming Session Management Web Service | OSA7 | 3 | Rel-7 | C5 | Thu 26/10/06 | Fri 09/03/07 | 100% | CP-070200 | - | Telenor | - | - | 29.199-19, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
5967 | 340003 | Parlay-X Multimedia Multicast Control Web Service | OSA7 | 3 | Rel-7 | C5 | Thu 26/10/06 | Fri 09/03/07 | 100% | CP-070200 | - | ETRI | - | - | 29.199-20, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
5968 | 340004 | OSA API Conference Call Control SCF | OSA7 | 3 | Rel-7 | C5 | Thu 26/10/06 | Fri 09/03/07 | 100% | CP-070200 | - | Ericsson | - | - | 29.198-04-5, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
5969 | 31053 | Selective Disabling of UE Capabilities | SDoUE | 1 | Rel-7 | S1,S2,C1 | Mon 24/01/05 | Fri 15/06/07 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | - |  |  |  |  | Mon 30/08/04 | Thu 17/07/08
5970 | 32088 | Stage 1 of SDoUE | SDoUE-CR | 2 | Rel-7 | S1 | Mon 24/01/05 | Fri 08/12/06 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | 22.011 |  |  |  |  | Mon 30/08/04 | Thu 17/07/08
5971 | 32089 | Deleted - TR on different possible architectures | SDoUE-FS | 2 | Rel-7 | S2 | Mon 21/03/05 | Fri 16/12/05 | 100% | SP-050182 | - | Vodafone | Gavin.Wong@vodafone.com | Moved from FS section Feb 06. Abandoned at SP-30 | 23.805 abandonned at SP-30; descendant C1 24.305 |  |  | SP-30 |  | Tue 07/06/05 | Thu 17/07/08
5972 | 7036 | Stage 3 of SDoUE | SDoUE | 2 | Rel-7 | C1 | Fri 10/03/06 | Fri 15/06/07 | 100% | CP-070121 | - | Ericsson | christian.herrero@ericsson.com | - | 24.305 |  |  |  |  | Wed 22/03/06 | Thu 17/07/08
5973 | 7041 | Network selection enhancements (NSP) | NSP | 1 | Rel-7 | S1 | Wed 15/03/06 | Fri 15/06/07 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | - |  |  |  |  | Fri 04/11/05 | Wed 22/03/06
5974 | 320012 | Stage 1 of NSP | NSP-TS | 2 | Rel-7 | S1 | Wed 15/03/06 | Wed 06/12/06 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | 22.101, 22.011, 23.122, 24.008, 25.304, 31.102, 45.008 |  |  |  |  | Mon 17/07/06 | Tue 15/04/08
5975 | 320013 | Procedural aspects of NSP | NSP-CR | 2 | Rel-7 | C1 | Fri 02/06/06 | Fri 15/06/07 | 100% | CP-060357 | - | Motorola | Andrew Howell | - | 23.122, 24.008, 31.102 |  |  |  |  | Wed 21/06/06 | Fri 04/05/07
5976 | 25048 | Network selection enhancements (NSP) - UE Conformance Testing | NSP-CR_UEConTest | 1 | Rel-7 | R5 | Fri 01/06/07 | Fri 05/12/08 | 100% | RP-080135 | RP-080819 | Nokia | jarkko.hellsten@nokia.com | RP#42 completed. Testing for Feature UID_7041 (NSP-CR) | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Tue 09/12/08
5977 | 32064 | Access Class Barring and Overload Protection | ACBOP | 1 | Rel-7 | S2,C1 | Mon 15/03/04 | Fri 08/09/06 | 100% | SP-040338 | - | Vodafone | chris.pudney@vodafone.com | - | 23.898 |  |  |  |  | Wed 14/04/04 | Tue 15/07/08
5978 | 32065 | TR on Stage 2 | ACBOP | 2 | Rel-7 | S2 | Mon 15/03/04 | Thu 31/03/05 | 100% | SP-040338 | - | NTT DoCoMo | Jean-Jacques Davidian (davidian@docomo.fr) | - | 23.898 |  |  |  |  | Wed 14/04/04 | Tue 15/07/08
5979 | 11048 | Stage 3 CN aspects of ACBOP | ACBOP | 2 | Rel-7 | C1 | Mon 06/06/05 | Tue 31/01/06 | 100% | - | - | - | - | - | 24.008 |  |  |  |  | Thu 02/09/04 | Tue 15/07/08
5980 | 20010 | Deleted - Potential impact on Iu interface Overload functionality | ACBOP | 2 | Rel-7 | RP | Mon 15/03/04 | Mon 15/03/04 | 100% | - | - | - | - | - | 25.413 |  |  | RP-25 |  | Wed 14/04/04 | Wed 13/10/04
5981 | 20009 | Deleted - Extra ACBOP information in RAN | ACBOP | 2 | Rel-7 | RP | Mon 15/03/04 | Mon 15/03/04 | 100% | - | - | - | - | - | 25.331 |  |  | RP-25 |  | Wed 14/04/04 | Wed 13/10/04
5982 | 50117 | Deleted - Extra ACBOP information in GERAN | ACBOP | 2 | Rel-7 | GP | Fri 08/09/06 | Fri 08/09/06 | 100% | - | - | - | - | - | 44.018 |  |  | RP-33 |  | Wed 14/04/04 | Thu 20/07/06
5983 | 32074 | System enhancements for Fixed Broadband access to IMS | FBI | 1 | Rel-7 | S2,S3,S5,C1,C3,C4,IETF | Wed 05/11/03 | Fri 09/12/11 | 100% | SP-060145 | - | - | - | - | - |  |  |  |  | Mon 09/06/03 | Thu 21/10/04
5984 | 7001 | TISPAN Rel 1 related aspects | FBI-TIS1 | 2 | Rel-7 | S2,S3,C1,C3,C4,IETF | Wed 05/11/03 | Fri 09/12/11 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Thu 16/02/06
5985 | 32075 | Stage 2 of FBI for TISPAN R1 | - | 3 | Rel-7 | S2 | Thu 14/10/04 | Wed 08/03/06 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Wed 31/05/06
5986 | 11050 | Protocol impact of FBI for TISPAN R1 | - | 3 | Rel-7 | S3,C1,C3,C4,IETF | Wed 05/11/03 | Fri 09/12/11 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | - |  |  |  |  | Fri 03/09/04 | Thu 16/02/06
5987 | 521031 | (IETF) CT aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1-IETF,C3-IETF | Wed 05/11/03 | Fri 09/12/11 | 100% | NP-040618 | - | Roland Jesske | - | CP#54 completed | RFC 6432 (was draft-jesske-dispatch-update3326-reason-responses) | 52 | 27 |  |  | Mon 20/06/11 | Tue 13/12/11
5988 | 11060 | CT1 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1 | Wed 05/11/03 | Thu 30/11/06 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 24.819, 24.229 |  |  |  |  | Fri 03/09/04 | Fri 05/01/07
5989 | 13025 | CT3 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C3 | Wed 05/11/03 | Fri 08/12/06 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 29.163, 29.209 |  |  |  |  | Fri 03/09/04 | Thu 12/10/06
5990 | 14020 | CT4 aspects of FBI for TISPAN R1 | FBI-TIS1-st3-c4 | 4 | Rel-7 | C4 | Fri 13/01/06 | Fri 09/03/07 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | CT4#32: a set of CRs on FBI for cable labs | 29.229 |  |  |  |  | Fri 03/09/04 | Thu 08/03/07
5991 | 33027 | Security Enhancements for FBI | FBI-ISE | 3 | Rel-7 | S3 | Tue 28/06/05 | Thu 08/12/05 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | Duplicated entry ("ACCSEC2", "Access Security Enhancements", SP-040865) deleted by A.Sultan | 33.203 |  |  |  |  | Mon 20/06/05 | Tue 29/05/07
5992 | 7002 | PacketCable Related aspects | FBI-PCBL | 2 | Rel-7 | S2,S5,C1 | Wed 01/02/06 | Wed 14/03/07 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | - |  |  |  |  | Thu 16/02/06 | Thu 16/02/06
5993 | 7003 | Stage 1,2 of FBI for PacketCable | - | 3 | Rel-7 | S2 | Wed 01/02/06 | Fri 15/12/06 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | 22.228, 23.228 |  |  |  |  | Thu 16/02/06 | Tue 19/09/06
5994 | 7004 | Protocol impact of FBI for PacketCable | - | 3 | Rel-7 | C1 | Mon 01/05/06 | Wed 14/03/07 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Thu 08/03/07
5995 | 7032 | SA5 Charging aspects of FBI for PacketCable | FBI-PCBL-CH | 3 | Rel-7 | S5 | Fri 31/03/06 | Thu 07/12/06 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | 03/2006 SP#31 WID approved | 32.240, 32.260, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Thu 29/03/07
5996 | 32081 | Support of SMS over generic 3GPP IP access | SMSIP | 1 | Rel-7 | S2,C4,C1 | Thu 14/10/04 | Thu 14/06/07 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID (removed MMS) | - |  |  |  |  | Thu 14/10/04 | Fri 18/07/08
5997 | 32094 | FS on SMSIP | - | 2 | Rel-7 | S2 | Thu 14/10/04 | Mon 13/06/05 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.804 |  |  |  |  | Tue 07/06/05 | Tue 15/07/08
5998 | 32095 | Stage 2 for SMSIP | - | 2 | Rel-7 | S2 | Wed 08/06/05 | Fri 15/09/06 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.204 |  |  |  |  | Tue 07/06/05 | Tue 15/07/08
5999 | 310001 | Stage 3 for SMSIP | SMSIP-St3 | 2 | Rel-7 | C4,C1 | Wed 08/06/05 | Thu 14/06/07 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | - |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
6000 | 310002 | CT1 aspects for SMSIP | - | 3 | Rel-7 | C1 | Wed 08/06/05 | Thu 14/06/07 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.040, 24.229 |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
6001 | 310003 | CT4 aspects for SMSIP | SMSIP-St3-c4 | 3 | Rel-7 | C4 | Wed 08/06/05 | Fri 01/06/07 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.008, 29.002 |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
6002 | 32082 | Evolution of Policy Control and Charging | PCC | 1 | Rel-7 | S2,S5,C3,C1 | Thu 14/10/04 | Fri 30/11/07 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID adding SA5 charging. 23.125 will be discontinued from Rel-7. | - |  |  |  |  | Thu 14/10/04 | Fri 18/07/08
6003 | 32102 | Deleted - TR for PCC | - | 2 | Rel-7 | S2 | Thu 14/10/04 | Thu 29/12/05 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-30: S2 has no intention for TR completion | 23.803 |  |  | SP-33 |  | Fri 01/07/05 | Fri 18/07/08
6004 | 32103 | Stage 2 for PCC | - | 2 | Rel-7 | S2 | Mon 04/07/05 | Fri 15/09/06 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.203 |  |  |  |  | Fri 01/07/05 | Fri 18/07/08
6005 | 32109 | Evolution of policy control and flow based bearer level charging | - | 2 | Rel-7 | S2 | Tue 01/08/06 | Fri 29/12/06 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.207, 23.002, 23.228 |  |  |  |  | Fri 01/07/05 | Fri 18/07/08
6006 | 7033 | SA5 Charging aspects of PCC | PCC-CH | 2 | Rel-7 | S5 | Fri 31/03/06 | Fri 15/06/07 | 100% | SP-060217 | - | Orange | alain.bibas@orange-ft.com | SP-31 updated WID with SA5 charging. | 32.250, 32.251, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Fri 18/07/08
6007 | 13029 | Gx reference point for Policy and Charging Control | PCC-Gx | 2 | Rel-7 | C3 | Fri 02/12/05 | Fri 30/11/07 | 100% | CP-060434 | - | Siemens | Thomas.Belling@nsn.com | - | 29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208) |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
6008 | 13030 | Rx reference point for PCC CT3 aspects | PCC-Rx | 2 | Rel-7 | C3,C1 | Fri 02/12/05 | Fri 30/11/07 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | WID approved at CP#30, Revised at CP#31, Revised at CP#33 | - |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
6009 | 310006 | PCC-Rx CT3 aspects | PCC-Rx-c3 | 3 | Rel-7 | C3 | Fri 02/12/05 | Fri 30/11/07 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 29.213, 29.214 (not progressed to Rel-7: 29.209, 29.211) |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
6010 | 7008 | PCC-Rx CT1 aspects | PCC-Rx-Gx-c1 | 3 | Rel-7 | C1 | Fri 02/12/05 | Fri 15/06/07 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 24.229 |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
6011 | 32091 | Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC | 1 | Rel-7 | S2,S1,S5,C1,C4 | Fri 31/12/04 | Fri 15/06/07 | 100% | SP-060292 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | WID approved SP#27¦updated SP#28¦updated SP#32 | - |  |  |  |  | Tue 07/06/05 | Mon 21/07/08
6012 | 32104 | TR for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | Fri 31/12/04 | Thu 08/12/05 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.806 |  |  |  |  | Fri 01/07/05 | Mon 21/07/08
6013 | 31085 | Stage 1 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S1 | Thu 17/03/05 | Wed 28/09/05 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 22.101 |  |  |  |  | Mon 19/09/05 | Mon 21/07/08
6014 | 32105 | Stage 2 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | Tue 06/09/05 | Fri 08/09/06 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.206 |  |  |  |  | Fri 01/07/05 | Mon 21/07/08
6015 | 35079 | SA5 Charging for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-CH | 2 | Rel-7 | S5 | Fri 17/03/06 | Thu 14/06/07 | 100% | SP-060292 | - | Orange | alain.bibas@orange-ft.com | 03/2006 SP#31 WID approved | 32.250, 32.260 |  |  |  |  | Mon 20/03/06 | Mon 21/07/08
6016 | 11058 | Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | C1,C4 | Wed 01/02/06 | Fri 15/06/07 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
6017 | 11066 | CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C1 | Wed 01/02/06 | Fri 15/06/07 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 24.206, 24.216 |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
6018 | 14027 | CT4 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-St3-c4 | 3 | Rel-7 | C4 | Fri 09/06/06 | Fri 09/03/07 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 23.003 |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
6019 | 13032 | Deleted - CT3 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C3 | Thu 02/11/06 | Thu 02/11/06 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.163 |  |  | CP-33 |  | Tue 04/10/05 | Mon 21/07/08
6020 | 7046 | One Tunnel solution for optimization of Packet Data Traffic | OPTUNEL | 1 | Rel-7 | S2 | Mon 27/03/06 | Wed 31/10/07 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | - |  |  |  |  | Wed 22/03/06 | Tue 15/07/08
6021 | 320002 | Deleted - Study on Stage 2 for One Tunnel solution | OPTUNEL-Study | 2 | Rel-7 | S2 | Mon 27/03/06 | Fri 15/09/06 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | TR for Info SP-33. SP-34: S2 Report intention to discontinue TR | 23.809 |  |  | SP-34 |  | Mon 30/08/04 | Tue 15/07/08
6022 | 340013 | One Tunnel Deployment Guideline | OPTUNEL-Guide | 2 | Rel-7 | S2 | Mon 23/10/06 | Wed 31/10/07 | 100% | SP-060819 | - | Huawei | lan.liu@huawei.com | - | 23.919 | 34 |  |  |  | Mon 30/08/04 | Tue 15/07/08
6023 | 320003 | Stage 2 specification for One Tunnel solution | OPTUNEL-Stage2 | 2 | Rel-7 | S2 | Mon 11/09/06 | Fri 15/12/06 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | 23.06 |  |  |  |  | Mon 30/08/04 | Tue 15/07/08
6024 | 320029 | CSI Terminating Session handling | CSItermS | 1 | Rel-7 | S2,C1 | Thu 08/06/06 | Fri 15/06/07 | 100% | SP-060437 | - | Samsung | Osok Song | Triggered by the abandoned Study UID_32117 | - |  |  |  |  | Wed 19/07/06 | Thu 17/07/08
6025 | 340014 | Stage 2 of CStermS | - | 2 | Rel-7 | S2 | Thu 08/06/06 | Fri 02/03/07 | 100% | SP-060437 | - | Samsung | Osok Song | - | 23.279 | 34 |  |  |  | Fri 05/01/07 | Thu 17/07/08
6026 | 340015 | Stage 3 of CStermS | - | 2 | Rel-7 | C1 | Thu 14/12/06 | Fri 15/06/07 | 100% | CP-070239 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID. CP-35 updated WID | 24.229, 24.279 | 34 |  |  |  | Fri 05/01/07 | Thu 17/07/08
6027 | 340011 | Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling | - | 2 | Rel-7 | C1 | Fri 09/03/07 | Fri 09/03/07 | 100% | CP-060647 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID | 24.229, 24.179, 24.279 | 34 |  | CP-34 |  | Mon 18/12/06 | Thu 17/07/08
6028 | 33022 | Liberty Alliance and 3GPP Security Interworking | LibSec | 1 | Rel-7 | S3 | Thu 10/03/05 | Thu 30/11/06 | 100% | SP-050145 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#27. | 33.98 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
6029 | 33023 | Trust Requirements for Open Platforms in 3GPP | TrustOP | 1 | Rel-7 | S3 | Mon 03/01/05 | Thu 30/11/06 | 100% | SP-040863 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#26. | 33.905 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
6030 | 33024 | Development of UEA2 and UIA2 | AlgUEA2 | 1 | Rel-7 | S3 | Wed 01/12/04 | Fri 09/12/05 | 100% | SP-040864 | - | TeliaSonera | per.christoffersson@teliasonera.com | WID approved SP#26, Dependant on Funding Availability. | 35.919, 35.215, 35.216, 35.217, 35.218 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
6031 | 33026 | Lawful Interception in the 3GPP Rel-7 architecture | LI-7A | 1 | Rel-7 | S3 | Tue 28/06/05 | Thu 08/12/05 | 100% | SP-050237 | - | BMWI | berthold.wilhelm@regtp.de | - | 33.106, 33.107, 33.108 |  |  |  |  | Mon 20/06/05 | Wed 16/07/08
6032 | 33028 | Key establishment between a UICC and a terminal | KeyEstUTerm | 1 | Rel-7 | S3 | Wed 07/12/05 | Thu 28/09/06 | 100% | SP-050780 | - | Gemalto | mireille.pauliac@gemplus.com | - | 33.11 |  |  |  |  | Mon 12/12/05 | Thu 10/01/08
6033 | 330008 | NDS Authentication Framework Extension for Transport Layer Security | NDSAFTLS | 1 | Rel-7 | S3 | Thu 28/09/06 | Wed 06/12/06 | 100% | SP-060507 | - | Nokia | tiina.s.koskinen@nokia.com | TLS profile is moved to Rel-8 | 33.31 |  |  |  |  | Fri 06/10/06 | Wed 16/07/08
6034 | 732030 | Security enhancements | SEC7 | 1 | Rel-7 | S3,C1,C4 | Mon 12/09/05 | Thu 30/11/06 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6035 | 732031 | HTTPS connection between a UICC and a NAF | SEC7-HSUN | 2 | Rel-7 | S3,C1 | Mon 12/09/05 | Mon 12/09/05 | 100% | SP-050573 | - | Gemalto | JSeif@axalto.com, mireille.pauliac@gemplus.com | - | 33.918, 33.222, 24.109 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6036 | 732032 | 2G GBA: 2G SIM usage in 3GPP GAA framework | SEC7-2GGBA | 2 | Rel-7 | S3 | Mon 12/09/05 | Mon 05/12/05 | 100% | SP-050576 | - | Nokia | Silke.Holtmanns@nokia.com | - | 33.920, 33.220 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6037 | 732033 | Generic Authentication Architecture usage extensions and optimizations | SEC7-GAA2 | 2 | Rel-7 | S3 | Mon 12/09/05 | Thu 30/11/06 | 100% | SP-060429 | - | Nokia | Silke.Holtmanns@nokia.com | 33.223 goes to R8 | 33.220, 29.109, 24.109, (33.223 goes to R8) |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6038 | 32034 | SS7 TCAP security Gateway | SEC7-NDS-TCAPsec | 2 | Rel-7 | S3,C4 | Mon 12/09/05 | Mon 14/08/06 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | - |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6039 | 310004 | SA3 aspects of SEC7-NDS-TCAPsec | SEC7-NDS-TCAPsec-SA3 | 3 | Rel-7 | S3 | Mon 12/09/05 | Fri 10/03/06 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | 33.204 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
6040 | 310005 | TCAPsec Gateway | SEC7-TCAP | 3 | Rel-7 | C4 | Mon 03/04/06 | Mon 14/08/06 | 100% | CP-060170 | - | Siemens | Ulrich.wiehe@gksag.de | - | 29.204, 29.002 |  |  |  |  | Fri 07/10/05 | Wed 16/07/08
6041 | 711052 | IMS Stage 3 IETF Protocol Alignment | IMSProtoc | 1 | Rel-7 | C1 | Fri 10/12/04 | Wed 14/03/07 | 100% | CP-060101 | - | - | - | TR 24.930: Signalling flows for the session setup in the IM CN subsystem based on Session Initiation Protocol (SIP) | 24.93 | 71 | 36 |  |  | Wed 05/01/05 | Tue 29/05/07
6042 | 7043 | Interoperability between VGCS/VBS and A/Gb flexibility | VGCSFlex | 1 | Rel-7 | C1,C4 | Wed 22/03/06 | Fri 09/03/07 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | Voice Group Call Service | - |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
6043 | 7044 | CT1 aspects of VGCSFlex | - | 2 | Rel-7 | C1 | Wed 22/03/06 | Mon 30/10/06 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 43.069 |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
6044 | 7045 | CT4 aspects of VGCSFlex | VGCSFlex-c4 | 2 | Rel-7 | C4 | Wed 22/03/06 | Fri 09/03/07 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 29.002 |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
6045 | 13023 | DIAMETER on the GGSN Gi interface | DIAMGi | 1 | Rel-7 | C3 | Fri 10/09/04 | Fri 08/12/06 | 100% | CP-060431 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.061 |  |  |  |  | Tue 18/01/05 | Tue 15/07/08
6046 | 13022 | DIAMETER on the PDG Wi interface | DIAMWi | 1 | Rel-7 | C3 | Fri 10/09/04 | Fri 08/12/06 | 100% | CP-060432 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.161 |  |  |  |  | Tue 18/01/05 | Tue 15/07/08
6047 | 13033 | Interworking between the 3GPP CS domain with BICC or ISUP as signalling protocol and external SIP-I networks | ExtSIPI | 1 | Rel-7 | C3 | Fri 22/09/06 | Tue 22/07/08 | 100% | CP-070101 | - | Siemens | Thomas.Belling@nsn.com | - | 29.164 |  |  |  |  | Fri 06/10/06 | Thu 17/04/08
6048 | 340047 | PDU multiplexing at Nb Interface with IP transport | NbIPMux | 1 | Rel-7 | C3 | Mon 04/12/06 | Tue 22/07/08 | 100% | CP-070105 | - | Alcatel-Lucent | Jean.Rzeznik@alcatel-lucent.fr | - | 29.414 | 34 |  |  |  | Thu 08/03/07 | Fri 04/05/07
6049 | 14012 | Mp (MRFC - MRFP) interface | Mp | 1 | Rel-7 | C4,C1 | Mon 13/02/06 | Fri 08/06/07 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | - |  |  |  |  | Mon 13/01/03 | Tue 15/07/08
6050 | 11061 | CT1 aspects of Mp | - | 2 | Rel-7 | C1 | Mon 13/02/06 | Mon 13/02/06 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 24.229 |  |  |  |  | Mon 13/01/03 | Tue 15/07/08
6051 | 13026 | Deleted - CT3 aspects of Mp | - | 2 | Rel-7 | C3 | Fri 22/09/06 | Fri 22/09/06 | 100% | - | - | Ericsson | philip.hodges@ericsson.com | CP#34: CT3 not involved in Mp interface definition | 29.162 |  |  | CP-33 |  | Mon 13/01/03 | Tue 15/07/08
6052 | 320009 | Procedures description | Mp-PROCc4 | 2 | Rel-7 | C4 | Fri 02/06/06 | Fri 09/03/07 | 100% | CP-070246 | - | Huawei | Chencheng@huawei.com | - | 23.333 |  |  |  |  | Wed 21/06/06 | Tue 15/07/08
6053 | 14021 | Stage 3 for Mp (MRFC - MRFP) interface | Mp-St3c4 | 2 | Rel-7 | C4 | Mon 13/02/06 | Fri 08/06/07 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 29.333 |  |  |  |  | Mon 13/01/03 | Tue 15/07/08
6054 | 340016 | Routeing of MT-SMS via the HPLMN | SMSviaH | 1 | Rel-7 | C4,C1 | Fri 01/12/06 | Fri 09/03/07 | 100% | CP-070032 | - | Vodafone | Nick.Russell@vodafone.com | WID approved in CP#34 | 23.040, 29.002 | 34 |  |  |  | Fri 07/10/05 | Wed 12/09/07
6055 | 350003 | Mobile Termination whilst the MS is moving to another MSC | MTmovMS | 1 | Rel-7 | C4 | Fri 09/03/07 | Thu 31/05/07 | 100% | CP-070334 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | - | 23.008, 23.012, 23.018, 23.078, 23.079, 29.002 |  |  |  |  | Thu 29/03/07 | Tue 29/05/07
6056 | 743009 | ISIM API for Java Card | APIJAVA | 1 | Rel-7 | C6 | Mon 14/03/05 | Fri 27/07/07 | 100% | CP-050145 | - | Sun | Sebastian Hans | - | 31.103, 102 241 | 74 | 38 |  |  | Fri 04/11/05 | Wed 12/09/07
6057 | 440042 | Rel-7 (U)SIM API Testing (TS 31.213) | USIM_API_Test | 1 | Rel-7 | C6 | Sat 30/05/09 | Fri 19/03/10 | 100% | CP-090450 | - | Sagem Orga | gerrit.hartbrod@sagem-orga.com | CP#47 completed. Update of Rel-6 (U)SIM API for Java Card Testing UID_43007 under Rel-6 UICC/USIM enhancements and interworking UID_1800 | 31.213 | 44 | 23 |  |  | Fri 29/05/09 | Tue 09/03/10
6058 | 330001 | High speed interface between the UICC and the ME | HSI | 1 | Rel-7 | C6 | Fri 22/09/06 | Fri 30/11/07 | 100% | CP-070259 | - | Gemalto | jacques.seif@GEMALTO.COM | Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45 | 31.101 |  |  |  |  | Thu 21/09/06 | Fri 11/01/08
6059 | 34030 | Video Codec Performance Requirements | VICPer | 1 | Rel-7 | S4 | Mon 03/01/05 | Thu 07/06/07 | 100% | SP-040836 | - | Siemens | juergen.pandel@siemens.com | - | 26.234, 26.235, 26.346, 26.140, 26.902 |  |  |  |  | Thu 13/01/05 | Tue 29/05/07
6060 | 34032 | Dynamic and Interactive Multimedia Scenes | DIMS | 1 | Rel-7 | S4 | Tue 15/03/05 | Thu 07/06/07 | 100% | SP-050195 | - | Streamezzo | gaelle.martin-cocher@streamezzo.com | - | 26.140, 26.142, 26.234, 26.244, 23.346 |  |  |  |  | Mon 21/03/05 | Tue 29/05/07
6061 | 34034 | 3G-324M Video Telephony Call Setup Times Improvements | VTCSTI | 1 | Rel-7 | S4 | Wed 08/06/05 | Wed 27/09/06 | 100% | SP-050404 | - | Vodafone | edward.hall@vodafone.co.uk | - | 26.911 |  |  |  |  | Thu 16/06/05 | Wed 29/11/06
6062 | 34035 | Optimizations for Multimedia Telephony over IMS | OMTIMS | 1 | Rel-7 | S4 | Wed 28/09/05 | Thu 29/09/05 | 100% | SP-060226 | - | Ericsson | olle.franceschi@ericsson.com | Aug2015: 99%->100 | 26.235, 26.236 |  |  |  |  | Tue 04/10/05 | Wed 12/08/15
6063 | 34037 | Deleted - Characterisation of Adaptive Jitter Management Performance for VoIP Services | OMTIMS-CAJMP | 2 | Rel-7 | S4 | Wed 28/09/05 | Thu 29/09/05 | 100% | SP-050432 | - | Lucent | dhuo@lucent.com | SP-35 stopped | - |  |  | SP-35 |  | Tue 04/10/05 | Thu 29/03/07
6064 | 34036 | End-to-End Multimedia Services Performance Metrics | E2EMSPM | 1 | Rel-7 | S4 | Wed 28/09/05 | Thu 15/03/07 | 100% | SP-050433 | - | China Mobile | zhangyanyf@chinamobile.com | - | 26.944 |  |  |  |  | Tue 04/10/05 | Thu 08/03/07
6065 | 34039 | Packet Switched Streaming Enhancements | PSSe | 1 | Rel-7 | S4 | Thu 08/06/06 | Thu 07/06/07 | 100% | SP-060361 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.234, 26.244 |  |  |  |  | Tue 24/01/06 | Tue 29/05/07
6066 | 35041 | Rel-7 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM7 | 1 | Rel-7 | S5 | Fri 02/09/05 | Fri 15/06/07 | 100% | - | - | Huawei | Christian.Toche@huawei.com | OAM7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | 30.817 |  |  |  |  | Wed 09/03/05 | Thu 29/03/07
6067 | 35042 | Rel-7 Network Infrastructure Management | OAM7-NIM | 2 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6068 | 35044 | Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network) | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050302 | - | Motorola | - | - | 32.731/2/3/5, 32.631/2/3/5 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6069 | 35046 | Co-operative Element Management interface (CO-OP) (Study + Implementation) | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050304 | - | Motorola | - | - | 32.806, 32.814, 32.101 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6070 | 35047 | Network Management (NM) Itf-N performance criteria | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050305 | - | China Mobile | - | - | 32.811 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
6071 | 35048 | Delta synchronization between IRP Manager and IRP Agent (Study + Implementation) | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050306 | - | Siemens | - | - | 32.391/2/3/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
6072 | 35049 | Subscription Management (SuM) IRP Solution Sets | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 07/12/06 | 100% | SP-060739 | - | Ericsson | - | - | 32.307/317/607/667/665, 32.101, 32.175 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6073 | 35050 | Integration Reference Point (IRP) Security Management | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050308 | - | Huawei | Christian.Toche@huawei.com | - | 32.372/3/5, 32.111,32.30x,32.32x,32.33x,32.34x,32.35x,32.36x,32.41x,32.60x,32.61x,32.66x |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6074 | 35052 | Partial suspension of Itf-N during maintenance/testing (Study + Implementation) | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050310 | - | Siemens | - | - | 32.381/2/3/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
6075 | 35054 | Deleted - Management of Legacy Equipment | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Fri 15/12/06 | 100% | SP-050312 | - | Siemens | - | Request to TSG#35 to STOP the WI | new 32.xxx |  |  | SP-35 |  | Fri 17/06/05 | Thu 29/03/07
6076 | 35055 | Deleted - Rules for Vendor Specific Extensions | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050313 | - | Siemens | - | Request to TSG#35 to STOP the WI | 32.62n; For n = 1 to 5 |  |  | SP-35 |  | Fri 17/06/05 | Thu 29/03/07
6077 | 35064 | Backward and Forward Compatibility of IRP systems | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050630 | - | Ericsson | - | - | 32.154 |  |  |  |  | Fri 16/09/05 | Fri 22/06/07
6078 | 35071 | Repeater Network Resource Model (NRM) definition | - | 3 | Rel-7 | S5 | Mon 13/02/06 | Thu 07/12/06 | 100% | SP-050731 | - | China Mobile | - | - | 32.721/2/3/5 |  |  |  |  | Thu 24/11/05 | Thu 29/03/07
6079 | 35072 | UTRAN radio channel power monitoring | - | 3 | Rel-7 | S5 | Mon 13/02/06 | Thu 15/03/07 | 100% | SP-050733 | - | China Mobile | - | - | 32.405, 32.64n; For n = 1 to 5 |  |  |  |  | Thu 24/11/05 | Thu 29/03/07
6080 | 340009 | Notification XML Schema | - | 3 | Rel-7 | S5 | Thu 07/12/06 | Thu 15/03/07 | 100% | SP-060754 | - | Huawei | Christian.Toche@huawei.com | 12/2006 SP#34 WID approved | New 32.325/345/365/415, CR to 32.335/615/665 |  |  |  |  | Fri 15/12/06 | Thu 29/03/07
6081 | 35043 | Rel-7 Performance Management | OAM7-PM | 2 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6082 | 35057 | Performance measurements definition for CN CS | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050315 | - | China Mobile | - | - | 32.407, 32.408 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6083 | 35058 | Enhancement UTRAN performance measurements definition | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050316 | - | China Mobile | - | - | 32.405 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
6084 | 35059 | Add TDD specific counters in Performance measurement | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 07/12/06 | 100% | SP-050317 | - | CATT | - | - | 32.405 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6085 | 35060 | ATM bearer network Performance measurements | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050318 | - | ZTE | - | - | No impact on 32.404, 32.405, 32.406, 32.407 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
6086 | 35069 | Performance measurements definition for IMS | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050631 | - | China Mobile | - | - | 32.404,32.409,32.437, 32.632/3/4/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
6087 | 35073 | HSDPA performance measurements | - | 3 | Rel-7 | S5 | Mon 13/02/06 | Thu 14/06/07 | 100% | SP-060379 | - | China Mobile | - | - | 32.405 |  |  |  |  | Thu 24/11/05 | Fri 22/06/07
6088 | 35039 | Rel-7 Trace Management | OAM7-Trace | 2 | Rel-7 | S5 | Fri 02/09/05 | Fri 15/06/07 | 100% | SP-050628 | - | Vodafone | - | - | - |  |  |  |  | Fri 08/11/02 | Thu 29/03/07
6089 | 35040 | End-to-end Service Level tracing for IMS | - | 3 | Rel-7 | S5 | Fri 11/11/05 | Thu 15/03/07 | 100% | SP-050627 | - | Vodafone | - | 07/2005: OMA (Stage 1), Stage 2/3 SA5, CT1/3/4 | 32.101, 32.421, 32.422, 32.423 |  |  | SP-31 |  | Wed 02/03/05 | Thu 29/03/07
6090 | 35062 | Trace record content for UTRAN TDD | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 07/12/06 | 100% | SP-050628 | - | Nokia | - | - | 32.421, 32.422, 32.423 |  |  |  |  | Wed 02/03/05 | Thu 29/03/07
6091 | 35063 | IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Thu 14/06/07 | 100% | SP-050629 | - | Nokia | - | - | 32.441, 32.442, 32.443, 32.445, 32.632, 32.633, 32.635 |  |  |  |  | Wed 02/03/05 | Fri 22/06/07
6092 | 11046 | Deleted - SIP enhancements for trace | - | 3 | Rel-7 | C1 | Fri 15/06/07 | Fri 15/06/07 | 100% | - | - | - | - | combined with UID 11067 | - |  |  | CP-32 |  | Mon 01/03/04 | Wed 29/11/06
6093 | 35070 | Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | Fri 02/09/05 | Fri 15/12/06 | 100% | SP-050629 | - | Nokia | - | - | 32.421,32.422,32.423. 3 new 32.4x1,2,3 |  |  | SP-33 |  | Wed 02/03/05 | Thu 29/03/07
6094 | 320007 | Rel-7 Charging Management small Enhancements | CH7 | 1 | Rel-7 | S5 | Mon 22/05/06 | Thu 14/06/07 | 100% | - | - | Orange | alain.bibas@orange-ft.com | CH7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | 30.817 |  |  |  |  | Mon 22/05/06 | Mon 09/03/09
6095 | 320008 | Alternate Charged Party (ACP) for IMS | CH7-IMS-ACP | 2 | Rel-7 | S5 | Mon 22/05/06 | Thu 14/06/07 | 100% | SP-060442 | - | Lucent | njmazzarella@alcatel-lucent.com | - | 32.240, 32.260, 32.298, 32.299 |  |  |  |  | Mon 22/05/06 | Fri 22/06/07
6096 | 330004 | Align 3GPP Charging with OMA PoC Enabler Release 2.0 | CH7-PoC | 2 | Rel-7 | S5 | Thu 28/09/06 | Thu 14/06/07 | 100% | SP-060546 | - | Siemens | Gerald.Goermer@nsn.com | 09/2006 SP#33 WID approved | 32.240, 32.272, 32.299, 32.298 |  |  |  |  | Mon 09/10/06 | Fri 22/06/07
6097 | 2468 | Multiple-Input Multiple-Output (MIMO) antennas | MIMO | 1 | Rel-7 | R1,R5 | Fri 14/03/03 | Fri 07/03/08 | 100% | RP-030192 | - | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007¦SR in RP-070037and RP-070531 | 25.876, 25.996 |  |  |  |  | Tue 20/03/01 | Wed 25/06/08
6098 | 21006 | MIMO - Physical layer | MIMO-Phys | 2 | Rel-7 | R1 | Fri 12/09/03 | Thu 15/03/07 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007¦SR in RP-070037 | 25.211, 25.212, 25.213, 25.214, 25.215, 25.221 |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
6099 | 22003 | MIMO - Layer 2,3 aspects | MIMO-L23 | 2 | Rel-7 | R2 | Fri 12/09/03 | Thu 15/03/07 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007¦SR in RP-070037 | 25.876 |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
6100 | 23008 | MIMO - Iub/Iur Protocol Aspects | MIMO-IurIub | 2 | Rel-7 | R3 | Fri 14/03/03 | Thu 15/03/07 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007¦SR in RP-070037 | - |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
6101 | 24008 | MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | MIMO-RF | 2 | Rel-7 | R4 | Fri 12/12/03 | Mon 17/09/07 | 100% | RP-030192 | RP-070531 | Alcatel-Lucent | ngm@Alcatel-Lucent.com | Completed Sep 2007¦SR in RP-070531 | - |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
6102 | 25036 | UE Conformance Testing for Multiple Input Multiple Output antennas (MIMO) | MIMO-UEConTest | 2 | Rel-7 | R5 | Fri 09/03/07 | Fri 07/03/08 | 100% | - | - | Qualcomm | svora@qualcomm.com | BB place holder for a number of RAN5 Tasks | - |  |  |  |  | Mon 19/03/07 | Wed 16/06/10
6103 | 25037 | Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD | MIMO-UEConTest_FDD | 3 | Rel-7 | R5 | Fri 09/03/07 | Fri 07/03/08 | 100% | - | - | Qualcomm | svora@qualcomm.com | - | 34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Wed 20/09/06 | Wed 16/06/10
6104 | 20028 | Rel-7 Improvements of the Radio Interface | - | 1 | Rel-7 | RP,GP | Wed 15/09/04 | Mon 04/06/07 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Tue 04/01/05 | Wed 25/06/08
6105 | 20060 | Extended UMTS 1.7/2.1 GHz | RInImp-UMTS1721Ext | 2 | Rel-7 | R4 | Wed 15/03/06 | Fri 15/12/06 | 100% | RP-060180 | RP-060681 | Ericsson | johan.skold@ericsson.com | RP#34 completed. Introduction of Band X (Extended UMTS 1.7/2.1 GHz) in 25.307 | 25.806, 25.101, 25.104, 25.133, 24.141, 25.331, 25.306, 25.307, 25.423, 25.461, 25.463, 34.121 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6106 | 20067 | UMTS 2.6 GHz 7.68 Mcps TDD | RInImp-UMTS26VHCRTDD | 2 | Rel-7 | R4 | Thu 15/06/06 | Fri 15/09/06 | 100% | RP-060349 | RP-060451 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.113, 25.142, 34.124 |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
6107 | 20021 | UMTS 2.6 GHz | RInImp-UMTS2600 | 2 | Rel-7 | R4 | Wed 15/09/04 | Tue 14/06/05 | 100% | RP-040397 | RP-050184 | Nokia | jussi.numminen@nokia.com | RP#28 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6108 | 20025 | UMTS 2.6 GHz TDD | RInImp-UMTS2600TDD | 2 | Rel-7 | R4 | Wed 15/12/04 | Wed 14/12/05 | 100% | RP-040553 | RP-050661 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#30 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 25.331, 25.942, 25.306, 25.307, 34.122, 34.124 |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
6109 | 20027 | UMTS 900 MHz | RInImp-UMTS900 | 2 | Rel-7 | R4 | Wed 15/12/04 | Wed 14/12/05 | 100% | RP-040541 | RP-050662 | Nortel | Yannick Li (yli@nortelnetworks.com) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
6110 | 20043 | UMTS 1700 MHz | RInImp-UMTS1700 | 2 | Rel-7 | R4 | Tue 15/03/05 | Wed 14/12/05 | 100% | RP-050385 | RP-050824 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 34.121 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
6111 | 20024 | UE Antenna Performance Evaluation Method and Requirements | RInImp-UEAnt | 2 | Rel-7 | R4,GP | Wed 15/12/04 | Mon 04/06/07 | 100% | RP-050122 | RP-070281 | TeliaSonera | Christian.Bergljung@TeliaSonera.com | RP#36 completed | 25.101, new (25.914, 25.963) |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
6112 | 20045 | Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2) | RInImp-HSPerf-Type3 | 2 | Rel-7 | R4 | Tue 15/03/05 | Tue 15/03/05 | 100% | RP-050362 | RP-060015 | Cingular | Marc Grant | RP#27 completed | 25.101 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
6113 | 20062 | Additional minimum UE performance requirement for non-HSDPA channels based on type 1 enhanced receiver (Rx Diversity) | RInImp-RxDiv | 2 | Rel-7 | R4 | Thu 15/09/05 | Fri 15/12/06 | 100% | - | - | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | - | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 24/06/08
6114 | 20048 | Additional minimum UE performance requirement for DL physical channels in support of DCH/HS-DSCH operation based on type 1 enhanced receiver (RX-Diversity) | RInImp-RxDiv-DCH | 3 | Rel-7 | R4 | Thu 15/09/05 | Wed 14/06/06 | 100% | RP-060185 | RP-060235 | Cingular | Marc Grant | RP#32 completed | 25.101 |  |  |  |  | Wed 05/10/05 | Tue 27/07/10
6115 | 7028 | Additional minimum UE performance requirement for downlink physical channels in support of MTCH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-MBMS | 3 | Rel-7 | R4 | Wed 15/03/06 | Fri 15/12/06 | 100% | RP-060183 | RP-060678 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6116 | 7029 | Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-EDCH | 3 | Rel-7 | R4 | Wed 15/03/06 | Fri 15/12/06 | 100% | RP-060184 | RP-060679 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6117 | 20049 | Deleted Improved support of gaming over HSDPA/EDCH | RInImp-Gaming | 2 | Rel-7 | R2 | Thu 15/12/05 | Fri 15/12/06 | 100% | - | RP-060680 | Cingular | Don Zelmer (dz1069@att.com) | RP#34 stopped. SR in RP-060680 | - |  |  | RP-34 |  | Thu 15/12/05 | Tue 27/07/10
6118 | 20047 | Deleted (not approved at PCG) - UMTS 2.6 GHz FDD DL External | RInImp-UMTS2600Ext | 2 | Rel-7 | R4 | Thu 15/09/05 | Thu 15/09/05 | 100% | - | - | T-mobile | han.van.bussel@t-mobile.de | This item was conditionnaly approved pending decision of PCG#16 who decided not to approve it | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  | RP-31 | PCG-16 | Wed 05/10/05 | Thu 22/12/05
6119 | 25025 | Rel-7 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-7 | R5 | Fri 11/11/05 | Fri 12/09/08 | 100% | - | - | - | - | Linked to Feature UID_20028 (RInImp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
6120 | 25007 | UE Conformance Test for UMTS 2600 MHz | RInImp-UMTS2600_Test | 2 | Rel-7 | R5 | Fri 11/11/05 | Fri 02/06/06 | 100% | - | - | Nokia | Aleksi.Heino@nokia.com | RP#32 completed | 34.108, 34.121 |  |  |  |  | Thu 28/02/02 | Tue 21/03/06
6121 | 25008 | UE Conformance Test for UMTS 900 MHz (band VIII) | RInImp-UMTS900_Test | 2 | Rel-7 | R5 | Fri 11/11/05 | Fri 02/06/06 | 100% | - | - | Qualcomm | hanye@qualcomm.com | RP#32 completed | 34.108, 34.121 |  |  |  |  | Thu 28/02/02 | Tue 21/03/06
6122 | 25013 | Conformance Test Aspects – Improved Performance of HSDPA Receiver type 3 | RInImp-HSPerf-Type3_Test | 2 | Rel-7 | R5 | Fri 10/03/06 | Fri 01/12/06 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | RP#34 completed | 34.121, 34.108 |  |  |  |  | Tue 21/03/06 | Tue 21/03/06
6123 | 25020 | UE antenna Over The Air (OTA) conformance testing | RInImp-UEAnt_Test | 2 | Rel-7 | R5 | Wed 20/09/06 | Fri 12/09/08 | 100% | RP-060486 | RP-080535 | Nokia | Aleksi.Heino@nokia.com | RP#41 completed (GERAN aspects might need to be included later) | 34.114 |  |  |  |  | Wed 20/09/06 | Sun 14/09/08
6124 | 25015 | UE conformance testing for FDD Inter-Band Operation | RInImp-InterBand_Test | 2 | Rel-7 | R5 | Fri 02/06/06 | Fri 01/12/06 | 100% | - | - | NEC, Motorola | Jacob.John@motorola.com | RP#34 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Fri 01/12/06
6125 | 25028 | Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz | RInImp-UEConTest_UMTS1721Ext | 2 | Rel-7 | R5 | Fri 01/12/06 | Fri 01/06/07 | 100% | RP-060676 | RP-070312 | Motorola | carolyn.taylor@motorola.com | RP#36 completed | 34.108, 34.121-1, 34.121-2 |  |  |  |  | Wed 20/09/06 | Mon 11/06/07
6126 | 25039 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivEDCH | 2 | Rel-7 | R5 | Fri 01/06/07 | Fri 07/12/07 | 100% | RP-070414 | RP-070810 | Motorola | carolyn.taylor@motorola.com | RP#38 completed | - |  |  |  |  | Wed 20/09/06 | Tue 11/09/07
6127 | 25040 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of MTCGH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivMBMS | 2 | Rel-7 | R5 | Fri 01/06/07 | Fri 07/03/08 | 100% | RP-070381 | RP-080056 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.121-1, 34.121-2 |  |  |  |  | Wed 20/09/06 | Mon 10/03/08
6128 | 20029 | Rel-7 RAN improvements | - | 1 | Rel-7 | RP,S5 | Wed 15/12/04 | Fri 15/06/07 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Tue 04/01/05 | Wed 25/06/08
6129 | 20026 | Optimization of channelisation code utilisation for 1.28 Mcps TDD | RANimp-RABSE-CodOptLCRTDD | 2 | Rel-7 | R1 | Wed 15/12/04 | Fri 15/12/06 | 100% | RP-040552 | RP-060682 | UTStarcom | Ka Leong Lo (kaleong.lo@UTSTAR.COM) | RP#34 completed | - |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
6130 | 20031 | Delay optimization for procedures applicable to CS and PS Connections | RANimp-DelayOpt | 2 | Rel-7 | R2 | Tue 15/03/05 | Fri 15/09/06 | 100% | RP-050386 | RP-060453 | Nokia | juho.pirskanen@nokia.com | RP#33 completed | 25.815, 25.321, 25.322, 25.331 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6131 | 20132 | Improved support of IMS Realtime Services using HSDPA/HSUPA | RANimp-IMSRealTime | 2 | Rel-7 | R2 | Tue 15/03/05 | Wed 14/12/05 | 100% | RP-050160 | RP-050667 | Cingular | Don Zelmer (dz1069@att.com) | RP#30 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6132 | 20033 | UE Performance Requirements for MBMS (TDD) | MBMS-RAN-RF-TDD | 2 | Rel-7 | R4 | Tue 15/03/05 | Thu 15/06/06 | 100% | RP-050156 | RP-060477 | IPwireless | shwong@ipwireless.com | RP#32 completed | 25.102, 25.123 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6133 | 20046 | Continuous connectivity for packet data users | RANimp-CPC | 2 | Rel-7 | R1 | Mon 14/03/05 | Thu 15/03/07 | 100% | RP-050870 | RP-070033 | Siemens | Joern.Krause@siemens.com | RP#35 completed | 25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133 |  |  |  |  | Wed 05/10/05 | Tue 27/07/10
6134 | 7030 | Extended WCDMA Cell Range | RANimp-ExtCell | 2 | Rel-7 | R3 | Wed 15/03/06 | Fri 15/12/06 | 100% | RP-060212 | RP-060685 | Ericsson | Muhammad Kazmi | RP#34 completed | 25.133, 25.423, 25.425, 25.433, 25.435, 25.453, 25.331 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6135 | 7031 | 7.68 Mcps TDD Enhanced Uplink | RANimp-VHCRTDD-EDCH | 2 | Rel-7 | R1 | Wed 15/03/06 | Fri 15/12/06 | 100% | RP-060119 | RP-060684 | IPwireless | nanderson@ipwireless.com | RP#34 completed | 25.201, 25.202, 25.221, 25.222, 25.223, 25.224, 25.225, 25.331, 23.321, 25.306, 25.302, 25.401, 25.420, 25.423, 25.427, 25.433, 25.102, 25.105, 25.142 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6136 | 330009 | Enhanced CELL_FACH State in FDD | RANimp-EnhState | 2 | Rel-7 | R2 | Mon 25/09/06 | Mon 04/06/07 | 100% | RP-070245 | RP-070286 | Nokia | juho.pirskanen@nokia.com | RP#36 completed | 25.308, 25.304, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
6137 | 340038 | 64QAM for HSDPA (FDD) | RANimp-64QamDownlink | 2 | Rel-7 | R1 | Fri 15/12/06 | Mon 04/06/07 | 100% | RP-070223 | RP-070287 | Ericsson | Johan.Bergman@ericsson.com | RP#36 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
6138 | 340039 | Improved L2 support for high data rates | RANimp-L2DataRates | 2 | Rel-7 | R2 | Fri 15/12/06 | Mon 04/06/07 | 100% | RP-070242 | RP-070289 | Ericsson | Janne.Peisa@ericsson.com | RP#36 completed | 25.301, 25.308,25.306, 25.321, 25.322, 25.331, 25.433, 25.435, 25.423, 25.425, 25.999 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
6139 | 340040 | Introduction of 16QAM in HSUPA (FDD) | RANimp-16QamUplink | 2 | Rel-7 | R1 | Fri 15/12/06 | Mon 04/06/07 | 100% | RP-060844 | RP-070288 | Nokia | Karri.Ranta-aho@nsn.com | RP#36 completed | 25.319, 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.306, 25.321, 25.331, 25.423, 25.433 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
6140 | 20066 | Interface to control Tower Mounted Amplifiers (TMAs) | RANImp-TMA | 2 | Rel-7 | R3,S5 | Fri 02/06/06 | Fri 15/06/07 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | - |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
6141 | 20166 | RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs) | - | 3 | Rel-7 | R3 | Fri 02/06/06 | Fri 16/03/07 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | - |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
6142 | 340045 | OAM aspects to Interface to control TMAs | RANImp-TMA-OAM | 3 | Rel-7 | S5 | Fri 26/01/07 | Fri 15/06/07 | 100% | - | - | Vodafone | Adrian.Neal@vodafone.com | SP#36 completed | 32.642, 32.643, 32.645 – Align with RAN 25.466 |  |  |  |  | Thu 08/03/07 | Tue 27/07/10
6143 | 25026 | Rel-7 RAN improvements - UE Conformance Testing | - | 1 | Rel-7 | R5 | Wed 20/09/06 | Fri 18/09/09 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | - |  |  |  |  | Fri 22/09/06 | Tue 27/07/10
6144 | 25021 | Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink | RANimp-UEConTest_EDCHTDH | 2 | Rel-7 | R5 | Wed 20/09/06 | Fri 12/09/08 | 100% | RP-060484 | RP-080536 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6145 | 25031 | Conformance Test Aspects – 64QAM for HSDPA (FDD) | RANimp-UEConTest_64QamDownlink | 2 | Rel-7 | R5 | Fri 09/03/07 | Mon 03/03/08 | 100% | RP-071319 | RP-080059 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6146 | 25032 | Conformance Test Aspects – 16QAM for HSUPA (FDD) | RANimp-UEConTest_16QamUplink | 2 | Rel-7 | R5 | Fri 09/03/07 | Fri 30/05/08 | 100% | RP-070022 | RP-080281 | Motorola | carolyn.taylor@motorola.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6147 | 25033 | Conformance Test Aspects – Improved L2 support for high data rates | RANimp-UEConTest_L2DataRates | 2 | Rel-7 | R5 | Fri 09/03/07 | Fri 30/05/08 | 100% | RP-070020 | RP-080256 | Ericsson | leif.mattisson@ericsson.com | RP#40 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6148 | 25034 | Conformance Test Aspects – Continuous connectivity for packet data users | RANimp-UEConTest_CPC | 2 | Rel-7 | R5 | Fri 09/03/07 | Fri 30/05/08 | 100% | RP-070023 | RP-080282 | Nokia | jarkko.hellsten@nokia.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6149 | 25035 | Conformance Test Aspects – Enhanced CELL_FACH state in FDD | RANimp-UEConTest_EnhancedCellFACHState | 2 | Rel-7 | R5 | Fri 09/03/07 | Fri 18/09/09 | 100% | RP-080730 | RP-090711 | Nokia | jarkko.hellsten@nokia.com | RP#45 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6150 | 20014 | 7.68 Mcps TDD option | VHCRTDD | 1 | Rel-7 | R1,R2,R3,R4,R5 | Wed 15/09/04 | Fri 14/09/07 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | - |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6151 | 20015 | VHCRTDD: Stage 2 | VHCRTDD-Stage2 | 2 | Rel-7 | R1 | Wed 15/09/04 | Wed 15/03/06 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.202 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6152 | 20016 | VHCRTDD: Physical Layer | VHCRTDD-Phys | 2 | Rel-7 | R1 | Wed 15/09/04 | Wed 15/03/06 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.221, 25.222, 25.223, 25.224,25.225 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6153 | 20017 | VHCRTDD: Layer 2 and layer 3 protocol aspects | VHCRTDD-L23 | 2 | Rel-7 | R2 | Wed 15/09/04 | Wed 15/03/06 | 100% | RP-060119 | RP-060684 | IPwireless | drichards@ipwireless.com | RP#31 completed | 25.301, 25.302, 25.305, 25.306, 25.321, 25.331 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6154 | 20018 | VHCRTDD: UTRAN Iub/Iur Protocol Aspects | VHCRTDD-IurIub | 2 | Rel-7 | R3 | Wed 15/09/04 | Wed 15/03/06 | 100% | RP-060119 | RP-060684 | IPwireless | Peter Legg (plegg@ipwireless.com) | RP#31 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6155 | 20019 | VHCRTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | VHCRTDD-RF | 2 | Rel-7 | R4 | Wed 15/09/04 | Thu 15/06/06 | 100% | RP-060119 | RP-060684 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#32 completed | 25.102, 25.105, 25.123, 25.133, 25.142 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
6156 | 25027 | Conformance Test Aspects - 7.68 Mcps TDD | VHCRTDD-UEConTest | 2 | Rel-7 | R5 | Wed 20/09/06 | Fri 14/09/07 | 100% | RP-060482 | RP-070307 | IPWireless | tspeight@ipwireless.com | RP#37 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
6157 | 20035 | 3.84 Mcps TDD Enhanced Uplink | EDCHTDD | 1 | Rel-7 | RP | Tue 15/03/05 | Fri 15/09/06 | 100% | RP-050100 | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6158 | 20036 | EDCHTDD: Stage 2 | EDCHTDD-Stage2 | 2 | Rel-7 | R2 | Tue 15/03/05 | Thu 15/06/06 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6159 | 20037 | EDCHTDD: Physical Layer | EDCHTDD-Phys | 2 | Rel-7 | R1 | Tue 15/03/05 | Fri 15/09/06 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | 25.201, 25.221,25.222, 25.223, 25.224, 25.225 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6160 | 20038 | EDCHTDD: Layer 2 and 3 Protocol Aspects | EDCHTDD-L23 | 2 | Rel-7 | R2 | Tue 15/03/05 | Fri 15/09/06 | 100% | - | RP-060462 | IPwireless | drichards@ipwireless.com | RP#33 completed | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6161 | 20039 | EDCHTDD: UTRAN Iub/Iur Protocol Aspects | EDCHTDD-IurIub | 2 | Rel-7 | R3 | Tue 15/03/05 | Fri 15/09/06 | 100% | - | RP-060462 | Interdigital | jim.miller@interdigital.com | RP#33 completed | 25.401, 25.420, 25.423, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6162 | 20040 | EDCHTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCHTDD-RF | 2 | Rel-7 | R4 | Tue 15/03/05 | Fri 15/09/06 | 100% | - | RP-060462 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.142 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
6163 | 20055 | 1.28 Mcps TDD Enhanced Uplink | LCRTDD-EDCH | 1 | Rel-7 | R1,R2,R3,R4,R5 | Wed 15/03/06 | Fri 12/09/08 | 100% | RP-060202 | RP-070296 | CATT | Haijing Hu | RP#35 completed | - |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6164 | 20056 | 1.28 Mcps TDD Enhanced Uplink: Physical Layer | LCRTDD-EDCH-Phys | 2 | Rel-7 | R1 | Wed 15/03/06 | Thu 15/03/07 | 100% | - | RP-070038 | CATT | Ke Wang | RP#35 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.225 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6165 | 20057 | 1.28 Mcps TDD Enhanced Uplink: Layer 2 and 3 Protocol Aspects | LCRTDD-EDCH-L23 | 2 | Rel-7 | R2 | Wed 15/03/06 | Thu 15/03/07 | 100% | - | RP-070038 | CATT | Haiyang Quan | RP#35 completed | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6166 | 20058 | 1.28 Mcps TDD Enhanced Uplink: UTRAN Iub/Iur Protocol Aspects | LCRTDD-EDCH-IubIur | 2 | Rel-7 | R3 | Wed 15/03/06 | Thu 15/03/07 | 100% | - | RP-070038 | CATT | Yincheng Zhang | RP#35 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6167 | 20059 | 1.28 Mcps TDD Enhanced Uplink: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | LCRTDD-EDCH-RF | 2 | Rel-7 | R4 | Wed 15/03/06 | Fri 15/06/07 | 100% | - | RP-070296 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#36 completed | 25.102, 25.105, 25.123, 25.142 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6168 | 350146 | 1.28 Mcps TDD Enhanced Uplink - UE Conformance Testing | LCRTDD-EDCH-UEConTest | 2 | Rel-7 | R5 | Thu 20/09/07 | Fri 12/09/08 | 100% | RP-070724 | RP-080539 | CATT | chenxiaozhong@datangmobile.cn | RP#41 completed | 34.108, 34.122, 34.123-1/2/3 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
6169 | 490016 | Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD | LCRTDD_MB_MF_UEConTest | 1 | Rel-7 | R5 | Fri 17/09/10 | Fri 16/09/11 | 100% | RP-100805 | RP-110968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD. | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Wed 08/09/10 | Tue 06/09/11
6170 | 50118 | MS Antenna Performance Evaluation Method and Requirements | APEMR | 1 | Rel-7 | GP | Fri 28/01/05 | Fri 16/11/07 | 100% | GP-050284 | - | TeliaSonera | Ulf.Tegth@teliasonera.com | GP#36 completed for R7 | 25.914, 25.144, 45.005 |  |  |  |  | Wed 05/09/07 | Mon 19/05/08
6171 | 50119 | Lower 700 MHz Inclusion in the GERAN Specifications | GSM710 | 1 | Rel-7 | GP | Mon 03/01/05 | Fri 30/06/06 | 100% | GP-050543 | - | UTC | dcotton@mtview.union-tel.com | - | - |  |  |  |  | Tue 01/02/05 | Tue 19/09/06
6172 | 51138 | Inclusion of the 698 – 746 MHz band into GERAN core specifications | GSM710-core | 2 | Rel-7 | G1 | Mon 03/01/05 | Thu 30/06/05 | 100% | - | - | - | - | Completed | 24.008, 43.022, 44.018, 44.118, 45, 001, 45.005, |  |  |  |  | Mon 12/09/05 | Thu 15/09/05
6173 | 53184 | Aspects of GSM710 | GSM-710-test | 2 | Rel-7 | G1,G3new | Wed 31/08/05 | Fri 30/06/06 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 12/09/05 | Thu 20/07/06
6174 | 53084 | G1 aspects of GSM710 | - | 3 | Rel-7 | G1 | Wed 31/08/05 | Fri 30/06/06 | 100% | - | - | - | - | - | 51.021 |  |  |  |  | Mon 12/09/05 | Thu 20/07/06
6175 | 55094 | G3 aspects of GSM710 | - | 3 | Rel-7 | G3new | Wed 31/08/05 | Fri 30/06/06 | 100% | - | - | - | - | - | 51.01 |  |  |  |  | Tue 20/12/05 | Mon 17/07/06
6176 | 50564 | Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB | 1 | Rel-7 | GP | Fri 08/04/05 | Fri 31/08/07 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | Originally started Nov. 2003 as GP-030443 | - |  |  |  |  | Thu 21/04/05 | Tue 29/05/07
6177 | 52143 | Minimise the transfer delay between the SGSN and the MS | SCSAGB-MTD | 2 | Rel-7 | GP | Fri 08/04/05 | Fri 31/08/07 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  |  |  | Wed 03/05/06 | Thu 10/01/08
6178 | 51137 | Definition of radio resource management functionality for Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB-RRM | 2 | Rel-7 | G1 | Fri 08/04/05 | Fri 31/08/07 | 100% | GP-061502 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  |  |  | Thu 21/04/05 | Thu 10/01/08
6179 | 52144 | Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode | SCSAGB-RLCNP | 2 | Rel-7 | G2 | Fri 30/06/06 | Fri 17/11/06 | 100% | GP-061503 | - | Ericsson | gunnar.hedby@ericsson.com | - | 43.955, 43.064, 44.060, 45.001, 45.002, 45.003, 45.005, 45.010, 51.010, 51.021 |  |  |  |  | Wed 05/07/06 | Thu 10/01/08
6180 | 52138 | Deleted- Radio Channel Support | SCSAGB-RCHS | 2 | Rel-7 | G2 | Mon 17/07/06 | Mon 17/07/06 | 100% | GP-051166 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  | SP-32 |  | Thu 21/04/05 | Thu 11/05/06
6181 | 52139 | Deleted- Modifications to FLO | SCSAGB-FLO | 2 | Rel-7 | G2 | Mon 17/07/06 | Mon 17/07/06 | 100% | GP-051165 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  | SP-32 |  | Thu 21/04/05 | Thu 09/03/06
6182 | 50565 | Addition of new frequency band to GSM (T-GSM810) | TGSM810 | 1 | Rel-7 | GP | Fri 08/04/05 | Fri 31/08/07 | 100% | GP-050945 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060, 51.010-1, 51.021 |  |  |  |  | Thu 21/04/05 | Tue 29/05/07
6183 | 50566 | Changes to core specification | TGSM810-Core | 2 | Rel-7 | GP | Fri 08/04/05 | Fri 02/09/05 | 100% | GP-050946 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060 |  |  |  |  | Thu 21/04/05 | Thu 15/09/05
6184 | 55092 | Changes to MS testing specification | TGSM810-MStest | 2 | Rel-7 | G3new | Fri 08/04/05 | Fri 31/08/07 | 100% | GP-050947 | - | Huawei | chende@huawei.com | - | 51010-1 |  |  |  |  | Thu 21/04/05 | Wed 12/09/07
6185 | 53082 | Changes to BTS testing specification | TGSM810-BTStest | 2 | Rel-7 | G1 | Fri 08/04/05 | Fri 11/11/05 | 100% | GP-050948 | - | Huawei | chende@huawei.com | - | 51021 |  |  |  |  | Thu 21/04/05 | Thu 22/12/05
6186 | 50567 | Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM | 1 | Rel-7 | GP | Fri 08/04/05 | Fri 17/11/06 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed. Started at GP#24 | - |  |  |  |  | Thu 21/04/05 | Tue 19/09/06
6187 | 55093 | GERAN2 part of Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM-G2 | 2 | Rel-7 | G2 | Fri 08/04/05 | Fri 30/06/06 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed | 43.055, 44.018, 44.060 |  |  |  |  | Thu 21/04/05 | Mon 17/07/06
6188 | 55095 | Deleted - MS Conformance Testing | HODSRDTM-MStest | 2 | Rel-7 | G3new | Fri 08/04/05 | Fri 17/11/06 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51-010 |  |  | GP-32 |  | Mon 21/11/05 | Mon 15/12/08
6189 | 53083 | Deleted - BTS conformance testing | HODSRDTM-BTStest | 2 | Rel-7 | G1 | Fri 08/04/05 | Fri 17/11/06 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51.026 |  |  | GP-32 |  | Thu 21/04/05 | Mon 15/12/08
6190 | 50569 | Mobile Station Receive Diversity (DARP Phase II) | MSRD2 | 1 | Rel-7 | GP | Fri 11/11/05 | Fri 16/11/07 | 100% | GP-061491 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | - |  |  |  |  | Mon 21/11/05 | Mon 19/05/08
6191 | 50571 | Performance Requirements for Mobile Station Receive Diversity, DARP Phase II | MSRD2-PerfReq | 2 | Rel-7 | GP | Fri 11/11/05 | Fri 16/02/07 | 100% | GP-060115 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
6192 | 50572 | Capability signalling of Mobile Station Receive Diversity, DARP Phase II | MSRD2-CapSig | 2 | Rel-7 | GP | Fri 11/11/05 | Fri 16/02/07 | 100% | GP-060116 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 24.008 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
6193 | 50573 | Test Scenarios for Mobile Station Receive Diversity, DARP Phase II | MSRD2-TestSc | 2 | Rel-7 | GP | Fri 11/11/05 | Fri 16/02/07 | 100% | GP-060117 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
6194 | 50570 | MS conformance test of DARP Phase II (MSRD) | MSRD2-Msconf | 2 | Rel-7 | GP | Fri 11/11/05 | Fri 16/11/07 | 100% | GP-060114 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | 51.01 |  |  |  |  | Mon 21/11/05 | Wed 12/09/07
6195 | 50579 | Downlink Dual Carrier | GDCDL | 1 | Rel-7 | GP | Fri 20/01/06 | Fri 04/09/09 | 100% | GP-061331 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | - |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
6196 | 51139 | Downlink Dual Carrier Stage 2 | GDCDL-Stage2 | 2 | Rel-7 | G1 | Fri 20/01/06 | Fri 30/06/06 | 100% | GP-060484 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#30 completed | 43.055, 43.064 |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
6197 | 52142 | Downlink Dual Carrier Stage 3 | GDCDL-Stage3 | 2 | Rel-7 | G1 | Fri 20/01/06 | Fri 31/08/07 | 100% | GP-060485 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.005, 45.008 |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
6198 | 53086 | Downlink Dual Carrier – MS Conformance Test | GDCDL-MStest | 2 | Rel-7 | G3new | Fri 20/01/06 | Fri 04/09/09 | 100% | GP-060486 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#43 completed | 51.01 |  |  |  |  | Tue 24/01/06 | Mon 07/09/09
6199 | 50580 | Support of SIGTRAN in GERAN | GSIGT | 1 | Rel-7 | GP | Fri 20/01/06 | Fri 30/06/06 | 100% | GP-060450 | - | Ericsson | peter.ostrup@ericsson.com | GP#30 completed | 48.001, 48.006, 43.059, 49.031 |  |  |  |  | Tue 24/01/06 | Thu 02/04/09
6200 | 50582 | Latency Reductions | LATRED | 1 | Rel-7 | GP | Fri 30/06/06 | Fri 31/08/07 | 100% | GP-061519 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Wed 12/09/07
6201 | 52145 | Improved Ack/Nack reporting | LATRED-ACKNAR | 2 | Rel-7 | G2 | Fri 30/06/06 | Fri 31/08/07 | 100% | GP-061520 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
6202 | 52146 | Reduced TTI | LATRED-REDTTI | 2 | Rel-7 | G2 | Fri 30/06/06 | Fri 31/08/07 | 100% | GP-061521 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
6203 | 52147 | PS Handover between GERAN/UTRAN mode and GAN Mode | GUGAN | 1 | Rel-7 | G2 | Fri 30/06/06 | Fri 16/02/07 | 100% | GP-061349 | - | Ericsson | John.Diachina@Ericsson.com | GP#33 completed | 43.318, 44.318, 43.129, 25.306, 24.008, 44.060, 25.331, 51.010 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
6204 | 50584 | Higher Uplink performance for GERAN Evolution | HUGE | 1 | Rel-7 | GP | Fri 08/09/06 | Fri 20/05/11 | 100% | GP-071083 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | - |  |  |  |  | Wed 13/09/06 | Mon 26/07/10
6205 | 51140 | Stage 2 for HUGE | HUGE-Stage2 | 2 | Rel-7 | G1 | Fri 08/09/06 | Fri 07/09/07 | 100% | GP-061902 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
6206 | 51141 | Layer 1 Support for HUGE | HUGE-Layer1 | 2 | Rel-7 | G1 | Fri 08/09/06 | Fri 22/02/08 | 100% | GP-061903 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#37 completed | 45.001, 45.002, 45.003, 45.004, 45.008 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
6207 | 52149 | Layer 2/3 Support for HUGE | HUGE-Layer23 | 2 | Rel-7 | G2 | Fri 08/09/06 | Fri 31/08/07 | 100% | GP-061904 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 24.008, 44.018, 44.060 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
6208 | 51142 | Performance requirements for HUGE | HUGE-Perfreq | 2 | Rel-7 | G1 | Fri 08/09/06 | Fri 29/08/08 | 100% | GP-061905 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | 45.005 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
6209 | 51143 | BTS Conformance Test for HUGE | HUGE-BTStest | 2 | Rel-7 | G1 | Fri 08/09/06 | Fri 04/09/09 | 100% | GP-061907 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#43 completed | 51.021 |  |  |  |  | Wed 13/09/06 | Mon 07/09/09
6210 | 53087 | MS Conformance Test for HUGE | HUGE-Mstest | 2 | Rel-7 | G3new | Fri 08/09/06 | Fri 20/05/11 | 100% | GP-061906 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#50 completed | 51.01 |  |  |  |  | Wed 13/09/06 | Sat 21/05/11
6211 | 50121 | REduced symbol Duration, Higher Order modulation and Turbo coding (RED HOT) for downlink | REDHOT | 1 | Rel-7 | GP | Fri 17/11/06 | Fri 20/05/11 | 100% | GP-071080 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | - |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
6212 | 51144 | Stage 2 for REDHOT | REDHOT-Stage2 | 2 | Rel-7 | G1 | Fri 17/11/06 | Fri 31/08/07 | 100% | GP-062489 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064 |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
6213 | 51145 | Stage 3 for REDHOT | REDHOT-Stage3 | 2 | Rel-7 | G1 | Fri 17/11/06 | Fri 16/05/08 | 100% | GP-062490 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.003, 45.004, 45.005, 45.008 |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
6214 | 51146 | BTS Conformance Tests for REDHOT | REDHOT-BTStest | 2 | Rel-7 | G1 | Fri 17/11/06 | Fri 15/05/09 | 100% | GP-062492 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#42 completed | 51.021 |  |  |  |  | Mon 20/11/06 | Mon 18/05/09
6215 | 53088 | MS Conformance Tests for REDHOT | REDHOT-Mstest | 2 | Rel-7 | G3new | Fri 17/11/06 | Fri 20/05/11 | 100% | GP-062491 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#50 completed | 51.01 |  |  |  |  | Mon 20/11/06 | Sat 21/05/11
6216 | 60110 | (Small) Technical Enhancements and Improvements for Rel-7 | TEI7 | 1 | Rel-7 | SP,CP,RP,GP | Mon 26/03/07 | Mon 26/03/07 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 04/11/05 | Thu 20/04/06
6217 | 25030 | Test - (Small) Technical Enhancements and Improvements for Rel-7 | TEI7_Test | 1 | Rel-7 | R5 | Fri 02/06/06 | Wed 28/11/07 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 26/05/10 | Wed 26/05/10
6218 | 32113 | Deleted - PS domain and IMS support for IMS Emergency sessions | IMS-EMER | 1 | Rel-7 | S2 | Fri 23/06/06 | Fri 23/06/06 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Fri 28/03/03 | Thu 22/12/05
6219 | 32114 | Deleted - IMS aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | Fri 23/06/06 | Fri 23/06/06 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Tue 22/03/05 | Thu 22/12/05
6220 | 32115 | Deleted - PS domain aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | Fri 23/06/06 | Fri 23/06/06 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Tue 22/03/05 | Thu 22/12/05
6221 | 32005 | Deleted - IMS Local services | IMSLocal | 1 | Rel-7 | S2 | Fri 06/01/06 | Fri 06/01/06 | 99% | - | - | - | - | - | 23.228 |  |  | SP-28 |  | Mon 08/10/01 | Thu 30/05/02
6222 | 32019 | Deleted - Stage 2 | - | 2 | Rel-7 | S2 | Fri 06/01/06 | Fri 06/01/06 | 100% | - | - | - | - | DAB - Not yet required in SA2 as it exists in previous releases | - |  |  | SP-26 |  | Mon 25/03/02 | Mon 06/12/04
6223 | 11035 | Deleted - Stage 3 for IMS Local services | - | 2 | Rel-7 | C1 | Fri 06/01/06 | Fri 06/01/06 | 100% | - | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  | SP-25 |  | Mon 13/01/03 | Thu 09/09/04
6224 | 32078 | Deleted - IMS Phase 3 | - | 1 | Rel-7 | S2 | Fri 06/01/06 | Fri 06/01/06 | 100% | - | - | - | - | - | - |  |  | SP-25 |  | Wed 08/09/04 | Thu 09/09/04
6225 | 701216 | Deleted - Improvements of Radio Interface | - | 1 | Rel-7 | RP | Wed 15/09/04 | Wed 15/09/04 | 100% | - | - | - | - | Stage 2 description of Interim conclusion | - | 70 | 36 | SP-24 |  | Fri 31/03/00 | Thu 08/07/04
6226 | 14018 | Deleted: Generic User Profile Phase 2 | - | 1 | Rel-7 | C4 | Mon 08/08/05 | Fri 30/06/06 | 100% | - | - | - | - | Created at TSG#27 by A. Sultan because of the move to Rel-7 of "Common Objects". | - |  |  | SP-27 |  | Wed 09/03/05 | Wed 09/03/05
6227 | 42003 | Deleted - Stage 3 - Common objects | - | 1 | Rel-7 | C4 | Mon 08/08/05 | Mon 08/08/05 | 100% | TP-020275 | - | - | - | No progress in CN4#26. This have to be moved to Rel-7. It was deleted from WID | 24.241 |  |  | SP-27 |  | Tue 09/10/01 | Wed 09/03/05
6228 | 0 | Release 7 Studies | - | 1 | Rel-7 | CP,GP,RP,SP | Mon 28/06/04 | Mon 17/09/07 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
6229 | 31082 | Study on Multimedia Telephony Capabilities for IMS | MITE | 1 | Rel-7 | S1 | Mon 11/07/05 | Mon 31/07/06 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | Spin-off Feature UID_7038 (MTSI) | 22.973 |  |  |  |  | Thu 21/04/05 | Tue 01/07/08
6230 | 31050 | Study on Behaviour of Multi system UEs | BMSU | 1 | Rel-7 | S1 | Mon 28/06/04 | Thu 15/12/05 | 100% | SP-050502 | - | Qualcomm | dwilliams@qualcomm.com | - | 22.936 |  |  |  |  | Mon 30/08/04 | Fri 27/06/08
6231 | 31055 | Study on Combining CS calls and IMS sessions | IRTSD-CS_IMS | 1 | Rel-7 | S1 | Mon 28/06/04 | Thu 17/03/05 | 100% | SP-040467 | - | TeliaSonera | robert.frank@teliasonera.com | - | 22.979 |  |  |  |  | Mon 30/08/04 | Tue 27/07/10
6232 | 31059 | Study on All-IP Network | FS_AIPN | 1 | Rel-7 | S1 | Mon 28/06/04 | Wed 16/03/05 | 100% | SP-040303 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | 07/08 Moved to Rel-7 as Study out of stopped Rel-8 Feature UID_31067 All-IP Network (AIPN) | 22.978 |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
6233 | 31075 | Study on Videotelephony teleservice | VidTel | 1 | Rel-7 | S1 | Tue 01/03/05 | Tue 17/01/06 | 100% | SP-050506 | - | T-Mobile | michael.kurz@t-mobile.at | - | 22.903 |  |  |  |  | Tue 22/03/05 | Fri 27/06/08
6234 | 31073 | Study on Network Selection Principles | NetSel | 1 | Rel-7 | S1 | Tue 15/03/05 | Thu 08/12/05 | 100% | SP-050227 | - | O2 | chris.friel@O2.com | Spin-off Feature Network selection enhancements (NSP-CR) UID_7041 | 22.811 |  |  |  |  | Tue 22/03/05 | Fri 27/06/08
6235 | 31041 | Study on Multimedia Priority Service | PRIOR-MM | 1 | Rel-7 | S1 | Fri 28/03/03 | Fri 30/06/06 | 100% | SP-060329 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | Spin-off Feature PRIOR UID_340044 | 22.953 |  |  |  |  | Fri 28/03/03 | Tue 31/08/10
6236 | 31083 | Study on Transferring of emergency Call data | eCALL | 1 | Rel-7 | S1 | Mon 11/07/05 | Fri 31/03/06 | 100% | SP-050388 | - | Motorola | jian.j.wu@motorola.com | - | 22.967 |  |  |  |  | Mon 20/06/05 | Tue 31/08/10
6237 | 32073 | Study on Enhancement of E2E QoS | QoS7 | 1 | Rel-7 | S2 | Mon 28/06/04 | Thu 15/09/05 | 100% | SP-040326 | - | Huawei | Robert Jaksa | - | 23.802 |  |  |  |  | Mon 30/08/04 | Mon 30/06/08
6238 | 35066 | Study on SOAP/HTTP IRP Solution Sets | OAM7-NIM-XML | 1 | Rel-7 | S5 | Fri 02/09/05 | Thu 07/12/06 | 100% | SP-050610 | - | Nortel | Suzèle Lariven (lariven@nortel.com) | SP#34 completed | 32.809 |  |  |  |  | Fri 16/09/05 | Tue 27/07/10
6239 | 35067 | Study on Itf-N Implementation Conformance Statement (ICS) template | OAM7-NIM-ICS | 1 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050609 | - | China Mobile | Li Yewen (liyewen@chinamobile.com) | SP#35 completed | 32.812 |  |  |  |  | Fri 16/09/05 | Thu 29/03/07
6240 | 35068 | Study on IRP Information Model | OAM7-NIM-IM | 1 | Rel-7 | S5 | Fri 02/09/05 | Thu 15/03/07 | 100% | SP-050611 | - | Motorola | trevor.pirt@motorola.com | SP#35 completed | 32.81 |  |  |  |  | Fri 16/09/05 | Tue 27/07/10
6241 | 7034 | Study on Bandwidth Saving at Nb Interface with IP transport | BSNbIP | 1 | Rel-7 | C3 | Fri 10/03/06 | Fri 09/03/07 | 100% | CP-060438 | - | Siemens | Thomas.Belling@siemens.com | Moved to FS at CT32 (in line with slides) | 29.814 |  |  |  |  | Mon 20/03/06 | Tue 27/07/10
6242 | 14019 | Study on Routeing of MT-SMS via the HPLMN | SMS7 | 1 | Rel-7 | C4 | Fri 07/10/05 | Fri 01/12/06 | 100% | CP-060701 | - | Vodafone | Nick.Russell@vodafone.com | Previously known as "Study of a SMS Centre for MT SMS" | 23.84 |  |  |  |  | Fri 07/10/05 | Mon 30/06/08
6243 | 7025 | Feasibility Study on the TCAPsec Gateway concept | FS_SEC7-TCAP | 1 | Rel-7 | C4 | Fri 28/10/05 | Fri 10/03/06 | 100% | CP-050687 | - | Siemens | Ulrich.wiehe@gksag.de | TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway | 29.8 |  |  |  |  | Fri 07/10/05 | Tue 01/07/08
6244 | 7050 | Study on using M2PA in 3GPP network | FS-M2PA | 1 | Rel-7 | C4 | Wed 22/03/06 | Fri 08/06/07 | 100% | CP-060698 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 29.801 |  |  |  |  | Wed 22/03/06 | Tue 01/07/08
6245 | 320018 | Study on Support of (G)MSC-S - (G)MSC-S Nc Interface based on the SIP-I protocol | NcSIP | 1 | Rel-7 | C4,C3 | Mon 15/05/06 | Fri 14/09/07 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802 |  |  |  |  | Wed 21/06/06 | Tue 01/07/08
6246 | 330002 | CT4 aspects of NcSIP | - | 2 | Rel-7 | C4 | Mon 15/05/06 | Fri 01/06/07 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802 |  |  |  |  | Thu 21/09/06 | Tue 01/07/08
6247 | 330003 | CT3 aspects of NcSIP | - | 2 | Rel-7 | C3 | Mon 15/05/06 | Fri 14/09/07 | 100% | CP-070034 | - | Ericsson | ragnar.huslende@ericsson.com | - | 29.802 |  |  |  |  | Thu 21/09/06 | Tue 01/07/08
6248 | 20023 | Study on Evolved UTRA and UTRAN | RANFS-Evo | 1 | Rel-7 | RP | Wed 15/12/04 | Fri 15/09/06 | 100% | RP-040461 | RP-060472 | NTT DoCoMo | nakamurata@NTTDOCOMO.CO.JP | RP#33 (Sep 2006) completed. SR in RP-060472 | 25.912 |  |  |  |  | Tue 04/01/05 | Mon 23/06/08
6249 | 20034 | Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph | RANFS-HSTrains | 1 | Rel-7 | R4 | Tue 15/03/05 | Thu 15/06/06 | 100% | RP-050146 | RP-060412 | Vodafone | Mike.vogel@vodafone.com,tim.frost@vodafone.com | RP#32 (Jun 2006) completed. SR in RP-060412 | none |  |  |  |  | Tue 15/03/05 | Mon 23/06/08
6250 | 20041 | Study on UTRA Tower Mounted Amplifier (FDD) | RANFS-TMA | 1 | Rel-7 | R4 | Wed 15/06/05 | Tue 14/03/06 | 100% | RP-050387 | RP-060035 | Ericsson | Klas.Sjerling@ericsson.com | RP#31 (Mar 2006) completed. SR in RP-060035 | 25.818 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
6251 | 20044 | Study on Continuous connectivity for packet data users | RANFS-cont-packet | 1 | Rel-7 | R1 | Tue 15/03/05 | Wed 14/09/05 | 100% | RP-050391 | RP-050427 | Siemens | joerg.gustrau@siemens.com | RP#29 (Sep 2006) completed. SR in RP-050427 | none |  |  |  |  | Mon 20/06/05 | Mon 23/06/08
6252 | 20051 | Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN | RANFS-MBMSImp | 1 | Rel-7 | R2 | Thu 15/12/05 | Fri 15/12/06 | 100% | RP-050746 | RP-060692 | LG Electronics | leego@lge.com | RP#34 completed | 25.905 |  |  |  |  | Thu 15/12/05 | Thu 26/07/12
6253 | 20052 | Deleted - Study on Performance Improvements in Small Cells using HSDPA/EDCH | SMALLCELLS | 1 | Rel-7 | R1,R4 | Thu 15/12/05 | Thu 15/06/06 | 100% | RP-050782 | RP-060263 | Cingular | Marc Grant | RP#32 (Jun 2006) stopped at 0% completion | none |  |  | SP-69 |  | Thu 15/12/05 | Mon 23/06/08
6254 | 20053 | Study on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | RANFS-IC | 1 | Rel-7 | R4 | Thu 15/12/05 | Mon 04/06/07 | 100% | RP-050880 | RP-070499 | Cingular | Marc Grant | RP#36 (May 2007) completed. SR in RP-070499 | 25.963 |  |  |  |  | Thu 15/12/05 | Mon 23/06/08
6255 | 20065 | Study on Scope of future FDD HSPA Evolution | RANFS-HSPAEvo | 1 | Rel-7 | RP | Wed 15/03/06 | Mon 17/09/07 | 100% | RP-060217 | RP-070533 | Cingular | Don Zelmer (dz1069@att.com) | RP#37 (Sep 2007) completed. SR in RP-070533 | 25.999 |  |  |  |  | Tue 21/03/06 | Mon 23/06/08
6256 | 330013 | Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met | FSUEPow | 1 | Rel-7 | R4 | Fri 22/06/07 | Fri 22/06/07 | 100% | RP-060641 | RP-070534 | Nokia | Chris.callender@nokia.com, tiina.s.koskinen@nokia.com | RP#37 (Sep 2007) completed. SR in RP-070534 | 25.906 |  |  |  |  | Fri 06/10/06 | Mon 23/06/08
6257 | 50568 | Study on Future GERAN Evolution | FGE | 1 | Rel-7 | GP | Fri 08/04/05 | Fri 16/02/07 | 100% | GP-051052 | - | Nokia | eddie.riddington@nokia.com | GP#33 completed | 45.912 |  |  |  |  | Thu 21/04/05 | Thu 08/03/07
6258 | 50120 | Study on GAN Enhancements | EGAN | 1 | Rel-7 | GP | Fri 31/08/07 | Fri 31/08/07 | 100% | GP-062298 | - | T-Mobile | janne.linkola@t-mobile.com | GP#35 completed | 43.902 |  |  |  |  | Mon 20/11/06 | Tue 29/05/07
6259 | 31054 | Deleted - Study on IMS with real time services deployment | IRTSD | 1 | Rel-7 | S1 | Mon 28/06/04 | Mon 12/09/05 | 100% | SP-040465 | - | - | - | - | - |  |  | SP-30 |  | Mon 30/08/04 | Fri 27/06/08
6260 | 31077 | Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN) | PNPAN | 1 | Rel-7 | S1 | Thu 08/12/05 | Thu 08/12/05 | 100% | SP-050386 | - | Vodafone | armin.toepfer@vodafone.com | - | - |  |  | SP-30 |  | Thu 21/04/05 | Thu 22/12/05
6261 | 31087 | Deleted - Study on Customised Alerting Tone (CAT) Requirements (was duplicated) | - | 1 | Rel-7 | S1 | Fri 30/06/06 | Fri 30/06/06 | 100% | SP-050607 | - | - | - | Awaiting MCC SA3 input | - |  |  | SP-31 |  | Fri 04/11/05 | Wed 22/03/06
6262 | 732028 | Deleted - IMS security extensions (covered by UID33027) | IMS-SE | 1 | Rel-7 | S3 | Thu 08/12/05 | Thu 08/12/05 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | - | - |  |  | SP-30 |  | Mon 20/06/05 | Thu 22/12/05
6263 | 32029 | Deleted - Study on applicability of GALILEO for LCS | Galileo | 1 | Rel-7 | S2 | Thu 30/06/05 | Thu 30/06/05 | 100% | SP-020541 | - | - | - | - | - |  |  | SP-25 |  | Fri 08/11/02 | Wed 08/09/04
6264 | 32058 | Deleted - TR on Stage 2 | - | 2 | Rel-7 | S2 | Thu 30/06/05 | Thu 30/06/05 | 100% | - | - | - | - | - | - |  |  | SP-25 |  | Wed 23/07/03 | Thu 21/10/04
6265 | 50095 | Deleted - GERAN review of the TR | - | 2 | Rel-7 | GP | Thu 30/06/05 | Thu 30/06/05 | 100% | - | - | - | - | - | - |  |  | SP-26 |  | Wed 23/07/03 | Mon 06/12/04
6266 | 32076 | Deleted - Study on Stage 2 (IMS services using CS bearers) | IRTSD-IMSCS | 1 | Rel-7 | S2 | Mon 28/06/04 | Mon 12/09/05 | 100% | SP-040479 | - | Nortel | Mark Watson | SP-30: S2 has no intention for TR completion | 23.899 |  |  | SP-30 |  | Mon 30/08/04 | Thu 26/06/08
6267 | 32099 | Deleted - VoIMS bearer related enhancements | VoIMS | 1 | Rel-7 | S2 | Fri 21/07/06 | Fri 21/07/06 | 100% | - | - | - | - | Created by MCC to group all VoIMS related items, after consultation of chairs | - |  |  | SP-32 |  | Thu 15/09/05 | Wed 25/06/08
6268 | 32098 | Deleted - Study on enhancement of radio performance for VoIMS | - | 2 | Rel-7 | S2 | Fri 21/07/06 | Fri 21/07/06 | 100% | SP-050351 | - | Nortel | Laurence Lautier (lautierl@nortel.com) | WID approved SP#28. SA2#52 stopped | 23.807 |  |  | SP-32 |  | Wed 22/06/05 | Wed 31/05/06
6269 | 32112 | Deleted - Study on IMS enhancements and optimizations for real time communication. | IMS-RT | 1 | Rel-7 | S2 | Mon 10/10/05 | Fri 01/06/07 | 100% | SP-050492 | - | Ericsson | stephen.terrill@ericsson.com | abandoned at 65% | 23.818 |  |  | SP-35 |  | Thu 16/02/06 | Fri 22/06/07
6270 | 32117 | Deleted - Study on Terminating Session handling | CSIterm | 1 | Rel-7 | S2 | Mon 09/01/06 | Fri 29/12/06 | 100% | SP-050811 | - | Samsung | - | SP#32 Jun 2006 Study abandoned => spin-off Implementation work UID_320029 | 23.819 |  |  | SP-32 |  | Tue 20/12/05 | Mon 30/06/08
6271 | 34040 | Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) | - | 1 | Rel-7 | S4 | Fri 22/06/07 | Fri 22/06/07 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP-38 stopped | 26.967 |  |  | SP-38 |  | Sun 10/12/06 | Fri 22/06/07
6272 | 35045 | Deleted - Study on IRP usage scenarios | OAM-Study | 1 | Rel-7 | S5 | Fri 02/09/05 | Thu 07/12/06 | 100% | SP-050303 | - | Lucent | - | - | 32.8xy |  |  | SP-32 |  | Fri 17/06/05 | Thu 29/03/07
6273 | 360009 | Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053) | RANFS-InterfCanc | 1 | Rel-7 | R4 | Wed 28/03/07 | Wed 28/03/07 | 100% | - | - | - | - | Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | - |  |  | SP-38 |  | Thu 21/06/07 | Thu 10/01/08
6274 | 50552 | Deleted - Study on enhanced support of Video Telephony | VIDGER | 1 | Rel-7 | GP | Fri 30/06/06 | Fri 30/06/06 | 100% | GP-042221 | - | Ericsson | stefan.g.eriksson@ericsson.com | FS CLOSED at G#28 (no input) | - |  |  | SP-32 |  | Fri 15/10/04 | Thu 09/03/06
6275 | 0 | --- RELEASE 6 --- | - | 1 | Rel-6 | NP,GP,RP,SP,TP | Fri 28/06/02 | Fri 30/12/05 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
6276 | 1216 | Rel-6 Improvements of Radio Interface | - | 1 | Rel-6 | R2,R4,R5 | Mon 14/08/00 | Fri 01/12/06 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 08/07/04
6277 | 20032 | Improved support of IMS Realtime Services using HSDPA/EDCH | RInImp-IMSRealTime | 2 | Rel-6 | R2 | Tue 15/03/05 | Wed 14/12/05 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | - | - |  |  |  |  | Mon 20/06/05 | Fri 13/01/06
6278 | 24006 | Improving Receiver Performance Requirements for the FDD UE | RInImp-UERecPerf | 2 | Rel-6 | R4 | Fri 08/03/02 | Fri 19/09/03 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | 25.101 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
6279 | 24004 | Base station classification for FDD | RInImp-BSClass-FDD | 2 | Rel-6 | R4 | Mon 14/08/00 | Wed 04/12/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 16/09/02 | Thu 08/07/04
6280 | 1476 | FDD Base station classification | - | 3 | Rel-6 | R4 | Mon 14/08/00 | Wed 04/12/02 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | 25.104, 25.141 |  |  |  |  | Wed 26/07/00 | Thu 08/07/04
6281 | 24007 | UMTS-850 | RInImp-UMTS850 | 2 | Rel-6 | R4 | Fri 06/12/02 | Fri 12/12/03 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | Introduction of UMTS850 (Band V) in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331, 25.942 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
6282 | 24009 | DS-CDMA introduction in the 800 MHz band | RInImp-UMTS800 | 2 | Rel-6 | R4 | Fri 14/03/03 | Fri 12/12/03 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | Introduction of UMTS800 in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
6283 | 24010 | UMTS 1.7/2.1 GHz | RInImp-UMTS1721 | 2 | Rel-6 | R4 | Fri 14/03/03 | Fri 14/03/03 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | Introduction of UMTS1700/2100 (Band IV) | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
6284 | 25010 | Conformance Test Aspects – UMTS 1.7/2.1 GHz Band | RInImp-UMTS1721_Test | 2 | Rel-6 | R5 | Fri 10/03/06 | Fri 01/12/06 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | TS34.121, TS34.108 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
6285 | 24013 | Improved Receiver Performance Requirements for HSDPA | RInImp-HSPerf | 2 | Rel-6 | R4,R5 | Fri 19/09/03 | Fri 09/06/06 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | - | - |  |  |  |  | Tue 13/01/04 | Thu 08/07/04
6286 | 20011 | Improved Minimum Performance Requirements for HSDPA UE categories 7 and 8 | RInImp-HSPerf-10code | 3 | Rel-6 | R4 | Wed 15/09/04 | Fri 09/06/06 | 100% | - | - | Nokia | jussi.numminen@nokia.com | Approved at RP#25 as RP-040375 | 25.101 |  |  |  |  | Mon 27/09/04 | Fri 13/01/06
6287 | 25001 | Testing of Improved Minimum Performance for HSDPA | RInImp-HSPerf-10Code_Test | 3 | Rel-6 | R5 | Fri 19/09/03 | Thu 16/03/06 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
6288 | 24014 | Performance Requirements of Receive Diversity for HSDPA | RInImp-HSPerf-RxDiv | 3 | Rel-6 | R4 | Mon 15/12/03 | Tue 07/06/05 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | - | 25.101 |  |  |  |  | Tue 13/01/04 | Fri 25/03/05
6289 | 25002 | Testing of Performance of Receiver diversity for HSDPA | RInImp-HSPerf-RxDiv_Test | 3 | Rel-6 | R5 | Fri 19/09/03 | Thu 16/03/06 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
6290 | 3 | Rel-6 RAN Feasibility Studies | - | 1 | Rel-6 | RP | Mon 14/08/00 | Mon 14/03/05 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 07/12/03 | Sun 07/12/03
6291 | 23007 | FS of the improved access to UE measurement data for CRNC to support TDD RRM | RANimp-RRMopt-FSUEMsD | 2 | Rel-6 | R3 | Fri 06/12/02 | Thu 18/12/03 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.801, 25.423 |  |  |  |  | Thu 13/02/03 | Thu 21/10/04
6292 | 1506 | FS on Radio link performance enhancements | RInImp-Rlperf | 2 | Rel-6 | R1 | Mon 14/08/00 | Tue 14/09/04 | 100% | - | - | Nokia | antti.toskala@nokia.com | Study finished at RP#25 | 25.899 |  |  |  |  | Thu 02/10/03 | Wed 13/10/04
6293 | 21000 | FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD | RInImp-IfIsMLCR | 2 | Rel-6 | R1 | Fri 14/12/01 | Fri 19/09/03 | 100% | - | - | Samsung | Li Xiao Qiang (xqli@samsung.co.kr) | - | 25.888 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
6294 | 21003 | FS for the analysis of OFDM for UTRAN enhancement | RInImp-FSOFDM | 2 | Rel-6 | R1 | Mon 10/06/02 | Mon 14/06/04 | 100% | - | - | Nortel | Sarah Boumendil | - | 25.892 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
6295 | 21004 | FS on Uplink Enhancements for Dedicated Transport Channels | RInImp-FSUpDTrCh | 2 | Rel-6 | R1 | Fri 06/09/02 | Fri 12/03/04 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.896 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
6296 | 21005 | FS on Analysis on Higher Chip Rates for UTRA TDD evolutions | RInImp-FSVHCRTDD | 2 | Rel-6 | R1 | Fri 06/09/02 | Tue 14/09/04 | 100% | - | - | IPWireless | mbeale@ipwireless.com | Study finished at RP#25 | 25.895 |  |  |  |  | Thu 02/10/03 | Wed 13/10/04
6297 | 24011 | FS on Low Output Powers for general purpose FDD BSs | RInImp-FSLoPw | 2 | Rel-6 | R3 | Fri 13/06/03 | Fri 12/03/04 | 100% | - | - | Telefónica | Ana Burgos (burgos_a@tsm.es) | - | 25.807 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
6298 | 21007 | FS on Uplink enhancements for UTRA TDD | RInImp-FSUpEnhTDD | 2 | Rel-6 | R1 | Fri 06/06/03 | Mon 14/03/05 | 100% | - | - | Interdigital | Marian.Rudolf@InterDigital.com | - | 25.804 |  |  |  |  | Thu 02/10/03 | Fri 25/03/05
6299 | 24005 | FS on UE antenna efficiency test methods performance requirements (2) | RInImp-UEAnTM2 | 2 | Rel-6 | R4 | Fri 08/03/02 | Fri 06/09/02 | 100% | - | - | Allgon | Alf Ahlström (alf.ahlstrom@pwav.com) | The RInImp-UEAnTM FS was re-opened at TSG RP#15 upon request from WG4 | - |  |  |  |  | Thu 30/05/02 | Thu 08/07/04
6300 | 23006 | Deleted - FS on the evolution of the UTRAN architecture | RANimp-FSEvo | 2 | Rel-6 | R3 | Mon 09/09/02 | Tue 14/12/04 | 100% | - | - | Nokia | woonhee.hwang@nsn.com, Antti.Toskala@nokia.com | Study Closed, work will continue within the FS on evolved UTRA and UTRAN | - |  |  | RP-26 |  | Mon 16/09/02 | Thu 13/01/05
6301 | 20003 | FDD Enhanced Uplink | EDCH | 1 | Rel-6 | R2,R1,R3,R4,R5 | Mon 15/03/04 | Fri 14/09/07 | 100% | - | - | Ericsson | Joakim Bergström | - | - |  |  |  |  | Thu 18/03/04 | Thu 08/07/04
6302 | 20004 | FDD Enhanced Uplink - Stage 2 | EDCH-Stage2 | 2 | Rel-6 | R2 | Mon 15/03/04 | Tue 14/12/04 | 100% | - | - | - | - | - | 25.309 |  |  |  |  | Sun 21/03/04 | Thu 13/01/05
6303 | 20005 | FDD Enhanced Uplink - Physical Layer | EDCH-Phys | 2 | Rel-6 | R1 | Mon 15/03/04 | Mon 14/03/05 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.211, 25.212, 25.213, 25.214, 25.215 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
6304 | 20006 | FDD Enhanced Uplink - Layer 2 and 3 Protocol Aspects | EDCH-L23 | 2 | Rel-6 | R2 | Mon 15/03/04 | Mon 14/03/05 | 100% | - | - | Ericsson | Joakim Bergström | - | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
6305 | 20007 | FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects | EDCH-IurIub | 2 | Rel-6 | R3 | Mon 15/03/04 | Mon 14/03/05 | 100% | - | - | Nortel | Saso Stojanovski | - | 25.401, 25.420, 25.423, 25.430, 25.433 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
6306 | 20008 | FDD Enhanced Uplink - RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCH-RF | 2 | Rel-6 | R4 | Mon 15/03/04 | Thu 24/06/04 | 100% | - | - | Ericsson | thomas.unshelm@ericsson.com | - | 25.101, 25.104, 25.133, 25.141 |  |  |  |  | Thu 18/03/04 | Fri 13/01/06
6307 | 25003 | Conformance Test Aspects – FDD Enhanced Uplink | EDCH_Test | 2 | Rel-6 | R5 | Fri 03/06/05 | Fri 14/09/07 | 100% | - | - | Ericsson | Leif.Mattisson@ericsson.com | - | 34.108, 34.109, 34.121, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 18/03/04 | Wed 16/06/10
6308 | 9 | Rel-6 RAN improvements | - | 1 | Rel-6 | RP,S5 | Mon 09/09/02 | Mon 14/03/05 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Fri 31/03/00 | Thu 08/07/04
6309 | 624 | RAB support enhancement | - | 2 | Rel-6 | R2 | Fri 14/03/03 | Mon 14/03/05 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | building block without particular end date | 25.862 |  |  |  |  | Fri 31/03/00 | Thu 13/01/05
6310 | 21008 | Optimization of downlink channelisation code utilisation | RANimp-RABSE-CodeOptFDD | 3 | Rel-6 | R1 | Fri 12/03/04 | Mon 14/03/05 | 100% | - | - | Nortel | Sarah Boumendil | - | - |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
6311 | 21009 | optimization of channelisation code utilisation for 3.84 Mcps TDD | RANimp-RABSE-CodOptTDD | 3 | Rel-6 | R1 | Mon 15/03/04 | Mon 14/03/05 | 100% | - | - | IPWireless | Nicholas Anderson | WIDS modified in RP#26, RP-040551 | - |  |  |  |  | Thu 18/03/04 | Fri 13/01/06
6312 | 20013 | HS-DPCCH ACK/NACK Enhancement | RANimp-RABSE-ACKNACK | 3 | Rel-6 | R1 | Wed 15/09/04 | Tue 14/12/04 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | Approved at RP#25 as RP-040390 | 25.212, 25.214, 24.331, 25.433 |  |  |  |  | Mon 27/09/04 | Fri 25/03/05
6313 | 23009 | Deleted - Iu enhancements for IMS support in RAN | RANimp-RABSE-IuEnhIMS | 3 | Rel-6 | R3 | Fri 14/03/03 | Thu 03/06/04 | 100% | - | - | Nortel | Philippe.Godin@nortelnetworks.com | Closed RP#24 due to the lack of progress | - |  |  | RP-24 |  | Thu 27/03/03 | Fri 13/01/06
6314 | 23005 | Deleted - Improvement of RRM across RNS and RNS/BSS | RANimp-RRM1 | 3 | Rel-6 | R3 | Fri 05/12/03 | Fri 05/12/03 | 100% | - | - | Nokia | antti.toskala@nokia.com | abandoned RP-23 | - |  |  | RP-23 |  | Tue 19/10/04 | Thu 21/10/04
6315 | 20999 | Beamforming Enhancements | RANimp-BFE | 2 | Rel-6 | R1 | Fri 19/09/03 | Fri 19/12/03 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | 24.215, 25.423, 25.425, 25.433, 25.435 |  |  |  |  | Thu 29/11/01 | Thu 08/07/04
6316 | 23012 | Rel-6 RRM optimization for Iur and Iub | RANimp-RRMopt-UEMsD | 2 | Rel-6 | R3 | Fri 19/09/03 | Fri 12/03/04 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Thu 27/03/03 | Thu 08/07/04
6317 | 23014 | Improved access to UE measurement data for CRNC to support TDD RRM | - | 3 | Rel-6 | R3 | Fri 19/09/03 | Fri 12/03/04 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.423 |  |  | RP-22 |  | Thu 02/10/03 | Thu 13/01/05
6318 | 23010 | Remote Control of Electrical Tilting Antennas | RANimp-TiltAnt | 2 | Rel-6 | R3,S5 | Fri 14/03/03 | Thu 16/09/04 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | - | - |  |  |  |  | Thu 27/03/03 | Wed 14/04/04
6319 | 23015 | Tilting Antenna - RAN aspects | - | 3 | Rel-6 | R3 | Fri 14/03/03 | Tue 14/09/04 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | Finished at RP#25 | 25.460, 25.461, 25.462, 25.463 |  |  |  |  | Thu 27/03/03 | Wed 13/10/04
6320 | 35023 | OAM&P impacts | RANimp-TiltAnt-OAM | 3 | Rel-6 | S5 | Fri 27/02/04 | Thu 16/09/04 | 100% | S5-048270 | - | Vodafone | Adrian.Neal@vodafone.com | SP#25 09/2004 completed | 32.804, 32.64x |  |  |  |  | Tue 30/03/04 | Fri 13/01/06
6321 | 23011 | Network Assisted Cell Change (NACC) from UTRAN to GERAN - network-side aspects | RANimp-NACC | 2 | Rel-6 | R3 | Mon 09/09/02 | Tue 15/06/04 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | - | - |  |  |  |  | Thu 27/03/03 | Thu 08/07/04
6322 | 32023 | Location Services enhancements 2 | LCS2 | 1 | Rel-6 | S2,S5,N4,R2,R4,R5,OMA | Mon 15/01/01 | Thu 16/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Sat 02/06/12
6323 | 32024 | Improvement on Le interface | - | 2 | Rel-6 | S2,OMA | Mon 17/06/02 | Wed 15/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Mon 21/05/12
6324 | 32051 | Stage 2 for Improvement on Le interface | - | 3 | Rel-6 | S2 | Mon 17/06/02 | Mon 22/09/03 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
6325 | 32053 | Stage 3 - impacts MLP (Mobile Location Protocol) | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Wed 15/12/04 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6326 | 32001 | Enhanced support for anonymity and user privacy | - | 2 | Rel-6 | S2,OMA | Mon 08/07/02 | Wed 15/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Wed 19/09/01 | Mon 21/05/12
6327 | 32047 | Stage 2 for Enhanced support for anonymity and user privacy | - | 3 | Rel-6 | S2 | Mon 08/07/02 | Fri 27/06/03 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
6328 | 32054 | Stage 3 - impacts MLP and RLP | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Wed 15/12/04 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6329 | 32025 | Enhanced inter-GMLC interface | - | 2 | Rel-6 | S2,OMA | Mon 24/06/02 | Wed 15/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Wed 19/09/01 | Mon 21/05/12
6330 | 32048 | Stage 2 for Enhanced inter-GMLC interface | - | 3 | Rel-6 | S2 | Mon 24/06/02 | Fri 05/09/03 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
6331 | 32055 | Stage 3 - definition of RLP and PCP | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Wed 15/12/04 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6332 | 32012 | Location Services support for IMS public identities | - | 2 | Rel-6 | S2,OMA | Mon 24/02/03 | Wed 15/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Thu 24/01/02 | Mon 21/05/12
6333 | 32049 | Stage 2 for Location Services support for IMS public identities | - | 3 | Rel-6 | S2 | Mon 24/02/03 | Fri 23/01/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
6334 | 32056 | OMA Stage 3 for Location Services support for IMS public identities - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Wed 15/12/04 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6335 | 32026 | New area event for location service triggering reports | - | 2 | Rel-6 | S2,N4,OMA | Mon 03/06/02 | Wed 15/12/04 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Mon 21/05/12
6336 | 32050 | Stage 2 for New area event for location service triggering reports | - | 3 | Rel-6 | S2 | Mon 03/06/02 | Fri 27/06/03 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
6337 | 14015 | Stage 3 for UE-CN signalling | - | 3 | Rel-6 | N4 | Thu 09/10/03 | Tue 31/08/04 | 100% | SP-030127 | - | Nokia | - | Current stage 3 fullfills stage 2 | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6338 | 32057 | Stage 3 for New area event for location service triggering reports - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Wed 15/12/04 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
6339 | 20001 | UE positioning for Location Services enhancements 2 | LCS2-UEpos | 2 | Rel-6 | R2,R4,R5 | Mon 15/01/01 | Tue 14/09/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 16/09/02 | Mon 21/05/12
6340 | 2475 | Open SMLC-SRNC Interface within the UTRAN to support UTRAN Rel-4 positioning methods | LCS-Rel4Pos | 3 | Rel-6 | R2 | Mon 15/01/01 | Fri 19/09/03 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | 25.305, 25.401, 25.450, 25.452, 25.453 |  |  |  |  | Tue 20/03/01 | Mon 21/05/12
6341 | 24012 | A-GPS minimum performance specification | LCS-UEPos-AGPSPerf | 3 | Rel-6 | R4,R5 | Fri 06/06/03 | Tue 14/09/04 | 100% | - | - | AT&T Wireless | donglin.shen@attws.com | RP#25 completed (FDD) | new 25.171, 34.171 (testing) |  |  |  |  | Fri 04/07/03 | Mon 21/05/12
6342 | 22002 | Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods | LCS2-UEpos-FSBlank | 3 | Rel-6 | R2 | Mon 01/07/02 | Fri 19/09/03 | 100% | - | - | Cambridge Positioning Systems | david.bartlett@cursor-system.com | RP#38 Work stopped | new 25.894 |  |  | RP-38 |  | Fri 21/06/02 | Mon 21/05/12
6343 | 2457 | Deleted - UE positioning enhancements - other methods | LCS2-UEpos-enh | 3 | Rel-6 | R2 | Fri 26/09/03 | Fri 26/09/03 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | RP#24 Work stopped | - |  |  | RP-24 |  | Tue 19/10/04 | Mon 21/05/12
6344 | 35035 | LCS charging | LCS2-CH | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/12/04 | 100% | SP-040778 | - | France Telecom | alain.bibas@orange-ft.com | SP#26 completed | new 32.271 |  |  |  |  | Fri 29/10/04 | Mon 21/05/12
6345 | 1571 | Rel-6 Security enhancements | SEC16 | 1 | Rel-6 | S3 | Wed 03/01/01 | Fri 26/11/04 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID. Acronym changed from "SEC1, Rel-6" | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
6346 | 2026 | Enhanced HE control of security (including positive authentication reporting) | - | 2 | Rel-6 | S3 | Wed 03/01/01 | Thu 25/09/03 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID S3-000490 (Enhanced home control of security by HE) | 33.102 |  |  |  |  | Fri 22/09/00 | Mon 08/08/11
6347 | 2027 | Deleted - SEC1 Stage 2 (Enhanced HE control of security) | - | 3 | Rel-6 | S3 | Wed 03/01/01 | Fri 14/06/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-16 |  | Fri 22/09/00 | Mon 12/03/01
6348 | 33006 | Rel-6 Network Domain Security | SEC1-NDS | 3 | Rel-6 | S3 | Mon 17/06/02 | Thu 25/09/03 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID S3-000606 (Network Domain Security) | 33.102, 33.103, 33.105 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
6349 | 33007 | Rel-6 IP network layer security (NDS/IP) | SEC1-NDS-IP | 4 | Rel-6 | S3 | Mon 17/06/02 | Thu 25/09/03 | 100% | SP-000420 | - | - | - | SP#9 approved WID S3-000626 (Access security for IP-based services) | 33.21 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
6350 | 33017 | Network Domain Security; Authentication Framework (NDS/AF) | SEC1-NDS-AF | 2 | Rel-6 | S3 | Fri 15/02/02 | Fri 13/02/04 | 100% | SP-030108 | - | Nokia | tommi.viitanen@nokia.com | SP#19 approved WID | 33.81 |  |  |  |  | Thu 27/03/03 | Mon 08/08/11
6351 | 33019 | Key Management of group keys for Voice Group Call Services | SECGKYV | 2 | Rel-6 | S3 | Fri 26/09/03 | Fri 26/11/04 | 100% | SP-030491 | - | Vodafone | benno.tietz@vodafone.com | - | 42.068, 43.068, 44.068, 42.069, 43.069, 44.069, 31.102, 24.008, 48.008, 42.009, 43.020, New TSs (55.236, 55.205) MILENAGE algorithms |  |  |  |  | Tue 14/10/03 | Thu 13/01/05
6352 | 33020 | Network Domain Security; MAP application layer security (NDS/MAPsec) | MAPSEC | 1 | Rel-6 | S3 | Tue 06/07/04 | Wed 29/12/04 | 100% | SP-040280 | - | Vodafone | Peter.Howard@vodafone.com | SP#19 approved WID. Marked as closed 12/2008 (was marked 20% complete) | 33.2 |  |  |  |  | Fri 25/07/03 | Mon 08/08/11
6353 | 32021 | IMS Phase 2 | IMS2 | 1 | Rel-6 | S1,S2,S3,S5,NP,R5 | Mon 28/08/00 | Fri 14/09/07 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 25/03/02 | Thu 08/07/04
6354 | 14014 | Enhancements to the Cx and Sh interfaces | IMS2-CCR | 2 | Rel-6 | N4 | Fri 06/06/03 | Tue 31/08/04 | 100% | NP-030229 | - | - | - | Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done. | - |  |  |  |  | Mon 09/06/03 | Fri 25/03/05
6355 | 25009 | Conformance Test Aspects – IMS Call Control Rel-6 enhancements | IMS2_CCR_Test | 2 | Rel-6 | R5 | Fri 10/03/06 | Fri 14/09/07 | 100% | - | - | Ericsson | Jacob.John@motorola.com, Leif.Mattisson@ericsson.com | - | 34.229-1, 34.229-2, 34.229-3, 34.108 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
6356 | 31025 | IMS Group Management | IMSGM | 2 | Rel-6 | S1 | Thu 14/03/02 | Wed 08/12/04 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Wed 08/09/04
6357 | 31026 | Stage 1 - TS on IMS group management | - | 3 | Rel-6 | S1 | Thu 14/03/02 | Mon 09/12/02 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Sun 07/12/03
6358 | 32036 | Stage 2 for IMS Group Management | - | 3 | Rel-6 | S2 | Mon 26/05/03 | Wed 31/12/03 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Tue 08/06/04
6359 | 11036 | Stage 3 for IMS Group management (e.g. chat) | - | 3 | Rel-6 | N1 | Fri 13/12/02 | Wed 08/12/04 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on CPCP in Rel-6. Complete, if unresolved IETF dependencies are dropped (-> LS to CN plenary) | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
6360 | 11037 | IMS Conferencing | - | 2 | Rel-6 | N1 | Mon 04/11/02 | Wed 08/12/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 13/01/03 | Mon 13/01/03
6361 | 32037 | Stage 2 for IMS Conferencing | - | 3 | Rel-6 | S2 | Mon 04/11/02 | Wed 31/12/03 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Fri 12/03/04
6362 | 32038 | Stage 3 for IMS Conferencing | - | 3 | Rel-6 | N1 | Fri 13/12/02 | Wed 08/12/04 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on IETF dependenciES in CP-150Rel-6. Higher figure if CPCP is dropped (-> LS to CN plenary) | - |  |  |  |  | Fri 28/02/03 | Fri 25/03/05
6363 | 31022 | IMS Messaging | IMSM | 2 | Rel-6 | S1 | Thu 14/03/02 | Fri 30/12/05 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Wed 08/09/04
6364 | 31023 | TR on support of messaging in the IMS | IMSM-TR | 3 | Rel-6 | S1 | Thu 14/03/02 | Mon 09/12/02 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | New 22.940 |  |  |  |  | Thu 21/03/02 | Tue 07/09/10
6365 | 31034 | Stage 1 22.340 | IMSM-TS | 3 | Rel-6 | S1 | Mon 11/11/02 | Wed 11/12/02 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.34 |  |  |  |  | Mon 13/01/03 | Tue 07/09/10
6366 | 31033 | CRs to 22.140 & 22.228 | IMSM-CR | 3 | Rel-6 | S1 | Thu 14/03/02 | Mon 17/03/03 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.140,22.228 |  |  |  |  | Mon 13/01/03 | Tue 07/09/10
6367 | 32700 | Stage 2 for IMS Messaging | - | 3 | Rel-6 | S2 | Mon 04/11/02 | Tue 31/08/04 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 26/09/02 | Wed 08/09/04
6368 | 11039 | Stage 3 for IMS Messaging | - | 3 | Rel-6 | N1 | Fri 13/12/02 | Wed 08/12/04 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
6369 | 60001 | SIP/SIMPLE Instant messaging | - | 3 | Rel-6 | OMA | Thu 01/01/04 | Fri 30/12/05 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
6370 | 11040 | Additional SIP Capabilities support not covered by Rel-5 | - | 2 | Rel-6 | N1 | Mon 11/11/02 | Fri 17/06/05 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 13/01/03 | Mon 13/01/03
6371 | 32041 | Stage 2 for add SIP cap (e.g. forking) | - | 3 | Rel-6 | S2 | Mon 11/11/02 | Fri 20/02/04 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Fri 12/03/04
6372 | 32042 | Stage 3 for Additional SIP Capabilities | - | 3 | Rel-6 | N1 | Fri 13/12/02 | Wed 08/09/04 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Thu 02/06/05
6373 | 11052 | Procedured associated with IMS-ALG | - | 3 | Rel-6 | N1 | Mon 06/09/04 | Fri 17/06/05 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 20/04/05 | Thu 02/06/05
6374 | 11041 | Review additional SIP Capabilities against IMS | - | 2 | Rel-6 | N1 | Fri 13/12/02 | Wed 08/09/04 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
6375 | 2048 | Interworking between IMS and IP networks | IMS-CCR-IWIP | 2 | Rel-6 | N3 | Mon 28/08/00 | Wed 08/12/04 | 100% | NP-020091 | - | BT | nigel.holland@bt.com | [DAB 14.02.02] - end date pushed back to March 2003 | 23.821, 29.061, 29.162 |  |  |  |  | Mon 09/10/00 | Mon 13/01/03
6376 | 13004 | Interworking for 3GPP_SIP and IETF_SIP | - | 3 | Rel-6 | N3 | Mon 28/08/00 | Fri 13/06/03 | 100% | - | - | Siemens | Thomas.Belling@nsn.com | [DAB - 20.08.03] - CN Part of TR Complete @ CN#20 | New 29.962 |  |  |  |  | Thu 28/02/02 | Mon 15/09/03
6377 | 13005 | Interworking for IPv6 to IPv4 | - | 3 | Rel-6 | N3 | Mon 28/08/00 | Wed 08/12/04 | 100% | - | - | - | - | - | 29.163 |  |  |  |  | Thu 28/02/02 | Wed 09/03/05
6378 | 11044 | Interworking for IPv6 to IPv4 (SIP / SDP aspects) | - | 3 | Rel-6 | N1 | Tue 11/05/04 | Wed 08/09/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/03/04 | Wed 08/09/04
6379 | 11017 | stage 3 of interworking with non-IMS IP networks | - | 3 | Rel-6 | N1 | Wed 14/03/01 | Wed 08/09/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Wed 08/09/04
6380 | 2047 | Interworking between IMS and CS networks | IMS-CCR-IWCS | 2 | Rel-6 | N3 | Mon 28/08/00 | Thu 18/03/04 | 100% | NP-030292 | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | [DAB - 25.05.04] - CN3 consider this work to be complete | 29.163, 29.061, 24.228, and New CN4 specification |  |  |  |  | Thu 24/01/02 | Thu 09/09/04
6381 | 14001 | Mn interface (IM-MGW to MGCF) enhancements (CN4 Part) | IMS-CCR-Mn | 2 | Rel-6 | N4 | Tue 07/08/01 | Wed 01/09/04 | 100% | - | - | - | - | TISPAN issue is open | - |  |  |  |  | Mon 08/10/01 | Wed 09/03/05
6382 | 31036 | Study of subscriber and operators relationship in IMS and related ISIM requirements for Rel 6” | - | 2 | Rel-6 | S1 | Fri 15/11/02 | Thu 12/12/02 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Mon 13/01/03 | Fri 04/07/03
6383 | 33012 | Lawful Interception in Rel-6 architecture | SEC1-LI | 2 | Rel-6 | S3 | Mon 09/12/02 | Thu 18/12/03 | 100% | SP-030106 | - | Reg TP, Nortel | berthold.wilhelm@regtp.de, Ron Ryan | Acronym changed from "SEC1-LI, Rel6" | 33.106, 33.107, 33.108 |  |  |  |  | Wed 15/01/03 | Tue 24/03/15
6384 | 31042 | IMS Subscription and access scenarios | - | 2 | Rel-6 | S1 | Mon 16/12/02 | Fri 13/06/03 | 100% | - | - | TeliaSonera | FRANK, Robert | - | 22.8 |  |  |  |  | Fri 28/03/03 | Tue 31/08/10
6385 | 35032 | IMS charging | IMS2-CH | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/12/04 | 100% | SP-030049 | - | Ericsson | Patrik TEPPO | SP#26 12/2004 completed | 32.26 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6386 | 11051 | IMS Management objects | - | 2 | Rel-6 | N1 | Fri 03/09/04 | Fri 04/11/05 | 100% | NP-040494 | - | - | - | - | 24.167 |  |  |  |  | Mon 06/12/04 | Wed 09/03/05
6387 | 32027 | Deleted - Stage 2 of IMS Phase 2 | - | 2 | Rel-6 | S2 | Fri 19/09/03 | Fri 19/09/03 | 100% | SP-020544 | - | - | - | - | - |  |  | SP-21 |  | Tue 19/10/04 | Thu 21/10/04
6388 | 32063 | 3GPP Enablers for services like Push to Talk over Cellular (PoC) | PoC | 1 | Rel-6 | S2,S4,S5 | Mon 08/09/03 | Thu 09/06/05 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | - |  |  |  |  | Wed 15/10/03 | Thu 08/07/04
6389 | 32068 | Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC) | - | 2 | Rel-6 | S2 | Mon 08/09/03 | Tue 30/11/04 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | 23.979 |  |  |  |  | Wed 15/10/03 | Mon 06/12/04
6390 | 60002 | Dependencies on OMA PoC | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Mon 28/02/05 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | - |  |  |  |  | Wed 15/10/03 | Fri 25/03/05
6391 | 34029 | Selection of one or more PoC codec(s) for PoC | - | 2 | Rel-6 | S4 | Mon 13/09/04 | Thu 16/12/04 | 100% | - | - | - | - | Completed | 26.235, 26.236 |  |  |  |  | Fri 01/10/04 | Mon 06/12/04
6392 | 35036 | PoC charging | PoC-CH | 2 | Rel-6 | S5 | Mon 27/09/04 | Thu 09/06/05 | 100% | SP-050032 | - | Siemens | Gerald.Goermer@nsn.com | SP#28 06/2005 completed | 32.272 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6393 | 32062 | Study on Interworking aspects and migration scenarios for IPv4 based IMS Implementations | IPv4IMS | 1 | Rel-6 | S2 | Mon 08/09/03 | Fri 25/06/04 | 100% | SP-040327 | - | Siemens | Alexander Milinski | - | 23.981 |  |  |  |  | Wed 15/10/03 | Wed 18/11/09
6394 | 11032 | Interoperability and Commonality between IMS using different IP-connectivity Networks | IMSCOOP | 1 | Rel-6 | S2 | Mon 16/09/02 | Fri 12/12/03 | 100% | - | - | - | - | - | 23.864 |  |  |  |  | Thu 26/09/02 | Thu 08/07/04
6395 | 32028 | Stage 2 for Interoperability | - | 2 | Rel-6 | S2 | Mon 16/09/02 | Tue 30/09/03 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2 | 23.864 |  |  |  |  | Fri 08/11/02 | Thu 08/07/04
6396 | 32061 | Stage 2 for commonality | - | 2 | Rel-6 | S2 | Mon 16/09/02 | Fri 19/09/03 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.864 |  |  |  |  | Mon 15/09/03 | Thu 08/07/04
6397 | 11033 | Stage 3 for Interoperability and Commonality between IMS using different IP-connectivity Networks | - | 2 | Rel-6 | N1 | Mon 14/10/02 | Fri 12/12/03 | 100% | NP-020572 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Fri 08/11/02 | Fri 12/03/04
6398 | 1365 | Support of Push Services | PUSH | 1 | Rel-6 | S1 | Wed 03/01/01 | Fri 27/02/04 | 100% | SP-000669 | - | NTT Comware | Yoshinori Kitada | Changed from FS to actual support of Push | 23.976 |  |  |  |  | Wed 19/04/00 | Wed 19/01/05
6399 | 31004 | Stage 1 for Support of Push Services | - | 2 | Rel-6 | S1 | Wed 03/01/01 | Fri 14/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Fri 04/07/03
6400 | 32701 | TR 23.976 on Push Architecture | - | 2 | Rel-6 | S2 | Mon 11/11/02 | Fri 27/02/04 | 100% | SP-030126 | - | Research In Motion | Nick Alfano | - | 23.976 |  |  |  |  | Thu 26/09/02 | Thu 08/07/04
6401 | 42009 | Rel-6 Multimedia Messaging (MMS) enhancements | MMS6 | 1 | Rel-6 | T2,S1,S4,S5,OMA | Thu 15/08/02 | Wed 07/12/05 | 100% | TP-030175 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | - |  |  |  |  | Thu 26/09/02 | Mon 06/12/04
6402 | 42010 | Definition of service requirements for MMS6 | MMS6-SR | 2 | Rel-6 | S1 | Fri 15/11/02 | Fri 19/12/03 | 100% | - | - | - | - | - | 22.14 |  |  |  |  | Thu 26/09/02 | Fri 12/03/04
6403 | 31031 | Definition of service requirements charging | - | 3 | Rel-6 | S1 | Fri 15/11/02 | Fri 19/12/03 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.14 |  |  |  |  | Mon 13/01/03 | Fri 12/03/04
6404 | 42011 | Technical realization of MMS6 | - | 2 | Rel-6 | T2 | Fri 06/09/02 | Fri 10/12/04 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 23.14 |  |  |  |  | Thu 26/09/02 | Mon 06/12/04
6405 | 42012 | OMA dependencies | - | 2 | Rel-6 | OMA | Fri 15/08/03 | Fri 29/04/05 | 100% | - | - | - | - | - | OMA specs |  |  |  |  | Thu 26/09/02 | Fri 25/03/05
6406 | 42013 | MMS formats and codecs for MMS6 | MMS6-Codec | 2 | Rel-6 | S4 | Thu 15/08/02 | Wed 07/12/05 | 100% | - | - | Nokia | roberto.castagno@nokia.com | - | 26.140, 26.936 |  |  |  |  | Thu 26/09/02 | Fri 13/01/06
6407 | 42014 | Handling of private addressing schemes in MMS | - | 2 | Rel-6 | T2 | Wed 10/12/03 | Fri 10/12/04 | 100% | TP-030299 | - | T-Mobile | Steffen.Habermann@T-MOBILE.DE | - | 23.14 |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6408 | 35034 | MMS charging | MMS6-CH | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | SP-040778 | - | - | - | SP#25 09/2004 completed | 32.27 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6409 | 42015 | Deleted - FS Multiple MMS Relay/Server Architecture | - | 2 | Rel-6 | T2 | Fri 10/12/04 | Fri 10/12/04 | 100% | TP-030301 | - | Telefónica Móviles | Juan Gorospe (gorospe_j@tsm.es) | originally it was intended to create a FS TR but most likely the work will become an Annex of 23.140 | probably Annex to 23.140 |  |  | TP-26 |  | Mon 01/12/03 | Wed 08/09/04
6410 | 42005 | Rel-6 MExE enhancements | MEXE6 | 1 | Rel-6 | T2 | Fri 08/03/02 | Fri 06/06/03 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 21/03/02 | Thu 21/03/02
6411 | 42006 | MExE Rel-6 Improvements and Investigations | MEXE6-ENHANC | 2 | Rel-6 | T2 | Fri 08/03/02 | Wed 12/03/03 | 100% | TP-020017 | - | TTPCom | Lars Brenk ( (lsb_ttpcom@HOTMAIL.COM) | - | - |  |  |  |  | Thu 21/03/02 | Wed 18/11/09
6412 | 42007 | MExE Run-Time Independent Framework Feasibility Study | MEXE6-RTIF | 2 | Rel-6 | T2 | Fri 08/03/02 | Fri 06/06/03 | 100% | TP-020086 | - | Nokia Siemens Networks | balazs.bertenyi@nokia.com | - | 22.857 |  |  |  |  | Thu 21/03/02 | Tue 31/08/10
6413 | 2062 | Subscription Management | SuM | 1 | Rel-6 | S5 | Fri 20/09/02 | Thu 17/03/05 | 100% | SP-040763 | - | T-Mobile | istvan.aba@t-mobile.at | SP#27 03/2005 completed | 32.140/1, 32.171/2/5, 32.803 |  |  |  |  | Mon 09/10/00 | Fri 13/01/06
6414 | 2499 | Presence Capability | PRESNC | 1 | Rel-6 | S1,S2,S3,S4,N1,N3,N4,OMA | Mon 19/03/01 | Wed 07/12/05 | 100% | SP-010064 | - | Motorola | Mark Cataldo | merged "Presence Service Enhancements" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date | - |  |  |  |  | Fri 30/03/01 | Wed 08/09/04
6415 | 2501 | Stage 1 for Presence Capability | - | 2 | Rel-6 | S1 | Mon 19/03/01 | Fri 18/07/03 | 100% | SP-010064 | - | Motorola | Mark Cataldo | TP#16 moved Stage 1 to Rel-6 TS 22.141 (existed already in Rel-5) | 22.141 |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
6416 | 2502 | Stage 2 for Presence Capability | - | 2 | Rel-6 | S2 | Wed 12/09/01 | Fri 20/09/02 | 100% | SP-010517 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.002, 24.229, New 23.141 |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
6417 | 2503 | Stage 3 for Presence Capability | - | 2 | Rel-6 | N1,N4 | Mon 01/04/02 | Wed 08/12/04 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Dependency to 2 IETF drafts, no known work at the moment | New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328) |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
6418 | 13018 | Stage 3 (CN3 Part Pk interface) | - | 2 | Rel-6 | N3 | Mon 01/04/02 | Fri 11/03/05 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.061, 29.161 |  |  |  |  | Tue 08/06/04 | Tue 09/08/11
6419 | 34025 | Media Codecs and Formats for IMS Messaging and Presence | PRESNC-COFIMP | 2 | Rel-6 | S4 | Thu 12/06/03 | Wed 07/12/05 | 100% | SP-030212 | - | Nokia | harri.honko@nokia.com | - | 26.141, 26.936 |  |  |  |  | Fri 04/07/03 | Fri 13/01/06
6420 | 2504 | Security aspects of Presence Capability | - | 2 | Rel-6 | S3 | Mon 26/08/02 | Thu 12/12/02 | 100% | SP-020514 | - | Ericsson | krister.boman@erv.ericsson.se | SP#17 approved WID S3-020429 | - |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
6421 | 60003 | SIMPLE Presence | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Thu 31/03/05 | 100% | SP-040232 | - | - | OMA-LIAISON@mail.openmobilealliance.org | SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables | - |  |  |  |  | Tue 08/06/04 | Tue 09/08/11
6422 | 50056 | Enhanced A/Gb feasibility study | AGbEnFS | 1 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None |  |  |  |  | Thu 23/05/02 | Wed 18/11/09
6423 | 50057 | Feasibility study on A/Gb enhancements | AGbEnFS-FS | 2 | Rel-6 | G2 | Fri 30/08/02 | Fri 08/11/02 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None |  |  |  |  | Thu 23/05/02 | Wed 18/11/09
6424 | 50080 | Requirements for the support of conversational services | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
6425 | 50084 | Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Mon 13/01/03 | Wed 18/11/09
6426 | 50093 | Outline of impact and feasibility of these building blocks and their different solutions | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Mon 13/01/03 | Wed 18/11/09
6427 | 50081 | Impact on 3GPP architecture and requirement to co-ordinatge with other TSGs (CN, SA) | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
6428 | 50082 | Standardisation effort | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
6429 | 50083 | Dependency to other features of Enhanced A/Gb feasibility study | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 08/11/02 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
6430 | 50063 | Flexible Layer One for GERAN | FLOGER | 1 | Rel-6 | GP,S3 | Mon 03/01/00 | Fri 25/06/04 | 100% | GP-021018 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Tue 16/09/03
6431 | 50064 | Realisation of a Flexible Layer One | FLOGER-Real | 2 | Rel-6 | GP | Mon 03/01/00 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
6432 | 50065 | Technical Report on Realisation of a Flexible Layer One | - | 3 | Rel-6 | GP | Fri 19/04/02 | Fri 06/02/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6433 | 51002 | Architecture in 45.001 and 43.051 | - | 3 | Rel-6 | G1 | Fri 19/04/02 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6434 | 51003 | Multiplexing in 45.002 | - | 3 | Rel-6 | G1 | Fri 19/04/02 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6435 | 51004 | Channel Coding in 45.003 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | Fri 19/04/02 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6436 | 51005 | Performance Requirements in 45.005 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | Mon 03/01/00 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6437 | 51006 | Radio subsystem link control in 45.008 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | Fri 19/04/02 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6438 | 52071 | Requirements in 44.004 | - | 3 | Rel-6 | G2 | Fri 19/04/02 | Fri 23/04/04 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
6439 | 52072 | Signalling and protocol support for a Flexible Layer One | FLOGER-SigPro | 2 | Rel-6 | G2 | Fri 19/04/02 | Fri 25/06/04 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Mon 06/12/04
6440 | 52073 | Modifications to RLC/MAC in 44.060 and 44.160 | - | 3 | Rel-6 | G2 | Fri 19/04/02 | Fri 25/06/04 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
6441 | 52074 | Modifications to RRC in 44.118 and 44.018 | - | 3 | Rel-6 | G2 | Fri 19/04/02 | Fri 25/06/04 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
6442 | 52075 | Security for a Flexible Layer One | FLOGER-SecFLO | 2 | Rel-6 | S3,G2 | Fri 19/04/02 | Fri 29/08/03 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Wed 14/01/04
6443 | 52076 | Ciphering in 44.060, 44.160, 44.018, 44.118 | - | 3 | Rel-6 | S3,G2 | Fri 19/04/02 | Fri 29/08/03 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | 44.060, 44.160, 44.018, 44.118 |  |  |  |  | Thu 23/05/02 | Tue 16/09/03
6444 | 55077 | Deleted - GERAN MS Conformance test for the Flexible Layer One - DELETE | FLOGER-Msconf | 2 | Rel-6 | G4,G5 | Fri 06/02/04 | Fri 06/02/04 | 100% | GP-021022 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-27 |  | Thu 23/05/02 | Wed 09/03/05
6445 | 55078 | Deleted at TSG #27 - MS Test in 51.010 | - | 3 | Rel-6 | G4,G5 | Fri 06/02/04 | Fri 06/02/04 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-22 |  | Thu 23/05/02 | Wed 09/03/05
6446 | 55079 | Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE | FLOGER-BTSconf | 2 | Rel-6 | G3new | Fri 06/02/04 | Fri 06/02/04 | 100% | GP-021023 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-27 |  | Thu 23/05/02 | Wed 09/03/05
6447 | 53080 | Deleted at TGS #27 - BTS Test in 51.021 - DELETE | - | 3 | Rel-6 | G3new | Fri 06/02/04 | Fri 06/02/04 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-22 |  | Thu 26/09/02 | Wed 09/03/05
6448 | 50041 | Uplink TDOA feasibility study | TDOAF | 1 | Rel-6 | GP | Fri 30/11/01 | Fri 28/06/02 | 100% | GP-012794 | - | TruePosition | Bob Gross (rlgross@trueposition.com) | - | 45.811 |  |  |  |  | Mon 10/12/01 | Thu 24/04/03
6449 | 2544 | Multimedia Broadcast and Multicast Service | MBMS | 1 | Rel-6 | S1,S2,S3,S4,S5,N1,N3,R2,R4,R5,T1,GP,G2,G3new | Fri 11/05/01 | Fri 07/03/08 | 100% | - | - | - | - | SP#13 Title renamed | - |  |  |  |  | Mon 28/05/01 | Thu 26/07/12
6450 | 2545 | Stage 1 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S1 | Fri 11/05/01 | Mon 01/04/02 | 100% | - | - | - | - | - | 22.146, 22.101 |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
6451 | 32002 | Stage 2 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S2 | Mon 24/09/01 | Wed 17/03/04 | 100% | SP-010516 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Thu 26/07/12
6452 | 32702 | TR on MBMS Architectural Study | - | 3 | Rel-6 | S2 | Mon 24/09/01 | Fri 23/08/02 | 100% | - | - | - | - | - | 23.846 |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6453 | 32703 | Stage 2 MBMS Specification Work | - | 3 | Rel-6 | S2 | Mon 19/08/02 | Wed 17/03/04 | 100% | - | - | - | - | - | 23.246 |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6454 | 11030 | Support of the MBMS in CN protocols | - | 2 | Rel-6 | N1 | Tue 18/06/02 | Wed 08/12/04 | 100% | NP-040493 | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Thu 26/07/12
6455 | 13015 | Gmb interface for MBMS (CN3 part) | - | 2 | Rel-6 | N3 | Fri 29/08/03 | Wed 08/12/04 | 100% | - | - | - | - | - | 29.061 |  |  |  |  | Mon 13/10/03 | Thu 26/07/12
6456 | 33008 | Security aspects of MBMS | - | 2 | Rel-6 | S3 | Mon 01/07/02 | Fri 18/03/05 | 100% | SP-020514 | - | 3 | adrian.escott@three.co.uk | SP#17 approved WID S3-020433 | New 33.246 |  |  |  |  | Fri 08/11/02 | Thu 26/07/12
6457 | 35038 | MBMS Charging | MBMS-CH | 2 | Rel-6 | S5 | Tue 11/01/05 | Thu 09/06/05 | 100% | SP-040779 | - | - | - | SP#28 completed | 32.273 |  |  |  |  | Fri 29/10/04 | Thu 26/07/12
6458 | 31045 | MBMS User Services | - | 2 | Rel-6 | S1,S4 | Tue 13/05/03 | Thu 16/03/06 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
6459 | 31044 | Stage 1 for MBMS User Services | - | 3 | Rel-6 | S1 | Tue 13/05/03 | Thu 01/04/04 | 100% | - | - | - | - | - | 22.246 |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
6460 | 34026 | Definition of MBMS user services, media codecs, formats and transport/application protocols using MBMS | MBMS-TSMBMS | 3 | Rel-6 | S4 | Thu 12/06/03 | Thu 16/03/06 | 100% | SP-030674 | - | Nokia | igor.curcio@nokia.com | - | 26.346, 26.936, 26.946 |  |  |  |  | Fri 04/07/03 | Thu 26/07/12
6461 | 2481 | Introduction of MBMS in RAN | MBMS-RAN | 2 | Rel-6 | R2,R4 | Tue 01/01/02 | Wed 14/09/05 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | - |  |  |  |  | Tue 20/03/01 | Thu 26/07/12
6462 | 20022 | Introduction of MBMS in RAN (physical & upper layers, access network interfaces) | - | 3 | Rel-6 | R2 | Tue 01/01/02 | Tue 14/12/04 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | 25.346, 25.304, 25.321, 25.322, 25.323 |  |  |  |  | Mon 27/09/04 | Thu 26/07/12
6463 | 20020 | UE Performance Requirements for MBMS | MBMS-RAN-RF | 3 | Rel-6 | R4 | Wed 15/09/04 | Wed 14/09/05 | 100% | RP-040370 | - | Ericsson | Torgny.Palenius@ericsson.com | RP#25 approved WID RP-040370 | 25.101, 25.133 |  |  |  |  | Mon 27/09/04 | Thu 26/07/12
6464 | 25024 | MBMS UE Conformance Testing | MBMS-UEConTest | 2 | Rel-6 | R5,T1 | Fri 10/03/06 | Fri 07/03/08 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 22/09/06 | Thu 26/07/12
6465 | 25014 | RF/RRM Conformance Test Aspects – MBMS (FDD) | MBMS-RAN-RF_Test | 3 | Rel-6 | R5,T1 | Fri 02/06/06 | Fri 07/03/08 | 100% | - | - | Ericsson | leif.mattisson@ericsson.com | - | 34.108, 34.109, 34.121-1, 34.121-2 |  |  |  |  | Thu 28/02/02 | Thu 26/07/12
6466 | 25022 | Conformance Test Aspects - MBMS for 3.84 Mcps and 7.68 Mcps TDD | MBMS-UEConTest_TDH | 3 | Rel-6 | R5,T1 | Wed 20/09/06 | Fri 07/12/07 | 100% | - | - | IPWireless | Timothy Speight (tspeight@ipwireless.com) | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Thu 26/07/12
6467 | 25023 | Signalling Conformance Test Aspects – MBMS for LCR TDD | MBMS-UEConTest_SIGTDL | 3 | Rel-6 | R5,T1 | Wed 20/09/06 | Fri 07/12/07 | 100% | - | - | Datang | zhaojian@datangmobile.cn | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Thu 26/07/12
6468 | 25011 | Conformance Test Aspects – MBMS | MBMS_Test | 3 | Rel-6 | R5,T1 | Fri 10/03/06 | Fri 14/09/07 | 100% | - | - | Qualcomm | Shubhang Vora (svora@qualcomm.com) | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Thu 26/07/12
6469 | 25038 | Conformance Test Aspects - 1.28 Mcps TDD MBMS RF/RRM | MBMS-UEConTest_RFTDL | 3 | Rel-6 | R5,T1 | Fri 01/06/07 | Fri 07/12/07 | 100% | - | - | Datang | chenxiaozhong@datangmobile.cn | - | 34.108, 34.109, 34.122 |  |  |  |  | Thu 28/02/02 | Thu 26/07/12
6470 | 50085 | Support of MBMS in GERAN | MBMS-GERAN | 2 | Rel-6 | GP,G2,G3new | Thu 30/08/01 | Fri 28/01/05 | 100% | GP-022566 | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6471 | 50086 | MBMS Impact on the logical and physical channels | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6472 | 52085 | MBMS Re-synchronisation at cell change | - | 3 | Rel-6 | G2 | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6473 | 50098 | Simultaneous support of MBMS services | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
6474 | 50099 | Simultaneous support of MBMS and non-MBMS services | - | 3 | Rel-6 | GP | Thu 30/08/01 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
6475 | 50100 | MBMS Resynchronization at cell change | - | 3 | Rel-6 | GP | Thu 30/08/01 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
6476 | 50087 | MBMS Decision making process between point-to-point or point-to-multipoint configurations | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6477 | 50088 | MBMS channel allocations procedures to multiple MSs | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6478 | 50089 | MBMS Changes to the Gb interface | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6479 | 50090 | GERAN specific changes to the Iu-ps interface for MBMS | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6480 | 50091 | Interaction between MBMS and Iu-flex | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6481 | 50092 | MBMS Security aspects | - | 3 | Rel-6 | GP | Fri 30/08/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
6482 | 53081 | MBMS-GERAN - MS conformance tests | - | 3 | Rel-6 | G3new | Fri 25/01/02 | Fri 28/01/05 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
6483 | 55091 | Deleted - MS conformance tests - G5 | - | 3 | Rel-6 | G5 | Fri 27/06/03 | Fri 27/06/03 | 100% | - | - | - | - | - | - |  |  | GP-19 |  | Wed 20/10/04 | Thu 26/07/12
6484 | 31006 | Speech Recognition and Speech Enabled Services | SRSES | 1 | Rel-6 | S1,S2,S4,OMA | Mon 08/10/01 | Fri 30/12/05 | 100% | SP-010572 | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Wed 08/09/04
6485 | 31007 | Speech Enabled Services Based on Distributed Speech Recognition (DSR) | DSR | 2 | Rel-6 | S1 | Mon 08/10/01 | Fri 15/03/02 | 100% | SP-010581 | - | Qualcomm | Dwilliams@qualcomm.com | - | 22.977, 22.941, 23.207, 22.243 |  |  |  |  | Tue 09/10/01 | Fri 12/03/04
6486 | 32999 | TR on Architectural impacts | - | 2 | Rel-6 | S2 | Mon 12/05/03 | Tue 02/03/04 | 100% | - | - | - | - | - | 23.877 |  |  |  |  | Thu 29/11/01 | Thu 08/07/04
6487 | 34700 | Codec Work to Support Speech Recognition Framework for Automated Voice Services | SRSES-Codec | 2 | Rel-6 | S4 | Tue 15/10/02 | Thu 16/12/04 | 100% | SP-020687 | - | Motorola | David Pearce (bdp003@motorola.com) | - | 26.235, 26.236, 26.243, 26.177, 26.943 |  |  |  |  | Mon 13/01/03 | Mon 06/12/04
6488 | 60004 | Multimodal support | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Fri 30/12/05 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
6489 | 11021 | Deleted - SES codec negotiation at Session Description Protocol (SDP) | - | 2 | Rel-6 | N1 | Wed 04/06/03 | Wed 04/06/03 | 100% | - | - | - | - | Abandoned NP-23 | - |  |  | NP-23 |  | Wed 20/10/04 | Thu 21/10/04
6490 | 31008 | Generic User Profile Rel-6 | GUP | 1 | Rel-6 | S1,S3,N4 | Mon 08/10/01 | Thu 03/03/05 | 100% | SP-040515 | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Fri 28/03/03
6491 | 31009 | Stage 1 - Requirements for Generic User Profile | - | 2 | Rel-6 | S1 | Mon 08/10/01 | Fri 30/05/03 | 100% | - | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 22.240, 22.228 |  |  |  |  | Tue 09/10/01 | Fri 25/03/05
6492 | 32008 | Stage 2 - Architecture | - | 2 | Rel-6 | S2 | Mon 28/01/02 | Fri 06/06/03 | 100% | SP-020539 | - | Nokia | harri.o.koskinen@nokia.com | - | 23.24 |  |  |  |  | Tue 09/10/01 | Fri 12/03/04
6493 | 42002 | Stage 2 - Data Description Method | - | 2 | Rel-6 | N4 | Thu 05/12/02 | Thu 03/03/05 | 100% | TP-020275 | - | T-Mobile | kurt.bischinger@t-mobile.at | TR approved in CN#26 | 23.241 |  |  |  |  | Tue 09/10/01 | Wed 09/03/05
6494 | 14008 | Stage 3 - Network | - | 2 | Rel-6 | N4 | Mon 19/05/03 | Thu 03/03/05 | 100% | - | - | - | - | - | 29.24 |  |  |  |  | Thu 21/03/02 | Wed 09/03/05
6495 | 33009 | Security aspects of GUP | - | 2 | Rel-6 | S3 | Tue 16/07/02 | Thu 18/09/03 | 100% | SP-030109 | - | Lucent | Bradley Owen (bvowen@lucent.com) | SP#19 approved WID | 33.102, 33.203, 33.210 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
6496 | 31010 | Digital Rights Management | DRM | 1 | Rel-6 | S1,OMA | Mon 08/10/01 | Fri 28/05/04 | 100% | SP-010577 | - | - | - | Foreseen start and completion dates introduced by MCC (no indication at all on the WID) | - |  |  |  |  | Thu 11/10/01 | Thu 11/10/01
6497 | 31011 | Requirements for Digital Rights Management | - | 2 | Rel-6 | S1 | Mon 08/10/01 | Thu 13/06/02 | 100% | - | - | Openwave | nicholas.wood@openwave.com | - | - |  |  |  |  | Thu 11/10/01 | Fri 04/07/03
6498 | 60005 | Stage 2 for Digital Rights Management | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Fri 28/05/04 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
6499 | 60006 | Stage 3 for Digital Rights Management | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Fri 28/05/04 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
6500 | 33001 | Security for Digital Rights Management | - | 2 | Rel-6 | OMA | Mon 17/06/02 | Mon 03/03/03 | 100% | - | - | - | - | SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17 | - |  |  |  |  | Thu 11/10/01 | Fri 25/03/05
6501 | 31037 | Deleted - Monitoring of Stages 2 and 3 progress (actual work to be done by OMA) | - | 2 | Rel-6 | S1 | Fri 21/03/03 | Fri 21/03/03 | 100% | - | - | - | - | Replaced by UID 60005 and 60006 | - |  |  | SP-19 |  | Wed 15/01/03 | Wed 08/09/04
6502 | 31012 | WLAN-UMTS Interworking Rel-6 | WLAN | 1 | Rel-6 | S1,S2,S3,S5,N1,N3,N4,T3 | Mon 03/01/00 | Thu 22/09/05 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | - |  |  |  |  | Thu 11/10/01 | Fri 12/03/04
6503 | 31020 | Technical Report on WLAN-UMTS Interworking | WLAN-TR | 2 | Rel-6 | S1 | Mon 03/01/00 | Fri 13/06/03 | 100% | SP-030712 | - | T-mobile | Mark.Younge@t-mobile.com | - | 22.934 |  |  |  |  | Thu 28/02/02 | Tue 08/06/04
6504 | 31035 | Stage 1 for WLAN-UMTS Interworking Rel-6 | WLAN-TS | 2 | Rel-6 | S1 | Mon 06/01/03 | Fri 11/06/04 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | 22.101, 22.105 |  |  |  |  | Mon 13/01/03 | Tue 08/06/04
6505 | 32018 | Architecture Definition for scenarii 2 and 3 | - | 2 | Rel-6 | S2 | Mon 25/03/02 | Mon 31/05/04 | 100% | SP-020542 | - | - | - | - | 23.234 |  |  |  |  | Mon 25/03/02 | Thu 08/07/04
6506 | 32704 | Security aspects of WLAN-UMTS Interworking | - | 2 | Rel-6 | S3 | Mon 30/09/02 | Fri 21/03/03 | 100% | SP-020514 | - | Ericsson, BT | luis.lopez-soria@ece.ericsson.se, colin.blanchard@bt.com | SP#17 approved WID S3-020451 | 21.133, 33.106, 33.107, 33.108, 33.200, 33.203, 33.210, New 33.234 |  |  |  |  | Thu 26/09/02 | Tue 09/08/11
6507 | 14013 | Stage 3 - CN4 aspects | WLAN-IW | 2 | Rel-6 | N4 | Fri 23/05/03 | Wed 01/09/04 | 100% | NP-030490 | - | Nokia | raquel.rodriguez@nokia.com | WID approved at CN#19 | 29.234, 29.061 |  |  |  |  | Thu 27/03/03 | Wed 09/03/05
6508 | 13019 | Stage 3 - CN3 aspects (Wi Interface for Scenario 3) | - | 2 | Rel-6 | N3 | Fri 23/05/03 | Thu 30/09/04 | 100% | - | - | - | - | - | 29.161 |  |  |  |  | Tue 08/06/04 | Wed 09/03/05
6509 | 11042 | Stage 3 for scenario 2 | - | 2 | Rel-6 | N1 | Fri 23/05/03 | Wed 08/09/04 | 100% | NP-030490 | - | - | - | - | - |  |  |  |  | Mon 09/06/03 | Wed 09/03/05
6510 | 11047 | Stage 3 for scenario 3 | - | 2 | Rel-6 | N1 | Fri 23/05/03 | Wed 08/12/04 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/06/04 | Wed 09/03/05
6511 | 35033 | WLAN charging | WLAN-CH | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 22/09/05 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | - | 32.252 |  |  |  |  | Fri 29/10/04 | Mon 15/08/11
6512 | 43010 | USIM enhancements for WLAN Interworking | - | 2 | Rel-6 | T3 | Fri 05/09/03 | Fri 04/03/05 | 100% | TP-030185 | - | Axalto | Jabellan@axalto.com | - | 31.102 |  |  |  |  | Mon 06/12/04 | Thu 01/09/11
6513 | 31015 | Priority Service | PRIOR1 | 1 | Rel-6 | S1 | Thu 30/05/02 | Fri 26/09/03 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
6514 | 31016 | Feasibility Study on Priority Service | PRIOR-FS | 2 | Rel-6 | S1 | Fri 14/06/02 | Fri 14/06/02 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.95 |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
6515 | 31017 | Stage 1 - Requirements for Priority Service | PRIOR-SR | 2 | Rel-6 | S1 | Thu 30/05/02 | Wed 17/09/03 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
6516 | 31043 | Priority service implementation guide | - | 2 | Rel-6 | S1 | Fri 28/03/03 | Fri 26/09/03 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.952 |  |  |  |  | Fri 04/07/03 | Tue 31/08/10
6517 | 31018 | Network Sharing | NTShar | 1 | Rel-6 | S1,S2,N1,R2,R5 | Mon 20/01/03 | Fri 10/03/06 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | - |  |  |  |  | Wed 27/02/02 | Tue 10/11/09
6518 | 31019 | Technical Report on Network Sharing | NTShar-TR | 2 | Rel-6 | S1 | Mon 20/01/03 | Fri 19/12/03 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.951 |  |  |  |  | Wed 27/02/02 | Tue 10/11/09
6519 | 31038 | Stage 1 - CRs to implement Network Sharing | NTSharCR | 2 | Rel-6 | S1 | Mon 20/01/03 | Fri 19/12/03 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.011, 22.101, 22.115, 22.129 |  |  |  |  | Fri 14/03/03 | Tue 10/11/09
6520 | 32044 | Stage 2 for Network Sharing | - | 2 | Rel-6 | S2 | Thu 27/02/03 | Fri 30/07/04 | 100% | SP-030123 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.002, 23.060, 23.221, 23.236, new 23.251, 23.851 |  |  |  |  | Thu 27/03/03 | Tue 10/11/09
6521 | 11043 | Network sharing - stage 3 | - | 2 | Rel-6 | N1 | Fri 23/05/03 | Wed 08/12/04 | 100% | NP-040429 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.008, 23.122, 24.007, 24.008, 29.018 |  |  |  |  | Mon 09/06/03 | Tue 10/11/09
6522 | 22004 | Enhancement of the support of network sharing in the UTRAN | NTShar-UTRANEnh | 2 | Rel-6 | R2 | Fri 19/09/03 | Fri 19/09/03 | 100% | - | - | TeliaSonera | Anders.Dahlen@TeliaSonera.com | - | 25.401, 25.413, 25.331, 25.304 |  |  |  |  | Thu 02/10/03 | Thu 13/01/05
6523 | 25004 | Conformance Test Aspects – Network Sharing | NTShar-UTRANEnh_Test | 2 | Rel-6 | R5 | Fri 11/03/05 | Fri 10/03/06 | 100% | - | - | TeliaSonera | Niklas.Wiren@TeliaSonera.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
6524 | 32016 | QoS Improvements | QoS1 | 1 | Rel-6 | S2,N3 | Mon 15/07/02 | Wed 08/12/04 | 100% | SP-010719 | - | Nokia | - | - | 23.107, 23.207, 23.221 |  |  |  |  | Thu 24/01/02 | Thu 24/01/02
6525 | 32017 | FS on Dynamic Policy control enhancements for end-to-end QoS | - | 2 | Rel-6 | S2 | Mon 15/07/02 | Fri 23/04/04 | 100% | SP-020540 | - | Nortel | Claire Mousset | - | 23.917 withdrawn (Contenall in 23.207) |  |  |  |  | Thu 24/01/02 | Thu 08/07/04
6526 | 32059 | Definition of the Gq interface | - | 2 | Rel-6 | S2 | Tue 01/07/03 | Fri 23/04/04 | 100% | SP-030306 | - | - | Janne Rinne | - | 23.207 |  |  |  |  | Wed 23/07/03 | Thu 08/07/04
6527 | 13016 | Gq interface specification for Dynamic Policy control enhancements – Stage 3 | - | 2 | Rel-6 | N3 | Fri 29/08/03 | Wed 08/12/04 | 100% | NP-030198 | - | Nokia | Anna.Sillanpaai@nokia.com | [DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004 | 29.207, 29.208, 29.209 |  |  |  |  | Mon 13/10/03 | Wed 09/03/05
6528 | 33002 | Subscriber certificates | SEC1-SC | 1 | Rel-6 | S3,S2,N1,N4,T3,OMA | Mon 25/02/02 | Wed 08/12/04 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | SP#14 approved WID | - |  |  |  |  | Thu 24/01/02 | Mon 08/08/11
6529 | 32705 | Stage 1 of Subscriber certificates | - | 2 | Rel-6 | S3 | Mon 25/02/02 | Thu 12/09/02 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | - | New (33.220, 33.221, 33.222, 33.246, 33.919) |  |  |  |  | Thu 26/09/02 | Mon 07/06/10
6530 | 32706 | Architecture review | - | 2 | Rel-6 | S2 | Mon 14/10/02 | Thu 14/11/02 | 100% | - | - | Nokia | - | - | - |  |  |  |  | Thu 26/09/02 | Tue 10/11/09
6531 | 14504 | Stage 3 for Subscriber certificates | - | 2 | Rel-6 | N4,T3 | Fri 19/09/03 | Tue 30/11/04 | 100% | NP-030399 | - | Nokia | Lauri Laitinen | Finished in CN4#26 | 23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111 |  |  |  |  | Wed 15/10/03 | Tue 10/11/09
6532 | 11049 | Stage 3 Ua & Ub interfaces | - | 2 | Rel-6 | N1 | Mon 03/11/03 | Wed 08/12/04 | 100% | - | - | Nokia | - | - | 24.109 |  |  |  |  | Mon 01/03/04 | Tue 10/11/09
6533 | 60007 | OMA dependencies on Subscriber certificates | - | 2 | Rel-6 | OMA | Thu 01/01/04 | Tue 08/06/04 | 100% | - | - | Nokia | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040420 | - |  |  |  |  | Tue 08/06/04 | Tue 10/11/09
6534 | 15010 | Rel-6 Open Service Access (OSA) enhancements | OSA3 | 1 | Rel-6 | N5 | Thu 31/10/02 | Thu 10/03/05 | 100% | NP-040351 | - | Alcatel | Chelo.Abarca@alcatel.fr | CN#25: Updated WID NP-040351 replaces NP-040144. | 22.127, 23.198, 29.198, 29.199, 29.998 |  |  |  |  | Wed 20/03/02 | Thu 13/01/05
6535 | 31040 | Scope of the Open Service Access Release 6 | - | 2 | Rel-6 | S1 | Fri 28/03/03 | Fri 27/06/03 | 100% | SP-030038 | - | - | - | - | - |  |  |  |  | Fri 28/03/03 | Fri 12/03/04
6536 | 15038 | OSA Stage 2 | - | 2 | Rel-6 | N5 | Fri 13/08/04 | Thu 10/03/05 | 100% | - | - | - | - | Inherited by CN5 from SA2 at TSG#25 Sep 2004. SA2's 23.127 (OSA/VHE Stage 2) replaced from Rel-6 onwards by a new CN5 TS 23.198 (Stage 2 OSA-only). | 23.198 OSA Stage 2-ONLY replaces 23.127 (OSA/VHE) from Rel-6 onwards |  |  |  |  | Fri 03/09/04 | Fri 25/03/05
6537 | 15026 | Multi Media Messaging function | - | 2 | Rel-6 | N5 | Thu 31/10/02 | Fri 10/09/04 | 100% | - | - | - | - | - | 29.198-15 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
6538 | 15028 | Policy management extensions | - | 2 | Rel-6 | N5 | Thu 31/10/02 | Fri 12/12/03 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
6539 | 15029 | TS on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | Thu 31/10/02 | Fri 26/03/04 | 100% | - | - | - | - | N5#26: Split WI into TS & TR. | 29.198-14 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
6540 | 15032 | OSA interfaces at different levels of abstractions (Parlay X, Web services) | - | 2 | Rel-6 | N5 | Mon 14/07/03 | Fri 10/09/04 | 100% | - | - | - | - | - | 29.199 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
6541 | 15033 | Introduction of migration support mechanism | - | 2 | Rel-6 | N5 | Thu 31/10/02 | Wed 10/12/03 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
6542 | 15036 | Framework Function for Federation | - | 2 | Rel-6 | N5 | Mon 03/02/03 | Fri 12/12/03 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
6543 | 60008 | OMA potential overlaps with 3GPP OSA Stage 3 (Web services) | - | 2 | Rel-6 | OMA | Thu 18/12/03 | Thu 16/09/04 | 100% | - | - | - | - | TSG#25 Approved CN5 29.199 Parlay X Web services. Ongoing 3GPP/OMA co-ordination to avoid OMA producing conflicting/OVERLAPING specs (NP-040283/SP-040493). | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
6544 | 15037 | Deleted - TR on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | Fri 17/09/04 | Fri 17/09/04 | 100% | - | - | - | - | N5#26:TR Completion 09/04¦consistent with CN1 delayed Rel-6 completion. | - |  |  | NP-24 |  | Wed 20/10/04 | Thu 21/10/04
6545 | 50401 | Addition of frequency bands to GSM (TAPS) | TAPS | 1 | Rel-6 | GP | Fri 28/06/02 | Fri 28/01/05 | 100% | GP-022072 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Wed 09/03/05
6546 | 50094 | Addition of frequency bands to GSM – Changes to core specs | TAPS-Specs | 2 | Rel-6 | G1 | Fri 15/11/02 | Fri 20/12/02 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Thu 13/02/03
6547 | 51102 | Changes to core specs | - | 3 | Rel-6 | G1 | Fri 15/11/02 | Fri 20/12/02 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Thu 13/02/03
6548 | 54102 | Deleted - Addition of frequency bands to GSM – Changes for conformance tests | TAPS-Conf | 2 | Rel-6 | G4 | Fri 28/06/02 | Fri 28/01/05 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | - |  |  | GP-23 |  | Wed 31/07/02 | Wed 09/03/05
6549 | 54103 | Deleted - 51.010-1 Add testing | - | 3 | Rel-6 | G4 | Fri 28/06/02 | Fri 28/01/05 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | - |  |  | GP-23 |  | Wed 31/07/02 | Wed 09/03/05
6550 | 50130 | Seamless support of streaming services in A/Gb mode | SSStrea | 1 | Rel-6 | GP,S3 | Mon 03/01/00 | Fri 17/06/05 | 100% | GP-022561 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Wed 14/01/04
6551 | 51131 | Identification of requirements for streaming | - | 2 | Rel-6 | G1 | Fri 27/06/03 | Fri 29/08/03 | 100% | GP-022564 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
6552 | 51133 | Requirements for streaming | - | 3 | Rel-6 | G1 | Fri 27/06/03 | Fri 29/08/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6553 | 51132 | Performance study of cell change mechanisms | - | 2 | Rel-6 | G1 | Mon 03/01/00 | Fri 29/08/03 | 100% | GP-022562 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
6554 | 51134 | Performance of NACC | - | 3 | Rel-6 | G1 | Mon 03/01/00 | Fri 29/08/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6555 | 51135 | Performance of cell change in DTM for the PS domain | - | 3 | Rel-6 | G1 | Mon 03/01/00 | Fri 29/08/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6556 | 51136 | Handover for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G1 | Mon 03/01/00 | Fri 29/08/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6557 | 52131 | Reduction of service interruption times and packet loss during mobility procedures | - | 2 | Rel-6 | G2 | Fri 27/06/03 | Fri 17/06/05 | 100% | GP-022563 | - | Vodafone | José Luis Carrizo Martínez | Completed at GERP#17 | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
6558 | 52133 | optimizations of existing mechanisms/procedures | - | 3 | Rel-6 | G2 | Fri 27/06/03 | Fri 21/11/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6559 | 52134 | Inter-system NACC | - | 3 | Rel-6 | G2 | Fri 27/06/03 | Fri 21/11/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6560 | 52135 | PS Handover (within GERAN and between GERAN and UTRAN) | - | 3 | Rel-6 | G2 | Fri 27/06/03 | Fri 17/06/05 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6561 | 52136 | Dependency to other features of Reduction of service interruption times and packet loss during mobility procedures | - | 3 | Rel-6 | G2 | Fri 27/06/03 | Fri 21/11/03 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
6562 | 54131 | Deleted - MS conformance testing for Seamless support of streaming services in A/Gb mode | - | 2 | Rel-6 | G3new | Fri 19/12/03 | Fri 30/01/04 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | - |  |  | GP-27 |  | Thu 26/09/02 | Tue 13/10/09
6563 | 54132 | Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G4,G5 | Fri 19/12/03 | Fri 30/01/04 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | - |  |  | GP-27 |  | Thu 13/02/03 | Tue 13/10/09
6564 | 33013 | GERAN A/Gb mode security enhancements | - | 2 | Rel-6 | S3 | Thu 26/09/02 | Fri 28/01/05 | 100% | SP-030107 | - | Vodafone | peter.howard@vodafone.com | SP#19 approved WID | 33.102 |  |  |  |  | Wed 15/01/03 | Mon 08/08/11
6565 | 34300 | Performance characterisation of default codecs for PS conversational multimedia application | CODCAR | 1 | Rel-6 | S4 | Fri 13/09/02 | Thu 10/06/04 | 100% | SP-020433 | - | Nokia | pasi.s.ojala@nokia.com | - | 26.935 |  |  |  |  | Thu 26/09/02 | Wed 08/09/04
6566 | 31030 | Study on Privacy Capability | PrivCap | 1 | Rel-6 | S1 | Mon 10/11/03 | Wed 03/03/04 | 100% | SP-020579 | - | Lucent | Michael Boote (mboote@alcatel-lucent.com) | - | 22.949 |  |  |  |  | Fri 08/11/02 | Tue 31/08/10
6567 | 35010 | Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM6 | 1 | Rel-6 | S5 | Thu 12/09/02 | Fri 11/03/05 | 100% | SP-040766 | - | - | - | SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4. | - |  |  |  |  | Fri 08/11/02 | Thu 13/01/05
6568 | 35011 | Principles, high level Requirements and Architecture | - | 2 | Rel-6 | S5 | Thu 12/09/02 | Thu 16/09/04 | 100% | SP-040767 | - | Motorola | - | SP#25 09/2004 completed | 32.101, 32.102 |  |  |  |  | Fri 08/11/02 | Fri 13/01/06
6569 | 35012 | Performance Management | - | 2 | Rel-6 | S5 | Thu 12/09/02 | Thu 16/12/04 | 100% | SP-040782 | - | Nortel | - | SP#26 12/2004 completed | 32.401, 32.403, 52.402, 32.411, 32.412, 32.413, 32.432, 32.435, 32.436 |  |  |  |  | Fri 08/11/02 | Fri 13/01/06
6570 | 35014 | Network Infrastructure Management | - | 2 | Rel-6 | S5 | Thu 12/09/02 | Thu 16/12/04 | 100% | SP-040789 | - | Ericsson | thomas.tovinger@ericsson.com | SP#26 12/2004 completed | 32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5 |  |  |  |  | Fri 08/11/02 | Mon 21/02/11
6571 | 35015 | Rel-6 Trace Management | OAM-Trace | 2 | Rel-6 | S5,N4,R3 | Fri 20/09/02 | Fri 11/03/05 | 100% | SP-040782 | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 SA5 completed 12/04. Signalling Based Trace Activation for IMS (SIP) moved to Rel-7. Reason: CN1 cannot complete 24.229 trace without IETF dependency => estimate 05/2005. | - |  |  |  |  | Fri 08/11/02 | Wed 09/03/05
6572 | 35022 | Subscriber and UE trace management | - | 3 | Rel-6 | S5 | Fri 20/09/02 | Thu 16/12/04 | 100% | - | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 completed | 32.421, 32.422, 32.423, 52.008 |  |  |  |  | Fri 03/10/03 | Fri 13/01/06
6573 | 23013 | Subscriber and equipment trace in UTRAN | OAM-Trace-RAN | 3 | Rel-6 | R3 | Fri 06/06/03 | Tue 15/06/04 | 100% | - | - | Nortel | Yann Sehedi (sehedic@nortelnetworks.com) | - | 25.413, 25.420, 25.423 |  |  |  |  | Fri 04/07/03 | Thu 13/01/05
6574 | 14016 | Trace Management, Stage3 | - | 3 | Rel-6 | N4 | Wed 09/06/04 | Fri 11/03/05 | 100% | NP-040411 | - | Nokia | seppo.kauntola@nokia.com | - | 23.205, 29.232, 29.060, 29.002, 29.228 |  |  |  |  | Mon 01/03/04 | Wed 09/03/05
6575 | 35016 | Rel-6 Charging Management | CH | 1 | Rel-6 | S5,S2,N3 | Thu 21/11/02 | Thu 09/06/05 | 100% | SP-040773 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | SP#28 Target 09/2005 for WLAN Charging 32.252 | - |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
6576 | 35037 | Charging architecture and principles | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.24 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6577 | 35024 | Charging Data Record (CDR) file format and transfer | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 18/03/04 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.297 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6578 | 35025 | CDR parameter description | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 09/06/05 | 100% | - | - | - | - | SP#28 06/2005 completed | 32.298 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6579 | 35026 | Diameter charging applications | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.299 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6580 | 35027 | Online Charging System (OCS) architecture study | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 18/09/03 | 100% | - | - | - | - | SP#21 09/2003 completed | 32.815 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6581 | 35028 | OCS: Applications and interfaces | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/12/04 | 100% | - | - | - | - | SP#26 12/2004 completed | 32.296 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6582 | 35017 | Charging Management for Bearer level | CH-BC | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | SP#28 Target 09/2005 for WLAN Charging 32.252 | - |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
6583 | 35029 | CS domain charging | - | 3 | Rel-6 | S5 | Fri 21/03/03 | Thu 18/03/04 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.25 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6584 | 35030 | PS domain charging | - | 3 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.251 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6585 | 35031 | CDR transfer | - | 3 | Rel-6 | S5 | Fri 21/03/03 | Thu 16/09/04 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.295 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
6586 | 35019 | Charging Management for the Service domain | - | 2 | Rel-6 | S5 | Fri 21/03/03 | Thu 09/06/05 | 100% | SP-040778 | - | Siemens | Gerald.Goermer@nsn.com | SP#26: Updated WID SP-040778 was SP-030050. Target completion 06/2005. Consisting of MMS-CH, LCS-CH, WLAN-CH, POC-CH, MBMS-CH | 32.252, 32.270, 32.271, 32.272 |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
6587 | 32030 | Overall architectural aspects of IP flow based bearer level charging | CH-FBC | 2 | Rel-6 | S2,N3 | Thu 21/11/02 | Fri 11/03/05 | 100% | SP-040041 | - | - | - | - | 23.125 |  |  |  |  | Wed 15/01/03 | Thu 08/07/04
6588 | 32069 | Overall definition of FBC architecture | - | 3 | Rel-6 | S2 | Thu 21/11/02 | Tue 02/03/04 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 20/05/04 | Wed 09/03/05
6589 | 32070 | Study on providing policy control with FBC | - | 3 | Rel-6 | S2 | Mon 02/02/04 | Fri 30/07/04 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 20/05/04 | Thu 21/10/04
6590 | 13020 | Gx interface for flow based charging | - | 3 | Rel-6 | N3 | Mon 02/02/04 | Wed 08/12/04 | 100% | NP-040245 | - | Nokia | juha.a.rasanen@nokia.com | - | 29.21 |  |  |  |  | Thu 20/05/04 | Wed 09/03/05
6591 | 13021 | Rx interface for flow based charging | - | 3 | Rel-6 | N3 | Mon 02/02/04 | Fri 11/03/05 | 100% | NP-040339 | - | Nortel | Javier Gonzalez Gallego | - | 29.209 |  |  |  |  | Thu 20/05/04 | Fri 25/03/05
6592 | 1800 | Rel-6 UICC/USIM enhancements and interworking | USAT1 | 1 | Rel-6 | T3 | Mon 25/09/00 | Thu 10/03/05 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Fri 01/12/00
6593 | 1802 | UICC API | USAT1-API | 2 | Rel-6 | T3 | Wed 20/03/02 | Thu 10/03/05 | 100% | - | - | - | - | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan | - |  |  |  |  | Thu 14/09/00 | Mon 12/03/01
6594 | 43001 | Rel-6 Java API Test specification | - | 3 | Rel-6 | T3 | Wed 20/03/02 | Mon 10/06/02 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | - |  |  |  |  | Thu 30/05/02 | Tue 09/02/10
6595 | 43006 | 2G/3G Java Card™ API based applet interworking | - | 3 | Rel-6 | T3 | Mon 17/03/03 | Fri 05/03/04 | 100% | TP-030031 | - | Oberthur Card Systems | Stéphane Andrau | - | - |  |  |  |  | Mon 08/09/03 | Wed 19/01/05
6596 | 43007 | (U)SIM API for Java Card Testing | - | 3 | Rel-6 | T3 | Mon 17/03/03 | Thu 10/03/05 | 100% | TP-040186 | - | Axalto | Christophe Begassat (cbegassat@axalto.com) | - | 31.213 |  |  |  |  | Mon 08/09/03 | Thu 02/06/05
6597 | 43003 | Deleted - Java API Test specification (TS 43.019 Rel-5) | - | 3 | Rel-6 | T3 | Thu 30/05/02 | Mon 09/06/03 | 100% | TP-020122 | - | Microelectrónica Española | Mario Pérez | MOVED to Rel-5 WP | - |  |  | TP-20 |  | Thu 26/09/02 | Tue 09/02/10
6598 | 43004 | Rel-6 USIM toolkit enhancements | USAT1-API-MULTOS | 2 | Rel-6 | T3 | Mon 25/09/00 | Fri 04/03/05 | 100% | - | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Fri 29/11/02 | Wed 19/01/05
6599 | 502031 | C SIM API | - | 3 | Rel-6 | T3 | Mon 25/09/00 | Fri 27/09/02 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | 31.101, 31.102, 31.103, 31.111, 31.113, new 31.115, 31.116 |  |  |  |  | Wed 27/09/00 | Tue 09/02/10
6600 | 502032 | Specification of C SIM API | - | 4 | Rel-6 | T3 | Mon 25/09/00 | Fri 27/09/02 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Sun 09/04/00 | Tue 09/02/10
6601 | 502033 | Test specification for C SIM API | - | 4 | Rel-6 | T3 | Mon 01/01/01 | Fri 28/09/01 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Thu 14/09/00 | Tue 09/02/10
6602 | 43009 | USIM application toolkit Conformance Test Specification for Mobile Equipments | - | 3 | Rel-6 | T3 | Fri 05/12/03 | Fri 04/03/05 | 100% | TP-030259 | - | Gemplus | Eric.laffont@gemplus.com | - | 31.124 |  |  |  |  | Mon 06/12/04 | Thu 02/06/05
6603 | 34022 | Packet Switched Streaming Services Rel-6 | PSSrel6 | 1 | Rel-6 | S4,S1 | Mon 18/11/02 | Wed 07/12/05 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | - | - |  |  |  |  | Thu 28/11/02 | Fri 13/11/09
6604 | 31039 | Stage 1 for Packet Switched Streaming Services Rel-6 | - | 2 | Rel-6 | S1 | Mon 18/11/02 | Mon 17/03/03 | 100% | SP-020685 | - | Ericsson | - | 2nd resp SA4 | 22.233 |  |  |  |  | Fri 14/03/03 | Fri 13/11/09
6605 | 34024 | Stage 3 for Packet Switched Streaming Services Rel-6 | PSSrel6-Stage3 | 2 | Rel-6 | S4 | Fri 13/12/02 | Wed 07/12/05 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | TR tbc by Sept. 05 | 26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936 |  |  |  |  | Thu 27/03/03 | Fri 13/11/09
6606 | 34023 | AMR-WB extension for high audio quality | AMRWB+ | 1 | Rel-6 | S4 | Fri 13/12/02 | Wed 07/12/05 | 100% | SP-030083 | - | Nokia | janne.m.vainio@nokia.com | TR tbc by Sept. 05 | 26.290, 26.304, 26.273, 26.274, 26.412, 26.936 |  |  |  |  | Thu 28/11/02 | Fri 13/01/06
6607 | 34027 | Codec Enhancements for Packet Switched Conversational Multimedia Applications | CEPSCM | 1 | Rel-6 | S4 | Tue 16/03/04 | Thu 16/12/04 | 100% | SP-040066 | - | Nokia | miska.hannuksela@nokia.com | - | 26.235, 26.236 |  |  |  |  | Tue 02/03/04 | Mon 06/12/04
6608 | 34028 | 3G-324M Improvements | 3G-324MI | 1 | Rel-6 | S4 | Tue 16/03/04 | Thu 16/12/04 | 100% | SP-040067 | - | Ericsson | bo.burman@ericsson.com | - | 26.111, 26.911 |  |  |  |  | Tue 02/03/04 | Mon 06/12/04
6609 | 51101 | Single Antenna Receiver Interference Cancellation (SAIC) | SAIC | 1 | Rel-6 | GP,G1 | Fri 15/11/02 | Fri 25/06/04 | 100% | GP-023400 | - | Cingular | Marc Grant | - | 45.903 |  |  |  |  | Thu 13/02/03 | Wed 18/11/09
6610 | 12006 | Enhancement of dialled service for CAMEL | EDCAMEL | 1 | Rel-6 | S1,N2,N4 | Fri 28/03/03 | Wed 31/12/03 | 100% | SP-020818 | - | Samsung | craig.bishop@samsung.com | - | 22.078 |  |  |  |  | Fri 14/03/03 | Fri 13/11/09
6611 | 12007 | Stages 2 and 3 for Enhancement of dialled service for CAMEL | - | 2 | Rel-6 | N2,N4 | Fri 28/03/03 | Wed 31/12/03 | 100% | NP-030153 | - | Samsung | Richard Brook | - | 23.008, 23.016, 23.018, 23.078, 29.002, 29.078 |  |  |  |  | Thu 27/03/03 | Fri 13/11/09
6612 | 32060 | Study on Bandwidth and resource savings in CS networks | BARS | 1 | Rel-6 | S2 | Sun 01/06/03 | Wed 16/06/04 | 100% | SP-030308 | - | - | - | - | 23.977 |  |  |  |  | Wed 23/07/03 | Thu 08/07/04
6613 | 50600 | Multiple TBF in A/Gb mode | MULTBF | 1 | Rel-6 | GP,G2 | Fri 05/04/02 | Fri 28/01/05 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved from Rel-5 UID_50058 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | - |  |  |  |  | Thu 31/07/03 | Fri 13/01/06
6614 | 50601 | Multiple TBF in A/Gb mode - Core | MULTBF-Agbmode | 2 | Rel-6 | GP,G2 | Fri 05/04/02 | Fri 29/08/03 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
6615 | 50602 | Multiple TBF Concept paper | - | 3 | Rel-6 | GP,G2 | Fri 05/04/02 | Fri 29/08/03 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
6616 | 50603 | Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-6 | GP,G2 | Fri 05/04/02 | Fri 29/08/03 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
6617 | 50604 | Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-6 | GP,G2 | Fri 05/04/02 | Fri 29/08/03 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Mon 06/12/04
6618 | 50605 | Deleted - Multiple TBF in A/Gb mode – MS testing | MULTBF-Testing | 2 | Rel-6 | G3new | Fri 28/01/05 | Fri 28/01/05 | 100% | GP-022098 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | - |  |  | GP-27 |  | Thu 31/07/03 | Wed 09/03/05
6619 | 50096 | Alignment between the test-regimes for GERAN capable MS | ALTERE | 1 | Rel-6 | G3new | Fri 29/08/03 | Fri 02/09/05 | 99% | GP-032236 | - | Ericsson | anthony.toubassi@sonyericsson.com | - | - |  |  |  |  | Tue 16/09/03 | Fri 13/01/06
6620 | 50097 | Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010. | ALTERE-TC | 2 | Rel-6 | G3new | Fri 29/08/03 | Fri 02/09/05 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 16/09/03 | Fri 13/01/06
6621 | 50444 | Addition of U-TDOA in the CS domain | UTDOACS | 1 | Rel-6 | GP | Fri 21/11/03 | Fri 23/04/04 | 100% | GP-032773 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | Completed, except for potential LMU performance specs | - |  |  |  |  | Mon 01/12/03 | Fri 12/03/04
6622 | 50445 | Addition of U-TDOA in the PS domain | UTDOAPS | 1 | Rel-6 | GP | Fri 27/06/03 | Fri 12/11/04 | 100% | GP-032774 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6623 | 50101 | Downlink Advanced Receiver Performance | DARP | 1 | Rel-6 | GP | Fri 21/11/03 | Fri 02/09/05 | 100% | GP-041966 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6624 | 50102 | DARP test scenarios | DARP-TS | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 27/08/04 | 100% | GP-041967 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6625 | 50103 | DARP for GMSK modulated voice services | DARP-GMSK | 2 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | GP-041968 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6626 | 50104 | Performance requirements in 45.005 for DARP for GMSK modulated voice services | DARP-GMSK-Perf | 3 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6627 | 50105 | Radio subsystem link control in 45.008 for DARP for GMSK modulated voice services | DARP-GMSK-LC | 3 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6628 | 50106 | DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE | 2 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | GP-041969 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Wed 09/03/05
6629 | 50107 | Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-Perf | 3 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6630 | 50108 | Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-LC | 3 | Rel-6 | GP | Fri 06/02/04 | Fri 12/11/04 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6631 | 50115 | DARP Capability signalling | DARP-CAPSIG | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 12/11/04 | 100% | GP-041970 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
6632 | 50116 | GERAN MS Conformance test for DARP | ARP-ConfTest | 2 | Rel-6 | G3new | Fri 27/08/04 | Fri 02/09/05 | 100% | GP-041971 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6633 | 50109 | Reduction of PS service interruption in Dual Transfer Mode | PSintDTM | 1 | Rel-6 | G2 | Fri 21/11/03 | Fri 24/06/05 | 100% | GP-032548 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6634 | 50110 | Use case and requirement definition | PSintDTM-Req | 2 | Rel-6 | G2 | Fri 21/11/03 | Fri 23/04/04 | 100% | GP-032549 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6635 | 50111 | Performance Study of Current Procedures | PSintDTM-Perf | 2 | Rel-6 | G2 | Fri 21/11/03 | Fri 23/04/04 | 100% | GP-032550 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6636 | 50112 | Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures | PSintDTM-Reduct | 2 | Rel-6 | G2 | Fri 23/04/04 | Fri 12/11/04 | 100% | GP-032551 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
6637 | 50113 | Deleted - MS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfMS | 2 | Rel-6 | G3new | Fri 25/06/04 | Fri 24/06/05 | 100% | - | - | - | - | - | - |  |  | GP-25 |  | Mon 01/12/03 | Fri 12/12/08
6638 | 50114 | Deleted - BTS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfBTS | 2 | Rel-6 | G3new | Fri 24/06/05 | Fri 24/06/05 | 100% | - | - | - | - | - | - |  |  | GP-25 |  | Mon 01/12/03 | Fri 13/01/06
6639 | 12008 | CAMEL prepay interworking with SCUDIF | SCCAMEL | 1 | Rel-6 | N4,N3,S1 | Mon 08/12/03 | Tue 05/10/04 | 100% | NP-030584 | - | Nokia | Keijo.Palviainen@Nokia.Com | - | 22.078, 23.078, 29.078, 29.002, 23.172 |  |  |  |  | Wed 03/03/04 | Fri 13/11/09
6640 | 31046 | Circuit Switched Video and Voice Service Improvements | CS_VSS | 1 | Rel-6 | S2,N1 | Mon 12/01/04 | Fri 02/09/05 | 100% | SP-040331 | - | Vodafone | John Watson | - | - |  |  |  |  | Fri 14/03/03 | Thu 08/07/04
6641 | 31047 | Deleted - Stage 1 - Requirements | - | 2 | Rel-6 | S1 | Mon 12/01/04 | Thu 14/10/04 | 100% | SP-040331 | - | Vodafone | John Watson | - | 22.101 |  |  | SP-26 |  | Tue 27/01/04 | Tue 08/06/04
6642 | 32071 | Stage 2 Study on architecture alternatives | - | 2 | Rel-6 | S2 | Mon 12/01/04 | Thu 16/12/04 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | 23.903 |  |  |  |  | Thu 20/05/04 | Mon 06/12/04
6643 | 32072 | Deleted - Stage 2 description on Redial | - | 2 | Rel-6 | S2 | Mon 03/05/04 | Thu 16/12/04 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | - |  |  | SP-26 |  | Thu 20/05/04 | Wed 09/03/05
6644 | 11053 | Switching between voice and video call - Redial solution | - | 2 | Rel-6 | N1 | Mon 03/01/05 | Fri 17/06/05 | 100% | SP-040331 | - | Vodafone | - | - | 23.009, 24.008 |  |  |  |  | Wed 20/04/05 | Thu 02/06/05
6645 | 52137 | Deleted - CS_VSS - GERAN2 Part | - | 2 | Rel-6 | G2 | Fri 02/09/05 | Fri 02/09/05 | 100% | SP-040331 | - | Vodafone | - | - | - |  |  | GP-26 |  | Wed 28/01/04 | Thu 21/04/05
6646 | 13017 | Deleted - CS_VSS - CN3 Part | - | 2 | Rel-6 | N3 | Thu 14/10/04 | Thu 14/10/04 | 100% | SP-040331 | - | Vodafone | - | - | - |  |  | TP-26 |  | Wed 20/10/04 | Thu 21/10/04
6647 | 13024 | Reorganisation of CS Data Specifications | CSData | 1 | Rel-6 | N3 | Fri 19/11/04 | Wed 08/12/04 | 100% | NP-040563 | - | Siemens | Thomas.Belling@nsn.com | Created at TSG#27 as 100 % complete | 23.910, 29.007, New 23.202 |  |  |  |  | Wed 02/03/05 | Wed 09/03/05
6648 | 50553 | Generic Access to A/Gb Interface (GAAI) | GAAI | 1 | Rel-6 | GP | Fri 25/06/04 | Fri 20/01/06 | 100% | GP-042247 | - | Motorola | - | - | - |  |  |  |  | Fri 15/10/04 | Fri 13/01/06
6649 | 50544 | FS on GAAI | GAAG | 2 | Rel-6 | GP | Fri 25/06/04 | Fri 27/08/04 | 100% | GP-041592 | - | Motorola | - | Feasibility Study | 43.901 |  |  |  |  | Wed 30/06/04 | Fri 25/03/05
6650 | 50554 | GAAI – Stage 2 | GAAI-Stage2 | 2 | Rel-6 | GP | Fri 27/08/04 | Fri 08/04/05 | 100% | - | - | Ericsson | jari.vikberg@ericsson.com | - | 43.318 |  |  |  |  | Fri 15/10/04 | Fri 25/03/05
6651 | 50555 | GAAI – Stage 3 | GAAI-Stage3 | 2 | Rel-6 | GP | Fri 27/08/04 | Fri 08/04/05 | 100% | - | - | - | - | - | 44.318 |  |  |  |  | Fri 15/10/04 | Fri 13/01/06
6652 | 50556 | MS Conformance Test for GAAI | GAAI-CT | 2 | Rel-6 | GP | Fri 27/08/04 | Fri 20/01/06 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | - |  |  |  |  | Fri 15/10/04 | Fri 12/12/08
6653 | 50559 | Support of PS Handover for GERAN A/Gb mode | SPSHAGB | 1 | Rel-6 | GP,G2 | Mon 03/11/03 | Wed 24/08/05 | 100% | GP-051160 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB- Originally Started Nov 2003 as GP-030443 | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
6654 | 50560 | Stage 2 for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-Stage2 | 2 | Rel-6 | GP,G2 | Mon 03/11/03 | Wed 24/08/05 | 100% | GP-051161 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-Stage2 | 43.129 |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
6655 | 50561 | PS handover for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-PSHO | 2 | Rel-6 | GP,G2 | Mon 03/11/03 | Wed 24/08/05 | 100% | GP-051162 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-PSH | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
6656 | 50562 | Definition of radio resource management functionality for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-RRM | 2 | Rel-6 | GP,G2 | Mon 03/11/03 | Wed 24/08/05 | 100% | GP-051163 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-RRM | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
6657 | 33018 | Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces | - | 1 | Rel-6 | S3 | Thu 03/07/03 | Fri 26/12/03 | 100% | SP-030341 | - | Toshiba | Raziq Yaqub (ryaqub@tari.toshiba.com) | SP#20 approved WID | 33.817 |  |  |  |  | Fri 25/07/03 | Tue 09/08/11
6658 | 33021 | Study on Security for early IMS | SEC-IMS | 1 | Rel-6 | S3 | Fri 01/10/04 | Mon 28/03/05 | 100% | SP-040691 | - | Vodafone | Peter.Howard@vodafone.com | SP#24 approved WID. SP#46 withdrawn TR 33.978 from Rel-8 onwards | 33.978 |  |  |  |  | Fri 25/07/03 | Tue 09/08/11
6659 | 60111 | (Small) Technical Enhancements and Improvements for Rel-6 | TEI6 | 1 | Rel-6 | SP,CP,RP,GP | Fri 02/06/06 | Fri 02/06/06 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 6 CR not related to any feature and with very limited impact on the system. Moved in from Stoyan/Testing WP | - |  |  |  |  | Thu 21/09/06 | Tue 06/05/08
6660 | 25019 | Test - (Small) Technical Enhancements and Improvements for Rel-6 | TEI6_Test | 1 | Rel-6 | R5,T1 | Fri 02/06/06 | Tue 06/05/08 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing | 34.108,34.121-1/2,34.122,34.123-1/2/3 |  |  |  |  | Thu 21/09/06 | Tue 06/05/08
6661 | 31029 | Deleted - Study of Feature Interactions Requirements | FINTER | 1 | Rel-6 | S1 | Thu 16/09/04 | Thu 16/09/04 | 100% | SP-020578 | - | - | - | SP#25 stopped | - |  |  | SP-25 |  | Wed 20/10/04 | Tue 02/03/10
6662 | 50563 | Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials | - | 1 | Rel-6 | GP,G2 | Thu 25/08/05 | Fri 02/09/05 | 100% | GP-041837 | - | Siemens | kenneth.isaacs@roke.co.uk | GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials | 44.018, 44.068, 48.008 |  |  | GP-26 |  | Wed 20/04/05 | Thu 21/04/05
6663 | 50500 | Deleted SCSAGB - Support of Conversational Services in A/Gb mode via the PS domain | - | 1 | Rel-6 | GP,N1 | Fri 21/11/03 | Thu 19/02/04 | 100% | GP-030443 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | - |  |  | GP-18 |  | Thu 13/02/03 | Tue 02/03/10
6664 | 50501 | Deleted - Creation of a TR | SCSAGB-TR | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 21/11/03 | 100% | GP-030444 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
6665 | 50502 | Deleted - Stage 2 | SCSAGB-Stage2 | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 21/11/03 | 100% | GP-030445 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
6666 | 50503 | Deleted - Radio Channel Support | SCSAGB-RCS | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 21/11/03 | 100% | GP-030446 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
6667 | 50504 | Deleted SCSAGB-RRM - Definition of radio resource management functionality | - | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 21/11/03 | 100% | GP-030447 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
6668 | 50505 | Deleted - replaced by 50561 - PS Handover | SCSAGB-PSH | 2 | Rel-6 | GP,N1 | Mon 24/11/03 | Thu 19/02/04 | 100% | GP-030448 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | - |  |  | GP-18 |  | Thu 13/02/03 | Tue 02/03/10
6669 | 50506 | Deleted SCSAGB-FLO - Modifications to FLO | - | 2 | Rel-6 | GP | Fri 21/11/03 | Fri 21/11/03 | 100% | GP-030449 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | RP-29 |  | Thu 13/02/03 | Tue 02/03/10
6670 | 2 | Deleted - Rel-6 Evolutions of the transport in the UTRAN (ETRAN) | - | 1 | Rel-6 | RP | Wed 31/12/03 | Wed 31/12/03 | 100% | - | - | Alcatel | Francois Courau | Generic feature ETRAN | - |  |  | RP-22 |  | Thu 02/10/03 | Thu 08/07/04
6671 | 0 | --- RELEASE 5 --- | - | 1 | Rel-5 | NP,GP,RP,SP,TP | Mon 03/01/00 | Thu 29/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
6672 | 625 | IP transport in the UTRAN | ETRAN-IPtrans | 1 | Rel-5 | R3 | Mon 17/07/00 | Fri 29/03/02 | 100% | - | - | Alcatel | Nicolas Drevon | - | - |  |  |  |  | Fri 31/03/00 | Wed 12/12/01
6673 | 2455 | Feasibility study on SS7 signalling transportation in the core network with SCCP-User Adaptation (SUA) | FS_SS7IP | 1 | Rel-5 | N4 | Mon 12/03/01 | Fri 21/12/01 | 100% | NP-010460 | - | - | - | - | 29.903 |  |  |  |  | Mon 12/03/01 | Wed 12/12/01
6674 | 2476 | High Speed Downlink Packet Access | HSDPA | 1 | Rel-5 | R2,R5 | Mon 02/04/01 | Fri 09/03/07 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | - |  |  |  |  | Tue 20/03/01 | Mon 10/12/01
6675 | 2477 | Physical Layer for High Speed Downlink Packet Access | HSDPA-Phys | 2 | Rel-5 | R1 | Thu 05/04/01 | Fri 29/03/02 | 100% | RP-010262 | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
6676 | 2478 | Layer 2 and 3 aspects | HSDPA-L23 | 2 | Rel-5 | R2 | Thu 05/04/01 | Fri 29/03/02 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | - |  |  |  |  | Tue 20/03/01 | Thu 28/02/02
6677 | 2479 | Iub/Iur protocol aspects - for High Speed Downlink Packet Access | HSDPA-IubIur | 2 | Rel-5 | R3 | Mon 02/04/01 | Fri 29/03/02 | 100% | RP-010262 | - | Motorola | Mike Diesen | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
6678 | 2480 | RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | HSDPA-RF | 2 | Rel-5 | R4 | Mon 09/04/01 | Fri 06/06/03 | 100% | RP-010262 | - | Motorola | Howard Benn | - | - |  |  |  |  | Tue 20/03/01 | Thu 27/03/03
6679 | 25000 | Conformance Testing of HSDPA | HSDPA_Test | 2 | Rel-5 | R5 | Fri 19/09/03 | Fri 22/09/06 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
6680 | 25012 | Conformance Testing of HCR TDD HSDPA | HSDPA_HCRTDD_Test | 2 | Rel-5 | R5 | Fri 10/03/06 | Fri 09/03/07 | 100% | - | - | IPWireless | drichards@ipwireless.com | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
6681 | 501216 | Rel-5 Improvements of Radio Interface | - | 1 | Rel-5 | RP | Mon 14/08/00 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 11/10/01
6682 | 1471 | Base station classification for TDD | RInImp-BSClass | 2 | Rel-5 | R4 | Mon 14/08/00 | Fri 14/06/02 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Wed 26/04/00 | Wed 03/10/01
6683 | 1477 | TDD Base station classification | RInImp-BSClass-TDD | 3 | Rel-5 | R4 | Mon 14/08/00 | Fri 08/03/02 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Wed 26/07/00 | Fri 21/06/02
6684 | 24002 | Base Station Classification for 1.28 Mcps TDD option | RInImp-BSClass-LCRTDD | 3 | Rel-5 | R4 | Fri 15/06/01 | Fri 14/06/02 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | - |  |  |  |  | Thu 05/07/01 | Fri 21/06/02
6685 | 2469 | Enhancement on the DSCH hard split mode | RInImp-DSCHhsp | 2 | Rel-5 | R1 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Samsung | Jaeyoel KIM | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
6686 | 1217 | Hybrid ARQ II/III | RInImp-HARQ | 2 | Rel-5 | R2 | Mon 21/08/00 | Fri 28/12/01 | 100% | - | - | Siemens | armin.sitte@siemens.com | Stopped at RP#14¦work on this task was performed as part of High Speed Downlink Packet Access feature | - |  |  | RP-14 |  | Wed 26/04/00 | Thu 24/01/02
6687 | 1221 | FS on USTS | RInImp-USTS | 2 | Rel-5 | R1 | Mon 14/08/00 | Fri 21/12/01 | 100% | - | - | SK Telecom | D. Kim | - | - |  |  |  |  | Wed 26/04/00 | Thu 28/02/02
6688 | 1997 | FS on UE antenna efficiency test method performance requirements | RInImp-UEAnTM | 2 | Rel-5 | R4 | Mon 25/09/00 | Fri 14/09/01 | 100% | - | - | Allgon | O. Edvardsson | - | - |  |  |  |  | Tue 26/09/00 | Wed 03/10/01
6689 | 2494 | FS on the re-introduction of the downlink SIR measurement | RInImp-SIR | 2 | Rel-5 | R4 | Mon 12/03/01 | Fri 14/12/01 | 100% | - | - | Ericsson | Torgny.Palenius@ericsson.com | - | - |  |  |  |  | Tue 27/03/01 | Thu 29/11/01
6690 | 2493 | FS on mitigating the effect of CPICH interference at the UE | RInImp-CPICH_Intf | 2 | Rel-5 | R4 | Mon 19/03/01 | Fri 08/03/02 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | - |  |  |  |  | Tue 27/03/01 | Fri 01/03/02
6691 | 1839 | Deleted - Conformance Test Spec. improvements in Radio Interface | - | 2 | Rel-5 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 14/09/00 | Thu 11/10/01
6692 | 2210 | Deleted - Testing improvement of inter-frequency and inter-system measurement | - | 3 | Rel-5 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
6693 | 2211 | Deleted - Testing Hybrid ARQ II/III | - | 3 | Rel-5 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
6694 | 500009 | Rel-5 RAN improvements | - | 1 | Rel-5 | RP | Fri 16/03/01 | Fri 09/03/07 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Fri 21/06/02
6695 | 656 | RRM optimization for Iur and Iub | RANimp-RRMopt | 2 | Rel-5 | R3 | Fri 16/03/01 | Tue 04/06/02 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6696 | 23000 | Iur common transport channel efficiency optimization | RANimp-RRMopt-ctc | 3 | Rel-5 | R3 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | - |  |  |  |  | Wed 19/09/01 | Thu 21/03/02
6697 | 23001 | Iur neighbouring cell reporting efficiency optimization | RANimp-RRMopt-ncr | 3 | Rel-5 | R3 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | - |  |  |  |  | Wed 19/09/01 | Fri 01/03/02
6698 | 23002 | FS Introduction of direct transport bearers between SRNC and Node-B | RAN-imp-RRMopt-DTB | 3 | Rel-5 | R3 | Fri 15/06/01 | Tue 04/06/02 | 100% | - | - | Ericsson | Risto Sepponen | FS was closed and introduction of WI not agreed at RAN #16 | - |  |  |  |  | Wed 19/09/01 | Fri 08/11/02
6699 | 2488 | RL Timing Adjustment | RANimp-RLTA | 2 | Rel-5 | R3 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Ericsson | Elena Voltolina | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
6700 | 2489 | Separation of resource reservation and radio link activation | RANimp-SepRR | 2 | Rel-5 | R3 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
6701 | 23003 | FS SRNS Relocation Procedure Enhancement | RANimp-SRNS | 2 | Rel-5 | R3 | Fri 15/06/01 | Tue 03/09/02 | 100% | - | - | Nokia | Olivier Guyot | - | - |  |  |  |  | Wed 19/09/01 | Fri 08/11/02
6702 | 2490 | FS Improvement of Radio Resource Management across RNS and RNS/PSS | RANimp-ImpRRM | 2 | Rel-5 | R3 | Fri 16/03/01 | Fri 21/12/01 | 100% | - | - | Nokia | antti.toskala@nokia.com | FS was closed and WI was introduced at RAN #14 | - |  |  |  |  | Tue 20/03/01 | Fri 08/11/02
6703 | 2491 | Re-arrangements of Iub transport bearers | RANimp-TTPS | 2 | Rel-5 | R3 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
6704 | 22000 | RAB support enhancement for Rel-5 | RANimp-RABSE5 | 2 | Rel-5 | R2 | Mon 02/04/01 | Fri 28/06/02 | 100% | - | - | Nokia | Juha Mikola | RFC 3095 context relocation | - |  |  |  |  | Thu 30/05/02 | Fri 21/06/02
6705 | 25005 | Testing of ROHC performance | RANimp-RABSE5_Test | 2 | Rel-5 | R5 | Fri 09/09/05 | Fri 09/03/07 | 100% | - | - | Nokia | jarkko.hellsten@nokia.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
6706 | 21001 | Beamforming requirements for UE | RANimp-BFR-UE | 2 | Rel-5 | R1 | Fri 21/09/01 | Fri 14/12/01 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | - |  |  |  |  | Thu 28/02/02 | Thu 28/02/02
6707 | 21002 | Support of Site Selection Diversity Transmission in UTRAN | RANimp-SSDT | 2 | Rel-5 | R1 | Fri 14/12/01 | Tue 04/06/02 | 100% | - | - | NEC | - | RP-020356 | - |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
6708 | 2472 | Node B Synchronisation for 1.28 Mcps TDD | RANimp-NBSLCR | 2 | Rel-5 | R1 | Fri 16/03/01 | Fri 29/03/02 | 100% | - | - | CATT | Jinling HU | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
6709 | 2102 | Deleted - Conformance Test Aspects - RAN Improvements | - | 2 | Rel-5 | T1 | Tue 01/01/02 | Mon 01/03/04 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-23 |  | Wed 01/11/00 | Sat 01/04/00
6710 | 2222 | Deleted - Testing Radio access bearer support enhancements | - | 3 | Rel-5 | T1 | Tue 01/01/02 | Mon 02/09/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
6711 | 41010 | Deleted - General changes to TS34.121 and TS34.122 corresponding to release 5 | RANimp-test,TEI5 | 3 | Rel-5 | T1 | Mon 03/03/03 | Mon 01/03/04 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121, 34.122 |  |  | TP-23 |  | Fri 14/03/03 | Fri 14/03/03
6712 | 23004 | UTRAN Sharing in Connected Mode | NETSHARE | 1 | Rel-5 | R3 | Mon 03/12/01 | Tue 03/09/02 | 100% | - | - | Ericsson | Martin Israelsson | Formerly 'Shared Network support in connected mode', renamed at RAN #16. | - |  |  |  |  | Thu 21/03/02 | Fri 08/11/02
6713 | 1273 | Provisioning of IP-based multimedia services | IMS | 1 | Rel-5 | S1,S2,S3,S5,NP,T3,T1,R5 | Mon 03/01/00 | Fri 01/12/06 | 100% | SP-000216 | - | Openwave | Mark Cataldo | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
6714 | 1274 | Call control and roaming to support IMS in UMTS | IMS-CCR | 2 | Rel-5 | S2,R5 | Mon 03/01/00 | Fri 01/12/06 | 100% | SP-010339 | - | Lucent | Liz Daniel | - | - |  |  |  |  | Sun 09/04/00 | Thu 24/01/02
6715 | 1633 | Stage 1 for Call control and roaming to support IMS in UMTS | - | 3 | Rel-5 | S1 | Mon 21/02/00 | Fri 15/12/00 | 100% | - | - | Motorola | Mark Cataldo | Issues include e.g.: Roaming requirements, Requirements on supplementary services, Interworking requirements | 22.228 |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
6716 | 1514 | Stage 2 (Architecture and Main flows) | - | 3 | Rel-5 | S2 | Fri 14/04/00 | Fri 23/03/01 | 100% | SP-000289 | - | Lucent | Liz Daniel | Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol | 23.228 |  |  |  |  | Fri 28/07/00 | Thu 08/02/01
6717 | 1296 | Impact on MM/CC/SM | IMS-CCR-IWMM | 3 | Rel-5 | N1 | Mon 28/08/00 | Fri 08/03/02 | 100% | NP-010434 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Per 26/2-02: This is understood to be the PCO & TFT CRs which CN1 provides to TSGN #15 for approval. If this is correct understanding, then the task is 100 % complete. | - |  |  |  |  | Wed 19/04/00 | Mon 25/03/02
6718 | 2233 | SIP Call Control protocol for the IMS | - | 3 | Rel-5 | N1 | Mon 02/10/00 | Fri 22/03/02 | 100% | NP-010643 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | TSGN_10 approved the change:CN1 - SA2 SIP joint meeting spotted one more place for improvement: work tasks with ID 1998 and 1278 are actually subtasks under of single CN1 WT. One WI has been approved for the CN1 WT with title "SIP Call Control protocol | 24.228, 24.229, 23.218 |  |  |  |  | Mon 11/12/00 | Thu 24/01/02
6719 | 1998 | IMS signalling flows | - | 4 | Rel-5 | N1 | Mon 02/10/00 | Fri 22/03/02 | 100% | - | - | - | - | 24.228 | 24.228 |  |  |  |  | Fri 25/08/00 | Fri 14/03/03
6720 | 1278 | IMS stage 3 | - | 4 | Rel-5 | N1 | Mon 02/10/00 | Fri 22/03/02 | 100% | - | - | - | - | 24.229 | 24.229 |  |  |  |  | Wed 19/04/00 | Fri 14/03/03
6721 | 2255 | IMS Session Handling; stage 2 | - | 4 | Rel-5 | N1 | Mon 02/10/00 | Fri 22/03/02 | 100% | - | - | - | - | 23.218 | 23.218 |  |  |  |  | Thu 08/02/01 | Thu 28/02/02
6722 | 25006 | Conformance Test Aspects – IMS Call Control | IMS-CCR_Test | 3 | Rel-5 | R5 | Fri 11/03/05 | Fri 01/12/06 | 100% | - | - | Motorola | Jacob.John@motorola.com | - | 34.108, 34.229-1, 34.229-2, 34.229-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
6723 | 10004 | Main IETF dependencies | - | 3 | Rel-5 | NP | Mon 03/01/00 | Fri 14/06/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 25/01/02 | Fri 28/03/03
6724 | 2521 | IETF: RFC 3261 (Session Initiation Protocol) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Fri 22/03/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
6725 | 2523 | IETF: RFC 3262 (Reliability of provisional responses) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Fri 22/03/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 25/03/02 | Fri 14/03/03
6726 | 2522 | IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
6727 | 2524 | IETF: RFC 3323 (SIP extensions for caller identity and privacy) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
6728 | 2525 | IETF: RFC 3313 (SIP extensions for media authorization) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
6729 | 11000 | IETF: RFC 3265 (specific event notification) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Fri 22/03/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6730 | 11001 | IETF: RFC editor Queue (refer method) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Fri 07/06/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6731 | 11002 | IETF: RFC editor Queue (DHCP options for SIP servers) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6732 | 11004 | IETF: RFC 3267 (AMR and AMR WB RTP and SDP) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Fri 22/03/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6733 | 11005 | IETF: RFC 3266 (IPv6 support within SDP) | - | 4 | Rel-5 | N1 | Mon 03/01/00 | Fri 22/03/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6734 | 11022 | IETF: RFC 3311 (The Update method) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
6735 | 11023 | IETF: RFC 3324 (Network Asserted Identity) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
6736 | 11024 | IETF: RFC editor Queue (Various 3GPP Private Extensions) | - | 4 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
6737 | 1290 | Addressing | - | 4 | Rel-5 | S2 | Mon 09/10/00 | Fri 22/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Sat 01/04/00
6738 | 1291 | Architectural issues | - | 5 | Rel-5 | S2 | Mon 09/10/00 | Fri 31/08/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Thu 08/02/01
6739 | 1292 | Impact on HSS | - | 5 | Rel-5 | N4 | Wed 15/11/00 | Fri 22/03/02 | 100% | - | - | - | - | Covered by 29.228 & 29228 | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
6740 | 2530 | Service Examples (Work stopped) | IMS-Sex | 4 | Rel-5 | S1 | Tue 17/04/01 | Fri 14/06/02 | 100% | - | - | Motorola | Mark Cataldo | - | 22.928 |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
6741 | 2531 | IMS Framework Report (work stopped) | IMS-FrWk | 5 | Rel-5 | S1 | Tue 17/04/01 | Fri 14/06/02 | 100% | - | - | SBC | Randolph Wohlert (rwohlert@tri.sbc.com) | - | 22.941 |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
6742 | 1298 | Access Security for IMS | IMS-ASEC | 2 | Rel-5 | S3,T3 | Mon 08/10/01 | Fri 28/06/02 | 100% | SP-010323 | - | Ericsson | krister.boman@emw.ericsson.se | - | - |  |  |  |  | Tue 18/04/00 | Mon 08/08/11
6743 | 43000 | IMS impacts on UICC (ISIM application) | - | 3 | Rel-5 | T3 | Mon 08/10/01 | Fri 21/06/02 | 100% | TP-010251 | - | Vodafone | Jeremy Norris | - | 33.102, New 31.103 |  |  |  |  | Mon 08/10/01 | Thu 26/09/02
6744 | 11014 | Deleted - SIP extensions for Integrity protection | - | 3 | Rel-5 | N1 | Mon 17/12/01 | Fri 28/06/02 | 100% | - | - | - | - | CN1 is not aware of any requirements and is not doing anything on this task | - |  |  | SP-69 |  | Fri 05/10/01 | Fri 21/06/02
6745 | 2574 | Security Aspects of Requirement for Network Configuration Independence | SEC1-NCI | 2 | Rel-5 | S3 | Mon 02/07/01 | Fri 28/12/01 | 100% | SP-010324 | - | AT&T Wireless | hugh.shieh@attws.com | Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C | 33.203 |  |  |  |  | Sat 09/06/01 | Mon 08/08/11
6746 | 1299 | IMS Lawful Interception | IMS-LI | 2 | Rel-5 | S3 | Mon 04/09/00 | Fri 29/03/02 | 100% | SP-010621 | - | Reg TP | berthold.wilhelm@regtp.de | SP#17 completed | 33.106, 33.107, New 33.108 |  |  |  |  | Sun 09/04/00 | Mon 08/08/11
6747 | 35007 | Charging and OAM&P for IMS | IMS-OAM | 2 | Rel-5 | S5 | Mon 25/12/00 | Wed 12/06/02 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6748 | 2036 | Multimedia codecs and protocols for conversational PS services | IMS-CODEC | 2 | Rel-5 | S4 | Wed 26/07/00 | Fri 27/09/02 | 100% | SP-000398 | - | Toshiba, Nokia | B. Aronson (Toshiba), pasi.s.ojala@nokia.com | - | 26.235, 26.236 |  |  |  |  | Wed 27/09/00 | Thu 27/03/03
6749 | 2039 | Codecs | - | 3 | Rel-5 | S4 | Wed 26/07/00 | Thu 14/03/02 | 100% | SP-000398 | - | - | - | - | 26.235, 26.236 |  |  |  |  | Thu 28/09/00 | Mon 25/03/02
6750 | 34020 | Transport protocols | - | 3 | Rel-5 | S4 | Tue 12/03/02 | Tue 12/03/02 | 100% | - | - | Nokia | P. Ojala | - | 26.236 |  |  |  |  | Mon 25/03/02 | Mon 25/03/02
6751 | 34006 | recommendation for QoS parameter values for various media types | - | 3 | Rel-5 | S4 | Mon 31/12/01 | Fri 27/09/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 28/09/00 | Mon 13/01/03
6752 | 11025 | IETF: RFC 3310 (HTTP Digest Authentication using AKA) | - | 3 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
6753 | 11026 | IETF: RFC 3329 (Security mechanism agreement for SIP connections) | - | 3 | Rel-5 | N1 | Fri 24/11/00 | Mon 13/05/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
6754 | 32003 | SIP message compression | - | 2 | Rel-5 | S2 | Mon 24/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Mon 25/03/02
6755 | 32004 | Stage 2 for SIP message compression | - | 3 | Rel-5 | S2 | Mon 24/09/01 | Fri 26/10/01 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Sat 24/11/01
6756 | 11015 | Compression signalling | - | 3 | Rel-5 | N1 | Fri 28/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6757 | 10001 | Stage 3 description of IMS interfaces | - | 2 | Rel-5 | NP | Wed 14/03/01 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 24/01/02
6758 | 1286 | Cx interface (HSS to CSCF) | - | 3 | Rel-5 | N4 | Wed 14/03/01 | Fri 07/06/02 | 100% | NP-010626 | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
6759 | 14997 | Mp interface (MRFC - MRFP) enhancements | - | 3 | Rel-5 | N4 | Wed 14/03/01 | Fri 08/03/02 | 100% | - | - | - | - | [DAB 08-03-02] - No work required in CN4 | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
6760 | 11016 | Mw interface (CSCF to P-CSCF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
6761 | 11018 | Mr interface (CSCF to MRF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 29/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
6762 | 14003 | Dx interface (I-CSCF to SLF) | - | 3 | Rel-5 | N4 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4 | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
6763 | 13001 | Go interface (GGSN to PCF) | - | 3 | Rel-5 | N3 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | [DAB - 23/05/03] - 100 % complete | - |  |  |  |  | Mon 08/10/01 | Fri 25/07/03
6764 | 11019 | ISC (IMS Service Control) Interface | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
6765 | 14006 | Sh interface (HSS to AS) | - | 3 | Rel-5 | N4 | Thu 14/02/02 | Fri 07/06/02 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4 | - |  |  |  |  | Thu 11/10/01 | Thu 30/05/02
6766 | 14998 | Si interface (HSS to IM-SSF) | - | 3 | Rel-5 | N4 | Wed 16/01/02 | Fri 30/08/02 | 100% | - | - | - | - | SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete) | - |  |  |  |  | Mon 25/03/02 | Thu 30/05/02
6767 | 11020 | Gm interface (UE to CSCF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
6768 | 11027 | Mi interface (CSCF to BGCF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
6769 | 11028 | Mj interface (BGCF to MGCF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
6770 | 11029 | Mk interface (BGCF to BGCF) | - | 3 | Rel-5 | N1 | Wed 14/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
6771 | 1310 | Support of VHE/OSA by entities and protocols of the IMS (e.g. CSCF) | IMS-ONOSA | 2 | Rel-5 | N5 | Fri 21/09/01 | Fri 07/06/02 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6772 | 12000 | CAMEL control of IMS services | IMS-CAMEL | 2 | Rel-5 | N2 | Mon 16/04/01 | Fri 06/09/02 | 100% | NP-020305 | - | Lucent | Angelica Remoquillo | - | - |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6773 | 12001 | Stage2 work 'general' | - | 3 | Rel-5 | N2 | Mon 16/04/01 | Fri 06/09/02 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Mon 08/10/01 | Mon 13/01/03
6774 | 12002 | Stage3 work 'CAP' | - | 3 | Rel-5 | N2 | Mon 07/01/02 | Fri 06/09/02 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Thu 24/01/02 | Mon 13/01/03
6775 | 12003 | Stage2 work 'Si interface' | - | 3 | Rel-5 | N2 | Mon 07/01/02 | Fri 06/09/02 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Thu 24/01/02 | Mon 13/01/03
6776 | 12004 | Stage3 work 'Si interface' | - | 3 | Rel-5 | N4 | Thu 14/02/02 | Fri 07/06/02 | 100% | - | - | - | - | [DAB 08-03-02] - UID 12004 is MASTER of UID 14998 | - |  |  |  |  | Thu 24/01/02 | Thu 30/05/02
6777 | 14004 | Deleted - SDM issues for CAMEL control of IMS | - | 3 | Rel-5 | N4 | Thu 14/02/02 | Fri 07/06/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | NP-17 |  | Mon 08/10/01 | Fri 12/12/08
6778 | 31002 | Pre-pay/real-time charging in IMS | - | 2 | Rel-5 | S1 | Fri 15/06/01 | Fri 15/03/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Wed 11/07/01 | Thu 28/02/02
6779 | 35005 | IMS Charging | OAM-CH | 2 | Rel-5 | S2,S5 | Mon 06/08/01 | Thu 12/09/02 | 100% | SP-010631 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.225 |  |  |  |  | Mon 08/10/01 | Mon 13/01/03
6780 | 32006 | Charging Implications of IMS architecture | - | 3 | Rel-5 | S2 | Mon 06/08/01 | Fri 16/11/01 | 100% | SP-010519 | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
6781 | 35006 | Charging management for IMS (off-line & on-line) | - | 3 | Rel-5 | S5 | Mon 19/11/01 | Thu 12/09/02 | 100% | - | - | - | - | - | 32.225 |  |  |  |  | Mon 08/10/01 | Fri 08/11/02
6782 | 34012 | Billing, accounting and call detail record aspects | - | 3 | Rel-5 | S5 | Thu 27/09/01 | Thu 12/09/02 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.225 |  |  |  |  | Tue 09/10/01 | Fri 08/11/02
6783 | 10002 | Other IETF dependencies | - | 2 | Rel-5 | NP | Fri 24/11/00 | Fri 07/06/02 | 100% | - | - | - | - | Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined) | - |  |  |  |  | Thu 11/10/01 | Mon 25/03/02
6784 | 11011 | IETF: draft-ietf-aaa-diameter - should be CN4 | - | 3 | Rel-5 | NP | Fri 24/11/00 | Fri 07/06/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | - |  |  |  |  | Mon 08/10/01 | Fri 12/12/08
6785 | 11999 | IETF: draft-johansson-aaa-diameter-mm-app - should be CN4 | - | 3 | Rel-5 | NP | Fri 24/11/00 | Fri 07/06/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Mon 08/10/01 | Fri 12/12/08
6786 | 1844 | Conformance Test Aspects - Provisioning of IMS | IMS-TEST | 2 | Rel-5 | T1 | Mon 18/03/02 | Fri 27/12/02 | 100% | - | - | - | - | The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008 | - |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
6787 | 41004 | Testing of support for IMS - prose | - | 2 | Rel-5 | T1 | Wed 18/09/02 | Tue 30/09/03 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123 |  |  |  |  | Thu 26/09/02 | Fri 12/12/08
6788 | 41005 | Testing of support for IMS - TTCN | - | 2 | Rel-5 | T1 | Wed 18/09/02 | Wed 03/03/04 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123 |  |  |  |  | Thu 26/09/02 | Fri 12/12/08
6789 | 740068 | UE Conformance Test Aspects – IMS for Converged IP Communications | IMS_CONV_IP_COM-UEConTest | 1 | Rel-5 | R5 | Wed 14/12/16 | Fri 15/12/17 | 100% | RP-171635 |  | Rohnert, Hans | Hans.Rohnert.ext@rohde-schwarz.com | UID: 740999->740068¦Rel-14->Rel-519/9/17: Compl:0%->75%¦ 8/1/18: Compl:75%->100% | 34.229-1, 34.229-2, 34.229-3 | 74 | 38 |  |  | Wed 01/02/17 | Mon 08/01/18
6790 | 34001 | Extended Transparent End-to-End PS Streaming Service | PSS-E | 1 | Rel-5 | S4 | Thu 03/01/02 | Mon 17/03/03 | 100% | SP-010392 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.233, 26.234 |  |  |  |  | Thu 28/06/01 | Thu 28/02/02
6791 | 34002 | Stage 1 for Extended Transparent End-to-End PS Streaming Service | - | 2 | Rel-5 | S1 | Mon 18/11/02 | Mon 17/03/03 | 100% | SP-010392 | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4 | 22.233 |  |  |  |  | Thu 28/06/01 | Mon 25/03/02
6792 | 31032 | Interaction with other services | - | 3 | Rel-5 | S1 | Mon 18/11/02 | Mon 17/03/03 | 100% | - | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4. Marked as closed 12/2008 (was marked 65% complete) | 22.233 |  |  |  |  | Mon 13/01/03 | Fri 12/12/08
6793 | 34003 | Stage 2 (version Rel-5 of TS 26.234) | - | 2 | Rel-5 | S4 | Thu 03/01/02 | Thu 14/03/02 | 100% | SP-010392 | - | - | - | 2nd resp SA2 | 26.234 |  |  |  |  | Thu 28/06/01 | Mon 25/03/02
6794 | 34019 | RTP usage model | - | 2 | Rel-5 | S4 | Thu 03/01/02 | Fri 06/12/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | 26.937 |  |  |  |  | Mon 25/03/02 | Fri 12/12/08
6795 | 501637 | Rel-5 Open Service Access (OSA) enhancements | OSA1 | 1 | Rel-5 | S1,S3 | Tue 27/04/99 | Fri 20/12/02 | 100% | SP-000216 | - | Siemens | joerg.swetina@neclab.eu | - | 22.127, 23.127, 29.198-x, 29.998-x |  |  |  |  | Tue 08/08/00 | Fri 25/07/03
6796 | 32010 | General Stage 2 for Rel-5 | - | 2 | Rel-5 | S2 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 47% complete) | - |  |  |  |  | Tue 21/11/00 | Fri 12/12/08
6797 | 1429 | OSA APIs for Multimedia Call Control | OSA1-CSCF | 2 | Rel-5 | S2 | Tue 11/07/00 | Fri 07/06/02 | 100% | - | - | - | - | For Rel5 even if completed by March | - |  |  |  |  | Wed 19/04/00 | Thu 24/01/02
6798 | 1430 | Stage 1 for OSA APIs for Multimedia Call Control | - | 3 | Rel-5 | S1 | Tue 11/07/00 | Thu 14/03/02 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127 |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
6799 | 15002 | Stages 2 and 3 for Multimedia Call Control | - | 3 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198-04 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
6800 | 15003 | Generic user interaction - Stage 3 | - | 2 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198-05 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
6801 | 15004 | OSA Charging - Stage 3 | - | 2 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198-12 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
6802 | 15007 | Call Control Service Mapping; Multiparty Call Control SIP - Stage 3 | - | 2 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.998-04-4 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
6803 | 15999 | WSDL APIs for SOAP/HTTP - Stage 3 | - | 2 | Rel-5 | N5 | Mon 11/09/00 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Mon 25/03/02 | Fri 21/06/02
6804 | 1419 | OSA Security | OSA1-SEC | 2 | Rel-5 | S3 | Tue 11/07/00 | Fri 20/12/02 | 100% | SP-000302 | - | Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Mon 08/08/11
6805 | 2121 | Stage 1 for OSA Security | - | 3 | Rel-5 | S1 | Tue 11/07/00 | Fri 09/11/01 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127 |  |  |  |  | Wed 22/11/00 | Thu 28/02/02
6806 | 1421 | OSA Stage 3 | - | 3 | Rel-5 | S3 | Mon 23/10/00 | Fri 14/06/02 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Sun 07/08/11
6807 | 1422 | security related SCF(s) definition | - | 3 | Rel-5 | N5 | Fri 21/09/01 | Fri 07/06/02 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6808 | 1423 | OSA changes required from supporting platforms, e.g. gsmSCF, HLR | - | 3 | Rel-5 | S3 | Mon 11/09/00 | Thu 14/12/00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Mon 08/08/11
6809 | 15017 | OSA Security (moved from Rel-6) | - | 3 | Rel-5 | S3 | Thu 14/03/02 | Fri 20/12/02 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 20/03/02 | Mon 08/08/11
6810 | 401424 | Interactions OSA - e-commerce | OSA1-ECOM | 2 | Rel-5 | S2 | Tue 27/04/99 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6811 | 1425 | Stage 1 for Interactions OSA - e-commerce | - | 3 | Rel-5 | S1 | Tue 27/04/99 | Thu 28/12/00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | Marked as closed 12/2008 (was marked 95% complete) | 22.127 |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
6812 | 1529 | Stages 2 and 3 for Interactions OSA - e-commerce | - | 3 | Rel-5 | N5 | Fri 21/09/01 | Fri 07/06/02 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Fri 28/07/00 | Fri 21/06/02
6813 | 15005 | Policy Management - Stage 3 | - | 2 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198-13 |  |  |  |  | Thu 28/02/02 | Thu 26/09/02
6814 | 15006 | Presence and Availability Management (PAM) - Stage 3 | - | 2 | Rel-5 | N5 | Tue 11/09/01 | Fri 07/06/02 | 100% | - | - | - | - | - | 29.198-14 |  |  |  |  | Thu 28/02/02 | Thu 26/09/02
6815 | 1786 | LCS - OSA interfaces | OSA1-LCSI | 2 | Rel-5 | S1 | Mon 11/09/00 | Fri 07/06/02 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | az: CN#13 - changed to Rel5 | - |  |  |  |  | Wed 19/04/00 | Mon 08/10/01
6816 | 1787 | Stage 1 for LCS - OSA interfaces | - | 3 | Rel-5 | S1 | Mon 11/09/00 | Fri 08/12/00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127 |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
6817 | 2124 | Stage 2 for LCS - OSA interfaces | - | 3 | Rel-5 | S2 | Mon 11/12/00 | Mon 11/12/00 | 100% | - | - | Ericsson | Christophe GOURRAUD | az 24/05/01: Rel4 completion 90->100%. | 23.127 |  |  |  |  | Wed 22/11/00 | Wed 06/06/01
6818 | 1788 | Stage 3 for LCS - OSA interfaces | - | 3 | Rel-5 | N5 | Fri 21/09/01 | Fri 07/06/02 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
6819 | 2540 | Access to User Profile | OSA2-UP | 2 | Rel-5 | S1 | Fri 01/06/01 | Thu 20/12/01 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
6820 | 1433 | Retrieval of Terminal capabilities | OSA2-TC | 2 | Rel-5 | S2 | Tue 11/07/00 | Fri 13/12/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
6821 | 1434 | Stage 1 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | S1 | Tue 11/07/00 | Wed 10/01/01 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127 |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
6822 | 1436 | Stages 2 and 3 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | N5 | Fri 21/09/01 | Fri 13/12/02 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
6823 | 2122 | Provisioning of the terminal capabilities | - | 3 | Rel-5 | T2 | Mon 02/04/01 | Fri 13/12/02 | 100% | - | - | - | - | According to T2 SWG1 M. Cataldo this is automatically supported by the MExE support of UAProf therefore 100% complete | 23.057 |  |  |  |  | Wed 22/11/00 | Fri 25/07/03
6824 | 1638 | CAMEL phase 4 | CAMEL4 | 1 | Rel-5 | S1 | Mon 17/04/00 | Fri 06/09/02 | 100% | NP-020486 | - | Nokia | keijo.palviainen@nokia.com | - | - |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
6825 | 1461 | Service requirements | - | 2 | Rel-5 | S1 | Mon 17/04/00 | Fri 14/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
6826 | 2012 | Call Party Handling | CAMEL4-CPH | 2 | Rel-5 | N2 | Mon 10/07/00 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 15/09/00 | Thu 30/05/02
6827 | 2013 | Mid call procedure for MO and MT calls | CAMEL4-MCP | 2 | Rel-5 | N2 | Mon 17/07/00 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 30/05/02
6828 | 2014 | Interactions with Optimal Routing | CAMEL4-IOR | 2 | Rel-5 | N2 | Mon 17/07/00 | Fri 08/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
6829 | 2015 | Inclusion of flexible tone injection | CAMEL4-IFTI | 2 | Rel-5 | N2 | Mon 17/07/00 | Fri 08/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
6830 | 2016 | CSE control over MT SMS | CAMEL4-CCSMS | 2 | Rel-5 | N2 | Mon 17/07/00 | Fri 08/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
6831 | 2460 | Notification of GPRS mobility management to CSE | CAMEL4-NMM | 2 | Rel-5 | N2 | Fri 02/03/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/03/01 | Thu 30/05/02
6832 | 2458 | Provision of location information of called subscriber | CAMEL4-LOCB | 2 | Rel-5 | N2 | Fri 02/03/01 | Fri 08/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/03/01 | Thu 28/02/02
6833 | 2514 | Inclusion of ODB data in the CSE_HLR interface | CAMEL4-ODB | 2 | Rel-5 | N2 | Mon 09/07/01 | Fri 08/03/02 | 100% | - | - | - | - | Added on May 29, 2001 | - |  |  |  |  | Tue 29/05/01 | Thu 28/02/02
6834 | 2515 | Location information during an ongoing call (Handover DP) | CAMEL4-HODP | 2 | Rel-5 | N2 | Mon 14/05/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 29/05/01 | Thu 30/05/02
6835 | 2516 | GPRS Any Time Interrogation | CAMEL4-ATI | 2 | Rel-5 | N2 | Mon 09/07/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 29/05/01 | Thu 30/05/02
6836 | 2599 | Transfer of IMEI (with SW version) to CSE (CAMEL4-ATI) | - | 2 | Rel-5 | N2 | Mon 09/07/01 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 25/03/02 | Thu 30/05/02
6837 | 12005 | Handling of partial implementations of CAMEL4 | CAMEL4-SUB | 2 | Rel-5 | N2 | Fri 08/03/02 | Fri 06/09/02 | 100% | - | - | - | - | stage2 and stage3 CRs for approval at CN#17 | - |  |  |  |  | Thu 30/05/02 | Thu 26/09/02
6838 | 2464 | Rel-5 MExE enhancements | MEXE5 | 1 | Rel-5 | T2 | Mon 26/03/01 | Fri 08/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Tue 13/03/01
6839 | 2466 | MExE Rel-5 Improvements and Investigations | MEXE5-ENHANC | 2 | Rel-5 | T2 | Mon 26/03/01 | Fri 08/03/02 | 100% | TP-010071 | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Thu 21/03/02
6840 | 1625 | Wideband Telephony Service - AMR | AMRWB | 1 | Rel-5 | S4 | Sat 01/01/00 | Fri 19/12/03 | 100% | SP-99354 | - | Siemens | Imre.Varga@mch.siemens.de | - | - |  |  |  |  | Tue 08/08/00 | Thu 27/03/03
6841 | 62 | Specification | - | 2 | Rel-5 | S4 | Sat 01/01/00 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 27/03/03
6842 | 31005 | Stage 1 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S1 | Mon 01/10/01 | Fri 22/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 05/10/01 | Fri 01/03/02
6843 | 32007 | Stage 2 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | Mon 03/01/00 | Mon 17/04/00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 05/10/01 | Thu 28/02/02
6844 | 1459 | Design Constraints for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | Mon 03/01/00 | Mon 07/02/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
6845 | 1460 | General Description for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | Mon 07/02/00 | Mon 17/04/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
6846 | 1626 | Feasibility Study for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | Fri 28/04/00 | Fri 02/06/00 | 100% | SP-000024 | - | - | - | S4,TD SP-000024: TR 26.901 v.4.0.0 | 26.901 |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
6847 | 1656 | N1 Aspects for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N1 | Fri 21/09/01 | Fri 21/12/01 | 100% | - | - | - | - | Some of N1 tasks: Indication of supported codecs by the MS, Bearer cap negociation, codec indication to MS | - |  |  |  |  | Tue 08/08/00 | Thu 26/09/02
6848 | 14005 | N4 work for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N4 | Wed 13/02/02 | Fri 07/06/02 | 100% | N4-010538 | - | - | - | CN4#11 30/11/01: No inputs to CN4 at this meeting | - |  |  |  |  | Tue 08/08/00 | Thu 30/05/02
6849 | 67 | Codec issues | - | 3 | Rel-5 | S4 | Mon 03/01/00 | Fri 07/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
6850 | 1627 | Codec qualification | - | 4 | Rel-5 | S4 | Wed 02/02/00 | Wed 31/05/00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
6851 | 74 | Codec selection tests | - | 4 | Rel-5 | S4 | Thu 01/06/00 | Fri 20/10/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
6852 | 891 | Codec selection | - | 4 | Rel-5 | S4 | Mon 23/10/00 | Fri 27/10/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
6853 | 34007 | TFO AMR-WB | AMRWB-TFO | 4 | Rel-5 | S4 | Tue 18/12/01 | Thu 14/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 26/09/02
6854 | 890 | Other codec issues (verif., characterization) | - | 4 | Rel-5 | S4 | Fri 29/09/00 | Fri 07/06/02 | 100% | - | - | - | - | ANSI C-Code , Test Sequences, Speech Transcoding Functions, Error Concealment of lost frames, Source Controlled Bit-Rate Operation, Voice Activity Detector, Frame Structure | 26.976 |  |  |  |  | Wed 05/04/00 | Mon 13/01/03
6855 | 34008 | AMR-WB and narrrowband interworking | AMRWB-IWG | 4 | Rel-5 | S4 | Thu 27/09/01 | Thu 14/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
6856 | 34009 | Interworking with fixed broadband networks | - | 4 | Rel-5 | S4 | Thu 27/09/01 | Thu 14/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
6857 | 34010 | Tones and announcements | - | 4 | Rel-5 | S4 | Thu 27/09/01 | Thu 14/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
6858 | 34011 | Deleted - WB Conferencing and WB Voice Group calls | - | 4 | Rel-5 | S1 | Mon 03/01/00 | Mon 03/01/00 | 100% | - | - | - | - | - | - |  |  | SP-07 |  | Tue 09/10/01 | Fri 25/07/03
6859 | 1855 | Conformance tests (CRs to 34 series) | - | 3 | Rel-5 | T1 | Sat 01/01/00 | Wed 12/04/00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Mon 13/01/03
6860 | 76 | Terminal Acoustic Characteristics | - | 4 | Rel-5 | S4 | Sat 01/01/00 | Wed 12/04/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Sat 01/04/00
6861 | 1628 | Definition for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | Sat 01/01/00 | Mon 31/01/00 | 100% | - | - | - | - | - | 26.131 |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
6862 | 1629 | Test specification for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | Tue 01/02/00 | Wed 12/04/00 | 100% | - | - | - | - | - | 26.132 |  |  |  |  | Tue 08/08/00 | Tue 20/03/01
6863 | 34004 | Floating-point ANSI-C code for the AMR-WB speech codec | AMRWB-FP | 2 | Rel-5 | S4 | Tue 25/09/01 | Thu 14/03/02 | 100% | SP-010459 | - | Nokia | janne.m.vainio@nokia.com | - | 26.204 |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
6864 | 80 | Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | GAMRWB | 2 | Rel-5 | GP | Mon 03/01/00 | Fri 28/06/02 | 100% | GP-000453 | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Wed 31/07/02
6865 | 50298 | Channel coding in 45.003 for Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | - | 3 | Rel-5 | GP | Mon 03/01/00 | Fri 05/04/02 | 100% | - | - | - | - | 50098 -> 50298 | - |  |  |  |  | Thu 01/02/01 | Tue 06/05/08
6866 | 2266 | Signalling for the A interface | - | 3 | Rel-5 | GP | Mon 03/01/00 | Fri 29/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6867 | 2267 | Signalling for Iu | - | 3 | Rel-5 | GP | Mon 03/01/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6868 | 2268 | Receiver performance in TS 45.005 | - | 3 | Rel-5 | GP | Mon 02/04/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6869 | 50000 | Link Adaptation in 45.009 | - | 3 | Rel-5 | GP | Mon 26/03/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Wed 31/07/02
6870 | 2269 | Deleted - GERAN MS conformance test for AMR-WB | - | 2 | Rel-5 | GP | Mon 03/01/00 | Fri 19/12/03 | 100% | GP-000454 | - | - | - | Not started 02/2003. Marked as stopped 12/2008 | - |  |  | SP-69 |  | Thu 01/02/01 | Fri 12/12/08
6871 | 2270 | Deleted - MS test for AMR-WB | - | 3 | Rel-5 | GP | Mon 03/01/00 | Fri 19/12/03 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
6872 | 2271 | GERAN BTS conformance test for AMR-WB | - | 2 | Rel-5 | GP | Mon 03/01/00 | Mon 02/12/02 | 100% | GP-000455 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
6873 | 1826 | Rel-5 Terminal interfaces | TLM5 | 1 | Rel-5 | T2 | Mon 14/05/01 | Wed 20/03/02 | 100% | - | - | - | - | Acronym changed from "TI, TLMN5" | - |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
6874 | 2573 | Terminal local model enhancements | TLM5 | 2 | Rel-5 | T2 | Mon 14/05/01 | Wed 20/03/02 | 100% | TP-010224 | - | - | - | - | 23.227 |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
6875 | 1536 | Rel-5 Location Services enhancements | LCS1 | 1 | Rel-5 | S2,S1,S3,S5,N4,R2,R3,GP | Mon 03/04/00 | Fri 27/06/03 | 100% | SP-010518 | - | Nokia | Jan Kall | . Acronym changed from "LCS1, Rel-5" | - |  |  |  |  | Fri 28/07/00 | Tue 24/03/15
6876 | 1600 | UE positioning for Rel-5 Location Services enhancements | LCS1-Uepos | 2 | Rel-5 | R2 | Mon 15/01/01 | Fri 29/03/02 | 100% | - | - | - | - | Acronym changed from "LCS1-Uepos, Rel-5" | - |  |  |  |  | Wed 26/07/00 | Tue 24/03/15
6877 | 2474 | UE positioning enhancements for 1.28 Mcps TDD | LCS-128Pos | 3 | Rel-5 | R2 | Mon 09/04/01 | Fri 29/03/02 | 100% | RP-010215 | - | CATT | Xiaohua Mei | - | 25.123, 25.224, 25.225, 25.302, 25.303, 25.304, 25.305, 25.331, 25.420, 25.423, 25.430, 25.433, New 25.859 |  |  |  |  | Tue 20/03/01 | Thu 28/02/02
6878 | 2125 | Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning | LCS-INTF | 3 | Rel-5 | R2 | Mon 15/01/01 | Fri 12/10/01 | 100% | RP-010414 | - | Qualcomm | Kirk Burroughs | RP#13 completed | - |  |  |  |  | Mon 27/11/00 | Thu 24/01/02
6879 | 1171 | Event Based and Periodic LCS | LCS1-EBP | 2 | Rel-5 | S1,S2,N4 | Mon 22/05/00 | Fri 07/06/02 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | - | - |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
6880 | 1641 | Stage 1 for Event based and Periodic LCS | - | 3 | Rel-5 | S1 | Mon 22/05/00 | Fri 17/11/00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | Evaluate Event based and Periodic LCS to be included in R00, corresponding Stage 1 description | 22.071 |  |  |  |  | Tue 08/08/00 | Sat 01/04/00
6881 | 1538 | Stage 2 for Event based and Periodic LCS | - | 3 | Rel-5 | S2 | Mon 06/11/00 | Fri 26/01/01 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 51% complete) | - |  |  |  |  | Fri 28/07/00 | Fri 12/12/08
6882 | 1179 | Impact on MAP | - | 3 | Rel-5 | N4 | Fri 15/03/02 | Fri 07/06/02 | 100% | - | - | - | - | Possible impact on UTRAN of LCS quality level request | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
6883 | 2436 | Location Services for GERAN in A/Gb Mode | LCS-GERAN | 2 | Rel-5 | GP | Mon 03/04/00 | Fri 08/02/02 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
6884 | 2437 | GERAN LCS Stage 2 (first release) | - | 3 | Rel-5 | GP,S2,G1,G2 | Mon 03/04/00 | Fri 08/02/02 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
6885 | 2438 | Gb interface support for LCS | - | 3 | Rel-5 | GP | Mon 03/04/00 | Fri 31/08/01 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
6886 | 2440 | L3 protocol support for LCS | - | 3 | Rel-5 | GP | Mon 03/04/00 | Fri 01/06/01 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
6887 | 2441 | Stage 3 for Location Services for GERAN in A/Gb Mode | - | 3 | Rel-5 | GP | Mon 03/04/00 | Fri 01/06/01 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
6888 | 2442 | Location Services for GERAN in Iu Mode | - | 2 | Rel-5 | S2,G1,G2,R2,R3 | Mon 03/04/00 | Fri 28/06/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6889 | 2443 | GERAN LCS Stage 2 | - | 3 | Rel-5 | S2,G1,G2 | Mon 03/04/00 | Fri 28/06/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6890 | 2444 | Iu-ps interface support for LCS | - | 3 | Rel-5 | R2,R3 | Mon 03/04/00 | Fri 28/06/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6891 | 2445 | Iu-cs interface support for LCS | - | 3 | Rel-5 | R2,R3 | Mon 03/04/00 | Fri 28/06/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6892 | 2446 | Iur-g interface support for LCS | - | 3 | Rel-5 | G1,G2 | Wed 23/01/02 | Fri 19/04/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | FFS | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6893 | 2447 | RRC protocol support for LCS | - | 3 | Rel-5 | G1,G2,R2,R3 | Mon 20/08/01 | Fri 30/11/01 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6894 | 2448 | Additional impacts on Broadcast of LCS data on packet channels | - | 3 | Rel-5 | G1,G2,R2,R3 | Mon 20/08/01 | Wed 05/12/01 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6895 | 2449 | Stage 3 for Location Services for GERAN in Iu Mode | - | 3 | Rel-5 | G1,G2,R2,R3 | Mon 25/03/02 | Fri 28/06/02 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6896 | 50068 | GERAN MS Conformance test for LCS | LCS-GERAN-MSconf | 2 | Rel-5 | GP | Mon 03/06/02 | Fri 27/06/03 | 100% | GP-000458 | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
6897 | 55069 | LCS MS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | Mon 03/06/02 | Fri 27/06/03 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
6898 | 55070 | LCS MS test cases | - | 3 | Rel-5 | G4,G5 | Mon 03/06/02 | Fri 27/06/03 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
6899 | 50069 | Deleted - GERAN BTS Conformance test for LCS | LCS-GERAN-BTSconf | 2 | Rel-5 | GP | Mon 03/06/02 | Fri 27/06/03 | 100% | GP-000459 | - | - | - | Not started 02/3003. Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Mon 21/05/12
6900 | 55071 | Deleted - LCS BTS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | Mon 03/06/02 | Fri 27/06/03 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Fri 12/12/08
6901 | 55072 | Deleted - LCS BTS test cases | - | 3 | Rel-5 | G4,G5 | Mon 03/06/02 | Fri 27/06/03 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Fri 12/12/08
6902 | 544 | LCS interoperation stage 2 aspects | - | 2 | Rel-5 | S2 | Mon 28/08/00 | Fri 28/06/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 17% complete) | - |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
6903 | 2434 | LCS interoperability aspects to GERAN (LCS-GERAN) | - | 2 | Rel-5 | GP,S5 | Mon 28/08/00 | Fri 28/06/02 | 100% | GP-000456 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 21/05/12
6904 | 2435 | Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN | - | 3 | Rel-5 | GP,S2,S5,R2,R3,G2,G1 | Mon 28/08/00 | Fri 28/06/02 | 100% | GP-000456 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 21/05/12
6905 | 1183 | FS on LCS support in the IMS | - | 2 | Rel-5 | S1 | Mon 12/02/01 | Fri 18/01/02 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 75% complete) | - |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
6906 | 35008 | Charging and OAM&P for LCS enhancements | LCS1-OAM | 2 | Rel-5 | S5 | Fri 21/09/01 | Fri 28/06/02 | 100% | SP-010461 | - | - | - | - | 32.200-series |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
6907 | 521 | New security aspects of LCS | LCS1-SEC | 2 | Rel-5 | S3,S2 | Fri 14/04/00 | Fri 28/12/01 | 100% | SP-000421 | - | Nokia | valtteri.niemi@nokia.com | SP#9 updated WID S3-000609 (Location services security) | 23.271, 43.059 |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
6908 | 32011 | Specification for the Le interface | LCS1-Le | 2 | Rel-5 | S2 | Mon 14/01/02 | Fri 15/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 24/01/02 | Mon 21/05/12
6909 | 32022 | Deleted - CHECK STATUS - Inter-GMLC interface | - | 2 | Rel-5 | S2 | Thu 30/05/02 | Mon 30/12/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-10 |  | Thu 30/05/02 | Fri 12/12/08
6910 | 501571 | Rel-5 Security enhancements (SEC1) | - | 1 | Rel-5 | S3 | Mon 21/02/00 | Fri 28/06/02 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | Added BB UE authentication and rapporteur added. TO BE DELETED | - |  |  |  |  | Sun 09/04/00 | Mon 08/08/11
6911 | 1576 | Rel-5 Network Domain Security (SEC1-NDS) | - | 2 | Rel-5 | S3 | Mon 21/02/00 | Fri 28/06/02 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE | New 33.200 (exisalso for Rel-4) |  |  |  |  | Tue 18/04/00 | Mon 08/08/11
6912 | 2576 | Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP) | - | 3 | Rel-5 | S3 | Thu 15/06/00 | Fri 15/03/02 | 100% | SP-010326 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286) | New 33.210 |  |  |  |  | Sat 09/06/01 | Mon 08/08/11
6913 | 1577 | Deleted - Control plane protection in core network (e.g., GTP, CAP, MAP/IP, provided by IPsec) | - | 3 | Rel-5 | S3 | Fri 12/05/00 | Fri 07/06/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-16 |  | Tue 18/04/00 | Fri 12/12/08
6914 | 1578 | Deleted - Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | Fri 12/05/00 | Thu 21/06/01 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | - |  |  | SP-12 |  | Sun 09/04/00 | Fri 12/12/08
6915 | 1579 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | Fri 14/09/01 | Fri 07/06/02 | 100% | - | - | - | - | Waiting for input from SA3!. Marked as stopped 12/2008 | - |  |  | NP-16 |  | Sun 09/04/00 | Fri 12/12/08
6916 | 1580 | Deleted - User plane protection in core network (e.g., provided by IPsec) | - | 3 | Rel-5 | S3 | Mon 21/02/00 | Fri 28/06/02 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | - |  |  | SP-16 |  | Tue 18/04/00 | Fri 12/12/08
6917 | 1581 | Deleted -Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | Mon 21/02/00 | Thu 21/06/01 | 100% | - | - | - | - | - | - |  |  | SP-12 |  | Sun 09/04/00 | Fri 08/11/02
6918 | 1582 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | Fri 14/09/01 | Fri 28/06/02 | 100% | - | - | - | - | 14/02/2002 requirements are not clear/not receivedMarked as closed 12/2008 (was marked 95 complete) | - |  |  | NP-16 |  | Sun 09/04/00 | Fri 12/12/08
6919 | 2243 | Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IUFLEX | 1 | Rel-5 | S2,N1,N4,R3,GP | Mon 02/10/00 | Fri 28/06/02 | 100% | SP-000619 | - | Ericsson | stephen.terrill@ericsson.com | No clear indication on the end date. Put to Rel5 by AS. | 23.236 |  |  |  |  | Wed 13/12/00 | Thu 24/01/02
6920 | 2244 | Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | S2 | Wed 03/01/01 | Fri 21/09/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 13/12/00 | Wed 19/09/01
6921 | 20000 | Stage 3: RAN node selecting CN node | - | 2 | Rel-5 | R3 | Mon 24/09/01 | Fri 22/03/02 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | Not identified | - |  |  |  |  | Wed 19/09/01 | Fri 01/03/02
6922 | 2248 | N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N1 | Mon 17/09/01 | Fri 28/06/02 | 100% | NP-010693 | - | - | - | - | 24.008 and check 29.018 |  |  |  |  | Wed 13/12/00 | Thu 26/09/02
6923 | 2249 | N4 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N4 | Mon 02/10/00 | Fri 08/03/02 | 100% | NP-000737 | - | - | - | DAB 12.12.01 - % complete to 66% | - |  |  |  |  | Wed 13/12/00 | Mon 25/03/02
6924 | 50067 | GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IDCRAN-GERAN | 2 | Rel-5 | GP | Fri 08/02/02 | Fri 28/06/02 | 100% | GP-020492 | - | Ericsson | ingemar.backlund@era.ericsson.se | Accept changes Gb over IP | - |  |  |  |  | Thu 23/05/02 | Thu 26/09/02
6925 | 51068 | Stage 2 (changes to ) | - | 3 | Rel-5 | G1 | Fri 08/02/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6926 | 51069 | 43.051 Introduction of support for IDNNS in GERAN Iu mode | - | 3 | Rel-5 | G1 | Fri 08/02/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6927 | 52070 | Stage 3 (changes to ) | - | 3 | Rel-5 | G2 | Fri 08/02/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6928 | 52077 | 48.016 Use of Gb interface concepts when a network applies IDNNS | - | 3 | Rel-5 | G2 | Fri 08/02/02 | Fri 28/06/02 | 100% | - | - | - | - | Closed, accept changes for Gb over IP | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6929 | 52078 | 48.018 Include MSC/VLR identity in CS IMSI paging | - | 3 | Rel-5 | G2 | Fri 08/02/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6930 | 2320 | Deleted - GERAN improvements 3 (new transport layer on interface A) | GEIMP3 | 1 | Rel-5 | GP | Fri 06/04/01 | Fri 20/12/02 | 100% | GP-010909 | - | - | - | Terminated - not standardized. Marked as stopped 12/2008 | - |  |  | SP-69 |  | Thu 01/02/01 | Fri 12/12/08
6931 | 2321 | Deleted - Evolution of the transport for A | GEIMP3-EtA | 2 | Rel-5 | GP | Fri 06/04/01 | Fri 20/12/02 | 100% | GP-010910 | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
6932 | 2322 | Deleted - Definition of a new A/Ater interface Transport Layer option based on the Iu Interface Transport Layer | - | 3 | Rel-5 | GP | Fri 06/04/01 | Fri 20/12/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
6933 | 2323 | Deleted - Adaptation of the Layer 3 BSSMAP procedures as required | - | 3 | Rel-5 | GP | Fri 06/04/01 | Fri 20/12/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
6934 | 501142 | Rel-5 Charging Management & Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM5 | 1 | Rel-5 | S5 | Mon 10/09/01 | Thu 12/09/02 | 100% | SP-010461 | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Fri 21/06/02
6935 | 35002 | Rel-5 Principles, high level Requirements and Architecture | - | 2 | Rel-5 | S5 | Mon 17/09/01 | Fri 28/06/02 | 100% | SP-010461 | - | Motorola | - | - | 32.101, 32.102 |  |  |  |  | Wed 26/04/00 | Fri 21/06/02
6936 | 35003 | Rel-5 Performance Management | - | 2 | Rel-5 | S5 | Mon 17/09/01 | Thu 12/09/02 | 100% | SP-010631 | - | Nortel | - | - | 32.4xy, 52.402 |  |  |  |  | Wed 26/04/00 | Fri 08/11/02
6937 | 35004 | Rel-5 Charging Management | - | 2 | Rel-5 | S5 | Mon 10/09/01 | Thu 12/09/02 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.200, 32.205, 32.215, 32.225, 32.235 |  |  |  |  | Wed 26/04/00 | Fri 08/11/02
6938 | 35001 | Rel-5 Network Infrastructure Management | - | 2 | Rel-5 | S5 | Fri 21/09/01 | Thu 12/09/02 | 100% | SP-010461 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.6xy, 32.3xy |  |  |  |  | Mon 08/10/01 | Fri 08/11/02
6939 | 2392 | GERAN enhancements for streaming services 1 (RLC enhancements) | - | 1 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | GP-010429 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6940 | 2394 | Concept for GERAN enhancements for streaming services 1 (RLC enhancements) | - | 2 | Rel-5 | GP | Mon 06/11/00 | Wed 31/10/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6941 | 2395 | RLC protocol enhancement (SDU Discard) | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6942 | 2396 | GERAN enhancements for streaming services 2 (usage of ECSD) | - | 1 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | GP-010430 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6943 | 2398 | Usage of ECSD Concept | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6944 | 2399 | Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6945 | 2400 | Stage 3 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6946 | 2401 | RLC PDU formats | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6947 | 2402 | MAC header | - | 2 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6948 | 2412 | GERAN/UTRAN interface evolution 1 (evolution of Iu PS) | GERUEV1 | 1 | Rel-5 | GP,R3 | Fri 01/09/00 | Fri 28/06/02 | 100% | GP-010481 | - | SBC | Marc Grant | SBC, Motorola, Nokia, Ericsson, Nortel | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6949 | 2413 | Evolution of Iu ps | GERUEV1-IuPS | 2 | Rel-5 | GP,R3 | Fri 01/09/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6950 | 2414 | Identification of GERAN requirements on Iu ps | - | 3 | Rel-5 | GP,R3 | Fri 01/09/00 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Tue 21/05/02
6951 | 2415 | Update of Evolution of Iu ps specifications | - | 3 | Rel-5 | GP,R3 | Mon 03/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6952 | 2416 | GERAN/UTRAN interface evolution 2 (evolution of Iu CS) | GERUEV2 | 1 | Rel-5 | GP,R3 | Thu 29/06/00 | Fri 28/06/02 | 100% | GP-010417 | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6953 | 2417 | Evolution of Iu cs | GERUEV2-IuCS | 2 | Rel-5 | GP,R3 | Thu 29/06/00 | Fri 28/06/02 | 100% | GP-000430 | - | Lucent | Krishna Balachandran | Lucent, Ericsson, AWS, Nortel | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6954 | 2418 | Identification of GERAN requirements on Iu cs | - | 3 | Rel-5 | GP,R3 | Thu 29/06/00 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6955 | 2419 | Update of Evolution of Iu cs specifications | - | 3 | Rel-5 | GP,R3 | Fri 01/09/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
6956 | 2556 | End to End QoS for PS Domain including IMS | E2EQoS | 1 | Rel-5 | S2,S5,N3 | Mon 28/08/00 | Fri 28/06/02 | 100% | SP-010343 | - | Ericsson | Johnson.oyama@era.ericcson.se | Acronym changed from "E2EQoS, Rel-5" | - |  |  |  |  | Fri 08/06/01 | Tue 24/03/15
6957 | 2557 | E2E QoSConcept and Architecture | - | 2 | Rel-5 | S2 | Wed 03/01/01 | Fri 07/09/01 | 100% | - | - | - | - | - | 23.207 |  |  |  |  | Fri 08/06/01 | Sat 24/11/01
6958 | 2558 | E2E QoS interworking | E2EQoS-IW | 2 | Rel-5 | N3 | Mon 28/08/00 | Fri 07/06/02 | 100% | NP-010528 | - | Lucent | Daisuke Yokota (yokota@lucent.com) | [DAB - 30/07/02] - % complete to 95% (if we exclude Diffserv). Marked as closed 12/2008 (was marked 95% complete) | 29.208, 29.207, 27.060, 29.061, 24.008, 24.228, , 24.229, 29.060, 29.163 |  |  |  |  | Fri 08/06/01 | Fri 12/12/08
6959 | 2559 | QoS Management (Provisioning and Monitoring) | E2EQoS-OAM | 2 | Rel-5 | S5 | Fri 21/09/01 | Fri 28/06/02 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Fri 08/06/01 | Fri 08/11/02
6960 | 2569 | Rel-5 Messaging enhancements | MESS5 | 1 | Rel-5 | T2 | Fri 15/06/01 | Mon 31/03/03 | 100% | - | - | - | - | support of UAProf, so this in my opinion is 100% complete | - |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6961 | 2571 | Rel-5 Multimedia Messaging (MMS) enhancements | MESS5-MMS | 2 | Rel-5 | T2 | Fri 15/06/01 | Mon 31/03/03 | 100% | TP-010130 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | - |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
6962 | 31000 | Definition of service requirements for MESS5-MMS | MESS5-SR | 3 | Rel-5 | S1 | Fri 15/06/01 | Fri 15/03/02 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.14 |  |  |  |  | Wed 04/07/01 | Fri 25/07/03
6963 | 42000 | Technical realization of MESS5-MMS | - | 3 | Rel-5 | T2 | Fri 15/06/01 | Fri 07/06/02 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | stage 3 MM7 is missing | 23.14 |  |  |  |  | Wed 04/07/01 | Thu 27/03/03
6964 | 42008 | WAP Forum dependency: MM1 stage 3 | - | 3 | Rel-5 | T2 | Fri 15/06/01 | Mon 31/03/03 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 80% complete) | - |  |  |  |  | Thu 30/05/02 | Fri 12/12/08
6965 | 34018 | MMS formats and codecs for MESS5-MMS | - | 3 | Rel-5 | S4 | Mon 03/12/01 | Fri 15/03/02 | 100% | - | - | - | - | - | 26.14 |  |  |  |  | Thu 24/01/02 | Thu 28/02/02
6966 | 2572 | Enhanced Messaging Service (EMS) enhancements | MESS5-EMS | 2 | Rel-5 | T2 | Fri 15/06/01 | Fri 08/03/02 | 100% | TP-010153 | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.04 |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
6967 | 31001 | Definition of service requirements for Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | S1 | Fri 15/06/01 | Fri 14/09/01 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | - |  |  |  |  | Wed 04/07/01 | Thu 28/02/02
6968 | 42001 | Technical realization of Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | T2 | Fri 15/06/01 | Fri 08/03/02 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.04 |  |  |  |  | Wed 04/07/01 | Thu 28/02/02
6969 | 50001 | GERAN Inter BSC NACC improvements over the Gb Interface | GERNACC | 1 | Rel-5 | GP | Mon 03/09/01 | Fri 28/06/02 | 100% | GP-012313 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6970 | 14501 | Modification of core network protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Cnmod | 2 | Rel-5 | N4,S2 | Mon 03/09/01 | Fri 19/04/02 | 100% | GP-011877 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6971 | 32502 | Stage 2 - Concept | - | 3 | Rel-5 | N4,S2 | Mon 03/09/01 | Wed 31/10/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6972 | 14502 | Stage 2 - 23.060 change - Definition of Inter BSC NACC | - | 3 | Rel-5 | N4,S2 | Mon 03/09/01 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6973 | 14503 | Stage 3 (changes to TS 29.060) | - | 3 | Rel-5 | N4 | Mon 03/09/01 | Fri 08/03/02 | 100% | - | - | - | - | IP 30/11/01: Input awaited from GERAN2 to CN4 | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6974 | 50002 | Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Gbmod | 2 | Rel-5 | GP | Fri 30/11/01 | Fri 28/06/02 | 100% | GP-012314 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6975 | 50003 | Stage 3 (changes to TS 48.018) | - | 3 | Rel-5 | GP | Fri 30/11/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
6976 | 50033 | Enhanced Power Control | EPC | 1 | Rel-5 | GP | Mon 26/11/01 | Fri 19/12/03 | 100% | GP-012748 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
6977 | 50034 | Realization of Enhanced power control and signalling support | - | 2 | Rel-5 | GP | Mon 26/11/01 | Fri 30/11/01 | 100% | GP-012749 | - | - | - | Completed 11/2001 | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
6978 | 50035 | Deleted - GERAN MS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | Mon 10/12/01 | Fri 19/12/03 | 100% | GP-012750 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Thu 13/02/03
6979 | 50036 | Deleted - GERAN BTS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | Mon 10/12/01 | Fri 19/12/03 | 100% | GP-012751 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Thu 13/02/03
6980 | 50037 | 8PSK AMR HR | 8PSK-AH | 1 | Rel-5 | GP | Mon 10/12/01 | Fri 19/12/03 | 100% | GP-012752 | - | - | - | Completed for Rel-5 | - |  |  |  |  | Mon 10/12/01 | Mon 13/01/03
6981 | 50038 | Definition of channel coding, performance requirements and signalling support | - | 2 | Rel-5 | GP | Mon 10/12/01 | Fri 28/06/02 | 100% | GP-012753 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Wed 31/07/02
6982 | 50061 | Concept | - | 3 | Rel-5 | GP | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6983 | 52004 | Changes to 44.018 | - | 3 | Rel-5 | G2 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6984 | 51025 | Changes to 45.001 | - | 3 | Rel-5 | G1 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6985 | 51026 | Changes to 45.002 | - | 3 | Rel-5 | G1 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6986 | 51027 | Changes to 45.003 | - | 3 | Rel-5 | G1 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6987 | 51028 | Changes to 45.005 | - | 3 | Rel-5 | G1 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6988 | 52005 | Changes to 24.008 | - | 3 | Rel-5 | G2 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6989 | 52006 | Changes to 48.058 | - | 3 | Rel-5 | G2 | Mon 10/12/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
6990 | 50039 | Deleted - GERAN MS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | Mon 10/12/01 | Fri 19/12/03 | 100% | GP-012754 | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Fri 12/12/08
6991 | 50040 | GERAN BTS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | Mon 10/12/01 | Fri 20/12/02 | 100% | GP-012755 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Mon 13/01/03
6992 | 13000 | Service Change and UDI Fallback | SCUDIF | 1 | Rel-5 | N3 | Mon 08/10/01 | Fri 07/06/02 | 100% | NP-020164 | - | Ericsson | Rune.Werner.Wiik@ericsson.no | - | 29.007, 27.001, 24.008 |  |  |  |  | Wed 19/09/01 | Fri 25/07/03
6993 | 501800 | Rel-5 USIM toolkit enhancements | USAT5 | 1 | Rel-5 | T3,S1 | Mon 05/06/00 | Fri 26/09/03 | 100% | - | - | G & D | Michael Meyer | Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk | 22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA) |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
6994 | 43002 | Deleted - Test specification for USIM toolkit security mechanisms | - | 2 | Rel-5 | T3 | Tue 28/05/02 | Fri 26/09/03 | 100% | TP-020028 | - | Gemplus | Sophie Viallet | Marked as stopped 12/2008 | - |  |  | TP-21 |  | Thu 30/05/02 | Mon 13/01/03
6995 | 1801 | Protocol Standardisation of a SIM Toolkit Interpreter | - | 2 | Rel-5 | T3,T2 | Mon 05/06/00 | Wed 22/01/03 | 100% | TP-000116 | - | G & D | Michael Meyer | 28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13. | T2 27.103 |  |  |  |  | Thu 14/09/00 | Mon 28/05/01
6996 | 2497 | Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | Mon 05/06/00 | Fri 16/03/01 | 100% | - | - | - | - | 5/10/2001: Stage one comepeted at TP-12. | 31.112, 31.113, 31.114 |  |  |  |  | Fri 30/03/01 | Fri 05/10/01
6997 | 2496 | Stage 2 and 3 | - | 3 | Rel-5 | T3 | Wed 03/01/01 | Fri 08/03/02 | 100% | - | - | - | - | 5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14. | 31.112, 31.113, 31.114 |  |  |  |  | Fri 30/03/01 | Tue 04/06/02
6998 | 2518 | Test specification for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | Mon 03/09/01 | Wed 22/01/03 | 100% | TP-010111 | - | Gemplus | Gérald MAUNIER | 5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete) | - |  |  |  |  | Fri 30/03/01 | Fri 12/12/08
6999 | 501802 | (U)SIM API | USAT5-API | 2 | Rel-5 | T3 | Wed 20/03/02 | Fri 20/09/02 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4 | - |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
7000 | 504301 | Rel-5 Java API Test specification | - | 3 | Rel-5 | T3 | Wed 20/03/02 | Fri 20/09/02 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | 51.013 |  |  |  |  | Thu 30/05/02 | Thu 26/09/02
7001 | 30001 | (Small) Technical Enhancements and Improvements for Rel-5 | TEI5 | 1 | Rel-5 | SP,CP,RP,GP | Mon 03/01/00 | Mon 03/01/00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system | - |  |  |  |  | Tue 26/09/00 | Sat 01/04/00
7002 | 25018 | Test - (Small) Technical Enhancements and Improvements for Rel-5 | TEI5_Test | 1 | Rel-5 | R5,T1 | Mon 03/01/00 | Wed 31/12/08 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP. | 34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3 |  |  |  |  | Tue 21/03/06 | Tue 06/05/08
7003 | 31013 | Technical Report on UE Functionality Split | UESPLIT | 1 | Rel-5 | S1 | Mon 03/01/00 | Mon 01/05/00 | 100% | SP-010484 | - | Motorola | jian.j.wu@motorola.com | - | New 22.944 |  |  |  |  | Thu 11/10/01 | Tue 14/09/10
7004 | 2520 | User Equipment Management | UEM | 1 | Rel-5 | S5 | Thu 21/06/01 | Fri 28/06/02 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802 |  |  |  |  | Wed 06/06/01 | Fri 21/06/02
7005 | 35000 | FS on User Equipment (UE) Management | OAM-UEM | 2 | Rel-5 | S5 | Thu 21/06/01 | Fri 28/06/02 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802 |  |  |  |  | Tue 03/07/01 | Fri 21/06/02
7006 | 50201 | Flow control supporting an MS with multiple data flows with different QoS over the Gb interface | FlowCon | 1 | Rel-5 | GP | Mon 24/06/02 | Fri 30/08/02 | 100% | GP-021767 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50101 -> 50201 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
7007 | 50202 | Update of stage 2 specifications | - | 2 | Rel-5 | GP | Mon 24/06/02 | Fri 30/08/02 | 100% | - | - | - | - | 50102 -> 50202 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
7008 | 32097 | Concept document 23.060 (changes to) | - | 3 | Rel-5 | S2 | Fri 28/06/02 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/07/02 | Thu 26/09/02
7009 | 50203 | Flow Control | - | 3 | Rel-5 | GP | Mon 24/06/02 | Fri 28/06/02 | 100% | - | - | - | - | 50103 -> 50203 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
7010 | 50204 | Modification of BSSGP protocol | - | 2 | Rel-5 | GP | Mon 24/06/02 | Fri 28/06/02 | 100% | GP-021508 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50104 -> 50204 | - |  |  |  |  | Wed 31/07/02 | Fri 26/10/12
7011 | 52095 | Stage 3 (changes to 48.018) | - | 3 | Rel-5 | G2 | Mon 24/06/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/07/02 | Thu 26/09/02
7012 | 50058 | Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF) | - | 1 | Rel-5 | GP | Fri 19/04/02 | Fri 28/11/03 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
7013 | 50059 | Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode) | - | 2 | Rel-5 | GP | Fri 19/04/02 | Fri 22/08/03 | 100% | GP-021263 | - | - | - | Marked as closed 12/2008 (was marked 26% complete) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
7014 | 50060 | Deleted - Multiple TBF Concept paper | - | 3 | Rel-5 | GP | Fri 19/04/02 | Fri 22/08/03 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
7015 | 51001 | Deleted - Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-5 | G1 | Fri 19/04/02 | Fri 22/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 23/05/02 | Thu 12/11/09
7016 | 50062 | Deleted - Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-5 | G2 | Fri 19/04/02 | Fri 22/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 23/05/02 | Thu 12/11/09
7017 | 50206 | Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing | - | 2 | Rel-5 | GP | Mon 24/06/02 | Fri 28/11/03 | 100% | GP-022098 | - | Ericsson | ingemar.backlund@era.ericsson.se | 08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Wed 31/07/02 | Thu 12/11/09
7018 | 54101 | Deleted - MS conformance tests for Multiple TBF in A/Gb mode | - | 3 | Rel-5 | G4 | Mon 24/06/02 | Fri 28/11/03 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Wed 31/07/02 | Thu 12/11/09
7019 | 2345 | Alignment of 3G functional split and Iu | GER3GAL | 1 | Rel-5 | GP | Thu 08/06/00 | Fri 19/12/03 | 100% | GP-021256 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 26/09/02
7020 | 2346 | GERAN user / control plane | GER3GAL-GUCOPL | 2 | Rel-5 | GP | Mon 07/08/00 | Fri 30/08/02 | 100% | GP-021255 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
7021 | 2347 | Alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | Mon 07/08/00 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
7022 | 50300 | Enhanced power control - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 31/08/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 12/09/01
7023 | 2423 | Stage 2 - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | Mon 07/08/00 | Fri 29/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7024 | 2348 | Adoption of the UTRAN PDCP | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 21/12/01 | 100% | - | - | - | - | Responsible is GERAN¦RAN WG2 help may be needed. | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
7025 | 50043 | Development of RLC / MAC | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Mon 13/01/03
7026 | 50044 | Development of GERAN RRC | - | 4 | Rel-5 | GP | Fri 22/06/01 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
7027 | 50045 | Ciphering and integrity protection concept paper | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7028 | 50046 | Multiple TBF or equivalent Concept paper | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 08/02/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7029 | 50047 | Paging concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7030 | 50048 | Dedicated Physical subchannels, includes traffic and control channels | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7031 | 50049 | Iu support and broadcast concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7032 | 50050 | Impact of using RLC instead of LAPDm concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 08/02/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7033 | 50051 | Contention resolution, mobile station identity, and access concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7034 | 50052 | PDCP concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 19/04/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7035 | 50053 | Downlink delayed TBF release | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 30/08/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Thu 26/09/02
7036 | 50054 | Add transparent RLC Concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 08/02/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7037 | 50055 | Handover concept | - | 4 | Rel-5 | GP | Fri 31/08/01 | Fri 08/02/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
7038 | 2424 | Physical layer alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | Mon 06/11/00 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7039 | 2356 | PDTCH/TCH in 45.003 | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7040 | 2357 | Control channels in 45.003 | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7041 | 2358 | Receiver performance in 45.005 for PDTCH/TCH and control channels | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7042 | 2359 | Iu rg interface | GER3GAL-Iurg | 2 | Rel-5 | GP,RP | Mon 06/11/00 | Fri 28/06/02 | 100% | GP-010428 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
7043 | 2425 | Inter BSS interface | - | 3 | Rel-5 | GP,RP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
7044 | 2360 | Identification of requirements for Inter BSS interface | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7045 | 2361 | Stage 2 for Inter BSS interface | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7046 | 2362 | Adoption of relevant parts from Iur - for Inter BSS interface | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7047 | 2363 | Complementation with GERAN specifics - for Inter BSS interface | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7048 | 2364 | Stage 3 for Inter BSS interface | - | 4 | Rel-5 | GP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7049 | 2426 | Inter BSS-RNS interface | - | 3 | Rel-5 | GP,RP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
7050 | 2365 | Identification of requirements for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7051 | 2366 | Stage 2 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7052 | 2367 | Adoption of relevant parts from Iur - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7053 | 2368 | Complementation with GERAN specifics - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | Wed 30/01/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7054 | 2369 | Stage 3 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | Wed 30/01/02 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7055 | 2370 | Voice over GERAN PS and CS concept | - | 2 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | GP-011252 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
7056 | 2371 | Architecture for A, Iu cs and Iu ps | - | 3 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7057 | 2372 | Transcoder position/operation | - | 3 | Rel-5 | GP | Mon 06/11/00 | Fri 13/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7058 | 2373 | Handover for Voice over GERAN PS and CS | - | 3 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7059 | 2374 | RTP payload | - | 3 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
7060 | 2375 | Codec renegotiation concept | - | 3 | Rel-5 | GP,R3 | Mon 06/11/00 | Fri 29/03/02 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 08/11/02 | Fri 08/11/02
7061 | 2376 | LA | - | 3 | Rel-5 | GP | Mon 06/11/00 | Fri 13/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 08/11/02 | Fri 08/11/02
7062 | 2388 | Deleted - GERAN MS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | Mon 11/06/01 | Fri 19/12/03 | 100% | GP-021253 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
7063 | 2389 | Deleted - MS test for GERAN interface evolution | - | 3 | Rel-5 | GP | Mon 11/06/01 | Fri 19/12/03 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
7064 | 2390 | GERAN BSS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | Thu 08/06/00 | Fri 19/12/03 | 100% | GP-021254 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  |  |  | Thu 01/02/01 | Fri 12/12/08
7065 | 2391 | Deleted - BSS test | - | 3 | Rel-5 | GP | Thu 08/06/00 | Fri 19/12/03 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
7066 | 2330 | GERAN support for IMS | GERIMS | 1 | Rel-5 | GP | Mon 01/05/00 | Fri 20/12/02 | 100% | GP-010420 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7067 | 2331 | GERAN Header adaptation | GERIMS-HEADAPT | 2 | Rel-5 | GP,S2,RP | Mon 01/05/00 | Fri 20/12/02 | 100% | GP-010421 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
7068 | 2332 | Definition of compression and removal modes for PDCP protocol | - | 3 | Rel-5 | GP,S2,RP | Mon 24/07/00 | Fri 01/09/00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7069 | 2333 | Conceptual description in stage 2 | - | 3 | Rel-5 | GP,S2,RP | Mon 01/05/00 | Wed 31/10/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7070 | 2334 | Necessary changes on stage 3 regarding header removal | - | 3 | Rel-5 | GP,S2,RP | Mon 06/11/00 | Fri 20/12/02 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
7071 | 2335 | Deleted - GERAN Radio access bearer design for IMS | GERIMS-RABDES | 2 | Rel-5 | GP,S2,RP | Mon 06/11/00 | Fri 28/06/02 | 100% | GP-010422 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-10 |  | Thu 01/02/01 | Fri 12/12/08
7072 | 2422 | Deleted - MuM control signalling for conversational multimedia services | - | 3 | Rel-5 | GP,S2,RP | Mon 06/11/00 | Fri 28/06/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-10 |  | Thu 01/02/01 | Fri 12/12/08
7073 | 2431 | Deleted - Identification of requirements for MuM control signalling for conversational multimedia services | - | 4 | Rel-5 | GP,S2,RP | Mon 06/11/00 | Fri 08/02/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | - |  |  | GP-08 |  | Tue 13/02/01 | Mon 13/01/03
7074 | 2337 | Deleted - Necessary modifications due to SIP | - | 4 | Rel-5 | GP,S2,RP | Mon 06/05/02 | Fri 28/06/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | - |  |  | GP-10 |  | Thu 01/02/01 | Mon 13/01/03
7075 | 2341 | Deleted - GERAN MS Conformance test for support of IMS | GERIMS-MSconf | 2 | Rel-5 | GP | Mon 11/06/01 | Fri 20/12/02 | 100% | GP-010424 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
7076 | 2342 | Deleted - MS test for support of IMS | - | 3 | Rel-5 | G4 | Mon 11/06/01 | Fri 20/12/02 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
7077 | 2343 | Deleted - GERAN BTS Conformance test for support of IMS | GERIMS-BTSconf | 2 | Rel-5 | GP | Mon 11/06/01 | Fri 20/12/02 | 100% | GP-010425 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
7078 | 54001 | MS Conformance Testing of Dual Transfer Mode | MSCTDTM | 1 | Rel-5 | G4,G5 | Mon 11/11/02 | Fri 07/02/03 | 100% | GP-023236 | - | Vodafone | Dave Fox | Needed to complete DTM (R99) | - |  |  |  |  | Mon 13/01/03 | Thu 13/02/03
7079 | 32033 | Handling of early Ues | LATE_UE | 1 | Rel-5 | S2 | Mon 03/01/00 | Fri 27/06/03 | 100% | SP-030125 | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 15/01/03
7080 | 32031 | Feasibility Study on Handling of early Ues | - | 2 | Rel-5 | S2 | Mon 07/10/02 | Fri 13/12/02 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 15/01/03
7081 | 32032 | Stage 2 for Handling of early Ues | - | 2 | Rel-5 | S2 | Mon 06/01/03 | Fri 27/06/03 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 23/07/03
7082 | 22001 | FS for the Early Mobile Handling in UTRAN | FSEarlyUE | 2 | Rel-5 | R2 | Mon 09/09/02 | Fri 06/06/03 | 100% | - | - | Vodafone | alan.law@vodafone.com | - | - |  |  |  |  | Mon 16/09/02 | Fri 04/07/03
7083 | 96 | Note: Stage 3 RAN part not shown | - | 2 | Rel-5 | RP | Mon 03/01/00 | Mon 03/01/00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 09/10/00 | Thu 11/10/01
7084 | 0 | --- RELEASE 4 --- | - | 1 | Rel-4 | NP,GP,RP,SP,TP | Mon 03/01/00 | Fri 30/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
7085 | 1861 | Miscellaneous UE Conformance Testing Activities | MISTST1 | 1 | Rel-4 | T1 | Mon 02/04/01 | Wed 01/12/04 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Mon 13/01/03
7086 | 1862 | Optimization of Test Time, RF Aspects (FDD) | MISTST1-OpFDD | 2 | Rel-4 | T1 | Mon 24/09/01 | Wed 03/09/03 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete) | 34.121 |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
7087 | 1863 | Optimization of Test Time, RF Aspects (TDD) | MISTST1-OpTDD | 2 | Rel-4 | T1 | Mon 24/09/01 | Wed 03/09/03 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times | 34.122 |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
7088 | 1907 | Extensions to R99 Test cases | MISTST1-Ext | 2 | Rel-4 | T1 | Mon 02/04/01 | Tue 02/12/03 | 100% | TP-030052 | - | - | - | Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete) | 34.123 p 1,2 |  |  |  |  | Thu 24/08/00 | Fri 12/12/08
7089 | 2564 | Extension to R99 Test cases - TTCN | - | 2 | Rel-4 | T1 | Fri 28/06/02 | Wed 03/03/04 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Fri 01/06/01 | Fri 12/12/08
7090 | 2565 | Creation of R99 TCs for TDD - prose | MISTST1-TDD | 2 | Rel-4 | T1 | Mon 01/10/01 | Thu 01/07/04 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | 34.123-1 |  |  |  |  | Fri 01/06/01 | Fri 12/12/08
7091 | 2566 | Deleted - Creation of R99 TCs for TDD - TTCN | - | 2 | Rel-4 | T1 | Tue 03/09/02 | Wed 01/12/04 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-26 |  | Fri 01/06/01 | Fri 12/12/08
7092 | 1908 | Deleted - Review all other work items for impact on new or exiting 34 series specs. | - | 2 | Rel-4 | T1 | Tue 02/07/02 | Fri 27/12/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.121,122,123,125 |  |  | TP-18 |  | Wed 06/09/00 | Fri 12/12/08
7093 | 1340 | Real Time Facsimile | FAX-RT | 1 | Rel-4 | S1 | Tue 22/02/00 | Fri 23/06/00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
7094 | 1341 | Real Time Fax | - | 2 | Rel-4 | S2 | Tue 22/02/00 | Fri 23/06/00 | 100% | SP-000169 | - | - | - | postponed from R99 to R00, SP-000169 | - |  |  |  |  | Sun 09/04/00 | Wed 15/11/00
7095 | 1808 | Terminal capabilities, AT commands | - | 3 | Rel-4 | T2 | Tue 22/02/00 | Fri 23/06/00 | 100% | - | - | - | - | - | 21.904, 27.007 |  |  |  |  | Thu 14/09/00 | Sat 01/04/00
7096 | 1343 | Signalling aspects (e.g. ICM) | - | 3 | Rel-4 | N1 | Tue 22/02/00 | Fri 23/06/00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 15/11/00
7097 | 1648 | Service provision | - | 3 | Rel-4 | N3 | Tue 22/02/00 | Fri 23/06/00 | 100% | - | - | - | - | - | 23.146 |  |  |  |  | Tue 08/08/00 | Wed 15/11/00
7098 | 1345 | Review whether service/stage 1 aspects need to be aligned | - | 3 | Rel-4 | S1 | Fri 14/04/00 | Fri 23/06/00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
7099 | 1346 | Review whether architecture/stage 2 aspects need to be aligned | - | 3 | Rel-4 | S2 | Fri 14/04/00 | Fri 23/06/00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
7100 | 1539 | Transparent End-to-End PS mobile streaming application | PSTREAM | 1 | Rel-4 | S4 | Mon 03/04/00 | Wed 21/03/01 | 100% | SP-000345 | - | - | - | - | 26.233, 26.234 |  |  |  |  | Fri 28/07/00 | Tue 20/03/01
7101 | 1818 | Multimedia Messaging | MMS4 | 1 | Rel-4 | T2,S1 | Tue 22/02/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | Acronym changed from "MMS, Rel-4" | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
7102 | 136 | Definition of service requirements for Multimedia Messaging | - | 2 | Rel-4 | S1 | Tue 22/02/00 | Wed 31/05/00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
7103 | 1819 | Review of definition of service requirements | - | 2 | Rel-4 | T2 | Thu 01/06/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | - | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
7104 | 1820 | Technical Realisation | - | 2 | Rel-4 | T2 | Mon 10/04/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
7105 | 1821 | Review of definition of reference Achitecture model | - | 3 | Rel-4 | T2 | Mon 10/04/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
7106 | 1822 | Fulfill Requirements of Stage 1 | - | 3 | Rel-4 | T2 | Mon 10/04/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | e.g. minimum set of media formats, media format conversion, personalization of MMS. | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
7107 | 1823 | Definition of MMS primitives in Stage 2 | - | 3 | Rel-4 | T2 | Mon 10/04/00 | Wed 14/03/01 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
7108 | 1541 | Transcoder-Free Operation | TrFO | 1 | Rel-4 | N4,S2,N1 | Mon 03/01/00 | Fri 30/03/01 | 100% | - | - | - | - | Lead given to CN4 from CN | - |  |  |  |  | Fri 28/07/00 | Mon 25/03/02
7109 | 112 | Out-of-Band Transcoder Control solution | TrFO-OoBTC | 2 | Rel-4 | N4 | Mon 03/01/00 | Fri 30/03/01 | 100% | N4-000531 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | - |  |  |  |  | Thu 06/04/00 | Wed 08/07/09
7110 | 1512 | implementation in UTRAN | TrFO-OoBTC-UTRAN | 3 | Rel-4 | R3 | Mon 11/09/00 | Fri 30/03/01 | 100% | - | - | Siemens | Alexander Vesely | moved according to NP-000575 | 25.401, 25.410, 25.413, 25.415, 23.153 |  |  |  |  | Wed 26/07/00 | Tue 20/03/01
7111 | 896 | Impact on architecture, Principles and Terminology | - | 3 | Rel-4 | S2 | Mon 03/01/00 | Fri 20/10/00 | 100% | - | - | - | - | e.g. study cascading TrFO/TFO/TrFO | - |  |  |  |  | Thu 06/04/00 | Wed 13/12/00
7112 | 1657 | Codec Negotiation between UE and MSC | - | 3 | Rel-4 | N1 | Mon 14/08/00 | Fri 02/02/01 | 100% | - | - | Motorola | Andrew Howell | the link to NP-000085has been deleted because refering to a R99 status sheet | 24.008, 23.009, 23.108, (29.002) |  |  |  |  | Tue 08/08/00 | Mon 04/12/00
7113 | 115 | Codec Negotiation inter MSC | - | 3 | Rel-4 | N4 | Mon 03/07/00 | Fri 22/12/00 | 100% | - | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues | - |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
7114 | 894 | Bearer establishment inter MSC | - | 3 | Rel-4 | N4 | Mon 03/07/00 | Fri 22/12/00 | 100% | NP-000127 | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex. | 23.153 |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
7115 | 905 | Speech Transcoder: Location and Control at the UMTS Core Network Border | TrFO-STLC | 2 | Rel-4 | S2 | Mon 10/04/00 | Fri 29/09/00 | 100% | - | - | - | - | WI description and Tdoc S2-99352 | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
7116 | 124 | Transcoder at Edge | - | 3 | Rel-4 | NP | Mon 10/04/00 | Fri 29/09/00 | 100% | - | - | - | - | WI description and Tdoc S2-99352 | - |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
7117 | 2310 | GERAN improvements 1 (Gb over IP) | GEIMP1 | 1 | Rel-4 | GP | Tue 09/05/00 | Mon 19/03/01 | 100% | GP-000433 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7118 | 2311 | Gb over IP (Ip-fication of Gb) | GbIP | 2 | Rel-4 | GP | Tue 09/05/00 | Mon 19/03/01 | 100% | GP-000434 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7119 | 2312 | Concept of Gb over IP (Ip-fication of Gb) | - | 3 | Rel-4 | GP | Tue 09/05/00 | Fri 10/11/00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7120 | 2313 | Changes to 08.16, 08.18 | - | 3 | Rel-4 | GP | Tue 09/05/00 | Mon 19/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7121 | 2314 | GERAN improvements 2 (NACC) | GEIMP2 | 1 | Rel-4 | GP | Mon 06/11/00 | Tue 10/06/03 | 100% | GP-012812 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
7122 | 2315 | Gb enhancements | Gben | 2 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | GP-000436 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7123 | 2316 | Intra BSC NACC (Network Assisted Cell Change) | - | 3 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7124 | 2420 | Concept | - | 4 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7125 | 2317 | Changes in 03.64 | - | 4 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7126 | 2318 | Changes in 04.60 | - | 4 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7127 | 2319 | Changes in 44.008 | - | 4 | Rel-4 | GP | Mon 06/11/00 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
7128 | 50030 | MS conformance test for Intra BSC NACC | GEIMP2-Msconf | 2 | Rel-4 | GP | Fri 30/11/01 | Tue 10/06/03 | 100% | GP-012811 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
7129 | 50299 | Changes in 51.010 | - | 3 | Rel-4 | G5,G4 | Fri 30/11/01 | Tue 10/06/03 | 100% | - | - | - | - | az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Thu 23/05/02 | Tue 06/05/08
7130 | 2324 | GERAN improvements 4 (Delayed TBF) | GEIMP4 | 1 | Rel-4 | GP | Mon 15/01/01 | Fri 08/06/01 | 100% | GP-010363 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7131 | 2325 | Gb enhancements 2 | GEIMP4-Gben2 | 2 | Rel-4 | GP | Mon 15/01/01 | Fri 08/06/01 | 100% | GP-010363 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
7132 | 2429 | Stage 2 for Gb enhancements 2 | - | 3 | Rel-4 | GP | Mon 15/01/01 | Fri 08/06/01 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/02/01 | Fri 01/03/02
7133 | 2421 | Stage 3 (changes in 44.060) | - | 3 | Rel-4 | G2 | Mon 15/01/01 | Fri 06/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
7134 | 2327 | Definition of enhanced countdown procedure | - | 4 | Rel-4 | G2 | Mon 15/01/01 | Fri 06/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
7135 | 2328 | Definition of enhanced TBF release procedure | - | 4 | Rel-4 | G2 | Mon 15/01/01 | Fri 06/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
7136 | 2329 | Definition of USF=FREE type polling mechanism on PDCH | - | 4 | Rel-4 | G2 | Mon 15/01/01 | Fri 06/04/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
7137 | 1222 | Low Chip Rate TDD option | LCRTDD | 1 | Rel-4 | R1 | Wed 19/07/00 | Tue 02/12/03 | 100% | - | - | CWTS | G. Yang | - | - |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7138 | 1223 | Physical layer for Low Chip Rate TDD option | LCRTDD-Phys | 2 | Rel-4 | R1 | Wed 19/07/00 | Fri 30/03/01 | 100% | - | - | CWTS | G. Yang | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
7139 | 1224 | Layer 2 and layer 3 protocol aspects | LCRTDD-L23 | 2 | Rel-4 | R2 | Wed 19/07/00 | Fri 30/03/01 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
7140 | 1225 | RF radio transmission/reception, system performance requirements and conformance testing | LCRTDD-RF | 2 | Rel-4 | R4 | Mon 14/08/00 | Fri 30/03/01 | 100% | - | - | CWTS | D. Zhang | - | - |  |  |  |  | Wed 26/04/00 | Fri 30/03/01
7141 | 1227 | UE radio access capability | LCRTDD-UErac | 2 | Rel-4 | R2 | Mon 14/08/00 | Fri 30/03/01 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
7142 | 1228 | Iub/Iur protocol aspects - for Low Chip Rate TDD option | LCRTDD-IubIur | 2 | Rel-4 | R3 | Mon 14/08/00 | Fri 30/03/01 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Tue 20/03/01
7143 | 2262 | Low chiprate TDD interworking with GERAN | - | 2 | Rel-4 | GP | Fri 01/09/00 | Fri 19/01/01 | 100% | GP-000432 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7144 | 2263 | Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD | - | 3 | Rel-4 | GP | Fri 01/09/00 | Fri 19/01/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7145 | 2103 | Conformance Test Aspects - Low Chip Rate TDD | - | 2 | Rel-4 | T1 | Mon 17/09/01 | Tue 02/12/03 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 01/11/00 | Sat 01/04/00
7146 | 2217 | Testing Layer 2 and layer 3 protocol aspects | - | 3 | Rel-4 | T1 | Mon 17/09/01 | Wed 02/07/03 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | 34.123-1, 34.123-2 |  |  |  |  | Thu 16/11/00 | Fri 14/03/03
7147 | 2562 | Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN | - | 3 | Rel-4 | T1 | Tue 03/12/02 | Tue 02/12/03 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3 |  |  | TP-22 |  | Thu 31/05/01 | Fri 14/03/03
7148 | 2218 | Testing RF Radio Transmission and Reception | - | 3 | Rel-4 | T1 | Mon 17/09/01 | Fri 28/06/02 | 100% | TP-030052 | - | - | - | duration set to 6 months (was 0), finish date set | - |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
7149 | 1322 | Enable bearer independent CS architecture | CSSPLIT | 1 | Rel-4 | S2,N3,N4 | Mon 03/01/00 | Fri 01/03/02 | 100% | SP-000288 | - | Siemens | Alexander Milinski | - | - |  |  |  |  | Sun 09/04/00 | Sat 06/08/11
7150 | 1323 | Enable bearer-independent call control | - | 2 | Rel-4 | N4 | Mon 03/01/00 | Thu 16/08/01 | 100% | N4-000512 | - | Ericsson | Heinz-Peter.Keutmann@eed.ericsson.se | DAB 12.12.01 should be 100% hence closed | - |  |  |  |  | Sun 09/04/00 | Thu 24/01/02
7151 | 1516 | Architecture and Stage 2 description | - | 3 | Rel-4 | S2 | Mon 03/01/00 | Fri 08/09/00 | 100% | - | - | - | - | R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000 | 23.002 |  |  |  |  | Fri 28/07/00 | Sat 01/04/00
7152 | 1325 | Standardisation of protocols (control & user planes) over Nb interface | - | 3 | Rel-4 | N3 | Tue 02/01/01 | Fri 30/03/01 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 30/05/01
7153 | 1326 | Standardisation of protocols over reference points between MSC server and Gateway MSC server | - | 3 | Rel-4 | N4 | Mon 25/09/00 | Fri 23/03/01 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
7154 | 1616 | Standardisation of detailed stage 2 description | - | 3 | Rel-4 | N4 | Mon 17/07/00 | Fri 23/03/01 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Mon 12/03/01
7155 | 1327 | Bearer control between MSC server and MGW | - | 3 | Rel-4 | N4 | Fri 01/09/00 | Thu 16/08/01 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
7156 | 1328 | stage 3 - protocol issues | - | 4 | Rel-4 | N4 | Fri 01/09/00 | Thu 16/08/01 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
7157 | 1329 | stage 3 - parameter value issues | - | 4 | Rel-4 | N3 | Tue 02/01/01 | Fri 30/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 30/05/01
7158 | 2052 | Deleted - Conformance Test Aspects - Enable bearer independent CS architecture | CSSPLIT-TEST | 2 | Rel-4 | T1 | Mon 05/03/01 | Fri 01/03/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-15 |  | Mon 09/10/00 | Sat 01/04/00
7159 | 1445 | MExE enhancements Rel-4 | MEXE | 1 | Rel-4 | T2,S3 | Mon 03/01/00 | Fri 14/12/01 | 100% | TP-030052 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Fri 14/09/01
7160 | 1447 | MExE Security Analysis Activity | MEXE-SEC | 2 | Rel-4 | S3,T2 | Tue 22/02/00 | Fri 14/12/01 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | SP#12 updated WID | - |  |  |  |  | Tue 18/04/00 | Sat 06/08/11
7161 | 2045 | Stage 3 for MExE Security | - | 3 | Rel-4 | S3 | Mon 17/07/00 | Fri 14/12/01 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 21.133, 33.102 |  |  |  |  | Mon 09/10/00 | Sat 06/08/11
7162 | 1448 | Terminal aspects for MExE Security | - | 3 | Rel-4 | T2 | Tue 22/02/00 | Fri 15/12/00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 23.057 |  |  |  |  | Sun 09/04/00 | Tue 13/03/01
7163 | 1810 | MExE Rel-4 Improvements and Investigations | MEXE-ENHANC | 2 | Rel-4 | T2 | Mon 03/01/00 | Fri 15/12/00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7164 | 1812 | 3rd MExE classmark | - | 3 | Rel-4 | T2 | Mon 03/01/00 | Fri 15/12/00 | 100% | - | - | Motorola | Mark Cataldo | Additional features for MExE R2000 | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7165 | 1814 | FS on Secure download mechanism and capabilities to support SDR concepts | - | 3 | Rel-4 | T2 | Mon 07/02/00 | Fri 15/12/00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7166 | 1815 | FS on Support of MP3/MPEG4 content | - | 3 | Rel-4 | T2 | Mon 07/02/00 | Fri 15/12/00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7167 | 1631 | Tandem Free aspects for 3G and between 2G and 3G systems | TFO | 1 | Rel-4 | S4 | Tue 22/02/00 | Fri 15/06/01 | 100% | - | - | - | - | RAN and CN to verify no problems for GSM terminals roaming in 3G R99 | - |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
7168 | 1632 | Tandem Free AMR | TFO-AMR | 2 | Rel-4 | S4 | Tue 22/02/00 | Fri 15/06/01 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | - |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
7169 | 130 | Specification of Tandem Free AMR | - | 3 | Rel-4 | S4 | Tue 22/02/00 | Fri 23/03/01 | 100% | - | - | - | - | - | 28.062 |  |  |  |  | Thu 06/04/00 | Tue 20/03/01
7170 | 907 | Impact of Tandem Free AMR on: | - | 3 | Rel-4 | NP | Mon 08/01/01 | Fri 15/06/01 | 100% | - | - | - | - | "Implementation" changed to "Impact on:" by A. Sultan (for better wording) | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
7171 | 131 | CN | - | 4 | Rel-4 | NP | Mon 26/03/01 | Fri 15/06/01 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | - |  |  |  |  | Thu 06/04/00 | Fri 30/03/01
7172 | 132 | GERAN | - | 4 | Rel-4 | GP | Mon 08/01/01 | Fri 06/04/01 | 100% | - | - | - | - | End date Modified from June to March to have it in Rel4 | - |  |  |  |  | Thu 06/04/00 | Thu 28/02/02
7173 | 2230 | Advanced Speech Call Items enhancements_Rel-4 | ASCI4 | 1 | Rel-4 | N1 | Sun 03/12/00 | Thu 14/03/02 | 100% | NP-000730 | - | Nortel | sonia.garapaty@nortelnetworks.com | Approved at CN#10. Acronym changed from ASCI, Rel-4 | - |  |  |  |  | Mon 11/12/00 | Tue 24/03/15
7174 | 2232 | Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI) | - | 2 | Rel-4 | N4 | Sun 03/12/00 | Thu 14/03/02 | 100% | - | - | Sagem | Vivien Perlic | CN4#11 30/11/02: no inputs received in CN4 | 23.067, 24.067 |  |  |  |  | Mon 11/12/00 | Wed 12/12/01
7175 | 2231 | Stages 2 and 3 on A interface | - | 2 | Rel-4 | N1 | Sun 03/12/00 | Fri 23/03/01 | 100% | - | - | Nortel | sonia.garapaty@nortelnetworks.com | - | 44.068, 44.069, 24.008 |  |  |  |  | Mon 11/12/00 | Wed 30/05/01
7176 | 2403 | 700 MHz spectrum support | 700SS | 1 | Rel-4 | GP | Mon 03/01/00 | Fri 20/12/02 | 100% | GP-000449 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
7177 | 2404 | GERAN support for the 700 MHz band | - | 2 | Rel-4 | GP | Mon 03/01/00 | Fri 19/01/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7178 | 2405 | Signalling support | - | 3 | Rel-4 | GP | Mon 03/01/00 | Fri 19/01/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7179 | 2406 | Physical layer definitions - for GERAN support for the 700 MHz band | - | 3 | Rel-4 | GP | Mon 03/01/00 | Fri 19/01/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7180 | 2407 | Receiver performance and RF budget | - | 3 | Rel-4 | GP | Mon 03/01/00 | Fri 19/01/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
7181 | 2408 | GERAN MS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | Mon 02/04/01 | Fri 30/11/01 | 100% | GP-000451 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
7182 | 2410 | GERAN BTS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | Mon 02/04/01 | Fri 20/12/02 | 100% | GP-000452 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
7183 | 2463 | Operator Determined Barring for Packet Oriented Services | ODB | 1 | Rel-4 | NP | Thu 01/06/00 | Mon 19/03/01 | 100% | NP-010089 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Completed WI missing from the P-plan Added for tracking | - |  |  |  |  | Tue 20/03/01 | Tue 20/03/01
7184 | 2546 | UMTS QoS Architecture for PS Domain | QoSPS | 1 | Rel-4 | S2,S5,R3,GP | Mon 03/01/00 | Wed 27/11/02 | 100% | SP-010342 | - | Ericsson | Ina.widegren@era.ericsson.se | - | - |  |  |  |  | Fri 08/06/01 | Thu 24/01/02
7185 | 2548 | Architecture | - | 2 | Rel-4 | S2 | Mon 05/06/00 | Wed 03/01/01 | 100% | - | - | - | - | - | 23.107 |  |  |  |  | Fri 08/06/01 | Thu 24/01/02
7186 | 2550 | Charging and OAM&P for QoS Management | QoSPS-OAM | 2 | Rel-4 | S5 | Fri 21/09/01 | Fri 28/06/02 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Fri 08/06/01 | Fri 21/06/02
7187 | 1681 | RAB Quality of Service (re)Negotiation over Iu | QoSPS-MAPEND-RABQoS | 2 | Rel-4 | R3 | Mon 21/08/00 | Fri 23/03/01 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | 25.413 |  |  |  |  | Wed 26/07/00 | Fri 16/02/01
7188 | 1991 | RAB Quality of Service Negotiation over Iu | QoSPS-MAPEND-RABQoS-Negot | 3 | Rel-4 | R3 | Mon 21/08/00 | Fri 23/03/01 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
7189 | 2456 | RAB Quality of Service Negotiation over Iu during relocation | QoSPS-MAPEND-RABQoS-NegotReloc | 3 | Rel-4 | R3 | Fri 02/03/01 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 09/03/01 | Mon 12/03/01
7190 | 1992 | RAB Quality of Service Re-Negotiation over Iu | QoSPS-MAPEND-RABQoS-ReNegot | 3 | Rel-4 | R3 | Mon 25/09/00 | Fri 23/03/01 | 100% | - | - | Motorola | S. Irwin | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
7191 | 1553 | GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms | GERQoS | 2 | Rel-4 | GP | Mon 03/01/00 | Fri 30/11/01 | 100% | GP-010431 | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7192 | 2306 | Handover Concept for the PS domain | - | 3 | Rel-4 | GP | Mon 03/01/00 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
7193 | 2309 | Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | GP | Mon 03/01/00 | Wed 19/01/00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/02/01 | Thu 24/01/02
7194 | 2307 | Update of stage 2 | - | 4 | Rel-4 | GP | Mon 03/01/00 | Tue 13/02/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 24/01/02
7195 | 2308 | Update of relevant stage 3 specs -> RRC | - | 4 | Rel-4 | G2 | Mon 03/01/00 | Fri 30/11/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
7196 | 50010 | Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover | GERQoS-Mstest | 2 | Rel-4 | G4,R3 | Fri 31/08/01 | Wed 27/11/02 | 100% | GP-012287 | - | - | - | Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
7197 | 50011 | Deleted - Handover for the PS domain | - | 3 | Rel-4 | G4,R3 | Fri 31/08/01 | Wed 27/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
7198 | 50012 | Deleted - Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | G4,R3 | Fri 31/08/01 | Wed 27/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
7199 | 50013 | Deleted - Update of stage 2 | - | 4 | Rel-4 | G4,R3 | Fri 31/08/01 | Wed 27/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
7200 | 50014 | Deleted - Update of relevant stage 3 specs | - | 4 | Rel-4 | G4,R3 | Fri 31/08/01 | Wed 27/11/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
7201 | 1685 | PS-domain handover for real-time services | QoSPS-PSdoRTS | 2 | Rel-4 | R3 | Mon 28/08/00 | Fri 30/03/01 | 100% | - | - | Nokia | atte.lansisalmi@nokia.com | - | - |  |  |  |  | Wed 19/04/00 | Mon 12/03/01
7202 | 2554 | Deleted - RAB QoS Renegotiation at Relocation | - | 2 | Rel-4 | R3 | Wed 03/01/01 | Fri 23/03/01 | 100% | - | - | - | - | Marked as stopped 12/2008 | 25.851, 25.946 |  |  | RP-11 |  | Fri 08/06/01 | Fri 12/12/08
7203 | 1993 | (Small) Technical Enhancements and Improvements for Rel-4 | TEI4 | 1 | Rel-4 | SP,CP,RP,GP | Mon 03/01/00 | Mon 03/01/00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system | - |  |  |  |  | Tue 26/09/00 | Sat 01/04/00
7204 | 25017 | Test - (Small) Technical Enhancements and Improvements for Rel-4 | TEI4_Test | 1 | Rel-4 | R5,T1 | Mon 03/01/00 | Fri 30/03/01 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP | - |  |  |  |  | Tue 21/03/06 | Tue 06/05/08
7205 | 400002 | Rel-4 Evolutions of the transport in the UTRAN | ETRAN | 1 | Rel-4 | RP | Mon 21/08/00 | Fri 23/08/02 | 100% | - | - | Alcatel | Francois Courau | - | - |  |  |  |  | Fri 31/03/00 | Fri 17/11/00
7206 | 12 | QoS optimization for AAL2 connections over Iub and Iur interfaces | ETRAN-QoSAAL2 | 2 | Rel-4 | R3 | Mon 21/08/00 | Fri 30/03/01 | 100% | - | - | Japan Telecom | T. Yoshimura | - | - |  |  |  |  | Fri 31/03/00 | Tue 20/03/01
7207 | 1995 | Transport bearer modification procedure on Iub, Iur, and Iu | ETRAN-MigrMod | 2 | Rel-4 | R3 | Mon 02/10/00 | Fri 30/03/01 | 100% | - | - | Japan Telecom | T. Yoshimura | - | - |  |  |  |  | Tue 26/09/00 | Tue 20/03/01
7208 | 401834 | Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN | - | 2 | Rel-4 | T1 | Mon 25/02/02 | Fri 23/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 14/09/00 | Tue 13/10/09
7209 | 2208 | Deleted - Testing RAB support enhancements | CT-RABS? | 3 | Rel-4 | T1 | Mon 25/02/02 | Fri 23/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3 |  |  | TP-17 |  | Thu 16/11/00 | Tue 13/10/09
7210 | 400004 | Rel-4 Evolutions of the transport in the CN | CNTRSP | 1 | Rel-4 | N4,N1,N2,S2 | Mon 29/05/00 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Tue 20/03/01
7211 | 859 | IP Transport of CN protocols (e.g. CAP, MAP) | SS7IP | 2 | Rel-4 | N4 | Thu 07/12/00 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Tue 20/03/01
7212 | 1679 | Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP) | - | 3 | Rel-4 | N4 | Thu 07/12/00 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 25/08/00 | Tue 13/03/01
7213 | 2018 | CAP | - | 4 | Rel-4 | N2 | Thu 07/12/00 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 25/08/00 | Tue 13/03/01
7214 | 2019 | MAP | - | 4 | Rel-4 | N4 | Thu 07/12/00 | Fri 23/03/01 | 100% | - | - | - | - | - | 29.202 |  |  |  |  | Fri 25/08/00 | Mon 12/03/01
7215 | 2253 | BSSAP+ | SS7IP-BSSAP+ | 4 | Rel-4 | N1 | Mon 15/01/01 | Wed 14/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/02/01 | Mon 12/03/01
7216 | 1513 | FS on Transport and control separation in the PS CN domain | - | 2 | Rel-4 | S2 | Mon 29/05/00 | Fri 23/03/01 | 100% | SP-000293 | - | Ericsson | Juan-Antonio.Ibanez@eed.ericsson.se | - | - |  |  |  |  | Fri 28/07/00 | Wed 19/09/01
7217 | 1615 | Architectural impacts | - | 3 | Rel-4 | S2 | Mon 29/05/00 | Fri 23/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Thu 08/02/01
7218 | 401216 | Rel-4 Improvements of Radio Interface | - | 1 | Rel-4 | RP | Mon 10/07/00 | Fri 14/03/03 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 11/10/01
7219 | 1509 | UTRA repeater specification (master) | RInImp-REP | 2 | Rel-4 | R4 | Mon 10/07/00 | Wed 21/03/01 | 100% | - | - | Mikom, Allgon | T. Kummetz, Mikom; Alf Ahlström, Allgon | - | - |  |  |  |  | Wed 26/07/00 | Fri 30/03/01
7220 | 1994 | DSCH power control improvement in soft handover | RInImp-DSCHsho | 2 | Rel-4 | R1 | Mon 11/09/00 | Fri 23/03/01 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
7221 | 1996 | UMTS 1800 | RInImp-UMTS18 | 2 | Rel-4 | R4 | Mon 25/09/00 | Fri 14/12/01 | 100% | - | - | Motorola | Howard Benn | - | - |  |  |  |  | Tue 26/09/00 | Thu 29/11/01
7222 | 2467 | UMTS 1900 | RInImp-UMTS19 | 2 | Rel-4 | R4 | Mon 19/03/01 | Fri 14/12/01 | 100% | - | - | Motorola | Howard Benn | - | 25.101 |  |  |  |  | Mon 19/03/01 | Thu 09/07/09
7223 | 1219 | FS on High Speed downlink packet access | RInImp-HSDPA | 2 | Rel-4 | R2 | Mon 21/08/00 | Fri 23/03/01 | 100% | - | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
7224 | 1510 | Deleted - FS on improved common DL channel for Cell-FACH state | RInImp-DLCFACH | 2 | Rel-4 | R2 | Mon 11/09/00 | Fri 28/12/01 | 100% | - | - | GBT | J. Kwak | Stopped at RP#14 | - |  |  | RP-14 |  | Wed 26/04/00 | Tue 13/10/09
7225 | 401839 | Conformance Test Spec. Rel-4 improvements in Radio Interface | - | 2 | Rel-4 | T1 | Mon 08/10/01 | Fri 14/03/03 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Thu 11/10/01
7226 | 2212 | Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type | - | 3 | Rel-4 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
7227 | 2213 | Deleted - Testing Terminal Power saving features | - | 3 | Rel-4 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
7228 | 2214 | Deleted - Testing DSCH power control improvement in soft handover | - | 3 | Rel-4 | T1 | Mon 18/02/02 | Fri 30/08/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
7229 | 2215 | Testing UMTS 1800 | - | 3 | Rel-4 | T1 | Mon 08/10/01 | Fri 14/06/02 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1 |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
7230 | 41000 | Testing UMTS 1900 | - | 3 | Rel-4 | T1 | Mon 08/10/01 | Fri 14/06/02 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1 |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
7231 | 2561 | Testing UMTS 1800 - TTCN | - | 3 | Rel-4 | T1 | Mon 17/06/02 | Fri 14/03/03 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
7232 | 41001 | Testing UMTS 1900 - TTCN | - | 3 | Rel-4 | T1 | Mon 17/06/02 | Fri 14/03/03 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
7233 | 400009 | Rel-4 RAN improvements | - | 1 | Rel-4 | RP | Mon 14/08/00 | Wed 17/03/04 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Fri 17/11/00
7234 | 655 | Node B synchronization for TDD | RANimp-NBsync | 2 | Rel-4 | R1 | Mon 14/08/00 | Fri 23/03/01 | 100% | - | - | Siemens | S. Oestreich | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
7235 | 2206 | RAB support enhancement for Rel-4 | RANimp-RABSE | 2 | Rel-4 | R2 | Mon 21/08/00 | Fri 23/03/01 | 100% | - | - | Ericsson | M. Israelsson, A. Krishnarajah | 29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2 | - |  |  |  |  | Mon 04/12/00 | Thu 28/02/02
7236 | 402102 | Deleted - Conformance Test Aspects - Rel-4 RAN Improvements | - | 2 | Rel-4 | T1 | Tue 01/01/02 | Wed 17/03/04 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-23 |  | Wed 01/11/00 | Sat 01/04/00
7237 | 402222 | Deleted - Testing Radio access bearer support enhancments | - | 3 | Rel-4 | T1 | Tue 01/01/02 | Mon 02/09/02 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Tue 09/04/02
7238 | 402461 | Deleted - Testing RAB support enhancements-Robust Header Compression | RABimp-RoCH | 3 | Rel-4 | T1 | Tue 28/05/02 | Wed 03/09/03 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-1, -2 |  |  | TP-21 |  | Tue 20/03/01 | Fri 14/03/03
7239 | 41006 | Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN | - | 3 | Rel-4 | T1 | Tue 28/05/02 | Wed 17/03/04 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-3 |  |  | TP-23 |  | Thu 26/09/02 | Fri 14/03/03
7240 | 41007 | Testing of Extended Robut Header Compression | Ext-RoHC | 3 | Rel-4 | T1 | Wed 18/09/02 | Tue 30/09/03 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 15% complete) | 34.123-1, -2 |  |  |  |  | Thu 26/09/02 | Fri 14/03/03
7241 | 41008 | Deleted - Testing of Extended Robut Header Compression - TTCN | - | 3 | Rel-4 | T1 | Wed 18/09/02 | Tue 16/12/03 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3 |  |  | TP-22 |  | Thu 26/09/02 | Fri 14/03/03
7242 | 41009 | Deleted - General changes to TS34.121 corresponding to release 4 | RANimp-test,TEI4 | 3 | Rel-4 | T1 | Mon 03/03/03 | Wed 03/03/04 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121 |  |  | TP-23 |  | Fri 14/03/03 | Fri 14/03/03
7243 | 401652 | Rel-4 Emergency call enhancements | EMC1-CS | 1 | Rel-4 | N1,S1,T1 | Mon 03/01/00 | Tue 28/05/02 | 100% | - | - | Ericsson | - | Acronym changed from EMC1, EMC1-CS | - |  |  |  |  | Tue 08/08/00 | Tue 24/03/15
7244 | 1654 | For CS based calls | EMC1-CS | 2 | Rel-4 | N1 | Mon 03/01/00 | Tue 28/05/02 | 100% | NP-010136 | - | Ericsson | - | WI approved in TSG_10 | - |  |  |  |  | Tue 08/08/00 | Wed 30/05/01
7245 | 1320 | Distinction in CS domain of emergency call types to different emergency services | - | 3 | Rel-4 | S1 | Mon 01/05/00 | Fri 23/06/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Mon 21/07/08
7246 | 1999 | Distinction in CS domain of emergency calls to different emergency types | - | 3 | Rel-4 | N1 | Thu 24/08/00 | Fri 22/09/00 | 100% | NP-010136 | - | - | - | Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres. | 24.008 |  |  |  |  | Sat 23/09/00 | Mon 21/07/08
7247 | 402224 | Deleted - Conformance Test Aspects - Emergency call enhancements | - | 3 | Rel-4 | T1 | Mon 03/01/00 | Fri 28/07/00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | TP-08 |  | Thu 16/11/00 | Fri 12/12/08
7248 | 2226 | Testing CS based emergency calls | - | 3 | Rel-4 | T1 | Mon 25/02/02 | Tue 28/05/02 | 100% | TP-030052 | - | - | - | - | 34.123-1 |  |  |  |  | Tue 28/11/00 | Mon 13/01/03
7249 | 2563 | Testing CS based emergency calls - TTCN | - | 3 | Rel-4 | T1 | Thu 22/11/01 | Tue 28/05/02 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
7250 | 401826 | Rel-4 Terminal interfaces | TI | 1 | Rel-4 | T2 | Mon 03/01/00 | Thu 15/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7251 | 1827 | AT commands enhancements | TI-ATC | 2 | Rel-4 | T2 | Mon 03/01/00 | Wed 14/03/01 | 100% | - | - | - | - | - | 27.007 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
7252 | 1828 | Specification of AT commands for new services | - | 3 | Rel-4 | T2 | Mon 03/01/00 | Wed 14/03/01 | 100% | - | - | - | - | goal not completely achieved because of missing input | 27.007 |  |  |  |  | Thu 14/09/00 | Tue 20/03/01
7253 | 1829 | Wide Area Data Synchronization | TI-WADS | 2 | Rel-4 | T2 | Mon 03/01/00 | Wed 14/03/01 | 100% | - | - | - | - | AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added | - |  |  |  |  | Thu 14/09/00 | Tue 19/12/00
7254 | 1830 | Continues evolution of Synchronization protocol | TI-SYNC-EVOL | 3 | Rel-4 | T2 | Mon 03/01/00 | Wed 14/03/01 | 100% | - | - | - | - | - | 27.903, 27.103 |  |  |  |  | Thu 14/09/00 | Tue 20/03/01
7255 | 1832 | Terminal local model | TLM | 2 | Rel-4 | T2 | Tue 16/05/00 | Thu 15/03/01 | 100% | TP-000080 | - | Ericsson | Olga.Tome@ECS.ERICSSON.SE | - | 23.227 |  |  |  |  | Thu 14/09/00 | Fri 14/09/01
7256 | 401536 | Rel-4 Location Services enhancements | LCS4 | 1 | Rel-4 | S2,S1,T2,N1,N4,R3,R2 | Mon 03/04/00 | Fri 28/12/01 | 100% | SP-010518 | - | Nokia | Jan Kall | Acronym changed form LCS1 | - |  |  |  |  | Fri 28/07/00 | Tue 24/03/15
7257 | 2229 | CBS interactions | LCS4-CBS | 2 | Rel-4 | T2 | Mon 03/04/00 | Fri 28/12/01 | 100% | - | - | - | - | - | 23.041 |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
7258 | 523 | LCS support in the CS domain | LCS4-CS | 2 | Rel-4 | S2 | Mon 15/05/00 | Fri 19/01/01 | 100% | - | - | - | - | Only MAP impact foreseen so far. To be further split if needed. | - |  |  |  |  | Wed 19/04/00 | Tue 24/03/15
7259 | 525 | LCS support in the PS domain | LCS4-PS | 2 | Rel-4 | S2,S1,N1,N4 | Mon 01/05/00 | Fri 28/12/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Tue 24/03/15
7260 | 1642 | Stage 1 for LCS support in the PS domain | - | 3 | Rel-4 | S1 | Mon 03/07/00 | Fri 25/08/00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established | 22.071 |  |  |  |  | Tue 08/08/00 | Sat 01/04/00
7261 | 1181 | Stage 2 for LCS support in the PS domain | - | 3 | Rel-4 | S2,R2,G1 | Mon 01/05/00 | Fri 19/01/01 | 100% | - | - | - | - | SP#10 completed | 25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part) |  |  |  |  | Wed 19/04/00 | Wed 13/12/00
7262 | 1180 | Stage 3 for LCS support in the PS domain | - | 3 | Rel-4 | N1,N4 | Mon 21/08/00 | Fri 28/12/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Wed 10/10/01
7263 | 526 | Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS) | - | 4 | Rel-4 | N1 | Mon 21/08/00 | Fri 28/12/01 | 100% | - | - | Nokia | Janne Muhonen | - | - |  |  |  |  | Wed 19/04/00 | Mon 25/03/02
7264 | 2462 | MAP impacts of LCS | - | 4 | Rel-4 | N4 | Mon 21/08/00 | Fri 30/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 20/03/01 | Tue 20/03/01
7265 | 527 | GTP signalling for LCS | - | 4 | Rel-4 | N4 | Mon 21/08/00 | Fri 30/03/01 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Mon 12/03/01
7266 | 401600 | UE positioning Rel-4 | LCS1-UEpos | 2 | Rel-4 | R3,R2 | Mon 03/04/00 | Fri 30/03/01 | 100% | RP-000509 | RP-010045 | - | - | - | - |  |  |  |  | Wed 26/07/00 | Tue 09/04/02
7267 | 1601 | Iub/Iur interfaces for methods Rel 99 | LCS1-UEpos-IubIur | 3 | Rel-4 | R3 | Mon 03/04/00 | Fri 30/03/01 | 100% | RP-000509 | RP-010045 | Ericsson | Yun-Chao Hu | - | 25.401, 25.420, 25.423, 25.430, 25.433, new 25.850 |  |  |  |  | Wed 26/07/00 | Tue 20/03/01
7268 | 1602 | UE positioning enhancements - IPDL for TDD | LCS1-UEpos-enh | 3 | Rel-4 | R2 | Mon 28/08/00 | Fri 23/03/01 | 100% | RP-000509 | RP-010045 | Siemens | Armin Sitte | 5 Mar 2001: split of IPDL for TDD agreed by R2 | new 25.847 |  |  |  |  | Wed 26/07/00 | Tue 22/05/12
7269 | 401560 | Rel-4 UICC/(U)SIM enhancements and interworking | UICC1 | 1 | Rel-4 | T3 | Mon 24/07/00 | Fri 23/03/01 | 100% | - | - | - | - | Acronym changed from UICC1, Rel-4 | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
7270 | 1799 | Common PCN Handset Specification (CPHS) | UICC1-CPHS | 2 | Rel-4 | T3 | Mon 24/07/00 | Fri 23/03/01 | 100% | TP-000116 | - | One2One | - | 28/5/2001: CRs approved at TP-11. WI complete. | 27.103 |  |  |  |  | Thu 14/09/00 | Mon 28/05/01
7271 | 401800 | Rel-4 (U)SIM toolkit enhancements | USAT4 | 1 | Rel-4 | T3,S1 | Mon 05/06/00 | Fri 23/03/01 | 100% | - | - | Gemplus | Jean-Francois Rubon | Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM | 23.048 (USAT1SM), 43.019 (USAT1APIJAVA) |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
7272 | 2034 | USAT local link | USAT1-LocLnk | 2 | Rel-4 | T3,S1 | Mon 05/06/00 | Fri 23/03/01 | 100% | TP-000116 | - | Gemplus | Jean-Francois Rubon | 25/5/2001:CR was approved at TP-11. WI is complete | 22.038, 31.111 |  |  |  |  | Wed 27/09/00 | Mon 28/05/01
7273 | 401571 | Rel-4 Security enhancements | SEC4 | 1 | Rel-4 | S3,N4,N1 | Mon 03/01/00 | Fri 15/03/02 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | acronym changed from SEC1 | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
7274 | 1331 | Rel-4 Lawful Interception | SEC4-LI | 2 | Rel-4 | S3 | Mon 21/08/00 | Fri 23/03/01 | 100% | - | - | - | - | Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI | 33.107 |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
7275 | 1587 | Evolution of GSM CS algorithms (e.g. A5/3 development and deployment) | SEC1-CSALGO1 | 2 | Rel-4 | S3 | Mon 03/01/00 | Mon 15/01/01 | 100% | SP-000306 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105 |  |  |  |  | Sun 09/04/00 | Tue 17/11/09
7276 | 1588 | Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | SEC1-PSALGO1 | 2 | Rel-4 | S3,N4,N1 | Tue 22/02/00 | Fri 22/12/00 | 100% | SP-000307 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105 |  |  |  |  | Sun 09/04/00 | Tue 17/11/09
7277 | 1589 | Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | - | 3 | Rel-4 | S3 | Tue 22/02/00 | Fri 24/11/00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED | - |  |  | SP-69 |  | Sun 09/04/00 | Sat 06/08/11
7278 | 1618 | Impact on GTP | - | 3 | Rel-4 | N4 | Mon 20/03/00 | Fri 22/12/00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | - | - |  |  |  |  | Tue 08/08/00 | Wed 13/12/00
7279 | 1661 | GEA capability indication in MS CM | SEC1-PSALGO1-GEACAP | 3 | Rel-4 | N1 | Mon 19/06/00 | Fri 22/12/00 | 100% | - | - | Vodafone Airtouch | Duncan Mills | - | - |  |  |  |  | Tue 08/08/00 | Wed 15/11/00
7280 | 401583 | Deleted - MAP application layer security | SEC1-MAPAL | 2 | Rel-4 | S3 | Mon 03/01/00 | Fri 15/03/02 | 100% | - | - | - | - | REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008 | - |  |  | SP-15 |  | Sun 09/04/00 | Tue 17/11/09
7281 | 401584 | Deleted - Main aspects of MAP application layer security | - | 3 | Rel-4 | S3 | Mon 21/02/00 | Thu 29/03/01 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | SP-11 |  | Sun 09/04/00 | Tue 09/04/02
7282 | 402025 | Deleted - Other stage 3 aspects | - | 3 | Rel-4 | N4 | Tue 22/02/00 | Fri 24/11/00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | CP-10 |  | Sun 09/04/00 | Tue 09/04/02
7283 | 401594 | Deleted - Visibility and Configurability of security | SEC1-VCS | 3 | Rel-4 | S3 | Mon 03/01/00 | Fri 15/03/02 | 100% | SP-000305 | - | France Telecom | Sebastien.nguyenngoc@rd.francetelecom.com | CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008 | - |  |  | SP-15 |  | Sun 09/04/00 | Tue 17/11/09
7284 | 401142 | Rel-4 Charging and OAM&P | OAM4 | 1 | Rel-4 | S5 | Fri 01/12/00 | Fri 05/10/01 | 100% | SP-010461 | - | - | - | SP#13 approved WID | - |  |  |  |  | Wed 26/04/00 | Thu 24/01/02
7285 | 2089 | Rel-4 Principles, high level Requirements and Architecture | - | 2 | Rel-4 | S5 | Fri 01/12/00 | Thu 21/06/01 | 100% | SP-010461 | - | Motorola, Telia | Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE | - | 32.101, 32.102 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7286 | 2088 | Rel-4 Performance Management | - | 2 | Rel-4 | S5 | Fri 01/12/00 | Fri 28/09/01 | 100% | SP-010238 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.4xy, 52.402 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7287 | 2081 | Fault Management | - | 2 | Rel-4 | S5 | Fri 01/12/00 | Fri 05/10/01 | 100% | SP-000524 | - | Lucent | - | - | 32.111-1/4 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7288 | 2082 | Configuration Management | - | 2 | Rel-4 | S5 | Fri 01/12/00 | Thu 21/06/01 | 100% | SP-000524 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.106-1/8 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
7289 | 2083 | Rel-4 Charging Management | - | 2 | Rel-4 | S5 | Fri 01/12/00 | Fri 28/09/01 | 100% | SP-000524 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.200, 32.205, 32.215, 32.235 |  |  |  |  | Wed 26/04/00 | Tue 07/07/09
7290 | 2071 | UTRAN Operations and Maintenance procedures | UOAM | 2 | Rel-4 | S5 | Fri 01/12/00 | Thu 21/06/01 | 100% | SP-000524 | - | Mannesmann Mobilfunk | bert.boden@d2mannesmann.de | - | 32.8 |  |  |  |  | Mon 09/10/00 | Mon 13/01/03
7291 | 1517 | Global Text Telephony | GTT | 1 | Rel-4 | S1,S2,S4,T1,R5 | Mon 03/01/00 | Mon 19/03/01 | 100% | SP-010340 | - | Ericsson | gunnar.hellstrom@omnitor.se | SP#12 updated WID SP-000162=>SP-010340 | - |  |  |  |  | Fri 28/07/00 | Wed 14/10/09
7292 | 1634 | Stage 1 for Global Text Telephony | - | 2 | Rel-4 | S1 | Wed 05/04/00 | Fri 22/12/00 | 100% | SP-010340 | - | - | - | - | 22.226 |  |  |  |  | Tue 08/08/00 | Wed 09/05/12
7293 | 1519 | Stage 2 for Global Text Telephony | - | 2 | Rel-4 | S2 | Mon 03/01/00 | Fri 13/10/00 | 100% | SP-010340 | - | - | - | - | 23.226 |  |  |  |  | Fri 28/07/00 | Thu 24/01/02
7294 | 2234 | Specification of Cellular Text telephone Modem | GTT-CTM | 2 | Rel-4 | S4 | Mon 11/09/00 | Mon 19/03/01 | 100% | SP-010340 | - | - | - | - | - |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
7295 | 2238 | General description and C-code | - | 3 | Rel-4 | S4 | Mon 11/09/00 | Mon 11/12/00 | 100% | - | - | - | - | - | 26.226, 26.230 |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
7296 | 2237 | Minimum Performance requirements | - | 3 | Rel-4 | S4 | Mon 11/09/00 | Mon 19/03/01 | 100% | - | - | - | - | - | 26.231 |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
7297 | 1852 | Deleted - Conformance Test Aspects - Global Text Telephony | GTT_Test | 2 | Rel-4 | R5,T1 | Thu 21/09/00 | Thu 21/09/00 | 100% | - | - | - | - | RP#45 work item abandoned/closed (it was never really started) | - |  |  | RP-45 | PCG-23 | Thu 14/09/00 | Tue 15/09/09
7298 | 0 | --- RELEASE 99 --- | - | 1 | R99 | NP,SP,TP,SMG | Mon 03/01/00 | Fri 29/12/00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
7299 | 60150 | UMTS Features | - | 1 | R99 | S1,S2,S4,SMG,N3,N4,RP | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
7300 | 60102 | UMTS_SERVICES | UMTS_SERVICES | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7301 | 60103 | UMTS phase 1 | UMTS1 | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.1 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7302 | 60119 | UMTS Capabilities | UMTS_Capabil | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7303 | 60164 | Architecture of the GSM-UMTS platform | - | 2 | R99 | S2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface” | 23.002, 23.008, 23.060, 23.101, 23.110 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7304 | 60165 | UMTS Terrestrial Radio Access Network | UTRAN | 2 | R99 | RP | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224, |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7305 | 60083 | UMTS 1800, UMTS 1900 | Rlnlmp19,Rlnlmp18 | 2 | R99 | R2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 25.307 CR#0002, 0003 Inclusion of release independent RF related information |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
7306 | 60149 | Mandatory speech codec for narrowband telephony service | Mandatory_Speech_Codec,AMR-NB,AMR | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99060 | - | - | - | Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec. | 04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
7307 | 60055 | Codec for low bitrate multimedia telephony service | Low_bit_rate_codec_for_MM_Tel.,H.324M | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99060 | - | - | - | - | 26.104, 26.110, 26.111, 26.911, 26.912, 26.915 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
7308 | 60109 | 3G Audio-Visual Terminal characteristics | WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99129 | - | - | - | - | 26.131, 26.132 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
7309 | 60104 | Updates_for_UMTS | Updates_for_UMTS | 2 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 24.022, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7310 | 60124 | UMTS | UMTS | 2 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 27.060, 29.061 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7311 | 60151 | UMTS and GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7312 | 60147 | Multimedia Messaging Service | MMS | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols. | 22.140, 23.040, 23.140 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7313 | 60121 | Location Services | LCS | 2 | R99 | S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99327 | - | - | - | LCS provide ability to localize a terminal | 02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010 |  |  |  |  | Thu 16/07/09 | Sat 06/08/11
7314 | 60118 | Customised Application for Mobile network Enhanced Logic Phase 3 | CAMEL3 | 2 | R99 | S1,S2,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99368 | - | - | - | CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN. | 22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7315 | 60218 | Global view | - | 3 | R99 | S1,S2,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.078, 23.078, 29.078 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7316 | 60318 | Multiple Subscriber Profile (MSP) based on CAMEL phase 3 | - | 3 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls. | 22.097 (Advanced Addressing) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7317 | 60038 | Short Message Service enhancements / Enhanced Messaging Service (EMS) | EMS | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS. | 23.038, 23.039, 23.040, 23.042 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7318 | 60122 | Mobile Station Execution Environment | MExE | 2 | R99 | S1,SMG1,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based. | 02.57, 22.057, 22.101, 23.057 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7319 | 60123 | MS_Classmark | MS_Classmark | 2 | R99 | N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. | 24.008 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
7320 | 60057 | MultiCall | Multicall | 2 | R99 | S1,N1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | NP-000348 | - | - | - | Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time. | 22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7321 | 60058 | Stage 1 for Multicall | - | 3 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.030, 22.083, 22.087 |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
7322 | 60105 | Virtual Home Environment | VHE | 2 | R99 | S1,SMG1,S2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. | 02.01, 22.105, 22.121,23.127 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7323 | 60067 | Open Service Access | OSA | 2 | R99 | S1,S2,N5 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community. | 22.121, 23.127, 29.198, 29.998 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7324 | 60091 | Super Charger mechanism for signalling traffic associated with mobility | Super_Charger | 2 | R99 | N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and | 21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7325 | 60039 | Follow_Me service | Follow_Me | 2 | R99 | S1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD | 21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7326 | 60093 | Wide area network Synchronization and object exchange | SYNC | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. | 27.103, 27.903 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7327 | 60145 | R99 Terminal Interfaces | - | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7328 | 60166 | AT commands for 3GPP | - | 3 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services. | 27.005, 27.007 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7329 | 60167 | Physical interfaces | - | 3 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements | 27.901 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7330 | 60168 | Multiplexer | MUXMS-TE | 3 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it. | 27.01 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7331 | 60169 | Bearer Services | - | 2 | R99 | S1,T2,N1,N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7332 | 60012 | Circuit Switched Bearer Services | Circuit_switched_Bearer_Services | 3 | R99 | S1,N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002, 23.910, 27.001, 29.007 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7333 | 60021 | Stage 1 for Circuit Switched Bearer Services | CS_Bearerss_in_UMTS | 4 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
7334 | 60019 | CS_Bearers | CS_Bearers | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7335 | 60020 | CS_Bearerss | CS_Bearerss | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 04.21, 23.910, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7336 | 60022 | CS_Data | CS_Data | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 27.001, 27.002, 27.003, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7337 | 60023 | CS_Data_Bearers | CS_Data_Bearers | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.910, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7338 | 60024 | Deleted - CN3 poart of Circuit Switched Bearer Services | CSBS | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.910, 27.001, 29.007 |  |  | NP-06 |  | Thu 30/07/09 | Tue 09/02/10
7339 | 60040 | Frame Tunnelling Mode | FTM | 3 | R99 | T2,N1,N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | NP-99285 | - | - | - | FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side. | 22.002, 27.001, 27.007, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7340 | 60171 | Access to ISPs and Intranets – Wireless/Remote access to LANs | InterworkingwithPDN(DHCP) | 3 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | N3-99069 | - | - | - | Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. | 29.061 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7341 | 60070 | PHS Internet Access Forum Specification | PIAFS | 3 | R99 | S1,N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | NP-99285 | - | - | - | PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter). | 22.002, 27.001, 27.007, 29.007 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7342 | 60170 | Personal Handyphone System Internet Access Forum Standard (PIAFS) | - | 4 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf | 22.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7343 | 60092 | Support_of_PIAFS_in_UMTS | Support_of_PIAFS_in_UMTS | 4 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 27.001, 27.007, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7344 | 60172 | Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM) | UICC,USIM | 2 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99084 | - | - | - | For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102) | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7345 | 60173 | UICC / Terminal interface; Physical and logical characteristics | UICC | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99084 | - | - | - | Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator. | 31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7346 | 60142 | UICC/(U)SIM enhancements and interworking | UICC99 | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Acronym changed from UICC1 | 31.102, 31.900 |  |  |  |  | Wed 08/07/09 | Tue 24/03/15
7347 | 60174 | Characteristics of the USIM application | USIM | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99084 | - | - | - | Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist | 31.102 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7348 | 60114 | UICC Application Identifiers | AID,Application_Identifiers | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99184 | - | - | - | Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5). | 21.111, 31.110 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7349 | 60139 | SIM Application Toolkit | SAT | 3 | R99 | S1,T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 11.14, 22.030, 22.100, 22.101 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7350 | 60141 | USIM Application Toolkit | USAT | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99184 | - | - | - | Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101. | 31.111 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7351 | 60175 | Bearer Independent Protocol for SAT applications to exchange data over the GSM network | BIP | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD) | 03.48, 11.10, 11.14 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7352 | 60176 | Administrative commands and functions for IC cards | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000. | ETSI 102 222 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7353 | 60177 | USIM and UICC requirements | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99084 | - | - | - | High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services | 21.111 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7354 | 60140 | SIM_API | SIM_API | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 3.19 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7355 | 60086 | SIM_toolkit_API | SIM_toolkit | 3 | R99 | SMG9,T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 03.48, 11.11, 11.14 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7356 | 60087 | Deleted - 1.8 Volt SIM ME interface | SMIME_1.8V | 3 | R99 | SMG9 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 11.18 |  |  | TP-06 |  | Thu 30/07/09 | Tue 09/02/10
7357 | 60178 | USIM/UICC Testing | - | 2 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7358 | 60179 | Terminal tests for the UICC Interface | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99184 | - | - | - | Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121 | 31.12 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7359 | 60180 | USIM application test specification | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-99184 | - | - | - | Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface. | 31.121 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7360 | 60181 | USIM conformance test specification | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102. | 31.122 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7361 | 60182 | SIM toolkit test specification | - | 3 | R99 | T3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests. | 11.10-4 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7362 | 60137 | Security for UMTS and GSM Features | Security | 2 | R99 | S3,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7363 | 60183 | Fraud Information Gathering Service (for connection-orientated services) | FIGS | 3 | R99 | S3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure | New 22.031, 23.031 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7364 | 60085 | Immediate Service Termination / SECurity Immediate Service Termination | IST,SECIST | 3 | R99 | S3,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress. | 03.35, 22.032, 23.008, 23.016, 23.035, 29.002 |  |  |  |  | Wed 08/07/09 | Tue 21/07/09
7365 | 60018 | Core_Network_Security | Core_Network_Security | 3 | R99 | N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7366 | 60152 | GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7367 | 60184 | Dual Transfer Mode within GSM and GPRS | DTM | 2 | R99 | SMG,N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | 2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)” | 03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
7368 | 60013 | Class A Dual Transfer Mode | Class_A_Dual_Transfer_Mode_(DTM) | 3 | R99 | SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 5.1 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7369 | 60027 | Dual Transfer Mode | - | 3 | R99 | SMG,N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7370 | 60185 | General Packet Radio Service enahancements | GPRSenhancements | 2 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. | 05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7371 | 60132 | General Packet Radio Service | GPRS | 3 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
7372 | 60133 | GPRS2 | GPRS2 | 3 | R99 | SMG1,N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2) | 02.60, 23.003 |  |  |  |  | Thu 09/07/09 | Mon 06/07/09
7373 | 60134 | GPRS Tunnelling Protocol enhancement | GTP_enhancement | 3 | R99 | N4,N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.003, 23.008, 29.060 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
7374 | 60186 | Enhanced Data rates for GSM Evolution - Phase 1 | EDGE-Phase1 | 2 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation. | 10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7375 | 60030 | Enhanced Data rates for GSM Evolution | EDGE | 3 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008, |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7376 | 60034 | EDGE-Layer1 | EDGE-Layer1 | 3 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 05.05, 05.10, 05.50 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7377 | 60135 | High Speed Circuit Switched Data | HSCSD | 3 | R99 | SMG1,SMG2,SMG7 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No additional features for R99. | 02.34, 04.18, 11.10-1 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7378 | 60029 | Enhanced Circuit Switched Data - Phase 1 | ECSD | 3 | R99 | S1,SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info | 05.02, 08.58, 22.034 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7379 | 60032 | EDGE-Enhanced Circuit Switched Data | EDGE-ECSD | 3 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 5.03 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7380 | 60035 | Enhanced GPRS - Phase 1 | EGPRS | 3 | R99 | SMG,N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7381 | 60033 | EDGE-EGPRS | EDGE-EGPRS | 3 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 05.03, 05.05, 05.08 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7382 | 60069 | Packet Flow Context (PFC) | PFC | 3 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 4.18 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7383 | 60031 | Support for EGPRS in ANSI-136 networks and EDGE COMPACT | EDGE-Compact | 3 | R99 | SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7384 | 60036 | EGPRS COMPACT | EGPRS-Compact | 3 | R99 | SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 04.18, 05.02 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7385 | 60136 | COMPACT | COMPACT | 3 | R99 | SMG,N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 03.22, 04.18, 04.60, 05.08, 23.122, 24.008 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7386 | 60047 | GSM_400 | GSM_400 | 2 | R99 | SMG2,SMG7,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info. | 02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7387 | 60048 | GSM_450 | GSM_450 | 2 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 03.22, 03.30, 05.01, 05.05, 05.08 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7388 | 60131 | GSM_700 | GSM_700 | 2 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 5.05 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7389 | 60041 | Deleted - GERAN | GERAN | 2 | R99 | SMG2,S2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | G2: 04.18 CR#A248 , 04.60 CR#B090 |  |  | SP-06 |  | Thu 30/07/09 | Tue 09/02/10
7390 | 60153 | GSM Features transposed to UMTS | - | 1 | R99 | S1,S3,T2,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7391 | 60187 | Cell Broadcast Service | CBS | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks | 23.041 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7392 | 60188 | GSM mobile number portability euro MNP / North American MNP | MNP | 2 | R99 | S1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability. | 22.066 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7393 | 60144 | Mobile Number Portability | - | 3 | R99 | N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.018, 23.066, 29.002 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7394 | 60189 | Automatic establishment of roaming relations | - | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | Telecom Italia | enrico.scarrone@telecomitalia.it | framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other. | 22.101, 22.971 |  |  |  |  | Thu 16/07/09 | Tue 31/08/10
7395 | 60190 | Advanced addressing | - | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.101, 22.75U, 22.975 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7396 | 60191 | UMTS numbering, addressing and identities | - | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity. | 22.101 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7397 | 60192 | Lawful Interception for GSM Features transposed to UMTS | LI | 2 | R99 | S3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported. | New 33.106, 33.107 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7398 | 60154 | Charging | - | 1 | R99 | S1,S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7399 | 60011 | R99 Charging | Charging | 2 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.115, 23.121 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7400 | 60215 | R99 OAM Charging Management | OAMCH,CH | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99271 | - | - | - | - | 32.005, 32.015 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7401 | 60155 | Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM1999 | 1 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99581 | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 09/02/10
7402 | 60073 | OAM Principles and High-level Requirements | PR,Princs_&_Reqs_(PR) | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99581 | - | - | - | - | 32.101 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7403 | 60062 | OAM Architecture | OAMAR,AR,Telecom_Management_Arch_(AR) | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99581 | - | - | - | - | 32.101, 32.102 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7404 | 60014 | OAM Configuration Management | OAMCM,CM | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99273 | - | - | - | - | 32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7405 | 60063 | OAM Fault Management | OAMFM | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99272 | - | - | - | - | 32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7406 | 60064 | OAM Performance Management | OAMPM,PM | 2 | R99 | S5 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99274 | - | - | - | - | 12.04, 32.104 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7407 | 60106 | Vocabulary | Vocabulary | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 21.905 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7408 | 60037 | Emergency | Emergency | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7409 | 60049 | GSM General Bearer Services (GBS) and interworking scenarios support in UMTS | GSM_to_UMTS_Evol | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7410 | 60043 | GPRS_Mobile_IP_interworking | GPRS_Mobile_IP_interworking | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7411 | 60046 | GSM/UMTS interworking | 2G3Ginterworking | 1 | R99 | N1,N2,N4,R3,S1,SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7412 | 60050 | Handover | Handover | 1 | R99 | S1,SMG2,N1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7413 | 60120 | 2G3Ghandover | 2G3Ghandover | 1 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7414 | 60088 | Service Provider Name Indication | SPANME | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99 | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7415 | 60026 | Data & Data_CleanUp | Data,Data_CleanUp | 1 | R99 | SMG1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.01, 02.02, 02.04, 02.34 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7416 | 60125 | Unstructured Supplementary Service Data (USSD) | USSD | 1 | R99 | SMG1,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No additional features for R99. | 02.04, 02.90, 23.090, 29.002 |  |  |  |  | Tue 07/07/09 | Tue 07/07/09
7417 | 60126 | Man-Machine Interface (MMI) of the User Equipment (UE) | MMI | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Data services streamlining + Support for Anonymous Call Rejection | 22.03 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
7418 | 60127 | Network Identity and Timezone (NITZ) | NITZ | 1 | R99 | SMG1,SMG3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.42, 04.08 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
7419 | 60128 | Deleted - Operator Determined Barring for Packet Oriented Services | ODB_Enh. | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Remove ODB for Packet Oriented Services from R99 | 22.041 |  |  | SP-69 |  | Thu 09/07/09 | Tue 07/07/09
7420 | 60068 | Packet Flow Management | Packet_Flow_Management | 1 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 8.18 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7421 | 60044 | GPRS_Point-To-Multipoint Group call | GPRS_PTMG | 1 | R99 | SMG1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 2.6 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7422 | 60156 | Call Forwarding | - | 1 | R99 | SMG1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 22/07/09 | Tue 09/02/10
7423 | 60010 | Call Forwarding enhancements | CF_enhancements | 2 | R99 | N4,N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No additional features for R99. | 23.078, 23.079, 23.082, 29.002, 29.078 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7424 | 60116 | Call_Forwarding | Call_Forwarding | 2 | R99 | SMG1,N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.82, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7425 | 60117 | Call_Forwarding_Enhancements | Call_Forwarding_Enhancements | 2 | R99 | N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.082 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7426 | 60157 | Quality of Service | - | 1 | R99 | S2,T2,N1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
7427 | 60076 | End-to-end UMTS Quality of Service management | QoS | 2 | R99 | S2,T2,N1,N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | 23.107, 23.907, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7428 | 60130 | End-to-end QoS for PS Domain including IMS | E2EQoS99 | 2 | R99 | S2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Acronym changed from E2EQos | 23.060, 23.170 |  |  |  |  | Wed 08/07/09 | Tue 24/03/15
7429 | 60045 | GPRS-enhanced_QoS | GPRS-enhanced_QoS | 2 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | AT-commands for Enhanced QoS Support management | 27.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7430 | 60077 | QoS_enhancements | QoS_enhancements | 2 | R99 | N2,N1,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.008, 23.016, 24.008, 29.002, 29.060 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7431 | 60129 | Support of Localised Service Area | SoLSA | 1 | R99 | SMG2,SMG3,SMG7,N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99. | 04.08, 04.18, 08.08, 11.10-1, 29.002 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
7432 | 60100 | Transcoder_location | Transcoder_location | 1 | R99 | S2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum. | 23.11 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7433 | 60113 | Antenna_test_methods | Antenna_test_methods | 1 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 3.3 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7434 | 60107 | WBAMR / high quality speech in UMTS Phase 1 but not in R99 | WBAMR | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Add requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7435 | 60138 | Codec | - | 1 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7436 | 60015 | Codecs for Multimedia Telephony Service | Codec_for_Multimedia_Telephony | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7437 | 60415 | Codecs for Multimedia Telephony Service | Multimedia_Codec | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7438 | 60515 | Codecs for Multimedia Telephony Service | CSM | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7439 | 60615 | Codecs for Multimedia Telephony Service | WI2MMC | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7440 | 60715 | Codecs for Multimedia Telephony Service | Codec(s)_for_CS_MM_Tel._Serv | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7441 | 60815 | Codecs for Multimedia Telephony Service | Codec(s)_for_MM_Tel_Service | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7442 | 60915 | Codecs for Multimedia Telephony Service | - | 3 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7443 | 60078 | QoS for Speech and Multimedia Codec | QoS_for_Speech_&_MM_Codecs_/_AMR | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | SP-99060 | - | - | - | - | 26.102, 26.912 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7444 | 60099 | Tandem Free Operation - Adaptive Multi-Rate codec types | TFOAMR | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | UMTS_AMR2 is default Codec Type in R99 dual_mode terminals | 26.103 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7445 | 60112 | Noise Suppression for AMR | AMRNS | 2 | R99 | S4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078. | 06.77, 06.78 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
7446 | 60065 | Out-of-Band Transcoder | OoBT | 2 | R99 | N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR | 23.009, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7447 | 60066 | Out-of-Band Transcoder Control | OoBTC | 2 | R99 | N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | 24.008 CR#0572 in NP-020220 was approved under this WI | 24.008 CR#0572 in NP-020220 |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
7448 | 60143 | Advanced Speech Call Items enhancements | ASCI | 1 | R99 | SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
7449 | 60009 | Call Control improvements | CC_Related_items | 1 | R99 | N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441). | 24.007, 24.008 |  |  |  |  | Mon 06/07/09 | Thu 23/07/09
7450 | 60059 | Multimedia | Multimedia | 1 | R99 | N1,N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 24.008, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7451 | 60089 | Sub-System Number allocation for RANAP, RNSAP | SSN_allocation | 1 | R99 | N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part | 23.003 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7452 | 60053 | Intranet / ISP access with DHCP end-to-end | ISPaccess | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Access to an Intranet/ISP with DHCP end to end | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7453 | 60072 | Point_to_Multipoint_Services | Point_to_Multipoint_Services | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Support for the IP-Multicast protocol | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7454 | 60146 | Facsimile | FAX | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.003, 22.100 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7455 | 60081 | Realtime_NT_FAX_in_UMTS | Realtime_NT_FAX_in_UMTS | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX | 27.001, 27.003 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7456 | 60042 | Gateway Location Register (GLR) - Mobile Application Part (MAP) specification | GLR | 1 | R99 | N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 29.12 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7457 | 60056 | Multiple Subscriber Profile phase 2 | MSP2 | 1 | R99 | S1,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7458 | 60074 | Prepaging | Prepaging | 1 | R99 | N2,N4 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.018, 23.082, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7459 | 60148 | Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS | - | 1 | R99 | SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Re-definition of channel quality measure used for AMR link adaptation for DARP MS | 5.09 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
7460 | 60051 | Harmonized Standard | HS | 1 | R99 | SMG2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 13.21 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7461 | 60090 | Streamlining of specifications | Streamlining | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 27.060, 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7462 | 60079 | R99_Service_Clean_up | R99_Service_Clean_up | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7463 | 60094 | (Small) Technical Enhancements and Improvements for R99 | TEI | 1 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7464 | 60095 | TEI_[CS_Data] | TEI_[CS_Data] | 2 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7465 | 60096 | TEI_[GPRS] | TEI_[GPRS] | 2 | R99 | N3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7466 | 25016 | R99 UE Conformance Testing | TEI_Test | 1 | R99 | R5,T1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard. | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7467 | 60084 | Deleted - RTEI | RTEI | 2 | R99 | T1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150 |  |  | TP-06 |  | Thu 30/07/09 | Tue 09/02/10
7468 | 60193 | Common test environments for User Equipment (UE); Conformance testing | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | - | 34.108 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7469 | 60194 | Terminal conformance specification, Radio transmission and reception (FDD) | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode. | 34.121 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7470 | 60195 | Terminal conformance specification, Radio transmission and reception (TDD) | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode. | 34.122 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7471 | 60196 | UE conformance specification; Part 1: Protocol conformance specification | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure. | 34.123-1 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7472 | 60197 | UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. | 34.123-2 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7473 | 60198 | UE conformance specification; Part 3: Abstract test suites (ATSs) | - | 2 | R99 | R5,T1 | Fri 01/01/99 | Fri 01/01/99 | 100% | - | - | - | - | Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. | 34.123-3 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
7474 | 60028 | Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system | DTMF | 1 | R99 | N1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.014 CR#0004 |  |  | NP-06 |  | Thu 30/07/09 | Tue 09/02/10
7475 | 60052 | Deleted - Intersystem_Change | Intersystem_Change | 1 | R99 | SMG | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 04.18 CR#A243 |  |  | SMG |  | Thu 30/07/09 | Tue 09/02/10
7476 | 60054 | Deleted - Long_Forwardedto_Numbers | Long_Forwardedto_Numbers | 1 | R99 | N2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 29.002 |  |  | NP-06 |  | Mon 06/07/09 | Mon 06/07/09
7477 | 60080 | Deleted - RANimp-FSEarlyUE | RANimp-FSEarlyUE | 1 | R99 | R3 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547 |  |  | RP-06 |  | Thu 30/07/09 | Tue 09/02/10
7478 | 0 | Release 1999 Studies | - | 1 | R99 | S1,T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 14/06/10
7479 | 60061 | Advanced Addressing/Numbering | Numbering | 1 | R99 | S1 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | Vodafone | mona.mustapha@vodafone.com | Study on requirements for numbering and addressing for UMTS | 22.975 |  |  |  |  | Mon 06/07/09 | Tue 31/08/10
7480 | 60161 | Combined GSM and Mobile IP mobility handling in UMTS IP CN | - | 1 | R99 | S2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | - | 23.923 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10
7481 | 60101 | UE Capabilities Requirements | UCR | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure | 21.904 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
7482 | 60158 | Electrical safety requirements and regulations | - | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions. | 34.907 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7483 | 60159 | Specific Absorbtion Rate (SAR) requirements and regulations in different regions | - | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. | 34.925 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7484 | 60160 | Multi-mode UE issues | - | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs | 21.810, 21.910 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
7485 | 60162 | Provision of fax service in GSM and UMTS | - | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | Ericsson | peter.bleckert@ericsson.com | CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3 | 22.945 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10
7486 | 60163 | Separating Radio Resources and Mobility Management specific parts of the MS Classmark | - | 1 | R99 | T2 | Fri 01/01/99 | Fri 31/12/99 | 100% | - | - | - | - | CP#27: change of WG as a result of closure of CN and T. | 23.814 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10