{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp","index":0,"n_rows":8046,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version September 11th 2022",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[{"$f":"A2+1","v":2},0,"Pre TSG#97 version",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[{"$f":"A3+1","v":3},0,"Next milestones: Rel-17 Perf: Sept 22; Rel-18:St.2: Mar.23, St.3: Dec.23",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[6,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,null,null,null,null,"2022-09-09","2022-09-09"]
[7,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTTB4MBS",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,null,null,null,null,"2022-09-09","2022-09-09"]
[8,970042,"MPS for Messaging services ","MPS4msg",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,null,null,null,null,"2022-09-09","2022-09-09"]
[9,970041,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220937",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,null,null,null,null,"2022-09-09","2022-09-09"]
[10,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","2022-06-02","2023-03-10",0.1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10",22.916,96,49,null,null,"2022-06-02","2022-09-09"]
[11,960019,"Study on Energy Efficiency as service criteria ","FS_EnergyServ",1,"Rel-19","S1","2022-06-02","2023-03-10",0.1,"SP-220446",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10",22.882000000000001,96,49,null,null,"2022-06-02","2022-09-09"]
[12,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","2022-06-02","2023-06-12",0.3,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30",22.841000000000001,96,49,null,null,"2022-06-02","2022-09-09"]
[13,960017,"Study on UAV Phase 3 ","FS_UAV_Ph3",1,"Rel-19","S1","2022-06-02","2023-06-12",0.2,"SP-220680",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20",null,96,49,null,null,"2022-06-02","2022-09-09"]
[14,960016,"Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",1,"Rel-19","S1","2022-06-02","2023-03-10",0.35,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35",null,96,49,null,null,"2022-06-02","2022-09-09"]
[15,960015,"Study on roaming value added services ","FS_RVAS",1,"Rel-19","S1","2022-06-02","2023-03-10",0.6,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60",22.876999999999999,96,49,null,null,"2022-06-02","2022-09-09"]
[16,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","2022-03-10","2022-12-12",0.15,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;","22.875; 22.876",95,48,null,null,"2022-03-10","2022-07-13"]
[17,950003,"Study on Integrated Sensing and Communication ","FS_Sensing",1,"Rel-19","S1","2022-03-10","2023-06-12",0.4,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40",22.837,95,48,null,null,"2022-03-10","2022-09-09"]
[18,950004,"Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",1,"Rel-19","S1","2022-03-10","2022-12-12",0.5,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50",22.84,95,48,null,null,"2022-03-10","2022-09-09"]
[19,950005,"Study on Localized Mobile Metaverse Services ","FS_Metaverse",1,"Rel-19","S1","2022-03-10","2023-03-10",0.4,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40",22.856000000000002,95,48,null,null,"2022-03-10","2022-09-09"]
[20,950006,"Study on Network Sharing Aspects ","FS_NetShare",1,"Rel-19","S1","2022-03-10","2022-12-12",0.2,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20",22.850999999999999,95,48,null,null,"2022-03-10","2022-09-09"]
[21,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","2022-03-10","2023-09-12",0.3,"SP-220437",null,"Gach, Guillaume, UIC ","gach@uic.org ","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30",22.989000000000001,95,48,null,null,"2022-03-10","2022-09-09"]
[22,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","2019-09-19","2022-09-08",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"2019-09-13","2022-09-09"]
[23,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","2022-09-12","2024-03-12",0,"SP-220752",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ",null,"33.107; 33.108; 33.126; 33.127; 33.128 ",null,null,null,null,"2022-09-11","NA"]
[24,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[25,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[26,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18","S1","2021-06-11","2023-03-12",0.04,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[27,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","2021-06-11","2021-06-18",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[28,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220808",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[{"$f":"A29+1","v":29},920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[{"$f":"A30+1","v":30},940060,"Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",1,"Rel-18","S2","2021-12-20","2023-03-10",0.6,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60","23.700-27",94,48,null,null,"2021-12-19","2022-06-04"]
[31,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","2021-12-20","2022-09-12",0.5,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50","23.700-28",94,48,null,null,"2021-12-19","2022-06-04"]
[32,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18","R2","2021-12-13","2023-06-24",0.04,"RP-221819",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819",null,94,48,null,null,"2022-01-06","2022-07-12"]
[33,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221819","RP-221170 / 1746","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"2022-01-06","2022-09-09"]
[34,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","2021-12-13","2023-06-24",0,"RP-221819","RP-221170 / 1746","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[35,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18","R2","2021-12-13","2022-12-23",0.05,"RP-221806",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806",null,94,48,null,null,"2022-01-06","2022-07-12"]
[36,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2022-09-23",0.1,"RP-220979","RP-221553 / 1759","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[37,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","2022-03-07","2022-12-23",0,"RP-220979",null,"MediaTek",null,"20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...",null,95,48,null,null,"2022-06-04","2022-09-09"]
[38,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","2022-09-12","2023-03-12",0,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ",null,null,null,null,null,null,"2022-09-11","NA"]
[39,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","2022-06-02","2022-12-12",0,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ",null,null,96,49,null,null,"2022-06-02","NA"]
[40,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","2022-06-01","2022-06-15",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[41,0,"Rel-18 Internet of Things (IoT), MTC","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[42,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18","S1","2020-06-25","2022-09-12",0.9,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[43,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"2020-06-25","2021-09-13"]
[44,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[45,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[46,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","2021-12-20","2022-09-12",0.6,"SP-211643",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60","23.700-88",94,48,null,null,"2021-12-19","2022-06-04"]
[47,940021,"Study on Application layer support for Personal IoT Networks","FS_PINAPP",1,"Rel-18","S6","2021-12-13","2022-09-12",0.4,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40","23.700-78",94,48,null,null,"2021-12-13","2022-06-04"]
[48,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;",33.881999999999998,96,49,null,null,"2022-06-02","2022-07-13"]
[49,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","2021-06-11","2022-06-10",0.6,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60","23.700-97",92,47,null,null,"2021-06-11","2022-06-04"]
[50,950074,"NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18","R4","2022-03-15","2023-06-24",0.22,"RP-221556",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556",null,95,48,null,null,"2022-04-05","2022-07-12"]
[51,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.5,"RP-221556","RP-221555","Tim Frost, MediaTek Inc.","tim dot frost at mediatek dot com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...","36.102; 36.105; 36.108",95,48,null,null,"2022-04-05","2022-09-09"]
[52,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-Perf",2,"Rel-18","R4","2022-03-15","2023-06-24",0,"RP-221556","RP-221555","Tim Frost, MediaTek Inc.","tim dot frost at mediatek dot com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...",36.180999999999997,95,48,null,null,"2022-04-05","2022-09-09"]
[53,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-23",0.45,"RP-221548",null,"MediaTek ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[54,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[55,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[56,940051,"Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",1,"Rel-18","S2","2021-12-20","2022-09-12",0.5,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22","23.256 ; 23.700-58",94,48,null,null,"2021-12-19","2022-06-04"]
[57,960034,"Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;",33.890999999999998,96,49,null,null,"2022-06-02","2022-07-13"]
[58,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","2021-09-13","2022-09-12",0.5,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465","23.700-55",93,47,null,null,"2021-09-13","2022-06-04"]
[59,970038,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18","S6","2022-09-12","2023-03-12",0,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,null,null,null,null,"2022-09-11","NA"]
[60,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","2021-12-13","2022-12-23",0.05,"RP-213600",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far",null,94,48,null,null,"2022-01-06","NA"]
[61,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.05,"RP-213600","RP-221498","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[62,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[63,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"2020-06-25","2023-03-12",0.61,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[64,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"2020-06-25","2021-06-11"]
[65,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[66,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","2021-12-20","2022-12-12",0.6,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60","23.700-86",94,48,null,null,"2021-12-19","2022-06-04"]
[67,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;",33.893000000000001,96,49,null,null,"2022-06-02","2022-07-13"]
[68,940058,"Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",1,"Rel-18","S2","2021-12-20","2022-12-12",0.55000000000000004,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22","23.700-71",94,48,null,null,"2021-12-19","2022-06-04"]
[69,970021,"5GC LoCation Services - Phase 3 ","LCS_Ph3",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,null,null,null,null,"2022-09-11","NA"]
[70,940081,"Study on expanded and improved NR positioning","FS_NR_pos_enh2",1,"Rel-18","R1","2021-12-13","2022-12-22",0.4,"RP-213588","RP-221591","Alexey Khoryaev, Intel Corporation","alexey.khoryaev@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...",38.859000000000002,94,48,null,null,"2022-01-06","2022-09-09"]
[71,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"2021-12-13","2023-06-24",0.08,"RP-221798",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798",null,94,48,null,null,"2022-01-06","2022-07-12"]
[72,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","2021-12-13","2022-12-23",0.2,"RP-221798","RP-221064","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[73,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-221798","RP-221064","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[74,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"2021-12-13","2023-06-24",0.04,"RP-221262",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262",null,94,48,null,null,"2022-01-06","2022-07-12"]
[75,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221262","RP-221261","Youngdae LEE, LG Electronics","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[76,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","2021-12-13","2023-06-24",0,"RP-221262","RP-221261","Youngdae LEE, LG Electronics","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[77,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-23",0.05,"RP-221447",null,"CATT ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[78,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"2021-12-13","2022-09-23",0,"RP-213583",null,"ZTE",null,"no Perf. part",null,94,48,null,null,"2022-01-06","NA"]
[79,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","2021-12-13","2022-09-23",0,"RP-213583","RP-221310","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[80,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-10",0.3,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20","23.700-33",95,48,null,null,"2021-12-19","2022-03-12"]
[81,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",0.55000000000000004,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55","23.700-33",94,48,null,null,"2021-12-19","2022-06-04"]
[82,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","2022-03-10","2023-03-10",0.05,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;","33.740; 33.741",95,48,null,null,"2022-03-10","2022-07-13"]
[83,920015,"Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",1,"Rel-18","S6","2021-06-11","2022-09-12",0.55000000000000004,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55","23.700-96",92,47,null,null,"2021-06-11","2022-06-04"]
[84,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[85,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[86,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[87,940061,"Study on generic group management, exposure and communication enhancements ","FS_GMEC",1,"Rel-18","S2","2021-12-20","2022-09-12",0.7,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70","23.700-74",94,48,null,null,"2021-12-19","2022-06-04"]
[88,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","2021-09-10","2022-12-12",0.5,"SP-210957",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50","23.434 ; 23.545",93,47,null,null,"2021-09-10","2022-06-04"]
[89,940024,"Enhanced Service Enabler Architecture Layer for Verticals Phase 2 ","eSEAL2",1,"Rel-18","S6","2021-12-10","2022-12-12",0.2,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20",23.434000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[90,970037,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18","S6","2022-09-12","2023-03-12",0,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,23.434000000000001,null,null,null,null,"2022-09-11","NA"]
[91,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"2021-03-18","2021-06-11"]
[92,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","2020-09-01","2020-09-17",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"2020-09-11","NA"]
[93,960012,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18","S6","2022-06-02","2023-03-12",0,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ",null,"23.222; 23.434 ",96,49,null,null,"2022-06-02","NA"]
[{"$f":"A94+1","v":94},960028,"Study on SNAAPP securitY ","FS_SNAAPPY",1,"Rel-18","S3","2022-06-02","2022-12-12",0,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;",33.884,96,49,null,null,"2022-06-02","2022-07-13"]
[95,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"2020-06-25","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"2021-06-11","NA"]
[96,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[97,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"2021-06-11","2021-12-10"]
[98,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","2021-12-13","2022-12-12",0.25,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25",28.902000000000001,94,48,null,null,"2021-12-13","2022-06-04"]
[99,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",0.85,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85","23.700-95",92,47,null,null,"2021-06-11","2022-06-04"]
[100,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"2022-06-03","2023-12-12",0,"CP-221105",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,96,49,null,null,"2022-06-03","NA"]
[101,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","2022-06-03","2023-12-12",0,"CP-221105",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,24.558,96,49,null,null,"2022-06-03","NA"]
[102,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","2022-06-03","2023-12-12",0,"CP-221105",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,"29.116, 29.122, 29.222, 29.255, 29.257, 29.343, 29.486, 29.522, 29.538, 29.549, 29.558",96,49,null,null,"2022-06-03","NA"]
[103,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[104,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","2022-06-02","2022-06-10",0.45,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45",22.100999999999999,96,49,null,null,"2022-06-02","2022-06-04"]
[105,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","2021-12-10","2023-03-10",0.1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10",33.18,94,48,null,null,"2021-12-10","2022-06-04"]
[106,940025,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18","S6","2021-12-10","2023-03-10",0.3,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2022-06-04"]
[107,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"2020-06-25","2022-06-10",0.96,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","NA"]
[108,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","2020-06-25","2021-09-20",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"2020-06-26","2021-09-13"]
[109,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","2021-09-10","2022-06-10",0.9,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","2022-06-04"]
[110,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"2019-03-07","2023-12-15",0,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[111,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","2019-03-07","2020-06-10",0,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[112,970033,"   CT aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","2022-09-12","2023-12-15",0,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com",null,"24.281, 24.282, 24.379, 24.380, 24.481, 24.483, 24.484, 42.581, 24.582",null,null,null,null,"2022-09-05","NA"]
[113,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"2019-03-07","2023-12-15",0,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[114,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","2019-03-07","2020-06-10",0,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[115,970034,"   CT aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","2022-09-12","2023-12-15",0,"CP-222176",null,"Haitao Wei, Huawei","weihaitao@huawei.com",null,"24.281, 24.282, 24.379, 24.380, 24.481, 24.483, 24.484, 24.581, 24.582",null,null,null,null,"2022-09-05","NA"]
[116,970027,"ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","2022-09-12","2023-03-12",0,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ",null,33.503,null,null,null,null,"2022-09-11","NA"]
[117,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[118,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[119,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","2019-09-19","2021-12-10",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"2019-09-13","2021-09-13"]
[120,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","2021-12-13","2023-03-10",0.25,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25","23.700-38",94,48,null,null,"2021-12-13","2022-06-04"]
[121,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","2021-12-13","2022-09-12",0.75,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75","23.700-76",94,48,null,null,"2021-12-13","2022-06-04"]
[122,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","2018-06-06","2022-06-10",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"2018-06-06","2022-06-04"]
[123,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[124,940071,"Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",1,"Rel-18","S2","2021-12-20","2022-09-12",0.6,"SP-220071",null,"Tricci So, OPPO ","tricci.so@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60","23.700-80",94,48,null,null,"2021-12-19","2022-06-04"]
[125,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"2019-12-06","2021-12-10",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"2021-06-11","2022-07-13"]
[126,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","2019-12-06","2021-06-11",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"2019-12-06","2022-06-21"]
[127,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"2021-06-11","2022-06-21"]
[128,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_Air",1,"Rel-18","R1","2021-12-13","2022-12-23",0.1,"RP-221348","RP-221347","Juan Montojo, Qualcomm","juanm@qti.qualcomm.com","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....",38.843000000000004,94,48,null,null,"2022-01-06","2022-09-09"]
[129,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18","R3","2021-12-13","2023-06-23",0.1,"RP-220635",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635",null,94,48,null,null,"2022-01-06","2022-04-05"]
[130,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","2021-12-13","2023-06-23",0.1,"RP-213602","RP-221381","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[131,960031,"Deleted- Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list",33.877000000000002,96,49,null,null,"2022-06-02","2022-07-13"]
[132,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","2021-12-13","2022-09-12",0.1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10",28.908000000000001,94,48,null,null,"2021-12-13","2022-06-04"]
[133,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-18","S4","2022-03-12","2022-03-12",0.1,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10",26.927,95,48,null,null,"2022-03-10","2022-06-04"]
[134,960037,"Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",1,"Rel-18","S3","2022-06-21","2023-03-12",0,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;",33.898000000000003,96,49,null,null,"2022-06-21","2022-07-13"]
[135,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[136,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221458",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458",null,94,48,null,null,"2022-01-06","2022-07-12"]
[137,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221458","RP-221459","Erlin Zeng, CATT","erlin.zeng@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[138,940067,"Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",1,"Rel-18","S2","2021-12-20","2022-09-12",0.55000000000000004,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55","23.700-47",94,48,null,null,"2021-12-19","2022-06-04"]
[139,960041,"Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;",33.883000000000003,96,49,null,null,"2022-06-02","2022-07-13"]
[140,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18","R4","2021-06-15","2023-06-23",0.15,"RP-220518",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518",null,92,47,null,null,"2021-07-02","2022-04-05"]
[141,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","2021-06-15","2023-06-23",0.15,"RP-220518","RP-221337","Roland Beutler, EBU","Roland.Beutler@swr.de","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[142,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[143,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[144,0,"Rel-18 Slice","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[145,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","2021-03-12","2022-09-22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[146,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","2021-03-18","2023-03-10",0.8,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23","New ",91,46,null,null,"2021-03-18","2022-06-04"]
[147,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"2020-06-25","2023-03-12",0.49,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[148,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","2020-06-25","2021-03-17",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"2020-06-25","2021-06-11"]
[149,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[150,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","2021-12-20","2022-09-12",0.5,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50","23.700-41; 23.700-17",94,48,null,null,"2021-12-19","2022-06-04"]
[151,970022,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220812",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[152,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;",33.886000000000003,96,49,null,null,"2022-06-02","2022-07-13"]
[153,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","2021-12-10","2022-09-12",0.35,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35","28.531; 28.541 ",94,48,null,null,"2021-12-10","2022-06-04"]
[154,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","2022-03-10","2023-06-12",0,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23",28.835999999999999,95,48,null,null,"2022-03-10","2022-09-11"]
[155,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","2021-03-18","2021-12-10",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"2021-03-18","2022-06-04"]
[156,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","2022-06-15","2023-03-10",0,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675",26.940999999999999,96,49,null,null,"2022-06-03","2022-08-17"]
[157,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","2021-12-10","2022-03-11",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"2021-12-10","2022-06-04"]
[{"$f":"A158+1","v":158},910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","2021-03-18","2022-06-10",0.85,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85","23.700-99",91,46,null,null,"2021-03-18","2022-06-04"]
[159,960013,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18","S6","2022-06-02","2023-03-12",0,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;","23.434 ; 23.435",96,49,null,null,"2022-06-02","2022-07-13"]
[160,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","2022-06-03","2023-09-12",0.6,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"2022-06-03","2022-07-13"]
[161,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[162,940068,"Study on architecture enhancement for XR and media services ","FS_XRM",1,"Rel-18","S2","2021-12-20","2022-12-12",0.4,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705","23.700-60",94,48,null,null,"2021-12-19","2022-06-21"]
[163,940087,"Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",1,"Rel-18","R2","2021-12-13","2022-12-22",0.3,"RP-220285","RP-221079","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...",38.835000000000001,94,48,null,null,"2022-01-06","2022-09-09"]
[164,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","2022-03-10","2023-06-12",0.1,"SP-220239",null,"Naotaka MORITA, NTT ","naotaka.morita@ntt-at.co.jp ","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ",26.93,95,48,null,null,"2022-03-10","2022-06-04"]
[165,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","2022-03-15","2023-12-12",0.05,"SP-220241",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5",26.113,95,48,null,null,"2022-03-10","2022-06-04"]
[166,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","2022-03-10","2023-03-10",0.3,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30","26.998 ; 26.806",95,48,null,null,"2022-03-10","2022-06-04"]
[167,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","2022-03-10","2023-03-10",0.08,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"2022-03-10","2022-06-04"]
[168,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","2022-06-03","2023-12-08",0,"SP-220668",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668",26.263999999999999,96,49,null,null,"2022-06-03","2022-08-17"]
[169,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","2022-06-03","2023-12-08",0,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672",null,96,49,null,null,"2022-06-03","2022-08-17"]
[170,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","2022-06-03","2023-12-08",0,"SP-220685",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685",26.565000000000001,96,49,null,null,"2022-06-03","2022-08-17"]
[171,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","2022-06-03","2023-06-08",0,"SP-220613",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP",26.521999999999998,96,49,null,null,"2022-06-03","2022-08-03"]
[172,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","2022-06-03","2023-12-08",0,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708",26.812000000000001,96,49,null,null,"2022-06-03","2022-08-17"]
[173,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","2022-06-03","2022-12-08",0,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR","26.998; ",96,49,null,null,"2022-06-03","NA"]
[174,0,"Rel-18 Energy and complexity saving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[175,940080,"Study on network energy savings for NR","FS_Netw_Energy_NR",1,"Rel-18","R1","2021-12-13","2022-12-22",0.1,"RP-221443","RP-221442","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443",38.863999999999997,94,48,null,null,"2022-01-06","2022-07-12"]
[176,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","2021-12-13","2022-12-23",0,"RP-221271","RP-221270","Xiaodong Shen, vivo Communication Technology","shenxiaodong@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...",38.869,94,48,null,null,"2022-01-06","2022-09-09"]
[177,940086,"Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",1,"Rel-18","R1","2021-12-13","2022-09-22",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...",38.865000000000002,94,48,null,null,"2022-01-06","2022-09-09"]
[178,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","2021-12-20","2022-09-12",0.7,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70","23.700-68",94,48,null,null,"2021-12-19","2022-06-04"]
[179,970013,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[180,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[181,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","2020-06-25","2021-12-10",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"2020-06-25","2021-12-10"]
[182,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","2020-06-25","2021-09-16",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"2020-06-26","2022-03-12"]
[183,950025,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18","S6","2022-03-10","2022-12-12",0.4,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-03-10","2022-06-04"]
[184,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"2020-12-04","2022-06-21"]
[185,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","2021-09-13","2022-09-12",0.65,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466","23.700-64",93,47,null,null,"2021-09-13","2022-06-04"]
[186,970039,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18","S6","2022-09-12","2023-03-12",0,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",null,null,null,null,"2022-09-11","NA"]
[187,970003,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ",null,"23.287; 23.501 ",null,null,null,null,"2022-09-11","NA"]
[188,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18","R4","2022-03-15","2023-03-24",0.02,"RP-220985",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ",null,95,48,null,null,"2022-04-05","NA"]
[189,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","2022-03-15","2022-09-23",0,"RP-220985","RP-221405","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[190,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","2022-03-15","2023-03-24",0,"RP-220985","RP-221405","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[191,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",7.0000000000000007E-2,"RP-221402",null,"Samsung ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[192,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[193,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"2019-09-19","2023-06-12",0.61,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"2021-06-11","NA"]
[194,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","2019-09-19","2021-09-08",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"2019-09-13","2021-09-13"]
[195,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","2021-06-11","2021-12-12",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"2021-06-11","2021-09-13"]
[196,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","2021-12-20","2022-09-12",0.55000000000000004,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55","23.700-87",94,48,null,null,"2021-12-19","2022-06-04"]
[197,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220804",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ",null,"23.228; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[198,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","2022-06-02","2023-06-12",0,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;",33.89,96,49,null,null,"2022-06-02","2022-07-13"]
[199,940070,"Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",1,"Rel-18","S2","2021-12-20","2022-09-12",0.7,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70","23.700-53",94,48,null,null,"2021-12-19","2022-06-04"]
[200,970023,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220813",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[201,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","2021-12-20","2022-12-12",0.6,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417","23.700-62",94,48,null,null,"2021-12-19","2022-06-21"]
[202,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","2019-03-07","2022-12-02",0.2,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->","26.260, new",83,42,null,null,"2019-03-14","2022-06-04"]
[203,770024,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18","S4","2017-09-08","2023-12-12",0.35,"SP-170611",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35","26.114, new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2022-06-04"]
[204,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[205,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","2020-12-04","2021-06-11",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"2020-12-04","2021-12-10"]
[206,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[207,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[208,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","2022-06-02","2023-06-12",0,"SP-220468",null,"Samar Shailendra, Intel ","samar.shailendra@intel.com ","13/7/22: 23.958 added;",23.957999999999998,96,49,null,null,"2022-06-02","2022-07-13"]
[209,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",0.75,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75","23.700-98",92,47,null,null,"2021-06-11","2022-06-04"]
[210,970040,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18","S6","2022-09-12","2023-03-12",0,"SP-220916",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,23.558,null,null,null,null,"2022-09-11","NA"]
[211,950049,"Study on Edge Computing phase 2","FS_EDGE_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-12",0.34,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2021-12-19","2022-03-12"]
[212,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",0.55000000000000004,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55","23.700-48",94,48,null,null,"2021-12-19","2022-06-04"]
[213,970026,"   Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220816",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ",null,"23.548; 23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[214,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","2022-03-10","2022-12-12",0.3,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;",33.738999999999997,95,48,null,null,"2022-03-10","2022-07-13"]
[215,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[216,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"2020-09-16","2023-03-12",0.66,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"2021-06-11","NA"]
[217,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","2020-09-16","2021-06-11",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"2020-09-10","2021-09-13"]
[218,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[219,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ",null,"23.501; 23.502; 23.402 ",null,null,null,null,"2022-09-11","NA"]
[220,0,"Rel-18 Other topics","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[221,970031,"Management Data Analytics phase 2 ","MDAS_Ph2",1,"Rel-18","S5","2022-09-12","2023-12-12",0,"SP-220894",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ",null,"28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",null,null,null,null,"2022-09-11","NA"]
[{"$f":"A222+1","v":222},970036,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18","S6","2022-09-12","2023-03-12",0,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ",null,23.434000000000001,null,null,null,null,"2022-09-11","NA"]
[223,970020,"Seamless UE context recovery ","SUECR",1,"Rel-18","S2","2022-09-12","2022-12-12",0,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[224,970019,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[225,970017,"5G AM Policy ","AMP",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220807",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[226,970012,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[227,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","2021-12-20","2022-09-12",0.7,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70","23.700-46",94,48,null,null,"2021-12-19","2022-06-04"]
[228,970011,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[229,970010,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220800",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[230,970004,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18","S2","2022-09-12","2022-12-12",0,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ",null,"23.503; 23.501; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[231,970009,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,null,null,null,null,"2022-09-11","NA"]
[232,970005,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18","S2","2022-09-12","2022-09-19",0,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,null,null,null,null,"2022-09-11","NA"]
[233,970006,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[234,970007,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18","S2","2022-09-12","2022-12-12",0,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",null,null,null,null,"2022-09-11","NA"]
[235,970008,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",null,null,null,null,"2022-09-11","NA"]
[236,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18","C3","2019-03-07","2019-03-07",0,"CP-222131",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525, 29.507, 29.513, 29.518",null,null,null,null,"2022-03-10","NA"]
[237,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","2019-03-07","2019-03-07",0,"CP-222131",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525, 29.507, 29.513, 29.518",null,null,null,null,"2022-09-07","NA"]
[238,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","2019-03-07","2019-03-07",0,"CP-222131",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525, 29.507, 29.513, 29.518",null,null,null,null,"2022-09-07","NA"]
[239,950026,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18","S6","2022-03-10","2023-03-10",0.3,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30",23.553999999999998,95,48,null,null,"2022-03-10","2022-06-04"]
[240,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","2022-03-10","2023-03-10",0.1,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;","33.926 ; 33.537",95,48,null,null,"2022-03-10","2022-07-13"]
[241,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","2022-03-10","2023-03-10",0.05,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;","33.926 ; 33.742",95,48,null,null,"2022-03-10","2022-07-13"]
[242,950020,"Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",1,"Rel-18","S3","2022-03-10","2022-12-12",0.3,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30",null,95,48,null,null,"2022-03-10","2022-06-04"]
[243,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.15,"SP-220327",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;",33.737000000000002,95,48,null,null,"2022-03-10","2022-07-13"]
[244,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"2020-06-25","2023-03-12",0.69,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"2021-03-18","NA"]
[245,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","2020-06-25","2021-03-12",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"2020-06-25","2021-06-11"]
[246,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","2021-12-20","2022-09-12",0.65,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65","23.700-25",94,48,null,null,"2021-12-19","2022-06-04"]
[247,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","2021-03-18","2021-09-12",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"2021-03-18","2021-06-11"]
[248,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","2022-09-12","2023-03-12",0,"SP-220814",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2022-09-11","NA"]
[249,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","2022-03-10","2022-09-12",0.15,"SP-220146",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15",28.832000000000001,95,48,null,null,"2022-03-10","2022-06-04"]
[250,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","2021-12-13","2022-09-22",1,"RP-221438","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[251,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18","S1","2020-09-16","2022-09-12",0.83,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[252,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","2020-09-16","2021-09-08",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"2020-09-10","2021-09-13"]
[253,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-14"]
[254,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","2021-12-20","2022-09-12",0.55000000000000004,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55","23.700-05",94,48,null,null,"2021-12-19","2022-06-04"]
[255,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18","R3","2021-12-13","2023-06-24",0.02,"RP-221815",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815",null,94,48,null,null,"2022-01-06","2022-07-12"]
[256,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","2021-12-13","2022-12-23",0.05,"RP-221815","RP-221179","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[257,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","2021-12-13","2023-06-24",0,"RP-221815","RP-221179","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[258,840085,"Study on enhancement of support for 5WWC","FS_5WWC_Ph2",1,"Rel-18","S2","2021-12-20","2022-09-12",0.6,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. Rapp changed from Huan Li, Huawei; 4/6/22: 30%->60; 21/6/22: WID:SP-211640...","23.700-16",84,43,null,null,"2017-06-03","2022-06-21"]
[259,960030,"Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220528",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;",33.887,96,49,null,null,"2022-06-02","2022-07-13"]
[260,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18","R3","2021-12-13","2022-12-23",0.1,"RP-221803",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803",null,94,48,null,null,"2022-01-06","2022-07-12"]
[261,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","2021-12-13","2022-12-23",0.1,"RP-221803","RP-221244","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[262,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","2021-12-13","2022-12-12",0.1,"SP-211433",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10",28.863,94,48,null,null,"2021-12-13","2022-06-04"]
[263,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","2022-03-10","2022-03-11",7.0000000000000007E-2,"SP-220351",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7",null,95,48,null,null,"2022-03-10","2022-06-04"]
[264,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"2021-09-10","2022-09-12",0.26,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"2021-09-10","2022-01-07"]
[265,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[266,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","2021-12-20","2022-09-12",0,"SP-211595",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ",null,"23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"2021-12-19","NA"]
[267,940064,"Study on 5G AM Policy","FS_AMP",1,"Rel-18","S2","2021-12-20","2022-09-12",0.8,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647","23.700-89",94,48,null,null,"2021-12-19","2022-06-21"]
[268,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18","R3","2021-01-01","2023-06-23",0.09,"RP-221825",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825",null,94,48,null,null,"2022-01-06","2022-07-12"]
[269,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","2021-01-01","2022-12-23",0.1,"RP-221825","RP-221372","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[270,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-06-23",7.0000000000000007E-2,"RP-221365","RP-221366","Luting Kong, CMCC","kongluting@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[271,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","2021-12-10","2023-06-12",0.05,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5","28.313; ; 28.317",94,48,null,null,"2021-12-10","2022-06-04"]
[272,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","2020-12-04","2021-03-12",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-04","2020-12-05"]
[273,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","2021-03-18","2021-03-25",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-03-19"]
[274,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[275,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","2021-12-10","2023-03-12",0,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;","33.527; 33.927; 33.936",94,48,null,null,"2021-12-10","2022-01-07"]
[276,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.1,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10","33.926; 33.117, 33.511, 33.512, 33.513, 33.514, 33.515, 33.516, 33.517, 33.518, 33.519, 33.520, 33.521, 33.522, 33.326 ",95,48,null,null,"2022-03-10","2022-06-04"]
[277,930013,"Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",1,"Rel-18","S6","2021-09-13","2022-09-12",0.6,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467","23.700-34",93,47,null,null,"2021-09-13","2022-06-04"]
[278,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;",33.892000000000003,96,49,null,null,"2022-06-02","2022-07-13"]
[279,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","2018-09-06","2022-12-12",0.9,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[280,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","2022-06-02","2022-12-12",0,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ",null,null,96,49,null,null,"2022-06-02","NA"]
[281,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","2022-06-02","2023-12-12",0,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"2022-06-03","2022-08-03"]
[282,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","2022-06-02","2023-03-10",0,"SP-220667",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667",26.501000000000001,96,49,null,null,"2022-06-03","2022-08-17"]
[283,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.02,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,96,49,null,null,"2022-06-03","NA"]
[284,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","2022-06-03","2023-12-12",0.05,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"2022-06-03","NA"]
[285,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",0,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","NA"]
[{"$f":"A286+1","v":286},960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","2022-06-03","2023-03-10",0.6,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"2022-06-03","2022-07-13"]
[287,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[288,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[289,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[290,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[291,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[292,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[293,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[294,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18","C1","2022-06-03","2023-12-08",0.1,"CP-221270",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229, 24.281, 24.282, 24.379, 24.380, 24.481, 24.482, 24.483, 24.484, 24.581, 24.582, 29.379, 29.380, 29.582",96,49,null,null,"2022-06-03","2022-06-20"]
[295,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","2022-06-03","2022-12-08",0.2,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229, 24.173, 24.629, 24.605, 24.239, 24.604, 24.642",96,49,null,null,"2022-06-03","2022-06-20"]
[296,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18","C1","2019-03-07","2019-03-07",0,"CP-222177",null,"Gkatzikis, Lazaros, Nokia","lazaros.gkatzikis@nokia.com",null,"23.218, 24.229, 24.930, 29.163, 29.165, 29.292",96,49,null,null,"2022-06-03","2022-06-20"]
[297,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","2019-03-07","2019-03-07",0,"CP-222177",null,"Gkatzikis, Lazaros, Nokia","lazaros.gkatzikis@nokia.com",null,"23.218, 24.229, 24.930, 29.163, 29.165, 29.292",null,null,null,null,"2022-09-07","NA"]
[298,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","2019-03-07","2019-03-07",0,"CP-222177",null,"Gkatzikis, Lazaros, Nokia","lazaros.gkatzikis@nokia.com",null,"23.218, 24.229, 24.930, 29.163, 29.165, 29.292",null,null,null,null,"2022-09-07","NA"]
[299,0,"Rel-18 Other NR-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[300,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221876",null,"ZTE ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[301,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221876",null,"ZTE ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[302,961210,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221876",null,"ZTE ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[303,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221877",null,"ZTE ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[304,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221877",null,"ZTE ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[305,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221877",null,"ZTE ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[306,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18","R4","2022-06-15","2023-12-15",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[307,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","2022-06-15","2023-12-15",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[308,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221835",null,"Ericsson ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[309,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221835",null,"Ericsson ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[310,961207,"   Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221835",null,"Ericsson ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[311,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.25,"RP-221838",null,"Ericsson ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[312,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.25,"RP-221838",null,"Ericsson ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[313,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.25,"RP-221838",null,"Ericsson ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[314,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18","R4","2022-06-15","2023-03-23",0.1,"RP-221778",null,"Spark NZ Ltd ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[315,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",0.1,"RP-221778",null,"Spark NZ Ltd ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[316,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","2022-06-15","2023-03-23",0.1,"RP-221778",null,"Spark NZ Ltd ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[317,960098,"Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221845",null,"Huawei ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[318,960198,"   Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221845",null,"Huawei ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[319,960298,"   Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221845",null,"Huawei ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[320,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221844",null,"Huawei ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[321,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221844",null,"Huawei ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[322,960295,"   Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221844",null,"Huawei ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[323,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18","R4","2022-06-15","2023-03-23",0.08,"RP-221813",null,"Apple ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[324,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","2022-06-15","2023-03-23",0.15,"RP-221813",null,"Apple ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[325,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","2022-06-15","2023-03-15",0,"RP-221813",null,"Apple ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[326,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18","R4","2021-12-13","2023-06-24",0,"RP-220401",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401",null,94,48,null,null,"2022-01-06","2022-04-05"]
[327,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","2021-12-13","2022-12-23",0,"RP-220401","RP-221415","Toni L hteensuo, Nokia","toni.h.lahteensuo@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[328,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","2021-12-13","2023-06-24",0,"RP-220401","RP-221415","Toni L hteensuo, Nokia","toni.h.lahteensuo@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[329,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18","R1","2021-12-13","2023-06-24",0.38,"RP-221622",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622",null,94,48,null,null,"2022-01-06","2022-07-12"]
[330,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","2021-12-13","2022-12-23",0.95,"RP-221622","RP-221621","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[331,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-221622","RP-221621","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[332,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18","R1","2021-12-13","2023-06-24",0.12,"RP-221435",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435",null,94,48,null,null,"2022-01-06","2022-07-12"]
[333,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","2021-12-13","2022-12-23",0.3,"RP-221435","RP-221436","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada@docomo-lab.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[334,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-221435","RP-221436","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada@docomo-lab.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[335,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-221858",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858",null,94,48,null,null,"2022-01-06","2022-07-12"]
[336,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","2021-12-13","2022-12-23",0,"RP-221858","RP-221282","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[337,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-221858","RP-221282","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[338,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18","R1","2021-12-13","2023-06-24",0.08,"RP-213598",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO",null,94,48,null,null,"2022-01-06","NA"]
[339,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","2021-12-13","2022-12-23",0.2,"RP-213598","RP-221393","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[340,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","2021-12-13","2023-06-24",0,"RP-213598","RP-221393","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[341,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","2021-12-13","2022-12-23",0.15,"RP-221352","RP-221351","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...",38.857999999999997,94,48,null,null,"2022-01-06","2022-09-09"]
[342,940083,"Study on NR network-controlled repeaters","FS_NR_netcon_repeater",1,"Rel-18","R1","2021-12-13","2022-09-22",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...",38.866999999999997,94,48,null,null,"2022-01-06","2022-09-09"]
[343,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18","R2","2021-12-13","2023-06-24",0.04,"RP-221799",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799",null,94,48,null,null,"2022-01-06","2022-07-12"]
[344,940198,"   Core part: Further NR mobility enhancements","NR_mob_enh2-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221799","RP-221557","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[345,940298,"   Perf. part: Further NR mobility enhancements","NR_mob_enh2-Perf",2,"Rel-18","R2","2021-12-13","2023-06-24",0,"RP-221799","RP-221557","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[346,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-221281",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281",null,94,48,null,null,"2022-01-06","2022-07-12"]
[347,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_Enh-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.1,"RP-213589","RP-221280","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[348,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18","R4","2022-03-15","2022-12-22",0.25,"RP-220971",null,"Ligado Networks ",null,null,null,95,48,null,null,"2022-04-05","NA"]
[349,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","2022-03-15","2022-12-22",0.5,"RP-220971","RP-221061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[{"$f":"A350+1","v":350},950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","2022-03-15","2022-12-22",0,"RP-220971","RP-221061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,95,48,null,null,"2022-04-05","2022-06-20"]
[351,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18","R4","2022-03-15","2022-12-23",0,"RP-220916",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ",null,95,48,null,null,"2022-04-05","NA"]
[352,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","2022-03-15","2022-09-23",0,"RP-220916","RP-221165","Aurelian Bria, Ericsson","aurelian.bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[353,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","2022-03-15","2022-12-23",0,"RP-220916","RP-221165","Aurelian Bria, Ericsson","aurelian.bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[354,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18","R4","2022-03-15","2022-12-23",0,"RP-220932",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ",null,95,48,null,null,"2022-04-05","NA"]
[355,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","2022-03-15","2022-12-23",0,"RP-220932RP-221288","RP-221287","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...",38.878,95,48,null,null,"2022-04-05","2022-09-09"]
[356,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18","R4","2022-03-15","2023-03-24",0.02,"RP-221369",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369",null,95,48,null,null,"2022-04-05","2022-07-12"]
[357,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.05,"RP-221369","RP-221370","Shao Zhe, CMCC","Shaozhe@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[358,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","2022-03-15","2023-03-24",0,"RP-221369","RP-221370","Shao Zhe, CMCC","Shaozhe@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[359,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18","R4","2022-03-15","2023-03-24",0.1,"RP-221862",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862",null,95,48,null,null,"2022-04-05","2022-07-12"]
[360,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.1,"RP-221862","RP-221207","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...",38.890999999999998,95,48,null,null,"2022-04-05","2022-09-09"]
[361,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","2022-03-15","2023-03-24",0.1,"RP-221862","RP-221207","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[362,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18","R4","2022-03-15","2023-03-24",0.03,"RP-221753",null,"Qualcomm ",null,"; 12/7/22: WID:RP-220974->RP-221753",null,95,48,null,null,"2022-04-05","2022-07-12"]
[363,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","2022-03-15","2022-09-23",0.1,"RP-221753","RP-221225 / 1752","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[364,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","2022-03-15","2023-03-24",0,"RP-221753","RP-221225 / 1752","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[365,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18","R4","2022-03-15","2023-06-24",0.02,"RP-221696",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696",null,95,48,null,null,"2022-04-05","2022-07-12"]
[366,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.05,"RP-220977","RP-221697","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[367,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","2022-03-15","2023-06-24",0,"RP-220977","RP-221697","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[368,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18","R4","2022-03-15","2023-06-23",0.1,"RP-221496",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496",null,95,48,null,null,"2022-04-05","2022-07-12"]
[369,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.1,"RP-221496","RP-221495","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...",38.881,95,48,null,null,"2022-04-05","2022-09-09"]
[370,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","2022-03-15","2023-06-23",0.1,"RP-221496","RP-221495","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[371,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18","R4","2022-03-15","2022-12-23",0.04,"RP-221809",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809",null,95,48,null,null,"2022-04-05","2022-07-12"]
[372,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","2022-03-15","2022-09-23",0.1,"RP-221809","RP-221742","Yasuki Suzuki","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[373,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","2022-03-15","2022-12-23",0,"RP-221809","RP-221742","Yasuki Suzuki","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[374,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18","R4","2022-03-15","2023-06-24",0.04,"RP-220772",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772",null,95,48,null,null,"2022-04-05","2022-04-05"]
[375,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","2022-03-15","2022-12-23",0.1,"RP-221018","RP-221560","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[376,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","2022-03-15","2023-06-24",0,"RP-221018","RP-221560","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[377,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","2022-06-15","2022-12-15",0,"RP-221872",null,"Qualcomm ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[378,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[379,961009,"Rel-18 band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) ","NR_SUL_combos_R18",1,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221839",null,"Huawei ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[380,961109,"   Core part: Rel-18 band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) ","NR_SUL_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221839",null,"Huawei ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[381,961209,"   Perf. part: Rel-18 band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) ","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221839",null,"Huawei ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[382,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWV",1,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221841",null,"Nokia ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[383,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-222058",null,"Nokia ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[384,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.02,"RP-221264",null,"CHTTL ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[385,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221264RevisedWID:Rel-18DualConnectivity(DC)of1bandLTE(1DL/1UL)and1NRband(1DL/1UL)",null,"CHTTL ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[386,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221264RevisedWID:Rel-18DualConnectivity(DC)of1bandLTE(1DL/1UL)and1NRband(1DL/1UL)",null,"CHTTL ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[387,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221400",null,"Samsung ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[388,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221400",null,"Samsung ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[389,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221400",null,"Samsung ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[390,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221800",null,"LG Electronics ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[391,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221800",null,"LG Electronics ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[392,961203,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221800",null,"LG Electronics ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[393,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221832",null,"Huawei ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[394,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221832",null,"Huawei ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[395,961204,"   Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221832",null,"Huawei ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[396,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221833",null,"Nokia ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[397,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221833",null,"Nokia ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[398,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221833",null,"Nokia ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[399,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221834",null,"ZTE ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[400,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221834",null,"ZTE ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[401,961206,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221834",null,"ZTE ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[402,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18","R4","2022-06-15","2022-12-23",0.02,"RP-221879",null,"CATT ",null,null,null,null,null,null,null,"2022-08-03","NA"]
[403,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221879",null,"CATT ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[404,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221879",null,"CATT ",null,"9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[405,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18","R4","2022-06-15","2022-12-23",0.05,"RP-221843",null,"China Telecom ","LTE, NR ",null,null,null,null,null,null,"2022-08-03","NA"]
[406,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.1,"RP-221843",null,"China Telecom ","LTE, NR ","9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[407,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0,"RP-221843",null,"China Telecom ","LTE, NR ","9/9/22: CD:1...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[408,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[409,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18","R4","2022-06-15","2022-12-23",0.2,"RP-221831",null,"Huawei ","LTE ",null,null,null,null,null,null,"2022-08-03","NA"]
[410,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","2022-06-15","2022-12-23",0.2,"RP-221831",null,"Huawei ","LTE ","9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[411,960299,"   Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","2022-06-15","2022-12-23",0.2,"RP-221831",null,"Huawei ","LTE ","9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[412,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","2022-06-15","2022-12-22",0.99,"RP-221846",null,"China Mobile ","LTE ",null,null,null,null,null,null,"2022-08-03","NA"]
[413,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",0.99,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...",null,null,null,null,null,"2022-08-03","2022-09-09"]
[{"$f":"A414+1","v":414},0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"2017-12-15","2017-12-15",0.34,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[415,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","2022-03-15","2023-06-23",0.15,"RP-221790","RP-221266 / 1769","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...",38.845999999999997,95,48,null,null,"2022-04-05","2022-09-09"]
[416,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","2022-03-15","2022-12-23",0.1,"RP-220988","RP-221391","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"2022-04-05","2022-09-09"]
[417,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","2022-03-15","2023-06-23",0.1,"RP-221001","RP-221530","Richard Kybett, Huawei","Richard.kybett@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...",38.877000000000002,95,48,null,null,"2022-04-05","2022-09-09"]
[418,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","2019-03-07","2023-03-23",0.2,"RP-221464","RP-221460","Yuexia Song, CATT","songyuexia@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...",38.872,95,48,null,null,"2022-04-05","2022-09-09"]
[419,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-18","RP","2017-12-15","2023-03-23",0.93,"RP-220157","RP-221209","Dominique Everaere","dominique.everaere@ericsson.com","SI under RAN leadership¦TR 37.8XX27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957; 14...","37.890; 37.107",78,40,null,null,"2018-01-08","2022-06-20"]
[420,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","2019-09-19","2022-06-22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"2019-10-08","2022-07-12"]
[421,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","2020-09-17","2022-12-22",0.85,"RP-220461","RP-221330","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"2020-09-25","2022-09-09"]
[422,0,"Rel-18 other Studies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[423,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","2019-12-06","2021-12-10",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"2019-12-06","2021-12-10"]
[424,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","2021-12-13","2023-03-10",0.1,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10",33.869999999999997,94,48,null,null,"2021-12-13","2022-06-04"]
[425,940019,"Study on Application Data Analytics Enablement Service ","FS_ADAES",1,"Rel-18","S6","2021-12-13","2022-09-12",0.55000000000000004,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55","23.700-36",94,48,null,null,"2021-12-13","2022-06-04"]
[426,940073,"Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",1,"Rel-18","S2","2021-12-20","2022-09-12",0.5,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678","23.700-81; 23.700-85",94,48,null,null,"2021-12-19","2022-06-21"]
[427,950021,"Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",1,"Rel-18","S3","2022-03-10","2023-03-10",0.1,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;",33.738,95,48,null,null,"2022-03-10","2022-07-13"]
[428,940075,"Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",0.5,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418","23.700-08",94,48,null,null,"2021-12-19","2022-06-21"]
[429,960033,"Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;",33.857999999999997,96,49,null,null,"2022-06-02","2022-07-13"]
[430,940043,"Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",1,"Rel-18","S5","2021-12-13","2023-03-12",0,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;",28.827999999999999,94,48,null,null,"2021-12-13","2022-01-07"]
[431,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","2021-12-13","2022-09-12",0.3,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30",null,94,48,null,null,"2021-12-13","2022-06-04"]
[432,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","2021-12-20","2022-12-12",0.7,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22","New ; 23.760",84,43,null,null,"2019-05-31","2022-06-04"]
[433,940052,"Study on System Enabler for Service Function Chaining ","FS_SFC",1,"Rel-18","S2","2021-12-20","2022-09-12",0.6,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change","23.700-18",94,48,null,null,"2021-12-19","2022-06-21"]
[434,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"2021-12-19","2022-06-04"]
[435,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","2018-12-13","2022-12-12",0.62,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%-> ",null,82,42,null,null,"2018-12-06","2022-06-04"]
[436,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","2018-06-06","2022-03-11",0.8,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"2018-06-06","2021-09-13"]
[437,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674",33.893999999999998,96,49,null,null,"2022-06-02","2022-08-17"]
[438,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-12",0,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;",33.896000000000001,96,49,null,null,"2022-06-02","2022-07-13"]
[439,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","2023-06-07","2023-06-08",0.1,"CP-221088",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;","29.xxx; 29.831",96,49,null,null,"2022-06-20","2022-07-13"]
[440,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[441,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","2021-12-10","2023-03-12",0,"SP-211441",null,"Cornily Jean-Michel, Orange ","jeanmichel.cornily@orange.com ",null,"28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"2021-12-10","NA"]
[442,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","2021-12-10","2022-12-12",0.3,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30","33.926 ; 33.526",94,48,null,null,"2021-12-10","2022-06-04"]
[443,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","2022-06-02","2022-09-12",0,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"2022-06-02","2022-08-17"]
[444,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","2022-06-02","2023-12-12",0,"SP-220690",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690","28.552; 32.425; 28.554; 28.550 ",96,49,null,null,"2022-06-02","2022-08-17"]
[445,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","2020-03-25","2022-12-12",0.95,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"2019-12-06","2022-06-04"]
[446,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","2022-03-10","2023-03-10",0.1,"SP-220154",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"2022-03-10","2022-06-04"]
[447,930033,"Access control for management service ","MSAC",1,"Rel-18","S5","2020-09-16","2022-12-12",0.81,"SP-210859",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ",null,"28.533; 28.540; 28.622; 28.623; 28.532; ",93,47,null,null,"2021-09-10","NA"]
[448,890016,"   Study on access control for management service ","FS_MNSAC",2,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"2020-09-11","2021-09-13"]
[449,930010,"   Access control for management service ","MSAC",2,"Rel-18","S5","2021-09-10","2022-12-12",0.67,"SP-210859",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18","28.533; 28.540; 28.622; 28.623; 28.532; ",93,47,null,null,"2021-09-10","2022-06-04"]
[450,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","2021-12-10","2022-09-12",0.85,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18","28.531; 28.541 ",94,48,null,null,"2021-12-10","2022-06-04"]
[451,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","2020-09-16","2022-03-11",0.1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18",null,89,45,null,null,"2020-09-10","2021-12-13"]
[452,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","2021-03-18","2022-03-11",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"2021-03-18","2022-06-04"]
[453,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","2021-03-18","2022-03-11",0.6,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60","New ",91,46,null,null,"2021-03-18","2022-06-04"]
[454,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","2021-06-11","2022-09-12",0.35,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35",33.875999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[455,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","2021-12-13","2022-12-12",0.3,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30",28.864000000000001,94,48,null,null,"2021-12-13","2022-06-04"]
[456,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","2021-12-13","2022-12-12",0.4,"SP-211436",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40",28.907,94,48,null,null,"2021-12-13","2022-06-04"]
[457,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","2021-12-13","2023-06-12",0.1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jeanmichel.cornily@orange.com ","7/1/22: 28.913 added;; 4/6/22: 0%->10",28.913,94,48,null,null,"2021-12-13","2022-06-04"]
[458,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","2021-12-13","2022-06-10",0.3,"SP-211442",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30",28.864999999999998,94,48,null,null,"2021-12-13","2022-06-04"]
[459,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","2021-12-13","2023-03-10",0.1,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10",28.908999999999999,94,48,null,null,"2021-12-13","2022-06-04"]
[460,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","2021-12-13","2022-09-12",0.25,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25",28.91,94,48,null,null,"2021-12-13","2022-06-04"]
[461,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","2021-12-13","2022-09-12",0.4,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40",28.911999999999999,94,48,null,null,"2021-12-13","2022-06-04"]
[462,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","2022-03-10","2022-12-12",0.1,"SP-220145",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10",28.831,95,48,null,null,"2022-03-10","2022-06-04"]
[463,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","2022-03-10","2022-09-12",0.15,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15",28.902999999999999,95,48,null,null,"2022-03-10","2022-06-04"]
[464,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","2022-03-10","2022-12-12",0.25,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25",28.832999999999998,95,48,null,null,"2022-03-10","2022-06-04"]
[465,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","2022-03-10","2023-03-10",0.05,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5",28.834,95,48,null,null,"2022-03-10","2022-06-04"]
[466,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","2022-03-10","2022-09-12",0.3,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30",28.835000000000001,95,48,null,null,"2022-03-10","2022-06-04"]
[467,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","2022-03-10","2022-12-12",0.15,"SP-220152",null,"Allwang, Christiane, Nokia ","christiane.allwang@nokia.com ","5/4/22: 28.837 added;; 4/6/22: 0%->15",28.837,95,48,null,null,"2022-03-10","2022-06-04"]
[468,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","2022-03-10","2023-03-10",0.1,"SP-220153",null,"<Wang>, <Chen>, <CMCC ","wangchenyj@chinamobile.com ","5/4/22: 28.830 added;; 4/6/22: 0%->10",28.83,95,48,null,null,"2022-03-10","2022-06-04"]
[469,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","2022-06-02","2022-12-12",0,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ",null,null,96,49,null,null,"2022-06-02","NA"]
[470,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","2021-01-12","2023-03-10",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03",null,90,46,null,null,"2021-01-12","2022-06-21"]
[471,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","2021-06-11","2023-03-10",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03",null,92,47,null,null,"2021-06-11","2022-06-21"]
[472,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","2021-06-11","2023-03-10",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03",null,92,47,null,null,"2021-06-11","2022-06-21"]
[473,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","2022-09-12","2023-03-12",0,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ",null,"32.156; 32.160 ",null,null,null,null,"2022-09-11","NA"]
[474,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","2022-09-12","2023-06-12",0,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ",null,null,null,null,null,null,"2022-09-11","NA"]
[475,970032,"Study on Time Sensitive Networking Charging ","FS_TSNCH",1,"Rel-18","S5","2022-09-12","2023-06-12",0,"SP-220895",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ",null,null,null,null,null,null,"2022-09-11","NA"]
[476,0,"Rel-18 other aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[477,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"2021-03-12","2023-03-10",0,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[{"$f":"A478+1","v":478},920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","2021-03-12","2023-03-10",0.05,"SP-210830",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5","33.128;33.127;33.126;33.108;33.107 ",92,47,null,null,"2021-06-11","2022-06-04"]
[479,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"2019-03-07","2019-03-07",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"2022-03-13","NA"]
[480,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[481,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[482,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"2019-03-07","2019-12-12",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[483,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[484,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"2019-05-31","2020-06-26"]
[485,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","2019-06-06","2021-03-12",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"2019-05-31","2021-03-19"]
[486,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"2020-06-12","2022-06-10",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","NA"]
[487,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","2022-03-12"]
[488,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"2021-03-18","2021-09-10"]
[489,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"2021-03-18","2022-06-20"]
[490,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[491,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"2021-03-18","2022-06-04"]
[492,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[493,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"2020-06-25","2022-06-04"]
[494,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[495,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","2018-06-06","2019-06-12",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"2018-06-06","2019-09-13"]
[496,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[497,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","2021-03-18","2022-06-10",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"2021-03-18","2022-06-04"]
[498,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","2019-03-07","2021-06-11",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"2018-12-06","2021-09-13"]
[499,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","2019-06-06","2020-03-12",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,null,null,"2019-05-31","2022-03-22"]
[500,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","2020-12-04","2021-12-10",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"2020-12-04","2022-03-12"]
[501,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[502,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2019-12-06"]
[503,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-06-28"]
[504,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-09-13"]
[505,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"2020-09-25","2022-06-04"]
[506,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"2019-05-31","2020-06-25"]
[507,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"2019-09-13","NA"]
[508,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"2018-09-06","2019-09-13"]
[509,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","2019-09-19","2019-12-12",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[510,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"2019-05-31","2020-12-05"]
[511,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","2020-03-25","2021-09-08",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"2019-05-31","2021-12-10"]
[512,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"2021-03-18","2021-06-11"]
[513,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"2021-03-18","2022-06-20"]
[514,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"2021-03-18","2022-03-12"]
[515,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"2021-03-18","2022-06-20"]
[516,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"2021-01-06","2021-04-07"]
[517,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[518,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[519,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-09-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...",null,90,46,null,null,"2021-01-06","2022-09-09"]
[520,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"2019-05-31","NA"]
[521,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","2018-09-06","2019-09-13",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"2018-09-06","2019-12-06"]
[522,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"2019-05-31","2019-12-06"]
[523,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"2014-08-29","2014-08-29"]
[524,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"2018-09-06","2019-12-13",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[525,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","2018-09-06","2019-12-13",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[526,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"2019-05-31","2019-12-06"]
[527,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","2018-12-06","2020-12-15",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"2018-12-06","2020-12-05"]
[528,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","2018-12-06","2021-03-12",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"2018-12-06","2021-03-21"]
[529,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"2020-12-04","2021-03-21"]
[530,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","2020-12-04","2021-06-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"2020-12-04","2021-07-02"]
[531,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"2021-06-11","2022-03-12"]
[532,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"2021-06-11","2022-03-12"]
[533,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",0.9,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90",33.853999999999999,88,45,null,null,"2020-06-25","2021-12-13"]
[534,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"2018-09-06","2022-03-11",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"2018-09-06","NA"]
[535,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","2018-09-06","2018-12-14",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"2018-09-06","2018-12-04"]
[536,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"2020-12-03","2021-12-10"]
[537,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"2021-03-18","2021-06-11"]
[538,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[539,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"2021-03-18","2022-03-12"]
[540,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[541,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","2021-06-11","2022-03-11",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"2021-06-11","2022-03-12"]
[{"$f":"A542+1","v":542},0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[543,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","NA"]
[544,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","2018-06-06","2018-09-14",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[545,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","2018-06-06","2020-06-25",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"2018-06-06","2020-06-26"]
[546,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","2019-12-06","2021-09-08",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","2021-12-10"]
[547,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2021-06-11"]
[548,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-06-04"]
[549,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","2020-09-16","2021-09-10",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[550,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[551,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","2021-09-13","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"2020-09-12","2022-06-04"]
[552,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"2019-12-16","2022-12-23",0.59,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"2020-01-14","2022-04-05"]
[553,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-213691","RP-221168 / 1745","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"2020-01-14","2022-06-20"]
[554,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R2","2019-12-16","2022-12-22",0.35,"RP-213691","RP-221168 / 1745","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[555,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.05,"RP-221241",null,"Qualcomm ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[556,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2021-06-15","2022-06-22",0.99,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"2021-07-02","NA"]
[557,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","2021-06-15","2022-06-22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[558,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"2021-09-10","2022-03-12"]
[559,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"2022-03-12","2022-06-20"]
[560,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[561,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[562,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-06-04"]
[563,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","2019-03-07","2021-03-12",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"2019-03-14","2021-03-21"]
[564,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2019-12-16","2021-06-15",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"2020-01-14","2021-07-02"]
[565,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[566,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"2019-09-13","2021-06-11"]
[567,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","2020-06-12","2021-06-11",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"2020-06-25","2021-06-11"]
[568,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","2021-06-11","2021-06-20",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-03-24"]
[569,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"2020-12-03","NA"]
[570,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"2020-12-03","2021-09-13"]
[571,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"2021-03-18","2021-09-10"]
[572,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[573,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[574,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[575,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[576,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"2020-01-14","2022-04-05"]
[577,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","2021-12-21","2022-03-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[578,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","2019-03-07","2022-09-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[579,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"2019-12-16","2022-12-23",0.77,"RP-212594",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594",null,86,44,null,null,"2020-01-14","2021-09-29"]
[580,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-212594","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[581,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","2019-12-16","2022-12-22",0.7,"RP-212594","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[582,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.15,"RP-221238",null,"Qualcomm ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[583,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"2019-12-16","2023-06-23",0.77,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"2020-01-14","2022-04-05"]
[584,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-220152","RP-221198","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[585,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","2020-06-15","2022-12-22",0.85,"RP-220152","RP-221198","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...",null,86,44,null,null,"2020-09-25","2022-09-09"]
[586,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-23",0.05,"RP-221416",null,"Nokia ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[587,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[588,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"2019-12-16","2022-09-23",0.95,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"2020-01-14","2021-01-06"]
[589,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[590,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[591,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-23",0.05,"RP-221448",null,"CATT ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[592,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","2019-12-16","2020-09-15",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[593,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","2019-06-06","2020-06-12",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"2019-05-31","2022-03-22"]
[594,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-02-10"]
[595,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-06-11"]
[596,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"2021-03-18","2021-06-11"]
[597,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[598,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[599,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"2019-09-19","2022-03-12",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"2021-03-18","NA"]
[600,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"2019-09-13","2021-03-19"]
[601,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","2021-03-18","2021-09-08",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"2021-03-18","2021-12-10"]
[602,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"2021-06-11","2022-03-12"]
[603,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","2021-06-11","2022-03-12",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"2021-06-11","2022-03-22"]
[604,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","2021-06-11","2022-03-12",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"2021-06-11","2022-06-04"]
[605,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A606+1","v":606},920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","2021-06-15","2022-12-22",0.8,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"2021-07-02","2021-09-29"]
[607,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"2021-07-02","2022-03-22"]
[608,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"2021-07-02","2022-03-22"]
[609,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","2021-12-13","2022-12-22",0.52,"RP-213229","RP-221490","Chunying GU, Huawei","guchunying@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[610,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"2019-12-16","2022-12-23",0.84,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"2020-01-14","2021-09-29"]
[611,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[612,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_FeMIMO-Perf",2,"Rel-17","R1","2019-12-16","2022-12-22",0.85,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[613,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.05,"RP-221401",null,"Samsung ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[614,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"2020-01-14","2021-07-02"]
[615,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[616,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"2019-12-16","2022-12-23",0.93,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"2020-01-14","2022-07-12"]
[617,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[618,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100",null,86,44,null,null,"2020-01-14","2022-09-09"]
[619,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-22",0.99,"RP-213291","RP-221452","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...",null,88,45,null,null,"2020-07-28","2022-09-09"]
[620,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.03,"RP-221545",null,"MediaTek ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[621,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"2019-12-16","2022-09-22",1,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"2020-01-14","2020-07-28"]
[622,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[623,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[624,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"2019-03-11","2022-09-22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"2020-01-14","2022-07-12"]
[625,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[626,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[627,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","2019-03-11","2021-12-10",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"2019-03-14","2022-03-12"]
[628,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"2019-12-16","2022-03-09",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"2020-01-14","2022-01-21"]
[629,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-09",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[630,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"2020-09-15","2022-12-23",0.84,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126...",null,89,45,null,null,"2020-10-11","2022-07-12"]
[631,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","2021-12-14","2022-06-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"2022-03-22","2022-06-20"]
[632,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"2020-10-11","2022-09-09"]
[633,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.05,"RP-221299",null,"ChinaTelecom ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[634,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"2020-09-15","2023-03-23",0.82,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"2020-10-11","2022-01-06"]
[635,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[636,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Noki...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[637,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","2022-06-15","2023-03-23",0.05,"RP-221240",null,"Qualcomm ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[638,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"2020-10-11","2022-01-06"]
[639,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[640,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[641,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-06-23",0.83,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"2020-10-11","2021-04-07"]
[642,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[643,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[644,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-23",0.23,"RP-221359",null,"CMCC ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[645,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366...",38.850999999999999,89,45,null,null,"2020-10-11","2022-07-12"]
[646,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[647,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[648,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"2020-10-11","2021-04-07"]
[649,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[650,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[651,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"2020-10-11","2022-01-06"]
[652,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporati...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[653,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"2020-10-11","2022-09-09"]
[654,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"2020-09-15","2022-12-23",0.88,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"2020-10-11","2022-04-05"]
[655,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[656,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[657,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.11,"RP-221848",null,"Huawei ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[658,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","2021-12-13","2022-09-22",0.99,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"2022-01-06","2022-04-05"]
[659,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","2021-12-13","2022-03-12",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[660,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","2021-12-13","2022-03-12",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[661,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",1,"RP-221159",null,"ChinaUnicom ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[662,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[663,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"2020-01-14","2022-04-05"]
[664,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[665,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[666,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"2019-12-06","2022-06-21"]
[667,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","2019-09-19","2020-09-14",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"2019-09-13","2020-09-13"]
[668,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","2020-06-12","2021-12-10",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"2020-06-26","2021-12-13"]
[669,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A670+1","v":670},870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"2019-05-31","2021-06-11"]
[671,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","2018-09-14","2020-03-12",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"2018-09-14","2020-12-05"]
[672,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"2020-06-25","2022-03-12"]
[673,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","2019-09-19","2020-03-12",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"2019-09-13","2020-03-26"]
[674,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"2019-03-07","2022-06-10",0.89,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[675,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"2019-03-14","2021-03-19"]
[676,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","2020-12-03","2021-09-10",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-06-04"]
[677,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","2021-06-11","2022-03-11",0.97,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"2021-06-11","2022-06-04"]
[678,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"2021-06-11","2022-06-20"]
[679,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"2021-06-11","2022-06-20"]
[680,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","2021-06-11","2022-03-12",0,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"2022-06-20","NA"]
[681,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[682,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","2019-09-02","2019-12-12",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[683,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"2021-12-10","2022-06-04"]
[684,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","2019-12-16","2023-06-23",0.67,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"2020-01-14","2022-04-05"]
[685,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[686,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","2022-03-15","2023-06-23",0.09,"RP-220423","RP-221497","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[687,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"2020-09-11","2021-03-21"]
[688,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"2020-09-11","2021-06-11"]
[689,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"2021-06-11","2022-06-04"]
[690,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"2019-12-06","2022-03-11",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"2019-12-06","2020-09-13"]
[691,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"2019-12-06","2021-06-11"]
[692,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","2020-06-17","2022-03-11",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"2020-09-25","2022-06-04"]
[693,880020,"Protocol enhancements for Mission Critical Services ","MCProtoc17",1,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-202193",null,"AXELL, Jörgen ","jorgen.axell@ericsson.com ","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/12/21: 70%-> ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[694,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","2018-12-13","2022-03-11",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"2018-12-07","2022-06-04"]
[695,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","2020-09-16","2021-09-08",0.65,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"2020-09-25","2021-09-13"]
[696,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[697,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"2019-03-07","2022-06-07",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222, 23.558",86,44,null,null,"2019-12-06","2020-03-26"]
[698,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","2019-03-07","2019-12-05",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-03-26"]
[699,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222, 23.558",86,44,null,null,"2019-12-06","2021-06-11"]
[700,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"2020-12-05","2021-06-11"]
[701,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","2020-12-07","2022-03-11",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"2020-12-05","2022-06-04"]
[702,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","2020-12-07","2022-03-11",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"2020-12-05","2022-03-12"]
[703,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"2022-06-20","2022-08-03"]
[704,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-12-05"]
[705,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[706,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[707,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"2021-03-18","2021-09-10"]
[708,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"2021-03-18","2022-06-04"]
[709,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"2021-03-18","2022-03-12"]
[710,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"2021-03-18","2022-06-04"]
[711,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","2021-06-11","2021-12-10",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"2021-06-11","2022-03-12"]
[712,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","2021-06-11","2022-03-11",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"2021-06-11","2022-06-04"]
[713,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"2020-06-25","2022-03-12"]
[714,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"2021-12-10","2022-06-04"]
[715,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"2021-09-10","2022-03-22"]
[716,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","2020-06-25","2021-12-10",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"2020-06-26","2022-06-21"]
[717,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"2021-09-10","2022-06-04"]
[718,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","2020-03-25","2021-09-08",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"2019-12-06","2021-09-13"]
[719,0,"Rel-17 Slicing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[720,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"2021-06-11","2023-03-12",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"2021-06-11","2022-04-28"]
[721,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"2021-06-11","2022-06-20"]
[722,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","2021-06-11","2023-03-12",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[723,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","2021-06-11","2022-03-12",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"2021-06-11","2022-03-12"]
[724,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"2021-06-11","2022-03-12"]
[725,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"2019-09-19","2022-12-22",0.93,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[726,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"2019-09-13","2021-03-19"]
[727,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-22"]
[728,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","2021-03-18","2022-12-22",0.9,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"2021-03-18","2021-10-01"]
[729,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[730,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"2021-03-18","2022-06-04"]
[731,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"2021-03-18","2022-03-12"]
[732,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","2022-03-15","2022-12-22",0.5,"RP-220621","RP-221367","Luting Kong, Xiaozhong Chen, CMCC, CATT","kongluting@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[733,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","2019-03-07","2022-09-22",0.85,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"2021-04-07","2022-07-12"]
[{"$f":"A734+1","v":734},911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","2021-03-12","2022-06-22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[735,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",0.12,"RP-221364",null,"CMCC ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[736,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","2022-06-03","2022-06-20",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-03","2022-06-04"]
[737,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-20","2022-08-03"]
[738,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","2019-12-06","2021-12-10",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"2019-12-06","2021-12-13"]
[739,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","2022-03-10","2022-03-12",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"2022-03-10","2022-03-12"]
[740,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[741,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","NA"]
[742,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","2019-03-07","2019-09-06",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"2019-03-14","2019-12-06"]
[743,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","2019-12-06"]
[744,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"2018-12-06","2021-09-13"]
[745,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[746,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"2021-03-18","2021-09-10"]
[747,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[748,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[749,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"2020-12-04","2021-09-13"]
[750,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"2019-12-09","2022-09-23",0.82,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"2020-06-10","2022-01-06"]
[751,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","2019-12-09","2022-03-22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"2020-06-10","2022-06-20"]
[752,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","2022-03-15","2022-09-23",0.05,"RP-221193","RP-221194","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193",null,95,48,null,null,"2022-04-05","2022-07-12"]
[753,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","2021-12-13","2023-06-24",0.02,"RP-220955",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955",null,94,48,null,null,"2022-01-06","2022-04-05"]
[754,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","2021-12-13","2022-12-23",0.05,"RP-220955","RP-221273","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[755,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","2022-03-15","2023-06-24",0,"RP-220955","RP-221273","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...",null,95,48,null,null,"2022-06-04","2022-09-09"]
[756,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[757,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"2019-06-06","2021-12-12",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[758,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","2019-06-06","2020-12-11",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[759,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"2020-09-10","2022-03-12"]
[760,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","2021-09-10","2021-12-12",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[761,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"2020-09-11","2021-06-11"]
[762,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"2020-09-11","2021-12-13"]
[763,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"2021-09-10","NA"]
[764,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"2021-09-10","2022-06-04"]
[765,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"2021-09-10","2022-03-12"]
[766,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","2021-09-29","2022-03-12",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"2021-09-29","NA"]
[767,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"2021-09-29","2022-03-12"]
[768,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","2021-09-29","2022-03-12",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"2021-09-29","2022-06-04"]
[769,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"2020-09-16","2022-06-10",0.95,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"2020-09-25","2021-06-11"]
[770,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","2020-09-16","2022-06-10",0.95,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22",33.866999999999997,89,45,null,null,"2020-09-25","2022-03-12"]
[771,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","2021-09-10","2022-06-10",0.95,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[772,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"2021-03-18","2021-12-13"]
[773,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-213669",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case",null,94,48,null,null,"2022-01-06","NA"]
[774,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-213669",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"2022-01-06","2022-06-04"]
[775,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"2021-03-18","2021-06-11"]
[776,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","2021-06-12","2021-06-12",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"2021-08-12","2022-03-11"]
[777,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"2021-03-18","2022-03-12",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2021-09-13"]
[778,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2022-03-12"]
[779,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"2021-12-10","2022-06-04"]
[780,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","2021-12-10","2022-03-12",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"2021-12-10","2022-03-12"]
[781,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"2021-12-10","2022-06-04"]
[782,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[783,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[784,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"2022-03-10","2022-06-04"]
[785,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","2020-12-07","2020-12-18",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-05","2020-12-05"]
[786,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[787,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"2019-03-07","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[788,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","2019-05-09","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[789,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","2019-03-07","2019-03-07",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"2020-12-05","2021-03-21"]
[790,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","2019-03-07","2019-03-07",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ",null,null,null,null,null,null,"2022-09-07","NA"]
[791,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","2019-03-07","2019-03-07",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ",null,null,null,null,null,null,"2022-09-07","NA"]
[792,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"2020-12-04","2021-12-13"]
[793,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"2020-12-04","2021-03-21"]
[794,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","2020-12-04","2021-06-15",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"2020-12-04","2021-09-13"]
[795,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"2021-06-11","2022-06-04"]
[796,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100",29.548999999999999,92,47,null,null,"2021-06-11","2022-06-04"]
[797,940018,"   Security enhancement for SEAL ","eSEAL",2,"Rel-17","S3","2021-12-10","2021-12-12",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100",33.433999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[{"$f":"A798+1","v":798},900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[799,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"2019-06-26","2021-03-19"]
[800,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","2020-12-03","2021-06-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"2020-12-03","2021-09-13"]
[801,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[802,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"2021-03-18","2022-06-04"]
[803,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"2021-03-18","2021-12-13"]
[804,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"2021-03-18","2022-03-12"]
[805,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"2020-12-03","NA"]
[806,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","2019-06-06","2020-12-15",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"2019-05-31","2021-03-19"]
[807,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","2020-09-16","2022-03-11",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22",33.866,89,45,null,null,"2020-09-10","2022-03-12"]
[808,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[809,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"2021-03-19","2021-06-11"]
[810,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"2021-03-19","2022-06-04"]
[811,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[812,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[813,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"2019-03-07","2022-06-10",0.99,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"2020-12-03","NA"]
[814,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"2019-03-14","2021-12-10"]
[815,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-12"]
[816,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"2021-03-18","2022-07-13"]
[817,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"2021-03-18","2022-06-04"]
[818,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100",29.556999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[819,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90",29.559000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[820,920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"2021-03-18","2022-06-04"]
[821,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"2020-09-10","2022-06-21"]
[822,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[823,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ",33.847000000000001,88,45,null,null,"2020-06-25","2022-06-04"]
[824,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","2021-09-10","2022-06-10",0.92,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92","New ; 33.503",93,47,null,null,"2021-09-10","2022-06-04"]
[825,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"2021-04-07","2021-09-29"]
[826,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","2021-03-12","2022-03-22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, h...",38.350999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[827,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[828,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"2019-09-13","2020-06-26"]
[829,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","2019-09-19","2020-06-12",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"2019-09-13","2022-03-12"]
[830,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"2020-09-11","2020-09-25"]
[831,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100",24.501000000000001,89,45,null,null,"2020-09-11","2022-03-12"]
[832,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"2020-09-11","2022-03-12"]
[833,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"2020-09-11","2022-03-12"]
[834,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","2020-09-17","2022-12-23",0.75,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"2020-09-25","2021-09-29"]
[835,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","2020-09-17","2022-03-22",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[836,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.05,"RP-221300",null,"ChinaTelecom ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[837,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"2017-12-15","2022-03-11",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"2019-05-31","NA"]
[838,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","2017-12-15","2019-09-12",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"2017-12-15","2020-08-17"]
[839,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","2019-09-19","2020-06-12",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,null,null,"2019-09-13","2022-03-22"]
[840,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"2019-05-31","2019-12-06"]
[841,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","2020-03-25","2021-06-11",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"2020-03-25","2022-03-12"]
[842,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"2020-06-26","NA"]
[843,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[844,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[845,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[846,890011,"Mission critical security enhancements phase 2 ","MCXSec2",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200879",null,"Woodward, Tim, Motorola Solutions, Inc, ","tim.woodward@motorolasolutions.com ","; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 80%->82; 13/12/21: 82%->100",33.18,89,45,null,null,"2020-09-11","2021-12-13"]
[847,890070,"PAP/CHAP protocols usage in 5GS ","PAP_CHAP",1,"Rel-17","ct","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 29.561 ; 12/3/22: 99%->100",null,89,45,null,null,"2020-09-25","2022-03-12"]
[848,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[849,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","2020-09-16","2021-03-12",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[850,890001,"Service-based support for SMS in 5GC ","SMS_SBI",1,"Rel-17",null,"2020-09-16","2022-03-12",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","25/9/20: WID:CP-202028->CP-202242; 10/9/21: WID:CP-202242->CP-212023",null,89,45,null,null,"2020-09-11","2021-09-10"]
[851,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","2020-09-16","2022-03-12",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"2020-09-11","2022-03-12"]
[852,890029,"   CT4 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35; 13/9/21: FCD:Wed 08/09/->03/22; 13/9/21: 35%->40; 1/10/21: 23.540 added;; 13/12/21: 40%->45; 12/3/22: 45%->65; 22/3/22: 29.577 added;; 22/3/22: 29.579 added;; 22/3/22:...","29.503; 29.540; 29.571; 23.540; 29.577; 29.579; 29.578",89,45,null,null,"2020-09-11","2022-08-03"]
[853,840048,"Enhanced Relays for Energy eFficiency and Extensive Coverage ","REFEC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[854,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100",22.866,81,41,null,null,"2018-09-06","2019-12-06"]
[855,840034,"   Stage 1 of REFEC","REFEC",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ","13/9/19: 0%->90; 6/12/19: 90%->100",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-06"]
[856,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[857,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","2018-06-06","2019-03-14",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100",22.841999999999999,80,41,null,null,"2018-06-06","2019-05-31"]
[858,840030,"   Stage 1 of NCIS","NCIS",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191039",null,"Ning YANG, oppo ","yangning@oppo.com ","13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[859,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","2019-06-06","2021-06-11",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"2019-05-31","2021-06-11"]
[860,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","2020-09-16","2021-06-11",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"2020-09-10","2021-06-11"]
[861,880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"2019-09-02","2020-12-11",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[{"$f":"A862+1","v":862},850041,"   Stage 1 of MuDE","MuDE",2,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[863,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","2020-06-25","2020-12-11",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"2020-06-26","2021-06-11"]
[864,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"2020-06-26","2021-09-10"]
[865,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[866,880014,"   CT4 aspects of BEPoP","BEPoP",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 45%->55; 13/12/21: 55%->80; 12/3/22: 80%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[867,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","2020-06-25","2021-09-10",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"2020-06-25","2021-12-13"]
[868,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100",23.18,84,43,null,null,"2019-05-31","2020-12-05"]
[869,840016,"Stopped - Supporting Flexible Local Area Data Network ","FLADN",1,"Rel-17","S2","2019-06-06","2020-09-11",1,"SP-190563",null,"LG Electronics, Hyunsook Kim ","hyuns.kim@lge.com ","21/1/22: stopped at 0%; 21/1/22: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2022-01-21"]
[870,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","2018-12-13","2022-03-11",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"2019-03-14","2022-03-12"]
[871,860012,"Handsets Featuring Non-Traditional Earpieces","HaNTE",1,"Rel-17","S4","2019-12-06","2022-03-11",1,"SP-190989",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com","25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11 ","26.131; 26.132; 26.801",86,44,null,null,"2019-12-06","2022-03-12"]
[872,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-03-12"]
[873,920008,"   Stage 2 of EVEX","EVEX",2,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-06-04"]
[874,960021,"   Stage 3 (CT3) of EVEX","EVEX",2,"Rel-17","C3","2022-06-01","2022-06-10",1,"CP-221104",null,"Waqar Zia, Qualcomm Incorporated","wzia@qti.qualcomm.com",null,"29.522, 29.517, 29.591",96,49,null,null,"2022-05-30","NA"]
[875,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","2021-06-11","2021-09-08",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"2021-06-11","2021-12-13"]
[876,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"2021-06-11","2022-03-12"]
[877,920011,"8K Television over 5G ","8K_TV_5G",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210381",null,"Thomas Stockhammer ","tsto@qti.qualcomm.com ","; 13/9/21: 0%->40; 13/12/21: 40%->60; 12/3/22: 60%->100","26.955;26.925;26.511;26.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[878,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","2019-03-07","2019-03-21",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"2017-12-15","2019-03-14"]
[879,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[880,880049,"Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON",1,"Rel-17",null,"2019-09-02","2022-03-11",1,"CP-210148",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148",22.260999999999999,85,43,null,null,"2019-09-13","2021-06-13"]
[881,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","2019-09-02","2021-06-18",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100",22.260999999999999,85,43,null,null,"2019-09-13","2022-03-11"]
[882,880022,"   Stage 3 (CT1) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50; 13/9/21: 50%->70; 13/9/21: FCD:Fri 18/06/->03/22; 13/12/21: 70%->92; 12/3/22: 92%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[883,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"2020-06-26","2022-03-12"]
[884,920061,"   Stage 3 (CT6) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C6","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/9/21: 0%->70; 13/9/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100; 4/6/22: 100 ",null,92,47,null,null,"2020-06-26","2022-06-04"]
[885,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"2018-06-06","2022-03-12",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2020-12-05"]
[886,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","2019-09-19","2021-12-10",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2021-12-13"]
[887,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"2021-03-18","2022-03-12"]
[888,910047,"   Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",2,"Rel-17","S3","2018-06-06","2022-03-12",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 24/3/22: 0%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2021-03-19","2022-03-24"]
[889,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"2019-03-07","2022-03-12",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"2019-09-13","NA"]
[890,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[891,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","2019-09-13","2019-12-12",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"2019-09-13","2019-12-06"]
[892,920062,"   Stage 2 of MINT","MINT",2,"Rel-17","S2","2021-08-12","2021-12-10",1,"SP-210582",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","13/9/21: 0%->50; 10/12/21: 50%->90; 12/3/22: 90%->98; 4/6/22: 98%->100","23.501; 23.502 ",92,47,null,null,"2021-08-12","2022-06-04"]
[893,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","2020-12-07","2021-03-12",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"2020-12-05","2021-09-13"]
[894,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","2021-09-29","2022-03-12",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","NA"]
[895,930049,"      CT1 aspects of MINT","MINT",3,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 13/12/21: 0%->50; 12/3/22: 50%->85; 4/6/22: 85%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[896,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-20"]
[897,930048,"      CT6 aspects of MINT","MINT",3,"Rel-17","C6","2021-09-29","2022-03-12",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->100; 4/6/22: 100%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[898,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","2022-03-10","2022-03-12",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100",33.500999999999998,95,48,null,null,"2022-03-10","2022-03-22"]
[899,860008,"IMS emergency support for Stand-alone Non-Public Network (SNPN)","IESNPN",1,"Rel-17","S1","2019-12-06","2019-12-13",1,"SP-191038",null,"Wong, Curt; ","curt.wong@charter.com ","6/12/19: 0%->100","22.101; 22.261; 22.228 ",86,44,null,null,"2019-12-06","2019-12-06"]
[900,870023,"Management of non-public networks (NPN)","OAM_NPN",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200189",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21; 13/9/21: 50%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->100","28.541; 28.531; 28.533; 28.552; 28.554 ",87,44,null,null,"2019-12-06","2022-03-12"]
[901,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","2019-12-06","2021-06-11",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"2019-12-06","2021-12-13"]
[902,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","2020-03-25","2022-06-10",0.99,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"2020-03-25","2020-06-26"]
[903,890013,"   eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) ","SCAS_5G_NSSAAF",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200720",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->100","33.926; 33.326",89,45,null,null,"2020-09-11","2021-09-13"]
[904,870017,"   eSCAS_5G for Non-3GPP InterWorking Function","SCAS_5G_N3IWF",2,"Rel-17","S3","2020-03-25","2021-12-10",1,"SP-200146",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->100","33.926; 33.520",87,44,null,null,"2020-03-25","2021-12-13"]
[905,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","22.521; 33.926",87,44,null,null,"2020-03-25","2022-06-04"]
[906,870019,"   eSCAS_5G for Service Communication Proxy","SCAS_5G_SECOP",2,"Rel-17","S3","2020-03-25","2022-06-10",0.95,"SP-200148",null,"Wei Lu, Nokia","wei.lu@nokia-sbell.com","26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 70%->95; 12/3/22: 95%->95; 12/3/22: FCD:10/12/2021->06/22","33.522; 33.926",87,44,null,null,"2020-03-25","2022-03-12"]
[907,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"2020-06-25","2021-09-13"]
[908,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2020-06-28"]
[909,870016,"   Stage 2 aspects of enh3MCPTT","enh3MCPTT",2,"Rel-17","S6","2020-03-25","2021-06-15",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-06-11"]
[910,900039,"   Stage 3 aspects of enh3MCPTT","enh3MCPTT-CT",2,"Rel-17","C1","2020-09-14","2021-09-08",1,"CP-202188",null,null,null,"; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48; 13/12/21: 48%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-12-13"]
[911,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","2019-06-06","2021-12-10",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"2019-05-31","2022-03-12"]
[912,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","2018-12-13","2021-03-12",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"2018-12-06","2021-06-11"]
[913,890012,"Enhancements to User Plane Integrity Protection Support in 5GS ","eUPIP_SEC",1,"Rel-17","S3","2020-09-16","2021-03-12",1,"SP-200719",null,"Anand Palanigounder, Qualcomm Incorporated ","apg@qti.qualcomm.com ","; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100",33.500999999999998,89,45,null,null,"2020-09-11","2021-03-19"]
[914,950040,"Non-Seamless WLAN offload in 5GS ","NSWO_5G",1,"Rel-17","S3","2021-05-25","2022-03-12",0.99,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ",null,33.500999999999998,95,48,null,null,"2021-12-10","NA"]
[915,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","2021-05-25","2021-09-08",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"2021-05-25","2022-06-04"]
[916,940011,"   Security aspects of NSWO","NSWO_5G",2,"Rel-17","S3","2021-12-10","2022-03-12",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ","; 12/3/22: FCD:12/12/2021->3/22; 12/3/22: 0%->100",33.500999999999998,94,48,null,null,"2021-12-10","2022-03-12"]
[917,950041,"   CT1 aspects of NSWO","NSWO_5G",2,"Rel-17","C1","2022-03-10","2022-03-12",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 22/3/22: 0%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-03-22"]
[918,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[919,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","2022-03-10","2022-03-12",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[920,860025,"Lawful Interception Rel-17 ","LI17",1,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[921,850047,"(Small) Technical Enhancements and Improvements for Rel-17","TEI17",1,"Rel-17",null,"2020-03-11","2022-03-12",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,85,43,null,null,"2015-06-15","2015-06-15"]
[922,940047,"   IMS Optimization for HSS Group ID in an SBA environment (St. 2)","TEI17_IMSGID",2,"Rel-17","S2","2020-03-11","2022-03-11",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[923,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[924,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","2020-03-11","2022-03-11",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100",24.228999999999999,94,48,null,null,"2021-12-10","2022-03-12"]
[925,910044,"   Same PCF Selection For AMF and SMF ","TEI17_SPSFAS",2,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ",null,null,88,45,null,null,"2020-06-25","NA"]
[{"$f":"A926+1","v":926},880016,"      Stage 2 for TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ","23.501, 23.502 ; 19/3/21: 0%->100",null,88,45,null,null,"2020-06-25","2021-03-19"]
[927,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[928,910045,"         CT3 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C3","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184; 13/9/21: 98%->100",29.513000000000002,91,46,null,null,"2021-03-18","2021-09-13"]
[929,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"2021-03-18","2021-09-13"]
[930,930036,"   System enhancement for Redundant PDU Session ","TEI17_SE_RPS",2,"Rel-17",null,"2020-03-25","2022-03-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501, 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[931,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501, 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[932,930001,"      CT aspects of TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","ct","2021-09-10","2022-03-12",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ",null,"24.501; 24.526; 27.007; 29.513; 29.525; 29.561; 29.502 ",93,47,null,null,"2021-09-10","NA"]
[933,930037,"         CT1 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C1","2021-09-10","2022-03-12",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","24.501; 24.526; 27.007",93,47,null,null,"2021-09-10","2021-12-13"]
[934,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"2021-09-10","2022-03-12"]
[935,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","2021-09-10","2022-03-12",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100",29.501999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[936,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"2020-03-25","2021-09-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[937,870004,"      Stage 2 for TEI17_SAPES","TEI17_SAPES",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ","19/3/21: 0%->100","23.228; 23.167",87,44,null,null,"2020-06-10","2021-03-19"]
[938,910020,"      CT aspects on TEI17_SAPES","TEI17_SAPES",3,"Rel-17","ct","2021-03-19","2021-09-12",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ",null,"24.229; 29.165 ",91,46,null,null,"2021-03-19","NA"]
[939,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","2021-03-19","2021-09-12",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[940,910080,"         CT3 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C3","2021-03-19","2021-09-12",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[941,910081,"   Dynamically Changing AM Policies in the 5GC ","TEI17_DCAMP",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,null,null,87,44,null,null,"2020-06-10","NA"]
[942,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"2020-06-10","2021-03-19"]
[943,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"2021-03-19","2021-09-10"]
[944,910082,"         CT3 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: 0%->30; 13/9/21: 30%->50; 13/12/21: 50%->75; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[945,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[946,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"2020-06-10","2021-03-19"]
[947,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"2020-06-10","NA"]
[948,870007,"      Stage 2 for TEI17_GEM ","TEI17_GEM",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com","11/6/21: 0%->100",23.681999999999999,87,44,null,null,"2020-06-10","2021-06-11"]
[949,910010,"      CT aspects on TEI17_GEM ","TEI17_GEM",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: WID:CP-210185->CP-211195; 10/9/21: WID:CP-211195->CP-212165","29.122 29.336 ",91,46,null,null,"2021-03-19","2021-09-10"]
[950,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[951,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[952,920041,"   Support of different slices over different Non 3GPP access ","TEI17_N3SLICE",2,"Rel-17",null,"2020-03-11","2021-06-20",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[953,870008,"      Stage 2 for TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[954,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","2021-06-11","2021-06-20",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-10-01"]
[955,920001,"      CT4 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C4","2021-06-11","2021-06-20",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-06-11"]
[956,910087,"   N7/N40 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",2,"Rel-17",null,"2020-03-11","2021-09-12",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[957,870009,"      Stage 2 for TEI17_NIESGU","TEI17_NIESGU",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ","11/6/21: 0%->100","23.060; 23.401; 23.503; 23.203 ",87,44,null,null,"2020-06-10","2021-06-11"]
[958,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[959,910011,"      CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194; 13/9/21: 90%->100","29.512; 29.513 ",91,46,null,null,"2021-03-19","2021-09-13"]
[960,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","2021-03-19","2021-09-12",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"2021-03-19","2021-09-13"]
[961,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","2021-12-10","2022-03-22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"2022-04-21","NA"]
[962,880019,"Stage-3 5GS NAS protocol development 17 ","5GProtoc17",1,"Rel-17","C1","2020-06-25","2022-03-11",0.87,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","NA"]
[963,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[964,880045,"   Stage-3 5GS NAS protocol development 17 non-IETF aspects","5GProtoc17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",0.7,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","1/10/21: 0%->70","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","2021-10-01"]
[965,880021,"Stage-3 SAE Protocol Development ","SAES17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[966,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"2020-06-26","2022-03-12"]
[967,880047,"   Stage-3 SAE Protocol Development CSFB aspects","SAES17-CSFB",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[968,880048,"   Stage-3 SAE Protocol Development non 3GPP aspects","SAES17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[969,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"2020-06-26","2021-03-21"]
[970,880023,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 20%->40; 13/9/21: 40%->60; 13/12/21: 60%->80; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 80%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[971,911035,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 0%->60; 13/9/21: 60%->70; 13/12/21: 70%->85; 12/3/22: 85%->100; 12/3/22: FCD:10/09/2021->3/22","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[972,880032,"Packet Flow Description (PFD) management enhancement ","pfdManEnh",1,"Rel-17","C3","2020-06-25","2021-06-11",1,"CP-210183",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100","29.251; 29.551 ",88,45,null,null,"2020-06-26","2021-06-11"]
[973,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[974,880053,"   CT3 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088; 13/9/21: 65%->75; 13/12/21: 75%->85; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 85%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; ",88,45,null,null,"2020-06-26","2022-03-12"]
[975,880054,"   CT4 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50; 13/9/21: 50%->60; 13/12/21: 60%->80; 13/12/21: FCD:Mon 20/09/->03/22; 12/3/22: 80%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; ",88,45,null,null,"2020-06-26","2022-03-12"]
[976,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[977,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","2019-03-07","2019-03-07",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"2021-12-10","2022-03-12"]
[978,970052,"   CT3 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C3","2019-03-07","2019-03-07",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",null,null,null,null,"2022-09-07","NA"]
[979,970053,"   CT4 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",null,null,null,null,"2022-09-07","NA"]
[980,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","2021-12-10","2022-06-10",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"2021-12-10","2022-06-04"]
[981,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","2021-12-10","2022-03-12",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"2021-12-10","2022-03-12"]
[982,820009,"Study on authentication enhancements in 5GS","FS_AUTH_ENH",1,"Rel-17","S3","2018-12-13","2021-12-10",1,"SP-190713",null,"Tsiatsis, Vlasios, ","vlasios.tsiatsis@ericsson.com ","07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202 ","new",82,42,null,null,"2018-12-06","2022-03-12"]
[983,940012,"Authentication enhancements in 5GS ","AUTH_ENH",1,"Rel-17","S3","2021-12-10","2022-03-12",1,"SP-211360",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 24/3/22: 0%->100",33.101999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[984,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","2022-03-10","2022-03-12",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"2022-03-10","2022-03-12"]
[985,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"2022-03-10","2022-06-20"]
[986,0,"Rel-17 Management-only Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[987,900021,"Management Aspects of 5G Network Sharing ","MANS",1,"Rel-17","S5","2020-12-04","2022-03-11",1,"SP-201080",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25; 13/9/21: 25%->30; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 30%->60; 12/3/22: 60%->100",null,90,46,null,null,"2020-12-04","2022-03-12"]
[988,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","2021-06-11","2021-12-10",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"2021-06-11","2021-12-13"]
[989,910030,"File Management ","FIMA",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210135",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 11/6/21: 0%->25; 13/9/21: 25%->60; 13/12/21: 60%->75; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 75%->100","28.537; 28.622; 28.623; 28.532 ",91,46,null,null,"2021-03-18","2022-03-12"]
[{"$f":"A990+1","v":990},930032,"Improved support for NSA in the service-based management architecture ","NSA_SBMA",1,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-211121",null,"Lan Zou, Huawei ","zoulan@huawei.com ",null,"28.623; 28.622; 28.659; 28.663 ",91,46,null,null,"2021-09-10","NA"]
[991,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"2021-09-10","2022-03-12"]
[992,880029,"Enhancement of Handover Optimization ","E_HOO",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200466",null,"Elmdahl, Per, Ericsson ","per dot Elmdahl at Ericsson dot com ","28.552; 28.313; 28.541 ; 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:18/06/2021->03/22; 11/6/21: 10%->30; 13/9/21: 30%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[993,880028,"Management data collection control and discovery ","MADCOL",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200465",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30; 13/9/21: 30%->35; 13/9/21: FCD:Wed 22/09/->03/22; 13/12/21: 35%->40; 12/3/22: 40%->45; 4/6/22: 45%->100",null,88,45,null,null,"2020-06-26","2022-06-04"]
[994,880026,"Management of the enhanced tenant concept ","eMEMTANE",1,"Rel-17","S5","2020-06-26","2021-12-15",1,"SP-220293",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->20; 12/3/22: 20%->100; 22/3/22: WID:SP-200463->SP-220293",null,88,45,null,null,"2020-06-26","2022-03-22"]
[995,880025,"Enhancements of 5G performance measurements and KPIs ","ePM_KPI_5G",1,"Rel-17","S5","2020-06-12","2022-03-11",1,"SP-200462",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","28.552; 32.425; 28.554; 32.426; 32.450; 32.451; 32.455 ; 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->40; 11/6/21: 40%->50; 13/9/21: 50%->60; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[996,810027,"Intent driven management service for mobile network","IDMS_MN",1,"Rel-17","S5","2018-09-06","2022-03-11",1,"SP-180899",null,"Zou Lan, Huawei ","zoulan@huawei.com","7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[997,820035,"Discovery of management services in 5G ","5GDMS",1,"Rel-17","S5","2018-12-13","2022-03-11",1,"SP-200770",null,"Brendan Hassett, Huawei Technologies Sweden AB ","brendan.t.hassett@huawei.com","¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ","28.533; 28.532; 28.531 ",82,42,null,null,"2018-12-07","2022-03-12"]
[998,860024,"Network policy managementfor 5G mobile networks ","NPM",1,"Rel-17","S5","2019-12-06","2022-03-11",1,"SP-191211",null,"China Mobile Shasha Guo ","guoshasha@chinamobile.com ","; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75; 13/9/21: 75%->78; 13/12/21: 78%->100","28.532; 28.541 ",86,44,null,null,"2019-12-06","2021-12-13"]
[999,850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","2019-09-19","2021-03-12",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"2019-09-13","2021-03-21"]
[1000,940078,"Enhancements of Management Data Analytics Service ","eMDAS",1,"Rel-17","S5","2021-03-18","2021-12-10",1,"SP-210132",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 13/9/21: 0%->10; 13/9/21: FCD:Fri 10/12/->12/21; 13/12/21: 10%->45. UID was at 0, corrected; 12/3/22: 45%->65; 4/6/22: 65%->100","28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533; 28.105",91,46,null,null,"2021-03-18","2022-06-04"]
[1001,870022,"Enhancements on EE for 5G networks ","EE5GPLUS",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200188",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->55; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->70; 13/12/21: 70%->100","28.310; 28.552; 28.554; 28.541 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1002,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"2019-12-06","2021-12-13"]
[1003,870024,"Enhancement on Management Aspects of 5G Service-Level Agreement ","EMA5SLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-210860",null,"SHI, Xiaonan, CMCC ","shixiaonan@chinamobile.com ","; 13/9/20: 0%->5; 5/12/20: 5%->40; 21/3/21: 40%->60; 21/3/21: FCD:18/03/2021->06/21; 11/6/21: 60%->65; 11/6/21: FCD:Fri 11/06/->12/21; 10/9/21: WID:SP-200190->SP-210860; 13/9/21: 65%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85 ","28.541; 28.531 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1004,870025,"Management of MDT enhancement in 5G ","e_5GMDT",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200191",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75; 13/9/21: 75%->85; 13/12/21: 85%->95; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 95%->100","32.421; 32.422; 32.423; 28.622; 28.623; 28.523 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1005,870026,"Additional NRM features ","adNRM",1,"Rel-17","S5","2020-02-05","2022-03-11",1,"SP-200192",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com","; 10/6/20: FCD:19/03/2020->06/20; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->30; 13/9/21: 30%->50; 13/9/21: FCD:Tue 15/06/->12/21; 13/12/21: 50%->80; 13/12/21: FCD:Fri 10/12/->03/22; 01/22: rapporteur change from Jing Ping; 12/3/22: 80%->100","28.540; 28.541; 28.622; 28.623 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1006,860061,"Study on NR QoE (Quality of Experience) management and optimizations for diverse services","FS_NR_QoE",1,"Rel-17","R3","2019-12-16","2020-09-15",1,"RP-193256",null,"China Unicom",null,"affects: NR.; 25/9/20: 38.890 added;; 7/4/21: 0%->100",38.89,86,44,null,null,"2020-01-14","2021-04-07"]
[1007,870030,"Enhanced Closed loop SLS Assurance ","eCOSLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200196",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 50%->60; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->90; 4/6/22: 90%->100","28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 ",87,44,null,null,"2019-12-06","2022-06-04"]
[1008,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","2022-03-10","2022-06-10",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1009,0,"Rel-17 Other NR-only improvements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1010,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"2021-01-01","2022-03-22",1,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"2021-06-04","2021-07-02"]
[1011,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","2021-01-01","2022-03-22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1012,911009,"Rel-17 Power Class 2 UE for NR inter-band CA with or without SUL configurations with x (16>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-221516",null,"Huawei ",null,"basket WI; TR 38.8xx ; 2/7/21: WID:RP-210543->RP-211378; 29/9/21: WID:RP-211378->RP-212182; 6/1/22: WID:RP-212182->RP-213650; 5/4/22: WID:RP-213650->RP-220701; 12/7/22: WID:RP-220701->RP-221516",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1013,911109,"   Core part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","basket WI; TR 38.8xx ; 2/7/21: 38.842 added;; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->78% ; 20/6/22: Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.com; ","38.842; 38.541",91,46,null,null,"2021-04-07","2022-06-20"]
[1014,911209,"   Stopped - Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: Stat Rep: RP-212181->RP-220699 ; 6/6/22: CD:12/06/2022->22/06/2022 ; 20/6/22:Stopped at 0%; Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.c...",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1015,911010,"Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS",1,"Rel-17",null,"2021-03-12","2022-12-23",0.84,"RP-212030",null,"Vivo ",null,"compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: WID:RP-210807->RP-211158; 29/9/21: WID:RP-211158->RP-212030; 1/10/21: 38.161 added;; ",38.161000000000001,91,46,null,null,"2021-04-07","2022-06-04"]
[1016,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","2021-03-12","2022-03-22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ",38.834000000000003,91,46,null,null,"2021-04-07","2022-06-20"]
[1017,911210,"   Perf. part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-221785","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy ; 22/3/22: Compl:0%->20%; 22/3/22: CD:08/09/2022->12/09/2022 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com s...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1018,960088,"   UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.05,"RP-221690",null,"Apple ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[1019,911012,"High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79",1,"Rel-17",null,"2021-03-12","2023-03-23",0.9,"RP-210843",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1020,911112,"   Core part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1021,911212,"   Perf. part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1022,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","2021-09-17","2023-03-23",0.84,"RP-211979","RP-221356","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...",null,93,47,null,null,"2021-09-29","2022-09-09"]
[1023,911013,"High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34",1,"Rel-17",null,"2021-03-12","2022-09-12",1,"RP-210844",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1024,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1025,911213,"   Perf. part: NR_UE_PC2_n34","NR_UE_PC2_n34-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1026,930053,"   UE Conformance - High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34-UEConTest",2,"Rel-17","R5","2021-09-17","2022-09-12",1,"RP-221760","RP-221357","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n34-Core ; 6/1/22: WID:RP-211980->RP-213034; 22/3/22: Compl:0%->53% ; 20/6/22: FCD:12/09/2022->22/06/2022; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-211980->RP-221760",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1027,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"2021-03-12","2023-03-23",0.91,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1028,911114,"   Core part: NR_UE_PC2_n39","NR_UE_PC2_n39-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1029,911214,"   Perf. part: NR_UE_PC2_n39","NR_UE_PC2_n39-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1030,930054,"   UE Conformance - High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39-UEConTest",2,"Rel-17","R5","2021-09-17","2023-03-23",0.85,"RP-211981","RP-221355","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n39-Core ; 6/1/22: WID:RP-211981->RP-213035; 22/3/22: Compl:0%->47% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ...",null,93,47,null,null,"2021-09-29","2022-09-09"]
[1031,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"2021-04-07","NA"]
[1032,911115,"   Core part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1033,911215,"   Perf. part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 6/1/22: 0%->100",null,91,46,null,null,"2021-04-07","2022-01-06"]
[1034,911006,"NR Uplink Data Compression (UDC) ","NR_UDC",1,"Rel-17",null,"2021-03-12","2023-06-23",0.53,"RP-220140",null,"CATT ",null,"no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core ; 2/7/21: WID:RP-210909->RP-211203; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1035,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","2021-03-12","2022-03-12",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2022-04-05"]
[1036,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-23",7.0000000000000007E-2,"RP-221449",null,"CATT ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[1037,910097,"Study on optimizations of pi/2 BPSK uplink power in NR ","FS_NR_Opt_pi2BPSK",1,"Rel-17","R4","2021-03-12","2022-03-12",1,"RP-213535","RP-220136","Huawei ",null,"; 1/10/21: 38.868 added;; 6/1/22: WID:RP-210910->RP-213535 ; ",38.868000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1038,910096,"Study on band combination handling in RAN4 ","FS_NR_ENDC_combo_rules",1,"Rel-17","R4","2021-03-12","2022-03-22",1,"RP-211146","RP-220164","ZTE ",null,"TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC ; 2/7/21: WID:RP-210773->RP-211146; 2/7/21: 38.862 added;13/9/21: Compl:0%->50%13/9/21: CD:Sat 12/03/22->Tue 22/03/2213/9/21: Stat ",38.862000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1039,880078,"Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs","NR_MIMO_OTA",1,"Rel-17",null,"2020-06-22","2022-09-22",0.95,"RP-213101",null,"CAICT",null,"25/9/20: WID:RP-201302->RP-201800; 6/1/22: WID:RP-201800->RP-213101",null,88,45,null,null,"2020-07-28","2022-01-06"]
[1040,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"2020-07-28","2022-06-20"]
[1041,880278,"   Perf. Part: NR_MIMO_OTA","NR_MIMO_OTA-Perf",2,"Rel-17","R4","2020-06-22","2022-09-22",0.9,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","; 13/9/21: Compl:0%->20%; 13/9/21: CD:Wed 15 ; 22/3/22: Compl:20%->35%; ; 6/6/22: Compl:35%->55% 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com 9/...",null,88,45,null,null,"2020-07-28","2022-09-09"]
[1042,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"2020-03-25","2022-12-23",0.67,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"2020-03-26","2021-01-06"]
[1043,870164,"   Core part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1044,870264,"   Perf. Part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Perf",2,"Rel-17","R4","2020-03-25","2021-03-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1045,950062,"   UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 ","NR_FR2_FWA_Bn257_Bn258-UEConTest",2,"Rel-17","R5","2022-03-15","2022-12-23",0.05,"RP-220424","RP-221492","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_FR2_FWA_Bn257_Bn258-Core 6/6/22: Compl:0%->5% 6/6/22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ",null,95,48,null,null,"2022-04-05","2022-06-20"]
[1046,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1047,880192,"   Core part: NR_bands_R17_BWs","NR_bands_R17_BWs-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221212","RP-221213","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","; 13/9/21: Compl:0%->50%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:50%->80%; 20/6/22: Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1048,880093,"Introduction of channel bandwidths 35MHz and 45MHz for NR FR1","NR_FR1_35MHz_45MHz_BW",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722; 2/7/21: WID:RP-210722->RP-211386",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1049,880193,"   Core part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1050,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1051,880097,"SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL","NR_SAR_PC2_interB_SUL_2BUL",1,"Rel-17",null,"2020-03-19","2022-09-22",1,"RP-212530",null,"China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 2/7/21: WID:RP-201584->RP-211494; 29/9/21: WID:RP-211494->RP-212530",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1052,880197,"   Core part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Core",2,"Rel-17","R4","2020-03-19","2021-09-21",1,"RP-212530","RP-211830","China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 13/9/21: Compl:0%->100%; 13/9/21: CD:Fri 19/03/21->Tue 21/09/21; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; ; 29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1053,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","2020-03-19","2022-03-21",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"2020-07-28","2021-09-13"]
[{"$f":"A1054+1","v":1054},920065,"   UE Conformance - SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL ","NR_SAR_PC2_interB_SUL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2022-09-22",1,"RP-211139","RP-221295","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_SAR_PC2_interB_SUL_2BUL-Core ; 13/9/21: Compl:0%->5%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 13/9/ ; 22/3/22: Compl:5%->23% ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinateleco...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[1055,900061,"NR coverage enhancements ","NR_cov_enh",1,"Rel-17",null,"2019-03-07","2023-06-23",0.76,"RP-211566",null,"China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 7/4/21: WID:RP-202928->RP-210855; 2/7/21: WID:RP-210855->RP-211566",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1056,860036,"   Study on on NR coverage enhancements","FS_NR_cov_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-200861",null,"China Telecom",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1057,900161,"   Core part: NR_cov_enh","NR_cov_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-211566","RP-220563","China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211826 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1058,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-12-22",0.9,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...",null,90,46,null,null,"2021-01-06","2022-09-09"]
[1059,950063,"   UE Conformance - NR coverage enhancements ","NR_cov_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-06-23",0.09,"RP-220576RP-221298","RP-221297","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_cov_enh-Core ; 6/6/22: Compl:0%->5% ; 6/6/22: CD:15/06/2023->23/ ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-220576->RP-221298 ; ;...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[1060,900062,"Support of reduced capability NR devices ","NR_redcap",1,"Rel-17",null,"2019-12-16","2023-06-23",0.8,"RP-220966",null,"Ericsson ",null,"follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202933->RP-210918; 2/7/21: WID:RP-210918->RP-211574; 5/4/22: WID:RP-211574->RP-220966",null,90,46,null,null,"2021-01-06","2022-04-05"]
[1061,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1062,900162,"   Core part: NR_redcap","NR_redcap-Core",2,"Rel-17","R1","2020-12-14","2022-06-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 22/ 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1063,900262,"   Perf. part: NR_redcap","NR_redcap-Perf",2,"Rel-17","R1","2020-12-14","2022-12-22",0.75,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap ; 22/3/22: Compl:0%->25%; 22/3/22: CD:08/09/2022- 6/6/22: Compl ; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com ...",null,90,46,null,null,"2021-01-06","2022-09-09"]
[1064,950066,"   UE Conformance - Support of reduced capability NR devices ","NR_redcap_plus_ARCH-UEConTest",2,"Rel-17","R5","2022-03-15","2023-06-23",0.31,"RP-222830","RP-221156","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 WI NR_redcap-Core and CT1 REL-17 WI ARCH_NR_REDCAP 6/6/22: Compl:0%->13% ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ...",null,95,48,null,null,"2022-04-05","2022-09-09"]
[1065,930018,"   Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S2","2021-09-10","2021-12-12",1,"SP-211100",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 10/12/21: 0%->100","23.501; 23.502 ",93,47,null,null,"2021-09-10","2021-12-10"]
[1066,940005,"   CT1 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","24.501; 23.122; 24.008; 24.368",94,48,null,null,"2022-01-07","2022-06-04"]
[1067,950047,"   CT3 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-221265",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: WID:CP-213081->CP-220304; 12/3/22: 0%->100; 4/6/22: WID:CP-220304->CP-221265","24.501; 23.122; 24.008; 24.368",95,48,null,null,"2022-03-12","2022-06-04"]
[1068,940100,"   CT4 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","29.571; 29.502; 29.540; 29.518; 23.008",94,48,null,null,"2022-01-07","2022-06-04"]
[1069,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","2021-12-10","2022-03-12",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"2022-01-07","2022-06-04"]
[1070,940027,"   Charging aspects of Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211428",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 12/3/22: 0%->35; 4/6/22: 35%->100","32.255; 32.298; 32.291 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1071,900064,"Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 ","NR_bands_UL_MIMO_PC3_R17",1,"Rel-17",null,"2020-12-14","2023-06-23",0.73,"RP-221518",null,"Huawei ",null,"basket WI ; 7/4/21: WID:RP-202819->RP-210557; 2/7/21: WID:RP-210557->RP-211380; 29/9/21: WID:RP-211380->RP-212184; 6/1/22: WID:RP-212184->RP-213137; 5/4/22: WID:RP-213137->RP-220704; 12/7/22: WID:RP-220704->RP-221518",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1072,900164,"   Core part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Core",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: Compl:0%->70%; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1073,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1074,940090,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-17","NR_bands_UL_MIMO_PC3_R17-UEConTest",2,"Rel-17","R5","2021-12-13","2023-06-23",0.19,"RP-220745","RP-221489","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_bands_UL_MIMO_PC3_R17; 22/3/22: Compl:0%->8%; 22/3/22: Stat Rep: ->RP-220419; 5/4/22: WID:RP-213227->RP-220745 ; 6/6/22: CD:12/09/2022->22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyu...",null,94,48,null,null,"2022-01-06","2022-09-09"]
[1075,900167,"Introduction of bandwidth combination set 4 (BCS4) for NR ","NR_BCS4-Core",1,"Rel-17","R4","2019-03-07","2022-06-22",1,"RP-202832","RP-221317","Per Lindell, Ericsson","per.lindell@ericsson.com","no Perf. part ; 20/6/22: FCD:03/06/2020->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221317; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1076,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"2020-12-14","2022-03-22",1,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;",37.866999999999997,90,46,null,null,"2021-01-06","2021-07-02"]
[1077,900168,"   Core part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI; TR 37.8xx ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478 ; ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1078,900268,"   Perf. part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI ; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478; 13/9/21: Stat Rep: ->RP-211833 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1079,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"2020-12-14","2023-03-23",0.91,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"2021-01-06","NA"]
[1080,900169,"   Core part: HPUE_PC1_5_n77_n78","HPUE_PC1_5_n77_n78-Core",2,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-202912","RP-212049","Qualcomm ",null,"no Perf. part ; 13/9/21: Compl:0%->100% ; 29/9/21: 100%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1081,930055,"   UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78-UEConTest",2,"Rel-17","R5","2021-09-17","2023-03-23",0.86,"RP-212581","RP-221239","Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia","jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com","tested: REL-17 WI HPUE_PC1_5_n77_n78-Core ; 22/3/22: Compl:0%->50%; ; 6/6/22: Compl:50%->61%20/6/22: Rapporteur: Verizon->Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia; Rap eMail: ->jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com; ...",null,93,47,null,null,"2021-09-29","2022-09-09"]
[1082,900070,"NR repeaters ","NR_repeaters",1,"Rel-17",null,"2020-12-14","2022-12-22",0.9,"RP-213514",null,"Qualcomm ",null,"no Perf. part ; 7/4/21: WID:RP-202927->RP-210818; 29/9/21: WID:RP-210818->RP-212129; 6/1/22: WID:RP-212129->RP-213514",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1083,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"2021-01-06","2022-06-20"]
[1084,930250,"   Perf. part: NR repeaters ","NR_repeaters-Perf",2,"Rel-17","R4","2021-09-17","2022-12-22",0.8,"RP-213514","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","Core part (UID=900170) started in Dec.20 while Perf. Part (UID=930250) started in 17/09/21 via revised WID RP-212129; TS 38.1??-1, TS 38.1??-2 ; 7/1/22: 38.115-2 and 38.115-1 added;; 20/6/22: FCD:17/09/2022->22/09/2022; Compl:0%->30%; WID: RP-213514->R...","38.115-2; 38.115-1",93,47,null,null,"2021-09-29","2022-09-09"]
[1085,930056,"Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC",1,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302",null,"Qualcomm ",null,"no Perf. part ; 12/7/22: WID:RP-212622->RP-221302",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1086,930156,"   Core part: Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-Core",2,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302","RP-221588","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","no Perf. Part ; 22/3/22: Compl:0%->75%; … 20/6/22: WID: RP-212622->RP-221302; Stat Rep: RP-220514->RP-221588; Rapporteur: Qualcomm->Gene Fong, Qualcomm Incorporated; Rap eMail: ->gfong@qti.qualcomm.com; ",null,93,47,null,null,"2021-09-29","2022-06-20"]
[1087,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","2021-09-17","2022-12-22",0.9,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"2021-09-29","2022-01-06"]
[1088,930157,"   Core part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Core",2,"Rel-17","R4","2021-09-17","2022-03-15",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ]; TR 36.8xx ; 7/1/22: 36.779 added ; ",36.779000000000003,93,47,null,null,"2021-09-29","2022-03-22"]
[1089,930257,"   Perf. part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Perf",2,"Rel-17","R4","2021-09-17","2022-03-15",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ] ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1090,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-22",0.72,"RP-221417",null,"Puloli ",null,"9/9/22: Comp...",null,96,49,null,null,"2022-07-12","2022-09-09"]
[1091,930058,"High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD",1,"Rel-17","R4","2021-09-17","2022-12-23",0.88,"RP-212633",null,"China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ",null,93,47,null,null,"2021-09-29","NA"]
[1092,930158,"   Core part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Core",2,"Rel-17","R4","2021-09-17","2022-03-15",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1093,930258,"   Perf. part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Perf",2,"Rel-17","R4","2021-09-17","2022-03-15",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1094,960070,"   UE Conformance - High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-23",0.67,"RP-221158",null,"ChinaUnicom ",null,"9/9/22: Comp...",null,null,null,null,null,"2022-07-12","2022-09-09"]
[1095,0,"Rel-17 NR Carrier Aggregation","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1096,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1097,881005,"NR itrabCA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R17_Intra",1,"Rel-17",null,"2016-06-09","2022-06-22",1,"RP-221319",null,"Ericsson",null,"25/9/20: WID:RP-200663->RP-201571; 6/1/21: WID:RP-201571->RP-202187; 7/4/21: WID:RP-202187->RP-210210; 2/7/21: WID:RP-210210->RP-211585; 29/9/21: WID:RP-211585->RP-211757; 6/1/22: WID:RP-211757->RP-212900; 5/4/22: WID:RP-212900->RP-220825; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1098,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1099,881205,"   Perf. Part: NR_CA_R17_Intra","NR_CA_R17_Intra-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1100,0,"   Rel-17 NR inter band Carrier Aggregation (iterbCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1101,900063,"High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1","NR_intra_HPUE_R17",1,"Rel-17",null,"2021-02-10","2022-06-22",1,"RP-221774",null,"Huawei",null,"7/4/21: WID:RP-202818->RP-210555; 29/9/21: WID:RP-210555->RP-212180; 6/1/22: WID:RP-212180->RP-213133; 5/4/22: WID:RP-213133->RP-220930; 12/7/22: WID:RP-220930->RP-221774",null,90,46,null,null,"2021-02-10","2022-07-12"]
[1102,900163,"   Core part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Core",2,"Rel-17","R4","2021-02-10","2022-06-22",1,"RP-221774","RP-221513 / 1773","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->10%; 22/3/22: CD:22/03/2022->10/06/2022 ; 20/6/22: Stat Rep: RP-221513->RP-221513 / 1773; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; ",null,90,46,null,null,"2021-02-10","2022-06-20"]
[1103,900263,"   Stopped - Perf. Part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Perf",2,"Rel-17","R4","2021-02-10","2022-06-12",1,"RP-221774","RP-220696","Huawei",null,"; 13/9/21: CD:Thu 09/12/21->Wed 22/06/22; ; 22/3/22: CD:22/06/2022->12/06/2022; 22/3/22: WID: RP-213133->RP-213132; 22/3/22: Stat Rep: RP-212179->RP-220696. 12/7/22: stopped at 0%. 0%->100",null,90,46,null,null,"2021-02-10","2022-07-12"]
[1104,881006,"NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2)","NR_CADC_R17_2BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221250",null,"ZTE",null,"25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495; 2/7/21: WID:RP-210495->RP-211058; 29/9/21: WID:RP-211058->RP-212511; 6/1/22: WID:RP-212511->RP-212887; 5/4/22: WID:RP-212887->RP-220144; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1105,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1106,881206,"   Perf. part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1107,881007,"NR iterbCA for 3 bands DL with 1 band UL","NR_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221772",null,"CATT",null,"25/9/20: WID:RP-200922->RP-201787; 6/1/21: WID:RP-201787->RP-202720; 7/4/21: WID:RP-202720->RP-210901; 2/7/21: WID:RP-210901->RP-211215; 29/9/21: WID:RP-211215->RP-212239; 6/1/22: WID:RP-212239->RP-213299; 5/4/22: WID:RP-213299->RP-220738; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1108,881107,"   Core part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1109,881207,"   Perf. part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: CD:15/09/2021->12/06/2022; 22/3/22: Stat Rep: ->RP-220737 ; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1110,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1111,881108,"   Core part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1112,881208,"   Perf. part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1113,881009,"NR iterbCA for 4 bands DL with 1 band UL","NR_CA_R17_4BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221321",null,"Ericsson",null,"25/9/20: WID:RP-200665->RP-201573; 6/1/21: WID:RP-201573->RP-202189; 7/4/21: WID:RP-202189->RP-210760; 2/7/21: WID:RP-210760->RP-211171; 29/9/21: WID:RP-211171->RP-211759; 6/1/22: WID:RP-211759->RP-212902; 5/4/22: WID:RP-212902->RP-220827; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1114,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1115,881209,"   Perf. part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1116,881010,"NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands","NR_CADC_R17_4BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221396",null,"Samsung",null,"25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802; 2/7/21: WID:RP-210802->RP-211194; 29/9/21: WID:RP-211194->RP-212110; 6/1/22: WID:RP-212110->RP-213111; 5/4/22: WID:RP-213111->RP-220676; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1117,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A1118+1","v":1118},881210,"   Perf. part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","; 13/9/21: Compl:0%->70%; ; 22/3/22: Compl:70%->90%; 20/6/22: Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1119,881011,"NR iterbCA for 5 bands DL with x bands UL (x=1, 2)","NR_CADC_R17_5BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221510",null,"Huawei",null,"25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561; 2/7/21: WID:RP-210561->RP-211373; 29/9/21: WID:RP-211373->RP-212176; 6/1/22: WID:RP-212176->RP-213129; 5/4/22: WID:RP-213129->RP-220692; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1120,881111,"   Core part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3/22: 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1121,881211,"   Perf. part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1122,890054,"Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)","NR_PC2_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-09-17","2022-12-22",0.76,"RP-221866",null,"China Telecom ",null,"basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 6/1/21: WID:RP-202102->RP-202373; 7/4/21: WID:RP-202373->RP-210476; 2/7/21: WID:RP-210476->RP-211131; 2/7/21: 38.841 added;; 29/9/21: WID:RP-211131->RP-211831; 6/1/22: WID:RP...",38.841000000000001,89,45,null,null,"2020-09-25","2022-07-12"]
[1123,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1124,890254,"   Perf. part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI ; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211131->RP-202102 RP-202373 RP-210476 RP-211131; 13/9/21: Stat Rep: ->RP-211832; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: WID: RP-213649->RP‑213649; 22/3/22: Stat Rep: RP-211832-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1125,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2022-12-22",0.21,"RP-211140","RP-221296","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[1126,0,"Rel-17 NR and LTE","-",1,"Rel-17",null,"2020-03-25","2020-09-15",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1127,920072,"LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip","RP-211995","CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 13/9/21: Compl:0%->100% ; ",null,92,47,null,null,"2021-07-02","2021-09-13"]
[1128,920172,"   Core part: LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core",2,"Rel-17","R4","2021-06-15","2021-12-15",1,"RP-211996",null,"CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 29/9/21: WID:RP-211509->RP-211996",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1129,940089,"   UE Conformance - LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest",2,"Rel-17","R5","2021-12-13","2022-12-12",1,"RP-213036","RP-220625","CMCC",null,"tested: REL-17 WI DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1130,920073,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2021-06-15","2022-06-22",0.99,"RP-221795",null,"Nokia ",null,"this is not a basket WI ; 29/9/21: WID:RP-211571->RP-212533; 6/1/22: WID:RP-212533->RP-213106; 5/4/22: WID:RP-213106->RP-220767; 12/7/22: WID:RP-220767->RP-221795",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1131,920173,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; …; 7/1/22: 37.828 and 37.828 added;; 22/3/22: Compl:0%->50% ; 20/6/22: Compl:50%->100%; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail...","37.828; 37.828",92,47,null,null,"2021-07-02","2022-06-20"]
[1132,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","2021-09-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1133,920074,"Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL",1,"Rel-17","R4","2021-06-15","2022-06-22",0.99,"RP-221524",null,"Huawei ",null,"basket WI; TR 37.717-11-41 ; 29/9/21: WID:RP-211592->RP-212606; 6/1/22: WID:RP-212606->RP-213142; 5/4/22: WID:RP-213142->RP-220712; 12/7/22: WID:RP-220712->RP-221524",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1134,920174,"   Core part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI; TR 37.717-11-41 ; 20/6/22: FCD:15/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221523; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1135,920274,"   Perf. part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Perf",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI ; 22/3/22: Compl:0%->15%; 22/3/22: CD:15/03/2022->10/06/2022; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1136,911019,"Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths","ENDC_R17_1BLTE_1BNR_MSD",1,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part; 2/7/21: WID:RP-210891->RP-211384; 29/9/21: WID:RP-211384->RP-212187; 6/1/22: WID:RP-212187->RP-213140; 5/4/22: WID:RP-213140->RP-220709",null,91,46,null,null,"2021-04-09","2022-04-05"]
[1137,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"2021-04-09","2022-06-20"]
[1138,930259,"   Stopped - Perf. Part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Perf",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon ",null,"4/6/22: Stopped at 70%. This Perf. part is not needed",null,93,47,null,null,"2022-03-13","2022-06-04"]
[1139,911011,"Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR",1,"Rel-17",null,"2021-03-12","2022-12-22",0.69,"RP-221322",null,"Ericsson ",null,"basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: WID:RP-210816->RP-211172; 29/9/21: WID:RP-211172->RP-211760; 6/1/22: WID:RP-211760->RP-213467; 5/4/22: WID:RP-213467->RP-220828; 12/7/22: WID:RP-220...",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1140,911111,"   Core part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: 37.827 added; ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; List of Impacted TS & TR updated; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1141,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1142,930051,"   UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-22",0.06,"RP-211870","RP-221221","Leif MATTISSON, Ericsson","Leif[dot]mattisson[at]ericsson[dot]com","tested: REL-17 WI ENDC_PC2_R17_xLTE_yNR ; 22/3/22: Compl:0%->5%; 22/3/22: CD:15/12/2022->12/12/2022; 22/3/22 6/6/22: CD:12/12/2022->22/12/2022 ; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Ericsson; Rap eMail: ->Leif[dot]mattisson[at]ericsson[d...",null,93,47,null,null,"2021-09-29","2022-09-09"]
[1143,911018,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC ","LTE_NR_Simult_RxTx",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-221521",null,"Huawei ",null,"; 2/7/21: WID:RP-210890->RP-211382; 5/4/22: WID:RP-211382->RP-220707; 12/7/22: WID:RP-220707->RP-221521",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1144,911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",38.838999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1145,911218,"   Stopped - Perf. part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 6/6/22: Compl:70%->0%6/6/22: CD:22/03/2022->22/06/20226/6/22: WID: RP-220707->RP-2113826/6/22: Stat Rep: RP-212185->RP-221520; 20/6/22: Compl:0%->100%; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; Sto",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1146,890052,"Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) ","DC_R17_5BLTE_1BNR_6DL2UL",1,"Rel-17",null,"2020-09-17","2022-03-22",1,"RP-220672",null,"Samsung ",null,"basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801; 2/7/21: WID:RP-210801->RP-211195; 6/1/22: WID:RP-211195->RP-213112; 5/4/22: WID:RP-213112->RP-220672",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1147,890152,"   Core part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-22",1,"RP-220672","RP-220673","Samsung ",null,"basket WI; TR 37.717-51-11 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1148,890252,"   Perf. part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-22",1,"RP-220672","RP-220673","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1149,890053,"Rel-17 Dual Connectivity (DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) ","DC_R17_xBLTE_2BNR_yDL3UL",1,"Rel-17",null,"2020-09-17","2022-03-22",1,"RP-220674",null,"Samsung ",null,"basket WI; TR 37.717-21-22 ; 6/1/21: WID:RP-201643->RP-202542; 5/4/22: WID:RP-202542->RP-220674",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1150,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-22",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1151,890253,"   Perf. part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-22",1,"RP-220674","RP-220675","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1152,880080,"Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band","NR_LTE_V2X_PC5_combos",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-213297",null,"CATT",null,"25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588; 6/1/22: WID:RP-210588->RP-213297",37.875,88,45,null,null,"2020-07-28","2022-01-06"]
[1153,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1154,880280,"   Perf. part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->9 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1155,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"2020-06-22","2023-03-23",0.79,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1156,880194,"   Core part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3/2 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1157,880294,"   Perf. part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1158,911000,"   UE Conformance - ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-UEConTest",2,"Rel-17","R5","2021-03-12","2023-03-23",0.37,"RP-211420","RP-221151","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 basket WI ENDC_UE_PC2_R17_NR_TDD-Core ; 2/7/21: WID:RP-210401->RP-211420; 2/7/21: 0%->10 ; ; 6/6/22: Com ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ; ;...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1159,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1160,880195,"   Core part: DSS_LTE_B38_NR_Bn38","DSS_LTE_B38_NR_Bn38-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1161,880096,"LTE/NR spectrum sharing in Band 40/n40","DSS_LTE_B40_NR_Bn40",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: WID:RP-201362->RP-202084",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1162,880196,"   Core part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1163,880296,"   Perf. part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Perf",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1164,880098,"Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_1BLTE_1BNR_2DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221257",null,"CHTTL",null,"25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204; 2/7/21: WID:RP-210204->RP-211162; 29/9/21: WID:RP-211162->RP-212096; 6/1/22: WID:RP-212096->RP-213060; 5/4/22: WID:RP-213060->RP-220398; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1165,880198,"   Core part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: Compl:0%->75%; ; 22/3/22: Compl:75%->90%; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1166,880298,"   Perf. part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:0%->90%; ; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1167,880099,"Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_2BLTE_1BNR_3DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221508",null,"Huawei",null,"25/9/20: WID:RP-201369->RP-202060; 6/1/21: WID:RP-202060->RP-202613; 7/4/21: WID:RP-202613->RP-210559; 2/7/21: WID:RP-210559->RP-211371; 29/9/21: WID:RP-211371->RP-212174; 6/1/22: WID:RP-212174->RP-213127; 5/4/22: WID:RP-213127->RP-220689; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1168,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1169,890263,"   Perf. part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-17","R4","2020-09-16","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221507; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1170,881000,"Dual Connectivity (DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_3BLTE_1BNR_4DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221320",null,"Ericsson",null,"25/9/20: WID:RP-201370->RP-201572; 6/1/21: WID:RP-201572->RP-202188; 7/4/21: WID:RP-202188->RP-210211; 2/7/21: WID:RP-210211->RP-211170; 29/9/21: WID:RP-211170->RP-211758; 6/1/22: WID:RP-211758->RP-212901; 5/4/22: WID:RP-212901->RP-220826; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1171,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1172,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1173,881001,"Dual Connectivity (DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_4BLTE_1BNR_5DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221073",null,"Nokia",null,"25/9/20: WID:RP-201371->RP-201483; 6/1/21: WID:RP-201483->RP-202590; 7/4/21: WID:RP-202590->RP-210766; 2/7/21: WID:RP-210766->RP-211319; 29/9/21: WID:RP-211319->RP-212532; 6/1/22: WID:RP-212532->RP-213251; 5/4/22: WID:RP-213251->RP-220999; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1174,881101,"   Core part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1175,881201,"   Perf. part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1176,881002,"Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R17_xBLTE_2BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221182",null,"LG Electronics",null,"25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202; 2/7/21: WID:RP-210202->RP-211043; 29/9/21: WID:RP-211043->RP-211750; 6/1/22: WID:RP-211750->RP-212876; 5/4/22: WID:RP-212876->RP-220302; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1177,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1178,881202,"   Perf. part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1179,881003,"Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL)","DC_R17_xBLTE_yBNR_3DL3UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221232",null,"ZTE",null,"25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344; 2/7/21: WID:RP-210344->RP-211054; 29/9/21: WID:RP-211054->RP-211803; 6/1/22: WID:RP-211803->RP-212883; 5/4/22: WID:RP-212883->RP-220202; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1180,881103,"   Core part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1181,881203,"   Perf. part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A1182+1","v":1182},881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1183,881104,"   Core part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1184,881204,"   Perf. part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1185,881012,"band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R17",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221512",null,"Huawei",null,"25/9/20: WID:RP-201026->RP-201726; 6/1/21: WID:RP-201726->RP-202611; 7/4/21: WID:RP-202611->RP-210563; 2/7/21: WID:RP-210563->RP-211375; 29/9/21: WID:RP-211375->RP-212178; 6/1/22: WID:RP-212178->RP-213131; 5/4/22: WID:RP-213131->RP-220695; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1186,881112,"   Core part: NR_SUL_combos_R17","NR_SUL_combos_R17-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1187,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1188,900056,"UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2022-12-22",0.11,"RP-202568","RP-221488","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 basket WIs: NR_CA_R17_Intra, NR_CADC_R17_2BDL_xBUL, NR_CA_R17_3BDL_1BUL, NR_CADC_R17_3BDL_2BUL, NR_CA_R17_4BDL_1BUL, NR_CADC_R17_4BDL_2BUL, NR_CADC_R17_5BDL_xBUL, NR_SUL_combos_R17, DC_R17_1BLTE_1BNR_2DL2UL, DC_R17_2BLTE_1BNR_3DL2UL, DC_...",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1189,0,"Rel-17 NR new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1190,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"2021-03-12","2023-03-22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1191,911116,"   Core part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Core",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP‑211495","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 1/10/21: 38.853 added;; 22/3/22: Compl:0 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->95%; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wen...",38.853000000000002,91,46,null,null,"2021-04-07","2022-09-09"]
[1192,911216,"   Perf. part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Perf",2,"Rel-17","R4","2021-03-12","2023-03-22",1,"RP-221768","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","; 22/3/22: Compl:0%->90% ; 20/6/22: FCD:22/03/2023->22/06/2022; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wendler, UIC; Rap eMail: ->ingo dot wendler at sbb dot ch; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1193,911017,"Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_1900MHz_TDD",1,"Rel-17",null,"2021-03-12","2022-03-12",1,"RP-211542",null,"Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 2/7/21: WID:RP-210879->RP-211542",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1194,911117,"   Core part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Core",2,"Rel-17","R4","2021-03-12","2022-03-12",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 1/10/21: 38.852 added ; ",38.851999999999997,91,46,null,null,"2021-04-07","2022-03-22"]
[1195,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","2021-03-12","2022-03-12",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1196,860041,"Extending current NR operation to 71GHz","NR_ext_to_71GHz",1,"Rel-17","R1","2019-12-16","2022-12-22",0.79,"RP-213540",null,"Qualcomm",null,"affects: NR.; 25/9/20: WID:RP-193229->RP-201845; 6/1/21: WID:RP-201845->RP-202925; 7/4/21: WID:RP-202925->RP-210862; 2/7/21: WID:RP-210862->RP-211584; 29/9/21: WID:RP-211584->RP-212637; 6/1/22: WID:RP-212637->RP-213540",null,86,44,null,null,"2020-01-14","2022-01-06"]
[1197,860141,"   Core part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Core",2,"Rel-17","R1","2019-12-16","2022-09-22",1,"RP-213540","RP-221349 / 1749","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: Compl:0%->45%; ; 22/3/22: Compl:45%->90%; 20/6/22: Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation; Rap eMail: ->jingsun@qti.qualcomm.com; ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1198,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","2019-12-16","2022-12-22",0.6,"RP-213540","RP-221349 / 1749","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1199,860037,"Study on supporting NR from 52.6 GHz to 71 GHz","FS_NR_52_to_71GHz",1,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-201838",null,"Intel",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193259->RP-200902; 25/9/20: WID:RP-200902->RP-201838; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1200,870060,"Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz","FS_NR_IMT_param",1,"Rel-17","R4","2020-03-25","2020-12-15",1,"RP-202276",null,"Ericsson",null,"affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1201,870063,"Introduction of NR band n13","NR_n13",1,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx",null,87,44,null,null,"2020-03-26","NA"]
[1202,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1203,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1204,880082,"Introduction of NR 47GHz band","NR_47GHz_band",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"RP-212528","RP-211772","Ericsson",null,"7/4/21: WID:RP-201232->RP-210827; 2/7/21: WID:RP-210827->RP-211568; 13/9/21: C ",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1205,880182,"   Core part: Introduction of NR 47GHz band","NR_47GHz_band-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"2/7/21: 0%->100; 29/9/21: WID:RP-211568->RP-212528",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1206,880282,"   Perf. part: Introduction of NR 47GHz band","NR_47GHz_band-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1207,880084,"Introduction of NR band 24","NR_band_n24",1,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: WID:RP-201357->RP-211505",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1208,880184,"   Core part: Introduction of NR band 24","NR_band_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1209,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1210,890050,"Introduction of 6GHz NR licensed bands ","NR_6GHz",1,"Rel-17","R4","2020-09-17","2022-09-22",0.99,"RP-221504",null,"Huawei ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844; 6/1/22: WID:RP-202844->RP-213696; 5/4/22: WID:RP-213696->RP-220686; 12/7/22: WID:RP-220686->RP-221504",null,89,45,null,null,"2020-09-25","2022-07-12"]
[1211,890150,"   Core part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 22/3/22: Compl:0%->35% ; 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->l...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1212,890250,"   Perf. part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Perf",2,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Fri 17/06/22->Wed 22/06/22 ; 22/3/22: Compl:0%->20%; 2 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->...",null,89,45,null,null,"2020-09-25","2022-09-09"]
[1213,920075,"Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full",1,"Rel-17","R4","2021-06-15","2022-06-15",0.43,"RP-213683",null,"Apple ",null,"in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 29/9/21: WID:RP-211602->RP-212302; 6/1/22: WID:RP-212302->RP-213683",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1214,920175,"   Core part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Core",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-212683","RP-220450","Alexander Sayenko","asayenko@apple.com","in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 20/6/22: FCD:15/03/2022->22/03/2022; Compl:0%->100%; WID: RP-213683->RP-212683; Stat Rep: ->RP-220450; Rapporteur: Apple->Al...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1215,920275,"   Perf. part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Perf",2,"Rel-17","R4","2021-06-15","2022-06-15",0,"RP-213683",null,"Apple ",null,null,null,92,47,null,null,"2021-07-02","NA"]
[1216,890051,"Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU",1,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604",null,"Nokia ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762; 29/9/21: WID:RP-210762->RP-212625; 6/1/22: WID:RP-212625->RP-213604",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1217,890151,"   Core part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 10/2/21: 38.849 added;; 13/9/21: Compl:0%->30%; 13/9/21: CD:Tue 15/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",38.848999999999997,89,45,null,null,"2020-09-25","2022-03-22"]
[1218,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1219,900065,"Introduction of NR band n67 ","NR_n67",1,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-202829",null,"Ericsson ",null,null,null,90,46,null,null,"2021-01-06","NA"]
[1220,900165,"   Core part: Introduction of NR band n67 ","NR_n67-Core",2,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1221,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1222,900066,"Introduction of NR band n85 ","NR_n85",1,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-210707",null,"Ericsson ",null,"; 7/4/21: WID:RP-202830->RP-210707",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1223,900166,"   Core part: Introduction of NR band n85 ","NR_n85-Core",2,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1224,900266,"   Perf. part: Introduction of NR band n85 ","NR_n85-Perf",2,"Rel-17","R4","2020-12-14","2021-06-12",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1225,880083,"Introduction of 1.6 GHz NR supplemental uplink (SUL) band with same uplink frequency range of Band 24","NR_SUL_UL_n24",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: WID:RP-201251->RP-210341",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1226,880183,"   Core part: NR_SUL_UL_n24","NR_SUL_UL_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1227,880283,"   Perf. part: NR_SUL_UL_n24","NR_SUL_UL_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1228,880085,"Introduction of NR supplemental uplink (SUL) band 1880-1920MHz","NR_SUL_band_1880_1920MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1229,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1230,880285,"   Perf. part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1231,880086,"Introduction of NR supplemental uplink (SUL) band 2300-2400MHz","NR_SUL_band_2300_2400MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1232,880186,"   Core part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1233,880286,"   Perf. part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1234,900055,"UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2022-12-22",0.36,"RP-202567","RP-221487","Yuxin Hao, Huawei Technologies. Co., Ltd","haoyuxin@huawei.com","tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co.,...",null,90,46,null,null,"2021-01-06","2022-09-09"]
[1235,0,"Rel-17 LTE new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1236,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.82,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"2021-04-08","2021-07-02"]
[1237,911120,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1-Core",2,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.97,"RP-211144","RP-220172","EBU",null,"WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part; 13/9/21: C ; ",null,91,46,null,null,"2021-04-08","2022-03-22"]
[1238,880079,"Additional LTE bands for UE categories M1/M2/NB1/NB2","LTE_bands_R17_M1_M2_NB1_NB2",1,"Rel-17",null,"2020-06-08","2022-06-22",1,"RP-220816",null,"Ericsson",null,"25/9/20: WID:RP-200804->RP-201646; 29/9/21: WID:RP-201646->RP-211857; 6/1/22: WID:RP-211857->RP-212906; 5/4/22: WID:RP-212906->RP-220816",null,88,45,null,null,"2020-07-28","2022-04-05"]
[1239,880179,"   Core part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Core",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1240,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1241,880081,"Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits","LTE_B24_mod",1,"Rel-17",null,"2020-06-15","2021-12-15",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: WID:RP-201356->RP-211507",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1242,880181,"   Core part: LTE_B24_mod","LTE_B24_mod-Core",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1243,880281,"   Perf. part: LTE_B24_mod","LTE_B24_mod-Perf",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1244,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","2021-06-15","2021-12-15",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1245,0,"Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A1246+1","v":1246},880087,"LTE iterbCA for 2 bands DL with 1 band UL","LTE_CA_R17_2BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221389",null,"Qualcomm",null,"25/9/20: WID:RP-201248->RP-201754; 6/1/21: WID:RP-201754->RP-202573; 7/4/21: WID:RP-202573->RP-210227; 2/7/21: WID:RP-210227->RP-211560; 29/9/21: WID:RP-211560->RP-211859; 6/1/22: WID:RP-211859->RP-212933; 5/4/22: WID:RP-212933->RP-220552; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1247,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1248,880287,"   Perf. part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 6/6/22: Comp ; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1249,880088,"LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221526",null,"Huawei",null,"25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540; 2/7/21: WID:RP-210540->RP-211388; 29/9/21: WID:RP-211388->RP-212192; 6/1/22: WID:RP-212192->RP-213144; 5/4/22: WID:RP-213144->RP-220715; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1250,880188,"   Core part: LTE_CA_R17_3BDL_1BUL","LTE_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221526","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","; 22/3/22: Compl:0%->67%; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1251,880288,"   Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220713","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","6/1/21: stopped at 0%; 22/3/22: Compl:100%->10%; 22/3/22: CD:15/09/2021->10/06/2022 ; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1252,880089,"LTE iterbCA Core for x bands DL (x=4, 5, 6) with 1 band UL","LTE_CA_R17_xBDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221305",null,"Nokia",null,"25/9/20: WID:RP-201245->RP-201911; 6/1/21: WID:RP-201911->RP-202212; 7/4/21: WID:RP-202212->RP-210837; 2/7/21: WID:RP-210837->RP-211068; 29/9/21: WID:RP-211068->RP-211885; 6/1/22: WID:RP-211885->RP-212813; 5/4/22: WID:RP-212813->RP-220175; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1253,880189,"   Core part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1254,880289,"   Perf. part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1255,880090,"LTE iterbCA for 2 bands DL with 2 bands UL","LTE_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221528",null,"Huawei",null,"25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542; 2/7/21: WID:RP-210542->RP-211390; 29/9/21: WID:RP-211390->RP-212194; 5/4/22: WID:RP-212194->RP-220718; 12/7/22: WID:RP-220718->RP-221528",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1256,880190,"   Core part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","; 22/3/22: Compl:0%->70%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1257,880290,"   Perf. part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","22/3/22: CD:15/09/2021->12/06/202222/3/22: Stat Rep: ->RP-220716 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1258,880091,"LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL","LTE_CA_R17_xBDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221188",null,"LG",null,"25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200; 2/7/21: WID:RP-210200->RP-211041; 29/9/21: WID:RP-211041->RP-211748; 6/1/22: WID:RP-211748->RP-212874; 5/4/22: WID:RP-212874->RP-220295; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1259,880191,"   Core part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1260,880291,"   Perf. part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1261,0,"Release 17 other Studies","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1262,840021,"Stopped - Study on the Usage of User Identifiers in the 5G System ","FS_UUI5",1,"Rel-17","S2","2019-06-06","2020-06-12",1,"SP-190450",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; 21/1/22: stopped at 0%; 21/1/22: 0%->100","New ; 23.700-094; ",84,43,null,null,"2019-05-31","2022-01-21"]
[1263,830031,"Stopped - Study on service-based support for SMS in 5GC","FS_SB_SMS",1,"Rel-17","S2","2019-03-07","2019-12-05",1,"SP-190184",null,"George Foti ","George dot Foti at ericsson dot com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,null,null,"2019-03-14","2022-01-21"]
[1264,830034,"Stopped - Study on UPF enhancement for control and SBA","FS_UPCAS",1,"Rel-17","S2","2019-03-07","2020-03-06",1,"SP-190187",null,"Dan Wang, China Mobile","wangdanyjy@chinamobile.com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,null,null,"2019-03-14","2022-01-21"]
[1265,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"2020-09-10","2022-03-12"]
[1266,900020,"Study on enhanced Security Aspects of the 5G Service Based Architecture ","FS_eSBA_SEC",1,"Rel-17","S3","2020-12-04","2021-12-10",0.75,"SP-201021",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","10/2/21: 33.875 added;; 19/3/21: 0%->45; 19/3/21: FCD:11/06/2021->09/21; 11/6/21: 45%->70; 11/6/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->75",33.875,90,46,null,null,"2020-12-04","2022-06-04"]
[1267,880004,"Stopped - Study on security aspects of the Disaggregated gNB Architecture ","FS_disagg_gNB_Sec",1,"Rel-17","S3","2020-06-25","2021-03-12",1,"SP-200349",null,"Sen XU, China Telecom ","xusen@chinatelecom.cn ","12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100. 13/7/22: marked as stopped (was already at 100%!) as per e-mail from Mirko on 02/06/22 14.03",33.840000000000003,88,45,null,null,"2020-06-25","2021-03-19"]
[1268,810037,"Study on SECAM and SCAS for 3GPP virtualized network products","FS_VNP_SECAM_SCAS",1,"Rel-17","S3","2018-10-02","2021-12-10",1,"SP-180696",null,"Minpeng Qi, China Mobile","qiminpeng@chinamobile.com","2/10/18: Moved from Rel-17¦7/12/18: 0%->5¦20/3/19: 5%->20; 13/9/19: 20%->30; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 30%->35; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 35%->60; 5/12/20: 60%->70; ","New",81,41,null,null,"2018-09-06","2021-09-13"]
[1269,820010,"Study on Long Term Key Update Process (LTKUP) Detailed solutions","FS_LTKUP_Detail",1,"Rel-17","S3","2018-12-13","2020-03-12",1,"SP-181038",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100",null,82,42,null,null,"2018-12-06","2020-06-26"]
[1270,880011,"Study on 5G Glass-type AR/MR Devices ","FS_5GSTAR",1,"Rel-17","S4","2020-06-25","2022-03-11",1,"SP-200399",null,"Hakju Ryan Lee ","hakju00.lee@samsung.com ","25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 65%->80; 13/12/21: 80%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100",26.998000000000001,88,45,null,null,"2020-06-25","2022-03-12"]
[1271,850004,"Study on VR Streaming Conformance and Guidelines ","FS_VR_CoGui",1,"Rel-17","S4","2019-09-13","2022-03-11",1,"SP-190642",null,"Igor CURCIO ","igor.curcio@nokia.com ","; 8/10/19: 26.999 added;; 8/10/19: 26.119 added;; 25/3/20: 0%->10; 20/4/20: FCD:12/06/2020->12/20; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 10%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100","New ; 26.999; 26.119",85,43,null,null,"2019-09-13","2022-03-12"]
[1272,900029,"Study on 5G media streaming extensions ","FS_5GMS_EXT",1,"Rel-17","S4","2020-12-04","2022-03-11",1,"SP-200937",null,"Iraj Sodagar, Company, Tencent ","irajs@live.com ","21/3/21: 0%->5; 11/6/21: 5%->40; 2/7/21: 26.804 added;; 13/9/21: 40%->50; 13/12/21: 50%->60; 13/12/21: FCD:Wed 08/09/->03/22; 12/3/22: 60%->100",26.803999999999998,90,46,null,null,"2020-12-03","2022-03-12"]
[1273,870015,"Study on Streaming Architecture extensions For Edge processing ","FS_EMSA",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200056",null,"Bouazizi, Imed, Qualcomm ","bouazizi@qti.qualcomm.com ","10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100",null,87,44,null,null,"2019-12-06","2021-06-11"]
[1274,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-17","S4","2020-03-25","2022-09-12",0.8,"SP-200054",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1 ",26.925000000000001,87,44,null,null,"2019-12-06","2022-06-04"]
[1275,870011,"Study on 5G Video Codec Characteristics ","FS_5GVideo",1,"Rel-17","S4","2020-03-25","2022-06-10",1,"SP-200052",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->75; 13/12/21: 75%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->90; 12/3/22: FC ",null,87,44,null,null,"2019-12-06","2022-06-04"]
[1276,870012,"Study on the use of NBMP in FLUS ","FS_FLUS_NBMP",1,"Rel-17","S4","2020-03-25","2021-09-08",1,"SP-200053",null,"Iraj Sodagar","irajsodagar@tencent.com ","; 10/6/20: 0%->10; 5/12/20: 10%->30; 5/12/20: FCD:11/12/2020->09/20; 21/3/21: 30%->40; 11/6/21: 40%->96; 13/9/21: 96%->100",26.939,87,44,null,null,"2019-12-06","2021-09-13"]
[1277,911032,"Study on enhanced IMS to 5GC Integration Phase 2 ","FS_eIMS5G2",1,"Rel-17","ct","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15","23.700-10",88,45,null,null,"2020-06-26","2021-03-21"]
[1278,880024,"   CT1 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 13/9/21: 15%->60; 13/12/21: 60%->90; 12/3/22: FCD:08/09/2021->3/22; 12/3/22: 90%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1279,911036,"   CT3 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C3","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 0%->5; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 5%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1280,911033,"   CT4 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C4","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 30%->40; 11/6/21: 40%->30; 14/6/21: 30%->40; 13/9/21: 40%->50; 13/9/21: FCD:Wed 08/09/->12/21; 13/ ","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1281,890002,"Study on Port Number Allocation Alternatives for New 3GPP Interfaces ","FS_PortAl",1,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-220391",null,"Giorgi Gulbani, Huawei","giorgi.gulbani@huawei.com ","13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->85; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 85%->100; 22/3/22: WID:CP-202243->CP-220391",null,89,45,null,null,"2020-09-11","2022-03-22"]
[1282,880075,"Study on scenarios and requirements of in-coverage, partial coverage, and out-of-coverage NR positioning use cases","FS_NR_pos_cov",1,"Rel-17","RP","2020-06-22","2021-09-15",1,"RP-201518",null,"LG Electronics",null,"25/9/20: WID:RP-201384->RP-201518; 29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1283,860062,"Study on XR (Extended Reality) evaluations for NR","FS_NR_XR_eval",1,"Rel-17","R1","2019-12-16","2021-12-21",1,"RP-210460","RP-212047","Qualcomm",null,"affects: NR.; 28/7/20: WID:RP-193241->RP-201145; 7/4/21: WID:RP-201145->RP-210460; 13/9/21: Compl:0%->70% ; 6/1/22: 70%->100",null,86,44,null,null,"2020-01-14","2022-01-06"]
[1284,860039,"Study on enhancement of RAN slicing for NR","FS_NR_slice",1,"Rel-17","R2","2019-12-16","2020-12-15",1,"RP-201612",null,"CMCC",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193254->RP-201612; 2/7/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1285,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","2020-06-22","2022-03-22",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"2020-07-28","2022-04-05"]
[1286,880077,"Study on high-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands 5 and 12 and NR band n71","FS_LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2020-03-19","2020-03-19",1,"RP-201261",null,"Nokia",null,"25/9/20: 37.880 added;; 2/7/21: 0%->100",37.880000000000003,88,45,null,null,"2020-07-28","2021-07-02"]
[1287,900058,"Study on high power UE (power class 2) for one NR FDD band ","FS_NR_PC2_UE_FDD",1,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-212892","RP-211854","China Unicom ",null,"TR 38.8xx ; 13/9/21: Compl:0%->100%; 13/9/21: CD:Wed 08/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP- ; 29/9/21: 100%->100; 6/1/22: WID:RP-202870->RP-212892",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1288,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","2020-12-14","2021-09-08",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1289,890021,"Study on charging aspects of 5GS CIoT ","FS_5G_CIoT_CH",1,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200771",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","5/12/20: 0%->15; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 15%->30; 13/9/21: 30%->70; 13/9/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->100",null,89,45,null,null,"2020-09-10","2022-06-04"]
[1290,0,"--- RELEASE 16 ---","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1291,0,"Release 16 Features and related studies","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1292,0,"Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC)","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1293,830098,"Enhancement of URLLC support in the 5G Core network","5G_URLLC",1,"Rel-16",null,"2017-12-15","2021-06-11",1,"SP-181122",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-03-14"]
[1294,790008,"   Study on enhancement of URLLC supporting in 5GC ","FS_5G_URLLC",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180118",null,"Hui Ni, Huawei","Hui.ni@huawei.com","7/6/18: 0%->15¦6/8/18: 23.725 added;¦10/9/18: 15%->60¦7/12/18: 60%->85¦14/3/19: 85%->90; 31/5/19: 90%->95; 13/9/19: 95%->100","23.xyz; 23.725",79,40,null,null,"2018-03-15","2019-09-13"]
[1295,810036,"   Study on the security of URLLC for 5GS ","FS_5G_URLLC_SEC",2,"Rel-16","S3","2018-09-06","2019-06-12",1,"SP-180910",null,"Rong Wu, Huawei Technologies","Raina.wu@huawei.com","7/12/18: 0%->20¦20/3/19: FCD:019->06/19¦20/3/19: 20%->65; 31/5/19: 65%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1296,820019,"   Stage 2 of 5G_URLLC ","5G_URLLC",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181233",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1297,840026,"   Security of URLLC for 5GS ","5G_URLLC_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190351",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 6/12/19: FCD:12/12/2019->03/20; 9/4/21: 80%->100",33.500999999999998,84,43,null,null,"2019-05-31","2021-04-09"]
[1298,840005,"   CT Aspects of 5G_URLLC","5G_URLLC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","16/9/19: WID:CP-191063->CP-192022",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1299,870059,"      CT1 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100",null,87,44,null,null,"2019-05-31","2020-03-26"]
[1300,840060,"      CT3 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","29.512; 29.513; 29.514; 29.522; 29.508",84,43,null,null,"2019-05-31","2020-03-26"]
[1301,840061,"      CT4 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","31/5/19: 0%->5; 13/9/19: 5%->20; 6/12/19: 20%->60; 26/3/20: 60%->98; 26/6/20: 98%->100","29.244; 29.502; 29.503; 29.510; 29.281",84,43,null,null,"2019-05-31","2020-06-26"]
[1302,890020,"   Charging enhancement for URLLC ","5G_URLLC",2,"Rel-17","S5","2020-09-16","2021-06-11",1,"SP-200769",null,"Chen, Shan, Huawei ","chenshan@huawei.com ","; 5/12/20: 0%->20; 5/12/20: FCD:12/03/2021->06/20; 21/3/21: 20%->30; 13/9/21: 30%->100","32.255; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1303,780030,"   Stopped - Study on EPC support for Mobility with Low Latency Communication","FS_LLC_Mob",2,"Rel-16","S2","2017-12-15","2018-09-14",1,"SP-171069",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395","new 23.739",78,40,null,null,"2017-12-15","2018-06-07"]
[1304,790009,"   Stopped - Study on enht of systems using EPS for UR and Availability using commodity equipment","FS_EPS_URACE",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180119",null,"Chris Pudney","chris.pudney@vodafone.com","7/6/18: 0%->10¦6/8/18: 23.736 added¦6/6/19: stopped at 10% as per SP-190395; 6/6/19: 10%->100","new; 23.736",79,40,null,null,"2018-03-15","2019-06-06"]
[1305,830074,"Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC)","NR_L1enh_URLLC",1,"Rel-16","R1","2018-06-15","2022-12-22",0.96,"RP-191584",null,"Huawei",null,"26/6/19: WID:RP-190726->RP-191584",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1306,800095,"   Study on physical layer enhancements for NR UR Low Latency Cases","FS_NR_L1enh_URLLC",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181477",null,"Huawei",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1307,830174,"   Core part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Core",2,"Rel-16","R1","2019-03-01","2020-03-01",1,"RP-190726",null,"Huawei",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1308,830274,"   Perf. part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-190726",null,"Huawei",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[1309,900054,"   UE Conformance Test Aspects - Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-UEConTest",2,"Rel-16","R5","2020-12-14","2022-12-22",0.9,"RP-202566","RP-221485","Chunying GU, Huawei","guchunying@huawei.com","tested: REL-16 WI NR_L1enh_URLLC-Core ; 8/4/21: 0%->5; 2/7/21: 5%->16; 22/3/22: Compl:16 ; 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[{"$f":"A1310+1","v":1310},830080,"Support of NR Industrial Internet of Things (IoT)","NR_IIOT",1,"Rel-16","R2","2018-06-15","2022-03-11",0.99,"RP-192590",null,"Nokia",null,"26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1311,810060,"   Study on channel modeling for indoor industrial scenarios","FS_IIIOT_CM",2,"Rel-16","R1","2018-09-14","2019-09-13",1,"RP-182138",null,"Ericsson",null,"8/10/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-10-08"]
[1312,800098,"   Study on NR Industrial Internet of Things (IoT)","FS_NR_IIOT",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181479",null,"Nokia",null,"TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100",38.825000000000003,80,41,null,null,"2018-06-27","2019-03-26"]
[1313,830180,"   Core part: Support of NR Industrial Internet of Things (IoT)","NR_IIOT-Core",2,"Rel-16","R2","2019-03-01","2020-03-01",1,"RP-200797",null,"Nokia",null,"28/7/20: WID:RP-192590->RP-200797; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1314,880067,"   UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT)","NR_IioT-UEConTest",2,"Rel-16","R5","2020-06-22","2022-03-11",1,"RP-200757","RP-220623","CMCC",null,"8/10/20: 0%->5; 8/4/21: 5%->68; 2/7/21: 68%->77; 13/9/21: Compl:77%->95%; 13/9/21: C ; 29/9/21: WID:RP-200757->RP-211786; 6/1/22: WID:RP-211786->RP-212943; ",null,88,45,null,null,"2020-07-28","2022-03-22"]
[1315,820999,"5GS Enhanced support of Vertical and LAN Services","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",82,42,null,null,"2014-08-29","2014-08-29"]
[1316,750004,"Study on Communication for Automation in Vertical Domains","FS_CAV",1,"Rel-16","S1","2017-03-02","2018-03-15",1,"SP-170169",null,"Walewski, Joachim, Siemens AG","joachim.walewski@siemens.com ","7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100",22.803999999999998,75,38,null,null,"2017-03-02","2018-06-07"]
[1317,800007,"Service requirements for cyber-physical control applications in vertical domains","cyberCAV",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180321",null,"Joachim W. Walewski (Siemens)",null,"10/9/18: 5%->40¦4/12/18: 40%->100","22.261; 22.104",80,41,null,null,"2018-06-06","2018-12-04"]
[1318,830042,"5GS Enhanced support of Vertical and LAN Services","Vertical_LAN",1,"Rel-16",null,"2018-06-06","2020-03-12",0.99,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com",null,null,82,42,null,null,"2018-12-06","2018-06-14"]
[1319,800028,"   Study on 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180507",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","10/9/18: 0%->25¦7/12/18: 25%->88¦14/3/19: 88%->92; 31/5/19: 92%->100",23.734000000000002,80,41,null,null,"2018-06-06","2019-05-31"]
[1320,820017,"   Stage 2 of Vertical_LAN","Vertical_LAN",2,"Rel-16","S2","2018-12-13","2019-06-24",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-12-06"]
[1321,810038,"   Study on Security for 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN_SEC",2,"Rel-16","S3","2018-09-06","2019-12-12",1,"SP-180697",null,"Jerichow, Anja (Nokia) ","anja.jerichow@nokia.com ","7/12/18: 0%->10¦20/3/19: FCD:019->06/19¦20/3/19: 10%->65; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->78; 6/12/19: 78%->92; 25/3/20: 92%->100","New",81,41,null,null,"2018-09-06","2020-03-25"]
[1322,840027,"   Security for Vertical_LAN ","Vertical_LAN_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190352",null,"Jerichow, Anja, Nokia ","anja.jerichow@nokia.com ","13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100",33.500999999999998,84,43,null,null,"2019-05-31","2020-06-26"]
[1323,830010,"   CT aspects of Vertical_LAN","Vertical_LAN",2,"Rel-16","ct","2019-03-14","2020-03-12",0.99,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272",null,83,42,null,null,"2018-12-06","2019-12-09"]
[1324,830035,"      CT1 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->20; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 20%->75; 6/12/19: 75%->90; 26/3/20: 90%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.368; 24.501; 24.526",83,42,null,null,"2018-12-06","2020-09-13"]
[1325,830036,"      CT3 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-201174",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174","29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061",83,42,null,null,"2018-12-06","2020-06-26"]
[1326,830037,"      CT4 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->5; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 5%->50; 6/12/19: 50%->85; 26/3/20: 85%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.509; 29.510; 29.518; 29.571; 29.244; 29.281",83,42,null,null,"2018-12-06","2020-06-26"]
[1327,850048,"Service Enabler Architecture Layer for Verticals","SEAL",1,"Rel-16",null,"2019-03-07","2020-06-12",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 8/10/19: 33.434 added;; 8/10/19: 24.548 added;","new 23.434; 33.434; 24.548; 24.547",85,42,null,null,"2018-12-06","2019-10-08"]
[1328,820027,"   Stage 2 of SEAL","SEAL",2,"Rel-16","S6","2019-03-07","2019-08-29",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 13/9/19: 0%->100","new 23.434",82,42,null,null,"2018-12-06","2019-09-13"]
[1329,850019,"   Security aspects of SEAL","SEAL",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190901",null,"Rajavelsamy Rajadurai (Samsung) ","rajvel@samsung.com ","; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1330,850006,"   CT aspects of SEAL ","SEAL",2,"Rel-16","ct","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ",null,"New ",85,43,null,null,"2019-09-13","NA"]
[1331,850049,"      CT1 aspects of SEAL ","SEAL",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 6/12/19: 0%->60; 6/12/19: 60%->60; 26/3/20: 60%->80; 26/6/20: 80%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1332,850050,"      CT3 aspects of SEAL ","SEAL",3,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 26/3/20: 0%->75; 26/6/20: 75%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1333,820067,"NR-based access to unlicensed spectrum","NR_unlic",1,"Rel-16","R1","2017-03-15","2019-12-15",0.74,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834",null,82,42,null,null,"2019-01-16","2020-09-25"]
[1334,750045,"   Study on NR-based access to unlicensed spectrum","FS_NR_unlic",2,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181339",null,"Qualcomm",null,"TR 38.8XX19/6/17: WID: RP-170828->RP-171416¦30/6/17: 32.889 added;¦19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%¦27/6/18: Compl:10%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦16/1/19: 40%->100",32.889000000000003,75,38,null,null,"2017-03-21","2019-01-16"]
[1335,820167,"   Core part: NR-based access to unlicensed spectrum","NR_unlic-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[1336,820267,"   Perf. part: NR-based access to unlicensed spectrum","NR_unlic-Perf",2,"Rel-16","R4","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 2/7/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-07-02"]
[1337,911003,"   UE Conformance Test Aspects - NR-based access to unlicensed spectrum ","NR_unlic-UEConTest",2,"Rel-16","R5","2021-03-12","2022-12-22",0.2,"RP-210708","RP-221249","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","tested: REL-16 WI NR_unlic-Core ; 2/7/21: 0%->5 ; ; 6/6/22: Compl:18%->20% ; ; 20/6/22: Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1338,800006,"LAN support in 5G","5GLAN",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","11/3/22: 99%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2022-03-11"]
[1339,760007,"   Study on LAN Support in 5G ","FS_5GLAN",2,"Rel-16","S1","2017-06-05","2018-03-15",1,"SP-170456",null,"Nasielski, Jack, Qualcomm Incorporated","jackn@qti.qualcomm.com","11/9/17: 0%->35¦15/12/17: 35%->65¦16/3/18: 65%->100","22.821; ",76,39,null,null,"2017-06-03","2018-03-16"]
[1340,800047,"   Stage 1 of 5GLAN","5GLAN",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","10/9/18: 40%->75¦10/9/18: FCD:09/18->12/18¦4/12/18: 75%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2018-12-04"]
[1341,830024,"Study on non-public networks management","FS_OAM_NPN",1,"Rel-16","S5","2019-03-07","2020-06-12",1,"SP-190137",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com","31/5/19: 0%->2; 13/9/19: 2%->10; 26/3/20: 10%->70; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-06-28"]
[1342,0,"Cellular IoT support and evolution ","-",1,"Rel-16",null,"2016-06-18","2016-06-18",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1343,830043,"Cellular IoT support and evolution for the 5G System","5G_CIoT",1,"Rel-16",null,"2017-09-08","2020-06-12",0.99,"SP-181118",null,null,null,null,null,83,42,null,null,"2018-12-06","NA"]
[1344,770038,"   Study on 5G_CIoT","FS_CIoT_5G",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180614",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","11/09/17: rapporteur change¦15/12/17: 23.724 added;¦16/3/18: 0%->20¦7/6/18: 20%->50¦15/6/18: WID:SP-170801->SP-180614¦15/6/18: FCD:09/18->12/18¦10/9/18: 50%->70¦7/12/18: 70%->95; 31/5/19: 95%->100","New; 23.724",77,39,null,null,"2017-09-08","2019-05-31"]
[1345,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[1346,830013,"   CT aspects of 5G_CIoT","5G_CIoT",2,"Rel-16","ct","2019-03-14","2020-03-12",0.99,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 9/12/19: WID:CP-111237->CP-193274; 25/3/20: WID:CP-193274->CP-200147",null,83,42,null,null,"2018-12-06","2020-03-25"]
[1347,830038,"      CT1 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->40; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 40%->60; 6/12/19: 60%->85; 26/3/20: 85%->92; 26/6/20: 92%->99; 13/9/20: 99%->100","23.122; 24.250; 24.301; 24.368; 24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1348,830039,"      CT3 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100","29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514",83,42,null,null,"2018-12-06","2020-06-26"]
[1349,830040,"      CT4 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->10; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 10%->25; 6/12/19: 25%->60; 26/3/20: 60%->90; 26/6/20: 90%->100","23.008; 29.274; 29.502; 29.503; 29.505; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[1350,830041,"      CT6 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C6","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 26/3/20: 0%->100","TBD",83,42,null,null,"2018-12-06","2020-03-26"]
[1351,850014,"   Security of 5G_CIoT","5G_CIoT",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190897",null,"Henrik Normann, Ericsson ","henrik.normann@ericsson.com ","6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1352,800033,"Study on evolution of Cellular IoT security for the 5G System","FS_CIoT_sec_5G",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180440",null,"Noamen Ben Henda ","noamen.ben.henda@ericsson.com","6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100","New; 33.861",80,41,null,null,"2018-06-06","2020-06-26"]
[1353,760040,"Study on MBMS User Services for IoT","FS_MBMS_IoT",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170592",null,"Cedric thienot, Expway","cedric (dot) thienot (at) expway (dot) com","11/9/17: 0%->10¦15/12/17: 10%->30¦16/3/18: 30%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->90¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 90%->100","26.8xx",76,39,null,null,"2017-06-03","2018-09-10"]
[1354,800083,"Additional MTC enhancements for LTE","LTE_eMTC5",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦16/1/19: WID:RP-181450->RP-182891¦26/3/19: WID:RP-182891->RP-190770; 26/6/19: WID:RP-190770->RP-191356; 14/1/20: WID:RP-191356->RP-192875",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1355,800183,"   Core part: Additional MTC enhancements for LTE","LTE_eMTC5-Core",2,"Rel-16","R1","2018-06-15","2019-12-15",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1356,800283,"   Perf. part: Additional MTC enhancements for LTE","LTE_eMTC5-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"26/3/19: WID:RP-182891->RP-190770; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1357,800084,"Additional enhancements for NB-IoT","NB_IOTenh3",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1358,800184,"   Core part: Additional enhancements for NB-IoT","NB_IOTenh3-Core",2,"Rel-16","R1","2018-06-15","2019-12-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦26/3/19: WID:RP-182902->RP-190757; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1359,800284,"   Perf. part: Additional enhancements for NB-IoT","NB_IOTenh3-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"26/3/19: WID:RP-182902->RP-190757; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1360,810050,"5G message service","5GMSG",1,"Rel-16","S1","2016-06-18","2018-12-14",1,"SP-180772",null,null,null,null,22.262,81,41,null,null,"2018-09-06","NA"]
[1361,770004,"   Study on 5G message service for MIoT","FS_5GMSG",2,"Rel-16","S1","2016-06-18","2018-09-14",1,"SP-170704",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","15/12/17: 22.824 added;¦15/12/17: 0%->25¦16/3/18: 25%->60¦10/9/18: 60%->95¦4/12/18: 95%->100","New; 22.824",77,39,null,null,"2017-09-08","2018-12-04"]
[1362,810014,"   Message Service Within the 5G System requirements ","MSGin5G",2,"Rel-16","S1","2018-09-06","2018-12-14",1,"SP-180920",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","4/12/18: 0%->100","22.262; 22.261",81,41,null,null,"2018-09-06","2021-06-11"]
[1363,0,"Advanced V2X support","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1364,790002,"Study on Improvement of V2X Service Handling ","FS_V2XIMP",1,"Rel-16","S1","2018-03-15","2018-06-14",1,"SP-180247",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100",22.885999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[1365,820024,"Improvement of V2X service Handling ","V2XIMP",1,"Rel-16","S1","2018-10-25","2018-12-04",1,"SP-181013",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","4/12/18: 0%->95¦14/3/19: 95%->100",22.186,82,42,null,null,"2018-12-04","2019-03-14"]
[1366,840074,"Application layer support for V2X services ","V2XAPP",1,"Rel-16",null,"2017-12-15","2020-03-12",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65","New",84,41,null,null,"2018-09-06","2019-03-14"]
[1367,780025,"   Study on V2XAPP","FS_V2XAPP",2,"Rel-16","S6","2017-12-15","2018-09-14",1,"SP-171071",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100",null,78,40,null,null,"2017-12-15","2018-12-07"]
[1368,810020,"   Stage 2 of V2XAPP","V2XAPP",2,"Rel-16","S6","2018-09-06","2019-06-14",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65; 31/5/19: 65%->95; 13/9/19: 95%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1369,840010,"   CT aspects of V2XAPP ","V2XAPP",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191153->CP-192077",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1370,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[1371,840076,"      CT3 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->60; 26/3/20: 60%->100","29.122; 29.116",84,43,null,null,"2019-05-31","2020-03-26"]
[1372,840077,"      CT4 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100","23.003; 23.008",84,43,null,null,"2019-05-31","2020-03-26"]
[1373,840078,"Architecture enhancements for 3GPP support of advanced V2X services","eV2XARC",1,"Rel-16",null,"2017-06-05","2020-03-12",0.99,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30","23.501; 23.502; 23.503; 23.285",84,43,null,null,"2018-12-06","2019-03-14"]
[{"$f":"A1374+1","v":1374},760043,"   Study on eV2XARC","FS_eV2XARC",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180733","SP-170412","LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","11/9/17: 0%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170379->SP 170590¦16/3/18: 20%->25¦7/6/18: 25%->35¦10/9/18: 35%->58¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP 170590->SP-180733¦7/12/18: 58%->88¦14/3/19: 88%->95; 31/5/19: 95%->100",23.786000000000001,76,39,null,null,"2017-06-03","2019-05-31"]
[1375,820018,"   Stage 2 of eV2XARC","eV2XARC",2,"Rel-16","S2","2018-12-13","2019-06-14",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100","23.501; 23.502; 23.503; 23.285; 24.588",82,42,null,null,"2018-12-06","2020-03-25"]
[1376,840011,"   CT aspects of eV2XARC ","eV2XARC",2,"Rel-16","ct","2019-06-06","2020-03-12",0.99,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191154->CP-192078; 25/3/20: WID:CP-192078->CP-200291; 2/7/20: WID:CP-200291->CP-201343",null,84,43,null,null,"2019-05-31","2020-07-02"]
[1377,840079,"      CT1 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.501; 24.301; 27.007",84,43,null,null,"2019-05-31","2020-09-13"]
[1378,840080,"      CT3 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 26/3/20: 80%->90; 26/6/20: 90%->100; 26/6/20: WID:CP-200291->CP-201199","29.512; 29.513; 29.514; 29.519; 29.122; 29.522",84,43,null,null,"2019-05-31","2020-06-26"]
[1379,840081,"      CT4 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571",84,43,null,null,"2019-05-31","2020-06-26"]
[1380,840082,"      CT6 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C6","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100",31.102,84,43,null,null,"2019-05-31","2020-03-26"]
[1381,860014,"   Security Aspects of eV2XARC","eV2XARC",2,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191125",null,"Dongjoo Kim, LG Electronics Inc. ","dongjoo7.kim@lge.com ","; 6/12/19: 0%->10; 25/3/20: 10%->70; 26/6/20: 70%->95; 12/9/20: 95%->98; 5/12/20: 98%->99; 19/3/21: 99%->100","33.220, TS 33.536",86,44,null,null,"2019-12-06","2021-03-19"]
[1382,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1383,770029,"Study on V2X Media Handling and Interaction","FS_mV2X",1,"Rel-16","S4","2017-09-08","2019-09-12",1,"SP-170799",null,"Jung, Kyunghun, Samsung Electronics Co., Ltd","kyunghun.jung@samsung.com","15/12/17: 26.985 added;¦15/12/17: 0%->30¦16/3/18: 30%->50¦22/3/18: FCD:09/18->12/18¦7/6/18: 50%->60. 14/06/18: Moved from Rel-15¦10/9/18: 60%->80¦13/12/18: 80%->60¦13/12/18: FCD:12/18->09/19¦12/3/19: 60%->70; 31/5/19: 70%->80; 26/6/20: 80%->100","New; 26.985",77,39,null,null,"2017-09-08","2020-06-26"]
[1384,830023,"Study on Security Aspects of 3GPP support for Advanced V2X Services ","FS_eV2X_Sec",1,"Rel-16","S3","2019-03-07","2020-03-12",1,"SP-190108",null,"Joonwoong Kim, LG Electronics","joonwoong.kim@lge.com","31/5/19: 0%->20; 13/9/19: 20%->60; 13/9/19: FCD:05/09/2019->12/20; 6/12/19: 60%->75; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 75%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[1385,830078,"5G V2X with NR sidelink","5G_V2X_NRSL",1,"Rel-16","R1","2019-03-01","2022-12-22",0.75,"RP-200129",null,"LG Electronics",null,"26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1386,830178,"   Core part: 5G V2X with NR sidelink","5G_V2X_NRSL-Core",2,"Rel-16","R1","2019-03-01","2020-03-01",1,"RP-200129",null,"LG Electronics",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1387,830278,"   Perf. part: 5G V2X with NR sidelink","5G_V2X_NRSL-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200129",null,"LG Electronics",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1388,880069,"   UE Conformance Test Aspects - 5G V2X with NR sidelink","5G_V2X_NRSL_eV2XARC-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-22",0.49,"RP-221484","RP-221482","Xuesong Wang, Huawei Technologies. Co., Ltd","wangxuesong743@huawei.com","8/10/20: 0%->5; 8/4/21: 5%->11; 2/7/21: 11%->18; 22/3/22: Compl:18%->43%; ; 5/4/22: WID:RP-200894->RP-220744 ; ; 20/6/22: Rapporteur: Huawei->Xuesong Wang, Huawei Technologies. Co., Ltd; Rap eMail: ->wangxuesong743@huawei.com; ; 12/7/22: WID:RP-20089...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1389,0,"5G Location and Positionning Services","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1390,800013,"5G positioning services","5G_HYPOS",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ",null,22.260999999999999,80,41,null,null,"2018-06-06","NA"]
[1391,760006,"   Study on positioning use cases","FS_5G_HYPOS",2,"Rel-16","S1","2017-06-05","2018-06-15",1,"SP-170589",null,"Ries, Lionel, ESA ","lionel.ries@esa.int","11/9/17: 0%->10¦15/12/17: 10%->50¦15/12/17: FCD:03/18->06/18¦16/3/18: 50%->75¦7/6/18: 75%->90¦10/9/18: 90%->100",22.872,76,39,null,null,"2017-06-03","2018-09-10"]
[1392,800049,"   Stage 1 of 5G_HYPOS","5G_HYPOS",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ","10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1393,830102,"Enhancement to the 5GC LoCation Services","5G_eLCS",1,"Rel-16",null,"2017-12-15","2020-06-12",0.98,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn",null,"23.501; 23.502",83,42,null,null,"2018-12-06","NA"]
[1394,780028,"   Study on Enhancement to the 5GC Location Services","FS_eLCS",2,"Rel-16","S2","2017-12-15","2019-03-14",1,"SP-180734",null,"Ming Ai, CATT","aiming@catt.cn","16/3/18: 0%->15¦7/6/18: 15%->45¦10/9/18: 45%->55¦10/9/18: FCD:12/18->03/19¦2/10/18: WID:SP-170937->SP-180734¦7/12/18: 55%->100","new 23.731",78,40,null,null,"2017-12-15","2018-12-07"]
[1395,810035,"   Study on Security of the enhancement to the 5GC location services","FS_eLCS_Sec",2,"Rel-16","S3","2018-09-06","2019-12-13",1,"SP-180694",null,"Wei Zhou, CATT","zhouwei@catt.cn","7/12/18: 0%->5¦20/3/19: 5%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1396,820016,"   Stage 2 of 5G_eLCS","5G_eLCS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn","14/3/19: 0%->45; 31/5/19: 45%->85; 26/6/19: 29.515 added;; 13/9/19: 85%->100","23.501; 23.502; 29.515",82,42,null,null,"2018-12-06","2019-09-13"]
[1397,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",0.95,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1398,830044,"      CT1 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 13/9/19: 0%->40; 6/12/19: 40%->90; 26/6/20: 90%->99; 13/9/20: 99%->100","24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1399,830045,"      CT3 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C3","2019-03-07","2019-12-05",0.85,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85","29.522; 29.122",83,42,null,null,"2018-12-06","2020-06-26"]
[1400,830046,"      CT4 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100","24.080; 29.518; 29.572; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-06-26"]
[1401,850017,"   Security of 5G_eLCS","5G_eLCS",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190900",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 6/12/19: 0%->75; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 75%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1402,830077,"NR positioning support","NR_pos",1,"Rel-16","R1","2018-06-15","2022-12-22",0.92,"RP-192581",null,"Intel",null,"26/6/19: WID:RP-190752->RP-191156; 14/1/20: WID:RP-191156->RP-192581",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1403,800092,"   Study on NR positioning support","FS_NR_pos",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181399",null,"Intel",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1404,830073,"   Study on local NR positioning in NG-RAN","FS_NR_local_pos",2,"Rel-16","R3","2019-03-01","2019-12-15",1,"RP-191774",null,"CMCC",null,"8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100",38.856000000000002,83,42,null,null,"2019-03-26","2020-01-14"]
[1405,830177,"   Core part: NR positioning support","NR_pos-Core",2,"Rel-16","R1","2019-03-01","2020-03-01",1,"RP-192581",null,"Intel",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1406,830277,"   Perf. part: NR positioning support","NR_pos-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-192581",null,"Intel",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1407,900057,"   UE Conformance Test Aspects - NR positioning support ","NR_pos-UEConTest",2,"Rel-16","R5","2020-12-14","2022-12-22",0.75,"RP-221450","RP-221451","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5; 29/9/21: WID:RP-202727->RP-212227; 22/3/22: Compl:5%->54%; ; 20/6/22: Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; ; 12/7/22: WID:RP-212227->RP-221450",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1408,0,"UE radio capability signalling optimization","-",1,"Rel-16",null,"2018-06-06","2018-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1409,840054,"Optimisations on UE radio capability signalling","RACS",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"RP-191460",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","26/6/19: WID:SP-190180->RP-191460","23.501; 23.502; 23.401",84,43,null,null,"2019-03-14","2019-06-26"]
[1410,800025,"   Study on RACS","FS_RACS",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180599",null,"Haris Zisimopoulos, Qualcomm Incorporated ","harisz@qti.qualcomm.com","10/9/18: 0%->40¦7/12/18: 40%->70¦14/3/19: 70%->100","New",80,41,null,null,"2018-06-06","2019-03-14"]
[1411,830027,"   Stage 2 of RACS","RACS",2,"Rel-16","S2","2019-03-07","2019-06-06",1,"SP-190180",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","31/5/19: 0%->90; 26/6/19: 29.673 added;; 13/9/19: 90%->100","23.501; 23.502; 23.401; 29.673",83,42,null,null,"2019-03-14","2019-09-13"]
[1412,840003,"   CT aspects of RACS","RACS",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","17/9/19: WID:CP-191061->CP-192207; 25/3/20: WID:CP-192207->CP-200058",null,84,43,null,null,"2019-05-31","2020-03-25"]
[1413,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[1414,840056,"      CT3 aspects of RACS","RACS",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->90; 26/3/20: 90%->100","29.122; 29.522",84,43,null,null,"2019-05-31","2020-03-26"]
[1415,840057,"      CT4 aspects of RACS","RACS",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->20; 6/12/19: 20%->75; 26/3/20: 75%->90; 26/6/20: 90%->100","23.003; 23.008; 29.230; 29.274; 29.510; 29.518",84,43,null,null,"2019-05-31","2020-06-26"]
[1416,830079,"Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN",1,"Rel-16","R2","2018-06-15","2022-12-22",0.93,"RP-200164",null,"MediaTek",null,"26/3/20: WID:RP-190657->RP-200164",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1417,800097,"   Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects","FS_RACS_RAN",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181459",null,"MediaTek",null,"TR 37.873¦related SA2 SI FS_RACS was started at SA #80 ¦6/8/18: 37.873 added;¦26/3/19: 0%->100",37.872999999999998,80,41,null,null,"2018-06-27","2019-03-26"]
[1418,830179,"   Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN-Core",2,"Rel-16","R2","2019-03-01","2020-03-01",1,"RP-200164",null,"MediaTek",null,"26/6/19: WID:RP-190657->RP-191088; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1419,880073,"   UE Conformance Test Aspects - Optimisations on UE radio capability signalling - NR/E-UTRA Aspects","RACS-UEConTest",2,"Rel-16","R5","2020-03-19","2022-12-22",0.89,"RP-201152","RP-221246","Qualcomm",null,"8/10/20: 0%->5; 7/4/21: WID:RP-201153->RP-210714; 8/4/21: 5%->25; 8/4/21: FCD:19/03/2021->09/21; 2/7/21: 25%->50; 22/3/22: ; 5/4/22: WID:RP-210714->RP-220434 ; ",null,88,45,null,null,"2020-07-28","2022-06-06"]
[1420,800099,"Study on solutions for NR to support non-terrestrial networks (NTN)","FS_NR_NTN_solutions",1,"Rel-16","R3","2018-06-15","2019-12-15",1,"RP-221169",null,"Thales",null,"TR 38.8xx¦compare REL-15 SI FS_NR_nonterr_nw¦26/3/19: WID:RP-181370->RP-190710; 14/1/20: 0%->100; 2/7/21: WID:RP-190710->RP-211557; 29/9/21: WID:RP-211557->RP-211784; 6/1/22: WID:RP-211784->RP-213691; 12/7/22: WID:RP-213691->RP-221169",null,80,41,null,null,"2018-06-27","2022-07-12"]
[1421,0,"Enablers for Network Automation Architecture for 5G","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1422,830047,"Enablers for Network Automation for 5G ","eNA",1,"Rel-16",null,"2017-06-05","2020-03-12",0.99,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1423,760047,"   Study of enablers for Network Automation for 5G ","FS_eNA",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180792",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","16/3/18: FCD:09/18->06/18¦16/3/18: 0%->15¦7/6/18: 15%->30¦15/6/18: WID:SP-170383->SP-180613¦15/6/18: FCD:06/18->09/18¦10/9/18: 30%->50¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-180613->SP-180792¦7/12/18: 50%->90¦14/3/19: 90%->94; 31/5/19: 94%->100","new 23.791",76,39,null,null,"2017-06-03","2019-05-31"]
[1424,820020,"   Stage 2 of eNA","eNA",2,"Rel-16","S2","2018-12-06","2019-06-17",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 26/6/19: 29.517 added;; 13/9/19: 85%->92; 6/12/19: 92%->97; 25/3/20: 97%->100","23.501; 23.502; 23.503; 29.517",82,42,null,null,"2018-12-06","2020-03-25"]
[1425,830009,"   CT aspects of eNA","eNA",2,"Rel-16","ct","2019-03-07","2020-03-12",0.99,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1426,830048,"      CT3 aspects of eNA","eNA",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->55; 6/12/19: 55%->85; 6/12/19: FCD:05/12/2019->03/20; 26/3/20: 85%->100","29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[1427,830049,"      CT4 aspects of eNA","eNA",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100","29.244; 29.510; 29.518; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-03-26"]
[1428,0,"Wireless and Wireline Convergence Enhancement ","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1429,760044,"Study on the Wireless and Wireline Convergence for the 5G system architecture ","FS_5WWC",1,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-170380",null,"Marco Spini, Huawei Technologies","m.spini@huawei.com","11/9/17: 0%->15¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 15%->25¦7/6/18: 25%->35¦10/9/18: 35%->60¦10/9/18: FCD:06/18->12/18¦7/12/18: 60%->100",23.716000000000001,76,39,null,null,"2017-06-03","2018-12-07"]
[1430,800031,"Study on the security of the Wireless and Wireline Convergence for the 5G system architecture","FS_5WWC_SEC",1,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180438",null,"He Li, Huawei Technologies","LIHE2@HUAWEI.COM","6/8/18: 33.807 added;¦10/9/18: 0%->5¦7/12/18: 5%->30¦20/3/19: 30%->60¦20/3/19: FCD:019->09/19; 31/5/19: 60%->75; 8/10/19: 75%->100","New; 33.807",80,41,null,null,"2018-06-06","2019-10-08"]
[1431,830050,"Wireless and Wireline Convergence for the 5G system architecture","5WWC",1,"Rel-16",null,"2018-12-06","2020-06-12",0.99,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1432,820014,"   Stage 2 of 5WWC","5WWC",2,"Rel-16","S2","2018-12-06","2019-06-13",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1433,830015,"   CT aspects of 5WWC","5WWC",2,"Rel-16","ct","2019-03-07","2020-03-12",0.99,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156. Confusion with UID (was 829910 instead of 830015); 17/9/19: WID:CP-191156->CP-192079; 9/12/19: WID:CP-192079->CP-193145; 2/7/20: WID:CP-193145->CP-192079",null,83,42,null,null,"2018-12-06","2020-07-02"]
[1434,829911,"      CT1 aspects of 5WWC","5WWC",3,"Rel-16","C1","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100","24.501; 24.502; 24.526",82,42,null,null,"2018-12-06","2020-06-30"]
[1435,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[1436,829914,"      CT4 aspects of 5WWC","5WWC",3,"Rel-16","C4","2019-06-13","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 0%->5; 6/12/19: 5%->60; 26/3/20: 60%->95; 26/6/20: 95%->100","23.003; 29.518; 29.502; 29.509; 29.244; 29.503; 29.571; 29.505",82,42,null,null,"2018-12-06","2020-06-26"]
[1437,850015,"   Security of 5WWC","5WWC",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190898",null,"He Li, Huawei Technologies ","lihe2@huawei.com ","13/9/19: 0%->100; 8/10/19: 100%->0; 6/12/19: 0%->90; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 90%->95; 26/6/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[{"$f":"A1438+1","v":1438},860019,"   Charging Aspect for 5WWC ","5WWC",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191188",null,"ZHU, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","32.240; 32.255; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-06-28"]
[1439,830082,"   NG interface usage for WWC","5WWC-NG_interface",2,"Rel-16","R3","2019-03-01","2019-12-15",1,"RP-190772",null,"Huawei",null,null,null,83,42,null,null,"2019-03-26","NA"]
[1440,830182,"      Core part: NG interface usage for WWC","5WWC-NG_interface-Core",3,"Rel-16","R3","2019-03-01","2019-12-15",1,"RP-190999",null,"Huawei",null,"26/6/19: WID:RP-190772->RP-190999; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1441,0,"Mission Critical, Public Warning, Railways and Maritime","-",1,"Rel-16",null,"2016-09-19","2016-09-19",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1442,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[1443,800024,"Study into discreet listening and logging for mission critical services","FS_MCLOG",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-181138",null,"Chater-Lea, David, Motorola Solutions","david.chater-lea@motorolasolutions.com","6/8/18: 23.784 added;¦10/9/18: 0%->10¦7/12/18: 10%->50¦7/12/18: FCD:03/19->06/19¦14/12/18: WID:SP-180384->SP-181138¦14/3/19: 50%->75; 31/5/19: 75%->100","New; 23.784",80,41,null,null,"2018-06-06","2019-05-31"]
[1444,800022,"Enhanced Mission Critical Push-to-talk architecture phase 2","enh2MCPTT",1,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[1445,860026,"   Stage 2 of enh2MCPTT ","enh2MCPTT",2,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100; 1/7/20: 0%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2020-07-01"]
[1446,860003,"   CT aspects of enh2MCPTT ","enh2MCPTT-CT",2,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193148",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","; 26/3/20: 0%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484 ",86,44,null,null,"2019-12-06","2020-03-26"]
[1447,830051,"Enhancements to Functional architecture and information flows for Mission Critical Data","eMCData2",1,"Rel-16","S6","2018-06-06","2020-03-12",0.99,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40",null,83,42,null,null,"2018-06-06","2018-12-07"]
[1448,800018,"   Stage 2 of eMCData2","eMCData2",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40¦14/3/19: 40%->75; 31/5/19: 75%->90; 13/9/19: 90%->100","23.280; 23.282",80,41,null,null,"2018-06-06","2019-09-13"]
[1449,830014,"   CT aspects of eMCData2","eMCData2",2,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193146",null,"Val Oprescu (AT&T)","vo4887@att.com ","31/5/19: 0%->15; 13/9/19: 15%->25; 17/9/19: WID:CP-190199->CP-192081; 6/12/19: 25%->55; 9/12/19: FCD:12/12/2019->03/20; 9/12/19: WID:CP-192081->CP-193146; 26/3/20: 55%->70; 26/6/20: 70%->100","24.282; 24.582; 24.483; 24.484; 24.zzz",83,42,null,null,"2018-06-06","2020-06-26"]
[1450,850051,"MCData File Distribution support over xMB","MC_XMB",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,85,43,null,null,"2018-09-06","2019-05-31"]
[1451,810004,"   Stage 2 of MC_XMB","MC_XMB",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,81,41,null,null,"2018-09-06","2019-05-31"]
[1452,850007,"   CT aspects of MC_XMB","MC_XMB-CT",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192253",null,"Wenliang Xu, Ericsson ","wenliang.xu@ericsson.com ","; 6/12/19: 0%->90; 26/3/20: 90%->100",29.116,85,43,null,null,"2019-09-13","2020-03-26"]
[1453,810011,"Protocol enhancements for Mission Critical Services","MCProtoc16",1,"Rel-16","C1","2018-09-06","2019-12-20",1,"CP-182110",null,"AXELL, Jörgen","jorgen.axell@ericsson.com","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980",81,41,null,null,"2018-09-06","2020-03-26"]
[1454,800053,"MBMS APIs for Mission Critical Services","MBMSAPI_MCS",1,"Rel-16","S6","2017-06-05","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com",null,"New",80,41,null,null,"2018-06-06","NA"]
[1455,760051,"   Study on MBMS APIs for MC Services","FS_MBMSAPI_MC",2,"Rel-16","S6","2017-06-05","2018-06-15",1,"SP-180237",null,"Ling Zhang, TD Tech Ltd","zhangling@td-tech.com","12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100","new 23.792",76,39,null,null,"2017-06-03","2018-06-14"]
[1456,800020,"   Stage 2 of MBMS APIs for MC Services","MBMSAPI_MCS",2,"Rel-16","S6","2018-06-06","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com","6/8/18: 23.479 added;¦10/9/18: 0%->15¦7/12/18: 15%->65¦14/3/19: 65%->90; 31/5/19: 90%->100","New; 23.479",80,41,null,null,"2018-06-06","2019-05-31"]
[1457,840013,"Enhancement of 3GPP Northbound APIs ","eNAPIs",1,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: WID:CP-192184->CP-193175","29.122; 29.222; 29.522; 29.116 ",84,43,null,null,"2019-05-31","2019-12-09"]
[1458,850053,"   CT3 aspects of eNAPIs","eNAPIs",2,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 6/12/19: 50%->85; 6/12/19: WID:CP-192184->CP-193175; 26/3/20: 85%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[1459,850059,"   CT4 aspects of eNAPIs","eNAPIs",2,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[1460,800019,"Enhanced Mission Critical System Migration and Interconnection","eMCSMI",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-180379",null,"Chater-Lea, David; Motorola Solutions","david.chater-lea@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->10¦7/12/18: FCD:03/19->06/19¦14/3/19: 10%->50; 31/5/19: 50%->100. ","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[1461,810054,"Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",1,"Rel-16",null,"2018-06-06","2019-06-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com",null,null,80,41,null,null,"2018-09-10","NA"]
[1462,800021,"   Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180680",null,"Monnes, Peter, Harris Corporation","pmonnes at harris dot com ","10/9/18: 0%->5¦2/10/18: WID:SP-180381->SP-180680¦7/12/18: 5%->15¦14/3/19: 15%->40; 31/5/19: 40%->70; 13/9/19: 70%->100",23.283000000000001,80,41,null,null,"2018-06-06","2019-09-13"]
[1463,800016,"Stage 3 for MC Communication Interworking with Land Mobile Radio Systems","MCCI_CT",1,"Rel-16","C1","2018-06-06","2019-09-12",1,"CP-190203",null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com","10/9/18: 5%->15¦7/12/18: 15%->45¦10/12/18: FCD:12/18->06/19¦10/12/18: WID:CP-181187->CP-183247. 06/03/19: both name and acronym changed (was MCCI3)¦14/3/19: 45%->60¦18/3/19: WID:CP-183248->CP-190203¦18/3/19: FCD:019->09/19; 31/5/19: 60%->70; 13/9/19: 7 ","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482",80,41,null,null,"2018-06-06","2020-03-26"]
[1464,800032,"Mission Critical Services Security Enhancements","MCXSec",1,"Rel-16","S3","2018-06-06","2020-06-11",1,"SP-180596",null,"Woodward, Tim, Motorola Solutions, Inc",null,"10/9/18: 0%->40¦7/12/18: 40%->50¦20/3/19: FCD:019->09/19¦20/3/19: 50%->0; 31/5/19: 0%->45; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 45%->55; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 55%->75; 26/6/20: 75%->80; 12/9/20: FCD:12/03/2020->06/20; 9/4/21: 80% ",33.18,80,41,null,null,"2018-06-06","2021-04-09"]
[1465,780003,"Enhancements of Public Warning System ","ePWS",1,"Rel-16",null,"2016-09-19","2020-03-12",0.99,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[1466,730005,"   Study on enhancements of Public Warning System","FS_ePWS",2,"Rel-16","S1","2016-09-19","2017-09-14",1,"SP-160733",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->5¦2/3/17: 5%->45¦7/6/17: 45%->75¦30/6/17: 22.869 added;¦25/8/17: 75%->95¦15/12/17: 95%->100",22.869,73,37,null,null,"2016-09-19","2017-12-15"]
[1467,800052,"   Stage 1 of ePWS","ePWS",2,"Rel-16","S1","2017-12-15","2018-12-14",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[1468,810012,"   CT aspects of enhancements of Public Warning System ","ePWS",2,"Rel-16","ct","2018-09-06","2020-03-12",0.99,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155",null,81,41,null,null,"2018-09-06","2019-06-03"]
[1469,810053,"      Study on stages 2 and 3 of enhancements of ePWS","ePWS",3,"Rel-16","C1","2018-09-10","2019-06-14",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","7/12/18: 0%->10¦21/3/19: 10%->30; 31/5/19: 30%->85; 3/6/19: WID:CP-182228->CP-191155; 13/9/19: 85%->100","New",81,41,null,null,"2018-09-10","2019-09-13"]
[1470,810047,"      CT1 aspects of ePWS ","ePWS",3,"Rel-16","C1","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","14/3/19: 0%->30; 3/6/19: FCD:14/06/2019->03/20; 3/6/19: WID:CP-182228->CP-191155; 20/9/19: 0%->100; 6/12/19: 100%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",23.041,81,41,null,null,"2018-09-06","2020-06-26"]
[1471,810048,"      deleted- CT4 aspects of ePWS (Possible impacts)","ePWS",3,"Rel-16","C4","2018-09-06","2019-12-13",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155; 16/9/19: 0%->100",29.167999999999999,81,41,null,null,"2018-09-06","2019-09-16"]
[1472,760054,"Mobile Communication System for Railways 2","MONASTERY2",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 10%->35","New 22.289; 22.280; 22.281; 22.282; 22.179",76,42,null,null,"2017-06-03","2017-12-15"]
[1473,760005,"   Study on MONASTERY2","FS_FRMCS2",2,"Rel-16","S1","2017-06-05","2019-06-14",1,"SP-170588",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 35%->50¦16/3/18: 50%->80¦7/6/18: 80%->85¦10/9/18: FCD:06/18->06/19¦4/12/18: 85%->100","New 22.889",76,39,null,null,"2017-06-03","2018-12-04"]
[1474,790023,"   Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2","FS_FRMCS2_SA6",2,"Rel-16","S6","2018-03-15","2019-03-12",1,"SP-181133",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","19/4/18: 0%->5¦14/6/18: 5%->15¦6/8/18: 23.796 added;¦10/9/18: 15%->20¦7/12/18: 20%->65¦7/12/18: FCD:12/18->03/19¦14/3/19: 65%->100","23.cde; 23.796",79,40,null,null,"2018-03-15","2019-03-14"]
[1475,760004,"   Stage 1 of MONASTERY2","MONASTERY2",2,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","16/3/18: 35%->55¦7/6/18: 55%->70¦7/6/18: FCD:06/18->12/18¦10/9/18: 70%->75¦4/12/18: 75%->100","New 22.289; 22.280; 22.281; 22.282; 22.179",76,39,null,null,"2017-06-03","2018-12-04"]
[1476,830007,"   Application Architecture for MONASTERY2","MONASTERY2",2,"Rel-16","S6","2019-03-14","2019-06-13",1,"SP-190064",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","31/5/19: 0%->100","23.280; 23.379; 23.281; 23.282",83,42,null,null,"2019-03-14","2019-05-31"]
[1477,840009,"   CT aspects of MONASTERY2 ","MONASTERY2",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","9/12/19: WID:CP-191152->CP-193143",null,84,43,null,null,"2019-05-31","2019-12-09"]
[1478,840072,"      CT1 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/19: 0%->10; 6/12/19: 10%->50; 26/3/20: 50%->65; 26/6/20: 65%->100","24.379 ; 24.281 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.581; 24.582",84,43,null,null,"2019-05-31","2020-06-26"]
[1479,840073,"      deleted: CT3 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","2/7/20: deleted, put at 100% (was at 0)",29.164999999999999,84,43,null,null,"2019-05-31","NA"]
[1480,840092,"NR support for high speed train scenario","NR_HST",1,"Rel-16","R4","2019-06-17","2022-06-22",0.99,"RP-191788",null,"CMCC",null,"8/10/19: WID:RP-191512->RP-191788",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1481,840192,"   Core part: NR support for high speed train scenario","NR_HST-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-191788",null,"CMCC",null,"28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1482,840292,"   Perf. part: NR support for high speed train scenario","NR_HST-Perf",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-202320",null,"CMCC",null,"6/1/21: WID:RP-191788->RP-202320; 6/1/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-01-06"]
[1483,900050,"   UE Conformance Test Aspects - NR support for high speed train scenario ","NR_HST-UEConTest",2,"Rel-16","R5","2020-12-14","2022-06-22",1,"RP-221362","RP-221361","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-16 WI NR_HST-Core ; 7/4/21: WID:RP-202328->RP-210372; 8/4/21: 0%->39; 2/7/21: 39%->41; 13/9/21: Compl:41%->44%; ; ; ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 12/7/22: WID:RP-202328->RP-221362",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1484,800011,"Maritime Communication Services over 3GPP System","MARCOM",1,"Rel-16","S1","2016-09-19","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com",null,"22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","NA"]
[1485,730007,"   Study on Maritime Communication Services over 3GPP system","FS_MARCOM",2,"Rel-16","S1","2016-09-19","2018-06-15",1,"SP-170453",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->10¦2/3/17: 10%->15¦2/3/17: WID:SP-160556->SP-170166¦10/3/17: FCD:06/17->06/20¦21/3/17: 22.819 added;¦8/6/17: WID:SP-170166->SP-170453¦25/8/17: 15%->35¦15/12/17: 35%->55¦16/3/18: 55%->75¦7/6/18: 75%->95¦10/9/18: 95%->100",22.818999999999999,73,37,null,null,"2016-09-19","2018-09-10"]
[1486,800051,"   Stage 1 of MARCOM","MARCOM",2,"Rel-16","S1","2018-06-06","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com","10/9/18: 0%->70¦4/12/18: 70%->95¦14/3/19: 95%->100","22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","2019-03-14"]
[1487,0,"Streaming and TV","-",1,"Rel-16",null,"2016-12-01","2019-06-05",0.68,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1488,800008,"Enhancement of LTE for Efficient delivery of Streaming Service","eLSTR",1,"Rel-16","S1","2016-12-01","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn",null,"22.278; 22.115",80,41,null,null,"2018-06-06","NA"]
[1489,740001,"   Study on eLSTR","FS_eLESTR",2,"Rel-16","S1","2016-12-01","2018-03-15",1,"SP-160960",null,"China Telecommunications, XIA Xu","xiaxu@ctbri.com.cn","2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100",22.832999999999998,74,38,null,null,"2016-12-01","2018-03-16"]
[1490,800054,"   Stage 1 of eLSTR","eLSTR",2,"Rel-16","S1","2018-05-08","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn","15/6/18: FCD:06/18->09/18¦10/9/18: 90%->100","22.278; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[1491,800001,"Enhancements to Framework for Live Uplink Streaming","E_FLUS",1,"Rel-16","S4","2018-06-06","2020-07-03",0.95,"SP-180285",null,"Lo, Charles, Qualcomm Incorporated","clo@qti.qualcomm.com","10/9/18: 0%->20¦7/12/18: 20%->40¦7/3/19: 40%->45¦7/3/19: FCD:03/19->09/19; 31/5/19: 45%->55; 13/9/19: FCD:20/09/2019->12/20; 13/9/19: 55%->75; 6/12/19: 75%->85; 25/3/20: 85%->90; 25/3/20: FCD:12/12/2019->06/20; 10/6/20: 90%->100; 26/6/20: FCD:12/06/202 ","26.238; 26.939",80,41,null,null,"2018-06-06","2020-06-26"]
[1492,810003,"Coverage and Handoff Enhancements for Multimedia ","CHEM",1,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180664",null,"Nikolai Leung","nleung@qti.qualcomm.com","7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[1493,770027,"Study on QoE metrics for VR","FS_QoE_VR",1,"Rel-16","S4","2017-09-08","2019-09-20",1,"SP-170614",null,"Ericsson (Gunnar Heikkilä","gunnar.heikkila@ericsson.com","15/12/17: 26.929 added;¦15/12/17: 26.119 added;¦15/12/17: FCD:06/18->09/18¦15/12/17: 0%->10¦16/3/18: 10%->15¦7/6/18: 15%->20¦7/6/18: FCD:09/18->12/18. 14/06/18: Moved from Rel-15¦10/9/18: 20%->25¦12/3/19: 25%->55¦12/3/19: FCD:12/18->09/19; 31/5/19: 55% ","New; 26.929; 26.119",77,39,null,null,"2017-09-08","2019-05-31"]
[1494,760039,"Study on 5G enhanced Mobile Broadband Media Distribution","FS_5GMedia_Distribution",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170334",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd., ","i (dot) Bouazizi (at) Samsung (dot) com ","11/9/17: 0%->10¦15/12/17: FCD:03/18->06/20¦15/12/17: 10%->25¦16/3/18: 25%->60¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->75; 26/6/20: 75%->100; 25/9/20: 26.998 added;","26.8xx; 26.998",76,39,null,null,"2017-06-03","2020-09-25"]
[1495,820002,"Media streaming architecture ","5GMSA",1,"Rel-16","S4","2018-12-06","2019-06-12",1,"SP-180984",null,"Frédéric GABIN ","Frederic.gabin@ericsson.com ","; 31/5/19: 0%->100","26.501; 26.233 ",82,42,null,null,"2018-12-07","2019-05-31"]
[1496,840000,"VR QoE metrics ","VRQoE",1,"Rel-16","S4","2019-06-06","2020-03-12",1,"SP-190331",null,"Gunnar HEIKKILÄ ","gunnar.heikkila@ericsson.com ","22.280¦22.281¦22.282¦22.179¦22.289 ; 13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2020-03-25"]
[1497,810040,"Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",1,"Rel-16","S4","2017-06-05","2019-12-12",1,"SP-180663",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[1498,760041,"   Study on Media Handling Aspects of Conversational Services in 5G Systems","FS_5G_MEDIA_MTSI",2,"Rel-16","S4","2017-06-05","2018-09-15",1,"SP-170336",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","11/9/17: 0%->5¦15/12/17: 5%->35¦16/3/18: 35%->55¦16/3/18: FCD:03/18->09/18¦7/6/18: 55%->80. 14/06/18: Moved from Rel-15¦10/9/18: 80%->100",26.919,76,39,null,null,"2017-06-03","2018-09-10"]
[1499,810002,"   Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",2,"Rel-16","S4","2018-09-06","2019-12-12",1,"SP-190640",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->35¦7/3/19: 35%->50; 31/5/19: 50%->75; 13/9/19: 75%->80; 13/9/19: FCD:13/09/2019->12/20; 19/9/19: WID:SP-180663->SP-190640; 6/12/19: 80%->90; 25/3/20: 90%->100","26.114; 26.131; 26.132; 26.223; 26.919",81,41,null,null,"2018-09-06","2020-03-25"]
[1500,770031,"Study on EVS Float Conformance Non Bit-Exact","FS_EVS_FCNBE",1,"Rel-16","S4","2017-09-08","2018-09-14",1,"SP-170618",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100","New; 26.843",77,39,null,null,"2017-09-08","2018-09-10"]
[1501,820001,"EVS Floating-point Conformance for Non Bit-Exact ","EVS_FCNBE",1,"Rel-16","S4","2018-06-06","2019-12-12",1,"SP-180983",null,"Fabrice, Plante, Intel ","fabrice.m.plante@intel.om ","¦7/3/19: 0%->25¦7/3/19: 0%->25¦7/3/19: 0%->25. CANNOT CHANGE STARTING DATE… Real one: Thu 06/12/18; 31/5/19: 25%->50; 13/9/19: 50%->80; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 80%->100",26.443999999999999,82,42,null,null,"2018-06-06","2019-12-06"]
[{"$f":"A1502+1","v":1502},800003,"Addition of HLG HDR to TV Video Profiles","HLG_HDR",1,"Rel-16","S4","2018-06-06","2018-09-14",1,"SP-180287",null,"Paul Szucs, Sony Europe Limited","paul.szucs@sony.com","10/9/18: 0%->100","26.116; 26.346; 26.234",80,41,null,null,"2018-06-06","2018-09-10"]
[1503,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1504,800012,"User Identities and Authentication","UIA",1,"Rel-16","S1","2017-12-15","2018-09-14",1,"SP-180328",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at",null,"22.101; 22.115",80,41,null,null,"2018-06-06","NA"]
[1505,780004,"   Study on a Layer for User Centric Identifiers and Authentication","FS_LUCIA",2,"Rel-16","S1","2017-12-15","2018-06-14",1,"SP-170995",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","16/3/18: 0%->60¦7/6/18: 60%->90¦10/9/18: 90%->100",22.904,78,40,null,null,"2017-12-15","2018-09-10"]
[1506,800050,"   Stage 1 of User Identities and Authentication","UIA",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180328",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","10/9/18: 0%->100","22.101; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[1507,810044,"Multi-device and multi-identity","MuD",1,"Rel-16",null,"2018-06-06","2020-06-15",0.99,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com",null,null,80,41,null,null,"2018-06-06","NA"]
[1508,800004,"   Stage 1 of Multi-device and multi-identity","MuD",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com","10/9/18: 85%->90¦4/12/18: 90%->100",22.172999999999998,80,41,null,null,"2018-06-06","2018-12-04"]
[1509,810010,"   CT aspects of Multi-device and multi-identity","MuD",2,"Rel-16","ct","2018-09-06","2020-06-15",0.99,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","9/12/19: WID:CP-182227->CP-193273; 25/3/20: WID:CP-193273->CP-200148",null,81,41,null,null,"2018-06-06","2020-03-25"]
[1510,810045,"      CT1 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C1","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->10¦14/3/19: 10%->15; 31/5/19: 15%->35; 13/9/19: 35%->65; 6/12/19: 65%->85; 25/3/20: FCD:14/06/2019->03/20; 26/3/20: 85%->100; 2/7/20: FCD:25/03/2020->06/20","24.173; 24.229; 24.167",81,41,null,null,"2018-06-06","2020-07-02"]
[1511,810046,"      CT3 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C3","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->5; 13/9/19: 5%->95; 6/12/19: 95%->98; 26/3/20: 98%->100; 2/7/20: FCD:25/03/2020->06/20",29.164999999999999,81,41,null,null,"2018-06-06","2020-07-02"]
[1512,0,"Slicing","-",1,"Rel-16",null,"2017-09-08","2017-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1513,830103,"Enhancement of Network Slicing","eNS",1,"Rel-16",null,"2018-03-15","2022-09-12",0.94,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com",null,null,83,42,null,null,"2018-12-06","NA"]
[1514,790011,"   Study on Enhancement of Network Slicing","FS_eNS",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180503",null,"ZTE, Tricci So ","tso at ztetx dot com","7/6/18: 0%->10¦15/6/18: WID:SP-180121->SP-180503¦6/8/18: 23.740 added;¦10/9/18: 10%->50¦7/12/18: 50%->85¦7/12/18: 85%->¦14/3/19: 85%->100","new; 23.740",79,40,null,null,"2018-03-15","2019-03-14"]
[1515,820023,"   Stage 2 of eNS","eNS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com","14/3/19: 0%->60; 31/5/19: 60%->100",null,82,42,null,null,"2018-12-06","2019-05-31"]
[1516,830011,"   CT aspects of eNS","eNS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","2/7/20: WID:CP-190196->CP-201161",null,83,42,null,null,"2018-12-06","2020-07-02"]
[1517,830052,"      CT1 aspects of eNS","eNS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","13/9/19: 0%->40; 6/12/19: 40%->85; 26/3/20: 85%->95; 26/6/20: 95%->97; 13/9/20: 97%->100",24.501000000000001,83,42,null,null,"2018-12-06","2020-09-13"]
[1518,830053,"      CT3 aspects of eNS","eNS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","6/12/19: 0%->80; 26/3/20: 80%->98; 26/6/20: 98%->100","29.061; 29.561",83,42,null,null,"2018-12-06","2020-06-26"]
[1519,830054,"      CT4 aspects of eNS","eNS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","31/5/19: 0%->30; 13/9/19: 30%->50; 6/12/19: 50%->95; 26/3/20: 95%->85 (went down); 26/6/20: 85%->100","29.502; 29.503; 29.505; 29.509; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[1520,810034,"   Study on Security aspects of Enhancement of Network Slicing","FS_eNS_SEC",2,"Rel-16","S3","2018-09-06","2020-03-12",1,"SP-180692",null,null,"Suresh.p.nair@nokia.com","7/12/18: 0%->15¦20/3/19: 15%->65¦20/3/19: FCD:019->06/19; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New",81,41,null,null,"2018-09-06","2020-06-26"]
[1521,850022,"   Security aspects of Enhanced Network Slicing ","eNS",2,"Rel-16","S3","2019-09-19","2021-06-11",1,"SP-190712",null,"Suresh.p.nair@nokia.com ",null,"; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 30%->95; 12/9/20: 95%->97; 19/3/21: FCD:12/06/2020->06/21; 11/6/21: 97%->100","New ",85,43,null,null,"2019-09-13","2021-06-11"]
[1522,910099,"   UE Conformance Test Aspects - Enhancement of Network Slicing ","eNS-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-12",0.67,"RP-211443","R5-220262","CMCC ",null,"tested: CT1 and SA3 REL-16 WI eNS (Enhancement of Network Slicing); compare REL-17 SI FS_NR_slice; 2/7/21: 0%->15; 13/9/21: Compl:15%->47%; ; 6/1/22: 47%->100 ; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1523,810051,"Business Role Models for Network Slicing ","BRMNS",1,"Rel-16","S1","2017-09-08","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com",null,22.260999999999999,81,41,null,null,"2018-09-06","NA"]
[1524,770005,"   Study on Business Role Models for Network Slicing ","FS_BMNS",2,"Rel-16","S1","2017-09-08","2018-09-14",1,"SP-180169",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100","New; 22.830",77,39,null,null,"2017-09-08","2018-12-04"]
[1525,810015,"   Business Role Models for Network Slicing ","BRMNS",2,"Rel-16","S1","2018-09-06","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","10/9/18: 0%->95¦4/12/18: 95%->100",22.260999999999999,81,41,null,null,"2018-09-06","2018-12-04"]
[1526,810022,"Study on tenancy concept in 5G networks and network slicing management","FS_TENANCYC",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180815",null,"ZHU, Lei (Huawei","Lei.zhu@huawei.com ","7/12/18: 0%->20¦14/3/19: 20%->26; 31/5/19: 26%->40; 13/9/19: 40%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1527,810031,"Enhancement of performance assurance for 5G networks including network slicing","5G_SLICE_ePA",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2019-05-31"]
[1528,850055,"   Overall aspects of 5G_SLICE_ePA","5G_SLICE_ePA",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70; 13/9/19: 70%->85; 13/9/19: 85%->; 26/3/20: 85%->97; 28/6/20: 97%->100","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2020-06-28"]
[1529,850029,"   KPI reporting ","5G_SLICE_ePA-KPI",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190881",null,"ZHU, Weihong, ZTE Corporation ","zhu.weihong@zte.com.cn ","; 26/3/20: 0%->100","28.550; 28.554; 28.622; 28.532 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1530,820029,"Study on Charging Aspects of Network Slicing ","FS_NETSLICE_CH",1,"Rel-16","S5","2018-12-13","2019-12-12",1,"SP-181065",null,"Chen Shan, Huawei","chenshan@huawei.com ","14/3/19: 0%->30¦14/3/19: FCD:06/19->09/19; 31/5/19: 30%->45; 13/9/19: 45%->85; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 85%->100",null,82,42,null,null,"2018-12-07","2019-12-06"]
[1531,0,"Other cross-TSG Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1532,760003,"Provision of Access to Restricted Local Operator Services by Unauthenticated UEs","PARLOS",1,"Rel-16",null,"2016-12-01","2019-12-13",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16","22.115; 22.101; 22.228",76,38,null,null,"2017-06-03","2017-06-07"]
[1533,740002,"   Study on Stage 1 of PARLOS","FS_PARLOS",2,"Rel-15","S1","2016-12-01","2018-09-10",1,"SP-160904",null,"Covell, Betsy","betsy.covell@nokia.com","1/12/16: 0%->75¦2/3/17: 75%->100¦10/9/18: FCD:03/17->09/18",22.82,74,38,null,null,"2016-12-01","2018-09-10"]
[1534,760046,"   Study on Stage 2 for PARLOS","FS_PARLOS_SA2",2,"Rel-16","S2","2017-06-05","2018-09-14",1,"SP-180501",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com","11/9/17: 0%->20¦16/3/18: FCD:12/17->12/18.¦16/3/18: 20%->45¦23/3/18: WID:SP-170382->SP-180116¦23/3/18: FCD:12/18->06/18¦7/6/18: 45%->70¦15/6/18: WID:SP-180116->SP-180501¦15/6/18: FCD:06/18->09/18¦10/9/18: 70%->100",23.715,76,39,null,null,"2017-06-03","2018-09-10"]
[1535,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[1536,760071,"   Stage 1 of PARLOS","PARLOS",2,"Rel-16","S1","2017-05-10","2017-06-08",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","7/6/17: 0%->100","22.115; 22.101; 22.228",76,39,null,null,"2017-06-03","2017-06-07"]
[1537,810008,"   Stage 2 of PARLOS","PARLOS",2,"Rel-16","S2","2018-09-06","2019-03-15",1,"SP-180738",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com)","14/3/19: 0%->95; 31/5/19: 95%->100","23.401; 23.203; 23.221; 23.228; 23.167",81,41,null,null,"2018-09-06","2019-05-31"]
[1538,830012,"   CT aspects of PARLOS","PARLOS",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com",null,null,83,42,null,null,"2018-09-06","NA"]
[1539,830062,"      CT1 aspects of PARLOS","PARLOS",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->80; 13/9/19: 80%->95; 6/12/19: 95%->98; 26/3/20: 98%->100","24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007",83,42,null,null,"2018-09-06","2020-03-26"]
[1540,830063,"      CT3 aspects of PARLOS","PARLOS",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","13/9/19: 0%->95; 26/3/20: 95%->100","29.212; 29.213; 29.214",83,42,null,null,"2018-09-06","2020-03-26"]
[1541,830064,"      CT4 aspects of PARLOS","PARLOS",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","6/12/19: 0%->100","29.228; 29.229; 29.274",83,42,null,null,"2018-09-06","2019-12-06"]
[1542,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[1543,860015,"   Security Aspects of PARLOS ","PARLOS",2,"Rel-16","S3","2019-12-06","2019-12-13",1,"SP-191126",null,"Schumacher, Greg, Sprint ","Gregory.schumacher@sprint.com ","; 6/12/19: 0%->100",33.401000000000003,86,44,null,null,"2019-12-06","2019-12-06"]
[1544,820043,"Enhancing Topology of SMF and UPF in 5G Networks","ETSUN",1,"Rel-16",null,"2017-09-08","2020-03-12",1,"SP-181116",null,null,null,null,null,82,42,null,null,"2018-12-05","NA"]
[1545,770039,"   Study on ETSUN","FS_ETSUN",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180731",null,"Laurent Thiebaut (Nokia)","Laurent.thiebaut@nokia.com","15/12/17: 23.726 added;¦16/3/18: 0%->25¦7/6/18: 25%->40¦10/9/18: 40%->65¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170743->SP-180731¦2/10/18: FCD:12/18->12/18¦7/12/18: 65%->100",23.725999999999999,77,39,null,null,"2017-09-08","2018-12-07"]
[1546,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[1547,830002,"   CT aspects of ETSUN","ETSUN",2,"Rel-16","ct","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,83,42,null,null,"2018-12-05","NA"]
[1548,830055,"      CT3 aspects of ETSUN","ETSUN",3,"Rel-16","C3","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","13/9/19: 0%->80; 6/12/19: 80%->85; 26/3/20: 85%->100","29.508; 29.561",83,42,null,null,"2018-12-05","2020-03-26"]
[1549,830056,"      CT4 aspects of ETSUN","ETSUN",3,"Rel-16","C4","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","31/5/19: 0%->25; 13/9/19: 25%->95; 6/12/19: 95%->100","29.244; 29.502; 29.510; 29.518; 29.281",83,42,null,null,"2018-12-05","2019-12-06"]
[1550,850024,"   Charging aspects of ETSUN ","ETSUN",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190880",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 6/12/19: 0%->70; 26/3/20: 70%->100","32.255; 32.291; 32.298 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1551,820044,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture","ATSSS",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com",null,"23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","NA"]
[1552,760052,"   Study on ATSSS","FS_ATSSS",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180732",null,"So, Tricci, ZTE","tso@ztetx.com","11/9/17: 0%->100¦14/9/17: 100%->10¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 10%->20¦7/6/18: 20%->40¦10/9/18: 40%->70¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170411->SP-180732¦2/10/18: FCD:12/18->12/18¦7/12/18: 70%->100","new 23.793",76,39,null,null,"2017-06-03","2018-12-07"]
[1553,820021,"   Stage 2 of ATSSS","ATSSS",2,"Rel-16","S2","2018-12-14","2019-06-21",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com","14/3/19: 0%->45; 31/5/19: 45%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1554,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[1555,830057,"      CT1 aspects of ATSSS","ATSSS",3,"Rel-16","C1","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->55; 6/12/19: 55%->65; 26/3/20: 65%->70; 26/6/20: 70%->100","24.501; 24.526; 24.502",83,42,null,null,"2018-12-06","2020-06-26"]
[1556,830058,"      CT3 aspects of ATSSS","ATSSS",3,"Rel-16","C3","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->50; 13/9/19: 50%->55; 6/12/19: 55%->60; 26/3/20: 60%->100","29.512; 29.513",83,42,null,null,"2018-12-06","2020-03-26"]
[1557,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[1558,840999,"      (IETF) TCP Extensions for Multipath Operation with Multiple Addresses (draft-ietf-mptcp-rfc6824bis)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,null,null,null,null,"23/4/20: 80%->100; 9/4/21: RFC 8684 added;","RFC 8684",84,43,null,null,"2019-06-26","2021-04-09"]
[1559,840998,"      (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,null,null,null,null,"23/4/20: 30%->90; 25/9/20: 90%->100; 9/4/21: RFC 8803 added;","RFC 8803",84,43,null,null,"2019-06-26","2021-04-09"]
[1560,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1561,810041,"Single radio voice continuity from 5GS to 3G","5G_SRVCC",1,"Rel-16",null,"2018-03-15","2021-12-10",0.99,"SP-180737",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn",null,"23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","NA"]
[1562,790010,"   Study for single radio voice continuity from 5GS to 3G","FS_5G-SRVCC",2,"Rel-16","S2","2018-03-15","2018-06-15",1,"SP-180239",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","7/6/18: 0%->80¦6/8/18: 23.756 added;¦10/9/18: 80%->100",23.756,79,40,null,null,"2018-03-15","2018-09-10"]
[1563,810007,"   Single radio voice continuity from 5GS to 3G","5G_SRVCC",2,"Rel-16","S2","2018-09-06","2019-03-14",1,"SP-180897",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","14/3/19: 0%->100","23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","2019-03-14"]
[1564,820008,"   Security aspects of single radio voice continuity from 5GS to UTRAN ","5GS_UTRAN_SEC",2,"Rel-16","S3","2018-12-13","2019-06-12",1,"SP-190703",null,"Feng Gao, China Unicom ","gaofeng149@chinaunicom.cn ","20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703","33.501; 33.401; 33.220",82,42,null,null,"2018-12-13","2019-09-20"]
[1565,820069,"   RAN aspects of 5G_SRVCC","SRVCC_NR_to_UMTS",2,"Rel-16","R2","2018-12-15","2019-12-15",0.99,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: WID:RP-190713->RP-200151",null,82,42,null,null,"2019-01-16","2020-03-26"]
[{"$f":"A1566+1","v":1566},820169,"      Core part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Core",3,"Rel-16","R2","2018-12-15","2019-12-15",1,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-03-26"]
[1567,830270,"      Perf. part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-200151",null,"China Unicom",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1568,890046,"      UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G ","SRVCC_NR_to_UMTS-UEConTest",3,"Rel-16","R5","2020-09-17","2021-12-10",1,"RP-210400",null,"China Unicom ",null,"tested: REL-16 WI SRVCC_NR_to_UMTS-Core ; 7/4/21: WID:RP-201794->RP-210400; 8/4/21: 0%->31; 8/4/21: FCD:08/09/2021->09/21; 2/7/21: FCD:Fri 10/09/->12/21; 2/7/21: 31%->85; 6/1/22: 85%->100",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1569,840004,"   CT aspect of 5G_SRVCC","5G_SRVCC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","6/12/19: WID:CP-191062->CP-193014",null,84,43,null,null,"2019-05-31","2019-12-06"]
[1570,840058,"      CT1 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","24.501; 24.237; 24.008; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[1571,860027,"      CT3 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","6/12/19: created, 0%->60; 26/3/20: 60%->100",null,86,44,null,null,"2019-05-31","2020-03-26"]
[1572,840059,"      CT4 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100","29.303; 29.503; 29.504; 29.505; 29.518; 29.274",84,43,null,null,"2019-05-31","2020-03-26"]
[1573,790005,"Study on Remote Identification of Uncrewed Aerial Systems","FS_ID_UAS",1,"Rel-16","S1","2018-03-15","2018-09-14",1,"SP-180172",null,"Eddy Hall; Qualcomm Incorporated","edhall@qti.qualcomm.com","7/6/18: 0%->60¦10/9/18: 60%->100",22.824999999999999,79,40,null,null,"2018-03-15","2018-09-10"]
[1574,800034,"Study on Security Aspects of the 5G Service Based Architecture","FS_SBA_Sec",1,"Rel-16","S3","2018-06-06","2020-03-12",1,"SP-180598",null,"Hans Christian Rudolph, Deutsche Telekom AG","hans-christian.rudolph@telekom.de","6/8/18: 33.855 added;¦10/9/18: 65%->75¦7/12/18: 75%->76¦20/3/19: 76%->65¦20/3/19: FCD:018->09/19; 31/5/19: 65%->75; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New; 33.855",80,41,null,null,"2018-06-06","2020-06-26"]
[1575,820045,"Enhancements to the Service-Based 5G System Architecture","5G_eSBA",1,"Rel-16",null,"2018-03-15","2020-06-12",1,"SP-181125",null,null,null,null,null,82,42,null,null,"2018-12-06","NA"]
[1576,790007,"   Study on Enhancements to the Service-Based 5G System Architecture","FS_eSBA",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180231",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","7/6/18: 0%->15¦6/8/18: 23.742 added;¦10/9/18: 15%->60¦7/12/18: 60%->100","23.xxx; 23.742",79,40,null,null,"2018-03-15","2018-12-07"]
[1577,820022,"   Stage 2 of 5G_eSBA","5G_eSBA",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181125",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1578,830001,"   CT aspects of 5G_eSBA","5G_eSBA",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com",null,null,83,42,null,null,"2018-12-06","NA"]
[1579,830060,"      CT3 aspects of 5G_eSBA","5G_eSBA",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com","6/12/19: 0%->30; 26/3/20: 30%->100","29.507; 29.508; 29.513; 29.512; 29.514; 29.519; 29.520; 29.521; 29.523; 29.525; 29.551; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[1580,830061,"      CT4 aspects of 5G_eSBA","5G_eSBA",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com","31/5/19: 0%->10; 13/9/19: 10%->40; 6/12/19: 40%->70; 26/3/20: 70%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.518; 29.531; 29.540; 29.571; 29.572; 29.573",83,42,null,null,"2018-12-06","2020-06-26"]
[1581,850016,"   Security for 5G_eSBA","5G_eSBA",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190899",null,"Nagendra Bykampadi, Nokia ","nagendra.bykampadi@nokia.com ","; 6/12/19: 0%->45; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 45%->70; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 70%->95; 12/9/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-09-12"]
[1582,780029,"Study on Enhanced IMS to 5GC Integration","FS_eIMS5G",1,"Rel-16","S2","2017-12-15","2019-06-14",1,"SP-180736",null,"Joul, Chris, T-Mobile USA","chris <dot> joul <at> t-mobile <dot> com","16/3/18: 0%->20¦7/6/18: 20%->40¦10/9/18: FCD:09/18->06/19¦2/10/18: WID:SP-171052->SP-180736¦14/3/19: 40%->70; 6/12/19: 70%->100","new 23.794",78,40,null,null,"2017-12-15","2019-12-06"]
[1583,840062,"SBA aspects of enhanced IMS to 5GC integration","eIMS5G_SBA",1,"Rel-16",null,"2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,null,"23.501; 23.502; 23.503; 23.228",84,42,null,null,"2019-03-14","NA"]
[1584,830028,"   Stage 2 of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","S2","2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,"31/5/19: 0%->100","23.501; 23.502; 23.503; 23.228",83,42,null,null,"2019-03-14","2019-05-31"]
[1585,840006,"   CT aspects of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","16/9/19: WID:CP-191065->CP-192023",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1586,850056,"      CT1 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","6/12/19: 0%->70; 26/6/20: 70%->100",null,85,43,null,null,"2019-05-31","2020-06-26"]
[1587,840063,"      CT3 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.513; 29.514",84,43,null,null,"2019-05-31","2020-03-26"]
[1588,840064,"      CT4 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->25; 6/12/19: 25%->50; 26/3/20: 50%->90; 26/6/20: 90%->100","29.510; 29.571; 23.380",84,43,null,null,"2019-05-31","2020-06-26"]
[1589,830081,"Private Network Support for NG-RAN","NG_RAN_PRN",1,"Rel-16","R3","2019-03-01","2022-12-22",0.92,"RP-200122",null,"China Telecom",null,"26/3/20: WID:RP-190729->RP-200122",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1590,830181,"   Core part: Private Network Support for NG-RAN","NG_RAN_PRN-Core",2,"Rel-16","R3","2019-03-01","2020-03-01",1,"RP-200122",null,"China Telecom",null,"26/6/19: WID:RP-190729->RP-191563; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1591,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-22",0.89,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1592,810039,"Media Handling Aspects of RAN Delay Budget Reporting in MTSI","E2E_DELAY",1,"Rel-16",null,"2017-12-15","2019-12-12",1,"SP-180662",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[1593,780022,"   Study on E2E_DELAY","FS_E2E_DELAY",2,"Rel-16","S4","2017-12-15","2018-09-14",1,"SP-170837",null,"Oyman, Ozgur, Company: Intel, ","ozgur.oyman@intel.com ","16/3/18: 0%->10¦7/6/18: 10%->60¦10/9/18: 60%->100","new",78,40,null,null,"2017-12-15","2018-09-10"]
[1594,810001,"   Stage 2 of E2E_DELAY","E2E_DELAY",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180662",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->75¦7/3/19: 75%->85¦7/3/19: FCD:03/19->06/19; 31/5/19: 85%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-05-31"]
[1595,830004,"   CT Aspects of E2E_DELAY","E2E_DELAY",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com",null,null,83,42,null,null,"2018-09-06","NA"]
[1596,830066,"      CT1 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100; 13/9/19: 100%->100",24.228999999999999,83,42,null,null,"2018-09-06","2019-09-13"]
[1597,830067,"      CT3 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100",29.161999999999999,83,42,null,null,"2018-09-06","2019-05-31"]
[1598,830068,"      CT4 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100","23.334; 29.334; 29.238; 23.333; 29.333",83,42,null,null,"2018-09-06","2019-05-31"]
[1599,830069,"Enhancements for Common API Framework for 3GPP Northbound APIs ","eCAPIF",1,"Rel-16",null,"2018-03-15","2020-03-12",1,"SP-181137",null,"Basavaraj Pattan, Samsung","basavarajjp@samsung.com ","7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137",23.222000000000001,83,42,null,null,"2018-03-15","2018-12-13"]
[1600,790022,"   Stage 2 for eCAPIF","eCAPIF",2,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181137",null,"Basavaraj Pattan, Samsung","basavarajjp@samsung.com ","7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137¦14/3/19: 45%->80; 31/5/19: 80%->100",23.222000000000001,79,40,null,null,"2018-03-15","2019-05-31"]
[1601,830022,"   Security aspects of eCAPIF","eCAPIF",2,"Rel-16","S3","2019-03-07","2019-12-12",1,"SP-1901240",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","31/5/19: 0%->30; 31/5/19: 0%->30; 31/5/19: 0%->30; 13/9/19: 30%->90; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 90%->100",33.122,83,42,null,null,"2019-03-14","2019-12-06"]
[1602,850008,"   CT aspects of eCAPIF ","eCAPIF",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192254",null,"Narendranath Durga, Tangudu (Samsung) ","n.tangudu {@]samsung.com ","; 6/12/19: 0%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",29.222000000000001,85,43,null,null,"2019-09-13","2020-06-26"]
[1603,840065,"User data interworking, Coexistence and Migration","UDICOM",1,"Rel-16","S2","2019-03-14","2019-06-14",0.99,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ",null,"23.501; 23.502; 23.228",84,42,null,null,"2019-03-14","NA"]
[1604,800055,"   Study on UDICOM","FS_UDICoM",2,"Rel-16","S2","2018-06-15","2019-06-12",1,"SP-190148",null,"Susana Sabater (Vodafone","susana.sabater@vodafone.com","10/9/18: 0%->30¦2/10/18: WID:SP-180620->SP-180735¦7/12/18: 30%->80¦14/12/18: FCD:12/18->03/20¦14/3/19: 80%->100¦21/3/19: WID:SP-181110->SP-190148¦21/3/19: FCD:019->06/19; 13/9/19: 75%->100","23.732; new",80,41,null,null,"2018-06-15","2019-09-13"]
[1605,830029,"   Stage 2 of UDICOM","UDICOM",2,"Rel-16","S2","2019-03-14","2019-06-14",1,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ","6/6/19: 0%->100; 26/6/19: 23.632 added;","23.501; 23.502; 23.228; 23.632",83,42,null,null,"2019-03-14","2019-06-26"]
[1606,840007,"   CT aspects of UDICOM","UDICOM",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193016",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->75; 9/12/19: WID:CP-191066->CP-193016; 26/3/20: 75%->90; 26/6/20: 90%->100","29.503; 29.505; 29.571; 29.510 ",84,43,null,null,"2019-05-31","2020-06-26"]
[1607,910008,"UICC-terminal interface testing for UEs with non-removable UICCs ","nrUICC_UEConTest",1,"Rel-16","C6","2021-03-18","2022-03-11",0.15,"CP-210285",null,"Marquordt, Arne, COMPRION GmbH ","amarquordt@comprion.com ","; 21/3/21: 0%->5; 13/9/21: 5%->10; 13/9/21: FCD:Fri 10/12/->03/22; 4/6/22: 10%->15","31.122; 31.213 ",91,46,null,null,"2021-03-18","2022-06-04"]
[1608,800036,"Study on authentication and key management for applications based on 3GPP credential in 5G","FS_AKMA",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180443",null,"Jin Peng, China Mobile","pengjin@chinamobile.com","6/8/18: 33.835 added;¦7/12/18: 5%->20¦20/3/19: 20%->60¦20/3/19: FCD:019->09/19; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->12/19; 6/12/19: 70%->95; 26/6/20: 95%->100","New; 33.835",80,41,null,null,"2018-06-06","2020-06-26"]
[1609,900018,"Removal of AKMA from Rel-16 ","RM_AKMA_R16",1,"Rel-16","S3","2020-12-04","2020-12-12",1,"SP-201019",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","33.535; 33.501; 33.220 ; 9/4/21: 0%->100",null,90,46,null,null,"2020-12-04","2021-04-09"]
[1610,0,"NR-related Release 16 Features","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1611,860058,"Addition of wider channel bandwidth in NR band n3","NR_n3_BW",1,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 26/3/20: WID:RP-193056->RP-200305",null,86,44,null,null,"2020-01-14","2020-03-26"]
[1612,860158,"   Core part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1613,860258,"   Perf. part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1614,860059,"Addition of wider channel bandwidth in NR band n65","NR_n65_BW",1,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 26/3/20: WID:RP-193057->RP-200306",null,86,44,null,null,"2020-01-14","2020-03-26"]
[1615,860159,"   Core part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1616,860259,"   Perf. part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1617,830075,"UE Power Saving in NR","NR_UE_pow_sav",1,"Rel-16","R1","2018-06-15","2020-09-15",1,"RP-200494",null,"CATT",null,"26/6/19: WID:RP-190727->RP-191607; 30/6/20: WID:RP-191607->RP-200494",null,83,42,null,null,"2019-03-26","2020-06-30"]
[1618,800094,"   Study on UE power saving in NR","FS_NR_UE_pow_sav",2,"Rel-16","R1","2018-06-15","2019-06-15",1,"RP-181463",null,"CATT",null,"TR 38.8xx; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[1619,830175,"   Core part: UE Power Saving in NR","NR_UE_pow_sav-Core",2,"Rel-16","R1","2019-03-01","2020-03-01",1,"RP-200494",null,"CATT",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1620,830275,"   Perf. part: UE Power Saving in NR","NR_UE_pow_sav-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200494",null,"CATT",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[1621,800072,"Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16",1,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 26/6/19: WID:RP-1907 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1622,800172,"   Core part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16-Core",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1623,800272,"   Perf. part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16-Perf",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201018",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1624,800057,"NR intra-band Carrier Aggregation",null,1,"Rel-16",null,"2018-06-15","2019-12-15",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[1625,800073,"   Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦16/1/19: WID:RP-181426->RP-182256¦26/3/19: WID:RP-182256->RP-190689; 26/6/19: WID:RP-190689->RP-191194; 8/10/19: WID:RP-191194->RP-191812; 14/1/20: WID:RP-191812->RP-192445; 26/3/20: WID:RP-192445->RP-200101; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1626,800173,"      Core part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1627,800273,"      Perf. part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200656",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1628,800074,"   Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦16/1/19: WID:RP-180817->RP-182501¦26/3/19: WID:RP-182501->RP-190494; 26/6/19: WID:RP-190494->RP-191565; 8/10/19: WID:RP-191565->RP-191822; 14/1/20: WID:RP-191822->RP-192615; 26/3/20: WID:RP-192615->RP-200168; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1629,800174,"      Core part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[{"$f":"A1630+1","v":1630},800274,"      Perf. part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201253",null,"ZTE",null,"basket WI¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1631,830099,"NR inter-band Carrier Aggregation",null,1,"Rel-16",null,"2019-03-01","2022-12-22",0.72,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,83,42,null,null,"2019-03-26","NA"]
[1632,830083,"   UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations","NR_CADC_NR_LTE_DC_R16-UEConTest",2,"Rel-16","R5","2019-03-01","2022-12-22",0.42,"RP-190321","RP-221360","Dan SONG, Leif Mattisson, Yu SHI, CMCC, Ericsson, China Unicom","songdan@chinamobile.com, leif.mattisson@ericsson.com, shiyu19@chinaunicom.cn","8/10/19: WID:RP-190321->RP-191772; 28/7/20: WID:RP-191772->RP-200759; 8/10/20: 0%->6; 8/10/20: FCD:01/06/2020->06/21; 8/4/21: 6%->6; 2/7/21: FCD:Fri 11/06/->12/21; 2/7/21: 6%->7 ; 22/3/22: Co ; 20/6/22: Rapporteur: CMCC->Dan SONG, Leif Mattisson, Y...",null,83,42,null,null,"2019-03-26","2022-06-20"]
[1633,830095,"   Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200918",null,"CATT",null,"26/6/19: WID:RP-190692->RP-191153; 8/10/19: WID:RP-191153->RP-192245; 14/1/20: WID:RP-192245->RP-193206; 26/3/20: WID:RP-193206->RP-200238; 28/7/20: WID:RP-200238->RP-200918",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1634,830195,"      Core part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL-Core",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200918",null,"CATT",null,"26/6/19: 38.716-03-01 added;; 28/7/20: 0%->100","38.716-03-01",83,42,null,null,"2019-03-26","2020-07-28"]
[1635,830295,"      Perf. part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200918",null,"CATT",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1636,830096,"   Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL",2,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200673",null,"ZTE",null,"26/6/19: WID:RP-190693->RP-191566; 8/10/19: WID:RP-191566->RP-191824; 14/1/20: WID:RP-191824->RP-192617; 26/3/20: WID:RP-192617->RP-200171; 28/7/20: WID:RP-200171->RP-200673",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1637,830196,"      Core part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL-Core",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200673",null,"ZTE",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1638,830296,"      Perf. part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL-Perf",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200673",null,"ZTE",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1639,831000,"New bands for New Radio",null,1,"Rel-16","R4","2018-06-15","2022-09-22",0.94,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[1640,850062,"   UE Conformance Test Aspects for new Rel-16 NR bands and extension of existing NR bands","NR_bands_BW_R16-UEConTest",2,"Rel-16","R5","2019-09-19","2022-09-22",0.76,"RP-200146","RP-221220","Leif MATTISSON, Ericsson","Leif[dot]mattisson[at]ericsson[dot]com","testing all new NR band(s) and NR channel bandwidth addition Wis of REL-16; 14/1/20: WID:RP-192128->RP-192893; 26/3/20: WID:RP-192893->RP-200146; 28/7/20: WID:RP-200146->RP-200633; 8/10/20: 0%->47; 8/10/20: FCD:15/06/2020->12/20; 8/4/21: 47%->67; 8/4/2...",null,85,43,null,null,"2019-10-08","2022-06-20"]
[1641,800077,"   Band 65 for New Radio","NR_band_n65",2,"Rel-16","R4","2018-06-15","2018-12-15",1,"RP-190360",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258¦26/3/19: WID:RP-182258->RP-190360",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1642,800177,"      Core part: Band 65 for New Radio","NR_band_n65-Core",3,"Rel-16","R4","2018-06-15","2018-12-15",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[1643,800277,"      Perf. part: Band 65 for New Radio","NR_band_n65-Perf",3,"Rel-16","R4","2018-06-15","2018-12-15",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[1644,820073,"   Introduction of NR band n18","NR_n18",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-191556",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: WID:RP-190173->RP-191556",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1645,820173,"      Core part: Introduction of NR band n18","NR_n18-Core",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1646,820273,"      Perf. part: Introduction of NR band n18","NR_n18-Perf",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1647,820077,"   Introduction of NR band n48","NR_n48",2,"Rel-16","R4","2018-12-13","2019-06-01",1,"RP-190908",null,"US Cellular",null,"26/6/19: WID:RP-182865->RP-190908",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1648,820177,"      Core part: Introduction of NR band n48","NR_n48-Core",3,"Rel-16","R4","2018-12-13","2019-03-18",1,"RP-182865",null,"US Cellular",null,"26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1649,830271,"      Perf. part: Introduction of NR band n48","NR_n48-Perf",3,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190140",null,"Nokia",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1650,830090,"   Introduction of NR band n14","NR_n14",2,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190965",null,"AT&T",null,"26/6/19: WID:RP-190165->RP-190965",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1651,830190,"      Core part: Introduction of NR band n14","NR_n14-Core",3,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190165",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1652,830290,"      Perf. part: Introduction of NR band n14","NR_n14-Perf",3,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190165",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1653,830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1654,830191,"      Core part: Introduction of NR band n30","NR_n30-Core",3,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190166",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1655,830291,"      Perf. part: Introduction of NR band n30","NR_n30-Perf",3,"Rel-16","R4","2019-03-01","2019-06-01",1,"RP-190166",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1656,830097,"   Introduction of NR band n259","NR_n259",2,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-200249",null,"Ericsson",null,"26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1657,830197,"      Core part: Introduction of NR band n259","NR_n259-Core",3,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1658,830297,"      Perf. part: Introduction of NR band n259","NR_n259-Perf",3,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1659,850067,"   Introduction of NR band n26","NR_n26",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192736",null,"Sprint",null,"UL: 814-849MHz, DL: 859-894MHz; 14/1/20: WID:RP-192273->RP-192736",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1660,850167,"      Core part: Introduction of NR band n26","NR_n26-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1661,850267,"      Perf. part: Introduction of NR band n26","NR_n26-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1662,840097,"   Introduction of NR supplementary DL band n29","NR_n29",2,"Rel-16","R4","2019-06-17","2019-09-15",1,"RP-192236",null,"Dish Network",null,"8/10/19: WID:RP-191474->RP-192236",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1663,840197,"      Core part: Introduction of NR supplementary DL band n29","NR_n29-Core",3,"Rel-16","R4","2019-06-17","2019-09-15",1,"RP-192236",null,"Dish Network",null,"8/10/19: 0%->100",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1664,840297,"      Perf. part: Introduction of NR supplementary DL band n29","NR_n29-Perf",3,"Rel-16","R4","2019-06-17","2019-09-15",1,"RP-192236",null,"Dish Network",null,"8/10/19: 0%->100",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1665,850068,"   Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192584",null,"CMCC",null,"14/1/20: WID:RP-192274->RP-192584",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1666,850168,"      Core part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1667,850268,"      Perf. part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1668,860056,"   Introduction of band n53","NR_n53",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-192409",null,"Globalstar",null,"affects: NR.",null,86,44,null,null,"2020-02-18","NA"]
[1669,860156,"      Core part: Introduction of band n53","NR_n53-Core",3,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[1670,860256,"      Perf. part: Introduction of band n53","NR_n53-Perf",3,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[1671,831001,"New Radio Band-related topics",null,1,"Rel-16","R4","2018-12-13","2022-12-22",0.94,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[1672,830087,"   RF requirements for NR frequency range 1 (FR1)","NR_RF_FR1",2,"Rel-16","R4","2019-03-01","2022-12-22",0.8,"RP-193266",null,"Huawei",null,"26/6/19: WID:RP-190759->RP-191114; 8/10/19: WID:RP-191114->RP-192282; 14/1/20: WID:RP-192282->RP-193266",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1673,830187,"      Core part: RF requirements for NR FR1","NR_RF_FR1-Core",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-193266",null,"Huawei",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1674,830287,"      Perf. Part: RF requirements for NR FR1","NR_RF_FR1-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193266",null,"Huawei",null,"6/1/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-01-06"]
[1675,870061,"      UE Conformance Test Aspects - RF requirements for NR FR1","NR_RF_FR1-UEConTest",3,"Rel-16","R5","2020-03-25","2022-12-22",0.64,"RP-200094","RP-221479","Chunying Gu, Huawei Technologies. Co., Ltd.","guchunying@huawei.com","affects: NR. TR 38.8xx; 8/10/20: 0%->15; 8/4/21: 15%->43; ; 6/6/22: CD:10/06/2022->22/12/2022 ; 20/6/22: Rapporteur: Huawei->Chunying Gu, Huawei Technologies. Co., Ltd.; Rap eMail: ->guchunying@huawei.com; ",null,87,44,null,null,"2020-01-14","2022-06-20"]
[1676,830088,"   Add support of NR DL 256QAM for frequency range 2 (FR2)","NR_DL256QAM_FR2",2,"Rel-16","R4","2019-03-01","2022-06-22",0.99,"RP-200124",null,"China Telecom",null,"26/6/19: WID:RP-190760->RP-190925; 8/10/19: WID:RP-190925->RP-191891; 26/3/20: WID:RP-191891->RP-200124",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1677,830188,"      Core part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Core",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200124",null,"China Telecom",null,"8/10/19: 38.883 added;; 28/7/20: 0%->100",38.883000000000003,83,42,null,null,"2019-03-26","2020-07-28"]
[1678,830288,"      Perf. part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Perf",3,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200124",null,"China Telecom",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[1679,900051,"      UE Conformance Test Aspects - Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-UEConTest",3,"Rel-16","R5","2020-12-14","2022-06-22",1,"RP-202371","RP-220571","China Telecom ",null,"tested: REL-16 WI NR_DL256QAM_FR2-Core ; 8/4/21: 0%->20; 2/7/21: 20%->44; 13/9/21: Compl:44%->82%; 13/9/21: CD:Fri 10/06/22->Wed 22/06/22 ; ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1680,830089,"   NR RF requirement enhancements for frequency range 2 (FR2)","NR_RF_FR2_req_enh",2,"Rel-16","R4","2019-03-01","2022-12-22",0.87,"RP-201606",null,"Nokia",null,"26/6/19: WID:RP-190761->RP-191290; 8/10/19: WID:RP-191290->RP-192227; 14/1/20: WID:RP-192227->RP-192653; 26/3/20: WID:RP-192653->RP-200246; 28/7/20: WID:RP-200246->RP-200668; 25/9/20: WID:RP-200668->RP-201606",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1681,830189,"      Core part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Core",3,"Rel-16","R4","2019-03-01","2020-03-01",1,"RP-200668",null,"Nokia",null,"8/10/19: 38.831 added;; 25/9/20: 0%->100",38.831000000000003,83,42,null,null,"2019-03-26","2020-09-25"]
[1682,850073,"      Perf. part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-200668",null,"Nokia",null,"25/9/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-09-25"]
[1683,910098,"      UE Conformance Test Aspects - NR RF requirement enhancements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh-UEConTest",3,"Rel-16","R5","2021-03-12","2022-12-22",0.77,"RP-212304","RP-221065","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","tested: REL-16 WI NR_RF_FR2_req_enh-Core ; 2/7/21: 0%->20; 29/9/21: WID:RP-210363->RP-212304; 22/3/22: Compl:20%->57% ; ; ; 20/6/22: Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin...",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1684,830092,"   Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5","NR_SUL_UL_n5",2,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-192080",null,"Huawei",null,"26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1685,830192,"      Core part: Introduction of an NR SUL band with same uplink frequency range as NR band n5","NR_SUL_UL_n5-Core",3,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-192080",null,"Huawei",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1686,830292,"      Perf. part: Introduction of an NR SUL band with same uplink frequency range as NR band n5","NR_SUL_UL_n5-Perf",3,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-192080",null,"Huawei",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1687,820074,"   Adding wider channel bandwidths in NR band n7","NR_n7_BW",2,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137",null,82,42,null,null,"2019-01-16","2019-03-26"]
[1688,820174,"      Core part: Adding wider channel bandwidths in NR band n7","NR_n7_BW-Core",3,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[1689,830093,"   Addition of wider channel bandwidth in NR band n38","NR_n38_BW",2,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-191472",null,"Huawei",null,"26/6/19: WID:RP-190392->RP-191472; 14/1/20: WID:RP-191472->RP-192513; 13/6/21: WID:RP-192513->RP-191472",null,83,42,null,null,"2019-03-26","2021-06-13"]
[1690,830193,"      Core part: Addition of wider channel bandwidth in NR band n38","NR_n38_BW-Core",3,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-191472",null,"Huawei",null,"14/1/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1691,830293,"      Perf. part: Addition of wider channel bandwidth in NR band n38","NR_n38_BW-Perf",3,"Rel-16","R4","2019-03-01","2019-12-15",1,"RP-191472",null,"Huawei",null,"14/1/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1692,850063,"   Addition of further channel bandwidths in NR band 38","NR_n38_BW2",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192513",null,"Ericsson",null,"13/6/21: WID:RP-192215->RP-192513",null,85,43,null,null,"2019-10-08","2021-06-13"]
[1693,850163,"      Core part: Addition of further channel bandwidths in NR band 38","NR_n38_BW2-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192513",null,"Ericsson",null,"compare REL-16 WI NR_n38_BW; 26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[{"$f":"A1694+1","v":1694},850263,"      Perf. part: Addition of further channel bandwidths in NR band 38","NR_n38_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192513",null,"Ericsson",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1695,820075,"   Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 26/6/19: WID:RP-190174->RP-191569; 8/10/19: WID:RP-191569->RP-191681",null,82,42,null,null,"2019-01-16","2019-10-08"]
[1696,820175,"      Core part: Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[1697,820275,"      Stopped - Perf. part: Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW-Perf",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174. 08/10/2019: stopped at 0%; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[1698,820076,"   Adding wider channel bandwidths in NR band n50","NR_n50_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[1699,820176,"      Core part: Adding wider channel bandwidths in NR band n50","NR_n50_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1700,850064,"   Addition of wider channel bandwidths in NR band n75","NR_n75_BW",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192216",null,"Ericsson",null,null,null,85,43,null,null,"2019-10-08","NA"]
[1701,850164,"      Core part: Addition of wider channel bandwidths in NR band n75","NR_n75_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192216",null,"Ericsson",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1702,850264,"      Perf. part: Addition of wider channel bandwidths in NR band n75","NR_n75_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192216",null,"Ericsson",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1703,850065,"   Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192401",null,"Nokia",null,"14/1/20: WID:RP-192219->RP-192401",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1704,850165,"      Core part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1705,850265,"      Perf. part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1706,850066,"   Addition of wider channel bandwidths in NR band n28","NR_n28_BW",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192656",null,"CBN",null,"14/1/20: WID:RP-192261->RP-192656",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1707,850166,"      Core part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1708,850266,"      Perf. part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1709,850069,"   Addition of new channel bandwidth in NR band n1","NR_n1_BW2",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192801",null,"China Unicom",null,"8/10/19: WID:RP-192275->RP-192009. compare REL-16 WI NR_n1_BW; 14/1/20: WID:RP-192275->RP-192801",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1710,850169,"      Core part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[1711,850269,"      Perf. part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[1712,850070,"   Addition of asymmetric channel bandwidth for NR band n66","NR_n66_BW",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-200265",null,"Huawei",null,"no Perf. Part; 14/1/20: WID:RP-192276->RP-192808; 26/3/20: WID:RP-192808->RP-200265",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1713,850170,"      Core part: Addition of asymmetric channel bandwidth for NR band n66","NR_n66_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-201010",null,"Huawei",null,"28/7/20: WID:RP-200265->RP-201010; 28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[1714,800085,"Enhancements on MIMO for NR","NR_eMIMO",1,"Rel-16","R1","2018-06-15","2022-12-22",0.86,"RP-200474",null,"Samsung",null,"16/1/19: WID:RP-181453->RP-182863; 8/10/19: WID:RP-182863->RP-192271; 26/3/20: WID:RP-192271->RP-200474",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1715,800185,"   Core part: Enhancements on MIMO for NR","NR_eMIMO-Core",2,"Rel-16","R1","2018-06-15","2019-12-15",1,"RP-200474",null,"Samsung",null,"25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[1716,800285,"   Perf. part: Enhancements on MIMO for NR","NR_eMIMO-Perf",2,"Rel-16","R4","2018-06-15","2020-09-15",1,"RP-200474",null,"Samsung",null,"7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[1717,880070,"   UE Conformance Test Aspects - Enhancements on MIMO for NR","NR_eMIMO-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-22",0.64,"RP-200895","RP-221483","Chunying GU, Huawei","guchunying@huawei.com","8/10/20: 0%->1; 8/4/21: 1%->16; 2/7/21: 16%->20; 22/3/22: Compl:20%->57%; 6/6/22: Compl:57%-> ; 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1718,800087,"NR mobility enhancements","NR_Mob_enh",1,"Rel-16","R2","2018-06-15","2022-12-22",0.99,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 8/10/19: WID:RP-190489->RP-192277; 14/1/20: WID:RP-192277->RP-192534",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1719,800187,"   Core part: NR mobility enhancements","NR_Mob_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-15",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1720,800287,"   Perf. part: NR mobility enhancements","NR_Mob_enh-Perf",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1721,880068,"   UE Conformance Test Aspects - NR Mobility Enhancements","NR_Mob_enh-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-22",0.97,"RP-221481","RP-221480","Zhaobing Yang, Huawei Technologies. Co., Ltd.","yangzhaobing @hisilicon.com","8/10/20: 0%->5; 8/4/21: 5%->35; 22 6/6/22: CD:10 ; 20/6/22: Rapporteur: Huawei->Zhaobing Yang, Huawei Technologies. Co., Ltd.; Rap eMail: ->yangzhaobing @hisilicon.com; ; 12/7/22: WID:RP-200893->RP-221481",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1722,820068,"2-step RACH for NR","NR_2step_RACH",1,"Rel-16","R1","2018-12-15","2019-12-15",0.88,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 8/10/19: WID:RP-190711->RP-192330; 26/3/20: WID:RP-192330->RP-200085",null,82,42,null,null,"2019-01-16","2020-03-26"]
[1723,820168,"   Core part: 2-step RACH for NR","NR_2step_RACH-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 28/7/20: 0%->100; 28/7/20: 100%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[1724,820268,"   Perf. part: 2-step RACH for NR","NR_2step_RACH-Perf",2,"Rel-16","R4","2018-12-15","2019-06-20",1,"RP-200085",null,"ZTE",null,"26/3/19: WID:RP-182894->RP-190711; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[1725,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-12-22",0.77,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; ; ; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1726,840091,"SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR","NR_SON_MDT",1,"Rel-16","R3","2019-06-17","2022-06-22",0.99,"RP-191594",null,"CMCC",null,"no Perf. part; impact on SA2, SA5, CT4?; TR 38.314",null,84,43,null,null,"2019-06-26","NA"]
[1727,840191,"   Core part: SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR","NR_SON_MDT-Core",2,"Rel-16","R3","2019-06-17","2020-03-15",1,"RP-192610",null,"CMCC",null,"no Perf. part; impact on SA2, SA5, CT4?; TR 38.314; 8/10/19: WID:RP-191594->RP-191776; 8/10/19: 38.314 added;; 14/1/20: WID:RP-191776->RP-192610; 28/7/20: 0%->100",38.314,84,43,null,null,"2019-06-26","2020-07-28"]
[1728,890043,"   UE Conformance Test Aspects - SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR ","NR_SON_MDT-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-210377","RP-221368","Wenjia DONG, Leif Mattisson, CMCC, Ericsson","dongwenjia@chinamobile.com, leif.mattisson@ericsson.com","tested: REL-16 WI NR_SON_MDT-Core ; 7/4/21: WID:RP-201625->RP-210377; 8/4/21: 0%->37; 2/7/21: 37%->71; 13/9/21: Compl:71%->85%; ; ; ; 20/6/22: Rapporteur: CMCC->Wenjia DONG, Leif Mattisson, CMCC, Ericsson; Rap eMail: ->dongwenjia@chinamobile.com, ...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1729,810030,"Study on Self-Organizing Networks (SON) for 5G","FS_SON_5G",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180827",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com ","7/12/18: 0%->10¦14/3/19: 10%->40; 31/5/19: 40%->50; 6/12/19: 50%->100","New",81,41,null,null,"2018-09-06","2019-12-06"]
[1730,850030,"Self-Organizing Networks (SON) for 5G networks ","SON_5G",1,"Rel-16","S5","2019-09-19","2020-09-14",1,"SP-200763",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/19: 0%->80; 8/10/19: 28.544 added;; 8/10/19: 28.313 added;; 28/6/20: 80%->75; 13/9/20: 75%->100; 13/9/20: WID:SP-190785->SP-200763; 13/9/20: FCD:12/03/2020->09/20","28.552; 28.545 ; 28.544; 28.313",85,43,null,null,"2019-09-13","2020-09-13"]
[1731,840093,"RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas",1,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"8/10/19: WID:RP-191580->RP-191992; 26/3/20: WID:RP-191992->RP-200240; 28/7/20: WID:RP-200240->RP-201345; 25/9/20: WID:RP-201345->RP-201975; 6/1/21: WID:RP-201975->RP-202723; 7/4/21: WID:RP-202723->RP-210590",null,84,43,null,null,"2019-06-26","2021-04-07"]
[1732,840193,"   Core part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-210590",null,"CATT",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[1733,840293,"   Perf. part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Perf",2,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"2/7/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-07-02"]
[1734,840094,"NR performance requirement enhancement","NR_perf_enh",1,"Rel-16","R4","2019-06-17","2022-06-22",0.99,"RP-200472",null,"China Telecom",null,"no Core part; 8/10/19: WID:RP-191587->RP-192281; 14/1/20: WID:RP-192281->RP-192532; 26/3/20: WID:RP-192532->RP-200472",null,84,43,null,null,"2019-06-26","2020-03-26"]
[1735,840294,"   Perf. part: NR performance requirement enhancement","NR_perf_enh-Perf",2,"Rel-16","R4","2019-06-17","2019-09-15",1,"RP-200472",null,"China Telecom",null,"no Core part; 7/4/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-04-07"]
[1736,890048,"   UE Conformance Test Aspects - NR performance requirement enhancement ","NR_perf_enh-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-202557","RP-221294","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","tested: REL-16 WI NR_perf_enh-Perf ; 6/1/21: WID:RP-201941->RP-202557; Qualcomm -> China Telecom; 8/4/21: 0%->15; 2/7/21: 15%->18; 13/9/21: Compl:18%->21%; ; ; ; 20/6/22: Rapporteur: Qualcomm -> China Telecom->Wu Jingzhou, Balasubramanian Vijay, C...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1737,840095,"NR RRM enhancement","NR_RRM_enh",1,"Rel-16","R4","2019-06-17","2023-12-15",0.54,"RP-201883",null,"Intel",null,"8/10/19: WID:RP-191601->RP-192157; 14/1/20: WID:RP-192157->RP-193211; 26/3/20: WID:RP-193211->RP-200256; 28/7/20: WID:RP-200256->RP-201112; 25/9/20: WID:RP-201112->RP-201883",null,84,43,null,null,"2019-06-26","2020-09-25"]
[1738,840195,"   Core part: NR RRM enhancement","NR_RRM_enh-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-201883",null,"Intel",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[1739,840295,"   Perf. part: NR RRM enhancement","NR_RRM_enh-Perf",2,"Rel-16","R4","2019-06-17","2020-06-15",1,"RP-202655",null,"Intel",null,"6/1/21: WID:RP-201883->RP-202655; 7/4/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-04-07"]
[1740,960089,"   UE Conformance Test Aspects - NR RRM enhancements ","NR_RRM_enh-UEConTest",2,"Rel-16","R5","2022-06-15","2023-12-15",0,"RP-221705",null,"Apple ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[1741,840096,"Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL",1,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 8/10/19: WID:RP-191196->RP-191814; 14/1/20: WID:RP-191814->RP-192447; 26/3/20: WID:RP-192447->RP-200103; 28/7/20: WID:RP-200103->RP-200658",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1742,840196,"   Core part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1743,840296,"   Perf. part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL-Perf",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-200658",null,"Ericsson",null,"basket WI; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1744,840098,"Addition of wider channel bandwidth in NR band n1","NR_n1_BW",1,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-192009",null,"Ericsson",null,"8/10/19: WID:RP-191595->RP-192009",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1745,840198,"   Core part: Addition of wider channel bandwidth in NR band n1","NR_n1_BW-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-192009",null,"Ericsson",null,"26/3/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-03-26"]
[1746,840298,"   Perf. part: Addition of wider channel bandwidth in NR band n1","NR_n1_BW-Perf",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-192009",null,"Ericsson",null,"26/3/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-03-26"]
[1747,840099,"Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW",1,"Rel-16","R4","2019-06-17","2019-12-15",1,"RP-191606",null,"Huawei",null,"no Perf. part",null,84,43,null,null,"2019-06-26","NA"]
[1748,840199,"   Core part: Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW-Core",2,"Rel-16","R4","2019-06-17","2019-12-15",1,"RP-192822",null,"Huawei",null,"no Perf. part; 8/10/19: WID:RP-191606->RP-192349; 14/1/20: WID:RP-192349->RP-192822; 26/3/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-03-26"]
[1749,841000,"Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL",1,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1750,841100,"   Core part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Core",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1751,841200,"   Perf. part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Perf",2,"Rel-16","R4","2019-06-17","2020-03-15",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1752,841001,"Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex",1,"Rel-16","R4","2019-06-17","2019-12-15",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[1753,841101,"   Core part: Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex-Core",2,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[1754,850074,"   Perf. part: Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex-Perf",2,"Rel-16","R4","2019-09-19","2019-12-15",1,"RP-192820",null,"Huawei",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1755,841002,"Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC",1,"Rel-16","R4","2019-07-31","2022-06-22",0.46,"RP-191604",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI",null,84,43,null,null,"2019-07-31","NA"]
[1756,841102,"   Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-Core",2,"Rel-16","R4","2019-07-31","2020-03-12",0,"RP-192093",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093",null,84,43,null,null,"2019-07-31","2019-10-08"]
[1757,940091,"   UE Conformance Test Aspects - Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-UEConTest",2,"Rel-16","R5","2021-12-13","2022-06-22",1,"RP-213228","RP-221486","Huawei",null,"tested: REL-16 WI DC_Pcmax_3UL_CC-Core; 22/3/22: Compl:0%->71%; ; ",null,94,48,null,null,"2022-01-06","2022-06-06"]
[{"$f":"A1758+1","v":1758},880074,"Addition of NR UE measurements to enable OTA conformance testing","NR_OTA_Uemeas",1,"Rel-16","R1","2020-06-22","2020-07-28",1,"RP-200824",null,"Keysight Technologies",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1759,880174,"   Core part: Addition of NR UE measurements to enable OTA conformance testing","NR_OTA_Uemeas-Core",2,"Rel-16","R1","2020-06-22","2020-07-28",1,"RP-200824",null,"Keysight Technologies",null,"28/7/20: 0%->100; 28/7/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-07-28"]
[1760,0,"Release 16 Features impacting both LTE and NR","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1761,860054,"Over the air (OTA) base station (BS) testing TR","OTA_BS_testing",1,"Rel-16","R4","2019-03-07","2019-06-05",1,"RP-193225",null,"Huawei",null,"affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16",null,86,44,null,null,"2020-02-18","NA"]
[1762,860254,"   Perf. Part: Over the air (OTA) base station (BS) testing TR","OTA_BS_testing-Perf",2,"Rel-16","R4","2019-03-07","2019-06-05",1,"RP-201021",null,"Huawei",null,"affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16; 26/3/20: WID:RP-193225->RP-200276; 28/7/20: WID:RP-200276->RP-201021; 25/9/20: 37.941 added;; 6/1/21: 0%->100",37.941000000000003,86,44,null,null,"2020-01-14","2021-01-06"]
[1763,860055,"High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","ENDC_UE_PC2_FDD_TDD",1,"Rel-16","R4","2019-12-16","2021-12-17",1,"RP-193244",null,"China Unicom",null,"affects: LTE, NR. no Perf. part",null,86,44,null,null,"2020-02-18","NA"]
[1764,860155,"   Core part: High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","ENDC_UE_PC2_FDD_TDD-Core",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-201578",null,"China Unicom",null,"affects: LTE, NR. no Perf. part; 25/9/20: WID:RP-193244->RP-201578; 25/9/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-09-25"]
[1765,890044,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) ","ENDC_UE_PC2_FDD_TDD-UEConTest",2,"Rel-16","R5","2020-09-17","2021-12-17",1,"RP-212501",null,"China Unicom ",null,"tested: REL-16 WI ENDC_UE_PC2_FDD_TDD-Core ; 8/4/21: 0%->78; 29/9/21: WID:RP-201776->RP-212501; 29/9/21: 78%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1766,860057,"Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL",1,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 26/3/20: WID:RP-192784->RP-200228; 28/7/20: WID:RP-200228->RP-200905",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1767,860157,"   Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL-Core",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 28/7/20: 0%->100; 25/9/20: 37.716-41-22 added;","37.716-41-22",86,44,null,null,"2020-01-14","2020-09-25"]
[1768,860257,"   Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1769,860060,"LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex",1,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 26/3/20: WID:RP-193213->RP-200234; 28/7/20: WID:RP-200234->RP-201359; 25/9/20: WID:RP-201359->RP-201858",null,86,44,null,null,"2020-01-14","2020-09-25"]
[1770,860160,"   Core part: LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex-Core",2,"Rel-16","R4","2019-12-16","2020-03-15",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1771,800088,"LTE-NR & NR-NR Dual Connectivity and NR Carrier Aggregation enhancements","LTE_NR_DC_CA_enh",1,"Rel-16","R2","2018-06-15","2022-12-22",0.8,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 26/6/19: WID:RP-190452->RP-191600; 8/10/19: WID:RP-191600->RP-192336; 28/7/20: WID:RP-192336->RP-200791",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1772,800188,"   Core part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements","LTE_NR_DC_CA_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-15",1,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[1773,800288,"   Perf. part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements","LTE_NR_DC_CA_enh-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200791",null,"Ericsson",null,"26/3/19: WID:RP-181469->RP-190452; 2/7/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-07-02"]
[1774,911004,"   UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements ","LTE_NR_DC_CA_enh-UEConTest",2,"Rel-16","R5","2021-03-12","2022-12-22",0.4,"RP-211442","RP-221416","Matti Kangas","matti.kangas@nokia.com","lested: REL-16 WI LTE_NR_DC_CA_enh-Core ; 2/7/21: WID:RP-210746->RP-211442; 2/7/21: 0%->5; 5/4/22: WID:RP-211442->RP-220801; 20/6/22: FCD:11/03/2022->22/12/2022; Compl:5%->40%; WID: RP-220801->RP-211442; Stat Rep: ->RP-221416; Rapporteur: Nokia->Matti...",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1775,820079,"High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD",1,"Rel-16","R4","2018-12-13","2020-03-18",0.99,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315",null,82,42,null,null,"2019-01-16","2019-03-26"]
[1776,820061,"   Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","FS_ENDC_UE_PC2_FDD_TDD",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-192268",null,"China Unicom",null,"EN-DC = E-UTRA-NR Dual Connectivity¦TR 37.8xx¦26/3/19: WID:RP-182895->RP-190167; 8/10/19: WID:RP-190167->RP-192268; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[1777,820179,"   Core part: High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-Core",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[1778,820279,"   Perf. part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-Perf",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[1779,870062,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-UEConTest",2,"Rel-16","R5","2019-03-07","2020-03-18",1,"RP-202066",null,"CMCC",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200434->RP-200761; 25/9/20: WID:RP-200761->RP-202066; 25/9/20: 0%->100",null,87,44,null,null,"2020-01-14","2020-09-25"]
[1780,790054,"eNB(s) Architecture Evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo",1,"Rel-16","R3","2018-03-15","2019-12-13",1,"RP-192917",null,"China Unicom",null,"follow-up WI of REL-15 SI FS_LTE_arch_evo; 14/1/20: WID:RP-180531->RP-192917",null,79,40,null,null,"2018-03-27","2020-01-14"]
[1781,790154,"   Core part: eNB(s) Architecture Evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo-Core",2,"Rel-16","R3","2018-03-15","2019-12-13",1,"RP-192917",null,"China Unicom",null,"follow-up WI of REL-15 SI FS_LTE_arch_evo¦27/6/18: Compl:0%->15%¦27/6/18: CD:Fri 15/06/18->Sun 15/12/19¦27/6/18: WID: RP-180531->RP-181375¦27/6/18: Release: Rel-15->Rel-16¦6/8/18: 37.470 to 473 and 36.470 to 473 added;; 14/1/20: 15%->100","37.470; 37.471; 37.472; 37.473; 36.470; 36.471; 36.472; 36.473",79,40,null,null,"2018-03-27","2020-01-14"]
[1782,820080,"LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex",1,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191588",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: WID:RP-190175->RP-191588",null,82,42,null,null,"2019-03-26","2019-06-26"]
[1783,820180,"   Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex-Core",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-190175",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1784,800078,"29 dBm UE Power Class for LTE band 41 and NR Band n41","LTE_NR_B41_Bn41_PC29dBm",1,"Rel-16","R4","2018-06-15","2022-09-22",0.82,"RP-201134",null,"Sprint",null,"no Perf. part¦26/3/19: WID:RP-181655->RP-190502; 14/1/20: WID:RP-190502->RP-192738; 28/7/20: WID:RP-192738->RP-201134",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1785,800178,"   Core part: 29 dBm UE Power Class for LTE band 41 and NR Band n41","LTE_NR_B41_Bn41_PC29dBm-Core",2,"Rel-16","R4","2018-06-15","2019-06-15",1,"RP-201134",null,"Sprint",null,"no Perf. part¦7/3/19: WID:RP-181460->RP-181655¦26/3/19: WID:RP-181655->RP-190502; 25/9/20: 0%->100; 25/9/20: 100%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[1786,920068,"   UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41 and NR Band n41 ","LTE_NR_B41_Bn41_PC29dBm-UEConTest",2,"Rel-16","R5","2021-06-15","2022-09-22",0.67,"RP-211443","RP-221180 / R5-222679","Scott Probasco, Dan SONG, T-Mobile, CMCC","scott.probasco@t-mobile.com, songdan@chinamobile.com","tested: REL-17 WI LTE_NR_B41_Bn41_PC29dBm-Core ; 5/4/22: WID:RP-211443->RP-220124 6/6/22: C ; 20/6/22: Stat Rep: R5-222679->RP-221180 / R5-222679; Rapporteur: T-Mobile USA->Scott Probasco, Dan SONG, T-Mobile, CMCC; Rap eMail: ->scott.probasco@t-mobile....",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1787,800058,"Dual Connectivity (EN-DC) ",null,1,"Rel-16",null,"2018-06-15","2019-12-15",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[1788,800066,"   Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦16/1/19: WID:RP-181447->RP-182567¦26/3/19: WID:RP-182567->RP-190705; 26/6/19: WID:RP-190705->RP-191568; 8/10/19: WID:RP-191568->RP-191752; 14/1/20: WID:RP-191752->RP-192742; 26/3/20: WID:RP-192742->RP-200221; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1789,800166,"      Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1790,800266,"      Perf. part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1791,800067,"   Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201278",null,"Huawei",null,"basket WI¦TR 37.716-02-01¦16/1/19: WID:RP-181357->RP-182557¦26/3/19: WID:RP-182557->RP-190379; 26/6/19: WID:RP-190379->RP-191124; 8/10/19: WID:RP-191124->RP-192087; 14/1/20: WID:RP-192087->RP-192815; 26/3/20: WID:RP-192815->RP-200271; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1792,800167,"      Core part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201278",null,"Huawei",null,"basket WI¦TR 37.716-02-01¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1793,800267,"      Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201278",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1794,800068,"   Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200657",null,"Ericsson",null,"basket WI¦TR 37.716-03-01¦16/1/19: WID:RP-181407->RP-182257¦26/3/19: WID:RP-182257->RP-190159; 26/6/19: WID:RP-190159->RP-191195; 8/10/19: WID:RP-191195->RP-191813; 14/1/20: WID:RP-191813->RP-192446; 26/3/20: WID:RP-192446->RP-200102; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1795,800168,"      Core part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200657",null,"Ericsson",null,"basket WI¦TR 37.716-03-01¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1796,800268,"      Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200657",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1797,800069,"   Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦16/1/19: WID:RP-181001->RP-182534¦26/3/19: WID:RP-182534->RP-190294; 26/6/19: WID:RP-190294->RP-191205; 8/10/19: WID:RP-191205->RP-191728; 14/1/20: WID:RP-191728->RP-192768; 26/3/20: WID:RP-192768->RP-200134; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1798,800169,"      Core part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1799,800269,"      Perf. part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200648",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1800,800070,"   Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01",null,80,41,null,null,"2018-06-27","NA"]
[1801,800170,"      Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1802,800270,"      Stopped: Perf. part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-180997",null,"Samsung",null,"basket WI; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1803,800071,"   Dual Connectivity (EN-DC) of x bands (x=1, 2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦16/1/19: WID:RP-180777->RP-182302, \"x=1\" added¦26/3/19: WID:RP-182302->RP-190151; 26/6/19: WID:RP-190151->RP-190949; 8/10/19: WID:RP-190949->RP-191744; 14/1/20: WID:RP-191744->RP-192592; 26/3/20: WID:RP-192592->RP-200080; 28/7 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1804,800171,"      Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1805,800271,"      Perf. part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200744",null,"LG Electronics",null,"basket WI¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1806,0,"LTE-related Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1807,790057,"E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US",1,"Rel-16","R4","2018-03-15","2019-06-18",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: WID:RP-180583->RP-182405",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[1808,790157,"   Core part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Core",2,"Rel-16","R4","2018-03-15","2018-12-15",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: 0%->100",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[1809,790257,"   Perf. part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Perf",2,"Rel-16","R4","2018-03-15","2018-12-15",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦16/1/19: 0%->100",null,79,40,null,null,"2018-03-27","2019-01-16"]
[1810,820063,"   UE Conformance Test Aspects - E-UTRA 2.4 GHz TDD Band for US (Band 53)","LTE_TDD_2400_US-UEConTest",2,"Rel-15","R5","2018-12-13","2019-06-18",1,"RP-182406",null,"Globalstar",null,"tested: REL-15 WI LTE_TDD_2400_US-Core; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1811,800059,"LTE intra-band Carrier Aggregation (CA)",null,1,"Rel-16",null,"2018-06-15","2022-12-22",0.82,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[1812,800060,"   Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200655",null,"Ericsson",null,"basket WI¦TR 36.716-01-01¦16/1/19: WID:RP-180806->SP-182255¦26/3/19: WID:RP-182255->RP-190157; 26/6/19: WID:RP-190157->RP-191193; 8/10/19: WID:RP-191193->RP-191811; 14/1/20: WID:RP-191811->RP-192444; 26/3/20: WID:RP-192444->RP-200100; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1813,800160,"      Core part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦TR 36.716-01-01¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1814,800260,"      Perf. part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200655",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1815,800061,"   Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 8/10/19: WID:RP-191085->RP-191733; 14/1/20: WID:RP-191733->RP-192525; 26/3/20: WID:RP-192525->RP-200231; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1816,800161,"      Core part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1817,800261,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1818,800062,"   Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201012",null,"Huawei",null,"basket WI¦TR 36.716-03-01¦16/1/19: WID:RP-181436->RP-182553¦26/3/19: WID:RP-182553->RP-190375; 26/6/19: WID:RP-190375->RP-191120; 8/10/19: WID:RP-191120->RP-192083; 14/1/20: WID:RP-192083->RP-192811; 26/3/20: WID:RP-192811->RP-200451; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1819,800162,"      Core part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201012",null,"Huawei",null,"basket WI¦TR 36.716-03-01¦26/3/19: WID:RP-182553->RP-190375; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1820,800262,"      Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201012",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182553->; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1821,800063,"   Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201238",null,"Nokia",null,"basket WI¦TR 36.716-04-01¦16/1/19: WID:RP-181408->RP-182330¦26/3/19: WID:RP-182330->RP-190138; 26/6/19: WID:RP-190138->RP-190906; 8/10/19: WID:RP-190906->RP-191730; 14/1/20: WID:RP-191730->RP-192423; 26/3/20: WID:RP-192423->RP-200157; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[{"$f":"A1822+1","v":1822},800163,"      Core part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201238",null,"Nokia",null,"basket WI¦TR 36.716-04-01¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1823,800263,"      Perf. part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201238",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1824,800064,"   Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1825,800164,"      Core part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1826,800264,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1827,800065,"   Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200740",null,"LG Electronics",null,"basket WI¦TR 36.716-00-02¦16/1/19: WID:RP-180778->RP-182301¦26/3/19: WID:RP-182301->RP-190150; 26/6/19: WID:RP-190150->RP-190946; 8/10/19: WID:RP-190946->RP-191743; 14/1/20: WID:RP-191743->RP-192586; 26/3/20: WID:RP-192586->RP-200510; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1828,800165,"      Core part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200740",null,"LG Electronics",null,"basket WI¦TR 36.716-00-02¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1829,800265,"      Perf. part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200740",null,"LG Electronics",null,"basket WI¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1830,810061,"   UE Conformance Test Aspects – Rel-16 LTE CA configurations","LTE_CA_R16-UEConTest",2,"Rel-16","R5","2018-09-14","2022-12-22",7.0000000000000007E-2,"RP-171886","RP-221219","Leif MATTISSON","Leif[dot]mattisson[at]ericsson[dot]com","16/1/19: WID:RP-181605->RP-182648; 8/10/20: 0%->7; 8/10/20: FCD:19/06/2020->12/20; 8/4/21: 7%->7; 8/4/21: FCD:11/12/2020->09/21; 2/7/21: 7%->; 2/7/21: FCD:Wed 08/09/->03/22; 20/6/22: FCD:11/03/2022->22/12/2022; WID: RP-182648->RP-171886; Stat Rep: ->RP...",null,81,41,null,null,"2018-09-25","2022-06-20"]
[1831,830076,"LTE-based 5G terrestrial broadcast","LTE_terr_bcast",1,"Rel-16","R1","2018-06-15","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"8/10/19: WID:RP-190732->RP-191924; 8/10/19: 36.276 added;; 14/1/20: WID:RP-191924->RP-193050","36.276; 36.476",83,42,null,null,"2019-03-26","2020-01-14"]
[1832,800091,"   Study on LTE-based 5G terrestrial broadcast","FS_LTE_terr_bcast",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181342",null,"Qualcomm",null,"TR 36.7xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1833,830176,"   Core part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Core",2,"Rel-16","R1","2019-03-01","2019-12-15",1,"RP-193050",null,"Qualcomm",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1834,830276,"   Perf. part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Perf",2,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1835,830094,"Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72",1,"Rel-16","R4","2019-03-01","2020-09-11",0.99,"RP-191285",null,"Nokia",null,"26/6/19: WID:RP-190665->RP-191285",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1836,830194,"   Core part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Core",2,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1837,830294,"   Perf. part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Perf",2,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1838,860030,"   UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-UEConTest",2,"Rel-16","R5","2019-12-16","2020-09-11",1,"RP-192506",null,"Airbus",null,"affects: LTE. tested: REL-16 WI LTE_PC2_B31_B72-Core; 25/9/20: 0%->100; 8/10/20: FCD:15/03/2020->09/20",null,86,44,null,null,"2020-01-14","2020-10-08"]
[1839,800056,"Additional LTE bands",null,1,"Rel-16",null,"2018-06-15","2021-09-21",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[1840,800075,"   Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1",2,"Rel-16","R4","2018-06-15","2021-09-21",1,"RP-202522","RP-211863","Ericsson",null,"basket WI¦16/1/19: WID:RP-181006->RP-182768¦26/3/19: WID:RP-182768->RP-190332; 14/1/20: WID:RP-190332->RP-192453; 26/3/20: WID:RP-192453->RP-200153; 28/7/20: WID:RP-200153->RP-201200; 13/9/21: Compl ",null,80,41,null,null,"2018-06-27","2021-09-13"]
[1841,800175,"      Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1842,800275,"      Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Perf",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1843,900052,"      UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16 ","LTE_bands_R16_M1_NB1-UEConTest",3,"Rel-16","R5","2020-12-14","2021-09-08",1,"RP-202522",null,"Ericsson ",null,"tested: REL-16 WI LTE_bands_R16_M1_NB1-Core ; 8/4/21: 0%->26; 2/7/21: 26%->80",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1844,800076,"   Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2",2,"Rel-16","R4","2018-06-15","2021-09-21",1,"RP-202523","RP-211864","Ericsson",null,"basket WI¦no Perf. part¦16/1/19: WID:RP-181007->RP-182769¦26/3/19: WID:RP-182769->RP-190333; 14/1/20: WID:RP-190333->RP-192454; 26/3/20: WID:RP-192454->RP-200154; 13/9/21: Compl:86%->100% ; ",null,80,41,null,null,"2018-06-27","2021-09-13"]
[1845,800176,"      Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2-Core",3,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-201201",null,"Ericsson",null,"basket WI¦no Perf. part¦26/3/19: WID:RP-182769->RP-190333; 28/7/20: WID:RP-200154->RP-201201; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1846,900053,"      UE Conformance Test Aspects - Additional LTE bands for UE category M2 and/or NB2 in Rel-16 ","LTE_bands_R16_M2_NB2-UEConTest",3,"Rel-16","R5","2020-12-14","2021-09-08",1,"RP-202523",null,"Ericsson ",null,"tested: REL-16 WI LTE_bands_R16_M2_NB2-Core ; 8/4/21: 0%->33; 2/7/21: 33%->59",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1847,800079,"Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2",1,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-181482",null,"NTT DOCOMO",null,null,null,80,41,null,null,"2018-06-27","NA"]
[1848,800179,"   Core part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Core",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-181482",null,"NTT DOCOMO",null,"14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1849,800279,"   Perf. part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Perf",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-181482",null,"NTT DOCOMO",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1850,800082,"Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM",1,"Rel-16","R1","2018-06-15","2022-12-22",0.56999999999999995,"RP-193190",null,"LG Electronics",null,"16/1/19: WID:RP-181431->RP-182864¦26/3/19: WID:RP-182864->RP-190700; 26/6/19: WID:RP-190700->RP-191546; 8/10/19: WID:RP-191546->RP-191997; 14/1/20: WID:RP-191997->RP-193190",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1851,800182,"   Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Core",2,"Rel-16","R1","2018-06-15","2019-06-15",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1852,800282,"   Perf. part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Perf",2,"Rel-16","R4","2018-06-15","2019-06-15",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1853,890047,"   UE Conformance Test Aspects - Cross Link Interference (CLI) handling for NR ","NR_CLI-UEConTest",2,"Rel-16","R5","2020-09-17","2022-12-22",0.19,"RP-210716","RP-221247","Vijay Balasubramanian","vijayb@qti.qualcomm.com","tested: CLI part of REL-16 WI NR_CLI_RIM-Core ; 7/4/21: WID:RP-201940->RP-210716; 8/4/21: 0%->5; 20/6/22: FCD:17/12/2021->22/12/2022; Compl:5%->19%; Stat Rep: ->RP-221247; Rapporteur: Qualcomm->Vijay Balasubramanian; Rap eMail: ->vijayb@qti.qualcomm.c...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1854,800086,"DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE",1,"Rel-16","R1","2018-06-15","2019-12-15",1,"RP-192766",null,"Huawei",null,"16/1/19: WID:RP-181485->RP-182901; 14/1/20: WID:RP-182901->RP-192766",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1855,800186,"   Core part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Core",2,"Rel-16","R1","2018-06-15","2019-12-15",1,"RP-192766",null,"Huawei",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1856,800286,"   Perf. part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Perf",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-192766",null,"Huawei",null,"28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1857,820071,"Transfer of Iuant interface specifications from 25-series to 37-series","Iuant_transfer",1,"Rel-16","R3","2018-12-13","2019-03-18",1,"RP-190160",null,"Huawei",null,"administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf .",null,82,42,null,null,"2019-01-16","2019-03-26"]
[1858,820171,"   Core part: Transfer of Iuant interface specifications from 25-series to 37-series","Iuant_transfer-Core",2,"Rel-16","R3","2018-12-13","2019-03-18",1,"RP-190160",null,"Huawei",null,"administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf .",null,82,42,null,null,"2019-01-16","2019-03-26"]
[1859,820072,"Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility","Direct_data_fw_NR",1,"Rel-16","R3","2018-12-13","2019-06-18",1,"RP-182886",null,"Ericsson",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[1860,820172,"   Core part: Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility","Direct_data_fw_NR-Core",2,"Rel-16","R3","2018-12-13","2019-06-18",1,"RP-182886",null,"Ericsson",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1861,800089,"Even further mobility enhancement in E-UTRAN","LTE_feMob",1,"Rel-16","R2","2018-06-15","2022-06-22",0.99,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 26/6/19: WID:RP-190272->RP-190921; 26/3/20: WID:RP-190921->RP-200148",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1862,800189,"   Core part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Core",2,"Rel-16","R2","2018-06-15","2019-12-15",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1863,800289,"   Perf. part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Perf",2,"Rel-16","R4","2018-06-15","2019-12-15",1,"RP-200148",null,"China Telecom",null,"26/3/19: WID:RP-181475->RP-190272; 7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[1864,880066,"   UE Conformance Test Aspects - Even further mobility enhancement in E-UTRAN","LTE_feMob-UEConTest",2,"Rel-16","R5","2020-06-22","2022-06-22",1,"RP-200731","RP-221293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","8/10/20: 0%->5; 8/4/21: 5%->16; 13/9/21: Compl:16%->32%; 13/9/21: CD:Wed 15/12/21->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211837 ; ; ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1865,820078,"410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR",1,"Rel-16","R4","2018-12-13","2020-12-17",0.99,"RP-191287",null,"Nokia",null,"26/6/19: WID:RP-182898->RP-191287",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1866,820178,"   Core part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR-Core",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-182898",null,"Nokia",null,"26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1867,820278,"   Perf. part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR-Perf",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-182898",null,"Nokia",null,"26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[1868,890041,"   UE Conformance Test Aspects - 410-430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe (Bands 87 and 88) ","LTE410_Europe_PPDR-UEConTest",2,"Rel-16","R5","2020-09-17","2020-12-17",1,"RP-201479",null,"Nokia ",null,"tested: REL-16 WI LTE410_Europe_PPDR-Core ; 6/1/21: 0%->100",null,89,45,null,null,"2020-09-25","2021-01-06"]
[1869,850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-15",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[1870,850172,"   Core part: Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC-Core",2,"Rel-16","R2","2019-09-19","2020-03-15",1,"RP-192408",null,"Reliance Jio",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1871,850272,"   Perf. part: Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC-Perf",2,"Rel-16","R4","2019-09-19","2020-03-15",1,"RP-192408",null,"Reliance Jio",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[1872,0,"All other Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1873,840001,"5G Media Streaming stage 3 ","5GMS3",1,"Rel-16","S4","2019-06-06","2020-09-15",1,"SP-190464",null,"Paul Szucs, Sony","Paul.Szucs@Sony.com","13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->70; 25/3/20: FCD:12/03/2020->06/20; 10/6/20: 70%->85; 26/6/20: FCD:12/06/2020->09/20; 12/9/20: 85%->100. Moved to Rel-16","26.234; 26.247; 26.117; 26.502; 26.503; 26.504; 26.511; 26.512",84,43,null,null,"2019-05-31","2020-09-12"]
[1874,880009,"User Plane Integrity Protection ","UPIP_SEC",1,"Rel-16","S3","2020-06-12","2020-06-25",1,"SP-200656",null,"Tim Evans, Vodafone Group ","tim.evans1@vodafone.com ","33.501; 33.401 ; 26/6/20: 0%->100; 25/9/20: WID:SP-200354->SP-200656",null,88,45,null,null,"2020-06-25","2020-09-25"]
[1875,880001,"Removal of H.263 and MPEG-4 Visual from 3GPP Services","RM_H263_MP4V",1,"Rel-16","S4","2020-06-25","2020-09-16",1,"SP-200400",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","26.140; 26.114; 26.244; 26.346; 26.234; 26/6/20: 0%->60; 12/9/20: 60%->100",null,88,45,null,null,"2020-06-25","2020-09-12"]
[1876,830086,"Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications","MSR_GSM_UTRA_LTE_NR",1,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-190642",null,"Ericsson",null,null,null,83,42,null,null,"2019-03-26","NA"]
[1877,830186,"   Core part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Core",2,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1878,830286,"   Perf. Part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Perf",2,"Rel-16","R4","2019-03-01","2019-09-15",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[1879,840066,"Volume Based Charging Aspects for VoLTE","VBCLTE",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50","32.251; 32.260; 32.298; 32.299",84,43,null,null,"2018-09-06","2019-03-14"]
[1880,810021,"   Stage 2 of VBCLTE","VBCLTE",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50; 13/9/19: 50%->55; 13/9/19: FCD:14/06/2019->12/20; 6/12/19: 55%->100","32.251; 32.260; 32.298; 32.299",81,41,null,null,"2018-09-06","2019-12-06"]
[1881,840012,"   CT aspects of VBCLTE","VBCLTE",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-191110",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ",null,null,84,43,null,null,"2019-05-31","NA"]
[1882,840067,"      Stopped - CT1 aspects of VBCLTE","VBCLTE",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191110",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/20: 0%->100",24.228999999999999,84,43,null,null,"2019-05-31","2020-07-02"]
[1883,840068,"      CT3 aspects of VBCLTE","VBCLTE",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201206",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","6/12/19: 0%->100; 26/6/20: WID:CP-191110->CP-201206","29.212; 29.213; 29.214",84,43,null,null,"2019-05-31","2020-06-26"]
[1884,820070,"Integrated access and backhaul for NR","NR_IAB",1,"Rel-16",null,"2017-03-15","2020-06-12",1,"RP-210442",null,"Qualcomm",null,"follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 26/6/19: WID:RP-190712->RP-191558; 8/10/19: WID:RP-191558->RP-192188; 14/1/20: WID:RP-192188->RP-193226; 26/3/20: WID:RP-193226->RP-200084; 28/7/20: WID:RP-200084->RP-200840; 25/9/2 ",38.808999999999997,82,42,null,null,"2019-01-16","2021-04-07"]
[1885,750047,"   Study on NR_IAB","FS_NR_IAB",2,"Rel-16","R2","2017-03-15","2018-12-14",1,"RP-181349",null,"Qualcomm",null,"TR 38.8XX¦30/6/17: 38.874 added;¦19/9/17: WID: RP-170831->RP-171880¦8/1/18: WID: RP-171880->RP-17229027/3/18: Compl:0%->20%¦27/6/18: Compl:20%->50%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18;¦16/1/19: 50%->100",38.874000000000002,75,38,null,null,"2017-03-21","2019-01-16"]
[{"$f":"A1886+1","v":1886},850009,"   Architecture enhancements for the support of Integrated access and backhaul (IAB) ","IABARC",2,"Rel-16","S2","2019-09-19","2020-03-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-09-13"]
[1887,850060,"      Stage 2 of IABARC","IABARC",3,"Rel-16","S2","2019-09-19","2019-12-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33; 6/12/19: 33%->100","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-12-06"]
[1888,850002,"      CT4 aspects of IABARC ","IABARC",3,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP201074",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: WID:CP-193015->CP 201074","24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 ",85,43,null,null,"2019-09-13","2020-07-02"]
[1889,880059,"      CT1 aspects of IABARC ","IABARC",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP201074",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: 0%->100","24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 ",85,43,null,null,"2019-09-13","2020-07-02"]
[1890,820170,"   Core part: NR_IAB","NR_IAB-Core",2,"Rel-16","R2","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 28/7/20: WID:RP-200084->RP-200840; 25/9/20: 0%->100; 25/9/20: 38.175 added;; 25/9/20: 38.809 added;","38.175; 38.809",82,42,null,null,"2019-01-16","2020-09-25"]
[1891,820270,"   Perf. Part: NR_IAB","NR_IAB-Perf",2,"Rel-16","R4","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added;; 2/7/21: 0%->100","38.809; 38.176-1; 38.176-2",82,42,null,null,"2019-01-16","2021-07-02"]
[1892,850020,"   Security for IAB ","NR_IAB",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190902",null,"Rajavelsamy Rajadurai, Samsung ","rajvel{@]samsung.com ","; 6/12/19: 0%->65; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1893,860013,"User Plane Gateway Function for Inter-PLMN Security ","UPGF",1,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191123",null,"Steve Kohalmi, Juniper Networks ","skohalmi@juniper.net ","; 6/12/19: 0%->90; 25/3/20: 90%->100",33.500999999999998,86,44,null,null,"2019-12-06","2020-03-25"]
[1894,790003,"Enhancements to IMS for new real time communication services","enIMS",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180137",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","7/6/18: 0%->25¦10/9/18: 25%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100","22.261; 22.468; 22.228; 22.280; 22.281; 22.282; 22.179",79,40,null,null,"2018-03-15","2018-12-04"]
[1895,820028,"Enhancement of 5G PCC related services ","en5GPccSer",1,"Rel-16","C3","2018-12-13","2019-12-19",1,"CP-183246",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","¦14/3/19: 0%->10; 31/5/19: 10%->60; 13/9/19: 60%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 ",82,42,null,null,"2018-12-07","2020-03-26"]
[1896,810023,"Energy efficiency of 5G","EE_5G",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-191193",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com ","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->45; 13/9/19: 45%->70; 12/12/19: WID:SP-180819->SP-191193; 12/12/19: FCD:13/12/2019->03/20; 26/3/20: 70%->95; 28/6/20: 95%->100","28.540; 28.541; 28.552; 28.554",81,41,null,null,"2018-09-06","2020-06-28"]
[1897,820039,"Signalling Improvements for Network Efficiency in 5GS ","SINE_5G",1,"Rel-16","C1","2018-12-13","2019-12-12",1,"CP-190142",null,"Shu, Lin ","shulin@huawei.com ","¦14/3/19: 0%->50¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183085->CP-190142; 31/5/19: 50%->75; 13/9/19: 75%->85; 6/12/19: 85%->95; 26/3/20: 95%->100","24.501; 24.301; 24.368; 27.007; 24.008 ",82,42,null,null,"2018-12-07","2020-03-26"]
[1898,790001,"New Services and Markets Technology Enablers – Phase 2 ","SMARTER_Ph2",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180589",null,"Li, Alice, Vodafone","alice.li@vodafone.com","7/6/18: WID:SP-180138->SP-180313¦7/6/18: 0%->10¦10/9/18: 10%->40¦4/12/18: 40%->100","22.261; 22.278",79,40,null,null,"2018-03-15","2018-12-04"]
[1899,780055,"5G Voice Service Continuity ","5GVSC",1,"Rel-16","S1","2017-12-21","2018-03-13",1,"SP-171077",null,"Qun Wei, China Unicom","weiqun5@chinaunico.cn","16/3/18: 0%->100",22.260999999999999,78,40,null,null,"2017-12-21","2018-03-16"]
[1900,790015,"Security Assurance Specification for 5G ","SCAS_5G",1,"Rel-16","S3","2018-03-15","2019-09-13",1,"SP-180689",null,"Marcus Wong, Huawei Technologies ","mwong@huawei.com","27/3/18: added: 33.514¦33.513¦33.511¦33.512¦33.515 ¦6/8/18: 33.511 to 515 added;¦10/9/18: 0%->10¦2/10/18: WID:SP-180238->SP-180689¦7/12/18: 10%->20¦20/3/19: 20%->60; 31/5/19: 60%->75; 13/9/19: 75%->100","33.216; 33.926; 33.515; 33.511; 33.512; 33.513; 33.514; 33.515",79,40,null,null,"2018-03-15","2019-09-13"]
[1901,840069,"5GS Transfer of Policies for Background Data Transfer","xBDT",1,"Rel-16",null,"2019-03-07","2020-03-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com",null,"23.501; 23.502; 23.503",84,43,null,null,"2018-06-06","NA"]
[1902,800030,"   Stage 2 of xBDT","xBDT",2,"Rel-16","S2","2019-03-07","2019-12-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com","31/5/19: 0%->100","23.501; 23.502; 23.503",80,41,null,null,"2018-06-06","2019-05-31"]
[1903,840014,"   CT aspects of xBDT","xBDT",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","17/9/19: WID:CP-191113->CP-192182",null,84,43,null,null,"2019-05-31","2019-09-17"]
[1904,840070,"      CT1 aspects of xBDT","xBDT",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","13/9/19: 0%->100",24.526,84,43,null,null,"2019-05-31","2019-09-13"]
[1905,840071,"      CT3 aspects of xBDT","xBDT",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","13/9/19: 0%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","29.519; 29.513; 29.514; 29.122; 29.522; 29.525",84,43,null,null,"2019-05-31","2020-03-26"]
[1906,850057,"      CT4 aspects of xBDT","xBDT",3,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","26/3/20: 0%->100",null,85,43,null,null,"2019-05-31","2020-03-26"]
[1907,770020,"Service Interactivity","SerInter",1,"Rel-16","S4","2017-09-08","2019-12-12",1,"SP-170796",null,"Lo, Charles, Qualcomm Incorporated","clo@qti.qualcomm.com","15/12/17: 0%->10¦16/3/18: 10%->20¦7/6/18: 20%->40¦7/6/18: FCD:06/18->12/18. Moved from Rel-15¦10/9/18: 40%->50¦7/12/18: 50%->60¦7/3/19: 60%->70¦7/3/19: FCD:12/18->06/19; 31/5/19: FCD:14/06/2019->09/20; 31/5/19: 70%->80; 13/9/19: FCD:12/09/2019->12/20; ","26.346; 26.247; 26.347",77,39,null,null,"2017-09-08","2019-12-06"]
[1908,800002,"Alternative EVS implementation using updated fixed-point basic operators","Alt_FX_EVS",1,"Rel-16","S4","2018-06-06","2018-12-14",1,"SP-180286",null,"Pawate, Raj, Cadence Design Systems Inc","pawateb@cadence.com","6/8/18: 26.452 added;¦10/9/18: 0%->20¦7/12/18: 20%->90¦7/3/19: 90%->100","26.441; 26.442; 26.444; 26.445; 26.446; 26.447; 26.449; 26.450; 26.451; 26.952; 26.452",80,41,null,null,"2018-06-06","2019-03-07"]
[1909,800046,"Shared Data Handling on Nudm and Nudr","Shared_Data",1,"Rel-16","C4","2018-06-06","2018-12-14",1,"CP-181136",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com","10/9/18: 0%->90¦10/12/18: 90%->100","29.503; 29.505; 29.504",80,41,null,null,"2018-06-06","2018-12-10"]
[1910,790019,"Usage of CAPIF for xMB API","CAPIF4xMB",1,"Rel-16","S4","2018-03-15","2018-12-14",1,"SP-180031",null,"Thorsten Lohmar, Ericsson LM ","Thorsten.lohmar@ericsson.com","7/6/18: 0%->25¦6/8/18: 26.348 added;¦10/9/18: 25%->40¦7/12/18: 40%->100","26.346, new; 26.348",79,40,null,null,"2018-03-15","2018-12-07"]
[1911,800009,"Policy delivery to UE for background data transfer","PDBDT",1,"Rel-16","S1","2018-05-08","2018-06-15",1,"SP-180324",null,"Takatsugu Kito, KDDI","ta-kito at kddi dot com ","10/9/18: 90%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-09-10"]
[1912,790004,"QoS Monitoring ","QoS_MON",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180141",null,"Amar Deol ","amar.deol@huawei.com","7/6/18: 0%->60¦10/9/18: 60%->85¦10/9/18: FCD:06/18->12/18¦4/12/18: 85%->100",22.260999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[1913,800005,"Inter-RAT Mobility requirements for real time service","MOBRT",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180592",null,"Yang Xu, Oppo","xuyang@oppo.com","10/9/18: 70%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-09-10"]
[1914,760058,"Management of QoE measurement collection","QOED",1,"Rel-16","S5","2017-06-05","2019-12-12",1,"SP-181069",null,"Petersen, Robert, Ericsson","robert <dot> petersen <at>ericsson<dot>ericsson","30/6/17: 28.309 added;¦30/6/17: 28.308 added;¦30/6/17: 28.307 added;¦30/6/17: 28.406 added;¦11/9/17: 0%->5¦15/12/17: 5%->15¦16/3/18: 15%->25¦7/6/18: FCD:06/18->12/18. 16/6/16: moved from Rel-15¦10/9/18: 25%->30¦7/12/18: 30%->40¦13/12/18: FCD: ; 31/5/ ","32.101; 32.103; 6 new TS; 28.309; 28.308; 28.307; 28.406; 28.405; 28.404",76,39,null,null,"2017-06-07","2020-09-13"]
[1915,760059,"Study on network policy management for mobile networks based on NFV scenarios","FS_NETPOL",1,"Rel-15","S5","2017-06-05","2018-06-14",1,"SP-170593",null,"China Mobile Jinglei Liu ","liujinglei@chinamobile.com","30/6/17: 32.871 added;¦11/9/17: 0%->20¦15/12/17: 20%->30¦16/3/18: 30%->35¦7/6/18: 35%->100","new; 32.871",76,39,null,null,"2017-06-05","2018-06-07"]
[1916,810025,"Network policy management for mobile networks based on NFV scenarios","NETPOL",1,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-191194",null,"China Mobile Hao Zhang ","zhanghao@chinamobile.com","7/12/18: 0%->10; 13/9/19: 10%->85; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 85%->100; 12/12/19: WID:SP-180821->SP-191194","New",81,41,null,null,"2018-09-06","2019-12-12"]
[1917,810024,"OAM aspects of LTE and WLAN integration","OAM_LTE_WLAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180820",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","7/12/18: 0%->50¦14/3/19: 50%->100","32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659",81,41,null,null,"2018-09-06","2019-03-14"]
[1918,810026,"Methodology for 5G management specifications","METHOGY",1,"Rel-16","S5","2018-09-06","2019-03-15",1,"SP-180822",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com","7/12/18: 0%->60¦14/3/19: 60%->85; 13/9/19: 85%->100","New; 32.156",81,41,null,null,"2018-09-06","2019-09-13"]
[1919,820030,"Nchf Online and Offline charging services ","OFSBI_CH",1,"Rel-16","S5","2018-12-13","2019-09-19",1,"SP-181066",null,"Zhu Lei, Huawei","Zhulei@huawei.com ","¦14/3/19: 0%->40; 31/5/19: 40%->70; 13/9/19: 70%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-09-13"]
[1920,820031,"Charging Enhancement of 5GC interworking with EPC ","5GIEPC_CH",1,"Rel-16","S5","2018-12-13","2019-09-19",1,"SP-181067",null,"Chen Shan, Huawei ","chenshan@huawei.com ","¦14/3/19: 0%->30; 31/5/19: 30%->60; 13/9/19: 60%->100","32.255; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-09-13"]
[1921,820032,"NRM enhancements ","eNRM",1,"Rel-16","S5","2018-12-13","2020-03-12",1,"SP-190778",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","¦14/3/19: 0%->10¦21/3/19: WID:SP-181068 ->SP-190140¦21/3/19: FCD:019->09/19; 31/5/19: 10%->20; 13/9/19: 20%->40; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-190140->SP-190778; 26/3/20: 40%->92; 28/6/20: 92%->98; 13/9/20: 98%->100","28.540; 28.541; 28.622 ; 28.623; 28.620",82,42,null,null,"2018-12-07","2020-09-13"]
[1922,820033,"Network Exposure Charging in 5G System Architecture ","5GS_Ph1_NEFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181070",null,"Tornkvist, Robert, Ericsson ","robert(dot)tornkvist(at)Ericsson(dot)com ","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100","32.240; 32.254; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-12-06"]
[1923,820034,"Charging AMF in 5G System Architecture Phase 1 ","5GS_Ph1_AMFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181071",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->70; 6/12/19: 70%->100","32.240; 32.290; 32.291; 32.298; 32.297 ",82,42,null,null,"2018-12-07","2019-12-06"]
[1924,820036,"Trace Management in the context of Services Based Management Architecture ","TM_SBMA",1,"Rel-16","S5","2018-12-13","2020-03-12",1,"SP-181073",null,"Andrianov, Anatoly, Nokia ","anatoly.andrianov@nokia.com ","; 31/5/19: 0%->10; 13/9/19: FCD:19/06/2019->03/20; 26/3/20: 10%->50; 28/6/20: 50%->100","32.421; 32.422; 28.530; 28.532; 28.533; 28.540; 28.541 ",82,42,null,null,"2018-12-07","2020-06-28"]
[1925,820005,"Lawful Interception Rel-16 ","LI16",1,"Rel-16","S3LI","2018-12-13","2021-06-11",1,"SP-181210",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ","31/5/19: 0%->15; 13/9/19: 15%->40; 6/12/19: 40%->55; 25/3/20: 55%->60; 25/3/20: FCD:19/12/2019->03/20; 26/6/20: FCD:13/03/2020->09/20; 26/6/20: 60%->85; 12/9/20: 85%->92; 5/12/20: 92%->97; 19/3/21: 97%->99; 19/3/21: FCD:15/09/2020->06/21; 11/6/21: 99%- ","33.107; 33.108; 33.126; 33.127; 33.128 ",82,42,null,null,"2018-12-07","2021-06-11"]
[1926,820038,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 30/6/20: 99%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",82,42,null,null,"2018-12-07","2020-06-30"]
[1927,870077,"   CT1 aspects of IMSProtoc16","IMSProtoc16",2,"Rel-16","C1","2018-12-13","2019-12-13",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019->","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",87,44,null,null,"2018-12-07","2020-04-23"]
[1928,880060,"   CT3 aspects of IMSProtoc16","IMSProtoc16",2,"Rel-16","C3","2018-12-13","2019-12-13",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019->","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",87,44,null,null,"2018-12-07","2020-04-23"]
[1929,870078,"   (IETF) Location Source Parameter for the SIP Geolocation Header Field (draft-ietf-sipcore-locparam)","5GProtoc16",2,"Rel-16","C1-IETF","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 30/6/20: 90%->100; 9/4/21: RFC 8787 added;","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ; RFC 8787",87,44,null,null,"2018-12-07","2021-04-09"]
[1930,820041,"Stage-3 5GS NAS protocol development ","5GProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 25/3/20: WID:CP-183087->CP-200146","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-03-25"]
[1931,820049,"   Stage-3 5GS NAS protocol development general aspects","5GProtoc16",2,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 26/6/20: 98%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-06-26"]
[1932,820050,"   Stage-3 5GS NAS protocol development for support for non-3GPP accesses","5GProtoc16-non3GPP",2,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 25/3/20: FCD:19/12/2019->03/20; 30/6/20: 50%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-06-30"]
[1933,820042,"Stage-3 SAE Protocol Development for Rel16","SAES16",1,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","NA"]
[1934,820046,"   Stage-3 SAE Protocol Development for Rel16 general aspects","SAES16",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-03-26"]
[1935,820047,"   Stage-3 SAE Protocol Development for Rel16 for CS Fallback in EPS","SAES16-CSFB",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[1936,820048,"   Stage-3 SAE Protocol Development Rel16 for support for non-3GPP accesses","SAES16-non3GPP",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[1937,840018,"S6b Optional for ePDG connected to 5GS ","5GS_S6b_Optional",1,"Rel-16","S2","2019-05-09","2019-06-06",1,"SP-190447",null,"Irfan Ali, Cisco ","irfaali at cisco dot com ","6/6/19: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1938,840002,"Service Based Interface Protocol Improvements ","SBIProtoc16",1,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ",null,null,84,43,null,null,"2019-05-31","NA"]
[1939,840052,"   CT3 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","13/9/19: 0%->25; 6/12/19: 25%->75; 26/3/20: 75%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554",84,43,null,null,"2019-05-31","2020-03-26"]
[1940,840053,"   CT4 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","31/5/19: 0%->10; 6/12/19: 10%->90; 26/3/20: 90%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.531; 29.540; 29.518; 29.571; 29.572; 29.573",84,43,null,null,"2019-05-31","2020-06-26"]
[1941,840008,"Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 ","ISAT-MO-WITHDRAW",1,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191151",null,"Dawes, Peter, Vodafone ","peter(dot)dawes(at)vodafone(dot)com ","; 13/9/19: 0%->100",24.323,84,43,null,null,"2019-05-31","2019-09-13"]
[1942,840051,"Lawful Interception Report Rel-16 ","LIR16",1,"Rel-16","S3LI","2019-06-06","2019-12-12",0,"SP-190342",null,"Nag Rao, Nokia ","nagaraja.rao@nokia.com ",null,"New ",84,43,null,null,"2019-05-31","NA"]
[1943,850003,"RTCP Verification for Real-Time Services ","RTCPVer",1,"Rel-16","S4","2019-09-13","2020-03-12",1,"SP-190639",null,"Burman, Bo, Ericsson LM, ","bo.burman@ericsson.com ","; 8/10/19: 26.139 added;; 6/12/19: 0%->60; 25/3/20: 60%->100","26.114; 24.380; 24.581; 26.281; New ; 26.139",85,43,null,null,"2019-09-13","2020-03-25"]
[1944,850025,"Network Slice Performance and Analytics Charging in 5G System ","5GS_NSPACH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190780",null,"Chen Shan, Huawei ","chenshan@huawei.com ","8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201",85,43,null,null,"2019-09-13","2020-09-13"]
[1945,850026,"Closed loop SLS Assurance ","COSLA",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190781",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","; 8/10/19: 28.536 added;; 26/3/20: 0%->55; 28/6/20: 55%->100","28.533; 28.540; 28.541; 28.530; 28.531; 28.545; 28.546; 28.550; 28.552; 28.553 ; 28.536; 28.535",85,43,null,null,"2019-09-13","2020-06-28"]
[1946,850027,"Streaming trace reporting ","OAM_RTT",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190782",null,"Andrianov, Anatoly, Nokia ","anatoly.andrianov@nokia.com ","; 26/3/20: 0%->25; 28/6/20: 25%->100","32.421; 32.422; 32.423; 28.532; 28.533 ",85,43,null,null,"2019-09-13","2020-06-28"]
[1947,850031,"Enhancement of 3GPP management system for multiple tenant environment support ","MEMTANE",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190786",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","28.531; 28.532; 28.533; 28.541; 28.552; 28.554 ",85,43,null,null,"2019-09-13","2020-06-28"]
[1948,850033,"Network Slice Management Charging in 5G System ","5GS_NSMCH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190788",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 8/10/19: 28.202 added;; 6/12/19: 0%->5; 28/6/20: 5%->50; 13/9/20: 50%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.202",85,43,null,null,"2019-09-13","2020-09-13"]
[1949,850034,"Management Aspects of 5G Service-Level Agreement ","MA5SLA",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-200185",null,"Hu, Yushuang, CMCC ","huyushuang@chinamobile.com ","; 25/3/20: WID:SP-190789->SP-200185; 26/3/20: 0%->100","28.540; 28.541 ",85,43,null,null,"2019-09-13","2020-03-26"]
[{"$f":"A1950+1","v":1950},850001,"Load and Overload Control of 5GC Service Based Interfaces ","LOLC",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","; 25/3/20: WID:CP-192019->CP-200059",null,85,43,null,null,"2019-09-13","2020-03-25"]
[1951,800044,"   Study on Load and Overload Control of 5GC Service Based Interfaces","FS_LOLC",2,"Rel-16","C4","2018-06-06","2019-06-14",1,"CP-181195",null,"Sridhar Bhaskaran (Huawei)","sridhar.bhaskaran@huawei.com","6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100","New; 22.943",80,41,null,null,"2018-06-06","2019-12-06"]
[1952,850052,"   Deleted: C3 aspects of LOLC (TBD)","LOLC",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","2/7/20: deleted, put at 100% (was at 0)","TBD",85,43,null,null,"2019-09-13","NA"]
[1953,850054,"   C4 aspects of LOLC ","LOLC",2,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","; 26/3/20: 0%->90; 26/6/20: 90%->100","29.500; 29.510",85,43,null,null,"2019-09-13","2020-06-26"]
[1954,880056,"5GS Enhanced support of Over the air (OTA) mechanism for UICC configuration parameter update ","5GS_OTAF",1,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1955,880057,"   C1 aspects of 5GS_OTAF","5GS_OTAF",2,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1956,850005,"   C4 aspects of 5GS_OTAF","5GS_OTAF",2,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1957,830026,"Integration of ONAP and 3GPP 5G management framework","ONAP3GPP",1,"Rel-16","S5","2019-03-07","2020-03-12",1,"SP-190139",null,"SMITH David K., AT&T ","DS9930@att.com","31/5/19: 0%->10; 13/9/19: 10%->25; 13/9/19: FCD:05/03/2020->03/20; 26/3/20: 25%->100","28.540; 28.622; 28.623; 28.532",83,42,null,null,"2019-03-14","2020-03-26"]
[1958,860011,"Support of Hybrid DASH/HLS over eMBMS ","DAHOE",1,"Rel-16","S4","2019-12-06","2020-03-12",1,"SP-190988",null,"Thienot, Cédric, Enensys","cedric.thienot@enensys.com","25/3/20: 0%->100","26.346; 26.347; 26.348",86,44,null,null,"2019-12-06","2020-03-25"]
[1959,860017,"3GPP profiles for cryptographic algorithms and security protocols ","CryptPr",1,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191129",null,"Christine Jost, Ericsson ","christine.jost@ericsson.com ","; 25/3/20: 0%->100","33.210, 33.310, 33.501 ",86,44,null,null,"2019-12-06","2020-03-25"]
[1960,860020,"CHF-controlled quota management ","CHFCQM",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191189",null,"Lagha, Naceur, Amdocs ","nlagha@amdocs.com ","; 26/3/20: 0%->50; 28/6/20: 50%->100","32.255; 32.290; 32.291 ",86,44,null,null,"2019-12-06","2020-06-28"]
[1961,860021,"Management of MDT in 5G ","5GMDT",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191190",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 26/3/20: 0%->100","32.421; 32.422; 32.423; 28.532; 28.533 ",86,44,null,null,"2019-12-06","2020-03-26"]
[1962,860023,"5G management capabilities ","5GMNC",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191195",null,"CORNILY, Jean-Michel, ORANGE ","jeanmichel.cornily@orange.com ","; 26/3/20: 0%->100",28.532,86,44,null,null,"2019-12-06","2020-03-26"]
[1963,860001,"Nudsf Service Based Interface ","NUDSF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193270",null,"Askerup, Anders, Hewlett Packard Enterprise, ","Anders.Askerup@hpe.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.510; 29.500 ",86,44,null,null,"2019-12-06","2020-07-02"]
[1964,840029,"Study on Nudsf Service Based Interface ","FS_NUDSF",1,"Rel-16","C4","2019-06-06","2019-12-12",1,"CP-191236",null,"Askerup, Anders, Hewlett Packard Enterprise ","Anders.Askerup@hpe.com ","31/5/19: 0%->10; 6/12/19: 10%->100",29.808,84,43,null,null,"2019-05-31","2019-12-06"]
[1965,860002,"Nsoraf Service Based Interface ","NSORAF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193017",null,"EL MOATAMID, Abdessamad, Orange ","abdessamad.elmoatamid@orange.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.503; 29.510 ",86,44,null,null,"2019-12-06","2020-07-02"]
[1966,860004,"Video enhancement of IMS CAT/CRS/announcement services ","eIMSVideo",1,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193149",null,"Hongxia Hao, Huawei ","haohongxia@huawei.com ","; 26/3/20: 0%->33; 26/6/20: 33%->100","24.182; 24.183; 24.628 ",86,44,null,null,"2019-12-06","2020-06-26"]
[1967,870010,"Ambient noise test methodology for evaluation of acoustic UE performance ","ANTeM",1,"Rel-16","S4","2020-02-17","2020-03-25",1,"SP-200051",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.de ","; 26/6/20: 0%->100",26.132000000000001,87,44,null,null,"2020-03-25","2020-06-26"]
[1968,890045,"UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR ","B1C_BDS_pos_UEConTest",1,"Rel-16","R5","2020-09-17","2021-09-08",1,"RP-201777",null,"CATT ",null,"tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71; 2/7/21: FCD:Thu 17/06/->09/21; 29/9/21: 71%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1969,911002,"UE Conformance Test Aspects - Support of eCall over IMS for NR ","NR_EIEI-UEConTest",1,"Rel-16","R5","2021-03-12","2022-09-22",0.79,"RP-210704","RP-221248","Bharadwaj Kumar Cheruvu, Qualcomm","bcheruvu[at]qti.qualcomm.com","tested: REL-16 TEI CRs of SA2/CT1/R2; compare LTE REL-14 WI EIEI-UEConTest \"Evolution to and Interworking with eCall in IMS\" ; 2/7/21: 0%->5; 22/3/22: ; ; 20/6/22: Rapporteur: Qualcomm->Bharadwaj Kumar Cheruvu, Qualcomm; Rap eMail: ->bcheruvu[at]qti.q...",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1970,960003,"UE Conformance Test Aspects Release 16 ","UEConTest_R16",1,"Rel-16","C6","2022-06-03","2023-09-12",0,"CP-221184",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","20/6/22: FCD:12/06/2023->09/20","31.121; 31.124 ",96,49,null,null,"2022-06-03","2022-06-20"]
[1971,770050,"(Small) Technical Enhancements and Improvements for Rel-16","TEI16",1,"Rel-16",null,"2017-09-11","2020-06-30",0,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,77,41,null,null,"2015-06-15","2015-06-15"]
[1972,800100,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446)","TEI16",2,"Rel-16","S3-IETF","2017-09-11","2018-12-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[1973,860099,"   (Small) Test Technical Enhancements and Improvements for Rel-16","TEI16_Test",2,"Rel-16","R5","2020-01-23","2020-06-30",0,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,86,41,null,null,"2018-06-27","NA"]
[1974,0,"Release 16 Studies with no corresponding Feature","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1975,0,"Release 16 Studies on 5G/5GS/5GC/NR","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1976,800029,"Stopped - Study on system architecture for next generation real time communication services","FS_NG_RTC",1,"Rel-16","S2","2018-06-06","2019-03-14",1,"SP-180508",null,"Yi Jiang ","jiangyi at chinamobile dot com","03/22: stopped at 0% (\"deprioritised\"in SA2 language)","New",80,41,null,null,"2018-06-06","2022-03-22"]
[1977,790014,"Study on security aspects of single radio voice continuity from 5G to UTRAN","FS_5G_UTRAN_SEC",1,"Rel-16","S3","2018-03-15","2019-03-15",1,"SP-180209",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","27/3/18: 33.856 added;¦7/6/18: 0%->50¦10/9/18: 50%->79¦7/12/18: 79%->100",33.856000000000002,79,40,null,null,"2018-03-15","2018-12-07"]
[1978,780023,"Study on supporting 256-bit algorithms for 5G ","FS_256_Algo",1,"Rel-16","S3","2017-12-15","2018-09-14",1,"SP-171054",null,"Evans, Tim, Vodafone Group","tim.evans1@vodafone.com","16/3/18: 0%->30¦7/6/18: 30%->55¦10/9/18: 55%->60¦7/12/18: 60%->100","new",78,40,null,null,"2017-12-15","2018-12-07"]
[1979,780001,"Study on User Plane Protocol in 5GC","FS_UPPS",1,"Rel-16","C4","2017-12-15","2019-06-14",1,"CP-182052",null,"Satoru Matsushima, SoftBank Corp","satoru.matsushima@g.softbank.co.jp","16/3/18: 0%->5¦2/10/18: WID:CP-173160->CP-182052¦2/10/18: FCD:09/18->06/19¦14/3/19: 20%->70; 31/5/19: 70%->90; 14/1/20: 90%->100",29.891999999999999,78,40,null,null,"2017-12-15","2020-01-14"]
[1980,790012,"Stopped - Study on Application Awareness Interworking between LTE and NR","FS_AAI_LTE_NR",1,"Rel-16","S2","2018-03-15","2019-03-14",1,"SP-180122",null,"Biao Long, China Telecom","longb.gd@chinatelecom.cn","7/6/18: 0%->30¦6/8/18: 23.727 added; 03/22: stopped at 30% (\"deprioritised\"in SA2 language)","new; 23.727",79,40,null,null,"2018-03-15","2022-03-22"]
[1981,800090,"Study on NR beyond 52.6 GHz","FS_NR_beyond_52GHz",1,"Rel-16","RP","2018-06-15","2018-09-14",1,"RP-181435",null,"Intel",null,"14/1/20: 0%->100","38.8xx",80,41,null,null,"2018-08-06","2020-01-14"]
[1982,800093,"Study on remote interference management for NR","FS_NR_RIM",1,"Rel-16","R1","2018-06-15","2018-12-15",1,"RP-181430",null,"CMCC",null,"TR 38.8xx¦see follow-up REL-16 WI NR_CLI_RIM¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[1983,801000,"Study on RAN-centric data collection and utilization for LTE and NR","FS_LTE_NR_data_collect",1,"Rel-16","R3","2018-06-01","2019-06-01",1,"RP-181456",null,"CMCC",null,"TR 37.8XX, related to SON, MDT; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[1984,801001,"Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR UEs","FS_NR_MIMO_OTA_test",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201069",null,"CAICT",null,"related REL-15 SI FS_NR_test_methods; 23/1/20: 0%->45; 23/1/20: WID:RP-181402->RP-182305; 28/7/20: WID:RP-182305->RP-201069; 28/7/20: 45%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1985,801002,"Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR","FS_NR_2RX_vehUE",1,"Rel-16","R4","2018-06-01","2018-12-15",1,"RP-181467",null,"Samsung",null,"TR 38.8XX¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[1986,750044,"Study of test methods for New Radio","FS_NR_test_methods",1,"Rel-16","R4","2017-03-15","2018-09-14",1,"RP-180546",null,"Intel",null,"TR 38.8XX¦19/6/17: Compl:0%->10%¦19/6/17: WID: RP-170824->RP-171021¦30/6/17: 38.810 added;19/9/17: Compl:10%->15%19/9/17: WID: RP-171021->RP-171828¦8/1/18: Compl:15%->20%27/3/18: Compl:20%->45%27/3/18: CD:Thu 15/ ¦2¦16/1/19: 75%->100",38.81,75,38,null,null,"2017-03-21","2019-01-16"]
[1987,750046,"Study on Non-Orthogonal Multiple Access (NOMA) for NR","FS_NR_NOMA",1,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181403",null,"ZTE",null,"TR 38.8XX¦19/6/17: WID: RP-170829->RP-171043¦30/6/17: 32.812 added;¦27/6/18: Compl:0%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦27/6/18: WID: RP-171043->RP-181403;¦16/1/19: 40%->100",32.811999999999998,75,38,null,null,"2017-03-21","2019-01-16"]
[1988,810033,"Stopped - Study of KDF negotiation for 5G System Security","FS_5GS_KDF",1,"Rel-16","S3","2018-09-06","2019-06-14",1,"SP-180691",null,"Ahmad Muhanna ","ahmad.muhanna@huawei.com","7/12/18: 0%->55¦20/3/19: 55%->100","New",81,41,null,null,"2018-09-06","2019-03-20"]
[1989,760053,"Study on Long Term Key Update Procedures","FS_LTKUP",1,"Rel-16","S3","2017-06-05","2018-12-14",1,"SP-170413",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","11/9/17: 0%->10¦15/12/17: 10%->70¦15/12/17: FCD:12/17->03/18¦16/3/18: 70%->90¦16/3/18: FCD:03/18->06/18¦7/6/18: FCD:06/18->12/18. 10/9/18: moved from Rel-15 as per SP-180687¦7/12/18: 90%->100","Internal TR",76,39,null,null,"2017-06-03","2018-12-07"]
[1990,810006,"Study on eXtended Reality (XR) in 5G","FS_5GXR",1,"Rel-16","S4","2018-10-02","2020-03-12",1,"SP-180667",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","2/10/18: Moved from Rel-17. 17/01/19: acronym corrected from FS_XR5G¦12/3/19: 0%->35; 31/5/19: 35%->45; 13/9/19: 45%->60; 13/9/19: FCD:13/12/2019->03/20; 25/3/20: 60%->100; 25/9/20: 26.998 added;","26.9xx; 26.998",81,41,null,null,"2018-09-06","2020-09-25"]
[1991,820060,"Study on 7 - 24 GHz frequency range for NR","FS_7to24GHz_NR",1,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-192076",null,"Huawei",null,"TR. 38.8xx¦26/3/19: WID:RP-182884->RP-190373; 8/10/19: WID:RP-190373->RP-192076; 28/7/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[1992,830006,"Study on UEs Supporting Handset Mode with Non-Traditional Earpieces","FS_HaNTE",1,"Rel-16","S4","2019-03-07","2019-09-05",1,"SP-190041",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com ","31/5/19: 0%->10; 13/9/19: 10%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[1993,830072,"Study on enhancement for disaggregated gNB architecture","FS_enh_disagg_gNB",1,"Rel-16","R3","2019-03-01","2019-12-15",1,"RP-191975",null,"China Telecom",null,"26/6/19: WID:RP-190702->RP-191481; 8/10/19: WID:RP-191481->RP-191975; 8/10/19: 38.823 added;; 14/1/20: 0%->100",38.823,83,42,null,null,"2019-03-26","2020-01-14"]
[1994,840090,"Study on 5G NR UE Application Layer Data Throughput Performance","FS_UE_5GNR_App_Data_Perf",1,"Rel-16","R5","2019-06-17","2021-09-08",1,"RP-212470",null,"Qualcomm",null,"compare: REL-11 SI FS_UE_App_Data_Perf; TR 37.9xx. 07/2019: title changed from \"…UE 5G NR…\"; 8/10/19: 37.901-5 added;; 14/1/20: WID:RP-191590->RP-192712; 8/10/20: 0%->87; 8/10/20: FCD:13/03/2020->12/20; 6/1/21: WID:RP-192712->RP-202849; 7/4/21: WID:RP- ","37.901-5",84,43,null,null,"2019-06-26","2022-04-05"]
[1995,0,"Release 16 other Studies","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1996,770002,"Study on using Satellite Access in 5G","FS_5GSAT",1,"Rel-16","S1","2017-09-08","2018-06-15",1,"SP-170702",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","15/12/17: 22.822 added;¦15/12/17: 0%->30¦15/12/17: FCD:12/17->06/18¦16/3/18: 30%->70¦7/6/18: 70%->100","New; 22.822",77,39,null,null,"2017-09-08","2018-06-07"]
[1997,770003,"Study on enhancements to IMS for new real time communication services","FS_enIMS",1,"Rel-16","S1","2017-09-08","2017-12-15",1,"SP-170703",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","11/9/17: 0%->20¦15/12/17: 22.823 added;¦15/12/17: 20%->75¦16/3/18: 75%->100; 25/9/20: 26.998 added;","New; 22.823; 26.998",77,39,null,null,"2017-09-08","2020-09-25"]
[1998,800037,"Stopped - Study on protocol enhancement for real time communication","FS_PROTIMP",1,"Rel-16","S5","2018-06-06","2020-06-12",1,"SP-180597",null,"Olaf Pollakowski, Nokia","olaf.pollakowski@nokia.com","6/8/18: 28.823 added;; 26/3/20: FCD:14/03/2019->06/20; 25/9/20: Stopped, so 0%->100","New; 28.823",80,41,null,null,"2018-06-06","2020-09-25"]
[1999,800038,"Study on integration of ONAP and 3GPP configuration management services for 5G networks","FS_ONAPCINT",1,"Rel-16","S5","2018-06-06","2019-03-14",1,"SP-181075",null,"Li Gang, Ericsson","gang.g.li@ericsson.com","10/9/18: 0%->5¦7/12/18: 5%->60¦14/12/18: WID:SP-180388->SP-181075¦14/3/19: 60%->100; 26/6/19: 28.890 added;","New; 28.890",80,41,null,null,"2018-06-06","2019-06-26"]
[2001,800039,"Study on management aspects of edge computing","FS_MAN_EC",1,"Rel-16","S5","2018-06-06","2019-03-14",1,"SP-180390",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com","6/8/18: 28.803 added;¦10/9/18: 0%->10¦7/12/18: 10%->20¦14/3/19: 20%->50; 31/5/19: 50%->65; 13/9/19: 65%->100","New; 28.803",80,41,null,null,"2018-06-06","2019-09-13"]
[2003,810029,"Study on management aspects of communication services","FS_CSMAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180923",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com.","7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[2006,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[2010,0,"--- RELEASE 15 ---","-",1,"Rel-15",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2012,740005,"5G System - Phase 1","5GS_Ph1",1,"Rel-15",null,"2016-06-09","2019-06-14",0.97,"SP-160958",null,"China Mobile, Tao Sun","suntao@chinamobile.com","15/12/17: 23.503 added;",null,74,38,null,null,"2016-12-01","2017-12-15"]
[2015,740061,"   Stage 2 of 5G System - Phase 1","5GS_Ph1",2,"Rel-15","S2","2016-12-01","2017-12-14",1,"SP-160958",null,"China Mobile, Tao Sun","suntao@chinamobile.com","3/3/17: 0%->30¦7/6/17: 30%->55¦11/9/17: 55%->75¦21/12/17: 75%->95¦11/6/18: 95%->100","23.401, 23.167, 23.271, 23.002; 23.228, 23.401, 23.167, 23.271, 23.502, 23.501; 23.503",74,38,null,null,"2016-12-01","2018-06-11"]
[2016,750016,"   Security aspects of 5G System - Phase 1","5GS_Ph1-SEC",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-180693",null,"NTT DOCOMO, Alf Zugenmaier ","alf.zugenmaier@hm.edu","7/6/17: 0%->10¦11/9/17: 10%->30¦15/12/17: 30%->65¦21/12/17: WID:SP-170234->SP-170881¦16/3/18: 65%->85¦16/3/18: FCD:03/18->06/18¦7/6/18: 85%->95¦10/9/18: WID:SP-170881->100¦10/9/18: 95%->100¦2/10/18: WID:SP-170881->SP-180693","33.501; 33.401; 33.210; 33.310; 33.220",75,38,null,null,"2017-03-02","2018-10-02"]
[2019,750026,"      Studies on CT1 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15",null,"2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","18/12/17: WID:CP-172034->CP-173161","23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-12-18"]
[2023,770045,"         Study on 5G Non-3GPP access networks","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 15%->55¦15/12/17: 55%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[2025,770047,"         Study on 5G System core network impact on services, network functions and capabilities","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 20%->65¦15/12/17: 65%->85¦16/3/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-03-16"]
[2028,780009,"         5G Network selection","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","16/3/18: 0%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2032,780013,"         5G Interworking with EPC","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2035,750027,"      Study on CT3 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C3","2017-03-03","2017-12-14",1,"CP-183243",null,"Fernandez, Susana (Ericsson)","Susana.Fernandez at ericsson.com","5/6/17: 0%->20¦15/12/17: 20%->95¦22/3/18: 95%->100","29.213; 29.214; 29.219; 29.122",75,38,null,null,"2017-03-03","2018-03-22"]
[2036,790044,"      CT3 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C3","2017-12-15","2018-06-14",1,"CP-183243",null,"Fernandez, Susana (Ericsson)","Susana.Fernandez at ericsson.com","5/6/17: 0%->20¦15/12/17: 20%->95¦7/6/18: 35%->70¦7/6/18: 70%->100","29.213; 29.214; 29.219; 29.122",75,38,null,null,"2017-03-03","2018-06-07"]
[2038,870080,"      (IETF) Improved Extensible Authentication Protocol Method for 3GPP Mobile Network Authentication and Key Agreement (EAP-AKA') (draft-ietf-emu-rfc5448bis)","5GS_Ph1-CT",3,"Rel-15","C4-IETF","2017-03-03","2017-12-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"20/6/22: Compl:80%->100%",null,87,44,null,null,"2017-03-03","2022-06-20"]
[2041,800081,"   UE Conformance Test Aspects – 5G System Non-3GPP Access","5GS_Ph1-CT_n3GPPA-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-181032",null,"Motorola",null,"tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2045,770019,"      CT4 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C4","2017-09-04","2018-06-15",1,"CP-180094",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","23.008; 29.228; 29.229; 29.328; 29.329; 23.003",77,39,null,null,"2017-03-03","2018-06-07"]
[2047,780035,"   Data Charging in 5G System Architecture Phase 1","5GS_Ph1-DCH",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170952",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","16/3/18: 0%->10¦7/6/18: 10%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100",32.24,78,40,null,null,"2017-12-15","2018-09-10"]
[2050,800041,"   UE Conformance Test Aspects - CT6 aspects of 5G System ","5GS_Ph1_UEConTest",2,"Rel-15","C6","2018-06-07","2019-06-14",1,"CP-183242",null,"Azem, Dania (COMPRION GmbH)","DAzem@comprion.com","10/12/18: 0%->5¦10/12/18: 5%->¦10/12/18: WID:CP-181187->CP-183242; 31/5/19: 5%->10; 6/12/19: 10%->60; 26/3/20: 60%->85; 26/6/20: 85%->95; 13/9/20: 95%->98; 13/12/21: 98%->100","31.121 ; 31.124",80,41,null,null,"2017-03-02","2021-12-13"]
[2054,760001,"   CT aspects of EDCE5","EDCE5-CT",2,"Rel-15","ct","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","18/12/17: WID:CP-171045->CP-173038",null,76,39,null,null,"2017-06-05","2017-12-18"]
[2057,760070,"      CT4 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C4","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","11/9/17: 0%->50¦15/12/17: 50%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",76,39,null,null,"2017-06-05","2017-12-15"]
[2058,760062,"   Charging aspects of EDCE5: PS Charging enhancements to support 5G New Radio via Dual Connectivity","EDCE5-CH",2,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170487",null,"Törnkvist, Robert, Ericsson","robert.tornkvist(at)ericsson.com","15/12/17: 0%->20¦16/3/18: 20%->100","32.251; 32.298; 32.299",76,39,null,null,"2017-06-05","2018-03-16"]
[2062,750072,"LTE connectivity to 5G-CN","LTE_5GCN_connect",1,"Rel-15","R2","2017-03-15","2018-12-20",1,"RP-171432",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-170840->RP-171432",null,75,38,null,null,"2017-03-21","2017-09-14"]
[2063,750172,"   Core part: LTE connectivity to 5G-CN","LTE_5GCN_connect-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",1,"RP-180860","RP-180862","Huawei",null,"no Perf. Part19/6/17: Compl:0%->5%19/6/17: WID: RP-170840->RP-17143219/9/17: Compl:5%->10%¦8/1/18: Compl:10%->20%¦27/3/18: Compl:20%->30%¦ ¦27/6/18: Compl:30%->99%¦7/3/19: 99%->100",null,75,38,null,null,"2017-03-21","2019-03-07"]
[2067,750003,"Enhancement of 3GPP support for V2X scenarios","eV2X",1,"Rel-15",null,"2016-06-09","2017-03-22",1,"SP-170158",null,"Chun, SungDuck, LG Electronics","sungduck.chun@lge.com ",null,null,75,38,null,null,"2017-03-02","NA"]
[2070,750075,"V2X new band combinations for LTE","LTE_V2X_CA_bands",1,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-170752",null,"LG Electronics",null,"no Perf. part¦12/7/17: 36.787 added;",36.786999999999999,75,38,null,null,"2017-03-21","2017-07-12"]
[2073,750162,"   Core part: V2X phase 2 based on LTE","LTE_eV2X-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-171740","RP-180858","Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦19/6/17: Compl:0%->15%¦ 30/6/17: 36.788 added;¦19/9/17: Compl:15%->30% 8/1/18: Compl:30%->55%27/3/18: Compl:55%->75%",36.787999999999997,75,38,null,null,"2017-03-21","2018-06-27"]
[2076,0,"Release 15 Features on Ultra/Highly Reliable Low Latency Communication","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2079,750161,"   Core part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-181259","RP-180693","Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: Compl:0%->10%¦8/1/18: WID: RP-171489->RP-172845¦27/3/18: Compl:10%->30%¦27/6/18: Compl:30%->99%¦27/6/18: CD:Fri 15",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2080,750261,"   Perf. part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Perf",2,"Rel-15","R4","2017-03-15","2018-12-15",0,"RP-181259",null,"Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: WID: RP-171489->RP-172845¦27/6/18: WID: RP-172845->RP-181259",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2084,720083,"Study on MC Security Enhancements","FS_MC_Sec",1,"Rel-15","S3","2016-06-17","2018-03-15",1,"SP-170416",null,"Haigh, Peter, CESG","peter.haigh@cesg.gsi.gov.uk ","28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17","33.xxx; 33.280; 39.880",72,37,null,null,"2016-06-17","2018-03-16"]
[2085,760050,"MC Communication Interworking between LTE and non-LTE Systems (Stage 3 in Rel16)","MCCI",1,"Rel-15","S6","2017-06-05","2017-12-14",1,"SP-170578",null,"Monnes, Peter, Harris Corporation","pmonnes at harris dot com ","11/9/17: 0%->40¦15/12/17: 40%->87¦16/3/18: 87%->100. 10/9/18: moved from Rel-15 since too late for St 3 in Rel-15 as said in CT81. 12/9/18: moved back to Rel-15, while St.3 will be Rel-16","New 23.283; 23.280; 23.379; 23.282",76,39,null,null,"2017-06-03","2018-03-16"]
[2089,770009,"   Stage 3 of enhMCPTT","enhMCPTT-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172030",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com","15/12/17: 0%->10¦7/6/18: 10%->20¦10/9/18: 20%->80¦7/12/18: 80%->85¦10/12/18: 85%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[2092,770011,"   Stage 3 of eMCData","eMCData-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172146",null,"HASON, Baruh","Baruh.Hason@motorolasolutions.com","20/3/18: 0%->30¦7/6/18: 30%->85¦10/12/18: 85%->100","24.282; 24.582; 24.481; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[2095,770013,"   Stage 3 of eMCVideo","eMCVideo-CT",2,"Rel-15","ct","2017-09-08","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","7/6/18: WID:CP-172032->CP-181084",null,77,39,null,null,"2017-06-03","2018-06-07"]
[2097,770015,"      CT3 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C3","2017-12-05","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","10/9/18: 0%->100","29.165; 29.213; 29.214",77,39,null,null,"2017-06-03","2018-09-10"]
[2101,800043,"   Stage 2 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","S6","2017-03-03","2017-12-15",1,"SP-170686",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100","23.280 + 23.281 + 23.282 + 23.379",75,38,null,null,"2017-03-03","2018-03-16"]
[2102,800017,"   Stage 3 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","C1","2018-04-09","2018-06-07",1,"CP-183105",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","12/6/18: 10%->30¦10/9/18: 30%->70¦7/12/18: 70%->100","24.281; 24.282; 24.379; 24.380; 24.581; 24.380",80,41,null,null,"2018-06-06","2018-12-10"]
[2105,890042,"UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo ","MCenhUEConTest",1,"Rel-15","R5","2020-09-17","2022-06-22",1,"RP-212956","RP-221332","KAHN, Jason, NIST (U.S. Department of Commerce)","jason.kahn@nist.gov","tested: REL-15 SA/CT WIs enhMCPTT, eMCVideo, eMCData, MBMS_Mcservices, MCSMI, MCProtoc15, MCOver ; 8/4/21: 0%->16; 2/7/21: 16%->33; 13/9/21: Compl:33%->40%; 13/9/21: CD:Fri 17/12/21->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211764; 6/1/22: WID:RP-201487-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2108,780016,"AT Commands for CIoT-Ext","AT_CIoT-Ext",1,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-173083",null,"Bakker, John-Luc (Blackberry)","jbakker@blackberry.com","20/3/18: 0%->20¦7/6/18: 20%->100",27.007000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[2111,750259,"   Perf. part: Even further enhanced MTC for LTE","LTE_eMTC4-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-172811",null,"Ericsson",null,"note: RAN #75 approved WID RP-170732 with working agreement19/6/17: WID: RP-170732->RP-171427¦8/1/18: WID: RP-171427->RP-172811¦27/6/18: Compl:0%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2114,750166,"   Core part: Further NB-IoT enhancements","NB_IOTenh2-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.95,"RP-182389","RP-180851","Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2118,750010,"Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery","ProSe_WLAN_DD",1,"Rel-15",null,"2016-11-15","2018-03-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[2121,760026,"   Stage 3 of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",2,"Rel-15","ct","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","18/12/17: WID:CP-171102->CP-173084",null,76,39,null,null,"2017-06-02","2017-12-18"]
[2123,760028,"      CT4 aspects of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",3,"Rel-15","C4","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","15/12/17: 0%->100","29.345; 29.230; 23.008",76,39,null,null,"2017-06-02","2017-12-15"]
[2124,780045,"   Charging of ProSe_WLAN_DD","ProSe_WLAN_DD-CH",2,"Rel-15","S5","2017-12-15","2018-03-15",1,"SP-170947",null,"Yizhi Yao, Intel Corporation ","yizhi.yao@intel.com","15/12/17: 0%->40¦16/3/18: 40%->100","32.277; 32.298; 32.299",74,38,null,null,"2016-12-01","2018-03-16"]
[2127,760021,"   Stage 2 of VoWLAN","VoWLAN",2,"Rel-15","S2","2017-05-09","2017-06-08",1,"SP-170378",null,"Drevon Nicolas, Nokia","nicolas.drevon@nokia.com ","15/12/17: 0%->100",23.402000000000001,76,39,null,null,"2017-06-02","2017-12-15"]
[2130,760024,"      CT4 aspects of VoWLAN","VoWLAN-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: 0%->100",29.274000000000001,76,39,null,null,"2017-06-02","2018-06-07"]
[2134,770030,"Study on 3GPP codecs for VR audio","FS_CODVRA",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170617",null,"Toftgård, Tomas, Ericsson","tomas.toftgard@ericsson.com ","15/12/17: 0%->100¦15/12/17: FCD:09/17->12/17",26.917999999999999,77,39,null,null,"2017-09-08","2017-12-15"]
[2136,770023,"Addition of HDR to TV Video Profiles","HDR",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170610",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->100","26.116; 26.346; 26.234; 26.247; 26.244",77,39,null,null,"2017-09-08","2017-12-15"]
[2140,790017,"Diameter Overload Control Mechanisms for Charging","DOCME_CH",1,"Rel-15","S5","2018-03-15","2018-09-14",1,"SP-180077",null,"Törnkvist, Robert, Ericsson","robert(dot)tornkvist(at)Ericsson(dot)com ","7/6/18: 0%->10¦7/6/18: FCD:06/18->09/18¦10/9/18: 10%->100",32.298999999999999,79,40,null,null,"2018-03-15","2018-09-10"]
[2143,790021,"Media Handling Aspects of 5G Conversational Services","5G_MTSI_Codecs",1,"Rel-15","S4","2018-03-15","2018-09-14",1,"SP-180650",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/6/18: 0%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-180033->SP-180650","26.114; 26.223",79,40,null,null,"2018-03-15","2018-10-02"]
[2145,790026,"   CT1 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C1","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","16/3/18: 0%->80¦7/6/18: 80%->100","24.237; 24.008",79,40,null,null,"2018-03-16","2018-06-07"]
[2146,790027,"   CT3 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","22/3/18: 0%->95¦10/9/18: 95%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[2149,790036,"   Stage 3 of INOBEAR","INOBEAR-CT",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com",null,null,79,40,null,null,"2017-12-15","NA"]
[2153,780170,"   Core part: Increased number of E-UTRAN data bearers","INOBEARRAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-180569",null,"Samsung",null,"27/3/18: WID: RP-172835->RP-180569¦27/6/18: Compl:0%->99%¦27/6/18:",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2156,750017,"   Study on security aspects of enhancements to ProSe UE-to-Network Relay","FS_REAR_Sec",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-170270",null,null,"lihe2@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->50¦15/12/17: 50%->79¦16/3/18: 79%->99¦16/3/18: FCD:03/18->06/18¦7/6/18: 99%->100",null,75,38,null,null,"2017-03-02","2018-06-07"]
[2158,780046,"Enhanced VoLTE performance","eVoLP",1,"Rel-15",null,"2016-12-01","2018-06-15",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,78,40,null,null,"2017-12-15","NA"]
[2162,780043,"      CT4 aspects of EvoLP","eVoLP-CT",3,"Rel-15","C4","2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com","7/6/18: 0%->100",29.274000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[2165,770052,"      S4 aspects of FS_eVoLP","FS_eVoLP",3,"Rel-15","S4","2017-09-14","2018-06-15",1,"SP-170615",null,"Venkatraman, Atti, Qualcomm Incorporated","vatti@qti.qualcomm.com ","15/12/17: 26.959 added;¦15/12/17: 0%->50¦16/3/18: 50%->75¦16/3/18: FCD:03/18->06/18¦7/6/18: 75%->100",26.959,77,39,null,null,"2017-09-14","2018-06-07"]
[2168,770006,"   Stage 1 of USOS","USOS",2,"Rel-15","S1","2016-02-01","2016-03-01",1,"SP-160117","SP-170526","Edward Hall, Qualcomm Incorporated","edhall@qti.qualcomm.com",null,"22.101, 22.115",71,36,null,null,"2016-03-01","2016-03-01"]
[2169,770036,"   Stage 2 of USOS","USOS",2,"Rel-15","S2","2017-09-08","2017-12-15",1,"SP-170740",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","15/12/17: 0%->100","23.401; 23.203",77,39,null,null,"2017-09-08","2017-12-15"]
[2171,750007,"Mobile Communication System for Railways","MONASTERY",1,"Rel-15",null,"2016-06-09","2018-06-15",1,"SP-170163",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com",null,null,75,38,null,null,"2017-03-02","NA"]
[2175,770040,"   Stage 2 of MONASTERY","MONASTERY",2,"Rel-15","S6","2017-09-08","2017-12-15",1,"SP-170756",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com ","14/9/17: SA6 and not SA2¦15/12/17: 0%->100","23.280; 23.379",77,39,null,null,"2017-09-08","2017-12-15"]
[2178,790033,"      CT3 aspects of MONASTERY","MONASTERY",3,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","10/9/18: 0%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[2181,760030,"PS Data Off Phase 2 ","PS_DATA_OFF2",1,"Rel-15",null,"2017-03-02","2018-06-14",1,"SP-170246",null,"Murhammer, Leopold, Deutsche Telekom AG","leopold.murhammer@t-mobile.at",null,null,75,38,null,null,"2017-03-02","NA"]
[2184,760032,"      CT1 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C1","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","24.008; 24.301; 27.007; 24.229; 24.368; 24.167; 24.173; 24.275; 24.341; 24.390; 24.391",76,39,null,null,"2017-06-02","2018-06-07"]
[2187,760035,"Northbound APIs for SCEF – SCS/AS Interworking","NAPS",1,"Rel-15",null,"2017-03-02","2018-06-15",1,"SP-170240",null,"Vaidya, Maulik, Huawei","Maulik.vaidya@huawei.com ","6/3/17: 0%->10",null,75,38,null,null,"2017-03-02","2017-03-06"]
[2190,760036,"      CT3 aspects of NAPS","NAPS-CT",3,"Rel-15","C3","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90¦15/12/17: 90%->65. 18/12/17: WID corrected¦16/3/18: 65%->72¦7/6/18: 72%->85¦7/6/18: 85%->95¦10/9/18: 95%->100","29.336; 29.128; 29.230",76,39,null,null,"2017-06-02","2018-09-10"]
[2191,780007,"      CT4 aspects of NAPS","NAPS-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","7/6/18: 95%->100",null,78,40,null,null,"2017-06-02","2018-06-07"]
[2195,750031,"   Study on CAPIF","FS_CAPIF",2,"Rel-15","S6","2017-03-10","2017-09-14",1,"SP-170405",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","21/3/17: added impacted TR¦7/6/17: 0%->35¦8/6/17: WID:SP-170279->SP-170405¦11/9/17: 35%->70¦15/12/17: 70%->100","new 23.722",75,38,null,null,"2017-03-10","2017-12-15"]
[2197,790042,"   Stage 3 of CAPIF","CAPIF-CT",2,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-180151",null,"Nishant Gupta, Samsung","nishant.gup@samsung.com ","16/3/18: 0%->10¦27/3/18: 29.222 added¦19/4/18: CAPIF->CAPIF-CT¦7/6/18: 10%->35¦7/6/18: 35%->85¦10/9/18: 85%->100","29.122; 29.116; 29.222",79,40,null,null,"2018-03-16","2018-09-10"]
[2200,780056,"   General aspects of NETSLICE","NETSLICE",2,"Rel-15","S5","2016-06-13","2018-09-14",1,"SP-180816",null,"Jan Groenendijk, Ericsson","jan<dot>groenendijk<at>ericsson<dot>com","21/12/17: created from the Feature level, since SP-170960 contains its own specs and completions¦16/3/18: 46%->60¦7/6/18: 60%->85¦7/6/18: FCD:06/18->09/18¦8/8/18: WID:SP-170960->SP 180124¦10/9/18: 85%->100","32.101; 32.103; 28.530",76,39,null,null,"2017-06-05","2018-09-10"]
[2203,760065,"   Provisioning of network slicing for 5G networks and services","NETSLICE-PRO_NS",2,"Rel-15","S5","2017-06-05","2018-09-14",1,"SP-180818",null,"Zhang Kai, Huawei","kai.zhangkai@huawei.com","15/12/17: 0%->15¦21/12/17: WID:SP-170580->SP-170955¦16/3/18: 15%->40¦27/3/18: 28.532 added;¦7/6/18: 40%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100¦2/10/18: WID:SP-170955->SP-180818",28.530999999999999,76,39,null,null,"2017-06-05","2018-10-02"]
[{"$f":"A2206+1","v":2206},780039,"   Management and virtualization aspects of 5G networks","NETSLICE-MNFV5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170958",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com","16/3/18: 0%->25¦7/6/18: 25%->75¦7/6/18: FCD:06/18->09/18¦10/9/18: 75%->100","28.500; 28.510; 28.511; 28.512; 28.513; 28.515; 28.516; 28.517; 28.518; 28.520; 28.521; 28.522; 28.523; 28.525; 28.526; 28.527; 28.528",78,40,null,null,"2017-12-15","2018-09-10"]
[2209,810042,"      CT3 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C3","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.507; 29.512",81,41,null,null,"2018-09-06","2018-09-10"]
[2210,810043,"      CT4 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C4","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274",81,41,null,null,"2018-09-06","2018-09-10"]
[2213,780017,"   Study on Policy and Charging for Volume Based Charging","FS_PC_VBC",2,"Rel-15","C3","2016-12-01","2017-12-15",1,"CP-172135",null,"Huang, Zhenning, China Mobile","huangzhenning <at> chinamobile <dot> com","6/3/17: 0%->30¦21/3/17: 29.827 added;¦5/6/17: 30%->60¦8/9/17: WID:CP-160822->CP-172058¦11/9/17: FCD:06/17->12/17",29.827000000000002,74,38,null,null,"2016-12-01","2017-09-11"]
[2216,790040,"   CT1 aspects of PV_VBC","PC_VBC",2,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180051",null,"Huang Zhenning (China Mobile)","huangzhenning (at) chinamobile (dot) com","7/6/18: 0%->100","24.605; 24.147",79,40,null,null,"2018-03-16","2018-06-07"]
[2219,770034,"Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management","OAM_SON_AAS",1,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170658",null,"Nokia (Weixing Wang)","weixing.wang@nokia-sbell.com","15/12/17: 0%->80¦10/9/18: 80%->100","28.627; 28.628; 28.629; 28.658; 28.659",77,39,null,null,"2017-09-08","2018-09-10"]
[2222,780036,"Management Enhancement for EPC CUPS ","ME_CUPS",1,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170954",null,"Huawei (ZHU, Lei","lei.zhu@huawei.com","ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14¦16/3/18: 0%->5¦7/6/18: 5%->60¦10/9/18: 60%->100","32.426; 32.455; 28.658; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-09-10"]
[2225,730006,"   Stage 1 of eCNAM","eCNAM",2,"Rel-15","S1","2016-09-15","2016-12-15",1,"SP-160548",null,"Hala Mowafy, Ericsson",null,"1/12/16: 0%->100¦30/6/17: 24.196 added;","22.173; 24.196",73,37,null,null,"2016-09-19","2017-06-30"]
[2229,750001,"Enhancement of background data transfer","eBT",1,"Rel-15","S1","2017-01-16","2017-03-08",1,"SP-170161",null,"Atsushi Minokuchi, NTT DOCOMO","minokuchi at nttdocomo dot com",null,22.100999999999999,75,38,null,null,"2017-03-02","NA"]
[2230,760016,"Stage-3 SAE Protocol Development - Phase 6","SAES6",1,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","NA"]
[2232,760018,"   SAES6 for support for non-3GPP accesses","SAES6-non3GPP",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","2018-06-07"]
[2235,720075,"Security Assurance Specification for PGW network product class","SCAS_PGW",1,"Rel-15","S3","2016-06-17","2017-12-12",1,"SP-160481",null,"Peng Jin, China Mobile","pengjin@chinamobile.com","28/7/16: 33.250 added¦19/9/16: 0%->10¦6/10/16: 33.216 added¦1/12/16: 10%->40. 06/03/17: moved from Rel-14.¦6/3/17: 40%->80¦7/6/17: FCD:06/17->12/17¦7/6/17: 80%->95¦11/9/17: 95%->100","33.250; 33.216",72,37,null,null,"2016-06-17","2017-09-11"]
[2238,760009,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C1","2017-06-02","2018-06-13",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com","14/9/17: 0%->40¦15/12/17: 40%->60¦16/3/18: 60%->80¦7/6/18: 80%->100","23.218; 24.229; 24.930",76,39,null,null,"2014-12-04","2018-06-07"]
[2242,870065,"      (IETF) Update to Private Header Field P-Visited-Network-ID in Session Initiation Protocol (SIP) Requests and Responses (draft-jesske-update-p-visited-network)","IMSProtoc8",3,"Rel-15","C1-IETF","2020-01-08","2020-04-23",0.25,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,87,44,null,null,"2020-04-23","NA"]
[2245,750015,"   Stopped - Study on R15 Lawful Interception Service","FS_15LIS",2,"Rel-15","S3LI","2017-03-02","2018-09-14",1,"SP-170040",null,"Gerry McQuaid, Vodafone","Gerald.McQuaid@vodafone.com","12/7/17: 0%->5¦11/9/17: 5%->10¦16/3/18: 24%->35¦7/6/18: 35%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->85. 17/01/19: deleted as per Alex's e-mail 13 Nov. Was at 85%",null,75,38,82,null,"2016-07-27","2018-09-10"]
[2247,750068,"DL interference mitigation for UMTS","UTRA_DL_IM",1,"Rel-15","R2","2017-03-15","2017-06-15",1,"RP-170703",null,"Qualcomm",null,"no Perf. part",null,75,38,null,null,"2017-03-21","2017-03-21"]
[2251,750077,"   Study on a simplified HS-SCCH for UMTS","FS_UTRA_simple_HSSCCH",2,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171477",null,"gerardo.agni.medina.acosta@ericsson.com ","gerardo.agni.medina.acosta@ericsson.com ","19/6/17: Compl:0%->100%¦30/6/17: 25.709 added;",25.709,75,38,null,null,"2017-03-21","2017-06-30"]
[2254,780020,"Receive acoustic output test in the presence of background noise","RAOT",1,"Rel-15","S4","2017-12-15","2018-06-15",1,"SP-170835",null,"ISBERG, Peter, Sony Mobile Communications","peter.isberg [at] sony.com","16/3/18: 0%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->100","26.131; 26.132",78,40,null,null,"2017-12-15","2018-06-07"]
[2256,780032,"REST Solution Sets","REST_SS",1,"Rel-15",null,"2016-09-19","2019-09-16",0.27,"SP-170950",null,null,null,null,null,78,41,null,null,"2017-12-15","NA"]
[2257,730057,"   Study on a RESTful HTTP-based Solution Set","FS_OAM_RESTFUL",2,"Rel-15","S5","2016-09-19","2017-12-12",1,"SP-160613",null,"Nokia: Pollakowski, Olaf","olaf.pollakowski@nokia.com","6/10/16: 32.866 added¦1/12/16: 0%->5¦7/6/17: 5%->45¦7/6/17: FCD:06/17->12/17¦11/9/17: 45%->80¦15/12/17: 80%->100",32.866,73,37,null,null,"2016-09-19","2017-12-15"]
[2260,800115,"   (IETF) JSON Schema Validation: A Vocabulary for Structural Validation of JSON (draft-handrews-json-schema-validation)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",0,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com",null,null,80,41,null,null,"2018-07-10","NA"]
[2264,800101,"   (IETF) PASSporT SHAKEN Extension (draft-ietf-stir-passport-shaken)--> RFC 8588","eSPECTRE",2,"Rel-15","C1-IETF","2018-06-14","2018-09-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Axell, Jörgen, Ericsson",null,"23/4/20: 25%->100",null,null,null,null,null,"2018-06-27","2020-04-23"]
[2267,750033,"(Small) Technical Enhancements and Improvements for Rel-15","TEI15",1,"Rel-15",null,"2017-03-17","2018-06-15",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[{"$f":"A2270+1","v":2270},0,"Release 15 Features on LTE improvements","-",1,"Rel-15",null,"2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2273,800080,"   UE Conformance Test Aspects - UL Data Compression in LTE","LTE_UDC-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-190311",null,"CATT",null,"tested: REL-15 WI LTE_UDC-Core¦26/3/19: WID:RP-180918->RP-190311¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2276,770268,"   Perf. part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Perf",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"¦27/3/18: Compl:0%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[2277,770069,"Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1",1,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-172077",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[2280,780066,"   UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-UEConTest",2,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-172713",null,"Ericsson",null,"tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2282,770071,"Extended-Band12 new E-UTRA Band","Ext_B12_LTE",1,"Rel-15","R4","2017-09-15","2019-06-01",1,"RP-172111",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[2286,710073,"Stopped - Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON",1,"Rel-15",null,"2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459",null,71,36,null,null,"2016-03-22","2017-09-14"]
[2289,740045,"   Stopped - Stage 3 of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",2,"Rel-15","ct","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[2291,740047,"      Stopped - CT4 aspects of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",3,"Rel-15","C4","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"29.274, 29.272",74,38,null,null,"2016-12-01","NA"]
[2295,710274,"   Perf. part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA-Perf",2,"Rel-15","R4","2016-03-15","2018-09-14",0.5,"RP-181297",null,"Huawei",null,"1/7/16: WID: RP-160548->RP-1609401/7/16: Release: Rel-15->Rel-14¦26/9/16: WID: RP-160940->RP-161668 20/12/16: Stat Rep: -->¦21/3/17: Compl:0%->10%;",null,71,36,null,null,"2016-03-22","2018-06-27"]
[2298,720291,"   Perf. part: Shortened TTI and processing time for LTE","LTE_sTTIandPT-Perf",2,"Rel-15","R4","2016-09-14","2018-09-14",1,"RP-171468",null,"Ericsson",null,"¦26/9/16: WID: RP-161299->RP-161922¦20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113¦19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%¦27/6/18: Compl:33%->60%¦26/3/19: 60%->100",null,72,37,null,null,"2016-07-01","2019-03-26"]
[2299,820064,"   UE Conformance Test Aspects - Shortened TTI and processing time for LTE","LTE_sTTIandPT-UEConTest",2,"Rel-15","R5","2018-12-15","2020-12-12",1,"RP-191003",null,"Huawei",null,"tested: REL-15 WI LTE_sTTIandPT-Core; 26/6/19: WID:RP-182429->RP-191003; 8/10/20: 0%->90; 8/10/20: 0%->90; 8/10/20: FCD:20/06/2019->12/20; 7/4/21: 0%->100; 8/4/21: 100%->100",null,null,null,null,null,"2019-01-16","2021-04-08"]
[2302,740272,"   Perf. part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR-Perf",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-162514",null,"Airbus",null,"19/6/17: Compl:0%->50%19/9/17: Compl:50%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2306,740274,"   Perf. part: E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-Perf",2,"Rel-15","R4","2016-12-15","2017-03-15",0,"RP-170212",null,"Airbus",null,"21/3/17: CD:Thu 15/06/17->Wed 15/03/17 ",null,74,38,null,null,"2016-12-20","2017-03-21"]
[2308,740075,"FDD operating band in the L-band for LTE","LTE_FDD_L_Band",1,"Rel-15",null,"2016-12-15","2018-09-14",1,"RP-162536",null,"NTT DOCOMO",null,"21/3/17: 36.751 added;",36.750999999999998,74,38,null,null,"2016-12-20","2017-03-21"]
[2311,780062,"   UE Conformance Test Aspects - FDD operating band in the L-band for LTE","LTE_FDD_L_band-UEConTest",2,"Rel-15","R5","2017-12-15","2018-09-14",1,"RP-180145",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ;; 11/10/20: 60%->100",null,78,40,null,null,"2018-01-08","2020-10-11"]
[2315,740077,"Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2",1,"Rel-15",null,"2016-12-15","2018-12-14",1,"RP-162571",null,"Sprint",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[2317,780065,"   UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-UEConTest",2,"Rel-15","R5","2017-12-15","2018-12-14",1,"RP-172698",null,"Sprint",null,"tested: REL-15 WI LTE_CA_C_B41_PC2-Core¦27/3/18: Co ;; 28/7/20: 5%->100",null,78,40,null,null,"2018-01-08","2020-07-28"]
[2320,740080,"TDD operating band in the L-band for LTE","LTE_TDD_L_Band",1,"Rel-15",null,"2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: 36.753 added;¦14/9/17: WID:RP-162557->RP-170304",36.753,74,38,null,null,"2016-12-20","2017-09-14"]
[2321,740180,"   Core part: TDD operating band in the L-band for LTE","LTE_TDD_L_Band-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: Compl:0%->15%¦19/6/17: Compl:15%->70%¦ 19/9/17: Compl:70%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2324,750160,"   Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-180584","RP-180318","Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦19/6/17: Compl:0%->70%¦19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%¦27/3/18: Compl:90%->99%¦27/3/18: CD:Thu 15/03/18->Fri ¦27/6/18: CD:Fri",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2328,750263,"   Perf. part: UE Positioning Accuracy Enhancements for LTE","LCS_LTE_acc_enh-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-181298",null,"Nokia",null,"¦19/6/17: WID: RP-170813->RP-171508¦8/1/18: Compl:0%->30%¦8/1/18: WID: RP-171508->RP-172313¦27/6/18: Compl:30%->100%¦27/6/18: WID: RP-17231",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2330,750164,"   Core part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-171740","RP-180854","Huawei",null,"¦19/6/17: Compl:0%->20%¦19/6/17: CD:Sat 15/12/18->Thu 15/03/18 19/6/17: FCD:03/18->06/18¦12/7/17: 36.783 added;19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->85%27/3/18: Compl:85%->99%",36.783000000000001,75,38,null,null,"2017-03-21","2018-06-27"]
[2333,750165,"   Core part: Enhancements to LTE operation in unlicensed spectrum","LTE_unlic-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-180402","RP-180948","Nokia",null,"note: The is actually a further LAA enhancement¦19/6/17: Compl:0%->15%¦19/6/17: CD:Fri 15 19/9/17: Compl:15%->30%¦8/1/18: Compl:30%->65%¦ 27/3/18: Compl:65%->85% 27/3/18: 37.107 added;;","37.107; 37.106",75,38,null,null,"2017-03-21","2018-06-27"]
[2337,750070,"Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming",1,"Rel-15","R2","2017-03-15","2018-12-14",0.99,"RP-170786",null,"China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core",null,75,38,null,null,"2017-03-21","2017-03-21"]
[2340,750071,"Enhancing LTE CA Utilization","LTE_euCA",1,"Rel-15","R2","2017-03-15","2021-09-08",0.97,"RP-170805",null,"Nokia",null,null,null,75,38,null,null,"2017-03-21","2017-03-21"]
[2341,750171,"   Core part: Enhancing LTE CA Utilization","LTE_euCA-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.9,"RP-180561","RP-181069","Nokia",null,"19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2343,820066,"   UE Conformance Test Aspects - Enhancing LTE CA Utilization","LTE_euCA-UEConTest",2,"Rel-15","R5","2018-12-15","2021-09-08",1,"RP-182619",null,"Nokia",null,"tested: REL-15 WI LTE_euCA-Core; 8/10/20: 0%->35; 8/10/20: FCD:15/12/2019->12/20; 8/4/21: 0%->56; 8/4/21: FCD:12/12/2020->09/20; 2/7/21: 0%->82; 29/9/21: 0%->100",null,null,null,null,null,"2019-01-16","2021-09-29"]
[2346,750273,"   Perf. part: 450 MHz Band for LTE in Region 3","LTE450_Reg3-Perf",2,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170952",null,"China Unicom",null,"¦19/6/17: WID: RP-170159->RP-170952¦8/1/18: Compl:0%->100%",null,75,38,null,null,"2017-03-21","2018-01-08"]
[2350,750274,"   Perf. part: US 600 MHz Band for LTE","LTE600_US-Perf",2,"Rel-15","R4","2017-03-15","2017-09-15",1,"RP-171142",null,"Ericsson",null,"¦19/6/17: Compl:0%->95%¦19 19/9/17: Compl:95%->100%",null,75,38,null,null,"2017-03-21","2017-09-19"]
[2352,750076,"LAA/eLAA for the CBRS 3.5GHz band in the United States","LTE_3550_CBRS_US_LAA",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170804",null,"AT&T",null,"compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2 Acronym changed, was \"LTE_TDD_3550_CBRS_US_LAA\"",null,75,38,null,null,"2017-03-21","2017-06-19"]
[2355,760097,"Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171131",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2359,760198,"   Core part: Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40-Core",2,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,"19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[2362,850061,"   UE Conformance Test Aspects – LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-UEConTest",2,"Rel-15","R5","2019-09-19","2021-06-11",1,"RP-192116",null,"Huawei",null,"8/10/20: 0%->50; 8/10/20: FCD:15/09/2020->12/20; 8/4/21: 50%->98; 8/4/21: FCD:11/12/2020->06/21; 2/7/21: 98%->100",null,85,43,null,null,"2019-10-08","2021-07-02"]
[2363,761000,"New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa",1,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-171506",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2367,761101,"   Core part: UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM-Core",2,"Rel-15","R4","2017-06-15","2018-09-14",0.85,"RP-181315",null,"Ericsson",null,"¦19/9/17: Compl:0%->15%¦8/1/18: Compl:15%->50%27/3/18: Compl:50%->70%¦27/6/18: Compl:70%->85%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2368,761201,"   Perf. part: UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-12-15",1,"RP-181315",null,"Ericsson",null,"¦27/6/18: WID: RP-171408->RP-181315¦16/1/19: 0%->100",null,76,39,null,null,"2017-06-16","2019-01-16"]
[2372,780069,"Enhanced LTE Support for Aerial Vehicles","LTE_Aerial",1,"Rel-15","R2","2017-03-15","2019-06-19",0.99,"RP-172826",null,"Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2375,820062,"   UE Conformance Test Aspects - Enhanced LTE Support for Aerial Vehicles","LTE_Aerial-UEConTest",2,"Rel-15","R5","2018-12-15","2019-06-19",1,"RP-192747",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_Aerial-Core; 8/10/19: WID:RP-182324->RP-191747; 14/1/20: WID:RP-191747->RP-192747; 14/1/20: 0%->100",null,null,null,null,null,"2019-01-16","2020-01-14"]
[2378,780072,"UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172842",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2381,780073,"ProSe Support for Band 72 in LTE","LTE450_B72_Europe_ProSe",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-182441",null,"Airbus",null,"This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78¦compare REL-15 WI LTE450_Europe_PPDR-Core¦16/1/19: WID:RP-172568->RP-182441",null,78,40,null,null,"2018-01-08","2019-01-16"]
[2384,780074,"LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172839",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2385,780174,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL-Core",2,"Rel-15","R4","2017-12-15","2018-06-15",1,"RP-181442",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01¦27/3/18: Compl:0%->10%¦27/3/18: 36.715-00-01 added;¦27/6/18: Compl:10%->100%;","36.715-00-01",78,40,null,null,"2018-01-08","2018-06-27"]
[2389,761003,"LTE CRS-Interference Mitigation performance requirements for single RX chain UEs","LTE_1RX_CRS_IM",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171465",null,"Intel",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2390,761203,"   Perf. part: LTE CRS-Interference Mitigation performance requirements for single RX chain UEs","LTE_1RX_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-N1122",null,"Intel",null,"¦19/9/17: Compl:0%->20%¦19/9/17: WID: RP-171465->RP-171831¦8/1/18: Compl:20%->60%¦27/3/18: Compl:60%->85%¦27/6/18: Compl:85%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2394,760091,"LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171026",null,"Qualcomm",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2397,760092,"LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171126",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2401,760193,"   Core part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"12/7/17: 36.715-04-01 added;¦19/9/17: Compl:0%->54% 8/1/18: Compl:54%->65%;27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;","36.715-04-01",76,39,null,null,"2017-06-16","2018-06-27"]
[2402,760293,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"19/9/17: Compl:0%->54%¦ 8/1/18: Compl:54%->65%¦27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2406,760095,"LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171127",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2407,760195,"   Core part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180957",null,"Huawei",null,"12/7/17: 36.715-02-02 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60%","36.715-02-02",76,39,null,null,"2017-06-16","2018-06-27"]
[2410,760196,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"12/7/17: 36.715-00-02 added;¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->80%¦ ¦27/6/18: ","36.715-00-02",76,39,null,null,"2017-06-16","2018-06-27"]
[2413,580037,"Stopped - LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements","LTE_UTRA_TRP_TRS",1,"Rel-15",null,"2012-12-15","2017-12-15",0.82,"RP-130703","-","Nokia","petri.j.vasenkari@nokia.com","Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022","UTRA, LTE",58,30,null,null,"2012-12-10","2014-09-15"]
[2416,790053,"Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh",1,"Rel-15","R6","2018-03-15","2018-09-15",0.9,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh",null,79,40,null,null,"2018-03-27","NA"]
[2419,790056,"LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5","LTE_CA_R15_xDL3UL",1,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-180573",null,"KDDI",null,"basket CA WI¦no Perf. part",null,79,40,null,null,"2018-03-27","NA"]
[2423,790155,"   Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-180688",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16",null,79,40,null,null,"2018-03-27","2018-06-27"]
[2426,0,"Release 15 Studies on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2428,750043,"Study on CU-DU lower layer split for New Radio","FS_NR_CU_DU_LLS",1,"Rel-15","R3","2017-03-15","2018-06-15",1,"RP-180684",null,"NTT DOCOMO",null,"CU = central unit, DU = distributed unit¦results will be captured in existing TR 38.801¦19/9/17: Compl:0%->30%¦19/9/17: WID: RP-170818->RP-171717¦15/12/17: 38.816 added;¦8/1/18: Compl:30%->95%¦8/1/18: CD:Fr ¦27/6/18",38.816000000000003,75,38,null,null,"2017-03-21","2018-06-27"]
[2429,750040,"Study on NR to support non-terrestrial networks","FS_NR_nonterr_nw",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171450",null,"Thales",null,"TR 38.8XX19/6/17: Compl:0%->25%19/6/17: CD:Fri 15/12/17->Thu 15/03/1819/6/17: WID: RP-170717->RP-171450¦30/6/17: 38.811 added;¦19/9/17: Compl:25%->40%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/18¦27/3/18: Compl:40%->45%¦27/6/18: Compl:4",38.811,75,38,null,null,"2017-03-21","2018-06-27"]
[2432,0,"Release 15 Studies on 4G/LTE","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2435,740066,"Study on uplink data compression in LTE","FS_LTE_UDC",1,"Rel-15","R2","2016-12-15","2017-09-15",1,"RP-170403",null,"CATT",null,"¦21/3/17: WID: RP-162541->RP-170403¦21/3/17: 36.754 added;19/6/17: Compl:0%->90%¦19/9/17: Compl:90%->100",36.753999999999998,74,38,null,null,"2016-12-20","2017-09-19"]
[2439,710063,"Study on further enhancements to LTE Device to Device (D2D), UE to network relays for IoT (Internet of Things) and wearables","FS_feD2D_IoT_relay_wearable",1,"Rel-15","R2","2016-03-15","2017-12-15",1,"RP-170295",null,"Qualcomm",null,"1/7/16: Compl:0%->2%;26/9/16: Compl:2%->5%¦6/10/16: 36.746 added¦20/12/16: Compl:5%->15%;21/3/17: Compl:15%->35%…19/6/17: ;",36.746000000000002,71,36,null,null,"2016-03-22","2018-01-08"]
[2441,750049,"Study on evaluation methodology of new V2X use cases for LTE and NR","FS_LTE_NR_V2X_eval",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171093",null,"LG Electronics",null,"TR 38.8XX19/6/17: WID: RP-170837->RP-171093¦12/7/17: 37.885 added;19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->10%¦8/1/18: CD:Fri 15/12/17->Thu 15/03/18¦27/3/18: Compl:10%->30%¦27/3/18: CD:Thu 15/03/18->Fri 15/06/18¦27/",37.884999999999998,75,38,null,null,"2017-03-21","2018-06-27"]
[2445,720041,"Study on Technical Requirements for a new secure platform for 3GPP applications","FS_NG_SP",1,"Rel-15","C6","2016-06-13","2017-09-12",1,"CP-160371",null,"Heiko Kruse","heiko.kruse@safrangroup.com","16/9/16: 0%->15. ¦5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet)¦5/6/17: FCD:12/16->09/20¦15/12/17: 70%->100",31.800999999999998,72,37,null,null,"2016-06-13","2017-12-15"]
[2448,750050,"Study on Architecture Evolution for E-UTRAN","FS_LTE_arch_evo",1,"Rel-15","R3","2017-03-15","2018-03-15",1,"RP-172707",null,"China Unicom",null,"TR 36.8XX¦12/7/17: 36.756 added;19/9/17: Compl:0%->40%¦15/12/17: 37.876 added;¦8/1/18: Compl:40%->827/3/18: Compl:85%->100%","36.756; 37.876",75,38,null,null,"2017-03-21","2018-03-27"]
[2450,720025,"Study on User Services Enhancements in 3GPP for TV Services","FS_USE_3GPP_4_TV",1,"Rel-15","S4","2016-06-13","2017-09-12",1,"SP-160273",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","19/9/16: 0%->30¦6/10/16: 26.917 added¦1/12/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: 60%->75¦6/3/17: FCD:03/17->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: 75%->80¦7/6/17: FCD:06/17->09/17¦11/9/17: 80%->100","26.9xx; 26.917",72,37,null,null,"2016-06-11","2017-09-11"]
[2451,700047,"Study on OAM support for assessment of energy efficiency in mobile access networks","FS_OAM_EE",1,"Rel-15","S5","2015-11-02","2017-06-09",1,"SP-160430",null,"Cornily,Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","13/6/16: WID:SP-150674->SP-160430¦13/6/16: 0%->55¦1/12/16: 55%->80¦6/3/17: FCD:03/17->06/17¦6/3/17: 80%->90¦21/3/17: moved from rel-14¦7/6/17: 90%->100",32.856000000000002,70,36,null,null,"2015-12-07","2017-06-07"]
[2454,760056,"Study on OAM aspects of LTE and WLAN integration ","FS_OAM_LWI",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170480",null,"Yizhi Yao, Intel Corporation","yizhi.yao@intel.com","30/6/17: 32.868 added;¦11/9/17: 0%->10¦15/12/17: 10%->50¦16/3/18: 50%->90¦7/6/18: 90%->100","new; 32.868",76,39,null,null,"2017-06-03","2018-06-07"]
[2458,720046,"Study on Management Aspects of Next Generation Network architecture and features","FS_MAN_NGNAF",1,"Rel-15","S5","2016-06-13","2017-12-12",1,"SP-160399",null,"Nokia Networks, Yizhi Yao","Yizhi.yao@nokia.com","28/7/16: 28.802 added¦19/9/16: 0%->5¦1/12/16: 5%->10¦6/3/17: FCD:03/17->06/17¦6/3/17: 10%->40¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 40%->60¦11/9/17: 60%->70¦15/12/17: 70%->100","(new); 28.802",72,37,null,null,"2016-06-13","2017-12-15"]
[2461,650036,"Stopped - Study on IMS Enhanced Spoofed Call Prevention and Detection","FS_ESCAPADES",1,"Rel-15","S3","2014-09-19","2017-12-15",1,"SP-140611","-","Sprint","Gregory.schumacher@sprint.com","Dec.14: TR number added. 3/3/15: 0->5%¦June2015: Compl:5%->25¦9/12/15: 25%->30¦21/3/17: moved from Rel-13¦21/3/17: FCD:09/15->12/17¦7/6/17: Stopped (30%->100%)",33.832000000000001,64,33,null,null,"2014-09-04","2017-06-07"]
[2463,710015,"STOPPED - Study on UE characteristics and performance for Video","FS_UE_VTPerf",1,"Rel-15","S4","2016-03-01","2017-06-15",1,"SP-160085",null,"Stéphane PROUST, Orange","stephane.proust@orange.com","11/6/16: 0%->10¦19/9/16: 10%->30, FCD: 12/16->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: Stopped, so 30%->100",26.931999999999999,71,36,null,null,"2016-03-01","2017-06-07"]
[2467,0,"Release 14 on Mission Critical","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2470,740022,"   Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",2,"Rel-14",null,"2016-06-13","2017-06-14",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379, 23.280, 23.281, 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[2473,740024,"         CT1 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C1","2016-12-01","2017-06-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","6/3/17: 0%->20¦5/6/17: 20%->95¦14/9/17: 95%->97¦15/12/17: 97%->100","24.379, 24.380, 24.381, 24.382, 24.383, 24.384",74,38,null,null,"2016-12-01","2017-12-15"]
[2474,740025,"         CT3 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[2476,740027,"         CT6 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C6","2016-12-01","2017-06-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100. No work identified for CT6.","31.102, 31.103",74,38,null,null,"2016-12-01","2017-06-05"]
[2480,670006,"      Study on Mission Critical Video over LTE","FS_MCVideo",3,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150048",null,"Villebrun, Emmanuelle (French MoI)","emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","1/4/15:TR number added¦June2015: Compl:0%->50¦07/09/15: 50%->70¦7/12/15: 70%->100","New 22.879",67,34,null,null,"2015-03-04","2015-12-07"]
[2483,750018,"      MCVideo codecs and media handling","MCImp-MCVideo",3,"Rel-14","S4","2017-01-11","2017-03-16",1,"SP-170244",null,"John Lambrou (Motorola Solutions)","john (dot) lambrou (at) motorolasolutions (dot) com","6/3/17: 0%->100",26.280999999999999,75,38,null,null,"2017-03-03","2017-03-06"]
[2486,740035,"         CT3 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C3","2016-12-01","2017-03-15",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[2489,720054,"   Mission Critical Data over LTE ","MCImp-MCData",2,"Rel-14",null,"2015-04-14","2017-06-14",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100",null,70,36,null,null,"2015-12-07","2016-07-28"]
[2492,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[2495,740030,"         CT3 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C3","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[2496,740031,"         CT4 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","6/3/17: 0%->100","23.003, 23.335, 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[2500,730008,"Protocol enhancements for MCPTT over LTE","MCPTTProtoc1",1,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","This Feature is a stage-3 only feature that fixes/enhances MCPTT protocol level (not visible from stage2). Not to be confused with Rel-14 MCPTT Stage 3.",null,73,37,null,null,"2016-09-16","2016-09-16"]
[2502,730010,"   CT3 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","2/12/16: 0%->20¦6/3/17: 20%->100","29.165, 29.212, 29.213, 29.214",73,37,null,null,"2016-09-16","2017-03-06"]
[2505,0,"Release 14 on V2X","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2508,720011,"   Architecture enhancements for LTE support of V2X services","V2XARC",2,"Rel-14","S2","2016-06-09","2016-12-15",1,"SP-160317",null,"LG Electronics, LaeYoung Kim","laeyoung.kim@lge.com","28/7/16: 23.285 added¦19/9/16: 0%->85¦1/12/16: FCD:09/16->12/16¦1/12/16: 85%->100",23.285,72,37,null,null,"2016-06-09","2016-12-01"]
[2512,720290,"      Perf. part: LTE-based V2X Services","LTE_V2X-Perf",3,"Rel-14","R4","2016-06-15","2017-09-15",1,"RP-162519",null,"LG Electronics",null,"¦26/9/16: WID: RP-161298->RP-161894¦20/12/16: WID: RP-161894->RP-162519¦20/12/16: Stat Rep: ->RP-162519¦19/6/17: Compl:0%->75%¦19/9/17: Compl:75%->100%",null,72,37,null,null,"2016-07-01","2017-09-19"]
[2513,760086,"      UE Conformance Test Aspects - Support for LTE-based V2X Services","LTE_V2X-UEConTest",3,"Rel-14","R5","2017-06-15","2018-12-14",1,"RP-192556",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->40%¦ 27/3/18: Compl:40%->55%; 14/1/20: WID:RP-172356->RP-192556; 14/1/20: 65%->100",null,76,39,null,null,"2017-06-16","2020-01-14"]
[2515,730027,"      CT1 aspects of V2X Services","V2X-CT",3,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 24.385 added¦6/10/16: 24.386 added¦2/12/16: 0%->65¦6/3/17: 65%->100","23.122, 24.301, 24.334; 24.385; 24.386",73,37,null,null,"2016-09-16","2017-03-06"]
[2518,730030,"      CT6 aspects of V2X Services","V2X-CT",3,"Rel-14","C6","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","7/3/17: 0%->100","31.102, 31.111",73,37,null,null,"2016-09-16","2017-03-07"]
[2521,700050,"      Study on Stage 2 of LTE support for V2X services","FS_V2XARC",3,"Rel-14","S2","2015-09-07","2016-06-17",1,"SP-150852",null,"LG Electronics, LaeYoung Kim","laeyoung.kim@lge.com","11/12/15: WID:SP-150625->SP-150743¦7/3/16: 10%->22¦7/3/16: WID:SP-150743->SP-150852¦9/6/16: 22%->80¦19/9/16: 80%->100",23.785,70,36,null,null,"2015-12-07","2016-09-19"]
[2524,700061,"Support for V2V services based on LTE sidelink","LTE_SL_V2V",1,"Rel-14",null,"2015-12-15","2018-09-14",1,"RP-152293",null,"LG Electronics",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[2527,730073,"   UE Conformance Test Aspects - Support for V2V services based on LTE sidelink","LTE_SL_V2V-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-172358",null,"Huawei",null,"¦20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ;; 11/10/20: 98%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[2530,710024,"   Non-IP for Cellular IoT for EC-EGPRS ","NonIP_GPRS",2,"Rel-14","S2","2016-03-02","2016-06-15",1,"SP-160196",null,"Hans Ronneke, Ericsson","hans . Ronneke (a) ericsson . Com","9/6/16: 0%->50¦19/9/16: 50%->100","23.060, 23.682, 23.401?",71,36,null,null,"2016-03-02","2016-09-19"]
[2534,710027,"      CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦2/12/16: 65%->100","29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007",71,36,null,null,"2016-03-02","2016-12-02"]
[2535,720092,"Further enhanced MTC for LTE","LTE_feMTC",1,"Rel-14",null,"2016-06-15","2018-09-14",1,"RP-161321",null,"Ericsson",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2537,720292,"   Perf. part: Further enhanced MTC for LTE","LTE_feMTC-Perf",2,"Rel-14","R4","2016-06-15","2017-12-15",1,"RP-170532",null,"Ericsson",null,"¦26/9/16: WID: RP-161321->RP-161464¦20/12/16: WID: RP-161464->RP-162520¦20/12/16: Stat Rep: ->RP-16252021/3/17: CD:Fri 15/09/17->Fri 15/12/1721/3/17 19/6/17: Compl:0%->35%19/9/17: Compl:35%->60%¦8/1/18: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2018-01-08"]
[2540,720193,"   Core part: Enhancements of NB-IoT","NB_IOTenh-Core",2,"Rel-14","R1","2016-06-15","2017-06-15",1,"RP-171060","RP-171061","Huawei",null,"26/9/16: Compl:0%->13%26/9/16: WID: RP-161324->RP-161901¦20/12/16: Compl:13%->70%¦21/3/17: Compl:70%->95%¦21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:95%->100%",null,72,37,null,null,"2016-07-01","2017-06-19"]
[2543,730021,"AT Commands for CIoT","AT_CIoT",1,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160477",null,"John-Luc Bakker",null,"2/12/16: 10%->95¦6/3/17: 95%->100",null,73,37,null,null,"2016-09-16","2017-03-06"]
[2547,740038,"   Stage 3 of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","21/3/17: 24.250 added;",24.25,74,38,null,null,"2016-12-01","2017-03-21"]
[2550,730077,"Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh",1,"Rel-14","R6","2016-09-15","2018-06-15",0.99,"RP-161806",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2553,730083,"New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands",1,"Rel-14","R4","2016-09-15","2017-09-15",0.99,"RP-161890",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2556,750057,"   UE Conformance Test Aspects - New band support for Rel-14 NB-IoT","NB_IOT_R14_bands-UEConTest",2,"Rel-14","R5","2017-03-15","2017-09-15",1,"RP-170495",null,"Ericsson",null,"tested: REL-14 NB_IOT_R14_bands-Core (which got an exception at RAN #75 to still complete in REL-14 by RAN #76);",null,75,38,null,null,"2017-03-21","2017-09-19"]
[2559,720007,"   Enhancements of Dedicated Core Networks selection mechanism","eDecor",2,"Rel-14","S2","2016-06-09","2016-09-15",1,"SP-160310",null,"Roland Gustafsson","Roland.Gustafsson@ericsson.com","19/9/16: 70%->100","23.401, 23.060, 23.251",72,37,null,null,"2015-09-17","2016-09-19"]
[2561,730014,"      CT1 aspects of eDecor","eDecor-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100","24.301, 24.008, 24.368",73,37,null,null,"2016-09-16","2017-06-05"]
[2562,730015,"      CT4 aspects of eDecor","eDecor-CT",3,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.303, 23.003, 23.008",73,37,null,null,"2016-09-16","2017-03-06"]
[2565,740167,"      Core part: RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE-Core",3,"Rel-14","R3","2016-12-15","2017-03-15",1,"RP-162543","RP-170547","Ericsson",null,"21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547",null,74,38,null,null,"2016-12-20","2017-03-21"]
[2569,740178,"   Core part: Addition of band 25 and 26 to LTE MTC cat.0","LC_MTC_LTE_cat0_B25_B26-Core",2,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162572",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[2572,720031,"EIR check for WLAN access to EPC","EWE",1,"Rel-14",null,"2015-11-02","2016-09-15",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002, 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[2574,720002,"   CT aspects of EWE","EWE-CT",2,"Rel-14","ct","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com",null,null,72,37,null,null,"2016-06-13","NA"]
[2578,730049,"   Support of EAP Re-authentication Protocol for WLAN Interworking","ERP",2,"Rel-14","S3","2016-09-16","2017-03-15",1,"SP-160568",null,"ORANGE, Todor Gamishev","Todor dot Gamishev at Orange dot com","1/12/16: 0%->90¦6/3/17: 90%->100",33.402000000000001,73,37,null,null,"2016-09-16","2017-03-06"]
[2581,730046,"      CT4 aspects of ERP","ERP-CT",3,"Rel-14","C4","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com","2/12/16: 0%->50¦6/3/17: 50%->95¦5/6/17: 95%->100","29.273, 23.008, 23.003",73,37,null,null,"2016-09-16","2017-06-05"]
[2582,720019,"Phase 2 of the Support of Emergency services over WLAN","SEW2",1,"Rel-14",null,"2015-09-01","2017-03-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com",null,"new 23.771, 23.402, 23.167",72,37,null,null,"2015-04-01","2016-06-09"]
[2585,730017,"   CT aspects of SEW2","SEW2-CT",2,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","5/12/16: WID:CP-160476->CP-160694",null,73,37,null,null,"2016-09-16","2016-12-05"]
[2587,730019,"      CT4 aspects of SEW2","SEW2-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 0%->100","23.003, 29.272, 29.273, 29.274, 29.328",73,37,null,null,"2016-09-16","2016-12-02"]
[2591,710175,"   Core part: Enhanced LTE-WLAN Aggregation (LWA)","LTE_WLAN_aggr-Core",2,"Rel-14","R2","2016-03-15","2017-03-15",1,"RP-160923","RP-170330","Intel",null,"follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923¦26/9/16: Compl:25%->45%¦20/12/16: Compl:45%->75%¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:75%->100% ¦21/3/17",null,71,36,null,null,"2016-03-22","2017-03-21"]
[2594,680004,"   Stage 1 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S1","2015-05-11","2015-06-19",1,"SP-150275",null,"Kurt Bischinger",null,null,22.100999999999999,68,35,null,null,"2015-06-09","2015-06-09"]
[2596,710020,"   CT aspects of evolution to and interworking with eCall in IMS","EIEI-CT",2,"Rel-14",null,"2016-03-02","2016-09-15",1,"CP-160053",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,null,71,36,null,null,"2016-03-02","2016-03-02"]
[2600,760084,"   UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI)","EIEI-UEConTest",2,"Rel-14","R5","2017-06-15","2018-03-15",1,"RP-171057",null,"Qualcomm",null,"¦19/9/17: Compl:0%->45%¦8/1/18: Compl:45%->80%¦27/3/18: Compl:80%->100%",null,76,39,null,null,"2017-06-16","2018-03-27"]
[2603,720034,"   CT aspects for PWDIMS","PWDIMS-CT",2,"Rel-14","ct","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,null,null,72,37,null,null,"2016-06-11","NA"]
[2604,720035,"      CT1 aspects for PWDIMS","PWDIMS-CT",3,"Rel-14","C1","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,"2/12/16: 0%->15¦6/3/17: 15%->100","24.623, 24.611",72,37,null,null,"2016-06-11","2017-03-06"]
[2607,630107,"   CT1 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C1","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728¦5/6/17: 0%->100","24.229, 24.323",63,32,null,null,"2014-01-29","2017-06-05"]
[2611,630207,"   CT3 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C3","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 0%->100",29.164999999999999,63,32,null,null,"2014-01-29","2017-06-05"]
[2613,0,"Other Release 14 ","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2616,740018,"   Stage 3 of User Controlled Spoofed Call Treatment","SPECTRE-CT",2,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160696",null,"Dolly, Martin","md3135@att.com","2/12/16: 0%->25¦6/3/17: 25%->100","24.229, 29.165",74,38,null,null,"2016-09-19","2017-03-06"]
[2620,670010,"   Study on 3GPP Enhancement for TV Video service","FS_EnTV",2,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150052",null,"Zhiming Li (Huawei)","lizhiming@huawei.com","1/4/15:TR number added¦June2015: Compl:0%->20¦07/09/15: 20%->75¦7/12/15: 75%->100",22.815999999999999,67,34,null,null,"2015-03-04","2015-12-07"]
[2622,710046,"      Study on System Architecture Enhancements to eMBMS for TV Video Service","FS_AE_enTV",3,"Rel-14","S2","2016-03-11","2016-09-15",1,"SP-160225",null,"Miguel Griot, Qualcomm","mgriot@qti.qualcomm.com","9/6/16: 0%->70¦28/7/16: 23.746 added¦19/9/16: 70%->100",23.745999999999999,71,36,null,null,"2016-03-11","2016-09-19"]
[2625,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347, 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[2626,740049,"   Stage 3 of system architecture enhancements for TV service ","AE_enTV-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","21/3/17: 29.116 added;","24.116, 24.117; 29.116",74,38,null,null,"2016-12-01","2017-03-21"]
[2629,740052,"      CT4 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","5/6/17: 0%->100","29.274, 23.003",74,38,null,null,"2016-12-01","2017-06-05"]
[2633,721004,"Lawful Interception Rel-14","LI14",1,"Rel-14","S3LI","2016-06-15","2017-12-15",1,"SP-170038",null,"Koen JASPERS, PIDS",null,"1/12/16: 0%->10¦2/3/17: WID:SP-160375->SP-1570038¦3/3/17: 8%->15¦6/3/17: 15%->20¦9/3/17: WID:SP-1570038->SP-170038¦7/6/17: 20%->50¦11/9/17: 50%->80¦15/12/17: 80%->100",null,72,37,null,null,"2016-07-27","2017-12-15"]
[2635,730032,"   CT1 aspects of SIP Reason header extension","REAS_EXT",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160481",null,"Mohali, Marianne","marianne.mohali@orange.com","2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100",24.228999999999999,73,37,null,null,"2016-09-16","2017-06-05"]
[2638,690034,"Enhancements to User Location Reporting Support","eULRS",1,"Rel-14","S1","2015-09-09","2015-12-18",1,"SP-150540",null,null,null,"2/3/16: 0%->100",null,68,35,null,null,"2015-09-09","2016-03-02"]
[2642,740058,"   (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583","DLoCMe",2,"Rel-14","C4-IETF","2016-12-02","2017-03-15",0.9,"CP-160645",null,null,null,"2/12/16: 0%->90",null,74,38,null,null,"2016-12-02","2016-12-02"]
[2645,740054,"   CT aspects of Diameter Base Protocol Specification Update","DBPU",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[2646,740055,"      CT3 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","6/3/17: 0%->100","29.061, 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.368, 29.468, 29.213, 29.155, 29.201",74,38,null,null,"2016-12-01","2017-03-06"]
[2648,740013,"   Charging aspects for Diameter Base Protocol Specification Update","DBPU-CH",2,"Rel-14","S5","2016-12-01","2017-03-10",1,"SP-160837",null,"Nokia","Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","6/3/17: 0%->100","32.240, 32.251, 32.260, 32.270, 32.271, 32.272, 32.273, 32.274, 32.275, 32.278, 32.280, 32.295, 32.296, 32.297, 32.299",74,38,null,null,"2016-12-01","2017-03-06"]
[2651,720064,"   CT aspects of MMCMH_Enh","MMCMH_Enh-CT",2,"Rel-14","ct","2016-03-02","2017-03-21",0.99,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","To be checked at SA4 if a part can stay in Rel-13 (now Stages 1 and 2 by SA4 in UID660050), while the CT aspects are in Rel-14. 06/16: Name changed from \"CT aspects of (or \"Enhancements of\") MTSI Extension on Multi-stream\". Acronym changed from \"MMCMH-",null,72,37,null,null,"2016-03-02","2016-06-13"]
[2655,750038,"      (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","MMCMH_Enh-CT",3,"Rel-14","C1-IETF","2017-03-21","2017-03-21",0.9,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ericsson","tomas.frankkila@ericsson.com","23/4/20: 50%->90; 9/4/21: RFC 8853 added;","RFC 8853",75,38,null,null,"2017-03-21","2021-04-09"]
[2657,710002,"Stopped - CT aspects of (or \"Enhancements of\") MTSI Extension on Multi-stream","MMCMH-CT",1,"Rel-14","ct","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT",null,71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[2660,710030,"   deleted -CT4 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","23.333, 29.333, 23.334, 29.334, 29.238",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[2664,730001,"   CT aspects for CUPS","CUPS-CT",2,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[2667,690048,"OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM14",1,"Rel-14","S5","2015-03-12","2017-12-12",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,68,35,null,null,"2015-09-16","2015-09-16"]
[2668,680035,"   Management of mobile networks that include virtualized network functions","OAM14-MAMO_VNF",2,"Rel-14","S5","2015-06-15","2017-12-12",1,"SP-150362",null,"Jinglei Liu, China Mobile","liujinglei@chinamobile.com","June2015: WID:SP-150308->SP-150362",null,68,35,null,null,"2015-06-15","2015-06-18"]
[2672,690041,"      Performance management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-PM",3,"Rel-14","S5","2015-09-16","2017-12-12",1,"SP-160402",null,"Intel (Joey Chou, joey.chou@intel.com)","joey.chou@intel.com","5/10/15: 28.523¦28.522¦28.521¦28.520 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->30¦13/6/16: WID:SP-150401->SP-160402¦19/9/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->75¦7/6/17: 75%->90¦7/6/17: FCD:0","28.523; 28.522; 28.521; 28.520; 32.426, 32.409, 32.401",69,35,null,null,"2015-06-15","2017-09-11"]
[2673,690042,"      Lifecycle management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-LCM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160427",null,"Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks","anatoly.andrianov@nokia.com","5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%-","28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709",69,35,null,null,"2015-06-15","2017-06-07"]
[2677,680050,"Development of super-wideband and fullband P.835","DESUDAPS",1,"Rel-14","S4","2015-06-16","2017-06-15",1,"SP-150215","SP-170346","Scott Isabelle (Knowles, Inc.)","sisabelle@audience.com","06/15: FCD corrected to Dec.15¦Aug2015: 0%->5¦07/09/15: 5%->20, FCD: 12/15->06.16¦7/12/15: 20%->40, MOVED TO REL-14¦7/3/16: 40%->50. 15/4/16: 6/16->12/16¦11/6/16: 50%->60¦19/9/16: 60%->70, fcd: 12/16->06/17¦1/12/16: 70%->75¦6/3/17: 75%->80¦7/6","26.131, 26.132",68,35,null,null,"2015-06-18","2017-06-07"]
[2680,680002,"Control of Applications when Third party Servers encounter difficulties","CATS",1,"Rel-14","S1","2015-05-11","2015-09-16",1,"SP-150273","SP-170338","Eriko Yoshida, KDDI","er-yoshida (at) kddi (dot) com","07/09/15: 0%->100",22.010999999999999,68,35,null,null,"2015-06-09","2015-09-07"]
[2683,720079,"   Study on Stage 2 of PS Data off function","FS_PS_DATA_OFF",2,"Rel-14","S2","2016-06-17","2016-12-15",1,"SP-160318",null,"Orange, david <dot> cailliere <at> orange <dot> com","david <dot> cailliere <at> orange <dot> com","28/7/16: 23.702 added¦19/9/16: 0%->60¦1/12/16: FCD:09/16->12/16¦1/12/16: 60%->100",23.702000000000002,72,37,null,null,"2016-06-17","2016-12-01"]
[2686,740042,"      CT1 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->95¦5/6/17: 95%->100","24.008, 24.301, 27.007, 24.229, 24.368, 24.167",74,38,null,null,"2016-12-01","2017-06-05"]
[2689,740014,"   Charging Aspect for 3GPP PS Data off Function ","PS_DATA_OFF-CH",2,"Rel-14","S5","2016-12-01","2017-06-09",1,"SP-160839",null,"Huawei， Chen, Shan","chenshan@huawei.com","6/3/17: 0%->70¦6/3/17: FCD:03/17->06/17¦7/6/17: 70%->100","32.251, 32.298, 32.299",74,38,null,null,"2016-12-01","2017-06-07"]
[2690,710003,"SCC AS Restoration","SCCAS_RES",1,"Rel-14","C4","2016-03-02","2016-12-15",1,"CP-160118",null,"China Mobile, Hao Zhang, ","zhanghao@chinamobile.com","13/6/16: 0%->100",23.38,71,36,null,null,"2016-03-02","2016-06-13"]
[2693,680003,"   Study on enhancement to FMSS for Rel 14","FS_eFMSS",2,"Rel-14","S1","2015-05-11","2015-12-16",1,"SP-150280",null,"Lu Lu, China Mobile","lulu@chinamobile.com","7/12/15: 70%->100",22.808,68,35,null,null,"2015-06-09","2015-12-07"]
[2696,710010,"Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",1,"Rel-14",null,"2016-03-01","2016-12-01",0.92,"SP-160081","SP-170515","Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10",26.222999999999999,71,36,null,null,"2016-03-01","2016-06-11"]
[2699,800103,"      (IETF) RTP Payload Format for Flexible Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->100",null,80,41,null,null,"2018-06-27","2020-04-23"]
[2702,800106,"      (IETF) Session Signaling for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-signaling)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8848 added;","RFC 8848",80,41,null,null,"2018-06-27","2021-04-09"]
[2706,800110,"      (IETF) Session Description Protocol (SDP) Offer/Answer Procedures For Stream Control Transmission Protocol (SCTP) over Datagram Transport Layer Security (DTLS) Transport. (draft-ietf-mmusic-sctp-sdp)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8841 added;","RFC 8841",80,41,null,null,"2018-06-27","2021-04-09"]
[2707,800111,"      (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8864 added;","RFC 8864",80,41,null,null,"2018-06-27","2021-04-09"]
[2711,680053,"   Study on S8 Home Routing Architecture","FS_V8",2,"Rel-14","S2","2015-06-18","2016-03-10",1,"SP-150255",null,"Motohiro ABE","motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com","07/09/15: 0%->10¦07/09/15: 10%->100¦7/12/15: 100%->10% (mistake?) then 10%->70, FCD: 12/15-?03/16¦7/3/16: 70%->80¦9/6/16: 80%->100","New 23.xxx",68,35,null,null,"2015-06-18","2016-06-09"]
[2712,690049,"   Study on LI in S8 Home Routing Architecture for VoLTE ","FS_LIV8",2,"Rel-14","S3","2015-09-17","2016-06-17",1,"SP-150461",null,"Greg Schumacher (SPRINT) Gregory ","Schumacher@sprint.com","7/12/15: 0%->45¦28/1/16: 33.827 added¦7/3/16: 45%->55¦19/9/16: 55%->65¦15/12/17: 65%->100",33.826999999999998,69,35,null,null,"2015-09-17","2017-12-15"]
[2715,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[{"$f":"A2718+1","v":2718},720020,"Improvements of awareness of user location change","AULC",1,"Rel-14",null,"2015-09-17","2017-06-09",1,"SP-160308","SP-170524","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-09-17","2016-06-09"]
[2721,730034,"   CT Aspect of AULC","AULC-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[2724,730054,"   Charging Aspects of Improvements of AULC","AULC-CH",2,"Rel-14","S5","2016-09-19","2017-06-09",1,"SP-160609",null,"Huawei， Chen, Shan","chenshan@huawei.com","1/12/16: 0%->40¦6/3/17: 40%->80¦6/3/17: FCD:03/17->06/17¦7/6/17: 80%->100","TS32.251, TS32.298, TS32.299",73,37,null,null,"2016-09-19","2017-06-07"]
[2728,720014,"Sponsored data connectivity improvements","SDCI",1,"Rel-14",null,"2015-11-02","2016-12-15",1,"SP-160309","SP-170523","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[2731,730037,"   CT Aspects of SDCI","SDCI-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.251 added;",29.251000000000001,73,37,null,null,"2016-09-16","2016-10-06"]
[2733,710017,"Stage-3 SAE Protocol Development - Phase 5","SAES5",1,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",71,36,null,null,"2016-03-02","2016-03-02"]
[2734,710018,"   SAES5 CS Fallback in EPS","SAES5-CSFB",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","11/6/16: 0%->5¦16/9/16: 5%->20¦2/12/16: 20%->70¦6/3/17: 70%->100","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",71,36,null,null,"2016-03-02","2017-03-06"]
[2737,720012,"Group based enhancements in the network capability exposure functions","GENCEF",1,"Rel-14","S2","2015-11-02","2016-12-16",1,"SP-160311","SP-170517","Samsung, Sung Hwan Won","sunghwan.won@samsung.com",null,null,70,36,null,null,"2015-12-07","2016-06-09"]
[2740,720084,"Robust Call Setup for VoLTE subscriber in LTE","RobVoLTE",1,"Rel-14",null,"2015-11-02","2018-09-14",0.99,"SP-160312",null,null,null,null,null,72,37,null,null,"2015-12-07","NA"]
[2744,730078,"   Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh",2,"Rel-14","R2","2016-09-15","2018-09-14",0.99,"RP-161856",null,"CMCC",null,null,null,73,37,null,null,"2016-12-14","2016-09-26"]
[2746,760089,"      UE Conformance Test Aspects –Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh-UEConTest",3,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-171385",null,"CATT",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->60%¦ 27/3/18: Compl:60 ;; 11/10/20: 95%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[2750,720038,"   CT1 aspects of IOC_UE_conf","IOC_UE_conf",2,"Rel-14","C1","2016-06-13","2017-03-15",1,"CP-160828",null,"Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦16/9/16: 10%->20¦17/10/16: WID:CP-160296->CP-160374¦2/12/16: 20%->75¦6/3/17: 75%->100","24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.275",72,37,null,null,"2016-06-11","2017-03-06"]
[2753,710012,"Rel-14 Charging","CH14",1,"Rel-14","S5","2016-03-01","2017-06-09",1,"SP-160021",null,null,null,"Umbrella Feature",null,71,36,null,null,"2016-03-01","2016-03-01"]
[2756,720049,"   Charging Aspects of Enhanced Proximity-based Services","CH14-ProSe",2,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160428","SP-170408","Chen, Shan","chenshan@huawei.com","19/9/16: 0%->40¦1/12/16: 40%->60¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100","32.240, 32.251, 32.277, 32.298, 32.299",72,37,null,null,"2016-06-13","2017-06-07"]
[2757,740019,"Determination of Completeness of Charging Information in IMS","CH14-DCCII",1,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160398",null,"Jesske, Roland (Deutsche Telekom)",null,"19/9/16: 0%->10","32.240, 32.260, 32.298, 32.299",72,37,null,null,"2016-06-13","2016-09-19"]
[2759,740059,"   CT Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160697","CP-171048","Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,74,38,null,null,"2016-12-01","2017-03-21"]
[2763,700160,"   Core part: Enhanced LAA for LTE","LTE_eLAA-Core",2,"Rel-14","R1","2015-12-15","2017-03-15",1,"RP-162235","RP-170269","Ericsson",null,"22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881¦26/9/16: Compl:60%->92%¦26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: WID: ¦20/12/16: Compl:92%->97%¦20/12/16:21/3/17: Compl:",null,70,36,null,null,"2016-01-01","2017-03-21"]
[2766,700062,"RRC optimization for UMTS","UTRA_RRCopt",1,"Rel-14","R2","2015-12-15","2016-09-15",1,"RP-152267",null,"Ericsson",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[2768,700063,"DTX/DRX enhancements in CELL_FACH","FACH_DTXDRX",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-152286",null,"Huawei",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[2772,700277,"   Perf. part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06",null,70,36,null,null,"2016-01-01","2016-07-01"]
[2775,700178,"   Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3","LTE_1980_2170_REG3-Core",2,"Rel-14","R4","2015-12-15","2015-12-15",0,"RP-152238",null,"KT Corp.",null,null,null,70,36,null,null,"2016-01-01","2015-12-22"]
[2778,760083,"   UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs-UEConTest",2,"Rel-14","R5","2017-06-15","2017-09-15",1,"RP-170931",null,"Dish Network",null,"¦19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[2779,700079,"LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3",1,"Rel-14","R4","2015-12-15","2017-12-15",0.99,"RP-152253",null,"Orange",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[2781,700279,"   Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"¦22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16",null,70,36,null,null,"2016-01-01","2016-07-01"]
[2785,700280,"   Perf. part: Multi-Band Base Station testing with three or more bands","MB_BS_test_3B-Perf",2,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-162442",null,"Alcatel-Lucent",null,"22/3/16: Compl:0%->5%22/3/16: WID: RP-152205->RP-160063¦1/7/16: Compl:5%->30%26/9/16: Compl:30%->60%26/¦20/12/16: Compl:60%->100%¦",null,70,36,null,null,"2016-01-01","2016-12-20"]
[2788,700282,"   Perf. part: Performance enhancements for high speed scenario in LTE","LTE_high_speed-Perf",2,"Rel-14","R4","2015-12-15","2017-06-15",1,"RP-171039",null,"NTT DOCOMO",null,"22/3/16: WID: RP-152263->RP-1601721/7/16: Compl:0%->20%¦26/9/16: Compl:20%->25%¦20/12/16: Compl:25%->35% ¦21/3/17: Compl:35%->70%¦19/6/17: Compl:70%->100%¦19/6/17: WID: RP-160172->RP-171039",null,70,36,null,null,"2016-01-01","2017-06-19"]
[2791,710172,"   Core part: Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2-Core",2,"Rel-14","R2","2016-03-15","2016-12-15",1,"RP-162026","RP-162506","Huawei",null,"follow-up WI of REL-13 WI UTRA_LTE_iPos_enh1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->60%¦26/9/16: WID:¦20/12/16: Compl:60%->100%¦",null,71,36,null,null,"2016-03-22","2016-12-20"]
[2794,710076,"Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE","LTE_MIMO_OTA",1,"Rel-14","R4","2016-03-15","2018-03-15",0.99,"RP-160603",null,"Intel",null,"follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[2797,710077,"Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO",1,"Rel-14","R1","2016-03-15","2022-06-22",0.99,"RP-160623",null,"Samsung",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[2798,710177,"   Core part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160623","RP-170173","Samsung",null,"¦1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->80%¦20/12/16: Stat Rep: -->¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170173",null,71,36,null,null,"2016-03-22","2017-03-21"]
[2801,710078,"Further mobility enhancements in LTE","LTE_eMob",1,"Rel-14","R2","2016-03-15","2017-06-15",1,"RP-160636",null,"ZTE",null,"no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[2805,710179,"   Core part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-162488","RP-170115","Ericsson",null,"1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->85%¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->21/3/17: Compl:85%->100%21/3/17: Stat Rep: ->RP-170115",null,71,36,null,null,"2016-03-22","2017-03-21"]
[2807,780063,"   UE Conformance Test Aspects - Uplink capacity enhancements for LTE","LTE_UL_CAP_enh-UEConTest",2,"Rel-14","R5","2017-12-15","2018-12-14",1,"RP-172639",null,"Ericsson",null,"tested: REL-14 WI LTE_UL_CAP_enh-Core¦related to UL 256 QAM27/3 ;¦26/3/19: 35%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[2810,780064,"   UE Conformance Test Aspects - L2 latency reduction techniques for LTE","LTE_LATRED_L2-UEConTest",2,"Rel-14","R5","2017-12-15","2018-03-15",1,"RP-180530",null,"Ericsson",null,"tested: REL-14 WI LTE_LATRED_L2-Core27/3/18: Compl:0%->100%;",null,78,40,null,null,"2018-01-08","2018-03-27"]
[2813,710281,"   Perf. part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[2817,750054,"   UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-UEConTest",2,"Rel-14","R5","2017-03-15","2018-06-15",1,"RP-180848",null,"Huawei",null,"tested: REL-14 LTE_SRS_switch-Core;¦19/6/17: Compl:0%->5%¦8/1/18: Compl:27/3/ ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2818,710084,"Downlink Multiuser Superposition Transmission for LTE","LTE_MUST",1,"Rel-14","R1","2016-03-15","2017-06-15",1,"RP-160680",null,"MediaTek",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[2820,710284,"   Perf. part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-161019",null,"MediaTek",null,"1/7/16: WID: RP-160680->RP-161019¦26/9/16: CD:Fri 15/09/17->Thu 15/06/17¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:0%->25%19/6/17: Compl:25%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[2823,720071,"   (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc8",2,"Rel-14","C1-IETF","2016-06-14","2017-03-15",1,"CP-160294",null,"Alcatel-Lucent","Keith Drage",null,"draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update (became RFC 8122)",72,37,null,null,"2014-12-04","2015-12-07"]
[2826,720094,"Multi-Carrier Enhancements for UMTS","UTRA_MCe",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-161259",null,"Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe",null,72,37,null,null,"2016-07-08","2016-06-22"]
[2829,720095,"Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US",1,"Rel-14","R4","2016-06-15","2017-06-15",1,"RP-161219",null,"Nokia",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2832,740069,"   UE Conformance Test Aspects – Citizens Broadband Radio Service (CBRS) 3.5GHz Band for LTE in the United States (Band 48)","LTE_TDD_3550_CBRS_US-UEConTest",2,"Rel-14","R5","2016-12-15","2017-06-15",1,"RP-162254",null,"Nokia",null,"21/3/17: Compl:0%->60% ¦ 19/6/17: Compl:60%->100%",null,74,38,null,null,"2016-12-20","2017-06-19"]
[2835,720296,"   Perf. part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[2839,721003,"Positioning Enhancements for GERAN","ePOS_GERAN",1,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-161260",null,"Ericsson",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2840,721103,"   Core part: Positioning Enhancements for GERAN","ePOS_GERAN-Core",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052","RP-170920","Ericsson",null,"26/9/16: Compl:0%->30%¦20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ¦19/6/17: Compl:80%->100%;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[2842,730079,"Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN","UMTS_QMC_Streaming",1,"Rel-14","R2","2014-12-03","2018-03-15",0.99,"RP-161917",null,"China Unicom",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2845,750055,"   UE Conformance Test Aspects -Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN","UMTS_QMC_Streaming-UEConTest",2,"Rel-14","R5","2017-03-15","2018-03-15",1,"RP-180559",null,"Huawei",null,"tested: REL-14 UMTS_QMC_Streaming-Core;19/6/17: Comp 19/ 8/1/18: 27/3/",null,75,38,null,null,"2017-03-21","2018-03-27"]
[2848,730180,"   Core part: Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID-Core",2,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161896","RP-170478","China Telecom",null,"¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478",null,73,37,null,null,"2016-09-26","2017-03-21"]
[2852,740071,"   Introduction of new band support for 4Rx antenna ports for LTE","LTE_4Rx_AP_DL_bands",2,"Rel-14","R4","2016-12-15","2018-09-14",0.99,"RP-162496",null,"Huawei",null,"Pending acronym",null,74,38,null,null,"2016-12-20","2016-12-20"]
[2855,730085,"Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX",1,"Rel-14","R4","2016-09-15","2018-09-14",0.99,"RP-161898",null,"Qualcomm",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2858,760085,"   UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE","LTE_UE_cat_1RX-UEConTest",2,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-180263",null,"Qualcomm",null,"¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[2861,710083,"LTE Measurement Gap Enhancement","LTE_meas_gap_enh",1,"Rel-14",null,"2016-03-15","2017-06-15",1,"RP-160678",null,"Intel",null,null,null,71,36,null,null,"2016-03-22","2017-03-21"]
[2864,730082,"Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE","LTE_eCRSIM_eSUMIMO",1,"Rel-14",null,"2016-09-15","2017-09-15",1,"RP-161877",null,"Intel",null,null,39.747,73,37,null,null,"2016-09-26","2016-09-26"]
[2866,780051,"Miscellaneous IETF dependencies","TEI14_IETF",1,"Rel-14",null,"2017-03-15","2020-06-05",0.75,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"Created upon demand of RAN5",null,78,40,null,null,"2017-12-18","NA"]
[2867,870066,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel)","TEI14_IETF",2,"Rel-14","CT1-IETF","2020-02-06","2020-06-05",0.8,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"9/4/21: RFC 8865 added;","RFC 8865",78,40,null,null,"2017-12-18","2021-04-09"]
[2870,780054,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel) ","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-12-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"22/3/18: 25%->100. was (IETF) BFCP floor control signalling over Data Channels (draft-schwarz-mmusic-bfcp-usage-data-channel). ; 9/4/21: RFC 8865 added;","RFC 8865",78,40,null,null,"2017-12-18","2021-04-09"]
[2874,620062,"Security Assurance Specification for 3GPP network products","SCAS",1,"Rel-14","S3","2013-12-09","2017-06-15",1,"SP-150292","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","Triggered by Rel-12 TR 33.805 Study on Security Assurance Methodology for 3GPP Network Elements (FS_SECAM)¦June2015: WID:SP-130718->SP-150292. Aug 15: TR numb added¦28/1/16: 33.926 added¦28/7/16: 33.250 added;06/10/16: moved to Rel-14 as per John/M ","33.199; 33.926, 33.117; 33.250; 33.515",62,32,null,null,"2013-11-22","2018-08-06"]
[2877,620262,"   Security Assurance Specification for 3GPP network product classes","SCAS-SA3",2,"Rel-14","S3","2013-12-13","2017-06-15",1,"SP-150716","-","China Mobile","Judy Zhu (zhuhongru@chinamobile.com)","June2015: 0%->5¦7/12/15: 5%->72.¦10/12/15: WID:SP-130718->SP-150716¦7/3/16: 72%->75¦28/7/16: 33.250 added¦19/9/16: 75%->90. FCD set to 12.16 (was 03/16). 6/3/17: moved from Rel-14.¦15/2/18: moved back to Rel-14¦6/8/18: 33.515 added;","New 33.116, 33.117; 33.250; 22.511; 22.512; 22.513; 22.514; 33.515",62,32,null,null,"2013-11-22","2018-08-06"]
[2879,689999,"(Small) Test Technical Enhancements and Improvements for Rel-14","TEI14_Test",1,"Rel-14","SP,CP,RP,GP","2016-09-13","2018-12-20",1,"-",null,"-","-","Created upon demand of RAN5","-",68,35,null,null,"2015-01-12","2016-02-24"]
[2883,690286,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[2886,690287,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[2887,690088,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[2890,709999,"Rel-14LTE Advanced inter-band Carrier Aggregation","LTE_AIBCA_Rel14",1,"Rel-14","R4","2015-12-15","2021-09-21",0.87,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[2892,700169,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL","LTE_CA_R14_5DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170143",null,"Nokia Networks",null,"28/1/16: 36.714-05-01 added¦22/3/16: Compl:0%->15%¦22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%¦26/9/16: Compl:40%->60%¦20/12/16: Compl ¦21/3/17","36.714-05-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2896,700270,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-170123",null,"Qualcomm",null,"22/3/16: WID: RP-152196->RP-1606161/7/16: Compl:0%->30%1/7/16: WID: RP-160616->RP-161202¦26/9/16: Compl:30%->50% 20/12/16: Compl:50%->75% 21/3/17: Compl:75%->80%;",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2899,700271,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"¦22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-16094726/9/16: WID: RP-160947->RP-161676¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->90",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2901,700172,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL-Core",3,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,"28/1/16: 36.714-03-03 added;22/3/16: Compl:0%->1%1/7/16: Compl:1%->15%¦21/3/17: Compl:15%->100%","36.714-03-03","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2905,700273,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0,"RP-170128",null,"LG Electronics",null,"22/3/16: WID: RP-152246->RP-1601481/7/16: WID: RP-160148->RP-160748¦26/9/16: WID: RP-160748->RP-161487¦20/12/16: WID: RP-161487->RP-16203621/3/17:",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2908,700274,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"¦22/3/16: WID: RP-152249->RP-160614¦1/7/16: Compl:0%->38%¦1/7/16: WID: RP-160614->RP-16082126/9/16: Compl:38%->0%¦20/12/16: Compl:0%->95% ¦21/3/17: CD:Wed 1",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[2909,700075,"   LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra",2,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-152250",null,"Ericsson",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[2912,700076,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-152278",null,"Huawei",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[2916,0,"Release 14 Studies","-",1,"Rel-14","SP,RP,CP,GP","2014-09-17","2015-12-11",1,"-","-",null,"-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2918,700058,"Study on Scenarios and Requirements for Next Generation Access Technologies","FS_NG_SReq",1,"Rel-14","RP","2015-12-15","2016-12-15",1,"RP-160811",null,"CMCC",null,"22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%¦14/12/16: FCD:09/16->12/16¦14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re","38.xxx",70,36,null,null,"2016-01-01","2016-12-20"]
[2921,620071,"Study on Multimedia Broadcast Supplement for Public Warning System","FS_MBSP",1,"Rel-14","S1","2013-12-11","2014-12-12",1,"SP-130599",null,"Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100%",22.815000000000001,62,32,null,null,"2013-11-26","2014-12-03"]
[2925,670011,"Study on Paging Policy Enhancements and Procedure Optimizations in LTE","FS_PPEPO_LTE",1,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150053",null,"Zhuoyun Zhang (China Unicom)","zhangzy910@chinaunicom.cn","1/4/15:TR number added¦June2015: Compl:0%->40¦07/09/15: 40%->60¦7/12/15: 60%->100","New 22.838",67,34,null,null,"2015-03-04","2015-12-07"]
[2927,680057,"Study on High Power LTE UE for Band 41","FS_LTE_B41_HPUE",1,"Rel-14","R4","2015-06-15","2016-06-15",1,"RP-160092",null,"Sprint",null,"7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ¦22/3/16: Compl:10%->40%¦22/3/16: WID: RP-151104->RP-1600921/7/16: Compl",36.886000000000003,68,35,null,null,"2015-07-03","2016-07-01"]
[2930,700036,"Study on UICC power optimization for MTC","FS_UICC_MTC_OPT",1,"Rel-14","C6","2016-06-15","2016-12-15",1,"CP-150875",null,"Berionne, Michele","micheleb [at] qti [dot] qualcomm [dot] com","7/3/16: 0%->100¦5/6/17: 71%->100",31.97,70,36,null,null,"2015-12-07","2017-06-05"]
[2931,710013,"Study on Server and Network Assisted DASH for 3GPP","FS_SAND",1,"Rel-14","S4","2016-03-01","2016-12-15",1,"SP-160083",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100","TR26.957 ",71,36,null,null,"2016-03-01","2016-12-01"]
[2934,710058,"Study on HSPA and LTE Joint Operation","FS_UTRA_LTE_JOP",1,"Rel-14","R3","2016-03-15","2016-12-15",1,"RP-160571",null,"China Unicom",null,"¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦","New 37.805",71,36,null,null,"2016-03-22","2016-12-20"]
[2938,670015,"Study on Determination of Completeness of Charging Information in IMS","FS_DCCHII",1,"Rel-14","S5","2015-03-05","2016-03-11",1,"SP-150106",null,"Jesske, Roland","r.jesske@telekom.de","11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request¦June2015: Compl:0%->7¦07/09/15: 7%->15¦7/12/15: 15%->60, FCD: 09/15->03/16¦7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14","32.xyz",67,34,null,null,"2015-03-05","2016-03-22"]
[2940,720026,"Study on MBMS usage and codecs for MCPTT call and MC Video Service","FS_MCP_V",1,"Rel-14","S4","2016-06-13","2017-03-15",1,"SP-160274",null,"Zhiming Li, Huawei","lizhiming@huawei.com","28/7/16: 26.880 added¦19/9/16: 0%->30, FCD: 12/16->03/17¦1/12/16: 30%->60¦6/3/17: 60%->100",26.88,72,37,null,null,"2016-06-11","2017-03-06"]
[2943,720089,"Study on Downlink MIMO for GERAN","FS_DOMIMO_RAN6",1,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161261",null,"Nokia, Alcatel-Lucent Shanghai Bell",null,"continuation of GERAN SI UID 590034, DOMIMO under RAN626/9/16: Compl:0%->100%",null,72,37,null,null,"2016-07-01","2016-09-26"]
[2947,700023,"   FS_SMARTER – massive Internet of Things","FS_SMARTER-mIoT",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150817",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","2/3/16: 35%->65¦9/6/16: 65%->100","New 22.861",70,36,null,null,"2015-12-07","2016-06-09"]
[2950,700026,"   FS_SMARTER – Network Operation","FS_SMARTER-NEO",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150820",null,"Lu Lu","lulu@chinamobile.com","2/3/16: 30%->60¦19/9/16: 60%->100","New 22.864",70,36,null,null,"2015-12-07","2016-09-19"]
[2951,700017,"SA2 aspects on Study on Architecture and Security for next Generation System","FS_NextGen",1,"Rel-14","S2","2015-12-07","2016-12-15",1,"SP-160727",null,"suntao@chinamobile.com, devaki.chandramouli@nokia.com","suntao@chinamobile.com, devaki.chandramouli@nokia.com","28/1/16: 23.799 added¦Acronym corrected (\"NexGen\"->\"NextGen\")¦7/3/16: 5%->15¦10/3/16: WID:SP-150853->SP-160200. Name changed from \"Study on Architecture for next Generation System\"¦9/6/16: 15%->35¦19/9/16: 35%->64¦22/9/16: WID:SP-160227->SP-16072",23.798999999999999,70,36,null,null,"2015-12-07","2016-12-01"]
[2953,0,"--- RELEASE 13 ---","-",1,"Rel-13","SP,RP,CP,GP","2013-12-11","2014-11-25",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[2956,670030,"   SA2 Study on Architecture Enhancements at the EPS and IMS Level to Support MCPTT","MCPTT",2,"Rel-13","S2","2015-03-13","2015-06-17",1,"SP-150356",null,"Randy Bloomfield (randy@its.bldrdoc.gov)","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164.¦June2015: Compl:0%->30, WID updated¦07/09/15: 30%->100, \"To be confirmed\" deleted, since SA2 has completed it.",null,67,34,null,null,"2015-03-13","2015-09-07"]
[2960,640143,"   Functional architecture and information flows to support MCPTT","MCPTT",2,"Rel-13","S6","2015-06-18","2015-12-11",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","June2015: added as per SP-150356¦June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID¦07/09/15: 15%->50¦07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15¦7/3/16: 85%->100","New 23.179",64,33,null,null,"2014-06-04","2016-03-07"]
[2963,690011,"   MCPTT protocol aspects","MCPTT-CT",2,"Rel-13","ct","2015-09-07","2016-06-30",0.96,"CP-150793",null,"Keith Drage, Alcatel-Lucent",null,"7/12/15: WID:CP-150587->CP-150793¦28/1/16: 24.384 added;",null,69,35,null,null,"2015-09-07","2016-01-28"]
[2966,690097,"         Call Control – Off Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.379000000000001,69,35,null,null,"2015-09-29","2016-12-05"]
[2969,691000,"         Broadcast – Call Control and Floor Control","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->50¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 50%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","24.379, 24.380",69,35,null,null,"2015-09-29","2016-12-05"]
[2972,691003,"         Management Object","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->10¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 10%->100. Name changed from \"Configuration management\"¦7/3/16: WID:CP-150863->CP-160160¦5/12/1",24.382999999999999,69,35,null,null,"2015-09-29","2016-12-05"]
[2973,710033,"         Configuration management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Introduced from CT1 WP update in 03/16¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.384,71,36,null,null,"2016-03-07","2016-12-05"]
[2977,710034,"      (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",0.25,"CP-160817",null,"Ericsson","christer.holmberg@ericsson.com","5/12/16: WID:CP-160160->CP-160817","draft-holmberg-dispatch-mcptt-rp-namespace",71,36,null,null,"2016-03-07","2016-12-05"]
[2978,870072,"      (IETF) OAuth 2.0 Token Exchange (draft-ietf-oauth-token-exchange) --> RFC 8693","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",1,"CP-160817",null,null,null,null,null,87,44,null,null,"2016-03-07","2016-12-05"]
[2982,670031,"   Deleted (duplicated): Application Architecture to support MCPTT","MCPTT",2,"Rel-13","S6","2015-03-13","2015-03-13",1,"SP-150356",null,"U.S. Department of Commerce","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated. 7/15: removed since duplicates 640143 and 660054 (only 640143 is kept)",null,67,34,"SP-69",null,"2015-03-13","2015-07-31"]
[2985,670090,"   TR on Profiling and Extensions of MBMS","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100","new 26.852",67,34,null,null,"2015-04-08","2015-12-07"]
[2988,680047,"   Stage 1 fo Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-150463","S1-143304","General Dynamics","paul.piggin@gd-broadband.com","SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463","New 22.346",63,32,null,null,"2014-02-05","2015-09-14"]
[2991,700037,"   CT aspects for IOPS","IOPS-CT",2,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com",null,null,70,36,null,null,"2015-12-07","2015-12-07"]
[2994,650018,"Enhanced Calling Information Presentation","ECIP",1,"Rel-13","S1","2014-09-15","2015-12-16",1,"SP-140513","S1-143311","China Mobile","LI Xiaofan (lixiaofan@chinamobile.com","SP#65 approved WID & completed. Triggered by Rel-13 TR 22.810. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067. 31/07/15: 100%","22.182 (CAT), 22.183 (CRS) ",62,32,null,null,"2013-11-26","2015-07-31"]
[2995,650019,"Flexible Mobile Service Steering","FMSS",1,"Rel-13","S1,S2","2014-09-15","2016-03-11",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS)",22.100999999999999,65,33,null,null,"2013-11-26","2014-08-28"]
[2998,660003,"   Flexible Mobile Service Steering - Stage 2","FMSS-SA2",2,"Rel-13","S2","2014-12-12","2015-06-17",1,"SP-140703",null,"Lu Lu, China Mobile","lulu@chinamobile.com","07/09/15: 0%->90¦07/09/15: 90%->100",null,66,34,null,null,"2014-12-03","2015-09-07"]
[3001,640052,"Application specific Congestion control for Data Communication","ACDC",1,"Rel-13","S1,C1","2014-06-18","2016-03-11",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. Triggered by Rel-13 Study TR 22.806",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[3004,660139,"      CT1 part of Stage 3 for Application specific Congestion control for Data Communication","ACDC-CT",3,"Rel-13","C1","2014-12-04","2015-12-16",1,"CP-150282",null,"Kim, Jaehyun, LGE","jaehyun7.kim@lge.com","Presented at CT#66¦June2015: Compl:0%->10. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282¦07/09/15: 5%->70¦7/12/15: 70%->100","24.105, 24.301, 24.008, 27.007, 23.122",66,34,null,null,"2015-05-05","2015-12-07"]
[3007,670159,"      Core part: RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN-Core",3,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150662","RP-151275","LG Electronics",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150512->RP-150662 03/07/15: Stat Rep: ->RP-150661 29/09/15: Compl:25%->70% 29/09/15: Stat Rep: RP-150661->RP-151275¦1/1/16: Compl:70%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3011,580058,"   Deleted - Stage 2 for User Plane Congestion management","UPCON-SA2Del",2,"Rel-13","S2","2012-12-19","2013-12-11",1,"SP-140631","-","NEC","andreas.maeder@neclab.eu","SP#62 stopped at 0% completion","TBD",58,30,"SP-62","PCG-32","2012-11-13","2014-09-16"]
[3012,630019,"   BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON",2,"Rel-13","S2","2014-03-07","2015-03-13",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control","-",63,32,null,null,"2014-03-04","2014-09-16"]
[3016,650207,"         CT4 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C4","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->20¦WID: CP-140734->CP-140929. Mar. 15: 50%¦June2015: Compl:50%->90. WID: CP-140929-> CP-150365.¦07/09/15: 90%->100","23.003, 29.303, New 29.405 (UPCON over Nq)",65,33,null,null,"2014-07-29","2015-09-07"]
[3017,630020,"   Deleted - BB2: Application and Content Prioritization","UPCON-CONDEL",2,"Rel-13","S2","2014-03-07","2014-09-17",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Content specific UP prioritization (Video), Application specific UP prioritization","TBD",63,32,"SP-65","PCG-33","2014-03-04","2014-09-16"]
[3020,650128,"   TR on Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",2,"Rel-13","S4","2014-09-09","2015-09-16",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100","New 26.9xy",65,33,null,null,"2014-09-05","2015-12-07"]
[3023,710036,"   (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",0.9,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90; 9/4/21: RFC 8849 added;","26.22; RFC 8849",71,36,null,null,"2016-03-07","2021-04-09"]
[3027,600145,"   Stage 1 for RAN Sharing Enhancements","RSE-SA1",2,"Rel-13","S1","2013-06-19","2013-12-11",1,"SP-130330","-","NEC","joerg.swetina@neclab.eu","SP#62 completed",22.100999999999999,60,31,null,null,"2013-06-03","2013-11-26"]
[3029,650121,"      Core part: RAN aspects of RAN Sharing Enhancements for LTE","RSE-RAN_LTE-Core",3,"Rel-13","R3","2014-09-12","2015-12-15",1,"RP-151827","RP-151295","NEC","Siva.Vakeesar@emea.nec.com","¦CD:Mon 15/06/15->Tue 15/09/15¦Stat Rep: -->RP-141891 1st Apr 15: Compl:15%->20% 1st Apr 15: Stat Rep: RP-141891->RP-150289 03/07/15: Compl:20%->75% 03/07/15: Stat Rep: RP-150289->RP-150875 29/09/15: Compl:75%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/1","36.300, 36.413, 36.423",65,33,null,null,"2014-06-16","2016-01-01"]
[3033,640038,"   Stage 2 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140630","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part)¦June2015: Compl:0%->85¦07/09/15: 85%->100",23.228000000000002,64,33,null,null,"2014-06-12","2015-09-07"]
[3036,690037,"   (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third Party Authorization (draft-ietf-tram-turn-third-party-authz)","eWebRTCi",2,"Rel-13","S3-IET","2014-09-17","2015-08-12",1,"SP-150474","-","Alcatel-Lucent",null,"TS 33.203 CR0235 draft-ietf-tram-turn-third-party-authz¦7/3/16: 10%->100; 9/4/21: RFC 7635 added;","33.203, RRC 7635 (was draft-ietf-tram-turn-third-party-authz); RFC 7635",69,35,null,null,"2014-09-04","2021-04-09"]
[{"$f":"A3038+1","v":3038},690015,"      CT1 aspects 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C1","2015-09-07","2015-12-18",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: 0%->100¦7/12/15: WID:CP-150498->CP-150790->CP-150767","24.371, 24.229",69,35,null,null,"2015-09-07","2015-12-07"]
[3039,690029,"      CT3 aspects for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150644¦7/3/16: 0%->100",29.213999999999999,69,35,null,null,"2015-09-07","2016-03-07"]
[3042,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",0.75,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371, 24.229, 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[3046,630016,"Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks","CSPS_Coord",1,"Rel-13","S2","2014-03-07","2016-05-12",1,"SP-140168","-","Ericsson","roland.gustafsson@ericsson.com","Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios","Stage 2",63,32,null,null,"2014-02-05","2014-03-04"]
[3049,650100,"   RAN aspects for improvements to CS/PS coordination in GERAN Shared Networks","CSPS_Coord_GERAN",2,"Rel-13","G2","2015-03-11","2016-05-12",1,"GP-150225",null,"Nicklas Johansson, Ericsson LM","Nicklas.Johansson@Ericsson.com","June2015: Compl:0%->35¦07/09/15: 35%->50, FCD:08/15->11/15¦7/12/15: 50%->95, FCD: 12/15->02/16. 02/03/16: FCD: 02/16->05/16¦13/6/16: 95%->100","48.008, 48.018",65,33,null,null,"2015-05-07","2016-06-13"]
[3051,640140,"   Stage 1 for Enhancements to Proximity-based Services","eProSe-SA1",2,"Rel-13","S1","2014-06-19","2014-09-17",1,"SP-140386","-","Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced.","22.115, 22.278",64,33,null,null,"2014-05-27","2014-09-03"]
[3055,680006,"   CT aspects of enhancements to Proximity-based","eProSe-Ext-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,"23.122, 24.301, 24.333, 24.334",68,35,null,null,"2015-06-15","2015-06-15"]
[3058,680009,"      CT4 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->10¦7/12/15: 10%->80. FCD->03/16. ES in CP-150616¦7/3/16: 80%->100","31.102, 31.111",68,35,null,null,"2015-06-15","2016-03-07"]
[3061,729999,"   Note: Charging Aspects done in Rel-14 under CH14-Prose (UID 720049)","eProSe",2,"Rel-13","S5","2015-06-17","2015-06-17",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,72,37,null,null,"2016-06-13","2016-12-01"]
[3062,640045,"voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD",1,"Rel-13","S1,S2,C4,C1,C3","2014-06-16","2014-12-12",1,"SP-140394","-","Alcatel-Lucent","(betsy.covell@alcatel-lucent.com)","-","Stage 1/2",64,33,null,null,"2014-05-29","2014-06-11"]
[3064,640245,"   Stage 2 for voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-SA2",2,"Rel-13","S2","2014-06-18","2014-12-12",1,"SP-140394","-","Alcatel-Lucent","laurent.thiebaut@alcatel-lucent.com","Architectural enhancements allowing a differentiated paging policy for IMS voice calls over E-UTRAN. Dec.14: 25->100%","23.228, 23.401",64,33,null,null,"2014-06-11","2014-12-03"]
[3068,650303,"      CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Mar.15: 0->100%",29.061,65,33,null,null,"2014-07-29","2015-03-04"]
[3071,640247,"   Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM-SA2",2,"Rel-13","S2","2014-06-23","2015-09-16",1,"SP-150250",null,"Tricci So, ZTE","tso@zte.com.cn","June2015: Compl:0%->65, WID: SP-140279->SP-150250¦07/09/15: 52%->100","23.402, New 23.203",64,33,null,null,"2014-05-30","2015-09-07"]
[3073,680019,"   CT aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation","zhou.xingyue@zte.com.cn","14/09/15: WID:CP-150285->CP-150497¦7/12/15: WID:CP-150497->CP-150791->874",24.161000000000001,68,35,null,null,"2015-06-15","2015-12-07"]
[3077,640053,"Double Resource Reuse for Multiple Media Sessions","DRuMS",1,"Rel-13","S2","2014-03-14","2015-03-13",1,"SP-140393","-","Ericsson","George.Foti@ericsson.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-06-11"]
[3080,660047,"      CT1 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,"5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100","24.229, 24.615, 24.610, 24.605",66,34,null,null,"2014-12-09","2015-09-07"]
[3083,640055,"STOPPED - Study on Lawful Interception Service Evolution","FS_LISE",1,"Rel-13","S3","2014-06-23","2015-12-09",1,"SP-140303","-","Alcatel-Lucent","terry.jacobson@alcatel-lucent.com","Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points. 3/3/15: 0->5%¦7/12/15: 5%->10. Stoppped at 10% in March 2017.¦6/3/17: 10%->100",33.826000000000001,64,33,null,null,"2014-06-11","2017-03-06"]
[3084,640058,"Video enhancements by Region-Of-Interest information signalling","ROI",1,"Rel-13","S4","2014-06-18","2015-12-16",1,"SP-140219","-","Intel","ozgur.oyman@intel.com","Dec.14: 5->20%. Mar.15: 40%¦07/09/15: 43%->100",26.114000000000001,64,33,null,null,"2014-06-06","2015-09-07"]
[3088,680033,"      CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->10¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 10%->100",29.161999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[3090,650026,"TV video profile","TVProf",1,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Mar. 15: 5->15%","-",65,33,null,null,"2014-09-05","2015-03-05"]
[3093,650027,"Enhanced LTE UE Delay test methods and requirements","E_LTE_UED",1,"Rel-13","S4","2014-09-09","2016-06-15",1,"SP-140482","-","Orange","stephane.ragot@orange.com","Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->50¦7/12/15: 50%->80, FCD: 12/15->03/16. ES in SP-150652¦7/3/16: FCD: 03/16->06/16¦11/6/16: 80%->100","26.131, 26.132",65,33,null,null,"2014-09-05","2016-06-11"]
[3096,670016,"   SA4 aspects of EVS in 3G Circuit-Switched networks","EVSoCS-S4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%¦Aug2015: 10%->20¦07/09/15: 20%->40¦7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103, 28.062, New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-03-07"]
[3099,670018,"      CT3 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C3","2015-03-04","2016-03-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","June2015: Compl:0%->10¦07/09/15: 10%->15¦7/12/15: 15%->90. FCD -> 03/16, ES in CP-150638¦7/3/16: 90%->100","29.163, 29.414, 29.415",67,34,null,null,"2015-03-04","2016-03-07"]
[{"$f":"A3102+1","v":3102},660173,"      Core part: Support of EVS over UTRAN CS","EVSoCS_UTRAN-Core",3,"Rel-13","R2,R1,R3","2015-06-16","2015-12-15",1,"RP-142282","RP-151282","Francesco Pica - Qualcomm Incorporated ","fpica@qti.qualcomm.com","Rapporteur details and involved WGs updated 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150128. 5/5/15: 0->10% 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150128->RP-150759 29/09/15: Compl:25%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3103,650031,"Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP)","eDASH",1,"Rel-13","S4","2014-09-09","2015-12-16",1,"SP-150448","-","Qualcomm, Huawei","Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com)","Triggered by Rel-12 Dec.14: 0->10%. Mar. 15: 15%¦June2015: Compl:15%->25. WID updated¦Aug2015: 25%->30¦07/09/15: 30%->60¦14/09/15: WID:SP-150211->SP-150448¦7/12/15: 60%->100","26.233, 26.234, 26.244, 26.247, 26.938, 26.346, 26.946",65,33,null,null,"2014-09-05","2015-12-07"]
[3106,650132,"   SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",2,"Rel-13","S4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65: WID SP-130670=>SP-140601 (moved from Rel12 incl. new TR to Rel-13). FCD 03/15=>06/15. St1 in TS 22.173. 12/14: 70->40%, CD: 06/15->09/15. 03/15: 50%. June 15: FCD: 09/15->12/15¦08/15: 60%¦09/15: 75%¦7/12. ES in SP-150658¦7/3/16: 90%->100",26.114000000000001,59,30,null,null,"2013-02-20","2016-03-07"]
[3110,660046,"      CT4 Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",3,"Rel-13","C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,"FCD -> 03/16, ES in CP-150620¦7/3/16: 0%->100","23.333, 23.334, 29.238, 29.332, 29.333, 29.334",66,34,null,null,"2014-12-09","2016-03-07"]
[3112,710042,"   Codec aspects for MMCMH","MMCMH",2,"Rel-13","S4","2014-12-12","2015-12-17",1,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Introduced by MCC to dissociate S4 from IeTF aspects","26.114, New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[3115,660051,"Video Telephony Robustness Improvements Extensions","VTRI_EXT",1,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","New TR added. 3/3/15: \"extensions\" added in the title. Mar. 15: 0->10%","26.922 (new), 26.114",66,34,null,null,"2014-12-12","2015-03-05"]
[3118,690038,"   (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627","VTRI_EXT",2,"Rel-13","S4-IETF","2014-12-12","2015-09-11",1,"SP-15047",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added; 23/4/20: 10%->100","26.114, draft-ietf-payload-flexible-fec-scheme",69,35,null,null,"2015-03-03","2020-04-23"]
[3122,560034,"   Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",2,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0","-",56,29,null,null,"2012-05-14","2014-09-01"]
[3123,560134,"      TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",3,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13.. Dec.14: 72->78. Mar 15: 80%¦June2015: Compl:80%->85¦07/09/15: 85%->90¦7/12/15: 90%->100","New 32.838",56,29,null,null,"2012-05-14","2015-12-07"]
[3125,560235,"   Converged management Performance Management Interface Definitions","OAM-PMID",2,"Rel-13","S5","2012-06-20","2015-12-11",1,"SP-150678","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678","new TSs 32.863 ",56,29,null,null,"2012-05-14","2015-12-07"]
[3128,560236,"      WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface","WLAN-OAM-SA5ietf",3,"Rel-13","S5","2012-06-27","2015-06-17",1,"SP-140535","-","Intel","joey.chou@intel.com","SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified¦June2015: Compl:5%->20¦07/09/15: 20%->60¦7/12/15: 60%->100","new 28.403",56,29,null,null,"2012-06-12","2015-12-07"]
[3131,641000,"Rel-13 Charging","CH13",1,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-150307","-","-","-","CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150307","-",64,33,null,null,"2014-06-06","2015-06-18"]
[3134,640259,"      Specification of Inter-PLMN PS domain online charging","iPLMN-PS-OCH",3,"Rel-13","S5","2014-06-23","2015-12-16",1,"SP-140324","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","07/09/15: 0%->80¦7/12/15: 80%->100","32.251, 32.299",64,33,null,null,"2014-06-06","2015-12-07"]
[3137,680037,"   Announcements for IMS Online Charging","ANIMO",2,"Rel-13","S5","2015-06-15","2015-12-14",1,"SP-150675",null,"Amdocs, Naceur <dot> Lagha <at> Amdocs <dot> com",null,"07/09/15: 0%->30¦7/12/15: 30%->100¦7/12/15: WID:SP-150307->SP-150675","32.260, 32.275, 32.299, 32.240, 32.281",68,35,null,null,"2015-06-14","2015-12-07"]
[3140,610105,"   CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C4","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15. Dec.14: 10->100","23.334, 29.334",61,31,null,null,"2013-08-10","2014-12-04"]
[3144,550117,"   Core part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US-Core",2,"Rel-13","R4,R2,R3","2013-08-06","2015-03-10",0.15,"RP-121397","RP-141452","LightSquared","masoud.olfat@lightsquared.com","RP#65 completion 03/15=>06/15. On hold till 12/2014","25.101, 25.104, 25.113, 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, new 36.832",55,28,null,null,"2012-02-23","2014-09-09"]
[3147,640119,"   Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB_sig-Core",2,"Rel-13","R3","2014-06-18","2015-09-15",1,"RP-141032","RP-151213","Samsung","sunghwan.won@samsung.com","CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141805 1st Apr 15: Compl:15%->30% 1st Apr 15: Stat Rep: RP-141805->RP-150162 03/07/15: Compl:30%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150162->RP-150846 29/09/1","36.300, 36.423",64,33,null,null,"2014-06-16","2015-09-29"]
[3149,640136,"   Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Core",2,"Rel-13","R4","2014-06-17","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:5%->15%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL), New 36.862 (Technical Report for 2 GHz Band in Region 1)",64,33,null,null,"2014-06-16","2016-01-01"]
[3150,640236,"   Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Perf",2,"Rel-13","R4","2014-06-18","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150106->RP-150705 29/09/15: Stat","36.101, 36.104, 36.133, 36.141, 36.307, 36.862",64,33,null,null,"2014-06-16","2016-01-01"]
[3153,650134,"   Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments","UTRA_LTE_SON_AAS-Core",2,"Rel-13","R3","2014-09-12","2015-06-15",1,"RP-141624","RP-150727","Nokia Networks","krzysztof.kordybach@nsn.com","CD:Tue 16/06/15->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141854 1st Apr 15: Compl:15%->25% 1st Apr 15: Stat Rep: RP-141854->RP-150110 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150110->RP-150727","36.300, 36.423, 36.413, 25.413",65,33,null,null,"2014-06-16","2015-06-18"]
[3157,660030,"Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",1,"Rel-13","C1","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[3160,660028,"P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",1,"Rel-13","C4","2014-12-03","2015-12-14",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","WID added, acronym. June 2015: WID: CP-140995-> CP-150275",null,66,34,null,null,"2014-12-04","2014-12-09"]
[3163,680012,"Mobile Equipment Identity signalling over WLAN ","MEI_WLAN",1,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com",null,"24.244, 24.302, 29.273, 29.274, 29.275, 23.008",68,35,null,null,"2015-06-15","2015-06-15"]
[{"$f":"A3166+1","v":3166},680041,"Authentication Signalling Improvements for WLAN","ASI_WLAN",1,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150330",null,"Youyang Yu","yuyouyang@huawei.com","07/09/15: 0%->40¦7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727¦7/3/16: 95%->100","24.302, 24.244",68,35,null,null,"2015-06-15","2016-03-07"]
[3169,670038,"   CS Fallback in EPS - Phase 4","SAES4-CSFB",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[3171,660034,"Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",1,"Rel-13","C1,C3","2014-12-03","2015-03-13",0.74,"CP-140928",null,"Orange",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[3172,660134,"   Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",2,"Rel-13","C1","2014-12-03","2015-03-13",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Orange",null,"5/5/15: created¦June2015: Compl:0%->70¦07/09/15: 70%->100",24.228999999999999,66,34,null,null,"2015-05-05","2015-09-07"]
[3175,660042,"Warning Status Report in EPS","WSR_EPS",1,"Rel-13","C4","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"5/5/15: acronym changed from \"WSR_EP\"¦7/12/15: WID:CP-140998->CP-150792",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3179,660017,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",1,"Rel-13","C1","2014-12-03","2017-06-20",0.7,"CP-140815",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%","23.218, 24.998, 24.930",66,34,null,null,"2014-12-04","2015-03-04"]
[3182,670097,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C3","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","2/4/15: added, following CT3 chair's info that the WID also has a CT3 part¦June2015: Compl:0%->20¦07/09/15: 20%->40¦7/12/15: 40%->100",null,67,34,null,null,"2015-04-02","2015-12-07"]
[3184,670020,"H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",1,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du","duxiaoning@chinamobile.com",null,23.334,67,34,null,null,"2015-03-04","2015-03-09"]
[3188,680014,"Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",1,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com",null,"23.334, 29.334, 29.162, 29.238, 23.333, 29.333, 29.163, 29.332, 29.292, 29.232, 29.235",68,35,null,null,"2015-06-15","2015-06-15"]
[3191,640044,"(SA66: on hold) Co-ordinated packet data network gateway (P-GW) change for SIPTO","CSIPTO",1,"Rel-13","S1","2014-06-18","2014-09-16",1,"SP-140509","S1-143306","Intel","Eric.siow@intel.com","SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO)",22.100999999999999,64,33,null,null,"2014-05-27","2014-12-12"]
[3192,660012,"   Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO","CSIPTO-ST1",2,"Rel-13","S1","2014-06-18","2014-09-16",1,"SP-140509","S1-143306","Intel","Eric.siow@intel.com","SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO). Dec.14: former S1-only feature split",22.100999999999999,64,33,null,null,"2014-05-27","2014-12-03"]
[3195,640251,"   Deleted - Stage 2 for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S2","2015-03-13","2015-03-13",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part)",23.271999999999998,64,33,"SP-69",null,"2014-06-11","2014-06-11"]
[3198,650125,"   TR for SRVCC Enhancements for Transcoding Avoidance","SETA-SA2TR",2,"Rel-13","S2","2014-09-19","2015-03-13",1,"SP-140436","-","Ericsson","George.Foti@ericsson.com","Dec.14: 0->70%¦14/09/15: 70%->100. Stopped without conclusion, no intention to continue the study nor to do any mormative work.","New 23.7xy",65,33,null,null,"2014-08-05","2015-09-14"]
[3201,590130,"   Core part: Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA-Core",2,"Rel-13","R4","2013-03-04","2016-03-15",1,"RP-160188","RP-151241","Huawei","ronnie.zhang@huawei.com","¦CD:Thu 11/12/14->Tue 15/12/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241¦","New 37.142 (AAS BS Tx & Rx), New 37.842, 37.114, 37.145-1, 37.145-2",59,30,null,null,"2013-02-26","2016-03-22"]
[3204,660174,"   Core part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Core",2,"Rel-13","R2,R1,R3","2015-08-14","2016-03-15",1,"RP-150441","RP-151337","Qualcomm Incorporated, Shailesh Patil","patil@qti.qualcomm.com ","Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3208,660077,"UE core requirements for uplink 64 QAM","LTE_UL64QAM",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-142222",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3210,680069,"UE Conformance Test Aspects - Core Requirements for Uplink 64QAM for E-UTRA","LTE_UL64QAM-UEConTest",1,"Rel-13","R5","2015-06-15","2015-12-15",1,"RP-150812","RP-151174","CMCC",null,"tested Core part: LTE_UL64QAM-Core which is not yet completed 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151174 1/1/16: Compl:5%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3213,660079,"CRS Interference Mitigation for LTE Homogenous Deployments","LTE_CRSIM",1,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142263",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3214,660279,"   Perf. part: CRS Interference Mitigation for LTE Homogenous Deployments","LTE_CRSIM-Perf",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142263","RP-151171","Ericsson","Ericsson","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Mon 15/06/15->Tue 15/03/16 1st Apr 15: Stat Rep: ->RP-150061 03/07/15: Compl:10%->20% 03/07/15: Stat Rep: RP-150061->RP-150584 29/09/15: Compl:20%->30% 29/09/15: Stat Rep: RP-150584->RP-151171 ",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3217,670255,"   Perf. part: Dual Connectivity enhancements for LTE","LTE_dualC_enh-Perf",2,"Rel-13","R4","2015-03-16","2016-06-15",1,"RP-151739","RP-151330","NTT DOCOMO",null,"03/07/15: Stat Rep: ->RP-150744 29/09/15: Stat Rep: RP-150744->RP-151330 ¦1/1/16: WID: RP-150490->RP-15173922/3/16: Compl:0%->50%;",null,67,34,null,null,"2015-04-01","2016-07-01"]
[3221,670058,"LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio",1,"Rel-13","R2","2015-03-16","2018-09-14",0.99,"RP-150510",null,"Intel",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3223,670258,"   Perf. part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Perf",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081 29/09/15: Stat Rep: RP-151081->RP-1515631/1/16: Compl:0%->10% ¦22/3/16: Compl:10%->100%¦",null,67,34,null,null,"2015-04-01","2016-03-22"]
[3226,670160,"   Core part: RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network","CSPS_Coord-UTRA-Core",2,"Rel-13","R3","2015-03-16","2015-12-15",1,"RP-150500","RP-151289","Ericsson",null,"03/07/15: Compl:0%->45% 03/07/15: Stat Rep: ->RP-150842 29/09/15: Compl:45%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150842->RP-1512891/1/16: Compl:80%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[{"$f":"A3230+1","v":3230},700066,"   UE Conformance Test Aspects - LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-UEConTest",2,"Rel-13","R5","2015-12-15","2017-09-15",1,"RP-160078",null,"Ericsson",null,"¦22/3/16: Compl:0%->10%¦1/7/16: Compl:10%->25%¦ 26/9/16: 21/3/17: Compl:60%->70 ;",null,70,36,null,null,"2016-01-01","2017-09-19"]
[3232,670162,"   Core part: AWS-Extension Band for LTE","LTE_AWS_EXT-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150800","RP-151343","Ericsson",null,"03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3235,670063,"Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset",1,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150171",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3236,670163,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150602","RP-150536","Nokia Networks",null,"03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3239,670164,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425","RP-150536","Samsung",null,"03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3243,680044,"Message interworking during PS to CS SRVCC ","mSRVCC",1,"Rel-13","C1","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com",null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[3245,680046,"   CT3 aspects of Message interworking during PS to CS SRVCC ","mSRVCC",2,"Rel-13","C3","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com","07/09/15: 0%->70¦7/12/15: 70%->100",29.292000000000002,68,35,null,null,"2015-06-15","2015-12-07"]
[3248,690009,"   CT aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",2,"Rel-13","ct","2015-09-07","2016-03-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[3252,690036,"      CT6 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C6","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/3/16: 0%->100",31.102,69,35,null,null,"2015-09-07","2016-03-07"]
[3255,690046,"   MBMS Enhancements","MBMS_enh_St2",2,"Rel-13","S2","2015-08-10","2015-09-16",1,"SP-150520",null,"Nokia Networks, Curt Wong",null,"SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_","23.246, 23.468",69,35,null,null,"2015-09-16","2015-10-14"]
[3256,700006,"   CT aspects of MBMS Enhancements","MBMS_enh-CT",2,"Rel-13","C3","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,null,70,36,null,null,"2015-12-07","NA"]
[3258,700007,"      CT4 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C4","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,"29.274, 23.008, 29.230",70,36,null,null,"2015-12-07","2015-12-07"]
[3261,690026,"   CT3 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100","29.212, 29.213",69,35,null,null,"2015-09-07","2015-12-08"]
[3265,700010,"   CT4 aspects of DiaPri","DiaPri",2,"Rel-13","C4","2015-11-02","2016-03-11",1,"CP-150613",null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com","ES in CP-150622¦7/3/16: 70%->100","29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.338, 29.344, 29.345",70,36,null,null,"2015-12-07","2016-03-07"]
[3268,680159,"   Core part: Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC-Core",2,"Rel-13","R1,R2,R3","2015-10-15","2015-12-15",1,"RP-151880","RP-151564","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3271,680160,"   Core part: Licensed-Assisted Access using LTE","LTE_LAA-Core",2,"Rel-13","R1","2015-06-15","2015-12-15",1,"RP-151045","RP-151390","Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-1513901/1/16: Compl:25%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3274,680061,"Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO",1,"Rel-13","R1","2015-06-15","2018-12-14",0.99,"RP-151085","-","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3277,770062,"   UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE","LTE_EBF_FDMIMO-UEConTest",2,"Rel-13","R5","2017-09-15","2018-12-14",1,"RP-172651",null,"Ericsson",null,"¦8/1/18: Compl:0%->5%¦27/3/18: Compl:5%->10%¦27/6/18: CD:Fri 15/06/18-; 26/3/20: 10%->100",null,77,39,null,null,"2017-09-19","2020-03-26"]
[3278,680062,"L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23",1,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-151043","-","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3282,680264,"   Perf. part: Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-Perf",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151110","RP-151237","Huawei",null,"follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Stat Rep: -->RP-1512371/1/16: Compl:0%->100% ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3283,710069,"   UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161681","-","Huawei",null,"testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16",null,71,36,null,null,"2016-03-22","2016-09-26"]
[3287,680167,"   Core part: RAN sharing enhancements for UMTS","RSE_UTRA_GUSH-Core",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151251","RP-151239","Huawei",null,"no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE¦29/09/15: Compl:0%->30% 29/09/15: WID: RP-151086->RP-151251 29/09/15: Stat Rep: -->RP-151239 ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3290,750051,"   UE Conformance Test Aspects - Interference Mitigation for Downlink Control Channels of LTE","LTE_IM_DLCCH-UEConTest",2,"Rel-13","R5","2017-03-15","2018-09-14",1,"RP-180176",null,"Intel",null,"tested: REL-13 LTE_IM_DLCCH-Perf (note: WI had no Core part);19/6/171 8/1/18: C 27/3/18 ;¦26/3/19: 84%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[3293,690064,"Dual Carrier HSUPA Enhancements for UTRAN CS","DC_HSUPA_CS",1,"Rel-13","R2","2015-09-15","2015-12-15",1,"RP-151607","-","Nokia Networks",null,"no Perf. part¦compare REL-13 WI HSUPA_DB_MC",null,69,35,null,null,"2015-09-29","NA"]
[3296,670042,"   Study on further Enhancements of Minimization of Drive Tests for E-UTRAN","FS_LTE_eMDT2",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-150472","RP-151181","CMCC",null,"03/07/15: Compl:0%->70% 03/07/15: Stat Rep: -->RP-150806 29/09/15: Compl:70%->100% 29/09/15: Stat Rep: RP-150806->RP-151181",36.880000000000003,67,34,null,null,"2015-04-01","2015-09-29"]
[3299,690066,"LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy",1,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-151615","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio",null,69,35,null,null,"2015-09-29","NA"]
[3300,690166,"   Core part: LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy-Core",2,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-160608","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio1/1/16: Compl:0%->95% 22/3/16: Compl:95%->100%¦28/7/16: 36.361 added;",36.360999999999997,69,35,null,null,"2015-09-29","2016-07-28"]
[3303,690267,"   Perf. part: Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh-Perf",2,"Rel-13","R4","2015-09-15","2016-06-15",1,"RP-160332","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh 1/1/16: Compl:0%->10% 1/1/16: WID: RP-151624->RP-152251¦22/3/16: Compl:10%->20%¦22/3/16: WID: RP-152251->RP-160332 28/7/16: 37.171 added¦28/7/16: 37.958 added;","37.171; 37.958",69,35,null,null,"2015-09-29","2016-07-28"]
[3306,720099,"   UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS","UTRA_LTE_iPos_enh-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-170233",null,"NextNav",null,"tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl:",null,72,37,null,null,"2016-07-01","2017-03-21"]
[3309,700256,"   Perf. Part: Power saving enhancements for UMTS","UTRA_SDATA_POWSAV-Perf",2,"Rel-13","R4","2015-12-15","2016-03-15",1,"RP-151998",null,"Ericsson",null,"¦22/3/16: Compl:0%->100%",null,70,36,null,null,"2016-01-01","2016-03-22"]
[3312,680273,"   Perf. part: 700MHz E-UTRA FDD Band for Arab Region","LTE_FDD_700_ARAB-Perf",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151042","RP-151207","Etisalat",null,"REL-independent from REL-9 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13 ",null,68,35,null,null,"2015-07-03","2016-03-22"]
[3316,0,"Release 13 Features on Internet of Things (IoT)","-",1,"Rel-13","SP,RP,CP,GP","2013-09-12","2015-05-12",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[3317,620063,"Service Requirements Maintenance for Machine-Type Communications (MTC)","SRMMTC",1,"Rel-13","S1","2015-09-15","2016-06-10",1,"SP-130600","-","KPN","toon.norp@tno.nl","SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13.",22.367999999999999,62,32,null,null,"2013-11-26","2014-09-03"]
[3321,700013,"   CT aspects of CIoT","CIoT-CT",2,"Rel-13","C1","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","11/6/16: WID:CP-150795->CP-160292",null,70,36,null,null,"2015-12-07","2016-06-11"]
[3322,700014,"      CT1 aspects of CIoT","CIoT-CT",3,"Rel-13","C1","2015-12-07","2016-03-11",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->35¦11/6/16: 35%->100¦11/6/16: WID:CP-150795->CP-160292","24.301, 24.008, 23.122",70,36,null,null,"2015-12-07","2016-06-11"]
[3325,700052,"      CT6 aspects of CIoT","CIoT-CT",3,"Rel-13","C6","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","11/6/16: WID:CP-150795->CP-160292¦13/6/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-06-13"]
[3328,690163,"      Core part: Narrowband Internet of Things (IOT)","NB_IOT-Core",3,"Rel-13","R1","2015-09-15","2016-06-15",1,"RP-160933","-","Vodafone",null,"no Perf. part¦note: WI only stays in REL-13 because of PCG decision1/1/16: Compl:0%->25% 22/3/16: Compl:25%->75%;1/7/16: Com",36.802,69,35,null,null,"2015-09-29","2016-07-01"]
[3332,690006,"Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things","CIoT_EC_GSM",1,"Rel-13","G1,G2","2015-09-25","2016-09-15",0.69,"GP-151039",null,"Marteen Sunberg, Ericsson","Marteen.Sunberg@Ericsson.com","7/12/15: 0%->60",null,69,35,null,null,"2015-09-07","2015-12-07"]
[3334,700004,"   Test for CIoT_EC_GSM","CIoT_EC_GSM_GERAN3new",2,"Rel-13","G3","2015-11-11","2016-05-12",0,"GP-151149",null,"Sierra Wireless S.A","Marteen.Sunberg@Ericsson.com","7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new",null,70,36,null,null,"2015-09-07","2016-03-02"]
[3338,660008,"   Study on Extended DRX cycle for Power Consumption Optimization","FS_eDRX",2,"Rel-13","S2","2014-12-03","2015-12-11",1,"SP-140881",null,"Miguel Griot, Qualcomm ","mgriot@qti.qualcomm.com","No Ran aspects yet. GERAN in FS_uPoD.29/1: TS number added Mar15: 0->30%¦June2015: Compl:30%->95, Exc S granted in SP-150352¦07/09/15: 95%->100",23.77,66,34,null,null,"2014-12-03","2015-09-07"]
[3341,690020,"      CT1 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100","24.301, 24.008, 29.118",69,35,null,null,"2015-09-07","2016-03-07"]
[3343,690021,"      CT4 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C4","2015-09-07","2015-12-17",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 40%->100¦8/12/15: 100%->95¦8/3/16: 95%->100",29.212,69,35,null,null,"2015-09-07","2016-03-08"]
[3344,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[3347,710071,"   UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE","LTE_extDRX-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-160602","-","Qualcomm",null,"testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT;",null,71,36,null,null,"2016-03-22","2016-09-26"]
[3351,670027,"Optimizations to Support High Latency Communications","HLcom",1,"Rel-13","S2","2014-09-19","2015-12-16",1,"SP-150030",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com",null,"23.401, 23.060, 23.682",67,34,null,null,"2015-03-05","2015-03-05"]
[3354,680015,"   CT aspects of Optimizations to Support High Latency","HLcom-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150399",null,"Yong Yang, Ericsson","frank.yong.yang@ericsson.com","07/09/15: 0%->80¦7/12/15: 80%->100","29.274, 29.060, 29.281, 23.008, 29.272, 29.230, 29.002, 29.336, 29.xyz",68,35,null,null,"2015-06-15","2015-12-07"]
[3356,650133,"   Core part: Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-Core",2,"Rel-13","R1,R2,R4","2014-09-12","2016-03-15",1,"RP-150492","RP-151186","Ericsson","johan.bergman@ericsson.com","3/3/15: WID: RP-141865¦Stat Rep: -->RP-141785 1st Apr 15: Compl:10%->25% 1st Apr 15: WID: RP-141865->RP-150492 1st Apr 15: Stat Rep: RP-141785->RP-150495 03/07/15: Compl:25%->45% 03/07/15: Stat Rep: RP-150495->RP-150583 29/09/15: Compl:45%->65% 29/09/","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.302, 36.306, 36.321, 36.331",65,33,null,null,"2014-06-16","2016-03-22"]
[3360,640050,"Group based Enhancements","GROUPE",1,"Rel-13","S2,S3","2014-06-18","2015-12-16",1,"SP-140706","-","Huawei","ZhangWanqiang@huawei.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[3363,640350,"   TR on Security for Group based Enhancements","GROUPE",2,"Rel-13","S3","2014-06-18","2015-06-12",1,"SP-140706","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. 3/3/15: 5->10%.¦June2015: Compl:10%->60¦11/12/15: 60%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[3366,680028,"      CT1 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->15¦7/12/15: 15%->100¦7/12/15: WID:CP-150240->CP-150816","24.008, 24.301",68,35,null,null,"2015-06-15","2015-12-07"]
[3367,680029,"      DELETED: CT3 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","7/12/15: WID:CP-150240->CP-150816. CT3 task removed",29.468,68,35,null,null,"2015-06-15","2015-12-07"]
[3369,640049,"Monitoring Enhancements","MONTE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140705","-","Intel","puneet.jain@intel.com","Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added;",32.277999999999999,64,33,null,null,"2014-05-30","2015-10-05"]
[3373,640449,"   Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[3376,680025,"      CT1 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->95¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 95%->100","24.301, 24.008",68,35,null,null,"2015-06-15","2015-12-07"]
[3378,680027,"      CT4 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","61907/09/15: 0%->50¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 50%->85. FCD -> 03/16, ES in CP-150619¦7/3/16: 85%->100","New 29.128, 29.272, 29.002, 29.336, 29.230, 23.008",68,35,null,null,"2015-06-15","2016-03-07"]
[3382,690004,"   CT aspects of Dedicated Core Networks","DECOR-CT",2,"Rel-13","ct","2015-06-25","2016-03-11",1,"CP-150423",null,"Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com)","Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com)",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[3385,680066,"   Dedicated Core Networks RAN Aspects","DECOR-UTRA_LTE",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151048","-","Ericsson",null,"no Perf. part¦note: DECOR is a REL-13 SA2 WI;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3388,610130,"   TR on Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-06-18",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements)","New 22.853",61,31,null,null,"2013-08-26","2014-05-27"]
[3389,610230,"   Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-09-17",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#65 completed","22.101, 22.115, 22.368, TBD",61,31,null,null,"2013-08-26","2014-08-28"]
[3393,640348,"   TR on Security for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S3","2014-06-23","2015-06-17",1,"SP-140704","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. Dec.14: 0->40%. 3/3/15: 45%.¦June2015: Compl:45%->60¦11/12/15: 60%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[3395,680001,"   CT aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","14/09/15: WID:CP-150402->CP-150487->CP-150576",null,68,35,null,null,"2015-06-15","2015-09-14"]
[3398,621000,"Rel-13 LTE Carrier Aggregation","LTE_CA_Rel13",1,"Rel-13","R4","2013-12-09","2018-12-14",0.95,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,62,32,null,null,"2012-12-14","2015-01-15"]
[3401,690280,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3404,690281,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3407,620223,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27","LTE_CA_B8_B27-Perf",3,"Rel-13","R4","2013-12-09","2015-12-15",0.3,"RP-140120","RP-151131","KT","ilwhan.kim@kt.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.141, 36.307",62,32,null,null,"2013-12-07","2015-09-29"]
[3408,620032,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27",2,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[3411,630033,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22",2,"Rel-13","R4","2014-03-06","2015-06-15",1,"RP-140094","-","Orange, Ericsson","erika.tejedor@ericsson.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[3414,640022,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12",2,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","-","U.S. Cellular","sebastian.thalanany@uscellular.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-21"]
[3417,640025,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140692","-","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[3420,640032,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140974","-","Huawei","leo.liuye@huawei.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[3423,650037,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38","LTE_CA_B3_B38",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141129","-","Nokia Networks","iwajlo.angelow@nsn.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3427,650138,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3428,650238,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3430,650139,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->35%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3433,650140,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40-Core",3,"Rel-13","R4","2014-09-12","2015-12-15",1,"RP-141168","RP-151131","Ericsson","imadur.rahman@ericsson.com","CD:Wed 11/03/15->Sun 15/03/15¦Compl:0%->30%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:30%->70% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2016-01-01"]
[3436,650141,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40-Core",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","RP-151131","KT","ilwhan.kim@kt.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2016-01-01"]
[3439,650142,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150832","RP-150536","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3442,650143,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-142007","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","¦WID: RP-142043->RP-142007¦Stat Rep: -->RP-141732 1st Apr 15: Compl:75%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3446,650244,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3449,650245,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3452,650247,"      Perf. Part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_C_B42_3DL-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-151027","RP-150536","CATT","Yuexia Song (songyuexia@catt.cn)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Stat ","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3454,650149,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141845","RP-150536","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3455,650249,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41-Perf",3,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141845","RP-150536","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3458,650251,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3462,660072,"   LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C",2,"Rel-13",null,"2014-12-15","2018-09-14",1,"RP-142286",null,"Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13",null,66,34,null,null,"2015-01-12","2015-01-15"]
[3465,730074,"      UE Conformance Test Aspects - LTE Carrier Aggregation Enhancement Beyond 5 Carriers: PUCCH on Scell","LTE_CA_enh_b5C_PUCCH-UEConTest",3,"Rel-13","R5","2016-09-15","2018-09-14",1,"RP-192558",null,"Huawei",null,"¦20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%¦19/9/17: Compl:8%->15%¦8/1/18: 27/3/18; 14/1/20: WID:RP-171764->RP-192558; 14/1/20: 20%->100",null,73,37,null,null,"2016-09-26","2020-01-14"]
[3468,660280,"      Perf. part: HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-151852","RP-151281","Qualcomm","Qualcomm","1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Stat Rep: RP-150761->RP-1512811/1/16: Compl:0%->90% ¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3471,660281,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3474,660282,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3475,660083,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777",null,"China Unicom","China Unicom",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3478,660084,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141791",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3480,660284,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150639","RP-151131","NTT DOCOMO","NTT DOCOMO","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[3484,660086,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141802",null,"ZTE","ZTE",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3487,660087,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28",2,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-141826",null,"Softbank Mobile","Softbank Mobile",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3489,660287,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3493,660089,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28","LTE_CA_B7_B7_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141882",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3496,660090,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141946",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3497,660190,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151258","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3500,660191,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151259","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3503,660192,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151261","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->95% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3506,660193,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->95% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3509,660194,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150719","RP-150536","Nokia Networks","Nokia Networks","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3513,660295,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3515,660196,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3518,660197,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->60% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3519,660297,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3522,660298,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-151071","RP-150536","Huawei","Huawei","03/07/15: Compl:0%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3526,661000,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3528,661200,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209","RP-151131","Huawei","Huawei","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3531,661201,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238","RP-150536","Intel","Intel","03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3535,661003,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142198",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3538,661004,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142199",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3539,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3541,661005,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142200",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3544,661006,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142201",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3548,661107,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150451","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[{"$f":"A3550+1","v":3550},661008,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142203",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3553,661009,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3557,661110,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150678","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3560,661111,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3561,661211,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3563,661112,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13","LTE_CA_2UL_R13-A3-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150409","RP-151131","Ericsson","Ericsson","1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3566,661113,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 15/03/16->Tue 15/12/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3570,670265,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150641","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3573,670266,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150642","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3576,670267,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150643","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3579,670268,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42","LTE_CA_B3_B19_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150644","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3582,670269,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3583,670070,"   Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3587,670171,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3588,670271,"      Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3592,670073,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3595,670074,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3599,670175,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12","LTE_CA_B2_B4_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150660","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3600,670275,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12","LTE_CA_B2_B4_B4_B12-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150660","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3604,670077,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150075",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3605,670177,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150658","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3608,670178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151216","RP-151131","SK Telecom",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3611,670179,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[{"$f":"A3614+1","v":3614},670180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3617,670181,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064","RP-151131","KDDI",null,"03/07/15: Compl:0%->70% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:70%->90% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3621,670282,"      Perf. Part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13","LTE_CA_2UL_R13-A4-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150616","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3622,670083,"   LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150479",null,"Nokia Corporation",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3626,670184,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246","RP-150536","Huawei",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3627,670284,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246","RP-150536","Huawei",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3630,670285,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151177","RP-151131","CMCC",null,"03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3633,670286,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438","RP-151131","CATT",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3637,680078,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32",2,"Rel-13","R4","2015-06-15","2016-03-15",0.9,"RP-150864","-","Ericsson",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3639,680278,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32-Perf",3,"Rel-14","R4","2015-06-15","2016-03-15",0.9,"RP-150864","RP-151131","Ericsson",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->90%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[3643,680080,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3646,680081,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","-","Nokia Networks",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3648,680281,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","RP-151131","Nokia Networks",null,"29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-151131¦1/1/16: Comp",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3649,680082,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","-","KDDI",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3652,680083,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151112","-","KDDI",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3656,680185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","RP-151131","Rogers Communications",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[3659,680186,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3661,680087,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3665,680188,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3668,680189,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3671,680190,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3672,680290,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3674,680191,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[{"$f":"A3678+1","v":3678},680292,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3681,680293,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3683,680194,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3687,680295,"      Perf. part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3690,680296,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[3693,680297,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[3694,680098,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3698,681100,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3700,681001,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3703,681002,"   LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra",2,"Rel-14","R4","2015-06-15","2015-12-15",1,"RP-150817","-","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL whi",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3706,681003,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","-","Intel",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3709,681004,"   Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","-","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3712,681005,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","-","Intel",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[3713,681105,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3716,681106,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_NC_B42_4DL-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151102","RP-151131","Huawei",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3719,680174,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","RP-151131","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[3722,680176,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","RP-151131","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[3725,680172,"      Core part: Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151037","RP-151242","Huawei",null,"Aug 15: TR numb added 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151242",36.892000000000003,68,35,null,null,"2015-07-03","2016-01-01"]
[3728,680084,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42","LTE_CA_B41_B41_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150627",null,"ZTE",null,null,null,68,35,null,null,"2015-08-12","2015-08-12"]
[3732,690173,"      Core part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3733,690273,"      Perf. part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3735,690174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3738,690175,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40","LTE_CA_B5_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151200","-","ZTE",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3741,690176,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3744,690177,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 ","LTE_CA_B3_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151448","-","ZTE",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3747,690178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3751,690279,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3754,690282,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,1,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3757,690283,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40","LTE_CA_B3_B28_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151363","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3759,690184,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3760,690284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3763,690285,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[3767,690090,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","NA"]
[3770,690091,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151512","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[3773,690092,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151513","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[3776,690093,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","NA"]
[3779,690094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case¦5/10/15: 36.899-13 added;","36.899-13",69,35,null,null,"2015-09-29","2015-10-05"]
[3780,690194,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3783,690195,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12 ¦",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3785,700065,"   UE Conformance Test Aspects - Rel-13 LTE CA configurations","LTE_CA_Rel13-UEConTest",2,"Rel-13","R5","2015-12-15","2018-12-14",1,"RP-161553",null,"Ericsson",null,"¦22/3/16: Compl:0%->5%;1/7/16: Compl:5%->22%26/9/16: Compl:22%->¦2 21/3/17: Compl:39% ;; 14/1/20: 62%->100",null,70,36,null,null,"2016-01-01","2020-01-14"]
[3789,690007,"(Small) Security Enhancements and Improvements for Rel-13","SEC13",1,"Rel-13","S3","2006-12-12","2015-12-21",1,"-","PCG-31","-","-","-","-",61,31,null,null,"2015-01-12","2013-09-14"]
[3792,640001,"Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things","FS_IoT_LC",1,"Rel-13","G1,G2","2014-05-30","2015-08-28",1,"GP-150354","-","Vodafone","chris.pudney@vodafone.com","GP#62 approved WID. Dec.14: 15->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100¦14/09/15: WID:GP-140421->GP-150354","45.8xy",66,33,null,null,"2014-05-30","2015-09-14"]
[3794,670036,"Study on Battery Efficient Security for very low Throughput Machine Type Communication Devices","FS_BEST_MTC_Sec",1,"Rel-13","S3","2015-03-13","2015-12-11",1,"SP-150171",null,"Barry, Aguibou, VODAFONE Group Plc","Barry, Aguibou, VODAFONE Group Plc","TR number added¦June2015: Compl:0%->10¦7/12/15: 10%->50¦11/12/15: 50%->75¦7/3/16: 75%->95¦19/9/16: 95%->100¦6/10/16: 33.163 added;","32.863; 33.163",67,34,null,null,"2015-03-13","2016-10-06"]
[3798,0,"Release 13 other Studies","-",1,"Rel-13","SP,R2","2013-09-12","2015-12-25",1,"-","-","-","-","-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[3801,670095,"Study on Security Aspects of Isolated E-UTRAN Operation for Public Safety","FS_IOPS_Sec",1,"Rel-13","S3","2015-03-12","2015-09-18",1,"SP-150074",null,"Paul Piggin, General Dynamics UK","paul.piggin@gd-broadband.com","TR added¦June2015: Compl:0%->30¦7/12/15: 30%->100","New 33.897",67,34,null,null,"2015-04-02","2015-12-07"]
[3802,610033,"(SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO","FS_CSIPTO",1,"Rel-13","S1","2013-09-13","2014-06-18",1,"SP-130417","-","Intel","Eric.siow@intel.com","SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET",22.827999999999999,61,31,null,null,"2013-08-26","2014-12-12"]
[3805,630017,"Study on RAN Sharing Enhancements on GERAN and UTRAN","FS_GUSH",1,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-140073","-","Telefónica","chris.friel@telefonica.com","SP#65 completed. Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","22.852 updates",63,32,null,null,"2014-02-05","2014-08-29"]
[3808,520135,"   SA2 part of Study on Usage Monitoring Control PCC Enhancement","FS_UMONC_sas",2,"Rel-13","S2","2013-06-14","2014-12-12",1,"SP-150029","-","China Telecom","Jinyan Li (lijy@ctbri.com.cn)","SP#64 revived. Updated WID SP-120554=>SP-140403. Changed Justification/objectives/Rapporteut ZTE=>China Unciom. SP#58 SA2 stopped (at 70% completion). Dec.14: 80->100%. Mar 15: WID SP-140403->SP-150029",23.858000000000001,52,27,null,null,"2011-05-19","2015-03-05"]
[3811,610043,"Study on Subscriber Privacy Impact in 3GPP","FS_SPI",1,"Rel-13","S3","2013-09-17","2015-12-16",1,"SP-130399","-","China Unicom","Feng Gao (gaofeng149@chinaunicom.cn)","SP#65 moved to Rel-13. Completion 09/14=>12/15. Related to SA1 TR 22.949 Rel-6 Study on Privacy Capability (PrivCap) UID_31030 studied generalized privacy capability (protection of personal data and non-disclosure of identity). Dec.14: 80->85¦June2015",33.848999999999997,61,31,null,null,"2013-09-03","2016-03-07"]
[3814,620060,"Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks","FS_REVOLTE_IMS_CH",1,"Rel-13","S5","2013-12-17","2015-06-12",1,"SP-130609","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","SP#64 moved to Rel-13. Completion 06/14=>12/14. Dec.14: 35->55, CD: 12/14->06/15. Mar 15: 55->75%¦June2015: Compl:75%->100",32.848999999999997,62,32,null,null,"2013-11-28","2015-06-15"]
[3818,590034,"Study on Downlink MIMO","FS_DOMIMO",1,"Rel-13","G1,G2","2014-08-14","2016-05-12",1,"GP-130288","-","Nokia Networks","juergen.hofmann@nokia.com","GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID. Dec.14: 50->65%, CD: 02/15->05/15. 7/9/15: FCD: 11/15->02/16¦2/3/16: 65%->75, FCD: 02/16->05/16¦11/9/17: 75%->100","45.8xy",57,30,null,null,"2013-03-04","2017-09-11"]
[3820,620013,"Stopped at 20% - Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO)","FS_UL_MU_MIMO",1,"Rel-13","G1,G2","2014-04-17","2016-02-19",1,"GP-131131","-","Huawei","Chao Luo (chluo@huawei.com)","GP#62 completion 11/14=>02/15. GP#60 approved WID. Dec.14: 02/15->05/15. 02/03/16: stopped at 20%",45.875999999999998,60,32,"SP#71",null,"2013-11-22","2014-12-03"]
[3823,620045,"Study on Multi-RAT joint coordination","FS_MultiRAT_JC",1,"Rel-13","R4","2013-12-06","2015-06-15",1,"RP-150417","RP-150807","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","¦WID: RP-142043->RP-132086¦Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807","UTRA, LTE 37.870",62,32,null,null,"2013-11-27","2015-06-18"]
[3824,640016,"Study on Advanced Wireless Services (AWS) - Extension band for LTE","FS_LTE_AWS_EXT",1,"Rel-13","R4","2013-12-16","2014-12-15",1,"RP-141037","RP-141968","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141429->RP-141968. 5/5/15: 2nd TR number added (to be clarified why two TR for a same topic)","36.849, 36.869",64,33,null,null,"2014-06-16","2015-05-05"]
[3827,650015,"Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","FS_LTE_EBF_FDMIMO",1,"Rel-13","R1","2014-09-12","2015-06-15",1,"RP-150930","RP-150734","Nokia Networks (DL), Samsung (UL)","bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com","3/3/15: WID: RP-141831¦Stat Rep: -->RP-141822, impacted TR number added. 1st Apr 15: Compl:30%->45% 1st Apr 15: Stat Rep: RP-141822->RP-150346. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake) 03/07/15: Compl:45%->100% 03/07/15: WID: RP-141831->RP-1",36.896999999999998,65,33,null,null,"2014-09-15","2015-06-18"]
[3831,660063,"Study on possible additional configuration for LTE TDD","FS_LTE_TDD_add_config",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150652","RP-151283","NTT DOCOMO, Hideaki Takahashi","NTT DOCOMO","TR 36.825 rapporteur: CATT. TR number added. 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150151 03/07/15: Compl:5%->35% 03/07/15: WID: RP-142248->RP-150652 03/07/15: Stat Rep: RP-150151->RP-150805 29/09/15: Compl:35%->100% 29/09/15: Stat Rep: R",36.825000000000003,66,34,null,null,"2015-01-12","2015-09-29"]
[3833,660065,"Study on Enhanced Multiuser Transmissions and Network Assisted Interference Cancellation for LTE","FS_LTE_MUTX_NAIC",1,"Rel-13","R1","2014-12-15","2015-03-15",0,"RP-142315","RP-150213","MediaTek","MediaTek","1st Apr 15: CD:Tue 15/12/15->Sun 15/03/15 1st Apr 15: Stat Rep: ->RP-150213. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake)",null,66,34,null,null,"2015-01-12","2015-05-05"]
[3836,660068,"Study on further enhancements of small cell higher layer aspects for LTE","FS_LTE_SC_enh2_hilayer",1,"Rel-13","R3","2014-12-15","2015-09-15",1,"RP-142283","RP-151243","Huawei","Huawei","03/07/15: Compl:10%->30% 03/07/15: Stat Rep: RP-150226->RP-150683 29/09/15: Compl:30%->100% 29/09/15: Stat Rep: RP-150683->RP-151243. 7/10/15: responsible group corrected (R4->R3) and TS (37.876->36.876)",36.875999999999998,66,34,null,null,"2015-01-12","2015-10-07"]
[3840,660061,"Study on Enhanced Multiuser Transmissions and Network","FS_MUIC_LTE",1,"Rel-13","R1","2014-12-12","2015-12-11",0,"RP-142315",null,"Pei-Kai Liao","pk.liao@mediatek.com","TR added",36.890999999999998,67,34,null,null,"2014-12-12","2015-01-29"]
[3843,670044,"Study on Measurement gap enhancement for LTE","FS_LTE_meas_gap",1,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150515","RP-151317",null,null,"03/07/15: Compl:0%->15% 03/07/15: CD:Thu 10/12/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150754 03/07/15: Release: REL-13->Rel-13. Aug 15: TR numb added 29/09/15: Compl:15%->65% 29/09/15: Stat Rep: RP-150754->RP-151317",36.893999999999998,67,34,null,null,"2015-05-11","2016-01-01"]
[3844,670087,"Study on Phase 1 of the Support of Emergency services over WLAN","FS_SEW",1,"Rel-13","S2","2015-03-12","2015-06-18",1,"SP-150251",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251","new 23.771",67,34,null,null,"2015-04-01","2015-06-18"]
[3846,680013,"Study on SCC AS Restoration","FS_SCCAS_RES",1,"Rel-13","C4","2015-06-15","2015-06-15",1,"CP-150398",null,"Hao Zhang,, China Mobile","zhanghao@chinamobile.com","07/09/15: 5%->20¦7/12/15: 20%->100","New 29.812",68,35,null,null,"2015-06-15","2015-12-07"]
[3849,680056,"Study onLTE Advanced inter-band Carrier Aggregation of Band 20 and Band 28","FS_LTE_CA_B20_B28",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151515","RP-151231","TeliaSonera",null,"29/09/15: Compl:0%->20% 29/09/15: WID: RP-151101->RP-151515 29/09/15: Stat Rep: -->RP-151231 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3853,560435,"Stopped - Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR","FS_OAM_NGMN_NGCOR",1,"Rel-13","S5","2012-06-26","2017-12-15",1,"SP-140787","-","Huawei","zoulan@huawei.com","SP#65 updated WID SP-140349=>SP-140539. Dec.14: 35->45, 12/14: 28.821 added. Mar 15: 45->50%¦June2015: Compl:50%->60. 07/09/15: FCD: 09/15->12/15¦7/12/15: FCD:12/15->03/16¦21/3/17:marked as stopped, was 60%","32.837, 28.821",56,29,null,null,"2012-05-14","2017-03-21"]
[3855,0,"Stage 1 - ONLY Features","-",1,"Rel-12","SP,CP","2011-09-27","2014-03-05",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[3858,500031,"Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers","MOSAP",1,"Rel-12","S1,S2","2010-12-16","2013-12-11",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#58 Stage 2 stopped (TR only, no normative work done)","Stage 1",50,26,null,null,"2010-11-29","2012-11-22"]
[3862,520027,"IMS Network-Independent Public User Identities","INIPUI",1,"Rel-12","S1","2011-06-08","2012-06-20",1,"SP-120425","-","Vodafone","mona.mustapha@vodafone.com","Triggered by Rel-11 TR 22.894 (FS_INIPUI)","Stage 1",52,27,null,null,"2011-05-19","2012-06-19"]
[3865,530143,"   Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls","SMURFs-SA1",2,"Rel-12","S1","2011-09-21","2012-06-20",1,"SP-110653","-","Vodafone","mona.mustapha@vodafone.com","SP#56 completed",22.277999999999999,53,27,null,null,"2011-07-19","2012-06-08"]
[3866,550024,"Advanced IP Interconnection of Services (IPXS) for national interconnect","IPXSNAT",1,"Rel-12","S1","2012-03-06","2012-09-12",1,"SP-120428","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051.","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[{"$f":"A3870+1","v":3870},560019,"Explicit Communication Transfer Blind (ECT Blind) service interactions","ECTB",1,"Rel-12","S1","2012-06-18","2012-06-20",1,"SP-120301","-","Orange","philippe.lottin@orange.com","SP#56 WID approved & Stage 1 completed","Stage 1",56,29,null,null,"2012-05-14","2012-06-08"]
[3871,560119,"   Stage 1 for Explicit Communication Transfer Blind (ECT Blind) service interactions","ECTB-SA1",2,"Rel-12","S1","2012-06-18","2012-06-20",1,"SP-120301","-","Orange","philippe.lottin@orange.com","SP#56 new WID approved & work completed. Clarify the service interactions between ECT Blind and other MMTEL Supplementary Services",22.172999999999998,56,29,null,null,"2012-05-14","2012-06-08"]
[3875,580160,"   Stage 1 for Sequential Flexible Alerting","SEQ_FA",2,"Rel-12","S1","2012-12-10","2012-12-12",1,"SP-120895","-","Orange","bruno.tossou@orange-ftgroup.com","SP#58 approved WID & Stage 1 completed",22.172999999999998,58,30,null,null,"2012-11-16","2012-11-21"]
[3878,590040,"Emergency Session Identification","ESID",1,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130126","-","Telecom Italia","carmen.catalano@telecomitalia.it","SP#59 Stage 1 completed. ","Stage 1",59,30,null,null,"2013-02-19","2013-02-19"]
[3881,590141,"   Deleted - Stage 1 for Application and Service Access Control","ASAC-SA1del",2,"Rel-12","S1","2013-03-06","2013-06-19",1,"SP-130124","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster)",22.010999999999999,59,30,"SP-60","PCG-31","2013-02-19","2013-02-19"]
[3884,0,"SA1/SA2 Features","-",1,"Rel-12","SP,CP,RP","2013-05-17","2014-03-07",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[3887,500328,"   BB1: SIPTO at the Local Network","LIMONET-SIPTO",2,"Rel-12","S2","2010-10-22","2014-03-05",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#60 completed","23.060, 23.401",50,26,null,null,"2010-11-26","2013-06-06"]
[3888,501328,"      Stage 2 for SIPTO at the Local Network","LIMONET-SIPTO-SA2",3,"Rel-12","S2","2010-10-22","2013-06-19",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#60 completed","23.060, 23.401",50,26,null,null,"2010-11-26","2013-06-06"]
[3892,590020,"   RAN aspects for SIPTO at the Local Network","LIMONET-RAN",2,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","-","Huawei","zheng.zhou@huawei.com","-","UTRA, LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[3893,590120,"      Core part: RAN aspects for SIPTO at the Local Network","LIMONET-RAN-Core",3,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","RP-131512","Huawei","zheng.zhou@huawei.com","RP#62 completed","25.401, 25.413, 25.423, 25.467, 25.469, 36.300, 36.413, 36.423",59,30,null,null,"2013-02-26","2013-11-29"]
[3897,530116,"         Deleted - CT1 part of CN aspects of LIPA Mobility","LIMONET-LIPA-del3",4,"Rel-12","C1","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","24.008, 24.301",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[3900,510149,"   TR on Stage 2 for Operator Policies for IP Interface Selection","OPIIS",2,"Rel-12","S2","2011-03-23","2012-12-12",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","SP#58 completed","new 23.853",51,26,null,null,"2011-02-21","2012-12-10"]
[3904,520129,"   TR on Stage 2 for SMS submit and delivery without MSISDN in IMS","SMSMI-SA2TR",2,"Rel-12","S2","2011-06-08","2012-12-12",1,"SP-120321","-","Nokia Siemens Networks","curt.wong@nsn.com","SP#58 completed","new 23.863",52,27,null,null,"2011-05-26","2012-11-22"]
[3905,520229,"   Stage 2 for SMS submit and delivery without MSISDN in IMS","SMSMI-SA2",2,"Rel-12","S2","2011-06-13","2012-12-12",1,"SP-120321","-","Nokia Siemens Networks","curt.wong@nsn.com","SP#58 completed","23.204, 23.682",52,27,null,null,"2011-05-26","2012-06-09"]
[3909,530042,"IMS-based Telepresence","IMS_TELEP",1,"Rel-12","S1,C1,C3,C4,IETF","2010-03-22","2014-12-09",0.93,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified","Stage 1/2/3",53,27,null,null,"2011-07-19","2012-06-08"]
[3910,530142,"   Stage 1 for IMS-based Telepresence","IMS_TELEP",2,"Rel-12","S1","2011-09-22","2012-06-20",1,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","SP#56 completed. 2/4/15: acronym changed to IMS_TELEP",22.228000000000002,53,27,null,null,"2011-07-19","2015-04-02"]
[3913,580003,"      CT1 part of IMS Telepresence (Stage 3)","IMS_TELEP",3,"Rel-12","C1","2012-12-07","2014-12-09",1,"CP-140624","CP-140616","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 TS 24.103v100 for Information. Updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140616. Dec.14: 90->100%. 2/4/15: acronym changed to IMS_TELEP","24.147, 24.166, 24.229, New 24.103",58,30,null,null,"2012-11-19","2015-04-02"]
[3916,641003,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",0.9,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-datachannel); 9/4/21: RFC 8850 added;","draft-ietf-clue-datachannel; RFC 8850",64,33,null,null,"2014-06-06","2021-04-09"]
[3919,580004,"      CT3 part of IMS Telepresence (Stage 3)","IMS_TELEP",3,"Rel-12","C3","2012-12-07","2014-09-11",1,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 completed. 2/4/15: acronym changed to IMS_TELEP",29.164999999999999,58,30,null,null,"2012-11-19","2015-04-02"]
[3922,560120,"   Stage 1 for Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S1","2012-06-18","2013-06-19",1,"SP-140433","-","Nokia Networks","Juergen.Merkel@nsn.com","SP#60 completed. TS 22.468 v100 for 1-step Approval","New 22.468",56,29,null,null,"2012-05-14","2014-09-07"]
[3926,610035,"   Security for Group Communication System Enablers for LTE (Stage 2)","GCSE_LTE",2,"Rel-12","S3","2013-09-13","2014-06-18",1,"SP-140433","-","Nokia Networks","anja.jerichow@nsn.com","SP#64 completed",33.246000000000002,61,31,null,null,"2013-09-03","2014-09-07"]
[3929,640210,"      CT4 part of Group Communication System Enablers for LTE","GCSE_LTE-CT",3,"Rel-12","C4","2014-06-13","2014-12-09",1,"CP-140559","CP-140725","Nokia Networks","thomas.belling@nsn.com","CP#65 completion 09/14=>12/14. Exception in CP-140725. Dec.14: 35->100","23.007, 23.008",64,33,null,null,"2014-06-10","2014-12-04"]
[3931,640037,"   Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM",2,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","-","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","-","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[3932,640137,"      Core part: Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM-Core",3,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","RP-150081","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:25%->80%¦Stat Rep: RP-141327->RP-141863 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141863->RP-150081",36.412999999999997,64,33,null,null,"2014-06-16","2015-04-01"]
[3935,570030,"   Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance","MTCe-SRM",2,"Rel-12","S1","2012-09-13","2013-03-06",1,"SP-130105","-","KPN","toon.norp@tno.nl","SP#59 completed. Updated WID SP-120541=>SP-130105","22.101, 22.368",57,29,null,null,"2012-08-06","2013-02-19"]
[3938,560122,"   BB1: Small Data and Device Triggering Enhancements (SDDTE)","MTCe-SDDTE",2,"Rel-12","S2,C4,C3","2012-06-18","2014-09-11",1,"SP-120450","-","Intel","puneet.jain@intel.com ","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[3942,630101,"         CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement","MTCe-SDDTE-CT",4,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#65 completed. Updated WID CP-140272=>CP-140489","29.002, 29.336, 23.008, 29.337, 29.338, 29.230",63,32,null,null,"2014-01-29","2014-07-29"]
[3944,560222,"   Deleted - BB2: Monitoring Enhancements (MONTE)","MTCe-MONTE",2,"Rel-12","S2","2012-06-18","2012-12-12",1,"SP-120438","-","Intel","puneet.jain@intel.com ","SP#58 stopped (at 20% completion)",23.681999999999999,56,29,"SP-58","PCG-30","2012-04-13","2012-12-14"]
[3948,620007,"      Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT",3,"Rel-12",null,"2013-12-06","2016-03-15",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","-","Stage 3",62,32,null,null,"2013-11-18","2013-11-18"]
[3951,620307,"         CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT6",4,"Rel-12","C6","2013-12-09","2014-12-09",1,"CP-130714","CP-140697","Ericsson","mikael.wass@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140697¦June2015: Compl:90%->100","31.101, 31.102, 31.111",62,32,null,null,"2013-11-18","2015-06-15"]
[3953,650009,"      Support of Power Saving Mode in GERAN","MTCe-UEPCOP-GERAN",3,"Rel-12","G1","2014-08-25","2014-08-29",1,"GP-140628",null,"Ericsson","sajal.kumar.das@ericsson.com","GP#63 approved WID and completed",43.021999999999998,63,33,null,null,"2014-08-29","2014-08-29"]
[3954,700005,"      Testing of Support of Power Saving Mode in GERAN","MTCe-UEPCOP_GERAN3new",3,"Rel-12","G3","2015-11-11","2016-05-12",0.1,"GP-151186",null,"Ericsson","sajal.kumar.das@ericsson.com","7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new¦2/3/16: 0%->10",null,70,36,null,null,"2014-08-29","2016-03-02"]
[3957,620143,"      Core part: RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN-Core",3,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","RP-141096","ZTE","sergio.parolari@zte.com.cn","RP#65 completed","25.300, 25.304, 25.413, 36.300, 36.304, 36.413, 36.423",62,32,null,null,"2013-12-07","2014-09-15"]
[3961,670048,"   UE Conformance Test Aspects - Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2016-12-15",1,"RP-160069",null,"Ericsson",null,"03/07/15: Compl:0%->13% 03/07/15: WID: RP-150135->RP-150838 03/07/15: Stat Rep: ->RP-150833 29/09/15: Compl:13%->25% 29/09/15: Stat Rep: RP-150833->RP-151165 ¦1/1/16: Compl:25%->70% ¦1/1/16: CD:Tue 15/12/15->Tue 15/03/16 ",null,67,34,null,null,"2015-04-01","2016-12-20"]
[3964,560124,"   BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F",2,"Rel-12","S2,S5,C3,C1,C4","2012-06-20","2014-12-12",1,"SP-120275","-","Huawei","marco.spini@huawei.com","-","-",56,29,null,null,"2012-06-04","2013-01-08"]
[3966,562124,"      Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F-SA2",3,"Rel-12","S2","2012-06-20","2013-12-11",1,"SP-120275","-","Huawei","marco.spini@huawei.com","SP#62 completed","23.139, 23.203",56,29,null,null,"2012-06-04","2013-11-28"]
[3970,620010,"         CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C4","2013-12-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed",29.273,62,32,null,null,"2013-11-19","2014-04-16"]
[3973,560224,"   BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI)","P4C-TI",2,"Rel-12","S2","2012-06-20","2013-06-19",1,"SP-120444","-","Alcatel-Lucent","konstantin.livanos@alcatel-lucent.com","-","-",56,29,null,null,"2012-06-04","2013-01-08"]
[3976,560324,"   Deleted - BB3: Policy and Charging Control for 3GPP UEs connected to fixed broadband access network via S2b and S2c reference points for EPC routed traffic (P4C-S2bc)","P4C-S2bc",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120445","-","ZTE","Tricci So (tso@zteusa.com)","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[3977,560424,"   Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB)","P4C-HeNB",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120278","-","NEC","Stefan.Schmid@neclab.eu","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[3979,560624,"   Deleted - BB6: Policy and Charging Control for 3GPP UEs connected to fixed broadband access networks via S2a reference point for EPC routed traffic in convergence (P4C-TC)","P4C-TC",2,"Rel-12","S2","2012-06-20","2012-12-12",1,"SP-120280","-","ZTE","Tricci So (tso@zteusa.com)","SP#58 stopped (at 30% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[3983,560225,"   Stage 2 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA2",2,"Rel-12","S2","2012-06-25","2013-06-19",1,"SP-120862","-","Deutsche Telekom","michele.zarri@telekom.com","SP#60 completed",23.228000000000002,56,29,null,null,"2012-05-11","2013-06-06"]
[3986,610207,"      CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",3,"Rel-12","C3","2013-09-06","2014-06-11",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","CP#64 completed",29.164999999999999,61,31,null,null,"2013-08-10","2014-04-16"]
[3989,560226,"   Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SA2",2,"Rel-12","S2","2012-06-22","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","23.402, 23.865",56,29,null,null,"2012-11-22","2013-11-28"]
[3992,570028,"Deleted - IMS Registration Control","IMS_RegCon",1,"Rel-12","S1,S2,C1,C4","2012-01-31","2013-12-11",1,"SP-120735","-","China Mobile","lulu@chinamobile.com","SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information)","Stage 1/2/3",57,29,"SP-62","PCG-32","2012-08-06","2013-12-10"]
[3995,600016,"   Deleted - CT aspects of IMS registration control","IMS_RegCon-CT",2,"Rel-12","C1,C4","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","Stage 2/3",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[3996,600116,"      Deleted - CT1 aspects of CT aspects of IMS registration control (Stage 2/3)","IMS_RegCon-CT1",3,"Rel-12","C1","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","23.218, 24.229",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[3999,580159,"   Stage 1 for Proximity-based Services","ProSe-SA1",2,"Rel-12","S1","2012-12-13","2013-06-19",1,"SP-140574","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#60 completed","22.115, 22.278",58,30,null,null,"2012-11-16","2014-09-15"]
[4003,651104,"   (IETF) Security for Proximity-based Services (ietf-avtcore-srtp-aes-gcm)","ProSe",2,"Rel-12","S3-IETF","2014-09-12","2014-12-09",1,"SP-140574","-","Atle Monrad","atle.monrad@ericsson.com","Submitted to IESG for publication¦7/3/16: 75%->100; 9/4/21: RFC 7714 added;","RFC 7714 (was ietf-avtcore-srtp-aes-gcm); RFC 7714",65,33,null,null,"2014-09-15","2021-04-09"]
[4005,640139,"      Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use","ProSe-CH-SA5TR",3,"Rel-12","S5","2014-06-19","2014-12-12",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100%","New 32.844",64,33,null,null,"2014-06-06","2014-12-12"]
[4008,630106,"      CT1 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140290","CP-140615","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100%","24.301, 23.122, New TSs (24.333, 24.334)",63,32,null,null,"2014-01-29","2014-12-04"]
[4011,630406,"      CT6 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C6","2014-03-06","2014-12-09",1,"CP-140290","CP-140695","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140695. Dec.14: 60->100%",31.102,63,32,null,null,"2014-01-29","2014-12-03"]
[4014,630230,"      Perf. part: LTE Device to Device Proximity Services","LTE_D2D_Prox-Perf",3,"Rel-12","R4","2014-03-11","2015-12-15",1,"RP-142043","RP-151276","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","¦CD:Sat 15/03/14->Sun 15/03/15¦Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:10%->25% 1st Apr 15: Stat Rep: RP-141894->RP-150094 03/07/15: Compl:25%->70% 03/07/15: Stat Rep: RP-150094->RP-150760 29/09/15: Compl:70%->95% 29/09/15: CD:Tue 15/09/15->","36.101, 36.133",63,32,null,null,"2014-03-10","2016-01-01"]
[4017,580162,"   Stage 1 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S1","2012-12-14","2013-06-19",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","SP#60 completed","22.101, 22.228",58,30,null,null,"2012-11-16","2013-09-09"]
[4018,600040,"   TR on Stage 2 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S2","2013-06-19","2013-12-11",1,"SP-130707","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#62 completed. TR 23.701v100 for Information & Approval","New 23.701",60,31,null,null,"2013-06-06","2013-09-09"]
[4021,880055,"   (IETF) WebRTC Data Channel Establishment Protocol (draft-ietf-rtcweb-data-protocol)","IMS_WebRTC",2,"Rel-12","C1-IETF","2013-06-25","2014-12-12",0.9,"CP-140192",null,null,null,"9/4/21: RFC 8832 added;","RFC 8832",88,45,null,null,"2020-06-26","2021-04-09"]
[4024,630003,"   CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT",2,"Rel-12","C1,C4,IETF","2014-03-05","2019-03-07",0.97,"CP-140192","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","-","Stage 3",63,32,null,null,"2014-01-29","2014-09-06"]
[4027,630103,"      CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT1",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140192","CP-140621","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. Dec.14: 70->90%. 3/3/15: 100% cpltd.","24.229, New 24.371",63,32,null,null,"2014-01-29","2015-03-03"]
[4030,651001,"      Deleted - (IETF) Web Real Time Communication access to IMS (draft-ietf-sipcore-sip-authn)","IMS_WebRTC-yusef",3,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress; 23/4/20: 25%->100","draft-yusef-sipcore-sip-oaut. Replaced by replaced by draft-ietf-sipcore-sip-token-authnz",65,33,null,null,"2014-09-02","2020-04-23"]
[4033,630203,"      CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT4",3,"Rel-12","C4","2014-03-05","2014-12-09",1,"CP-140192","CP-140732","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","CP#65 completion 09/14=>12/14. Exception in CP-140732. Dec.14: 30->80%. Mar. 15: 100%","23.334, 29.334",63,32,null,null,"2014-01-29","2015-03-04"]
[4037,590039,"Application Based Charging","ABC",1,"Rel-12","S2,S5,C3","2013-03-07","2014-06-18",1,"SP-130328","-","Allot","Alla Goldner (agoldner@allot.com)","Triggered by TR 23.800 Study on Application Based Charging (FS_ABC) UID_560038","Stage 2/3",59,30,null,null,"2013-02-21","2013-06-06"]
[4038,590139,"   Stage 2 for Application Based Charging","ABC-SA2",2,"Rel-12","S2","2013-03-07","2013-06-19",1,"SP-130328","-","Allot","Alla Goldner (agoldner@allot.com)","SP#60 completed",23.202999999999999,59,30,null,null,"2013-02-21","2013-07-25"]
[4040,600049,"   CT3 aspects of Application Based Charging (Stage 3)","ABC-CT3",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130353","-","Allot","Alla Goldner (agoldner@allot.com)","CP#62 completed","29.212, 29.213, 29.214, 29.215, 29.219",60,31,null,null,"2013-05-29","2013-10-21"]
[4043,610009,"   Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",2,"Rel-12","C1,C4","2013-09-09","2014-12-09",1,"CP-130715","-","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#62 updated WID CP-130580=>CP-130715","Stage 3",61,31,null,null,"2013-08-10","2013-11-28"]
[4046,610039,"Optimized Offloading to WLAN in 3GPP-RAT Mobility","WORM",1,"Rel-12","S2,C1","2013-09-12","2014-06-13",1,"SP-130392","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB)","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[4050,610140,"   Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-SA2",2,"Rel-12","S2","2013-09-12","2014-03-07",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","SP#63 completed","23.203, 23.228, 23.402",61,31,null,null,"2013-07-25","2014-02-04"]
[4053,620208,"      CT1 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C1","2013-12-09","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed",24.228999999999999,62,32,null,null,"2013-11-19","2014-07-28"]
[4056,620161,"   Stage 2 for Core Network Overload - User Location Information reporting improvement","CNO_ULI-SA2",2,"Rel-12","S2","2013-12-11","2014-03-07",1,"SP-130717","-","Alcatel-Lucent","nicolas.drevon@alcatel-lucent.com","SP#63 completed","23.060, 23.203, 23.401",62,32,null,null,"2013-11-28","2014-02-04"]
[4059,630104,"      CT3 part of CT aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CT",3,"Rel-12","C3","2014-03-05","2014-06-13",1,"CP-140093","-","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","CP#64 completed","29.212, 29.213",63,32,null,null,"2014-01-29","2014-06-03"]
[{"$f":"A4062+1","v":4062},510054,"Security aspects of Public Warning System","PWS_Sec",1,"Rel-12","S3,S1","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","-","-",51,26,null,null,"2012-06-02","2014-06-09"]
[4064,510354,"   TR on SA3 part for Security aspects of Public Warning System","PWS_Sec-SA3TR",2,"Rel-12","S3","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#65 completed. TR 33.969v100 for 1-step Approval. Former TR 33.869 changed to 33.969.","New 33.869 changed to 33.969",51,26,null,null,"2012-06-02","2014-09-04"]
[4065,511354,"   Deleted - SA3 part for Security aspects of Public Warning System","PWS_Sec-del1",2,"Rel-12","S3","2011-03-30","2014-06-18",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#64 stopped","New 33.269",51,26,"SP-64","PCG-33","2012-06-02","2014-06-09"]
[4068,510454,"   Deleted - CT1 part for Security aspects of Public Warning System","PWS_Sec-del4",2,"Rel-12","C1","2011-03-25","2012-06-20",1,"SP-120434","-","ST-Ericsson","mikael.wass@ericsson.com","TSG#56 work stopped. SP#56 updated WID SP-110223=>SP-120334 (removed all but SA3 impacted specs)",23.041,51,26,"SP-56","PCG-29","2012-06-02","2012-06-08"]
[4072,560130,"   SA3 part of Extended IMS media plane security features (Stage 2)","eMEDIASEC-SA3",2,"Rel-12","S3","2012-06-20","2014-06-18",1,"SP-120447","-","Vodafone","Aguibou.Barry@vodafone.com","SP#64 completed",33.328000000000003,56,29,null,null,"2012-06-02","2014-06-10"]
[4075,600051,"      TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects","eMEDIASEC-CT",3,"Rel-12","C4","2012-12-13","2014-09-11",1,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completed. TR 29.828v200 for Approval. 2/4/15: acronym changed to eMEDIASEC-CT","New 29.828",58,30,null,null,"2012-11-14","2015-04-02"]
[4078,641009,"      (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-mmusic-sdp-for-gw)","eMEDIASEC-CT",3,"Rel-12","C4-IETF","2014-06-12","2014-12-09",0,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Work in progress. 2/4/15: acronym changed to eMEDIASEC-CT¦22/3/18: 100%->0","draft-schwarz-mmusic-sdp-for-gw",64,33,null,null,"2014-06-12","2018-03-22"]
[4081,580008,"      CT3 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C3","2012-12-19","2014-12-09",1,"CP-130597","CP-140569","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completion 06/14=>12/14. Level 100%=>80%. Exception in CP-140569. CP#64 completed. Dec.14: 80->100. 2/4/15: acronym changed to eMEDIASEC-CT",29.161999999999999,58,30,null,null,"2012-11-14","2015-04-02"]
[4084,580164,"   SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3)","TURAN-SA3",2,"Rel-12","S3","2012-12-13","2014-06-18",1,"SP-130245","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#64 completed","33.203, 33.402",58,30,null,null,"2012-11-12","2014-06-09"]
[4085,600050,"   CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3)","TURAN-CT",2,"Rel-12","C1","2013-06-14","2014-06-13",1,"CP-130716","-","Huawei","Haitao Wei (weihaitao@huawei.com)","CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs","24.229, 24.302, New 24.322",60,31,null,null,"2013-05-28","2014-05-26"]
[4088,470031,"   Stage 1 for Codec for Enhanced Voice Services","EVS_codec-SA1",2,"Rel-12","S1","2010-03-25","2010-03-25",1,"SP-140007","-","Huawei","lei.miao@huawei.com","SP#47 completed",22.172999999999998,47,24,null,null,"2010-03-10","2010-03-22"]
[4091,650005,"   CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",2,"Rel-12","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140800","-","Nokia Networks","Jan.Kall@nsn.com","Stage 3¦WID: CP-140492-> CP-140800",null,65,33,null,null,"2014-07-29","2014-12-09"]
[4094,650305,"      CT3 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C3","2014-09-16","2014-12-09",1,"CP-140800","CP-140560","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800","29.163, 29.292",65,33,null,null,"2014-07-29","2014-12-09"]
[4097,560140,"   SA4 part of Coordination of Video Orientation","CVO-SA4",2,"Rel-12","S4","2012-06-07","2013-03-06",1,"SP-120228","-","Ericsson","frederic.gabin@ericsson.com","SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering","26.114, 26.141, 26.234, 26.346",56,29,null,null,"2012-06-07","2013-02-16"]
[4099,600106,"      CT4 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C4","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","23.333, 23.334, 29.238, 29.332, 29.333, 29.334",60,31,null,null,"2013-05-28","2014-01-29"]
[4103,570133,"   TR on Evaluation of High Efficiency Video Coding for 3GPP Services","HEVC-SA4TR",2,"Rel-12","S4","2012-09-12","2014-06-19",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed. TR 26.906v200 for Approval","New 26.906",57,29,null,null,"2012-08-30","2014-04-16"]
[4106,580065,"Mobile stereoscopic 3D services extensions","M3DV_Ext",1,"Rel-12","S4","2012-12-12","2013-09-11",1,"SP-120768","-","Huawei","lukasz.kondrad@huawei.com","SP#61 completed. Related to Rel-11 Study On Mobile 3D Video Coding (FS_M3DVC) TR 26.905 and Rel-11 Mobile 3D Video Coding (M3DVC)","26.114, 26.245, 26.247, 26.430",58,30,null,null,"2012-11-12","2013-07-24"]
[4107,580066,"IMS-based Streaming and Download Delivery Enhancements","IMS_SDE",1,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","Provide an extension of IMS based PSS and MBMS user services","-",58,30,null,null,"2012-11-12","2013-04-19"]
[4110,580067,"Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE","ART_LTE",1,"Rel-12","S4","2012-12-12","2014-12-12",1,"SP-120769","-","Qualcomm","Andre Schevciw (aschevci@qualcomm.com)","Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods","Stage 3",58,30,null,null,"2012-11-12","2013-04-19"]
[4114,590043,"MBMS Improvements","MI",1,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130024","SP-140471","Ericsson","eric.turcotte@ericsson.com","Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description",null,59,30,null,null,"2013-02-20","2014-09-05"]
[4116,590143,"   Enhanced MBMS Operation","MI-EMO",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 85->100","26.247, 26.346",59,30,null,null,"2013-02-20","2015-03-05"]
[4119,590044,"End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI",1,"Rel-12","S4","2013-03-06","2015-09-14",1,"SP-140600","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040",26.114000000000001,59,30,null,null,"2013-02-20","2014-09-09"]
[4123,600207,"      CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C1","2013-06-21","2014-09-12",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%",24.228999999999999,60,31,null,null,"2013-05-29","2015-05-05"]
[4125,620066,"Video Coding Enhancements in IMS Messaging and Presence","VCEIMP",1,"Rel-12","S4","2013-12-11","2014-03-07",1,"SP-130579","-","Ericsson","frederic.gabin@ericsson.com","SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141",26.140999999999998,62,32,null,null,"2013-11-29","2014-01-29"]
[4128,560131,"   Rel-12 Self-Organizing Networks (SON) - OAM aspects","OAM12-SON",2,"Rel-12","S5","2011-09-21","2013-12-11",1,"-","-","-","-","OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI","-",56,29,null,null,"2012-04-18","2012-11-19"]
[4129,560033,"      Multi-vendor Plug and Play eNB connection to the network","SON-NM-MUPPET",3,"Rel-12","S5","2011-09-21","2013-12-11",1,"SP-120777","-","NSN","anatoly.andrianov@nsn.com","SP#62 completed. TS 32.508v200 for Approval, TS 32.509v100 for 1-step Approval","32.501, New TSs (32.508, 32.509)",56,29,null,null,"2012-04-18","2013-11-27"]
[4132,560335,"      3GPP Fault Management Solution Profile for NGMN NGCOR","OAM-FMSP",3,"Rel-12","S5","2012-06-20","2013-06-19",1,"SP-120778","-","Ericsson","thomas.tovinger@ericsson.com","SP#60 completed. TS 28.390v200 for Approval","new 28.390",56,29,null,null,"2012-05-23","2013-06-13"]
[4136,580053,"   Rel-12 Network Infrastructure Management","OAM12-NIM",2,"Rel-12","S5","2013-12-11","2014-12-12",1,"-","-","-","-","-","-",58,30,null,null,"2012-11-15","2012-11-19"]
[4138,630012,"      Radio Planning Tool (RPT) interface","OAM-RPTi-SA5",3,"Rel-12","S5","2014-03-07","2014-12-12",1,"SP-140026","SP-140546","Nokia Networks","olaf.pollakowski@nsn.com","SP#65 completion 09/14=>12/14. Exception in SP-140546. SP#65 v100 TS 28.667/8 for Information. Dec.14: 60->100","32.101, New TSs (28.667, 28.668, 28.669)",63,32,null,null,"2014-02-27","2014-12-04"]
[4141,620157,"      OAM aspects of Network Sharing - Concepts and high-level requirements","OAM-SHARE-SA5c",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. LM 80->100","new 32.130",62,32,null,null,"2013-11-28","2014-12-04"]
[4145,610041,"   Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3)","CHIPS",2,"Rel-12","S5","2013-09-12","2014-06-18",1,"SP-130642","-","Ericsson","david.shrader@ericsson.com","SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS","32.251, 32.298, 32.299",61,31,null,null,"2013-09-04","2015-12-07"]
[4148,530018,"IMS Emergency PSAP Callback (Stage 3)","EMC_PC",1,"Rel-12","C1,C3,IETF","2011-09-21","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls","Stage 3",53,27,null,null,"2011-08-27","2013-11-18"]
[4149,530118,"   CT1 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C1","2011-09-22","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#64 completed. 2/4/15: acronym changed to EMC_PC","24.229, tied to completion of IETF dependencies: 24.604, 24.605, 24.610, 24.611, 24.629",53,27,null,null,"2011-08-27","2015-04-02"]
[4151,530218,"   CT3 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C3","2011-09-24","2013-09-06",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#61 completed. 2/4/15: acronym changed to EMC_PC","29.163, 29.165",53,27,null,null,"2011-08-27","2015-04-02"]
[4154,580009,"Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD",1,"Rel-12","C1,C4,R3","2012-12-07","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality.","Stage 2/3",58,30,null,null,"2012-11-19","2013-09-04"]
[4158,590121,"      Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE","REP_WMD-RFR_PWS-Core",3,"Rel-12","R3","2013-03-04","2014-06-13",1,"RP-130398","RP-140637","one2many, Huawei","peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com)","RP#64 completed",36.412999999999997,59,30,null,null,"2013-02-26","2014-03-04"]
[4160,580112,"   CT1 part of Single Radio Voice Call Continuity (SRVCC) before ringing","bSRVCC",2,"Rel-12","C1","2012-12-07","2013-06-14",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","CP#60 completed. 2/4/15: acronym changed to bSRVCC","24.008, 24.237",58,30,null,null,"2012-11-19","2015-04-02"]
[4163,580013,"IMS Stage 3 IETF Protocol Alignment - phase 6","IMSProtoc6",1,"Rel-12","C1,C3,IETF","2012-12-07","2014-12-09",0.99,"CP-120905","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","-","Stage 3",58,30,null,null,"2012-11-19","2012-12-06"]
[4167,660038,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id)","IMSProtoc6",2,"Rel-12","C1-IETF","2014-09-12","2014-12-09",1,"CP-120905",null,"christer.holmberg@ericsson.com",null,"work in progress. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 25%->100; 9/4/21: RFC 7989 added;","draft-ietf-insipid-session-id; RFC 7989",65,34,null,null,"2014-12-04","2021-04-09"]
[4170,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[4171,580017,"   SAE Protocol Development (Stage 3) - Phase 3","SAES3-CT1",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[4175,580021,"   Stage 2 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C1","2012-12-07","2013-03-01",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#59 completed",23.218,58,30,null,null,"2012-11-19","2013-02-16"]
[4176,580022,"   Stage 3 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C4","2012-12-10","2013-06-14",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#60 completed","29.328, 29.329, 29.364",58,30,null,null,"2012-11-19","2013-05-29"]
[4180,580024,"Diameter based interface between SGSN-GMLC (Stage 3)","Dia_SGSN_GMLC",1,"Rel-12","C4","2012-12-10","2013-12-06",1,"CP-130598","-","Cisco","Nirav Salot (nsalot@cisco.com)","CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol)","29.002, 29.172, 29.173, 29.230, 29.272",58,30,null,null,"2012-11-20","2013-11-18"]
[4183,590112,"   CT4 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C4","2013-03-01","2013-12-06",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed","23.007, 23.008, 29.274",59,30,null,null,"2013-03-07","2013-11-18"]
[4186,590114,"   Stage 2 for Dual Radio VCC enhancements","eDRVCC",2,"Rel-12","S2","2012-09-19","2013-03-01",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). 2/4/15: acronym changed to eDRVCC",23.236999999999998,59,30,null,null,"2013-02-16","2015-04-02"]
[4189,590414,"      CT3 part of Stage 3 for Dual Radio VCC enhancements","eDRVCC",3,"Rel-12","C3","2013-03-01","2013-09-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#61 completed. 2/4/15: acronym changed to eDRVCC",29.164999999999999,59,30,null,null,"2013-02-16","2015-04-02"]
[4192,600209,"   CT1 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed",24.228999999999999,60,31,null,null,"2013-05-28","2013-11-19"]
[4193,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162, 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[4197,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[4198,640999,"   Common for HSS & PCRF solutions","PCSCF_RES",2,"Rel-12","C4,C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[4202,640998,"   HSS based solution","PCSCF_RES",2,"Rel-12","C4,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[4205,640997,"   PCRF based solution","PCSCF_RES",2,"Rel-12","C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Huawei","susan.shishufeng@huawei.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[4209,610108,"   CT1 part of Updating IMS to conform to RFC 6665","UP6665",2,"Rel-12","C1","2013-09-09","2014-12-09",1,"CP-130717","CP-140620","BlackBerry","Andrew Allen (aallen@blackberry.com)","CP#65 completion 09/14=>12/14. Exception in CP-140620. 3/3/15: 100% cpltd.","23.218, 24.141, 24.147, 24.229, 24.237, 24.292, 24.337, 24.341, 24.604, 24.606, 24.623, 24.628, 24.629, 24.642",61,31,null,null,"2013-07-25","2015-03-03"]
[4210,610208,"   CT3 part of Updating IMS to conform to RFC 6665","UP6665",2,"Rel-12","C3","2013-09-09","2013-12-06",1,"CP-130717","-","BlackBerry","Andrew Allen (aallen@blackberry.com)","CP#62 completed","29.163, 29.165",61,31,null,null,"2013-07-25","2013-11-19"]
[4214,620004,"IMS Operator Determined Call Barring enhancements (Stage 3)","eIODB",1,"Rel-12","C1,C3","2013-12-06","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision","Stage 3",62,32,null,null,"2013-11-18","2013-11-18"]
[4215,620104,"   CT1 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C1","2013-12-06","2014-06-13",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#64 completed","24.229, 24.315",62,32,null,null,"2013-11-18","2014-05-26"]
[4218,630002,"Interactive Connectivity Establishment (ICE, IETF RFC 5245) impacts on IMS H.248 profiles","ICEH248",1,"Rel-12","C4,C3","2014-03-05","2014-09-11",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","Add optional ICE support as defined in Rel-8 TS (23.228, 24.229) to Iq, Ix, Mn, Mp, Mc interfaces. SA2 Rel-12 TS 23.228 requires support for ICE in eP-CSCF, eIMS-AGW for WebRTC","Stage 2/3",63,32,null,null,"2014-01-29","2014-06-03"]
[4221,630005,"Transfer of ETSI business trunking specifications","IMS_Corp2",1,"Rel-12","C1,S1","2014-03-05","2014-12-09",1,"SP-140170","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com, Youssef Chadli","Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060","-",63,32,null,null,"2014-01-29","2014-03-07"]
[4224,630008,"Support of ALT-C attribute","ALTC",1,"Rel-12","C4,C1,C3","2014-03-10","2014-12-09",1,"CP-140191","-","Orange","lionel.morand@orange.com","SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network.","-",63,32,null,null,"2014-01-29","2014-03-03"]
[4227,630308,"   CT3 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C3","2014-03-10","2014-12-09",1,"CP-140191","CP-140563","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140563. Dec.14: 0->100",29.161999999999999,63,32,null,null,"2014-01-29","2014-12-04"]
[4231,640004,"Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",1,"Rel-12","C1,C3","2014-06-13","2014-12-09",1,"CP-140285","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases.","-",64,33,null,null,"2014-04-07","2014-04-07"]
[4234,640007,"Indication of NNI Routeing scenarios in SIP requests","NNI_RS",1,"Rel-12","C1,C3,IETF","2014-06-13","2014-12-09",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025","-",64,33,null,null,"2014-04-07","2014-04-07"]
[4236,641008,"   (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (draft-holmberg-dispatch-iotl)","NNI_RS",2,"Rel-12","C1-IETF","2014-06-13","2014-12-09",1,"CP-140288","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Publication requested¦7/3/16: 50%->100","draft-holmberg-dispatch-iotl",64,33,null,null,"2014-06-06","2016-03-07"]
[4237,640207,"   CT3 part of Indication of NNI Routeing scenarios in SIP requests","NNI_RS",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","CP#65 completed","29.079, 29.165",64,33,null,null,"2014-04-07","2014-07-31"]
[4240,640011,"Overload Control for PCC based Diameter applications","DOCME-PCC",1,"Rel-12","C3,IETF","2014-06-13","2014-12-09",1,"CP-140405","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)","-",64,33,null,null,"2014-06-10","2014-06-16"]
[4244,530002,"Introduction of ER-GSM band for GSM-R","RT_ERGSM",1,"Rel-12","G1,C1,G3new","2011-09-16","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios.","GERAN",51,27,null,null,"2011-09-06","2014-03-07"]
[4247,530202,"   CT1 part of Introduction of ER-GSM band for GSM-R","RT_ERGSM",2,"Rel-12","C1","2011-09-28","2013-12-06",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","CP#62 completed. Added ERGSM capability indication (24.008 CR#2469R1)",24.007999999999999,53,27,null,null,"2011-09-06","2013-11-19"]
[4249,570102,"   Core part: Downlink Multi Carrier GERAN","DMCG",2,"Rel-12","G2,G1","2013-07-22","2014-05-30",1,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","GP#62 completed. GP#55 approved WID","43.064, 44.004, 44.018, 44.060, 45.002, 45.003, 45.005, 45.008, 48.018",55,29,null,null,"2012-09-03","2014-05-30"]
[4253,590333,"   CT1 introduction of MS capability support for MS supporting MSRD for VAMOS","MSRD_VAMOS",2,"Rel-12","C1","2013-03-01","2013-12-06",1,"GP-130849","-","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","CP#62 completed",24.007999999999999,57,30,null,null,"2013-03-04","2014-08-29"]
[4256,620014,"New Training Sequence Codes (TSC) for GERAN","NewToN",1,"Rel-12","G1,G2,C1","2013-11-22","2014-12-09",0.93,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002","GERAN",60,32,null,null,"2013-11-22","2014-05-27"]
[4258,620214,"   GERAN2 part of New Training Sequence Codes (TSC) for GERAN","NewToN",2,"Rel-12","G2","2013-11-22","2014-11-19",0.8,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. ","44.018, 44.060",60,32,null,null,"2013-11-22","2014-05-30"]
[4259,620314,"   CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3)","NewToN",2,"Rel-12","C1","2013-11-22","2014-12-09",1,"GP-131139","CP-140604","Ericsson","Mårten Sundberg","CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604. 3/3/15: 100% cpltd.",24.007999999999999,60,32,null,null,"2013-11-22","2015-03-03"]
[4262,570021,"Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3)","EHNB_enh3",1,"Rel-12","R3,R2","2012-09-12","2013-12-06",1,"RP-130741","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Triggered by FS_EHNB_enh (TR 37.803)","UTRA, LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[4266,590219,"   Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA","LCS_BDS-UTRA-Perf",2,"Rel-12","R4","2013-03-07","2014-06-13",1,"RP-130416","RP-140714","ZTE","Ling Soonleh (soonleh.ling@zte.com.cn)","RP#64 completed. TS 25.173v100 for 1-step Approval","25.172 (FDD), new 25.173 (TDD)",59,30,null,null,"2013-02-26","2014-06-11"]
[4269,640013,"   Test part: BeiDou Navigation Satellite System (BDS) Positioning Support for LTE and UMTS","LCS_BDS-UEConTest",2,"Rel-12","R5","2014-06-15","2015-06-15",1,"RP-140730","RP-150656","CATT","Chen Xiaiozhong (chenxiaozhong@catt.cn)","¦Stat Rep: RP-141350->RP-141950 1st Apr 15: Compl:80%->90% 1st Apr 15: Stat Rep: RP-141950->RP-150357 03/07/15: Compl:90%->100% 03/07/15: Stat Rep: RP-150357->RP-150656","34.108, 36.508, 37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5",64,33,null,null,"2014-06-10","2015-06-18"]
[4271,620111,"   GERAN2 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",2,"Rel-12","G2","2013-11-22","2014-08-29",1,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#63 completed","44.031, 49.031, 44.071, 48.031",60,32,null,null,"2013-11-22","2014-08-29"]
[4275,600019,"Deleted - New Base Station specification structure","BSspec_struc",1,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-130851","-","Ericsson","johan.skold@ericsson.com","Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc)","UTRA, LTE, MSR",60,31,"RP-62","PCG-32","2013-06-17","2013-06-17"]
[4278,600021,"L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL",1,"Rel-12","R4,R2,R3","2013-06-17","2015-12-15",1,"RP-140092","-","Orange","olfa.benhaddada@orange.com","ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1","UTRA, LTE",60,31,null,null,"2013-06-17","2013-12-07"]
[4281,670047,"   UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-UEConTest",2,"Rel-12","R5","2015-03-16","2015-12-15",1,"RP-150835","RP-151163","Ericsson",null,"03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163¦1/1/16",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4282,600027,"LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON",1,"Rel-12","R3,S2,C4,G2","2013-06-18","2014-06-13",1,"RP-130831","-","China Telecom","Jinlian_wu@189.cn","Triggered by Rel-12 TR 37.813 (FS_LTE_HRPD_SON). SA2 should verify the architecture solution in TR 37.813 for inter-RAT load balancing between LTE-HRPD. CT4 should specify the RIM extension to support the feature.","UTRA, LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[4284,600127,"   Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON-Core",2,"Rel-12","R3","2013-06-18","2014-06-13",1,"RP-130831","RP-140745","China Telecom","Jinlian_wu@189.cn","RP#64 completed","36.300, 36.413",60,31,null,null,"2013-06-17","2014-06-12"]
[4288,620142,"   Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-Core",2,"Rel-12","R4,R2","2013-12-15","2014-12-15",1,"RP-132061","RP-141787","Ericsson","christopher.callender@ericsson.com","¦CD:Thu 18/12/14->Mon 15/12/14¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787","25.133, 25.331, 36.133",62,32,null,null,"2013-12-07","2015-01-12"]
[4291,620048,"WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw",1,"Rel-12","R2,S2,C1,C4","2013-12-06","2014-12-09",1,"RP-140981","-","Intel","sasha.sirotkin@intel.com","Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw)","UTRA, LTE",62,32,null,null,"2013-12-09","2013-12-09"]
[4294,640006,"   CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3)","UTRA_LTE_WLAN_interw-CT",2,"Rel-12","C1,C4","2014-09-09","2014-12-09",1,"CP-140623","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 revised WID CP-140287=>CP-140623 (added CT4 part)","Stage 2/3",64,33,null,null,"2014-04-07","2014-09-09"]
[4297,660075,"UE Conformance Test Aspects – WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-UEConTest",1,"Rel-12","R5","2014-12-15","2016-03-15",1,"RP-151270","RP-151264","Intel","Intel","Rel13->Rel-12¦Moved at appropriate place 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150098 03/07/15: Compl:5%->20% 03/07/15: Stat Rep: RP-150098->RP-150929 29/09/15: Compl:20%->60% 29/09/15: WID: RP-141879->RP-151270 29/09/15: Stat Rep: RP-15",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4300,530125,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7-Core",3,"Rel-12","R4","2011-09-19","2014-09-12",1,"RP-141487","RP-141084","Ericsson","christian.bergljung@ericsson.com ","RP#65 completed. Updated WID RP-132042=>RP-141487","36.101, 36.104, new generic 36.851",53,27,null,null,"2011-09-15","2014-09-20"]
[4301,530225,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7-Perf",3,"Rel-12","R4","2011-10-03","2014-09-12",1,"RP-141487","RP-141084","Ericsson","christian.bergljung@ericsson.com ","RP#65 completed","36.141, 36.307",53,27,null,null,"2011-09-15","2014-09-08"]
[4304,530229,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25-Perf",3,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","RP-130759","Sprint","George.Cummings@sprint.com","RP#60 completed","36.141, 36.307",53,27,null,null,"2011-09-15","2013-06-10"]
[4308,670049,"   UE Conformance Test Aspects - Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 2UL","LTE_CA_Rel12_2UL-UEConTest",2,"Rel-12","R5","2015-03-16","2016-12-15",1,"RP-160071",null,"Ericsson","NA","03/07/15: Compl:0%->29% 03/07/15: Stat Rep: ->RP-150834 29/09/15: Compl:29%->55% 29/09/15: Stat Rep: RP-150834->RP-151166 1/1/16: Compl:55%->70% 1/1/16: CD:Tue 15/12/15->Tue 15/03/16 1/1/16: WID: RP-1¦",null,67,34,null,null,"2015-04-01","2016-12-20"]
[4310,550111,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3-Core",3,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","RP-131573","SK Telecom","haesung.park@sk.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-2-03",55,28,null,null,"2012-02-23","2013-12-02"]
[4313,560115,"      Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1-Core",3,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-120826","RP-130549","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#60 stopped at 10% completion (rationale in RP-130670)","36.101, 36.104, 36.133, 36.141, 36.307, new 36.835",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[4316,560116,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4-Core",3,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-131135","RP-131039","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed. Updated WID RP-130842=>RP-131135","36.101, 36.104, 36.133, new 36.833-2-04",56,29,null,null,"2012-06-13","2013-08-28"]
[4320,560217,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4-Perf",3,"Rel-12","R4","2012-06-22","2013-09-06",1,"RP-130175","RP-131376","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed","36.101, 36.104, 36.133, 36.141, 36.307",56,29,null,null,"2012-06-13","2013-08-28"]
[4321,570012,"   LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29",2,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","-","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-03"]
[4323,570212,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29-Perf",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","RP-130536","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[4326,570213,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26-Perf",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","RP-130528","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#60 completed. Updated WID RP-130199=>RP-130658","36.101, 36.104, 36.133, 36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-07"]
[4329,570214,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19-Perf",3,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130198","RP-130526","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-08"]
[4332,570215,"      Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39","LTE_CA_B38_B39-Perf",3,"Rel-12","R4","2012-09-11","2012-12-07",1,"RP-121178","RP-121625","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#58 stopped at 0% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41)","36.133, 36.141",57,29,"RP-58","PCG-30","2012-09-03","2012-12-11"]
[4335,570216,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3-Perf",3,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","RP-131030","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","RP#61 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-09-04"]
[4338,570218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Perf",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130181","RP-130516","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[4342,580032,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26",2,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[4343,580132,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26-Core",3,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","RP-131005","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.101, 36.104, 36.133, new generic 36.851",58,30,null,null,"2012-12-10","2013-08-28"]
[4345,580033,"   LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41",2,"Rel-12","R4","2012-12-10","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","Inter-band 2DL","LTE",58,30,null,null,"2012-12-10","2014-03-05"]
[4348,580034,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12",2,"Rel-12","R4","2012-12-10","2014-09-12",1,"RP-140474","-","US Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 2DL","LTE",58,30,null,null,"2012-12-10","2014-09-08"]
[4351,580035,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","-","Ericsson","christian.bergljung@ericsson.com","Intra-band NC","LTE",58,30,null,null,"2012-12-10","2013-02-28"]
[4355,580136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-131679","RP-131567","NII Holdings","bill.shvodian@nii.com","RP#62 completed","36.101, 36.104, new 36.833-1-27",58,30,null,null,"2012-12-10","2013-12-06"]
[4358,590122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130523","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-02-26"]
[4361,590124,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130533","NTT DOCOMO","Kei ANDO","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-06-08"]
[4364,590125,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Core",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131549","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.101, 36.104, 36.133, new generic 36.851",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[4367,590129,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141941","RP-141732","Huawei","Liu Ye (leo.liuye@huawei.com)","¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[4369,590028,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-130327","-","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[4370,590128,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-130327","RP-141732","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[4373,590123,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140853","RP-141732","Ericsson","christian.bergljung@ericsson.com ","¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[4377,590231,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141967","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[4380,590226,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[{"$f":"A4382+1","v":4382},590127,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39-Core",3,"Rel-12","R4","2013-03-04","2014-03-06",1,"RP-131171","RP-140428","China Mobile","Li Nan (linan@chinamobile.com)","RP#63 completed","36.101, 36.104, 36.133, New 36.833-1-39 [instead of 36.845]",59,30,null,null,"2013-02-26","2014-03-05"]
[4386,600023,"   Deleted -LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL",2,"Rel-12","R4","2013-06-19","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","Intra-band NC 2UL","LTE",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[4389,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[4390,600124,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL-Core",3,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-141784","RP-141732","T-Mobile USA","nelson.ueng@t-mobile.com","¦WID: RP-142043->RP-141784¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, new 36.833-4-04",60,31,null,null,"2013-06-17","2015-01-12"]
[4393,600125,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","RP-131565","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-1-23 [instead of 36.864]",60,31,null,null,"2013-06-17","2013-12-02"]
[4396,600126,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131700","RP-131577","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-2-23",60,31,null,null,"2013-06-17","2013-12-19"]
[4399,600128,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","RP-131705","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",60,31,null,null,"2013-06-05","2013-12-02"]
[4402,600129,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset-Core",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","RP-131003","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.101, new generic 36.851",60,31,null,null,"2013-06-05","2013-08-28"]
[4404,600030,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130675","-","AT&T","marc.grant@att.com","Inter-band 2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[4408,600131,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30-Core",3,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. TR 36.853v200 for Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[4411,600132,"      Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131130","RP-131590","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131652 discussion","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4412,600232,"      Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131130","RP-131591","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131652 discussion","36.101, 36.104, 36.133, 36.141, 36.307",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4415,600233,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[4419,600035,"   Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131133","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,"RP-62","PCG-32","2013-06-17","2013-06-17"]
[4421,600235,"      Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131133","RP-131599","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131653 discussion","36.101, 36.104, 36.133, 36.141, 36.307",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4424,600236,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[4428,600038,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-141435","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[4430,600238,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141435","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[4433,600239,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13","LTE_CA_B4_B4_B13-Perf",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141433","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[4434,610017,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","-","Huawei","Liehai Liu (liuliehai@huawei.com)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4437,610018,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4441,610119,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11","LTE_CA_B1_B11-Core",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131354","RP-140569","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#64 completed","36.101, 36.104, new generic 36.851",61,31,null,null,"2013-09-07","2014-06-20"]
[4443,610020,"   LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11",2,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","-","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","Inter-band CA 2DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[{"$f":"A4446+1","v":4446},610021,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7",2,"Rel-12","R4","2013-09-09","2013-12-02",1,"RP-131365","-","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4450,610122,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL-Core",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-140100","RP-141084","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101, 36.104, 36.133, 36.307, New 36.833-5-41",61,31,null,null,"2013-09-07","2014-09-08"]
[4453,610123,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2-Core",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","RP-140569","Ericsson","imadur.rahman@ericsson.com","RP#64 completed. TR 36.833-2-02v100 for 1-step Approval","36.101, 36.104, 36.133, New 36.833-2-02",61,31,null,null,"2013-09-07","2014-06-12"]
[4454,610223,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2-Perf",3,"Rel-12","R4","2013-09-10","2014-06-13",1,"RP-131366","RP-140569","Ericsson","imadur.rahman@ericsson.com","RP#64 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2014-06-12"]
[4456,620118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.101, 36.104, 36.133, new generic 36.851",62,32,null,null,"2013-12-07","2014-09-08"]
[4459,620119,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-141803","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, 36.307, new generic 36.851",62,32,null,null,"2013-12-07","2015-01-12"]
[4463,620220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set","LTE_CA_B2_B4_BWset-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-131656","RP-140428","T-Mobile USA","nelson.ueng@t-mobile.com","RP#63 completed",36.307000000000002,62,32,null,null,"2013-12-07","2014-03-04"]
[4465,620121,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed","36.101, 36.104, 36.133, new generic 36.851",62,32,null,null,"2013-12-07","2014-06-20"]
[4468,620122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27-Core",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#63 completed. Updated WID RP-131752=>RP-140119","36.101, 36.104, 36.133, 36.307, New generic 36.851",62,32,null,null,"2013-12-07","2014-03-13"]
[4472,620272,"      Perf. part:LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","RP#63 completed",36.140999999999998,62,32,null,null,"2013-12-09","2014-03-05"]
[4475,620224,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","RP-141084","KT","Ilwhan Kim (ilwhan.kim@kt.com)","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-22"]
[4476,620025,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","-","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-22"]
[4480,620126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4481,620226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[4485,620028,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140190","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4488,620029,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12","LTE_CA_B2_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131654","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4491,620030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4494,620031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20","LTE_CA_B3_B7_B20",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141224","-","Vodafone","luis.anaya@vodafone.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-21"]
[4497,620033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4498,620133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4501,620134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4504,620135,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131653=>RP-141214","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4507,620137,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","RP-140569","CATT","Yuexia Song (songyuexia@catt.cn)","RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728","36.101, 36.104, 36.133, new 36.833-1-42",62,32,null,null,"2013-12-07","2014-06-12"]
[{"$f":"A4510+1","v":4510},620136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","RP-140569","Orange","Olfa BEN HADDADA","RP#64 completed","36.101, 36.307",62,32,null,null,"2013-12-07","2014-06-20"]
[4514,620238,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL-Perf",3,"Rel-12","R4","2013-12-09","2015-03-13",1,"RP-140101","RP-150013","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:60%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013",36.140999999999998,62,32,null,null,"2013-12-07","2015-04-01"]
[4515,620039,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[4519,620150,"      Core part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Core",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[4520,620250,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Perf",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.141, 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[4523,620251,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[4526,620252,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20","LTE_CA_B1_B7_B20-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-141223","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[4529,620253,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732","36.101, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-09","2015-01-12"]
[4532,630023,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20_BWset",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140447","-","NSN","iwajlo.angelow@nsn.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[4536,630025,"   Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback","LTE_CA_3DL_FB_BW",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140454","-","Qualcomm","Fong Gene (gfong@qti.qualcomm.com)","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[4539,630126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-03-10"]
[4541,630027,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","-","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[4542,630127,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-21"]
[4545,630128,"      Core part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7","LTE_CA_B3_B3_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141126","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated RP-140390=>RP-141126","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-08"]
[4549,630229,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL-Perf",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","RP-140569","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#64 completed. Updated WID RP-140453=>RP-140948","36.141, 36.307",63,32,null,null,"2014-03-10","2014-06-20"]
[4552,630235,"      Deleted - Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 stopped. Updated WID RP-140987=>RP-141235 (removed Perf. Part)",36.307000000000002,63,32,"RP-65","PCG-33","2014-03-10","2014-09-21"]
[4554,630136,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","RP-141084","Huawei","leo.liuye@huawei.com","RP#65 completed","36.101, 36.104, 36.851",63,32,null,null,"2014-03-10","2014-09-08"]
[4558,630237,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141709","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-22"]
[4561,630238,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141236","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[4564,630245,"      Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-140452","RP-141084","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#65 completed",36.307000000000002,63,32,null,null,"2014-03-10","2014-09-08"]
[4565,640020,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4_Bwset2",2,"Rel-12","R4","2014-06-15","2014-09-12",1,"RP-140599","-","T-Mobile USA","nelson.ueng@T-Mobile.com","Inter-band CA 2DL. Mar 15: acronym changed from LTE_CA_B2_B4_Bwset_","LTE",64,33,null,null,"2014-06-16","2015-03-10"]
[4567,640021,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_BWset",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","-","AT&T","marc.grant@att.com","2DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4571,640127,"      Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","RP-150188","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:10%->90%¦Stat Rep: RP-141303->RP-141839 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141839->RP-150188",36.100999999999999,64,33,null,null,"2014-06-16","2015-04-01"]
[{"$f":"A4574+1","v":4574},640228,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141, 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[4576,640129,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2014-09-08"]
[4580,640230,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","RP-150013","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","CD:Thu 11/12/14->Tue 15/03/16¦Compl:50%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: CD:Tue 15/03/16->Sun 15/03/15 1st Apr 15: Stat Rep: RP-141732->RP-150013","36.141, 36.307",64,33,null,null,"2014-06-16","2015-04-01"]
[4583,640231,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","RP-141084","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","RP#65 completed","36.141, 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[4586,650054,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Perf",3,"Rel-12","R4","2014-09-08","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 updated WID RP-140950=>RP-141127 (added Perf. Part). Completed.",36.307000000000002,65,33,null,null,"2014-09-21","2014-10-05"]
[4587,650010,"   LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28",2,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 2DL","LTE",65,33,null,null,"2014-03-10","2014-09-10"]
[4589,650210,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28-Perf",3,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","-","36.141, 36.307",65,33,null,null,"2014-03-10","2014-09-10"]
[4593,630039,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4596,630040,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4599,630041,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4602,630042,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4605,630043,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26","LTE_CA_B1_B3_B26",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140194","-","China Telecom","Zhao Dong (zhaodong@ctbri.com.cn)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4606,630143,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26","LTE_CA_B1_B3_B26-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140194","RP-141732","China Telecom","Zhao Dong (zhaodong@ctbri.com.cn)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[4609,630144,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141788","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141788¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[4613,640223,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133, 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[4615,640124,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, 36.307, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[4618,640126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41-Core",3,"Rel-12","R4","2014-06-16","2014-12-15",1,"RP-142301","RP-141732","China Mobile","PAN Qun (panqun@chinamobile.com)","¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[4621,640133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[4625,640234,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[4626,650046,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41",2,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141673","-","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-10-05"]
[4628,650246,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12",36.140999999999998,65,33,null,null,"2014-06-16","2015-01-12"]
[4631,650248,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41","LTE_CA_B39_B39_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142302","RP-141732","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[4634,650250,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","RP-141732","AT&T","marc.grant@att.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[4637,650252,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[4640,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[4644,570217,"   Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band-Perf",2,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130843","RP-130570","AT&T","marc.grant@att.com","RP#60 completed. Updated WID RP-121419=>RP-130843","36.101, 36.133, 36.141",57,29,null,null,"2012-09-03","2013-06-11"]
[4647,570119,"   Core part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Core",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-121414","RP-130567","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#60 completed. TR 36.840 v100 for 1-step Approval","36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new 36.840",57,29,null,null,"2012-09-03","2013-06-05"]
[4648,570219,"   Perf. part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Perf",2,"Rel-12","R4","2012-09-13","2013-09-06",1,"RP-121414","RP-131070","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#61 completed","36.133, 36.141, 37.141",57,29,null,null,"2012-09-03","2013-08-30"]
[4650,570020,"Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh",1,"Rel-12","R1,R4","2012-09-11","2016-03-15",1,"RP-121416","-","Alcatel-Lucent","Min Zhang (min.hs.zhang@alcatel-lucent.com)","Stage 3","LTE",57,29,null,null,"2012-09-03","2012-12-06"]
[4653,670045,"   UE Conformance Test Aspects - Further DL MIMO Enhancement for LTE-Advanced","LTE_eDL_MIMO_enh-UEConTest",2,"Rel-12","R5","2015-03-16","2016-03-15",1,"RP-150071","RP-151189","ZTE",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150606 29/09/15: Compl:10%->70% 29/09/15: Stat Rep: RP-150606->RP-1511891/1/16: Compl:70%->75%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4656,570225,"   Deleted - Perf. part: New Carrier Type for LTE","LTE_NCT-Perf",2,"Rel-12","R4","2012-09-17","2013-09-06",1,"RP-122028","RP-130985","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 0% completion","36.101, 36.104, 36.133, 36.141",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[4660,690072,"   UE Conformance Test Aspects - Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-UEConTest",2,"Rel-12","R5","2015-09-15","2018-03-15",1,"RP-151398",null,"CATT",null,"tested: REL-12 WI LTE_TDD_eIMTA-Core;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15% 21/3/ 19 827/3/",null,69,35,null,null,"2015-09-29","2018-03-27"]
[4663,580030,"Further enhancements for HeNB mobility-X2-GW","EHNB_enh2_X2GW",1,"Rel-12","R3","2012-12-10","2014-06-13",1,"RP-122006","-","Alcatel-Lucent","Philippe.Godin@alcatel-lucent.com","Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11¦remaining work including solution definition is Rel-12","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[4666,580231,"   Perf. part: 8 Rx Antennas for LTE UL","LTE_UL_8Rx-Perf",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","RP-131523","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","RP#62 completed","36.104, 36.141",58,30,null,null,"2012-09-03","2013-11-29"]
[4669,600213,"   Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD-Perf",2,"Rel-12","R4","2013-06-15","2014-12-15",1,"RP-140465","RP-141972","Nokia","lars.e.lindh@nokia.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141374->RP-141972","36.101, 36.104, 36.133",60,31,null,null,"2013-06-17","2015-01-12"]
[4672,600214,"   Perf. part: LTE Coverage Enhancements","Cov_Enh_LTE-Perf",2,"Rel-12","R4","2013-06-15","2014-12-15",1,"RP-130833","RP-141833","China Telecom","Xiaoming She (shexm@ctbri.com.cn)","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141149->RP-141833","36.101, 36.104, 36.133, 36.141",60,31,null,null,"2013-06-17","2015-01-12"]
[4674,610024,"Further MBMS operations support for E-UTRAN","MBMS_LTE_OS",1,"Rel-12","R2,R1,R3,R4","2013-09-15","2014-12-15",1,"RP-140282","-","Verizon","yeesin.chan@verizonwireless.com","Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS.","LTE",61,31,null,null,"2013-09-07","2014-09-09"]
[4675,610124,"   Core part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Core",2,"Rel-12","R2,R1,R3,R4","2013-09-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821","36.133, 36.214, 36.300, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320",61,31,null,null,"2013-09-07","2015-01-12"]
[4678,620140,"   Core part: Dual connectivity for LTE","LTE_SC_enh_dualC-Core",2,"Rel-12","R2,R1,R3,R4","2013-12-15","2014-12-15",1,"RP-141797","RP-141796","NTT DOCOMO, NEC","RAN1/2/4 tooru.uchino.fv@nttdocomo.com, RAN3 Chenghock Ng (ngcheng@da.jp.nec.com)","¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141264->RP-141796","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.322, 36.323, 36.331, 36.410, 36.413, 36.420, 36.423, new RAN3 36.425",62,32,null,null,"2013-12-07","2015-01-12"]
[4682,680070,"   UE Conformance Test Aspects - Dual connectivity for LTE","LTE_SC_enh_dualC-UEConTest",2,"Rel-12","R5","2015-06-15","2017-09-15",1,"RP-150840",null,"Ericsson",null,"tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16¦ ;",null,68,35,null,null,"2015-07-03","2017-09-19"]
[4685,620241,"   Perf. part: E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141459","RP-150690","Huawei","Elean FAN (fanxiaoan@huawei.com)","¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-","36.101, 36.104, 36.133, 36.141",62,32,null,null,"2013-12-09","2015-06-18"]
[4687,620047,"Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB",1,"Rel-12","R3,R1","2013-12-15","2014-12-12",1,"RP-140983","-","Samsung","Sung Hwan Won (sunghwan.won@samsung.com)","Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation).","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[4691,640105,"   Stage 1 Prioritization of Multimedia Telephony (MMTel) and Mobile Originating-SMS for Access Class Barring (ACB)","-",2,"Rel-12","S1","2014-03-05","2014-03-07",1,"CP-140286","-","-","-","SP#63 SP-140065 CR under TEI12",22.010999999999999,64,33,null,null,"2014-04-07","2014-04-07"]
[4694,630032,"Positioning Enhancements for RF Pattern Matching in E-UTRA","LCS_LTE_RFPMT",1,"Rel-12","R3,R2","2014-04-25","2014-06-13",1,"RP-140177","-","Polaris Wireless","Gordon Scot (sgordon@polariswireless.com)","follow-up of TR 36.809 FS_LCS_LTE_RFPMT","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[4695,630132,"   Core part: Positioning Enhancements for RF Pattern Matching in E-UTRA","LCS_LTE_RFPMT-Core",2,"Rel-12","R3,R2","2014-04-25","2014-06-13",1,"RP-140177","RP-140591","Polaris Wireless","Gordon Scot (sgordon@polariswireless.com)","RP#64 completed","36.305, 36.455",63,32,null,null,"2014-03-10","2014-06-12"]
[4698,630246,"   Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Perf",2,"Rel-12","R4","2014-03-11","2015-09-15",1,"RP-151297","RP-151296","MediaTek","Craig.Burnet@mediatek.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->25%¦Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862",36.100999999999999,63,32,null,null,"2014-03-10","2015-09-29"]
[4701,630147,"   Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO","LTE_SUMIMO_RX-Perf",2,"Rel-12","R4","2014-03-06","2015-03-13",1,"RP-140520","RP-150229","Huawei","Qian Cheng (Q.Cheng@Huawei.com)","CD:Fri 13/03/15->Sun 15/03/15¦Compl:50%->80%¦Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229",36.100999999999999,63,32,null,null,"2014-03-10","2015-04-01"]
[4704,580128,"   Core part: HSPA signalling enhancements for more efficient resource usage for LCR TDD","LCR_TDD_HSPA_sign_enh-Core",2,"Rel-12","R1,R2,R3","2012-12-15","2013-12-20",1,"RP-121984","RP-131499","CATT","Yanping Xing (xingyanping@catt.cn)","Prev CD:Fri 06/12/13¦Prev %:100%","25.222, 25.224, 25.331, 25.423, 25.433",58,30,null,null,"2012-12-10","2014-12-08"]
[4707,600117,"   Core part: HNB Positioning for UTRA","UTRA_HNB_Pos-Core",2,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","RP-131974","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID)","25.305, 25.467, new 25.470",60,31,null,null,"2013-06-17","2013-12-09"]
[4709,610125,"   Core part: Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh-Core",2,"Rel-12","R1,R2,R3,R4","2013-11-18","2014-09-12",1,"RP-140771","RP-141137","Qualcomm","arjunb@qti.qualcomm.com","RP#65 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433",61,31,null,null,"2013-09-07","2014-09-09"]
[4713,610126,"   Core part: UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob-Core",2,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","RP-140636","Huawei","Xudong Yang (yangxudong@huawei.com)","RP#64 completed. TS 25.300v100 for 1-step Approval","25.101, 25.104, 25.133, 25.141, 25.304, 25.306, 25.331, 25.433, new 25.300",61,31,null,null,"2013-09-07","2014-06-12"]
[4716,620154,"   Core part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Core",2,"Rel-12","R1","2013-12-06","2014-09-12",1,"RP-141701","RP-141702","Huawei","carmela.cozzo@huawei.com","RP#65 completed. Updated WID RP-140463=>RP-141701","25.101, 25.211, 25.212, 25.213, 25.214, 25.300, 25.302, 25.306, 25.308, 25.319, 25.331, 25.423, 25.433",62,32,null,null,"2013-12-09","2014-09-15"]
[4717,620254,"   Perf. part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-141701","RP-141898","Huawei","carmela.cozzo@huawei.com","¦Stat Rep: RP-141702->RP-141898","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[4720,620255,"   Perf. part: Enhanced Broadcast of System Information","UTRA_SIBenh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140131","RP-142080","Ericsson","martin.van.der.zee@ericsson.com","¦Stat Rep: RP-141230->RP-142080","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[4724,560018,"(Small) Technical Enhancements and Improvements for Rel-12","TEI12",1,"Rel-12","SP,CP,RP,GP","2012-12-25","2014-09-16",1,"-","-","-","-","-","-",56,29,null,null,"2012-07-13","2013-12-06"]
[4726,610001,"Test - (Small) Technical Enhancements and Improvements for Rel-12","TEI12_Test",1,"Rel-12","R5,G3new","2014-10-24","2015-12-11",1,"-","-","-","-","-","-",61,31,null,null,"2013-07-29","2013-07-29"]
[4729,480032,"Study on enhancements for Machine-Type Communications (MTC)","FS_MTCe",1,"Rel-12","S1","2010-06-10","2013-03-06",1,"SP-100448","-","Huawei","laurence.meriau@huawei.com","SP#59 completed. TR 22.888 v100 for Information & Approval. Study addition of new MTC-related use cases and functionality and improvements to existing requirements in TS 22.368",22.888000000000002,48,25,null,null,"2010-05-28","2013-02-19"]
[4733,530044,"Study on Proximity-based Services","FS_ProSe",1,"Rel-12","S1","2011-09-22","2013-03-05",1,"SP-110638","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#59 completed",22.803000000000001,53,27,null,null,"2011-09-08","2013-02-19"]
[4735,540028,"Study on RAN Sharing Enhancements","FS_RSE",1,"Rel-12","S1","2011-12-14","2013-06-19",1,"SP-110820","-","NEC","joerg.swetina@neclab.eu","SP#60 completed. Extend Rel-6 Network Sharing UID_31018 (basic scenarios of network/RAN sharing) to cover more complex scenarios that arise due to recent needs for more dynamic co-operation among operators",22.852,54,28,null,null,"2011-11-29","2013-06-18"]
[4736,460025,"Deleted - Study on UICC/USIM enhancements","FS_U2e",1,"Rel-12","S1","2009-12-10","2012-03-07",1,"SP-090903","-","Giesecke & Devrient","ilario.macchi@gi-de.com ","SP#55 work stopped. Triggered by GSMA Smart SIM and 3GNBK projects, and to evolve from traditional USAT to multimedia USIM toolkit support, particularly to Smart Card Web Server",22.817,46,24,"SP-55","PCG-28","2009-12-06","2012-03-04"]
[4739,490234,"   SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S2","2010-09-23","2012-06-20",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#56 completed. TR 23.844v100 for Information and Approval",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-14"]
[4742,490136,"   Study on Core Network Overload solutions (Phase 1)","FS_CNO",2,"Rel-12","S2","2010-09-23","2012-12-12",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","Phase 1: complete study of overload control related to MAP /Diameter signalling, other 3GPP Core Network signalling optimization",23.843,49,25,null,null,"2010-08-31","2012-08-30"]
[4746,560037,"Study on Optimized Offloading to WLAN in 3GPP-RAT Mobility","FS_WORM",1,"Rel-12","S2","2012-06-18","2013-09-11",1,"SP-120261","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","SP#61 completed. Linked to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP), UID_410043 MAPIM, UID_450041 IFOM, UID_530046 SaMOG",23.89,56,29,null,null,"2012-05-11","2013-07-25"]
[4748,410043,"Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",1,"Rel-12","S2,S1","2008-08-08","2012-12-12",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM)",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[4751,560039,"Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces","FS_NBIFOM",1,"Rel-12","S2","2012-06-18","2013-03-06",1,"SP-120742","-","ZTE","Tricci So (tso@zteusa.com)","SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility)",23.861000000000001,56,29,"SP-59","PCG-30","2012-06-04","2013-02-27"]
[4755,570035,"Study on Security Assurance Methodology for 3GPP Network Elements","FS_SECAM",1,"Rel-12","S3","2012-09-13","2014-06-18",1,"SP-120654","-","Orange","loic.habermacher@orange.com","SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible)",33.805,57,29,null,null,"2012-08-31","2014-05-21"]
[4758,470050,"Study on version handling","FS_OAM_VH",1,"Rel-12","S5","2010-03-25","2012-12-12",1,"SP-100082","-","Ericsson","thomas.tovinger@ericsson.com","SP#58 completed",32.83,47,24,null,null,"2010-02-12","2012-11-21"]
[4759,510046,"Study on management of Heterogeneous Networks","FS_OAM_HetNet",1,"Rel-12","S5","2011-03-23","2014-06-18",1,"SP-130046","-","Ericsson","ulf.hubinette@ericsson.com","SP#64 completed",32.835000000000001,51,26,null,null,"2012-06-02","2014-05-27"]
[4761,560032,"Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","FS_SON_NM_CCO",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140028","-","Ericsson","robert.petersen@ericsson.com","SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060)",32.835999999999999,56,29,null,null,"2012-04-18","2014-08-25"]
[4764,580025,"Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests","FS_NNI_RS",1,"Rel-12","C3","2012-12-10","2014-06-13",1,"CP-130166","-","Ericsson","Jan.Holm@ericsson.com","CP#64 completed",24.802,58,30,null,null,"2012-11-20","2014-06-18"]
[4768,620001,"Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME","FS_ISIM_CR",1,"Rel-12","C6","2013-12-09","2014-12-09",1,"CP-130812","-","Gemalto","ly-thanh.phan@gemalto.com","CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage¦June2015: Compl:30%->100",31.829000000000001,62,32,null,null,"2013-11-22","2015-06-15"]
[4771,520001,"Study on Voice services over Adaptive Multi-user channels on One Slot (VAMOS) enhancements","FS_eVAMOS",1,"Rel-12","GP,G2,G1","2010-10-27","2014-05-30",1,"GP-110991","-","China Mobile, Huawei","Chao Luo (chluo@huawei.com), dengjuan@chinamobile.com","GP#62 completed. TR 43.801v100 for 1-step Approval. GP#50 approved WID. Triggered by Rel-8 TR 45.914 Study Multi-User-Reusing One Timeslot (MUROS) UID_50590 and Rel-9 VAMOS UID_420002",43.801000000000002,50,27,null,null,"2011-05-21","2014-05-30"]
[4774,530052,"Study on Provision of low-cost MTC UEs based on LTE","FS_LC_MTC_LTE",1,"Rel-12","R1,R2,R4","2011-09-19","2013-06-14",1,"RP-121441","RP-130583","Vodafone","prakash.bhat@vodafone.com","RP#60 completed","LTE 36.888",53,27,null,null,"2011-09-19","2013-06-07"]
[4777,580041,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects","FS_LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122032","RP-131618","Huawei","Elean Fan (fanxiaoan@huawei.com)","RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.872",58,30,null,null,"2012-12-10","2013-12-03"]
[4780,580042,"Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE","FS_LTE_3D_channel",1,"Rel-12","R1","2012-12-10","2014-09-12",1,"RP-141237","RP-141206","Nokia Networks","bishwarup.mondal@nsn.com","RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network","LTE 36.873",58,30,null,null,"2012-12-10","2014-09-21"]
[4781,580046,"Study on Energy Saving Enhancement for E-UTRAN","FS_Netw_Energy_enh_LTE",1,"Rel-12","R3","2012-12-10","2014-06-13",1,"RP-122035","RP-140604","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","RP#64 completed. Identify potential solutions for energy saving in E-UTRAN non-overlapping scenario. Evaluate possible enhancements in overlapping scenario, so that a subset can be used for further investigation/standardization","LTE 36.887",58,30,null,null,"2012-12-10","2014-06-12"]
[4785,600015,"Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul ","FS_COMP_LTE_nibackhaul",1,"Rel-12","R1","2013-06-18","2013-12-06",1,"RP-130847","RP-131626","Samsung","Hyojin Lee (hyojin257.lee@samsung.com)","RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332)","LTE 36.874",60,31,null,null,"2013-06-17","2013-12-03"]
[4786,610028,"Study on Group Communication for LTE","FS_LTE_GC",1,"Rel-12","R2,R3","2013-09-10","2014-03-06",1,"RP-131382","RP-140182","Alcatel-Lucent","chandrika.worrall@alcatel-lucent.com","RP#63 completed. Evaluate ability of LTE to meet public safety requirements agreed in SA for GC (GC is a key functionality of Land Mobile Radio/Private Mobile Radio and public safety systems)","LTE 36.868",61,31,null,null,"2013-09-07","2014-03-14"]
[4790,550020,"Study on LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","FS_LTE_HRPD_SON",1,"Rel-12","R3","2012-03-02","2013-06-14",1,"RP-121982","RP-130585","China Telecom","Wu Jinlian (wujl@gsta.com)","RP#60 completed","UTRA, LTE 37.813",55,28,null,null,"2012-02-23","2013-06-05"]
[4793,580047,"Study on RAN Enhancements for UMTS/HSPA and LTE Interworking","FS_HSPA_LTE_interworking",1,"Rel-12","R3","2012-12-10","2013-12-06",1,"RP-122036","RP-131612","China Unicom","Meng Zhang (zhangmeng68@chinaunicom.cn)","RP#62 completed. TR 37.852v100 for Information & Approval","UTRA, LTE 37.852",58,30,null,null,"2012-12-10","2013-12-03"]
[4796,580050,"Study on Base Station specification structure","FS_BSspec_struc",1,"Rel-12","R4","2012-12-10","2013-06-14",1,"RP-122039","RP-130580","Ericsson","johan.skold@ericsson.com","RP#60 completed (1-step approval). Study new BS spec structure to avoid duplicate work for new RF features (in case of identical features among different RATs)¦avoid future discussions on how to implement new featurES in CP-150single-RAT/multi-RAT specs","UTRA, LTE, MSR 37.810",58,30,null,null,"2012-12-10","2013-06-07"]
[4799,580039,"Study on Scalable UMTS FDD bandwidth","FS_UTRA_SCAL",1,"Rel-12","R1,R4","2012-12-10","2013-12-06",1,"RP-130221","RP-132035","China Unicom","Han Xiao (hanxiao91@chinaunicom.cn)","RP#62 completed. TR 25.701v200 for Approval","UTRA 25.701",58,30,null,null,"2012-12-10","2013-12-18"]
[4802,580043,"Study on Further Enhanced Uplink (EUL) enhancements","FS_EDCH_enh",1,"Rel-12","R2,R1,R3","2012-12-10","2013-12-06",1,"RP-130347","RP-131608","Ericsson","alessandro.caverni@ericsson.com ","RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.)","UTRA 25.700",58,30,null,null,"2012-12-10","2013-12-02"]
[4803,600018,"Study on HNB Emergency Warning Area for UTRA","FS_HNB_warn_area",1,"Rel-12","R3","2013-06-18","2014-03-06",1,"RP-131258","RP-140129","Alcatel-Lucent, Ip.access","Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com ","RP#63 completed. TR 25.703 v100 for 1-step approval","UTRA 25.703",60,31,null,null,"2013-06-17","2014-02-26"]
[4806,470051,"Advanced IP Interconnection of Services","IPXS",1,"Rel-11","S1,S2,C1,C3","2010-03-25","2012-09-12",1,"SP-100876","-","Telefónica","chris.friel@O2.com","CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS)","-",47,24,null,null,"2002-03-05","2012-11-19"]
[4809,530004,"   Stage 3 for Advanced IP Interconnection of Services","IPXS",2,"Rel-11","C1,C3","2011-09-13","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed","Stage 3",53,27,null,null,"2011-08-29","2011-08-29"]
[4812,480030,"System Improvements to Machine-Type Communications","SIMTC",1,"Rel-11","S1,S2,S5,C1,C3,C4,C6,R2,R3,R5","2009-12-10","2014-03-06",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#58 completed. Updated WID SP-110877=>SP-120848. Enhancements to Rel-10 Feature UID_410031 (NIMTC) based on Rel-11 Study on enhancements to MTC","-",48,25,null,null,"2010-05-28","2012-11-12"]
[4815,520021,"   BB1: Stage 2 Reachability Aspects of SIMTC","SIMTC-Reach",2,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682)","23.221, New 23.368",52,27,null,null,"2011-05-26","2012-11-12"]
[4819,520421,"      Identifiers – especially removal of MSISDN dependencies in the architecture","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed","New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[4820,520521,"      MSISDN-less / PS-Only","SIMTC-Reach",3,"Rel-11","S2","2011-06-13","2012-03-07",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#55 completed","23.060, 23.272, New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[4824,530206,"      CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","29.061, New 29.368",53,27,null,null,"2011-08-29","2015-01-22"]
[4825,530306,"      CT4 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C4","2011-09-19","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","23.003, 23.008, 29.002, 29.060, 29.230, New (29.336, 29.337)",53,27,null,null,"2011-08-29","2015-01-22"]
[4828,530105,"      Deleted - Stage 2 CS aspects for SIMTC ","SIMTC-CS",3,"Rel-11","C4","2011-09-16","2012-09-06",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 stopped",23.012,53,27,"CP-57","PCG-29","2011-08-29","2012-08-13"]
[4831,530405,"         Deleted - CT6 part of Stage 3 CS aspects for SIMTC ","SIMTC-CS",4,"Rel-11","C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 stopped",31.102,53,27,"CP-57","PCG-29","2012-06-15","2012-08-13"]
[4835,530009,"   RAN overload control for Machine-Type Communications","SIMTC-RAN_OC",2,"Rel-11","R2,R3,C1,C6","2011-09-16","2012-09-07",1,"RP-111373","-","Huawei","Jeff Gao (gaoyongqiang@huawei.com)","Stage 2,3. TSG#57 completed","UTRA, LTE",53,27,null,null,"2011-09-15","2012-09-06"]
[4837,530209,"      Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 3",53,27,null,null,"2011-08-29","2012-08-24"]
[4841,540019,"   BB5: Charging of SIMTC (Stage 2/3)","SIMTC-CH",2,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-120848","-","Ericsson","patrik.teppo@ericsson.com","SP#58 completed","32.240, 32.251, 32.298, 32.299",54,28,null,null,"2011-10-24","2012-11-19"]
[4844,520222,"      Deleted - Small Data Transmissions (TS 22.368, 7.2.5)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[4846,530207,"         Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C1","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","-","23.122, 24.008, 24.301, 24.368",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[4847,530307,"         Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-",31.102,53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[4850,520223,"      Deleted - Lower Power Consumption (TS 22.368, 7.1.1)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[4854,530208,"         Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-","31.101, 31.102",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[4857,520124,"      Deleted - Secure Connection MTC Feature (TS 22.368, 7.2.10)","SIMTC-Sec",3,"Rel-11","S3","2011-06-08","2012-09-12",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#57 stopped (activity transferred to Rel-12 Feature MTCe","TBD",52,27,"CP-57","PCG-29","2011-05-26","2012-11-12"]
[4859,480330,"   Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications","SIMTC",2,"Rel-11","S2","2010-06-10","2011-06-08",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#52 stopped","TBD",48,25,"SP-52","PCG-27","2010-05-28","2012-11-12"]
[4863,520003,"   Stage 3 for USSD simulation service in IMS","USSI",2,"Rel-11","C1,C3","2011-06-03","2012-12-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228","-",52,27,null,null,"2011-05-18","2012-11-19"]
[4866,490031,"QoS Control Based on Subscriber Spending Limits","QoS_SSL",1,"Rel-11","S1,S2,S5,C3","2010-09-23","2012-06-20",1,"SP-110519","-","Vodafone","mona.mustapha@vodafone.com","TSG#56 completed","-",49,25,null,null,"2010-09-02","2012-06-14"]
[4869,500029,"   Charging for QoS Control Based on Subscriber Spending Limits (Stage 2)","QoS_SSL",2,"Rel-11","S5","2010-12-16","2012-06-20",1,"SP-110519","-","Nokia Siemens Networks, Huawei","Gerald.Goermer@nsn.com, shan.mingjun@huawei.com","SP#56 completed","32.240, 32.296",50,26,null,null,"2010-11-27","2012-04-02"]
[4870,520004,"   CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3)","QoS_SSL-CT3",2,"Rel-11","C3","2011-06-03","2012-06-15",1,"CP-120203","-","Huawei","QiaoWeihua@huawei.com","CP#56 completed","29.212, 29.213, 29.214, 29.215, new 29.219",52,27,null,null,"2011-05-18","2012-04-20"]
[4872,490132,"   TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S2","2010-09-23","2012-03-07",1,"SP-110347","-","Vodafone","Susana.Sabater@vodafone.com ","SP#55 completed","new 23.849",49,25,null,null,"2010-08-31","2012-03-05"]
[4876,530121,"   Stage 2 for Inclusion of Media Resource Broker","MRB",2,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed",23.218,53,27,null,null,"2011-08-25","2012-08-14"]
[4879,531005,"      (IETF) Inclusion of Media Resource Broker [RFC 6917 (was draft-ietf-mediactrl-mrb)]","MRB",3,"Rel-11","C1-IETF","2011-09-16","2013-06-14",1,"CP-120277","-","Keith Drage","-","CP#60 completed","RFC 6917 (was draft-ietf-mediactrl-mrb)",53,27,null,null,"2011-08-25","2013-06-10"]
[4881,500030,"Non Voice Emergency Services","NOVES",1,"Rel-11","S1,S2","2010-12-16","2012-03-07",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES)","-",50,26,null,null,"2010-11-29","2012-03-16"]
[4885,510147,"   Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",2,"Rel-11","S1","2011-03-23","2011-09-21",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 completed ",22.228000000000002,51,26,null,null,"2011-02-21","2011-08-24"]
[4888,520128,"   Stage 1 for Anonymous Call Rejection in the CS domain","ACR_CS",2,"Rel-11","S1","2011-06-07","2011-06-08",1,"SP-110421","-","Alcatel-Lucent","Betsy.Covell@alcatel-lucent.com","SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013)","22.004, 22.081, 22.082, 22.085, 22.088",52,27,null,null,"2011-05-19","2011-09-19"]
[4889,530011,"   Core Network aspects of Anonymous Call Rejection in the CS domain","ACR_CS-CN",2,"Rel-11","C4,C3","2011-09-14","2011-12-02",1,"CP-110587","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#54 completed","Stage 2/3",53,27,null,null,"2011-08-27","2011-08-27"]
[4892,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[4896,541001,"   (IETF) Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2-IETF","2011-12-12","2012-12-12",1,"SP-120539","-","Lionel Morand","Lionel Morand","Solved by IANA-registration. No RFC needed","-",54,28,null,null,"2011-12-06","2012-11-22"]
[4898,530112,"      TR on Stage 3 BB I for BBAI; UE to network protocols","BBAI_BBI-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#56 completed. Identify additional FMC specific procedurES in CP-150addition to those in 24.302 (on access authentication & authorization and tunnel management¦IP mobility mode selection¦security aspects)","new 24.820",53,27,null,null,"2011-08-29","2012-06-14"]
[4901,530212,"      CT1 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#57 completed","24.229, new 24.139",53,27,null,null,"2011-08-29","2012-09-05"]
[4904,490026,"   Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CTofldS1",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-120419","-","Ericsson","Olle.Eriksson@ericsson.com","SP#53 completed. 22/01: acronym modified",22.277999999999999,49,25,null,null,"2010-09-01","2015-01-22"]
[4907,530113,"      TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#56 completed ",24.82,53,27,null,null,"2011-08-29","2012-06-14"]
[4910,530413,"      CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C4","2011-09-16","2012-03-02",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#55 completed","23.008, 29.273",53,27,null,null,"2011-08-29","2012-08-13"]
[4911,490027,"   Deleted - Stage 1 BB III: BBF convergence and network based mobility ","-",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-120539","-","Huawei","Amar Deol (adeol@huawei.com)","SP#57 stopped. Updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#53 completed",22.277999999999999,49,25,"SP-57","PCG-29","2010-09-01","2012-06-09"]
[4914,530114,"      Deleted - TR on Stage 3 BB III for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","-",3,"Rel-11","C1","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","new 24.820",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[4918,480035,"Single Radio Voice Call Continuity (SRVCC) aspect of enhancements for Multimedia Priority Service","eMPS_SRVCC",1,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#54 completed. Analyze and if needed specify mechanisms for the priority handling of SRVCC with regard to LTE/EPC","Stage 2",48,25,null,null,"2010-06-06","2011-08-12"]
[4920,480235,"   Stage 2 on SRVCC for eMPS","eMPS_SRVCC",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#54 completed","23.216, 23.237",48,25,null,null,"2010-06-06","2012-03-04"]
[4923,520005,"   CN aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",2,"Rel-11","C1,C3,C4","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","Stage 3. CP#56 completed","-",52,27,null,null,"2011-05-18","2012-06-06"]
[4926,520305,"      CT4 aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",3,"Rel-11","C4","2011-06-03","2011-12-02",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","CP#54 completed",29.28,52,27,null,null,"2011-05-18","2012-06-06"]
[4930,480238,"   Stage 2 for Network-provided Location information for IMS","NWK-PL2IMS",2,"Rel-11","S2","2010-06-15","2012-03-07",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","SP#55 completed","23.060, 23.203, 23.228, 23.401",48,25,null,null,"2010-06-06","2012-02-20"]
[4931,490029,"   Charging for Network-provided Location information for IMS","NWK-PL2IMS_CH",2,"Rel-11","S5","2010-09-23","2012-09-12",1,"SP-110700","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#57 completed","Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299)",49,25,null,null,"2010-09-03","2012-09-05"]
[4933,550108,"      CT3 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C3","2012-03-02","2012-09-07",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","29.212, 29.214, 29.215",55,28,null,null,"2012-02-22","2015-03-03"]
[4936,500032,"Service Awareness and Privacy Policies","SAPP",1,"Rel-11","S2,S1,C3","2010-10-12","2011-12-02",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047","-",50,26,null,null,"2010-11-26","2011-08-12"]
[4939,510003,"   CT3 part of Service Awareness and Privacy Policies","SAPP-CT3",2,"Rel-11","C3","2011-03-18","2011-12-02",1,"CP-110136","-","Allot","Alla Goldner (agoldner@allot.com)","CP#54 completed. Stage 3 to support Application Detection and Control Functionality. Update Gx / introduce Sd reference points and procedures. Update S9 reference point in roaming scenarios","29.212, 29.213, 29.214, 29.215",51,26,null,null,"2011-03-02","2011-11-24"]
[4942,530017,"   CT aspects of VPLMN Autonomous CSG Roaming","VCSG-St3",2,"Rel-11","C4","2011-12-07","2011-12-07",1,"CP-120196","-","ZTE","Fei Lu (lu.fei1@zte.com.cn)","CP#57 completed","23.003, 23.007, 23.008, 23.012, 29.002, 29.230, 29.272",53,27,null,null,"2011-08-27","2012-08-13"]
[4945,510248,"   Stage 2 for Data Identification in ANDSF","DIDA",2,"Rel-11","S2","2011-03-24","2012-03-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#55 completed",23.402000000000001,51,26,null,null,"2011-02-21","2012-02-20"]
[4949,540010,"   CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","Stage 3. CP#56 completed","Stage 3",54,28,null,null,"2011-11-23","2012-09-24"]
[4952,530001,"Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC",1,"Rel-11","S2,C1,C3,C4,G2,R2,R3,R5","2011-09-12","2015-03-13",1,"SP-110475","-","Orange","antoine.mouquet@orange-ftgroup.com","Stage 1 in Rel-8 TS 22.278 clause 7.1.4.2. Triggered by Rel-11 TR 23.885 Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (FS_rSRVCC) UID_460030","-",53,27,null,null,"2011-08-12","2011-09-20"]
[4955,530301,"      CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.009, 24.008, 24.229, 24.237, 24.292, 24.301",53,27,null,null,"2011-08-25","2012-08-14"]
[4957,530501,"      CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C4","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.003, 23.008, 29.002, 29.230, 29.272, 29.280, 29.303, 29.305, 29.328",53,27,null,null,"2011-08-25","2012-08-14"]
[{"$f":"A4958+1","v":4958},530601,"   GERAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3)","rSRVCC-GERAN",2,"Rel-11","G2","2011-09-12","2013-06-28",1,"GP-111290","-","ZTE","li.jing4@zte.com.cn","GP#60 completed. GP#51 approved WID","44.018, 48.008",51,27,null,null,"2011-08-25","2013-09-04"]
[4961,640012,"   Test part: Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-UEConTest",2,"Rel-11","R5","2014-06-15","2015-03-13",1,"RP-141786","RP-150133","Ericsson","calle.hagenfeldt@ericsson.com","¦Stat Rep: RP-141167->RP-141771 1st Apr 15: Compl:40%->100% 1st Apr 15: Stat Rep: RP-141771->RP-150133","36.508, 36.523-1, 36.523-2, 36.523-3",64,33,null,null,"2014-06-10","2015-04-01"]
[4965,540111,"      CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#57 completed","23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303",54,28,null,null,"2011-10-26","2012-08-13"]
[4968,540311,"      CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C3","2011-12-02","2012-06-15",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#56 completed","29.212, 29.213, 29.215",54,28,null,null,"2011-10-26","2012-06-01"]
[4971,540030,"   Charging for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CH",2,"Rel-11","S5","2011-12-14","2012-09-12",1,"SP-110886","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","Stage 2/3. SP#57 completed","32.240, 32.260, 32.298, 32.299",54,28,null,null,"2011-12-08","2012-09-05"]
[4974,550204,"      CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CT",3,"Rel-11","C3","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","29.165, 29.162, 29.079",55,28,null,null,"2012-02-20","2012-11-20"]
[4977,570007,"   Stage 3 for IMS Overload Control","IOC",2,"Rel-11","C1,C3,IETF","2012-09-05","2014-12-09",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","-","-",57,29,null,null,"2012-08-13","2012-11-20"]
[4979,570207,"      CT3 part of Stage 3 for IMS Overload Control","IOC",3,"Rel-11","C3","2012-09-05","2012-12-07",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","CP#58 completed",29.164999999999999,57,29,null,null,"2012-08-13","2012-11-20"]
[4980,571001,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control)","RFC 7339",57,29,null,null,"2012-09-03","2015-03-10"]
[4983,520030,"Rel-11 Security small Enhancements","SEC11",1,"Rel-11","S3","2011-06-08","2012-09-12",1,"-","-","-","-","SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature","-",52,27,null,null,"2011-04-19","2012-08-16"]
[4987,560009,"   Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms)","EEA3_EIA3_UEConTest",2,"Rel-11","R5","2012-06-18","2012-09-07",1,"RP-120631","RP-120968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223)","36.523-1, 36.523-2, 36.523-3",56,29,null,null,"2012-06-04","2012-09-04"]
[4990,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[4992,540212,"   Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",2,"Rel-11","C4,C1","2011-12-02","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed","Stage 3",54,28,null,null,"2011-11-23","2012-08-14"]
[4996,530048,"Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements","EMM",1,"Rel-11","S4","2011-09-07","2013-03-06",1,"SP-120025","-","Qualcomm","Nikolai Leung (nleung@qualcomm.com)","Stage 3. SP#59 completed","26.140, 26.234, 26.247, New 26.951=>26.851",53,27,null,null,"2011-09-07","2013-02-16"]
[4999,530348,"   IMS-based PSS and MBMS Streaming Synchronization Enhancements","EMM-IPME",2,"Rel-11","S4","2011-09-07","2012-09-12",1,"SP-120025","-","InterDigital Communications","hang.liu@interdigital.com","SP#58 completed","26.237, new 26.951=>26.851",53,27,null,null,"2011-09-07","2012-12-11"]
[5000,560041,"Mobile 3D Video Coding","M3DV",1,"Rel-11","S4","2012-06-07","2012-09-12",1,"SP-120229","-","Orange","gilles.teniou@orange.com","SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905.","26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905",56,29,null,null,"2012-06-07","2012-08-20"]
[5003,510056,"      IRP framework enhancements to support Management of Converged Networks","OAM-FMC-IRP",3,"Rel-11","S5","2011-03-23","2013-03-07",1,"SP-120652","-","Nokia Siemens Networks, Ericsson","thomas.tovinger@ericsson.com, olaf.pollakowski@nsn.com","SP#59 completed. Triggered by SA5 Studies TR 32.833, 32.828, 32.831","32.101/103/150, new (28.620/621/622/623/624/625/626/627/628/629/631/632/633/651/652/653/654/655/656/657/658/659/661/662/663/671/672/673/674/675/676/701/702/703/704/705/706/707/708/709/731/732/733/734/735/736/751/752/753, 32.107/156/157/853/854",51,26,null,null,"2011-03-09","2012-12-05"]
[5006,510058,"      Enhanced Management of UE based network performance measurements","OAM-ePM-UE",3,"Rel-11","S5","2011-03-23","2012-12-12",1,"SP-110135","-","Huawei, Ericsson, Nokia Siemens Networks","Zou Lan (zlan@huawei.com), ulf.hubinette@ericsson.com, gyula.bodog@nsn.com","SP#58 completed","32.421, 32.422, 32.423, 32.441, 32.442, 32.446",51,26,null,null,"2011-02-22","2012-11-21"]
[5009,510351,"   Rel-11 Self-Organizing Networks (SON) - OAM aspects","OAM11-SON",2,"Rel-11","S5","2011-03-23","2013-03-06",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2011-02-22"]
[5012,540031,"      Inter-RAT Energy Saving Management","OAM-IRAT-ESM",3,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-110701","-","Nokia Siemens Networks, Huawei","clemens.suerbaum@nsn.com, xiahaitao@huawei.com","SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs","32.405, 32.551, 32.522, 32.526, 32.642, 32.646, 32.762, 32.766",54,28,null,null,"2011-11-22","2012-11-19"]
[5016,550019,"   Unification of Charging session from SIP AS and SRVCC functions in IMS","UCHIMS_AS-SRVCC",2,"Rel-11","S5","2012-03-07","2012-12-12",1,"SP-120042","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#58 completed","32.260, 32.275, 32.298, 32.299",55,28,null,null,"2012-02-22","2012-12-05"]
[5018,510129,"   Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","S1","2010-10-27","2011-09-21",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","SP#53 completed under IPXS",22.114999999999998,51,26,null,null,"2011-02-22","2011-10-07"]
[5021,480011,"User Data Convergence - Data Model","UDC_DM",1,"Rel-11","C4,S1","2010-03-25","2012-09-07",1,"CP-110384","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#57 completed. SP#48 Stage 1 completed as Rel-10","-",48,25,null,null,"2010-05-26","2012-08-13"]
[{"$f":"A5022+1","v":5022},480036,"   Stage 1 for UDC Data Model","UDC_DM",2,"Rel-11","S1","2010-03-25","2011-09-21",1,"-","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","SP#53 completed under Rel-10 UDC",22.100999999999999,48,25,null,null,"2010-05-26","2011-09-19"]
[5025,510004,"Definition of the UICC Application for Hosting Party Module","HPM_UICC",1,"Rel-11","C6","2011-03-18","2012-06-15",1,"CP-110289","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#56 completed","31.102, New 31.104",51,26,null,null,"2011-03-03","2012-09-25"]
[5029,581001,"   (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077)","eNR_EPC",2,"Rel-11","C4-IETF","2012-12-07","2013-12-06",1,"CP-120449","-","Lionel Morand","Lionel Morand","CP#62 completed","RFC 7077 (was draft-ietf-netext-update-notifications)",58,30,null,null,"2012-11-24","2013-11-28"]
[5031,570009,"   CT3 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C3","2012-09-10","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed",29.212,57,29,null,null,"2012-08-13","2012-11-20"]
[5034,520209,"   CT1 part of Reference Location Information (Stage 3)","RLI",2,"Rel-11","C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed",24.228999999999999,52,27,null,null,"2011-05-18","2011-06-01"]
[5038,800113,"   (IETF) A P-Served-User Header Field Parameter for Originating CDIV session case in SIP (draft-ietf-sipcore-originating-cdiv-parameter) --> RFC 8498","IMSProtoc5",2,"Rel-11","C1-IETF","2013-03-01","2014-09-12",1,"CP-110437",null,"Roland Jesske","Roland Jesske","26/6/19: 25%->100; 23/4/20: 100%->100",null,80,41,null,null,"2018-06-27","2020-04-23"]
[5040,520210,"   CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C3","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","29.163, 29.165",52,27,null,null,"2011-05-18","2012-08-14"]
[5041,581002,"   Deleted - (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (avasarala-dispatch-comm-div-notification)","IMSProtoc5",2,"Rel-11","C3-IETF","2012-12-07","2014-09-12",1,"CP-110437","-","Andrew Allen","Andrew Allen","CP#64 Draft removed from 3GPP documentation","draft-avasarala-dispatch-comm-div-notification",58,30,"CP-65","PCG-33","2011-05-18","2014-09-02"]
[5044,540018,"   CN aspects of Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","C4,C3","2011-12-02","2012-09-07",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","CP#57 completed","-",54,28,null,null,"2011-10-26","2012-08-13"]
[5047,530103,"   GERAN2 part of Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","G2","2011-09-19","2012-08-31",1,"GP-111876","-","China Mobile, Huawei","Juan Deng, Yang Zhao","GP#55 completed. GP#51 approved WID",48.018000000000001,51,27,null,null,"2011-09-06","2012-08-31"]
[5051,530020,"GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3)","RT_VGCS_Red",1,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069)","Stage 2/3",53,27,null,null,"2011-08-27","2012-08-14"]
[5053,530220,"   Deleted - CT4 part of GCSMSC and GCR Redundancy for VGCS/VBS","RT_VGCS_Red",2,"Rel-11","C4","2011-09-19","2012-06-15",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#56 stopped (no CT4 impact)",29.001999999999999,53,27,"CP-56","PCG-29","2011-08-27","2012-09-25"]
[5056,540117,"   CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",2,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed","23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334",54,28,null,null,"2011-10-26","2012-08-13"]
[5060,560006,"PS Additional Number (Stage 3)","PSAN",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120253","-","Deutsche Telekom","Yvette.koza@t-mobile.at","CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact)","23.003, 23.008, 29.002, 29.272, 29.230",56,29,null,null,"2012-04-23","2012-08-13"]
[5063,570110,"   CT1 part of IMS Operator Determined Call Barring","IODB",2,"Rel-11","C1","2012-09-10","2013-06-14",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","CP#60 completed. Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CT decision.","New 24.315",57,29,null,null,"2012-08-13","2013-06-13"]
[5064,570210,"   CT4 part of IMS Operator Determined Call Barring","IODB",2,"Rel-11","C4","2012-09-07","2013-03-12",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","CP#58 completed","23.008 , 23.015 , 29.328 , 29.329 , 29.364",57,29,null,null,"2012-08-13","2012-11-17"]
[5066,570111,"   CT3 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C3","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",29.163,57,29,null,null,"2012-08-13","2012-11-20"]
[5069,540016,"Deleted - Enhancement of the Protocols for SMS over SGs (Stage 3)","PROTOC_SMS_SGs",1,"Rel-11","C4,C1","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped. Reason: Protocols for SMS over SGs is replaced by the SIMTC SMS in MME solution (as solution not only for MTC user but for general subscribers)","Stage 3",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[5073,510001,"Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",1,"Rel-11","G2,S2,C1","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001","GERAN",49,26,null,null,"2011-03-04","2013-05-17"]
[5076,510301,"   CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","C1,C4","2011-06-03","2012-12-07",1,"CP-120563","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#58 completed","-",49,26,null,null,"2012-06-02","2012-11-19"]
[5079,560042,"   Stage 2 for Gateway Core Network Sharing for GERAN","Full_MOCN-GERAN-GWCN",2,"Rel-11","S2","2012-06-18","2013-03-06",1,"SP-120268","-","Vodafone","chris.pudney@vodafone.com","SP#59 completed. (23.251CR0062R2 as TEI11. TS 23.251 specifies both MOCN and GWCN for E-UTRAN and UTRAN, but GWCN is not yet supported on GERAN. Extend Full_MOCN-GERAN to also cover GWCN GERAN",23.251000000000001,56,29,null,null,"2012-06-04","2012-11-22"]
[5082,540203,"   Perf. part: Medium range/local area requirements for multicarrier BTS","MRLA-Perf",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111782","-","Ericsson","Eric Nordström","Test spec. GP#56 completed. GP#52 approved WID",51.021000000000001,52,28,null,null,"2011-11-25","2012-11-23"]
[5085,500120,"   Core part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Core",2,"Rel-11","R4,R2,R3","2010-12-10","2012-03-02",1,"RP-111396","RP-120075","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[{"$f":"A5086+1","v":5086},500220,"   Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Perf",2,"Rel-11","R4","2010-12-10","2012-03-02",1,"RP-111396","RP-120076","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[5090,530033,"Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2013-12-06",1,"RP-121204","-","MediaTek","Johan Johansson","Stage 2/3","UTRA, LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5091,530133,"   Core part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-Core",2,"Rel-11","R2,R1,R3,R4","2011-09-19","2012-12-07",1,"RP-121204","RP-121556","MediaTek","Johan Johansson","RP#58 completed","25.133, 25.123, 25.304, 25.331, 25.413, 25.423, 36.133, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320, 36.300",53,27,null,null,"2011-09-15","2012-11-27"]
[5095,570001,"   GERAN part: Network Energy Saving for E-UTRAN","-",2,"Rel-11","GP","2012-08-27","2012-08-31",1,"GP-121178","-","Alcatel-Lucent","marguerite.woch@alcatel-lucent.com","GP#55 approved WID and completed. Stage 3. ChangES in CP-150RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature","48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)]",55,29,null,null,"2012-09-01","2012-09-01"]
[5098,530237,"   Perf. part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-Perf",2,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-111383","RP-121559","Ericsson","johan.skold@ericsson.com","RP#58 completed","25.141, 36.141, 37.141",53,27,null,null,"2011-09-15","2012-09-04"]
[5101,550115,"   Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Core",2,"Rel-11","R4,G1","2012-02-06","2012-12-07",1,"RP-120857","RP-121985","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#58 completed","25.104, 25.105, 36.104, 37.104, new 37.812",55,28,null,null,"2012-02-23","2012-12-05"]
[5104,560113,"   Core part: Further enhancements to H(e)NB mobility - Part 1","EHNB_enh1-Core",2,"Rel-11","R3,R2","2012-06-15","2012-12-07",1,"RP-121427","RP-121563","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#58 completed","25.413, 25.467, 25.469, 36.300, 36.413, 36.423",56,29,null,null,"2012-06-13","2012-11-27"]
[5107,430011,"Network-Based Positioning Support for LTE","LCS_LTE-NBPS",1,"Rel-11","R2,R1,R3,R4","2009-03-05","2014-06-13",1,"RP-131259","-","TruePosition","terri.brooks@trueposition.com","-","LTE",43,22,null,null,"2009-03-06","2012-09-04"]
[5108,430111,"   Core part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Core",2,"Rel-11","R2,R1,R3,R4","2009-03-05","2013-06-12",1,"RP-131259","RP-130483","TruePosition","terri.brooks@trueposition.com","RP#60 completed","36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new (36.111, 36.456, 36.457, 36.458, 36.459)",43,22,null,null,"2009-03-06","2013-08-29"]
[5111,480126,"   Core part: Service continuity improvements for MBMS for LTE","MBMS_LTE_SC-Core",2,"Rel-11","R2,R3","2010-06-04","2012-09-07",1,"RP-120258","RP-121001","Huawei","David.Lecompte@huawei.com ","RP#57 completed","25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445",48,25,null,null,"2010-06-04","2012-09-06"]
[5114,510121,"   Core part: Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE-Core",2,"Rel-11","R1,R2,R3,R4","2011-03-22","2012-12-07",1,"RP-120860","RP-121986","China Mobile","ShenXiaodong@chinamobile.com","RP#58 completed","36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.321, 36.331, 36.413, 36.423",51,26,null,null,"2011-03-14","2012-12-05"]
[5117,510028,"New Band LTE Downlink FDD 716-728 MHz (Band 29, Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29)","LTE_DL_FDD700",1,"Rel-11","R4","2011-03-22","2012-12-07",1,"RP-110435","-","AT&T","marc.grant@att.com ","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[5120,510031,"LTE RAN Enhancements for Diverse Data Applications","LTE_eDDA",1,"Rel-11","R2,R5","2011-03-18","2013-09-06",1,"RP-120256","-","BlackBerry","Gordon Young (gyoung@rim.com)","Stage 2/3","LTE",51,26,null,null,"2011-03-14","2013-08-28"]
[5124,510132,"   Core part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-Core",2,"Rel-11","R1,R2,R4","2011-06-15","2012-09-07",1,"RP-120602","RP-120570","NII Holdings","bill.shvodian@nii.com","RP#56 completed","25.101, 25.104, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.307, 37.104, 37.113",51,26,null,null,"2011-03-14","2012-06-09"]
[5125,510232,"   Perf. part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-Perf",2,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-120602","RP-120571","NII Holdings","bill.shvodian@nii.com","RP#56 completed","25.123, 25.133, 25.141, 36.133, 36.141, 37.141",51,26,null,null,"2011-03-14","2012-06-09"]
[5129,520217,"   Perf. part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Perf",2,"Rel-11","R4","2011-06-09","2012-06-15",1,"RP-110875","RP-120573","Ericsson","olav.queseth@ericsson.com","RP#56 completed","36.133, 36.141, 37.141",52,27,null,null,"2011-06-02","2012-06-09"]
[5130,560011,"   Test part: LTE for 700 MHz Digital Dividend","LTE_APAC700-UEConTest",2,"Rel-11","R5","2012-06-18","2013-06-14",1,"RP-120600","RP-130467","Ericsson","fredrik.sundstrom@ericsson.com","RP#60 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1",56,29,null,null,"2012-06-06","2013-06-03"]
[5133,520219,"   Perf. part: Relays for LTE (part 2)","LTE_Relay2-Perf",2,"Rel-11","R4","2009-12-04","2013-06-14",1,"RP-110914","RP-130487","Ericsson","christian.hoymann@ericsson.com ","RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213","36.133, new 36.117 (E-UTRA Relay conformance testing)",46,24,null,null,"2009-11-30","2013-06-04"]
[5137,530032,"Coordinated Multi-Point Operation for LTE","COMP_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-09-19","2014-12-15",1,"RP-111365","-","Huawei, Samsung","Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com","Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE)","LTE",53,27,null,null,"2011-09-15","2011-09-15"]
[5140,530332,"   Core part: Coordinated Multi-Point Operation for LTE – Downlink","COMP_LTE_DL-Core",2,"Rel-11","R1,R2,R3,R4","2011-09-19","2012-12-07",1,"RP-111365","RP-121577","Samsung","Juho Lee (juho95.lee@samsung.com)","RP#58 completed","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423",53,27,null,null,"2011-09-15","2012-11-27"]
[5142,590004,"   Test part: Coordinated Multi-Point Operation for LTE","COMP_LTE-UEConTest",2,"Rel-11","R5","2013-03-15","2014-12-15",1,"RP-130376","RP-141782","Samsung","Stoyan.Baev@partner.samsung.com",null,"36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2015-01-12"]
[5146,590005,"   Test part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-UEConTest",2,"Rel-11","R5","2013-03-04","2014-09-12",1,"RP-130304","RP-141256","Huawei","Xu Kai (xk.xukai@huawei.com)","RP#65 completed","36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2014-09-09"]
[5149,590006,"   Test part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-09-06",1,"RP-130169","RP-130949","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#61 completed","36.521-1, 36.521-2",59,30,null,null,"2013-02-26","2013-08-29"]
[5151,550113,"   Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-Perf",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120382","RP-121582","Renesas Mobile","Timo Roman","RP#58 completed",36.100999999999999,55,28,null,null,"2012-02-23","2012-11-27"]
[5152,600002,"   Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-UEConTest",2,"Rel-11","R5","2013-06-18","2014-09-12",1,"RP-140491","RP-141602","Broadcom","jarkko.hellsten@kolumbus.fi","RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101","36.508, 36.521-1, 36.521-2, New 36.904",60,31,null,null,"2013-05-22","2014-09-07"]
[5155,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[5159,510230,"      Perf. part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Perf",3,"Rel-11","R4","2011-03-15","2014-12-12",1,"RP-121999","RP-141969","Nokia","lars.e.lindh@nokia.com","¦Stat Rep: RP-141377->RP-141969","36.101, 36.104, 36.133, 36.141",51,26,null,null,"2011-03-14","2015-01-12"]
[5162,580258,"   Rel-11 inter-band Carrier Aggregation","-",2,"Rel-11","R4","2010-12-10","2012-12-07",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[5164,480123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Core",4,"Rel-11","R4","2010-12-10","2012-09-07",1,"RP-120830","RP-121022","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",48,25,null,null,"2010-06-04","2012-09-04"]
[5168,500217,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-121458","RP-121595","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",50,26,null,null,"2010-12-10","2012-11-26"]
[5171,500218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 13","LTE_CA_B4_B13-Perf",4,"Rel-11","R4","2010-12-21","2012-12-07",1,"RP-120905","RP-121594","Ericsson","christian.bergljung@ericsson.com ","RP#58 completed","36.101, 36.133, 36.141",50,26,null,null,"2010-12-10","2012-11-27"]
[5174,510222,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12-Perf",4,"Rel-11","R4","2011-03-29","2012-12-07",1,"RP-120877","RP-121593","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","RP#58 completed","36.133, 36.141",51,26,null,null,"2011-03-14","2012-11-27"]
[5175,510023,"      LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","-","US Cellular","sebastian.thalanany@uscellular.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[5177,510223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-120221","RP-121597","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",51,26,null,null,"2011-03-14","2012-11-27"]
[5181,510025,"      LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17",3,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110432","-","AT&T","marc.grant@att.com ","Stage 3. RP#57 Core completed. RP#58 Perf completed","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[5184,510026,"      LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5",3,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110433","-","AT&T","marc.grant@att.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[5186,510226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110433","RP-121589","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5190,530023,"      LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120887","-","Vodafone","tim.frost@vodafone.com","Stage 3. RP#57 completed","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[5193,530024,"      LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20",3,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-120888","-","Vodafone","Luis.Anaya@vodafone.com","Stage 3. RP#58 completed","LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5194,530124,"         Core part: LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-120888","RP-121600","Vodafone","Luis.Anaya@vodafone.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[5197,530126,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120899","RP-121042","SK Telecom","Haesung Park","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",53,27,null,null,"2011-09-15","2012-09-04"]
[5201,530227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Perf",4,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-121152","RP-121591","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",53,27,null,null,"2011-09-15","2012-11-27"]
[5203,540120,"         Core part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Core",4,"Rel-11","R4,R2","2011-12-09","2012-12-07",1,"RP-120898","RP-121602","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-12-04"]
[5206,540121,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18-Core",4,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-120892","RP-121052","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-09-04"]
[5209,540122,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Core",4,"Rel-11","R4,R2","2012-03-05","2012-09-07",1,"RP-120866","RP-120552","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-06-15"]
[5212,540123,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Core",4,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-121173","RP-121054","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-09-04"]
[5215,550118,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Core",4,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-121162","RP-121586","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",55,28,null,null,"2012-02-23","2012-11-27"]
[5216,550218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Perf",4,"Rel-11","R4","2012-03-06","2012-12-07",1,"RP-121162","RP-121587","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed","36.133, 36.141",55,28,null,null,"2012-02-23","2012-11-27"]
[5219,520115,"         Core part: LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38-Core",4,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110862","RP-121060","Huawei","ronnie.zhang@huawei.com","RP#57 completed. TR 36.830 v100 for Information & Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-38 [instead of 36.830]",52,27,null,null,"2011-06-02","2012-09-04"]
[5223,520216,"         Perf. part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Perf",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120127","Clearwire","michael.hart@clearwire.com","RP#55 completed","36.101, 36.104, 36.133, 36.141, 36.307",52,27,null,null,"2011-06-02","2012-02-23"]
[5225,530128,"         Core part: LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-121193","RP-121062","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","RP#57 completed. TR 36.831 v100 for Information & Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-07 [instead of 36.831] ",53,27,null,null,"2011-09-15","2012-09-04"]
[5228,450116,"   Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest-Core",2,"Rel-11","R4","2009-09-18","2011-12-09",1,"RP-111381","RP-111456","CATR","Guo Lin (guolin@emcite.com)","RP#54 completed","25.144, 25.914, 34.114",45,23,null,null,"2009-09-15","2011-11-29"]
[5231,500119,"   Core part: Eight carrier HSDPA","8C_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-06-15",1,"RP-101419","RP-120971","Ericsson","johan.hultell@ericsson.com","RP#57 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306",50,26,null,null,"2010-12-10","2012-09-04"]
[5235,530038,"   Test part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc-UEConTest",2,"Rel-11","R5","2011-09-19","2012-03-02",1,"RP-111181","RP-120052","China Mobile","Ma Shuai (mashuai@chinamobile.com)","RP#55 completed","34.108, 34.122",53,27,null,null,"2011-09-06","2012-02-23"]
[5236,500022,"Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv",1,"Rel-11","R1,R4,R2,R3,R5","2010-12-10","2014-06-13",1,"RP-120367","-","Huawei","zongjie.wang@huawei.com","Stage 2/3","UTRA",50,26,null,null,"2010-12-10","2012-02-28"]
[5238,500222,"   Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop","HSPA_UL_TxDiv-CL-Perf",2,"Rel-11","R4","2010-12-14","2013-09-06",1,"RP-120367","RP-130477","Huawei","zongjie.wang@huawei.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",50,26,null,null,"2010-12-10","2013-08-30"]
[5241,590008,"   Test part: Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv-UEConTest",2,"Rel-11","R5","2013-03-04","2014-06-13",1,"RP-130351","RP-140767","Qualcomm","Shubhang Vora (svora@qti.qualcomm.com)","RP#64 completed","34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",59,30,null,null,"2013-01-29","2014-06-10"]
[5244,510218,"   Perf. part: Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config-Perf",2,"Rel-11","R4","2011-03-24","2012-06-15",1,"RP-110308","RP-120475","Telus Communications","jorge.delrio@telus.com ","RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",51,26,null,null,"2011-03-14","2012-06-09"]
[5247,510219,"   Perf. part: Non-contiguous 4C-HSDPA operation","NC_4C_HSDPA-Perf",2,"Rel-11","R4","2011-03-23","2013-03-01",1,"RP-110416","RP-130049","Ericsson","muhammad.kazmi@ericsson.com","RP#59 completed","25.101, 25.104, 25.133, 25.141",51,26,null,null,"2011-03-14","2013-02-27"]
[5250,510220,"   Perf. part: Further Enhancements to CELL_FACH","Cell_FACH_enh-Perf",2,"Rel-11","R4","2011-03-24","2013-12-06",1,"RP-111321","RP-131459","Qualcomm","Heechoon Lee (heechoon@qti.qualcomm.com)","RP#62 completed","25.101, 25.104, 25.133, 25.141",51,26,null,null,"2011-03-14","2013-11-29"]
[5254,530234,"   Perf. part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-Perf",2,"Rel-11","R4","2011-09-20","2013-09-06",1,"RP-111375","RP-130959","Nokia Siemens Networks","kamil.bechta@nsn.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",53,27,null,null,"2011-09-15","2013-08-29"]
[5257,530135,"   Core part: Four Branch MIMO transmission for HSDPA","4Tx_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2011-09-19","2012-12-07",1,"RP-111393","RP-121549","Ericsson","johan.hultell@ericsson.com","RP#58 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306",53,27,null,null,"2011-09-15","2012-11-27"]
[5260,540109,"   Core part: MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA-Core",2,"Rel-11","R1,R2,R3,R4","2011-12-09","2012-12-07",1,"RP-121794","RP-121554","Nokia Siemens Networks","Karri Ranta-aho","RP#58 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 25.423, 25.433, 26.306",54,28,null,null,"2011-12-07","2013-02-27"]
[5262,540024,"HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC",1,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","-","Ericsson","muhammad.kazmi@ericsson.com","Stage 3","UTRA",54,28,null,null,"2011-12-07","2012-09-04"]
[5263,540124,"   Core part: HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC-Core",2,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","RP-120987","Ericsson","muhammad.kazmi@ericsson.com","RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",54,28,null,null,"2011-12-07","2012-09-04"]
[5266,480004,"(Small) Technical Enhancements and Improvements for Rel-11","TEI11",1,"Rel-11","SP,CP,RP,GP","2010-06-18","2012-09-20",1,"-","-","-","-","SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs#","-",48,25,null,null,"2009-06-02","2010-12-13"]
[5270,450047,"Study on IMS based Peer-to-Peer Content Distribution Services","FS_IMS_P2P",1,"Rel-11","S1,S2","2009-09-11","2010-06-10",1,"SP-090491","-","China Mobile","Li Gang (ligangyf@chinamobile.com)","SP#48 completed. 3/3/15: start date corrected (was 05/09)",22.905999999999999,45,23,null,null,"2009-09-21","2015-03-03"]
[5273,490033,"Study on IMS Network-Independent Public User Identities","FS_INIPUI",1,"Rel-11","S1","2010-09-23","2011-06-08",1,"SP-100652","-","Vodafone","mona.mustapha@vodafone.com","SP#52 completed",22.893999999999998,49,25,null,null,"2010-09-21","2011-05-18"]
[5276,440048,"Study on IPv6 Migration","FS_IP6M",1,"Rel-11","S2","2009-06-04","2011-06-08",1,"SP-090362","-","China Mobile","Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com)","SP#52 completed",23.975000000000001,44,23,null,null,"2009-05-31","2011-05-26"]
[5279,380084,"Study on UTRAN key management enhancements","FS_UKM",1,"Rel-11","S3","2007-12-20","2012-03-07",1,"SP-090283","-","Ericsson","karl.norrman@ericsson.com","SP#55 completed",33.859000000000002,38,21,null,null,"2007-12-20","2012-11-20"]
[5282,480047,"Study on Management of Converged Networks","FS_ManCon",1,"Rel-11","S5","2010-06-10","2012-09-12",1,"SP-100377","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@nsn.com)","SP#57 completed. TR 32.833v200 for Approval",32.832999999999998,48,25,null,null,"2010-05-26","2012-08-30"]
[5283,490039,"Study on User Data Convergence (UDC) information model handling and provisioning: Example Use Cases","FS_UDC_AppUseCase",1,"Rel-11","S5","2010-09-23","2011-12-14",1,"SP-110127","-","Alcatel-Lucent","Nick Mazzarella (njmazzarella@alcatel-lucent.com)","SP#54 completed",32.901000000000003,49,25,null,null,"2010-09-03","2012-04-02"]
[5286,490014,"Study on EPC Nodes Restoration","FS_EPC_NR",1,"Rel-11","C4","2010-09-17","2012-12-07",1,"CP-100700","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed. Continue work in Rel-11 especially to cover handling of Idle mode Signalling Reduction (ISR). Linked to SA2 UID_490036 Study on Core Network Overload solutions",23.856999999999999,49,25,null,null,"2010-09-01","2012-11-14"]
[5289,480028,"Study on Signalling and procedure for interference avoidance for in-device coexistence","FS_SPIA_IDC",1,"Rel-11","R2,R4","2010-06-04","2011-09-16",1,"RP-100671","RP-111057","China Mobile","Zhenping Hu (huzhenping@chinamobile.com)","RP#53 completed. Studied coexistence scenario of LTE and Industrial, Scientific and Medical (ISM) Radio within the same device working in adjacent frequencies","LTE 36.816",48,25,null,null,"2010-06-01","2011-09-12"]
[5292,510039,"Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","FS_LTE_TDD_eIMTA",1,"Rel-11","R1,R4","2011-03-22","2012-06-15",1,"RP-110450","RP-120587","CATT","Zukang Shen (shenzukang@catt.cn)","RP#56 completed. TR 36.828 for Information and Approval","LTE 36.828",51,26,null,null,"2011-03-21","2012-06-09"]
[5295,550022,"Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology","FS_LTE_OTA",1,"Rel-11","R4","2012-03-05","2012-09-07",1,"RP-120412","RP-121083","CATR","Xudong An (anxudong@emcite.com)","RP#57 completed","LTE 25.914, New 37.902",55,28,null,null,"2012-02-23","2012-09-03"]
[5297,440016,"Study on Extending 850 MHz","FS_e850",1,"Rel-11","R4","2009-05-30","2012-09-07",1,"RP-090666","RP-121080","Ericsson","christian.bergljung@ericsson.com ","RP#57 completed. TR 37.806 v200 for Approval","UTRA, LTE 37.806",44,23,null,null,"2009-05-26","2012-09-04"]
[5301,510038,"Study on Interference analysis between 800~900 MHz bands","FS_B800_B900_Interf_LTE",1,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-111752","RP-120586","LG Uplus","Koo Yeon Sang (yskoo@lguplus.co.kr)","RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 ","UTRA, LTE impac37.804",51,26,null,null,"2011-03-21","2012-06-06"]
[5304,500015,"Study on HSDPA Multipoint Transmission","FS_HSDPA_MP_TX",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101439","RP-111049","Nokia Siemens Networks","karri.ranta-aho@nsn.com ","RP#53 completed","UTRA 25.872",50,26,null,null,"2010-12-08","2011-09-09"]
[5305,530057,"Study on UE Over The Air (OTA) test method with Head and Hand Phantoms","FS_OTA_phantoms_UTRA",1,"Rel-11","R4,R5","2011-09-19","2012-09-07",1,"RP-120208","RP-121078","Nokia","petri.j.vasenkari@nokia.com","RP#57 completed","UTRA 25.914",53,27,null,null,"2011-09-19","2012-09-06"]
[5308,0,"--- RELEASE 10 ---","-",1,"Rel-10","CP,GP,RP,SP","2008-12-11","2011-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[5311,460029,"   Stage 2 on enhancements for Multimedia Priority Service","ePRIOR-St2",2,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","-",46,24,null,null,"2009-12-06","2015-01-22"]
[5314,460529,"      Stage 2 on eMPS for IMS Aspects","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002, 23.203, 23.221, 23.228, 23.272, 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[5317,490108,"      CT4 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C4","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","23.008, 29.002, 29.228, 29.229, 29.272, 29.274, 29.277, 29.328, 29.329",49,25,null,null,"2010-09-01","2011-02-28"]
[5321,410031,"   Stage 1 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-100863","-","KPN","toon.norp@tno.nl","SP#47 completed","22.011, New 22.368",41,21,null,null,"2008-09-15","2010-03-09"]
[5323,490037,"   Stage 2 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S2","2010-08-30","2010-09-23",1,"SP-100863","-","Samsung","erik.guttman@partner.samsung.com","SP#49 completed","23.060, 23.236, 23.401",45,23,null,null,"2009-09-21","2010-12-13"]
[5326,480005,"   CN part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",2,"Rel-10","C1,C4,C6","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","Stage 3",48,25,null,null,"2010-05-26","2011-06-01"]
[5327,480105,"      CT1 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C1","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","23.122, 24.008, 24.301, New 24.368",48,25,null,null,"2010-05-26","2011-06-01"]
[5330,510005,"      CT6 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C6","2011-03-18","2011-06-03",1,"-","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#52 completed",31.102,51,26,null,null,"2011-03-10","2011-05-18"]
[5334,570004,"   UE Conformance Test Aspects - Network Improvements for Machine-Type Communications","NIMTC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-06-14",1,"RP-121124","RP-130465","Ericsson","calle.hagenfeldt@ericsson.com","RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024","34.123-1, 34.123-2, 34.123-3, 36.523-1, 36.523-2, 36.523-3 ",57,29,null,null,"2012-09-05","2013-06-03"]
[5336,430135,"   Stage 2 for Multi Access PDN Connectivity","MAPCON",2,"Rel-10","S2","2009-03-13","2010-09-23",1,"SP-090659","-","Telecom Italia","ivano.guardini@telecomitalia.it","SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control)","23.237, 23.401, 23.402",43,22,null,null,"2010-10-25","2010-10-25"]
[5339,500204,"      CT1 aspects of Multi Access PDN Connectivity","MAPCON-St3",3,"Rel-10","C1","2010-12-10","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed","24.302, 24.312",50,26,null,null,"2010-10-25","2011-02-28"]
[5343,450029,"   Stage 2 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-100167","-","Huawei","Lee Valerius (lvalerius@huawei.com)","SP#49 completed","23.237, 23.292, new 23.831",45,23,null,null,"2009-09-21","2010-09-06"]
[5346,450030,"IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",1,"Rel-10","S1,S2,C3","2009-09-24","2010-09-17",1,"SP-090615","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM","-",45,23,null,null,"2009-09-08","2010-03-09"]
[5347,450031,"   Stage 1 for CPM-SMS","CPM-SMS",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-090615","-","China Mobile","Qing Huang","SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C)",22.34,45,23,null,null,"2009-09-08","2010-03-09"]
[5349,460017,"   Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",2,"Rel-10","C3","2009-12-04","2010-09-17",1,"CP-090859","-","Ericsson","Jan Holm","CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204",29.311,46,24,null,null,"2009-11-30","2010-09-01"]
[5352,470002,"   CT1 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#51 completed","24.173, 24.642",47,24,null,null,"2010-03-17","2011-02-14"]
[5356,450036,"   TR on Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S2","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#51 completed. TR 23.829 for Approval","New 23.829",45,23,null,null,"2009-09-08","2010-12-01"]
[5358,450040,"   OAM&P for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S5","2009-09-24","2011-03-23",1,"SP-110131","-","Huawei, China Mobile","Zou Lan (zlan@huawei.com), Chen Gang (chengang@chinamobile.com)","SP#51 completed. Updated WID SP-100696=>SP-110131","32.581, 32.582, 32.584, 32.591, 32.592, 32.642, 32.646, 32.772, 32.782",45,23,null,null,"2009-09-08","2011-03-17"]
[5361,450338,"      Stage 2 for Local IP Access","LIPA",3,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#49 completed (has impacts to RAN)","23.060, 23.401",45,23,null,null,"2009-09-08","2010-09-06"]
[5365,450038,"   Stage 2/3 for SIPTO for macro networks","SIPTO",2,"Rel-10","S2,C4,C1","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","-","-",45,23,null,null,"2009-09-08","2010-12-01"]
[5368,480107,"         CT4 part of Stage 3 for SIPTO for macro networks","SIPTO",4,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","23.003, 23.008, 29.002, 29.272, 29.303",48,25,null,null,"2010-05-26","2011-03-08"]
[5369,480207,"         CT1 part of Stage 3 for SIPTO for macro networks","SIPTO",4,"Rel-10","C1","2010-06-04","2010-12-10",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#50 completed","24.008, 24.301",48,25,null,null,"2010-05-26","2011-03-08"]
[5371,450042,"   Stage 1 for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S1","2009-09-24","2009-12-10",1,"SP-100089","-","Qualcomm","David Williams (dwilliam@qualcomm.com)","SP#46 completed",22.277999999999999,45,23,null,null,"2009-09-08","2010-10-01"]
[5374,480009,"   Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",2,"Rel-10","C1,C3","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","Stage 3",48,25,null,null,"2010-05-26","2010-12-09"]
[5378,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[5381,490038,"   SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S4","2010-09-23","2011-03-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#51 completed",26.114000000000001,49,25,null,null,"2010-09-14","2011-02-18"]
[5384,531006,"      (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3-IETF,C4-IETF","2009-07-15","2012-09-07",1,"CP-100702","-","Lionel Morand","-","CP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",53,27,null,null,"2011-08-31","2012-09-03"]
[5387,450053,"Extended H(e)NB features","EHNBF",1,"Rel-10","S1,S2,S3","2008-12-11","2010-09-23",1,"SP-100407","-","NEC","joerg.swetina@neclab.eu","SP#49 completed. Adds extensions to Rel-9 functionality in UID_400035 Enhanced Home NodeB / eNodeB (EHNB)","UTRA, LTE",45,23,null,null,"2009-09-08","2010-07-23"]
[5390,480034,"   Extended H(e)NB Security features (Stage 2)","EHNBF-Sec",2,"Rel-10","S3","2010-06-10","2010-09-23",1,"SP-100257","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#49 completed",33.32,48,25,null,null,"2010-05-05","2010-07-23"]
[5391,460028,"Optimal Media Routing","OMR",1,"Rel-10","S2,S5,C3,C1","2010-03-25","2011-06-08",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","CP#52 completed. SP#47 Stage 2 completed. Triggered by TR 23.894 (UID_370050 Study on System enhancements for the use of IMS servicES in CP-150local breakout)","-",46,24,null,null,"2009-12-06","2011-05-17"]
[5395,480210,"      CT1 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 completed. WID updated CP-100327=>CP-110134",24.228999999999999,48,25,null,null,"2010-05-26","2011-03-10"]
[5396,480310,"      Deleted - CT4 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134","-",48,25,"CP-51","PCG-26","2010-05-26","2011-03-10"]
[5400,470028,"   Stage 2 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","SP#49 completed",23.167000000000002,47,24,null,null,"2010-03-10","2010-09-06"]
[5403,480137,"   Stage 2 for S2b Mobility based on GTP","SMOG",2,"Rel-10","S2","2010-06-10","2010-09-23",1,"SP-100357","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#49 completed","23.002, 23.203, 23.402",48,25,null,null,"2010-06-06","2010-09-06"]
[5407,490309,"      CT1 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C1","2010-09-17","2010-12-10",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#50 completed",24.302,49,25,null,null,"2010-09-01","2010-11-25"]
[5408,500006,"Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST",1,"Rel-10","S2,C3","2010-10-12","2011-03-18",1,"SP-110196","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user","-",50,26,null,null,"2010-11-26","2011-03-19"]
[5412,470129,"   LI for CAT (Customer Alerting Tones)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5413,470229,"   LI for CRS (Customized Ringing Signal)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5416,470529,"   LI for MEDIASEC (IMS Media security)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5419,470829,"   LI for LCLS (Local Call Local Switch)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5422,470134,"   HTTP-based Streaming and Download Services in 3GPP","HTTP_SDS",2,"Rel-10","S4","2010-03-25","2011-06-08",1,"SP-100032","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#52 completed","26.234, 26.244, 26.346, new 26.247",47,24,null,null,"2010-03-10","2011-05-26"]
[5425,480041,"Enhancements and Addition of Audio Tests to 26.131 and 26.132","EAAT",1,"Rel-10","S4","2010-06-10","2011-06-08",1,"SP-100306","-","Vodafone","ramin.afchar@vodafone.com","SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec","26.131, 26.132",48,25,null,null,"2010-05-28","2011-05-17"]
[5429,460033,"      Common RAT Network Resource Model (NRM)","RAT_NRM_common",3,"Rel-10","S5","2009-12-10","2011-06-08",1,"SP-100293","-","Ericsson","robert.petersen@ericsson.com ","SP#52 completed. Share equipment btw several RATs (RET,TMA,repeaters) to reduce costs. With existing modelling is difficult to see that several cells are affected when an antenna tilt is changed etc","32.616, 32.642, 32.646, 32.652, 32.656, 32.762, 32.766 new (32.791, 32.792, 32.796)",46,24,null,null,"2009-12-01","2011-05-16"]
[5430,470035,"      IRP Solution Set specification organisation improvements","OAM-IRP-SS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100774","-","Nokia Siemens Networks, Huawei","Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) ","SP#51 completed","32.153, new (32.111-6,32.126,32.176,32.306,32.316,32.326,32.336,32.346,32.356,32.366,32.376,32.386,32.396,32.416,32.446,32.506/26/36,32.606,32.616,32.626,32.636,32.646,32.656,32.666,32.676,32.696,32.716,32.726,32.736,32.746,32.756,32.766,32.776,32.786)",47,24,null,null,"2010-02-12","2011-03-09"]
[5434,510042,"      Inventory Management Network Resource Model enhancements","OAM-IM-NMR",3,"Rel-10","S5","2011-03-23","2011-06-08",1,"SP-110141","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items","32.690, 32.691, 32.692, 32.696",51,26,null,null,"2011-03-09","2011-05-16"]
[5435,460034,"   Rel-10 Self-Organizing Networks (SON) - OAM aspects","OAM10-SON",2,"Rel-10","S5","2009-12-10","2011-06-08",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[5438,470037,"      OAM aspects of Energy Saving in Radio Networks","OAM-ES",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-110128","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management¦Energy Savings Management (FS_OAM_ESM) UID_430044","32.425, 32.522, 32.526, 32.626, 32.762, 32.766, new 32.551",47,24,null,null,"2010-02-12","2011-03-17"]
[5442,470041,"      Key Performance Indicators (KPIs) for EPC","OAM-PM-KPI_EPC",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100084","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#51 completed","new 32.455",47,24,null,null,"2010-02-12","2011-03-09"]
[5445,510006,"         CN aspects of Management of UE based network performance measurements","-",4,"Rel-10","C4","2011-02-21","2011-03-18",1,"-","-","Nokia Siemens Networks","ulrich.wiehe@nsn.com ","CP#51 completed under the SA5 WI code","23.008 (CR#0330), 29.002 (CR#1007), 29.230 (CR#0207), 29.272 (CR#0329)",51,26,null,null,"2011-02-28","2011-02-28"]
[5447,470044,"Rel-10 Charging Management small Enhancements","CH10",1,"Rel-10","S5","2009-06-04","2011-03-23",1,"-","-","-","-","CH10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI",30.82,47,24,null,null,"2010-02-12","2010-02-12"]
[5451,490010,"   CT1 part - AoC enhancements (Stage 3)","eAoC",2,"Rel-10","C1","2010-09-17","2011-06-03",1,"CP-100645","-","Deutsche Telekom","reinhard.lauster@t-mobile.at","CP#52 completed. SA1 Stage 1 in 22.115, 22.173, 22.024. Add mobile-specific CAI format and volume charging elements. Extensions to existing AoC XML",24.646999999999998,49,25,null,null,"2010-09-07","2011-05-23"]
[5454,480014,"Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications","II-NNI2",1,"Rel-10","C3","2010-06-04","2013-03-01",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI)","-",48,25,null,null,"2010-05-26","2013-02-21"]
[5456,561001,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6794)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2013-03-01",1,"CP-100326","-","Lionel Morand","Lionel Morand","CP#59 completed AUTH 48 RFC-to-be-6794","RFC 6794 (was draft-ietf-sip-session-policy-framework)",56,29,null,null,"2012-04-20","2013-02-21"]
[5457,561002,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6809)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2012-12-07",1,"CP-100326","-","christer.holmberg@ericsson.com","Christer Holmberg","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",56,29,null,null,"2012-04-20","2012-12-04"]
[5460,490012,"Communication Control for IMS by USIM (Stage 3)","CC_IMS_USIM",1,"Rel-10","C6","2010-09-17","2011-03-18",1,"CP-100647","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed. Stage 1 in TS 22.038 USAT service description. Linked to CT6's UID_1273 Rel-5 BB Provisioning of IP-based multimedia services (24.229, 31.103) and UID_390021 Rel-8 BB CT6 aspects of SAE (31.102, 31.111)","31.102, 31.103, 31.111",49,25,null,null,"2010-09-06","2011-03-03"]
[5464,500010,"Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3)","eSRVCC",1,"Rel-10","C1,C4,IETF","2010-12-10","2012-12-07",1,"CP-100881","-","China Mobile","Jiang Y (jiangyi@chinamobile.com)","Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049","-",50,26,null,null,"2010-10-25","2013-02-21"]
[5467,521003,"   (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809)","eSRVCC",2,"Rel-10","C1-IETF","2010-12-10","2012-12-07",1,"CP-100881","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",52,27,null,null,"2011-06-20","2013-02-21"]
[5469,500111,"   CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3)","aSRVCC",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-110145","-","ZTE","li.shitao@zte.com.cn","CP#52 completed","24.008, 24.237",50,26,null,null,"2011-03-16","2011-05-23"]
[5473,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212, 29.213, 29.214, 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[5476,510008,"EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated","EPC_NR",1,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110092","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014","Stage 2/3: 23.007, 29.274",51,26,null,null,"2011-02-22","2011-03-18"]
[5479,510010,"UICC access to IMS Specification","IMS-UICC-S",1,"Rel-10","C6,C1","2011-03-16","2011-06-03",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC","-",51,26,null,null,"2011-03-03","2011-05-18"]
[5480,510110,"   CT6 part of UICC access to IMS Specification","IMS-UICC-S",2,"Rel-10","C6","2011-03-16","2011-03-18",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed","31.102, 31.103, 31.111",51,26,null,null,"2011-03-03","2011-03-10"]
[5482,550006,"Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features","USIM_R10_Test",1,"Rel-10","C6","2012-03-05","2013-12-03",1,"CP-120396","-","Gemalto","Denis.Praca@gemalto.com","CP#62 stopped (at 70% completion 06/13). Testing for New featurES in CP-150Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111","31.121, 31.124, New 31.ABC (Conformance Testing of specific features)",55,28,"CP-62","PCG-32","2012-02-22","2013-06-06"]
[5486,440023,"   Deleted - CT3 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C3","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT3 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[5489,480002,"Tightened Link Level Performance Requirements for Single Antenna MS","TIGHTER",1,"Rel-10","G1,G2,C1,G3new","2010-09-03","2013-03-01",1,"GP-101083","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#46 approved WID","GERAN",46,25,null,null,"2010-05-27","2013-03-16"]
[5491,480202,"   TIGHTER Performance Requirements","TIGHTER",2,"Rel-10","G1,G2","2010-09-03","2011-05-20",1,"GP-101084","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#50 completed","45.005, 45.015",46,25,null,null,"2010-05-27","2011-05-21"]
[5495,490201,"   CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",2,"Rel-10","C1","2010-05-21","2010-12-10",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#50 completed","24.008 CR#1644",47,25,null,null,"2010-05-27","2011-03-04"]
[5498,490102,"   GERAN part for Enhancements of Iur-g interface (Stage 2/3)","eIurg-GERAN",2,"Rel-10","G2","2010-09-03","2011-03-04",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#49 completed. GP#48 updated WID GP-101659=>GP-101758 (restricting the scope to GERAN BSC and TD-SCDMA RNC only). GP#47 approved WID","43.130, 48.008",47,25,null,null,"2010-09-05","2011-03-04"]
[5499,490021,"   Core part: Enhancements of Iur-g interface (Stage 2/3)","eIurg-RAN",2,"Rel-10","R3","2010-09-03","2011-06-03",1,"RP-101232","RP-110526","ZTE","Liu Junqiang (liu.junqiang@zte.com.cn)","RP#52 completed","UTRA Stage 2 (25.401, 25.420), Stage 3 (25.423)",49,25,null,null,"2010-09-05","2011-05-26"]
[5502,460014,"1.28 Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF",1,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","-","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866)","UTRA",46,24,null,null,"2009-11-30","2010-12-03"]
[5506,470112,"   Core part: MU-MIMO for 1.28Mcps TDD","MUMIMO_LCR_TDD-Core",2,"Rel-10","R1,R2,R3","2010-03-19","2010-12-10",1,"RP-100347","RP-101085","CATT","Yanping Xing (xingyanping@datangmobile.cn)","RP#50 completed","25.221, 25.222, 25.224, 25.306, 25.308, 25.319, 25.331, 25.423, 25.425, 25.433, 25.435",47,24,null,null,"2010-03-19","2010-12-03"]
[5508,450027,"AGNSS Minimum Performance for UTRAN","AGNSSPerf_UTRAN",1,"Rel-10","R4,R5","2009-09-18","2011-09-16",1,"RP-100363","-","Thales","Michel.monnerat@thalesaleniaspace.com","RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures)","UTRA",45,23,null,null,"2009-09-15","2010-12-08"]
[5511,460005,"Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN","LCS_UMTS_RFPMT",1,"Rel-10","R2,R3","2009-12-04","2011-03-18",1,"RP-091427","RP-110048","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907)","UTRA",46,24,null,null,"2009-11-30","2011-03-11"]
[5514,460115,"   Core part: Four carrier HSDPA","4C_HSDPA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-03-18",1,"RP-100991","RP-110046","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#51 completed. RP#52 TR 25.864 v200 for Approval","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306, new 25.864",46,24,null,null,"2009-11-30","2011-05-27"]
[5517,470013,"Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD",1,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-100168","-","TD Tech","dafei.wang@td-tech.com","Stage 3. RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2011-06-01"]
[5520,480020,"Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN",1,"Rel-10","R3,R2,R5","2010-06-04","2012-12-07",1,"RP-100688","-","ZTE","Zhai.hengxing@zte.com.cn","RP#52 Core completed. Automatic Neighbour Relation (ANR) function for UTRAN relieves operators from the burden of manually managing the Neighbour cell Relations (NRs)","UTRA",48,25,null,null,"2010-06-03","2013-04-15"]
[5521,480120,"   Core part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-Core",2,"Rel-10","R3,R2","2010-06-04","2011-06-03",1,"RP-100688","RP-110522","ZTE","Zhai.hengxing@zte.com.cn","RP#52 completed","25.331, 25.413, 25.423, new 25.484 (Stage 2)",48,25,null,null,"2010-06-03","2011-05-31"]
[5524,480121,"   Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100657","RP-110523","AT&T","Vince Spatafora (vs5785@att.com)","RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",48,25,null,null,"2010-06-03","2011-05-24"]
[5527,490023,"   Core part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-Core",2,"Rel-10","R4","2010-09-17","2011-06-03",1,"RP-100993","RP-110524","Qualcomm","Heechoon Lee","RP#52 completed",25.103999999999999,49,25,null,null,"2010-09-10","2011-05-27"]
[5530,490022,"Interfrequency detected set measurements for UMTS","Interf_dset_meas_UMTS",1,"Rel-10","R2,R4","2010-09-17","2010-12-10",1,"RP-101015","RP-101093","Nokia","Chris.callender@nokia.com","RP#50 completed","UTRA 25.133, 25.331",49,25,null,null,"2010-09-11","2010-12-08"]
[5533,460207,"   Perf. part: Carrier Aggregation for LTE","LTE_CA-Perf",2,"Rel-10","R4","2009-12-04","2011-12-09",1,"RP-100661","RP-111452","Nokia","lars.e.lindh@nokia.com","RP#54 completed","36.101, 36.104, 36.133, 36.141, 37.141",46,24,null,null,"2009-11-30","2012-06-07"]
[5537,460208,"   Perf. part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Perf",2,"Rel-10","R4","2009-12-04","2012-03-02",1,"RP-091429","RP-120053","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#55 completed","36.101, 36.104, 36.133, 36.141",46,24,null,null,"2009-11-30","2012-02-23"]
[5540,460109,"   Core part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-Core",2,"Rel-10","R1,R2,R4","2000-01-03","2001-06-29",1,"RP-100959","RP-110537","Huawei","Mattias.wennstrom@huawei.com","RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 (36.807, 36.817)",46,24,null,null,"2009-11-30","2012-06-07"]
[5541,460209,"   Perf. part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-Perf",2,"Rel-10","R4","2009-12-04","2011-09-16",1,"RP-100959","RP-110992","Huawei","Mattias.wennstrom@huawei.com","RP#53 completed","36.101, 36.104, 36.133, 36.141, 36.817",46,24,null,null,"2009-11-30","2011-09-12"]
[5543,460013,"Relays for LTE","LTE_Relay",1,"Rel-10","R1,R2,R4,S2,S3,C4,C6","2009-12-04","2011-06-08",1,"RP-110911","-","Ericsson","christian.hoymann@ericsson.com","RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11)","LTE",46,24,null,null,"2009-11-30","2011-02-14"]
[5546,520020,"   Stage 2 for Relays for LTE","LTE_Relay",2,"Rel-10","S2","2011-06-06","2011-06-08",1,"-","-","Vodafone","chris.pudney@vodafone.com","SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview",23.401,52,27,null,null,"2011-06-06","2011-06-06"]
[5549,500138,"      Security for LTE Relay Nodes (Stage 2)","LTE_Relay-Sec",3,"Rel-10","S3","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","SP#51 completed (impacting Stage 3 in CT and RAN)","33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413",50,26,null,null,"2010-11-25","2011-02-14"]
[5552,470007,"Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE",1,"Rel-10","R1,R2,R3,R4,R5","2010-03-19","2014-06-13",1,"RP-100383","-","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#56 completed","LTE",47,24,null,null,"2010-03-19","2011-03-14"]
[5555,550001,"   Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-UEConTest",2,"Rel-10","R5","2012-03-05","2014-06-13",1,"RP-120217","RP-140766","Qualcomm","Anjali Mishra (ajha@qualcomm.com)","RP#64 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",55,28,null,null,"2012-02-23","2014-06-10"]
[5559,480019,"   UE conformance test part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-UEConTest",2,"Rel-10","R5","2010-06-04","2010-12-10",1,"RP-100615","RP-101071","Clearwire","michael.hart@clearwire.com","RP#50 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",48,25,null,null,"2010-06-01","2010-12-03"]
[5562,470209,"   Perf. part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-110775","RP-110546","DBSD","Mariam.Sorond@ico.com","RP#52 completed","36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.811",47,24,null,null,"2010-03-19","2011-06-01"]
[5565,470110,"   Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Core",2,"Rel-10","R4,R2","2009-12-11","2010-12-10",1,"RP-101284","RP-101117","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#51 completed","25.101, 25.104, 25.141, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new RAN4 36.813",47,24,null,null,"2010-03-19","2011-03-17"]
[5567,510015,"   Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-03-18","2011-09-16",1,"RP-110777","RP-110980","LightSquared","masoud.olfat@lightsquared.com","RP#53 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2",51,26,null,null,"2011-03-10","2011-09-06"]
[5568,470011,"LTE Self Optimizing Networks (SON) enhancements","SONenh_LTE",1,"Rel-10","R3,R2,R4","2010-03-19","2011-06-03",1,"RP-101004","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#52 completed","LTE",47,24,null,null,"2010-03-19","2011-05-24"]
[5571,480127,"   Core part: Further enhancements to MBMS for LTE","MBMS_LTE_enh-Core",2,"Rel-10","R2,R3","2010-06-04","2011-03-18",1,"RP-101244","RP-110083","Huawei","Ms Zhao Junhui (zhaojh@huawei.com)","RP#51 completed","25.446, 36.300, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445",48,25,null,null,"2010-06-04","2011-03-14"]
[5575,420013,"   Conformance Test Aspects – LTE 3500","LTE-UEConTest_LTE3500",2,"Rel-10","R5","2008-12-05","2013-06-14",1,"RP-080859","RP-130461","Ericsson","fredrik.sundstrom@ericsson.com","RP#60 completed","36.508, 36.521-1, 36.521-2, 36.521-3",42,22,null,null,"2008-11-27","2013-06-03"]
[5578,460103,"   Core part: Minimization of Drive Tests for E-UTRAN and UTRAN","MDT_UMTSLTE-Core",2,"Rel-10","R2,R4,R3","2009-12-04","2011-06-03",1,"RP-100360","RP-110528","Nokia Siemens Networks","malgorzata.tomala@nsn.com","RP#52 completed","25.133, 25.215, 25.304, 25.331, 25.423, 36.133, 36.214, 36.300, 36.304, 36.331, 36.413, 36.423, new 37.320 (Stage 2)",46,24,null,null,"2009-11-30","2011-05-24"]
[5581,470105,"   Core part: HNB and HeNB Mobility Enhancements","HNB_HENB_mob_enh-Core",2,"Rel-10","R3,R2","2010-03-19","2011-03-18",1,"RP-110183","RP-110058","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#51 completed","25.413, 25.467, 25.469, 36.300, 36.413, 36.423, new 25.471",47,24,null,null,"2010-03-19","2011-03-11"]
[5584,480124,"   Core part: Expanded 1900 MHz Band for UTRA and LTE","E1900-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100676","RP-110529","Sprint","nick.j.baustert@sprint.com","RP#52 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new 36.818",48,25,null,null,"2010-06-04","2011-05-24"]
[5587,480025,"Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments","MSR_NC",1,"Rel-10","R4,G1","2010-06-04","2011-11-25",1,"RP-101402","-","Ericsson","johan.skold@ericsson.com","-","UTRA, LTE, GERAN",48,25,null,null,"2010-06-04","2011-09-12"]
[5588,480125,"   Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-Core",2,"Rel-10","R4","2010-06-04","2011-06-03",1,"RP-101402","RP-110531","Ericsson","johan.skold@ericsson.com","RP#52 completed","25.104, 36.104, 37.104, new 37.802",48,25,null,null,"2010-06-04","2011-06-01"]
[5591,490104,"      GERAN Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-GERAN",3,"Rel-10","G1","2010-09-03","2011-09-02",1,"GP-101618","-","Ericsson","mats.y.samuelsson@ericsson.com ","GP#51 completed. GP#47 approved WID",45.005000000000003,47,25,null,null,"2010-09-05","2011-05-21"]
[5594,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[5597,350014,"Deleted - Registration in Densely-populated area (RED)","RED",1,"Rel-10","S1","2007-03-12","2009-09-24",1,"SP-070133","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned","-",35,18,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[5600,380062,"Deleted - Network Selection for non-3GPP Access","N3GtoNSP",1,"Rel-10","S1,C6","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned","-",38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[5602,380262,"   Deleted - CT6 issues for N3GtoNSP","N3GtoNSP",2,"Rel-10","C6","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",36.299999999999997,38,21,"CP-45","PCG-23","2007-12-13","2009-09-21"]
[5606,440043,"Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9","eEHNB",1,"Rel-10","S2","2008-12-11","2010-03-25",1,"-","-","Alcatel-Lucent","Nicolas Drevon","SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB)","-",44,23,"SP-47","PCG-24","2007-12-13","2009-06-01"]
[5609,460210,"   Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-UEConTest",2,"Rel-10","R5","2009-12-04","2011-06-03",1,"RP-091432","RP-110504","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions)","36.521-1",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[5610,460012,"Deleted - Latency reductions for LTE","LTE_LATRED",1,"Rel-10","R2,R1","2009-12-04","2010-12-10",1,"RP-091449","-","Ericsson","henrik.enbuske@ericsson.com","RP#50 work stopped (RP-101266)","LTE",46,24,"RP-50","PCG-26","2009-11-30","2010-12-08"]
[5613,470106,"   Deleted - Core part: Enhanced Interference Management for Home NodeBs","HNB_IM-Core",2,"Rel-10","R3","2010-03-19","2010-09-17",1,"RP-100392","RP-100754","Qualcomm","Andrei Radulescu (aradules@qualcomm.com)","RP#49 stopped (no further standardization needed)","25.413, 25.467, 25.469",47,24,"RP-49","PCG-25","2010-03-19","2010-09-09"]
[5616,370047,"   Use cases definition and service and system requirements","FS_EV_EPS-S1",2,"Rel-10","S1","2007-09-03","2008-12-11",1,"SP-070698","-","France Telecom","philippe.lottin@orange.com","SP#47 completed. TR 22.813-100 for Approval",22.812999999999999,37,19,null,null,"2007-10-04","2010-08-31"]
[5619,410039,"Study on Personal Broadcast Service","FS_PBS",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080504","-","ETRI","Jaihyung Cho","SP#47 completed",22.946999999999999,41,21,null,null,"2008-09-15","2010-03-09"]
[5622,370050,"Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media","FS_IMS_LBO_ORM",1,"Rel-10","S2","2007-10-01","2009-12-10",1,"SP-080556","-","Telecom Italia, BT","mario.madella@telecomitalia.it, victor.kueh@bt.com","SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011",23.893999999999998,37,19,null,null,"2007-10-02","2009-11-25"]
[5626,470049,"Study on S2b Mobility based on GTP","FS_SMOG",1,"Rel-10","S2","2010-03-25","2010-06-10",1,"SP-100169","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101",23.834,47,24,null,null,"2010-03-10","2010-06-07"]
[5628,480044,"Study on Improved Video Coding Support","FS_IVCS",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100304","-","Nokia, ETRI","imed.bouazizi@nokia.com, jaihyung@etri.re.kr","SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039)",26.904,48,25,null,null,"2010-05-28","2011-02-18"]
[5631,440069,"Study on Integration of Device Management Information with Itf-N","FS_IDMI_Itf-N",1,"Rel-10","S5","2009-06-04","2010-03-25",1,"SP-100088","-","Motorola","Yizhi Yao (yzyao@motorola.com)","SP#47 completed",32.826999999999998,44,23,null,null,"2009-05-18","2010-03-23"]
[5632,460037,"Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model","FS_3GNRM_TMFSID",1,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-090759","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#51 completed",32.828000000000003,46,24,null,null,"2009-12-01","2011-03-09"]
[5635,480046,"Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM","FS_3G_TMF_PM",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100291","-","Alcatel-Lucent","Padma.Sudarsan@alcatel-lucent.com ","SP#51 completed",32.831000000000003,48,25,null,null,"2010-05-26","2011-03-22"]
[5639,450014,"Study on Uplink Tx Diversity for HSPA","FS_UL-TxDiv-HSPA",1,"Rel-10","R4","2009-08-18","2010-06-04",1,"RP-090987","RP-100499","Qualcomm","Heechoon Lee (heechoon@qualcomm.com)","RP#48 completed","UTRA 25.863",45,23,null,null,"2009-09-15","2010-06-01"]
[5641,470015,"Study on Potential solutions for energy saving for E-UTRAN","FS_Energy_LTE",1,"Rel-10","R3,R2","2010-02-02","2011-06-03",1,"RP-100674","RP-110597","China Mobile","Yang Ning (yangning@chinamobile.com)","RP#52 completed","LTE 36.927",47,24,null,null,"2010-03-19","2011-06-02"]
[5644,410042,"Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services","FS_eIMS_IBCF",1,"Rel-10","S2","2008-09-18","2010-12-15",1,"SP-090809","-","Starent Networks","Rajat Ghai (rghai@starentnetworks.com)","SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS)",23.847999999999999,41,21,"SP-50","PCG-26","2008-09-15","2010-12-13"]
[5648,400035,"Enhanced Home NodeB / eNodeB","EHNB",1,"Rel-9","S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP","2008-06-05","2011-12-09",1,"SP-090214","-","T-Mobile","michael.kurz@t-mobile.at ","RP#54 Testing completed","UTRA, LTE",40,21,null,null,"2007-12-13","2011-11-29"]
[5651,420035,"   Security aspects of Enhanced Home NodeB / eNodeB","EHNB-Sec",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080879","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#46 completed","New 33.320",42,22,null,null,"2008-12-09","2009-12-07"]
[5652,450003,"   CT1 aspects - Support of Home NB and Home eNB enhancements","EHNB-CT1",2,"Rel-9","C1","2009-09-18","2010-12-10",1,"CP-090741","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#50 completed (Roaming aspects for manual CSG selection, Support of temporary users and CSG membership changes, Support of user controlled and operator controlled lists)","23.122, 24.008, 24.285, 24.301",45,23,null,null,"2009-07-09","2010-11-25"]
[5654,420036,"   3G HNB Gateway and LTE HeNB Gateway OAM&P","HNB-OAM_GW",2,"Rel-9","S5","2008-12-11","2010-03-25",1,"SP-100087","-","China Mobile","GangChen (chengang@chinamobile.com)","SP#47 completed","32.632, 32.633, 32.635, New (32.771, 32.772, 32.773, 32.775, 32.781, 32.782, 32.783, 32.785)",42,22,null,null,"2008-12-03","2010-03-22"]
[5657,420008,"   LTE FDD Home eNodeB RF Requirements","HeNB-RF_FDD",2,"Rel-9","R4","2008-12-05","2010-03-19",1,"RP-091300","RP-100035","Motorola ","Ying Cai (yingcai@motorola.com)","RP#47 completed","36.104, 36.141, New 36.921",42,22,null,null,"2008-12-04","2010-03-16"]
[5661,490020,"   Conformance Test Aspects – Home NB enhancements for FDD","EHNB-UTRA_FDD_UEConTest",2,"Rel-9","R5","2010-09-17","2011-12-09",1,"RP-111315","RP-111679","Huawei","trica_li@huawei.com","UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367)","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-09","2011-12-07"]
[5663,440001,"   Home NB and Home eNB enhancements - GERAN aspects","EHNB-GERAN",2,"Rel-9","GP","2009-05-18","2010-09-03",1,"GP-090975","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk ","GP#47 completed. GP#42 WID approved","43.055, 43.129, 44.018, 44.060, 45.008, 48.008, 48.018",42,23,null,null,"2009-05-18","2010-09-04"]
[5666,410011,"   CT4 aspects of VAS4SMS Interface and Signalling Flow","VAS4SMS",2,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090813","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed","new 23.142",41,21,null,null,"2008-09-11","2009-12-02"]
[5670,380067,"Customized Ringing Signal","CRS",1,"Rel-9","S1,C1","2007-12-06","2009-12-03",1,"SP-080502","-","SK Telecom, China Mobile","Donghee Shim (SK Telecom), Jianping Zheng (China Mobile)","CP#48 completed","-",38,21,null,null,"2007-12-13","2010-05-28"]
[5673,380057,"Public Warning System","PWS",1,"Rel-9","S1,C1,C4,R2,R3,R5","2007-12-06","2012-12-07",1,"SP-070876","-","T-Mobile","Mark.Younge@t-mobile.com","TSG#46 completed. Larger scope than Rel-8 Feature UID_370051 (ETWS). Triggered by TR 22.968 Study UID_320025 (FS_PWS)","LTE",38,21,null,null,"2007-12-13","2009-12-03"]
[5674,380058,"   Stage 1 for Public Warning System","PWS",2,"Rel-9","S1","2007-12-06","2008-12-11",1,"SP-070876","-","T-Mobile","Mark.Younge@t-mobile.com","SP#42 completed",22.268000000000001,38,21,null,null,"2007-12-13","2008-12-05"]
[5676,440030,"      CT1 aspects of Stage 3 for Public Warning System","PWS-St3",3,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#46 completed",23.041,44,23,null,null,"2009-05-13","2009-12-03"]
[5679,540005,"   Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE","PWS-RAN_UEConTest",2,"Rel-9","R5","2011-12-02","2012-12-07",1,"RP-111564","RP-121525","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#58 completed","36.508, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2012-12-04"]
[5683,430102,"   Stage 3 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-09","2010-06-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#48 completed",24.259,43,22,null,null,"2009-03-05","2010-05-28"]
[5686,430031,"   Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services)","eMMTel-SS-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090196","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#47 completed","32.275, 32.298, 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[5689,400034,"User Data Convergence (UDC)","UDC",1,"Rel-9","S1,S5,C4","2008-06-05","2010-06-10",1,"SP-080448","-","Nokia Siemens Networks","juergen.merkel@nsn.com ","SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808","-",40,21,null,null,"2007-12-13","2010-08-31"]
[5692,430003,"      User Data Convergence (UDC) Technical Realization (Stage 2)","UDC-CN",3,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","CP#47 completed","new 23.335",43,22,null,null,"2009-03-04","2010-03-09"]
[5695,440062,"      UDC – Framework for Model Handling and Management","UDC-MMAN-MFRM",3,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090311","-","T-Mobile","istvan.aba@t-mobile.at","SP#48 completed","32.172, new 32.181",44,23,null,null,"2009-05-18","2010-05-26"]
[5696,440061,"      UDC – Common Baseline Information Model","UDC-MMAN-CBIM",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090310","-","China Mobile, Ericsson","Lan Si Zhong, Miguel Garcia","SP#47 completed","32.172, new 32.182 ",44,23,null,null,"2009-05-18","2010-03-08"]
[5700,410034,"      Stage 2 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",3,"Rel-9","S2","2008-09-18","2009-06-04",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","SP#57 Removal of the MSC server assisted mid-call feature from Rel-9 by 23.237CR#0433 (CT1 proposed moving this feature to Rel-10). SP#44 completed. TR 23.838 for Approval","23.237, 23.292, 23.216, new 23.838",41,21,null,null,"2008-09-15","2012-07-20"]
[5701,440034,"      Stage 3 for IMS Service Continuity Enhancements: Service, Policy, Interactions and Inter UE Transfer","IMS_SCC-SPI",3,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090440","-","Qualcomm","Roozbeh Atarius (ratarius@qualcomm.com)","CP#47 completed","24.216, 24.229, 24.237",44,23,null,null,"2009-05-13","2010-03-02"]
[5705,430004,"   Stage 3 - IMS Centralized Services support via I1 interface","IMS_SCC-ICS_I1",2,"Rel-9","C1","2009-03-06","2010-03-19",1,"CP-090640","-","Huawei","Lili Yang(kadyyang@huawei.com)","CP#47 completed","24.237, 24.292, new 24.294",43,22,null,null,"2009-03-05","2010-03-02"]
[5708,440040,"   Stage 3 for Service Specific Access Control in EPS","SSAC",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090885","-","NTT DoCoMo","Hideyuki Yamashita (yamashitahi@s1.nttdocomo.co.jp)","CP#47 completed","24.173, 27.007",44,23,null,null,"2009-05-13","2010-03-02"]
[5712,410037,"   Stage 2 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",2,"Rel-9","S2","2008-01-14","2009-06-04",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#44 completed","23.869, 23.060, 23.167, 23.203, 23.221, 23.228, 23.271, 23.401, 23.402",38,21,null,null,"2008-09-15","2009-06-01"]
[5713,420022,"   Security aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS-Sec",2,"Rel-9","S3","2008-12-12","2010-06-10",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#48 completed","33.401, 33.402",42,22,null,null,"2008-12-09","2010-05-05"]
[5717,440037,"      CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC3",3,"Rel-9","C3","2009-05-29","2009-09-18",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#45 completed","29.212, 29.213, 29.214, 29.215",44,23,null,null,"2009-05-13","2009-09-09"]
[5718,440038,"      CT4 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC4",3,"Rel-9","C4","2009-05-29","2009-12-04",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#46 completed","23.003, 23.008, 29.060, 29.272, 29.273, 29.274, 29.275, 29.276",44,23,null,null,"2009-05-13","2009-11-16"]
[5721,410038,"   Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",2,"Rel-9","S2,C1,C4,C3,IETF","2008-09-18","2014-06-13",1,"SP-090099","-","China Mobile","Yu Qing (Yuqing@chinamobile.com)","CP#56 added IETF dependency","-",41,21,null,null,"2008-09-15","2009-03-05"]
[5724,440027,"         CT1 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","24.229, 24.237",44,23,null,null,"2009-05-13","2009-12-02"]
[5727,561003,"         (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254)","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C3-IETF","2012-04-20","2014-06-13",1,"CP-090882","-","Andrew Allen","Andrew Allen","CP#64 completed","RFC 7254 (was draft-montemurro-gsma-imei-urn)",56,29,null,null,"2012-04-20","2014-06-06"]
[5730,400048,"      Stage 2 for LCS Control Plane Solution for EPS","LCS_EPS-CPS",3,"Rel-9","S2","2008-06-05","2009-06-04",1,"SP-080445","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","SP#44 completed","23.891, 23.271, 23.401, 23.402",40,21,null,null,"2007-12-13","2009-06-01"]
[5734,470018,"   Conformance Test Aspects – Positioning Support for LTE","LCS_LTE_UEConTest",2,"Rel-9","R5","2010-03-19","2012-03-02",1,"RP-111209","RP-120034","Qualcomm","Shubhang Vora (svoral@qualcomm.com)","RP#55 completed. RP#56 TS 37.571-4 v200 for Approval","36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5)",47,24,null,null,"2010-03-17","2012-06-06"]
[5737,420023,"   Security for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#46 completed",33.246000000000002,42,22,null,null,"2008-12-09","2009-12-09"]
[5739,440025,"   CT4 aspects of MBMS support in EPS (Stage 3)","MBMS_EPS",2,"Rel-9","C4","2009-05-29","2009-12-04",1,"CP-090325","-","China Mobile, ZTE","wangjingyf@chinamobile.com, lu.fei1@zte.com.cn","CP#46 completed","29.274, 29.281, 23.007, 23.008",44,23,null,null,"2009-05-13","2009-11-16"]
[5740,440026,"   CT3 aspects of MBMS support in EPS (Stage 3)","MBMS_EPS",2,"Rel-9","C3","2009-05-29","2009-12-04",1,"CP-090330","-","ZTE, China Mobile","zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com","CP#46 completed",29.061,44,23,null,null,"2009-05-13","2009-11-25"]
[5743,420024,"Access Network Discovery and Selection Function enhancements","eANDSF",1,"Rel-9","S2,C1","2008-12-11","2010-03-19",1,"SP-080887","-","Motorola","Apostolis Salkintzis (salki@motorola.com)","CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8","22.278, SA3 33.402 CR#0055",42,22,null,null,"2008-12-05","2010-03-04"]
[5747,430134,"   Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",2,"Rel-9","S2","2009-03-13","2009-06-04",1,"SP-090098","-","Samsung","erik.guttman@partner.samsung.com","SP#44 completed","23.060, 23.203, 23.401, 23.402",43,22,null,null,"2009-03-05","2009-09-08"]
[5750,450049,"System aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",1,"Rel-9","S2,S4,C1,C3,R2,IETF","2007-05-07","2012-09-12",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE","LTE",45,23,null,null,"2009-05-28","2012-09-03"]
[5752,450051,"   SA4 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090653","-","Qualcomm","Nikolai Leung","SP#46 completed",26.114000000000001,45,23,null,null,"2009-05-28","2009-12-07"]
[5756,33025,"Access Security Enhancements","ACCSEC2",1,"Rel-9","S3","2007-07-02","2009-06-04",1,"SP-040865","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security)","33.102, 43.020",33,17,null,null,"2005-03-24","2010-08-06"]
[5759,410029,"   SA3 work on PUCI","PUCI",2,"Rel-9","S3","2008-09-18","2009-12-10",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#46 completed. No normative work done in Rel-9","New 33.937",41,21,null,null,"2008-09-15","2009-12-07"]
[5761,430136,"   SA3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3","2009-03-13","2010-03-25",1,"SP-090128","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","New 33.828, 33.328",43,22,null,null,"2009-02-11","2010-03-01"]
[5762,521007,"   (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3-IETF,C1-IETF,C3-IETF","2009-03-18","2012-09-14",1,"SP-090128","-","Peter Dawes","-","CP#57 completed, ietf-draft discontinued, documented within 3GPP","draft-dawes-dispatch-mediasec-parameter",52,27,null,null,"2011-06-20","2012-09-03"]
[5765,450010,"      CT1 aspects of IMS Media Plane Security","MEDIASEC_CORE",3,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#47 completed","23.218, 24.229",45,23,null,null,"2009-02-11","2010-03-02"]
[5769,420039,"   SA3 part of eGBAPush (Generic push layer)","eGBAPush",2,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#47 completed","New 33.224",39,21,null,null,"2008-03-22","2010-02-23"]
[5772,440156,"   SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3","2009-06-04","2010-03-25",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","33.102, 33.210, 33.310, 33.401, 33.402",44,23,null,null,"2009-05-18","2010-03-01"]
[5774,440256,"   Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","C4","2009-06-04","2009-12-04",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","CP#46 completed. No impact on CT4 specs","-",44,23,"CP-46","PCG-24","2009-05-18","2009-11-25"]
[5778,440457,"   CT4 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C4","2009-06-04","2009-12-10",1,"SP-090287","-","Ericsson","Karl Norrman","CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060","-",44,23,null,null,"2009-05-18","2009-11-16"]
[5781,440257,"   Deleted - SA2 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090287","-","Ericsson","Karl Norrman","SP#45 work stopped/abandoned",23.06,44,23,"SP-45","PCG-23","2009-05-18","2009-09-07"]
[5782,420027,"Timed Graphics","TG",1,"Rel-9","S4","2008-12-11","2010-03-25",1,"SP-080683","-","Ericsson","clinton.priddle@ericsson.com","SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142)","26.114, 26.140, 26.234, 26.244, 26.245, 26.346, New 26.430",42,22,null,null,"2008-11-23","2010-02-01"]
[5785,430038,"   PSS and MBMS extensions","PMA-MBS_Ext",2,"Rel-9","S4","2009-03-12","2010-03-25",1,"SP-090262","-","Ericsson","Clinton.Priddle@ericsson.com","SP#47 completed. Extends Rel-8 UID_34043 (PSS_MBMS_OMTV) & ensures compatibility with UID_34046 (IMS_PSS_MBMS_US)","26.234, 26.346",43,22,null,null,"2009-02-02","2010-03-08"]
[5787,430046,"IMS based PSS and MBMS User Service extensions","IMS_PSS_MBMS_US_EXT",1,"Rel-9","S4","2009-03-12","2009-12-10",1,"SP-090225","-","Ericsson","Markus Kampmann","SP#46 completed. Work extending Rel-8 UID_34046 (IMS_PSS_MBMS_US), SA2 UID_410034 IMSSCC-SPI (IMS Service Continuity Enhancements: Service, Policy and Interactions) ",26.236999999999998,43,22,null,null,"2009-02-02","2009-12-07"]
[5791,420030,"   Rel-9 Network Infrastructure Management","OAM9-NIM",2,"Rel-9","S5","2008-12-11","2010-03-25",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[5794,440065,"      IRP SOAP Solution Sets continuation from Rel-8","-",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090314","-","Ericsson","John Power","SP#47 completed. Continuation of Rel-8 UID_400030 IRP SOAP Solution Sets","New (32.127/ 327/ 337/ 357/ 387/ 397/ 447/ 397/ 447/ 507/ 537), 32.121,32.122,32.123,32,32.321,32.322,32.323,32.325,32.331,32.332,32.333,32.335,32.351,32.352,32.353,32.381,32.382,32.383,32.385,32.391,32.392,32.393,32.395,32.441,32.442,32.443",44,23,null,null,"2009-05-18","2010-03-22"]
[5797,430041,"      Enhancement of E-UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-03-12","2010-06-10",1,"SP-090053","-","Motorola, Huawei","Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com)","SP#48 completed",32.424999999999997,43,22,null,null,"2009-02-23","2010-05-26"]
[5800,390007,"      SON self-optimization management (moved from Rel-8 LTE_SON-OAM)","-",3,"Rel-9","S5","2008-02-22","2010-06-10",1,"SP-100091","-","Huawei","Lan Zou (zlan@huawei.com)","SP#48 completed","32.425, new (32.521, 32.522, 32.523, 32.525)",39,21,null,null,"2005-06-17","2010-05-26"]
[5803,420033,"   Deleted - Rel-9 Trace","OAM9-Trace",2,"Rel-9","S5","2009-03-13","2009-12-10",1,"-","-","-","-","SP#46 stopped (no work in Rel-9)","-",42,22,"SP-46","PCG-24","2008-11-25","2009-12-01"]
[5804,440068,"Rel-9 Charging Management small Enhancements","CH9",1,"Rel-9","S5","2009-06-04","2010-03-25",1,"-","-","-","-","CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,44,23,null,null,"2009-05-19","2010-03-08"]
[5807,400010,"   CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications","CS-IBCF",2,"Rel-9","C4","2008-05-30","2009-12-04",1,"CP-090073","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#46 completed","23.231, 29.232, new 29.238",40,21,null,null,"2007-09-05","2009-11-25"]
[5811,410009,"IMS Application Level Gateway Control Function (ALGCF) – IMS Access Media Gateway (IMA-MGW); Iq Interface; Stage 2 and Stage 3","IMS_AGCF",1,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090020","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed ","New 23.334, 29.334",41,21,null,null,"2007-09-05","2009-11-16"]
[5813,420017,"   Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service","eCAT-SS",2,"Rel-9","C1","2008-12-05","2010-06-04",1,"CP-080796","-","China Mobile","Jiang Yi","CP#48 completed",24.181999999999999,42,22,null,null,"2008-12-04","2010-05-28"]
[5816,440019,"   CT1 aspects of Completion of IMS Restoration Procedures","eIMS_RP",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed",24.228999999999999,44,23,null,null,"2009-05-13","2010-03-02"]
[5819,440139,"   CT1 aspects of IMS Stage 3 - IETF Protocol Alignment - phase 3","IMSProtoc3",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090491","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","23.218, 24.229, 24.930",44,23,null,null,"2009-05-13","2010-03-02"]
[5822,440070,"Operational description of the Inter-IMS Network to Network Interface (II-NNI)","II-NNI",1,"Rel-9","C3,IETF","2009-05-29","2014-12-09",1,"CP-090331","-","Orange","sebastien.daudet@orange-ftgroup.com","-","-",44,23,null,null,"2009-05-29","2013-02-28"]
[5825,561005,"   (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7316)","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-09-12",1,"CP-090331","-","Keith Drage","Keith Drage","CP#65 complete","RFC 7316 (was draft-vanelburg-dispatch-private-network-ind)",56,29,null,null,"2012-04-20","2014-09-03"]
[5826,561006,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100","draft-ietf-salud-alert-info-urns",56,29,null,null,"2012-04-20","2016-03-07"]
[5829,561009,"   Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2013-12-06",1,"CP-090331","-","Peter Dawes","peter.dawes@vodafone.com","CP#62 removed from Rel-8 to Rel-11. Not completed internet-draft","Rel-12 remains draft-dawes-sipping-debug",56,29,"SP-69",null,"2012-04-20","2013-11-27"]
[5832,450009,"PCC enhancements","PCC-Enh",1,"Rel-9","C3","2009-09-18","2009-12-04",1,"CP-090744","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#46 completed","29.212, 29.213, 29.215",45,23,null,null,"2009-03-05","2009-09-17"]
[5835,410023,"Rel-9 Improvements of the Radio Interface","RInImp9",1,"Rel-9","RP,GP","2008-09-12","2010-03-19",1,"-","-","-","-","RP#41 umbrella Feature created to host Rel-9 WIs","GERAN, UTRA, LTE",41,21,null,null,"2005-01-04","2010-03-16"]
[5838,420009,"      RAN4 part of RF requirements for Multicarrier and Multi RAT BS","RInImp9-Rfmulti",3,"Rel-9","R4","2008-12-05","2010-03-19",1,"RP-091381","RP-100027","Ericsson","johan.skold@ericsson.com","RP#48 completed","UTRA, LTE 25.104, 25.105, 36.104, new 37.104, 37.113, 37.141, 37.900",42,22,null,null,"2008-11-23","2010-06-01"]
[5842,430010,"   Performance requirement for LCR TDD with UE speeds up to 350 km/h","RInImp9-LCRTDD350",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-090258","RP-091035","CATT","Yuexia Song (songyuexia@catt.cn)","RP#46 completed","UTRA 25.102, 25.105, 25.142",43,22,null,null,"2009-02-27","2009-12-02"]
[5845,440007,"   Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe","RInImp-UEConTest-UMTSLTE800EU",2,"Rel-9","R5","2009-05-19","2010-09-17",1,"RP-090485","RP-100736","Ericsson","fredrik.sundstrom@ericsson.com","RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe","UTRA, LTE 34.108, 34.121-1, 34.121-2, 36.508, 36.521-1, 36.521-2, 36.521-3",44,23,null,null,"2009-05-18","2010-09-08"]
[5846,450017,"   Conformance Test Aspects – Extended UMTS/LTE 1500 MHz","UMTSLTE1500_UEConTest",2,"Rel-9","R5","2009-09-18","2010-06-04",1,"RP-091366","RP-100487","NTT DoCoMo","Nguyen Dung Dao (dao@nttdocomo.co.jp)","RP#48 completed","UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",45,23,null,null,"2009-09-15","2010-06-01"]
[5848,470019,"   Conformance Test Aspects – Performance requirement for LCR TDD with UE speeds up to 350 km/h","RInImp9-LCRTDD350_UEConTest",2,"Rel-9","R5","2010-03-19","2010-06-04",1,"RP-100167","RP-100496","CATT","Xiaozhong Chen (chexiaozhong@datangmobile.cn)","RP#48 completed. Testing for UID_430010 Performance requirement for LCR TDD with UE speeds up to 350 km/h","UTRA 34.122",47,24,null,null,"2010-03-17","2010-06-01"]
[5851,430014,"   Dual-Cell HSUPA","RANimp-DC_HSUPA",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090014","RP-100030","Nokia Siemens Networks","Karri Ranta-aho (karri.ranta-aho@nsn.com)","RP#47 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.319, 25.306, 25.321, 25.331, 25.423, 25.433",43,22,null,null,"2009-03-06","2010-03-16"]
[{"$f":"A5854+1","v":5854},430018,"   Transmit Antenna Array (TxAA) extension for non-MIMO UEs","RANimp-TxAA_nonMIMO",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090013","RP-091040","Nokia","Arto Lehti (arto.lehti@nokia.com)","RP#46 completed","25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433",43,22,null,null,"2009-03-06","2009-11-26"]
[5858,510014,"   Conformance Test Aspects – Dual-Cell HSUPA","RANimp-DC_HSUPA_UEConTest",2,"Rel-9","R5","2011-03-18","2012-12-07",1,"RP-110116","RP-121524","Ericsson","leif.mattisson@ericsson.com","RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA","UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",51,26,null,null,"2011-03-10","2012-11-28"]
[5861,430019,"   LTE Pico NodeB RF Requirements","LTEimp-Pico_eNB-RF",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-091155","RP-091045","Huawei","Liyan Yin (yinliyan@huawei.com)","RP#46 completed","36.104, 36.141, new 36.931",43,22,null,null,"2009-02-27","2010-02-08"]
[5864,420011,"Rel-9 Self-Organizing Networks (SON)","SON",1,"Rel-9","R3,R2","2009-03-06","2009-03-06",1,"RP-090162","RP-100038","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#47 completed","LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902",42,22,null,null,"2008-12-05","2010-03-10"]
[5867,38004,"   AGNSS Testing Procedures","AGNSSPTP-MStest",2,"Rel-9","G3new","2008-05-16","2011-05-20",1,"GP-092343","-","Thales","Michel.monnerat@thalesaleniaspace.com","GP#50 completed","51.010-1, new 51.010-7",38,20,null,null,"2008-05-19","2011-05-21"]
[5870,420004,"   Stage 3 for Voice services over Adaptive Multi-user channels on One Slot","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-03-04",1,"GP-081965","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#49 completed. GP#40 WID approved","24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058",40,22,null,null,"2008-11-23","2011-03-04"]
[5872,490005,"   VAMOS - MS conformance testing","VAMOS_MStest",2,"Rel-9","G3new","2010-09-03","2012-03-02",1,"GP-101604","-","BlackBerry","Raveendra Seetharam (rseetharam@rim.com)","GP#53 completed. GP#47 WID approved","51.010-1, 51.010-2",47,25,null,null,"2010-09-04","2012-03-02"]
[5873,500001,"   VAMOS - BTS conformance testing","VAMOS_BTStest",2,"Rel-9","G1","2010-11-26","2011-09-02",1,"GP-102005","-","Nokia Siemens Networks","eddie.riddington@nsn.com","GP#51 completed. GP#48 WID approved",51.021000000000001,48,26,null,null,"2010-11-27","2011-05-21"]
[5876,440202,"   CT1 part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre","CEBRO",2,"Rel-9","C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed",23.041,42,23,null,null,"2009-05-18","2010-03-02"]
[5880,330017,"Deleted - Services Alignment and Migration","ServAl",1,"Rel-9","S1","2006-12-06","2008-09-18",1,"SP-070126","-","Telefónica O2","chris.friel@O2.com","SP#41 closed (no tangible result of this work¦no CR against TR 22.983). Triggered by Study UID_370086 (FSServAl) ","-",33,17,"SP-41","PCG-21","2006-10-06","2010-08-05"]
[5883,380081,"Deleted - Support of WiMAX - LTE Mobility","WiMAX_LTE_Mobility",1,"Rel-9","R2","2008-06-06","2009-12-25",1,"RP-070511","-","Samsung","-","RP#39: No agreed WID","36.306, 36.331, 36.413, 36.300, 36.214, 36.133, 36.304",38,21,"SP-39","PCG-21","2007-12-17","2009-03-24"]
[5886,390040,"Deleted - SAES Enhancements (non RAN aspects)","SAES_Ph2",1,"Rel-9","S2","2007-06-25","2008-12-08",1,"-","-","Nokia Siemens Networks","-","SP#39 created to host Rel-9 Wis. BUT no agreed WID","-",39,20,"SP-39","PCG-21","2005-01-31","2009-03-24"]
[5889,390042,"   Deleted - SAE for generic support for non-3GPP accesses","SAES_Ph2",2,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[5892,0,"Release 9 Studies","-",1,"Rel-9","CP,RP,SP","2008-06-05","2008-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[5893,400036,"Study on Service Specific Access Control in EPS","FS_SSAC",1,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080319","-","NTT DoCoMo","Shin-ichi Isobe (isobes@nttdocomo.co.jp)","SP#42 completed. Spin-off Feature UID_420020 (SSAC)",22.986000000000001,40,21,null,null,"2007-12-13","2010-08-31"]
[5896,320031,"Study on Service Continuity for Emergency Voice Calls","FS_VCCEm",1,"Rel-9","S2","2006-06-08","2009-03-12",1,"SP-080555","-","Nortel","Ricky Kaura (rkaura@nortel.com)","SP#43 completed",23.826000000000001,32,17,null,null,"2006-07-19","2009-02-24"]
[5899,360007,"Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB","FS_OAM-SON-HNB",1,"Rel-9","S5","2007-06-07","2009-06-04",1,"SP-080461","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036)",32.820999999999998,36,19,null,null,"2007-05-28","2009-05-18"]
[5902,380079,"Study on Evaluation of the inclusion of Path Loss Based Technology in the UTRAN","FS_RAN-Pathloss",1,"Rel-9","R4","2007-12-17","2009-12-04",1,"RP-071050","RP-091080","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#46 completed",25.907,38,21,null,null,"2007-12-17","2009-11-26"]
[5905,420012,"Study on E-UTRAN Mobility Evaluation and Enhancement","FS_EUTRAN_mob",1,"Rel-9","R1","2008-12-05","2009-05-29",1,"RP-081137","RP-090426","Qualcomm","Rajat Prakash (rprakash@qualcomm.com)","RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed)","none",42,22,null,null,"2008-12-04","2009-05-20"]
[5907,430027,"Study on Enhanced Interference Management for HNBs","FS_eInterfMgmt_HNB",1,"Rel-9","R4","2009-03-06","2009-05-29",1,"RP-090361","RP-090429","Qualcomm","Farhad Meshkati (fmeshkat@qualcomm.com)","RP#44 completed. Linked to UID_420008 LTE FDD Home eNodeB RF Requirements. Spin-off RAN3 UID_440015 Study on Enhanced Interference Management Mechanisms for HNBs",25.966999999999999,43,22,null,null,"2009-03-10","2009-06-25"]
[5911,320005,"3GPP System Architecture Evolution Specification - Evolved Packet System (non RAN aspects)","SAES",1,"Rel-8","S1,S2,S3,S5,C1,C3,C4,C6,IETF","2006-04-12","2012-06-15",1,"SP-080132","-","T-Mobile","michael.kurz@t-mobile.at ","Role model for SAE/LTE system wide project management by SA2 in SP-060166","-",32,17,null,null,"2005-01-31","2009-12-08"]
[5914,350024,"      Stage 2 for High level functions ","SAES-SA-HLF",3,"Rel-8","S2","2007-01-02","2008-06-02",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed","New 23.402",35,18,null,null,"2007-03-29","2010-07-28"]
[5915,390044,"      Stage 2 Security Architecture","SAES",3,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080132","-","Nokia Siemens Networks","marc.blommaert.ext@nsn.com","SP#42 completed","33.210, 33.310, New 33.401",39,21,null,null,"2008-03-19","2010-07-28"]
[{"$f":"A5918+1","v":5918},340062,"      Stage 3 (CT4) of SAE impact on existing capabilities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","New (29.274, 29.275)",34,18,null,null,"2006-07-19","2010-07-28"]
[5922,340028,"      Stage 3 for SAE / LTE identities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",23.003,34,18,null,null,"2006-07-19","2010-07-28"]
[5924,350025,"   SAE for LTE access ","SAES-LTE",2,"Rel-8","S2,C1,C3,C4","2007-01-02","2009-03-06",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed","-",35,18,null,null,"2007-03-29","2010-07-28"]
[5927,370006,"         Stage 2 for SAES-SA-FP_LTE with GTP variant","SAES-SA-FP_LTE-GTP-St2",4,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","23.401, 23.060, 23.002, 23.246, 23.203, 23.107, 23.234, 23.271",37,19,null,null,"2007-09-19","2010-07-28"]
[5931,370018,"         CT4 Stage 3 for PMIP protocol within EPC","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.275, 29.282",37,19,null,null,"2006-07-19","2010-07-28"]
[5933,340020,"      Stage 3 for UE Non-Access-Stratum (NAS) mobility procedures in idle and active mode","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.007, 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[5934,340050,"      Stage 3 for Session management, bearer control and QoS aspects","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.007, 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[5937,340026,"      Stage 3 for EPC - HSS interface","SAES-LTE",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",29.271999999999998,34,18,null,null,"2006-07-19","2010-07-28"]
[5940,380031,"      Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008, 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[5944,380032,"      Stage 3 for EPC to UTRAN","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.275, 29.281",38,21,null,null,"2006-07-19","2010-07-28"]
[5946,370009,"      Stage 2 for Interoperation between LTE and CDMA2000","EPStoC2k",3,"Rel-8","S2","2007-06-18","2008-09-18",1,"SP-080132","-","Motorola, Vodafone","Irfan.Ali@motorola.com, chris.pudney@vodafone.com","SP#41 completed (except: Handover of multiple PDNs=>Rel-9)","23.401, 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[5949,350027,"   SAE for support for non-3GPP accesses ","SAES-SA-FP_n3GPP",2,"Rel-8","S2,S3,C1,C4,IETF","2007-01-02","2012-06-15",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037","-",35,18,null,null,"2007-03-29","2010-07-28"]
[5953,521011,"      (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt)","SAES-SA-FP_n3GPP",3,"Rel-8","C1-IETF","2007-02-05","2012-06-15",1,"CP-080493","-","Mark Jones","-","CP#56 completed; 9/4/21: RFC 6610 added;","RFC 6610 (was draft-ietf-mip6-hiopt); RFC 6610",52,27,null,null,"2011-06-20","2021-04-09"]
[5956,380030,"      Stage 3 for Inter-system mobility between E-UTRAN and non 3GPP accesses","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008, 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[5957,360019,"      Stage 2 for Optimized Dual-Radio Handover with WiMAX","SAES-SA-FP_n3GPP-OptWIMAX",3,"Rel-8","S2","2007-06-25","2008-06-05",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed",23.402000000000001,36,19,null,null,"2007-04-26","2010-07-28"]
[5959,370010,"      Stage 3 security aspects for DSMIPv6 Access","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303000000000001,37,19,null,null,"2006-07-19","2010-07-28"]
[5962,370011,"      Stage 3 for interfaces within EPC","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-09-19","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.281",37,19,null,null,"2007-09-19","2010-07-28"]
[5966,340059,"      Stage 3 for EPC - AAA interface","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[5968,350030,"   Single Radio Voice Call Continuity for 3GPP (SRVCC)","SAES-SRVCC",2,"Rel-8","S2,C1,C4","2007-01-02","2009-03-06",1,"SP-070949","-","Nokia Siemens Networks","curt.c.wong@nokia.com","CP#43 completed. SP#38 WID approved (extract from SAE WID SP-070817).","-",35,18,null,null,"2007-03-29","2010-07-28"]
[5971,410006,"      MME to MSC interface for SRVCC","SAES-SRVCC",3,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080793","-","Nokia Siemens Networks","Giorgi Gulbani","CP#43 completed","23.003, 23.008, New (29.274, 29.277, 29.280)",41,21,null,null,"2008-09-01","2010-07-28"]
[5975,400001,"      Stage 2 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","SP#40 completed","New (23.272, 23.401)",40,21,null,null,"2007-03-29","2010-07-28"]
[5978,390039,"   System enhancements for the use of IMS services in local breakout","SAES-IMS_LBO",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080090","-","Telecom Italia","mario.madella@telecomitalia.it","SP#40 completed","23.228, 23.221, 23.203",39,21,null,null,"2007-10-02","2010-07-28"]
[5979,390010,"   EPC Data Definitions","EPC-OAM",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"-","-","-","-","SP#43 completed","-",39,21,null,null,"2005-06-17","2010-07-28"]
[5983,400104,"   Domain Name System Procedures for Evolved Packet System (DEPS)","SAES-DEPS",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080280","-","TeliaSonera","jouni.korhonen@teliasonera.com","CP#43 completed","23.003, New 29.303",40,21,null,null,"2006-07-19","2010-07-28"]
[5984,410007,"   InterWorking Function (IWF) between MAP based and Diameter based interfaces","SAES-MAP2Diam",2,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080644","-","Huawei","liming49985@huawei.com","CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam)","New 29.305",41,21,null,null,"2007-11-19","2010-07-28"]
[5988,490015,"      Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS)","SAES-ISIM_IMS_Test",3,"Rel-8","C6","2010-09-17","2011-06-03",1,"CP-100602","-","Comprion","Udo Willenbrink (uwillenbrink@comprion.com )","CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229).","31.121, 31.124, New 31.134",49,25,null,null,"2010-09-06","2011-05-18"]
[5991,390020,"   Deleted - Issues for CT4 TR 29.803","SAES",2,"Rel-8","C4","2007-01-04","2008-09-12",1,"CP-080068","-","Huawei","-","CP#41 Work stopped and continued in Normative specifications",29.803000000000001,39,21,"CP-41","PCG-21","2006-07-19","2009-03-24"]
[5994,340019,"   Deleted - CT aspects of SAES","SAES-St3",2,"Rel-8","C3,C1,C4","2007-09-04","2008-03-14",1,"CP-060674","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[5997,350020,"      Deleted - CT3 aspects of SAES","SAES",3,"Rel-8","C3","2007-09-04","2007-09-04",1,"CP-060675","-","-","-","SP#37 stopped","-",35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6000,340027,"      Deleted - User and Control plane protocols","SAES-St3-prot",3,"Rel-8","C4","2007-09-21","2007-09-21",1,"CP-060676","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6001,340037,"   Deleted - Architecture enhancements for non-3GPP accesses","SAES-non_3GPP",2,"Rel-8","S2","2007-09-04","2007-09-04",1,"SP-060926","-","Motorola","Irfan.Ali@motorola.com","SP#34 stopped. Replaced by UID_350027 and its children",23.402000000000001,34,18,"SP-34",null,"2006-06-23","2009-03-24"]
[6005,370025,"IMS Centralized Service control","ICSRA",1,"Rel-8","S1,S2,C1,C3,C4,IETF","2005-11-01","2014-12-09",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","CP#46 completed","-",37,19,null,null,"2007-10-02","2009-12-02"]
[6006,380039,"   Stage 1 for ICS Requirement and Architecture","ICSRA",2,"Rel-8","S1","2007-09-03","2008-03-12",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","SP#39 completed",22.100999999999999,38,21,null,null,"2007-10-02","2008-07-23"]
[6010,521014,"      (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2014-12-09",1,"CP-091046","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[6013,521017,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7006)","ICSRA",3,"Rel-8","C1-IETF","2008-06-03","2013-12-06",1,"CP-091046","-","Andrew Allen","-","CP#62 completed","RFC7006 (was draft-ietf-mmusic-sdp-miscellaneous-caps)",52,27,null,null,"2011-06-20","2013-11-27"]
[6017,400105,"      Deleted - Stage 3 for ICSRA – I1 interface","ICSRA",3,"Rel-8","C1","2008-05-30","2008-09-12",1,"CP-080492","-","Huawei","xupeili@huawei.com","CP#41 work stopped",24.292999999999999,40,21,"CP-41","PCG-21","2008-03-03","2009-12-02"]
[6018,370059,"IMS Multimedia Telephony and Supplementary Services","IMSTSS",1,"Rel-8","S1,S5,C1,C3,C4,IETF","2007-05-02","2014-12-09",1,"-","-","-","-","SP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[6022,380002,"      Documentation of TISPAN R1 and R2 in CT3","REDOC_TIS-C3",3,"Rel-8","C3","2007-11-28","2009-03-06",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#43 completed","29.162, 29.163, 29.658",38,21,null,null,"2007-11-28","2009-12-07"]
[6023,380003,"      Documentation of TISPAN R1 and R2 in CT4","REDOC_TIS-C4",3,"Rel-8","C4","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","29.228, 29.229",38,21,null,null,"2007-11-28","2008-09-01"]
[6026,380041,"      Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging","MMTel-CH",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-080848","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","CP#43 completed","32.275, 32.298/299",38,21,null,null,"2005-06-17","2009-02-23"]
[6029,380008,"      CT3 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C3","2007-05-02","2008-12-05",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#42 completed",29.163,38,21,null,null,"2007-11-14","2012-01-11"]
[6032,390059,"      Stage 1 FA","FA",3,"Rel-8","S1","2008-01-30","2008-06-05",1,"-","-","Telecom Italia","-","SP#40 completed ",22.172999999999998,39,21,null,null,"2008-03-03","2008-09-18"]
[6035,380010,"      CT1 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C1","2007-11-30","2009-03-06",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.615, 24.229, 24.173",38,21,null,null,"2007-11-14","2009-02-20"]
[6039,370003,"      Add Interconnection Border Control Function (IBCF) to IMS Charging","CH8_IMS",3,"Rel-8","S5","2007-09-17","2008-03-12",1,"SP-070621","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#39 completed","32.260, 32.298",37,19,null,null,"2007-09-15","2008-03-23"]
[6042,390050,"   Stage 1 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","22.228, 22.173, 22.101, 22.153",39,21,null,null,"2008-03-03","2015-03-24"]
[6044,390052,"   Security CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#42 completed [issues addressed under UID_370078 (IMS-Sec)]. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","33.141, 33.203, 33.210",39,21,null,null,"2008-03-03","2015-03-24"]
[6045,390113,"   Stage 3 CIMS_3GPP2","REDOC_3GPP2",2,"Rel-8","C1,C3,C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","-","-",39,21,null,null,"2008-03-03","2008-12-04"]
[6048,390027,"      Stage 3 CIMS_3GPP2 (CT4)","REDOC_3GPP2",3,"Rel-8","C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","29.228, 29.229, 29.328, 29.329",39,21,null,null,"2008-03-03","2009-03-26"]
[6052,350010,"      CT1 aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070122","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed","-",35,18,null,null,"2007-03-29","2008-05-13"]
[6055,350013,"      CT1,CT3 aspects of PktCbl-Interwork","PktCbl-Intw",3,"Rel-8","C1,C3","2007-03-26","2008-03-14",1,"CP-070575","-","Cablelabs","D.Hancock@CableLabs.com","CP#39 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-03-03"]
[6057,350033,"      SA3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","S3","2006-12-06","2008-03-12",1,"SP-060933","-","Cablelabs","s.dotson@cablelabs.com","SP#39 completed","33.203, 33.210, 33.220",35,18,null,null,"2005-11-04","2008-03-23"]
[6061,360012,"IMS System enhancements for corporate network access","IMS_Corp",1,"Rel-8","S2,S1,C1,C4,IETF","2007-06-22","2014-09-12",1,"SP-080095","-","Orange","Delphin Barankanira","CP#47 completed","-",36,19,null,null,"2007-06-22","2010-07-29"]
[6064,390022,"   CT1 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C1","2008-03-07","2010-03-19",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","24.229, 24.503",39,21,null,null,"2008-03-07","2010-03-03"]
[6066,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228, 29.229, 23.003, 23.008, 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[6067,380069,"Maintenance of TISPAN documentation","MAINTISP",1,"Rel-8","S2,C1,C3,C4,IETF","2007-07-02","2014-06-13",1,"-","-","-","-","SP#40 completed","-",38,21,null,null,"2007-12-13","2010-07-29"]
[6070,380043,"   Documentation of TISPAN NGN R1 and R2 in 3GPP SA2","IMS_Comm_Doc",2,"Rel-8","S2","2008-01-14","2008-06-05",1,"SP-070823","-","Nokia Siemens Networks","jozsef.varga@nsn.com","SP#40 completed","23.228, 23.204, 23.167",38,21,null,null,"2007-10-02","2008-05-27"]
[6074,390057,"   Stage 2 IMS Service Continuity","IMS-Cont",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080092","-","LG Electronics","JaeSeung SONG (anthonys@lge.com)","SP#40 completed","23.237, 23.292",39,21,null,null,"2007-10-02","2008-05-27"]
[6077,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203, 33.141, 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[6079,390154,"   CT4 part of Stage 3 for IMS-Sec","IMS-Sec",2,"Rel-8","C4","2007-06-07","2009-03-06",1,"-","-","Ericsson","-","CP#43 completed","-",39,21,null,null,"2007-11-21","2009-02-20"]
[6083,34146,"   SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",2,"Rel-8","S4,S3","2008-03-12","2008-03-12",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#43 completed","26.234, 26.346, 33.246, New 26.237",34,18,null,null,"2008-03-18","2011-06-30"]
[6086,7013,"   Stage 1 and 2 defined in earlier Releases","MIW-IMS",2,"Rel-8","S2","2005-09-23","2005-11-30",1,"-","-","Vodafone","nico.gabriele@vodafone.com","SP#31 Moved from FS section Feb 2006","-",70,36,null,null,"2006-02-16","2010-07-30"]
[6087,7014,"   Stage 3 of MW-IMS","MIW-IMS-St3C3",2,"Rel-8","C3","2005-09-23","2007-11-30",1,"CP-070096","-","Vodafone","nico.gabriele@vodafone.com","Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021","29.863, 29.163",70,36,null,null,"2006-02-16","2008-08-05"]
[6090,360029,"IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",1,"Rel-8","C1,IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","-",36,19,null,null,"2007-09-05","2009-02-20"]
[6092,521023,"   (IETF) IMS Stage 3 IETF Protocol Alignment (draft-bakker-sipping-3gpp-ims-xml-body-handling)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2012-12-07",1,"CP-080794","-","Andrew Allen","-","CP#58 completed. ietf-draft discontinued. Documented within 3GPP","draft-bakker-sipping-3gpp-ims-xml-body-handling",52,27,null,null,"2011-06-20","2012-11-24"]
[6096,380015,"   CT1 part of Stage 3 MGCF UUSIW","UUSIW",2,"Rel-8","C1","2007-11-30","2008-12-05",1,"CP-070782","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#42 completed","24.279, 24.229",38,21,null,null,"2007-11-13","2008-11-21"]
[6099,380016,"   CT3 part of Stage 3 MGCF UUSIW","UUSIW",2,"Rel-8","C3","2007-11-30","2009-03-12",1,"CP-070782","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#43 completed",29.163,38,21,null,null,"2007-11-13","2009-02-19"]
[6102,380020,"   Stage 3 Overlap (CT3)","Overlap",2,"Rel-8","C3","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed",29.163,38,21,null,null,"2007-11-13","2008-11-25"]
[6105,380135,"   AS/MRFC Stage 2","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed",23.218,38,21,null,null,"2007-11-14","2012-01-10"]
[6108,400012,"IMS Restoration Procedures","IMS_RP",1,"Rel-8","C4,C1","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 ","-",40,21,null,null,"2007-03-29","2010-07-30"]
[6109,400026,"   IMS Restoration Procedures (CT4)","IMS_RP",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed","23.380, 29.228, 29.229, 29.230, 23.008",40,21,null,null,"2007-03-29","2010-07-30"]
[6112,340030,"I-WLAN Network Selection Principle (NSP)","IWLANNSP",1,"Rel-8","S1,C1,C6","2007-06-14","2009-03-06",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","CP#43 completed","-",34,18,null,null,"2005-11-04","2009-02-25"]
[6116,370049,"Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",1,"Rel-8","S2,C1","2007-09-14","2009-03-06",1,"SP-070701","-","Orange","xiaobao.chen@orange-ftgroup.com","CP#43 completed","-",37,19,null,null,"2005-11-04","2008-05-27"]
[6118,400013,"   CT1 aspects of Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",2,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-080320","-","Orange","reina.nader@orange-ftgroup.com","CP#43 completed","24.303, new 24.327",40,21,null,null,"2007-11-21","2010-07-30"]
[6121,320021,"   SA1 aspects of EVA","EVA",2,"Rel-8","S1","2006-03-15","2006-12-06",1,"SP-070904","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#38 completed",42.067999999999998,32,17,null,null,"2006-03-21","2008-05-16"]
[6124,320020,"   CT4 aspects of EVA","EVA",2,"Rel-8","C4","2006-06-02","2007-11-30",1,"CP-060260","-","Nortel","-","CP#38 completed",29.001999999999999,32,17,null,null,"2006-06-21","2008-05-16"]
[6127,7012,"   Stage 1 for PNM","PNM",2,"Rel-8","S1","2005-07-11","2006-07-31",1,"SP-080327","-","Vodafone","armin.toepfer@vodafone.com","SP#31 completed",22.259,null,null,null,null,"2006-02-16","2008-06-04"]
[6130,350001,"      CT1 aspects of Stage 3 PNM","PNM",3,"Rel-8","C1","2007-03-26","2009-03-06",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#43 completed","24.259, 24.229",null,null,null,null,"2007-03-29","2009-02-20"]
[6131,350002,"      Deleted - CT4 aspects of Stage 3 PNM","PNM",3,"Rel-8","C4","2007-03-26","2008-12-05",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#42 no impact on CT4 specs","-",null,null,"CP-42",null,"2007-03-29","2010-07-30"]
[6134,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[6137,34042,"eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution","eCall_Phase2",1,"Rel-8","S4","2007-12-06","2009-09-24",1,"SP-070756","-","Airbiquity","lhong@airbiquity.com & rrobinson@airbiquity.com","SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData)","26.267, 26.268, 26.269, 26.967, 26.969",null,null,null,null,"2007-12-09","2010-08-02"]
[6140,380060,"IP Interconnection of Services ","IPinterc",1,"Rel-8","S1,S2,S5,C3","2006-08-16","2009-03-06",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#43 completed","-",38,21,null,null,"2007-12-13","2010-08-02"]
[6143,360024,"      Stage 2 for IMS_NNI","IMS_NNI",3,"Rel-8","S2","2007-06-22","2007-12-06",1,"SP-080554","-","Telecom Italia","Mario Madella (mario.madella@telecomitalia.it)","SP#38 completed","23.002, 23.228",null,null,null,null,"2007-06-22","2010-08-02"]
[6147,7006,"      Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8","FBI2-TISP2-s2",3,"Rel-8","S2","2007-11-30","2007-11-30",1,"-","-","Nokia Siemens Networks","-","SP#36 stopped","-",null,null,"SP-36",null,"2006-02-16","2009-03-24"]
[6150,360026,"   SIP-I based circuit-switched core network; Stage 2","SIP_Nc-St2",2,"Rel-8","C4","2007-09-14","2008-12-05",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#42 completed","23.231, 23.153, 23.205",null,null,null,null,"2007-09-05","2008-11-22"]
[6151,360027,"   Application of SIP-I Protocols to Circuit Switched (CS) core network architecture; Stage 3","SIP_Nc-St3C4",2,"Rel-8","C4","2007-09-14","2008-12-05",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#42 completed","29.231, 29.232, 29.332",null,null,null,null,"2007-09-05","2008-11-22"]
[6153,370051,"Earthquake and Tsunami Warning System","ETWS",1,"Rel-8","S1,S2,C1,C4,G2","2007-09-10","2009-05-15",1,"SP-070815","-","NTT DoCoMo","kitaharar@nttdocomo.co.jp","SP#43 Larger scope Feature UID_380057 (PWS) moved to Rel-9","-",37,null,null,null,"2007-11-19","2010-08-02"]
[6156,400015,"   CT1 aspects of ETWS","ETWS",2,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080951","-","NTT DoCoMo","yamashitahi@s1.nttdocomo.co.jp","CP#42 completed",23.041,40,21,null,null,"2007-12-13","2010-08-02"]
[6159,440011,"Conformance Test Aspects – UMTS Earthquake and Tsunami Warning System (ETWS) FDD","ETWS_UMTS_UEConTestFDD",1,"Rel-8","R5","2009-05-29","2010-03-12",1,"RP-090467","RP-100068","NTT DoCoMo","Makoto Ito (itohm@nttdocomo.co.jp)","RP#47 completed. Testing for Rel-8 ETWS UID_370051","34.108, 34.123-1, 34.123-2",44,23,null,null,"2009-05-28","2010-03-08"]
[6163,330006,"Local Charging Zone Requirements","LCZR",1,"Rel-8","S1","2006-09-28","2008-03-12",1,"SP-060482","-","China Mobile","liuhongyfw@chinamobile.com","SP#39 Stage 1 completed",22.114999999999998,null,null,null,null,"2006-10-06","2008-03-25"]
[6166,370029,"   TISPAN requirements for customized multimedia information services","TISCMI",2,"Rel-8","S1","2007-09-03","2007-12-10",1,"SP-070880","-","China Mobile","fenglingjuan@chinamobile.com","SP#38 completed",22.181999999999999,37,null,null,null,"2007-10-02","2008-07-24"]
[6169,390071,"      CAT solution for voice and video call in CS domain","CAT-SS",3,"Rel-8","C3","2008-03-12","2009-09-18",1,"CP-080496","-","Nortel","milanpa@nortel.com","CP#45 completed. Triggered by Study UID_360031 (TR 29.882)",29.163,39,21,null,null,"2008-03-03","2010-08-02"]
[6172,410015,"      CT1 part of CAT Service in 3GPP CS domain","CAT-3G_CS",3,"Rel-8","C1","2008-09-12","2008-12-05",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","CP#42 completed. Triggered by Study UID_360031 (TR 29.882)","24.008, 23.014",41,21,null,null,"2008-09-11","2012-01-11"]
[6175,350048,"   Stage 2 for MESSIW","MESSIW",2,"Rel-8","S2","2007-04-26","2008-03-07",1,"SP-070816","-","Huawei","patrice.hede@huawei.com","SP#39 completed","23.811, 23.204",null,null,null,null,"2005-11-04","2008-03-22"]
[6177,400017,"   CT1 part of Stage 3 for MESSIW","MESSIW",2,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080773","-","Huawei","xupeili@huawei.com","CP#42 completed",24.228999999999999,40,21,null,null,"2006-07-19","2010-08-02"]
[6178,340044,"Multimedia Priority Service","PRIOR_EMR",1,"Rel-8","S1,C1,C3,C4","2006-06-08","2009-09-18",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","CP#45 completed","-",34,null,null,null,"2003-03-28","2009-09-09"]
[6182,370020,"   Deleted - Stage 3 for PRIOR","PRIOR-EMR",2,"Rel-8","C3","2007-09-21","2009-05-29",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2)","29.212, 29.213, 29.214, 29.163",37,null,"CP-44","PCG-23","2007-09-25","2009-05-29"]
[6185,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6188,370013,"      Parlay-X Content Management web service (store/manage meta-data)","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-21",37,null,null,null,"2007-09-13","2009-01-19"]
[6190,370015,"      Parlay-X Terminal status web service","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-08",37,null,null,null,"2007-09-13","2009-01-19"]
[6194,380049,"      Deleted - Topology Hiding (22.127 CR 0086 S1-071838)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6197,380052,"      Deleted - Access policy (22.127 CR 0089 S1-071763)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6198,380053,"      Deleted - API usage accounting (22.127 CR 0090 S1-071792)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6201,390067,"      Framework Enterprise Operator (Service Subscription function)","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-03",39,21,null,null,"2008-03-26","2009-01-19"]
[6204,390070,"      PAM Presence Agent","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-14",39,21,null,null,"2008-03-26","2009-01-19"]
[6207,380017,"   Stage 3 for PPACR (CT1)","PPACR-CT1",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070783","-","NTT DoCoMo","-","CP#42 completed","24.008, 23.122, 24.301",38,21,null,null,"2007-11-14","2008-11-21"]
[6210,380070,"   Stage 1 for CHRGMPH","CHRGMPH-s1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-03-20"]
[6212,380066,"   Stage 1 for Home NodeB / eNodeB","HomeNB-S1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-070952","-","Vodafone","John Watson","SP#39 completed","22.011, 22.115",38,21,null,null,"2007-12-13","2008-07-24"]
[6216,390033,"UTRA HNB","HNB",1,"Rel-8","RP,S5","2008-03-07","2009-06-04",1,"-","-","-","-","SP#44 completed","-",39,21,null,null,"2005-01-04","2008-06-03"]
[6219,390034,"   FDD Home NodeB RF requirements","HNB-RF",2,"Rel-8","R4","2008-03-07","2009-03-06",1,"RP-080971","RP-090041","Motorola","Ying Cai (yingcai@motorola.com)","RP#43 completed","25.104, 25.141, new 25.967",39,21,null,null,"2004-09-27","2009-02-27"]
[6220,420037,"   3G Home NodeB OAM&P Type 1 Management Interface","HNB-3G_OAM",2,"Rel-8","S5","2008-12-11","2009-06-04",1,"SP-080708","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Complements work in BroadBand Forum","new (32.581, 32.582, 32.583, 32.584)",42,22,null,null,"2008-12-03","2009-05-18"]
[6223,350015,"Lawful Interception in the 3GPP Rel-8","LI8",1,"Rel-8","S3","2007-03-12","2009-03-12",1,"SP-070238","-","BMWI, Verizon","berthold.wilhelm@bnetza.de, ron_ryan@verizon.net ","SP#43 completed","33.106, 33.107, 33.108",null,null,null,null,"2007-03-29","2009-03-11"]
[6227,390346,"   CT4 part of GBAPush ","GBAPush",2,"Rel-8","C4","2008-03-12","2009-03-06",1,"CP-090112","-","Ericsson","Rolf Blom","CP#43 completed",29.109000000000002,39,21,null,null,"2008-03-22","2009-03-04"]
[6229,34043,"Extending PSS and MBMS User Services for optimized Mobile TV","PSS_MBMS_OMTV",1,"Rel-8","S4","2007-12-06","2008-12-11",1,"SP-070757","-","Ericsson","thorsten.lohmar@ericsson.com","SP#42 completed. SP#38 WID approved. ","26.234, 26.346, 26.946",null,null,null,null,"2007-12-09","2008-11-21"]
[6232,400018,"   CT3 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#43 completed",29.163,40,21,null,null,"2007-12-09","2009-02-20"]
[6236,340064,"   Rel-8 Network Infrastructure Management","OAM8-NIM",2,"Rel-8","S5","2007-06-07","2009-12-04",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[{"$f":"A6238+1","v":6238},35053,"      Advanced Alarming on Itf-N","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070492","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#40 completed","32.121, 32.122, 32.123",null,null,null,null,"2005-06-17","2008-06-04"]
[6239,35056,"      CN CS Bearer Transport Network (BTN) relative NRM","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070300","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#40 completed","32.632, 32.633, 32.635",null,null,null,null,"2005-06-17","2008-04-28"]
[6242,450052,"      Create missing specifications for IRP XML definitions","OAM8-NIM",3,"Rel-8","S5","2009-09-24","2009-12-04",1,"SP-090553","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x)","new (32.125, 32.355, 32.505, 32.535), 32.150, 32.153, 32.335 ",45,23,null,null,"2009-09-11","2009-12-01"]
[6245,35061,"      IP bearer network Performance measurement definitions","OAM8-PM",3,"Rel-8","S5","2007-06-07","2008-12-11",1,"SP-070301","-","China Mobile","lilianyuan@chinamobile.com","SP#42 completed","32.321, 32.322, 32.323, 32.325",null,null,null,null,"2005-06-17","2010-08-02"]
[6249,11067,"      CT1 part of Service Level Tracing in IMS","OAM8-Trace",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080315","-","Vodafone","peter.dawes@vodafone.com","CP#42 completed","24.323, 24.229",null,null,null,null,"2008-03-17","2010-08-02"]
[6251,531003,"      Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event)","OAM8-Trace",3,"Rel-8","C1-IETF","2008-03-07","2011-12-09",1,"CP-080315","-","Peter Dawes","peter.dawes@vodafone.com","CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100","draft-dawes-sipping-debug-event",53,27,null,null,"2011-07-29","2021-04-09"]
[6254,870081,"   (IETF) A Two-Way Active Measurement Protocol (TWAMP) (draft-ietf-ippm-twamp) --> RFC 5357","OAM8",2,"Rel-8","S5-IETF","2008-03-07","2010-09-06",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[6258,410045,"   Introduce Online Charging from SMS-SC into the SMS Charging Specifications","CH8",2,"Rel-8","S5","2008-09-18","2008-12-11",1,"SP-080463","-","Acision","erik.gebler@acision.com","SP#42 completed. Linked to SA2 UID 32081 (Support of SMS over IP networks) and CT4 UID 340016 (Routeing of MT-SMS via the HPLMN).","32.274, 32.299",41,21,null,null,"2008-09-15","2008-11-25"]
[6261,380025,"   Stage 2 for eMp","eMp",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed",23.332999999999998,38,21,null,null,"2007-11-19","2010-08-02"]
[6262,380026,"   Stage 3 for eMp","eMp",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed",29.332999999999998,38,21,null,null,"2007-11-19","2010-08-02"]
[6264,320015,"   Requirements for Contact Manager","eUPHBOOK-St1",2,"Rel-8","C6","2006-06-22","2007-12-21",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#38 completed",21.111000000000001,null,null,null,null,"2006-01-24","2008-05-29"]
[6267,320016,"   Deleted - Implementation of eUPHBOOK","eUPHBOOK-St23",2,"Rel-8","C6","2007-06-21","2007-06-21",1,"CP-060355","-","Giesecke & Devrient","Claus Dietze","SP#33 stopped",31.102,null,null,"SP-33",null,"2006-01-24","2009-03-24"]
[6271,330020,"   LTE – eUTRAN Interfaces","LTE-interfaces",2,"Rel-8","R3","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Ericsson","Martin Israelsson","RP#42 completed","36.401, 36.410, 36.411, 36.412, 36.413, 36.414, 36.420, 36.421, 36.422, 36.423, 36.424, 25.413",null,null,null,null,"2006-03-21","2009-12-18"]
[6273,370046,"   LTE – FDD repeaters","LTE-Repeaters",2,"Rel-8","R4","2007-09-14","2009-03-06",1,"RP-070749","RP-090037","Powerwave Technologies, Andrew Wireless","ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com","RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report)","36.106, 36.143, 25.113",37,null,null,null,"2007-10-01","2010-03-16"]
[6276,380036,"      E-UTRAN Network Resource Model (NRM) Integration Reference Point (IRP)","E-UTRAN-OAM",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070738","-","Ericsson ","ELMDAHL, Per","SP#43 completed","new (32.761, 32.762, 32.763, 32.765)",38,21,null,null,"2005-06-17","2010-07-29"]
[6280,390104,"      SON Concepts and requirements","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080275","-","Vodafone","GOMPAKIS, Panagiotis","SP#42 completed","new 32.500",39,21,null,null,"2005-06-17","2008-11-25"]
[6283,25029,"Rel-8 LTE – Terminal Conformance Test Specification","LTE-UEConTest",1,"Rel-8","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Testing for Feature UID_20068 (LTE)","-",null,null,null,null,"2006-03-21","2008-06-01"]
[6284,25041,"   3G LTE – Terminal Protocol Conformance Test Specifications","LTE-UEConTest_SIG",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080647","RP-091060","NEC, Motorola","david.lecompte@nectech.fr, Jacob.John@motorola.com","RP#46 completed","36.521-1, 36.521-2, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3",null,null,null,null,"2006-03-21","2009-11-27"]
[6288,350035,"   UMTS 700 MHz FDD","RInImp8-UMTS700",2,"Rel-8","R4","2007-03-05","2008-05-30",1,"RP-070127","RP-080260","Nokia","Tuomo Saynajakangas","RP#40 completed","25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,null,null,"2004-09-27","2010-03-16"]
[6289,410018,"   UMTS 1880 MHz TDD","RInImp9-UMTS1880TDD",2,"Rel-8","R4","2008-09-12","2009-03-06",1,"RP-080757","RP-090044","CATT","Yuexia Song (songyuexia@catt.cn)","RP#43 completed","25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307",41,21,null,null,"2008-09-11","2009-03-10"]
[6293,370033,"   Performance requirements for 15 code reception with 16QAM/QPSK (FDD)","RInImp8-Hsdpa15codes",2,"Rel-8","R4","2007-06-11","2008-03-07",1,"RP-070745","RP-080043","Vodafone","tim.frost@vodafone.com","RP#39 completed",25.100999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6296,25050,"   Conformance Test Aspects – CS Voice Service over HSPA","RInImp8-CsHspa_UEConTest",2,"Rel-8","R5","2007-06-01","2008-09-12",1,"RP-080160","RP-080542","Huawei","baoyi@huawei.com","RP#41 completed","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2008-03-11","2008-09-09"]
[6299,360013,"   Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-64QamMimoHsdpa",2,"Rel-8","R1","2007-06-04","2008-09-12",1,"RP-070500","RP-080518","Ericsson","Johan.Bergman@ericsson.com","RP#41 completed","25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141",null,null,null,null,"2007-06-21","2010-08-03"]
[{"$f":"A6302+1","v":6302},370038,"   Enhanced UE Discontinuous Reception (DRX) for FDD","RANimp-DRX",2,"Rel-8","R2","2007-09-14","2008-09-12",1,"RP-070679","RP-080520","Nokia","luis.barreto@nokia.com","RP#41 completed. Continuation of Rel-7 work item \"Continuous connectivity for packet data users\" UID_20046.","25.306, 25.308, 25.321, 25.331, 25.423",37,null,null,null,"2007-10-01","2010-08-03"]
[6305,380075,"   64QAM for 1.28 Mcps TDD HSDPA","RANimp-64Qam1.28TDD",2,"Rel-8","R1","2007-12-04","2008-12-05",1,"RP-070924","RP-080806","ZTE","zfmail@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.102, 25.105, 25.123, 25.142, 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433",38,21,null,null,"2007-12-17","2010-08-03"]
[6306,380076,"   Enhanced CELL_FACH state in 1.28 Mcps TDD","RANimp-EnhState1.28TDD",2,"Rel-8","R2","2007-12-04","2008-12-05",1,"RP-071038","RP-080807","ZTE","zhang.yincheng@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.123, 25.221, 25.222, 25.224, 25.301, 25.302, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.401, 25.423, 25.425, 25.433, 25.435",38,21,null,null,"2007-12-17","2010-08-03"]
[6309,390030,"   HS-DSCH Serving Cell Change Enhancements","RANimp-HSDSCH",2,"Rel-8","R2","2008-03-07","2008-12-05",1,"RP-080227","RP-080811","Ericsson","henrik.enbuske@ericsson.com","RP#42 completed","25.101, 25.104, 25.133, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433",39,21,null,null,"2008-03-17","2010-08-03"]
[6312,25126,"Rel-8 RAN improvements - UE Conformance Testing","-",1,"Rel-8","R5","2008-05-30","2010-09-17",1,"-","-","-","-","Linked to Feature UID_20029 (RANimp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[6315,440010,"   Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates","RANimp-UEConTest_ImprovedL2LCRTDD",2,"Rel-8","R5","2009-05-29","2010-09-17",1,"RP-090491","RP-100737","CATT","Xiaozhong Chen (chenxiaozhong@datangmobile.cn)","RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink","34.108, 34.123-1, 34.123-2, 34.123-3",44,23,null,null,"2009-05-20","2010-09-09"]
[6318,430024,"   Conformance Test Aspects – Enhanced Uplink for CELL_FACH State in FDD","RANimp-UEConTest_EnhancedRACHCellFACHState",2,"Rel-8","R5","2009-03-06","2010-06-04",1,"RP-090152","RP-100483","Nokia","jarkko.hellsten@nokia.com","RP#48 completed. Testing for UID_370037","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",43,22,null,null,"2009-02-27","2010-08-03"]
[6322,450025,"   Conformance Test Aspects – MIMO for 1.28 Mcps TDD","RANimp-UEConTest_MIMOLCRTDD",2,"Rel-8","R5","2009-09-18","2010-06-04",1,"RP-100120","RP-100660","ZTE","huang.chun2@zte.com.cn","PR#48 completed. Testing for UID_400050","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[6323,450026,"   Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements","HSDSCH_UEConTest",2,"Rel-8","R5","2009-09-18","2010-03-19",1,"RP-090756","RP-100077","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#47 completed. Testing for UID_390030","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[6327,51583,"   G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G1","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","43.055, 43.129, 43.246, 45.002, 45.008, 45.010",null,null,null,null,"2006-09-13","2010-09-09"]
[6328,52583,"   G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G2","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","44.018, 44.060, 48.008, 48.018",null,null,null,null,"2006-09-13","2010-09-09"]
[6331,55586,"U-TDOA Enhancement","GUTEN",1,"Rel-8","GP","2007-05-18","2007-11-16",1,"GP-070865","-","TruePosition","Terry Brooks (terri.brooks@trueposition.com)","GP#36 completed U-TDOA (Uplink Time Difference of Arrival) ","43.059, 45.008, 48.071",null,null,null,null,"2007-05-21","2009-05-30"]
[6334,53089,"   Update TS 51.010 Mobile Station (MS) Conformance Specification for GAN Enhancements","GANENH-MStest",2,"Rel-8","G3new","2007-05-15","2009-09-04",1,"GP-071563","-","T-Mobile","mohammed.versi@t-mobile.com","GP#43 completed",51.01,null,null,null,null,"2007-09-06","2009-09-07"]
[6337,400042,"   Media Requirements for CS over IP based User Plane","AoIP-CSoIP",2,"Rel-8","S4","2007-12-05","2008-12-11",1,"SP-080444","-","China Mobile, Ericsson","Karl.Hellwig@Ericsson.com","SP#42 completed","26.102, 26.103, 26.202",40,21,null,null,"2007-12-09","2008-11-21"]
[6340,400124,"      CT1 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722",23.009,40,21,null,null,"2007-09-19","2012-01-11"]
[6344,420038,"   Stage 1 for ANSS for LCS","ANSS",2,"Rel-8","S1","2008-12-11","2008-12-11",1,"-","-","-","-","SP#42 completed by 22.071 CR0077",22.071000000000002,42,22,null,null,"2008-12-08","2010-02-09"]
[6347,51149,"Conformance testing for the Latency Reductions feature","CTLATRED",1,"Rel-8","G1,G3new","2008-02-22","2010-03-05",1,"GP-080367","-","Ericsson","mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com","GP#45 completed","-",null,21,null,null,"2008-02-26","2010-03-05"]
[6349,51150,"   BTS conformance testing for the Latency Reductions feature","CTLATRED-BTStest",2,"Rel-8","G1","2008-02-22","2009-02-20",1,"GP-080369","-","Ericsson","mats.y.samuelsson@ericsson.com","GP#41 completed",51.021000000000001,null,21,null,null,"2008-02-26","2009-02-20"]
[6350,53091,"MS conformance testing of changes introduced by WI \"Support of Packet-switched Handover for GERAN A/Gb mode\"","PSHCT-MStest",1,"Rel-8","G3new","2008-02-22","2008-11-21",1,"GP-080411","-","Rohde & Schwarz","Franz.Segerer@ROHDE-SCHWARZ.COM","GP#40 completed",51.01,null,21,null,null,"2008-02-26","2008-11-22"]
[6353,400025,"Test - (Small) Technical Enhancements and Improvements for Rel-8","TEI8_Test",1,"Rel-8","R5,G3new","2007-03-07","2010-12-24",1,"-","-","-","-","-","-",40,21,null,null,"2005-11-04","2010-12-07"]
[6357,330010,"Deleted - never approved- FBI Phase 2 ","FBI2",1,"Rel-8","S2","2007-09-28","2007-09-28",1,"-","-","Nokia Siemens Networks","-","SP#38 stopped","-",null,null,"SP-38",null,"2003-06-09","2009-03-24"]
[6360,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[6362,400223,"   Deleted - Contact Manager API for Java™ Card test specification ","eUPHBOOK-Test",2,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Gemalto","jacques.seif@gemalto.com","CP#47 work stopped/abandoned","31.321 (internal interface (API))",40,21,"CP-47","PCG-24","2008-11-24","2010-03-09"]
[{"$f":"A6366+1","v":6366},7027,"Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M)","FS_M2M",1,"Rel-8","S1","2005-11-04","2007-03-08",1,"SP-050527","-","Siemens","Juergen Merkel","SP#35 completed. Spin-off SA3 Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M (UID_370053). SP#40 Spin-off new Feature UID_410030 (NIMTC)",22.867999999999999,null,null,null,null,"2005-11-04","2008-03-24"]
[6369,320025,"Study on support of a Public Warning System","FS_PWS",1,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-080054","-","T-Mobile","mark.younge@t-mobile.com","SP#39 completed. Spin-off Rel-9 Feature UID_380057 (PWS)",22.968,null,null,null,null,"2006-06-23","2008-03-20"]
[6372,340034,"Study on Value Added Services for Short Message Service","FS_VAS4SMS",1,"Rel-8","S1","2006-12-06","2007-12-07",1,"SP-060786","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","SP#38 completed. Spin-off New Feature UID_370026 (VAS4SM)",22.942,34,null,null,null,"2006-10-06","2010-08-31"]
[6373,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[6375,32085,"Study on 3GPP System Architecture Evolution","FS_SAE",1,"Rel-8","S2,S3","2004-12-03","2009-03-12",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#43 completed","-",null,null,null,null,"2005-01-31","2009-02-20"]
[6379,320028,"Study on Stage 2 aspects of IMS Service Brokering","FS_ISB_ST2",1,"Rel-8","S2","2006-06-19","2008-09-18",1,"SP-060443","-","Telcordia","raquel@research.telcordia.com","SP#41 completed. No spin-off activity proposed. [Note: IMS Service Brokering enhancements UID_31088 moved back from R8 to R7 to give a home to 22228CR0036_(Rel-7)_S1-051232. Hence, Rel-7 ISB has Stage 1 only (and is misaligned with Rel-7 Stages 2/3.]",23.81,null,null,null,null,"2006-07-17","2008-09-14"]
[6382,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[6384,330012,"   Study on centralized IMS services control ","FS_IMS_CSC",2,"Rel-8","S2","2006-10-23","2008-03-12",1,"SP-070494","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","SP#39 completed",23.891999999999999,null,null,null,null,"2006-02-16","2008-03-22"]
[6388,35065,"Study on Element Operations Systems Function (EOSF) definition","OAM7-NIM-EOSF",1,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070307","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#40 completed. WID updated SP-050608=>SP-070307",32.819000000000003,null,null,null,null,"2005-09-16","2008-04-28"]
[6391,340036,"Study on Management for LTE and SAE","FS_OAM_LTE_SAE",1,"Rel-8","S5","2006-12-07","2008-12-11",1,"SP-060753","-","Ericsson","robert.petersen@ericsson.com ","SP#42 completed",32.816000000000003,34,null,null,null,"2006-12-15","2008-11-25"]
[6392,350004,"Study on Charging Aspects of 3GPP System Evolution","FS_SAEcharg",1,"Rel-8","S5","2007-04-02","2007-12-06",1,"SP-070174","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#38 completed",32.82,null,null,null,null,"2005-11-24","2008-03-17"]
[6395,360030,"Study on IMS Application Server Service Data Descriptions for AS interoperability","FS_IMS_ASIO",1,"Rel-8","C4","2007-09-14","2008-09-12",1,"CP-070685","-","Alcatel-Lucent","Jean-Jacques Trottin","CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO)",29.864000000000001,null,null,null,null,"2007-09-05","2008-09-11"]
[6397,380023,"Study on InterWorking Function between MAP based and Diameter based interfaces","FS_MAP2Diam",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-070760","-","Huawei","liming49985@huawei.com","CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005",29.805,38,21,null,null,"2007-11-19","2008-11-22"]
[6401,350039,"Study on 3G Home NodeB/eNodeB","FS_RAN-HNBeNB",1,"Rel-8","R4","2007-03-05","2008-05-30",1,"RP-070257","RP-080289","Motorola","howard.thomas@motorola.com","RP#40 completed",25.82,null,null,null,null,"2007-03-29","2008-06-26"]
[6404,51148,"Study on Optimized Transmit Pulse Shape for Downlink EGPRS2-B ","WIDER",1,"Rel-8","G1","2007-11-16","2010-05-21",1,"GP-072026","-","Research In Motion, Nokia Siemens Networks","jdwyer@RIM.COM and eddie.riddington@nsn.com","GP#46 completed",45.912999999999997,null,null,null,null,"2008-02-26","2010-05-27"]
[6407,380068,"Deleted - Study on Evaluation of LCS Control Plane Solution for EPS","FS_LCS_EPS",1,"Rel-8","S2","2008-01-14","2008-05-30",1,"SP-070819","-","SiRF","-","SP#40 spin-off Feature UID_400038 (LCS_CPS_EPS). SP#40 FS stopped",23.890999999999998,38,null,"SP-40","PCG-21","2007-10-02","2009-03-24"]
[6410,0,"--- RELEASE 7 ---","-",1,"Rel-7","CP,GP,RP,SP","2005-05-02","2007-12-06",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6413,32107,"   Stage 1,2 of ServID","ServID",2,"Rel-7","S1,S2","2005-11-11","2006-05-31",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-","22.228, 23.228, 23.203",null,null,null,null,"2005-07-01","2008-07-01"]
[6414,320010,"   Stage 3 of ServID","ServID",2,"Rel-7","C1","2006-03-31","2007-03-15",1,"CP-060259","-","Ericsson","christer.holmberg@ericsson.com","CP#32 approved WID","23.218, 24.229",null,null,null,null,"2006-03-20","2008-07-01"]
[6417,7009,"   Deleted - TR on GRUU","GRUU",2,"Rel-7","S2","2005-11-14","2006-09-14",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","Abandoned","-",null,null,"SP-32",null,"2006-02-16","2008-07-01"]
[6421,7039,"   Stage 1 of MTSI","MTSI-REQ",2,"Rel-7","S1","2006-02-01","2006-09-29",1,"SP-060224","-","Ericsson","peter.bleckert@ericsson.com","-",22.172999999999998,null,null,null,null,"2006-03-21","2008-06-25"]
[6423,7040,"   Media handling and interaction in MTSI","MTSI-MHI",2,"Rel-7","S4","2006-03-15","2007-03-15",1,"SP-060225","-","Ericsson","olle.franceschi@ericsson.com","-",26.114000000000001,null,null,null,null,"2006-03-21","2008-06-25"]
[6426,7023,"   Deleted - duplicates UID7039 - IMS Multimedia Telephony Service ","MMTEL",2,"Rel-7","S1","2007-06-15","2007-06-15",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","-",22.172999999999998,null,null,"SP-32",null,"2006-03-02","2008-06-25"]
[6429,387001,"Maintenance of TISPAN release 1 common IMS","MCIMSTR1",1,"Rel-7","S2","2007-07-02","2008-03-07",1,"SP-070915","-","Ericsson","Raymond Forbes","-","http://www.3gpp.org/specs/TISPAN-IMS-ansfer.htm",38,21,null,null,"2008-01-10","2008-07-21"]
[6433,380004,"   Maintenance of TISPAN R1","MAINT_R1",2,"Rel-7","C1,C3,C4","2007-11-09","2008-03-07",1,"CP-080211","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#39 completed","24.404, 24.405, 24.406, 24.407, 24.408, 24.410, 24.411, 24.416, 29.421, 24.423, 24.428, 24.429, 29.433, 24.441, 24.403, 29.427, 24.430, 29.412",38,21,null,null,"2007-11-19","2008-04-15"]
[6434,32045,"PS domain and IMS impacts for supporting IMS Emergency calls (EMC1)","EMC1",1,"Rel-7","S2,S1,C1,C4,IETF","2000-09-18","2011-12-09",1,"SP-050604","-","Siemens","Rainer Liebhart","-","EMC1",null,null,null,null,"2003-03-27","2003-03-28"]
[6436,32046,"   Study on Stage 2 for IMS-level solution","EMC1",2,"Rel-7","S2","2003-02-26","2005-09-16",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2003-03-27","2005-12-22"]
[6439,32101,"   Deleted - Stage 2 Specification Phase - GPRS-level","EMC1",2,"Rel-7","S2","2007-03-02","2007-03-02",1,"SP-050604","-","Siemens","Rainer Liebhart","-","-",null,null,"SP-32",null,"2004-10-14","2007-06-22"]
[6442,521030,"      (IETF) CT1 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1-IETF","2006-01-09","2011-12-09",1,"CP-050529","-","Keith Drage","-","CP#54 completed","RFC 6442 (was draft-ietf-sipcore-location-conveyance)",52,27,null,null,"2011-06-20","2011-12-13"]
[6445,1646,"      CT1 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","24.008, 24.234",null,null,null,null,"2000-08-08","2007-09-12"]
[6448,34033,"Performance Characterization of VoIMS over HSDPA\\EUL channels","VoIMS-PCVoIMS",1,"Rel-7","S4","2005-03-15","2007-12-06",1,"SP-050089","-","Alcatel-Lucent","mcgowan@alcatel-lucent.com","-",26.934999999999999,null,null,null,null,"2005-03-21","2008-01-10"]
[6452,32110,"WLAN Interworking – Private Network access from WLAN 3GPP IP Access","WLANPNA",1,"Rel-7","S2,C1,C3,C4","2005-10-10","2006-09-26",1,"SP-050489","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2003-03-28","2005-10-07"]
[6455,11064,"      CT1 aspets for WLAN-PNA","WLANPNA-st3",3,"Rel-7","C1","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29",24.234000000000002,null,null,null,null,"2005-12-22","2006-05-31"]
[6456,13027,"      CT3 aspets for WLAN-PNA","WLANPNA-st3",3,"Rel-7","C3","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29",29.161000000000001,null,null,null,null,"2005-12-22","2006-06-23"]
[6458,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[6461,14028,"   Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking","WLANQOS",2,"Rel-7","C4","2006-09-22","2007-03-09",1,"CP-060418","-","Huawei","zhang.peng@huawei.com","CP#33 approved WID","29.234, 23.008",null,null,null,null,"2006-10-11","2008-07-18"]
[6464,32093,"   Stage 2 for LCS3 (including IMS emergency location aspects)","LCS3",2,"Rel-7","S2","2004-12-31","2006-09-15",1,"SP-050119","-","SiRF","brodilitz@sirf.com","SP#27 approved WID",23.271000000000001,null,null,null,null,"2005-03-22","2008-07-02"]
[6468,20012,"   Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications","LCS3-UEPos-UTDOA",2,"Rel-7","R2","2004-09-15","2007-12-17",1,"RP-040387","RP-070797","TruePosition","Robert Gross (rgross@polariswireless.com)","-","25.305, 25.453, new 25.111",null,null,null,null,"2004-09-27","2008-07-02"]
[6471,32108,"      Deleted - Study of work on an LCS architecture for I-WLAN.","LCS3-IWLAN-FSs2",3,"Rel-7","S2","2006-06-26","2007-03-02",1,"SP-060291","-","LG Electronics","dhshim@lge.com ; phede@lge.com","SP#41 TR withdrawn. All work transferred to specs",23.837,null,null,"SP-35",null,"2006-02-16","2008-07-02"]
[6474,31084,"MBMS Enhancements","MBMSE",1,"Rel-7","S1,R1,C3","2005-07-11","2007-11-30",1,"SP-050389","-","China Mobile","liuhongyfw@chinamobile.com","-","-",null,null,null,null,"2005-06-20","2008-06-25"]
[6477,340043,"   MBMS TDD Physical layer Enhancements","MBMSE-RANPhysTDD",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070241","RP-070291","IPWireless","Nicholas Anderson","-","25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123",34,null,null,null,"2005-11-21","2008-06-25"]
[6480,400058,"MBMS - UE Conformance Testing","MBMSE_UEConTest",1,"Rel-7","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Linked to Rel-7 Feature UID_31084 (MBMSE)","-",40,21,null,null,"2008-03-11","2009-04-01"]
[6482,400059,"   Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement","MBMSE-RANPhysLCRTDD_UEConTest",2,"Rel-7","R5","2008-05-30","2009-09-18",1,"RP-080318","RP-090715","CATT","chenxiaozhong@datangmobile.cn","RP#45 completed","34.108, 34.123-1",40,21,null,null,"2008-06-03","2009-09-11"]
[6483,400060,"   Conformance Test Aspects – MBSFN for FDD","MBMSE-UEConTest_RANPhysFDD",2,"Rel-7","R5","2008-05-30","2009-12-04",1,"RP-080336","RP-091214","Huawei","Xiang Li (trica_li@huawei.com)","RP#46 completed","34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",40,21,null,null,"2008-06-03","2009-11-26"]
[6487,50548,"   Towards AGNSS Concept","AGNSS-GP",2,"Rel-7","GP","2004-06-28","2007-08-31",1,"GP-042677","-","Alcatel","richard.couty@space.alcatel.fr","GP#36 completed","43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031",null,null,null,null,"2004-08-30","2012-05-21"]
[6490,31048,"Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM","USSD-USIM",1,"Rel-7","S1,C6","2004-03-05","2005-08-12",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","-",null,null,null,null,"2004-06-08","2008-09-10"]
[6493,31063,"Combinational Services ","CSICS",1,"Rel-7","S1,S2,C1,S4","2005-01-17","2006-03-06",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-","-",null,null,null,null,"2004-12-17","2008-07-02"]
[6495,32084,"   Stage 2 for CSICS","CSICS",2,"Rel-7","S2","2005-01-17","2005-07-15",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-",23.279,null,null,null,null,"2005-06-07","2008-07-02"]
[6499,31066,"   Stage 1 for CAMEL Trunk Triggers","TTCAMEL",2,"Rel-7","S1","2004-12-17","2005-12-05",1,"SP-040743","-","Nortel","Amar Deol (deola@nortelnetworks.com)","-",22.077999999999999,null,null,null,null,"2004-12-17","2008-07-18"]
[6502,320027,"   Stage 1 for ISB","ISB-s1",2,"Rel-7","S1","2005-12-07","2006-03-13",1,"SP-050830","-","Telcordia","jbakker@telcordia.com","No Rel-8 changes",22.228000000000002,null,null,null,null,"2005-11-04","2008-03-25"]
[6503,11045,"Enhancements of VGCS for public authority officials","EVGCS",1,"Rel-7","S1,C1,C4,G2","2004-08-27","2007-06-15",1,"SP-040304","-","-","-","Moved from Rel-6 UID_50563 Enhancements of VGCS in public networks for communication of public authority officials","43.068, 44.068, 24.008, 29.002",75,38,null,null,"2004-09-03","2006-07-17"]
[6506,11062,"      CT1 aspects of EVGCS","EVGCS",3,"Rel-7","C1","2004-08-27","2007-06-15",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-","43.068, 44.068, 24.008",null,null,null,null,"2005-09-14","2007-09-12"]
[6509,11055,"Improvements of VGCS for parallel use of services","IVGCS",1,"Rel-7","S1","2005-03-15","2007-03-15",1,"SP-070167","-","-","-","Voice Group Call Service","-",null,null,null,null,"2005-03-02","2007-03-26"]
[6512,11057,"   Protocol aspects ","IVGCS",2,"Rel-7","C1","2005-12-01","2007-03-15",1,"NP-050141","-","T-Mobile","Dieter Jacobsohn","Previous name (before CT32) was Architecture and protocol aspects",44.067999999999998,null,null,null,null,"2005-09-14","2006-05-31"]
[6515,31071,"Open Service Access (OSA) Rel-7 ","OSA7",1,"Rel-7","S1,C5","2005-03-15","2007-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-","-",null,null,null,null,"2005-03-22","2005-09-15"]
[6517,31072,"      Service Requirements for OSA Service Broker","OSA7",3,"Rel-7","S1","2005-03-15","2005-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-",22.126999999999999,null,null,null,null,"2005-03-22","2006-02-16"]
[6521,7018,"      Parlay X Message Broadcast Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-15, 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[6524,340001,"      Parlay-X Device Capabilities and Configuration","OSA7",3,"Rel-7","C5","2006-10-26","2007-06-08",1,"CP-070200","-","Telenor","-","-","29.199-18, 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[6525,340002,"      Parlay-X Multimedia Streaming Session Management Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","Telenor","-","-","29.199-19, 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[6528,31053,"Selective Disabling of UE Capabilities","SDoUE",1,"Rel-7","S1,S2,C1","2005-01-24","2007-06-15",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06","-",null,null,null,null,"2004-08-30","2008-07-17"]
[6532,7041,"Network selection enhancements (NSP)","NSP",1,"Rel-7","S1","2006-03-15","2007-06-15",1,"SP-060220","-","O2","chris.friel@O2.com","-","-",null,null,null,null,"2005-11-04","2006-03-22"]
[6534,320013,"   Procedural aspects of NSP","NSP-CR",2,"Rel-7","C1","2006-06-02","2007-06-15",1,"CP-060357","-","Motorola","Andrew Howell","-","23.122, 24.008, 31.102",null,null,null,null,"2006-06-21","2007-05-04"]
[6537,32065,"   TR on Stage 2","ACBOP",2,"Rel-7","S2","2004-03-15","2005-03-31",1,"SP-040338","-","NTT DoCoMo","Jean-Jacques Davidian (davidian@docomo.fr)","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[6541,50117,"   Deleted - Extra ACBOP information in GERAN","ACBOP",2,"Rel-7","GP","2006-09-08","2006-09-08",1,"-","-","-","-","-",44.018000000000001,null,null,"RP-33",null,"2004-04-14","2006-07-20"]
[6543,7001,"   TISPAN Rel 1 related aspects","FBI-TIS1",2,"Rel-7","S2,S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2006-02-16"]
[6544,32075,"      Stage 2 of FBI for TISPAN R1","-",3,"Rel-7","S2","2004-10-14","2006-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2006-05-31"]
[6547,11060,"         CT1 aspects of FBI for TISPAN R1","-",4,"Rel-7","C1","2003-11-05","2006-11-30",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","24.819, 24.229",null,null,null,null,"2004-09-03","2007-01-05"]
[6550,33027,"      Security Enhancements for FBI","FBI-ISE",3,"Rel-7","S3","2005-06-28","2005-12-08",1,"SP-050395","-","Ericsson","Bengt.Sahlin@ericsson.com","Duplicated entry (\"ACCSEC2\", \"Access Security Enhancements\", SP-040865) deleted by A.Sultan",33.203000000000003,null,null,null,null,"2005-06-20","2007-05-29"]
[6554,7032,"      SA5 Charging aspects of FBI for PacketCable","FBI-PCBL-CH",3,"Rel-7","S5","2006-03-31","2006-12-07",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","03/2006 SP#31 WID approved","32.240, 32.260, 32.298, 32.299",null,null,null,null,"2006-03-20","2007-03-29"]
[6556,32094,"   FS on SMSIP","-",2,"Rel-7","S2","2004-10-14","2005-06-13",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID",23.803999999999998,null,null,null,null,"2005-06-07","2008-07-15"]
[6559,310002,"      CT1 aspects for SMSIP","-",3,"Rel-7","C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","23.040, 24.229",null,null,null,null,"2006-04-13","2008-07-15"]
[6563,32103,"   Stage 2 for PCC","-",2,"Rel-7","S2","2005-07-04","2006-09-15",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.",23.202999999999999,null,null,null,null,"2005-07-01","2008-07-18"]
[6566,13029,"   Gx reference point for Policy and Charging Control","PCC-Gx",2,"Rel-7","C3","2005-12-02","2007-11-30",1,"CP-060434","-","Siemens","Thomas.Belling@nsn.com","-","29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208)",null,null,null,null,"2005-12-13","2008-07-18"]
[6567,13030,"   Rx reference point for PCC CT3 aspects","PCC-Rx",2,"Rel-7","C3,C1","2005-12-02","2007-11-30",1,"CP-060435","-","Ericsson","j.javier.pastor@ericsson.com","WID approved at CP#30, Revised at CP#31, Revised at CP#33","-",null,null,null,null,"2005-12-13","2008-07-18"]
[6569,7008,"      PCC-Rx CT1 aspects","PCC-Rx-Gx-c1",3,"Rel-7","C1","2005-12-02","2007-06-15",1,"CP-060435","-","Ericsson","j.javier.pastor@ericsson.com","-",24.228999999999999,null,null,null,null,"2005-12-13","2008-07-18"]
[6572,31085,"   Stage 1 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S1","2005-03-17","2005-09-28",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",22.100999999999999,null,null,null,null,"2005-09-19","2008-07-21"]
[6576,11066,"      CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C1","2006-02-01","2007-06-15",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-","24.206, 24.216",null,null,null,null,"2005-10-04","2008-07-21"]
[6578,13032,"      Deleted - CT3 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C3","2006-11-02","2006-11-02",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-",29.163,null,null,"CP-33",null,"2005-10-04","2008-07-21"]
[6582,320003,"   Stage 2 specification for One Tunnel solution","OPTUNEL-Stage2",2,"Rel-7","S2","2006-09-11","2006-12-15",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","-",23.06,null,null,null,null,"2004-08-30","2008-07-15"]
[6585,340015,"   Stage 3 of CStermS","-",2,"Rel-7","C1","2006-12-14","2007-06-15",1,"CP-070239","-","Samsung","chenho.chin@samsung.com","CP-34 approved WID. CP-35 updated WID ","24.229, 24.279",34,null,null,null,"2007-01-05","2008-07-17"]
[6588,33023,"Trust Requirements for Open Platforms in 3GPP","TrustOP",1,"Rel-7","S3","2005-01-03","2006-11-30",1,"SP-040863","-","Nokia","Silke.Holtmanns@nokia.com","WID approved SP#26. ",33.905000000000001,null,null,null,null,"2005-03-24","2008-07-16"]
[6589,33024,"Development of UEA2 and UIA2","AlgUEA2",1,"Rel-7","S3","2004-12-01","2005-12-09",1,"SP-040864","-","TeliaSonera","per.christoffersson@teliasonera.com","WID approved SP#26, Dependant on Funding Availability. ","35.919, 35.215, 35.216, 35.217, 35.218",null,null,null,null,"2005-03-24","2008-07-16"]
[6593,732030,"Security enhancements","SEC7",1,"Rel-7","S3,C1,C4","2005-09-12","2006-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2005-11-04","2008-07-16"]
[6594,732031,"   HTTPS connection between a UICC and a NAF","SEC7-HSUN",2,"Rel-7","S3,C1","2005-09-12","2005-09-12",1,"SP-050573","-","Gemalto","JSeif@axalto.com, mireille.pauliac@gemplus.com","-","33.918, 33.222, 24.109",null,null,null,null,"2005-11-04","2008-07-16"]
[6598,310004,"      SA3 aspects of SEC7-NDS-TCAPsec","SEC7-NDS-TCAPsec-SA3",3,"Rel-7","S3","2005-09-12","2006-03-10",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-",33.204000000000001,null,null,null,null,"2005-11-04","2008-07-16"]
[6601,7043,"Interoperability between VGCS/VBS and A/Gb flexibility","VGCSFlex",1,"Rel-7","C1,C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","Voice Group Call Service","-",null,null,null,null,"2006-03-22","2008-07-21"]
[6604,13023,"DIAMETER on the GGSN Gi interface","DIAMGi",1,"Rel-7","C3","2004-09-10","2006-12-08",1,"CP-060431","-","Vodafone","Nico.Gabriele@vodafone.com","-",29.061,null,null,null,null,"2005-01-18","2008-07-15"]
[6607,340047,"PDU multiplexing at Nb Interface with IP transport","NbIPMux",1,"Rel-7","C3","2006-12-04","2008-07-22",1,"CP-070105","-","Alcatel-Lucent","Jean.Rzeznik@alcatel-lucent.fr","-",29.414000000000001,34,null,null,null,"2007-03-08","2007-05-04"]
[6610,13026,"   Deleted - CT3 aspects of Mp","-",2,"Rel-7","C3","2006-09-22","2006-09-22",1,"-","-","Ericsson","philip.hodges@ericsson.com","CP#34: CT3 not involved in Mp interface definition",29.161999999999999,null,null,"CP-33",null,"2003-01-13","2008-07-15"]
[6611,320009,"   Procedures description","Mp-PROCc4",2,"Rel-7","C4","2006-06-02","2007-03-09",1,"CP-070246","-","Huawei","Chencheng@huawei.com","-",23.332999999999998,null,null,null,null,"2006-06-21","2008-07-15"]
[6614,350003,"Mobile Termination whilst the MS is moving to another MSC","MTmovMS",1,"Rel-7","C4","2007-03-09","2007-05-31",1,"CP-070334","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","-","23.008, 23.012, 23.018, 23.078, 23.079, 29.002",null,null,null,null,"2007-03-29","2007-05-29"]
[6617,330001,"High speed interface between the UICC and the ME","HSI",1,"Rel-7","C6","2006-09-22","2007-11-30",1,"CP-070259","-","Gemalto","jacques.seif@GEMALTO.COM","Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45",31.100999999999999,null,null,null,null,"2006-09-21","2008-01-11"]
[6620,34034,"3G-324M Video Telephony Call Setup Times Improvements","VTCSTI",1,"Rel-7","S4","2005-06-08","2006-09-27",1,"SP-050404","-","Vodafone","edward.hall@vodafone.co.uk","-",26.911000000000001,null,null,null,null,"2005-06-16","2006-11-29"]
[6623,34036,"End-to-End Multimedia Services Performance Metrics","E2EMSPM",1,"Rel-7","S4","2005-09-28","2007-03-15",1,"SP-050433","-","China Mobile","zhangyanyf@chinamobile.com","-",26.943999999999999,null,null,null,null,"2005-10-04","2007-03-08"]
[6627,35044,"      Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050302","-","Motorola","-","-","32.731/2/3/5, 32.631/2/3/5",null,null,null,null,"2005-06-17","2007-03-29"]
[6628,35046,"      Co-operative Element Management interface (CO-OP) (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050304","-","Motorola","-","-","32.806, 32.814, 32.101",null,null,null,null,"2005-06-17","2007-03-29"]
[6632,35050,"      Integration Reference Point (IRP) Security Management","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050308","-","Huawei","Christian.Toche@huawei.com","-","32.372/3/5, 32.111,32.30x,32.32x,32.33x,32.34x,32.35x,32.36x,32.41x,32.60x,32.61x,32.66x",null,null,null,null,"2005-06-17","2007-03-29"]
[6633,35052,"      Partial suspension of Itf-N during maintenance/testing (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050310","-","Siemens","-","-","32.381/2/3/5",null,null,null,null,"2005-06-17","2007-06-22"]
[6636,35064,"      Backward and Forward Compatibility of IRP systems","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050630","-","Ericsson ","-","-",32.154000000000003,null,null,null,null,"2005-09-16","2007-06-22"]
[6640,35043,"   Rel-7 Performance Management","OAM7-PM",2,"Rel-7","S5","2005-09-02","2007-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2005-06-17","2007-03-29"]
[6643,35059,"      Add TDD specific counters in Performance measurement","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050317","-","CATT","-","-",32.405000000000001,null,null,null,null,"2005-06-17","2007-03-29"]
[6645,35069,"      Performance measurements definition for IMS","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050631","-","China Mobile","-","-","32.404,32.409,32.437, 32.632/3/4/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[6649,35062,"      Trace record content for UTRAN TDD","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050628","-","Nokia","-","-","32.421, 32.422, 32.423",null,null,null,null,"2005-03-02","2007-03-29"]
[6652,35070,"      Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management","-",3,"Rel-7","S5","2005-09-02","2006-12-15",1,"SP-050629","-","Nokia","-","-","32.421,32.422,32.423. 3 new 32.4x1,2,3",null,null,"SP-33",null,"2005-03-02","2007-03-29"]
[6654,320008,"   Alternate Charged Party (ACP) for IMS","CH7-IMS-ACP",2,"Rel-7","S5","2006-05-22","2007-06-14",1,"SP-060442","-","Lucent","njmazzarella@alcatel-lucent.com","-","32.240, 32.260, 32.298, 32.299",null,null,null,null,"2006-05-22","2007-06-22"]
[6655,330004,"   Align 3GPP Charging with OMA PoC Enabler Release 2.0","CH7-PoC",2,"Rel-7","S5","2006-09-28","2007-06-14",1,"SP-060546","-","Siemens","Gerald.Goermer@nsn.com","09/2006 SP#33 WID approved","32.240, 32.272, 32.299, 32.298",null,null,null,null,"2006-10-09","2007-06-22"]
[6658,22003,"   MIMO - Layer 2,3 aspects","MIMO-L23",2,"Rel-7","R2","2003-09-12","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037",25.876000000000001,null,null,null,null,"2003-03-27","2008-06-24"]
[6662,25037,"      Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD","MIMO-UEConTest_FDD",3,"Rel-7","R5","2007-03-09","2008-03-07",1,"-","-","Qualcomm","svora@qualcomm.com","-","34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-20","2010-06-16"]
[6665,20067,"   UMTS 2.6 GHz 7.68 Mcps TDD","RInImp-UMTS26VHCRTDD",2,"Rel-7","R4","2006-06-15","2006-09-15",1,"RP-060349","RP-060451","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#33 completed","25.102, 25.105, 25.123, 25.113, 25.142, 34.124",null,null,null,null,"2006-06-21","2010-07-27"]
[6667,20025,"   UMTS 2.6 GHz TDD","RInImp-UMTS2600TDD",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040553","RP-050661","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#30 completed","25.102, 25.105, 25.113, 25.123, 25.142, 25.331, 25.942, 25.306, 25.307, 34.122, 34.124",null,null,null,null,"2005-01-04","2010-07-27"]
[6671,20045,"   Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2)","RInImp-HSPerf-Type3",2,"Rel-7","R4","2005-03-15","2005-03-15",1,"RP-050362","RP-060015","Cingular","Marc Grant","RP#27 completed",25.100999999999999,null,null,null,null,"2005-06-20","2010-07-27"]
[6674,7028,"      Additional minimum UE performance requirement for downlink physical channels in support of MTCH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-MBMS",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060183","RP-060678","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[6677,20047,"   Deleted (not approved at PCG) - UMTS 2.6 GHz FDD DL External","RInImp-UMTS2600Ext",2,"Rel-7","R4","2005-09-15","2005-09-15",1,"-","-","T-mobile","han.van.bussel@t-mobile.de","This item was conditionnaly approved pending decision of PCG#16 who decided not to approve it","25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,"RP-31","PCG-16","2005-10-05","2005-12-22"]
[6678,25025,"Rel-7 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-7","R5","2005-11-11","2008-09-12",1,"-","-","-","-","Linked to Feature UID_20028 (RInImp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[6680,25008,"   UE Conformance Test for UMTS 900 MHz (band VIII)","RInImp-UMTS900_Test",2,"Rel-7","R5","2005-11-11","2006-06-02",1,"-","-","Qualcomm","hanye@qualcomm.com","RP#32 completed","34.108, 34.121",null,null,null,null,"2002-02-28","2006-03-21"]
[6684,25028,"   Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz","RInImp-UEConTest_UMTS1721Ext",2,"Rel-7","R5","2006-12-01","2007-06-01",1,"RP-060676","RP-070312","Motorola","carolyn.taylor@motorola.com","RP#36 completed","34.108, 34.121-1, 34.121-2",null,null,null,null,"2006-09-20","2007-06-11"]
[6687,20029,"Rel-7 RAN improvements","-",1,"Rel-7","RP,S5","2004-12-15","2007-06-15",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2005-01-04","2008-06-25"]
[6689,20031,"   Delay optimization for procedures applicable to CS and PS Connections","RANimp-DelayOpt",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050386","RP-060453","Nokia","juho.pirskanen@nokia.com","RP#33 completed","25.815, 25.321, 25.322, 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[6693,7030,"   Extended WCDMA Cell Range","RANimp-ExtCell",2,"Rel-7","R3","2006-03-15","2006-12-15",1,"RP-060212","RP-060685","Ericsson","Muhammad Kazmi","RP#34 completed","25.133, 25.423, 25.425, 25.433, 25.435, 25.453, 25.331",null,null,null,null,"2006-03-21","2010-07-27"]
[6696,340038,"   64QAM for HSDPA (FDD)","RANimp-64QamDownlink",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070223","RP-070287","Ericsson","Johan.Bergman@ericsson.com","RP#36 completed","25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141",null,null,null,null,"2006-10-06","2010-07-27"]
[6697,340039,"   Improved L2 support for high data rates","RANimp-L2DataRates",2,"Rel-7","R2","2006-12-15","2007-06-04",1,"RP-070242","RP-070289","Ericsson","Janne.Peisa@ericsson.com","RP#36 completed","25.301, 25.308,25.306, 25.321, 25.322, 25.331, 25.433, 25.435, 25.423, 25.425, 25.999",null,null,null,null,"2006-10-06","2010-07-27"]
[6700,20166,"      RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs)","-",3,"Rel-7","R3","2006-06-02","2007-03-16",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[6704,25031,"   Conformance Test Aspects – 64QAM for HSDPA (FDD)","RANimp-UEConTest_64QamDownlink",2,"Rel-7","R5","2007-03-09","2008-03-03",1,"RP-071319","RP-080059","Ericsson","leif.mattisson@ericsson.com","RP#39 completed","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[6706,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[6709,20014,"7.68 Mcps TDD option","VHCRTDD",1,"Rel-7","R1,R2,R3,R4,R5","2004-09-15","2007-09-14",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","-",null,null,null,null,"2004-09-27","2010-07-27"]
[6712,20017,"   VHCRTDD: Layer 2 and layer 3 protocol aspects","VHCRTDD-L23",2,"Rel-7","R2","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","drichards@ipwireless.com","RP#31 completed","25.301, 25.302, 25.305, 25.306, 25.321, 25.331",null,null,null,null,"2004-09-27","2010-07-27"]
[6715,25027,"   Conformance Test Aspects - 7.68 Mcps TDD","VHCRTDD-UEConTest",2,"Rel-7","R5","2006-09-20","2007-09-14",1,"RP-060482","RP-070307","IPWireless","tspeight@ipwireless.com","RP#37 completed","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[6718,20037,"   EDCHTDD: Physical Layer","EDCHTDD-Phys",2,"Rel-7","R1","2005-03-15","2006-09-15",1,"-","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","25.201, 25.221,25.222, 25.223, 25.224, 25.225",null,null,null,null,"2005-03-15","2010-07-27"]
[6719,20038,"   EDCHTDD: Layer 2 and 3 Protocol Aspects","EDCHTDD-L23",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"-","RP-060462","IPwireless","drichards@ipwireless.com","RP#33 completed","25.301, 25.302, 25.306, 25.321, 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[6722,20055,"1.28 Mcps TDD Enhanced Uplink","LCRTDD-EDCH",1,"Rel-7","R1,R2,R3,R4,R5","2006-03-15","2008-09-12",1,"RP-060202","RP-070296","CATT","Haijing Hu","RP#35 completed","-",null,null,null,null,"2006-03-21","2010-07-27"]
[6726,20059,"   1.28 Mcps TDD Enhanced Uplink: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","LCRTDD-EDCH-RF",2,"Rel-7","R4","2006-03-15","2007-06-15",1,"-","RP-070296","CATT","Yuexia Song (songyuexia@catt.cn)","RP#36 completed","25.102, 25.105, 25.123, 25.142",null,null,null,null,"2006-03-21","2010-07-27"]
[6728,490016,"Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD","LCRTDD_MB_MF_UEConTest",1,"Rel-7","R5","2010-09-17","2011-09-16",1,"RP-100805","RP-110968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD.","UTRA 34.108, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-08","2011-09-06"]
[6731,51138,"   Inclusion of the 698 – 746 MHz band into GERAN core specifications","GSM710-core",2,"Rel-7","G1","2005-01-03","2005-06-30",1,"-","-","-","-","Completed","24.008, 43.022, 44.018, 44.118, 45, 001, 45.005, ",null,null,null,null,"2005-09-12","2005-09-15"]
[6735,50564,"Support of Conversational Services in A/Gb mode via the PS domain","SCSAGB",1,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-061501","-","Ericsson","gunnar.hedby@ericsson.com","Originally started Nov. 2003 as GP-030443","-",null,null,null,null,"2005-04-21","2007-05-29"]
[6738,52144,"   Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode","SCSAGB-RLCNP",2,"Rel-7","G2","2006-06-30","2006-11-17",1,"GP-061503","-","Ericsson","gunnar.hedby@ericsson.com","-","43.955, 43.064, 44.060, 45.001, 45.002, 45.003, 45.005, 45.010, 51.010, 51.021",null,null,null,null,"2006-07-05","2008-01-10"]
[6739,52138,"   Deleted- Radio Channel Support","SCSAGB-RCHS",2,"Rel-7","G2","2006-07-17","2006-07-17",1,"GP-051166","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,"SP-32",null,"2005-04-21","2006-05-11"]
[6741,50565,"Addition of new frequency band to GSM (T-GSM810)","TGSM810",1,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-050945","-","Huawei","chende@huawei.com","-","45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060, 51.010-1, 51.021",null,null,null,null,"2005-04-21","2007-05-29"]
[6744,53082,"   Changes to BTS testing specification","TGSM810-BTStest",2,"Rel-7","G1","2005-04-08","2005-11-11",1,"GP-050948","-","Huawei","chende@huawei.com","-",51021,null,null,null,null,"2005-04-21","2005-12-22"]
[6747,55095,"   Deleted - MS Conformance Testing","HODSRDTM-MStest",2,"Rel-7","G3new","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","Stopped, no work done. 12/2008 Marked as stopped (\"deleted\")","51-010",null,null,"GP-32",null,"2005-11-21","2008-12-15"]
[{"$f":"A6750+1","v":6750},50571,"   Performance Requirements for Mobile Station Receive Diversity, DARP Phase II","MSRD2-PerfReq",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060115","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",45.005000000000003,null,null,null,null,"2005-11-21","2007-03-08"]
[6753,50570,"   MS conformance test of DARP Phase II (MSRD)","MSRD2-Msconf",2,"Rel-7","GP","2005-11-11","2007-11-16",1,"GP-060114","-","Nokia","kent.pedersen@nokia.com","GP#36 completed",51.01,null,null,null,null,"2005-11-21","2007-09-12"]
[6757,53086,"   Downlink Dual Carrier – MS Conformance Test ","GDCDL-MStest",2,"Rel-7","G3new","2006-01-20","2009-09-04",1,"GP-060486","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#43 completed",51.01,null,null,null,null,"2006-01-24","2009-09-07"]
[6760,52145,"   Improved Ack/Nack reporting","LATRED-ACKNAR",2,"Rel-7","G2","2006-06-30","2007-08-31",1,"GP-061520","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021",null,null,null,null,"2006-07-05","2008-12-15"]
[6763,50584,"Higher Uplink performance for GERAN Evolution ","HUGE",1,"Rel-7","GP","2006-09-08","2011-05-20",1,"GP-071083","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#39 completed","-",null,null,null,null,"2006-09-13","2010-07-26"]
[6765,51141,"   Layer 1 Support for HUGE","HUGE-Layer1",2,"Rel-7","G1","2006-09-08","2008-02-22",1,"GP-061903","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#37 completed","45.001, 45.002, 45.003, 45.004, 45.008",null,null,null,null,"2006-09-13","2008-12-15"]
[6766,52149,"   Layer 2/3 Support for HUGE","HUGE-Layer23",2,"Rel-7","G2","2006-09-08","2007-08-31",1,"GP-061904","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#35 completed","24.008, 44.018, 44.060",null,null,null,null,"2006-09-13","2008-12-15"]
[6769,53087,"   MS Conformance Test for HUGE","HUGE-Mstest",2,"Rel-7","G3new","2006-09-08","2011-05-20",1,"GP-061906","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#50 completed",51.01,null,null,null,null,"2006-09-13","2011-05-21"]
[6773,51146,"   BTS Conformance Tests for REDHOT","REDHOT-BTStest",2,"Rel-7","G1","2006-11-17","2009-05-15",1,"GP-062492","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#42 completed",51.021000000000001,null,null,null,null,"2006-11-20","2009-05-18"]
[6776,25030,"Test - (Small) Technical Enhancements and Improvements for Rel-7","TEI7_Test",1,"Rel-7","R5","2006-06-02","2007-11-28",1,"-","-","-","-","-","-",null,null,null,null,"2010-05-26","2010-05-26"]
[6779,32115,"   Deleted - PS domain aspects to support IMS Emergency sessions","-",2,"Rel-7","S2","2006-06-23","2006-06-23",1,"SP-050604","-","Nokia","curt.c.wong@nokia.com","Approved at SP#29","23.867, 23.abc, 23.060, 23.002, 23.271",null,null,"SP-30",null,"2005-03-22","2005-12-22"]
[6782,11035,"   Deleted - Stage 3 for IMS Local services","-",2,"Rel-7","C1","2006-01-06","2006-01-06",1,"-","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,"SP-25",null,"2003-01-13","2004-09-09"]
[6785,14018,"Deleted: Generic User Profile Phase 2","-",1,"Rel-7","C4","2005-08-08","2006-06-30",1,"-","-","-","-","Created at TSG#27 by A. Sultan because of the move to Rel-7 of \"Common Objects\". ","-",null,null,"SP-27",null,"2005-03-09","2005-03-09"]
[6787,0,"Release 7 Studies","-",1,"Rel-7","CP,GP,RP,SP","2004-06-28","2007-09-17",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6788,31082,"Study on Multimedia Telephony Capabilities for IMS","MITE",1,"Rel-7","S1","2005-07-11","2006-07-31",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","Spin-off Feature UID_7038 (MTSI)",22.972999999999999,null,null,null,null,"2005-04-21","2008-07-01"]
[6792,31075,"Study on Videotelephony teleservice","VidTel",1,"Rel-7","S1","2005-03-01","2006-01-17",1,"SP-050506","-","T-Mobile","michael.kurz@t-mobile.at ","-",22.902999999999999,null,null,null,null,"2005-03-22","2008-06-27"]
[6795,31083,"Study on Transferring of emergency Call data","eCALL",1,"Rel-7","S1","2005-07-11","2006-03-31",1,"SP-050388","-","Motorola","jian.j.wu@motorola.com ","-",22.966999999999999,null,null,null,null,"2005-06-20","2010-08-31"]
[6798,35067,"Study on Itf-N Implementation Conformance Statement (ICS) template","OAM7-NIM-ICS",1,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050609","-","China Mobile","Li Yewen (liyewen@chinamobile.com)","SP#35 completed",32.811999999999998,null,null,null,null,"2005-09-16","2007-03-29"]
[6800,7034,"Study on Bandwidth Saving at Nb Interface with IP transport","BSNbIP",1,"Rel-7","C3","2006-03-10","2007-03-09",1,"CP-060438","-","Siemens","Thomas.Belling@siemens.com","Moved to FS at CT32 (in line with slides)",29.814,null,null,null,null,"2006-03-20","2010-07-27"]
[6804,320018,"Study on Support of (G)MSC-S - (G)MSC-S Nc Interface based on the SIP-I protocol","NcSIP",1,"Rel-7","C4,C3","2006-05-15","2007-09-14",1,"CP-070034","-","Vodafone","david.hutton@vodafone.com","-",29.802,null,null,null,null,"2006-06-21","2008-07-01"]
[6807,20023,"Study on Evolved UTRA and UTRAN","RANFS-Evo",1,"Rel-7","RP","2004-12-15","2006-09-15",1,"RP-040461","RP-060472","NTT DoCoMo","nakamurata@NTTDOCOMO.CO.JP","RP#33 (Sep 2006) completed. SR in RP-060472",25.911999999999999,null,null,null,null,"2005-01-04","2008-06-23"]
[6808,20034,"Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph","RANFS-HSTrains",1,"Rel-7","R4","2005-03-15","2006-06-15",1,"RP-050146","RP-060412","Vodafone","Mike.vogel@vodafone.com,tim.frost@vodafone.com","RP#32 (Jun 2006) completed. SR in RP-060412","none",null,null,null,null,"2005-03-15","2008-06-23"]
[6811,20051,"Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN","RANFS-MBMSImp",1,"Rel-7","R2","2005-12-15","2006-12-15",1,"RP-050746","RP-060692","LG Electronics","leego@lge.com","RP#34 completed",25.905000000000001,null,null,null,null,"2005-12-15","2012-07-26"]
[{"$f":"A6814+1","v":6814},20065,"Study on Scope of future FDD HSPA Evolution","RANFS-HSPAEvo",1,"Rel-7","RP","2006-03-15","2007-09-17",1,"RP-060217","RP-070533","Cingular","Don Zelmer (dz1069@att.com)","RP#37 (Sep 2007) completed. SR in RP-070533",25.998999999999999,null,null,null,null,"2006-03-21","2008-06-23"]
[6817,50120,"Study on GAN Enhancements","EGAN",1,"Rel-7","GP","2007-08-31","2007-08-31",1,"GP-062298","-","T-Mobile","janne.linkola@t-mobile.com","GP#35 completed",43.902000000000001,null,null,null,null,"2006-11-20","2007-05-29"]
[6820,31087,"Deleted - Study on Customised Alerting Tone (CAT) Requirements (was duplicated)","-",1,"Rel-7","S1","2006-06-30","2006-06-30",1,"SP-050607","-","-","-","Awaiting MCC SA3 input","-",null,null,"SP-31",null,"2005-11-04","2006-03-22"]
[6824,50095,"   Deleted - GERAN review of the TR","-",2,"Rel-7","GP","2005-06-30","2005-06-30",1,"-","-","-","-","-","-",null,null,"SP-26",null,"2003-07-23","2004-12-06"]
[6826,32099,"Deleted - VoIMS bearer related enhancements","VoIMS",1,"Rel-7","S2","2006-07-21","2006-07-21",1,"-","-","-","-","Created by MCC to group all VoIMS related items, after consultation of chairs","-",null,null,"SP-32",null,"2005-09-15","2008-06-25"]
[6827,32098,"   Deleted - Study on enhancement of radio performance for VoIMS","-",2,"Rel-7","S2","2006-07-21","2006-07-21",1,"SP-050351","-","Nortel","Laurence Lautier (lautierl@nortel.com)","WID approved SP#28. SA2#52 stopped",23.806999999999999,null,null,"SP-32",null,"2005-06-22","2006-05-31"]
[6830,34040,"Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) ","-",1,"Rel-7","S4","2007-06-22","2007-06-22",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP-38 stopped",26.966999999999999,null,null,"SP-38",null,"2006-12-10","2007-06-22"]
[6833,50552,"Deleted - Study on enhanced support of Video Telephony","VIDGER",1,"Rel-7","GP","2006-06-30","2006-06-30",1,"GP-042221","-","Ericsson","stefan.g.eriksson@ericsson.com","FS CLOSED at G#28 (no input)","-",null,null,"SP-32",null,"2004-10-15","2006-03-09"]
[6837,24006,"   Improving Receiver Performance Requirements for the FDD UE","RInImp-UERecPerf",2,"Rel-6","R4","2002-03-08","2003-09-19",1,"-","-","Intel","shimon.moshavi@INTEL.COM","-",25.100999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[6839,1476,"      FDD Base station classification","-",3,"Rel-6","R4","2000-08-14","2002-12-04",1,"-","-","Nokia","antti.toskala@nokia.com","-","25.104, 25.141",null,null,null,null,"2000-07-26","2004-07-08"]
[6842,24010,"   UMTS 1.7/2.1 GHz","RInImp-UMTS1721",2,"Rel-6","R4","2003-03-14","2003-03-14",1,"-","-","Nokia","jussi.numminen@NOKIA.COM","Introduction of UMTS1700/2100 (Band IV)","25.101, 25.104, 25.133, 25.141, 25.307, 25.331",null,null,null,null,"2003-10-02","2009-07-09"]
[6846,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[6848,25002,"      Testing of Performance of Receiver diversity for HSDPA","RInImp-HSPerf-RxDiv_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[6849,3,"Rel-6 RAN Feasibility Studies","-",1,"Rel-6","RP","2000-08-14","2005-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-07","2003-12-07"]
[6852,21000,"   FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD","RInImp-IfIsMLCR",2,"Rel-6","R1","2001-12-14","2003-09-19",1,"-","-","Samsung","Li Xiao Qiang (xqli@samsung.co.kr)","-",25.888000000000002,null,null,null,null,"2003-10-02","2004-07-08"]
[6855,21005,"   FS on Analysis on Higher Chip Rates for UTRA TDD evolutions","RInImp-FSVHCRTDD",2,"Rel-6","R1","2002-09-06","2004-09-14",1,"-","-","IPWireless","mbeale@ipwireless.com","Study finished at RP#25",25.895,null,null,null,null,"2003-10-02","2004-10-13"]
[6859,23006,"   Deleted - FS on the evolution of the UTRAN architecture","RANimp-FSEvo",2,"Rel-6","R3","2002-09-09","2004-12-14",1,"-","-","Nokia","woonhee.hwang@nsn.com, Antti.Toskala@nokia.com","Study Closed, work will continue within the FS on evolved UTRA and UTRAN","-",null,null,"RP-26",null,"2002-09-16","2005-01-13"]
[6861,20004,"   FDD Enhanced Uplink - Stage 2","EDCH-Stage2",2,"Rel-6","R2","2004-03-15","2004-12-14",1,"-","-","-","-","-",25.309000000000001,null,null,null,null,"2004-03-21","2005-01-13"]
[6864,20007,"   FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects","EDCH-IurIub",2,"Rel-6","R3","2004-03-15","2005-03-14",1,"-","-","Nortel","Saso Stojanovski","-","25.401, 25.420, 25.423, 25.430, 25.433",null,null,null,null,"2004-03-18","2005-03-25"]
[6868,624,"   RAB support enhancement","-",2,"Rel-6","R2","2003-03-14","2005-03-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","building block without particular end date",25.861999999999998,null,null,null,null,"2000-03-31","2005-01-13"]
[6871,20013,"      HS-DPCCH ACK/NACK Enhancement","RANimp-RABSE-ACKNACK",3,"Rel-6","R1","2004-09-15","2004-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","Approved at RP#25 as RP-040390","25.212, 25.214, 24.331, 25.433",null,null,null,null,"2004-09-27","2005-03-25"]
[6872,23009,"      Deleted - Iu enhancements for IMS support in RAN","RANimp-RABSE-IuEnhIMS",3,"Rel-6","R3","2003-03-14","2004-06-03",1,"-","-","Nortel","Philippe.Godin@nortelnetworks.com","Closed RP#24 due to the lack of progress","-",null,null,"RP-24",null,"2003-03-27","2006-01-13"]
[6874,20999,"   Beamforming Enhancements","RANimp-BFE",2,"Rel-6","R1","2003-09-19","2003-12-19",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","-","24.215, 25.423, 25.425, 25.433, 25.435",null,null,null,null,"2001-11-29","2004-07-08"]
[6877,23010,"   Remote Control of Electrical Tilting Antennas","RANimp-TiltAnt",2,"Rel-6","R3,S5","2003-03-14","2004-09-16",1,"-","-","Vodafone","Andreas.Hauser@vodafone.com","-","-",null,null,null,null,"2003-03-27","2004-04-14"]
[6881,32023,"Location Services enhancements 2","LCS2",1,"Rel-6","S2,S5,N4,R2,R4,R5,OMA","2001-01-15","2004-12-16",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-06-02"]
[6884,32053,"      Stage 3 - impacts MLP (Mobile Location Protocol) ","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[6887,32054,"      Stage 3 - impacts MLP and RLP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[6890,32055,"      Stage 3 - definition of RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[6893,32056,"      OMA Stage 3 for Location Services support for IMS public identities - impacts MLP, RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[6894,32026,"   New area event for location service triggering reports","-",2,"Rel-6","S2,N4,OMA","2002-06-03","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-05-21"]
[6898,20001,"   UE positioning for Location Services enhancements 2","LCS2-UEpos",2,"Rel-6","R2,R4,R5","2001-01-15","2004-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-16","2012-05-21"]
[6899,2475,"      Open SMLC-SRNC Interface within the UTRAN to support UTRAN Rel-4 positioning methods","LCS-Rel4Pos",3,"Rel-6","R2","2001-01-15","2003-09-19",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","-","25.305, 25.401, 25.450, 25.452, 25.453",null,null,null,null,"2001-03-20","2012-05-21"]
[6903,35035,"   LCS charging","LCS2-CH",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"SP-040778","-","France Telecom","alain.bibas@orange-ft.com","SP#26 completed","new 32.271",null,null,null,null,"2004-10-29","2012-05-21"]
[6906,2027,"      Deleted - SEC1 Stage 2 (Enhanced HE control of security)","-",3,"Rel-6","S3","2001-01-03","2002-06-14",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-09-22","2001-03-12"]
[6909,33017,"   Network Domain Security; Authentication Framework (NDS/AF)","SEC1-NDS-AF",2,"Rel-6","S3","2002-02-15","2004-02-13",1,"SP-030108","-","Nokia","tommi.viitanen@nokia.com","SP#19 approved WID",33.81,null,null,null,null,"2003-03-27","2011-08-08"]
[6912,32021,"IMS Phase 2","IMS2",1,"Rel-6","S1,S2,S3,S5,NP,R5","2000-08-28","2007-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-25","2004-07-08"]
[6915,31025,"   IMS Group Management","IMSGM",2,"Rel-6","S1","2002-03-14","2004-12-08",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[6916,31026,"      Stage 1 - TS on IMS group management","-",3,"Rel-6","S1","2002-03-14","2002-12-09",1,"-","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2003-12-07"]
[6919,11037,"   IMS Conferencing","-",2,"Rel-6","N1","2002-11-04","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[6922,31022,"   IMS Messaging","IMSM",2,"Rel-6","S1","2002-03-14","2005-12-30",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[6925,31033,"      CRs to 22.140 & 22.228","IMSM-CR",3,"Rel-6","S1","2002-03-14","2003-03-17",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","22.140,22.228",null,null,null,null,"2003-01-13","2010-09-07"]
[6928,60001,"      SIP/SIMPLE Instant messaging","-",3,"Rel-6","OMA","2004-01-01","2005-12-30",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040232","-",null,null,null,null,"2004-06-08","2005-03-25"]
[6932,11052,"      Procedured associated with IMS-ALG","-",3,"Rel-6","N1","2004-09-06","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2005-04-20","2005-06-02"]
[6933,11041,"   Review additional SIP Capabilities against IMS","-",2,"Rel-6","N1","2002-12-13","2004-09-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2003-01-13","2005-03-25"]
[6937,11044,"      Interworking for IPv6 to IPv4 (SIP / SDP aspects)","-",3,"Rel-6","N1","2004-05-11","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-03-01","2004-09-08"]
[6938,11017,"      stage 3 of interworking with non-IMS IP networks","-",3,"Rel-6","N1","2001-03-14","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2004-09-08"]
[6941,31036,"   Study of subscriber and operators relationship in IMS and related ISIM requirements for Rel 6”","-",2,"Rel-6","S1","2002-11-15","2002-12-12",1,"-","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2003-01-13","2003-07-04"]
[6945,11051,"   IMS Management objects","-",2,"Rel-6","N1","2004-09-03","2005-11-04",1,"NP-040494","-","-","-","-",24.167000000000002,null,null,null,null,"2004-12-06","2005-03-09"]
[6948,32068,"   Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC)","-",2,"Rel-6","S2","2003-09-08","2004-11-30",1,"SP-030384","-","Ericsson","Shabnam Sultana","-",23.978999999999999,null,null,null,null,"2003-10-15","2004-12-06"]
[6950,34029,"   Selection of one or more PoC codec(s) for PoC","-",2,"Rel-6","S4","2004-09-13","2004-12-16",1,"-","-","-","-","Completed","26.235, 26.236",null,null,null,null,"2004-10-01","2004-12-06"]
[6954,32028,"   Stage 2 for Interoperability","-",2,"Rel-6","S2","2002-09-16","2003-09-30",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2",23.864000000000001,null,null,null,null,"2002-11-08","2004-07-08"]
[6957,1365,"Support of Push Services","PUSH",1,"Rel-6","S1","2001-01-03","2004-02-27",1,"SP-000669","-","NTT Comware","Yoshinori Kitada","Changed from FS to actual support of Push",23.975999999999999,null,null,null,null,"2000-04-19","2005-01-19"]
[6959,32701,"   TR 23.976 on Push Architecture","-",2,"Rel-6","S2","2002-11-11","2004-02-27",1,"SP-030126","-","Research In Motion","Nick Alfano","-",23.975999999999999,null,null,null,null,"2002-09-26","2004-07-08"]
[6960,42009,"Rel-6 Multimedia Messaging (MMS) enhancements","MMS6",1,"Rel-6","T2,S1,S4,S5,OMA","2002-08-15","2005-12-07",1,"TP-030175","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2002-09-26","2004-12-06"]
[6963,42011,"   Technical realization of MMS6","-",2,"Rel-6","T2","2002-09-06","2004-12-10",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",23.14,null,null,null,null,"2002-09-26","2004-12-06"]
[6967,35034,"   MMS charging","MMS6-CH",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"SP-040778","-","-","-","SP#25 09/2004 completed",32.270000000000003,null,null,null,null,"2004-10-29","2006-01-13"]
[6970,42006,"   MExE Rel-6 Improvements and Investigations ","MEXE6-ENHANC",2,"Rel-6","T2","2002-03-08","2003-03-12",1,"TP-020017","-","TTPCom","Lars Brenk ( (lsb_ttpcom@HOTMAIL.COM)","-","-",null,null,null,null,"2002-03-21","2009-11-18"]
[6972,2062,"Subscription Management","SuM",1,"Rel-6","S5","2002-09-20","2005-03-17",1,"SP-040763","-","T-Mobile","istvan.aba@t-mobile.at","SP#27 03/2005 completed","32.140/1, 32.171/2/5, 32.803",null,null,null,null,"2000-10-09","2006-01-13"]
[6976,2503,"   Stage 3 for Presence Capability","-",2,"Rel-6","N1,N4","2002-04-01","2004-12-08",1,"NP-040492","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Dependency to 2 IETF drafts, no known work at the moment","New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328)",null,null,null,null,"2001-03-30","2011-08-09"]
[6979,2504,"   Security aspects of Presence Capability","-",2,"Rel-6","S3","2002-08-26","2002-12-12",1,"SP-020514","-","Ericsson","krister.boman@erv.ericsson.se","SP#17 approved WID S3-020429","-",null,null,null,null,"2001-03-30","2011-08-09"]
[6980,60003,"   SIMPLE Presence","-",2,"Rel-6","OMA","2004-01-01","2005-03-31",1,"SP-040232","-","-","OMA-LIAISON@mail.openmobilealliance.org","SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables","-",null,null,null,null,"2004-06-08","2011-08-09"]
[6983,50080,"      Requirements for the support of conversational services","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[6985,50093,"      Outline of impact and feasibility of these building blocks and their different solutions","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2003-01-13","2009-11-18"]
[6989,50063,"Flexible Layer One for GERAN","FLOGER",1,"Rel-6","GP,S3","2000-01-03","2004-06-25",1,"GP-021018","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2003-09-16"]
[6992,51002,"      Architecture in 45.001 and 43.051","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[6994,51004,"      Channel Coding in 45.003 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[6998,52072,"   Signalling and protocol support for a Flexible Layer One","FLOGER-SigPro",2,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-12-06"]
[7001,52075,"   Security for a Flexible Layer One","FLOGER-SecFLO",2,"Rel-6","S3,G2","2002-04-19","2003-08-29",1,"GP-021021","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-01-14"]
[7002,52076,"      Ciphering in 44.060, 44.160, 44.018, 44.118","-",3,"Rel-6","S3,G2","2002-04-19","2003-08-29",1,"GP-021021","-","Nokia","benoist.sebire@nokia.com","-","44.060, 44.160, 44.018, 44.118",null,null,null,null,"2002-05-23","2003-09-16"]
[7005,55079,"   Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE","FLOGER-BTSconf",2,"Rel-6","G3new","2004-02-06","2004-02-06",1,"GP-021023","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-27",null,"2002-05-23","2005-03-09"]
[7009,2545,"   Stage 1 for Multimedia Broadcast and Multicast Service","-",2,"Rel-6","S1","2001-05-11","2002-04-01",1,"-","-","-","-","-","22.146, 22.101",null,null,null,null,"2001-03-30","2012-07-26"]
[7011,32702,"      TR on MBMS Architectural Study","-",3,"Rel-6","S2","2001-09-24","2002-08-23",1,"-","-","-","-","-",23.846,null,null,null,null,"2002-09-26","2012-07-26"]
[7014,13015,"   Gmb interface for MBMS (CN3 part)","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"-","-","-","-","-",29.061,null,null,null,null,"2003-10-13","2012-07-26"]
[7017,31045,"   MBMS User Services","-",2,"Rel-6","S1,S4","2003-05-13","2006-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-30","2012-07-26"]
[7020,2481,"   Introduction of MBMS in RAN","MBMS-RAN",2,"Rel-6","R2,R4","2002-01-01","2005-09-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","-",null,null,null,null,"2001-03-20","2012-07-26"]
[7023,25024,"   MBMS UE Conformance Testing","MBMS-UEConTest",2,"Rel-6","R5,T1","2006-03-10","2008-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2006-09-22","2012-07-26"]
[7024,25014,"      RF/RRM Conformance Test Aspects – MBMS (FDD)","MBMS-RAN-RF_Test",3,"Rel-6","R5,T1","2006-06-02","2008-03-07",1,"-","-","Ericsson","leif.mattisson@ericsson.com","-","34.108, 34.109, 34.121-1, 34.121-2",null,null,null,null,"2002-02-28","2012-07-26"]
[7027,25011,"      Conformance Test Aspects – MBMS","MBMS_Test",3,"Rel-6","R5,T1","2006-03-10","2007-09-14",1,"-","-","Qualcomm","Shubhang Vora (svora@qualcomm.com)","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2012-07-26"]
[7031,52085,"      MBMS Re-synchronisation at cell change","-",3,"Rel-6","G2","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7033,50099,"      Simultaneous support of MBMS and non-MBMS services","-",3,"Rel-6","GP","2001-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7036,50088,"      MBMS channel allocations procedures to multiple MSs","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7040,50092,"      MBMS Security aspects","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7043,31006,"Speech Recognition and Speech Enabled Services","SRSES",1,"Rel-6","S1,S2,S4,OMA","2001-10-08","2005-12-30",1,"SP-010572","-","-","-","-","-",null,null,null,null,"2001-10-09","2004-09-08"]
[7044,31007,"   Speech Enabled Services Based on Distributed Speech Recognition (DSR)","DSR",2,"Rel-6","S1","2001-10-08","2002-03-15",1,"SP-010581","-","Qualcomm","Dwilliams@qualcomm.com","-","22.977, 22.941, 23.207, 22.243",null,null,null,null,"2001-10-09","2004-03-12"]
[7046,34700,"   Codec Work to Support Speech Recognition Framework for Automated Voice Services","SRSES-Codec",2,"Rel-6","S4","2002-10-15","2004-12-16",1,"SP-020687","-","Motorola","David Pearce (bdp003@motorola.com)","-","26.235, 26.236, 26.243, 26.177, 26.943",null,null,null,null,"2003-01-13","2004-12-06"]
[7049,31008,"Generic User Profile Rel-6","GUP",1,"Rel-6","S1,S3,N4","2001-10-08","2005-03-03",1,"SP-040515","-","-","-","-","-",null,null,null,null,"2001-10-09","2003-03-28"]
[7052,42002,"   Stage 2 - Data Description Method","-",2,"Rel-6","N4","2002-12-05","2005-03-03",1,"TP-020275","-","T-Mobile","kurt.bischinger@t-mobile.at","TR approved in CN#26",23.241,null,null,null,null,"2001-10-09","2005-03-09"]
[7055,31010,"Digital Rights Management","DRM",1,"Rel-6","S1,OMA","2001-10-08","2004-05-28",1,"SP-010577","-","-","-","Foreseen start and completion dates introduced by MCC (no indication at all on the WID)","-",null,null,null,null,"2001-10-11","2001-10-11"]
[7058,60006,"   Stage 3 for Digital Rights Management","-",2,"Rel-6","OMA","2004-01-01","2004-05-28",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2004-06-08","2005-03-25"]
[7062,31020,"   Technical Report on WLAN-UMTS Interworking","WLAN-TR",2,"Rel-6","S1","2000-01-03","2003-06-13",1,"SP-030712","-","T-mobile","Mark.Younge@t-mobile.com ","-",22.934000000000001,null,null,null,null,"2002-02-28","2004-06-08"]
[7065,32704,"   Security aspects of WLAN-UMTS Interworking","-",2,"Rel-6","S3","2002-09-30","2003-03-21",1,"SP-020514","-","Ericsson, BT","luis.lopez-soria@ece.ericsson.se, colin.blanchard@bt.com","SP#17 approved WID S3-020451","21.133, 33.106, 33.107, 33.108, 33.200, 33.203, 33.210, New 33.234",null,null,null,null,"2002-09-26","2011-08-09"]
[7068,11042,"   Stage 3 for scenario 2","-",2,"Rel-6","N1","2003-05-23","2004-09-08",1,"NP-030490","-","-","-","-","-",null,null,null,null,"2003-06-09","2005-03-09"]
[{"$f":"A7070+1","v":7070},35033,"   WLAN charging","WLAN-CH",2,"Rel-6","S5","2003-03-21","2005-09-22",1,"SP-030048","-","Nokia","Benni ALEXANDER ","-",32.252000000000002,null,null,null,null,"2004-10-29","2011-08-15"]
[7071,43010,"   USIM enhancements for WLAN Interworking","-",2,"Rel-6","T3","2003-09-05","2005-03-04",1,"TP-030185","-","Axalto","Jabellan@axalto.com","-",31.102,null,null,null,null,"2004-12-06","2011-09-01"]
[7074,31017,"   Stage 1 - Requirements for Priority Service","PRIOR-SR",2,"Rel-6","S1","2002-05-30","2003-09-17",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-","-",null,null,null,null,"2002-02-27","2010-08-31"]
[7078,31038,"   Stage 1 - CRs to implement Network Sharing","NTSharCR",2,"Rel-6","S1","2003-01-20","2003-12-19",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","22.011, 22.101, 22.115, 22.129",null,null,null,null,"2003-03-14","2009-11-10"]
[7081,22004,"   Enhancement of the support of network sharing in the UTRAN","NTShar-UTRANEnh",2,"Rel-6","R2","2003-09-19","2003-09-19",1,"-","-","TeliaSonera","Anders.Dahlen@TeliaSonera.com","-","25.401, 25.413, 25.331, 25.304",null,null,null,null,"2003-10-02","2005-01-13"]
[7084,32017,"   FS on Dynamic Policy control enhancements for end-to-end QoS","-",2,"Rel-6","S2","2002-07-15","2004-04-23",1,"SP-020540","-","Nortel","Claire Mousset","-","23.917 withdrawn (Contenall in 23.207)",null,null,null,null,"2002-01-24","2004-07-08"]
[7087,33002,"Subscriber certificates","SEC1-SC",1,"Rel-6","S3,S2,N1,N4,T3,OMA","2002-02-25","2004-12-08",1,"SP-010622","-","Nokia","valtteri.niemi@nokia.com","SP#14 approved WID","-",null,null,null,null,"2002-01-24","2011-08-08"]
[7090,14504,"   Stage 3 for Subscriber certificates","-",2,"Rel-6","N4,T3","2003-09-19","2004-11-30",1,"NP-030399","-","Nokia","Lauri Laitinen","Finished in CN4#26","23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111",null,null,null,null,"2003-10-15","2009-11-10"]
[7091,11049,"   Stage 3 Ua & Ub interfaces","-",2,"Rel-6","N1","2003-11-03","2004-12-08",1,"-","-","Nokia","-","-",24.109000000000002,null,null,null,null,"2004-03-01","2009-11-10"]
[7094,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[7097,15028,"   Policy management extensions","-",2,"Rel-6","N5","2002-10-31","2003-12-12",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-01-13","2005-01-13"]
[7100,15033,"   Introduction of migration support mechanism","-",2,"Rel-6","N5","2002-10-31","2003-12-10",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-03-27","2005-01-13"]
[7103,15037,"   Deleted - TR on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2004-09-17","2004-09-17",1,"-","-","-","-","N5#26:TR Completion 09/04¦consistent with CN1 delayed Rel-6 completion.","-",null,null,"NP-24",null,"2004-10-20","2004-10-21"]
[7105,50094,"   Addition of frequency bands to GSM – Changes to core specs","TAPS-Specs",2,"Rel-6","G1","2002-11-15","2002-12-20",1,"GP-022073","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2003-02-13"]
[7109,50130,"Seamless support of streaming services in A/Gb mode","SSStrea",1,"Rel-6","GP,S3","2000-01-03","2005-06-17",1,"GP-022561","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2004-01-14"]
[7112,51132,"   Performance study of cell change mechanisms","-",2,"Rel-6","G1","2000-01-03","2003-08-29",1,"GP-022562","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7113,51134,"      Performance of NACC","-",3,"Rel-6","G1","2000-01-03","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7116,52131,"   Reduction of service interruption times and packet loss during mobility procedures","-",2,"Rel-6","G2","2003-06-27","2005-06-17",1,"GP-022563","-","Vodafone","José Luis Carrizo Martínez","Completed at GERP#17","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7119,52135,"      PS Handover (within GERAN and between GERAN and UTRAN)","-",3,"Rel-6","G2","2003-06-27","2005-06-17",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7122,54132,"      Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode","-",3,"Rel-6","G4,G5","2003-12-19","2004-01-30",1,"GP-023424","-","Vodafone","José Luis Carrizo Martínez","Marked as stopped 10/2009","-",null,null,"GP-27",null,"2003-02-13","2009-10-13"]
[7125,31030,"Study on Privacy Capability","PrivCap",1,"Rel-6","S1","2003-11-10","2004-03-03",1,"SP-020579","-","Lucent","Michael Boote (mboote@alcatel-lucent.com)","-",22.949000000000002,null,null,null,null,"2002-11-08","2010-08-31"]
[7129,35014,"   Network Infrastructure Management ","-",2,"Rel-6","S5","2002-09-12","2004-12-16",1,"SP-040789","-","Ericsson","thomas.tovinger@ericsson.com","SP#26 12/2004 completed","32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5",null,null,null,null,"2002-11-08","2011-02-21"]
[7131,35022,"      Subscriber and UE trace management","-",3,"Rel-6","S5","2002-09-20","2004-12-16",1,"-","-","Nokia","kari.t.ronka@nokia.com","SP#26 12/2004 completed","32.421, 32.422, 32.423, 52.008",null,null,null,null,"2003-10-03","2006-01-13"]
[7132,23013,"      Subscriber and equipment trace in UTRAN","OAM-Trace-RAN",3,"Rel-6","R3","2003-06-06","2004-06-15",1,"-","-","Nortel","Yann Sehedi (sehedic@nortelnetworks.com)","-","25.413, 25.420, 25.423",null,null,null,null,"2003-07-04","2005-01-13"]
[7135,35037,"   Charging architecture and principles","-",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.24,null,null,null,null,"2004-10-29","2006-01-13"]
[7138,35026,"   Diameter charging applications","-",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.298999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[7142,35029,"      CS domain charging","-",3,"Rel-6","S5","2003-03-21","2004-03-18",1,"-","-","-","-","SP#23 03/2004 completed",32.25,null,null,null,null,"2004-10-29","2006-01-13"]
[7144,35031,"      CDR transfer","-",3,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.295000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[7147,32069,"      Overall definition of FBC architecture","-",3,"Rel-6","S2","2002-11-21","2004-03-02",1,"-","-","-","-","-","-",null,null,null,null,"2004-05-20","2005-03-09"]
[7151,1800,"Rel-6 UICC/USIM enhancements and interworking","USAT1",1,"Rel-6","T3","2000-09-25","2005-03-10",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2000-12-01"]
[7154,43006,"      2G/3G Java Card™ API based applet interworking","-",3,"Rel-6","T3","2003-03-17","2004-03-05",1,"TP-030031","-","Oberthur Card Systems","Stéphane Andrau","-","-",null,null,null,null,"2003-09-08","2005-01-19"]
[7155,43007,"      (U)SIM API for Java Card Testing","-",3,"Rel-6","T3","2003-03-17","2005-03-10",1,"TP-040186","-","Axalto","Christophe Begassat (cbegassat@axalto.com)","-",31.213000000000001,null,null,null,null,"2003-09-08","2005-06-02"]
[7157,43004,"   Rel-6 USIM toolkit enhancements","USAT1-API-MULTOS",2,"Rel-6","T3","2000-09-25","2005-03-04",1,"-","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2002-11-29","2005-01-19"]
[7160,502033,"         Test specification for C SIM API","-",4,"Rel-6","T3","2001-01-01","2001-09-28",1,"TP-000155","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2000-09-14","2010-02-09"]
[7164,34024,"   Stage 3 for Packet Switched Streaming Services Rel-6","PSSrel6-Stage3",2,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-020685","-","Ericsson","olle.franceschi@ericsson.com","TR tbc by Sept. 05","26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936",null,null,null,null,"2003-03-27","2009-11-13"]
[7166,34027,"Codec Enhancements for Packet Switched Conversational Multimedia Applications","CEPSCM",1,"Rel-6","S4","2004-03-16","2004-12-16",1,"SP-040066","-","Nokia","miska.hannuksela@nokia.com","-","26.235, 26.236",null,null,null,null,"2004-03-02","2004-12-06"]
[7169,12006,"Enhancement of dialled service for CAMEL","EDCAMEL",1,"Rel-6","S1,N2,N4","2003-03-28","2003-12-31",1,"SP-020818","-","Samsung","craig.bishop@samsung.com","-",22.077999999999999,null,null,null,null,"2003-03-14","2009-11-13"]
[7173,50601,"   Multiple TBF in A/Gb mode - Core","MULTBF-Agbmode",2,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","-","-",null,null,null,null,"2003-07-31","2003-09-16"]
[7176,50604,"      Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2004-12-06"]
[7177,50605,"   Deleted - Multiple TBF in A/Gb mode – MS testing","MULTBF-Testing",2,"Rel-6","G3new","2005-01-28","2005-01-28",1,"GP-022098","-","Ericsson","gunnar.mildh@era.ericsson.se","-","-",null,null,"GP-27",null,"2003-07-31","2005-03-09"]
[7179,50097,"   Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010.","ALTERE-TC",2,"Rel-6","G3new","2003-08-29","2005-09-02",1,"-","-","-","-","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[7182,50101,"Downlink Advanced Receiver Performance","DARP",1,"Rel-6","GP","2003-11-21","2005-09-02",1,"GP-041966","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7186,50105,"      Radio subsystem link control in 45.008 for DARP for GMSK modulated voice services","DARP-GMSK-LC",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7189,50108,"      Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-LC",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7192,50109,"Reduction of PS service interruption in Dual Transfer Mode","PSintDTM",1,"Rel-6","G2","2003-11-21","2005-06-24",1,"GP-032548","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7195,50112,"   Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures","PSintDTM-Reduct",2,"Rel-6","G2","2004-04-23","2004-11-12",1,"GP-032551","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[{"$f":"A7198+1","v":7198},12008,"CAMEL prepay interworking with SCUDIF","SCCAMEL",1,"Rel-6","N4,N3,S1","2003-12-08","2004-10-05",1,"NP-030584","-","Nokia","Keijo.Palviainen@Nokia.Com","-","22.078, 23.078, 29.078, 29.002, 23.172",null,null,null,null,"2004-03-03","2009-11-13"]
[7199,31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[7203,11053,"   Switching between voice and video call - Redial solution","-",2,"Rel-6","N1","2005-01-03","2005-06-17",1,"SP-040331","-","Vodafone","-","-","23.009, 24.008",null,null,null,null,"2005-04-20","2005-06-02"]
[7204,52137,"   Deleted - CS_VSS - GERAN2 Part","-",2,"Rel-6","G2","2005-09-02","2005-09-02",1,"SP-040331","-","Vodafone","-","-","-",null,null,"GP-26",null,"2004-01-28","2005-04-21"]
[7208,50544,"   FS on GAAI","GAAG",2,"Rel-6","GP","2004-06-25","2004-08-27",1,"GP-041592","-","Motorola","-","Feasibility Study",43.901000000000003,null,null,null,null,"2004-06-30","2005-03-25"]
[7211,50556,"   MS Conformance Test for GAAI","GAAI-CT",2,"Rel-6","GP","2004-08-27","2006-01-20",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)","-",null,null,null,null,"2004-10-15","2008-12-12"]
[7215,50562,"   Definition of radio resource management functionality for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-RRM",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051163","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-RRM","-",null,null,null,null,"2005-04-20","2006-01-13"]
[7216,33018,"Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces","-",1,"Rel-6","S3","2003-07-03","2003-12-26",1,"SP-030341","-","Toshiba","Raziq Yaqub (ryaqub@tari.toshiba.com)","SP#20 approved WID",33.817,null,null,null,null,"2003-07-25","2011-08-09"]
[7220,31029,"Deleted - Study of Feature Interactions Requirements","FINTER",1,"Rel-6","S1","2004-09-16","2004-09-16",1,"SP-020578","-","-","-","SP#25 stopped","-",null,null,"SP-25",null,"2004-10-20","2010-03-02"]
[7221,50563,"Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials","-",1,"Rel-6","GP,G2","2005-08-25","2005-09-02",1,"GP-041837","-","Siemens","kenneth.isaacs@roke.co.uk","GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials","44.018, 44.068, 48.008",null,null,"GP-26",null,"2005-04-20","2005-04-21"]
[7224,50502,"   Deleted - Stage 2","SCSAGB-Stage2",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030445","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[7227,50505,"   Deleted - replaced by 50561 - PS Handover","SCSAGB-PSH",2,"Rel-6","GP,N1","2003-11-24","2004-02-19",1,"GP-030448","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Started","-",null,null,"GP-18",null,"2003-02-13","2010-03-02"]
[7230,0,"--- RELEASE 5 ---","-",1,"Rel-5","NP,GP,RP,SP,TP","2000-01-03","2001-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7233,2476,"High Speed Downlink Packet Access","HSDPA",1,"Rel-5","R2,R5","2001-04-02","2007-03-09",1,"-","-","Motorola","Ravi Kuchibhotla","-","-",null,null,null,null,"2001-03-20","2001-12-10"]
[7237,2480,"   RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","HSDPA-RF",2,"Rel-5","R4","2001-04-09","2003-06-06",1,"RP-010262","-","Motorola","Howard Benn","-","-",null,null,null,null,"2001-03-20","2003-03-27"]
[7238,25000,"   Conformance Testing of HSDPA","HSDPA_Test",2,"Rel-5","R5","2003-09-19","2006-09-22",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7242,1477,"      TDD Base station classification","RInImp-BSClass-TDD",3,"Rel-5","R4","2000-08-14","2002-03-08",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-07-26","2002-06-21"]
[7243,24002,"      Base Station Classification for 1.28 Mcps TDD option","RInImp-BSClass-LCRTDD",3,"Rel-5","R4","2001-06-15","2002-06-14",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","-","-",null,null,null,null,"2001-07-05","2002-06-21"]
[7246,1221,"   FS on USTS","RInImp-USTS",2,"Rel-5","R1","2000-08-14","2001-12-21",1,"-","-","SK Telecom","D. Kim","-","-",null,null,null,null,"2000-04-26","2002-02-28"]
[7250,1839,"   Deleted - Conformance Test Spec. improvements in Radio Interface","-",2,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2001-10-11"]
[7253,500009,"Rel-5 RAN improvements","-",1,"Rel-5","RP","2001-03-16","2007-03-09",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2002-06-21"]
[7255,23000,"      Iur common transport channel efficiency optimization","RANimp-RRMopt-ctc",3,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Shahrokh Amirijoo","-","-",null,null,null,null,"2001-09-19","2002-03-21"]
[7259,2489,"   Separation of resource reservation and radio link activation","RANimp-SepRR",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[{"$f":"A7262+1","v":7262},2491,"   Re-arrangements of Iub transport bearers","RANimp-TTPS",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[7264,25005,"   Testing of ROHC performance","RANimp-RABSE5_Test",2,"Rel-5","R5","2005-09-09","2007-03-09",1,"-","-","Nokia","jarkko.hellsten@nokia.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[7265,21001,"   Beamforming requirements for UE","RANimp-BFR-UE",2,"Rel-5","R1","2001-09-21","2001-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","-","-",null,null,null,null,"2002-02-28","2002-02-28"]
[7268,2102,"   Deleted - Conformance Test Aspects - RAN Improvements","-",2,"Rel-5","T1","2002-01-01","2004-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[7272,1273,"Provisioning of IP-based multimedia services","IMS",1,"Rel-5","S1,S2,S3,S5,NP,T3,T1,R5","2000-01-03","2006-12-01",1,"SP-000216","-","Openwave","Mark Cataldo","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7275,1514,"      Stage 2 (Architecture and Main flows)","-",3,"Rel-5","S2","2000-04-14","2001-03-23",1,"SP-000289","-","Lucent","Liz Daniel","Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol",23.228000000000002,null,null,null,null,"2000-07-28","2001-02-08"]
[7277,2233,"      SIP Call Control protocol for the IMS","-",3,"Rel-5","N1","2000-10-02","2002-03-22",1,"NP-010643","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","TSGN_10 approved the change:CN1 - SA2 SIP joint meeting spotted one more place for improvement: work tasks with ID 1998 and 1278 are actually subtasks under of single CN1 WT. One WI has been approved for the CN1 WT with title \"SIP Call Control protocol","24.228, 24.229, 23.218",null,null,null,null,"2000-12-11","2002-01-24"]
[7281,25006,"      Conformance Test Aspects – IMS Call Control","IMS-CCR_Test",3,"Rel-5","R5","2005-03-11","2006-12-01",1,"-","-","Motorola","Jacob.John@motorola.com","-","34.108, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2002-02-28","2010-06-16"]
[7284,2523,"         IETF: RFC 3262 (Reliability of provisional responses)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-03-25","2003-03-14"]
[7285,2522,"         IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[7288,11000,"         IETF: RFC 3265 (specific event notification)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7290,11002,"         IETF: RFC editor Queue (DHCP options for SIP servers)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7294,11023,"         IETF: RFC 3324 (Network Asserted Identity)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7297,1291,"            Architectural issues","-",5,"Rel-5","S2","2000-10-09","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-02-08"]
[7299,2530,"         Service Examples (Work stopped)","IMS-Sex",4,"Rel-5","S1","2001-04-17","2002-06-14",1,"-","-","Motorola","Mark Cataldo","-",22.928000000000001,null,null,null,null,"2001-05-28","2003-07-25"]
[7303,11014,"      Deleted - SIP extensions for Integrity protection","-",3,"Rel-5","N1","2001-12-17","2002-06-28",1,"-","-","-","-","CN1 is not aware of any requirements and is not doing anything on this task","-",null,null,"SP-69",null,"2001-10-05","2002-06-21"]
[7306,35007,"   Charging and OAM&P for IMS","IMS-OAM",2,"Rel-5","S5","2000-12-25","2002-06-12",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2000-04-19","2002-06-21"]
[7307,2036,"   Multimedia codecs and protocols for conversational PS services","IMS-CODEC",2,"Rel-5","S4","2000-07-26","2002-09-27",1,"SP-000398","-","Toshiba, Nokia","B. Aronson (Toshiba), pasi.s.ojala@nokia.com","-","26.235, 26.236",null,null,null,null,"2000-09-27","2003-03-27"]
[7310,34006,"      recommendation for QoS parameter values for various media types","-",3,"Rel-5","S4","2001-12-31","2002-09-27",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-28","2003-01-13"]
[7314,32004,"      Stage 2 for SIP message compression","-",3,"Rel-5","S2","2001-09-24","2001-10-26",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2001-11-24"]
[7316,10001,"   Stage 3 description of IMS interfaces","-",2,"Rel-5","NP","2001-03-14","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-01-24"]
[7319,11016,"      Mw interface (CSCF to P-CSCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7322,13001,"      Go interface (GGSN to PCF)","-",3,"Rel-5","N3","2001-03-14","2002-06-07",1,"-","-","-","-","[DAB - 23/05/03] - 100 % complete","-",null,null,null,null,"2001-10-08","2003-07-25"]
[7325,14998,"      Si interface (HSS to IM-SSF)","-",3,"Rel-5","N4","2002-01-16","2002-08-30",1,"-","-","-","-","SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete)","-",null,null,null,null,"2002-03-25","2002-05-30"]
[7328,11028,"      Mj interface (BGCF to MGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[7329,11029,"      Mk interface (BGCF to BGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[7332,12001,"      Stage2 work 'general'","-",3,"Rel-5","N2","2001-04-16","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2001-10-08","2003-01-13"]
[7335,12004,"      Stage3 work 'Si interface'","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","[DAB 08-03-02] - UID 12004 is MASTER of UID 14998","-",null,null,null,null,"2002-01-24","2002-05-30"]
[7338,35005,"   IMS Charging","OAM-CH",2,"Rel-5","S2,S5","2001-08-06","2002-09-12",1,"SP-010631","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-",32.225000000000001,null,null,null,null,"2001-10-08","2003-01-13"]
[7341,34012,"      Billing, accounting and call detail record aspects","-",3,"Rel-5","S5","2001-09-27","2002-09-12",1,"SP-010631","-","T-Mobile","Karl-Heinz.Nenner@T-MOBILE.DE","-",32.225000000000001,null,null,null,null,"2001-10-09","2002-11-08"]
[7345,1844,"   Conformance Test Aspects - Provisioning of IMS","IMS-TEST",2,"Rel-5","T1","2002-03-18","2002-12-27",1,"-","-","-","-","The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008","-",null,null,null,null,"2000-09-14","2008-12-12"]
[7348,740068,"UE Conformance Test Aspects – IMS for Converged IP Communications ","IMS_CONV_IP_COM-UEConTest",1,"Rel-5","R5","2016-12-14","2017-12-15",1,"RP-171635",null,"Rohnert, Hans","Hans.Rohnert.ext@rohde-schwarz.com","UID: 740999->740068¦Rel-14->Rel-519/9/17: Compl:0%->75%¦ 8/1/18: Compl:75%->100%","34.229-1, 34.229-2, 34.229-3",74,38,null,null,"2017-02-01","2018-01-08"]
[7349,34001,"Extended Transparent End-to-End PS Streaming Service","PSS-E",1,"Rel-5","S4","2002-01-03","2003-03-17",1,"SP-010392","-","Ericsson","olle.franceschi@ericsson.com","-","26.233, 26.234",null,null,null,null,"2001-06-28","2002-02-28"]
[7351,31032,"      Interaction with other services","-",3,"Rel-5","S1","2002-11-18","2003-03-17",1,"-","-","Vodafone","stephen.wolak@vodafone.com","2nd resp SA4. Marked as closed 12/2008 (was marked 65% complete)",22.233000000000001,null,null,null,null,"2003-01-13","2008-12-12"]
[7354,501637,"Rel-5 Open Service Access (OSA) enhancements","OSA1",1,"Rel-5","S1,S3","1999-04-27","2002-12-20",1,"SP-000216","-","Siemens","joerg.swetina@neclab.eu","-","22.127, 23.127, 29.198-x, 29.998-x",null,null,null,null,"2000-08-08","2003-07-25"]
[7357,1430,"      Stage 1 for OSA APIs for Multimedia Call Control","-",3,"Rel-5","S1","2000-07-11","2002-03-14",1,"-","-","Siemens","Manfred.leitgeb@siemens.at","-",22.126999999999999,null,null,null,null,"2000-04-19","2002-05-30"]
[7360,15004,"   OSA Charging - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-12",null,null,null,null,"2002-02-28","2002-06-21"]
[7363,1419,"   OSA Security","OSA1-SEC",2,"Rel-5","S3","2000-07-11","2002-12-20",1,"SP-000302","-","Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[7367,1423,"      OSA changes required from supporting platforms, e.g. gsmSCF, HLR ","-",3,"Rel-5","S3","2000-09-11","2000-12-14",1,"SP-000302","-","BT, Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[7370,1425,"      Stage 1 for Interactions OSA - e-commerce","-",3,"Rel-5","S1","1999-04-27","2000-12-28",1,"-","-","Siemens","joerg.swetina@neclab.eu","Marked as closed 12/2008 (was marked 95% complete)",22.126999999999999,null,null,null,null,"2000-04-19","2008-12-12"]
[7373,15006,"   Presence and Availability Management (PAM) - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-14",null,null,null,null,"2002-02-28","2002-09-26"]
[7375,1787,"      Stage 1 for LCS - OSA interfaces","-",3,"Rel-5","S1","2000-09-11","2000-12-08",1,"-","-","Siemens","joerg.swetina@neclab.eu","-",22.126999999999999,null,null,null,null,"2000-04-19","2002-05-30"]
[7376,2124,"      Stage 2 for LCS - OSA interfaces","-",3,"Rel-5","S2","2000-12-11","2000-12-11",1,"-","-","Ericsson","Christophe GOURRAUD","az 24/05/01: Rel4 completion 90->100%.",23.126999999999999,null,null,null,null,"2000-11-22","2001-06-06"]
[7380,1434,"      Stage 1 for Retrieval of Terminal capabilities","-",3,"Rel-5","S1","2000-07-11","2001-01-10",1,"-","-","Siemens","joerg.swetina@neclab.eu","-",22.126999999999999,null,null,null,null,"2000-04-19","2003-07-25"]
[7383,1638,"CAMEL phase 4","CAMEL4",1,"Rel-5","S1","2000-04-17","2002-09-06",1,"NP-020486","-","Nokia","keijo.palviainen@nokia.com","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[7386,2013,"   Mid call procedure for MO and MT calls ","CAMEL4-MCP",2,"Rel-5","N2","2000-07-17","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-05-30"]
[7389,2016,"   CSE control over MT SMS","CAMEL4-CCSMS",2,"Rel-5","N2","2000-07-17","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7392,2514,"   Inclusion of ODB data in the CSE_HLR interface","CAMEL4-ODB",2,"Rel-5","N2","2001-07-09","2002-03-08",1,"-","-","-","-","Added on May 29, 2001","-",null,null,null,null,"2001-05-29","2002-02-28"]
[7395,2599,"   Transfer of IMEI (with SW version) to CSE (CAMEL4-ATI)","-",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-25","2002-05-30"]
[7396,12005,"   Handling of partial implementations of CAMEL4","CAMEL4-SUB",2,"Rel-5","N2","2002-03-08","2002-09-06",1,"-","-","-","-","stage2 and stage3 CRs for approval at CN#17","-",null,null,null,null,"2002-05-30","2002-09-26"]
[7399,1625,"Wideband Telephony Service - AMR","AMRWB",1,"Rel-5","S4","2000-01-01","2003-12-19",1,"SP-99354","-","Siemens","Imre.Varga@mch.siemens.de","-","-",null,null,null,null,"2000-08-08","2003-03-27"]
[7402,32007,"      Stage 2 for Wideband Telephony Service - AMR","-",3,"Rel-5","S4","2000-01-03","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-02-28"]
[7405,1626,"      Feasibility Study for Wideband Telephony Service - AMR","-",3,"Rel-5","S4","2000-04-28","2000-06-02",1,"SP-000024","-","-","-","S4,TD SP-000024: TR 26.901 v.4.0.0",26.901,null,null,null,null,"2000-08-08","2002-02-28"]
[7408,67,"      Codec issues","-",3,"Rel-5","S4","2000-01-03","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7410,74,"         Codec selection tests","-",4,"Rel-5","S4","2000-06-01","2000-10-20",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7414,34008,"         AMR-WB and narrrowband interworking","AMRWB-IWG",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[7417,34011,"         Deleted - WB Conferencing and WB Voice Group calls","-",4,"Rel-5","S1","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,"SP-07",null,"2001-10-09","2003-07-25"]
[7418,1855,"      Conformance tests (CRs to 34 series) ","-",3,"Rel-5","T1","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[7421,1629,"            Test specification for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-02-01","2000-04-12",1,"-","-","-","-","-",26.132000000000001,null,null,null,null,"2000-08-08","2001-03-20"]
[7424,50298,"      Channel coding in 45.003 for Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR","-",3,"Rel-5","GP","2000-01-03","2002-04-05",1,"-","-","-","-","50098 -> 50298","-",null,null,null,null,"2001-02-01","2008-05-06"]
[7427,2268,"      Receiver performance in TS 45.005","-",3,"Rel-5","GP","2001-04-02","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7430,2270,"      Deleted - MS test for AMR-WB","-",3,"Rel-5","GP","2000-01-03","2003-12-19",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[7434,1536,"Rel-5 Location Services enhancements","LCS1",1,"Rel-5","S2,S1,S3,S5,N4,R2,R3,GP","2000-04-03","2003-06-27",1,"SP-010518","-","Nokia","Jan Kall",". Acronym changed from \"LCS1, Rel-5\"","-",null,null,null,null,"2000-07-28","2015-03-24"]
[7436,2474,"      UE positioning enhancements for 1.28 Mcps TDD","LCS-128Pos",3,"Rel-5","R2","2001-04-09","2002-03-29",1,"RP-010215","-","CATT","Xiaohua Mei","-","25.123, 25.224, 25.225, 25.302, 25.303, 25.304, 25.305, 25.331, 25.420, 25.423, 25.430, 25.433, New 25.859",null,null,null,null,"2001-03-20","2002-02-28"]
[7437,2125,"      Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning","LCS-INTF",3,"Rel-5","R2","2001-01-15","2001-10-12",1,"RP-010414","-","Qualcomm","Kirk Burroughs","RP#13 completed","-",null,null,null,null,"2000-11-27","2002-01-24"]
[7440,1538,"      Stage 2 for Event based and Periodic LCS","-",3,"Rel-5","S2","2000-11-06","2001-01-26",1,"-","-","-","-","Marked as closed 12/2008 (was marked 51% complete)","-",null,null,null,null,"2000-07-28","2008-12-12"]
[7443,2437,"      GERAN LCS Stage 2 (first release)","-",3,"Rel-5","GP,S2,G1,G2","2000-04-03","2002-02-08",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[7447,2442,"   Location Services for GERAN in Iu Mode","-",2,"Rel-5","S2,G1,G2,R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7449,2444,"      Iu-ps interface support for LCS","-",3,"Rel-5","R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7452,2447,"      RRC protocol support for LCS","-",3,"Rel-5","G1,G2,R2,R3","2001-08-20","2001-11-30",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7456,55069,"      LCS MS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","-",null,null,null,null,"2002-05-23","2012-05-21"]
[7459,55071,"      Deleted - LCS BTS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2008-12-12"]
[7460,55072,"      Deleted - LCS BTS test cases","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2008-12-12"]
[7462,2434,"   LCS interoperability aspects to GERAN (LCS-GERAN)","-",2,"Rel-5","GP,S5","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[7465,35008,"   Charging and OAM&P for LCS enhancements","LCS1-OAM",2,"Rel-5","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32.200-series",null,null,null,null,"2000-04-19","2012-05-21"]
[7469,501571,"Rel-5 Security enhancements (SEC1)","-",1,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","Added BB UE authentication and rapporteur added. TO BE DELETED","-",null,null,null,null,"2000-04-09","2011-08-08"]
[7471,2576,"      Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP)","-",3,"Rel-5","S3","2000-06-15","2002-03-15",1,"SP-010326","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286)","New 33.210",null,null,null,null,"2001-06-09","2011-08-08"]
[7475,1580,"      Deleted - User plane protection in core network (e.g., provided by IPsec)","-",3,"Rel-5","S3","2000-02-21","2002-06-28",1,"-","-","-","-","TO BE DELETED. Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-04-18","2008-12-12"]
[7478,2243,"Intra Domain Connection of RAN Nodes to Multiple CN Nodes","IUFLEX",1,"Rel-5","S2,N1,N4,R3,GP","2000-10-02","2002-06-28",1,"SP-000619","-","Ericsson","stephen.terrill@ericsson.com","No clear indication on the end date. Put to Rel5 by AS.",23.236000000000001,null,null,null,null,"2000-12-13","2002-01-24"]
[7481,2248,"   N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","N1","2001-09-17","2002-06-28",1,"NP-010693","-","-","-","-","24.008 and check 29.018",null,null,null,null,"2000-12-13","2002-09-26"]
[7482,2249,"   N4 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","N4","2000-10-02","2002-03-08",1,"NP-000737","-","-","-","DAB 12.12.01 - % complete to 66%","-",null,null,null,null,"2000-12-13","2002-03-25"]
[7484,51068,"      Stage 2 (changes to )","-",3,"Rel-5","G1","2002-02-08","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7487,52077,"      48.016 Use of Gb interface concepts when a network applies IDNNS","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","Closed, accept changes for Gb over IP","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7491,2322,"      Deleted - Definition of a new A/Ater interface Transport Layer option based on the Iu Interface Transport Layer","-",3,"Rel-5","GP","2001-04-06","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[7494,35002,"   Rel-5 Principles, high level Requirements and Architecture","-",2,"Rel-5","S5","2001-09-17","2002-06-28",1,"SP-010461","-","Motorola","-","-","32.101, 32.102",null,null,null,null,"2000-04-26","2002-06-21"]
[7497,35001,"   Rel-5 Network Infrastructure Management ","-",2,"Rel-5","S5","2001-09-21","2002-09-12",1,"SP-010461","-","Ericsson","thomas.tovinger@ericsson.com","-","32.6xy, 32.3xy",null,null,null,null,"2001-10-08","2002-11-08"]
[7500,2395,"   RLC protocol enhancement (SDU Discard)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7503,2399,"   Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD)","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7504,2400,"   Stage 3 for GERAN enhancements for streaming services 2 (usage of ECSD)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7508,2413,"   Evolution of Iu ps","GERUEV1-IuPS",2,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7509,2414,"      Identification of GERAN requirements on Iu ps","-",3,"Rel-5","GP,R3","2000-09-01","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-05-21"]
[7513,2418,"      Identification of GERAN requirements on Iu cs","-",3,"Rel-5","GP,R3","2000-06-29","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7516,2557,"   E2E QoSConcept and Architecture","-",2,"Rel-5","S2","2001-01-03","2001-09-07",1,"-","-","-","-","-",23.207000000000001,null,null,null,null,"2001-06-08","2001-11-24"]
[7520,2571,"   Rel-5 Multimedia Messaging (MMS) enhancements","MESS5-MMS",2,"Rel-5","T2","2001-06-15","2003-03-31",1,"TP-010130","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2000-09-14","2003-03-27"]
[7521,31000,"      Definition of service requirements for MESS5-MMS","MESS5-SR",3,"Rel-5","S1","2001-06-15","2002-03-15",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",22.14,null,null,null,null,"2001-07-04","2003-07-25"]
[7525,2572,"   Enhanced Messaging Service (EMS) enhancements","MESS5-EMS",2,"Rel-5","T2","2001-06-15","2002-03-08",1,"TP-010153","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-",23.04,null,null,null,null,"2000-09-14","2003-03-27"]
[7526,31001,"      Definition of service requirements for Enhanced Messaging Service (EMS) enhancements","-",3,"Rel-5","S1","2001-06-15","2001-09-14",1,"-","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-","-",null,null,null,null,"2001-07-04","2002-02-28"]
[7529,14501,"   Modification of core network protocols for GERAN Inter BSC NACC over Gb Interface","GERNACC-Cnmod",2,"Rel-5","N4,S2","2001-09-03","2002-04-19",1,"GP-011877","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[7532,14503,"      Stage 3 (changes to TS 29.060)","-",3,"Rel-5","N4","2001-09-03","2002-03-08",1,"-","-","-","-","IP 30/11/01: Input awaited from GERAN2 to CN4","-",null,null,null,null,"2001-09-19","2002-07-31"]
[7535,50033,"Enhanced Power Control","EPC",1,"Rel-5","GP","2001-11-26","2003-12-19",1,"GP-012748","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[7538,50036,"   Deleted - GERAN BTS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012751","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[7542,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7545,51027,"      Changes to 45.003","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7546,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7547,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7548,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7549,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[7550,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[7551,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[7552,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[7553,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[7554,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[7555,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[7556,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[7557,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[7558,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[7559,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[7560,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[7561,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[7562,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[7563,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[7564,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[7565,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7566,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7567,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[7568,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7569,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[7570,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[7571,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[7572,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[7573,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[7574,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[7575,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[7576,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[7577,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[7578,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[7579,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[7580,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[7581,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[{"$f":"A7582+1","v":7582},2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7583,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[7584,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[7585,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7586,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7587,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7588,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7589,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7590,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7591,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7592,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7593,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7594,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[7595,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7596,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[7597,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7598,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7599,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7600,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7601,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[7602,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7603,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7604,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7605,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7606,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7607,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7608,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7609,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7610,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7611,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7612,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7613,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7614,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7615,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7616,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7617,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7618,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[7619,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[7620,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[7621,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[7622,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[7623,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[7624,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[7625,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7626,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[7627,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7628,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7629,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[7630,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[7631,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[7632,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[7633,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[7634,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[7635,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[7636,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[7637,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[7638,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[7639,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[7640,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[7641,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[7642,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[7643,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7644,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[7645,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[{"$f":"A7646+1","v":7646},1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[7647,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[7648,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[7649,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[7650,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[7651,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[7652,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[7653,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[7654,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[7655,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[7656,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[7657,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[7658,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[7659,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[7660,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[7661,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[7662,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[7663,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[7664,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[7665,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[7666,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[7667,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[7668,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[7669,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[7670,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[7671,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[7672,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[7673,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[7674,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[7675,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[7676,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7677,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7678,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7679,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7680,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[7681,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7682,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7683,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7684,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7685,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7686,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7687,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[7688,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[7689,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7690,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[7691,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[7692,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[7693,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[7694,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[7695,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[7696,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[7697,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7698,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7699,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[7700,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7701,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[7702,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7703,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7704,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[7705,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[7706,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[7707,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[7708,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[7709,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[{"$f":"A7710+1","v":7710},1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[7711,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[7712,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[7713,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[7714,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[7715,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[7716,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[7717,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[7718,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[7719,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[7720,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[7721,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[7722,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[7723,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[7724,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[7725,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[7726,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[7727,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[7728,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[7729,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[7730,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[7731,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[7732,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[7733,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[7734,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[7735,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[7736,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7737,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7738,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7739,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[7740,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7741,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[7742,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[7743,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[7744,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[7745,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[7746,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[7747,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[7748,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[7749,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[7750,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[7751,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[7752,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[7753,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[7754,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[7755,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[7756,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[7757,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[7758,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[7759,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[7760,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[7761,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[7762,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[7763,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[7764,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[7765,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[7766,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[7767,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[7768,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[7769,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[7770,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[7771,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[7772,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[7773,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[{"$f":"A7774+1","v":7774},2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[7775,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[7776,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[7777,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[7778,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[7779,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[7780,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[7781,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[7782,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7783,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[7784,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[7785,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[7786,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[7787,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[7788,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[7789,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[7790,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[7791,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[7792,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[7793,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7794,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[7795,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[7796,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[7797,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[7798,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[7799,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[7800,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[7801,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[7802,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[7803,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[7804,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[7805,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[7806,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[7807,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[7808,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[7809,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[7810,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[7811,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[7812,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[7813,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[7814,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[7815,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[7816,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[7817,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[7818,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[7819,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[7820,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[7821,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[7822,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[7823,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[7824,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[7825,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[7826,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[7827,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[7828,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[7829,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[7830,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[7831,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[7832,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[7833,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[7834,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[7835,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[7836,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[7837,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[{"$f":"A7838+1","v":7838},1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[7839,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[7840,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[7841,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[7842,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[7843,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[7844,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[7845,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[7846,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[7847,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[7848,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[7849,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[7850,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[7851,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[7852,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[7853,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[7854,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[7855,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[7856,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[7857,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[7858,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[7859,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[7860,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[7861,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[7862,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[7863,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[7864,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[7865,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[7866,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[7867,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[7868,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7869,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[7870,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[7871,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[7872,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[7873,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[7874,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[7875,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[7876,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[7877,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[7878,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[7879,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[7880,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[7881,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[7882,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[7883,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[7884,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[7885,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[7886,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[7887,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[7888,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[7889,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[7890,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[7891,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[7892,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[7893,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[7894,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7895,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7896,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7897,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[7898,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7899,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[7900,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[7901,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A7902+1","v":7902},60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7903,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[7904,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[7905,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[7906,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[7907,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[7908,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[7909,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[7910,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[7911,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[7912,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[7913,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[7914,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[7915,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[7916,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[7917,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[7918,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[7919,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[7920,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[7921,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[7922,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[7923,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[7924,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[7925,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[7926,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[7927,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[7928,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[7929,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[7930,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[7931,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[7932,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[7933,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[7934,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[7935,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[7936,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[7937,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[7938,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[7939,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[7940,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[7941,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[7942,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[7943,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[7944,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[7945,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[7946,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[7947,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[7948,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[7949,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[7950,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[7951,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[7952,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[7953,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[7954,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[7955,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[7956,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[7957,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[7958,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[7959,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[7960,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[7961,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[7962,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[7963,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[7964,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[7965,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[{"$f":"A7966+1","v":7966},60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[7967,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[7968,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[7969,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[7970,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[7971,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[7972,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[7973,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[7974,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[7975,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[7976,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[7977,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[7978,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[7979,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[7980,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[7981,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[7982,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[7983,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[7984,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[7985,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[7986,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[7987,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[7988,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[7989,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[7990,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[7991,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[7992,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[7993,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[7994,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[7995,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[7996,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[7997,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[7998,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[7999,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8000,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8001,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8002,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[8003,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[8004,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[8005,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8006,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[8007,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8008,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[8009,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8010,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[8011,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8012,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8013,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[8014,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[8015,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[8016,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[8017,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8018,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[8019,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[8020,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8021,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8022,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8023,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8024,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8025,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[8026,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8027,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[8028,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[8029,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[{"$f":"A8030+1","v":8030},60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[8031,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[8032,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[8033,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8034,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[8035,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[8036,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[8037,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[8038,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[8039,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[8040,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[8041,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[8042,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[8043,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[8044,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[8045,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]