{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp","index":0,"n_rows":8475,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version September 21st 2023",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[{"$f":"A2+1","v":2},0,"Pre TSG#101 version",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[{"$f":"A3+1","v":3},0,"Next key milestone: Rel-18 (St.3 & RAN): Mar 24. Rel-19: content def: Dec. 23",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[{"$f":"A4+1","v":4},0,null,null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[6,950003,"Study on Integrated Sensing and Communication ","FS_Sensing",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",22.837,95,48,null,null,"2022-03-10","2023-09-06"]
[7,1000026,"Integrated Sensing and Communication ","Sensing",1,"Rel-19","S1","2023-06-08","2023-12-12",0.8,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80",22.137,100,null,null,null,"2023-06-08","2023-09-06"]
[8,950004,"Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",1,"Rel-19","S1","2022-03-10","2023-12-12",0.95,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95",22.84,95,48,null,null,"2022-03-10","2023-09-06"]
[9,950005,"Study on Localized Mobile Metaverse Services ","FS_Metaverse",1,"Rel-19","S1","2022-03-10","2023-09-09",0.9,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20",22.856000000000002,95,48,null,null,"2022-03-10","2023-06-08"]
[10,1000028,"Mobile Metaverse Services ","Metaverse",1,"Rel-19","S1","2023-06-08","2023-12-12",0.8,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;","new 22.156, 22.261 ; 22.156",100,null,null,null,"2023-06-08","2023-09-21"]
[11,1010032,"Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",1,"Rel-19","S2","2023-09-20","2024-06-06",0,"SP-231198",null,"Devaki Chandramouli (Nokia). ","Devaki.chandramouli@nokia.com","9/23: company-submitted WID, to be corrected",null,101,null,null,null,"2023-09-20","NA"]
[12,950006,"Study on Network Sharing Aspects ","FS_NetShare",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100",22.850999999999999,95,48,null,null,"2022-03-10","2023-09-06"]
[13,1000029,"Indirect Network Sharing ","NetShare",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100",22.260999999999999,100,null,null,null,"2023-06-08","2023-09-06"]
[14,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","2022-03-10","2023-12-12",0.9,"SP-220437",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90",22.989000000000001,95,48,null,null,"2022-03-10","2023-09-06"]
[15,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","2023-06-08","2023-12-12",0.5,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50","22.280; 22.179; 22.289; 22.261 ",100,null,null,null,"2023-06-08","2023-09-06"]
[16,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23:...","22.875; 22.876",95,48,null,null,"2022-03-10","2023-09-06"]
[17,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","2023-06-08","2023-12-12",0.8,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80",22.260999999999999,100,null,null,null,"2023-06-08","2023-09-06"]
[18,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","2023-09-07","2024-09-09",0,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ",null,null,101,null,null,null,"2023-09-07","NA"]
[19,960016,"Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",1,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[20,1000024,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19","S1","2023-06-08","2023-12-12",0.95,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95",22.260999999999999,100,null,null,null,"2023-06-08","2023-09-06"]
[21,1010033,"Study on Integration of satellite components in the 5G architecture Phase III ","FS_5GSAT_ARCH_Ph3",1,"Rel-19","S2","2023-09-20","2024-06-06",0,"S2-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected",null,101,null,null,null,"2023-09-20","NA"]
[22,960017,"Study on UAV Phase 3 ","FS_UAV_Ph3",1,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[23,1000032,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19","S1","2023-06-08","2023-12-12",0.95,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95",null,100,null,null,null,"2023-06-08","2023-09-06"]
[24,1010008,"Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",1,"Rel-19","S6","2023-09-07","2024-12-12",0,"SP-230991",null,"Monrad, Atle, InterDigital ","<atle.monrad@interdigital.com> ",null,"23.255; 23.434 ",101,null,null,null,"2023-09-07","NA"]
[25,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","2022-06-02","2023-09-09",0.95,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95",22.841000000000001,96,49,null,null,"2022-06-02","2023-09-06"]
[26,960019,"Study on Energy Efficiency as service criteria ","FS_EnergyServ",1,"Rel-19","S1","2022-06-02","2023-09-09",0.95,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95",22.882000000000001,96,49,null,null,"2022-06-02","2023-09-06"]
[27,1000033,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19","S1","2023-06-08","2023-12-12",0.75,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75",22.260999999999999,100,null,null,null,"2023-06-08","2023-09-06"]
[28,1010029,"Study on Energy Efficiency and Energy Saving","FS_EnergySys",1,"Rel-19","S2","2023-09-09","2024-06-06",0,"SP-231192",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected","SP-231192",101,null,null,null,"2023-09-20","NA"]
[29,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","2022-06-02","2023-12-12",0.9,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90",22.916,96,49,null,null,"2022-06-02","2023-09-06"]
[30,960015,"Study on roaming value added services ","FS_RVAS",1,"Rel-19","S1","2022-06-02","2022-12-12",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100",22.876999999999999,96,49,null,null,"2022-06-02","2022-12-10"]
[31,990051,"Roaming Value-Added Services ","RVAS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[32,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","2019-09-19","2022-09-08",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"2019-09-13","2022-09-09"]
[33,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","2023-03-16","2023-12-12",0.6,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60",22.847999999999999,99,50,null,null,"2023-03-16","2023-09-06"]
[34,990052,"Supporting UE Mobility for XR Services ","XRMobility",1,"Rel-19","S1","2023-03-16","2023-06-06",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-09-06"]
[35,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100",22.103999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[36,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100",22.010999999999999,99,50,null,null,"2023-03-16","2023-08-09"]
[37,1010030,"Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",1,"Rel-19","S2","2023-09-20","2024-06-06",0,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected",null,101,null,null,null,"2023-09-20","NA"]
[38,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[39,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[40,970042,"MPS for Messaging services ","MPS4msg",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[41,1010031,"Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",1,"Rel-19","S2","2023-09-20","2024-06-06",0,"SP-231197",null,"Robert (Peraton Labs) ","rstreijl@peratonlabs.com","9/23: company-submitted WID, to be corrected",null,101,null,null,null,"2023-09-20","NA"]
[42,970041,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[43,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","2022-12-09","2022-12-20",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100",22.260999999999999,98,50,null,null,"2022-12-09","2022-12-10"]
[44,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,null,null,null,"2023-06-08","2023-06-08"]
[45,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,null,null,null,"2023-09-06","2023-09-06"]
[46,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,null,null,null,"2023-09-06","2023-09-06"]
[47,1000027,"NPN security considerations ","SecNPN",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,22.260999999999999,100,null,null,null,"2023-06-08","NA"]
[48,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","2022-12-13","2024-09-12",0.35,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35",26.933,98,50,null,null,"2022-12-09","2023-09-07"]
[49,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","2023-06-08","2024-09-09",0.1,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10","23.222 ; 23.700-92",100,null,null,null,"2023-06-08","2023-09-07"]
[50,1000035,"Study on enhanced application layer support for location services ","FS_eLSAPP",1,"Rel-19","S6","2023-06-08","2024-06-06",0.15,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15","23.434 ; 23.700-72",100,null,null,null,"2023-06-08","2023-09-07"]
[51,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.05,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5","23.280; 23.379; 23.281; 23.282 ",100,null,null,null,"2023-06-08","2023-09-07"]
[52,1000037,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19","S6","2023-06-08","2024-09-09",0,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0",null,100,null,null,null,"2023-06-08","2023-09-07"]
[53,1000038,"Railways specific Enhancements to Mission Critical Services ","enh4FRMCS",1,"Rel-19","S6","2023-06-08","2024-12-12",0.1,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,null,null,null,"2023-06-08","2023-09-07"]
[54,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.05,"SP-230988",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,null,null,null,"2023-06-08","2023-09-07"]
[55,1010006,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19","S6","2023-09-07","2024-12-12",0,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ",null,null,101,null,null,null,"2023-09-07","NA"]
[56,1010007,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19","S6","2023-09-07","2024-12-12",0,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ",null,23.558,101,null,null,null,"2023-09-07","NA"]
[57,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-19","S6","2023-09-07","2024-09-09",0,"SP-231161",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ",null,null,101,null,null,null,"2023-09-07","NA"]
[58,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","2023-09-06","2024-09-09",0,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ",null,33.926000000000002,101,null,null,null,"2023-09-06","NA"]
[59,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","2023-09-06","2024-09-09",0,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in",null,null,101,null,null,null,"2023-09-06","NA"]
[60,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","2023-09-06","2024-03-03",0,"SP-231159",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ",null,null,101,null,null,null,"2023-09-06","NA"]
[61,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","2023-03-23","2024-09-09",0,"SP-230242",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater","33.107; 33.108; 33.126; 33.127; 33.128 ",97,49,null,null,"2022-09-11","2023-03-16"]
[62,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"2022-09-09","2022-12-12",0,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[63,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[64,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[65,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"2021-06-11","2023-12-12",0.92,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[66,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","2021-06-11","2021-06-18",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[67,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"2021-12-19","2022-12-10"]
[68,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[69,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","2022-12-16","2023-12-12",0.8,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,"x","2022-09-11","2023-06-06"]
[70,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","2022-12-16","2023-12-12",0.9,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,"x","2022-09-11","NA"]
[71,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[72,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"2021-12-19","2022-12-10"]
[73,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"2022-12-09","2024-03-03",0.28000000000000003,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","NA"]
[74,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","2023-06-08"]
[75,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.35,"CP-232167",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,"x","2022-12-09","2023-06-06"]
[76,990056,"   CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",0,"CP-232167",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com",null,"24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,"x","2022-12-09","NA"]
[77,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","2023-09-07","2024-03-03",0,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ",null,"32.255; 32.256; 32.291; 32.298 ",101,null,null,null,"2023-09-07","NA"]
[78,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.33,"RP-230809",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809",null,94,48,null,null,"2022-01-06","2023-03-29"]
[79,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.75,"RP-231484","RP-231563","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"2022-01-06","2023-09-06"]
[80,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0,"RP-231484","RP-231563","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[81,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.38,"RP-223519",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519",null,94,48,null,null,"2022-01-06","2023-01-09"]
[82,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.82,"RP-231407","RP-232310","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[83,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","2022-03-07","2024-06-06",0,"RP-231407","RP-232310","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"2022-06-04","2023-09-06"]
[84,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"2022-12-13","2023-12-12",0.88,"RP-230706",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;",38.741,98,50,null,null,"2023-01-09","2023-06-08"]
[85,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.8,"RP-231179","RP-231967","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[86,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.95,"RP-231179","RP-231967","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[87,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"2022-09-11","2023-09-07"]
[88,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","2022-06-02","2023-06-06",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-06-08"]
[89,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","2022-06-01","2022-06-15",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[90,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","2019-03-07","2019-09-12",0.8,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80",22.844000000000001,98,50,null,null,"2022-12-09","2023-09-07"]
[91,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-231499",null,"Thales ",null,null,null,100,null,null,null,"2023-06-29","NA"]
[92,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-231499","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,null,null,null,"2023-06-29","2023-09-21"]
[93,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","2023-03-03","2024-06-06",0.11,"RP-231487",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487",null,99,50,null,null,"2023-03-29","2023-09-07"]
[94,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0.3,"RP-231487","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"2023-03-29","2023-09-21"]
[95,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","2023-03-03","2024-06-06",0,"RP-231487","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ",null,99,50,null,null,"2023-03-29","2023-09-21"]
[96,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","2023-03-03","2024-06-06",0.23,"RP-230792",null,"MediaTek ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[97,991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0.6,"RP-231479","RP-232313","Aijun CAO, MediaTek Inc.","aijun.cao@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[98,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","2023-03-03","2024-06-06",0,"RP-231479","RP-232313","Aijun CAO, MediaTek Inc.","aijun.cao@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[99,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"2022-03-15","2023-12-12",0.82,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437",null,95,48,null,null,"2022-04-05","2023-01-09"]
[100,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"2022-04-05","2023-01-09"]
[101,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...",36.180999999999997,95,48,null,null,"2022-04-05","2023-06-07"]
[102,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","2022-12-13","2023-12-12",0.46,"RP-223064","RP-232244","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"2023-01-09","2023-09-21"]
[103,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[104,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"2020-06-25","2024-03-03",0.82,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[105,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"2020-06-25","2021-09-13"]
[106,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[107,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[108,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"2021-12-19","2023-03-15"]
[109,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[110,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","2023-03-13","2024-03-03",0.8,"CP-230197",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-06"]
[111,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","2023-03-13","2024-03-03",0.65,"CP-230197",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-09"]
[112,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","2023-03-13","2024-03-03",0.3,"CP-230197",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","NA"]
[113,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"2021-12-13","2024-03-03",0.68,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"2022-12-09","NA"]
[114,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"2021-12-13","2023-03-31"]
[115,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100",23.542000000000002,98,50,null,null,"2022-12-09","2023-06-08"]
[116,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","2023-03-13","2024-03-03",0.6,"CP-230332",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%",27.007000000000001,99,50,null,null,"2022-12-09","2023-06-06"]
[117,990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","2023-03-13","2024-03-15",0.3,"CP-230332",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"2022-12-09","2023-06-09"]
[118,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.881999999999998,96,49,null,null,"2022-06-02","2023-06-08"]
[119,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","2021-06-11","2022-06-09",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"2021-06-11","2023-06-08"]
[120,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[121,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[122,940080,"Study on network energy savings for NR","FS_Netw_Energy_NR",1,"Rel-18","R1","2021-12-13","2022-12-01",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...",38.863999999999997,94,48,null,null,"2022-01-06","2023-03-29"]
[123,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","2021-12-13","2023-12-12",0.85,"RP-222644","RP-231812","Xiaodong Shen, vivo Communication Technology","shenxiaodong@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...",38.869,94,48,null,null,"2022-01-06","2023-09-06"]
[124,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"2021-12-12","2024-06-06",0.45,"RP-223544",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544",null,97,49,null,null,"2022-09-23","2023-01-09"]
[125,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",0.75,"RP-223544","RP-231628","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"2022-09-23","2023-09-06"]
[126,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",0,"RP-223544","RP-231628","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[127,940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","2021-12-12","2022-09-09",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...;...",38.865000000000002,94,48,null,null,"2022-01-06","2022-09-23"]
[128,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"2021-12-19","2022-12-10"]
[129,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"2022-12-15","2023-12-13",0.98,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[130,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2023-06-08"]
[131,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","2022-12-15","2023-12-12",0.95,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[132,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","NA"]
[133,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redca",1,"Rel-18","R4","2023-03-06","2023-12-12",0.5,"RP-230743",null,"Ericsson",null,null,null,99,50,null,null,"2023-04-07","NA"]
[134,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",0.5,"RP-231049","RP-231881","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[135,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"2022-12-13","2024-06-06",0.3,"RP-223540",null,"Huawei ",null,null,null,98,50,null,null,"2023-01-09","NA"]
[136,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","2022-12-13","2023-12-12",0.75,"RP-230566","RP-231926","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[137,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",0,"RP-230566","RP-231926","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[138,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[139,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.75,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ",23.256,99,50,null,null,"2022-12-09","NA"]
[140,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"2021-12-19","2023-03-15"]
[141,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100",23.256,98,50,null,null,"2022-12-09","2023-06-08"]
[142,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100",33.890999999999998,96,49,null,null,"2022-06-02","2023-03-17"]
[143,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100",33.256,99,50,null,null,"2023-03-16","2023-09-07"]
[144,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.8,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"2022-12-09","2023-06-06"]
[145,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",0.6,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-09"]
[146,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[147,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",0,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","NA"]
[148,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","2021-09-13","2022-12-12",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"2021-09-13","2022-12-11"]
[149,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",0.67,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,97,49,null,null,"2022-09-11","NA"]
[150,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100",23.254999999999999,97,49,null,null,"2022-12-11","2023-06-08"]
[151,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",0.7,"CP-230189",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,"x","2022-09-11","2023-06-06"]
[152,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.4,"CP-230189",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,"x","2022-09-11","2023-06-09"]
[153,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","2021-12-13","2023-12-12",0.8,"RP-230782",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782",null,94,48,null,null,"2022-01-06","2023-03-29"]
[154,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.8,"RP-230782","RP-231864","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[155,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","2023-03-03","2023-12-12",0.8,"RP-230783",null,"Nokia ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[156,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","2023-03-03","2023-12-12",0.8,"RP-230783","RP-231865","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[157,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[158,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"2020-06-25","2024-03-03",0.75,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[159,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"2020-06-25","2021-06-11"]
[160,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[161,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"2021-12-19","2023-03-15"]
[162,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"2022-12-09","2023-06-08"]
[163,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100",33.893000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[164,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100",33.533000000000001,99,50,null,null,"2023-03-16","2023-09-07"]
[165,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","2023-03-13","2024-03-03",0.5,"CP-230331",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"2022-12-09","2023-06-06"]
[166,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","2023-03-13","2024-03-03",0.6,"CP-230331",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com",null,"24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"2022-12-09","NA"]
[167,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","2023-03-13","2024-03-03",0.5,"CP-230331",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[168,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","2023-06-08","2023-12-12",0.15,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15",28.844999999999999,100,null,null,null,"2023-06-08","2023-09-07"]
[169,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"2022-09-30","2024-03-03",0.73,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[170,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"2021-12-19","2022-12-10"]
[171,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","2022-09-30","2023-06-06",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100",23.273,97,49,null,null,"2022-09-11","2023-06-08"]
[172,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",0.3,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%",23.273,97,49,null,"x","2022-09-11","2023-06-06"]
[173,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",0.7,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30",23.273,97,49,null,"x","2022-09-11","2023-06-09"]
[174,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","2022-12-16","2024-03-03",0.8,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65",23.273,97,49,null,"x","2022-09-11","2023-06-09"]
[175,940081,"Study on expanded and improved NR positioning","FS_NR_pos_enh2",1,"Rel-18","R1","2022-12-13","2024-06-06",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...",38.859000000000002,94,48,null,null,"2022-01-06","2023-01-09"]
[176,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"2022-12-13","2024-06-06",0.28000000000000003,"RP-230328",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328",null,98,50,null,null,"2023-01-09","2023-03-29"]
[177,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","2022-12-13","2023-12-12",0.7,"RP-231460","RP-232041","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...",38.354999999999997,98,50,null,null,"2023-01-09","2023-09-06"]
[178,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",0,"RP-231460","RP-232041","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[179,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.38,"RP-230077",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077",null,94,48,null,null,"2022-01-06","2023-03-29"]
[180,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",0.85,"RP-230077","RP-231583","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...",38.786000000000001,94,48,null,null,"2022-01-06","2023-09-06"]
[181,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0,"RP-230077","RP-231583","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[182,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.28999999999999998,"RP-223501",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501",null,94,48,null,null,"2022-01-06","2023-01-09"]
[183,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.8,"RP-223501","RP-231725","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[184,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0,"RP-223501","RP-231725","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[185,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.15,"RP-221447","RP-231837","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[186,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"2021-12-13","2023-12-12",0.99,"RP-222993",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993",null,94,48,null,null,"2022-01-06","2023-01-09"]
[187,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.99,"RP-222993","RP-232648","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[188,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-10",0.95,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20","23.700-33",95,48,null,null,"2021-12-19","2022-03-12"]
[189,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"2021-12-19","2022-12-10"]
[190,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","2022-03-10","2023-03-10",0.9,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"2022-03-10","2023-06-08"]
[191,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"2022-09-27","2023-12-12",0.85,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","NA"]
[192,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","2022-09-27","2023-06-06",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","2023-06-08"]
[193,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",0.85,"CP-223110",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[194,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.8,"CP-223110",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[195,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",0.75,"CP-223110",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-06"]
[196,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","2022-12-16","2023-12-12",0.85,"CP-223110",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","NA"]
[197,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.9,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90",33.503,99,50,null,null,"2023-03-16","2023-06-08"]
[198,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"2021-06-11","2024-03-03",0.96,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,23.434000000000001,99,50,null,null,"2022-12-09","NA"]
[199,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","2021-06-11","2022-09-12",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"2021-06-11","2022-12-11"]
[200,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100",23.434000000000001,98,50,null,null,"2022-12-09","2023-06-08"]
[201,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-06"]
[202,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","2023-03-13","2024-03-03",0.85,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-09"]
[203,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[204,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[205,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[206,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"2021-12-20","2024-03-03",0.81,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-01-09"]
[207,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"2021-12-19","2023-03-15"]
[208,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","2022-09-23","2023-03-03",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-06-08"]
[209,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","2023-03-13","2024-03-03",0.7,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,"x","2022-09-23","2023-06-06"]
[210,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","2023-03-13","2024-03-03",0.6,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,"x","2022-09-23","2023-06-06"]
[211,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","2023-03-13","2024-03-03",0.85,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,"x","2022-09-23","2023-06-06"]
[212,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","2021-09-10","2023-03-03",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"2021-09-10","2023-06-30"]
[213,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"2021-12-10","2023-09-09",0.74,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,23.434000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[214,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","2021-12-12","2023-06-06",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...",23.434000000000001,94,48,null,null,"2022-12-11","2023-06-08"]
[215,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","2021-12-12","2022-12-12",0.45,"CP-232170",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,"x","2021-12-10","2023-06-06"]
[216,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","2021-12-10","2022-12-09",0.6,"CP-232170",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,"x","2021-12-10","2023-06-09"]
[217,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","2023-03-16","2023-09-09",0.8,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80",33.433999999999997,99,50,null,null,"2023-03-16","2023-06-08"]
[218,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"2021-09-13","2024-03-03",0.59,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"2022-09-11","2022-09-23"]
[219,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"2021-09-13","2022-12-11"]
[220,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"2022-12-11","2023-06-08"]
[221,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","2022-12-16","2024-03-03",0.2,"CP-231284",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[222,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","2022-12-16","2024-03-03",0.5,"CP-231284",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"2022-09-11","2023-06-09"]
[223,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","2023-06-08","2023-09-09",0,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ",null,33.433999999999997,100,null,null,null,"2023-06-08","NA"]
[224,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"2021-03-18","2021-06-11"]
[225,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","2020-09-01","2020-09-17",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"2020-09-11","NA"]
[226,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"2022-06-02","2023-09-09",0.67,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"2022-06-02","2022-12-11"]
[227,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"2023-03-16","2023-06-08"]
[228,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.884,96,49,null,null,"2022-06-02","2023-06-08"]
[229,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","2023-03-16","2023-09-09",0.5,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50",33.122,99,50,null,null,"2023-03-16","2023-06-08"]
[230,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","2023-03-16","2023-09-09",0,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,29.222000000000001,99,50,null,null,"2023-03-16","2023-06-08"]
[231,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"2020-06-25","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"2021-06-11","NA"]
[232,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[233,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"2021-06-11","2021-12-10"]
[234,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100",28.902000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[235,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"2021-06-11","2022-12-11"]
[236,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"2022-06-03","2024-03-03",0.72,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"2022-06-03","2023-06-30"]
[237,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","2022-06-06","2024-03-03",0.75,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->",24.558,96,49,null,null,"2022-06-03","2023-06-09"]
[238,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","2022-06-03","2024-03-03",0.7,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"2022-06-03","2023-06-06"]
[239,980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","2022-12-09","2023-12-12",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100",28.843,98,50,null,null,"2022-12-09","2023-09-07"]
[240,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",0,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ",null,"32.240; 32.290 ",101,null,null,null,"2023-09-06","NA"]
[241,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[242,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","2022-06-02","2022-06-10",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100",22.100999999999999,96,49,null,null,"2022-06-02","2022-09-12"]
[243,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100",33.18,94,48,null,null,"2021-12-10","2023-06-08"]
[244,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"2021-12-10","2024-03-03",0.66,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-03-17"]
[245,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","2021-12-10","2023-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-06-08"]
[246,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","2023-06-07","2024-03-03",0.1,"CP-231355",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,null,null,null,"2023-06-07","2023-06-30"]
[247,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"2020-06-25","2024-03-03",0.72,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","NA"]
[248,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","2020-06-25","2021-09-20",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"2020-06-26","2021-09-13"]
[249,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","2021-09-10","2022-06-10",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","2022-09-12"]
[250,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","2023-03-13","2024-03-03",0.15,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,"x","2021-09-10","2022-09-12"]
[251,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"2019-03-07","2023-12-12",0.94,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[252,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","2019-03-07","2022-03-11",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100",23.289000000000001,93,47,null,null,"2021-09-10","2022-12-11"]
[253,970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","2022-09-13","2023-12-12",0.8,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"2022-09-05","2023-06-06"]
[254,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"2019-03-07","2023-12-12",0.74,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[255,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","2019-03-07","2022-09-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22",23.289000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[256,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","2022-09-13","2023-12-12",0,"CP-222176",null,"Haitao Wei, Huawei","weihaitao@huawei.com",null,"24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"2022-09-05","NA"]
[257,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%",33.503,97,49,101,null,"2022-09-11","2023-06-08"]
[258,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[259,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[260,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","2022-12-09","2024-03-04",0.5,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[261,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[262,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","2023-09-09","2024-03-04",0,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"2022-12-09","2023-06-08"]
[263,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","2019-09-19","2021-12-10",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"2019-09-13","2021-09-13"]
[264,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","2021-12-13","2023-03-03",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"2021-12-13","2023-06-08"]
[265,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"2021-12-13","2023-03-17"]
[266,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","2018-06-06","2022-06-10",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"2018-06-06","2022-06-04"]
[267,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[268,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"2019-12-06","2021-12-10",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"2021-06-11","2022-07-13"]
[269,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","2019-12-06","2021-06-11",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"2019-12-06","2022-06-21"]
[270,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"2021-06-11","2022-06-21"]
[271,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","2021-12-13","2023-12-12",0.8,"RP-221348","RP-232659","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...",38.843000000000004,94,48,null,null,"2022-01-06","2023-09-21"]
[272,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"2021-12-20","2024-03-03",0.87,"SP-221329",null,"Tricci So, OPPO ","tricci.so@oppo.com ","10/12/22: 0%->5","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2022-12-10"]
[273,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","2022-06-21","2023-03-03",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100",33.898000000000003,96,49,null,null,"2022-06-21","2023-09-07"]
[274,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220071",null,"Tricci So, OPPO ","tricci.so@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"2021-12-19","2022-12-10"]
[275,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230095",null,"Tricci So, OPPO ","tricci.so@oppo.com ","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2023-06-08"]
[276,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","2023-03-13","2024-03-03",0.7,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"2022-12-09","2023-06-06"]
[277,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","2023-03-13","2024-03-03",0.75,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"2022-12-09","2023-06-06"]
[278,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"2021-12-13","2023-12-12",0.8,"RP-220635",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635",null,94,48,null,null,"2022-01-06","2022-04-05"]
[279,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.8,"RP-220635","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[280,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100",33.877000000000002,96,49,null,null,"2022-06-02","2023-09-07"]
[281,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100",28.908000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[282,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","2023-03-17","2023-12-12",0.35,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"2023-03-17","2023-09-07"]
[283,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-18","S4","2022-03-12","2024-03-03",0.4,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;","26.927; 26.847",95,48,null,null,"2022-03-10","2023-09-21"]
[284,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[285,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",0.75,"RP-221458",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458",null,94,48,null,null,"2022-01-06","2022-07-12"]
[286,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.75,"RP-221458","RP-231830","Erlin Zeng, CATT","erlin.zeng@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[287,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.82,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","NA"]
[288,940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"2021-12-19","2022-12-10"]
[289,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","2023-06-08"]
[290,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.85,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024",null,99,50,null,"x","2022-12-09","2023-06-30"]
[291,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",0.7,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","; 9/6/23: 15%->40",null,99,50,null,"x","2022-12-09","2023-06-09"]
[292,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",0.7,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,"x","2022-12-09","2023-06-06"]
[293,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","2023-06-08","2023-09-09",0,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ",null,33.500999999999998,100,null,null,null,"2023-06-08","NA"]
[294,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100",33.883000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[295,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"2021-06-15","2023-09-08",1,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"2021-07-02","2023-01-09"]
[296,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","2021-06-15","2023-09-08",1,"RP-231216","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",36.792000000000002,92,47,null,null,"2021-07-02","2023-09-21"]
[297,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[298,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024",31.102,92,47,null,null,"2021-07-02","2023-06-06"]
[299,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","2023-03-13","2023-03-24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[300,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[301,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[302,0,"Rel-18 Slice","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[303,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","2021-03-12","2022-09-22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[304,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[305,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"2020-06-25","2024-03-03",0.39,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[306,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","2020-06-25","2021-03-17",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"2020-06-25","2021-06-11"]
[307,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[308,1000023,"   CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","2023-06-07","2024-03-03",0.2,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,null,null,"x","2023-06-07","NA"]
[309,1000044,"   CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","2023-06-07","2024-03-03",0,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ",null,"23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,null,null,"x","2023-06-07","NA"]
[310,1000045,"   CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","2023-06-07","2024-03-03",0,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ",null,"23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,null,null,"x","2023-06-07","NA"]
[311,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.84,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","NA"]
[312,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"2021-12-19","2022-12-10"]
[313,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","2022-06-02","2023-03-03",0.9,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90",33.886000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[314,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[315,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",0.8,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[316,990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.7,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-09"]
[317,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.75,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[318,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",0.7,"RP-230787",null,"ZTE ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[319,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",0.7,"RP-231396","RP-231889","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[320,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","2021-12-10","2023-12-12",0.7,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[321,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","2022-03-10","2023-12-12",0.85,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23",28.835999999999999,95,48,null,null,"2022-03-10","2023-09-07"]
[322,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","2023-03-16","2023-12-12",0.75,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75",28.312000000000001,99,50,null,null,"2023-03-16","2023-09-07"]
[323,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","2021-03-18","2021-12-10",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"2021-03-18","2022-06-04"]
[324,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","2022-06-15","2023-12-12",0.65,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65",26.940999999999999,96,49,null,null,"2022-06-03","2023-09-07"]
[325,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","2021-12-10","2022-03-11",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"2021-12-10","2022-06-04"]
[326,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","2021-03-18","2022-09-12",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"2021-03-18","2022-12-11"]
[327,960013,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[328,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","2022-06-03","2023-09-09",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"2022-06-03","2022-07-13"]
[329,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","2022-12-12","2023-12-12",0.5,"SP-230176",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"2022-12-09","2023-09-07"]
[330,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","2023-06-30","2024-03-03",0.9,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;",31.105,100,null,null,null,"2023-06-30","2023-09-21"]
[331,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[332,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",0.86,"RP-230786",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786",null,98,50,null,null,"2023-01-09","2023-03-29"]
[333,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","2022-12-13","2023-12-12",0.68,"RP-223502","RP-231606","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[334,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","2021-12-13","2023-03-03",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...",38.835000000000001,94,48,null,null,"2022-01-06","2023-03-17"]
[335,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"2021-12-20","2024-03-03",0.89,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"2022-12-09","NA"]
[336,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"2021-12-19","2022-12-10"]
[337,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-09-07"]
[338,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","2023-03-13","2024-03-03",0.75,"CP-232134",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,"x","2022-12-09","2023-06-06"]
[339,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","2023-03-13","2024-03-03",0.85,"CP-232134",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,"x","2022-12-09","2023-06-06"]
[340,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","2022-03-10","2024-03-03",0.55000000000000004,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...",26.93,95,48,null,null,"2022-03-10","2023-09-07"]
[341,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","2022-03-15","2024-03-03",0.55000000000000004,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24",26.113,95,48,null,null,"2022-03-10","2023-09-07"]
[342,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","2022-03-10","2023-06-06",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"2022-03-10","2023-06-08"]
[343,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","2022-03-10","2024-03-03",0.65,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"2022-03-10","2023-09-07"]
[344,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","2022-06-03","2024-03-03",0.3,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20",26.263999999999999,96,49,null,null,"2022-06-03","2023-06-08"]
[345,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","2022-06-03","2023-06-06",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"2022-06-03","2023-06-08"]
[346,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","2022-06-03","2024-03-03",0.5,"SP-220685",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50",26.565000000000001,96,49,null,null,"2022-06-03","2023-09-07"]
[347,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","2022-06-03","2024-03-03",0.45,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...",26.521999999999998,96,49,null,null,"2022-06-03","2023-09-07"]
[348,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","2023-03-16","2024-03-03",0.15,"SP-230167",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15","26.119 ; 26.566; 26.866; 26.865",99,50,null,null,"2023-03-16","2023-09-07"]
[349,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","2022-06-03","2024-03-03",0.5,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24",26.812000000000001,96,49,null,null,"2022-06-03","2023-09-07"]
[350,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","2022-06-03","2022-12-08",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"2022-06-03","2022-12-11"]
[351,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[352,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","2020-06-25","2021-12-10",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"2020-06-25","2021-12-10"]
[353,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","2020-06-25","2021-09-16",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"2020-06-26","2022-03-12"]
[354,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"2022-03-03","2023-12-12",0.35,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-03-10","2022-09-12"]
[355,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","2022-03-03","2022-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-12-11","2023-06-08"]
[356,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","2022-12-16","2023-12-12",0.2,"CP-223105",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2023-06-06"]
[357,980071,"   CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","2022-12-16","2023-12-12",0,"CP-223105",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,"24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2022-09-12"]
[358,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"2020-12-04","2022-06-21"]
[359,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"2021-09-13","2022-12-11"]
[360,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"2022-09-09","2024-03-03",0.46,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"2022-09-11","NA"]
[361,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"2022-12-11","2023-06-08"]
[362,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",0.6,"CP-231285",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[363,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",0,"CP-231285",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","NA"]
[364,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"2022-09-12","2024-03-03",0.43,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[365,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[366,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","2023-06-07","2024-03-03",0.5,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,null,null,null,"2023-06-07","NA"]
[367,1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","2023-06-07","2024-03-03",0,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,null,null,null,"2023-06-07","NA"]
[368,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"2022-03-15","2024-03-03",0.62,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"2022-04-05","2022-09-23"]
[369,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","2022-03-15","2023-09-22",1,"RP-222272","RP-231730","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[370,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","2022-03-16","2024-03-03",0.5,"RP-222272","RP-231730","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[371,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.4,"RP-221402","RP-231729","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[372,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[373,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"2019-09-19","2024-03-03",0.79,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"2021-06-11","NA"]
[374,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","2019-09-19","2021-09-08",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"2019-09-13","2021-09-13"]
[375,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"2021-06-11","2021-09-13"]
[376,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"2021-12-19","2023-03-16"]
[377,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[378,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","2023-03-13","2024-03-03",0.3,"CP-232169",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,"x","2022-09-11","2023-06-06"]
[379,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","2023-03-13","2024-03-03",0.9,"CP-232169",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,"x","2022-09-11","NA"]
[380,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","2023-03-13","2024-03-03",0.45,"CP-232169",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175",97,49,null,"x","2022-09-11","2023-06-06"]
[381,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","2022-06-02","2023-06-06",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100",33.89,96,49,null,null,"2022-06-02","2023-06-08"]
[382,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",0,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ",null,33.328000000000003,99,50,null,null,"2023-03-16","NA"]
[383,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","2023-06-08","2024-03-03",0,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ",null,"32.260; 32.255; 32.291; 32.298 ",100,null,null,null,"2023-06-08","NA"]
[384,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.77,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[385,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"2021-12-19","2022-12-10"]
[386,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[387,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",0.6,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[388,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.7,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-09"]
[389,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.6,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[390,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"2021-12-19","2023-03-15"]
[391,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"2022-09-12","2024-03-03",0.95,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2022-12-10"]
[392,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[393,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-232027",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,"x","2022-09-11","2023-06-06"]
[394,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","2023-04-18","2024-03-03",0.95,"CP-232027",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,"x","2022-09-11","2023-06-09"]
[395,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","2019-03-07","2024-03-03",0.5,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/24","26.260; new",83,42,null,null,"2019-03-14","2023-09-07"]
[396,770024,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18","S4","2017-09-08","2024-03-03",0.75,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2023-09-07"]
[397,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"2020-12-04","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[398,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","2020-12-04","2021-06-11",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"2020-12-04","2021-12-10"]
[399,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[400,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[401,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",0.57999999999999996,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"2022-09-11","2022-09-12"]
[402,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-03-03",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"2022-12-11","2023-06-08"]
[403,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","2022-12-15","2023-12-12",0.4,"CP-231197",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[404,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","2022-12-15","2023-12-12",0.55000000000000004,"CP-231197",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[405,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","2022-06-02","2023-12-12",0.65,"SP-231156",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156",23.957999999999998,96,49,null,null,"2022-06-02","2023-09-13"]
[406,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"2021-06-11","2022-12-11"]
[407,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"2021-12-20","2023-12-12",0.87,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2022-12-11","NA"]
[408,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2021-12-19","2022-03-12"]
[409,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"2021-12-19","2022-12-10"]
[410,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","2022-03-10","2022-12-12",0.9,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90",33.738999999999997,95,48,null,null,"2022-03-10","2023-06-08"]
[411,970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","2022-09-23","2023-06-06",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[412,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.7,"CP-220325",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[413,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",0.6,"CP-220325",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-06"]
[414,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.95,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95","33.558; 33.501 ",99,50,null,null,"2023-03-16","2023-09-07"]
[415,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[416,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"2020-09-16","2021-09-08",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"2021-06-11","NA"]
[417,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","2020-09-16","2021-06-11",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"2020-09-10","2021-09-13"]
[418,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[419,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"2021-12-13","2024-03-03",0.81,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2022-12-10"]
[420,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"2021-12-19","2023-03-15"]
[421,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2023-06-08"]
[422,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",0.99,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99",33.857999999999997,96,49,null,null,"2022-06-02","2023-06-08"]
[423,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.9,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90",33.500999999999998,99,50,null,null,"2023-03-16","2023-09-07"]
[424,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",0.75,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-30"]
[425,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","2022-12-15","2024-03-03",0.6,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-09"]
[426,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",0.75,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-06"]
[427,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100",28.827999999999999,94,48,null,null,"2021-12-13","2023-03-17"]
[428,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","2023-03-16","2024-03-03",0.3,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"2023-03-16","2023-09-07"]
[429,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","2023-03-06","2023-12-12",0.99,"RP-231185","RP-232633","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"2023-04-07","2023-09-21"]
[430,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[431,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"2019-05-31","2023-03-15"]
[432,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"2022-09-09","2024-03-03",0.7,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","NA"]
[433,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[434,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","2022-12-16","2024-03-03",0.6,"CP-232132",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,"x","2022-09-23","2023-06-06"]
[435,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","2022-12-16","2024-03-03",0.7,"CP-232132",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,"x","2022-09-23","2023-06-06"]
[436,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","2022-12-16","2024-03-03",0.6,"CP-232132",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,"x","2022-09-23","2023-06-06"]
[437,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"2022-09-12","2023-12-12",0.92,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-03-22"]
[438,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[439,1000040,"   CT aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","2023-06-07","2023-12-12",0.8,"CP-232133",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,null,null,"x","2023-06-07","NA"]
[440,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"2019-03-07","2023-12-13",0.38,"CP-222238",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"2022-03-10","NA"]
[441,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","2019-03-07","2023-12-12",0.75,"CP-222238",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"2022-09-07","2023-06-06"]
[442,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","2019-03-11","2023-12-12",0,"CP-222238",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,29.518000000000001,97,49,null,null,"2022-09-07","NA"]
[443,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"2019-03-07","2024-03-03",0.52,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[444,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"2021-12-19","2022-09-12"]
[445,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","2019-03-07","2023-03-03",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-03-15"]
[446,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","2023-03-13","2024-03-03",0.85,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,"x","2022-09-11","2023-06-06"]
[447,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","2023-03-13","2024-03-03",0.95,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,"x","2022-09-11","2023-06-06"]
[448,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"2021-12-20","2023-09-09",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,97,49,null,null,"2022-09-11","NA"]
[449,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102",23.501999999999999,97,49,null,null,"2022-09-11","2023-03-16"]
[450,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","2021-12-20","2023-09-09",1,"CP-232129",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,"x","2022-09-11","2023-06-06"]
[451,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[452,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-18","S4","2023-06-08","2023-12-12",0.1,"SP-230539",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10",26.954999999999998,100,null,null,null,"2023-06-08","2023-09-07"]
[453,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","2023-06-08","2024-03-03",0.3,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;","26.955 ; 26.966",100,null,null,null,"2023-06-08","2023-09-21"]
[454,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-18","S4","2023-06-08","2024-03-03",0.05,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;",26.812999999999999,100,null,null,null,"2023-06-08","2023-09-21"]
[455,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","2021-12-13","2022-12-12",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"2021-12-13","2022-12-11"]
[456,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","2022-06-02","2024-03-03",0.35,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"2022-06-03","2023-09-07"]
[457,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","2022-12-09","2023-03-03",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"2022-12-09","2023-03-17"]
[458,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","2022-06-02","2023-06-06",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100",26.501000000000001,96,49,null,null,"2022-06-03","2023-06-08"]
[459,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","2022-12-12","2023-12-12",0.5,"SP-221346",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50",26.114000000000001,98,50,null,null,"2022-12-09","2023-09-07"]
[460,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","2020-03-25","2023-09-09",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...",26.925000000000001,87,44,null,null,"2019-12-06","2023-09-07"]
[461,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","2023-06-08","2024-03-03",0.15,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15","26.140; 26.141 ; 26.143",100,null,null,null,"2023-06-08","2023-09-07"]
[462,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","2023-06-08","2024-03-03",0.25,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;","26.512; 26.247; 26.517; 26.532 ; 26.510",100,null,null,null,"2023-06-08","2023-09-21"]
[463,0,"Rel-18 Other topics","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[464,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.84,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[465,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"2017-06-03","2023-03-15"]
[466,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100",33.887,96,49,null,null,"2022-06-02","2023-06-08"]
[467,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-09","2023-06-08"]
[468,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",0.75,"CP-232171",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,"x","2022-09-11","2023-06-30"]
[469,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","2022-12-16","2024-03-03",0.8,"CP-232171",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,"x","2022-09-11","2023-06-09"]
[470,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",0.9,"CP-232171",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,"x","2022-09-11","2023-06-06"]
[471,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",0.8,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[472,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","2023-09-06","2024-03-03",0,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ",null,"32.255; 32.291; 32.298 ",101,null,null,null,"2023-09-06","NA"]
[473,980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"2022-09-09","2023-12-12",0.71,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-23","NA"]
[474,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-12","2023-06-08"]
[475,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,"x","2022-09-23","NA"]
[476,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","2022-12-15","2023-12-12",0.75,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,"x","2022-09-23","2023-06-06"]
[477,970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","2022-09-23","2023-12-12",0.5,"SP-220981",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"2022-09-11","2023-09-07"]
[478,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"2021-12-13","2024-03-03",0.38,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"2022-09-11","2022-12-11"]
[479,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","2021-12-13","2022-09-12",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"2021-12-13","2022-12-11"]
[480,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","2022-09-12","2023-06-06",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"2022-09-11","2023-06-08"]
[481,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","2022-09-12","2024-03-03",0.08,"CP-230333",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"2022-09-11","2023-06-06"]
[482,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","2022-09-12","2024-03-03",0.05,"CP-230333",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5",29.548999999999999,97,49,null,null,"2022-09-11","2023-06-09"]
[483,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"2021-12-19","2022-06-04"]
[484,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"2022-09-08","2023-09-09",0.91,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[485,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[486,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","2022-12-16","2023-09-09",0.95,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[487,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","2022-12-16","2023-09-09",0.8,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-09"]
[488,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","2022-12-16","2023-09-09",0.95,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","NA"]
[489,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"2021-12-20","2024-03-03",0.92,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[490,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[491,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231193",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[492,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","2021-12-20","2023-12-12",0.8,"CP-231193",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[493,940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"2021-12-19","2022-12-10"]
[494,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"2021-12-19","2023-03-15"]
[495,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"2022-09-08","2024-03-03",0.89,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[496,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","2022-09-08","2023-06-06",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[497,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[498,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","2022-12-16","2024-03-03",0.8,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[499,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","2022-12-16","2023-12-12",0.8,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[500,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[501,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100",23.273,97,49,null,null,"2022-12-10","2022-12-10"]
[502,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[503,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[504,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"2022-12-10","2023-03-22"]
[505,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"2022-09-11","2023-06-06"]
[506,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-09-11","NA"]
[507,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-12-10","2023-03-22"]
[508,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","2023-06-06"]
[509,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,"x","2022-09-11","NA"]
[510,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,"x","2022-09-11","NA"]
[511,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"2022-09-08","2024-03-03",0.92,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[512,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[513,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","2022-12-16","2024-03-03",0.95,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,"x","2022-09-11","2023-06-06"]
[514,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","2022-12-16","2024-03-03",0.96,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,"x","2022-09-11","2023-06-09"]
[515,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,"x","2022-09-11","NA"]
[516,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"2022-03-10","2023-12-15",0.76,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70",23.553999999999998,95,48,null,null,"2022-03-10","2022-12-11"]
[517,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","2022-03-10","2023-03-03",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100",23.553999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[518,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","2023-03-13","2023-12-15",0.35,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-06"]
[519,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","2023-03-13","2023-12-15",0.85,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-09"]
[520,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","2023-02-02","2023-03-03",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[521,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"2020-06-25","2024-03-03",0.94,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"2021-03-18","NA"]
[522,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","2020-06-25","2021-03-12",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"2020-06-25","2021-06-11"]
[523,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"2021-12-19","2023-03-15"]
[524,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"2021-03-18","2021-06-11"]
[525,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[526,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-30"]
[527,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","2022-12-16","2024-03-03",0.9,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-06"]
[528,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","2022-12-16","2023-12-12",0.75,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"2022-09-11","2023-06-30"]
[529,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772",28.832000000000001,95,48,null,null,"2022-03-10","2023-06-30"]
[530,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","2021-12-13","2022-09-22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",38.878999999999998,94,48,null,null,"2022-01-06","2022-09-23"]
[531,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",0.6,"RP-230754",null,"Nokia ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[532,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",0.6,"RP-231106","RP-231581","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[533,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"2020-09-16","2024-03-03",0.96,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[534,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","2020-09-16","2021-09-08",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"2020-09-10","2021-09-13"]
[535,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-14"]
[536,980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100","23.501; 23.502; 23.503; 23.273 ",98,50,null,null,"2022-12-09","2023-06-08"]
[537,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","2023-03-13","2024-03-03",0.9,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,"x","2022-12-09","2023-06-06"]
[538,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,"x","2022-12-09","2023-06-06"]
[539,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"2021-12-19","2022-12-10"]
[540,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"2021-12-13","2024-06-06",0.31,"RP-222671",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671",null,94,48,null,null,"2022-01-06","2022-09-23"]
[541,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.7,"RP-222671","RP-231849","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[542,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","2021-12-15","2024-06-06",0,"RP-222671","RP-231849","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[543,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",0.7,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"2022-01-06","2023-01-09"]
[544,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.7,"RP-223488","RP-232394","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[545,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","2021-12-13","2024-03-03",0.65,"SP-211433",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65",28.863,94,48,null,null,"2021-12-13","2023-09-07"]
[546,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","2022-03-10","2024-03-03",0.88,"SP-220351",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88",null,95,48,null,null,"2022-03-10","2023-09-07"]
[547,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"2021-09-10","2024-03-03",0.74,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"2021-09-10","2022-01-07"]
[548,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[549,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"2021-12-19","2023-06-08"]
[550,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","2023-06-07","2024-03-03",0.5,"CP-232166",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,null,null,"x","2023-06-07","NA"]
[551,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","2023-06-07","2024-03-03",0.4,"CP-232166",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,null,null,"x","2023-06-07","NA"]
[552,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"2021-01-01","2023-12-12",0.87,"RP-221825",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825",null,94,48,null,null,"2022-01-06","2022-07-12"]
[553,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","2021-01-01","2023-12-12",0.8,"RP-231157","RP-232234","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[554,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-223069","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[555,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","2021-12-10","2023-12-12",0.65,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65","28.313; ; 28.317",94,48,null,null,"2021-12-10","2023-09-07"]
[556,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","2020-12-04","2021-03-12",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-04","2020-12-05"]
[557,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","2021-03-18","2021-03-25",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-03-19"]
[558,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","2022-09-16","2023-06-06",0.98,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[559,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","2022-12-16","2023-06-06",0.98,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"2022-09-19","2023-06-06"]
[560,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","2022-09-16","2022-09-16",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,31.102,97,49,null,null,"2022-09-19","NA"]
[561,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","2021-12-10","2023-03-03",0.75,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75","33.527; 33.927; 33.936",94,48,null,null,"2021-12-10","2023-03-17"]
[562,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.3,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"2022-03-10","2023-03-17"]
[563,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100",33.892000000000003,96,49,null,null,"2022-06-02","2023-09-07"]
[564,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","2018-09-06","2022-12-09",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ...","New",81,41,null,null,"2018-09-06","2023-06-08"]
[565,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"2022-06-02","2023-09-07"]
[566,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.5,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","2023-06-06"]
[567,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[568,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[569,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.5,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","2023-06-06"]
[570,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[571,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[572,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[573,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"2022-06-03","2024-03-03",0.55000000000000004,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,"x","2022-06-03","2022-06-20"]
[574,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","2022-06-03","2024-03-03",0.5,"CP-232163",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,"x","2022-06-03","2023-06-09"]
[575,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","2022-06-06","2024-03-03",0.6,"CP-232163",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,"x","2022-06-03","2023-06-09"]
[576,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","2022-06-03","2024-03-03",0.8,"CP-232163",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,"x","2022-06-03","2023-06-06"]
[577,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","2022-06-03","2022-12-08",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"2022-06-03","2022-06-20"]
[578,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.6,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,"x","2022-06-03","2022-06-20"]
[579,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.5,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,"x","2022-09-07","2023-06-06"]
[580,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",0.7,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,"x","2022-09-07","2023-06-09"]
[581,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","2022-03-07","2024-03-03",0.4,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,"x","2022-06-03","2023-06-06"]
[582,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","2022-12-15","2023-12-12",0.6,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"2022-06-03","2023-06-06"]
[583,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","2023-03-13","2023-12-15",0.9,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"2022-06-03","2023-06-06"]
[584,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-18","C4","2022-08-25","2024-03-03",0,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,"x","2022-06-03","2023-09-21"]
[585,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,null,null,null,"2023-09-20","NA"]
[586,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",22.260999999999999,101,null,null,null,"2023-09-20","NA"]
[587,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",33.500999999999998,101,null,null,null,"2023-09-20","NA"]
[588,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[589,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","2022-03-10","2023-03-03",0.95,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95","33.926 ; 33.537",95,48,null,null,"2022-03-10","2023-06-08"]
[590,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","2023-03-16","2023-12-12",0.4,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23","33.926 ; 33.528",99,50,null,null,"2023-03-16","2023-09-07"]
[591,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[592,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","2022-12-09","2023-09-09",0.8,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[593,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","2022-03-10","2023-03-03",0.99,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99","33.926 ; 33.742; 33.523",95,48,null,null,"2022-03-10","2023-06-08"]
[594,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","2022-03-10","2024-03-03",0.83,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ",null,"33.501; 33.535 ",98,50,null,null,"2022-12-09","NA"]
[595,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"2022-03-10","2023-03-17"]
[596,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2023-09-07"]
[597,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","2023-09-09","2024-03-03",0.4,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"2022-12-09","NA"]
[598,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.95,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95",33.737000000000002,95,48,null,null,"2022-03-10","2023-06-08"]
[599,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","2023-03-16","2023-09-09",0.95,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95",33.534999999999997,99,50,null,null,"2023-03-16","2023-06-08"]
[600,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","2021-12-13","2023-03-03",0.8,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80",33.869999999999997,94,48,null,null,"2021-12-13","2023-09-07"]
[601,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","2018-12-13","2022-12-09",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%->...",null,82,42,null,null,"2018-12-06","2023-09-07"]
[602,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100",33.893999999999998,96,49,null,null,"2022-06-02","2023-09-07"]
[603,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100",33.896000000000001,96,49,null,null,"2022-06-02","2023-03-17"]
[604,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","2023-05-01","2023-06-06",0,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ",null,33.500999999999998,100,null,null,null,"2023-06-08","NA"]
[605,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","2023-09-06","2024-03-03",0,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ",null,33.926000000000002,101,null,null,null,"2023-09-06","NA"]
[606,0,"Rel-18 Other NR-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[607,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"2022-03-15","2024-03-03",0.54,"RP-230314",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314",null,95,48,null,null,"2022-04-05","2023-03-29"]
[608,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","2023-06-07","2023-12-12",0.33,"RP-231492","RP-232250","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[609,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","2022-03-15","2024-03-03",0.6,"RP-231492","RP-232250","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...",38.878,95,48,null,null,"2022-04-05","2023-09-06"]
[610,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","2023-03-06","2023-12-12",0.4,"RP-230791",null,"Vodafone",null,null,null,99,50,null,null,"2023-04-07","NA"]
[611,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",0.8,"RP-231476","RP-232630","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"2023-04-07","2023-09-21"]
[612,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",0,"RP-231476","RP-232630","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630; ",null,99,50,null,null,"2023-04-07","2023-09-21"]
[613,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","2023-03-06","2024-06-06",0.23,"RP-230805",null,"Vodafone",null,null,null,99,50,null,null,"2023-04-07","NA"]
[614,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",0.6,"RP-231486","RP-231924","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[615,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","2023-03-07","2024-06-06",0,"RP-231486","RP-231924","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[616,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","2023-03-06","2023-12-12",0.5,"RP-230813",null,"Ericsson",null,null,null,99,50,null,null,"2023-04-07","NA"]
[617,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",0.5,"RP-231469","RP-231756","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[618,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","2023-03-06","2023-12-12",0.4,"RP-230764",null,"CATT",null,null,null,99,50,null,null,"2023-04-07","NA"]
[619,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",0.8,"RP-231450","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[620,991246,"   Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",0,"RP-231450","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ",null,99,50,null,null,"2023-04-07","2023-09-06"]
[621,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"2022-12-13","2023-12-12",0.5,"RP-230719",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719",null,98,50,null,null,"2023-01-09","2023-03-29"]
[622,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.5,"RP-230719","RP-232237","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"2023-01-09","2023-09-06"]
[623,981247,"   Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.5,"RP-230719","RP-232237","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[624,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"2022-12-13","2023-12-12",0.6,"RP-230137",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137",null,98,50,null,null,"2023-01-09","2023-03-29"]
[625,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.6,"RP-231119","RP-231845","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[626,981242,"   Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.6,"RP-231119","RP-231845","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[627,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"2023-01-09","2023-03-29"]
[628,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[629,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[630,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"2022-12-13","2023-12-12",0.25,"RP-230723",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723",null,98,50,null,null,"2023-01-09","2023-03-29"]
[631,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-230723","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated;...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[632,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-230723","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eo...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[633,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"2022-09-12","2025-06-06",0.32,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"2022-10-19","2023-01-09"]
[634,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.67,"RP-223499","RP-232239","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...",38.895000000000003,97,49,null,null,"2022-10-19","2023-09-06"]
[635,970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","2022-09-13","2023-12-12",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"2022-10-19","2022-12-09"]
[636,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",0.28999999999999998,"RP-231152","RP-232245","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ",null,100,null,null,null,"2023-06-29","2023-09-21"]
[637,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",0.51,"RP-230352",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352",null,97,49,null,null,"2022-10-19","2023-03-29"]
[638,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.7,"RP-231064","RP-232206","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...",38.896000000000001,97,49,null,null,"2022-10-19","2023-09-06"]
[639,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",0.7,"RP-231064","RP-232206","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"2022-10-19","2023-09-06"]
[640,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.05,"RP-230869","RP-231549","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[641,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"2022-09-12","2023-12-12",0.4,"RP-230479",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479",null,97,49,null,null,"2022-10-19","2023-03-29"]
[642,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.8,"RP-231139","RP-232376","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....",38.896999999999998,97,49,null,null,"2022-10-19","2023-09-06"]
[643,970287,"   Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","2022-09-13","2023-12-12",0,"RP-231139","RP-232376","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,null,null,"2022-10-19","2023-09-06"]
[644,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"2022-09-12","2023-12-12",0.38,"RP-230309",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309",null,97,49,null,null,"2022-10-19","2023-03-29"]
[645,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.75,"RP-231196","RP-232257","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...",38.899000000000001,97,49,null,null,"2022-10-19","2023-09-06"]
[646,970289,"   Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",0,"RP-231196","RP-232257","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"2022-10-19","2023-09-06"]
[647,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"2022-09-12","2023-12-12",0.3,"RP-230354",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354",null,97,49,null,null,"2022-10-19","2023-03-29"]
[648,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.3,"RP-231063","RP-232211","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...",38.85,97,49,null,null,"2022-10-19","2023-09-06"]
[649,970290,"   Perf. part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",0.3,"RP-231063","RP-232211","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,null,null,"2022-10-19","2023-09-06"]
[650,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"2022-09-08","2023-12-12",0.2,"RP-230756",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756",null,97,49,null,null,"2022-09-23","2023-03-29"]
[651,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",0.2,"RP-231010","RP-231705","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"2022-09-23","2023-09-06"]
[652,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","2022-09-08","2024-06-06",0.51,"RP-223509",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509",null,97,49,null,null,"2022-09-23","2023-01-09"]
[653,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",0.8,"RP-223509","RP-232336","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[654,970281,"   Perf. part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",0.3,"RP-223509","RP-232336","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[655,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.8,"RP-230133",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133",null,96,49,null,null,"2022-08-03","2023-03-29"]
[656,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231115","RP-231841","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"2022-08-03","2023-09-06"]
[657,961210,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231115","RP-231841","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[658,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.75,"RP-230084",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084",null,96,49,null,null,"2022-08-03","2023-03-29"]
[659,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.75,"RP-231100","RP-231861","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"2022-08-03","2023-09-06"]
[660,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",0.75,"RP-231100","RP-231861","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"2022-08-03","2023-09-06"]
[661,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"2022-06-16","2023-12-12",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[662,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[663,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"2022-06-15","2023-12-12",0.91,"RP-230067",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067",null,96,49,null,null,"2022-08-03","2023-03-29"]
[664,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.91,"RP-231030","RP-231622","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"2022-08-03","2023-09-06"]
[665,961207,"   Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.91,"RP-231030","RP-231622","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[666,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.54,"RP-230421",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421",null,96,49,null,null,"2022-08-03","2023-03-29"]
[667,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.54,"RP-231034","RP-231739","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[668,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.54,"RP-231034","RP-231739","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[669,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"2022-06-15","2023-03-03",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"2022-08-03","2023-03-29"]
[670,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...",38.892000000000003,96,49,null,null,"2022-08-03","2023-03-17"]
[671,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"2022-08-03","2023-03-17"]
[672,960098,"Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"2022-06-16","2023-12-12",0,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-222498",null,96,49,null,null,"2022-08-03","2022-09-23"]
[673,960198,"   Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-222498","RP-232364","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...",null,96,49,null,null,"2022-08-03","2023-09-06"]
[674,960298,"   Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-222498","RP-232364","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...",null,96,49,null,null,"2022-08-03","2023-09-06"]
[675,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",0.65,"RP-223516",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516",null,96,49,null,null,"2022-08-03","2023-01-09"]
[676,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.7,"RP-231494","RP-232373","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[677,960295,"   Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.7,"RP-231494","RP-232373","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[678,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.49,"RP-230868","RP-231550","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[679,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"2022-06-15","2023-06-06",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"2022-08-03","2023-03-29"]
[680,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","2022-06-15","2023-06-06",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"2022-08-03","2023-06-07"]
[681,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","2022-06-15","2023-06-06",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"2022-08-03","2023-03-31"]
[682,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"2021-12-13","2024-06-06",0.42,"RP-230186",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186",null,94,48,null,null,"2022-01-06","2023-03-29"]
[683,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","2021-12-13","2023-12-12",0.95,"RP-231425","RP-231712","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[684,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","2021-12-15","2024-06-06",0,"RP-231425","RP-231712","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[685,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.42,"RP-221622",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622",null,94,48,null,null,"2022-01-06","2022-07-12"]
[686,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",0.95,"RP-221622","RP-232132","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[687,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0,"RP-221622","RP-232132","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[688,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.44,"RP-222251",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251",null,94,48,null,null,"2022-01-06","2022-09-23"]
[689,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",0.98,"RP-222251","RP-232089","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[690,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0,"RP-222251","RP-232089","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[691,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.38,"RP-221858",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858",null,94,48,null,null,"2022-01-06","2022-07-12"]
[692,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",0.85,"RP-221858","RP-232272","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[693,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0,"RP-221858","RP-232272","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[694,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"2021-12-13","2024-06-06",0.4,"RP-223276",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276",null,94,48,null,null,"2022-01-06","2023-01-09"]
[695,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",0.9,"RP-223276","RP-231717","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[696,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0,"RP-223276","RP-231717","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[697,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","2021-12-13","2023-12-12",0.94,"RP-223041","RP-232231","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...",38.857999999999997,94,48,null,null,"2022-01-06","2023-09-06"]
[698,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"2022-09-08","2024-06-06",0.73,"RP-230175",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175",null,97,49,null,null,"2022-09-23","2023-03-29"]
[699,970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",0.95,"RP-230175","RP-232635","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"2022-09-23","2023-09-21"]
[700,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",0.3,"RP-230175","RP-232635","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"2022-09-23","2023-09-21"]
[701,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","2022-09-08","2024-06-06",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%-...",38.866999999999997,94,48,null,null,"2022-01-06","2022-09-23"]
[702,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.36,"RP-223520",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520",null,94,48,null,null,"2022-01-06","2023-01-09"]
[703,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.8,"RP-231475","RP-232311","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[704,940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0,"RP-231475","RP-232311","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[705,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",0.99,"RP-221281",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281",null,94,48,null,null,"2022-01-06","2022-07-12"]
[706,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.99,"RP-221281","RP-232631","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[707,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"2022-03-15","2023-12-12",0.99,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"2022-04-05","2023-01-09"]
[708,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"2022-04-05","2023-01-09"]
[709,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"2022-04-05","2023-01-09"]
[710,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","2023-03-03","2023-12-12",0.99,"RP-230907","RP-231546","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[711,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"2022-03-15","2023-12-12",0.88,"RP-220916",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ",null,95,48,null,null,"2022-04-05","NA"]
[712,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-220916","RP-232637","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"2022-04-05","2023-09-21"]
[713,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","2022-03-15","2023-12-12",0.8,"RP-220916","RP-232637","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"2022-04-05","2023-09-21"]
[714,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"2022-03-15","2024-03-03",0.53,"RP-230279",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279",null,95,48,null,null,"2022-04-05","2023-03-29"]
[715,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.85,"RP-230279","RP-232236","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[716,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","2022-03-16","2024-03-03",0.25,"RP-230279","RP-232236","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[717,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"2022-03-15","2024-03-01",0.75,"RP-222909",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909",null,95,48,null,null,"2022-04-05","2023-01-09"]
[718,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.75,"RP-222909","RP-232607","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...",38.890999999999998,95,48,null,null,"2022-04-05","2023-09-21"]
[719,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","2022-03-15","2024-03-01",0.75,"RP-222909","RP-232607","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"2022-04-05","2023-09-21"]
[720,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"2022-03-15","2023-11-30",0.51,"RP-223527","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"2022-04-05","2023-01-09"]
[721,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.85,"RP-231714","RP-231715","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...",38.750999999999998,95,48,null,null,"2022-04-05","2023-09-21"]
[722,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","2022-03-15","2024-03-03",0.2,"RP-231714","RP-231715","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[723,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"2022-03-15","2024-06-06",0.4,"RP-221696",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696",null,95,48,null,null,"2022-04-05","2022-07-12"]
[724,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.9,"RP-221696","RP-232104","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[725,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","2022-03-17","2024-06-06",0,"RP-221696","RP-232104","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[726,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"2022-03-15","2024-06-06",0.8,"RP-230753",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753",null,95,48,null,null,"2022-04-05","2023-03-29"]
[727,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.8,"RP-231490","RP-232365","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...",38.881,95,48,null,null,"2022-04-05","2023-09-06"]
[728,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",0.8,"RP-231490","RP-232365","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[729,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"2022-03-15","2023-12-12",0.83,"RP-230742",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742",null,95,48,null,null,"2022-04-05","2023-03-29"]
[730,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-231066","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[731,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","2022-03-16","2023-12-12",0.7,"RP-231066","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[732,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"2022-03-15","2024-06-06",0.42,"RP-230755",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755",null,95,48,null,null,"2022-04-05","2023-03-29"]
[733,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.8,"RP-231477","RP-232312","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[734,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",0,"RP-231477","RP-232312","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[735,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","2022-12-14","2024-03-03",0.63,"RP-223246","RP-232306","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[736,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","2022-06-15","2023-03-03",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualco...",38.893000000000001,96,49,null,null,"2022-07-12","2023-03-31"]
[737,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2024-06-06",0.05,"RP-231249","RP-232360","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[738,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[739,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"2022-09-12","2023-12-12",0.66,"RP-230069",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069",null,97,49,null,null,"2022-10-19","2023-03-29"]
[740,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",0.66,"RP-231032","RP-231624","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...",38.898000000000003,97,49,null,null,"2022-10-19","2023-09-06"]
[741,970288,"   Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",0.66,"RP-231032","RP-231624","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,null,null,"2022-10-19","2023-09-06"]
[742,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2024-06-06",0.05,"RP-231199","RP-232259","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[743,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",0.43,"RP-223424",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424",null,96,49,null,null,"2022-08-03","2023-01-09"]
[744,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.6,"RP-231434","RP-231616","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....",37.829000000000001,96,49,null,null,"2022-08-03","2023-09-06"]
[745,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.18,"RP-231429","RP-231612","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[746,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2024-06-06",0.05,"RP-231248","RP-232359","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[747,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"2022-12-13","2023-12-12",0.85,"RP-230161",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161",null,98,50,null,null,"2023-01-09","2023-03-29"]
[748,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.85,"RP-231013","RP-231718","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[749,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"2022-09-08","2023-12-12",0.8,"RP-223354",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354",null,97,49,null,null,"2022-09-23","2023-01-09"]
[750,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",0.8,"RP-223354","RP-232375","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",38.893999999999998,97,49,null,null,"2022-09-23","2023-09-06"]
[751,970284,"   Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","2022-09-08","2023-12-12",0.8,"RP-223354","RP-232375","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,null,null,"2022-09-23","2023-09-06"]
[752,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"2022-09-08","2024-06-06",0.49,"RP-223112",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112",null,97,49,null,null,"2022-09-23","2023-01-09"]
[753,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",0.75,"RP-223112","RP-231822","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...",38.869999999999997,97,49,null,null,"2022-09-23","2023-09-06"]
[754,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",0.3,"RP-223112","RP-231822","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[755,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",0.8,"RP-230475",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475",null,96,49,null,null,"2022-08-03","2023-03-29"]
[756,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231134","RP-232371","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"2022-08-03","2023-09-06"]
[757,961209,"   Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231134","RP-232371","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[758,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.4,"RP-230338",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338",null,96,49,null,null,"2022-08-03","2023-03-29"]
[759,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231086","RP-232300","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"2022-08-03","2023-09-06"]
[760,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-231086","RP-232300","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"2022-08-03","2023-09-06"]
[761,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.6,"RP-222237",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237",null,96,49,null,null,"2022-08-03","2022-09-23"]
[762,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.6,"RP-222237","RP-231727","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[763,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.6,"RP-222237","RP-231727","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[764,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.75,"RP-230725",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725",null,96,49,null,null,"2022-08-03","2023-03-29"]
[765,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.75,"RP-231059","RP-231724","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"2022-08-03","2023-09-06"]
[766,961203,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.75,"RP-231059","RP-231724","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[767,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.75,"RP-230473",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473",null,96,49,null,null,"2022-08-03","2023-03-29"]
[768,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.75,"RP-231132","RP-232369","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"2022-08-03","2023-09-06"]
[769,961204,"   Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.75,"RP-231132","RP-232369","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%; Stat Rep: RP-223.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[770,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.4,"RP-230090",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090",null,96,49,null,null,"2022-08-03","2023-03-29"]
[771,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.45,"RP-230985","R4-232247","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[772,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.35,"RP-230985","R4-232247","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[773,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.8,"RP-230135",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135",null,96,49,null,null,"2022-08-03","2023-03-29"]
[774,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231117","RP-231843","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[775,961206,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.8,"RP-231117","RP-231843","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[776,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",0.25,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"2022-08-03","2023-03-29"]
[777,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.5,"RP-230390","RP-231834","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ",37.878,96,49,null,null,"2022-08-03","2023-09-06"]
[778,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0,"RP-230390","RP-231834","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[779,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",0.5,"RP-222288",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288",null,96,49,null,null,"2022-08-03","2022-09-23"]
[780,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.99,"RP-231194","RP-232269","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...",37.877000000000002,96,49,null,null,"2022-08-03","2023-09-06"]
[781,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0,"RP-231194","RP-232269","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"2022-08-03","2023-09-06"]
[782,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[783,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"2022-12-13","2023-12-12",0.99,"RP-222824",null,"Ericsson ",null,null,null,98,50,null,null,"2023-01-09","NA"]
[784,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.99,"RP-222824","RP-231880","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[785,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.99,"RP-222824","RP-231880","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ",null,98,50,null,null,"2023-01-09","2023-09-06"]
[786,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"2022-12-12","2023-06-06",0.55000000000000004,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"2023-01-09","2023-03-29"]
[787,981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","2022-12-12","2023-06-06",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"2023-01-09","2023-06-29"]
[788,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","2022-12-12","2023-06-06",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[789,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"2023-01-09","2023-03-29"]
[790,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[791,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"2022-06-15","2023-12-12",0.38,"RP-230471",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471",null,96,49,null,null,"2022-08-03","2023-03-29"]
[792,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",0.38,"RP-231130","RP-232367","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"2022-08-03","2023-09-06"]
[793,960299,"   Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.38,"RP-231130","RP-232367","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....",null,96,49,null,null,"2022-08-03","2023-09-06"]
[794,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"2022-08-03","NA"]
[795,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"2022-08-03","2023-01-09"]
[796,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[797,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[798,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[799,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"2017-12-15","2017-12-15",0.34,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[800,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","2023-03-03","2023-09-08",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23:...",null,99,50,null,null,"2023-03-29","2023-09-21"]
[801,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","2023-03-03","2023-12-12",0.4,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;",37.911000000000001,99,50,null,null,"2023-03-29","2023-09-21"]
[802,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","2022-09-08","2023-09-08",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...",38.847999999999999,97,49,null,null,"2022-09-23","2023-09-21"]
[803,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-231468","RP-231862","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...",38.845999999999997,95,48,null,null,"2022-04-05","2023-09-06"]
[804,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","2022-03-15","2023-12-12",0.8,"RP-230814","RP-232001","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"2022-04-05","2023-09-06"]
[805,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...",38.877000000000002,95,48,null,null,"2022-04-05","2023-06-07"]
[806,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","2022-03-03","2023-03-03",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...",38.872,95,48,null,null,"2022-04-05","2023-03-17"]
[807,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-18","RP","2017-12-15","2023-12-12",0.98,"RP-230415","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","SI under RAN leadership¦TR 37.8XX27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957; 14...","37.890; 37.107",78,40,null,null,"2018-01-08","2023-09-21"]
[808,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","2019-09-19","2022-06-22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"2019-10-08","2022-07-12"]
[809,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","2020-09-17","2023-03-03",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"2020-09-25","2023-03-17"]
[810,0,"Rel-18 Network automation","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[811,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.8,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"2022-12-09","2022-12-10"]
[812,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"2021-12-19","2022-12-10"]
[813,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","2022-03-10","2023-03-03",0.95,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95",33.738,95,48,null,null,"2022-03-10","2023-06-08"]
[814,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",0.65,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[815,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2023-06-08"]
[816,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.75,"CP-230119",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[817,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.5,"CP-230119",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[818,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","2022-12-15","2024-03-03",0.95,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"2022-06-03","2023-06-06"]
[819,0,"Rel-18 other Studies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[820,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","2019-12-06","2021-12-10",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"2019-12-06","2021-12-10"]
[821,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","2022-06-02","2023-09-09",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"2022-06-20","2023-06-30"]
[822,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[823,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","2023-06-30","2024-03-03",0.3,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30","28.531; 28.533; 28.526 ",100,null,null,null,"2023-06-30","2023-09-07"]
[824,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","2023-05-01","2023-06-06",0,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ",null,"32.240; 32.255; 32.256; 32.291; 32.298 ",100,null,null,null,"2023-06-08","NA"]
[825,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","2023-06-08","2024-03-03",0.3,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30","28.552; 28.554; 28.622 ; 28.318",100,null,null,null,"2023-06-08","2023-09-07"]
[826,980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","2022-12-12","2023-09-09",0.18,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18",28.84,98,50,null,null,"2022-12-09","2023-09-07"]
[827,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",0.4,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"2022-12-09","2023-09-07"]
[828,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","2021-12-10","2023-12-12",0.55000000000000004,"SP-211441",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[829,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","2021-12-10","2022-12-09",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"2021-12-10","2023-09-07"]
[830,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"2022-06-02","2022-12-11"]
[831,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","2022-06-02","2023-12-12",0.8,"SP-220690",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80","28.552; 32.425; 28.554; 28.550 ",96,49,null,null,"2022-06-02","2023-09-07"]
[832,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","2020-03-25","2023-12-12",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"2019-12-06","2023-06-08"]
[833,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","2022-03-10","2023-03-03",1,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"2022-03-10","2023-06-30"]
[834,930033,"Access control for management service ","MSAC",1,"Rel-18","S5","2020-09-16","2023-12-12",0.81,"SP-210859",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ",null,"28.533; 28.540; 28.622; 28.623; 28.532; ",93,47,null,null,"2021-09-10","NA"]
[835,890016,"   Study on access control for management service ","FS_MNSAC",2,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"2020-09-11","2021-09-13"]
[836,930010,"   Access control for management service ","MSAC",2,"Rel-18","S5","2021-09-10","2023-12-12",0.73,"SP-210859",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73","28.533; 28.540; 28.622; 28.623; 28.532; ",93,47,null,null,"2021-09-10","2023-09-07"]
[837,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","2021-09-10","2023-12-12",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[838,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","2020-09-16","2022-03-10",0.1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18",null,89,45,null,null,"2020-09-10","2021-12-13"]
[839,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","2021-03-18","2022-03-11",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"2021-03-18","2022-06-04"]
[840,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[841,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","2023-03-16","2023-12-12",0.1,"SP-230776",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161",99,50,null,null,"2023-03-16","2023-09-21"]
[842,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100",28.864000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[843,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","2023-03-16","2023-12-12",0.75,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75","28.541; 28.552; 28.554 ",99,50,null,null,"2023-03-16","2023-09-07"]
[844,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100",28.907,94,48,null,null,"2021-12-13","2023-03-17"]
[845,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100",28.913,94,48,null,null,"2021-12-13","2023-06-08"]
[846,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","2021-12-13","2024-03-03",0.6,"SP-211442",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->",28.864999999999998,94,48,null,null,"2021-12-13","2023-09-07"]
[847,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","2021-12-13","2024-03-03",0.7,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24",28.908999999999999,94,48,null,null,"2021-12-13","2023-09-07"]
[848,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","2021-12-13","2023-12-12",0.85,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85",28.91,94,48,null,null,"2021-12-13","2023-09-07"]
[849,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100",28.911999999999999,94,48,null,null,"2021-12-13","2023-06-08"]
[850,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774",28.831,95,48,null,null,"2022-03-10","2023-06-30"]
[851,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",28.902999999999999,95,48,null,null,"2022-03-10","2023-06-08"]
[852,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","2022-03-10","2023-03-03",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->",28.832999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[853,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","2023-03-16","2023-12-12",0.9,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90","28.541; 28.552; 28.554 ",99,50,null,null,"2023-03-16","2023-09-07"]
[854,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",28.834,95,48,null,null,"2022-03-10","2023-06-08"]
[855,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100",28.835000000000001,95,48,null,null,"2022-03-10","2023-06-08"]
[856,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","2023-06-08","2024-03-03",0.3,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30","32.130; 28.541; 28.552 ",100,null,null,null,"2023-06-08","2023-09-07"]
[857,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773",28.837,95,48,null,null,"2022-03-10","2023-06-30"]
[858,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","2022-03-10","2024-03-03",0.4,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40",28.83,95,48,null,null,"2022-03-10","2023-09-07"]
[859,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"2022-06-02","2023-06-08"]
[860,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","2021-01-12","2023-03-03",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"2021-01-12","2023-03-17"]
[861,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","2021-06-11","2023-12-12",0.96,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"2021-06-11","2023-09-07"]
[862,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","2023-03-16","2023-09-09",0,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ",null,"32.240; 32.290 ",99,50,null,null,"2023-03-16","NA"]
[863,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","2021-06-11","2023-09-09",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"2021-06-11","2023-09-07"]
[864,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","2023-09-06","2024-03-03",0,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ",null,"32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,null,null,null,"2023-09-06","NA"]
[865,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","2022-09-12","2023-03-10",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"2022-09-11","2023-03-17"]
[866,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","2022-09-12","2024-03-03",0.45,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45","; 28.842",97,49,null,null,"2022-09-11","2023-09-07"]
[867,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","2022-09-12","2023-12-12",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100",28.838999999999999,97,49,null,null,"2022-09-11","2023-09-07"]
[868,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",0,"SP-231151",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,null,null,null,"2023-09-06","2023-09-21"]
[869,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","2023-03-16","2024-03-03",0.4,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"2023-03-16","2023-09-07"]
[870,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","2023-03-16","2023-12-12",0.3,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"2023-03-16","2023-09-07"]
[871,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","2023-03-16","2023-12-12",0.4,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"2023-03-16","2023-09-07"]
[872,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[873,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","2021-06-11","2023-03-03",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...",33.875999999999998,92,47,null,null,"2021-06-11","2023-06-08"]
[874,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100",33.31,99,50,null,null,"2023-03-16","2023-09-07"]
[875,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","2022-12-09","2023-03-03",0.95,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95",33.500999999999998,98,50,null,null,"2022-12-09","2023-06-08"]
[876,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.65,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","NA"]
[877,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","2022-06-03","2023-12-12",0.6,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"2022-06-03","2023-06-06"]
[878,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",0.7,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","2023-06-09"]
[879,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","2022-06-03","2023-03-03",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"2022-06-03","2022-07-13"]
[880,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","2023-06-07","2024-03-03",0.3,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,null,null,null,"2023-06-07","2023-06-30"]
[881,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","2023-12-12","2023-12-12",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"2018-06-06","2021-09-13"]
[882,0,"Rel-18 other aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[883,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"2021-03-12","2023-03-03",0,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[884,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","2021-03-12","2023-09-09",0.2,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"2021-06-11","2023-03-31"]
[885,1000001,"Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",1,"Rel-18","C4","2023-06-07","2023-12-12",0.4,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;",29.856999999999999,100,null,null,null,"2023-06-07","2023-06-30"]
[886,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"2019-03-07","2019-03-07",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"2022-03-13","NA"]
[887,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","2022-01-05","2023-03-16",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"2023-06-08","2023-06-08"]
[888,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[889,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[890,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"2019-03-07","2019-12-12",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[891,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[892,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"2019-05-31","2020-06-26"]
[893,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","2019-06-06","2021-03-12",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"2019-05-31","2021-03-19"]
[894,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"2020-06-12","2022-06-10",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","NA"]
[895,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","2022-03-12"]
[896,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"2021-03-18","2021-09-10"]
[897,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"2021-03-18","2022-06-20"]
[898,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[899,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"2021-03-18","2022-06-04"]
[900,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[901,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"2020-06-25","2022-06-04"]
[902,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[903,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","2018-06-06","2019-06-12",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"2018-06-06","2019-09-13"]
[904,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[905,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","2021-03-18","2022-06-10",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"2021-03-18","2022-06-04"]
[906,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","2019-03-07","2021-06-11",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"2018-12-06","2021-09-13"]
[907,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","2019-06-06","2020-03-12",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"2019-05-31","2022-03-22"]
[908,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","2020-12-04","2021-12-10",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"2020-12-04","2022-03-12"]
[909,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[910,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2019-12-06"]
[911,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-06-28"]
[912,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-09-13"]
[913,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"2020-09-25","2022-06-04"]
[914,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"2019-05-31","2020-06-25"]
[915,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"2019-09-13","NA"]
[916,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"2018-09-06","2019-09-13"]
[917,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","2019-09-19","2019-12-12",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[918,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"2019-05-31","2020-12-05"]
[919,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","2020-03-25","2021-09-08",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"2019-05-31","2021-12-10"]
[920,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"2021-03-18","2021-06-11"]
[921,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"2021-03-18","2022-06-20"]
[922,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"2021-03-18","2022-03-12"]
[923,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"2021-03-18","2022-06-20"]
[924,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"2019-03-07","2024-06-06",0.76,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"2021-01-06","2021-04-07"]
[925,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[926,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[927,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-09-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"2021-01-06","2022-09-23"]
[928,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","2022-09-08","2024-06-06",0.17,"RP-222384","RP-231838","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[929,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"2019-05-31","NA"]
[930,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","2018-09-06","2019-09-13",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"2018-09-06","2019-12-06"]
[931,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"2019-05-31","2019-12-06"]
[932,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"2014-08-29","2014-08-29"]
[933,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"2018-09-06","2019-12-13",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[934,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","2018-09-06","2019-12-13",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[935,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"2019-05-31","2019-12-06"]
[936,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","2018-12-06","2020-12-15",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"2018-12-06","2020-12-05"]
[937,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","2018-12-06","2021-03-12",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"2018-12-06","2021-03-21"]
[938,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"2020-12-04","2021-03-21"]
[939,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","2020-12-04","2021-06-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"2020-12-04","2021-07-02"]
[940,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"2021-06-11","2022-03-12"]
[941,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"2021-06-11","2022-03-12"]
[942,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100",33.853999999999999,88,45,null,null,"2020-06-25","2023-03-31"]
[943,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"2018-09-06","2023-12-12",0.92,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"2018-09-06","NA"]
[944,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","2018-09-06","2018-12-14",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"2018-09-06","2018-12-04"]
[945,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"2020-12-03","2021-12-10"]
[946,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"2021-03-18","2021-06-11"]
[947,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[948,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"2021-03-18","2022-03-12"]
[949,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[950,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","2021-06-11","2022-03-11",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"2021-06-11","2022-03-12"]
[951,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","2023-03-03","2023-12-12",0.4,"RP-230716","RP-231997","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[952,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[953,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","NA"]
[954,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","2018-06-06","2018-09-14",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[955,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","2018-06-06","2020-06-25",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"2018-06-06","2020-06-26"]
[956,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","2019-12-06","2021-09-08",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","2021-12-10"]
[957,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2021-06-11"]
[958,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-06-04"]
[959,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","2020-09-16","2021-09-10",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[960,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[961,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","2021-09-13","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"2020-09-12","2022-06-04"]
[962,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"2019-12-16","2023-12-12",0.9,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"2020-01-14","2022-04-05"]
[963,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","2019-12-16","2022-06-06",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"2020-01-14","2023-03-17"]
[964,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","2019-12-16","2023-03-03",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[965,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.5,"RP-221241","RP-232016","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"2022-07-12","2023-09-06"]
[966,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2021-06-15","2023-12-12",0.99,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"2021-07-02","NA"]
[967,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","2021-06-15","2022-06-22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[968,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.98,"RP-231308","RP-232307","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[969,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"2021-09-10","2022-03-12"]
[970,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"2022-03-12","2022-06-20"]
[971,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[972,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[973,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-06-04"]
[974,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","2019-03-07","2021-03-12",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"2019-03-14","2021-03-21"]
[975,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2019-12-16","2021-06-15",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"2020-01-14","2021-07-02"]
[976,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[977,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"2019-09-13","2021-06-11"]
[978,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","2020-06-12","2021-06-11",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"2020-06-25","2021-06-11"]
[979,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","2021-06-11","2021-06-18",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-03-24"]
[980,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"2020-12-03","NA"]
[981,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"2020-12-03","2021-09-13"]
[982,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"2021-03-18","2021-09-10"]
[983,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[984,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[985,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[986,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[987,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"2020-01-14","2022-04-05"]
[988,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","2021-12-21","2022-03-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[989,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","2019-03-07","2022-09-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[990,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"2019-12-16","2023-12-12",0.97,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"2020-01-14","2022-09-23"]
[991,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[992,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","2019-12-16","2022-12-21",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[993,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.85,"RP-221238","RP-231999","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[994,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"2019-12-16","2023-12-12",0.96,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"2020-01-14","2022-04-05"]
[995,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"2020-01-14","2022-12-09"]
[996,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","2020-06-15","2022-12-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...;...",null,86,44,null,null,"2020-09-25","2022-12-09"]
[997,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.82,"RP-221416","RP-231544","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"2022-07-12","2023-09-06"]
[998,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[999,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"2019-12-16","2024-03-03",0.76,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1000,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","2019-12-16","2022-03-11",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1001,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1002,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-03",0.05,"RP-221448","RP-231836","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1003,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","2019-12-16","2020-09-15",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1004,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","2019-06-06","2020-06-12",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"2019-05-31","2022-03-22"]
[1005,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-02-10"]
[1006,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-06-11"]
[1007,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1008,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1009,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1010,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"2021-03-18","NA"]
[1011,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"2019-09-13","2021-03-19"]
[1012,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","2021-03-18","2021-09-08",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"2021-03-18","2021-12-10"]
[1013,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1014,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"2021-06-11","2022-03-22"]
[1015,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"2021-06-11","2022-06-04"]
[1016,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1017,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","2021-06-15","2023-09-22",0.99,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1018,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"2021-07-02","2022-03-22"]
[1019,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"2021-07-02","2022-03-22"]
[1020,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","2021-12-13","2023-09-22",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[1021,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"2019-12-16","2023-12-12",0.87,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"2020-01-14","2021-09-29"]
[1022,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1023,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","2019-12-16","2022-12-01",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1024,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.4,"RP-221401","RP-231728","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1025,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1026,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1027,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"2019-12-16","2023-12-12",0.99,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1028,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1029,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1030,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-01",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"2020-07-28","2023-01-09"]
[1031,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.97,"RP-230631","RP-232305","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1032,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"2019-12-16","2024-03-03",0.91,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1033,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1034,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1035,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","2023-03-03","2024-03-03",0.46,"RP-230436","RP-232355","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[1036,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"2019-03-11","2022-09-22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1037,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1038,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1039,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","2019-03-11","2021-12-10",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"2019-03-14","2022-03-12"]
[1040,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"2019-12-16","2022-03-09",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"2020-01-14","2022-01-21"]
[1041,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-09",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1042,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"2020-09-15","2023-12-12",0.8,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126...",null,89,45,null,null,"2020-10-11","2022-07-12"]
[1043,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","2021-12-14","2022-06-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"2022-03-22","2022-06-20"]
[1044,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"2020-10-11","2022-09-09"]
[1045,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.45,"RP-221299","RP-232254","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1046,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"2020-09-15","2023-12-12",0.97,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1047,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1048,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Noki...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1049,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.9,"RP-221240","RP-232015","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1050,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1051,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1052,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1053,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-06-06",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1054,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1055,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1056,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1057,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"2020-09-15","2023-12-12",0.82,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366...",38.850999999999999,89,45,null,null,"2020-10-11","2022-07-12"]
[1058,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1059,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1060,970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","2022-09-08","2023-12-12",0.27,"RP-221932","RP-231611","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"2022-09-23","2023-09-06"]
[1061,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1062,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1063,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1064,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1065,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporati...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1066,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1067,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-12-12",0.8,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"2020-10-11","2022-04-05"]
[1068,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1069,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1070,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.32,"RP-221848","RP-232354","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1071,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","2021-12-13","2022-09-22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"2022-01-06","2022-04-05"]
[1072,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1073,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1074,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"2022-07-12","2022-09-23"]
[1075,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1076,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1077,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1078,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1079,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"2019-12-06","2022-06-21"]
[1080,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","2019-09-19","2020-09-14",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"2019-09-13","2020-09-13"]
[1081,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","2020-06-12","2021-12-10",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"2020-06-26","2021-12-13"]
[1082,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1083,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"2019-05-31","2021-06-11"]
[1084,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","2018-09-14","2020-03-12",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"2018-09-14","2020-12-05"]
[1085,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"2020-06-25","2022-03-12"]
[1086,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","2019-09-19","2020-03-12",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"2019-09-13","2020-03-26"]
[1087,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"2019-03-07","2024-03-03",0.93,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1088,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"2019-03-14","2021-03-19"]
[1089,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","2020-12-03","2021-09-10",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-06-04"]
[1090,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"2021-06-11","2022-06-04"]
[1091,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"2021-06-11","2022-06-20"]
[1092,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"2021-06-11","2022-06-20"]
[1093,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"2022-06-20","NA"]
[1094,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1095,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",0.3,"SP-230623",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30","32.240; 32.255; 32.298; 32.291 ",100,null,null,null,"2023-06-08","2023-09-07"]
[1096,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","2019-09-02","2019-12-12",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1097,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1098,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","2019-12-16","2023-12-12",0.96,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1099,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1100,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",0.9,"RP-220423","RP-232352","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1101,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"2020-09-11","2021-03-21"]
[1102,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"2020-09-11","2021-06-11"]
[1103,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1104,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"2019-12-06","2022-03-11",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1105,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"2019-12-06","2021-06-11"]
[1106,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","2020-06-17","2022-03-11",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"2020-09-25","2022-06-04"]
[1107,880020,"Protocol enhancements for Mission Critical Services ","MCProtoc17",1,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-202193",null,"AXELL, Jörgen ","jorgen.axell@ericsson.com ","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/12/21: 70%-> ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1108,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","2018-12-13","2022-03-11",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"2018-12-07","2022-06-04"]
[1109,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","2020-09-16","2021-09-08",0.65,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"2020-09-25","2021-09-13"]
[1110,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1111,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"2019-03-07","2022-06-07",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"2019-12-06","2020-03-26"]
[1112,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","2019-03-07","2019-12-05",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-03-26"]
[1113,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"2019-12-06","2021-06-11"]
[1114,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"2020-12-05","2021-06-11"]
[1115,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","2020-12-07","2022-03-11",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"2020-12-05","2022-06-04"]
[1116,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","2020-12-07","2022-03-11",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1117,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"2022-06-20","2022-08-03"]
[1118,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-12-05"]
[1119,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1120,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1121,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"2021-03-18","2021-09-10"]
[1122,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"2021-03-18","2022-06-04"]
[1123,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"2021-03-18","2022-03-12"]
[1124,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"2021-03-18","2022-06-04"]
[1125,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","2021-06-11","2021-12-10",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"2021-06-11","2022-03-12"]
[1126,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","2021-06-11","2022-03-11",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1127,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"2020-06-25","2022-03-12"]
[1128,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"2021-12-10","2022-06-04"]
[1129,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"2021-09-10","2022-03-22"]
[1130,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","2020-06-25","2021-12-10",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"2020-06-26","2022-06-21"]
[1131,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"2021-09-10","2022-06-04"]
[1132,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","2020-03-25","2021-09-08",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"2019-12-06","2021-09-13"]
[1133,0,"Rel-17 Slicing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1134,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"2021-06-11","2022-04-28"]
[1135,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"2021-06-11","2022-06-20"]
[1136,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1137,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1138,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1139,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"2019-09-19","2023-06-06",0.99,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1140,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"2019-09-13","2021-03-19"]
[1141,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-22"]
[1142,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","2021-03-18","2023-06-06",0.99,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"2021-03-18","2021-10-01"]
[1143,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1144,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"2021-03-18","2022-06-04"]
[1145,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"2021-03-18","2022-03-12"]
[1146,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","2022-03-15","2023-06-06",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"2022-04-05","2023-06-07"]
[1147,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","2019-03-07","2023-09-22",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1148,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","2021-03-12","2022-06-22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1149,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","2022-06-15","2023-09-22",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1150,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","2022-06-03","2022-06-20",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-03","2022-06-04"]
[1151,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-20","2022-08-03"]
[1152,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","2019-12-06","2021-12-10",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"2019-12-06","2021-12-13"]
[1153,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","2022-03-10","2022-03-11",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"2022-03-10","2022-03-12"]
[1154,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1155,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","NA"]
[1156,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","2019-03-07","2019-09-06",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"2019-03-14","2019-12-06"]
[1157,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1158,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"2018-12-06","2021-09-13"]
[1159,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1160,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1161,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1162,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1163,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"2020-12-04","2021-09-13"]
[1164,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"2019-12-09","2023-09-22",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"2020-06-10","2022-01-06"]
[1165,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","2019-12-09","2022-03-22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"2020-06-10","2022-06-20"]
[1166,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1167,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","2021-12-13","2024-06-06",0.31,"RP-230751",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751",null,94,48,null,null,"2022-01-06","2023-03-29"]
[1168,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",0.65,"RP-231461","RP-231817","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[1169,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","2022-03-15","2024-06-06",0,"RP-231461","RP-231817","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"2022-06-04","2023-09-06"]
[1170,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1171,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"2019-06-06","2021-12-10",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1172,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","2019-06-06","2020-12-11",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1173,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"2020-09-10","2022-03-12"]
[1174,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1175,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"2020-09-11","2021-06-11"]
[1176,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"2020-09-11","2021-12-13"]
[1177,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"2021-09-10","NA"]
[1178,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"2021-09-10","2022-06-04"]
[1179,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"2021-09-10","2022-03-12"]
[1180,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","2021-09-29","2024-03-03",0.56999999999999995,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"2021-09-29","NA"]
[1181,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"2021-09-29","2022-03-12"]
[1182,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"2021-09-29","2022-06-04"]
[1183,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","2023-06-08","2024-03-03",0.05,"RP-230873","RP-231826","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[1184,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"2020-09-25","2021-06-11"]
[1185,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.866999999999997,89,45,null,null,"2020-09-25","2023-03-31"]
[1186,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.500999999999998,93,47,null,null,"2021-09-10","2023-03-31"]
[1187,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"2021-03-18","2021-12-13"]
[1188,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","2021-12-13","2023-12-12",0.69,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"2022-01-06","2023-03-29"]
[1189,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"2022-01-06","2022-06-04"]
[1190,970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","2022-09-08","2023-12-12",0.62,"RP-230070","RP-231582","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[1191,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1192,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","2021-06-12","2021-06-12",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"2021-08-12","2022-03-11"]
[1193,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"2021-03-18","2022-03-11",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2021-09-13"]
[1194,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1195,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"2021-12-10","2022-06-04"]
[1196,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"2021-12-10","2022-03-12"]
[1197,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1198,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->",33.534999999999997,92,47,null,null,"2021-06-11","2022-09-12"]
[1199,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[1200,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"2022-03-10","2022-06-04"]
[1201,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","2020-12-07","2020-12-18",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-05","2020-12-05"]
[1202,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1203,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"2019-03-07","2021-09-10",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1204,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","2019-05-09","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1205,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"2020-12-05","2021-03-21"]
[1206,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1207,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1208,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"2020-12-04","2021-12-13"]
[1209,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"2020-12-04","2021-03-21"]
[1210,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","2020-12-04","2021-06-15",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"2020-12-04","2021-09-13"]
[1211,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"2021-06-11","2022-06-04"]
[1212,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100",29.548999999999999,92,47,null,null,"2021-06-11","2022-06-04"]
[1213,940018,"   Security for eSEAL ","eSEAL",2,"Rel-17","S3","2021-12-10","2021-12-10",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100",33.433999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1214,900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1215,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"2019-06-26","2021-03-19"]
[1216,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","2020-12-03","2021-06-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"2020-12-03","2021-09-13"]
[1217,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1218,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"2021-03-18","2022-06-04"]
[1219,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"2021-03-18","2021-12-13"]
[1220,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"2021-03-18","2022-03-12"]
[1221,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"2020-12-03","NA"]
[1222,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","2019-06-06","2020-12-15",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"2019-05-31","2021-03-19"]
[1223,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","2020-09-16","2022-03-11",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22",33.866,89,45,null,null,"2020-09-10","2022-03-12"]
[1224,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1225,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"2021-03-19","2021-06-11"]
[1226,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"2021-03-19","2022-06-04"]
[1227,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1228,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1229,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"2019-03-07","2022-06-10",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"2020-12-03","NA"]
[1230,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"2019-03-14","2021-12-10"]
[1231,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-12"]
[1232,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"2021-03-18","2022-07-13"]
[1233,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1234,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100",29.556999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1235,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90",29.559000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1236,920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"2021-03-18","2022-06-04"]
[1237,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"2020-09-10","2022-06-21"]
[1238,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1239,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ",33.847000000000001,88,45,null,null,"2020-06-25","2022-06-04"]
[1240,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"2021-09-10","2023-03-31"]
[1241,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1242,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","2021-03-12","2022-03-22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, h...",38.350999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1243,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1244,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"2019-09-13","2020-06-26"]
[1245,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","2019-09-19","2020-06-12",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"2019-09-13","2022-03-12"]
[1246,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"2020-09-11","2020-09-25"]
[1247,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100",24.501000000000001,89,45,null,null,"2020-09-11","2022-03-12"]
[1248,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"2020-09-11","2022-03-12"]
[1249,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"2020-09-11","2022-03-12"]
[1250,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","2020-09-17","2023-12-12",0.72,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1251,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","2020-09-17","2022-03-11",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1252,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.45,"RP-221300","RP-232258","Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm","gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222942; Rapporteur: ChinaTelecom->Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm; Rap eMail: ->gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com; 17/3/23: FCD:30/11/202.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1253,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"2017-12-15","2022-03-11",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"2019-05-31","NA"]
[1254,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","2017-12-15","2019-09-12",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"2017-12-15","2020-08-17"]
[1255,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","2019-09-19","2020-06-12",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,96,null,"2019-09-13","2022-03-22"]
[1256,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1257,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","2020-03-25","2021-06-11",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"2020-03-25","2022-03-12"]
[1258,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"2020-06-26","NA"]
[1259,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1260,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1261,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1262,890011,"Mission critical security enhancements phase 2 ","MCXSec2",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200879",null,"Woodward, Tim, Motorola Solutions, Inc, ","tim.woodward@motorolasolutions.com ","; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 80%->82; 13/12/21: 82%->100",33.18,89,45,null,null,"2020-09-11","2021-12-13"]
[1263,890070,"PAP/CHAP protocols usage in 5GS ","PAP_CHAP",1,"Rel-17","ct","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 29.561 ; 12/3/22: 99%->100",null,89,45,null,null,"2020-09-25","2022-03-12"]
[1264,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1265,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","2020-09-16","2021-03-12",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1266,890001,"Service-based support for SMS in 5GC ","SMS_SBI",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","25/9/20: WID:CP-202028->CP-202242; 10/9/21: WID:CP-202242->CP-212023",null,89,45,null,null,"2020-09-11","2021-09-10"]
[1267,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"2020-09-11","2022-03-12"]
[1268,890029,"   CT4 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35; 13/9/21: FCD:Wed 08/09/->03/22; 13/9/21: 35%->40; 1/10/21: 23.540 added;; 13/12/21: 40%->45; 12/3/22: 45%->65; 22/3/22: 29.577 added;; 22/3/22: 29.579 added;; 22/3/22:...","29.503; 29.540; 29.571; 23.540; 29.577; 29.579; 29.578",89,45,null,null,"2020-09-11","2022-08-03"]
[1269,840048,"Enhanced Relays for Energy eFficiency and Extensive Coverage ","REFEC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1270,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100",22.866,81,41,null,null,"2018-09-06","2019-12-06"]
[1271,840034,"   Stage 1 of REFEC","REFEC",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ","13/9/19: 0%->90; 6/12/19: 90%->100",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-06"]
[1272,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1273,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","2018-06-06","2019-03-14",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100",22.841999999999999,80,41,null,null,"2018-06-06","2019-05-31"]
[1274,840030,"   Stage 1 of NCIS","NCIS",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191039",null,"Ning YANG, oppo ","yangning@oppo.com ","13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1275,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","2019-06-06","2021-06-11",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"2019-05-31","2021-06-11"]
[1276,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","2020-09-16","2021-06-11",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"2020-09-10","2021-06-11"]
[1277,880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"2019-09-02","2020-12-11",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1278,850041,"   Stage 1 of MuDE","MuDE",2,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1279,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","2020-06-25","2020-12-11",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"2020-06-26","2021-06-11"]
[1280,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"2020-06-26","2021-09-10"]
[1281,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1282,880014,"   CT4 aspects of BEPoP","BEPoP",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 45%->55; 13/12/21: 55%->80; 12/3/22: 80%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1283,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","2020-06-25","2021-09-10",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"2020-06-25","2021-12-13"]
[1284,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100",23.18,84,43,null,null,"2019-05-31","2020-12-05"]
[1285,840016,"Stopped - Supporting Flexible Local Area Data Network ","FLADN",1,"Rel-17","S2","2019-06-06","2020-09-11",1,"SP-190563",null,"LG Electronics, Hyunsook Kim ","hyuns.kim@lge.com ","21/1/22: stopped at 0%; 21/1/22: 0%->100","23.501; 23.502 ",84,43,95,null,"2019-05-31","2022-01-21"]
[1286,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","2018-12-13","2022-03-11",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"2019-03-14","2022-03-12"]
[1287,860012,"Handsets Featuring Non-Traditional Earpieces","HaNTE",1,"Rel-17","S4","2019-12-06","2022-03-11",1,"SP-190989",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com","25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11 ","26.131; 26.132; 26.801",86,44,null,null,"2019-12-06","2022-03-12"]
[1288,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-03-12"]
[1289,920008,"   Stage 2 of EVEX","EVEX",2,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-06-04"]
[1290,960021,"   Stage 3 (CT3) of EVEX","EVEX",2,"Rel-17","C3","2022-06-01","2022-06-10",1,"CP-222128",null,"Waqar Zia, Qualcomm Incorporated","wzia@qti.qualcomm.com",null,"29.522; 29.517; 29.591",96,49,null,"x","2022-05-30","NA"]
[1291,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","2021-06-11","2021-09-08",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"2021-06-11","2021-12-13"]
[1292,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"2021-06-11","2022-03-12"]
[1293,920011,"8K Television over 5G ","8K_TV_5G",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210381",null,"Thomas Stockhammer ","tsto@qti.qualcomm.com ","; 13/9/21: 0%->40; 13/12/21: 40%->60; 12/3/22: 60%->100","26.955;26.925;26.511;26.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1294,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","2019-03-07","2019-03-21",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"2017-12-15","2019-03-14"]
[1295,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1296,880049,"Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON",1,"Rel-17",null,"2019-09-02","2023-03-03",1,"CP-210148",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148",22.260999999999999,85,43,null,null,"2019-09-13","2021-06-13"]
[1297,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","2019-09-02","2021-06-18",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100",22.260999999999999,85,43,null,null,"2019-09-13","2022-03-11"]
[1298,880022,"   Stage 3 (CT1) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50; 13/9/21: 50%->70; 13/9/21: FCD:Fri 18/06/->03/22; 13/12/21: 70%->92; 12/3/22: 92%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1299,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"2020-06-26","2022-03-12"]
[1300,920061,"   Stage 3 (CT6) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C6","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/9/21: 0%->70; 13/9/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100; 4/6/22: 100 ",null,92,47,null,null,"2020-06-26","2022-06-04"]
[1301,970073,"   UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON-UEConTest",2,"Rel-17","R5","2022-09-08","2023-03-03",1,"RP-222255","RP-230359","Masahiro Takano, NTT DOCOMO, INC","masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->80%; Stat Rep: ->RP-223159; Rapporteur: NTT DOCOMO->Masahiro Takano, NTT DOCOMO, INC; Rap eMail: ->masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com; 17/3/23: FCD:09/09/2023->03/03/2023; Compl:80%->100%; ...",null,97,49,null,null,"2022-09-23","2023-03-17"]
[1302,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2020-12-05"]
[1303,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","2019-09-19","2021-12-10",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2021-12-13"]
[1304,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1305,910047,"   Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",2,"Rel-17","S3","2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 24/3/22: 0%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2021-03-19","2022-03-24"]
[1306,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"2019-09-13","NA"]
[1307,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[1308,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","2019-09-13","2019-12-12",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"2019-09-13","2019-12-06"]
[1309,920062,"   Stage 2 of MINT","MINT",2,"Rel-17","S2","2021-08-12","2021-12-10",1,"SP-210582",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","13/9/21: 0%->50; 10/12/21: 50%->90; 12/3/22: 90%->98; 4/6/22: 98%->100","23.501; 23.502 ",92,47,null,null,"2021-08-12","2022-06-04"]
[1310,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","2020-12-07","2021-03-12",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"2020-12-05","2021-09-13"]
[1311,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","NA"]
[1312,930049,"      CT1 aspects of MINT","MINT",3,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 13/12/21: 0%->50; 12/3/22: 50%->85; 4/6/22: 85%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1313,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-20"]
[1314,930048,"      CT6 aspects of MINT","MINT",3,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->100; 4/6/22: 100%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1315,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","2022-03-10","2022-03-11",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100",33.500999999999998,95,48,null,null,"2022-03-10","2022-03-22"]
[1316,860008,"IMS emergency support for Stand-alone Non-Public Network (SNPN)","IESNPN",1,"Rel-17","S1","2019-12-06","2019-12-13",1,"SP-191038",null,"Wong, Curt; ","curt.wong@charter.com ","6/12/19: 0%->100","22.101; 22.261; 22.228 ",86,44,null,null,"2019-12-06","2019-12-06"]
[1317,870023,"Management of non-public networks (NPN)","OAM_NPN",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200189",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21; 13/9/21: 50%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->100","28.541; 28.531; 28.533; 28.552; 28.554 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1318,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","2019-12-06","2021-06-11",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"2019-12-06","2021-12-13"]
[1319,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"2020-03-25","2020-06-26"]
[1320,890013,"   eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) ","SCAS_5G_NSSAAF",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200720",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->100","33.926; 33.326",89,45,null,null,"2020-09-11","2021-09-13"]
[1321,870017,"   eSCAS_5G for Non-3GPP InterWorking Function","SCAS_5G_N3IWF",2,"Rel-17","S3","2020-03-25","2021-12-10",1,"SP-200146",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->100","33.926; 33.520",87,44,null,null,"2020-03-25","2021-12-13"]
[1322,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"2020-03-25","2022-06-04"]
[1323,870019,"   eSCAS_5G for Service Communication Proxy","SCAS_5G_SECOP",2,"Rel-17","S3","2020-03-25","2022-06-09",1,"SP-200148",null,"Wei Lu, Nokia","wei.lu@nokia-sbell.com","26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 70%->95; 12/3/22: 95%->95; 12/3/22: FCD:10/12/2021->06/22; 31/3/23: 95%->100","33.522; 33.926",87,44,null,null,"2020-03-25","2023-03-31"]
[1324,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"2020-06-25","2021-09-13"]
[1325,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2020-06-28"]
[1326,870016,"   Stage 2 aspects of enh3MCPTT","enh3MCPTT",2,"Rel-17","S6","2020-03-25","2021-06-15",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-06-11"]
[1327,900039,"   Stage 3 aspects of enh3MCPTT","enh3MCPTT-CT",2,"Rel-17","C1","2020-09-14","2021-09-08",1,"CP-202188",null,null,null,"; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48; 13/12/21: 48%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1328,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","2019-06-06","2021-12-10",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"2019-05-31","2022-03-12"]
[1329,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","2018-12-13","2021-03-12",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"2018-12-06","2021-06-11"]
[1330,890012,"Enhancements to User Plane Integrity Protection Support in 5GS ","eUPIP_SEC",1,"Rel-17","S3","2020-09-16","2021-03-12",1,"SP-200719",null,"Anand Palanigounder, Qualcomm Incorporated ","apg@qti.qualcomm.com ","; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100",33.500999999999998,89,45,null,null,"2020-09-11","2021-03-19"]
[1331,950040,"Non-Seamless WLAN offload in 5GS ","NSWO_5G",1,"Rel-17","S3","2021-05-25","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ",null,33.500999999999998,95,48,null,null,"2021-12-10","NA"]
[1332,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","2021-05-25","2021-09-08",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"2021-05-25","2022-06-04"]
[1333,940011,"   Security aspects of NSWO","NSWO_5G",2,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ","; 12/3/22: FCD:12/12/2021->3/22; 12/3/22: 0%->100",33.500999999999998,94,48,null,null,"2021-12-10","2022-03-12"]
[1334,950041,"   CT1 aspects of NSWO","NSWO_5G",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 22/3/22: 0%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-03-22"]
[1335,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1336,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1337,990122,"Lawful Interception Rel-17 ","LI17",1,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1338,860025,"   Lawful Interception Rel-17 general aspects","LI17",2,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1339,990120,"   (IETF) PASSporT Extension for Rich Call Data (draft-ietf-stir-passport-rcd)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1340,990121,"   (IETF) Messaging Use Cases and Extensions for STIR (draft-ietf-stir-messaging)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1341,850047,"(Small) Technical Enhancements and Improvements for Rel-17","TEI17",1,"Rel-17",null,"2020-03-11","2022-03-11",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,85,43,null,null,"2015-06-15","2015-06-15"]
[1342,940047,"   IMS Optimization for HSS Group ID in an SBA environment (St. 2)","TEI17_IMSGID",2,"Rel-17","S2","2020-03-11","2022-03-11",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1343,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1344,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","2020-03-11","2022-03-11",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100",24.228999999999999,94,48,null,null,"2021-12-10","2022-03-12"]
[1345,910044,"   Same PCF Selection For AMF and SMF ","TEI17_SPSFAS",2,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ",null,null,88,45,null,null,"2020-06-25","NA"]
[1346,880016,"      Stage 2 for TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ","23.501, 23.502 ; 19/3/21: 0%->100",null,88,45,null,null,"2020-06-25","2021-03-19"]
[1347,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1348,910045,"         CT3 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C3","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184; 13/9/21: 98%->100",29.513000000000002,91,46,null,null,"2021-03-18","2021-09-13"]
[1349,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"2021-03-18","2021-09-13"]
[1350,930036,"   System enhancement for Redundant PDU Session ","TEI17_SE_RPS",2,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1351,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1352,930001,"      CT aspects of TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ",null,"24.501; 24.526; 27.007; 29.513; 29.525; 29.561; 29.502 ",93,47,null,null,"2021-09-10","NA"]
[1353,930037,"         CT1 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","24.501; 24.526; 27.007",93,47,null,null,"2021-09-10","2021-12-13"]
[1354,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"2021-09-10","2022-03-12"]
[1355,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100",29.501999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[1356,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"2020-03-25","2021-09-10",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1357,870004,"      Stage 2 for TEI17_SAPES","TEI17_SAPES",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ","19/3/21: 0%->100","23.228; 23.167",87,44,null,null,"2020-06-10","2021-03-19"]
[1358,910020,"      CT aspects on TEI17_SAPES","TEI17_SAPES",3,"Rel-17","ct","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ",null,"24.229; 29.165 ",91,46,null,null,"2021-03-19","NA"]
[1359,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1360,910080,"         CT3 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1361,910081,"   Dynamically Changing AM Policies in the 5GC ","TEI17_DCAMP",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,null,null,87,44,null,null,"2020-06-10","NA"]
[1362,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"2020-06-10","2021-03-19"]
[1363,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1364,910082,"         CT3 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: 0%->30; 13/9/21: 30%->50; 13/12/21: 50%->75; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1365,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1366,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"2020-06-10","2021-03-19"]
[1367,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"2020-06-10","NA"]
[1368,870007,"      Stage 2 for TEI17_GEM ","TEI17_GEM",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com","11/6/21: 0%->100",23.681999999999999,87,44,null,null,"2020-06-10","2021-06-11"]
[1369,910010,"      CT aspects on TEI17_GEM ","TEI17_GEM",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: WID:CP-210185->CP-211195; 10/9/21: WID:CP-211195->CP-212165","29.122 29.336 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1370,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1371,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1372,920041,"   Support of different slices over different Non 3GPP access ","TEI17_N3SLICE",2,"Rel-17",null,"2020-03-11","2021-06-18",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1373,870008,"      Stage 2 for TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1374,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-10-01"]
[1375,920001,"      CT4 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C4","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-06-11"]
[1376,910087,"   N7/N40 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",2,"Rel-17",null,"2020-03-11","2021-09-10",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1377,870009,"      Stage 2 for TEI17_NIESGU","TEI17_NIESGU",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ","11/6/21: 0%->100","23.060; 23.401; 23.503; 23.203 ",87,44,null,null,"2020-06-10","2021-06-11"]
[1378,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1379,910011,"      CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194; 13/9/21: 90%->100","29.512; 29.513 ",91,46,null,null,"2021-03-19","2021-09-13"]
[1380,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"2021-03-19","2021-09-13"]
[1381,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","2021-12-10","2022-03-22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"2022-04-21","NA"]
[1382,880019,"Stage-3 5GS NAS protocol development 17 ","5GProtoc17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","NA"]
[1383,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1384,880045,"   Stage-3 5GS NAS protocol development 17 non-IETF aspects","5GProtoc17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","1/10/21: 0%->70; 23/9/22: 70%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","2022-09-23"]
[1385,880021,"Stage-3 SAE Protocol Development ","SAES17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1386,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1387,880047,"   Stage-3 SAE Protocol Development CSFB aspects","SAES17-CSFB",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1388,880048,"   Stage-3 SAE Protocol Development non 3GPP aspects","SAES17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1389,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","2020-06-25","2023-09-22",0.92,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"2020-06-26","2021-03-21"]
[1390,880023,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 20%->40; 13/9/21: 40%->60; 13/12/21: 60%->80; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 80%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1391,911035,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 0%->60; 13/9/21: 60%->70; 13/12/21: 70%->85; 12/3/22: 85%->100; 12/3/22: FCD:10/09/2021->3/22","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1392,1000055,"   UE Conformance - IMS Data Channel ","IMSProtoc17_dataCH-UEContest",2,"Rel-17","R5","2023-06-07","2023-09-22",0.05,"RP-231246","RP-232356","Zhaobing Yang, Huawei Technologies. Co., Ltd","yangzhaobing@hisilicon.com","6/9/23: FCD:12/12/2023->22/09/2023; Compl:0%->5%; Stat Rep: ->RP-232356; Rapporteur: HiSilicon->Zhaobing Yang, Huawei Technologies. Co., Ltd; Rap eMail: ->yangzhaobing@hisilicon.com; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[1393,880032,"Packet Flow Description (PFD) management enhancement ","pfdManEnh",1,"Rel-17","C3","2020-06-25","2021-06-11",1,"CP-210183",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100","29.251; 29.551 ",88,45,null,null,"2020-06-26","2021-06-11"]
[1394,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1395,880053,"   CT3 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088; 13/9/21: 65%->75; 13/12/21: 75%->85; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 85%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1396,880054,"   CT4 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50; 13/9/21: 50%->60; 13/12/21: 60%->80; 13/12/21: FCD:Mon 20/09/->03/22; 12/3/22: 80%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1397,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1398,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1399,970052,"   CT3 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C3","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1400,970053,"   CT4 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1401,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","2021-12-10","2022-06-10",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1402,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1403,820009,"Study on authentication enhancements in 5GS","FS_AUTH_ENH",1,"Rel-17","S3","2018-12-13","2021-12-10",1,"SP-190713",null,"Tsiatsis, Vlasios, ","vlasios.tsiatsis@ericsson.com ","07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202 ","new",82,42,null,null,"2018-12-06","2022-03-12"]
[1404,940012,"Authentication enhancements in 5GS ","AUTH_ENH",1,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211360",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 24/3/22: 0%->100",33.101999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1405,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"2022-03-10","2022-03-12"]
[1406,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"2022-03-10","2022-06-20"]
[1407,990004,"Update of conformance test specifications to Rel-17","UEConTest_R17",1,"Rel-17","C6","2021-06-14","2024-06-14",0.05,"CP-230022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com","Tests eV2XARC_Ph2;eCPSOR_CON;5G_ProSe;5GSAT_ARCH-CT;ING_5GS;MINT;NSWO_5G;ARCH_NR_REDCAP;IoT_SAT_ARCH_EPS","31.121; 31.124",92,47,null,null,"2021-08-12","NA"]
[1408,0,"Rel-17 Management-only Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1409,900021,"Management Aspects of 5G Network Sharing ","MANS",1,"Rel-17","S5","2020-12-04","2022-03-11",1,"SP-201080",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25; 13/9/21: 25%->30; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 30%->60; 12/3/22: 60%->100",null,90,46,null,null,"2020-12-04","2022-03-12"]
[1410,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","2021-06-11","2021-12-10",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"2021-06-11","2021-12-13"]
[1411,910030,"File Management ","FIMA",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210135",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 11/6/21: 0%->25; 13/9/21: 25%->60; 13/12/21: 60%->75; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 75%->100","28.537; 28.622; 28.623; 28.532 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1412,930032,"Improved support for NSA in the service-based management architecture ","NSA_SBMA",1,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-211121",null,"Lan Zou, Huawei ","zoulan@huawei.com ",null,"28.623; 28.622; 28.659; 28.663 ",91,46,null,null,"2021-09-10","NA"]
[1413,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1414,880029,"Enhancement of Handover Optimization ","E_HOO",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200466",null,"Elmdahl, Per, Ericsson ","per dot Elmdahl at Ericsson dot com ","28.552; 28.313; 28.541 ; 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:18/06/2021->03/22; 11/6/21: 10%->30; 13/9/21: 30%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1415,880028,"Management data collection control and discovery ","MADCOL",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200465",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30; 13/9/21: 30%->35; 13/9/21: FCD:Wed 22/09/->03/22; 13/12/21: 35%->40; 12/3/22: 40%->45; 4/6/22: 45%->100",null,88,45,null,null,"2020-06-26","2022-06-04"]
[1416,880026,"Management of the enhanced tenant concept ","eMEMTANE",1,"Rel-17","S5","2020-06-26","2021-12-15",1,"SP-220293",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->20; 12/3/22: 20%->100; 22/3/22: WID:SP-200463->SP-220293",null,88,45,null,null,"2020-06-26","2022-03-22"]
[1417,880025,"Enhancements of 5G performance measurements and KPIs ","ePM_KPI_5G",1,"Rel-17","S5","2020-06-12","2022-03-11",1,"SP-200462",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","28.552; 32.425; 28.554; 32.426; 32.450; 32.451; 32.455 ; 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->40; 11/6/21: 40%->50; 13/9/21: 50%->60; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1418,810027,"Intent driven management service for mobile network","IDMS_MN",1,"Rel-17","S5","2018-09-06","2022-03-11",1,"SP-180899",null,"Zou Lan, Huawei ","zoulan@huawei.com","7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[1419,820035,"Discovery of management services in 5G ","5GDMS",1,"Rel-17","S5","2018-12-13","2022-03-11",1,"SP-200770",null,"Brendan Hassett, Huawei Technologies Sweden AB ","brendan.t.hassett@huawei.com","¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ","28.533; 28.532; 28.531 ",82,42,null,null,"2018-12-07","2022-03-12"]
[1420,860024,"Network policy managementfor 5G mobile networks ","NPM",1,"Rel-17","S5","2019-12-06","2022-03-11",1,"SP-191211",null,"China Mobile Shasha Guo ","guoshasha@chinamobile.com ","; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75; 13/9/21: 75%->78; 13/12/21: 78%->100","28.532; 28.541 ",86,44,null,null,"2019-12-06","2021-12-13"]
[1421,850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","2019-09-19","2021-03-12",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"2019-09-13","2021-03-21"]
[1422,940078,"Enhancements of Management Data Analytics Service ","eMDAS",1,"Rel-17","S5","2021-03-18","2021-12-10",1,"SP-210132",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 13/9/21: 0%->10; 13/9/21: FCD:Fri 10/12/->12/21; 13/12/21: 10%->45. UID was at 0, corrected; 12/3/22: 45%->65; 4/6/22: 65%->100","28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533; 28.105",91,46,null,null,"2021-03-18","2022-06-04"]
[1423,870022,"Enhancements on EE for 5G networks ","EE5GPLUS",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200188",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->55; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->70; 13/12/21: 70%->100","28.310; 28.552; 28.554; 28.541 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1424,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"2019-12-06","2021-12-13"]
[1425,870024,"Enhancement on Management Aspects of 5G Service-Level Agreement ","EMA5SLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-210860",null,"SHI, Xiaonan, CMCC ","shixiaonan@chinamobile.com ","; 13/9/20: 0%->5; 5/12/20: 5%->40; 21/3/21: 40%->60; 21/3/21: FCD:18/03/2021->06/21; 11/6/21: 60%->65; 11/6/21: FCD:Fri 11/06/->12/21; 10/9/21: WID:SP-200190->SP-210860; 13/9/21: 65%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85 ","28.541; 28.531 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1426,870025,"Management of MDT enhancement in 5G ","e_5GMDT",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200191",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75; 13/9/21: 75%->85; 13/12/21: 85%->95; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 95%->100","32.421; 32.422; 32.423; 28.622; 28.623; 28.523 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1427,870026,"Additional NRM features ","adNRM",1,"Rel-17","S5","2020-02-05","2022-03-11",1,"SP-200192",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com","; 10/6/20: FCD:19/03/2020->06/20; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->30; 13/9/21: 30%->50; 13/9/21: FCD:Tue 15/06/->12/21; 13/12/21: 50%->80; 13/12/21: FCD:Fri 10/12/->03/22; 01/22: rapporteur change from Jing Ping; 12/3/22: 80%->100","28.540; 28.541; 28.622; 28.623 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1428,870030,"Enhanced Closed loop SLS Assurance ","eCOSLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200196",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 50%->60; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->90; 4/6/22: 90%->100","28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 ",87,44,null,null,"2019-12-06","2022-06-04"]
[1429,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","2022-03-10","2022-06-10",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1430,0,"Rel-17 Other NR-only improvements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1431,860061,"Study on NR QoE (Quality of Experience) management and optimizations for diverse services","FS_NR_QoE",1,"Rel-17","R3","2019-12-16","2020-09-15",1,"RP-193256",null,"China Unicom",null,"affects: NR.; 25/9/20: 38.890 added;; 7/4/21: 0%->100",38.89,86,44,null,null,"2020-01-14","2021-04-07"]
[1432,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"2021-01-01","2024-03-03",0.56000000000000005,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"2021-06-04","2021-07-02"]
[1433,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","2021-01-01","2022-03-22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1434,970072,"   UE Conformance - NR QoE management and optimizations for diverse services ","NR_QoE-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-03",0.2,"RP-222102","RP-231734","Bo J NSSON, Ericsson","Bo[dot]jonsson[at]ericsson[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->5%; Stat Rep: ->RP-222818; Rapporteur: Ericsson->Bo J NSSON, Ericsson; Rap eMail: ->Bo[dot]jonsson[at]ericsson[dot]com; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-222818->RP-230267; ;...; 6/9/23: C...",null,97,49,null,null,"2022-09-23","2023-09-06"]
[1435,911009,"Rel-17 Power Class 2 UE for NR inter-band CA with or without SUL configurations with x (16>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL",1,"Rel-17",null,"2021-03-12","2024-06-06",0.74,"RP-221516",null,"Huawei ",null,"basket WI; TR 38.8xx ; 2/7/21: WID:RP-210543->RP-211378; 29/9/21: WID:RP-211378->RP-212182; 6/1/22: WID:RP-212182->RP-213650; 5/4/22: WID:RP-213650->RP-220701; 12/7/22: WID:RP-220701->RP-221516",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1436,911109,"   Core part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","basket WI; TR 38.8xx ; 2/7/21: 38.842 added;; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->78% ; 20/6/22: Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.com; ","38.842; 38.541",91,46,null,null,"2021-04-07","2022-06-20"]
[1437,911209,"   Stopped - Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: Stat Rep: RP-212181->RP-220699 ; 6/6/22: CD:12/06/2022->22/06/2022 ; 20/6/22:Stopped at 0%; Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.c...",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1438,1000056,"   UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-UEConTest",2,"Rel-17","R5","2023-06-08","2024-06-06",0.09,"RP-231247","RP-232358","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->9%; Stat Rep: ->RP-232358; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ",null,100,null,null,null,"2023-06-29","2023-09-06"]
[1439,911010,"Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS",1,"Rel-17",null,"2021-03-12","2023-12-12",0.83,"RP-212030",null,"Vivo ",null,"compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: WID:RP-210807->RP-211158; 29/9/21: WID:RP-211158->RP-212030; 1/10/21: 38.161 added;; ",38.161000000000001,91,46,null,null,"2021-04-07","2022-06-04"]
[1440,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","2021-03-12","2022-03-22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ",38.834000000000003,91,46,null,null,"2021-04-07","2022-06-20"]
[1441,911210,"   Perf. part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-222269","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy ; 22/3/22: Compl:0%->20%; 22/3/22: CD:08/09/2022->12/09/2022 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com s...;...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[1442,960088,"   UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.55000000000000004,"RP-221690","RP-231968","Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo","ashwin_mohan[at]apple.com, Jose.Fortes[at]rohde-schwarz.com,ruixin.wang[at]vivo.com","9/9/22: Comp...; 23/9/22: 38.561 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->9%; Stat Rep: ->RP-223197; Rapporteur: Apple->Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo; Rap eMail: ->ashwin_mohan[at]apple...",38.561,96,49,null,null,"2022-07-12","2023-09-06"]
[1443,911012,"High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79",1,"Rel-17",null,"2021-03-12","2022-12-01",1,"RP-210843",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1444,911112,"   Core part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1445,911212,"   Perf. part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1446,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-211979","RP-223061","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...; 9/12/22: FCD:23/03/2023->01/12/2022; Compl:84%->100%; Stat R...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1447,911013,"High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-210844",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1448,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1449,911213,"   Perf. part: NR_UE_PC2_n34","NR_UE_PC2_n34-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1450,930053,"   UE Conformance - High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34-UEConTest",2,"Rel-17","R5","2021-09-17","2022-06-22",1,"RP-221760","RP-221357","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n34-Core ; 6/1/22: WID:RP-211980->RP-213034; 22/3/22: Compl:0%->53% ; 20/6/22: FCD:12/09/2022->22/06/2022; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-211980->RP-221760",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1451,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"2021-03-12","2023-09-22",1,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1452,911114,"   Core part: NR_UE_PC2_n39","NR_UE_PC2_n39-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1453,911214,"   Perf. part: NR_UE_PC2_n39","NR_UE_PC2_n39-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1454,930054,"   UE Conformance - High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39-UEConTest",2,"Rel-17","R5","2021-09-17","2023-09-22",1,"RP-211981","RP-232243","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n39-Core ; 6/1/22: WID:RP-211981->RP-213035; 22/3/22: Compl:0%->47% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ...; 23/9/22: WID:RP-211981->RP-222651; 9/12/22: FCD:23/03/2023->01/0...",null,93,47,null,null,"2021-09-29","2023-09-06"]
[1455,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"2021-04-07","NA"]
[1456,911115,"   Core part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1457,911215,"   Perf. part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 6/1/22: 0%->100",null,91,46,null,null,"2021-04-07","2022-01-06"]
[1458,911006,"NR Uplink Data Compression (UDC) ","NR_UDC",1,"Rel-17",null,"2021-03-12","2023-06-06",1,"RP-220140",null,"CATT ",null,"no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core ; 2/7/21: WID:RP-210909->RP-211203; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1459,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","2021-03-12","2022-03-11",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2022-04-05"]
[1460,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221449","RP-230395","Huiying ZHANG, CATT","zhanghuiying@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%->33%; Stat Rep: ->RP-223139; Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn; 17/3/23: Compl:33%->67%; Stat Rep: RP-223139->RP-230395; ;...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1461,910097,"Study on optimizations of pi/2 BPSK uplink power in NR ","FS_NR_Opt_pi2BPSK",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-213535","RP-220136","Huawei ",null,"; 1/10/21: 38.868 added;; 6/1/22: WID:RP-210910->RP-213535 ; ",38.868000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1462,910096,"Study on band combination handling in RAN4 ","FS_NR_ENDC_combo_rules",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-211146","RP-220164","ZTE ",null,"TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC ; 2/7/21: WID:RP-210773->RP-211146; 2/7/21: 38.862 added;13/9/21: Compl:0%->50%13/9/21: CD:Sat 12/03/22->Tue 22/03/2213/9/21: Stat ",38.862000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1463,880078,"Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs","NR_MIMO_OTA",1,"Rel-17",null,"2020-06-22","2023-12-12",0.89,"RP-213101",null,"CAICT",null,"25/9/20: WID:RP-201302->RP-201800; 6/1/22: WID:RP-201800->RP-213101",null,88,45,null,null,"2020-07-28","2022-01-06"]
[1464,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"2020-07-28","2022-06-20"]
[1465,880278,"   Perf. Part: NR_MIMO_OTA","NR_MIMO_OTA-Perf",2,"Rel-17","R4","2020-06-22","2022-09-22",1,"RP-222348","RP-222634","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","; 13/9/21: Compl:0%->20%; 13/9/21: CD:Wed 15 ; 22/3/22: Compl:20%->35%; ; 6/6/22: Compl:35%->55% 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com 9/...; 23/9/22: 90%->100;...",null,88,45,null,null,"2020-07-28","2022-09-23"]
[1466,970071,"   UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs ","NR_MIMO_OTA-UEConTest",2,"Rel-17","R5","2022-09-08","2023-12-12",0.5,"RP-221939","RP-231969","Istvan Szini, Apple","Istvan@apple.com","19/10/22: 38.551 added;; 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->5%; Stat Rep: ->RP-223198; Rapporteur: Apple->Istvan Szini, Apple; Rap eMail: ->Istvan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->8%; Stat Rep: RP-223198->RP-2301.....",38.551000000000002,97,49,null,null,"2022-09-23","2023-09-06"]
[1467,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"2020-03-25","2023-12-12",0.62,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"2020-03-26","2021-01-06"]
[1468,870164,"   Core part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1469,870264,"   Perf. Part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Perf",2,"Rel-17","R4","2020-03-25","2021-03-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1470,950062,"   UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 ","NR_FR2_FWA_Bn257_Bn258-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",0.3,"RP-220424","RP-232353","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_FR2_FWA_Bn257_Bn258-Core 6/6/22: Compl:0%->5% 6/6/22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221492->RP-223221.....",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1471,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1472,880192,"   Core part: NR_bands_R17_BWs","NR_bands_R17_BWs-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221212","RP-221213","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","; 13/9/21: Compl:0%->50%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:50%->80%; 20/6/22: Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1473,880093,"Introduction of channel bandwidths 35MHz and 45MHz for NR FR1","NR_FR1_35MHz_45MHz_BW",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722; 2/7/21: WID:RP-210722->RP-211386",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1474,880193,"   Core part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1475,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1476,880097,"SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL","NR_SAR_PC2_interB_SUL_2BUL",1,"Rel-17",null,"2020-03-19","2022-09-22",1,"RP-212530",null,"China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 2/7/21: WID:RP-201584->RP-211494; 29/9/21: WID:RP-211494->RP-212530",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1477,880197,"   Core part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Core",2,"Rel-17","R4","2020-03-19","2021-09-21",1,"RP-212530","RP-211830","China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 13/9/21: Compl:0%->100%; 13/9/21: CD:Fri 19/03/21->Tue 21/09/21; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; ; 29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1478,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","2020-03-19","2022-03-21",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1479,920065,"   UE Conformance - SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL ","NR_SAR_PC2_interB_SUL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2022-09-22",1,"RP-211139","RP-221295","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_SAR_PC2_interB_SUL_2BUL-Core ; 13/9/21: Compl:0%->5%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 13/9/ ; 22/3/22: Compl:5%->23% ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinateleco...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[1480,900061,"NR coverage enhancements ","NR_cov_enh",1,"Rel-17",null,"2019-03-07","2023-12-12",0.97,"RP-211566",null,"China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 7/4/21: WID:RP-202928->RP-210855; 2/7/21: WID:RP-210855->RP-211566",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1481,860036,"   Study on on NR coverage enhancements","FS_NR_cov_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-200861",null,"China Telecom",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1482,900161,"   Core part: NR_cov_enh","NR_cov_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-11",1,"RP-211566","RP-220563","China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211826 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1483,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-12-21",1,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1484,950063,"   UE Conformance - NR coverage enhancements ","NR_cov_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",0.91,"RP-221298","RP-232253","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_cov_enh-Core ; 6/6/22: Compl:0%->5% ; 6/6/22: CD:15/06/2023->23/ ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-220576->RP-221298 ; ;...; 9/12/22: FCD:23/06...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1485,900062,"Support of reduced capability NR devices ","NR_redcap",1,"Rel-17",null,"2019-12-16","2023-12-12",0.96,"RP-220966",null,"Ericsson ",null,"follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202933->RP-210918; 2/7/21: WID:RP-210918->RP-211574; 5/4/22: WID:RP-211574->RP-220966",null,90,46,null,null,"2021-01-06","2022-04-05"]
[1486,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1487,900162,"   Core part: NR_redcap","NR_redcap-Core",2,"Rel-17","R1","2020-12-14","2022-06-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 22/ 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1488,900262,"   Perf. part: NR_redcap","NR_redcap-Perf",2,"Rel-17","R1","2020-12-14","2022-12-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap ; 22/3/22: Compl:0%->25%; 22/3/22: CD:08/09/2022- 6/6/22: Compl ; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com ...; 9/12/22: 75%->100; 9/1/23: 100%...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1489,950066,"   UE Conformance - Support of reduced capability NR devices ","NR_redcap_plus_ARCH-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",0.82,"RP-222136","RP-231547","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 WI NR_redcap-Core and CT1 REL-17 WI ARCH_NR_REDCAP 6/6/22: Compl:0%->13% ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ...; 23/9/22: WID:RP-222830->RP-222136; 9/12/22: FCD:23/06/2023->...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1490,930018,"   Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211100",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 10/12/21: 0%->100","23.501; 23.502 ",93,47,null,null,"2021-09-10","2021-12-10"]
[1491,940005,"   CT1 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","24.501; 23.122; 24.008; 24.368",94,48,null,null,"2022-01-07","2022-06-04"]
[1492,950047,"   CT3 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-221265",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: WID:CP-213081->CP-220304; 12/3/22: 0%->100; 4/6/22: WID:CP-220304->CP-221265","24.501; 23.122; 24.008; 24.368",95,48,null,null,"2022-03-12","2022-06-04"]
[1493,940100,"   CT4 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","29.571; 29.502; 29.540; 29.518; 23.008",94,48,null,null,"2022-01-07","2022-06-04"]
[1494,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"2022-01-07","2022-06-04"]
[1495,940027,"   Charging aspects of Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211428",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 12/3/22: 0%->35; 4/6/22: 35%->100","32.255; 32.298; 32.291 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1496,900064,"Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 ","NR_bands_UL_MIMO_PC3_R17",1,"Rel-17",null,"2020-12-14","2023-06-06",1,"RP-221518",null,"Huawei ",null,"basket WI ; 7/4/21: WID:RP-202819->RP-210557; 2/7/21: WID:RP-210557->RP-211380; 29/9/21: WID:RP-211380->RP-212184; 6/1/22: WID:RP-212184->RP-213137; 5/4/22: WID:RP-213137->RP-220704; 12/7/22: WID:RP-220704->RP-221518",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1497,900164,"   Core part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Core",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: Compl:0%->70%; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1498,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1499,940090,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-17","NR_bands_UL_MIMO_PC3_R17-UEConTest",2,"Rel-17","R5","2021-12-13","2023-06-06",1,"RP-220745","RP-230431","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_bands_UL_MIMO_PC3_R17; 22/3/22: Compl:0%->8%; 22/3/22: Stat Rep: ->RP-220419; 5/4/22: WID:RP-213227->RP-220745 ; 6/6/22: CD:12/09/2022->22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyu...",null,94,48,null,null,"2022-01-06","2023-06-07"]
[1500,900167,"Introduction of bandwidth combination set 4 (BCS4) for NR ","NR_BCS4-Core",1,"Rel-17","R4","2019-03-07","2022-06-22",1,"RP-202832","RP-221317","Per Lindell, Ericsson","per.lindell@ericsson.com","no Perf. part ; 20/6/22: FCD:03/06/2020->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221317; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1501,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"2020-12-14","2023-12-12",0.87,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;",37.866999999999997,90,46,null,null,"2021-01-06","2021-07-02"]
[1502,900168,"   Core part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Core",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI; TR 37.8xx ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478 ; ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1503,900268,"   Perf. part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI ; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478; 13/9/21: Stat Rep: ->RP-211833 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1504,981033,"   UE Conformance - Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17-UEConTest",2,"Rel-17","R5","2022-12-13","2023-12-12",0.55000000000000004,"RP-222948","RP-232255","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","17/3/23: FCD:12/12/2023->06/06/2023; Compl:0%->5%; Stat Rep: ->RP-230318; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; 31/3/23: FCD:06/06/2023->12/12/2023; Stat Rep: RP-230318->RP-230715; ...; 6/9/23:...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[1505,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"2020-12-14","2022-12-01",1,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"2021-01-06","NA"]
[1506,900169,"   Core part: HPUE_PC1_5_n77_n78","HPUE_PC1_5_n77_n78-Core",2,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-202912","RP-212049","Qualcomm ",null,"no Perf. part ; 13/9/21: Compl:0%->100% ; 29/9/21: 100%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1507,930055,"   UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-212581","RP-223280","Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia","jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com","tested: REL-17 WI HPUE_PC1_5_n77_n78-Core ; 22/3/22: Compl:0%->50%; ; 6/6/22: Compl:50%->61%20/6/22: Rapporteur: Verizon->Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia; Rap eMail: ->jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com; ...;...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1508,900070,"NR repeaters ","NR_repeaters",1,"Rel-17",null,"2020-12-14","2022-12-21",1,"RP-213514",null,"Qualcomm ",null,"no Perf. part ; 7/4/21: WID:RP-202927->RP-210818; 29/9/21: WID:RP-210818->RP-212129; 6/1/22: WID:RP-212129->RP-213514",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1509,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"2021-01-06","2022-06-20"]
[1510,930250,"   Perf. part: NR repeaters ","NR_repeaters-Perf",2,"Rel-17","R4","2021-09-17","2022-12-21",1,"RP-222275","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","Core part (UID=900170) started in Dec.20 while Perf. Part (UID=930250) started in 17/09/21 via revised WID RP-212129; TS 38.1??-1, TS 38.1??-2 ; 7/1/22: 38.115-2 and 38.115-1 added;; 20/6/22: FCD:17/09/2022->22/09/2022; Compl:0%->30%; WID: RP-213514->R...","38.115-2; 38.115-1",93,47,null,null,"2021-09-29","2023-01-09"]
[1511,930056,"Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC",1,"Rel-17","R4","2021-09-17","2023-09-22",0.99,"RP-221302",null,"Qualcomm ",null,"no Perf. part ; 12/7/22: WID:RP-212622->RP-221302",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1512,930156,"   Core part: Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-Core",2,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302","RP-221588","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","no Perf. Part ; 22/3/22: Compl:0%->75%; … 20/6/22: WID: RP-212622->RP-221302; Stat Rep: RP-220514->RP-221588; Rapporteur: Qualcomm->Gene Fong, Qualcomm Incorporated; Rap eMail: ->gfong@qti.qualcomm.com; ",null,93,47,null,null,"2021-09-29","2022-06-20"]
[1513,981036,"   UE Conformance - Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-UEConTest",2,"Rel-17","R5","2022-12-13","2023-09-22",1,"RP-221302","RP-232018","Kevin Wang / Jingzhou wu, Qualcomm / China Telecom","kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->52%; Stat Rep: ->RP-230101; Rapporteur: Qualcomm->Kevin Wang / Jingzhou wu, Qualcomm / China Telecom; Rap eMail: ->kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn; ...; 6/9/23: FCD:09/09/2023->22/09/2...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[1514,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"2021-09-29","2022-01-06"]
[1515,930157,"   Core part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ]; TR 36.8xx ; 7/1/22: 36.779 added ; ",36.779000000000003,93,47,null,null,"2021-09-29","2022-03-22"]
[1516,930257,"   Perf. part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ] ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1517,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-221417","RP-222802","Heng Pan, Puloli","heng.pan@puloli.com","9/9/22: Comp...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:72%->100%; Stat Rep: ->RP-222802; Rapporteur: Puloli->Heng Pan, Puloli; Rap eMail: ->heng.pan@puloli.com; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1518,930058,"High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212633",null,"China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ",null,93,47,null,null,"2021-09-29","NA"]
[1519,930158,"   Core part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1520,930258,"   Perf. part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1521,960070,"   UE Conformance - High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-222809","RP-222808","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2022; Compl:67%->100%; WID: RP-221158->RP-222809; Stat Rep: ->RP-222808; Rapporteur: ChinaUnicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1522,0,"Rel-17 NR Carrier Aggregation","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1523,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1524,881005,"NR itrabCA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R17_Intra",1,"Rel-17",null,"2016-06-09","2022-06-22",1,"RP-221319",null,"Ericsson",null,"25/9/20: WID:RP-200663->RP-201571; 6/1/21: WID:RP-201571->RP-202187; 7/4/21: WID:RP-202187->RP-210210; 2/7/21: WID:RP-210210->RP-211585; 29/9/21: WID:RP-211585->RP-211757; 6/1/22: WID:RP-211757->RP-212900; 5/4/22: WID:RP-212900->RP-220825; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1525,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1526,881205,"   Perf. Part: NR_CA_R17_Intra","NR_CA_R17_Intra-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1527,0,"   Rel-17 NR inter band Carrier Aggregation (iterbCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1528,900063,"High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1","NR_intra_HPUE_R17",1,"Rel-17",null,"2021-02-10","2022-06-22",1,"RP-221774",null,"Huawei",null,"7/4/21: WID:RP-202818->RP-210555; 29/9/21: WID:RP-210555->RP-212180; 6/1/22: WID:RP-212180->RP-213133; 5/4/22: WID:RP-213133->RP-220930; 12/7/22: WID:RP-220930->RP-221774",null,90,46,null,null,"2021-02-10","2022-07-12"]
[1529,900163,"   Core part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Core",2,"Rel-17","R4","2021-02-10","2022-06-22",1,"RP-221774","RP-221513 / 1773","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->10%; 22/3/22: CD:22/03/2022->10/06/2022 ; 20/6/22: Stat Rep: RP-221513->RP-221513 / 1773; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; ",null,90,46,null,null,"2021-02-10","2022-06-20"]
[1530,900263,"   Stopped - Perf. Part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Perf",2,"Rel-17","R4","2021-02-10","2022-06-10",1,"RP-221774","RP-220696","Huawei",null,"; 13/9/21: CD:Thu 09/12/21->Wed 22/06/22; ; 22/3/22: CD:22/06/2022->12/06/2022; 22/3/22: WID: RP-213133->RP-213132; 22/3/22: Stat Rep: RP-212179->RP-220696. 12/7/22: stopped at 0%. 0%->100",null,90,46,96,null,"2021-02-10","2022-07-12"]
[1531,881006,"NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2)","NR_CADC_R17_2BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221250",null,"ZTE",null,"25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495; 2/7/21: WID:RP-210495->RP-211058; 29/9/21: WID:RP-211058->RP-212511; 6/1/22: WID:RP-212511->RP-212887; 5/4/22: WID:RP-212887->RP-220144; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1532,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1533,881206,"   Perf. part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1534,881007,"NR iterbCA for 3 bands DL with 1 band UL","NR_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221772",null,"CATT",null,"25/9/20: WID:RP-200922->RP-201787; 6/1/21: WID:RP-201787->RP-202720; 7/4/21: WID:RP-202720->RP-210901; 2/7/21: WID:RP-210901->RP-211215; 29/9/21: WID:RP-211215->RP-212239; 6/1/22: WID:RP-212239->RP-213299; 5/4/22: WID:RP-213299->RP-220738; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1535,881107,"   Core part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1536,881207,"   Perf. part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: CD:15/09/2021->12/06/2022; 22/3/22: Stat Rep: ->RP-220737 ; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1537,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1538,881108,"   Core part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1539,881208,"   Perf. part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1540,881009,"NR iterbCA for 4 bands DL with 1 band UL","NR_CA_R17_4BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221321",null,"Ericsson",null,"25/9/20: WID:RP-200665->RP-201573; 6/1/21: WID:RP-201573->RP-202189; 7/4/21: WID:RP-202189->RP-210760; 2/7/21: WID:RP-210760->RP-211171; 29/9/21: WID:RP-211171->RP-211759; 6/1/22: WID:RP-211759->RP-212902; 5/4/22: WID:RP-212902->RP-220827; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1541,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1542,881209,"   Perf. part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1543,881010,"NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands","NR_CADC_R17_4BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221396",null,"Samsung",null,"25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802; 2/7/21: WID:RP-210802->RP-211194; 29/9/21: WID:RP-211194->RP-212110; 6/1/22: WID:RP-212110->RP-213111; 5/4/22: WID:RP-213111->RP-220676; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1544,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1545,881210,"   Perf. part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","; 13/9/21: Compl:0%->70%; ; 22/3/22: Compl:70%->90%; 20/6/22: Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1546,881011,"NR iterbCA for 5 bands DL with x bands UL (x=1, 2)","NR_CADC_R17_5BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221510",null,"Huawei",null,"25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561; 2/7/21: WID:RP-210561->RP-211373; 29/9/21: WID:RP-211373->RP-212176; 6/1/22: WID:RP-212176->RP-213129; 5/4/22: WID:RP-213129->RP-220692; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1547,881111,"   Core part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3/22: 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1548,881211,"   Perf. part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1549,890054,"Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)","NR_PC2_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-09-17","2023-12-12",0.83,"RP-221866",null,"China Telecom ",null,"basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 6/1/21: WID:RP-202102->RP-202373; 7/4/21: WID:RP-202373->RP-210476; 2/7/21: WID:RP-210476->RP-211131; 2/7/21: 38.841 added;; 29/9/21: WID:RP-211131->RP-211831; 6/1/22: WID:RP...",38.841000000000001,89,45,null,null,"2020-09-25","2022-07-12"]
[1550,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1551,890254,"   Perf. part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI ; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211131->RP-202102 RP-202373 RP-210476 RP-211131; 13/9/21: Stat Rep: ->RP-211832; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: WID: RP-213649->RP‑213649; 22/3/22: Stat Rep: RP-211832-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1552,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2023-12-12",0.6,"RP-211140","RP-232252","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...;...",null,92,47,null,null,"2021-07-02","2023-09-06"]
[1553,0,"Rel-17 NR and LTE","-",1,"Rel-17",null,"2020-03-25","2020-09-15",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1554,920072,"LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip","RP-211995","CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 13/9/21: Compl:0%->100% ; ",null,92,47,null,null,"2021-07-02","2021-09-13"]
[1555,920172,"   Core part: LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core",2,"Rel-17","R4","2021-06-15","2021-12-15",1,"RP-211996",null,"CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 29/9/21: WID:RP-211509->RP-211996",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1556,940089,"   UE Conformance - LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest",2,"Rel-17","R5","2021-12-13","2022-03-11",1,"RP-213036","RP-220625","CMCC",null,"tested: REL-17 WI DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1557,920073,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795",null,"Nokia ",null,"this is not a basket WI ; 29/9/21: WID:RP-211571->RP-212533; 6/1/22: WID:RP-212533->RP-213106; 5/4/22: WID:RP-213106->RP-220767; 12/7/22: WID:RP-220767->RP-221795",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1558,920173,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; …; 7/1/22: 37.828 and 37.828 added;; 22/3/22: Compl:0%->50% ; 20/6/22: Compl:50%->100%; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail...","37.828; 37.828",92,47,null,null,"2021-07-02","2022-06-20"]
[1559,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","2021-09-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1560,920074,"Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524",null,"Huawei ",null,"basket WI; TR 37.717-11-41 ; 29/9/21: WID:RP-211592->RP-212606; 6/1/22: WID:RP-212606->RP-213142; 5/4/22: WID:RP-213142->RP-220712; 12/7/22: WID:RP-220712->RP-221524",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1561,920174,"   Core part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI; TR 37.717-11-41 ; 20/6/22: FCD:15/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221523; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1562,920274,"   Perf. part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Perf",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI ; 22/3/22: Compl:0%->15%; 22/3/22: CD:15/03/2022->10/06/2022; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1563,911019,"Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths","ENDC_R17_1BLTE_1BNR_MSD",1,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part; 2/7/21: WID:RP-210891->RP-211384; 29/9/21: WID:RP-211384->RP-212187; 6/1/22: WID:RP-212187->RP-213140; 5/4/22: WID:RP-213140->RP-220709",null,91,46,null,null,"2021-04-09","2022-04-05"]
[1564,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"2021-04-09","2022-06-20"]
[1565,930259,"   Stopped - Perf. Part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Perf",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon ",null,"4/6/22: Stopped at 70%. This Perf. part is not needed",null,93,47,96,null,"2022-03-13","2022-06-04"]
[1566,911011,"Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR",1,"Rel-17",null,"2021-03-12","2023-12-12",0.56000000000000005,"RP-221322",null,"Ericsson ",null,"basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: WID:RP-210816->RP-211172; 29/9/21: WID:RP-211172->RP-211760; 6/1/22: WID:RP-211760->RP-213467; 5/4/22: WID:RP-213467->RP-220828; 12/7/22: WID:RP-220...",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1567,911111,"   Core part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: 37.827 added; ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; List of Impacted TS & TR updated; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1568,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1569,930051,"   UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR-UEConTest",2,"Rel-17","R5","2021-09-17","2023-12-12",0.06,"RP-230082","RP-231733","Jakub KOLODZIEJ, Ericsson","Jakub[dot]kolodziej[at]ericsson[dot]com","tested: REL-17 WI ENDC_PC2_R17_xLTE_yNR ; 22/3/22: Compl:0%->5%; 22/3/22: CD:15/12/2022->12/12/2022; 22/3/22 6/6/22: CD:12/12/2022->22/12/2022 ; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Ericsson; Rap eMail: ->Leif[dot]mattisson[at]ericsson[d...",null,93,47,null,null,"2021-09-29","2023-09-06"]
[1570,911018,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC ","LTE_NR_Simult_RxTx",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-221521",null,"Huawei ",null,"; 2/7/21: WID:RP-210890->RP-211382; 5/4/22: WID:RP-211382->RP-220707; 12/7/22: WID:RP-220707->RP-221521",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1571,911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",38.838999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1572,911218,"   Stopped - Perf. part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 6/6/22: Compl:70%->0%6/6/22: CD:22/03/2022->22/06/20226/6/22: WID: RP-220707->RP-2113826/6/22: Stat Rep: RP-212185->RP-221520; 20/6/22: Compl:0%->100%; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; Sto",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1573,890052,"Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) ","DC_R17_5BLTE_1BNR_6DL2UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220672",null,"Samsung ",null,"basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801; 2/7/21: WID:RP-210801->RP-211195; 6/1/22: WID:RP-211195->RP-213112; 5/4/22: WID:RP-213112->RP-220672",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1574,890152,"   Core part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI; TR 37.717-51-11 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1575,890252,"   Perf. part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1576,890053,"Rel-17 Dual Connectivity (DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) ","DC_R17_xBLTE_2BNR_yDL3UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220674",null,"Samsung ",null,"basket WI; TR 37.717-21-22 ; 6/1/21: WID:RP-201643->RP-202542; 5/4/22: WID:RP-202542->RP-220674",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1577,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1578,890253,"   Perf. part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1579,880080,"Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band","NR_LTE_V2X_PC5_combos",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-213297",null,"CATT",null,"25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588; 6/1/22: WID:RP-210588->RP-213297",37.875,88,45,null,null,"2020-07-28","2022-01-06"]
[1580,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1581,880280,"   Perf. part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->9 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1582,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"2020-06-22","2023-06-06",1,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1583,880194,"   Core part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3/2 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1584,880294,"   Perf. part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1585,911000,"   UE Conformance - ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-UEConTest",2,"Rel-17","R5","2021-03-12","2023-06-06",1,"RP-211420","RP-230698","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 basket WI ENDC_UE_PC2_R17_NR_TDD-Core ; 2/7/21: WID:RP-210401->RP-211420; 2/7/21: 0%->10 ; ; 6/6/22: Com ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ; ;...; 9/12/22: FCD:23/03/2023->01...",null,91,46,null,null,"2021-04-07","2023-06-07"]
[1586,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1587,880195,"   Core part: DSS_LTE_B38_NR_Bn38","DSS_LTE_B38_NR_Bn38-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1588,880096,"LTE/NR spectrum sharing in Band 40/n40","DSS_LTE_B40_NR_Bn40",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: WID:RP-201362->RP-202084",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1589,880196,"   Core part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1590,880296,"   Perf. part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Perf",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1591,880098,"Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_1BLTE_1BNR_2DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221257",null,"CHTTL",null,"25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204; 2/7/21: WID:RP-210204->RP-211162; 29/9/21: WID:RP-211162->RP-212096; 6/1/22: WID:RP-212096->RP-213060; 5/4/22: WID:RP-213060->RP-220398; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1592,880198,"   Core part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: Compl:0%->75%; ; 22/3/22: Compl:75%->90%; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1593,880298,"   Perf. part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:0%->90%; ; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1594,880099,"Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_2BLTE_1BNR_3DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221508",null,"Huawei",null,"25/9/20: WID:RP-201369->RP-202060; 6/1/21: WID:RP-202060->RP-202613; 7/4/21: WID:RP-202613->RP-210559; 2/7/21: WID:RP-210559->RP-211371; 29/9/21: WID:RP-211371->RP-212174; 6/1/22: WID:RP-212174->RP-213127; 5/4/22: WID:RP-213127->RP-220689; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1595,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1596,890263,"   Perf. part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-17","R4","2020-09-16","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221507; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1597,881000,"Dual Connectivity (DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_3BLTE_1BNR_4DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221320",null,"Ericsson",null,"25/9/20: WID:RP-201370->RP-201572; 6/1/21: WID:RP-201572->RP-202188; 7/4/21: WID:RP-202188->RP-210211; 2/7/21: WID:RP-210211->RP-211170; 29/9/21: WID:RP-211170->RP-211758; 6/1/22: WID:RP-211758->RP-212901; 5/4/22: WID:RP-212901->RP-220826; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1598,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1599,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1600,881001,"Dual Connectivity (DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_4BLTE_1BNR_5DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221073",null,"Nokia",null,"25/9/20: WID:RP-201371->RP-201483; 6/1/21: WID:RP-201483->RP-202590; 7/4/21: WID:RP-202590->RP-210766; 2/7/21: WID:RP-210766->RP-211319; 29/9/21: WID:RP-211319->RP-212532; 6/1/22: WID:RP-212532->RP-213251; 5/4/22: WID:RP-213251->RP-220999; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1601,881101,"   Core part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1602,881201,"   Perf. part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1603,881002,"Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R17_xBLTE_2BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221182",null,"LG Electronics",null,"25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202; 2/7/21: WID:RP-210202->RP-211043; 29/9/21: WID:RP-211043->RP-211750; 6/1/22: WID:RP-211750->RP-212876; 5/4/22: WID:RP-212876->RP-220302; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1604,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1605,881202,"   Perf. part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1606,881003,"Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL)","DC_R17_xBLTE_yBNR_3DL3UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221232",null,"ZTE",null,"25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344; 2/7/21: WID:RP-210344->RP-211054; 29/9/21: WID:RP-211054->RP-211803; 6/1/22: WID:RP-211803->RP-212883; 5/4/22: WID:RP-212883->RP-220202; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1607,881103,"   Core part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1608,881203,"   Perf. part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1609,881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1610,881104,"   Core part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1611,881204,"   Perf. part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1612,881012,"band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R17",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221512",null,"Huawei",null,"25/9/20: WID:RP-201026->RP-201726; 6/1/21: WID:RP-201726->RP-202611; 7/4/21: WID:RP-202611->RP-210563; 2/7/21: WID:RP-210563->RP-211375; 29/9/21: WID:RP-211375->RP-212178; 6/1/22: WID:RP-212178->RP-213131; 5/4/22: WID:RP-213131->RP-220695; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1613,881112,"   Core part: NR_SUL_combos_R17","NR_SUL_combos_R17-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1614,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1615,900056,"UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2023-12-12",0.11,"RP-231237","RP-232350","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 basket WIs: NR_CA_R17_Intra, NR_CADC_R17_2BDL_xBUL, NR_CA_R17_3BDL_1BUL, NR_CADC_R17_3BDL_2BUL, NR_CA_R17_4BDL_1BUL, NR_CADC_R17_4BDL_2BUL, NR_CADC_R17_5BDL_xBUL, NR_SUL_combos_R17, DC_R17_1BLTE_1BNR_2DL2UL, DC_R17_2BLTE_1BNR_3DL2UL, DC_...",null,90,46,null,null,"2021-01-06","2023-09-06"]
[1616,0,"Rel-17 NR new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1617,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1618,911116,"   Core part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Core",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP‑211495","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 1/10/21: 38.853 added;; 22/3/22: Compl:0 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->95%; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wen...",38.853000000000002,91,46,null,null,"2021-04-07","2022-09-09"]
[1619,911216,"   Perf. part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221768","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","; 22/3/22: Compl:0%->90% ; 20/6/22: FCD:22/03/2023->22/06/2022; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wendler, UIC; Rap eMail: ->ingo dot wendler at sbb dot ch; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1620,911017,"Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_1900MHz_TDD",1,"Rel-17",null,"2021-03-12","2022-03-11",1,"RP-211542",null,"Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 2/7/21: WID:RP-210879->RP-211542",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1621,911117,"   Core part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Core",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 1/10/21: 38.852 added ; ",38.851999999999997,91,46,null,null,"2021-04-07","2022-03-22"]
[1622,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1623,860041,"Extending current NR operation to 71GHz","NR_ext_to_71GHz",1,"Rel-17","R1","2019-12-16","2023-03-03",0.99,"RP-222656",null,"Qualcomm",null,"affects: NR.; 25/9/20: WID:RP-193229->RP-201845; 6/1/21: WID:RP-201845->RP-202925; 7/4/21: WID:RP-202925->RP-210862; 2/7/21: WID:RP-210862->RP-211584; 29/9/21: WID:RP-211584->RP-212637; 6/1/22: WID:RP-212637->RP-213540; 23/9/22: WID:RP-213540->RP-222656",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1624,860141,"   Core part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Core",2,"Rel-17","R1","2019-12-16","2022-09-22",1,"RP-222656","RP-222655","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: Compl:0%->45%; ; 22/3/22: Compl:45%->90%; 20/6/22: Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation; Rap eMail: ->jingsun@qti.qualcomm.com; ...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1625,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","2019-12-16","2023-03-03",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1626,860037,"Study on supporting NR from 52.6 GHz to 71 GHz","FS_NR_52_to_71GHz",1,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-201838",null,"Intel",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193259->RP-200902; 25/9/20: WID:RP-200902->RP-201838; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1627,870060,"Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz","FS_NR_IMT_param",1,"Rel-17","R4","2020-03-25","2020-12-15",1,"RP-202276",null,"Ericsson",null,"affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1628,870063,"Introduction of NR band n13","NR_n13",1,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx",null,87,44,null,null,"2020-03-26","NA"]
[1629,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1630,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1631,880082,"Introduction of NR 47GHz band","NR_47GHz_band",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"RP-212528","RP-211772","Ericsson",null,"7/4/21: WID:RP-201232->RP-210827; 2/7/21: WID:RP-210827->RP-211568; 13/9/21: C ",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1632,880182,"   Core part: Introduction of NR 47GHz band","NR_47GHz_band-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"2/7/21: 0%->100; 29/9/21: WID:RP-211568->RP-212528",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1633,880282,"   Perf. part: Introduction of NR 47GHz band","NR_47GHz_band-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1634,880084,"Introduction of NR band 24","NR_band_n24",1,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: WID:RP-201357->RP-211505",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1635,880184,"   Core part: Introduction of NR band 24","NR_band_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1636,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1637,890050,"Introduction of 6GHz NR licensed bands ","NR_6GHz",1,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504",null,"Huawei ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844; 6/1/22: WID:RP-202844->RP-213696; 5/4/22: WID:RP-213696->RP-220686; 12/7/22: WID:RP-220686->RP-221504",null,89,45,null,null,"2020-09-25","2022-07-12"]
[1638,890150,"   Core part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 22/3/22: Compl:0%->35% ; 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->l...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1639,890250,"   Perf. part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Perf",2,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Fri 17/06/22->Wed 22/06/22 ; 22/3/22: Compl:0%->20%; 2 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->...",null,89,45,null,null,"2020-09-25","2022-09-09"]
[1640,920075,"Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full",1,"Rel-17","R4","2021-06-15","2022-06-15",0.43,"RP-213683",null,"Apple ",null,"in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 29/9/21: WID:RP-211602->RP-212302; 6/1/22: WID:RP-212302->RP-213683",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1641,920175,"   Core part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Core",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-212683","RP-220450","Alexander Sayenko","asayenko@apple.com","in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 20/6/22: FCD:15/03/2022->22/03/2022; Compl:0%->100%; WID: RP-213683->RP-212683; Stat Rep: ->RP-220450; Rapporteur: Apple->Al...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1642,920275,"   Perf. part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Perf",2,"Rel-17","R4","2021-06-16","2022-06-15",0,"RP-213683",null,"Apple ",null,null,null,92,47,null,null,"2021-07-02","NA"]
[1643,890051,"Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU",1,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604",null,"Nokia ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762; 29/9/21: WID:RP-210762->RP-212625; 6/1/22: WID:RP-212625->RP-213604",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1644,890151,"   Core part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 10/2/21: 38.849 added;; 13/9/21: Compl:0%->30%; 13/9/21: CD:Tue 15/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",38.848999999999997,89,45,null,null,"2020-09-25","2022-03-22"]
[1645,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1646,900065,"Introduction of NR band n67 ","NR_n67",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,null,null,90,46,null,null,"2021-01-06","NA"]
[1647,900165,"   Core part: Introduction of NR band n67 ","NR_n67-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1648,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1649,900066,"Introduction of NR band n85 ","NR_n85",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 7/4/21: WID:RP-202830->RP-210707",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1650,900166,"   Core part: Introduction of NR band n85 ","NR_n85-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1651,900266,"   Perf. part: Introduction of NR band n85 ","NR_n85-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1652,880083,"Introduction of 1.6 GHz NR supplemental uplink (SUL) band with same uplink frequency range of Band 24","NR_SUL_UL_n24",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: WID:RP-201251->RP-210341",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1653,880183,"   Core part: NR_SUL_UL_n24","NR_SUL_UL_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1654,880283,"   Perf. part: NR_SUL_UL_n24","NR_SUL_UL_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1655,880085,"Introduction of NR supplemental uplink (SUL) band 1880-1920MHz","NR_SUL_band_1880_1920MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1656,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1657,880285,"   Perf. part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1658,880086,"Introduction of NR supplemental uplink (SUL) band 2300-2400MHz","NR_SUL_band_2300_2400MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1659,880186,"   Core part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1660,880286,"   Perf. part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1661,900055,"UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2022-12-01",1,"RP-223434","RP-223215","Yuxin Hao, Huawei Technologies. Co., Ltd","haoyuxin@huawei.com","tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co.,...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1662,0,"Rel-17 LTE new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1663,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.82,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"2021-04-08","2021-07-02"]
[1664,911120,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1-Core",2,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.97,"RP-211144","RP-220172","EBU",null,"WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part; 13/9/21: C ; ",null,91,46,null,null,"2021-04-08","2022-03-22"]
[1665,880079,"Additional LTE bands for UE categories M1/M2/NB1/NB2","LTE_bands_R17_M1_M2_NB1_NB2",1,"Rel-17",null,"2020-06-08","2022-06-22",1,"RP-220816",null,"Ericsson",null,"25/9/20: WID:RP-200804->RP-201646; 29/9/21: WID:RP-201646->RP-211857; 6/1/22: WID:RP-211857->RP-212906; 5/4/22: WID:RP-212906->RP-220816",null,88,45,null,null,"2020-07-28","2022-04-05"]
[1666,880179,"   Core part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Core",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1667,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1668,880081,"Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits","LTE_B24_mod",1,"Rel-17",null,"2020-06-15","2021-12-15",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: WID:RP-201356->RP-211507",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1669,880181,"   Core part: LTE_B24_mod","LTE_B24_mod-Core",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1670,880281,"   Perf. part: LTE_B24_mod","LTE_B24_mod-Perf",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1671,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","2021-06-15","2021-12-15",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1672,0,"Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1673,880087,"LTE iterbCA for 2 bands DL with 1 band UL","LTE_CA_R17_2BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221389",null,"Qualcomm",null,"25/9/20: WID:RP-201248->RP-201754; 6/1/21: WID:RP-201754->RP-202573; 7/4/21: WID:RP-202573->RP-210227; 2/7/21: WID:RP-210227->RP-211560; 29/9/21: WID:RP-211560->RP-211859; 6/1/22: WID:RP-211859->RP-212933; 5/4/22: WID:RP-212933->RP-220552; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1674,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1675,880287,"   Perf. part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 6/6/22: Comp ; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1676,880088,"LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221526",null,"Huawei",null,"25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540; 2/7/21: WID:RP-210540->RP-211388; 29/9/21: WID:RP-211388->RP-212192; 6/1/22: WID:RP-212192->RP-213144; 5/4/22: WID:RP-213144->RP-220715; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1677,880188,"   Core part: LTE_CA_R17_3BDL_1BUL","LTE_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221526","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","; 22/3/22: Compl:0%->67%; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1678,880288,"   Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220713","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","6/1/21: stopped at 0%; 22/3/22: Compl:100%->10%; 22/3/22: CD:15/09/2021->10/06/2022 ; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,96,null,"2020-07-28","2022-06-20"]
[1679,880089,"LTE iterbCA Core for x bands DL (x=4, 5, 6) with 1 band UL","LTE_CA_R17_xBDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221305",null,"Nokia",null,"25/9/20: WID:RP-201245->RP-201911; 6/1/21: WID:RP-201911->RP-202212; 7/4/21: WID:RP-202212->RP-210837; 2/7/21: WID:RP-210837->RP-211068; 29/9/21: WID:RP-211068->RP-211885; 6/1/22: WID:RP-211885->RP-212813; 5/4/22: WID:RP-212813->RP-220175; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1680,880189,"   Core part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1681,880289,"   Perf. part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1682,880090,"LTE iterbCA for 2 bands DL with 2 bands UL","LTE_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221528",null,"Huawei",null,"25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542; 2/7/21: WID:RP-210542->RP-211390; 29/9/21: WID:RP-211390->RP-212194; 5/4/22: WID:RP-212194->RP-220718; 12/7/22: WID:RP-220718->RP-221528",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1683,880190,"   Core part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","; 22/3/22: Compl:0%->70%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1684,880290,"   Perf. part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","22/3/22: CD:15/09/2021->12/06/202222/3/22: Stat Rep: ->RP-220716 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1685,880091,"LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL","LTE_CA_R17_xBDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221188",null,"LG",null,"25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200; 2/7/21: WID:RP-210200->RP-211041; 29/9/21: WID:RP-211041->RP-211748; 6/1/22: WID:RP-211748->RP-212874; 5/4/22: WID:RP-212874->RP-220295; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1686,880191,"   Core part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1687,880291,"   Perf. part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1688,0,"Release 17 other Studies","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1689,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"2020-09-10","2022-03-12"]
[1690,900020,"Study on enhanced Security Aspects of the 5G Service Based Architecture ","FS_eSBA_SEC",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201021",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","10/2/21: 33.875 added;; 19/3/21: 0%->45; 19/3/21: FCD:11/06/2021->09/21; 11/6/21: 45%->70; 11/6/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->75; 12/9/22: 75%->87; 31/3/23: 87%->100",33.875,90,46,null,null,"2020-12-04","2023-03-31"]
[1691,810037,"Study on SECAM and SCAS for 3GPP virtualized network products","FS_VNP_SECAM_SCAS",1,"Rel-17","S3","2018-10-02","2021-12-10",1,"SP-180696",null,"Minpeng Qi, China Mobile","qiminpeng@chinamobile.com","2/10/18: Moved from Rel-17¦7/12/18: 0%->5¦20/3/19: 5%->20; 13/9/19: 20%->30; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 30%->35; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 35%->60; 5/12/20: 60%->70; ","New",81,41,null,null,"2018-09-06","2021-09-13"]
[1692,820010,"Study on Long Term Key Update Process (LTKUP) Detailed solutions","FS_LTKUP_Detail",1,"Rel-17","S3","2018-12-13","2020-03-12",1,"SP-181038",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100",null,82,42,null,null,"2018-12-06","2020-06-26"]
[1693,880011,"Study on 5G Glass-type AR/MR Devices ","FS_5GSTAR",1,"Rel-17","S4","2020-06-25","2022-03-11",1,"SP-200399",null,"Hakju Ryan Lee ","hakju00.lee@samsung.com ","25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 65%->80; 13/12/21: 80%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100",26.998000000000001,88,45,null,null,"2020-06-25","2022-03-12"]
[1694,850004,"Study on VR Streaming Conformance and Guidelines ","FS_VR_CoGui",1,"Rel-17","S4","2019-09-13","2022-03-11",1,"SP-190642",null,"Igor CURCIO ","igor.curcio@nokia.com ","; 8/10/19: 26.999 added;; 8/10/19: 26.119 added;; 25/3/20: 0%->10; 20/4/20: FCD:12/06/2020->12/20; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 10%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100","New ; 26.999; 26.119",85,43,null,null,"2019-09-13","2022-03-12"]
[1695,900029,"Study on 5G media streaming extensions ","FS_5GMS_EXT",1,"Rel-17","S4","2020-12-04","2022-03-11",1,"SP-200937",null,"Iraj Sodagar, Company, Tencent ","irajs@live.com ","21/3/21: 0%->5; 11/6/21: 5%->40; 2/7/21: 26.804 added;; 13/9/21: 40%->50; 13/12/21: 50%->60; 13/12/21: FCD:Wed 08/09/->03/22; 12/3/22: 60%->100",26.803999999999998,90,46,null,null,"2020-12-03","2022-03-12"]
[1696,870015,"Study on Streaming Architecture extensions For Edge processing ","FS_EMSA",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200056",null,"Bouazizi, Imed, Qualcomm ","bouazizi@qti.qualcomm.com ","10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100",null,87,44,null,null,"2019-12-06","2021-06-11"]
[1697,870011,"Study on 5G Video Codec Characteristics ","FS_5GVideo",1,"Rel-17","S4","2020-03-25","2022-06-10",1,"SP-200052",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->75; 13/12/21: 75%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->90; 12/3/22: FC ",null,87,44,null,null,"2019-12-06","2022-06-04"]
[1698,870012,"Study on the use of NBMP in FLUS ","FS_FLUS_NBMP",1,"Rel-17","S4","2020-03-25","2021-09-08",1,"SP-200053",null,"Iraj Sodagar","irajsodagar@tencent.com ","; 10/6/20: 0%->10; 5/12/20: 10%->30; 5/12/20: FCD:11/12/2020->09/20; 21/3/21: 30%->40; 11/6/21: 40%->96; 13/9/21: 96%->100",26.939,87,44,null,null,"2019-12-06","2021-09-13"]
[1699,911032,"Study on enhanced IMS to 5GC Integration Phase 2 ","FS_eIMS5G2",1,"Rel-17","ct","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15","23.700-10",88,45,null,null,"2020-06-26","2021-03-21"]
[1700,880024,"   CT1 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 13/9/21: 15%->60; 13/12/21: 60%->90; 12/3/22: FCD:08/09/2021->3/22; 12/3/22: 90%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1701,911036,"   CT3 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C3","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 0%->5; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 5%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1702,911033,"   CT4 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C4","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 30%->40; 11/6/21: 40%->30; 14/6/21: 30%->40; 13/9/21: 40%->50; 13/9/21: FCD:Wed 08/09/->12/21; 13/ ","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1703,890002,"Study on Port Number Allocation Alternatives for New 3GPP Interfaces ","FS_PortAl",1,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-220391",null,"Giorgi Gulbani, Huawei","giorgi.gulbani@huawei.com ","13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->85; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 85%->100; 22/3/22: WID:CP-202243->CP-220391",null,89,45,null,null,"2020-09-11","2022-03-22"]
[1704,880075,"Study on scenarios and requirements of in-coverage, partial coverage, and out-of-coverage NR positioning use cases","FS_NR_pos_cov",1,"Rel-17","RP","2020-06-22","2021-09-15",1,"RP-201518",null,"LG Electronics",null,"25/9/20: WID:RP-201384->RP-201518; 29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1705,860062,"Study on XR (Extended Reality) evaluations for NR","FS_NR_XR_eval",1,"Rel-17","R1","2019-12-16","2021-12-21",1,"RP-210460","RP-212047","Qualcomm",null,"affects: NR.; 28/7/20: WID:RP-193241->RP-201145; 7/4/21: WID:RP-201145->RP-210460; 13/9/21: Compl:0%->70% ; 6/1/22: 70%->100",null,86,44,null,null,"2020-01-14","2022-01-06"]
[1706,860039,"Study on enhancement of RAN slicing for NR","FS_NR_slice",1,"Rel-17","R2","2019-12-16","2020-12-15",1,"RP-201612",null,"CMCC",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193254->RP-201612; 2/7/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1707,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","2020-06-22","2022-03-11",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"2020-07-28","2022-04-05"]
[1708,880077,"Study on high-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands 5 and 12 and NR band n71","FS_LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2020-03-19","2020-03-19",1,"RP-201261",null,"Nokia",null,"25/9/20: 37.880 added;; 2/7/21: 0%->100",37.880000000000003,88,45,null,null,"2020-07-28","2021-07-02"]
[1709,900058,"Study on high power UE (power class 2) for one NR FDD band ","FS_NR_PC2_UE_FDD",1,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-212892","RP-211854","China Unicom ",null,"TR 38.8xx ; 13/9/21: Compl:0%->100%; 13/9/21: CD:Wed 08/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP- ; 29/9/21: 100%->100; 6/1/22: WID:RP-202870->RP-212892",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1710,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","2020-12-14","2021-09-08",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1711,890021,"Study on charging aspects of 5GS CIoT ","FS_5G_CIoT_CH",1,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200771",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","5/12/20: 0%->15; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 15%->30; 13/9/21: 30%->70; 13/9/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->100",null,89,45,null,null,"2020-09-10","2022-06-04"]
[1712,840021,"Stopped - Study on the Usage of User Identifiers in the 5G System ","FS_UUI5",1,"Rel-17","S2","2019-06-06","2020-06-12",1,"SP-190450",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; 21/1/22: stopped at 0%; 21/1/22: 0%->100","New ; 23.700-094; ",84,43,95,null,"2019-05-31","2022-01-21"]
[1713,830031,"Stopped - Study on service-based support for SMS in 5GC","FS_SB_SMS",1,"Rel-17","S2","2019-03-07","2019-12-05",1,"SP-190184",null,"George Foti ","George dot Foti at ericsson dot com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,95,null,"2019-03-14","2022-01-21"]
[1714,830034,"Stopped - Study on UPF enhancement for control and SBA","FS_UPCAS",1,"Rel-17","S2","2019-03-07","2020-03-06",1,"SP-190187",null,"Dan Wang, China Mobile","wangdanyjy@chinamobile.com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,95,null,"2019-03-14","2022-01-21"]
[1715,880004,"Stopped - Study on security aspects of the Disaggregated gNB Architecture ","FS_disagg_gNB_Sec",1,"Rel-17","S3","2020-06-25","2021-03-12",1,"SP-200349",null,"Sen XU, China Telecom ","xusen@chinatelecom.cn ","12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100. 13/7/22: marked as stopped (was already at 100%!) as per e-mail from Mirko on 02/06/22 14.03",33.840000000000003,88,45,95,null,"2020-06-25","2021-03-19"]
[1716,0,"--- RELEASE 16 ---","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1717,0,"Release 16 Features and related studies","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1718,0,"Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC)","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1719,830098,"Enhancement of URLLC support in the 5G Core network","5G_URLLC",1,"Rel-16",null,"2017-12-15","2024-03-03",0.92,"SP-181122",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-03-14"]
[1720,790008,"   Study on enhancement of URLLC supporting in 5GC ","FS_5G_URLLC",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180118",null,"Hui Ni, Huawei","Hui.ni@huawei.com","7/6/18: 0%->15¦6/8/18: 23.725 added;¦10/9/18: 15%->60¦7/12/18: 60%->85¦14/3/19: 85%->90; 31/5/19: 90%->95; 13/9/19: 95%->100","23.xyz; 23.725",79,40,null,null,"2018-03-15","2019-09-13"]
[1721,810036,"   Study on the security of URLLC for 5GS ","FS_5G_URLLC_SEC",2,"Rel-16","S3","2018-09-06","2019-06-12",1,"SP-180910",null,"Rong Wu, Huawei Technologies","Raina.wu@huawei.com","7/12/18: 0%->20¦20/3/19: FCD:019->06/19¦20/3/19: 20%->65; 31/5/19: 65%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1722,820019,"   Stage 2 of 5G_URLLC ","5G_URLLC",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181233",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1723,840026,"   Security of URLLC for 5GS ","5G_URLLC_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190351",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 6/12/19: FCD:12/12/2019->03/20; 9/4/21: 80%->100",33.500999999999998,84,43,null,null,"2019-05-31","2021-04-09"]
[1724,840005,"   CT Aspects of 5G_URLLC","5G_URLLC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","16/9/19: WID:CP-191063->CP-192022",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1725,870059,"      CT1 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100",null,87,44,null,null,"2019-05-31","2020-03-26"]
[1726,840060,"      CT3 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","29.512; 29.513; 29.514; 29.522; 29.508",84,43,null,null,"2019-05-31","2020-03-26"]
[1727,840061,"      CT4 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","31/5/19: 0%->5; 13/9/19: 5%->20; 6/12/19: 20%->60; 26/3/20: 60%->98; 26/6/20: 98%->100","29.244; 29.502; 29.503; 29.510; 29.281",84,43,null,null,"2019-05-31","2020-06-26"]
[1728,890020,"   Charging enhancement for URLLC ","5G_URLLC",2,"Rel-17","S5","2020-09-16","2021-06-11",1,"SP-200769",null,"Chen, Shan, Huawei ","chenshan@huawei.com ","; 5/12/20: 0%->20; 5/12/20: FCD:12/03/2021->06/20; 21/3/21: 20%->30; 13/9/21: 30%->100","32.255; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1729,1000013,"   Management Aspects of URLLC ","URLLC_Mgt",2,"Rel-18","S5","2023-06-08","2024-03-03",0.1,"SP-230631",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn ","; 7/9/23: 0%->10","28.541; 28.552; 28.554 ",100,null,null,null,"2023-06-08","2023-09-07"]
[1730,780030,"   Stopped - Study on EPC support for Mobility with Low Latency Communication","FS_LLC_Mob",2,"Rel-16","S2","2017-12-15","2018-09-14",1,"SP-171069",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395","new 23.739",78,40,null,null,"2017-12-15","2018-06-07"]
[1731,790009,"   Stopped - Study on enht of systems using EPS for UR and Availability using commodity equipment","FS_EPS_URACE",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180119",null,"Chris Pudney","chris.pudney@vodafone.com","7/6/18: 0%->10¦6/8/18: 23.736 added¦6/6/19: stopped at 10% as per SP-190395; 6/6/19: 10%->100","new; 23.736",79,40,null,null,"2018-03-15","2019-06-06"]
[1732,830074,"Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC)","NR_L1enh_URLLC",1,"Rel-16","R1","2018-06-15","2023-12-12",0.99,"RP-191584",null,"Huawei",null,"26/6/19: WID:RP-190726->RP-191584",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1733,800095,"   Study on physical layer enhancements for NR UR Low Latency Cases","FS_NR_L1enh_URLLC",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181477",null,"Huawei",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1734,830174,"   Core part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-190726",null,"Huawei",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1735,830274,"   Perf. part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-190726",null,"Huawei",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[1736,900054,"   UE Conformance Test Aspects - Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-UEConTest",2,"Rel-16","R5","2020-12-14","2023-12-12",0.99,"RP-202566","RP-232349","Chunying GU, Huawei","guchunying@huawei.com","tested: REL-16 WI NR_L1enh_URLLC-Core ; 8/4/21: 0%->5; 2/7/21: 5%->16; 22/3/22: Compl:16 ; 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 9/12/22: FCD:22/12/2022->01/12/2023; Compl:90%->91%; Stat Rep: RP-2214.....",null,90,46,null,null,"2021-01-06","2023-09-06"]
[1737,830080,"Support of NR Industrial Internet of Things (IoT)","NR_IIOT",1,"Rel-16","R2","2018-06-15","2022-03-11",1,"RP-192590",null,"Nokia",null,"26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1738,810060,"   Study on channel modeling for indoor industrial scenarios","FS_IIIOT_CM",2,"Rel-16","R1","2018-09-14","2019-09-13",1,"RP-182138",null,"Ericsson",null,"8/10/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-10-08"]
[1739,800098,"   Study on NR Industrial Internet of Things (IoT)","FS_NR_IIOT",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181479",null,"Nokia",null,"TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100",38.825000000000003,80,41,null,null,"2018-06-27","2019-03-26"]
[1740,830180,"   Core part: Support of NR Industrial Internet of Things (IoT)","NR_IIOT-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200797",null,"Nokia",null,"28/7/20: WID:RP-192590->RP-200797; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1741,880067,"   UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT)","NR_IioT-UEConTest",2,"Rel-16","R5","2020-06-22","2022-03-11",1,"RP-200757","RP-220623","CMCC",null,"8/10/20: 0%->5; 8/4/21: 5%->68; 2/7/21: 68%->77; 13/9/21: Compl:77%->95%; 13/9/21: C ; 29/9/21: WID:RP-200757->RP-211786; 6/1/22: WID:RP-211786->RP-212943; ",null,88,45,null,null,"2020-07-28","2022-03-22"]
[1742,820999,"5GS Enhanced support of Vertical and LAN Services","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",82,42,null,null,"2014-08-29","2014-08-29"]
[1743,750004,"Study on Communication for Automation in Vertical Domains","FS_CAV",1,"Rel-16","S1","2017-03-02","2018-03-15",1,"SP-170169",null,"Walewski, Joachim, Siemens AG","joachim.walewski@siemens.com ","7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100",22.803999999999998,75,38,null,null,"2017-03-02","2018-06-07"]
[1744,800007,"Service requirements for cyber-physical control applications in vertical domains","cyberCAV",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180321",null,"Joachim W. Walewski (Siemens)",null,"10/9/18: 5%->40¦4/12/18: 40%->100","22.261; 22.104",80,41,null,null,"2018-06-06","2018-12-04"]
[1745,830042,"5GS Enhanced support of Vertical and LAN Services","Vertical_LAN",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com",null,null,82,42,null,null,"2018-12-06","2018-06-14"]
[1746,800028,"   Study on 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180507",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","10/9/18: 0%->25¦7/12/18: 25%->88¦14/3/19: 88%->92; 31/5/19: 92%->100",23.734000000000002,80,41,null,null,"2018-06-06","2019-05-31"]
[1747,820017,"   Stage 2 of Vertical_LAN","Vertical_LAN",2,"Rel-16","S2","2018-12-13","2019-06-24",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-12-06"]
[1748,810038,"   Study on Security for 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN_SEC",2,"Rel-16","S3","2018-09-06","2019-12-12",1,"SP-180697",null,"Jerichow, Anja (Nokia) ","anja.jerichow@nokia.com ","7/12/18: 0%->10¦20/3/19: FCD:019->06/19¦20/3/19: 10%->65; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->78; 6/12/19: 78%->92; 25/3/20: 92%->100","New",81,41,null,null,"2018-09-06","2020-03-25"]
[1749,840027,"   Security for Vertical_LAN ","Vertical_LAN_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190352",null,"Jerichow, Anja, Nokia ","anja.jerichow@nokia.com ","13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100",33.500999999999998,84,43,null,null,"2019-05-31","2020-06-26"]
[1750,830010,"   CT aspects of Vertical_LAN","Vertical_LAN",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272",null,83,42,null,null,"2018-12-06","2019-12-09"]
[1751,830035,"      CT1 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->20; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 20%->75; 6/12/19: 75%->90; 26/3/20: 90%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.368; 24.501; 24.526",83,42,null,null,"2018-12-06","2020-09-13"]
[1752,830036,"      CT3 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-201174",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174","29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061",83,42,null,null,"2018-12-06","2020-06-26"]
[1753,830037,"      CT4 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->5; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 5%->50; 6/12/19: 50%->85; 26/3/20: 85%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.509; 29.510; 29.518; 29.571; 29.244; 29.281",83,42,null,null,"2018-12-06","2020-06-26"]
[1754,850048,"Service Enabler Architecture Layer for Verticals","SEAL",1,"Rel-16",null,"2019-03-07","2020-06-12",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 8/10/19: 33.434 added;; 8/10/19: 24.548 added;","new 23.434; 33.434; 24.548; 24.547",85,42,null,null,"2018-12-06","2019-10-08"]
[1755,820027,"   Stage 2 of SEAL","SEAL",2,"Rel-16","S6","2019-03-07","2019-08-29",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 13/9/19: 0%->100","new 23.434",82,42,null,null,"2018-12-06","2019-09-13"]
[1756,850019,"   Security aspects of SEAL","SEAL",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190901",null,"Rajavelsamy Rajadurai (Samsung) ","rajvel@samsung.com ","; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1757,850006,"   CT aspects of SEAL ","SEAL",2,"Rel-16","ct","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ",null,"New ",85,43,null,null,"2019-09-13","NA"]
[1758,850049,"      CT1 aspects of SEAL ","SEAL",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 6/12/19: 0%->60; 6/12/19: 60%->60; 26/3/20: 60%->80; 26/6/20: 80%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1759,850050,"      CT3 aspects of SEAL ","SEAL",3,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 26/3/20: 0%->75; 26/6/20: 75%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1760,820067,"NR-based access to unlicensed spectrum","NR_unlic",1,"Rel-16","R1","2017-03-15","2019-12-15",0.83,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834",null,82,42,null,null,"2019-01-16","2020-09-25"]
[1761,750045,"   Study on NR-based access to unlicensed spectrum","FS_NR_unlic",2,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181339",null,"Qualcomm",null,"TR 38.8XX19/6/17: WID: RP-170828->RP-171416¦30/6/17: 32.889 added;¦19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%¦27/6/18: Compl:10%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦16/1/19: 40%->100",32.889000000000003,75,38,null,null,"2017-03-21","2019-01-16"]
[1762,820167,"   Core part: NR-based access to unlicensed spectrum","NR_unlic-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[1763,820267,"   Perf. part: NR-based access to unlicensed spectrum","NR_unlic-Perf",2,"Rel-16","R4","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 2/7/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-07-02"]
[1764,911003,"   UE Conformance Test Aspects - NR-based access to unlicensed spectrum ","NR_unlic-UEConTest",2,"Rel-16","R5","2021-03-12","2023-12-12",0.6,"RP-210708","RP-232012","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","tested: REL-16 WI NR_unlic-Core ; 2/7/21: 0%->5 ; ; 6/6/22: Compl:18%->20% 20/6/22: Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com ; 9/...; 9/12/22: FCD:22/12/2022->01/06/2023; Compl:25%->28%; Stat Re...",null,91,46,null,null,"2021-04-07","2023-09-06"]
[1765,800006,"LAN support in 5G","5GLAN",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","11/3/22: 99%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2022-03-11"]
[1766,760007,"   Study on LAN Support in 5G ","FS_5GLAN",2,"Rel-16","S1","2017-06-05","2018-03-15",1,"SP-170456",null,"Nasielski, Jack, Qualcomm Incorporated","jackn@qti.qualcomm.com","11/9/17: 0%->35¦15/12/17: 35%->65¦16/3/18: 65%->100","22.821; ",76,39,null,null,"2017-06-03","2018-03-16"]
[1767,800047,"   Stage 1 of 5GLAN","5GLAN",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","10/9/18: 40%->75¦10/9/18: FCD:09/18->12/18¦4/12/18: 75%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2018-12-04"]
[1768,830024,"Study on non-public networks management","FS_OAM_NPN",1,"Rel-16","S5","2019-03-07","2020-06-12",1,"SP-190137",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com","31/5/19: 0%->2; 13/9/19: 2%->10; 26/3/20: 10%->70; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-06-28"]
[1769,0,"Cellular IoT support and evolution ","-",1,"Rel-16",null,"2016-06-18","2016-06-18",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1770,830043,"Cellular IoT support and evolution for the 5G System","5G_CIoT",1,"Rel-16",null,"2017-09-08","2020-06-12",1,"SP-181118",null,null,null,null,null,83,42,null,null,"2018-12-06","NA"]
[1771,770038,"   Study on 5G_CIoT","FS_CIoT_5G",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180614",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","11/09/17: rapporteur change¦15/12/17: 23.724 added;¦16/3/18: 0%->20¦7/6/18: 20%->50¦15/6/18: WID:SP-170801->SP-180614¦15/6/18: FCD:09/18->12/18¦10/9/18: 50%->70¦7/12/18: 70%->95; 31/5/19: 95%->100","New; 23.724",77,39,null,null,"2017-09-08","2019-05-31"]
[1772,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[1773,830013,"   CT aspects of 5G_CIoT","5G_CIoT",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 9/12/19: WID:CP-111237->CP-193274; 25/3/20: WID:CP-193274->CP-200147",null,83,42,null,null,"2018-12-06","2020-03-25"]
[1774,830038,"      CT1 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->40; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 40%->60; 6/12/19: 60%->85; 26/3/20: 85%->92; 26/6/20: 92%->99; 13/9/20: 99%->100","23.122; 24.250; 24.301; 24.368; 24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1775,830039,"      CT3 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100","29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514",83,42,null,null,"2018-12-06","2020-06-26"]
[1776,830040,"      CT4 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->10; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 10%->25; 6/12/19: 25%->60; 26/3/20: 60%->90; 26/6/20: 90%->100","23.008; 29.274; 29.502; 29.503; 29.505; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[1777,830041,"      CT6 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C6","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 26/3/20: 0%->100","TBD",83,42,null,null,"2018-12-06","2020-03-26"]
[1778,850014,"   Security of 5G_CIoT","5G_CIoT",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190897",null,"Henrik Normann, Ericsson ","henrik.normann@ericsson.com ","6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1779,800033,"Study on evolution of Cellular IoT security for the 5G System","FS_CIoT_sec_5G",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180440",null,"Noamen Ben Henda ","noamen.ben.henda@ericsson.com","6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100","New; 33.861",80,41,null,null,"2018-06-06","2020-06-26"]
[1780,760040,"Study on MBMS User Services for IoT","FS_MBMS_IoT",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170592",null,"Cedric thienot, Expway","cedric (dot) thienot (at) expway (dot) com","11/9/17: 0%->10¦15/12/17: 10%->30¦16/3/18: 30%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->90¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 90%->100","26.8xx",76,39,null,null,"2017-06-03","2018-09-10"]
[1781,800083,"Additional MTC enhancements for LTE","LTE_eMTC5",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦16/1/19: WID:RP-181450->RP-182891¦26/3/19: WID:RP-182891->RP-190770; 26/6/19: WID:RP-190770->RP-191356; 14/1/20: WID:RP-191356->RP-192875",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1782,800183,"   Core part: Additional MTC enhancements for LTE","LTE_eMTC5-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1783,800283,"   Perf. part: Additional MTC enhancements for LTE","LTE_eMTC5-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"26/3/19: WID:RP-182891->RP-190770; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1784,800084,"Additional enhancements for NB-IoT","NB_IOTenh3",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1785,800184,"   Core part: Additional enhancements for NB-IoT","NB_IOTenh3-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦26/3/19: WID:RP-182902->RP-190757; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1786,800284,"   Perf. part: Additional enhancements for NB-IoT","NB_IOTenh3-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"26/3/19: WID:RP-182902->RP-190757; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1787,810050,"5G message service","5GMSG",1,"Rel-16","S1","2016-06-18","2018-12-14",1,"SP-180772",null,null,null,null,22.262,81,41,null,null,"2018-09-06","NA"]
[1788,770004,"   Study on 5G message service for MIoT","FS_5GMSG",2,"Rel-16","S1","2016-06-18","2018-09-14",1,"SP-170704",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","15/12/17: 22.824 added;¦15/12/17: 0%->25¦16/3/18: 25%->60¦10/9/18: 60%->95¦4/12/18: 95%->100","New; 22.824",77,39,null,null,"2017-09-08","2018-12-04"]
[1789,810014,"   Message Service Within the 5G System requirements ","MSGin5G",2,"Rel-16","S1","2018-09-06","2018-12-14",1,"SP-180920",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","4/12/18: 0%->100","22.262; 22.261",81,41,null,null,"2018-09-06","2021-06-11"]
[1790,0,"Advanced V2X support","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1791,790002,"Study on Improvement of V2X Service Handling ","FS_V2XIMP",1,"Rel-16","S1","2018-03-15","2018-06-14",1,"SP-180247",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100",22.885999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[1792,820024,"Improvement of V2X service Handling ","V2XIMP",1,"Rel-16","S1","2018-10-25","2018-12-04",1,"SP-181013",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","4/12/18: 0%->95¦14/3/19: 95%->100",22.186,82,42,null,null,"2018-12-04","2019-03-14"]
[1793,840074,"Application layer support for V2X services ","V2XAPP",1,"Rel-16",null,"2017-12-15","2020-03-12",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65","New",84,41,null,null,"2018-09-06","2019-03-14"]
[1794,780025,"   Study on V2XAPP","FS_V2XAPP",2,"Rel-16","S6","2017-12-15","2018-09-14",1,"SP-171071",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100",null,78,40,null,null,"2017-12-15","2018-12-07"]
[1795,810020,"   Stage 2 of V2XAPP","V2XAPP",2,"Rel-16","S6","2018-09-06","2019-06-14",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65; 31/5/19: 65%->95; 13/9/19: 95%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1796,840010,"   CT aspects of V2XAPP ","V2XAPP",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191153->CP-192077",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1797,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[1798,840076,"      CT3 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->60; 26/3/20: 60%->100","29.122; 29.116",84,43,null,null,"2019-05-31","2020-03-26"]
[1799,840077,"      CT4 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100","23.003; 23.008",84,43,null,null,"2019-05-31","2020-03-26"]
[1800,840078,"Architecture enhancements for 3GPP support of advanced V2X services","eV2XARC",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30","23.501; 23.502; 23.503; 23.285",84,43,null,null,"2018-12-06","2019-03-14"]
[1801,760043,"   Study on eV2XARC","FS_eV2XARC",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180733","SP-170412","LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","11/9/17: 0%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170379->SP 170590¦16/3/18: 20%->25¦7/6/18: 25%->35¦10/9/18: 35%->58¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP 170590->SP-180733¦7/12/18: 58%->88¦14/3/19: 88%->95; 31/5/19: 95%->100",23.786000000000001,76,39,null,null,"2017-06-03","2019-05-31"]
[1802,820018,"   Stage 2 of eV2XARC","eV2XARC",2,"Rel-16","S2","2018-12-13","2019-06-14",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100","23.501; 23.502; 23.503; 23.285; 24.588",82,42,null,null,"2018-12-06","2020-03-25"]
[1803,840011,"   CT aspects of eV2XARC ","eV2XARC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191154->CP-192078; 25/3/20: WID:CP-192078->CP-200291; 2/7/20: WID:CP-200291->CP-201343",null,84,43,null,null,"2019-05-31","2020-07-02"]
[1804,840079,"      CT1 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.501; 24.301; 27.007",84,43,null,null,"2019-05-31","2020-09-13"]
[1805,840080,"      CT3 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 26/3/20: 80%->90; 26/6/20: 90%->100; 26/6/20: WID:CP-200291->CP-201199","29.512; 29.513; 29.514; 29.519; 29.122; 29.522",84,43,null,null,"2019-05-31","2020-06-26"]
[1806,840081,"      CT4 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571",84,43,null,null,"2019-05-31","2020-06-26"]
[1807,840082,"      CT6 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C6","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100",31.102,84,43,null,null,"2019-05-31","2020-03-26"]
[1808,860014,"   Security Aspects of eV2XARC","eV2XARC",2,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191125",null,"Dongjoo Kim, LG Electronics Inc. ","dongjoo7.kim@lge.com ","; 6/12/19: 0%->10; 25/3/20: 10%->70; 26/6/20: 70%->95; 12/9/20: 95%->98; 5/12/20: 98%->99; 19/3/21: 99%->100","33.220; TS 33.536",86,44,null,null,"2019-12-06","2021-03-19"]
[1809,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1810,770029,"Study on V2X Media Handling and Interaction","FS_mV2X",1,"Rel-16","S4","2017-09-08","2019-09-12",1,"SP-170799",null,"Jung, Kyunghun, Samsung Electronics Co., Ltd","kyunghun.jung@samsung.com","15/12/17: 26.985 added;¦15/12/17: 0%->30¦16/3/18: 30%->50¦22/3/18: FCD:09/18->12/18¦7/6/18: 50%->60. 14/06/18: Moved from Rel-15¦10/9/18: 60%->80¦13/12/18: 80%->60¦13/12/18: FCD:12/18->09/19¦12/3/19: 60%->70; 31/5/19: 70%->80; 26/6/20: 80%->100","New; 26.985",77,39,null,null,"2017-09-08","2020-06-26"]
[1811,830023,"Study on Security Aspects of 3GPP support for Advanced V2X Services ","FS_eV2X_Sec",1,"Rel-16","S3","2019-03-07","2020-03-12",1,"SP-190108",null,"Joonwoong Kim, LG Electronics","joonwoong.kim@lge.com","31/5/19: 0%->20; 13/9/19: 20%->60; 13/9/19: FCD:05/09/2019->12/20; 6/12/19: 60%->75; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 75%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[1812,830078,"5G V2X with NR sidelink","5G_V2X_NRSL",1,"Rel-16","R1","2019-03-01","2023-12-12",0.79,"RP-200129",null,"LG Electronics",null,"26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1813,830178,"   Core part: 5G V2X with NR sidelink","5G_V2X_NRSL-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-200129",null,"LG Electronics",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1814,830278,"   Perf. part: 5G V2X with NR sidelink","5G_V2X_NRSL-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200129",null,"LG Electronics",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1815,880069,"   UE Conformance Test Aspects - 5G V2X with NR sidelink","5G_V2X_NRSL_eV2XARC-UEConTest",2,"Rel-16","R5","2020-06-22","2023-12-12",0.63,"RP-200894","RP-232348","Xuesong Wang, Huawei Technologies. Co., Ltd","wangxuesong743@huawei.com","8/10/20: 0%->5; 8/4/21: 5%->11; 2/7/21: 11%->18; 22/3/22: Compl:18%->43%; ; 5/4/22: WID:RP-200894->RP-220744 20/6/22: Rapporteur: Huawei->Xuesong Wang, Huawei Technologies. Co., Ltd; Rap eMail: ->wangxuesong743@huawei.com12/7/22: WID:RP-20089...; 9/1...",null,88,45,null,null,"2020-07-28","2023-09-06"]
[1816,0,"5G Location and Positionning Services","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1817,800013,"5G positioning services","5G_HYPOS",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ",null,22.260999999999999,80,41,null,null,"2018-06-06","NA"]
[1818,760006,"   Study on positioning use cases","FS_5G_HYPOS",2,"Rel-16","S1","2017-06-05","2018-06-15",1,"SP-170589",null,"Ries, Lionel, ESA ","lionel.ries@esa.int","11/9/17: 0%->10¦15/12/17: 10%->50¦15/12/17: FCD:03/18->06/18¦16/3/18: 50%->75¦7/6/18: 75%->90¦10/9/18: 90%->100",22.872,76,39,null,null,"2017-06-03","2018-09-10"]
[1819,800049,"   Stage 1 of 5G_HYPOS","5G_HYPOS",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ","10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1820,830102,"Enhancement to the 5GC LoCation Services","5G_eLCS",1,"Rel-16",null,"2017-12-15","2020-06-12",0.98,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn",null,"23.501; 23.502",83,42,null,null,"2018-12-06","NA"]
[1821,780028,"   Study on Enhancement to the 5GC Location Services","FS_eLCS",2,"Rel-16","S2","2017-12-15","2019-03-14",1,"SP-180734",null,"Ming Ai, CATT","aiming@catt.cn","16/3/18: 0%->15¦7/6/18: 15%->45¦10/9/18: 45%->55¦10/9/18: FCD:12/18->03/19¦2/10/18: WID:SP-170937->SP-180734¦7/12/18: 55%->100","new 23.731",78,40,null,null,"2017-12-15","2018-12-07"]
[1822,810035,"   Study on Security of the enhancement to the 5GC location services","FS_eLCS_Sec",2,"Rel-16","S3","2018-09-06","2019-12-13",1,"SP-180694",null,"Wei Zhou, CATT","zhouwei@catt.cn","7/12/18: 0%->5¦20/3/19: 5%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1823,820016,"   Stage 2 of 5G_eLCS","5G_eLCS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn","14/3/19: 0%->45; 31/5/19: 45%->85; 26/6/19: 29.515 added;; 13/9/19: 85%->100","23.501; 23.502; 29.515",82,42,null,null,"2018-12-06","2019-09-13"]
[1824,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",0.95,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1825,830044,"      CT1 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 13/9/19: 0%->40; 6/12/19: 40%->90; 26/6/20: 90%->99; 13/9/20: 99%->100","24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1826,830045,"      CT3 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C3","2019-03-07","2019-12-05",0.85,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85","29.522; 29.122",83,42,null,null,"2018-12-06","2020-06-26"]
[1827,830046,"      CT4 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100","24.080; 29.518; 29.572; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-06-26"]
[1828,850017,"   Security of 5G_eLCS","5G_eLCS",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190900",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 6/12/19: 0%->75; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 75%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1829,830077,"NR positioning support","NR_pos",1,"Rel-16","R1","2018-06-15","2023-09-08",0.99,"RP-192581",null,"Intel",null,"26/6/19: WID:RP-190752->RP-191156; 14/1/20: WID:RP-191156->RP-192581",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1830,800092,"   Study on NR positioning support","FS_NR_pos",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181399",null,"Intel",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1831,830073,"   Study on local NR positioning in NG-RAN","FS_NR_local_pos",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-191774",null,"CMCC",null,"8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100",38.856000000000002,83,42,null,null,"2019-03-26","2020-01-14"]
[1832,830177,"   Core part: NR positioning support","NR_pos-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-192581",null,"Intel",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1833,830277,"   Perf. part: NR positioning support","NR_pos-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-192581",null,"Intel",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1834,900057,"   UE Conformance Test Aspects - NR positioning support ","NR_pos-UEConTest",2,"Rel-16","R5","2020-12-14","2023-09-08",1,"RP-212227","RP-231835","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5; 29/9/21: WID:RP-202727->RP-212227; 22/3/22: Compl:5%->54%; ; 20/6/22: Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn12/7/22: WID:RP-212227->RP-221450 ; ;...; 9/12/22: FCD:22/12...",null,90,46,null,null,"2021-01-06","2023-09-06"]
[1835,0,"UE radio capability signalling optimization","-",1,"Rel-16",null,"2018-06-06","2018-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1836,840054,"Optimisations on UE radio capability signalling","RACS",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"RP-191460",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","26/6/19: WID:SP-190180->RP-191460","23.501; 23.502; 23.401",84,43,null,null,"2019-03-14","2019-06-26"]
[1837,800025,"   Study on RACS","FS_RACS",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180599",null,"Haris Zisimopoulos, Qualcomm Incorporated ","harisz@qti.qualcomm.com","10/9/18: 0%->40¦7/12/18: 40%->70¦14/3/19: 70%->100","New",80,41,null,null,"2018-06-06","2019-03-14"]
[1838,830027,"   Stage 2 of RACS","RACS",2,"Rel-16","S2","2019-03-07","2019-06-06",1,"SP-190180",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","31/5/19: 0%->90; 26/6/19: 29.673 added;; 13/9/19: 90%->100","23.501; 23.502; 23.401; 29.673",83,42,null,null,"2019-03-14","2019-09-13"]
[1839,840003,"   CT aspects of RACS","RACS",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","17/9/19: WID:CP-191061->CP-192207; 25/3/20: WID:CP-192207->CP-200058",null,84,43,null,null,"2019-05-31","2020-03-25"]
[1840,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[1841,840056,"      CT3 aspects of RACS","RACS",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->90; 26/3/20: 90%->100","29.122; 29.522",84,43,null,null,"2019-05-31","2020-03-26"]
[1842,840057,"      CT4 aspects of RACS","RACS",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->20; 6/12/19: 20%->75; 26/3/20: 75%->90; 26/6/20: 90%->100","23.003; 23.008; 29.230; 29.274; 29.510; 29.518",84,43,null,null,"2019-05-31","2020-06-26"]
[1843,830079,"Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN",1,"Rel-16","R2","2018-06-15","2023-03-03",0.99,"RP-200164",null,"MediaTek",null,"26/3/20: WID:RP-190657->RP-200164",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1844,800097,"   Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects","FS_RACS_RAN",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181459",null,"MediaTek",null,"TR 37.873¦related SA2 SI FS_RACS was started at SA #80 ¦6/8/18: 37.873 added;¦26/3/19: 0%->100",37.872999999999998,80,41,null,null,"2018-06-27","2019-03-26"]
[1845,830179,"   Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200164",null,"MediaTek",null,"26/6/19: WID:RP-190657->RP-191088; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1846,880073,"   UE Conformance Test Aspects - Optimisations on UE radio capability signalling - NR/E-UTRA Aspects","RACS-UEConTest",2,"Rel-16","R5","2020-03-19","2023-03-03",1,"RP-201152","RP-230098","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 7/4/21: WID:RP-201153->RP-210714; 8/4/21: 5%->25; 8/4/21: FCD:19/03/2021->09/21; 2/7/21: 25%->50; 22/3/22: ; 5/4/22: WID:RP-210714->RP-220434 ; 9/12/22: Acronym:RACS-UEConTest->NG_RAN_PRN_Vertical_LAN-UEConTest; FCD:22/12/2022->01/03...",null,88,45,null,null,"2020-07-28","2023-03-17"]
[1847,800099,"Study on solutions for NR to support non-terrestrial networks (NTN)","FS_NR_NTN_solutions",1,"Rel-16","R3","2018-06-15","2019-12-13",1,"RP-190710",null,"Thales",null,"TR 38.xx1¦compare REL-15 SI FS_NR_nonterr_nw¦26/3/19: WID:RP-181370->RP-190710; 14/1/20: 0%->100",38.820999999999998,80,41,null,null,"2018-06-27","2023-03-17"]
[1848,0,"Enablers for Network Automation Architecture for 5G","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1849,830047,"Enablers for Network Automation for 5G ","eNA",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1850,760047,"   Study of enablers for Network Automation for 5G ","FS_eNA",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180792",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","16/3/18: FCD:09/18->06/18¦16/3/18: 0%->15¦7/6/18: 15%->30¦15/6/18: WID:SP-170383->SP-180613¦15/6/18: FCD:06/18->09/18¦10/9/18: 30%->50¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-180613->SP-180792¦7/12/18: 50%->90¦14/3/19: 90%->94; 31/5/19: 94%->100","new 23.791",76,39,null,null,"2017-06-03","2019-05-31"]
[1851,820020,"   Stage 2 of eNA","eNA",2,"Rel-16","S2","2018-12-06","2019-06-17",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 26/6/19: 29.517 added;; 13/9/19: 85%->92; 6/12/19: 92%->97; 25/3/20: 97%->100","23.501; 23.502; 23.503; 29.517",82,42,null,null,"2018-12-06","2020-03-25"]
[1852,830009,"   CT aspects of eNA","eNA",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1853,830048,"      CT3 aspects of eNA","eNA",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->55; 6/12/19: 55%->85; 6/12/19: FCD:05/12/2019->03/20; 26/3/20: 85%->100","29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[1854,830049,"      CT4 aspects of eNA","eNA",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100","29.244; 29.510; 29.518; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-03-26"]
[1855,0,"Wireless and Wireline Convergence Enhancement ","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1856,760044,"Study on the Wireless and Wireline Convergence for the 5G system architecture ","FS_5WWC",1,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-170380",null,"Marco Spini, Huawei Technologies","m.spini@huawei.com","11/9/17: 0%->15¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 15%->25¦7/6/18: 25%->35¦10/9/18: 35%->60¦10/9/18: FCD:06/18->12/18¦7/12/18: 60%->100",23.716000000000001,76,39,null,null,"2017-06-03","2018-12-07"]
[1857,800031,"Study on the security of the Wireless and Wireline Convergence for the 5G system architecture","FS_5WWC_SEC",1,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180438",null,"He Li, Huawei Technologies","LIHE2@HUAWEI.COM","6/8/18: 33.807 added;¦10/9/18: 0%->5¦7/12/18: 5%->30¦20/3/19: 30%->60¦20/3/19: FCD:019->09/19; 31/5/19: 60%->75; 8/10/19: 75%->100","New; 33.807",80,41,null,null,"2018-06-06","2019-10-08"]
[1858,830050,"Wireless and Wireline Convergence for the 5G system architecture","5WWC",1,"Rel-16",null,"2018-12-06","2020-06-12",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1859,820014,"   Stage 2 of 5WWC","5WWC",2,"Rel-16","S2","2018-12-06","2019-06-13",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1860,830015,"   CT aspects of 5WWC","5WWC",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156. Confusion with UID (was 829910 instead of 830015); 17/9/19: WID:CP-191156->CP-192079; 9/12/19: WID:CP-192079->CP-193145; 2/7/20: WID:CP-193145->CP-192079",null,83,42,null,null,"2018-12-06","2020-07-02"]
[1861,829911,"      CT1 aspects of 5WWC","5WWC",3,"Rel-16","C1","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100","24.501; 24.502; 24.526",82,42,null,null,"2018-12-06","2020-06-30"]
[1862,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[1863,829914,"      CT4 aspects of 5WWC","5WWC",3,"Rel-16","C4","2019-06-13","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 0%->5; 6/12/19: 5%->60; 26/3/20: 60%->95; 26/6/20: 95%->100","23.003; 29.518; 29.502; 29.509; 29.244; 29.503; 29.571; 29.505",82,42,null,null,"2018-12-06","2020-06-26"]
[1864,850015,"   Security of 5WWC","5WWC",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190898",null,"He Li, Huawei Technologies ","lihe2@huawei.com ","13/9/19: 0%->100; 8/10/19: 100%->0; 6/12/19: 0%->90; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 90%->95; 26/6/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1865,860019,"   Charging Aspect for 5WWC ","5WWC",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191188",null,"ZHU, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","32.240; 32.255; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-06-28"]
[1866,830082,"   NG interface usage for WWC","5WWC-NG_interface",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190772",null,"Huawei",null,null,null,83,42,null,null,"2019-03-26","NA"]
[1867,830182,"      Core part: NG interface usage for WWC","5WWC-NG_interface-Core",3,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190999",null,"Huawei",null,"26/6/19: WID:RP-190772->RP-190999; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1868,0,"Mission Critical, Public Warning, Railways and Maritime","-",1,"Rel-16",null,"2016-09-19","2016-09-19",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1869,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[1870,800024,"Study into discreet listening and logging for mission critical services","FS_MCLOG",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-181138",null,"Chater-Lea, David, Motorola Solutions","david.chater-lea@motorolasolutions.com","6/8/18: 23.784 added;¦10/9/18: 0%->10¦7/12/18: 10%->50¦7/12/18: FCD:03/19->06/19¦14/12/18: WID:SP-180384->SP-181138¦14/3/19: 50%->75; 31/5/19: 75%->100","New; 23.784",80,41,null,null,"2018-06-06","2019-05-31"]
[1871,800022,"Enhanced Mission Critical Push-to-talk architecture phase 2","enh2MCPTT",1,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[1872,860026,"   Stage 2 of enh2MCPTT ","enh2MCPTT",2,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100; 1/7/20: 0%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2020-07-01"]
[1873,860003,"   CT aspects of enh2MCPTT ","enh2MCPTT-CT",2,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193148",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","; 26/3/20: 0%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484 ",86,44,null,null,"2019-12-06","2020-03-26"]
[1874,830051,"Enhancements to Functional architecture and information flows for Mission Critical Data","eMCData2",1,"Rel-16","S6","2018-06-06","2020-03-12",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40",null,83,42,null,null,"2018-06-06","2018-12-07"]
[1875,800018,"   Stage 2 of eMCData2","eMCData2",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40¦14/3/19: 40%->75; 31/5/19: 75%->90; 13/9/19: 90%->100","23.280; 23.282",80,41,null,null,"2018-06-06","2019-09-13"]
[1876,830014,"   CT aspects of eMCData2","eMCData2",2,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193146",null,"Val Oprescu (AT&T)","vo4887@att.com ","31/5/19: 0%->15; 13/9/19: 15%->25; 17/9/19: WID:CP-190199->CP-192081; 6/12/19: 25%->55; 9/12/19: FCD:12/12/2019->03/20; 9/12/19: WID:CP-192081->CP-193146; 26/3/20: 55%->70; 26/6/20: 70%->100","24.282; 24.582; 24.483; 24.484; 24.zzz",83,42,null,null,"2018-06-06","2020-06-26"]
[1877,850051,"MCData File Distribution support over xMB","MC_XMB",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,85,43,null,null,"2018-09-06","2019-05-31"]
[1878,810004,"   Stage 2 of MC_XMB","MC_XMB",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,81,41,null,null,"2018-09-06","2019-05-31"]
[1879,850007,"   CT aspects of MC_XMB","MC_XMB-CT",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192253",null,"Wenliang Xu, Ericsson ","wenliang.xu@ericsson.com ","; 6/12/19: 0%->90; 26/3/20: 90%->100",29.116,85,43,null,null,"2019-09-13","2020-03-26"]
[1880,810011,"Protocol enhancements for Mission Critical Services","MCProtoc16",1,"Rel-16","C1","2018-09-06","2019-12-20",1,"CP-182110",null,"AXELL, Jörgen","jorgen.axell@ericsson.com","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980",81,41,null,null,"2018-09-06","2020-03-26"]
[1881,970077,"Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) ","MCProtoc16_enh2MCPTT_eMCData2-ConTest",1,"Rel-16","R5","2022-09-08","2023-09-22",0.32,"RP-222549","RP-231716","Jason Kahn, NIST","jason.kahn@nist.gov","9/12/22: Acronym:MCProtoc16_enh2MCPTT_eMCData2-ConTest->MCProtoc16_enh2MCPTT_eMCData2-UEConTest; FCD:08/09/2024->30/08/2024; Compl:0%->5%; Stat Rep: ->RP-222804; Rapporteur: NIST->Jason Kahn, NIST; Rap eMail: ->jason.kahn@nist.gov; 10/1/23: acronym re...","36.579-9; 36.579-8",97,49,null,null,"2022-09-23","2023-09-06"]
[1882,800053,"MBMS APIs for Mission Critical Services","MBMSAPI_MCS",1,"Rel-16","S6","2017-06-05","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com",null,"New",80,41,null,null,"2018-06-06","NA"]
[1883,760051,"   Study on MBMS APIs for MC Services","FS_MBMSAPI_MC",2,"Rel-16","S6","2017-06-05","2018-06-15",1,"SP-180237",null,"Ling Zhang, TD Tech Ltd","zhangling@td-tech.com","12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100","new 23.792",76,39,null,null,"2017-06-03","2018-06-14"]
[1884,800020,"   Stage 2 of MBMS APIs for MC Services","MBMSAPI_MCS",2,"Rel-16","S6","2018-06-06","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com","6/8/18: 23.479 added;¦10/9/18: 0%->15¦7/12/18: 15%->65¦14/3/19: 65%->90; 31/5/19: 90%->100","New; 23.479",80,41,null,null,"2018-06-06","2019-05-31"]
[1885,840013,"Enhancement of 3GPP Northbound APIs ","eNAPIs",1,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: WID:CP-192184->CP-193175","29.122; 29.222; 29.522; 29.116 ",84,43,null,null,"2019-05-31","2019-12-09"]
[1886,850053,"   CT3 aspects of eNAPIs","eNAPIs",2,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 6/12/19: 50%->85; 6/12/19: WID:CP-192184->CP-193175; 26/3/20: 85%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[1887,850059,"   CT4 aspects of eNAPIs","eNAPIs",2,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[1888,800019,"Enhanced Mission Critical System Migration and Interconnection","eMCSMI",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-180379",null,"Chater-Lea, David; Motorola Solutions","david.chater-lea@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->10¦7/12/18: FCD:03/19->06/19¦14/3/19: 10%->50; 31/5/19: 50%->100. ","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[1889,810054,"Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",1,"Rel-16",null,"2018-06-06","2019-06-14",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com",null,null,80,41,null,null,"2018-09-10","NA"]
[1890,800021,"   Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180680",null,"Monnes, Peter, Harris Corporation","pmonnes at harris dot com ","10/9/18: 0%->5¦2/10/18: WID:SP-180381->SP-180680¦7/12/18: 5%->15¦14/3/19: 15%->40; 31/5/19: 40%->70; 13/9/19: 70%->100",23.283000000000001,80,41,null,null,"2018-06-06","2019-09-13"]
[1891,800016,"Stage 3 for MC Communication Interworking with Land Mobile Radio Systems","MCCI_CT",1,"Rel-16","C1","2018-06-06","2019-09-12",1,"CP-190203",null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com","10/9/18: 5%->15¦7/12/18: 15%->45¦10/12/18: FCD:12/18->06/19¦10/12/18: WID:CP-181187->CP-183247. 06/03/19: both name and acronym changed (was MCCI3)¦14/3/19: 45%->60¦18/3/19: WID:CP-183248->CP-190203¦18/3/19: FCD:019->09/19; 31/5/19: 60%->70; 13/9/19: 7 ","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482",80,41,null,null,"2018-06-06","2020-03-26"]
[1892,800032,"Mission Critical Services Security Enhancements","MCXSec",1,"Rel-16","S3","2018-06-06","2020-06-11",1,"SP-180596",null,"Woodward, Tim, Motorola Solutions, Inc",null,"10/9/18: 0%->40¦7/12/18: 40%->50¦20/3/19: FCD:019->09/19¦20/3/19: 50%->0; 31/5/19: 0%->45; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 45%->55; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 55%->75; 26/6/20: 75%->80; 12/9/20: FCD:12/03/2020->06/20; 9/4/21: 80% ",33.18,80,41,null,null,"2018-06-06","2021-04-09"]
[1893,780003,"Enhancements of Public Warning System ","ePWS",1,"Rel-16",null,"2016-09-19","2020-03-12",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[1894,730005,"   Study on enhancements of Public Warning System","FS_ePWS",2,"Rel-16","S1","2016-09-19","2017-09-14",1,"SP-160733",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->5¦2/3/17: 5%->45¦7/6/17: 45%->75¦30/6/17: 22.869 added;¦25/8/17: 75%->95¦15/12/17: 95%->100",22.869,73,37,null,null,"2016-09-19","2017-12-15"]
[1895,800052,"   Stage 1 of ePWS","ePWS",2,"Rel-16","S1","2017-12-15","2018-12-14",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[1896,810012,"   CT aspects of enhancements of Public Warning System ","ePWS",2,"Rel-16","ct","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155",null,81,41,null,null,"2018-09-06","2019-06-03"]
[1897,810053,"      Study on stages 2 and 3 of enhancements of ePWS","ePWS",3,"Rel-16","C1","2018-09-10","2019-06-14",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","7/12/18: 0%->10¦21/3/19: 10%->30; 31/5/19: 30%->85; 3/6/19: WID:CP-182228->CP-191155; 13/9/19: 85%->100","New",81,41,null,null,"2018-09-10","2019-09-13"]
[1898,810047,"      CT1 aspects of ePWS ","ePWS",3,"Rel-16","C1","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","14/3/19: 0%->30; 3/6/19: FCD:14/06/2019->03/20; 3/6/19: WID:CP-182228->CP-191155; 20/9/19: 0%->100; 6/12/19: 100%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",23.041,81,41,null,null,"2018-09-06","2020-06-26"]
[1899,810048,"      deleted- CT4 aspects of ePWS (Possible impacts)","ePWS",3,"Rel-16","C4","2018-09-06","2019-12-13",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155; 16/9/19: 0%->100",29.167999999999999,81,41,null,null,"2018-09-06","2019-09-16"]
[1900,760054,"Mobile Communication System for Railways 2","MONASTERY2",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 10%->35","New 22.289; 22.280; 22.281; 22.282; 22.179",76,42,null,null,"2017-06-03","2017-12-15"]
[1901,760005,"   Study on MONASTERY2","FS_FRMCS2",2,"Rel-16","S1","2017-06-05","2019-06-14",1,"SP-170588",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 35%->50¦16/3/18: 50%->80¦7/6/18: 80%->85¦10/9/18: FCD:06/18->06/19¦4/12/18: 85%->100","New 22.889",76,39,null,null,"2017-06-03","2018-12-04"]
[1902,790023,"   Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2","FS_FRMCS2_SA6",2,"Rel-16","S6","2018-03-15","2019-03-12",1,"SP-181133",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","19/4/18: 0%->5¦14/6/18: 5%->15¦6/8/18: 23.796 added;¦10/9/18: 15%->20¦7/12/18: 20%->65¦7/12/18: FCD:12/18->03/19¦14/3/19: 65%->100","23.cde; 23.796",79,40,null,null,"2018-03-15","2019-03-14"]
[1903,760004,"   Stage 1 of MONASTERY2","MONASTERY2",2,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","16/3/18: 35%->55¦7/6/18: 55%->70¦7/6/18: FCD:06/18->12/18¦10/9/18: 70%->75¦4/12/18: 75%->100","New 22.289; 22.280; 22.281; 22.282; 22.179",76,39,null,null,"2017-06-03","2018-12-04"]
[1904,830007,"   Application Architecture for MONASTERY2","MONASTERY2",2,"Rel-16","S6","2019-03-14","2019-06-13",1,"SP-190064",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","31/5/19: 0%->100","23.280; 23.379; 23.281; 23.282",83,42,null,null,"2019-03-14","2019-05-31"]
[1905,840009,"   CT aspects of MONASTERY2 ","MONASTERY2",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","9/12/19: WID:CP-191152->CP-193143",null,84,43,null,null,"2019-05-31","2019-12-09"]
[1906,840072,"      CT1 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/19: 0%->10; 6/12/19: 10%->50; 26/3/20: 50%->65; 26/6/20: 65%->100","24.379 ; 24.281 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.581; 24.582",84,43,null,null,"2019-05-31","2020-06-26"]
[1907,840073,"      deleted: CT3 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","2/7/20: deleted, put at 100% (was at 0)",29.164999999999999,84,43,null,null,"2019-05-31","NA"]
[1908,840092,"NR support for high speed train scenario","NR_HST",1,"Rel-16","R4","2019-06-17","2022-06-22",1,"RP-191788",null,"CMCC",null,"8/10/19: WID:RP-191512->RP-191788",null,84,43,null,null,"2019-06-26","2019-10-08"]
[1909,840192,"   Core part: NR support for high speed train scenario","NR_HST-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-191788",null,"CMCC",null,"28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[1910,840292,"   Perf. part: NR support for high speed train scenario","NR_HST-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-202320",null,"CMCC",null,"6/1/21: WID:RP-191788->RP-202320; 6/1/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-01-06"]
[1911,900050,"   UE Conformance Test Aspects - NR support for high speed train scenario ","NR_HST-UEConTest",2,"Rel-16","R5","2020-12-14","2022-06-22",1,"RP-221362","RP-221361","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-16 WI NR_HST-Core ; 7/4/21: WID:RP-202328->RP-210372; 8/4/21: 0%->39; 2/7/21: 39%->41; 13/9/21: Compl:41%->44%; ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-202328->RP-221362",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1912,800011,"Maritime Communication Services over 3GPP System","MARCOM",1,"Rel-16","S1","2016-09-19","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com",null,"22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","NA"]
[1913,730007,"   Study on Maritime Communication Services over 3GPP system","FS_MARCOM",2,"Rel-16","S1","2016-09-19","2018-06-15",1,"SP-170453",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->10¦2/3/17: 10%->15¦2/3/17: WID:SP-160556->SP-170166¦10/3/17: FCD:06/17->06/20¦21/3/17: 22.819 added;¦8/6/17: WID:SP-170166->SP-170453¦25/8/17: 15%->35¦15/12/17: 35%->55¦16/3/18: 55%->75¦7/6/18: 75%->95¦10/9/18: 95%->100",22.818999999999999,73,37,null,null,"2016-09-19","2018-09-10"]
[1914,800051,"   Stage 1 of MARCOM","MARCOM",2,"Rel-16","S1","2018-06-06","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com","10/9/18: 0%->70¦4/12/18: 70%->95¦14/3/19: 95%->100","22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","2019-03-14"]
[1915,0,"Streaming and TV","-",1,"Rel-16",null,"2016-12-01","2019-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1916,800008,"Enhancement of LTE for Efficient delivery of Streaming Service","eLSTR",1,"Rel-16","S1","2016-12-01","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn",null,"22.278; 22.115",80,41,null,null,"2018-06-06","NA"]
[1917,740001,"   Study on eLSTR","FS_eLESTR",2,"Rel-16","S1","2016-12-01","2018-03-15",1,"SP-160960",null,"China Telecommunications, XIA Xu","xiaxu@ctbri.com.cn","2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100",22.832999999999998,74,38,null,null,"2016-12-01","2018-03-16"]
[1918,800054,"   Stage 1 of eLSTR","eLSTR",2,"Rel-16","S1","2018-05-08","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn","15/6/18: FCD:06/18->09/18¦10/9/18: 90%->100","22.278; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[1919,800001,"Enhancements to Framework for Live Uplink Streaming","E_FLUS",1,"Rel-16","S4","2018-06-06","2020-07-03",0.95,"SP-180285",null,"Lo, Charles, Qualcomm Incorporated","clo@qti.qualcomm.com","10/9/18: 0%->20¦7/12/18: 20%->40¦7/3/19: 40%->45¦7/3/19: FCD:03/19->09/19; 31/5/19: 45%->55; 13/9/19: FCD:20/09/2019->12/20; 13/9/19: 55%->75; 6/12/19: 75%->85; 25/3/20: 85%->90; 25/3/20: FCD:12/12/2019->06/20; 10/6/20: 90%->100; 26/6/20: FCD:12/06/202 ","26.238; 26.939",80,41,null,null,"2018-06-06","2020-06-26"]
[1920,810003,"Coverage and Handoff Enhancements for Multimedia ","CHEM",1,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180664",null,"Nikolai Leung","nleung@qti.qualcomm.com","7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[1921,770027,"Study on QoE metrics for VR","FS_QoE_VR",1,"Rel-16","S4","2017-09-08","2019-09-20",1,"SP-170614",null,"Ericsson (Gunnar Heikkilä","gunnar.heikkila@ericsson.com","15/12/17: 26.929 added;¦15/12/17: 26.119 added;¦15/12/17: FCD:06/18->09/18¦15/12/17: 0%->10¦16/3/18: 10%->15¦7/6/18: 15%->20¦7/6/18: FCD:09/18->12/18. 14/06/18: Moved from Rel-15¦10/9/18: 20%->25¦12/3/19: 25%->55¦12/3/19: FCD:12/18->09/19; 31/5/19: 55% ","New; 26.929; 26.119",77,39,null,null,"2017-09-08","2019-05-31"]
[1922,760039,"Study on 5G enhanced Mobile Broadband Media Distribution","FS_5GMedia_Distribution",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170334",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd., ","i (dot) Bouazizi (at) Samsung (dot) com ","11/9/17: 0%->10¦15/12/17: FCD:03/18->06/20¦15/12/17: 10%->25¦16/3/18: 25%->60¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->75; 26/6/20: 75%->100; 25/9/20: 26.998 added;","26.8xx; 26.998",76,39,null,null,"2017-06-03","2020-09-25"]
[1923,820002,"Media streaming architecture ","5GMSA",1,"Rel-16","S4","2018-12-06","2019-06-12",1,"SP-180984",null,"Frédéric GABIN ","Frederic.gabin@ericsson.com ","; 31/5/19: 0%->100","26.501; 26.233 ",82,42,null,null,"2018-12-07","2019-05-31"]
[1924,840000,"VR QoE metrics ","VRQoE",1,"Rel-16","S4","2019-06-06","2020-03-12",1,"SP-190331",null,"Gunnar HEIKKILÄ ","gunnar.heikkila@ericsson.com ","22.280¦22.281¦22.282¦22.179¦22.289 ; 13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2020-03-25"]
[1925,810040,"Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",1,"Rel-16","S4","2017-06-05","2019-12-12",1,"SP-180663",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[1926,760041,"   Study on Media Handling Aspects of Conversational Services in 5G Systems","FS_5G_MEDIA_MTSI",2,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170336",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","11/9/17: 0%->5¦15/12/17: 5%->35¦16/3/18: 35%->55¦16/3/18: FCD:03/18->09/18¦7/6/18: 55%->80. 14/06/18: Moved from Rel-15¦10/9/18: 80%->100",26.919,76,39,null,null,"2017-06-03","2018-09-10"]
[1927,810002,"   Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",2,"Rel-16","S4","2018-09-06","2019-12-12",1,"SP-190640",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->35¦7/3/19: 35%->50; 31/5/19: 50%->75; 13/9/19: 75%->80; 13/9/19: FCD:13/09/2019->12/20; 19/9/19: WID:SP-180663->SP-190640; 6/12/19: 80%->90; 25/3/20: 90%->100","26.114; 26.131; 26.132; 26.223; 26.919",81,41,null,null,"2018-09-06","2020-03-25"]
[1928,770031,"Study on EVS Float Conformance Non Bit-Exact","FS_EVS_FCNBE",1,"Rel-16","S4","2017-09-08","2018-09-14",1,"SP-170618",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100","New; 26.843",77,39,null,null,"2017-09-08","2018-09-10"]
[1929,820001,"EVS Floating-point Conformance for Non Bit-Exact ","EVS_FCNBE",1,"Rel-16","S4","2018-06-06","2019-12-12",1,"SP-180983",null,"Fabrice, Plante, Intel ","fabrice.m.plante@intel.om ","¦7/3/19: 0%->25¦7/3/19: 0%->25¦7/3/19: 0%->25. CANNOT CHANGE STARTING DATE… Real one: Thu 06/12/18; 31/5/19: 25%->50; 13/9/19: 50%->80; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 80%->100",26.443999999999999,82,42,null,null,"2018-06-06","2019-12-06"]
[1930,800003,"Addition of HLG HDR to TV Video Profiles","HLG_HDR",1,"Rel-16","S4","2018-06-06","2018-09-14",1,"SP-180287",null,"Paul Szucs, Sony Europe Limited","paul.szucs@sony.com","10/9/18: 0%->100","26.116; 26.346; 26.234",80,41,null,null,"2018-06-06","2018-09-10"]
[1931,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1932,800012,"User Identities and Authentication","UIA",1,"Rel-16","S1","2017-12-15","2018-09-14",1,"SP-180328",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at",null,"22.101; 22.115",80,41,null,null,"2018-06-06","NA"]
[1933,780004,"   Study on a Layer for User Centric Identifiers and Authentication","FS_LUCIA",2,"Rel-16","S1","2017-12-15","2018-06-14",1,"SP-170995",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","16/3/18: 0%->60¦7/6/18: 60%->90¦10/9/18: 90%->100",22.904,78,40,null,null,"2017-12-15","2018-09-10"]
[1934,800050,"   Stage 1 of User Identities and Authentication","UIA",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180328",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","10/9/18: 0%->100","22.101; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[1935,810044,"Multi-device and multi-identity","MuD",1,"Rel-16",null,"2018-06-06","2020-06-15",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com",null,null,80,41,null,null,"2018-06-06","NA"]
[1936,800004,"   Stage 1 of Multi-device and multi-identity","MuD",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com","10/9/18: 85%->90¦4/12/18: 90%->100",22.172999999999998,80,41,null,null,"2018-06-06","2018-12-04"]
[1937,810010,"   CT aspects of Multi-device and multi-identity","MuD",2,"Rel-16","ct","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","9/12/19: WID:CP-182227->CP-193273; 25/3/20: WID:CP-193273->CP-200148",null,81,41,null,null,"2018-06-06","2020-03-25"]
[1938,810045,"      CT1 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C1","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->10¦14/3/19: 10%->15; 31/5/19: 15%->35; 13/9/19: 35%->65; 6/12/19: 65%->85; 25/3/20: FCD:14/06/2019->03/20; 26/3/20: 85%->100; 2/7/20: FCD:25/03/2020->06/20","24.173; 24.229; 24.167",81,41,null,null,"2018-06-06","2020-07-02"]
[1939,810046,"      CT3 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C3","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->5; 13/9/19: 5%->95; 6/12/19: 95%->98; 26/3/20: 98%->100; 2/7/20: FCD:25/03/2020->06/20",29.164999999999999,81,41,null,null,"2018-06-06","2020-07-02"]
[1940,0,"Slicing","-",1,"Rel-16",null,"2017-09-08","2017-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1941,830103,"Enhancement of Network Slicing","eNS",1,"Rel-16",null,"2018-03-15","2022-09-12",0.94,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com",null,null,83,42,null,null,"2018-12-06","NA"]
[1942,790011,"   Study on Enhancement of Network Slicing","FS_eNS",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180503",null,"ZTE, Tricci So ","tso at ztetx dot com","7/6/18: 0%->10¦15/6/18: WID:SP-180121->SP-180503¦6/8/18: 23.740 added;¦10/9/18: 10%->50¦7/12/18: 50%->85¦7/12/18: 85%->¦14/3/19: 85%->100","new; 23.740",79,40,null,null,"2018-03-15","2019-03-14"]
[1943,820023,"   Stage 2 of eNS","eNS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com","14/3/19: 0%->60; 31/5/19: 60%->100",null,82,42,null,null,"2018-12-06","2019-05-31"]
[1944,830011,"   CT aspects of eNS","eNS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","2/7/20: WID:CP-190196->CP-201161",null,83,42,null,null,"2018-12-06","2020-07-02"]
[1945,830052,"      CT1 aspects of eNS","eNS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","13/9/19: 0%->40; 6/12/19: 40%->85; 26/3/20: 85%->95; 26/6/20: 95%->97; 13/9/20: 97%->100",24.501000000000001,83,42,null,null,"2018-12-06","2020-09-13"]
[1946,830053,"      CT3 aspects of eNS","eNS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","6/12/19: 0%->80; 26/3/20: 80%->98; 26/6/20: 98%->100","29.061; 29.561",83,42,null,null,"2018-12-06","2020-06-26"]
[1947,830054,"      CT4 aspects of eNS","eNS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","31/5/19: 0%->30; 13/9/19: 30%->50; 6/12/19: 50%->95; 26/3/20: 95%->85 (went down); 26/6/20: 85%->100","29.502; 29.503; 29.505; 29.509; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[1948,810034,"   Study on Security aspects of Enhancement of Network Slicing","FS_eNS_SEC",2,"Rel-16","S3","2018-09-06","2020-03-12",1,"SP-180692",null,null,"Suresh.p.nair@nokia.com","7/12/18: 0%->15¦20/3/19: 15%->65¦20/3/19: FCD:019->06/19; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New",81,41,null,null,"2018-09-06","2020-06-26"]
[1949,850022,"   Security aspects of Enhanced Network Slicing ","eNS",2,"Rel-16","S3","2019-09-19","2021-06-11",1,"SP-190712",null,"Suresh.p.nair@nokia.com ",null,"; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 30%->95; 12/9/20: 95%->97; 19/3/21: FCD:12/06/2020->06/21; 11/6/21: 97%->100","New ",85,43,null,null,"2019-09-13","2021-06-11"]
[1950,910099,"   UE Conformance Test Aspects - Enhancement of Network Slicing ","eNS-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-12",0.67,"RP-211443","R5-220262","CMCC ",null,"tested: CT1 and SA3 REL-16 WI eNS (Enhancement of Network Slicing); compare REL-17 SI FS_NR_slice; 2/7/21: 0%->15; 13/9/21: Compl:15%->47%; ; 6/1/22: 47%->100 ; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1951,810051,"Business Role Models for Network Slicing ","BRMNS",1,"Rel-16","S1","2017-09-08","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com",null,22.260999999999999,81,41,null,null,"2018-09-06","NA"]
[1952,770005,"   Study on Business Role Models for Network Slicing ","FS_BMNS",2,"Rel-16","S1","2017-09-08","2018-09-14",1,"SP-180169",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100","New; 22.830",77,39,null,null,"2017-09-08","2018-12-04"]
[1953,810015,"   Business Role Models for Network Slicing ","BRMNS",2,"Rel-16","S1","2018-09-06","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","10/9/18: 0%->95¦4/12/18: 95%->100",22.260999999999999,81,41,null,null,"2018-09-06","2018-12-04"]
[1954,810022,"Study on tenancy concept in 5G networks and network slicing management","FS_TENANCYC",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180815",null,"ZHU, Lei (Huawei","Lei.zhu@huawei.com ","7/12/18: 0%->20¦14/3/19: 20%->26; 31/5/19: 26%->40; 13/9/19: 40%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1955,810031,"Enhancement of performance assurance for 5G networks including network slicing","5G_SLICE_ePA",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2019-05-31"]
[1956,850055,"   Overall aspects of 5G_SLICE_ePA","5G_SLICE_ePA",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70; 13/9/19: 70%->85; 13/9/19: 85%->; 26/3/20: 85%->97; 28/6/20: 97%->100","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2020-06-28"]
[1957,850029,"   KPI reporting ","5G_SLICE_ePA-KPI",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190881",null,"ZHU, Weihong, ZTE Corporation ","zhu.weihong@zte.com.cn ","; 26/3/20: 0%->100","28.550; 28.554; 28.622; 28.532 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1958,820029,"Study on Charging Aspects of Network Slicing ","FS_NETSLICE_CH",1,"Rel-16","S5","2018-12-13","2019-12-12",1,"SP-181065",null,"Chen Shan, Huawei","chenshan@huawei.com ","14/3/19: 0%->30¦14/3/19: FCD:06/19->09/19; 31/5/19: 30%->45; 13/9/19: 45%->85; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 85%->100",null,82,42,null,null,"2018-12-07","2019-12-06"]
[1959,0,"Other cross-TSG Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1960,760003,"Provision of Access to Restricted Local Operator Services by Unauthenticated UEs","PARLOS",1,"Rel-16",null,"2016-12-01","2019-12-13",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16","22.115; 22.101; 22.228",76,38,null,null,"2017-06-03","2017-06-07"]
[1961,740002,"   Study on Stage 1 of PARLOS","FS_PARLOS",2,"Rel-15","S1","2016-12-01","2018-09-10",1,"SP-160904",null,"Covell, Betsy","betsy.covell@nokia.com","1/12/16: 0%->75¦2/3/17: 75%->100¦10/9/18: FCD:03/17->09/18",22.82,74,38,null,null,"2016-12-01","2018-09-10"]
[1962,760046,"   Study on Stage 2 for PARLOS","FS_PARLOS_SA2",2,"Rel-16","S2","2017-06-05","2018-09-14",1,"SP-180501",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com","11/9/17: 0%->20¦16/3/18: FCD:12/17->12/18.¦16/3/18: 20%->45¦23/3/18: WID:SP-170382->SP-180116¦23/3/18: FCD:12/18->06/18¦7/6/18: 45%->70¦15/6/18: WID:SP-180116->SP-180501¦15/6/18: FCD:06/18->09/18¦10/9/18: 70%->100",23.715,76,39,null,null,"2017-06-03","2018-09-10"]
[1963,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[1964,760071,"   Stage 1 of PARLOS","PARLOS",2,"Rel-16","S1","2017-05-10","2017-06-08",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","7/6/17: 0%->100","22.115; 22.101; 22.228",76,39,null,null,"2017-06-03","2017-06-07"]
[1965,810008,"   Stage 2 of PARLOS","PARLOS",2,"Rel-16","S2","2018-09-06","2019-03-15",1,"SP-180738",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com)","14/3/19: 0%->95; 31/5/19: 95%->100","23.401; 23.203; 23.221; 23.228; 23.167",81,41,null,null,"2018-09-06","2019-05-31"]
[1966,830012,"   CT aspects of PARLOS","PARLOS",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com",null,null,83,42,null,null,"2018-09-06","NA"]
[1967,830062,"      CT1 aspects of PARLOS","PARLOS",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->80; 13/9/19: 80%->95; 6/12/19: 95%->98; 26/3/20: 98%->100","24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007",83,42,null,null,"2018-09-06","2020-03-26"]
[1968,830063,"      CT3 aspects of PARLOS","PARLOS",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","13/9/19: 0%->95; 26/3/20: 95%->100","29.212; 29.213; 29.214",83,42,null,null,"2018-09-06","2020-03-26"]
[1969,830064,"      CT4 aspects of PARLOS","PARLOS",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","6/12/19: 0%->100","29.228; 29.229; 29.274",83,42,null,null,"2018-09-06","2019-12-06"]
[1970,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[1971,860015,"   Security Aspects of PARLOS ","PARLOS",2,"Rel-16","S3","2019-12-06","2019-12-13",1,"SP-191126",null,"Schumacher, Greg, Sprint ","Gregory.schumacher@sprint.com ","; 6/12/19: 0%->100",33.401000000000003,86,44,null,null,"2019-12-06","2019-12-06"]
[1972,820043,"Enhancing Topology of SMF and UPF in 5G Networks","ETSUN",1,"Rel-16",null,"2017-09-08","2020-03-12",1,"SP-181116",null,null,null,null,null,82,42,null,null,"2018-12-05","NA"]
[1973,770039,"   Study on ETSUN","FS_ETSUN",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180731",null,"Laurent Thiebaut (Nokia)","Laurent.thiebaut@nokia.com","15/12/17: 23.726 added;¦16/3/18: 0%->25¦7/6/18: 25%->40¦10/9/18: 40%->65¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170743->SP-180731¦2/10/18: FCD:12/18->12/18¦7/12/18: 65%->100",23.725999999999999,77,39,null,null,"2017-09-08","2018-12-07"]
[1974,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[1975,830002,"   CT aspects of ETSUN","ETSUN",2,"Rel-16","ct","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,83,42,null,null,"2018-12-05","NA"]
[1976,830055,"      CT3 aspects of ETSUN","ETSUN",3,"Rel-16","C3","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","13/9/19: 0%->80; 6/12/19: 80%->85; 26/3/20: 85%->100","29.508; 29.561",83,42,null,null,"2018-12-05","2020-03-26"]
[1977,830056,"      CT4 aspects of ETSUN","ETSUN",3,"Rel-16","C4","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","31/5/19: 0%->25; 13/9/19: 25%->95; 6/12/19: 95%->100","29.244; 29.502; 29.510; 29.518; 29.281",83,42,null,null,"2018-12-05","2019-12-06"]
[1978,850024,"   Charging aspects of ETSUN ","ETSUN",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190880",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 6/12/19: 0%->70; 26/3/20: 70%->100","32.255; 32.291; 32.298 ",85,43,null,null,"2019-09-13","2020-03-26"]
[1979,820044,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture","ATSSS",1,"Rel-16",null,"2017-06-05","2023-12-12",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com",null,"23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","NA"]
[1980,760052,"   Study on ATSSS","FS_ATSSS",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180732",null,"So, Tricci, ZTE","tso@ztetx.com","11/9/17: 0%->100¦14/9/17: 100%->10¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 10%->20¦7/6/18: 20%->40¦10/9/18: 40%->70¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170411->SP-180732¦2/10/18: FCD:12/18->12/18¦7/12/18: 70%->100","new 23.793",76,39,null,null,"2017-06-03","2018-12-07"]
[1981,820021,"   Stage 2 of ATSSS","ATSSS",2,"Rel-16","S2","2018-12-14","2019-06-21",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com","14/3/19: 0%->45; 31/5/19: 45%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1982,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[1983,830057,"      CT1 aspects of ATSSS","ATSSS",3,"Rel-16","C1","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->55; 6/12/19: 55%->65; 26/3/20: 65%->70; 26/6/20: 70%->100","24.501; 24.526; 24.502",83,42,null,null,"2018-12-06","2020-06-26"]
[1984,830058,"      CT3 aspects of ATSSS","ATSSS",3,"Rel-16","C3","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->50; 13/9/19: 50%->55; 6/12/19: 55%->60; 26/3/20: 60%->100","29.512; 29.513",83,42,null,null,"2018-12-06","2020-03-26"]
[1985,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[1986,840999,"      (IETF) TCP Extensions for Multipath Operation with Multiple Addresses (draft-ietf-mptcp-rfc6824bis)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"23/4/20: 80%->100; 9/4/21: RFC 8684 added;","RFC 8684",84,43,null,null,"2019-06-26","2021-04-09"]
[1987,840998,"      (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"23/4/20: 30%->90; 25/9/20: 90%->100; 9/4/21: RFC 8803 added;","RFC 8803",84,43,null,null,"2019-06-26","2021-04-09"]
[1988,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1989,970076,"   UE Conformance Test Aspects - Access Traffic Steering, Switch and Splitting support in 5G system ","ATSSS-UEConTest",2,"Rel-16","R5","2022-09-08","2023-12-12",1,"RP-222547","RP-230078","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->5%; Stat Rep: ->RP-222738; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->55%; Stat Rep: RP-222738->RP-230078; ...",null,97,49,null,null,"2022-09-23","2023-06-07"]
[1990,810041,"Single radio voice continuity from 5GS to 3G","5G_SRVCC",1,"Rel-16",null,"2018-03-15","2021-12-10",1,"SP-180737",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn",null,"23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","NA"]
[1991,790010,"   Study for single radio voice continuity from 5GS to 3G","FS_5G-SRVCC",2,"Rel-16","S2","2018-03-15","2018-06-15",1,"SP-180239",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","7/6/18: 0%->80¦6/8/18: 23.756 added;¦10/9/18: 80%->100",23.756,79,40,null,null,"2018-03-15","2018-09-10"]
[1992,810007,"   Single radio voice continuity from 5GS to 3G","5G_SRVCC",2,"Rel-16","S2","2018-09-06","2019-03-14",1,"SP-180897",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","14/3/19: 0%->100","23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","2019-03-14"]
[1993,820008,"   Security aspects of single radio voice continuity from 5GS to UTRAN ","5GS_UTRAN_SEC",2,"Rel-16","S3","2018-12-13","2019-06-12",1,"SP-190703",null,"Feng Gao, China Unicom ","gaofeng149@chinaunicom.cn ","20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703","33.501; 33.401; 33.220",82,42,null,null,"2018-12-13","2019-09-20"]
[1994,820069,"   RAN aspects of 5G_SRVCC","SRVCC_NR_to_UMTS",2,"Rel-16","R2","2018-12-15","2019-12-15",1,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: WID:RP-190713->RP-200151",null,82,42,null,null,"2019-01-16","2020-03-26"]
[1995,820169,"      Core part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Core",3,"Rel-16","R2","2018-12-15","2019-12-15",1,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-03-26"]
[1996,830270,"      Perf. part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-200151",null,"China Unicom",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1997,890046,"      UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G ","SRVCC_NR_to_UMTS-UEConTest",3,"Rel-16","R5","2020-09-17","2021-12-10",1,"RP-210400",null,"China Unicom ",null,"tested: REL-16 WI SRVCC_NR_to_UMTS-Core ; 7/4/21: WID:RP-201794->RP-210400; 8/4/21: 0%->31; 8/4/21: FCD:08/09/2021->09/21; 2/7/21: FCD:Fri 10/09/->12/21; 2/7/21: 31%->85; 6/1/22: 85%->100",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1998,840004,"   CT aspect of 5G_SRVCC","5G_SRVCC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","6/12/19: WID:CP-191062->CP-193014",null,84,43,null,null,"2019-05-31","2019-12-06"]
[1999,840058,"      CT1 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","24.501; 24.237; 24.008; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[2001,840059,"      CT4 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100","29.303; 29.503; 29.504; 29.505; 29.518; 29.274",84,43,null,null,"2019-05-31","2020-03-26"]
[2003,800034,"Study on Security Aspects of the 5G Service Based Architecture","FS_SBA_Sec",1,"Rel-16","S3","2018-06-06","2020-03-12",1,"SP-180598",null,"Hans Christian Rudolph, Deutsche Telekom AG","hans-christian.rudolph@telekom.de","6/8/18: 33.855 added;¦10/9/18: 65%->75¦7/12/18: 75%->76¦20/3/19: 76%->65¦20/3/19: FCD:018->09/19; 31/5/19: 65%->75; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New; 33.855",80,41,null,null,"2018-06-06","2020-06-26"]
[2006,820022,"   Stage 2 of 5G_eSBA","5G_eSBA",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181125",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2010,850016,"   Security for 5G_eSBA","5G_eSBA",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190899",null,"Nagendra Bykampadi, Nokia ","nagendra.bykampadi@nokia.com ","; 6/12/19: 0%->45; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 45%->70; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 70%->95; 12/9/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-09-12"]
[2013,830028,"   Stage 2 of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","S2","2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,"31/5/19: 0%->100","23.501; 23.502; 23.503; 23.228",83,42,null,null,"2019-03-14","2019-05-31"]
[2016,840063,"      CT3 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.513; 29.514",84,43,null,null,"2019-05-31","2020-03-26"]
[2017,840064,"      CT4 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->25; 6/12/19: 25%->50; 26/3/20: 50%->90; 26/6/20: 90%->100","29.510; 29.571; 23.380",84,43,null,null,"2019-05-31","2020-06-26"]
[2020,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-21",1,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com 9/9/22: Compl:89%->97%; 29/3/23: 97%-...",null,88,45,null,null,"2020-07-28","2023-03-29"]
[2024,830004,"   CT Aspects of E2E_DELAY","E2E_DELAY",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2027,830068,"      CT4 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100","23.334; 29.334; 29.238; 23.333; 29.333",83,42,null,null,"2018-09-06","2019-05-31"]
[2030,830022,"   Security aspects of eCAPIF","eCAPIF",2,"Rel-16","S3","2019-03-07","2019-12-12",1,"SP-1901240",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","31/5/19: 0%->30; 31/5/19: 0%->30; 31/5/19: 0%->30; 13/9/19: 30%->90; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 90%->100",33.122,83,42,null,null,"2019-03-14","2019-12-06"]
[2034,830029,"   Stage 2 of UDICOM","UDICOM",2,"Rel-16","S2","2019-03-14","2019-06-14",1,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ","6/6/19: 0%->100; 26/6/19: 23.632 added;","23.501; 23.502; 23.228; 23.632",83,42,null,null,"2019-03-14","2019-06-26"]
[2037,800036,"Study on authentication and key management for applications based on 3GPP credential in 5G","FS_AKMA",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180443",null,"Jin Peng, China Mobile","pengjin@chinamobile.com","6/8/18: 33.835 added;¦7/12/18: 5%->20¦20/3/19: 20%->60¦20/3/19: FCD:019->09/19; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->12/19; 6/12/19: 70%->95; 26/6/20: 95%->100","New; 33.835",80,41,null,null,"2018-06-06","2020-06-26"]
[2040,860058,"Addition of wider channel bandwidth in NR band n3","NR_n3_BW",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 26/3/20: WID:RP-193056->RP-200305",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2041,860158,"   Core part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2044,860159,"   Core part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2048,830175,"   Core part: UE Power Saving in NR","NR_UE_pow_sav-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-200494",null,"CATT",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2051,800172,"   Core part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16-Core",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2054,800073,"   Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦16/1/19: WID:RP-181426->RP-182256¦26/3/19: WID:RP-182256->RP-190689; 26/6/19: WID:RP-190689->RP-191194; 8/10/19: WID:RP-191194->RP-191812; 14/1/20: WID:RP-191812->RP-192445; 26/3/20: WID:RP-192445->RP-200101; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2058,800174,"      Core part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2061,830083,"   UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations","NR_CADC_NR_LTE_DC_R16-UEConTest",2,"Rel-16","R5","2019-03-01","2023-12-12",0.42,"RP-190321","RP-232240","Dan SONG, Jakub Kolodziej, Yu SHI, CMCC, Ericsson, China Unicom","songdan@chinamobile.com, jakub.kolodziej@ericsson.com, shiyu19@chinaunicom.cn","8/10/19: WID:RP-190321->RP-191772; 28/7/20: WID:RP-191772->RP-200759; 8/10/20: 0%->6; 8/10/20: FCD:01/06/2020->06/21; 8/4/21: 6%->6; 2/7/21: FCD:Fri 11/06/->12/21; 2/7/21: 6%->7 ; 22/3/22: Co ; 20/6/22: Rapporteur: CMCC->Dan SONG, Leif Mattisson, Y...",null,83,42,null,null,"2019-03-26","2023-09-06"]
[2062,830095,"   Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200918",null,"CATT",null,"26/6/19: WID:RP-190692->RP-191153; 8/10/19: WID:RP-191153->RP-192245; 14/1/20: WID:RP-192245->RP-193206; 26/3/20: WID:RP-193206->RP-200238; 28/7/20: WID:RP-200238->RP-200918",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2065,830096,"   Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"26/6/19: WID:RP-190693->RP-191566; 8/10/19: WID:RP-191566->RP-191824; 14/1/20: WID:RP-191824->RP-192617; 26/3/20: WID:RP-192617->RP-200171; 28/7/20: WID:RP-200171->RP-200673",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2068,831000,"New bands for New Radio",null,1,"Rel-16","R4","2018-06-15","2022-12-01",0.99,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[2072,800277,"      Perf. part: Band 65 for New Radio","NR_band_n65-Perf",3,"Rel-16","R4","2018-06-15","2018-12-14",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2075,820273,"      Perf. part: Introduction of NR band n18","NR_n18-Perf",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2078,830271,"      Perf. part: Introduction of NR band n48","NR_n48-Perf",3,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190140",null,"Nokia",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2082,830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2085,830097,"   Introduction of NR band n259","NR_n259",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-200249",null,"Ericsson",null,"26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2086,830197,"      Core part: Introduction of NR band n259","NR_n259-Core",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2089,850167,"      Core part: Introduction of NR band n26","NR_n26-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2092,840197,"      Core part: Introduction of NR supplementary DL band n29","NR_n29-Core",3,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: 0%->100",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2096,850268,"      Perf. part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2099,860256,"      Perf. part: Introduction of band n53","NR_n53-Perf",3,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2102,830187,"      Core part: RF requirements for NR FR1","NR_RF_FR1-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-193266",null,"Huawei",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2106,830188,"      Core part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200124",null,"China Telecom",null,"8/10/19: 38.883 added;; 28/7/20: 0%->100",38.883000000000003,83,42,null,null,"2019-03-26","2020-07-28"]
[2109,830089,"   NR RF requirement enhancements for frequency range 2 (FR2)","NR_RF_FR2_req_enh",2,"Rel-16","R4","2019-03-01","2023-09-22",0.99,"RP-201606",null,"Nokia",null,"26/6/19: WID:RP-190761->RP-191290; 8/10/19: WID:RP-191290->RP-192227; 14/1/20: WID:RP-192227->RP-192653; 26/3/20: WID:RP-192653->RP-200246; 28/7/20: WID:RP-200246->RP-200668; 25/9/20: WID:RP-200668->RP-201606",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2110,830189,"      Core part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200668",null,"Nokia",null,"8/10/19: 38.831 added;; 25/9/20: 0%->100",38.831000000000003,83,42,null,null,"2019-03-26","2020-09-25"]
[2113,830092,"   Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5","NR_SUL_UL_n5",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2116,820074,"   Adding wider channel bandwidths in NR band n7","NR_n7_BW",2,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2120,830293,"      Perf. part: Addition of wider channel bandwidth in NR band n38","NR_n38_BW-Perf",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191472",null,"Huawei",null,"14/1/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-01-14"]
[2123,850263,"      Perf. part: Addition of further channel bandwidths in NR band 38","NR_n38_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192513",null,"Ericsson",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2127,820076,"   Adding wider channel bandwidths in NR band n50","NR_n50_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[2130,850164,"      Core part: Addition of wider channel bandwidths in NR band n75","NR_n75_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192216",null,"Ericsson",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2133,850165,"      Core part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2134,850265,"      Perf. part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2137,850266,"      Perf. part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2140,850269,"      Perf. part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[2144,800185,"   Core part: Enhancements on MIMO for NR","NR_eMIMO-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-200474",null,"Samsung",null,"25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[2147,800087,"NR mobility enhancements","NR_Mob_enh",1,"Rel-16","R2","2018-06-15","2022-09-22",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 8/10/19: WID:RP-190489->RP-192277; 14/1/20: WID:RP-192277->RP-192534",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2151,820068,"2-step RACH for NR","NR_2step_RACH",1,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 8/10/19: WID:RP-190711->RP-192330; 26/3/20: WID:RP-192330->RP-200085",null,82,42,null,null,"2019-01-16","2020-03-26"]
[2154,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-22",1,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[2157,890043,"   UE Conformance Test Aspects - SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR ","NR_SON_MDT-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-210377","RP-221368","Wenjia DONG, Leif Mattisson, CMCC, Ericsson","dongwenjia@chinamobile.com, leif.mattisson@ericsson.com","tested: REL-16 WI NR_SON_MDT-Core ; 7/4/21: WID:RP-201625->RP-210377; 8/4/21: 0%->37; 2/7/21: 37%->71; 13/9/21: Compl:71%->85%; ; 20/6/22: Rapporteur: CMCC->Wenjia DONG, Leif Mattisson, CMCC, Ericsson; Rap eMail: ->dongwenjia@chinamobile.com, ...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2158,810030,"Study on Self-Organizing Networks (SON) for 5G","FS_SON_5G",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180827",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com ","7/12/18: 0%->10¦14/3/19: 10%->40; 31/5/19: 40%->50; 6/12/19: 50%->100","New",81,41,null,null,"2018-09-06","2019-12-06"]
[2161,840193,"   Core part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-210590",null,"CATT",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[2165,890048,"   UE Conformance Test Aspects - NR performance requirement enhancement ","NR_perf_enh-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-202557","RP-221294","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","tested: REL-16 WI NR_perf_enh-Perf ; 6/1/21: WID:RP-201941->RP-202557; Qualcomm -> China Telecom; 8/4/21: 0%->15; 2/7/21: 15%->18; 13/9/21: Compl:18%->21%; ; 20/6/22: Rapporteur: Qualcomm -> China Telecom->Wu Jingzhou, Balasubramanian Vijay, C...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2168,840295,"   Perf. part: NR RRM enhancement","NR_RRM_enh-Perf",2,"Rel-16","R4","2019-06-17","2020-06-15",1,"RP-202655",null,"Intel",null,"6/1/21: WID:RP-201883->RP-202655; 7/4/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-04-07"]
[2171,840196,"   Core part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2175,840298,"   Perf. part: Addition of wider channel bandwidth in NR band n1","NR_n1_BW-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-192009",null,"Ericsson",null,"26/3/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-03-26"]
[2178,841000,"Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2181,841001,"Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[2182,841101,"   Core part: Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex-Core",2,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[2185,841102,"   Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-Core",2,"Rel-16","R4","2019-07-31","2020-03-12",0,"RP-192093",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093",null,84,43,null,null,"2019-07-31","2019-10-08"]
[2189,0,"Release 16 Features impacting both LTE and NR","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2192,860055,"High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","ENDC_UE_PC2_FDD_TDD",1,"Rel-16","R4","2019-12-16","2021-12-17",1,"RP-193244",null,"China Unicom",null,"affects: LTE, NR. no Perf. part",null,86,44,null,null,"2020-02-18","NA"]
[2195,860057,"Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 26/3/20: WID:RP-192784->RP-200228; 28/7/20: WID:RP-200228->RP-200905",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2199,860160,"   Core part: LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[2202,800288,"   Perf. part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements","LTE_NR_DC_CA_enh-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200791",null,"Ericsson",null,"26/3/19: WID:RP-181469->RP-190452; 2/7/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-07-02"]
[2205,820061,"   Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","FS_ENDC_UE_PC2_FDD_TDD",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-192268",null,"China Unicom",null,"EN-DC = E-UTRA-NR Dual Connectivity¦TR 37.8xx¦26/3/19: WID:RP-182895->RP-190167; 8/10/19: WID:RP-190167->RP-192268; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[2206,820179,"   Core part: High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-Core",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[2209,790054,"eNB(s) Architecture Evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo",1,"Rel-16","R3","2018-03-15","2019-12-13",1,"RP-192917",null,"China Unicom",null,"follow-up WI of REL-15 SI FS_LTE_arch_evo; 14/1/20: WID:RP-180531->RP-192917",null,79,40,null,null,"2018-03-27","2020-01-14"]
[2213,800078,"29 dBm UE Power Class for LTE band 41 and NR Band n41","LTE_NR_B41_Bn41_PC29dBm",1,"Rel-16","R4","2018-06-15","2022-12-01",0.99,"RP-201134",null,"Sprint",null,"no Perf. part¦26/3/19: WID:RP-181655->RP-190502; 14/1/20: WID:RP-190502->RP-192738; 28/7/20: WID:RP-192738->RP-201134",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2216,800058,"Dual Connectivity (EN-DC) ",null,1,"Rel-16",null,"2018-06-15","2019-12-13",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2219,800266,"      Perf. part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2223,800068,"   Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200657",null,"Ericsson",null,"basket WI¦TR 37.716-03-01¦16/1/19: WID:RP-181407->RP-182257¦26/3/19: WID:RP-182257->RP-190159; 26/6/19: WID:RP-190159->RP-191195; 8/10/19: WID:RP-191195->RP-191813; 14/1/20: WID:RP-191813->RP-192446; 26/3/20: WID:RP-192446->RP-200102; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2226,800069,"   Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦16/1/19: WID:RP-181001->RP-182534¦26/3/19: WID:RP-182534->RP-190294; 26/6/19: WID:RP-190294->RP-191205; 8/10/19: WID:RP-191205->RP-191728; 14/1/20: WID:RP-191728->RP-192768; 26/3/20: WID:RP-192768->RP-200134; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2227,800169,"      Core part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2230,800170,"      Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2233,800171,"      Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2237,790157,"   Core part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Core",2,"Rel-16","R4","2018-03-15","2018-12-14",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: 0%->100",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[2240,800059,"LTE intra-band Carrier Aggregation (CA)",null,1,"Rel-16",null,"2018-06-15","2022-12-21",0.82,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2242,800160,"      Core part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦TR 36.716-01-01¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2246,800261,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2249,800262,"      Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182553->; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2250,800063,"   Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201238",null,"Nokia",null,"basket WI¦TR 36.716-04-01¦16/1/19: WID:RP-181408->RP-182330¦26/3/19: WID:RP-182330->RP-190138; 26/6/19: WID:RP-190138->RP-190906; 8/10/19: WID:RP-190906->RP-191730; 14/1/20: WID:RP-191730->RP-192423; 26/3/20: WID:RP-192423->RP-200157; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2253,800064,"   Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2256,800065,"   Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200740",null,"LG Electronics",null,"basket WI¦TR 36.716-00-02¦16/1/19: WID:RP-180778->RP-182301¦26/3/19: WID:RP-182301->RP-190150; 26/6/19: WID:RP-190150->RP-190946; 8/10/19: WID:RP-190946->RP-191743; 14/1/20: WID:RP-191743->RP-192586; 26/3/20: WID:RP-192586->RP-200510; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2260,830076,"LTE-based 5G terrestrial broadcast","LTE_terr_bcast",1,"Rel-16","R1","2018-06-15","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"8/10/19: WID:RP-190732->RP-191924; 8/10/19: 36.276 added;; 14/1/20: WID:RP-191924->RP-193050","36.276; 36.476",83,42,null,null,"2019-03-26","2020-01-14"]
[2263,830276,"   Perf. part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Perf",2,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2266,830294,"   Perf. part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Perf",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2270,800175,"      Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2273,800076,"   Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2",2,"Rel-16","R4","2018-06-15","2021-09-21",1,"RP-202523","RP-211864","Ericsson",null,"basket WI¦no Perf. part¦16/1/19: WID:RP-181007->RP-182769¦26/3/19: WID:RP-182769->RP-190333; 14/1/20: WID:RP-190333->RP-192454; 26/3/20: WID:RP-192454->RP-200154; 13/9/21: Compl:86%->100% ; ",null,80,41,null,null,"2018-06-27","2021-09-13"]
[2274,800176,"      Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201201",null,"Ericsson",null,"basket WI¦no Perf. part¦26/3/19: WID:RP-182769->RP-190333; 28/7/20: WID:RP-200154->RP-201201; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2277,800179,"   Core part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Core",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,"14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2280,800182,"   Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Core",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2284,800186,"   Core part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2287,820171,"   Core part: Transfer of Iuant interface specifications from 25-series to 37-series","Iuant_transfer-Core",2,"Rel-16","R3","2018-12-13","2019-03-18",1,"RP-190160",null,"Huawei",null,"administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf .",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2291,800189,"   Core part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2294,820078,"410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR",1,"Rel-16","R4","2018-12-13","2020-12-17",1,"RP-191287",null,"Nokia",null,"26/6/19: WID:RP-182898->RP-191287",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2297,890041,"   UE Conformance Test Aspects - 410-430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe (Bands 87 and 88) ","LTE410_Europe_PPDR-UEConTest",2,"Rel-16","R5","2020-09-17","2020-12-17",1,"RP-201479",null,"Nokia ",null,"tested: REL-16 WI LTE410_Europe_PPDR-Core ; 6/1/21: 0%->100",null,89,45,null,null,"2020-09-25","2021-01-06"]
[2298,850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2301,0,"All other Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2304,880001,"Removal of H.263 and MPEG-4 Visual from 3GPP Services","RM_H263_MP4V",1,"Rel-16","S4","2020-06-25","2020-09-16",1,"SP-200400",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","26.140; 26.114; 26.244; 26.346; 26.234; 26/6/20: 0%->60; 12/9/20: 60%->100",null,88,45,null,null,"2020-06-25","2020-09-12"]
[2308,840066,"Volume Based Charging Aspects for VoLTE","VBCLTE",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50","32.251; 32.260; 32.298; 32.299",84,43,null,null,"2018-09-06","2019-03-14"]
[2311,840067,"      Stopped - CT1 aspects of VBCLTE","VBCLTE",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191110",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/20: 0%->100",24.228999999999999,84,43,null,null,"2019-05-31","2020-07-02"]
[2315,850009,"   Architecture enhancements for the support of Integrated access and backhaul (IAB) ","IABARC",2,"Rel-16","S2","2019-09-19","2020-03-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-09-13"]
[2318,880059,"      CT1 aspects of IABARC ","IABARC",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP201074",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: 0%->100","24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 ",85,43,null,null,"2019-09-13","2020-07-02"]
[2321,850020,"   Security for IAB ","NR_IAB",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190902",null,"Rajavelsamy Rajadurai, Samsung ","rajvel{@]samsung.com ","; 6/12/19: 0%->65; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[2322,860013,"User Plane Gateway Function for Inter-PLMN Security ","UPGF",1,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191123",null,"Steve Kohalmi, Juniper Networks ","skohalmi@juniper.net ","; 6/12/19: 0%->90; 25/3/20: 90%->100",33.500999999999998,86,44,null,null,"2019-12-06","2020-03-25"]
[2325,810023,"Energy efficiency of 5G","EE_5G",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-191193",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com ","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->45; 13/9/19: 45%->70; 12/12/19: WID:SP-180819->SP-191193; 12/12/19: FCD:13/12/2019->03/20; 26/3/20: 70%->95; 28/6/20: 95%->100","28.540; 28.541; 28.552; 28.554",81,41,null,null,"2018-09-06","2020-06-28"]
[2329,790015,"Security Assurance Specification for 5G ","SCAS_5G",1,"Rel-16","S3","2018-03-15","2019-09-13",1,"SP-180689",null,"Marcus Wong, Huawei Technologies ","mwong@huawei.com","27/3/18: added: 33.514¦33.513¦33.511¦33.512¦33.515 ¦6/8/18: 33.511 to 515 added;¦10/9/18: 0%->10¦2/10/18: WID:SP-180238->SP-180689¦7/12/18: 10%->20¦20/3/19: 20%->60; 31/5/19: 60%->75; 13/9/19: 75%->100","33.216; 33.926; 33.515; 33.511; 33.512; 33.513; 33.514; 33.515",79,40,null,null,"2018-03-15","2019-09-13"]
[2332,840014,"   CT aspects of xBDT","xBDT",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","17/9/19: WID:CP-191113->CP-192182",null,84,43,null,null,"2019-05-31","2019-09-17"]
[2335,850057,"      CT4 aspects of xBDT","xBDT",3,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","26/3/20: 0%->100",null,85,43,null,null,"2019-05-31","2020-03-26"]
[2339,790019,"Usage of CAPIF for xMB API","CAPIF4xMB",1,"Rel-16","S4","2018-03-15","2018-12-14",1,"SP-180031",null,"Thorsten Lohmar, Ericsson LM ","Thorsten.lohmar@ericsson.com","7/6/18: 0%->25¦6/8/18: 26.348 added;¦10/9/18: 25%->40¦7/12/18: 40%->100","26.346; new; 26.348",79,40,null,null,"2018-03-15","2018-12-07"]
[2342,800005,"Inter-RAT Mobility requirements for real time service","MOBRT",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180592",null,"Yang Xu, Oppo","xuyang@oppo.com","10/9/18: 70%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-09-10"]
[2345,810025,"Network policy management for mobile networks based on NFV scenarios","NETPOL",1,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-191194",null,"China Mobile Hao Zhang ","zhanghao@chinamobile.com","7/12/18: 0%->10; 13/9/19: 10%->85; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 85%->100; 12/12/19: WID:SP-180821->SP-191194","New",81,41,null,null,"2018-09-06","2019-12-12"]
[2346,810024,"OAM aspects of LTE and WLAN integration","OAM_LTE_WLAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180820",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","7/12/18: 0%->50¦14/3/19: 50%->100","32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659",81,41,null,null,"2018-09-06","2019-03-14"]
[2349,820031,"Charging Enhancement of 5GC interworking with EPC ","5GIEPC_CH",1,"Rel-16","S5","2018-12-13","2019-09-19",1,"SP-181067",null,"Chen Shan, Huawei ","chenshan@huawei.com ","¦14/3/19: 0%->30; 31/5/19: 30%->60; 13/9/19: 60%->100","32.255; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-09-13"]
[2353,820036,"Trace Management in the context of Services Based Management Architecture ","TM_SBMA",1,"Rel-16","S5","2018-12-13","2020-03-12",1,"SP-181073",null,"Andrianov, Anatoly, Nokia ","anatoly.andrianov@nokia.com ","; 31/5/19: 0%->10; 13/9/19: FCD:19/06/2019->03/20; 26/3/20: 10%->50; 28/6/20: 50%->100","32.421; 32.422; 28.530; 28.532; 28.533; 28.540; 28.541 ",82,42,null,null,"2018-12-07","2020-06-28"]
[2356,870077,"   CT1 aspects of IMSProtoc16","IMSProtoc16",2,"Rel-16","C1","2018-12-13","2019-12-13",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019->","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",87,44,null,null,"2018-12-07","2020-04-23"]
[2359,820041,"Stage-3 5GS NAS protocol development ","5GProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 25/3/20: WID:CP-183087->CP-200146","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-03-25"]
[2363,820046,"   Stage-3 SAE Protocol Development for Rel16 general aspects","SAES16",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-03-26"]
[2366,840018,"S6b Optional for ePDG connected to 5GS ","5GS_S6b_Optional",1,"Rel-16","S2","2019-05-09","2019-06-06",1,"SP-190447",null,"Irfan Ali, Cisco ","irfaali at cisco dot com ","6/6/19: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[2369,840053,"   CT4 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","31/5/19: 0%->10; 6/12/19: 10%->90; 26/3/20: 90%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.531; 29.540; 29.518; 29.571; 29.572; 29.573",84,43,null,null,"2019-05-31","2020-06-26"]
[2370,840008,"Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 ","ISAT-MO-WITHDRAW",1,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191151",null,"Dawes, Peter, Vodafone ","peter(dot)dawes(at)vodafone(dot)com ","; 13/9/19: 0%->100",24.323,84,43,null,null,"2019-05-31","2019-09-13"]
[2373,850025,"Network Slice Performance and Analytics Charging in 5G System ","5GS_NSPACH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190780",null,"Chen Shan, Huawei ","chenshan@huawei.com ","8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201",85,43,null,null,"2019-09-13","2020-09-13"]
[2377,850033,"Network Slice Management Charging in 5G System ","5GS_NSMCH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190788",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 8/10/19: 28.202 added;; 6/12/19: 0%->5; 28/6/20: 5%->50; 13/9/20: 50%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.202",85,43,null,null,"2019-09-13","2020-09-13"]
[2380,800044,"   Study on Load and Overload Control of 5GC Service Based Interfaces","FS_LOLC",2,"Rel-16","C4","2018-06-06","2019-06-14",1,"CP-181195",null,"Sridhar Bhaskaran (Huawei)","sridhar.bhaskaran@huawei.com","6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100","New; 22.943",80,41,null,null,"2018-06-06","2019-12-06"]
[2383,880056,"5GS Enhanced support of Over the air (OTA) mechanism for UICC configuration parameter update ","5GS_OTAF",1,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[2387,860011,"Support of Hybrid DASH/HLS over eMBMS ","DAHOE",1,"Rel-16","S4","2019-12-06","2020-03-12",1,"SP-190988",null,"Thienot, Cédric, Enensys","cedric.thienot@enensys.com","25/3/20: 0%->100","26.346; 26.347; 26.348",86,44,null,null,"2019-12-06","2020-03-25"]
[2390,860021,"Management of MDT in 5G ","5GMDT",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191190",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 26/3/20: 0%->100","32.421; 32.422; 32.423; 28.532; 28.533 ",86,44,null,null,"2019-12-06","2020-03-26"]
[2391,860023,"5G management capabilities ","5GMNC",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191195",null,"CORNILY, Jean-Michel, ORANGE ","jeanmichel.cornily@orange.com ","; 26/3/20: 0%->100",28.532,86,44,null,null,"2019-12-06","2020-03-26"]
[2394,860002,"Nsoraf Service Based Interface ","NSORAF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193017",null,"EL MOATAMID, Abdessamad, Orange ","abdessamad.elmoatamid@orange.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.503; 29.510 ",86,44,null,null,"2019-12-06","2020-07-02"]
[2397,890045,"UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR ","B1C_BDS_pos_UEConTest",1,"Rel-16","R5","2020-09-17","2021-09-08",1,"RP-201777",null,"CATT ",null,"tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71; 2/7/21: FCD:Thu 17/06/->09/21; 29/9/21: 71%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[2401,800100,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446)","TEI16",2,"Rel-16","S3-IETF","2017-09-11","2017-09-11",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2404,0,"Release 16 Studies on 5G/5GS/5GC/NR","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2407,780023,"Study on supporting 256-bit algorithms for 5G ","FS_256_Algo",1,"Rel-16","S3","2017-12-15","2018-09-14",1,"SP-171054",null,"Evans, Tim, Vodafone Group","tim.evans1@vodafone.com","16/3/18: 0%->30¦7/6/18: 30%->55¦10/9/18: 55%->60¦7/12/18: 60%->100","new",78,40,null,null,"2017-12-15","2018-12-07"]
[2411,800093,"Study on remote interference management for NR","FS_NR_RIM",1,"Rel-16","R1","2018-06-15","2018-12-14",1,"RP-181430",null,"CMCC",null,"TR 38.8xx¦see follow-up REL-16 WI NR_CLI_RIM¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[2414,801002,"Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR","FS_NR_2RX_vehUE",1,"Rel-16","R4","2018-06-01","2018-12-14",1,"RP-181467",null,"Samsung",null,"TR 38.8XX¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[2415,750044,"Study of test methods for New Radio","FS_NR_test_methods",1,"Rel-16","R4","2017-03-15","2018-09-14",1,"RP-180546",null,"Intel",null,"TR 38.8XX¦19/6/17: Compl:0%->10%¦19/6/17: WID: RP-170824->RP-171021¦30/6/17: 38.810 added;19/9/17: Compl:10%->15%19/9/17: WID: RP-171021->RP-171828¦8/1/18: Compl:15%->20%27/3/18: Compl:20%->45%27/3/18: CD:Thu 15/ ¦2¦16/1/19: 75%->100",38.81,75,38,null,null,"2017-03-21","2019-01-16"]
[2418,760053,"Study on Long Term Key Update Procedures","FS_LTKUP",1,"Rel-16","S3","2017-06-05","2018-12-14",1,"SP-170413",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","11/9/17: 0%->10¦15/12/17: 10%->70¦15/12/17: FCD:12/17->03/18¦16/3/18: 70%->90¦16/3/18: FCD:03/18->06/18¦7/6/18: FCD:06/18->12/18. 10/9/18: moved from Rel-15 as per SP-180687¦7/12/18: 90%->100","Internal TR",76,39,null,null,"2017-06-03","2018-12-07"]
[2421,830006,"Study on UEs Supporting Handset Mode with Non-Traditional Earpieces","FS_HaNTE",1,"Rel-16","S4","2019-03-07","2019-09-05",1,"SP-190041",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com ","31/5/19: 0%->10; 13/9/19: 10%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[2425,770002,"Study on using Satellite Access in 5G","FS_5GSAT",1,"Rel-16","S1","2017-09-08","2018-06-15",1,"SP-170702",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","15/12/17: 22.822 added;¦15/12/17: 0%->30¦15/12/17: FCD:12/17->06/18¦16/3/18: 30%->70¦7/6/18: 70%->100","New; 22.822",77,39,null,null,"2017-09-08","2018-06-07"]
[2428,800038,"Study on integration of ONAP and 3GPP configuration management services for 5G networks","FS_ONAPCINT",1,"Rel-16","S5","2018-06-06","2019-03-14",1,"SP-181075",null,"Li Gang, Ericsson","gang.g.li@ericsson.com","10/9/18: 0%->5¦7/12/18: 5%->60¦14/12/18: WID:SP-180388->SP-181075¦14/3/19: 60%->100; 26/6/19: 28.890 added;","New; 28.890",80,41,null,null,"2018-06-06","2019-06-26"]
[2432,810029,"Study on management aspects of communication services","FS_CSMAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180923",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com.","7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[2435,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[2438,850018,"Study on storage and transport of 5GC security parameters for ARPF authentication ","FS_5GC_SEC_ARPF",1,"Rel-16","S3","2019-09-19","2021-03-12",1,"SP-190708",null,"Evans, Timothy, Vodafone ","tim.evans1@vodafone.com ","; 8/10/19: 33.502 added;; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 30%->60; 12/9/20: 60%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->98; 11/6/21: ","New ; 33.502",85,43,null,null,"2019-09-13","2021-06-11"]
[{"$f":"A2439+1","v":2439},0,"--- RELEASE 15 ---","-",1,"Rel-15",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2442,750019,"   Study on Charging Aspects of 5G System Architecture Phase 1","FS_5GS_Ph1_CH",2,"Rel-15","S5","2017-03-03","2017-12-15",1,"SP-170953",null,"Chen, Shan, Huawei","chenshan@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->60¦11/9/17: WID:SP-170128->SP-170659¦15/12/17: 60%->100¦21/12/17: WID:SP-170659->SP-170953",null,75,38,null,null,"2017-03-03","2017-12-21"]
[{"$f":"A2445+1","v":2445},750016,"   Security aspects of 5G System - Phase 1","5GS_Ph1-SEC",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-180693",null,"NTT DOCOMO, Alf Zugenmaier ","alf.zugenmaier@hm.edu","7/6/17: 0%->10¦11/9/17: 10%->30¦15/12/17: 30%->65¦21/12/17: WID:SP-170234->SP-170881¦16/3/18: 65%->85¦16/3/18: FCD:03/18->06/18¦7/6/18: 85%->95¦10/9/18: WID:SP-170881->100¦10/9/18: 95%->100¦2/10/18: WID:SP-170881->SP-180693","33.501; 33.401; 33.210; 33.310; 33.220",75,38,null,null,"2017-03-02","2018-10-02"]
[2449,770042,"         Study on 5G Network selection","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 10%->55¦15/12/17: 55%->80¦16/3/18: 80%->100",null,77,39,null,null,"2017-03-03","2018-03-16"]
[2452,770045,"         Study on 5G Non-3GPP access networks","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 15%->55¦15/12/17: 55%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[2456,780008,"      CT1 aspects of 5G System - Phase 1 (normative work)","5GS_Ph1-CT",3,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-09-08"]
[2459,780011,"         5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->35¦16/3/18: 35%->85¦7/6/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2462,780014,"         5G System core network impact on services, network functions and capabilities","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->70¦7/6/18: 70%->90¦10/9/18: 90%->100",null,77,39,null,null,"2017-03-03","2018-09-10"]
[2463,780015,"         5G Network slicing","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2466,750028,"      CT4 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C4","2017-03-03","2017-12-14",1,"CP-183243",null,"Landais, Bruno (Nokia)","Bruno.Landais at nokia.com","5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦7/6/18: 50%->95¦10/9/18: 95%->99¦10/12/18: 99%->100","23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303",75,38,null,null,"2017-03-03","2018-12-10"]
[2469,790043,"      CT6 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C6","2018-03-16","2018-06-14",1,"CP-183243",null,"Landais, Bruno (Nokia)","Bruno.Landais at nokia.com","5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦16/3/18: 0%->20¦7/6/18: 20%->90¦10/9/18: 90%->95. 10/9/18: 95->100 as per CT81 discussions¦10/12/18: 100%->95¦11/12/18: 95%->100","23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303",75,38,null,null,"2017-03-03","2018-12-11"]
[2473,770018,"      CT3 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C3","2017-09-04","2018-06-15",1,"CP-180094",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->80¦10/9/18: 80%->100","29.213; 29.214",77,39,null,null,"2017-03-03","2018-09-10"]
[2476,780035,"   Data Charging in 5G System Architecture Phase 1","5GS_Ph1-DCH",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170952",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","16/3/18: 0%->10¦7/6/18: 10%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100",32.24,78,40,null,null,"2017-12-15","2018-09-10"]
[2479,800041,"   UE Conformance Test Aspects - CT6 aspects of 5G System ","5GS_Ph1_UEConTest",2,"Rel-15","C6","2018-06-07","2019-06-14",1,"CP-183242",null,"Azem, Dania (COMPRION GmbH)","DAzem@comprion.com","10/12/18: 0%->5¦10/12/18: 5%->¦10/12/18: WID:CP-181187->CP-183242; 31/5/19: 5%->10; 6/12/19: 10%->60; 26/3/20: 60%->85; 26/6/20: 85%->95; 13/9/20: 95%->98; 13/12/21: 98%->100","31.121 ; 31.124",80,41,null,null,"2017-03-02","2021-12-13"]
[2482,750036,"   SA3 aspects of EDCE5","EDCE5",2,"Rel-15","S3","2017-03-02","2017-09-14",1,"SP-170233",null,"Adrian Escott, Qualcomm Incorporated",null,"7/6/17: 0%->60¦11/9/17: 60%->70¦15/12/17: 70%->100",null,75,38,null,null,"2017-03-02","2017-12-15"]
[2485,760069,"      CT3 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C3","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com",null,"29.212; 29.213; 29.214; 29.215; 29.201",76,39,null,null,"2017-06-05","NA"]
[2486,760070,"      CT4 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C4","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","11/9/17: 0%->50¦15/12/17: 50%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",76,39,null,null,"2017-06-05","2017-12-15"]
[2489,750167,"   Core part: New Radio Access Technology","NR_newRAT-Core",2,"Rel-15","R1","2017-03-15","2018-12-14",1,"RP-190213","RP-181466","NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT¦19/6/17: Compl:0%->22%19/6/17: WID: RP-170855->RP-171485¦30/6/17 & 12/6/17: impacted specs added19/9/17: Compl:22%->50%19/9/17: WID: RP-171485->RP-172115¦15/12/17: added: 38.818¦37.865-01-01¦37.834-01-01¦37 .; 2 ","37.340;37.834-01-01;37.863-05-01;37.864-41-21;37.865-01-01;38.101;38.104;38.12?;38.201/2;38.211/2;38.213to215;38.300;38.304to307;38.321to323;38.331;38.401;38.410to414;38.455;38.470to475;38.815;38.817-01-02;38.818; 38.113; 29.413; 37.864-11-22; 38.415; 38.",75,38,null,null,"2017-03-21","2019-06-26"]
[2493,761205,"   Perf. part: LTE connectivity to 5G-CN","LTE_5GCN_connect-Perf",2,"Rel-15","R4","2017-06-20","2018-12-20",1,"RP-180860","RP-180862","Huawei",null,"16/1/19: 0%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2496,750003,"Enhancement of 3GPP support for V2X scenarios","eV2X",1,"Rel-15",null,"2016-06-09","2017-03-22",1,"SP-170158",null,"Chun, SungDuck, LG Electronics","sungduck.chun@lge.com ",null,null,75,38,null,null,"2017-03-02","NA"]
[2499,750075,"V2X new band combinations for LTE","LTE_V2X_CA_bands",1,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-170752",null,"LG Electronics",null,"no Perf. part¦12/7/17: 36.787 added;",36.786999999999999,75,38,null,null,"2017-03-21","2017-07-12"]
[2503,750262,"   Perf. Part: V2X phase 2 based on LTE","LTE_eV2X-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-182549",null,"Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #7519/6/17: WID: RP-170798->RP-17106919/9/17: WID: RP-171069->RP-171740¦27/6/18: Compl:0%->5%¦16/1/19: 5%->100¦16/1/19: WID:RP-171740->RP-182549",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2506,770037,"EPC support for E-UTRAN Ultra Reliable Low Latency Communication ","EPS_URLLC",1,"Rel-15","S2","2017-09-08","2018-03-15",1,"SP-170811",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","15/12/17: WID:SP-170797->SP-170811¦15/12/17: 0%->15¦20/3/18: 15%->100","23.401; 23.214; 23.203",77,39,null,null,"2017-09-08","2018-03-20"]
[{"$f":"A2509+1","v":2509},750261,"   Perf. part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Perf",2,"Rel-15","R4","2017-03-15","2018-12-15",0,"RP-181259",null,"Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: WID: RP-171489->RP-172845¦27/6/18: WID: RP-172845->RP-181259",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2510,0,"Release 15 Features on improvements of Mission Critical (MC)","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2513,720083,"Study on MC Security Enhancements","FS_MC_Sec",1,"Rel-15","S3","2016-06-17","2018-03-15",1,"SP-170416",null,"Haigh, Peter, CESG","peter.haigh@cesg.gsi.gov.uk ","28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17","33.xxx; 33.280; 39.880",72,37,null,null,"2016-06-17","2018-03-16"]
[2517,770008,"   Stage 2 of enhMCPTT","enhMCPTT",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170248",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->25¦11/9/17: 25%->45¦15/12/17: 45%->100","23.280 + 23.379",75,38,null,null,"2017-03-03","2017-12-15"]
[2520,770010,"   Stage 2 of eMCData","eMCData",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170462",null,"David Freeman, Home Office","david@dnf-consulting.co.uk","21/3/17: impacted TS/TR added¦7/6/17: 0%->10¦8/6/17: WID:SP-170249->SP-170462¦11/9/17: 10%->15¦15/12/17: 15%->100","23.280 + 23.282",75,38,null,null,"2017-03-03","2017-12-15"]
[2523,770012,"   Stage 2 of eMCVideo","eMCVideo",2,"Rel-15","S6","2017-06-05","2017-12-14",1,"SP-170401",null,"Niranth Amogh, Huawei Telecommunications (India","namogh@huawei.com","7/6/17: 0%->10¦11/9/17: 10%->60¦15/12/17: 60%->100","23.280; 23.281",76,39,null,null,"2017-06-03","2017-12-15"]
[2527,770016,"      CT6 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C6","2017-12-05","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","10/9/18: 0%->100","31.102; 31.103",77,39,null,null,"2017-06-03","2018-09-10"]
[2530,800043,"   Stage 2 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","S6","2017-03-03","2017-12-15",1,"SP-170686",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100","23.280 + 23.281 + 23.282 + 23.379",75,38,null,null,"2017-03-03","2018-03-16"]
[2533,770007,"Protocol enhancements for Mission Critical Services","MCProtoc15",1,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172145",null,"Jörgen Axell",null,"14/9/17: 0%->15¦15/12/17: 15%->40¦20/3/18: 40%->70¦7/6/18: 70%->100",null,77,39,null,null,"2017-09-08","2018-06-07"]
[2534,890042,"UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo ","MCenhUEConTest",1,"Rel-15","R5","2020-09-17","2022-06-22",1,"RP-212956","RP-221332","KAHN, Jason, NIST (U.S. Department of Commerce)","jason.kahn@nist.gov","tested: REL-15 SA/CT WIs enhMCPTT, eMCVideo, eMCData, MBMS_Mcservices, MCSMI, MCProtoc15, MCOver ; 8/4/21: 0%->16; 2/7/21: 16%->33; 13/9/21: Compl:33%->40%; 13/9/21: CD:Fri 17/12/21->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211764; 6/1/22: WID:RP-201487-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2537,780016,"AT Commands for CIoT-Ext","AT_CIoT-Ext",1,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-173083",null,"Bakker, John-Luc (Blackberry)","jbakker@blackberry.com","20/3/18: 0%->20¦7/6/18: 20%->100",27.007000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[2541,860032,"   UE Conformance Test Aspects - Even further enhanced MTC for LTE","LTE_eMTC4-UEConTest",2,"Rel-15","R5","2019-12-16","2021-12-21",1,"RP-192894","RP-211862","Ericsson",null,"affects: LTE. tested: REL-15 WI LTE_eMTC4-Core; 8/10/20: 0%->47; 8/4/21: 47%->54; 8/4/21: FCD:15/12/2020->06/21; 2/7/21: FCD:Fri 11/06/->12/21; 2/7/21: 54%->77; 13/9/21: Compl:77%->80%; ; 6/1/22: 80%->100",null,86,44,null,null,"2020-01-14","2022-01-06"]
[2544,750266,"   Perf. part: Further NB-IoT enhancements","NB_IOTenh2-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-182389",null,"Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦8/1 ;¦26/3/19: 30%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[2547,750010,"Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery","ProSe_WLAN_DD",1,"Rel-15",null,"2016-11-15","2018-03-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[2551,760027,"      CT1 aspects of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",3,"Rel-15","C1","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","14/9/17: 0%->60¦15/12/17: 60%->100",24.334,76,39,null,null,"2017-06-02","2017-12-15"]
[2554,760020,"Complementary Features for Voice services over WLAN","VoWLAN",1,"Rel-15",null,"2016-06-13","2018-06-14",1,"SP-170378",null,null,null,null,null,76,39,null,null,"2017-06-02","NA"]
[2555,720082,"   Study on Complementary Features for Voice services over WLAN","FS_VoWLAN",2,"Rel-15","S2","2016-06-13","2017-03-15",1,"SP-160506",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com","28/7/16: 23.751 added¦19/9/16: 0%->10., 7/12/16: moved from Rel-14, according to SP-160806¦6/3/17: 10%->80¦7/6/17: 80%->100",23.751000000000001,72,37,null,null,"2016-06-17","2017-06-07"]
[2558,760023,"      CT1 aspects of VoWLAN","VoWLAN-CT",3,"Rel-15","C1","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","14/9/17: 0%->70¦15/12/17: 70%->100","24.302 ; 24.312 ; 24.244 ",76,39,null,null,"2017-06-02","2017-12-15"]
[2561,0,"Release 15 Features on Virtual Reality (VR)","-",1,"Rel-15",null,"2016-03-01","2016-03-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2565,770023,"Addition of HDR to TV Video Profiles","HDR",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170610",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->100","26.116; 26.346; 26.234; 26.247; 26.244",77,39,null,null,"2017-09-08","2017-12-15"]
[2568,790016,"Forward compatibility for 3GPP Diameter Charging Applications","FWDCA",1,"Rel-15","S5","2018-03-15","2018-06-15",1,"SP-180076",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.251; 32.277; 32.299",79,40,null,null,"2018-03-15","2018-06-07"]
[2571,790020,"FEC and ROHC Activation for GCSE over MBMS","FRASE",1,"Rel-15","S4","2018-03-15","2018-09-14",1,"SP-180206",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd","i.bouazizi@samsung.com.","7/6/18: 0%->30¦7/6/18: FCD:06/18->09/18¦10/9/18: 30%->100","26.346; new",79,40,null,null,"2018-03-15","2018-09-10"]
[2575,790027,"   CT3 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","22/3/18: 0%->95¦10/9/18: 95%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[2578,790036,"   Stage 3 of INOBEAR","INOBEAR-CT",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com",null,null,79,40,null,null,"2017-12-15","NA"]
[2579,790037,"      CT1 aspects of INOBEAR","INOBEAR-CT",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com","7/6/18: 0%->100","24.301; 24.007",79,40,null,null,"2017-12-15","2018-06-07"]
[2582,780170,"   Core part: Increased number of E-UTRAN data bearers","INOBEARRAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-180569",null,"Samsung",null,"27/3/18: WID: RP-172835->RP-180569¦27/6/18: Compl:0%->99%¦27/6/18:",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2585,750017,"   Study on security aspects of enhancements to ProSe UE-to-Network Relay","FS_REAR_Sec",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-170270",null,null,"lihe2@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->50¦15/12/17: 50%->79¦16/3/18: 79%->99¦16/3/18: FCD:03/18->06/18¦7/6/18: 99%->100",null,75,38,null,null,"2017-03-02","2018-06-07"]
[2589,780044,"   CT aspects on enhanced VoLTE performance","eVoLP-CT",2,"Rel-15",null,"2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com",null,null,78,40,null,null,"2017-12-15","NA"]
[2592,770051,"   Study on enhanced VoLTE performance","FS_eVoLP",2,"Rel-15",null,"2016-12-01","2018-06-15",1,"SP-160833",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100",23.759,74,38,null,null,"2016-12-01","2017-09-11"]
[2596,740008,"   Study on unlicensed spectrum offloading system enhancements","FS_USOS",2,"Rel-15","S2","2016-12-01","2017-06-15",1,"SP-160835",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100",23.728999999999999,74,38,null,null,"2016-12-01","2017-09-11"]
[2599,770001,"   Stage 3 of USOS","USOS-CT",2,"Rel-15","C4","2017-09-08","2018-03-15",1,"CP-172028",null,"Lena Chaponniere, Qualcomm Incorporated","lguellec@qti.qualcomm.com","15/12/17: acronym corrected to USOS-CT as per the approved WID¦18/12/17: 0%->60¦16/3/18: 60%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",77,39,null,null,"2016-03-01","2018-03-16"]
[2602,750024,"   Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) ","FS_FRMCS_ARCH",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170269",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com ","21/3/17: added impacted TR¦7/6/17: 0%->10¦11/9/17: 10%->50¦15/12/17: 50%->100","new 23.790",75,38,null,null,"2017-03-03","2017-12-15"]
[2603,750006,"   Stage 1 of MONASTERY","MONASTERY",2,"Rel-15","S1","2017-03-02","2017-06-15",1,"SP-170697",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","7/6/17: 0%->10¦8/9/17: WID:SP-170163->SP-170697¦11/9/17: 10%->100","22.280; 22.179",75,38,null,null,"2017-03-02","2017-09-11"]
[2606,790032,"      CT1 aspects of MONASTERY","MONASTERY",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","16/3/18: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","24.379; 24.380; 24.481; 24.483; 24.484",79,40,null,null,"2018-03-16","2018-09-10"]
[2609,790013,"   Security Architecture of MONASTERY","MONASTERY_SEC",2,"Rel-15","S3","2018-01-11","2018-03-16",1,"SP-180052",null,"Woodward, Tim, Motorola Solutions",null,"16/3/18: 0%->100",33.18,79,40,null,null,"2018-03-15","2018-03-16"]
[2613,760032,"      CT1 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C1","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","24.008; 24.301; 27.007; 24.229; 24.368; 24.167; 24.173; 24.275; 24.341; 24.390; 24.391",76,39,null,null,"2017-06-02","2018-06-07"]
[2616,760035,"Northbound APIs for SCEF – SCS/AS Interworking","NAPS",1,"Rel-15",null,"2017-03-02","2018-06-15",1,"SP-170240",null,"Vaidya, Maulik, Huawei","Maulik.vaidya@huawei.com ","6/3/17: 0%->10",null,75,38,null,null,"2017-03-02","2017-03-06"]
[2620,780007,"      CT4 aspects of NAPS","NAPS-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","7/6/18: 95%->100",null,78,40,null,null,"2017-06-02","2018-06-07"]
[2623,770049,"Common API Framework for 3GPP Northbound APIs ","CAPIF",1,"Rel-15",null,"2017-03-10","2018-06-15",1,"SP-170798",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","15/12/17: 23.222 added;","New; 23.222",77,39,null,null,"2017-09-08","2017-12-15"]
[2626,790042,"   Stage 3 of CAPIF","CAPIF-CT",2,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-180151",null,"Nishant Gupta, Samsung","nishant.gup@samsung.com ","16/3/18: 0%->10¦27/3/18: 29.222 added¦19/4/18: CAPIF->CAPIF-CT¦7/6/18: 10%->35¦7/6/18: 35%->85¦10/9/18: 85%->100","29.122; 29.116; 29.222",79,40,null,null,"2018-03-16","2018-09-10"]
[2627,780024,"   Security aspects of CAPIF","CAPIF-Sec",2,"Rel-15","S3","2017-12-15","2018-06-14",1,"SP-171051",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","16/3/18: 0%->40¦7/6/18: 40%->100",null,78,40,null,null,"2017-12-15","2018-06-07"]
[2630,720048,"   Study on management and orchestration of network slicing for next generation network","FS_MONETS",2,"Rel-15","S5","2016-06-13","2017-09-12",1,"SP-160394",null,"Ericsson , Robert Petersen",null,"28/7/16: 28.801 added¦19/9/16: 0%->10¦1/12/16: 10%->25¦6/3/17: FCD:03/17->06/17¦6/3/17: 25%->60¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->09/17¦7/6/17: 60%->90¦11/9/17: 90%->100","32.8xx; 28.801",72,37,null,null,"2016-06-13","2017-09-11"]
[2633,780037,"   Network Resource Model (NRM) for 5G networks and network slicing","NETSLICE-5GNRM",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180812",null,"Nokia (Jing Ping","jing.ping@nokia-sbell.com","16/3/18: 0%->25¦7/6/18: 25%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170956->SP-180812","28.657; 28.658; 28.659; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-10-02"]
[{"$f":"A2637+1","v":2637},810009,"   CT aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",2,"Rel-15","ct","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,81,41,null,null,"2018-09-06","NA"]
[2640,780041,"   Fault Supervision for 5G networks and network slicing","NETSLICE-FS5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180817",null,"Zhu Weihong, ZTE","zhu.weihong@zte.com.cn","16/3/18: 0%->20¦7/6/18: 20%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170961->SP-180817",28.545000000000002,78,40,null,null,"2017-12-15","2018-10-02"]
[2644,780018,"      CT1 aspects of FS_PC_VBC","FS_PC_VBC",3,"Rel-15","C1","2016-12-01","2017-12-15",1,"CP-172135",null,"Huang, Zhenning, China Mobile","huangzhenning <at> chinamobile <dot> com","15/12/17: 0%->100",29.827000000000002,74,38,null,null,"2016-12-01","2017-12-15"]
[2647,760037,"Framework for Live Uplink Streaming ","FLUS",1,"Rel-15","S4","2017-06-05","2018-06-14",1,"SP-170824",null,"Park, Kyungmo, SK Telecom","kyungmo.park@sk.com","30/6/17: 26.238 added;¦11/9/17: 0%->10¦15/12/17: 10%->85¦15/12/17: FCD:12/17->06/18¦21/12/17: WID:SP-170576->SP-170824¦16/3/18: 85%->90¦7/6/18: 90%->100","New TS; 26.238",76,39,null,null,"2017-06-03","2018-06-07"]
[2650,770021,"SAND for MBMS","SAND4M",1,"Rel-15","S4","2017-09-08","2018-06-15",1,"SP-170827",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->50¦15/12/17: FCD:12/17->03/18¦21/12/17: WID:SP-170608->SP-170827¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->100","26.247; 26.346; 26.347; TR26.946",77,39,null,null,"2017-09-08","2018-06-07"]
[2651,780036,"Management Enhancement for EPC CUPS ","ME_CUPS",1,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170954",null,"Huawei (ZHU, Lei","lei.zhu@huawei.com","ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14¦16/3/18: 0%->5¦7/6/18: 5%->60¦10/9/18: 60%->100","32.426; 32.455; 28.658; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-09-10"]
[2654,730006,"   Stage 1 of eCNAM","eCNAM",2,"Rel-15","S1","2016-09-15","2016-12-15",1,"SP-160548",null,"Hala Mowafy, Ericsson",null,"1/12/16: 0%->100¦30/6/17: 24.196 added;","22.173; 24.196",73,37,null,null,"2016-09-19","2017-06-30"]
[2658,750001,"Enhancement of background data transfer","eBT",1,"Rel-15","S1","2017-01-16","2017-03-08",1,"SP-170161",null,"Atsushi Minokuchi, NTT DOCOMO","minokuchi at nttdocomo dot com",null,22.100999999999999,75,38,null,null,"2017-03-02","NA"]
[2661,760018,"   SAES6 for support for non-3GPP accesses","SAES6-non3GPP",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","2018-06-07"]
[2664,720075,"Security Assurance Specification for PGW network product class","SCAS_PGW",1,"Rel-15","S3","2016-06-17","2017-12-12",1,"SP-160481",null,"Peng Jin, China Mobile","pengjin@chinamobile.com","28/7/16: 33.250 added¦19/9/16: 0%->10¦6/10/16: 33.216 added¦1/12/16: 10%->40. 06/03/17: moved from Rel-14.¦6/3/17: 40%->80¦7/6/17: FCD:06/17->12/17¦7/6/17: 80%->95¦11/9/17: 95%->100","33.250; 33.216",72,37,null,null,"2016-06-17","2017-09-11"]
[2668,760010,"   (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C1-IETF","2017-06-02","2020-04-23",0.91,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com",null,null,76,39,null,null,"2014-12-04","NA"]
[2671,870065,"      (IETF) Update to Private Header Field P-Visited-Network-ID in Session Initiation Protocol (SIP) Requests and Responses (draft-jesske-update-p-visited-network)","IMSProtoc8",3,"Rel-15","C1-IETF","2020-01-08","2020-04-23",0.25,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,87,44,null,null,"2020-04-23","NA"]
[2674,750015,"   Stopped - Study on R15 Lawful Interception Service","FS_15LIS",2,"Rel-15","S3LI","2017-03-02","2018-09-14",1,"SP-170040",null,"Gerry McQuaid, Vodafone","Gerald.McQuaid@vodafone.com","12/7/17: 0%->5¦11/9/17: 5%->10¦16/3/18: 24%->35¦7/6/18: 35%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->85. 17/01/19: deleted as per Alex's e-mail 13 Nov. Was at 85%",null,75,38,82,null,"2016-07-27","2018-09-10"]
[2675,750013,"   Normative work on Lawful Interception Rel-15","LI15",2,"Rel-15","S3LI","2017-03-02","2019-03-12",1,"SP-170839",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","12/7/17: 0%->5¦15/12/17: 5%->10¦10/9/18: 17%->40¦7/12/18: FCD:12/18->03/19¦7/12/18: 40%->75¦20/3/19: 75%->80; 31/5/19: 80%->100",null,75,38,null,null,"2016-07-27","2019-05-31"]
[2678,760055,"Control and monitoring of Power, Energy and Environmental (PEE) parameters in Radio Access Networks (RAN)","PEE_CMON",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170479",null,"Jean-Michel CORNILY, ORANGE",null,"30/6/17: 28.306 added;¦30/6/17: 28.305 added;¦30/6/17: 28.304 added;¦11/9/17: 0%->20¦15/12/17: 20%->80¦16/3/18: 80%->100","New TSs; 52.402; 32.405; 32.425; 32.101; 32.103; 28.306; 28.305; 28.304",76,39,null,null,"2017-06-03","2018-03-16"]
[2682,760057,"Charging for enhancement to Flexible Mobile Service Steering (eFMSS) ","eFMSS_CH",1,"Rel-15","S5","2017-06-05","2017-12-14",1,"SP-170482",null,"Long,Biao, China Telecom","longb.gd@chinatelecom.cn. ","11/9/17: 0%->70¦15/12/17: 70%->100","32.251; 32.298; 32.299",76,39,null,null,"2017-06-03","2017-12-15"]
[2685,780032,"REST Solution Sets","REST_SS",1,"Rel-15",null,"2016-09-19","2019-09-16",0.27,"SP-170950",null,null,null,null,null,78,41,null,null,"2017-12-15","NA"]
[2688,800114,"   (IETF) JSON Schema: A Media Type for Describing JSON Documents (draft-handrews-json-schema)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",0,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com",null,null,80,41,null,null,"2018-07-10","NA"]
[2692,790029,"   CT1 aspects of eSPECTRE","eSPECTRE",2,"Rel-15","C1","2018-03-15","2018-06-14",1,"CP-180096",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","16/3/18: 0%->5; 7/6/18: 5%->50; 10/9/18: 50%->100",24.228999999999999,79,null,null,null,"2018-03-16","2018-09-10"]
[2695,790030,"   CT3 aspects of eSPECTRE","eSPECTRE",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180096",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","10/9/18: 0%->100","29.163; 29.165",79,null,null,null,"2018-03-16","2018-09-10"]
[2698,750034,"(Small) Test Technical Enhancements and Improvements for Rel-15","TEI15_Test",1,"Rel-15",null,"2017-03-17","2017-12-15",1,"-",null,"-","-","Created upon demand of RAN5","-",75,38,null,null,"2015-01-12","2016-02-24"]
[2699,0,"Release 15 Features on LTE improvements","-",1,"Rel-15",null,"2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2702,800080,"   UE Conformance Test Aspects - UL Data Compression in LTE","LTE_UDC-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-190311",null,"CATT",null,"tested: REL-15 WI LTE_UDC-Core¦26/3/19: WID:RP-180918->RP-190311¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2706,770069,"Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1",1,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-172077",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[2709,780066,"   UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-UEConTest",2,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-172713",null,"Ericsson",null,"tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2712,770171,"   Core part: Extended-Band12 new E-UTRA Band","Ext_B12_LTE-Core",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180159",null,"Ericsson",null,"15/12/17: 37.761 added;¦8/1/18: Compl:0%->25%¦27/3/18: Compl:25%->100%;",37.761000000000003,77,39,null,null,"2017-09-19","2018-03-27"]
[2716,710173,"   Stopped - Core part: Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON-Core",2,"Rel-15","R2","2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/12/16->Wed 15/03/17¦1/7/16: WID: RP-160540->RP-16093726/9/16: Compl:10%->30%¦20/12/16: Compl:30%->75%¦20/12/16: Stat Rep: --> 21/3/17: Compl:75%->79% 21/3/17: CD:W ¦27/6/",null,71,36,null,null,"2016-03-22","2018-06-27"]
[2718,740045,"   Stopped - Stage 3 of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",2,"Rel-15","ct","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[2719,740046,"      Stopped - CT1 aspects of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",3,"Rel-15","C1","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->25¦11/9/17: 25%->0","24.008; 24.301; 29.118; 24.368; 27.007",74,38,null,null,"2016-12-01","2017-09-11"]
[2722,710074,"Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA",1,"Rel-15",null,"2016-03-15","2018-09-14",0.71,"RP-161668",null,"Huawei",null,"follow-up WI of REL-13 WI AAS_BS_LTE_UTRA¦14/9/17: WID:RP-160548->RP-161668",37.843000000000004,71,36,null,null,"2016-03-22","2017-09-14"]
[2725,720091,"Shortened TTI and processing time for LTE","LTE_sTTIandPT",1,"Rel-15",null,"2016-06-15","2020-12-12",0.99,"RP-161299",null,"Ericsson",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2729,740072,"450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR",1,"Rel-15",null,"2016-12-15","2018-03-15",1,"RP-162514",null,"Airbus",null,"21/3/17: 36.748 added;",36.747999999999998,74,38,null,null,"2016-12-20","2017-03-21"]
[2732,770065,"   UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72)","LTE450_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180528",null,"Airbus",null,"¦8/1/18: Compl:0%->77%¦27/3/18: Compl:77%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[2735,740274,"   Perf. part: E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-Perf",2,"Rel-15","R4","2016-12-15","2017-03-15",0,"RP-170212",null,"Airbus",null,"21/3/17: CD:Thu 15/06/17->Wed 15/03/17 ",null,74,38,null,null,"2016-12-20","2017-03-21"]
[2739,740275,"   Perf. part: FDD operating band in the L-band for LTE","LTE_FDD_L_Band-Perf",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171403",null,"NTT DOCOMO",null,"19/6/17: Compl:0%->99%19/6/17: CD:Thu 15/06/19/9/17: Compl:99%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2742,740176,"   Core part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"21/3/17: Compl:0%->20%19/6/17: Compl:20%->50%;19/9/17: Compl:50%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2743,740276,"   Perf. part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Perf",2,"Rel-15","R4","2017-03-17","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17 19/9/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2746,780065,"   UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-UEConTest",2,"Rel-15","R5","2017-12-15","2018-12-14",1,"RP-172698",null,"Sprint",null,"tested: REL-15 WI LTE_CA_C_B41_PC2-Core¦27/3/18: Co ;; 28/7/20: 5%->100",null,78,40,null,null,"2018-01-08","2020-07-28"]
[2749,740080,"TDD operating band in the L-band for LTE","LTE_TDD_L_Band",1,"Rel-15",null,"2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: 36.753 added;¦14/9/17: WID:RP-162557->RP-170304",36.753,74,38,null,null,"2016-12-20","2017-09-14"]
[2753,750160,"   Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-180584","RP-180318","Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦19/6/17: Compl:0%->70%¦19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%¦27/3/18: Compl:90%->99%¦27/3/18: CD:Thu 15/03/18->Fri ¦27/6/18: CD:Fri",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2756,750163,"   Core part: UE Positioning Accuracy Enhancements for LTE","LCS_LTE_acc_enh-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",1,"RP-181298","RP-180947","Nokia",null,"¦19/6/17: Compl:0%->10%¦19/6/17: CD:Fri 15/12/17->Fri 15/06/18 19/9/17: Compl:10%->20%¦8/1/18: Compl:20%->40%¦8/1/18: WID: RP-171508->RP-17231327/3/18: Compl:40%->50%¦27/6/18: Compl:50%->99%;; 24/4/20: 99%->100",null,75,38,null,null,"2017-03-21","2020-04-24"]
[2760,750264,"   Perf. part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL-Perf",2,"Rel-15","R4","2016-09-14","2018-12-14",1,"RP-171740",null,"Huawei",null,"¦19/6/17: CD:Sat 15/12/18->Fri 15/06/18¦19/6/17: WID: RP-170838->RP-171067 19/9/17: WID: RP-171067->RP-17173827/3/18: Compl:0%->25%¦27/6/18: Compl:25%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2763,750265,"   Perf. part: Enhancements to LTE operation in unlicensed spectrum","LTE_unlic-Perf",2,"Rel-15","R4","2017-12-14","2018-12-14",1,"RP-180402",null,"Nokia",null,"19/6/17: CD:Thu 15/03/18->Sat 15/12/18¦8/1/18: WID: RP-170848->RP-17284127/3/18: WID: RP-172841->RP-180402¦16/1/19: 0%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2766,750070,"Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming",1,"Rel-15","R2","2017-03-15","2018-12-14",0.99,"RP-170786",null,"China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core",null,75,38,null,null,"2017-03-21","2017-03-21"]
[2767,750170,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170956","RP-172192","China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core¦19/6/17: Compl:0%->25%¦19/6/17: WID: RP- 19/9/17: Compl:25%->45%¦8/1/18: Compl:45%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2770,750171,"   Core part: Enhancing LTE CA Utilization","LTE_euCA-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.9,"RP-180561","RP-181069","Nokia",null,"19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2773,750073,"450 MHz Band for LTE in Region 3","LTE450_Reg3",1,"Rel-15","R4","2017-03-15","2019-03-15",1,"RP-170952",null,"China Unicom",null,"14/9/17: WID:RP-170159->RP-170952",null,75,38,null,null,"2017-03-21","2017-09-14"]
[2777,750074,"US 600 MHz Band for LTE","LTE600_US",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170740",null,"Ericsson",null,null,null,75,38,null,null,"2017-03-21","2017-03-21"]
[2780,770060,"   UE Conformance Test Aspects - US 600 MHz Band for LTE (Band 71)","LTE600_US-UEConTest",2,"Rel-15","R5","2017-09-15","2017-12-15",1,"RP-172195",null,"Dish Network",null,"¦8/1/18: Compl:0%->100%¦",null,77,39,null,null,"2017-09-19","2018-01-08"]
[2784,760097,"Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171131",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2787,760098,"Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40",1,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2790,760199,"   Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171755",null,"Huawei",null,"19/9/17: Compl:0%->10%¦ 15/12/17: 36.760 added;¦8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%¦27/6/18: Comp",36.76,76,39,null,null,"2017-06-16","2018-06-27"]
[2791,850061,"   UE Conformance Test Aspects – LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-UEConTest",2,"Rel-15","R5","2019-09-19","2021-06-11",1,"RP-192116",null,"Huawei",null,"8/10/20: 0%->50; 8/10/20: FCD:15/09/2020->12/20; 8/4/21: 50%->98; 8/4/21: FCD:11/12/2020->06/21; 2/7/21: 98%->100",null,85,43,null,null,"2019-10-08","2021-07-02"]
[2794,761200,"   Perf. part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Perf",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"¦19/9/17: WID: RP-171506->RP-171759¦27/3/18: Compl:0%->100%;",null,76,39,null,null,"2017-06-16","2018-03-27"]
[2797,761201,"   Perf. part: UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-12-14",1,"RP-181315",null,"Ericsson",null,"¦27/6/18: WID: RP-171408->RP-181315¦16/1/19: 0%->100",null,76,39,null,null,"2017-06-16","2019-01-16"]
[2801,780069,"Enhanced LTE Support for Aerial Vehicles","LTE_Aerial",1,"Rel-15","R2","2017-03-15","2019-06-19",0.99,"RP-172826",null,"Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2804,820062,"   UE Conformance Test Aspects - Enhanced LTE Support for Aerial Vehicles","LTE_Aerial-UEConTest",2,"Rel-15","R5","2018-12-15","2019-06-19",1,"RP-192747",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_Aerial-Core; 8/10/19: WID:RP-182324->RP-191747; 14/1/20: WID:RP-191747->RP-192747; 14/1/20: 0%->100",null,null,null,null,null,"2019-01-16","2020-01-14"]
[2808,780172,"   Core part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Core",2,"Rel-15","R4","2017-12-15","2018-06-15",1,"RP-180960","RP-180959","Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL27/3/18: Compl:0%->40%¦27/6/18: Compl:40%->100%",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2811,780173,"   Core part: ProSe Support for Band 72 in LTE","LTE450_B72_Europe_ProSe-Core",2,"Rel-15","R4","2017-12-15","2017-12-15",1,"RP-182441",null,"Airbus",null,"This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78¦compare REL-15 WI LTE450_Europe_PPDR-Core;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2814,780174,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL-Core",2,"Rel-15","R4","2017-12-15","2018-06-15",1,"RP-181442",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01¦27/3/18: Compl:0%->10%¦27/3/18: 36.715-00-01 added;¦27/6/18: Compl:10%->100%;","36.715-00-01",78,40,null,null,"2018-01-08","2018-06-27"]
[2815,780274,"   Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-181442",null,"Qualcomm",null,"basket CA WI27/3/18: CD:Sat 15/12/18->Fri 15/06/18 ¦27/6/18: Compl:0%->50%;¦16/1/19: 50%->100",null,78,40,null,null,"2018-01-08","2019-01-16"]
[2818,761003,"LTE CRS-Interference Mitigation performance requirements for single RX chain UEs","LTE_1RX_CRS_IM",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171465",null,"Intel",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2822,760290,"   Perf. part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180800",null,"Ericsson",null,"19/9/17: Compl:0%->25%¦ 8/1/18: Compl:25%->70%¦8/1/18:27/3/18: Compl:70%->67%¦ ¦27/6/18: Compl:67%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2825,760291,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-181013",null,"Qualcomm",null,"¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->30%;27/3/18: Compl:30%->40% ¦27/6/18: Compl:40%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2828,760292,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180955",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2832,760094,"LTE Advanced inter-band CA Rel-15 for 5DL/1UL","LTE_CA_R15_5DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171466",null,"Nokia",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2835,760095,"LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171127",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2838,760096,"LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170946",null,"LG Electronics",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2839,760196,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"12/7/17: 36.715-00-02 added;¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->80%¦ ¦27/6/18: ","36.715-00-02",76,39,null,null,"2017-06-16","2018-06-27"]
[2842,580037,"Stopped - LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements","LTE_UTRA_TRP_TRS",1,"Rel-15",null,"2012-12-15","2017-12-15",0.82,"RP-130703","-","Nokia","petri.j.vasenkari@nokia.com","Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022","UTRA; LTE",58,30,null,null,"2012-12-10","2014-09-15"]
[2846,790153,"   Core part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Core",2,"Rel-15","R6","2018-03-15","2018-09-14",0.8,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;",null,79,40,null,null,"2018-03-27","2018-06-27"]
[2849,790156,"   Core part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5","LTE_CA_R15_xDL3UL-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-181311",null,"KDDI",null,"basket CA WI¦no Perf. part¦27/6/18: Compl:0%->100%¦…",null,79,40,null,null,"2018-03-27","2018-06-27"]
[2852,790155,"   Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-180688",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16",null,79,40,null,null,"2018-03-27","2018-06-27"]
[2856,730056,"Study on management aspects of virtualized network functions that are part of the NR","FS_MA_RNVNF",1,"Rel-15","S5","2016-09-19","2017-12-15",1,"SP-160703",null,"Intel (Joey Chou","joey.chou@intel.com","6/10/16: Acronym FS_MA_RVNF ->FS_MA_RNVNF ¦6/10/16: 32.864 added¦1/12/16: 0%->5¦6/3/17: 5%->10¦7/6/17: 10%->40¦11/9/17: 40%->70¦15/12/17: 70%->100¦15/12/17: FCD:09/17->12/17",32.863999999999997,73,37,null,null,"2016-09-19","2017-12-15"]
[2859,710045,"STOPPED AT SA#77 - SA3 aspects on Study on Architecture and Security for Next Generation System","FS_NSA",1,"Rel-15","S3","2016-03-01","2017-12-12",1,"SP-160727",null,"Vesa Torvinen, Ericsson","vesa.torvinen@ericsson.com","19/9/16: 0%->25¦22/9/16: WID:SP-160227->SP-160727¦22/9/16: FCD:12/16->03/17¦1/12/16: 25%->45¦6/3/17: 45%->60¦7/6/17: FCD:03/17->12/17 so Rel-14->Rel-15¦7/6/17: 60%->65¦11/9/17: 65%->100",33.899000000000001,71,36,null,null,"2016-03-01","2017-09-11"]
[2860,760080,"Study on separation of CP and UP for split option 2 of NR","FS_NR_CPUP_Split",1,"Rel-15","R3","2017-06-15","2017-12-15",1,"RP-171905",null,"Ericsson",null,"19/9/17: Compl:0%->45%19/9/17: WID: RP-171421->RP-171905¦15/12/17: 38.806 added;¦8/1/18: Compl:45%->100%",38.805999999999997,76,39,null,null,"2017-06-16","2018-01-08"]
[2863,730070,"Study on interference cancellation receiver for LTE BS","FS_LTE_IC_BS",1,"Rel-15","R4","2016-09-15","2017-06-15",1,"RP-161485",null,"China Telecom",null,"6/10/16: 36.766 added¦20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%¦19/6/17: Compl:65%->100%",36.765999999999998,73,37,null,null,"2016-09-26","2017-06-19"]
[2866,0,"Other Release 15 Studies","-",1,"Rel-15",null,"2017-09-08","2018-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2870,750049,"Study on evaluation methodology of new V2X use cases for LTE and NR","FS_LTE_NR_V2X_eval",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171093",null,"LG Electronics",null,"TR 38.8XX19/6/17: WID: RP-170837->RP-171093¦12/7/17: 37.885 added;19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->10%¦8/1/18: CD:Fri 15/12/17->Thu 15/03/18¦27/3/18: Compl:10%->30%¦27/3/18: CD:Thu 15/03/18->Fri 15/06/18¦27/",37.884999999999998,75,38,null,null,"2017-03-21","2018-06-27"]
[2873,740016,"Study on Management Enhancement of CUPS of EPC Nodes","FS_MECUPS",1,"Rel-15","S5","2016-12-01","2017-12-12",1,"SP-160925",null,"Huawei; Jiang, Junyi","jiangjunyi@huawei.com","6/3/17: 0%->5¦7/6/17: 5%->40¦7/6/17: FCD:09/17->12/17¦11/9/17: 40%->50¦15/12/17: 50%->100",32.866999999999997,74,38,null,null,"2016-12-01","2017-12-15"]
[2876,750041,"Study on scheduling enhancements with CA for UMTS","FS_UTRA_CA_sched_enh",1,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171065",null,"Huawei",null,"TR 25.7XX¦19/6/17: Compl:0%->100%¦ 12/7/17: 25.708 added;",25.707999999999998,75,38,null,null,"2017-03-21","2017-07-12"]
[2880,700047,"Study on OAM support for assessment of energy efficiency in mobile access networks","FS_OAM_EE",1,"Rel-15","S5","2015-11-02","2017-06-09",1,"SP-160430",null,"Cornily,Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","13/6/16: WID:SP-150674->SP-160430¦13/6/16: 0%->55¦1/12/16: 55%->80¦6/3/17: FCD:03/17->06/17¦6/3/17: 80%->90¦21/3/17: moved from rel-14¦7/6/17: 90%->100",32.856000000000002,70,36,null,null,"2015-12-07","2017-06-07"]
[2883,760056,"Study on OAM aspects of LTE and WLAN integration ","FS_OAM_LWI",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170480",null,"Yizhi Yao, Intel Corporation","yizhi.yao@intel.com","30/6/17: 32.868 added;¦11/9/17: 0%->10¦15/12/17: 10%->50¦16/3/18: 50%->90¦7/6/18: 90%->100","new; 32.868",76,39,null,null,"2017-06-03","2018-06-07"]
[2884,680054,"Study on Overload Control for Diameter Charging Applications","FS_DOCME_CH",1,"Rel-15","S5","2015-06-18","2017-12-15",1,"SP-170481",null,"GUO Wenjie, ZTE","guo.wenjie1@zte.com.cn","Aug2015: moved to Rel-14 (email CT and EG)¦07/09/15: 0%->5¦7/3/16: 5%->10¦13/6/16: FCD:03/16->09/16¦19/9/16: FCD: 09/16->06/17¦6/3/17: FCD:03/17->12/17¦21/3/17: moved from rel-14¦7/6/17: 10%->25¦8/6/17: WID:SP-150310->SP-170481¦11/9/17: 25%->3","New 32.869",68,35,null,null,"2015-06-26","2017-12-15"]
[2887,720046,"Study on Management Aspects of Next Generation Network architecture and features","FS_MAN_NGNAF",1,"Rel-15","S5","2016-06-13","2017-12-12",1,"SP-160399",null,"Nokia Networks, Yizhi Yao","Yizhi.yao@nokia.com","28/7/16: 28.802 added¦19/9/16: 0%->5¦1/12/16: 5%->10¦6/3/17: FCD:03/17->06/17¦6/3/17: 10%->40¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 40%->60¦11/9/17: 60%->70¦15/12/17: 70%->100","(new); 28.802",72,37,null,null,"2016-06-13","2017-12-15"]
[2890,650036,"Stopped - Study on IMS Enhanced Spoofed Call Prevention and Detection","FS_ESCAPADES",1,"Rel-15","S3","2014-09-19","2017-12-15",1,"SP-140611","-","Sprint","Gregory.schumacher@sprint.com","Dec.14: TR number added. 3/3/15: 0->5%¦June2015: Compl:5%->25¦9/12/15: 25%->30¦21/3/17: moved from Rel-13¦21/3/17: FCD:09/15->12/17¦7/6/17: Stopped (30%->100%)",33.832000000000001,64,33,null,null,"2014-09-04","2017-06-07"]
[2894,760064,"Study on system and functional aspects of Energy Efficiency in 5G networks ","FS_EE_5G",1,"Rel-15","S5","2017-06-05","2018-12-14",1,"SP-170489",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","30/6/17: 32.872 added;¦11/9/17: 0%->5¦15/12/17: 32.972 added;¦15/12/17: 5%->40¦16/3/18: 40%->60¦7/6/18: 60%->65¦7/6/18: FCD:06/18->12/18¦10/9/18: 65%->85¦7/12/18: 85%->100","new; 32.872; 32.972",76,39,null,null,"2017-06-05","2018-12-07"]
[2897,700027,"Mission Critical Improvements","MCImp",1,"Rel-14",null,"2015-04-14","2019-12-13",1,"https://www.3gpp.org/ftp/Information/WI_Sheet/.zip",null,null,null,"Umbrella Feature",null,70,36,null,null,"2015-12-07","2015-12-11"]
[2900,720056,"      Stage 2 of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379, 23.280, 23.281, 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[2904,740026,"         CT4 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","6/3/17: 0%->100","23.003, 29.228, 23.335, 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[2907,720055,"   Common functional architecture to support mission critical services","MCImp-MC_ARCH",2,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160489",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","28/7/16: 23.280 added¦19/9/16: 0%->40¦1/12/16: 40%->95¦3/3/17: 95%->100","23.280, 23.379, 23.281, 23.282; 23.280",72,37,null,null,"2016-06-13","2017-03-03"]
[2908,720053,"   Mission Critical Video over LTE ","MCImp-MCVideo",2,"Rel-14",null,"2015-04-14","2017-06-14",1,"SP-150849",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160106¦0->80%¦9/6/16: 80%->100",null,70,36,null,null,"2015-12-07","2016-06-09"]
[2911,720051,"      Stage 2 for MCVideo","MCImp-MCVideo",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160491",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","28/7/16: 23.281 added¦19/9/16: 0%->25¦1/12/16: 25%->95¦3/3/17: 95%->100","23.281, 23.280, 23.379, 23.282; 23.281",72,37,null,null,"2016-06-13","2017-03-03"]
[2914,740034,"         CT1 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C1","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","6/3/17: 0%->25¦5/6/17: 25%->90¦14/9/17: 90%->100","24.381, 24.382, 24.383, 24.384",74,38,null,null,"2016-12-01","2017-09-14"]
[2918,720054,"   Mission Critical Data over LTE ","MCImp-MCData",2,"Rel-14",null,"2015-04-14","2017-06-14",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100",null,70,36,null,null,"2015-12-07","2016-07-28"]
[2921,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[2925,740031,"         CT4 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","6/3/17: 0%->100","23.003, 23.335, 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[2928,790052,"   UE Conformance Test Aspects - Mission Critical Improvements","MCImp-UEConTest",2,"Rel-14","R5","2018-03-15","2019-12-13",1,"RP-180527",null,"NIST",null,"tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements)¦to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).;; 25/9/20: 5%->100",null,79,40,null,null,"2018-03-27","2020-09-25"]
[2931,730010,"   CT3 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","2/12/16: 0%->20¦6/3/17: 20%->100","29.165, 29.212, 29.213, 29.214",73,37,null,null,"2016-09-16","2017-03-06"]
[2932,730011,"   CT4 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","6/3/17: 0%->100","23.003, 23.008, 29.283",73,37,null,null,"2016-09-16","2017-03-06"]
[2935,720030,"LTE support for V2X services","V2XLTE",1,"Rel-14",null,"2015-02-09","2018-12-14",1,"SP-150573",null,null,null,"7/12/15: 0%->5¦28/1/16: 22.185 added¦2/3/16: 5%->90¦9/6/16: 90%->100","22.278; 22.185",68,35,null,null,"2015-09-09","2016-06-09"]
[2938,740009,"   Security aspect of LTE support of V2X services","V2XLTE-Sec",2,"Rel-14","S3","2016-12-01","2017-06-15",1,"SP-160955",null,"Huawei, Marcus Wong","mwong@huawei.com","6/3/17: 0%->75¦7/6/17: 75%->100",33.185000000000002,74,38,null,null,"2016-12-01","2017-06-07"]
[2942,760086,"      UE Conformance Test Aspects - Support for LTE-based V2X Services","LTE_V2X-UEConTest",3,"Rel-14","R5","2017-06-15","2018-12-14",1,"RP-192556",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->40%¦ 27/3/18: Compl:40%->55%; 14/1/20: WID:RP-172356->RP-192556; 14/1/20: 65%->100",null,76,39,null,null,"2017-06-16","2020-01-14"]
[2945,730028,"      CT3 aspects of V2X Services","V2X-CT",3,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 29.387 added¦2/12/16: 0%->40¦6/3/17: 40%->60¦5/6/17: 60%->100","29.212, 29.468; 29.387",73,37,null,null,"2016-09-16","2017-06-05"]
[2949,670009,"      Study on Stage 1 of LTE support for V2X services","FS_V2XLTE_S1",3,"Rel-14","S1","2015-02-09","2015-02-09",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75¦7/12/15: 75%->100","New 22.885",67,34,null,null,"2015-12-07","2015-12-07"]
[2952,680058,"      RAN1 Study on LTE-based V2X Services","FS_LTE_V2X",3,"Rel-14","R1","2015-06-15","2016-06-15",1,"RP-161263",null,"LG Electronics",null,"29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ¦28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15¦",33.884999999999998,68,35,null,null,"2015-07-03","2016-07-01"]
[2955,700261,"   Perf. part: Support for V2V services based on LTE sidelink","LTE_SL_V2V-Perf",2,"Rel-14","R4","2015-12-15","2017-06-15",1,"RP-161603",null,"LG Electronics",null,"22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-16127226/9/16: WID: RP-161272->RP-161603¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:80%->100%",null,70,36,null,null,"2016-01-01","2017-06-19"]
[{"$f":"A2957+1","v":2957},0,"Release 14 on CIoT","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2958,710023,"Non-IP for Cellular Internet of Things (CIoT) for 2G/3G-GPRS(EC-EGPRS)","NonIP_GPRS",1,"Rel-14",null,"2016-03-02","2016-09-15",1,"SP-160196",null,null,null,null,null,71,36,null,null,"2016-03-02","2016-03-02"]
[2961,710026,"      CT1 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C1","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: 0%->50¦11/6/16: WID:CP-160161->CP-160293¦16/9/16: 50%->65¦2/12/16: 65%->100",24.007999999999999,71,36,null,null,"2016-03-02","2016-12-02"]
[2965,720192,"   Core part: Further enhanced MTC for LTE","LTE_feMTC-Core",2,"Rel-14","R1","2016-06-15","2017-06-15",1,"RP-170532","RP-171441","Ericsson",null,"26/9/16: Compl:0%->12%26/9/16: WID: RP-161321->RP-161464¦20/12/16: Compl:12%->70%¦20/12/16: WID: RP-161464->RP-16252021/3/17: Compl:70%->95% ¦21/3/17: CD19/6/17: Compl:95%->100%",null,72,37,null,null,"2016-07-01","2017-06-19"]
[2968,720093,"Enhancements of NB-IoT","NB_IOTenh",1,"Rel-14",null,"2016-06-15","2018-12-14",1,"RP-161324",null,"Huawei",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2972,730021,"AT Commands for CIoT","AT_CIoT",1,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160477",null,"John-Luc Bakker",null,"2/12/16: 10%->95¦6/3/17: 95%->100",null,73,37,null,null,"2016-09-16","2017-03-06"]
[2975,730059,"   Stage 2 of Extended architecture support for Cellular Internet of Things","CIoT_Ext",2,"Rel-14","S2","2016-09-15","2016-12-16",1,"SP-160830",null,"Intel : Puneet Jain","puneet.jain@intel.com","1/12/16: 0%->100¦1/12/16: WID:SP-160732->SP-160830","23.401, 23.682, 23.060, 23.271",73,37,null,null,"2016-09-19","2016-12-01"]
[2978,740040,"      CT4 aspects of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","6/3/17: 0%->90¦5/6/17: 90%->100","23.008, 29.272, 29.002, 29.336, 29.128, 29.171, 29.172, 29.173",74,38,null,null,"2016-12-01","2017-06-05"]
[2979,730077,"Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh",1,"Rel-14","R6","2016-09-15","2018-06-15",0.99,"RP-161806",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2982,730083,"New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands",1,"Rel-14","R4","2016-09-15","2017-09-15",0.99,"RP-161890",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[2986,720006,"Enhancements of Dedicated Core Networks selection mechanism","eDecor",1,"Rel-14",null,"2015-09-17","2017-12-15",0.99,"SP-160310","SP-170537","Roland Gustafsson","Roland.Gustafsson@ericsson.com","7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95",23.710999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[2989,730013,"   CT aspects of eDecor","eDecor-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[2992,730016,"      CT6 aspects of eDecor","eDecor-CT",3,"Rel-14","C6","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100","31.102, 31.111",73,37,null,null,"2016-09-16","2017-06-05"]
[2996,760002,"   Stopped - GSM aspects of eDECOR","eDecor",2,"Rel-14","R6","2017-04-04","2017-06-15",1,"SP-160310",null,"Ericsson",null,"Verbal addition by Paolo U. 21/09/17: verbal deletion by Paolo","44.060, 44.018, 48.018",76,39,null,null,"2017-05-29","NA"]
[2999,740179,"Addition of bands 25 and 40 to LTE MTC cat.1","LTE_MTCe2_L1_cat1_B25_B40-Core",1,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162573",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3002,700039,"   Stage 2 of EWE","EWE",2,"Rel-14","S2","2015-11-02","2016-06-17",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002, 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[3003,720002,"   CT aspects of EWE","EWE-CT",2,"Rel-14","ct","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com",null,null,72,37,null,null,"2016-06-13","NA"]
[3006,730048,"Support of EAP Re-authentication Protocol for WLAN Interworking","ERP",1,"Rel-14",null,"2016-09-16","2017-03-16",1,"SP-160568",null,"ORANGE, Todor Gamishev","Todor dot Gamishev at Orange dot com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3010,730046,"      CT4 aspects of ERP","ERP-CT",3,"Rel-14","C4","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com","2/12/16: 0%->50¦6/3/17: 50%->95¦5/6/17: 95%->100","29.273, 23.008, 23.003",73,37,null,null,"2016-09-16","2017-06-05"]
[3013,720018,"   Support of Emergency services over WLAN - phase 2","SEW2",2,"Rel-14","S2","2016-06-13","2016-09-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com","11/6/16: 0%->45¦19/9/16: 45%->100","23.402, 23.167",72,37,null,null,"2015-04-01","2016-09-19"]
[3016,730019,"      CT4 aspects of SEW2","SEW2-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 0%->100","23.003, 29.272, 29.273, 29.274, 29.328",73,37,null,null,"2016-09-16","2016-12-02"]
[3020,710175,"   Core part: Enhanced LTE-WLAN Aggregation (LWA)","LTE_WLAN_aggr-Core",2,"Rel-14","R2","2016-03-15","2017-03-15",1,"RP-160923","RP-170330","Intel",null,"follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923¦26/9/16: Compl:25%->45%¦20/12/16: Compl:45%->75%¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:75%->100% ¦21/3/17",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3023,680004,"   Stage 1 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S1","2015-05-11","2015-06-19",1,"SP-150275",null,"Kurt Bischinger",null,null,22.100999999999999,68,35,null,null,"2015-06-09","2015-06-09"]
[3024,700021,"   Stage 2 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S2","2015-12-11","2016-06-10",1,"SP-150623",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","7/3/16: 0%->20¦9/6/16: 20%->100. FCD: 03/16->06/16","23.167, 23.401",68,35,null,null,"2015-12-07","2016-06-09"]
[3027,720068,"      (IETF) Next-Generation Pan-European eCall (draft-ietf-ecrit-ecall)","EIEI-CT",3,"Rel-14","C1-IETF","2016-03-02","2016-09-15",1,"CP-160053",null,null,null,"18/12/17: 30%->100; 9/4/21: RFC 8147 added;","draft-ietf-ecrit-ecall; RFC 8147",72,37,null,null,"2016-03-02","2021-04-09"]
[3030,720074,"Password based service activation for IMS Multimedia Telephony service","PWDIMS",1,"Rel-14",null,"2015-03-11","2016-12-15",1,"SP-150041","SP-170536","Peter Bleckert (Ericsson)",null,"1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100%",22.172999999999998,67,34,null,null,"2015-03-04","2015-07-31"]
[3034,720036,"      CT3 aspects for PWDIMS","PWDIMS-CT",3,"Rel-14","C3","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,"5/6/17: 0%->100",29.292000000000002,72,37,null,null,"2016-06-11","2017-06-05"]
[3037,651003,"   (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497","ISAT",2,"Rel-14","C1-IETF","2014-09-12","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦13/6/16: 25%->28; 26/6/19: 28%->100","draft-dawes-sipping-debug",65,33,null,null,"2014-09-02","2019-06-26"]
[3040,630207,"   CT3 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C3","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 0%->100",29.164999999999999,63,32,null,null,"2014-01-29","2017-06-05"]
[3044,730004,"   Stage 1 of User Controlled Spoofed Call Treatment","SPECTRE",2,"Rel-14","S1","2016-08-23","2016-09-19",1,"SP-160898",null,"Greg Schumacher, Sprint",null,"1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898","22.228, 22.173",73,37,null,null,"2016-09-19","2016-12-01"]
[3047,780049,"   (IETF) Authenticated Identity Management in SIP (draft-ietf-stir-rfc4474bis)","SPECTRE-CT_IETF2",2,"Rel-14","C1-IETF","2017-06-15","2018-06-15",1,null,null,"Christer Holmberg","christer.holmberg@ericsson.com","22/3/18: 0%->100; 9/4/21: RFC 8224 added;","RFC 8224",78,40,null,null,"2017-12-18","2021-04-09"]
[3048,700032,"Enhancement for TV service","EnTV",1,"Rel-14",null,"2015-04-14","2017-06-09",1,"SP-150756","SP-170532","Zhiming Li","Lizhiming@huawei.com","2/3/16: 0%->100",22.100999999999999,70,36,null,null,"2015-12-07","2016-03-02"]
[3051,710046,"      Study on System Architecture Enhancements to eMBMS for TV Video Service","FS_AE_enTV",3,"Rel-14","S2","2016-03-11","2016-09-15",1,"SP-160225",null,"Miguel Griot, Qualcomm","mgriot@qti.qualcomm.com","9/6/16: 0%->70¦28/7/16: 23.746 added¦19/9/16: 70%->100",23.745999999999999,71,36,null,null,"2016-03-11","2016-09-19"]
[3054,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347, 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[3058,740052,"      CT4 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","5/6/17: 0%->100","29.274, 23.003",74,38,null,null,"2016-12-01","2017-06-05"]
[3061,670003,"Multimedia Priority Service Modifications","MPS_Mods",1,"Rel-14","S1","2015-03-11","2016-06-15",1,"SP-150043",null,"Ray P. Singh (Applied Communications Science)","rsingh@appcomsci.com","1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%¦07/09/15: 25%->40¦7/12/15: 40%->70¦2/3/16: 70%->80¦9/6/16: 80%->100",22.152999999999999,67,34,null,null,"2015-03-04","2016-06-09"]
[3064,730032,"   CT1 aspects of SIP Reason header extension","REAS_EXT",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160481",null,"Mohali, Marianne","marianne.mohali@orange.com","2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100",24.228999999999999,73,37,null,null,"2016-09-16","2017-06-05"]
[3068,730002,"Diameter Load Control Mechanism","DLoCMe",1,"Rel-14","ct","2014-12-03","2017-03-15",0.98,"CP-160645","CP-171049","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","5/12/16: WID:CP-160412->CP-160645",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3071,740058,"   (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583","DLoCMe",2,"Rel-14","C4-IETF","2016-12-02","2017-03-15",0.9,"CP-160645",null,null,null,"2/12/16: 0%->90",null,74,38,null,null,"2016-12-02","2016-12-02"]
[3072,660025,"   Study on Diameter Load Control Mechanisms","FS_DLoCME",2,"Rel-13","C4","2014-12-03","2015-09-11",1,"CP-140996",null,"Alcatel-Lucent",null,"0->5%. Mar. 15: 10%¦7/12/15: 10%->40¦13/6/16: 40%->100","New 29.810",66,34,null,null,"2014-12-04","2016-06-13"]
[3075,740055,"      CT3 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","6/3/17: 0%->100","29.061, 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.368, 29.468, 29.213, 29.155, 29.201",74,38,null,null,"2016-12-01","2017-03-06"]
[3078,720060,"Enhancements to Multi-stream Multiparty Conferencing Media Handling","MMCMH_Enh",1,"Rel-14",null,"2016-03-02","2017-03-21",0.99,"SP-160272","SP-170528","Nikolai Leung","nleung@qti.qualcomm.com",null,26.114000000000001,72,37,null,null,"2016-06-11","NA"]
[3082,720066,"      CT3 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C3","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Acronym changed from \"MMCMH-CT\"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦6/3/17: 0%->100","29.162, 29.213, 29.214, 29.165",72,37,null,null,"2016-03-02","2017-03-06"]
[{"$f":"A3085+1","v":3085},750039,"      (IETF) RTP Payload Format Restrictions (draft-ietf-mmusic-rid)","MMCMH_Enh-CT",3,"Rel-14","C1-IETF","2017-03-21","2017-03-21",0.9,null,null,"Ericsson",null,"23/4/20: 20%->90; 9/4/21: RFC 8851 added;","RFC 8851",75,38,null,null,"2017-03-21","2021-04-09"]
[3089,710030,"   deleted -CT4 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","23.333, 29.333, 23.334, 29.334, 29.238",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3092,720009,"   Control and User Plane Separation of EPC nodes","CUPS",2,"Rel-14","S2","2016-06-09","2016-09-15",1,"SP-160316",null,"Huawei, Mirko Schramm","mirko.schramm@huawei.com","19/9/16: 0%->80¦1/12/16: 80%->100","23.214, 23.002, 23.203, 23.401, 23.402",72,37,null,null,"2015-09-17","2016-12-01"]
[3095,730040,"      CT4 aspects for CUPS","CUPS-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com","2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100","23.007, 29.274, 29.281, 29.303, 23.008",73,37,null,null,"2016-09-16","2017-06-05"]
[3096,690048,"OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM14",1,"Rel-14","S5","2015-03-12","2017-12-12",1,null,null,null,null,null,null,68,35,null,null,"2015-09-16","2015-09-16"]
[3099,690039,"      Configuration Management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-CM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160401",null,"ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn)","zhu.weihong@zte.com.cn","5/10/15: 28.513¦28.512¦28.511¦28.510 added¦7/12/15: 0%->15¦7/3/16: 15%->20¦13/6/16: 20%->30¦19/9/16: 30%->50¦1/12/16: 50%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100","28.513; 28.512; 28.511; 28.510; 28.621, 28.622, 28.623, 28.704, 28.707",69,35,null,null,"2015-06-15","2017-06-07"]
[3102,690042,"      Lifecycle management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-LCM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160427",null,"Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks","anatoly.andrianov@nokia.com","5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%-","28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709",69,35,null,null,"2015-06-15","2017-06-07"]
[3106,680050,"Development of super-wideband and fullband P.835","DESUDAPS",1,"Rel-14","S4","2015-06-16","2017-06-15",1,"SP-150215","SP-170346","Scott Isabelle (Knowles, Inc.)","sisabelle@audience.com","06/15: FCD corrected to Dec.15¦Aug2015: 0%->5¦07/09/15: 5%->20, FCD: 12/15->06.16¦7/12/15: 20%->40, MOVED TO REL-14¦7/3/16: 40%->50. 15/4/16: 6/16->12/16¦11/6/16: 50%->60¦19/9/16: 60%->70, fcd: 12/16->06/17¦1/12/16: 70%->75¦6/3/17: 75%->80¦7/6","26.131, 26.132",68,35,null,null,"2015-06-18","2017-06-07"]
[3109,680002,"Control of Applications when Third party Servers encounter difficulties","CATS",1,"Rel-14","S1","2015-05-11","2015-09-16",1,"SP-150273","SP-170338","Eriko Yoshida, KDDI","er-yoshida (at) kddi (dot) com","07/09/15: 0%->100",22.010999999999999,68,35,null,null,"2015-06-09","2015-09-07"]
[3113,740004,"   Stage 2 of PS Data Off","PS_DATA_OFF",2,"Rel-14","S2","2016-11-17","2016-12-15",1,"SP-160831",null,"Christophe Petit (Orange)","kris (dot) petit (at) orange (dot) com","1/12/16: 0%->100","23.401, 23.203, 23.060, 23.228, 23.292, 23.221",74,38,null,null,"2016-12-01","2016-12-01"]
[3116,740043,"      CT3 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->60¦8/6/17: 60%->100","29.212, 29.213",74,38,null,null,"2016-12-01","2017-06-08"]
[3119,710003,"SCC AS Restoration","SCCAS_RES",1,"Rel-14","C4","2016-03-02","2016-12-15",1,"CP-160118",null,"China Mobile, Hao Zhang, ","zhanghao@chinamobile.com","13/6/16: 0%->100",23.38,71,36,null,null,"2016-03-02","2016-06-13"]
[3120,710004,"Paging Policy Enhancements and Procedure","PPEPO_LTE",1,"Rel-14","S1","2016-02-01","2016-03-01",1,"SP-160113","SP-170549","China Unicom, Zhuoyun Zhang","zhangzy910@chinaunicom.cn",null,22.100999999999999,71,36,null,null,"2016-03-01","2016-03-01"]
[3123,710005,"   Stage 1 of Enhancement to Flexible Mobile Service Steering ","eFMSS",2,"Rel-14","S1","2016-02-01","2016-03-01",1,"SP-160115",null,"China Mobile, Lu Lu","lulu@chinamobile.com",null,"22.115, 22.101",71,36,null,null,"2016-03-01","2016-03-01"]
[3127,720061,"   (IETF) Other IETF aspects of IMS_TELEP_EXT","IMS_TELEP_EXT",2,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.91,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com",null,"draft-ietf-payload-rtp-h265, -flexible-fec-scheme , draft-ietf-clue-framework , -datachannel, -signalling, -data-model-schema, -protocol, -rtp-mapping, draft-ietf-mmusic-sctp-sdp, -data-channel-sdpneg, draft-ietf-tsvwg-sctp-dtls-encaps",72,37,null,null,"2016-03-01","NA"]
[3130,800105,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8850 added;","RFC 8850",80,41,null,null,"2018-06-27","2021-04-09"]
[3133,800108,"      (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8847 added;","RFC 8847",80,41,null,null,"2018-06-27","2021-04-09"]
[3137,710011,"Improved Streaming QoE Reporting in 3GPP","IQoE",1,"Rel-14","S4","2016-03-01","2017-03-15",1,"SP-160082","SP-170521","Zhiming Li, Huawei","Lizhiming@huawei.com","11/6/16: 0%->10¦19/9/16: 10%->55. FDC: 12/16->03/17¦1/12/16: 55%->65¦6/3/17: 65%->100","New 26.909, 26.247, 26.346",71,36,null,null,"2016-03-01","2017-03-06"]
[3140,680053,"   Study on S8 Home Routing Architecture","FS_V8",2,"Rel-14","S2","2015-06-18","2016-03-10",1,"SP-150255",null,"Motohiro ABE","motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com","07/09/15: 0%->10¦07/09/15: 10%->100¦7/12/15: 100%->10% (mistake?) then 10%->70, FCD: 12/15-?03/16¦7/3/16: 70%->80¦9/6/16: 80%->100","New 23.xxx",68,35,null,null,"2015-06-18","2016-06-09"]
[3143,730023,"   CT Aspects of V8","V8-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3144,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[3147,720020,"Improvements of awareness of user location change","AULC",1,"Rel-14",null,"2015-09-17","2017-06-09",1,"SP-160308","SP-170524","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-09-17","2016-06-09"]
[3151,730035,"      CT3 Aspect of AULC","AULC-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.212, 29.213",73,37,null,null,"2016-09-16","2017-03-06"]
[3154,720022,"Service Domain Centralization","SeDoC",1,"Rel-14","S2","2015-11-02","2016-09-19",1,"SP-160675",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[3157,720014,"Sponsored data connectivity improvements","SDCI",1,"Rel-14",null,"2015-11-02","2016-12-15",1,"SP-160309","SP-170523","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[3161,730038,"      CT3 Aspects of SDCI","SDCI-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.250 added¦2/12/16: 10%->30¦6/3/17: 30%->80¦5/6/17: 80%->100","29.212, 29.213, 29.214, 29.201, 29.250",73,37,null,null,"2016-09-16","2017-06-05"]
[3164,710019,"   SAES5 for support for non-3GPP accesses","SAES5-non3GPP",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","11/6/16: 0%->15¦16/9/16: 15%->20¦2/12/16: 20%->85¦6/3/17: 85%->100","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",71,36,null,null,"2016-03-02","2017-03-06"]
[3167,700043,"   Study on group based enhancements in the network capability exposure functions","FS_GENCEF",2,"Rel-14","S2","2015-11-02","2016-06-10",1,"SP-160311",null,"Samsung, Sung Hwan Won","sunghwan.won@samsung.com","28/1/16: 23.773 added¦28/1/16: 23.742 added¦7/3/16: 0%->10¦9/6/16: 10%->100","23.xyz; 23.773; 23.742",70,36,null,null,"2015-12-07","2016-06-09"]
[3168,720013,"   Group based enhancements in the network capability exposure functions","GENCEF",2,"Rel-14","S2","2016-06-09","2016-12-16",1,"SP-160311",null,"Samsung, Sunghoon Kim","s.hun.kim@samsung.com","19/9/16: 0%->90¦1/12/16: FCD:09/16->12/16¦1/12/16: 90%->100",23.681999999999999,72,37,null,null,"2015-12-07","2016-12-01"]
[3171,720301,"   Robust Call Setup for VoLTE subscriber in LTE","RobVoLTE",2,"Rel-14","S2","2016-06-17","2016-09-15",1,"SP-160312",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com","19/9/16: 0%->100. 1/12/16: UID changed: 720085 -> 720301 (720085 was also used for RP-161181)","23.228, 23.237",72,37,null,null,"2015-12-07","2016-12-01"]
[3175,760089,"      UE Conformance Test Aspects –Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh-UEConTest",3,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-171385",null,"CATT",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->60%¦ 27/3/18: Compl:60 ;; 11/10/20: 95%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3178,720037,"Improved operator control using new UE configuration parameters","IOC_UE_conf",1,"Rel-14",null,"2016-06-13","2017-03-15",1,"CP-160828","CP-171176","Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦17/10/16: WID:CP-160296->CP-160374¦5/12/16: WID:CP-160374->CP-160828","24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.XXX, 24.YYY",72,37,null,null,"2016-06-11","2016-12-05"]
[3181,720001,"Shared Subscription Data Update","eSDU",1,"Rel-14","C4","2016-06-13","2016-12-15",1,"CP-160644","CP-171050","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","13/6/16: 0%->25¦2/12/16: 25%->100¦5/12/16: WID:CP-160243->CP-160644","29.272, 29.002, 29.305, 29.230",72,37,null,null,"2016-06-13","2016-12-05"]
[3185,720049,"   Charging Aspects of Enhanced Proximity-based Services","CH14-ProSe",2,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160428","SP-170408","Chen, Shan","chenshan@huawei.com","19/9/16: 0%->40¦1/12/16: 40%->60¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100","32.240, 32.251, 32.277, 32.298, 32.299",72,37,null,null,"2016-06-13","2017-06-07"]
[3188,740059,"   CT Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160697","CP-171048","Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,74,38,null,null,"2016-12-01","2017-03-21"]
[3189,740020,"      CT1 Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",3,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160697",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","2/12/16: 0%->10¦6/3/17: 10%->35¦5/6/17: 35%->100",24.228999999999999,74,38,null,null,"2016-12-01","2017-06-05"]
[3192,700160,"   Core part: Enhanced LAA for LTE","LTE_eLAA-Core",2,"Rel-14","R1","2015-12-15","2017-03-15",1,"RP-162235","RP-170269","Ericsson",null,"22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881¦26/9/16: Compl:60%->92%¦26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: WID: ¦20/12/16: Compl:92%->97%¦20/12/16:21/3/17: Compl:",null,70,36,null,null,"2016-01-01","2017-03-21"]
[3196,700162,"   Core part: RRC optimization for UMTS","UTRA_RRCopt-Core",2,"Rel-14","R2","2015-12-15","2016-09-15",1,"RP-160287","RP-172758","Ericsson",null,"22/3/16: Compl:0%->8%¦ 1/7/16: Compl:8%->70%26/9/16: Compl:70%->100%¦8/1/18: Stat Rep: ->RP-172758",null,70,36,null,null,"2016-01-01","2018-01-08"]
[3198,700163,"   Core part: DTX/DRX enhancements in CELL_FACH","FACH_DTXDRX-Core",2,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-162513","RP-162132","Huawei",null,"22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->50%26/9/16: Compl:50%->65%¦20/12/16: Compl:65%->100%¦",null,70,36,null,null,"2016-01-01","2016-12-20"]
[3201,700277,"   Perf. part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06",null,70,36,null,null,"2016-01-01","2016-07-01"]
[3204,700178,"   Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3","LTE_1980_2170_REG3-Core",2,"Rel-14","R4","2015-12-15","2015-12-15",0,"RP-152238",null,"KT Corp.",null,null,null,70,36,null,null,"2016-01-01","2015-12-22"]
[3208,700079,"LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3",1,"Rel-14","R4","2015-12-15","2017-12-15",0.99,"RP-152253",null,"Orange",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3211,750052,"   UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69)","LTE_FDD_2600_CA_B3-UEConTest",2,"Rel-14","R5","2017-03-15","2017-12-15",1,"RP-172257",null,"Bureau Veritas",null,"¦19/9/17: Compl:43%->96%¦8/1/18: Compl:96%->100%¦",null,75,38,null,null,"2017-06-19","2018-01-08"]
[3212,700080,"Multi-Band Base Station testing with three or more bands","MB_BS_test_3B",1,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-152205",null,"Alcatel-Lucent",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3215,700081,"Performance enhancements for high speed scenario in LTE","LTE_high_speed",1,"Rel-14","R4","2015-12-15","2018-09-14",0.99,"RP-152263",null,"NTT DOCOMO",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3218,750056,"   UE Conformance Test Aspects - Performance enhancements for high speed scenario in LTE","LTE_high_speed-UEConTest",2,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170367",null,"CMCC",null,"tested: REL-14 LTE_high_speed-Core;¦19/6/17: Compl: 1 8/1/18:27/3/ ;; 11/10/20: 95%->100",null,75,38,null,null,"2017-03-21","2020-10-11"]
[3222,750053,"   UE Conformance Test Aspects - RAT Independent Further Indoor Positioning Enhancements for LTE","LTE_iPos_enh2_RI-UEConTest",2,"Rel-14","R5","2017-03-15","2017-12-15",1,"RP-172317",null,"NextNav",null,"tested: REL-14 UTRA_LTE_iPos_enh2-Core (but only RAT independent aspects for LTE);¦ ;",null,75,38,null,null,"2017-03-21","2018-01-08"]
[3225,730071,"   UE Conformance Test Aspects - Radiated Performance of Multiple-antenna Receivers in the LTE UE","LTE_MIMO_OTA-UEConTest",2,"Rel-14","R5","2016-09-15","2018-03-15",1,"RP-171615",null,"Intel",null,"¦20/12/16: Compl:0%->5%21/3/17: Compl:5%->20%19/6/17: Compl:20% 1 8/1/18: C27/3/",null,73,37,null,null,"2016-09-26","2018-03-27"]
[3228,710277,"   Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Perf",2,"Rel-14","R4","2016-03-15","2017-12-15",1,"RP-160623",null,"Samsung",null,"¦20/12/16: Stat Rep: -->¦19/6/17: Compl:0%->50%19/9/17: Compl:50%->70%19/9/17: CD:Fri 15/09/17->Fri 15/12/17¦8/1/18: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3232,740265,"   Perf. Part: Further mobility enhancements in LTE","LTE_eMob-Perf",2,"Rel-14","R4","2016-12-15","2017-06-15",1,"RP-162503",null,"ZTE",null,null,null,74,38,null,null,"2017-06-19","NA"]
[3235,710279,"   Perf. part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-162488",null,"Ericsson",null,"¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->;21/3/17: Compl:0%->20%19/6/17: Compl:20%->75%¦19/9/17: Compl:75%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3236,780063,"   UE Conformance Test Aspects - Uplink capacity enhancements for LTE","LTE_UL_CAP_enh-UEConTest",2,"Rel-14","R5","2017-12-15","2018-12-14",1,"RP-172639",null,"Ericsson",null,"tested: REL-14 WI LTE_UL_CAP_enh-Core¦related to UL 256 QAM27/3 ;¦26/3/19: 35%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3239,780064,"   UE Conformance Test Aspects - L2 latency reduction techniques for LTE","LTE_LATRED_L2-UEConTest",2,"Rel-14","R5","2017-12-15","2018-03-15",1,"RP-180530",null,"Ericsson",null,"tested: REL-14 WI LTE_LATRED_L2-Core27/3/18: Compl:0%->100%;",null,78,40,null,null,"2018-01-08","2018-03-27"]
[3242,710281,"   Perf. part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3246,750054,"   UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-UEConTest",2,"Rel-14","R5","2017-03-15","2018-06-15",1,"RP-180848",null,"Huawei",null,"tested: REL-14 LTE_SRS_switch-Core;¦19/6/17: Compl:0%->5%¦8/1/18: Compl:27/3/ ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3249,710284,"   Perf. part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-161019",null,"MediaTek",null,"1/7/16: WID: RP-160680->RP-161019¦26/9/16: CD:Fri 15/09/17->Thu 15/06/17¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:0%->25%19/6/17: Compl:25%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3253,800112,"   (IETF) Session Description Protocol (SDP) Offer/Answer Considerations for Datagram Transport Layer Security (DTLS) and Transport Layer Security (TLS) (draft-ietf-mmusic-dtls-sdp)","IMSProtoc8",2,"Rel-14","C1-IETF","2016-06-14","2017-03-15",0.9,"CP-160294",null,"Alcatel-Lucent","Keith Drage","23/4/20: 25%->90; 9/4/21: RFC 8842 added;","RFC 8842",80,41,null,null,"2018-06-27","2021-04-09"]
[3256,700059,"   Study on Multi-Carrier Enhancements for UMTS","FS_UTRA_MCe",2,"Rel-14","R1","2015-12-15","2016-06-15",1,"RP-152290",null,"Huawei",null,"22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->100%¦28/7/16: 25.707 added;",25.707000000000001,70,36,null,null,"2016-01-01","2016-07-28"]
[3259,720195,"   Core part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US-Core",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-162007",null,"Nokia",null,"26/9/16: Compl:0%->70%¦6/10/16: 36.744 added¦20/12/16: Compl:70%->100%¦",36.744,72,37,null,null,"2016-07-01","2016-12-20"]
[3260,720295,"   Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-162007",null,"Nokia",null,"¦20/12/16: Compl:0%->100%¦",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3263,720196,"   Core part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Core",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"follow-up WI of SI FS_LTE_B41_HPUE¦26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3266,721002,"Dedicated Core Networks for GERAN","DECOR_GERAN",1,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161029",null,"Ericsson",null,"no Perf. part¦DECOR was a REL-13 SA2 feature",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3270,721203,"   Perf. part: Positioning Enhancements for GERAN","ePOS_GERAN-Perf",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052",null,"Ericsson",null,"¦20/12/16: Compl:0%->50% ¦21/3/17: Compl:50%->80%¦19/6/17: Compl:80%->100%¦",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3273,730179,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN","UMTS_QMC_Streaming-Core",2,"Rel-14","R2","2016-09-15","2017-03-15",1,"RP-161917","RP-170259","China Unicom",null,"¦20/12/16: Compl:0%->60% ¦21/3/17: Compl:60%->100%",null,73,37,null,null,"2016-09-26","2017-03-21"]
[{"$f":"A3277+1","v":3277},730180,"   Core part: Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID-Core",2,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161896","RP-170478","China Telecom",null,"¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3280,730284,"   Perf. part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL)","LTE_4Rx_AP_DL_CA-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-161897",null,"Ericsson",null,"¦20/12/16: Compl:0%->30%;21/3/17: Compl:30%->50%19/6/17: Compl:50%->90%¦19/9/17: Compl:90%->100%",null,73,37,null,null,"2016-09-26","2017-09-19"]
[3283,750058,"      UE Conformance Test Aspects - 4 Rx antenna ports with CA for LTE DL","LTE_4Rx_AP_DL_CA-UEConTest",3,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170704",null,"Ericsson",null,"tested: REL-14 LTE_4Rx_AP_DL_CA-Core¦19/6/17: C 1 8/1/18: C 27/3/ ;¦26/3/19: 90%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[3284,730085,"Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX",1,"Rel-14","R4","2016-09-15","2018-09-14",0.99,"RP-161898",null,"Qualcomm",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3287,760085,"   UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE","LTE_UE_cat_1RX-UEConTest",2,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-180263",null,"Qualcomm",null,"¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3291,710183,"   Core part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Core",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912","RP-171330","Intel",null,"¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3294,730282,"   Perf. part: Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE","LTE_eCRSIM_eSUMIMO-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-162303",null,"Intel",null,"6/10/16: 36.176 added¦20/12/16: Compl:0%->30%21/3/17: Compl:30%->50% ¦21/3/17: Release: Rel-15->Rel-14¦19/6/17: Compl:50%->85%19/9/17: Compl:85%->100%",36.176000000000002,73,37,null,null,"2016-09-26","2017-09-19"]
[3297,780052,"   (IETF) SDP Offer/Answer Clarifications for RTP/RTCP Multiplexing [RFC 5761 (was draft-ietf-avtcore-5761-update)]","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-09-15",1,null,null,null,null,null,null,78,40,null,null,"2017-12-18","NA"]
[3301,870069,"   (IETF) Indicating Exclusive Support of RTP/RTCP Multiplexing using SDP (draft-ietf-mmusic-mux-exclusive) ","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",0.9,null,null,null,null,"9/4/21: RFC 8858 added;","RFC 8858",87,44,null,null,"2020-04-23","2021-04-09"]
[3304,620162,"   STOPPED - TR on Pilot development of Security Assurance Specification for MME network product class","SCAS-SA3Pil_TR",2,"Rel-14","S3","2013-12-09","2014-12-12",1,"SP-130718","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","This TR collects input for the new TS 33.116. Dec.14: 55->70%. 3/3/15: 70->55%. 10/03/15: 55->75%¦June2015: Compl:75%->80¦7/12/15: STOPPED AT 80% (marked as 100% here since no more work expected)","New 33.806",62,32,null,null,"2013-11-22","2015-12-07"]
[3307,680099,"(Small) Technical Enhancements and Improvements for Rel-14","TEI14",1,"Rel-14","SP,CP,RP,R4","2015-05-11","2015-06-18",1,null,null,null,null,null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[3308,689999,"(Small) Test Technical Enhancements and Improvements for Rel-14","TEI14_Test",1,"Rel-14","SP,CP,RP,GP","2016-09-13","2018-12-20",1,"-",null,"-","-","Created upon demand of RAN5","-",68,35,null,null,"2015-01-12","2016-02-24"]
[3311,690186,"      Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12-Core",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3315,690287,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3318,690288,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3321,700169,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL","LTE_CA_R14_5DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170143",null,"Nokia Networks",null,"28/1/16: 36.714-05-01 added¦22/3/16: Compl:0%->15%¦22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%¦26/9/16: Compl:40%->60%¦20/12/16: Compl ¦21/3/17","36.714-05-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3325,700270,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-170123",null,"Qualcomm",null,"22/3/16: WID: RP-152196->RP-1606161/7/16: Compl:0%->30%1/7/16: WID: RP-160616->RP-161202¦26/9/16: Compl:30%->50% 20/12/16: Compl:50%->75% 21/3/17: Compl:75%->80%;",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3328,700271,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"¦22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-16094726/9/16: WID: RP-160947->RP-161676¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->90",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3331,700272,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL-Perf",3,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,"¦1/7/16: Compl:0%->15%21/3/17: Compl:15%->100%",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3332,700073,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.48,"RP-152246",null,"LG Electronics",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3335,700074,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-152249",null,"Ericsson",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3339,700175,"      Core part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613¦1/7/16: Compl:60%->50%¦1/7/16: WID: RP-160613¦26/9/16: Compl:50%->44%¦20/12/16:21/3/1","36.714-00-00","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3342,700176,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170309",null,"Huawei",null,"28/1/16: 36.714-03-01 added;22/3/16: Compl:0%->15%22/3/16: WID: RP-152278->RP-1605821/7/16: Compl:15%->40%1/7/1626/9/16: Compl:40%->60%¦20/12/16: Compl:60%->80 21/3/1","36.714-03-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3345,0,"Release 14 Studies","-",1,"Rel-14","SP,RP,CP,GP","2014-09-17","2015-12-11",1,"-","-",null,"-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3349,610032,"Study on need for Multiple Access Point Names","FS_MAPN",1,"Rel-14","S1","2013-09-12","2015-06-19",1,"SP-130416",null,"Giesecke & Devrient","Ilario.macchi@gi-de.com","SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%¦June2015: Compl:90%->100",22.802,61,31,null,null,"2013-08-26","2015-06-15"]
[3352,640060,"Study on User Location Reporting Support enhancements","FS_eULRS",1,"Rel-14","S1","2014-06-19","2015-06-17",1,"SP-140402",null,"China Unicom","Zhuoyun Zhang ( zhangzy910@chinaunicom.cn)","SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%¦June2015: Compl:90%->100",22.899000000000001,64,33,null,null,"2014-05-29","2015-06-15"]
[3353,640061,"Study on Control of Applications when Third party Servers encounter difficulties","FS_CATS",1,"Rel-14","S1","2014-06-19","2015-06-15",1,"SP-140758",null,"KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#65 completion 12/14=>03/15. Moved to Rel-14. Linked to Rel-13 Feature SEES and Rel-13 TR 22.806 (FS_ACDC). Dec.14: 30->60%, WID SP-140246->SP-140758, CD: 12/14->03/15. Mar.15: CD: 03/13->06/15. 60->90%¦June2015: Compl:90%->100",22.818000000000001,64,33,null,null,"2014-05-29","2015-06-15"]
[3356,680057,"Study on High Power LTE UE for Band 41","FS_LTE_B41_HPUE",1,"Rel-14","R4","2015-06-15","2016-06-15",1,"RP-160092",null,"Sprint",null,"7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ¦22/3/16: Compl:10%->40%¦22/3/16: WID: RP-151104->RP-1600921/7/16: Compl",36.886000000000003,68,35,null,null,"2015-07-03","2016-07-01"]
[3359,700036,"Study on UICC power optimization for MTC","FS_UICC_MTC_OPT",1,"Rel-14","C6","2016-06-15","2016-12-15",1,"CP-150875",null,"Berionne, Michele","micheleb [at] qti [dot] qualcomm [dot] com","7/3/16: 0%->100¦5/6/17: 71%->100",31.97,70,36,null,null,"2015-12-07","2017-06-05"]
[3363,710058,"Study on HSPA and LTE Joint Operation","FS_UTRA_LTE_JOP",1,"Rel-14","R3","2016-03-15","2016-12-15",1,"RP-160571",null,"China Unicom",null,"¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦","New 37.805",71,36,null,null,"2016-03-22","2016-12-20"]
[3366,710061,"Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","FS_feCOMP_LTE",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160954",null,"Intel",null,"¦1/7/16: Compl:0%->15%¦26/9/16: Compl:15%->30%¦20/12/16: Compl:30%->80%21/3/17: Compl:80%->100%",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3369,720026,"Study on MBMS usage and codecs for MCPTT call and MC Video Service","FS_MCP_V",1,"Rel-14","S4","2016-06-13","2017-03-15",1,"SP-160274",null,"Zhiming Li, Huawei","lizhiming@huawei.com","28/7/16: 26.880 added¦19/9/16: 0%->30, FCD: 12/16->03/17¦1/12/16: 30%->60¦6/3/17: 60%->100",26.88,72,37,null,null,"2016-06-11","2017-03-06"]
[3373,700018,"Release 14 studies on 5G MObile Network for Advanced communications",null,1,"Rel-14","S1","2015-02-02","2016-12-15",1,"SP-150142",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","11/3: WID: SP-150050->150142¦June2015: Compl:0%->20¦07/09/15: 20%->60. 07/12/15: Created by MCC as BB to dissociate SA1 versus SA2 aspects","New 22.891",67,34,null,null,"2015-03-04","2015-09-07"]
[3376,700023,"   FS_SMARTER – massive Internet of Things","FS_SMARTER-mIoT",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150817",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","2/3/16: 35%->65¦9/6/16: 65%->100","New 22.861",70,36,null,null,"2015-12-07","2016-06-09"]
[3377,700024,"   FS_SMARTER – Critical Communications","FS_SMARTER-CRIC",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150818",null,"Kanerva, Mikko","mikko.kanerva@nokia.com","2/3/16: 15%->60¦9/6/16: 60%->95¦7/6/17: 95%->100","New 22.862",70,36,null,null,"2015-12-07","2017-06-07"]
[3380,700017,"SA2 aspects on Study on Architecture and Security for next Generation System","FS_NextGen",1,"Rel-14","S2","2015-12-07","2016-12-15",1,"SP-160727",null,"suntao@chinamobile.com, devaki.chandramouli@nokia.com","suntao@chinamobile.com, devaki.chandramouli@nokia.com","28/1/16: 23.799 added¦Acronym corrected (\"NexGen\"->\"NextGen\")¦7/3/16: 5%->15¦10/3/16: WID:SP-150853->SP-160200. Name changed from \"Study on Architecture for next Generation System\"¦9/6/16: 15%->35¦19/9/16: 35%->64¦22/9/16: WID:SP-160227->SP-16072",23.798999999999999,70,36,null,null,"2015-12-07","2016-12-01"]
[3383,620064,"Mission Critical Push To Talk over LTE (MCPTT)","MCPTT",1,"Rel-13",null,"2013-12-11","2018-06-15",0.98,"SP-150356","-","NIST","david.cypher@nist.gov","SP#65 updated WID SP-140276=>SP-140435. Mar 15: WID: SP-140879->SP-150164. 4/15: S4 added. 6/15: WID updated","Stage 1/2; ",62,32,null,null,"2013-11-26","2016-07-28"]
[3387,670022,"   Study on media, codecs and MBMS enhancements for MCPTT","MCPTT",2,"Rel-13","S4","2014-12-12","2016-03-11",1,"SP-150356",null,"Zhiming Li (lizhiming@huawei.com)","Zhiming Li (lizhiming@huawei.com)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. 5/5/15: TR number added¦June2015: Compl:0%->5, WID updated¦Aug2015: 5%->15¦07/09/15: 15%->40¦7/12/15: 40%->80, FCD: 12/15->03/16¦7/3/16: 80%->85; 26/6/20: 85%->100","New 26.879",67,34,null,null,"2015-03-05","2020-06-26"]
[3390,660053,"   Security of MCPTT","MCPTT",2,"Rel-13","S3","2014-12-12","2016-03-11",1,"SP-150356",null,"Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015¦June2015: Compl:5%->15, WID updated. 7/9/15: TS number added¦7/12/15: 15%->60. FCD -> 03/16, ES in SP-150729¦7/3/16: 60%->85¦1/12/16: 85%->98¦6/3/17: 98%->100",33.179000000000002,66,34,null,null,"2014-12-12","2017-03-06"]
[3393,690017,"      CT1 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","7/12/15: WID:CP-150587->CP-150793¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","24.379, 24.380 24.38, 24.382, 24.383, 24.384, 24.229",69,35,null,null,"2015-09-07","2016-12-05"]
[3397,690099,"         Floor Control – Off Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->85¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 85%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.38,69,35,null,null,"2015-09-29","2016-12-05"]
[3400,691002,"         Identity management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.382000000000001,69,35,null,null,"2015-09-29","2016-12-05"]
[3401,691003,"         Management Object","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->10¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 10%->100. Name changed from \"Configuration management\"¦7/3/16: WID:CP-150863->CP-160160¦5/12/1",24.382999999999999,69,35,null,null,"2015-09-29","2016-12-05"]
[3404,690018,"      CT4 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C4","2015-09-07","2016-03-11",1,"CP-160817",null,"Alcatel-Lucent, Keith Drage","keith.drage@alcatel-lucent.com","7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150864¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","23.003, 23.008, 29.283",69,35,null,null,"2015-09-07","2016-12-05"]
[3407,870072,"      (IETF) OAuth 2.0 Token Exchange (draft-ietf-oauth-token-exchange) --> RFC 8693","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",1,"CP-160817",null,null,null,null,null,87,44,null,null,"2016-03-07","2016-12-05"]
[3411,670031,"   Deleted (duplicated): Application Architecture to support MCPTT","MCPTT",2,"Rel-13","S6","2015-03-13","2015-03-13",1,"SP-150356",null,"U.S. Department of Commerce","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated. 7/15: removed since duplicates 640143 and 660054 (only 640143 is kept)",null,67,34,"SP-69",null,"2015-03-13","2015-07-31"]
[3414,670090,"   TR on Profiling and Extensions of MBMS","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100","new 26.852",67,34,null,null,"2015-04-08","2015-12-07"]
[3418,680048,"   Stage 2 for Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S2","2015-06-18","2015-12-30",1,"SP-150463",null,"Phil Young","phil.young@gd-broadband.com","07/09/15: 0%->100¦14/09/15: WID:SP 150358->SP-150463",23.401,63,32,null,null,"2014-02-05","2015-09-14"]
[3421,700038,"      CT6 aspects for IOPS","IOPS-CT",3,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com","ES in CP-150837¦7/3/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-03-07"]
[3424,650019,"Flexible Mobile Service Steering","FMSS",1,"Rel-13","S1,S2","2014-09-15","2016-03-11",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS)",22.100999999999999,65,33,null,null,"2013-11-26","2014-08-28"]
[3425,650055,"   Stage 1 for Flexible Mobile Service Steering","FMSS-ST1",2,"Rel-13","S1","2014-09-15","2014-09-17",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS). Dec.14: moved from Feature to S1 BB",22.100999999999999,65,33,null,null,"2013-11-26","2014-12-03"]
[3428,690024,"   CT3 Aspect of Flexible Mobile Service Steering","FMSS-CT",2,"Rel-13","C3","2015-09-09","2016-03-11",1,"CP-150799",null,"ZTE,Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100","29.abc, 29.212, 29.213",69,35,null,null,"2015-09-09","2016-03-07"]
[3431,660013,"   Stage 1 for Application specific Congestion control for Data Communication","ACDC-ST1",2,"Rel-13","S1","2014-06-18","2014-09-17",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","Results from MCC Split of the SA1 feature into F+BB for stage 1",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[3435,670059,"   RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150512",null,"LG Electronics",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3437,570029,"User Plane Congestion management","UPCON",1,"Rel-13","S1,S2,C3,C4","2012-09-12","2015-03-18",1,"SP-140631","-","KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON)","Stage 1/2/3",57,29,null,null,"2012-08-06","2014-09-16"]
[3441,630019,"   BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON",2,"Rel-13","S2","2014-03-07","2015-03-13",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control","-",63,32,null,null,"2014-03-04","2014-09-16"]
[3444,650107,"         CT3 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C3","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->60¦WID: CP-140734->CP-140929. Mar.15: 60->95%¦June2015: Compl:95%->100. WID: CP-140929-> CP-150365.","29.201, 29.212, 29.213, 29.214, 29.215, 29.219, New 29.217 (PCC over Np)",65,33,null,null,"2014-07-29","2015-06-15"]
[3447,630021,"   Deleted - BB3: Uplink traffic and attended/unattended traffic","UPCON-TRAFDEL",2,"Rel-13","S2","2014-03-07","2014-09-17",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Uplink Congestion Management, Un/Attended UE Information","TBD",63,32,"SP-65","PCG-33","2014-03-04","2014-09-16"]
[3448,650028,"Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",1,"Rel-13",null,"2014-09-09","2017-03-15",0.95,"SP-140483","-","Intel","ozgur.oyman@intel.com","Can be seen as an \"enhancement\" of Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042. Mar. 15: 20%","-",65,33,null,null,"2014-09-05","2015-03-05"]
[3451,710035,"   (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol) ","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",0.9,null,null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90. was (IETF) CLUE Protocol (draft-ietf-clue-protocol); 9/4/21: RFC 8847 added;","26.22; RFC 8847",71,36,null,null,"2016-03-07","2021-04-09"]
[3455,600045,"RAN Sharing Enhancements","RSE",1,"Rel-13","S1,R3","2013-06-19","2015-12-15",1,"SP-130330","-","NEC","joerg.swetina@neclab.eu","Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","-",60,31,null,null,"2013-06-03","2013-11-26"]
[3458,650121,"      Core part: RAN aspects of RAN Sharing Enhancements for LTE","RSE-RAN_LTE-Core",3,"Rel-13","R3","2014-09-12","2015-12-15",1,"RP-151827","RP-151295","NEC","Siva.Vakeesar@emea.nec.com","¦CD:Mon 15/06/15->Tue 15/09/15¦Stat Rep: -->RP-141891 1st Apr 15: Compl:15%->20% 1st Apr 15: Stat Rep: RP-141891->RP-150289 03/07/15: Compl:20%->75% 03/07/15: Stat Rep: RP-150289->RP-150875 29/09/15: Compl:75%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/1","36.300, 36.413, 36.423",65,33,null,null,"2014-06-16","2016-01-01"]
[3461,640138,"   TR on Stage 2 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S2","2014-06-19","2015-03-18",1,"SP-140630","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 9->55%¦June2015: Compl:55%->85¦07/09/15: 85%->100","New 23.706",64,33,null,null,"2014-06-12","2015-09-07"]
[3465,690037,"   (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third Party Authorization (draft-ietf-tram-turn-third-party-authz)","eWebRTCi",2,"Rel-13","S3-IET","2014-09-17","2015-08-12",1,"SP-150474","-","Alcatel-Lucent",null,"TS 33.203 CR0235 draft-ietf-tram-turn-third-party-authz¦7/3/16: 10%->100; 9/4/21: RFC 7635 added;","33.203, RRC 7635 (was draft-ietf-tram-turn-third-party-authz); RFC 7635",69,35,null,null,"2014-09-04","2021-04-09"]
[3468,690029,"      CT3 aspects for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150644¦7/3/16: 0%->100",29.213999999999999,69,35,null,null,"2015-09-07","2016-03-07"]
[3471,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",0.75,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371, 24.229, 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[3472,710041,"      (IETF) A Language for Rules Describing JSON Content (draft-newton-json-content-rules)","eWebRTCi-CT",3,"Rel-13","C3-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates. This individual draft will not further progress in IETF but is kept as reference in version -09; 23/4/20: 25%->100","24.371, 24.229, 26.223",71,36,null,null,"2016-03-07","2020-04-23"]
[3475,630016,"Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks","CSPS_Coord",1,"Rel-13","S2","2014-03-07","2016-05-12",1,"SP-140168","-","Ericsson","roland.gustafsson@ericsson.com","Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios","Stage 2",63,32,null,null,"2014-02-05","2014-03-04"]
[3479,640040,"Enhancements to Proximity-based Services","eProSe",1,"Rel-13","S1,S2,S3","2013-03-18","2016-03-11",1,"SP-140386","-","Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","-","Stage 1/2",64,33,null,null,"2014-05-27","2014-09-05"]
[3482,640141,"   TR on Stage 2 for Enhancements to Proximity-based Services - Extensions","eProSe-Ext-SA2TR",2,"Rel-13","S2","2014-06-18","2015-03-13",1,"SP-150028","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:60%->90¦07/09/15: 90%->95¦07/09/15: 95%->100","New 23.713",64,33,null,null,"2014-06-17","2015-09-07"]
[3485,680007,"      CT1 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->40¦7/12/15: 40%->90. FCD -> 03/16, ES in CP-150724¦7/3/16: 90%->100",29.343,68,35,null,null,"2015-06-15","2016-03-07"]
[3489,590035,"   Study on Security for Proximity-based Services","FS_ProSe_Sec",2,"Rel-13","S3","2013-03-18","2015-06-17",1,"SP-140629","-","Qualcomm","Adrian Escott (aescott@qti.qualcomm.com)","SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information. 4/3/15: 95%->70% (more topics to be included)¦June2015: Compl:70%->75¦7/12/15: 75%->95¦7/3/1",33.832999999999998,59,30,null,null,"2013-02-20","2016-12-01"]
[3492,640145,"   Stage 1 for voice over E-UTRAN Paging Policy Differentiation","voE_UTRA-N_PPD-SA1",2,"Rel-13","S1","2014-06-16","2014-06-18",1,"SP-140394","-","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#64 approved WID & completed","22.228, 22.278",64,33,null,null,"2014-05-29","2014-06-11"]
[3495,650103,"      CT4 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C4","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Mar.15: 0->100%","29.274, 29.281",65,33,null,null,"2014-07-29","2015-03-04"]
[3496,650203,"      CT1 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C1","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Dec.14: 0->50%¦07/09/15: 50%->50¦7/12/15: 50%->100",24.228999999999999,65,33,null,null,"2014-07-29","2015-12-07"]
[3499,640147,"   TR for IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM-SA2TR",2,"Rel-13","S2","2014-06-18","2015-03-13",1,"SP-140279","-","Tricci So, ZTE","tso@zte.com.cn","Revived the Rel-12 DRAFT TR 23.861 stopped at SP#59 (at 40% completion). Dec.14: 20->60%¦June2015: Compl:60%->90, WID: SP-140279->SP-150250","New 23.861",64,33,null,null,"2014-05-30","2015-06-18"]
[3503,680020,"      CT1 aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",3,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation. ES in 641","zhou.xingyue@zte.com.cn","07/09/15: 0%->25¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 25%->75¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 75%->100","24.301, 24.302, 24.244, 24.008",68,35,null,null,"2015-06-15","2016-03-07"]
[3506,640053,"Double Resource Reuse for Multiple Media Sessions","DRuMS",1,"Rel-13","S2","2014-03-14","2015-03-13",1,"SP-140393","-","Ericsson","George.Foti@ericsson.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-06-11"]
[3509,660047,"      CT1 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,"5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100","24.229, 24.615, 24.610, 24.605",66,34,null,null,"2014-12-09","2015-09-07"]
[3513,640058,"Video enhancements by Region-Of-Interest information signalling","ROI",1,"Rel-13","S4","2014-06-18","2015-12-16",1,"SP-140219","-","Intel","ozgur.oyman@intel.com","Dec.14: 5->20%. Mar.15: 40%¦07/09/15: 43%->100",26.114000000000001,64,33,null,null,"2014-06-06","2015-09-07"]
[3516,680032,"      CT1 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->50¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 50%->100",24.228999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[3517,680033,"      CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->10¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 10%->100",29.161999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[3520,650126,"   TR on TV video profile","TVProf-SA4TR",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16¦7/3/16: 85%->100","New 26.9xy. ES in SP-150650",65,33,null,null,"2014-09-05","2016-03-07"]
[3523,650029,"HTML5 Presentation Layer","HTML5",1,"Rel-13","S4","2014-09-09","2015-12-16",1,"SP-140484","-","Samsung","Imed Bouazizi (i.bouazizi@samsung.com)","Triggered by Rel-12 TR 26.907 (Study of HTML5 and 3GPP User Services). Dec.14: 0->5%. Mar. 15: 10%¦June2015: Compl:10%->20¦Aug2015: 20%->40¦07/09/15: 40%->70¦7/12/15: 70%->100","26.140, 26.234, 26.247, 26.346, New 26.xyz",65,33,null,null,"2014-09-05","2015-12-07"]
[3527,670017,"      CT1 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C1","2015-03-04","2015-12-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->90¦7/12/15: 90%->100",24.007999999999999,67,34,null,null,"2015-03-04","2015-12-07"]
[3530,660073,"   Support of EVS over UTRAN CS","EVSoCS_UTRAN",2,"Rel-13","R2,R1,R3","2015-06-16","2015-12-15",1,"RP-142282",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-15"]
[{"$f":"A3533+1","v":3533},650032,"QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",1,"Rel-13","S4,C3,C1,C4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040","-",59,30,null,null,"2013-02-20","2014-09-20"]
[3537,660044,"      CT3 Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",3,"Rel-13","C3","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,"7/12/15: 0%->70. FCD -> 03/16, ES in CP-150636¦7/3/16: 70%->100","29.162, 29.163, 29.213, 29.214",66,34,null,null,"2014-12-09","2016-03-07"]
[3540,660050,"MTSI Extension on Multi-stream Multiparty","MMCMH",1,"Rel-13",null,"2014-12-12","2016-03-07",0.98,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Mar. 15: 0->10%. WID: SP-140738->SP-150097¦June2015: Compl:10%->30¦Aug2015: 30%->50, FCD: sep->Dec 2015¦07/09/15: 50%->60¦7/12/15: 60%->100¦10/12/15: WID:SP-150097->SP-150660. Might be moved to Rel-14 (see note in UID710002)","26.114, New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[3541,710042,"   Codec aspects for MMCMH","MMCMH",2,"Rel-13","S4","2014-12-12","2015-12-17",1,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Introduced by MCC to dissociate S4 from IeTF aspects","26.114, New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[3544,660051,"Video Telephony Robustness Improvements Extensions","VTRI_EXT",1,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","New TR added. 3/3/15: \"extensions\" added in the title. Mar. 15: 0->10%","26.922 (new), 26.114",66,34,null,null,"2014-12-12","2015-03-05"]
[3547,690038,"   (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627","VTRI_EXT",2,"Rel-13","S4-IETF","2014-12-12","2015-09-11",1,"SP-15047",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added; 23/4/20: 10%->100","26.114, draft-ietf-payload-flexible-fec-scheme",69,35,null,null,"2015-03-03","2020-04-23"]
[3551,560034,"   Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",2,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0","-",56,29,null,null,"2012-05-14","2014-09-01"]
[3554,560235,"   Converged management Performance Management Interface Definitions","OAM-PMID",2,"Rel-13","S5","2012-06-20","2015-12-11",1,"SP-150678","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678","new TSs 32.863 ",56,29,null,null,"2012-05-14","2015-12-07"]
[3558,600044,"   Energy Efficiency related Performance Measurements","OAM-PM_EE",2,"Rel-13","S5","2013-06-21","2016-03-11",1,"SP-140612","-","Nokia Networks","Yizhi.yao@nsn.com","SP#65 updated WID SP-130263=>SP-140612. Completion 09/14=>06/15. Moved to Rel-13¦June2015: Compl:25%->40¦07/09/15: 40%->50. ES in SP-150708¦7/3/16: 50%->100",32.424999999999997,60,31,null,null,"2013-06-02","2016-03-07"]
[3561,640059,"   Inter-PLMN PS domain online charging","iPLMN-PS-OCH",2,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-140324","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations","Stage 2/3",64,33,null,null,"2014-06-06","2014-06-06"]
[3564,660056,"   ULI and release causes for charging enhancement for VoLTE","ULRELC-CH",2,"Rel-13","S5","2014-12-12","2015-12-07",1,"SP-140785",null,"Alcatel-Lucent, Maryse Gardella","Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com","Acronym changed to ULRELC-CH. Mar15: 0->5%. CD: 12/14->09/15. 06/15: 20%¦07/09/15: 20%->40¦7/12/15: 40%->100, FCD: 09/15->12/15","32.251, 32.260, 32.299, 32.298, ",66,34,null,null,"2014-12-12","2015-12-07"]
[3565,670025,"   Charging on enhancements for IMS Service Continuity","CHeISC",2,"Rel-13","S5","2015-03-05","2015-09-09",1,"SP-150055",null,"Gerald Goermer","Gerald <dot> Goermer <at> nsn <dot> com","06/15: 0->50%¦07/09/15: 50%->100. FCD: 12/15->09/15","32.260, 32.299, 32.298",67,34,null,null,"2015-03-05","2015-09-07"]
[3568,610005,"Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS","RTCP_MUX",1,"Rel-13","C4,C1,C3","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Stage 2/3","Stage 2/3",61,31,null,null,"2013-08-10","2014-09-03"]
[3571,610305,"   CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C3","2013-09-13","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15¦8/12/15: 0%->100","29.213, 29.214",61,31,null,null,"2013-08-10","2015-12-08"]
[3575,640019,"Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB_sig",1,"Rel-13","R3","2014-06-18","2015-09-15",1,"RP-141032","-","Samsung","sunghwan.won@samsung.com","Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015)","LTE",64,33,null,null,"2014-06-16","2014-06-23"]
[3578,640136,"   Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Core",2,"Rel-13","R4","2014-06-17","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:5%->15%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL), New 36.862 (Technical Report for 2 GHz Band in Region 1)",64,33,null,null,"2014-06-16","2016-01-01"]
[3582,650134,"   Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments","UTRA_LTE_SON_AAS-Core",2,"Rel-13","R3","2014-09-12","2015-06-15",1,"RP-141624","RP-150727","Nokia Networks","krzysztof.kordybach@nsn.com","CD:Tue 16/06/15->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141854 1st Apr 15: Compl:15%->25% 1st Apr 15: Stat Rep: RP-141854->RP-150110 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150110->RP-150727","36.300, 36.423, 36.413, 25.413",65,33,null,null,"2014-06-16","2015-06-18"]
[3585,660020,"   CT3 Aspect of Usage Monitoring Control extension ","eUMONC-CT3",2,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140927",null,"ZTE",null,"Mar.15: 10->100%","29.212, 29.215",66,34,null,null,"2014-12-04","2015-03-04"]
[3588,660023,"   CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",2,"Rel-13","C4","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,"Mar.15: 0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN","29.274, 29.275",66,34,null,null,"2014-12-04","2015-05-05"]
[3589,660028,"P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",1,"Rel-13","C4","2014-12-03","2015-12-14",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","WID added, acronym. June 2015: WID: CP-140995-> CP-150275",null,66,34,null,null,"2014-12-04","2014-12-09"]
[3592,680012,"Mobile Equipment Identity signalling over WLAN ","MEI_WLAN",1,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com",null,"24.244, 24.302, 29.273, 29.274, 29.275, 23.008",68,35,null,null,"2015-06-15","2015-06-15"]
[3595,680041,"Authentication Signalling Improvements for WLAN","ASI_WLAN",1,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150330",null,"Youyang Yu","yuyouyang@huawei.com","07/09/15: 0%->40¦7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727¦7/3/16: 95%->100","24.302, 24.244",68,35,null,null,"2015-06-15","2016-03-07"]
[3599,670039,"   SAE for support for non-3GPP accesses - Phase 4","SAES4-non3GPP",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->50¦7/12/15: 50%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[3602,660036,"   (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters","INNB_IW",2,"Rel-13","C1-IETF","2014-12-03","2015-03-10",0,"CP-140928",null,"Orange",null,"Mar15: resp WG:C1->C1-IETF. WID changed from INNB_IW-CT1","draft-mohali-dispatch-cause-for-service-number",66,34,null,null,"2014-12-04","2015-03-18"]
[3606,660029,"   CT4 aspects of Warning Status Report in EPS","WSR_EPS",2,"Rel-13","C4","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from \"WSR_EP\"¦7/12/15: 0%->100¦7/12/15: WID:CP-140998->CP-150792",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3609,670096,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3612,670013,"Retry restriction for Improving System Efficiency","RISE",1,"Rel-13","C1","2015-03-04","2015-12-15",1,"CP-150495",null,"Huawei, Lin Shu","shulin@huawei.com","Continuation of Rel-12 SINE UID 620006. 5/5/15: acronym changed from \"RISE\"¦June2015: Compl:0%->10¦07/09/15: 10%->70¦14/09/15: WID:CP-150092->CP-150495¦7/12/15: 70%->100",null,67,34,null,null,"2015-03-04","2015-12-07"]
[3613,670020,"H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",1,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du","duxiaoning@chinamobile.com",null,23.334,67,34,null,null,"2015-03-04","2015-03-09"]
[3616,670026,"Review of dedicated 3GPP UICC features","Red_UCe",1,"Rel-13","C6","2015-03-09","2015-12-11",1,"CP-150152",null,"Blackberry, Adrian Buckley","abuckley@blackberry.com","Results from the homonymous Study¦June2015: Compl:0%->60¦07/09/15: 60%->75¦7/3/16: 75%->100","31.102, 31.111, 31.121, 31.124",67,34,null,null,"2015-03-09","2016-03-07"]
[3620,640044,"(SA66: on hold) Co-ordinated packet data network gateway (P-GW) change for SIPTO","CSIPTO",1,"Rel-13","S1","2014-06-18","2014-09-16",1,"SP-140509","S1-143306","Intel","Eric.siow@intel.com","SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO)",22.100999999999999,64,33,null,null,"2014-05-27","2014-12-12"]
[3623,640151,"   TR for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S2","2014-06-18","2014-12-12",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Dec.14: 35->85%¦14/09/15: 85%->100. SA#69: decision not to continue the work on this. No normative work.","New 23.772",64,33,null,null,"2014-06-11","2015-09-14"]
[3626,650025,"SRVCC Enhancements for Transcoding Avoidance","SETA",1,"Rel-13","S2","2014-09-19","2015-06-17",1,"SP-140436","-","Ericsson","George.Foti@ericsson.com","Enhance chances for end-to-end transcoder free operation (TrFo) where possible/ ensure proper CS radio resources are reserved for optimal RAN codec. Address TrFo of EVS codecs during SRVCC that are not covered by Rel-12","Stage 2",65,33,null,null,"2014-08-05","2014-12-12"]
[3630,590130,"   Core part: Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA-Core",2,"Rel-13","R4","2013-03-04","2016-03-15",1,"RP-160188","RP-151241","Huawei","ronnie.zhang@huawei.com","¦CD:Thu 11/12/14->Tue 15/12/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241¦","New 37.142 (AAS BS Tx & Rx), New 37.842, 37.114, 37.145-1, 37.145-2",59,30,null,null,"2013-02-26","2016-03-22"]
[3633,660174,"   Core part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Core",2,"Rel-13","R2,R1,R3","2015-08-14","2016-03-15",1,"RP-150441","RP-151337","Qualcomm Incorporated, Shailesh Patil","patil@qti.qualcomm.com ","Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3636,660176,"   Core part: Radiated requirements for the verification of multi-antenna reception performance of UEs","UTRA_LTE_MIMO_OTA-Core",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-160344","RP-151573","Intel","Intel","1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142221->RP-150261 1st Apr 15: Stat Rep: ->RP-150260 03/07/15: Compl:5%->15% 03/07/15: Stat Rep: RP-150260->RP-150746 29/09/15: Compl:15%->25% 29/09/15: WID: RP-150261->RP-151574 29/09/15: Stat Rep: RP-15074",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3637,660077,"UE core requirements for uplink 64 QAM","LTE_UL64QAM",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-142222",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3640,660078,"Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS",1,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-142223",null,"China Telecom","China Telecom",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3644,670055,"Dual Connectivity enhancements for LTE","LTE_dualC_enh",1,"Rel-13","R2","2015-03-16","2016-06-15",1,"RP-150490",null,"NTT DOCOMO",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3647,670056,"Multicarrier Load Distribution of UEs in LTE","LTE_MC_load",1,"Rel-13","R2","2015-03-16","2016-09-15",1,"RP-150491",null,"ZTE",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3650,670058,"LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio",1,"Rel-13","R2","2015-03-16","2018-09-14",0.99,"RP-150510",null,"Intel",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3654,670060,"RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network","CSPS_Coord-UTRA",1,"Rel-13","R3","2015-03-16","2015-12-15",1,"RP-150500",null,"Ericsson",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3657,670161,"   Core part: LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150427","RP-151265","Ericsson",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150803->RP-151265¦1/1/16: Compl:50%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3660,670062,"AWS-Extension Band for LTE","LTE_AWS_EXT",1,"Rel-13","R4","2015-03-16","2016-09-15",1,"RP-150428",null,"Ericsson",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[{"$f":"A3661+1","v":3661},670162,"   Core part: AWS-Extension Band for LTE","LTE_AWS_EXT-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150800","RP-151343","Ericsson",null,"03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3664,670063,"Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset",1,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150171",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3668,670164,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425","RP-150536","Samsung",null,"03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3671,670154,"   Core part: Multiflow Enhancements for UTRA","HSDPA_MFTX_enh-Core",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-151021","RP-151302","Nokia","alexander.sayenko@nokia.com","03/07/15: Compl:0%->80% 03/07/15: WID: RP-150288->RP-151021 03/07/15: Stat Rep: ->RP-150827 29/09/15: Compl:80%->100% 29/09/15: Stat Rep: RP-150827->RP-151302",null,67,34,null,null,"2015-05-05","2015-09-29"]
[3674,680046,"   CT3 aspects of Message interworking during PS to CS SRVCC ","mSRVCC",2,"Rel-13","C3","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com","07/09/15: 0%->70¦7/12/15: 70%->100",29.292000000000002,68,35,null,null,"2015-06-15","2015-12-07"]
[3677,690009,"   CT aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",2,"Rel-13","ct","2015-09-07","2016-03-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[3680,690023,"      CT4 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C4","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 0%->100","23.003, 23.008, 29.273, 29.274",69,35,null,null,"2015-09-07","2015-12-07"]
[3681,690036,"      CT6 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C6","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/3/16: 0%->100",31.102,69,35,null,null,"2015-09-07","2016-03-07"]
[3684,690046,"   MBMS Enhancements","MBMS_enh_St2",2,"Rel-13","S2","2015-08-10","2015-09-16",1,"SP-150520",null,"Nokia Networks, Curt Wong",null,"SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_","23.246, 23.468",69,35,null,null,"2015-09-16","2015-10-14"]
[3687,700007,"      CT4 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C4","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,"29.274, 23.008, 29.230",70,36,null,null,"2015-12-07","2015-12-07"]
[3691,690027,"   CT4 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C4","2015-09-07","2015-12-18",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: 95%->100","29.274, 29.274, 29.275, 29.282, 29.273, 29.230, 23.008, 29.273",69,35,null,null,"2015-09-07","2015-12-07"]
[3694,700010,"   CT4 aspects of DiaPri","DiaPri",2,"Rel-13","C4","2015-11-02","2016-03-11",1,"CP-150613",null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com","ES in CP-150622¦7/3/16: 70%->100","29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.338, 29.344, 29.345",70,36,null,null,"2015-12-07","2016-03-07"]
[3697,680159,"   Core part: Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC-Core",2,"Rel-13","R1,R2,R3","2015-10-15","2015-12-15",1,"RP-151880","RP-151564","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3701,680260,"   Perf. part: Licensed-Assisted Access using LTE","LTE_LAA-Perf",2,"Rel-13","R4","2015-06-15","2016-12-15",1,"RP-151045",null,"Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Stat Rep: -->RP-15139022/3/16: Compl:0%->33%¦1/7/16: Compl:3¦26/9/16: Compl:50%->90%¦20/12/16: Compl:90%->100%¦20/12/16: Stat Rep: RP-151390->",null,68,35,null,null,"2015-07-03","2016-12-20"]
[3704,680161,"   Core part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO-Core",2,"Rel-13","R1","2015-06-15","2015-12-15",1,"RP-151085","RP-151565","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-151565 1/1/16: Compl:25%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3705,680261,"   Perf. part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO-Perf",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151085","RP-151565","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Stat Rep: -->RP-151565 ¦1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->35%;26/9/16: Compl:70%->100%",null,68,35,null,null,"2015-07-03","2016-09-26"]
[3708,680162,"   Core part: L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-152184","RP-151238","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3711,680264,"   Perf. part: Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-Perf",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151110","RP-151237","Huawei",null,"follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Stat Rep: -->RP-1512371/1/16: Compl:0%->100% ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3715,680067,"RAN sharing enhancements for UMTS","RSE_UTRA_GUSH",1,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151086","-","Huawei",null,"no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3718,680271,"   Perf. part: Interference mitigation for downlink control channels of LTE","LTE_IM_DLCCH-Perf",2,"Rel-13","R4","2015-06-15","2016-06-15",1,"RP-160908","RP-151301","Intel",null,"only Perf. part, no Core part¦29/09/15: CD:Tue 15/03/16->Wed 15/06/16 29/09/15: Stat Rep: -->RP-1513011/1/16: Compl:0%->40%22/3/16: Compl:40%->70%",null,68,35,null,null,"2015-07-03","2016-07-01"]
[3722,690064,"Dual Carrier HSUPA Enhancements for UTRAN CS","DC_HSUPA_CS",1,"Rel-13","R2","2015-09-15","2015-12-15",1,"RP-151607","-","Nokia Networks",null,"no Perf. part¦compare REL-13 WI HSUPA_DB_MC",null,69,35,null,null,"2015-09-29","NA"]
[{"$f":"A3725+1","v":3725},670042,"   Study on further Enhancements of Minimization of Drive Tests for E-UTRAN","FS_LTE_eMDT2",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-150472","RP-151181","CMCC",null,"03/07/15: Compl:0%->70% 03/07/15: Stat Rep: -->RP-150806 29/09/15: Compl:70%->100% 29/09/15: Stat Rep: RP-150806->RP-151181",36.880000000000003,67,34,null,null,"2015-04-01","2015-09-29"]
[3728,690066,"LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy",1,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-151615","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio",null,69,35,null,null,"2015-09-29","NA"]
[3729,690166,"   Core part: LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy-Core",2,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-160608","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio1/1/16: Compl:0%->95% 22/3/16: Compl:95%->100%¦28/7/16: 36.361 added;",36.360999999999997,69,35,null,null,"2015-09-29","2016-07-28"]
[3732,690267,"   Perf. part: Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh-Perf",2,"Rel-13","R4","2015-09-15","2016-06-15",1,"RP-160332","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh 1/1/16: Compl:0%->10% 1/1/16: WID: RP-151624->RP-152251¦22/3/16: Compl:10%->20%¦22/3/16: WID: RP-152251->RP-160332 28/7/16: 37.171 added¦28/7/16: 37.958 added;","37.171; 37.958",69,35,null,null,"2015-09-29","2016-07-28"]
[3735,720099,"   UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS","UTRA_LTE_iPos_enh-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-170233",null,"NextNav",null,"tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl:",null,72,37,null,null,"2016-07-01","2017-03-21"]
[3739,680073,"700MHz E-UTRA FDD Band for Arab Region","LTE_FDD_700_ARAB",1,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151042","-","Etisalat",null,"REL-independent from REL-9",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3742,680075,"European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150861","-","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3746,620063,"Service Requirements Maintenance for Machine-Type Communications (MTC)","SRMMTC",1,"Rel-13","S1","2015-09-15","2016-06-10",1,"SP-130600","-","KPN","toon.norp@tno.nl","SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13.",22.367999999999999,62,32,null,null,"2013-11-26","2014-09-03"]
[3749,700046,"   Security Aspects of CIoT (aka NB-IoT)","CIoT",2,"Rel-13","S3","2015-11-02","2016-06-10",1,"SP-150844",null,"Tim Evans, Vodafone",null,"7/3/16: 0%->39¦19/9/16: 39%->100",33.401000000000003,70,36,null,null,"2015-12-07","2016-09-19"]
[3752,700051,"      CT3 aspects of CIoT","CIoT-CT",3,"Rel-13","C3","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->90¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 90%->100","29.061, 29.212",70,36,null,null,"2015-12-07","2016-06-13"]
[3753,700015,"      CT4 aspects of CIoT","CIoT-CT",3,"Rel-13","C4","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->65¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 65%->100","29.272, 29.274, 23.008, 23.007, 29.128, 29.275, 29.230, 29.336, 29.281, 29.002, 29.303",70,36,null,null,"2015-12-07","2016-06-13"]
[3756,690063,"   RAN aspects of CIoT aka Narrowband Internet of Things (IOT)","NB_IOT",2,"Rel-13","R1","2015-09-15","2016-12-15",1,"RP-151621","-","Vodafone",null,"no Perf. part¦note: WI only stays in REL-13 because of PCG decision",null,69,35,null,null,"2015-09-29","NA"]
[3759,720043,"   Management for NB-IoT","NB_IOT-OAM",2,"Rel-13","S5","2016-05-12","2016-06-15",1,"SP-160396",null,"Huawei, Kai ZHANG","kai.zhangkai@huawei.com","13/6/16: 0%->100","28.657, 28.658, 28.659, 32.425",72,37,null,null,"2016-06-13","2016-06-13"]
[3763,700004,"   Test for CIoT_EC_GSM","CIoT_EC_GSM_GERAN3new",2,"Rel-13","G3","2015-11-11","2016-05-12",0,"GP-151149",null,"Sierra Wireless S.A","Marteen.Sunberg@Ericsson.com","7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new",null,70,36,null,null,"2015-09-07","2016-03-02"]
[3766,690005,"Extended DRX cycle for Power Consumption","eDRX",1,"Rel-13","S2,R2,G2","2014-12-03","2016-09-15",0.93,"SP-150369",null,"Miguel Griot","mgriot@qti.qualcomm.com","June2015: WID:SP-150254->SP-150369","23.401, 23.060, 23.682, 23.271, 23.272",68,35,null,null,"2015-06-18","2015-06-18"]
[3770,690020,"      CT1 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100","24.301, 24.008, 29.118",69,35,null,null,"2015-09-07","2016-03-07"]
[3773,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[3776,710071,"   UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE","LTE_extDRX-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-160602","-","Qualcomm",null,"testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT;",null,71,36,null,null,"2016-03-22","2016-09-26"]
[3777,690001,"   Extended DRX (eDRX) for GSM","eDRX_GSM",2,"Rel-13","G2,G1","2015-08-28","2016-05-12",0.44,"GPC150624",null,"John Diachina, Ericsson LM","John.Diachina@Ericsson.com","07/09/15: 0%->40¦7/12/15: 40%->100","43.064, 44.018, 44.060, 45.008, 48.018, 43.022",69,35,null,null,"2015-08-12","2015-12-07"]
[3780,670027,"Optimizations to Support High Latency Communications","HLcom",1,"Rel-13","S2","2014-09-19","2015-12-16",1,"SP-150030",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com",null,"23.401, 23.060, 23.682",67,34,null,null,"2015-03-05","2015-03-05"]
[3784,650033,"Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1",1,"Rel-13","R1,R4,R2","2014-09-12","2017-09-15",0.99,"RP-141660","-","Ericsson","johan.bergman@ericsson.com","Triggered by Rel-12 TR 36.888 Study on Provision of low-cost MTC UEs based on LTE (FS_LC_MTC_LTE) and Low cost & enhanced coverage MTC UE for LTE (LC_MTC_UE)","LTE",65,33,null,null,"2014-06-16","2014-10-05"]
[3787,710067,"   UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-UEConTest",2,"Rel-13","R5","2016-03-15","2017-09-15",1,"RP-171156",null,"Ericsson",null,"testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3790,640150,"   TR for Group based Enhancements","GROUPE",2,"Rel-13","S2","2014-06-18","2015-03-18",1,"SP-140706","-","Huawei, Wanqiang Zhang","ZhangWanqiang@huawei.com","Dec.14: 20->70%. Mar15: 90%¦June2015: Compl:90%->100","New 23.769",64,33,null,null,"2014-05-30","2015-06-15"]
[3794,680016,"   CT aspects of Group based Enhancements","GROUPE-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","7/12/15: WID:CP-150240->CP-150816","24.008, 24.301, 29.468, 29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003",68,35,null,null,"2015-06-15","2015-12-07"]
[3797,680030,"      CT4 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->80¦7/12/15: 80%->100¦7/12/15: WID:CP-150240->CP-150816","29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003",68,35,null,null,"2015-06-15","2015-12-07"]
[3800,640249,"   Stage 2 for Monitoring Enhancements","MONTE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140705","-","Intel, Puneet Jain","puneet.jain@intel.com","-¦June2015: Compl:0%->100","23.682, TBD",64,33,null,null,"2014-05-30","2015-06-15"]
[3801,640349,"   TR on Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-18","2015-06-12",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs.3/3/15: 5->10%.¦June2015: Compl:10%->15¦11/12/15: 15%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[3804,680011,"   Monitoring Enhancements CT aspects","MONTE-CT",2,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","14/09/15: WID:CP-150396->CP-150422",null,68,35,null,null,"2015-06-15","2015-09-14"]
[3808,640046,"Dedicated Core Networks","DECOR",1,"Rel-13","S2","2014-06-18","2016-03-11",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","06/15: WID: SP-140707-> SP-150249","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[3811,690004,"   CT aspects of Dedicated Core Networks","DECOR-CT",2,"Rel-13","ct","2015-06-25","2016-03-11",1,"CP-150423",null,"Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com)","Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com)",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[3814,680066,"   Dedicated Core Networks RAN Aspects","DECOR-UTRA_LTE",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151048","-","Ericsson",null,"no Perf. part¦note: DECOR is a REL-13 SA2 WI;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3818,610230,"   Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-09-17",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#65 completed","22.101, 22.115, 22.368, TBD",61,31,null,null,"2013-08-26","2014-08-28"]
[3821,640248,"   Stage 2 for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140704","-","Intel, Puneet Jain","puneet.jain@intel.com","-¦June2015: Compl:0%->100","23.682, 33.187",64,33,null,null,"2014-05-30","2015-06-15"]
[3824,680001,"   CT aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","14/09/15: WID:CP-150402->CP-150487->CP-150576",null,68,35,null,null,"2015-06-15","2015-09-14"]
[3825,680023,"      CT3 aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",3,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei. FCD+3, ES in 642","wuyizhuang@huawei.com","07/09/15: 0%->35¦14/09/15: WID:CP-150402->CP-150487->CP-150576¦7/12/15: 35%->90¦7/3/16: 90%->100",29.154,68,35,null,null,"2015-06-15","2016-03-07"]
[3828,690080,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3832,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3835,620123,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27","LTE_CA_B8_B27-Core",3,"Rel-13","R4","2013-12-09","2015-12-15",0.3,"RP-140120","RP-151131","KT","ilwhan.kim@kt.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101, 36.104, 36.133, generic 36.851",62,32,null,null,"2013-12-07","2015-09-29"]
[3838,620132,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27-Core",3,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","RP-151131","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Thu 18/06/15->Mon 15/06/15¦Compl:25%->25%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2015-09-29"]
[3842,630233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22-Perf",3,"Rel-13","R4","2014-03-11","2015-06-15",1,"RP-140094","RP-150536","Orange, Ericsson","erika.tejedor@ericsson.com","CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-141732->RP-150536","36.141, 36.307",63,32,null,null,"2014-03-10","2015-06-18"]
[3845,640222,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","RP-150536","U.S. Cellular","sebastian.thalanany@uscellular.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:0%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, 36.141, 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[3846,640025,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140692","-","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[3849,640032,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140974","-","Huawei","leo.liuye@huawei.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[3852,650037,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38","LTE_CA_B3_B38",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141129","-","Nokia Networks","iwajlo.angelow@nsn.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3856,650138,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3859,650139,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->35%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3862,650140,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40-Core",3,"Rel-13","R4","2014-09-12","2015-12-15",1,"RP-141168","RP-151131","Ericsson","imadur.rahman@ericsson.com","CD:Wed 11/03/15->Sun 15/03/15¦Compl:0%->30%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:30%->70% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2016-01-01"]
[3866,650241,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","RP-151131","KT","ilwhan.kim@kt.com","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1","36.141, 36.307",65,33,null,null,"2014-06-16","2016-01-01"]
[3869,650242,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150832","RP-150536","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3870,650043,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141336","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3873,650044,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141337","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3876,650045,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40",2,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141675","-","SK Telecom","haesung.park@sk.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3880,650147,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_C_B42_3DL-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-151027","RP-150536","CATT","Yuexia Song (songyuexia@catt.cn)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Sta","36.101, 36.104, 36.133, New 36.833-5-42",65,33,null,null,"2014-06-16","2015-06-18"]
[3883,650149,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141845","RP-150536","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3887,650251,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3890,650253,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29","LTE_CA_B2_B5_B29-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141667","RP-150536","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3893,660272,"      Perf. part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C-Perf",3,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-151984","RP-151285","Nokia Networks","Nokia","1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Stat Rep: RP-150769->RP-151285¦22/3/16: ;",null,66,34,null,null,"2015-01-12","2016-07-01"]
[3894,730074,"      UE Conformance Test Aspects - LTE Carrier Aggregation Enhancement Beyond 5 Carriers: PUCCH on Scell","LTE_CA_enh_b5C_PUCCH-UEConTest",3,"Rel-13","R5","2016-09-15","2018-09-14",1,"RP-192558",null,"Huawei",null,"¦20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%¦19/9/17: Compl:8%->15%¦8/1/18: 27/3/18; 14/1/20: WID:RP-171764->RP-192558; 14/1/20: 20%->100",null,73,37,null,null,"2016-09-26","2020-01-14"]
[3897,660280,"      Perf. part: HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-151852","RP-151281","Qualcomm","Qualcomm","1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Stat Rep: RP-150761->RP-1512811/1/16: Compl:0%->90% ¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3900,660281,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3904,660083,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777",null,"China Unicom","China Unicom",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3907,660084,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141791",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3911,660185,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42","LTE_CA_B21_B42_B42-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150640","RP-150536","NTT DOCOMO","NTT DOCOMO","1st Apr 15: Compl:0%->90% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3913,660086,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141802",null,"ZTE","ZTE",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3916,660087,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28",2,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-141826",null,"Softbank Mobile","Softbank Mobile",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[{"$f":"A3917+1","v":3917},660187,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3920,660188,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7_Bwset-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141881","RP-150536","Ericsson","Ericsson","Acronym changed from LTE_CA_B3_B7_B7-Core 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3923,660189,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28","LTE_CA_B7_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141882","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3927,660290,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151258","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3930,660291,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151259","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3934,660093,"   LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3937,660094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142038",null,"Nokia Networks","Nokia Networks",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3940,660095,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28",2,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193",null,"Softbank Mobile","Softbank Mobile",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3941,660195,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3944,660196,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/",null,66,34,null,null,"2015-01-12","2016-03-22"]
[3948,660297,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3951,660298,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-151071","RP-150536","Huawei","Huawei","03/07/15: Compl:0%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3954,660299,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150234","RP-150536","Huawei","Huawei","1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[3958,661001,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238",null,"Intel","Intel",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3961,661002,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28","LTE_CA_B3_B7_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142244",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3964,661003,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142198",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3965,661103,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150449","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3968,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3972,661205,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150450","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3975,661206,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150452","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3978,661207,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150451","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3982,661009,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3985,661010,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141935",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[3986,661110,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150678","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3989,661111,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3992,661112,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13","LTE_CA_2UL_R13-A3-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150409","RP-151131","Ericsson","Ericsson","1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[3996,661213,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 18/12/18->Tue 15/12/15 1st Apr 15: Stat Rep: -->RP-150013 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150536->RP-151131 ¦",null,66,31,null,null,"2013-09-14","2016-01-01"]
[3999,670265,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150641","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4002,670266,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150642","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4006,670068,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42","LTE_CA_B3_B19_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150124",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4009,670069,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150125",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4010,670169,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4013,670170,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4016,670171,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4020,670272,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12","LTE_CA_B2_B7_B12-Perf",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150431","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 122/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4023,670273,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7-Perf",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 1/1/1¦22/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4026,670274,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4030,670076,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150074",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4033,670077,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150075",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4034,670177,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150658","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4037,670178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151216","RP-151131","SK Telecom",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4040,670179,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4044,670280,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4047,670281,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064","RP-151131","KDDI",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4051,670083,"   LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150479",null,"Nokia Corporation",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4054,670084,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246",null,"Huawei",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4057,670085,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150437",null,"CMCC",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4058,670185,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151177","RP-151131","CMCC",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4061,670186,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438","RP-151131","CATT",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4064,680177,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11","LTE_CA_B1_B8_B11-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150609","RP-151131","Softbank Mobile",null,"29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4068,680278,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32-Perf",3,"Rel-14","R4","2015-06-15","2016-03-15",0.9,"RP-150864","RP-151131","Ericsson",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->90%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4071,680279,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","RP-151131","Huawei",null,"29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4075,680081,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","-","Nokia Networks",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4078,680082,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","-","KDDI",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4081,680083,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151112","-","KDDI",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4082,680183,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151158","RP-151131","KDDI",null,"29/09/15: Compl:0%->40% 29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4085,680185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","RP-151131","Rogers Communications",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4088,680186,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4092,680287,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4095,680288,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4099,680090,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4102,680091,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4105,680092,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4106,680192,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[{"$f":"A4109+1","v":4109},680193,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4113,680294,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4116,680295,"      Perf. part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4119,680296,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4123,680098,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4126,681000,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4129,681001,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4130,681101,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4133,681102,"      Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4137,681203,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4140,681204,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","RP-151131","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4143,681205,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4147,680074,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","-","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4150,680076,"   Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","-","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4152,680276,"      Perf. part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","RP-151131","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4153,680072,"   Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151037","-","Huawei",null,"Aug 15: TR numb added",null,68,35,null,null,"2015-08-12","2015-08-12"]
[4156,710068,"      UE Conformance Test Aspects - Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China-UEConTest",3,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161679","-","Huawei",null,"testing REL-13 LTE_TDD_1447MHz_China-Core¦1/7/16: C¦",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4160,690073,"   LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4163,690074,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4166,690075,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40","LTE_CA_B5_B40_B40",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151200","-","ZTE",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4170,690176,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[{"$f":"A4173+1","v":4173},690177,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 ","LTE_CA_B3_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151448","-","ZTE",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4174,690277,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 ","LTE_CA_B3_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151448","-","ZTE",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4177,690278,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4180,690279,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4184,690083,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40","LTE_CA_B3_B28_B40_B40",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151363","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4187,690084,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4190,690085,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4194,690189,"      Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42","LTE_CA_B1_B3_B19_B42_B42-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151159","-","NTT DOCOMO",null,null,"36.857-13",69,35,null,null,"2015-09-29","2016-01-01"]
[4197,690190,"      Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4198,690290,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4201,690291,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-160141","-","Telstra",null,"22/3/16: Compl:95%->100%;",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4204,690292,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151513","-","Telstra",null,"¦22/3/16: Compl:95%->100%",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4208,690094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case¦5/10/15: 36.899-13 added;","36.899-13",69,35,null,null,"2015-09-29","2015-10-05"]
[4211,690095,"   Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12",null,69,35,null,null,"2015-09-29","NA"]
[4215,610034,"(Small) Technical Enhancements and Improvements for Rel-13","TEI13",1,"Rel-13","SP,CP,RP,GP","2013-09-18","2015-12-21",1,"-","PCG-31","-","-","-","-",61,31,null,null,"2015-01-12","2013-09-14"]
[4218,690007,"(Small) Security Enhancements and Improvements for Rel-13","SEC13",1,"Rel-13","S3","2006-12-12","2015-12-21",1,"-","PCG-31","-","-","-","-",61,31,null,null,"2015-01-12","2013-09-14"]
[4221,640001,"Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things","FS_IoT_LC",1,"Rel-13","G1,G2","2014-05-30","2015-08-28",1,"GP-150354","-","Vodafone","chris.pudney@vodafone.com","GP#62 approved WID. Dec.14: 15->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100¦14/09/15: WID:GP-140421->GP-150354","45.8xy",66,33,null,null,"2014-05-30","2015-09-14"]
[4222,670029,"Study on architecture enhancements of cellular systems for ultra low complexity and low throughput Internet of Things","FS_AE_CIoT",1,"Rel-13","S2","2015-03-13","2015-12-11",1,"SP-150167",null,"puneet.jain@intel.com","puneet.jain@intel.com","07/09/15: 0%->20¦07/09/15: 20%->65¦7/12/15: 65%->95¦7/3/16: 95%->100","New 23.8xx",67,34,null,null,"2015-03-13","2016-03-07"]
[4225,570034,"Study on Application specific Congestion control for Data Communication","FS_ACDC",1,"Rel-13","S1","2012-09-17","2014-09-17",1,"SP-130415","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion)",22.806000000000001,57,29,null,null,"2012-08-31","2014-08-29"]
[4228,600046,"Study on Isolated E-UTRAN Operation for Public Safety","FS_IOPS",1,"Rel-13","S1","2013-06-25","2014-06-18",1,"SP-130596","-","General Dynamics","paul.piggin@gd-broadband.com","SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and FeaturES in CP-150ProSe, GCSE_LTE",22.896999999999998,60,31,null,null,"2013-05-30","2014-05-27"]
[4232,620069,"Study on Flexible Mobile Service Steering","FS_FMSS",1,"Rel-13","S1","2013-12-13","2014-09-17",1,"SP-130597","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 completed. TR 22.808v200 for Approval. Study supporting traffic classification and service chain selection capabilities per operator’s policy in order to realize efficient and flexible mobile service steering in the Gi-LAN network",22.808,62,32,null,null,"2013-11-26","2014-08-28"]
[4235,520035,"Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group","FS_UMONC_sas",1,"Rel-13","S2","2011-06-08","2014-12-12",1,"SP-140403","-","China Telecom","Jinyan Li (lijy@ctbri.com.cn)","SP#64 revived. Added to the Title \"for Service, Application and Subscriber Group\", Changed Acronym: FS_UMONC=>FS_UMONC_sas",23.858000000000001,52,27,null,null,"2011-05-19","2014-06-19"]
[4239,500034,"Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int_Sec",1,"Rel-13","S3","2010-12-28","2015-06-12",1,"SP-150368","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%¦June2015: Compl:65%->100¦June2015: WID:SP-140576->SP-150368",33.895000000000003,50,26,null,null,"2010-11-25","2015-06-18"]
[4242,620059,"Study on Application and Partitioning of Itf-N","FS_OAM_AP_Itf-N",1,"Rel-13","S5","2013-12-17","2015-09-11",1,"SP-130681","-","China Mobile","Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com)","-Dec.14: 15->30%, CD: 12/14->09/15¦June2015: Compl:30%->60¦07/09/15: 60%->100","32.861 ",62,32,null,null,"2013-11-28","2015-09-07"]
[4245,590010,"Study on Review of dedicated 3GPP UICC features","FS_Red_UCe",1,"Rel-13","C6","2013-03-13","2015-12-16",1,"CP-130168","-","BlackBerry","Adrian Buckley (abuckley@blackberry.com)","CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100%",31.901,59,30,null,null,"2013-02-20","2014-12-03"]
[4246,490006,"Study on Solutions for GSM/EDGE BTS Energy Saving","FS_Energy_BTS",1,"Rel-13","G1,G2","2011-08-30","2015-11-20",1,"GP-101638","-","Nokia Networks","juergen.hofmann@nokia.com","GP#63 moved to Rel-13. Completion 08/14=>11/14. GP#55 TR 45.926v100 for Information. GP#47 approved WID. Dec.14: 90->95%. 3/3/15: start date corrected (was 03/09). 7/9/15: FCD: 8/15->11/15¦7/12/15: 95%->100",45.926000000000002,47,25,null,null,"2010-09-05","2015-12-07"]
[4249,620013,"Stopped at 20% - Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO)","FS_UL_MU_MIMO",1,"Rel-13","G1,G2","2014-04-17","2016-02-19",1,"GP-131131","-","Huawei","Chao Luo (chluo@huawei.com)","GP#62 completion 11/14=>02/15. GP#60 approved WID. Dec.14: 02/15->05/15. 02/03/16: stopped at 20%",45.875999999999998,60,32,"SP#71",null,"2013-11-22","2014-12-03"]
[4253,640016,"Study on Advanced Wireless Services (AWS) - Extension band for LTE","FS_LTE_AWS_EXT",1,"Rel-13","R4","2013-12-16","2014-12-15",1,"RP-141037","RP-141968","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141429->RP-141968. 5/5/15: 2nd TR number added (to be clarified why two TR for a same topic)","36.849, 36.869",64,33,null,null,"2014-06-16","2015-05-05"]
[4256,650015,"Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","FS_LTE_EBF_FDMIMO",1,"Rel-13","R1","2014-09-12","2015-06-15",1,"RP-150930","RP-150734","Nokia Networks (DL), Samsung (UL)","bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com","3/3/15: WID: RP-141831¦Stat Rep: -->RP-141822, impacted TR number added. 1st Apr 15: Compl:30%->45% 1st Apr 15: Stat Rep: RP-141822->RP-150346. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake) 03/07/15: Compl:45%->100% 03/07/15: WID: RP-141831->RP-1",36.896999999999998,65,33,null,null,"2014-09-15","2015-06-18"]
[4259,660057,"Study on Video Enhancements in 3GPP Multimedia Services","FS_VE_3MS",1,"Rel-13","S4","2014-12-12","2015-12-11",1,"SP-140741",null,"Ye-Kui Wang, Qualcomm Incorporated","yekuiw@qti.qualcomm.com","Mar. 15: 0->20%¦June2015: Compl:20%->40¦07/09/15: 40%->80¦7/12/15: 80%->100",null,66,34,null,null,"2014-12-12","2015-12-07"]
[4263,660066,"Study on Support of single-cell point-to-multipoint transmission in LTE","FS_LTE_SC_PTM",1,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150177","RP-150695","Jeff GAO","gaoyongqiang@huawei.com","deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695",36.89,66,34,null,null,"2015-01-12","2015-06-18"]
[4266,660069,"Study on RAN sharing enhancements for UMTS","FS_RSE_UTRA_GUSH",1,"Rel-13","R3","2014-12-15","2015-06-15",1,"RP-150686","RP-150684","Huawei","Huawei","03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3)",25.756,66,34,null,null,"2015-01-12","2015-10-07"]
[4269,660061,"Study on Enhanced Multiuser Transmissions and Network","FS_MUIC_LTE",1,"Rel-13","R1","2014-12-12","2015-12-11",0,"RP-142315",null,"Pei-Kai Liao","pk.liao@mediatek.com","TR added",36.890999999999998,67,34,null,null,"2014-12-12","2015-01-29"]
[4270,670040,"Study on regulatory aspects for flexible duplex for E-UTRAN","FS_LTE_flex_duplex_reg",1,"Rel-13","RP","2016-06-15","2016-12-15",1,"RP-150470","RP-151307","LG Electronics Inc.",null,"TR added 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: -->RP-150770 29/09/15: Compl:5%->100% 29/09/15: Stat Rep: RP-150770->RP-151307",36.881999999999998,67,34,null,null,"2015-04-01","2015-09-29"]
[4273,670087,"Study on Phase 1 of the Support of Emergency services over WLAN","FS_SEW",1,"Rel-13","S2","2015-03-12","2015-06-18",1,"SP-150251",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251","new 23.771",67,34,null,null,"2015-04-01","2015-06-18"]
[4277,680055,"Study on Network Assistance for Network Synchronization in LTE","FS_LTE_NW_SYNC",1,"Rel-14","R3","2015-06-15","2016-12-15",1,"RP-151252",null,"Huawei",null,"Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: WID: RP-151084->RP-151252 29/09/15: Stat Rep: -->RP-151240 22/3/16: Compl:60%->80%¦22/3/16: CD:Tue 15/03/16->Wed 15/06/16¦ ¦","New 36.898",68,35,null,null,"2015-07-03","2016-12-20"]
[4280,690061,"Study on new AWS-3/4 Band for LTE","FS_LTE_AWS_3_4",1,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151626","-","Dish Network",null,null,36.869999999999997,69,35,null,null,"2015-09-29","2016-01-01"]
[4283,0,"--- RELEASE 12 ---","-",1,"Rel-12","SP,CP,RP,GP","2013-10-14","2014-12-12",1,"-","-","-","-","-","-",null,null,null,null,"2011-09-08","2014-09-17"]
[4287,500031,"Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers","MOSAP",1,"Rel-12","S1,S2","2010-12-16","2013-12-11",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#58 Stage 2 stopped (TR only, no normative work done)","Stage 1",50,26,null,null,"2010-11-29","2012-11-22"]
[4290,520026,"   Deleted - Stage 2 for MOSAP","MOSAP-SA2Del",2,"Rel-12","S2","2011-06-14","2012-12-12",1,"SP-120427","-","Intel","chang.hong.shan@intel.com","SP#58 stopped (no normative work done)","TBD",52,27,"SP-58","PCG-30","2011-05-26","2012-11-22"]
[4293,530043,"Service and Media Reachability for Users over Restrictive Firewalls","SMURFs",1,"Rel-12","S1","2011-09-21","2012-06-20",1,"SP-110653","-","Vodafone","mona.mustapha@vodafone.com","SP#56 Stage 1 completed","Stage 1",53,27,null,null,"2011-07-19","2011-09-15"]
[4294,530143,"   Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls","SMURFs-SA1",2,"Rel-12","S1","2011-09-21","2012-06-20",1,"SP-110653","-","Vodafone","mona.mustapha@vodafone.com","SP#56 completed",22.277999999999999,53,27,null,null,"2011-07-19","2012-06-08"]
[4297,550025,"Integration of Single Sign-On (SSO) frameworks with 3GPP networks","SSO_Int",1,"Rel-12","S1","2012-03-08","2012-09-12",1,"SP-120184","-","InterDigital","christopher.wallace@interdigital.com","SP#57 Stage 1 completed. Triggered by Rel-12 TR 22.895. Linked to SA3 33.8xy (Study on Security aspects of SSO_Int), 33.914 (SSO application security for common IMS based on SIP Digest), 33.924 (i/w GBA and OpenID), 33.980 (i/w GBA and Liberty Alliance)","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[{"$f":"A4301+1","v":4301},570027,"IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2)","IMSSat",1,"Rel-12","S1","2012-02-02","2012-09-12",1,"SP-120543","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS","Stage 1",57,29,null,null,"2012-08-06","2012-08-08"]
[4304,580160,"   Stage 1 for Sequential Flexible Alerting","SEQ_FA",2,"Rel-12","S1","2012-12-10","2012-12-12",1,"SP-120895","-","Orange","bruno.tossou@orange-ftgroup.com","SP#58 approved WID & Stage 1 completed",22.172999999999998,58,30,null,null,"2012-11-16","2012-11-21"]
[4307,590040,"Emergency Session Identification","ESID",1,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130126","-","Telecom Italia","carmen.catalano@telecomitalia.it","SP#59 Stage 1 completed. ","Stage 1",59,30,null,null,"2013-02-19","2013-02-19"]
[4311,590042,"Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode","PMOC",1,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130111","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#59 Stage 1 completed","Stage 1",59,30,null,null,"2013-02-19","2013-02-19"]
[4314,500028,"LIPA Mobility and SIPTO at the Local Network","LIMONET",1,"Rel-12","S2,C4,C1,R3","2010-10-15","2014-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","CP#63 completed. SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility). Linked to UID_450035 Local IP Access and Selected IP Traffic Offload (LIPA_SIPTO)","Stage 2/3",50,26,null,null,"2010-11-26","2013-02-27"]
[4315,500128,"   TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network","LIMONET-SA3",2,"Rel-12","S2","2010-10-15","2013-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#59 completed. TR 23.859 v100 for Information and Approval","new 23.859",50,26,null,null,"2010-11-26","2013-02-27"]
[4318,530015,"      Stage 3 CN aspects of SIPTO at the Local Network","LIMONET-SIPTO",3,"Rel-12","C4,C1","2011-09-24","2014-03-05",1,"CP-130274","-","Huawei","peter.schmitt@huawei.com","CP#63 completed","Stage 3",53,27,null,null,"2011-08-27","2014-01-29"]
[4321,590020,"   RAN aspects for SIPTO at the Local Network","LIMONET-RAN",2,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","-","Huawei","zheng.zhou@huawei.com","-","UTRA, LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[4325,530016,"      Deleted - Stage 3 CN aspects of LIPA Mobility","LIMONET-LIPA-del2",3,"Rel-12","C1,C4","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","Stage 3",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[4328,510049,"Operator Policies for IP Interface Selection","OPIIS",1,"Rel-12","S2,C1","2011-03-23","2013-12-06",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network)","Stage 2/3",51,26,null,null,"2011-02-21","2013-02-27"]
[4331,600047,"   Stage 3 for Operator Policies for IP Interface Selection","OPIIS-CT",2,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130215","-","LG Electronics","Jaehyun Kim (jaehyun7.kim@lge.com)","CP#62 completed. Specify Inter-APN Routing Policies for selecting an IP interface to route IP flows among a choice of available interfacES in CP-150both 3GPP and non-3GPP accesses","24.302, 24.312",60,31,null,null,"2013-05-28","2013-11-18"]
[4335,590013,"   Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",2,"Rel-12","C1,C4","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS","Stage 3",59,30,null,null,"2013-02-16","2013-11-18"]
[4338,530042,"IMS-based Telepresence","IMS_TELEP",1,"Rel-12","S1,C1,C3,C4,IETF","2010-03-22","2014-12-09",0.93,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified","Stage 1/2/3",53,27,null,null,"2011-07-19","2012-06-08"]
[4339,530142,"   Stage 1 for IMS-based Telepresence","IMS_TELEP",2,"Rel-12","S1","2011-09-22","2012-06-20",1,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","SP#56 completed. 2/4/15: acronym changed to IMS_TELEP",22.228000000000002,53,27,null,null,"2011-07-19","2015-04-02"]
[4342,580003,"      CT1 part of IMS Telepresence (Stage 3)","IMS_TELEP",3,"Rel-12","C1","2012-12-07","2014-12-09",1,"CP-140624","CP-140616","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 TS 24.103v100 for Information. Updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140616. Dec.14: 90->100%. 2/4/15: acronym changed to IMS_TELEP","24.147, 24.166, 24.229, New 24.103",58,30,null,null,"2012-11-19","2015-04-02"]
[4345,641003,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",0.9,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-datachannel); 9/4/21: RFC 8850 added;","draft-ietf-clue-datachannel; RFC 8850",64,33,null,null,"2014-06-06","2021-04-09"]
[4349,610011,"      CT4 part of IMS Telepresence (Stage 2/3)","IMS_TELEP",3,"Rel-12","C4","2013-09-13","2014-12-09",1,"CP-140624","CP-140477","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140477. Mar.15: 0->100%. 2/4/15: acronym changed to IMS_TELEP","23.333, 29.333",61,31,null,null,"2013-08-11","2015-04-02"]
[4352,590037,"   TR on Architecture enhancements to support Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S2","2013-03-07","2014-03-07",1,"SP-140433","-","Nokia Networks","rainer.liebhart@nsn.com ","SP#63 completed. TR 23.768v200 for Approval","New 23.768",59,30,null,null,"2013-02-21","2014-09-07"]
[4355,610035,"   Security for Group Communication System Enablers for LTE (Stage 2)","GCSE_LTE",2,"Rel-12","S3","2013-09-13","2014-06-18",1,"SP-140433","-","Nokia Networks","anja.jerichow@nsn.com","SP#64 completed",33.246000000000002,61,31,null,null,"2013-09-03","2014-09-07"]
[4359,650008,"      CT1 part of Group Communication System Enablers for LTE","GCSE_LTE-CT",3,"Rel-12","C1","2014-09-12","2014-12-09",1,"CP-140559","CP-140614","Nokia Networks","thomas.belling@nsn.com","CP#65 updated WID CP-140452=>CP-140559 (added CT1 part). Exception in CP-140614. Dec.14: 90->100%",24.300999999999998,65,33,null,null,"2014-07-30","2014-12-04"]
[4362,560022,"Machine-Type and other mobile data applications Communications enhancements","MTCe",1,"Rel-12",null,"2009-12-10","2016-05-12",0.98,"SP-130327","-","Intel","puneet.jain@intel.com","-","Stage 1/2/3",56,29,null,null,"2012-04-13","2013-11-28"]
[4363,560021,"   Stage 1 for Support for Interworking with M2M Service Enablement","MTCe-SIMSE",2,"Rel-12","S1","2012-06-18","2013-03-06",1,"SP-120436","-","KPN","toon.norp@tno.nl","SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer)",22.367999999999999,56,29,null,null,"2012-05-14","2013-02-19"]
[4366,560522,"   Security and Privacy aspects for Machine-Type and other mobile data applications Communications enhancements (Stage 2)","MTCe-SA3",2,"Rel-12","S3","2012-06-22","2014-03-07",1,"SP-130327","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#63 completed. TS 33.187v100 for 1-step Approval","New 33.187",56,29,null,null,"2012-06-02","2014-02-27"]
[4369,562122,"      Stage 2 for BB1: Small Data and Device Triggering Enhancements","MTCe-SDDTE",3,"Rel-12","S2","2012-06-26","2013-12-11",1,"SP-120450","-","Intel","puneet.jain@intel.com ","SP#62 completed",23.681999999999999,56,29,null,null,"2012-04-13","2013-11-28"]
[4373,560222,"   Deleted - BB2: Monitoring Enhancements (MONTE)","MTCe-MONTE",2,"Rel-12","S2","2012-06-18","2012-12-12",1,"SP-120438","-","Intel","puneet.jain@intel.com ","SP#58 stopped (at 20% completion)",23.681999999999999,56,29,"SP-58","PCG-30","2012-04-13","2012-12-14"]
[4376,562322,"      Stage 2 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",3,"Rel-12","S2","2012-06-26","2013-12-11",1,"SP-120442","-","Ericsson","peter.hedman@ericsson.com ","SP#62 completed","23.060, 23.401, 23.682",56,29,null,null,"2012-04-13","2013-11-28"]
[4380,620307,"         CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT6",4,"Rel-12","C6","2013-12-09","2014-12-09",1,"CP-130714","CP-140697","Ericsson","mikael.wass@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140697¦June2015: Compl:90%->100","31.101, 31.102, 31.111",62,32,null,null,"2013-11-18","2015-06-15"]
[4383,700005,"      Testing of Support of Power Saving Mode in GERAN","MTCe-UEPCOP_GERAN3new",3,"Rel-12","G3","2015-11-11","2016-05-12",0.1,"GP-151186",null,"Ericsson","sajal.kumar.das@ericsson.com","7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new¦2/3/16: 0%->10",null,70,36,null,null,"2014-08-29","2016-03-02"]
[4386,620143,"      Core part: RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN-Core",3,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","RP-141096","ZTE","sergio.parolari@zte.com.cn","RP#65 completed","25.300, 25.304, 25.413, 36.300, 36.304, 36.413, 36.423",62,32,null,null,"2013-12-07","2014-09-15"]
[4387,600012,"Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE",1,"Rel-12","R1,R2,R4","2013-06-15","2016-12-15",1,"RP-130848","-","Vodafone","eric.bouton@vodafone.com","Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE)","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[4391,560024,"Policy and Charging Control for supporting fixed broadband access networks","P4C",1,"Rel-12","S2,S1,S5,C3,C1,C4","2012-06-20","2014-12-12",1,"SP-120443","-","Huawei","marco.spini@huawei.com","Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work","Stage 1/2/3",56,29,null,null,"2012-04-13","2013-01-08"]
[4392,570031,"   Stage 1 for Policy and Charging Support for Fixed Mobile Convergence","P4C-FMC",2,"Rel-12","S1","2012-09-10","2012-09-12",1,"SP-120542","-","Huawei","amar.deol@huawei.com","SP#57 completed",22.277999999999999,57,29,null,null,"2012-08-06","2013-01-08"]
[4396,610012,"      Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",3,"Rel-12","C3,C1,C4","2013-09-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","-","Stage 3",61,31,null,null,"2013-08-12","2014-04-16"]
[4399,620010,"         CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C4","2013-12-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed",29.273,62,32,null,null,"2013-11-19","2014-04-16"]
[4403,560824,"      TR on Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI)","P4C-TI-SA2TR",3,"Rel-12","S2","2012-06-20","2013-06-19",1,"SP-120444","-","Alcatel-Lucent","konstantin.livanos@alcatel-lucent.com","SP#60 completed","new 23.839",56,29,null,null,"2012-06-04","2013-06-17"]
[4406,560424,"   Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB)","P4C-HeNB",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120278","-","NEC","Stefan.Schmid@neclab.eu","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[4409,560025,"IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI",1,"Rel-12","S2,S1,C1,C3","2011-09-28","2014-12-09",1,"SP-120862","-","Deutsche Telekom","michele.zarri@telekom.com","Linked to Rel-11 IPXS Feature UID_470051 Advanced IP Interconnection of Services. This WI defines a generic framework for interconnecting with any type of IMS based network including IP-PBXs.","Stage 1/2/3",56,29,null,null,"2012-05-11","2012-12-10"]
[4410,560325,"   Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA1",2,"Rel-12","S1","2011-09-28","2012-09-12",1,"SP-120862","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#57 completed. 22.228CR#0171 ",22.228000000000002,56,29,null,null,"2012-05-11","2012-12-10"]
[4413,610007,"   CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",2,"Rel-12","C1,C3","2013-09-06","2014-12-09",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","-","Stage 3",61,31,null,null,"2013-08-10","2014-03-03"]
[4417,560126,"   TR on Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SATR",2,"Rel-12","S2,S1","2012-06-18","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","New 23.865",56,29,null,null,"2012-05-11","2013-11-28"]
[4420,620005,"   CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3)","WLAN_NS-CT",2,"Rel-12","C1","2013-12-06","2014-12-09",1,"CP-130712","CP-140622","Qualcomm","Amer Catovic, amerc@qualcomm.com","CP#65 completion 09/14=>12/14. CP#65 exception CP-140622. Dec.14: 95->100%","24.302, 24.312",62,32,null,null,"2013-11-19","2014-12-04"]
[4423,580056,"   Deleted - Stage 2 for IMS Registration Control","IMS_RegCon-del2",2,"Rel-12","S2","2012-12-13","2013-12-11",1,"SP-120735","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 stopped at 50% completion",23.228000000000002,58,30,"SP-62","PCG-32","2012-11-13","2013-12-10"]
[4427,580059,"Proximity-based Services","ProSe",1,"Rel-12",null,"2012-12-13","2017-06-15",1,"SP-140574","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044","Stage 1/2",58,30,null,null,"2012-11-16","2014-09-15"]
[4430,580359,"   Stage 2 for Proximity-based Services","ProSe-SA2",2,"Rel-12","S2","2012-12-19","2014-06-18",1,"SP-140574","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval","New 23.303",58,30,null,null,"2012-11-16","2014-09-15"]
[4433,640039,"   Charging Aspects of Proximity-based Services","ProSe-CH",2,"Rel-12","S5","2014-06-19","2015-03-13",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 exception in SP-140543. Mar15: 85->100%","Stage 2/3",64,33,null,null,"2014-06-06","2015-03-05"]
[4434,640139,"      Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use","ProSe-CH-SA5TR",3,"Rel-12","S5","2014-06-19","2014-12-12",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100%","New 32.844",64,33,null,null,"2014-06-06","2014-12-12"]
[4437,630106,"      CT1 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140290","CP-140615","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100%","24.301, 23.122, New TSs (24.333, 24.334)",63,32,null,null,"2014-01-29","2014-12-04"]
[4441,630030,"   LTE Device to Device Proximity Services","LTE_D2D_Prox",2,"Rel-12",null,"2014-03-11","2017-06-15",1,"RP-140955","-","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","follow-up of TR 36.843 FS_LTE_D2D_Prox","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4444,670046,"      UE Conformance Test Aspects – LTE Device-to-Device Proximity Services","LTE_D2D_Prox-UEConTest",3,"Rel-12","R5","2015-03-16","2017-06-15",1,"RP-160382",null,"Qualcomm","svora@qti.qualcomm.com","rapporteur e-mail added 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150765 29/09/15: Compl:10%->30% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150765->RP-151280 1/1/16: Compl:30%->45% 1/1/16: WID: RP-1¦ ;",null,67,34,null,null,"2015-04-01","2017-06-19"]
[4447,600040,"   TR on Stage 2 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S2","2013-06-19","2013-12-11",1,"SP-130707","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#62 completed. TR 23.701v100 for Information & Approval","New 23.701",60,31,null,null,"2013-06-06","2013-09-09"]
[4451,620067,"   TR on Security for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S3","2013-12-11","2014-09-17",1,"SP-130707","-","Ericsson","oscar.ohlsson@ericsson.com","SP#65 completed. TR 33.871v200 for Approval","New 33.871",62,32,null,null,"2013-12-05","2014-09-04"]
[4454,870070,"      (IETF) Trickle ICE: Incremental Provisioning of Candidates for the Interactive Connectivity Establishment (ICE) Protocol (draft-ietf-ice-trickle)","IMS_WebRTC-CT",3,"Rel-12","C1-IETF","2019-03-07","2019-03-07",0.9,null,null,null,null,"9/4/21: RFC 8838 added;","RFC 8838",87,44,null,null,"2020-04-23","2021-04-09"]
[4457,641006,"      (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-data-channel)","IMS_WebRTC-data",3,"Rel-12","C1-IETF","2014-03-06","2014-12-09",0.9,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Submitted to IESG for publication. Mar15: In RFC-Editors queue; 9/4/21: RFC 8831 added;","draft-ietf-rtcweb-data-channel; RFC 8831",64,33,null,null,"2014-06-06","2021-04-09"]
[4458,641007,"      (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-stun-consent-freshness)","IMS_WebRTC-stun",3,"Rel-12","C1-IETF","2014-03-06","2014-12-09",1,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Mar15: Publication requested¦7/3/16: 50%->100; 9/4/21: RFC 7675 added;","draft-ietf-rtcweb-stun-consent-freshness; RFC 7675",64,33,null,null,"2014-06-06","2021-04-09"]
[4461,660031,"      Deleted - (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id)","IMS_WebRTC-holmb",3,"Rel-12","C1-IETF","2014-09-12","2014-12-09",1,"CP-140192",null,"christer.holmberg@ericsson.com",null,"7/3/16: 25%->100 since deleted (draft no longer needed). ","draft-holmberg-sipcore-auth-id",66,34,null,null,"2014-12-04","2016-03-07"]
[4465,600048,"   CT3 aspects of Usage Monitoring Control PCC enhancement (Stage 3)","UMONC-CT3",2,"Rel-12","C3","2013-06-14","2013-09-06",1,"CP-130396","-","ZTE","zhou.xiaoyun@zte.com.cn","CP#61 completed. 2/4/15: acronym changed to \"UMONC-CT3\"","29.212, 29.214, 29.215",60,31,null,null,"2013-05-29","2015-04-02"]
[4468,600011,"   Charging for Application Based Charging","ABC-CT5",2,"Rel-12","S5","2013-06-19","2014-06-18",1,"SP-130328","-","Openet Telecom","alan.mcnamee@openet.com","SP#64 completed","32.240, 32.251, 32.296, 32.298, 32.299",60,31,null,null,"2013-05-29","2014-06-10"]
[4471,610138,"   Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-SA2",2,"Rel-12","S2","2013-09-11","2014-03-07",1,"SP-130391","-","ZTE","Tricci So (tso@zteusa.com)","SP#63 completed",23.402000000000001,61,31,null,null,"2013-07-25","2014-02-04"]
[4475,610039,"Optimized Offloading to WLAN in 3GPP-RAT Mobility","WORM",1,"Rel-12","S2,C1","2013-09-12","2014-06-13",1,"SP-130392","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB)","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[4478,610040,"Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN",1,"Rel-12","S2,C3,C1,C4","2013-09-12","2014-09-11",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[4479,610140,"   Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-SA2",2,"Rel-12","S2","2013-09-12","2014-03-07",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","SP#63 completed","23.203, 23.228, 23.402",61,31,null,null,"2013-07-25","2014-02-04"]
[4482,620208,"      CT1 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C1","2013-12-09","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed",24.228999999999999,62,32,null,null,"2013-11-19","2014-07-28"]
[4485,620161,"   Stage 2 for Core Network Overload - User Location Information reporting improvement","CNO_ULI-SA2",2,"Rel-12","S2","2013-12-11","2014-03-07",1,"SP-130717","-","Alcatel-Lucent","nicolas.drevon@alcatel-lucent.com","SP#63 completed","23.060, 23.203, 23.401",62,32,null,null,"2013-11-28","2014-02-04"]
[4489,630204,"      CT4 part of CT aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CT",3,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140093","-","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","CP#65 completed","23.008, 29.060, 29.274",63,32,null,null,"2014-01-29","2014-07-28"]
[4492,560029,"   Stage 1 for Protection against false PWS Warning Notifications","PWS_Sec-SA1",2,"Rel-12","S1","2012-06-15","2012-09-12",1,"SP-120433","-","Vodafone","adrian.neal@vodafone.com","SP#57 completed. Specify reqs to protect against false PWS Warning Notifications (Optional as not all regions/countries require this functionality). WID covers all objectivES in CP-150SA3 PWS_Sec Feature-level WID replacing the original Stage 1 UID_510154",22.268000000000001,56,29,null,null,"2012-06-07","2012-08-07"]
[4495,510154,"   Deleted - Stage 1 for Security aspects of Public Warning System","PWS_Sec-del2",2,"Rel-12","S1","2011-03-23","2012-06-20",1,"SP-120434","-","ST-Ericsson","john.mattsson@ericsson.com","Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. ",22.268000000000001,51,26,"SP-56","PCG-29","2012-06-02","2012-06-26"]
[4499,520031,"Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2)","Web_GBA",1,"Rel-12","S3","2011-06-08","2013-06-20",1,"SP-120890","-","Nokia","Silke.Holtmanns@nokia.com","SP#60 completed","33.220, 33.222, New 33.823",52,27,null,null,"2011-05-17","2013-07-01"]
[4502,611003,"   (IETF) SA3 part of Extended IMS media plane security features (RFC 7345)","eMEDIASECSA3IETF",2,"Rel-12","S3-IETF","2012-06-20","2014-09-12",1,"SP-120447","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","SP#65 completed","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",61,31,null,null,"2013-09-23","2014-09-02"]
[4503,580005,"   CT aspects of Extended IMS media plane security features (Stage 2/3)","eMEDIASEC-CT",2,"Rel-12","C4,C1,C3,IETF","2012-12-13","2014-12-09",0.95,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","-","Stage 2/3",58,30,null,null,"2012-11-14","2013-11-19"]
[4506,621001,"      (IETF) CT4 part of Extended IMS media plane security features (RFC 7345)","eMEDIASEC-CT",3,"Rel-12","C4-IETF","2012-12-18","2014-09-11",1,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",62,32,null,null,"2013-11-27","2015-04-02"]
[4509,621002,"      (IETF) CT1 part of Extended IMS media plane security features (RFC 7345)","eMEDIASEC-CT",3,"Rel-12","C1-IETF","2014-03-06","2014-09-11",1,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",62,32,null,null,"2013-11-27","2015-04-02"]
[4513,580164,"   SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3)","TURAN-SA3",2,"Rel-12","S3","2012-12-13","2014-06-18",1,"SP-130245","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#64 completed","33.203, 33.402",58,30,null,null,"2012-11-12","2014-06-09"]
[4516,470030,"Codec for Enhanced Voice Services","EVS_codec",1,"Rel-12","S4,S1,C4,C1,C3","2010-03-25","2016-03-15",1,"SP-140151","-","Huawei","lei.miao@huawei.com","Triggered by UID_370045 Study on enhanced voice service requirements for EPS (TR 22.813)","-",47,24,null,null,"2010-03-10","2014-02-27"]
[4519,470132,"   TR on Performance characterization of Codec for Enhanced Voice Services","EVS_codec-SA4TR",2,"Rel-12","S4","2010-03-25","2014-12-12",1,"SP-140151","SP-140467","Huawei","lei.miao@huawei.com","SP#65 completion 09/14=>12/14. Ongoing TR 26.952 EVS Codec Performance Characterization. Exception in SP-140467","New 26.952",47,24,null,null,"2010-03-10","2015-06-26"]
[4523,650305,"      CT3 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C3","2014-09-16","2014-12-09",1,"CP-140800","CP-140560","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800","29.163, 29.292",65,33,null,null,"2014-07-29","2014-12-09"]
[4526,560140,"   SA4 part of Coordination of Video Orientation","CVO-SA4",2,"Rel-12","S4","2012-06-07","2013-03-06",1,"SP-120228","-","Ericsson","frederic.gabin@ericsson.com","SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering","26.114, 26.141, 26.234, 26.346",56,29,null,null,"2012-06-07","2013-02-16"]
[4527,600006,"   CT aspects of Coordination of Video Orientation","CVO-CT",2,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","Complete CVO support (both, basic 2 bit orientation and additional option for extra 6 bit granularity) within CN protocols/procedures for IMS nodes, e.g. IMS ALG/AGW,IBCF/TrGW,MRFC/MRFP & add support of CVO-related SDP attributes to be negotiated by UE","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[4530,600306,"      CT3 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162, 29.163",60,31,null,null,"2013-05-28","2013-11-18"]
[4533,570233,"   High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI, IMS Messaging and Presence","HEVC-SA4",2,"Rel-12","S4","2012-09-17","2014-06-18",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed","26.114, 26.140, 26.141, 26.234, 26.244, 26.247, 26.346",57,29,null,null,"2012-08-30","2014-04-16"]
[4537,580166,"   TR on IMS-based Streaming and Download Delivery Enhancements","IMS_SDE-SA4TR",2,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","SP#63 completed. Identify use cases and requirements based on Rel-10/11 PSS and MBMS functionality to be addressed for IMS-based streaming and download enhancements","new 26.827",58,30,null,null,"2012-11-12","2014-01-29"]
[4540,580167,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects","ART_LTE-NBWB",2,"Rel-12","S4","2012-12-12","2013-12-11",1,"SP-120771","-","Sony Mobile Communications","Peter.Isberg@sony.com","SP#62 completed","26.131, 26.132",58,30,null,null,"2012-11-12","2013-11-18"]
[4544,590343,"   TR on Enhanced MBMS Operation","MI-EMOTR",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.848v100 for Information. Dec.14: 85->100. ","New 26.848",59,30,null,null,"2013-02-20","2015-03-05"]
[4547,590243,"   MBMS operation on Demand","MI-MooD",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130026","SP-140471","Qualcomm","Charles Lo (clo@qti.qualcomm.com) ","SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 75->100",26.346,59,30,null,null,"2013-02-20","2015-03-05"]
[4550,600007,"   CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",2,"Rel-12","C3,C1,C4","2013-06-21","2015-09-14",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","Stage 2/3. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","Stage 2/3",60,31,null,null,"2013-02-20","2015-05-05"]
[4551,600107,"      CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C3","2013-06-21","2015-09-14",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","Dec.14: CD: 09/14->09/15. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","29.162, 29.163, 29.213, 29.214",60,31,null,null,"2013-05-29","2015-05-05"]
[4554,620066,"Video Coding Enhancements in IMS Messaging and Presence","VCEIMP",1,"Rel-12","S4","2013-12-11","2014-03-07",1,"SP-130579","-","Ericsson","frederic.gabin@ericsson.com","SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141",26.140999999999998,62,32,null,null,"2013-11-29","2014-01-29"]
[{"$f":"A4557+1","v":4557},560131,"   Rel-12 Self-Organizing Networks (SON) - OAM aspects","OAM12-SON",2,"Rel-12","S5","2011-09-21","2013-12-11",1,"-","-","-","-","OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI","-",56,29,null,null,"2012-04-18","2012-11-19"]
[4561,560335,"      3GPP Fault Management Solution Profile for NGMN NGCOR","OAM-FMSP",3,"Rel-12","S5","2012-06-20","2013-06-19",1,"SP-120778","-","Ericsson","thomas.tovinger@ericsson.com","SP#60 completed. TS 28.390v200 for Approval","new 28.390",56,29,null,null,"2012-05-23","2013-06-13"]
[4564,530250,"      NIM part Network Management for 3GPP Interworking WLAN","OAM-IWLAN-SA5NM",3,"Rel-12","S5","2011-09-21","2013-12-11",1,"SP-140542","-","China Mobile","Chengang@chinamobile.com, lijian@chinamobile.com","SP#65 discontinue I-WLAN specs: Move parts (e.g. IOCs) applicable for EPC and non-3GPP access interworking NRMs from 28.601/2/6 to 28.611/2/6. Withdraw 28.601/2/6 (CN and non-3GPP access i/w NRMs). SP#62 completed. TSs 28.601/2/6/11/12/16 for Approval","32.632, 32.636, 32.752, 32.756, new (28.611, 28.612, 28.616, withdrawn 28.601, 28.602, 28.606)",53,27,null,null,"2011-08-27","2014-09-10"]
[4568,580054,"   Deleted - Rel-12 Performance Management","OAM12-PM",2,"Rel-12","S5","2013-06-21","2014-09-16",1,"-","-","-","-","OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI","-",58,30,"SP-69",null,"2012-11-15","2014-08-19"]
[4571,620257,"      OAM aspects of Network Sharing - Impacts on existing specifications","OAM-SHARE-SA5imp",3,"Rel-12","S5","2013-12-12","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. Dec.14: 60->100","28.401,28.621/2/3,28.651/2/3,28.654/5/6,28.657/8/9,28.701/2/3,28.731/2/3,28.734/5/6,32.101/2,32.111-1/2/3/6,32.121/2/6,32.155,32.171/2/6,32.300/1/2/6,32.311/2/6,32.321/2/6,32.331/2/6,32.341/2/6,32.351/352/6,32.361/2/6,32.381/2/6,32.405/6/7/8/9/10/11/12/41",62,32,null,null,"2013-11-28","2014-12-04"]
[4574,610041,"   Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3)","CHIPS",2,"Rel-12","S5","2013-09-12","2014-06-18",1,"SP-130642","-","Ericsson","david.shrader@ericsson.com","SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS","32.251, 32.298, 32.299",61,31,null,null,"2013-09-04","2015-12-07"]
[4575,610042,"   Charging using an Alternative Roaming Provider (Stage 2/3)","CHARP",2,"Rel-12","S5","2013-09-12","2014-06-18",1,"SP-130428","-","Ericsson","david.shrader@ericsson.com","SP#64 completed. TS 32.276v200 for Approval, 32.293v100 for 1-step Approval","32.240, 32.299, New TSs [32.276 (Voice Call Service Charging), 32.293 (Proxy Function)]",61,31,null,null,"2013-09-04","2014-06-10"]
[4578,530118,"   CT1 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C1","2011-09-22","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#64 completed. 2/4/15: acronym changed to EMC_PC","24.229, tied to completion of IETF dependencies: 24.604, 24.605, 24.610, 24.611, 24.629",53,27,null,null,"2011-08-27","2015-04-02"]
[4582,570008,"Interworking between a PLMN with WLAN to access the EPC and a PDN (Stage 3)","SAES_WLAN_EPC_intwk",1,"Rel-12","C3","2012-09-10","2013-09-06",1,"CP-130395","-","Huawei","Christian.Herrero@huawei.com","CP#61 completed. Linked to Rel-8 Feature SAES in CP-150System Architecture Evolution specification - Evolved Packet System (non RAN aspects) UID_320005",29.061,57,29,null,null,"2012-08-13","2013-08-12"]
[4585,580011,"   CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD-CT4",2,"Rel-12","C4","2012-12-10","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","CP#64 completed","23.007, 29.168",58,30,null,null,"2012-11-19","2014-05-25"]
[4588,580012,"Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3)","bSRVCC",1,"Rel-12","C1,C3,R5","2012-12-07","2014-03-06",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12","GERAN, UTRA, LTE",58,30,null,null,"2012-11-19","2013-06-10"]
[4592,580013,"IMS Stage 3 IETF Protocol Alignment - phase 6","IMSProtoc6",1,"Rel-12","C1,C3,IETF","2012-12-07","2014-12-09",0.99,"CP-120905","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","-","Stage 3",58,30,null,null,"2012-11-19","2012-12-06"]
[4595,651002,"   Deleted - (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-jesske-sipcore-sip-tree-cap-indicators)","IMSProtoc6",2,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 9/4/21: 25%->100","draft-allen-sipcore-sip-tree-cap-indicators",65,33,null,null,"2014-09-02","2021-04-09"]
[4598,611001,"   (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C3-IETF","2013-09-06","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",61,31,null,null,"2013-08-23","2017-03-21"]
[4599,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[4602,580019,"   SAE for support for non-3GPP accesses - Phase 3","SAES3-non3GPP",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[4606,580023,"Diameter based interface between SGSN and SMS central functions (Stage 2/3)","Dia_SGSN_SMS",1,"Rel-12","C4,C1","2012-12-10","2013-12-06",1,"CP-130437","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#62 completed","Stage 2/3",58,30,null,null,"2012-11-20","2013-11-18"]
[4609,580024,"Diameter based interface between SGSN-GMLC (Stage 3)","Dia_SGSN_GMLC",1,"Rel-12","C4","2012-12-10","2013-12-06",1,"CP-130598","-","Cisco","Nirav Salot (nsalot@cisco.com)","CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol)","29.002, 29.172, 29.173, 29.230, 29.272",58,30,null,null,"2012-11-20","2013-11-18"]
[4612,590112,"   CT4 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C4","2013-03-01","2013-12-06",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed","23.007, 23.008, 29.274",59,30,null,null,"2013-03-07","2013-11-18"]
[4616,590214,"   Stage 3 for Dual Radio VCC enhancements","eDRVCC",2,"Rel-12","C1,C3","2013-03-01","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed","Stage 3",59,30,null,null,"2013-02-19","2013-11-18"]
[4619,600009,"CT aspects of Signalling of Image Size (Stage 2/3)","SIS_CT",1,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[4622,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162, 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[4623,600010,"IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S)","ICS_IWE",1,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130352","-","Orange","marianne.mohali@orange.com ","CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS)",29.292000000000002,60,31,null,null,"2013-05-28","2013-11-19"]
[4626,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[4630,650002,"      CT3 part of Common for HSS & PCRF solutions","PCSCF_RES",3,"Rel-12","C3","2013-05-03","2014-12-09",1,"CP-140490","CP-140687","Huawei","susan.shishufeng@huawei.com","CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687","29.061, 29.165",65,33,null,null,"2013-08-10","2014-06-03"]
[4632,610210,"      CT4 part of HSS based solution","PCSCF_RES",3,"Rel-12","C4","2013-09-06","2014-12-09",1,"CP-140490","CP-140481","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140481. Dec.14: 90->100","29.002, 29.228, 29.229, 29.272, 29.305",61,31,null,null,"2013-08-10","2014-12-04"]
[4635,640015,"      CT3 part of PCRF based solution","PCSCF_RES",3,"Rel-12","C3","2013-05-03","2014-12-09",1,"CP-140490","CP-140687","Huawei","susan.shishufeng@huawei.com","CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687","29.212, 29.213, 29.214, 29.215",64,33,null,null,"2013-08-10","2014-06-03"]
[4639,610208,"   CT3 part of Updating IMS to conform to RFC 6665","UP6665",2,"Rel-12","C3","2013-09-09","2013-12-06",1,"CP-130717","-","BlackBerry","Andrew Allen (aallen@blackberry.com)","CP#62 completed","29.163, 29.165",61,31,null,null,"2013-07-25","2013-11-19"]
[4642,670035,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-roach-sipcore-6665-clarifications)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100","draft-roach-sipcore-6665-clarification",67,34,null,null,"2015-03-13","2015-09-14"]
[4643,620004,"IMS Operator Determined Call Barring enhancements (Stage 3)","eIODB",1,"Rel-12","C1,C3","2013-12-06","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision","Stage 3",62,32,null,null,"2013-11-18","2013-11-18"]
[4646,620006,"Signalling Improvements for Network Efficiency (Stage 3)","SINE",1,"Rel-12","C1","2013-12-06","2014-12-09",1,"CP-130713","CP-140617","Huawei","Lin Shu (shulin@huawei.com)","CP#65 completion 09/14=>12/14. Exception in CP-140617.Dec.14: 80->85%. 3/3/15: 100% cpltd.","24.008, 24.301",62,32,null,null,"2013-11-18","2015-03-03"]
[4649,630202,"   CT3 part of ICE impacts on IMS H.248 profiles (Stage 2)","ICEH248",2,"Rel-12","C3","2014-03-05","2014-06-13",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#64 completed","29.162, 29.163, 29.292",63,32,null,null,"2014-01-29","2014-06-03"]
[4653,630008,"Support of ALT-C attribute","ALTC",1,"Rel-12","C4,C1,C3","2014-03-10","2014-12-09",1,"CP-140191","-","Orange","lionel.morand@orange.com","SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network.","-",63,32,null,null,"2014-01-29","2014-03-03"]
[4656,630308,"   CT3 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C3","2014-03-10","2014-12-09",1,"CP-140191","CP-140563","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140563. Dec.14: 0->100",29.161999999999999,63,32,null,null,"2014-01-29","2014-12-04"]
[4659,641010,"   (IETF) Diameter Overload Control Mechanisms (draft-ietf-dime-ovli)","DOCME",2,"Rel-12","C4-IETF","2014-06-13","2014-12-09",1,"CP-140273","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Mar15: In WGLC¦7/3/16: 50%->100; 9/4/21: RFC 7683 added;","draft-ietf-dime-ovli; RFC 7683",64,33,null,null,"2014-05-25","2021-04-09"]
[4663,640007,"Indication of NNI Routeing scenarios in SIP requests","NNI_RS",1,"Rel-12","C1,C3,IETF","2014-06-13","2014-12-09",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025","-",64,33,null,null,"2014-04-07","2014-04-07"]
[4666,640207,"   CT3 part of Indication of NNI Routeing scenarios in SIP requests","NNI_RS",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","CP#65 completed","29.079, 29.165",64,33,null,null,"2014-04-07","2014-07-31"]
[4667,640008,"Unstructured Supplementary Service Data (USSD) method selection (Stage 3)","USSD_MS",1,"Rel-12","C1","2014-06-11","2014-06-13",1,"CP-140450","-","Ericsson","ivo.sedlacek@ericsson.com","CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain)","24.173, 24.390, New 24.391",64,33,null,null,"2014-04-07","2014-06-12"]
[4670,640111,"   CT3 part of Overload Control for PCC based Diameter applications","DOCME-PCC",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140405","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#65 completed","29.212, 29.213, 29.214",64,33,null,null,"2014-06-10","2014-07-31"]
[4673,530002,"Introduction of ER-GSM band for GSM-R","RT_ERGSM",1,"Rel-12","G1,C1,G3new","2011-09-16","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios.","GERAN",51,27,null,null,"2011-09-06","2014-03-07"]
[4677,570002,"Downlink Multi Carrier GERAN","DMCG",1,"Rel-12","G2,G1,C1,G3new","2012-09-10","2015-03-13",0.91,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2","GERAN",55,29,null,null,"2012-09-03","2014-03-01"]
[4680,570302,"   Test part: Downlink Multi Carrier GERAN","DMCG-MStest",2,"Rel-12","G3new","2012-09-10","2015-03-13",0.8,"GP-120930","-","ST-Ericsson","hakan.e.grunditz@stericsson.com","GP#63 completion 08/14=>11/14. Dec.14: 35->80%, CD:11/14->03/15","51.010-1, 51.010-2",55,29,null,null,"2012-09-03","2014-12-03"]
[4684,590233,"   MSRD for VAMOS - MS Conformance Test","MSRD_VAMOS-Test",2,"Rel-12","G3new","2013-03-06","2014-11-21",1,"GP-130849","GP-140579","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 85->100","51.010-1, 51.010-2",57,30,null,null,"2013-03-04","2014-12-03"]
[4687,620214,"   GERAN2 part of New Training Sequence Codes (TSC) for GERAN","NewToN",2,"Rel-12","G2","2013-11-22","2014-11-19",0.8,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. ","44.018, 44.060",60,32,null,null,"2013-11-22","2014-05-30"]
[4690,550116,"   Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS","HSPA_LTE_measRP_MIMO-Perf",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-120368","RP-131507","Vodafone","luis.anaya@vodafone.com","RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI)","new 37.977",55,28,null,null,"2012-02-23","2013-08-30"]
[4691,570021,"Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3)","EHNB_enh3",1,"Rel-12","R3,R2","2012-09-12","2013-12-06",1,"RP-130741","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Triggered by FS_EHNB_enh (TR 37.803)","UTRA, LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[4694,590119,"   Core part: Support for BeiDou Navigation Satellite System (BDS) for UTRA","LCS_BDS-UTRA-Core",2,"Rel-12","R2,R3","2013-06-02","2014-03-06",1,"RP-130416","RP-131500","ZTE","Huang He (huang.he4@zte.com.cn)","RP#62 completed","25.305, 25.306, 25.331, 25.453, 25.413, 25.423, 25.433",59,30,null,null,"2013-02-26","2013-11-29"]
[4697,590419,"   Perf. part: Support for BeiDou Navigation Satellite System (BDS) for LTE","LCS_BDS-LTE-Perf",2,"Rel-12","R4","2013-03-07","2014-06-13",1,"RP-130416","RP-140713","ZTE","Ling Soonleh (soonleh.ling@zte.com.cn)","RP#64 completed",36.170999999999999,59,30,null,null,"2013-02-26","2014-06-12"]
[4701,620211,"   GERAN1 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",2,"Rel-12","G1","2013-11-22","2014-08-29",1,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#63 completed","43.059, 45.005",60,32,null,null,"2013-11-22","2014-08-29"]
[4704,600019,"Deleted - New Base Station specification structure","BSspec_struc",1,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-130851","-","Ericsson","johan.skold@ericsson.com","Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc)","UTRA, LTE, MSR",60,31,"RP-62","PCG-32","2013-06-17","2013-06-17"]
[4708,600121,"   Core part: L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-Core",2,"Rel-12","R4,R2,R3","2014-02-13","2014-06-13",1,"RP-140092","RP-140633","Orange","olfa.benhaddada@orange.com","RP#64 completed. RP#65 forgotten TR 37.814 v100 for 1-step Approval","25.101, 25.104, 25.113, 25.133, 25.307, 25.327, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, 37.104, 37.113, new 37.814",60,31,null,null,"2013-06-17","2014-09-15"]
[4711,600027,"LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON",1,"Rel-12","R3,S2,C4,G2","2013-06-18","2014-06-13",1,"RP-130831","-","China Telecom","Jinlian_wu@189.cn","Triggered by Rel-12 TR 37.813 (FS_LTE_HRPD_SON). SA2 should verify the architecture solution in TR 37.813 for inter-RAT load balancing between LTE-HRPD. CT4 should specify the RIM extension to support the feature.","UTRA, LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[4714,610003,"   CT aspects for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON (Stage 3)","LTE_HRPD_SON-CT",2,"Rel-12","C4","2013-09-04","2013-09-06",1,"CP-130434","-","Huawei","Xiaoyan SHI (sean.shixiaoyan@huawei.com","CP#61 WID approved & Completed","29.274, 29.276, 29.280",61,31,null,null,"2013-08-11","2013-08-13"]
[4715,610015,"   GERAN aspects for LTE-HRPD inter-RAT SON, RAN Information Management (RIM) - Stage 3","LTE_HRPD_SON-RIM",2,"Rel-12","G2","2013-08-26","2013-08-30",1,"GP-130817","-","Alcatel-Lucent","marguerite.woch@alcatel-lucent.com","GP#59 WID approved & Completed",48.018000000000001,59,31,null,null,"2013-08-11","2013-10-01"]
[4718,620242,"   Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-132061","RP-150596","Ericsson","christopher.callender@ericsson.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787 1st Apr 15: Compl:5%->40% 1st Apr 15: Stat Rep: RP-141787->RP-150063 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150063->RP-150596","25.133, 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[4721,620148,"   Core part: WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-Core",2,"Rel-12","R2","2013-12-06","2014-09-12",1,"RP-140981","RP-141310","Intel","sasha.sirotkin@intel.com","SP#65 completed","25.304, 25.306, 25.331, 36.304, 36.306, 36.331",62,32,null,null,"2013-12-09","2014-09-09"]
[4725,650001,"      CT4 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3)","UTRA_LTE_WLAN_interw-CT",3,"Rel-12","C4","2014-09-12","2014-12-09",1,"CP-140623","CP-140482","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 revised WID CP-140287=>CP-140623 (added CT4 part). Exception in CP-140482. Dec.14: 50->100","23.008, 29.002, 29.272, 29.274, 29.305",65,33,null,null,"2014-07-28","2014-12-04"]
[4728,530025,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7",2,"Rel-12","R4","2011-09-19","2014-09-12",1,"RP-141487","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band CA 2DL","LTE",53,27,null,null,"2011-09-15","2013-12-07"]
[4732,530129,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25-Core",3,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","RP-130563","Sprint","George.Cummings@sprint.com","RP#60 completed. TR 36.841 for 1-step Approval","36.101, 36.104, 36.133, new 36.833-2-25",53,27,null,null,"2011-09-15","2013-06-07"]
[4735,550110,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL-Core",3,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","RP-130098","SK Telecom","Seungpyo Hong","RP#59 stopped (covered by new WI LTE_CA_2UL-A4)","36.101, 36.104, 36.133, 36.307, new generic 36.851",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[4738,550011,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","-","SK Telecom","haesung.park@sk.com","Intra-band NC","LTE",55,28,null,null,"2012-02-23","2012-02-23"]
[4739,550111,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3-Core",3,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","RP-131573","SK Telecom","haesung.park@sk.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-2-03",55,28,null,null,"2012-02-23","2013-12-02"]
[4742,560115,"      Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1-Core",3,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-120826","RP-130549","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#60 stopped at 10% completion (rationale in RP-130670)","36.101, 36.104, 36.133, 36.141, 36.307, new 36.835",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[4746,560216,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4-Perf",3,"Rel-12","R4","2012-06-22","2013-09-06",1,"RP-131135","RP-131040","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed. Updated WID RP-130842=>RP-131135","36.101, 36.104, 36.133, 36.141, 36.307",56,29,null,null,"2012-06-13","2013-08-28"]
[{"$f":"A4749+1","v":4749},560217,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4-Perf",3,"Rel-12","R4","2012-06-22","2013-09-06",1,"RP-130175","RP-131376","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed","36.101, 36.104, 36.133, 36.141, 36.307",56,29,null,null,"2012-06-13","2013-08-28"]
[4752,570212,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29-Perf",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","RP-130536","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[4756,570014,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130198","-","NTT DOCOMO","Kei ANDO","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[4759,570015,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39","LTE_CA_B38_B39",2,"Rel-12","R4","2012-09-11","2012-12-07",1,"RP-121178","-","China Mobile","Pan Qun (panqun@chinamobile.com)","Inter-band 1 UL","LTE",57,29,"RP-58","PCG-30","2012-09-03","2012-12-11"]
[4762,570016,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3",2,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","-","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","Intra-band NC","LTE",57,29,null,null,"2012-09-03","2013-08-29"]
[4763,570116,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3-Core",3,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","RP-131029","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs)","36.101, 36.104, 36.133, new 36.833-1-03",57,29,null,null,"2012-09-03","2013-09-04"]
[4766,570118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Core",3,"Rel-12","R4","2012-02-02","2013-06-14",1,"RP-130181","RP-130515","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.101, 36.104, new generic 36.851",57,29,null,null,"2012-09-03","2013-06-04"]
[4770,570226,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28","LTE_CA_B3_B28-Perf",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130189","RP-130530","eAccess","FukumotoShiro@eaccess.net","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-05"]
[4773,580232,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26-Perf",3,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","RP-131006","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.141, 36.307",58,30,null,null,"2012-12-10","2013-08-28"]
[4776,580233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41-Perf",3,"Rel-12","R4","2012-12-14","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#63 completed","36.133, 36.141",58,30,null,null,"2012-12-10","2014-03-05"]
[4780,580035,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","-","Ericsson","christian.bergljung@ericsson.com","Intra-band NC","LTE",58,30,null,null,"2012-12-10","2013-02-28"]
[4783,580036,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27",2,"Rel-12","R4","2012-12-10","2014-06-13",1,"RP-131679","-","NII Holdings","bill.shvodian@nii.com","Intra-band contig. CA 2DL/1UL","LTE",58,30,null,null,"2012-12-10","2013-12-19"]
[4786,590022,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13",2,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band 1 UL","LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[4787,590122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130523","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-02-26"]
[4790,590124,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130533","NTT DOCOMO","Kei ANDO","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-06-08"]
[4794,590225,"      Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Perf",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131550","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.141, 36.307",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[4797,590229,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141941","RP-141732","Huawei","Liu Ye (leo.liuye@huawei.com)","¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732",36.133000000000003,59,30,null,null,"2013-02-26","2015-01-12"]
[4800,590228,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-130327","RP-141732","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[4804,590031,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141160","-","Nokia","petri.j.vasenkari@nokia.com","Inter-band CA 2UL. RP#65 updated WID RP-140476=>RP-141160.","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[4807,590026,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141195","-","NTT DOCOMO","kei.andou.ye@nttdocomo.com","Inter-band CA 2UL. RP#65 updated WID RP-131146=>RP-141195. Changed Rapp Renesas=>Broadcom=>NTT DOCOMO","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[4808,590126,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[4811,590127,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39-Core",3,"Rel-12","R4","2013-03-04","2014-03-06",1,"RP-131171","RP-140428","China Mobile","Li Nan (linan@chinamobile.com)","RP#63 completed","36.101, 36.104, 36.133, New 36.833-1-39 [instead of 36.845]",59,30,null,null,"2013-02-26","2014-03-05"]
[4814,600122,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL","LTE_CA_NC_2UL-Core",3,"Rel-12","R4","2013-06-18","2014-12-15",1,"RP-141962","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141962¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, 36.306, 36.331, New 36.833-4",60,31,null,null,"2013-06-17","2015-01-12"]
[4818,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[4821,600025,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band C CA","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[4824,600026,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23",2,"Rel-12","R4","2013-06-18","2014-06-13",1,"RP-131700","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2013-12-19"]
[4828,600128,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","RP-131705","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",60,31,null,null,"2013-06-05","2013-12-02"]
[4831,600129,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset-Core",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","RP-131003","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.101, new generic 36.851",60,31,null,null,"2013-06-05","2013-08-28"]
[4832,600229,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset-Perf",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","RP-131004","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed",36.307000000000002,60,31,null,null,"2013-06-05","2013-08-28"]
[4835,600230,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5-Perf",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130675","RP-131010","AT&T","marc.grant@att.com","RP#61 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-05","2013-08-30"]
[4838,600231,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30-Perf",3,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[4842,600033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30",2,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[4845,600034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30","LTE_CA_B4_B5_B30",2,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141213","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[4849,600135,"      Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131133","RP-131598","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131653 discussion","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4852,600136,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131699=>RP- 141215","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[4855,600137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed. Updated RP-131684=>RP-141434","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-21"]
[4856,600237,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[4859,600238,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141435","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[4862,600239,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13","LTE_CA_B4_B4_B13-Perf",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141433","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[4866,610018,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4869,610019,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11","LTE_CA_B1_B11",2,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131354","-","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","Inter-band CA 2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4872,610020,"   LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11",2,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","-","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","Inter-band CA 2DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[4875,610021,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7",2,"Rel-12","R4","2013-09-09","2013-12-02",1,"RP-131365","-","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4878,610022,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL",2,"Rel-12","R4","2013-09-09","2015-03-13",1,"RP-140100","-","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","Intra-band contig. CA 3DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[4879,610122,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL-Core",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-140100","RP-141084","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101, 36.104, 36.133, 36.307, New 36.833-5-41",61,31,null,null,"2013-09-07","2014-09-08"]
[4882,610123,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2-Core",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","RP-140569","Ericsson","imadur.rahman@ericsson.com","RP#64 completed. TR 36.833-2-02v100 for 1-step Approval","36.101, 36.104, 36.133, New 36.833-2-02",61,31,null,null,"2013-09-07","2014-06-12"]
[4885,620118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.101, 36.104, 36.133, new generic 36.851",62,32,null,null,"2013-12-07","2014-09-08"]
[4889,620219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-141803","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.133, 36.141",62,32,null,null,"2013-12-07","2015-01-12"]
[4892,620220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set","LTE_CA_B2_B4_BWset-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-131656","RP-140428","T-Mobile USA","nelson.ueng@t-mobile.com","RP#63 completed",36.307000000000002,62,32,null,null,"2013-12-07","2014-03-04"]
[4896,620022,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[4899,620072,"   LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","Inter-band 2DL","LTE",62,32,null,null,"2013-12-09","2014-03-05"]
[4902,620024,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","-","KT","Ilwhan Kim (ilwhan.kim@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-22"]
[4903,620124,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","RP-141084","KT","Ilwhan Kim (ilwhan.kim@kt.com)","RP#65 completed. Updated WID RP-131753=>RP-141654","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[4906,620125,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed. Updated WID RP-140209=>RP-141462","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[4910,620226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[4913,620227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12","LTE_CA_B2_B4_B12-Perf",3,"Rel-12","R4","2013-12-09","2014-12-11",1,"RP-140189","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completion 09/14=>12/14","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-12"]
[4916,620228,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-140190","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[4920,620030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4923,620031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20","LTE_CA_B3_B7_B20",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141224","-","Vodafone","luis.anaya@vodafone.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-21"]
[4926,620033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[4927,620133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4930,620134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[4934,620235,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[4937,620237,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","RP-140569","CATT","Yuexia Song (songyuexia@catt.cn)","RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728","36.141, 36.307",62,32,null,null,"2013-12-07","2014-06-12"]
[4940,620236,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","RP-140569","Orange","Olfa BEN HADDADA","RP#64 completed",36.307000000000002,62,32,null,null,"2013-12-07","2014-06-20"]
[4944,620039,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[4947,620050,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5",2,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","-","SK Telecom","haesung.park@sk.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-09","2014-09-21"]
[4948,620150,"      Core part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Core",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[4951,620151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-141017=>RP-141222","36.101, 36.104, 36.133, new generic 36.851 (2 Band CA with 1UL), 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[4954,620152,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20","LTE_CA_B1_B7_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141223","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-140243=>RP-141223","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[4958,620253,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732","36.101, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-09","2015-01-12"]
[4961,630023,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20_BWset",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140447","-","NSN","iwajlo.angelow@nsn.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[4964,630124,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140448","RP-140569","NSN","iwajlo.angelow@nsn.com","RP#64 completed","36.101, 36.851",63,32,null,null,"2014-03-10","2014-06-20"]
[4968,630126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-03-10"]
[4971,630127,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-21"]
[4972,630227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[4975,630228,"      Perf. part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7","LTE_CA_B3_B3_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141126","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated RP-140390=>RP-141126","36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-08"]
[4978,630229,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL-Perf",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","RP-140569","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#64 completed. Updated WID RP-140453=>RP-140948","36.141, 36.307",63,32,null,null,"2014-03-10","2014-06-20"]
[4982,630036,"   LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","-","Huawei","leo.liuye@huawei.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[4985,630037,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141709","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-22"]
[4988,630038,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141236","-","T-Mobile USA","nelson.ueng@T-Mobile.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[4992,630145,"      Core part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140452","RP-141084","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#65 completed","36.101, 36.307, 36.833-2-25",63,32,null,null,"2014-03-10","2014-09-08"]
[4995,640120,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4_BWset2-Core",3,"Rel-12","R4","2014-06-15","2014-09-12",1,"RP-140599","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","Dec 14: Prev CD:Fri 12/09/14¦Prev %:100%, title changed. Mar 15: Acronym changed to LTE_CA_B2_B4_BWset2-Core_","36.101, 36.851",64,33,null,null,"2014-06-16","2015-03-10"]
[4996,640021,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_BWset",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","-","AT&T","marc.grant@att.com","2DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4999,640027,"   E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","-","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","LTE","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5002,640128,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2014-09-08"]
[5006,640229,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141, 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5009,640230,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","RP-150013","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","CD:Thu 11/12/14->Tue 15/03/16¦Compl:50%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: CD:Tue 15/03/16->Sun 15/03/15 1st Apr 15: Stat Rep: RP-141732->RP-150013","36.141, 36.307",64,33,null,null,"2014-06-16","2015-04-01"]
[5013,640035,"   Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141127","-","TeliaSonera","Ralf.Schuh@TeliaSonera.com","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5016,650010,"   LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28",2,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 2DL","LTE",65,33,null,null,"2014-03-10","2014-09-10"]
[5019,630034,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","-","Intel","xinrong.wang@intel.com ","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5020,630134,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.851 (2 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5023,630139,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5026,630140,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5030,630241,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.133, 36.141, 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5033,630242,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.133, 36.141, 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5037,630044,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141610","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5040,640023,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","-","Rogers Wireless","pavlo.nebesny@rci.rogers.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5043,640024,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","-","Rogers Wireless","pavlo.nebesny@rci.rogers.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5044,640124,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, 36.307, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5047,640126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41-Core",3,"Rel-12","R4","2014-06-16","2014-12-15",1,"RP-142301","RP-141732","China Mobile","PAN Qun (panqun@chinamobile.com)","¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5050,640133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5054,640234,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5057,650246,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12",36.140999999999998,65,33,null,null,"2014-06-16","2015-01-12"]
[5061,650050,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29",2,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","-","AT&T","marc.grant@att.com","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[5064,650052,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29",2,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","-","Huawei","SHAN Huiping (shanhuiping@huawei.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[5067,610013,"UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation","LTE_CA_Rel12-UEConTest",1,"Rel-12","R5","2013-09-15","2015-03-13",1,"RP-150077","RP-150076","Microsoft","jussi.kuusisto@microsoft.com","¦Stat Rep: RP-141444->RP-141774 1st Apr 15: Compl:75%->100% 1st Apr 15: WID: RP-140621->RP-150077 1st Apr 15: Stat Rep: RP-141774->RP-150076","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5",61,31,null,null,"2013-08-30","2015-04-01"]
[5068,650011,"UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 3DL","LTE_CA_Rel12_3DL-UEConTest",1,"Rel-12","R5","2014-09-15","2016-03-15",1,"RP-151821","RP-151464","Microsoft","jussi.kuusisto@microsoft.com","¦Stat Rep: -->RP-141775 1st Apr 15: Compl:6%->12% 1st Apr 15: CD:Tue 15/09/15->Tue 15/12/15 1st Apr 15: WID: RP-142231->RP-150079 1st Apr 15: Stat Rep: RP-141775->RP-150078 03/07/15: Compl:12%->35% 03/07/15: WID: RP-150079->RP-150594 03/07/15: Stat Re","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5",65,33,null,null,"2014-09-09","2016-03-22"]
[5071,570017,"LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band",1,"Rel-12","R4,R2,R5","2012-09-12","2014-12-15",1,"RP-130843","-","AT&T","marc.grant@att.com","RP#58 RP-121701 work can start based on FCC Order (FCC-12-130) http://hraunfoss.fcc.gov/edocs_public/attachmatch/FCC-12-130A1.pdf","LTE",57,29,null,null,"2012-09-03","2013-06-11"]
[5075,570019,"Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil",1,"Rel-12","R4,R5","2012-09-11","2013-12-06",1,"RP-121414","-","Huawei","Liehai Liu (liuliehai@huawei.com)","-","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[5078,600005,"   Test part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-UEConTest",2,"Rel-12","R5","2013-06-18","2013-12-06",1,"RP-130646","RP-131457","Huawei","Xiang Li (tricia.li@huawei.com)","RP#62 completed","36.508, 36.521-1, 36.521-2, 36.521-3",60,31,null,null,"2013-05-30","2013-11-29"]
[5081,570220,"   Perf. part: Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh-Perf",2,"Rel-12","R4","2012-09-15","2014-12-15",1,"RP-121416","RP-142042","Alcatel-Lucent","ren.da@alcatel-lucent.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141378->RP-142042",36.100999999999999,57,29,null,null,"2012-09-03","2015-01-12"]
[5085,570225,"   Deleted - Perf. part: New Carrier Type for LTE","LTE_NCT-Perf",2,"Rel-12","R4","2012-09-17","2013-09-06",1,"RP-122028","RP-130985","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 0% completion","36.101, 36.104, 36.133, 36.141",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[5088,580227,"   Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Perf",2,"Rel-12","R4","2012-12-15","2015-09-15",1,"RP-121772","RP-151447","CATT","Zukang Shen (shenzukang@catt.cn)","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141342->RP-141948 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141948->RP-150154 03/07/15: Compl:55%->95% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150","36.101, 36.104, 36.133, 36.141",58,30,null,null,"2012-09-03","2015-09-29"]
[5091,580129,"   Core part: HetNet Mobility enhancements for LTE","HetNet_eMOB_LTE-Core",2,"Rel-12","R2,R4","2012-04-13","2014-09-12",1,"RP-122007","RP-141413","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","SP#65 completed","36.133, 36.304, 36.331",58,30,null,null,"2012-12-10","2014-09-09"]
[5092,580030,"Further enhancements for HeNB mobility-X2-GW","EHNB_enh2_X2GW",1,"Rel-12","R3","2012-12-10","2014-06-13",1,"RP-122006","-","Alcatel-Lucent","Philippe.Godin@alcatel-lucent.com","Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11¦remaining work including solution definition is Rel-12","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[5095,580231,"   Perf. part: 8 Rx Antennas for LTE UL","LTE_UL_8Rx-Perf",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","RP-131523","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","RP#62 completed","36.104, 36.141",58,30,null,null,"2012-09-03","2013-11-29"]
[5099,600014,"LTE Coverage Enhancements","Cov_Enh_LTE",1,"Rel-12","R1,R2,R4,R5","2013-03-01","2015-06-15",1,"RP-130833","-","China Telecom","Xiaoming She (shexm@ctbri.com.cn)","Triggered by Rel-11 TR 36.824 (FS_Cov_Enh_LTE)","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[5102,650012,"   Test part: LTE Coverage Enhancements","Cov_Enh_LTE-UEConTest",2,"Rel-12","R5","2014-09-15","2015-06-15",1,"RP-141150","RP-150631","China Telecom","YANG Shan (yangshan@ctbri.com.cn)","¦Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631","36.508, 36.523-1, 36.523-2, 36.523-3",65,33,null,null,"2014-09-09","2015-06-18"]
[5105,620073,"   Perf. part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Wed 17/12/14->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821",36.133000000000003,62,32,null,null,"2013-12-18","2015-01-12"]
[5108,620240,"   Perf. part: Dual Connectivity for LTE","LTE_SC_enh_dualC-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141797","RP-150791","NTT DOCOMO","kunihiko.teshima.hg@nttdocomo.com","¦Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791","36.101, 36.104, 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[5111,680070,"   UE Conformance Test Aspects - Dual connectivity for LTE","LTE_SC_enh_dualC-UEConTest",2,"Rel-12","R5","2015-06-15","2017-09-15",1,"RP-150840",null,"Ericsson",null,"tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16¦ ;",null,68,35,null,null,"2015-07-03","2017-09-19"]
[5112,620041,"E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2013-12-15","2017-06-15",1,"RP-141459","-","Huawei","Elean FAN (fanxiaoan@huawei.com)","Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041)","LTE",62,32,null,null,"2013-12-09","2014-09-15"]
[5115,680068,"   UE Conformance Test Aspects - E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-UEConTest",2,"Rel-12","R5","2015-06-15","2017-06-15",1,"RP-160414",null,"Huawei",null,"tested Core part: LTE_SC_enh_L1-Core 29/09/15: Compl:0%->10% 29/09/15: CD:Wed 15/06/16->Thu 15/12/16 29/09/15: Stat Rep: -->RP-151247¦1/1/16: Compl:10%->40%¦ ",null,68,35,null,null,"2015-07-03","2017-06-19"]
[5118,630031,"Smart Congestion Mitigation in E-UTRAN","SCM_LTE",1,"Rel-12","R2,S1,C1","2014-03-05","2015-09-15",1,"RP-140434","-","LG Electronics","youngdae.lee@lge.com","follow-up of TR 36.848 FS_SCM_LTE","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5122,670051,"   UE Conformance Test Aspects - Smart Congestion Mitigation in E-UTRAN","SCM_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2015-09-15",1,"RP-150797","RP-151445","NTT DOCOMO",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150202->RP-150797 03/07/15: Stat Rep: ->RP-150794 29/09/15: Compl:60%->100% 29/09/15: Stat Rep: RP-150794->RP-151445",null,67,34,null,null,"2015-04-01","2015-09-29"]
[5125,630046,"Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS",1,"Rel-12","R1,R2,R4,R3","2014-03-11","2017-03-15",1,"RP-141634","-","MediaTek","Craig.Burnet@mediatek.com","follow-up of TR 36.866 FS_LTE_NAICS","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5128,690070,"   UE Conformance Test Aspects: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-UEConTest",2,"Rel-12","R5","2015-09-15","2017-03-15",1,"RP-160265",null,"Mediatek",null,"tested: LTE_NAICS was a REL-12 RAN1 WI¦1/1/16: Compl:0%->35%¦1/1/16: WID: RP-151298->RP-151945¦",null,69,35,null,null,"2015-09-29","2017-03-21"]
[5132,580028,"HSPA signalling enhancements for more efficient resource usage for LCR","LCR_TDD_HSPA_sign_enh",1,"Rel-12","R1,R2,R3,R4","2012-12-11","2013-12-20",1,"RP-121984","-","CATT","Yanping Xing (xingyanping@catt.cn)","Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026","UTRA",58,30,null,null,"2012-12-10","2012-12-10"]
[5135,600017,"HNB Positioning for UTRA","UTRA_HNB_Pos",1,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 completed","UTRA",60,31,null,null,"2013-06-17","2013-12-09"]
[5136,600117,"   Core part: HNB Positioning for UTRA","UTRA_HNB_Pos-Core",2,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","RP-131974","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID)","25.305, 25.467, new 25.470",60,31,null,null,"2013-06-17","2013-12-09"]
[5139,610225,"   Perf. part: Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh-Perf",2,"Rel-12","R4","2013-09-15","2014-12-15",1,"RP-140771","RP-141970","Qualcomm","arjunb@qti.qualcomm.com","¦Stat Rep: RP-141137->RP-141970","25.101, 25.104, 25.133",61,31,null,null,"2013-09-07","2015-01-12"]
[5142,610126,"   Core part: UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob-Core",2,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","RP-140636","Huawei","Xudong Yang (yangxudong@huawei.com)","RP#64 completed. TS 25.300v100 for 1-step Approval","25.101, 25.104, 25.133, 25.141, 25.304, 25.306, 25.331, 25.433, new 25.300",61,31,null,null,"2013-09-07","2014-06-12"]
[5146,620254,"   Perf. part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-141701","RP-141898","Huawei","carmela.cozzo@huawei.com","¦Stat Rep: RP-141702->RP-141898","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[5149,620255,"   Perf. part: Enhanced Broadcast of System Information","UTRA_SIBenh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140131","RP-142080","Ericsson","martin.van.der.zee@ericsson.com","¦Stat Rep: RP-141230->RP-142080","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[5152,620249,"   Perf. part: Further Enhanced Uplink (EUL) enhancements","EDCH_enh-Perf",2,"Rel-12","R4","2013-12-15","2015-03-13",1,"RP-140127","RP-150062","Ericsson","mark.curran@ericsson.com","¦CD:Wed 18/03/15->Sun 15/03/15¦Stat Rep: RP-141684->RP-141860 1st Apr 15: Compl:75%->100% 1st Apr 15: Stat Rep: RP-141860->RP-150062","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-04-01"]
[5156,0,"Release 12 Studies","-",1,"Rel-12","SP,CP,GP,RP","2013-08-05","2014-09-16",0.8,"-","-","-","-","-","-","-","-",null,null,"2011-09-08","2011-09-15"]
[5159,490035,"Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int",1,"Rel-12","S1","2010-09-23","2012-03-07",1,"SP-100640","-","InterDigital","christopher.wallace@interdigital.com ","SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec)",22.895,49,25,null,null,"2010-08-31","2012-02-22"]
[5160,500035,"Study on Continuity of Data Sessions to Local Networks","FS_CSN",1,"Rel-12","S1","2010-12-16","2011-12-14",1,"SP-100885","-","NEC","joerg.swetina@neclab.eu","SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC)",22.896000000000001,50,26,null,null,"2010-11-25","2011-11-29"]
[5163,540027,"Study on User Plane Congestion management","FS_UPCON",1,"Rel-12","S1","2011-12-14","2012-09-12",1,"SP-110819","-","KDDI","John Visser (jvisser@rogers.com)","SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits)",22.805,54,28,null,null,"2011-11-29","2012-08-07"]
[5166,490034,"Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",1,"Rel-12","S2,S1,S3","2010-09-23","2012-12-12",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","Triggered by TR 22.906 SA1 Study on IMS based Peer-to-Peer Content Distribution Services UID_450047",23.844000000000001,49,25,null,null,"2010-09-15","2012-11-22"]
[5170,490036,"Study on Core Network Overload solutions","FS_CNO",1,"Rel-12","S2","2010-09-23","2013-12-11",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014)",23.843,49,25,null,null,"2010-08-31","2013-11-28"]
[5173,500037,"Study on System Enhancements for Energy Efficiency","FS_SEEE",1,"Rel-12","S2","2010-12-16","2012-06-20",1,"SP-100888","-","Huawei","frank.mademann@huawei.com","SP#56 completed",23.866,50,26,null,null,"2010-11-25","2012-06-19"]
[5177,410043,"Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",1,"Rel-12","S2,S1","2008-08-08","2012-12-12",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM)",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5180,560039,"Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces","FS_NBIFOM",1,"Rel-12","S2","2012-06-18","2013-03-06",1,"SP-120742","-","ZTE","Tricci So (tso@zteusa.com)","SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility)",23.861000000000001,56,29,"SP-59","PCG-30","2012-06-04","2013-02-27"]
[5183,550026,"Study on Security on spoofed call detection and prevention (Stage 2)","FS_SPOOF",1,"Rel-12","S3","2012-03-07","2014-09-17",1,"SP-120030","-","China Mobile","lixiangjun@chinamobile.com","SP#65 completed. TR 33.831v100 for 1-step Approval. Linked to Rel-11 SPUCI TR 33.838",33.831000000000003,55,28,null,null,"2012-02-20","2014-09-03"]
[5184,570035,"Study on Security Assurance Methodology for 3GPP Network Elements","FS_SECAM",1,"Rel-12","S3","2012-09-13","2014-06-18",1,"SP-120654","-","Orange","loic.habermacher@orange.com","SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible)",33.805,57,29,null,null,"2012-08-31","2014-05-21"]
[5187,470050,"Study on version handling","FS_OAM_VH",1,"Rel-12","S5","2010-03-25","2012-12-12",1,"SP-100082","-","Ericsson","thomas.tovinger@ericsson.com","SP#58 completed",32.83,47,24,null,null,"2010-02-12","2012-11-21"]
[5190,560032,"Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","FS_SON_NM_CCO",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140028","-","Ericsson","robert.petersen@ericsson.com","SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060)",32.835999999999999,56,29,null,null,"2012-04-18","2014-08-25"]
[5194,580026,"Study on Diameter Overload Control Mechanisms","FS_DOCME",1,"Rel-12","C4","2012-01-05","2014-09-11",1,"CP-120917","-","Orange","lionel.morand@orange.com","CP#65 completed. TR 29.809 v200 for Approval. Triggered by SA2 Rel-12 TR 23.843 Study on Core Network Overload solutions (FS_CNO) UID_490036. Coordinate with CT3, SA5",29.809000000000001,58,30,null,null,"2012-11-20","2014-07-28"]
[{"$f":"A5197+1","v":5197},620001,"Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME","FS_ISIM_CR",1,"Rel-12","C6","2013-12-09","2014-12-09",1,"CP-130812","-","Gemalto","ly-thanh.phan@gemalto.com","CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage¦June2015: Compl:30%->100",31.829000000000001,62,32,null,null,"2013-11-22","2015-06-15"]
[5201,520002,"Study on GERAN enhancements for Mobile Data Applications","FS_GERAN_eMDA",1,"Rel-12","G2,G1","2011-04-04","2014-08-29",1,"GP-110999","-","Huawei","ming.fang@huawei.com ","GP#63 completed. TR 43.802v200 for Approval. GP#50 approved WID (mobile coucou). Triggered by RAN#51 (Mar 2011) WID in RP-110454 (LTE RAN Enhancements for Diverse Data Applications) UID_510031",43.802,50,27,null,null,"2011-05-21","2014-08-29"]
[5204,530054,"Deleted - Study on Mobile Relay for E-UTRA","FS_LTE_mobRelay",1,"Rel-12","R3,R1","2005-05-19","2014-06-23",1,"RP-131375","RP-140726","CATT","Haijing Hu (huhaijing@catt.cn)","RP#64 stopped at 80% completion","LTE 36.836",53,27,"RP-64","PCG-33","2011-09-19","2014-06-23"]
[5207,580044,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects","FS_LTE_SC_enh_hilayer",1,"Rel-12","R2,R3","2012-12-10","2013-12-06",1,"RP-122033","RP-131619","NTT DOCOMO","Hideaki Takahashi (h-takahashi@nttdocomo.co.jp)","RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.842",58,30,null,null,"2012-12-10","2013-12-03"]
[5208,580038,"Study on LTE Device-to-Device Proximity Services - Radio Aspects","FS_LTE_D2D_Prox",1,"Rel-12","R1,R2,R3,R4","2012-12-17","2014-03-06",1,"RP-122009","RP-140416","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","RP#63 completed. TR 36.843 for 1-step approval (90% complete). Started normative work. Linked to Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) and Feature ProSe","LTE 36.843",58,30,null,null,"2012-12-10","2014-03-14"]
[5211,590016,"Study on Expansion of LTE_FDD_1670_US to include 1670-1680MHz Band for LTE in the US","FS_LTE_FDD_1670_US",1,"Rel-13","R4","2013-03-01","2014-12-15",1,"RP-130202","RP-141815","LightSquared","masoud.olfat@lightsquared.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:80%->100%¦Stat Rep: RP-141453->RP-141815","LTE 36.844",59,30,null,null,"2013-02-26","2015-01-12"]
[5214,600015,"Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul ","FS_COMP_LTE_nibackhaul",1,"Rel-12","R1","2013-06-18","2013-12-06",1,"RP-130847","RP-131626","Samsung","Hyojin Lee (hyojin257.lee@samsung.com)","RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332)","LTE 36.874",60,31,null,null,"2013-06-17","2013-12-03"]
[5218,530056,"Study on RF and EMC requirements for active Antenna Array System (AAS) Base Station","FS_AAS_BS_LTE_UTRA",1,"Rel-12","R4,R1","2011-09-19","2013-03-01",1,"RP-111349","RP-130124","Huawei","Ronnie.zhang@huawei.com","RP#59 completed","UTRA, LTE 37.840",53,27,null,null,"2011-09-19","2013-02-28"]
[5221,580045,"Study on WLAN/3GPP Radio Interworking","FS_UTRA_LTE_WLAN_interw",1,"Rel-12","R2","2012-12-10","2013-12-06",1,"RP-122038","RP-131611","Intel","sasha.sirotkin@intel.com","RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized¦User experience suboptimal when UE connects to overloaded WLAN.","UTRA, LTE 37.834",58,30,null,null,"2012-12-10","2013-12-03"]
[5225,580050,"Study on Base Station specification structure","FS_BSspec_struc",1,"Rel-12","R4","2012-12-10","2013-06-14",1,"RP-122039","RP-130580","Ericsson","johan.skold@ericsson.com","RP#60 completed (1-step approval). Study new BS spec structure to avoid duplicate work for new RF features (in case of identical features among different RATs)¦avoid future discussions on how to implement new featurES in CP-150single-RAT/multi-RAT specs","UTRA, LTE, MSR 37.810",58,30,null,null,"2012-12-10","2013-06-07"]
[5228,580039,"Study on Scalable UMTS FDD bandwidth","FS_UTRA_SCAL",1,"Rel-12","R1,R4","2012-12-10","2013-12-06",1,"RP-130221","RP-132035","China Unicom","Han Xiao (hanxiao91@chinaunicom.cn)","RP#62 completed. TR 25.701v200 for Approval","UTRA 25.701",58,30,null,null,"2012-12-10","2013-12-18"]
[5231,580043,"Study on Further Enhanced Uplink (EUL) enhancements","FS_EDCH_enh",1,"Rel-12","R2,R1,R3","2012-12-10","2013-12-06",1,"RP-130347","RP-131608","Ericsson","alessandro.caverni@ericsson.com ","RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.)","UTRA 25.700",58,30,null,null,"2012-12-10","2013-12-02"]
[5232,600018,"Study on HNB Emergency Warning Area for UTRA","FS_HNB_warn_area",1,"Rel-12","R3","2013-06-18","2014-03-06",1,"RP-131258","RP-140129","Alcatel-Lucent, Ip.access","Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com ","RP#63 completed. TR 25.703 v100 for 1-step approval","UTRA 25.703",60,31,null,null,"2013-06-17","2014-02-26"]
[5235,470051,"Advanced IP Interconnection of Services","IPXS",1,"Rel-11","S1,S2,C1,C3","2010-03-25","2012-09-12",1,"SP-100876","-","Telefónica","chris.friel@O2.com","CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS)","-",47,24,null,null,"2002-03-05","2012-11-19"]
[5239,530104,"      CT1 part of Stage 3 for Advanced IP Interconnection of Services","IPXS",3,"Rel-11","C1","2011-09-16","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed",24.228999999999999,53,27,null,null,"2011-08-29","2012-11-19"]
[5242,480130,"   Stage 1 for SIMTC","SIMTC",2,"Rel-11","S1","2010-06-10","2011-09-21",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#53 completed. SP#57 added MTC definitions in 21.905","22.368, 21.905 (MTC definitions)",48,25,null,null,"2010-05-28","2012-11-12"]
[5245,520121,"      Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7)","SIMTC-Reach",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","-",52,27,"SP-54","PCG-28","2011-05-26","2012-11-12"]
[5249,520521,"      MSISDN-less / PS-Only","SIMTC-Reach",3,"Rel-11","S2","2011-06-13","2012-03-07",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#55 completed","23.060, 23.272, New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5252,530106,"      CT1 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","23.040, 24.008, 24.301, 24.341, 24.368",53,27,null,null,"2011-08-29","2015-01-22"]
[5255,530406,"      CT6 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C6","2011-09-19","2012-09-07",1,"CP-120617","-","ST Ericsson","Andrzej Winiarski","22/01: acronym modified",31.102,53,27,null,null,"2011-08-29","2015-01-22"]
[5256,530005,"   Stage 2/3 for CS aspects for SIMTC ","SIMTC-CS",2,"Rel-11","C4,C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 2/3",53,27,null,null,"2011-08-29","2012-08-13"]
[5259,530305,"         CT1 part of Stage 3 CS aspects for SIMTC ","SIMTC-CS",4,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed","24.008, 24.301",53,27,null,null,"2012-06-15","2012-08-13"]
[5263,560202,"      CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",3,"Rel-11","C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed. TS 29.338 v200 for Approval","23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New 29.338 ",56,29,null,null,"2012-04-23","2012-11-28"]
[5266,530209,"      Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 3",53,27,null,null,"2011-08-29","2012-08-24"]
[5269,610014,"   Test part: System Improvements for Machine-Type Communications","SIMTC-UEConTest",2,"Rel-11","R5","2013-09-09","2014-03-06",1,"RP-140077","RP-140075","Ericsson","calle.hagenfeldt@ericsson.com","RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC","34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3",61,31,null,null,"2013-09-03","2014-03-03"]
[5273,520222,"      Deleted - Small Data Transmissions (TS 22.368, 7.2.5)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5276,530307,"         Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-",31.102,53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[5277,520023,"   Deleted - BB3: Stage 2 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",2,"Rel-11","S2","2011-06-08","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5280,520323,"      Deleted - MTC Monitoring (TS 22.368, 7.2.8)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-08","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5283,530208,"         Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-","31.101, 31.102",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[5287,530058,"      Deleted - MTC Location Privacy","SIMTC-Priv",3,"Rel-11","S3","2011-09-19","2012-09-12",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#57 stopped (activity transferred to Rel-12 Feature MTCe","TBD",53,27,"CP-57","PCG-29","2011-09-13","2012-11-12"]
[5290,480031,"Unstructured Supplementary Service Data (USSD) simulation service in IMS","USSI",1,"Rel-11","S1,C1,C3","2010-06-10","2012-12-07",1,"SP-100408","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","CP#58 completed","-",48,25,null,null,"2010-06-06","2012-11-19"]
[5293,520103,"      CT1 part of Stage 3 for USSD simulation service in IMS","USSI",3,"Rel-11","C1","2011-06-03","2012-12-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at, TS 24.390 Rapp: lili.yang@huawei.com","CP#58 completed","24.173, 24.229, new 24.390",52,27,null,null,"2011-05-18","2012-11-19"]
[5297,510043,"   Stage 2 for QoS Control Based on Subscriber Spending Limits","QoS_SSL",2,"Rel-11","S2","2011-03-23","2011-09-21",1,"SP-110519","-","Huawei","Xu Xia (xiatony@huawei.com)","SP#53 completed",23.202999999999999,51,26,null,null,"2011-03-10","2011-08-12"]
[5300,490032,"Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",1,"Rel-11","S1,S2","2010-09-23","2012-03-07",1,"SP-110347","-","Vodafone","mona.mustapha@vodafone.com","SP#55 completed (Stage 2/3 specified under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021. Triggered by S1-102236/GSMA RILTE 10_007r1 (IREG LS_038 to 3GPP on Optimal Media Routing drawbacks)","-",49,25,null,null,"2010-08-31","2012-03-05"]
[5301,490132,"   TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S2","2010-09-23","2012-03-07",1,"SP-110347","-","Vodafone","Susana.Sabater@vodafone.com ","SP#55 completed","new 23.849",49,25,null,null,"2010-08-31","2012-03-05"]
[5304,530021,"Inclusion of Media Resource Broker (Stage 2/3)","MRB",1,"Rel-11","C1,C3,IETF","2011-09-16","2013-06-14",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032","Stage 2/3",53,27,null,null,"2011-08-25","2012-06-06"]
[5307,530321,"      CT1 part of Stage 3 for Inclusion of Media Resource Broker","MRB",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed","24.229, 29.165",53,27,null,null,"2011-08-25","2012-08-14"]
[5311,500130,"   Stage 1 for Non Voice Emergency Services","NOVES",2,"Rel-11","S1","2010-12-16","2011-09-21",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed",22.100999999999999,50,26,null,null,"2010-11-29","2011-08-24"]
[5314,510147,"   Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",2,"Rel-11","S1","2011-03-23","2011-09-21",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 completed ",22.228000000000002,51,26,null,null,"2011-02-21","2011-08-24"]
[5317,520128,"   Stage 1 for Anonymous Call Rejection in the CS domain","ACR_CS",2,"Rel-11","S1","2011-06-07","2011-06-08",1,"SP-110421","-","Alcatel-Lucent","Betsy.Covell@alcatel-lucent.com","SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013)","22.004, 22.081, 22.082, 22.085, 22.088",52,27,null,null,"2011-05-19","2011-09-19"]
[5321,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[5324,470023,"   Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2","2010-03-26","2012-06-20",1,"SP-120539","-","Ericsson","stefan.rommer@ericsson.com","SP#56 completed","23.203, new 23.139",47,24,null,null,"2009-12-06","2012-06-09"]
[{"$f":"A5325+1","v":5325},541001,"   (IETF) Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2-IETF","2011-12-12","2012-12-12",1,"SP-120539","-","Lionel Morand","Lionel Morand","Solved by IANA-registration. No RFC needed","-",54,28,null,null,"2011-12-06","2012-11-22"]
[5328,550005,"      TR on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface","BBAI_BBI-CT",3,"Rel-11","C4","2012-03-02","2012-06-15",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#56 completed","new 29.839",55,28,null,null,"2012-02-20","2012-06-14"]
[5331,530312,"      CT3 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C3","2011-09-16","2012-09-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#57 completed","29.212, 29.213, 29.215",53,27,null,null,"2011-08-29","2012-08-13"]
[5335,530013,"   Stage 3 BB II - Core Network impacts: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",2,"Rel-11","C3,C1,C4","2011-09-16","2012-09-07",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#57 completed","Stage 3",53,27,null,null,"2011-08-29","2012-06-14"]
[5338,530313,"      CT3 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C3","2011-09-16","2012-09-07",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#57 completed","29.212, 29.213, 29.215",53,27,null,null,"2011-08-29","2012-08-13"]
[5342,530014,"   Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility ","-",2,"Rel-11","C3,C1,C4","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2012-03-06"]
[5345,530314,"      Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C3","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","29.212, 29.213, 29.215",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5347,480035,"Single Radio Voice Call Continuity (SRVCC) aspect of enhancements for Multimedia Priority Service","eMPS_SRVCC",1,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#54 completed. Analyze and if needed specify mechanisms for the priority handling of SRVCC with regard to LTE/EPC","Stage 2",48,25,null,null,"2010-06-06","2011-08-12"]
[5348,480135,"   TR on SRVCC for eMPS","eMPS_SRVCC",2,"Rel-11","S2","2010-06-10","2011-06-08",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#52 completed","new 23.854",48,25,null,null,"2010-06-06","2011-08-12"]
[5351,500126,"   Stage 2 for Single Radio Video Call Continuity for 3G-CS","vSRVCC",2,"Rel-11","S2","2010-10-15","2011-09-21",1,"SP-100704","-","Samsung","xiaowan.ke@samsung.com","SP#53 completed. Triggered by Feasibility Study on video call handover capability in TR 23.886 UID_470048 Study on Single Radio Video Call Continuity for 3G-CS (FS_vSRVCC)","23.203, 23.216, 23.237",50,26,null,null,"2010-11-26","2012-06-18"]
[5354,520205,"      CT3 aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",3,"Rel-11","C3","2011-06-03","2011-12-02",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","CP#54 completed","29.211, 29.212, 29.213, 29.215",52,27,null,null,"2011-05-18","2012-06-06"]
[5358,480138,"   TR on Stage 2 for Network-provided Location information for IMS","NWK-PL2IMS",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","SP#54 completed","new 23.842",48,25,null,null,"2010-06-06","2011-12-06"]
[5361,550008,"   CT aspects of Network-provided Location information for IMS (Stage 3)","NWK-PL2IMS-CT",2,"Rel-11","C3,C4,C1","2012-03-02","2013-03-01",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","Stage 3. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","-",55,28,null,null,"2012-02-22","2015-03-03"]
[5365,500032,"Service Awareness and Privacy Policies","SAPP",1,"Rel-11","S2,S1,C3","2010-10-12","2011-12-02",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047","-",50,26,null,null,"2010-11-26","2011-08-12"]
[5368,510003,"   CT3 part of Service Awareness and Privacy Policies","SAPP-CT3",2,"Rel-11","C3","2011-03-18","2011-12-02",1,"CP-110136","-","Allot","Alla Goldner (agoldner@allot.com)","CP#54 completed. Stage 3 to support Application Detection and Control Functionality. Update Gx / introduce Sd reference points and procedures. Update S9 reference point in roaming scenarios","29.212, 29.213, 29.214, 29.215",51,26,null,null,"2011-03-02","2011-11-24"]
[5371,530017,"   CT aspects of VPLMN Autonomous CSG Roaming","VCSG-St3",2,"Rel-11","C4","2011-12-07","2011-12-07",1,"CP-120196","-","ZTE","Fei Lu (lu.fei1@zte.com.cn)","CP#57 completed","23.003, 23.007, 23.008, 23.012, 29.002, 29.230, 29.272",53,27,null,null,"2011-08-27","2012-08-13"]
[5372,510048,"Data Identification in Access Network Discovery and Selection Function (ANDSF)","DIDA",1,"Rel-11","S2,C1","2011-03-23","2012-12-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions","Stage 2/3",51,26,null,null,"2011-02-21","2012-11-19"]
[5375,550003,"   CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3","DIDA-CT",2,"Rel-11","C1","2012-03-02","2012-12-07",1,"CP-120089","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#58 completed","24.302, 24.312",55,28,null,null,"2012-02-20","2013-01-21"]
[5379,540110,"      CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",3,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","CP#56 completed",29.273,54,28,null,null,"2011-11-23","2012-09-24"]
[5382,530101,"   Stage 2 for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC",2,"Rel-11","S2","2011-09-22","2012-06-20",1,"SP-110475","-","Orange","antoine.mouquet@orange-ftgroup.com ","SP#56 completed","23.216, 23.237",53,27,null,null,"2011-08-12","2012-06-18"]
[5385,530401,"      CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","29.165, 29.292",53,27,null,null,"2011-08-25","2012-08-14"]
[{"$f":"A5389+1","v":5389},530801,"      Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-RAN_UTRA-Core",3,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-111334","RP-121553","Huawei","liwei.qiu@huawei.com","RP#58 completed","25.331, 25.401, 25.413",53,27,null,null,"2011-08-25","2012-11-27"]
[5392,530146,"   Stage 2 for S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",2,"Rel-11","S2","2011-09-22","2012-03-07",1,"SP-110642","-","ZTE","zhu.chunhui@zte.com.cn","SP#55 completed","23.002, 23.203, 23.402",53,27,null,null,"2011-08-12","2012-02-20"]
[5395,561010,"      Deleted - (IETF) CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C4-IETF","2012-04-23","2014-03-05",1,"CP-110802","-","Lionel Morand","-","CP#63 Draft removed from 3GPP documentation","draft-ietf-radext-ieee802ext",56,29,"CP-53","PCG-32","2012-04-20","2014-02-19"]
[5396,540211,"      Deleted - CT1 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C1","2011-12-02","2012-06-15",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#56 stopped (no CT1 impact)",24.302,54,28,"CP-56","PCG-29","2011-10-26","2012-06-01"]
[5399,540129,"   Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",2,"Rel-11","S2","2011-11-28","2011-12-14",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","SP#54 completed","23.002, 23.228",54,28,null,null,"2011-10-25","2011-11-28"]
[5403,550204,"      CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CT",3,"Rel-11","C3","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","29.165, 29.162, 29.079",55,28,null,null,"2012-02-20","2012-11-20"]
[5406,570007,"   Stage 3 for IMS Overload Control","IOC",2,"Rel-11","C1,C3,IETF","2012-09-05","2014-12-09",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","-","-",57,29,null,null,"2012-08-13","2012-11-20"]
[5409,571001,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control)","RFC 7339",57,29,null,null,"2012-09-03","2015-03-10"]
[5413,520032,"Lawful Interception in the 3GPP Rel-11","LI11",1,"Rel-11","S3","2011-06-10","2012-06-20",1,"SP-110424","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com ","Stage 1/2/3. SP#56 completed","33.106, 33.107, 33.108",52,27,null,null,"2011-05-17","2012-06-08"]
[5416,560009,"   Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms)","EEA3_EIA3_UEConTest",2,"Rel-11","R5","2012-06-18","2012-09-07",1,"RP-120631","RP-120968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223)","36.523-1, 36.523-2, 36.523-3",56,29,null,null,"2012-06-04","2012-09-04"]
[5419,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[5420,540112,"   Stage 2 for GBA extensions for re-use of SIP Digest credentials","GBA-ext",2,"Rel-11","S3","2011-12-14","2012-03-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","SP#55 completed",33.22,54,28,null,null,"2011-11-28","2012-02-20"]
[5423,540412,"      CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",3,"Rel-11","C1","2011-12-05","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",24.109000000000002,54,28,null,null,"2011-11-23","2012-08-14"]
[5427,530248,"   Download Delivery Enhancements for MBMS","EMM-DDE",2,"Rel-11","S4","2011-09-21","2012-12-12",1,"SP-120025","-","Qualcomm","Nikolai Leung (nleung@qualcomm.com)","SP#58 completed","26.346, new 26.951=>26.851",53,27,null,null,"2011-09-07","2012-12-11"]
[5430,510051,"Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM11",1,"Rel-11","S5","2011-03-23","2013-03-07",1,"-","-","-","-","OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI","-",51,26,null,null,"2011-02-22","2011-02-22"]
[5433,510251,"   Rel-11 Performance Management","OAM11-PM",2,"Rel-11","S5","2011-03-23","2012-12-12",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2012-11-19"]
[5437,530049,"      Management of Carrier Aggregation for LTE","OAM-CA",3,"Rel-11","S5","2011-09-21","2012-12-12",1,"SP-120776","-","Nokia Siemens Networks, Ericsson","yizhi.yao@nsn.com, per.elmdahl@ericsson.com","SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA)",32.424999999999997,53,27,null,null,"2011-08-27","2012-11-20"]
[5440,530051,"      LTE Self-Organizing Networks (SON) coordination management","OAM-SON-LTE_COORD",3,"Rel-11","S5","2011-09-21","2013-03-06",1,"SP-110637","-","Huawei, Nokia Siemens Networks","kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com","SP#59 completed","LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766",53,27,null,null,"2011-08-27","2013-02-16"]
[5441,540031,"      Inter-RAT Energy Saving Management","OAM-IRAT-ESM",3,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-110701","-","Nokia Siemens Networks, Huawei","clemens.suerbaum@nsn.com, xiahaitao@huawei.com","SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs","32.405, 32.551, 32.522, 32.526, 32.642, 32.646, 32.762, 32.766",54,28,null,null,"2011-11-22","2012-11-19"]
[5444,510060,"   Charging for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Data Bases","PEST-CH",2,"Rel-11","S5","2011-03-21","2011-09-21",1,"SP-110126","-","Ericsson","patrik.teppo@@ericsson.com","SP#53 completed. Stage 3","32.251, 32.298, 32.299",51,26,null,null,"2011-02-22","2011-08-26"]
[5447,510129,"   Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","S1","2010-10-27","2011-09-21",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","SP#53 completed under IPXS",22.114999999999998,51,26,null,null,"2011-02-22","2011-10-07"]
[5451,480036,"   Stage 1 for UDC Data Model","UDC_DM",2,"Rel-11","S1","2010-03-25","2011-09-21",1,"-","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","SP#53 completed under Rel-10 UDC",22.100999999999999,48,25,null,null,"2010-05-26","2011-09-19"]
[5454,510004,"Definition of the UICC Application for Hosting Party Module","HPM_UICC",1,"Rel-11","C6","2011-03-18","2012-06-15",1,"CP-110289","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#56 completed","31.102, New 31.104",51,26,null,null,"2011-03-03","2012-09-25"]
[5457,520108,"   CT4 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C4","2011-06-03","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed","23.007, 23.008, 23.018, 29.274, 29.275",52,27,null,null,"2011-05-18","2012-11-20"]
[5461,520009,"Reference Location Information (Stage 3)","RLI",1,"Rel-11","C4,C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11)","-",52,27,null,null,"2011-05-18","2011-06-01"]
[5464,520010,"IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",1,"Rel-11","C1,C3,IETF","2011-06-07","2014-09-12",0.99,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","-",52,27,null,null,"2011-05-18","2013-02-28"]
[5465,520110,"   CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C1","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","23.218, 24.229, 24.930",52,27,null,null,"2011-05-18","2012-08-14"]
[5468,611002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135)","IMSProtoc5",2,"Rel-11","C1-IETF","2013-09-06","2014-06-13",1,"CP-110437","-","Roland Jesske","Roland Jesske","CP#64 completed","RFC 7135 (was draft-polk-local-emergency-rph-namespace)",61,31,null,null,"2013-08-23","2014-06-06"]
[5471,530003,"Service Identification for RRC Improvements in GERAN (Stage 2/3)","SIRIG",1,"Rel-11","S2,C4,C3,G2","2011-09-19","2012-09-07",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","TSG#57, GP#55 completed. CT defined a generic solution (not only for GERAN)","GERAN",51,27,null,null,"2011-09-06","2012-09-06"]
[5475,550009,"      Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN","SIRIG",3,"Rel-11","C3","2012-03-02","2012-06-15",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","CP#56 stopped (SA2 decided NO CT3 impact)",29.212,55,28,"CP-56","PCG-29","2012-02-20","2012-04-20"]
[5478,530119,"   SAE Protocol Development (Stage 3) - Phase 2","SAES2",2,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110639","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",53,27,null,null,"2011-09-08","2012-08-14"]
[5481,530120,"   CT1 part of GCSMSC and GCR Redundancy for VGCS/VBS","RT_VGCS_Red",2,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed","43.068, 43.069",53,27,null,null,"2011-08-27","2012-08-14"]
[5485,540117,"   CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",2,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed","23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334",54,28,null,null,"2011-10-26","2012-08-13"]
[5488,560005,"AT commands for Universal Resource Identifier (URI) support","ATURI",1,"Rel-11","C1","2012-06-15","2013-03-01",1,"CP-120275","-","Intel","frank.kowalewski@intel.com","CP#59 completed. Define new AT cmd for URI addresses for IMS services (eg VoLTE). 27.007(AT cmd to control MT functions and GSM/UMTS/LTE network services from TE), 27.005(AT commands for SMS). Currently address types for AT cmd based on dialling#","27.005, 27.007",56,29,null,null,"2012-06-02","2013-02-16"]
[5489,560006,"PS Additional Number (Stage 3)","PSAN",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120253","-","Deutsche Telekom","Yvette.koza@t-mobile.at","CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact)","23.003, 23.008, 29.002, 29.272, 29.230",56,29,null,null,"2012-04-23","2012-08-13"]
[5492,570110,"   CT1 part of IMS Operator Determined Call Barring","IODB",2,"Rel-11","C1","2012-09-10","2013-06-14",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","CP#60 completed. Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CT decision.","New 24.315",57,29,null,null,"2012-08-13","2013-06-13"]
[5495,570111,"   CT3 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C3","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",29.163,57,29,null,null,"2012-08-13","2012-11-20"]
[5499,540116,"   Deleted - TR Study on enhancement of protocols for SMS service over SGs","PROTOC_SMS_SGs",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped (abandonned new TR 29.818)","new 29.818",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[5502,510001,"Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",1,"Rel-11","G2,S2,C1","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001","GERAN",49,26,null,null,"2011-03-04","2013-05-17"]
[5506,510401,"      CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C1","2011-06-03","2012-12-07",1,"CP-120563","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#58 completed",24.007999999999999,49,26,null,null,"2011-03-04","2012-11-19"]
[5509,540003,"Medium range/local area requirements for multicarrier BTS","MRLA",1,"Rel-11","G1","2011-11-25","2012-11-23",1,"GP-111780","-","Ericsson","Eric Nordström","GP#56 completed. GP#52 approved WID","GERAN",52,28,null,null,"2011-11-25","2012-11-23"]
[5512,550023,"Domain Specific Access Control in GERAN","GDSAC",1,"Rel-11","G2","2012-03-05","2012-08-31",1,"GP-120452","-","Vodafone","chris.pudney@vodafone.com","GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001)","GERAN 44.018",53,28,null,null,"2012-04-18","2012-08-31"]
[5513,500020,"Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB",1,"Rel-11","R4,R2,R3,R5","2010-12-10","2013-03-01",1,"RP-111396","-","Sprint","John.J.Humbert@Sprint.com","Stage 3. Triggered by R4 Rel-10 LTE TR 37.806 Study on Extending 850 MHz (UID_440016)","UTRA, LTE",50,26,null,null,"2010-12-10","2012-02-23"]
[5516,510016,"   Test part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-UEConTest",2,"Rel-11","R5","2011-03-18","2013-03-01",1,"RP-110377","RP-130043","Sprint","John.J.Humbert@Sprint.com","RP#59 completed","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",51,26,null,null,"2011-03-10","2013-02-27"]
[5519,530033,"Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2013-12-06",1,"RP-121204","-","MediaTek","Johan Johansson","Stage 2/3","UTRA, LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5523,530136,"   Core part: Network Energy Saving for E-UTRAN","Netw_Energy_LTE-Core",2,"Rel-11","R3","2011-09-19","2012-09-07",1,"RP-120620","RP-121016","China Mobile","yangning@chinamobile.com","RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well","25.413, 36.300, 36.413, 36.423",53,27,null,null,"2011-09-15","2012-09-06"]
[5526,530137,"   Core part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-Core",2,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-111383","RP-121558","Ericsson","johan.skold@ericsson.com","RP#58 completed. TR 37.809 v200 for Approval","25.104, 36.104, 37.104, new 37.809",53,27,null,null,"2011-09-15","2012-12-05"]
[5530,550115,"   Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Core",2,"Rel-11","R4,G1","2012-02-06","2012-12-07",1,"RP-120857","RP-121985","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#58 completed","25.104, 25.105, 36.104, 37.104, new 37.812",55,28,null,null,"2012-02-23","2012-12-05"]
[5533,560113,"   Core part: Further enhancements to H(e)NB mobility - Part 1","EHNB_enh1-Core",2,"Rel-11","R3,R2","2012-06-15","2012-12-07",1,"RP-121427","RP-121563","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#58 completed","25.413, 25.467, 25.469, 36.300, 36.413, 36.423",56,29,null,null,"2012-06-13","2012-11-27"]
[5536,430011,"Network-Based Positioning Support for LTE","LCS_LTE-NBPS",1,"Rel-11","R2,R1,R3,R4","2009-03-05","2014-06-13",1,"RP-131259","-","TruePosition","terri.brooks@trueposition.com","-","LTE",43,22,null,null,"2009-03-06","2012-09-04"]
[5537,430111,"   Core part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Core",2,"Rel-11","R2,R1,R3,R4","2009-03-05","2013-06-12",1,"RP-131259","RP-130483","TruePosition","terri.brooks@trueposition.com","RP#60 completed","36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new (36.111, 36.456, 36.457, 36.458, 36.459)",43,22,null,null,"2009-03-06","2013-08-29"]
[5540,480126,"   Core part: Service continuity improvements for MBMS for LTE","MBMS_LTE_SC-Core",2,"Rel-11","R2,R3","2010-06-04","2012-09-07",1,"RP-120258","RP-121001","Huawei","David.Lecompte@huawei.com ","RP#57 completed","25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445",48,25,null,null,"2010-06-04","2012-09-06"]
[5544,510221,"   Perf. part: Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE-Perf",2,"Rel-11","R4","2011-03-23","2013-12-06",1,"RP-120860","RP-131463","China Mobile","ShenXiaodong@chinamobile.com","RP#62 completed","36.101, 36.104, 36.133, 36.141",51,26,null,null,"2011-03-14","2013-11-29"]
[5547,510128,"   Core part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700-Core",2,"Rel-11","R4","2011-03-22","2012-12-07",1,"RP-110710","RP-121604","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.141, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5550,510131,"   Core part: LTE RAN Enhancements for Diverse Data Applications","LTE_eDDA-Core",2,"Rel-11","R2","2011-03-18","2012-12-07",1,"RP-120256","RP-121571","BlackBerry","Gordon Young (gyoung@rim.com)","RP#58 completed","36.300, 36.321, 36.331, new 36.822",51,26,null,null,"2011-03-14","2012-11-29"]
[5554,510232,"   Perf. part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-Perf",2,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-120602","RP-120571","NII Holdings","bill.shvodian@nii.com","RP#56 completed","25.123, 25.133, 25.141, 36.133, 36.141, 37.141",51,26,null,null,"2011-03-14","2012-06-09"]
[5557,520117,"   Core part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Core",2,"Rel-11","R4,R2,R3","2011-06-07","2012-06-15",1,"RP-110875","RP-120572","Ericsson","olav.queseth@ericsson.com","RP#56 completed. TR 36.820 v100 for Information and Approval","25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.113, new 36.820",52,27,null,null,"2011-06-02","2012-06-09"]
[5560,520019,"Relays for LTE (part 2)","LTE_Relay2",1,"Rel-11","R4","2009-12-04","2013-06-14",1,"RP-110914","-","Ericsson","christian.hoymann@ericsson.com ","Continuation of Rel-10 (open RAN4 Core & Perf parts)","LTE",46,24,null,null,"2009-11-30","2011-06-06"]
[5561,520119,"   Core part: Relays for LTE (part 2)","LTE_Relay2-Core",2,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110914","RP-121008","Ericsson","christian.hoymann@ericsson.com ","RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10","36.133, new RAN4 (36.116, 36.826)",52,27,null,null,"2011-06-03","2012-09-04"]
[5564,530131,"   Core part: Signalling and Procedure for Interference Avoidance for in-device coexistence","SPIA_IDC_LTE-Core",2,"Rel-11","R2,R4","2011-09-19","2012-12-07",1,"RP-111355","RP-121573","China Mobile","Zhenping HU","RP#58 completed","36.133, 36.300, 36.306, 36.321, 36.331",53,27,null,null,"2011-09-15","2012-11-27"]
[5568,530232,"   Perf. part: Coordinated Multi-Point Operation for LTE – Uplink","COMP_LTE_UL-Perf",2,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-111365","RP-121576","Huawei","Xinwei Zhi (zhixinwei@huawei.com)","RP#58 completed","36.101, 36.104, 36.133, 36.141",53,27,null,null,"2011-09-15","2012-11-27"]
[5571,590004,"   Test part: Coordinated Multi-Point Operation for LTE","COMP_LTE-UEConTest",2,"Rel-11","R5","2013-03-15","2014-12-15",1,"RP-130376","RP-141782","Samsung","Stoyan.Baev@partner.samsung.com",null,"36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2015-01-12"]
[5574,540225,"   Perf. part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-Perf",2,"Rel-11","R4","2011-12-16","2014-06-13",1,"RP-120871","RP-140651","Alcatel-Lucent","teck.hu@alcatel-lucent.com","RP#64 completed","36.101, 36.104, 36.133, 36.141",54,28,null,null,"2011-12-07","2014-06-11"]
[5578,590006,"   Test part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-09-06",1,"RP-130169","RP-130949","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#61 completed","36.521-1, 36.521-2",59,30,null,null,"2013-02-26","2013-08-29"]
[{"$f":"A5581+1","v":5581},600002,"   Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-UEConTest",2,"Rel-11","R5","2013-06-18","2014-09-12",1,"RP-140491","RP-141602","Broadcom","jarkko.hellsten@kolumbus.fi","RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101","36.508, 36.521-1, 36.521-2, New 36.904",60,31,null,null,"2013-05-22","2014-09-07"]
[5584,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[5586,510030,"   LTE Carrier Aggregation Enhancements","LTE_CA_enh",2,"Rel-11","R1,R2,R3,R4,R5","2011-03-15","2014-12-12",1,"RP-121999","-","Nokia","lars.e.lindh@nokia.com","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-09-04"]
[5587,510130,"      Core part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Core",3,"Rel-11","R1,R2,R4,R3","2011-03-22","2013-08-27",1,"RP-121999","RP-130059","Nokia","lars.e.lindh@nokia.com","RP#59 completed. New TR 36.823 v100 for Information and Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new 36.823",51,26,null,null,"2011-03-14","2013-02-27"]
[5591,580258,"   Rel-11 inter-band Carrier Aggregation","-",2,"Rel-11","R4","2010-12-10","2012-12-07",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[5594,480223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-120830","RP-121023","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed","36.133, 36.141",48,25,null,null,"2010-06-04","2012-09-04"]
[5597,500217,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-121458","RP-121595","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",50,26,null,null,"2010-12-10","2012-11-26"]
[5601,510022,"      LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120877","-","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[5604,510023,"      LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","-","US Cellular","sebastian.thalanany@uscellular.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[5605,510123,"         Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","RP-121596","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[5608,510124,"         Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20-Core",4,"Rel-11","R4","2011-03-22","2012-09-07",1,"RP-120889","RP-121032","Huawei","Steven Chen","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[5611,510125,"         Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17-Core",4,"Rel-11","R4","2011-03-23","2012-09-07",1,"RP-110432","RP-121034","AT&T","marc.grant@att.com ","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[5615,510226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110433","RP-121589","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5618,510227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110434","RP-121599","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5621,530223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20-Perf",4,"Rel-11","R4","2011-09-20","2012-09-07",1,"RP-120887","RP-121047","Vodafone","tim.frost@vodafone.com","RP#57 completed","36.101, 36.104, 36.133, 36.141, 36.307",53,27,null,null,"2011-09-15","2012-09-04"]
[5625,530026,"      LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120899","-","SK Telecom","Haesung Park","Stage 3. RP#57 completed","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[5628,530027,"      LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7",3,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-121152","-","Rogers Wireless","takwing.wan@rci.rogers.com","Stage 3. RP#58 completed","LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5629,530127,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-121152","RP-121590","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[5632,540120,"         Core part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Core",4,"Rel-11","R4,R2","2011-12-09","2012-12-07",1,"RP-120898","RP-121602","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-12-04"]
[5635,540121,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18-Core",4,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-120892","RP-121052","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-09-04"]
[5639,540222,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Perf",4,"Rel-11","R4","2011-12-12","2012-06-15",1,"RP-120866","RP-120553","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed","36.133, 36.141",54,28,null,null,"2011-12-07","2012-06-15"]
[5642,540223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Perf",4,"Rel-11","R4","2011-12-13","2012-12-07",1,"RP-121173","RP-121055","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed","36.133, 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[{"$f":"A5645+1","v":5645},550218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Perf",4,"Rel-11","R4","2012-03-06","2012-12-07",1,"RP-121162","RP-121587","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed","36.133, 36.141",55,28,null,null,"2012-02-23","2012-11-27"]
[5649,520215,"         Perf. part: LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38-Perf",4,"Rel-11","R4","2011-06-08","2012-09-07",1,"RP-110862","RP-121061","Huawei","ronnie.zhang@huawei.com","RP#57 completed","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141",52,27,null,null,"2011-06-02","2012-09-04"]
[5652,520216,"         Perf. part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Perf",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120127","Clearwire","michael.hart@clearwire.com","RP#55 completed","36.101, 36.104, 36.133, 36.141, 36.307",52,27,null,null,"2011-06-02","2012-02-23"]
[5653,530028,"      LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-121193","-","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","Stage 3. RP#57 completed. Updated WID RP-111356=>RP-121193. WI only covers intra-band contiguous and not non-contiguous aspects","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[5656,450016,"UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest",1,"Rel-11","R4,R5","2009-09-18","2016-09-15",1,"RP-111381","-","CATR","Guo Lin (guolin@emcite.com)","-","UTRA",45,23,null,null,"2009-09-15","2011-09-17"]
[5659,500019,"Eight carrier HSDPA","8C_HSDPA",1,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-12-07",1,"RP-101419","-","Ericsson","johan.hultell@ericsson.com","Stage 3","UTRA",50,26,null,null,"2010-12-10","2012-09-04"]
[5663,500121,"   Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc-Perf",2,"Rel-11","R4","2010-12-10","2011-09-16",1,"RP-111244","RP-110996","China Mobile","Li Nan (linan@chinamobile.com)","RP#53 completed. TR 25.873v100 for Approval","25.102, new 25.873",50,26,null,null,"2010-12-10","2011-09-12"]
[5666,500122,"   Core part: Uplink Transmit Diversity for HSPA - Closed Loop","HSPA_UL_TxDiv-CL-Core",2,"Rel-11","R1,R4,R2,R3","2010-12-10","2012-12-07",1,"RP-120367","RP-121542","Huawei","zongjie.wang@huawei.com","RP#58 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433",50,26,null,null,"2010-12-10","2012-11-28"]
[5670,590008,"   Test part: Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv-UEConTest",2,"Rel-11","R5","2013-03-04","2014-06-13",1,"RP-130351","RP-140767","Qualcomm","Shubhang Vora (svora@qti.qualcomm.com)","RP#64 completed","34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",59,30,null,null,"2013-01-29","2014-06-10"]
[5673,510218,"   Perf. part: Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config-Perf",2,"Rel-11","R4","2011-03-24","2012-06-15",1,"RP-110308","RP-120475","Telus Communications","jorge.delrio@telus.com ","RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",51,26,null,null,"2011-03-14","2012-06-09"]
[5676,510219,"   Perf. part: Non-contiguous 4C-HSDPA operation","NC_4C_HSDPA-Perf",2,"Rel-11","R4","2011-03-23","2013-03-01",1,"RP-110416","RP-130049","Ericsson","muhammad.kazmi@ericsson.com","RP#59 completed","25.101, 25.104, 25.133, 25.141",51,26,null,null,"2011-03-14","2013-02-27"]
[5677,510020,"Further Enhancements to CELL_FACH","Cell_FACH_enh",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-18","2015-03-13",1,"RP-111321","-","Qualcomm","Ravi Agarwal","-","UTRA",51,26,null,null,"2011-03-14","2011-09-16"]
[5680,600004,"   Test part: Further Enhancements to CELL_FACH","Cell_FACH_enh-UEConTest",2,"Rel-11","R5","2013-06-15","2015-03-13",1,"RP-130644","RP-150132","Ericsson","leif.mattisson@ericsson.com","¦Stat Rep: RP-141164->RP-141770 1st Apr 15: Compl:92%->100% 1st Apr 15: Stat Rep: RP-141770->RP-150132","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 ",60,31,null,null,"2013-05-22","2015-04-01"]
[5683,530234,"   Perf. part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-Perf",2,"Rel-11","R4","2011-09-20","2013-09-06",1,"RP-111375","RP-130959","Nokia Siemens Networks","kamil.bechta@nsn.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",53,27,null,null,"2011-09-15","2013-08-29"]
[5687,530235,"   Perf. part: Four Branch MIMO transmission for HSDPA","4Tx_HSDPA-Perf",2,"Rel-11","R4","2011-09-21","2013-12-06",1,"RP-111393","RP-131460","Ericsson","johan.hultell@ericsson.com","RP#62 completed","25.101, 25.104, 25.133, 25.141",53,27,null,null,"2011-09-15","2013-11-29"]
[5690,540209,"   Perf. part: MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA-Perf",2,"Rel-11","R4","2011-12-13","2013-09-06",1,"RP-121794","RP-130960","Nokia Siemens Networks","kamil.bechta@nsn.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",54,28,null,null,"2011-12-07","2013-08-29"]
[5694,620015,"Split TTCN Test Models for IMS testing in TS 34.229-3","IMS-CCR_Test2",1,"Rel-11","R5","2013-12-09","2014-09-12",1,"RP-140440","RP-141155","Spirent","richard.catmur@spirent.com","SP#65 completed. TS 34.229-4 for Approval. Split out of old TS 34.229-3 a new TS 34.229-4","34.229-3, New 34.229-4",62,32,null,null,"2013-11-25","2014-09-09"]
[5697,571004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-11 (RFC 7077)","TEI11_IETF",1,"Rel-11","C4-IETF","2012-09-07","2013-12-06",1,"-","-","Lionel Morand","Lionel Morand","CP#62 completed","RFC 7077 (was draft-ietf-netext-update-notifications)",57,29,"-",null,"2012-09-03","2013-11-28"]
[5700,460024,"Study on Non Voice Emergency Services","FS_NOVES",1,"Rel-11","S1","2009-12-10","2011-09-21",1,"SP-090897","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed. Spin-off Feature UID_500030 Non Voice Emergency Services (NOVES) ",22.870999999999999,46,24,null,null,"2009-12-06","2011-08-24"]
[5701,480033,"Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX","FS_VINE",1,"Rel-11","S1,S2","2010-09-23","2011-03-23",1,"SP-100411","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices",22.809000000000001,48,25,null,null,"2010-06-06","2011-06-06"]
[5704,440047,"Study on Policy solutions and enhancements","FS_PP",1,"Rel-11","S2,S1","2009-06-12","2011-06-10",1,"SP-090895","-","AT&T","farooq.bari@att.com","SP#52 completed. 3/3/15: start and finish dates corrected (was start on Jan-00, ends on Jan-02)",23.812999999999999,44,23,null,null,"2009-05-31","2015-03-03"]
[5708,380084,"Study on UTRAN key management enhancements","FS_UKM",1,"Rel-11","S3","2007-12-20","2012-03-07",1,"SP-090283","-","Ericsson","karl.norrman@ericsson.com","SP#55 completed",33.859000000000002,38,21,null,null,"2007-12-20","2012-11-20"]
[5711,480047,"Study on Management of Converged Networks","FS_ManCon",1,"Rel-11","S5","2010-06-10","2012-09-12",1,"SP-100377","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@nsn.com)","SP#57 completed. TR 32.833v200 for Approval",32.832999999999998,48,25,null,null,"2010-05-26","2012-08-30"]
[5714,480015,"Study on impacts on UE-Core Network signalling from Energy Saving","FS_UE-CN_ES",1,"Rel-11","C1","2010-06-04","2011-06-03",1,"CP-100330","-","NEC","gottfried.punz@nw.neclab.eu ","CP#52 completed. Linked to SA5 UID_430044 (FS_OAM-ESM) & UID_470037 (OAM-ES), RAN3 UID_470015 (FS_Energy_LTE), RAN1 UID_460016 (FS_Energy_UMTS)",24.826000000000001,48,25,null,null,"2010-05-29","2011-05-23"]
[5718,480028,"Study on Signalling and procedure for interference avoidance for in-device coexistence","FS_SPIA_IDC",1,"Rel-11","R2,R4","2010-06-04","2011-09-16",1,"RP-100671","RP-111057","China Mobile","Zhenping Hu (huzhenping@chinamobile.com)","RP#53 completed. Studied coexistence scenario of LTE and Industrial, Scientific and Medical (ISM) Radio within the same device working in adjacent frequencies","LTE 36.816",48,25,null,null,"2010-06-01","2011-09-12"]
[5721,510039,"Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","FS_LTE_TDD_eIMTA",1,"Rel-11","R1,R4","2011-03-22","2012-06-15",1,"RP-110450","RP-120587","CATT","Zukang Shen (shenzukang@catt.cn)","RP#56 completed. TR 36.828 for Information and Approval","LTE 36.828",51,26,null,null,"2011-03-21","2012-06-09"]
[5724,550022,"Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology","FS_LTE_OTA",1,"Rel-11","R4","2012-03-05","2012-09-07",1,"RP-120412","RP-121083","CATR","Xudong An (anxudong@emcite.com)","RP#57 completed","LTE 25.914, New 37.902",55,28,null,null,"2012-02-23","2012-09-03"]
[5725,430020,"Study on Measurement of Radiated Performance for MIMO and multi-antenna reception for HSPA and LTE terminals","FS_HSPA_LTE_measRP_MIMO_multi-antenna",1,"Rel-11","R4","2009-03-06","2012-03-02",1,"RP-111754","RP-120154","Vodafone","Tim.frost@vodafone.com","RP#55 completed. TR 37.976 v200 for Approval","UTRA, LTE 37.976",43,22,null,null,"2009-03-06","2012-02-23"]
[5728,500002,"Study on UE Application Layer Data Throughput Performance","FS_UE_App_Data_Perf",1,"Rel-11","R5,R4","2010-09-16","2011-09-16",1,"RP-101422","RP-111543","Spirent","ron.borsato@spirent.com","RP#54 completed","UTRA, LTE 37.901",50,26,null,null,"2010-12-08","2011-11-29"]
[5732,500014,"Study on Uplink MIMO","FS_UTRA_UL_MIMO",1,"Rel-11","R1","2010-12-10","2011-09-16",1,"RP-101432","RP-111048","Qualcomm","Sharad Sambhwani","RP#53 completed (1-step Approval)","UTRA 25.871",50,26,null,null,"2010-12-08","2011-09-02"]
[5735,540026,"Study on HSPA feedback and signalling efficiency enhancements for LCR TDD","FS_LCRTDD_HSPAenh",1,"Rel-11","R1","2011-12-07","2012-09-07",1,"RP-111766","RP-121079","TD Tech","limei.wei@td-tech.com","RP#57 completed. TR 25.874 v100 for Information & Approval","UTRA 25.874",54,28,null,null,"2011-12-07","2012-06-09"]
[5738,390073,"Enhancements for Multimedia Priority Service","eMPS",1,"Rel-10","S1,S2,C4,C3,C1","2006-03-13","2011-03-18",1,"SP-080051","-","Telcordia","jgarraha@telcordia.com","CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044)","-",39,21,null,null,"2003-03-28","2011-03-01"]
[5742,460429,"      Stage 2 on eMPS for EPS Bearer Service","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002, 23.203, 23.221, 23.228, 23.272, 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[5745,490008,"   Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",2,"Rel-10","C4,C3,C1","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","Stage 3",49,25,null,null,"2010-09-01","2010-12-09"]
[5748,490308,"      CT1 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C1","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","24.008, 24.229, 24.301",49,25,null,null,"2010-09-01","2011-02-28"]
[5749,410030,"Network Improvements for Machine-Type Communications","NIMTC",1,"Rel-10","S1,S2,S5,C1,C4,C6,G2,R2,R3,R5,G3new","2008-09-18","2013-11-22",1,"SP-100863","-","KPN","toon.norp@tno.nl","Triggered by Rel-8 UID_7027 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) TR 22.868","-",41,21,null,null,"2008-09-15","2011-02-28"]
[5752,490037,"   Stage 2 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S2","2010-08-30","2010-09-23",1,"SP-100863","-","Samsung","erik.guttman@partner.samsung.com","SP#49 completed","23.060, 23.236, 23.401",45,23,null,null,"2009-09-21","2010-12-13"]
[5756,480105,"      CT1 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C1","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","23.122, 24.008, 24.301, New 24.368",48,25,null,null,"2010-05-26","2011-06-01"]
[5759,510005,"      CT6 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C6","2011-03-18","2011-06-03",1,"-","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#52 completed",31.102,51,26,null,null,"2011-03-10","2011-05-18"]
[5762,490024,"   RAN mechanisms to avoid CN overload due to Machine-Type Communications","NIMTC-RAN_overload",2,"Rel-10","R2,R3","2010-09-17","2011-03-18",1,"RP-101026","RP-110063","Huawei","Jeff Gao (gaoyq@huawei.com)","RP#51 completed","UTRA, LTE 25.331, 25.413, 36.331, 36.413",49,25,null,null,"2010-09-20","2011-03-14"]
[5766,500004,"   CT aspects of Multi Access PDN Connectivity","MAPCON-St3",2,"Rel-10","C4,C1,C3","2010-11-15","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed","-",50,26,null,null,"2010-10-25","2010-12-09"]
[5769,500304,"      CT3 aspects of Multi Access PDN Connectivity","MAPCON-St3",3,"Rel-10","C3","2010-11-15","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed",29.215,50,26,null,null,"2010-10-25","2011-03-01"]
[5770,440052,"IMS Service Continuity – Inter Device Transfer enhancements","IMS_SC_eIDT",1,"Rel-10","S1,S2,C1,IETF","2009-06-04","2012-12-07",1,"SP-090452","-","Huawei","Amar Deol (adeol@huawei.com)","CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements","-",44,23,null,null,"2009-05-25","2010-03-09"]
[{"$f":"A5773+1","v":5773},470001,"   Stage 3 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-110285","-","Huawei","georg.mayer@huawei.com ","CP#51 completed. WID updated CP-100334=>CP-110285","24.216, 24.229, 24.237, new (24.837, 24.337)",47,24,null,null,"2010-03-17","2011-03-17"]
[5776,450031,"   Stage 1 for CPM-SMS","CPM-SMS",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-090615","-","China Mobile","Qing Huang","SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C)",22.34,45,23,null,null,"2009-09-08","2010-03-09"]
[5780,450034,"   Stage 1 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","S1","2009-09-24","2009-09-24",1,"SP-090493","-","Deutsche Telekom","Kurt Bischinger","SP#45 completed","22.173 CR#0056r1",45,23,null,null,"2009-09-08","2010-10-01"]
[5783,450035,"Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",1,"Rel-10","S2,S1,S3,S5,C4,C1","2009-09-24","2011-03-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","TSG#51 completed. Updated WID SP-100696=>SP-110131. SP#49 Stage 2 & Security completed. UID_400035 Enhanced Home NodeB/eNodeB (EHNB) formerly covered Local IP Access to Internet and Local access to Home Network from the Home NodeB/eNodeB","-",45,23,null,null,"2009-09-08","2010-12-13"]
[5786,450039,"   Security for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S3","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, Qualcomm","Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com)","SP#49 completed","33.102, 33.107, 33.108, 33.320, 33.401",45,23,null,null,"2009-09-08","2010-07-23"]
[5790,450338,"      Stage 2 for Local IP Access","LIPA",3,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#49 completed (has impacts to RAN)","23.060, 23.401",45,23,null,null,"2009-09-08","2010-09-06"]
[5793,480208,"         CT1 part of Stage 3 for Local IP Access","LIPA",4,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","24.008, 24.301",48,25,null,null,"2010-05-26","2011-02-28"]
[5794,450038,"   Stage 2/3 for SIPTO for macro networks","SIPTO",2,"Rel-10","S2,C4,C1","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","-","-",45,23,null,null,"2009-09-08","2010-12-01"]
[5797,480107,"         CT4 part of Stage 3 for SIPTO for macro networks","SIPTO",4,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","23.003, 23.008, 29.002, 29.272, 29.303",48,25,null,null,"2010-05-26","2011-03-08"]
[5800,450042,"   Stage 1 for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S1","2009-09-24","2009-12-10",1,"SP-100089","-","Qualcomm","David Williams (dwilliam@qualcomm.com)","SP#46 completed",22.277999999999999,45,23,null,null,"2009-09-08","2010-10-01"]
[5804,480109,"      CT1 part of Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",3,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","24.008, 24.301, 24.302, 24.303, 24.312, 24.327",48,25,null,null,"2010-05-26","2011-02-28"]
[5807,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[5811,490007,"   CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",2,"Rel-10","C4,C3,C1","2009-07-15","2012-09-07",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed","Stage 2/3 ",49,25,null,null,"2010-09-01","2011-03-09"]
[5814,490207,"      CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed","29.162, 29.163, 29.213, 29.235, 29.292",49,25,null,null,"2010-09-01","2011-05-17"]
[5817,450153,"   Stage 1 of Extended H(e)NB features","EHNBF",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-100407","-","NEC","joerg.swetina@neclab.eu","SP#47 completed",22.22,45,23,null,null,"2009-09-08","2010-06-08"]
[5818,420034,"   IMS aspects of Architecture for Home NodeB","EHNB-IMS",2,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080799","-","Alcatel-Lucent","Nicolas Drevon","SP#47 completed. Chosen solution has no normative impacts","New 23.832",42,22,null,null,"2008-12-09","2010-02-26"]
[5821,460128,"   Stage 2 for Optimal Media Routing","OMR",2,"Rel-10","S2","2010-03-25","2010-03-25",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","SP#47 completed",23.228000000000002,46,24,null,null,"2009-12-06","2010-02-26"]
[5825,480310,"      Deleted - CT4 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134","-",48,25,"CP-51","PCG-26","2010-05-26","2011-03-10"]
[5827,470026,"IMS Emergency Session Enhancements","IESE",1,"Rel-10","S1,S2,C1","2010-03-25","2011-06-03",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","CP#52 completed. SP#49 completed. Source of external requirements: ETSI TISPAN TS 181.019 (Business Communication Requirements)","-",47,24,null,null,"2010-03-10","2011-05-23"]
[5830,500005,"   Stage 3 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-100880","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","CP#52 completed",24.228999999999999,50,26,null,null,"2010-10-25","2011-05-23"]
[5834,490109,"      CT4 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C4","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed","23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303",49,25,null,null,"2010-09-01","2011-03-18"]
[{"$f":"A5837+1","v":5837},500006,"Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST",1,"Rel-10","S2,C3","2010-10-12","2011-03-18",1,"SP-110196","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user","-",50,26,null,null,"2010-11-26","2011-03-19"]
[5840,470029,"Lawful Interception in the 3GPP Rel-10","LI10",1,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106 (LI requirements), 33.107 (LI architecture and functions), 33.108 (Handover interface for LI)",47,24,null,null,"2010-02-23","2011-03-12"]
[5841,470129,"   LI for CAT (Customer Alerting Tones)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5844,470429,"   LI for VCC (Voice Call Continuity)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5847,470729,"   LI for MBMS enhancements","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5851,470134,"   HTTP-based Streaming and Download Services in 3GPP","HTTP_SDS",2,"Rel-10","S4","2010-03-25","2011-06-08",1,"SP-100032","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#52 completed","26.234, 26.244, 26.346, new 26.247",47,24,null,null,"2010-03-10","2011-05-26"]
[5854,480041,"Enhancements and Addition of Audio Tests to 26.131 and 26.132","EAAT",1,"Rel-10","S4","2010-06-10","2011-06-08",1,"SP-100306","-","Vodafone","ramin.afchar@vodafone.com","SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec","26.131, 26.132",48,25,null,null,"2010-05-28","2011-05-17"]
[5858,460033,"      Common RAT Network Resource Model (NRM)","RAT_NRM_common",3,"Rel-10","S5","2009-12-10","2011-06-08",1,"SP-100293","-","Ericsson","robert.petersen@ericsson.com ","SP#52 completed. Share equipment btw several RATs (RET,TMA,repeaters) to reduce costs. With existing modelling is difficult to see that several cells are affected when an antenna tilt is changed etc","32.616, 32.642, 32.646, 32.652, 32.656, 32.762, 32.766 new (32.791, 32.792, 32.796)",46,24,null,null,"2009-12-01","2011-05-16"]
[5861,480042,"      IRP Overview, Profiles & Usage Guide","OAM-NIM-IRP_OPU",3,"Rel-10","S5","2010-06-10","2011-06-08",1,"SP-110277","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@NSN.com)","SP#52 completed. Updated WID SP-100777=>SP-110277","new 32.103",48,25,null,null,"2010-05-26","2011-06-06"]
[5864,460034,"   Rel-10 Self-Organizing Networks (SON) - OAM aspects","OAM10-SON",2,"Rel-10","S5","2009-12-10","2011-06-08",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[5865,460035,"      SON Self-optimization management continuation","LTE-SON-OAM_SO",3,"Rel-10","S5","2009-12-10","2011-06-08",1,"SP-110130","-","Huawei","Lan Zou (zlan@huawei.com)","SP#52 completed. Cont'd Rel-9 SON self-optimization management UID_390007","32.425, 32.521, 32.522, 32.526, 32.762, 32.766",46,24,null,null,"2009-12-01","2011-05-13"]
[5868,470038,"   Rel-10 Subscription Management (SuM) evolution","OAM10-SuM",2,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100086","-","Ericsson","leo.yang@ericsson.com","SP#51 completed","32.172, 32.175, 32.176",47,24,null,null,"2010-03-23","2011-03-09"]
[5872,470042,"      Management of UE based network performance measurements","OAM-PM-UE",3,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"SP-100612","-","Huawei, Nokia Siemens Networks, Ericsson","Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com","SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE)","-",47,24,null,null,"2010-02-12","2011-03-22"]
[5875,470043,"      3G HNB and LTE HeNB Subsystem performance measurements","OAM-PM-HeNS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100081","-","China Mobile","Chen Gang (chengang@chinamobile.com)","SP#51 completed","32.582, 32.592, new (32.452, 32.453)",47,24,null,null,"2010-03-08","2011-03-09"]
[5878,470046,"Advice of Charge (AoC) service support enhancements","eAoC",1,"Rel-10","S5,C1","2010-03-25","2011-06-03",1,"SP-100080","-","Deutsche Telekom","matthias.seibel@telekom.de","CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work","-",47,24,null,null,"2010-03-23","2011-05-23"]
[5882,480012,"Enhanced User Data Convergence (UDC) Model","eUDC",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100295","-","China Mobile","Lan Sizhong (lansizhong@chinamobile.com)","CP#51 completed. Specify CRUD (Create/Read/Update/Delete) operations based on SOAP protocol, which may be used by the applications having no high real-time requirement to the data access operations",29.335000000000001,48,25,null,null,"2010-05-26","2011-02-28"]
[5885,561001,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6794)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2013-03-01",1,"CP-100326","-","Lionel Morand","Lionel Morand","CP#59 completed AUTH 48 RFC-to-be-6794","RFC 6794 (was draft-ietf-sip-session-policy-framework)",56,29,null,null,"2012-04-20","2013-02-21"]
[5888,490011,"AT Commands for USIM Application Toolkit (USAT)","AT_UICC",1,"Rel-10","C1","2010-09-17","2011-03-18",1,"CP-100646","-","ST-Ericsson","magnus.mk.karlsson@stericsson.com ","CP#51 completed",27.007000000000001,49,25,null,null,"2010-05-29","2011-02-14"]
[5889,490012,"Communication Control for IMS by USIM (Stage 3)","CC_IMS_USIM",1,"Rel-10","C6","2010-09-17","2011-03-18",1,"CP-100647","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed. Stage 1 in TS 22.038 USAT service description. Linked to CT6's UID_1273 Rel-5 BB Provisioning of IP-based multimedia services (24.229, 31.103) and UID_390021 Rel-8 BB CT6 aspects of SAE (31.102, 31.111)","31.102, 31.103, 31.111",49,25,null,null,"2010-09-06","2011-03-03"]
[5892,500008,"USAT using AT Commands","USAT_AT",1,"Rel-10","C6","2010-12-10","2011-03-18",1,"CP-100884","-","Giesecke & Devrient","enric.fort@gi-de.com ","CP#51 completed. Stage 3 based on SA1 22.038CR#37r1 (Make USAT proactive capability reqs applicable to ME as a whole without regard to any particular configuration¦e.g. a modem connected to an external display)","Stage 3 31.102, 31.111",50,26,null,null,"2010-11-28","2011-03-03"]
[5896,521003,"   (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809)","eSRVCC",2,"Rel-10","C1-IETF","2010-12-10","2012-12-07",1,"CP-100881","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",52,27,null,null,"2011-06-20","2013-02-21"]
[5899,570005,"   Conformance test aspects SRVCC in alerting phase","aSRVCC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-03-01",1,"RP-121700","RP-130042","NTT DoCoMo","Takao.Shimizu.rp@nttdocomo.com","RP#59 completed","36.523-1, 36.523-2, 36.523-3, 34.229-1, 34.229-2, 34.229-3",57,29,null,null,"2012-09-05","2013-02-27"]
[5902,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212, 29.213, 29.214, 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[5906,510108,"EPC Node Restoration with Idle mode Signalling Reduction (ISR) activated","EPC_NR_ISR",1,"Rel-10","C4","2011-03-16","2011-06-03",1,"CP-110287","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#52 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014","Stage 2/3: 23.007, 29.274",51,26,null,null,"2011-02-22","2011-05-17"]
[5909,510110,"   CT6 part of UICC access to IMS Specification","IMS-UICC-S",2,"Rel-10","C6","2011-03-16","2011-03-18",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed","31.102, 31.103, 31.111",51,26,null,null,"2011-03-03","2011-03-10"]
[5912,440021,"CN aspects of Local Call Local Switch","LCLS-CN",1,"Rel-10","C4","2009-05-29","2011-03-18",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","GERAN Stage 2/3",44,23,null,null,"2009-05-13","2010-12-09"]
[5913,440022,"   TR on CN aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C4","2009-05-29","2010-09-16",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#49 completed","new 23.889",44,23,null,null,"2009-05-13","2010-12-09"]
[5916,440024,"   Deleted - CT1 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C1","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT1 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[5920,480202,"   TIGHTER Performance Requirements","TIGHTER",2,"Rel-10","G1,G2","2010-09-03","2011-05-20",1,"GP-101084","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#50 completed","45.005, 45.015",46,25,null,null,"2010-05-27","2011-05-21"]
[5923,490101,"   Stage 2 for Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",2,"Rel-10","S2","2010-05-21","2010-12-16",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","SP#50 completed",23.251000000000001,47,25,null,null,"2010-05-27","2010-11-30"]
[5926,490002,"Enhancements of Iur-g interface","eIurg",1,"Rel-10","G2,R3","2010-09-03","2011-06-03",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#47 approved WID","GERAN,UTRA",47,25,null,null,"2010-09-05","2011-05-26"]
[5930,450019,"1.28 Mcps TDD Multi-carrier HSUPA","TDD_MC_HSUPA",1,"Rel-10","R1,R2,R3,R4","2009-09-18","2010-12-10",1,"RP-090990","RP-101079","CATR","Aihui Song (songaihui@mail.ritt.com.cn)","RP#50 completed","UTRA 25.102, 25.105, 25.123, 25.221, 25.222, 25.223, 25.224, 25.225, 25.306, 25.319, 25.321, 25.331, 25.423, 25.427, 25.433",45,23,null,null,"2009-09-15","2010-12-03"]
[5933,460214,"   Perf. part: 1.28Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF-Perf",2,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","RP-101081","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. TR 25.968 v100 for Approval","25.142, new 25.968",46,24,null,null,"2009-11-30","2010-12-03"]
[5934,470012,"Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD","MUMIMO_LCR_TDD",1,"Rel-10","R1,R2,R3,R4","2010-03-19","2011-06-03",1,"RP-100347","-","CATT","Yanping Xing (xingyanping@datangmobile.cn)","RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2010-03-23"]
[5937,450027,"AGNSS Minimum Performance for UTRAN","AGNSSPerf_UTRAN",1,"Rel-10","R4,R5","2009-09-18","2011-09-16",1,"RP-100363","-","Thales","Michel.monnerat@thalesaleniaspace.com","RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures)","UTRA",45,23,null,null,"2009-09-15","2010-12-08"]
[5940,460005,"Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN","LCS_UMTS_RFPMT",1,"Rel-10","R2,R3","2009-12-04","2011-03-18",1,"RP-091427","RP-110048","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907)","UTRA",46,24,null,null,"2009-11-30","2011-03-11"]
[5944,460215,"   Perf. part: Four carrier HSDPA","4C_HSDPA-Perf",2,"Rel-10","R4","2009-12-04","2011-09-16",1,"RP-100991","RP-110986","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#53 completed","25.101, 25.104, 25.133, 25.141",46,24,null,null,"2009-11-30","2011-09-12"]
[5947,470113,"   Core part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD-Core",2,"Rel-10","R4","2010-03-19","2010-06-04",1,"RP-100168","RP-100454","TD Tech","dafei.wang@td-tech.com","RP#48 completed",25.102,47,24,null,null,"2010-03-19","2010-06-01"]
[5950,480120,"   Core part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-Core",2,"Rel-10","R3,R2","2010-06-04","2011-06-03",1,"RP-100688","RP-110522","ZTE","Zhai.hengxing@zte.com.cn","RP#52 completed","25.331, 25.413, 25.423, new 25.484 (Stage 2)",48,25,null,null,"2010-06-03","2011-05-31"]
[5954,480221,"   Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Perf",2,"Rel-10","R4,R2","2010-06-04","2010-09-17",1,"RP-100657","RP-100759","AT&T","Vince Spatafora (vs5785@att.com)","RP#49 stopped (Reason: no need for Performance work)","25.101, 25.104, 25.141, 25.317",48,25,"RP-49","PCG-25","2010-06-03","2010-09-09"]
[5957,480122,"   Perf. part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-Perf",2,"Rel-10","R4","2010-06-04","2011-06-03",1,"RP-100993","RP-110525","Qualcomm","Heechoon Lee","RP#52 completed","25.101, 25.141",48,25,null,null,"2010-06-03","2011-05-27"]
[5958,510017,"   Test part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-UEConTest",2,"Rel-10","R5","2011-03-18","2012-03-02",1,"RP-110244","RP-120042","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#55 completed","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",51,26,null,null,"2011-03-10","2012-02-23"]
[5961,460107,"   Core part: Carrier Aggregation for LTE","LTE_CA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-06-03",1,"RP-100661","RP-110535","Nokia","lars.e.lindh@nokia.com","RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, 37.104, new RAN4 (36.807, 36.808)",46,24,null,null,"2009-11-30","2012-06-07"]
[5964,460008,"Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO",1,"Rel-10","R1,R2,R4,R5","2009-12-04","2013-06-14",1,"RP-100196","-","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","-","LTE",46,24,null,null,"2009-11-30","2010-03-19"]
[5968,460009,"Uplink Multiple Antenna Transmission for LTE","LTE_UL_MIMO",1,"Rel-10","R1,R2,R4,R5","2000-01-03","2013-03-01",1,"RP-100959","-","Huawei","Mattias.wennstrom@huawei.com","-","LTE",46,24,null,null,"2009-11-30","2011-09-12"]
[5971,540007,"   Test part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-UEConTest",2,"Rel-10","R5","2011-12-02","2013-03-01",1,"RP-111614","RP-130038","Huawei","Zhang Xin (suzanna.zhang@huawei.com)","RP#59 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2013-02-27"]
[5975,520020,"   Stage 2 for Relays for LTE","LTE_Relay",2,"Rel-10","S2","2011-06-06","2011-06-08",1,"-","-","Vodafone","chris.pudney@vodafone.com","SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview",23.401,52,27,null,null,"2011-06-06","2011-06-06"]
[5978,500138,"      Security for LTE Relay Nodes (Stage 2)","LTE_Relay-Sec",3,"Rel-10","S3","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","SP#51 completed (impacting Stage 3 in CT and RAN)","33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413",50,26,null,null,"2010-11-25","2011-02-14"]
[5981,470007,"Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE",1,"Rel-10","R1,R2,R3,R4,R5","2010-03-19","2014-06-13",1,"RP-100383","-","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#56 completed","LTE",47,24,null,null,"2010-03-19","2011-03-14"]
[5982,470107,"   Core part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-Core",2,"Rel-10","R1,R2,R3,R4","2010-03-19","2011-06-03",1,"RP-100383","RP-110543","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#52 completed","36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423",47,24,null,null,"2010-03-19","2011-05-27"]
[5985,470008,"LTE TDD in 2600MHz for US","LTE_TDD_2600_US",1,"Rel-10","R4,R2,R3,R5","2010-03-19","2010-12-10",1,"RP-101003","-","Clearwire","michael.hart@clearwire.com","RP#50 Testing completed. RP#49 Core+Perf completed","LTE",47,24,null,null,"2010-03-19","2010-12-03"]
[5988,480019,"   UE conformance test part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-UEConTest",2,"Rel-10","R5","2010-06-04","2010-12-10",1,"RP-100615","RP-101071","Clearwire","michael.hart@clearwire.com","RP#50 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",48,25,null,null,"2010-06-01","2010-12-03"]
[5992,520012,"   Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-06-07","2011-12-09",1,"RP-110623","RP-111444","DBSD","Mariam.Sorond@ico.com","RP#54 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",52,27,null,null,"2011-05-23","2011-11-29"]
[5995,470210,"   Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-101284","RP-110548","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#52 completed","34.121-1, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.521-1, 36.813",47,24,null,null,"2010-03-19","2011-05-24"]
[5999,480027,"Further enhancements to MBMS for LTE","MBMS_LTE_enh",1,"Rel-10","R2,R3,R5","2010-06-04","2012-03-02",1,"RP-101244","-","Huawei","Ms Zhao Junhui (zhaojh@huawei.com)","RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives","LTE",48,25,null,null,"2010-06-04","2011-03-14"]
[6002,380173,"UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",1,"Rel-10","R4,R2,R3,R5","2007-11-30","2013-06-14",1,"RP-091380","-","Ericsson","johan.skold@ericsson.com","-","UTRA, LTE",38,21,null,null,"2007-12-17","2013-06-03"]
[6005,420014,"   Conformance Test Aspects – UMTS 3500","RInImp-UEConTest_UMTS3500",2,"Rel-10","R5","2008-12-05","2012-06-15",1,"RP-110386","RP-120450","Ericsson","fredrik.sundstrom@ericsson.com","RP#56 completed","34.108, 34.121-1, 34.121-2",42,22,null,null,"2008-11-27","2012-06-05"]
[6006,460003,"Minimization of Drive Tests for E-UTRAN and UTRAN","MDT_UMTSLTE",1,"Rel-10","R2,R4,R3,R5","2009-12-04","2013-03-01",1,"RP-100360","-","Nokia Siemens Networks","malgorzata.tomala@nsn.com","Triggered by UID_430021 TR 36.805 (Study on Minimization of drive-tests in NGN)","UTRA, LTE",46,24,null,null,"2009-11-30","2013-02-27"]
[6009,470005,"HNB and HeNB Mobility Enhancements","HNB_HENB_mob_enh",1,"Rel-10","R3,R2,R5","2010-03-19","2012-12-07",1,"RP-110183","-","Alcatel-Lucent","Martin,Warner@alcatel-lucent.com","-","UTRA, LTE",47,24,null,null,"2010-03-19","2011-04-08"]
[6012,480024,"Expanded 1900 MHz Band for UTRA and LTE","E1900",1,"Rel-10","R4,R2,R5","2010-06-04","2012-09-07",1,"RP-100676","-","Sprint","nick.j.baustert@sprint.com","Expand UTRA and E-UTRA band 2 to include frequencies between 1910 – 1915 MHz and 1990-1995 MHz (US FCC allocation)","UTRA, LTE",48,25,null,null,"2010-06-04","2012-09-04"]
[6016,480025,"Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments","MSR_NC",1,"Rel-10","R4,G1","2010-06-04","2011-11-25",1,"RP-101402","-","Ericsson","johan.skold@ericsson.com","-","UTRA, LTE, GERAN",48,25,null,null,"2010-06-04","2011-09-12"]
[6019,490004,"   GERAN part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-GERAN",2,"Rel-10","G1","2010-09-03","2011-11-25",1,"GP-101618","-","Ericsson","mats.y.samuelsson@ericsson.com ","-","-",47,25,null,null,"2010-09-05","2011-05-21"]
[6023,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[6026,350014,"Deleted - Registration in Densely-populated area (RED)","RED",1,"Rel-10","S1","2007-03-12","2009-09-24",1,"SP-070133","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned","-",35,18,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[{"$f":"A6029+1","v":6029},380062,"Deleted - Network Selection for non-3GPP Access","N3GtoNSP",1,"Rel-10","S1,C6","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned","-",38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6030,380162,"   Deleted - Stage 1 for N3GtoNSP","N3GtoNSP",2,"Rel-10","S1","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",22.010999999999999,38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6033,420026,"   Deleted - Stage 2 for GTPchaining","GTPchaining",2,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080798","-","Huawei","Haining Wang (wanghaining@huawei.com)","SP#47 work stopped",23.402000000000001,42,22,"SP-47","PCG-24","2008-12-05","2010-03-07"]
[6037,460110,"   Deleted - Core part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-Core",2,"Rel-10","R4","2009-12-04","2011-06-03",1,"RP-091432","RP-110539","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped at 55% (lack of contributions)",36.100999999999999,46,24,"RP-52","PCG-27","2009-11-30","2011-03-16"]
[6040,460112,"   Deleted - Core part: Latency reductions for LTE","LTE_LATRED-Core",2,"Rel-10","R2,R1","2009-12-04","2010-12-10",1,"RP-091449","RP-101112","Ericsson","henrik.enbuske@ericsson.com","RP#50 work stopped (RP-101266)","36.213, 36.300, 36.306, 36.321, 36.331",46,24,"RP-50","PCG-26","2009-11-30","2010-12-08"]
[6043,0,"Release 10 Studies","-",1,"Rel-10","CP,GP,RP,SP","2009-03-12","2009-03-12",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6047,380083,"Study on advanced requirements for IP interconnect ","FS_IPXS",1,"Rel-10","S1","2007-12-04","2009-12-10",1,"SP-070878","-","Telefónica O2","chris.friel@O2.com","SP#46 completed. Linked to Rel-8 Feature UID_380060 IP Interconnection of Services (IPinterc). Spin-off Feature Rel-11 UID_470051 Advanced IP Interconnection of Services",22.893000000000001,38,21,null,null,"2007-12-20","2010-08-11"]
[6050,430030,"Study on Haptic Services","FS_Haptics",1,"Rel-10","S1","2009-03-12","2010-03-25",1,"SP-090664","-","SK Telecom","jinhan.song@sktelecom.com ","SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses",22.986999999999998,43,22,null,null,"2009-02-12","2010-08-11"]
[6053,440049,"Study on Single Radio Voice Call Continuity enhancements","FS_eSRVCC",1,"Rel-10","S2","2009-06-04","2010-09-23",1,"SP-090363","-","China Mobile","Hou zhiqiang (houzhiqiang@chinamobile.com), Jiang Yi (jiangyi@chinamobile.com)","SP#49 completed (Conclusion: select the SIP anchoring based solution for normative work CR (TEI10) introducing and completing stage-2). Analyzed performance of Rel-8 SRVCC solution from E-UTRAN/HSPA to UTRAN/GERAN",23.856000000000002,44,23,null,null,"2009-05-31","2010-09-06"]
[6054,470048,"Study on Single Radio Video Call Continuity for 3G-CS","FS_vSRVCC",1,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100168","-","Samsung","Haris Zisimopoulos (haris.z@samsung.com)","SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user",23.885999999999999,47,24,null,null,"2010-03-10","2010-09-15"]
[6057,480044,"Study on Improved Video Coding Support","FS_IVCS",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100304","-","Nokia, ETRI","imed.bouazizi@nokia.com, jaihyung@etri.re.kr","SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039)",26.904,48,25,null,null,"2010-05-28","2011-02-18"]
[6061,460037,"Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model","FS_3GNRM_TMFSID",1,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-090759","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#51 completed",32.828000000000003,46,24,null,null,"2009-12-01","2011-03-09"]
[6064,480046,"Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM","FS_3G_TMF_PM",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100291","-","Alcatel-Lucent","Padma.Sudarsan@alcatel-lucent.com ","SP#51 completed",32.831000000000003,48,25,null,null,"2010-05-26","2011-03-22"]
[6066,480016,"Study on User Data Convergence (UDC) evolution ","FS_UDCe",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100296","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model",23.844999999999999,48,25,null,null,"2010-05-26","2011-02-28"]
[6070,470015,"Study on Potential solutions for energy saving for E-UTRAN","FS_Energy_LTE",1,"Rel-10","R3,R2","2010-02-02","2011-06-03",1,"RP-100674","RP-110597","China Mobile","Yang Ning (yangning@chinamobile.com)","RP#52 completed","LTE 36.927",47,24,null,null,"2010-03-19","2011-06-02"]
[6073,410042,"Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services","FS_eIMS_IBCF",1,"Rel-10","S2","2008-09-18","2010-12-15",1,"SP-090809","-","Starent Networks","Rajat Ghai (rghai@starentnetworks.com)","SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS)",23.847999999999999,41,21,"SP-50","PCG-26","2008-09-15","2010-12-13"]
[6074,440050,"Deleted - Study on EPC Charging enhancement","FS_EPCcharg",1,"Rel-10","S5","2009-06-04","2010-03-25",1,"SP-090318","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#47 work stopped. Issue covered by Rel-10 UID_460039 Charging for LIPA_SIPTO and UID_4700xy Charging for IFOM ","-",44,23,"SP-47","PCG-24","2009-05-18","2009-07-06"]
[6077,400035,"Enhanced Home NodeB / eNodeB","EHNB",1,"Rel-9","S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP","2008-06-05","2011-12-09",1,"SP-090214","-","T-Mobile","michael.kurz@t-mobile.at ","RP#54 Testing completed","UTRA, LTE",40,21,null,null,"2007-12-13","2011-11-29"]
[6080,420035,"   Security aspects of Enhanced Home NodeB / eNodeB","EHNB-Sec",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080879","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#46 completed","New 33.320",42,22,null,null,"2008-12-09","2009-12-07"]
[6084,430012,"   3G HNB and LTE HeNB OAM&P Type 1 Interface","HNB_eHNB-OAM_Type1",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090208","-","Huawei","Zou Lan (zlan@huawei.com)","SP#47 completed","32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594)",43,22,null,null,"2009-03-09","2010-03-08"]
[6087,430005,"   LTE TDD Home eNodeB RF Requirements","HeNB-RF_TDD",2,"Rel-9","R4","2009-03-06","2010-03-19",1,"RP-091386","RP-100036","China Mobile","Nan Li (linan@chinamobile.com)","RP#47 completed","36.104, 36.141, 36.300, 36.331, 36.413, New 36.922",43,22,null,null,"2009-03-03","2010-03-16"]
[6090,490020,"   Conformance Test Aspects – Home NB enhancements for FDD","EHNB-UTRA_FDD_UEConTest",2,"Rel-9","R5","2010-09-17","2011-12-09",1,"RP-111315","RP-111679","Huawei","trica_li@huawei.com","UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367)","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-09","2011-12-07"]
[6094,370126,"   Stage 1 for VAS4SMS","VAS4SMS",2,"Rel-9","S1","2007-09-10","2008-03-12",1,"SP-070572","-","China Mobile","Wu Bin (wubin@chinamobile.com)","SP#39 completed. SP#43 Feature moved to Rel-9","new 22.142",37,19,null,null,"2007-10-02","2009-03-04"]
[6097,370027,"Definition of End-User Identity","EUI",1,"Rel-9","S1","2007-09-03","2008-12-11",1,"SP-090380","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905)","-",37,19,null,null,"2007-10-02","2010-08-05"]
[6098,410024,"   Stage 1 for Definition of End-User Identity","EUI",2,"Rel-9","S1","2007-09-03","2008-12-11",1,"SP-090380","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905)",21.905000000000001,38,21,null,null,"2007-10-02","2009-06-11"]
[6101,440041,"   Stage 3 for IMS Customized Ringing Signal (CRS) Service","CRS",2,"Rel-9","C1","2009-05-29","2009-12-03",1,"CP-090444","-","China Mobile","wangzhao","CP#48 completed","24.173, new 24.183",44,23,null,null,"2009-05-13","2010-05-28"]
[6104,440029,"   Stage 3 for Public Warning System","PWS-St3",2,"Rel-9","C1,C4","2009-05-29","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","RP#46 completed","-",44,23,null,null,"2009-05-13","2009-12-03"]
[6108,540005,"   Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE","PWS-RAN_UEConTest",2,"Rel-9","R5","2011-12-02","2012-12-07",1,"RP-111564","RP-121525","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#58 completed","36.508, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2012-12-04"]
[6111,430002,"   Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-06","2009-12-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#46 completed",23.259,43,22,null,null,"2009-03-05","2009-11-16"]
[6114,400044,"   Stage 1 for eMMTel","eMMTel",2,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080503","-","France Telecom","philippe.lottin@orange.com","SP#42 completed",22.172999999999998,40,21,null,null,"2007-12-13","2008-12-05"]
[6118,400034,"User Data Convergence (UDC)","UDC",1,"Rel-9","S1,S5,C4","2008-06-05","2010-06-10",1,"SP-080448","-","Nokia Siemens Networks","juergen.merkel@nsn.com ","SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808","-",40,21,null,null,"2007-12-13","2010-08-31"]
[6121,430003,"      User Data Convergence (UDC) Technical Realization (Stage 2)","UDC-CN",3,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","CP#47 completed","new 23.335",43,22,null,null,"2009-03-04","2010-03-09"]
[6122,450002,"      User Data Convergence (UDC) Protocol Description","UDC-CN",3,"Rel-9","C4","2009-09-18","2010-03-19",1,"CP-090516","-","China Mobile, Ericsson","Lan Si Zhong (lansizhong@chinamobile.com), emiliano.merino@ericsson.com","CP#47 completed","new 29.335",45,23,null,null,"2009-03-04","2010-03-09"]
[6125,440061,"      UDC – Common Baseline Information Model","UDC-MMAN-CBIM",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090310","-","China Mobile, Ericsson","Lan Si Zhong, Miguel Garcia","SP#47 completed","32.172, new 32.182 ",44,23,null,null,"2009-05-18","2010-03-08"]
[6128,410134,"   Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","-","-",41,21,null,null,"2008-09-15","2012-07-20"]
[6132,410035,"      Stage 2 for IMS Centralized Services","IMS_SCC-ICS",3,"Rel-9","S2","2008-09-18","2009-06-04",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","SP#44 completed. TR 23.883 for Information + Approval","23.292, new 23.883",41,21,null,null,"2008-09-15","2009-06-02"]
[6135,420020,"Service Specific Access Control in EPS","SSAC",1,"Rel-9","S1,C1,R5","2008-12-11","2012-06-15",1,"SP-080882","-","NTT DoCoMo","Frederic Thepot (thepot@docomolab-euro.com)","CP#47 completed. Triggered by TR 22.986 Study on Service Specific Access Control in EPS. As EPS is a PS-Domain only system, Domain Specific Access Control (DSAC) doesn't apply, hence SSAC allows restriction of voice and non-voice calls separately","-",42,22,null,null,"2008-12-05","2010-03-04"]
[6139,380064,"Support for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",1,"Rel-9","S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF","2000-01-03","2014-06-13",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","RP#56 completed testing. CP#47 completed. SP#48 completed","GERAN, LTE",38,21,null,null,"2007-10-02","2012-06-05"]
[6142,420022,"   Security aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS-Sec",2,"Rel-9","S3","2008-12-12","2010-06-10",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#48 completed","33.401, 33.402",42,22,null,null,"2008-12-09","2010-05-05"]
[6145,480029,"      Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS_UEConTest",3,"Rel-9","R5","2010-06-04","2012-06-15",1,"RP-100567","RP-120445","Samsung","stoyan.baev@partner.samsung.com","RP#56 completed","34.108, 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2, 34.229-3, 36.508, 36.523-1, 36.523-2, 36.523-3",48,25,null,null,"2010-06-04","2012-06-05"]
[6146,440037,"      CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC3",3,"Rel-9","C3","2009-05-29","2009-09-18",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#45 completed","29.212, 29.213, 29.214, 29.215",44,23,null,null,"2009-05-13","2009-09-09"]
[6149,470017,"   Conformance Test Aspects – Support for IMS Emergency Calls over LTE","IMS_EMER_LTE_UEConTest",2,"Rel-9","R5","2010-03-25","2010-12-10",1,"RP-100118","RP-101068","Ericsson","leif.mattisson@ericsson.com","RP#50 completed","36.508, 36.523-1, 36.523-2, 36.523-3",47,24,null,null,"2010-03-10","2010-12-08"]
[6152,460018,"      CT aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",3,"Rel-9","C1,C4,C3,IETF","2009-05-29","2014-06-13",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","-",46,24,null,null,"2009-05-13","2009-12-02"]
[6156,561003,"         (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254)","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C3-IETF","2012-04-20","2014-06-13",1,"CP-090882","-","Andrew Allen","Andrew Allen","CP#64 completed","RFC 7254 (was draft-montemurro-gsma-imei-urn)",56,29,null,null,"2012-04-20","2014-06-06"]
[6159,400048,"      Stage 2 for LCS Control Plane Solution for EPS","LCS_EPS-CPS",3,"Rel-9","S2","2008-06-05","2009-06-04",1,"SP-080445","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","SP#44 completed","23.891, 23.271, 23.401, 23.402",40,21,null,null,"2007-12-13","2009-06-01"]
[6163,470018,"   Conformance Test Aspects – Positioning Support for LTE","LCS_LTE_UEConTest",2,"Rel-9","R5","2010-03-19","2012-03-02",1,"RP-111209","RP-120034","Qualcomm","Shubhang Vora (svoral@qualcomm.com)","RP#55 completed. RP#56 TS 37.571-4 v200 for Approval","36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5)",47,24,null,null,"2010-03-17","2012-06-06"]
[6166,420023,"   Security for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#46 completed",33.246000000000002,42,22,null,null,"2008-12-09","2009-12-09"]
[6169,440026,"   CT3 aspects of MBMS support in EPS (Stage 3)","MBMS_EPS",2,"Rel-9","C3","2009-05-29","2009-12-04",1,"CP-090330","-","ZTE, China Mobile","zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com","CP#46 completed",29.061,44,23,null,null,"2009-05-13","2009-11-25"]
[6170,430007,"   MBMS support in LTE","MBMS_LTE",2,"Rel-9","R2,R3,R4","2009-03-06","2010-03-19",1,"RP-091457","RP-100033","Huawei","arnaud.meylan@huawei.com","RP#47 completed","25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445",43,22,null,null,"2009-03-10","2010-03-16"]
[6173,420040,"   Stage 2 for Access Network Discovery and Selection Function enhancements","eANDSF",2,"Rel-9","S2","2008-12-11","2009-06-04",1,"SP-080887","-","Motorola","Apostolis Salkintzis (salki@motorola.com)","SP#44 completed","23.402, 23.002",42,22,null,null,"2008-12-05","2009-06-01"]
[6176,430134,"   Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",2,"Rel-9","S2","2009-03-13","2009-06-04",1,"SP-090098","-","Samsung","erik.guttman@partner.samsung.com","SP#44 completed","23.060, 23.203, 23.401, 23.402",43,22,null,null,"2009-03-05","2009-09-08"]
[6180,450050,"   SA2 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#45 completed (CR adding support for Explicit Congestion Notification)","23.401 CR#1103r3",45,23,null,null,"2009-05-28","2009-09-21"]
[6183,521005,"   (IETF) SA4 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S4-IETF","2009-06-04","2012-09-12",1,"SP-090653","-","Lionel Morand","-","SP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",52,27,null,null,"2011-06-20","2012-09-03"]
[6187,410028,"   Stage 1 for PUCI","PUCI",2,"Rel-9","S1","2008-09-18","2008-12-11",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#42 completed",22.228000000000002,41,21,null,null,"2008-09-15","2008-12-05"]
[6190,430136,"   SA3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3","2009-03-13","2010-03-25",1,"SP-090128","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","New 33.828, 33.328",43,22,null,null,"2009-02-11","2010-03-01"]
[6193,460020,"   CN aspects of IMS Media Plane Security","MEDIASEC_CORE",2,"Rel-9","C1,C4,C3","2009-09-18","2010-06-04",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#48 completed","-",45,23,null,null,"2009-02-11","2009-12-02"]
[6194,450010,"      CT1 aspects of IMS Media Plane Security","MEDIASEC_CORE",3,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#47 completed","23.218, 24.229",45,23,null,null,"2009-02-11","2010-03-02"]
[6197,440053,"GBAPush enhancements (Generic push layer)","eGBAPush",1,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed","New 33.224",44,23,null,null,"2009-02-11","2009-09-21"]
[6201,440156,"   SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3","2009-06-04","2010-03-25",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","33.102, 33.210, 33.310, 33.401, 33.402",44,23,null,null,"2009-05-18","2010-03-01"]
[6204,440057,"128 bit encryption for GSM and GPRS","A5/4-GEA4",1,"Rel-9","S3,C1,C4,G2,G3new","2009-06-04","2009-12-10",1,"SP-090287","-","Ericsson","Karl Norrman","Allow 128 as an alternative to 64 bit keys (Stage 2/3 + Test spec)","-",44,23,null,null,"2009-05-18","2009-11-25"]
[6207,440457,"   CT4 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C4","2009-06-04","2009-12-10",1,"SP-090287","-","Ericsson","Karl Norrman","CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060","-",44,23,null,null,"2009-05-18","2009-11-16"]
[6211,420027,"Timed Graphics","TG",1,"Rel-9","S4","2008-12-11","2010-03-25",1,"SP-080683","-","Ericsson","clinton.priddle@ericsson.com","SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142)","26.114, 26.140, 26.234, 26.244, 26.245, 26.346, New 26.430",42,22,null,null,"2008-11-23","2010-02-01"]
[6214,430038,"   PSS and MBMS extensions","PMA-MBS_Ext",2,"Rel-9","S4","2009-03-12","2010-03-25",1,"SP-090262","-","Ericsson","Clinton.Priddle@ericsson.com","SP#47 completed. Extends Rel-8 UID_34043 (PSS_MBMS_OMTV) & ensures compatibility with UID_34046 (IMS_PSS_MBMS_US)","26.234, 26.346",43,22,null,null,"2009-02-02","2010-03-08"]
[6217,440051,"Syndicated Feed Reception within 3GPP environments","SFR",1,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090260","-","Ericsson","Thorsten.Lohmar@ericsson.com","SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD.","New 26.150",44,23,null,null,"2009-05-31","2009-12-07"]
[6218,450048,"Distortion Measurement Test Methods and Requirements","DTMR",1,"Rel-9","S4","2009-09-24","2010-03-25",1,"SP-090575","-","Motorola","Stephen Kendall (wcsk01@motorola.com)","SP#47 completed","26.131, 26.132",45,23,null,null,"2009-09-21","2009-12-02"]
[{"$f":"A6221+1","v":6221},420031,"      Software Management for Network Elements","OAM9-NE_SWM",3,"Rel-9","S5","2008-12-11","2010-03-25",1,"SP-080756","-","Huawei, Nokia Siemens Networks","Bidipta Das (bidipta@huawei.com), Clemens Suerbaum (clemens.suerbaum@nsn.com)","SP#47 completed","32.531, 32.532, 32.533, new 32.537",42,22,null,null,"2008-12-03","2010-03-08"]
[6225,440059,"      Enhancement of UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-06-04","2009-12-10",1,"SP-090308","-","China Mobile","liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao","SP#46 completed",32.405000000000001,44,23,null,null,"2009-05-18","2009-12-01"]
[6228,430043,"   Rel-9 Self-Organizing Networks (SON) - OAM aspects","OAM9-SON",2,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","SP#43 umbrella BB created to host OAM WIs","-",43,22,null,null,"2009-03-09","2010-02-09"]
[6231,440058,"   Rel-9 Subscription Management (SuM) evolution","OAM9-SuM",2,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090307","-","Ericsson","frode.nergard@ericsson.com","SP#48 completed","32.140, 32.141, 32.152, 32.172, 32.175",44,23,null,null,"2009-05-18","2010-05-26"]
[6235,400109,"   CT3 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications","CS-IBCF",2,"Rel-9","C3","2008-05-30","2010-03-19",1,"CP-090073","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#47 completed",29.234999999999999,40,21,null,null,"2007-09-05","2010-03-02"]
[6238,410108,"   CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","new 29.238",41,21,null,null,"2007-09-05","2009-11-16"]
[6239,410208,"   CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C3","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","29.162, 29.235",41,21,null,null,"2007-09-05","2009-11-25"]
[6242,420017,"   Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service","eCAT-SS",2,"Rel-9","C1","2008-12-05","2010-06-04",1,"CP-080796","-","China Mobile","Jiang Yi","CP#48 completed",24.181999999999999,42,22,null,null,"2008-12-04","2010-05-28"]
[6245,440019,"   CT1 aspects of Completion of IMS Restoration Procedures","eIMS_RP",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed",24.228999999999999,44,23,null,null,"2009-05-13","2010-03-02"]
[6249,521009,"   (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7329)","IMSProtoc3",2,"Rel-9","C1-IETF","2009-05-29","2014-12-05",1,"CP-090491","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed","RFC 7329 (was draft-kaplan-insipid-session-id)",52,27,null,null,"2011-06-20","2014-09-03"]
[6252,440170,"   Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3","2009-05-29","2010-06-04",1,"CP-090331","-","Orange","-","CP#48 completed",29.164999999999999,44,23,null,null,"2012-04-20","2010-05-27"]
[6255,561006,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100","draft-ietf-salud-alert-info-urns",56,29,null,null,"2012-04-20","2016-03-07"]
[6259,591002,"   Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface (avasarala-dispatch-comm-div-notification)","II-NNI",2,"Rel-9","C3-IETF","2013-03-01","2014-06-13",1,"CP-090331","-","Andrew Allen","Andrew Allen","CP#64 Draft removed from 3GPP documentation","draft-avasarala-dispatch-comm-div-notification",59,30,"SP-69",null,"2013-02-21","2014-06-06"]
[6262,460004,"3GPP IMS Conferencing Management Object (MO)","IMS_ConfMO",1,"Rel-9","C1","2009-12-03","2009-12-04",1,"-","-","-","-","CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2)","New 24.166",46,24,null,null,"2009-12-08","2010-02-09"]
[6263,470004,"In Case of Emergency (ICE) Graphics","ICE_Graphics",1,"Rel-9","C6","2010-03-17","2010-03-19",1,"CP-100178","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#47 approved WID and completed. Added capability to store ICE graphical information (picture). Linked to CT6 Rel-8 ICE Feature UID_380059 In Case of Emergency numbers storage and easy access on UICC","31.102 CR#0433",47,24,null,null,"2010-03-09","2010-03-17"]
[6266,410019,"   RF requirements for Multicarrier and Multi-RAT BS","RInImp9-RFmulti",2,"Rel-9","R4,G1","2008-11-21","2010-03-19",1,"RP-091381","-","Ericsson","Johan.skold@ericsson.com","RP#47 completed. RF requirements specification applicable to Multi-Standard Radio (MSR) Base Station with multiple carriers and/or multiple 3GPP Radio Access Technologies (RAT)","GERAN, UTRA, LTE",41,21,null,null,"2008-09-11","2010-03-16"]
[6269,420010,"   Extended UMTS/LTE 800 MHz","RInImp9-UMTSLTE800",2,"Rel-9","R4,R2,R3","2008-12-05","2008-12-05",1,"RP-080884","RP-090687","NTT DoCoMo","Shingo Suwa (suwas@nttdocomo.co.jp)","RP#45 completed","UTRA, LTE 25.101, 25.104, 25.113, 25.133, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466, new 36.800",42,22,null,null,"2008-12-04","2009-10-07"]
[6273,440006,"Rel-9 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-9","R5","2009-05-19","2010-09-17",1,"-","-","-","-","-","UTRA, LTE",44,23,null,null,"2009-05-18","2009-05-28"]
[6276,440012,"   TDD UE Over The Air (Antenna) conformance testing methodology","UEAnt_TDDTest",2,"Rel-9","R5","2009-05-30","2009-09-18",1,"RP-090621","RP-090727","CATR","Qu Yan (quyan@emcite.com)","RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head)","UTRA 34.114",44,23,null,null,"2009-05-20","2009-09-10"]
[6279,430013,"Rel-9 RAN improvements","-",1,"Rel-9","RP","2009-03-06","2010-09-08",1,"-","-","-","-","RP#47 completed","UTRA",43,22,null,null,"2009-03-06","2010-09-08"]
[6283,430018,"   Transmit Antenna Array (TxAA) extension for non-MIMO UEs","RANimp-TxAA_nonMIMO",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090013","RP-091040","Nokia","Arto Lehti (arto.lehti@nokia.com)","RP#46 completed","25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433",43,22,null,null,"2009-03-06","2009-11-26"]
[6286,490019,"   Conformance Test Aspects – Combination of DC-HSDPA with MIMO","RANimp-DC_MIMO_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-101001","RP-110510","Ericsson","leif.mattisson@ericsson.com","UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO","UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-08","2011-05-18"]
[6287,510014,"   Conformance Test Aspects – Dual-Cell HSUPA","RANimp-DC_HSUPA_UEConTest",2,"Rel-9","R5","2011-03-18","2012-12-07",1,"RP-110116","RP-121524","Ericsson","leif.mattisson@ericsson.com","RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA","UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",51,26,null,null,"2011-03-10","2012-11-28"]
[6290,430019,"   LTE Pico NodeB RF Requirements","LTEimp-Pico_eNB-RF",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-091155","RP-091045","Huawei","Liyan Yin (yinliyan@huawei.com)","RP#46 completed","36.104, 36.141, new 36.931",43,22,null,null,"2009-02-27","2010-02-08"]
[6293,420011,"Rel-9 Self-Organizing Networks (SON)","SON",1,"Rel-9","R3,R2","2009-03-06","2009-03-06",1,"RP-090162","RP-100038","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#47 completed","LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902",42,22,null,null,"2008-12-05","2010-03-10"]
[6297,420002,"Voice services over Adaptive Multi-user channels on One Slot","VAMOS",1,"Rel-9","GP,G1,G2,G3new","2008-11-21","2012-03-02",1,"GP-081949","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","Triggered by UID_50590 (MUROS) Study on Multi-User Reusing-One-Slot","-",42,22,null,null,"2008-11-23","2010-05-27"]
[6300,420005,"   VAMOS Radio Performance Requirements","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-05-20",1,"GP-081966","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#50 completed. GP#40 WID approved",45.005000000000003,40,22,null,null,"2008-11-23","2011-05-21"]
[6303,440002,"Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC)","CEBRO",1,"Rel-9","GP,C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed. GP#45 completed. GP#42 WID approved","-",42,23,null,null,"2009-05-18","2010-03-05"]
[6306,440003,"Hybrid Location","HILT",1,"Rel-9","GP","2009-05-18","2009-11-20",1,"GP-091075","-","TruePosition","Matt Ward (mward@trueposition.com)","GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT)","43.059, 48.071",42,23,null,null,"2009-05-18","2009-09-07"]
[6309,330017,"Deleted - Services Alignment and Migration","ServAl",1,"Rel-9","S1","2006-12-06","2008-09-18",1,"SP-070126","-","Telefónica O2","chris.friel@O2.com","SP#41 closed (no tangible result of this work¦no CR against TR 22.983). Triggered by Study UID_370086 (FSServAl) ","-",33,17,"SP-41","PCG-21","2006-10-06","2010-08-05"]
[6310,410001,"   Deleted - Stage 1 for ServAl","-",2,"Rel-9","S1","2006-12-06","2008-09-18",1,"SP-070126","-","Telefónica O2","chris.friel@O2.com","SP#41 closed (no tangible result of this work¦no CR against TR 22.983)",22.983000000000001,33,21,"SP-41","PCG-21","2006-10-06","2010-08-05"]
[6313,380082,"Deleted - Support of WiMAX - UMTS Mobility","WiMAX_UMTS_Mobility",1,"Rel-9","R2","2008-06-06","2009-12-25",1,"RP-070511","-","Intel","-","RP#39: No agreed WID","25.306, 25.331, 25.413",38,21,"SP-39","PCG-21","2007-12-17","2009-03-24"]
[6316,350028,"   Deleted - Functions and procedures for SAE to support LTE MBMS","SAES_Ph2",2,"Rel-9","S2","2007-06-25","2008-12-08",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. WID returned to SA2 for re-consideration & remove MBMS for EPS from Rel 8","-",35,18,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[6320,440071,"Deleted - Lawful Interception in the 3GPP Rel-9","LI9",1,"Rel-9","S3","2009-06-04","2010-03-25",1,"SP-090831","-","PIDS, Nortel","Koen Jaspers, Ronald Ryan","SP#47 stopped. WI + new topics moved to Rel-10","33.106, 33.107, 33.108",44,23,"SP-47","PCG-24","2009-06-02","2010-03-01"]
[6323,350052,"Study on CS Domain Services over EPS access","FS_CSoPS",1,"Rel-9","S2","2007-04-25","2009-03-12",1,"SP-080800","-","T-Mobile","Karl-Heinz.Nenner@T-Mobile.net","SP#43 completed. Linked to Combinational Services UID_31064, Services Alignment and Migration (ServAl) UID_330017 and 3GPP System Architecture Evolution (SAES) UID_3208",23.879000000000001,35,18,null,null,"2007-03-29","2010-08-09"]
[6327,360006,"Study on System Maintenance over Itf-N","FS_OAM-Maint-Itf-N",1,"Rel-9","S5","2007-06-07","2009-09-24",1,"SP-070306","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#45 completed",32.822000000000003,36,19,null,null,"2007-05-28","2009-09-07"]
[6330,400029,"Study on Service Oriented Architecture (SOA) for IRP","FS_OAM_SOA_IRP",1,"Rel-9","S5","2008-06-05","2009-06-04",1,"SP-080281","-","Ericsson","edwin.tse@ericsson.com","SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP",32.823999999999998,40,21,null,null,"2007-05-28","2009-06-02"]
[6333,410016,"Study on 1.28 Mcps TDD Home NodeB","FS_RAN-HNBLCRTDD",1,"Rel-9","R4","2008-02-20","2009-12-04",1,"RP-080767","RP-091081","TD Tech","Li Rong (lirong@td-tech.com)","RP#46 completed",25.866,41,21,null,null,"2007-12-17","2009-12-03"]
[6334,420012,"Study on E-UTRAN Mobility Evaluation and Enhancement","FS_EUTRAN_mob",1,"Rel-9","R1","2008-12-05","2009-05-29",1,"RP-081137","RP-090426","Qualcomm","Rajat Prakash (rprakash@qualcomm.com)","RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed)","none",42,22,null,null,"2008-12-04","2009-05-20"]
[6337,440015,"Study on Enhanced Interference Management Mechanisms for HNBs","FS_eInterfMgmtMchsm_HNB",1,"Rel-9","R3","2009-05-30","2009-09-18",1,"RP-090667","RP-090733","Qualcomm","Farhad Meshkati (fmeshkat@qualcomm.com)","RP#45 completed. Triggered by RAN4 UID_430027 Study on Enhanced Interference Management for HNBs",25.966999999999999,44,23,null,null,"2009-05-26","2009-09-15"]
[6340,320005,"3GPP System Architecture Evolution Specification - Evolved Packet System (non RAN aspects)","SAES",1,"Rel-8","S1,S2,S3,S5,C1,C3,C4,C6,IETF","2006-04-12","2012-06-15",1,"SP-080132","-","T-Mobile","michael.kurz@t-mobile.at ","Role model for SAE/LTE system wide project management by SA2 in SP-060166","-",32,17,null,null,"2005-01-31","2009-12-08"]
[6344,390044,"      Stage 2 Security Architecture","SAES",3,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080132","-","Nokia Siemens Networks","marc.blommaert.ext@nsn.com","SP#42 completed","33.210, 33.310, New 33.401",39,21,null,null,"2008-03-19","2010-07-28"]
[6347,340062,"      Stage 3 (CT4) of SAE impact on existing capabilities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","New (29.274, 29.275)",34,18,null,null,"2006-07-19","2010-07-28"]
[6351,340028,"      Stage 3 for SAE / LTE identities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",23.003,34,18,null,null,"2006-07-19","2010-07-28"]
[6354,340060,"      CT4 Stage 3 for protocol between EPCs","SAES-LTE",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[6357,340055,"         CT4 Stage 3 for GTP v2 protocol","SAES-SA-FP_LTE-GTP",4,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",29.274000000000001,34,18,null,null,"2006-07-19","2010-07-28"]
[6358,350043,"      SAES-SA-FP_LTE with PMIP variant","SAES-SA-FP_LTE-IETF",3,"Rel-8","S2,C4","2007-01-02","2009-03-06",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","CP#43 completed","-",35,18,null,null,"2007-04-26","2010-07-28"]
[6361,410004,"         Mobile IPv4 (MIPv4) based Mobility protocols","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Motorola","Lewis Milton","CP#42 completed",29.279,41,21,null,null,"2006-07-19","2010-07-28"]
[6365,340025,"      Stage 3 for QoS mechanisms","SAES-LTE",3,"Rel-8","C3","2007-02-05","2008-12-05",1,"CP-080576","-","Ericsson ","j.javier.pastor@ericsson.com","CP#42 completed",29.213000000000001,34,18,null,null,"2006-07-19","2010-07-28"]
[6368,370008,"      Stage 2 for Interoperation between LTE and 2G/3G","EPSto2_3G",3,"Rel-8","S2","2007-02-05","2008-09-18",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#41 completed","23.401, 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[6371,390008,"      Stage 2 GPRS for EPC (23.060, etc.)","SAES-SA-FP_3GPP",3,"Rel-8","S2","2008-01-14","2008-09-18",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#41 completed",23.06,39,21,null,null,"2007-09-19","2010-07-28"]
[6375,370009,"      Stage 2 for Interoperation between LTE and CDMA2000","EPStoC2k",3,"Rel-8","S2","2007-06-18","2008-09-18",1,"SP-080132","-","Motorola, Vodafone","Irfan.Ali@motorola.com, chris.pudney@vodafone.com","SP#41 completed (except: Handover of multiple PDNs=>Rel-9)","23.401, 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[6378,350027,"   SAE for support for non-3GPP accesses ","SAES-SA-FP_n3GPP",2,"Rel-8","S2,S3,C1,C4,IETF","2007-01-02","2012-06-15",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6381,360022,"      Stage 3 for Mobility management based on DSMIPv6","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303000000000001,36,19,null,null,"2007-09-12","2010-07-28"]
[6382,521011,"      (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt)","SAES-SA-FP_n3GPP",3,"Rel-8","C1-IETF","2007-02-05","2012-06-15",1,"CP-080493","-","Mark Jones","-","CP#56 completed; 9/4/21: RFC 6610 added;","RFC 6610 (was draft-ietf-mip6-hiopt); RFC 6610",52,27,null,null,"2011-06-20","2021-04-09"]
[6385,380030,"      Stage 3 for Inter-system mobility between E-UTRAN and non 3GPP accesses","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008, 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[6389,390172,"      Stage 3 security aspects for MIPv4 Access","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[6392,340057,"      Stage 3 for Interfaces EPC - non-3GPP IP access ","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.273, 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[6395,340059,"      Stage 3 for EPC - AAA interface","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[6399,410005,"      Stage 3 for SRVCC in EPS","SAES-SRVCC",3,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-080793","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","23.009, 24.008, New 24.301",41,21,null,null,"2008-09-03","2010-07-28"]
[6402,350031,"   SAE impacts on IMS","SAES-SA_IMS",2,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6403,390036,"   CS Fallback in EPS","SAES-CSFB",2,"Rel-8","S2,C1,C4","2008-03-12","2009-03-06",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","CP#43 completed","-",39,21,null,null,"2007-03-29","2010-07-28"]
[6406,400003,"      CT4 part of Stage 3 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-080791","-","NEC","yannick.lair@nectech.fr","CP#42 completed","23.007, 23.008, 29.274, New 29.277",40,21,null,null,"2007-03-29","2010-07-28"]
[6409,380037,"      EPC Network Resource Model (NRM) Integration Reference Point (IRP)","EPC-OAM",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070737","-","Huawei","WANG, Xuelong","SP#43 completed","New (32.751, 32.752, 32.753, 32.755)",38,21,null,null,"2005-06-17","2009-02-23"]
[{"$f":"A6413+1","v":6413},410007,"   InterWorking Function (IWF) between MAP based and Diameter based interfaces","SAES-MAP2Diam",2,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080644","-","Huawei","liming49985@huawei.com","CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam)","New 29.305",41,21,null,null,"2007-11-19","2010-07-28"]
[6416,420018,"      Test interworking of LTE Terminals with the USIM","SAES-USIM_LTE-Test",3,"Rel-8","C6","2008-12-05","2010-12-10",1,"CP-100598","-","Comprion","Udo Willenbrink (uwillenbrink@comprion.com )","CP#50 completed. Steering of Roaming test cases have been introduced. Remaining issues CSG display testing (Provide Local Information, Call Control for EPS/PDN, Event Download (Access Technology Change - Multiple Access Technologies)","31.121, 31.124",42,22,null,null,"2008-12-03","2010-11-28"]
[6419,390019,"   Issues for CT3 TR 29.804","SAES",2,"Rel-8","C3","2007-02-05","2008-09-12",1,"CP-080068","-","Ericsson ","j.javier.pastor@ericsson.com","CP#41 completed",29.803999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[6423,340019,"   Deleted - CT aspects of SAES","SAES-St3",2,"Rel-8","C3,C1,C4","2007-09-04","2008-03-14",1,"CP-060674","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6426,350020,"      Deleted - CT3 aspects of SAES","SAES",3,"Rel-8","C3","2007-09-04","2007-09-04",1,"CP-060675","-","-","-","SP#37 stopped","-",35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6427,350021,"      Deleted - CT4 aspects of SAES","SAES",3,"Rel-8","C4","2007-09-04","2007-09-04",1,"CP-060676","-","-","-","SP#37 stopped",29.803000000000001,35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6430,340037,"   Deleted - Architecture enhancements for non-3GPP accesses","SAES-non_3GPP",2,"Rel-8","S2","2007-09-04","2007-09-04",1,"SP-060926","-","Motorola","Irfan.Ali@motorola.com","SP#34 stopped. Replaced by UID_350027 and its children",23.402000000000001,34,18,"SP-34",null,"2006-06-23","2009-03-24"]
[6433,450022,"Conformance Test Aspects – Mobility management based on DSMIPv6 (Dual-Stack Mobile IPv6)","DSMIPv6_UEConTest",1,"Rel-8","R5","2009-09-18","2010-09-17",1,"RP-090754","RP-100738","Qualcomm","Lena Chaponniere (lchaponn@qualcomm.com)","RP#49 completed. Testing for CT1's UID_360022 (24.303) under Rel-8 Feature SAES","36.508, 36.523-1, 36.523-2, 36.523-3",45,23,null,null,"2009-09-15","2010-09-09"]
[6437,400205,"   Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data","ICSRA",2,"Rel-8","C1,C3,C4,IETF","2005-11-01","2014-12-09",1,"CP-091046","-","Ericsson","sean.schneyer@ericsson.com","CP#46 completed","-","-","-",null,null,"2009-12-02","2009-12-07"]
[6440,521015,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 6871)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2013-03-01",1,"CP-091046","-","Andrew Allen","-","CP#59 completed","RFC 6871 (was draft-ietf-mmusic-sdp-media-capabilities)",52,27,null,null,"2011-06-20","2013-02-28"]
[6443,400006,"      CT3 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-091046","-","Mavenir","Brett Wallis ( brett@mavenir.com)","CP#43 completed","new 29.292",40,21,null,null,"2008-03-03","2009-12-07"]
[6447,370059,"IMS Multimedia Telephony and Supplementary Services","IMSTSS",1,"Rel-8","S1,S5,C1,C3,C4,IETF","2007-05-02","2014-12-09",1,"-","-","-","-","SP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[6450,380001,"      Documentation of TISPAN R1 and R2 in CT1","REDOC_TIS-C1",3,"Rel-8","C1","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","24.141, 24.147, 24.173, 24.229, 24.247, 24.341, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.616, 24.623, 24.628, 24.629, 24.647, 24.654",38,21,null,null,"2007-11-28","2008-08-01"]
[6451,380002,"      Documentation of TISPAN R1 and R2 in CT3","REDOC_TIS-C3",3,"Rel-8","C3","2007-11-28","2009-03-06",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#43 completed","29.162, 29.163, 29.658",38,21,null,null,"2007-11-28","2009-12-07"]
[6454,370024,"      Merging TISPAN MMTel [requirements] for Common IMS","TMMTEL",3,"Rel-8","S1","2007-09-10","2007-12-07",1,"SP-070569","-","Nokia Siemens Networks","-","SP#38 completed",22.172999999999998,37,19,null,null,"2007-10-02","2007-11-19"]
[6457,380007,"      CT1 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C1","2007-05-02","2009-03-06",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.642, 24.229, 24.173",38,21,null,null,"2007-11-14","2012-01-11"]
[6461,390059,"      Stage 1 FA","FA",3,"Rel-8","S1","2008-01-30","2008-06-05",1,"-","-","Telecom Italia","-","SP#40 completed ",22.172999999999998,39,21,null,null,"2008-03-03","2008-09-18"]
[6464,380010,"      CT1 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C1","2007-11-30","2009-03-06",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.615, 24.229, 24.173",38,21,null,null,"2007-11-14","2009-02-20"]
[6468,370003,"      Add Interconnection Border Control Function (IBCF) to IMS Charging","CH8_IMS",3,"Rel-8","S5","2007-09-17","2008-03-12",1,"SP-070621","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#39 completed","32.260, 32.298",37,19,null,null,"2007-09-15","2008-03-23"]
[6471,390050,"   Stage 1 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","22.228, 22.173, 22.101, 22.153",39,21,null,null,"2008-03-03","2015-03-24"]
[6474,390113,"   Stage 3 CIMS_3GPP2","REDOC_3GPP2",2,"Rel-8","C1,C3,C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","-","-",39,21,null,null,"2008-03-03","2008-12-04"]
[6475,390013,"      Stage 3 CIMS_3GPP2 (CT1)","REDOC_3GPP2",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","23.218, 24.141, 24.147, 24.173, 24.229, 24.238, 24.247, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.629, 24.930",39,21,null,null,"2008-03-03","2008-12-04"]
[6478,350005,"IMS Enhancements for support of Packet Cable access","PktCbl",1,"Rel-8","S2,S3,C1,C3,C4","2006-12-06","2008-05-30",1,"-","-","Cablelabs","Bernie McKibben (b.mckibben@cablelabs.com)","CP#40 completed","-",35,18,null,null,"2007-03-29","2007-03-29"]
[6481,350010,"      CT1 aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070122","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed","-",35,18,null,null,"2007-03-29","2008-05-13"]
[6485,340008,"   IMS Enhancements for Security Requirements in Support of Cable Deployments","PktCbl-Sec",2,"Rel-8","S3,C1,C3,C4","2006-12-06","2008-05-30",1,"SP-060933","-","Cablelabs","s.dotson@cablelabs.com","CP#40 completed","-",34,18,null,null,"2005-11-04","2007-05-29"]
[6488,380029,"      CT3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C3","2007-03-26","2007-11-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#38 completed",29.163,38,21,null,null,"2007-03-29","2008-03-07"]
[6492,360014,"   SA2 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S2","2007-06-22","2008-09-18",1,"SP-080095","-","Orange","Delphin Barankanira","no Stage 2 impacts",23.228000000000002,36,19,null,null,"2007-06-22","2010-07-29"]
[6495,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228, 29.229, 23.003, 23.008, 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[6498,521021,"   Deleted - (IETF) Maintenance of TISPAN R2 (avasarala-dispatch-comm-div-notification)","MAINT_R2_IETF",2,"Rel-8","C1-IETF","2007-11-09","2014-06-13",1,"CP-080229","-","Andrew Allen","-","CP#64 Draft removed from 3GPP documentation","draft-avasarala-dispatch-comm-div-notification",52,27,"SP-69",null,"2011-06-20","2014-06-06"]
[6499,380043,"   Documentation of TISPAN NGN R1 and R2 in 3GPP SA2","IMS_Comm_Doc",2,"Rel-8","S2","2008-01-14","2008-06-05",1,"SP-070823","-","Nokia Siemens Networks","jozsef.varga@nsn.com","SP#40 completed","23.228, 23.204, 23.167",38,21,null,null,"2007-10-02","2008-05-27"]
[6502,390072,"   Stage 1 IMS Service Continuity","IMS-Cont",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080092","-","LG Electronics","JaeSeung SONG (anthonys@lge.com)","SP#40 completed","-",39,21,null,null,"2007-10-02","2008-05-27"]
[6506,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203, 33.141, 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[6509,380012,"   CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication","NBA",2,"Rel-8","C1","2007-11-14","2009-03-06",1,"CP-070781","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed",24.228999999999999,39,21,null,null,"2007-11-19","2009-02-20"]
[6512,34146,"   SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",2,"Rel-8","S4,S3","2008-03-12","2008-03-12",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#43 completed","26.234, 26.346, 33.246, New 26.237",34,18,null,null,"2008-03-18","2011-06-30"]
[6516,7014,"   Stage 3 of MW-IMS","MIW-IMS-St3C3",2,"Rel-8","C3","2005-09-23","2007-11-30",1,"CP-070096","-","Vodafone","nico.gabriele@vodafone.com","Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021","29.863, 29.163",70,36,null,null,"2006-02-16","2008-08-05"]
[6519,360029,"IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",1,"Rel-8","C1,IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","-",36,19,null,null,"2007-09-05","2009-02-20"]
[6522,521024,"   (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2012-06-15",1,"CP-080794","-","Keith Drage","-","CP#56 completed","RFC 6544 (was draft-ietf-mmusic-ice-tcp)",52,27,null,null,"2011-06-20","2012-04-20"]
[6523,521025,"   (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[6526,521026,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui)","RFC 7433",52,27,null,null,"2011-06-20","2015-03-10"]
[6530,380019,"   Stage 3 Overlap (CT1)","Overlap",2,"Rel-8","C1","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed",24.228999999999999,38,21,null,null,"2007-11-13","2009-02-20"]
[6533,380035,"AS/MRFC Stage 2 and 3","MRFC_TS",1,"Rel-8","C1,IETF","2007-11-14","2012-06-15",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","Triggered by Study UID_7048 (MRFC)","-",38,21,null,null,"2007-11-14","2010-07-30"]
[6536,521027,"   (IETF) AS/MRFC Stage 2 and 3 (RFC 6505)","MRFC_TS",2,"Rel-8","C1-IETF","2007-11-14","2012-06-15",1,"CP-070784","-","Keith Drage","-","CP#56 completed","RFC 6505 (was draft-ietf-mediactrl-mixer-control-package)",52,27,null,null,"2011-06-20","2012-04-20"]
[6540,410003,"IMS Application Server Service Data Descriptions for AS interoperability","IMS_ASIO",1,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080451","-","Alcatel-Lucent","nhberry@alcatel-lucent.com","CP#43 completed. Triggered by UID_360030 (FS_IMS_ASIO)","29.328, 29.329, 29.364",41,21,null,null,"2007-09-05","2009-02-20"]
[6542,390024,"   Stage 1 for I-WLAN NSP","IWLANNSP",2,"Rel-8","S1","2007-06-14","2007-06-14",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","SP#36 completed",22.234000000000002,39,21,null,null,"2005-11-04","2008-03-25"]
[6545,370049,"Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",1,"Rel-8","S2,C1","2007-09-14","2009-03-06",1,"SP-070701","-","Orange","xiaobao.chen@orange-ftgroup.com","CP#43 completed","-",37,19,null,null,"2005-11-04","2008-05-27"]
[6546,380045,"   Stage 2 for Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",2,"Rel-8","S2","2007-09-14","2008-06-05",1,"SP-070701","-","Orange","xiaobao.chen@orange-ftgroup.com","SP#40 completed","new 23.327",38,21,null,null,"2007-11-21","2010-07-30"]
[6549,7042,"Enhancements for Voice Group Call Service (VGCS) Applications (EVA)","EVA",1,"Rel-8","S1,C1,C4,G2","2006-03-15","2009-09-18",1,"SP-070904","-","Nortel","Amar Deol (deola@nortelnetworks.com)","CP#45 completed","-",70,36,null,null,"2006-03-21","2010-07-30"]
[6553,320020,"   CT4 aspects of EVA","EVA",2,"Rel-8","C4","2006-06-02","2007-11-30",1,"CP-060260","-","Nortel","-","CP#38 completed",29.001999999999999,32,17,null,null,"2006-06-21","2008-05-16"]
[6556,7012,"   Stage 1 for PNM","PNM",2,"Rel-8","S1","2005-07-11","2006-07-31",1,"SP-080327","-","Vodafone","armin.toepfer@vodafone.com","SP#31 completed",22.259,null,null,null,null,"2006-02-16","2008-06-04"]
[6559,350001,"      CT1 aspects of Stage 3 PNM","PNM",3,"Rel-8","C1","2007-03-26","2009-03-06",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#43 completed","24.259, 24.229",null,null,null,null,"2007-03-29","2009-02-20"]
[6563,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[6566,34042,"eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution","eCall_Phase2",1,"Rel-8","S4","2007-12-06","2009-09-24",1,"SP-070756","-","Airbiquity","lhong@airbiquity.com & rrobinson@airbiquity.com","SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData)","26.267, 26.268, 26.269, 26.967, 26.969",null,null,null,null,"2007-12-09","2010-08-02"]
[6567,450001,"eCall Conformance Testing","eCall_MSTest",1,"Rel-8","G3new","2009-09-04","2010-09-03",1,"GP-091098","-","Ericsson, Qualcomm","Vikrant Jain (vikrantj@qualcomm.com)","GP#47 completed. GP#43 WID approved. Testing for Rel-8 eCall_Phase2 (UID_34042) and EData (UID_330005)","51.010-1, 51.010-2",45,23,null,null,"2009-09-07","2010-09-04"]
[6570,380061,"   Stage 1 for IPinterc","IPinterc",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#39 completed. ","22.101, 22.228",38,21,null,null,"2007-12-13","2010-08-02"]
[6573,360011,"      IMS inter-operator service interconnection interface","FBI2-IOPSI",3,"Rel-8","C3","2007-06-01","2009-03-06",1,"CP-080578","-","Telecom Italia","antonio.ascolese@telecomitalia.it","CP#43 completed","29.865, 29.165",null,null,null,null,"2007-06-20","2010-08-02"]
[6577,360025,"Support of (G)MSC-S – (G)MSC-S Nc Interface based on the SIP-I protocol","SIP_Nc",1,"Rel-8","C4,C3","2007-09-14","2009-03-06",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#43 completed. Stage 1 in Feature UID_380060 (IPinterc). CP#40 updated WID CP-070517=>CP-080282","-",null,null,null,null,"2007-09-05","2008-05-28"]
[6580,360027,"   Application of SIP-I Protocols to Circuit Switched (CS) core network architecture; Stage 3","SIP_Nc-St3C4",2,"Rel-8","C4","2007-09-14","2008-12-05",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#42 completed","29.231, 29.232, 29.332",null,null,null,null,"2007-09-05","2008-11-22"]
[6583,370052,"   Stage 1 for ETWS","ETWS",2,"Rel-8","S1","2007-09-10","2008-03-12",1,"SP-070815","-","NTT DoCoMo","kitaharar@nttdocomo.co.jp","SP#39 completed",22.167999999999999,37,null,null,null,"2007-11-19","2008-03-20"]
[6587,430045,"   ETWS primary notification message definition in GERAN","ETWS",2,"Rel-8","G2","2009-03-12","2009-05-15",1,"SP-090154","-","Ericsson","claes-goran.persson@ericsson.com","SP#44 completed with CT1 help (GERAN2 LS_in SP-090154)","44.018, 44.060",43,22,null,null,"2009-03-10","2009-05-30"]
[6590,380159,"   Stage 1 for ICE","ICE",2,"Rel-8","S1","2007-03-13","2008-03-12",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","SP#39 Stage 1 completed","22.030, 22.101",38,21,null,null,"2007-12-13","2008-06-17"]
[6591,380259,"   CT6 aspects of ICE","ICE",2,"Rel-8","C6","2007-03-13","2009-03-06",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","CP#43 completed (ICE Graphics not in Rel-8 / not explicitly in SA1 WID either)",31.102,38,21,null,null,"2007-12-13","2010-09-06"]
[6594,370028,"   Stage 1 for CAT","CAT",2,"Rel-8","S1","2006-12-06","2007-09-20",1,"SP-070122","-","China Mobile","fenglingjuan@chinamobile.com","-",22.181999999999999,37,null,null,null,"2007-10-02","2008-09-10"]
[6597,390114,"      IMS CAT SS","CAT-SS",3,"Rel-8","C1","2008-04-21","2008-12-04",1,"CP-080496","-","Nortel","milanpa@nortel.com","CP#42 completed",24.181999999999999,39,21,null,null,"2008-03-03","2008-11-21"]
[6601,410015,"      CT1 part of CAT Service in 3GPP CS domain","CAT-3G_CS",3,"Rel-8","C1","2008-09-12","2008-12-05",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","CP#42 completed. Triggered by Study UID_360031 (TR 29.882)","24.008, 23.014",41,21,null,null,"2008-09-11","2012-01-11"]
[6604,350048,"   Stage 2 for MESSIW","MESSIW",2,"Rel-8","S2","2007-04-26","2008-03-07",1,"SP-070816","-","Huawei","patrice.hede@huawei.com","SP#39 completed","23.811, 23.204",null,null,null,null,"2005-11-04","2008-03-22"]
[6607,340044,"Multimedia Priority Service","PRIOR_EMR",1,"Rel-8","S1,C1,C3,C4","2006-06-08","2009-09-18",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","CP#45 completed","-",34,null,null,null,"2003-03-28","2009-09-09"]
[6611,370020,"   Deleted - Stage 3 for PRIOR","PRIOR-EMR",2,"Rel-8","C3","2007-09-21","2009-05-29",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2)","29.212, 29.213, 29.214, 29.163",37,null,"CP-44","PCG-23","2007-09-25","2009-05-29"]
[6614,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6615,360005,"   Rel-8 OSA Stage 2/3 enhancements","OSA8-IMS",2,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","SP#40 maintenance & new OSA work moved to OMA","23.198, 29.198, 29.199",null,null,null,null,"2005-12-14","2010-08-02"]
[6618,370014,"      Parlay-X Policy web service ","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-22",37,null,null,null,"2007-09-13","2009-01-19"]
[6621,380047,"      Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6625,380051,"      Deleted - Event notification (22.127 CR 0088 S1-071762)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6628,380054,"      Presence alignment with OMA and IETF (22.127 CR 0092 S1-071764)","OSA8-IMS",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-14/13",38,21,null,null,"2007-12-05","2009-01-19"]
[6632,390069,"      Connectivity Manager SCF","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-10",39,21,null,null,"2008-03-26","2009-01-19"]
[6635,370084,"   Stage 1 for PPACR","PPACR-S1",2,"Rel-8","S1","2007-06-12","2007-09-14",1,"SP-070501","-","NTT DoCoMo","Morita Takashi","SP#37 completed",22.010999999999999,37,null,null,null,"2007-10-16","2008-05-16"]
[6638,380063,"Charging for multi-phases services","CHRGMPH",1,"Rel-8","S1","2007-12-06","2008-03-12",0.99,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 Stage 1 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-12-10"]
[6639,380070,"   Stage 1 for CHRGMPH","CHRGMPH-s1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-03-20"]
[6642,420019,"   Support of Closed Subscriber Group (CSG)","-",2,"Rel-8","C4","2008-12-05","2009-03-06",1,"-","-","CT#42","Hannu Hietalahti","CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG","29.002, 29.272, 23.008, 23.003",42,22,null,null,"2008-12-04","2009-02-23"]
[6645,390033,"UTRA HNB","HNB",1,"Rel-8","RP,S5","2008-03-07","2009-06-04",1,"-","-","-","-","SP#44 completed","-",39,21,null,null,"2005-01-04","2008-06-03"]
[6649,420037,"   3G Home NodeB OAM&P Type 1 Management Interface","HNB-3G_OAM",2,"Rel-8","S5","2008-12-11","2009-06-04",1,"SP-080708","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Complements work in BroadBand Forum","new (32.581, 32.582, 32.583, 32.584)",42,22,null,null,"2008-12-03","2009-05-18"]
[6652,350015,"Lawful Interception in the 3GPP Rel-8","LI8",1,"Rel-8","S3","2007-03-12","2009-03-12",1,"SP-070238","-","BMWI, Verizon","berthold.wilhelm@bnetza.de, ron_ryan@verizon.net ","SP#43 completed","33.106, 33.107, 33.108",null,null,null,null,"2007-03-29","2009-03-11"]
[6656,390346,"   CT4 part of GBAPush ","GBAPush",2,"Rel-8","C4","2008-03-12","2009-03-06",1,"CP-090112","-","Ericsson","Rolf Blom","CP#43 completed",29.109000000000002,39,21,null,null,"2008-03-22","2009-03-04"]
[6659,400028,"Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI","MTSI_eMHI",1,"Rel-8","S4,C3,C4","2007-12-06","2009-03-12",1,"SP-080443","-","Ericsson, Qualcomm","olle.franceschi@ericsson.com, nleung@qualcomm.com","TSG#43 completed","-",40,21,null,null,"2007-12-09","2009-02-21"]
[6662,400020,"   CT4 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#43 completed",29.332000000000001,40,21,null,null,"2007-12-09","2009-02-20"]
[6663,400019,"   Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C1","2008-05-30","2008-12-12",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774","-",40,21,"CP-42",null,"2007-12-09","2010-08-02"]
[6666,35051,"      Telecom Management Methodology","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2009-03-12",1,"SP-070296","-","Ericsson ","thomas.tovinger@ericsson.com","SP#43 completed","32.155, 32.153",null,null,null,null,"2005-06-17","2009-02-23"]
[6670,400030,"      IRP SOAP Solution Sets","OAM8-NIM",3,"Rel-8","S5","2008-06-05","2009-03-12",1,"SP-090148","-","Ericsson","edwin.tse@ericsson.com","SP#43 completed","32.111-7, 32.617, 32.417, 32.367, 32.347, 32.111-1, 32.111-2, 32.111-3, 32.111-5, 32.307, 32.317, 32.341, 32.342, 32.343, 32.345, 32.361, 32.362, 32.363, 32.365, 32.411, 32.412, 32.413, 32.415, 32.611, 32.612, 32.613, 32.615, 32.625",40,21,null,null,"2007-09-15","2009-08-11"]
[6673,340065,"   Rel-8 Performance Management","OAM8-PM",2,"Rel-8","S5","2007-06-07","2009-03-12",1,"-","-","-","Li Jian (lijian@chinamobile.com)","-","-",34,null,null,null,"2007-07-13","2008-06-26"]
[6676,360002,"      Key Performance Indicators (KPIs) for UMTS and GSM","OAM8-PM",3,"Rel-8","S5","2007-06-07","2009-03-12",1,"SP-070299","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#43 completed",32.409999999999997,null,null,null,null,"2007-05-28","2009-02-23"]
[6680,531003,"      Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event)","OAM8-Trace",3,"Rel-8","C1-IETF","2008-03-07","2011-12-09",1,"CP-080315","-","Peter Dawes","peter.dawes@vodafone.com","CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100","draft-dawes-sipping-debug-event",53,27,null,null,"2011-07-29","2021-04-09"]
[6683,870081,"   (IETF) A Two-Way Active Measurement Protocol (TWAMP) (draft-ietf-ippm-twamp) --> RFC 5357","OAM8",2,"Rel-8","S5-IETF","2008-03-07","2010-09-06",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[6686,360003,"   SMS online charging","CH8",2,"Rel-8","S5","2007-06-07","2007-12-14",1,"SP-070293","-","Vodafone","Gavin.Wong@vodafone.com","SP#38 completed","32.240, 32.299, new 32.274",null,null,null,null,"2007-05-29","2008-03-17"]
[6687,410045,"   Introduce Online Charging from SMS-SC into the SMS Charging Specifications","CH8",2,"Rel-8","S5","2008-09-18","2008-12-11",1,"SP-080463","-","Acision","erik.gebler@acision.com","SP#42 completed. Linked to SA2 UID 32081 (Support of SMS over IP networks) and CT4 UID 340016 (Routeing of MT-SMS via the HPLMN).","32.274, 32.299",41,21,null,null,"2008-09-15","2008-11-25"]
[6690,380025,"   Stage 2 for eMp","eMp",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed",23.332999999999998,38,21,null,null,"2007-11-19","2010-08-02"]
[6694,350046,"   External interface for eUPHBOOK","eUPHBOOK-Ext_Spec",2,"Rel-8","C6","2007-05-07","2008-03-07",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#39 completed","new 31.220",null,null,null,null,"2006-01-24","2008-05-29"]
[6697,20068,"Rel-8 LTE – 3G Long Term Evolution - Evolved Packet System RAN part","LTE",1,"Rel-8","RP,S5","2006-09-25","2009-03-12",1,"RP-080747","RP-080741","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","RP#43 completed. Role model for SAE/LTE system wide project management by SA2 in SP-060166","LTE 36.300, 36.938",null,null,null,null,"2006-06-21","2009-12-18"]
[6700,330020,"   LTE – eUTRAN Interfaces","LTE-interfaces",2,"Rel-8","R3","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Ericsson","Martin Israelsson","RP#42 completed","36.401, 36.410, 36.411, 36.412, 36.413, 36.414, 36.420, 36.421, 36.422, 36.423, 36.424, 25.413",null,null,null,null,"2006-03-21","2009-12-18"]
[6704,370001,"      Subscriber and Equipment Trace for E-UTRAN and EPC","E-UTRAN-OAM",3,"Rel-8","S5","2007-09-17","2009-03-12",1,"SP-070617","-","Ericsson","robert.petersen@ericsson.com ","SP#43 completed","32.421, 2.422, 32.423, 2.441, 32.442, 32.443, 32.445",37,null,null,null,"2007-09-15","2010-07-29"]
[6707,390003,"      Key Performance Indicators (KPIs) for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080063","-","Ericsson ","ulf.hubinette@ericsson.com ","SP#43 completed","new (32.450, 32.451)",39,21,null,null,"2005-06-17","2009-02-23"]
[6710,390005,"      Self-Establishment of eNBs, including automated Software Management","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080849","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#42 completed","new (32.501, 32.502, 32.503, 32.531, 32.532, 32.533)",39,21,null,null,"2005-06-17","2010-03-22"]
[6711,390006,"      SON Automatic Neighbour Relations (ANR) List Management","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080066","-","Ericsson ","edwin.tse@ericsson.com","SP#42 completed","32.761, 32.762, 32.763, 32.765, new 32.511",39,21,null,null,"2005-06-17","2008-12-01"]
[6714,25042,"   LTE – Terminal Radio Transmission and Reception Conformance Test Specifications","LTE-UEConTest_RF",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080601","RP-091059","Agilent","andrea_leonardi@agilent.com","RP#46 completed. RP#50 TR 36.903 v100 for Approval","36.521-1, 36.521-2, 36.521-3, new 36.903",null,null,null,null,"2009-06-02","2010-12-10"]
[6718,410018,"   UMTS 1880 MHz TDD","RInImp9-UMTS1880TDD",2,"Rel-8","R4","2008-09-12","2009-03-06",1,"RP-080757","RP-090044","CATT","Yuexia Song (songyuexia@catt.cn)","RP#43 completed","25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307",41,21,null,null,"2008-09-11","2009-03-10"]
[6721,370032,"   CS Voice Service over HSPA","RInImp8-CsHspa",2,"Rel-8","R2","2007-07-19","2008-03-07",1,"RP-070765","RP-080042","Nokia Siemens Networks","woonhee.hwang@nsn.com","RP#39 completed","25.323, 25.331, 25.322",37,null,null,null,"2007-10-02","2010-08-02"]
[6724,25125,"Rel-8 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-8","R5","2007-06-01","2008-12-05",1,"-","-","-","-","05/08: Linked to Feature UID_20028 (RInImp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[6728,360013,"   Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-64QamMimoHsdpa",2,"Rel-8","R1","2007-06-04","2008-09-12",1,"RP-070500","RP-080518","Ericsson","Johan.Bergman@ericsson.com","RP#41 completed","25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141",null,null,null,null,"2007-06-21","2010-08-03"]
[6731,370038,"   Enhanced UE Discontinuous Reception (DRX) for FDD","RANimp-DRX",2,"Rel-8","R2","2007-09-14","2008-09-12",1,"RP-070679","RP-080520","Nokia","luis.barreto@nokia.com","RP#41 completed. Continuation of Rel-7 work item \"Continuous connectivity for packet data users\" UID_20046.","25.306, 25.308, 25.321, 25.331, 25.423",37,null,null,null,"2007-10-01","2010-08-03"]
[6732,370039,"   Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure","RANimp-SrnsReloc",2,"Rel-8","R3","2007-09-14","2008-09-12",1,"RP-070759","RP-080521","Nokia Siemens Networks","masatoshi.nakamata@nsn.com","RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution","25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.214, 25.133",37,null,null,null,"2007-10-01","2010-08-03"]
[6735,380076,"   Enhanced CELL_FACH state in 1.28 Mcps TDD","RANimp-EnhState1.28TDD",2,"Rel-8","R2","2007-12-04","2008-12-05",1,"RP-071038","RP-080807","ZTE","zhang.yincheng@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.123, 25.221, 25.222, 25.224, 25.301, 25.302, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.401, 25.423, 25.425, 25.433, 25.435",38,21,null,null,"2007-12-17","2010-08-03"]
[6738,390030,"   HS-DSCH Serving Cell Change Enhancements","RANimp-HSDSCH",2,"Rel-8","R2","2008-03-07","2008-12-05",1,"RP-080227","RP-080811","Ericsson","henrik.enbuske@ericsson.com","RP#42 completed","25.101, 25.104, 25.133, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433",39,21,null,null,"2008-03-17","2010-08-03"]
[6742,410020,"   Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-UEConTest_64QamMimoHsdpa",2,"Rel-8","R5","2008-09-12","2009-12-04",1,"RP-080759","RP-091058","Ericsson","leif.mattisson@ericsson.com","RP#46 completed. Testing for UID_360013","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2",41,21,null,null,"2008-06-03","2010-08-03"]
[6745,400057,"   Conformance Test Aspects – 64QAM for 1.28 Mcps TDD HSDPA","RANimp-UEConTest_64Qam1.28TDD",2,"Rel-8","R5","2008-05-30","2009-05-29",1,"RP-080334","RP-090415","ZTE","ma.zijiang@zte.com.cn","RP#44 completed. Testing for UID_380075","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",40,21,null,null,"2008-06-03","2010-08-03"]
[6748,430028,"   Conformance Test Aspects – Receiver Type3i","RANimp-UEConTest_ReceiverType3i",2,"Rel-8","R5","2009-03-06","2009-12-04",1,"RP-090010","RP-091066","Qualcomm","Ashok Kumar Narayanaswamy (anarayan@qualcomm.com)","RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD","34.108, 34.121-1, 34.121-2",43,22,null,null,"2009-03-10","2010-08-03"]
[6752,450026,"   Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements","HSDSCH_UEConTest",2,"Rel-8","R5","2009-09-18","2010-03-19",1,"RP-090756","RP-100077","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#47 completed. Testing for UID_390030","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[6755,50583,"GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",1,"Rel-8","GP,G1,C1,G3new","2006-09-08","2011-11-25",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed. GP#52 completed MS conformance testing","44.018, 44.060, 45.002, 45.008, 45.010, 48.008, 48.018, 51.010",null,null,null,null,"2006-09-13","2011-11-25"]
[6756,51583,"   G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G1","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","43.055, 43.129, 43.246, 45.002, 45.008, 45.010",null,null,null,null,"2006-09-13","2010-09-09"]
[6759,54583,"   Testing for GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G3new","2006-09-08","2011-11-25",1,"GP-061757","-","Renesas Mobile","deepa.kamath@renesasmobile.com","GP#52 completed",51.01,null,null,null,null,"2006-09-13","2011-11-25"]
[6762,50588,"   Update to GAN specifications","GANENH-SPEC",2,"Rel-8","GP","2007-08-31","2008-02-22",1,"GP-071560","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed","43.318, 44.318",null,null,null,null,"2007-09-06","2008-05-19"]
[6766,400042,"   Media Requirements for CS over IP based User Plane","AoIP-CSoIP",2,"Rel-8","S4","2007-12-05","2008-12-11",1,"SP-080444","-","China Mobile, Ericsson","Karl.Hellwig@Ericsson.com","SP#42 completed","26.102, 26.103, 26.202",40,21,null,null,"2007-12-09","2008-11-21"]
[6769,400124,"      CT1 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722",23.009,40,21,null,null,"2007-09-19","2012-01-11"]
[6772,38001,"Support for Additional Navigation Satellite Systems (ANSS) for LCS","ANSS",1,"Rel-8","S1,G2,R2","2008-05-16","2008-12-11",1,"GP-081784","-","Qualcomm","Mungal Dhanda","GP#40 completed","-",null,null,null,null,"2008-05-19","2009-02-19"]
[6776,51149,"Conformance testing for the Latency Reductions feature","CTLATRED",1,"Rel-8","G1,G3new","2008-02-22","2010-03-05",1,"GP-080367","-","Ericsson","mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com","GP#45 completed","-",null,21,null,null,"2008-02-26","2010-03-05"]
[6779,53091,"MS conformance testing of changes introduced by WI \"Support of Packet-switched Handover for GERAN A/Gb mode\"","PSHCT-MStest",1,"Rel-8","G3new","2008-02-22","2008-11-21",1,"GP-080411","-","Rohde & Schwarz","Franz.Segerer@ROHDE-SCHWARZ.COM","GP#40 completed",51.01,null,21,null,null,"2008-02-26","2008-11-22"]
[6781,521029,"(IETF) (Small) Technical Enhancements and Improvements for Rel-8","TEI8_IETF",1,"Rel-8","C1-IETF","2007-01-01","2012-09-07",1,"-","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#57 completed","RFC 6714 (was draft-ietf-simple-msrp-cema)",52,27,null,null,"2011-06-20","2012-09-03"]
[6782,400025,"Test - (Small) Technical Enhancements and Improvements for Rel-8","TEI8_Test",1,"Rel-8","R5,G3new","2007-03-07","2010-12-24",1,"-","-","-","-","-","-",40,21,null,null,"2005-11-04","2010-12-07"]
[6785,340032,"Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN","LCS4_IWLAN",1,"Rel-8","S2","2007-09-28","2007-09-28",1,"SP-060818","-","LG Electronics","dhshim@lge.com","SP#35 stopped","23.234, 23.271, 23.167",34,null,"SP-35",null,"2006-03-22","2009-03-24"]
[6789,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[6792,53092,"Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain","SCSAGBCT-MStest",1,"Rel-8","G3new","2008-02-25","2009-09-04",1,"GP-080330","-","Nokia","arsi.heino@nokia.com","GP#43 work stopped/abandoned (completion 0%)",51.01,null,21,"GP-43","PCG-23","2008-02-26","2009-09-07"]
[6796,31089,"Study on Network Composition","FS_NetComp",1,"Rel-8","S1","2005-12-07","2007-12-12",1,"SP-060478","-","Nokia Siemens Networks","joerg.swetina@neclab.eu","SP#38 completed",22.98,null,null,null,null,"2005-12-12","2008-03-24"]
[6799,330016,"Study on Paging Permission with Access Control","FS_PPAC",1,"Rel-8","S1","2006-09-28","2007-09-20",1,"SP-060785","-","NTT DoCoMo","Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp)","SP#37 completed. Spin-off new Feature UID_370084 (PPACR)",22.908000000000001,null,null,null,null,"2006-10-06","2010-08-31"]
[6802,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[6803,370086,"Study on Services Alignment and Migration","FS_ServAl",1,"Rel-8","S1","2006-12-06","2008-03-12",1,"SP-070126","-","Telefónica O2","chris.friel@O2.com","SP#39 completed. Spin-off Rel-9 Feature UID_330017 Services Alignment and Migration (ServAl)",22.983000000000001,37,null,null,null,"2006-10-06","2010-08-05"]
[6806,32087,"   Stage 2 study on 3GPP architectural development","FS_SAE",2,"Rel-8","S2","2006-01-09","2008-09-18",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#41 completed",23.882000000000001,null,null,null,null,"2005-01-31","2008-09-14"]
[6809,7049,"Study on IMS utilizing multicast bearer services","FS_MLTICAST-IMS",1,"Rel-8","S2","2006-03-22","2007-12-06",1,"SP-060148","-","Nokia Siemens Networks","-","SP#38 completed",23.847000000000001,null,null,null,null,"2006-03-22","2008-03-24"]
[6813,330012,"   Study on centralized IMS services control ","FS_IMS_CSC",2,"Rel-8","S2","2006-10-23","2008-03-12",1,"SP-070494","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","SP#39 completed",23.891999999999999,null,null,null,null,"2006-02-16","2008-03-22"]
[6816,360015,"Study on Transferring of emergency call data – in-band modem solution","eCALLIBMS",1,"Rel-8","S4","2006-12-07","2007-12-12",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2)",26.966999999999999,null,null,null,null,"2006-12-10","2008-05-16"]
[6820,340036,"Study on Management for LTE and SAE","FS_OAM_LTE_SAE",1,"Rel-8","S5","2006-12-07","2008-12-11",1,"SP-060753","-","Ericsson","robert.petersen@ericsson.com ","SP#42 completed",32.816000000000003,34,null,null,null,"2006-12-15","2008-11-25"]
[6823,350018,"Study on IMS Restoration Procedures","FS_IMS_RP",1,"Rel-8","C4","2007-03-26","2008-05-30",1,"CP-070031","-","Ericsson","german.blanco@ericsson.com","CP#40 completed. Spin-off WID UID_400012 (IMS_RP)",23.82,null,null,null,null,"2007-03-29","2008-05-29"]
[6826,380023,"Study on InterWorking Function between MAP based and Diameter based interfaces","FS_MAP2Diam",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-070760","-","Huawei","liming49985@huawei.com","CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005",29.805,38,21,null,null,"2007-11-19","2008-11-22"]
[6827,370041,"Study on Scope of future HSPA Evolution for 1.28 Mcps TDD","FS_RAN-LCRTDDHSPAEvo",1,"Rel-8","R1","2007-09-14","2008-05-30",1,"RP-070748","RP-080290","RITT","Xu Fei","RP#40 completed",25.824000000000002,37,null,null,null,"2007-06-21","2008-06-12"]
[6830,350039,"Study on 3G Home NodeB/eNodeB","FS_RAN-HNBeNB",1,"Rel-8","R4","2007-03-05","2008-05-30",1,"RP-070257","RP-080289","Motorola","howard.thomas@motorola.com","RP#40 completed",25.82,null,null,null,null,"2007-03-29","2008-06-26"]
[6834,350017,"Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems","FS_SM3GWLAN",1,"Rel-8","S2","2007-03-20","2008-09-18",1,"SP-070106","-","Orange","-","SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327.","withdrawn 23.827",null,null,"SP-41","PCG-21","2007-03-29","2008-09-17"]
[6837,380080,"Deleted - Study on HS-PDSCH serving cell change enhancements","FS_RAN-HSPDSCH",1,"Rel-8","R4","2007-12-17","2008-03-07",1,"RP-071044","RP-080070","Qualcomm","-","RP#39 stopped (no TR produced). Spin-off HS-DSCH Serving Cell Change Enhancements (UID_39003)","none",38,21,"RP-39","PCG-21","2007-12-17","2008-06-26"]
[6840,732097,"Identification of Communication Services in IMS","ServID",1,"Rel-7","S2,S1,C1,S5","2005-05-02","2007-09-14",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","WID approved SP#28. WID updated SP#32","-",null,null,null,null,"2005-06-22","2008-07-01"]
[6844,7035,"   Charging of ServID","ServID",2,"Rel-7","S5","2006-03-31","2007-09-14",1,"SP-060293","-","Orange","alain.bibas@orange-ft.com","-","32.260, 32.298, 32.299",null,null,null,null,"2006-03-20","2008-07-01"]
[6847,7010,"   Stage 1,2 of GRUU","GRUU",2,"Rel-7","S1,S2","2006-07-03","2006-09-29",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","SP#29 approved WID","22.228, 23.228, 23.218, 24.229",null,null,null,null,"2006-02-16","2008-07-01"]
[6850,7039,"   Stage 1 of MTSI","MTSI-REQ",2,"Rel-7","S1","2006-02-01","2006-09-29",1,"SP-060224","-","Ericsson","peter.bleckert@ericsson.com","-",22.172999999999998,null,null,null,null,"2006-03-21","2008-06-25"]
[6851,7037,"   Stage 3 of MTSI","MTSI",2,"Rel-7","C1","2006-03-10","2007-06-14",1,"CP-060257","-","Ericsson","christer.holmberg@ericsson.com","-",24.172999999999998,null,null,null,null,"2006-03-22","2008-06-25"]
[6854,690071,"   UE Conformance Test Aspects – Multimedia Telephony Services for IMS (MTSI) over WLAN","MTSI_WLAN-UEConTest",2,"Rel-7","R5","2015-09-15","2016-12-15",1,"RP-151770",null,"Ericsson",null,"tested: REL-7 WI MTSI¦1/1/16: Compl:0%->5%1/1/16: WID: RP-151334->RP-15177022/3/16: Compl:5%->10% ",null,69,35,null,null,"2015-09-29","2016-12-20"]
[6858,387001,"Maintenance of TISPAN release 1 common IMS","MCIMSTR1",1,"Rel-7","S2","2007-07-02","2008-03-07",1,"SP-070915","-","Ericsson","Raymond Forbes","-","http://www.3gpp.org/specs/TISPAN-IMS-ansfer.htm",38,21,null,null,"2008-01-10","2008-07-21"]
[{"$f":"A6861+1","v":6861},380072,"   SA1,SA2 part of Maintenance of TISPAN release 1 common IMS","IMS_Comm_Mtce7",2,"Rel-7","S2,S1","2007-07-02","2007-12-06",1,"SP-080501","-","BT, Ericsson","Dick Knight, Raymond Forbes","SP#38 completed","22.173, 22.273, 22.401, 23.406, 23.417, 23.508, 23.509, 23.511",38,21,null,null,"2007-10-02","2010-07-29"]
[6864,1314,"   Service Requirements for IP-based emergency calls","EMC1",2,"Rel-7","S1","2000-09-18","2004-06-25",1,"SP-050604","-","Siemens","Rainer Liebhart","-",22.100999999999999,null,null,null,null,"2000-04-19","2004-06-08"]
[6868,32101,"   Deleted - Stage 2 Specification Phase - GPRS-level","EMC1",2,"Rel-7","S2","2007-03-02","2007-03-02",1,"SP-050604","-","Siemens","Rainer Liebhart","-","-",null,null,"SP-32",null,"2004-10-14","2007-06-22"]
[6871,521030,"      (IETF) CT1 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1-IETF","2006-01-09","2011-12-09",1,"CP-050529","-","Keith Drage","-","CP#54 completed","RFC 6442 (was draft-ietf-sipcore-location-conveyance)",52,27,null,null,"2011-06-20","2011-12-13"]
[6874,1646,"      CT1 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","24.008, 24.234",null,null,null,null,"2000-08-08","2007-09-12"]
[6875,14026,"      CT4 PS domain aspects to support IMS Emergency sessions","EMC1-GPRSc4",3,"Rel-7","C4","2006-01-09","2007-06-01",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-",29.06,null,null,null,null,"2000-08-08","2007-05-29"]
[6878,31062,"WLAN-UMTS Interworking Phase 2","WLAN2",1,"Rel-7","S1,S2","2004-01-05","2005-06-07",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","Created at SP#27 because of WLAN items belonging to Rel-7. Acronym changed from \"WLAN2, WLAN-SC\"","33.234 (SP-36 SA3 CRs approved)",null,null,null,null,"2005-03-09","2015-03-24"]
[6882,32111,"   WLAN-PNA - Stage 2","WLANPNA-st2",2,"Rel-7","S2","2005-10-10","2006-06-23",1,"SP-050489","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Approved at SP#29","23.234, 33.234",null,null,null,null,"2005-12-20","2006-05-31"]
[6885,13027,"      CT3 aspets for WLAN-PNA","WLANPNA-st3",3,"Rel-7","C3","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29",29.161000000000001,null,null,null,null,"2005-12-22","2006-06-23"]
[6888,7015,"   Deleted - TR on support of QoS on WLAN","WLANQOS",2,"Rel-7","S2","2005-03-14","2006-01-31",1,"SP-050682","-","Samsung","-","SP#32 stopped",23.835999999999999,null,null,"SP-32",null,"2006-02-16","2008-07-18"]
[6892,32079,"Location Services enhancements","LCS3",1,"Rel-7","S1,S2,GP,C4,R2","2004-06-28","2007-12-17",1,"SP-040682","-","-","-","-","-",null,null,null,null,"2002-06-21","2008-07-02"]
[6895,14025,"   CT4 aspects for LCS UEPos-LBS","LCS3-UEPos-LBS",2,"Rel-7","C4","2006-01-02","2006-12-01",1,"CP-050240","-","SiRF","brodilitz@sirf.com","-","24.030, 24.080, 29.002",null,null,null,null,"2005-06-20","2008-07-02"]
[6896,20042,"   UE positioning - Velocity","LCS3-UEPos-Velocity",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050300","RP-060459","SiRF","BRodilitz@SiRF.com","-","25.305, 25.331, 25.410, 25.413, 25.453",null,null,null,null,"2005-06-20","2008-07-02"]
[6899,32077,"      FS on 3GPP system to WLAN Interworking with LCS","LCS3-IWLAN-FSs1",3,"Rel-7","S1","2004-06-28","2006-06-30",1,"SP-060291","-","Telcordia","Mike Loushine","-","new 22.935",null,null,null,null,"2004-08-30","2010-08-31"]
[6902,20030,"   Deleted - UE positioning Rel-7","LCS3-UEpos",2,"Rel-7","RP","2004-09-15","2007-12-17",1,"-","-","-","-","-","-",null,null,"RP-38",null,"2005-01-04","2008-06-25"]
[6906,340043,"   MBMS TDD Physical layer Enhancements","MBMSE-RANPhysTDD",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070241","RP-070291","IPWireless","Nicholas Anderson","-","25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123",34,null,null,null,"2005-11-21","2008-06-25"]
[6909,400058,"MBMS - UE Conformance Testing","MBMSE_UEConTest",1,"Rel-7","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Linked to Rel-7 Feature UID_31084 (MBMSE)","-",40,21,null,null,"2008-03-11","2009-04-01"]
[6912,400060,"   Conformance Test Aspects – MBSFN for FDD","MBMSE-UEConTest_RANPhysFDD",2,"Rel-7","R5","2008-05-30","2009-12-04",1,"RP-080336","RP-091214","Huawei","Xiang Li (trica_li@huawei.com)","RP#46 completed","34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",40,21,null,null,"2008-06-03","2009-11-26"]
[6916,50548,"   Towards AGNSS Concept","AGNSS-GP",2,"Rel-7","GP","2004-06-28","2007-08-31",1,"GP-042677","-","Alcatel","richard.couty@space.alcatel.fr","GP#36 completed","43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031",null,null,null,null,"2004-08-30","2012-05-21"]
[6919,31048,"Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM","USSD-USIM",1,"Rel-7","S1,C6","2004-03-05","2005-08-12",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","-",null,null,null,null,"2004-06-08","2008-09-10"]
[6920,31060,"   Stage 1 for USSD message delivery and transfer to USIM","USSD-USIM",2,"Rel-7","S1","2004-03-18","2004-10-15",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-",22.09,null,null,null,null,"2004-06-08","2008-09-10"]
[6923,31064,"   Stage 1 for CSICS","CSICS",2,"Rel-7","S1","2005-01-17","2005-06-09",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-",22.279,null,null,null,null,"2005-02-28","2008-07-02"]
[6926,34031,"   Stage 3 for codec aspects","CSICS-Codec",2,"Rel-7","S4","2005-03-15","2005-12-07",1,"SP-050091","-","Ericsson","Per.Frojdh@ericsson.com","-","26.141, 26.235",null,null,null,null,"2005-03-22","2008-07-02"]
[6930,31088,"IMS Service Brokering enhancements","ISB",1,"Rel-7","S1","2005-12-07","2006-03-13",1,"SP-050830","-","Telcordia","jbakker@telcordia.com","No CR submitted in rel-8 (according to CR database). ",22.228000000000002,null,null,null,null,"2005-11-04","2008-03-25"]
[6933,31061,"   Stage 1 for Enhancements of VGCS for public authority officials","EVGCS",2,"Rel-7","S1","2004-08-27","2004-08-27",1,"SP-040304","-","Siemens","joerg.swetina@neclab.eu","Voice Group Call Service","42.068, 43.068",null,null,null,null,"2004-08-30","2006-09-19"]
[6937,752076,"   GERAN2 aspects of EVGCS","EVGCS",2,"Rel-7","G2","2004-08-27","2007-02-16",1,"GP-071855","-","Siemens","kenneth.isaacs@roke.co.uk","-","-",75,38,null,null,"2004-10-15","2007-03-08"]
[6940,32090,"   Stage 2 modifications for VGCS improvements","IVGCS",2,"Rel-7","C1","2005-12-01","2007-03-14",1,"NP-050141","-","T-Mobile","kurt.bischinger@t-mobile.at","-",43.067999999999998,null,null,null,null,"2005-03-22","2007-03-08"]
[6943,14023,"      Deleted - CT4 aspects of IVGCS","IVGCS-St3-c4",3,"Rel-7","C4","2007-03-09","2007-03-09",1,"NP-050141","-","T-mobile","-","CT4#33 stage 2 solution is still open. ",29.001999999999999,null,null,"CP-35",null,"2005-09-14","2007-03-29"]
[6944,31071,"Open Service Access (OSA) Rel-7 ","OSA7",1,"Rel-7","S1,C5","2005-03-15","2007-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-","-",null,null,null,null,"2005-03-22","2005-09-15"]
[6947,43011,"      Stage 2 OSA API Service Brokering","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","AePONA","damian.oneill@aepona.com","-",23.198,null,null,null,null,"2005-03-22","2012-07-26"]
[6950,7018,"      Parlay X Message Broadcast Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-15, 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[6954,340002,"      Parlay-X Multimedia Streaming Session Management Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","Telenor","-","-","29.199-19, 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[6957,31053,"Selective Disabling of UE Capabilities","SDoUE",1,"Rel-7","S1,S2,C1","2005-01-24","2007-06-15",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06","-",null,null,null,null,"2004-08-30","2008-07-17"]
[6961,7041,"Network selection enhancements (NSP)","NSP",1,"Rel-7","S1","2006-03-15","2007-06-15",1,"SP-060220","-","O2","chris.friel@O2.com","-","-",null,null,null,null,"2005-11-04","2006-03-22"]
[6964,25048,"Network selection enhancements (NSP) - UE Conformance Testing","NSP-CR_UEConTest",1,"Rel-7","R5","2007-06-01","2008-12-05",1,"RP-080135","RP-080819","Nokia","jarkko.hellsten@nokia.com","RP#42 completed. Testing for Feature UID_7041 (NSP-CR)","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2008-12-09"]
[6967,11048,"   Stage 3 CN aspects of ACBOP","ACBOP",2,"Rel-7","C1","2005-06-06","2006-01-31",1,"-","-","-","-","-",24.007999999999999,null,null,null,null,"2004-09-02","2008-07-15"]
[6968,20010,"   Deleted - Potential impact on Iu interface Overload functionality","ACBOP",2,"Rel-7","RP","2004-03-15","2004-03-15",1,"-","-","-","-","-",25.413,null,null,"RP-25",null,"2004-04-14","2004-10-13"]
[6971,32074,"System enhancements for Fixed Broadband access to IMS","FBI",1,"Rel-7","S2,S3,S5,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"SP-060145","-","-","-","-","-",null,null,null,null,"2003-06-09","2004-10-21"]
[6974,11050,"      Protocol impact of FBI for TISPAN R1","-",3,"Rel-7","S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","-",null,null,null,null,"2004-09-03","2006-02-16"]
[6978,14020,"         CT4 aspects of FBI for TISPAN R1","FBI-TIS1-st3-c4",4,"Rel-7","C4","2006-01-13","2007-03-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","CT4#32: a set of CRs on FBI for cable labs",29.228999999999999,null,null,null,null,"2004-09-03","2007-03-08"]
[6981,7003,"      Stage 1,2 of FBI for PacketCable","-",3,"Rel-7","S2","2006-02-01","2006-12-15",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","-","22.228, 23.228",null,null,null,null,"2006-02-16","2006-09-19"]
[6985,32094,"   FS on SMSIP","-",2,"Rel-7","S2","2004-10-14","2005-06-13",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID",23.803999999999998,null,null,null,null,"2005-06-07","2008-07-15"]
[6988,310002,"      CT1 aspects for SMSIP","-",3,"Rel-7","C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","23.040, 24.229",null,null,null,null,"2006-04-13","2008-07-15"]
[6991,32102,"   Deleted - TR for PCC","-",2,"Rel-7","S2","2004-10-14","2005-12-29",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-30: S2 has no intention for TR completion",23.803000000000001,null,null,"SP-33",null,"2005-07-01","2008-07-18"]
[6992,32103,"   Stage 2 for PCC","-",2,"Rel-7","S2","2005-07-04","2006-09-15",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.",23.202999999999999,null,null,null,null,"2005-07-01","2008-07-18"]
[6995,13029,"   Gx reference point for Policy and Charging Control","PCC-Gx",2,"Rel-7","C3","2005-12-02","2007-11-30",1,"CP-060434","-","Siemens","Thomas.Belling@nsn.com","-","29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208)",null,null,null,null,"2005-12-13","2008-07-18"]
[6999,32091,"Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC",1,"Rel-7","S2,S1,S5,C1,C4","2004-12-31","2007-06-15",1,"SP-060292","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","WID approved SP#27¦updated SP#28¦updated SP#32","-",null,null,null,null,"2005-06-07","2008-07-21"]
[7002,32105,"   Stage 2 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S2","2005-09-06","2006-09-08",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",23.206,null,null,null,null,"2005-07-01","2008-07-21"]
[7005,11066,"      CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C1","2006-02-01","2007-06-15",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-","24.206, 24.216",null,null,null,null,"2005-10-04","2008-07-21"]
[7009,320002,"   Deleted - Study on Stage 2 for One Tunnel solution","OPTUNEL-Study",2,"Rel-7","S2","2006-03-27","2006-09-15",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","TR for Info SP-33. SP-34: S2 Report intention to discontinue TR",23.809000000000001,null,null,"SP-34",null,"2004-08-30","2008-07-15"]
[7012,320029,"CSI Terminating Session handling","CSItermS",1,"Rel-7","S2,C1","2006-06-08","2007-06-15",1,"SP-060437","-","Samsung","Osok Song","Triggered by the abandoned Study UID_32117 ","-",null,null,null,null,"2006-07-19","2008-07-17"]
[7015,340011,"   Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling","-",2,"Rel-7","C1","2007-03-09","2007-03-09",1,"CP-060647","-","Samsung","chenho.chin@samsung.com","CP-34 approved WID ","24.229, 24.179, 24.279",34,null,"CP-34",null,"2006-12-18","2008-07-17"]
[7016,33022,"Liberty Alliance and 3GPP Security Interworking","LibSec",1,"Rel-7","S3","2005-03-10","2006-11-30",1,"SP-050145","-","Nokia","Silke.Holtmanns@nokia.com","WID approved SP#27.",33.979999999999997,null,null,null,null,"2005-03-24","2008-07-16"]
[7020,33028,"Key establishment between a UICC and a terminal","KeyEstUTerm",1,"Rel-7","S3","2005-12-07","2006-09-28",1,"SP-050780","-","Gemalto","mireille.pauliac@gemplus.com","-",33.11,null,null,null,null,"2005-12-12","2008-01-10"]
[7022,732030,"Security enhancements","SEC7",1,"Rel-7","S3,C1,C4","2005-09-12","2006-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2005-11-04","2008-07-16"]
[7025,732033,"   Generic Authentication Architecture usage extensions and optimizations","SEC7-GAA2",2,"Rel-7","S3","2005-09-12","2006-11-30",1,"SP-060429","-","Nokia","Silke.Holtmanns@nokia.com","33.223 goes to R8","33.220, 29.109, 24.109, (33.223 goes to R8)",null,null,null,null,"2005-11-04","2008-07-16"]
[7028,310005,"      TCAPsec Gateway","SEC7-TCAP",3,"Rel-7","C4","2006-04-03","2006-08-14",1,"CP-060170","-","Siemens","Ulrich.wiehe@gksag.de","-","29.204, 29.002",null,null,null,null,"2005-10-07","2008-07-16"]
[7032,7045,"   CT4 aspects of VGCSFlex","VGCSFlex-c4",2,"Rel-7","C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","-",29.001999999999999,null,null,null,null,"2006-03-22","2008-07-21"]
[7035,13033,"Interworking between the 3GPP CS domain with BICC or ISUP as signalling protocol and external SIP-I networks","ExtSIPI",1,"Rel-7","C3","2006-09-22","2008-07-22",1,"CP-070101","-","Siemens","Thomas.Belling@nsn.com","-",29.164000000000001,null,null,null,null,"2006-10-06","2008-04-17"]
[7038,11061,"   CT1 aspects of Mp","-",2,"Rel-7","C1","2006-02-13","2006-02-13",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-",24.228999999999999,null,null,null,null,"2003-01-13","2008-07-15"]
[7039,13026,"   Deleted - CT3 aspects of Mp","-",2,"Rel-7","C3","2006-09-22","2006-09-22",1,"-","-","Ericsson","philip.hodges@ericsson.com","CP#34: CT3 not involved in Mp interface definition",29.161999999999999,null,null,"CP-33",null,"2003-01-13","2008-07-15"]
[7042,340016,"Routeing of MT-SMS via the HPLMN","SMSviaH",1,"Rel-7","C4,C1","2006-12-01","2007-03-09",1,"CP-070032","-","Vodafone","Nick.Russell@vodafone.com","WID approved in CP#34","23.040, 29.002",34,null,null,null,"2005-10-07","2007-09-12"]
[7046,330001,"High speed interface between the UICC and the ME","HSI",1,"Rel-7","C6","2006-09-22","2007-11-30",1,"CP-070259","-","Gemalto","jacques.seif@GEMALTO.COM","Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45",31.100999999999999,null,null,null,null,"2006-09-21","2008-01-11"]
[7049,34034,"3G-324M Video Telephony Call Setup Times Improvements","VTCSTI",1,"Rel-7","S4","2005-06-08","2006-09-27",1,"SP-050404","-","Vodafone","edward.hall@vodafone.co.uk","-",26.911000000000001,null,null,null,null,"2005-06-16","2006-11-29"]
[7052,34036,"End-to-End Multimedia Services Performance Metrics","E2EMSPM",1,"Rel-7","S4","2005-09-28","2007-03-15",1,"SP-050433","-","China Mobile","zhangyanyf@chinamobile.com","-",26.943999999999999,null,null,null,null,"2005-10-04","2007-03-08"]
[7056,35044,"      Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050302","-","Motorola","-","-","32.731/2/3/5, 32.631/2/3/5",null,null,null,null,"2005-06-17","2007-03-29"]
[7059,35048,"      Delta synchronization between IRP Manager and IRP Agent (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050306","-","Siemens","-","-","32.391/2/3/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[7060,35049,"      Subscription Management (SuM) IRP Solution Sets","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-060739","-","Ericsson ","-","-","32.307/317/607/667/665, 32.101, 32.175",null,null,null,null,"2005-06-17","2007-03-29"]
[7063,35054,"      Deleted - Management of Legacy Equipment","-",3,"Rel-7","S5","2005-09-02","2006-12-15",1,"SP-050312","-","Siemens","-","Request to TSG#35 to STOP the WI","new 32.xxx",null,null,"SP-35",null,"2005-06-17","2007-03-29"]
[7066,35071,"      Repeater Network Resource Model (NRM) definition","-",3,"Rel-7","S5","2006-02-13","2006-12-07",1,"SP-050731","-","China Mobile","-","-","32.721/2/3/5",null,null,null,null,"2005-11-24","2007-03-29"]
[7070,35057,"      Performance measurements definition for CN CS","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050315","-","China Mobile","-","-","32.407, 32.408",null,null,null,null,"2005-06-17","2007-03-29"]
[7073,35060,"      ATM bearer network Performance measurements","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050318","-","ZTE","-","-","No impact on 32.404, 32.405, 32.406, 32.407 ",null,null,null,null,"2005-06-17","2007-03-29"]
[7076,35039,"   Rel-7 Trace Management","OAM7-Trace",2,"Rel-7","S5","2005-09-02","2007-06-15",1,"SP-050628","-","Vodafone","-","-","-",null,null,null,null,"2002-11-08","2007-03-29"]
[7080,11046,"      Deleted - SIP enhancements for trace","-",3,"Rel-7","C1","2007-06-15","2007-06-15",1,"-","-","-","-","combined with UID 11067","-",null,null,"CP-32",null,"2004-03-01","2006-11-29"]
[7083,320008,"   Alternate Charged Party (ACP) for IMS","CH7-IMS-ACP",2,"Rel-7","S5","2006-05-22","2007-06-14",1,"SP-060442","-","Lucent","njmazzarella@alcatel-lucent.com","-","32.240, 32.260, 32.298, 32.299",null,null,null,null,"2006-05-22","2007-06-22"]
[7084,330004,"   Align 3GPP Charging with OMA PoC Enabler Release 2.0","CH7-PoC",2,"Rel-7","S5","2006-09-28","2007-06-14",1,"SP-060546","-","Siemens","Gerald.Goermer@nsn.com","09/2006 SP#33 WID approved","32.240, 32.272, 32.299, 32.298",null,null,null,null,"2006-10-09","2007-06-22"]
[7087,22003,"   MIMO - Layer 2,3 aspects","MIMO-L23",2,"Rel-7","R2","2003-09-12","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037",25.876000000000001,null,null,null,null,"2003-03-27","2008-06-24"]
[7090,25036,"   UE Conformance Testing for Multiple Input Multiple Output antennas (MIMO)","MIMO-UEConTest",2,"Rel-7","R5","2007-03-09","2008-03-07",1,"-","-","Qualcomm","svora@qualcomm.com","BB place holder for a number of RAN5 Tasks","-",null,null,null,null,"2007-03-19","2010-06-16"]
[7094,20067,"   UMTS 2.6 GHz 7.68 Mcps TDD","RInImp-UMTS26VHCRTDD",2,"Rel-7","R4","2006-06-15","2006-09-15",1,"RP-060349","RP-060451","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#33 completed","25.102, 25.105, 25.123, 25.113, 25.142, 34.124",null,null,null,null,"2006-06-21","2010-07-27"]
[7097,20027,"   UMTS 900 MHz","RInImp-UMTS900",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040541","RP-050662","Nortel","Yannick Li (yli@nortelnetworks.com)","RP#30 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,null,null,"2005-01-04","2010-07-27"]
[7101,20062,"   Additional minimum UE performance requirement for non-HSDPA channels based on type 1 enhanced receiver (Rx Diversity)","RInImp-RxDiv",2,"Rel-7","R4","2005-09-15","2006-12-15",1,"-","-","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","-",25.100999999999999,null,null,null,null,"2006-03-21","2008-06-24"]
[7104,7029,"      Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-EDCH",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060184","RP-060679","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[7107,25025,"Rel-7 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-7","R5","2005-11-11","2008-09-12",1,"-","-","-","-","Linked to Feature UID_20028 (RInImp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[7108,25007,"   UE Conformance Test for UMTS 2600 MHz","RInImp-UMTS2600_Test",2,"Rel-7","R5","2005-11-11","2006-06-02",1,"-","-","Nokia","Aleksi.Heino@nokia.com","RP#32 completed","34.108, 34.121",null,null,null,null,"2002-02-28","2006-03-21"]
[7111,25020,"   UE antenna Over The Air (OTA) conformance testing","RInImp-UEAnt_Test",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060486","RP-080535","Nokia","Aleksi.Heino@nokia.com","RP#41 completed (GERAN aspects might need to be included later)",34.113999999999997,null,null,null,null,"2006-09-20","2008-09-14"]
[7114,25039,"   Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-UEConTest_RxDivEDCH",2,"Rel-7","R5","2007-06-01","2007-12-07",1,"RP-070414","RP-070810","Motorola","carolyn.taylor@motorola.com","RP#38 completed","-",null,null,null,null,"2006-09-20","2007-09-11"]
[7118,20031,"   Delay optimization for procedures applicable to CS and PS Connections","RANimp-DelayOpt",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050386","RP-060453","Nokia","juho.pirskanen@nokia.com","RP#33 completed","25.815, 25.321, 25.322, 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[7121,20046,"   Continuous connectivity for packet data users","RANimp-CPC",2,"Rel-7","R1","2005-03-14","2007-03-15",1,"RP-050870","RP-070033","Siemens","Joern.Krause@siemens.com ","RP#35 completed","25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133",null,null,null,null,"2005-10-05","2010-07-27"]
[7125,340038,"   64QAM for HSDPA (FDD)","RANimp-64QamDownlink",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070223","RP-070287","Ericsson","Johan.Bergman@ericsson.com","RP#36 completed","25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141",null,null,null,null,"2006-10-06","2010-07-27"]
[7128,20066,"   Interface to control Tower Mounted Amplifiers (TMAs)","RANImp-TMA",2,"Rel-7","R3,S5","2006-06-02","2007-06-15",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[7131,25026,"Rel-7 RAN improvements - UE Conformance Testing","-",1,"Rel-7","R5","2006-09-20","2009-09-18",1,"-","-","-","-","Linked to Feature UID_20029 (RANimp) ","-",null,null,null,null,"2006-09-22","2010-07-27"]
[7132,25021,"   Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink","RANimp-UEConTest_EDCHTDH",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060484","RP-080536","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7135,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7138,20014,"7.68 Mcps TDD option","VHCRTDD",1,"Rel-7","R1,R2,R3,R4,R5","2004-09-15","2007-09-14",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","-",null,null,null,null,"2004-09-27","2010-07-27"]
[7142,20018,"   VHCRTDD: UTRAN Iub/Iur Protocol Aspects","VHCRTDD-IurIub",2,"Rel-7","R3","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Peter Legg (plegg@ipwireless.com)","RP#31 completed","25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435",null,null,null,null,"2004-09-27","2010-07-27"]
[7145,20035,"3.84 Mcps TDD Enhanced Uplink","EDCHTDD",1,"Rel-7","RP","2005-03-15","2006-09-15",1,"RP-050100","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7149,20039,"   EDCHTDD: UTRAN Iub/Iur Protocol Aspects","EDCHTDD-IurIub",2,"Rel-7","R3","2005-03-15","2006-09-15",1,"-","RP-060462","Interdigital","jim.miller@interdigital.com","RP#33 completed","25.401, 25.420, 25.423, 25.427, 25.430, 25.433, 25.435",null,null,null,null,"2005-03-15","2010-07-27"]
[7152,20056,"   1.28 Mcps TDD Enhanced Uplink: Physical Layer","LCRTDD-EDCH-Phys",2,"Rel-7","R1","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Ke Wang ","RP#35 completed","25.201, 25.221, 25.222, 25.223, 25.224, 25.225",null,null,null,null,"2006-03-21","2010-07-27"]
[7155,20059,"   1.28 Mcps TDD Enhanced Uplink: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","LCRTDD-EDCH-RF",2,"Rel-7","R4","2006-03-15","2007-06-15",1,"-","RP-070296","CATT","Yuexia Song (songyuexia@catt.cn)","RP#36 completed","25.102, 25.105, 25.123, 25.142",null,null,null,null,"2006-03-21","2010-07-27"]
[7156,350146,"   1.28 Mcps TDD Enhanced Uplink - UE Conformance Testing","LCRTDD-EDCH-UEConTest",2,"Rel-7","R5","2007-09-20","2008-09-12",1,"RP-070724","RP-080539","CATT","chenxiaozhong@datangmobile.cn","RP#41 completed","34.108, 34.122, 34.123-1/2/3",null,null,null,null,"2006-03-21","2010-07-27"]
[7159,50119,"Lower 700 MHz Inclusion in the GERAN Specifications","GSM710",1,"Rel-7","GP","2005-01-03","2006-06-30",1,"GP-050543","-","UTC","dcotton@mtview.union-tel.com","-","-",null,null,null,null,"2005-02-01","2006-09-19"]
[7163,55094,"      G3 aspects of GSM710","-",3,"Rel-7","G3new","2005-08-31","2006-06-30",1,"-","-","-","-","-",51.01,null,null,null,null,"2005-12-20","2006-07-17"]
[7166,51137,"   Definition of radio resource management functionality for Support of Conversational Services in A/Gb mode via the PS domain","SCSAGB-RRM",2,"Rel-7","G1","2005-04-08","2007-08-31",1,"GP-061502","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,null,null,"2005-04-21","2008-01-10"]
[7169,52139,"   Deleted- Modifications to FLO","SCSAGB-FLO",2,"Rel-7","G2","2006-07-17","2006-07-17",1,"GP-051165","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,"SP-32",null,"2005-04-21","2006-03-09"]
[7173,53082,"   Changes to BTS testing specification","TGSM810-BTStest",2,"Rel-7","G1","2005-04-08","2005-11-11",1,"GP-050948","-","Huawei","chende@huawei.com","-",51021,null,null,null,null,"2005-04-21","2005-12-22"]
[7176,55095,"   Deleted - MS Conformance Testing","HODSRDTM-MStest",2,"Rel-7","G3new","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","Stopped, no work done. 12/2008 Marked as stopped (\"deleted\")","51-010",null,null,"GP-32",null,"2005-11-21","2008-12-15"]
[7179,50571,"   Performance Requirements for Mobile Station Receive Diversity, DARP Phase II","MSRD2-PerfReq",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060115","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",45.005000000000003,null,null,null,null,"2005-11-21","2007-03-08"]
[7180,50572,"   Capability signalling of Mobile Station Receive Diversity, DARP Phase II","MSRD2-CapSig",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060116","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",24.007999999999999,null,null,null,null,"2005-11-21","2007-03-08"]
[7183,50579,"Downlink Dual Carrier","GDCDL",1,"Rel-7","GP","2006-01-20","2009-09-04",1,"GP-061331","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#35 completed","-",null,null,null,null,"2006-01-24","2009-04-01"]
[7187,50580,"Support of SIGTRAN in GERAN","GSIGT",1,"Rel-7","GP","2006-01-20","2006-06-30",1,"GP-060450","-","Ericsson","peter.ostrup@ericsson.com","GP#30 completed","48.001, 48.006, 43.059, 49.031",null,null,null,null,"2006-01-24","2009-04-02"]
[7190,52146,"   Reduced TTI","LATRED-REDTTI",2,"Rel-7","G2","2006-06-30","2007-08-31",1,"GP-061521","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021",null,null,null,null,"2006-07-05","2008-12-15"]
[7193,51140,"   Stage 2 for HUGE","HUGE-Stage2",2,"Rel-7","G1","2006-09-08","2007-09-07",1,"GP-061902","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#35 completed","43.055, 43.064",null,null,null,null,"2006-09-13","2008-12-15"]
[7197,51143,"   BTS Conformance Test for HUGE","HUGE-BTStest",2,"Rel-7","G1","2006-09-08","2009-09-04",1,"GP-061907","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#43 completed",51.021000000000001,null,null,null,null,"2006-09-13","2009-09-07"]
[7200,51144,"   Stage 2 for REDHOT","REDHOT-Stage2",2,"Rel-7","G1","2006-11-17","2007-08-31",1,"GP-062489","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#35 completed","43.055, 43.064",null,null,null,null,"2006-11-20","2008-12-15"]
[7201,51145,"   Stage 3 for REDHOT","REDHOT-Stage3",2,"Rel-7","G1","2006-11-17","2008-05-16",1,"GP-062490","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#38 completed","24.008, 44.018, 44.060, 45.001, 45.002, 45.003, 45.004, 45.005, 45.008",null,null,null,null,"2006-11-20","2008-12-15"]
[7204,60110,"(Small) Technical Enhancements and Improvements for Rel-7","TEI7",1,"Rel-7","SP,CP,RP,GP","2007-03-26","2007-03-26",1,"-","-","-","-","-","-",null,null,null,null,"2005-11-04","2006-04-20"]
[7207,32114,"   Deleted - IMS aspects to support IMS Emergency sessions","-",2,"Rel-7","S2","2006-06-23","2006-06-23",1,"SP-050604","-","Nokia","curt.c.wong@nokia.com","Approved at SP#29","23.867, 23.abc, 23.060, 23.002, 23.271",null,null,"SP-30",null,"2005-03-22","2005-12-22"]
[7211,11035,"   Deleted - Stage 3 for IMS Local services","-",2,"Rel-7","C1","2006-01-06","2006-01-06",1,"-","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,"SP-25",null,"2003-01-13","2004-09-09"]
[7214,14018,"Deleted: Generic User Profile Phase 2","-",1,"Rel-7","C4","2005-08-08","2006-06-30",1,"-","-","-","-","Created at TSG#27 by A. Sultan because of the move to Rel-7 of \"Common Objects\". ","-",null,null,"SP-27",null,"2005-03-09","2005-03-09"]
[7217,31082,"Study on Multimedia Telephony Capabilities for IMS","MITE",1,"Rel-7","S1","2005-07-11","2006-07-31",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","Spin-off Feature UID_7038 (MTSI)",22.972999999999999,null,null,null,null,"2005-04-21","2008-07-01"]
[7221,31075,"Study on Videotelephony teleservice","VidTel",1,"Rel-7","S1","2005-03-01","2006-01-17",1,"SP-050506","-","T-Mobile","michael.kurz@t-mobile.at ","-",22.902999999999999,null,null,null,null,"2005-03-22","2008-06-27"]
[7224,31083,"Study on Transferring of emergency Call data","eCALL",1,"Rel-7","S1","2005-07-11","2006-03-31",1,"SP-050388","-","Motorola","jian.j.wu@motorola.com ","-",22.966999999999999,null,null,null,null,"2005-06-20","2010-08-31"]
[7225,32073,"Study on Enhancement of E2E QoS","QoS7",1,"Rel-7","S2","2004-06-28","2005-09-15",1,"SP-040326","-","Huawei","Robert Jaksa","-",23.802,null,null,null,null,"2004-08-30","2008-06-30"]
[7228,35068,"Study on IRP Information Model","OAM7-NIM-IM",1,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050611","-","Motorola","trevor.pirt@motorola.com ","SP#35 completed",32.81,null,null,null,null,"2005-09-16","2010-07-27"]
[7231,7025,"Feasibility Study on the TCAPsec Gateway concept","FS_SEC7-TCAP",1,"Rel-7","C4","2005-10-28","2006-03-10",1,"CP-050687","-","Siemens","Ulrich.wiehe@gksag.de","TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway",29.8,null,null,null,null,"2005-10-07","2008-07-01"]
[7235,330003,"   CT3 aspects of NcSIP","-",2,"Rel-7","C3","2006-05-15","2007-09-14",1,"CP-070034","-","Ericsson","ragnar.huslende@ericsson.com","-",29.802,null,null,null,null,"2006-09-21","2008-07-01"]
[7238,20041,"Study on UTRA Tower Mounted Amplifier (FDD)","RANFS-TMA",1,"Rel-7","R4","2005-06-15","2006-03-14",1,"RP-050387","RP-060035","Ericsson","Klas.Sjerling@ericsson.com","RP#31 (Mar 2006) completed. SR in RP-060035",25.818000000000001,null,null,null,null,"2005-06-20","2010-07-27"]
[7241,20052,"Deleted - Study on Performance Improvements in Small Cells using HSDPA/EDCH","SMALLCELLS",1,"Rel-7","R1,R4","2005-12-15","2006-06-15",1,"RP-050782","RP-060263","Cingular","Marc Grant","RP#32 (Jun 2006) stopped at 0% completion","none",null,null,"SP-69",null,"2005-12-15","2008-06-23"]
[{"$f":"A7245+1","v":7245},50568,"Study on Future GERAN Evolution","FGE",1,"Rel-7","GP","2005-04-08","2007-02-16",1,"GP-051052","-","Nokia","eddie.riddington@nokia.com","GP#33 completed",45.911999999999999,null,null,null,null,"2005-04-21","2007-03-08"]
[7248,31077,"Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN)","PNPAN",1,"Rel-7","S1","2005-12-08","2005-12-08",1,"SP-050386","-","Vodafone","armin.toepfer@vodafone.com","-","-",null,null,"SP-30",null,"2005-04-21","2005-12-22"]
[7249,31087,"Deleted - Study on Customised Alerting Tone (CAT) Requirements (was duplicated)","-",1,"Rel-7","S1","2006-06-30","2006-06-30",1,"SP-050607","-","-","-","Awaiting MCC SA3 input","-",null,null,"SP-31",null,"2005-11-04","2006-03-22"]
[7252,32058,"   Deleted - TR on Stage 2","-",2,"Rel-7","S2","2005-06-30","2005-06-30",1,"-","-","-","-","-","-",null,null,"SP-25",null,"2003-07-23","2004-10-21"]
[7255,32099,"Deleted - VoIMS bearer related enhancements","VoIMS",1,"Rel-7","S2","2006-07-21","2006-07-21",1,"-","-","-","-","Created by MCC to group all VoIMS related items, after consultation of chairs","-",null,null,"SP-32",null,"2005-09-15","2008-06-25"]
[7259,34040,"Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) ","-",1,"Rel-7","S4","2007-06-22","2007-06-22",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP-38 stopped",26.966999999999999,null,null,"SP-38",null,"2006-12-10","2007-06-22"]
[7261,360009,"Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053)","RANFS-InterfCanc",1,"Rel-7","R4","2007-03-28","2007-03-28",1,"-","-","-","-","Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD)","-",null,null,"SP-38",null,"2007-06-21","2008-01-10"]
[7265,20032,"   Improved support of IMS Realtime Services using HSDPA/EDCH","RInImp-IMSRealTime",2,"Rel-6","R2","2005-03-15","2005-12-14",1,"-","-","Cingular","Don Zelmer (dz1069@att.com)","-","-",null,null,null,null,"2005-06-20","2006-01-13"]
[7268,1476,"      FDD Base station classification","-",3,"Rel-6","R4","2000-08-14","2002-12-04",1,"-","-","Nokia","antti.toskala@nokia.com","-","25.104, 25.141",null,null,null,null,"2000-07-26","2004-07-08"]
[7271,24010,"   UMTS 1.7/2.1 GHz","RInImp-UMTS1721",2,"Rel-6","R4","2003-03-14","2003-03-14",1,"-","-","Nokia","jussi.numminen@NOKIA.COM","Introduction of UMTS1700/2100 (Band IV)","25.101, 25.104, 25.133, 25.141, 25.307, 25.331",null,null,null,null,"2003-10-02","2009-07-09"]
[7272,25010,"   Conformance Test Aspects – UMTS 1.7/2.1 GHz Band","RInImp-UMTS1721_Test",2,"Rel-6","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","TS34.121, TS34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[7275,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7278,3,"Rel-6 RAN Feasibility Studies","-",1,"Rel-6","RP","2000-08-14","2005-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-07","2003-12-07"]
[7282,21003,"   FS for the analysis of OFDM for UTRAN enhancement","RInImp-FSOFDM",2,"Rel-6","R1","2002-06-10","2004-06-14",1,"-","-","Nortel","Sarah Boumendil","-",25.891999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7285,24011,"   FS on Low Output Powers for general purpose FDD BSs","RInImp-FSLoPw",2,"Rel-6","R3","2003-06-13","2004-03-12",1,"-","-","Telefónica","Ana Burgos (burgos_a@tsm.es)","-",25.806999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7289,20003,"FDD Enhanced Uplink","EDCH",1,"Rel-6","R2,R1,R3,R4,R5","2004-03-15","2007-09-14",1,"-","-","Ericsson","Joakim Bergström ","-","-",null,null,null,null,"2004-03-18","2004-07-08"]
[7292,20006,"   FDD Enhanced Uplink - Layer 2 and 3 Protocol Aspects","EDCH-L23",2,"Rel-6","R2","2004-03-15","2005-03-14",1,"-","-","Ericsson","Joakim Bergström ","-","25.301, 25.302, 25.306, 25.321, 25.331",null,null,null,null,"2004-03-18","2005-03-25"]
[7295,25003,"   Conformance Test Aspects – FDD Enhanced Uplink","EDCH_Test",2,"Rel-6","R5","2005-06-03","2007-09-14",1,"-","-","Ericsson","Leif.Mattisson@ericsson.com","-","34.108, 34.109, 34.121, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-03-18","2010-06-16"]
[7296,9,"Rel-6 RAN improvements","-",1,"Rel-6","RP,S5","2002-09-09","2005-03-14",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2000-03-31","2004-07-08"]
[7299,21009,"      optimization of channelisation code utilisation for 3.84 Mcps TDD","RANimp-RABSE-CodOptTDD",3,"Rel-6","R1","2004-03-15","2005-03-14",1,"-","-","IPWireless","Nicholas Anderson","WIDS modified in RP#26, RP-040551","-",null,null,null,null,"2004-03-18","2006-01-13"]
[7302,23005,"      Deleted - Improvement of RRM across RNS and RNS/BSS","RANimp-RRM1",3,"Rel-6","R3","2003-12-05","2003-12-05",1,"-","-","Nokia","antti.toskala@nokia.com","abandoned RP-23","-",null,null,"RP-23",null,"2004-10-19","2004-10-21"]
[7306,23010,"   Remote Control of Electrical Tilting Antennas","RANimp-TiltAnt",2,"Rel-6","R3,S5","2003-03-14","2004-09-16",1,"-","-","Vodafone","Andreas.Hauser@vodafone.com","-","-",null,null,null,null,"2003-03-27","2004-04-14"]
[{"$f":"A7309+1","v":7309},23011,"   Network Assisted Cell Change (NACC) from UTRAN to GERAN - network-side aspects","RANimp-NACC",2,"Rel-6","R3","2002-09-09","2004-06-15",1,"-","-","Vodafone","Brendan.McWilliams@gb.vodafone.co.uk","-","-",null,null,null,null,"2003-03-27","2004-07-08"]
[7313,32053,"      Stage 3 - impacts MLP (Mobile Location Protocol) ","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7316,32054,"      Stage 3 - impacts MLP and RLP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7319,32055,"      Stage 3 - definition of RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7320,32012,"   Location Services support for IMS public identities","-",2,"Rel-6","S2,OMA","2003-02-24","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-01-24","2012-05-21"]
[7323,32026,"   New area event for location service triggering reports","-",2,"Rel-6","S2,N4,OMA","2002-06-03","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-05-21"]
[7327,20001,"   UE positioning for Location Services enhancements 2","LCS2-UEpos",2,"Rel-6","R2,R4,R5","2001-01-15","2004-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-16","2012-05-21"]
[7330,22002,"      Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods","LCS2-UEpos-FSBlank",3,"Rel-6","R2","2002-07-01","2003-09-19",1,"-","-","Cambridge Positioning Systems","david.bartlett@cursor-system.com","RP#38 Work stopped","new 25.894",null,null,"RP-38",null,"2002-06-21","2012-05-21"]
[7333,1571,"Rel-6 Security enhancements","SEC16",1,"Rel-6","S3","2001-01-03","2004-11-26",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID. Acronym changed from \"SEC1, Rel-6\"","-",null,null,null,null,"2000-04-09","2015-03-24"]
[7337,33007,"         Rel-6 IP network layer security (NDS/IP)","SEC1-NDS-IP",4,"Rel-6","S3","2002-06-17","2003-09-25",1,"SP-000420","-","-","-","SP#9 approved WID S3-000626 (Access security for IP-based services)",33.21,null,null,null,null,"2002-11-08","2011-08-08"]
[7340,33020,"Network Domain Security; MAP application layer security (NDS/MAPsec)","MAPSEC",1,"Rel-6","S3","2004-07-06","2004-12-29",1,"SP-040280","-","Vodafone","Peter.Howard@vodafone.com","SP#19 approved WID. Marked as closed 12/2008 (was marked 20% complete)",33.200000000000003,null,null,null,null,"2003-07-25","2011-08-08"]
[7343,25009,"   Conformance Test Aspects – IMS Call Control Rel-6 enhancements","IMS2_CCR_Test",2,"Rel-6","R5","2006-03-10","2007-09-14",1,"-","-","Ericsson","Jacob.John@motorola.com, Leif.Mattisson@ericsson.com","-","34.229-1, 34.229-2, 34.229-3, 34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[7344,31025,"   IMS Group Management","IMSGM",2,"Rel-6","S1","2002-03-14","2004-12-08",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7347,11036,"      Stage 3 for IMS Group management (e.g. chat)","-",3,"Rel-6","N1","2002-12-13","2004-12-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Depends on CN decision on CPCP in Rel-6. Complete, if unresolved IETF dependencies are dropped (-> LS to CN plenary)","-",null,null,null,null,"2003-01-13","2005-03-25"]
[7351,31022,"   IMS Messaging","IMSM",2,"Rel-6","S1","2002-03-14","2005-12-30",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7354,31033,"      CRs to 22.140 & 22.228","IMSM-CR",3,"Rel-6","S1","2002-03-14","2003-03-17",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","22.140,22.228",null,null,null,null,"2003-01-13","2010-09-07"]
[7357,60001,"      SIP/SIMPLE Instant messaging","-",3,"Rel-6","OMA","2004-01-01","2005-12-30",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040232","-",null,null,null,null,"2004-06-08","2005-03-25"]
[7361,11052,"      Procedured associated with IMS-ALG","-",3,"Rel-6","N1","2004-09-06","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2005-04-20","2005-06-02"]
[7364,13004,"      Interworking for 3GPP_SIP and IETF_SIP","-",3,"Rel-6","N3","2000-08-28","2003-06-13",1,"-","-","Siemens","Thomas.Belling@nsn.com","[DAB - 20.08.03] - CN Part of TR Complete @ CN#20","New 29.962",null,null,null,null,"2002-02-28","2003-09-15"]
[7365,13005,"      Interworking for IPv6 to IPv4","-",3,"Rel-6","N3","2000-08-28","2004-12-08",1,"-","-","-","-","-",29.163,null,null,null,null,"2002-02-28","2005-03-09"]
[7368,2047,"   Interworking between IMS and CS networks","IMS-CCR-IWCS",2,"Rel-6","N3","2000-08-28","2004-03-18",1,"NP-030292","-","Vodafone","Brendan.McWilliams@gb.vodafone.co.uk","[DAB - 25.05.04] - CN3 consider this work to be complete","29.163, 29.061, 24.228, and New CN4 specification",null,null,null,null,"2002-01-24","2004-09-09"]
[7371,33012,"   Lawful Interception in Rel-6 architecture","SEC1-LI",2,"Rel-6","S3","2002-12-09","2003-12-18",1,"SP-030106","-","Reg TP, Nortel","berthold.wilhelm@regtp.de, Ron Ryan","Acronym changed from \"SEC1-LI, Rel6\"","33.106, 33.107, 33.108",null,null,null,null,"2003-01-15","2015-03-24"]
[7375,32027,"   Deleted - Stage 2 of IMS Phase 2","-",2,"Rel-6","S2","2003-09-19","2003-09-19",1,"SP-020544","-","-","-","-","-",null,null,"SP-21",null,"2004-10-19","2004-10-21"]
[7378,60002,"   Dependencies on OMA PoC","-",2,"Rel-6","OMA","2004-01-01","2005-02-28",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040232","-",null,null,null,null,"2003-10-15","2005-03-25"]
[7381,32062,"Study on Interworking aspects and migration scenarios for IPv4 based IMS Implementations","IPv4IMS",1,"Rel-6","S2","2003-09-08","2004-06-25",1,"SP-040327","-","Siemens","Alexander Milinski","-",23.981000000000002,null,null,null,null,"2003-10-15","2009-11-18"]
[7385,11033,"   Stage 3 for Interoperability and Commonality between IMS using different IP-connectivity Networks","-",2,"Rel-6","N1","2002-10-14","2003-12-12",1,"NP-020572","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2002-11-08","2004-03-12"]
[7388,32701,"   TR 23.976 on Push Architecture","-",2,"Rel-6","S2","2002-11-11","2004-02-27",1,"SP-030126","-","Research In Motion","Nick Alfano","-",23.975999999999999,null,null,null,null,"2002-09-26","2004-07-08"]
[7389,42009,"Rel-6 Multimedia Messaging (MMS) enhancements","MMS6",1,"Rel-6","T2,S1,S4,S5,OMA","2002-08-15","2005-12-07",1,"TP-030175","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2002-09-26","2004-12-06"]
[7392,42011,"   Technical realization of MMS6","-",2,"Rel-6","T2","2002-09-06","2004-12-10",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",23.14,null,null,null,null,"2002-09-26","2004-12-06"]
[7395,42014,"   Handling of private addressing schemes in MMS","-",2,"Rel-6","T2","2003-12-10","2004-12-10",1,"TP-030299","-","T-Mobile","Steffen.Habermann@T-MOBILE.DE","-",23.14,null,null,null,null,"2003-12-01","2004-12-06"]
[7399,42006,"   MExE Rel-6 Improvements and Investigations ","MEXE6-ENHANC",2,"Rel-6","T2","2002-03-08","2003-03-12",1,"TP-020017","-","TTPCom","Lars Brenk ( (lsb_ttpcom@HOTMAIL.COM)","-","-",null,null,null,null,"2002-03-21","2009-11-18"]
[7402,2499,"Presence Capability","PRESNC",1,"Rel-6","S1,S2,S3,S4,N1,N3,N4,OMA","2001-03-19","2005-12-07",1,"SP-010064","-","Motorola","Mark Cataldo","merged \"Presence Service Enhancements\" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date","-",null,null,null,null,"2001-03-30","2004-09-08"]
[7405,2503,"   Stage 3 for Presence Capability","-",2,"Rel-6","N1,N4","2002-04-01","2004-12-08",1,"NP-040492","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Dependency to 2 IETF drafts, no known work at the moment","New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328)",null,null,null,null,"2001-03-30","2011-08-09"]
[7409,60003,"   SIMPLE Presence","-",2,"Rel-6","OMA","2004-01-01","2005-03-31",1,"SP-040232","-","-","OMA-LIAISON@mail.openmobilealliance.org","SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables","-",null,null,null,null,"2004-06-08","2011-08-09"]
[7412,50080,"      Requirements for the support of conversational services","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[7413,50084,"      Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2003-01-13","2009-11-18"]
[7416,50082,"      Standardisation effort","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[7419,50064,"   Realisation of a Flexible Layer One","FLOGER-Real",2,"Rel-6","GP","2000-01-03","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[7423,51004,"      Channel Coding in 45.003 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7426,52071,"      Requirements in 44.004","-",3,"Rel-6","G2","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7430,52075,"   Security for a Flexible Layer One","FLOGER-SecFLO",2,"Rel-6","S3,G2","2002-04-19","2003-08-29",1,"GP-021021","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-01-14"]
[7433,55078,"      Deleted at TSG #27 - MS Test in 51.010","-",3,"Rel-6","G4,G5","2004-02-06","2004-02-06",1,"-","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-22",null,"2002-05-23","2005-03-09"]
[7436,50041,"Uplink TDOA feasibility study","TDOAF",1,"Rel-6","GP","2001-11-30","2002-06-28",1,"GP-012794","-","TruePosition","Bob Gross (rlgross@trueposition.com)","-",45.811,null,null,null,null,"2001-12-10","2003-04-24"]
[{"$f":"A7437+1","v":7437},2544,"Multimedia Broadcast and Multicast Service","MBMS",1,"Rel-6","S1,S2,S3,S4,S5,N1,N3,R2,R4,R5,T1,GP,G2,G3new","2001-05-11","2008-03-07",1,"-","-","-","-","SP#13 Title renamed","-",null,null,null,null,"2001-05-28","2012-07-26"]
[7440,32702,"      TR on MBMS Architectural Study","-",3,"Rel-6","S2","2001-09-24","2002-08-23",1,"-","-","-","-","-",23.846,null,null,null,null,"2002-09-26","2012-07-26"]
[7443,13015,"   Gmb interface for MBMS (CN3 part)","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"-","-","-","-","-",29.061,null,null,null,null,"2003-10-13","2012-07-26"]
[7447,31044,"      Stage 1 for MBMS User Services","-",3,"Rel-6","S1","2003-05-13","2004-04-01",1,"-","-","-","-","-",22.245999999999999,null,null,null,null,"2001-03-30","2012-07-26"]
[7450,20022,"      Introduction of MBMS in RAN (physical & upper layers, access network interfaces)","-",3,"Rel-6","R2","2002-01-01","2004-12-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","25.346, 25.304, 25.321, 25.322, 25.323",null,null,null,null,"2004-09-27","2012-07-26"]
[7454,25022,"      Conformance Test Aspects - MBMS for 3.84 Mcps and 7.68 Mcps TDD","MBMS-UEConTest_TDH",3,"Rel-6","R5,T1","2006-09-20","2007-12-07",1,"-","-","IPWireless","Timothy Speight (tspeight@ipwireless.com)","-","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2012-07-26"]
[7457,25038,"      Conformance Test Aspects - 1.28 Mcps TDD MBMS RF/RRM","MBMS-UEConTest_RFTDL",3,"Rel-6","R5,T1","2007-06-01","2007-12-07",1,"-","-","Datang","chenxiaozhong@datangmobile.cn","-","34.108, 34.109, 34.122",null,null,null,null,"2002-02-28","2012-07-26"]
[7460,52085,"      MBMS Re-synchronisation at cell change","-",3,"Rel-6","G2","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7461,50098,"      Simultaneous support of MBMS services","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7464,50087,"      MBMS Decision making process between point-to-point or point-to-multipoint configurations","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7467,50090,"      GERAN specific changes to the Iu-ps interface for MBMS","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7471,55091,"      Deleted - MS conformance tests - G5","-",3,"Rel-6","G5","2003-06-27","2003-06-27",1,"-","-","-","-","-","-",null,null,"GP-19",null,"2004-10-20","2012-07-26"]
[7474,32999,"   TR on Architectural impacts","-",2,"Rel-6","S2","2003-05-12","2004-03-02",1,"-","-","-","-","-",23.876999999999999,null,null,null,null,"2001-11-29","2004-07-08"]
[7478,31008,"Generic User Profile Rel-6","GUP",1,"Rel-6","S1,S3,N4","2001-10-08","2005-03-03",1,"SP-040515","-","-","-","-","-",null,null,null,null,"2001-10-09","2003-03-28"]
[7481,42002,"   Stage 2 - Data Description Method","-",2,"Rel-6","N4","2002-12-05","2005-03-03",1,"TP-020275","-","T-Mobile","kurt.bischinger@t-mobile.at","TR approved in CN#26",23.241,null,null,null,null,"2001-10-09","2005-03-09"]
[7484,31010,"Digital Rights Management","DRM",1,"Rel-6","S1,OMA","2001-10-08","2004-05-28",1,"SP-010577","-","-","-","Foreseen start and completion dates introduced by MCC (no indication at all on the WID)","-",null,null,null,null,"2001-10-11","2001-10-11"]
[7485,31011,"   Requirements for Digital Rights Management","-",2,"Rel-6","S1","2001-10-08","2002-06-13",1,"-","-","Openwave","nicholas.wood@openwave.com","-","-",null,null,null,null,"2001-10-11","2003-07-04"]
[7488,33001,"   Security for Digital Rights Management","-",2,"Rel-6","OMA","2002-06-17","2003-03-03",1,"-","-","-","-","SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17","-",null,null,null,null,"2001-10-11","2005-03-25"]
[7492,31035,"   Stage 1 for WLAN-UMTS Interworking Rel-6","WLAN-TS",2,"Rel-6","S1","2003-01-06","2004-06-11",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","-","22.101, 22.105",null,null,null,null,"2003-01-13","2004-06-08"]
[7495,14013,"   Stage 3 - CN4 aspects","WLAN-IW",2,"Rel-6","N4","2003-05-23","2004-09-01",1,"NP-030490","-","Nokia","raquel.rodriguez@nokia.com","WID approved at CN#19","29.234, 29.061",null,null,null,null,"2003-03-27","2005-03-09"]
[7498,11047,"   Stage 3 for scenario 3","-",2,"Rel-6","N1","2003-05-23","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-06-08","2005-03-09"]
[{"$f":"A7501+1","v":7501},31015,"Priority Service","PRIOR1",1,"Rel-6","S1","2002-05-30","2003-09-26",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-","-",null,null,null,null,"2002-02-27","2010-08-31"]
[7504,31043,"   Priority service implementation guide","-",2,"Rel-6","S1","2003-03-28","2003-09-26",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-",22.952000000000002,null,null,null,null,"2003-07-04","2010-08-31"]
[7507,31038,"   Stage 1 - CRs to implement Network Sharing","NTSharCR",2,"Rel-6","S1","2003-01-20","2003-12-19",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","22.011, 22.101, 22.115, 22.129",null,null,null,null,"2003-03-14","2009-11-10"]
[7508,32044,"   Stage 2 for Network Sharing ","-",2,"Rel-6","S2","2003-02-27","2004-07-30",1,"SP-030123","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","23.002, 23.060, 23.221, 23.236, new 23.251, 23.851",null,null,null,null,"2003-03-27","2009-11-10"]
[7511,25004,"   Conformance Test Aspects – Network Sharing","NTShar-UTRANEnh_Test",2,"Rel-6","R5","2005-03-11","2006-03-10",1,"-","-","TeliaSonera","Niklas.Wiren@TeliaSonera.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[7515,13016,"   Gq interface specification for Dynamic Policy control enhancements – Stage 3","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"NP-030198","-","Nokia","Anna.Sillanpaai@nokia.com","[DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004","29.207, 29.208, 29.209",null,null,null,null,"2003-10-13","2005-03-09"]
[7518,32706,"   Architecture review","-",2,"Rel-6","S2","2002-10-14","2002-11-14",1,"-","-","Nokia","-","-","-",null,null,null,null,"2002-09-26","2009-11-10"]
[7521,60007,"   OMA dependencies on Subscriber certificates","-",2,"Rel-6","OMA","2004-01-01","2004-06-08",1,"-","-","Nokia","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040420","-",null,null,null,null,"2004-06-08","2009-11-10"]
[7525,15026,"   Multi Media Messaging function","-",2,"Rel-6","N5","2002-10-31","2004-09-10",1,"-","-","-","-","-","29.198-15",null,null,null,null,"2003-01-13","2005-01-13"]
[7528,15032,"   OSA interfaces at different levels of abstractions (Parlay X, Web services)","-",2,"Rel-6","N5","2003-07-14","2004-09-10",1,"-","-","-","-","-",29.199000000000002,null,null,null,null,"2003-03-27","2005-01-13"]
[7529,15033,"   Introduction of migration support mechanism","-",2,"Rel-6","N5","2002-10-31","2003-12-10",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-03-27","2005-01-13"]
[7532,15037,"   Deleted - TR on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2004-09-17","2004-09-17",1,"-","-","-","-","N5#26:TR Completion 09/04¦consistent with CN1 delayed Rel-6 completion.","-",null,null,"NP-24",null,"2004-10-20","2004-10-21"]
[7535,51102,"      Changes to core specs","-",3,"Rel-6","G1","2002-11-15","2002-12-20",1,"GP-022073","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2003-02-13"]
[7539,51131,"   Identification of requirements for streaming","-",2,"Rel-6","G1","2003-06-27","2003-08-29",1,"GP-022564","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7542,51134,"      Performance of NACC","-",3,"Rel-6","G1","2000-01-03","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7545,52131,"   Reduction of service interruption times and packet loss during mobility procedures","-",2,"Rel-6","G2","2003-06-27","2005-06-17",1,"GP-022563","-","Vodafone","José Luis Carrizo Martínez","Completed at GERP#17","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7549,52136,"      Dependency to other features of Reduction of service interruption times and packet loss during mobility procedures","-",3,"Rel-6","G2","2003-06-27","2003-11-21",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7552,33013,"   GERAN A/Gb mode security enhancements","-",2,"Rel-6","S3","2002-09-26","2005-01-28",1,"SP-030107","-","Vodafone","peter.howard@vodafone.com","SP#19 approved WID",33.101999999999997,null,null,null,null,"2003-01-15","2011-08-08"]
[7553,34300,"Performance characterisation of default codecs for PS conversational multimedia application","CODCAR",1,"Rel-6","S4","2002-09-13","2004-06-10",1,"SP-020433","-","Nokia","pasi.s.ojala@nokia.com","-",26.934999999999999,null,null,null,null,"2002-09-26","2004-09-08"]
[7556,35011,"   Principles, high level Requirements and Architecture","-",2,"Rel-6","S5","2002-09-12","2004-09-16",1,"SP-040767","-","Motorola","-","SP#25 09/2004 completed","32.101, 32.102",null,null,null,null,"2002-11-08","2006-01-13"]
[7559,35015,"   Rel-6 Trace Management","OAM-Trace",2,"Rel-6","S5,N4,R3","2002-09-20","2005-03-11",1,"SP-040782","-","Nokia","kari.t.ronka@nokia.com","SP#26 12/2004 SA5 completed 12/04. Signalling Based Trace Activation for IMS (SIP) moved to Rel-7. Reason: CN1 cannot complete 24.229 trace without IETF dependency => estimate 05/2005.","-",null,null,null,null,"2002-11-08","2005-03-09"]
[7563,35016,"Rel-6 Charging Management","CH",1,"Rel-6","S5,S2,N3","2002-11-21","2005-06-09",1,"SP-040773","-","T-Mobile","karl-heinz.nenner@t-mobile.de","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[7566,35025,"   CDR parameter description","-",2,"Rel-6","S5","2003-03-21","2005-06-09",1,"-","-","-","-","SP#28 06/2005 completed",32.298000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[7569,35028,"   OCS: Applications and interfaces","-",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"-","-","-","-","SP#26 12/2004 completed",32.295999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[7573,35031,"      CDR transfer","-",3,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.295000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[7576,32069,"      Overall definition of FBC architecture","-",3,"Rel-6","S2","2002-11-21","2004-03-02",1,"-","-","-","-","-","-",null,null,null,null,"2004-05-20","2005-03-09"]
[7577,32070,"      Study on providing policy control with FBC","-",3,"Rel-6","S2","2004-02-02","2004-07-30",1,"-","-","-","-","-","-",null,null,null,null,"2004-05-20","2004-10-21"]
[7580,1800,"Rel-6 UICC/USIM enhancements and interworking","USAT1",1,"Rel-6","T3","2000-09-25","2005-03-10",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2000-12-01"]
[7583,43006,"      2G/3G Java Card™ API based applet interworking","-",3,"Rel-6","T3","2003-03-17","2004-03-05",1,"TP-030031","-","Oberthur Card Systems","Stéphane Andrau","-","-",null,null,null,null,"2003-09-08","2005-01-19"]
[7587,502031,"      C SIM API","-",3,"Rel-6","T3","2000-09-25","2002-09-27",1,"TP-000155","-","Aspects Software","Neil Livingston","-","31.101, 31.102, 31.103, 31.111, 31.113, new 31.115, 31.116",null,null,null,null,"2000-09-27","2010-02-09"]
[7590,43009,"      USIM application toolkit Conformance Test Specification for Mobile Equipments ","-",3,"Rel-6","T3","2003-12-05","2005-03-04",1,"TP-030259","-","Gemplus","Eric.laffont@gemplus.com","-",31.123999999999999,null,null,null,null,"2004-12-06","2005-06-02"]
[7594,34023,"AMR-WB extension for high audio quality","AMRWB+",1,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-030083","-","Nokia","janne.m.vainio@nokia.com","TR tbc by Sept. 05","26.290, 26.304, 26.273, 26.274, 26.412, 26.936",null,null,null,null,"2002-11-28","2006-01-13"]
[7597,51101,"Single Antenna Receiver Interference Cancellation (SAIC)","SAIC",1,"Rel-6","GP,G1","2002-11-15","2004-06-25",1,"GP-023400","-","Cingular","Marc Grant","-",45.902999999999999,null,null,null,null,"2003-02-13","2009-11-18"]
[7600,32060,"Study on Bandwidth and resource savings in CS networks","BARS",1,"Rel-6","S2","2003-06-01","2004-06-16",1,"SP-030308","-","-","-","-",23.977,null,null,null,null,"2003-07-23","2004-07-08"]
[7601,50600,"Multiple TBF in A/Gb mode","MULTBF",1,"Rel-6","GP,G2","2002-04-05","2005-01-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved from Rel-5 UID_50058 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,null,null,"2003-07-31","2006-01-13"]
[7604,50603,"      Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2003-09-16"]
[7607,50096,"Alignment between the test-regimes for GERAN capable MS","ALTERE",1,"Rel-6","G3new","2003-08-29","2005-09-02",0.99,"GP-032236","-","Ericsson","anthony.toubassi@sonyericsson.com ","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[7611,50101,"Downlink Advanced Receiver Performance","DARP",1,"Rel-6","GP","2003-11-21","2005-09-02",1,"GP-041966","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7614,50104,"      Performance requirements in 45.005 for DARP for GMSK modulated voice services","DARP-GMSK-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7618,50108,"      Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-LC",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7621,50109,"Reduction of PS service interruption in Dual Transfer Mode","PSintDTM",1,"Rel-6","G2","2003-11-21","2005-06-24",1,"GP-032548","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7624,50112,"   Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures","PSintDTM-Reduct",2,"Rel-6","G2","2004-04-23","2004-11-12",1,"GP-032551","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7625,50113,"   Deleted - MS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfMS",2,"Rel-6","G3new","2004-06-25","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2008-12-12"]
[7628,31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[7632,11053,"   Switching between voice and video call - Redial solution","-",2,"Rel-6","N1","2005-01-03","2005-06-17",1,"SP-040331","-","Vodafone","-","-","23.009, 24.008",null,null,null,null,"2005-04-20","2005-06-02"]
[7635,13024,"Reorganisation of CS Data Specifications","CSData",1,"Rel-6","N3","2004-11-19","2004-12-08",1,"NP-040563","-","Siemens","Thomas.Belling@nsn.com","Created at TSG#27 as 100 % complete","23.910, 29.007, New 23.202",null,null,null,null,"2005-03-02","2005-03-09"]
[7638,50554,"   GAAI – Stage 2","GAAI-Stage2",2,"Rel-6","GP","2004-08-27","2005-04-08",1,"-","-","Ericsson","jari.vikberg@ericsson.com","-",43.317999999999998,null,null,null,null,"2004-10-15","2005-03-25"]
[7642,50560,"   Stage 2 for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-Stage2",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051161","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-Stage2",43.128999999999998,null,null,null,null,"2005-04-20","2006-01-13"]
[7645,33018,"Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces","-",1,"Rel-6","S3","2003-07-03","2003-12-26",1,"SP-030341","-","Toshiba","Raziq Yaqub (ryaqub@tari.toshiba.com)","SP#20 approved WID",33.817,null,null,null,null,"2003-07-25","2011-08-09"]
[7648,25019,"Test - (Small) Technical Enhancements and Improvements for Rel-6","TEI6_Test",1,"Rel-6","R5,T1","2006-06-02","2008-05-06",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing","34.108,34.121-1/2,34.122,34.123-1/2/3",null,null,null,null,"2006-09-21","2008-05-06"]
[7649,31029,"Deleted - Study of Feature Interactions Requirements","FINTER",1,"Rel-6","S1","2004-09-16","2004-09-16",1,"SP-020578","-","-","-","SP#25 stopped","-",null,null,"SP-25",null,"2004-10-20","2010-03-02"]
[7652,50501,"   Deleted - Creation of a TR","SCSAGB-TR",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030444","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","-","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[7656,50505,"   Deleted - replaced by 50561 - PS Handover","SCSAGB-PSH",2,"Rel-6","GP,N1","2003-11-24","2004-02-19",1,"GP-030448","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Started","-",null,null,"GP-18",null,"2003-02-13","2010-03-02"]
[7659,0,"--- RELEASE 5 ---","-",1,"Rel-5","NP,GP,RP,SP,TP","2000-01-03","2001-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7662,2476,"High Speed Downlink Packet Access","HSDPA",1,"Rel-5","R2,R5","2001-04-02","2007-03-09",1,"-","-","Motorola","Ravi Kuchibhotla","-","-",null,null,null,null,"2001-03-20","2001-12-10"]
[7666,2480,"   RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","HSDPA-RF",2,"Rel-5","R4","2001-04-09","2003-06-06",1,"RP-010262","-","Motorola","Howard Benn","-","-",null,null,null,null,"2001-03-20","2003-03-27"]
[7669,501216,"Rel-5 Improvements of Radio Interface","-",1,"Rel-5","RP","2000-08-14","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[7672,24002,"      Base Station Classification for 1.28 Mcps TDD option","RInImp-BSClass-LCRTDD",3,"Rel-5","R4","2001-06-15","2002-06-14",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","-","-",null,null,null,null,"2001-07-05","2002-06-21"]
[7673,2469,"   Enhancement on the DSCH hard split mode","RInImp-DSCHhsp",2,"Rel-5","R1","2001-03-16","2002-03-29",1,"-","-","Samsung","Jaeyoel KIM","-","-",null,null,null,null,"2001-03-20","2002-03-25"]
[7676,1997,"   FS on UE antenna efficiency test method performance requirements","RInImp-UEAnTM",2,"Rel-5","R4","2000-09-25","2001-09-14",1,"-","-","Allgon","O. Edvardsson","-","-",null,null,null,null,"2000-09-26","2001-10-03"]
[7680,2210,"      Deleted - Testing improvement of inter-frequency and inter-system measurement","-",3,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[7683,656,"   RRM optimization for Iur and Iub","RANimp-RRMopt",2,"Rel-5","R3","2001-03-16","2002-06-04",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[7686,23002,"      FS Introduction of direct transport bearers between SRNC and Node-B","RAN-imp-RRMopt-DTB",3,"Rel-5","R3","2001-06-15","2002-06-04",1,"-","-","Ericsson","Risto Sepponen","FS was closed and introduction of WI not agreed at RAN #16 ","-",null,null,null,null,"2001-09-19","2002-11-08"]
[7690,2490,"   FS Improvement of Radio Resource Management across RNS and RNS/PSS","RANimp-ImpRRM",2,"Rel-5","R3","2001-03-16","2001-12-21",1,"-","-","Nokia","antti.toskala@nokia.com","FS was closed and WI was introduced at RAN #14 ","-",null,null,null,null,"2001-03-20","2002-11-08"]
[{"$f":"A7693+1","v":7693},25005,"   Testing of ROHC performance","RANimp-RABSE5_Test",2,"Rel-5","R5","2005-09-09","2007-03-09",1,"-","-","Nokia","jarkko.hellsten@nokia.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[7694,21001,"   Beamforming requirements for UE","RANimp-BFR-UE",2,"Rel-5","R1","2001-09-21","2001-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","-","-",null,null,null,null,"2002-02-28","2002-02-28"]
[7697,2102,"   Deleted - Conformance Test Aspects - RAN Improvements","-",2,"Rel-5","T1","2002-01-01","2004-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[7700,23004,"UTRAN Sharing in Connected Mode","NETSHARE",1,"Rel-5","R3","2001-12-03","2002-09-03",1,"-","-","Ericsson ","Martin Israelsson","Formerly 'Shared Network support in connected mode', renamed at RAN #16.","-",null,null,null,null,"2002-03-21","2002-11-08"]
[7704,1514,"      Stage 2 (Architecture and Main flows)","-",3,"Rel-5","S2","2000-04-14","2001-03-23",1,"SP-000289","-","Lucent","Liz Daniel","Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol",23.228000000000002,null,null,null,null,"2000-07-28","2001-02-08"]
[7707,1998,"         IMS signalling flows","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228000000000002,24.228000000000002,null,null,null,null,"2000-08-25","2003-03-14"]
[7710,25006,"      Conformance Test Aspects – IMS Call Control","IMS-CCR_Test",3,"Rel-5","R5","2005-03-11","2006-12-01",1,"-","-","Motorola","Jacob.John@motorola.com","-","34.108, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2002-02-28","2010-06-16"]
[7714,2522,"         IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[7717,11000,"         IETF: RFC 3265 (specific event notification)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7718,11001,"         IETF: RFC editor Queue (refer method)","-",4,"Rel-5","N1","2000-11-24","2002-06-07",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7721,11005,"         IETF: RFC 3266 (IPv6 support within SDP)","-",4,"Rel-5","N1","2000-01-03","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7724,11024,"         IETF: RFC editor Queue (Various 3GPP Private Extensions)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7728,2530,"         Service Examples (Work stopped)","IMS-Sex",4,"Rel-5","S1","2001-04-17","2002-06-14",1,"-","-","Motorola","Mark Cataldo","-",22.928000000000001,null,null,null,null,"2001-05-28","2003-07-25"]
[7731,43000,"      IMS impacts on UICC (ISIM application)","-",3,"Rel-5","T3","2001-10-08","2002-06-21",1,"TP-010251","-","Vodafone","Jeremy Norris","-","33.102, New 31.103",null,null,null,null,"2001-10-08","2002-09-26"]
[7734,1299,"   IMS Lawful Interception","IMS-LI",2,"Rel-5","S3","2000-09-04","2002-03-29",1,"SP-010621","-","Reg TP","berthold.wilhelm@regtp.de","SP#17 completed","33.106, 33.107, New 33.108",null,null,null,null,"2000-04-09","2011-08-08"]
[7737,2039,"      Codecs","-",3,"Rel-5","S4","2000-07-26","2002-03-14",1,"SP-000398","-","-","-","-","26.235, 26.236",null,null,null,null,"2000-09-28","2002-03-25"]
[7740,11025,"      IETF: RFC 3310 (HTTP Digest Authentication using AKA)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7741,11026,"      IETF: RFC 3329 (Security mechanism agreement for SIP connections)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7744,11015,"      Compression signalling","-",3,"Rel-5","N1","2001-09-28","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7747,14997,"      Mp interface (MRFC - MRFP) enhancements","-",3,"Rel-5","N4","2001-03-14","2002-03-08",1,"-","-","-","-","[DAB 08-03-02] - No work required in CN4","-",null,null,null,null,"2001-10-08","2002-05-30"]
[7751,13001,"      Go interface (GGSN to PCF)","-",3,"Rel-5","N3","2001-03-14","2002-06-07",1,"-","-","-","-","[DAB - 23/05/03] - 100 % complete","-",null,null,null,null,"2001-10-08","2003-07-25"]
[7754,14998,"      Si interface (HSS to IM-SSF)","-",3,"Rel-5","N4","2002-01-16","2002-08-30",1,"-","-","-","-","SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete)","-",null,null,null,null,"2002-03-25","2002-05-30"]
[7758,11029,"      Mk interface (BGCF to BGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[7761,12001,"      Stage2 work 'general'","-",3,"Rel-5","N2","2001-04-16","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2001-10-08","2003-01-13"]
[7764,12004,"      Stage3 work 'Si interface'","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","[DAB 08-03-02] - UID 12004 is MASTER of UID 14998","-",null,null,null,null,"2002-01-24","2002-05-30"]
[7765,14004,"      Deleted - SDM issues for CAMEL control of IMS","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"NP-17",null,"2001-10-08","2008-12-12"]
[7768,32006,"      Charging Implications of IMS architecture","-",3,"Rel-5","S2","2001-08-06","2001-11-16",1,"SP-010519","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-02-28"]
[7771,10002,"   Other IETF dependencies","-",2,"Rel-5","NP","2000-11-24","2002-06-07",1,"-","-","-","-","Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined)","-",null,null,null,null,"2001-10-11","2002-03-25"]
[7775,41004,"   Testing of support for IMS - prose","-",2,"Rel-5","T1","2002-09-18","2003-09-30",1,"TP-030052","-","Anritsu","dan.fox@eu.anritsu.com","Marked as stopped 12/2008","34.108, 34.123",null,null,null,null,"2002-09-26","2008-12-12"]
[7778,34001,"Extended Transparent End-to-End PS Streaming Service","PSS-E",1,"Rel-5","S4","2002-01-03","2003-03-17",1,"SP-010392","-","Ericsson","olle.franceschi@ericsson.com","-","26.233, 26.234",null,null,null,null,"2001-06-28","2002-02-28"]
[7782,34019,"   RTP usage model","-",2,"Rel-5","S4","2002-01-03","2002-12-06",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)",26.937000000000001,null,null,null,null,"2002-03-25","2008-12-12"]
[7785,1429,"   OSA APIs for Multimedia Call Control","OSA1-CSCF",2,"Rel-5","S2","2000-07-11","2002-06-07",1,"-","-","-","-","For Rel5 even if completed by March","-",null,null,null,null,"2000-04-19","2002-01-24"]
[7788,15003,"   Generic user interaction - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-05",null,null,null,null,"2002-02-28","2002-06-21"]
[7789,15004,"   OSA Charging - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-12",null,null,null,null,"2002-02-28","2002-06-21"]
[7792,1419,"   OSA Security","OSA1-SEC",2,"Rel-5","S3","2000-07-11","2002-12-20",1,"SP-000302","-","Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[7796,1423,"      OSA changes required from supporting platforms, e.g. gsmSCF, HLR ","-",3,"Rel-5","S3","2000-09-11","2000-12-14",1,"SP-000302","-","BT, Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[7799,1425,"      Stage 1 for Interactions OSA - e-commerce","-",3,"Rel-5","S1","1999-04-27","2000-12-28",1,"-","-","Siemens","joerg.swetina@neclab.eu","Marked as closed 12/2008 (was marked 95% complete)",22.126999999999999,null,null,null,null,"2000-04-19","2008-12-12"]
[7802,15006,"   Presence and Availability Management (PAM) - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-14",null,null,null,null,"2002-02-28","2002-09-26"]
[7806,1788,"      Stage 3 for LCS - OSA interfaces","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2002-06-21"]
[7809,1434,"      Stage 1 for Retrieval of Terminal capabilities","-",3,"Rel-5","S1","2000-07-11","2001-01-10",1,"-","-","Siemens","joerg.swetina@neclab.eu","-",22.126999999999999,null,null,null,null,"2000-04-19","2003-07-25"]
[7812,1638,"CAMEL phase 4","CAMEL4",1,"Rel-5","S1","2000-04-17","2002-09-06",1,"NP-020486","-","Nokia","keijo.palviainen@nokia.com","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[7813,1461,"   Service requirements","-",2,"Rel-5","S1","2000-04-17","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7816,2014,"   Interactions with Optimal Routing","CAMEL4-IOR",2,"Rel-5","N2","2000-07-17","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7820,2458,"   Provision of location information of called subscriber","CAMEL4-LOCB",2,"Rel-5","N2","2001-03-02","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-02-28"]
[7823,2516,"   GPRS Any Time Interrogation","CAMEL4-ATI",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[7826,2464,"Rel-5 MExE enhancements","MEXE5",1,"Rel-5","T2","2001-03-26","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-13"]
[7830,31005,"      Stage 1 for Wideband Telephony Service - AMR","-",3,"Rel-5","S1","2001-10-01","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-03-01"]
[7833,1460,"         General Description for Wideband Telephony Service - AMR","-",4,"Rel-5","S4","2000-02-07","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7836,14005,"      N4 work for Wideband Telephony Service - AMR","-",3,"Rel-5","N4","2002-02-13","2002-06-07",1,"N4-010538","-","-","-","CN4#11 30/11/01: No inputs to CN4 at this meeting","-",null,null,null,null,"2000-08-08","2002-05-30"]
[7837,67,"      Codec issues","-",3,"Rel-5","S4","2000-01-03","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7840,891,"         Codec selection","-",4,"Rel-5","S4","2000-10-23","2000-10-27",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7844,34009,"         Interworking with fixed broadband networks","-",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[7847,1855,"      Conformance tests (CRs to 34 series) ","-",3,"Rel-5","T1","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[7850,1629,"            Test specification for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-02-01","2000-04-12",1,"-","-","-","-","-",26.132000000000001,null,null,null,null,"2000-08-08","2001-03-20"]
[7854,2266,"      Signalling for the A interface","-",3,"Rel-5","GP","2000-01-03","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[7857,50000,"      Link Adaptation in 45.009","-",3,"Rel-5","GP","2001-03-26","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-07-31"]
[7858,2269,"   Deleted - GERAN MS conformance test for AMR-WB","-",2,"Rel-5","GP","2000-01-03","2003-12-19",1,"GP-000454","-","-","-","Not started 02/2003. Marked as stopped 12/2008","-",null,null,"SP-69",null,"2001-02-01","2008-12-12"]
[7861,1826,"Rel-5 Terminal interfaces","TLM5",1,"Rel-5","T2","2001-05-14","2002-03-20",1,"-","-","-","-","Acronym changed from \"TI, TLMN5\"","-",null,null,null,null,"2000-09-14","2015-03-24"]
[7864,1600,"   UE positioning for Rel-5 Location Services enhancements","LCS1-Uepos",2,"Rel-5","R2","2001-01-15","2002-03-29",1,"-","-","-","-","Acronym changed from \"LCS1-Uepos, Rel-5\"","-",null,null,null,null,"2000-07-26","2015-03-24"]
[7868,1641,"      Stage 1 for Event based and Periodic LCS","-",3,"Rel-5","S1","2000-05-22","2000-11-17",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","Evaluate Event based and Periodic LCS to be included in R00, corresponding Stage 1 description",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[7871,2436,"   Location Services for GERAN in A/Gb Mode","LCS-GERAN",2,"Rel-5","GP","2000-04-03","2002-02-08",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[7874,2440,"      L3 protocol support for LCS","-",3,"Rel-5","GP","2000-04-03","2001-06-01",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[7878,2444,"      Iu-ps interface support for LCS","-",3,"Rel-5","R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7881,2447,"      RRC protocol support for LCS","-",3,"Rel-5","G1,G2,R2,R3","2001-08-20","2001-11-30",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7882,2448,"      Additional impacts on Broadcast of LCS data on packet channels","-",3,"Rel-5","G1,G2,R2,R3","2001-08-20","2001-12-05",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[{"$f":"A7885+1","v":7885},55069,"      LCS MS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","-",null,null,null,null,"2002-05-23","2012-05-21"]
[7888,55071,"      Deleted - LCS BTS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2008-12-12"]
[7892,2435,"      Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN","-",3,"Rel-5","GP,S2,S5,R2,R3,G2,G1","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[7895,521,"   New security aspects of LCS","LCS1-SEC",2,"Rel-5","S3,S2","2000-04-14","2001-12-28",1,"SP-000421","-","Nokia","valtteri.niemi@nokia.com","SP#9 updated WID S3-000609 (Location services security)","23.271, 43.059",null,null,null,null,"2000-04-19","2012-05-21"]
[7899,1576,"   Rel-5 Network Domain Security (SEC1-NDS)","-",2,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000420","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE","New 33.200 (exisalso for Rel-4)",null,null,null,null,"2000-04-18","2011-08-08"]
[7902,1578,"         Deleted - Main aspects of User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","S3","2000-05-12","2001-06-21",1,"-","-","-","-","TO BE DELETED. Marked as stopped 12/2008","-",null,null,"SP-12",null,"2000-04-09","2008-12-12"]
[7905,1581,"         Deleted -Main aspects of User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","S3","2000-02-21","2001-06-21",1,"-","-","-","-","-","-",null,null,"SP-12",null,"2000-04-09","2002-11-08"]
[7906,1582,"         Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","N4","2001-09-14","2002-06-28",1,"-","-","-","-","14/02/2002 requirements are not clear/not receivedMarked as closed 12/2008 (was marked 95 complete)","-",null,null,"NP-16",null,"2000-04-09","2008-12-12"]
[7909,20000,"   Stage 3: RAN node selecting CN node","-",2,"Rel-5","R3","2001-09-24","2002-03-22",1,"-","-","Vodafone","Brendan.McWilliams@gb.vodafone.co.uk","Not identified","-",null,null,null,null,"2001-09-19","2002-03-01"]
[7912,50067,"   GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","IDCRAN-GERAN",2,"Rel-5","GP","2002-02-08","2002-06-28",1,"GP-020492","-","Ericsson","ingemar.backlund@era.ericsson.se","Accept changes Gb over IP","-",null,null,null,null,"2002-05-23","2002-09-26"]
[7916,52077,"      48.016 Use of Gb interface concepts when a network applies IDNNS","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","Closed, accept changes for Gb over IP","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7919,2321,"   Deleted - Evolution of the transport for A","GEIMP3-EtA",2,"Rel-5","GP","2001-04-06","2002-12-20",1,"GP-010910","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[7923,35002,"   Rel-5 Principles, high level Requirements and Architecture","-",2,"Rel-5","S5","2001-09-17","2002-06-28",1,"SP-010461","-","Motorola","-","-","32.101, 32.102",null,null,null,null,"2000-04-26","2002-06-21"]
[7926,35001,"   Rel-5 Network Infrastructure Management ","-",2,"Rel-5","S5","2001-09-21","2002-09-12",1,"SP-010461","-","Ericsson","thomas.tovinger@ericsson.com","-","32.6xy, 32.3xy",null,null,null,null,"2001-10-08","2002-11-08"]
[7929,2395,"   RLC protocol enhancement (SDU Discard)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7930,2396,"GERAN enhancements for streaming services 2 (usage of ECSD)","-",1,"Rel-5","GP","2000-11-06","2002-06-28",1,"GP-010430","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7933,2400,"   Stage 3 for GERAN enhancements for streaming services 2 (usage of ECSD)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7936,2412,"GERAN/UTRAN interface evolution 1 (evolution of Iu PS)","GERUEV1",1,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"GP-010481","-","SBC","Marc Grant","SBC, Motorola, Nokia, Ericsson, Nortel","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7940,2416,"GERAN/UTRAN interface evolution 2 (evolution of Iu CS)","GERUEV2",1,"Rel-5","GP,R3","2000-06-29","2002-06-28",1,"GP-010417","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7943,2419,"      Update of Evolution of Iu cs specifications ","-",3,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[7947,2559,"   QoS Management (Provisioning and Monitoring)","E2EQoS-OAM",2,"Rel-5","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-11-08"]
[7950,31000,"      Definition of service requirements for MESS5-MMS","MESS5-SR",3,"Rel-5","S1","2001-06-15","2002-03-15",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",22.14,null,null,null,null,"2001-07-04","2003-07-25"]
[7953,34018,"      MMS formats and codecs for MESS5-MMS","-",3,"Rel-5","S4","2001-12-03","2002-03-15",1,"-","-","-","-","-",26.14,null,null,null,null,"2002-01-24","2002-02-28"]
[7954,2572,"   Enhanced Messaging Service (EMS) enhancements","MESS5-EMS",2,"Rel-5","T2","2001-06-15","2002-03-08",1,"TP-010153","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-",23.04,null,null,null,null,"2000-09-14","2003-03-27"]
[7957,50001,"GERAN Inter BSC NACC improvements over the Gb Interface","GERNACC",1,"Rel-5","GP","2001-09-03","2002-06-28",1,"GP-012313","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[7961,14503,"      Stage 3 (changes to TS 29.060)","-",3,"Rel-5","N4","2001-09-03","2002-03-08",1,"-","-","-","-","IP 30/11/01: Input awaited from GERAN2 to CN4","-",null,null,null,null,"2001-09-19","2002-07-31"]
[7964,50033,"Enhanced Power Control","EPC",1,"Rel-5","GP","2001-11-26","2003-12-19",1,"GP-012748","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[7967,50036,"   Deleted - GERAN BTS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012751","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[7971,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7974,51027,"      Changes to 45.003","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7975,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7976,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7977,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[7978,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[7979,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[7980,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[7981,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[7982,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[7983,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[7984,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[7985,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[7986,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[7987,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[7988,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[7989,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[7990,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[7991,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[7992,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[7993,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[7994,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7995,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7996,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[7997,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[7998,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[7999,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8000,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8001,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8002,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8003,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8004,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8005,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8006,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8007,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8008,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8009,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8010,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8011,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8012,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[{"$f":"A8013+1","v":8013},50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8014,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8015,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8016,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8017,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8018,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8019,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8020,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8021,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8022,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8023,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8024,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8025,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8026,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8027,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8028,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8029,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8030,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8031,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8032,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8033,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8034,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8035,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8036,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8037,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8038,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8039,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8040,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8041,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8042,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8043,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8044,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8045,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8046,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8047,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8048,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8049,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8050,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8051,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8052,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8053,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8054,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8055,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8056,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8057,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8058,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8059,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8060,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8061,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8062,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8063,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8064,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8065,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8066,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8067,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8068,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8069,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8070,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8071,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8072,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8073,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8074,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8075,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[8076,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[{"$f":"A8077+1","v":8077},2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8078,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8079,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8080,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8081,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8082,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8083,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8084,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8085,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8086,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8087,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8088,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8089,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8090,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8091,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8092,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8093,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8094,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8095,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8096,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8097,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[8098,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8099,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8100,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8101,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8102,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8103,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8104,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8105,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8106,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8107,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8108,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8109,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8110,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8111,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8112,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8113,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8114,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8115,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8116,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8117,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8118,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8119,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8120,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8121,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8122,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8123,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8124,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8125,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8126,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8127,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8128,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8129,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8130,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8131,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8132,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8133,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8134,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8135,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8136,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8137,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8138,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8139,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[8140,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[{"$f":"A8141+1","v":8141},1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8142,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8143,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8144,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8145,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8146,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[8147,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8148,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8149,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8150,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8151,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8152,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8153,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8154,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8155,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8156,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8157,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8158,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8159,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8160,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8161,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[8162,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8163,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8164,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8165,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8166,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8167,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8168,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8169,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8170,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8171,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8172,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8173,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8174,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8175,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8176,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8177,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8178,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8179,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8180,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8181,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8182,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8183,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8184,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8185,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8186,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8187,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8188,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8189,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8190,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8191,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8192,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8193,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8194,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8195,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8196,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8197,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8198,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8199,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8200,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8201,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8202,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8203,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[8204,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[{"$f":"A8205+1","v":8205},1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[8206,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8207,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[8208,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8209,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[8210,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[8211,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8212,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[8213,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[8214,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8215,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8216,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8217,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8218,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8219,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8220,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8221,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8222,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8223,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[8224,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8225,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[8226,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[8227,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[8228,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[8229,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[8230,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8231,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[8232,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[8233,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[8234,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[8235,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[8236,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[8237,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8238,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8239,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[8240,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[8241,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[8242,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[8243,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[8244,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8245,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[8246,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8247,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8248,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8249,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[8250,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[8251,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[8252,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8253,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8254,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[8255,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[8256,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[8257,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8258,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[8259,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8260,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[8261,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8262,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[8263,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8264,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8265,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[8266,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[8267,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[8268,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[{"$f":"A8269+1","v":8269},401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[8270,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[8271,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8272,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[8273,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[8274,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[8275,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[8276,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[8277,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[8278,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[8279,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[8280,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[8281,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[8282,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[8283,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[8284,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[8285,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[8286,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[8287,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[8288,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8289,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[8290,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8291,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8292,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[8293,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[8294,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[8295,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[8296,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[8297,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8298,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[8299,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8300,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[8301,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[8302,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8303,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8304,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[8305,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[8306,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[8307,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[8308,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[8309,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[8310,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[8311,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[8312,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8313,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8314,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[8315,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8316,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8317,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[8318,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[8319,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8320,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8321,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[8322,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8323,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8324,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8325,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8326,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8327,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8328,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[8329,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[8330,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8331,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8332,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[{"$f":"A8333+1","v":8333},60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[8334,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[8335,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[8336,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8337,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[8338,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8339,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[8340,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[8341,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8342,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[8343,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[8344,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8345,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8346,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[8347,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[8348,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[8349,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[8350,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[8351,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[8352,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[8353,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8354,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8355,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[8356,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[8357,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8358,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[8359,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[8360,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[8361,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[8362,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[8363,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[8364,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[8365,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[8366,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[8367,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[8368,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8369,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8370,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8371,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[8372,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[8373,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[8374,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8375,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8376,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[8377,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[8378,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8379,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[8380,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8381,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[8382,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[8383,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[8384,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8385,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[8386,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8387,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[8388,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[8389,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[8390,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[8391,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[8392,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[8393,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[8394,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[8395,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8396,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A8397+1","v":8397},60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8398,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8399,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[8400,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8401,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8402,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8403,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[8404,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[8405,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[8406,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[8407,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[8408,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8409,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[8410,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[8411,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[8412,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8413,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8414,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8415,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8416,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[8417,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8418,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[8419,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8420,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[8421,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[8422,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8423,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8424,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8425,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8426,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8427,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8428,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8429,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8430,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8431,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[8432,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[8433,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[8434,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8435,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[8436,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8437,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[8438,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8439,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[8440,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8441,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8442,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[8443,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[8444,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[8445,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[8446,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8447,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[8448,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[8449,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8450,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8451,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8452,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8453,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8454,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[8455,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8456,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[8457,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[8458,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[8459,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[8460,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[{"$f":"A8461+1","v":8461},60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[8462,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8463,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[8464,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[8465,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[8466,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[8467,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[8468,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[8469,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[8470,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[8471,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[8472,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[8473,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[8474,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]