{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp","index":0,"n_rows":8599,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version January 4th 2024",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[{"$f":"A2+1","v":2},0,"Post TSG#102 version ",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[{"$f":"A3+1","v":3},0,"Next key milestones: Rel-18 (St.3 & RAN): Mar 24. Rel-19: ST.2: Dec 24; St.3: Sept.25",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[6,0,"Rel-19 Energy Efficiency, Energy Saving","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A7+1","v":7},1020060,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19",null,"2022-06-02","2024-09-09",0.57999999999999996,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[{"$f":"A8+1","v":8},960019,"   Study on Energy Efficiency as service criteria ","FS_EnergyServ",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.882000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[9,1000033,"   Stage 1 of Energy Efficiency as Service Criteria ","EnergyServ",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[10,1010029,"   Study on Energy Efficiency and Energy Saving","FS_EnergySys",2,"Rel-19","S2","2023-09-09","2024-06-06",0.15,"SP-231391",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;","SP-231192; 23.700-66; 28.880",101,51,null,null,"2023-09-20","2024-01-04"]
[11,1020021,"   Study on energy efficiency and energy saving aspects of 5G networks and services ","FS_Energy_OAM_Ph3",2,"Rel-19","S5","2023-12-07","2024-09-09",0,"SP-231723",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com","4/1/24: 28.866 added;",28.866,102,52,null,null,"2023-12-07","2024-01-04"]
[12,1020095,"Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh",1,"Rel-19",null,"2023-12-12","2026-03-03",0,"RP-234065",null,"Ericsson ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[13,1021095,"   Core part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Core",2,"Rel-19","R1","2023-12-12","2025-09-09",0,"RP-234065",null,"Ericsson ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[14,1022095,"   Perf. part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234065",null,"Ericsson ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[15,1020094,"Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS",1,"Rel-19",null,"2023-12-12","2026-03-03",0,"RP-234056",null,"vivo ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[16,1021094,"   Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Core",2,"Rel-19","R1","2023-12-12","2025-09-09",0,"RP-234056",null,"vivo ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[17,1022094,"   Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234056",null,"vivo ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[18,0,"Rel-19 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[19,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23:...","22.875; 22.876",95,48,null,null,"2022-03-10","2023-09-06"]
[20,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80; 8/12/23: 80%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[21,1020068,"Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","FS_AIML_CN",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231800",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com) ",null,null,102,52,null,null,"2024-01-03","NA"]
[22,1020007,"Study on AI/ML management - phase 2 ","FS_AIML_MGT_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231780",null,"Yizhi Yao (Intel) ","yizhi.yao@intel.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[23,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","2023-09-07","2024-09-09",0.35,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","8/12/23: 0%->35; 4/1/24: 23.700-82 added;","23.700-82",101,51,null,null,"2023-09-07","2024-01-04"]
[24,1020083,"Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","FS_NR_AIML_NGRAN_enh",1,"Rel-19","R3","2023-12-12","2024-06-06",0,"RP-234054",null,"ZTE ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[25,1020084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR ","FS_NR_AIML_Mob",1,"Rel-19","R2","2019-03-07","2021-05-28",0,"RP-234055",null,"Oppo ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[26,1020093,"Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air",1,"Rel-19",null,"2023-12-12","2026-03-03",0,"RP-234039",null,"Qualcomm ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[27,1021093,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Core",2,"Rel-19","R1","2023-12-12","2025-09-09",0,"RP-234039",null,"Qualcomm ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[28,1022093,"   Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234039",null,"Qualcomm ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[29,0,"Rel-19 Ambient power-enabled Internet of Things ","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[30,1020055,"Ambient power-enabled Internet of Things ","AmbientIoT",1,"Rel-19",null,"2022-03-10","2024-12-12",0.65,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[31,950004,"   Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.84,95,48,null,null,"2022-03-10","2023-12-08"]
[32,1020071,"   Study on Architecture support of Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S2","2024-01-03","2024-12-12",0,"SP-231803",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[33,1020030,"   Stage 1 of Ambient power-enabled Internet of Things ","AmbientIoT",2,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[34,1020085,"Study on solutions for Ambient IoT (Internet of Things) in NR ","FS_Ambient_IoT_solutions",1,"Rel-19","R1","2023-12-12","2024-12-12",0,"RP-234058",null,"CMCC ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[35,0,"See also IoT_NTN_Ph3 under Satellite/NTN ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[36,0,"Rel-19 Satellite (5GSAT), NTN","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[37,1020058,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19",null,"2022-06-02","2024-09-09",0.59,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[38,960016,"   Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[39,1000024,"   Stage 1 of Satellite access Phase 3 ","5GSAT_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[40,1010033,"   Study on Integration of satellite components in the 5G architecture Phase 3","FS_5GSAT_Ph3_ARCH",2,"Rel-19","S2","2023-09-20","2024-06-06",0.15,"SP-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;","23.700-29; 28.874",101,51,null,null,"2023-09-20","2024-01-04"]
[41,1020053,"   Study on application enablement for Satellite access enabled 5G Services ","FS_5GSAT_Ph3_App",2,"Rel-19","S6","2024-01-03","2024-09-09",0,"SP-231738",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","8/12/23: 0%->5",null,102,52,null,null,"2023-12-07","2023-12-08"]
[42,1020044,"Study on Security Aspects of 5G Satellite Access Phase 3 ","FS_5GSAT_Ph3_SEC",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231790",null,"Zhou Wei ","zhouwei@catt.cn ","No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;","33.700-29",102,52,null,null,"2023-12-07","2024-01-04"]
[43,1020097,"Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3",1,"Rel-19",null,"2023-12-12","2026-03-03",0,"RP-234078",null,"Thales ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[44,1021097,"   Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-12","2025-09-09",0,"RP-234078",null,"Thales ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[45,1022097,"   Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234078",null,"Thales ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[46,1020096,"Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3",1,"Rel-19",null,"2023-12-12","2025-09-09",0,"RP-234077",null,"Mediatek ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[47,1021096,"   Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-12","2025-09-09",0,"RP-234077",null,"Mediatek ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[48,0,"Rel-19 XR (eXtended Reality), Metaverse","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[49,1020056,"Localized Mobile Metaverse Services ","Metaverse",1,"Rel-19",null,"2022-03-10","2024-09-09",0.75,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[50,950005,"   Study on Localized Mobile Metaverse Services ","FS_Metaverse",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100",22.856000000000002,95,48,null,null,"2022-03-10","2023-12-08"]
[51,1000028,"   Stage 1 of Localized Mobile Metaverse Services ","Metaverse",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[52,1020052,"   Study on application enablement for Localized Mobile Metaverse Services ","FS_Metaverse_App",2,"Rel-19","S6","2024-01-03","2024-09-09",0,"SP-231806",null,"Shah, Sapan, Samsung ","sapan.shah@samsung.com ","8/12/23: 0%->10",null,102,52,null,null,"2023-12-07","2023-12-08"]
[53,1010032,"Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231671",null,"Primary Rapporteur: Devaki Chandramouli (Nokia) ","devaki.chandramouli@nokia.com. ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13","23.700-70",101,51,null,null,"2023-09-20","2023-12-08"]
[54,1020051,"Study on Application enabler for XR Services ","FS_XRApp",1,"Rel-19","S6","2024-01-03","2024-09-09",0,"SP-2315739",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","8/12/23: 0%->10",null,102,52,null,null,"2023-12-07","2023-12-08"]
[55,990052,"Supporting UE Mobility for XR Services ","XRMobility",1,"Rel-19","S1","2023-03-16","2023-06-06",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-09-06"]
[56,1020098,"XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3",1,"Rel-19",null,"2023-12-12","2026-03-03",0,"RP-234080",null,"Nokia ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[57,1021098,"   Core part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Core",2,"Rel-19","R2","2023-12-12","2025-09-09",0,"RP-234080",null,"Nokia ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[58,1022098,"   Perf. part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234080",null,"Nokia ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[59,0,"Rel-19 other topics","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[60,1020057,"Integrated Sensing and Communication ","Sensing",1,"Rel-19",null,"2022-03-10","2024-09-09",0.73,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[61,950003,"   Study on Integrated Sensing and Communication ","FS_Sensing",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",22.837,95,48,null,null,"2022-03-10","2023-09-06"]
[62,1020054,"   Study on Sensing application enabler for vertical applications ","FS_SensingAPP",2,"Rel-19","S6","2023-12-07","2024-09-09",0,"SP-231579",null,"Yanmei Yang, Huawei ","yangyanmei@huawei.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[63,1000026,"   Stage 1 of Integrated Sensing and Communication ","Sensing",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[64,1020086,"Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR",1,"Rel-19","R1","2023-12-12","2025-06-06",0,"RP-234069",null,"Xiaomi ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[65,1020059,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19",null,"2022-06-02","2024-12-12",0.57999999999999996,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[66,960017,"   Study on (Stage 1 of) UAV Phase 3 ","FS_UAV_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[67,1020069,"   Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM ","FS_UAS_Ph3",2,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231801",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[68,1000032,"   Stage 1 of Uncrewed Aerial System Phase 3 ","UAS_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[69,1010008,"   Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",2,"Rel-19","S6","2023-09-07","2024-12-12",0.2,"SP-230991",null,"Monrad, Atle, InterDigital ","<atle.monrad@interdigital.com> ","; 8/12/23: 0%->20","23.255; 23.434 ",101,51,null,null,"2023-09-07","2023-12-08"]
[70,950006,"Study on Network Sharing Aspects ","FS_NetShare",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100",22.850999999999999,95,48,null,null,"2022-03-10","2023-09-06"]
[71,1000029,"Indirect Network Sharing ","NetShare",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-09-06"]
[{"$f":"A72+1","v":72},1020070,"Study on Multi-Access (DualSteer and ATSSS_Ph4) ","FS_MASSS",1,"Rel-19","S2","2024-01-03","2024-09-09",0,"SP-231802",null,"Krisztian Kiss (Apple) ","krisztian@apple.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[73,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.841000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[74,1020031,"Upper layer traffic steering and switching over dual 3GPP access ","DualSteer",1,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231412",null,"Pica Francesco, Qualcomm ","fpica<at>qti.qualcomm.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[75,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[76,1020004,"Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","FS_eEDGE_5GC_Ph3",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231796",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[77,1020002,"Study on System aspects of 5G NR Femto ","FS_5G_Femto",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231797",null,"Malla Reddy Sama (NTT DOCOMO) ","sama@docomolab-euro.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[78,1020066,"Study on Proximity-based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231798",null,"Hugh Shieh (AT&T) ","hs6220@att.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[79,1020067,"Study on Vehicle Mounted Relays Phase 2 ","FS_VMR_Ph2",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231799",null,"Primary Rapporteur: Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[80,1020063,"Study on User Identities and Authentication Architecture ","FS_UIA_ARC",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231804",null,"Michael Starsinic, Interdigital ","Michael.Starsinic@Interdigital.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[81,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-220437",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.989000000000001,95,48,null,null,"2022-03-10","2023-12-08"]
[82,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50; 8/12/23: 50%->100","22.280; 22.179; 22.289; 22.261 ",100,51,null,null,"2023-06-08","2023-12-08"]
[83,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","2019-09-19","2022-09-08",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"2019-09-13","2022-09-09"]
[84,1020003,"Study on UPF enhancement for Exposure And SBA Phase 2 ","FS_UPEAS_Ph2",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231795",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,null,102,52,null,null,"2024-01-03","NA"]
[85,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","2022-06-02","2023-12-12",1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.916,96,49,null,null,"2022-06-02","2023-12-08"]
[86,960015,"Study on roaming value added services ","FS_RVAS",1,"Rel-19","S1","2022-06-02","2022-12-12",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100",22.876999999999999,96,49,null,null,"2022-06-02","2022-12-10"]
[87,990051,"Roaming Value-Added Services ","RVAS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[88,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","2023-03-16","2024-06-06",0.65,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65",22.847999999999999,99,50,null,null,"2023-03-16","2023-12-08"]
[89,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100",22.103999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[90,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100",22.010999999999999,99,50,null,null,"2023-03-16","2023-08-09"]
[91,1010030,"Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",1,"Rel-19","S2","2023-09-20","2024-06-06",0.15,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15","23.700-77",101,51,null,null,"2023-09-20","2023-12-08"]
[92,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[93,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,51,null,null,"2023-06-08","2023-06-08"]
[94,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[95,970042,"MPS for Messaging services ","MPS4msg",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[96,1010031,"Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",1,"Rel-19","S2","2024-01-03","2024-06-06",0,"SP-231197",null,"Robert Streijl (Peraton Labs) ","rstreijl@peratonlabs.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20","23.700-75",101,51,null,null,"2023-09-20","2023-12-08"]
[97,970041,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[98,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","2022-12-09","2022-12-20",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100",22.260999999999999,98,50,null,null,"2022-12-09","2022-12-10"]
[99,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[100,1000027,"Non-Public Network (NPN) security considerations ","SecNPN",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,22.260999999999999,100,51,null,null,"2023-06-08","NA"]
[101,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","2022-12-13","2024-09-12",0.45,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45",26.933,98,50,null,null,"2022-12-09","2023-12-08"]
[102,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","2023-06-08","2024-09-09",0.2,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20","23.222 ; 23.700-92",100,51,null,null,"2023-06-08","2023-12-08"]
[103,1000035,"Study on enhanced application layer support for location services ","FS_eLSAPP",1,"Rel-19","S6","2023-06-08","2024-06-06",0.25,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25","23.434 ; 23.700-72",100,51,null,null,"2023-06-08","2023-12-08"]
[104,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.4,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5; 8/12/23: 5%->40","23.280; 23.379; 23.281; 23.282 ",100,51,null,null,"2023-06-08","2023-12-08"]
[105,1000037,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19","S6","2023-06-08","2024-09-09",0.2,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20",null,100,51,null,null,"2023-06-08","2023-12-08"]
[106,1000038,"Railways specific Enhancements to Mission Critical Services ","enh4FRMCS",1,"Rel-19","S6","2023-06-08","2024-12-12",0.3,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10; 8/12/23: 10%->30","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2023-12-08"]
[107,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.3,"SP-230988",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2023-12-08"]
[108,1010006,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19","S6","2023-09-07","2024-12-12",0.25,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25",null,101,51,null,null,"2023-09-07","2023-12-08"]
[109,1010007,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19","S6","2023-09-07","2024-12-12",0.15,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15",23.558,101,51,null,null,"2023-09-07","2023-12-08"]
[110,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-19","S6","2023-09-07","2024-09-09",0.2,"SP-231161",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ","8/12/23: 0%->20; 4/1/24: 23.946 added;",23.946000000000002,101,51,null,null,"2023-09-07","2024-01-04"]
[111,1020062,"Study on CAPIF Phase 3 ","FS_CAPIF_Ph3",1,"Rel-19","S6","2024-01-03","2024-09-09",0,"SP-231741",null,"Preciado Rojas, Diego, Nokia ","diego.preciado_rojas@nokia.com ",null,null,102,52,null,null,"2024-01-03","NA"]
[112,0,"Rel-19 miscellaneous Security",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[113,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","2023-09-06","2024-09-09",0.1,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 8/12/23: 0%->10",33.926000000000002,101,51,null,null,"2023-09-06","2023-12-08"]
[114,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","2023-09-06","2024-09-09",0.1,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in","8/12/23: 0%->10; 4/1/24: 33.529 added;",33.529000000000003,101,51,null,null,"2023-09-06","2024-01-04"]
[115,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","2023-09-06","2024-03-03",0.1,"SP-231159",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ","8/12/23: 0%->10; 4/1/24: 35.248 added;","35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240",101,51,null,null,"2023-09-06","2024-01-04"]
[116,1020036,"Addition of Milenage-256 algorithm ","Milenage_256",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231792",null,"Mireille Pauliac ","mireille.pauliac@thalesgroup.com ","4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;","35.237; 35.236; 35.235; 35.234",102,52,null,null,"2023-12-07","2024-01-04"]
[117,1020041,"Study on enabling a cryptographic algorithm transition to 256-bits ","FS_CAT256",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231788",null,"Yuto Nakano ","yt-nakano@kddi.com ","4/1/24: 33.700-41 added;","33.700-41",102,52,null,null,"2023-12-07","2024-01-04"]
[118,1020034,"Study on enablers for Zero Trust Security ","FS_eZTS",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231784",null,"Sheeba Backia Mary Baskaran ","smary@lenovo.com ","4/1/24: 33.794 added;",33.793999999999997,102,52,null,null,"2023-12-07","2024-01-04"]
[119,1020035,"Mission critical security enhancements for release 19 ","MCXSec4",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231783",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ",null,33.18,102,52,null,null,"2023-12-07","NA"]
[120,1020038,"Study on the security support for the Next Generation Real Time Communication services phase 2 ","FS_NG_RTC_SEC_Ph2",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231785",null,"Vlasios Tsiatsis ","vlasios.tsiatsis@ericsson.com ","4/1/24: 33.790 added;",33.79,102,52,null,null,"2023-12-07","2024-01-04"]
[121,1020039,"Study on security for PLMN hosting a NPN ","PLMNNPN_SEC",1,"Rel-19","S3","2024-01-03","2024-09-09",0,"SP-231786",null,"Jun Shen","shenjun6@chinatelecom.cn","4/1/24: 33.757 added;",33.756999999999998,102,52,null,null,"2023-12-07","2024-01-04"]
[122,1020040,"Study of ACME for Automated Certificate Management in SBA ","FS_ACME_SBA",1,"Rel-19","S3","2024-01-03","2024-06-06",0,"SP-231787",null,"Charles Eckel ","eckelcu(at)cisco.com ","4/1/24: 33.776 added;",33.776000000000003,102,52,null,null,"2023-12-07","2024-01-04"]
[123,1020042,"3GPP profiles for cryptographic algorithms and security protocols ","CryptoSP",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231793",null,"Mohsin Khan A ","mohsin.a.khan@ericsson.com ",null,"33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 ",102,52,null,null,"2023-12-07","NA"]
[124,1020043,"Study on mitigations against bidding down attacks ","FS_MiBiDA",1,"Rel-19","S3","2024-01-03","2024-06-06",0,"SP-231789",null,"Noamen Ben Henda ","noamen.ben.henda@huawei.com ","4/1/24: 33.701 added;",33.701000000000001,102,52,null,null,"2023-12-07","2024-01-04"]
[125,1020045,"Security for mobility over non-3GPP access to avoid full primary authentication ","FS_Non3GPPMob_Sec",1,"Rel-19","S3","2024-01-03","2024-12-12",0,"SP-231791",null,"Saurabh Khare, Nokia ","Saurabh.Khare@nokia.com ","4/1/24: 33.702 added;",33.701999999999998,102,52,null,null,"2023-12-07","2024-01-04"]
[126,0,"Rel-19 miscellaneous OAM&charging",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[127,1020008,"Study on intent driven management services for mobile network phase 3 ","FS_IDMS_MN_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231737",null,"Ruiyue Xu (Huawei) ","xuruiyue@huawei.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[128,1020009,"Study on closed control loop management ","FS_CCLM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231735",null,"Deepanshu Gautam (Samsung) ","deepanshu.g@samsung.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[129,1020010,"Study on Cloud Aspects of Management and Orchestration ","FS_Cloud_OAM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231781",null,"Bahar Sadeghi (Microsoft) ","bahar.sadeghi@microsoft.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[130,1020011,"Study on Service Based Management Architecture enhancement phase 3 ","FS_SBMA_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231725",null,"Kai Zhang (Huawei) ","kai.zhangkai@huawei.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[131,1020012,"Study on data management regarding subscriptions and reporting ","FS_Data_SREP",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231732",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[132,1020013,"Study on Management Aspects of NTN Phase 2 ","FS_NTN_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231733",null,"MingRui Sun (China Unicom) ","sunmr19@chinaunicom.cn ",null,null,102,52,null,null,"2023-12-07","NA"]
[133,1020014,"Study on management of IAB nodes ","FS_NR_mobile_IAB_OAM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231729",null,"JunFeng Wang (Ericsson) ","junfeng.a.wang@ericsson.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[134,1020015,"Study on Management of Network Sharing Phase3 ","FS_NetShare_OAM_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231731",null,"ZhaoNing Wang (China Unicom) ","wangzn18@chinaunicom.cn ",null,null,102,52,null,null,"2023-12-07","NA"]
[135,1020016,"Study on Enablers for Security Monitoring ","FS_SECM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231736",null,"Clifton Fernandes (Nokia) ","clifton.fernandes@nokia.com ","4/1/24: 28.870 added;",28.87,102,52,null,null,"2023-12-07","2024-01-04"]
[{"$f":"A136+1","v":136},1020017,"Study on management aspects of RedCap feature ","FS_NR_RedCap_OAM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231734",null,"Zhen Xing (China Unicom) ","xingz12@chinaunicom.cn ",null,null,102,52,null,null,"2023-12-07","NA"]
[137,1020018,"Study on management aspects of Network Digital Twin ","FS_NDT",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231428",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com ","4/1/24: 28.915 added;",28.914999999999999,102,52,null,null,"2023-12-07","2024-01-04"]
[138,1020019,"Study on Management Data Analytics (MDA) Phase 3 ","FS_eMDAS_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231726",null,"Brendan T Hassett (Huawei) ","brendan.t.hassett@huawei.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[139,1020020,"Study on Enhancement of Management Aspects related to NWDAF Phase 2 ","FS_NWDAF_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231724",null,"Primary Rapporteur: Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ",null,null,102,52,null,null,"2023-12-07","NA"]
[140,1020033,"Study on Management of planned configurations ","FS_PlanM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231721",null,"Olaf Pollakowski (Nokia) ","olaf.pollakowski@nokia.com ","4/1/24: 28.872 added;",28.872,102,52,null,null,"2024-01-03","2024-01-04"]
[141,1020022,"Study on Enhanced OAM for management exposure to external consumers ","FS_MExpo",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231728",null,"Primary Rapporteur: Scott Probasco (Nokia) ","scott.probasco@nokia.com ",null,null,102,52,null,null,"2023-12-07","NA"]
[142,1020025,"Data management phase 2 ","MADCOL_Ph2",1,"Rel-19","S5","2024-01-03","2025-06-06",0,"SP-231746",null,"Sivaramakrishnan Swaminathan (Nokia) ","sivaramakrishnan.swaminathan@nokia.com ",null,"28.622; 28.623 ",102,52,null,null,"2023-12-07","NA"]
[143,1020026,"5G performance measurements and KPIs phase 4 ","PM_KPI_5G_Ph4",1,"Rel-19","S5","2024-01-03","2025-06-06",0,"SP-231747",null,"Primary Rapporteur: XiuMin Chen (China Telecom) ","chenxiumin@chinatelecom.cn ",null,"28.552; 32.425; 28.554; 28.532; 28.550; 28.abc ",102,52,null,null,"2023-12-07","NA"]
[144,1020027,"5G Advanced NRM features phase 3 ","AdNRM_Ph3",1,"Rel-19","S5","2024-01-03","2025-06-06",0,"SP-231745",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ",null,"28.540; 28.541; 28.622; 28.623 ",102,52,null,null,"2023-12-07","NA"]
[145,1020028,"Subscriber and Equipment Trace and QoE collection management ","TraceQoE_OAM",1,"Rel-19","S5","2024-01-03","2025-06-06",0,"SP-231748",null,"Zu Qiang (Ericsson) ","zu.qiang@ericsson.com ",null,"32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 ",102,52,null,null,"2023-12-07","NA"]
[146,0,"Rel-19 NR-only: topics other than band",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[147,1020081,"Study on channel modelling enhancements for 7-24GHz for NR ","FS_NR_7_24GHz_CHmod",1,"Rel-19","R1","2023-12-12","2025-06-06",0,"RP-234018",null,"Intel ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[148,1020082,"Study on additional topological enhancements for NR ","FS_NR_WAB_5GFemto",1,"Rel-19","R3","2019-03-07","2021-05-28",0,"RP-234041",null,"NTT DOCOMO ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[149,1020089,"NR MIMO Phase 5 ","NR_MIMO_Ph5",1,"Rel-19","R1","2023-12-12","2026-03-03",0,"RP-234007",null,"Samsung ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[150,1021089,"   Core part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Core",2,"Rel-19","R1","2023-12-12","2025-09-09",0,"RP-234007",null,"Samsung ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[151,1022089,"   Perf. part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234007",null,"Samsung ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[152,1020090,"Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo",1,"Rel-19","R1","2023-12-12","2026-03-03",0,"RP-234035",null,"Huawei ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[153,1021090,"   Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Core",2,"Rel-19","R1","2023-12-12","2025-09-09",0,"RP-234035",null,"Huawei ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[154,1022090,"   Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234035",null,"Huawei ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[155,1020091,"NR mobility enhancements Phase 4 ","NR_Mob_Ph4",1,"Rel-19","R2","2023-12-12","2026-03-03",0,"RP-234036",null,"Apple ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[156,1021091,"   Core part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Core",2,"Rel-19","R2","2023-12-12","2025-09-09",0,"RP-234036",null,"Apple ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[157,1022091,"   Perf. part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Perf",2,"Rel-19","R4","2023-12-12","2026-03-03",0,"RP-234036",null,"Apple ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[158,1020092,"Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4",1,"Rel-19","R3","2023-12-12","2025-09-09",0,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[159,1021092,"   Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4-Core",2,"Rel-19","R3","2023-12-12","2025-09-09",0,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[160,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-19","RP","2017-12-15","2024-03-03",0.98,"RP-234033","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R...","37.890; 37.107",78,40,null,null,"2018-01-08","2024-01-02"]
[161,0,"Rel-19 other",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[162,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","2023-03-23","2024-09-09",0,"SP-230242",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater","33.107; 33.108; 33.126; 33.127; 33.128 ",97,49,null,null,"2022-09-11","2023-03-16"]
[163,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"2022-09-09","2022-12-12",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[164,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[165,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[166,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"2021-06-11","2023-12-12",1,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[167,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","2021-06-11","2021-06-18",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[168,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"2021-12-19","2022-12-10"]
[169,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[170,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","2023-06-06"]
[171,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","NA"]
[172,1020023,"Charging aspects of Satellite Backhaul in 5GS ","5GSATB_CH",1,"Rel-18","S5","2023-12-07","2024-03-03",0,"SP-231707",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ",null,"32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 ",102,52,null,null,"2023-12-07","NA"]
[173,1020029,"Management aspects of 5G system supporting satellite backhaul ","5GSATB_OAM",1,"Rel-18","S5","2023-12-07","2024-03-03",0,"SP-231708",null,"Wen Qi, China Telecom ","qiw@chinatelecom.cn ",null,"28.541; 28.552 ",102,52,null,null,"2024-01-03","NA"]
[174,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[175,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"2021-12-19","2022-12-10"]
[176,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"2022-12-09","2024-03-03",0.52,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","NA"]
[177,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","2023-06-08"]
[178,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.9,"CP-232167",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[179,990056,"   CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",0,"CP-232167",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com",null,"24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","NA"]
[180,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","2023-09-07","2024-03-03",0.35,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","; 8/12/23: 0%->35","32.255; 32.256; 32.291; 32.298 ",101,51,null,null,"2023-09-07","2023-12-08"]
[181,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.5,"RP-234011",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ...",null,94,48,null,null,"2022-01-06","2024-01-02"]
[182,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2024-03-01",0.95,"RP-234011","RP-232858","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"2022-01-06","2023-12-08"]
[183,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0.1,"RP-234011","RP-232858","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[184,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.52,"RP-234073",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073",null,94,48,null,null,"2022-01-06","2024-01-02"]
[185,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-234073","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[186,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","2022-03-07","2024-06-06",0.1,"RP-234073","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"2022-06-04","2023-12-08"]
[187,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-234043",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043",38.741,98,50,null,null,"2023-01-09","2024-01-02"]
[188,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[189,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[190,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"2022-09-11","2023-09-07"]
[191,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","2022-06-02","2023-06-06",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-06-08"]
[192,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","2022-06-01","2022-06-15",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[193,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","2022-06-01","2023-12-12",1,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100",22.844000000000001,98,50,null,null,"2022-12-09","2023-12-08"]
[194,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647",null,"Thales ",null,"6/10/23: WID:RP-231499->RP-232647",null,100,51,null,null,"2023-06-29","2023-10-06"]
[195,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,51,null,null,"2023-06-29","2023-09-21"]
[196,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","2023-03-03","2024-09-09",0.6,"RP-233856",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856",null,99,50,null,null,"2023-03-29","2024-01-02"]
[197,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","2023-03-03","2024-09-09",0.9,"RP-233856","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"2023-03-29","2023-12-08"]
[198,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-233856","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12...",null,99,50,null,null,"2023-03-29","2023-12-08"]
[199,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","2023-03-03","2024-06-06",0.38,"RP-234060",null,"MediaTek ",null,"2/1/24: WID:RP-230792->RP-234060",null,99,50,null,null,"2023-03-29","2024-01-02"]
[{"$f":"A200+1","v":200},991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",1,"RP-234060","RP-233258","Aijun CAO, MediaTek Inc.","aijun.cao@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2...",36.764000000000003,99,50,null,null,"2023-03-29","2024-01-04"]
[201,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","2023-03-03","2024-06-06",0,"RP-234060","RP-233258","Aijun CAO, MediaTek Inc.","aijun.cao@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[202,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"2022-03-15","2024-03-01",0.9,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437",null,95,48,null,null,"2022-04-05","2023-01-09"]
[203,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"2022-04-05","2023-01-09"]
[204,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...",36.180999999999997,95,48,null,null,"2022-04-05","2023-06-07"]
[205,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","2022-12-13","2024-03-01",0.75,"RP-223064","RP-233415","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"2023-01-09","2023-12-08"]
[206,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[207,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[208,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"2020-06-25","2021-09-13"]
[209,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[210,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[211,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"2021-12-19","2023-03-15"]
[212,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[213,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-06"]
[214,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-09"]
[215,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","NA"]
[216,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"2021-12-13","2024-03-03",0.93,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"2022-12-09","NA"]
[217,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"2021-12-13","2023-03-31"]
[218,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100",23.542000000000002,98,50,null,null,"2022-12-09","2023-06-08"]
[219,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","2023-03-13","2024-03-03",0.8,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%",27.007000000000001,99,50,null,null,"2022-12-09","2023-06-06"]
[220,990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","2023-03-13","2024-03-15",0.95,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"2022-12-09","2023-06-09"]
[221,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.881999999999998,96,49,null,null,"2022-06-02","2023-06-08"]
[222,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","2021-06-11","2022-06-09",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"2021-06-11","2023-06-08"]
[223,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[224,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[225,940080,"Study on network energy savings for NR","FS_Netw_Energy_NR",1,"Rel-18","R1","2021-12-13","2022-12-01",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...",38.863999999999997,94,48,null,null,"2022-01-06","2023-03-29"]
[226,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232672","RP-233067","Xueming Pan, vivo","panxueming@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...",38.869,94,48,null,null,"2022-01-06","2023-12-08"]
[227,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"2021-12-12","2024-06-06",0.54,"RP-233637",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637",null,97,49,null,null,"2022-09-23","2024-01-02"]
[228,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[229,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",0,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[230,940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","2021-12-12","2022-09-09",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...;...",38.865000000000002,94,48,null,null,"2022-01-06","2022-09-23"]
[231,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"2021-12-19","2022-12-10"]
[232,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"2022-12-15","2023-12-13",0.98,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[233,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added;","23.501; 23.502 ; 28.876",97,49,null,null,"2022-12-10","2024-01-04"]
[234,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","2022-12-15","2023-12-12",0.95,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[235,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","NA"]
[236,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894",null,"Ericsson",null,"2/1/24: WID:RP-230743->RP-232894",null,99,50,null,null,"2023-04-07","2024-01-02"]
[237,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894","RP-232xyz","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[238,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"2022-12-13","2024-06-06",0.49,"RP-234009",null,"Huawei ",null,"2/1/24: WID:RP-223540->RP-234009",null,98,50,null,null,"2023-01-09","2024-01-02"]
[239,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","2022-12-13","2023-12-12",1,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[240,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",0.15,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[241,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[242,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.84,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ",23.256,99,50,null,null,"2022-12-09","NA"]
[243,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"2021-12-19","2023-03-15"]
[244,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100",23.256,98,50,null,null,"2022-12-09","2023-06-08"]
[245,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100",33.890999999999998,96,49,null,null,"2022-06-02","2023-03-17"]
[246,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100",33.256,99,50,null,null,"2023-03-16","2023-09-07"]
[247,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.9,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"2022-12-09","2023-06-06"]
[248,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-09"]
[249,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[250,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",0,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","NA"]
[251,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","2021-09-13","2022-12-12",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"2021-09-13","2022-12-11"]
[252,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",0.89,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,97,49,null,null,"2022-09-11","NA"]
[253,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100",23.254999999999999,97,49,null,null,"2022-12-11","2023-06-08"]
[254,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",0.9,"CP-230189",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-06"]
[255,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.8,"CP-230189",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-09"]
[256,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386",null,94,48,null,null,"2022-01-06","2024-01-02"]
[257,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386","RP-233385","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[258,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389",null,"Nokia ",null,"2/1/24: WID:RP-230783->RP-233389",null,99,50,null,null,"2023-03-29","2024-01-02"]
[259,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389","RP-233388","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[260,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[261,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"2020-06-25","2024-03-03",0.9,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[262,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"2020-06-25","2021-06-11"]
[263,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[{"$f":"A264+1","v":264},940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"2021-12-19","2023-03-15"]
[265,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"2022-12-09","2023-06-08"]
[266,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100",33.893000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[267,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100",33.533000000000001,99,50,null,null,"2023-03-16","2023-09-07"]
[268,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","2023-03-13","2024-03-03",0.65,"CP-233309",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"2022-12-09","2023-06-06"]
[269,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","2023-03-13","2024-03-03",0.9,"CP-233309",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com",null,"24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"2022-12-09","NA"]
[270,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-233309",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%; 4/1/24: 29.586 added;","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586",99,50,null,null,"2022-12-09","2024-01-04"]
[271,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",0.7,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024",28.844999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[272,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"2022-09-30","2024-03-03",0.91,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[273,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"2021-12-19","2022-12-10"]
[274,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","2022-09-30","2023-06-06",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100",23.273,97,49,null,null,"2022-09-11","2023-06-08"]
[275,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",0.75,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%",23.273,97,49,null,null,"2022-09-11","2023-06-06"]
[276,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",0.95,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[277,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","2022-12-16","2024-03-03",0.9,"CP-232029",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[278,940081,"Study on expanded and improved NR positioning","FS_NR_pos_enh2",1,"Rel-18","R1","2022-12-13","2024-06-06",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...",38.859000000000002,94,48,null,null,"2022-01-06","2023-01-09"]
[279,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"2022-12-13","2024-06-06",0.45,"RP-233382",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382",null,98,50,null,null,"2023-01-09","2024-01-02"]
[280,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","2022-12-13","2024-03-01",0.99,"RP-233382","RP-233375","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...",38.354999999999997,98,50,null,null,"2023-01-09","2023-12-08"]
[281,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",0,"RP-233382","RP-233375","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[282,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.53,"RP-232789",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789",null,94,48,null,null,"2022-01-06","2024-01-02"]
[283,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...",38.786000000000001,94,48,null,null,"2022-01-06","2023-12-08"]
[284,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0.15,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[285,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.41,"RP-232972",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972",null,94,48,null,null,"2022-01-06","2024-01-02"]
[286,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[287,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0.1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[288,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.2,"RP-221447","RP-233003","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[289,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-234010",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010",null,94,48,null,null,"2022-01-06","2024-01-02"]
[290,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-234010","RP-232887","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[291,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-10",0.95,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20","23.700-33",95,48,null,null,"2021-12-19","2022-03-12"]
[292,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"2021-12-19","2022-12-10"]
[293,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","2022-03-10","2023-03-10",0.9,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"2022-03-10","2023-06-08"]
[294,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"2022-09-27","2023-12-12",0.94,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","NA"]
[295,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","2022-09-27","2023-06-06",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","2023-06-08"]
[296,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",0.95,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[297,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.95,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[298,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",0.9,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-06"]
[299,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","2022-12-16","2023-12-12",0.9,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","NA"]
[300,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.95,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90; 8/12/23: 90%->95",33.503,99,50,null,null,"2023-03-16","2023-12-08"]
[301,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"2021-06-11","2024-03-03",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,23.434000000000001,99,50,null,null,"2022-12-09","NA"]
[302,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","2021-06-11","2022-09-12",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"2021-06-11","2022-12-11"]
[303,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100",23.434000000000001,98,50,null,null,"2022-12-09","2023-06-08"]
[304,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-06"]
[305,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-09"]
[306,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[307,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[308,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[309,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"2021-12-20","2024-03-03",0.94,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-01-09"]
[310,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"2021-12-19","2023-03-15"]
[311,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","2022-09-23","2023-03-03",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-06-08"]
[312,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","2023-03-13","2024-03-03",0.9,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[313,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[314,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","2023-03-13","2024-03-03",0.95,"CP-232135",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[315,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","2021-09-10","2023-03-03",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"2021-09-10","2023-06-30"]
[316,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"2021-12-10","2023-09-09",0.81,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,23.434000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[317,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","2021-12-12","2023-06-06",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...",23.434000000000001,94,48,null,null,"2022-12-11","2023-06-08"]
[318,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","2021-12-12","2022-12-12",0.5,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-06"]
[319,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","2021-12-10","2022-12-09",0.85,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-09"]
[320,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","2023-03-16","2023-09-09",0.8,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80",33.433999999999997,99,50,null,null,"2023-03-16","2023-06-08"]
[321,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"2021-09-13","2024-03-03",0.82,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"2022-09-11","2022-09-23"]
[322,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"2021-09-13","2022-12-11"]
[323,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"2022-12-11","2023-06-08"]
[324,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","2022-12-16","2024-03-03",0.65,"CP-233213",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[325,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","2022-12-16","2024-03-03",0.9,"CP-233213",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"2022-09-11","2023-06-09"]
[326,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","2023-06-08","2023-09-09",0,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ",null,33.433999999999997,100,51,null,null,"2023-06-08","NA"]
[327,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"2021-03-18","2021-06-11"]
[{"$f":"A328+1","v":328},890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","2020-09-01","2020-09-17",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"2020-09-11","NA"]
[329,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"2022-06-02","2023-09-09",0.91,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"2022-06-02","2022-12-11"]
[330,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"2023-03-16","2023-06-08"]
[331,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.884,96,49,null,null,"2022-06-02","2023-06-08"]
[332,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","2023-03-16","2023-09-09",0.85,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50; 8/12/23: 50%->85",33.122,99,50,null,null,"2023-03-16","2023-12-08"]
[333,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","2023-03-16","2023-09-09",0.75,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,29.222000000000001,99,50,null,null,"2023-03-16","2023-06-08"]
[334,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"2020-06-25","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"2021-06-11","NA"]
[335,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[336,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"2021-06-11","2021-12-10"]
[337,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100",28.902000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[338,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"2021-06-11","2022-12-11"]
[339,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"2022-06-03","2024-03-03",0.88,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"2022-06-03","2023-06-30"]
[340,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","2022-06-06","2024-03-03",0.85,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->",24.558,96,49,null,null,"2022-06-03","2023-06-09"]
[341,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","2022-06-03","2024-03-03",0.9,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"2022-06-03","2023-06-06"]
[342,980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","2022-12-09","2023-12-12",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100",28.843,98,50,null,null,"2022-12-09","2023-09-07"]
[343,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",0.8,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ","; 8/12/23: 0%->80","32.240; 32.290 ",101,51,null,null,"2023-09-06","2023-12-08"]
[344,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[345,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","2022-06-02","2022-06-10",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100",22.100999999999999,96,49,null,null,"2022-06-02","2022-09-12"]
[346,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100",33.18,94,48,null,null,"2021-12-10","2023-06-08"]
[347,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"2021-12-10","2024-03-03",0.81,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-03-17"]
[348,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","2021-12-10","2023-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-06-08"]
[349,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","2023-06-07","2024-03-03",0.5,"CP-231355",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,51,null,null,"2023-06-07","2023-06-30"]
[350,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"2020-06-25","2024-03-03",0.74,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","NA"]
[351,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","2020-06-25","2021-09-20",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"2020-06-26","2021-09-13"]
[352,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","2021-09-10","2022-06-10",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","2022-09-12"]
[353,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","2023-03-13","2024-03-03",0.2,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,null,"2021-09-10","2022-09-12"]
[354,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"2019-03-07","2023-12-12",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[355,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","2019-03-07","2022-03-11",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100",23.289000000000001,93,47,null,null,"2021-09-10","2022-12-11"]
[356,970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","2022-09-13","2023-12-12",1,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"2022-09-05","2023-06-06"]
[357,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"2019-03-07","2023-12-12",0.9,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[358,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","2019-03-07","2022-09-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22",23.289000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[359,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","2022-09-13","2023-12-12",0.6,"CP-233210",null,"Haitao Wei, Huawei","weihaitao@huawei.com",null,"24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"2022-09-05","NA"]
[360,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%",33.503,97,49,101,null,"2022-09-11","2023-06-08"]
[361,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[362,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[363,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","2022-12-09","2024-03-04",0.75,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[364,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[365,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","2023-09-09","2024-03-04",0.5,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"2022-12-09","2023-06-08"]
[366,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","2019-09-19","2021-12-10",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"2019-09-13","2021-09-13"]
[367,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","2021-12-13","2023-03-03",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"2021-12-13","2023-06-08"]
[368,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"2021-12-13","2023-03-17"]
[369,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","2018-06-06","2022-06-10",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"2018-06-06","2022-06-04"]
[370,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[371,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"2019-12-06","2021-12-10",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"2021-06-11","2022-07-13"]
[372,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","2019-12-06","2021-06-11",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"2019-12-06","2022-06-21"]
[373,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"2021-06-11","2022-06-21"]
[374,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-221348","RP-233132","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...",38.843000000000004,94,48,null,null,"2022-01-06","2023-12-08"]
[375,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"2021-12-20","2024-03-03",0.96,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[376,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","2022-06-21","2023-03-03",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100",33.898000000000003,96,49,null,null,"2022-06-21","2023-09-07"]
[377,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220071",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"2021-12-19","2022-12-10"]
[378,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[379,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","2023-03-13","2024-03-03",0.92,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"2022-12-09","2023-06-06"]
[380,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"2022-12-09","2023-06-06"]
[381,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"2021-12-13","2023-12-12",0.8,"RP-233441",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441",null,94,48,null,null,"2022-01-06","2024-01-02"]
[382,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.8,"RP-233441","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[383,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100",33.877000000000002,96,49,null,null,"2022-06-02","2023-09-07"]
[384,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100",28.908000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[385,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","2023-03-17","2023-12-12",0.35,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"2023-03-17","2023-09-07"]
[386,1020023,"NEF Charging enhancement to support AI/ML in 5GS ","AIMLsysNEF_CH",1,"Rel-18","S5","2023-12-07","2023-12-12",0,"SP-231706",null,"Alla Goldner, OPPO ","v-alla.goldner@oppo.com ",null,"32.254; 32.291 ",102,52,null,null,"2023-12-07","NA"]
[387,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-18","S4","2022-03-12","2024-03-03",0.5,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50","26.927; 26.847",95,48,null,null,"2022-03-10","2023-12-08"]
[388,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[389,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-232993",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993",null,94,48,null,null,"2022-01-06","2024-01-02"]
[390,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232993","RP-232992","Rui Zhou, CATT","zhourui@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[391,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.92,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","NA"]
[{"$f":"A392+1","v":392},940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"2021-12-19","2022-12-10"]
[393,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","2023-06-08"]
[394,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",0.95,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024",null,99,50,null,null,"2022-12-09","2023-06-30"]
[395,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",0.95,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","; 9/6/23: 15%->40",null,99,50,null,null,"2022-12-09","2023-06-09"]
[396,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",0.95,"CP-232031",null,"Meng Li, Huawei, Huawei ","giorgi.gulbani@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,null,"2022-12-09","2023-06-06"]
[397,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","2023-06-08","2023-09-09",0,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ",null,33.500999999999998,100,51,null,null,"2023-06-08","NA"]
[398,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100",33.883000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[399,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"2021-06-15","2023-09-08",1,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"2021-07-02","2023-01-09"]
[400,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","2021-06-15","2023-09-08",1,"RP-232590","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",36.792000000000002,92,47,null,null,"2021-07-02","2023-10-06"]
[401,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[402,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024",31.102,92,47,null,null,"2021-07-02","2023-06-06"]
[403,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","2023-03-13","2023-03-24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[404,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[405,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[406,0,"Rel-18 Slice","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[407,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","2021-03-12","2022-09-22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[408,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[409,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[410,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","2020-06-25","2021-03-17",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"2020-06-25","2021-06-11"]
[411,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[412,1000023,"   Stopped – CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[413,1000044,"   Stopped – CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[414,1000045,"   Stopped – CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[415,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.94,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","NA"]
[416,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"2021-12-19","2022-12-10"]
[417,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","2022-06-02","2023-03-03",0.9,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90",33.886000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[418,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[419,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",0.95,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[420,990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.9,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-09"]
[421,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[422,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793",null,"ZTE ",null,"2/1/24: WID:RP-230787->RP-232793",null,99,50,null,null,"2023-03-29","2024-01-02"]
[423,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793","RP-232866","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[424,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[425,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","2022-03-10","2023-12-12",1,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12...",28.835999999999999,95,48,null,null,"2022-03-10","2023-12-08"]
[426,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added;","28.312 ; 28.914",99,50,null,null,"2023-03-16","2024-01-04"]
[427,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","2021-03-18","2021-12-10",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"2021-03-18","2022-06-04"]
[428,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","2022-06-15","2023-12-12",1,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100",26.940999999999999,96,49,null,null,"2022-06-03","2023-12-08"]
[429,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","2021-12-10","2022-03-11",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"2021-12-10","2022-06-04"]
[430,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","2021-03-18","2022-09-12",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"2021-03-18","2022-12-11"]
[431,1020049,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18",null,"2022-06-02","2024-03-15",0.17,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[432,960013,"   (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement","NSCALE",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[433,1020050,"   CT1 aspects of NSCALE","NSCALE",2,"Rel-18","C1","2022-06-02","2024-03-15",0,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,24.548999999999999,96,49,null,null,"2022-06-02","2023-06-08"]
[434,1020006,"   CT3 aspects of NSCALE","NSCALE",2,"Rel-18","C3","2022-06-02","2024-03-15",0.15,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.222, 29.520, 29.522, 29.549",96,49,null,null,"2022-06-02","2023-06-08"]
[435,1020046,"   CT4 aspects of NSCALE","NSCALE",2,"Rel-18","C4","2022-06-02","2024-03-15",0,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,29.536000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[436,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","2022-06-03","2023-09-09",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"2022-06-03","2022-07-13"]
[437,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","2021-01-12","2023-03-03",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"2021-01-12","2023-03-17"]
[438,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",0.75,"SP-231448",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"2022-12-09","2024-01-03"]
[439,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","2023-06-30","2024-03-03",1,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;",31.105,100,51,null,null,"2023-06-30","2023-09-21"]
[440,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[441,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-232778",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778",null,98,50,null,null,"2023-01-09","2024-01-02"]
[442,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","2022-12-13","2023-12-12",1,"RP-223502","RP-232779","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[443,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","2021-12-13","2023-03-03",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...",38.835000000000001,94,48,null,null,"2022-01-06","2023-03-17"]
[444,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"2021-12-20","2024-03-03",0.94,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"2022-12-09","NA"]
[445,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"2021-12-19","2022-12-10"]
[446,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-09-07"]
[447,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","2023-03-13","2024-03-03",0.85,"CP-232134",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[448,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","2023-03-13","2024-03-03",0.95,"CP-232134",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[449,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","2022-03-10","2024-03-03",0.7,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...",26.93,95,48,null,null,"2022-03-10","2023-12-08"]
[450,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","2022-03-15","2024-03-03",0.6,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60",26.113,95,48,null,null,"2022-03-10","2023-12-08"]
[451,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","2022-03-10","2023-06-06",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"2022-03-10","2023-06-08"]
[452,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","2022-03-10","2024-03-03",0.8,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"2022-03-10","2023-12-08"]
[453,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","2022-06-03","2024-03-03",0.5,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1...",26.263999999999999,96,49,null,null,"2022-06-03","2023-12-08"]
[454,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","2022-06-03","2023-06-06",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"2022-06-03","2023-06-08"]
[455,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","2022-06-03","2024-03-03",0.6,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...",26.521999999999998,96,49,null,null,"2022-06-03","2023-12-08"]
[{"$f":"A456+1","v":456},830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","2019-03-07","2024-03-03",0.6,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/...","26.260; new",83,42,null,null,"2019-03-14","2023-12-08"]
[457,770024,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18","S4","2017-09-08","2024-03-03",0.78,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2023-12-08"]
[458,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","2023-03-16","2024-03-03",0.25,"SP-231291",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291","26.119 ; 26.566; 26.866; 26.865",99,50,null,null,"2023-03-16","2023-12-08"]
[459,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","2022-06-03","2024-03-03",0.6,"SP-231291",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%...",26.565000000000001,96,49,null,null,"2022-06-03","2024-01-03"]
[460,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","2022-06-03","2024-03-03",0.65,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65",26.812000000000001,96,49,null,null,"2022-06-03","2023-12-08"]
[461,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","2022-06-03","2022-12-08",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"2022-06-03","2022-12-11"]
[462,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[463,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","2020-06-25","2021-12-10",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"2020-06-25","2021-12-10"]
[464,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","2020-06-25","2021-09-16",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"2020-06-26","2022-03-12"]
[465,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"2022-03-03","2023-12-12",0.5,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-03-10","2022-09-12"]
[466,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","2022-03-03","2022-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-12-11","2023-06-08"]
[467,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","2022-12-16","2023-12-12",0.6,"CP-233217",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2023-06-06"]
[468,980071,"   CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","2022-12-16","2023-12-12",0,"CP-233217",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,"24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2022-09-12"]
[469,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"2020-12-04","2022-06-21"]
[470,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"2021-09-13","2022-12-11"]
[471,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"2022-09-09","2024-03-03",0.92,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"2022-09-11","NA"]
[472,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"2022-12-11","2023-06-08"]
[473,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",0.85,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[474,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",0.95,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","NA"]
[475,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"2022-09-12","2024-03-03",0.51,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[476,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[477,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","2023-06-07","2024-03-03",0.7,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,51,null,null,"2023-06-07","NA"]
[478,1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","2023-06-07","2024-03-03",0,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,51,null,null,"2023-06-07","NA"]
[479,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"2022-03-15","2024-06-06",0.72,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"2022-04-05","2022-09-23"]
[480,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","2022-03-15","2023-09-22",1,"RP-222272","RP-233146","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[481,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","2022-03-16","2024-03-01",0.8,"RP-233151","RP-233146","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"2022-04-05","2024-01-02"]
[482,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.42,"RP-221402","RP-233141","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[483,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[484,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"2019-09-19","2024-03-03",0.87,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"2021-06-11","NA"]
[485,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","2019-09-19","2021-09-08",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"2019-09-13","2021-09-13"]
[486,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"2021-06-11","2021-09-13"]
[487,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"2021-12-19","2023-03-16"]
[488,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[489,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","2023-03-13","2024-03-03",0.7,"CP-233211",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,null,"2022-09-11","2023-06-06"]
[490,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-233211",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,null,"2022-09-11","NA"]
[491,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","2023-03-13","2024-03-03",0.6,"CP-233211",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"2022-09-11","2024-01-04"]
[492,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","2022-06-02","2023-06-06",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100",33.89,96,49,null,null,"2022-06-02","2023-06-08"]
[493,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",0,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ",null,33.328000000000003,99,50,null,null,"2023-03-16","NA"]
[494,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","2023-06-08","2024-03-03",0.4,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ","; 8/12/23: 0%->40","32.260; 32.255; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2023-12-08"]
[495,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.91,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[496,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"2021-12-19","2022-12-10"]
[497,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[498,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",0.8,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[499,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.95,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-09"]
[500,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.8,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[501,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"2021-12-19","2023-03-15"]
[502,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"2022-09-12","2024-03-03",0.98,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2022-12-10"]
[503,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[504,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","2023-03-13","2024-03-03",0.95,"CP-232027",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-06"]
[505,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","2023-04-18","2024-03-03",0.99,"CP-232027",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-09"]
[506,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"2020-12-04","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[507,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","2020-12-04","2021-06-11",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"2020-12-04","2021-12-10"]
[508,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[509,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[510,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",0.78,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"2022-09-11","2022-09-12"]
[511,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-03-03",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"2022-12-11","2023-06-08"]
[512,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","2022-12-15","2023-12-12",0.65,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[513,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","2022-12-15","2023-12-12",0.8,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[514,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","2022-06-02","2023-12-12",0.65,"SP-231156",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156",23.957999999999998,96,49,null,null,"2022-06-02","2023-09-13"]
[515,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"2021-06-11","2022-12-11"]
[516,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"2021-12-20","2023-12-12",0.95,null,null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2022-12-11","NA"]
[517,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2021-12-19","2022-03-12"]
[518,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"2021-12-19","2022-12-10"]
[519,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","2022-03-10","2022-12-12",0.9,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90",33.738999999999997,95,48,null,null,"2022-03-10","2023-06-08"]
[{"$f":"A520+1","v":520},970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","2022-09-23","2023-06-06",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[521,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",0.9,"CP-233026",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[522,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",0.9,"CP-233026",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-06"]
[523,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.95,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95","33.558; 33.501 ",99,50,null,null,"2023-03-16","2023-09-07"]
[524,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[525,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"2020-09-16","2021-09-08",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"2021-06-11","NA"]
[526,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","2020-09-16","2021-06-11",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"2020-09-10","2021-09-13"]
[527,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[528,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"2021-12-13","2024-03-03",0.92,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2022-12-10"]
[529,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"2021-12-19","2023-03-15"]
[530,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2023-06-08"]
[531,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",0.99,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99",33.857999999999997,96,49,null,null,"2022-06-02","2023-06-08"]
[532,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",0.9,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90",33.500999999999998,99,50,null,null,"2023-03-16","2023-09-07"]
[533,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",0.9,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-30"]
[534,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","2022-12-15","2024-03-03",0.95,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-09"]
[535,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",0.85,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-06"]
[536,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100",28.827999999999999,94,48,null,null,"2021-12-13","2023-03-17"]
[537,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","2023-03-16","2024-03-03",0.65,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"2023-03-16","2023-12-08"]
[538,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","2023-03-06","2023-12-12",1,"RP-233569","RP-233567","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"2023-04-07","2024-01-02"]
[539,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[540,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"2019-05-31","2023-03-15"]
[541,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"2022-09-09","2024-03-03",0.88,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","NA"]
[542,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[543,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","2022-12-16","2024-03-03",0.8,"CP-233206",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[544,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","2022-12-16","2024-03-03",0.9,"CP-233206",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[545,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","2022-12-16","2024-03-03",0.85,"CP-233206",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[546,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"2022-09-12","2023-12-12",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-03-22"]
[547,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[548,1000040,"   CT3 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,51,null,null,"2023-06-07","NA"]
[549,1020048,"   CT4 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C4","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",102,52,null,null,"2023-06-07","NA"]
[550,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"2019-03-07","2023-12-13",0.99,"CP_233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"2022-03-10","NA"]
[551,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","2019-03-07","2023-12-12",0.98,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"2022-09-07","2023-06-06"]
[552,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","2019-03-11","2023-12-12",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,29.518000000000001,97,49,null,null,"2022-09-07","NA"]
[553,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"2019-03-07","2024-03-03",0.73,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[554,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"2021-12-19","2022-09-12"]
[555,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","2019-03-07","2023-03-03",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-03-15"]
[556,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[557,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","2023-03-13","2024-03-03",0.95,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[558,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"2021-12-20","2023-09-09",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,97,49,null,null,"2022-09-11","NA"]
[559,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102",23.501999999999999,97,49,null,null,"2022-09-11","2023-03-16"]
[560,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[561,1020047,"   CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C4","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[562,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[563,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-18","S4","2023-06-08","2024-03-03",0.2,"SP-230539",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024",26.954999999999998,100,51,null,null,"2023-06-08","2023-12-08"]
[564,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","2023-06-08","2024-03-03",0.65,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65","26.955 ; 26.966",100,51,null,null,"2023-06-08","2023-12-08"]
[565,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-18","S4","2023-06-08","2024-03-03",0.2,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20",26.812999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[566,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","2021-12-13","2022-12-12",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"2021-12-13","2022-12-11"]
[567,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","2022-06-02","2024-03-03",0.65,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"2022-06-03","2023-12-08"]
[568,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","2022-12-09","2023-03-03",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"2022-12-09","2023-03-17"]
[569,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","2022-06-02","2023-06-06",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100",26.501000000000001,96,49,null,null,"2022-06-03","2023-06-08"]
[570,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","2022-12-12","2024-03-03",0.75,"SP-231709",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709",26.114000000000001,98,50,null,null,"2022-12-09","2024-01-03"]
[571,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","2020-03-25","2023-09-09",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...",26.925000000000001,87,44,null,null,"2019-12-06","2023-09-07"]
[572,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","2023-06-08","2024-03-03",0.4,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40","26.140; 26.141 ; 26.143",100,51,null,null,"2023-06-08","2023-12-08"]
[573,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","2023-06-08","2024-03-03",0.55000000000000004,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55","26.512; 26.247; 26.517; 26.532 ; 26.510",100,51,null,null,"2023-06-08","2023-12-08"]
[574,0,"Rel-18 Other topics","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[575,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",0.93,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[576,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"2017-06-03","2023-03-15"]
[577,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100",33.887,96,49,null,null,"2022-06-02","2023-06-08"]
[578,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-09","2023-06-08"]
[579,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",0.9,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-30"]
[580,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-09"]
[581,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[582,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",0.8,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[583,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","2023-09-06","2024-03-03",0.4,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 8/12/23: 0%->40","32.255; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2023-12-08"]
[{"$f":"A584+1","v":584},980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"2022-09-09","2023-12-12",0.95,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-23","NA"]
[585,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-12","2023-06-08"]
[586,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","NA"]
[587,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","2022-12-15","2023-12-12",0.9,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","2023-06-06"]
[588,970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","2022-09-23","2024-03-03",0.87,"SP-220981",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"2022-09-11","2023-12-08"]
[589,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"2021-12-13","2024-03-03",0.53,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"2022-09-11","2022-12-11"]
[590,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","2021-12-13","2022-09-12",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"2021-12-13","2022-12-11"]
[591,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","2022-09-12","2023-06-06",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"2022-09-11","2023-06-08"]
[592,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","2022-09-12","2024-03-03",0.2,"CP-230333",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"2022-09-11","2023-06-06"]
[593,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","2022-09-12","2024-03-03",0.4,"CP-230333",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5",29.548999999999999,97,49,null,null,"2022-09-11","2023-06-09"]
[594,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"2021-12-19","2022-06-04"]
[595,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"2022-09-08","2023-09-09",0.98,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[596,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[597,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","2022-12-16","2023-09-09",0.99,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[598,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-09"]
[599,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","2022-12-16","2023-09-09",0.95,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","NA"]
[600,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"2021-12-20","2024-03-03",0.96,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[601,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[602,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231193",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[603,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","2021-12-20","2023-12-12",0.9,"CP-231193",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[604,940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"2021-12-19","2022-12-10"]
[605,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"2021-12-19","2023-03-15"]
[606,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"2022-09-08","2024-03-03",0.99,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[607,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","2022-09-08","2023-06-06",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[608,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[609,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","2022-12-16","2024-03-03",0.98,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[610,1020064,"      (IETF) CT3 part of DetNet (draft-ietf-detnet-yang)","DetNet",3,"Rel-18","C3-IETF","2022-12-16","2024-03-03",0.98,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.513, 29.565",97,49,null,null,"2022-09-11","2023-06-06"]
[611,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[612,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[613,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100",23.273,97,49,null,null,"2022-12-10","2022-12-10"]
[614,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[615,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[616,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"2022-12-10","2023-03-22"]
[617,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"2022-09-11","2023-06-06"]
[618,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-09-11","NA"]
[619,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-12-10","2023-03-22"]
[620,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","2023-06-06"]
[621,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[622,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[623,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"2022-09-08","2024-03-03",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[624,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[625,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[626,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-09"]
[627,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","NA"]
[628,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"2022-03-10","2023-12-15",0.85,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70",23.553999999999998,95,48,null,null,"2022-03-10","2022-12-11"]
[629,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","2022-03-10","2023-03-03",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100",23.553999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[630,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","2023-03-13","2023-12-15",0.5,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-06"]
[631,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","2023-03-13","2023-12-15",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-09"]
[632,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","2023-02-02","2023-03-03",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[633,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"2020-06-25","2024-03-03",0.98,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"2021-03-18","NA"]
[634,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","2020-06-25","2021-03-12",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"2020-06-25","2021-06-11"]
[635,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"2021-12-19","2023-03-15"]
[636,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"2021-03-18","2021-06-11"]
[637,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[638,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-30"]
[639,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","2022-12-16","2024-03-03",0.98,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-06"]
[640,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","2022-12-16","2023-12-12",0.9,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"2022-09-11","2023-06-30"]
[641,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772",28.832000000000001,95,48,null,null,"2022-03-10","2023-06-30"]
[642,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","2021-12-13","2022-09-22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",38.878999999999998,94,48,null,null,"2022-01-06","2022-09-23"]
[643,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863",null,"Nokia ",null,"2/1/24: WID:RP-230754->RP-232863",null,99,50,null,null,"2023-03-29","2024-01-02"]
[644,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863","RP-232864","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[645,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"2020-09-16","2024-03-03",0.99,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[646,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","2020-09-16","2021-09-08",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"2020-09-10","2021-09-13"]
[647,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-14"]
[{"$f":"A648+1","v":648},980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added;","23.501; 23.502; 23.503; 23.273 ; 28.875",98,50,null,null,"2022-12-09","2024-01-04"]
[649,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","2023-03-13","2024-03-03",0.95,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[650,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[651,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"2021-12-19","2022-12-10"]
[652,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"2021-12-13","2024-06-06",0.56000000000000005,"RP-233320",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320",null,94,48,null,null,"2022-01-06","2024-01-02"]
[653,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-233320","RP-233319","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[654,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","2021-12-15","2024-06-06",0.2,"RP-233320","RP-233319","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[655,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"2022-01-06","2023-01-09"]
[656,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-223488","RP-233603","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[657,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-231432",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432",28.863,94,48,null,null,"2021-12-13","2024-01-03"]
[658,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","2022-03-10","2024-03-03",0.99,"SP-231440",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440",null,95,48,null,null,"2022-03-10","2024-01-03"]
[659,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"2021-09-10","2024-03-03",0.88,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"2021-09-10","2022-01-07"]
[660,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[661,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"2021-12-19","2023-06-08"]
[662,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","2023-06-07","2024-03-03",0.8,"CP-232166",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[663,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","2023-06-07","2024-03-03",0.7,"CP-232166",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[664,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"2021-01-01","2023-12-12",1,"RP-233438",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438",null,94,48,null,null,"2022-01-06","2024-01-02"]
[665,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","2021-01-01","2023-12-12",1,"RP-233438","RP-233437","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[666,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-233438","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"2022-04-05","2023-10-06"]
[667,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","2021-12-10","2024-03-03",0.9,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024","28.313; ; 28.317",94,48,null,null,"2021-12-10","2023-12-08"]
[668,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","2020-12-04","2021-03-12",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-04","2020-12-05"]
[669,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","2021-03-18","2021-03-25",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-03-19"]
[670,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","2022-09-16","2024-06-06",0.42,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[671,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","2022-12-16","2023-06-06",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"2022-09-19","2023-06-06"]
[672,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","2022-09-16","2022-09-16",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,31.102,97,49,null,null,"2022-09-19","NA"]
[673,1010052,"   UE Conformance - Signal level Enhanced Network Selection ","SENSE-UEContest",2,"Rel-18","R5","2023-09-09","2024-06-06",0.05,"RP-233770","RP-233769","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770",null,101,51,null,null,"2023-10-06","2024-01-02"]
[674,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","2021-12-10","2023-03-03",0.75,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75","33.527; 33.927; 33.936",94,48,null,null,"2021-12-10","2023-03-17"]
[675,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.3,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"2022-03-10","2023-03-17"]
[676,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100",33.892000000000003,96,49,null,null,"2022-06-02","2023-09-07"]
[677,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","2018-09-06","2022-12-09",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ...","New",81,41,null,null,"2018-09-06","2023-06-08"]
[678,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"2022-06-02","2023-09-07"]
[679,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.6,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","2023-06-06"]
[680,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[681,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[682,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.6,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","2023-06-06"]
[683,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[684,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[685,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[686,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"2022-06-03","2024-03-03",0.73,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2022-06-20"]
[687,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","2022-06-03","2024-03-03",0.6,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[688,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","2022-06-06","2024-03-03",0.9,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[689,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","2022-06-03","2024-03-03",0.8,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-06"]
[690,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","2022-06-03","2022-12-08",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"2022-06-03","2022-06-20"]
[691,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.75,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,null,"2022-06-03","2022-06-20"]
[692,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",0.6,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-06"]
[693,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",0.9,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-09"]
[694,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","2022-03-07","2024-03-03",0.4,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,null,"2022-06-03","2023-06-06"]
[695,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","2022-12-15","2023-12-12",0.9,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"2022-06-03","2023-06-06"]
[696,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","2023-03-13","2023-12-15",1,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"2022-06-03","2023-06-06"]
[697,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-18","C4","2022-08-25","2024-03-03",0.4,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,null,"2022-06-03","2023-09-21"]
[698,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,51,null,null,"2023-09-20","NA"]
[699,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",22.260999999999999,101,51,null,null,"2023-09-20","NA"]
[700,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100",33.500999999999998,101,51,null,null,"2023-09-20","2023-12-08"]
[701,1020001,"NRF API enhancements to avoid signalling and storing of redundant data","NRFe",1,"Rel-18","C4","2023-12-12","2024-03-15",0.4,"CP-233025",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com",null,"29.510, 29.571, 29.504",96,49,null,null,"2022-06-03","2023-06-06"]
[702,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[703,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","2022-03-10","2023-03-03",0.95,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95","33.926 ; 33.537",95,48,null,null,"2022-03-10","2023-06-08"]
[704,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","2023-03-16","2023-12-12",0.4,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23","33.926 ; 33.528",99,50,null,null,"2023-03-16","2023-09-07"]
[705,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[706,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","2022-12-09","2023-09-09",0.8,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[707,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","2022-03-10","2023-03-03",0.99,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99","33.926 ; 33.742; 33.523",95,48,null,null,"2022-03-10","2023-06-08"]
[708,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","2022-03-10","2024-03-03",0.89,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ",null,"33.501; 33.535 ",98,50,null,null,"2022-12-09","NA"]
[709,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"2022-03-10","2023-03-17"]
[710,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2023-09-07"]
[711,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","2023-09-09","2024-03-03",0.6,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"2022-12-09","NA"]
[{"$f":"A712+1","v":712},950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",0.95,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95",33.737000000000002,95,48,null,null,"2022-03-10","2023-06-08"]
[713,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","2023-03-16","2023-09-09",0.95,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95",33.534999999999997,99,50,null,null,"2023-03-16","2023-06-08"]
[714,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","2021-12-13","2023-03-03",0.8,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80",33.869999999999997,94,48,null,null,"2021-12-13","2023-09-07"]
[715,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","2018-12-13","2022-12-09",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%->...",null,82,42,null,null,"2018-12-06","2023-09-07"]
[716,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100",33.893999999999998,96,49,null,null,"2022-06-02","2023-09-07"]
[717,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100",33.896000000000001,96,49,null,null,"2022-06-02","2023-03-17"]
[718,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","2023-05-01","2023-06-06",0,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ",null,33.500999999999998,100,51,null,null,"2023-06-08","NA"]
[719,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","2023-09-06","2024-03-03",0.1,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 8/12/23: 0%->10",33.926000000000002,101,51,null,null,"2023-09-06","2023-12-08"]
[720,0,"Rel-18 NR-only: topics other than band","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[721,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"2022-03-15","2024-03-01",0.76,"RP-233586",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586",null,95,48,null,null,"2022-04-05","2024-01-02"]
[722,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","2023-06-07","2023-12-12",1,"RP-233586","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[723,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","2022-03-15","2024-03-01",0.7,"RP-233586","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...",38.878,95,48,null,null,"2022-04-05","2023-12-08"]
[724,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025",null,"Ericsson",null,"2/1/24: WID:RP-230813->RP-234025",null,99,50,null,null,"2023-04-07","2024-01-02"]
[725,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025","RP-233392","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[726,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"2022-12-13","2024-03-01",0.65,"RP-234004",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004",null,98,50,null,null,"2023-01-09","2024-01-02"]
[727,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",0.65,"RP-234004","RP-232928","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[728,981242,"   Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",0.65,"RP-234004","RP-232928","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[729,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"2022-09-12","2025-06-06",0.43,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"2022-10-19","2023-01-09"]
[730,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",1,"RP-223499","RP-233448","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...",38.895000000000003,97,49,null,null,"2022-10-19","2023-12-08"]
[731,970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","2022-09-13","2023-12-12",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"2022-10-19","2022-12-09"]
[732,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",0.35,"RP-231152","RP-233416","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[733,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",0.61,"RP-233031",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031",null,97,49,null,null,"2022-10-19","2024-01-02"]
[734,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","2022-09-12","2024-03-01",0.8,"RP-233031","RP-233032","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...",38.896000000000001,97,49,null,null,"2022-10-19","2023-12-08"]
[735,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-01",0.8,"RP-233031","RP-233032","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"2022-10-19","2023-12-08"]
[736,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.05,"RP-232774","RP-232773","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774",null,100,51,null,null,"2023-06-29","2024-01-02"]
[737,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"2022-09-12","2024-03-01",0.9,"RP-233975",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975",null,97,49,null,null,"2022-10-19","2024-01-02"]
[738,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","2022-09-12","2024-03-01",0.8,"RP-233975","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....",38.896999999999998,97,49,null,null,"2022-10-19","2023-12-08"]
[739,970287,"   Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","2022-09-13","2024-03-01",1,"RP-233975","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,102,null,"2022-10-19","2024-01-02"]
[740,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"2022-09-12","2024-03-03",0.4,"RP-233561",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561",null,97,49,null,null,"2022-10-19","2024-01-02"]
[741,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","2022-09-12","2024-03-01",0.8,"RP-233561","RP-233562","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...",38.899000000000001,97,49,null,null,"2022-10-19","2023-12-08"]
[742,970289,"   Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-03",0,"RP-233561","RP-233562","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"2022-10-19","2023-12-08"]
[743,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"2022-09-12","2024-03-01",0.65,"RP-234017",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017",null,97,49,null,null,"2022-10-19","2024-01-02"]
[744,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","2022-09-12","2024-03-01",0.3,"RP-234017","RP-233035","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...",38.85,97,49,null,null,"2022-10-19","2023-12-08"]
[745,970290,"   Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-01",1,"RP-234017","RP-233035","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,102,null,"2022-10-19","2024-01-02"]
[746,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"2022-09-08","2024-03-01",0.7,"RP-232952",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952",null,97,49,null,null,"2022-09-23","2024-01-02"]
[747,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","2022-09-08","2024-03-01",0.7,"RP-232952","RP-232951","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[748,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","2022-09-08","2024-06-06",0.71,"RP-233742",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742",38.761000000000003,97,49,null,null,"2022-09-23","2024-01-02"]
[749,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",1,"RP-233742","RP-233741","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[750,970281,"   Perf. part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",0.5,"RP-233742","RP-233741","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[751,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"2022-12-13","2024-03-01",0.7,"RP-233446",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446",null,98,50,null,null,"2023-01-09","2024-01-02"]
[752,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",0.7,"RP-233446","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"2023-01-09","2023-12-08"]
[753,981247,"   Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",0.7,"RP-233446","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[754,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"2021-12-13","2024-06-06",0.67,"RP-234027",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027",null,94,48,null,null,"2022-01-06","2024-01-02"]
[755,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","2021-12-13","2023-12-12",1,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[756,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","2021-12-15","2024-06-06",0.4,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[757,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.78,"RP-232957",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957",null,94,48,null,null,"2022-01-06","2024-01-02"]
[758,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[759,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0.6,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[760,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",0.5,"RP-234012",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012",null,94,48,null,null,"2022-01-06","2024-01-02"]
[761,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-234012","RP-233545","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[762,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0.1,"RP-234012","RP-233545","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[763,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.78,"RP-233558",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558",null,94,48,null,null,"2022-01-06","2024-01-02"]
[764,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-233558","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[765,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0.6,"RP-233558","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[766,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"2021-12-13","2024-06-06",0.57999999999999996,"RP-233028",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028",null,94,48,null,null,"2022-01-06","2024-01-02"]
[767,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[768,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",0.25,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[769,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-223041","RP-233435","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...",38.857999999999997,94,48,null,null,"2022-01-06","2023-12-08"]
[770,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"2022-09-08","2024-06-06",0.82,"RP-232886",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886",null,97,49,null,null,"2022-09-23","2024-01-02"]
[771,970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-232886","RP-232854","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[772,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",0.5,"RP-232886","RP-232854","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[773,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","2022-09-08","2024-06-06",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%-...",38.866999999999997,94,48,null,null,"2022-01-06","2022-09-23"]
[774,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",0.5,"RP-233970",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970",null,94,48,null,null,"2022-01-06","2024-01-02"]
[775,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","2021-12-13","2024-03-01",0.95,"RP-233970","RP-233251","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[{"$f":"A776+1","v":776},940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",0.1,"RP-233970","RP-233251","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[777,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-233485",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485",null,94,48,null,null,"2022-01-06","2024-01-02"]
[778,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233485","RP-233484","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[779,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-233976",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976",null,95,48,null,null,"2022-04-05","2024-01-02"]
[780,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[781,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[782,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"2022-03-15","2025-06-06",0.64,"RP-234023",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023",null,95,48,null,null,"2022-04-05","2024-01-02"]
[783,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-234023","RP-233443","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[784,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","2022-03-16","2024-03-01",0.8,"RP-234023","RP-233443","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[785,1020087,"   UE Conformance - Air-to-ground network for NR ","NR_ATG-UEConTest",2,"Rel-19","R5","2023-12-12","2025-06-06",0,"RP-233412",null,"CMCC ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[786,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"2022-03-15","2024-03-01",0.92,"RP-232791",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791",null,95,48,null,null,"2022-04-05","2024-01-02"]
[787,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-232791","RP-232790","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...",38.890999999999998,95,48,null,null,"2022-04-05","2023-12-08"]
[788,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","2022-03-15","2024-03-01",0.85,"RP-232791","RP-232790","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[789,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"2022-03-15","2023-11-30",0.74,"RP-234020","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"2022-04-05","2024-01-02"]
[790,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-234020","RP-233077","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...",38.750999999999998,95,48,null,null,"2022-04-05","2023-12-08"]
[791,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","2022-03-15","2024-03-01",0.5,"RP-234020","RP-233077","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[792,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"2022-03-15","2024-06-06",0.5,"RP-233496",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496",null,95,48,null,null,"2022-04-05","2024-01-02"]
[793,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233496","RP-233494","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[794,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","2022-03-17","2024-06-06",0.1,"RP-233496","RP-233494","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[795,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"2022-03-15","2024-06-06",0.92,"RP-233186",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186",null,95,48,null,null,"2022-04-05","2024-01-02"]
[796,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...",38.881,95,48,null,null,"2022-04-05","2023-12-08"]
[797,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",0.85,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[798,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"2022-03-15","2023-12-12",0.83,"RP-233513",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513",null,95,48,null,null,"2022-04-05","2024-01-02"]
[799,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[800,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","2022-03-16","2023-12-12",0.7,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[801,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"2022-03-15","2024-06-06",0.59,"RP-234021",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021",null,95,48,null,null,"2022-04-05","2024-01-02"]
[802,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-234021","RP-233256","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[803,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",0.1,"RP-234021","RP-233256","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[804,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","2022-12-14","2024-03-01",0.9,"RP-223246","RP-233248","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ; 8/12/23: FCD:03/03/2024...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[805,0,"Rel-18 NR-only: band related","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[806,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","2023-03-06","2023-12-12",0.99,"RP-233245",null,"Vodafone",null,"6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245",null,99,50,null,null,"2023-04-07","2024-01-02"]
[807,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[808,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[809,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","2023-03-06","2024-06-06",0.38,"RP-233999",null,"Vodafone",null,"6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999",null,99,50,null,null,"2023-04-07","2024-01-02"]
[810,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233999","RP-233039","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[811,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","2023-03-07","2024-06-06",0,"RP-233999","RP-233039","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[812,1010055,"Introduction of NR bands n31 and n72 ","NR_bands_n31_n72",1,"Rel-18","R4","2023-09-09","2023-12-12",0.99,"RP-233950",null,"Nokia ",null,"2/1/24: WID:RP-232691->RP-233950",null,101,51,null,null,"2023-10-06","2024-01-02"]
[813,1011055,"   Core part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Core",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[814,1012055,"   Perf. part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Perf",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[815,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991",null,"CATT",null,"6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991",null,99,50,null,null,"2023-04-07","2024-01-02"]
[816,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-233005","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[817,991246,"   Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102",null,99,50,102,null,"2023-04-07","2024-01-02"]
[818,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"2023-01-09","2023-03-29"]
[819,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[820,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[821,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"2022-12-13","2023-12-12",0.25,"RP-234044",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044",null,98,50,null,null,"2023-01-09","2024-01-02"]
[822,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated;...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[823,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eo...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[824,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.85,"RP-232920",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920",null,96,49,null,null,"2022-08-03","2024-01-02"]
[825,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-232920","RP-232922","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"2022-08-03","2023-12-08"]
[826,961210,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-232920","RP-232922","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[827,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.85,"RP-233231",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231",null,96,49,null,null,"2022-08-03","2024-01-02"]
[828,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-233231","RP-233232","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"2022-08-03","2023-12-08"]
[829,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-16","2024-03-01",0.85,"RP-233231","RP-233232","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"2022-08-03","2023-12-08"]
[830,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"2022-06-16","2023-12-12",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[831,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[832,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"2022-06-15","2024-03-01",0.96,"RP-233990",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990",null,96,49,null,null,"2022-08-03","2024-01-02"]
[833,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.92,"RP-233990","RP-233221","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"2022-08-03","2023-12-08"]
[834,961207,"   Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-233990","RP-233221","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,102,null,"2022-08-03","2024-01-02"]
[835,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.67,"RP-233696",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696",null,96,49,null,null,"2022-08-03","2024-01-02"]
[836,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.67,"RP-233696","RP-233694","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[837,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.67,"RP-233696","RP-233694","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[838,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"2022-06-15","2023-03-03",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"2022-08-03","2023-03-29"]
[839,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...",38.892000000000003,96,49,null,null,"2022-08-03","2023-03-17"]
[{"$f":"A840+1","v":840},960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"2022-08-03","2023-03-17"]
[841,960098,"Stopped - Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"2022-06-16","2023-12-12",1,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[842,960198,"   Stopped - Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#10...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[843,960298,"   Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[844,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",0.85,"RP-234040",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040",null,96,49,null,null,"2022-08-03","2024-01-02"]
[845,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.9,"RP-234040","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[846,960295,"   stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-234040","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[847,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.49,"RP-232772","RP-232771","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772",null,100,51,null,null,"2023-06-29","2024-01-02"]
[848,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"2022-06-15","2023-06-06",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"2022-08-03","2023-03-29"]
[849,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","2022-06-15","2023-06-06",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"2022-08-03","2023-06-07"]
[850,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","2022-06-15","2023-06-06",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"2022-08-03","2023-03-31"]
[851,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"2022-04-05","2023-01-09"]
[852,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"2022-04-05","2023-01-09"]
[853,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"2022-04-05","2023-01-09"]
[854,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","2023-03-03","2023-12-12",1,"RP-232783","RP-232784","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP...",null,99,50,null,null,"2023-03-29","2024-01-02"]
[855,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","2022-06-15","2023-03-03",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualco...",38.893000000000001,96,49,null,null,"2022-07-12","2023-03-31"]
[856,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.05,"RP-232361","RP-233768","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep...",null,100,51,null,null,"2023-06-29","2023-12-08"]
[857,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[858,1010053,"Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC",1,"Rel-18","R4","2023-09-09","2024-03-01",0.3,"RP-232941",null,"Oppo ",null,"2/1/24: WID:RP-232674->RP-232941",null,101,51,null,null,"2023-10-06","2024-01-02"]
[859,1011053,"   Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2023-09-09","2024-03-01",0.3,"RP-232941","RP-232940","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;",38.880000000000003,101,51,null,null,"2023-10-06","2024-01-04"]
[860,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"2022-09-12","2024-03-01",0.89,"RP-233977",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977",null,97,49,null,null,"2022-10-19","2024-01-02"]
[861,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","2022-09-12","2024-03-01",0.77,"RP-233977","RP-233224","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...",38.898000000000003,97,49,null,null,"2022-10-19","2023-12-08"]
[862,970288,"   Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-01",1,"RP-233977","RP-233224","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,102,null,"2022-10-19","2024-01-02"]
[863,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.15,"RP-231199","RP-233565","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[864,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",0.51,"RP-233180",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180",null,96,49,null,null,"2022-08-03","2024-01-02"]
[865,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.7,"RP-233180","RP-233178","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....",37.829000000000001,96,49,null,null,"2022-08-03","2023-12-08"]
[866,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-06-06",0.18,"RP-233180","RP-232856","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[867,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.05,"RP-231248","RP-233767","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[868,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"2022-12-13","2025-06-06",0.4,"RP-234046",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046",null,98,50,null,null,"2023-01-09","2024-01-02"]
[869,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234046","RP-232937","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[870,1020088,"   UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest",2,"Rel-19","R5","2023-12-12","2025-06-06",0,"RP-233771",null,"Huawei ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[871,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"2022-09-08","2024-03-01",0.93,"RP-234002",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002",null,97,49,null,null,"2022-09-23","2024-01-02"]
[872,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","2022-09-08","2024-03-01",0.85,"RP-234002","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",38.893999999999998,97,49,null,null,"2022-09-23","2023-12-08"]
[873,970284,"   Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","2022-09-08","2024-03-01",1,"RP-234002","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,102,null,"2022-09-23","2024-01-02"]
[874,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"2022-09-08","2024-06-06",0.71,"RP-234064",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064",null,97,49,null,null,"2022-09-23","2024-01-02"]
[875,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",1,"RP-234064","RP-233073","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...",38.869999999999997,97,49,null,null,"2022-09-23","2023-12-08"]
[876,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",0.5,"RP-234064","RP-233073","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[877,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"2022-06-15","2024-03-01",0.8,"RP-233197",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197",null,96,49,null,null,"2022-08-03","2024-01-02"]
[878,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-233197","RP-233195","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"2022-08-03","2023-12-08"]
[879,961209,"   Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-233197","RP-233195","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[880,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"2022-06-15","2024-03-03",0.43,"RP-233242",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242",null,96,49,null,null,"2022-08-03","2024-01-02"]
[881,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-233242","RP-233240","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"2022-08-03","2023-12-08"]
[882,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","2022-06-16","2024-03-03",0,"RP-233242","RP-233240","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"2022-08-03","2023-12-08"]
[883,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.7,"RP-233989",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989",null,96,49,null,null,"2022-08-03","2024-01-02"]
[884,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.7,"RP-233989","RP-233143","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[885,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.7,"RP-233989","RP-233143","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[886,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.8,"RP-233488",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488",null,96,49,null,null,"2022-08-03","2024-01-02"]
[887,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-233488","RP-233489","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"2022-08-03","2023-12-08"]
[888,961203,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-233488","RP-233489","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[889,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.93,"RP-233987",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987",null,96,49,null,null,"2022-08-03","2024-01-02"]
[890,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-233987","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"2022-08-03","2023-12-08"]
[891,961204,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-233987","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[892,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.75,"RP-233988",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988",null,96,49,null,null,"2022-08-03","2024-01-02"]
[893,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.7,"RP-233988","RP-233648","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[894,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-233988","RP-233648","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[895,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.85,"RP-232923",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923",null,96,49,null,null,"2022-08-03","2024-01-02"]
[896,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-232923","RP-232925","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[897,961206,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-232923","RP-232925","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[898,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",1,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"2022-08-03","2023-03-29"]
[899,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Comp...",37.878,96,49,null,null,"2022-08-03","2023-12-08"]
[900,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[901,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",1,"RP-233588",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588",null,96,49,null,null,"2022-08-03","2024-01-02"]
[902,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...",37.877000000000002,96,49,null,null,"2022-08-03","2023-12-08"]
[903,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"2022-08-03","2023-12-08"]
[{"$f":"A904+1","v":904},0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[905,1010054,"High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14",1,"Rel-18","R4","2023-09-09","2024-03-01",0.65,"RP-232946",null,"AT&T ",null,"2/1/24: WID:RP-232676->RP-232946",null,101,51,null,null,"2023-10-06","2024-01-02"]
[906,1011054,"   Core part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Core",2,"Rel-18","R4","2023-09-09","2024-03-01",0.5,"RP-232946","RP-232945","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;",36.770000000000003,101,51,null,null,"2023-10-06","2024-01-04"]
[907,1012054,"   Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Perf",2,"Rel-18","R4","2023-09-09","2024-03-01",0.8,"RP-232946","RP-232945","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[908,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-232892",null,"Ericsson ",null,"2/1/24: WID:RP-222824->RP-232892",null,98,50,null,null,"2023-01-09","2024-01-02"]
[909,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[910,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[911,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"2022-12-12","2023-06-06",0.55000000000000004,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"2023-01-09","2023-03-29"]
[912,981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","2022-12-12","2023-06-06",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"2023-01-09","2023-06-29"]
[913,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","2022-12-12","2023-06-06",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[914,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"2023-01-09","2023-03-29"]
[915,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[916,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"2022-06-15","2024-03-01",0.72,"RP-233927",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927",null,96,49,null,null,"2022-08-03","2024-01-02"]
[917,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",0.43,"RP-233927","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"2022-08-03","2023-12-08"]
[918,960299,"   Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-233927","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24:...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[919,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"2022-08-03","NA"]
[920,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"2022-08-03","2023-01-09"]
[921,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[922,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[923,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[924,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"2017-12-15","2017-12-15",0.34,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[925,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","2023-03-03","2023-09-08",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23:...",null,99,50,null,null,"2023-03-29","2023-09-21"]
[926,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","2023-03-03","2023-12-12",1,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100",37.911000000000001,99,50,null,null,"2023-03-29","2024-01-02"]
[927,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","2022-09-08","2023-09-08",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...",38.847999999999999,97,49,null,null,"2022-09-23","2023-10-06"]
[928,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-231468","RP-233234","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...",38.845999999999997,95,48,null,null,"2022-04-05","2023-12-08"]
[929,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233171","RP-233170","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"2022-04-05","2024-01-02"]
[930,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...",38.877000000000002,95,48,null,null,"2022-04-05","2023-06-07"]
[931,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","2022-03-03","2023-03-03",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...",38.872,95,48,null,null,"2022-04-05","2023-03-17"]
[932,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","2019-09-19","2022-06-22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"2019-10-08","2022-07-12"]
[933,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","2020-09-17","2023-03-03",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"2020-09-25","2023-03-17"]
[934,0,"Rel-18 Network automation","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[935,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",0.92,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"2022-12-09","2022-12-10"]
[936,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"2021-12-19","2022-12-10"]
[937,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","2022-03-10","2023-03-03",0.95,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95",33.738,95,48,null,null,"2022-03-10","2023-06-08"]
[938,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",0.65,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[939,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2023-06-08"]
[940,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",0.9,"CP-230119",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[941,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",0.9,"CP-230119",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[942,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","2022-12-15","2024-03-03",0.99,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"2022-06-03","2023-06-06"]
[943,0,"Rel-18 other Studies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[944,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","2019-12-06","2021-12-10",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"2019-12-06","2021-12-10"]
[945,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","2022-06-02","2023-09-09",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"2022-06-20","2023-06-30"]
[946,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[947,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","2023-06-30","2024-03-03",0.95,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30; 8/12/23: 30%->95","28.531; 28.533; 28.526 ",100,51,null,null,"2023-06-30","2023-12-08"]
[948,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","2023-05-01","2023-06-06",1,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ","; 8/12/23: 0%->100","32.240; 32.255; 32.256; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2023-12-08"]
[949,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","2023-06-08","2024-03-03",0.6,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;","28.552; 28.554; 28.622 ; 28.318; 28.879",100,51,null,null,"2023-06-08","2024-01-04"]
[950,980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","2022-12-12","2024-03-03",0.55000000000000004,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024",28.84,98,50,null,null,"2022-12-09","2023-12-08"]
[951,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",0.9,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"2022-12-09","2023-12-08"]
[952,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211441",null,"Cornily Jean-Michel, Huawei","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[953,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","2021-12-10","2022-12-09",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"2021-12-10","2023-09-07"]
[954,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"2022-06-02","2022-12-11"]
[955,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","2022-06-02","2024-03-03",0.99,"SP-231710",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;","28.552; 32.425; 28.554; 28.550 ; 28.558",96,49,null,null,"2022-06-02","2024-01-04"]
[956,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","2020-03-25","2023-12-12",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"2019-12-06","2023-06-08"]
[957,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","2022-03-10","2024-03-03",0.7,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"2022-03-10","2023-12-08"]
[958,890016,"Study on access control for management service ","FS_MNSAC",1,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"2020-09-11","2021-09-13"]
[959,930010,"Access control for management service ","MSAC",1,"Rel-18","S5","2021-09-10","2024-03-03",0.75,"SP-231711",null,"Clifton Fernandes, Nokia ","Clifton.fernandes@nokia.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP...",28.318999999999999,93,47,null,null,"2021-09-10","2024-01-03"]
[960,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","2021-09-10","2023-12-12",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[961,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","2020-09-16","2022-03-10",1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100",null,89,45,null,null,"2020-09-10","2023-12-08"]
[962,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","2021-03-18","2022-03-11",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"2021-03-18","2022-06-04"]
[963,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[964,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","2023-03-16","2024-03-03",0.55000000000000004,"SP-231443",null,"Zhang Kai, Huawei ","kai.zhangkai@huawei.com","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871",99,50,null,null,"2023-03-16","2024-01-04"]
[965,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100",28.864000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[966,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added;","28.541; 28.552; 28.554 ; 28.877",99,50,null,null,"2023-03-16","2024-01-04"]
[967,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100",28.907,94,48,null,null,"2021-12-13","2023-03-17"]
[{"$f":"A968+1","v":968},940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100",28.913,94,48,null,null,"2021-12-13","2023-06-08"]
[969,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","2021-12-13","2024-03-03",0.92,"SP-211442",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92",28.864999999999998,94,48,null,null,"2021-12-13","2023-12-08"]
[970,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","2021-12-13","2024-03-03",0.8,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80",28.908999999999999,94,48,null,null,"2021-12-13","2023-12-08"]
[971,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","2021-12-13","2023-12-12",1,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100",28.91,94,48,null,null,"2021-12-13","2023-12-08"]
[972,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100",28.911999999999999,94,48,null,null,"2021-12-13","2023-06-08"]
[973,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774",28.831,95,48,null,null,"2022-03-10","2023-06-30"]
[974,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",28.902999999999999,95,48,null,null,"2022-03-10","2023-06-08"]
[975,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","2022-03-10","2023-03-03",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->",28.832999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[976,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100","28.541; 28.552; 28.554 ",99,50,null,null,"2023-03-16","2023-12-08"]
[977,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added;","28.834; 28.869",95,48,null,null,"2022-03-10","2024-01-04"]
[978,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added;","28.835; 28.878",95,48,null,null,"2022-03-10","2024-01-04"]
[979,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","2023-06-08","2024-03-03",0.6,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30; 8/12/23: 30%->60","32.130; 28.541; 28.552 ",100,51,null,null,"2023-06-08","2023-12-08"]
[980,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773",28.837,95,48,null,null,"2022-03-10","2023-06-30"]
[981,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","2022-03-10","2024-03-03",0.65,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65",28.83,95,48,null,null,"2022-03-10","2023-12-08"]
[982,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"2022-06-02","2023-06-08"]
[983,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","2021-06-11","2023-12-12",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"2021-06-11","2023-12-08"]
[984,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","2023-03-16","2023-09-09",1,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 8/12/23: 0%->100","32.240; 32.290 ",99,50,null,null,"2023-03-16","2023-12-08"]
[985,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","2021-06-11","2023-09-09",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"2021-06-11","2023-09-07"]
[986,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","2023-09-06","2024-03-03",0.4,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","; 8/12/23: 0%->40","32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2023-12-08"]
[987,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","2022-09-12","2023-03-10",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"2022-09-11","2023-03-17"]
[988,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","2022-09-12","2024-03-03",0.8,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;","; 28.842; 28.873",97,49,null,null,"2022-09-11","2024-01-04"]
[989,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","2022-09-12","2023-12-12",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100",28.838999999999999,97,49,null,null,"2022-09-11","2023-09-07"]
[990,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",0.6,"SP-231151",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;; 8/12/23: 0%->60","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,51,null,null,"2023-09-06","2023-12-08"]
[991,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","2023-03-16","2024-03-03",0.8,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"2023-03-16","2023-12-08"]
[992,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30; 8/12/23: 30%->100","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"2023-03-16","2023-12-08"]
[993,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","2023-03-16","2024-03-03",0.65,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"2023-03-16","2023-12-08"]
[994,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[995,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","2021-06-11","2023-03-03",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...",33.875999999999998,92,47,null,null,"2021-06-11","2023-06-08"]
[996,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100",33.31,99,50,null,null,"2023-03-16","2023-09-07"]
[997,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","2022-12-09","2023-03-03",0.95,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95",33.500999999999998,98,50,null,null,"2022-12-09","2023-06-08"]
[998,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",0.85,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","NA"]
[999,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","2022-06-03","2023-12-12",0.8,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"2022-06-03","2023-06-06"]
[1000,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",0.9,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","2023-06-09"]
[1001,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","2022-06-03","2023-03-03",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"2022-06-03","2022-07-13"]
[1002,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","2023-06-07","2024-03-03",0.5,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,51,null,null,"2023-06-07","2023-06-30"]
[1003,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","2023-12-12","2023-12-12",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"2018-06-06","2021-09-13"]
[1004,0,"Rel-18 other aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1005,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"2021-03-12","2023-03-03",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[1006,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","2021-03-12","2023-09-09",0.2,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"2021-06-11","2023-03-31"]
[1007,1000001,"Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",1,"Rel-18","C4","2023-06-07","2023-12-12",0.5,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;",29.856999999999999,100,51,null,null,"2023-06-07","2023-06-30"]
[1008,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"2019-03-07","2019-03-07",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"2022-03-13","NA"]
[1009,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","2022-01-05","2023-03-16",1,null,null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"2023-06-08","2023-06-08"]
[1010,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1011,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1012,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"2019-03-07","2019-12-12",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1013,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[1014,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"2019-05-31","2020-06-26"]
[1015,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","2019-06-06","2021-03-12",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"2019-05-31","2021-03-19"]
[1016,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"2020-06-12","2022-06-10",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","NA"]
[1017,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","2022-03-12"]
[1018,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1019,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"2021-03-18","2022-06-20"]
[1020,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1021,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1022,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1023,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"2020-06-25","2022-06-04"]
[1024,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1025,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","2018-06-06","2019-06-12",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"2018-06-06","2019-09-13"]
[1026,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1027,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","2021-03-18","2022-06-10",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"2021-03-18","2022-06-04"]
[1028,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","2019-03-07","2021-06-11",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"2018-12-06","2021-09-13"]
[1029,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","2019-06-06","2020-03-12",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"2019-05-31","2022-03-22"]
[1030,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","2020-12-04","2021-12-10",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"2020-12-04","2022-03-12"]
[1031,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[{"$f":"A1032+1","v":1032},840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1033,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-06-28"]
[1034,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-09-13"]
[1035,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"2020-09-25","2022-06-04"]
[1036,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"2019-05-31","2020-06-25"]
[1037,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"2019-09-13","NA"]
[1038,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"2018-09-06","2019-09-13"]
[1039,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","2019-09-19","2019-12-12",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1040,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"2019-05-31","2020-12-05"]
[1041,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","2020-03-25","2021-09-08",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"2019-05-31","2021-12-10"]
[1042,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"2021-03-18","2021-06-11"]
[1043,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"2021-03-18","2022-06-20"]
[1044,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"2021-03-18","2022-03-12"]
[1045,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"2021-03-18","2022-06-20"]
[1046,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"2019-03-07","2024-06-06",0.79,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1047,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1048,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1049,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-09-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"2021-01-06","2022-09-23"]
[1050,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","2022-09-08","2024-06-06",0.27,"RP-222384","RP-233001","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[1051,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"2019-05-31","NA"]
[1052,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","2018-09-06","2019-09-13",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"2018-09-06","2019-12-06"]
[1053,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1054,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1055,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"2018-09-06","2019-12-13",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1056,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","2018-09-06","2019-12-13",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[1057,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"2019-05-31","2019-12-06"]
[1058,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","2018-12-06","2020-12-15",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"2018-12-06","2020-12-05"]
[1059,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","2018-12-06","2021-03-12",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"2018-12-06","2021-03-21"]
[1060,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"2020-12-04","2021-03-21"]
[1061,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","2020-12-04","2021-06-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"2020-12-04","2021-07-02"]
[1062,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1063,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1064,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100",33.853999999999999,88,45,null,null,"2020-06-25","2023-03-31"]
[1065,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"2018-09-06","2023-12-12",0.92,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"2018-09-06","NA"]
[1066,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","2018-09-06","2018-12-14",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"2018-09-06","2018-12-04"]
[1067,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"2020-12-03","2021-12-10"]
[1068,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1069,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1070,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"2021-03-18","2022-03-12"]
[1071,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1072,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","2021-06-11","2022-03-11",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"2021-06-11","2022-03-12"]
[1073,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","2023-03-03","2023-12-12",0.4,"RP-230716","RP-231997","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ",null,99,50,null,null,"2023-03-29","2023-09-06"]
[1074,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1075,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","NA"]
[1076,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","2018-06-06","2018-09-14",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1077,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","2018-06-06","2020-06-25",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"2018-06-06","2020-06-26"]
[1078,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","2019-12-06","2021-09-08",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","2021-12-10"]
[1079,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2021-06-11"]
[1080,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-06-04"]
[1081,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","2020-09-16","2021-09-10",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1082,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1083,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","2021-09-13","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"2020-09-12","2022-06-04"]
[1084,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"2019-12-16","2023-12-12",0.9,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"2020-01-14","2022-04-05"]
[1085,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","2019-12-16","2022-06-06",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"2020-01-14","2023-03-17"]
[1086,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","2019-12-16","2023-03-03",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1087,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",0.5,"RP-233929","RP-232016","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"2022-07-12","2024-01-02"]
[1088,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2021-06-15","2024-03-01",0.99,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"2021-07-02","NA"]
[1089,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","2021-06-15","2022-06-22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1090,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",0.99,"RP-233250","RP-233249","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"2022-07-12","2024-01-02"]
[1091,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1092,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"2022-03-12","2022-06-20"]
[1093,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1094,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1095,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-06-04"]
[{"$f":"A1096+1","v":1096},830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","2019-03-07","2021-03-12",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"2019-03-14","2021-03-21"]
[1097,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2019-12-16","2021-06-15",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"2020-01-14","2021-07-02"]
[1098,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1099,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"2019-09-13","2021-06-11"]
[1100,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","2020-06-12","2021-06-11",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"2020-06-25","2021-06-11"]
[1101,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","2021-06-11","2021-06-18",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-03-24"]
[1102,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"2020-12-03","NA"]
[1103,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"2020-12-03","2021-09-13"]
[1104,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1105,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1106,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1107,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1108,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1109,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1110,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","2021-12-21","2022-03-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1111,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","2019-03-07","2022-09-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1112,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"2019-12-16","2024-06-06",0.97,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1113,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1114,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","2019-12-16","2022-12-21",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1115,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.9,"RP-221238","RP-233874","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1116,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"2019-12-16","2023-12-12",1,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1117,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"2020-01-14","2022-12-09"]
[1118,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","2020-06-15","2022-12-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...;...",null,86,44,null,null,"2020-09-25","2022-12-09"]
[1119,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221416","RP-232885","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1120,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1121,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"2019-12-16","2024-03-01",0.76,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1122,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","2019-12-16","2022-03-11",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1123,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1124,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",0.05,"RP-221448","RP-233002","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1125,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","2019-12-16","2020-09-15",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1126,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","2019-06-06","2020-06-12",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"2019-05-31","2022-03-22"]
[1127,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-02-10"]
[1128,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-06-11"]
[1129,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1130,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1131,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1132,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"2021-03-18","NA"]
[1133,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"2019-09-13","2021-03-19"]
[1134,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","2021-03-18","2021-09-08",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"2021-03-18","2021-12-10"]
[1135,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1136,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"2021-06-11","2022-03-22"]
[1137,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"2021-06-11","2022-06-04"]
[1138,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1139,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","2021-06-15","2023-09-22",0.99,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1140,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"2021-07-02","2022-03-22"]
[1141,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"2021-07-02","2022-03-22"]
[1142,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","2021-12-13","2023-09-22",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[1143,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"2019-12-16","2024-06-06",0.91,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"2020-01-14","2021-09-29"]
[1144,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1145,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","2019-12-16","2022-12-01",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1146,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.67,"RP-221401","RP-233142","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1147,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1148,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1149,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"2019-12-16","2024-03-01",0.99,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1150,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1151,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1152,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-01",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"2020-07-28","2023-01-09"]
[1153,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",0.97,"RP-233247","RP-233246","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"2022-07-12","2024-01-02"]
[1154,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"2019-12-16","2024-03-01",0.99,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1155,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1156,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1157,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","2023-03-03","2024-03-01",0.94,"RP-233764","RP-233763","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ; 8/12/23: FCD:03/03/2024->01/03/2024; Compl:46%->94%; Stat Rep: RP-232355->RP-233763; ; 2/1/24: WID...",null,99,50,null,null,"2023-03-29","2024-01-02"]
[1158,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"2019-03-11","2022-09-22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1159,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[{"$f":"A1160+1","v":1160},860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1161,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","2019-03-11","2021-12-10",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"2019-03-14","2022-03-12"]
[1162,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"2019-12-16","2022-03-09",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"2020-01-14","2022-01-21"]
[1163,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-09",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1164,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"2020-09-15","2024-06-06",0.85,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126...",null,89,45,null,null,"2020-10-11","2022-07-12"]
[1165,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","2021-12-14","2022-06-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"2022-03-22","2022-06-20"]
[1166,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"2020-10-11","2022-09-09"]
[1167,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.65,"RP-233582","RP-233583","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"2022-07-12","2024-01-02"]
[1168,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"2020-09-15","2023-12-12",1,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1169,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1170,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Noki...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1171,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221240","RP-233873","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1172,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1173,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1174,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1175,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-06-06",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1176,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1177,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1178,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1179,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"2020-09-15","2024-03-01",0.95,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366...",38.850999999999999,89,45,null,null,"2020-10-11","2022-07-12"]
[1180,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1181,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1182,970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",0.81,"RP-221932","RP-232855","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[1183,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1184,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1185,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1186,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1187,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporati...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1188,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1189,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"2020-09-15","2024-06-06",0.82,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"2020-10-11","2022-04-05"]
[1190,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1191,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1192,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.5,"RP-221848","RP-233762","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1193,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","2021-12-13","2022-09-22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"2022-01-06","2022-04-05"]
[1194,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1195,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1196,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"2022-07-12","2022-09-23"]
[1197,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1198,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1199,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1200,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1201,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"2019-12-06","2022-06-21"]
[1202,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","2019-09-19","2020-09-14",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"2019-09-13","2020-09-13"]
[1203,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","2020-06-12","2021-12-10",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"2020-06-26","2021-12-13"]
[1204,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1205,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"2019-05-31","2021-06-11"]
[1206,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","2018-09-14","2020-03-12",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"2018-09-14","2020-12-05"]
[1207,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"2020-06-25","2022-03-12"]
[1208,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","2019-09-19","2020-03-12",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"2019-09-13","2020-03-26"]
[1209,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"2019-03-07","2024-03-03",0.97,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1210,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"2019-03-14","2021-03-19"]
[1211,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","2020-12-03","2021-09-10",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-06-04"]
[1212,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"2021-06-11","2022-06-04"]
[1213,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"2021-06-11","2022-06-20"]
[1214,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"2021-06-11","2022-06-20"]
[1215,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"2022-06-20","NA"]
[1216,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1217,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",0.65,"SP-231712",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30; 8/12/23: 30%->65; 3/1/24: WID:SP-230623->SP-231712","32.240; 32.255; 32.298; 32.291; 33.279; 33.290",100,51,null,null,"2023-06-08","2024-01-03"]
[1218,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","2019-09-02","2019-12-12",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1219,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1220,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","2019-12-16","2023-12-12",0.99,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1221,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1222,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",1,"RP-220423","RP-233760","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1223,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"2020-09-11","2021-03-21"]
[{"$f":"A1224+1","v":1224},890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"2020-09-11","2021-06-11"]
[1225,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1226,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"2019-12-06","2022-03-11",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1227,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"2019-12-06","2021-06-11"]
[1228,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","2020-06-17","2022-03-11",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"2020-09-25","2022-06-04"]
[1229,880020,"Protocol enhancements for Mission Critical Services ","MCProtoc17",1,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-202193",null,"AXELL, Jörgen ","jorgen.axell@ericsson.com ","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/12/21: 70%-> ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1230,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","2018-12-13","2022-03-11",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"2018-12-07","2022-06-04"]
[1231,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","2020-09-16","2021-09-08",0.65,null,null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"2020-09-25","2021-09-13"]
[1232,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1233,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"2019-03-07","2022-06-07",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"2019-12-06","2020-03-26"]
[1234,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","2019-03-07","2019-12-05",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-03-26"]
[1235,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"2019-12-06","2021-06-11"]
[1236,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"2020-12-05","2021-06-11"]
[1237,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","2020-12-07","2022-03-11",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"2020-12-05","2022-06-04"]
[1238,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","2020-12-07","2022-03-11",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1239,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"2022-06-20","2022-08-03"]
[1240,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-12-05"]
[1241,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1242,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1243,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"2021-03-18","2021-09-10"]
[1244,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"2021-03-18","2022-06-04"]
[1245,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"2021-03-18","2022-03-12"]
[1246,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"2021-03-18","2022-06-04"]
[1247,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","2021-06-11","2021-12-10",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"2021-06-11","2022-03-12"]
[1248,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","2021-06-11","2022-03-11",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1249,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"2020-06-25","2022-03-12"]
[1250,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"2021-12-10","2022-06-04"]
[1251,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"2021-09-10","2022-03-22"]
[1252,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","2020-06-25","2021-12-10",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"2020-06-26","2022-06-21"]
[1253,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"2021-09-10","2022-06-04"]
[1254,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","2020-03-25","2021-09-08",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"2019-12-06","2021-09-13"]
[1255,0,"Rel-17 Slicing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1256,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"2021-06-11","2022-04-28"]
[1257,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"2021-06-11","2022-06-20"]
[1258,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1259,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1260,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1261,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"2019-09-19","2023-06-06",0.99,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1262,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"2019-09-13","2021-03-19"]
[1263,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-22"]
[1264,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","2021-03-18","2023-06-06",0.99,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"2021-03-18","2021-10-01"]
[1265,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1266,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"2021-03-18","2022-06-04"]
[1267,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"2021-03-18","2022-03-12"]
[1268,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","2022-03-15","2023-06-06",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"2022-04-05","2023-06-07"]
[1269,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","2019-03-07","2023-09-22",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1270,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","2021-03-12","2022-06-22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1271,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","2022-06-15","2023-09-22",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1272,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","2022-06-03","2022-06-20",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-03","2022-06-04"]
[1273,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-20","2022-08-03"]
[1274,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","2019-12-06","2021-12-10",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"2019-12-06","2021-12-13"]
[1275,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","2022-03-10","2022-03-11",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"2022-03-10","2022-03-12"]
[1276,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1277,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","NA"]
[1278,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","2019-03-07","2019-09-06",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"2019-03-14","2019-12-06"]
[1279,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1280,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"2018-12-06","2021-09-13"]
[1281,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1282,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1283,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1284,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1285,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"2020-12-04","2021-09-13"]
[1286,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"2019-12-09","2023-09-22",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"2020-06-10","2022-01-06"]
[1287,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","2019-12-09","2022-03-22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"2020-06-10","2022-06-20"]
[{"$f":"A1288+1","v":1288},950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1289,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","2021-12-13","2024-06-06",0.52,"RP-233071",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1290,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1291,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","2022-03-15","2024-06-06",0.1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"2022-06-04","2023-12-08"]
[1292,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1293,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"2019-06-06","2021-12-10",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1294,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","2019-06-06","2020-12-11",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1295,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"2020-09-10","2022-03-12"]
[1296,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1297,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"2020-09-11","2021-06-11"]
[1298,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"2020-09-11","2021-12-13"]
[1299,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"2021-09-10","NA"]
[1300,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"2021-09-10","2022-06-04"]
[1301,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"2021-09-10","2022-03-12"]
[1302,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","2021-09-29","2024-03-03",0.56999999999999995,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"2021-09-29","NA"]
[1303,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"2021-09-29","2022-03-12"]
[1304,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"2021-09-29","2022-06-04"]
[1305,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","2023-06-08","2024-03-03",0.05,"RP-230873","RP-231826","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ",null,100,51,null,null,"2023-06-29","2023-09-06"]
[1306,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"2020-09-25","2021-06-11"]
[1307,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.866999999999997,89,45,null,null,"2020-09-25","2023-03-31"]
[1308,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.500999999999998,93,47,null,null,"2021-09-10","2023-03-31"]
[1309,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"2021-03-18","2021-12-13"]
[1310,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","2021-12-13","2024-03-01",0.79,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"2022-01-06","2023-03-29"]
[1311,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"2022-01-06","2022-06-04"]
[1312,970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",0.75,"RP-230070","RP-232760","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[1313,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1314,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","2021-06-12","2021-06-12",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"2021-08-12","2022-03-11"]
[1315,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"2021-03-18","2022-03-11",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2021-09-13"]
[1316,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1317,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"2021-12-10","2022-06-04"]
[1318,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"2021-12-10","2022-03-12"]
[1319,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1320,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->",33.534999999999997,92,47,null,null,"2021-06-11","2022-09-12"]
[1321,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[1322,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"2022-03-10","2022-06-04"]
[1323,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","2020-12-07","2020-12-18",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-05","2020-12-05"]
[1324,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1325,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"2019-03-07","2021-09-10",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1326,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","2019-05-09","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1327,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"2020-12-05","2021-03-21"]
[1328,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1329,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1330,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"2020-12-04","2021-12-13"]
[1331,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"2020-12-04","2021-03-21"]
[1332,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","2020-12-04","2021-06-15",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"2020-12-04","2021-09-13"]
[1333,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"2021-06-11","2022-06-04"]
[1334,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100",29.548999999999999,92,47,null,null,"2021-06-11","2022-06-04"]
[1335,940018,"   Security for eSEAL ","eSEAL",2,"Rel-17","S3","2021-12-10","2021-12-10",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100",33.433999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1336,900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"2019-03-07","2024-09-09",0.84,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1337,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"2019-06-26","2021-03-19"]
[1338,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","2020-12-03","2021-06-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"2020-12-03","2021-09-13"]
[1339,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1340,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"2021-03-18","2022-06-04"]
[1341,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"2021-03-18","2021-12-13"]
[1342,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"2021-03-18","2022-03-12"]
[1343,1010050,"   UE Conformance - ATSSS_Ph2","ATSSS_Ph2-UEConTest",2,"Rel-17","R5","2023-09-09","2024-09-09",0,"RP-231827",null,"China Telecom ",null,null,null,101,51,null,null,"2023-10-06","NA"]
[1344,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"2020-12-03","NA"]
[1345,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","2019-06-06","2020-12-15",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"2019-05-31","2021-03-19"]
[1346,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","2020-09-16","2022-03-11",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22",33.866,89,45,null,null,"2020-09-10","2022-03-12"]
[1347,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1348,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"2021-03-19","2021-06-11"]
[1349,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"2021-03-19","2022-06-04"]
[1350,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1351,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[{"$f":"A1352+1","v":1352},900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"2019-03-07","2022-06-10",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"2020-12-03","NA"]
[1353,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"2019-03-14","2021-12-10"]
[1354,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-12"]
[1355,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"2021-03-18","2022-07-13"]
[1356,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1357,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100",29.556999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1358,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90",29.559000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1359,920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"2021-03-18","2022-06-04"]
[1360,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"2020-09-10","2022-06-21"]
[1361,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1362,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ",33.847000000000001,88,45,null,null,"2020-06-25","2022-06-04"]
[1363,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"2021-09-10","2023-03-31"]
[1364,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1365,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","2021-03-12","2022-03-22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, h...",38.350999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1366,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1367,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"2019-09-13","2020-06-26"]
[1368,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","2019-09-19","2020-06-12",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"2019-09-13","2022-03-12"]
[1369,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"2020-09-11","2020-09-25"]
[1370,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100",24.501000000000001,89,45,null,null,"2020-09-11","2022-03-12"]
[1371,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"2020-09-11","2022-03-12"]
[1372,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"2020-09-11","2022-03-12"]
[1373,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","2020-09-17","2024-06-06",0.74,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1374,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","2020-09-17","2022-03-11",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1375,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-06-06",0.54,"RP-221300","RP-233564","Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm","gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222942; Rapporteur: ChinaTelecom->Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm; Rap eMail: ->gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com; 17/3/23: FCD:30/11/202.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1376,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"2017-12-15","2022-03-11",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"2019-05-31","NA"]
[1377,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","2017-12-15","2019-09-12",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"2017-12-15","2020-08-17"]
[1378,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","2019-09-19","2020-06-12",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,96,null,"2019-09-13","2022-03-22"]
[1379,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1380,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","2020-03-25","2021-06-11",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"2020-03-25","2022-03-12"]
[1381,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"2020-06-26","NA"]
[1382,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1383,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1384,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1385,890011,"Mission critical security enhancements phase 2 ","MCXSec2",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200879",null,"Woodward, Tim, Motorola Solutions, Inc, ","tim.woodward@motorolasolutions.com ","; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 80%->82; 13/12/21: 82%->100",33.18,89,45,null,null,"2020-09-11","2021-12-13"]
[1386,890070,"PAP/CHAP protocols usage in 5GS ","PAP_CHAP",1,"Rel-17","ct","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 29.561 ; 12/3/22: 99%->100",null,89,45,null,null,"2020-09-25","2022-03-12"]
[1387,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1388,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","2020-09-16","2021-03-12",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1389,890001,"Service-based support for SMS in 5GC ","SMS_SBI",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","25/9/20: WID:CP-202028->CP-202242; 10/9/21: WID:CP-202242->CP-212023",null,89,45,null,null,"2020-09-11","2021-09-10"]
[1390,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"2020-09-11","2022-03-12"]
[1391,890029,"   CT4 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35; 13/9/21: FCD:Wed 08/09/->03/22; 13/9/21: 35%->40; 1/10/21: 23.540 added;; 13/12/21: 40%->45; 12/3/22: 45%->65; 22/3/22: 29.577 added;; 22/3/22: 29.579 added;; 22/3/22:...","29.503; 29.540; 29.571; 23.540; 29.577; 29.579; 29.578",89,45,null,null,"2020-09-11","2022-08-03"]
[1392,840048,"Enhanced Relays for Energy eFficiency and Extensive Coverage ","REFEC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1393,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100",22.866,81,41,null,null,"2018-09-06","2019-12-06"]
[1394,840034,"   Stage 1 of REFEC","REFEC",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ","13/9/19: 0%->90; 6/12/19: 90%->100",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-06"]
[1395,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1396,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","2018-06-06","2019-03-14",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100",22.841999999999999,80,41,null,null,"2018-06-06","2019-05-31"]
[1397,840030,"   Stage 1 of NCIS","NCIS",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191039",null,"Ning YANG, oppo ","yangning@oppo.com ","13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1398,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","2019-06-06","2021-06-11",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"2019-05-31","2021-06-11"]
[1399,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","2020-09-16","2021-06-11",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"2020-09-10","2021-06-11"]
[1400,880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"2019-09-02","2020-12-11",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1401,850041,"   Stage 1 of MuDE","MuDE",2,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1402,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","2020-06-25","2020-12-11",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"2020-06-26","2021-06-11"]
[1403,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"2020-06-26","2021-09-10"]
[1404,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1405,880014,"   CT4 aspects of BEPoP","BEPoP",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 45%->55; 13/12/21: 55%->80; 12/3/22: 80%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1406,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","2020-06-25","2021-09-10",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"2020-06-25","2021-12-13"]
[1407,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100",23.18,84,43,null,null,"2019-05-31","2020-12-05"]
[1408,840016,"Stopped - Supporting Flexible Local Area Data Network ","FLADN",1,"Rel-17","S2","2019-06-06","2020-09-11",1,"SP-190563",null,"LG Electronics, Hyunsook Kim ","hyuns.kim@lge.com ","21/1/22: stopped at 0%; 21/1/22: 0%->100","23.501; 23.502 ",84,43,95,null,"2019-05-31","2022-01-21"]
[1409,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","2018-12-13","2022-03-11",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"2019-03-14","2022-03-12"]
[1410,860012,"Handsets Featuring Non-Traditional Earpieces","HaNTE",1,"Rel-17","S4","2019-12-06","2022-03-11",1,"SP-190989",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com","25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11 ","26.131; 26.132; 26.801",86,44,null,null,"2019-12-06","2022-03-12"]
[1411,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-03-12"]
[1412,920008,"   Stage 2 of EVEX","EVEX",2,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-06-04"]
[1413,960021,"   Stage 3 (CT3) of EVEX","EVEX",2,"Rel-17","C3","2022-06-01","2022-06-10",1,"CP-222128",null,"Waqar Zia, Qualcomm Incorporated","wzia@qti.qualcomm.com",null,"29.522; 29.517; 29.591",96,49,null,null,"2022-05-30","NA"]
[1414,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","2021-06-11","2021-09-08",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"2021-06-11","2021-12-13"]
[1415,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"2021-06-11","2022-03-12"]
[{"$f":"A1416+1","v":1416},920011,"8K Television over 5G ","8K_TV_5G",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210381",null,"Thomas Stockhammer ","tsto@qti.qualcomm.com ","; 13/9/21: 0%->40; 13/12/21: 40%->60; 12/3/22: 60%->100","26.955;26.925;26.511;26.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1417,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","2019-03-07","2019-03-21",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"2017-12-15","2019-03-14"]
[1418,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1419,880049,"Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON",1,"Rel-17",null,"2019-09-02","2023-03-03",1,"CP-210148",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148",22.260999999999999,85,43,null,null,"2019-09-13","2021-06-13"]
[1420,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","2019-09-02","2021-06-18",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100",22.260999999999999,85,43,null,null,"2019-09-13","2022-03-11"]
[1421,880022,"   Stage 3 (CT1) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50; 13/9/21: 50%->70; 13/9/21: FCD:Fri 18/06/->03/22; 13/12/21: 70%->92; 12/3/22: 92%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1422,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"2020-06-26","2022-03-12"]
[1423,920061,"   Stage 3 (CT6) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C6","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/9/21: 0%->70; 13/9/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100; 4/6/22: 100 ",null,92,47,null,null,"2020-06-26","2022-06-04"]
[1424,970073,"   UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON-UEConTest",2,"Rel-17","R5","2022-09-08","2023-03-03",1,"RP-222255","RP-230359","Masahiro Takano, NTT DOCOMO, INC","masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->80%; Stat Rep: ->RP-223159; Rapporteur: NTT DOCOMO->Masahiro Takano, NTT DOCOMO, INC; Rap eMail: ->masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com; 17/3/23: FCD:09/09/2023->03/03/2023; Compl:80%->100%; ...",null,97,49,null,null,"2022-09-23","2023-03-17"]
[1425,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2020-12-05"]
[1426,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","2019-09-19","2021-12-10",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2021-12-13"]
[1427,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1428,910047,"   Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",2,"Rel-17","S3","2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 24/3/22: 0%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2021-03-19","2022-03-24"]
[1429,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"2019-09-13","NA"]
[1430,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[1431,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","2019-09-13","2019-12-12",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"2019-09-13","2019-12-06"]
[1432,920062,"   Stage 2 of MINT","MINT",2,"Rel-17","S2","2021-08-12","2021-12-10",1,"SP-210582",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","13/9/21: 0%->50; 10/12/21: 50%->90; 12/3/22: 90%->98; 4/6/22: 98%->100","23.501; 23.502 ",92,47,null,null,"2021-08-12","2022-06-04"]
[1433,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","2020-12-07","2021-03-12",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"2020-12-05","2021-09-13"]
[1434,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","NA"]
[1435,930049,"      CT1 aspects of MINT","MINT",3,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 13/12/21: 0%->50; 12/3/22: 50%->85; 4/6/22: 85%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1436,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-20"]
[1437,930048,"      CT6 aspects of MINT","MINT",3,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->100; 4/6/22: 100%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1438,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","2022-03-10","2022-03-11",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100",33.500999999999998,95,48,null,null,"2022-03-10","2022-03-22"]
[1439,860008,"IMS emergency support for Stand-alone Non-Public Network (SNPN)","IESNPN",1,"Rel-17","S1","2019-12-06","2019-12-13",1,"SP-191038",null,"Wong, Curt; ","curt.wong@charter.com ","6/12/19: 0%->100","22.101; 22.261; 22.228 ",86,44,null,null,"2019-12-06","2019-12-06"]
[1440,870023,"Management of non-public networks (NPN)","OAM_NPN",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200189",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21; 13/9/21: 50%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->100","28.541; 28.531; 28.533; 28.552; 28.554 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1441,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","2019-12-06","2021-06-11",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"2019-12-06","2021-12-13"]
[1442,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"2020-03-25","2020-06-26"]
[1443,890013,"   eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) ","SCAS_5G_NSSAAF",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200720",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->100","33.926; 33.326",89,45,null,null,"2020-09-11","2021-09-13"]
[1444,870017,"   eSCAS_5G for Non-3GPP InterWorking Function","SCAS_5G_N3IWF",2,"Rel-17","S3","2020-03-25","2021-12-10",1,"SP-200146",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->100","33.926; 33.520",87,44,null,null,"2020-03-25","2021-12-13"]
[1445,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"2020-03-25","2022-06-04"]
[1446,870019,"   eSCAS_5G for Service Communication Proxy","SCAS_5G_SECOP",2,"Rel-17","S3","2020-03-25","2022-06-09",1,"SP-200148",null,"Wei Lu, Nokia","wei.lu@nokia-sbell.com","26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 70%->95; 12/3/22: 95%->95; 12/3/22: FCD:10/12/2021->06/22; 31/3/23: 95%->100","33.522; 33.926",87,44,null,null,"2020-03-25","2023-03-31"]
[1447,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"2020-06-25","2021-09-13"]
[1448,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2020-06-28"]
[1449,870016,"   Stage 2 aspects of enh3MCPTT","enh3MCPTT",2,"Rel-17","S6","2020-03-25","2021-06-15",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-06-11"]
[1450,900039,"   Stage 3 aspects of enh3MCPTT","enh3MCPTT-CT",2,"Rel-17","C1","2020-09-14","2021-09-08",1,"CP-202188",null,null,null,"; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48; 13/12/21: 48%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1451,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","2019-06-06","2021-12-10",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"2019-05-31","2022-03-12"]
[1452,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","2018-12-13","2021-03-12",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"2018-12-06","2021-06-11"]
[1453,890012,"Enhancements to User Plane Integrity Protection Support in 5GS ","eUPIP_SEC",1,"Rel-17","S3","2020-09-16","2021-03-12",1,"SP-200719",null,"Anand Palanigounder, Qualcomm Incorporated ","apg@qti.qualcomm.com ","; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100",33.500999999999998,89,45,null,null,"2020-09-11","2021-03-19"]
[1454,950040,"Non-Seamless WLAN offload in 5GS ","NSWO_5G",1,"Rel-17","S3","2021-05-25","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ",null,33.500999999999998,95,48,null,null,"2021-12-10","NA"]
[1455,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","2021-05-25","2021-09-08",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"2021-05-25","2022-06-04"]
[1456,940011,"   Security aspects of NSWO","NSWO_5G",2,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ","; 12/3/22: FCD:12/12/2021->3/22; 12/3/22: 0%->100",33.500999999999998,94,48,null,null,"2021-12-10","2022-03-12"]
[1457,950041,"   CT1 aspects of NSWO","NSWO_5G",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 22/3/22: 0%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-03-22"]
[1458,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1459,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1460,990122,"Lawful Interception Rel-17 ","LI17",1,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1461,860025,"   Lawful Interception Rel-17 general aspects","LI17",2,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1462,990120,"   (IETF) PASSporT Extension for Rich Call Data (draft-ietf-stir-passport-rcd)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1463,990121,"   (IETF) Messaging Use Cases and Extensions for STIR (draft-ietf-stir-messaging)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1464,850047,"(Small) Technical Enhancements and Improvements for Rel-17","TEI17",1,"Rel-17",null,"2020-03-11","2022-03-11",1,null,null,null,null,null,null,85,43,null,null,"2015-06-15","2015-06-15"]
[1465,940047,"   IMS Optimization for HSS Group ID in an SBA environment (St. 2)","TEI17_IMSGID",2,"Rel-17","S2","2020-03-11","2022-03-11",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1466,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1467,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","2020-03-11","2022-03-11",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100",24.228999999999999,94,48,null,null,"2021-12-10","2022-03-12"]
[1468,910044,"   Same PCF Selection For AMF and SMF ","TEI17_SPSFAS",2,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ",null,null,88,45,null,null,"2020-06-25","NA"]
[1469,880016,"      Stage 2 for TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ","23.501, 23.502 ; 19/3/21: 0%->100",null,88,45,null,null,"2020-06-25","2021-03-19"]
[1470,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1471,910045,"         CT3 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C3","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184; 13/9/21: 98%->100",29.513000000000002,91,46,null,null,"2021-03-18","2021-09-13"]
[1472,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"2021-03-18","2021-09-13"]
[1473,930036,"   System enhancement for Redundant PDU Session ","TEI17_SE_RPS",2,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1474,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1475,930001,"      CT aspects of TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ",null,"24.501; 24.526; 27.007; 29.513; 29.525; 29.561; 29.502 ",93,47,null,null,"2021-09-10","NA"]
[1476,930037,"         CT1 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","24.501; 24.526; 27.007",93,47,null,null,"2021-09-10","2021-12-13"]
[1477,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"2021-09-10","2022-03-12"]
[1478,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100",29.501999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[1479,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"2020-03-25","2021-09-10",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[{"$f":"A1480+1","v":1480},870004,"      Stage 2 for TEI17_SAPES","TEI17_SAPES",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ","19/3/21: 0%->100","23.228; 23.167",87,44,null,null,"2020-06-10","2021-03-19"]
[1481,910020,"      CT aspects on TEI17_SAPES","TEI17_SAPES",3,"Rel-17","ct","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ",null,"24.229; 29.165 ",91,46,null,null,"2021-03-19","NA"]
[1482,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1483,910080,"         CT3 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1484,910081,"   Dynamically Changing AM Policies in the 5GC ","TEI17_DCAMP",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,null,null,87,44,null,null,"2020-06-10","NA"]
[1485,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"2020-06-10","2021-03-19"]
[1486,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1487,910082,"         CT3 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: 0%->30; 13/9/21: 30%->50; 13/12/21: 50%->75; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1488,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1489,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"2020-06-10","2021-03-19"]
[1490,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"2020-06-10","NA"]
[1491,870007,"      Stage 2 for TEI17_GEM ","TEI17_GEM",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com","11/6/21: 0%->100",23.681999999999999,87,44,null,null,"2020-06-10","2021-06-11"]
[1492,910010,"      CT aspects on TEI17_GEM ","TEI17_GEM",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: WID:CP-210185->CP-211195; 10/9/21: WID:CP-211195->CP-212165","29.122 29.336 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1493,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1494,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1495,920041,"   Support of different slices over different Non 3GPP access ","TEI17_N3SLICE",2,"Rel-17",null,"2020-03-11","2021-06-18",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1496,870008,"      Stage 2 for TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1497,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-10-01"]
[1498,920001,"      CT4 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C4","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-06-11"]
[1499,910087,"   N7/N40 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",2,"Rel-17",null,"2020-03-11","2021-09-10",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1500,870009,"      Stage 2 for TEI17_NIESGU","TEI17_NIESGU",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ","11/6/21: 0%->100","23.060; 23.401; 23.503; 23.203 ",87,44,null,null,"2020-06-10","2021-06-11"]
[1501,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1502,910011,"      CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194; 13/9/21: 90%->100","29.512; 29.513 ",91,46,null,null,"2021-03-19","2021-09-13"]
[1503,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"2021-03-19","2021-09-13"]
[1504,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","2021-12-10","2022-03-22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"2022-04-21","NA"]
[1505,880019,"Stage-3 5GS NAS protocol development 17 ","5GProtoc17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","NA"]
[1506,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1507,880045,"   Stage-3 5GS NAS protocol development 17 non-IETF aspects","5GProtoc17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","1/10/21: 0%->70; 23/9/22: 70%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","2022-09-23"]
[1508,880021,"Stage-3 SAE Protocol Development ","SAES17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1509,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1510,880047,"   Stage-3 SAE Protocol Development CSFB aspects","SAES17-CSFB",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1511,880048,"   Stage-3 SAE Protocol Development non 3GPP aspects","SAES17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1512,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","2020-06-25","2024-09-09",0.75,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"2020-06-26","2021-03-21"]
[1513,880023,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 20%->40; 13/9/21: 40%->60; 13/12/21: 60%->80; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 80%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1514,911035,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 0%->60; 13/9/21: 60%->70; 13/12/21: 70%->85; 12/3/22: 85%->100; 12/3/22: FCD:10/09/2021->3/22","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1515,1000055,"   UE Conformance - IMS Data Channel ","IMSProtoc17_dataCH-UEContest",2,"Rel-17","R5","2023-06-07","2024-09-09",0.06,"RP-232357","RP-233765","Zhaobing Yang, Huawei Technologies. Co., Ltd","yangzhaobing@hisilicon.com","6/9/23: FCD:12/12/2023->22/09/2023; Compl:0%->5%; Stat Rep: ->RP-232356; Rapporteur: HiSilicon->Zhaobing Yang, Huawei Technologies. Co., Ltd; Rap eMail: ->yangzhaobing@hisilicon.com; ; 6/10/23: WID:RP-231246->RP-232357; 8/12/23: FCD:22/09/2023->09/09/2...",null,100,51,null,null,"2023-06-29","2023-12-08"]
[1516,880032,"Packet Flow Description (PFD) management enhancement ","pfdManEnh",1,"Rel-17","C3","2020-06-25","2021-06-11",1,"CP-210183",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100","29.251; 29.551 ",88,45,null,null,"2020-06-26","2021-06-11"]
[1517,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1518,880053,"   CT3 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088; 13/9/21: 65%->75; 13/12/21: 75%->85; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 85%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1519,880054,"   CT4 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50; 13/9/21: 50%->60; 13/12/21: 60%->80; 13/12/21: FCD:Mon 20/09/->03/22; 12/3/22: 80%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1520,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1521,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1522,970052,"   CT3 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C3","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1523,970053,"   CT4 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1524,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","2021-12-10","2022-06-10",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1525,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1526,820009,"Study on authentication enhancements in 5GS","FS_AUTH_ENH",1,"Rel-17","S3","2018-12-13","2021-12-10",1,"SP-190713",null,"Tsiatsis, Vlasios, ","vlasios.tsiatsis@ericsson.com ","07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202 ","new",82,42,null,null,"2018-12-06","2022-03-12"]
[1527,940012,"Authentication enhancements in 5GS ","AUTH_ENH",1,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211360",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 24/3/22: 0%->100",33.101999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1528,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"2022-03-10","2022-03-12"]
[1529,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"2022-03-10","2022-06-20"]
[1530,990004,"Update of conformance test specifications to Rel-17","UEConTest_R17",1,"Rel-17","C6","2021-06-14","2024-06-14",0.25,"CP-230022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com","Tests eV2XARC_Ph2;eCPSOR_CON;5G_ProSe;5GSAT_ARCH-CT;ING_5GS;MINT;NSWO_5G;ARCH_NR_REDCAP;IoT_SAT_ARCH_EPS","31.121; 31.124",92,47,null,null,"2021-08-12","NA"]
[1531,0,"Rel-17 Management-only Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1532,900021,"Management Aspects of 5G Network Sharing ","MANS",1,"Rel-17","S5","2020-12-04","2022-03-11",1,"SP-201080",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25; 13/9/21: 25%->30; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 30%->60; 12/3/22: 60%->100",null,90,46,null,null,"2020-12-04","2022-03-12"]
[1533,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","2021-06-11","2021-12-10",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"2021-06-11","2021-12-13"]
[1534,910030,"File Management ","FIMA",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210135",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 11/6/21: 0%->25; 13/9/21: 25%->60; 13/12/21: 60%->75; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 75%->100","28.537; 28.622; 28.623; 28.532 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1535,930032,"Improved support for NSA in the service-based management architecture ","NSA_SBMA",1,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-211121",null,"Lan Zou, Huawei ","zoulan@huawei.com ",null,"28.623; 28.622; 28.659; 28.663 ",91,46,null,null,"2021-09-10","NA"]
[1536,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1537,880029,"Enhancement of Handover Optimization ","E_HOO",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200466",null,"Elmdahl, Per, Ericsson ","per dot Elmdahl at Ericsson dot com ","28.552; 28.313; 28.541 ; 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:18/06/2021->03/22; 11/6/21: 10%->30; 13/9/21: 30%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1538,880028,"Management data collection control and discovery ","MADCOL",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200465",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30; 13/9/21: 30%->35; 13/9/21: FCD:Wed 22/09/->03/22; 13/12/21: 35%->40; 12/3/22: 40%->45; 4/6/22: 45%->100",null,88,45,null,null,"2020-06-26","2022-06-04"]
[1539,880026,"Management of the enhanced tenant concept ","eMEMTANE",1,"Rel-17","S5","2020-06-26","2021-12-15",1,"SP-220293",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->20; 12/3/22: 20%->100; 22/3/22: WID:SP-200463->SP-220293",null,88,45,null,null,"2020-06-26","2022-03-22"]
[1540,880025,"Enhancements of 5G performance measurements and KPIs ","ePM_KPI_5G",1,"Rel-17","S5","2020-06-12","2022-03-11",1,"SP-200462",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","28.552; 32.425; 28.554; 32.426; 32.450; 32.451; 32.455 ; 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->40; 11/6/21: 40%->50; 13/9/21: 50%->60; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1541,810027,"Intent driven management service for mobile network","IDMS_MN",1,"Rel-17","S5","2018-09-06","2022-03-11",1,"SP-180899",null,"Zou Lan, Huawei ","zoulan@huawei.com","7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[1542,820035,"Discovery of management services in 5G ","5GDMS",1,"Rel-17","S5","2018-12-13","2022-03-11",1,"SP-200770",null,"Brendan Hassett, Huawei Technologies Sweden AB ","brendan.t.hassett@huawei.com","¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ","28.533; 28.532; 28.531 ",82,42,null,null,"2018-12-07","2022-03-12"]
[1543,860024,"Network policy managementfor 5G mobile networks ","NPM",1,"Rel-17","S5","2019-12-06","2022-03-11",1,"SP-191211",null,"China Mobile Shasha Guo ","guoshasha@chinamobile.com ","; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75; 13/9/21: 75%->78; 13/12/21: 78%->100","28.532; 28.541 ",86,44,null,null,"2019-12-06","2021-12-13"]
[{"$f":"A1544+1","v":1544},850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","2019-09-19","2021-03-12",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"2019-09-13","2021-03-21"]
[1545,940078,"Enhancements of Management Data Analytics Service ","eMDAS",1,"Rel-17","S5","2021-03-18","2021-12-10",1,"SP-210132",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 13/9/21: 0%->10; 13/9/21: FCD:Fri 10/12/->12/21; 13/12/21: 10%->45. UID was at 0, corrected; 12/3/22: 45%->65; 4/6/22: 65%->100","28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533; 28.105",91,46,null,null,"2021-03-18","2022-06-04"]
[1546,870022,"Enhancements on EE for 5G networks ","EE5GPLUS",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200188",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->55; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->70; 13/12/21: 70%->100","28.310; 28.552; 28.554; 28.541 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1547,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"2019-12-06","2021-12-13"]
[1548,870024,"Enhancement on Management Aspects of 5G Service-Level Agreement ","EMA5SLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-210860",null,"SHI, Xiaonan, CMCC ","shixiaonan@chinamobile.com ","; 13/9/20: 0%->5; 5/12/20: 5%->40; 21/3/21: 40%->60; 21/3/21: FCD:18/03/2021->06/21; 11/6/21: 60%->65; 11/6/21: FCD:Fri 11/06/->12/21; 10/9/21: WID:SP-200190->SP-210860; 13/9/21: 65%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85 ","28.541; 28.531 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1549,870025,"Management of MDT enhancement in 5G ","e_5GMDT",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200191",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75; 13/9/21: 75%->85; 13/12/21: 85%->95; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 95%->100","32.421; 32.422; 32.423; 28.622; 28.623; 28.523 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1550,870026,"Additional NRM features ","adNRM",1,"Rel-17","S5","2020-02-05","2022-03-11",1,"SP-200192",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com","; 10/6/20: FCD:19/03/2020->06/20; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->30; 13/9/21: 30%->50; 13/9/21: FCD:Tue 15/06/->12/21; 13/12/21: 50%->80; 13/12/21: FCD:Fri 10/12/->03/22; 01/22: rapporteur change from Jing Ping; 12/3/22: 80%->100","28.540; 28.541; 28.622; 28.623 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1551,870030,"Enhanced Closed loop SLS Assurance ","eCOSLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200196",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 50%->60; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->90; 4/6/22: 90%->100; 4/1/24: 28.867...","28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 ; 28.867",87,44,null,null,"2019-12-06","2024-01-04"]
[1552,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","2022-03-10","2022-06-10",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1553,0,"Rel-17 Other NR-only improvements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1554,860061,"Study on NR QoE (Quality of Experience) management and optimizations for diverse services","FS_NR_QoE",1,"Rel-17","R3","2019-12-16","2020-09-15",1,"RP-193256",null,"China Unicom",null,"affects: NR.; 25/9/20: 38.890 added;; 7/4/21: 0%->100",38.89,86,44,null,null,"2020-01-14","2021-04-07"]
[1555,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"2021-01-01","2024-09-09",0.5,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"2021-06-04","2021-07-02"]
[1556,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","2021-01-01","2022-03-22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1557,970072,"   UE Conformance - NR QoE management and optimizations for diverse services ","NR_QoE-UEConTest",2,"Rel-17","R5","2022-09-08","2024-09-09",0.2,"RP-222102","RP-232955","Bo J NSSON, Ericsson","Bo[dot]jonsson[at]ericsson[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->5%; Stat Rep: ->RP-222818; Rapporteur: Ericsson->Bo J NSSON, Ericsson; Rap eMail: ->Bo[dot]jonsson[at]ericsson[dot]com; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-222818->RP-230267; ;...; 6/9/23: C...",null,97,49,null,null,"2022-09-23","2023-12-08"]
[1558,911009,"Rel-17 Power Class 2 UE for NR inter-band CA with or without SUL configurations with x (16>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL",1,"Rel-17",null,"2021-03-12","2025-06-06",0.6,"RP-221516",null,"Huawei ",null,"basket WI; TR 38.8xx ; 2/7/21: WID:RP-210543->RP-211378; 29/9/21: WID:RP-211378->RP-212182; 6/1/22: WID:RP-212182->RP-213650; 5/4/22: WID:RP-213650->RP-220701; 12/7/22: WID:RP-220701->RP-221516",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1559,911109,"   Core part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","basket WI; TR 38.8xx ; 2/7/21: 38.842 added;; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->78% ; 20/6/22: Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.com; ","38.842; 38.541",91,46,null,null,"2021-04-07","2022-06-20"]
[1560,911209,"   Stopped - Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: Stat Rep: RP-212181->RP-220699 ; 6/6/22: CD:12/06/2022->22/06/2022 ; 20/6/22:Stopped at 0%; Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.c...",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1561,1000056,"   UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-UEConTest",2,"Rel-17","R5","2023-06-08","2025-06-06",0.09,"RP-231247","RP-233766","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->9%; Stat Rep: ->RP-232358; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232358->RP-233766; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[1562,911010,"Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS",1,"Rel-17",null,"2021-03-12","2023-12-12",1,"RP-212030",null,"Vivo ",null,"compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: WID:RP-210807->RP-211158; 29/9/21: WID:RP-211158->RP-212030; 1/10/21: 38.161 added;; ",38.161000000000001,91,46,null,null,"2021-04-07","2022-06-04"]
[1563,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","2021-03-12","2022-03-22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ",38.834000000000003,91,46,null,null,"2021-04-07","2022-06-20"]
[1564,911210,"   Perf. part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-222269","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy ; 22/3/22: Compl:0%->20%; 22/3/22: CD:08/09/2022->12/09/2022 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com s...;...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[1565,960088,"   UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221690","RP-233311","Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo","ashwin_mohan[at]apple.com, Jose.Fortes[at]rohde-schwarz.com,ruixin.wang[at]vivo.com","9/9/22: Comp...; 23/9/22: 38.561 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->9%; Stat Rep: ->RP-223197; Rapporteur: Apple->Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo; Rap eMail: ->ashwin_mohan[at]apple...",38.561,96,49,null,null,"2022-07-12","2023-12-08"]
[1566,911012,"High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79",1,"Rel-17",null,"2021-03-12","2022-12-01",1,"RP-210843",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1567,911112,"   Core part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1568,911212,"   Perf. part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1569,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-211979","RP-223061","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...; 9/12/22: FCD:23/03/2023->01/12/2022; Compl:84%->100%; Stat R...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1570,911013,"High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-210844",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1571,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1572,911213,"   Perf. part: NR_UE_PC2_n34","NR_UE_PC2_n34-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1573,930053,"   UE Conformance - High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34-UEConTest",2,"Rel-17","R5","2021-09-17","2022-06-22",1,"RP-221760","RP-221357","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n34-Core ; 6/1/22: WID:RP-211980->RP-213034; 22/3/22: Compl:0%->53% ; 20/6/22: FCD:12/09/2022->22/06/2022; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-211980->RP-221760",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1574,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"2021-03-12","2023-09-22",1,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1575,911114,"   Core part: NR_UE_PC2_n39","NR_UE_PC2_n39-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1576,911214,"   Perf. part: NR_UE_PC2_n39","NR_UE_PC2_n39-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1577,930054,"   UE Conformance - High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39-UEConTest",2,"Rel-17","R5","2021-09-17","2023-09-22",1,"RP-211981","RP-232243","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n39-Core ; 6/1/22: WID:RP-211981->RP-213035; 22/3/22: Compl:0%->47% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ...; 23/9/22: WID:RP-211981->RP-222651; 9/12/22: FCD:23/03/2023->01/0...",null,93,47,null,null,"2021-09-29","2023-09-06"]
[1578,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"2021-04-07","NA"]
[1579,911115,"   Core part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1580,911215,"   Perf. part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 6/1/22: 0%->100",null,91,46,null,null,"2021-04-07","2022-01-06"]
[1581,911006,"NR Uplink Data Compression (UDC) ","NR_UDC",1,"Rel-17",null,"2021-03-12","2023-06-06",1,"RP-220140",null,"CATT ",null,"no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core ; 2/7/21: WID:RP-210909->RP-211203; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1582,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","2021-03-12","2022-03-11",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2022-04-05"]
[1583,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221449","RP-230395","Huiying ZHANG, CATT","zhanghuiying@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%->33%; Stat Rep: ->RP-223139; Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn; 17/3/23: Compl:33%->67%; Stat Rep: RP-223139->RP-230395; ;...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1584,910097,"Study on optimizations of pi/2 BPSK uplink power in NR ","FS_NR_Opt_pi2BPSK",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-213535","RP-220136","Huawei ",null,"; 1/10/21: 38.868 added;; 6/1/22: WID:RP-210910->RP-213535 ; ",38.868000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1585,910096,"Study on band combination handling in RAN4 ","FS_NR_ENDC_combo_rules",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-211146","RP-220164","ZTE ",null,"TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC ; 2/7/21: WID:RP-210773->RP-211146; 2/7/21: 38.862 added;13/9/21: Compl:0%->50%13/9/21: CD:Sat 12/03/22->Tue 22/03/2213/9/21: Stat ",38.862000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1586,880078,"Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs","NR_MIMO_OTA",1,"Rel-17",null,"2020-06-22","2023-12-12",1,"RP-213101",null,"CAICT",null,"25/9/20: WID:RP-201302->RP-201800; 6/1/22: WID:RP-201800->RP-213101",null,88,45,null,null,"2020-07-28","2022-01-06"]
[1587,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"2020-07-28","2022-06-20"]
[1588,880278,"   Perf. Part: NR_MIMO_OTA","NR_MIMO_OTA-Perf",2,"Rel-17","R4","2020-06-22","2022-09-22",1,"RP-222348","RP-222634","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","; 13/9/21: Compl:0%->20%; 13/9/21: CD:Wed 15 ; 22/3/22: Compl:20%->35%; ; 6/6/22: Compl:35%->55% 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com 9/...; 23/9/22: 90%->100;...",null,88,45,null,null,"2020-07-28","2022-09-23"]
[1589,970071,"   UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs ","NR_MIMO_OTA-UEConTest",2,"Rel-17","R5","2022-09-08","2023-12-12",1,"RP-221939","RP-233312","Istvan Szini, Apple","Istvan@apple.com","19/10/22: 38.551 added;; 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->5%; Stat Rep: ->RP-223198; Rapporteur: Apple->Istvan Szini, Apple; Rap eMail: ->Istvan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->8%; Stat Rep: RP-223198->RP-2301.....",38.551000000000002,97,49,null,null,"2022-09-23","2023-12-08"]
[1590,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"2020-03-25","2024-12-12",0.56000000000000005,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"2020-03-26","2021-01-06"]
[1591,870164,"   Core part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1592,870264,"   Perf. Part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Perf",2,"Rel-17","R4","2020-03-25","2021-03-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1593,950062,"   UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 ","NR_FR2_FWA_Bn257_Bn258-UEConTest",2,"Rel-17","R5","2022-03-15","2024-12-12",0.33,"RP-220424","RP-233761","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_FR2_FWA_Bn257_Bn258-Core 6/6/22: Compl:0%->5% 6/6/22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221492->RP-223221.....",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1594,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1595,880192,"   Core part: NR_bands_R17_BWs","NR_bands_R17_BWs-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221212","RP-221213","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","; 13/9/21: Compl:0%->50%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:50%->80%; 20/6/22: Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1596,880093,"Introduction of channel bandwidths 35MHz and 45MHz for NR FR1","NR_FR1_35MHz_45MHz_BW",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722; 2/7/21: WID:RP-210722->RP-211386",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1597,880193,"   Core part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1598,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1599,880097,"SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL","NR_SAR_PC2_interB_SUL_2BUL",1,"Rel-17",null,"2020-03-19","2022-09-22",1,"RP-212530",null,"China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 2/7/21: WID:RP-201584->RP-211494; 29/9/21: WID:RP-211494->RP-212530",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1600,880197,"   Core part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Core",2,"Rel-17","R4","2020-03-19","2021-09-21",1,"RP-212530","RP-211830","China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 13/9/21: Compl:0%->100%; 13/9/21: CD:Fri 19/03/21->Tue 21/09/21; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; ; 29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1601,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","2020-03-19","2022-03-21",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1602,920065,"   UE Conformance - SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL ","NR_SAR_PC2_interB_SUL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2022-09-22",1,"RP-211139","RP-221295","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_SAR_PC2_interB_SUL_2BUL-Core ; 13/9/21: Compl:0%->5%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 13/9/ ; 22/3/22: Compl:5%->23% ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinateleco...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[1603,900061,"NR coverage enhancements ","NR_cov_enh",1,"Rel-17",null,"2019-03-07","2024-03-01",0.99,"RP-211566",null,"China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 7/4/21: WID:RP-202928->RP-210855; 2/7/21: WID:RP-210855->RP-211566",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1604,860036,"   Study on on NR coverage enhancements","FS_NR_cov_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-200861",null,"China Telecom",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1605,900161,"   Core part: NR_cov_enh","NR_cov_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-11",1,"RP-211566","RP-220563","China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211826 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1606,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-12-21",1,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1607,950063,"   UE Conformance - NR coverage enhancements ","NR_cov_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2024-03-01",0.98,"RP-221298","RP-233578","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_cov_enh-Core ; 6/6/22: Compl:0%->5% ; 6/6/22: CD:15/06/2023->23/ ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-220576->RP-221298 ; ;...; 9/12/22: FCD:23/06...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[{"$f":"A1608+1","v":1608},900062,"Support of reduced capability NR devices ","NR_redcap",1,"Rel-17",null,"2019-12-16","2024-03-01",0.98,"RP-220966",null,"Ericsson ",null,"follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202933->RP-210918; 2/7/21: WID:RP-210918->RP-211574; 5/4/22: WID:RP-211574->RP-220966",null,90,46,null,null,"2021-01-06","2022-04-05"]
[1609,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1610,900162,"   Core part: NR_redcap","NR_redcap-Core",2,"Rel-17","R1","2020-12-14","2022-06-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 22/ 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1611,900262,"   Perf. part: NR_redcap","NR_redcap-Perf",2,"Rel-17","R1","2020-12-14","2022-12-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap ; 22/3/22: Compl:0%->25%; 22/3/22: CD:08/09/2022- 6/6/22: Compl ; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com ...; 9/12/22: 75%->100; 9/1/23: 100%...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1612,950066,"   UE Conformance - Support of reduced capability NR devices ","NR_redcap_plus_ARCH-UEConTest",2,"Rel-17","R5","2022-03-15","2024-03-01",0.92,"RP-232770","RP-232769","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 WI NR_redcap-Core and CT1 REL-17 WI ARCH_NR_REDCAP 6/6/22: Compl:0%->13% ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ...; 23/9/22: WID:RP-222830->RP-222136; 9/12/22: FCD:23/06/2023->...",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1613,930018,"   Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211100",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 10/12/21: 0%->100","23.501; 23.502 ",93,47,null,null,"2021-09-10","2021-12-10"]
[1614,940005,"   CT1 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","24.501; 23.122; 24.008; 24.368",94,48,null,null,"2022-01-07","2022-06-04"]
[1615,950047,"   CT3 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-221265",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: WID:CP-213081->CP-220304; 12/3/22: 0%->100; 4/6/22: WID:CP-220304->CP-221265","24.501; 23.122; 24.008; 24.368",95,48,null,null,"2022-03-12","2022-06-04"]
[1616,940100,"   CT4 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","29.571; 29.502; 29.540; 29.518; 23.008",94,48,null,null,"2022-01-07","2022-06-04"]
[1617,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"2022-01-07","2022-06-04"]
[1618,940027,"   Charging aspects of Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211428",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 12/3/22: 0%->35; 4/6/22: 35%->100","32.255; 32.298; 32.291 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1619,900064,"Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 ","NR_bands_UL_MIMO_PC3_R17",1,"Rel-17",null,"2020-12-14","2023-06-06",1,"RP-221518",null,"Huawei ",null,"basket WI ; 7/4/21: WID:RP-202819->RP-210557; 2/7/21: WID:RP-210557->RP-211380; 29/9/21: WID:RP-211380->RP-212184; 6/1/22: WID:RP-212184->RP-213137; 5/4/22: WID:RP-213137->RP-220704; 12/7/22: WID:RP-220704->RP-221518",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1620,900164,"   Core part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Core",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: Compl:0%->70%; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1621,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1622,940090,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-17","NR_bands_UL_MIMO_PC3_R17-UEConTest",2,"Rel-17","R5","2021-12-13","2023-06-06",1,"RP-220745","RP-230431","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_bands_UL_MIMO_PC3_R17; 22/3/22: Compl:0%->8%; 22/3/22: Stat Rep: ->RP-220419; 5/4/22: WID:RP-213227->RP-220745 ; 6/6/22: CD:12/09/2022->22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyu...",null,94,48,null,null,"2022-01-06","2023-06-07"]
[1623,900167,"Introduction of bandwidth combination set 4 (BCS4) for NR ","NR_BCS4-Core",1,"Rel-17","R4","2019-03-07","2022-06-22",1,"RP-202832","RP-221317","Per Lindell, Ericsson","per.lindell@ericsson.com","no Perf. part ; 20/6/22: FCD:03/06/2020->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221317; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1624,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"2020-12-14","2024-03-01",0.92,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;",37.866999999999997,90,46,null,null,"2021-01-06","2021-07-02"]
[1625,900168,"   Core part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Core",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI; TR 37.8xx ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478 ; ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1626,900268,"   Perf. part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI ; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478; 13/9/21: Stat Rep: ->RP-211833 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1627,981033,"   UE Conformance - Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17-UEConTest",2,"Rel-17","R5","2022-12-13","2024-03-01",0.76,"RP-222948","RP-233579","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","17/3/23: FCD:12/12/2023->06/06/2023; Compl:0%->5%; Stat Rep: ->RP-230318; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; 31/3/23: FCD:06/06/2023->12/12/2023; Stat Rep: RP-230318->RP-230715; ...; 6/9/23:...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1628,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"2020-12-14","2022-12-01",1,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"2021-01-06","NA"]
[1629,900169,"   Core part: HPUE_PC1_5_n77_n78","HPUE_PC1_5_n77_n78-Core",2,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-202912","RP-212049","Qualcomm ",null,"no Perf. part ; 13/9/21: Compl:0%->100% ; 29/9/21: 100%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1630,930055,"   UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-212581","RP-223280","Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia","jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com","tested: REL-17 WI HPUE_PC1_5_n77_n78-Core ; 22/3/22: Compl:0%->50%; ; 6/6/22: Compl:50%->61%20/6/22: Rapporteur: Verizon->Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia; Rap eMail: ->jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com; ...;...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1631,900070,"NR repeaters ","NR_repeaters",1,"Rel-17",null,"2020-12-14","2022-12-21",1,"RP-213514",null,"Qualcomm ",null,"no Perf. part ; 7/4/21: WID:RP-202927->RP-210818; 29/9/21: WID:RP-210818->RP-212129; 6/1/22: WID:RP-212129->RP-213514",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1632,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"2021-01-06","2022-06-20"]
[1633,930250,"   Perf. part: NR repeaters ","NR_repeaters-Perf",2,"Rel-17","R4","2021-09-17","2022-12-21",1,"RP-222275","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","Core part (UID=900170) started in Dec.20 while Perf. Part (UID=930250) started in 17/09/21 via revised WID RP-212129; TS 38.1??-1, TS 38.1??-2 ; 7/1/22: 38.115-2 and 38.115-1 added;; 20/6/22: FCD:17/09/2022->22/09/2022; Compl:0%->30%; WID: RP-213514->R...","38.115-2; 38.115-1",93,47,null,null,"2021-09-29","2023-01-09"]
[1634,930056,"Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC",1,"Rel-17","R4","2021-09-17","2023-09-22",0.99,"RP-221302",null,"Qualcomm ",null,"no Perf. part ; 12/7/22: WID:RP-212622->RP-221302",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1635,930156,"   Core part: Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-Core",2,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302","RP-221588","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","no Perf. Part ; 22/3/22: Compl:0%->75%; … 20/6/22: WID: RP-212622->RP-221302; Stat Rep: RP-220514->RP-221588; Rapporteur: Qualcomm->Gene Fong, Qualcomm Incorporated; Rap eMail: ->gfong@qti.qualcomm.com; ",null,93,47,null,null,"2021-09-29","2022-06-20"]
[1636,981036,"   UE Conformance - Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-UEConTest",2,"Rel-17","R5","2022-12-13","2023-09-22",1,"RP-221302","RP-232018","Kevin Wang / Jingzhou wu, Qualcomm / China Telecom","kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->52%; Stat Rep: ->RP-230101; Rapporteur: Qualcomm->Kevin Wang / Jingzhou wu, Qualcomm / China Telecom; Rap eMail: ->kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn; ...; 6/9/23: FCD:09/09/2023->22/09/2...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[1637,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"2021-09-29","2022-01-06"]
[1638,930157,"   Core part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ]; TR 36.8xx ; 7/1/22: 36.779 added ; ",36.779000000000003,93,47,null,null,"2021-09-29","2022-03-22"]
[1639,930257,"   Perf. part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ] ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1640,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-221417","RP-222802","Heng Pan, Puloli","heng.pan@puloli.com","9/9/22: Comp...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:72%->100%; Stat Rep: ->RP-222802; Rapporteur: Puloli->Heng Pan, Puloli; Rap eMail: ->heng.pan@puloli.com; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1641,930058,"High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212633",null,"China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ",null,93,47,null,null,"2021-09-29","NA"]
[1642,930158,"   Core part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1643,930258,"   Perf. part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1644,960070,"   UE Conformance - High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-222809","RP-222808","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2022; Compl:67%->100%; WID: RP-221158->RP-222809; Stat Rep: ->RP-222808; Rapporteur: ChinaUnicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1645,0,"Rel-17 NR Carrier Aggregation","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1646,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1647,881005,"NR itrabCA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R17_Intra",1,"Rel-17",null,"2016-06-09","2022-06-22",1,"RP-221319",null,"Ericsson",null,"25/9/20: WID:RP-200663->RP-201571; 6/1/21: WID:RP-201571->RP-202187; 7/4/21: WID:RP-202187->RP-210210; 2/7/21: WID:RP-210210->RP-211585; 29/9/21: WID:RP-211585->RP-211757; 6/1/22: WID:RP-211757->RP-212900; 5/4/22: WID:RP-212900->RP-220825; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1648,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1649,881205,"   Perf. Part: NR_CA_R17_Intra","NR_CA_R17_Intra-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1650,0,"   Rel-17 NR inter band Carrier Aggregation (iterbCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1651,900063,"High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1","NR_intra_HPUE_R17",1,"Rel-17",null,"2021-02-10","2022-06-22",1,"RP-221774",null,"Huawei",null,"7/4/21: WID:RP-202818->RP-210555; 29/9/21: WID:RP-210555->RP-212180; 6/1/22: WID:RP-212180->RP-213133; 5/4/22: WID:RP-213133->RP-220930; 12/7/22: WID:RP-220930->RP-221774",null,90,46,null,null,"2021-02-10","2022-07-12"]
[1652,900163,"   Core part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Core",2,"Rel-17","R4","2021-02-10","2022-06-22",1,"RP-221774","RP-221513 / 1773","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->10%; 22/3/22: CD:22/03/2022->10/06/2022 ; 20/6/22: Stat Rep: RP-221513->RP-221513 / 1773; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; ",null,90,46,null,null,"2021-02-10","2022-06-20"]
[1653,900263,"   Stopped - Perf. Part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Perf",2,"Rel-17","R4","2021-02-10","2022-06-10",1,"RP-221774","RP-220696","Huawei",null,"; 13/9/21: CD:Thu 09/12/21->Wed 22/06/22; ; 22/3/22: CD:22/06/2022->12/06/2022; 22/3/22: WID: RP-213133->RP-213132; 22/3/22: Stat Rep: RP-212179->RP-220696. 12/7/22: stopped at 0%. 0%->100",null,90,46,96,null,"2021-02-10","2022-07-12"]
[1654,881006,"NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2)","NR_CADC_R17_2BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221250",null,"ZTE",null,"25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495; 2/7/21: WID:RP-210495->RP-211058; 29/9/21: WID:RP-211058->RP-212511; 6/1/22: WID:RP-212511->RP-212887; 5/4/22: WID:RP-212887->RP-220144; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1655,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1656,881206,"   Perf. part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1657,881007,"NR iterbCA for 3 bands DL with 1 band UL","NR_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221772",null,"CATT",null,"25/9/20: WID:RP-200922->RP-201787; 6/1/21: WID:RP-201787->RP-202720; 7/4/21: WID:RP-202720->RP-210901; 2/7/21: WID:RP-210901->RP-211215; 29/9/21: WID:RP-211215->RP-212239; 6/1/22: WID:RP-212239->RP-213299; 5/4/22: WID:RP-213299->RP-220738; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1658,881107,"   Core part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1659,881207,"   Perf. part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: CD:15/09/2021->12/06/2022; 22/3/22: Stat Rep: ->RP-220737 ; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1660,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1661,881108,"   Core part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1662,881208,"   Perf. part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1663,881009,"NR iterbCA for 4 bands DL with 1 band UL","NR_CA_R17_4BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221321",null,"Ericsson",null,"25/9/20: WID:RP-200665->RP-201573; 6/1/21: WID:RP-201573->RP-202189; 7/4/21: WID:RP-202189->RP-210760; 2/7/21: WID:RP-210760->RP-211171; 29/9/21: WID:RP-211171->RP-211759; 6/1/22: WID:RP-211759->RP-212902; 5/4/22: WID:RP-212902->RP-220827; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1664,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1665,881209,"   Perf. part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1666,881010,"NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands","NR_CADC_R17_4BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221396",null,"Samsung",null,"25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802; 2/7/21: WID:RP-210802->RP-211194; 29/9/21: WID:RP-211194->RP-212110; 6/1/22: WID:RP-212110->RP-213111; 5/4/22: WID:RP-213111->RP-220676; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1667,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1668,881210,"   Perf. part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","; 13/9/21: Compl:0%->70%; ; 22/3/22: Compl:70%->90%; 20/6/22: Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1669,881011,"NR iterbCA for 5 bands DL with x bands UL (x=1, 2)","NR_CADC_R17_5BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221510",null,"Huawei",null,"25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561; 2/7/21: WID:RP-210561->RP-211373; 29/9/21: WID:RP-211373->RP-212176; 6/1/22: WID:RP-212176->RP-213129; 5/4/22: WID:RP-213129->RP-220692; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1670,881111,"   Core part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3/22: 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1671,881211,"   Perf. part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A1672+1","v":1672},890054,"Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)","NR_PC2_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-09-17","2023-12-12",1,"RP-221866",null,"China Telecom ",null,"basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 6/1/21: WID:RP-202102->RP-202373; 7/4/21: WID:RP-202373->RP-210476; 2/7/21: WID:RP-210476->RP-211131; 2/7/21: 38.841 added;; 29/9/21: WID:RP-211131->RP-211831; 6/1/22: WID:RP...",38.841000000000001,89,45,null,null,"2020-09-25","2022-07-12"]
[1673,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1674,890254,"   Perf. part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI ; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211131->RP-202102 RP-202373 RP-210476 RP-211131; 13/9/21: Stat Rep: ->RP-211832; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: WID: RP-213649->RP‑213649; 22/3/22: Stat Rep: RP-211832-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1675,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2023-12-12",1,"RP-233581","RP-233580","Jingzhou Wu, Dan Song, China Telecom, China Mobile","wujingzhou@chinatelecom.cn, songdan@chinamobile.com","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...;...",null,92,47,null,null,"2021-07-02","2024-01-02"]
[1676,0,"Rel-17 NR and LTE","-",1,"Rel-17",null,"2020-03-25","2020-09-15",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1677,920072,"LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39",1,"Rel-17","R4","2019-03-07","2019-03-07",1,null,"RP-211995","CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 13/9/21: Compl:0%->100% ; ",null,92,47,null,null,"2021-07-02","2021-09-13"]
[1678,920172,"   Core part: LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core",2,"Rel-17","R4","2021-06-15","2021-12-15",1,"RP-211996",null,"CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 29/9/21: WID:RP-211509->RP-211996",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1679,940089,"   UE Conformance - LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest",2,"Rel-17","R5","2021-12-13","2022-03-11",1,"RP-213036","RP-220625","CMCC",null,"tested: REL-17 WI DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1680,920073,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795",null,"Nokia ",null,"this is not a basket WI ; 29/9/21: WID:RP-211571->RP-212533; 6/1/22: WID:RP-212533->RP-213106; 5/4/22: WID:RP-213106->RP-220767; 12/7/22: WID:RP-220767->RP-221795",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1681,920173,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; …; 7/1/22: 37.828 and 37.828 added;; 22/3/22: Compl:0%->50% ; 20/6/22: Compl:50%->100%; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail...","37.828; 37.828",92,47,null,null,"2021-07-02","2022-06-20"]
[1682,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","2021-09-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1683,920074,"Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524",null,"Huawei ",null,"basket WI; TR 37.717-11-41 ; 29/9/21: WID:RP-211592->RP-212606; 6/1/22: WID:RP-212606->RP-213142; 5/4/22: WID:RP-213142->RP-220712; 12/7/22: WID:RP-220712->RP-221524",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1684,920174,"   Core part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI; TR 37.717-11-41 ; 20/6/22: FCD:15/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221523; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1685,920274,"   Perf. part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Perf",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI ; 22/3/22: Compl:0%->15%; 22/3/22: CD:15/03/2022->10/06/2022; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1686,911019,"Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths","ENDC_R17_1BLTE_1BNR_MSD",1,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part; 2/7/21: WID:RP-210891->RP-211384; 29/9/21: WID:RP-211384->RP-212187; 6/1/22: WID:RP-212187->RP-213140; 5/4/22: WID:RP-213140->RP-220709",null,91,46,null,null,"2021-04-09","2022-04-05"]
[1687,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"2021-04-09","2022-06-20"]
[1688,930259,"   Stopped - Perf. Part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Perf",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon ",null,"4/6/22: Stopped at 70%. This Perf. part is not needed",null,93,47,96,null,"2022-03-13","2022-06-04"]
[1689,911011,"Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR",1,"Rel-17",null,"2021-03-12","2024-06-06",0.51,"RP-221322",null,"Ericsson ",null,"basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: WID:RP-210816->RP-211172; 29/9/21: WID:RP-211172->RP-211760; 6/1/22: WID:RP-211760->RP-213467; 5/4/22: WID:RP-213467->RP-220828; 12/7/22: WID:RP-220...",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1690,911111,"   Core part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: 37.827 added; ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; List of Impacted TS & TR updated; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1691,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1692,930051,"   UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR-UEConTest",2,"Rel-17","R5","2021-09-17","2024-06-06",0.06,"RP-230082","RP-232954","Kuba KOLODZIEJ, Ericsson","Kuba[dot]kolodziej[at]ericsson[dot]com","tested: REL-17 WI ENDC_PC2_R17_xLTE_yNR ; 22/3/22: Compl:0%->5%; 22/3/22: CD:15/12/2022->12/12/2022; 22/3/22 6/6/22: CD:12/12/2022->22/12/2022 ; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Ericsson; Rap eMail: ->Leif[dot]mattisson[at]ericsson[d...",null,93,47,null,null,"2021-09-29","2023-12-08"]
[1693,911018,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC ","LTE_NR_Simult_RxTx",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-221521",null,"Huawei ",null,"; 2/7/21: WID:RP-210890->RP-211382; 5/4/22: WID:RP-211382->RP-220707; 12/7/22: WID:RP-220707->RP-221521",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1694,911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",38.838999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1695,911218,"   Stopped - Perf. part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 6/6/22: Compl:70%->0%6/6/22: CD:22/03/2022->22/06/20226/6/22: WID: RP-220707->RP-2113826/6/22: Stat Rep: RP-212185->RP-221520; 20/6/22: Compl:0%->100%; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; Sto",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1696,890052,"Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) ","DC_R17_5BLTE_1BNR_6DL2UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220672",null,"Samsung ",null,"basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801; 2/7/21: WID:RP-210801->RP-211195; 6/1/22: WID:RP-211195->RP-213112; 5/4/22: WID:RP-213112->RP-220672",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1697,890152,"   Core part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI; TR 37.717-51-11 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1698,890252,"   Perf. part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1699,890053,"Rel-17 Dual Connectivity (DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) ","DC_R17_xBLTE_2BNR_yDL3UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220674",null,"Samsung ",null,"basket WI; TR 37.717-21-22 ; 6/1/21: WID:RP-201643->RP-202542; 5/4/22: WID:RP-202542->RP-220674",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1700,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1701,890253,"   Perf. part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1702,880080,"Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band","NR_LTE_V2X_PC5_combos",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-213297",null,"CATT",null,"25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588; 6/1/22: WID:RP-210588->RP-213297",37.875,88,45,null,null,"2020-07-28","2022-01-06"]
[1703,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1704,880280,"   Perf. part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->9 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1705,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"2020-06-22","2023-06-06",1,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1706,880194,"   Core part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3/2 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1707,880294,"   Perf. part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1708,911000,"   UE Conformance - ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-UEConTest",2,"Rel-17","R5","2021-03-12","2023-06-06",1,"RP-211420","RP-230698","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 basket WI ENDC_UE_PC2_R17_NR_TDD-Core ; 2/7/21: WID:RP-210401->RP-211420; 2/7/21: 0%->10 ; ; 6/6/22: Com ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ; ;...; 9/12/22: FCD:23/03/2023->01...",null,91,46,null,null,"2021-04-07","2023-06-07"]
[1709,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1710,880195,"   Core part: DSS_LTE_B38_NR_Bn38","DSS_LTE_B38_NR_Bn38-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1711,880096,"LTE/NR spectrum sharing in Band 40/n40","DSS_LTE_B40_NR_Bn40",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: WID:RP-201362->RP-202084",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1712,880196,"   Core part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1713,880296,"   Perf. part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Perf",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1714,880098,"Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_1BLTE_1BNR_2DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221257",null,"CHTTL",null,"25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204; 2/7/21: WID:RP-210204->RP-211162; 29/9/21: WID:RP-211162->RP-212096; 6/1/22: WID:RP-212096->RP-213060; 5/4/22: WID:RP-213060->RP-220398; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1715,880198,"   Core part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: Compl:0%->75%; ; 22/3/22: Compl:75%->90%; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1716,880298,"   Perf. part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:0%->90%; ; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1717,880099,"Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_2BLTE_1BNR_3DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221508",null,"Huawei",null,"25/9/20: WID:RP-201369->RP-202060; 6/1/21: WID:RP-202060->RP-202613; 7/4/21: WID:RP-202613->RP-210559; 2/7/21: WID:RP-210559->RP-211371; 29/9/21: WID:RP-211371->RP-212174; 6/1/22: WID:RP-212174->RP-213127; 5/4/22: WID:RP-213127->RP-220689; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1718,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1719,890263,"   Perf. part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-17","R4","2020-09-16","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221507; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1720,881000,"Dual Connectivity (DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_3BLTE_1BNR_4DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221320",null,"Ericsson",null,"25/9/20: WID:RP-201370->RP-201572; 6/1/21: WID:RP-201572->RP-202188; 7/4/21: WID:RP-202188->RP-210211; 2/7/21: WID:RP-210211->RP-211170; 29/9/21: WID:RP-211170->RP-211758; 6/1/22: WID:RP-211758->RP-212901; 5/4/22: WID:RP-212901->RP-220826; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1721,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1722,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1723,881001,"Dual Connectivity (DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_4BLTE_1BNR_5DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221073",null,"Nokia",null,"25/9/20: WID:RP-201371->RP-201483; 6/1/21: WID:RP-201483->RP-202590; 7/4/21: WID:RP-202590->RP-210766; 2/7/21: WID:RP-210766->RP-211319; 29/9/21: WID:RP-211319->RP-212532; 6/1/22: WID:RP-212532->RP-213251; 5/4/22: WID:RP-213251->RP-220999; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1724,881101,"   Core part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1725,881201,"   Perf. part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1726,881002,"Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R17_xBLTE_2BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221182",null,"LG Electronics",null,"25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202; 2/7/21: WID:RP-210202->RP-211043; 29/9/21: WID:RP-211043->RP-211750; 6/1/22: WID:RP-211750->RP-212876; 5/4/22: WID:RP-212876->RP-220302; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1727,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1728,881202,"   Perf. part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1729,881003,"Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL)","DC_R17_xBLTE_yBNR_3DL3UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221232",null,"ZTE",null,"25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344; 2/7/21: WID:RP-210344->RP-211054; 29/9/21: WID:RP-211054->RP-211803; 6/1/22: WID:RP-211803->RP-212883; 5/4/22: WID:RP-212883->RP-220202; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1730,881103,"   Core part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1731,881203,"   Perf. part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1732,881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1733,881104,"   Core part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1734,881204,"   Perf. part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1735,881012,"band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R17",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221512",null,"Huawei",null,"25/9/20: WID:RP-201026->RP-201726; 6/1/21: WID:RP-201726->RP-202611; 7/4/21: WID:RP-202611->RP-210563; 2/7/21: WID:RP-210563->RP-211375; 29/9/21: WID:RP-211375->RP-212178; 6/1/22: WID:RP-212178->RP-213131; 5/4/22: WID:RP-213131->RP-220695; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[{"$f":"A1736+1","v":1736},881112,"   Core part: NR_SUL_combos_R17","NR_SUL_combos_R17-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1737,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1738,900056,"UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2024-12-12",0.11,"RP-231237","RP-233759","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 basket WIs: NR_CA_R17_Intra, NR_CADC_R17_2BDL_xBUL, NR_CA_R17_3BDL_1BUL, NR_CADC_R17_3BDL_2BUL, NR_CA_R17_4BDL_1BUL, NR_CADC_R17_4BDL_2BUL, NR_CADC_R17_5BDL_xBUL, NR_SUL_combos_R17, DC_R17_1BLTE_1BNR_2DL2UL, DC_R17_2BLTE_1BNR_3DL2UL, DC_...",null,90,46,null,null,"2021-01-06","2023-12-08"]
[1739,0,"Rel-17 NR new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1740,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1741,911116,"   Core part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Core",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP‑211495","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 1/10/21: 38.853 added;; 22/3/22: Compl:0 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->95%; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wen...",38.853000000000002,91,46,null,null,"2021-04-07","2022-09-09"]
[1742,911216,"   Perf. part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221768","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","; 22/3/22: Compl:0%->90% ; 20/6/22: FCD:22/03/2023->22/06/2022; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wendler, UIC; Rap eMail: ->ingo dot wendler at sbb dot ch; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1743,911017,"Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_1900MHz_TDD",1,"Rel-17",null,"2021-03-12","2022-03-11",1,"RP-211542",null,"Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 2/7/21: WID:RP-210879->RP-211542",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1744,911117,"   Core part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Core",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 1/10/21: 38.852 added ; ",38.851999999999997,91,46,null,null,"2021-04-07","2022-03-22"]
[1745,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1746,860041,"Extending current NR operation to 71GHz","NR_ext_to_71GHz",1,"Rel-17","R1","2019-12-16","2023-03-03",0.99,"RP-222656",null,"Qualcomm",null,"affects: NR.; 25/9/20: WID:RP-193229->RP-201845; 6/1/21: WID:RP-201845->RP-202925; 7/4/21: WID:RP-202925->RP-210862; 2/7/21: WID:RP-210862->RP-211584; 29/9/21: WID:RP-211584->RP-212637; 6/1/22: WID:RP-212637->RP-213540; 23/9/22: WID:RP-213540->RP-222656",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1747,860141,"   Core part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Core",2,"Rel-17","R1","2019-12-16","2022-09-22",1,"RP-222656","RP-222655","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: Compl:0%->45%; ; 22/3/22: Compl:45%->90%; 20/6/22: Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation; Rap eMail: ->jingsun@qti.qualcomm.com; ...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1748,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","2019-12-16","2023-03-03",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1749,860037,"Study on supporting NR from 52.6 GHz to 71 GHz","FS_NR_52_to_71GHz",1,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-201838",null,"Intel",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193259->RP-200902; 25/9/20: WID:RP-200902->RP-201838; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1750,870060,"Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz","FS_NR_IMT_param",1,"Rel-17","R4","2020-03-25","2020-12-15",1,"RP-202276",null,"Ericsson",null,"affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1751,870063,"Introduction of NR band n13","NR_n13",1,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx",null,87,44,null,null,"2020-03-26","NA"]
[1752,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1753,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1754,880082,"Introduction of NR 47GHz band","NR_47GHz_band",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"RP-212528","RP-211772","Ericsson",null,"7/4/21: WID:RP-201232->RP-210827; 2/7/21: WID:RP-210827->RP-211568; 13/9/21: C ",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1755,880182,"   Core part: Introduction of NR 47GHz band","NR_47GHz_band-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"2/7/21: 0%->100; 29/9/21: WID:RP-211568->RP-212528",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1756,880282,"   Perf. part: Introduction of NR 47GHz band","NR_47GHz_band-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1757,880084,"Introduction of NR band 24","NR_band_n24",1,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: WID:RP-201357->RP-211505",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1758,880184,"   Core part: Introduction of NR band 24","NR_band_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1759,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1760,890050,"Introduction of 6GHz NR licensed bands ","NR_6GHz",1,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504",null,"Huawei ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844; 6/1/22: WID:RP-202844->RP-213696; 5/4/22: WID:RP-213696->RP-220686; 12/7/22: WID:RP-220686->RP-221504",null,89,45,null,null,"2020-09-25","2022-07-12"]
[1761,890150,"   Core part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 22/3/22: Compl:0%->35% ; 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->l...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1762,890250,"   Perf. part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Perf",2,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Fri 17/06/22->Wed 22/06/22 ; 22/3/22: Compl:0%->20%; 2 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->...",null,89,45,null,null,"2020-09-25","2022-09-09"]
[1763,920075,"Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full",1,"Rel-17","R4","2021-06-15","2022-06-15",0.43,"RP-213683",null,"Apple ",null,"in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 29/9/21: WID:RP-211602->RP-212302; 6/1/22: WID:RP-212302->RP-213683",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1764,920175,"   Core part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Core",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-212683","RP-220450","Alexander Sayenko","asayenko@apple.com","in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 20/6/22: FCD:15/03/2022->22/03/2022; Compl:0%->100%; WID: RP-213683->RP-212683; Stat Rep: ->RP-220450; Rapporteur: Apple->Al...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1765,920275,"   Perf. part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Perf",2,"Rel-17","R4","2021-06-16","2022-06-15",0,"RP-213683",null,"Apple ",null,null,null,92,47,null,null,"2021-07-02","NA"]
[1766,890051,"Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU",1,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604",null,"Nokia ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762; 29/9/21: WID:RP-210762->RP-212625; 6/1/22: WID:RP-212625->RP-213604",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1767,890151,"   Core part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 10/2/21: 38.849 added;; 13/9/21: Compl:0%->30%; 13/9/21: CD:Tue 15/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",38.848999999999997,89,45,null,null,"2020-09-25","2022-03-22"]
[1768,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1769,900065,"Introduction of NR band n67 ","NR_n67",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,null,null,90,46,null,null,"2021-01-06","NA"]
[1770,900165,"   Core part: Introduction of NR band n67 ","NR_n67-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1771,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1772,900066,"Introduction of NR band n85 ","NR_n85",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 7/4/21: WID:RP-202830->RP-210707",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1773,900166,"   Core part: Introduction of NR band n85 ","NR_n85-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1774,900266,"   Perf. part: Introduction of NR band n85 ","NR_n85-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1775,880083,"Introduction of 1.6 GHz NR supplemental uplink (SUL) band with same uplink frequency range of Band 24","NR_SUL_UL_n24",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: WID:RP-201251->RP-210341",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1776,880183,"   Core part: NR_SUL_UL_n24","NR_SUL_UL_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1777,880283,"   Perf. part: NR_SUL_UL_n24","NR_SUL_UL_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1778,880085,"Introduction of NR supplemental uplink (SUL) band 1880-1920MHz","NR_SUL_band_1880_1920MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1779,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1780,880285,"   Perf. part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1781,880086,"Introduction of NR supplemental uplink (SUL) band 2300-2400MHz","NR_SUL_band_2300_2400MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1782,880186,"   Core part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1783,880286,"   Perf. part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1784,900055,"UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2022-12-01",1,"RP-223434","RP-223215","Yuxin Hao, Huawei Technologies. Co., Ltd","haoyuxin@huawei.com","tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co.,...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1785,0,"Rel-17 LTE new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1786,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.82,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"2021-04-08","2021-07-02"]
[1787,911120,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1-Core",2,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",0.97,"RP-211144","RP-220172","EBU",null,"WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part; 13/9/21: C ; ",null,91,46,null,null,"2021-04-08","2022-03-22"]
[1788,880079,"Additional LTE bands for UE categories M1/M2/NB1/NB2","LTE_bands_R17_M1_M2_NB1_NB2",1,"Rel-17",null,"2020-06-08","2022-06-22",1,"RP-220816",null,"Ericsson",null,"25/9/20: WID:RP-200804->RP-201646; 29/9/21: WID:RP-201646->RP-211857; 6/1/22: WID:RP-211857->RP-212906; 5/4/22: WID:RP-212906->RP-220816",null,88,45,null,null,"2020-07-28","2022-04-05"]
[1789,880179,"   Core part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Core",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1790,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1791,880081,"Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits","LTE_B24_mod",1,"Rel-17",null,"2020-06-15","2021-12-15",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: WID:RP-201356->RP-211507",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1792,880181,"   Core part: LTE_B24_mod","LTE_B24_mod-Core",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1793,880281,"   Perf. part: LTE_B24_mod","LTE_B24_mod-Perf",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1794,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","2021-06-15","2021-12-15",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1795,0,"Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1796,880087,"LTE iterbCA for 2 bands DL with 1 band UL","LTE_CA_R17_2BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221389",null,"Qualcomm",null,"25/9/20: WID:RP-201248->RP-201754; 6/1/21: WID:RP-201754->RP-202573; 7/4/21: WID:RP-202573->RP-210227; 2/7/21: WID:RP-210227->RP-211560; 29/9/21: WID:RP-211560->RP-211859; 6/1/22: WID:RP-211859->RP-212933; 5/4/22: WID:RP-212933->RP-220552; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1797,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1798,880287,"   Perf. part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 6/6/22: Comp ; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1799,880088,"LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221526",null,"Huawei",null,"25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540; 2/7/21: WID:RP-210540->RP-211388; 29/9/21: WID:RP-211388->RP-212192; 6/1/22: WID:RP-212192->RP-213144; 5/4/22: WID:RP-213144->RP-220715; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[{"$f":"A1800+1","v":1800},880188,"   Core part: LTE_CA_R17_3BDL_1BUL","LTE_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221526","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","; 22/3/22: Compl:0%->67%; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1801,880288,"   Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220713","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","6/1/21: stopped at 0%; 22/3/22: Compl:100%->10%; 22/3/22: CD:15/09/2021->10/06/2022 ; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,96,null,"2020-07-28","2022-06-20"]
[1802,880089,"LTE iterbCA Core for x bands DL (x=4, 5, 6) with 1 band UL","LTE_CA_R17_xBDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221305",null,"Nokia",null,"25/9/20: WID:RP-201245->RP-201911; 6/1/21: WID:RP-201911->RP-202212; 7/4/21: WID:RP-202212->RP-210837; 2/7/21: WID:RP-210837->RP-211068; 29/9/21: WID:RP-211068->RP-211885; 6/1/22: WID:RP-211885->RP-212813; 5/4/22: WID:RP-212813->RP-220175; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1803,880189,"   Core part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1804,880289,"   Perf. part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1805,880090,"LTE iterbCA for 2 bands DL with 2 bands UL","LTE_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221528",null,"Huawei",null,"25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542; 2/7/21: WID:RP-210542->RP-211390; 29/9/21: WID:RP-211390->RP-212194; 5/4/22: WID:RP-212194->RP-220718; 12/7/22: WID:RP-220718->RP-221528",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1806,880190,"   Core part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","; 22/3/22: Compl:0%->70%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1807,880290,"   Perf. part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","22/3/22: CD:15/09/2021->12/06/202222/3/22: Stat Rep: ->RP-220716 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1808,880091,"LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL","LTE_CA_R17_xBDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221188",null,"LG",null,"25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200; 2/7/21: WID:RP-210200->RP-211041; 29/9/21: WID:RP-211041->RP-211748; 6/1/22: WID:RP-211748->RP-212874; 5/4/22: WID:RP-212874->RP-220295; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1809,880191,"   Core part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1810,880291,"   Perf. part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1811,1010051,"UE Conformance - Rel-17 LTE CA Configurations ","LTE_CA_R17-UEConTest",1,"Rel-17","R5","2023-09-09","2024-12-12",0.05,"RP-232260","RP-233566","Lei GAO, China Telecom","gaol8@chinatelecom.cn","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233566; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[1812,0,"Release 17 other Studies","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1813,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"2020-09-10","2022-03-12"]
[1814,900020,"Study on enhanced Security Aspects of the 5G Service Based Architecture ","FS_eSBA_SEC",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201021",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","10/2/21: 33.875 added;; 19/3/21: 0%->45; 19/3/21: FCD:11/06/2021->09/21; 11/6/21: 45%->70; 11/6/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->75; 12/9/22: 75%->87; 31/3/23: 87%->100",33.875,90,46,null,null,"2020-12-04","2023-03-31"]
[1815,810037,"Study on SECAM and SCAS for 3GPP virtualized network products","FS_VNP_SECAM_SCAS",1,"Rel-17","S3","2018-10-02","2021-12-10",1,"SP-180696",null,"Minpeng Qi, China Mobile","qiminpeng@chinamobile.com","2/10/18: Moved from Rel-17¦7/12/18: 0%->5¦20/3/19: 5%->20; 13/9/19: 20%->30; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 30%->35; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 35%->60; 5/12/20: 60%->70; ","New",81,41,null,null,"2018-09-06","2021-09-13"]
[1816,820010,"Study on Long Term Key Update Process (LTKUP) Detailed solutions","FS_LTKUP_Detail",1,"Rel-17","S3","2018-12-13","2020-03-12",1,"SP-181038",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100",null,82,42,null,null,"2018-12-06","2020-06-26"]
[1817,880011,"Study on 5G Glass-type AR/MR Devices ","FS_5GSTAR",1,"Rel-17","S4","2020-06-25","2022-03-11",1,"SP-200399",null,"Hakju Ryan Lee ","hakju00.lee@samsung.com ","25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 65%->80; 13/12/21: 80%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100",26.998000000000001,88,45,null,null,"2020-06-25","2022-03-12"]
[1818,850004,"Study on VR Streaming Conformance and Guidelines ","FS_VR_CoGui",1,"Rel-17","S4","2019-09-13","2022-03-11",1,"SP-190642",null,"Igor CURCIO ","igor.curcio@nokia.com ","; 8/10/19: 26.999 added;; 8/10/19: 26.119 added;; 25/3/20: 0%->10; 20/4/20: FCD:12/06/2020->12/20; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 10%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100","New ; 26.999; 26.119",85,43,null,null,"2019-09-13","2022-03-12"]
[1819,900029,"Study on 5G media streaming extensions ","FS_5GMS_EXT",1,"Rel-17","S4","2020-12-04","2022-03-11",1,"SP-200937",null,"Iraj Sodagar, Company, Tencent ","irajs@live.com ","21/3/21: 0%->5; 11/6/21: 5%->40; 2/7/21: 26.804 added;; 13/9/21: 40%->50; 13/12/21: 50%->60; 13/12/21: FCD:Wed 08/09/->03/22; 12/3/22: 60%->100",26.803999999999998,90,46,null,null,"2020-12-03","2022-03-12"]
[1820,870015,"Study on Streaming Architecture extensions For Edge processing ","FS_EMSA",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200056",null,"Bouazizi, Imed, Qualcomm ","bouazizi@qti.qualcomm.com ","10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100",null,87,44,null,null,"2019-12-06","2021-06-11"]
[1821,870011,"Study on 5G Video Codec Characteristics ","FS_5GVideo",1,"Rel-17","S4","2020-03-25","2022-06-10",1,"SP-200052",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->75; 13/12/21: 75%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->90; 12/3/22: FC ",null,87,44,null,null,"2019-12-06","2022-06-04"]
[1822,870012,"Study on the use of NBMP in FLUS ","FS_FLUS_NBMP",1,"Rel-17","S4","2020-03-25","2021-09-08",1,"SP-200053",null,"Iraj Sodagar","irajsodagar@tencent.com ","; 10/6/20: 0%->10; 5/12/20: 10%->30; 5/12/20: FCD:11/12/2020->09/20; 21/3/21: 30%->40; 11/6/21: 40%->96; 13/9/21: 96%->100",26.939,87,44,null,null,"2019-12-06","2021-09-13"]
[1823,911032,"Study on enhanced IMS to 5GC Integration Phase 2 ","FS_eIMS5G2",1,"Rel-17","ct","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15","23.700-10",88,45,null,null,"2020-06-26","2021-03-21"]
[1824,880024,"   CT1 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 13/9/21: 15%->60; 13/12/21: 60%->90; 12/3/22: FCD:08/09/2021->3/22; 12/3/22: 90%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1825,911036,"   CT3 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C3","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 0%->5; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 5%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1826,911033,"   CT4 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C4","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 30%->40; 11/6/21: 40%->30; 14/6/21: 30%->40; 13/9/21: 40%->50; 13/9/21: FCD:Wed 08/09/->12/21; 13/ ","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[1827,890002,"Study on Port Number Allocation Alternatives for New 3GPP Interfaces ","FS_PortAl",1,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-220391",null,"Giorgi Gulbani, Huawei","giorgi.gulbani@huawei.com ","13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->85; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 85%->100; 22/3/22: WID:CP-202243->CP-220391",null,89,45,null,null,"2020-09-11","2022-03-22"]
[1828,880075,"Study on scenarios and requirements of in-coverage, partial coverage, and out-of-coverage NR positioning use cases","FS_NR_pos_cov",1,"Rel-17","RP","2020-06-22","2021-09-15",1,"RP-201518",null,"LG Electronics",null,"25/9/20: WID:RP-201384->RP-201518; 29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1829,860062,"Study on XR (Extended Reality) evaluations for NR","FS_NR_XR_eval",1,"Rel-17","R1","2019-12-16","2021-12-21",1,"RP-210460","RP-212047","Qualcomm",null,"affects: NR.; 28/7/20: WID:RP-193241->RP-201145; 7/4/21: WID:RP-201145->RP-210460; 13/9/21: Compl:0%->70% ; 6/1/22: 70%->100",null,86,44,null,null,"2020-01-14","2022-01-06"]
[1830,860039,"Study on enhancement of RAN slicing for NR","FS_NR_slice",1,"Rel-17","R2","2019-12-16","2020-12-15",1,"RP-201612",null,"CMCC",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193254->RP-201612; 2/7/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1831,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","2020-06-22","2022-03-11",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"2020-07-28","2022-04-05"]
[1832,880077,"Study on high-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands 5 and 12 and NR band n71","FS_LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2020-03-19","2020-03-19",1,"RP-201261",null,"Nokia",null,"25/9/20: 37.880 added;; 2/7/21: 0%->100",37.880000000000003,88,45,null,null,"2020-07-28","2021-07-02"]
[1833,900058,"Study on high power UE (power class 2) for one NR FDD band ","FS_NR_PC2_UE_FDD",1,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-212892","RP-211854","China Unicom ",null,"TR 38.8xx ; 13/9/21: Compl:0%->100%; 13/9/21: CD:Wed 08/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP- ; 29/9/21: 100%->100; 6/1/22: WID:RP-202870->RP-212892",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1834,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","2020-12-14","2021-09-08",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1835,890021,"Study on charging aspects of 5GS CIoT ","FS_5G_CIoT_CH",1,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200771",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","5/12/20: 0%->15; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 15%->30; 13/9/21: 30%->70; 13/9/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->100",null,89,45,null,null,"2020-09-10","2022-06-04"]
[1836,840021,"Stopped - Study on the Usage of User Identifiers in the 5G System ","FS_UUI5",1,"Rel-17","S2","2019-06-06","2020-06-12",1,"SP-190450",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; 21/1/22: stopped at 0%; 21/1/22: 0%->100","New ; 23.700-094; ",84,43,95,null,"2019-05-31","2022-01-21"]
[1837,830031,"Stopped - Study on service-based support for SMS in 5GC","FS_SB_SMS",1,"Rel-17","S2","2019-03-07","2019-12-05",1,"SP-190184",null,"George Foti ","George dot Foti at ericsson dot com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,95,null,"2019-03-14","2022-01-21"]
[1838,830034,"Stopped - Study on UPF enhancement for control and SBA","FS_UPCAS",1,"Rel-17","S2","2019-03-07","2020-03-06",1,"SP-190187",null,"Dan Wang, China Mobile","wangdanyjy@chinamobile.com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,95,null,"2019-03-14","2022-01-21"]
[1839,880004,"Stopped - Study on security aspects of the Disaggregated gNB Architecture ","FS_disagg_gNB_Sec",1,"Rel-17","S3","2020-06-25","2021-03-12",1,"SP-200349",null,"Sen XU, China Telecom ","xusen@chinatelecom.cn ","12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100. 13/7/22: marked as stopped (was already at 100%!) as per e-mail from Mirko on 02/06/22 14.03",33.840000000000003,88,45,95,null,"2020-06-25","2021-03-19"]
[1840,0,"--- RELEASE 16 ---","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1841,0,"Release 16 Features and related studies","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1842,0,"Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC)","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1843,830098,"Enhancement of URLLC support in the 5G Core network","5G_URLLC",1,"Rel-16",null,"2017-12-15","2024-03-03",0.93,"SP-181122",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-03-14"]
[1844,790008,"   Study on enhancement of URLLC supporting in 5GC ","FS_5G_URLLC",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180118",null,"Hui Ni, Huawei","Hui.ni@huawei.com","7/6/18: 0%->15¦6/8/18: 23.725 added;¦10/9/18: 15%->60¦7/12/18: 60%->85¦14/3/19: 85%->90; 31/5/19: 90%->95; 13/9/19: 95%->100","23.xyz; 23.725",79,40,null,null,"2018-03-15","2019-09-13"]
[1845,810036,"   Study on the security of URLLC for 5GS ","FS_5G_URLLC_SEC",2,"Rel-16","S3","2018-09-06","2019-06-12",1,"SP-180910",null,"Rong Wu, Huawei Technologies","Raina.wu@huawei.com","7/12/18: 0%->20¦20/3/19: FCD:019->06/19¦20/3/19: 20%->65; 31/5/19: 65%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1846,820019,"   Stage 2 of 5G_URLLC ","5G_URLLC",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181233",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1847,840026,"   Security of URLLC for 5GS ","5G_URLLC_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190351",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 6/12/19: FCD:12/12/2019->03/20; 9/4/21: 80%->100",33.500999999999998,84,43,null,null,"2019-05-31","2021-04-09"]
[1848,840005,"   CT Aspects of 5G_URLLC","5G_URLLC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","16/9/19: WID:CP-191063->CP-192022",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1849,870059,"      CT1 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100",null,87,44,null,null,"2019-05-31","2020-03-26"]
[1850,840060,"      CT3 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","29.512; 29.513; 29.514; 29.522; 29.508",84,43,null,null,"2019-05-31","2020-03-26"]
[1851,840061,"      CT4 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","31/5/19: 0%->5; 13/9/19: 5%->20; 6/12/19: 20%->60; 26/3/20: 60%->98; 26/6/20: 98%->100","29.244; 29.502; 29.503; 29.510; 29.281",84,43,null,null,"2019-05-31","2020-06-26"]
[1852,890020,"   Charging enhancement for URLLC ","5G_URLLC",2,"Rel-17","S5","2020-09-16","2021-06-11",1,"SP-200769",null,"Chen, Shan, Huawei ","chenshan@huawei.com ","; 5/12/20: 0%->20; 5/12/20: FCD:12/03/2021->06/20; 21/3/21: 20%->30; 13/9/21: 30%->100","32.255; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1853,1000013,"   Management Aspects of URLLC ","URLLC_Mgt",2,"Rel-18","S5","2023-06-08","2024-03-03",0.2,"SP-230631",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn ","; 7/9/23: 0%->10; 8/12/23: 10%->20","28.541; 28.552; 28.554 ",100,null,null,null,"2023-06-08","2023-12-08"]
[1854,780030,"   Stopped - Study on EPC support for Mobility with Low Latency Communication","FS_LLC_Mob",2,"Rel-16","S2","2017-12-15","2018-09-14",1,"SP-171069",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395","new 23.739",78,40,84,null,"2017-12-15","2018-06-07"]
[1855,790009,"   Stopped - Study on enht of systems using EPS for UR and Availability using commodity equipment","FS_EPS_URACE",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180119",null,"Chris Pudney","chris.pudney@vodafone.com","7/6/18: 0%->10¦6/8/18: 23.736 added¦6/6/19: stopped at 10% as per SP-190395; 6/6/19: 10%->100","new; 23.736",79,40,84,null,"2018-03-15","2019-06-06"]
[1856,830074,"Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC)","NR_L1enh_URLLC",1,"Rel-16","R1","2018-06-15","2023-12-12",0.99,"RP-191584",null,"Huawei",null,"26/6/19: WID:RP-190726->RP-191584",null,83,42,null,null,"2019-03-26","2019-06-26"]
[1857,800095,"   Study on physical layer enhancements for NR UR Low Latency Cases","FS_NR_L1enh_URLLC",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181477",null,"Huawei",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1858,830174,"   Core part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-190726",null,"Huawei",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1859,830274,"   Perf. part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-190726",null,"Huawei",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[1860,900054,"   UE Conformance Test Aspects - Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-UEConTest",2,"Rel-16","R5","2020-12-14","2023-12-12",1,"RP-202566","RP-233758","Chunying GU, Huawei","guchunying@huawei.com","tested: REL-16 WI NR_L1enh_URLLC-Core ; 8/4/21: 0%->5; 2/7/21: 5%->16; 22/3/22: Compl:16 ; 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 9/12/22: FCD:22/12/2022->01/12/2023; Compl:90%->91%; Stat Rep: RP-2214.....",null,90,46,null,null,"2021-01-06","2023-12-08"]
[1861,830080,"Support of NR Industrial Internet of Things (IoT)","NR_IIOT",1,"Rel-16","R2","2018-06-15","2022-03-11",1,"RP-192590",null,"Nokia",null,"26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1862,810060,"   Study on channel modeling for indoor industrial scenarios","FS_IIIOT_CM",2,"Rel-16","R1","2018-09-14","2019-09-13",1,"RP-182138",null,"Ericsson",null,"8/10/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-10-08"]
[1863,800098,"   Study on NR Industrial Internet of Things (IoT)","FS_NR_IIOT",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181479",null,"Nokia",null,"TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100",38.825000000000003,80,41,null,null,"2018-06-27","2019-03-26"]
[{"$f":"A1864+1","v":1864},830180,"   Core part: Support of NR Industrial Internet of Things (IoT)","NR_IIOT-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200797",null,"Nokia",null,"28/7/20: WID:RP-192590->RP-200797; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1865,880067,"   UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT)","NR_IioT-UEConTest",2,"Rel-16","R5","2020-06-22","2022-03-11",1,"RP-200757","RP-220623","CMCC",null,"8/10/20: 0%->5; 8/4/21: 5%->68; 2/7/21: 68%->77; 13/9/21: Compl:77%->95%; 13/9/21: C ; 29/9/21: WID:RP-200757->RP-211786; 6/1/22: WID:RP-211786->RP-212943; ",null,88,45,null,null,"2020-07-28","2022-03-22"]
[1866,820999,"5GS Enhanced support of Vertical and LAN Services","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",82,42,null,null,"2014-08-29","2014-08-29"]
[1867,750004,"Study on Communication for Automation in Vertical Domains","FS_CAV",1,"Rel-16","S1","2017-03-02","2018-03-15",1,"SP-170169",null,"Walewski, Joachim, Siemens AG","joachim.walewski@siemens.com ","7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100",22.803999999999998,75,38,null,null,"2017-03-02","2018-06-07"]
[1868,800007,"Service requirements for cyber-physical control applications in vertical domains","cyberCAV",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180321",null,"Joachim W. Walewski (Siemens)",null,"10/9/18: 5%->40¦4/12/18: 40%->100","22.261; 22.104",80,41,null,null,"2018-06-06","2018-12-04"]
[1869,830042,"5GS Enhanced support of Vertical and LAN Services","Vertical_LAN",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com",null,null,82,42,null,null,"2018-12-06","2018-06-14"]
[1870,800028,"   Study on 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180507",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","10/9/18: 0%->25¦7/12/18: 25%->88¦14/3/19: 88%->92; 31/5/19: 92%->100",23.734000000000002,80,41,null,null,"2018-06-06","2019-05-31"]
[1871,820017,"   Stage 2 of Vertical_LAN","Vertical_LAN",2,"Rel-16","S2","2018-12-13","2019-06-24",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-12-06"]
[1872,810038,"   Study on Security for 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN_SEC",2,"Rel-16","S3","2018-09-06","2019-12-12",1,"SP-180697",null,"Jerichow, Anja (Nokia) ","anja.jerichow@nokia.com ","7/12/18: 0%->10¦20/3/19: FCD:019->06/19¦20/3/19: 10%->65; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->78; 6/12/19: 78%->92; 25/3/20: 92%->100","New",81,41,null,null,"2018-09-06","2020-03-25"]
[1873,840027,"   Security for Vertical_LAN ","Vertical_LAN_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190352",null,"Jerichow, Anja, Nokia ","anja.jerichow@nokia.com ","13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100",33.500999999999998,84,43,null,null,"2019-05-31","2020-06-26"]
[1874,830010,"   CT aspects of Vertical_LAN","Vertical_LAN",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272",null,83,42,null,null,"2018-12-06","2019-12-09"]
[1875,830035,"      CT1 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->20; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 20%->75; 6/12/19: 75%->90; 26/3/20: 90%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.368; 24.501; 24.526",83,42,null,null,"2018-12-06","2020-09-13"]
[1876,830036,"      CT3 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-201174",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174","29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061",83,42,null,null,"2018-12-06","2020-06-26"]
[1877,830037,"      CT4 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->5; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 5%->50; 6/12/19: 50%->85; 26/3/20: 85%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.509; 29.510; 29.518; 29.571; 29.244; 29.281",83,42,null,null,"2018-12-06","2020-06-26"]
[1878,850048,"Service Enabler Architecture Layer for Verticals","SEAL",1,"Rel-16",null,"2019-03-07","2020-06-12",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 8/10/19: 33.434 added;; 8/10/19: 24.548 added;","new 23.434; 33.434; 24.548; 24.547",85,42,null,null,"2018-12-06","2019-10-08"]
[1879,820027,"   Stage 2 of SEAL","SEAL",2,"Rel-16","S6","2019-03-07","2019-08-29",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 13/9/19: 0%->100","new 23.434",82,42,null,null,"2018-12-06","2019-09-13"]
[1880,850019,"   Security aspects of SEAL","SEAL",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190901",null,"Rajavelsamy Rajadurai (Samsung) ","rajvel@samsung.com ","; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1881,850006,"   CT aspects of SEAL ","SEAL",2,"Rel-16","ct","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ",null,"New ",85,43,null,null,"2019-09-13","NA"]
[1882,850049,"      CT1 aspects of SEAL ","SEAL",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 6/12/19: 0%->60; 6/12/19: 60%->60; 26/3/20: 60%->80; 26/6/20: 80%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1883,850050,"      CT3 aspects of SEAL ","SEAL",3,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 26/3/20: 0%->75; 26/6/20: 75%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[1884,820067,"NR-based access to unlicensed spectrum","NR_unlic",1,"Rel-16","R1","2017-03-15","2019-12-15",0.84,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834",null,82,42,null,null,"2019-01-16","2020-09-25"]
[1885,750045,"   Study on NR-based access to unlicensed spectrum","FS_NR_unlic",2,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181339",null,"Qualcomm",null,"TR 38.8XX19/6/17: WID: RP-170828->RP-171416¦30/6/17: 32.889 added;¦19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%¦27/6/18: Compl:10%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦16/1/19: 40%->100",32.889000000000003,75,38,null,null,"2017-03-21","2019-01-16"]
[1886,820167,"   Core part: NR-based access to unlicensed spectrum","NR_unlic-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[1887,820267,"   Perf. part: NR-based access to unlicensed spectrum","NR_unlic-Perf",2,"Rel-16","R4","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 2/7/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-07-02"]
[1888,911003,"   UE Conformance Test Aspects - NR-based access to unlicensed spectrum ","NR_unlic-UEConTest",2,"Rel-16","R5","2021-03-12","2024-06-06",0.65,"RP-210708","RP-233872","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","tested: REL-16 WI NR_unlic-Core ; 2/7/21: 0%->5 ; ; 6/6/22: Compl:18%->20% 20/6/22: Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com ; 9/...; 9/12/22: FCD:22/12/2022->01/06/2023; Compl:25%->28%; Stat Re...",null,91,46,null,null,"2021-04-07","2023-12-08"]
[1889,800006,"LAN support in 5G","5GLAN",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","11/3/22: 99%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2022-03-11"]
[1890,760007,"   Study on LAN Support in 5G ","FS_5GLAN",2,"Rel-16","S1","2017-06-05","2018-03-15",1,"SP-170456",null,"Nasielski, Jack, Qualcomm Incorporated","jackn@qti.qualcomm.com","11/9/17: 0%->35¦15/12/17: 35%->65¦16/3/18: 65%->100","22.821; ",76,39,null,null,"2017-06-03","2018-03-16"]
[1891,800047,"   Stage 1 of 5GLAN","5GLAN",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","10/9/18: 40%->75¦10/9/18: FCD:09/18->12/18¦4/12/18: 75%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2018-12-04"]
[1892,830024,"Study on non-public networks management","FS_OAM_NPN",1,"Rel-16","S5","2019-03-07","2020-06-12",1,"SP-190137",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com","31/5/19: 0%->2; 13/9/19: 2%->10; 26/3/20: 10%->70; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-06-28"]
[1893,0,"Cellular IoT support and evolution ","-",1,"Rel-16",null,"2016-06-18","2016-06-18",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1894,830043,"Cellular IoT support and evolution for the 5G System","5G_CIoT",1,"Rel-16",null,"2017-09-08","2020-06-12",1,"SP-181118",null,null,null,null,null,83,42,null,null,"2018-12-06","NA"]
[1895,770038,"   Study on 5G_CIoT","FS_CIoT_5G",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180614",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","11/09/17: rapporteur change¦15/12/17: 23.724 added;¦16/3/18: 0%->20¦7/6/18: 20%->50¦15/6/18: WID:SP-170801->SP-180614¦15/6/18: FCD:09/18->12/18¦10/9/18: 50%->70¦7/12/18: 70%->95; 31/5/19: 95%->100","New; 23.724",77,39,null,null,"2017-09-08","2019-05-31"]
[1896,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[1897,830013,"   CT aspects of 5G_CIoT","5G_CIoT",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 9/12/19: WID:CP-111237->CP-193274; 25/3/20: WID:CP-193274->CP-200147",null,83,42,null,null,"2018-12-06","2020-03-25"]
[1898,830038,"      CT1 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->40; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 40%->60; 6/12/19: 60%->85; 26/3/20: 85%->92; 26/6/20: 92%->99; 13/9/20: 99%->100","23.122; 24.250; 24.301; 24.368; 24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1899,830039,"      CT3 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100","29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514",83,42,null,null,"2018-12-06","2020-06-26"]
[1900,830040,"      CT4 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->10; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 10%->25; 6/12/19: 25%->60; 26/3/20: 60%->90; 26/6/20: 90%->100","23.008; 29.274; 29.502; 29.503; 29.505; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[1901,830041,"      CT6 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C6","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 26/3/20: 0%->100","TBD",83,42,null,null,"2018-12-06","2020-03-26"]
[1902,850014,"   Security of 5G_CIoT","5G_CIoT",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190897",null,"Henrik Normann, Ericsson ","henrik.normann@ericsson.com ","6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1903,800033,"Study on evolution of Cellular IoT security for the 5G System","FS_CIoT_sec_5G",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180440",null,"Noamen Ben Henda ","noamen.ben.henda@ericsson.com","6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100","New; 33.861",80,41,null,null,"2018-06-06","2020-06-26"]
[1904,760040,"Study on MBMS User Services for IoT","FS_MBMS_IoT",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170592",null,"Cedric thienot, Expway","cedric (dot) thienot (at) expway (dot) com","11/9/17: 0%->10¦15/12/17: 10%->30¦16/3/18: 30%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->90¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 90%->100","26.8xx",76,39,null,null,"2017-06-03","2018-09-10"]
[1905,800083,"Additional MTC enhancements for LTE","LTE_eMTC5",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦16/1/19: WID:RP-181450->RP-182891¦26/3/19: WID:RP-182891->RP-190770; 26/6/19: WID:RP-190770->RP-191356; 14/1/20: WID:RP-191356->RP-192875",null,80,41,null,null,"2018-06-27","2020-01-14"]
[1906,800183,"   Core part: Additional MTC enhancements for LTE","LTE_eMTC5-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1907,800283,"   Perf. part: Additional MTC enhancements for LTE","LTE_eMTC5-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"26/3/19: WID:RP-182891->RP-190770; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1908,800084,"Additional enhancements for NB-IoT","NB_IOTenh3",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293",null,80,41,null,null,"2018-06-27","2020-03-26"]
[1909,800184,"   Core part: Additional enhancements for NB-IoT","NB_IOTenh3-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦26/3/19: WID:RP-182902->RP-190757; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[1910,800284,"   Perf. part: Additional enhancements for NB-IoT","NB_IOTenh3-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"26/3/19: WID:RP-182902->RP-190757; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[1911,810050,"5G message service","5GMSG",1,"Rel-16","S1","2016-06-18","2018-12-14",1,"SP-180772",null,null,null,null,22.262,81,41,null,null,"2018-09-06","NA"]
[1912,770004,"   Study on 5G message service for MIoT","FS_5GMSG",2,"Rel-16","S1","2016-06-18","2018-09-14",1,"SP-170704",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","15/12/17: 22.824 added;¦15/12/17: 0%->25¦16/3/18: 25%->60¦10/9/18: 60%->95¦4/12/18: 95%->100","New; 22.824",77,39,null,null,"2017-09-08","2018-12-04"]
[1913,810014,"   Message Service Within the 5G System requirements ","MSGin5G",2,"Rel-16","S1","2018-09-06","2018-12-14",1,"SP-180920",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","4/12/18: 0%->100","22.262; 22.261",81,41,null,null,"2018-09-06","2021-06-11"]
[1914,0,"Advanced V2X support","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1915,790002,"Study on Improvement of V2X Service Handling ","FS_V2XIMP",1,"Rel-16","S1","2018-03-15","2018-06-14",1,"SP-180247",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100",22.885999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[1916,820024,"Improvement of V2X service Handling ","V2XIMP",1,"Rel-16","S1","2018-10-25","2018-12-04",1,"SP-181013",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","4/12/18: 0%->95¦14/3/19: 95%->100",22.186,82,42,null,null,"2018-12-04","2019-03-14"]
[1917,840074,"Application layer support for V2X services ","V2XAPP",1,"Rel-16",null,"2017-12-15","2020-03-12",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65","New",84,41,null,null,"2018-09-06","2019-03-14"]
[1918,780025,"   Study on V2XAPP","FS_V2XAPP",2,"Rel-16","S6","2017-12-15","2018-09-14",1,"SP-171071",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100",null,78,40,null,null,"2017-12-15","2018-12-07"]
[1919,810020,"   Stage 2 of V2XAPP","V2XAPP",2,"Rel-16","S6","2018-09-06","2019-06-14",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65; 31/5/19: 65%->95; 13/9/19: 95%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1920,840010,"   CT aspects of V2XAPP ","V2XAPP",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191153->CP-192077",null,84,43,null,null,"2019-05-31","2019-09-16"]
[1921,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[1922,840076,"      CT3 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->60; 26/3/20: 60%->100","29.122; 29.116",84,43,null,null,"2019-05-31","2020-03-26"]
[1923,840077,"      CT4 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100","23.003; 23.008",84,43,null,null,"2019-05-31","2020-03-26"]
[1924,840078,"Architecture enhancements for 3GPP support of advanced V2X services","eV2XARC",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30","23.501; 23.502; 23.503; 23.285",84,43,null,null,"2018-12-06","2019-03-14"]
[1925,760043,"   Study on eV2XARC","FS_eV2XARC",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180733","SP-170412","LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","11/9/17: 0%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170379->SP 170590¦16/3/18: 20%->25¦7/6/18: 25%->35¦10/9/18: 35%->58¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP 170590->SP-180733¦7/12/18: 58%->88¦14/3/19: 88%->95; 31/5/19: 95%->100",23.786000000000001,76,39,null,null,"2017-06-03","2019-05-31"]
[1926,820018,"   Stage 2 of eV2XARC","eV2XARC",2,"Rel-16","S2","2018-12-13","2019-06-14",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100","23.501; 23.502; 23.503; 23.285; 24.588",82,42,null,null,"2018-12-06","2020-03-25"]
[1927,840011,"   CT aspects of eV2XARC ","eV2XARC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","16/9/19: WID:CP-191154->CP-192078; 25/3/20: WID:CP-192078->CP-200291; 2/7/20: WID:CP-200291->CP-201343",null,84,43,null,null,"2019-05-31","2020-07-02"]
[{"$f":"A1928+1","v":1928},840079,"      CT1 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.501; 24.301; 27.007",84,43,null,null,"2019-05-31","2020-09-13"]
[1929,840080,"      CT3 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 26/3/20: 80%->90; 26/6/20: 90%->100; 26/6/20: WID:CP-200291->CP-201199","29.512; 29.513; 29.514; 29.519; 29.122; 29.522",84,43,null,null,"2019-05-31","2020-06-26"]
[1930,840081,"      CT4 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->95; 26/6/20: 95%->100","23.003; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571",84,43,null,null,"2019-05-31","2020-06-26"]
[1931,840082,"      CT6 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C6","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100",31.102,84,43,null,null,"2019-05-31","2020-03-26"]
[1932,860014,"   Security Aspects of eV2XARC","eV2XARC",2,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191125",null,"Dongjoo Kim, LG Electronics Inc. ","dongjoo7.kim@lge.com ","; 6/12/19: 0%->10; 25/3/20: 10%->70; 26/6/20: 70%->95; 12/9/20: 95%->98; 5/12/20: 98%->99; 19/3/21: 99%->100","33.220; TS 33.536",86,44,null,null,"2019-12-06","2021-03-19"]
[1933,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1934,770029,"Study on V2X Media Handling and Interaction","FS_mV2X",1,"Rel-16","S4","2017-09-08","2019-09-12",1,"SP-170799",null,"Jung, Kyunghun, Samsung Electronics Co., Ltd","kyunghun.jung@samsung.com","15/12/17: 26.985 added;¦15/12/17: 0%->30¦16/3/18: 30%->50¦22/3/18: FCD:09/18->12/18¦7/6/18: 50%->60. 14/06/18: Moved from Rel-15¦10/9/18: 60%->80¦13/12/18: 80%->60¦13/12/18: FCD:12/18->09/19¦12/3/19: 60%->70; 31/5/19: 70%->80; 26/6/20: 80%->100","New; 26.985",77,39,null,null,"2017-09-08","2020-06-26"]
[1935,830023,"Study on Security Aspects of 3GPP support for Advanced V2X Services ","FS_eV2X_Sec",1,"Rel-16","S3","2019-03-07","2020-03-12",1,"SP-190108",null,"Joonwoong Kim, LG Electronics","joonwoong.kim@lge.com","31/5/19: 0%->20; 13/9/19: 20%->60; 13/9/19: FCD:05/09/2019->12/20; 6/12/19: 60%->75; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 75%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[1936,830078,"5G V2X with NR sidelink","5G_V2X_NRSL",1,"Rel-16","R1","2019-03-01","2024-06-06",0.77,"RP-200129",null,"LG Electronics",null,"26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1937,830178,"   Core part: 5G V2X with NR sidelink","5G_V2X_NRSL-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-200129",null,"LG Electronics",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1938,830278,"   Perf. part: 5G V2X with NR sidelink","5G_V2X_NRSL-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200129",null,"LG Electronics",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1939,880069,"   UE Conformance Test Aspects - 5G V2X with NR sidelink","5G_V2X_NRSL_eV2XARC-UEConTest",2,"Rel-16","R5","2020-06-22","2024-06-06",0.63,"RP-200894","RP-233757","Xuesong Wang, Huawei Technologies. Co., Ltd","wangxuesong743@huawei.com","8/10/20: 0%->5; 8/4/21: 5%->11; 2/7/21: 11%->18; 22/3/22: Compl:18%->43%; ; 5/4/22: WID:RP-200894->RP-220744 20/6/22: Rapporteur: Huawei->Xuesong Wang, Huawei Technologies. Co., Ltd; Rap eMail: ->wangxuesong743@huawei.com12/7/22: WID:RP-20089...; 9/1...",null,88,45,null,null,"2020-07-28","2023-12-08"]
[1940,0,"5G Location and Positionning Services","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1941,800013,"5G positioning services","5G_HYPOS",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ",null,22.260999999999999,80,41,null,null,"2018-06-06","NA"]
[1942,760006,"   Study on positioning use cases","FS_5G_HYPOS",2,"Rel-16","S1","2017-06-05","2018-06-15",1,"SP-170589",null,"Ries, Lionel, ESA ","lionel.ries@esa.int","11/9/17: 0%->10¦15/12/17: 10%->50¦15/12/17: FCD:03/18->06/18¦16/3/18: 50%->75¦7/6/18: 75%->90¦10/9/18: 90%->100",22.872,76,39,null,null,"2017-06-03","2018-09-10"]
[1943,800049,"   Stage 1 of 5G_HYPOS","5G_HYPOS",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ","10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1944,830102,"Enhancement to the 5GC LoCation Services","5G_eLCS",1,"Rel-16",null,"2017-12-15","2020-06-12",0.98,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn",null,"23.501; 23.502",83,42,null,null,"2018-12-06","NA"]
[1945,780028,"   Study on Enhancement to the 5GC Location Services","FS_eLCS",2,"Rel-16","S2","2017-12-15","2019-03-14",1,"SP-180734",null,"Ming Ai, CATT","aiming@catt.cn","16/3/18: 0%->15¦7/6/18: 15%->45¦10/9/18: 45%->55¦10/9/18: FCD:12/18->03/19¦2/10/18: WID:SP-170937->SP-180734¦7/12/18: 55%->100","new 23.731",78,40,null,null,"2017-12-15","2018-12-07"]
[1946,810035,"   Study on Security of the enhancement to the 5GC location services","FS_eLCS_Sec",2,"Rel-16","S3","2018-09-06","2019-12-13",1,"SP-180694",null,"Wei Zhou, CATT","zhouwei@catt.cn","7/12/18: 0%->5¦20/3/19: 5%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[1947,820016,"   Stage 2 of 5G_eLCS","5G_eLCS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn","14/3/19: 0%->45; 31/5/19: 45%->85; 26/6/19: 29.515 added;; 13/9/19: 85%->100","23.501; 23.502; 29.515",82,42,null,null,"2018-12-06","2019-09-13"]
[1948,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",0.95,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1949,830044,"      CT1 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 13/9/19: 0%->40; 6/12/19: 40%->90; 26/6/20: 90%->99; 13/9/20: 99%->100","24.501; 27.007",83,42,null,null,"2018-12-06","2020-09-13"]
[1950,830045,"      CT3 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C3","2019-03-07","2019-12-05",0.85,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85","29.522; 29.122",83,42,null,null,"2018-12-06","2020-06-26"]
[1951,830046,"      CT4 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100","24.080; 29.518; 29.572; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-06-26"]
[1952,850017,"   Security of 5G_eLCS","5G_eLCS",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190900",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 6/12/19: 0%->75; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 75%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1953,830077,"NR positioning support","NR_pos",1,"Rel-16","R1","2018-06-15","2023-09-08",0.99,"RP-192581",null,"Intel",null,"26/6/19: WID:RP-190752->RP-191156; 14/1/20: WID:RP-191156->RP-192581",null,83,42,null,null,"2019-03-26","2020-01-14"]
[1954,800092,"   Study on NR positioning support","FS_NR_pos",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181399",null,"Intel",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[1955,830073,"   Study on local NR positioning in NG-RAN","FS_NR_local_pos",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-191774",null,"CMCC",null,"8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100",38.856000000000002,83,42,null,null,"2019-03-26","2020-01-14"]
[1956,830177,"   Core part: NR positioning support","NR_pos-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-192581",null,"Intel",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[1957,830277,"   Perf. part: NR positioning support","NR_pos-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-192581",null,"Intel",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[1958,900057,"   UE Conformance Test Aspects - NR positioning support ","NR_pos-UEConTest",2,"Rel-16","R5","2020-12-14","2023-09-08",1,"RP-212227","RP-231835","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5; 29/9/21: WID:RP-202727->RP-212227; 22/3/22: Compl:5%->54%; ; 20/6/22: Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn12/7/22: WID:RP-212227->RP-221450 ; ;...; 9/12/22: FCD:22/12...",null,90,46,null,null,"2021-01-06","2023-09-06"]
[1959,0,"UE radio capability signalling optimization","-",1,"Rel-16",null,"2018-06-06","2018-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1960,840054,"Optimisations on UE radio capability signalling","RACS",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"RP-191460",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","26/6/19: WID:SP-190180->RP-191460","23.501; 23.502; 23.401",84,43,null,null,"2019-03-14","2019-06-26"]
[1961,800025,"   Study on RACS","FS_RACS",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180599",null,"Haris Zisimopoulos, Qualcomm Incorporated ","harisz@qti.qualcomm.com","10/9/18: 0%->40¦7/12/18: 40%->70¦14/3/19: 70%->100","New",80,41,null,null,"2018-06-06","2019-03-14"]
[1962,830027,"   Stage 2 of RACS","RACS",2,"Rel-16","S2","2019-03-07","2019-06-06",1,"SP-190180",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","31/5/19: 0%->90; 26/6/19: 29.673 added;; 13/9/19: 90%->100","23.501; 23.502; 23.401; 29.673",83,42,null,null,"2019-03-14","2019-09-13"]
[1963,840003,"   CT aspects of RACS","RACS",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","17/9/19: WID:CP-191061->CP-192207; 25/3/20: WID:CP-192207->CP-200058",null,84,43,null,null,"2019-05-31","2020-03-25"]
[1964,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[1965,840056,"      CT3 aspects of RACS","RACS",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->90; 26/3/20: 90%->100","29.122; 29.522",84,43,null,null,"2019-05-31","2020-03-26"]
[1966,840057,"      CT4 aspects of RACS","RACS",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->20; 6/12/19: 20%->75; 26/3/20: 75%->90; 26/6/20: 90%->100","23.003; 23.008; 29.230; 29.274; 29.510; 29.518",84,43,null,null,"2019-05-31","2020-06-26"]
[1967,830079,"Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN",1,"Rel-16","R2","2018-06-15","2023-03-03",0.99,"RP-200164",null,"MediaTek",null,"26/3/20: WID:RP-190657->RP-200164",null,83,42,null,null,"2019-03-26","2020-03-26"]
[1968,800097,"   Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects","FS_RACS_RAN",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181459",null,"MediaTek",null,"TR 37.873¦related SA2 SI FS_RACS was started at SA #80 ¦6/8/18: 37.873 added;¦26/3/19: 0%->100",37.872999999999998,80,41,null,null,"2018-06-27","2019-03-26"]
[1969,830179,"   Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200164",null,"MediaTek",null,"26/6/19: WID:RP-190657->RP-191088; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[1970,880073,"   UE Conformance Test Aspects - Optimisations on UE radio capability signalling - NR/E-UTRA Aspects","RACS-UEConTest",2,"Rel-16","R5","2020-03-19","2023-03-03",1,"RP-201152","RP-230098","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 7/4/21: WID:RP-201153->RP-210714; 8/4/21: 5%->25; 8/4/21: FCD:19/03/2021->09/21; 2/7/21: 25%->50; 22/3/22: ; 5/4/22: WID:RP-210714->RP-220434 ; 9/12/22: Acronym:RACS-UEConTest->NG_RAN_PRN_Vertical_LAN-UEConTest; FCD:22/12/2022->01/03...",null,88,45,null,null,"2020-07-28","2023-03-17"]
[1971,800099,"Study on solutions for NR to support non-terrestrial networks (NTN)","FS_NR_NTN_solutions",1,"Rel-16","R3","2018-06-15","2019-12-13",1,"RP-190710",null,"Thales",null,"TR 38.xx1¦compare REL-15 SI FS_NR_nonterr_nw¦26/3/19: WID:RP-181370->RP-190710; 14/1/20: 0%->100",38.820999999999998,80,41,null,null,"2018-06-27","2023-03-17"]
[1972,0,"Enablers for Network Automation Architecture for 5G","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1973,830047,"Enablers for Network Automation for 5G ","eNA",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1974,760047,"   Study of enablers for Network Automation for 5G ","FS_eNA",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180792",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","16/3/18: FCD:09/18->06/18¦16/3/18: 0%->15¦7/6/18: 15%->30¦15/6/18: WID:SP-170383->SP-180613¦15/6/18: FCD:06/18->09/18¦10/9/18: 30%->50¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-180613->SP-180792¦7/12/18: 50%->90¦14/3/19: 90%->94; 31/5/19: 94%->100","new 23.791",76,39,null,null,"2017-06-03","2019-05-31"]
[1975,820020,"   Stage 2 of eNA","eNA",2,"Rel-16","S2","2018-12-06","2019-06-17",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 26/6/19: 29.517 added;; 13/9/19: 85%->92; 6/12/19: 92%->97; 25/3/20: 97%->100","23.501; 23.502; 23.503; 29.517",82,42,null,null,"2018-12-06","2020-03-25"]
[1976,830009,"   CT aspects of eNA","eNA",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259",null,83,42,null,null,"2018-12-06","2019-09-17"]
[1977,830048,"      CT3 aspects of eNA","eNA",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->55; 6/12/19: 55%->85; 6/12/19: FCD:05/12/2019->03/20; 26/3/20: 85%->100","29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[1978,830049,"      CT4 aspects of eNA","eNA",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100","29.244; 29.510; 29.518; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-03-26"]
[1979,0,"Wireless and Wireline Convergence Enhancement ","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1980,760044,"Study on the Wireless and Wireline Convergence for the 5G system architecture ","FS_5WWC",1,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-170380",null,"Marco Spini, Huawei Technologies","m.spini@huawei.com","11/9/17: 0%->15¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 15%->25¦7/6/18: 25%->35¦10/9/18: 35%->60¦10/9/18: FCD:06/18->12/18¦7/12/18: 60%->100",23.716000000000001,76,39,null,null,"2017-06-03","2018-12-07"]
[1981,800031,"Study on the security of the Wireless and Wireline Convergence for the 5G system architecture","FS_5WWC_SEC",1,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180438",null,"He Li, Huawei Technologies","LIHE2@HUAWEI.COM","6/8/18: 33.807 added;¦10/9/18: 0%->5¦7/12/18: 5%->30¦20/3/19: 30%->60¦20/3/19: FCD:019->09/19; 31/5/19: 60%->75; 8/10/19: 75%->100","New; 33.807",80,41,null,null,"2018-06-06","2019-10-08"]
[1982,830050,"Wireless and Wireline Convergence for the 5G system architecture","5WWC",1,"Rel-16",null,"2018-12-06","2020-06-12",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[1983,820014,"   Stage 2 of 5WWC","5WWC",2,"Rel-16","S2","2018-12-06","2019-06-13",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[1984,830015,"   CT aspects of 5WWC","5WWC",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156. Confusion with UID (was 829910 instead of 830015); 17/9/19: WID:CP-191156->CP-192079; 9/12/19: WID:CP-192079->CP-193145; 2/7/20: WID:CP-193145->CP-192079",null,83,42,null,null,"2018-12-06","2020-07-02"]
[1985,829911,"      CT1 aspects of 5WWC","5WWC",3,"Rel-16","C1","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100","24.501; 24.502; 24.526",82,42,null,null,"2018-12-06","2020-06-30"]
[1986,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[1987,829914,"      CT4 aspects of 5WWC","5WWC",3,"Rel-16","C4","2019-06-13","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 0%->5; 6/12/19: 5%->60; 26/3/20: 60%->95; 26/6/20: 95%->100","23.003; 29.518; 29.502; 29.509; 29.244; 29.503; 29.571; 29.505",82,42,null,null,"2018-12-06","2020-06-26"]
[1988,850015,"   Security of 5WWC","5WWC",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190898",null,"He Li, Huawei Technologies ","lihe2@huawei.com ","13/9/19: 0%->100; 8/10/19: 100%->0; 6/12/19: 0%->90; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 90%->95; 26/6/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[1989,860019,"   Charging Aspect for 5WWC ","5WWC",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191188",null,"ZHU, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","32.240; 32.255; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-06-28"]
[1990,830082,"   NG interface usage for WWC","5WWC-NG_interface",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190772",null,"Huawei",null,null,null,83,42,null,null,"2019-03-26","NA"]
[1991,830182,"      Core part: NG interface usage for WWC","5WWC-NG_interface-Core",3,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190999",null,"Huawei",null,"26/6/19: WID:RP-190772->RP-190999; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[{"$f":"A1992+1","v":1992},0,"Mission Critical, Public Warning, Railways and Maritime","-",1,"Rel-16",null,"2016-09-19","2016-09-19",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1993,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[1994,800024,"Study into discreet listening and logging for mission critical services","FS_MCLOG",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-181138",null,"Chater-Lea, David, Motorola Solutions","david.chater-lea@motorolasolutions.com","6/8/18: 23.784 added;¦10/9/18: 0%->10¦7/12/18: 10%->50¦7/12/18: FCD:03/19->06/19¦14/12/18: WID:SP-180384->SP-181138¦14/3/19: 50%->75; 31/5/19: 75%->100","New; 23.784",80,41,null,null,"2018-06-06","2019-05-31"]
[1995,800022,"Enhanced Mission Critical Push-to-talk architecture phase 2","enh2MCPTT",1,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[1996,860026,"   Stage 2 of enh2MCPTT ","enh2MCPTT",2,"Rel-16","S6","2019-12-06","2020-03-12",1,"SP-190068",null,"Dom Lazara; Motorola Solutions","Dom.Lazara@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->35¦14/3/19: 35%->60¦14/3/19: FCD:03/19->06/19¦21/3/19: WID:SP-180382->SP-190068; 31/5/19: 60%->100; 1/7/20: 0%->100","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2020-07-01"]
[1997,860003,"   CT aspects of enh2MCPTT ","enh2MCPTT-CT",2,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193148",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","; 26/3/20: 0%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484 ",86,44,null,null,"2019-12-06","2020-03-26"]
[1998,830051,"Enhancements to Functional architecture and information flows for Mission Critical Data","eMCData2",1,"Rel-16","S6","2018-06-06","2020-03-12",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40",null,83,42,null,null,"2018-06-06","2018-12-07"]
[1999,800018,"   Stage 2 of eMCData2","eMCData2",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40¦14/3/19: 40%->75; 31/5/19: 75%->90; 13/9/19: 90%->100","23.280; 23.282",80,41,null,null,"2018-06-06","2019-09-13"]
[2000,830014,"   CT aspects of eMCData2","eMCData2",2,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193146",null,"Val Oprescu (AT&T)","vo4887@att.com ","31/5/19: 0%->15; 13/9/19: 15%->25; 17/9/19: WID:CP-190199->CP-192081; 6/12/19: 25%->55; 9/12/19: FCD:12/12/2019->03/20; 9/12/19: WID:CP-192081->CP-193146; 26/3/20: 55%->70; 26/6/20: 70%->100","24.282; 24.582; 24.483; 24.484; 24.zzz",83,42,null,null,"2018-06-06","2020-06-26"]
[2004,810011,"Protocol enhancements for Mission Critical Services","MCProtoc16",1,"Rel-16","C1","2018-09-06","2019-12-20",1,"CP-182110",null,"AXELL, Jörgen","jorgen.axell@ericsson.com","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980",81,41,null,null,"2018-09-06","2020-03-26"]
[2007,760051,"   Study on MBMS APIs for MC Services","FS_MBMSAPI_MC",2,"Rel-16","S6","2017-06-05","2018-06-15",1,"SP-180237",null,"Ling Zhang, TD Tech Ltd","zhangling@td-tech.com","12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100","new 23.792",76,39,null,null,"2017-06-03","2018-06-14"]
[2011,850059,"   CT4 aspects of eNAPIs","eNAPIs",2,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[2014,800021,"   Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180680",null,"Monnes, Peter, Harris Corporation","pmonnes at harris dot com ","10/9/18: 0%->5¦2/10/18: WID:SP-180381->SP-180680¦7/12/18: 5%->15¦14/3/19: 15%->40; 31/5/19: 40%->70; 13/9/19: 70%->100",23.283000000000001,80,41,null,null,"2018-06-06","2019-09-13"]
[2017,780003,"Enhancements of Public Warning System ","ePWS",1,"Rel-16",null,"2016-09-19","2020-03-12",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[2018,730005,"   Study on enhancements of Public Warning System","FS_ePWS",2,"Rel-16","S1","2016-09-19","2017-09-14",1,"SP-160733",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->5¦2/3/17: 5%->45¦7/6/17: 45%->75¦30/6/17: 22.869 added;¦25/8/17: 75%->95¦15/12/17: 95%->100",22.869,73,37,null,null,"2016-09-19","2017-12-15"]
[2021,810053,"      Study on stages 2 and 3 of enhancements of ePWS","ePWS",3,"Rel-16","C1","2018-09-10","2019-06-14",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","7/12/18: 0%->10¦21/3/19: 10%->30; 31/5/19: 30%->85; 3/6/19: WID:CP-182228->CP-191155; 13/9/19: 85%->100","New",81,41,null,null,"2018-09-10","2019-09-13"]
[2025,760005,"   Study on MONASTERY2","FS_FRMCS2",2,"Rel-16","S1","2017-06-05","2019-06-14",1,"SP-170588",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 35%->50¦16/3/18: 50%->80¦7/6/18: 80%->85¦10/9/18: FCD:06/18->06/19¦4/12/18: 85%->100","New 22.889",76,39,null,null,"2017-06-03","2018-12-04"]
[2028,830007,"   Application Architecture for MONASTERY2","MONASTERY2",2,"Rel-16","S6","2019-03-14","2019-06-13",1,"SP-190064",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","31/5/19: 0%->100","23.280; 23.379; 23.281; 23.282",83,42,null,null,"2019-03-14","2019-05-31"]
[2031,840073,"      deleted: CT3 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","2/7/20: deleted, put at 100% (was at 0)",29.164999999999999,84,43,null,null,"2019-05-31","NA"]
[2035,900050,"   UE Conformance Test Aspects - NR support for high speed train scenario ","NR_HST-UEConTest",2,"Rel-16","R5","2020-12-14","2022-06-22",1,"RP-221362","RP-221361","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-16 WI NR_HST-Core ; 7/4/21: WID:RP-202328->RP-210372; 8/4/21: 0%->39; 2/7/21: 39%->41; 13/9/21: Compl:41%->44%; ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-202328->RP-221362",null,90,46,null,null,"2021-01-06","2022-07-12"]
[2038,800051,"   Stage 1 of MARCOM","MARCOM",2,"Rel-16","S1","2018-06-06","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com","10/9/18: 0%->70¦4/12/18: 70%->95¦14/3/19: 95%->100","22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","2019-03-14"]
[2041,740001,"   Study on eLSTR","FS_eLESTR",2,"Rel-16","S1","2016-12-01","2018-03-15",1,"SP-160960",null,"China Telecommunications, XIA Xu","xiaxu@ctbri.com.cn","2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100",22.832999999999998,74,38,null,null,"2016-12-01","2018-03-16"]
[2042,800054,"   Stage 1 of eLSTR","eLSTR",2,"Rel-16","S1","2018-05-08","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn","15/6/18: FCD:06/18->09/18¦10/9/18: 90%->100","22.278; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[2045,770027,"Study on QoE metrics for VR","FS_QoE_VR",1,"Rel-16","S4","2017-09-08","2019-09-20",1,"SP-170614",null,"Ericsson (Gunnar Heikkilä","gunnar.heikkila@ericsson.com","15/12/17: 26.929 added;¦15/12/17: 26.119 added;¦15/12/17: FCD:06/18->09/18¦15/12/17: 0%->10¦16/3/18: 10%->15¦7/6/18: 15%->20¦7/6/18: FCD:09/18->12/18. 14/06/18: Moved from Rel-15¦10/9/18: 20%->25¦12/3/19: 25%->55¦12/3/19: FCD:12/18->09/19; 31/5/19: 55% ","New; 26.929; 26.119",77,39,null,null,"2017-09-08","2019-05-31"]
[2049,810040,"Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",1,"Rel-16","S4","2017-06-05","2019-12-12",1,"SP-180663",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[2052,770031,"Study on EVS Float Conformance Non Bit-Exact","FS_EVS_FCNBE",1,"Rel-16","S4","2017-09-08","2018-09-14",1,"SP-170618",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100","New; 26.843",77,39,null,null,"2017-09-08","2018-09-10"]
[2055,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2059,810044,"Multi-device and multi-identity","MuD",1,"Rel-16",null,"2018-06-06","2020-06-15",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com",null,null,80,41,null,null,"2018-06-06","NA"]
[2061,810010,"   CT aspects of Multi-device and multi-identity","MuD",2,"Rel-16","ct","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","9/12/19: WID:CP-182227->CP-193273; 25/3/20: WID:CP-193273->CP-200148",null,81,41,null,null,"2018-06-06","2020-03-25"]
[2064,0,"Slicing","-",1,"Rel-16",null,"2017-09-08","2017-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2067,820023,"   Stage 2 of eNS","eNS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com","14/3/19: 0%->60; 31/5/19: 60%->100",null,82,42,null,null,"2018-12-06","2019-05-31"]
[2070,830053,"      CT3 aspects of eNS","eNS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","6/12/19: 0%->80; 26/3/20: 80%->98; 26/6/20: 98%->100","29.061; 29.561",83,42,null,null,"2018-12-06","2020-06-26"]
[2074,910099,"   UE Conformance Test Aspects - Enhancement of Network Slicing ","eNS-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-12",0.67,"RP-211443","R5-220262","CMCC ",null,"tested: CT1 and SA3 REL-16 WI eNS (Enhancement of Network Slicing); compare REL-17 SI FS_NR_slice; 2/7/21: 0%->15; 13/9/21: Compl:15%->47%; ; 6/1/22: 47%->100 ; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[2077,810015,"   Business Role Models for Network Slicing ","BRMNS",2,"Rel-16","S1","2018-09-06","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","10/9/18: 0%->95¦4/12/18: 95%->100",22.260999999999999,81,41,null,null,"2018-09-06","2018-12-04"]
[2080,850055,"   Overall aspects of 5G_SLICE_ePA","5G_SLICE_ePA",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70; 13/9/19: 70%->85; 13/9/19: 85%->; 26/3/20: 85%->97; 28/6/20: 97%->100","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2020-06-28"]
[2084,760003,"Provision of Access to Restricted Local Operator Services by Unauthenticated UEs","PARLOS",1,"Rel-16",null,"2016-12-01","2019-12-13",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16","22.115; 22.101; 22.228",76,38,null,null,"2017-06-03","2017-06-07"]
[2087,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[2088,760071,"   Stage 1 of PARLOS","PARLOS",2,"Rel-16","S1","2017-05-10","2017-06-08",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","7/6/17: 0%->100","22.115; 22.101; 22.228",76,39,null,null,"2017-06-03","2017-06-07"]
[2091,830062,"      CT1 aspects of PARLOS","PARLOS",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->80; 13/9/19: 80%->95; 6/12/19: 95%->98; 26/3/20: 98%->100","24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007",83,42,null,null,"2018-09-06","2020-03-26"]
[2094,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[2098,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[2101,830056,"      CT4 aspects of ETSUN","ETSUN",3,"Rel-16","C4","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","31/5/19: 0%->25; 13/9/19: 25%->95; 6/12/19: 95%->100","29.244; 29.502; 29.510; 29.518; 29.281",83,42,null,null,"2018-12-05","2019-12-06"]
[2104,760052,"   Study on ATSSS","FS_ATSSS",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180732",null,"So, Tricci, ZTE","tso@ztetx.com","11/9/17: 0%->100¦14/9/17: 100%->10¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 10%->20¦7/6/18: 20%->40¦10/9/18: 40%->70¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170411->SP-180732¦2/10/18: FCD:12/18->12/18¦7/12/18: 70%->100","new 23.793",76,39,null,null,"2017-06-03","2018-12-07"]
[2108,830058,"      CT3 aspects of ATSSS","ATSSS",3,"Rel-16","C3","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->50; 13/9/19: 50%->55; 6/12/19: 55%->60; 26/3/20: 60%->100","29.512; 29.513",83,42,null,null,"2018-12-06","2020-03-26"]
[2111,840998,"      (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,null,null,null,null,"23/4/20: 30%->90; 25/9/20: 90%->100; 9/4/21: RFC 8803 added;","RFC 8803",84,43,null,null,"2019-06-26","2021-04-09"]
[2112,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[2115,790010,"   Study for single radio voice continuity from 5GS to 3G","FS_5G-SRVCC",2,"Rel-16","S2","2018-03-15","2018-06-15",1,"SP-180239",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","7/6/18: 0%->80¦6/8/18: 23.756 added;¦10/9/18: 80%->100",23.756,79,40,null,null,"2018-03-15","2018-09-10"]
[2118,820069,"   RAN aspects of 5G_SRVCC","SRVCC_NR_to_UMTS",2,"Rel-16","R2","2018-12-15","2019-12-15",1,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: WID:RP-190713->RP-200151",null,82,42,null,null,"2019-01-16","2020-03-26"]
[2122,840004,"   CT aspect of 5G_SRVCC","5G_SRVCC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","6/12/19: WID:CP-191062->CP-193014",null,84,43,null,null,"2019-05-31","2019-12-06"]
[2126,790005,"Study on Remote Identification of Uncrewed Aerial Systems","FS_ID_UAS",1,"Rel-16","S1","2018-03-15","2018-09-14",1,"SP-180172",null,"Eddy Hall; Qualcomm Incorporated","edhall@qti.qualcomm.com","7/6/18: 0%->60¦10/9/18: 60%->100",22.824999999999999,79,40,null,null,"2018-03-15","2018-09-10"]
[2130,820022,"   Stage 2 of 5G_eSBA","5G_eSBA",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181125",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2133,830061,"      CT4 aspects of 5G_eSBA","5G_eSBA",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com","31/5/19: 0%->10; 13/9/19: 10%->40; 6/12/19: 40%->70; 26/3/20: 70%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.518; 29.531; 29.540; 29.571; 29.572; 29.573",83,42,null,null,"2018-12-06","2020-06-26"]
[2136,840062,"SBA aspects of enhanced IMS to 5GC integration","eIMS5G_SBA",1,"Rel-16",null,"2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,null,"23.501; 23.502; 23.503; 23.228",84,42,null,null,"2019-03-14","NA"]
[2137,830028,"   Stage 2 of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","S2","2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,"31/5/19: 0%->100","23.501; 23.502; 23.503; 23.228",83,42,null,null,"2019-03-14","2019-05-31"]
[2140,840063,"      CT3 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.513; 29.514",84,43,null,null,"2019-05-31","2020-03-26"]
[2143,830181,"   Core part: Private Network Support for NG-RAN","NG_RAN_PRN-Core",2,"Rel-16","R3","2019-03-01","2020-02-28",1,"RP-200122",null,"China Telecom",null,"26/6/19: WID:RP-190729->RP-191563; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2147,810001,"   Stage 2 of E2E_DELAY","E2E_DELAY",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180662",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->75¦7/3/19: 75%->85¦7/3/19: FCD:03/19->06/19; 31/5/19: 85%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-05-31"]
[2150,830067,"      CT3 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100",29.161999999999999,83,42,null,null,"2018-09-06","2019-05-31"]
[2154,830022,"   Security aspects of eCAPIF","eCAPIF",2,"Rel-16","S3","2019-03-07","2019-12-12",1,"SP-1901240",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","31/5/19: 0%->30; 31/5/19: 0%->30; 31/5/19: 0%->30; 13/9/19: 30%->90; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 90%->100",33.122,83,42,null,null,"2019-03-14","2019-12-06"]
[2157,800055,"   Study on UDICOM","FS_UDICoM",2,"Rel-16","S2","2018-06-15","2019-06-12",1,"SP-190148",null,"Susana Sabater (Vodafone","susana.sabater@vodafone.com","10/9/18: 0%->30¦2/10/18: WID:SP-180620->SP-180735¦7/12/18: 30%->80¦14/12/18: FCD:12/18->03/20¦14/3/19: 80%->100¦21/3/19: WID:SP-181110->SP-190148¦21/3/19: FCD:019->06/19; 13/9/19: 75%->100","23.732; new",80,41,null,null,"2018-06-15","2019-09-13"]
[2160,910008,"UICC-terminal interface testing for UEs with non-removable UICCs ","nrUICC_UEConTest",1,"Rel-16","C6","2021-03-18","2022-03-10",0.8,"CP-210285",null,"Marquordt, Arne, COMPRION GmbH ","amarquordt@comprion.com ","; 21/3/21: 0%->5; 13/9/21: 5%->10; 13/9/21: FCD:Fri 10/12/->03/22; 4/6/22: 10%->15; 6/6/23: Compl:45%->60%","31.122; 31.213 ",91,46,null,null,"2021-03-18","2023-06-06"]
[2161,800036,"Study on authentication and key management for applications based on 3GPP credential in 5G","FS_AKMA",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180443",null,"Jin Peng, China Mobile","pengjin@chinamobile.com","6/8/18: 33.835 added;¦7/12/18: 5%->20¦20/3/19: 20%->60¦20/3/19: FCD:019->09/19; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->12/19; 6/12/19: 70%->95; 26/6/20: 95%->100","New; 33.835",80,41,null,null,"2018-06-06","2020-06-26"]
[2164,860058,"Addition of wider channel bandwidth in NR band n3","NR_n3_BW",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 26/3/20: WID:RP-193056->RP-200305",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2168,860159,"   Core part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2171,800094,"   Study on UE power saving in NR","FS_NR_UE_pow_sav",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-181463",null,"CATT",null,"TR 38.8xx; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2174,800072,"Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 26/6/19: WID:RP-1907 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2178,800073,"   Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦16/1/19: WID:RP-181426->RP-182256¦26/3/19: WID:RP-182256->RP-190689; 26/6/19: WID:RP-190689->RP-191194; 8/10/19: WID:RP-191194->RP-191812; 14/1/20: WID:RP-191812->RP-192445; 26/3/20: WID:RP-192445->RP-200101; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2181,800074,"   Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦16/1/19: WID:RP-180817->RP-182501¦26/3/19: WID:RP-182501->RP-190494; 26/6/19: WID:RP-190494->RP-191565; 8/10/19: WID:RP-191565->RP-191822; 14/1/20: WID:RP-191822->RP-192615; 26/3/20: WID:RP-192615->RP-200168; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2183,800274,"      Perf. part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2186,830095,"   Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200918",null,"CATT",null,"26/6/19: WID:RP-190692->RP-191153; 8/10/19: WID:RP-191153->RP-192245; 14/1/20: WID:RP-192245->RP-193206; 26/3/20: WID:RP-193206->RP-200238; 28/7/20: WID:RP-200238->RP-200918",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2189,830096,"   Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"26/6/19: WID:RP-190693->RP-191566; 8/10/19: WID:RP-191566->RP-191824; 14/1/20: WID:RP-191824->RP-192617; 26/3/20: WID:RP-192617->RP-200171; 28/7/20: WID:RP-200171->RP-200673",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2193,850062,"   UE Conformance Test Aspects for new Rel-16 NR bands and extension of existing NR bands","NR_bands_BW_R16-UEConTest",2,"Rel-16","R5","2019-09-19","2022-12-01",1,"RP-200146","RP-222816","Leif MATTISSON, Ericsson","Leif[dot]mattisson[at]ericsson[dot]com","testing all new NR band(s) and NR channel bandwidth addition Wis of REL-16; 14/1/20: WID:RP-192128->RP-192893; 26/3/20: WID:RP-192893->RP-200146; 28/7/20: WID:RP-200146->RP-200633; 8/10/20: 0%->47; 8/10/20: FCD:15/06/2020->12/20; 8/4/21: 47%->67; 8/4/2...",null,85,43,null,null,"2019-10-08","2023-01-09"]
[2196,800277,"      Perf. part: Band 65 for New Radio","NR_band_n65-Perf",3,"Rel-16","R4","2018-06-15","2018-12-14",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2199,820273,"      Perf. part: Introduction of NR band n18","NR_n18-Perf",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2203,830090,"   Introduction of NR band n14","NR_n14",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190965",null,"AT&T",null,"26/6/19: WID:RP-190165->RP-190965",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2206,830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2209,830097,"   Introduction of NR band n259","NR_n259",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-200249",null,"Ericsson",null,"26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2210,830197,"      Core part: Introduction of NR band n259","NR_n259-Core",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2213,850167,"      Core part: Introduction of NR band n26","NR_n26-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2217,840297,"      Perf. part: Introduction of NR supplementary DL band n29","NR_n29-Perf",3,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: 0%->100",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2220,850268,"      Perf. part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2223,860256,"      Perf. part: Introduction of band n53","NR_n53-Perf",3,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2227,830287,"      Perf. Part: RF requirements for NR FR1","NR_RF_FR1-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193266",null,"Huawei",null,"6/1/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-01-06"]
[2230,830188,"      Core part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200124",null,"China Telecom",null,"8/10/19: 38.883 added;; 28/7/20: 0%->100",38.883000000000003,83,42,null,null,"2019-03-26","2020-07-28"]
[2231,830288,"      Perf. part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Perf",3,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200124",null,"China Telecom",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[2234,830189,"      Core part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200668",null,"Nokia",null,"8/10/19: 38.831 added;; 25/9/20: 0%->100",38.831000000000003,83,42,null,null,"2019-03-26","2020-09-25"]
[2237,830092,"   Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5","NR_SUL_UL_n5",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2241,820174,"      Core part: Adding wider channel bandwidths in NR band n7","NR_n7_BW-Core",3,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2244,830293,"      Perf. part: Addition of wider channel bandwidth in NR band n38","NR_n38_BW-Perf",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191472",null,"Huawei",null,"14/1/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-01-14"]
[{"$f":"A2248+1","v":2248},820075,"   Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 26/6/19: WID:RP-190174->RP-191569; 8/10/19: WID:RP-191569->RP-191681",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2252,820176,"      Core part: Adding wider channel bandwidths in NR band n50","NR_n50_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2255,850264,"      Perf. part: Addition of wider channel bandwidths in NR band n75","NR_n75_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192216",null,"Ericsson",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2256,850065,"   Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: WID:RP-192219->RP-192401",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2259,850066,"   Addition of wider channel bandwidths in NR band n28","NR_n28_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"14/1/20: WID:RP-192261->RP-192656",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2262,850069,"   Addition of new channel bandwidth in NR band n1","NR_n1_BW2",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192801",null,"China Unicom",null,"8/10/19: WID:RP-192275->RP-192009. compare REL-16 WI NR_n1_BW; 14/1/20: WID:RP-192275->RP-192801",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2266,850170,"      Core part: Addition of asymmetric channel bandwidth for NR band n66","NR_n66_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-201010",null,"Huawei",null,"28/7/20: WID:RP-200265->RP-201010; 28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[2269,800285,"   Perf. part: Enhancements on MIMO for NR","NR_eMIMO-Perf",2,"Rel-16","R4","2018-06-15","2020-09-15",1,"RP-200474",null,"Samsung",null,"7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[2272,800187,"   Core part: NR mobility enhancements","NR_Mob_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2276,820168,"   Core part: 2-step RACH for NR","NR_2step_RACH-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 28/7/20: 0%->100; 28/7/20: 100%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[2279,840091,"SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR","NR_SON_MDT",1,"Rel-16","R3","2019-06-17","2022-06-22",1,"RP-191594",null,"CMCC",null,"no Perf. part; impact on SA2, SA5, CT4?; TR 38.314",null,84,43,null,null,"2019-06-26","NA"]
[2280,840191,"   Core part: SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR","NR_SON_MDT-Core",2,"Rel-16","R3","2019-06-17","2020-03-13",1,"RP-192610",null,"CMCC",null,"no Perf. part; impact on SA2, SA5, CT4?; TR 38.314; 8/10/19: WID:RP-191594->RP-191776; 8/10/19: 38.314 added;; 14/1/20: WID:RP-191776->RP-192610; 28/7/20: 0%->100",38.314,84,43,null,null,"2019-06-26","2020-07-28"]
[2283,850030,"Self-Organizing Networks (SON) for 5G networks ","SON_5G",1,"Rel-16","S5","2019-09-19","2020-09-14",1,"SP-200763",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/19: 0%->80; 8/10/19: 28.544 added;; 8/10/19: 28.313 added;; 28/6/20: 80%->75; 13/9/20: 75%->100; 13/9/20: WID:SP-190785->SP-200763; 13/9/20: FCD:12/03/2020->09/20","28.552; 28.545 ; 28.544; 28.313",85,43,null,null,"2019-09-13","2020-09-13"]
[2286,840293,"   Perf. part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Perf",2,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"2/7/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-07-02"]
[2290,840095,"NR RRM enhancement","NR_RRM_enh",1,"Rel-16","R4","2019-06-17","2024-06-06",0.73,"RP-201883",null,"Intel",null,"8/10/19: WID:RP-191601->RP-192157; 14/1/20: WID:RP-192157->RP-193211; 26/3/20: WID:RP-193211->RP-200256; 28/7/20: WID:RP-200256->RP-201112; 25/9/20: WID:RP-201112->RP-201883",null,84,43,null,null,"2019-06-26","2020-09-25"]
[2293,960089,"   UE Conformance Test Aspects - NR RRM enhancements ","NR_RRM_enh-UEConTest",2,"Rel-16","R5","2022-06-15","2024-06-06",0.5,"RP-233858","RP-233867","Xinrong Wang, Apple","xinrong_wang@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->9%; Stat Rep: ->RP-222901; Rapporteur: Apple->Ashwin Mohan, Apple; Rap eMail: ->ashwin_mohan[at]apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:9%->12%; Stat Rep: RP-22.....",null,96,49,null,null,"2022-07-12","2024-01-02"]
[2297,840098,"Addition of wider channel bandwidth in NR band n1","NR_n1_BW",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-192009",null,"Ericsson",null,"8/10/19: WID:RP-191595->RP-192009",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2300,840099,"Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-191606",null,"Huawei",null,"no Perf. part",null,84,43,null,null,"2019-06-26","NA"]
[2303,841100,"   Core part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2304,841200,"   Perf. part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2309,841102,"   Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-Core",2,"Rel-16","R4","2019-07-31","2020-03-12",0,"RP-192093",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093",null,84,43,null,null,"2019-07-31","2019-10-08"]
[2311,880074,"Addition of NR UE measurements to enable OTA conformance testing","NR_OTA_Uemeas",1,"Rel-16","R1","2020-06-22","2020-07-28",1,"RP-200824",null,"Keysight Technologies",null,null,null,88,45,null,null,"2020-07-28","NA"]
[2315,860254,"   Perf. Part: Over the air (OTA) base station (BS) testing TR","OTA_BS_testing-Perf",2,"Rel-16","R4","2019-03-07","2019-06-05",1,"RP-201021",null,"Huawei",null,"affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16; 26/3/20: WID:RP-193225->RP-200276; 28/7/20: WID:RP-200276->RP-201021; 25/9/20: 37.941 added;; 6/1/21: 0%->100",37.941000000000003,86,44,null,null,"2020-01-14","2021-01-06"]
[2318,890044,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) ","ENDC_UE_PC2_FDD_TDD-UEConTest",2,"Rel-16","R5","2020-09-17","2021-12-17",1,"RP-212501",null,"China Unicom ",null,"tested: REL-16 WI ENDC_UE_PC2_FDD_TDD-Core ; 8/4/21: 0%->78; 29/9/21: WID:RP-201776->RP-212501; 29/9/21: 78%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[2322,860060,"LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 26/3/20: WID:RP-193213->RP-200234; 28/7/20: WID:RP-200234->RP-201359; 25/9/20: WID:RP-201359->RP-201858",null,86,44,null,null,"2020-01-14","2020-09-25"]
[2325,800188,"   Core part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements","LTE_NR_DC_CA_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[2328,820079,"High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD",1,"Rel-16","R4","2018-12-13","2020-03-18",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2329,820061,"   Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","FS_ENDC_UE_PC2_FDD_TDD",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-192268",null,"China Unicom",null,"EN-DC = E-UTRA-NR Dual Connectivity¦TR 37.8xx¦26/3/19: WID:RP-182895->RP-190167; 8/10/19: WID:RP-190167->RP-192268; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[2332,870062,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-UEConTest",2,"Rel-16","R5","2019-03-07","2020-03-18",1,"RP-202066",null,"CMCC",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200434->RP-200761; 25/9/20: WID:RP-200761->RP-202066; 25/9/20: 0%->100",null,87,44,null,null,"2020-01-14","2020-09-25"]
[2336,820180,"   Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex-Core",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-190175",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2339,920068,"   UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41 and NR Band n41 ","LTE_NR_B41_Bn41_PC29dBm-UEConTest",2,"Rel-16","R5","2021-06-15","2022-12-01",1,"RP-211443","RP-223059","Dan SONG, CMCC, T-Mobile","songdan@chinamobile.com","tested: REL-17 WI LTE_NR_B41_Bn41_PC29dBm-Core ; 5/4/22: WID:RP-211443->RP-220124 6/6/22: C ; 20/6/22: Stat Rep: R5-222679->RP-221180 / R5-222679; Rapporteur: T-Mobile USA->Scott Probasco, Dan SONG, T-Mobile, CMCC; Rap eMail: ->scott.probasco@t-mobile....",null,92,47,null,null,"2021-07-02","2023-01-09"]
[2342,800166,"      Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2346,800267,"      Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2349,800268,"      Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200657",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2352,800269,"      Perf. part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2353,800070,"   Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01",null,80,41,null,null,"2018-06-27","NA"]
[2356,800071,"   Dual Connectivity (EN-DC) of x bands (x=1, 2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦16/1/19: WID:RP-180777->RP-182302, \"x=1\" added¦26/3/19: WID:RP-182302->RP-190151; 26/6/19: WID:RP-190151->RP-190949; 8/10/19: WID:RP-190949->RP-191744; 14/1/20: WID:RP-191744->RP-192592; 26/3/20: WID:RP-192592->RP-200080; 28/7 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2360,790057,"E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US",1,"Rel-16","R4","2018-03-15","2019-06-18",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: WID:RP-180583->RP-182405",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[2363,820063,"   UE Conformance Test Aspects - E-UTRA 2.4 GHz TDD Band for US (Band 53)","LTE_TDD_2400_US-UEConTest",2,"Rel-15","R5","2018-12-13","2019-06-18",1,"RP-182406",null,"Globalstar",null,"tested: REL-15 WI LTE_TDD_2400_US-Core; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2366,800160,"      Core part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦TR 36.716-01-01¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2370,800261,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2374,800063,"   Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201238",null,"Nokia",null,"basket WI¦TR 36.716-04-01¦16/1/19: WID:RP-181408->RP-182330¦26/3/19: WID:RP-182330->RP-190138; 26/6/19: WID:RP-190138->RP-190906; 8/10/19: WID:RP-190906->RP-191730; 14/1/20: WID:RP-191730->RP-192423; 26/3/20: WID:RP-192423->RP-200157; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2377,800064,"   Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2378,800164,"      Core part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2381,800165,"      Core part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200740",null,"LG Electronics",null,"basket WI¦TR 36.716-00-02¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2385,800091,"   Study on LTE-based 5G terrestrial broadcast","FS_LTE_terr_bcast",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181342",null,"Qualcomm",null,"TR 36.7xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2388,830094,"Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72",1,"Rel-16","R4","2019-03-01","2020-09-11",1,"RP-191285",null,"Nokia",null,"26/6/19: WID:RP-190665->RP-191285",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2391,860030,"   UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-UEConTest",2,"Rel-16","R5","2019-12-16","2020-09-11",1,"RP-192506",null,"Airbus",null,"affects: LTE. tested: REL-16 WI LTE_PC2_B31_B72-Core; 25/9/20: 0%->100; 8/10/20: FCD:15/03/2020->09/20",null,86,44,null,null,"2020-01-14","2020-10-08"]
[2395,800275,"      Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2398,800176,"      Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201201",null,"Ericsson",null,"basket WI¦no Perf. part¦26/3/19: WID:RP-182769->RP-190333; 28/7/20: WID:RP-200154->RP-201201; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2399,900053,"      UE Conformance Test Aspects - Additional LTE bands for UE category M2 and/or NB2 in Rel-16 ","LTE_bands_R16_M2_NB2-UEConTest",3,"Rel-16","R5","2020-12-14","2021-09-08",1,"RP-202523",null,"Ericsson ",null,"tested: REL-16 WI LTE_bands_R16_M2_NB2-Core ; 8/4/21: 0%->33; 2/7/21: 33%->59",null,90,46,null,null,"2021-01-06","2021-07-02"]
[2402,800279,"   Perf. part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2405,800282,"   Perf. part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Perf",2,"Rel-16","R4","2018-06-15","2019-06-14",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2409,800286,"   Perf. part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2412,820072,"Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility","Direct_data_fw_NR",1,"Rel-16","R3","2018-12-13","2019-06-18",1,"RP-182886",null,"Ericsson",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[2415,800189,"   Core part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2419,820178,"   Core part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR-Core",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-182898",null,"Nokia",null,"26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2422,850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2423,850172,"   Core part: Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC-Core",2,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2426,840001,"5G Media Streaming stage 3 ","5GMS3",1,"Rel-16","S4","2019-06-06","2020-09-15",1,"SP-190464",null,"Paul Szucs, Sony","Paul.Szucs@Sony.com","13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->70; 25/3/20: FCD:12/03/2020->06/20; 10/6/20: 70%->85; 26/6/20: FCD:12/06/2020->09/20; 12/9/20: 85%->100. Moved to Rel-16","26.234; 26.247; 26.117; 26.502; 26.503; 26.504; 26.511; 26.512",84,43,null,null,"2019-05-31","2020-09-12"]
[2431,830286,"   Perf. Part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Perf",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2434,840012,"   CT aspects of VBCLTE","VBCLTE",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-191110",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ",null,null,84,43,null,null,"2019-05-31","NA"]
[2437,820070,"Integrated access and backhaul for NR","NR_IAB",1,"Rel-16",null,"2017-03-15","2020-06-12",1,"RP-210442",null,"Qualcomm",null,"follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 26/6/19: WID:RP-190712->RP-191558; 8/10/19: WID:RP-191558->RP-192188; 14/1/20: WID:RP-192188->RP-193226; 26/3/20: WID:RP-193226->RP-200084; 28/7/20: WID:RP-200084->RP-200840; 25/9/2 ",38.808999999999997,82,42,null,null,"2019-01-16","2021-04-07"]
[2441,850002,"      CT4 aspects of IABARC ","IABARC",3,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP201074",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: WID:CP-193015->CP 201074","24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 ",85,43,null,null,"2019-09-13","2020-07-02"]
[2444,820270,"   Perf. Part: NR_IAB","NR_IAB-Perf",2,"Rel-16","R4","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added;; 2/7/21: 0%->100","38.809; 38.176-1; 38.176-2",82,42,null,null,"2019-01-16","2021-07-02"]
[2447,790003,"Enhancements to IMS for new real time communication services","enIMS",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180137",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","7/6/18: 0%->25¦10/9/18: 25%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100","22.261; 22.468; 22.228; 22.280; 22.281; 22.282; 22.179",79,40,null,null,"2018-03-15","2018-12-04"]
[2448,820028,"Enhancement of 5G PCC related services ","en5GPccSer",1,"Rel-16","C3","2018-12-13","2019-12-19",1,"CP-183246",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","¦14/3/19: 0%->10; 31/5/19: 10%->60; 13/9/19: 60%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 ",82,42,null,null,"2018-12-07","2020-03-26"]
[2451,790001,"New Services and Markets Technology Enablers – Phase 2 ","SMARTER_Ph2",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180589",null,"Li, Alice, Vodafone","alice.li@vodafone.com","7/6/18: WID:SP-180138->SP-180313¦7/6/18: 0%->10¦10/9/18: 10%->40¦4/12/18: 40%->100","22.261; 22.278",79,40,null,null,"2018-03-15","2018-12-04"]
[2454,840069,"5GS Transfer of Policies for Background Data Transfer","xBDT",1,"Rel-16",null,"2019-03-07","2020-03-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com",null,"23.501; 23.502; 23.503",84,43,null,null,"2018-06-06","NA"]
[2458,840071,"      CT3 aspects of xBDT","xBDT",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","13/9/19: 0%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","29.519; 29.513; 29.514; 29.122; 29.522; 29.525",84,43,null,null,"2019-05-31","2020-03-26"]
[2461,800002,"Alternative EVS implementation using updated fixed-point basic operators","Alt_FX_EVS",1,"Rel-16","S4","2018-06-06","2018-12-14",1,"SP-180286",null,"Pawate, Raj, Cadence Design Systems Inc","pawateb@cadence.com","6/8/18: 26.452 added;¦10/9/18: 0%->20¦7/12/18: 20%->90¦7/3/19: 90%->100","26.441; 26.442; 26.444; 26.445; 26.446; 26.447; 26.449; 26.450; 26.451; 26.952; 26.452",80,41,null,null,"2018-06-06","2019-03-07"]
[2465,790004,"QoS Monitoring ","QoS_MON",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180141",null,"Amar Deol ","amar.deol@huawei.com","7/6/18: 0%->60¦10/9/18: 60%->85¦10/9/18: FCD:06/18->12/18¦4/12/18: 85%->100",22.260999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[2468,760059,"Study on network policy management for mobile networks based on NFV scenarios","FS_NETPOL",1,"Rel-15","S5","2017-06-05","2018-06-14",1,"SP-170593",null,"China Mobile Jinglei Liu ","liujinglei@chinamobile.com","30/6/17: 32.871 added;¦11/9/17: 0%->20¦15/12/17: 20%->30¦16/3/18: 30%->35¦7/6/18: 35%->100","new; 32.871",76,39,null,null,"2017-06-05","2018-06-07"]
[2471,810026,"Methodology for 5G management specifications","METHOGY",1,"Rel-16","S5","2018-09-06","2019-03-15",1,"SP-180822",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com","7/12/18: 0%->60¦14/3/19: 60%->85; 13/9/19: 85%->100","New; 32.156",81,41,null,null,"2018-09-06","2019-09-13"]
[2472,820030,"Nchf Online and Offline charging services ","OFSBI_CH",1,"Rel-16","S5","2018-12-13","2019-09-19",1,"SP-181066",null,"Zhu Lei, Huawei","Zhulei@huawei.com ","¦14/3/19: 0%->40; 31/5/19: 40%->70; 13/9/19: 70%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-09-13"]
[2475,820033,"Network Exposure Charging in 5G System Architecture ","5GS_Ph1_NEFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181070",null,"Tornkvist, Robert, Ericsson ","robert(dot)tornkvist(at)Ericsson(dot)com ","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100","32.240; 32.254; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-12-06"]
[2478,820005,"Lawful Interception Rel-16 ","LI16",1,"Rel-16","S3LI","2018-12-13","2021-06-11",1,"SP-181210",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ","31/5/19: 0%->15; 13/9/19: 15%->40; 6/12/19: 40%->55; 25/3/20: 55%->60; 25/3/20: FCD:19/12/2019->03/20; 26/6/20: FCD:13/03/2020->09/20; 26/6/20: 60%->85; 12/9/20: 85%->92; 5/12/20: 92%->97; 19/3/21: 97%->99; 19/3/21: FCD:15/09/2020->06/21; 11/6/21: 99%- ","33.107; 33.108; 33.126; 33.127; 33.128 ",82,42,null,null,"2018-12-07","2021-06-11"]
[2482,870078,"   (IETF) Location Source Parameter for the SIP Geolocation Header Field (draft-ietf-sipcore-locparam)","5GProtoc16",2,"Rel-16","C1-IETF","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 30/6/20: 90%->100; 9/4/21: RFC 8787 added;","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ; RFC 8787",87,44,null,null,"2018-12-07","2021-04-09"]
[2485,820050,"   Stage-3 5GS NAS protocol development for support for non-3GPP accesses","5GProtoc16-non3GPP",2,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 25/3/20: FCD:19/12/2019->03/20; 30/6/20: 50%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-06-30"]
[2489,820048,"   Stage-3 SAE Protocol Development Rel16 for support for non-3GPP accesses","SAES16-non3GPP",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[2492,840052,"   CT3 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","13/9/19: 0%->25; 6/12/19: 25%->75; 26/3/20: 75%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554",84,43,null,null,"2019-05-31","2020-03-26"]
[2496,850003,"RTCP Verification for Real-Time Services ","RTCPVer",1,"Rel-16","S4","2019-09-13","2020-03-12",1,"SP-190639",null,"Burman, Bo, Ericsson LM, ","bo.burman@ericsson.com ","; 8/10/19: 26.139 added;; 6/12/19: 0%->60; 25/3/20: 60%->100","26.114; 24.380; 24.581; 26.281; New ; 26.139",85,43,null,null,"2019-09-13","2020-03-25"]
[2497,850025,"Network Slice Performance and Analytics Charging in 5G System ","5GS_NSPACH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190780",null,"Chen Shan, Huawei ","chenshan@huawei.com ","8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201",85,43,null,null,"2019-09-13","2020-09-13"]
[2500,850031,"Enhancement of 3GPP management system for multiple tenant environment support ","MEMTANE",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190786",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","28.531; 28.532; 28.533; 28.541; 28.552; 28.554 ",85,43,null,null,"2019-09-13","2020-06-28"]
[{"$f":"A2504+1","v":2504},800044,"   Study on Load and Overload Control of 5GC Service Based Interfaces","FS_LOLC",2,"Rel-16","C4","2018-06-06","2019-06-14",1,"CP-181195",null,"Sridhar Bhaskaran (Huawei)","sridhar.bhaskaran@huawei.com","6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100","New; 22.943",80,41,null,null,"2018-06-06","2019-12-06"]
[2507,880056,"5GS Enhanced support of Over the air (OTA) mechanism for UICC configuration parameter update ","5GS_OTAF",1,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[2510,830026,"Integration of ONAP and 3GPP 5G management framework","ONAP3GPP",1,"Rel-16","S5","2019-03-07","2020-03-12",1,"SP-190139",null,"SMITH David K., AT&T ","DS9930@att.com","31/5/19: 0%->10; 13/9/19: 10%->25; 13/9/19: FCD:05/03/2020->03/20; 26/3/20: 25%->100","28.540; 28.622; 28.623; 28.532",83,42,null,null,"2019-03-14","2020-03-26"]
[2514,860021,"Management of MDT in 5G ","5GMDT",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191190",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 26/3/20: 0%->100","32.421; 32.422; 32.423; 28.532; 28.533 ",86,44,null,null,"2019-12-06","2020-03-26"]
[2517,840029,"Study on Nudsf Service Based Interface ","FS_NUDSF",1,"Rel-16","C4","2019-06-06","2019-12-12",1,"CP-191236",null,"Askerup, Anders, Hewlett Packard Enterprise ","Anders.Askerup@hpe.com ","31/5/19: 0%->10; 6/12/19: 10%->100",29.808,84,43,null,null,"2019-05-31","2019-12-06"]
[2520,870010,"Ambient noise test methodology for evaluation of acoustic UE performance ","ANTeM",1,"Rel-16","S4","2020-02-17","2020-03-25",1,"SP-200051",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.de ","; 26/6/20: 0%->100",26.132000000000001,87,44,null,null,"2020-03-25","2020-06-26"]
[2521,890045,"UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR ","B1C_BDS_pos_UEConTest",1,"Rel-16","R5","2020-09-17","2021-09-08",1,"RP-201777",null,"CATT ",null,"tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71; 2/7/21: FCD:Thu 17/06/->09/21; 29/9/21: 71%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[2524,770050,"(Small) Technical Enhancements and Improvements for Rel-16","TEI16",1,"Rel-16",null,"2017-09-11","2020-06-30",0,null,null,null,null,null,null,77,41,null,null,"2015-06-15","2015-06-15"]
[2528,0,"Release 16 Studies on 5G/5GS/5GC/NR","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2531,780023,"Study on supporting 256-bit algorithms for 5G ","FS_256_Algo",1,"Rel-16","S3","2017-12-15","2018-09-14",1,"SP-171054",null,"Evans, Tim, Vodafone Group","tim.evans1@vodafone.com","16/3/18: 0%->30¦7/6/18: 30%->55¦10/9/18: 55%->60¦7/12/18: 60%->100","new",78,40,null,null,"2017-12-15","2018-12-07"]
[2534,800090,"Study on NR beyond 52.6 GHz","FS_NR_beyond_52GHz",1,"Rel-16","RP","2018-06-15","2018-09-14",1,"RP-181435",null,"Intel",null,"14/1/20: 0%->100","38.8xx",80,41,null,null,"2018-08-06","2020-01-14"]
[2538,801002,"Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR","FS_NR_2RX_vehUE",1,"Rel-16","R4","2018-06-01","2018-12-14",1,"RP-181467",null,"Samsung",null,"TR 38.8XX¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[2541,810033,"Stopped - Study of KDF negotiation for 5G System Security","FS_5GS_KDF",1,"Rel-16","S3","2018-09-06","2019-06-14",1,"SP-180691",null,"Ahmad Muhanna ","ahmad.muhanna@huawei.com","7/12/18: 0%->55¦20/3/19: 55%->100","New",81,41,84,null,"2018-09-06","2019-03-20"]
[2544,820060,"Study on 7 - 24 GHz frequency range for NR","FS_7to24GHz_NR",1,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-192076",null,"Huawei",null,"TR. 38.8xx¦26/3/19: WID:RP-182884->RP-190373; 8/10/19: WID:RP-190373->RP-192076; 28/7/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[2545,830006,"Study on UEs Supporting Handset Mode with Non-Traditional Earpieces","FS_HaNTE",1,"Rel-16","S4","2019-03-07","2019-09-05",1,"SP-190041",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com ","31/5/19: 0%->10; 13/9/19: 10%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[2548,0,"Release 16 other Studies","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2553,780031,"Study on integration of ONAP DCAE and 3GPP management architecture ","FS_ONAPDCAE",1,"Rel-16","S5","2017-12-15","2019-03-15",1,"SP-181074",null,"ORANGE (Jean-Michel Cornily","jeanmichel.cornily@orange.com","16/3/18: 0%->10¦27/3/18: 28.900 added;¦7/6/18: 10%->20¦7/6/18: FCD:09/18->03/19¦15/6/18: WID:SP-170948->SP-180389¦10/9/18: 20%->35¦7/12/18: 35%->80¦14/12/18: WID:SP-180389->SP-181074¦14/3/19: 80%->100",28.9,78,40,null,null,"2017-12-15","2019-03-14"]
[2556,810029,"Study on management aspects of communication services","FS_CSMAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180923",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com.","7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[2559,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[2563,0,"--- RELEASE 15 ---","-",1,"Rel-15",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2566,750019,"   Study on Charging Aspects of 5G System Architecture Phase 1","FS_5GS_Ph1_CH",2,"Rel-15","S5","2017-03-03","2017-12-15",1,"SP-170953",null,"Chen, Shan, Huawei","chenshan@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->60¦11/9/17: WID:SP-170128->SP-170659¦15/12/17: 60%->100¦21/12/17: WID:SP-170659->SP-170953",null,75,38,null,null,"2017-03-03","2017-12-21"]
[2567,720005,"   (Stage 1 of 5G) New Services and Markets Technology Enablers","SMARTER",2,"Rel-15","S1","2016-06-09","2017-03-15",1,"SP-160364",null,"Li, Alice","alice.li@vodafone.com","Resulting from FS_SMARTER¦19/9/16: 0%->55¦6/10/16: 22.261 added¦1/12/16: FCD:09/16->03/20¦1/12/16: 55%->75¦2/3/17: 75%->90¦7/6/17: 90%->100",22.260999999999999,72,37,null,null,"2016-06-09","2017-06-07"]
[2570,870079,"   Security aspects of 5G System - Phase 1 IETF","5GS_Ph1-SEC",2,"Rel-15","S3-IETF","2017-03-02","2018-06-15",0.5,null,null,null,null,null,null,87,44,null,null,"2017-03-02","2018-10-02"]
[2573,770042,"         Study on 5G Network selection","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 10%->55¦15/12/17: 55%->80¦16/3/18: 80%->100",null,77,39,null,null,"2017-03-03","2018-03-16"]
[2577,770046,"         Study on 5G Interworking with EPC","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 15%->45¦15/12/17: 45%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[2580,780008,"      CT1 aspects of 5G System - Phase 1 (normative work)","5GS_Ph1-CT",3,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-09-08"]
[2583,780011,"         5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->35¦16/3/18: 35%->85¦7/6/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2587,780015,"         5G Network slicing","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2590,750028,"      CT4 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C4","2017-03-03","2017-12-14",1,"CP-183243",null,"Landais, Bruno (Nokia)","Bruno.Landais at nokia.com","5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦7/6/18: 50%->95¦10/9/18: 95%->99¦10/12/18: 99%->100","23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303",75,38,null,null,"2017-03-03","2018-12-10"]
[2591,870080,"      (IETF) Improved Extensible Authentication Protocol Method for 3GPP Mobile Network Authentication and Key Agreement (EAP-AKA') (draft-ietf-emu-rfc5448bis)","5GS_Ph1-CT",3,"Rel-15","C4-IETF","2017-03-03","2017-12-14",1,null,null,null,null,"20/6/22: Compl:80%->100%",null,87,44,null,null,"2017-03-03","2022-06-20"]
[2594,800081,"   UE Conformance Test Aspects – 5G System Non-3GPP Access","5GS_Ph1-CT_n3GPPA-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-181032",null,"Motorola",null,"tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2597,770018,"      CT3 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C3","2017-09-04","2018-06-15",1,"CP-180094",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->80¦10/9/18: 80%->100","29.213; 29.214",77,39,null,null,"2017-03-03","2018-09-10"]
[2601,810028,"   SMS Charging in 5G System Architecture Phase 1","5GS_Ph1-SMSCH",2,"Rel-15","S5","2018-09-06","2018-12-14",1,"SP-180824",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/12/18: 0%->100","32.240; 32.274; 32.290; 32.291; 32.299; 32.298",81,41,null,null,"2018-09-06","2018-12-07"]
[2604,750035,"EPC enhancements to support 5G New Radio via Dual Connectivity","EDCE5",1,"Rel-15",null,"2017-03-02","2018-03-15",1,"SP-170583",null,"Chris Pudney, Vodafone Group","Chris Pudney, Vodafone Group","9/6/17: WID:SP-170058->SP-170583",null,75,38,null,null,"2017-03-02","2017-06-09"]
[2608,760068,"      CT1 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C1","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","14/9/17: 0%->65¦15/12/17: 65%->100","24.301; 27.007",76,39,null,null,"2017-06-05","2017-12-15"]
[2611,760062,"   Charging aspects of EDCE5: PS Charging enhancements to support 5G New Radio via Dual Connectivity","EDCE5-CH",2,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170487",null,"Törnkvist, Robert, Ericsson","robert.tornkvist(at)ericsson.com","15/12/17: 0%->20¦16/3/18: 20%->100","32.251; 32.298; 32.299",76,39,null,null,"2017-06-05","2018-03-16"]
[2614,750267,"   Perf. part: New Radio Access Technology","NR_newRAT-Perf",2,"Rel-15","R4","2017-03-15","2019-06-14",1,"RP-191971",null,"NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦19/6/17: WID: RP-170855->RP-171485¦12/7/17: 38.133 added;¦12/7/17: 38.141 added;¦19/9/17: WID: RP-171485->RP-172115¦15/12/17: 38.101-4 added¦8/1/18: WID: RP-172115->RP-172834¦27/3/18: W ; 8/ ","38.133; 38.141; 38.101-4; 38.171",75,38,null,null,"2017-03-21","2020-01-14"]
[2618,760087,"UE Conformance Test Aspects - 5G system with NR and LTE","5GS_NR_LTE-UEConTest",1,"Rel-15","R5","2017-06-15","2021-12-14",0.87,"RP-211228",null,"Ericsson",null,"¦19/9/17: Compl:0%->2%¦15/12/17: impacted specs add¦15/12/17: 38.508-2 added;¦ ;; 8/10/19: WID:RP-181206->RP-192123; 8/10/19: 34.229-5 added;; 24/4/20: FCD:14/12/2018->12/20; 24/4/20: 15%->69; 8/10/20: 69%->79; 8/10/20: FCD:15/12/2020->12/20; 7/4/21: W ","38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2; 34.229-5",76,39,null,null,"2017-06-16","2021-07-02"]
[2619,0,"Release 15 Features on V2X","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2622,750002,"   Stage 1 of Enhancement of 3GPP support for V2X scenarios","eV2X",2,"Rel-15","S1","2017-01-09","2017-03-22",1,"SP-170158",null,"Chun, SungDuck, LG Electronics","sungduck.chun@lge.com ","7/6/17: 90%->100",22.186,75,38,null,null,"2017-03-02","2017-06-07"]
[2626,750162,"   Core part: V2X phase 2 based on LTE","LTE_eV2X-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-171740","RP-180858","Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦19/6/17: Compl:0%->15%¦ 30/6/17: 36.788 added;¦19/9/17: Compl:15%->30% 8/1/18: Compl:30%->55%27/3/18: Compl:55%->75%",36.787999999999997,75,38,null,null,"2017-03-21","2018-06-27"]
[2629,0,"Release 15 Features on Ultra/Highly Reliable Low Latency Communication","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2633,750261,"   Perf. part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Perf",2,"Rel-15","R4","2017-03-15","2018-12-15",0,"RP-181259",null,"Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: WID: RP-171489->RP-172845¦27/6/18: WID: RP-172845->RP-181259",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2636,720058,"Study on MC Communication Interworking between LTE and non-LTE Systems","FS_MCCI",1,"Rel-15","S6","2016-06-13","2017-06-12",1,"SP-160881",null,"Monnes, Peter (Harris Corp.)",null,"28/7/16: 23.782 added¦19/9/16: WID:SP-160341->SP-160527¦19/9/16: 0%->20¦1/12/16: WID:SP-160527->SP-160881¦1/12/16: 20%->22¦9/12/16: FCD:12/16->06/17, Rel-14->Rel-15¦3/3/17: 22%->50¦7/6/17: 50%->90¦11/9/17: 90%->100","New 23.782",72,37,null,null,"2016-06-13","2017-09-11"]
[2639,780002,"Removal of 'over LTE' limitation from Mission Critical Specifications","MCOver",1,"Rel-15","S1","2017-11-15","2017-12-15",1,"SP-180354",null,"Kees Verweij ;The Police of the Netherlands","KeesdotVerweijatPolitiedotNL","7/6/18: WID:SP-170986->SP-180354","22.179; 22.280; 22.281; 22.282; 22.468",78,40,null,null,"2017-12-15","2018-06-07"]
[2640,750021,"Enhancements to MCPTT functional architecture and information flows ","enhMCPTT",1,"Rel-15",null,"2017-03-03","2018-06-15",1,"SP-170248",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->25","23.280 + 23.379",75,38,null,null,"2017-03-03","2017-06-07"]
[2643,750022,"Enhancements to MC Data Functional architecture and information flows","eMCData",1,"Rel-15",null,"2017-03-03","2018-06-15",1,"SP-170462",null,"David Freeman, Home Office","david@dnf-consulting.co.uk","21/3/17: impacted TS/TR added¦7/6/17: 0%->10¦8/6/17: WID:SP-170249->SP-170462","23.280 + 23.282",75,38,null,null,"2017-03-03","2017-06-08"]
[2646,760048,"Enhancements to MC Video Functional architecture and information flows","eMCVideo",1,"Rel-15",null,"2017-06-05","2018-06-15",1,"SP-170401",null,"Niranth Amogh, Huawei Telecommunications (India","namogh@huawei.com","7/6/17: 0%->10","23.280; 23.281",76,39,null,null,"2017-06-03","2017-06-07"]
[2650,770015,"      CT3 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C3","2017-12-05","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","10/9/18: 0%->100","29.165; 29.213; 29.214",77,39,null,null,"2017-06-03","2018-09-10"]
[2653,750023,"MBMS usage for MC communication services ","MBMS_Mcservices",1,"Rel-15","S6","2017-03-03","2018-06-07",1,"SP-170686",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100. Problem with % complete when set as Parent Feature. Has to be left as independent item…","23.280 + 23.281 + 23.282 + 23.379",75,38,null,null,"2017-03-03","2018-03-16"]
[2657,770007,"Protocol enhancements for Mission Critical Services","MCProtoc15",1,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172145",null,"Jörgen Axell",null,"14/9/17: 0%->15¦15/12/17: 15%->40¦20/3/18: 40%->70¦7/6/18: 70%->100",null,77,39,null,null,"2017-09-08","2018-06-07"]
[2660,730050,"Battery Efficient Security for very low Throughput MTC Devices","BEST_MTC_Sec",1,"Rel-15","S3","2016-09-19","2018-03-15",1,"SP-160569",null,"Evans, Tim, VODAFONE Group Plc.",null,"6/10/16: 33.163 added 6/3/17: FCD:12/16->09/17¦6/3/17: 0%->20. Moved from Rel-14.¦7/6/17: 20%->95¦15/12/17: FCD:09/17->03/18¦16/3/18: 95%->100","33.401; 43.020; 33.220; 33.163",73,37,null,null,"2016-09-19","2018-03-16"]
[2663,750159,"   Core part: Even further enhanced MTC for LTE","LTE_eMTC4-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",1,"RP-172811","RP-181213","Ericsson",null,"WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦19/6/17: Compl:0%- 19/9/ 8/1 2 ;¦16/1/19: 97%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2664,750259,"   Perf. part: Even further enhanced MTC for LTE","LTE_eMTC4-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-172811",null,"Ericsson",null,"note: RAN #75 approved WID RP-170732 with working agreement19/6/17: WID: RP-170732->RP-171427¦8/1/18: WID: RP-171427->RP-172811¦27/6/18: Compl:0%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2667,750166,"   Core part: Further NB-IoT enhancements","NB_IOTenh2-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.95,"RP-182389","RP-180851","Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2671,750010,"Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery","ProSe_WLAN_DD",1,"Rel-15",null,"2016-11-15","2018-03-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[2674,760026,"   Stage 3 of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",2,"Rel-15","ct","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","18/12/17: WID:CP-171102->CP-173084",null,76,39,null,null,"2017-06-02","2017-12-18"]
[2679,720082,"   Study on Complementary Features for Voice services over WLAN","FS_VoWLAN",2,"Rel-15","S2","2016-06-13","2017-03-15",1,"SP-160506",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com","28/7/16: 23.751 added¦19/9/16: 0%->10., 7/12/16: moved from Rel-14, according to SP-160806¦6/3/17: 10%->80¦7/6/17: 80%->100",23.751000000000001,72,37,null,null,"2016-06-17","2017-06-07"]
[2682,760023,"      CT1 aspects of VoWLAN","VoWLAN-CT",3,"Rel-15","C1","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","14/9/17: 0%->70¦15/12/17: 70%->100","24.302 ; 24.312 ; 24.244 ",76,39,null,null,"2017-06-02","2017-12-15"]
[2685,0,"Release 15 Features on Virtual Reality (VR)","-",1,"Rel-15",null,"2016-03-01","2016-03-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2688,770022,"Test Methodologies for the Evaluation of Perceived Listening Quality in Immersive Audio Systems","LiQuImAS",1,"Rel-15","S4","2017-09-08","2018-09-14",1,"SP-170609",null,"Schevciw, Andre – Qualcomm Incorporated ","aschevci@qti.qualcomm.com","15/12/17: added: 26.861¦26.261¦26.260¦26.259¦15/12/17: 0%->15¦16/3/18: 15%->20¦7/6/18: 20%->35¦7/6/18: FCD:06/18->09/18¦10/9/18: 35%->100","New; 26.861; 26.261; 26.260; 26.259",77,39,null,null,"2017-09-08","2018-09-10"]
[2689,770023,"Addition of HDR to TV Video Profiles","HDR",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170610",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->100","26.116; 26.346; 26.234; 26.247; 26.244",77,39,null,null,"2017-09-08","2017-12-15"]
[2692,790016,"Forward compatibility for 3GPP Diameter Charging Applications","FWDCA",1,"Rel-15","S5","2018-03-15","2018-06-15",1,"SP-180076",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.251; 32.277; 32.299",79,40,null,null,"2018-03-15","2018-06-07"]
[{"$f":"A2696+1","v":2696},790021,"Media Handling Aspects of 5G Conversational Services","5G_MTSI_Codecs",1,"Rel-15","S4","2018-03-15","2018-09-14",1,"SP-180650",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/6/18: 0%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-180033->SP-180650","26.114; 26.223",79,40,null,null,"2018-03-15","2018-10-02"]
[2699,790027,"   CT3 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","22/3/18: 0%->95¦10/9/18: 95%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[2702,790036,"   Stage 3 of INOBEAR","INOBEAR-CT",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com",null,null,79,40,null,null,"2017-12-15","NA"]
[2706,780170,"   Core part: Increased number of E-UTRAN data bearers","INOBEARRAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-180569",null,"Samsung",null,"27/3/18: WID: RP-172835->RP-180569¦27/6/18: Compl:0%->99%¦27/6/18:",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2709,750017,"   Study on security aspects of enhancements to ProSe UE-to-Network Relay","FS_REAR_Sec",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-170270",null,null,"lihe2@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->50¦15/12/17: 50%->79¦16/3/18: 79%->99¦16/3/18: FCD:03/18->06/18¦7/6/18: 99%->100",null,75,38,null,null,"2017-03-02","2018-06-07"]
[2712,780026,"   Stage 2 of eVoLP","eVoLP",2,"Rel-15","S2","2017-10-12","2017-12-15",1,"SP-170935",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com",null,"23.401; 23.203",78,40,null,null,"2017-12-15","NA"]
[2713,780044,"   CT aspects on enhanced VoLTE performance","eVoLP-CT",2,"Rel-15",null,"2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com",null,null,78,40,null,null,"2017-12-15","NA"]
[2716,770051,"   Study on enhanced VoLTE performance","FS_eVoLP",2,"Rel-15",null,"2016-12-01","2018-06-15",1,"SP-160833",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100",23.759,74,38,null,null,"2016-12-01","2017-09-11"]
[2720,740008,"   Study on unlicensed spectrum offloading system enhancements","FS_USOS",2,"Rel-15","S2","2016-12-01","2017-06-15",1,"SP-160835",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100",23.728999999999999,74,38,null,null,"2016-12-01","2017-09-11"]
[2723,770001,"   Stage 3 of USOS","USOS-CT",2,"Rel-15","C4","2017-09-08","2018-03-15",1,"CP-172028",null,"Lena Chaponniere, Qualcomm Incorporated","lguellec@qti.qualcomm.com","15/12/17: acronym corrected to USOS-CT as per the approved WID¦18/12/17: 0%->60¦16/3/18: 60%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",77,39,null,null,"2016-03-01","2018-03-16"]
[2726,750024,"   Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) ","FS_FRMCS_ARCH",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170269",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com ","21/3/17: added impacted TR¦7/6/17: 0%->10¦11/9/17: 10%->50¦15/12/17: 50%->100","new 23.790",75,38,null,null,"2017-03-03","2017-12-15"]
[2730,790032,"      CT1 aspects of MONASTERY","MONASTERY",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","16/3/18: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","24.379; 24.380; 24.481; 24.483; 24.484",79,40,null,null,"2018-03-16","2018-09-10"]
[2733,790013,"   Security Architecture of MONASTERY","MONASTERY_SEC",2,"Rel-15","S3","2018-01-11","2018-03-16",1,"SP-180052",null,"Woodward, Tim, Motorola Solutions",null,"16/3/18: 0%->100",33.18,79,40,null,null,"2018-03-15","2018-03-16"]
[2734,760030,"PS Data Off Phase 2 ","PS_DATA_OFF2",1,"Rel-15",null,"2017-03-02","2018-06-14",1,"SP-170246",null,"Murhammer, Leopold, Deutsche Telekom AG","leopold.murhammer@t-mobile.at",null,null,75,38,null,null,"2017-03-02","NA"]
[2740,760035,"Northbound APIs for SCEF – SCS/AS Interworking","NAPS",1,"Rel-15",null,"2017-03-02","2018-06-15",1,"SP-170240",null,"Vaidya, Maulik, Huawei","Maulik.vaidya@huawei.com ","6/3/17: 0%->10",null,75,38,null,null,"2017-03-02","2017-03-06"]
[2741,750009,"   Stage 2 of NAPS","NAPS",2,"Rel-15","S2","2017-03-02","2017-09-15",1,"SP-170240",null,"Zhu Fenqin, Huawei","zhufenqin@huawei.com","6/3/17: 0%->10¦7/6/17: 10%->85¦30/6/17: 29.122 added;¦11/9/17: 85%->100¦15/12/17: rapoprteur changed",29.122,75,38,null,null,"2017-03-02","2017-12-15"]
[2745,770032,"   Security aspects of NAPS","NAPS-Sec",2,"Rel-15","S3","2017-09-08","2018-03-16",1,"SP-170635",null,"Zhao, Xuwen, Huawei","zhaoxuwen@huawei.com ","15/12/17: 0%->60¦16/3/18: 60%->100",33.186999999999998,77,39,null,null,"2017-09-08","2018-03-16"]
[2748,750031,"   Study on CAPIF","FS_CAPIF",2,"Rel-15","S6","2017-03-10","2017-09-14",1,"SP-170405",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","21/3/17: added impacted TR¦7/6/17: 0%->35¦8/6/17: WID:SP-170279->SP-170405¦11/9/17: 35%->70¦15/12/17: 70%->100","new 23.722",75,38,null,null,"2017-03-10","2017-12-15"]
[2751,780024,"   Security aspects of CAPIF","CAPIF-Sec",2,"Rel-15","S3","2017-12-15","2018-06-14",1,"SP-171051",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","16/3/18: 0%->40¦7/6/18: 40%->100",null,78,40,null,null,"2017-12-15","2018-06-07"]
[2755,770033,"   Study on security aspect of 5G Network Slicing Provisioning","FS_NETSLICE_MGT_Sec",2,"Rel-15","S3","2017-09-08","2018-06-15",1,"SP-170636",null,"SA3: Huawei ","lei.zhongding@huawei.com","11/9/17: 0%->5¦15/12/17: 33.811 added;¦15/12/17: 5%->20. Acronym corrected.¦16/3/18: 20%->30¦7/6/18: 30%->100",33.811,77,39,null,null,"2017-09-08","2018-06-07"]
[2758,780038,"   Performance Assurance for 5G networks including network slicing","NETSLICE-ADPM5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180814",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","16/3/18: 0%->10¦7/6/18: 10%->50¦7/6/18: FCD:06/18->09/18¦10/9/18: 50%->100¦2/10/18: WID:SP-170957->SP-180814",32.404000000000003,78,40,null,null,"2017-12-15","2018-10-02"]
[2759,780039,"   Management and virtualization aspects of 5G networks","NETSLICE-MNFV5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170958",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com","16/3/18: 0%->25¦7/6/18: 25%->75¦7/6/18: FCD:06/18->09/18¦10/9/18: 75%->100","28.500; 28.510; 28.511; 28.512; 28.513; 28.515; 28.516; 28.517; 28.518; 28.520; 28.521; 28.522; 28.523; 28.525; 28.526; 28.527; 28.528",78,40,null,null,"2017-12-15","2018-09-10"]
[2762,810042,"      CT3 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C3","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.507; 29.512",81,41,null,null,"2018-09-06","2018-09-10"]
[2765,790039,"Policy and Charging for Volume Based Charging","PC_VBC",1,"Rel-15",null,"2016-12-01","2018-06-15",1,null,null,null,null,null,null,78,40,null,null,"2018-03-16","NA"]
[2769,790040,"   CT1 aspects of PV_VBC","PC_VBC",2,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180051",null,"Huang Zhenning (China Mobile)","huangzhenning (at) chinamobile (dot) com","7/6/18: 0%->100","24.605; 24.147",79,40,null,null,"2018-03-16","2018-06-07"]
[2772,770034,"Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management","OAM_SON_AAS",1,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170658",null,"Nokia (Weixing Wang)","weixing.wang@nokia-sbell.com","15/12/17: 0%->80¦10/9/18: 80%->100","28.627; 28.628; 28.629; 28.658; 28.659",77,39,null,null,"2017-09-08","2018-09-10"]
[2776,760038,"Enhanced QoE Reporting for MTSI","EQoE_MTSI",1,"Rel-15","S4","2017-06-05","2018-03-15",1,"SP-170333",null,"Gunnar Heikkilä, Ericsson LM","gunnar.heikkila@ericsson.com","11/9/17: 0%->10¦15/12/17: 10%->80¦16/3/18: 80%->100",26.114000000000001,76,39,null,null,"2017-06-03","2018-03-16"]
[2779,760013,"   CT aspects of eCNAM","eCNAM-CT",2,"Rel-15","ct","2017-06-02","2018-03-14",1,"CP-171181",null,"Mowafy, Hala. Ericsson","hala.mowafy@ericsson.com",null,null,76,39,null,null,"2017-06-02","NA"]
[2782,750001,"Enhancement of background data transfer","eBT",1,"Rel-15","S1","2017-01-16","2017-03-08",1,"SP-170161",null,"Atsushi Minokuchi, NTT DOCOMO","minokuchi at nttdocomo dot com",null,22.100999999999999,75,38,null,null,"2017-03-02","NA"]
[2783,760016,"Stage-3 SAE Protocol Development - Phase 6","SAES6",1,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","NA"]
[2786,760019,"   SAE Protocol Development (Stage 3) - Phase 6","SAES6",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,null,null,"14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100",null,72,37,null,null,"2015-03-24","2018-06-07"]
[2789,750005,"HPLMN Radio Access Technology deployment Optimisation in Network Selection","HORNS",1,"Rel-15","S1","2017-03-02","2017-06-15",1,"SP-170277",null,"Eddy Hall, Qualcomm Incorporated","edhall@qti.qualcomm.com ","7/6/17: 75%->100",null,75,38,null,null,"2017-03-02","2017-06-07"]
[2793,780047,"      (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id)","IMSProtoc9",3,"Rel-15","C1-IETF","2017-06-02","2018-06-15",1,null,null,"Christer Holmberg","christer.holmberg@ericsson.com","22/3/18: 0%->100; 9/4/21: RFC 8262 added;","RFC 8262",78,40,null,null,"2017-12-18","2021-04-09"]
[2796,760011,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C3","2017-06-02","2018-06-13",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com","15/12/17: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","29.163; 29.165; 29.949",76,39,null,null,"2015-04-02","2018-09-10"]
[2801,750168,"   Core part: DL interference mitigation for UMTS","UTRA_DL_IM-Core",2,"Rel-14","R2","2017-03-15","2017-06-15",1,"RP-171136","RP-171135","Qualcomm",null,"no Perf. part19/6/17: Compl:0%->100%",null,75,38,null,null,"2017-03-21","2017-06-19"]
[2804,750077,"   Study on a simplified HS-SCCH for UMTS","FS_UTRA_simple_HSSCCH",2,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171477",null,"gerardo.agni.medina.acosta@ericsson.com ","gerardo.agni.medina.acosta@ericsson.com ","19/6/17: Compl:0%->100%¦30/6/17: 25.709 added;",25.709,75,38,null,null,"2017-03-21","2017-06-30"]
[2807,780020,"Receive acoustic output test in the presence of background noise","RAOT",1,"Rel-15","S4","2017-12-15","2018-06-15",1,"SP-170835",null,"ISBERG, Peter, Sony Mobile Communications","peter.isberg [at] sony.com","16/3/18: 0%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->100","26.131; 26.132",78,40,null,null,"2017-12-15","2018-06-07"]
[2808,780021,"Speech quality in the presence of ambient noise for super-wideband and fullband modes","SPAN",1,"Rel-15","S4","2017-12-15","2018-09-14",1,"SP-170836",null,"Reimes, Jan – HEAD acoustics GmbH ","jan.reimes@head-acoustics.de ","16/3/18: 0%->50¦7/6/18: 50%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100",26.131,78,40,null,null,"2017-12-15","2018-09-10"]
[2811,780033,"   REST Solution Sets (normative work)","REST_SS",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com","16/3/18: 0%->20¦7/6/18: 20%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->100",32.100999999999999,78,40,null,null,"2017-12-15","2018-09-10"]
[2814,800116,"   (IETF) JSON Hyper-Schema: A Vocabulary for Hypermedia Annotation of JSON (draft-handrews-json-schema-hyperschema)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",0,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com",null,null,80,41,null,null,"2018-07-10","NA"]
[2818,870073,"   (IETF) PASSporT Extension for Diverted Calls (draft-ietf-stir-passport-divert) ","eSPECTRE",2,"Rel-15","C1-IETF","2019-03-07","2019-03-07",0.8,null,null,null,null,"9/4/21: RFC 8946 added;","RFC 8946",87,44,null,null,"2020-04-23","2021-04-09"]
[2821,800102,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (draft-ietf-tls-tls13)","TEI15",2,"Rel-15","S3-IETF","2017-03-17","2018-06-15",1,null,null,null,null,"26/6/19: 25%->100; 9/4/21: RFC 8446 added;","RFC 8446",80,41,null,null,"2018-06-27","2021-04-09"]
[2825,770167,"   Core part: UL data compression in LTE ","LTE_UDC-Core",2,"Rel-15","R2","2000-01-03","2018-09-14",0.99,"RP-180914","RP-180912","CATT",null,"¦8/1/18: Compl:0%->70%¦8/1/18: CD:Mon 03/01/00->Thu 15/03/18¦27/3/18: Compl:70%->99%27/3/1 ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18;",null,77,39,null,null,"2017-09-19","2018-06-27"]
[2828,770168,"   Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Core",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"15/12/17: 36.715-04 added;¦8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%;","36.715-04",77,39,null,null,"2017-09-19","2018-03-27"]
[2831,770169,"   Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-Core",2,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-180262",null,"Ericsson",null,"¦8/1/18: Compl:0%->99%27/3/18: WID: RP-172077->RP-180262¦27/6/18: Compl:99%->100%",null,77,39,null,null,"2017-09-19","2018-06-27"]
[2832,770269,"   Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-Perf",2,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-180262",null,"Ericsson",null,"¦27/3/18: Compl:0%->99% ¦27/6/18: Compl:99%->100%",null,77,39,null,null,"2017-09-19","2018-06-27"]
[2835,770071,"Extended-Band12 new E-UTRA Band","Ext_B12_LTE",1,"Rel-15","R4","2017-09-15","2019-05-31",1,"RP-172111",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[2839,710073,"Stopped - Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON",1,"Rel-15",null,"2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459",null,71,36,null,null,"2016-03-22","2017-09-14"]
[2842,740045,"   Stopped - Stage 3 of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",2,"Rel-15","ct","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[2845,740048,"      Stopped - CT6 aspects of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",3,"Rel-15","C6","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/3/17: 0%->100",31.102,74,38,null,null,"2016-12-01","2017-03-07"]
[2849,720091,"Shortened TTI and processing time for LTE","LTE_sTTIandPT",1,"Rel-15",null,"2016-06-15","2020-12-12",0.99,"RP-161299",null,"Ericsson",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[2852,820064,"   UE Conformance Test Aspects - Shortened TTI and processing time for LTE","LTE_sTTIandPT-UEConTest",2,"Rel-15","R5","2018-12-15","2020-12-12",1,"RP-191003",null,"Huawei",null,"tested: REL-15 WI LTE_sTTIandPT-Core; 26/6/19: WID:RP-182429->RP-191003; 8/10/20: 0%->90; 8/10/20: 0%->90; 8/10/20: FCD:20/06/2019->12/20; 7/4/21: 0%->100; 8/4/21: 100%->100",null,null,null,null,null,"2019-01-16","2021-04-08"]
[2855,740272,"   Perf. part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR-Perf",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-162514",null,"Airbus",null,"19/6/17: Compl:0%->50%19/9/17: Compl:50%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2856,770065,"   UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72)","LTE450_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180528",null,"Airbus",null,"¦8/1/18: Compl:0%->77%¦27/3/18: Compl:77%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[2862,740175,"   Core part: FDD operating band in the L-band for LTE","LTE_FDD_L_Band-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171403",null,"NTT DOCOMO",null,"21/3/17: Compl:0%->50%¦19/6/17: Compl:50%->99%¦19/9/17: Compl:99%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2864,780062,"   UE Conformance Test Aspects - FDD operating band in the L-band for LTE","LTE_FDD_L_band-UEConTest",2,"Rel-15","R5","2017-12-15","2018-09-14",1,"RP-180145",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ;; 11/10/20: 60%->100",null,78,40,null,null,"2018-01-08","2020-10-11"]
[2867,740276,"   Perf. part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Perf",2,"Rel-15","R4","2017-03-17","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17 19/9/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2870,780065,"   UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-UEConTest",2,"Rel-15","R5","2017-12-15","2018-12-14",1,"RP-172698",null,"Sprint",null,"tested: REL-15 WI LTE_CA_C_B41_PC2-Core¦27/3/18: Co ;; 28/7/20: 5%->100",null,78,40,null,null,"2018-01-08","2020-07-28"]
[2874,740180,"   Core part: TDD operating band in the L-band for LTE","LTE_TDD_L_Band-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: Compl:0%->15%¦19/6/17: Compl:15%->70%¦ 19/9/17: Compl:70%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[2877,750160,"   Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-180584","RP-180318","Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦19/6/17: Compl:0%->70%¦19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%¦27/3/18: Compl:90%->99%¦27/3/18: CD:Thu 15/03/18->Fri ¦27/6/18: CD:Fri",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2878,750260,"   Perf. part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-180584",null,"Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #7519/6/17: WID: RP-170750->RP-171031¦8/1/18: Compl:0%->65%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:65%->80%27/3/ ¦27/6/18: Compl:80%->100%",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2881,750263,"   Perf. part: UE Positioning Accuracy Enhancements for LTE","LCS_LTE_acc_enh-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-181298",null,"Nokia",null,"¦19/6/17: WID: RP-170813->RP-171508¦8/1/18: Compl:0%->30%¦8/1/18: WID: RP-171508->RP-172313¦27/6/18: Compl:30%->100%¦27/6/18: WID: RP-17231",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2884,750264,"   Perf. part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL-Perf",2,"Rel-15","R4","2016-09-14","2018-12-14",1,"RP-171740",null,"Huawei",null,"¦19/6/17: CD:Sat 15/12/18->Fri 15/06/18¦19/6/17: WID: RP-170838->RP-171067 19/9/17: WID: RP-171067->RP-17173827/3/18: Compl:0%->25%¦27/6/18: Compl:25%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[{"$f":"A2888+1","v":2888},750069,"Further video enhancements for LTE","LTE_ViLTE_enh2",1,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170781",null,"CMCC",null,"no Perf. part¦compare REL-14 WI LTE_VoLTE_ViLTE_enh",null,75,38,null,null,"2017-03-21","2017-03-21"]
[2891,750170,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170956","RP-172192","China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core¦19/6/17: Compl:0%->25%¦19/6/17: WID: RP- 19/9/17: Compl:25%->45%¦8/1/18: Compl:45%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2894,750171,"   Core part: Enhancing LTE CA Utilization","LTE_euCA-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.9,"RP-180561","RP-181069","Nokia",null,"19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2898,750173,"   Core part: 450 MHz Band for LTE in Region 3","LTE450_Reg3-Core",2,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170952",null,"China Unicom",null,"¦19/6/17: Compl:0%->30%¦19 12/7/17: 36.759 added;¦19/9/17: Compl:30%->80%¦8/1/18: Compl:80%->100%",36.759,75,38,null,null,"2017-03-21","2018-01-08"]
[2901,750074,"US 600 MHz Band for LTE","LTE600_US",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170740",null,"Ericsson",null,null,null,75,38,null,null,"2017-03-21","2017-03-21"]
[2902,750174,"   Core part: US 600 MHz Band for LTE","LTE600_US-Core",2,"Rel-15","R4","2017-03-15","2017-09-15",1,"RP-171142",null,"Ericsson",null,"¦19/6/17: Compl:0%->95%¦19 12/7/17: 36.755 added;19/9/17: Compl:95%->100%",36.755000000000003,75,38,null,null,"2017-03-21","2017-09-19"]
[2905,750076,"LAA/eLAA for the CBRS 3.5GHz band in the United States","LTE_3550_CBRS_US_LAA",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170804",null,"AT&T",null,"compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2 Acronym changed, was \"LTE_TDD_3550_CBRS_US_LAA\"",null,75,38,null,null,"2017-03-21","2017-06-19"]
[2908,760097,"Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171131",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2912,760198,"   Core part: Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40-Core",2,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,"19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[2915,850061,"   UE Conformance Test Aspects – LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-UEConTest",2,"Rel-15","R5","2019-09-19","2021-06-11",1,"RP-192116",null,"Huawei",null,"8/10/20: 0%->50; 8/10/20: FCD:15/09/2020->12/20; 8/4/21: 50%->98; 8/4/21: FCD:11/12/2020->06/21; 2/7/21: 98%->100",null,85,43,null,null,"2019-10-08","2021-07-02"]
[2918,761200,"   Perf. part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Perf",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"¦19/9/17: WID: RP-171506->RP-171759¦27/3/18: Compl:0%->100%;",null,76,39,null,null,"2017-06-16","2018-03-27"]
[2922,780068,"Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN",1,"Rel-15","R2","2017-12-15","2019-12-15",0.98,"RP-172820",null,"CMCC",null,"MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2923,780168,"   Core part: Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.95,"RP-180306","RP-180867","CMCC",null,"MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact27/3/18: Compl:0%->30%2 ¦27/6/18: Compl:30%->95%",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2927,780169,"   Core part: Enhanced LTE Support for Aerial Vehicles","LTE_Aerial-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-181310","RP-181045","Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part¦27/3/18: Compl:0%->15%¦27/6/18: Compl:15%->99%;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2930,780171,"   Core part: Separation of CP and UP for Split Option 2 of NR","NR_CPUP_Split-Core",2,"Rel-15","R3","2017-12-15","2018-06-15",1,"RP-180326","RP-181149","Ericsson",null,"follow-up WI of REL-15 SI FS_NR_CPUP_Split¦introduction of E1 interface. 30/1/18: acronym updated27/3/18: Compl:0%->30%27/3/18: WID: RP-172831->RP-180326¦27/6/18: Compl:30%->100%¦27/6/18: Stat Rep: ->RP-181149",null,78,40,null,null,"2018-01-08","2018-06-27"]
[2933,780272,"   Perf. part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-180960",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL¦27/6/18: Compl:0%->30%¦26/3/19: 30%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[2937,780074,"LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172839",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01",null,78,40,null,null,"2018-01-08","2018-01-08"]
[2940,761002,"Performance requirements of interference cancellation receiver for LTE BS","LTE_IC_BS",1,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171411",null,"China Telecom",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2944,760090,"LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170962",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2947,760091,"LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171026",null,"Qualcomm",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2950,760092,"LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171126",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2951,760192,"   Core part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180955",null,"Huawei",null,"12/7/17: 36.715-03-01 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%¦27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%;","36.715-03-01",76,39,null,null,"2017-06-16","2018-06-27"]
[2954,760193,"   Core part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"12/7/17: 36.715-04-01 added;¦19/9/17: Compl:0%->54% 8/1/18: Compl:54%->65%;27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;","36.715-04-01",76,39,null,null,"2017-06-16","2018-06-27"]
[2957,760194,"   Core part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL","LTE_CA_R15_5DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180743",null,"Nokia",null,"12/7/17: 36.715-05-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->50%;27/3/18: Compl:50%->75% ¦27/6/18: Compl:75%->100%;","36.715-05-01",76,39,null,null,"2017-06-16","2018-06-27"]
[2961,760295,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180957",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2964,760296,"   Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"19/9/17: CD:Sat 15/09/18->Fri 15/06/18¦ 8/1/18: Compl:0%->50%¦27/3/18: Compl:50%->80% ¦27/6/18: Compl:80%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[2968,630011,"   Stopped - Test part: LTE UE TRP and TRS and UTRA Hand Phantom","LTE_UTRA_TRP_TRS-UEConTest",2,"Rel-15","R5","2014-03-15","2017-12-15",0.78,"RP-150070",null,"ZTE","TAYLOR Carolyn (carolyn.tayl@zte.com.cn)","Stat Rep: RP-141132->RP-141848¦Rel 12->Rel13 1st Apr 15: Compl:15%->20% 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: WID: RP-140090->RP-150070 1st Apr 15: Stat Rep: RP-141848->RP-150069 03/07/15: Compl:20%->25% 03/07/15: Stat Rep: RP-150069->","New 37.544 ",63,32,null,null,"2014-03-04","2018-01-08"]
[2971,790253,"   Perf. part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Perf",2,"Rel-15","R6","2018-03-15","2018-09-14",1,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;¦10/9/18: 80%->100",null,79,40,null,null,"2018-03-27","2018-09-10"]
[2974,801203,"   Perf. Part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5","LTE_CA_R15_xDL3UL-Perf",2,"Rel-15","R4","2018-05-15","2018-05-15",1,"RP-181311",null,"KDDI",null,"Perf. Part was introduced and completed at RAN #80",null,80,41,null,null,"2018-06-27","NA"]
[2975,790055,"Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72",1,"Rel-15","R4","2018-03-15","2018-12-14",1,"RP-180178",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;",null,79,40,null,null,"2018-03-27","NA"]
[2978,0,"Release 15 Studies","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2981,750043,"Study on CU-DU lower layer split for New Radio","FS_NR_CU_DU_LLS",1,"Rel-15","R3","2017-03-15","2018-06-15",1,"RP-180684",null,"NTT DOCOMO",null,"CU = central unit, DU = distributed unit¦results will be captured in existing TR 38.801¦19/9/17: Compl:0%->30%¦19/9/17: WID: RP-170818->RP-171717¦15/12/17: 38.816 added;¦8/1/18: Compl:30%->95%¦8/1/18: CD:Fr ¦27/6/18",38.816000000000003,75,38,null,null,"2017-03-21","2018-06-27"]
[2984,760080,"Study on separation of CP and UP for split option 2 of NR","FS_NR_CPUP_Split",1,"Rel-15","R3","2017-06-15","2017-12-15",1,"RP-171905",null,"Ericsson",null,"19/9/17: Compl:0%->45%19/9/17: WID: RP-171421->RP-171905¦15/12/17: 38.806 added;¦8/1/18: Compl:45%->100%",38.805999999999997,76,39,null,null,"2017-06-16","2018-01-08"]
[2989,760081,"Study on LTE DL 8Rx antenna ports","FS_LTE_8Rx_AP_DL",1,"Rel-15","R4","2017-06-15","2017-12-15",1,"RP-171753",null,"Huawei",null,"12/7/17: 36.757 added;¦19/9/17: Compl:0%->35%¦ 8/1/18: Compl:35%->100%",36.756999999999998,76,39,null,null,"2017-06-16","2018-01-08"]
[2993,710049,"Study on Energy Efficiency Aspects of 3GPP Standards","FS_ENEFF",1,"Rel-15","SP","2016-03-11","2017-06-09",1,"SP-160224","_SP-170533","Orange, Xiaobao Chen","xiaobao.chen@orange.com","28/7/16: 21.866 added;¦9/6/17: FCD:12/16->9/6/17 (Rel-14->Rel-15)¦0%->100",21.866,71,36,null,null,"2016-03-11","2017-06-09"]
[2996,710032,"Study on Enhanced Isolated E-UTRAN Operation for Public Safety","FS_IOPS_LB",1,"Rel-15","S2","2016-03-07","2016-12-15",1,"SP-160171",null,"Antoine Mouquet, Orange","antoine.mouquet@orange.com","9/6/16: 0%->6¦28/7/16: 23.798 added¦1/12/16: FCD:09/16->12/16¦1/12/16: 6%->15. 7/12/16: Moved from Rel-14 according to SP-160806.¦6/3/17: 15%->50¦7/6/17: 50%->100",23.797999999999998,71,36,null,null,"2016-03-07","2017-06-07"]
[2999,750030,"Study on technical requirements for a new secure platform for 3GPP applications","FS_NG_SP2",1,"Rel-15","C6","2017-03-03","2017-09-14",1,"CP-170183",null,"Heiko Kruse","heiko.kruse@safrangroup.com","21/3/17: 31.801 added;¦11/9/17: 0%->70¦15/12/17: 70%->100",31.800999999999998,75,38,null,null,"2017-03-03","2017-12-15"]
[3000,750041,"Study on scheduling enhancements with CA for UMTS","FS_UTRA_CA_sched_enh",1,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171065",null,"Huawei",null,"TR 25.7XX¦19/6/17: Compl:0%->100%¦ 12/7/17: 25.708 added;",25.707999999999998,75,38,null,null,"2017-03-21","2017-07-12"]
[3003,720025,"Study on User Services Enhancements in 3GPP for TV Services","FS_USE_3GPP_4_TV",1,"Rel-15","S4","2016-06-13","2017-09-12",1,"SP-160273",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","19/9/16: 0%->30¦6/10/16: 26.917 added¦1/12/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: 60%->75¦6/3/17: FCD:03/17->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: 75%->80¦7/6/17: FCD:06/17->09/17¦11/9/17: 80%->100","26.9xx; 26.917",72,37,null,null,"2016-06-11","2017-09-11"]
[3007,760056,"Study on OAM aspects of LTE and WLAN integration ","FS_OAM_LWI",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170480",null,"Yizhi Yao, Intel Corporation","yizhi.yao@intel.com","30/6/17: 32.868 added;¦11/9/17: 0%->10¦15/12/17: 10%->50¦16/3/18: 50%->90¦7/6/18: 90%->100","new; 32.868",76,39,null,null,"2017-06-03","2018-06-07"]
[3010,710007,"Study on Implementation for the Partitioning of Itf-N","FS_IMP_ITFN",1,"Rel-15","S5","2016-03-01","2018-03-15",1,"SP-160020",null,"Hu, Yaxi, China Mobile","huyaxi@cmdi.chinamobile.com","13/6/16: 0%->10¦19/9/16: 10%->35¦1/12/16: 35%->40¦6/3/17: FCD:03/17->03/18¦21/3/17: moved from rel-14¦7/6/17: 40%->60¦11/9/17: 60%->80¦15/12/17: 80%->100","New 32.880",71,36,null,null,"2016-03-01","2017-12-15"]
[3013,720063,"Study on SON for eCoMP for LTE","FS_LTE_SON_eCOMP",1,"Rel-15","R3","2016-06-15","2017-06-15",1,"RP-161181",null,"Nokia",null,"26/9/16: Compl:0%->10%. ¦20/12/16: Compl:10%->40%21/3/17: Compl:40%->60%¦19/6/17: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3017,780061,"Study on UE Application Layer Data Throughput Performance Expansion for CA","FS_UE_App_Data_Perf_CA",1,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-180203",null,"PCTEST Engineering Lab",null,"compare REL-11 SI FS_UE_App_Data_Perf¦note: SI FS_UE_App_Data_Perf_CA is addressing 2DL/1UL involving also an unlicensed carrier of REL-13 LTE_LAA¦instead of a new TR, the TR 37.901 will be updated for REL-15¦ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3020,0,"Release 14 on Mission Critical","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3023,740022,"   Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",2,"Rel-14",null,"2016-06-13","2017-06-14",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379, 23.280, 23.281, 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[3024,720056,"      Stage 2 of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379, 23.280, 23.281, 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[3027,740025,"         CT3 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3031,720055,"   Common functional architecture to support mission critical services","MCImp-MC_ARCH",2,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160489",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","28/7/16: 23.280 added¦19/9/16: 0%->40¦1/12/16: 40%->95¦3/3/17: 95%->100","23.280, 23.379, 23.281, 23.282; 23.280",72,37,null,null,"2016-06-13","2017-03-03"]
[3034,700030,"      Stage 1 of MCVideo","MCImp-MCVideo",3,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150849",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160106¦0->80%¦9/6/16: 80%->100","New 22.281",70,36,null,null,"2015-12-07","2016-06-09"]
[3037,740033,"      Stage 3 of MCVideo","MCImp-MCVIDEO-CT",3,"Rel-14","ct","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ",null,"24.581, 24.281 ",74,38,null,null,"2016-12-01","NA"]
[3041,740037,"         CT6 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C6","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","5/6/17: 0%->100. No work identified for CT6.","31.102, 31.103",74,38,null,null,"2016-12-01","2017-06-05"]
[3044,700031,"      Stage 1 of MCData","MCImp-MCData",3,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100","New 22.282",70,36,null,null,"2015-12-07","2016-06-09"]
[3045,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[3049,740031,"         CT4 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","6/3/17: 0%->100","23.003, 23.335, 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[3052,790052,"   UE Conformance Test Aspects - Mission Critical Improvements","MCImp-UEConTest",2,"Rel-14","R5","2018-03-15","2019-12-13",1,"RP-180527",null,"NIST",null,"tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements)¦to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).;; 25/9/20: 5%->100",null,79,40,null,null,"2018-03-27","2020-09-25"]
[3056,730011,"   CT4 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","6/3/17: 0%->100","23.003, 23.008, 29.283",73,37,null,null,"2016-09-16","2017-03-06"]
[3059,720030,"LTE support for V2X services","V2XLTE",1,"Rel-14",null,"2015-02-09","2018-12-14",1,"SP-150573",null,null,null,"7/12/15: 0%->5¦28/1/16: 22.185 added¦2/3/16: 5%->90¦9/6/16: 90%->100","22.278; 22.185",68,35,null,null,"2015-09-09","2016-06-09"]
[3062,740009,"   Security aspect of LTE support of V2X services","V2XLTE-Sec",2,"Rel-14","S3","2016-12-01","2017-06-15",1,"SP-160955",null,"Huawei, Marcus Wong","mwong@huawei.com","6/3/17: 0%->75¦7/6/17: 75%->100",33.185000000000002,74,38,null,null,"2016-12-01","2017-06-07"]
[3066,760086,"      UE Conformance Test Aspects - Support for LTE-based V2X Services","LTE_V2X-UEConTest",3,"Rel-14","R5","2017-06-15","2018-12-14",1,"RP-192556",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->40%¦ 27/3/18: Compl:40%->55%; 14/1/20: WID:RP-172356->RP-192556; 14/1/20: 65%->100",null,76,39,null,null,"2017-06-16","2020-01-14"]
[3069,730028,"      CT3 aspects of V2X Services","V2X-CT",3,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 29.387 added¦2/12/16: 0%->40¦6/3/17: 40%->60¦5/6/17: 60%->100","29.212, 29.468; 29.387",73,37,null,null,"2016-09-16","2017-06-05"]
[3070,730029,"      CT4 aspects of V2X Services","V2X-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 29.388 added¦6/10/16: 29.389 added¦2/12/16: 0%->80¦6/3/17: 80%->100","23.003, 23.007, 23.008, 29.272; 29.388; 29.389",73,37,null,null,"2016-09-16","2017-03-06"]
[3073,670009,"      Study on Stage 1 of LTE support for V2X services","FS_V2XLTE_S1",3,"Rel-14","S1","2015-02-09","2015-02-09",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75¦7/12/15: 75%->100","New 22.885",67,34,null,null,"2015-12-07","2015-12-07"]
[3076,680058,"      RAN1 Study on LTE-based V2X Services","FS_LTE_V2X",3,"Rel-14","R1","2015-06-15","2016-06-15",1,"RP-161263",null,"LG Electronics",null,"29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ¦28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15¦",33.884999999999998,68,35,null,null,"2015-07-03","2016-07-01"]
[{"$f":"A3080+1","v":3080},730073,"   UE Conformance Test Aspects - Support for V2V services based on LTE sidelink","LTE_SL_V2V-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-172358",null,"Huawei",null,"¦20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ;; 11/10/20: 98%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3083,710024,"   Non-IP for Cellular IoT for EC-EGPRS ","NonIP_GPRS",2,"Rel-14","S2","2016-03-02","2016-06-15",1,"SP-160196",null,"Hans Ronneke, Ericsson","hans . Ronneke (a) ericsson . Com","9/6/16: 0%->50¦19/9/16: 50%->100","23.060, 23.682, 23.401?",71,36,null,null,"2016-03-02","2016-09-19"]
[3086,720069,"      CT3 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C3","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦20/9/16: 0%->100","29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007",72,37,null,null,"2016-03-02","2016-09-20"]
[3090,720292,"   Perf. part: Further enhanced MTC for LTE","LTE_feMTC-Perf",2,"Rel-14","R4","2016-06-15","2017-12-15",1,"RP-170532",null,"Ericsson",null,"¦26/9/16: WID: RP-161321->RP-161464¦20/12/16: WID: RP-161464->RP-162520¦20/12/16: Stat Rep: ->RP-16252021/3/17: CD:Fri 15/09/17->Fri 15/12/1721/3/17 19/6/17: Compl:0%->35%19/9/17: Compl:35%->60%¦8/1/18: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2018-01-08"]
[3093,720193,"   Core part: Enhancements of NB-IoT","NB_IOTenh-Core",2,"Rel-14","R1","2016-06-15","2017-06-15",1,"RP-171060","RP-171061","Huawei",null,"26/9/16: Compl:0%->13%26/9/16: WID: RP-161324->RP-161901¦20/12/16: Compl:13%->70%¦21/3/17: Compl:70%->95%¦21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:95%->100%",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3094,720293,"   Perf. part: Enhancements of NB-IoT","NB_IOTenh-Perf",2,"Rel-14","R4","2016-06-15","2017-12-15",1,"RP-171060",null,"Huawei",null,"26/9/16: WID: RP-161324->RP-16190121/3/17: CD:Fri 15/09/17->Fri 15/12/17¦19/6/17: Compl:0%->50%¦19/6/17: WID: RP-161901->RP-171060¦19/9/17: Compl:50%->60%¦8/1/18: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2018-01-08"]
[3097,730359,"Extended architecture support for Cellular Internet of Things","CIoT_Ext",1,"Rel-14",null,"2016-06-17","2017-03-14",1,"SP-160732",null,"Intel : Puneet Jain","puneet.jain@intel.com",null,"23.401, 23.682, 23.060",73,37,null,null,"2016-09-19","2016-09-19"]
[3100,740038,"   Stage 3 of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","21/3/17: 24.250 added;",24.25,74,38,null,null,"2016-12-01","2017-03-21"]
[3104,730177,"   Core part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh-Core",2,"Rel-14","R6","2016-09-15","2017-06-15",1,"RP-161806","RP-171321","Nokia",null,"¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80%19/6/17: Compl:80%->100%",null,73,37,null,null,"2016-09-26","2017-06-19"]
[3106,730083,"New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands",1,"Rel-14","R4","2016-09-15","2017-09-15",0.99,"RP-161890",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3112,720007,"   Enhancements of Dedicated Core Networks selection mechanism","eDecor",2,"Rel-14","S2","2016-06-09","2016-09-15",1,"SP-160310",null,"Roland Gustafsson","Roland.Gustafsson@ericsson.com","19/9/16: 70%->100","23.401, 23.060, 23.251",72,37,null,null,"2015-09-17","2016-09-19"]
[3115,730015,"      CT4 aspects of eDecor","eDecor-CT",3,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.303, 23.003, 23.008",73,37,null,null,"2016-09-16","2017-03-06"]
[3118,740167,"      Core part: RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE-Core",3,"Rel-14","R3","2016-12-15","2017-03-15",1,"RP-162543","RP-170547","Ericsson",null,"21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3119,760088,"      UE Conformance Test Aspects - Enhancements of Dedicated Core Networks for UTRA and LTE","eDECOR-UTRA_LTE-UEConTest",3,"Rel-14","R5","2017-06-15","2017-12-15",1,"RP-171899",null,"Ericsson",null,"¦19/9/17: Compl:0%->50%¦ 8/1/18: Compl:50%->100%",null,76,39,null,null,"2017-06-16","2018-01-08"]
[3122,740178,"   Core part: Addition of band 25 and 26 to LTE MTC cat.0","LC_MTC_LTE_cat0_B25_B26-Core",2,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162572",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3125,720031,"EIR check for WLAN access to EPC","EWE",1,"Rel-14",null,"2015-11-02","2016-09-15",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002, 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[3129,720033,"      CT4 aspects of EWE","EWE-CT",3,"Rel-14","C4","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com","2/12/16: 0%->100",29.273,72,37,null,null,"2016-06-13","2016-12-02"]
[3132,730003,"   CT aspects of ERP","ERP-CT",2,"Rel-14","ct","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3136,690033,"   Study on Phase 2 of the Support of Emergency services over WLAN","FS_SEW2",2,"Rel-14","S2","2015-09-01","2016-06-16",1,"SP-160173",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251¦7/12/15: 0%->30, FCD: 12/15->06/16¦7/3/16: 30%->75¦7/3/16: WID:SP-150251->SP-160173¦9/6/16: 75%->100","new 23.771",67,34,null,null,"2015-04-01","2016-06-09"]
[3139,730018,"      CT1 aspects of SEW2","SEW2-CT",3,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 20%->95¦5/6/17: 95%->100","24.302, 24.312, 24.301, 24.244, 24.229, 24.237",73,37,null,null,"2016-09-16","2017-06-05"]
[3142,720076,"T-ADS supporting WLAN Access","TADS_WLAN",1,"Rel-14","S2","2016-03-15","2016-09-15",1,"SP-160488","SP-170519","Jiang Yi","jiangyi (at) chinamobile (dot) com","19/9/16: 0%->100","23.292, 23.221, 23.402",72,37,null,null,"2016-06-17","2016-09-19"]
[3143,710075,"Enhanced LTE-WLAN Aggregation (LWA)","LTE_WLAN_aggr",1,"Rel-14","R2","2016-03-15","2017-03-15",1,"RP-160600",null,"Intel",null,"follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3146,700020,"Evolution to and Interworking with eCall in IMS","EIEI",1,"Rel-14",null,"2015-05-11","2018-03-15",1,"SP-150275","SP-170538","Kurt Bischinger",null,"12/15: created by MCC to distinguish Stage 1 from Stage 2",22.100999999999999,68,35,null,null,"2015-12-07","2015-06-09"]
[3150,710021,"      CT1 aspects of evolution to and interworking with eCall in IMS","EIEI-CT",3,"Rel-14","C1","2016-03-02","2016-09-15",1,"CP-160053",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","11/6/16: 0%->35¦16/9/16: 35%->85¦2/12/16: 85%->100","24.229, 24.301",71,36,null,null,"2016-03-02","2016-12-02"]
[3153,760084,"   UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI)","EIEI-UEConTest",2,"Rel-14","R5","2017-06-15","2018-03-15",1,"RP-171057",null,"Qualcomm",null,"¦19/9/17: Compl:0%->45%¦8/1/18: Compl:45%->80%¦27/3/18: Compl:80%->100%",null,76,39,null,null,"2017-06-16","2018-03-27"]
[3156,720034,"   CT aspects for PWDIMS","PWDIMS-CT",2,"Rel-14","ct","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,null,null,72,37,null,null,"2016-06-11","NA"]
[3160,630107,"   CT1 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C1","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728¦5/6/17: 0%->100","24.229, 24.323",63,32,null,null,"2014-01-29","2017-06-05"]
[3163,651203,"   (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497","ISAT",2,"Rel-14","C4-IETF","2014-09-12","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 25%->70; 26/6/19: 70%->100","draft-dawes-sipping-debug",65,33,null,null,"2014-09-02","2019-06-26"]
[3166,0,"Other Release 14 ","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3167,740017,"User Controlled Spoofed Call Treatment","SPECTRE",1,"Rel-14",null,"2016-08-23","2018-06-15",1,"SP-160898",null,"Greg Schumacher, Sprint",null,"1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898",null,73,37,null,null,"2016-09-19","2016-12-01"]
[3171,780049,"   (IETF) Authenticated Identity Management in SIP (draft-ietf-stir-rfc4474bis)","SPECTRE-CT_IETF2",2,"Rel-14","C1-IETF","2017-06-15","2018-06-15",1,null,null,"Christer Holmberg","christer.holmberg@ericsson.com","22/3/18: 0%->100; 9/4/21: RFC 8224 added;","RFC 8224",78,40,null,null,"2017-12-18","2021-04-09"]
[3175,710046,"      Study on System Architecture Enhancements to eMBMS for TV Video Service","FS_AE_enTV",3,"Rel-14","S2","2016-03-11","2016-09-15",1,"SP-160225",null,"Miguel Griot, Qualcomm","mgriot@qti.qualcomm.com","9/6/16: 0%->70¦28/7/16: 23.746 added¦19/9/16: 70%->100",23.745999999999999,71,36,null,null,"2016-03-11","2016-09-19"]
[3178,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347, 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[3181,740051,"      CT3 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","6/3/17: 0%->80¦6/3/17: 80%->100",29.061,74,38,null,null,"2016-12-01","2017-03-06"]
[3185,670003,"Multimedia Priority Service Modifications","MPS_Mods",1,"Rel-14","S1","2015-03-11","2016-06-15",1,"SP-150043",null,"Ray P. Singh (Applied Communications Science)","rsingh@appcomsci.com","1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%¦07/09/15: 25%->40¦7/12/15: 40%->70¦2/3/16: 70%->80¦9/6/16: 80%->100",22.152999999999999,67,34,null,null,"2015-03-04","2016-06-09"]
[3188,730032,"   CT1 aspects of SIP Reason header extension","REAS_EXT",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160481",null,"Mohali, Marianne","marianne.mohali@orange.com","2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100",24.228999999999999,73,37,null,null,"2016-09-16","2017-06-05"]
[3191,690034,"Enhancements to User Location Reporting Support","eULRS",1,"Rel-14","S1","2015-09-09","2015-12-18",1,"SP-150540",null,null,null,"2/3/16: 0%->100",null,68,35,null,null,"2015-09-09","2016-03-02"]
[3192,730002,"Diameter Load Control Mechanism","DLoCMe",1,"Rel-14","ct","2014-12-03","2017-03-15",0.98,"CP-160645","CP-171049","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","5/12/16: WID:CP-160412->CP-160645",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3195,740058,"   (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583","DLoCMe",2,"Rel-14","C4-IETF","2016-12-02","2017-03-15",0.9,"CP-160645",null,null,null,"2/12/16: 0%->90",null,74,38,null,null,"2016-12-02","2016-12-02"]
[3199,740055,"      CT3 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","6/3/17: 0%->100","29.061, 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.368, 29.468, 29.213, 29.155, 29.201",74,38,null,null,"2016-12-01","2017-03-06"]
[3202,720060,"Enhancements to Multi-stream Multiparty Conferencing Media Handling","MMCMH_Enh",1,"Rel-14",null,"2016-03-02","2017-03-21",0.99,"SP-160272","SP-170528","Nikolai Leung","nleung@qti.qualcomm.com",null,26.114000000000001,72,37,null,null,"2016-06-11","NA"]
[3205,720065,"      CT1 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Name changed from \"CT1 aspects of MTSI Extension on Multi-stream\". Acronym changed from \"MMCMH-CT\"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦2/12/16: 0%->95¦6/3/17: 95%->100",24.228999999999999,72,37,null,null,"2016-03-02","2017-03-06"]
[3209,750039,"      (IETF) RTP Payload Format Restrictions (draft-ietf-mmusic-rid)","MMCMH_Enh-CT",3,"Rel-14","C1-IETF","2017-03-21","2017-03-21",0.9,null,null,"Ericsson",null,"23/4/20: 20%->90; 9/4/21: RFC 8851 added;","RFC 8851",75,38,null,null,"2017-03-21","2021-04-09"]
[3212,710029,"   deleted -CT3 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C3","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","29.162, 29.213, 29.214, 29.165",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3213,710030,"   deleted -CT4 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","23.333, 29.333, 23.334, 29.334, 29.238",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3216,720009,"   Control and User Plane Separation of EPC nodes","CUPS",2,"Rel-14","S2","2016-06-09","2016-09-15",1,"SP-160316",null,"Huawei, Mirko Schramm","mirko.schramm@huawei.com","19/9/16: 0%->80¦1/12/16: 80%->100","23.214, 23.002, 23.203, 23.401, 23.402",72,37,null,null,"2015-09-17","2016-12-01"]
[3219,730040,"      CT4 aspects for CUPS","CUPS-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com","2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100","23.007, 29.274, 29.281, 29.303, 23.008",73,37,null,null,"2016-09-16","2017-06-05"]
[3223,690039,"      Configuration Management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-CM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160401",null,"ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn)","zhu.weihong@zte.com.cn","5/10/15: 28.513¦28.512¦28.511¦28.510 added¦7/12/15: 0%->15¦7/3/16: 15%->20¦13/6/16: 20%->30¦19/9/16: 30%->50¦1/12/16: 50%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100","28.513; 28.512; 28.511; 28.510; 28.621, 28.622, 28.623, 28.704, 28.707",69,35,null,null,"2015-06-15","2017-06-07"]
[3226,690042,"      Lifecycle management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-LCM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160427",null,"Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks","anatoly.andrianov@nokia.com","5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%-","28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709",69,35,null,null,"2015-06-15","2017-06-07"]
[3229,720044,"   OAM support for Licensed Shared Access (LSA)","OAM14-LSA",2,"Rel-14","S5","2016-06-13","2017-06-12",1,"SP-160397",null,"Nokia: Olaf Pollakowski",null,"28/7/16: 28.303 added¦28/7/16: 28.302 added¦28/7/16: 28.301 added¦19/9/16: 0%->20¦1/12/16: 20%->30¦6/3/17: 30%->40¦7/6/17: 40%->100","32.101; 28.303; 28.302; 28.301",72,37,null,null,"2015-03-12","2017-06-07"]
[3232,670005,"Enhancements to Domain Selection between VoLTE and CDMA CS","eDSVCC",1,"Rel-14","S1","2015-03-11","2015-06-15",1,"SP-150045",null,"China Telecom, Hongmei Zhu","zhuhongmei@gsta.com","1/4/15: rapporteur added, Impacted TS added¦June2015: Compl:0%->100",22.100999999999999,67,34,null,null,"2015-03-04","2015-06-15"]
[3237,740004,"   Stage 2 of PS Data Off","PS_DATA_OFF",2,"Rel-14","S2","2016-11-17","2016-12-15",1,"SP-160831",null,"Christophe Petit (Orange)","kris (dot) petit (at) orange (dot) com","1/12/16: 0%->100","23.401, 23.203, 23.060, 23.228, 23.292, 23.221",74,38,null,null,"2016-12-01","2016-12-01"]
[3238,740041,"   Stage 3 of PS Data Off","PS_DATA_OFF-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[3241,740044,"      CT6 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/3/17: 0%->100","31.102, 31.103, 31.111",74,38,null,null,"2016-12-01","2017-03-07"]
[3244,710004,"Paging Policy Enhancements and Procedure","PPEPO_LTE",1,"Rel-14","S1","2016-02-01","2016-03-01",1,"SP-160113","SP-170549","China Unicom, Zhuoyun Zhang","zhangzy910@chinaunicom.cn",null,22.100999999999999,71,36,null,null,"2016-03-01","2016-03-01"]
[3248,720078,"   Stage 2 of Enhancement to Flexible Mobile Service Steering ","eFMSS",2,"Rel-14","S2","2016-06-17","2016-09-15",1,"SP-160314",null,"ZTE, Tricci So",null,"19/9/16: 0%->100",23.202999999999999,72,37,null,null,"2016-03-01","2016-09-19"]
[3251,720061,"   (IETF) Other IETF aspects of IMS_TELEP_EXT","IMS_TELEP_EXT",2,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.91,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com",null,"draft-ietf-payload-rtp-h265, -flexible-fec-scheme , draft-ietf-clue-framework , -datachannel, -signalling, -data-model-schema, -protocol, -rtp-mapping, draft-ietf-mmusic-sctp-sdp, -data-channel-sdpneg, draft-ietf-tsvwg-sctp-dtls-encaps",72,37,null,null,"2016-03-01","NA"]
[3254,800105,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8850 added;","RFC 8850",80,41,null,null,"2018-06-27","2021-04-09"]
[3258,800109,"      (IETF) Mapping RTP streams to CLUE Media Captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8849 added;","RFC 8849",80,41,null,null,"2018-06-27","2021-04-09"]
[3261,710011,"Improved Streaming QoE Reporting in 3GPP","IQoE",1,"Rel-14","S4","2016-03-01","2017-03-15",1,"SP-160082","SP-170521","Zhiming Li, Huawei","Lizhiming@huawei.com","11/6/16: 0%->10¦19/9/16: 10%->55. FDC: 12/16->03/17¦1/12/16: 55%->65¦6/3/17: 65%->100","New 26.909, 26.247, 26.346",71,36,null,null,"2016-03-01","2017-03-06"]
[3262,710085,"New GPRS algorithms for EASE","EASE_ALGOs_SA3",1,"Rel-14","S3","2016-03-15","2016-06-15",1,"SP-160203",null,"Tim Evans, Vodafone",null,"Discussion whether it should be Rel-13. To be concluded at SA#72.¦13/6/16: 0%->60¦1/12/16: 60%->70¦6/3/17: 70%->100","55.241, 55.242, 55.243, 55.251, 55.252, 55.253",71,36,null,null,"2016-03-22","2017-03-06"]
[3265,690049,"   Study on LI in S8 Home Routing Architecture for VoLTE ","FS_LIV8",2,"Rel-14","S3","2015-09-17","2016-06-17",1,"SP-150461",null,"Greg Schumacher (SPRINT) Gregory ","Schumacher@sprint.com","7/12/15: 0%->45¦28/1/16: 33.827 added¦7/3/16: 45%->55¦19/9/16: 55%->65¦15/12/17: 65%->100",33.826999999999998,69,35,null,null,"2015-09-17","2017-12-15"]
[3268,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[{"$f":"A3272+1","v":3272},690050,"   Study on improvement of awareness of user location change","FS_AULC",2,"Rel-14","S2","2015-09-17","2016-06-17",1,"SP-150517",null,"Yang Xu","xuyang49@chinaunicom.cn","7/12/15: 0%->40¦7/3/16: 40%->70¦9/6/16: 70%->100",23.71,69,35,null,null,"2015-09-17","2016-06-09"]
[3275,730035,"      CT3 Aspect of AULC","AULC-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.212, 29.213",73,37,null,null,"2016-09-16","2017-03-06"]
[3279,700040,"   Study on Service Domain Centralization","FS_SeDoC",2,"Rel-14","S2","2015-11-02","2016-09-15",1,"SP-160306",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com","Comes back from previous release¦28/1/16: 23.719 added¦7/3/16: 0%->30¦7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70¦11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16¦1/12/16: 70%->100",23.719000000000001,70,36,null,null,"2015-12-07","2016-12-01"]
[3282,700041,"   Study on sponsored data connectivity improvements","FS_SDCI",2,"Rel-14","S2","2015-11-02","2016-06-10",1,"SP-150627",null,"Yang Xu","xuyang49@chinaunicom.cn","28/1/16: 23.721 added¦7/3/16: 10%->40¦9/6/16: 40%->100",23.721,70,36,null,null,"2015-12-07","2016-06-09"]
[3285,730038,"      CT3 Aspects of SDCI","SDCI-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.250 added¦2/12/16: 10%->30¦6/3/17: 30%->80¦5/6/17: 80%->100","29.212, 29.213, 29.214, 29.201, 29.250",73,37,null,null,"2016-09-16","2017-06-05"]
[3286,710017,"Stage-3 SAE Protocol Development - Phase 5","SAES5",1,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",71,36,null,null,"2016-03-02","2016-03-02"]
[3289,720073,"   SAE Protocol Development (Stage 3) - Phase 5","SAES5",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,null,null,"Added following CT1's chair e-mail 14/06/16¦16/9/16: 0%->20¦2/12/16: 20%->85¦6/3/17: 85%->100",null,72,37,null,null,"2015-03-24","2017-03-06"]
[3293,720084,"Robust Call Setup for VoLTE subscriber in LTE","RobVoLTE",1,"Rel-14",null,"2015-11-02","2018-09-14",0.99,"SP-160312",null,null,null,null,null,72,37,null,null,"2015-12-07","NA"]
[3297,730078,"   Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh",2,"Rel-14","R2","2016-09-15","2018-09-14",0.99,"RP-161856",null,"CMCC",null,null,null,73,37,null,null,"2016-12-14","2016-09-26"]
[3300,740010,"   RAN-Assisted Codec Adaptation in MTSI","LTE_VoLTE_ViLTE_enh-S4",2,"Rel-14","S4","2016-12-01","2017-06-09",1,"SP-160778","SP-170516","Ozgur Oyman, Intel","ozgur.oyman@intel.com","6/3/17: 0%->65¦6/3/17: FCD:03/17->06/17¦7/6/17: 65%->100",null,74,38,null,null,"2016-12-01","2017-06-07"]
[3304,720039,"   CT6 aspects of IOC_UE_conf","IOC_UE_conf",2,"Rel-14","C6","2016-06-13","2017-03-15",1,"CP-160828",null,"Adrian Buckley","abuckley@blackberry.com","11/6/16: 0%->10¦14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100","31.102, 31.103",72,37,null,null,"2016-06-11","2017-06-05"]
[3307,710008,"   Resource Optimization for PS Domain Online","CH14-ROPOCH",2,"Rel-14","S5","2016-03-01","2017-06-09",1,"SP-160021",null,"Shrader, David(Ericsson)","david.shrader@ericsson.com","13/6/16: 0%->10. FCD:09/16->03/17¦19/9/16: FCD: 09/16->03/17¦19/9/16: 10%->20¦1/12/16: 20%->50¦6/3/17: 50%->80¦6/3/17: FCD:03/17->06/20¦7/6/17: 80%->100","32.251, 32.299",71,36,null,null,"2016-03-01","2017-06-07"]
[3310,740019,"Determination of Completeness of Charging Information in IMS","CH14-DCCII",1,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160398",null,"Jesske, Roland (Deutsche Telekom)",null,"19/9/16: 0%->10","32.240, 32.260, 32.298, 32.299",72,37,null,null,"2016-06-13","2016-09-19"]
[3311,720045,"   Determination of Completeness of Charging Information in IMS","CH14-DCCII",2,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160398","SP-170344","Jesske, Roland (Deutsche Telekom)",null,"19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦7/6/17: 10%->100","32.240, 32.260, 32.298, 32.299",72,37,null,null,"2016-06-13","2017-06-07"]
[3314,740021,"      CT3 Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160697",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","8/6/17: 0%->100",29.164999999999999,74,38,null,null,"2016-12-01","2017-06-08"]
[3318,730075,"   UE Conformance Test Aspects - Enhanced LAA for LTE","LTE_eLAA-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-171577",null,"Intel",null,"¦21/3/17: Compl:0%->5% ;19/6/17: Compl:5%->6%¦19/9/17: Compl 8/1/18: C2 ;; 11/10/20: 85%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3321,700063,"DTX/DRX enhancements in CELL_FACH","FACH_DTXDRX",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-152286",null,"Huawei",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3324,700177,"   Core part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Core",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"¦22/3/16: Compl:0%->60%¦1/7/16: Compl:60%->100%¦1/7/16: CD:Th",36.749000000000002,70,36,null,null,"2016-01-01","2016-07-01"]
[3328,700178,"   Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3","LTE_1980_2170_REG3-Core",2,"Rel-14","R4","2015-12-15","2015-12-15",0,"RP-152238",null,"KT Corp.",null,null,null,70,36,null,null,"2016-01-01","2015-12-22"]
[3331,760083,"   UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs-UEConTest",2,"Rel-14","R5","2017-06-15","2017-09-15",1,"RP-170931",null,"Dish Network",null,"¦19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[3334,700279,"   Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"¦22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16",null,70,36,null,null,"2016-01-01","2016-07-01"]
[3335,750052,"   UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69)","LTE_FDD_2600_CA_B3-UEConTest",2,"Rel-14","R5","2017-03-15","2017-12-15",1,"RP-172257",null,"Bureau Veritas",null,"¦19/9/17: Compl:43%->96%¦8/1/18: Compl:96%->100%¦",null,75,38,null,null,"2017-06-19","2018-01-08"]
[3338,700280,"   Perf. part: Multi-Band Base Station testing with three or more bands","MB_BS_test_3B-Perf",2,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-162442",null,"Alcatel-Lucent",null,"22/3/16: Compl:0%->5%22/3/16: WID: RP-152205->RP-160063¦1/7/16: Compl:5%->30%26/9/16: Compl:30%->60%26/¦20/12/16: Compl:60%->100%¦",null,70,36,null,null,"2016-01-01","2016-12-20"]
[3342,750056,"   UE Conformance Test Aspects - Performance enhancements for high speed scenario in LTE","LTE_high_speed-UEConTest",2,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170367",null,"CMCC",null,"tested: REL-14 LTE_high_speed-Core;¦19/6/17: Compl: 1 8/1/18:27/3/ ;; 11/10/20: 95%->100",null,75,38,null,null,"2017-03-21","2020-10-11"]
[3345,710272,"   Perf. part: Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-162026",null,"Huawei",null,"26/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160538->RP-161850¦20/12/16: Compl:0%->30%¦20/12/16: WI21/3/17: Compl:30%->50%19/6/17: Compl:50%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3348,710176,"   Core part: Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE","LTE_MIMO_OTA-Core",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170278",null,"Intel",null,"follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part1/7/16: Compl:0%->10%1/7/16: WID: RP-160603->RP-16091426/9/16: Compl:10%->15%¦20/12/16: Compl:15%->25%¦20/12/16: WID: RP-160914->RP-162306;21/3/17: Compl:25%->33%;1 ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3352,710277,"   Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Perf",2,"Rel-14","R4","2016-03-15","2017-12-15",1,"RP-160623",null,"Samsung",null,"¦20/12/16: Stat Rep: -->¦19/6/17: Compl:0%->50%19/9/17: Compl:50%->70%19/9/17: CD:Fri 15/09/17->Fri 15/12/17¦8/1/18: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3354,710078,"Further mobility enhancements in LTE","LTE_eMob",1,"Rel-14","R2","2016-03-15","2017-06-15",1,"RP-160636",null,"ZTE",null,"no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3359,710279,"   Perf. part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-162488",null,"Ericsson",null,"¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->;21/3/17: Compl:0%->20%19/6/17: Compl:20%->75%¦19/9/17: Compl:75%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3360,780063,"   UE Conformance Test Aspects - Uplink capacity enhancements for LTE","LTE_UL_CAP_enh-UEConTest",2,"Rel-14","R5","2017-12-15","2018-12-14",1,"RP-172639",null,"Ericsson",null,"tested: REL-14 WI LTE_UL_CAP_enh-Core¦related to UL 256 QAM27/3 ;¦26/3/19: 35%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3363,780064,"   UE Conformance Test Aspects - L2 latency reduction techniques for LTE","LTE_LATRED_L2-UEConTest",2,"Rel-14","R5","2017-12-15","2018-03-15",1,"RP-180530",null,"Ericsson",null,"tested: REL-14 WI LTE_LATRED_L2-Core27/3/18: Compl:0%->100%;",null,78,40,null,null,"2018-01-08","2018-03-27"]
[3367,710082,"SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch",1,"Rel-14","R1","2016-03-15","2018-06-15",0.99,"RP-160676",null,"Huawei",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[3370,750054,"   UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-UEConTest",2,"Rel-14","R5","2017-03-15","2018-06-15",1,"RP-180848",null,"Huawei",null,"tested: REL-14 LTE_SRS_switch-Core;¦19/6/17: Compl:0%->5%¦8/1/18: Compl:27/3/ ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3373,710284,"   Perf. part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-161019",null,"MediaTek",null,"1/7/16: WID: RP-160680->RP-161019¦26/9/16: CD:Fri 15/09/17->Thu 15/06/17¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:0%->25%19/6/17: Compl:25%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3377,800112,"   (IETF) Session Description Protocol (SDP) Offer/Answer Considerations for Datagram Transport Layer Security (DTLS) and Transport Layer Security (TLS) (draft-ietf-mmusic-dtls-sdp)","IMSProtoc8",2,"Rel-14","C1-IETF","2016-06-14","2017-03-15",0.9,"CP-160294",null,"Alcatel-Lucent","Keith Drage","23/4/20: 25%->90; 9/4/21: RFC 8842 added;","RFC 8842",80,41,null,null,"2018-06-27","2021-04-09"]
[3380,700059,"   Study on Multi-Carrier Enhancements for UMTS","FS_UTRA_MCe",2,"Rel-14","R1","2015-12-15","2016-06-15",1,"RP-152290",null,"Huawei",null,"22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->100%¦28/7/16: 25.707 added;",25.707000000000001,70,36,null,null,"2016-01-01","2016-07-28"]
[3381,720194,"   Core part: Multi-Carrier Enhancements for UMTS","UTRA_MCe-Core",2,"Rel-14","R2","2016-06-15","2016-12-15",1,"RP-162453","RP-162129","Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe¦26/9/16: Compl:0%->35%¦20/12/16: Compl:35%->100%;",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3384,720295,"   Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-162007",null,"Nokia",null,"¦20/12/16: Compl:0%->100%¦",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3387,720196,"   Core part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Core",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"follow-up WI of SI FS_LTE_B41_HPUE¦26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3391,721102,"   Core part: Dedicated Core Networks for GERAN","DECOR_GERAN-Core",2,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161029","RP-170194","Ericsson",null,"no Perf. part¦DECOR was a REL-13 SA2 feature¦26/9/16: Compl:0%->100%21/3/17: Stat Rep: ->RP-170194",null,72,37,null,null,"2016-07-01","2017-03-21"]
[3394,721203,"   Perf. part: Positioning Enhancements for GERAN","ePOS_GERAN-Perf",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052",null,"Ericsson",null,"¦20/12/16: Compl:0%->50% ¦21/3/17: Compl:50%->80%¦19/6/17: Compl:80%->100%¦",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3397,730179,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN","UMTS_QMC_Streaming-Core",2,"Rel-14","R2","2016-09-15","2017-03-15",1,"RP-161917","RP-170259","China Unicom",null,"¦20/12/16: Compl:0%->60% ¦21/3/17: Compl:60%->100%",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3401,730180,"   Core part: Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID-Core",2,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161896","RP-170478","China Telecom",null,"¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3404,730284,"   Perf. part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL)","LTE_4Rx_AP_DL_CA-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-161897",null,"Ericsson",null,"¦20/12/16: Compl:0%->30%;21/3/17: Compl:30%->50%19/6/17: Compl:50%->90%¦19/9/17: Compl:90%->100%",null,73,37,null,null,"2016-09-26","2017-09-19"]
[3405,740071,"   Introduction of new band support for 4Rx antenna ports for LTE","LTE_4Rx_AP_DL_bands",2,"Rel-14","R4","2016-12-15","2018-09-14",0.99,"RP-162496",null,"Huawei",null,"Pending acronym",null,74,38,null,null,"2016-12-20","2016-12-20"]
[3408,730085,"Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX",1,"Rel-14","R4","2016-09-15","2018-09-14",0.99,"RP-161898",null,"Qualcomm",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3411,760085,"   UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE","LTE_UE_cat_1RX-UEConTest",2,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-180263",null,"Qualcomm",null,"¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3415,710183,"   Core part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Core",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912","RP-171330","Intel",null,"¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3419,780051,"Miscellaneous IETF dependencies","TEI14_IETF",1,"Rel-14",null,"2017-03-15","2020-06-05",0.75,null,null,null,null,"Created upon demand of RAN5",null,78,40,null,null,"2017-12-18","NA"]
[3422,780053,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel)","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-12-14",0.25,null,null,null,null,"was (IETF) T.140 Text Conversation over Data Channels (draft-schwarz-mmusic-t140-usage-data-channel); 9/4/21: RFC 8865 added;","RFC 8865",78,40,null,null,"2017-12-18","2021-04-09"]
[3426,870082,"   (IETF) IP Mobility Support for IPv4, Revised (draft-ietf-mip4-rfc3344bis) --> RFC 5944","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,null,null,87,44,null,null,"2020-04-23","NA"]
[3429,620362,"   TR on Security Assurance scheme for 3GPP network products","SCAS-SA3TR",2,"Rel-14","S3","2013-12-09","2016-12-15",1,"SP-150716","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","This TR contains results of the second WID objective. Dec.14: 75->85%¦June2015: Compl:85%->90¦7/12/15: 90%->92¦10/12/15: WID:SP-130718->SP-150716¦19/9/16: 92%->98. FCD set to 12.16 (was 03/16)¦6/10/16: 33.216 added¦1/12/16: 81%->100","New 33.916; 33.216",62,32,null,null,"2013-11-22","2016-12-01"]
[3430,620262,"   Security Assurance Specification for 3GPP network product classes","SCAS-SA3",2,"Rel-14","S3","2013-12-13","2017-06-15",1,"SP-150716","-","China Mobile","Judy Zhu (zhuhongru@chinamobile.com)","June2015: 0%->5¦7/12/15: 5%->72.¦10/12/15: WID:SP-130718->SP-150716¦7/3/16: 72%->75¦28/7/16: 33.250 added¦19/9/16: 75%->90. FCD set to 12.16 (was 03/16). 6/3/17: moved from Rel-14.¦15/2/18: moved back to Rel-14¦6/8/18: 33.515 added;","New 33.116, 33.117; 33.250; 22.511; 22.512; 22.513; 22.514; 33.515",62,32,null,null,"2013-11-22","2018-08-06"]
[3433,709998,"Rel-14 LTE Carrier Aggregation","LTE_CA_Rel14",1,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[3436,690286,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3440,690088,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[3443,709999,"Rel-14LTE Advanced inter-band Carrier Aggregation","LTE_AIBCA_Rel14",1,"Rel-14","R4","2015-12-15","2021-09-21",0.87,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[3447,700070,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-152196",null,"Qualcomm",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3450,700071,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-152237",null,"Huawei",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3453,700072,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL",2,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3454,700172,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL-Core",3,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,"28/1/16: 36.714-03-03 added;22/3/16: Compl:0%->1%1/7/16: Compl:1%->15%¦21/3/17: Compl:15%->100%","36.714-03-03","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3457,700173,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170128",null,"LG Electronics",null,"28/1/16: 36.714-00-02 added¦22/3/16: Compl:0%->10%¦22/3/16: WID: RP-152246->RP-160148¦1/7/16: Compl:10%->40%¦26/9/16: Compl:40%->70%¦20/¦21/3/17: ","36.714-00-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3460,700174,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%¦26/9/16: Compl:38%->74%¦20/12/16: Compl:74%->9521/3/1","36.714-04-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[{"$f":"A3464+1","v":3464},700275,"      Perf. part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"¦22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-16082226/9/16: WID: RP-160822->RP-161473¦20/12/16: Compl:50%->64% 21/3/17: Compl:64%->",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3467,700276,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170309",null,"Huawei",null,"22/3/16: WID: RP-152278->RP-160582¦1/7/16: WID: RP-160582->RP-160945¦26/9/16: WID: RP-160945->RP-161674¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->90%;",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3471,700058,"Study on Scenarios and Requirements for Next Generation Access Technologies","FS_NG_SReq",1,"Rel-14","RP","2015-12-15","2016-12-15",1,"RP-160811",null,"CMCC",null,"22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%¦14/12/16: FCD:09/16->12/16¦14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re","38.xxx",70,36,null,null,"2016-01-01","2016-12-20"]
[3474,620071,"Study on Multimedia Broadcast Supplement for Public Warning System","FS_MBSP",1,"Rel-14","S1","2013-12-11","2014-12-12",1,"SP-130599",null,"Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100%",22.815000000000001,62,32,null,null,"2013-11-26","2014-12-03"]
[3476,640060,"Study on User Location Reporting Support enhancements","FS_eULRS",1,"Rel-14","S1","2014-06-19","2015-06-17",1,"SP-140402",null,"China Unicom","Zhuoyun Zhang ( zhangzy910@chinaunicom.cn)","SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%¦June2015: Compl:90%->100",22.899000000000001,64,33,null,null,"2014-05-29","2015-06-15"]
[3479,670041,"Study on Latency reduction techniques for LTE","FS_LTE_LATRED",1,"Rel-14","R2","2015-03-16","2016-06-15",1,"RP-150465",null,"Ericsson",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%;",36.881,67,34,null,null,"2015-04-01","2016-07-01"]
[3482,720085,"Stopped - Study on SON for eCoMP for LTE","delFS_LTE_SON_eCOMP",1,"Rel-14","R3","2016-06-14","2016-06-16",1,"RP-161181",null,"Nokia",null,"26/9/16: Compl:0%->10%. 1/12/16: Deleted: 720085 was allocated twice: to FS_LTE_SON-ECOMP (now in 720063) and to ROBVOLTE (now in 720301)","23.228, 23.237",72,37,null,null,"2015-12-07","2016-09-26"]
[3486,710057,"Study on enhancement of VoLTE","FS_LTE_eVoLTE",1,"Rel-14","R2","2016-03-15","2016-09-15",1,"RP-160902","-","CMCC",null,"1/7/16: Compl:0%->75%1/7/16: WI¦28/7/16: 36.750 added¦26/9/16: Compl:75%->100%",36.75,71,36,null,null,"2016-03-22","2016-09-26"]
[3489,710060,"Study on Context Aware Service Delivery in RAN for LTE","FS_LTE_context",1,"Rel-14","R3","2016-03-15","2017-03-15",1,"RP-160906",null,"CMCC",null,"1/7/16: Compl:0%->25%1/26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->70% ¦21/3/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3492,660058,"Study on Interactivity Support for 3GPP-based Streaming and Download Services","FS_IS3",1,"Rel-14","S4","2014-12-12","2017-03-10",1,"SP-140742",null,"Lo, Charles, Qualcomm ","clo@qti.qualcomm.com","TR number added. Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->30, FCD: 12/15->03/16¦7/3/16: 30%->40. 15/4/16: moved from Rel-13. FCD: 11/3/16->23/9/16¦11/6/16: 40%->50¦19/9/16: 50%->70, FCD:09/16->12/16¦1/12/16: 70%->80;",26.952999999999999,66,34,null,null,"2014-12-12","2017-03-06"]
[3496,720089,"Study on Downlink MIMO for GERAN","FS_DOMIMO_RAN6",1,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161261",null,"Nokia, Alcatel-Lucent Shanghai Bell",null,"continuation of GERAN SI UID 590034, DOMIMO under RAN626/9/16: Compl:0%->100%",null,72,37,null,null,"2016-07-01","2016-09-26"]
[3499,670008,"   General aspects of FS_SMARTER SA1","FS_SMARTER",2,"Rel-14","S1","2015-02-02","2016-02-12",1,"SP-150142",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","7/12/15: 60%->85¦2/3/16: 85%->95¦7/6/17: 95%->100","New 22.891",67,34,null,null,"2015-03-04","2017-06-07"]
[3502,700025,"   FS_SMARTER – enhanced Mobile Broadband","FS_SMARTER-eMBB",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150819",null,"Laurence Meriau","laurence.meriau@huawei.com","2/3/16: 40%->75¦9/6/16: 75%->100","New 22.863",70,36,null,null,"2015-12-07","2016-06-09"]
[3503,700026,"   FS_SMARTER – Network Operation","FS_SMARTER-NEO",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150820",null,"Lu Lu","lulu@chinamobile.com","2/3/16: 30%->60¦19/9/16: 60%->100","New 22.864",70,36,null,null,"2015-12-07","2016-09-19"]
[3506,0,"--- RELEASE 13 ---","-",1,"Rel-13","SP,RP,CP,GP","2013-12-11","2014-11-25",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[3510,670032,"   Study on Security Enhancements for MCPTT","MCPTT",2,"Rel-13","S3","2015-03-13","2016-03-11",1,"SP-150356",null,"Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated¦7/12/15: 0%->75¦10/12/15: FCD->March, ES in SP-150729¦7/3/16: 75%->80¦28/7/16: 33.280 added¦28/7/16: 39.880 added¦1/12/16: 80%->100","33.879; 33.280; 39.880",67,34,null,null,"2015-03-13","2016-12-01"]
[3513,640143,"   Functional architecture and information flows to support MCPTT","MCPTT",2,"Rel-13","S6","2015-06-18","2015-12-11",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","June2015: added as per SP-150356¦June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID¦07/09/15: 15%->50¦07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15¦7/3/16: 85%->100","New 23.179",64,33,null,null,"2014-06-04","2016-03-07"]
[3516,690011,"   MCPTT protocol aspects","MCPTT-CT",2,"Rel-13","ct","2015-09-07","2016-06-30",0.96,"CP-150793",null,"Keith Drage, Alcatel-Lucent",null,"7/12/15: WID:CP-150587->CP-150793¦28/1/16: 24.384 added;",null,69,35,null,null,"2015-09-07","2016-01-28"]
[3520,690098,"         Floor Control – On Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->80¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 80%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.38,69,35,null,null,"2015-09-29","2016-12-05"]
[3523,691001,"         Group management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.381,69,35,null,null,"2015-09-29","2016-12-05"]
[3526,710033,"         Configuration management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Introduced from CT1 WP update in 03/16¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.384,71,36,null,null,"2016-03-07","2016-12-05"]
[3527,690028,"      CT3 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-160817",null,"Alcatel-Lucent, Keith Drage","keith.drage@alcatel-lucent.com","7/12/15: 0%->70¦7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150643¦7/3/16: 70%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",29.164999999999999,69,35,null,null,"2015-09-07","2016-12-05"]
[3530,710034,"      (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",0.25,"CP-160817",null,"Ericsson","christer.holmberg@ericsson.com","5/12/16: WID:CP-160160->CP-160817","draft-holmberg-dispatch-mcptt-rp-namespace",71,36,null,null,"2016-03-07","2016-12-05"]
[3534,640062,"   Deleted: SA2 aspects for MCPTT","MCPTT",2,"Rel-13","S2","2015-03-13","2015-03-13",1,"SP-150356","-","Randy Bloomfield (randy@its.bldrdoc.gov)","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: transferred to SA6. Was 06/14 to 06/15. 6/15: WID updated","New 23.179",64,33,"SP-69",null,"2014-06-04","2015-06-18"]
[3537,670024,"MBMS Extensions and Profiling","MEPRO",1,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","1/4/15: TS number added¦14/09/15: WID:SP-150099->SP-150439","26.346, new 26.852",67,34,null,null,"2015-03-05","2015-09-14"]
[3541,680047,"   Stage 1 fo Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-150463","S1-143304","General Dynamics","paul.piggin@gd-broadband.com","SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463","New 22.346",63,32,null,null,"2014-02-05","2015-09-14"]
[3545,700038,"      CT6 aspects for IOPS","IOPS-CT",3,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com","ES in CP-150837¦7/3/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-03-07"]
[3548,650019,"Flexible Mobile Service Steering","FMSS",1,"Rel-13","S1,S2","2014-09-15","2016-03-11",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS)",22.100999999999999,65,33,null,null,"2013-11-26","2014-08-28"]
[3549,650055,"   Stage 1 for Flexible Mobile Service Steering","FMSS-ST1",2,"Rel-13","S1","2014-09-15","2014-09-17",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS). Dec.14: moved from Feature to S1 BB",22.100999999999999,65,33,null,null,"2013-11-26","2014-12-03"]
[3552,690024,"   CT3 Aspect of Flexible Mobile Service Steering","FMSS-CT",2,"Rel-13","C3","2015-09-09","2016-03-11",1,"CP-150799",null,"ZTE,Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100","29.abc, 29.212, 29.213",69,35,null,null,"2015-09-09","2016-03-07"]
[3555,660013,"   Stage 1 for Application specific Congestion control for Data Communication","ACDC-ST1",2,"Rel-13","S1","2014-06-18","2014-09-17",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","Results from MCC Split of the SA1 feature into F+BB for stage 1",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[3559,670059,"   RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150512",null,"LG Electronics",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3562,570129,"   Stage 1 for User Plane Congestion management","UPCON-ST1",2,"Rel-13","S1","2012-09-12","2013-03-06",1,"SP-140631","-","KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101. 3/3/15: start date corrected (was Mar 12)",22.100999999999999,57,29,null,null,"2012-08-06","2015-03-03"]
[3565,630019,"   BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON",2,"Rel-13","S2","2014-03-07","2015-03-13",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control","-",63,32,null,null,"2014-03-04","2014-09-16"]
[3569,650207,"         CT4 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C4","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->20¦WID: CP-140734->CP-140929. Mar. 15: 50%¦June2015: Compl:50%->90. WID: CP-140929-> CP-150365.¦07/09/15: 90%->100","23.003, 29.303, New 29.405 (UPCON over Nq)",65,33,null,null,"2014-07-29","2015-09-07"]
[3572,650028,"Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",1,"Rel-13",null,"2014-09-09","2017-03-15",0.95,"SP-140483","-","Intel","ozgur.oyman@intel.com","Can be seen as an \"enhancement\" of Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042. Mar. 15: 20%","-",65,33,null,null,"2014-09-05","2015-03-05"]
[3573,650128,"   TR on Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",2,"Rel-13","S4","2014-09-09","2015-09-16",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100","New 26.9xy",65,33,null,null,"2014-09-05","2015-12-07"]
[3576,710036,"   (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",0.9,null,null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90; 9/4/21: RFC 8849 added;","26.22; RFC 8849",71,36,null,null,"2016-03-07","2021-04-09"]
[3579,600045,"RAN Sharing Enhancements","RSE",1,"Rel-13","S1,R3","2013-06-19","2015-12-15",1,"SP-130330","-","NEC","joerg.swetina@neclab.eu","Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","-",60,31,null,null,"2013-06-03","2013-11-26"]
[3583,630014,"Enhancements to WEBRTC interoperability","eWebRTCi",1,"Rel-13","S1,S2,S3","2014-03-07","2016-06-16",0.99,"SP-140630","-","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part, SA1 change). Add enhanced interoperability support for WebRTC to Rel-12 Web Real Time Communication (WebRTC) Access to IMS.","Stage 1/2",63,32,null,null,"2014-02-05","2014-09-16"]
[3586,640038,"   Stage 2 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140630","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part)¦June2015: Compl:0%->85¦07/09/15: 85%->100",23.228000000000002,64,33,null,null,"2014-06-12","2015-09-07"]
[3590,690012,"   Stage 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",2,"Rel-13","ct","2015-09-07","2016-06-16",0.97,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767",null,69,35,null,null,"2015-09-07","2015-12-07"]
[3593,690016,"      CT4 aspects for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C4","2015-09-07","2016-03-11",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150623¦7/3/16: 0%->100","29.228, 23.334, 29.334, 23.008",69,35,null,null,"2015-09-07","2016-03-07"]
[3596,710041,"      (IETF) A Language for Rules Describing JSON Content (draft-newton-json-content-rules)","eWebRTCi-CT",3,"Rel-13","C3-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates. This individual draft will not further progress in IETF but is kept as reference in version -09; 23/4/20: 25%->100","24.371, 24.229, 26.223",71,36,null,null,"2016-03-07","2020-04-23"]
[3597,870074,"      Deleted - (IETF) Oauth 2.0 Proof-of-Possession (PoP) Security Architecture (draft-ietf-oauth-pop-architecture) ","eWebRTCi-CT",3,"Rel-13","S3-IETF","2015-12-08","2016-06-16",1,null,null,null,null,"9/4/21: 25%->100",null,87,44,null,null,"2016-03-07","2021-04-09"]
[3602,650100,"   RAN aspects for improvements to CS/PS coordination in GERAN Shared Networks","CSPS_Coord_GERAN",2,"Rel-13","G2","2015-03-11","2016-05-12",1,"GP-150225",null,"Nicklas Johansson, Ericsson LM","Nicklas.Johansson@Ericsson.com","June2015: Compl:0%->35¦07/09/15: 35%->50, FCD:08/15->11/15¦7/12/15: 50%->95, FCD: 12/15->02/16. 02/03/16: FCD: 02/16->05/16¦13/6/16: 95%->100","48.008, 48.018",65,33,null,null,"2015-05-07","2016-06-13"]
[3604,640140,"   Stage 1 for Enhancements to Proximity-based Services","eProSe-SA1",2,"Rel-13","S1","2014-06-19","2014-09-17",1,"SP-140386","-","Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced.","22.115, 22.278",64,33,null,null,"2014-05-27","2014-09-03"]
[3608,680006,"   CT aspects of enhancements to Proximity-based","eProSe-Ext-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,"23.122, 24.301, 24.333, 24.334",68,35,null,null,"2015-06-15","2015-06-15"]
[3611,680009,"      CT4 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->10¦7/12/15: 10%->80. FCD->03/16. ES in CP-150616¦7/3/16: 80%->100","31.102, 31.111",68,35,null,null,"2015-06-15","2016-03-07"]
[3615,640045,"voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD",1,"Rel-13","S1,S2,C4,C1,C3","2014-06-16","2014-12-12",1,"SP-140394","-","Alcatel-Lucent","(betsy.covell@alcatel-lucent.com)","-","Stage 1/2",64,33,null,null,"2014-05-29","2014-06-11"]
[3618,650003,"   CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",2,"Rel-13","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Stage 3","Stage 3",65,33,null,null,"2014-07-29","2014-07-29"]
[3621,650303,"      CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Mar.15: 0->100%",29.061,65,33,null,null,"2014-07-29","2015-03-04"]
[3622,640047,"IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM",1,"Rel-13","S2","2014-06-18","2016-06-15",1,"SP-150250","-","Tricci So, ZTE","tso@zte.com.cn","06/15: WID: SP-140279->SP-150250","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[3625,690043,"   Charging Aspects of IP Flow Mobility support for S2a and S2b Interfaces (NBIFOM) ","NBIFOM-CH",2,"Rel-13","S5","2015-09-16","2016-06-15",1,"SP-150406",null,"GUO Wenjie, ZTE","guo.wenjie1@zte.com.cn","7/12/15: 0%->50. ES in SP-150710 (wrong UID mentioned in the ES)¦7/3/16: 50%->85%, FCD:03/16->06/16¦13/6/16: 85%->100","32.251, 32.298, 32.299",69,35,null,null,"2014-05-30","2016-06-13"]
[3628,680021,"      CT3 aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",3,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150874",null,"680001Xingyue(Joy) Zhou, ZTECorporation. ES in 641","zhou.xingyue@zte.com.cn","07/09/15: 0%->40¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 40%->95¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 95%->100","29.212, 29.213, 29.214, 29.215",68,35,null,null,"2015-06-15","2016-03-07"]
[3632,660019,"   CT aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",2,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,null,"24.229, 24.615, 24.610, 24.605, 29.212, 29.213, 29.214, 29.215",66,34,null,null,"2014-12-04","2014-12-04"]
[3635,640056,"Lawful Interception in the 3GPP Rel-13","LI13",1,"Rel-13","S3","2014-06-18","2016-12-15",1,"SP-160043","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com","SP#65 updated WID SP-140400=>SP-140578. 2/4/15: WID SP-140815->SP-150111¦June2015: Compl:0%->10. WID: SP-150111->SP-150290¦14/09/15: WID:SP-150290->SP-150460¦7/12/15: 10%->15¦7/3/16: 13%->20¦7/3/16: WID:SP-150460->SP-160043¦19/9/16: 20%->60. FCD","33.106, 33.107, 33.108",64,33,null,null,"2014-06-11","2016-12-01"]
[3639,680017,"   CT Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","14/09/15: WID:CP-150241->CP-150425",null,68,35,null,null,"2015-06-15","2015-09-14"]
[3642,680034,"      CT4 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->5¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 5%->100","23.334, 29.334, 29.238",68,35,null,null,"2015-06-15","2015-12-07"]
[3645,650226,"   Specification on TV video profile","TVProf-SA4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16. ES in SP-150650¦7/3/16: 85%->100","26.234, 26.244, 26.346, 26.247, New 26.xyz. ES in SP-150650",65,33,null,null,"2014-09-05","2016-03-07"]
[3646,650027,"Enhanced LTE UE Delay test methods and requirements","E_LTE_UED",1,"Rel-13","S4","2014-09-09","2016-06-15",1,"SP-140482","-","Orange","stephane.ragot@orange.com","Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->50¦7/12/15: 50%->80, FCD: 12/15->03/16. ES in SP-150652¦7/3/16: FCD: 03/16->06/16¦11/6/16: 80%->100","26.131, 26.132",65,33,null,null,"2014-09-05","2016-06-11"]
[3649,670016,"   SA4 aspects of EVS in 3G Circuit-Switched networks","EVSoCS-S4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%¦Aug2015: 10%->20¦07/09/15: 20%->40¦7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103, 28.062, New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-03-07"]
[3653,670019,"      CT4 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","June2015: Compl:0%->95. FCD -> 03/16, ES in CP-150618¦7/3/16: 95%->100","23.153, 23.334, 29.002, 29.231, 29.232, 29.332, 29.334",67,34,null,null,"2015-03-04","2016-03-07"]
[{"$f":"A3656+1","v":3656},650031,"Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP)","eDASH",1,"Rel-13","S4","2014-09-09","2015-12-16",1,"SP-150448","-","Qualcomm, Huawei","Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com)","Triggered by Rel-12 Dec.14: 0->10%. Mar. 15: 15%¦June2015: Compl:15%->25. WID updated¦Aug2015: 25%->30¦07/09/15: 30%->60¦14/09/15: WID:SP-150211->SP-150448¦7/12/15: 60%->100","26.233, 26.234, 26.244, 26.247, 26.938, 26.346, 26.946",65,33,null,null,"2014-09-05","2015-12-07"]
[3659,650132,"   SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",2,"Rel-13","S4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65: WID SP-130670=>SP-140601 (moved from Rel12 incl. new TR to Rel-13). FCD 03/15=>06/15. St1 in TS 22.173. 12/14: 70->40%, CD: 06/15->09/15. 03/15: 50%. June 15: FCD: 09/15->12/15¦08/15: 60%¦09/15: 75%¦7/12. ES in SP-150658¦7/3/16: 90%->100",26.114000000000001,59,30,null,null,"2013-02-20","2016-03-07"]
[3663,660046,"      CT4 Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",3,"Rel-13","C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,"FCD -> 03/16, ES in CP-150620¦7/3/16: 0%->100","23.333, 23.334, 29.238, 29.332, 29.333, 29.334",66,34,null,null,"2014-12-09","2016-03-07"]
[3667,720062,"   (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","MMCMH",2,"Rel-13","S4-IETF","2015-12-07","2016-03-07",0.9,null,null,null,null,"Was (IETF) (draft-ietf-mmusic-sdp-simulcast); 23/4/20: 0%->90; 9/4/21: RFC 8853 added;","RFC 8853",72,37,null,null,"2016-06-13","2021-04-09"]
[3670,660251,"   Specification on Video Telephony Robustness Improvements","VTRI_EXT",2,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","3/3/15: created to distinguish TR and TS tasks¦June2015: Compl:10%->40¦Aug2015: 40%->95¦07/09/15: 95%->100","26.922 (new), 26.114",66,34,null,null,"2015-03-03","2015-09-07"]
[3671,690038,"   (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627","VTRI_EXT",2,"Rel-13","S4-IETF","2014-12-12","2015-09-11",1,"SP-15047",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added; 23/4/20: 10%->100","26.114, draft-ietf-payload-flexible-fec-scheme",69,35,null,null,"2015-03-03","2020-04-23"]
[3674,560132,"   Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","SON-NM-CCO",2,"Rel-13","S5","2014-09-19","2015-12-11",1,"SP-140060","-","Ericsson","robert.petersen@ericsson.com","SP#64 work not started. Dec.14: 0->20, cd: 06/15->12/15. Mar 15: 20->30%¦June2015: Compl:30%->50¦07/09/15: 50%->60¦7/12/15: 60%->100","28.627, 28.628, 32.103, 32.422, 32.425, 32.442",56,29,null,null,"2012-04-18","2015-12-07"]
[3678,560235,"   Converged management Performance Management Interface Definitions","OAM-PMID",2,"Rel-13","S5","2012-06-20","2015-12-11",1,"SP-150678","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678","new TSs 32.863 ",56,29,null,null,"2012-05-14","2015-12-07"]
[3681,560236,"      WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface","WLAN-OAM-SA5ietf",3,"Rel-13","S5","2012-06-27","2015-06-17",1,"SP-140535","-","Intel","joey.chou@intel.com","SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified¦June2015: Compl:5%->20¦07/09/15: 20%->60¦7/12/15: 60%->100","new 28.403",56,29,null,null,"2012-06-12","2015-12-07"]
[3684,641000,"Rel-13 Charging","CH13",1,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-150307","-","-","-","CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150307","-",64,33,null,null,"2014-06-06","2015-06-18"]
[3688,660056,"   ULI and release causes for charging enhancement for VoLTE","ULRELC-CH",2,"Rel-13","S5","2014-12-12","2015-12-07",1,"SP-140785",null,"Alcatel-Lucent, Maryse Gardella","Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com","Acronym changed to ULRELC-CH. Mar15: 0->5%. CD: 12/14->09/15. 06/15: 20%¦07/09/15: 20%->40¦7/12/15: 40%->100, FCD: 09/15->12/15","32.251, 32.260, 32.299, 32.298, ",66,34,null,null,"2014-12-12","2015-12-07"]
[3691,680038,"   Enhanced S2a Mobility Over Trusted WLAN access to EPC - Charging ","eSaMOG-CH",2,"Rel-13","S5","2015-06-15","2015-09-17",1,"SP-150344",null,"Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com",null,"07/09/15: 0%->30¦7/12/15: 30%->100","32.240, 32.251, 32.299, 32.298",68,35,null,null,"2015-06-14","2015-12-07"]
[3694,610205,"   CT1 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C1","2013-09-13","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15¦7/12/15: 0%->100",24.228999999999999,61,31,null,null,"2013-08-10","2015-12-07"]
[3695,610305,"   CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C3","2013-09-13","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15¦8/12/15: 0%->100","29.213, 29.214",61,31,null,null,"2013-08-10","2015-12-08"]
[3698,550217,"   Perf. Part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US-Perf",2,"Rel-13","R4","2012-03-05","2015-06-09",0.05,"RP-121397","RP-141452","LightSquared","masoud.olfat@lightsquared.com","RP#65 completion 06/15=>09/15. . On hold till 12/2014","25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.113, 36.124, 36.133, 36.141, 36.307",55,28,null,null,"2012-02-23","2014-09-09"]
[3702,640136,"   Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Core",2,"Rel-13","R4","2014-06-17","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:5%->15%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL), New 36.862 (Technical Report for 2 GHz Band in Region 1)",64,33,null,null,"2014-06-16","2016-01-01"]
[3705,650034,"Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments","UTRA_LTE_SON_AAS",1,"Rel-13","R3,G2","2014-09-12","2015-06-15",1,"RP-141624","-","Nokia Networks","krzysztof.kordybach@nsn.com","Triggered by TR 37.822 Study on Next-Generation SON for UTRA and LTE (FS_UTRA_LTE_NG_SON)","LTE",65,33,null,null,"2014-06-16","2014-09-16"]
[3708,660022,"   Stage 2 of Usage Monitoring Control PCC Extension","eUMONC-SA2",2,"Rel-13","S2","2014-12-03","2015-06-16",1,"SP-140709",null,"China Telecom, Jinyan Li","lijy@ctbri.com.cn","June2015: Compl:6%->100. Verbal indication from SA2 chair",23.202999999999999,66,34,null,null,"2014-12-03","2015-06-15"]
[3712,660023,"   CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",2,"Rel-13","C4","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,"Mar.15: 0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN","29.274, 29.275",66,34,null,null,"2014-12-04","2015-05-05"]
[3715,660040,"   CT4 aspects of P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",2,"Rel-13","C4","2014-12-03","2015-12-11",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","Dec.14: 0->5%. Mar.15: 5->100%. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:100%->75. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 75%->85¦7/12/15: 85%->100","New 29.8xy, 23.380, 29.273, 29.274, 29.275, 23.008",66,34,null,null,"2014-12-09","2015-12-07"]
[3716,680012,"Mobile Equipment Identity signalling over WLAN ","MEI_WLAN",1,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com",null,"24.244, 24.302, 29.273, 29.274, 29.275, 23.008",68,35,null,null,"2015-06-15","2015-06-15"]
[3719,680041,"Authentication Signalling Improvements for WLAN","ASI_WLAN",1,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150330",null,"Youyang Yu","yuyouyang@huawei.com","07/09/15: 0%->40¦7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727¦7/3/16: 95%->100","24.302, 24.244",68,35,null,null,"2015-06-15","2016-03-07"]
[3724,660034,"Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",1,"Rel-13","C1,C3","2014-12-03","2015-03-13",0.74,"CP-140928",null,"Orange",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[3727,660021,"   CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",2,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140928",null,"Orange",null,"Mar.15: 80->90%. WID changed from INNB_IW-CT3¦June2015: Compl:0%->98¦07/09/15: 98%->99¦7/12/15: 99%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3730,660029,"   CT4 aspects of Warning Status Report in EPS","WSR_EPS",2,"Rel-13","C4","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from \"WSR_EP\"¦7/12/15: 0%->100¦7/12/15: WID:CP-140998->CP-150792",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3733,670096,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3737,670020,"H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",1,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du","duxiaoning@chinamobile.com",null,23.334,67,34,null,null,"2015-03-04","2015-03-09"]
[3740,670026,"Review of dedicated 3GPP UICC features","Red_UCe",1,"Rel-13","C6","2015-03-09","2015-12-11",1,"CP-150152",null,"Blackberry, Adrian Buckley","abuckley@blackberry.com","Results from the homonymous Study¦June2015: Compl:0%->60¦07/09/15: 60%->75¦7/3/16: 75%->100","31.102, 31.111, 31.121, 31.124",67,34,null,null,"2015-03-09","2016-03-07"]
[3741,680014,"Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",1,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com",null,"23.334, 29.334, 29.162, 29.238, 23.333, 29.333, 29.163, 29.332, 29.292, 29.232, 29.235",68,35,null,null,"2015-06-15","2015-06-15"]
[3744,640044,"(SA66: on hold) Co-ordinated packet data network gateway (P-GW) change for SIPTO","CSIPTO",1,"Rel-13","S1","2014-06-18","2014-09-16",1,"SP-140509","S1-143306","Intel","Eric.siow@intel.com","SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO)",22.100999999999999,64,33,null,null,"2014-05-27","2014-12-12"]
[3747,640151,"   TR for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S2","2014-06-18","2014-12-12",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Dec.14: 35->85%¦14/09/15: 85%->100. SA#69: decision not to continue the work on this. No normative work.","New 23.772",64,33,null,null,"2014-06-11","2015-09-14"]
[3751,650125,"   TR for SRVCC Enhancements for Transcoding Avoidance","SETA-SA2TR",2,"Rel-13","S2","2014-09-19","2015-03-13",1,"SP-140436","-","Ericsson","George.Foti@ericsson.com","Dec.14: 0->70%¦14/09/15: 70%->100. Stopped without conclusion, no intention to continue the study nor to do any mormative work.","New 23.7xy",65,33,null,null,"2014-08-05","2015-09-14"]
[3754,590130,"   Core part: Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA-Core",2,"Rel-13","R4","2013-03-04","2016-03-15",1,"RP-160188","RP-151241","Huawei","ronnie.zhang@huawei.com","¦CD:Thu 11/12/14->Tue 15/12/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241¦","New 37.142 (AAS BS Tx & Rx), New 37.842, 37.114, 37.145-1, 37.145-2",59,30,null,null,"2013-02-26","2016-03-22"]
[3758,660274,"   Perf. part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Perf",2,"Rel-13","R4","2014-12-15","2016-09-15",1,"RP-150441","RP-151337","Qualcomm","Qualcomm","1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Stat Rep: RP-150795->RP-151337¦1/1/16: CD¦22/3/16: Compl:0%->10%;26/9/16: Compl:85%->100%",null,66,34,null,null,"2015-01-12","2016-09-26"]
[3761,660077,"UE core requirements for uplink 64 QAM","LTE_UL64QAM",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-142222",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3764,660078,"Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS",1,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-142223",null,"China Telecom","China Telecom",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3765,660278,"   Perf. part: Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS-Perf",2,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-150206","RP-151215","China Telecom","China Telecom","1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142223->RP-150206 1st Apr 15: Stat Rep: ->RP-150204 03/07/15: Compl:10%->35% 03/07/15: Stat Rep: RP-150204->RP-150630 29/09/15: Compl:35%->50% 29/09/15: Stat Rep: RP-150630->RP-151215¦",null,66,34,null,null,"2015-01-12","2016-07-01"]
[3768,670055,"Dual Connectivity enhancements for LTE","LTE_dualC_enh",1,"Rel-13","R2","2015-03-16","2016-06-15",1,"RP-150490",null,"NTT DOCOMO",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3771,670056,"Multicarrier Load Distribution of UEs in LTE","LTE_MC_load",1,"Rel-13","R2","2015-03-16","2016-09-15",1,"RP-150491",null,"ZTE",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3775,670158,"   Core part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Core",2,"Rel-13","R2","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081, 07/08/15: impacted TSs added 29/09/15: Compl:30%->35% 29/09/15: Stat Rep: RP-151081->RP-151563;","36.461, 36.462, 36.463, 36.464, 36.465, 36.622, 36.623, 36.624, 36.625, 36.360",67,34,null,null,"2015-04-01","2016-03-22"]
[3778,670060,"RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network","CSPS_Coord-UTRA",1,"Rel-13","R3","2015-03-16","2015-12-15",1,"RP-150500",null,"Ericsson",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3782,670261,"   Perf. part: LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-Perf",2,"Rel-13","R4","2000-01-03","2016-09-15",1,"RP-161237","RP-151265","Ericsson",null,"03/07/15: Compl:0%->15% 03/07/15: CD:Mon 02/10/00->Wed 15/06/16 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:15%->35% 29/09/15: Stat Rep: RP-150803->RP-15126522/3/16: Compl:60%-;26/9/16: Compl:90%->100%",null,67,34,null,null,"2015-04-01","2016-09-26"]
[3785,670162,"   Core part: AWS-Extension Band for LTE","LTE_AWS_EXT-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150800","RP-151343","Ericsson",null,"03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3789,670163,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150602","RP-150536","Nokia Networks",null,"03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3790,670263,"   Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset-Perf",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150602","RP-150536","Nokia Networks",null,"03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3793,670264,"   Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset-Perf",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425","RP-150536","Samsung",null,"03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3796,680044,"Message interworking during PS to CS SRVCC ","mSRVCC",1,"Rel-13","C1","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com",null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[3800,680051,"   Stage 2 of Support of Emergency services over WLAN - phase 1","SEW1",2,"Rel-13","S2","2015-06-18","2015-09-16",1,"SP-150253",null,"Laurent thiebaut","Laurent.thiebaut@alcatel-lucent.com ","07/09/15: 0%->100","23.402, 23.167, 23.271, 23.203, 23.228",68,35,null,null,"2015-06-18","2015-09-07"]
[3803,690025,"      CT3 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C3","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 0%->100","29.212, 29.214",69,35,null,null,"2015-09-07","2015-12-07"]
[3807,660010,"   MBMS Enhancements TR Phase","FS_MBMS_enh_TR",2,"Rel-13","S2","2014-12-03","2015-09-14",1,"SP-150516",null,"Nokia Networks, Curt Wong",null,"Acronym changed from \"MBMS_enh-SA2TR\". Mar15: 0->10%¦June2015: Compl:10%->50¦07/09/15: 50%->70. acronym changed from \"MBMS_enh\" to \"MBMS_enh_TR\"¦07/09/15: 70%->100¦14/09/15: WID:SP-140883->SP-150516","23.8xy",66,34,null,null,"2014-12-03","2015-09-14"]
[3810,700035,"      CT3 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C3","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,"8/12/15: 0%->100","29.061, 29.468",70,36,null,null,"2015-12-07","2015-12-08"]
[3813,690002,"EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",1,"Rel-13","C4","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[3814,690026,"   CT3 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100","29.212, 29.213",69,35,null,null,"2015-09-07","2015-12-08"]
[3817,700009,"   CT3 aspects of DiaPri","DiaPri",2,"Rel-13","C3","2015-11-02","2016-03-11",1,"CP-150613",null,"Intel, Vivek Gupta",null,"ES in CP-150645¦7/3/16: 65%->100","29.153, 29.154, 29.201, 29.212, 29.213, 29.214, 29.215, 29.217, 29.219",70,36,null,null,"2015-12-07","2016-03-07"]
[3821,680159,"   Core part: Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC-Core",2,"Rel-13","R1,R2,R3","2015-10-15","2015-12-15",1,"RP-151880","RP-151564","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3824,680160,"   Core part: Licensed-Assisted Access using LTE","LTE_LAA-Core",2,"Rel-13","R1","2015-06-15","2015-12-15",1,"RP-151045","RP-151390","Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-1513901/1/16: Compl:25%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3827,680061,"Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO",1,"Rel-13","R1","2015-06-15","2018-12-14",0.99,"RP-151085","-","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3831,680062,"L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23",1,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-151043","-","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3834,680164,"   Core part: Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-151110","RP-151237","Huawei",null,"follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151237 1/1/16: Compl:30%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3837,680065,"Extension of Dual Connectivity in E-UTRAN","LTE_dualC_ext",1,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151008","-","Samsung",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_dualC_ext;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3838,680165,"   Core part: Extension of Dual Connectivity in E-UTRAN","LTE_dualC_ext-Core",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151798","RP-151214","Samsung",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_dualC_ext¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151214¦1/1/16: Compl:3",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3841,680071,"Interference mitigation for downlink control channels of LTE","LTE_IM_DLCCH",1,"Rel-13","R4","2015-06-15","2018-09-14",0.99,"RP-151107","-","Intel",null,"only Perf. part, no Core part;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[3845,690162,"   Core part: Network-Assisted Interference Cancellation and Suppression for UMTS","UTRA_NAICS-Core",2,"Rel-13","R1","2015-09-15","2015-12-15",1,"RP-151879","-","Huawei",null,"no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS ¦1/1/16: Compl:0%->100% ¦1/1/16: WID: RP-151577->RP-151879",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3850,690165,"   Core part: Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2-Core",2,"Rel-13","R2","2015-09-15","2015-12-15",1,"RP-151611","-","CMCC",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_eMDT2¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[3852,690066,"LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy",1,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-151615","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio",null,69,35,null,null,"2015-09-29","NA"]
[3856,690267,"   Perf. part: Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh-Perf",2,"Rel-13","R4","2015-09-15","2016-06-15",1,"RP-160332","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh 1/1/16: Compl:0%->10% 1/1/16: WID: RP-151624->RP-152251¦22/3/16: Compl:10%->20%¦22/3/16: WID: RP-152251->RP-160332 28/7/16: 37.171 added¦28/7/16: 37.958 added;","37.171; 37.958",69,35,null,null,"2015-09-29","2016-07-28"]
[3859,720099,"   UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS","UTRA_LTE_iPos_enh-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-170233",null,"NextNav",null,"tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl:",null,72,37,null,null,"2016-07-01","2017-03-21"]
[3862,700256,"   Perf. Part: Power saving enhancements for UMTS","UTRA_SDATA_POWSAV-Perf",2,"Rel-13","R4","2015-12-15","2016-03-15",1,"RP-151998",null,"Ericsson",null,"¦22/3/16: Compl:0%->100%",null,70,36,null,null,"2016-01-01","2016-03-22"]
[3863,680073,"700MHz E-UTRA FDD Band for Arab Region","LTE_FDD_700_ARAB",1,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151042","-","Etisalat",null,"REL-independent from REL-9",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3866,680075,"European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150861","-","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it",null,68,35,null,null,"2015-07-03","2015-07-03"]
[3870,620063,"Service Requirements Maintenance for Machine-Type Communications (MTC)","SRMMTC",1,"Rel-13","S1","2015-09-15","2016-06-10",1,"SP-130600","-","KPN","toon.norp@tno.nl","SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13.",22.367999999999999,62,32,null,null,"2013-11-26","2014-09-03"]
[3873,700046,"   Security Aspects of CIoT (aka NB-IoT)","CIoT",2,"Rel-13","S3","2015-11-02","2016-06-10",1,"SP-150844",null,"Tim Evans, Vodafone",null,"7/3/16: 0%->39¦19/9/16: 39%->100",33.401000000000003,70,36,null,null,"2015-12-07","2016-09-19"]
[3876,700051,"      CT3 aspects of CIoT","CIoT-CT",3,"Rel-13","C3","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->90¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 90%->100","29.061, 29.212",70,36,null,null,"2015-12-07","2016-06-13"]
[3880,690063,"   RAN aspects of CIoT aka Narrowband Internet of Things (IOT)","NB_IOT",2,"Rel-13","R1","2015-09-15","2016-12-15",1,"RP-151621","-","Vodafone",null,"no Perf. part¦note: WI only stays in REL-13 because of PCG decision",null,69,35,null,null,"2015-09-29","NA"]
[3883,720043,"   Management for NB-IoT","NB_IOT-OAM",2,"Rel-13","S5","2016-05-12","2016-06-15",1,"SP-160396",null,"Huawei, Kai ZHANG","kai.zhangkai@huawei.com","13/6/16: 0%->100","28.657, 28.658, 28.659, 32.425",72,37,null,null,"2016-06-13","2016-06-13"]
[3884,710065,"   UE Conformance Test Aspects - Narrowband Internet of Things (NB-IOT)","NB_IOT-UEConTest",2,"Rel-13","R5","2016-03-15","2017-12-15",1,"RP-160047",null,"CMCC",null,"testing REL-13 NB_IOT-Core1/7/16: Compl:0%->5%¦26/9¦20/12/1¦21/3/17: Compl: ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3887,700004,"   Test for CIoT_EC_GSM","CIoT_EC_GSM_GERAN3new",2,"Rel-13","G3","2015-11-11","2016-05-12",0,"GP-151149",null,"Sierra Wireless S.A","Marteen.Sunberg@Ericsson.com","7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new",null,70,36,null,null,"2015-09-07","2016-03-02"]
[3890,690005,"Extended DRX cycle for Power Consumption","eDRX",1,"Rel-13","S2,R2,G2","2014-12-03","2016-09-15",0.93,"SP-150369",null,"Miguel Griot","mgriot@qti.qualcomm.com","June2015: WID:SP-150254->SP-150369","23.401, 23.060, 23.682, 23.271, 23.272",68,35,null,null,"2015-06-18","2015-06-18"]
[3894,690020,"      CT1 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100","24.301, 24.008, 29.118",69,35,null,null,"2015-09-07","2016-03-07"]
[3897,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[3900,710071,"   UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE","LTE_extDRX-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-160602","-","Qualcomm",null,"testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT;",null,71,36,null,null,"2016-03-22","2016-09-26"]
[3904,670027,"Optimizations to Support High Latency Communications","HLcom",1,"Rel-13","S2","2014-09-19","2015-12-16",1,"SP-150030",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com",null,"23.401, 23.060, 23.682",67,34,null,null,"2015-03-05","2015-03-05"]
[3907,680015,"   CT aspects of Optimizations to Support High Latency","HLcom-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150399",null,"Yong Yang, Ericsson","frank.yong.yang@ericsson.com","07/09/15: 0%->80¦7/12/15: 80%->100","29.274, 29.060, 29.281, 23.008, 29.272, 29.230, 29.002, 29.336, 29.xyz",68,35,null,null,"2015-06-15","2015-12-07"]
[3911,710067,"   UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-UEConTest",2,"Rel-13","R5","2016-03-15","2017-09-15",1,"RP-171156",null,"Ericsson",null,"testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[{"$f":"A3912+1","v":3912},690045,"EGPRS Access Security Enhancements in relation to Cellular IoT","EASE_EC_GSM",1,"Rel-13","S3","2015-09-16","2016-03-11",1,"SP-150462",null,"Vesa Torvinen, Ericsson",null,"7/12/15: 0%->5¦28/1/16: 33.420 added¦7/3/16: 5%->80¦11/6/16: 80%->98¦19/9/16: 98%->99¦21/3/17: 99%->100->99%¦7/6/17: 99%->100","New 33.420",69,35,null,null,"2015-09-16","2017-06-07"]
[3915,640250,"   Stage 2 for Group based Enhancements","GROUPE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140706","-","Huawei","ZhangWanqiang@huawei.com","Mar15: 0->20%¦June2015: Compl:20%->100","23.682, TBD",64,33,null,null,"2014-05-30","2015-06-15"]
[3919,680028,"      CT1 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->15¦7/12/15: 15%->100¦7/12/15: WID:CP-150240->CP-150816","24.008, 24.301",68,35,null,null,"2015-06-15","2015-12-07"]
[3922,640049,"Monitoring Enhancements","MONTE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140705","-","Intel","puneet.jain@intel.com","Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added;",32.277999999999999,64,33,null,null,"2014-05-30","2015-10-05"]
[3926,640449,"   Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[3929,680025,"      CT1 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->95¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 95%->100","24.301, 24.008",68,35,null,null,"2015-06-15","2015-12-07"]
[3932,640046,"Dedicated Core Networks","DECOR",1,"Rel-13","S2","2014-06-18","2016-03-11",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","06/15: WID: SP-140707-> SP-150249","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[3933,640146,"   TR for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-18","2014-12-12",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Dec.14: 30->100%. 06/15: WID: SP-140707-> SP-150249","New 23.707",64,33,null,null,"2014-05-30","2015-06-18"]
[3936,690014,"      CT1 aspects for Dedicated Core Networks CT aspects","DECOR-CT",3,"Rel-13","C1","2015-09-07","2015-12-17",1,"CP-150423",null,"Huawei",null,"7/12/15: 0%->100","24.301, 24.008",69,35,null,null,"2015-09-07","2015-12-07"]
[3939,680166,"      Core part: Dedicated Core Networks","DECOR-UTRA_LTE-Core",3,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151048","RP-151290","Ericsson",null,"no Perf. part¦note: DECOR is a REL-13 SA2 WI¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-1512901/1/16: Compl:30%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[3943,640048,"Architecture Enhancements for Service capability Exposure","AESE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140704","-","Intel","puneet.jain@intel.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[3946,640348,"   TR on Security for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S3","2014-06-23","2015-06-17",1,"SP-140704","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. Dec.14: 0->40%. 3/3/15: 45%.¦June2015: Compl:45%->60¦11/12/15: 60%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[3950,680024,"      CT4 aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","07/09/15: 0%->40¦14/09/15: WID:CP-150402->CP-150487->CP-150576¦7/12/15: 40%->100","29.201, 29.336, 29.230, 29.272, 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[3953,690180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3956,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3957,690281,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[3960,620223,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27","LTE_CA_B8_B27-Perf",3,"Rel-13","R4","2013-12-09","2015-12-15",0.3,"RP-140120","RP-151131","KT","ilwhan.kim@kt.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.141, 36.307",62,32,null,null,"2013-12-07","2015-09-29"]
[3963,620232,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27-Perf",3,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","RP-151131","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Thu 18/06/15->Mon 15/06/15¦Compl:25%->25%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2015-09-29"]
[3967,640022,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12",2,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","-","U.S. Cellular","sebastian.thalanany@uscellular.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-21"]
[3972,640225,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-150874","RP-150536","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536",36.307000000000002,64,33,null,null,"2014-06-16","2015-06-18"]
[3975,640232,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-140974","RP-150536","Huawei","leo.liuye@huawei.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[3978,650237,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38","LTE_CA_B3_B38-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150717","RP-150536","Nokia Networks","iwajlo.angelow@nsn.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->90%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141129->RP-150717 03/07/15: Stat Rep: RP-150013->RP-15","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3981,650238,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[3982,650039,"   LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","-","Huawei","alf.ahlstrom@huawei.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3985,650040,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40",2,"Rel-13","R4","2014-09-12","2015-12-15",1,"RP-141168","-","Ericsson","imadur.rahman@ericsson.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[3989,650141,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40-Core",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","RP-151131","KT","ilwhan.kim@kt.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2016-01-01"]
[3992,650142,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150832","RP-150536","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3995,650143,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-142007","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","¦WID: RP-142043->RP-142007¦Stat Rep: -->RP-141732 1st Apr 15: Compl:75%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[3999,650244,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4002,650245,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4005,650247,"      Perf. Part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_C_B42_3DL-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-151027","RP-150536","CATT","Yuexia Song (songyuexia@catt.cn)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Stat ","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4006,650049,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41",2,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141290","-","China Mobile","PAN, Qun (panqun@chinamobile.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4009,650051,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","-","Samsung","xutao.zhou@samsung.com","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4013,650153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29","LTE_CA_B2_B5_B29-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141667","RP-150536","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, New 36.8xy (inter-band CA 2DL/1UL (introduce CA_B5-B29), New 36.8xz (inter-band CA 3DL/1UL)",65,33,null,null,"2014-06-16","2015-06-18"]
[4016,660172,"      Core part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C-Core",3,"Rel-13","R1","2014-12-15","2015-12-15",1,"RP-151984","RP-151285","Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: Compl:10%->40% 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Compl:4",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4019,660080,"   HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142237",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-15"]
[4023,660181,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4026,660182,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4027,660282,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4033,660284,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150639","RP-151131","NTT DOCOMO","NTT DOCOMO","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4034,660085,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42","LTE_CA_B21_B42_B42",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141792",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4038,660186,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150614","RP-151131","ZTE","ZTE","1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP-",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4041,660187,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4044,660188,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7_Bwset-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141881","RP-150536","Ericsson","Ericsson","Acronym changed from LTE_CA_B3_B7_B7-Core 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4048,660289,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28","LTE_CA_B7_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141882","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4051,660290,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151258","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4052,660091,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141947",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4055,660092,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141949",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4058,660093,"   LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4062,660194,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150719","RP-150536","Nokia Networks","Nokia Networks","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4065,660195,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4068,660196,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4072,660297,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4075,660298,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-151071","RP-150536","Huawei","Huawei","03/07/15: Compl:0%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4076,660099,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142208",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4079,661000,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4082,661001,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238",null,"Intel","Intel",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4086,661102,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28","LTE_CA_B3_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142244","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4089,661103,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150449","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4094,661005,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142200",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4097,661006,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142201",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4100,661007,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142202",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4101,661107,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150451","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[{"$f":"A4104+1","v":4104},661108,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150453","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4107,661109,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4111,661210,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150678","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4114,661211,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4118,661013,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4121,670065,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150121",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4124,670066,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150122",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4125,670166,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150642","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4128,670167,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150643","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4131,670168,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42","LTE_CA_B3_B19_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150644","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4135,670269,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4138,670270,"      Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4142,670072,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12","LTE_CA_B2_B7_B12",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150431",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4145,670073,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4148,670074,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4149,670174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4152,670175,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12","LTE_CA_B2_B4_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150660","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4155,670176,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150659","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4160,670078,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150434",null,"SK Telecom",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4163,670079,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4167,670180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4170,670181,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064","RP-151131","KDDI",null,"03/07/15: Compl:0%->70% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:70%->90% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4173,670182,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13","LTE_CA_2UL_R13-A4-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150616","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4174,670282,"      Perf. Part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13","LTE_CA_2UL_R13-A4-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150616","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4177,670283,"      Perf. part:LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151230","RP-151131","Nokia Corporation",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4181,670085,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150437",null,"CMCC",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4184,670086,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438",null,"CATT",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4187,680077,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11","LTE_CA_B1_B8_B11",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150609","-","Softbank Mobile",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4191,680178,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32-Core",3,"Rel-14","R4","2015-06-15","2016-03-15",0.9,"RP-150864","RP-151131","Ericsson",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-1511311/22/3/16: Compl:50%->90%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4194,680179,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","RP-151131","Huawei",null,"29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4195,680279,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","RP-151131","Huawei",null,"29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4198,680280,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","RP-151131","Huawei",null,"29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4201,680281,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","RP-151131","Nokia Networks",null,"29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-151131¦1/1/16: Comp",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4205,680083,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151112","-","KDDI",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4208,680085,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","-","Rogers Communications",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4211,680086,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4215,680187,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4216,680287,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4220,680089,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4223,680090,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4226,680091,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4230,680192,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4233,680193,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4236,680194,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4240,680295,"      Perf. part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4243,680296,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4244,680097,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4247,680098,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4250,681000,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4254,681101,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4257,681102,"      Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4261,681203,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4264,681204,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","RP-151131","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4267,681205,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4268,681006,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_NC_B42_4DL",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151102","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4271,680074,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","-","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4274,680076,"   Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","-","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4277,680072,"   Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151037","-","Huawei",null,"Aug 15: TR numb added",null,68,35,null,null,"2015-08-12","2015-08-12"]
[4282,680184,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42","LTE_CA_B41_B41_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151562","RP-151131","ZTE",null,"29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131",null,68,35,null,null,"2015-08-12","2016-01-01"]
[4286,690273,"      Perf. part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4289,690274,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4292,690275,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40","LTE_CA_B5_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151200","-","ZTE",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4293,690076,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[{"$f":"A4296+1","v":4296},690077,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 ","LTE_CA_B3_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151448","-","ZTE",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4300,690178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4303,690179,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4306,690182,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,"¦1/1",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4310,690283,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40","LTE_CA_B3_B28_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151363","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4313,690284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4316,690285,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4317,690089,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42","LTE_CA_B1_B3_B19_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151159","-","NTT DOCOMO",null,null,"36.857-13",69,35,null,null,"2015-09-29","NA"]
[4320,690090,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4324,690191,"      Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28-Core",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-160141","-","Telstra",null,"¦22/3/16: Compl:95%->100%;",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4327,690192,"      Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B3_B7_B7_B28-Core",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151513","-","Telstra",null,"22/3/16: Compl:95%->100%",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4330,690193,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4334,690294,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4337,690295,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12 ¦",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4338,700065,"   UE Conformance Test Aspects - Rel-13 LTE CA configurations","LTE_CA_Rel13-UEConTest",2,"Rel-13","R5","2015-12-15","2018-12-14",1,"RP-161553",null,"Ericsson",null,"¦22/3/16: Compl:0%->5%;1/7/16: Compl:5%->22%26/9/16: Compl:22%->¦2 21/3/17: Compl:39% ;; 14/1/20: 62%->100",null,70,36,null,null,"2016-01-01","2020-01-14"]
[4342,690007,"(Small) Security Enhancements and Improvements for Rel-13","SEC13",1,"Rel-13","S3","2006-12-12","2015-12-21",1,"-","PCG-31","-","-","-","-",61,31,null,null,"2015-01-12","2013-09-14"]
[4345,640001,"Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things","FS_IoT_LC",1,"Rel-13","G1,G2","2014-05-30","2015-08-28",1,"GP-150354","-","Vodafone","chris.pudney@vodafone.com","GP#62 approved WID. Dec.14: 15->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100¦14/09/15: WID:GP-140421->GP-150354","45.8xy",66,33,null,null,"2014-05-30","2015-09-14"]
[4349,570034,"Study on Application specific Congestion control for Data Communication","FS_ACDC",1,"Rel-13","S1","2012-09-17","2014-09-17",1,"SP-130415","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion)",22.806000000000001,57,29,null,null,"2012-08-31","2014-08-29"]
[4352,600046,"Study on Isolated E-UTRAN Operation for Public Safety","FS_IOPS",1,"Rel-13","S1","2013-06-25","2014-06-18",1,"SP-130596","-","General Dynamics","paul.piggin@gd-broadband.com","SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and FeaturES in CP-150ProSe, GCSE_LTE",22.896999999999998,60,31,null,null,"2013-05-30","2014-05-27"]
[4355,610033,"(SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO","FS_CSIPTO",1,"Rel-13","S1","2013-09-13","2014-06-18",1,"SP-130417","-","Intel","Eric.siow@intel.com","SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET",22.827999999999999,61,31,null,null,"2013-08-26","2014-12-12"]
[4359,520035,"Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group","FS_UMONC_sas",1,"Rel-13","S2","2011-06-08","2014-12-12",1,"SP-140403","-","China Telecom","Jinyan Li (lijy@ctbri.com.cn)","SP#64 revived. Added to the Title \"for Service, Application and Subscriber Group\", Changed Acronym: FS_UMONC=>FS_UMONC_sas",23.858000000000001,52,27,null,null,"2011-05-19","2014-06-19"]
[4362,520235,"   Deleted - SA5 part of Study on Usage Monitoring Control enhancement","-",2,"-","S5","2012-03-02","2012-09-12",1,"SP-120554","-","Huawei","Hui Cai (Sarah.Cai@huawei.com)","SP#57 stopped",32.857999999999997,52,27,"SP-57","PCG-29","2011-05-19","2012-08-30"]
[4363,500034,"Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int_Sec",1,"Rel-13","S3","2010-12-28","2015-06-12",1,"SP-150368","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%¦June2015: Compl:65%->100¦June2015: WID:SP-140576->SP-150368",33.895000000000003,50,26,null,null,"2010-11-25","2015-06-18"]
[4366,620059,"Study on Application and Partitioning of Itf-N","FS_OAM_AP_Itf-N",1,"Rel-13","S5","2013-12-17","2015-09-11",1,"SP-130681","-","China Mobile","Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com)","-Dec.14: 15->30%, CD: 12/14->09/15¦June2015: Compl:30%->60¦07/09/15: 60%->100","32.861 ",62,32,null,null,"2013-11-28","2015-09-07"]
[4369,590010,"Study on Review of dedicated 3GPP UICC features","FS_Red_UCe",1,"Rel-13","C6","2013-03-13","2015-12-16",1,"CP-130168","-","BlackBerry","Adrian Buckley (abuckley@blackberry.com)","CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100%",31.901,59,30,null,null,"2013-02-20","2014-12-03"]
[4373,620013,"Stopped at 20% - Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO)","FS_UL_MU_MIMO",1,"Rel-13","G1,G2","2014-04-17","2016-02-19",1,"GP-131131","-","Huawei","Chao Luo (chluo@huawei.com)","GP#62 completion 11/14=>02/15. GP#60 approved WID. Dec.14: 02/15->05/15. 02/03/16: stopped at 20%",45.875999999999998,60,32,"SP#71",null,"2013-11-22","2014-12-03"]
[4376,620045,"Study on Multi-RAT joint coordination","FS_MultiRAT_JC",1,"Rel-13","R4","2013-12-06","2015-06-15",1,"RP-150417","RP-150807","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","¦WID: RP-142043->RP-132086¦Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807","UTRA, LTE 37.870",62,32,null,null,"2013-11-27","2015-06-18"]
[4379,650014,"Study on Downlink enhancements for UMTS","FS_UTRA_EDL",1,"Rel-13","R2,R1","2014-09-12","2015-06-15",1,"RP-150224","RP-150681","Huawei","jun.chen@huawei.com","WID: RP-141901¦Stat Rep: -->RP-142233 1st Apr 15: Compl:40%->80% 1st Apr 15: WID: RP-141901->RP-150224 1st Apr 15: Stat Rep: RP-142233->RP-150223. 5/5/15: R4 replaced by R1 (correction mistake) 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150223->","UTRA 25.706",65,33,null,null,"2014-09-15","2015-06-18"]
[4383,660057,"Study on Video Enhancements in 3GPP Multimedia Services","FS_VE_3MS",1,"Rel-13","S4","2014-12-12","2015-12-11",1,"SP-140741",null,"Ye-Kui Wang, Qualcomm Incorporated","yekuiw@qti.qualcomm.com","Mar. 15: 0->20%¦June2015: Compl:20%->40¦07/09/15: 40%->80¦7/12/15: 80%->100",null,66,34,null,null,"2014-12-12","2015-12-07"]
[4386,660065,"Study on Enhanced Multiuser Transmissions and Network Assisted Interference Cancellation for LTE","FS_LTE_MUTX_NAIC",1,"Rel-13","R1","2014-12-15","2015-03-15",0,"RP-142315","RP-150213","MediaTek","MediaTek","1st Apr 15: CD:Tue 15/12/15->Sun 15/03/15 1st Apr 15: Stat Rep: ->RP-150213. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake)",null,66,34,null,null,"2015-01-12","2015-05-05"]
[4387,660066,"Study on Support of single-cell point-to-multipoint transmission in LTE","FS_LTE_SC_PTM",1,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150177","RP-150695","Jeff GAO","gaoyongqiang@huawei.com","deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695",36.89,66,34,null,null,"2015-01-12","2015-06-18"]
[4390,660069,"Study on RAN sharing enhancements for UMTS","FS_RSE_UTRA_GUSH",1,"Rel-13","R3","2014-12-15","2015-06-15",1,"RP-150686","RP-150684","Huawei","Huawei","03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3)",25.756,66,34,null,null,"2015-01-12","2015-10-07"]
[4393,660061,"Study on Enhanced Multiuser Transmissions and Network","FS_MUIC_LTE",1,"Rel-13","R1","2014-12-12","2015-12-11",0,"RP-142315",null,"Pei-Kai Liao","pk.liao@mediatek.com","TR added",36.890999999999998,67,34,null,null,"2014-12-12","2015-01-29"]
[4397,670087,"Study on Phase 1 of the Support of Emergency services over WLAN","FS_SEW",1,"Rel-13","S2","2015-03-12","2015-06-18",1,"SP-150251",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251","new 23.771",67,34,null,null,"2015-04-01","2015-06-18"]
[4399,680013,"Study on SCC AS Restoration","FS_SCCAS_RES",1,"Rel-13","C4","2015-06-15","2015-06-15",1,"CP-150398",null,"Hao Zhang,, China Mobile","zhanghao@chinamobile.com","07/09/15: 5%->20¦7/12/15: 20%->100","New 29.812",68,35,null,null,"2015-06-15","2015-12-07"]
[4404,690061,"Study on new AWS-3/4 Band for LTE","FS_LTE_AWS_3_4",1,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151626","-","Dish Network",null,null,36.869999999999997,69,35,null,null,"2015-09-29","2016-01-01"]
[4408,0,"Stage 1 - ONLY Features","-",1,"Rel-12","SP,CP","2011-09-27","2014-03-05",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[4411,500031,"Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers","MOSAP",1,"Rel-12","S1,S2","2010-12-16","2013-12-11",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#58 Stage 2 stopped (TR only, no normative work done)","Stage 1",50,26,null,null,"2010-11-29","2012-11-22"]
[4412,500131,"   Stage 1 for MOSAP","MOSAP-SA1",2,"Rel-12","S1","2010-12-16","2011-09-21",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#53 completed",22.277999999999999,50,26,null,null,"2010-11-29","2012-06-09"]
[4415,520027,"IMS Network-Independent Public User Identities","INIPUI",1,"Rel-12","S1","2011-06-08","2012-06-20",1,"SP-120425","-","Vodafone","mona.mustapha@vodafone.com","Triggered by Rel-11 TR 22.894 (FS_INIPUI)","Stage 1",52,27,null,null,"2011-05-19","2012-06-19"]
[4418,530143,"   Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls","SMURFs-SA1",2,"Rel-12","S1","2011-09-21","2012-06-20",1,"SP-110653","-","Vodafone","mona.mustapha@vodafone.com","SP#56 completed",22.277999999999999,53,27,null,null,"2011-07-19","2012-06-08"]
[4422,550125,"   Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks","SSO_Int-SA1",2,"Rel-12","S1","2012-03-08","2012-09-12",1,"SP-120184","-","InterDigital","christopher.wallace@interdigital.com","SP#57 completed",22.100999999999999,55,28,null,null,"2012-02-22","2012-08-07"]
[4425,570027,"IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2)","IMSSat",1,"Rel-12","S1","2012-02-02","2012-09-12",1,"SP-120543","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS","Stage 1",57,29,null,null,"2012-08-06","2012-08-08"]
[4429,580061,"Language and Modality Information for communications","LangInfo",1,"Rel-12","S1","2012-12-11","2013-03-06",1,"SP-130108","-","Orange","philippe.lottin@orange.com","SP#59 Stage 1 completed. Triggered by Rel-11 Study on Non Voice Emergency Services (FS_NOVES) TR 22.871 use case 10","Stage 1",58,30,null,null,"2012-11-16","2013-02-19"]
[4432,590140,"   Stage 1 for Emergency Session Identification ","ESID-SA1",2,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130126","-","Telecom Italia","carmen.catalano@telecomitalia.it","SP#59 completed (22.101 CR#0445)",22.100999999999999,59,30,null,null,"2013-02-19","2013-02-19"]
[4435,590042,"Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode","PMOC",1,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130111","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#59 Stage 1 completed","Stage 1",59,30,null,null,"2013-02-19","2013-02-19"]
[4436,590142,"   Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode","PMOC-SA1",2,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130111","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#59 completed",22.010999999999999,59,30,null,null,"2013-02-19","2013-02-19"]
[4439,500128,"   TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network","LIMONET-SA3",2,"Rel-12","S2","2010-10-15","2013-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#59 completed. TR 23.859 v100 for Information and Approval","new 23.859",50,26,null,null,"2010-11-26","2013-02-27"]
[4442,530015,"      Stage 3 CN aspects of SIPTO at the Local Network","LIMONET-SIPTO",3,"Rel-12","C4,C1","2011-09-24","2014-03-05",1,"CP-130274","-","Huawei","peter.schmitt@huawei.com","CP#63 completed","Stage 3",53,27,null,null,"2011-08-27","2014-01-29"]
[4446,590120,"      Core part: RAN aspects for SIPTO at the Local Network","LIMONET-RAN-Core",3,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","RP-131512","Huawei","zheng.zhou@huawei.com","RP#62 completed","25.401, 25.413, 25.423, 25.467, 25.469, 36.300, 36.413, 36.423",59,30,null,null,"2013-02-26","2013-11-29"]
[4449,530016,"      Deleted - Stage 3 CN aspects of LIPA Mobility","LIMONET-LIPA-del2",3,"Rel-12","C1,C4","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","Stage 3",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[4453,510149,"   TR on Stage 2 for Operator Policies for IP Interface Selection","OPIIS",2,"Rel-12","S2","2011-03-23","2012-12-12",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","SP#58 completed","new 23.853",51,26,null,null,"2011-02-21","2012-12-10"]
[4456,520029,"Short Message Service (SMS) submit and delivery without MSISDN in IMS","SMSMI",1,"Rel-12","S2,C1,C4","2011-06-08","2013-12-06",1,"SP-120321","-","Nokia Siemens Networks","curt.wong@nsn.com","Linked to Rel-7 SMSIP (Support of SMS over generic 3GPP IP access), Rel-11 SIMTC, Rel-12 TR 22.988 SA1 Study on alternatives to E.164 for MTC","Stage 2/3",52,27,null,null,"2011-05-26","2013-11-18"]
[4459,590013,"   Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",2,"Rel-12","C1,C4","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS","Stage 3",59,30,null,null,"2013-02-16","2013-11-18"]
[4460,590113,"      CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",3,"Rel-12","C1","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed","23.040, 24.341",59,30,null,null,"2013-02-16","2013-11-18"]
[4464,580001,"   CT part for IMS Telepresence (Stage 2/3)","IMS_TELEP",2,"Rel-12","C1,C3,C4,IETF","2010-03-22","2014-12-09",0.93,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 updated WID CP-140196=>CP-140624. 2/4/15: acronym changed to IMS_TELEP","Stage 2/3",58,30,null,null,"2012-11-19","2015-04-02"]
[4468,641002,"      (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",0.9,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-framework ); 9/4/21: RFC 8845 added;","draft-ietf-clue-framework; RFC 8845",64,33,null,null,"2014-06-06","2021-04-09"]
[4471,641005,"      (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",0.9,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-data-model-schema); 9/4/21: RFC 8846 added;","draft-ietf-clue-data-model-schema; RFC 8846",64,33,null,null,"2014-06-06","2021-04-09"]
[4474,560020,"Group Communication System Enablers for LTE","GCSE_LTE",1,"Rel-12","S1,S2,S3,C3,C4,R3,C1","2012-06-18","2015-03-13",1,"SP-140433","-","Nokia Networks","Juergen.Merkel@nsn.com","Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety","Stage 1/2/3",56,29,null,null,"2012-05-14","2014-09-07"]
[4478,610135,"   TR on Security for Group Communication System Enablers for LTE (Stage 2)","GCSE_LTE",2,"Rel-12","S3","2013-09-12","2014-06-18",1,"SP-140433","-","Nokia Networks","anja.jerichow@nsn.com","SP#64 completed. TR 33.888v100 for 1-step Approval","New 33.888",61,31,null,null,"2013-09-03","2014-09-07"]
[4481,640110,"      CT3 part of Group Communication System Enablers for LTE","GCSE_LTE-CT",3,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140559","-","Nokia Networks","thomas.belling@nsn.com","CP#65 completed. TS 29.468v200 for Approval","29.212, 29.213, 29.214, 29.274, New 29.468",64,33,null,null,"2014-06-10","2014-09-06"]
[4484,640037,"   Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM",2,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","-","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","-","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4485,640137,"      Core part: Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM-Core",3,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","RP-150081","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:25%->80%¦Stat Rep: RP-141327->RP-141863 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141863->RP-150081",36.412999999999997,64,33,null,null,"2014-06-16","2015-04-01"]
[{"$f":"A4488+1","v":4488},570030,"   Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance","MTCe-SRM",2,"Rel-12","S1","2012-09-13","2013-03-06",1,"SP-130105","-","KPN","toon.norp@tno.nl","SP#59 completed. Updated WID SP-120541=>SP-130105","22.101, 22.368",57,29,null,null,"2012-08-06","2013-02-19"]
[4492,560622,"      TR on Stage 2 BB1: Small Data and Device Triggering Enhancements","MTCe-SDDTE",3,"Rel-12","S2","2012-06-18","2013-12-11",1,"SP-120450","-","Intel","puneet.jain@intel.com ","SP#62 completed. TR 23.887v200 for Approval","New 23.887",56,29,null,null,"2012-04-13","2013-11-28"]
[4495,630101,"         CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement","MTCe-SDDTE-CT",4,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#65 completed. Updated WID CP-140272=>CP-140489","29.002, 29.336, 23.008, 29.337, 29.338, 29.230",63,32,null,null,"2014-01-29","2014-07-29"]
[4498,560322,"   BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",2,"Rel-12",null,"2012-06-18","2016-05-12",0.93,"SP-120442","-","Ericsson","peter.hedman@ericsson.com","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[4502,620107,"         CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT1",4,"Rel-12","C1","2013-12-06","2014-09-11",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","CP#65 completed","24.008, 24.301",62,32,null,null,"2013-11-18","2014-07-28"]
[4505,690068,"         UE Conformance Test Aspects - UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-UEConTest",4,"Rel-12","R5","2015-09-15","2016-03-15",1,"RP-151161","-","Ericsson",null,"tested: MTCe-UEPCOP was a REL-12 SA2 WI¦NAS over LTE and UTRA;1/1/16: Compl:0%->25%22/3/16: C",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4508,560422,"   Deleted - BB4: Group based MTC feature (GROUP)","MTCe-GROUP",2,"Rel-12","S2","2012-06-20","2012-12-12",1,"SP-120267","-","KPN","Annemieke Kips","SP#58 stopped (at 25% completion)",23.681999999999999,56,29,"SP-58","PCG-30","2012-04-13","2012-12-14"]
[4509,620043,"   RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN",2,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","-","ZTE","sergio.parolari@zte.com.cn","Triggered by TR 23.887 Machine Type and other mobile data applications Communications Enhancements (MTCe), TR 37.869 Study on Enhancements MTC and other Mobile Data Applications¦RAN aspects (FS_MTCe_RAN), Rel-11 TR 23.888 SIMTC","UTRA, LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[4512,600112,"   Core part: Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE-Core",2,"Rel-12","R1,R2,R4","2013-06-15","2014-12-15",1,"RP-140522","RP-142024","Vodafone","eric.bouton@vodafone.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141221->RP-142024","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331",60,31,null,null,"2013-06-17","2015-01-12"]
[4516,570031,"   Stage 1 for Policy and Charging Support for Fixed Mobile Convergence","P4C-FMC",2,"Rel-12","S1","2012-09-10","2012-09-12",1,"SP-120542","-","Huawei","amar.deol@huawei.com","SP#57 completed",22.277999999999999,57,29,null,null,"2012-08-06","2013-01-08"]
[4519,562124,"      Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F-SA2",3,"Rel-12","S2","2012-06-20","2013-12-11",1,"SP-120275","-","Huawei","marco.spini@huawei.com","SP#62 completed","23.139, 23.203",56,29,null,null,"2012-06-04","2013-11-28"]
[4522,620009,"         CT1 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C1","2013-12-06","2014-03-05",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#63 completed",24.302,62,32,null,null,"2013-11-19","2014-01-29"]
[4525,600043,"      Traffic Detection Function (TDF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3)","P4C-F-CH_T",3,"Rel-12","S5","2013-06-24","2014-06-18",1,"SP-130262","-","Openet Telecom","alan.mcnamee@openet.com","SP#64 completed","Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299)",60,31,null,null,"2013-06-02","2014-06-10"]
[4530,560424,"   Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB)","P4C-HeNB",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120278","-","NEC","Stefan.Schmid@neclab.eu","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[4531,560524,"   Deleted - BB5: Policy and Charging Control for supporting Layer 2 traffic in fixed broadband access network (P4C-FL2)","P4C-FL2",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120279","-","Huawei","marco.spini@huawei.com","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[4534,560325,"   Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA1",2,"Rel-12","S1","2011-09-28","2012-09-12",1,"SP-120862","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#57 completed. 22.228CR#0171 ",22.228000000000002,56,29,null,null,"2012-05-11","2012-12-10"]
[4537,610007,"   CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",2,"Rel-12","C1,C3","2013-09-06","2014-12-09",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","-","Stage 3",61,31,null,null,"2013-08-10","2014-03-03"]
[4541,560126,"   TR on Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SATR",2,"Rel-12","S2,S1","2012-06-18","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","New 23.865",56,29,null,null,"2012-05-11","2013-11-28"]
[4544,620005,"   CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3)","WLAN_NS-CT",2,"Rel-12","C1","2013-12-06","2014-12-09",1,"CP-130712","CP-140622","Qualcomm","Amer Catovic, amerc@qualcomm.com","CP#65 completion 09/14=>12/14. CP#65 exception CP-140622. Dec.14: 95->100%","24.302, 24.312",62,32,null,null,"2013-11-19","2014-12-04"]
[4547,580056,"   Deleted - Stage 2 for IMS Registration Control","IMS_RegCon-del2",2,"Rel-12","S2","2012-12-13","2013-12-11",1,"SP-120735","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 stopped at 50% completion",23.228000000000002,58,30,"SP-62","PCG-32","2012-11-13","2013-12-10"]
[4551,580059,"Proximity-based Services","ProSe",1,"Rel-12",null,"2012-12-13","2017-06-15",1,"SP-140574","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044","Stage 1/2",58,30,null,null,"2012-11-16","2014-09-15"]
[4554,580359,"   Stage 2 for Proximity-based Services","ProSe-SA2",2,"Rel-12","S2","2012-12-19","2014-06-18",1,"SP-140574","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval","New 23.303",58,30,null,null,"2012-11-16","2014-09-15"]
[4555,590036,"   Security for Proximity-based Services","ProSe-SA3",2,"Rel-12","S3","2013-03-13","2014-12-12",1,"SP-140574","SP-140584","Qualcomm","Adrian Escott (aescott@qti.qualcomm.com)","SP#65 re-opened. Completion 06/14=>12/14. Exception in SP-140584. Updated WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). SP#64 completed. TS 33.303 v100 for 1-step Approval¦Aug2015: 90%->100","33.220, New 33.303",59,30,null,null,"2013-02-20","2015-08-14"]
[4558,640139,"      Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use","ProSe-CH-SA5TR",3,"Rel-12","S5","2014-06-19","2014-12-12",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100%","New 32.844",64,33,null,null,"2014-06-06","2014-12-12"]
[4561,630106,"      CT1 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140290","CP-140615","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100%","24.301, 23.122, New TSs (24.333, 24.334)",63,32,null,null,"2014-01-29","2014-12-04"]
[4565,630030,"   LTE Device to Device Proximity Services","LTE_D2D_Prox",2,"Rel-12",null,"2014-03-11","2017-06-15",1,"RP-140955","-","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","follow-up of TR 36.843 FS_LTE_D2D_Prox","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4568,670046,"      UE Conformance Test Aspects – LTE Device-to-Device Proximity Services","LTE_D2D_Prox-UEConTest",3,"Rel-12","R5","2015-03-16","2017-06-15",1,"RP-160382",null,"Qualcomm","svora@qti.qualcomm.com","rapporteur e-mail added 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150765 29/09/15: Compl:10%->30% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150765->RP-151280 1/1/16: Compl:30%->45% 1/1/16: WID: RP-1¦ ;",null,67,34,null,null,"2015-04-01","2017-06-19"]
[4571,600040,"   TR on Stage 2 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S2","2013-06-19","2013-12-11",1,"SP-130707","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#62 completed. TR 23.701v100 for Information & Approval","New 23.701",60,31,null,null,"2013-06-06","2013-09-09"]
[4575,620067,"   TR on Security for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S3","2013-12-11","2014-09-17",1,"SP-130707","-","Ericsson","oscar.ohlsson@ericsson.com","SP#65 completed. TR 33.871v200 for Approval","New 33.871",62,32,null,null,"2013-12-05","2014-09-04"]
[4578,870070,"      (IETF) Trickle ICE: Incremental Provisioning of Candidates for the Interactive Connectivity Establishment (ICE) Protocol (draft-ietf-ice-trickle)","IMS_WebRTC-CT",3,"Rel-12","C1-IETF","2019-03-07","2019-03-07",0.9,null,null,null,null,"9/4/21: RFC 8838 added;","RFC 8838",87,44,null,null,"2020-04-23","2021-04-09"]
[4579,870071,"      (IETF) Trickle ICE: Incremental Provisioning of Candidates for the Interactive Connectivity Establishment (ICE) Protocol (draft-ietf-ice-trickle)","IMS_WebRTC-CT",3,"Rel-12","C1-IETF","2019-03-07","2019-03-07",0.9,null,null,null,null,"9/4/21: RFC 8838 added;","RFC 8838",87,44,null,null,"2020-04-23","2021-04-09"]
[4582,641007,"      (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-stun-consent-freshness)","IMS_WebRTC-stun",3,"Rel-12","C1-IETF","2014-03-06","2014-12-09",1,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Mar15: Publication requested¦7/3/16: 50%->100; 9/4/21: RFC 7675 added;","draft-ietf-rtcweb-stun-consent-freshness; RFC 7675",64,33,null,null,"2014-06-06","2021-04-09"]
[4586,630203,"      CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT4",3,"Rel-12","C4","2014-03-05","2014-12-09",1,"CP-140192","CP-140732","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","CP#65 completion 09/14=>12/14. Exception in CP-140732. Dec.14: 30->80%. Mar. 15: 100%","23.334, 29.334",63,32,null,null,"2014-01-29","2015-03-04"]
[4590,590039,"Application Based Charging","ABC",1,"Rel-12","S2,S5,C3","2013-03-07","2014-06-18",1,"SP-130328","-","Allot","Alla Goldner (agoldner@allot.com)","Triggered by TR 23.800 Study on Application Based Charging (FS_ABC) UID_560038","Stage 2/3",59,30,null,null,"2013-02-21","2013-06-06"]
[4593,600049,"   CT3 aspects of Application Based Charging (Stage 3)","ABC-CT3",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130353","-","Allot","Alla Goldner (agoldner@allot.com)","CP#62 completed","29.212, 29.213, 29.214, 29.215, 29.219",60,31,null,null,"2013-05-29","2013-10-21"]
[4597,610109,"      CT1 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",3,"Rel-12","C1","2013-09-09","2014-12-09",1,"CP-130715","CP-140608","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#65 completion 09/14=>12/14. Exception in CP-140608. TS 24.244 v200 for Approval. Dec.14: 95->100%","24.302, New 24.244 (WLAN control plane protocol for trusted WLAN access to EPC)",61,31,null,null,"2013-08-10","2014-12-04"]
[4600,610139,"   Stage 2 for Optimized Offloading to WLAN in 3GPP-RAT Mobility","WORM-SA2",2,"Rel-12","S2","2013-09-12","2013-12-11",1,"SP-130392","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","SP#62 completed","23.272, 23.401, 23.402",61,31,null,null,"2013-07-25","2013-11-28"]
[4603,610140,"   Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-SA2",2,"Rel-12","S2","2013-09-12","2014-03-07",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","SP#63 completed","23.203, 23.228, 23.402",61,31,null,null,"2013-07-25","2014-02-04"]
[4604,620008,"   CT aspects of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case (Stage 3)","NETLOC_TWAN-CT",2,"Rel-12","C3,C1,C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","-","Stage 3",62,32,null,null,"2013-11-19","2013-11-19"]
[4607,620308,"      CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed","29.273, 29.274, 29.275, 29.328, 29.329",62,32,null,null,"2013-11-19","2014-07-28"]
[4610,650017,"   Charging aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CH",2,"Rel-12","S5","2014-09-15","2014-09-17",1,"SP-140541","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#65 New WID approved & completed. Introduction of Presence Reporting Areas for Charging","32.251, 32.298, 32.299",65,33,null,null,"2014-08-24","2014-09-10"]
[4614,560028,"Rel-12 Security small Enhancements","SEC12",1,"Rel-12","S3","2011-03-23","2014-09-17",1,"-","-","-","-","SEC12 is an umbrella Feature for Security related TEI12 type of changes that are not part of any other dedicated feature","Stage 2/3",56,29,null,null,"2012-06-02","2014-09-04"]
[4617,510354,"   TR on SA3 part for Security aspects of Public Warning System","PWS_Sec-SA3TR",2,"Rel-12","S3","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#65 completed. TR 33.969v100 for 1-step Approval. Former TR 33.869 changed to 33.969.","New 33.869 changed to 33.969",51,26,null,null,"2012-06-02","2014-09-04"]
[4621,510454,"   Deleted - CT1 part for Security aspects of Public Warning System","PWS_Sec-del4",2,"Rel-12","C1","2011-03-25","2012-06-20",1,"SP-120434","-","ST-Ericsson","mikael.wass@ericsson.com","TSG#56 work stopped. SP#56 updated WID SP-110223=>SP-120334 (removed all but SA3 impacted specs)",23.041,51,26,"SP-56","PCG-29","2012-06-02","2012-06-08"]
[4624,560030,"Extended IMS media plane security features","eMEDIASEC",1,"Rel-12","S3,C4,C1,C3,IETF","2012-06-20","2014-12-09",0.97,"SP-120447","-","Vodafone","Aguibou.Barry@vodafone.com","Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC)","Stage 2/3",56,29,null,null,"2012-06-02","2013-02-19"]
[4627,580005,"   CT aspects of Extended IMS media plane security features (Stage 2/3)","eMEDIASEC-CT",2,"Rel-12","C4,C1,C3,IETF","2012-12-13","2014-12-09",0.95,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","-","Stage 2/3",58,30,null,null,"2012-11-14","2013-11-19"]
[4628,600051,"      TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects","eMEDIASEC-CT",3,"Rel-12","C4","2012-12-13","2014-09-11",1,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completed. TR 29.828v200 for Approval. 2/4/15: acronym changed to eMEDIASEC-CT","New 29.828",58,30,null,null,"2012-11-14","2015-04-02"]
[4631,641009,"      (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-mmusic-sdp-for-gw)","eMEDIASEC-CT",3,"Rel-12","C4-IETF","2014-06-12","2014-12-09",0,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Work in progress. 2/4/15: acronym changed to eMEDIASEC-CT¦22/3/18: 100%->0","draft-schwarz-mmusic-sdp-for-gw",64,33,null,null,"2014-06-12","2018-03-22"]
[4635,570032,"Lawful Interception in the 3GPP Rel-12","LI12",1,"Rel-12","S3","2012-09-17","2014-12-12",1,"SP-130650","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com","3/3/15: 75->100%","33.106, 33.107, 33.108",57,29,null,null,"2012-08-31","2015-03-03"]
[4638,600050,"   CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3)","TURAN-CT",2,"Rel-12","C1","2013-06-14","2014-06-13",1,"CP-130716","-","Huawei","Haitao Wei (weihaitao@huawei.com)","CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs","24.229, 24.302, New 24.322",60,31,null,null,"2013-05-28","2014-05-26"]
[4641,470031,"   Stage 1 for Codec for Enhanced Voice Services","EVS_codec-SA1",2,"Rel-12","S1","2010-03-25","2010-03-25",1,"SP-140007","-","Huawei","lei.miao@huawei.com","SP#47 completed",22.172999999999998,47,24,null,null,"2010-03-10","2010-03-22"]
[4645,650105,"      CT4 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C4","2014-09-16","2014-12-09",1,"CP-140800","CP-140478","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140478. Dec.14: 0->100¦WID: CP-140492-> CP-140800","23.334, 29.232, 29.238, 29.332, 29.333, 29.334",65,33,null,null,"2014-07-29","2014-12-09"]
[4647,650305,"      CT3 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C3","2014-09-16","2014-12-09",1,"CP-140800","CP-140560","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800","29.163, 29.292",65,33,null,null,"2014-07-29","2014-12-09"]
[4652,600106,"      CT4 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C4","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","23.333, 23.334, 29.238, 29.332, 29.333, 29.334",60,31,null,null,"2013-05-28","2014-01-29"]
[4653,600206,"      CT1 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed",24.228999999999999,60,31,null,null,"2013-05-28","2013-11-18"]
[4656,570133,"   TR on Evaluation of High Efficiency Video Coding for 3GPP Services","HEVC-SA4TR",2,"Rel-12","S4","2012-09-12","2014-06-19",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed. TR 26.906v200 for Approval","New 26.906",57,29,null,null,"2012-08-30","2014-04-16"]
[4660,580066,"IMS-based Streaming and Download Delivery Enhancements","IMS_SDE",1,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","Provide an extension of IMS based PSS and MBMS user services","-",58,30,null,null,"2012-11-12","2013-04-19"]
[4663,580067,"Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE","ART_LTE",1,"Rel-12","S4","2012-12-12","2014-12-12",1,"SP-120769","-","Qualcomm","Andre Schevciw (aschevci@qualcomm.com)","Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods","Stage 3",58,30,null,null,"2012-11-12","2013-04-19"]
[4666,580367,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - Super wideband and fullband aspects","ART_LTE-SUPER",2,"Rel-12","S4","2012-12-12","2014-12-12",1,"SP-120772","SP-140470","Sony Mobile Communications","peter.isberg@sonymobile.com","SP#65 completion 09/14=>12/14. Exception in SP-140470. Dec.14: 65->100","26.131, 26.132",58,30,null,null,"2012-11-12","2014-12-03"]
[4670,590443,"   TR on MBMS operation on Demand","MI-MooDTR",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130026","SP-140471","Qualcomm","Charles Lo (clo@qti.qualcomm.com) ","SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.849v100 for Information. Dec.14: 75->100","New 26.849",59,30,null,null,"2013-02-20","2015-03-05"]
[4673,670098,"   S4 aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI",2,"Rel-12","S4","2013-03-06","2014-09-16",1,"SP-140600","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040",26.114000000000001,59,30,null,null,"2013-02-20","2014-09-09"]
[4676,600207,"      CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C1","2013-06-21","2014-09-12",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%",24.228999999999999,60,31,null,null,"2013-05-29","2015-05-05"]
[4677,600307,"      CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C4","2013-06-21","2014-09-12",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","23.333, 23.334, 29.238, 29.332, 29.333, 29.334",60,31,null,null,"2013-05-29","2015-05-05"]
[{"$f":"A4680+1","v":4680},560031,"Rel-12 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM12",1,"Rel-12","S5","2011-09-21","2014-12-12",1,"-","-","-","-","OAM12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI","-",56,29,null,null,"2012-04-18","2012-04-18"]
[4684,560135,"      Converged Management Model Alignment (Phase 2)","OAM-MODAL",3,"Rel-12","S5","2012-06-20","2014-09-17",1,"SP-140322","-","NSN","olaf.pollakowski@nsn.com","SP#65 completed. TR 28.280v100 for 1-step Approval","32.156, new 28.820",56,29,null,null,"2012-05-14","2014-08-25"]
[4687,530150,"      Performance measurements part Network Management for 3GPP Interworking WLAN","OAM-IWLAN-SA5P",3,"Rel-12","S5","2011-09-22","2014-09-17",1,"SP-140542","-","China Mobile","Chengang@chinamobile.com, lijian@chinamobile.com","SP#65 completed. TS 28.402v100 for 1-step Approval, withdraw New TS 28.401 (CN and non-3GPP access i/w PMs). Moved PMs for EPC and non-3GPP access i/w from 28.401=>28.402","new 28.401, withdrawn new 28.402",53,27,null,null,"2011-08-27","2014-09-10"]
[4690,620056,"      Alarm quality improvements","OAM-AMI-SA5",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130611","SP-140544","TeliaSonera","tommy.berggren@teliasonera.com","SP#65 completion 09/14=>12/14. Exception in SP-140544. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) . Dec.14: 50->100","32.111-1, 32.111-2, 32.111-6",62,32,null,null,"2013-11-28","2014-12-04"]
[4694,620157,"      OAM aspects of Network Sharing - Concepts and high-level requirements","OAM-SHARE-SA5c",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. LM 80->100","new 32.130",62,32,null,null,"2013-11-28","2014-12-04"]
[4697,580051,"   Short Message Service - Service Center (SMS-SC) Offline Charging","SMS-SC-CH",2,"Rel-12","S5","2012-12-12","2014-03-10",1,"SP-140027","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027","32.240, 32.274, 32.297, 32.298, 32.299",58,30,null,null,"2012-11-20","2014-02-27"]
[4698,610041,"   Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3)","CHIPS",2,"Rel-12","S5","2013-09-12","2014-06-18",1,"SP-130642","-","Ericsson","david.shrader@ericsson.com","SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS","32.251, 32.298, 32.299",61,31,null,null,"2013-09-04","2015-12-07"]
[4701,530018,"IMS Emergency PSAP Callback (Stage 3)","EMC_PC",1,"Rel-12","C1,C3,IETF","2011-09-21","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls","Stage 3",53,27,null,null,"2011-08-27","2013-11-18"]
[4704,530218,"   CT3 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C3","2011-09-24","2013-09-06",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#61 completed. 2/4/15: acronym changed to EMC_PC","29.163, 29.165",53,27,null,null,"2011-08-27","2015-04-02"]
[4708,580010,"   CT1 part of Reporting Enhancements in Warning Message Delivery (Stage 2)","REP_WMD-CT1",2,"Rel-12","C1","2012-12-07","2014-03-04",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","CP#63 completed",23.041,58,30,null,null,"2012-11-19","2014-03-03"]
[4712,580012,"Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3)","bSRVCC",1,"Rel-12","C1,C3,R5","2012-12-07","2014-03-06",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12","GERAN, UTRA, LTE",58,30,null,null,"2012-11-19","2013-06-10"]
[4715,620017,"   Test part: Single Radio Voice Call Continuity (SRVCC) before ringing","bSRVCC-UEConTest",2,"Rel-12","R5","2013-12-06","2014-03-06",1,"RP-131919","RP-140422","NTT DOCOMO","Masahiro.Tamaoki.eu@nttdocomo.com","RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3)","34.229-1, 34.229-2, 36.523-1, 36.523-2 ",62,32,null,null,"2013-11-25","2013-12-14"]
[4719,651002,"   Deleted - (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-jesske-sipcore-sip-tree-cap-indicators)","IMSProtoc6",2,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 9/4/21: 25%->100","draft-allen-sipcore-sip-tree-cap-indicators",65,33,null,null,"2014-09-02","2021-04-09"]
[4722,611001,"   (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C3-IETF","2013-09-06","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",61,31,null,null,"2013-08-23","2017-03-21"]
[4723,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[4726,580019,"   SAE for support for non-3GPP accesses - Phase 3","SAES3-non3GPP",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[4729,580022,"   Stage 3 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C4","2012-12-10","2013-06-14",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#60 completed","29.328, 29.329, 29.364",58,30,null,null,"2012-11-19","2013-05-29"]
[4733,580024,"Diameter based interface between SGSN-GMLC (Stage 3)","Dia_SGSN_GMLC",1,"Rel-12","C4","2012-12-10","2013-12-06",1,"CP-130598","-","Cisco","Nirav Salot (nsalot@cisco.com)","CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol)","29.002, 29.172, 29.173, 29.230, 29.272",58,30,null,null,"2012-11-20","2013-11-18"]
[4736,590112,"   CT4 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C4","2013-03-01","2013-12-06",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed","23.007, 23.008, 29.274",59,30,null,null,"2013-03-07","2013-11-18"]
[4740,590214,"   Stage 3 for Dual Radio VCC enhancements","eDRVCC",2,"Rel-12","C1,C3","2013-03-01","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed","Stage 3",59,30,null,null,"2013-02-19","2013-11-18"]
[4743,600009,"CT aspects of Signalling of Image Size (Stage 2/3)","SIS_CT",1,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[4746,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162, 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[4747,600010,"IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S)","ICS_IWE",1,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130352","-","Orange","marianne.mohali@orange.com ","CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS)",29.292000000000002,60,31,null,null,"2013-05-28","2013-11-19"]
[4750,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[4753,640014,"      CT1 part of Common for HSS & PCRF solutions","PCSCF_RES",3,"Rel-12","C1","2013-04-03","2014-12-05",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed",24.007999999999999,64,33,null,null,"2013-08-10","2014-09-06"]
[4757,640114,"      CT1 part of HSS based solution","PCSCF_RES",3,"Rel-12","C1","2013-04-03","2014-12-09",1,"CP-140490","CP-140605","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100%",24.228999999999999,64,33,null,null,"2013-08-10","2014-12-04"]
[4760,640214,"      CT1 part of PCRF based solution","PCSCF_RES",3,"Rel-12","C1","2013-04-03","2014-12-09",1,"CP-140490","CP-140605","Huawei","susan.shishufeng@huawei.com","CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100",24.228999999999999,64,33,null,null,"2013-08-10","2014-12-04"]
[4764,670033,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-clarifications)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date; 9/4/21: RFC 7647 added;","draft-ietf-sipcore-refer-clarification; RFC 7647",67,34,null,null,"2015-03-13","2021-04-09"]
[4767,620004,"IMS Operator Determined Call Barring enhancements (Stage 3)","eIODB",1,"Rel-12","C1,C3","2013-12-06","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision","Stage 3",62,32,null,null,"2013-11-18","2013-11-18"]
[4770,620006,"Signalling Improvements for Network Efficiency (Stage 3)","SINE",1,"Rel-12","C1","2013-12-06","2014-12-09",1,"CP-130713","CP-140617","Huawei","Lin Shu (shulin@huawei.com)","CP#65 completion 09/14=>12/14. Exception in CP-140617.Dec.14: 80->85%. 3/3/15: 100% cpltd.","24.008, 24.301",62,32,null,null,"2013-11-18","2015-03-03"]
[4773,630202,"   CT3 part of ICE impacts on IMS H.248 profiles (Stage 2)","ICEH248",2,"Rel-12","C3","2014-03-05","2014-06-13",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#64 completed","29.162, 29.163, 29.292",63,32,null,null,"2014-01-29","2014-06-03"]
[4775,630105,"   SA1 part of Transfer of ETSI business trunking specifications","IMS_Corp2",2,"Rel-12","S1","2014-03-05","2014-09-17",1,"SP-140170","S1-143300","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 completed. TS 22.519v200 for Approval","New 22.519 (ETSI 181 019)",63,32,null,null,"2014-03-06","2014-09-03"]
[4778,630108,"   CT4 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C4","2014-03-10","2014-12-09",1,"CP-140191","CP-140485","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140485. Dec.14: 0->100","23.334, 29.238, 29.334",63,32,null,null,"2014-01-29","2014-12-04"]
[4782,640103,"   CT4 part of Diameter Overload Control Mechanisms","DOCME",2,"Rel-12","C4","2014-06-13","2014-12-09",1,"CP-140273","CP-140486","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140486. Dec.14: 70->100","29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.344, 29.345",64,33,null,null,"2014-05-25","2014-12-04"]
[4785,640104,"   CT1 part of Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",2,"Rel-12","C1","2014-06-13","2014-12-09",1,"CP-140285","CP-140609","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","CP#65 completion 09/14=>12/14. Exception in CP-140609. Dec.14: 85->100","24.229, 24.259, 24.604",64,33,null,null,"2014-04-07","2014-12-04"]
[4789,641008,"   (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (draft-holmberg-dispatch-iotl)","NNI_RS",2,"Rel-12","C1-IETF","2014-06-13","2014-12-09",1,"CP-140288","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Publication requested¦7/3/16: 50%->100","draft-holmberg-dispatch-iotl",64,33,null,null,"2014-06-06","2016-03-07"]
[4792,640009,"Representational State Transfer (REST) reference point between Application Function (AF) and Protocol Converter (PC)","REST_AF_PC",1,"Rel-12","C3","2014-06-13","2014-12-09",1,"CP-140451","CP-140561","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","CP#65 completion 09/14=>12/14. TS 29.201v200 for Approval. Exception in CP-140561. Dec.14: 80->100","29.213, 29.214, new 29.201",64,33,null,null,"2014-06-10","2014-12-04"]
[4795,641011,"   (IETF) Overload Control for PCC based Diameter applications","DOCME-PCC",2,"Rel-12","C3-IETF","2014-06-13","2014-12-09",1,"CP-140405","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress¦7/3/16: 50%->100","draft-ietf-dime-ovli",64,33,null,null,"2014-06-10","2016-03-07"]
[4796,650004,"Network Initiated USSD Simulation Services in IMS","USSI-NET",1,"Rel-12","C1","2014-09-12","2014-12-09",1,"CP-140625","CP-140610","AT&T","Martin Dolly (md3135@att.com)","CP#65 exception in CP-140610. Dec.14: 75->100",24.39,65,33,null,null,"2014-07-28","2014-12-04"]
[4799,610016,"   Test part: Introduction of ER-GSM band for GSM-R","RT_ERGSM",2,"Rel-12","G3new","2013-09-02","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","GP#61 completed","51.010, 51.021",59,31,null,null,"2013-09-04","2014-03-07"]
[4803,570202,"   CT part: Downlink Multi Carrier GERAN","DMCG",2,"Rel-12","C1","2012-09-10","2014-09-11",1,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","CP#65 completed",24.007999999999999,55,29,null,null,"2012-09-03","2014-07-28"]
[4806,590333,"   CT1 introduction of MS capability support for MS supporting MSRD for VAMOS","MSRD_VAMOS",2,"Rel-12","C1","2013-03-01","2013-12-06",1,"GP-130849","-","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","CP#62 completed",24.007999999999999,57,30,null,null,"2013-03-04","2014-08-29"]
[4809,620014,"New Training Sequence Codes (TSC) for GERAN","NewToN",1,"Rel-12","G1,G2,C1","2013-11-22","2014-12-09",0.93,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002","GERAN",60,32,null,null,"2013-11-22","2014-05-27"]
[4813,550016,"Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS","HSPA_LTE_measRP_MIMO",1,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-120368","-","Vodafone","Luis Anaya","RP#59 moved to Rel-12. Triggered by FS_HSPA_LTE_measRP_MIMO_multi-antenna. Core functionality exists since Rel-6 & Rel-7 (MIMO). Adds a very generic test method to test UEs with 2 or more Rx antennas","UTRA, LTE",55,28,null,null,"2012-02-23","2013-03-14"]
[4816,570121,"   Core part: Further enhancements to H(e)NB mobility - Part 3","EHNB_enh3-Core",2,"Rel-12","R3,R2","2012-09-12","2013-12-06",1,"RP-130741","RP-131508","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 completed","25.304, 25.331, 25.367, 25.467, 25.469, 36.300, 36.331",57,29,null,null,"2012-09-04","2013-11-29"]
[4819,590219,"   Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA","LCS_BDS-UTRA-Perf",2,"Rel-12","R4","2013-03-07","2014-06-13",1,"RP-130416","RP-140714","ZTE","Ling Soonleh (soonleh.ling@zte.com.cn)","RP#64 completed. TS 25.173v100 for 1-step Approval","25.172 (FDD), new 25.173 (TDD)",59,30,null,null,"2013-02-26","2014-06-11"]
[4820,590319,"   Core part: Support for BeiDou Navigation Satellite System (BDS) for LTE","LCS_BDS-LTE-Core",2,"Rel-12","R2","2013-03-04","2013-12-06",1,"RP-130416","RP-131525","CATR","Ying Du (duying1@catr.cn)","RP#62 completed","36.305, 36.355",59,30,null,null,"2013-02-26","2013-11-29"]
[4823,620011,"Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",1,"Rel-12","G2,G1,G3new","2013-11-22","2015-03-13",0.93,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001","GERAN",60,32,null,null,"2013-11-22","2014-03-01"]
[4827,620311,"   Deleted - Test part: Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN-MStest",2,"Rel-12","G3new","2013-11-22","2014-02-28",1,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#61 stopped","51.010-1",60,32,"GP-61","PCG-32","2013-11-22","2014-03-01"]
[4830,600219,"   Deleted - Perf. part: New Base Station specification structure","BSspec_struc-Perf",2,"Rel-12","R4","2013-06-20","2013-12-06",1,"RP-130851","RP-131514","Ericsson","johan.skold@ericsson.com","RP#62 stopped (at 0% completion)","25.113, 25.141, 25.142, 36.113, 36.141, 37.113, 37.141, 37.810, New 37.xyz (New RF test specification, New 37.xyw (ew EMC specification)",60,31,"RP-62","PCG-32","2013-06-17","2013-11-29"]
[4834,670047,"   UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-UEConTest",2,"Rel-12","R5","2015-03-16","2015-12-15",1,"RP-150835","RP-151163","Ericsson",null,"03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163¦1/1/16",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4838,610003,"   CT aspects for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON (Stage 3)","LTE_HRPD_SON-CT",2,"Rel-12","C4","2013-09-04","2013-09-06",1,"CP-130434","-","Huawei","Xiaoyan SHI (sean.shixiaoyan@huawei.com","CP#61 WID approved & Completed","29.274, 29.276, 29.280",61,31,null,null,"2013-08-11","2013-08-13"]
[4841,620142,"   Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-Core",2,"Rel-12","R4,R2","2013-12-15","2014-12-15",1,"RP-132061","RP-141787","Ericsson","christopher.callender@ericsson.com","¦CD:Thu 18/12/14->Mon 15/12/14¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787","25.133, 25.331, 36.133",62,32,null,null,"2013-12-07","2015-01-12"]
[4844,620048,"WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw",1,"Rel-12","R2,S2,C1,C4","2013-12-06","2014-12-09",1,"RP-140981","-","Intel","sasha.sirotkin@intel.com","Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw)","UTRA, LTE",62,32,null,null,"2013-12-09","2013-12-09"]
[4845,620148,"   Core part: WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-Core",2,"Rel-12","R2","2013-12-06","2014-09-12",1,"RP-140981","RP-141310","Intel","sasha.sirotkin@intel.com","SP#65 completed","25.304, 25.306, 25.331, 36.304, 36.306, 36.331",62,32,null,null,"2013-12-09","2014-09-09"]
[4848,640106,"      CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3)","UTRA_LTE_WLAN_interw-CT",3,"Rel-12","C1","2014-09-09","2014-12-09",1,"CP-140623","CP-140720","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd.","24.008, 24.301, 24.302, 24.312",64,33,null,null,"2014-04-07","2015-03-03"]
[4852,530025,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7",2,"Rel-12","R4","2011-09-19","2014-09-12",1,"RP-141487","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band CA 2DL","LTE",53,27,null,null,"2011-09-15","2013-12-07"]
[4855,530029,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25",2,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","-","Sprint","George.Cummings@sprint.com","Intra-band NC","LTE",53,27,null,null,"2011-09-15","2013-06-07"]
[4858,550010,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL",2,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","-","SK Telecom","Seungpyo Hong","Inter-band 2UL","LTE",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[4862,550011,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","-","SK Telecom","haesung.park@sk.com","Intra-band NC","LTE",55,28,null,null,"2012-02-23","2012-02-23"]
[4865,560015,"   Deleted - LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1",2,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-130298","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Intra-band C ","LTE",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[4866,560115,"      Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1-Core",3,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-120826","RP-130549","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#60 stopped at 10% completion (rationale in RP-130670)","36.101, 36.104, 36.133, 36.141, 36.307, new 36.835",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[4869,560116,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4-Core",3,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-131135","RP-131039","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed. Updated WID RP-130842=>RP-131135","36.101, 36.104, 36.133, new 36.833-2-04",56,29,null,null,"2012-06-13","2013-08-28"]
[{"$f":"A4872+1","v":4872},560117,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4-Core",3,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-130175","RP-131007","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed","36.101, 36.104, 36.133, new generic 36.851",56,29,null,null,"2012-06-13","2013-08-28"]
[4876,570212,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29-Perf",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","RP-130536","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[4879,570213,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26-Perf",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","RP-130528","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#60 completed. Updated WID RP-130199=>RP-130658","36.101, 36.104, 36.133, 36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-07"]
[4882,570214,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19-Perf",3,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130198","RP-130526","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-08"]
[4886,570016,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3",2,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","-","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","Intra-band NC","LTE",57,29,null,null,"2012-09-03","2013-08-29"]
[4889,570018,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8",2,"Rel-12","R4","2012-02-02","2013-06-14",1,"RP-130181","-","Softbank Mobile","Kenichi Kihara","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-11-28"]
[4890,570118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Core",3,"Rel-12","R4","2012-02-02","2013-06-14",1,"RP-130181","RP-130515","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.101, 36.104, new generic 36.851",57,29,null,null,"2012-09-03","2013-06-04"]
[4895,580032,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26",2,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[4897,580232,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26-Perf",3,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","RP-131006","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.141, 36.307",58,30,null,null,"2012-12-10","2013-08-28"]
[4901,580034,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12",2,"Rel-12","R4","2012-12-10","2014-09-12",1,"RP-140474","-","US Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 2DL","LTE",58,30,null,null,"2012-12-10","2014-09-08"]
[4904,580035,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","-","Ericsson","christian.bergljung@ericsson.com","Intra-band NC","LTE",58,30,null,null,"2012-12-10","2013-02-28"]
[4908,580136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-131679","RP-131567","NII Holdings","bill.shvodian@nii.com","RP#62 completed","36.101, 36.104, new 36.833-1-27",58,30,null,null,"2012-12-10","2013-12-06"]
[4911,590122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130523","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-02-26"]
[4914,590124,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130533","NTT DOCOMO","Kei ANDO","RP#60 completed","36.101, 36.104, 36.133, new generic 36.851",59,30,null,null,"2013-02-26","2013-06-08"]
[4915,590224,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Perf",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130534","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141, 36.307",59,30,null,null,"2013-02-26","2013-06-08"]
[4918,590225,"      Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Perf",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131550","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.141, 36.307",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[4921,590229,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141941","RP-141732","Huawei","Liu Ye (leo.liuye@huawei.com)","¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732",36.133000000000003,59,30,null,null,"2013-02-26","2015-01-12"]
[4925,590023,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140853","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[4928,590031,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141160","-","Nokia","petri.j.vasenkari@nokia.com","Inter-band CA 2UL. RP#65 updated WID RP-140476=>RP-141160.","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[4932,590126,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[4935,590127,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39-Core",3,"Rel-12","R4","2013-03-04","2014-03-06",1,"RP-131171","RP-140428","China Mobile","Li Nan (linan@chinamobile.com)","RP#63 completed","36.101, 36.104, 36.133, New 36.833-1-39 [instead of 36.845]",59,30,null,null,"2013-02-26","2014-03-05"]
[4938,600122,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL","LTE_CA_NC_2UL-Core",3,"Rel-12","R4","2013-06-18","2014-12-15",1,"RP-141962","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141962¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, 36.306, 36.331, New 36.833-4",60,31,null,null,"2013-06-17","2015-01-12"]
[4939,600023,"   Deleted -LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL",2,"Rel-12","R4","2013-06-19","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","Intra-band NC 2UL","LTE",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[4942,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[4945,600025,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band C CA","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[4949,600126,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131700","RP-131577","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-2-23",60,31,null,null,"2013-06-17","2013-12-19"]
[4952,600128,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","RP-131705","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",60,31,null,null,"2013-06-05","2013-12-02"]
[4956,600229,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset-Perf",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","RP-131004","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed",36.307000000000002,60,31,null,null,"2013-06-05","2013-08-28"]
[4960,600031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[4963,600032,"   Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131130","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4964,600132,"      Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131130","RP-131590","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131652 discussion","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4967,600133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Core",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131697=>RP-141212","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[4971,600234,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30","LTE_CA_B4_B5_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141213","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[4974,600235,"      Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131133","RP-131599","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131653 discussion","36.101, 36.104, 36.133, 36.141, 36.307",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[4977,600236,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[4981,600038,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-141435","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[4984,600039,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13","LTE_CA_B4_B4_B13",2,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141433","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[4987,610017,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","-","Huawei","Liehai Liu (liuliehai@huawei.com)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[4988,610117,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28-Core",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","RP-131545","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#62 completed","36.101, 36.104, 36.307",61,31,null,null,"2013-09-07","2013-09-07"]
[4991,610118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Core",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131543","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",61,31,null,null,"2013-09-07","2013-12-02"]
[4995,610219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11","LTE_CA_B1_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131354","RP-140569","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#64 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2014-06-20"]
[4998,610220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","RP-141084","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#65 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2014-09-08"]
[5001,610221,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7-Perf",3,"Rel-12","R4","2013-09-09","2013-12-02",1,"RP-131365","RP-131542","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#62 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2013-12-02"]
[5005,610023,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2",2,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","-","Ericsson","imadur.rahman@ericsson.com","Intra-band non-contig. CA 2DL","LTE",61,31,null,null,"2013-09-07","2013-09-07"]
[5008,620018,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","-","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5009,620118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.101, 36.104, 36.133, new generic 36.851",62,32,null,null,"2013-12-07","2014-09-08"]
[5012,620119,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-141803","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, 36.307, new generic 36.851",62,32,null,null,"2013-12-07","2015-01-12"]
[5017,620021,"   LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","-","NII Holdings","bill.shvodian@nii.com","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5020,620022,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5023,620072,"   LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","Inter-band 2DL","LTE",62,32,null,null,"2013-12-09","2014-03-05"]
[5026,620024,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","-","KT","Ilwhan Kim (ilwhan.kim@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-22"]
[5030,620125,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed. Updated WID RP-140209=>RP-141462","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[5033,620126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5034,620226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5037,620227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12","LTE_CA_B2_B4_B12-Perf",3,"Rel-12","R4","2013-12-09","2014-12-11",1,"RP-140189","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completion 09/14=>12/14","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-12"]
[5040,620228,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-140190","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5044,620030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5047,620031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20","LTE_CA_B3_B7_B20",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141224","-","Vodafone","luis.anaya@vodafone.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-21"]
[5050,620033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5054,620134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5057,620135,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131653=>RP-141214","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5058,620235,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5061,620237,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","RP-140569","CATT","Yuexia Song (songyuexia@catt.cn)","RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728","36.141, 36.307",62,32,null,null,"2013-12-07","2014-06-12"]
[{"$f":"A5064+1","v":5064},620236,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","RP-140569","Orange","Olfa BEN HADDADA","RP#64 completed",36.307000000000002,62,32,null,null,"2013-12-07","2014-06-20"]
[5068,620039,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5071,620050,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5",2,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","-","SK Telecom","haesung.park@sk.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-09","2014-09-21"]
[5075,620151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-141017=>RP-141222","36.101, 36.104, 36.133, new generic 36.851 (2 Band CA with 1UL), 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5078,620152,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20","LTE_CA_B1_B7_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141223","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-140243=>RP-141223","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5082,620253,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732","36.101, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-09","2015-01-12"]
[5083,630022,"   Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700_B29_Bwset",2,"Rel-12","R4","2014-03-03","2014-03-06",1,"RP-140084","-","AT&T","marc.grant@att.com","Inter-band 2DL/1UL","LTE",63,32,null,null,"2014-03-10","2014-03-12"]
[5086,630123,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140447","RP-140569","NSN","iwajlo.angelow@nsn.com","RP#64 completed","36.101, 36.851",63,32,null,null,"2014-03-10","2014-06-20"]
[5089,630025,"   Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback","LTE_CA_3DL_FB_BW",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140454","-","Qualcomm","Fong Gene (gfong@qti.qualcomm.com)","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5093,630226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_","36.141, 36.307",63,32,null,null,"2014-03-10","2015-03-10"]
[5096,630227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[5100,630029,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","-","China Mobile","Pan Qun (panqun@chinamobile.com)","Intra-band contig. CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5103,630035,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset",2,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[5106,630036,"   LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","-","Huawei","leo.liuye@huawei.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[5107,630136,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","RP-141084","Huawei","leo.liuye@huawei.com","RP#65 completed","36.101, 36.104, 36.851",63,32,null,null,"2014-03-10","2014-09-08"]
[5110,630137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141709","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed. Updated WID RP-140116=>RP-141709","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-22"]
[5113,630138,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141236","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","RP#65 completed. Updated WID RP-140117=>RP-141236","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-21"]
[5117,630245,"      Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-140452","RP-141084","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#65 completed",36.307000000000002,63,32,null,null,"2014-03-10","2014-09-08"]
[5120,640021,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_BWset",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","-","AT&T","marc.grant@att.com","2DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5124,640127,"      Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","RP-150188","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:10%->90%¦Stat Rep: RP-141303->RP-141839 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141839->RP-150188",36.100999999999999,64,33,null,null,"2014-06-16","2015-04-01"]
[5127,640228,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141, 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5130,640229,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141, 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5131,640030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5134,640031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5138,640135,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated WID RP-140950=>RP-141127",36.100999999999999,64,33,null,null,"2014-06-16","2014-09-08"]
[5143,630034,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","-","Intel","xinrong.wang@intel.com ","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5145,630234,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.133, 36.141, 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5149,630040,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5152,630041,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5155,630042,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5156,630142,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5159,630143,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26","LTE_CA_B1_B3_B26-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140194","RP-141732","China Telecom","Zhao Dong (zhaodong@ctbri.com.cn)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5163,630244,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28-Perf",3,"Rel-12","R4","2014-03-11","2014-12-15",1,"RP-141788","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141788¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5166,640223,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133, 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[5169,640224,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133, 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[5173,640033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140963","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5176,640034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140964","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5177,640134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5180,650146,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.307, New 36.833-x-yz ",65,33,null,null,"2014-06-16","2015-01-12"]
[5183,650148,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41","LTE_CA_B39_B39_B41-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142302","RP-141732","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5187,650250,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","RP-141732","AT&T","marc.grant@att.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5190,650252,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5193,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[5197,570217,"   Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band-Perf",2,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130843","RP-130570","AT&T","marc.grant@att.com","RP#60 completed. Updated WID RP-121419=>RP-130843","36.101, 36.133, 36.141",57,29,null,null,"2012-09-03","2013-06-11"]
[5200,570119,"   Core part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Core",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-121414","RP-130567","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#60 completed. TR 36.840 v100 for 1-step Approval","36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new 36.840",57,29,null,null,"2012-09-03","2013-06-05"]
[5204,570120,"   Core part: Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh-Core",2,"Rel-12","R1","2012-09-11","2014-06-13",1,"RP-121416","RP-140652","Alcatel-Lucent","Min Zhang (min.hs.zhang@alcatel-lucent.com)","RP#64 completed","36.211, 36.212, 36.213, 36.331",57,29,null,null,"2012-09-03","2014-07-06"]
[5205,570220,"   Perf. part: Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh-Perf",2,"Rel-12","R4","2012-09-15","2014-12-15",1,"RP-121416","RP-142042","Alcatel-Lucent","ren.da@alcatel-lucent.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141378->RP-142042",36.100999999999999,57,29,null,null,"2012-09-03","2015-01-12"]
[5208,570125,"   Deleted - Core part: New Carrier Type for LTE","LTE_NCT-Core",2,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122028","RP-130984","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 20% completion","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.321, 36.331",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[5212,580227,"   Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Perf",2,"Rel-12","R4","2012-12-15","2015-09-15",1,"RP-121772","RP-151447","CATT","Zukang Shen (shenzukang@catt.cn)","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141342->RP-141948 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141948->RP-150154 03/07/15: Compl:55%->95% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150","36.101, 36.104, 36.133, 36.141",58,30,null,null,"2012-09-03","2015-09-29"]
[5215,580129,"   Core part: HetNet Mobility enhancements for LTE","HetNet_eMOB_LTE-Core",2,"Rel-12","R2,R4","2012-04-13","2014-09-12",1,"RP-122007","RP-141413","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","SP#65 completed","36.133, 36.304, 36.331",58,30,null,null,"2012-12-10","2014-09-09"]
[5218,580031,"8 Rx Antennas for LTE UL","LTE_UL_8Rx",1,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","-","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","WI has perf. part only (as change from 4Rx to 8Rx has no Core spec impact) ","LTE",58,30,null,null,"2012-09-03","2012-12-10"]
[5222,600213,"   Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD-Perf",2,"Rel-12","R4","2013-06-15","2014-12-15",1,"RP-140465","RP-141972","Nokia","lars.e.lindh@nokia.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141374->RP-141972","36.101, 36.104, 36.133",60,31,null,null,"2013-06-17","2015-01-12"]
[5225,600214,"   Perf. part: LTE Coverage Enhancements","Cov_Enh_LTE-Perf",2,"Rel-12","R4","2013-06-15","2014-12-15",1,"RP-130833","RP-141833","China Telecom","Xiaoming She (shexm@ctbri.com.cn)","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141149->RP-141833","36.101, 36.104, 36.133, 36.141",60,31,null,null,"2013-06-17","2015-01-12"]
[5226,650012,"   Test part: LTE Coverage Enhancements","Cov_Enh_LTE-UEConTest",2,"Rel-12","R5","2014-09-15","2015-06-15",1,"RP-141150","RP-150631","China Telecom","YANG Shan (yangshan@ctbri.com.cn)","¦Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631","36.508, 36.523-1, 36.523-2, 36.523-3",65,33,null,null,"2014-09-09","2015-06-18"]
[5229,620073,"   Perf. part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Wed 17/12/14->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821",36.133000000000003,62,32,null,null,"2013-12-18","2015-01-12"]
[5232,620240,"   Perf. part: Dual Connectivity for LTE","LTE_SC_enh_dualC-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141797","RP-150791","NTT DOCOMO","kunihiko.teshima.hg@nttdocomo.com","¦Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791","36.101, 36.104, 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[5236,620041,"E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2013-12-15","2017-06-15",1,"RP-141459","-","Huawei","Elean FAN (fanxiaoan@huawei.com)","Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041)","LTE",62,32,null,null,"2013-12-09","2014-09-15"]
[5239,680068,"   UE Conformance Test Aspects - E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-UEConTest",2,"Rel-12","R5","2015-06-15","2017-06-15",1,"RP-160414",null,"Huawei",null,"tested Core part: LTE_SC_enh_L1-Core 29/09/15: Compl:0%->10% 29/09/15: CD:Wed 15/06/16->Thu 15/12/16 29/09/15: Stat Rep: -->RP-151247¦1/1/16: Compl:10%->40%¦ ",null,68,35,null,null,"2015-07-03","2017-06-19"]
[5243,630131,"   Core part: Smart Congestion Mitigation in E-UTRAN","SCM_LTE-Core",2,"Rel-12","R2","2014-03-06","2014-09-12",1,"RP-140434","RP-141292","LG Electronics","youngdae.lee@lge.com","RP#65 completed",36.331000000000003,63,32,null,null,"2014-03-10","2014-09-21"]
[5246,670051,"   UE Conformance Test Aspects - Smart Congestion Mitigation in E-UTRAN","SCM_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2015-09-15",1,"RP-150797","RP-151445","NTT DOCOMO",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150202->RP-150797 03/07/15: Stat Rep: ->RP-150794 29/09/15: Compl:60%->100% 29/09/15: Stat Rep: RP-150794->RP-151445",null,67,34,null,null,"2015-04-01","2015-09-29"]
[5249,630046,"Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS",1,"Rel-12","R1,R2,R4,R3","2014-03-11","2017-03-15",1,"RP-141634","-","MediaTek","Craig.Burnet@mediatek.com","follow-up of TR 36.866 FS_LTE_NAICS","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5250,630146,"   Core part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Core",2,"Rel-12","R1,R2,R4,R3","2014-07-11","2014-12-15",1,"RP-141634","RP-141866","MediaTek","Craig.Burnet@mediatek.com","CD:Mon 08/12/14->Mon 15/12/14¦Compl:95%->100%¦Stat Rep: RP-141621->RP-141866","36.211, 36.213, 36.300, 36.331, 36.423",63,32,null,null,"2014-03-10","2015-01-12"]
[5253,630047,"Performance requirements of interference cancellation and suppression receiver for SU-MIMO","LTE_SUMIMO_RX",1,"Rel-12","R4","2014-03-06","2015-12-15",1,"RP-140520","-","Huawei","Qian Cheng (Q.Cheng@Huawei.com)","no Core part","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[{"$f":"A5256+1","v":5256},580028,"HSPA signalling enhancements for more efficient resource usage for LCR","LCR_TDD_HSPA_sign_enh",1,"Rel-12","R1,R2,R3,R4","2012-12-11","2013-12-20",1,"RP-121984","-","CATT","Yanping Xing (xingyanping@catt.cn)","Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026","UTRA",58,30,null,null,"2012-12-10","2012-12-10"]
[5260,600117,"   Core part: HNB Positioning for UTRA","UTRA_HNB_Pos-Core",2,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","RP-131974","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID)","25.305, 25.467, new 25.470",60,31,null,null,"2013-06-17","2013-12-09"]
[5265,610026,"UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob",1,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","-","Huawei","Xudong Yang (yangxudong@huawei.com)","Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2013-09-07"]
[5268,620054,"UMTS Heterogeneous Networks enhancements","UTRA_HetNet_enh",1,"Rel-12","R1,R2,R3,R4","2013-12-06","2014-12-15",1,"RP-141701","-","Huawei","carmela.cozzo@huawei.com","Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet)¦the 1st part is addressed by UTRA_HetNet_mob UID_610026","UTRA",62,32,null,null,"2013-12-09","2014-09-15"]
[5271,620055,"Enhanced Broadcast of System Information","UTRA_SIBenh",1,"Rel-12","R2,R1,R3,R4","2013-12-06","2014-12-15",1,"RP-140131","-","Ericsson","martin.van.der.zee@ericsson.com","Triggered by Rel-12 UTRA TR 25.704 Study on Enhanced Broadcast of System Information (FS_UTRA_SIBenh)","UTRA",62,32,null,null,"2013-12-09","2014-09-15"]
[5274,620049,"Further Enhanced Uplink (EUL) enhancements","EDCH_enh",1,"Rel-12","R2","2013-12-15","2015-03-13",1,"RP-140127","-","Ericsson","mark.curran@ericsson.com","Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh)","UTRA",62,32,null,null,"2013-12-09","2014-09-15"]
[5275,620149,"   Core part: Further Enhanced Uplink (EUL) enhancements","EDCH_enh-Core",2,"Rel-12","R2,R1,R3,R4","2013-12-15","2014-12-15",1,"RP-140127","RP-141860","Ericsson","mark.curran@ericsson.com","¦Stat Rep: RP-141684->RP-141860","25.211, 25.212, 25.214, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.425, 25.433, 25.435",62,32,null,null,"2013-12-09","2015-01-12"]
[5278,660032,"(IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id)","TEI12_IETF",1,"Rel-12","C1-IETF","2014-06-13","2014-12-09",1,"CP-140815",null,"Alcatel-Lucent",null,"Mar15: In WGLC¦21/3/17: 50%->100; 9/4/21: RFC 7989 added;","draft-ietf-insipid-session-id; RFC 7989",66,34,null,null,"2014-12-04","2021-04-09"]
[5281,470020,"Study on Alternatives to E.164 for Machine-Type Communications","FS_AMTC",1,"Rel-12","S1","2010-03-25","2012-03-07",1,"SP-100198","-","T-Mobile USA","gary.jones@T-Mobile.com","SP#55 completed. Determine an alternative to E.164 for identifying individual devices and route messages between those devices",22.988,47,24,null,null,"2010-03-23","2012-02-22"]
[5285,500036,"Study on non-MTC Mobile Data Applications Impacts","FS_MODAI",1,"Rel-12","S1","2010-12-16","2011-12-14",1,"SP-100889","-","Huawei, China Mobile","Amar Deol (adeol@huawei.com), Gang Li","SP#54 completed. Linked to UID_490036 SA2 Rel-11 TR 23.843 Study on Core Network Overload solutions (FS_CNO)",22.800999999999998,50,26,null,null,"2010-11-25","2011-11-29"]
[5288,540028,"Study on RAN Sharing Enhancements","FS_RSE",1,"Rel-12","S1","2011-12-14","2013-06-19",1,"SP-110820","-","NEC","joerg.swetina@neclab.eu","SP#60 completed. Extend Rel-6 Network Sharing UID_31018 (basic scenarios of network/RAN sharing) to cover more complex scenarios that arise due to recent needs for more dynamic co-operation among operators",22.852,54,28,null,null,"2011-11-29","2013-06-18"]
[5292,490234,"   SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S2","2010-09-23","2012-06-20",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#56 completed. TR 23.844v100 for Information and Approval",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-14"]
[5295,490136,"   Study on Core Network Overload solutions (Phase 1)","FS_CNO",2,"Rel-12","S2","2010-09-23","2012-12-12",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","Phase 1: complete study of overload control related to MAP /Diameter signalling, other 3GPP Core Network signalling optimization",23.843,49,25,null,null,"2010-08-31","2012-08-30"]
[5298,510061,"Study on S2a Mobility based On GTP and WLAN access to EPC","FS_SaMOG",1,"Rel-12","S2","2011-03-23","2013-09-11",1,"SP-120426","-","ZTE","Tricci So (tso@zteusa.com)","SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI",23.852,51,26,null,null,"2011-02-21","2013-07-25"]
[5299,560037,"Study on Optimized Offloading to WLAN in 3GPP-RAT Mobility","FS_WORM",1,"Rel-12","S2","2012-06-18","2013-09-11",1,"SP-120261","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","SP#61 completed. Linked to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP), UID_410043 MAPIM, UID_450041 IFOM, UID_530046 SaMOG",23.89,56,29,null,null,"2012-05-11","2013-07-25"]
[5302,410143,"   SA1 part of Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",2,"Rel-12","S1","2008-08-08","2011-09-21",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","SP#53 completed",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5306,530047,"Deleted - Study on Firewall traversal (Stage 2)","FS_Fire",1,"Rel-12","S3","2011-06-17","2014-09-17",1,"SP-120849","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#65 stopped. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043",33.83,53,27,"SP-65","PCG-33","2011-07-19","2014-05-21"]
[5309,540033,"Study on Improved Support for Dynamic Adaptive Streaming over HTTP in 3GPP","FS_IS_DASH",1,"Rel-12","S4","2011-12-14","2014-09-16",1,"SP-140486","-","Qualcomm","c_tstock@qualcomm.com","SP#65 completed. TR 26.938v200 for Approval. SP#60 TR 26.938v100 for Information. Linked to Feature UID_470034 HTTP-based Streaming and Download Services",26.937999999999999,54,28,null,null,"2011-12-14","2014-09-05"]
[5312,510046,"Study on management of Heterogeneous Networks","FS_OAM_HetNet",1,"Rel-12","S5","2011-03-23","2014-06-18",1,"SP-130046","-","Ericsson","ulf.hubinette@ericsson.com","SP#64 completed",32.835000000000001,51,26,null,null,"2012-06-02","2014-05-27"]
[5316,580052,"Study on Alarm Management","FS_OAM_AM",1,"Rel-12","S5","2012-12-07","2013-09-11",1,"SP-120774","-","TeliaSonera","tommy.berggren@teliasonera.com","SP#61 completed",32.859000000000002,58,30,null,null,"2012-11-21","2013-09-04"]
[5319,590011,"Study on XML based access of AF to the PCRF","FS_XML_AF_PCRF",1,"Rel-12","C3","2013-03-01","2013-12-04",1,"CP-130167","-","Alcatel-Lucent","horst.brinkman@alcatel-lucent.com","CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications",29.817,59,30,null,null,"2013-02-16","2014-06-19"]
[5322,620002,"Study on Shared Data Update for Multiple Subscribers","FS_SHARED_SubData_UPD",1,"Rel-12","C4","2013-12-06","2014-12-09",1,"CP-130809","-","Huawei","Susan Shi (susan.shishufeng@huawei.com)","CP#65 TR 29.854v200 for Approval. Completion 09/14=>12/14. Dec.14: 80->85%. Mar.15: 100%",29.853999999999999,62,32,null,null,"2013-11-19","2015-03-04"]
[5326,500016,"Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN","FS_LCS_LTE_RFPMT",1,"Rel-12","R4","2010-12-10","2013-09-06",1,"RP-120885","RP-131082","Polaris Wireless","Scot Gordon (sgordon@polariswireless.com)","RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005","LTE 36.809",50,26,null,null,"2010-12-10","2013-08-28"]
[5327,530052,"Study on Provision of low-cost MTC UEs based on LTE","FS_LC_MTC_LTE",1,"Rel-12","R1,R2,R4","2011-09-19","2013-06-14",1,"RP-121441","RP-130583","Vodafone","prakash.bhat@vodafone.com","RP#60 completed","LTE 36.888",53,27,null,null,"2011-09-19","2013-06-07"]
[5331,580044,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects","FS_LTE_SC_enh_hilayer",1,"Rel-12","R2,R3","2012-12-10","2013-12-06",1,"RP-122033","RP-131619","NTT DOCOMO","Hideaki Takahashi (h-takahashi@nttdocomo.co.jp)","RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.842",58,30,null,null,"2012-12-10","2013-12-03"]
[5334,580046,"Study on Energy Saving Enhancement for E-UTRAN","FS_Netw_Energy_enh_LTE",1,"Rel-12","R3","2012-12-10","2014-06-13",1,"RP-122035","RP-140604","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","RP#64 completed. Identify potential solutions for energy saving in E-UTRAN non-overlapping scenario. Evaluate possible enhancements in overlapping scenario, so that a subset can be used for further investigation/standardization","LTE 36.887",58,30,null,null,"2012-12-10","2014-06-12"]
[5337,590018,"Study on Network-Assisted Interference Cancellation and Suppression for LTE","FS_LTE_NAICS",1,"Rel-12","R1,R4","2013-03-08","2014-03-06",1,"RP-130404","RP-132108","MediaTek","jeff.zhuang@mediatek.com","RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work","LTE 36.866",59,30,null,null,"2013-02-26","2014-03-14"]
[5341,620044,"Study on RAN aspects of RAN Sharing Enhancements for LTE","FS_RSE-RAN_LTE",1,"Rel-12","R3","2013-12-06","2014-06-13",1,"RP-132116","RP-140746","NEC","Siva.Vakeesar@emea.nec.com","RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1)","LTE 36.856",62,32,null,null,"2013-11-27","2014-06-12"]
[5344,550021,"Study on Passive InterModulation (PIM) handling for UTRA and LTE Base Stations","FS_BS_PIM",1,"Rel-12","R4,G1","2012-03-05","2013-09-06",1,"RP-120268","RP-131076","Ericsson","johan.skold@ericsson.com","RP#61 completed (Conclusion: no spin-off WI). Linked to Rel-10 WI on Multi-standard radio Base Station RF requirements for non-contiguous spectrum deployments (MSR_NC) UID_480025","UTRA, LTE 37.808",55,28,null,null,"2012-02-23","2013-08-30"]
[5345,580045,"Study on WLAN/3GPP Radio Interworking","FS_UTRA_LTE_WLAN_interw",1,"Rel-12","R2","2012-12-10","2013-12-06",1,"RP-122038","RP-131611","Intel","sasha.sirotkin@intel.com","RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized¦User experience suboptimal when UE connects to overloaded WLAN.","UTRA, LTE 37.834",58,30,null,null,"2012-12-10","2013-12-03"]
[5348,580049,"Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","FS_UTRA_LTE_1980_2170_REG1",1,"Rel-12","R4","2012-12-11","2014-09-12",1,"RP-140505","RP-141099","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1","UTRA, LTE 37.846",58,30,null,null,"2012-12-10","2014-09-22"]
[5351,570024,"Study on UMTS heterogeneous networks","FS_UTRA_HetNet",1,"Rel-12","R1,R2,R3","2012-06-12","2013-09-06",1,"RP-121436","RP-131606","Huawei","carmela.cozzo@huawei.com","RP#62 completed","UTRA 25.800",57,29,null,null,"2012-09-03","2013-12-02"]
[5355,580043,"Study on Further Enhanced Uplink (EUL) enhancements","FS_EDCH_enh",1,"Rel-12","R2,R1,R3","2012-12-10","2013-12-06",1,"RP-130347","RP-131608","Ericsson","alessandro.caverni@ericsson.com ","RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.)","UTRA 25.700",58,30,null,null,"2012-12-10","2013-12-02"]
[5358,0,"--- RELEASE 11 ---","-",1,"Rel-11","SP,CP,GP,RP","2013-06-02","2014-09-16",1,"-","-","-","-","-","-","-","-",null,null,"2006-05-31","2014-02-18"]
[5361,500025,"   Stage 2 for Advanced IP Interconnection of Services","IPXS",2,"Rel-11","S2","2010-12-16","2011-12-14",1,"SP-100876","-","Ericsson","fredrik.lindholm@ericsson.com","SP#54 completed",23.228000000000002,50,26,null,null,"2010-12-01","2011-11-28"]
[5365,480030,"System Improvements to Machine-Type Communications","SIMTC",1,"Rel-11","S1,S2,S5,C1,C3,C4,C6,R2,R3,R5","2009-12-10","2014-03-06",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#58 completed. Updated WID SP-110877=>SP-120848. Enhancements to Rel-10 Feature UID_410031 (NIMTC) based on Rel-11 Study on enhancements to MTC","-",48,25,null,null,"2010-05-28","2012-11-12"]
[5368,520021,"   BB1: Stage 2 Reachability Aspects of SIMTC","SIMTC-Reach",2,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682)","23.221, New 23.368",52,27,null,null,"2011-05-26","2012-11-12"]
[5369,520121,"      Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7)","SIMTC-Reach",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","-",52,27,"SP-54","PCG-28","2011-05-26","2012-11-12"]
[5372,520421,"      Identifiers – especially removal of MSISDN dependencies in the architecture","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed","New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5375,530006,"   BB1: Stage 3 (CS+PS) Reachability Aspects of SIMTC","SIMTC-ReachCSPS",2,"Rel-11","C1,C3,C4,C6","2011-09-19","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","Stage 3",53,27,null,null,"2011-08-29","2015-01-22"]
[5379,530406,"      CT6 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C6","2011-09-19","2012-09-07",1,"CP-120617","-","ST Ericsson","Andrzej Winiarski","22/01: acronym modified",31.102,53,27,null,null,"2011-08-29","2015-01-22"]
[5382,530205,"      Stage 3 CS aspects for SIMTC ","SIMTC-CS",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed","Stage 3",53,27,null,null,"2012-06-15","2012-08-13"]
[5385,560002,"   Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",2,"Rel-11","C1,C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed","Stage 2/3",56,29,null,null,"2012-04-23","2012-11-17"]
[5387,560202,"      CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",3,"Rel-11","C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed. TS 29.338 v200 for Approval","23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New 29.338 ",56,29,null,null,"2012-04-23","2012-11-28"]
[5393,610014,"   Test part: System Improvements for Machine-Type Communications","SIMTC-UEConTest",2,"Rel-11","R5","2013-09-09","2014-03-06",1,"RP-140077","RP-140075","Ericsson","calle.hagenfeldt@ericsson.com","RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC","34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3",61,31,null,null,"2013-09-03","2014-03-03"]
[5394,540019,"   BB5: Charging of SIMTC (Stage 2/3)","SIMTC-CH",2,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-120848","-","Ericsson","patrik.teppo@ericsson.com","SP#58 completed","32.240, 32.251, 32.298, 32.299",54,28,null,null,"2011-10-24","2012-11-19"]
[5397,520222,"      Deleted - Small Data Transmissions (TS 22.368, 7.2.5)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5400,530307,"         Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-",31.102,53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[5404,520323,"      Deleted - MTC Monitoring (TS 22.368, 7.2.8)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-08","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5407,530208,"         Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-","31.101, 31.102",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[5411,530058,"      Deleted - MTC Location Privacy","SIMTC-Priv",3,"Rel-11","S3","2011-09-19","2012-09-12",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#57 stopped (activity transferred to Rel-12 Feature MTCe","TBD",53,27,"CP-57","PCG-29","2011-09-13","2012-11-12"]
[5414,480031,"Unstructured Supplementary Service Data (USSD) simulation service in IMS","USSI",1,"Rel-11","S1,C1,C3","2010-06-10","2012-12-07",1,"SP-100408","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","CP#58 completed","-",48,25,null,null,"2010-06-06","2012-11-19"]
[5417,520103,"      CT1 part of Stage 3 for USSD simulation service in IMS","USSI",3,"Rel-11","C1","2011-06-03","2012-12-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at, TS 24.390 Rapp: lili.yang@huawei.com","CP#58 completed","24.173, 24.229, new 24.390",52,27,null,null,"2011-05-18","2012-11-19"]
[5418,520203,"      CT3 part of Stage 3 for USSD simulation service in IMS","USSI",3,"Rel-11","C3","2011-06-07","2012-09-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","CP#57 completed",29.164999999999999,52,27,null,null,"2011-05-18","2012-08-13"]
[5421,510043,"   Stage 2 for QoS Control Based on Subscriber Spending Limits","QoS_SSL",2,"Rel-11","S2","2011-03-23","2011-09-21",1,"SP-110519","-","Huawei","Xu Xia (xiatony@huawei.com)","SP#53 completed",23.202999999999999,51,26,null,null,"2011-03-10","2011-08-12"]
[5424,490032,"Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",1,"Rel-11","S1,S2","2010-09-23","2012-03-07",1,"SP-110347","-","Vodafone","mona.mustapha@vodafone.com","SP#55 completed (Stage 2/3 specified under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021. Triggered by S1-102236/GSMA RILTE 10_007r1 (IREG LS_038 to 3GPP on Optimal Media Routing drawbacks)","-",49,25,null,null,"2010-08-31","2012-03-05"]
[5428,530021,"Inclusion of Media Resource Broker (Stage 2/3)","MRB",1,"Rel-11","C1,C3,IETF","2011-09-16","2013-06-14",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032","Stage 2/3",53,27,null,null,"2011-08-25","2012-06-06"]
[5431,530321,"      CT1 part of Stage 3 for Inclusion of Media Resource Broker","MRB",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed","24.229, 29.165",53,27,null,null,"2011-08-25","2012-08-14"]
[5435,500130,"   Stage 1 for Non Voice Emergency Services","NOVES",2,"Rel-11","S1","2010-12-16","2011-09-21",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed",22.100999999999999,50,26,null,null,"2010-11-29","2011-08-24"]
[5438,510147,"   Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",2,"Rel-11","S1","2011-03-23","2011-09-21",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 completed ",22.228000000000002,51,26,null,null,"2011-02-21","2011-08-24"]
[5441,520128,"   Stage 1 for Anonymous Call Rejection in the CS domain","ACR_CS",2,"Rel-11","S1","2011-06-07","2011-06-08",1,"SP-110421","-","Alcatel-Lucent","Betsy.Covell@alcatel-lucent.com","SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013)","22.004, 22.081, 22.082, 22.085, 22.088",52,27,null,null,"2011-05-19","2011-09-19"]
[5442,530011,"   Core Network aspects of Anonymous Call Rejection in the CS domain","ACR_CS-CN",2,"Rel-11","C4,C3","2011-09-14","2011-12-02",1,"CP-110587","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#54 completed","Stage 2/3",53,27,null,null,"2011-08-27","2011-08-27"]
[5445,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[{"$f":"A5448+1","v":5448},470023,"   Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2","2010-03-26","2012-06-20",1,"SP-120539","-","Ericsson","stefan.rommer@ericsson.com","SP#56 completed","23.203, new 23.139",47,24,null,null,"2009-12-06","2012-06-09"]
[5453,551002,"      Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface","BBAI_BBI-CT",3,"Rel-11","C4-IETF","2012-03-02","2012-06-15",1,"CP-120419","-","Lionel Morand","-","Draft removed from 3GPP documentation","draft-so-ipsecme-ikev2-cpext",55,28,"CP-56","PCG-29","2012-03-05","2012-06-14"]
[5456,530412,"      CT4 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C4","2011-09-16","2012-12-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#58 completed","23.008, 29.273, 29.274, new 29.139",53,27,null,null,"2011-08-29","2012-11-28"]
[5460,530113,"      TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#56 completed ",24.82,53,27,null,null,"2011-08-29","2012-06-14"]
[5463,530413,"      CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C4","2011-09-16","2012-03-02",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#55 completed","23.008, 29.273",53,27,null,null,"2011-08-29","2012-08-13"]
[5466,530014,"   Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility ","-",2,"Rel-11","C3,C1,C4","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2012-03-06"]
[5467,530114,"      Deleted - TR on Stage 3 BB III for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","-",3,"Rel-11","C1","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","new 24.820",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5470,530414,"      Deleted - CT4 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C4","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","23.008, 29.273",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5474,500026,"Single Radio Video Call Continuity for 3G-CS","vSRVCC",1,"Rel-11","S2,C1,C3,C4","2010-10-15","2012-06-15",1,"SP-100704","-","Samsung","xiaowan.ke@samsung.com","CP#56 completed. Provide Single Radio VIDEO Call Continuity from E-UTRAN to UTRAN-CS based on the agreed architecture alternative in TR 23.886","-",50,26,null,null,"2010-11-26","2012-06-18"]
[5477,520105,"      CT1 aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",3,"Rel-11","C1","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","CP#56 completed","24.008, 24.237, 24.301",52,27,null,null,"2011-05-18","2012-06-06"]
[5480,480038,"Network-provided Location information for IMS (NETLOC)","NWK-PL2IMS",1,"Rel-11","S2,S1,S5,C3,C4,C1","2010-06-10","2013-03-01",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging.","-",48,25,null,null,"2010-06-06","2012-11-13"]
[5484,490029,"   Charging for Network-provided Location information for IMS","NWK-PL2IMS_CH",2,"Rel-11","S5","2010-09-23","2012-09-12",1,"SP-110700","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#57 completed","Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299)",49,25,null,null,"2010-09-03","2012-09-05"]
[5487,550208,"      CT4 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C4","2012-03-02","2012-06-15",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.305, 29.328, 29.329",55,28,null,null,"2012-02-22","2015-03-03"]
[5490,500132,"   Stage 1 for Service Awareness and Privacy Policies","SAPP",2,"Rel-11","S1","2010-10-12","2010-12-15",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","For deep packet inspection (i.e. Traffic Detection Functionality) SA1 indicated that no new requirements are needed (see Objective of FS_PP SA1,SA2 Rel-10 Study on Policy solutions and enhancements UID_440047 TR 23.813) ","-",50,26,null,null,"2010-11-26","2010-12-02"]
[5491,500232,"   Stage 2 for Service Awareness and Privacy Policies","SAPP",2,"Rel-11","S2","2010-10-15","2011-09-21",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","SP#53 completed",23.202999999999999,50,26,null,null,"2010-11-26","2011-08-12"]
[5494,500133,"   Stage 2 for VPLMN Autonomous CSG Roaming","VCSG",2,"Rel-11","S2","2010-10-15","2011-12-14",1,"SP-100706","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#54 completed","23.002, 23.060, 23.401",50,26,null,null,"2010-11-26","2011-11-28"]
[5498,510248,"   Stage 2 for Data Identification in ANDSF","DIDA",2,"Rel-11","S2","2011-03-24","2012-03-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#55 completed",23.402000000000001,51,26,null,null,"2011-02-21","2012-02-20"]
[5501,510150,"   Stage 2 for LOcation-Based Selection of gaTEways foR WLAN","LOBSTER",2,"Rel-11","S2","2011-03-23","2011-12-14",1,"SP-110752","-","ZTE","zhu.chunhui@zte.com.cn","SP#54 completed",23.402000000000001,51,26,null,null,"2011-03-18","2012-03-04"]
[5504,540210,"      Deleted - CT1 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",3,"Rel-11","C1","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","CP#56 stopped",24.302,54,28,"CP-56","PCG-29","2011-11-23","2012-09-24"]
[5508,530301,"      CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.009, 24.008, 24.229, 24.237, 24.292, 24.301",53,27,null,null,"2011-08-25","2012-08-14"]
[5509,530401,"      CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","29.165, 29.292",53,27,null,null,"2011-08-25","2012-08-14"]
[5513,530801,"      Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-RAN_UTRA-Core",3,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-111334","RP-121553","Huawei","liwei.qiu@huawei.com","RP#58 completed","25.331, 25.401, 25.413",53,27,null,null,"2011-08-25","2012-11-27"]
[5516,530146,"   Stage 2 for S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",2,"Rel-11","S2","2011-09-22","2012-03-07",1,"SP-110642","-","ZTE","zhu.chunhui@zte.com.cn","SP#55 completed","23.002, 23.203, 23.402",53,27,null,null,"2011-08-12","2012-02-20"]
[5519,561010,"      Deleted - (IETF) CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C4-IETF","2012-04-23","2014-03-05",1,"CP-110802","-","Lionel Morand","-","CP#63 Draft removed from 3GPP documentation","draft-ietf-radext-ieee802ext",56,29,"CP-53","PCG-32","2012-04-20","2014-02-19"]
[5523,540129,"   Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",2,"Rel-11","S2","2011-11-28","2011-12-14",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","SP#54 completed","23.002, 23.228",54,28,null,null,"2011-10-25","2011-11-28"]
[5526,550104,"      CT1 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CT",3,"Rel-11","C1","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","24.229, 24.292, 24.237",55,28,null,null,"2012-02-20","2012-11-20"]
[5529,560127,"   Stage 2 for IMS Overload Control","IOC",2,"Rel-11","S2","2012-06-18","2012-09-12",1,"SP-120273","-","Orange, China Mobile","antoine.mouquet@orange-ftgroup.com, YU Qing","SP#57 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. ",23.228000000000002,56,29,null,null,"2012-05-11","2012-07-24"]
[5533,571001,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control)","RFC 7339",57,29,null,null,"2012-09-03","2015-03-10"]
[5536,520030,"Rel-11 Security small Enhancements","SEC11",1,"Rel-11","S3","2011-06-08","2012-09-12",1,"-","-","-","-","SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature","-",52,27,null,null,"2011-04-19","2012-08-16"]
[5537,520032,"Lawful Interception in the 3GPP Rel-11","LI11",1,"Rel-11","S3","2011-06-10","2012-06-20",1,"SP-110424","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com ","Stage 1/2/3. SP#56 completed","33.106, 33.107, 33.108",52,27,null,null,"2011-05-17","2012-06-08"]
[5540,560009,"   Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms)","EEA3_EIA3_UEConTest",2,"Rel-11","R5","2012-06-18","2012-09-07",1,"RP-120631","RP-120968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223)","36.523-1, 36.523-2, 36.523-3",56,29,null,null,"2012-06-04","2012-09-04"]
[5543,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[5547,540412,"      CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",3,"Rel-11","C1","2011-12-05","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",24.109000000000002,54,28,null,null,"2011-11-23","2012-08-14"]
[5550,530148,"   Enhancement to FEC for MBMS","EMM-EFEC",2,"Rel-11","S4","2011-09-21","2013-03-06",1,"SP-120182","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#59 completed","26.346, new 26.947",53,27,null,null,"2011-09-07","2013-02-16"]
[5553,560041,"Mobile 3D Video Coding","M3DV",1,"Rel-11","S4","2012-06-07","2012-09-12",1,"SP-120229","-","Orange","gilles.teniou@orange.com","SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905.","26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905",56,29,null,null,"2012-06-07","2012-08-20"]
[5557,510251,"   Rel-11 Performance Management","OAM11-PM",2,"Rel-11","S5","2011-03-23","2012-12-12",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2012-11-19"]
[5560,520034,"      CN performance measurements enhancement","OAM-ePM-CN",3,"Rel-11","S5","2011-06-08","2012-09-12",1,"SP-110275","-","China Mobile","Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com), Li Jian (lijian@chinamobile.com)","SP#57 completed","32.406, 32.407, 32.426",52,27,null,null,"2011-05-19","2012-08-31"]
[5561,530049,"      Management of Carrier Aggregation for LTE","OAM-CA",3,"Rel-11","S5","2011-09-21","2012-12-12",1,"SP-120776","-","Nokia Siemens Networks, Ericsson","yizhi.yao@nsn.com, per.elmdahl@ericsson.com","SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA)",32.424999999999997,53,27,null,null,"2011-08-27","2012-11-20"]
[5564,530051,"      LTE Self-Organizing Networks (SON) coordination management","OAM-SON-LTE_COORD",3,"Rel-11","S5","2011-09-21","2013-03-06",1,"SP-110637","-","Huawei, Nokia Siemens Networks","kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com","SP#59 completed","LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766",53,27,null,null,"2011-08-27","2013-02-16"]
[5567,470045,"   Add solutions for Rc - reference point within the Online Charging System (OCS)","CH-Rc",2,"Rel-11","S5","2010-03-25","2011-09-21",1,"SP-110129","-","Huawei","shan.mingjun@huawei.com","SP#53 completed. Stage 3 (Stage 1 in 22.115). Triggered by Rel-10 TR 32.825 SA5 Study on Rc Reference Point Functionalities and Message Flows (UID_410044)","32.296, 32.299",47,24,null,null,"2010-02-12","2011-08-26"]
[5570,510029,"Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",1,"Rel-11","S5,S1,C1","2010-10-27","2012-06-15",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115","-",51,26,null,null,"2011-02-22","2012-06-01"]
[5575,480036,"   Stage 1 for UDC Data Model","UDC_DM",2,"Rel-11","S1","2010-03-25","2011-09-21",1,"-","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","SP#53 completed under Rel-10 UDC",22.100999999999999,48,25,null,null,"2010-05-26","2011-09-19"]
[5579,520007,"Usability improvement of Inter-IMS Network to Network Interface (II-NNI) specification for inter-connection by means of Option Item list","NNI_OI",1,"Rel-11","C3","2011-06-07","2012-06-15",1,"CP-110533","-","NTT","arai.kenjiro@lab.ntt.co.jp","CP#56 completed. Stage 3 (No architectural change, specify the list of selectable items related to control plane signalling directly for the same architecture)",29.164999999999999,52,27,null,null,"2011-05-18","2012-06-01"]
[5582,581001,"   (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077)","eNR_EPC",2,"Rel-11","C4-IETF","2012-12-07","2013-12-06",1,"CP-120449","-","Lionel Morand","Lionel Morand","CP#62 completed","RFC 7077 (was draft-ietf-netext-update-notifications)",58,30,null,null,"2012-11-24","2013-11-28"]
[5585,520009,"Reference Location Information (Stage 3)","RLI",1,"Rel-11","C4,C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11)","-",52,27,null,null,"2011-05-18","2011-06-01"]
[5586,520109,"   CT4 part of Reference Location Information (Stage 3)","RLI",2,"Rel-11","C4","2011-06-03","2011-06-03",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#52 completed","23.008, 29.228, 29.328, 29.329",52,27,null,null,"2011-05-18","2011-06-02"]
[5589,520110,"   CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C1","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","23.218, 24.229, 24.930",52,27,null,null,"2011-05-18","2012-08-14"]
[5592,611002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135)","IMSProtoc5",2,"Rel-11","C1-IETF","2013-09-06","2014-06-13",1,"CP-110437","-","Roland Jesske","Roland Jesske","CP#64 completed","RFC 7135 (was draft-polk-local-emergency-rph-namespace)",61,31,null,null,"2013-08-23","2014-06-06"]
[5596,560008,"   Stage 2 for Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","S2","2012-06-18","2012-09-07",1,"-","-","-","-","SP#57 completed","23.060, 23.251",56,29,null,null,"2012-06-18","2012-08-31"]
[5599,550009,"      Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN","SIRIG",3,"Rel-11","C3","2012-03-02","2012-06-15",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","CP#56 stopped (SA2 decided NO CT3 impact)",29.212,55,28,"CP-56","PCG-29","2012-02-20","2012-04-20"]
[5603,530219,"   CS Fallback in EPS - Phase 2","SAES2-CSFB",2,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110639","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",53,27,null,null,"2011-09-08","2012-08-14"]
[5606,530220,"   Deleted - CT4 part of GCSMSC and GCR Redundancy for VGCS/VBS","RT_VGCS_Red",2,"Rel-11","C4","2011-09-19","2012-06-15",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#56 stopped (no CT4 impact)",29.001999999999999,53,27,"CP-56","PCG-29","2011-08-27","2012-09-25"]
[5609,540117,"   CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",2,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed","23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334",54,28,null,null,"2011-10-26","2012-08-13"]
[5610,540217,"   CT3 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",2,"Rel-11","C3","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed","29.162, 29.163, 29.292",54,28,null,null,"2011-10-26","2012-08-13"]
[5613,560006,"PS Additional Number (Stage 3)","PSAN",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120253","-","Deutsche Telekom","Yvette.koza@t-mobile.at","CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact)","23.003, 23.008, 29.002, 29.272, 29.230",56,29,null,null,"2012-04-23","2012-08-13"]
[5617,570210,"   CT4 part of IMS Operator Determined Call Barring","IODB",2,"Rel-11","C4","2012-09-07","2013-03-12",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","CP#58 completed","23.008 , 23.015 , 29.328 , 29.329 , 29.364",57,29,null,null,"2012-08-13","2012-11-17"]
[5620,570211,"   CT1 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C1","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",24.228999999999999,57,29,null,null,"2012-08-13","2012-11-19"]
[5623,540116,"   Deleted - TR Study on enhancement of protocols for SMS service over SGs","PROTOC_SMS_SGs",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped (abandonned new TR 29.818)","new 29.818",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[5627,510101,"   GERAN part of Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","G2","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID","44.018, 44.060, 45.002, 45.008, 48.008, 48.018",49,26,null,null,"2011-03-04","2013-05-17"]
[5630,510401,"      CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C1","2011-06-03","2012-12-07",1,"CP-120563","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#58 completed",24.007999999999999,49,26,null,null,"2011-03-04","2012-11-19"]
[5631,560004,"      CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C4","2012-06-13","2012-09-07",1,"CP-120563","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#57 completed",23.003,54,29,null,null,"2012-06-02","2012-11-19"]
[5635,540203,"   Perf. part: Medium range/local area requirements for multicarrier BTS","MRLA-Perf",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111782","-","Ericsson","Eric Nordström","Test spec. GP#56 completed. GP#52 approved WID",51.021000000000001,52,28,null,null,"2011-11-25","2012-11-23"]
[5638,500120,"   Core part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Core",2,"Rel-11","R4,R2,R3","2010-12-10","2012-03-02",1,"RP-111396","RP-120075","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[5642,530130,"   Core part: Further Self Optimizing Networks (SON) enhancements","SONenh2_LTE_UTRA-Core",2,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-120314","RP-121557","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#58 completed","25.331, 25.401, 25.410, 25.413, 25.423, 25.433, 36.300, 36.331, 36.413, 36.423",53,27,null,null,"2011-09-15","2012-11-27"]
[5645,590001,"   Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-12-06",1,"RP-130172","RP-131447","NTT DoCoMo","masahiro.tamaoki.eu@nttdocomo.com","RP#62 completed","34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2013-08-13"]
[5648,570001,"   GERAN part: Network Energy Saving for E-UTRAN","-",2,"Rel-11","GP","2012-08-27","2012-08-31",1,"GP-121178","-","Alcatel-Lucent","marguerite.woch@alcatel-lucent.com","GP#55 approved WID and completed. Stage 3. ChangES in CP-150RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature","48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)]",55,29,null,null,"2012-09-01","2012-09-01"]
[5652,540002,"   GERAN part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-GERAN",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111779","-","Ericsson","Eric Nordström","GP#56 completed. GP#52 approved WID","45.005, 51.021",52,28,null,null,"2011-11-25","2012-11-23"]
[5655,550215,"   Perf. part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Perf",2,"Rel-11","R4,G1","2012-03-08","2014-03-06",1,"RP-120857","RP-140064","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#63 completed","25.141, 25.142, 36.141, 37.141",55,28,null,null,"2012-02-23","2014-03-03"]
[5658,560014,"Further enhancements to H(e)NB mobility - Part 2","EHNB_enh2",1,"Rel-11","R3,R2","2012-06-19","2012-12-07",1,"RP-121712","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2)","UTRA, LTE",56,29,null,null,"2012-06-13","2012-11-27"]
[5659,560114,"   Core part: Further enhancements to H(e)NB mobility - Part 2","EHNB_enh2-Core",2,"Rel-11","R3,R2","2012-06-19","2012-12-07",1,"RP-121712","RP-121564","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#58 completed Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Updated WID RP-121147=>RP-121712","25.413, 25.467, 25.469, 25.471",56,29,null,null,"2012-06-13","2012-11-27"]
[5662,430211,"   Perf. part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Perf",2,"Rel-11","R4","2009-03-24","2014-06-13",1,"RP-131259","RP-140626","TruePosition","terri.brooks@trueposition.com","RP#64 completed. TS 36.112v100 for 1-step Approval","36.111, new 36.112",43,22,null,null,"2009-03-06","2014-06-11"]
[5666,510021,"Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-22","2014-12-15",1,"RP-120860","-","China Mobile","ShenXiaodong@chinamobile.com","-","LTE",51,26,null,null,"2011-03-14","2012-12-05"]
[5669,600001,"   Test part: Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE-UEConTest",2,"Rel-11","R5","2013-06-15","2014-12-15",1,"RP-130649","RP-141847","ZTE","Carolyn Taylor (carolyn.tayl@zte.com.cn)","¦Stat Rep: RP-141131->RP-141847","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",60,31,null,null,"2013-05-22","2015-01-12"]
[5672,510228,"   Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700-Perf",2,"Rel-11","R4","2011-03-29","2012-12-07",1,"RP-110435","RP-121605","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5676,510032,"LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB",1,"Rel-11","R1,R2,R4,R5","2011-03-23","2013-03-01",1,"RP-120602","-","NII Holdings","bill.shvodian@nii.com","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-06-09"]
[5679,560010,"   Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-UEConTest",2,"Rel-11","R5","2012-06-18","2013-03-01",1,"RP-120603","RP-130045","NII Holdings","bill.shvodian@nii.com","RP#59 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1",56,29,null,null,"2012-06-06","2013-02-27"]
[5680,520017,"LTE for 700 MHz Digital Dividend","LTE_APAC700",1,"Rel-11","R4,R2,R3,R5","2011-06-07","2013-06-14",1,"RP-110875","-","Ericsson","olav.queseth@ericsson.com","Stage 3. Asian Pacific American Caucus (APAC) Asia-Pacific Telecommunity (APT) Wireless Forum","LTE",52,27,null,null,"2011-06-02","2012-06-09"]
[5683,560011,"   Test part: LTE for 700 MHz Digital Dividend","LTE_APAC700-UEConTest",2,"Rel-11","R5","2012-06-18","2013-06-14",1,"RP-120600","RP-130467","Ericsson","fredrik.sundstrom@ericsson.com","RP#60 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1",56,29,null,null,"2012-06-06","2013-06-03"]
[5686,520219,"   Perf. part: Relays for LTE (part 2)","LTE_Relay2-Perf",2,"Rel-11","R4","2009-12-04","2013-06-14",1,"RP-110914","RP-130487","Ericsson","christian.hoymann@ericsson.com ","RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213","36.133, new 36.117 (E-UTRA Relay conformance testing)",46,24,null,null,"2009-11-30","2013-06-04"]
[5690,530032,"Coordinated Multi-Point Operation for LTE","COMP_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-09-19","2014-12-15",1,"RP-111365","-","Huawei, Samsung","Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com","Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE)","LTE",53,27,null,null,"2011-09-15","2011-09-15"]
[5693,530332,"   Core part: Coordinated Multi-Point Operation for LTE – Downlink","COMP_LTE_DL-Core",2,"Rel-11","R1,R2,R3,R4","2011-09-19","2012-12-07",1,"RP-111365","RP-121577","Samsung","Juho Lee (juho95.lee@samsung.com)","RP#58 completed","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423",53,27,null,null,"2011-09-15","2012-11-27"]
[5696,540025,"Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl",1,"Rel-11","R1,R2,R4,R5","2011-12-09","2014-09-12",1,"RP-120871","-","Alcatel-Lucent","sigen.ye@alcatel-lucent.com","Stage 3. RP#58 Core completed. Triggered by UID_510037 Rel-11 TR 36.871 Study on further Downlink MIMO enhancements for LTE-Advanced (FS_LTE_eDL_MIMO_enh)","LTE",54,28,null,null,"2011-12-07","2012-11-28"]
[5701,550112,"   Core part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-Core",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120362","RP-121581","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#58 completed. TR 36.837 v100 for Information and Approval","36.101, new 36.837",55,28,null,null,"2012-02-23","2012-12-05"]
[{"$f":"A5704+1","v":5704},550113,"   Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-Perf",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120382","RP-121582","Renesas Mobile","Timo Roman","RP#58 completed",36.100999999999999,55,28,null,null,"2012-02-23","2012-11-27"]
[5705,600002,"   Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-UEConTest",2,"Rel-11","R5","2013-06-18","2014-09-12",1,"RP-140491","RP-141602","Broadcom","jarkko.hellsten@kolumbus.fi","RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101","36.508, 36.521-1, 36.521-2, New 36.904",60,31,null,null,"2013-05-22","2014-09-07"]
[5708,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[5711,510130,"      Core part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Core",3,"Rel-11","R1,R2,R4,R3","2011-03-22","2013-08-27",1,"RP-121999","RP-130059","Nokia","lars.e.lindh@nokia.com","RP#59 completed. New TR 36.823 v100 for Information and Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new 36.823",51,26,null,null,"2011-03-14","2013-02-27"]
[5715,580258,"   Rel-11 inter-band Carrier Aggregation","-",2,"Rel-11","R4","2010-12-10","2012-12-07",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[5718,480223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-120830","RP-121023","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed","36.133, 36.141",48,25,null,null,"2010-06-04","2012-09-04"]
[5721,500217,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-121458","RP-121595","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",50,26,null,null,"2010-12-10","2012-11-26"]
[5725,510022,"      LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120877","-","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[5728,510023,"      LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","-","US Cellular","sebastian.thalanany@uscellular.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[5729,510123,"         Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","RP-121596","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[5732,510124,"         Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20-Core",4,"Rel-11","R4","2011-03-22","2012-09-07",1,"RP-120889","RP-121032","Huawei","Steven Chen","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[5735,510125,"         Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17-Core",4,"Rel-11","R4","2011-03-23","2012-09-07",1,"RP-110432","RP-121034","AT&T","marc.grant@att.com ","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[5739,510226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110433","RP-121589","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5742,510227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110434","RP-121599","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5746,530024,"      LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20",3,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-120888","-","Vodafone","Luis.Anaya@vodafone.com","Stage 3. RP#58 completed","LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5749,530026,"      LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120899","-","SK Telecom","Haesung Park","Stage 3. RP#57 completed","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[5752,530027,"      LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7",3,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-121152","-","Rogers Wireless","takwing.wan@rci.rogers.com","Stage 3. RP#58 completed","LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5753,530127,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-121152","RP-121590","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[5757,540220,"         Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Perf",4,"Rel-11","R4","2011-12-15","2012-12-07",1,"RP-120898","RP-121603","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed",36.133000000000003,54,28,null,null,"2011-12-07","2012-12-04"]
[5760,540221,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18-Perf",4,"Rel-11","R4","2011-12-13","2012-09-07",1,"RP-120892","RP-121053","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#57 completed","36.133, 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[5764,540023,"      LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21",3,"Rel-11","R4,R2","2011-12-09","2012-12-07",1,"RP-121173","-","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","Stage 3. RP#57 completed. Updated WID RP-111764=>RP-121173","LTE",54,28,null,null,"2011-12-07","2012-09-04"]
[5767,550018,"      LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8",3,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-121162","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Stage 3. RP#58 completed","LTE",55,28,null,null,"2012-02-23","2012-11-27"]
[5771,520015,"      LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38",3,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110862","-","Huawei","ronnie.zhang@huawei.com","Stage 3. RP#57 completed. WI only covers intra-band contiguous and not non-contiguous aspects","LTE",52,27,null,null,"2011-06-02","2012-09-04"]
[5774,520016,"      LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41",3,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","-","Clearwire","michael.hart@clearwire.com","RP#55 completed. WI only covers intra-band contiguous and not non-contiguous aspects.","LTE",52,27,null,null,"2011-06-02","2012-02-23"]
[5777,530028,"      LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-121193","-","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","Stage 3. RP#57 completed. Updated WID RP-111356=>RP-121193. WI only covers intra-band contiguous and not non-contiguous aspects","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[5778,530128,"         Core part: LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-121193","RP-121062","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","RP#57 completed. TR 36.831 v100 for Information & Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-07 [instead of 36.831] ",53,27,null,null,"2011-09-15","2012-09-04"]
[5781,450116,"   Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest-Core",2,"Rel-11","R4","2009-09-18","2011-12-09",1,"RP-111381","RP-111456","CATR","Guo Lin (guolin@emcite.com)","RP#54 completed","25.144, 25.914, 34.114",45,23,null,null,"2009-09-15","2011-11-29"]
[5785,500219,"   Perf. part: Eight carrier HSDPA","8C_HSDPA-Perf",2,"Rel-11","R4","2010-12-15","2012-12-07",1,"RP-101419","RP-120972","Ericsson","johan.hultell@ericsson.com","RP#57 completed","25.101, 25.104, 25.133, 25.141",50,26,null,null,"2010-12-10","2012-09-04"]
[5788,530038,"   Test part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc-UEConTest",2,"Rel-11","R5","2011-09-19","2012-03-02",1,"RP-111181","RP-120052","China Mobile","Ma Shuai (mashuai@chinamobile.com)","RP#55 completed","34.108, 34.122",53,27,null,null,"2011-09-06","2012-02-23"]
[5791,500222,"   Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop","HSPA_UL_TxDiv-CL-Perf",2,"Rel-11","R4","2010-12-14","2013-09-06",1,"RP-120367","RP-130477","Huawei","zongjie.wang@huawei.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",50,26,null,null,"2010-12-10","2013-08-30"]
[5795,510018,"Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config",1,"Rel-11","R4,R2","2011-03-22","2012-06-15",1,"RP-110308","-","Telus Communications","jorge.delrio@telus.com ","-","UTRA",51,26,null,null,"2011-03-14","2011-06-01"]
[5798,510019,"Non-contiguous 4C-HSDPA operation","NC_4C_HSDPA",1,"Rel-11","R4,R2,R3","2011-03-23","2013-03-01",1,"RP-110416","-","Ericsson","muhammad.kazmi@ericsson.com","-","UTRA",51,26,null,null,"2011-03-14","2013-02-27"]
[5801,510020,"Further Enhancements to CELL_FACH","Cell_FACH_enh",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-18","2015-03-13",1,"RP-111321","-","Qualcomm","Ravi Agarwal","-","UTRA",51,26,null,null,"2011-03-14","2011-09-16"]
[5802,510120,"   Core part: Further Enhancements to CELL_FACH","Cell_FACH_enh-Core",2,"Rel-11","R2,R1,R3,R4","2011-03-18","2012-12-07",1,"RP-111321","RP-121547","Qualcomm","Ravi Agarwal","RP#58 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.433",51,26,null,null,"2011-03-14","2012-11-27"]
[5805,530034,"HSDPA Multiflow Data Transmission","HSDPA_MFTX",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2015-03-13",1,"RP-111375","-","Nokia Siemens Networks","Alexander Sayenko","Stage 2,3","UTRA",53,27,null,null,"2011-09-15","2011-09-15"]
[5809,530035,"Four Branch MIMO transmission for HSDPA","4Tx_HSDPA",1,"Rel-11","R1,R2,R3,R4","2011-09-19","2013-12-06",1,"RP-111393","-","Ericsson","johan.hultell@ericsson.com","Stage 3","UTRA",53,27,null,null,"2011-09-15","2012-11-27"]
[5812,540009,"MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA",1,"Rel-11","R1,R2,R3,R4","2011-12-09","2013-09-06",1,"RP-121794","-","Nokia Siemens Networks","Karri Ranta-aho","Specified UE and BS performance requirements for uplink MIMO together with QPSK and 16QAM modulations for E-DCH/HSUPA. 64QAM is for future releases","UTRA",54,28,null,null,"2011-12-07","2013-02-27"]
[5815,540024,"HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC",1,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","-","Ericsson","muhammad.kazmi@ericsson.com","Stage 3","UTRA",54,28,null,null,"2011-12-07","2012-09-04"]
[5818,620015,"Split TTCN Test Models for IMS testing in TS 34.229-3","IMS-CCR_Test2",1,"Rel-11","R5","2013-12-09","2014-09-12",1,"RP-140440","RP-141155","Spirent","richard.catmur@spirent.com","SP#65 completed. TS 34.229-4 for Approval. Split out of old TS 34.229-3 a new TS 34.229-4","34.229-3, New 34.229-4",62,32,null,null,"2013-11-25","2014-09-09"]
[5823,450047,"Study on IMS based Peer-to-Peer Content Distribution Services","FS_IMS_P2P",1,"Rel-11","S1,S2","2009-09-11","2010-06-10",1,"SP-090491","-","China Mobile","Li Gang (ligangyf@chinamobile.com)","SP#48 completed. 3/3/15: start date corrected (was 05/09)",22.905999999999999,45,23,null,null,"2009-09-21","2015-03-03"]
[5826,490033,"Study on IMS Network-Independent Public User Identities","FS_INIPUI",1,"Rel-11","S1","2010-09-23","2011-06-08",1,"SP-100652","-","Vodafone","mona.mustapha@vodafone.com","SP#52 completed",22.893999999999998,49,25,null,null,"2010-09-21","2011-05-18"]
[5827,410041,"Study on IMS Evolution","FS_eIMS",1,"Rel-11","S2","2008-09-18","2011-12-14",1,"SP-100360","-","China Mobile","Li Gang (ligangyf@chinamobile.com), Yu Qing (yuqing@chinamobile.com)","SP#54 completed",23.812000000000001,41,21,null,null,"2008-09-15","2011-11-28"]
[5830,460030,"Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","FS_rSRVCC",1,"Rel-11","S2","2009-12-10","2011-12-14",1,"SP-090806","-","Orange","delphin.barankanira@orange-ftgroup.com","SP#54 completed. Study on \"reverse direction\" from UTRAN/GERAN to E-UTRAN/HSPA (Rel-8 SRVCC was in the other direction E-UTRAN/HSPA to GERAN/UTRAN)",23.885000000000002,46,24,null,null,"2009-12-06","2012-03-04"]
[5834,520036,"Study on Mobile 3D Video Coding","FS_M3DVC",1,"Rel-11","S4","2011-06-08","2012-06-20",1,"SP-110310","-","Orange","gilles.teniou@orange-ftgroup.com","SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS",26.905000000000001,52,27,null,null,"2011-05-26","2012-08-20"]
[5837,510045,"Study on OAM aspects of inter-RAT Energy Saving","FS_OAM_ES_iRAT",1,"Rel-11","S5","2011-03-23","2011-12-14",1,"SP-110138","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES)",32.834000000000003,51,26,null,null,"2011-03-09","2012-04-02"]
[5840,480003,"Study on Signal Precoding enhancements for EGPRS2 DL","FS_SPEED",1,"Rel-11","G1,G2","2010-09-03","2012-03-02",1,"GP-111281","-","Ericsson","marten.sundberg@ericsson.com","GP#53 completed (03/12). GP#46 approved WID. ","GERAN 45.860",46,25,null,null,"2010-05-27","2012-03-02"]
[5844,510037,"Study on further Downlink MIMO enhancements for LTE-Advanced","FS_LTE_eDL_MIMO_enh",1,"Rel-11","R1","2011-03-18","2011-12-09",1,"RP-111366","RP-111550","Alcatel-Lucent","federico.boccardi@alcatel-lucent.com","RP#54 completed","LTE 36.871",51,26,null,null,"2011-03-21","2011-12-08"]
[5847,530055,"Study on Enhanced performance requirement for LTE UE","FS_enh_perf_UE_LTE",1,"Rel-11","R4,R1","2011-09-19","2012-03-02",1,"RP-111378","RP-120167","NTT DoCoMo","Yuta Sagae","RP#55 completed. TR 36.829 v100 for Information + Approval","LTE 36.829",53,27,null,null,"2011-09-19","2012-02-27"]
[5848,550022,"Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology","FS_LTE_OTA",1,"Rel-11","R4","2012-03-05","2012-09-07",1,"RP-120412","RP-121083","CATR","Xudong An (anxudong@emcite.com)","RP#57 completed","LTE 25.914, New 37.902",55,28,null,null,"2012-02-23","2012-09-03"]
[5851,450015,"Study on RAN improvements for Machine-Type Communications","FS_NIMTC_RAN",1,"Rel-11","R2,R1,R3,R4","2009-09-18","2011-09-16",1,"RP-100330","RP-111052","Huawei","Jeff Gao (gaoyq@huawei.com)","RP#53 completed. TR 37.868v100 for Approval (No WID change: RAN overload only). Triggered by TR 22.868 Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) UID_7027 and Rel-10 NIMTC UID_410030","UTRA, LTE 37.868",45,23,null,null,"2009-09-15","2011-09-06"]
[5854,510038,"Study on Interference analysis between 800~900 MHz bands","FS_B800_B900_Interf_LTE",1,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-111752","RP-120586","LG Uplus","Koo Yeon Sang (yskoo@lguplus.co.kr)","RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 ","UTRA, LTE impac37.804",51,26,null,null,"2011-03-21","2012-06-06"]
[5858,530057,"Study on UE Over The Air (OTA) test method with Head and Hand Phantoms","FS_OTA_phantoms_UTRA",1,"Rel-11","R4,R5","2011-09-19","2012-09-07",1,"RP-120208","RP-121078","Nokia","petri.j.vasenkari@nokia.com","RP#57 completed","UTRA 25.914",53,27,null,null,"2011-09-19","2012-09-06"]
[5861,0,"--- RELEASE 10 ---","-",1,"Rel-10","CP,GP,RP,SP","2008-12-11","2011-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[5864,460029,"   Stage 2 on enhancements for Multimedia Priority Service","ePRIOR-St2",2,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","-",46,24,null,null,"2009-12-06","2015-01-22"]
[5868,460229,"   Deleted - TR 23.854 on Stage 2 on enhancements for Multimedia Priority Service","-",2,"Rel-10","S2","2009-12-10","2010-12-16",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","SP#49 TR 23.854 v100 for Information. SP#50 moved to Rel-11 SRVCC aspect of enhancements for Multimedia Priority Service UID_480135 (place holder for solution alternatives and agreed functions to be reflected in affected existing TS)","new 23.854",46,24,"SP-50","PCG-27","2009-12-06","2010-11-30"]
[5871,490208,"      CT3 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","29.212, 29.213, 29.214",49,25,null,null,"2010-09-01","2011-03-01"]
[5872,490308,"      CT1 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C1","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","24.008, 24.229, 24.301",49,25,null,null,"2010-09-01","2011-02-28"]
[5875,450028,"   Deleted - TR on Stage 2 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S2","2009-09-24","2010-12-16",1,"SP-100863","-","Samsung","erik.guttman@partner.samsung.com","SP#50 updated WID SP-090832=>SP-100863 (TR 23.888 not submitted for approval to conclude Rel-10 NIMTC as it will continue to serve as basis for Rel-11 SIMTC work item)","New 23.888",45,23,"SP-50","PCG-26","2009-09-21","2010-12-01"]
[5879,480005,"   CN part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",2,"Rel-10","C1,C4,C6","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","Stage 3",48,25,null,null,"2010-05-26","2011-06-01"]
[5883,510005,"      CT6 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C6","2011-03-18","2011-06-03",1,"-","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#52 completed",31.102,51,26,null,null,"2011-03-10","2011-05-18"]
[5886,490024,"   RAN mechanisms to avoid CN overload due to Machine-Type Communications","NIMTC-RAN_overload",2,"Rel-10","R2,R3","2010-09-17","2011-03-18",1,"RP-101026","RP-110063","Huawei","Jeff Gao (gaoyq@huawei.com)","RP#51 completed","UTRA, LTE 25.331, 25.413, 36.331, 36.413",49,25,null,null,"2010-09-20","2011-03-14"]
[5890,500004,"   CT aspects of Multi Access PDN Connectivity","MAPCON-St3",2,"Rel-10","C4,C1,C3","2010-11-15","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed","-",50,26,null,null,"2010-10-25","2010-12-09"]
[5893,500304,"      CT3 aspects of Multi Access PDN Connectivity","MAPCON-St3",3,"Rel-10","C3","2010-11-15","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed",29.215,50,26,null,null,"2010-10-25","2011-03-01"]
[{"$f":"A5896+1","v":5896},450029,"   Stage 2 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-100167","-","Huawei","Lee Valerius (lvalerius@huawei.com)","SP#49 completed","23.237, 23.292, new 23.831",45,23,null,null,"2009-09-21","2010-09-06"]
[5897,470001,"   Stage 3 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-110285","-","Huawei","georg.mayer@huawei.com ","CP#51 completed. WID updated CP-100334=>CP-110285","24.216, 24.229, 24.237, new (24.837, 24.337)",47,24,null,null,"2010-03-17","2011-03-17"]
[5900,450031,"   Stage 1 for CPM-SMS","CPM-SMS",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-090615","-","China Mobile","Qing Huang","SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C)",22.34,45,23,null,null,"2009-09-08","2010-03-09"]
[5903,450033,"Completion of Communications on Not Logged-in","CCNL",1,"Rel-10","S1,C1,C3","2009-09-24","2011-03-18",1,"SP-090493","-","Deutsche Telekom","Kurt Bischinger","CP#51 completed. SP#45 Stage 1 completed","-",45,23,null,null,"2009-09-08","2009-09-08"]
[5907,450035,"Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",1,"Rel-10","S2,S1,S3,S5,C4,C1","2009-09-24","2011-03-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","TSG#51 completed. Updated WID SP-100696=>SP-110131. SP#49 Stage 2 & Security completed. UID_400035 Enhanced Home NodeB/eNodeB (EHNB) formerly covered Local IP Access to Internet and Local access to Home Network from the Home NodeB/eNodeB","-",45,23,null,null,"2009-09-08","2010-12-13"]
[5910,450039,"   Security for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S3","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, Qualcomm","Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com)","SP#49 completed","33.102, 33.107, 33.108, 33.320, 33.401",45,23,null,null,"2009-09-08","2010-07-23"]
[5914,450338,"      Stage 2 for Local IP Access","LIPA",3,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#49 completed (has impacts to RAN)","23.060, 23.401",45,23,null,null,"2009-09-08","2010-09-06"]
[5917,480208,"         CT1 part of Stage 3 for Local IP Access","LIPA",4,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","24.008, 24.301",48,25,null,null,"2010-05-26","2011-02-28"]
[5920,480007,"      Stage 3 for SIPTO for macro networks","SIPTO",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","-",48,25,null,null,"2010-05-26","2011-03-08"]
[5921,480107,"         CT4 part of Stage 3 for SIPTO for macro networks","SIPTO",4,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","23.003, 23.008, 29.002, 29.272, 29.303",48,25,null,null,"2010-05-26","2011-03-08"]
[5924,450042,"   Stage 1 for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S1","2009-09-24","2009-12-10",1,"SP-100089","-","Qualcomm","David Williams (dwilliam@qualcomm.com)","SP#46 completed",22.277999999999999,45,23,null,null,"2009-09-08","2010-10-01"]
[5927,480009,"   Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",2,"Rel-10","C1,C3","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","Stage 3",48,25,null,null,"2010-05-26","2010-12-09"]
[5931,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[5934,490038,"   SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S4","2010-09-23","2011-03-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#51 completed",26.114000000000001,49,25,null,null,"2010-09-14","2011-02-18"]
[5938,490207,"      CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed","29.162, 29.163, 29.213, 29.235, 29.292",49,25,null,null,"2010-09-01","2011-05-17"]
[5940,450053,"Extended H(e)NB features","EHNBF",1,"Rel-10","S1,S2,S3","2008-12-11","2010-09-23",1,"SP-100407","-","NEC","joerg.swetina@neclab.eu","SP#49 completed. Adds extensions to Rel-9 functionality in UID_400035 Enhanced Home NodeB / eNodeB (EHNB)","UTRA, LTE",45,23,null,null,"2009-09-08","2010-07-23"]
[5945,460128,"   Stage 2 for Optimal Media Routing","OMR",2,"Rel-10","S2","2010-03-25","2010-03-25",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","SP#47 completed",23.228000000000002,46,24,null,null,"2009-12-06","2010-02-26"]
[5946,480010,"   Stage 3 for Optimal Media Routing","OMR",2,"Rel-10","C3,C1,C4","2010-06-04","2011-06-03",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134","-",48,25,null,null,"2010-05-26","2011-03-10"]
[5949,480310,"      Deleted - CT4 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134","-",48,25,"CP-51","PCG-26","2010-05-26","2011-03-10"]
[5953,470028,"   Stage 2 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","SP#49 completed",23.167000000000002,47,24,null,null,"2010-03-10","2010-09-06"]
[5956,480137,"   Stage 2 for S2b Mobility based on GTP","SMOG",2,"Rel-10","S2","2010-06-10","2010-09-23",1,"SP-100357","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#49 completed","23.002, 23.203, 23.402",48,25,null,null,"2010-06-06","2010-09-06"]
[5959,490209,"      CT3 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed","29.212, 29.213, 29.215",49,25,null,null,"2010-09-01","2011-03-18"]
[5963,500206,"   CT3 aspects of Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST-CT3",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100860","-","ZTE","zhou.xiaoyun@zte.com.cn","CP#51 completed","29.212, 29.213, 29.214, 29.215",50,26,null,null,"2010-11-26","2011-03-01"]
[5966,470229,"   LI for CRS (Customized Ringing Signal)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5969,470529,"   LI for MEDIASEC (IMS Media security)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5970,470629,"   LI for H(e)NB also with Local IP Access and Selected IP Traffic Offload (LIPA, SIPTO)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[5973,470033,"Optimization of IMS based PSS and MBMS User Service","OPT_IMS_PSS_MBMS_US",1,"Rel-10","S4","2010-03-25","2011-03-23",1,"SP-100031","-","Ericsson","markus.kampmann@ericsson.com","SP#51 completed. Work to enhance UID_430046 Rel-9 IMS_PSS_MBMS_US_EXT",26.236999999999998,47,24,null,null,"2010-03-10","2011-03-02"]
[5977,480040,"PSS and MBMS enhancements","MBS_Enh",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100305","-","Ericsson","Markus.Kampmann@ericsson.com","SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). ","26.234, 26.346",48,25,null,null,"2010-05-28","2011-03-02"]
[5980,460031,"Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM10",1,"Rel-10","S5,C4","2009-12-10","2011-09-21",1,"-","-","-","-","OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI",30.82,46,24,null,null,"2009-12-01","2011-08-26"]
[5983,470035,"      IRP Solution Set specification organisation improvements","OAM-IRP-SS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100774","-","Nokia Siemens Networks, Huawei","Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) ","SP#51 completed","32.153, new (32.111-6,32.126,32.176,32.306,32.316,32.326,32.336,32.346,32.356,32.366,32.376,32.386,32.396,32.416,32.446,32.506/26/36,32.606,32.616,32.626,32.636,32.646,32.656,32.666,32.676,32.696,32.716,32.726,32.736,32.746,32.756,32.766,32.776,32.786)",47,24,null,null,"2010-02-12","2011-03-09"]
[5987,510042,"      Inventory Management Network Resource Model enhancements","OAM-IM-NMR",3,"Rel-10","S5","2011-03-23","2011-06-08",1,"SP-110141","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items","32.690, 32.691, 32.692, 32.696",51,26,null,null,"2011-03-09","2011-05-16"]
[5990,460036,"      SON Self-healing management","LTE-SON-OAM_SH",3,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-110150","-","ZTE","zhu.weihong@zte.com.cn","SP#51 completed. WID updated SP-100776=>SP-110150. Work moved to Rel-10 after split of the Rel-9 UID_390007 SON self-optimization (removed Self-Healing handling)","32.522, 32.526, 32.762, 32.766, new 32.541",46,24,null,null,"2009-12-01","2011-03-22"]
[5993,470039,"   Rel-10 Performance Management","-",2,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"-","-","-","-","umbrella BB","-",47,24,null,null,"2010-02-12","2010-02-12"]
[5994,470040,"      Key Performance Indicators (KPIs) for IMS","OAM-PM-KPI_IMS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100083","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#51 completed","new 32.454",47,24,null,null,"2010-02-12","2011-03-09"]
[5997,470142,"         SA5 aspects of Management of UE based network performance measurements","-",4,"Rel-10","S5","2010-03-25","2011-06-08",1,"SP-100612","-","Huawei, Nokia Siemens Networks, Ericsson","Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com","SP#52 completed","32.421, 32.422, 32.423, 32.441, 32.442, 32.446",47,24,null,null,"2010-02-12","2011-05-16"]
[6001,440063,"   IWLAN mobility charging","eIWLAN_Mob",2,"Rel-10","S5","2009-06-04","2011-03-23",1,"SP-100090","-","Orange","Jean-Luc Garcia (jl.garcia@orange-ftgroup.com)","SP#51 completed. RAT differentiation for charging. Completes Rel-8 Feature IWLAN_Mob UID_370049 Mobility between 3GPP-WLAN Interworking and 3GPP Systems. Cooperation with CT1,CT3 on affected protocols","32.240, 32.252, 32.298, 32.299",44,23,null,null,"2009-05-19","2011-01-28"]
[6005,470003,"IMS Stage 3 IETF Protocol Alignment - phase 4","IMSProtoc4",1,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100099","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not","23.218, 24.229, 24.930",47,24,null,null,"2010-03-17","2011-02-28"]
[6008,480114,"   Further improvements of II-NNI Stage 3","II-NNI2",2,"Rel-10","C3","2010-06-04","2011-03-18",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","CP#51 completed",29.164999999999999,48,25,null,null,"2012-04-20","2012-04-20"]
[6012,490011,"AT Commands for USIM Application Toolkit (USAT)","AT_UICC",1,"Rel-10","C1","2010-09-17","2011-03-18",1,"CP-100646","-","ST-Ericsson","magnus.mk.karlsson@stericsson.com ","CP#51 completed",27.007000000000001,49,25,null,null,"2010-05-29","2011-02-14"]
[6015,500007,"Introduction of Smart Card Web Server launch functionality","SCWS_L",1,"Rel-10","C6","2010-12-10","2011-03-18",1,"CP-100883","-","Telecom Italia","davide.pratone@telecomitalia.it","CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server servicES in CP-150an easy and simple manner",31.102,50,26,null,null,"2010-11-28","2011-03-03"]
[6016,500008,"USAT using AT Commands","USAT_AT",1,"Rel-10","C6","2010-12-10","2011-03-18",1,"CP-100884","-","Giesecke & Devrient","enric.fort@gi-de.com ","CP#51 completed. Stage 3 based on SA1 22.038CR#37r1 (Make USAT proactive capability reqs applicable to ME as a whole without regard to any particular configuration¦e.g. a modem connected to an external display)","Stage 3 31.102, 31.111",50,26,null,null,"2010-11-28","2011-03-03"]
[6019,500210,"   CT4 part of Stage 3 for SRVCC enhancements","eSRVCC",2,"Rel-10","C4","2010-12-10","2011-03-18",1,"CP-100881","-","China Mobile","Jiang Y (jiangyi@chinamobile.com)","CP#51 completed","23.003, 23.008, 29.002, 29.230, 29.272, 29.305, 29.328, 29.329",50,26,null,null,"2010-10-25","2011-02-28"]
[6022,500111,"   CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3)","aSRVCC",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-110145","-","ZTE","li.shitao@zte.com.cn","CP#52 completed","24.008, 24.237",50,26,null,null,"2011-03-16","2011-05-23"]
[6026,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212, 29.213, 29.214, 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[6029,510008,"EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated","EPC_NR",1,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110092","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014","Stage 2/3: 23.007, 29.274",51,26,null,null,"2011-02-22","2011-03-18"]
[6032,510010,"UICC access to IMS Specification","IMS-UICC-S",1,"Rel-10","C6,C1","2011-03-16","2011-06-03",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC","-",51,26,null,null,"2011-03-03","2011-05-18"]
[6036,440021,"CN aspects of Local Call Local Switch","LCLS-CN",1,"Rel-10","C4","2009-05-29","2011-03-18",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","GERAN Stage 2/3",44,23,null,null,"2009-05-13","2010-12-09"]
[6039,440023,"   Deleted - CT3 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C3","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT3 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[6040,440024,"   Deleted - CT1 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C1","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT1 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[6043,480102,"   CT1 part for TIGHTER","TIGHTER",2,"Rel-10","C1","2010-09-03","2011-06-03",1,"GP-101083","-","Renesas Mobile","marko.niemi@renesasmobile.com","CP#52 completed",24.007999999999999,46,25,null,null,"2010-05-27","2011-05-23"]
[6046,490001,"Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",1,"Rel-10","G2,S2,C1","2010-05-21","2011-03-04",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method","GERAN",47,25,null,null,"2010-05-27","2011-03-04"]
[6050,490002,"Enhancements of Iur-g interface","eIurg",1,"Rel-10","G2,R3","2010-09-03","2011-06-03",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#47 approved WID","GERAN,UTRA",47,25,null,null,"2010-09-05","2011-05-26"]
[6053,380077,"1.28 Mcps TDD Repeater","RANimp-Repeaters1.28TDD",1,"Rel-10","R4","2007-12-04","2010-03-19",1,"RP-071003","RP-100039","RITT","qinyan@chinattl.com","RP#47 completed","UTRA 25.113, New 25.116, 25.153 (testing)",38,21,null,null,"2007-12-17","2010-03-09"]
[6057,460214,"   Perf. part: 1.28Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF-Perf",2,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","RP-101081","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. TR 25.968 v100 for Approval","25.142, new 25.968",46,24,null,null,"2009-11-30","2010-12-03"]
[6060,470212,"   Perf. part: MU-MIMO for 1.28Mcps TDD","MUMIMO_LCR_TDD-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-100347","RP-110520","CATT","Sanjun Feng (fengsanjun@datangmobile.cn)","RP#52 completed","25.102, 25.105, 25.142",47,24,null,null,"2010-03-19","2011-05-24"]
[6063,480018,"   AGNSS test case development for UMTS","AGNSSPerf_UTRAN",2,"Rel-10","R5","2010-06-04","2011-09-16",1,"RP-101405","RP-110979","Thales","Michel.monnerat@thalesaleniaspace.com","RP#53 completed","34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.37.571-5, new 34.172",48,25,null,null,"2010-06-01","2011-09-06"]
[6066,460015,"Four carrier HSDPA","4C_HSDPA",1,"Rel-10","R1,R2,R3,R4,R5","2009-12-04","2013-09-06",1,"RP-100991","-","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#53 completed","UTRA",46,24,null,null,"2009-11-30","2011-09-12"]
[6068,460215,"   Perf. part: Four carrier HSDPA","4C_HSDPA-Perf",2,"Rel-10","R4","2009-12-04","2011-09-16",1,"RP-100991","RP-110986","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#53 completed","25.101, 25.104, 25.133, 25.141",46,24,null,null,"2009-11-30","2011-09-12"]
[6071,470113,"   Core part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD-Core",2,"Rel-10","R4","2010-03-19","2010-06-04",1,"RP-100168","RP-100454","TD Tech","dafei.wang@td-tech.com","RP#48 completed",25.102,47,24,null,null,"2010-03-19","2010-06-01"]
[6075,530039,"   Test part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-UEConTest",2,"Rel-10","R5","2011-09-19","2012-12-07",1,"RP-120599","RP-121529","Ericsson","leif.mattisson@ericsson.com","RP#58 completed","34.108, 34.123-1, 34.123-2, 34.123-3",53,27,null,null,"2011-09-09","2012-11-28"]
[6078,480221,"   Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Perf",2,"Rel-10","R4,R2","2010-06-04","2010-09-17",1,"RP-100657","RP-100759","AT&T","Vince Spatafora (vs5785@att.com)","RP#49 stopped (Reason: no need for Performance work)","25.101, 25.104, 25.141, 25.317",48,25,"RP-49","PCG-25","2010-06-03","2010-09-09"]
[6082,510017,"   Test part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-UEConTest",2,"Rel-10","R5","2011-03-18","2012-03-02",1,"RP-110244","RP-120042","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#55 completed","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",51,26,null,null,"2011-03-10","2012-02-23"]
[6085,460107,"   Core part: Carrier Aggregation for LTE","LTE_CA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-06-03",1,"RP-100661","RP-110535","Nokia","lars.e.lindh@nokia.com","RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, 37.104, new RAN4 (36.807, 36.808)",46,24,null,null,"2009-11-30","2012-06-07"]
[{"$f":"A6088+1","v":6088},460008,"Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO",1,"Rel-10","R1,R2,R4,R5","2009-12-04","2013-06-14",1,"RP-100196","-","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","-","LTE",46,24,null,null,"2009-11-30","2010-03-19"]
[6089,460108,"   Core part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-03-18",1,"RP-100196","RP-110067","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 36.807",46,24,null,null,"2009-11-30","2012-06-07"]
[6092,460009,"Uplink Multiple Antenna Transmission for LTE","LTE_UL_MIMO",1,"Rel-10","R1,R2,R4,R5","2000-01-03","2013-03-01",1,"RP-100959","-","Huawei","Mattias.wennstrom@huawei.com","-","LTE",46,24,null,null,"2009-11-30","2011-09-12"]
[6095,540007,"   Test part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-UEConTest",2,"Rel-10","R5","2011-12-02","2013-03-01",1,"RP-111614","RP-130038","Huawei","Zhang Xin (suzanna.zhang@huawei.com)","RP#59 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2013-02-27"]
[6099,520020,"   Stage 2 for Relays for LTE","LTE_Relay",2,"Rel-10","S2","2011-06-06","2011-06-08",1,"-","-","Vodafone","chris.pudney@vodafone.com","SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview",23.401,52,27,null,null,"2011-06-06","2011-06-06"]
[6102,500138,"      Security for LTE Relay Nodes (Stage 2)","LTE_Relay-Sec",3,"Rel-10","S3","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","SP#51 completed (impacting Stage 3 in CT and RAN)","33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413",50,26,null,null,"2010-11-25","2011-02-14"]
[6106,470107,"   Core part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-Core",2,"Rel-10","R1,R2,R3,R4","2010-03-19","2011-06-03",1,"RP-100383","RP-110543","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#52 completed","36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423",47,24,null,null,"2010-03-19","2011-05-27"]
[6109,470008,"LTE TDD in 2600MHz for US","LTE_TDD_2600_US",1,"Rel-10","R4,R2,R3,R5","2010-03-19","2010-12-10",1,"RP-101003","-","Clearwire","michael.hart@clearwire.com","RP#50 Testing completed. RP#49 Core+Perf completed","LTE",47,24,null,null,"2010-03-19","2010-12-03"]
[6112,480019,"   UE conformance test part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-UEConTest",2,"Rel-10","R5","2010-06-04","2010-12-10",1,"RP-100615","RP-101071","Clearwire","michael.hart@clearwire.com","RP#50 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",48,25,null,null,"2010-06-01","2010-12-03"]
[6113,470009,"Adding 2 GHz band LTE FDD (Band 23) for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America","S_Band_LTE_ATC_MSS",1,"Rel-10","R2,R4,R5","2010-03-19","2011-12-09",1,"RP-110775","-","DBSD","Mariam.Sorond@ico.com","RP#52 completed. Updated WID RP-101401=>RP-110775 (changed in Title \"LTE\" to \"LTE FDD (Band 23)\"","LTE",47,24,null,null,"2010-03-19","2011-06-01"]
[6116,520012,"   Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-06-07","2011-12-09",1,"RP-110623","RP-111444","DBSD","Mariam.Sorond@ico.com","RP#54 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",52,27,null,null,"2011-05-23","2011-11-29"]
[6120,510015,"   Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-03-18","2011-09-16",1,"RP-110777","RP-110980","LightSquared","masoud.olfat@lightsquared.com","RP#53 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2",51,26,null,null,"2011-03-10","2011-09-06"]
[6123,480027,"Further enhancements to MBMS for LTE","MBMS_LTE_enh",1,"Rel-10","R2,R3,R5","2010-06-04","2012-03-02",1,"RP-101244","-","Huawei","Ms Zhao Junhui (zhaojh@huawei.com)","RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives","LTE",48,25,null,null,"2010-06-04","2011-03-14"]
[6127,380073,"   Core part: UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",2,"Rel-10","R4,R2,R3","2007-11-30","2011-09-16",1,"RP-091380","RP-110987","Ericsson","johan.skold@ericsson.com","RP#53 completed. TR 37.801v200 for Approval","25.101, 25.104, 25.113, 25.133, 25.141, 25.307, 25.307, 25.331, 25.461, 25.463, 34.124, 36.101, 36.104, 36.113, 36.141, 36.331, new 37.801",38,21,null,null,"2007-12-17","2011-09-09"]
[6131,460103,"   Core part: Minimization of Drive Tests for E-UTRAN and UTRAN","MDT_UMTSLTE-Core",2,"Rel-10","R2,R4,R3","2009-12-04","2011-06-03",1,"RP-100360","RP-110528","Nokia Siemens Networks","malgorzata.tomala@nsn.com","RP#52 completed","25.133, 25.215, 25.304, 25.331, 25.423, 36.133, 36.214, 36.300, 36.304, 36.331, 36.413, 36.423, new 37.320 (Stage 2)",46,24,null,null,"2009-11-30","2011-05-24"]
[6134,470105,"   Core part: HNB and HeNB Mobility Enhancements","HNB_HENB_mob_enh-Core",2,"Rel-10","R3,R2","2010-03-19","2011-03-18",1,"RP-110183","RP-110058","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#51 completed","25.413, 25.467, 25.469, 36.300, 36.413, 36.423, new 25.471",47,24,null,null,"2010-03-19","2011-03-11"]
[6137,480124,"   Core part: Expanded 1900 MHz Band for UTRA and LTE","E1900-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100676","RP-110529","Sprint","nick.j.baustert@sprint.com","RP#52 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new 36.818",48,25,null,null,"2010-06-04","2011-05-24"]
[6138,480224,"   Perf. part: Expanded 1900 MHz Band for UTRA and LTE","E1900-Perf",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100676","RP-110530","Sprint","nick.j.baustert@sprint.com","RP#52 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new 36.818",48,25,null,null,"2010-06-04","2011-05-24"]
[6141,480125,"   Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-Core",2,"Rel-10","R4","2010-06-04","2011-06-03",1,"RP-101402","RP-110531","Ericsson","johan.skold@ericsson.com","RP#52 completed","25.104, 36.104, 37.104, new 37.802",48,25,null,null,"2010-06-04","2011-06-01"]
[6145,540001,"      GERAN BS Test part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-GERAN",3,"Rel-10","G1","2011-09-02","2011-11-25",1,"GP-101618","-","Ericsson","mats.y.samuelsson@ericsson.com ","GP#52 completed",51.021000000000001,52,28,null,null,"2011-11-25","2011-11-25"]
[6148,531001,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (RFC6275)","TEI10_IETF1",1,"Rel-10","C1-IETF","2009-06-04","2011-07-29",1,"-","-","-","-","SP#53/IETF#81: RFC 6275 completed","RFC 6275 (was draft-ietf-mext-rfc3775bis)",53,27,null,null,"2011-07-29","2011-08-31"]
[6151,370030,"   Deleted - Stage 1 for RED","RED",2,"Rel-10","S1","2007-03-12","2007-03-15",1,"SP-070133","-","NTT DoCoMo","takakurat@s1.nttdocomo.co.jp","SP#35 completed. SP#46 work stopped/abandoned","22.101 CR#0207",37,19,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6155,380262,"   Deleted - CT6 issues for N3GtoNSP","N3GtoNSP",2,"Rel-10","C6","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",36.299999999999997,38,21,"CP-45","PCG-23","2007-12-13","2009-09-21"]
[6158,430017,"Deleted - UTRAN 2 ms TTI uplink range improvement","RANimp-2mTTI_ULimp",1,"Rel-10","R1,R2,R3,R4","2009-03-06","2010-03-19",1,"RP-090333","RP-100040","Nokia Siemens Networks","Karri Ranta-aho (karri.ranta-aho@nsn.com)","RP#47 work stopped/abandoned (no CR approved). Cell sets the TTI (Transmission Time Interval) to 2 ms ","25.133, 25.212, 25.214, 25.321, 25.331",43,22,"RP-47","PCG-24","2009-10-07","2010-03-16"]
[6159,440043,"Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9","eEHNB",1,"Rel-10","S2","2008-12-11","2010-03-25",1,"-","-","Alcatel-Lucent","Nicolas Drevon","SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB)","-",44,23,"SP-47","PCG-24","2007-12-13","2009-06-01"]
[6162,460210,"   Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-UEConTest",2,"Rel-10","R5","2009-12-04","2011-06-03",1,"RP-091432","RP-110504","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions)","36.521-1",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[6165,470006,"Deleted - Enhanced Interference Management for Home NodeBs","HNB_IM",1,"Rel-10","R3","2010-03-19","2010-09-17",1,"RP-100392","RP-100754","Qualcomm","Andrei Radulescu (aradules@qualcomm.com)","RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs","UTRA",47,24,"RP-49","PCG-25","2010-03-19","2010-09-09"]
[6169,370047,"   Use cases definition and service and system requirements","FS_EV_EPS-S1",2,"Rel-10","S1","2007-09-03","2008-12-11",1,"SP-070698","-","France Telecom","philippe.lottin@orange.com","SP#47 completed. TR 22.813-100 for Approval",22.812999999999999,37,19,null,null,"2007-10-04","2010-08-31"]
[6172,410039,"Study on Personal Broadcast Service","FS_PBS",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080504","-","ETRI","Jaihyung Cho","SP#47 completed",22.946999999999999,41,21,null,null,"2008-09-15","2010-03-09"]
[6175,370050,"Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media","FS_IMS_LBO_ORM",1,"Rel-10","S2","2007-10-01","2009-12-10",1,"SP-080556","-","Telecom Italia, BT","mario.madella@telecomitalia.it, victor.kueh@bt.com","SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011",23.893999999999998,37,19,null,null,"2007-10-02","2009-11-25"]
[6179,470049,"Study on S2b Mobility based on GTP","FS_SMOG",1,"Rel-10","S2","2010-03-25","2010-06-10",1,"SP-100169","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101",23.834,47,24,null,null,"2010-03-10","2010-06-07"]
[6182,410044,"Study on Rc Reference Point Functionalities and Message Flows","FS_OAM_Rc",1,"Rel-10","S5","2008-09-18","2010-03-25",1,"SP-080464","-","Huawei","shan.mingjun@huawei.com","SP#47 completed",32.825000000000003,41,21,null,null,"2008-09-15","2010-03-23"]
[6183,430044,"Study on Telecommunication Management; Energy Savings Management","FS_OAM_ESM",1,"Rel-10","S5","2009-03-12","2010-03-25",1,"SP-090048","-","Orange, Vodafone","Jean-Michel Cornilly (Orange)","SP#47 completed. Study result might impact Feature UID_420011 Self Organising Networks (SON)",32.826000000000001,43,22,null,null,"2009-02-23","2010-03-08"]
[6188,480046,"Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM","FS_3G_TMF_PM",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100291","-","Alcatel-Lucent","Padma.Sudarsan@alcatel-lucent.com ","SP#51 completed",32.831000000000003,48,25,null,null,"2010-05-26","2011-03-22"]
[6190,480016,"Study on User Data Convergence (UDC) evolution ","FS_UDCe",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100296","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model",23.844999999999999,48,25,null,null,"2010-05-26","2011-02-28"]
[6194,470015,"Study on Potential solutions for energy saving for E-UTRAN","FS_Energy_LTE",1,"Rel-10","R3,R2","2010-02-02","2011-06-03",1,"RP-100674","RP-110597","China Mobile","Yang Ning (yangning@chinamobile.com)","RP#52 completed","LTE 36.927",47,24,null,null,"2010-03-19","2011-06-02"]
[6197,410042,"Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services","FS_eIMS_IBCF",1,"Rel-10","S2","2008-09-18","2010-12-15",1,"SP-090809","-","Starent Networks","Rajat Ghai (rghai@starentnetworks.com)","SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS)",23.847999999999999,41,21,"SP-50","PCG-26","2008-09-15","2010-12-13"]
[6200,0,"--- RELEASE 9 ---","-",1,"Rel-9","CP,GP,RP,SP","2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[6204,420035,"   Security aspects of Enhanced Home NodeB / eNodeB","EHNB-Sec",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080879","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#46 completed","New 33.320",42,22,null,null,"2008-12-09","2009-12-07"]
[6207,420036,"   3G HNB Gateway and LTE HeNB Gateway OAM&P","HNB-OAM_GW",2,"Rel-9","S5","2008-12-11","2010-03-25",1,"SP-100087","-","China Mobile","GangChen (chengang@chinamobile.com)","SP#47 completed","32.632, 32.633, 32.635, New (32.771, 32.772, 32.773, 32.775, 32.781, 32.782, 32.783, 32.785)",42,22,null,null,"2008-12-03","2010-03-22"]
[6208,430012,"   3G HNB and LTE HeNB OAM&P Type 1 Interface","HNB_eHNB-OAM_Type1",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090208","-","Huawei","Zou Lan (zlan@huawei.com)","SP#47 completed","32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594)",43,22,null,null,"2009-03-09","2010-03-08"]
[6211,430005,"   LTE TDD Home eNodeB RF Requirements","HeNB-RF_TDD",2,"Rel-9","R4","2009-03-06","2010-03-19",1,"RP-091386","RP-100036","China Mobile","Nan Li (linan@chinamobile.com)","RP#47 completed","36.104, 36.141, 36.300, 36.331, 36.413, New 36.922",43,22,null,null,"2009-03-03","2010-03-16"]
[6214,490020,"   Conformance Test Aspects – Home NB enhancements for FDD","EHNB-UTRA_FDD_UEConTest",2,"Rel-9","R5","2010-09-17","2011-12-09",1,"RP-111315","RP-111679","Huawei","trica_li@huawei.com","UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367)","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-09","2011-12-07"]
[6218,370126,"   Stage 1 for VAS4SMS","VAS4SMS",2,"Rel-9","S1","2007-09-10","2008-03-12",1,"SP-070572","-","China Mobile","Wu Bin (wubin@chinamobile.com)","SP#39 completed. SP#43 Feature moved to Rel-9","new 22.142",37,19,null,null,"2007-10-02","2009-03-04"]
[6221,370027,"Definition of End-User Identity","EUI",1,"Rel-9","S1","2007-09-03","2008-12-11",1,"SP-090380","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905)","-",37,19,null,null,"2007-10-02","2010-08-05"]
[6225,440041,"   Stage 3 for IMS Customized Ringing Signal (CRS) Service","CRS",2,"Rel-9","C1","2009-05-29","2009-12-03",1,"CP-090444","-","China Mobile","wangzhao","CP#48 completed","24.173, new 24.183",44,23,null,null,"2009-05-13","2010-05-28"]
[6228,440029,"   Stage 3 for Public Warning System","PWS-St3",2,"Rel-9","C1,C4","2009-05-29","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","RP#46 completed","-",44,23,null,null,"2009-05-13","2009-12-03"]
[6231,440005,"   Public Warning System (PWS) – RAN aspects","PWS-RAN",2,"Rel-9","R2,R3","2009-05-30","2009-12-04",1,"RP-090649","RP-091052","AT&T","don.zelmer@att.com","RP#46 completed","LTE 36.300, 36.302, 36.331, 36.413",44,23,null,null,"2009-05-20","2009-12-03"]
[6232,540005,"   Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE","PWS-RAN_UEConTest",2,"Rel-9","R5","2011-12-02","2012-12-07",1,"RP-111564","RP-121525","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#58 completed","36.508, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2012-12-04"]
[6235,430002,"   Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-06","2009-12-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#46 completed",23.259,43,22,null,null,"2009-03-05","2009-11-16"]
[6238,400044,"   Stage 1 for eMMTel","eMMTel",2,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080503","-","France Telecom","philippe.lottin@orange.com","SP#42 completed",22.172999999999998,40,21,null,null,"2007-12-13","2008-12-05"]
[6242,400034,"User Data Convergence (UDC)","UDC",1,"Rel-9","S1,S5,C4","2008-06-05","2010-06-10",1,"SP-080448","-","Nokia Siemens Networks","juergen.merkel@nsn.com ","SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808","-",40,21,null,null,"2007-12-13","2010-08-31"]
[6245,430003,"      User Data Convergence (UDC) Technical Realization (Stage 2)","UDC-CN",3,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","CP#47 completed","new 23.335",43,22,null,null,"2009-03-04","2010-03-09"]
[6249,440061,"      UDC – Common Baseline Information Model","UDC-MMAN-CBIM",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090310","-","China Mobile, Ericsson","Lan Si Zhong, Miguel Garcia","SP#47 completed","32.172, new 32.182 ",44,23,null,null,"2009-05-18","2010-03-08"]
[6253,410034,"      Stage 2 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",3,"Rel-9","S2","2008-09-18","2009-06-04",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","SP#57 Removal of the MSC server assisted mid-call feature from Rel-9 by 23.237CR#0433 (CT1 proposed moving this feature to Rel-10). SP#44 completed. TR 23.838 for Approval","23.237, 23.292, 23.216, new 23.838",41,21,null,null,"2008-09-15","2012-07-20"]
[6256,410035,"      Stage 2 for IMS Centralized Services","IMS_SCC-ICS",3,"Rel-9","S2","2008-09-18","2009-06-04",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","SP#44 completed. TR 23.883 for Information + Approval","23.292, new 23.883",41,21,null,null,"2008-09-15","2009-06-02"]
[6257,440033,"      Stage 3 for Enhancements to IMS Centralized Services","IMS_SCC-ICS",3,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090883","-","Nokia Siemens Networks","Peter.Leis@nsn.com","CP#47 completed","24.292, 24.604, 24.607, 24.608, 24.611, 24.623",44,23,null,null,"2009-05-13","2010-03-02"]
[6260,420021,"   Stage 1 for Service Specific Access Control in EPS","SSAC",2,"Rel-9","S1","2008-12-11","2008-12-11",1,"SP-080882","-","NTT DoCoMo","Frederic Thepot (thepot@docomolab-euro.com)","SP#42 completed. If UE supports E-UTRA and IMS, SSAC is a mandatory Rel-9 function (during congestion in emergency case earthquake/tsunami improves mobile communications).","22.011 CR0136",42,22,null,null,"2008-12-05","2010-02-09"]
[6263,380064,"Support for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",1,"Rel-9","S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF","2000-01-03","2014-06-13",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","RP#56 completed testing. CP#47 completed. SP#48 completed","GERAN, LTE",38,21,null,null,"2007-10-02","2012-06-05"]
[6267,440035,"   Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",2,"Rel-9","C1,C3,C4,R5","2009-05-29","2012-06-15",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","RP#56 completed testing. CP#47 completed","GERAN, LTE",44,23,null,null,"2009-05-13","2012-06-05"]
[6270,440037,"      CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC3",3,"Rel-9","C3","2009-05-29","2009-09-18",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#45 completed","29.212, 29.213, 29.214, 29.215",44,23,null,null,"2009-05-13","2009-09-09"]
[6274,410038,"   Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",2,"Rel-9","S2,C1,C4,C3,IETF","2008-09-18","2014-06-13",1,"SP-090099","-","China Mobile","Yu Qing (Yuqing@chinamobile.com)","CP#56 added IETF dependency","-",41,21,null,null,"2008-09-15","2009-03-05"]
[6277,440027,"         CT1 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","24.229, 24.237",44,23,null,null,"2009-05-13","2009-12-02"]
[{"$f":"A6280+1","v":6280},561003,"         (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254)","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C3-IETF","2012-04-20","2014-06-13",1,"CP-090882","-","Andrew Allen","Andrew Allen","CP#64 completed","RFC 7254 (was draft-montemurro-gsma-imei-urn)",56,29,null,null,"2012-04-20","2014-06-06"]
[6281,430006,"LCS for LTE and EPS","LCS_LTE_EPS",1,"Rel-9","S2,C1,C4,R2,R1,R3,R4,R5","2008-06-05","2012-03-02",1,"-","-","-","-","-","LTE",43,22,null,null,"2009-02-18","2010-03-16"]
[6284,440020,"      CT4 aspects of Control Plane LCS in the EPC","LCS_EPS-CPS",3,"Rel-9","C4","2009-05-29","2010-03-19",1,"CP-090811","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","CP#47 completed (IANA registrations outstanding). Stage 3 SLs and SLg interfaces & transport of positioning messages between E-SMLC and MME in the scope of UID_420006 (Positioning Support for LTE)","24.080, 29.002, 29.272, 29.230, new 24.171, 29.171, 29.172, 29.173",44,23,null,null,"2009-05-13","2010-03-09"]
[6288,400039,"MBMS support in EPS","MBMS_EPS",1,"Rel-9","S2,S3,S5,C3,C4,R2,R3,R4,R5","2008-06-05","2011-12-09",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","RP#47 completed. SP#46, CP#46 completed","LTE",40,21,null,null,"2007-12-13","2010-03-16"]
[6291,430033,"   MBMS Charging in EPS ","MBMS_EPS",2,"Rel-9","S5","2009-03-06","2009-12-10",1,"SP-090052","-","ZTE","guo.wenjie1@zte.com.cn","SP#46 completed","32.273, 32.251, 32.298, 32.299",43,22,null,null,"2009-02-23","2009-12-01"]
[6294,430007,"   MBMS support in LTE","MBMS_LTE",2,"Rel-9","R2,R3,R4","2009-03-06","2010-03-19",1,"RP-091457","RP-100033","Huawei","arnaud.meylan@huawei.com","RP#47 completed","25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445",43,22,null,null,"2009-03-10","2010-03-16"]
[6298,450006,"   CT1 aspects of Access Network Discovery and Selection Function enhancements","eANDSF",2,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090742","-","Panasonic","benjamin.limck@sg.panasonic.com","CP#47 completed","24.302, 24.312",45,23,null,null,"2009-09-08","2010-03-02"]
[6301,450007,"   CT4 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",2,"Rel-9","C4","2009-09-18","2009-12-04",1,"CP-090515","-","Samsung","Surjyakanta Mohapatra (surjya.kanta@samsung.com)","CP#46 completed","29.275, 23.008, 29.282",45,23,null,null,"2009-03-05","2009-11-16"]
[6304,450050,"   SA2 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#45 completed (CR adding support for Explicit Congestion Notification)","23.401 CR#1103r3",45,23,null,null,"2009-05-28","2009-09-21"]
[6305,450051,"   SA4 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090653","-","Qualcomm","Nikolai Leung","SP#46 completed",26.114000000000001,45,23,null,null,"2009-05-28","2009-12-07"]
[6308,521006,"   (IETF) CT aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","C1-IETF,C3-IETF,C4-IETF","2007-05-07","2012-09-07",1,"SP-090653","-","Lionel Morand","-","CP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",52,27,null,null,"2011-06-20","2012-09-03"]
[6314,430136,"   SA3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3","2009-03-13","2010-03-25",1,"SP-090128","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","New 33.828, 33.328",43,22,null,null,"2009-02-11","2010-03-01"]
[6316,870075,"   (IETF) Security Considerations for WebRTC (draft-ietf-rtcweb-security)","MEDIASEC",2,"Rel-9","S3-IETF","2002-03-01","2012-09-14",0.9,null,null,null,null,"9/4/21: RFC 8826 added;","RFC 8826",87,44,null,null,"2011-06-20","2021-04-09"]
[6319,450021,"      CT4 aspects of IMS Media Plane Security","MEDIASEC_CORE",3,"Rel-9","C4","2009-09-18","2010-03-19",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#47 completed","29.238, 23.334, 29.334",45,23,null,null,"2009-02-11","2010-03-09"]
[6323,440054,"Extended Identity Management","GBA-IdM",1,"Rel-9","S3","2009-06-04","2009-12-10",1,"SP-090284","-","Nokia","Silke.Holtmanns@nokia.com","SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous)","New 33.924, CT4 29.109 (added service code)",44,23,null,null,"2009-05-18","2010-02-23"]
[6326,521008,"   (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3-IETF","2009-06-04","2012-12-07",1,"SP-090286","-","Bengt Sahlin","-","CP#58 completed","RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols)",52,27,null,null,"2011-06-20","2012-11-24"]
[6327,440256,"   Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","C4","2009-06-04","2009-12-04",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","CP#46 completed. No impact on CT4 specs","-",44,23,"CP-46","PCG-24","2009-05-18","2009-11-25"]
[6330,440357,"   CT1 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C1","2009-06-04","2009-09-18",1,"SP-090287","-","Ericsson","Karl Norrman","CP#45 completed","24.008,44.064",44,23,null,null,"2009-05-18","2009-09-08"]
[6333,440657,"   GERAN3new (testing) part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","G3new","2009-06-04","2009-11-20",1,"GP-091212","-","Ericsson","Karl Norrman","GP#44 completed. GP#43 WID approved",51.01,44,23,null,null,"2009-05-18","2009-11-20"]
[6337,440046,"PSS and MBMS Aspects","PMA",1,"Rel-9","S4","2009-03-12","2010-03-25",1,"SP-090261","-","Ericsson, Nokia","Clinton.Priddle@ericsson.com, imed.bouazizi@nokia.com","Umbrella WI","-",44,23,null,null,"2009-05-31","2010-03-08"]
[6340,430046,"IMS based PSS and MBMS User Service extensions","IMS_PSS_MBMS_US_EXT",1,"Rel-9","S4","2009-03-12","2009-12-10",1,"SP-090225","-","Ericsson","Markus Kampmann","SP#46 completed. Work extending Rel-8 UID_34046 (IMS_PSS_MBMS_US), SA2 UID_410034 IMSSCC-SPI (IMS Service Continuity Enhancements: Service, Policy and Interactions) ",26.236999999999998,43,22,null,null,"2009-02-02","2009-12-07"]
[6343,420029,"Rel-9 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM9",1,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","OAM9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,42,22,null,null,"2008-11-25","2010-02-09"]
[6347,440065,"      IRP SOAP Solution Sets continuation from Rel-8","-",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090314","-","Ericsson","John Power","SP#47 completed. Continuation of Rel-8 UID_400030 IRP SOAP Solution Sets","New (32.127/ 327/ 337/ 357/ 387/ 397/ 447/ 397/ 447/ 507/ 537), 32.121,32.122,32.123,32,32.321,32.322,32.323,32.325,32.331,32.332,32.333,32.335,32.351,32.352,32.353,32.381,32.382,32.383,32.385,32.391,32.392,32.393,32.395,32.441,32.442,32.443",44,23,null,null,"2009-05-18","2010-03-22"]
[6350,430041,"      Enhancement of E-UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-03-12","2010-06-10",1,"SP-090053","-","Motorola, Huawei","Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com)","SP#48 completed",32.424999999999997,43,22,null,null,"2009-02-23","2010-05-26"]
[6351,430042,"      Enhancement of EPC Performance Measurements","-",3,"Rel-9","S5","2009-03-12","2009-12-10",1,"SP-090049","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#46 completed",32.426000000000002,43,22,null,null,"2009-02-25","2010-02-09"]
[6354,440067,"      Automatic Radio Network Configuration Data Preparation","-",3,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090869","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#48 completed","32.501, 32.502, 32.503, 32.505, new 32.507",44,23,null,null,"2009-05-18","2010-05-26"]
[6357,440068,"Rel-9 Charging Management small Enhancements","CH9",1,"Rel-9","S5","2009-06-04","2010-03-25",1,"-","-","-","-","CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,44,23,null,null,"2009-05-19","2010-03-08"]
[6361,410008,"IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",1,"Rel-9","C4,C3","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","-",41,21,null,null,"2007-09-05","2009-07-29"]
[6364,410009,"IMS Application Level Gateway Control Function (ALGCF) – IMS Access Media Gateway (IMA-MGW); Iq Interface; Stage 2 and Stage 3","IMS_AGCF",1,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090020","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed ","New 23.334, 29.334",41,21,null,null,"2007-09-05","2009-11-16"]
[6367,440017,"Completion of IMS Restoration Procedures","eIMS_RP",1,"Rel-9","C3,C4,C1","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed. Continuation of Rel-8 Feature UID_400012 IMS Restoration Procedures","-",44,23,null,null,"2009-05-13","2010-04-01"]
[6371,440039,"IMS Stage 3 IETF Protocol Alignment - phase 3","IMSProtoc3",1,"Rel-9","C1,IETF","2009-05-29","2014-12-05",1,"CP-090491","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","-",44,23,null,null,"2009-05-13","2010-03-02"]
[6375,440070,"Operational description of the Inter-IMS Network to Network Interface (II-NNI)","II-NNI",1,"Rel-9","C3,IETF","2009-05-29","2014-12-09",1,"CP-090331","-","Orange","sebastien.daudet@orange-ftgroup.com","-","-",44,23,null,null,"2009-05-29","2013-02-28"]
[6376,440170,"   Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3","2009-05-29","2010-06-04",1,"CP-090331","-","Orange","-","CP#48 completed",29.164999999999999,44,23,null,null,"2012-04-20","2010-05-27"]
[6379,561006,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100","draft-ietf-salud-alert-info-urns",56,29,null,null,"2012-04-20","2016-03-07"]
[6382,561009,"   Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2013-12-06",1,"CP-090331","-","Peter Dawes","peter.dawes@vodafone.com","CP#62 removed from Rel-8 to Rel-11. Not completed internet-draft","Rel-12 remains draft-dawes-sipping-debug",56,29,"SP-69",null,"2012-04-20","2013-11-27"]
[6386,460004,"3GPP IMS Conferencing Management Object (MO)","IMS_ConfMO",1,"Rel-9","C1","2009-12-03","2009-12-04",1,"-","-","-","-","CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2)","New 24.166",46,24,null,null,"2009-12-08","2010-02-09"]
[6389,410017,"   LCR TDD UE OTA Performance Requirements","RInImp9-RFLCROTA",2,"Rel-9","R4","2008-09-12","2009-05-29",1,"RP-080744","RP-090389","RITT","Wu Xiang (wuxiang@chinattl.com)","RP#44 completed technical work (RAN4 internal TR abandoned)","UTRA (no 25.8xy produced)",41,21,null,null,"2008-09-11","2009-09-09"]
[6393,420010,"   Extended UMTS/LTE 800 MHz","RInImp9-UMTSLTE800",2,"Rel-9","R4,R2,R3","2008-12-05","2008-12-05",1,"RP-080884","RP-090687","NTT DoCoMo","Shingo Suwa (suwas@nttdocomo.co.jp)","RP#45 completed","UTRA, LTE 25.101, 25.104, 25.113, 25.133, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466, new 36.800",42,22,null,null,"2008-12-04","2009-10-07"]
[6396,440004,"   Extended UMTS/LTE 1500 MHz","UMTSLTE1500",2,"Rel-9","R4,R2,R3","2009-05-30","2009-05-30",1,"RP-090470","RP-100029","NTT DoCoMo","Shingo Suwa (suwas@nttdocomo.co.jp)","RP#47 completed. For potential deployment in Japan","UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.331, new (36.821, 36.307)",44,23,null,null,"2009-05-22","2010-03-16"]
[6399,450017,"   Conformance Test Aspects – Extended UMTS/LTE 1500 MHz","UMTSLTE1500_UEConTest",2,"Rel-9","R5","2009-09-18","2010-06-04",1,"RP-091366","RP-100487","NTT DoCoMo","Nguyen Dung Dao (dao@nttdocomo.co.jp)","RP#48 completed","UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",45,23,null,null,"2009-09-15","2010-06-01"]
[6400,440012,"   TDD UE Over The Air (Antenna) conformance testing methodology","UEAnt_TDDTest",2,"Rel-9","R5","2009-05-30","2009-09-18",1,"RP-090621","RP-090727","CATR","Qu Yan (quyan@emcite.com)","RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head)","UTRA 34.114",44,23,null,null,"2009-05-20","2009-09-10"]
[6403,430013,"Rel-9 RAN improvements","-",1,"Rel-9","RP","2009-03-06","2010-09-08",1,"-","-","-","-","RP#47 completed","UTRA",43,22,null,null,"2009-03-06","2010-09-08"]
[6406,430016,"   Combination of DC-HSDPA with MIMO","RANimp-DC_MIMO",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090332","RP-091039","Ericsson","johan.bergman@ericsson.com","RP#46 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 26.306, 25.423, 25.433",43,22,null,null,"2009-03-06","2009-11-27"]
[6410,490019,"   Conformance Test Aspects – Combination of DC-HSDPA with MIMO","RANimp-DC_MIMO_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-101001","RP-110510","Ericsson","leif.mattisson@ericsson.com","UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO","UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-08","2011-05-18"]
[6413,420007,"LTE improvements","LTEimp",1,"Rel-9","R1,R2,R4,R5","2009-03-06","2011-06-03",1,"-","-","-","-","-","LTE",42,22,null,null,"2008-12-02","2009-01-21"]
[6417,420011,"Rel-9 Self-Organizing Networks (SON)","SON",1,"Rel-9","R3,R2","2009-03-06","2009-03-06",1,"RP-090162","RP-100038","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#47 completed","LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902",42,22,null,null,"2008-12-05","2010-03-10"]
[6420,38004,"   AGNSS Testing Procedures","AGNSSPTP-MStest",2,"Rel-9","G3new","2008-05-16","2011-05-20",1,"GP-092343","-","Thales","Michel.monnerat@thalesaleniaspace.com","GP#50 completed","51.010-1, new 51.010-7",38,20,null,null,"2008-05-19","2011-05-21"]
[6423,420004,"   Stage 3 for Voice services over Adaptive Multi-user channels on One Slot","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-03-04",1,"GP-081965","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#49 completed. GP#40 WID approved","24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058",40,22,null,null,"2008-11-23","2011-03-04"]
[6424,420005,"   VAMOS Radio Performance Requirements","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-05-20",1,"GP-081966","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#50 completed. GP#40 WID approved",45.005000000000003,40,22,null,null,"2008-11-23","2011-05-21"]
[6427,440002,"Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC)","CEBRO",1,"Rel-9","GP,C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed. GP#45 completed. GP#42 WID approved","-",42,23,null,null,"2009-05-18","2010-03-05"]
[6430,440003,"Hybrid Location","HILT",1,"Rel-9","GP","2009-05-18","2009-11-20",1,"GP-091075","-","TruePosition","Matt Ward (mward@trueposition.com)","GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT)","43.059, 48.071",42,23,null,null,"2009-05-18","2009-09-07"]
[6436,380081,"Deleted - Support of WiMAX - LTE Mobility","WiMAX_LTE_Mobility",1,"Rel-9","R2","2008-06-06","2009-12-25",1,"RP-070511","-","Samsung","-","RP#39: No agreed WID","36.306, 36.331, 36.413, 36.300, 36.214, 36.133, 36.304",38,21,"SP-39","PCG-21","2007-12-17","2009-03-24"]
[6438,380086,"Deleted - Definition of 3GPP UICC services over the new high-speed interface","UICCHS",1,"Rel-9","C6","2010-03-19","2010-03-19",1,"CP-070837","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#47 work stopped/abandoned","31.xyz",38,21,"CP-47","PCG-24","2008-01-31","2009-11-25"]
[6442,390042,"   Deleted - SAE for generic support for non-3GPP accesses","SAES_Ph2",2,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[6445,0,"Release 9 Studies","-",1,"Rel-9","CP,RP,SP","2008-06-05","2008-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6448,370043,"Study on Extended Support of IMS Emergency Calls","FS_IMS-eCall",1,"Rel-9","S2","2007-09-24","2008-12-11",1,"SP-070547","-","Qualcomm","Stephen Edge ","SP#42 completed",23.867999999999999,37,19,null,null,"2006-07-19","2008-11-22"]
[6449,320031,"Study on Service Continuity for Emergency Voice Calls","FS_VCCEm",1,"Rel-9","S2","2006-06-08","2009-03-12",1,"SP-080555","-","Nortel","Ricky Kaura (rkaura@nortel.com)","SP#43 completed",23.826000000000001,32,17,null,null,"2006-07-19","2009-02-24"]
[6452,360007,"Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB","FS_OAM-SON-HNB",1,"Rel-9","S5","2007-06-07","2009-06-04",1,"SP-080461","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036)",32.820999999999998,36,19,null,null,"2007-05-28","2009-05-18"]
[6456,390031,"Study on LTE-Advanced","FS_RAN_LTEA",1,"Rel-9","R1,R2,R3,R4","2008-03-21","2010-03-19",1,"RP-091360","RP-100080","NTT DoCoMo","Tetsushi Abe","RP#47 completed","36.913 , New 36.814, 36.912, R2 36.806 (Relay architectures for E-UTRA), R4 36.815 (LTE-Advanced feasibility studies in RAN4)",39,21,null,null,"2007-12-17","2010-03-16"]
[6459,430021,"Study on Minimization of drive-tests in Next Generation Networks","FS_NGN_min_drive-tests",1,"Rel-9","R2","2009-03-06","2009-12-04",1,"RP-090341","RP-091084","Qualcomm","Masato Kitazoe (mkitazoe@qualcomm.com)","RP#46 completed",36.805,43,22,null,null,"2009-03-06","2009-11-27"]
[6462,320026,"Deleted - Study on Protection against SMS and MMS spam","FS_CPSMal",1,"Rel-9","S3","2006-06-08","2009-09-24",1,"SP-060446","-","Orange","eric.gauthier@orange.ch","SP#45 work stopped/abandoned","33.9xx",32,17,"SP-45","PCG-23","2006-06-23","2009-09-21"]
[6466,370005,"   High level and common (for all accesses) functions ","EPS-ComF",2,"Rel-8","S2,S3,C1,C3,C4","2007-01-02","2009-05-29",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","CP#44 completed","-",37,19,null,null,"2007-09-19","2010-07-28"]
[6469,340051,"      Stage 3 (CT1) for SAE impact on services, network functions and capabilities","SAES",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.229, 27.007, New 24.305",34,18,null,null,"2006-07-19","2010-07-28"]
[{"$f":"A6472+1","v":6472},340049,"      Stage 2/3 for Network selection procedures","SAES",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed","23.122, New 24.302",34,18,null,null,"2006-07-19","2010-07-28"]
[6473,340023,"      Stage 3 EPC interworking with external PDNs (SGi)","SAES-St3-intwk",3,"Rel-8","C3","2007-02-05","2009-05-29",1,"CP-080772","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#44 completed",29.061,34,18,null,null,"2006-07-19","2010-07-28"]
[6476,370017,"      Unified guidelines for Diameter usage within 3GPP","SAES-DIAM",3,"Rel-8","C3","2007-09-21","2008-12-05",1,"CP-080055","-","Huawei","Javier Gonzalez Gallego","CP#42 completed","New 29.909",37,19,null,null,"2007-09-25","2010-07-28"]
[6480,370006,"         Stage 2 for SAES-SA-FP_LTE with GTP variant","SAES-SA-FP_LTE-GTP-St2",4,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","23.401, 23.060, 23.002, 23.246, 23.203, 23.107, 23.234, 23.271",37,19,null,null,"2007-09-19","2010-07-28"]
[6483,370007,"         Stage 2 for SAES-SA-FP_LTE with PMIP variant","SAES-SA-FP_LTE-IETF-St2",4,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","-",37,19,null,null,"2007-09-19","2010-07-28"]
[6486,340020,"      Stage 3 for UE Non-Access-Stratum (NAS) mobility procedures in idle and active mode","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.007, 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[6490,340026,"      Stage 3 for EPC - HSS interface","SAES-LTE",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",29.271999999999998,34,18,null,null,"2006-07-19","2010-07-28"]
[6493,380031,"      Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008, 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[6497,380032,"      Stage 3 for EPC to UTRAN","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.275, 29.281",38,21,null,null,"2006-07-19","2010-07-28"]
[6498,380033,"      Stage 3 for EPC to 3GPP2","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.277, 29.276",38,21,null,null,"2006-07-19","2010-07-28"]
[6501,340061,"      Stage 3 for MME - SGSN signalling free protocol","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.272, 29.274",34,18,null,null,"2006-07-19","2010-07-28"]
[6505,360022,"      Stage 3 for Mobility management based on DSMIPv6","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303000000000001,36,19,null,null,"2007-09-12","2010-07-28"]
[6508,390009,"      Stage 3 for Mobility management based on MIP v4","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303999999999998,39,21,null,null,"2008-03-03","2010-07-28"]
[6511,390045,"      Stage 2 Security aspects for non-3GPP Access","SAES-SA-FP_n3GPP",3,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080132","-","Nokia Siemens Networks","marc.blommaert.ext@nsn.com","SP#42 completed","33.402, 33.210, 33.310",39,21,null,null,"2008-03-19","2010-07-28"]
[6515,370011,"      Stage 3 for interfaces within EPC","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-09-19","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.281",37,19,null,null,"2007-09-19","2010-07-28"]
[6518,340058,"      Stage 3 for AAA/HSS related","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[6519,340059,"      Stage 3 for EPC - AAA interface","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[6522,350130,"      Stage 2 for 2G/3G SRVCC","SAES-SRVCC",3,"Rel-8","S2","2007-01-02","2008-09-18",1,"SP-070949","-","Nokia Siemens Networks","curt.c.wong@nokia.com","SP#41 completed. SP#38 WID approved","New 23.216",35,18,null,null,"2007-03-29","2010-07-28"]
[6525,360020,"   Voice Call Continuity for CDMA2000 1X","SAES-VCC_1X",2,"Rel-8","S2","2007-06-25","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","-",36,19,null,null,"2007-03-29","2010-07-28"]
[6529,400102,"      CT1 part of Stage 3 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-080791","-","NEC","yannick.lair@nectech.fr","CP#43 completed","24.007, 24.008, 24.011, 29.018, New (24.301, 24.801, 29.118)",40,21,null,null,"2007-03-29","2010-07-28"]
[6532,390010,"   EPC Data Definitions","EPC-OAM",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"-","-","-","-","SP#43 completed","-",39,21,null,null,"2005-06-17","2010-07-28"]
[6535,380038,"   EPC Charging","EPC-CH",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070736","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240, 32.296, 32.251, 32.252, 32.298, 32.299",38,21,null,null,"2005-06-17","2010-07-28"]
[6539,390121,"      Core specification for CT6 aspects of SAE","SAES",3,"Rel-8","C6","2008-03-07","2009-05-29",1,"CP-080164","-","Nokia","Rune Lindholm","CP#44 completed (specified Network Measurement Results collection via USAT)","31.102, 31.111",39,21,null,null,"2008-03-12","2010-07-28"]
[6542,390018,"   Issues for CT1 TR 24.801","SAES",2,"Rel-8","C1","2007-01-04","2008-12-05",1,"CP-080068","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed",24.800999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[6543,390019,"   Issues for CT3 TR 29.804","SAES",2,"Rel-8","C3","2007-02-05","2008-09-12",1,"CP-080068","-","Ericsson ","j.javier.pastor@ericsson.com","CP#41 completed",29.803999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[6546,350032,"   Deleted (covered by 380064): SAE aspects of Emergency Calls","SAES-SA-EmCall",2,"Rel-8","S2","2008-03-03","2008-03-03",1,"-","-","Nokia Siemens Networks","-","SP#37 stopped","-",35,18,"SP-37",null,"2007-03-29","2009-03-24"]
[6549,340052,"      Deleted - Interoperability","SAES-St3-interop",3,"Rel-8","C1","2008-03-14","2008-03-14",1,"CP-060674","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6553,340027,"      Deleted - User and Control plane protocols","SAES-St3-prot",3,"Rel-8","C4","2007-09-21","2007-09-21",1,"CP-060676","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6558,370025,"IMS Centralized Service control","ICSRA",1,"Rel-8","S1,S2,C1,C3,C4,IETF","2005-11-01","2014-12-09",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","CP#46 completed","-",37,19,null,null,"2007-10-02","2009-12-02"]
[6561,400205,"   Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data","ICSRA",2,"Rel-8","C1,C3,C4,IETF","2005-11-01","2014-12-09",1,"CP-091046","-","Ericsson","sean.schneyer@ericsson.com","CP#46 completed","-","-","-",null,null,"2009-12-02","2009-12-07"]
[6564,521015,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 6871)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2013-03-01",1,"CP-091046","-","Andrew Allen","-","CP#59 completed","RFC 6871 (was draft-ietf-mmusic-sdp-media-capabilities)",52,27,null,null,"2011-06-20","2013-02-28"]
[6567,400006,"      CT3 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-091046","-","Mavenir","Brett Wallis ( brett@mavenir.com)","CP#43 completed","new 29.292",40,21,null,null,"2008-03-03","2009-12-07"]
[6568,400007,"      CT4 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-091046","-","Ericsson","Sean Schneyer","CP#42 completed","23.003, 29.232, 23.018, 29.002",40,21,null,null,"2008-03-03","2009-12-07"]
[6571,370059,"IMS Multimedia Telephony and Supplementary Services","IMSTSS",1,"Rel-8","S1,S5,C1,C3,C4,IETF","2007-05-02","2014-12-09",1,"-","-","-","-","SP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[6574,380001,"      Documentation of TISPAN R1 and R2 in CT1","REDOC_TIS-C1",3,"Rel-8","C1","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","24.141, 24.147, 24.173, 24.229, 24.247, 24.341, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.616, 24.623, 24.628, 24.629, 24.647, 24.654",38,21,null,null,"2007-11-28","2008-08-01"]
[6578,370024,"      Merging TISPAN MMTel [requirements] for Common IMS","TMMTEL",3,"Rel-8","S1","2007-09-10","2007-12-07",1,"SP-070569","-","Nokia Siemens Networks","-","SP#38 completed",22.172999999999998,37,19,null,null,"2007-10-02","2007-11-19"]
[6581,380007,"      CT1 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C1","2007-05-02","2009-03-06",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.642, 24.229, 24.173",38,21,null,null,"2007-11-14","2012-01-11"]
[6585,390059,"      Stage 1 FA","FA",3,"Rel-8","S1","2008-01-30","2008-06-05",1,"-","-","Telecom Italia","-","SP#40 completed ",22.172999999999998,39,21,null,null,"2008-03-03","2008-09-18"]
[6588,380010,"      CT1 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C1","2007-11-30","2009-03-06",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.615, 24.229, 24.173",38,21,null,null,"2007-11-14","2009-02-20"]
[6591,370103,"   IMS Charging","CH8_IMS",2,"Rel-8","S5","2007-09-17","2009-03-12",1,"SP-070621","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#39 completed","32.260, 32.298",37,19,null,null,"2007-09-15","2008-03-23"]
[6592,370003,"      Add Interconnection Border Control Function (IBCF) to IMS Charging","CH8_IMS",3,"Rel-8","S5","2007-09-17","2008-03-12",1,"SP-070621","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#39 completed","32.260, 32.298",37,19,null,null,"2007-09-15","2008-03-23"]
[6595,390050,"   Stage 1 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","22.228, 22.173, 22.101, 22.153",39,21,null,null,"2008-03-03","2015-03-24"]
[6599,390013,"      Stage 3 CIMS_3GPP2 (CT1)","REDOC_3GPP2",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","23.218, 24.141, 24.147, 24.173, 24.229, 24.238, 24.247, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.629, 24.930",39,21,null,null,"2008-03-03","2008-12-04"]
[6602,350005,"IMS Enhancements for support of Packet Cable access","PktCbl",1,"Rel-8","S2,S3,C1,C3,C4","2006-12-06","2008-05-30",1,"-","-","Cablelabs","Bernie McKibben (b.mckibben@cablelabs.com)","CP#40 completed","-",35,18,null,null,"2007-03-29","2007-03-29"]
[6605,350010,"      CT1 aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070122","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed","-",35,18,null,null,"2007-03-29","2008-05-13"]
[6609,340008,"   IMS Enhancements for Security Requirements in Support of Cable Deployments","PktCbl-Sec",2,"Rel-8","S3,C1,C3,C4","2006-12-06","2008-05-30",1,"SP-060933","-","Cablelabs","s.dotson@cablelabs.com","CP#40 completed","-",34,18,null,null,"2005-11-04","2007-05-29"]
[6612,380029,"      CT3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C3","2007-03-26","2007-11-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#38 completed",29.163,38,21,null,null,"2007-03-29","2008-03-07"]
[6615,390049,"   SA1 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080095","-","Telecom Italia","-","SP#40 completed","-",39,21,null,null,"2007-06-22","2008-05-19"]
[6616,360014,"   SA2 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S2","2007-06-22","2008-09-18",1,"SP-080095","-","Orange","Delphin Barankanira","no Stage 2 impacts",23.228000000000002,36,19,null,null,"2007-06-22","2010-07-29"]
[6619,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228, 29.229, 23.003, 23.008, 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[6624,380044,"   Maintenance of TISPAN release 2 common IMS","IMS_Comm_Mtce8",2,"Rel-8","S2","2007-07-02","2007-12-06",1,"SP-070916","-","Telecom Italia","antonio.ascolese@telecomitalia.it","SP#38 completed","23.506, 23.507,23.517, 23.521",38,21,null,null,"2007-10-02","2010-07-29"]
[6627,390057,"   Stage 2 IMS Service Continuity","IMS-Cont",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080092","-","LG Electronics","JaeSeung SONG (anthonys@lge.com)","SP#40 completed","23.237, 23.292",39,21,null,null,"2007-10-02","2008-05-27"]
[6630,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203, 33.141, 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[6634,380013,"   CT4 part of Network Attachment Subsystem (NASS) Bundled Authentication","NBA-CT4",2,"Rel-8","C4","2007-11-14","2008-05-30",1,"CP-070781","-","Alcatel-Lucent","-","CP#40 completed","29.229, 29.228, 23.008",39,21,null,null,"2007-11-19","2008-05-14"]
[6637,521022,"   (IETF) IMS initiated and controlled PSS and MBMS User Service (RFC 6080)","IMS_PSS_MBMS_US",2,"Rel-8","S4-IETF","2008-03-12","2011-09-21",1,"SP-080201","-","Ericsson","-","SP#53/IETF#81 completed","RFC 6080 (was draft-ietf-sipping-config-framework)",52,27,null,null,"2011-06-20","2013-08-23"]
[6640,7014,"   Stage 3 of MW-IMS","MIW-IMS-St3C3",2,"Rel-8","C3","2005-09-23","2007-11-30",1,"CP-070096","-","Vodafone","nico.gabriele@vodafone.com","Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021","29.863, 29.163",70,36,null,null,"2006-02-16","2008-08-05"]
[6641,380021,"   Stage 3 for MW-IMS, MONA extension","MIW-IMS-St3C3_MONA",2,"Rel-8","C3","2007-11-05","2008-12-05",1,"CP-070729","-","Vodafone","Christer.Holmberg@ericsson.com","CP#42 completed","29.863, 29.163",38,21,null,null,"2007-11-13","2008-09-01"]
[6644,360129,"   CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",2,"Rel-8","C1","2007-06-22","2009-03-06",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","23.218, 24.229, 24.930",36,19,null,null,"2007-09-05","2009-02-20"]
[6648,380014,"Interworking between User-to-User Signalling (UUS) and SIP ","UUSIW",1,"Rel-8","C1,C3,IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#43 completed","-",38,21,null,null,"2007-11-13","2009-03-11"]
[6651,551001,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2011-03-17","2014-12-09",1,"CP-070782","-","Keith Drage","Keith Drage (drage@alcatel-lucent.com)","In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdn). June 2015: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn)","RFC 7434",55,28,null,null,"2012-03-03","2015-03-10"]
[6654,380019,"   Stage 3 Overlap (CT1)","Overlap",2,"Rel-8","C1","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed",24.228999999999999,38,21,null,null,"2007-11-13","2009-02-20"]
[6658,380135,"   AS/MRFC Stage 2","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed",23.218,38,21,null,null,"2007-11-14","2012-01-10"]
[6661,400012,"IMS Restoration Procedures","IMS_RP",1,"Rel-8","C4,C1","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 ","-",40,21,null,null,"2007-03-29","2010-07-30"]
[6662,400026,"   IMS Restoration Procedures (CT4)","IMS_RP",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed","23.380, 29.228, 29.229, 29.230, 23.008",40,21,null,null,"2007-03-29","2010-07-30"]
[6665,340030,"I-WLAN Network Selection Principle (NSP)","IWLANNSP",1,"Rel-8","S1,C1,C6","2007-06-14","2009-03-06",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","CP#43 completed","-",34,18,null,null,"2005-11-04","2009-02-25"]
[6668,390125,"   CT6 part of Stage 3 for I-WLAN NSP","IWLANNSP",2,"Rel-8","C6","2008-03-07","2008-12-11",1,"CP-080217","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","CP#42 completed","31.102, 31.111",39,21,null,null,"2008-03-07","2009-02-25"]
[6672,460006,"Conformance Test Aspects – Mobility between 3GPP WLAN Interworking and 3GPP Systems","IWLAN_Mob_UEConTest",1,"Rel-8","R5","2009-12-04","2010-09-17",1,"RP-091349","RP-100740","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","RP#49 completed. Testing for Rel-8 UID_400013 CT1 aspects of mobility between 3GPP WLAN Interworking and 3GPP Systems (24.327)","34.108, 34.123-1, 34.123-2, 34.123-3",46,24,null,null,"2009-11-30","2010-09-09"]
[6675,370019,"   VGCS/VBS and GPRS Interactions","EVA",2,"Rel-8","S1","2007-09-03","2008-03-21",1,"SP-070653","-","Huawei","Ling Liu","SP#39 completed","42.068, 42.069",37,19,null,null,"2007-10-02","2008-05-16"]
[6678,52148,"   GERAN2 aspects of EVA","EVA",2,"Rel-8","G2","2006-06-30","2008-02-22",1,"GP-071855","-","Nortel","frank.billenkamp@nortel.com","GP#37 completed","44.018, 48.008",null,null,null,null,"2006-07-05","2008-05-16"]
[6680,7012,"   Stage 1 for PNM","PNM",2,"Rel-8","S1","2005-07-11","2006-07-31",1,"SP-080327","-","Vodafone","armin.toepfer@vodafone.com","SP#31 completed",22.259,null,null,null,null,"2006-02-16","2008-06-04"]
[6686,350049,"   Deleted - Actual Requirements of PNM","PNM",2,"Rel-8","C1","2007-03-26","2007-03-26",1,"-","-","Ericsson","-","SP#37 stopped","-",null,null,"SP-37",null,"2007-05-04","2009-03-24"]
[6687,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[6690,34042,"eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution","eCall_Phase2",1,"Rel-8","S4","2007-12-06","2009-09-24",1,"SP-070756","-","Airbiquity","lhong@airbiquity.com & rrobinson@airbiquity.com","SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData)","26.267, 26.268, 26.269, 26.967, 26.969",null,null,null,null,"2007-12-09","2010-08-02"]
[6693,380060,"IP Interconnection of Services ","IPinterc",1,"Rel-8","S1,S2,S5,C3","2006-08-16","2009-03-06",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#43 completed","-",38,21,null,null,"2007-12-13","2010-08-02"]
[6697,360011,"      IMS inter-operator service interconnection interface","FBI2-IOPSI",3,"Rel-8","C3","2007-06-01","2009-03-06",1,"CP-080578","-","Telecom Italia","antonio.ascolese@telecomitalia.it","CP#43 completed","29.865, 29.165",null,null,null,null,"2007-06-20","2010-08-02"]
[6700,7006,"      Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8","FBI2-TISP2-s2",3,"Rel-8","S2","2007-11-30","2007-11-30",1,"-","-","Nokia Siemens Networks","-","SP#36 stopped","-",null,null,"SP-36",null,"2006-02-16","2009-03-24"]
[6703,360026,"   SIP-I based circuit-switched core network; Stage 2","SIP_Nc-St2",2,"Rel-8","C4","2007-09-14","2008-12-05",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#42 completed","23.231, 23.153, 23.205",null,null,null,null,"2007-09-05","2008-11-22"]
[6707,370052,"   Stage 1 for ETWS","ETWS",2,"Rel-8","S1","2007-09-10","2008-03-12",1,"SP-070815","-","NTT DoCoMo","kitaharar@nttdocomo.co.jp","SP#39 completed",22.167999999999999,37,null,null,null,"2007-11-19","2008-03-20"]
[6710,410021,"   CT4 aspects of ETWS","ETWS",2,"Rel-8","C4","2008-09-26","2008-12-05",1,"CP-080951","-","NTT DoCoMo","yamashitahi@s1.nttdocomo.co.jp","CP#42 completed",29.167999999999999,40,21,null,null,"2007-12-13","2010-08-02"]
[6711,430045,"   ETWS primary notification message definition in GERAN","ETWS",2,"Rel-8","G2","2009-03-12","2009-05-15",1,"SP-090154","-","Ericsson","claes-goran.persson@ericsson.com","SP#44 completed with CT1 help (GERAN2 LS_in SP-090154)","44.018, 44.060",43,22,null,null,"2009-03-10","2009-05-30"]
[6714,380159,"   Stage 1 for ICE","ICE",2,"Rel-8","S1","2007-03-13","2008-03-12",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","SP#39 Stage 1 completed","22.030, 22.101",38,21,null,null,"2007-12-13","2008-06-17"]
[6717,340029,"Customized Alerting Tone (CAT) service","CAT",1,"Rel-8","S1,C1,C3,C4","2006-12-06","2009-09-18",1,"SP-070122","-","China Mobile","fenglingjuan@chinamobile.com","CP#45 completed","-",34,null,null,null,"2005-11-04","2010-08-02"]
[6721,390114,"      IMS CAT SS","CAT-SS",3,"Rel-8","C1","2008-04-21","2008-12-04",1,"CP-080496","-","Nortel","milanpa@nortel.com","CP#42 completed",24.181999999999999,39,21,null,null,"2008-03-03","2008-11-21"]
[6724,410110,"      CT4 part of CAT Service in 3GPP CS domain","CAT-3G_CS",3,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","CP#43 completed. Triggered by Study UID_360031 (TR 29.882) ","23.205, 23.231, 29.002",41,21,null,null,"2008-09-11","2012-01-11"]
[{"$f":"A6728+1","v":6728},350048,"   Stage 2 for MESSIW","MESSIW",2,"Rel-8","S2","2007-04-26","2008-03-07",1,"SP-070816","-","Huawei","patrice.hede@huawei.com","SP#39 completed","23.811, 23.204",null,null,null,null,"2005-11-04","2008-03-22"]
[6731,340044,"Multimedia Priority Service","PRIOR_EMR",1,"Rel-8","S1,C1,C3,C4","2006-06-08","2009-09-18",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","CP#45 completed","-",34,null,null,null,"2003-03-28","2009-09-09"]
[6734,370021,"   CT4 part of Stage 3 for PRIOR","PRIOR_EMR",2,"Rel-8","C4","2007-09-21","2009-03-06",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","23.008, 29.228, 29.229",37,null,null,null,"2007-09-25","2009-03-11"]
[6735,370020,"   Deleted - Stage 3 for PRIOR","PRIOR-EMR",2,"Rel-8","C3","2007-09-21","2009-05-29",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2)","29.212, 29.213, 29.214, 29.163",37,null,"CP-44","PCG-23","2007-09-25","2009-05-29"]
[6738,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6741,370013,"      Parlay-X Content Management web service (store/manage meta-data)","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-21",37,null,null,null,"2007-09-13","2009-01-19"]
[6746,380048,"      Deleted - Privacy on Subscriber Identity (Liberty Alliance, OASIS) (22.127 CR 0085 S1-071835)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6749,380051,"      Deleted - Event notification (22.127 CR 0088 S1-071762)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6753,380055,"      Deleted - Service identification (22.127 CR 0095 S1-071837)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Ericsson","catherine.mulligan@ericsson.com","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","existing 29.199-xy",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6756,390069,"      Connectivity Manager SCF","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-10",39,21,null,null,"2008-03-26","2009-01-19"]
[6759,370084,"   Stage 1 for PPACR","PPACR-S1",2,"Rel-8","S1","2007-06-12","2007-09-14",1,"SP-070501","-","NTT DoCoMo","Morita Takashi","SP#37 completed",22.010999999999999,37,null,null,null,"2007-10-16","2008-05-16"]
[6760,380017,"   Stage 3 for PPACR (CT1)","PPACR-CT1",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070783","-","NTT DoCoMo","-","CP#42 completed","24.008, 23.122, 24.301",38,21,null,null,"2007-11-14","2008-11-21"]
[6763,380070,"   Stage 1 for CHRGMPH","CHRGMPH-s1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-03-20"]
[6767,410012,"   CSG and Idle Mode Mobility for LTE Home eNodeB","HomeNB-LTE",2,"Rel-8","C1","2008-09-12","2009-03-06",1,"CP-080498","-","Huawei","zhang.peng@huawei.com","CP#43 completed","23.122, new (24.285, 24.301, 24.801)",41,21,null,null,"2008-09-03","2009-03-11"]
[6770,400053,"   Support of UTRA HNB","HNB-supp",2,"Rel-8","R2","2008-05-30","2009-03-06",1,"RP-080752","RP-090040","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#43 completed","25.304, 25.306, 25.331, new 25.367",40,21,null,null,"2008-06-03","2009-02-27"]
[6773,420037,"   3G Home NodeB OAM&P Type 1 Management Interface","HNB-3G_OAM",2,"Rel-8","S5","2008-12-11","2009-06-04",1,"SP-080708","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Complements work in BroadBand Forum","new (32.581, 32.582, 32.583, 32.584)",42,22,null,null,"2008-12-03","2009-05-18"]
[6777,390046,"Generic Bootstrapping Architecture Push Function","GBAPush",1,"Rel-8","S3,C1,C4","2008-03-12","2009-03-06",1,"SP-080133","-","Ericsson","Rolf Blom","CP#43 completed","-",39,21,null,null,"2008-03-22","2009-02-20"]
[6780,390346,"   CT4 part of GBAPush ","GBAPush",2,"Rel-8","C4","2008-03-12","2009-03-06",1,"CP-090112","-","Ericsson","Rolf Blom","CP#43 completed",29.109000000000002,39,21,null,null,"2008-03-22","2009-03-04"]
[6783,400028,"Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI","MTSI_eMHI",1,"Rel-8","S4,C3,C4","2007-12-06","2009-03-12",1,"SP-080443","-","Ericsson, Qualcomm","olle.franceschi@ericsson.com, nleung@qualcomm.com","TSG#43 completed","-",40,21,null,null,"2007-12-09","2009-02-21"]
[6784,34041,"   MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size","MTSI_eMHI-DRASIS",2,"Rel-8","S4","2007-12-06","2009-03-12",1,"SP-080246","-","Qualcomm, Samsung","nleung@qualcomm.com & kyunghun.jung@samsung.com","SP#43 completed",26.114000000000001,null,null,null,null,"2007-12-09","2010-08-02"]
[6787,400019,"   Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C1","2008-05-30","2008-12-12",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774","-",40,21,"CP-42",null,"2007-12-09","2010-08-02"]
[6791,35053,"      Advanced Alarming on Itf-N","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070492","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#40 completed","32.121, 32.122, 32.123",null,null,null,null,"2005-06-17","2008-06-04"]
[6794,400030,"      IRP SOAP Solution Sets","OAM8-NIM",3,"Rel-8","S5","2008-06-05","2009-03-12",1,"SP-090148","-","Ericsson","edwin.tse@ericsson.com","SP#43 completed","32.111-7, 32.617, 32.417, 32.367, 32.347, 32.111-1, 32.111-2, 32.111-3, 32.111-5, 32.307, 32.317, 32.341, 32.342, 32.343, 32.345, 32.361, 32.362, 32.363, 32.365, 32.411, 32.412, 32.413, 32.415, 32.611, 32.612, 32.613, 32.615, 32.625",40,21,null,null,"2007-09-15","2009-08-11"]
[6797,340065,"   Rel-8 Performance Management","OAM8-PM",2,"Rel-8","S5","2007-06-07","2009-03-12",1,"-","-","-","Li Jian (lijian@chinamobile.com)","-","-",34,null,null,null,"2007-07-13","2008-06-26"]
[6801,340066,"   Rel-8 Trace Management","OAM8-Trace",2,"Rel-8","C1,C4,IETF","2008-03-07","2012-12-07",1,"-","-","-","-","-","-",34,null,null,null,"2007-06-22","2008-12-10"]
[6802,11067,"      CT1 part of Service Level Tracing in IMS","OAM8-Trace",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080315","-","Vodafone","peter.dawes@vodafone.com","CP#42 completed","24.323, 24.229",null,null,null,null,"2008-03-17","2010-08-02"]
[6808,350016,"Rel-8 Charging Management small Enhancements","CH8",1,"Rel-8","S5","2006-03-16","2008-12-11",1,"-","-","-","-","CH8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI",30.818000000000001,null,null,null,null,"2006-05-22","2009-03-24"]
[6809,350038,"   Online charging correlation","CH8",2,"Rel-8","S5","2006-03-16","2007-12-14",1,"SP-070077","-","Orange","Chahine, Rony ","SP#38 completed",32.295999999999999,null,null,null,null,"2008-03-17","2008-03-17"]
[6812,380046,"   Deleted - WLAN Offline Charging","CH8",2,"Rel-8","S5","2008-01-07","2008-12-11",1,"SP-070750","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#42 stopped","32.252, 32.298, 32.299",38,21,"SP-42","PCG-22","2005-06-17","2009-03-24"]
[6816,320014,"Contact Manager for 3GPP UICC applications","eUPHBOOK",1,"Rel-8","C6","2006-06-22","2008-12-05",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#42 completed. CP#40: WID updated CP-070622=>CP-080382. aka Enhanced USIM phonebook","-",null,null,null,null,"2006-01-24","2009-03-24"]
[6819,370004,"   Internal interface for eUPHBOOK","eUPHBOOK-Int_Spec",2,"Rel-8","C6","2007-05-07","2008-12-05",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#42 completed","new 31.221",37,null,null,null,"2006-01-24","2008-11-25"]
[6822,330018,"   LTE – Physical Layer","LTE-Phys",2,"Rel-8","R1","2006-09-25","2008-03-07",1,"RP-080747","RP-080741","NTT DoCoMo","Sadayuki Abeta","RP#39 completed","36.201, 36.211, 36.212, 36.213, 36.214, 25.215, 25.225",null,null,null,null,"2006-03-21","2009-12-18"]
[6826,370046,"   LTE – FDD repeaters","LTE-Repeaters",2,"Rel-8","R4","2007-09-14","2009-03-06",1,"RP-070749","RP-090037","Powerwave Technologies, Andrew Wireless","ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com","RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report)","36.106, 36.143, 25.113",37,null,null,null,"2007-10-01","2010-03-16"]
[6829,380036,"      E-UTRAN Network Resource Model (NRM) Integration Reference Point (IRP)","E-UTRAN-OAM",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070738","-","Ericsson ","ELMDAHL, Per","SP#43 completed","new (32.761, 32.762, 32.763, 32.765)",38,21,null,null,"2005-06-17","2010-07-29"]
[6830,390002,"      Performance measurements for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080062","-","Motorola, Huawei","Yizhi Yao (yzyao@motorola.com)","SP#43 completed","new 32.425",39,21,null,null,"2005-06-17","2010-07-29"]
[6833,390104,"      SON Concepts and requirements","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080275","-","Vodafone","GOMPAKIS, Panagiotis","SP#42 completed","new 32.500",39,21,null,null,"2005-06-17","2008-11-25"]
[6836,25029,"Rel-8 LTE – Terminal Conformance Test Specification","LTE-UEConTest",1,"Rel-8","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Testing for Feature UID_20068 (LTE)","-",null,null,null,null,"2006-03-21","2008-06-01"]
[6840,350034,"   UMTS 1500 MHz","RInImp8-UMTS1500",2,"Rel-8","R4","2007-03-05","2007-09-14",1,"RP-070078","RP-070526","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","RP#37 completed","25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,null,null,"2004-09-27","2009-07-09"]
[6843,380074,"   UMTS 2300 MHz TDD LCR","RInImp8-UMTS2300TDD",2,"Rel-8","R4","2007-12-17","2008-09-12",1,"RP-071016","RP-080517","CATT","Yuexia Song (songyuexia@catt.cn)","RP#41 completed. RP#47 abandoned draft 25.828","25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.306, 25.331, 34.122",38,21,null,null,"2007-12-17","2010-08-02"]
[6846,370033,"   Performance requirements for 15 code reception with 16QAM/QPSK (FDD)","RInImp8-Hsdpa15codes",2,"Rel-8","R4","2007-06-11","2008-03-07",1,"RP-070745","RP-080043","Vodafone","tim.frost@vodafone.com","RP#39 completed",25.100999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6850,400055,"   Conformance Test Aspects – Performance requirements for 15 code reception with 16QAM/QPSK (FDD)","RInImp8-UEConTest_Hsdpa15codes",2,"Rel-8","R5","2008-03-07","2008-12-05",1,"RP-080311","RP-080818","Ericsson","Mikael.Ziren@Ericsson.com","RP#42 completed","34.121-1, 34.121-2",40,21,null,null,"2008-06-03","2008-12-09"]
[6853,370036,"   Improved L2 for uplink","RANimp-UplinkL2dataRates",2,"Rel-8","R2","2007-09-14","2008-05-30",1,"RP-070717","RP-080265","Ericsson","Janne.Peisa@ericsson.com","RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD","25.319, 25.301, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, 25.427",37,null,null,null,"2007-10-02","2010-08-03"]
[6854,370037,"   Enhanced Uplink for CELL_FACH State in FDD","RANimp-UplinkEnhState",2,"Rel-8","R2","2007-09-14","2008-12-05",1,"RP-070677","RP-080804","Nokia Siemens Networks","markus.wimmer@nsn.com","RP#42 completed. Linked to UID_370036 Improved L2 for uplink","25.309, 25.211, 25.214, 25.321, 25.331, 25.423, 25.433",37,null,null,null,"2007-10-02","2010-08-03"]
[6857,370040,"   Enhancements for FDD HSPA Evolution","RANimp-HSPAEvo",2,"Rel-8","R3,R2","2007-09-14","2008-12-05",1,"RP-080830","RP-080805","Nokia Siemens Networks","masatoshi.nakamata@nsn.com","RP#42 completed. Triggered by Rel-7 Study on Scope of future FDD HSPA Evolution (UID_20065) TR 25.999","25.401, 25.413, 25.420, 25.423, 25.427, 25.433, 25.446, 25.301, 25.346",37,null,null,null,"2007-10-01","2010-08-03"]
[6860,390028,"   Continuous Connectivity for packet data users for 1.28 Mcps TDD","RANimp-LCRCPC",2,"Rel-8","R1","2008-03-07","2009-05-29",1,"RP-080085","RP-090394","TD Tech","chenying@td-tech.com","RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.929, 25.308, 25.319",39,21,null,null,"2008-03-17","2010-08-03"]
[6863,400050,"   MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","RANimp-MIMOLCR",2,"Rel-8","R1,R4","2008-01-24","2009-05-29",1,"RP-080485","RP-090313","CATT","wangke@datangmobile.cn","RP#43 completed","25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.102, 25.105, 25.142",40,21,null,null,"2008-03-17","2010-08-03"]
[6868,440010,"   Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates","RANimp-UEConTest_ImprovedL2LCRTDD",2,"Rel-8","R5","2009-05-29","2010-09-17",1,"RP-090491","RP-100737","CATT","Xiaozhong Chen (chenxiaozhong@datangmobile.cn)","RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink","34.108, 34.123-1, 34.123-2, 34.123-3",44,23,null,null,"2009-05-20","2010-09-09"]
[6871,430024,"   Conformance Test Aspects – Enhanced Uplink for CELL_FACH State in FDD","RANimp-UEConTest_EnhancedRACHCellFACHState",2,"Rel-8","R5","2009-03-06","2010-06-04",1,"RP-090152","RP-100483","Nokia","jarkko.hellsten@nokia.com","RP#48 completed. Testing for UID_370037","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",43,22,null,null,"2009-02-27","2010-08-03"]
[6875,450025,"   Conformance Test Aspects – MIMO for 1.28 Mcps TDD","RANimp-UEConTest_MIMOLCRTDD",2,"Rel-8","R5","2009-09-18","2010-06-04",1,"RP-100120","RP-100660","ZTE","huang.chun2@zte.com.cn","PR#48 completed. Testing for UID_400050","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[6878,440008,"Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast","MBSFN_IMB_UEConTest",1,"Rel-8","R5","2009-05-30","2010-03-19",1,"RP-090583","RP-100070","IPwireless","Phil Young (pyoung@ipwireless.com)","RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",44,23,null,null,"2009-05-21","2010-03-16"]
[6879,50583,"GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",1,"Rel-8","GP,G1,C1,G3new","2006-09-08","2011-11-25",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed. GP#52 completed MS conformance testing","44.018, 44.060, 45.002, 45.008, 45.010, 48.008, 48.018, 51.010",null,null,null,null,"2006-09-13","2011-11-25"]
[6882,53583,"   CT1 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","C1","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","-",24.007999999999999,null,null,null,null,"2006-09-13","2010-09-09"]
[6885,50587,"GAN Enhancements","GANENH",1,"Rel-8","GP","2007-05-15","2009-09-04",1,"GP-071484","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed. GP#43 completed Testing","-",null,null,null,null,"2007-09-06","2009-09-28"]
[6889,400041,"   GERAN aspects of AoIP","AoIP",2,"Rel-8","GP","2000-01-03","2008-11-21",1,"GP-081362","-","China Mobile, Ericsson","wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com","GP#40 completed. GP#39 updated WID GP-080901=>GP-081362. ","48.001, 48.002, 48.008, 48.020, 49.008, 48.103",40,21,null,null,"2008-05-28","2008-12-03"]
[6892,400324,"      CT4 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722","23.205, 23.153, 23.231, 29.232",40,21,null,null,"2007-09-19","2012-01-11"]
[6896,38001,"Support for Additional Navigation Satellite Systems (ANSS) for LCS","ANSS",1,"Rel-8","S1,G2,R2","2008-05-16","2008-12-11",1,"GP-081784","-","Qualcomm","Mungal Dhanda","GP#40 completed","-",null,null,null,null,"2008-05-19","2009-02-19"]
[6899,400051,"   RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS","RANimp-ANSS",2,"Rel-8","R2","2008-05-30","2008-12-05",1,"RP-080346","RP-080813","Qualcomm","Etienne Chaponniere (echaponn@qualcomm.com)","RP#42 WI closed at 95%. Considers Rel-9 performance requirements","25.305, 25.306, 25.331, 25.413, 25.423, 25.433, 25.453",40,21,null,null,"2008-03-17","2008-12-04"]
[6902,51150,"   BTS conformance testing for the Latency Reductions feature","CTLATRED-BTStest",2,"Rel-8","G1","2008-02-22","2009-02-20",1,"GP-080369","-","Ericsson","mats.y.samuelsson@ericsson.com","GP#41 completed",51.021000000000001,null,21,null,null,"2008-02-26","2009-02-20"]
[6903,53091,"MS conformance testing of changes introduced by WI \"Support of Packet-switched Handover for GERAN A/Gb mode\"","PSHCT-MStest",1,"Rel-8","G3new","2008-02-22","2008-11-21",1,"GP-080411","-","Rohde & Schwarz","Franz.Segerer@ROHDE-SCHWARZ.COM","GP#40 completed",51.01,null,21,null,null,"2008-02-26","2008-11-22"]
[6906,400025,"Test - (Small) Technical Enhancements and Improvements for Rel-8","TEI8_Test",1,"Rel-8","R5,G3new","2007-03-07","2010-12-24",1,"-","-","-","-","-","-",40,21,null,null,"2005-11-04","2010-12-07"]
[6909,340032,"Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN","LCS4_IWLAN",1,"Rel-8","S2","2007-09-28","2007-09-28",1,"SP-060818","-","LG Electronics","dhshim@lge.com","SP#35 stopped","23.234, 23.271, 23.167",34,null,"SP-35",null,"2006-03-22","2009-03-24"]
[6913,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[6916,53092,"Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain","SCSAGBCT-MStest",1,"Rel-8","G3new","2008-02-25","2009-09-04",1,"GP-080330","-","Nokia","arsi.heino@nokia.com","GP#43 work stopped/abandoned (completion 0%)",51.01,null,21,"GP-43","PCG-23","2008-02-26","2009-09-07"]
[{"$f":"A6920+1","v":6920},31089,"Study on Network Composition","FS_NetComp",1,"Rel-8","S1","2005-12-07","2007-12-12",1,"SP-060478","-","Nokia Siemens Networks","joerg.swetina@neclab.eu","SP#38 completed",22.98,null,null,null,null,"2005-12-12","2008-03-24"]
[6923,330016,"Study on Paging Permission with Access Control","FS_PPAC",1,"Rel-8","S1","2006-09-28","2007-09-20",1,"SP-060785","-","NTT DoCoMo","Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp)","SP#37 completed. Spin-off new Feature UID_370084 (PPACR)",22.908000000000001,null,null,null,null,"2006-10-06","2010-08-31"]
[6926,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[6928,32085,"Study on 3GPP System Architecture Evolution","FS_SAE",1,"Rel-8","S2,S3","2004-12-03","2009-03-12",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#43 completed","-",null,null,null,null,"2005-01-31","2009-02-20"]
[6931,7024,"   Security study for Inter-access mobility between non-3GPP and 3GPP system","FS_SAE",2,"Rel-8","S3","2007-09-03","2009-03-12",1,"SP-070163","-","Nokia","dajiang.zhang@nokia.com","SP#43 completed","33.821, 33.822",null,null,null,null,"2006-02-21","2009-02-20"]
[6935,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[6938,380078,"Study on Architecture of IMS based Customized Alerting Tone (CAT)","FS_CAT-St2",1,"Rel-8","S2","2007-12-04","2008-09-18",1,"SP-070905","-","China Mobile","WANG, Jing (wangjing@chinamobilecom)","SP#41 completed as Rel-8",23.872,38,21,null,null,"2007-12-20","2008-09-23"]
[6941,35065,"Study on Element Operations Systems Function (EOSF) definition","OAM7-NIM-EOSF",1,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070307","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#40 completed. WID updated SP-050608=>SP-070307",32.819000000000003,null,null,null,null,"2005-09-16","2008-04-28"]
[6945,350004,"Study on Charging Aspects of 3GPP System Evolution","FS_SAEcharg",1,"Rel-8","S5","2007-04-02","2007-12-06",1,"SP-070174","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#38 completed",32.82,null,null,null,null,"2005-11-24","2008-03-17"]
[6948,360030,"Study on IMS Application Server Service Data Descriptions for AS interoperability","FS_IMS_ASIO",1,"Rel-8","C4","2007-09-14","2008-09-12",1,"CP-070685","-","Alcatel-Lucent","Jean-Jacques Trottin","CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO)",29.864000000000001,null,null,null,null,"2007-09-05","2008-09-11"]
[6951,370041,"Study on Scope of future HSPA Evolution for 1.28 Mcps TDD","FS_RAN-LCRTDDHSPAEvo",1,"Rel-8","R1","2007-09-14","2008-05-30",1,"RP-070748","RP-080290","RITT","Xu Fei","RP#40 completed",25.824000000000002,37,null,null,null,"2007-06-21","2008-06-12"]
[6952,370042,"Study on Synchronized E-DCH for UTRA FDD","FS_RAN-UplinkSync",1,"Rel-8","R1","2007-09-14","2008-03-07",1,"RP-070678","RP-080068","Nokia Siemens Networks","Karri.Ranta-aho@nsn.com","RP#39 completed",25.823,37,null,null,null,"2007-06-21","2008-06-26"]
[6955,50589,"Study on A-interface over IP ","AINTIP",1,"Rel-8","GP","2007-08-31","2008-02-22",1,"GP-071562","-","China Mobile, Ericsson","paul.schliwa-bertling@ericsson.com","GP#37 completed. Spin-off implementation Feature AoIP (A-interface over IP) UID_50591",43.902999999999999,null,null,null,null,"2007-11-03","2008-03-03"]
[6959,370044,"Deleted - equals 340035 -FS on Service continuity between mobile and WLAN networks","FSSCMobToW",1,"Rel-8","S1","2007-09-03","2007-12-14",1,"SP-070557","-","BT","mike.meyerstein@bt.com","SP#39 stopped",22.937000000000001,37,null,"SP-39","PCG-21","2007-10-02","2009-03-24"]
[6962,390032,"Deleted - Study on Dual-Cell HSDPA operation","FS_RAN-DCHS",1,"Rel-8","R1","2007-08-15","2009-03-06",1,"RP-080228","RP-090066","Qualcomm","Josef Blanz","RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052)","withdrawn 25.825 v100",39,21,"RP-43","PCG-22","2007-12-17","2009-03-17"]
[6965,32106,"   TR on ServID","ServID",2,"Rel-7","S2","2005-05-02","2006-03-21",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-",23.815999999999999,null,null,null,null,"2005-07-01","2008-07-01"]
[6969,32116,"Supporting Globally Routable User Agent URIs in IMS","GRUU",1,"Rel-7","S2,S1,C1","2005-11-14","2007-06-15",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","SP#29 approved WID","-",null,null,null,null,"2003-03-28","2008-07-01"]
[6972,320011,"   Stage 3 of GRUU","GRUU",2,"Rel-7","C1","2006-06-02","2007-06-15",1,"CP-060358","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","CP#32 approved WID",24.228999999999999,null,null,null,null,"2006-02-16","2008-07-01"]
[6975,7037,"   Stage 3 of MTSI","MTSI",2,"Rel-7","C1","2006-03-10","2007-06-14",1,"CP-060257","-","Ericsson","christer.holmberg@ericsson.com","-",24.172999999999998,null,null,null,null,"2006-03-22","2008-06-25"]
[6976,7040,"   Media handling and interaction in MTSI","MTSI-MHI",2,"Rel-7","S4","2006-03-15","2007-03-15",1,"SP-060225","-","Ericsson","olle.franceschi@ericsson.com","-",26.114000000000001,null,null,null,null,"2006-03-21","2008-06-25"]
[6979,7023,"   Deleted - duplicates UID7039 - IMS Multimedia Telephony Service ","MMTEL",2,"Rel-7","S1","2007-06-15","2007-06-15",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","-",22.172999999999998,null,null,"SP-32",null,"2006-03-02","2008-06-25"]
[6983,387002,"   SA1 aspects of MCIMSTR1","MCIMSTR1-S1",2,"Rel-7","S1","2007-09-18","2007-12-06",1,"SP-070915","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","-","22.173, 22.273",38,21,null,null,"2008-01-10","2008-11-04"]
[6986,380004,"   Maintenance of TISPAN R1","MAINT_R1",2,"Rel-7","C1,C3,C4","2007-11-09","2008-03-07",1,"CP-080211","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#39 completed","24.404, 24.405, 24.406, 24.407, 24.408, 24.410, 24.411, 24.416, 29.421, 24.423, 24.428, 24.429, 29.433, 24.441, 24.403, 29.427, 24.430, 29.412",38,21,null,null,"2007-11-19","2008-04-15"]
[6989,32046,"   Study on Stage 2 for IMS-level solution","EMC1",2,"Rel-7","S2","2003-02-26","2005-09-16",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2003-03-27","2005-12-22"]
[6994,1315,"      CT1 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-",24.228999999999999,null,null,null,null,"2000-04-19","2007-09-12"]
[6997,13031,"      Deleted - CT3 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C3","2006-05-08","2006-09-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","Cancelled for Rel-7 and there is no corresponding Rel-8 WI",29.061,null,null,"CP-33",null,"2000-08-08","2008-07-01"]
[6998,1646,"      CT1 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","24.008, 24.234",null,null,null,null,"2000-08-08","2007-09-12"]
[7001,34033,"Performance Characterization of VoIMS over HSDPA\\EUL channels","VoIMS-PCVoIMS",1,"Rel-7","S4","2005-03-15","2007-12-06",1,"SP-050089","-","Alcatel-Lucent","mcgowan@alcatel-lucent.com","-",26.934999999999999,null,null,null,null,"2005-03-21","2008-01-10"]
[7004,32096,"   Stage 2 on Session Continuity: covered by SAE","WLAN2",2,"Rel-7","S2","2005-06-07","2005-06-07",1,"-","-","-","-","Acronym changed from \"WLAN2, WLAN-SC\"","-",null,null,null,null,"2005-06-07","2015-03-24"]
[7008,11064,"      CT1 aspets for WLAN-PNA","WLANPNA-st3",3,"Rel-7","C1","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29",24.234000000000002,null,null,null,null,"2005-12-22","2006-05-31"]
[7011,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[7014,14028,"   Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking","WLANQOS",2,"Rel-7","C4","2006-09-22","2007-03-09",1,"CP-060418","-","Huawei","zhang.peng@huawei.com","CP#33 approved WID","29.234, 23.008",null,null,null,null,"2006-10-11","2008-07-18"]
[7018,50558,"   LCS Enhancements related to Location-Based Services","LCS3-LBS",2,"Rel-7","GP","2005-01-03","2007-08-31",1,"GP-050265","-","SiRF","kjudge@sirf.com","-","43.059, 44.031, 48.008, 49.031",null,null,null,null,"2005-02-01","2008-07-02"]
[7021,20012,"   Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications","LCS3-UEPos-UTDOA",2,"Rel-7","R2","2004-09-15","2007-12-17",1,"RP-040387","RP-070797","TruePosition","Robert Gross (rgross@polariswireless.com)","-","25.305, 25.453, new 25.111",null,null,null,null,"2004-09-27","2008-07-02"]
[7022,31052,"   LCS for 3GPP Interworking WLAN","LCS3-IWLAN",2,"Rel-7","S1,S2","2004-06-28","2007-03-02",1,"SP-060291","-","Telcordia","Mike Loushine","-","-",null,null,null,null,"2004-08-30","2010-08-31"]
[7025,340007,"      Stage 2 for LCS architecture for I-WLAN","LCS3-IWLAN",3,"Rel-7","S2","2006-10-23","2007-03-02",1,"SP-060818","-","LG Electronics","dhshim@lge.com ; phede@lge.com","-","23.234, 23.271, 23.167",34,null,null,null,"2006-02-16","2011-08-15"]
[7028,340041,"   Stage 1 of MBMSE","MBMSE",2,"Rel-7","S1","2005-07-11","2005-12-08",1,"SP-050389","-","China Mobile","liuhongyfw@chinamobile.com","-","22.146, 22.246, 22.228",34,null,null,null,"2005-06-20","2008-04-15"]
[7032,340046,"   MBMS Mz interface","MBMSMz",2,"Rel-7","C3","2006-12-04","2007-11-30",1,"CP-070109","-","Huawei","Deng Tingting (ttdeng@huawei.com)","-",29.061,34,null,null,null,"2007-03-08","2008-07-21"]
[7035,400059,"   Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement","MBMSE-RANPhysLCRTDD_UEConTest",2,"Rel-7","R5","2008-05-30","2009-09-18",1,"RP-080318","RP-090715","CATT","chenxiaozhong@datangmobile.cn","RP#45 completed","34.108, 34.123-1",40,21,null,null,"2008-06-03","2009-09-11"]
[7039,50551,"   Stage 1/2 for Towards AGNSS Concept","AGNSS",2,"Rel-7","S1,S2","2007-02-16","2007-02-16",1,"SP-040681","-","Alcatel","richard.couty@space.alcatel.fr","-","22.071, 23.271",null,null,null,null,"2012-05-21","2012-05-21"]
[7042,50581,"A-GPS Minimum Performance","GAGR",1,"Rel-7","G1,G3","2006-04-28","2007-08-31",1,"GP-060834","-","Spirent","richard.catmur@spirentcom.com ","-","45.005, 51.010",null,null,null,null,"2006-05-03","2007-09-12"]
[7045,43008,"   Alignment with requirements regarding USSD usage","USSD-USIM",2,"Rel-7","C6","2004-03-05","2005-08-12",1,"TP-040069","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","31.111, 31.115, 31.130",null,null,null,null,"2004-09-02","2011-09-01"]
[7046,31063,"Combinational Services ","CSICS",1,"Rel-7","S1,S2,C1,S4","2005-01-17","2006-03-06",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-","-",null,null,null,null,"2004-12-17","2008-07-02"]
[7050,34031,"   Stage 3 for codec aspects","CSICS-Codec",2,"Rel-7","S4","2005-03-15","2005-12-07",1,"SP-050091","-","Ericsson","Per.Frojdh@ericsson.com","-","26.141, 26.235",null,null,null,null,"2005-03-22","2008-07-02"]
[7053,14017,"   CAMEL Trunk Originated Trigger Detection Points","CamelR7",2,"Rel-7","C4","2004-12-17","2005-12-05",1,"NP-040550","-","Nortel","David Hutton (dhutton@nortel.com)","-","-",null,null,null,null,"2004-12-17","2008-07-18"]
[7057,31061,"   Stage 1 for Enhancements of VGCS for public authority officials","EVGCS",2,"Rel-7","S1","2004-08-27","2004-08-27",1,"SP-040304","-","Siemens","joerg.swetina@neclab.eu","Voice Group Call Service","42.068, 43.068",null,null,null,null,"2004-08-30","2006-09-19"]
[7060,14022,"      CT4 aspects of EVGCS","EVGCS",3,"Rel-7","C4","2004-08-27","2006-03-10",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-",29.001999999999999,null,null,null,null,"2005-09-14","2007-03-08"]
[7064,32090,"   Stage 2 modifications for VGCS improvements","IVGCS",2,"Rel-7","C1","2005-12-01","2007-03-14",1,"NP-050141","-","T-Mobile","kurt.bischinger@t-mobile.at","-",43.067999999999998,null,null,null,null,"2005-03-22","2007-03-08"]
[7067,14023,"      Deleted - CT4 aspects of IVGCS","IVGCS-St3-c4",3,"Rel-7","C4","2007-03-09","2007-03-09",1,"NP-050141","-","T-mobile","-","CT4#33 stage 2 solution is still open. ",29.001999999999999,null,null,"CP-35",null,"2005-09-14","2007-03-29"]
[7070,31072,"      Service Requirements for OSA Service Broker","OSA7",3,"Rel-7","S1","2005-03-15","2005-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-",22.126999999999999,null,null,null,null,"2005-03-22","2006-02-16"]
[7071,43011,"      Stage 2 OSA API Service Brokering","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","AePONA","damian.oneill@aepona.com","-",23.198,null,null,null,null,"2005-03-22","2012-07-26"]
[7074,7018,"      Parlay X Message Broadcast Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-15, 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[7077,340001,"      Parlay-X Device Capabilities and Configuration","OSA7",3,"Rel-7","C5","2006-10-26","2007-06-08",1,"CP-070200","-","Telenor","-","-","29.199-18, 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[7081,31053,"Selective Disabling of UE Capabilities","SDoUE",1,"Rel-7","S1,S2,C1","2005-01-24","2007-06-15",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06","-",null,null,null,null,"2004-08-30","2008-07-17"]
[7084,7036,"   Stage 3 of SDoUE","SDoUE",2,"Rel-7","C1","2006-03-10","2007-06-15",1,"CP-070121","-","Ericsson","christian.herrero@ericsson.com","-",24.305,null,null,null,null,"2006-03-22","2008-07-17"]
[7088,25048,"Network selection enhancements (NSP) - UE Conformance Testing","NSP-CR_UEConTest",1,"Rel-7","R5","2007-06-01","2008-12-05",1,"RP-080135","RP-080819","Nokia","jarkko.hellsten@nokia.com","RP#42 completed. Testing for Feature UID_7041 (NSP-CR)","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2008-12-09"]
[7091,11048,"   Stage 3 CN aspects of ACBOP","ACBOP",2,"Rel-7","C1","2005-06-06","2006-01-31",1,"-","-","-","-","-",24.007999999999999,null,null,null,null,"2004-09-02","2008-07-15"]
[7094,50117,"   Deleted - Extra ACBOP information in GERAN","ACBOP",2,"Rel-7","GP","2006-09-08","2006-09-08",1,"-","-","-","-","-",44.018000000000001,null,null,"RP-33",null,"2004-04-14","2006-07-20"]
[7095,32074,"System enhancements for Fixed Broadband access to IMS","FBI",1,"Rel-7","S2,S3,S5,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"SP-060145","-","-","-","-","-",null,null,null,null,"2003-06-09","2004-10-21"]
[7098,11050,"      Protocol impact of FBI for TISPAN R1","-",3,"Rel-7","S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","-",null,null,null,null,"2004-09-03","2006-02-16"]
[7102,14020,"         CT4 aspects of FBI for TISPAN R1","FBI-TIS1-st3-c4",4,"Rel-7","C4","2006-01-13","2007-03-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","CT4#32: a set of CRs on FBI for cable labs",29.228999999999999,null,null,null,null,"2004-09-03","2007-03-08"]
[7105,7003,"      Stage 1,2 of FBI for PacketCable","-",3,"Rel-7","S2","2006-02-01","2006-12-15",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","-","22.228, 23.228",null,null,null,null,"2006-02-16","2006-09-19"]
[7108,32081,"Support of SMS over generic 3GPP IP access","SMSIP",1,"Rel-7","S2,C4,C1","2004-10-14","2007-06-14",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID (removed MMS)","-",null,null,null,null,"2004-10-14","2008-07-18"]
[7111,310001,"   Stage 3 for SMSIP","SMSIP-St3",2,"Rel-7","C4,C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","-",null,null,null,null,"2006-04-13","2008-07-15"]
[7116,32103,"   Stage 2 for PCC","-",2,"Rel-7","S2","2005-07-04","2006-09-15",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.",23.202999999999999,null,null,null,null,"2005-07-01","2008-07-18"]
[7119,13029,"   Gx reference point for Policy and Charging Control","PCC-Gx",2,"Rel-7","C3","2005-12-02","2007-11-30",1,"CP-060434","-","Siemens","Thomas.Belling@nsn.com","-","29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208)",null,null,null,null,"2005-12-13","2008-07-18"]
[7120,13030,"   Rx reference point for PCC CT3 aspects","PCC-Rx",2,"Rel-7","C3,C1","2005-12-02","2007-11-30",1,"CP-060435","-","Ericsson","j.javier.pastor@ericsson.com","WID approved at CP#30, Revised at CP#31, Revised at CP#33","-",null,null,null,null,"2005-12-13","2008-07-18"]
[7123,32091,"Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC",1,"Rel-7","S2,S1,S5,C1,C4","2004-12-31","2007-06-15",1,"SP-060292","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","WID approved SP#27¦updated SP#28¦updated SP#32","-",null,null,null,null,"2005-06-07","2008-07-21"]
[7127,35079,"   SA5 Charging for Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC-CH",2,"Rel-7","S5","2006-03-17","2007-06-14",1,"SP-060292","-","Orange","alain.bibas@orange-ft.com","03/2006 SP#31 WID approved","32.250, 32.260",null,null,null,null,"2006-03-20","2008-07-21"]
[7130,14027,"      CT4 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC-St3-c4",3,"Rel-7","C4","2006-06-09","2007-03-09",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-",23.003,null,null,null,null,"2005-10-04","2008-07-21"]
[7133,320002,"   Deleted - Study on Stage 2 for One Tunnel solution","OPTUNEL-Study",2,"Rel-7","S2","2006-03-27","2006-09-15",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","TR for Info SP-33. SP-34: S2 Report intention to discontinue TR",23.809000000000001,null,null,"SP-34",null,"2004-08-30","2008-07-15"]
[7137,340014,"   Stage 2 of CStermS","-",2,"Rel-7","S2","2006-06-08","2007-03-02",1,"SP-060437","-","Samsung","Osok Song","-",23.279,34,null,null,null,"2007-01-05","2008-07-17"]
[7140,33022,"Liberty Alliance and 3GPP Security Interworking","LibSec",1,"Rel-7","S3","2005-03-10","2006-11-30",1,"SP-050145","-","Nokia","Silke.Holtmanns@nokia.com","WID approved SP#27.",33.979999999999997,null,null,null,null,"2005-03-24","2008-07-16"]
[7143,33026,"Lawful Interception in the 3GPP Rel-7 architecture","LI-7A",1,"Rel-7","S3","2005-06-28","2005-12-08",1,"SP-050237","-","BMWI","berthold.wilhelm@regtp.de","-","33.106, 33.107, 33.108",null,null,null,null,"2005-06-20","2008-07-16"]
[7144,33028,"Key establishment between a UICC and a terminal","KeyEstUTerm",1,"Rel-7","S3","2005-12-07","2006-09-28",1,"SP-050780","-","Gemalto","mireille.pauliac@gemplus.com","-",33.11,null,null,null,null,"2005-12-12","2008-01-10"]
[7147,732031,"   HTTPS connection between a UICC and a NAF","SEC7-HSUN",2,"Rel-7","S3,C1","2005-09-12","2005-09-12",1,"SP-050573","-","Gemalto","JSeif@axalto.com, mireille.pauliac@gemplus.com","-","33.918, 33.222, 24.109",null,null,null,null,"2005-11-04","2008-07-16"]
[7151,310004,"      SA3 aspects of SEC7-NDS-TCAPsec","SEC7-NDS-TCAPsec-SA3",3,"Rel-7","S3","2005-09-12","2006-03-10",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-",33.204000000000001,null,null,null,null,"2005-11-04","2008-07-16"]
[7154,7043,"Interoperability between VGCS/VBS and A/Gb flexibility","VGCSFlex",1,"Rel-7","C1,C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","Voice Group Call Service","-",null,null,null,null,"2006-03-22","2008-07-21"]
[7157,13023,"DIAMETER on the GGSN Gi interface","DIAMGi",1,"Rel-7","C3","2004-09-10","2006-12-08",1,"CP-060431","-","Vodafone","Nico.Gabriele@vodafone.com","-",29.061,null,null,null,null,"2005-01-18","2008-07-15"]
[7161,14012,"Mp (MRFC - MRFP) interface","Mp",1,"Rel-7","C4,C1","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-","-",null,null,null,null,"2003-01-13","2008-07-15"]
[7164,320009,"   Procedures description","Mp-PROCc4",2,"Rel-7","C4","2006-06-02","2007-03-09",1,"CP-070246","-","Huawei","Chencheng@huawei.com","-",23.332999999999998,null,null,null,null,"2006-06-21","2008-07-15"]
[7165,14021,"   Stage 3 for Mp (MRFC - MRFP) interface","Mp-St3c4",2,"Rel-7","C4","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-",29.332999999999998,null,null,null,null,"2003-01-13","2008-07-15"]
[7168,743009,"ISIM API for Java Card","APIJAVA",1,"Rel-7","C6","2005-03-14","2007-07-27",1,"CP-050145","-","Sun","Sebastian Hans","-","31.103, 102 241",74,38,null,null,"2005-11-04","2007-09-12"]
[7172,34032,"Dynamic and Interactive Multimedia Scenes","DIMS",1,"Rel-7","S4","2005-03-15","2007-06-07",1,"SP-050195","-","Streamezzo","gaelle.martin-cocher@streamezzo.com","-","26.140, 26.142, 26.234, 26.244, 23.346",null,null,null,null,"2005-03-21","2007-05-29"]
[{"$f":"A7176+1","v":7176},34036,"End-to-End Multimedia Services Performance Metrics","E2EMSPM",1,"Rel-7","S4","2005-09-28","2007-03-15",1,"SP-050433","-","China Mobile","zhangyanyf@chinamobile.com","-",26.943999999999999,null,null,null,null,"2005-10-04","2007-03-08"]
[7179,35042,"   Rel-7 Network Infrastructure Management","OAM7-NIM",2,"Rel-7","S5","2005-09-02","2007-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2005-06-17","2007-03-29"]
[7182,35047,"      Network Management (NM) Itf-N performance criteria","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050305","-","China Mobile","-","-",32.811,null,null,null,null,"2005-06-17","2007-06-22"]
[7186,35052,"      Partial suspension of Itf-N during maintenance/testing (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050310","-","Siemens","-","-","32.381/2/3/5",null,null,null,null,"2005-06-17","2007-06-22"]
[7189,35064,"      Backward and Forward Compatibility of IRP systems","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050630","-","Ericsson ","-","-",32.154000000000003,null,null,null,null,"2005-09-16","2007-06-22"]
[7190,35071,"      Repeater Network Resource Model (NRM) definition","-",3,"Rel-7","S5","2006-02-13","2006-12-07",1,"SP-050731","-","China Mobile","-","-","32.721/2/3/5",null,null,null,null,"2005-11-24","2007-03-29"]
[7193,35043,"   Rel-7 Performance Management","OAM7-PM",2,"Rel-7","S5","2005-09-02","2007-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2005-06-17","2007-03-29"]
[7196,35059,"      Add TDD specific counters in Performance measurement","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050317","-","CATT","-","-",32.405000000000001,null,null,null,null,"2005-06-17","2007-03-29"]
[7200,35039,"   Rel-7 Trace Management","OAM7-Trace",2,"Rel-7","S5","2005-09-02","2007-06-15",1,"SP-050628","-","Vodafone","-","-","-",null,null,null,null,"2002-11-08","2007-03-29"]
[7203,35063,"      IRP for Subscriber and Equipment Trace Management","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050629","-","Nokia","-","-","32.441, 32.442, 32.443, 32.445, 32.632, 32.633, 32.635 ",null,null,null,null,"2005-03-02","2007-06-22"]
[7207,320008,"   Alternate Charged Party (ACP) for IMS","CH7-IMS-ACP",2,"Rel-7","S5","2006-05-22","2007-06-14",1,"SP-060442","-","Lucent","njmazzarella@alcatel-lucent.com","-","32.240, 32.260, 32.298, 32.299",null,null,null,null,"2006-05-22","2007-06-22"]
[7210,21006,"   MIMO - Physical layer","MIMO-Phys",2,"Rel-7","R1","2003-09-12","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037","25.211, 25.212, 25.213, 25.214, 25.215, 25.221",null,null,null,null,"2003-03-27","2008-06-24"]
[7213,24008,"   MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing","MIMO-RF",2,"Rel-7","R4","2003-12-12","2007-09-17",1,"RP-030192","RP-070531","Alcatel-Lucent","ngm@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070531","-",null,null,null,null,"2003-03-27","2008-06-24"]
[7214,25036,"   UE Conformance Testing for Multiple Input Multiple Output antennas (MIMO)","MIMO-UEConTest",2,"Rel-7","R5","2007-03-09","2008-03-07",1,"-","-","Qualcomm","svora@qualcomm.com","BB place holder for a number of RAN5 Tasks","-",null,null,null,null,"2007-03-19","2010-06-16"]
[7217,20060,"   Extended UMTS 1.7/2.1 GHz","RInImp-UMTS1721Ext",2,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060180","RP-060681","Ericsson","johan.skold@ericsson.com","RP#34 completed. Introduction of Band X (Extended UMTS 1.7/2.1 GHz) in 25.307","25.806, 25.101, 25.104, 25.133, 24.141, 25.331, 25.306, 25.307, 25.423, 25.461, 25.463, 34.121",null,null,null,null,"2006-03-21","2010-07-27"]
[7220,20025,"   UMTS 2.6 GHz TDD","RInImp-UMTS2600TDD",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040553","RP-050661","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#30 completed","25.102, 25.105, 25.113, 25.123, 25.142, 25.331, 25.942, 25.306, 25.307, 34.122, 34.124",null,null,null,null,"2005-01-04","2010-07-27"]
[7224,20045,"   Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2)","RInImp-HSPerf-Type3",2,"Rel-7","R4","2005-03-15","2005-03-15",1,"RP-050362","RP-060015","Cingular","Marc Grant","RP#27 completed",25.100999999999999,null,null,null,null,"2005-06-20","2010-07-27"]
[7227,7028,"      Additional minimum UE performance requirement for downlink physical channels in support of MTCH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-MBMS",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060183","RP-060678","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[7231,25025,"Rel-7 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-7","R5","2005-11-11","2008-09-12",1,"-","-","-","-","Linked to Feature UID_20028 (RInImp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[7234,25013,"   Conformance Test Aspects – Improved Performance of HSDPA Receiver type 3","RInImp-HSPerf-Type3_Test",2,"Rel-7","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","RP#34 completed","34.121, 34.108",null,null,null,null,"2006-03-21","2006-03-21"]
[7237,25028,"   Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz","RInImp-UEConTest_UMTS1721Ext",2,"Rel-7","R5","2006-12-01","2007-06-01",1,"RP-060676","RP-070312","Motorola","carolyn.taylor@motorola.com","RP#36 completed","34.108, 34.121-1, 34.121-2",null,null,null,null,"2006-09-20","2007-06-11"]
[7239,25040,"   Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of MTCGH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-UEConTest_RxDivMBMS",2,"Rel-7","R5","2007-06-01","2008-03-07",1,"RP-070381","RP-080056","Ericsson","leif.mattisson@ericsson.com","RP#39 completed","34.121-1, 34.121-2",null,null,null,null,"2006-09-20","2008-03-10"]
[7242,20031,"   Delay optimization for procedures applicable to CS and PS Connections","RANimp-DelayOpt",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050386","RP-060453","Nokia","juho.pirskanen@nokia.com","RP#33 completed","25.815, 25.321, 25.322, 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[7245,20046,"   Continuous connectivity for packet data users","RANimp-CPC",2,"Rel-7","R1","2005-03-14","2007-03-15",1,"RP-050870","RP-070033","Siemens","Joern.Krause@siemens.com ","RP#35 completed","25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133",null,null,null,null,"2005-10-05","2010-07-27"]
[7249,340038,"   64QAM for HSDPA (FDD)","RANimp-64QamDownlink",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070223","RP-070287","Ericsson","Johan.Bergman@ericsson.com","RP#36 completed","25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141",null,null,null,null,"2006-10-06","2010-07-27"]
[7252,20066,"   Interface to control Tower Mounted Amplifiers (TMAs)","RANImp-TMA",2,"Rel-7","R3,S5","2006-06-02","2007-06-15",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[7256,25021,"   Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink","RANimp-UEConTest_EDCHTDH",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060484","RP-080536","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7259,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7262,20014,"7.68 Mcps TDD option","VHCRTDD",1,"Rel-7","R1,R2,R3,R4,R5","2004-09-15","2007-09-14",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","-",null,null,null,null,"2004-09-27","2010-07-27"]
[7263,20015,"   VHCRTDD: Stage 2","VHCRTDD-Stage2",2,"Rel-7","R1","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed",25.202000000000002,null,null,null,null,"2004-09-27","2010-07-27"]
[7266,20018,"   VHCRTDD: UTRAN Iub/Iur Protocol Aspects","VHCRTDD-IurIub",2,"Rel-7","R3","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Peter Legg (plegg@ipwireless.com)","RP#31 completed","25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435",null,null,null,null,"2004-09-27","2010-07-27"]
[7270,20036,"   EDCHTDD: Stage 2","EDCHTDD-Stage2",2,"Rel-7","R2","2005-03-15","2006-06-15",1,"-","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7273,20039,"   EDCHTDD: UTRAN Iub/Iur Protocol Aspects","EDCHTDD-IurIub",2,"Rel-7","R3","2005-03-15","2006-09-15",1,"-","RP-060462","Interdigital","jim.miller@interdigital.com","RP#33 completed","25.401, 25.420, 25.423, 25.427, 25.430, 25.433, 25.435",null,null,null,null,"2005-03-15","2010-07-27"]
[7276,20056,"   1.28 Mcps TDD Enhanced Uplink: Physical Layer","LCRTDD-EDCH-Phys",2,"Rel-7","R1","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Ke Wang ","RP#35 completed","25.201, 25.221, 25.222, 25.223, 25.224, 25.225",null,null,null,null,"2006-03-21","2010-07-27"]
[7280,350146,"   1.28 Mcps TDD Enhanced Uplink - UE Conformance Testing","LCRTDD-EDCH-UEConTest",2,"Rel-7","R5","2007-09-20","2008-09-12",1,"RP-070724","RP-080539","CATT","chenxiaozhong@datangmobile.cn","RP#41 completed","34.108, 34.122, 34.123-1/2/3",null,null,null,null,"2006-03-21","2010-07-27"]
[7283,50119,"Lower 700 MHz Inclusion in the GERAN Specifications","GSM710",1,"Rel-7","GP","2005-01-03","2006-06-30",1,"GP-050543","-","UTC","dcotton@mtview.union-tel.com","-","-",null,null,null,null,"2005-02-01","2006-09-19"]
[7286,53084,"      G1 aspects of GSM710","-",3,"Rel-7","G1","2005-08-31","2006-06-30",1,"-","-","-","-","-",51.021000000000001,null,null,null,null,"2005-09-12","2006-07-20"]
[7287,55094,"      G3 aspects of GSM710","-",3,"Rel-7","G3new","2005-08-31","2006-06-30",1,"-","-","-","-","-",51.01,null,null,null,null,"2005-12-20","2006-07-17"]
[7290,51137,"   Definition of radio resource management functionality for Support of Conversational Services in A/Gb mode via the PS domain","SCSAGB-RRM",2,"Rel-7","G1","2005-04-08","2007-08-31",1,"GP-061502","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,null,null,"2005-04-21","2008-01-10"]
[7294,50565,"Addition of new frequency band to GSM (T-GSM810)","TGSM810",1,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-050945","-","Huawei","chende@huawei.com","-","45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060, 51.010-1, 51.021",null,null,null,null,"2005-04-21","2007-05-29"]
[7298,50567,"Handover of dedicated and shared resources while in Dual Transfer Mode","HODSRDTM",1,"Rel-7","GP","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","GP#30 completed. Started at GP#24","-",null,null,null,null,"2005-04-21","2006-09-19"]
[7301,53083,"   Deleted - BTS conformance testing","HODSRDTM-BTStest",2,"Rel-7","G1","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","Stopped, no work done. 12/2008 Marked as stopped (\"deleted\")",51.026000000000003,null,null,"GP-32",null,"2005-04-21","2008-12-15"]
[7305,50573,"   Test Scenarios for Mobile Station Receive Diversity, DARP Phase II ","MSRD2-TestSc",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060117","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",45.005000000000003,null,null,null,null,"2005-11-21","2007-03-08"]
[7308,51139,"   Downlink Dual Carrier Stage 2","GDCDL-Stage2",2,"Rel-7","G1","2006-01-20","2006-06-30",1,"GP-060484","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#30 completed","43.055, 43.064",null,null,null,null,"2006-01-24","2009-04-01"]
[7309,52142,"   Downlink Dual Carrier Stage 3","GDCDL-Stage3",2,"Rel-7","G1","2006-01-20","2007-08-31",1,"GP-060485","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#35 completed","24.008, 44.018, 44.060, 45.001, 45.002, 45.005, 45.008",null,null,null,null,"2006-01-24","2009-04-01"]
[7312,50582,"Latency Reductions","LATRED",1,"Rel-7","GP","2006-06-30","2007-08-31",1,"GP-061519","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021",null,null,null,null,"2006-07-05","2007-09-12"]
[7315,52147,"PS Handover between GERAN/UTRAN mode and GAN Mode","GUGAN",1,"Rel-7","G2","2006-06-30","2007-02-16",1,"GP-061349","-","Ericsson","John.Diachina@Ericsson.com","GP#33 completed","43.318, 44.318, 43.129, 25.306, 24.008, 44.060, 25.331, 51.010",null,null,null,null,"2006-07-05","2008-12-15"]
[7319,52149,"   Layer 2/3 Support for HUGE","HUGE-Layer23",2,"Rel-7","G2","2006-09-08","2007-08-31",1,"GP-061904","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#35 completed","24.008, 44.018, 44.060",null,null,null,null,"2006-09-13","2008-12-15"]
[7322,53087,"   MS Conformance Test for HUGE","HUGE-Mstest",2,"Rel-7","G3new","2006-09-08","2011-05-20",1,"GP-061906","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#50 completed",51.01,null,null,null,null,"2006-09-13","2011-05-21"]
[7325,51145,"   Stage 3 for REDHOT","REDHOT-Stage3",2,"Rel-7","G1","2006-11-17","2008-05-16",1,"GP-062490","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#38 completed","24.008, 44.018, 44.060, 45.001, 45.002, 45.003, 45.004, 45.005, 45.008",null,null,null,null,"2006-11-20","2008-12-15"]
[7329,25030,"Test - (Small) Technical Enhancements and Improvements for Rel-7","TEI7_Test",1,"Rel-7","R5","2006-06-02","2007-11-28",1,"-","-","-","-","-","-",null,null,null,null,"2010-05-26","2010-05-26"]
[7332,32115,"   Deleted - PS domain aspects to support IMS Emergency sessions","-",2,"Rel-7","S2","2006-06-23","2006-06-23",1,"SP-050604","-","Nokia","curt.c.wong@nokia.com","Approved at SP#29","23.867, 23.abc, 23.060, 23.002, 23.271",null,null,"SP-30",null,"2005-03-22","2005-12-22"]
[7333,32005,"Deleted - IMS Local services","IMSLocal",1,"Rel-7","S2","2006-01-06","2006-01-06",0.99,"-","-","-","-","-",23.228000000000002,null,null,"SP-28",null,"2001-10-08","2002-05-30"]
[7336,32078,"Deleted - IMS Phase 3","-",1,"Rel-7","S2","2006-01-06","2006-01-06",1,"-","-","-","-","-","-",null,null,"SP-25",null,"2004-09-08","2004-09-09"]
[7339,42003,"Deleted - Stage 3 - Common objects","-",1,"Rel-7","C4","2005-08-08","2005-08-08",1,"TP-020275","-","-","-","No progress in CN4#26. This have to be moved to Rel-7. It was deleted from WID",24.241,null,null,"SP-27",null,"2001-10-09","2005-03-09"]
[7343,31055,"Study on Combining CS calls and IMS sessions","IRTSD-CS_IMS",1,"Rel-7","S1","2004-06-28","2005-03-17",1,"SP-040467","-","TeliaSonera","robert.frank@teliasonera.com","-",22.978999999999999,null,null,null,null,"2004-08-30","2010-07-27"]
[7346,31073,"Study on Network Selection Principles","NetSel",1,"Rel-7","S1","2005-03-15","2005-12-08",1,"SP-050227","-","O2","chris.friel@O2.com","Spin-off Feature Network selection enhancements (NSP-CR) UID_7041",22.811,null,null,null,null,"2005-03-22","2008-06-27"]
[7349,32073,"Study on Enhancement of E2E QoS","QoS7",1,"Rel-7","S2","2004-06-28","2005-09-15",1,"SP-040326","-","Huawei","Robert Jaksa","-",23.802,null,null,null,null,"2004-08-30","2008-06-30"]
[7353,7034,"Study on Bandwidth Saving at Nb Interface with IP transport","BSNbIP",1,"Rel-7","C3","2006-03-10","2007-03-09",1,"CP-060438","-","Siemens","Thomas.Belling@siemens.com","Moved to FS at CT32 (in line with slides)",29.814,null,null,null,null,"2006-03-20","2010-07-27"]
[7356,7050,"Study on using M2PA in 3GPP network ","FS-M2PA",1,"Rel-7","C4","2006-03-22","2007-06-08",1,"CP-060698","-","China Mobile","zhaoyuyi@chinamobile.com","-",29.800999999999998,null,null,null,null,"2006-03-22","2008-07-01"]
[7359,330003,"   CT3 aspects of NcSIP","-",2,"Rel-7","C3","2006-05-15","2007-09-14",1,"CP-070034","-","Ericsson","ragnar.huslende@ericsson.com","-",29.802,null,null,null,null,"2006-09-21","2008-07-01"]
[7361,20034,"Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph","RANFS-HSTrains",1,"Rel-7","R4","2005-03-15","2006-06-15",1,"RP-050146","RP-060412","Vodafone","Mike.vogel@vodafone.com,tim.frost@vodafone.com","RP#32 (Jun 2006) completed. SR in RP-060412","none",null,null,null,null,"2005-03-15","2008-06-23"]
[7364,20051,"Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN","RANFS-MBMSImp",1,"Rel-7","R2","2005-12-15","2006-12-15",1,"RP-050746","RP-060692","LG Electronics","leego@lge.com","RP#34 completed",25.905000000000001,null,null,null,null,"2005-12-15","2012-07-26"]
[{"$f":"A7368+1","v":7368},330013,"Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met","FSUEPow",1,"Rel-7","R4","2007-06-22","2007-06-22",1,"RP-060641","RP-070534","Nokia","Chris.callender@nokia.com, tiina.s.koskinen@nokia.com","RP#37 (Sep 2007) completed. SR in RP-070534",25.905999999999999,null,null,null,null,"2006-10-06","2008-06-23"]
[7371,31054,"Deleted - Study on IMS with real time services deployment","IRTSD",1,"Rel-7","S1","2004-06-28","2005-09-12",1,"SP-040465","-","-","-","-","-",null,null,"SP-30",null,"2004-08-30","2008-06-27"]
[7375,32029,"Deleted - Study on applicability of GALILEO for LCS","Galileo",1,"Rel-7","S2","2005-06-30","2005-06-30",1,"SP-020541","-","-","-","-","-",null,null,"SP-25",null,"2002-11-08","2004-09-08"]
[7378,32076,"Deleted - Study on Stage 2 (IMS services using CS bearers)","IRTSD-IMSCS",1,"Rel-7","S2","2004-06-28","2005-09-12",1,"SP-040479","-","Nortel","Mark Watson","SP-30: S2 has no intention for TR completion",23.899000000000001,null,null,"SP-30",null,"2004-08-30","2008-06-26"]
[7381,32112,"Deleted - Study on IMS enhancements and optimizations for real time communication.","IMS-RT",1,"Rel-7","S2","2005-10-10","2007-06-01",1,"SP-050492","-","Ericsson","stephen.terrill@ericsson.com","abandoned at 65%",23.818000000000001,null,null,"SP-35",null,"2006-02-16","2007-06-22"]
[7382,32117,"Deleted - Study on Terminating Session handling","CSIterm",1,"Rel-7","S2","2006-01-09","2006-12-29",1,"SP-050811","-","Samsung","-","SP#32 Jun 2006 Study abandoned => spin-off Implementation work UID_320029",23.818999999999999,null,null,"SP-32",null,"2005-12-20","2008-06-30"]
[7385,360009,"Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053)","RANFS-InterfCanc",1,"Rel-7","R4","2007-03-28","2007-03-28",1,"-","-","-","-","Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD)","-",null,null,"SP-38",null,"2007-06-21","2008-01-10"]
[7388,1216,"Rel-6 Improvements of Radio Interface","-",1,"Rel-6","R2,R4,R5","2000-08-14","2006-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2004-07-08"]
[7392,1476,"      FDD Base station classification","-",3,"Rel-6","R4","2000-08-14","2002-12-04",1,"-","-","Nokia","antti.toskala@nokia.com","-","25.104, 25.141",null,null,null,null,"2000-07-26","2004-07-08"]
[7395,24010,"   UMTS 1.7/2.1 GHz","RInImp-UMTS1721",2,"Rel-6","R4","2003-03-14","2003-03-14",1,"-","-","Nokia","jussi.numminen@NOKIA.COM","Introduction of UMTS1700/2100 (Band IV)","25.101, 25.104, 25.133, 25.141, 25.307, 25.331",null,null,null,null,"2003-10-02","2009-07-09"]
[7399,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7402,3,"Rel-6 RAN Feasibility Studies","-",1,"Rel-6","RP","2000-08-14","2005-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-07","2003-12-07"]
[7405,21000,"   FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD","RInImp-IfIsMLCR",2,"Rel-6","R1","2001-12-14","2003-09-19",1,"-","-","Samsung","Li Xiao Qiang (xqli@samsung.co.kr)","-",25.888000000000002,null,null,null,null,"2003-10-02","2004-07-08"]
[7406,21003,"   FS for the analysis of OFDM for UTRAN enhancement","RInImp-FSOFDM",2,"Rel-6","R1","2002-06-10","2004-06-14",1,"-","-","Nortel","Sarah Boumendil","-",25.891999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7409,24011,"   FS on Low Output Powers for general purpose FDD BSs","RInImp-FSLoPw",2,"Rel-6","R3","2003-06-13","2004-03-12",1,"-","-","Telefónica","Ana Burgos (burgos_a@tsm.es)","-",25.806999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7412,23006,"   Deleted - FS on the evolution of the UTRAN architecture","RANimp-FSEvo",2,"Rel-6","R3","2002-09-09","2004-12-14",1,"-","-","Nokia","woonhee.hwang@nsn.com, Antti.Toskala@nokia.com","Study Closed, work will continue within the FS on evolved UTRA and UTRAN","-",null,null,"RP-26",null,"2002-09-16","2005-01-13"]
[7416,20006,"   FDD Enhanced Uplink - Layer 2 and 3 Protocol Aspects","EDCH-L23",2,"Rel-6","R2","2004-03-15","2005-03-14",1,"-","-","Ericsson","Joakim Bergström ","-","25.301, 25.302, 25.306, 25.321, 25.331",null,null,null,null,"2004-03-18","2005-03-25"]
[7420,9,"Rel-6 RAN improvements","-",1,"Rel-6","RP,S5","2002-09-09","2005-03-14",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2000-03-31","2004-07-08"]
[7424,20013,"      HS-DPCCH ACK/NACK Enhancement","RANimp-RABSE-ACKNACK",3,"Rel-6","R1","2004-09-15","2004-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","Approved at RP#25 as RP-040390","25.212, 25.214, 24.331, 25.433",null,null,null,null,"2004-09-27","2005-03-25"]
[7427,20999,"   Beamforming Enhancements","RANimp-BFE",2,"Rel-6","R1","2003-09-19","2003-12-19",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","-","24.215, 25.423, 25.425, 25.433, 25.435",null,null,null,null,"2001-11-29","2004-07-08"]
[7430,23010,"   Remote Control of Electrical Tilting Antennas","RANimp-TiltAnt",2,"Rel-6","R3,S5","2003-03-14","2004-09-16",1,"-","-","Vodafone","Andreas.Hauser@vodafone.com","-","-",null,null,null,null,"2003-03-27","2004-04-14"]
[7431,23015,"      Tilting Antenna - RAN aspects","-",3,"Rel-6","R3","2003-03-14","2004-09-14",1,"-","-","Vodafone","Andreas.Hauser@vodafone.com","Finished at RP#25","25.460, 25.461, 25.462, 25.463",null,null,null,null,"2003-03-27","2004-10-13"]
[7434,32023,"Location Services enhancements 2","LCS2",1,"Rel-6","S2,S5,N4,R2,R4,R5,OMA","2001-01-15","2004-12-16",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-06-02"]
[7438,32001,"   Enhanced support for anonymity and user privacy","-",2,"Rel-6","S2,OMA","2002-07-08","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2001-09-19","2012-05-21"]
[7441,32025,"   Enhanced inter-GMLC interface","-",2,"Rel-6","S2,OMA","2002-06-24","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2001-09-19","2012-05-21"]
[7444,32012,"   Location Services support for IMS public identities","-",2,"Rel-6","S2,OMA","2003-02-24","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-01-24","2012-05-21"]
[7448,32050,"      Stage 2 for New area event for location service triggering reports","-",3,"Rel-6","S2","2002-06-03","2003-06-27",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[7451,20001,"   UE positioning for Location Services enhancements 2","LCS2-UEpos",2,"Rel-6","R2,R4,R5","2001-01-15","2004-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-16","2012-05-21"]
[7454,22002,"      Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods","LCS2-UEpos-FSBlank",3,"Rel-6","R2","2002-07-01","2003-09-19",1,"-","-","Cambridge Positioning Systems","david.bartlett@cursor-system.com","RP#38 Work stopped","new 25.894",null,null,"RP-38",null,"2002-06-21","2012-05-21"]
[7455,2457,"      Deleted - UE positioning enhancements - other methods","LCS2-UEpos-enh",3,"Rel-6","R2","2003-09-26","2003-09-26",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","RP#24 Work stopped","-",null,null,"RP-24",null,"2004-10-19","2012-05-21"]
[7458,2026,"   Enhanced HE control of security (including positive authentication reporting)","-",2,"Rel-6","S3","2001-01-03","2003-09-25",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID S3-000490 (Enhanced home control of security by HE)",33.101999999999997,null,null,null,null,"2000-09-22","2011-08-08"]
[7462,33017,"   Network Domain Security; Authentication Framework (NDS/AF)","SEC1-NDS-AF",2,"Rel-6","S3","2002-02-15","2004-02-13",1,"SP-030108","-","Nokia","tommi.viitanen@nokia.com","SP#19 approved WID",33.81,null,null,null,null,"2003-03-27","2011-08-08"]
[7465,32021,"IMS Phase 2","IMS2",1,"Rel-6","S1,S2,S3,S5,NP,R5","2000-08-28","2007-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-25","2004-07-08"]
[7468,31025,"   IMS Group Management","IMSGM",2,"Rel-6","S1","2002-03-14","2004-12-08",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7472,11037,"   IMS Conferencing","-",2,"Rel-6","N1","2002-11-04","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[7475,31022,"   IMS Messaging","IMSM",2,"Rel-6","S1","2002-03-14","2005-12-30",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7476,31023,"      TR on support of messaging in the IMS","IMSM-TR",3,"Rel-6","S1","2002-03-14","2002-12-09",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","New 22.940",null,null,null,null,"2002-03-21","2010-09-07"]
[7481,60001,"      SIP/SIMPLE Instant messaging","-",3,"Rel-6","OMA","2004-01-01","2005-12-30",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040232","-",null,null,null,null,"2004-06-08","2005-03-25"]
[7483,32041,"      Stage 2 for add SIP cap (e.g. forking)","-",3,"Rel-6","S2","2002-11-11","2004-02-20",1,"-","-","-","-","-",23.228000000000002,null,null,null,null,"2003-02-27","2004-03-12"]
[7487,2048,"   Interworking between IMS and IP networks","IMS-CCR-IWIP",2,"Rel-6","N3","2000-08-28","2004-12-08",1,"NP-020091","-","BT","nigel.holland@bt.com","[DAB 14.02.02] - end date pushed back to March 2003","23.821, 29.061, 29.162",null,null,null,null,"2000-10-09","2003-01-13"]
[7490,11044,"      Interworking for IPv6 to IPv4 (SIP / SDP aspects)","-",3,"Rel-6","N1","2004-05-11","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-03-01","2004-09-08"]
[7493,14001,"   Mn interface (IM-MGW to MGCF) enhancements (CN4 Part)","IMS-CCR-Mn",2,"Rel-6","N4","2001-08-07","2004-09-01",1,"-","-","-","-","TISPAN issue is open","-",null,null,null,null,"2001-10-08","2005-03-09"]
[7497,35032,"   IMS charging","IMS2-CH",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"SP-030049","-","Ericsson","Patrik TEPPO ","SP#26 12/2004 completed",32.26,null,null,null,null,"2004-10-29","2006-01-13"]
[7500,32063,"3GPP Enablers for services like Push to Talk over Cellular (PoC)","PoC",1,"Rel-6","S2,S4,S5","2003-09-08","2005-06-09",1,"SP-030384","-","Ericsson","Shabnam Sultana","-","-",null,null,null,null,"2003-10-15","2004-07-08"]
[7501,32068,"   Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC)","-",2,"Rel-6","S2","2003-09-08","2004-11-30",1,"SP-030384","-","Ericsson","Shabnam Sultana","-",23.978999999999999,null,null,null,null,"2003-10-15","2004-12-06"]
[7504,35036,"   PoC charging","PoC-CH",2,"Rel-6","S5","2004-09-27","2005-06-09",1,"SP-050032","-","Siemens","Gerald.Goermer@nsn.com","SP#28 06/2005 completed",32.271999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[7507,32028,"   Stage 2 for Interoperability","-",2,"Rel-6","S2","2002-09-16","2003-09-30",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2",23.864000000000001,null,null,null,null,"2002-11-08","2004-07-08"]
[7511,31004,"   Stage 1 for Support of Push Services","-",2,"Rel-6","S1","2001-01-03","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2003-07-04"]
[7514,42010,"   Definition of service requirements for MMS6","MMS6-SR",2,"Rel-6","S1","2002-11-15","2003-12-19",1,"-","-","-","-","-",22.14,null,null,null,null,"2002-09-26","2004-03-12"]
[7517,42012,"   OMA dependencies","-",2,"Rel-6","OMA","2003-08-15","2005-04-29",1,"-","-","-","-","-","OMA specs",null,null,null,null,"2002-09-26","2005-03-25"]
[7521,42015,"   Deleted - FS Multiple MMS Relay/Server Architecture","-",2,"Rel-6","T2","2004-12-10","2004-12-10",1,"TP-030301","-","Telefónica Móviles","Juan Gorospe (gorospe_j@tsm.es)","originally it was intended to create a FS TR but most likely the work will become an Annex of 23.140","probably Annex to 23.140",null,null,"TP-26",null,"2003-12-01","2004-09-08"]
[7524,42007,"   MExE Run-Time Independent Framework Feasibility Study","MEXE6-RTIF",2,"Rel-6","T2","2002-03-08","2003-06-06",1,"TP-020086","-","Nokia Siemens Networks","balazs.bertenyi@nokia.com","-",22.856999999999999,null,null,null,null,"2002-03-21","2010-08-31"]
[7525,2062,"Subscription Management","SuM",1,"Rel-6","S5","2002-09-20","2005-03-17",1,"SP-040763","-","T-Mobile","istvan.aba@t-mobile.at","SP#27 03/2005 completed","32.140/1, 32.171/2/5, 32.803",null,null,null,null,"2000-10-09","2006-01-13"]
[7528,2502,"   Stage 2 for Presence Capability","-",2,"Rel-6","S2","2001-09-12","2002-09-20",1,"SP-010517","-","Nokia","balazs.bertenyi@nsn.com","-","23.002, 24.229, New 23.141",null,null,null,null,"2001-03-30","2011-08-09"]
[7531,34025,"   Media Codecs and Formats for IMS Messaging and Presence","PRESNC-COFIMP",2,"Rel-6","S4","2003-06-12","2005-12-07",1,"SP-030212","-","Nokia","harri.honko@nokia.com","-","26.141, 26.936",null,null,null,null,"2003-07-04","2006-01-13"]
[7535,50057,"   Feasibility study on A/Gb enhancements","AGbEnFS-FS",2,"Rel-6","G2","2002-08-30","2002-11-08",1,"GP-022565","-","Vodafone","jose-luis.carrizo@vodafone.co.uk","-","None",null,null,null,null,"2002-05-23","2009-11-18"]
[7538,50093,"      Outline of impact and feasibility of these building blocks and their different solutions","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2003-01-13","2009-11-18"]
[7542,50063,"Flexible Layer One for GERAN","FLOGER",1,"Rel-6","GP,S3","2000-01-03","2004-06-25",1,"GP-021018","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2003-09-16"]
[7546,51003,"      Multiplexing in 45.002","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7549,51006,"      Radio subsystem link control in 45.008 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7550,52071,"      Requirements in 44.004","-",3,"Rel-6","G2","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7553,52074,"      Modifications to RRC in 44.118 and 44.018","-",3,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[7556,55077,"   Deleted - GERAN MS Conformance test for the Flexible Layer One - DELETE","FLOGER-Msconf",2,"Rel-6","G4,G5","2004-02-06","2004-02-06",1,"GP-021022","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-27",null,"2002-05-23","2005-03-09"]
[{"$f":"A7560+1","v":7560},50041,"Uplink TDOA feasibility study","TDOAF",1,"Rel-6","GP","2001-11-30","2002-06-28",1,"GP-012794","-","TruePosition","Bob Gross (rlgross@trueposition.com)","-",45.811,null,null,null,null,"2001-12-10","2003-04-24"]
[7563,32002,"   Stage 2 for Multimedia Broadcast and Multicast Service","-",2,"Rel-6","S2","2001-09-24","2004-03-17",1,"SP-010516","-","-","-","-","-",null,null,null,null,"2001-09-19","2012-07-26"]
[7567,13015,"   Gmb interface for MBMS (CN3 part)","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"-","-","-","-","-",29.061,null,null,null,null,"2003-10-13","2012-07-26"]
[7570,31045,"   MBMS User Services","-",2,"Rel-6","S1,S4","2003-05-13","2006-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-30","2012-07-26"]
[7573,2481,"   Introduction of MBMS in RAN","MBMS-RAN",2,"Rel-6","R2,R4","2002-01-01","2005-09-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","-",null,null,null,null,"2001-03-20","2012-07-26"]
[7574,20022,"      Introduction of MBMS in RAN (physical & upper layers, access network interfaces)","-",3,"Rel-6","R2","2002-01-01","2004-12-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","25.346, 25.304, 25.321, 25.322, 25.323",null,null,null,null,"2004-09-27","2012-07-26"]
[7577,25014,"      RF/RRM Conformance Test Aspects – MBMS (FDD)","MBMS-RAN-RF_Test",3,"Rel-6","R5,T1","2006-06-02","2008-03-07",1,"-","-","Ericsson","leif.mattisson@ericsson.com","-","34.108, 34.109, 34.121-1, 34.121-2",null,null,null,null,"2002-02-28","2012-07-26"]
[7580,25011,"      Conformance Test Aspects – MBMS","MBMS_Test",3,"Rel-6","R5,T1","2006-03-10","2007-09-14",1,"-","-","Qualcomm","Shubhang Vora (svora@qualcomm.com)","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2012-07-26"]
[7584,52085,"      MBMS Re-synchronisation at cell change","-",3,"Rel-6","G2","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7587,50100,"      MBMS Resynchronization at cell change","-",3,"Rel-6","GP","2001-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7591,50090,"      GERAN specific changes to the Iu-ps interface for MBMS","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7594,53081,"      MBMS-GERAN - MS conformance tests","-",3,"Rel-6","G3new","2002-01-25","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7597,31007,"   Speech Enabled Services Based on Distributed Speech Recognition (DSR)","DSR",2,"Rel-6","S1","2001-10-08","2002-03-15",1,"SP-010581","-","Qualcomm","Dwilliams@qualcomm.com","-","22.977, 22.941, 23.207, 22.243",null,null,null,null,"2001-10-09","2004-03-12"]
[7598,32999,"   TR on Architectural impacts","-",2,"Rel-6","S2","2003-05-12","2004-03-02",1,"-","-","-","-","-",23.876999999999999,null,null,null,null,"2001-11-29","2004-07-08"]
[7601,11021,"   Deleted - SES codec negotiation at Session Description Protocol (SDP)","-",2,"Rel-6","N1","2003-06-04","2003-06-04",1,"-","-","-","-","Abandoned NP-23","-",null,null,"NP-23",null,"2004-10-20","2004-10-21"]
[7607,33009,"   Security aspects of GUP","-",2,"Rel-6","S3","2002-07-16","2003-09-18",1,"SP-030109","-","Lucent","Bradley Owen (bvowen@lucent.com)","SP#19 approved WID","33.102, 33.203, 33.210",null,null,null,null,"2002-11-08","2011-08-08"]
[7609,31011,"   Requirements for Digital Rights Management","-",2,"Rel-6","S1","2001-10-08","2002-06-13",1,"-","-","Openwave","nicholas.wood@openwave.com","-","-",null,null,null,null,"2001-10-11","2003-07-04"]
[7612,33001,"   Security for Digital Rights Management","-",2,"Rel-6","OMA","2002-06-17","2003-03-03",1,"-","-","-","-","SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17","-",null,null,null,null,"2001-10-11","2005-03-25"]
[7616,31035,"   Stage 1 for WLAN-UMTS Interworking Rel-6","WLAN-TS",2,"Rel-6","S1","2003-01-06","2004-06-11",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","-","22.101, 22.105",null,null,null,null,"2003-01-13","2004-06-08"]
[7619,14013,"   Stage 3 - CN4 aspects","WLAN-IW",2,"Rel-6","N4","2003-05-23","2004-09-01",1,"NP-030490","-","Nokia","raquel.rodriguez@nokia.com","WID approved at CN#19","29.234, 29.061",null,null,null,null,"2003-03-27","2005-03-09"]
[7622,11047,"   Stage 3 for scenario 3","-",2,"Rel-6","N1","2003-05-23","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-06-08","2005-03-09"]
[7623,35033,"   WLAN charging","WLAN-CH",2,"Rel-6","S5","2003-03-21","2005-09-22",1,"SP-030048","-","Nokia","Benni ALEXANDER ","-",32.252000000000002,null,null,null,null,"2004-10-29","2011-08-15"]
[7626,31016,"   Feasibility Study on Priority Service","PRIOR-FS",2,"Rel-6","S1","2002-06-14","2002-06-14",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-",22.95,null,null,null,null,"2002-02-27","2010-08-31"]
[7630,31019,"   Technical Report on Network Sharing ","NTShar-TR",2,"Rel-6","S1","2003-01-20","2003-12-19",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-",22.951000000000001,null,null,null,null,"2002-02-27","2009-11-10"]
[7633,11043,"   Network sharing - stage 3","-",2,"Rel-6","N1","2003-05-23","2004-12-08",1,"NP-040429","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","23.008, 23.122, 24.007, 24.008, 29.018",null,null,null,null,"2003-06-09","2009-11-10"]
[7636,32016,"QoS Improvements","QoS1",1,"Rel-6","S2,N3","2002-07-15","2004-12-08",1,"SP-010719","-","Nokia","-","-","23.107, 23.207, 23.221",null,null,null,null,"2002-01-24","2002-01-24"]
[7640,33002,"Subscriber certificates","SEC1-SC",1,"Rel-6","S3,S2,N1,N4,T3,OMA","2002-02-25","2004-12-08",1,"SP-010622","-","Nokia","valtteri.niemi@nokia.com","SP#14 approved WID","-",null,null,null,null,"2002-01-24","2011-08-08"]
[7643,14504,"   Stage 3 for Subscriber certificates","-",2,"Rel-6","N4,T3","2003-09-19","2004-11-30",1,"NP-030399","-","Nokia","Lauri Laitinen","Finished in CN4#26","23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111",null,null,null,null,"2003-10-15","2009-11-10"]
[7644,11049,"   Stage 3 Ua & Ub interfaces","-",2,"Rel-6","N1","2003-11-03","2004-12-08",1,"-","-","Nokia","-","-",24.109000000000002,null,null,null,null,"2004-03-01","2009-11-10"]
[7647,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[7650,15028,"   Policy management extensions","-",2,"Rel-6","N5","2002-10-31","2003-12-12",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-01-13","2005-01-13"]
[7654,15036,"   Framework Function for Federation","-",2,"Rel-6","N5","2003-02-03","2003-12-12",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-03-27","2005-01-13"]
[7657,50401,"Addition of frequency bands to GSM (TAPS)","TAPS",1,"Rel-6","GP","2002-06-28","2005-01-28",1,"GP-022072","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2005-03-09"]
[7660,54102,"   Deleted - Addition of frequency bands to GSM – Changes for conformance tests","TAPS-Conf",2,"Rel-6","G4","2002-06-28","2005-01-28",1,"GP-022074","-","Nokia","Torben Themsen","-","-",null,null,"GP-23",null,"2002-07-31","2005-03-09"]
[7664,51133,"      Requirements for streaming","-",3,"Rel-6","G1","2003-06-27","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7668,51136,"      Handover for Seamless support of streaming services in A/Gb mode","-",3,"Rel-6","G1","2000-01-03","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7669,52131,"   Reduction of service interruption times and packet loss during mobility procedures","-",2,"Rel-6","G2","2003-06-27","2005-06-17",1,"GP-022563","-","Vodafone","José Luis Carrizo Martínez","Completed at GERP#17","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7672,52135,"      PS Handover (within GERAN and between GERAN and UTRAN)","-",3,"Rel-6","G2","2003-06-27","2005-06-17",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7675,54132,"      Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode","-",3,"Rel-6","G4,G5","2003-12-19","2004-01-30",1,"GP-023424","-","Vodafone","José Luis Carrizo Martínez","Marked as stopped 10/2009","-",null,null,"GP-27",null,"2003-02-13","2009-10-13"]
[7679,35010,"Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM6",1,"Rel-6","S5","2002-09-12","2005-03-11",1,"SP-040766","-","-","-","SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4.","-",null,null,null,null,"2002-11-08","2005-01-13"]
[7682,35014,"   Network Infrastructure Management ","-",2,"Rel-6","S5","2002-09-12","2004-12-16",1,"SP-040789","-","Ericsson","thomas.tovinger@ericsson.com","SP#26 12/2004 completed","32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5",null,null,null,null,"2002-11-08","2011-02-21"]
[7685,23013,"      Subscriber and equipment trace in UTRAN","OAM-Trace-RAN",3,"Rel-6","R3","2003-06-06","2004-06-15",1,"-","-","Nortel","Yann Sehedi (sehedic@nortelnetworks.com)","-","25.413, 25.420, 25.423",null,null,null,null,"2003-07-04","2005-01-13"]
[7689,35024,"   Charging Data Record (CDR) file format and transfer","-",2,"Rel-6","S5","2003-03-21","2004-03-18",1,"-","-","-","-","SP#23 03/2004 completed",32.296999999999997,null,null,null,null,"2004-10-29","2006-01-13"]
[7692,35027,"   Online Charging System (OCS) architecture study","-",2,"Rel-6","S5","2003-03-21","2003-09-18",1,"-","-","-","-","SP#21 09/2003 completed",32.814999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[7693,35028,"   OCS: Applications and interfaces","-",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"-","-","-","-","SP#26 12/2004 completed",32.295999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[7696,35030,"      PS domain charging","-",3,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.250999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[7699,32030,"   Overall architectural aspects of IP flow based bearer level charging","CH-FBC",2,"Rel-6","S2,N3","2002-11-21","2005-03-11",1,"SP-040041","-","-","-","-",23.125,null,null,null,null,"2003-01-15","2004-07-08"]
[7703,13021,"      Rx interface for flow based charging","-",3,"Rel-6","N3","2004-02-02","2005-03-11",1,"NP-040339","-","Nortel","Javier Gonzalez Gallego","-",29.209,null,null,null,null,"2004-05-20","2005-03-25"]
[7706,43001,"      Rel-6 Java API Test specification","-",3,"Rel-6","T3","2002-03-20","2002-06-10",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-","-",null,null,null,null,"2002-05-30","2010-02-09"]
[7710,43004,"   Rel-6 USIM toolkit enhancements","USAT1-API-MULTOS",2,"Rel-6","T3","2000-09-25","2005-03-04",1,"-","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2002-11-29","2005-01-19"]
[7713,502033,"         Test specification for C SIM API","-",4,"Rel-6","T3","2001-01-01","2001-09-28",1,"TP-000155","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2000-09-14","2010-02-09"]
[7716,31039,"   Stage 1 for Packet Switched Streaming Services Rel-6","-",2,"Rel-6","S1","2002-11-18","2003-03-17",1,"SP-020685","-","Ericsson","-","2nd resp SA4",22.233000000000001,null,null,null,null,"2003-03-14","2009-11-13"]
[7717,34024,"   Stage 3 for Packet Switched Streaming Services Rel-6","PSSrel6-Stage3",2,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-020685","-","Ericsson","olle.franceschi@ericsson.com","TR tbc by Sept. 05","26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936",null,null,null,null,"2003-03-27","2009-11-13"]
[7720,34028,"3G-324M Improvements","3G-324MI",1,"Rel-6","S4","2004-03-16","2004-12-16",1,"SP-040067","-","Ericsson","bo.burman@ericsson.com","-","26.111, 26.911",null,null,null,null,"2004-03-02","2004-12-06"]
[7723,12007,"   Stages 2 and 3 for Enhancement of dialled service for CAMEL","-",2,"Rel-6","N2,N4","2003-03-28","2003-12-31",1,"NP-030153","-","Samsung","Richard Brook","-","23.008, 23.016, 23.018, 23.078, 29.002, 29.078",null,null,null,null,"2003-03-27","2009-11-13"]
[7729,50604,"      Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2004-12-06"]
[7731,50096,"Alignment between the test-regimes for GERAN capable MS","ALTERE",1,"Rel-6","G3new","2003-08-29","2005-09-02",0.99,"GP-032236","-","Ericsson","anthony.toubassi@sonyericsson.com ","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[7735,50101,"Downlink Advanced Receiver Performance","DARP",1,"Rel-6","GP","2003-11-21","2005-09-02",1,"GP-041966","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7738,50104,"      Performance requirements in 45.005 for DARP for GMSK modulated voice services","DARP-GMSK-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7741,50107,"      Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7742,50108,"      Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-LC",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7745,50109,"Reduction of PS service interruption in Dual Transfer Mode","PSintDTM",1,"Rel-6","G2","2003-11-21","2005-06-24",1,"GP-032548","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7749,50113,"   Deleted - MS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfMS",2,"Rel-6","G3new","2004-06-25","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2008-12-12"]
[{"$f":"A7752+1","v":7752},31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[7755,32072,"   Deleted - Stage 2 description on Redial","-",2,"Rel-6","S2","2004-05-03","2004-12-16",1,"SP-040331","-","Vodafone","chris.pudney@vodafone.com","-","-",null,null,"SP-26",null,"2004-05-20","2005-03-09"]
[7759,13024,"Reorganisation of CS Data Specifications","CSData",1,"Rel-6","N3","2004-11-19","2004-12-08",1,"NP-040563","-","Siemens","Thomas.Belling@nsn.com","Created at TSG#27 as 100 % complete","23.910, 29.007, New 23.202",null,null,null,null,"2005-03-02","2005-03-09"]
[7762,50554,"   GAAI – Stage 2","GAAI-Stage2",2,"Rel-6","GP","2004-08-27","2005-04-08",1,"-","-","Ericsson","jari.vikberg@ericsson.com","-",43.317999999999998,null,null,null,null,"2004-10-15","2005-03-25"]
[7765,50559,"Support of PS Handover for GERAN A/Gb mode","SPSHAGB",1,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051160","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB- Originally Started Nov 2003 as GP-030443","-",null,null,null,null,"2005-04-20","2006-01-13"]
[7766,50560,"   Stage 2 for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-Stage2",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051161","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-Stage2",43.128999999999998,null,null,null,null,"2005-04-20","2006-01-13"]
[7769,33018,"Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces","-",1,"Rel-6","S3","2003-07-03","2003-12-26",1,"SP-030341","-","Toshiba","Raziq Yaqub (ryaqub@tari.toshiba.com)","SP#20 approved WID",33.817,null,null,null,null,"2003-07-25","2011-08-09"]
[7773,31029,"Deleted - Study of Feature Interactions Requirements","FINTER",1,"Rel-6","S1","2004-09-16","2004-09-16",1,"SP-020578","-","-","-","SP#25 stopped","-",null,null,"SP-25",null,"2004-10-20","2010-03-02"]
[7776,50501,"   Deleted - Creation of a TR","SCSAGB-TR",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030444","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","-","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[7779,50504,"   Deleted SCSAGB-RRM - Definition of radio resource management functionality","-",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030447","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[7783,0,"--- RELEASE 5 ---","-",1,"Rel-5","NP,GP,RP,SP,TP","2000-01-03","2001-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7786,2476,"High Speed Downlink Packet Access","HSDPA",1,"Rel-5","R2,R5","2001-04-02","2007-03-09",1,"-","-","Motorola","Ravi Kuchibhotla","-","-",null,null,null,null,"2001-03-20","2001-12-10"]
[7790,2480,"   RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","HSDPA-RF",2,"Rel-5","R4","2001-04-09","2003-06-06",1,"RP-010262","-","Motorola","Howard Benn","-","-",null,null,null,null,"2001-03-20","2003-03-27"]
[7791,25000,"   Conformance Testing of HSDPA","HSDPA_Test",2,"Rel-5","R5","2003-09-19","2006-09-22",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7794,1471,"   Base station classification for TDD","RInImp-BSClass",2,"Rel-5","R4","2000-08-14","2002-06-14",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-04-26","2001-10-03"]
[7798,1217,"   Hybrid ARQ II/III","RInImp-HARQ",2,"Rel-5","R2","2000-08-21","2001-12-28",1,"-","-","Siemens","armin.sitte@siemens.com ","Stopped at RP#14¦work on this task was performed as part of High Speed Downlink Packet Access feature","-",null,null,"RP-14",null,"2000-04-26","2002-01-24"]
[7801,2494,"   FS on the re-introduction of the downlink SIR measurement","RInImp-SIR",2,"Rel-5","R4","2001-03-12","2001-12-14",1,"-","-","Ericsson","Torgny.Palenius@ericsson.com","-","-",null,null,null,null,"2001-03-27","2001-11-29"]
[7804,2210,"      Deleted - Testing improvement of inter-frequency and inter-system measurement","-",3,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[7808,23000,"      Iur common transport channel efficiency optimization","RANimp-RRMopt-ctc",3,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Shahrokh Amirijoo","-","-",null,null,null,null,"2001-09-19","2002-03-21"]
[7811,2488,"   RL Timing Adjustment","RANimp-RLTA",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Elena Voltolina","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[7812,2489,"   Separation of resource reservation and radio link activation","RANimp-SepRR",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[7815,2491,"   Re-arrangements of Iub transport bearers","RANimp-TTPS",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[7818,21001,"   Beamforming requirements for UE","RANimp-BFR-UE",2,"Rel-5","R1","2001-09-21","2001-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","-","-",null,null,null,null,"2002-02-28","2002-02-28"]
[7822,2222,"      Deleted - Testing Radio access bearer support enhancements","-",3,"Rel-5","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[7825,1273,"Provisioning of IP-based multimedia services","IMS",1,"Rel-5","S1,S2,S3,S5,NP,T3,T1,R5","2000-01-03","2006-12-01",1,"SP-000216","-","Openwave","Mark Cataldo","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7828,1514,"      Stage 2 (Architecture and Main flows)","-",3,"Rel-5","S2","2000-04-14","2001-03-23",1,"SP-000289","-","Lucent","Liz Daniel","Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol",23.228000000000002,null,null,null,null,"2000-07-28","2001-02-08"]
[7832,1278,"         IMS stage 3","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228999999999999,24.228999999999999,null,null,null,null,"2000-04-19","2003-03-14"]
[7835,10004,"      Main IETF dependencies","-",3,"Rel-5","NP","2000-01-03","2002-06-14",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-01-25","2003-03-28"]
[7836,2521,"         IETF: RFC 3261 (Session Initiation Protocol)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[7839,2524,"         IETF: RFC 3323 (SIP extensions for caller identity and privacy)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[7842,11001,"         IETF: RFC editor Queue (refer method)","-",4,"Rel-5","N1","2000-11-24","2002-06-07",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[7846,11022,"         IETF: RFC 3311 (The Update method)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7849,1290,"         Addressing","-",4,"Rel-5","S2","2000-10-09","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2000-04-01"]
[7851,1292,"            Impact on HSS ","-",5,"Rel-5","N4","2000-11-15","2002-03-22",1,"-","-","-","-","Covered by 29.228 & 29228","-",null,null,null,null,"2000-04-19","2002-05-30"]
[7857,2574,"   Security Aspects of Requirement for Network Configuration Independence","SEC1-NCI",2,"Rel-5","S3","2001-07-02","2001-12-28",1,"SP-010324","-","AT&T Wireless","hugh.shieh@attws.com","Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C",33.203000000000003,null,null,null,null,"2001-06-09","2011-08-08"]
[7860,2036,"   Multimedia codecs and protocols for conversational PS services","IMS-CODEC",2,"Rel-5","S4","2000-07-26","2002-09-27",1,"SP-000398","-","Toshiba, Nokia","B. Aronson (Toshiba), pasi.s.ojala@nokia.com","-","26.235, 26.236",null,null,null,null,"2000-09-27","2003-03-27"]
[7861,2039,"      Codecs","-",3,"Rel-5","S4","2000-07-26","2002-03-14",1,"SP-000398","-","-","-","-","26.235, 26.236",null,null,null,null,"2000-09-28","2002-03-25"]
[7864,11025,"      IETF: RFC 3310 (HTTP Digest Authentication using AKA)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[7867,32004,"      Stage 2 for SIP message compression","-",3,"Rel-5","S2","2001-09-24","2001-10-26",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2001-11-24"]
[7871,14997,"      Mp interface (MRFC - MRFP) enhancements","-",3,"Rel-5","N4","2001-03-14","2002-03-08",1,"-","-","-","-","[DAB 08-03-02] - No work required in CN4","-",null,null,null,null,"2001-10-08","2002-05-30"]
[7874,14003,"      Dx interface (I-CSCF to SLF)","-",3,"Rel-5","N4","2001-03-14","2002-06-07",1,"-","-","-","-","CN4#11 30/11/01: No inputs received in CN4","-",null,null,null,null,"2001-10-08","2002-05-30"]
[7878,14998,"      Si interface (HSS to IM-SSF)","-",3,"Rel-5","N4","2002-01-16","2002-08-30",1,"-","-","-","-","SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete)","-",null,null,null,null,"2002-03-25","2002-05-30"]
[7881,11028,"      Mj interface (BGCF to MGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[7884,12000,"   CAMEL control of IMS services","IMS-CAMEL",2,"Rel-5","N2","2001-04-16","2002-09-06",1,"NP-020305","-","Lucent","Angelica Remoquillo","-","-",null,null,null,null,"2000-04-19","2002-06-21"]
[7885,12001,"      Stage2 work 'general'","-",3,"Rel-5","N2","2001-04-16","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2001-10-08","2003-01-13"]
[7888,12004,"      Stage3 work 'Si interface'","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","[DAB 08-03-02] - UID 12004 is MASTER of UID 14998","-",null,null,null,null,"2002-01-24","2002-05-30"]
[7891,35005,"   IMS Charging","OAM-CH",2,"Rel-5","S2,S5","2001-08-06","2002-09-12",1,"SP-010631","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-",32.225000000000001,null,null,null,null,"2001-10-08","2003-01-13"]
[7895,10002,"   Other IETF dependencies","-",2,"Rel-5","NP","2000-11-24","2002-06-07",1,"-","-","-","-","Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined)","-",null,null,null,null,"2001-10-11","2002-03-25"]
[7898,1844,"   Conformance Test Aspects - Provisioning of IMS","IMS-TEST",2,"Rel-5","T1","2002-03-18","2002-12-27",1,"-","-","-","-","The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008","-",null,null,null,null,"2000-09-14","2008-12-12"]
[7902,34001,"Extended Transparent End-to-End PS Streaming Service","PSS-E",1,"Rel-5","S4","2002-01-03","2003-03-17",1,"SP-010392","-","Ericsson","olle.franceschi@ericsson.com","-","26.233, 26.234",null,null,null,null,"2001-06-28","2002-02-28"]
[7905,34003,"   Stage 2 (version Rel-5 of TS 26.234)","-",2,"Rel-5","S4","2002-01-03","2002-03-14",1,"SP-010392","-","-","-","2nd resp SA2",26.234000000000002,null,null,null,null,"2001-06-28","2002-03-25"]
[7908,32010,"   General Stage 2 for Rel-5","-",2,"Rel-5","S2","2001-09-11","2002-06-07",1,"-","-","-","-","Marked as closed 12/2008 (was marked 47% complete)","-",null,null,null,null,"2000-11-21","2008-12-12"]
[7909,1429,"   OSA APIs for Multimedia Call Control","OSA1-CSCF",2,"Rel-5","S2","2000-07-11","2002-06-07",1,"-","-","-","-","For Rel5 even if completed by March","-",null,null,null,null,"2000-04-19","2002-01-24"]
[7912,15003,"   Generic user interaction - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-05",null,null,null,null,"2002-02-28","2002-06-21"]
[7917,2121,"      Stage 1 for OSA Security","-",3,"Rel-5","S1","2000-07-11","2001-11-09",1,"-","-","Siemens","Manfred.leitgeb@siemens.at","-",22.126999999999999,null,null,null,null,"2000-11-22","2002-02-28"]
[7920,1423,"      OSA changes required from supporting platforms, e.g. gsmSCF, HLR ","-",3,"Rel-5","S3","2000-09-11","2000-12-14",1,"SP-000302","-","BT, Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[7923,1425,"      Stage 1 for Interactions OSA - e-commerce","-",3,"Rel-5","S1","1999-04-27","2000-12-28",1,"-","-","Siemens","joerg.swetina@neclab.eu","Marked as closed 12/2008 (was marked 95% complete)",22.126999999999999,null,null,null,null,"2000-04-19","2008-12-12"]
[7927,1786,"   LCS - OSA interfaces","OSA1-LCSI",2,"Rel-5","S1","2000-09-11","2002-06-07",1,"-","-","Siemens","joerg.swetina@neclab.eu","az: CN#13 - changed to Rel5","-",null,null,null,null,"2000-04-19","2001-10-08"]
[7930,1788,"      Stage 3 for LCS - OSA interfaces","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2002-06-21"]
[7933,1434,"      Stage 1 for Retrieval of Terminal capabilities","-",3,"Rel-5","S1","2000-07-11","2001-01-10",1,"-","-","Siemens","joerg.swetina@neclab.eu","-",22.126999999999999,null,null,null,null,"2000-04-19","2003-07-25"]
[7934,1436,"      Stages 2 and 3 for Retrieval of Terminal capabilities","-",3,"Rel-5","N5","2001-09-21","2002-12-13",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2003-07-25"]
[7937,1461,"   Service requirements","-",2,"Rel-5","S1","2000-04-17","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[7941,2015,"   Inclusion of flexible tone injection ","CAMEL4-IFTI",2,"Rel-5","N2","2000-07-17","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[{"$f":"A7944+1","v":7944},2458,"   Provision of location information of called subscriber","CAMEL4-LOCB",2,"Rel-5","N2","2001-03-02","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-02-28"]
[7947,2516,"   GPRS Any Time Interrogation","CAMEL4-ATI",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[7951,2466,"   MExE Rel-5 Improvements and Investigations","MEXE5-ENHANC",2,"Rel-5","T2","2001-03-26","2002-03-08",1,"TP-010071","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2002-03-21"]
[7954,31005,"      Stage 1 for Wideband Telephony Service - AMR","-",3,"Rel-5","S1","2001-10-01","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-03-01"]
[7957,1460,"         General Description for Wideband Telephony Service - AMR","-",4,"Rel-5","S4","2000-02-07","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7958,1626,"      Feasibility Study for Wideband Telephony Service - AMR","-",3,"Rel-5","S4","2000-04-28","2000-06-02",1,"SP-000024","-","-","-","S4,TD SP-000024: TR 26.901 v.4.0.0",26.901,null,null,null,null,"2000-08-08","2002-02-28"]
[7961,67,"      Codec issues","-",3,"Rel-5","S4","2000-01-03","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[7965,34007,"         TFO AMR-WB","AMRWB-TFO",4,"Rel-5","S4","2001-12-18","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-09-26"]
[7968,34009,"         Interworking with fixed broadband networks","-",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[7971,1855,"      Conformance tests (CRs to 34 series) ","-",3,"Rel-5","T1","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[7973,1628,"            Definition for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-01-01","2000-01-31",1,"-","-","-","-","-",26.131,null,null,null,null,"2000-08-08","2002-02-28"]
[7979,2267,"      Signalling for Iu","-",3,"Rel-5","GP","2000-01-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7980,2268,"      Receiver performance in TS 45.005","-",3,"Rel-5","GP","2001-04-02","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[7983,2270,"      Deleted - MS test for AMR-WB","-",3,"Rel-5","GP","2000-01-03","2003-12-19",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[7986,2573,"   Terminal local model enhancements","TLM5",2,"Rel-5","T2","2001-05-14","2002-03-20",1,"TP-010224","-","-","-","-",23.227,null,null,null,null,"2000-09-14","2003-03-27"]
[7990,2125,"      Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning","LCS-INTF",3,"Rel-5","R2","2001-01-15","2001-10-12",1,"RP-010414","-","Qualcomm","Kirk Burroughs","RP#13 completed","-",null,null,null,null,"2000-11-27","2002-01-24"]
[7993,1538,"      Stage 2 for Event based and Periodic LCS","-",3,"Rel-5","S2","2000-11-06","2001-01-26",1,"-","-","-","-","Marked as closed 12/2008 (was marked 51% complete)","-",null,null,null,null,"2000-07-28","2008-12-12"]
[7996,2437,"      GERAN LCS Stage 2 (first release)","-",3,"Rel-5","GP,S2,G1,G2","2000-04-03","2002-02-08",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8000,2442,"   Location Services for GERAN in Iu Mode","-",2,"Rel-5","S2,G1,G2,R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8003,2445,"      Iu-cs interface support for LCS","-",3,"Rel-5","R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8004,2446,"      Iur-g interface support for LCS","-",3,"Rel-5","G1,G2","2002-01-23","2002-04-19",1,"GP-011926","-","Nokia","Margaret Livingston","FFS","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8007,2449,"      Stage 3 for Location Services for GERAN in Iu Mode","-",3,"Rel-5","G1,G2,R2,R3","2002-03-25","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8010,55070,"      LCS MS test cases","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","-",null,null,null,null,"2002-05-23","2012-05-21"]
[8014,544,"   LCS interoperation stage 2 aspects","-",2,"Rel-5","S2","2000-08-28","2002-06-28",1,"-","-","-","-","Marked as closed 12/2008 (was marked 17% complete)","-",null,null,null,null,"2000-04-19","2008-12-12"]
[8017,1183,"   FS on LCS support in the IMS","-",2,"Rel-5","S1","2001-02-12","2002-01-18",1,"-","-","-","-","Marked as closed 12/2008 (was marked 75% complete)","-",null,null,null,null,"2000-04-19","2008-12-12"]
[8021,32022,"   Deleted - CHECK STATUS - Inter-GMLC interface","-",2,"Rel-5","S2","2002-05-30","2002-12-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"SP-10",null,"2002-05-30","2008-12-12"]
[8024,2576,"      Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP)","-",3,"Rel-5","S3","2000-06-15","2002-03-15",1,"SP-010326","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286)","New 33.210",null,null,null,null,"2001-06-09","2011-08-08"]
[8027,1579,"         Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","N4","2001-09-14","2002-06-07",1,"-","-","-","-","Waiting for input from SA3!. Marked as stopped 12/2008","-",null,null,"NP-16",null,"2000-04-09","2008-12-12"]
[8028,1580,"      Deleted - User plane protection in core network (e.g., provided by IPsec)","-",3,"Rel-5","S3","2000-02-21","2002-06-28",1,"-","-","-","-","TO BE DELETED. Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-04-18","2008-12-12"]
[8031,2243,"Intra Domain Connection of RAN Nodes to Multiple CN Nodes","IUFLEX",1,"Rel-5","S2,N1,N4,R3,GP","2000-10-02","2002-06-28",1,"SP-000619","-","Ericsson","stephen.terrill@ericsson.com","No clear indication on the end date. Put to Rel5 by AS.",23.236000000000001,null,null,null,null,"2000-12-13","2002-01-24"]
[8034,2248,"   N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","N1","2001-09-17","2002-06-28",1,"NP-010693","-","-","-","-","24.008 and check 29.018",null,null,null,null,"2000-12-13","2002-09-26"]
[8039,52070,"      Stage 3 (changes to )","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8042,2320,"Deleted - GERAN improvements 3 (new transport layer on interface A)","GEIMP3",1,"Rel-5","GP","2001-04-06","2002-12-20",1,"GP-010909","-","-","-","Terminated - not standardized. Marked as stopped 12/2008","-",null,null,"SP-69",null,"2001-02-01","2008-12-12"]
[8046,501142,"Rel-5 Charging Management & Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM5",1,"Rel-5","S5","2001-09-10","2002-09-12",1,"SP-010461","-","-","-","-","-",null,null,null,null,"2000-04-26","2002-06-21"]
[8049,35004,"   Rel-5 Charging Management","-",2,"Rel-5","S5","2001-09-10","2002-09-12",1,"SP-010631","-","T-Mobile","Karl-Heinz.Nenner@T-MOBILE.DE","-","32.200, 32.205, 32.215, 32.225, 32.235",null,null,null,null,"2000-04-26","2002-11-08"]
[8052,2394,"   Concept for GERAN enhancements for streaming services 1 (RLC enhancements)","-",2,"Rel-5","GP","2000-11-06","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8053,2395,"   RLC protocol enhancement (SDU Discard)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8056,2399,"   Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD)","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8059,2402,"   MAC header","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8063,2415,"      Update of Evolution of Iu ps specifications ","-",3,"Rel-5","GP,R3","2001-12-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8066,2418,"      Identification of GERAN requirements on Iu cs","-",3,"Rel-5","GP,R3","2000-06-29","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8070,2558,"   E2E QoS interworking","E2EQoS-IW",2,"Rel-5","N3","2000-08-28","2002-06-07",1,"NP-010528","-","Lucent","Daisuke Yokota (yokota@lucent.com)","[DAB - 30/07/02] - % complete to 95% (if we exclude Diffserv). Marked as closed 12/2008 (was marked 95% complete)","29.208, 29.207, 27.060, 29.061, 24.008, 24.228, , 24.229, 29.060, 29.163",null,null,null,null,"2001-06-08","2008-12-12"]
[8073,2571,"   Rel-5 Multimedia Messaging (MMS) enhancements","MESS5-MMS",2,"Rel-5","T2","2001-06-15","2003-03-31",1,"TP-010130","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2000-09-14","2003-03-27"]
[8076,42008,"      WAP Forum dependency: MM1 stage 3","-",3,"Rel-5","T2","2001-06-15","2003-03-31",1,"-","-","-","-","Marked as closed 12/2008 (was marked 80% complete)","-",null,null,null,null,"2002-05-30","2008-12-12"]
[8077,34018,"      MMS formats and codecs for MESS5-MMS","-",3,"Rel-5","S4","2001-12-03","2002-03-15",1,"-","-","-","-","-",26.14,null,null,null,null,"2002-01-24","2002-02-28"]
[8080,42001,"      Technical realization of Enhanced Messaging Service (EMS) enhancements","-",3,"Rel-5","T2","2001-06-15","2002-03-08",1,"-","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-",23.04,null,null,null,null,"2001-07-04","2002-02-28"]
[8084,14502,"      Stage 2 - 23.060 change - Definition of Inter BSC NACC","-",3,"Rel-5","N4,S2","2001-09-03","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8087,50003,"      Stage 3 (changes to TS 48.018)","-",3,"Rel-5","GP","2001-11-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8090,50035,"   Deleted - GERAN MS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012750","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[8094,50061,"      Concept","-",3,"Rel-5","GP","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8095,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8099,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8100,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8101,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8102,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[8103,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[8104,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[8105,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8106,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[8107,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[8108,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[8109,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[8110,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[8111,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[8112,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[8113,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8114,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[8115,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[8116,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[8117,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[8118,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8119,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8120,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8121,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8122,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[8123,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8124,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8125,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8126,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8127,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8128,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8129,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8130,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8131,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8132,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8133,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8134,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8135,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[{"$f":"A8136+1","v":8136},2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8137,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8138,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8139,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8140,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8141,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8142,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8143,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8144,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8145,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8146,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8147,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8148,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8149,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8150,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8151,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8152,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8153,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8154,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8155,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8156,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8157,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8158,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8159,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8160,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8161,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8162,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8163,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8164,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8165,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8166,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8167,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8168,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8169,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8170,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8171,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8172,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8173,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8174,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8175,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8176,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8177,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8178,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8179,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8180,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8181,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8182,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8183,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8184,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8185,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8186,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8187,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8188,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8189,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8190,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8191,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8192,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8193,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8194,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8195,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8196,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8197,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8198,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8199,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[{"$f":"A8200+1","v":8200},1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[8201,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8202,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8203,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8204,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8205,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8206,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8207,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8208,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8209,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8210,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8211,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8212,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8213,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8214,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8215,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8216,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8217,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8218,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8219,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8220,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8221,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[8222,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8223,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8224,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8225,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8226,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8227,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8228,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8229,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8230,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8231,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8232,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8233,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8234,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8235,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8236,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8237,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8238,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8239,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8240,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8241,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8242,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8243,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8244,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8245,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8246,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8247,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8248,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8249,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8250,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8251,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8252,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8253,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8254,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8255,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8256,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8257,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8258,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8259,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8260,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8261,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8262,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8263,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[{"$f":"A8264+1","v":8264},1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8265,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8266,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8267,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8268,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8269,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8270,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[8271,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8272,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8273,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8274,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8275,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8276,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8277,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8278,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8279,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8280,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8281,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8282,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8283,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8284,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8285,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[8286,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8287,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8288,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8289,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8290,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8291,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8292,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8293,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8294,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8295,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8296,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8297,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8298,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8299,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8300,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8301,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8302,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8303,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8304,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8305,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8306,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8307,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8308,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8309,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8310,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8311,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8312,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8313,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8314,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8315,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8316,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8317,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8318,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8319,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8320,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8321,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8322,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8323,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8324,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8325,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8326,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8327,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[{"$f":"A8328+1","v":8328},1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[8329,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[8330,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8331,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[8332,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8333,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[8334,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[8335,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8336,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[8337,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[8338,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8339,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8340,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8341,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8342,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8343,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8344,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8345,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8346,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8347,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[8348,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8349,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[8350,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[8351,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[8352,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[8353,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[8354,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8355,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[8356,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[8357,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[8358,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[8359,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[8360,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[8361,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8362,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8363,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[8364,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[8365,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[8366,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[8367,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[8368,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8369,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[8370,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8371,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8372,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8373,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[8374,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[8375,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[8376,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8377,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8378,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[8379,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[8380,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[8381,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8382,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[8383,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8384,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[8385,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8386,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[8387,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8388,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8389,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[8390,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[8391,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[{"$f":"A8392+1","v":8392},401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8393,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[8394,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[8395,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8396,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[8397,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[8398,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[8399,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[8400,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[8401,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[8402,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[8403,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[8404,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[8405,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[8406,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[8407,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[8408,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[8409,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[8410,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[8411,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[8412,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8413,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[8414,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8415,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8416,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[8417,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[8418,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[8419,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[8420,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[8421,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8422,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[8423,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8424,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[8425,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[8426,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8427,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8428,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[8429,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[8430,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[8431,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[8432,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[8433,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[8434,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[8435,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[8436,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8437,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8438,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[8439,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8440,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8441,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[8442,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[8443,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8444,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8445,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[8446,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8447,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8448,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8449,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8450,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8451,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8452,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[8453,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[8454,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8455,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A8456+1","v":8456},60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8457,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[8458,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[8459,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[8460,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8461,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[8462,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8463,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[8464,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[8465,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8466,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[8467,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[8468,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8469,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8470,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[8471,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[8472,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[8473,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[8474,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[8475,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[8476,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[8477,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8478,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8479,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[8480,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[8481,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8482,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[8483,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[8484,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[8485,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[8486,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[8487,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[8488,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[8489,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[8490,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[8491,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[8492,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8493,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8494,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8495,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[8496,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[8497,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[8498,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8499,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8500,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[8501,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[8502,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8503,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[8504,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8505,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[8506,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[8507,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[8508,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8509,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[8510,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8511,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[8512,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[8513,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[8514,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[8515,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[8516,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[8517,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[8518,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[8519,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A8520+1","v":8520},60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8521,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8522,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8523,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[8524,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8525,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8526,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8527,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[8528,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[8529,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[8530,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[8531,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[8532,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8533,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[8534,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[8535,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[8536,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8537,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8538,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8539,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8540,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[8541,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8542,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[8543,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8544,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[8545,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[8546,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8547,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8548,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8549,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8550,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8551,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8552,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8553,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8554,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8555,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[8556,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[8557,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[8558,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8559,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[8560,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8561,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[8562,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8563,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[8564,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8565,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8566,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[8567,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[8568,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[8569,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[8570,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8571,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[8572,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[8573,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8574,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8575,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8576,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8577,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8578,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[8579,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8580,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[8581,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[8582,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[8583,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[{"$f":"A8584+1","v":8584},60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[8585,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[8586,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8587,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[8588,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[8589,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[8590,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[8591,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[8592,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[8593,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[8594,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[8595,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[8596,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[8597,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[8598,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]