{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp","index":0,"n_rows":8782,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version July 16th 2024",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[2,0,"Post CT and SA#104 version (RAN#104 outputs not yet included)",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[3,0,"Next key milestones: Rel-19: St.2: Dec 24; St.3: Sept.25",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[{"$f":"A5+1","v":5},0,"--- RELEASE 20 ---","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A6+1","v":6},1030042,"Study on satellite access - Phase 4 ","FS_5GSAT_Ph4",1,"Rel-20","S1","2024-04-02","2025-03-03",0.3,"SP-240495",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","13/6/24: 0%->30",22.887,103,52,null,null,"2024-03-13","2024-06-13"]
[7,1030043,"Study on FRMCS Phase 6 ","FS_FRMCS_Ph6",1,"Rel-20","S1","2024-03-13","2024-09-09",0.2,"SP-240199",null,"Nikolopoulou, Vassiliki, UIC, ","nikolopoulou@uic.org ","; 13/6/24: 0%->20",22.989000000000001,103,52,null,null,"2024-03-13","2024-06-13"]
[8,1030044,"Study on Energy Efficiency as Service Criteria Phase 2 ","FS_EnergyServ_Ph2",1,"Rel-20","S1","2024-04-02","2025-03-03",0.25,"SP-240494",null,"Laurent-WalterGoix, Nokia ","laurent-walter.goix@NOKIA.COM ","13/6/24: 0%->25",22.882999999999999,103,52,null,null,"2024-03-13","2024-06-13"]
[9,1040011,"Lawful Interception Rel-20 ","LI20",1,"Rel-20","S3LI","2024-06-12","2027-03-03",0,"SP-241012",null,"Koen Jaspers, PIDS, ","k.b.jaspers@minjenv.nl ",null,"33.107; 33.108; 33.126; 33.127; 33.128; 33.928 ",null,null,null,null,"2024-06-12","NA"]
[10,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[11,0,"Rel-19 Energy Efficiency, Energy Saving","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[12,1020060,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19",null,"2022-06-02","2025-06-06",0.59,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[13,960019,"   Study on Energy Efficiency as service criteria ","FS_EnergyServ",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.882000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[14,1000033,"   Stage 1 of Energy Efficiency as Service Criteria ","EnergyServ",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[15,1040018,"   Charging Aspects for Energy Efficiency of 5G ","EnergySys_CH",2,"Rel-19","S5","2024-06-12","2025-06-06",0,"SP-241003",null,"YiMeng, DENG, Huawei, ","dengyimeng@huawei.com ",null,"32.240; 28.201; 28.202; 32.291; 32.298 ",null,null,null,null,"2024-06-12","NA"]
[16,1010029,"   Study on Energy Efficiency and Energy Saving","FS_EnergySys",2,"Rel-19","S2","2023-09-09","2024-06-06",0.99,"SP-231391",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;; 14/3/24: 15%->55; 13/6/24: 55%->100","SP-231192; 23.700-66; 28.880",101,51,null,null,"2023-09-20","2024-06-13"]
[17,1020021,"   Study on energy efficiency and energy saving aspects of 5G networks and services ","FS_Energy_OAM_Ph3",2,"Rel-19","S5","2023-12-08","2024-09-09",0.25,"SP-231723",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com","4/1/24: 28.866 added;; 14/3/24: 0%->10; 13/6/24: 10%->25",28.866,102,52,null,null,"2023-12-07","2024-06-13"]
[18,1030038,"   Study on security aspects of energy saving in 5G ","FS_Energy_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.3,"SP-240512",null,"Bo Bjerrum ","bo.bjerrum@nokia.com ","3/4/24: 33.766 added;; 13/6/24: 0%->30",33.765999999999998,103,52,null,null,"2024-03-14","2024-06-13"]
[19,1020095,"Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh",1,"Rel-19",null,"2023-12-13","2026-03-03",0.09,"RP-240170",null,"Ericsson ",null,"2/4/24: WID:RP-234065->RP-240170",null,102,52,null,null,"2024-01-02","2024-04-02"]
[20,1021095,"   Core part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.25,"RP-240170","RP-241182","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240169->RP-241182; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[21,1022095,"   Perf. part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240170","RP-241182","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Stat Rep: RP-240169->RP-241182; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[22,1030067,"   UE Conformance - Network energy savings for NR ","Netw_Energy_NR-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240291","RP-241378","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241378; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[23,1030004,"Study on Media enerGy consumption exposuRE and EvaluatioN framework ","FS_MediaEnergyGREEN",1,"Rel-19","S4","2024-04-02","2025-03-03",0.15,"SP-240481",null,"Julien Lemotheux, Orange, ","julien.lemotheux@orange.com ","14/5/24: 26.942 added;; 13/6/24: 0%->15",26.942,103,52,null,null,"2024-03-13","2024-06-13"]
[24,1020094,"Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS",1,"Rel-19",null,"2023-12-13","2026-03-03",0.09,"RP-240801",null,"vivo ",null,"2/4/24: WID:RP-234056->RP-240801",null,102,52,null,null,"2024-01-02","2024-04-02"]
[25,1021094,"   Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.2,"RP-240801","RP-241039","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Compl:8%->20%; Stat Rep: RP-240134->RP-241039; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[26,1022094,"   Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240801","RP-241039","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Stat Rep: RP-240134->RP-241039; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[27,0,"Rel-19 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[28,1040084,"Study on 3GPP AI/ML Consistency Alignment","FS_AIML_CAL",1,"Rel-19","SP","2024-06-20","2025-06-06",0,"SP-240970",null,"Johannes Achter, Magenta",null,null,null,null,null,null,null,"2024-06-20","NA"]
[29,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23:...","22.875; 22.876",95,48,null,null,"2022-03-10","2023-09-06"]
[30,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80; 8/12/23: 80%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[31,1040033,"Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ",null,"23.288; 23.501; 23.502; 23.503; 23.273 ",null,null,null,null,"2024-06-12","NA"]
[32,1040075,"Application enablement for AI/ML services ","AIML_App",1,"Rel-19","S6","2024-07-16","2024-12-12",0,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ",null,"23.436; 23.434; 23.558 ",null,null,null,null,"2024-06-12","NA"]
[33,1020068,"Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","FS_AIML_CN",1,"Rel-19","S2","2024-01-04","2024-06-06",1,"SP-231800",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com) ","14/3/24: 0%->25; 13/6/24: 25%->100",null,102,52,null,null,"2024-01-03","2024-06-13"]
[34,1030035,"Study on security aspects of Core Network Enhanced Support for AIML ","FS_AIML_CN_SEC",1,"Rel-19","S3","2024-04-02","2024-12-12",0.35,"SP-240509",null,"Chang Liu, ","liuchangyjy@chinamobile.com ","3/4/24: 33.784 added;; 13/6/24: 0%->35",33.783999999999999,103,52,null,null,"2024-03-14","2024-06-13"]
[35,1020007,"Study on AI/ML management - phase 2 ","FS_AIML_MGT_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0.19,"SP-240965",null,"Yizhi Yao (Intel) ","yizhi.yao@intel.com ","13/6/24: 0%->19; 16/7/24: WID:SP-231780->SP-240965",null,102,52,null,null,"2023-12-07","2024-07-16"]
[36,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","2023-09-07","2024-09-09",0.95,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","8/12/23: 0%->35; 4/1/24: 23.700-82 added;; 14/3/24: 35%->55; 13/6/24: 55%->95","23.700-82",101,51,null,null,"2023-09-07","2024-06-13"]
[37,1020083,"Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","FS_NR_AIML_NGRAN_enh",1,"Rel-19","R3","2023-12-13","2024-09-09",0.8,"RP-240323","RP-241097","ZTE ",null,"14/3/24: FCD:06/06/2024->/24; 2/4/24: WID:RP-234054->RP-240323; 3/4/24: 38.743 added;; 13/6/24: Compl:0%->80%; Stat Rep: ->RP-241097; ",38.743000000000002,102,52,null,null,"2024-01-02","2024-06-13"]
[38,1020084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR ","FS_NR_AIML_Mob",1,"Rel-19","R2","2019-03-07","2024-12-12",0,"RP-240082","RP-240083","Zhongda Du, OPPO","duzhongda@oppo.com","14/3/24: FCD:28/05/2021->12/12/2024; Stat Rep: ->RP-240083; Rapporteur: Oppo->Zhongda Du, OPPO; Rap eMail: ->duzhongda@oppo.com; ; 2/4/24: WID:RP-234055->RP-240082; 3/4/24: 38.744 added;",38.744,102,52,null,null,"2024-01-02","2024-04-03"]
[39,1020093,"Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air",1,"Rel-19",null,"2023-12-13","2026-03-03",0.09,"RP-240774",null,"Qualcomm ",null,"2/4/24: WID:RP-234039->RP-240774",null,102,52,null,null,"2024-01-02","2024-04-02"]
[40,1021093,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.2,"RP-240774","RP-241153","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsso...",null,102,52,null,null,"2024-01-02","2024-06-13"]
[41,1022093,"   Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240774","RP-241153","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com; ; 13/6/...",null,102,52,null,null,"2024-01-02","2024-06-13"]
[42,0,"Rel-19 Ambient power-enabled Internet of Things ","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[43,1020055,"Ambient power-enabled Internet of Things ","AmbientIoT",1,"Rel-19",null,"2022-03-10","2024-12-12",0.88,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[44,950004,"   Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.84,95,48,null,null,"2022-03-10","2023-12-08"]
[45,1020071,"   Study on Architecture support of Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S2","2024-01-04","2024-12-12",0.65,"SP-240969",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","14/3/24: 0%->25; 13/6/24: 25%->65; 16/7/24: WID:SP-231803->SP-240969",null,102,52,null,null,"2024-01-03","2024-07-16"]
[46,1020030,"   Stage 1 of Ambient power-enabled Internet of Things ","AmbientIoT",2,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[47,1020085,"Study on solutions for Ambient IoT (Internet of Things) in NR ","FS_Ambient_IoT_solutions",1,"Rel-19","R1","2023-12-13","2024-12-12",0.4,"RP-240826","RP-241206","Xiaodong Shen, CMCC","shenxiaodong@chinamobile.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240155; Rapporteur: CMCC->Xiaodong Shen, CMCC; Rap eMail: ->shenxiaodong@chinamobile.com; ; 2/4/24: WID:RP-234058->RP-240826; 3/4/24: 38.769 added;; 13/6/24: Compl:8%->40%; Stat Rep: RP-240155->RP-241206; ",38.768999999999998,102,52,null,null,"2024-01-02","2024-06-13"]
[48,1030031,"Study on Security Aspect of Ambient IoT Services in 5G ","FS_Ambient_IoT_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",0.3,"SP-240506",null,"Marcus Wong, ","marcus.wong@oppo.com ","3/4/24: 33.713 added;; 13/6/24: 0%->30",33.713000000000001,103,52,null,null,"2024-03-14","2024-06-13"]
[49,0,"See also IoT_NTN_Ph3 under Satellite/NTN ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[50,0,"Rel-19 Satellite (5GSAT), NTN","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[51,1020058,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19",null,"2022-06-02","2024-12-12",0.71,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[52,960016,"   Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[53,1000024,"   Stage 1 of Satellite access Phase 3 ","5GSAT_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[54,1010033,"   Study on Integration of satellite components in the 5G architecture Phase 3","FS_5GSAT_Ph3_ARCH",2,"Rel-19","S2","2023-09-20","2024-06-06",0.99,"SP-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;; 14/3/24: 15%->55; 13/6/24: 55%->100","23.700-29; 28.874",101,51,null,null,"2023-09-20","2024-06-13"]
[55,1020053,"   Study on application enablement for Satellite access enabled 5G Services ","FS_5GSAT_Ph3_App",2,"Rel-19","S6","2024-01-03","2024-09-09",0.6,"SP-240296",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","8/12/23: 0%->5; 14/3/24: 0%->25; 2/4/24: WID:SP-231738->SP-240296; 3/4/24: 23.700-01 added;; 13/6/24: 25%->60","23.700-01",102,52,null,null,"2023-12-07","2024-06-13"]
[56,1040027,"   Integration of satellite components in the 5G architecture Phase III ","5GSAT_Ph3_ARCH",2,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240986",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.682; 23.228; 23.401 ",null,null,null,null,"2024-06-12","NA"]
[57,1040077,"   Application enablement for satellite access Phase 3 ","5GSAT_Ph3_App",2,"Rel-19","S6","2024-07-16","2024-12-12",0,"SP-241010",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,"23.558; 23.434; 23.289 ",null,null,null,null,"2024-06-12","NA"]
[58,1020044,"Study on Security Aspects of 5G Satellite Access Phase 3 ","FS_5GSAT_Ph3_SEC",1,"Rel-19","S3","2024-01-04","2024-12-12",0.65,"SP-240232",null,"Zhou Wei ","zhouwei@catt.cn ","No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;; 14/3/24: 0%->10; 2/4/24: WID:SP-231790->SP-240232; 13/6/24: 10%->65","33.700-29",102,52,null,null,"2023-12-07","2024-06-13"]
[59,1040014,"Study on charging aspects of satellite access Phase 3 ","FS_5GSAT_Ph3_CH",1,"Rel-19","S5","2024-06-12","2024-12-12",0.1,"SP-240980",null,"Yingying Liu, CATT, ","liuyingying@cictmobile.com ","13/6/24: 0%->10",null,null,null,null,null,"2024-06-12","2024-06-13"]
[60,1020097,"Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3",1,"Rel-19",null,"2023-12-13","2026-03-03",0.11,"RP-240775",null,"Thales ",null,"2/4/24: WID:RP-234078->RP-240775",null,102,52,null,null,"2024-01-02","2024-04-02"]
[61,1021097,"   Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.25,"RP-240775","RP-240923","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240091->RP-240923; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[62,1022097,"   Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240775","RP-240923","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Stat Rep: RP-240091->RP-240923; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[63,1020096,"Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE)","IoT_NTN_Ph3",1,"Rel-19",null,"2023-12-13","2025-12-12",7.0000000000000007E-2,"RP-240776",null,"Mediatek ",null,"2/4/24: WID:RP-234077->RP-240776",null,102,52,null,null,"2024-01-02","2024-04-02"]
[64,1021096,"   Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.15,"RP-240776","RP-241356","Mediatek ",null,"13/6/24: Compl:0%->15%; Stat Rep: ->RP-241356; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[65,1032087,"   Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Perf",2,"Rel-19","R4","2024-03-03","2025-12-12",0,"RP-240776","RP-241356","Mediatek ",null,"13/6/24: FCD:03/03/2026->12/12/2025; Stat Rep: ->RP-241356; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[66,1030076,"Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob",1,"Rel-19","R2","2024-03-03","2025-09-09",0.7,"RP-240846",null,"Thales ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[67,1031076,"   Core part: Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob-Core",2,"Rel-19","R2","2024-03-03","2025-09-09",0.7,"RP-240846","RP-240925","Thales ",null,"13/6/24: Compl:0%->70%; Stat Rep: ->RP-240925; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[68,1030086,"Enhanced requirements and test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh",1,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240857",null,"Samsung ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[69,1031086,"   Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0,"RP-240857","RP-241280","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[{"$f":"A70+1","v":70},1032086,"   Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240857","RP-241280","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[71,0,"Rel-19 XR (eXtended Reality), Metaverse","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[72,1020056,"Localized Mobile Metaverse Services ","Metaverse",1,"Rel-19",null,"2022-03-10","2024-12-12",0.69,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[73,950005,"   Study on Localized Mobile Metaverse Services ","FS_Metaverse",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100",22.856000000000002,95,48,null,null,"2022-03-10","2023-12-08"]
[74,1000028,"   Stage 1 of Localized Mobile Metaverse Services ","Metaverse",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[75,1040076,"   Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19","S6","2024-07-16","2024-12-12",0,"SP-241009",null,"Shah, Sapan, Samsung ","<sapan.shah@samsung.com> ",null,"23.434; 23.542; 23.558; 23.436 ",null,null,null,null,"2024-06-12","NA"]
[76,1020052,"   Study on application enablement for Localized Mobile Metaverse Services ","FS_Metaverse_App",2,"Rel-19","S6","2024-01-03","2024-09-09",0.7,"SP-231806",null,"Shah, Sapan, Samsung ","sapan.shah@samsung.com ","8/12/23: 0%->10; 14/3/24: 0%->30; 3/4/24: 23.700-21 added;; 13/6/24: 30%->70","23.700-21",102,52,null,null,"2023-12-07","2024-06-13"]
[77,1030039,"   Study on security aspects of 5G Mobile Metaverse services ","FS_Metaverse_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.2,"SP-240508",null,"Rohini Rajendran, ","r.rohini@samsung.com ","3/4/24: 33.721 added;; 13/6/24: 0%->20",33.720999999999997,103,52,null,null,"2024-03-14","2024-06-13"]
[78,1010032,"Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",1,"Rel-19","S2","2024-01-03","2024-09-09",0.9,"SP-231671",null,"Primary Rapporteur: Devaki Chandramouli (Nokia) ","devaki.chandramouli@nokia.com. ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13; 14/3/24: 0%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->90","23.700-70",101,51,null,null,"2023-09-20","2024-06-13"]
[79,1040032,"Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240990",null,"Devaki Chandramouli (Nokia), ","devaki.chandramouli@nokia.com. ",null,"23.501; 23.502; 23.503; 23.316 ",null,null,null,null,"2024-06-12","NA"]
[80,1020051,"Study on Application enabler for XR Services ","FS_XRApp",1,"Rel-19","S6","2024-01-03","2024-09-09",0.65,"SP-2315739",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","8/12/23: 0%->10; 14/3/24: 0%->20; 3/4/24: 23.700-23 added;; 13/6/24: 20%->65","23.700-23",102,52,null,null,"2023-12-07","2024-06-13"]
[81,1040074,"Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",1,"Rel-19","S6","2024-07-16","2024-12-12",0,"SP-241007",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ",null,"23.433; 23.558 ",null,null,null,null,"2024-06-12","NA"]
[82,990052,"Supporting UE Mobility for XR Services ","XRMobility",1,"Rel-19","S1","2023-03-16","2023-06-06",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-09-06"]
[83,1020098,"XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3",1,"Rel-19",null,"2023-12-13","2026-03-03",0.08,"RP-240791",null,"Nokia ",null,"2/4/24: WID:RP-234080->RP-240791",null,102,52,null,null,"2024-01-02","2024-04-02"]
[84,1021098,"   Core part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.18,"RP-240791","RP-240927","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Compl:0%->2%; Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Compl:2%->18%; Stat Rep: RP-240081->RP-240927; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[85,1022098,"   Perf. part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240791","RP-240927","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Stat Rep: RP-240081->RP-240927; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[86,1030045,"Indirect Network Sharing ",null,1,"Rel-19",null,"2022-03-10","2024-12-12",0.81,null,null,null,null,null,null,103,52,null,null,"2024-03-13","NA"]
[87,950006,"   Study on Network Sharing Aspects ","FS_NetShare",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100",22.850999999999999,95,48,null,null,"2022-03-10","2023-09-06"]
[88,1000029,"   (Stage 1 of) Indirect Network Sharing ","NetShare",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-09-06"]
[89,1030011,"   (Stage 2 of) Indirect Network Sharing ","TEI19_NetShare",2,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240488",null,"Xing, Tianqi, China Unicom, ","xingtq@chinaunicom.cn ","; 13/6/24: FCD:12/12/2024->06/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[90,1040019,"   Charging enhancement for indirect network sharing ","NetShare_CH",2,"Rel-19","S5","2024-06-12","2024-12-12",0,"SP-241004",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ",null,"32.240; 32.255; 32.256 ",null,null,null,null,"2024-06-12","NA"]
[91,1030046,"Roaming Value-Added Services ",null,1,"Rel-19",null,"2022-06-02","2024-06-06",1,null,null,null,null,null,null,103,52,null,null,"2024-03-13","NA"]
[92,960015,"   Study on roaming value added services ","FS_RVAS",2,"Rel-19","S1","2022-06-02","2022-12-12",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100",22.876999999999999,96,49,null,null,"2022-06-02","2022-12-10"]
[93,990051,"   Roaming Value-Added Services ","RVAS",2,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[94,1030013,"   Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240119",null,"Qian Chen, Ericsson, ","qian.xb.chen@ericsson.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[95,0,"Rel-19 user plane","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[96,1040022,"Study on Spatial Computing for AR Services ","FS_ARSpatial",1,"Rel-19","S4","2024-06-06","2025-06-06",0,"SP-240927",null,"Hamza, Ahmed, InterDigital Canada ","<Ahmed.Hamza@InterDigital.com> ",null,null,null,null,null,null,"2024-06-12","NA"]
[97,1040021,"EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 ","IVAS_Codec_Ph2",1,"Rel-19","S4","2024-06-06","2025-06-06",0,"SP-241000",null,"Su, Huan-yu, Huawei Technologies Co Ltd., ","su.huanyu@huawei.com ",null,"26.114; 26.117; 26.119; 26.249; 26.250; 26.252; 26.253; 26.258; 26.997 ",null,null,null,null,"2024-06-12","NA"]
[98,1040020,"Study on Haptics in 5G Media Services ","FS_HapticsMed",1,"Rel-19","S4","2024-06-12","2025-03-03",0,"SP-240979",null,"Gaëlle Martin-Cocher, InterDigital ","Gaelle.Martin-Cocher@InterDigital.com",null,null,null,null,null,null,"2024-06-12","NA"]
[99,1040035,"UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2024-06-12","NA"]
[100,1030002,"Video Operating Points - Harmonization and Stereo MV-HEVC ","VOPS",1,"Rel-19","S4","2024-03-13","2025-03-03",0.15,"SP-240060",null,"Waqar Zia ","waqar_zia (at) apple.com ","14/5/24: 26.265 added;; 13/6/24: 0%->15",26.265000000000001,103,52,null,null,"2024-03-13","2024-06-13"]
[101,1030003,"Split rendering over IMS ","SR_IMS",1,"Rel-19","S4","2024-04-02","2025-03-03",0.1,"SP-240492",null,"He, Shane, Nokia Corporation ","shane.he@nokia.com ","; 14/5/24: 26.567 added;; 13/6/24: 0%->10","26.264 ; 26.567",103,52,null,null,"2024-03-13","2024-06-13"]
[102,1030005,"Study on Media Messaging ","FS_MeMe",1,"Rel-19","S4","2024-04-02","2025-03-03",0.1,"SP-240477",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","13/6/24: 0%->10; 13/6/24: FCD:12/12/2024->/25",null,103,52,null,null,"2024-03-13","2024-06-13"]
[103,1030006,"Study on Advanced Media Delivery ","FS_AMD",1,"Rel-19","S4","2024-04-02","2024-12-12",0.15,"SP-241011",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-240478->SP-241011","26.802; 26.804 ",103,52,null,null,"2024-03-13","2024-07-16"]
[104,1030007,"Study of 5G Real-time Transport Protocol Configurations, Phase 2 ","FS_5G_RTP_Ph2",1,"Rel-19","S4","2024-04-02","2024-12-12",0.4,"SP-240482",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","14/5/24: 26.822 added;; 13/6/24: 0%->40",26.821999999999999,103,52,null,null,"2024-03-13","2024-06-13"]
[105,1030008,"Study on Beyond 2D Video ","FS_Beyond2D",1,"Rel-19","S4","2024-04-02","2025-06-06",0.1,"SP-240479",null,"Jiayi Xu, ","xujiayi@chinamobile.com ","14/5/24: 26.956 added;; 13/6/24: 0%->10",26.956,103,52,null,null,"2024-03-13","2024-06-13"]
[106,1030009,"Study on Audio Codec APIs ","FS_ACAPI",1,"Rel-19","S4","2024-04-02","2025-03-03",0.1,null,null,"Stefan Döhla ","(stefan DOT doehla AT iis DOT fraunhofer DOT de) ","14/5/24: 26.858 added;; 13/6/24: 0%->10",26.858000000000001,103,52,null,null,"2024-03-13","2024-06-13"]
[107,0,"Rel-19 Non Public Network","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[108,1000027,"Non-Public Network (NPN) security considerations ","SecNPN",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,22.260999999999999,100,51,null,null,"2023-06-08","NA"]
[109,1020039,"Study on security for PLMN hosting a NPN ","PLMNNPN_SEC",1,"Rel-19","S3","2024-01-03","2024-09-09",0.7,"SP-231786",null,"Jun Shen","shenjun6@chinatelecom.cn","4/1/24: 33.757 added;; 14/3/24: 0%->25; 13/6/24: 25%->70",33.756999999999998,102,52,null,null,"2023-12-07","2024-06-13"]
[110,1030016,"ProSe support in NPN ","TEI19_ProSe_NPN",1,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"2024-03-13","2024-06-13"]
[111,0,"Rel-19 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[112,1030077,"UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4",1,"Rel-19","R4","2024-03-03","2026-03-03",0.09,"RP-240828",null,"Huawei ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[113,1031077,"   Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.2,"RP-240828","RP-241236","Huawei ",null,"13/6/24: Compl:0%->20%; Stat Rep: ->RP-241236; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[114,1032077,"   Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240828",null,"Huawei ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[115,1030082,"Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2",1,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240838",null,"KDDI ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[116,1031082,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0,"RP-240838",null,"KDDI ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[117,1032082,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240838",null,"KDDI ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[118,1030085,"TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3",1,"Rel-19","R4","2024-03-03","2026-03-03",0.04,"RP-240841",null,"Vivo ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[119,1031085,"   Core part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.1,"RP-240841","RP-241043","Vivo ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241043; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[120,1032085,"   Perf. part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240841","RP-241043","Vivo ",null,"13/6/24: Stat Rep: ->RP-241043; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[121,0,"Rel-19 other topics","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[122,1040082,"Monitoring of signalling traffic in 5G ","MonSTra",1,"Rel-19","S1","2024-05-06","2024-06-06",1,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100",22.260999999999999,null,null,null,null,"2024-06-12","2024-06-12"]
[123,1040071,"Study on MC services support on IOPS mode of operation for 5G ","FS_Generic_IOPS",1,"Rel-19","S6","2024-07-16","2025-06-06",0,"SP-241017",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ",null,null,null,null,null,null,"2024-06-12","NA"]
[124,1040036,"Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240996",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.548; 23.503 ",null,null,null,null,"2024-06-12","NA"]
[125,1020004,"Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","FS_eEDGE_5GC_Ph3",1,"Rel-19","S2","2024-01-04","2024-09-09",0.9,"SP-240962",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 16/7/24: WID:SP-231796->SP-240962",null,102,52,null,null,"2024-01-03","2024-07-16"]
[126,1030036,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","FS_EDGE_Ph3",1,"Rel-19","S3","2024-04-02","2024-12-12",0.3,"SP-240510",null,"Ge Yao, ","yaog9@chinaunicom.cn ","3/4/24: 33.749 added;; 13/6/24: 0%->30",33.749000000000002,103,52,null,null,"2024-03-14","2024-06-13"]
[127,1040034,"Multi-Access (ATSSS_Ph4) ","MASSS",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240994",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2024-06-12","NA"]
[128,1020070,"Study on Multi-Access (DualSteer and ATSSS_Ph4) ","FS_MASSS",1,"Rel-19","S2","2024-01-04","2024-09-09",0.7,"SP-240467",null,"Krisztian Kiss (Apple) ","krisztian@apple.com ","14/3/24: 0%->30; 2/4/24: WID:SP-231802->SP-240467; 2/4/24: FCD:09/09/2024->/24; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 30%->70",null,102,52,null,null,"2024-01-03","2024-06-13"]
[129,1030037,"Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) ","FS_MASSS_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",0.45,"SP-240511",null,"Kolekar, Abhijeet (Intel) ","abhijeet.kolekar@intel.com ","3/4/24: 33.754 added;; 13/6/24: 0%->45",33.753999999999998,103,52,null,null,"2024-03-14","2024-06-13"]
[130,1040026,"System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240985",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985","23.228; 23.502 ",null,null,null,null,"2024-06-12","2024-07-16"]
[131,1010030,"Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",1,"Rel-19","S2","2023-09-20","2024-09-09",0.95,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15; 14/3/24: 15%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->95","23.700-77",101,51,null,null,"2023-09-20","2024-06-13"]
[132,1040016,"Study on Charging aspects of next generation real time communication services phase 2 ","FS_NG_RTC_Ph2_CH",1,"Rel-19","S5","2024-06-12","2024-12-12",0.1,"SP-240982",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","13/6/24: 0%->10",null,null,null,null,null,"2024-06-12","2024-06-13"]
[133,1030040,"AKMA service disabling in roaming ","AKMA_Disable",1,"Rel-18","S3","2024-02-02","2024-03-03",1,"SP-240246",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","15/3/24: 0%->100",null,103,52,null,null,"2024-03-14","2024-03-15"]
[{"$f":"A134+1","v":134},1030010,"On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",1,"Rel-19","S2","2024-04-02","2024-12-12",0,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ",null,"23.502; 23.273 ",103,52,null,null,"2024-03-13","NA"]
[135,1030012,"Minimize the Number of Policy Associations ","TEI19_MINPA",1,"Rel-19","S2","2024-06-17","2025-03-03",0.33,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ",null,"23.502; 23.501; 23.503 ",103,52,null,null,"2024-03-13","NA"]
[136,1040078,"   Stage 2 of Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","S2","2024-06-17","2025-03-03",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ","13/6/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-06-13"]
[137,1040004,"   CT Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","C4","2024-06-17","2025-03-03",0,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"TS 29.503,TS 29.507,TS 29.513,TS 29.518,TS 29.525",101,51,null,null,"2023-09-06","2023-09-06"]
[138,1040052,"      CT3 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C3","2024-06-17","2025-03-03",0,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[139,1040053,"      CT4 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C4","2024-06-17","2025-03-03",0,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[140,1030014,"Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",1,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"2024-03-13","2024-06-13"]
[141,1030015,"Enhancing Parameter Provisioning with static UE IP address and UP security policy ","TEI19_IP_SP_EXP",1,"Rel-19","S2","2023-12-26","2025-06-06",0,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"2024-03-13","NA"]
[142,1040079,"   Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","S2","2023-12-26","2024-12-12",0,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20",null,101,51,null,null,"2023-09-06","2024-06-19"]
[143,1040007,"   CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","C3","2024-06-17","2025-06-06",0,"CP-241297",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.522,29.503,29.522",101,51,null,null,"2023-09-06","2023-09-06"]
[144,1040056,"      CT3 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C3","2024-06-17","2025-06-06",0,"CP-241297",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[145,1040057,"      CT4 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C4","2024-06-17","2025-06-06",0,"CP-241297",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[146,1030017,"Multiple Location Procedure for Emergency LCS Routing ","TEI19_MLR4RTR",1,"Rel-19","S2","2024-03-13","2024-12-12",0,"SP-240123",null,"Simon Cai (Nokia Shanghai-Bell)Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","Simon<dot>Ca<at> nokia<dash>sbell<dot>com ",null,23.273,103,52,null,null,"2024-03-13","NA"]
[147,1030018,"Roaming traffic offloading via session breakout in HPLMN ","TEI19_HSBO",1,"Rel-19","S2","2024-04-02","2024-12-12",0,"SP-240491",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ",null,23.501000000000001,103,52,null,null,"2024-03-13","NA"]
[148,1030019,"Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",1,"Rel-19","S2","2024-03-13","2024-12-12",0,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ",null,23.273,103,52,null,null,"2024-03-13","NA"]
[149,1030020,"QoS monitoring enhancement ","TEI19_QME",1,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-07-16"]
[150,1030021,"Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",1,"Rel-19","S2","2024-03-13","2024-12-12",0,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ",null,23.401,103,52,null,null,"2024-03-13","NA"]
[151,1030022,"Providing per-subscriber VLAN instructions from UDM and DN-AAA ","TEI19_VLANSUB",1,"Rel-19","S2","2023-12-26","2025-06-06",0,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"2024-03-13","NA"]
[152,1040080,"   Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","S2","2023-12-26","2024-12-12",0,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20",null,101,51,null,null,"2023-09-06","2024-06-19"]
[153,1040006,"   CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","C3","2024-06-17","2025-06-06",0,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.561,29.503,29.561",101,51,null,null,"2023-09-06","2023-09-06"]
[154,1040054,"      CT3 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C3","2024-06-17","2025-06-06",0,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[155,1040055,"      CT4 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C4","2024-06-17","2025-06-06",0,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[156,1030023,"NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",1,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[157,1020057,"Integrated Sensing and Communication ","Sensing",1,"Rel-19",null,"2022-03-10","2023-12-12",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[158,950003,"   Study on Integrated Sensing and Communication ","FS_Sensing",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",22.837,95,48,null,null,"2022-03-10","2023-09-06"]
[159,1000026,"   Stage 1 of Integrated Sensing and Communication ","Sensing",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[160,1020086,"Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR",1,"Rel-19","R1","2023-12-13","2025-06-06",0.22,"RP-240799","RP-241164","Yingyang Li, Jerome Vogedes, Xiaomi, AT&T","liyingyang@xiaomi.com, jerome.vogedes@att.com","14/3/24: Compl:0%->6%; Stat Rep: ->RP-240114; Rapporteur: Xiaomi->Yingyang Li, Jerome Vogedes, Xiaomi, AT&T; Rap eMail: ->liyingyang@xiaomi.com, jerome.vogedes@att.com; ; 2/4/24: WID:RP-234069->RP-240799; 13/6/24: Compl:6%->22%; Stat Rep: RP-240114->RP...",null,102,52,null,null,"2024-01-02","2024-06-13"]
[161,1020059,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19",null,"2022-06-02","2025-09-09",0.47,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[162,960017,"   Study on (Stage 1 of) UAV Phase 3 ","FS_UAV_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[163,1020069,"   Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM ","FS_UAS_Ph3",2,"Rel-19","S2","2024-01-04","2024-09-09",0.9,"SP-231801",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90",null,102,52,null,null,"2024-01-03","2024-06-13"]
[164,1000032,"   Stage 1 of Uncrewed Aerial System Phase 3 ","UAS_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[165,1040037,"   (Stage 2 of) UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240997",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ",null,"23.256; 23.288; 23.503; 23.502; 23.401 ",null,null,null,null,"2024-06-12","NA"]
[166,1010008,"   Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",2,"Rel-19","S6","2023-09-07","2024-12-12",0.6,"SP-240741",null,"Roy, Michel, InterDigital ","michel.roy@interdigital.com","; 8/12/23: 0%->20; 14/3/24: 20%->40; 13/6/24: 40%->60; 16/7/24: WID:SP-230991->SP-240741","23.255; 23.434 ",101,51,null,null,"2023-09-07","2024-07-16"]
[167,1040043,"   CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[168,1040069,"      CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[169,1040070,"      CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C3","2024-06-17","2025-09-09",0,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[170,1030033,"   UAS security enhancements ","FS_UAS_Ph3_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.5,"SP-240504",null,"Markus Hanhisalo, ","markus.hanhisalo@ericsson.com ","3/4/24: 33.759 added;; 13/6/24: 0%->50",33.759,103,52,null,null,"2024-03-14","2024-06-13"]
[171,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.841000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[172,1040017,"Study on Charging aspects of Uncrewed Aerial Systems ","FS_UAS_CH",1,"Rel-19","S5","2024-06-12","2024-12-12",0,"SP-240983",null,"Jia Dong, China Mobile, ","dongjia@chinamobile.com ",null,null,null,null,null,null,"2024-06-12","NA"]
[173,1020031,"Upper layer traffic steering and switching over dual 3GPP access ","DualSteer",1,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231412",null,"Pica Francesco, Qualcomm ","fpica<at>qti.qualcomm.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[174,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[175,1020002,"Study on System aspects of 5G NR Femto ","FS_5G_Femto",1,"Rel-19","S2","2024-01-04","2024-09-09",0.9,"SP-231797",null,"Malla Reddy Sama (NTT DOCOMO) ","sama@docomolab-euro.com ","14/3/24: 0%->40; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->90",null,102,52,null,null,"2024-01-03","2024-06-13"]
[176,1040028,"System aspects of 5G NR Femto ","5G_Femto",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240629",null,"Malla Reddy Sama ","sama@docomolab-euro.com ",null,"23.501; 23.502 ",null,null,null,null,"2024-06-12","NA"]
[177,1030028,"Study on security aspects of 5G NR Femto Document for: Approval ","FS_5G_Femto_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",0.3,"SP-240505",null,"Peilin LIU (ZTE) ","liu.peilin@zte.com.cn , ","3/4/24: 33.745 added;; 13/6/24: 0%->30",33.744999999999997,103,52,null,null,"2024-03-14","2024-06-13"]
[178,1020066,"Study on Proximity-based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3",1,"Rel-19","S2","2024-01-04","2024-09-09",0.9,"SP-231798",null,"Hugh Shieh (AT&T) ","hs6220@att.com ","14/3/24: 0%->45; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 45%->90",null,102,52,null,null,"2024-01-03","2024-06-13"]
[179,1040030,"Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240988",null,"Hugh Shieh (AT&T) ","hs6220@att.com ",null,23.303999999999998,null,null,null,null,"2024-06-12","NA"]
[180,1030034,"Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3_SEC",1,"Rel-19","S3","2024-04-02","2024-12-12",0.3,"SP-240513",null,"Lei, Ao (Huawei) ","leiao@huawei.com ","3/4/24: 33.743 added;; 13/6/24: 0%->30",33.743000000000002,103,52,null,null,"2024-03-14","2024-06-13"]
[181,1020067,"Study on Vehicle Mounted Relays Phase 2 ","FS_VMR_Ph2",1,"Rel-19","S2","2024-01-04","2024-09-09",0.95,"SP-240493",null,"Primary Rapporteur: Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","14/3/24: 0%->40; 2/4/24: WID:SP-231799->SP-240493; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->95",null,102,52,null,null,"2024-01-03","2024-06-13"]
[182,1040031,"Vehicle Mounted Relays Phase 2 ","VMR_Ph2",1,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ",null,"23.501; 23.502; 23.273 ",null,null,null,null,"2024-06-12","NA"]
[183,1020063,"Study on User Identities and Authentication Architecture ","FS_UIA_ARC",1,"Rel-19","S2","2024-01-04","2024-09-09",0.9,"SP-231804",null,"Michael Starsinic, Interdigital ","Michael.Starsinic@Interdigital.com ","14/3/24: 0%->35; 14/3/24: 23.700-32 added;; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 35%->90","23.700-32",102,52,null,null,"2024-01-03","2024-06-13"]
[184,1040085,"Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",1,"Rel-19","S2","2024-06-20","2024-12-12",0,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com",null,null,null,null,null,null,"2024-06-20","NA"]
[185,1030032,"Study on security aspects of User Identities and Authentication ","FS_UIA_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",0.35,"SP-240507",null,"Samir Ferdi, ","Samir.Ferdi@InterDigital.com ","3/4/24: 33.700-32 added;; 13/6/24: 0%->35","33.700-32",103,52,null,null,"2024-03-14","2024-06-13"]
[186,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-220437",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.989000000000001,95,48,null,null,"2022-03-10","2023-12-08"]
[187,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","2023-06-08","2024-12-12",0.55000000000000004,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50; 8/12/23: 50%->100","22.280; 22.179; 22.289; 22.261 ",100,51,null,null,"2023-06-08","2023-12-08"]
[188,1000038,"   Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","S6","2023-06-08","2024-12-12",0.55000000000000004,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10; 8/12/23: 10%->30; 14/3/24: 30%->40. 14/5/24: acronym: enh4FRMCS ->FRMCS_Ph5 ; 13/6/24: 40%->55","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2024-06-13"]
[189,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","2019-09-19","2022-09-08",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"2019-09-13","2022-09-09"]
[190,1020003,"Study on UPF enhancement for Exposure And SBA Phase 2 ","FS_UPEAS_Ph2",1,"Rel-19","S2","2024-01-04","2024-06-06",1,"SP-231795",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","14/3/24: 0%->45; 13/6/24: 45%->100",null,102,52,null,null,"2024-01-03","2024-06-13"]
[191,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","2022-06-02","2023-12-12",1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.916,96,49,null,null,"2022-06-02","2023-12-08"]
[192,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","2023-06-08","2024-12-12",0.4,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65",22.847999999999999,99,50,null,null,"2023-03-16","2023-12-08"]
[193,1030041,"Interconnect of SNPN ","ISN",1,"Rel-19","S1","2024-03-13","2024-03-29",1,"SP-240194",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 14/3/24: 0%->100",22.260999999999999,103,52,null,null,"2024-03-13","2024-03-14"]
[194,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100",22.103999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[195,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100",22.010999999999999,99,50,null,null,"2023-03-16","2023-08-09"]
[196,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[197,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,51,null,null,"2023-06-08","2023-06-08"]
[{"$f":"A198+1","v":198},970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[199,1040083,"MPS for Messaging services ","MPS4msg",1,"Rel-19",null,"2022-09-01","2024-12-12",0.49,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[200,970042,"   (stage 1 of) MPS for Messaging services ","MPS4msg",2,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[201,1040029,"   (stage 2 of) MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","S2","2024-06-12","2024-12-12",0,"SP-240987",null,"Robert Streijl (Peraton Labs), ","rstreijl@peratonlabs.com ",null,"23.401; 23.203; 23.501; 23.502; 23.503; 23.682; 23.204; 23.272; 23.228 ",null,null,null,null,"2024-06-12","NA"]
[202,1010031,"   Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",2,"Rel-19","S2","2024-01-03","2024-06-06",0.99,"SP-231197",null,"Robert Streijl (Peraton Labs) ","rstreijl@peratonlabs.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20; 14/3/24: 0%->70; 13/6/24: 70%->100","23.700-75",101,51,null,null,"2023-09-20","2024-06-13"]
[203,970041,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[204,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","2022-12-09","2022-12-20",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100",22.260999999999999,98,50,null,null,"2022-12-09","2022-12-10"]
[205,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[206,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","2022-12-13","2024-09-09",0.85,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45; 14/3/24: 45%->70; 13/6/24: 70%->85",26.933,98,50,null,null,"2022-12-09","2024-06-13"]
[207,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","2023-06-08","2024-09-09",0.7,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->35; 13/6/24: 35%->70","23.222 ; 23.700-92",100,51,null,null,"2023-06-08","2024-06-13"]
[208,1040073,"Application enablement aspects for MMTel ","MMTel_App",1,"Rel-19","S6","2024-07-16","2024-12-12",0,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,null,null,null,null,null,"2024-06-12","NA"]
[209,1000035,"Study on enhanced application layer support for location services ","FS_eLSAPP",1,"Rel-19","S6","2023-06-08","2024-09-09",0.85,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25; 14/3/24: 25%->40; 2/4/24: WID:SP-230778->SP-240295; 2/4/24: FCD:05/06/2024->/24; 13/6/24: 40%->85; 13/6/24: WID:SP-240295->SP-230778","23.434 ; 23.700-72",100,51,null,null,"2023-06-08","2024-06-13"]
[210,1040072,"Enhanced application layer support for location services ","eLSAPP",1,"Rel-19","S6","2024-06-12","2024-12-12",0,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,"23.434; 23.436 ",null,null,null,null,"2024-06-12","NA"]
[211,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.9,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5; 8/12/23: 5%->40; 14/3/24: 40%->90; 13/6/24: 90%->90","23.280; 23.379; 23.281; 23.282 ",100,51,null,null,"2023-06-08","2024-06-13"]
[212,1000037,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19","S6","2023-06-08","2024-09-09",0.4,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40",null,100,51,null,null,"2023-06-08","2024-06-13"]
[213,1030030,"Security aspects for MSGin5G Service Phase 3 ","5GMARCH_SEC_Ph3",1,"Rel-19","S3","2024-04-02","2024-12-12",0.7,"SP-240516",null,"Xiaoting Huang, ","huangxiaoting@chinamobile.com ","; 13/6/24: 0%->70",33.500999999999998,103,52,null,null,"2024-03-14","2024-06-13"]
[214,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","2023-06-08","2024-12-12",0.6,"SP-230988",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30; 14/3/24: 30%->40; 13/6/24: 40%->60","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2024-06-13"]
[215,1010006,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19","S6","2023-09-07","2024-12-12",0.7,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70",null,101,51,null,null,"2023-09-07","2024-06-13"]
[216,1040081,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19",null,"2023-09-07","2025-09-09",0.56999999999999995,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35",23.558,101,51,null,null,"2023-09-07","2024-03-14"]
[217,1010007,"   Stage 2 of enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",2,"Rel-19","S6","2023-09-07","2024-12-12",0.8,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35; 13/6/24: 35%->80",23.558,101,51,null,null,"2023-09-07","2024-06-13"]
[218,1040008,"   CT aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",2,"Rel-19","C3","2024-06-17","2025-06-06",0.44,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com",null,"24.558,29.558",101,51,null,null,"2023-09-06","2023-09-06"]
[219,1040058,"      CT1 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: FCD:06/06/2025->/25",null,101,51,null,null,"2023-09-06","2024-07-16"]
[220,1040059,"      CT3 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C3","2024-06-17","2025-06-06",1,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-07-16"]
[221,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-19","S6","2023-09-07","2024-09-09",0.8,"SP-231161",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ","8/12/23: 0%->20; 4/1/24: 23.946 added;; 14/3/24: 20%->55; 13/6/24: 55%->80",23.946000000000002,101,51,null,null,"2023-09-07","2024-06-13"]
[222,1020062,"Study on CAPIF Phase 3 ","FS_CAPIF_Ph3",1,"Rel-19","S6","2024-01-04","2024-09-09",0.55000000000000004,"SP-231741",null,"Preciado Rojas, Diego, Nokia ","diego.preciado_rojas@nokia.com ","14/3/24: 0%->20; 3/4/24: 23.700-22 added;; 13/6/24: 20%->55","23.700-22",102,52,null,null,"2024-01-03","2024-06-13"]
[223,1040025,"Study on security aspects of CAPIF Phase 3 ","FS_CAPIF_Ph3-sec",1,"Rel-19","S3","2024-06-12","2024-12-12",0,"SP-240654",null,"Henry Leung ( Xiaomi) ","lianghaoran@xiaomi.com ",null,null,null,null,null,null,"2024-06-12","NA"]
[224,1040015,"Study on Charging Aspects of CAPIF ","FS_CAPIF_CH",1,"Rel-19","S5","2024-06-12","2024-12-12",0.15,"SP-240981",null,"João Rodrigues, Nokia, ","joao.a.rodrigues@nokia.com ","13/6/24: 0%->15",null,null,null,null,null,"2024-06-12","2024-06-13"]
[225,0,"Rel-19 miscellaneous Security",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[226,1030029,"Security Assurance Specification for maintenance of 5G features ","SCAS_5G_Maint",1,"Rel-19","S3","2024-04-02","2025-03-03",0,"SP-240515",null,"Rong Wu (Huawei) ","raina.wu@huawei.com ",null,null,103,52,null,null,"2024-03-14","NA"]
[227,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","2023-09-06","2024-09-09",0.5,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 8/12/23: 0%->10; 3/4/24: 33.530 added;; 13/6/24: 10%->50","33.926 ; 33.530",101,51,null,null,"2023-09-06","2024-06-13"]
[228,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","2023-09-06","2024-09-09",0.7,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in","8/12/23: 0%->10; 4/1/24: 33.529 added;; 14/3/24: 10%->40; 13/6/24: 40%->70",33.529000000000003,101,51,null,null,"2023-09-06","2024-06-13"]
[229,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","2023-09-06","2024-03-03",1,"SP-240476",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ","8/12/23: 0%->10; 4/1/24: 35.248 added;; 14/3/24: 10%->100; 2/4/24: WID:SP-231159->SP-240476","35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240",101,51,null,null,"2023-09-06","2024-04-02"]
[230,1020036,"Addition of Milenage-256 algorithm ","Milenage_256",1,"Rel-19","S3","2024-01-03","2024-12-12",0.05,"SP-231792",null,"Mireille Pauliac ","mireille.pauliac@thalesgroup.com ","4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;; 14/3/24: 0%->5","35.237; 35.236; 35.235; 35.234",102,52,null,null,"2023-12-07","2024-03-14"]
[231,1020041,"Study on enabling a cryptographic algorithm transition to 256-bits ","FS_CAT256",1,"Rel-19","S3","2024-01-03","2024-12-12",0.9,"SP-231788",null,"Yuto Nakano ","yt-nakano@kddi.com ","4/1/24: 33.700-41 added;; 14/3/24: 0%->10; 13/6/24: 10%->90","33.700-41",102,52,null,null,"2023-12-07","2024-06-13"]
[232,1020034,"Study on enablers for Zero Trust Security ","FS_eZTS",1,"Rel-19","S3","2024-01-03","2024-12-12",0.5,"SP-231784",null,"Sheeba Backia Mary Baskaran ","smary@lenovo.com ","4/1/24: 33.794 added;; 14/3/24: 0%->20; 13/6/24: 20%->50",33.793999999999997,102,52,null,null,"2023-12-07","2024-06-13"]
[233,1020035,"Mission critical security enhancements for release 19 ","MCXSec4",1,"Rel-19","S3","2024-01-04","2024-12-12",0.1,"SP-231783",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 14/3/24: 0%->10",33.18,102,52,null,null,"2023-12-07","2024-03-14"]
[234,1020038,"Study on the security support for the Next Generation Real Time Communication services phase 2 ","FS_NG_RTC_SEC_Ph2",1,"Rel-19","S3","2024-01-03","2024-12-12",0.4,"SP-240233",null,"Vlasios Tsiatsis ","vlasios.tsiatsis@ericsson.com ","4/1/24: 33.790 added;; 14/3/24: 0%->17; 2/4/24: WID:SP-231785->SP-240233; 13/6/24: 17%->40",33.79,102,52,null,null,"2023-12-07","2024-06-13"]
[235,1020040,"Study of ACME for Automated Certificate Management in SBA ","FS_ACME_SBA",1,"Rel-19","S3","2024-01-03","2024-12-12",0.45,"SP-231787",null,"Charles Eckel ","eckelcu(at)cisco.com ","4/1/24: 33.776 added;; 14/3/24: 0%->15; 13/6/24: 15%->45; 13/6/24: FCD:06/06/2024->12/24",33.776000000000003,102,52,null,null,"2023-12-07","2024-06-13"]
[236,1020042,"3GPP profiles for cryptographic algorithms and security protocols ","CryptoSP",1,"Rel-19","S3","2024-01-03","2024-12-12",0.5,"SP-231793",null,"Mohsin Khan A ","mohsin.a.khan@ericsson.com ","; 14/3/24: 0%->20; 13/6/24: 20%->50","33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 ",102,52,null,null,"2023-12-07","2024-06-13"]
[237,1020043,"Study on mitigations against bidding down attacks ","FS_MiBiDA",1,"Rel-19","S3","2024-01-03","2024-12-12",0.85,"SP-231789",null,"Noamen Ben Henda ","noamen.ben.henda@huawei.com ","4/1/24: 33.701 added;; 14/3/24: 0%->20; 13/6/24: 20%->85; 13/6/24: FCD:05/06/2024->12/24",33.701000000000001,102,52,null,null,"2023-12-07","2024-06-13"]
[238,1020045,"Study on Security for mobility over non-3GPP access to avoid full primary authentication ","FS_Non3GPPMob_Sec",1,"Rel-19","S3","2024-01-03","2024-12-12",0.25,"SP-231791",null,"Saurabh Khare, Nokia ","Saurabh.Khare@nokia.com ","4/1/24: 33.702 added;; 14/3/24: 0%->25",33.701999999999998,102,52,null,null,"2023-12-07","2024-03-14"]
[239,1040024,"Security for mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",1,"Rel-19","S3","2024-06-12","2024-12-12",0,"SP-240653",null,"Khare, Saurabh ","saurabh.khare@nokia.com ",null,33.500999999999998,null,null,null,null,"2024-06-12","NA"]
[240,0,"Rel-19 miscellaneous OAM&charging",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[241,1020019,"Study on Management Data Analytics (MDA) Phase 3 ","FS_eMDAS_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0.7,"SP-240968",null,"Brendan T Hassett (Huawei) ","brendan.t.hassett@huawei.com ","13/6/24: 0%->70; 16/7/24: WID:SP-231726->SP-240968",null,102,52,null,null,"2023-12-07","2024-07-16"]
[242,1020008,"Study on intent driven management services for mobile network phase 3 ","FS_IDMS_MN_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0.7,"SP-231737",null,"Ruiyue Xu (Huawei) ","xuruiyue@huawei.com ","14/3/24: 0%->5; 13/6/24: 5%->70",null,102,52,null,null,"2023-12-07","2024-06-13"]
[243,1020009,"Study on closed control loop management ","FS_CCLM",1,"Rel-19","S5","2024-01-03","2024-09-09",0.4,"SP-231735",null,"Deepanshu Gautam (Samsung) ","deepanshu.g@samsung.com ","14/3/24: 0%->5; 13/6/24: 5%->40",null,102,52,null,null,"2023-12-07","2024-06-13"]
[244,1020018,"Study on management aspects of Network Digital Twin ","FS_NDT",1,"Rel-19","S5","2024-01-03","2024-09-09",0.65,"SP-231727",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com ","4/1/24: 28.915 added;; 14/3/24: 0%->5; 13/6/24: 5%->65; 13/6/24: WID:SP-231428->SP-231727",28.914999999999999,102,52,null,null,"2023-12-07","2024-06-13"]
[245,1020010,"Study on Cloud Aspects of Management and Orchestration ","FS_Cloud_OAM",1,"Rel-19","S5","2024-01-03","2024-09-09",0.4,"SP-231781",null,"Bahar Sadeghi (Microsoft) ","bahar.sadeghi@microsoft.com ","14/3/24: 0%->2; 13/6/24: 2%->40",null,102,52,null,null,"2023-12-07","2024-06-13"]
[246,1020016,"Study on Enablers for Security Monitoring ","FS_SECM",1,"Rel-19","S5","2024-01-03","2024-09-09",0,"SP-231736",null,"Clifton Fernandes (Nokia) ","clifton.fernandes@nokia.com ","4/1/24: 28.870 added;",28.87,102,52,null,null,"2023-12-07","2024-01-04"]
[247,1020011,"Study on Service Based Management Architecture enhancement phase 3 ","FS_SBMA_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0.45,"SP-231725",null,"Kai Zhang (Huawei) ","kai.zhangkai@huawei.com ","13/6/24: 0%->45",null,102,52,null,null,"2023-12-07","2024-06-13"]
[248,1020033,"Study on Management of planned configurations ","FS_PlanM",1,"Rel-19","S5","2024-01-04","2024-09-09",0.6,"SP-231721",null,"Olaf Pollakowski (Nokia) ","olaf.pollakowski@nokia.com ","4/1/24: 28.872 added;; 13/6/24: 0%->60",28.872,102,52,null,null,"2024-01-03","2024-06-13"]
[249,1020025,"Data management phase 2 ","MADCOL_Ph2",1,"Rel-19","S5","2024-01-03","2025-06-06",0.5,"SP-240877",null,"Sivaramakrishnan Swaminathan (Nokia) ","sivaramakrishnan.swaminathan@nokia.com ","; 13/6/24: 0%->50; 16/7/24: WID:SP-231746->SP-240877","28.622; 28.623 ",102,52,null,null,"2023-12-07","2024-07-16"]
[250,1020012,"Study on data management regarding subscriptions and reporting ","FS_Data_SREP",1,"Rel-19","S5","2024-01-03","2024-09-09",0.6,"SP-231732",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","13/6/24: 0%->60",null,102,52,null,null,"2023-12-07","2024-06-13"]
[251,1020026,"5G performance measurements and KPIs phase 4 ","PM_KPI_5G_Ph4",1,"Rel-19","S5","2024-01-03","2025-06-06",0.2,"SP-231747",null,"Primary Rapporteur: XiuMin Chen (China Telecom) ","chenxiumin@chinatelecom.cn ","; 13/6/24: 0%->20","28.552; 32.425; 28.554; 28.532; 28.550; 28.abc ",102,52,null,null,"2023-12-07","2024-06-13"]
[252,1020027,"5G Advanced NRM features phase 3 ","AdNRM_Ph3",1,"Rel-19","S5","2024-01-03","2025-06-06",0.15,"SP-240875",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-231745->SP-240875","28.540; 28.541; 28.622; 28.623 ",102,52,null,null,"2023-12-07","2024-07-16"]
[253,1020028,"Subscriber and Equipment Trace and QoE collection management ","TraceQoE_OAM",1,"Rel-19","S5","2024-01-03","2025-06-06",0.2,"SP-231748",null,"Zu Qiang (Ericsson) ","zu.qiang@ericsson.com ","; 13/6/24: 0%->20","32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 ",102,52,null,null,"2023-12-07","2024-06-13"]
[254,1020013,"Study on Management Aspects of NTN Phase 2 ","FS_NTN_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0.65,"SP-231733",null,"MingRui Sun (China Unicom) ","sunmr19@chinaunicom.cn ","13/6/24: 0%->65",null,102,52,null,null,"2023-12-07","2024-06-13"]
[255,1020014,"Study on management of IAB nodes ","FS_NR_mobile_IAB_OAM",1,"Rel-19","S5","2024-01-03","2024-12-12",0.4,"SP-231729",null,"JunFeng Wang (Ericsson) ","junfeng.a.wang@ericsson.com ","13/6/24: 0%->40; 13/6/24: FCD:09/09/2024->12/24",null,102,52,null,null,"2023-12-07","2024-06-13"]
[256,1020017,"Study on management aspects of RedCap feature ","FS_NR_RedCap_OAM",1,"Rel-19","S5","2024-01-03","2024-09-09",0.5,"SP-231734",null,"Zhen Xing (China Unicom) ","xingz12@chinaunicom.cn ","13/6/24: 0%->50",null,102,52,null,null,"2023-12-07","2024-06-13"]
[257,1020020,"Study on Enhancement of Management Aspects related to NWDAF Phase 2 ","FS_NWDAF_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",0.75,"SP-231724",null,"Primary Rapporteur: Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","13/6/24: 0%->75",null,102,52,null,null,"2023-12-07","2024-06-13"]
[258,1020015,"Study on Management of Network Sharing Phase3 ","FS_NetShare_OAM_Ph3",1,"Rel-19","S5","2024-01-03","2024-09-09",0.5,"SP-240966",null,"ZhaoNing Wang (China Unicom) ","wangzn18@chinaunicom.cn ","13/6/24: 0%->50; 16/7/24: WID:SP-231731->SP-240966",null,102,52,null,null,"2023-12-07","2024-07-16"]
[259,1020022,"Study on Enhanced OAM for management exposure to external consumers ","FS_MExpo",1,"Rel-19","S5","2024-01-03","2024-09-09",0.5,"SP-240967",null,"Srilakshmi Srinivasaraju (Nokia)","srilakshmi.s@nokia.com","14/3/24: 0%->5; 13/6/24: 5%->50; 16/7/24: WID:SP-231728->SP-240967",null,102,52,null,null,"2023-12-07","2024-07-16"]
[260,0,"Rel-19 NR-only: topics other than band",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[261,1020081,"Study on channel modelling enhancements for 7-24GHz for NR ","FS_NR_7_24GHz_CHmod",1,"Rel-19","R1","2023-12-13","2025-06-06",0.15,"RP-234018","RP-241099","LEE Daewon, Intel Corporation","daewon.lee@intel.com","14/3/24: Stat Rep: ->RP-240265; Rapporteur: Intel->LEE Daewon, Intel Corporation; Rap eMail: ->daewon.lee@intel.com; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240265->RP-241099; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[{"$f":"A262+1","v":262},1020082,"Study on additional topological enhancements for NR ","FS_NR_WAB_5GFemto",1,"Rel-19","R3","2023-12-12","2024-09-09",0.7,"RP-240319","RP-241263","Min, Tianyang, NTT DOCOMO","tianyang.min.ex@nttdocomo.com","14/3/24: FCD:28/05/2021->09/09/2024; Stat Rep: ->RP-240320; Rapporteur: NTT DOCOMO->Min, Tianyang, NTT DOCOMO; Rap eMail: ->tianyang.min.ex@nttdocomo.com; ; 2/4/24: WID:RP-234041->RP-240319; 3/4/24: 38.799 added;; 13/6/24: Compl:0%->70%; Stat Rep: RP-2...",38.798999999999999,102,52,null,null,"2024-01-02","2024-06-13"]
[263,1020089,"NR MIMO Phase 5 ","NR_MIMO_Ph5",1,"Rel-19",null,"2023-12-13","2026-03-03",0.15,"RP-240087",null,"Samsung ",null,"2/4/24: WID:RP-234007->RP-240087",null,102,52,null,null,"2024-01-02","2024-04-02"]
[264,1021089,"   Core part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.35,"RP-234007","RP-241051","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Compl:0%->15%; Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: Compl:15%->35%; WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[265,1022089,"   Perf. part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-234007","RP-241051","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[266,1020090,"Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo",1,"Rel-19",null,"2023-12-13","2026-03-03",0.08,"RP-240789",null,"Huawei ",null,"2/4/24: WID:RP-234035->RP-240789",null,102,52,null,null,"2024-01-02","2024-04-02"]
[267,1021090,"   Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.18,"RP-240789","RP-241286","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Compl:7%->18%; Stat Rep: RP-240171->RP-241286; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[268,1022090,"   Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240789","RP-241286","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Stat Rep: RP-240171->RP-241286; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[269,1020091,"NR mobility enhancements Phase 4 ","NR_Mob_Ph4",1,"Rel-19",null,"2023-12-13","2026-03-03",0.02,"RP-240299",null,"Apple ",null,"2/4/24: WID:RP-234036->RP-240299",null,102,52,null,null,"2024-01-02","2024-04-02"]
[270,1021091,"   Core part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.05,"RP-240299","RP-241514","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Compl:0%->5%; Stat Rep: RP-240298->RP-241514; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[271,1022091,"   Perf. part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240299","RP-241514","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Stat Rep: RP-240298->RP-241514; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[272,1040023,"   Security aspects of NR mobility enhancement Phase 4 ","NR_Mob_Ph4_Sec",2,"Rel-19","S3","2024-07-16","2025-03-03",0,"SP-240652",null,"Rajavelsamy R ","rajvel@samsung.com ",null,33.500999999999998,null,null,null,null,"2024-07-16","NA"]
[273,1020092,"Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4",1,"Rel-19",null,"2023-12-13","2025-09-09",0.15,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[274,1021092,"   Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4-Core",2,"Rel-19","R3","2023-12-13","2025-09-09",0.15,"RP-234038","RP-241081","Xufei Dong, China Unicom","dongxf37@chinaunicom.cn","14/3/24: Stat Rep: ->RP-240118; Rapporteur: China Unicom->Xufei Dong, China Unicom; Rap eMail: ->dongxf37@chinaunicom.cn; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240118->RP-241081; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[275,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-19","RP","2017-12-15","2024-03-03",1,"RP-234033","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R...","37.890; 37.107",78,40,null,null,"2018-01-08","2024-04-02"]
[276,1030074,"Study on NR FR2 OTA (Over the Air) testing Phase 3 ","FS_NR_FR2_OTA_Ph3",1,"Rel-19","R4","2024-03-03","2025-09-09",0.3,"RP-240856","RP-241157","Qualcomm ",null,"13/6/24: Compl:0%->30%; Stat Rep: SI ->RP-241157; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[277,1030075,"Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz ","FS_NR_IMT_4400_7125_14800MHz",1,"Rel-19","R4","2019-03-07","2021-03-09",0,"RP-240787","SI ","Ericsson ",null,"14/5/24: 38.922 added;",38.921999999999997,103,52,null,null,"2024-04-02","2024-05-14"]
[278,1030078,"NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo",1,"Rel-19",null,"2024-03-03","2026-03-03",0.04,"RP-240829",null,"ZTE ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[279,1031078,"   Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.1,"RP-240829","RP-241285","ZTE ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241285; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[280,1032078,"   Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240829","RP-241285","ZTE ",null,"13/6/24: Stat Rep: ->RP-241285; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[281,1030079,"NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5",1,"Rel-19",null,"2024-03-03","2026-03-03",0.02,"RP-240830",null,"Apple ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[282,1031079,"   Core part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.05,"RP-240830","RP-241268","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241268; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[283,1032079,"   Perf. part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240830","RP-241268","Apple ",null,"13/6/24: Stat Rep: ->RP-241268; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[284,1030080,"NR demodulation performance Phase 5 ","NR_demod_Ph5",1,"Rel-19",null,"2024-03-03","2025-09-09",0,"RP-240831",null,"China Telecom ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[285,1032080,"   Perf. part: NR demodulation performance Phase 5 ","NR_demod_Ph5-Perf",2,"Rel-19","R4","2024-03-03","2025-09-09",0,"RP-240831","RP-241296","China Telecom ",null,"13/6/24: FCD:03/03/2026->09/09/2025; Stat Rep: ->RP-241296; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[286,1030081,"NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2",1,"Rel-19","R4","2024-03-03","2025-06-06",0.1,"RP-240832",null,"Intel ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[287,1031081,"   Core part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Core",2,"Rel-19",null,"2024-03-03","2024-12-12",0.25,"RP-240832","RP-241496","Intel ",null,"13/6/24: Compl:0%->25%; Stat Rep: ->RP-241496; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[288,1032081,"   Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Perf",2,"Rel-19","R4","2024-03-03","2025-06-06",0,"RP-240832","RP-241496","Intel ",null,"13/6/24: Stat Rep: ->RP-241496; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[289,1030083,"Enhancements for Air-to-ground network for NR ","NR_ATG_enh",1,"Rel-19",null,"2024-03-03","2026-03-03",0.04,"RP-240839",null,"CMCC ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[290,1031083,"   Core part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.1,"RP-240839","RP-241214","CMCC ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241214; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[291,1032083,"   Perf. part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-240839","RP-241214","CMCC ",null,"13/6/24: Stat Rep: ->RP-241214; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[292,1030084,"NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS",1,"Rel-19",null,"2024-03-03","2025-09-09",0.15,"RP-240840",null,"OPPO ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[293,1031084,"   Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.15,"RP-240840","RP-241152","OPPO ",null,"14/5/24: 38.787 added;; 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241152; ",38.786999999999999,103,52,null,null,"2024-04-02","2024-06-13"]
[294,0,"Rel-19 other",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[295,1040001,"Service Based Interface Protocol Improvements Release 19","SBIProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[296,1040050,"   CT3 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[297,1040051,"   CT4 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C4","2024-06-17","2025-09-09",0,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[298,1040003,"Subscriber Data Migration","SUBDMIG",1,"Rel-19","C4","2024-06-17","2024-12-12",0,"CP-241023",null,"Jesus de Gregorio, Ericsson","Jesus de Gregorio, jesus.de.gregorio@ericsson.com",null,"23.527,29.503,29.504,29.510,29.571",101,51,null,null,"2023-09-06","2023-09-06"]
[299,1040005,"Study on Protocol for AI Data Collection from UPF","FS_PAIDC-UPF",1,"Rel-19","C4","2024-06-17","2025-03-03",0,"CP-241025",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[300,1040009,"Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241075",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[301,1040060,"   CT1 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241075",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[302,1040061,"   CT3 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C3","2024-06-17","2025-09-09",0,"CP-241075",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[303,1040039,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[304,1040062,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[305,1040063,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[306,1040041,"Protocol enhancements for Mission Critical Services","MCProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[307,1040064,"   CT1 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[308,1040065,"   CT3 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[309,1040066,"   CT4 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C4","2024-06-17","2025-09-09",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[310,1040042,"Enhancement of controlling RAT utilization","ECRATU",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241298",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,"24.008,24.301,24.501,23.122,23.008,29.272,29.503",101,51,null,null,"2023-09-06","2023-09-06"]
[311,1040067,"   CT1 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241298",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[312,1040068,"   CT4 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C4","2024-06-17","2025-09-09",0,"CP-241298",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[313,1040045,"Enhanced Mission Critical Location Management","enhMCLoc",1,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241288",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281,24.282,24.283,24.379,24.481,24.482,24.483,24.484,29.379",101,51,null,null,"2023-09-06","2023-09-06"]
[314,1040044,"Stage-3 5GS NAS protocol development 18 ","5GProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","2023-06-06"]
[315,1040046,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","NA"]
[316,1040047,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc19-non3GPP",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","NA"]
[317,1040040,"Stage-3 SAE Protocol Development ","SAES19",1,"Rel-19",null,"2024-06-17","2025-09-09",0,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","2023-06-06"]
[318,1040048,"   Stage-3 SAE Protocol Development general","SAES19",2,"Rel-19","C1","2024-06-17","2025-09-09",0,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","NA"]
[319,1040049,"   Stage-3 SAE Protocol Development non 3GPP","SAES19-non3GPP",2,"Rel-19","C1","2022-09-20","2023-12-12",0,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","NA"]
[320,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","2023-03-24","2024-09-09",0,"SP-230242",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater","33.107; 33.108; 33.126; 33.127; 33.128 ",97,49,null,null,"2022-09-11","2023-03-16"]
[321,1040010,"Lawful Interception Guidance Rel-19 ","LI19_Guide",1,"Rel-19","S3LI","2024-07-16","2025-03-03",0,"SP-240562",null,"Nag Rao, Nokia, ","nagaraja.rao@nokia.com ",null,null,null,null,null,null,"2024-07-16","NA"]
[322,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"2022-09-09","2022-12-12",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[323,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[324,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[325,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"2021-06-11","2023-12-12",1,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[{"$f":"A326+1","v":326},920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","2021-06-11","2021-06-18",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[327,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"2021-12-19","2022-12-10"]
[328,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[329,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","2023-06-06"]
[330,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","NA"]
[331,1020024,"Charging aspects of Satellite Backhaul in 5GS ","5GSATB_CH",1,"Rel-18","S5","2023-12-07","2024-03-03",1,"SP-240266",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","SP-231707 shows UID 1020023 but this duplicates with SP-231706, so changed here to 1020024.; 15/3/24: 0%->100; 2/4/24: WID:SP-231707->SP-240266","32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 ",102,52,null,null,"2023-12-07","2024-04-02"]
[332,1020029,"Management aspects of 5G system supporting satellite backhaul ","5GSATB_OAM",1,"Rel-18","S5","2023-12-07","2024-03-03",1,"SP-231708",null,"Wen Qi, China Telecom ","qiw@chinatelecom.cn ","; 14/3/24: 0%->100","28.541; 28.552 ",102,52,null,null,"2024-01-03","2024-03-14"]
[333,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[334,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"2021-12-19","2022-12-10"]
[335,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"2022-12-09","2024-03-03",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","NA"]
[336,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","2023-06-08"]
[337,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[338,990056,"   deleted - CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","; 15/3/24: 0%->100","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","2024-03-15"]
[339,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","2023-09-07","2024-03-03",1,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","; 8/12/23: 0%->35; 14/3/24: 35%->100","32.255; 32.256; 32.291; 32.298 ",101,51,null,null,"2023-09-07","2024-03-14"]
[340,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-240779",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ...",null,94,48,null,null,"2022-01-06","2024-04-02"]
[341,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2024-06-06",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"2022-01-06","2024-06-13"]
[342,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[343,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"2021-12-13","2025-12-12",0.75,"RP-234073",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073",null,94,48,null,null,"2022-01-06","2024-01-02"]
[344,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-234073","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[345,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","2022-03-07","2024-06-06",1,"RP-234073","RP-241350","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"2022-06-04","2024-06-13"]
[346,1030073,"   UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects ","IoT_NTN_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.16,"RP-240144","RP-241198","CMCC ",null,"13/6/24: Compl:0%->16%; WID: RP-240784->RP-240144; Stat Rep: ->RP-241198; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[347,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-234043",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043",38.741,98,50,null,null,"2023-01-09","2024-01-02"]
[348,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[349,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[350,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"2022-09-11","2023-09-07"]
[351,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","2022-06-02","2023-06-06",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-06-08"]
[352,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","2022-06-01","2022-06-15",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[353,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","2022-06-01","2023-12-12",1,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100",22.844000000000001,98,50,null,null,"2022-12-09","2023-12-08"]
[354,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647",null,"Thales ",null,"6/10/23: WID:RP-231499->RP-232647",null,100,51,null,null,"2023-06-29","2023-10-06"]
[355,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,51,null,null,"2023-06-29","2023-09-21"]
[356,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","2023-03-03","2024-06-06",0.44,"RP-240741",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856; 2/4/24: WID:RP-233856->RP-240741",null,99,50,null,null,"2023-03-29","2024-04-02"]
[357,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","2023-03-03","2024-03-03",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"2023-03-29","2024-04-02"]
[358,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","2023-03-03","2024-06-06",0,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12...",null,99,50,null,null,"2023-03-29","2024-03-14"]
[359,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","2023-03-03","2024-06-06",0.99,"RP-240451",null,"MediaTek ",null,"2/1/24: WID:RP-230792->RP-234060; 2/4/24: WID:RP-234060->RP-240451",null,99,50,null,null,"2023-03-29","2024-04-02"]
[360,991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",1,"RP-233259","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2...",36.764000000000003,99,50,null,null,"2023-03-29","2024-06-13"]
[361,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","2023-03-06","2024-06-06",1,"RP-233259","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ...",null,99,50,null,null,"2023-03-29","2024-06-13"]
[362,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"2022-03-15","2024-03-03",0.99,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437",null,95,48,null,null,"2022-04-05","2023-01-09"]
[363,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"2022-04-05","2023-01-09"]
[364,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...",36.180999999999997,95,48,null,null,"2022-04-05","2023-06-07"]
[365,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","2022-12-13","2024-03-03",0.99,"RP-240147","RP-240146","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"2023-01-09","2024-04-02"]
[366,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[367,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[368,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"2020-06-25","2021-09-13"]
[369,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[370,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[371,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"2021-12-19","2023-03-15"]
[372,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[373,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-06"]
[374,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-09"]
[375,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","NA"]
[376,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"2021-12-13","2024-03-03",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"2022-12-09","NA"]
[377,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"2021-12-13","2023-03-31"]
[378,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100",23.542000000000002,98,50,null,null,"2022-12-09","2023-06-08"]
[379,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%",27.007000000000001,99,50,null,null,"2022-12-09","2023-06-06"]
[380,990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","2023-03-13","2024-03-15",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"2022-12-09","2023-06-09"]
[381,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.881999999999998,96,49,null,null,"2022-06-02","2023-06-08"]
[382,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","2021-06-11","2022-06-09",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"2021-06-11","2023-06-08"]
[383,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[384,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[385,940080,"Study on network energy savings for NR","FS_Netw_Energy_NR",1,"Rel-18","R1","2021-12-13","2022-12-01",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...",38.863999999999997,94,48,null,null,"2022-01-06","2023-03-29"]
[386,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232672","RP-233067","Xueming Pan, vivo","panxueming@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...",38.869,94,48,null,null,"2022-01-06","2023-12-08"]
[387,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"2021-12-12","2025-12-12",0.69,"RP-233637",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637",null,97,49,null,null,"2022-09-23","2024-01-02"]
[388,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[389,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","2022-09-13","2024-06-06",1,"RP-233637","RP-241124","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[{"$f":"A390+1","v":390},940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","2021-12-12","2022-09-09",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...;...",38.865000000000002,94,48,null,null,"2022-01-06","2022-09-23"]
[391,1030062,"   UE Conformance - Enhanced support of reduced capability NR devices plus CT1 aspects ","NR_redcap_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240054","RP-240919","China Unicom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240919; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[392,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"2021-12-19","2022-12-10"]
[393,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"2022-12-15","2023-12-13",1,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[394,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added;","23.501; 23.502 ; 28.876",97,49,null,null,"2022-12-10","2024-01-04"]
[395,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","2022-12-15","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[396,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","NA"]
[397,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894",null,"Ericsson",null,"2/1/24: WID:RP-230743->RP-232894",null,99,50,null,null,"2023-04-07","2024-01-02"]
[398,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894","RP-232xyz","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[399,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"2022-12-13","2024-06-06",1,"RP-234009",null,"Huawei ",null,"2/1/24: WID:RP-223540->RP-234009",null,98,50,null,null,"2023-01-09","2024-01-02"]
[400,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","2022-12-13","2023-12-12",1,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[401,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",1,"RP-234009","RP-241239","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/...",null,98,50,null,null,"2023-01-09","2024-06-13"]
[402,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[403,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ",23.256,99,50,null,null,"2022-12-09","NA"]
[404,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"2021-12-19","2023-03-15"]
[405,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100",23.256,98,50,null,null,"2022-12-09","2023-06-08"]
[406,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100",33.890999999999998,96,49,null,null,"2022-06-02","2023-03-17"]
[407,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100",33.256,99,50,null,null,"2023-03-16","2023-09-07"]
[408,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"2022-12-09","2023-06-06"]
[409,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-09"]
[410,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[411,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","NA"]
[412,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","2021-09-13","2022-12-12",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"2021-09-13","2022-12-11"]
[413,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,97,49,null,null,"2022-09-11","NA"]
[414,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100",23.254999999999999,97,49,null,null,"2022-12-11","2023-06-08"]
[415,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-06"]
[416,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-09"]
[417,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386",null,94,48,null,null,"2022-01-06","2024-01-02"]
[418,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386","RP-233385","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[419,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389",null,"Nokia ",null,"2/1/24: WID:RP-230783->RP-233389",null,99,50,null,null,"2023-03-29","2024-01-02"]
[420,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389","RP-233388","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[421,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[422,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"2020-06-25","2025-03-03",0.92,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[423,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"2020-06-25","2021-06-11"]
[424,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[425,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"2021-12-19","2023-03-15"]
[426,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"2022-12-09","2023-06-08"]
[427,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100",33.893000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[428,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100",33.533000000000001,99,50,null,null,"2023-03-16","2023-09-07"]
[429,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"2022-12-09","2023-06-06"]
[430,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 16/7/24: 99%->100","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"2022-12-09","2024-07-16"]
[431,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%; 4/1/24: 29.586 added;","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586",99,50,null,null,"2022-12-09","2024-01-04"]
[432,1040013,"   Charging Aspects of Ranging and Sidelink Positioning","Ranging_SL_CH",2,"Rel-18","S5","2024-05-06","2025-03-03",0.2,"SP-241002",null,"Zhiwei Mo, China Telecom, ","mozw@chinatelecom.cn ",null,"32.240; 32.290; 32.271; 32.291; 32.298 ",null,null,null,null,"2024-06-13","2024-06-13"]
[433,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 70%->100",28.844999999999999,100,51,null,null,"2023-06-08","2024-03-14"]
[434,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"2022-09-30","2024-03-03",1,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[435,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"2021-12-19","2022-12-10"]
[436,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","2022-09-30","2023-06-06",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100",23.273,97,49,null,null,"2022-09-11","2023-06-08"]
[437,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%",23.273,97,49,null,null,"2022-09-11","2023-06-06"]
[438,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[439,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[440,940081,"Study on expanded and improved NR positioning","FS_NR_pos_enh2",1,"Rel-18","R1","2022-12-13","2024-06-06",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...",38.859000000000002,94,48,null,null,"2022-01-06","2023-01-09"]
[441,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"2022-12-13","2024-09-09",0.94,"RP-240778",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382; 2/4/24: WID:RP-233382->RP-240778",null,98,50,null,null,"2023-01-09","2024-04-02"]
[442,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","2022-12-13","2024-03-03",0.99,"RP-240778","RP-240302","Debdeep Chatterjee","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...",38.354999999999997,98,50,null,null,"2023-01-09","2024-03-14"]
[443,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","2022-12-15","2024-09-09",0.9,"RP-240778","RP-241184","Debdeep Chatterjee","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"2023-01-09","2024-06-13"]
[444,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-232789",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789",null,94,48,null,null,"2022-01-06","2024-01-02"]
[445,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...",38.786000000000001,94,48,null,null,"2022-01-06","2023-12-08"]
[446,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-232789","RP-240928","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[447,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"2021-12-13","2024-09-09",0.77,"RP-232972",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972",null,94,48,null,null,"2022-01-06","2024-01-02"]
[448,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[449,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-223501","RP-241088","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[450,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-09",0.3,"RP-221447","RP-241345","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[451,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-234010",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010",null,94,48,null,null,"2022-01-06","2024-01-02"]
[452,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-234010","RP-232887","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[453,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-10",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 14/3/24: 95%->100","23.700-33",95,48,null,null,"2021-12-19","2024-03-14"]
[{"$f":"A454+1","v":454},940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"2021-12-19","2022-12-10"]
[455,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","2022-03-10","2023-03-10",1,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"2022-03-10","2023-06-08"]
[456,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"2022-09-27","2023-12-12",1,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","NA"]
[457,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","2022-09-27","2023-06-06",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","2023-06-08"]
[458,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[459,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[460,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-06"]
[461,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","NA"]
[462,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90; 8/12/23: 90%->95; 15/3/24: 95%->100",33.503,99,50,null,null,"2023-03-16","2024-03-15"]
[463,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"2021-06-11","2024-03-03",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,23.434000000000001,99,50,null,null,"2022-12-09","NA"]
[464,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","2021-06-11","2022-09-12",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"2021-06-11","2022-12-11"]
[465,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100",23.434000000000001,98,50,null,null,"2022-12-09","2023-06-08"]
[466,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-06"]
[467,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-09"]
[468,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[469,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[470,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[471,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-01-09"]
[472,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"2021-12-19","2023-03-15"]
[473,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","2022-09-23","2023-03-03",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-06-08"]
[474,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[475,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[476,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[477,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","2021-09-10","2023-03-03",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"2021-09-10","2023-06-30"]
[478,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"2021-12-10","2023-09-09",1,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,23.434000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[479,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","2021-12-12","2023-06-06",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...",23.434000000000001,94,48,null,null,"2022-12-11","2023-06-08"]
[480,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","2021-12-12","2022-12-12",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-06"]
[481,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","2021-12-10","2022-12-09",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-09"]
[482,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.433999999999997,99,50,null,null,"2023-03-16","2024-03-15"]
[483,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"2021-09-13","2024-03-03",1,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"2022-09-11","2022-09-23"]
[484,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"2021-09-13","2022-12-11"]
[485,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"2022-12-11","2023-06-08"]
[486,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[487,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"2022-09-11","2023-06-09"]
[488,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","2023-06-08","2023-09-09",1,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ","; 15/3/24: 0%->100",33.433999999999997,100,51,null,null,"2023-06-08","2024-03-15"]
[489,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"2021-03-18","2021-06-11"]
[490,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","2020-09-01","2020-09-17",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"2020-09-11","NA"]
[491,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"2022-06-02","2023-09-09",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"2022-06-02","2022-12-11"]
[492,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"2023-03-16","2023-06-08"]
[493,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.884,96,49,null,null,"2022-06-02","2023-06-08"]
[494,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50; 8/12/23: 50%->85; 15/3/24: 85%->100",33.122,99,50,null,null,"2023-03-16","2024-03-15"]
[495,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","2023-03-16","2023-09-09",1,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,29.222000000000001,99,50,null,null,"2023-03-16","2023-06-08"]
[496,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"2020-06-25","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"2021-06-11","NA"]
[497,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[498,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"2021-06-11","2021-12-10"]
[499,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100",28.902000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[500,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"2021-06-11","2022-12-11"]
[501,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"2022-06-03","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"2022-06-03","2023-06-30"]
[502,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","2022-06-06","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->",24.558,96,49,null,null,"2022-06-03","2023-06-09"]
[503,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","2022-06-03","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"2022-06-03","2023-06-06"]
[504,980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","2022-12-09","2023-12-12",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100",28.843,98,50,null,null,"2022-12-09","2023-09-07"]
[505,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ","; 8/12/23: 0%->80; 14/3/24: 80%->100","32.240; 32.290 ",101,51,null,null,"2023-09-06","2024-03-14"]
[506,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[507,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","2022-06-02","2022-06-10",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100",22.100999999999999,96,49,null,null,"2022-06-02","2022-09-12"]
[508,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100",33.18,94,48,null,null,"2021-12-10","2023-06-08"]
[509,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"2021-12-10","2024-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-03-17"]
[510,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","2021-12-10","2023-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-06-08"]
[511,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-240297",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,51,null,null,"2023-06-07","2023-06-30"]
[512,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","NA"]
[513,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","2020-06-25","2021-09-20",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"2020-06-26","2021-09-13"]
[514,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","2021-09-10","2022-06-10",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","2022-09-12"]
[515,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,null,"2021-09-10","2022-09-12"]
[516,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"2019-03-07","2023-12-12",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[517,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","2019-03-07","2022-03-11",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100",23.289000000000001,93,47,null,null,"2021-09-10","2022-12-11"]
[{"$f":"A518+1","v":518},970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","2022-09-13","2023-12-12",1,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"2022-09-05","2023-06-06"]
[519,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"2019-03-07","2023-12-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[520,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","2019-03-07","2022-09-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22",23.289000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[521,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","2022-09-13","2023-12-12",1,"CP-233210",null,"Mengdi Ji, Huawei","jimengdi@huawei.com, ","3/24: rapporteur changed (was weihaitao@huawei.com)","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"2022-09-05","NA"]
[522,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%",33.503,97,49,101,null,"2022-09-11","2023-06-08"]
[523,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[524,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[525,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","2022-12-09","2024-03-03",0.99,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[526,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[527,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","2023-09-09","2024-03-03",1,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"2022-12-09","2023-06-08"]
[528,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","2019-09-19","2021-12-10",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"2019-09-13","2021-09-13"]
[529,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","2021-12-13","2023-03-03",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"2021-12-13","2023-06-08"]
[530,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"2021-12-13","2023-03-17"]
[531,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","2018-06-06","2022-06-10",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"2018-06-06","2022-06-04"]
[532,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[533,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"2019-12-06","2021-12-10",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"2021-06-11","2022-07-13"]
[534,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","2019-12-06","2021-06-11",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"2019-12-06","2022-06-21"]
[535,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"2021-06-11","2022-06-21"]
[536,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-221348","RP-233132","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...",38.843000000000004,94,48,null,null,"2022-01-06","2023-12-08"]
[537,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[538,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","2022-06-21","2023-03-03",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100",33.898000000000003,96,49,null,null,"2022-06-21","2023-09-07"]
[539,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220071",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"2021-12-19","2022-12-10"]
[540,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[541,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"2022-12-09","2023-06-06"]
[542,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"2022-12-09","2023-06-06"]
[543,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"2021-12-13","2023-12-12",0.8,"RP-233441",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441",null,94,48,null,null,"2022-01-06","2024-01-02"]
[544,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.8,"RP-233441","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[545,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100",33.877000000000002,96,49,null,null,"2022-06-02","2023-09-07"]
[546,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100",28.908000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[547,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","2023-03-17","2024-03-03",1,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35; 14/3/24: 35%->100; 14/3/24: FCD:12/12/2023->/24","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"2023-03-17","2024-03-14"]
[548,1020023,"NEF Charging enhancement to support AI/ML in 5GS ","AIMLsysNEF_CH",1,"Rel-18","S5","2023-12-07","2023-12-12",1,"SP-231706",null,"Alla Goldner, OPPO ","v-alla.goldner@oppo.com ","; 14/3/24: 0%->100; 14/3/24: 100%->100","32.254; 32.291 ",102,52,null,null,"2023-12-07","2024-03-14"]
[549,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-19","S4","2022-03-12","2025-03-03",0.75,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50; 14/3/24: 50%->60; 14/...","26.927; 26.847",95,48,null,null,"2022-03-10","2024-06-13"]
[550,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[551,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-232993",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993",null,94,48,null,null,"2022-01-06","2024-01-02"]
[552,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232993","RP-232992","Rui Zhou, CATT","zhourui@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[553,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","NA"]
[554,940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"2021-12-19","2022-12-10"]
[555,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","2023-06-08"]
[556,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024. 03/24: rapporteur changed (was giorgi.gulbani@huawei.com)",null,99,50,null,null,"2022-12-09","2023-06-30"]
[557,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 9/6/23: 15%->40",null,99,50,null,null,"2022-12-09","2023-06-09"]
[558,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,null,"2022-12-09","2023-06-06"]
[559,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","2023-06-08","2023-09-09",1,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"2023-06-08","2024-03-15"]
[560,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100",33.883000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[561,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"2021-06-15","2023-09-08",1,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"2021-07-02","2023-01-09"]
[562,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","2021-06-15","2023-09-08",1,"RP-232590","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",36.792000000000002,92,47,null,null,"2021-07-02","2023-10-06"]
[563,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[564,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024",31.102,92,47,null,null,"2021-07-02","2023-06-06"]
[565,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","2023-03-13","2023-03-24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[566,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[567,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[568,0,"Rel-18 Slice","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[569,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","2021-03-12","2022-09-22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[570,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[571,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[572,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","2020-06-25","2021-03-17",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"2020-06-25","2021-06-11"]
[573,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[574,1000023,"   Stopped – CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[575,1000044,"   Stopped – CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[576,1000045,"   Stopped – CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[577,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","NA"]
[578,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"2021-12-19","2022-12-10"]
[579,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90; 15/3/24: 90%->100",33.886000000000003,96,49,null,null,"2022-06-02","2024-03-15"]
[580,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[581,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[{"$f":"A582+1","v":582},990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-09"]
[583,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[584,1030024,"   Network Slice Replacement charging ","eNS_Ph3_CH",2,"Rel-18","S5","2024-02-02","2024-03-03",1,"SP-240475",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com) ","; 2/4/24: 0%->100","32.255; 32.256; 32.291; 32.298 ",103,52,null,null,"2024-03-14","2024-04-02"]
[585,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793",null,"ZTE ",null,"2/1/24: WID:RP-230787->RP-232793",null,99,50,null,null,"2023-03-29","2024-01-02"]
[586,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793","RP-232866","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[587,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[588,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","2022-03-10","2023-12-12",1,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12...",28.835999999999999,95,48,null,null,"2022-03-10","2023-12-08"]
[589,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added;","28.312 ; 28.914",99,50,null,null,"2023-03-16","2024-01-04"]
[590,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","2021-03-18","2021-12-10",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"2021-03-18","2022-06-04"]
[591,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","2022-06-15","2023-12-12",1,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100",26.940999999999999,96,49,null,null,"2022-06-03","2023-12-08"]
[592,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","2021-12-10","2022-03-11",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"2021-12-10","2022-06-04"]
[593,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","2021-03-18","2022-09-12",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"2021-03-18","2022-12-11"]
[594,1020049,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18",null,"2022-06-02","2024-03-15",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[595,960013,"   (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement","NSCALE",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[596,1020050,"   CT1 aspects of NSCALE","NSCALE",2,"Rel-18","C1","2022-06-02","2024-03-14",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,24.548999999999999,96,49,null,null,"2022-06-02","2023-06-08"]
[597,1020006,"   CT3 aspects of NSCALE","NSCALE",2,"Rel-18","C3","2022-06-02","2024-03-14",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.222, 29.520, 29.522, 29.549",96,49,null,null,"2022-06-02","2023-06-08"]
[598,1020046,"   CT4 aspects of NSCALE","NSCALE",2,"Rel-18","C4","2022-06-02","2024-03-15",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,29.536000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[599,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","2022-06-03","2023-09-09",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"2022-06-03","2022-07-13"]
[600,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","2021-01-12","2023-03-03",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"2021-01-12","2023-03-17"]
[601,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-231448",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448; 14/3/24: 75%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"2022-12-09","2024-03-14"]
[602,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","2023-06-30","2024-03-03",1,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;",31.105,100,51,null,null,"2023-06-30","2023-09-21"]
[603,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[604,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"2021-12-13","2025-12-12",0.57999999999999996,"RP-232778",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778",null,98,50,null,null,"2023-01-09","2024-01-02"]
[605,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","2022-12-13","2023-12-12",1,"RP-223502","RP-232779","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[606,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","2021-12-13","2023-03-03",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...",38.835000000000001,94,48,null,null,"2022-01-06","2023-03-17"]
[607,1030063,"   UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects ","NR_XR_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240088","RP-240936","Nokia ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240936; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[608,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"2022-12-09","NA"]
[609,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"2021-12-19","2022-12-10"]
[610,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-09-07"]
[611,1030048,"   CT1 aspects of XRM","XRM",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196; 2/4/24: 0%->98","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2024-04-02"]
[612,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[613,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[614,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","2022-03-10","2024-03-03",1,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...",26.93,95,48,null,null,"2022-03-10","2024-03-14"]
[615,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","2022-03-15","2024-06-06",1,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60; 14/3/24: FCD:03/03/2024->/...",26.113,95,48,null,null,"2022-03-10","2024-06-13"]
[616,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","2022-03-10","2023-06-06",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"2022-03-10","2023-06-08"]
[617,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","2022-03-10","2024-03-03",1,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024; 14/3/24: 80...","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"2022-03-10","2024-03-14"]
[618,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","2022-06-03","2024-06-06",1,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1...",26.263999999999999,96,49,null,null,"2022-06-03","2024-06-13"]
[619,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","2022-06-03","2023-06-06",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"2022-06-03","2023-06-08"]
[620,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","2022-06-03","2024-03-03",1,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...",26.521999999999998,96,49,null,null,"2022-06-03","2024-03-14"]
[621,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","2019-03-07","2024-06-06",1,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/...","26.260; new",83,42,null,null,"2019-03-14","2024-06-13"]
[622,1030047,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18",null,"2017-09-08","2024-06-06",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2023-12-08"]
[623,770024,"   EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",2,"Rel-18","S4","2017-09-08","2024-06-06",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2024-06-13"]
[624,1030025,"   CT3 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C3","2024-03-03","2024-06-06",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"2017-09-08","2023-12-08"]
[625,1030001,"   CT4 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C4","2024-03-03","2024-06-06",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"2017-09-08","2023-12-08"]
[626,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","2023-03-16","2024-06-06",1,"SP-231291",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291; 14/3/24: 25%->35; 14/3/24: FCD:03/03/2024->/24; 3/4/24: 26.249 added; 26.996 added;; 13/6/24: ...","26.119 ; 26.566; 26.866; 26.865; 26.249; 26.996",99,50,null,null,"2023-03-16","2024-06-13"]
[627,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","2022-06-03","2024-06-06",1,"SP-231291",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%...",26.565000000000001,96,49,null,null,"2022-06-03","2024-06-13"]
[628,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","2022-06-03","2024-03-03",1,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65; 14/3/24: 65%->100",26.812000000000001,96,49,null,null,"2022-06-03","2024-03-14"]
[629,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","2022-06-03","2022-12-08",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"2022-06-03","2022-12-11"]
[630,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[631,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","2020-06-25","2021-12-10",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"2020-06-25","2021-12-10"]
[632,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","2020-06-25","2021-09-16",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"2020-06-26","2022-03-12"]
[633,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"2022-03-03","2023-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-03-10","2022-09-12"]
[634,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","2022-03-03","2022-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-12-11","2023-06-08"]
[635,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2023-06-06"]
[636,980071,"   deleted - CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","2/4/24: deleted at 100%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2024-04-02"]
[637,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"2020-12-04","2022-06-21"]
[638,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"2021-09-13","2022-12-11"]
[639,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"2022-09-09","2024-03-03",1,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"2022-09-11","NA"]
[640,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"2022-12-11","2023-06-08"]
[641,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[642,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","NA"]
[643,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"2022-09-12","2024-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[644,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[645,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,51,null,null,"2023-06-07","NA"]
[{"$f":"A646+1","v":646},1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,51,null,null,"2023-06-07","NA"]
[647,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"2022-03-15","2025-12-12",0.69,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"2022-04-05","2022-09-23"]
[648,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","2022-03-15","2023-09-22",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[649,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","2022-03-16","2024-06-06",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[650,1030071,"   UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240371","RP-241278","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241278; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[651,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[652,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"2019-09-19","2024-03-03",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"2021-06-11","NA"]
[653,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","2019-09-19","2021-09-08",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"2019-09-13","2021-09-13"]
[654,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"2021-06-11","2021-09-13"]
[655,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"2021-12-19","2023-03-16"]
[656,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[657,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,null,"2022-09-11","2023-06-06"]
[658,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,null,"2022-09-11","NA"]
[659,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"2022-09-11","2024-01-04"]
[660,1030027,"   CT6 aspects of NG_RTC","NG_RTC",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"2022-09-11","2024-01-04"]
[661,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","2022-06-02","2023-06-06",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100",33.89,96,49,null,null,"2022-06-02","2023-06-08"]
[662,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","; 15/3/24: 0%->100",33.328000000000003,99,50,null,null,"2023-03-16","2024-03-15"]
[663,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.260; 32.255; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2024-03-14"]
[664,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[665,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"2021-12-19","2022-12-10"]
[666,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[667,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[668,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-09"]
[669,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[670,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"2021-12-19","2023-03-15"]
[671,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"2022-09-12","2024-03-03",1,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2022-12-10"]
[672,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[673,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-06"]
[674,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","2023-04-18","2024-03-03",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-09"]
[675,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"2020-12-04","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[676,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","2020-12-04","2021-06-11",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"2020-12-04","2021-12-10"]
[677,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[678,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[679,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"2022-09-11","2022-09-12"]
[680,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-03-03",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"2022-12-11","2023-06-08"]
[681,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","2022-12-15","2023-12-12",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[682,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","2022-12-15","2023-12-12",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[683,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","2022-06-02","2023-12-12",1,"SP-220990",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156; 15/3/24: 65%->98; 13/6/24: 98%->100; 13/6/24: WID:SP-231156...",23.957999999999998,96,49,null,null,"2022-06-02","2024-06-13"]
[684,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"2021-06-11","2022-12-11"]
[685,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"2021-12-20","2024-06-06",1,null,null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2022-12-11","NA"]
[686,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2021-12-19","2022-03-12"]
[687,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"2021-12-19","2022-12-10"]
[688,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90; 15/3/24: 90%->100",33.738999999999997,95,48,null,null,"2022-03-10","2024-03-15"]
[689,970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","2022-09-23","2023-06-06",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[690,1040038,"   CT1 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C1","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[691,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[692,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%; 16/7/24: WID:CP-233026->CP-241027","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2024-07-16"]
[693,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95; 15/3/24: 95%->100","33.558; 33.501 ",99,50,null,null,"2023-03-16","2024-03-15"]
[694,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[695,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"2020-09-16","2021-09-08",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"2021-06-11","NA"]
[696,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","2020-09-16","2021-06-11",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"2020-09-10","2021-09-13"]
[697,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[698,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"2021-12-13","2024-03-03",1,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2022-12-10"]
[699,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"2021-12-19","2023-03-15"]
[700,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2023-06-08"]
[701,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99; 15/3/24: 99%->100",33.857999999999997,96,49,null,null,"2022-06-02","2024-03-15"]
[702,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90; 14/3/24: 90%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-14"]
[703,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-30"]
[704,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","2022-12-15","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-09"]
[705,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-06"]
[706,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100",28.827999999999999,94,48,null,null,"2021-12-13","2023-03-17"]
[707,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65; 14/3/24: 65%->100","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"2023-03-16","2024-03-14"]
[708,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","2023-03-06","2023-12-12",1,"RP-233569","RP-233567","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"2023-04-07","2024-01-02"]
[709,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A710+1","v":710},840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"2019-05-31","2023-03-15"]
[711,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"2022-09-09","2024-06-06",1,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","NA"]
[712,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[713,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","2022-12-16","2024-06-06",1,"CP-240080",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[714,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","2022-12-16","2024-06-06",1,"CP-240080",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[715,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","2022-12-16","2024-06-06",1,"CP-240080",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[716,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"2022-09-12","2023-12-12",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-03-22"]
[717,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[718,1000040,"   CT3 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,51,null,null,"2023-06-07","NA"]
[719,1020048,"   CT4 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C4","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",102,52,null,null,"2023-06-07","NA"]
[720,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"2019-03-07","2023-12-13",1,"CP_233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"2022-03-10","NA"]
[721,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","2019-03-07","2023-12-12",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"2022-09-07","2023-06-06"]
[722,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","2019-03-11","2023-12-12",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,29.518000000000001,97,49,null,null,"2022-09-07","NA"]
[723,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"2019-03-07","2024-03-03",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[724,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"2021-12-19","2022-09-12"]
[725,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","2019-03-07","2019-03-07",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-03-15"]
[726,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[727,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[728,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"2021-12-20","2023-09-09",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,97,49,null,null,"2022-09-11","NA"]
[729,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102",23.501999999999999,97,49,null,null,"2022-09-11","2023-03-16"]
[730,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[731,1020047,"   CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C4","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[732,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[733,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-19","S4","2023-06-08","2025-03-03",0.3,"SP-230539",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->3/3/25; Rel-18->Rel-19; 13/6/24: 30%->",26.954999999999998,100,51,null,null,"2023-06-08","2024-06-13"]
[734,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","2023-06-08","2024-03-03",1,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65; 14/3/24: 65%->100","26.955 ; 26.966",100,51,null,null,"2023-06-08","2024-03-14"]
[735,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-19","S4","2023-06-08","2024-12-12",0.5,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->12/24; ; Rel-18->Rel-19; 13/6/24: 30%->50",26.812999999999999,100,51,null,null,"2023-06-08","2024-06-13"]
[736,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","2021-12-13","2022-12-12",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"2021-12-13","2022-12-11"]
[737,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","2022-06-02","2024-03-03",1,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65; 14/3/24: 65%->100","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"2022-06-03","2024-03-14"]
[738,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","2022-12-09","2023-03-03",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"2022-12-09","2023-03-17"]
[739,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","2022-06-02","2023-06-06",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100",26.501000000000001,96,49,null,null,"2022-06-03","2023-06-08"]
[740,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","2022-12-12","2024-03-03",1,"SP-231709",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709; 14/3/24: 75%->100; 3/4/24: 26.982 added;","26.114 ; 26.982",98,50,null,null,"2022-12-09","2024-04-03"]
[741,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","2020-03-25","2023-09-09",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...",26.925000000000001,87,44,null,null,"2019-12-06","2023-09-07"]
[742,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","2023-06-08","2024-03-03",1,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40; 14/3/24: 40%->100","26.140; 26.141 ; 26.143",100,51,null,null,"2023-06-08","2024-03-14"]
[743,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","2023-06-08","2024-06-06",1,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55; 14/3/24: 55%->75; 14/3/24: FCD:03/03/2024->/24; 13/6/24: 75%->100","26.512; 26.247; 26.517; 26.532 ; 26.510",100,51,null,null,"2023-06-08","2024-06-13"]
[744,0,"Rel-18 Other topics","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[745,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[746,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"2017-06-03","2023-03-15"]
[747,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100",33.887,96,49,null,null,"2022-06-02","2023-06-08"]
[748,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-09","2023-06-08"]
[749,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-30"]
[750,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-09"]
[751,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[752,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-15"]
[753,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.255; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2024-03-14"]
[754,980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-23","NA"]
[755,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-12","2023-06-08"]
[756,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","NA"]
[757,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","2022-12-15","2023-12-12",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","2023-06-06"]
[758,970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","2022-09-23","2024-03-03",1,"SP-240267",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 87%->100; 2/4/24: WID:SP-220981->SP-240267","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"2022-09-11","2024-04-02"]
[759,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"2021-12-13","2024-03-03",0.99,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"2022-09-11","2022-12-11"]
[760,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","2021-12-13","2022-09-12",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"2021-12-13","2022-12-11"]
[761,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","2022-09-12","2023-06-06",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"2022-09-11","2023-06-08"]
[762,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","2022-09-12","2024-03-03",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"2022-09-11","2023-06-06"]
[763,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","2022-09-12","2024-03-03",0.96,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5",29.548999999999999,97,49,null,null,"2022-09-11","2023-06-09"]
[764,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"2021-12-19","2022-06-04"]
[765,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"2022-09-08","2023-09-09",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[766,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[767,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[768,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-09"]
[769,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","NA"]
[770,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[771,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[772,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[773,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","2021-12-20","2023-12-12",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[{"$f":"A774+1","v":774},940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"2021-12-19","2022-12-10"]
[775,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"2021-12-19","2023-03-15"]
[776,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"2022-09-08","2024-03-03",0.77,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[777,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","2022-09-08","2023-06-06",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[778,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[779,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","2022-12-16","2024-03-03",0.25,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[780,1020064,"      (IETF) CT3 part of DetNet (draft-ietf-detnet-yang)","DetNet",3,"Rel-18","C3-IETF","2022-12-16","2024-03-03",0.25,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","2/4/24: 100%->25","29.513, 29.565",97,49,null,null,"2022-09-11","2024-04-02"]
[781,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[782,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[783,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100",23.273,97,49,null,null,"2022-12-10","2022-12-10"]
[784,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","2022-12-16","2023-06-06",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[785,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[786,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"2022-12-10","2023-03-22"]
[787,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"2022-09-11","2023-06-06"]
[788,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-09-11","NA"]
[789,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-12-10","2023-03-22"]
[790,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","2023-06-06"]
[791,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[792,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[793,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"2022-09-08","2024-03-03",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[794,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[795,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[796,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-09"]
[797,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","NA"]
[798,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"2022-03-10","2023-12-15",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70",23.553999999999998,95,48,null,null,"2022-03-10","2022-12-11"]
[799,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","2022-03-10","2023-03-03",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100",23.553999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[800,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","2023-03-13","2023-12-15",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-06"]
[801,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","2023-03-13","2023-12-15",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-09"]
[802,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","2023-02-02","2023-03-03",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[803,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"2021-03-18","NA"]
[804,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","2020-06-25","2021-03-12",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"2020-06-25","2021-06-11"]
[805,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"2021-12-19","2023-03-15"]
[806,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"2021-03-18","2021-06-11"]
[807,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[808,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-30"]
[809,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-06"]
[810,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"2022-09-11","2023-06-30"]
[811,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772",28.832000000000001,95,48,null,null,"2022-03-10","2023-06-30"]
[812,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","2021-12-13","2022-09-22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",38.878999999999998,94,48,null,null,"2022-01-06","2022-09-23"]
[813,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863",null,"Nokia ",null,"2/1/24: WID:RP-230754->RP-232863",null,99,50,null,null,"2023-03-29","2024-01-02"]
[814,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863","RP-232864","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[815,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"2020-09-16","2024-03-03",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[816,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","2020-09-16","2021-09-08",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"2020-09-10","2021-09-13"]
[817,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-14"]
[818,980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added;","23.501; 23.502; 23.503; 23.273 ; 28.875",98,50,null,null,"2022-12-09","2024-01-04"]
[819,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[820,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[821,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"2021-12-19","2022-12-10"]
[822,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-240104",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320; 2/4/24: WID:R...",null,94,48,null,null,"2022-01-06","2024-04-02"]
[823,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[824,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","2021-12-15","2024-06-06",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[825,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"2022-01-06","2023-01-09"]
[826,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-223488","RP-233603","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[827,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-231432",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432",28.863,94,48,null,null,"2021-12-13","2024-01-03"]
[828,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-231440",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440; 14/3/24: 99%->100",null,95,48,null,null,"2022-03-10","2024-03-14"]
[829,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"2021-09-10","2024-03-03",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"2021-09-10","2022-01-07"]
[830,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[831,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"2021-12-19","2023-06-08"]
[832,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[833,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[834,1030049,"   CT6 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[835,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"2021-01-01","2023-12-12",1,"RP-233438",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438",null,94,48,null,null,"2022-01-06","2024-01-02"]
[836,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","2021-01-01","2023-12-12",1,"RP-233438","RP-233437","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[837,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-233438","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"2022-04-05","2023-10-06"]
[{"$f":"A838+1","v":838},940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","2021-12-10","2024-03-03",1,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 90%->100","28.313; ; 28.317",94,48,null,null,"2021-12-10","2024-03-14"]
[839,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","2020-12-04","2021-03-12",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-04","2020-12-05"]
[840,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","2021-03-18","2021-03-25",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-03-19"]
[841,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","2022-09-16","2024-03-01",0.99,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[842,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","2022-12-16","2023-06-06",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"2022-09-19","2023-06-06"]
[843,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","2022-09-16","2022-09-16",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,31.102,97,49,null,null,"2022-09-19","NA"]
[844,1010052,"   UE Conformance - Signal level Enhanced Network Selection ","SENSE-UEContest",2,"Rel-18","R5","2023-09-09","2024-03-01",1,"RP-233770","RP-240288","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770; 14/3/24: FCD:05/06/2024->01/03/2024; Compl:5%->100%; Stat Rep: RP-233769->...",null,101,51,null,null,"2023-10-06","2024-03-14"]
[845,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75; 15/3/24: 75%->100","33.527; 33.927; 33.936",94,48,null,null,"2021-12-10","2024-03-15"]
[846,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30; 15/3/24: 30%->100","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"2022-03-10","2024-03-15"]
[847,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100",33.892000000000003,96,49,null,null,"2022-06-02","2023-09-07"]
[848,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","2018-09-06","2022-12-09",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ...","New",81,41,null,null,"2018-09-06","2023-06-08"]
[849,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"2022-06-02","2023-09-07"]
[850,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","2023-06-06"]
[851,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[852,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[853,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","2023-06-06"]
[854,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[855,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[856,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[857,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"2022-06-03","2024-03-03",1,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2022-06-20"]
[858,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","2022-06-03","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[859,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","2022-06-06","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[860,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","2022-06-03","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-06"]
[861,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","2022-06-03","2022-12-08",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"2022-06-03","2022-06-20"]
[862,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,null,"2022-06-03","2022-06-20"]
[863,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-06"]
[864,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-09"]
[865,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","2022-03-07","2024-03-03",1,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,null,"2022-06-03","2023-06-06"]
[866,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","2022-12-15","2023-12-12",1,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"2022-06-03","2023-06-06"]
[867,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","2023-03-13","2023-12-15",1,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"2022-06-03","2023-06-06"]
[868,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-18","C4","2022-08-25","2024-03-03",0.85,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,null,"2022-06-03","2023-09-21"]
[869,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,51,null,null,"2023-09-20","NA"]
[870,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",22.260999999999999,101,51,null,null,"2023-09-20","NA"]
[871,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100",33.500999999999998,101,51,null,null,"2023-09-20","2023-12-08"]
[872,1020001,"NRF API enhancements to avoid signalling and storing of redundant data","NRFe",1,"Rel-18","C4","2023-12-12","2024-03-15",1,"CP-233025",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com",null,"29.510, 29.571, 29.504",96,49,null,null,"2022-06-03","2023-06-06"]
[873,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[874,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95; 15/3/24: 95%->100","33.926 ; 33.537",95,48,null,null,"2022-03-10","2024-03-15"]
[875,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","2023-03-16","2023-12-12",1,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23; 15/3/24: 40%->100","33.926 ; 33.528",99,50,null,null,"2023-03-16","2024-03-15"]
[876,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[877,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","2022-12-09","2023-09-09",1,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23; 15/3/24: 80%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2024-03-15"]
[878,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99; 15/3/24: 99%->100","33.926 ; 33.742; 33.523",95,48,null,null,"2022-03-10","2024-03-15"]
[879,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","2022-03-10","2024-03-03",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 15/3/24: 99%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2024-03-15"]
[880,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"2022-03-10","2023-03-17"]
[881,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2023-09-07"]
[882,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","2023-09-09","2024-03-03",1,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"2022-12-09","NA"]
[883,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.737000000000002,95,48,null,null,"2022-03-10","2024-03-15"]
[884,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.534999999999997,99,50,null,null,"2023-03-16","2024-03-15"]
[885,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","2021-12-13","2023-03-03",1,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80; 15/3/24: 80%->100",33.869999999999997,94,48,null,null,"2021-12-13","2024-03-15"]
[886,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","2018-12-13","2022-12-09",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%->...",null,82,42,null,null,"2018-12-06","2023-09-07"]
[887,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100",33.893999999999998,96,49,null,null,"2022-06-02","2023-09-07"]
[888,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100",33.896000000000001,96,49,null,null,"2022-06-02","2023-03-17"]
[889,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","2023-05-01","2023-06-06",1,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"2023-06-08","2024-03-15"]
[890,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","2023-09-06","2024-03-03",1,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 8/12/23: 0%->10; 15/3/24: 10%->100",33.926000000000002,101,51,null,null,"2023-09-06","2024-03-15"]
[891,0,"Rel-18 NR-only: topics other than band","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[892,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"2022-03-15","2024-06-06",1,"RP-233586",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586",null,95,48,null,null,"2022-04-05","2024-01-02"]
[893,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","2023-06-07","2023-12-12",1,"RP-233586","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[894,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-233586","RP-241293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...",38.878,95,48,null,null,"2022-04-05","2024-06-13"]
[895,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025",null,"Ericsson",null,"2/1/24: WID:RP-230813->RP-234025",null,99,50,null,null,"2023-04-07","2024-01-02"]
[896,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025","RP-233392","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[897,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"2022-12-13","2024-03-01",1,"RP-240251",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004; 2/4/24: WID:RP-234004->RP-240251",null,98,50,null,null,"2023-01-09","2024-04-02"]
[898,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2024-03-14"]
[899,981242,"   Stopped - Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2024-04-02"]
[900,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"2022-09-12","2025-06-06",0.72,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"2022-10-19","2023-01-09"]
[901,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",1,"RP-223499","RP-233448","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...",38.895000000000003,97,49,null,null,"2022-10-19","2023-12-08"]
[{"$f":"A902+1","v":902},970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","2022-09-13","2023-12-12",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"2022-10-19","2022-12-09"]
[903,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",1,"RP-231152","RP-241200","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ; 14/3/24: FCD:05/...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[904,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"2022-09-12","2024-12-12",0.73,"RP-240120",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031; 2/4/24: WID:RP-233031->RP-240120",null,97,49,null,null,"2022-10-19","2024-04-02"]
[905,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240120","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...",38.896000000000001,97,49,null,null,"2022-10-19","2024-06-13"]
[906,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240120","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"2022-10-19","2024-06-13"]
[907,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-12-12",0.12,"RP-232774","RP-240906","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774; 14/3/24: FCD:05/06/2024->12/12/2024; Compl:...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[908,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-240428",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975; 2/4/24: WID:RP-233975->RP-240428",null,97,49,null,null,"2022-10-19","2024-04-02"]
[909,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240428","RP-241253","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....",38.896999999999998,97,49,null,null,"2022-10-19","2024-06-13"]
[910,970287,"   Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","2022-09-13","2024-03-01",1,"RP-240428","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,102,null,"2022-10-19","2024-01-02"]
[911,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",0.99,"RP-240763",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561; 2/4/24: WID:RP-233561->RP-240763",null,97,49,null,null,"2022-10-19","2024-04-02"]
[912,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240763","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...",38.899000000000001,97,49,null,null,"2022-10-19","2024-06-13"]
[913,970289,"   Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","2022-09-12","2022-09-12",0,"RP-240763","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"2022-10-19","2024-06-13"]
[914,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-240123",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017; 2/4/24: WID:RP-234017->RP-240123",null,97,49,null,null,"2022-10-19","2024-04-02"]
[915,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240123","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...",38.85,97,49,null,null,"2022-10-19","2024-06-13"]
[916,970290,"   Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-01",1,"RP-240123","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,102,null,"2022-10-19","2024-06-13"]
[917,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"2022-09-08","2024-03-01",1,"RP-232952",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952",null,97,49,null,null,"2022-09-23","2024-01-02"]
[918,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","2022-09-08","2024-03-01",1,"RP-232952","RP-240275","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"2022-09-23","2024-03-14"]
[919,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","2022-09-08","2024-06-06",0.99,"RP-240736",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742; 2/4/24: WID:RP-233742->RP-240736",38.761000000000003,97,49,null,null,"2022-09-23","2024-04-02"]
[920,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[921,970281,"   Perf. Part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[922,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"2022-12-13","2024-03-01",1,"RP-240796",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446; 2/4/24: WID:RP-233446->RP-240796",null,98,50,null,null,"2023-01-09","2024-04-02"]
[923,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240796","RP-240159","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"2023-01-09","2024-03-14"]
[924,981247,"   Stopped - Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240796","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"2023-01-09","2024-04-02"]
[925,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"2021-12-13","2025-12-12",0.66,"RP-234027",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027",null,94,48,null,null,"2022-01-06","2024-01-02"]
[926,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","2021-12-13","2023-12-12",1,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[927,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","2021-12-15","2024-06-06",0.7,"RP-233963","RP-240063","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2024-03-14"]
[928,1030060,"   UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 ","NR_FR1_lessthan_5MHz_BW-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.22,"RP-240044","RP-240908","Nokia ",null,"13/6/24: Compl:0%->22%; Stat Rep: ->RP-240908; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[929,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-232957",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957",null,94,48,null,null,"2022-01-06","2024-01-02"]
[930,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[931,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-232957","RP-241174","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[932,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"2021-12-13","2025-12-12",0.77,"RP-234012",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012",null,94,48,null,null,"2022-01-06","2024-01-02"]
[933,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[934,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[935,1030070,"   UE Conformance - Multi-carrier enhancements for NR ","NR_MC_enh-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.18,"RP-240346","RP-241301","China Telecom ",null,"13/6/24: Compl:0%->18%; Stat Rep: ->RP-241301; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[936,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"2021-12-13","2025-12-12",0.73,"RP-233558",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558",null,94,48,null,null,"2022-01-06","2024-01-02"]
[937,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-233558","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[938,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-233558","RP-241294","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[939,1030069,"   UE Conformance - Further NR coverage enhancements ","NR_cov_enh2-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240345","RP-241300","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241300; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[940,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"2021-12-13","2025-12-12",0.73,"RP-233028",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028",null,94,48,null,null,"2022-01-06","2024-01-02"]
[941,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[942,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-233028","RP-241282","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[943,1030072,"   UE Conformance - NR MIMO evolution for downlink and uplink ","NR_MIMO_evo_DL_UL-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.05,"RP-240372","RP-241279","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241279; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[944,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-223041","RP-233435","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...",38.857999999999997,94,48,null,null,"2022-01-06","2023-12-08"]
[945,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"2022-09-08","2024-06-06",1,"RP-232886",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886",null,97,49,null,null,"2022-09-23","2024-01-02"]
[946,970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"2022-09-23","2024-06-13"]
[947,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[948,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","2022-09-08","2024-06-06",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%-...",38.866999999999997,94,48,null,null,"2022-01-06","2022-09-23"]
[949,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-233970",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970",null,94,48,null,null,"2022-01-06","2024-01-02"]
[950,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","2021-12-13","2024-03-01",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[951,940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[952,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-233485",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485",null,94,48,null,null,"2022-01-06","2024-01-02"]
[953,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233485","RP-233484","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[954,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-233976",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976",null,95,48,null,null,"2022-04-05","2024-01-02"]
[955,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[956,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[957,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"2022-03-15","2025-06-06",0.86,"RP-240732",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023; 2/4/24: WID:RP-234023->RP-240732",null,95,48,null,null,"2022-04-05","2024-04-02"]
[958,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"2022-04-05","2024-03-14"]
[959,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","2022-03-16","2024-03-01",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"2022-04-05","2024-03-14"]
[960,1020087,"   UE Conformance - Air-to-ground network for NR ","NR_ATG-UEConTest",2,"Rel-18","R5","2023-12-13","2025-06-06",0.5,"RP-233412","RP-241201","Dan SONG, CMCC","songdan@chinamobile.com","14/3/24: Compl:0%->50%; Stat Rep: ->RP-240148; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 2/4/24: WID:RP-233412->RP-240750. corrected: Rel-19->Rel-18; 13/6/24: WID: RP-240750->RP-233412; Stat Rep: RP-240148->RP-241201; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[961,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"2022-03-15","2025-03-03",0.81,"RP-232791",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791",null,95,48,null,null,"2022-04-05","2024-01-02"]
[962,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-232791","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...",38.890999999999998,95,48,null,null,"2022-04-05","2024-06-13"]
[963,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-232791","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[964,1030065,"   UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-UEConTest",2,"Rel-18","R5","2024-03-03","2025-03-03",0.05,"RP-240125","RP-241175","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241175; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[965,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"2022-03-15","2023-11-30",1,"RP-234020","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"2022-04-05","2024-01-02"]
[{"$f":"A966+1","v":966},950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-234020","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...",38.750999999999998,95,48,null,null,"2022-04-05","2024-06-13"]
[967,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-234020","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[968,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"2022-03-15","2024-06-06",1,"RP-233496",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496",null,95,48,null,null,"2022-04-05","2024-01-02"]
[969,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[970,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","2022-03-17","2024-06-06",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[971,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"2022-03-15","2025-06-06",0.77,"RP-233186",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186",null,95,48,null,null,"2022-04-05","2024-01-02"]
[972,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...",38.881,95,48,null,null,"2022-04-05","2023-12-08"]
[973,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-232366","RP-241240","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[974,1030066,"   UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 ","NR_ENDC_RF_FR1_enh2-UEConTest",2,"Rel-18","R5","2024-03-03","2025-06-06",0.05,"RP-240290","RP-241377","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241377; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[975,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"2022-03-15","2023-12-12",0.97,"RP-233513",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513",null,95,48,null,null,"2022-04-05","2024-01-02"]
[976,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[977,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","2022-03-16","2023-12-12",1,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"2022-04-05","2024-04-02"]
[978,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"2022-03-15","2024-06-06",1,"RP-234021",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021",null,95,48,null,null,"2022-04-05","2024-01-02"]
[979,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[980,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[981,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","2022-12-14","2024-06-06",1,"RP-223246","RP-241346","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ; 8/12/23: FCD:03/03/2024...",null,98,50,null,null,"2023-01-09","2024-06-13"]
[982,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","2021-12-13","2025-06-06",0.78,"RP-233071",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071",null,94,48,null,null,"2022-01-06","2024-01-02"]
[983,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[984,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","2022-03-15","2024-06-06",1,"RP-231461","RP-241045","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"2022-06-04","2024-06-13"]
[985,1030061,"   UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR ","NR_DualTxRx_MUSIM-UEConTest",2,"Rel-18","R5","2024-03-03","2025-06-06",0.05,"RP-240045","RP-240909","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240909; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[986,0,"Rel-18 NR-only: band related","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[987,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","2023-03-06","2023-12-12",0.99,"RP-233245",null,"Vodafone",null,"6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245",null,99,50,null,null,"2023-04-07","2024-01-02"]
[988,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[989,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[990,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","2023-03-06","2024-06-06",0.99,"RP-233999",null,"Vodafone",null,"6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999",null,99,50,null,null,"2023-04-07","2024-01-02"]
[991,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ; 14/...",null,99,50,null,null,"2023-04-07","2024-06-13"]
[992,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","2023-03-08","2024-06-06",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039...",null,99,50,null,null,"2023-04-07","2024-06-13"]
[993,1010055,"Introduction of NR bands n31 and n72 ","NR_bands_n31_n72",1,"Rel-18","R4","2023-09-09","2023-12-12",0.99,"RP-233950",null,"Nokia ",null,"2/1/24: WID:RP-232691->RP-233950",null,101,51,null,null,"2023-10-06","2024-01-02"]
[994,1011055,"   Core part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Core",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[995,1012055,"   Perf. part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Perf",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[996,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991",null,"CATT",null,"6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991",null,99,50,null,null,"2023-04-07","2024-01-02"]
[997,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-233005","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[998,991246,"   Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102",null,99,50,102,null,"2023-04-07","2024-01-02"]
[999,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"2023-01-09","2023-03-29"]
[1000,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1001,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1002,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"2022-12-13","2023-12-12",0.25,"RP-234044",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1003,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated;...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[1004,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eo...",null,98,50,null,null,"2023-01-09","2023-09-21"]
[1005,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",0.93,"RP-240761",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920; 2/4/24: WID:RP-232920->RP-240761",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1006,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240761","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1007,961210,"   Stopped - Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-240761","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1008,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240166",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231; 2/4/24: WID:RP-233231->RP-240166",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1009,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240166","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1010,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-16","2024-06-06",1,"RP-240166","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1011,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"2022-06-16","2023-12-12",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[1012,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[1013,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240238",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990; 2/4/24: WID:RP-233990->RP-240238",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1014,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240238","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1015,961207,"   Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240238","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,102,null,"2022-08-03","2024-06-13"]
[1016,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240501",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696; 2/4/24: WID:RP-233696->RP-240501",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1017,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240501","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1018,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240501","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1019,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"2022-06-15","2023-03-03",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"2022-08-03","2023-03-29"]
[1020,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...",38.892000000000003,96,49,null,null,"2022-08-03","2023-03-17"]
[1021,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"2022-08-03","2023-03-17"]
[1022,960098,"Stopped - Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"2022-06-16","2023-12-12",1,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1023,960198,"   Stopped - Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#10...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1024,960298,"   Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1025,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"2022-06-15","2024-12-12",0.84,"RP-240422",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040; 2/4/24: WID:RP-234040->RP-240422",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1026,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240422","RP-240421","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"2022-08-03","2024-03-14"]
[1027,960295,"   stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240422","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1028,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-12-12",0.49,"RP-232772","RP-240918","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772; 14/3/24: FCD:05/06/2024->12/12/2024; Stat ...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1029,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"2022-06-15","2023-06-06",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"2022-08-03","2023-03-29"]
[{"$f":"A1030+1","v":1030},960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","2022-06-15","2023-06-06",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"2022-08-03","2023-06-07"]
[1031,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","2022-06-15","2023-06-06",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"2022-08-03","2023-03-31"]
[1032,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1033,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1034,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1035,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","2023-03-03","2023-12-12",1,"RP-232783","RP-232784","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP...",null,99,50,null,null,"2023-03-29","2024-01-02"]
[1036,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","2022-06-15","2023-03-03",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualco...",38.893000000000001,96,49,null,null,"2022-07-12","2023-03-31"]
[1037,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.12,"RP-240287","RP-241375","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1038,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1039,1010053,"Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC",1,"Rel-18","R4","2023-09-09","2024-06-06",1,"RP-240307",null,"Oppo ",null,"2/1/24: WID:RP-232674->RP-232941; 2/4/24: WID:RP-232941->RP-240307",null,101,51,null,null,"2023-10-06","2024-04-02"]
[1040,1011053,"   Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2023-09-09","2024-06-06",1,"RP-240307","RP-241150","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;; 14/3/24: FCD:01/03/2024->06/06/2024; Compl:30%->70%; Stat Rep: RP-232940->RP...",38.880000000000003,101,51,null,null,"2023-10-06","2024-06-13"]
[1041,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",0.91,"RP-240241",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977; 2/4/24: WID:RP-233977->RP-240241",null,97,49,null,null,"2022-10-19","2024-04-02"]
[1042,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240241","RP-241143","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...",38.898000000000003,97,49,null,null,"2022-10-19","2024-06-13"]
[1043,970288,"   Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",0.79,"RP-240241","RP-240240","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,102,null,"2022-10-19","2024-03-14"]
[1044,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.55000000000000004,"RP-231199","RP-241305","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ; 14/3...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1045,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"2022-06-15","2024-12-12",0.68,"RP-240361",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180; 2/4/24: WID:RP-233180->RP-240361",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1046,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240361","RP-240942","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....",37.829000000000001,96,49,null,null,"2022-08-03","2024-06-13"]
[1047,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-12-12",0.26,"RP-240095","RP-240913","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ; 14/3/24:...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1048,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.05,"RP-240285","RP-241374","Chunying GU, Huawei Technologies. Co., Ltd.","guchunying@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ; 14/3/24: ...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1049,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-234046",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1050,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234046","RP-232937","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1051,1020088,"UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest",1,"Rel-18","R5","2023-12-13","2025-06-06",0.26,"RP-233771","RP-241376","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240289; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; 2/4/24: corrected: rel-19->Rel-18; 13/6/24: Compl:7%->26%; Stat Rep: RP-240289->RP-241376; ",null,102,52,null,null,"2024-01-02","2024-06-13"]
[1052,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"2022-09-08","2025-06-06",0.88,"RP-240425",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002; 2/4/24: WID:RP-234002->RP-240425",null,97,49,null,null,"2022-09-23","2024-04-02"]
[1053,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","2022-09-08","2024-06-06",1,"RP-240425","RP-241250","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",38.893999999999998,97,49,null,null,"2022-09-23","2024-06-13"]
[1054,970284,"   Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","2022-09-08","2024-03-01",1,"RP-240425","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,102,null,"2022-09-23","2024-01-02"]
[1055,1030068,"   UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-UEConTest",2,"Rel-18","R5","2024-03-03","2025-06-06",0.57999999999999996,"RP-240292","RP-241379","Huawei ",null,"13/6/24: Compl:0%->58%; Stat Rep: ->RP-241379; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[1056,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"2022-09-08","2024-09-09",0.99,"RP-234064",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064",null,97,49,null,null,"2022-09-23","2024-01-02"]
[1057,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",1,"RP-234064","RP-241046","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...",38.869999999999997,97,49,null,null,"2022-09-23","2024-06-13"]
[1058,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-09-09",0.98,"RP-234064","RP-241046","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1059,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",0.91,"RP-240420",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197; 2/4/24: WID:RP-233197->RP-240420",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1060,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240420","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"2022-08-03","2024-06-13"]
[1061,961209,"   Stopped - Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-240420","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1062,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240482",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242; 2/4/24: WID:RP-233242->RP-240482",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1063,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240482","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"2022-08-03","2024-06-13"]
[1064,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","2022-06-16","2024-06-06",1,"RP-240482","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1065,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"2022-06-15","2024-06-06",0.87,"RP-240374",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989; 2/4/24: WID:RP-233989->RP-240374",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1066,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240374","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1067,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.7,"RP-240374","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1068,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",0.91,"RP-240758",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488; 2/4/24: WID:RP-233488->RP-240758",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1069,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240758","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"2022-08-03","2024-06-13"]
[1070,961203,"   Stopped - Perf. Part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.8,"RP-240758","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1071,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240417",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987; 2/4/24: WID:RP-233987->RP-240417",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1072,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240417","RP-241244","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"2022-08-03","2024-06-13"]
[1073,961204,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240417","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1074,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240384",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988; 2/4/24: WID:RP-233988->RP-240384",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1075,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240384","RP-241165","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1076,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240384","RP-240382","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"2022-08-03","2024-03-14"]
[1077,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",0.93,"RP-240760",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923; 2/4/24: WID:RP-232923->RP-240760",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1078,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240760","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1079,961206,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",0.85,"RP-240760","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1080,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",1,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"2022-08-03","2023-03-29"]
[1081,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Comp...",37.878,96,49,null,null,"2022-08-03","2023-12-08"]
[1082,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[1083,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",1,"RP-233588",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588",null,96,49,null,null,"2022-08-03","2024-01-02"]
[1084,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...",37.877000000000002,96,49,null,null,"2022-08-03","2023-12-08"]
[1085,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"2022-08-03","2023-12-08"]
[1086,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1087,1010054,"High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14",1,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946",null,"AT&T ",null,"2/1/24: WID:RP-232676->RP-232946",null,101,51,null,null,"2023-10-06","2024-01-02"]
[1088,1011054,"   Core part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Core",2,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;; 14/3/24: Compl:50%->100%; Stat Rep: RP-232945->RP-240075; List of Impacted TS & TR...",36.770000000000003,101,51,null,null,"2023-10-06","2024-03-14"]
[1089,1012054,"   Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Perf",2,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 14/3/24: Compl:80%->100%; Stat Rep: RP-232945->RP-240075; ",null,101,51,null,null,"2023-10-06","2024-03-14"]
[1090,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-232892",null,"Ericsson ",null,"2/1/24: WID:RP-222824->RP-232892",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1091,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1092,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1093,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"2022-12-12","2025-03-03",0.7,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"2023-01-09","2023-03-29"]
[{"$f":"A1094+1","v":1094},981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","2022-12-12","2023-06-06",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"2023-01-09","2023-06-29"]
[1095,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","2022-12-12","2023-06-06",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1096,1030064,"   UE Conformance - Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-UEConTest",2,"Rel-18","R5","2024-03-03","2025-03-03",0.85,"RP-240096","RP-240915","Nokia ",null,"13/6/24: Compl:0%->85%; Stat Rep: ->RP-240915; ",null,103,52,null,null,"2024-04-02","2024-06-13"]
[1097,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"2023-01-09","2023-03-29"]
[1098,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1099,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-240414",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927; 2/4/24: WID:RP-233927->RP-240414",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1100,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240414","RP-241241","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1101,960299,"   Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240414","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24:...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1102,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"2022-08-03","NA"]
[1103,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"2022-08-03","2023-01-09"]
[1104,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[1105,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[1106,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[1107,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"2017-12-15","2017-12-15",0.34,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1108,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","2023-03-03","2023-09-08",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23:...",null,99,50,null,null,"2023-03-29","2023-09-21"]
[1109,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","2023-03-03","2023-12-12",1,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100",37.911000000000001,99,50,null,null,"2023-03-29","2024-01-02"]
[1110,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","2022-09-08","2023-09-08",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...",38.847999999999999,97,49,null,null,"2022-09-23","2023-10-06"]
[1111,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-231468","RP-233234","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...",38.845999999999997,95,48,null,null,"2022-04-05","2023-12-08"]
[1112,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233171","RP-233170","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"2022-04-05","2024-01-02"]
[1113,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...",38.877000000000002,95,48,null,null,"2022-04-05","2023-06-07"]
[1114,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","2022-03-03","2023-03-03",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...",38.872,95,48,null,null,"2022-04-05","2023-03-17"]
[1115,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","2019-09-19","2022-06-22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"2019-10-08","2022-07-12"]
[1116,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","2020-09-17","2023-03-03",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"2020-09-25","2023-03-17"]
[1117,0,"Rel-18 Network automation","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1118,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"2022-12-09","2022-12-10"]
[1119,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"2021-12-19","2022-12-10"]
[1120,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.738,95,48,null,null,"2022-03-10","2024-03-15"]
[1121,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65; 15/3/24: 65%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-15"]
[1122,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2023-06-08"]
[1123,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[1124,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[1125,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","2022-12-15","2024-03-03",1,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"2022-06-03","2023-06-06"]
[1126,0,"Rel-18 other Studies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1127,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","2019-12-06","2021-12-10",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"2019-12-06","2021-12-10"]
[1128,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","2022-06-02","2023-09-09",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"2022-06-20","2023-06-30"]
[1129,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1130,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","2023-06-30","2024-03-03",1,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30; 8/12/23: 30%->95; 14/3/24: 95%->100","28.531; 28.533; 28.526 ",100,51,null,null,"2023-06-30","2024-03-14"]
[1131,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","2023-05-01","2023-06-06",1,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ","; 8/12/23: 0%->100","32.240; 32.255; 32.256; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2023-12-08"]
[1132,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;; 14/3/24: 60%->100","28.552; 28.554; 28.622 ; 28.318; 28.879",100,51,null,null,"2023-06-08","2024-03-14"]
[1133,980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024; 14/3/24: 55%->100",28.84,98,50,null,null,"2022-12-09","2024-03-14"]
[1134,1040012,"CHF Segmentation ","CHFSeg",1,"Rel-19","S5","2024-06-12","2025-03-03",0.05,"SP-241001",null,"Cetinkaya Egemen Kemal,Verizon ","(egemen.cetinkaya@verizon.com) ",null,"32.290; 32.291 ",null,null,null,null,"2024-06-12","2024-06-13"]
[1135,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90; 14/3/24: 90%->100","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"2022-12-09","2024-03-14"]
[1136,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211441",null,"Cornily Jean-Michel, Huawei","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[1137,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","2021-12-10","2022-12-09",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"2021-12-10","2023-09-07"]
[1138,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"2022-06-02","2022-12-11"]
[1139,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","2022-06-02","2024-03-03",1,"SP-240271",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;; 14/3...","28.552; 32.425; 28.554; 28.550 ; 28.558",96,49,null,null,"2022-06-02","2024-04-02"]
[1140,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","2020-03-25","2023-12-12",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"2019-12-06","2023-06-08"]
[1141,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024; 14/3/24: 70...","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"2022-03-10","2024-03-14"]
[1142,890016,"Study on access control for management service ","FS_MNSAC",1,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"2020-09-11","2021-09-13"]
[1143,930010,"Access control for management service ","MSAC",1,"Rel-18","S5","2021-09-10","2024-03-03",1,"SP-231711",null,"Clifton Fernandes, Nokia ","Clifton.fernandes@nokia.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP...",28.318999999999999,93,47,null,null,"2021-09-10","2024-03-14"]
[1144,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","2021-09-10","2023-12-12",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[1145,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","2020-09-16","2022-03-10",1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100",null,89,45,null,null,"2020-09-10","2023-12-08"]
[1146,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","2021-03-18","2022-03-11",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"2021-03-18","2022-06-04"]
[1147,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[1148,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-231443",null,"Zhang Kai, Huawei ","kai.zhangkai@huawei.com","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;; 14/3/24: 55%->100","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871",99,50,null,null,"2023-03-16","2024-03-14"]
[1149,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100",28.864000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[1150,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added;","28.541; 28.552; 28.554 ; 28.877",99,50,null,null,"2023-03-16","2024-01-04"]
[1151,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100",28.907,94,48,null,null,"2021-12-13","2023-03-17"]
[1152,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100",28.913,94,48,null,null,"2021-12-13","2023-06-08"]
[1153,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-240269",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92; 14/3/...",28.864999999999998,94,48,null,null,"2021-12-13","2024-04-02"]
[1154,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80; 14/3/24: 80%->100",28.908999999999999,94,48,null,null,"2021-12-13","2024-03-14"]
[1155,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","2021-12-13","2023-12-12",1,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100",28.91,94,48,null,null,"2021-12-13","2023-12-08"]
[1156,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100",28.911999999999999,94,48,null,null,"2021-12-13","2023-06-08"]
[1157,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774",28.831,95,48,null,null,"2022-03-10","2023-06-30"]
[{"$f":"A1158+1","v":1158},950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",28.902999999999999,95,48,null,null,"2022-03-10","2023-06-08"]
[1159,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","2022-03-10","2023-03-03",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->",28.832999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[1160,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100","28.541; 28.552; 28.554 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1161,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added;","28.834; 28.869",95,48,null,null,"2022-03-10","2024-01-04"]
[1162,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added;","28.835; 28.878",95,48,null,null,"2022-03-10","2024-01-04"]
[1163,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30; 8/12/23: 30%->60; 14/3/24: 60%->100","32.130; 28.541; 28.552 ",100,51,null,null,"2023-06-08","2024-03-14"]
[1164,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773",28.837,95,48,null,null,"2022-03-10","2023-06-30"]
[1165,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65; 14/3/24: 65%->100",28.83,95,48,null,null,"2022-03-10","2024-03-14"]
[1166,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"2022-06-02","2023-06-08"]
[1167,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","2021-06-11","2023-12-12",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"2021-06-11","2023-12-08"]
[1168,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","2023-03-16","2023-09-09",1,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 8/12/23: 0%->100","32.240; 32.290 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1169,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","2021-06-11","2023-09-09",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"2021-06-11","2023-09-07"]
[1170,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2024-03-14"]
[1171,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","2022-09-12","2023-03-10",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"2022-09-11","2023-03-17"]
[1172,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","2022-09-12","2024-03-03",1,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;; 14/3/24: 80%->100","; 28.842; 28.873",97,49,null,null,"2022-09-11","2024-03-14"]
[1173,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","2022-09-12","2023-12-12",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100",28.838999999999999,97,49,null,null,"2022-09-11","2023-09-07"]
[1174,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-240268",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;; 8/12/23: 0%->60; 14/3/24: 60%->100; 2/4/24: WID:SP-231151->SP-240268","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,51,null,null,"2023-09-06","2024-04-02"]
[1175,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80; 14/3/24: 80%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"2023-03-16","2024-03-14"]
[1176,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30; 8/12/23: 30%->100","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1177,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 65%->100","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"2023-03-16","2024-03-14"]
[1178,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1179,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","2021-06-11","2023-03-03",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...",33.875999999999998,92,47,null,null,"2021-06-11","2023-06-08"]
[1180,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100",33.31,99,50,null,null,"2023-03-16","2023-09-07"]
[1181,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","2022-12-09","2023-03-03",1,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.500999999999998,98,50,null,null,"2022-12-09","2024-03-15"]
[1182,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","NA"]
[1183,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"2022-06-03","2023-06-06"]
[1184,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","2023-06-09"]
[1185,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","2022-06-03","2023-03-03",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"2022-06-03","2022-07-13"]
[1186,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,51,null,null,"2023-06-07","2023-06-30"]
[1187,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","2023-12-12","2023-12-12",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"2018-06-06","2021-09-13"]
[1188,0,"Rel-18 other aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1189,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"2021-03-12","2023-03-03",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[1190,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","2021-03-12","2023-09-09",0.2,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"2021-06-11","2023-03-31"]
[1191,1000001,"Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",1,"Rel-18","C4","2023-06-07","2023-12-12",0.95,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;",29.856999999999999,100,51,null,null,"2023-06-07","2023-06-30"]
[1192,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"2019-03-07","2019-03-07",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"2022-03-13","NA"]
[1193,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","2022-01-05","2023-03-16",1,null,null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"2023-06-08","2023-06-08"]
[1194,1040002,"Update of conformance test specifications to Rel-18","UEConTest_R18",1,"Rel-18","C6","2023-06-29","2025-06-06",0,"CP-241022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,null,92,47,null,null,"2021-08-12","NA"]
[1195,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1196,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1197,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"2019-03-07","2019-12-12",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1198,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[1199,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"2019-05-31","2020-06-26"]
[1200,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","2019-06-06","2021-03-12",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"2019-05-31","2021-03-19"]
[1201,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"2020-06-12","2022-06-10",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","NA"]
[1202,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","2022-03-12"]
[1203,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1204,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"2021-03-18","2022-06-20"]
[1205,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1206,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1207,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1208,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"2020-06-25","2022-06-04"]
[1209,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1210,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","2018-06-06","2019-06-12",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"2018-06-06","2019-09-13"]
[1211,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1212,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","2021-03-18","2022-06-10",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"2021-03-18","2022-06-04"]
[1213,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","2019-03-07","2021-06-11",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"2018-12-06","2021-09-13"]
[1214,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","2019-06-06","2020-03-12",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"2019-05-31","2022-03-22"]
[1215,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","2020-12-04","2021-12-10",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"2020-12-04","2022-03-12"]
[1216,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1217,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1218,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-06-28"]
[1219,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-09-13"]
[1220,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"2020-09-25","2022-06-04"]
[1221,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"2019-05-31","2020-06-25"]
[{"$f":"A1222+1","v":1222},850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"2019-09-13","NA"]
[1223,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"2018-09-06","2019-09-13"]
[1224,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","2019-09-19","2019-12-12",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1225,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"2019-05-31","2020-12-05"]
[1226,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","2020-03-25","2021-09-08",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"2019-05-31","2021-12-10"]
[1227,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"2021-03-18","2021-06-11"]
[1228,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"2021-03-18","2022-06-20"]
[1229,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"2021-03-18","2022-03-12"]
[1230,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"2021-03-18","2022-06-20"]
[1231,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"2019-03-07","2024-12-12",0.85,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1232,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1233,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1234,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-09-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"2021-01-06","2022-09-23"]
[1235,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","2022-09-08","2024-12-12",0.56000000000000005,"RP-222384","RP-241343","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1236,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"2019-05-31","NA"]
[1237,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","2018-09-06","2019-09-13",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"2018-09-06","2019-12-06"]
[1238,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1239,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1240,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"2018-09-06","2019-12-13",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1241,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","2018-09-06","2019-12-13",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[1242,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"2019-05-31","2019-12-06"]
[1243,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","2018-12-06","2020-12-15",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"2018-12-06","2020-12-05"]
[1244,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","2018-12-06","2021-03-12",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"2018-12-06","2021-03-21"]
[1245,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"2020-12-04","2021-03-21"]
[1246,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","2020-12-04","2021-06-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"2020-12-04","2021-07-02"]
[1247,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1248,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1249,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100",33.853999999999999,88,45,null,null,"2020-06-25","2023-03-31"]
[1250,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"2018-09-06","2024-12-12",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"2018-09-06","NA"]
[1251,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","2018-09-06","2018-12-14",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"2018-09-06","2018-12-04"]
[1252,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"2020-12-03","2021-12-10"]
[1253,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1254,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1255,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"2021-03-18","2022-03-12"]
[1256,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1257,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","2021-06-11","2022-03-11",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"2021-06-11","2022-03-12"]
[1258,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","2023-03-03","2024-12-12",1,"RP-230716","RP-241126","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ; 14/3/24: FCD:12/12/2023->12/12/2024; Compl:40%->95%; ...",null,99,50,null,null,"2023-03-29","2024-06-13"]
[1259,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1260,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","NA"]
[1261,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","2018-06-06","2018-09-14",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1262,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","2018-06-06","2020-06-25",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"2018-06-06","2020-06-26"]
[1263,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","2019-12-06","2021-09-08",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","2021-12-10"]
[1264,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2021-06-11"]
[1265,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-06-04"]
[1266,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","2020-09-16","2021-09-10",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1267,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1268,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","2021-09-13","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"2020-09-12","2022-06-04"]
[1269,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"2019-12-16","2024-12-12",0.93,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"2020-01-14","2022-04-05"]
[1270,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","2019-12-16","2022-06-06",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"2020-01-14","2023-03-17"]
[1271,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","2019-12-16","2023-03-03",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1272,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-12-12",0.78,"RP-221241","RP-241155","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"2022-07-12","2024-06-13"]
[1273,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2021-06-15","2024-03-01",0.99,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"2021-07-02","NA"]
[1274,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","2021-06-15","2022-06-22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1275,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-233250","RP-240442","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"2022-07-12","2024-03-14"]
[1276,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1277,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"2022-03-12","2022-06-20"]
[1278,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1279,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1280,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-06-04"]
[1281,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","2019-03-07","2021-03-12",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"2019-03-14","2021-03-21"]
[1282,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2019-12-16","2021-06-15",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"2020-01-14","2021-07-02"]
[1283,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1284,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"2019-09-13","2021-06-11"]
[1285,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","2020-06-12","2021-06-11",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"2020-06-25","2021-06-11"]
[{"$f":"A1286+1","v":1286},920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","2021-06-11","2021-06-18",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-03-24"]
[1287,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"2020-12-03","NA"]
[1288,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"2020-12-03","2021-09-13"]
[1289,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1290,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1291,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1292,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1293,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1294,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1295,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","2021-12-21","2022-03-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1296,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","2019-03-07","2022-09-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1297,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"2019-12-16","2024-12-12",0.99,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1298,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1299,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","2019-12-16","2022-12-21",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1300,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","2022-06-15","2024-12-12",0.98,"RP-221238","RP-241125","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1301,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"2019-12-16","2023-12-12",1,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1302,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"2020-01-14","2022-12-09"]
[1303,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","2020-06-15","2022-12-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...;...",null,86,44,null,null,"2020-09-25","2022-12-09"]
[1304,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221416","RP-232885","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1305,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1306,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"2019-12-16","2024-09-09",0.71,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1307,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","2019-12-16","2022-03-11",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1308,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1309,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-09",0.05,"RP-221448","RP-241344","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1310,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","2019-12-16","2020-09-15",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1311,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","2019-06-06","2020-06-12",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"2019-05-31","2022-03-22"]
[1312,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-02-10"]
[1313,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-06-11"]
[1314,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1315,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1316,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1317,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"2021-03-18","NA"]
[1318,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"2019-09-13","2021-03-19"]
[1319,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","2021-03-18","2021-09-08",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"2021-03-18","2021-12-10"]
[1320,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1321,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"2021-06-11","2022-03-22"]
[1322,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"2021-06-11","2022-06-04"]
[1323,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1324,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","2021-06-15","2023-09-22",0.99,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1325,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"2021-07-02","2022-03-22"]
[1326,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"2021-07-02","2022-03-22"]
[1327,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","2021-12-13","2023-09-22",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[1328,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"2019-12-16","2024-12-12",0.97,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"2020-01-14","2021-09-29"]
[1329,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1330,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","2019-12-16","2022-12-01",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1331,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","2022-06-15","2024-12-12",0.92,"RP-221401","RP-241277","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1332,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1333,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1334,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"2019-12-16","2024-03-01",1,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1335,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1336,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1337,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-01",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"2020-07-28","2023-01-09"]
[1338,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-233247","RP-233246","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"2022-07-12","2024-04-02"]
[1339,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"2019-12-16","2024-06-06",1,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1340,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1341,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1342,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","2023-03-03","2024-06-06",1,"RP-233764","RP-241372","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ; 8/12/23: FCD:03/03/2024->01/03/2024; Compl:46%->94%; Stat Rep: RP-232355->RP-233763; ; 2/1/24: WID...",null,99,50,null,null,"2023-03-29","2024-06-13"]
[1343,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"2019-03-11","2022-09-22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1344,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1345,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1346,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","2019-03-11","2021-12-10",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"2019-03-14","2022-03-12"]
[1347,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"2019-12-16","2022-03-09",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"2020-01-14","2022-01-21"]
[1348,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-09",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1349,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"2020-09-15","2024-09-09",0.97,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126...",null,89,45,null,null,"2020-10-11","2022-07-12"]
[{"$f":"A1350+1","v":1350},941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","2021-12-14","2022-06-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"2022-03-22","2022-06-20"]
[1351,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"2020-10-11","2022-09-09"]
[1352,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-09",0.93,"RP-233586","RP-241299","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1353,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"2020-09-15","2023-12-12",1,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1354,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1355,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Noki...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1356,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221240","RP-233873","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1357,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1358,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1359,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1360,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-06-06",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1361,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1362,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1363,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1364,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"2020-09-15","2024-03-01",1,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366...",38.850999999999999,89,45,null,null,"2020-10-11","2022-07-12"]
[1365,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1366,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1367,970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",1,"RP-240751","RP-240092","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"2022-09-23","2024-04-02"]
[1368,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"2020-09-15","2024-12-12",0.83,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1369,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1370,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1371,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","2022-06-15","2024-12-12",0.6,"RP-221402","RP-241276","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1372,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1373,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporati...",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1374,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1375,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"2020-09-15","2024-03-01",1,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"2020-10-11","2022-04-05"]
[1376,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1377,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1378,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-221848","RP-240280","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"2022-07-12","2024-03-14"]
[1379,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","2021-12-13","2022-09-22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"2022-01-06","2022-04-05"]
[1380,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1381,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1382,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"2022-07-12","2022-09-23"]
[1383,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1384,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1385,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1386,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1387,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"2019-12-06","2022-06-21"]
[1388,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","2019-09-19","2020-09-14",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"2019-09-13","2020-09-13"]
[1389,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","2020-06-12","2021-12-10",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"2020-06-26","2021-12-13"]
[1390,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1391,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"2019-05-31","2021-06-11"]
[1392,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","2018-09-14","2020-03-12",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"2018-09-14","2020-12-05"]
[1393,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"2020-06-25","2022-03-12"]
[1394,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","2019-09-19","2020-03-12",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"2019-09-13","2020-03-26"]
[1395,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"2019-03-07","2024-03-03",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1396,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"2019-03-14","2021-03-19"]
[1397,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","2020-12-03","2021-09-10",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-06-04"]
[1398,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"2021-06-11","2022-06-04"]
[1399,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"2021-06-11","2022-06-20"]
[1400,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"2021-06-11","2022-06-20"]
[1401,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"2022-06-20","NA"]
[1402,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1403,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-231712",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30; 8/12/23: 30%->65; 3/1/24: WID:SP-230623->SP-231712; 14/3/24: 65%->100","32.240; 32.255; 32.298; 32.291; 33.279; 33.290",100,51,null,null,"2023-06-08","2024-03-14"]
[1404,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","2019-09-02","2019-12-12",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1405,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1406,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","2019-12-16","2023-12-12",0.99,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1407,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1408,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",1,"RP-220423","RP-233760","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1409,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"2020-09-11","2021-03-21"]
[1410,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"2020-09-11","2021-06-11"]
[1411,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1412,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"2019-12-06","2022-03-11",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1413,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"2019-12-06","2021-06-11"]
[{"$f":"A1414+1","v":1414},890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","2020-06-17","2022-03-11",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"2020-09-25","2022-06-04"]
[1415,880020,"Protocol enhancements for Mission Critical Services ","MCProtoc17",1,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-202193",null,"AXELL, Jörgen ","jorgen.axell@ericsson.com ","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/12/21: 70%-> ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1416,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","2018-12-13","2022-03-11",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"2018-12-07","2022-06-04"]
[1417,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","2020-09-16","2021-09-08",0.65,null,null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"2020-09-25","2021-09-13"]
[1418,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1419,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"2019-03-07","2022-06-07",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"2019-12-06","2020-03-26"]
[1420,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","2019-03-07","2019-12-05",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-03-26"]
[1421,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"2019-12-06","2021-06-11"]
[1422,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"2020-12-05","2021-06-11"]
[1423,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","2020-12-07","2022-03-11",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"2020-12-05","2022-06-04"]
[1424,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","2020-12-07","2022-03-11",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1425,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"2022-06-20","2022-08-03"]
[1426,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-12-05"]
[1427,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1428,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1429,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"2021-03-18","2021-09-10"]
[1430,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"2021-03-18","2022-06-04"]
[1431,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"2021-03-18","2022-03-12"]
[1432,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"2021-03-18","2022-06-04"]
[1433,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","2021-06-11","2021-12-10",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"2021-06-11","2022-03-12"]
[1434,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","2021-06-11","2022-03-11",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1435,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"2020-06-25","2022-03-12"]
[1436,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"2021-12-10","2022-06-04"]
[1437,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"2021-09-10","2022-03-22"]
[1438,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","2020-06-25","2021-12-10",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"2020-06-26","2022-06-21"]
[1439,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"2021-09-10","2022-06-04"]
[1440,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","2020-03-25","2021-09-08",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"2019-12-06","2021-09-13"]
[1441,0,"Rel-17 Slicing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1442,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"2021-06-11","2022-04-28"]
[1443,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"2021-06-11","2022-06-20"]
[1444,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1445,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1446,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1447,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"2019-09-19","2023-06-06",0.99,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1448,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"2019-09-13","2021-03-19"]
[1449,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-22"]
[1450,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","2021-03-18","2023-06-06",0.99,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"2021-03-18","2021-10-01"]
[1451,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1452,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"2021-03-18","2022-06-04"]
[1453,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"2021-03-18","2022-03-12"]
[1454,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","2022-03-15","2023-06-06",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"2022-04-05","2023-06-07"]
[1455,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","2019-03-07","2023-09-22",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1456,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","2021-03-12","2022-06-22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1457,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","2022-06-15","2023-09-22",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17.....",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1458,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","2022-06-03","2022-06-20",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-03","2022-06-04"]
[1459,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-20","2022-08-03"]
[1460,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","2019-12-06","2021-12-10",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"2019-12-06","2021-12-13"]
[1461,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","2022-03-10","2022-03-11",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"2022-03-10","2022-03-12"]
[1462,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1463,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","NA"]
[1464,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","2019-03-07","2019-09-06",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"2019-03-14","2019-12-06"]
[1465,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1466,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"2018-12-06","2021-09-13"]
[1467,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1468,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1469,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1470,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1471,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"2020-12-04","2021-09-13"]
[1472,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"2019-12-09","2023-09-22",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"2020-06-10","2022-01-06"]
[1473,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","2019-12-09","2022-03-22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"2020-06-10","2022-06-20"]
[1474,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1475,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1476,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"2019-06-06","2021-12-10",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1477,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","2019-06-06","2020-12-11",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[{"$f":"A1478+1","v":1478},890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"2020-09-10","2022-03-12"]
[1479,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1480,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"2020-09-11","2021-06-11"]
[1481,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"2020-09-11","2021-12-13"]
[1482,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"2021-09-10","NA"]
[1483,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"2021-09-10","2022-06-04"]
[1484,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"2021-09-10","2022-03-12"]
[1485,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","2021-09-29","2024-06-06",0.99,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"2021-09-29","NA"]
[1486,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"2021-09-29","2022-03-12"]
[1487,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"2021-09-29","2022-06-04"]
[1488,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","2023-06-08","2024-06-06",1,"RP-230873","RP-240910","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ; 14/3/24: FCD:03/03/2024->06/06/2024; Compl:5%->74%; Stat Rep: RP-231826->RP-240115; ; ...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1489,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"2020-09-25","2021-06-11"]
[1490,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.866999999999997,89,45,null,null,"2020-09-25","2023-03-31"]
[1491,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.500999999999998,93,47,null,null,"2021-09-10","2023-03-31"]
[1492,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"2021-03-18","2021-12-13"]
[1493,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","2021-12-13","2024-03-01",0.99,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"2022-01-06","2023-03-29"]
[1494,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"2022-01-06","2022-06-04"]
[1495,970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",1,"RP-240048","RP-240047","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"2022-09-23","2024-04-02"]
[1496,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1497,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","2021-06-12","2021-06-12",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"2021-08-12","2022-03-11"]
[1498,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"2021-03-18","2022-03-11",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2021-09-13"]
[1499,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1500,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"2021-12-10","2022-06-04"]
[1501,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"2021-12-10","2022-03-12"]
[1502,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1503,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->",33.534999999999997,92,47,null,null,"2021-06-11","2022-09-12"]
[1504,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[1505,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"2022-03-10","2022-06-04"]
[1506,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","2020-12-07","2020-12-18",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-05","2020-12-05"]
[1507,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1508,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"2019-03-07","2021-09-10",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1509,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","2019-05-09","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1510,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"2020-12-05","2021-03-21"]
[1511,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1512,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1513,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"2020-12-04","2021-12-13"]
[1514,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"2020-12-04","2021-03-21"]
[1515,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","2020-12-04","2021-06-15",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"2020-12-04","2021-09-13"]
[1516,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"2021-06-11","2022-06-04"]
[1517,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100",29.548999999999999,92,47,null,null,"2021-06-11","2022-06-04"]
[1518,940018,"   Security for eSEAL ","eSEAL",2,"Rel-17","S3","2021-12-10","2021-12-10",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100",33.433999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1519,900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"2019-03-07","2024-06-06",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1520,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"2019-06-26","2021-03-19"]
[1521,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","2020-12-03","2021-06-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"2020-12-03","2021-09-13"]
[1522,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1523,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"2021-03-18","2022-06-04"]
[1524,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"2021-03-18","2021-12-13"]
[1525,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"2021-03-18","2022-03-12"]
[1526,1010050,"   UE Conformance - ATSSS_Ph2","ATSSS_Ph2-UEConTest",2,"Rel-17","R5","2023-09-11","2024-06-06",1,"RP-231827","RP-240911","China Telecom ",null,"13/6/24: FCD:09/09/2024->06/06/2024; Compl:0%->100%; Stat Rep: ->RP-240911; ",null,101,51,null,null,"2023-10-06","2024-06-13"]
[1527,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"2020-12-03","NA"]
[1528,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","2019-06-06","2020-12-15",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"2019-05-31","2021-03-19"]
[1529,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","2020-09-16","2022-03-11",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22",33.866,89,45,null,null,"2020-09-10","2022-03-12"]
[1530,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1531,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"2021-03-19","2021-06-11"]
[1532,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"2021-03-19","2022-06-04"]
[1533,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1534,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1535,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"2019-03-07","2022-06-10",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"2020-12-03","NA"]
[1536,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"2019-03-14","2021-12-10"]
[1537,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-12"]
[1538,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"2021-03-18","2022-07-13"]
[1539,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1540,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100",29.556999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1541,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90",29.559000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[{"$f":"A1542+1","v":1542},920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"2021-03-18","2022-06-04"]
[1543,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"2020-09-10","2022-06-21"]
[1544,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1545,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ",33.847000000000001,88,45,null,null,"2020-06-25","2022-06-04"]
[1546,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"2021-09-10","2023-03-31"]
[1547,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1548,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","2021-03-12","2022-03-22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, h...",38.350999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1549,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1550,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"2019-09-13","2020-06-26"]
[1551,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","2019-09-19","2020-06-12",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"2019-09-13","2022-03-12"]
[1552,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"2020-09-11","2020-09-25"]
[1553,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100",24.501000000000001,89,45,null,null,"2020-09-11","2022-03-12"]
[1554,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"2020-09-11","2022-03-12"]
[1555,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"2020-09-11","2022-03-12"]
[1556,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","2020-09-17","2024-09-09",0.98,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1557,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","2020-09-17","2022-03-11",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1558,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-09",0.96,"RP-221300","RP-241304","Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm","gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222942; Rapporteur: ChinaTelecom->Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm; Rap eMail: ->gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com; 17/3/23: FCD:30/11/202.....",null,96,49,null,null,"2022-07-12","2024-06-13"]
[1559,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"2017-12-15","2022-03-11",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"2019-05-31","NA"]
[1560,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","2017-12-15","2019-09-12",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"2017-12-15","2020-08-17"]
[1561,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","2019-09-19","2020-06-12",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,96,null,"2019-09-13","2022-03-22"]
[1562,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1563,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","2020-03-25","2021-06-11",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"2020-03-25","2022-03-12"]
[1564,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"2020-06-26","NA"]
[1565,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1566,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1567,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1568,890011,"Mission critical security enhancements phase 2 ","MCXSec2",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200879",null,"Woodward, Tim, Motorola Solutions, Inc, ","tim.woodward@motorolasolutions.com ","; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 80%->82; 13/12/21: 82%->100",33.18,89,45,null,null,"2020-09-11","2021-12-13"]
[1569,890070,"PAP/CHAP protocols usage in 5GS ","PAP_CHAP",1,"Rel-17","ct","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 29.561 ; 12/3/22: 99%->100",null,89,45,null,null,"2020-09-25","2022-03-12"]
[1570,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1571,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","2020-09-16","2021-03-12",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1572,890001,"Service-based support for SMS in 5GC ","SMS_SBI",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","25/9/20: WID:CP-202028->CP-202242; 10/9/21: WID:CP-202242->CP-212023",null,89,45,null,null,"2020-09-11","2021-09-10"]
[1573,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"2020-09-11","2022-03-12"]
[1574,890029,"   CT4 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35; 13/9/21: FCD:Wed 08/09/->03/22; 13/9/21: 35%->40; 1/10/21: 23.540 added;; 13/12/21: 40%->45; 12/3/22: 45%->65; 22/3/22: 29.577 added;; 22/3/22: 29.579 added;; 22/3/22:...","29.503; 29.540; 29.571; 23.540; 29.577; 29.579; 29.578",89,45,null,null,"2020-09-11","2022-08-03"]
[1575,840048,"Enhanced Relays for Energy eFficiency and Extensive Coverage ","REFEC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1576,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100",22.866,81,41,null,null,"2018-09-06","2019-12-06"]
[1577,840034,"   Stage 1 of REFEC","REFEC",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ","13/9/19: 0%->90; 6/12/19: 90%->100",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-06"]
[1578,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1579,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","2018-06-06","2019-03-14",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100",22.841999999999999,80,41,null,null,"2018-06-06","2019-05-31"]
[1580,840030,"   Stage 1 of NCIS","NCIS",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191039",null,"Ning YANG, oppo ","yangning@oppo.com ","13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1581,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","2019-06-06","2021-06-11",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"2019-05-31","2021-06-11"]
[1582,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","2020-09-16","2021-06-11",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"2020-09-10","2021-06-11"]
[1583,880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"2019-09-02","2020-12-11",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1584,850041,"   Stage 1 of MuDE","MuDE",2,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1585,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","2020-06-25","2020-12-11",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"2020-06-26","2021-06-11"]
[1586,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"2020-06-26","2021-09-10"]
[1587,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1588,880014,"   CT4 aspects of BEPoP","BEPoP",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 45%->55; 13/12/21: 55%->80; 12/3/22: 80%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1589,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","2020-06-25","2021-09-10",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"2020-06-25","2021-12-13"]
[1590,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100",23.18,84,43,null,null,"2019-05-31","2020-12-05"]
[1591,840016,"Stopped - Supporting Flexible Local Area Data Network ","FLADN",1,"Rel-17","S2","2019-06-06","2020-09-11",1,"SP-190563",null,"LG Electronics, Hyunsook Kim ","hyuns.kim@lge.com ","21/1/22: stopped at 0%; 21/1/22: 0%->100","23.501; 23.502 ",84,43,95,null,"2019-05-31","2022-01-21"]
[1592,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","2018-12-13","2022-03-11",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"2019-03-14","2022-03-12"]
[1593,860012,"Handsets Featuring Non-Traditional Earpieces","HaNTE",1,"Rel-17","S4","2019-12-06","2022-03-11",1,"SP-190989",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com","25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11 ","26.131; 26.132; 26.801",86,44,null,null,"2019-12-06","2022-03-12"]
[1594,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-03-12"]
[1595,920008,"   Stage 2 of EVEX","EVEX",2,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-06-04"]
[1596,960021,"   Stage 3 (CT3) of EVEX","EVEX",2,"Rel-17","C3","2022-06-01","2022-06-10",1,"CP-222128",null,"Waqar Zia, Qualcomm Incorporated","wzia@qti.qualcomm.com",null,"29.522; 29.517; 29.591",96,49,null,null,"2022-05-30","NA"]
[1597,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","2021-06-11","2021-09-08",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"2021-06-11","2021-12-13"]
[1598,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"2021-06-11","2022-03-12"]
[1599,920011,"8K Television over 5G ","8K_TV_5G",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210381",null,"Thomas Stockhammer ","tsto@qti.qualcomm.com ","; 13/9/21: 0%->40; 13/12/21: 40%->60; 12/3/22: 60%->100","26.955;26.925;26.511;26.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1600,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","2019-03-07","2019-03-21",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"2017-12-15","2019-03-14"]
[1601,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1602,880049,"Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON",1,"Rel-17",null,"2019-09-02","2023-03-03",1,"CP-210148",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148",22.260999999999999,85,43,null,null,"2019-09-13","2021-06-13"]
[1603,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","2019-09-02","2021-06-18",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100",22.260999999999999,85,43,null,null,"2019-09-13","2022-03-11"]
[1604,880022,"   Stage 3 (CT1) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50; 13/9/21: 50%->70; 13/9/21: FCD:Fri 18/06/->03/22; 13/12/21: 70%->92; 12/3/22: 92%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1605,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"2020-06-26","2022-03-12"]
[{"$f":"A1606+1","v":1606},920061,"   Stage 3 (CT6) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C6","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/9/21: 0%->70; 13/9/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100; 4/6/22: 100 ",null,92,47,null,null,"2020-06-26","2022-06-04"]
[1607,970073,"   UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON-UEConTest",2,"Rel-17","R5","2022-09-08","2023-03-03",1,"RP-222255","RP-230359","Masahiro Takano, NTT DOCOMO, INC","masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->80%; Stat Rep: ->RP-223159; Rapporteur: NTT DOCOMO->Masahiro Takano, NTT DOCOMO, INC; Rap eMail: ->masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com; 17/3/23: FCD:09/09/2023->03/03/2023; Compl:80%->100%; ...",null,97,49,null,null,"2022-09-23","2023-03-17"]
[1608,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2020-12-05"]
[1609,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","2019-09-19","2021-12-10",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2021-12-13"]
[1610,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1611,910047,"   Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",2,"Rel-17","S3","2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 24/3/22: 0%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2021-03-19","2022-03-24"]
[1612,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"2019-09-13","NA"]
[1613,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[1614,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","2019-09-13","2019-12-12",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"2019-09-13","2019-12-06"]
[1615,920062,"   Stage 2 of MINT","MINT",2,"Rel-17","S2","2021-08-12","2021-12-10",1,"SP-210582",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","13/9/21: 0%->50; 10/12/21: 50%->90; 12/3/22: 90%->98; 4/6/22: 98%->100","23.501; 23.502 ",92,47,null,null,"2021-08-12","2022-06-04"]
[1616,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","2020-12-07","2021-03-12",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"2020-12-05","2021-09-13"]
[1617,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","NA"]
[1618,930049,"      CT1 aspects of MINT","MINT",3,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 13/12/21: 0%->50; 12/3/22: 50%->85; 4/6/22: 85%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1619,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-20"]
[1620,930048,"      CT6 aspects of MINT","MINT",3,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->100; 4/6/22: 100%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1621,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","2022-03-10","2022-03-11",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100",33.500999999999998,95,48,null,null,"2022-03-10","2022-03-22"]
[1622,860008,"IMS emergency support for Stand-alone Non-Public Network (SNPN)","IESNPN",1,"Rel-17","S1","2019-12-06","2019-12-13",1,"SP-191038",null,"Wong, Curt; ","curt.wong@charter.com ","6/12/19: 0%->100","22.101; 22.261; 22.228 ",86,44,null,null,"2019-12-06","2019-12-06"]
[1623,870023,"Management of non-public networks (NPN)","OAM_NPN",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200189",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21; 13/9/21: 50%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->100","28.541; 28.531; 28.533; 28.552; 28.554 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1624,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","2019-12-06","2021-06-11",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"2019-12-06","2021-12-13"]
[1625,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"2020-03-25","2020-06-26"]
[1626,890013,"   eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) ","SCAS_5G_NSSAAF",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200720",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->100","33.926; 33.326",89,45,null,null,"2020-09-11","2021-09-13"]
[1627,870017,"   eSCAS_5G for Non-3GPP InterWorking Function","SCAS_5G_N3IWF",2,"Rel-17","S3","2020-03-25","2021-12-10",1,"SP-200146",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->100","33.926; 33.520",87,44,null,null,"2020-03-25","2021-12-13"]
[1628,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"2020-03-25","2022-06-04"]
[1629,870019,"   eSCAS_5G for Service Communication Proxy","SCAS_5G_SECOP",2,"Rel-17","S3","2020-03-25","2022-06-09",1,"SP-200148",null,"Wei Lu, Nokia","wei.lu@nokia-sbell.com","26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 70%->95; 12/3/22: 95%->95; 12/3/22: FCD:10/12/2021->06/22; 31/3/23: 95%->100","33.522; 33.926",87,44,null,null,"2020-03-25","2023-03-31"]
[1630,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"2020-06-25","2021-09-13"]
[1631,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2020-06-28"]
[1632,870016,"   Stage 2 aspects of enh3MCPTT","enh3MCPTT",2,"Rel-17","S6","2020-03-25","2021-06-15",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-06-11"]
[1633,900039,"   Stage 3 aspects of enh3MCPTT","enh3MCPTT-CT",2,"Rel-17","C1","2020-09-14","2021-09-08",1,"CP-202188",null,null,null,"; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48; 13/12/21: 48%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1634,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","2019-06-06","2021-12-10",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"2019-05-31","2022-03-12"]
[1635,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","2018-12-13","2021-03-12",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"2018-12-06","2021-06-11"]
[1636,890012,"Enhancements to User Plane Integrity Protection Support in 5GS ","eUPIP_SEC",1,"Rel-17","S3","2020-09-16","2021-03-12",1,"SP-200719",null,"Anand Palanigounder, Qualcomm Incorporated ","apg@qti.qualcomm.com ","; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100",33.500999999999998,89,45,null,null,"2020-09-11","2021-03-19"]
[1637,950040,"Non-Seamless WLAN offload in 5GS ","NSWO_5G",1,"Rel-17","S3","2021-05-25","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ",null,33.500999999999998,95,48,null,null,"2021-12-10","NA"]
[1638,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","2021-05-25","2021-09-08",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"2021-05-25","2022-06-04"]
[1639,940011,"   Security aspects of NSWO","NSWO_5G",2,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ","; 12/3/22: FCD:12/12/2021->3/22; 12/3/22: 0%->100",33.500999999999998,94,48,null,null,"2021-12-10","2022-03-12"]
[1640,950041,"   CT1 aspects of NSWO","NSWO_5G",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 22/3/22: 0%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-03-22"]
[1641,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1642,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1643,990122,"Lawful Interception Rel-17 ","LI17",1,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1644,860025,"   Lawful Interception Rel-17 general aspects","LI17",2,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1645,990120,"   (IETF) PASSporT Extension for Rich Call Data (draft-ietf-stir-passport-rcd)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1646,990121,"   (IETF) Messaging Use Cases and Extensions for STIR (draft-ietf-stir-messaging)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1647,850047,"(Small) Technical Enhancements and Improvements for Rel-17","TEI17",1,"Rel-17",null,"2020-03-11","2022-03-11",1,null,null,null,null,null,null,85,43,null,null,"2015-06-15","2015-06-15"]
[1648,940047,"   IMS Optimization for HSS Group ID in an SBA environment (St. 2)","TEI17_IMSGID",2,"Rel-17","S2","2020-03-11","2022-03-11",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1649,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1650,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","2020-03-11","2022-03-11",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100",24.228999999999999,94,48,null,null,"2021-12-10","2022-03-12"]
[1651,910044,"   Same PCF Selection For AMF and SMF ","TEI17_SPSFAS",2,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ",null,null,88,45,null,null,"2020-06-25","NA"]
[1652,880016,"      Stage 2 for TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ","23.501, 23.502 ; 19/3/21: 0%->100",null,88,45,null,null,"2020-06-25","2021-03-19"]
[1653,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1654,910045,"         CT3 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C3","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184; 13/9/21: 98%->100",29.513000000000002,91,46,null,null,"2021-03-18","2021-09-13"]
[1655,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"2021-03-18","2021-09-13"]
[1656,930036,"   System enhancement for Redundant PDU Session ","TEI17_SE_RPS",2,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1657,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1658,930001,"      CT aspects of TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ",null,"24.501; 24.526; 27.007; 29.513; 29.525; 29.561; 29.502 ",93,47,null,null,"2021-09-10","NA"]
[1659,930037,"         CT1 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","24.501; 24.526; 27.007",93,47,null,null,"2021-09-10","2021-12-13"]
[1660,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"2021-09-10","2022-03-12"]
[1661,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100",29.501999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[1662,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"2020-03-25","2021-09-10",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1663,870004,"      Stage 2 for TEI17_SAPES","TEI17_SAPES",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ","19/3/21: 0%->100","23.228; 23.167",87,44,null,null,"2020-06-10","2021-03-19"]
[1664,910020,"      CT aspects on TEI17_SAPES","TEI17_SAPES",3,"Rel-17","ct","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ",null,"24.229; 29.165 ",91,46,null,null,"2021-03-19","NA"]
[1665,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1666,910080,"         CT3 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1667,910081,"   Dynamically Changing AM Policies in the 5GC ","TEI17_DCAMP",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,null,null,87,44,null,null,"2020-06-10","NA"]
[1668,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"2020-06-10","2021-03-19"]
[1669,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"2021-03-19","2021-09-10"]
[{"$f":"A1670+1","v":1670},910082,"         CT3 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: 0%->30; 13/9/21: 30%->50; 13/12/21: 50%->75; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1671,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1672,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"2020-06-10","2021-03-19"]
[1673,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"2020-06-10","NA"]
[1674,870007,"      Stage 2 for TEI17_GEM ","TEI17_GEM",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com","11/6/21: 0%->100",23.681999999999999,87,44,null,null,"2020-06-10","2021-06-11"]
[1675,910010,"      CT aspects on TEI17_GEM ","TEI17_GEM",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: WID:CP-210185->CP-211195; 10/9/21: WID:CP-211195->CP-212165","29.122 29.336 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1676,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1677,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1678,920041,"   Support of different slices over different Non 3GPP access ","TEI17_N3SLICE",2,"Rel-17",null,"2020-03-11","2021-06-18",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1679,870008,"      Stage 2 for TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1680,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-10-01"]
[1681,920001,"      CT4 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C4","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-06-11"]
[1682,910087,"   N7/N40 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",2,"Rel-17",null,"2020-03-11","2021-09-10",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1683,870009,"      Stage 2 for TEI17_NIESGU","TEI17_NIESGU",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ","11/6/21: 0%->100","23.060; 23.401; 23.503; 23.203 ",87,44,null,null,"2020-06-10","2021-06-11"]
[1684,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1685,910011,"      CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194; 13/9/21: 90%->100","29.512; 29.513 ",91,46,null,null,"2021-03-19","2021-09-13"]
[1686,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"2021-03-19","2021-09-13"]
[1687,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","2021-12-10","2022-03-22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"2022-04-21","NA"]
[1688,880019,"Stage-3 5GS NAS protocol development 17 ","5GProtoc17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","NA"]
[1689,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1690,880045,"   Stage-3 5GS NAS protocol development 17 non-IETF aspects","5GProtoc17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","1/10/21: 0%->70; 23/9/22: 70%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","2022-09-23"]
[1691,880021,"Stage-3 SAE Protocol Development ","SAES17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1692,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1693,880047,"   Stage-3 SAE Protocol Development CSFB aspects","SAES17-CSFB",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1694,880048,"   Stage-3 SAE Protocol Development non 3GPP aspects","SAES17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1695,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","2020-06-25","2024-06-06",0.79,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"2020-06-26","2021-03-21"]
[1696,880023,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 20%->40; 13/9/21: 40%->60; 13/12/21: 60%->80; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 80%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1697,911035,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 0%->60; 13/9/21: 60%->70; 13/12/21: 70%->85; 12/3/22: 85%->100; 12/3/22: FCD:10/09/2021->3/22","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1698,1000055,"   UE Conformance - IMS Data Channel ","IMSProtoc17_dataCH-UEContest",2,"Rel-17","R5","2023-06-07","2024-06-06",0.08,"RP-240283","RP-241373","Zhaobing Yang, Huawei Technologies. Co., Ltd","yangzhaobing@huawei.com","6/9/23: FCD:12/12/2023->22/09/2023; Compl:0%->5%; Stat Rep: ->RP-232356; Rapporteur: HiSilicon->Zhaobing Yang, Huawei Technologies. Co., Ltd; Rap eMail: ->yangzhaobing@hisilicon.com; ; 6/10/23: WID:RP-231246->RP-232357; 8/12/23: FCD:22/09/2023->09/09/2...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1699,880032,"Packet Flow Description (PFD) management enhancement ","pfdManEnh",1,"Rel-17","C3","2020-06-25","2021-06-11",1,"CP-210183",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100","29.251; 29.551 ",88,45,null,null,"2020-06-26","2021-06-11"]
[1700,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1701,880053,"   CT3 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088; 13/9/21: 65%->75; 13/12/21: 75%->85; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 85%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1702,880054,"   CT4 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50; 13/9/21: 50%->60; 13/12/21: 60%->80; 13/12/21: FCD:Mon 20/09/->03/22; 12/3/22: 80%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1703,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1704,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1705,970052,"   CT3 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C3","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1706,970053,"   CT4 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1707,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","2021-12-10","2022-06-10",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1708,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1709,820009,"Study on authentication enhancements in 5GS","FS_AUTH_ENH",1,"Rel-17","S3","2018-12-13","2021-12-10",1,"SP-190713",null,"Tsiatsis, Vlasios, ","vlasios.tsiatsis@ericsson.com ","07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202 ","new",82,42,null,null,"2018-12-06","2022-03-12"]
[1710,940012,"Authentication enhancements in 5GS ","AUTH_ENH",1,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211360",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 24/3/22: 0%->100",33.101999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1711,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"2022-03-10","2022-03-12"]
[1712,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"2022-03-10","2022-06-20"]
[1713,990004,"Update of conformance test specifications to Rel-17","UEConTest_R17",1,"Rel-17","C6","2021-06-14","2024-06-06",1,"CP-230022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com","Tests eV2XARC_Ph2;eCPSOR_CON;5G_ProSe;5GSAT_ARCH-CT;ING_5GS;MINT;NSWO_5G;ARCH_NR_REDCAP;IoT_SAT_ARCH_EPS","31.121; 31.124",92,47,null,null,"2021-08-12","NA"]
[1714,0,"Rel-17 Management-only Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1715,900021,"Management Aspects of 5G Network Sharing ","MANS",1,"Rel-17","S5","2020-12-04","2022-03-11",1,"SP-201080",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25; 13/9/21: 25%->30; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 30%->60; 12/3/22: 60%->100",null,90,46,null,null,"2020-12-04","2022-03-12"]
[1716,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","2021-06-11","2021-12-10",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"2021-06-11","2021-12-13"]
[1717,910030,"File Management ","FIMA",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210135",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 11/6/21: 0%->25; 13/9/21: 25%->60; 13/12/21: 60%->75; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 75%->100","28.537; 28.622; 28.623; 28.532 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1718,930032,"Improved support for NSA in the service-based management architecture ","NSA_SBMA",1,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-211121",null,"Lan Zou, Huawei ","zoulan@huawei.com ",null,"28.623; 28.622; 28.659; 28.663 ",91,46,null,null,"2021-09-10","NA"]
[1719,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1720,880029,"Enhancement of Handover Optimization ","E_HOO",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200466",null,"Elmdahl, Per, Ericsson ","per dot Elmdahl at Ericsson dot com ","28.552; 28.313; 28.541 ; 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:18/06/2021->03/22; 11/6/21: 10%->30; 13/9/21: 30%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1721,880028,"Management data collection control and discovery ","MADCOL",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200465",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30; 13/9/21: 30%->35; 13/9/21: FCD:Wed 22/09/->03/22; 13/12/21: 35%->40; 12/3/22: 40%->45; 4/6/22: 45%->100",null,88,45,null,null,"2020-06-26","2022-06-04"]
[1722,880026,"Management of the enhanced tenant concept ","eMEMTANE",1,"Rel-17","S5","2020-06-26","2021-12-15",1,"SP-220293",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->20; 12/3/22: 20%->100; 22/3/22: WID:SP-200463->SP-220293",null,88,45,null,null,"2020-06-26","2022-03-22"]
[1723,880025,"Enhancements of 5G performance measurements and KPIs ","ePM_KPI_5G",1,"Rel-17","S5","2020-06-12","2022-03-11",1,"SP-200462",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","28.552; 32.425; 28.554; 32.426; 32.450; 32.451; 32.455 ; 13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->40; 11/6/21: 40%->50; 13/9/21: 50%->60; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1724,810027,"Intent driven management service for mobile network","IDMS_MN",1,"Rel-17","S5","2018-09-06","2022-03-11",1,"SP-180899",null,"Zou Lan, Huawei ","zoulan@huawei.com","7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[1725,820035,"Discovery of management services in 5G ","5GDMS",1,"Rel-17","S5","2018-12-13","2022-03-11",1,"SP-200770",null,"Brendan Hassett, Huawei Technologies Sweden AB ","brendan.t.hassett@huawei.com","¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ","28.533; 28.532; 28.531 ",82,42,null,null,"2018-12-07","2022-03-12"]
[1726,860024,"Network policy managementfor 5G mobile networks ","NPM",1,"Rel-17","S5","2019-12-06","2022-03-11",1,"SP-191211",null,"China Mobile Shasha Guo ","guoshasha@chinamobile.com ","; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75; 13/9/21: 75%->78; 13/12/21: 78%->100","28.532; 28.541 ",86,44,null,null,"2019-12-06","2021-12-13"]
[1727,850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","2019-09-19","2021-03-12",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"2019-09-13","2021-03-21"]
[1728,940078,"Enhancements of Management Data Analytics Service ","eMDAS",1,"Rel-17","S5","2021-03-18","2021-12-10",1,"SP-210132",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 13/9/21: 0%->10; 13/9/21: FCD:Fri 10/12/->12/21; 13/12/21: 10%->45. UID was at 0, corrected; 12/3/22: 45%->65; 4/6/22: 65%->100","28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533; 28.105",91,46,null,null,"2021-03-18","2022-06-04"]
[1729,870022,"Enhancements on EE for 5G networks ","EE5GPLUS",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200188",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->55; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->70; 13/12/21: 70%->100","28.310; 28.552; 28.554; 28.541 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1730,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","2020-03-25","2021-12-10",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"2019-12-06","2021-12-13"]
[1731,870024,"Enhancement on Management Aspects of 5G Service-Level Agreement ","EMA5SLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-210860",null,"SHI, Xiaonan, CMCC ","shixiaonan@chinamobile.com ","; 13/9/20: 0%->5; 5/12/20: 5%->40; 21/3/21: 40%->60; 21/3/21: FCD:18/03/2021->06/21; 11/6/21: 60%->65; 11/6/21: FCD:Fri 11/06/->12/21; 10/9/21: WID:SP-200190->SP-210860; 13/9/21: 65%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85 ","28.541; 28.531 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1732,870025,"Management of MDT enhancement in 5G ","e_5GMDT",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200191",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75; 13/9/21: 75%->85; 13/12/21: 85%->95; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 95%->100","32.421; 32.422; 32.423; 28.622; 28.623; 28.523 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1733,870026,"Additional NRM features ","adNRM",1,"Rel-17","S5","2020-02-05","2022-03-11",1,"SP-200192",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com","; 10/6/20: FCD:19/03/2020->06/20; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->30; 13/9/21: 30%->50; 13/9/21: FCD:Tue 15/06/->12/21; 13/12/21: 50%->80; 13/12/21: FCD:Fri 10/12/->03/22; 01/22: rapporteur change from Jing Ping; 12/3/22: 80%->100","28.540; 28.541; 28.622; 28.623 ",87,44,null,null,"2019-12-06","2022-03-12"]
[{"$f":"A1734+1","v":1734},870030,"Enhanced Closed loop SLS Assurance ","eCOSLA",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200196",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 50%->60; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->90; 4/6/22: 90%->100; 4/1/24: 28.867...","28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 ; 28.867",87,44,null,null,"2019-12-06","2024-01-04"]
[1735,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","2022-03-10","2022-06-10",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1736,0,"Rel-17 Other NR-only improvements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1737,860061,"Study on NR QoE (Quality of Experience) management and optimizations for diverse services","FS_NR_QoE",1,"Rel-17","R3","2019-12-16","2020-09-15",1,"RP-193256",null,"China Unicom",null,"affects: NR.; 25/9/20: 38.890 added;; 7/4/21: 0%->100",38.89,86,44,null,null,"2020-01-14","2021-04-07"]
[1738,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"2021-01-01","2024-09-09",0.5,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"2021-06-04","2021-07-02"]
[1739,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","2021-01-01","2022-03-22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1740,970072,"   UE Conformance - NR QoE management and optimizations for diverse services ","NR_QoE-UEConTest",2,"Rel-17","R5","2022-09-08","2024-09-09",0.2,"RP-222102","RP-240946","Bo J NSSON, Ericsson","Bo[dot]jonsson[at]ericsson[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->5%; Stat Rep: ->RP-222818; Rapporteur: Ericsson->Bo J NSSON, Ericsson; Rap eMail: ->Bo[dot]jonsson[at]ericsson[dot]com; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-222818->RP-230267; ;...; 6/9/23: C...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1741,911009,"Rel-17 Power Class 2 UE for NR inter-band CA with or without SUL configurations with x (16>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL",1,"Rel-17",null,"2021-03-12","2025-06-06",0.6,"RP-221516",null,"Huawei ",null,"basket WI; TR 38.8xx ; 2/7/21: WID:RP-210543->RP-211378; 29/9/21: WID:RP-211378->RP-212182; 6/1/22: WID:RP-212182->RP-213650; 5/4/22: WID:RP-213650->RP-220701; 12/7/22: WID:RP-220701->RP-221516",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1742,911109,"   Core part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","basket WI; TR 38.8xx ; 2/7/21: 38.842 added;; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->78% ; 20/6/22: Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.com; ","38.842; 38.541",91,46,null,null,"2021-04-07","2022-06-20"]
[1743,911209,"   Stopped - Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: Stat Rep: RP-212181->RP-220699 ; 6/6/22: CD:12/06/2022->22/06/2022 ; 20/6/22:Stopped at 0%; Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.c...",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1744,1000056,"   UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-UEConTest",2,"Rel-17","R5","2023-06-08","2025-06-06",0.09,"RP-231247","RP-241369","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->9%; Stat Rep: ->RP-232358; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232358->RP-233766; ; 14/3/24: ...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1745,911010,"Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS",1,"Rel-17",null,"2021-03-12","2023-12-12",1,"RP-212030",null,"Vivo ",null,"compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: WID:RP-210807->RP-211158; 29/9/21: WID:RP-211158->RP-212030; 1/10/21: 38.161 added;; ",38.161000000000001,91,46,null,null,"2021-04-07","2022-06-04"]
[1746,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","2021-03-12","2022-03-22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ",38.834000000000003,91,46,null,null,"2021-04-07","2022-06-20"]
[1747,911210,"   Perf. part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-222269","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy ; 22/3/22: Compl:0%->20%; 22/3/22: CD:08/09/2022->12/09/2022 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com s...;...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[1748,960088,"   UE Conformance - Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221690","RP-233311","Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo","ashwin_mohan[at]apple.com, Jose.Fortes[at]rohde-schwarz.com,ruixin.wang[at]vivo.com","9/9/22: Comp...; 23/9/22: 38.561 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->9%; Stat Rep: ->RP-223197; Rapporteur: Apple->Ashwin Mohan, Jose Fortes, Ruixin Wang, Apple, Rohde and Schwarz, Vivo; Rap eMail: ->ashwin_mohan[at]apple...",38.561,96,49,null,null,"2022-07-12","2023-12-08"]
[1749,911012,"High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79",1,"Rel-17",null,"2021-03-12","2022-12-01",1,"RP-210843",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1750,911112,"   Core part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1751,911212,"   Perf. part: NR_UE_PC1_5_n79","NR_UE_PC1_5_n79-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210843",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1752,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-211979","RP-223061","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...; 9/12/22: FCD:23/03/2023->01/12/2022; Compl:84%->100%; Stat R...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1753,911013,"High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-210844",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1754,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1755,911213,"   Perf. part: NR_UE_PC2_n34","NR_UE_PC2_n34-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1756,930053,"   UE Conformance - High power UE (power class 2) for NR band n34 ","NR_UE_PC2_n34-UEConTest",2,"Rel-17","R5","2021-09-17","2022-06-22",1,"RP-221760","RP-221357","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n34-Core ; 6/1/22: WID:RP-211980->RP-213034; 22/3/22: Compl:0%->53% ; 20/6/22: FCD:12/09/2022->22/06/2022; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com12/7/22: WID:RP-211980->RP-221760",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1757,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"2021-03-12","2023-09-22",1,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"2021-04-07","NA"]
[1758,911114,"   Core part: NR_UE_PC2_n39","NR_UE_PC2_n39-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1759,911214,"   Perf. part: NR_UE_PC2_n39","NR_UE_PC2_n39-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1760,930054,"   UE Conformance - High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39-UEConTest",2,"Rel-17","R5","2021-09-17","2023-09-22",1,"RP-211981","RP-232243","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC2_n39-Core ; 6/1/22: WID:RP-211981->RP-213035; 22/3/22: Compl:0%->47% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ...; 23/9/22: WID:RP-211981->RP-222651; 9/12/22: FCD:23/03/2023->01/0...",null,93,47,null,null,"2021-09-29","2023-09-06"]
[1761,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"2021-04-07","NA"]
[1762,911115,"   Core part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1763,911215,"   Perf. part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 6/1/22: 0%->100",null,91,46,null,null,"2021-04-07","2022-01-06"]
[1764,911006,"NR Uplink Data Compression (UDC) ","NR_UDC",1,"Rel-17",null,"2021-03-12","2023-06-06",1,"RP-220140",null,"CATT ",null,"no Perf. part; compare RAN2 REL-15 WI LTE_UDC-Core ; 2/7/21: WID:RP-210909->RP-211203; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1765,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","2021-03-12","2022-03-11",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2022-04-05"]
[1766,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221449","RP-230395","Huiying ZHANG, CATT","zhanghuiying@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%->33%; Stat Rep: ->RP-223139; Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn; 17/3/23: Compl:33%->67%; Stat Rep: RP-223139->RP-230395; ;...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1767,910097,"Study on optimizations of pi/2 BPSK uplink power in NR ","FS_NR_Opt_pi2BPSK",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-213535","RP-220136","Huawei ",null,"; 1/10/21: 38.868 added;; 6/1/22: WID:RP-210910->RP-213535 ; ",38.868000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1768,910096,"Study on band combination handling in RAN4 ","FS_NR_ENDC_combo_rules",1,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP-211146","RP-220164","ZTE ",null,"TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC ; 2/7/21: WID:RP-210773->RP-211146; 2/7/21: 38.862 added;13/9/21: Compl:0%->50%13/9/21: CD:Sat 12/03/22->Tue 22/03/2213/9/21: Stat ",38.862000000000002,91,46,null,null,"2021-04-07","2022-03-22"]
[1769,880078,"Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs","NR_MIMO_OTA",1,"Rel-17",null,"2020-06-22","2023-12-12",1,"RP-213101",null,"CAICT",null,"25/9/20: WID:RP-201302->RP-201800; 6/1/22: WID:RP-201800->RP-213101",null,88,45,null,null,"2020-07-28","2022-01-06"]
[1770,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"2020-07-28","2022-06-20"]
[1771,880278,"   Perf. Part: NR_MIMO_OTA","NR_MIMO_OTA-Perf",2,"Rel-17","R4","2020-06-22","2022-09-22",1,"RP-222348","RP-222634","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","; 13/9/21: Compl:0%->20%; 13/9/21: CD:Wed 15 ; 22/3/22: Compl:20%->35%; ; 6/6/22: Compl:35%->55% 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com 9/...; 23/9/22: 90%->100;...",null,88,45,null,null,"2020-07-28","2022-09-23"]
[1772,970071,"   UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs ","NR_MIMO_OTA-UEConTest",2,"Rel-17","R5","2022-09-08","2023-12-12",1,"RP-221939","RP-233312","Istvan Szini, Apple","Istvan@apple.com","19/10/22: 38.551 added;; 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->5%; Stat Rep: ->RP-223198; Rapporteur: Apple->Istvan Szini, Apple; Rap eMail: ->Istvan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->8%; Stat Rep: RP-223198->RP-2301.....",38.551000000000002,97,49,null,null,"2022-09-23","2023-12-08"]
[1773,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"2020-03-25","2024-12-12",0.67,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"2020-03-26","2021-01-06"]
[1774,870164,"   Core part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1775,870264,"   Perf. Part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Perf",2,"Rel-17","R4","2020-03-25","2021-03-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1776,950062,"   UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 ","NR_FR2_FWA_Bn257_Bn258-UEConTest",2,"Rel-17","R5","2022-03-15","2024-12-12",0.49,"RP-220424","RP-241370","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_FR2_FWA_Bn257_Bn258-Core 6/6/22: Compl:0%->5% 6/6/22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221492->RP-223221.....",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1777,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1778,880192,"   Core part: NR_bands_R17_BWs","NR_bands_R17_BWs-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221212","RP-221213","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","; 13/9/21: Compl:0%->50%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:50%->80%; 20/6/22: Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1779,880093,"Introduction of channel bandwidths 35MHz and 45MHz for NR FR1","NR_FR1_35MHz_45MHz_BW",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722; 2/7/21: WID:RP-210722->RP-211386",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1780,880193,"   Core part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1781,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1782,880097,"SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL","NR_SAR_PC2_interB_SUL_2BUL",1,"Rel-17",null,"2020-03-19","2022-09-22",1,"RP-212530",null,"China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 2/7/21: WID:RP-201584->RP-211494; 29/9/21: WID:RP-211494->RP-212530",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1783,880197,"   Core part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Core",2,"Rel-17","R4","2020-03-19","2021-09-21",1,"RP-212530","RP-211830","China Telecom",null,"25/9/20: WID:RP-201337->RP-201584; 13/9/21: Compl:0%->100%; 13/9/21: CD:Fri 19/03/21->Tue 21/09/21; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; ; 29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1784,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","2020-03-19","2022-03-21",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1785,920065,"   UE Conformance - SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL ","NR_SAR_PC2_interB_SUL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2022-09-22",1,"RP-211139","RP-221295","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_SAR_PC2_interB_SUL_2BUL-Core ; 13/9/21: Compl:0%->5%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 13/9/ ; 22/3/22: Compl:5%->23% ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinateleco...",null,92,47,null,null,"2021-07-02","2022-09-09"]
[1786,900061,"NR coverage enhancements ","NR_cov_enh",1,"Rel-17",null,"2019-03-07","2024-03-01",1,"RP-211566",null,"China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 7/4/21: WID:RP-202928->RP-210855; 2/7/21: WID:RP-210855->RP-211566",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1787,860036,"   Study on on NR coverage enhancements","FS_NR_cov_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-200861",null,"China Telecom",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1788,900161,"   Core part: NR_cov_enh","NR_cov_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-11",1,"RP-211566","RP-220563","China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211826 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1789,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-12-21",1,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1790,950063,"   UE Conformance - NR coverage enhancements ","NR_cov_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2024-03-01",1,"RP-240341","RP-240340","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","tested: REL-17 WI NR_cov_enh-Core ; 6/6/22: Compl:0%->5% ; 6/6/22: CD:15/06/2023->23/ ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-220576->RP-221298 ; ;...; 9/12/22: FCD:23/06...",null,95,48,null,null,"2022-04-05","2024-04-02"]
[1791,900062,"Support of reduced capability NR devices ","NR_redcap",1,"Rel-17",null,"2019-12-16","2024-03-01",1,"RP-220966",null,"Ericsson ",null,"follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202933->RP-210918; 2/7/21: WID:RP-210918->RP-211574; 5/4/22: WID:RP-211574->RP-220966",null,90,46,null,null,"2021-01-06","2022-04-05"]
[1792,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1793,900162,"   Core part: NR_redcap","NR_redcap-Core",2,"Rel-17","R1","2020-12-14","2022-06-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 22/ 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1794,900262,"   Perf. part: NR_redcap","NR_redcap-Perf",2,"Rel-17","R1","2020-12-14","2022-12-22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap ; 22/3/22: Compl:0%->25%; 22/3/22: CD:08/09/2022- 6/6/22: Compl ; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com ...; 9/12/22: 75%->100; 9/1/23: 100%...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1795,950066,"   UE Conformance - Support of reduced capability NR devices ","NR_redcap_plus_ARCH-UEConTest",2,"Rel-17","R5","2022-03-15","2024-03-01",1,"RP-240053","RP-240050","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 WI NR_redcap-Core and CT1 REL-17 WI ARCH_NR_REDCAP 6/6/22: Compl:0%->13% ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ...; 23/9/22: WID:RP-222830->RP-222136; 9/12/22: FCD:23/06/2023->...",null,95,48,null,null,"2022-04-05","2024-04-02"]
[1796,930018,"   Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211100",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 10/12/21: 0%->100","23.501; 23.502 ",93,47,null,null,"2021-09-10","2021-12-10"]
[1797,940005,"   CT1 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","24.501; 23.122; 24.008; 24.368",94,48,null,null,"2022-01-07","2022-06-04"]
[{"$f":"A1798+1","v":1798},950047,"   CT3 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-221265",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: WID:CP-213081->CP-220304; 12/3/22: 0%->100; 4/6/22: WID:CP-220304->CP-221265","24.501; 23.122; 24.008; 24.368",95,48,null,null,"2022-03-12","2022-06-04"]
[1799,940100,"   CT4 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","29.571; 29.502; 29.540; 29.518; 23.008",94,48,null,null,"2022-01-07","2022-06-04"]
[1800,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"2022-01-07","2022-06-04"]
[1801,940027,"   Charging aspects of Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211428",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 12/3/22: 0%->35; 4/6/22: 35%->100","32.255; 32.298; 32.291 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1802,900064,"Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 ","NR_bands_UL_MIMO_PC3_R17",1,"Rel-17",null,"2020-12-14","2023-06-06",1,"RP-221518",null,"Huawei ",null,"basket WI ; 7/4/21: WID:RP-202819->RP-210557; 2/7/21: WID:RP-210557->RP-211380; 29/9/21: WID:RP-211380->RP-212184; 6/1/22: WID:RP-212184->RP-213137; 5/4/22: WID:RP-213137->RP-220704; 12/7/22: WID:RP-220704->RP-221518",null,90,46,null,null,"2021-01-06","2022-07-12"]
[1803,900164,"   Core part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Core",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: Compl:0%->70%; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1804,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1805,940090,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-17","NR_bands_UL_MIMO_PC3_R17-UEConTest",2,"Rel-17","R5","2021-12-13","2023-06-06",1,"RP-220745","RP-230431","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 WI NR_bands_UL_MIMO_PC3_R17; 22/3/22: Compl:0%->8%; 22/3/22: Stat Rep: ->RP-220419; 5/4/22: WID:RP-213227->RP-220745 ; 6/6/22: CD:12/09/2022->22 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyu...",null,94,48,null,null,"2022-01-06","2023-06-07"]
[1806,900167,"Introduction of bandwidth combination set 4 (BCS4) for NR ","NR_BCS4-Core",1,"Rel-17","R4","2019-03-07","2022-06-22",1,"RP-202832","RP-221317","Per Lindell, Ericsson","per.lindell@ericsson.com","no Perf. part ; 20/6/22: FCD:03/06/2020->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221317; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1807,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"2020-12-14","2024-03-01",1,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;",37.866999999999997,90,46,null,null,"2021-01-06","2021-07-02"]
[1808,900168,"   Core part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Core",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI; TR 37.8xx ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478 ; ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1809,900268,"   Perf. part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI ; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478; 13/9/21: Stat Rep: ->RP-211833 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[1810,981033,"   UE Conformance - Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17-UEConTest",2,"Rel-17","R5","2022-12-13","2024-03-01",1,"RP-240785","RP-240342","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","17/3/23: FCD:12/12/2023->06/06/2023; Compl:0%->5%; Stat Rep: ->RP-230318; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; 31/3/23: FCD:06/06/2023->12/12/2023; Stat Rep: RP-230318->RP-230715; ...; 6/9/23:...",null,98,50,null,null,"2023-01-09","2024-04-02"]
[1811,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"2020-12-14","2022-12-01",1,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"2021-01-06","NA"]
[1812,900169,"   Core part: HPUE_PC1_5_n77_n78","HPUE_PC1_5_n77_n78-Core",2,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-202912","RP-212049","Qualcomm ",null,"no Perf. part ; 13/9/21: Compl:0%->100% ; 29/9/21: 100%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[1813,930055,"   UE Conformance - High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-212581","RP-223280","Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia","jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com","tested: REL-17 WI HPUE_PC1_5_n77_n78-Core ; 22/3/22: Compl:0%->50%; ; 6/6/22: Compl:50%->61%20/6/22: Rapporteur: Verizon->Jinwen MA, Tuomo Saynajakangas, Verizon, Nokia; Rap eMail: ->jinwen.ma@verizonwireless.com, tuomo.saynajakangas@nokia.com; ...;...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[1814,900070,"NR repeaters ","NR_repeaters",1,"Rel-17",null,"2020-12-14","2022-12-21",1,"RP-213514",null,"Qualcomm ",null,"no Perf. part ; 7/4/21: WID:RP-202927->RP-210818; 29/9/21: WID:RP-210818->RP-212129; 6/1/22: WID:RP-212129->RP-213514",null,90,46,null,null,"2021-01-06","2022-01-06"]
[1815,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"2021-01-06","2022-06-20"]
[1816,930250,"   Perf. part: NR repeaters ","NR_repeaters-Perf",2,"Rel-17","R4","2021-09-17","2022-12-21",1,"RP-222275","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","Core part (UID=900170) started in Dec.20 while Perf. Part (UID=930250) started in 17/09/21 via revised WID RP-212129; TS 38.1??-1, TS 38.1??-2 ; 7/1/22: 38.115-2 and 38.115-1 added;; 20/6/22: FCD:17/09/2022->22/09/2022; Compl:0%->30%; WID: RP-213514->R...","38.115-2; 38.115-1",93,47,null,null,"2021-09-29","2023-01-09"]
[1817,930056,"Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC",1,"Rel-17","R4","2021-09-17","2023-09-22",0.99,"RP-221302",null,"Qualcomm ",null,"no Perf. part ; 12/7/22: WID:RP-212622->RP-221302",null,93,47,null,null,"2021-09-29","2022-07-12"]
[1818,930156,"   Core part: Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-Core",2,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302","RP-221588","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","no Perf. Part ; 22/3/22: Compl:0%->75%; … 20/6/22: WID: RP-212622->RP-221302; Stat Rep: RP-220514->RP-221588; Rapporteur: Qualcomm->Gene Fong, Qualcomm Incorporated; Rap eMail: ->gfong@qti.qualcomm.com; ",null,93,47,null,null,"2021-09-29","2022-06-20"]
[1819,981036,"   UE Conformance - Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-UEConTest",2,"Rel-17","R5","2022-12-13","2023-09-22",1,"RP-221302","RP-232018","Kevin Wang / Jingzhou wu, Qualcomm / China Telecom","kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->52%; Stat Rep: ->RP-230101; Rapporteur: Qualcomm->Kevin Wang / Jingzhou wu, Qualcomm / China Telecom; Rap eMail: ->kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn; ...; 6/9/23: FCD:09/09/2023->22/09/2...",null,98,50,null,null,"2023-01-09","2023-09-06"]
[1820,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"2021-09-29","2022-01-06"]
[1821,930157,"   Core part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ]; TR 36.8xx ; 7/1/22: 36.779 added ; ",36.779000000000003,93,47,null,null,"2021-09-29","2022-03-22"]
[1822,930257,"   Perf. part: Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212917","RP- 220404","Puloli ",null,"specs in [ ] ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1823,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-221417","RP-222802","Heng Pan, Puloli","heng.pan@puloli.com","9/9/22: Comp...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:72%->100%; Stat Rep: ->RP-222802; Rapporteur: Puloli->Heng Pan, Puloli; Rap eMail: ->heng.pan@puloli.com; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1824,930058,"High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD",1,"Rel-17","R4","2021-09-17","2022-12-01",0.99,"RP-212633",null,"China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ",null,93,47,null,null,"2021-09-29","NA"]
[1825,930158,"   Core part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Core",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1826,930258,"   Perf. part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[1827,960070,"   UE Conformance - High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-222809","RP-222808","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2022; Compl:67%->100%; WID: RP-221158->RP-222809; Stat Rep: ->RP-222808; Rapporteur: ChinaUnicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[1828,0,"Rel-17 NR Carrier Aggregation","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1829,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1830,881005,"NR itrabCA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R17_Intra",1,"Rel-17",null,"2016-06-09","2022-06-22",1,"RP-221319",null,"Ericsson",null,"25/9/20: WID:RP-200663->RP-201571; 6/1/21: WID:RP-201571->RP-202187; 7/4/21: WID:RP-202187->RP-210210; 2/7/21: WID:RP-210210->RP-211585; 29/9/21: WID:RP-211585->RP-211757; 6/1/22: WID:RP-211757->RP-212900; 5/4/22: WID:RP-212900->RP-220825; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1831,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1832,881205,"   Perf. Part: NR_CA_R17_Intra","NR_CA_R17_Intra-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1833,0,"   Rel-17 NR inter band Carrier Aggregation (iterbCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1834,900063,"High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1","NR_intra_HPUE_R17",1,"Rel-17",null,"2021-02-10","2022-06-22",1,"RP-221774",null,"Huawei",null,"7/4/21: WID:RP-202818->RP-210555; 29/9/21: WID:RP-210555->RP-212180; 6/1/22: WID:RP-212180->RP-213133; 5/4/22: WID:RP-213133->RP-220930; 12/7/22: WID:RP-220930->RP-221774",null,90,46,null,null,"2021-02-10","2022-07-12"]
[1835,900163,"   Core part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Core",2,"Rel-17","R4","2021-02-10","2022-06-22",1,"RP-221774","RP-221513 / 1773","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->10%; 22/3/22: CD:22/03/2022->10/06/2022 ; 20/6/22: Stat Rep: RP-221513->RP-221513 / 1773; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; ",null,90,46,null,null,"2021-02-10","2022-06-20"]
[1836,900263,"   Stopped - Perf. Part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Perf",2,"Rel-17","R4","2021-02-10","2022-06-10",1,"RP-221774","RP-220696","Huawei",null,"; 13/9/21: CD:Thu 09/12/21->Wed 22/06/22; ; 22/3/22: CD:22/06/2022->12/06/2022; 22/3/22: WID: RP-213133->RP-213132; 22/3/22: Stat Rep: RP-212179->RP-220696. 12/7/22: stopped at 0%. 0%->100",null,90,46,96,null,"2021-02-10","2022-07-12"]
[1837,881006,"NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2)","NR_CADC_R17_2BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221250",null,"ZTE",null,"25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495; 2/7/21: WID:RP-210495->RP-211058; 29/9/21: WID:RP-211058->RP-212511; 6/1/22: WID:RP-212511->RP-212887; 5/4/22: WID:RP-212887->RP-220144; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1838,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1839,881206,"   Perf. part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1840,881007,"NR iterbCA for 3 bands DL with 1 band UL","NR_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221772",null,"CATT",null,"25/9/20: WID:RP-200922->RP-201787; 6/1/21: WID:RP-201787->RP-202720; 7/4/21: WID:RP-202720->RP-210901; 2/7/21: WID:RP-210901->RP-211215; 29/9/21: WID:RP-211215->RP-212239; 6/1/22: WID:RP-212239->RP-213299; 5/4/22: WID:RP-213299->RP-220738; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1841,881107,"   Core part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1842,881207,"   Perf. part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: CD:15/09/2021->12/06/2022; 22/3/22: Stat Rep: ->RP-220737 ; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1843,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1844,881108,"   Core part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1845,881208,"   Perf. part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1846,881009,"NR iterbCA for 4 bands DL with 1 band UL","NR_CA_R17_4BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221321",null,"Ericsson",null,"25/9/20: WID:RP-200665->RP-201573; 6/1/21: WID:RP-201573->RP-202189; 7/4/21: WID:RP-202189->RP-210760; 2/7/21: WID:RP-210760->RP-211171; 29/9/21: WID:RP-211171->RP-211759; 6/1/22: WID:RP-211759->RP-212902; 5/4/22: WID:RP-212902->RP-220827; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1847,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1848,881209,"   Perf. part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1849,881010,"NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands","NR_CADC_R17_4BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221396",null,"Samsung",null,"25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802; 2/7/21: WID:RP-210802->RP-211194; 29/9/21: WID:RP-211194->RP-212110; 6/1/22: WID:RP-212110->RP-213111; 5/4/22: WID:RP-213111->RP-220676; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1850,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1851,881210,"   Perf. part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","; 13/9/21: Compl:0%->70%; ; 22/3/22: Compl:70%->90%; 20/6/22: Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1852,881011,"NR iterbCA for 5 bands DL with x bands UL (x=1, 2)","NR_CADC_R17_5BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221510",null,"Huawei",null,"25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561; 2/7/21: WID:RP-210561->RP-211373; 29/9/21: WID:RP-211373->RP-212176; 6/1/22: WID:RP-212176->RP-213129; 5/4/22: WID:RP-213129->RP-220692; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1853,881111,"   Core part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3/22: 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1854,881211,"   Perf. part: NR_CADC_R17_5BDL_xBUL","NR_CADC_R17_5BDL_xBUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221510","RP-221509","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->15%; ; 22/3/22: Compl:15%->40%; 22/3 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1855,890054,"Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2)","NR_PC2_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-09-17","2023-12-12",1,"RP-221866",null,"China Telecom ",null,"basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 6/1/21: WID:RP-202102->RP-202373; 7/4/21: WID:RP-202373->RP-210476; 2/7/21: WID:RP-210476->RP-211131; 2/7/21: 38.841 added;; 29/9/21: WID:RP-211131->RP-211831; 6/1/22: WID:RP...",38.841000000000001,89,45,null,null,"2020-09-25","2022-07-12"]
[1856,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1857,890254,"   Perf. part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI ; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211131->RP-202102 RP-202373 RP-210476 RP-211131; 13/9/21: Stat Rep: ->RP-211832; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: WID: RP-213649->RP‑213649; 22/3/22: Stat Rep: RP-211832-...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1858,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","2021-06-15","2023-12-12",1,"RP-233581","RP-233580","Jingzhou Wu, Dan Song, China Telecom, China Mobile","wujingzhou@chinatelecom.cn, songdan@chinamobile.com","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...;...",null,92,47,null,null,"2021-07-02","2024-01-02"]
[1859,0,"Rel-17 NR and LTE","-",1,"Rel-17",null,"2020-03-25","2020-09-15",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1860,920072,"LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39",1,"Rel-17","R4","2019-03-07","2019-03-07",1,null,"RP-211995","CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 13/9/21: Compl:0%->100% ; ",null,92,47,null,null,"2021-07-02","2021-09-13"]
[1861,920172,"   Core part: LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core",2,"Rel-17","R4","2021-06-15","2021-12-15",1,"RP-211996",null,"CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 29/9/21: WID:RP-211509->RP-211996",null,92,47,null,null,"2021-07-02","2021-09-29"]
[{"$f":"A1862+1","v":1862},940089,"   UE Conformance - LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest",2,"Rel-17","R5","2021-12-13","2022-03-11",1,"RP-213036","RP-220625","CMCC",null,"tested: REL-17 WI DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1863,920073,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795",null,"Nokia ",null,"this is not a basket WI ; 29/9/21: WID:RP-211571->RP-212533; 6/1/22: WID:RP-212533->RP-213106; 5/4/22: WID:RP-213106->RP-220767; 12/7/22: WID:RP-220767->RP-221795",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1864,920173,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; …; 7/1/22: 37.828 and 37.828 added;; 22/3/22: Compl:0%->50% ; 20/6/22: Compl:50%->100%; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail...","37.828; 37.828",92,47,null,null,"2021-07-02","2022-06-20"]
[1865,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","2021-09-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1866,920074,"Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524",null,"Huawei ",null,"basket WI; TR 37.717-11-41 ; 29/9/21: WID:RP-211592->RP-212606; 6/1/22: WID:RP-212606->RP-213142; 5/4/22: WID:RP-213142->RP-220712; 12/7/22: WID:RP-220712->RP-221524",null,92,47,null,null,"2021-07-02","2022-07-12"]
[1867,920174,"   Core part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI; TR 37.717-11-41 ; 20/6/22: FCD:15/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221523; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1868,920274,"   Perf. part: Rel-17 Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL1UL) and 4 bands NR inter-band CA (4DL1UL) ","DC_R17_xBLTE_4BNR_yDL2UL-Perf",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221524","RP-221523","Zhang, Peng, Huawei","zhangpeng169@huawei.com","basket WI ; 22/3/22: Compl:0%->15%; 22/3/22: CD:15/03/2022->10/06/2022; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1869,911019,"Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths","ENDC_R17_1BLTE_1BNR_MSD",1,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part; 2/7/21: WID:RP-210891->RP-211384; 29/9/21: WID:RP-211384->RP-212187; 6/1/22: WID:RP-212187->RP-213140; 5/4/22: WID:RP-213140->RP-220709",null,91,46,null,null,"2021-04-09","2022-04-05"]
[1870,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"2021-04-09","2022-06-20"]
[1871,930259,"   Stopped - Perf. Part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Perf",2,"Rel-17",null,"2021-03-25","2022-03-25",1,"RP-220709",null,"Huawei, HiSilicon ",null,"4/6/22: Stopped at 70%. This Perf. part is not needed",null,93,47,96,null,"2022-03-13","2022-06-04"]
[1872,911011,"Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR",1,"Rel-17",null,"2021-03-12","2024-09-09",0.49,"RP-221322",null,"Ericsson ",null,"basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: WID:RP-210816->RP-211172; 29/9/21: WID:RP-211172->RP-211760; 6/1/22: WID:RP-211760->RP-213467; 5/4/22: WID:RP-213467->RP-220828; 12/7/22: WID:RP-220...",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1873,911111,"   Core part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: 37.827 added; ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; List of Impacted TS & TR updated; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1874,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1875,930051,"   UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR-UEConTest",2,"Rel-17","R5","2021-09-17","2024-09-09",0.06,"RP-240074","RP-240945","Kuba KOLODZIEJ, Ericsson","Kuba[dot]kolodziej[at]ericsson[dot]com","tested: REL-17 WI ENDC_PC2_R17_xLTE_yNR ; 22/3/22: Compl:0%->5%; 22/3/22: CD:15/12/2022->12/12/2022; 22/3/22 6/6/22: CD:12/12/2022->22/12/2022 ; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Ericsson; Rap eMail: ->Leif[dot]mattisson[at]ericsson[d...",null,93,47,null,null,"2021-09-29","2024-06-13"]
[1876,911018,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC ","LTE_NR_Simult_RxTx",1,"Rel-17",null,"2021-03-12","2022-06-22",1,"RP-221521",null,"Huawei ",null,"; 2/7/21: WID:RP-210890->RP-211382; 5/4/22: WID:RP-211382->RP-220707; 12/7/22: WID:RP-220707->RP-221521",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1877,911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",38.838999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1878,911218,"   Stopped - Perf. part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 6/6/22: Compl:70%->0%6/6/22: CD:22/03/2022->22/06/20226/6/22: WID: RP-220707->RP-2113826/6/22: Stat Rep: RP-212185->RP-221520; 20/6/22: Compl:0%->100%; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; Sto",null,91,46,96,null,"2021-04-07","2022-06-20"]
[1879,890052,"Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) ","DC_R17_5BLTE_1BNR_6DL2UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220672",null,"Samsung ",null,"basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801; 2/7/21: WID:RP-210801->RP-211195; 6/1/22: WID:RP-211195->RP-213112; 5/4/22: WID:RP-213112->RP-220672",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1880,890152,"   Core part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI; TR 37.717-51-11 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1881,890252,"   Perf. part: DC_R17_5BLTE_1BNR_6DL2UL","DC_R17_5BLTE_1BNR_6DL2UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220672","RP-220673","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1882,890053,"Rel-17 Dual Connectivity (DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) ","DC_R17_xBLTE_2BNR_yDL3UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220674",null,"Samsung ",null,"basket WI; TR 37.717-21-22 ; 6/1/21: WID:RP-201643->RP-202542; 5/4/22: WID:RP-202542->RP-220674",null,89,45,null,null,"2020-09-25","2022-04-05"]
[1883,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1884,890253,"   Perf. part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI ; 13/9/21: Compl:0%->70%; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1885,880080,"Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band","NR_LTE_V2X_PC5_combos",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-213297",null,"CATT",null,"25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588; 6/1/22: WID:RP-210588->RP-213297",37.875,88,45,null,null,"2020-07-28","2022-01-06"]
[1886,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1887,880280,"   Perf. part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->9 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[1888,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"2020-06-22","2023-06-06",1,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1889,880194,"   Core part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3/2 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1890,880294,"   Perf. part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1891,911000,"   UE Conformance - ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-UEConTest",2,"Rel-17","R5","2021-03-12","2023-06-06",1,"RP-211420","RP-230698","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 basket WI ENDC_UE_PC2_R17_NR_TDD-Core ; 2/7/21: WID:RP-210401->RP-211420; 2/7/21: 0%->10 ; ; 6/6/22: Com ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ; ;...; 9/12/22: FCD:23/03/2023->01...",null,91,46,null,null,"2021-04-07","2023-06-07"]
[1892,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1893,880195,"   Core part: DSS_LTE_B38_NR_Bn38","DSS_LTE_B38_NR_Bn38-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1894,880096,"LTE/NR spectrum sharing in Band 40/n40","DSS_LTE_B40_NR_Bn40",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: WID:RP-201362->RP-202084",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1895,880196,"   Core part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Core",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1896,880296,"   Perf. part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Perf",2,"Rel-17","R4","2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: 0%->100",null,88,45,null,null,"2020-07-28","2020-09-25"]
[1897,880098,"Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_1BLTE_1BNR_2DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221257",null,"CHTTL",null,"25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204; 2/7/21: WID:RP-210204->RP-211162; 29/9/21: WID:RP-211162->RP-212096; 6/1/22: WID:RP-212096->RP-213060; 5/4/22: WID:RP-213060->RP-220398; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1898,880198,"   Core part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: Compl:0%->75%; ; 22/3/22: Compl:75%->90%; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1899,880298,"   Perf. part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:0%->90%; ; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1900,880099,"Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_2BLTE_1BNR_3DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221508",null,"Huawei",null,"25/9/20: WID:RP-201369->RP-202060; 6/1/21: WID:RP-202060->RP-202613; 7/4/21: WID:RP-202613->RP-210559; 2/7/21: WID:RP-210559->RP-211371; 29/9/21: WID:RP-211371->RP-212174; 6/1/22: WID:RP-212174->RP-213127; 5/4/22: WID:RP-213127->RP-220689; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1901,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1902,890263,"   Perf. part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-17","R4","2020-09-16","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221507; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1903,881000,"Dual Connectivity (DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_3BLTE_1BNR_4DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221320",null,"Ericsson",null,"25/9/20: WID:RP-201370->RP-201572; 6/1/21: WID:RP-201572->RP-202188; 7/4/21: WID:RP-202188->RP-210211; 2/7/21: WID:RP-210211->RP-211170; 29/9/21: WID:RP-211170->RP-211758; 6/1/22: WID:RP-211758->RP-212901; 5/4/22: WID:RP-212901->RP-220826; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1904,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1905,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1906,881001,"Dual Connectivity (DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_4BLTE_1BNR_5DL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221073",null,"Nokia",null,"25/9/20: WID:RP-201371->RP-201483; 6/1/21: WID:RP-201483->RP-202590; 7/4/21: WID:RP-202590->RP-210766; 2/7/21: WID:RP-210766->RP-211319; 29/9/21: WID:RP-211319->RP-212532; 6/1/22: WID:RP-212532->RP-213251; 5/4/22: WID:RP-213251->RP-220999; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1907,881101,"   Core part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1908,881201,"   Perf. part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1909,881002,"Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R17_xBLTE_2BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221182",null,"LG Electronics",null,"25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202; 2/7/21: WID:RP-210202->RP-211043; 29/9/21: WID:RP-211043->RP-211750; 6/1/22: WID:RP-211750->RP-212876; 5/4/22: WID:RP-212876->RP-220302; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1910,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1911,881202,"   Perf. part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1912,881003,"Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL)","DC_R17_xBLTE_yBNR_3DL3UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221232",null,"ZTE",null,"25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344; 2/7/21: WID:RP-210344->RP-211054; 29/9/21: WID:RP-211054->RP-211803; 6/1/22: WID:RP-211803->RP-212883; 5/4/22: WID:RP-212883->RP-220202; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1913,881103,"   Core part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1914,881203,"   Perf. part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1915,881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1916,881104,"   Core part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1917,881204,"   Perf. part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1918,881012,"band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R17",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221512",null,"Huawei",null,"25/9/20: WID:RP-201026->RP-201726; 6/1/21: WID:RP-201726->RP-202611; 7/4/21: WID:RP-202611->RP-210563; 2/7/21: WID:RP-210563->RP-211375; 29/9/21: WID:RP-211375->RP-212178; 6/1/22: WID:RP-212178->RP-213131; 5/4/22: WID:RP-213131->RP-220695; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1919,881112,"   Core part: NR_SUL_combos_R17","NR_SUL_combos_R17-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1920,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1921,900056,"UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2024-12-12",0.11,"RP-231237","RP-241368","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","tested: REL-17 basket WIs: NR_CA_R17_Intra, NR_CADC_R17_2BDL_xBUL, NR_CA_R17_3BDL_1BUL, NR_CADC_R17_3BDL_2BUL, NR_CA_R17_4BDL_1BUL, NR_CADC_R17_4BDL_2BUL, NR_CADC_R17_5BDL_xBUL, NR_SUL_combos_R17, DC_R17_1BLTE_1BNR_2DL2UL, DC_R17_2BLTE_1BNR_3DL2UL, DC_...",null,90,46,null,null,"2021-01-06","2024-06-13"]
[1922,0,"Rel-17 NR new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1923,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1924,911116,"   Core part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Core",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP‑211495","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 1/10/21: 38.853 added;; 22/3/22: Compl:0 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->95%; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wen...",38.853000000000002,91,46,null,null,"2021-04-07","2022-09-09"]
[1925,911216,"   Perf. part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Perf",2,"Rel-17","R4","2021-03-12","2022-06-22",1,"RP-221768","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","; 22/3/22: Compl:0%->90% ; 20/6/22: FCD:22/03/2023->22/06/2022; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wendler, UIC; Rap eMail: ->ingo dot wendler at sbb dot ch; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[{"$f":"A1926+1","v":1926},911017,"Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_1900MHz_TDD",1,"Rel-17",null,"2021-03-12","2022-03-11",1,"RP-211542",null,"Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 2/7/21: WID:RP-210879->RP-211542",null,91,46,null,null,"2021-04-07","2021-07-02"]
[1927,911117,"   Core part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Core",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 1/10/21: 38.852 added ; ",38.851999999999997,91,46,null,null,"2021-04-07","2022-03-22"]
[1928,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[1929,860041,"Extending current NR operation to 71GHz","NR_ext_to_71GHz",1,"Rel-17","R1","2019-12-16","2023-03-03",0.99,"RP-222656",null,"Qualcomm",null,"affects: NR.; 25/9/20: WID:RP-193229->RP-201845; 6/1/21: WID:RP-201845->RP-202925; 7/4/21: WID:RP-202925->RP-210862; 2/7/21: WID:RP-210862->RP-211584; 29/9/21: WID:RP-211584->RP-212637; 6/1/22: WID:RP-212637->RP-213540; 23/9/22: WID:RP-213540->RP-222656",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1930,860141,"   Core part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Core",2,"Rel-17","R1","2019-12-16","2022-09-22",1,"RP-222656","RP-222655","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: Compl:0%->45%; ; 22/3/22: Compl:45%->90%; 20/6/22: Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm; Intel Corporation; Rap eMail: ->jingsun@qti.qualcomm.com; ...;...",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1931,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","2019-12-16","2023-03-03",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1932,860037,"Study on supporting NR from 52.6 GHz to 71 GHz","FS_NR_52_to_71GHz",1,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-201838",null,"Intel",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193259->RP-200902; 25/9/20: WID:RP-200902->RP-201838; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1933,870060,"Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz","FS_NR_IMT_param",1,"Rel-17","R4","2020-03-25","2020-12-15",1,"RP-202276",null,"Ericsson",null,"affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[1934,870063,"Introduction of NR band n13","NR_n13",1,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx",null,87,44,null,null,"2020-03-26","NA"]
[1935,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1936,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[1937,880082,"Introduction of NR 47GHz band","NR_47GHz_band",1,"Rel-17","R4","2019-03-07","2019-03-07",1,"RP-212528","RP-211772","Ericsson",null,"7/4/21: WID:RP-201232->RP-210827; 2/7/21: WID:RP-210827->RP-211568; 13/9/21: C ",null,88,45,null,null,"2020-07-28","2021-09-13"]
[1938,880182,"   Core part: Introduction of NR 47GHz band","NR_47GHz_band-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"2/7/21: 0%->100; 29/9/21: WID:RP-211568->RP-212528",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1939,880282,"   Perf. part: Introduction of NR 47GHz band","NR_47GHz_band-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-212528",null,"Ericsson",null,"29/9/21: 100%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[1940,880084,"Introduction of NR band 24","NR_band_n24",1,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: WID:RP-201357->RP-211505",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1941,880184,"   Core part: Introduction of NR band 24","NR_band_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1942,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1943,890050,"Introduction of 6GHz NR licensed bands ","NR_6GHz",1,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504",null,"Huawei ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844; 6/1/22: WID:RP-202844->RP-213696; 5/4/22: WID:RP-213696->RP-220686; 12/7/22: WID:RP-220686->RP-221504",null,89,45,null,null,"2020-09-25","2022-07-12"]
[1944,890150,"   Core part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Core",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 22/3/22: Compl:0%->35% ; 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->l...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[1945,890250,"   Perf. part: Introduction of 6GHz NR licensed bands ","NR_6GHz-Perf",2,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504","RP-221503","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","missing target dates to be updated ; 13/9/21: CD:Fri 17/06/22->Wed 22/06/22 ; 22/3/22: Compl:0%->20%; 2 20/6/22: Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->...",null,89,45,null,null,"2020-09-25","2022-09-09"]
[1946,920075,"Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full",1,"Rel-17","R4","2021-06-15","2022-06-15",0.43,"RP-213683",null,"Apple ",null,"in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 29/9/21: WID:RP-211602->RP-212302; 6/1/22: WID:RP-212302->RP-213683",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1947,920175,"   Core part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Core",2,"Rel-17","R4","2021-06-15","2022-03-22",1,"RP-212683","RP-220450","Alexander Sayenko","asayenko@apple.com","in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 20/6/22: FCD:15/03/2022->22/03/2022; Compl:0%->100%; WID: RP-213683->RP-212683; Stat Rep: ->RP-220450; Rapporteur: Apple->Al...",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1948,920275,"   Perf. part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Perf",2,"Rel-17","R4","2021-06-16","2022-06-15",0,"RP-213683",null,"Apple ",null,null,null,92,47,null,null,"2021-07-02","NA"]
[1949,890051,"Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU",1,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604",null,"Nokia ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762; 29/9/21: WID:RP-210762->RP-212625; 6/1/22: WID:RP-212625->RP-213604",null,89,45,null,null,"2020-09-25","2022-01-06"]
[1950,890151,"   Core part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 10/2/21: 38.849 added;; 13/9/21: Compl:0%->30%; 13/9/21: CD:Tue 15/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",38.848999999999997,89,45,null,null,"2020-09-25","2022-03-22"]
[1951,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1952,900065,"Introduction of NR band n67 ","NR_n67",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,null,null,90,46,null,null,"2021-01-06","NA"]
[1953,900165,"   Core part: Introduction of NR band n67 ","NR_n67-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1954,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1955,900066,"Introduction of NR band n85 ","NR_n85",1,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 7/4/21: WID:RP-202830->RP-210707",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1956,900166,"   Core part: Introduction of NR band n85 ","NR_n85-Core",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1957,900266,"   Perf. part: Introduction of NR band n85 ","NR_n85-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[1958,880083,"Introduction of 1.6 GHz NR supplemental uplink (SUL) band with same uplink frequency range of Band 24","NR_SUL_UL_n24",1,"Rel-17",null,"2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: WID:RP-201251->RP-210341",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1959,880183,"   Core part: NR_SUL_UL_n24","NR_SUL_UL_n24-Core",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1960,880283,"   Perf. part: NR_SUL_UL_n24","NR_SUL_UL_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1961,880085,"Introduction of NR supplemental uplink (SUL) band 1880-1920MHz","NR_SUL_band_1880_1920MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1962,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1963,880285,"   Perf. part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1964,880086,"Introduction of NR supplemental uplink (SUL) band 2300-2400MHz","NR_SUL_band_2300_2400MHz",1,"Rel-17",null,"2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,null,null,88,45,null,null,"2020-07-28","NA"]
[1965,880186,"   Core part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1966,880286,"   Perf. part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[1967,900055,"UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R17-UEConTest",1,"Rel-17","R5","2020-12-14","2022-12-01",1,"RP-223434","RP-223215","Yuxin Hao, Huawei Technologies. Co., Ltd","haoyuxin@huawei.com","tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co.,...;...",null,90,46,null,null,"2021-01-06","2023-01-09"]
[1968,0,"Rel-17 LTE new/modified bands","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1969,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",1,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"2021-04-08","2021-07-02"]
[1970,911120,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1-Core",2,"Rel-17","R1,R2,R3","2021-01-01","2022-03-22",1,"RP-211144","RP-220172","EBU",null,"WID will be split into RAN1/2/3 REL-17 WID (part1; target March 22) and a RAN4 REL18 WID (part2; REL-indep. From REL-17; target March 23) at RAN #92e; no Perf. Part; 13/9/21: C ; ; 14/5/24: 97%->100",null,91,46,null,null,"2021-04-08","2024-05-14"]
[1971,880079,"Additional LTE bands for UE categories M1/M2/NB1/NB2","LTE_bands_R17_M1_M2_NB1_NB2",1,"Rel-17",null,"2020-06-08","2022-06-22",1,"RP-220816",null,"Ericsson",null,"25/9/20: WID:RP-200804->RP-201646; 29/9/21: WID:RP-201646->RP-211857; 6/1/22: WID:RP-211857->RP-212906; 5/4/22: WID:RP-212906->RP-220816",null,88,45,null,null,"2020-07-28","2022-04-05"]
[1972,880179,"   Core part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Core",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1973,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1974,880081,"Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits","LTE_B24_mod",1,"Rel-17",null,"2020-06-15","2021-12-15",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: WID:RP-201356->RP-211507",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1975,880181,"   Core part: LTE_B24_mod","LTE_B24_mod-Core",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-07-02"]
[1976,880281,"   Perf. part: LTE_B24_mod","LTE_B24_mod-Perf",2,"Rel-17","R4","2020-06-15","2021-03-19",1,"RP-211507",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[1977,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","2021-06-15","2021-12-15",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"2021-07-02","2022-01-06"]
[1978,0,"Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1979,880087,"LTE iterbCA for 2 bands DL with 1 band UL","LTE_CA_R17_2BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221389",null,"Qualcomm",null,"25/9/20: WID:RP-201248->RP-201754; 6/1/21: WID:RP-201754->RP-202573; 7/4/21: WID:RP-202573->RP-210227; 2/7/21: WID:RP-210227->RP-211560; 29/9/21: WID:RP-211560->RP-211859; 6/1/22: WID:RP-211859->RP-212933; 5/4/22: WID:RP-212933->RP-220552; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1980,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1981,880287,"   Perf. part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 6/6/22: Comp ; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1982,880088,"LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221526",null,"Huawei",null,"25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540; 2/7/21: WID:RP-210540->RP-211388; 29/9/21: WID:RP-211388->RP-212192; 6/1/22: WID:RP-212192->RP-213144; 5/4/22: WID:RP-213144->RP-220715; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1983,880188,"   Core part: LTE_CA_R17_3BDL_1BUL","LTE_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221526","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","; 22/3/22: Compl:0%->67%; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1984,880288,"   Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220713","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","6/1/21: stopped at 0%; 22/3/22: Compl:100%->10%; 22/3/22: CD:15/09/2021->10/06/2022 ; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,96,null,"2020-07-28","2022-06-20"]
[1985,880089,"LTE iterbCA Core for x bands DL (x=4, 5, 6) with 1 band UL","LTE_CA_R17_xBDL_1BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221305",null,"Nokia",null,"25/9/20: WID:RP-201245->RP-201911; 6/1/21: WID:RP-201911->RP-202212; 7/4/21: WID:RP-202212->RP-210837; 2/7/21: WID:RP-210837->RP-211068; 29/9/21: WID:RP-211068->RP-211885; 6/1/22: WID:RP-211885->RP-212813; 5/4/22: WID:RP-212813->RP-220175; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1986,880189,"   Core part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1987,880289,"   Perf. part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1988,880090,"LTE iterbCA for 2 bands DL with 2 bands UL","LTE_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221528",null,"Huawei",null,"25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542; 2/7/21: WID:RP-210542->RP-211390; 29/9/21: WID:RP-211390->RP-212194; 5/4/22: WID:RP-212194->RP-220718; 12/7/22: WID:RP-220718->RP-221528",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1989,880190,"   Core part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","; 22/3/22: Compl:0%->70%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A1990+1","v":1990},880290,"   Perf. part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","22/3/22: CD:15/09/2021->12/06/202222/3/22: Stat Rep: ->RP-220716 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1991,880091,"LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL","LTE_CA_R17_xBDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221188",null,"LG",null,"25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200; 2/7/21: WID:RP-210200->RP-211041; 29/9/21: WID:RP-211041->RP-211748; 6/1/22: WID:RP-211748->RP-212874; 5/4/22: WID:RP-212874->RP-220295; 12/7/22: WID...",null,88,45,null,null,"2020-07-28","2022-07-12"]
[1992,880191,"   Core part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1993,880291,"   Perf. part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[1994,1010051,"UE Conformance - Rel-17 LTE CA Configurations ","LTE_CA_R17-UEConTest",1,"Rel-17","R5","2023-09-09","2024-12-12",0.5,"RP-232260","RP-241306","Lei GAO, China Telecom","gaol8@chinatelecom.cn","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233566; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 14/3/24: FCD:11/12/2024->12/12/2024; Compl:5%->30%; Stat Rep: RP-233566->RP-240360; ; 13/6/24: Compl:30%->50%; Stat ...",null,101,51,null,null,"2023-10-06","2024-06-13"]
[1995,0,"Release 17 other Studies","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1996,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"2020-09-10","2022-03-12"]
[1997,900020,"Study on enhanced Security Aspects of the 5G Service Based Architecture ","FS_eSBA_SEC",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201021",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","10/2/21: 33.875 added;; 19/3/21: 0%->45; 19/3/21: FCD:11/06/2021->09/21; 11/6/21: 45%->70; 11/6/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->75; 12/9/22: 75%->87; 31/3/23: 87%->100",33.875,90,46,null,null,"2020-12-04","2023-03-31"]
[1998,810037,"Study on SECAM and SCAS for 3GPP virtualized network products","FS_VNP_SECAM_SCAS",1,"Rel-17","S3","2018-10-02","2021-12-10",1,"SP-180696",null,"Minpeng Qi, China Mobile","qiminpeng@chinamobile.com","2/10/18: Moved from Rel-17¦7/12/18: 0%->5¦20/3/19: 5%->20; 13/9/19: 20%->30; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 30%->35; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 35%->60; 5/12/20: 60%->70; ","New",81,41,null,null,"2018-09-06","2021-09-13"]
[1999,820010,"Study on Long Term Key Update Process (LTKUP) Detailed solutions","FS_LTKUP_Detail",1,"Rel-17","S3","2018-12-13","2020-03-12",1,"SP-181038",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100",null,82,42,null,null,"2018-12-06","2020-06-26"]
[2000,880011,"Study on 5G Glass-type AR/MR Devices ","FS_5GSTAR",1,"Rel-17","S4","2020-06-25","2022-03-11",1,"SP-200399",null,"Hakju Ryan Lee ","hakju00.lee@samsung.com ","25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 65%->80; 13/12/21: 80%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100",26.998000000000001,88,45,null,null,"2020-06-25","2022-03-12"]
[2004,870011,"Study on 5G Video Codec Characteristics ","FS_5GVideo",1,"Rel-17","S4","2020-03-25","2022-06-10",1,"SP-200052",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->75; 13/12/21: 75%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->90; 12/3/22: FC ",null,87,44,null,null,"2019-12-06","2022-06-04"]
[2007,880024,"   CT1 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 13/9/21: 15%->60; 13/12/21: 60%->90; 12/3/22: FCD:08/09/2021->3/22; 12/3/22: 90%->100","23.700-10",88,45,null,null,"2020-06-26","2022-03-12"]
[2011,880075,"Study on scenarios and requirements of in-coverage, partial coverage, and out-of-coverage NR positioning use cases","FS_NR_pos_cov",1,"Rel-17","RP","2020-06-22","2021-09-15",1,"RP-201518",null,"LG Electronics",null,"25/9/20: WID:RP-201384->RP-201518; 29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[2014,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","2020-06-22","2022-03-11",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"2020-07-28","2022-04-05"]
[2017,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","2020-12-14","2021-09-08",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[2018,890021,"Study on charging aspects of 5GS CIoT ","FS_5G_CIoT_CH",1,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200771",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","5/12/20: 0%->15; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 15%->30; 13/9/21: 30%->70; 13/9/21: FCD:Wed 08/09/->12/21; 4/6/22: 70%->100",null,89,45,null,null,"2020-09-10","2022-06-04"]
[2021,830034,"Stopped - Study on UPF enhancement for control and SBA","FS_UPCAS",1,"Rel-17","S2","2019-03-07","2020-03-06",1,"SP-190187",null,"Dan Wang, China Mobile","wangdanyjy@chinamobile.com","21/1/22: stopped at 0%; 21/1/22: 0%->100","New",83,42,95,null,"2019-03-14","2022-01-21"]
[2026,830098,"Enhancement of URLLC support in the 5G Core network","5G_URLLC",1,"Rel-16",null,"2017-12-15","2024-03-03",1,"SP-181122",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-03-14"]
[2029,820019,"   Stage 2 of 5G_URLLC ","5G_URLLC",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181233",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2032,870059,"      CT1 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100",null,87,44,null,null,"2019-05-31","2020-03-26"]
[2036,1000013,"   Management Aspects of URLLC ","URLLC_Mgt",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230631",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->100","28.541; 28.552; 28.554 ",100,51,null,null,"2023-06-08","2024-03-14"]
[2039,830074,"Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC)","NR_L1enh_URLLC",1,"Rel-16","R1","2018-06-15","2023-12-12",0.99,"RP-191584",null,"Huawei",null,"26/6/19: WID:RP-190726->RP-191584",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2042,830274,"   Perf. part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-190726",null,"Huawei",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[2046,800098,"   Study on NR Industrial Internet of Things (IoT)","FS_NR_IIOT",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181479",null,"Nokia",null,"TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100",38.825000000000003,80,41,null,null,"2018-06-27","2019-03-26"]
[2047,830180,"   Core part: Support of NR Industrial Internet of Things (IoT)","NR_IIOT-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200797",null,"Nokia",null,"28/7/20: WID:RP-192590->RP-200797; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2051,800007,"Service requirements for cyber-physical control applications in vertical domains","cyberCAV",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180321",null,"Joachim W. Walewski (Siemens)",null,"10/9/18: 5%->40¦4/12/18: 40%->100","22.261; 22.104",80,41,null,null,"2018-06-06","2018-12-04"]
[{"$f":"A2054+1","v":2054},820017,"   Stage 2 of Vertical_LAN","Vertical_LAN",2,"Rel-16","S2","2018-12-13","2019-06-24",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-12-06"]
[2057,830010,"   CT aspects of Vertical_LAN","Vertical_LAN",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272",null,83,42,null,null,"2018-12-06","2019-12-09"]
[2061,850048,"Service Enabler Architecture Layer for Verticals","SEAL",1,"Rel-16",null,"2019-03-07","2020-06-12",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 8/10/19: 33.434 added;; 8/10/19: 24.548 added;","new 23.434; 33.434; 24.548; 24.547",85,42,null,null,"2018-12-06","2019-10-08"]
[2064,850006,"   CT aspects of SEAL ","SEAL",2,"Rel-16","ct","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ",null,"New ",85,43,null,null,"2019-09-13","NA"]
[2067,820067,"NR-based access to unlicensed spectrum","NR_unlic",1,"Rel-16","R1","2017-03-15","2019-12-15",0.89,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834",null,82,42,null,null,"2019-01-16","2020-09-25"]
[2069,820167,"   Core part: NR-based access to unlicensed spectrum","NR_unlic-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[2072,800006,"LAN support in 5G","5GLAN",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","11/3/22: 99%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2022-03-11"]
[2076,0,"Cellular IoT support and evolution ","-",1,"Rel-16",null,"2016-06-18","2016-06-18",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2079,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[2082,830039,"      CT3 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100","29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514",83,42,null,null,"2018-12-06","2020-06-26"]
[2086,800033,"Study on evolution of Cellular IoT security for the 5G System","FS_CIoT_sec_5G",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180440",null,"Noamen Ben Henda ","noamen.ben.henda@ericsson.com","6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100","New; 33.861",80,41,null,null,"2018-06-06","2020-06-26"]
[2088,800083,"Additional MTC enhancements for LTE","LTE_eMTC5",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦16/1/19: WID:RP-181450->RP-182891¦26/3/19: WID:RP-182891->RP-190770; 26/6/19: WID:RP-190770->RP-191356; 14/1/20: WID:RP-191356->RP-192875",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2091,800084,"Additional enhancements for NB-IoT","NB_IOTenh3",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2094,810050,"5G message service","5GMSG",1,"Rel-16","S1","2016-06-18","2018-12-14",1,"SP-180772",null,null,null,null,22.262,81,41,null,null,"2018-09-06","NA"]
[2097,0,"Advanced V2X support","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2101,780025,"   Study on V2XAPP","FS_V2XAPP",2,"Rel-16","S6","2017-12-15","2018-09-14",1,"SP-171071",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100",null,78,40,null,null,"2017-12-15","2018-12-07"]
[2104,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[2107,840078,"Architecture enhancements for 3GPP support of advanced V2X services","eV2XARC",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30","23.501; 23.502; 23.503; 23.285",84,43,null,null,"2018-12-06","2019-03-14"]
[2109,820018,"   Stage 2 of eV2XARC","eV2XARC",2,"Rel-16","S2","2018-12-13","2019-06-14",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100","23.501; 23.502; 23.503; 23.285; 24.588",82,42,null,null,"2018-12-06","2020-03-25"]
[2115,860014,"   Security Aspects of eV2XARC","eV2XARC",2,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191125",null,"Dongjoo Kim, LG Electronics Inc. ","dongjoo7.kim@lge.com ","; 6/12/19: 0%->10; 25/3/20: 10%->70; 26/6/20: 70%->95; 12/9/20: 95%->98; 5/12/20: 98%->99; 19/3/21: 99%->100","33.220; TS 33.536",86,44,null,null,"2019-12-06","2021-03-19"]
[2116,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2119,830078,"5G V2X with NR sidelink","5G_V2X_NRSL",1,"Rel-16","R1","2019-03-01","2024-12-12",0.8,"RP-200129",null,"LG Electronics",null,"26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2122,880069,"   UE Conformance Test Aspects - 5G V2X with NR sidelink","5G_V2X_NRSL_eV2XARC-UEConTest",2,"Rel-16","R5","2020-06-22","2024-12-12",0.68,"RP-200894","RP-241367","Xuesong Wang, Huawei Technologies. Co., Ltd","wangxuesong743@huawei.com","8/10/20: 0%->5; 8/4/21: 5%->11; 2/7/21: 11%->18; 22/3/22: Compl:18%->43%; ; 5/4/22: WID:RP-200894->RP-220744 20/6/22: Rapporteur: Huawei->Xuesong Wang, Huawei Technologies. Co., Ltd; Rap eMail: ->wangxuesong743@huawei.com12/7/22: WID:RP-20089...; 9/1...",null,88,45,null,null,"2020-07-28","2024-06-13"]
[2126,800049,"   Stage 1 of 5G_HYPOS","5G_HYPOS",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ","10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[2129,810035,"   Study on Security of the enhancement to the 5GC location services","FS_eLCS_Sec",2,"Rel-16","S3","2018-09-06","2019-12-13",1,"SP-180694",null,"Wei Zhou, CATT","zhouwei@catt.cn","7/12/18: 0%->5¦20/3/19: 5%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[2134,830046,"      CT4 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100","24.080; 29.518; 29.572; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-06-26"]
[2137,800092,"   Study on NR positioning support","FS_NR_pos",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181399",null,"Intel",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2140,830277,"   Perf. part: NR positioning support","NR_pos-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-192581",null,"Intel",null,"2/7/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-07-02"]
[2141,900057,"   UE Conformance Test Aspects - NR positioning support ","NR_pos-UEConTest",2,"Rel-16","R5","2020-12-14","2023-09-08",1,"RP-212227","RP-231835","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5; 29/9/21: WID:RP-202727->RP-212227; 22/3/22: Compl:5%->54%; ; 20/6/22: Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn12/7/22: WID:RP-212227->RP-221450 ; ;...; 9/12/22: FCD:22/12...",null,90,46,null,null,"2021-01-06","2023-09-06"]
[2144,800025,"   Study on RACS","FS_RACS",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180599",null,"Haris Zisimopoulos, Qualcomm Incorporated ","harisz@qti.qualcomm.com","10/9/18: 0%->40¦7/12/18: 40%->70¦14/3/19: 70%->100","New",80,41,null,null,"2018-06-06","2019-03-14"]
[2147,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[2151,800097,"   Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects","FS_RACS_RAN",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181459",null,"MediaTek",null,"TR 37.873¦related SA2 SI FS_RACS was started at SA #80 ¦6/8/18: 37.873 added;¦26/3/19: 0%->100",37.872999999999998,80,41,null,null,"2018-06-27","2019-03-26"]
[2155,0,"Enablers for Network Automation Architecture for 5G","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2159,830009,"   CT aspects of eNA","eNA",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259",null,83,42,null,null,"2018-12-06","2019-09-17"]
[2162,0,"Wireless and Wireline Convergence Enhancement ","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2165,830050,"Wireless and Wireline Convergence for the 5G system architecture","5WWC",1,"Rel-16",null,"2018-12-06","2020-06-12",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[2166,820014,"   Stage 2 of 5WWC","5WWC",2,"Rel-16","S2","2018-12-06","2019-06-13",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2169,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[2173,830082,"   NG interface usage for WWC","5WWC-NG_interface",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190772",null,"Huawei",null,null,null,83,42,null,null,"2019-03-26","NA"]
[2176,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[2180,860003,"   CT aspects of enh2MCPTT ","enh2MCPTT-CT",2,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193148",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","; 26/3/20: 0%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484 ",86,44,null,null,"2019-12-06","2020-03-26"]
[2184,850051,"MCData File Distribution support over xMB","MC_XMB",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,85,43,null,null,"2018-09-06","2019-05-31"]
[2187,810011,"Protocol enhancements for Mission Critical Services","MCProtoc16",1,"Rel-16","C1","2018-09-06","2019-12-20",1,"CP-182110",null,"AXELL, Jörgen","jorgen.axell@ericsson.com","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980",81,41,null,null,"2018-09-06","2020-03-26"]
[2190,760051,"   Study on MBMS APIs for MC Services","FS_MBMSAPI_MC",2,"Rel-16","S6","2017-06-05","2018-06-15",1,"SP-180237",null,"Ling Zhang, TD Tech Ltd","zhangling@td-tech.com","12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100","new 23.792",76,39,null,null,"2017-06-03","2018-06-14"]
[2191,800020,"   Stage 2 of MBMS APIs for MC Services","MBMSAPI_MCS",2,"Rel-16","S6","2018-06-06","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com","6/8/18: 23.479 added;¦10/9/18: 0%->15¦7/12/18: 15%->65¦14/3/19: 65%->90; 31/5/19: 90%->100","New; 23.479",80,41,null,null,"2018-06-06","2019-05-31"]
[2194,850059,"   CT4 aspects of eNAPIs","eNAPIs",2,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[2197,800021,"   Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",2,"Rel-16","S6","2018-06-06","2019-06-14",1,"SP-180680",null,"Monnes, Peter, Harris Corporation","pmonnes at harris dot com ","10/9/18: 0%->5¦2/10/18: WID:SP-180381->SP-180680¦7/12/18: 5%->15¦14/3/19: 15%->40; 31/5/19: 40%->70; 13/9/19: 70%->100",23.283000000000001,80,41,null,null,"2018-06-06","2019-09-13"]
[2202,800052,"   Stage 1 of ePWS","ePWS",2,"Rel-16","S1","2017-12-15","2018-12-14",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[2205,810047,"      CT1 aspects of ePWS ","ePWS",3,"Rel-16","C1","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","14/3/19: 0%->30; 3/6/19: FCD:14/06/2019->03/20; 3/6/19: WID:CP-182228->CP-191155; 20/9/19: 0%->100; 6/12/19: 100%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",23.041,81,41,null,null,"2018-09-06","2020-06-26"]
[2209,790023,"   Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2","FS_FRMCS2_SA6",2,"Rel-16","S6","2018-03-15","2019-03-12",1,"SP-181133",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","19/4/18: 0%->5¦14/6/18: 5%->15¦6/8/18: 23.796 added;¦10/9/18: 15%->20¦7/12/18: 20%->65¦7/12/18: FCD:12/18->03/19¦14/3/19: 65%->100","23.cde; 23.796",79,40,null,null,"2018-03-15","2019-03-14"]
[2212,840009,"   CT aspects of MONASTERY2 ","MONASTERY2",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","9/12/19: WID:CP-191152->CP-193143",null,84,43,null,null,"2019-05-31","2019-12-09"]
[2215,840092,"NR support for high speed train scenario","NR_HST",1,"Rel-16","R4","2019-06-17","2022-06-22",1,"RP-191788",null,"CMCC",null,"8/10/19: WID:RP-191512->RP-191788",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2216,840192,"   Core part: NR support for high speed train scenario","NR_HST-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-191788",null,"CMCC",null,"28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2222,0,"Streaming and TV","-",1,"Rel-16",null,"2016-12-01","2019-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2224,740001,"   Study on eLSTR","FS_eLESTR",2,"Rel-16","S1","2016-12-01","2018-03-15",1,"SP-160960",null,"China Telecommunications, XIA Xu","xiaxu@ctbri.com.cn","2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100",22.832999999999998,74,38,null,null,"2016-12-01","2018-03-16"]
[2227,810003,"Coverage and Handoff Enhancements for Multimedia ","CHEM",1,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180664",null,"Nikolai Leung","nleung@qti.qualcomm.com","7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[2230,820002,"Media streaming architecture ","5GMSA",1,"Rel-16","S4","2018-12-06","2019-06-12",1,"SP-180984",null,"Frédéric GABIN ","Frederic.gabin@ericsson.com ","; 31/5/19: 0%->100","26.501; 26.233 ",82,42,null,null,"2018-12-07","2019-05-31"]
[2234,810002,"   Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",2,"Rel-16","S4","2018-09-06","2019-12-12",1,"SP-190640",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->35¦7/3/19: 35%->50; 31/5/19: 50%->75; 13/9/19: 75%->80; 13/9/19: FCD:13/09/2019->12/20; 19/9/19: WID:SP-180663->SP-190640; 6/12/19: 80%->90; 25/3/20: 90%->100","26.114; 26.131; 26.132; 26.223; 26.919",81,41,null,null,"2018-09-06","2020-03-25"]
[2237,800003,"Addition of HLG HDR to TV Video Profiles","HLG_HDR",1,"Rel-16","S4","2018-06-06","2018-09-14",1,"SP-180287",null,"Paul Szucs, Sony Europe Limited","paul.szucs@sony.com","10/9/18: 0%->100","26.116; 26.346; 26.234",80,41,null,null,"2018-06-06","2018-09-10"]
[2238,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2241,800050,"   Stage 1 of User Identities and Authentication","UIA",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180328",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","10/9/18: 0%->100","22.101; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[2247,0,"Slicing","-",1,"Rel-16",null,"2017-09-08","2017-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2249,790011,"   Study on Enhancement of Network Slicing","FS_eNS",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180503",null,"ZTE, Tricci So ","tso at ztetx dot com","7/6/18: 0%->10¦15/6/18: WID:SP-180121->SP-180503¦6/8/18: 23.740 added;¦10/9/18: 10%->50¦7/12/18: 50%->85¦7/12/18: 85%->¦14/3/19: 85%->100","new; 23.740",79,40,null,null,"2018-03-15","2019-03-14"]
[2252,830052,"      CT1 aspects of eNS","eNS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","13/9/19: 0%->40; 6/12/19: 40%->85; 26/3/20: 85%->95; 26/6/20: 95%->97; 13/9/20: 97%->100",24.501000000000001,83,42,null,null,"2018-12-06","2020-09-13"]
[2255,810034,"   Study on Security aspects of Enhancement of Network Slicing","FS_eNS_SEC",2,"Rel-16","S3","2018-09-06","2020-03-12",1,"SP-180692",null,null,"Suresh.p.nair@nokia.com","7/12/18: 0%->15¦20/3/19: 15%->65¦20/3/19: FCD:019->06/19; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New",81,41,null,null,"2018-09-06","2020-06-26"]
[2259,770005,"   Study on Business Role Models for Network Slicing ","FS_BMNS",2,"Rel-16","S1","2017-09-08","2018-09-14",1,"SP-180169",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100","New; 22.830",77,39,null,null,"2017-09-08","2018-12-04"]
[2262,810031,"Enhancement of performance assurance for 5G networks including network slicing","5G_SLICE_ePA",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2019-05-31"]
[2263,850055,"   Overall aspects of 5G_SLICE_ePA","5G_SLICE_ePA",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70; 13/9/19: 70%->85; 13/9/19: 85%->; 26/3/20: 85%->97; 28/6/20: 97%->100","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2020-06-28"]
[2268,740002,"   Study on Stage 1 of PARLOS","FS_PARLOS",2,"Rel-15","S1","2016-12-01","2018-09-10",1,"SP-160904",null,"Covell, Betsy","betsy.covell@nokia.com","1/12/16: 0%->75¦2/3/17: 75%->100¦10/9/18: FCD:03/17->09/18",22.82,74,38,null,null,"2016-12-01","2018-09-10"]
[2270,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[2274,830062,"      CT1 aspects of PARLOS","PARLOS",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->80; 13/9/19: 80%->95; 6/12/19: 95%->98; 26/3/20: 98%->100","24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007",83,42,null,null,"2018-09-06","2020-03-26"]
[2277,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[2280,770039,"   Study on ETSUN","FS_ETSUN",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180731",null,"Laurent Thiebaut (Nokia)","Laurent.thiebaut@nokia.com","15/12/17: 23.726 added;¦16/3/18: 0%->25¦7/6/18: 25%->40¦10/9/18: 40%->65¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170743->SP-180731¦2/10/18: FCD:12/18->12/18¦7/12/18: 65%->100",23.725999999999999,77,39,null,null,"2017-09-08","2018-12-07"]
[2284,830056,"      CT4 aspects of ETSUN","ETSUN",3,"Rel-16","C4","2019-03-08","2019-12-06",1,"CP-190192",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","31/5/19: 0%->25; 13/9/19: 25%->95; 6/12/19: 95%->100","29.244; 29.502; 29.510; 29.518; 29.281",83,42,null,null,"2018-12-05","2019-12-06"]
[2287,760052,"   Study on ATSSS","FS_ATSSS",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180732",null,"So, Tricci, ZTE","tso@ztetx.com","11/9/17: 0%->100¦14/9/17: 100%->10¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 10%->20¦7/6/18: 20%->40¦10/9/18: 40%->70¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170411->SP-180732¦2/10/18: FCD:12/18->12/18¦7/12/18: 70%->100","new 23.793",76,39,null,null,"2017-06-03","2018-12-07"]
[2289,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[2292,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[2295,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[2299,810007,"   Single radio voice continuity from 5GS to 3G","5G_SRVCC",2,"Rel-16","S2","2018-09-06","2019-03-14",1,"SP-180897",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","14/3/19: 0%->100","23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","2019-03-14"]
[2302,820169,"      Core part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Core",3,"Rel-16","R2","2018-12-15","2019-12-15",1,"RP-200151",null,"China Unicom",null,"no Perf. part¦26/3/19: WID:RP-182811->RP-190713; 26/3/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-03-26"]
[2306,840058,"      CT1 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","24.501; 24.237; 24.008; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[2309,790005,"Study on Remote Identification of Uncrewed Aerial Systems","FS_ID_UAS",1,"Rel-16","S1","2018-03-15","2018-09-14",1,"SP-180172",null,"Eddy Hall; Qualcomm Incorporated","edhall@qti.qualcomm.com","7/6/18: 0%->60¦10/9/18: 60%->100",22.824999999999999,79,40,null,null,"2018-03-15","2018-09-10"]
[{"$f":"A2310+1","v":2310},800034,"Study on Security Aspects of the 5G Service Based Architecture","FS_SBA_Sec",1,"Rel-16","S3","2018-06-06","2020-03-12",1,"SP-180598",null,"Hans Christian Rudolph, Deutsche Telekom AG","hans-christian.rudolph@telekom.de","6/8/18: 33.855 added;¦10/9/18: 65%->75¦7/12/18: 75%->76¦20/3/19: 76%->65¦20/3/19: FCD:018->09/19; 31/5/19: 65%->75; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New; 33.855",80,41,null,null,"2018-06-06","2020-06-26"]
[2314,830001,"   CT aspects of 5G_eSBA","5G_eSBA",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com",null,null,83,42,null,null,"2018-12-06","NA"]
[2317,850016,"   Security for 5G_eSBA","5G_eSBA",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190899",null,"Nagendra Bykampadi, Nokia ","nagendra.bykampadi@nokia.com ","; 6/12/19: 0%->45; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 45%->70; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 70%->95; 12/9/20: 95%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-09-12"]
[2320,830028,"   Stage 2 of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","S2","2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,"31/5/19: 0%->100","23.501; 23.502; 23.503; 23.228",83,42,null,null,"2019-03-14","2019-05-31"]
[2324,840064,"      CT4 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->25; 6/12/19: 25%->50; 26/3/20: 50%->90; 26/6/20: 90%->100","29.510; 29.571; 23.380",84,43,null,null,"2019-05-31","2020-06-26"]
[2327,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-21",1,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com 9/9/22: Compl:89%->97%; 29/3/23: 97%-...",null,88,45,null,null,"2020-07-28","2023-03-29"]
[2331,830004,"   CT Aspects of E2E_DELAY","E2E_DELAY",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2335,830069,"Enhancements for Common API Framework for 3GPP Northbound APIs ","eCAPIF",1,"Rel-16",null,"2018-03-15","2020-03-12",1,"SP-181137",null,"Basavaraj Pattan, Samsung","basavarajjp@samsung.com ","7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137",23.222000000000001,83,42,null,null,"2018-03-15","2018-12-13"]
[2338,850008,"   CT aspects of eCAPIF ","eCAPIF",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192254",null,"Narendranath Durga, Tangudu (Samsung) ","n.tangudu {@]samsung.com ","; 6/12/19: 0%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",29.222000000000001,85,43,null,null,"2019-09-13","2020-06-26"]
[2339,840065,"User data interworking, Coexistence and Migration","UDICOM",1,"Rel-16","S2","2019-03-14","2019-06-14",1,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ",null,"23.501; 23.502; 23.228",84,42,null,null,"2019-03-14","NA"]
[2342,840007,"   CT aspects of UDICOM","UDICOM",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193016",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->75; 9/12/19: WID:CP-191066->CP-193016; 26/3/20: 75%->90; 26/6/20: 90%->100","29.503; 29.505; 29.571; 29.510 ",84,43,null,null,"2019-05-31","2020-06-26"]
[2346,0,"NR-related Release 16 Features","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2349,860258,"   Perf. part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2352,860259,"   Perf. part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2356,830275,"   Perf. part: UE Power Saving in NR","NR_UE_pow_sav-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200494",null,"CATT",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[2360,800057,"NR intra-band Carrier Aggregation",null,1,"Rel-16",null,"2018-06-15","2019-12-13",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2363,800273,"      Perf. part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200656",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2364,800074,"   Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦16/1/19: WID:RP-180817->RP-182501¦26/3/19: WID:RP-182501->RP-190494; 26/6/19: WID:RP-190494->RP-191565; 8/10/19: WID:RP-191565->RP-191822; 14/1/20: WID:RP-191822->RP-192615; 26/3/20: WID:RP-192615->RP-200168; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2367,830099,"NR inter-band Carrier Aggregation",null,1,"Rel-16",null,"2019-03-01","2024-12-12",0.72,null,null,null,null,null,null,83,42,null,null,"2019-03-26","NA"]
[2371,830295,"      Perf. part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200918",null,"CATT",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[{"$f":"A2374+1","v":2374},830296,"      Perf. part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL-Perf",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2377,800077,"   Band 65 for New Radio","NR_band_n65",2,"Rel-16","R4","2018-06-15","2018-12-14",1,"RP-190360",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258¦26/3/19: WID:RP-182258->RP-190360",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2382,820273,"      Perf. part: Introduction of NR band n18","NR_n18-Perf",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2385,830271,"      Perf. part: Introduction of NR band n48","NR_n48-Perf",3,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190140",null,"Nokia",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2388,830290,"      Perf. part: Introduction of NR band n14","NR_n14-Perf",3,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190165",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2389,830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2392,830097,"   Introduction of NR band n259","NR_n259",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-200249",null,"Ericsson",null,"26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2396,850167,"      Core part: Introduction of NR band n26","NR_n26-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2398,840097,"   Introduction of NR supplementary DL band n29","NR_n29",2,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: WID:RP-191474->RP-192236",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2403,850268,"      Perf. part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2407,831001,"New Radio Band-related topics",null,1,"Rel-16","R4","2018-12-13","2023-12-12",0.99,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[2410,830287,"      Perf. Part: RF requirements for NR FR1","NR_RF_FR1-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193266",null,"Huawei",null,"6/1/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-01-06"]
[2411,870061,"      UE Conformance Test Aspects - RF requirements for NR FR1","NR_RF_FR1-UEConTest",3,"Rel-16","R5","2020-03-25","2023-12-12",1,"RP-230427","RP-233756","Yuxin HAO, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","affects: NR. TR 38.8xx; 8/10/20: 0%->15; 8/4/21: 15%->43; ; 6/6/22: CD:10/06/2022->22/12/2022 ; 20/6/22: Rapporteur: Huawei->Chunying Gu, Huawei Technologies. Co., Ltd.; Rap eMail: ->guchunying@huawei.com9/9/22: Compl:64%->69%; 9/12/22: FCD:22/12/20...",null,87,44,null,null,"2020-01-14","2023-12-08"]
[2414,830288,"      Perf. part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Perf",3,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200124",null,"China Telecom",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[2417,830189,"      Core part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200668",null,"Nokia",null,"8/10/19: 38.831 added;; 25/9/20: 0%->100",38.831000000000003,83,42,null,null,"2019-03-26","2020-09-25"]
[2423,820074,"   Adding wider channel bandwidths in NR band n7","NR_n7_BW",2,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2425,830093,"   Addition of wider channel bandwidth in NR band n38","NR_n38_BW",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191472",null,"Huawei",null,"26/6/19: WID:RP-190392->RP-191472; 14/1/20: WID:RP-191472->RP-192513; 13/6/21: WID:RP-192513->RP-191472",null,83,42,null,null,"2019-03-26","2021-06-13"]
[2428,850063,"   Addition of further channel bandwidths in NR band 38","NR_n38_BW2",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192513",null,"Ericsson",null,"13/6/21: WID:RP-192215->RP-192513",null,85,43,null,null,"2019-10-08","2021-06-13"]
[2432,820175,"      Core part: Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2435,820176,"      Core part: Adding wider channel bandwidths in NR band n50","NR_n50_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2436,850064,"   Addition of wider channel bandwidths in NR band n75","NR_n75_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192216",null,"Ericsson",null,null,null,85,43,null,null,"2019-10-08","NA"]
[2439,850065,"   Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: WID:RP-192219->RP-192401",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2444,850266,"      Perf. part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2447,850269,"      Perf. part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[2450,800085,"Enhancements on MIMO for NR","NR_eMIMO",1,"Rel-16","R1","2018-06-15","2022-09-22",1,"RP-200474",null,"Samsung",null,"16/1/19: WID:RP-181453->RP-182863; 8/10/19: WID:RP-182863->RP-192271; 26/3/20: WID:RP-192271->RP-200474",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2454,800087,"NR mobility enhancements","NR_Mob_enh",1,"Rel-16","R2","2018-06-15","2022-09-22",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 8/10/19: WID:RP-190489->RP-192277; 14/1/20: WID:RP-192277->RP-192534",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2457,880068,"   UE Conformance Test Aspects - NR Mobility Enhancements","NR_Mob_enh-UEConTest",2,"Rel-16","R5","2020-06-22","2022-09-22",1,"RP-221481","RP-221480","Zhaobing Yang, Huawei Technologies. Co., Ltd.","yangzhaobing @hisilicon.com","8/10/20: 0%->5; 8/4/21: 5%->35; 22 6/6/22: CD:10 ; 20/6/22: Rapporteur: Huawei->Zhaobing Yang, Huawei Technologies. Co., Ltd.; Rap eMail: ->yangzhaobing @hisilicon.com12/7/22: WID:RP-200893->RP-2214819/9/22: Compl:97%->100%9/9/22: ...",null,88,45,null,null,"2020-07-28","2022-09-09"]
[2460,820268,"   Perf. part: 2-step RACH for NR","NR_2step_RACH-Perf",2,"Rel-16","R4","2018-12-15","2019-06-20",1,"RP-200085",null,"ZTE",null,"26/3/19: WID:RP-182894->RP-190711; 6/1/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-01-06"]
[2461,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-22",1,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[2465,810030,"Study on Self-Organizing Networks (SON) for 5G","FS_SON_5G",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180827",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com ","7/12/18: 0%->10¦14/3/19: 10%->40; 31/5/19: 40%->50; 6/12/19: 50%->100","New",81,41,null,null,"2018-09-06","2019-12-06"]
[2468,840193,"   Core part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-210590",null,"CATT",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[2472,890048,"   UE Conformance Test Aspects - NR performance requirement enhancement ","NR_perf_enh-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-202557","RP-221294","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","tested: REL-16 WI NR_perf_enh-Perf ; 6/1/21: WID:RP-201941->RP-202557; Qualcomm -> China Telecom; 8/4/21: 0%->15; 2/7/21: 15%->18; 13/9/21: Compl:18%->21%; ; 20/6/22: Rapporteur: Qualcomm -> China Telecom->Wu Jingzhou, Balasubramanian Vijay, C...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2475,840295,"   Perf. part: NR RRM enhancement","NR_RRM_enh-Perf",2,"Rel-16","R4","2019-06-17","2020-06-15",1,"RP-202655",null,"Intel",null,"6/1/21: WID:RP-201883->RP-202655; 7/4/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-04-07"]
[2479,840296,"   Perf. part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-200658",null,"Ericsson",null,"basket WI; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2482,840298,"   Perf. part: Addition of wider channel bandwidth in NR band n1","NR_n1_BW-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-192009",null,"Ericsson",null,"26/3/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-03-26"]
[2485,841000,"Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2486,841100,"   Core part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2490,850074,"   Perf. part: Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex-Perf",2,"Rel-16","R4","2019-09-19","2019-12-13",1,"RP-192820",null,"Huawei",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2493,940091,"   UE Conformance Test Aspects - Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-UEConTest",2,"Rel-16","R5","2021-12-13","2022-06-22",1,"RP-213228","RP-221486","Huawei",null,"tested: REL-16 WI DC_Pcmax_3UL_CC-Core; 22/3/22: Compl:0%->71%; ; ",null,94,48,null,null,"2022-01-06","2022-06-06"]
[2497,860054,"Over the air (OTA) base station (BS) testing TR","OTA_BS_testing",1,"Rel-16","R4","2019-03-07","2019-06-05",1,"RP-193225",null,"Huawei",null,"affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16",null,86,44,null,null,"2020-02-18","NA"]
[2500,860155,"   Core part: High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","ENDC_UE_PC2_FDD_TDD-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-201578",null,"China Unicom",null,"affects: LTE, NR. no Perf. part; 25/9/20: WID:RP-193244->RP-201578; 25/9/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-09-25"]
[2504,860257,"   Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2507,800088,"LTE-NR & NR-NR Dual Connectivity and NR Carrier Aggregation enhancements","LTE_NR_DC_CA_enh",1,"Rel-16","R2","2018-06-15","2023-06-06",0.99,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 26/6/19: WID:RP-190452->RP-191600; 8/10/19: WID:RP-191600->RP-192336; 28/7/20: WID:RP-192336->RP-200791",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2510,911004,"   UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements ","LTE_NR_DC_CA_enh-UEConTest",2,"Rel-16","R5","2021-03-12","2023-06-06",1,"RP-231105","RP-230915","Matti Kangas","matti.kangas@nokia.com","lested: REL-16 WI LTE_NR_DC_CA_enh-Core ; 2/7/21: WID:RP-210746->RP-211442; 2/7/21: 0%->5; 5/4/22: WID:RP-211442->RP-220801; 20/6/22: FCD:11/03/2022->22/12/2022; Compl:5%->40%; WID: RP-220801->RP-211442; Stat Rep: ->RP-221416; Rapporteur: Nokia->Matti...",null,91,46,null,null,"2021-04-07","2023-08-09"]
[2511,820079,"High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD",1,"Rel-16","R4","2018-12-13","2020-03-18",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2515,870062,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-UEConTest",2,"Rel-16","R5","2019-03-07","2020-03-18",1,"RP-202066",null,"CMCC",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200434->RP-200761; 25/9/20: WID:RP-200761->RP-202066; 25/9/20: 0%->100",null,87,44,null,null,"2020-01-14","2020-09-25"]
[2519,820180,"   Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex-Core",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-190175",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2522,920068,"   UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41 and NR Band n41 ","LTE_NR_B41_Bn41_PC29dBm-UEConTest",2,"Rel-16","R5","2021-06-15","2022-12-01",1,"RP-211443","RP-223059","Dan SONG, CMCC, T-Mobile","songdan@chinamobile.com","tested: REL-17 WI LTE_NR_B41_Bn41_PC29dBm-Core ; 5/4/22: WID:RP-211443->RP-220124 6/6/22: C ; 20/6/22: Stat Rep: R5-222679->RP-221180 / R5-222679; Rapporteur: T-Mobile USA->Scott Probasco, Dan SONG, T-Mobile, CMCC; Rap eMail: ->scott.probasco@t-mobile....",null,92,47,null,null,"2021-07-02","2023-01-09"]
[2525,800166,"      Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2529,800267,"      Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2532,800268,"      Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200657",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2536,800070,"   Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01",null,80,41,null,null,"2018-06-27","NA"]
[2537,800170,"      Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2540,800171,"      Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2544,790157,"   Core part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Core",2,"Rel-16","R4","2018-03-15","2018-12-14",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: 0%->100",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[2547,800059,"LTE intra-band Carrier Aggregation (CA)",null,1,"Rel-16",null,"2018-06-15","2022-12-21",0.82,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2550,800260,"      Perf. part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2554,800062,"   Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦TR 36.716-03-01¦16/1/19: WID:RP-181436->RP-182553¦26/3/19: WID:RP-182553->RP-190375; 26/6/19: WID:RP-190375->RP-191120; 8/10/19: WID:RP-191120->RP-192083; 14/1/20: WID:RP-192083->RP-192811; 26/3/20: WID:RP-192811->RP-200451; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2557,800063,"   Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201238",null,"Nokia",null,"basket WI¦TR 36.716-04-01¦16/1/19: WID:RP-181408->RP-182330¦26/3/19: WID:RP-182330->RP-190138; 26/6/19: WID:RP-190138->RP-190906; 8/10/19: WID:RP-190906->RP-191730; 14/1/20: WID:RP-191730->RP-192423; 26/3/20: WID:RP-192423->RP-200157; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2561,800164,"      Core part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2562,800264,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2565,800265,"      Perf. part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200740",null,"LG Electronics",null,"basket WI¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2569,830176,"   Core part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Core",2,"Rel-16","R1","2019-03-01","2019-12-13",1,"RP-193050",null,"Qualcomm",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2572,830194,"   Core part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Core",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2575,800056,"Additional LTE bands",null,1,"Rel-16",null,"2018-06-15","2021-09-21",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2578,800275,"      Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2583,800079,"Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,null,null,80,41,null,null,"2018-06-27","NA"]
[2584,800179,"   Core part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Core",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,"14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2587,800182,"   Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Core",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2590,800086,"DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE",1,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"16/1/19: WID:RP-181485->RP-182901; 14/1/20: WID:RP-182901->RP-192766",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2594,820171,"   Core part: Transfer of Iuant interface specifications from 25-series to 37-series","Iuant_transfer-Core",2,"Rel-16","R3","2018-12-13","2019-03-18",1,"RP-190160",null,"Huawei",null,"administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf .",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2597,800089,"Even further mobility enhancement in E-UTRAN","LTE_feMob",1,"Rel-16","R2","2018-06-15","2022-06-22",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 26/6/19: WID:RP-190272->RP-190921; 26/3/20: WID:RP-190921->RP-200148",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2599,800289,"   Perf. part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200148",null,"China Telecom",null,"26/3/19: WID:RP-181475->RP-190272; 7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[2605,850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2608,0,"All other Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2609,840001,"5G Media Streaming stage 3 ","5GMS3",1,"Rel-16","S4","2019-06-06","2020-09-15",1,"SP-190464",null,"Paul Szucs, Sony","Paul.Szucs@Sony.com","13/9/19: 0%->25; 6/12/19: 25%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->70; 25/3/20: FCD:12/03/2020->06/20; 10/6/20: 70%->85; 26/6/20: FCD:12/06/2020->09/20; 12/9/20: 85%->100. Moved to Rel-16","26.234; 26.247; 26.117; 26.502; 26.503; 26.504; 26.511; 26.512",84,43,null,null,"2019-05-31","2020-09-12"]
[2612,830086,"Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications","MSR_GSM_UTRA_LTE_NR",1,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190642",null,"Ericsson",null,null,null,83,42,null,null,"2019-03-26","NA"]
[2615,840066,"Volume Based Charging Aspects for VoLTE","VBCLTE",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50","32.251; 32.260; 32.298; 32.299",84,43,null,null,"2018-09-06","2019-03-14"]
[2619,840068,"      CT3 aspects of VBCLTE","VBCLTE",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201206",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","6/12/19: 0%->100; 26/6/20: WID:CP-191110->CP-201206","29.212; 29.213; 29.214",84,43,null,null,"2019-05-31","2020-06-26"]
[2624,850002,"      CT4 aspects of IABARC ","IABARC",3,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP201074",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 9/12/19: WID:CP-192256->CP-193015; 26/3/20: 0%->100; 2/7/20: WID:CP-193015->CP 201074","24.301; 24.501; 23.008; 29.230; 29.272; 29.274; 29.503; 29.504; 29.505; 29.509; 29.518 ",85,43,null,null,"2019-09-13","2020-07-02"]
[2627,820270,"   Perf. Part: NR_IAB","NR_IAB-Perf",2,"Rel-16","R4","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added;; 2/7/21: 0%->100","38.809; 38.176-1; 38.176-2",82,42,null,null,"2019-01-16","2021-07-02"]
[{"$f":"A2630+1","v":2630},790003,"Enhancements to IMS for new real time communication services","enIMS",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180137",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","7/6/18: 0%->25¦10/9/18: 25%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100","22.261; 22.468; 22.228; 22.280; 22.281; 22.282; 22.179",79,40,null,null,"2018-03-15","2018-12-04"]
[2633,820039,"Signalling Improvements for Network Efficiency in 5GS ","SINE_5G",1,"Rel-16","C1","2018-12-13","2019-12-12",1,"CP-190142",null,"Shu, Lin ","shulin@huawei.com ","¦14/3/19: 0%->50¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183085->CP-190142; 31/5/19: 50%->75; 13/9/19: 75%->85; 6/12/19: 85%->95; 26/3/20: 95%->100","24.501; 24.301; 24.368; 27.007; 24.008 ",82,42,null,null,"2018-12-07","2020-03-26"]
[2634,790001,"New Services and Markets Technology Enablers – Phase 2 ","SMARTER_Ph2",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180589",null,"Li, Alice, Vodafone","alice.li@vodafone.com","7/6/18: WID:SP-180138->SP-180313¦7/6/18: 0%->10¦10/9/18: 10%->40¦4/12/18: 40%->100","22.261; 22.278",79,40,null,null,"2018-03-15","2018-12-04"]
[2637,840069,"5GS Transfer of Policies for Background Data Transfer","xBDT",1,"Rel-16",null,"2019-03-07","2020-03-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com",null,"23.501; 23.502; 23.503",84,43,null,null,"2018-06-06","NA"]
[2640,840070,"      CT1 aspects of xBDT","xBDT",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","13/9/19: 0%->100",24.526,84,43,null,null,"2019-05-31","2019-09-13"]
[2645,800046,"Shared Data Handling on Nudm and Nudr","Shared_Data",1,"Rel-16","C4","2018-06-06","2018-12-14",1,"CP-181136",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com","10/9/18: 0%->90¦10/12/18: 90%->100","29.503; 29.505; 29.504",80,41,null,null,"2018-06-06","2018-12-10"]
[2648,790004,"QoS Monitoring ","QoS_MON",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180141",null,"Amar Deol ","amar.deol@huawei.com","7/6/18: 0%->60¦10/9/18: 60%->85¦10/9/18: FCD:06/18->12/18¦4/12/18: 85%->100",22.260999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[2652,810025,"Network policy management for mobile networks based on NFV scenarios","NETPOL",1,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-191194",null,"China Mobile Hao Zhang ","zhanghao@chinamobile.com","7/12/18: 0%->10; 13/9/19: 10%->85; 13/9/19: FCD:13/09/2019->12/20; 6/12/19: 85%->100; 12/12/19: WID:SP-180821->SP-191194","New",81,41,null,null,"2018-09-06","2019-12-12"]
[2655,820030,"Nchf Online and Offline charging services ","OFSBI_CH",1,"Rel-16","S5","2018-12-13","2019-09-19",1,"SP-181066",null,"Zhu Lei, Huawei","Zhulei@huawei.com ","¦14/3/19: 0%->40; 31/5/19: 40%->70; 13/9/19: 70%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-09-13"]
[2658,820033,"Network Exposure Charging in 5G System Architecture ","5GS_Ph1_NEFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181070",null,"Tornkvist, Robert, Ericsson ","robert(dot)tornkvist(at)Ericsson(dot)com ","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100","32.240; 32.254; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-12-06"]
[2659,820034,"Charging AMF in 5G System Architecture Phase 1 ","5GS_Ph1_AMFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181071",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->70; 6/12/19: 70%->100","32.240; 32.290; 32.291; 32.298; 32.297 ",82,42,null,null,"2018-12-07","2019-12-06"]
[2662,820038,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 30/6/20: 99%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",82,42,null,null,"2018-12-07","2020-06-30"]
[2666,820041,"Stage-3 5GS NAS protocol development ","5GProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 25/3/20: WID:CP-183087->CP-200146","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-03-25"]
[2670,820046,"   Stage-3 SAE Protocol Development for Rel16 general aspects","SAES16",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 26/3/20: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-03-26"]
[2673,840018,"S6b Optional for ePDG connected to 5GS ","5GS_S6b_Optional",1,"Rel-16","S2","2019-05-09","2019-06-06",1,"SP-190447",null,"Irfan Ali, Cisco ","irfaali at cisco dot com ","6/6/19: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[2677,840008,"Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 ","ISAT-MO-WITHDRAW",1,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191151",null,"Dawes, Peter, Vodafone ","peter(dot)dawes(at)vodafone(dot)com ","; 13/9/19: 0%->100",24.323,84,43,null,null,"2019-05-31","2019-09-13"]
[2680,850025,"Network Slice Performance and Analytics Charging in 5G System ","5GS_NSPACH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190780",null,"Chen Shan, Huawei ","chenshan@huawei.com ","8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201",85,43,null,null,"2019-09-13","2020-09-13"]
[2683,850031,"Enhancement of 3GPP management system for multiple tenant environment support ","MEMTANE",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190786",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","28.531; 28.532; 28.533; 28.541; 28.552; 28.554 ",85,43,null,null,"2019-09-13","2020-06-28"]
[2684,850033,"Network Slice Management Charging in 5G System ","5GS_NSMCH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190788",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 8/10/19: 28.202 added;; 6/12/19: 0%->5; 28/6/20: 5%->50; 13/9/20: 50%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.202",85,43,null,null,"2019-09-13","2020-09-13"]
[2687,800044,"   Study on Load and Overload Control of 5GC Service Based Interfaces","FS_LOLC",2,"Rel-16","C4","2018-06-06","2019-06-14",1,"CP-181195",null,"Sridhar Bhaskaran (Huawei)","sridhar.bhaskaran@huawei.com","6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100","New; 22.943",80,41,null,null,"2018-06-06","2019-12-06"]
[2692,850005,"   C4 aspects of 5GS_OTAF","5GS_OTAF",2,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[2695,860017,"3GPP profiles for cryptographic algorithms and security protocols ","CryptPr",1,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191129",null,"Christine Jost, Ericsson ","christine.jost@ericsson.com ","; 25/3/20: 0%->100","33.210; 33.310; 33.501 ",86,44,null,null,"2019-12-06","2020-03-25"]
[2698,860023,"5G management capabilities ","5GMNC",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191195",null,"CORNILY, Jean-Michel, ORANGE ","jeanmichel.cornily@orange.com ","; 26/3/20: 0%->100",28.532,86,44,null,null,"2019-12-06","2020-03-26"]
[2702,860004,"Video enhancement of IMS CAT/CRS/announcement services ","eIMSVideo",1,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193149",null,"Hongxia Hao, Huawei ","haohongxia@huawei.com ","; 26/3/20: 0%->33; 26/6/20: 33%->100","24.182; 24.183; 24.628 ",86,44,null,null,"2019-12-06","2020-06-26"]
[2705,911002,"UE Conformance Test Aspects - Support of eCall over IMS for NR ","NR_EIEI-UEConTest",1,"Rel-16","R5","2021-03-12","2023-03-03",1,"RP-210704","RP-230094","Bharadwaj Kumar Cheruvu, Qualcomm","bcheruvu[at]qti.qualcomm.com","tested: REL-16 TEI CRs of SA2/CT1/R2; compare LTE REL-14 WI EIEI-UEConTest \"Evolution to and Interworking with eCall in IMS\" ; 2/7/21: 0%->5; 22/3/22: 20/6/22: Rapporteur: Qualcomm->Bharadwaj Kumar Cheruvu, Qualcomm; Rap eMail: ->bcheruvu[at]qti.q...;...",null,91,46,null,null,"2021-04-07","2023-03-17"]
[2708,800100,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446)","TEI16",2,"Rel-16","S3-IETF","2017-09-11","2017-09-11",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2712,800029,"Stopped - Study on system architecture for next generation real time communication services","FS_NG_RTC",1,"Rel-16","S2","2018-06-06","2019-03-14",1,"SP-180508",null,"Yi Jiang ","jiangyi at chinamobile dot com","03/22: stopped at 0% (\"deprioritised\"in SA2 language)","New",80,41,84,null,"2018-06-06","2022-03-22"]
[2713,790014,"Study on security aspects of single radio voice continuity from 5G to UTRAN","FS_5G_UTRAN_SEC",1,"Rel-16","S3","2018-03-15","2019-03-15",1,"SP-180209",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","27/3/18: 33.856 added;¦7/6/18: 0%->50¦10/9/18: 50%->79¦7/12/18: 79%->100",33.856000000000002,79,40,null,null,"2018-03-15","2018-12-07"]
[2717,800090,"Study on NR beyond 52.6 GHz","FS_NR_beyond_52GHz",1,"Rel-16","RP","2018-06-15","2018-09-14",1,"RP-181435",null,"Intel",null,"14/1/20: 0%->100","38.8xx",80,41,null,null,"2018-08-06","2020-01-14"]
[2720,801001,"Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR UEs","FS_NR_MIMO_OTA_test",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201069",null,"CAICT",null,"related REL-15 SI FS_NR_test_methods; 23/1/20: 0%->45; 23/1/20: WID:RP-181402->RP-182305; 28/7/20: WID:RP-182305->RP-201069; 28/7/20: 45%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2723,750046,"Study on Non-Orthogonal Multiple Access (NOMA) for NR","FS_NR_NOMA",1,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181403",null,"ZTE",null,"TR 38.8XX¦19/6/17: WID: RP-170829->RP-171043¦30/6/17: 32.812 added;¦27/6/18: Compl:0%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦27/6/18: WID: RP-171043->RP-181403;¦16/1/19: 40%->100",32.811999999999998,75,38,null,null,"2017-03-21","2019-01-16"]
[2727,820060,"Study on 7 - 24 GHz frequency range for NR","FS_7to24GHz_NR",1,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-192076",null,"Huawei",null,"TR. 38.8xx¦26/3/19: WID:RP-182884->RP-190373; 8/10/19: WID:RP-190373->RP-192076; 28/7/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[2730,840090,"Study on 5G NR UE Application Layer Data Throughput Performance","FS_UE_5GNR_App_Data_Perf",1,"Rel-16","R5","2019-06-17","2021-09-08",1,"RP-212470",null,"Qualcomm",null,"compare: REL-11 SI FS_UE_App_Data_Perf; TR 37.9xx. 07/2019: title changed from \"…UE 5G NR…\"; 8/10/19: 37.901-5 added;; 14/1/20: WID:RP-191590->RP-192712; 8/10/20: 0%->87; 8/10/20: FCD:13/03/2020->12/20; 6/1/21: WID:RP-192712->RP-202849; 7/4/21: WID:RP- ","37.901-5",84,43,null,null,"2019-06-26","2022-04-05"]
[2733,770003,"Study on enhancements to IMS for new real time communication services","FS_enIMS",1,"Rel-16","S1","2017-09-08","2017-12-15",1,"SP-170703",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","11/9/17: 0%->20¦15/12/17: 22.823 added;¦15/12/17: 20%->75¦16/3/18: 75%->100; 25/9/20: 26.998 added;","New; 22.823; 26.998",77,39,null,null,"2017-09-08","2020-09-25"]
[2737,800039,"Study on management aspects of edge computing","FS_MAN_EC",1,"Rel-16","S5","2018-06-06","2019-03-14",1,"SP-180390",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com","6/8/18: 28.803 added;¦10/9/18: 0%->10¦7/12/18: 10%->20¦14/3/19: 20%->50; 31/5/19: 50%->65; 13/9/19: 65%->100","New; 28.803",80,41,null,null,"2018-06-06","2019-09-13"]
[2738,750048,"Study on self-evaluation towards IMT-2020 submission","FS_5G_eval",1,"Rel-16","ITU-R AH,ITU-RAH","2016-12-14","2019-06-14",1,"RP-181318",null,"Huawei",null,"TR 38.9XX¦19/6/17: CD:Sat 15/09/18->Fri 15/06/18¦19/6/17: WID: RP-170832->RP-171451¦19/6/17: Release: Rel-16->Rel-15¦8/1/18: Compl:0%->15%27/3/18: Compl:15%->25%¦27/6/18: Compl:25%->35%¦27/6/18: CD:Fri 15/0; 26/6/19: 35%->100",null,75,38,null,null,"2017-03-21","2019-06-26"]
[2742,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[2745,850018,"Study on storage and transport of 5GC security parameters for ARPF authentication ","FS_5GC_SEC_ARPF",1,"Rel-16","S3","2019-09-19","2021-03-12",1,"SP-190708",null,"Evans, Timothy, Vodafone ","tim.evans1@vodafone.com ","; 8/10/19: 33.502 added;; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 30%->60; 12/9/20: 60%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->98; 11/6/21: ","New ; 33.502",85,43,null,null,"2019-09-13","2021-06-11"]
[2748,740005,"5G System - Phase 1","5GS_Ph1",1,"Rel-15",null,"2016-06-09","2019-06-14",0.97,"SP-160958",null,"China Mobile, Tao Sun","suntao@chinamobile.com","15/12/17: 23.503 added;",null,74,38,null,null,"2016-12-01","2017-12-15"]
[2752,750016,"   Security aspects of 5G System - Phase 1","5GS_Ph1-SEC",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-180693",null,"NTT DOCOMO, Alf Zugenmaier ","alf.zugenmaier@hm.edu","7/6/17: 0%->10¦11/9/17: 10%->30¦15/12/17: 30%->65¦21/12/17: WID:SP-170234->SP-170881¦16/3/18: 65%->85¦16/3/18: FCD:03/18->06/18¦7/6/18: 85%->95¦10/9/18: WID:SP-170881->100¦10/9/18: 95%->100¦2/10/18: WID:SP-170881->SP-180693","33.501; 33.401; 33.210; 33.310; 33.220",75,38,null,null,"2017-03-02","2018-10-02"]
[2755,750026,"      Studies on CT1 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15",null,"2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","18/12/17: WID:CP-172034->CP-173161","23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-12-18"]
[{"$f":"A2758+1","v":2758},770044,"         Study on 5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 35%->75¦15/12/17: 75%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[2760,770046,"         Study on 5G Interworking with EPC","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 15%->45¦15/12/17: 45%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[2763,780008,"      CT1 aspects of 5G System - Phase 1 (normative work)","5GS_Ph1-CT",3,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-09-08"]
[2767,780012,"         5G Non-3GPP access networks","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->95¦10/9/18: 95%->100",null,77,39,null,null,"2017-03-03","2018-09-10"]
[2770,780015,"         5G Network slicing","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[2773,750028,"      CT4 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C4","2017-03-03","2017-12-14",1,"CP-183243",null,"Landais, Bruno (Nokia)","Bruno.Landais at nokia.com","5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦7/6/18: 50%->95¦10/9/18: 95%->99¦10/12/18: 99%->100","23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303",75,38,null,null,"2017-03-03","2018-12-10"]
[2777,800081,"   UE Conformance Test Aspects – 5G System Non-3GPP Access","5GS_Ph1-CT_n3GPPA-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-181032",null,"Motorola",null,"tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2779,770017,"      CT1 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C1","2017-09-04","2018-06-15",1,"CP-180094",null,"Song Yue, China Mobile","songyue@chinamobile.com","14/9/17: 0%->10¦15/12/17: 10%->65¦rapporteur changed¦20/3/18: 65%->75¦7/6/18: 75%->95¦10/9/18: 95%->100","24.229; 24.167",77,39,null,null,"2017-03-03","2018-09-10"]
[2782,780034,"   Service Based Interface for 5G Charging","5GS_Ph1-SBI_CH",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170951",null,"Chen, Shan, Huawei","chenshan@huawei.com","16/3/18: 0%->15¦7/6/18: 15%->55¦7/6/18: FCD:06/18->09/18¦10/9/18: 55%->100","32.240; 32.298",78,40,null,null,"2017-12-15","2018-09-10"]
[2785,800040,"   Charging for IMS over 5G System Architecture Phase 1","5GS_Ph1_IMSCH",2,"Rel-15","S5","2018-05-07","2018-06-15",1,"SP-180391",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.240; 32.260; 32.299; 32.298",80,41,null,null,"2018-06-06","2018-06-07"]
[2788,750012,"   SA2 aspects of EDCE5","EDCE5",2,"Rel-15","S2","2017-03-02","2017-09-14",1,"SP-170583",null,"Chris Pudney, Vodafone Group",null,"7/6/17: 0%->55¦11/9/17: 55%->90¦15/12/17: 90%->100",null,75,38,null,null,"2017-03-02","2017-12-15"]
[2792,760069,"      CT3 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C3","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com",null,"29.212; 29.213; 29.214; 29.215; 29.201",76,39,null,null,"2017-06-05","NA"]
[2795,750067,"New Radio Access Technology","NR_newRAT",1,"Rel-15","R1","2017-03-15","2019-06-14",1,"RP-190213",null,"NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦30/6/17: 38.425 added;¦14/9/17: WID:RP-170855->RP-171485¦15/12/17: added: 38.305¦38.113¦37.863-04-01¦37.863-03-01¦37.863-02-01¦38.820-04-01¦38.820-03-01¦38.820-02-01¦15/12/17: 37.32 ","38.425; 38.424; 38.423; 38.422; 38.421; 38.420; 38.305; 38.113; 37.863-04-01; 37.863-03-01; 37.863-02-01; 38.820-04-01; 38.820-03-01; 38.820-02-01; 37.324; 37.872; 37.864-11-22; 37.866-00-02",75,38,null,null,"2017-03-21","2019-03-26"]
[2799,750172,"   Core part: LTE connectivity to 5G-CN","LTE_5GCN_connect-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",1,"RP-180860","RP-180862","Huawei",null,"no Perf. Part19/6/17: Compl:0%->5%19/6/17: WID: RP-170840->RP-17143219/9/17: Compl:5%->10%¦8/1/18: Compl:10%->20%¦27/3/18: Compl:20%->30%¦ ¦27/6/18: Compl:30%->99%¦7/3/19: 99%->100",null,75,38,null,null,"2017-03-21","2019-03-07"]
[2800,761205,"   Perf. part: LTE connectivity to 5G-CN","LTE_5GCN_connect-Perf",2,"Rel-15","R4","2017-06-20","2018-12-20",1,"RP-180860","RP-180862","Huawei",null,"16/1/19: 0%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2806,750075,"V2X new band combinations for LTE","LTE_V2X_CA_bands",1,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-170752",null,"LG Electronics",null,"no Perf. part¦12/7/17: 36.787 added;",36.786999999999999,75,38,null,null,"2017-03-21","2017-07-12"]
[2807,750175,"   Core part: V2X new band combinations for LTE","LTE_V2X_CA_bands-Core",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-180328",null,"LG Electronics",null,"no Perf. part¦19/6/17: Compl:0%->20%¦19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->50%¦27/3/18: Compl:50%->70%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2810,750262,"   Perf. Part: V2X phase 2 based on LTE","LTE_eV2X-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-182549",null,"Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #7519/6/17: WID: RP-170798->RP-17106919/9/17: WID: RP-171069->RP-171740¦27/6/18: Compl:0%->5%¦16/1/19: 5%->100¦16/1/19: WID:RP-171740->RP-182549",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2813,770037,"EPC support for E-UTRAN Ultra Reliable Low Latency Communication ","EPS_URLLC",1,"Rel-15","S2","2017-09-08","2018-03-15",1,"SP-170811",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","15/12/17: WID:SP-170797->SP-170811¦15/12/17: 0%->15¦20/3/18: 15%->100","23.401; 23.214; 23.203",77,39,null,null,"2017-09-08","2018-03-20"]
[2817,0,"Release 15 Features on improvements of Mission Critical (MC)","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2820,720083,"Study on MC Security Enhancements","FS_MC_Sec",1,"Rel-15","S3","2016-06-17","2018-03-15",1,"SP-170416",null,"Haigh, Peter, CESG","peter.haigh@cesg.gsi.gov.uk ","28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17","33.xxx; 33.280; 39.880",72,37,null,null,"2016-06-17","2018-03-16"]
[2825,770009,"   Stage 3 of enhMCPTT","enhMCPTT-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172030",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com","15/12/17: 0%->10¦7/6/18: 10%->20¦10/9/18: 20%->80¦7/12/18: 80%->85¦10/12/18: 85%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[2828,770011,"   Stage 3 of eMCData","eMCData-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172146",null,"HASON, Baruh","Baruh.Hason@motorolasolutions.com","20/3/18: 0%->30¦7/6/18: 30%->85¦10/12/18: 85%->100","24.282; 24.582; 24.481; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[2831,770013,"   Stage 3 of eMCVideo","eMCVideo-CT",2,"Rel-15","ct","2017-09-08","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","7/6/18: WID:CP-172032->CP-181084",null,77,39,null,null,"2017-06-03","2018-06-07"]
[2832,770014,"      CT1 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","20/3/18: 0%->25¦7/6/18: 25%->100¦12/6/18: 100%->99¦10/9/18: 99%->100","24.281; 24.581; 24.481; 24.483; 24.484",77,39,null,null,"2017-06-03","2018-09-10"]
[2835,760067,"MC Security Enhancements","eMCSec",1,"Rel-15","S3","2017-06-05","2018-06-15",1,"SP-170415",null,"Haigh, Peter, NCSC",null,"15/12/17: 0%->80¦15/12/17: FCD:12/17->03/18¦21/12/17: FCD:03/18->05/18. Exception in SP-171056¦16/3/18: 80%->90¦16/3/18: FCD:05/18->06/18¦7/6/18: 90%->100",33.18,76,39,null,null,"2017-06-07","2018-06-07"]
[2838,800017,"   Stage 3 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","C1","2018-04-09","2018-06-07",1,"CP-183105",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","12/6/18: 10%->30¦10/9/18: 30%->70¦7/12/18: 70%->100","24.281; 24.282; 24.379; 24.380; 24.581; 24.380",80,41,null,null,"2018-06-06","2018-12-10"]
[2842,0,"Release 15 Features on MTC-IoT","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2846,750159,"   Core part: Even further enhanced MTC for LTE","LTE_eMTC4-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",1,"RP-172811","RP-181213","Ericsson",null,"WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦19/6/17: Compl:0%- 19/9/ 8/1 2 ;¦16/1/19: 97%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[2850,750166,"   Core part: Further NB-IoT enhancements","NB_IOTenh2-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.95,"RP-182389","RP-180851","Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[2853,0,"Release 15 Features related to WLAN","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2856,750011,"   Stage 2 of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage2",2,"Rel-15","S2","2017-03-02","2017-06-15",1,"SP-170057",null,"Intel, Sašo Stojanovski ","saso.stojanovski@intel.com","6/3/17: 0%->55¦7/6/17: 55%->100",null,75,38,null,null,"2017-03-02","2017-06-07"]
[2857,760026,"   Stage 3 of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",2,"Rel-15","ct","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","18/12/17: WID:CP-171102->CP-173084",null,76,39,null,null,"2017-06-02","2017-12-18"]
[2860,780045,"   Charging of ProSe_WLAN_DD","ProSe_WLAN_DD-CH",2,"Rel-15","S5","2017-12-15","2018-03-15",1,"SP-170947",null,"Yizhi Yao, Intel Corporation ","yizhi.yao@intel.com","15/12/17: 0%->40¦16/3/18: 40%->100","32.277; 32.298; 32.299",74,38,null,null,"2016-12-01","2018-03-16"]
[2864,760022,"   CT aspects of VoWLAN","VoWLAN-CT",2,"Rel-15","ct","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: WID:CP-171101->CP-181083",null,76,39,null,null,"2017-06-02","2018-06-07"]
[2867,760025,"      CT6 aspects of VoWLAN","VoWLAN-CT",3,"Rel-15","C6","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: 0%->100",31.102,76,39,null,null,"2017-06-02","2018-06-07"]
[2871,770022,"Test Methodologies for the Evaluation of Perceived Listening Quality in Immersive Audio Systems","LiQuImAS",1,"Rel-15","S4","2017-09-08","2018-09-14",1,"SP-170609",null,"Schevciw, Andre – Qualcomm Incorporated ","aschevci@qti.qualcomm.com","15/12/17: added: 26.861¦26.261¦26.260¦26.259¦15/12/17: 0%->15¦16/3/18: 15%->20¦7/6/18: 20%->35¦7/6/18: FCD:06/18->09/18¦10/9/18: 35%->100","New; 26.861; 26.261; 26.260; 26.259",77,39,null,null,"2017-09-08","2018-09-10"]
[2875,790016,"Forward compatibility for 3GPP Diameter Charging Applications","FWDCA",1,"Rel-15","S5","2018-03-15","2018-06-15",1,"SP-180076",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.251; 32.277; 32.299",79,40,null,null,"2018-03-15","2018-06-07"]
[2878,790020,"FEC and ROHC Activation for GCSE over MBMS","FRASE",1,"Rel-15","S4","2018-03-15","2018-09-14",1,"SP-180206",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd","i.bouazizi@samsung.com.","7/6/18: 0%->30¦7/6/18: FCD:06/18->09/18¦10/9/18: 30%->100","26.346; new",79,40,null,null,"2018-03-15","2018-09-10"]
[2881,790026,"   CT1 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C1","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","16/3/18: 0%->80¦7/6/18: 80%->100","24.237; 24.008",79,40,null,null,"2018-03-16","2018-06-07"]
[2882,790027,"   CT3 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","22/3/18: 0%->95¦10/9/18: 95%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[2885,790036,"   Stage 3 of INOBEAR","INOBEAR-CT",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com",null,null,79,40,null,null,"2017-12-15","NA"]
[2888,780070,"Increased number of E-UTRAN data bearers","INOBEARRAN",1,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-172835",null,"Samsung",null,null,null,78,40,null,null,"2018-01-08","2018-01-08"]
[2893,710047,"   Stage 1 for REAR","REAR",2,"Rel-15","S1","2016-03-01","2016-06-15",1,"SP-160511",null,"Huawei, Laurence Meriau","laurence.meriau@huawei.com","Previously known as \"wearable devices\"¦9/6/16: 0%->100¦9/6/16: WID:SP-160231->SP-160371¦15/12/17: moved Rel-14->Rel-15","22.278; 22.115",71,36,null,null,"2016-03-11","2017-12-15"]
[2896,780044,"   CT aspects on enhanced VoLTE performance","eVoLP-CT",2,"Rel-15",null,"2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com",null,null,78,40,null,null,"2017-12-15","NA"]
[2900,740006,"      S2 aspects of FS_eVoLP","FS_eVoLP",3,"Rel-15","S2","2016-12-01","2017-09-14",1,"SP-160833",null,"Xiaobo Wu ",null,"1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100¦15/12/17: rapporteur changed",23.759,74,38,null,null,"2016-12-01","2017-12-15"]
[2903,740008,"   Study on unlicensed spectrum offloading system enhancements","FS_USOS",2,"Rel-15","S2","2016-12-01","2017-06-15",1,"SP-160835",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100",23.728999999999999,74,38,null,null,"2016-12-01","2017-09-11"]
[2904,770006,"   Stage 1 of USOS","USOS",2,"Rel-15","S1","2016-02-01","2016-03-01",1,"SP-160117","SP-170526","Edward Hall, Qualcomm Incorporated","edhall@qti.qualcomm.com",null,"22.101; 22.115",71,36,null,null,"2016-03-01","2016-03-01"]
[2907,750007,"Mobile Communication System for Railways","MONASTERY",1,"Rel-15",null,"2016-06-09","2018-06-15",1,"SP-170163",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com",null,null,75,38,null,null,"2017-03-02","NA"]
[2913,790032,"      CT1 aspects of MONASTERY","MONASTERY",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","16/3/18: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","24.379; 24.380; 24.481; 24.483; 24.484",79,40,null,null,"2018-03-16","2018-09-10"]
[2915,790034,"      Stopped - CT6 aspects of MONASTERY","MONASTERY",3,"Rel-15","C6","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","10/9/18: 0%->100","31.102; 31.103",79,40,84,null,"2018-03-16","2018-09-10"]
[2918,750008,"   Stage 2 of PS Data Off Phase 2 ","PS_DATA_OFF2",2,"Rel-15","S2","2017-03-02","2017-12-15",1,"SP-170246",null,"Murhammer, Leopold, Deutsche Telekom AG","leopold.murhammer@t-mobile.at","7/6/17: 0%->10¦11/9/17: 10%->85¦15/12/17: 85%->100¦15/12/17: FCD:09/17->12/17",null,75,38,null,null,"2017-03-02","2017-12-15"]
[2921,760033,"      CT4 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->100","29.272; 29.274; 29.328; 29.329; 29.228; 29.229; 23.008",76,39,null,null,"2017-06-02","2017-12-15"]
[2925,780006,"   Stage 3 of NAPS","NAPS-CT",2,"Rel-15","C3","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90. 18/12/17: WID corrected¦18/12/17: WID:CP-171143 ->CP-173112","29.336; 29.128; 29.230",78,40,null,null,"2017-06-02","2017-12-18"]
[2928,770032,"   Security aspects of NAPS","NAPS-Sec",2,"Rel-15","S3","2017-09-08","2018-03-16",1,"SP-170635",null,"Zhao, Xuwen, Huawei","zhaoxuwen@huawei.com ","15/12/17: 0%->60¦16/3/18: 60%->100",33.186999999999998,77,39,null,null,"2017-09-08","2018-03-16"]
[2929,760063,"   Carging aspects of NAPS","NAPS-CH",2,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170488",null,"Chen, Shan, Huawei","chenshan@huawei.com","30/6/17: 32.254 added;¦11/9/17: 0%->10¦15/12/17: 10%->20¦16/3/18: 20%->50¦7/6/18: 50%->100","New TS; impact 32.240; 32.298; 32.299; 32.254",76,39,null,null,"2017-06-05","2018-06-07"]
[2934,780024,"   Security aspects of CAPIF","CAPIF-Sec",2,"Rel-15","S3","2017-12-15","2018-06-14",1,"SP-171051",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","16/3/18: 0%->40¦7/6/18: 40%->100",null,78,40,null,null,"2017-12-15","2018-06-07"]
[2936,780056,"   General aspects of NETSLICE","NETSLICE",2,"Rel-15","S5","2016-06-13","2018-09-14",1,"SP-180816",null,"Jan Groenendijk, Ericsson","jan<dot>groenendijk<at>ericsson<dot>com","21/12/17: created from the Feature level, since SP-170960 contains its own specs and completions¦16/3/18: 46%->60¦7/6/18: 60%->85¦7/6/18: FCD:06/18->09/18¦8/8/18: WID:SP-170960->SP 180124¦10/9/18: 85%->100","32.101; 32.103; 28.530",76,39,null,null,"2017-06-05","2018-09-10"]
[2940,780037,"   Network Resource Model (NRM) for 5G networks and network slicing","NETSLICE-5GNRM",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180812",null,"Nokia (Jing Ping","jing.ping@nokia-sbell.com","16/3/18: 0%->25¦7/6/18: 25%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170956->SP-180812","28.657; 28.658; 28.659; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-10-02"]
[2943,780040,"   5G Trace management","NETSLICE-5GTRACE",2,"Rel-15","S5","2017-12-15","2018-06-07",1,"SP-170959",null,"Nokia (Anatoly Andrianov","anatoly.andrianov@nokia.com","7/6/18: 0%->100","32.421; 32.422; 32.423; 32.441; 32.442; 32.446",78,40,null,null,"2017-12-15","2018-06-07"]
[2946,810043,"      CT4 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C4","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274",81,41,null,null,"2018-09-06","2018-09-10"]
[{"$f":"A2950+1","v":2950},740057,"      CT3 aspects of FS_PC_VBC","FS_PC_VBC",3,"Rel-15","C3","2016-12-01","2017-12-15",1,"CP-172135",null,"Huang, Zhenning, China Mobile","huangzhenning <at> chinamobile <dot> com","6/3/17: 0%->30¦21/3/17: 29.827 added;¦5/6/17: 30%->60¦8/9/17: WID:CP-160822->CP-172058¦11/9/17: FCD:06/17->12/17¦15/12/17: 60%->61¦15/12/17: 61%->100",29.827000000000002,74,38,null,null,"2016-12-01","2017-12-15"]
[2953,790041,"   CT3 aspects of PV_VBC","PC_VBC",2,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-180051",null,"Huang Zhenning (China Mobile)","huangzhenning (at) chinamobile (dot) com","7/6/18: 0%->100","29.212; 29.213; 29.214",79,40,null,null,"2018-03-16","2018-06-07"]
[2955,770034,"Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management","OAM_SON_AAS",1,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170658",null,"Nokia (Weixing Wang)","weixing.wang@nokia-sbell.com","15/12/17: 0%->80¦10/9/18: 80%->100","28.627; 28.628; 28.629; 28.658; 28.659",77,39,null,null,"2017-09-08","2018-09-10"]
[2958,780036,"Management Enhancement for EPC CUPS ","ME_CUPS",1,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170954",null,"Huawei (ZHU, Lei","lei.zhu@huawei.com","ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14¦16/3/18: 0%->5¦7/6/18: 5%->60¦10/9/18: 60%->100","32.426; 32.455; 28.658; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-09-10"]
[2961,730006,"   Stage 1 of eCNAM","eCNAM",2,"Rel-15","S1","2016-09-15","2016-12-15",1,"SP-160548",null,"Hala Mowafy, Ericsson",null,"1/12/16: 0%->100¦30/6/17: 24.196 added;","22.173; 24.196",73,37,null,null,"2016-09-19","2017-06-30"]
[2965,750001,"Enhancement of background data transfer","eBT",1,"Rel-15","S1","2017-01-16","2017-03-08",1,"SP-170161",null,"Atsushi Minokuchi, NTT DOCOMO","minokuchi at nttdocomo dot com",null,22.100999999999999,75,38,null,null,"2017-03-02","NA"]
[2968,760018,"   SAES6 for support for non-3GPP accesses","SAES6-non3GPP",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","2018-06-07"]
[2972,750005,"HPLMN Radio Access Technology deployment Optimisation in Network Selection","HORNS",1,"Rel-15","S1","2017-03-02","2017-06-15",1,"SP-170277",null,"Eddy Hall, Qualcomm Incorporated","edhall@qti.qualcomm.com ","7/6/17: 75%->100",null,75,38,null,null,"2017-03-02","2017-06-07"]
[2975,760010,"   (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C1-IETF","2017-06-02","2020-04-23",0.99,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com",null,null,76,39,null,null,"2014-12-04","NA"]
[2978,870065,"      (IETF) Update to Private Header Field P-Visited-Network-ID in Session Initiation Protocol (SIP) Requests and Responses (draft-jesske-update-p-visited-network)","IMSProtoc8",3,"Rel-15","C1-IETF","2020-01-08","2020-04-23",1,null,null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,87,44,null,null,"2020-04-23","NA"]
[2980,750014,"Lawful Interception Rel-15","LI15",1,"Rel-15",null,"2017-03-02","2019-03-12",1,"SP-170839",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","21/12/17: WID:SP-170039->SP-170839¦16/3/18: 10%->20",null,75,38,null,null,"2016-07-27","2018-03-16"]
[2983,750068,"DL interference mitigation for UMTS","UTRA_DL_IM",1,"Rel-15","R2","2017-03-15","2017-06-15",1,"RP-170703",null,"Qualcomm",null,"no Perf. part",null,75,38,null,null,"2017-03-21","2017-03-21"]
[2986,760082,"Simplified HS-SCCH for UMTS","UTRA_simple_HSSCCH",1,"Rel-15","R6","2017-03-15","2017-12-15",1,"RP-171443",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[2990,780020,"Receive acoustic output test in the presence of background noise","RAOT",1,"Rel-15","S4","2017-12-15","2018-06-15",1,"SP-170835",null,"ISBERG, Peter, Sony Mobile Communications","peter.isberg [at] sony.com","16/3/18: 0%->80¦16/3/18: FCD:03/18->06/18¦7/6/18: 80%->100","26.131; 26.132",78,40,null,null,"2017-12-15","2018-06-07"]
[2993,730057,"   Study on a RESTful HTTP-based Solution Set","FS_OAM_RESTFUL",2,"Rel-15","S5","2016-09-19","2017-12-12",1,"SP-160613",null,"Nokia: Pollakowski, Olaf","olaf.pollakowski@nokia.com","6/10/16: 32.866 added¦1/12/16: 0%->5¦7/6/17: 5%->45¦7/6/17: FCD:06/17->12/17¦11/9/17: 45%->80¦15/12/17: 80%->100",32.866,73,37,null,null,"2016-09-19","2017-12-15"]
[2997,800116,"   (IETF) JSON Hyper-Schema: A Vocabulary for Hypermedia Annotation of JSON (draft-handrews-json-schema-hyperschema)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",0,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com",null,null,80,41,null,null,"2018-07-10","NA"]
[3000,800101,"   (IETF) PASSporT SHAKEN Extension (draft-ietf-stir-passport-shaken)--> RFC 8588","eSPECTRE",2,"Rel-15","C1-IETF","2018-06-14","2018-09-14",1,null,null,"Axell, Jörgen, Ericsson",null,"23/4/20: 25%->100",null,80,41,null,null,"2018-06-27","2020-04-23"]
[3001,870073,"   (IETF) PASSporT Extension for Diverted Calls (draft-ietf-stir-passport-divert) ","eSPECTRE",2,"Rel-15","C1-IETF","2019-03-07","2019-03-07",1,null,null,null,null,"9/4/21: RFC 8946 added;","RFC 8946",87,44,null,null,"2020-04-23","2021-04-09"]
[3005,750034,"(Small) Test Technical Enhancements and Improvements for Rel-15","TEI15_Test",1,"Rel-15",null,"2017-03-17","2017-12-15",1,"-",null,"-","-","Created upon demand of RAN5","-",75,38,null,null,"2015-01-12","2016-02-24"]
[3008,770167,"   Core part: UL data compression in LTE ","LTE_UDC-Core",2,"Rel-15","R2","2000-01-03","2018-09-14",0.99,"RP-180914","RP-180912","CATT",null,"¦8/1/18: Compl:0%->70%¦8/1/18: CD:Mon 03/01/00->Thu 15/03/18¦27/3/18: Compl:70%->99%27/3/1 ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18;",null,77,39,null,null,"2017-09-19","2018-06-27"]
[3011,770168,"   Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Core",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"15/12/17: 36.715-04 added;¦8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%;","36.715-04",77,39,null,null,"2017-09-19","2018-03-27"]
[3015,770269,"   Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-Perf",2,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-180262",null,"Ericsson",null,"¦27/3/18: Compl:0%->99% ¦27/6/18: Compl:99%->100%",null,77,39,null,null,"2017-09-19","2018-06-27"]
[3018,770071,"Extended-Band12 new E-UTRA Band","Ext_B12_LTE",1,"Rel-15","R4","2017-09-15","2019-05-31",1,"RP-172111",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[3022,710073,"Stopped - Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON",1,"Rel-15",null,"2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459",null,71,36,80,null,"2016-03-22","2017-09-14"]
[3026,740046,"      Stopped - CT1 aspects of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",3,"Rel-15","C1","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->25¦11/9/17: 25%->0","24.008; 24.301; 29.118; 24.368; 27.007",74,38,80,null,"2016-12-01","2017-09-11"]
[3029,710074,"Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA",1,"Rel-15",null,"2016-03-15","2018-09-14",0.71,"RP-161668",null,"Huawei",null,"follow-up WI of REL-13 WI AAS_BS_LTE_UTRA¦14/9/17: WID:RP-160548->RP-161668",37.843000000000004,71,36,null,null,"2016-03-22","2017-09-14"]
[3030,710174,"   Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA-Core",2,"Rel-15","R4","2016-03-15","2017-12-15",1,"RP-171745","RP-172345","Huawei",null,"follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/1726/9/16: Compl:5%->10% 20/12/16: Compl:10%->20%21/3/17: Compl:20%->40% ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3033,720191,"   Core part: Shortened TTI and processing time for LTE","LTE_sTTIandPT-Core",2,"Rel-15","R1","2016-06-15","2018-09-14",0.99,"RP-171468","RP-181008","Ericsson",null,"26/9/16: Compl:0%->5%¦20/12/16: Compl:5%->10%21/3/17: Compl:10%->30%19/6/17: Compl:30%->65%19/6/17: CD: 19/9/17: Compl:65%->75%¦8/1/18: Compl:75%->99%¦8/1/18: CD:Fri 15/12/17->F ¦27/6/18: CD:Fri 15/06/1",null,72,37,null,null,"2016-07-01","2018-06-27"]
[3037,740172,"   Core part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-162514",null,"Airbus",null,"21/3/17: Compl:0%->10%¦19/6/17: Compl:10%->75%¦19/9/17: Compl:75%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3040,740074,"E-UTRA 700MHz in Europe for Broadband-PPDR (Public Protection and Disaster Relief)","LTE700_Europe_PPDR",1,"Rel-15",null,"2016-12-15","2018-03-15",0.83,"RP-162534",null,"Airbus",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[3043,770066,"   UE Conformance Test Aspects - E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180529",null,"Airbus",null,"¦8/1/18: Compl:0%->64%27/3/18: Compl:64%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3047,780062,"   UE Conformance Test Aspects - FDD operating band in the L-band for LTE","LTE_FDD_L_band-UEConTest",2,"Rel-15","R5","2017-12-15","2018-09-14",1,"RP-180145",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ;; 11/10/20: 60%->100",null,78,40,null,null,"2018-01-08","2020-10-11"]
[3051,740077,"Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2",1,"Rel-15",null,"2016-12-15","2018-12-14",1,"RP-162571",null,"Sprint",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[3054,730081,"Addition of Power Class 1 UE to bands B3/B20/B28 for LTE","LTE_HPUE_B3_B20_B28",1,"Rel-15",null,"2016-09-15","2017-09-15",1,"RP-161871",null,"Motorola Solutions",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3055,730181,"   Core part: Addition of Power Class 1 UE to bands B3/B20/B28 for LTE","LTE_HPUE_B3_B20_B28-Core",2,"Rel-15","R4","2016-09-15","2017-09-15",1,"RP-171757",null,"Motorola Solutions",null,"¦20/12/16: Compl:0%->15%¦20/12/16: CD:Wed 15/03/17->Thu 15/06/1721/3/17: Compl:15%->70%19/6/17: Compl:70%->99%19/9/17: Compl:99%->100%;",null,73,37,null,null,"2016-09-26","2017-09-19"]
[3058,740280,"   Perf. part: TDD operating band in the L-band for LTE","LTE_TDD_L_Band-Perf",2,"Rel-15","R4","2017-03-17","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: WID: RP-162557->RP-170304¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17¦19/9/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3062,750063,"UE Positioning Accuracy Enhancements for LTE","LCS_LTE_acc_enh",1,"Rel-15","R2","2017-03-15","2018-09-14",1,"RP-171508",null,"Nokia",null,"14/9/17: WID:RP-170813->RP-171508",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3065,750064,"Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL",1,"Rel-15","R1","2016-09-14","2018-12-14",0.99,"RP-171067",null,"Huawei",null,"14/9/17: WID:RP-170838->RP-171067",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3068,750065,"Enhancements to LTE operation in unlicensed spectrum","LTE_unlic",1,"Rel-15","R1","2017-03-15","2018-12-14",0.99,"RP-180402",null,"Nokia",null,"note: The is actually a further LAA enhancement",null,75,38,null,null,"2017-03-21","2017-03-21"]
[3073,750070,"Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming",1,"Rel-15","R2","2017-03-15","2018-12-14",0.99,"RP-170786",null,"China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core",null,75,38,null,null,"2017-03-21","2017-03-21"]
[3076,750071,"Enhancing LTE CA Utilization","LTE_euCA",1,"Rel-15","R2","2017-03-15","2021-09-08",0.97,"RP-170805",null,"Nokia",null,null,null,75,38,null,null,"2017-03-21","2017-03-21"]
[3077,750171,"   Core part: Enhancing LTE CA Utilization","LTE_euCA-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.9,"RP-180561","RP-181069","Nokia",null,"19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3080,750073,"450 MHz Band for LTE in Region 3","LTE450_Reg3",1,"Rel-15","R4","2017-03-15","2019-03-15",1,"RP-170952",null,"China Unicom",null,"14/9/17: WID:RP-170159->RP-170952",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3083,790058,"   UE Conformance Test Aspects - 450 MHz Band for LTE in Region 3","LTE450_Reg3-UEConTest",2,"Rel-15","R5","2018-03-15","2019-03-15",1,"RP-181040",null,"China Unicom, Shi Yu ",null,"¦27/6/18: Compl:0%->5%;; 14/1/20: 5%->100","34.121-1; 36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1; 36.905",79,40,null,null,"2018-04-19","2020-01-14"]
[3087,770060,"   UE Conformance Test Aspects - US 600 MHz Band for LTE (Band 71)","LTE600_US-UEConTest",2,"Rel-15","R5","2017-09-15","2017-12-15",1,"RP-172195",null,"Dish Network",null,"¦8/1/18: Compl:0%->100%¦",null,77,39,null,null,"2017-09-19","2018-01-08"]
[3089,750176,"   Core part: LAA/eLAA for the CBRS 3.5GHz band in the United States","LTE_3550_CBRS_US_LAA-Core",2,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-172626",null,"AT&T",null,"compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2;19/6/17: Com¦Acronym changed, was \"LTE_TDD_3550_CBRS_US_LAA-Core\"¦12/7/17: 36.790 added;;",36.79,75,38,null,null,"2017-03-21","2018-01-08"]
[3094,760098,"Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40",1,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3098,850061,"   UE Conformance Test Aspects – LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-UEConTest",2,"Rel-15","R5","2019-09-19","2021-06-11",1,"RP-192116",null,"Huawei",null,"8/10/20: 0%->50; 8/10/20: FCD:15/09/2020->12/20; 8/4/21: 50%->98; 8/4/21: FCD:11/12/2020->06/21; 2/7/21: 98%->100",null,85,43,null,null,"2019-10-08","2021-07-02"]
[3101,761200,"   Perf. part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Perf",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"¦19/9/17: WID: RP-171506->RP-171759¦27/3/18: Compl:0%->100%;",null,76,39,null,null,"2017-06-16","2018-03-27"]
[3102,761001,"UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM",1,"Rel-15","R4","2017-06-15","2018-12-14",0.93,"RP-171408",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3105,780068,"Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN",1,"Rel-15","R2","2017-12-15","2019-12-15",0.98,"RP-172820",null,"CMCC",null,"MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3108,780069,"Enhanced LTE Support for Aerial Vehicles","LTE_Aerial",1,"Rel-15","R2","2017-03-15","2019-06-19",0.99,"RP-172826",null,"Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3114,780072,"UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172842",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3116,780272,"   Perf. part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-180960",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL¦27/6/18: Compl:0%->30%¦26/3/19: 30%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3119,810063,"   UE Conformance Test Aspects - ProSe Support for Band 72 in LTE","LTE450_B72_Europe_ProSe-UEConTest",2,"Rel-15","R5","2018-09-14","2018-12-14",1,"RP-181630",null,"Airbus",null,"16/1/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-01-16"]
[3123,761002,"Performance requirements of interference cancellation receiver for LTE BS","LTE_IC_BS",1,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171411",null,"China Telecom",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3126,761203,"   Perf. part: LTE CRS-Interference Mitigation performance requirements for single RX chain UEs","LTE_1RX_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-N1122",null,"Intel",null,"¦19/9/17: Compl:0%->20%¦19/9/17: WID: RP-171465->RP-171831¦8/1/18: Compl:20%->60%¦27/3/18: Compl:60%->85%¦27/6/18: Compl:85%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3127,760090,"LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170962",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3130,760091,"LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171026",null,"Qualcomm",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3135,760292,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180955",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3138,760293,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"19/9/17: Compl:0%->54%¦ 8/1/18: Compl:54%->65%¦27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3141,760294,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL","LTE_CA_R15_5DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180743",null,"Nokia",null,"¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->75%¦ ¦27/6/18: Compl:75%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3145,760096,"LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170946",null,"LG Electronics",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3148,770064,"UE Conformance Test Aspects – Rel-15 CA configurations","LTE_CA_R15-UEConTest",1,"Rel-15","R5","2017-09-15","2022-12-01",1,"RP-171886","RP-222814","Leif MATTISSON, Ericsson","Leif[dot]mattisson[at]ericsson[dot]com","¦8/1/18: Compl:0%->7%¦27/3/18: Compl:7%->8% ;; 8/10/20: 9%->22; 8/10/20: FCD:14/06/2019->12/20; 8/4/21: FCD:11/12/2020->09/21; 8/4/21: 22%->22; 2/7/21: FCD:Wed 08/09/->03/22; 2/7/21: 22%->24; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Er...;...",null,77,39,null,null,"2017-09-19","2023-01-09"]
[3151,630011,"   Stopped - Test part: LTE UE TRP and TRS and UTRA Hand Phantom","LTE_UTRA_TRP_TRS-UEConTest",2,"Rel-15","R5","2014-03-15","2017-12-15",0.78,"RP-150070",null,"ZTE","TAYLOR Carolyn (carolyn.tayl@zte.com.cn)","Stat Rep: RP-141132->RP-141848¦Rel 12->Rel13 1st Apr 15: Compl:15%->20% 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: WID: RP-140090->RP-150070 1st Apr 15: Stat Rep: RP-141848->RP-150069 03/07/15: Compl:20%->25% 03/07/15: Stat Rep: RP-150069->","New 37.544 ",63,32,80,null,"2014-03-04","2018-01-08"]
[3152,790053,"Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh",1,"Rel-15","R6","2018-03-15","2018-09-14",0.9,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh",null,79,40,null,null,"2018-03-27","NA"]
[3156,790156,"   Core part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5","LTE_CA_R15_xDL3UL-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-181311",null,"KDDI",null,"basket CA WI¦no Perf. part¦27/6/18: Compl:0%->100%¦…",null,79,40,null,null,"2018-03-27","2018-06-27"]
[3159,790155,"   Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-180688",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16",null,79,40,null,null,"2018-03-27","2018-06-27"]
[3163,730056,"Study on management aspects of virtualized network functions that are part of the NR","FS_MA_RNVNF",1,"Rel-15","S5","2016-09-19","2017-12-15",1,"SP-160703",null,"Intel (Joey Chou","joey.chou@intel.com","6/10/16: Acronym FS_MA_RVNF ->FS_MA_RNVNF ¦6/10/16: 32.864 added¦1/12/16: 0%->5¦6/3/17: 5%->10¦7/6/17: 10%->40¦11/9/17: 40%->70¦15/12/17: 70%->100¦15/12/17: FCD:09/17->12/17",32.863999999999997,73,37,null,null,"2016-09-19","2017-12-15"]
[3166,710045,"STOPPED AT SA#77 - SA3 aspects on Study on Architecture and Security for Next Generation System","FS_NSA",1,"Rel-15","S3","2016-03-01","2017-12-12",1,"SP-160727",null,"Vesa Torvinen, Ericsson","vesa.torvinen@ericsson.com","19/9/16: 0%->25¦22/9/16: WID:SP-160227->SP-160727¦22/9/16: FCD:12/16->03/17¦1/12/16: 25%->45¦6/3/17: 45%->60¦7/6/17: FCD:03/17->12/17 so Rel-14->Rel-15¦7/6/17: 60%->65¦11/9/17: 65%->100",33.899000000000001,71,36,null,null,"2016-03-01","2017-09-11"]
[3170,730070,"Study on interference cancellation receiver for LTE BS","FS_LTE_IC_BS",1,"Rel-15","R4","2016-09-15","2017-06-15",1,"RP-161485",null,"China Telecom",null,"6/10/16: 36.766 added¦20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%¦19/6/17: Compl:65%->100%",36.765999999999998,73,37,null,null,"2016-09-26","2017-06-19"]
[3173,0,"Other Release 15 Studies","-",1,"Rel-15",null,"2017-09-08","2018-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3176,710049,"Study on Energy Efficiency Aspects of 3GPP Standards","FS_ENEFF",1,"Rel-15","SP","2016-03-11","2017-06-09",1,"SP-160224","_SP-170533","Orange, Xiaobao Chen","xiaobao.chen@orange.com","28/7/16: 21.866 added;¦9/6/17: FCD:12/16->9/6/17 (Rel-14->Rel-15)¦0%->100",21.866,71,36,null,null,"2016-03-11","2017-06-09"]
[3177,750049,"Study on evaluation methodology of new V2X use cases for LTE and NR","FS_LTE_NR_V2X_eval",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171093",null,"LG Electronics",null,"TR 38.8XX19/6/17: WID: RP-170837->RP-171093¦12/7/17: 37.885 added;19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->10%¦8/1/18: CD:Fri 15/12/17->Thu 15/03/18¦27/3/18: Compl:10%->30%¦27/3/18: CD:Thu 15/03/18->Fri 15/06/18¦27/",37.884999999999998,75,38,null,null,"2017-03-21","2018-06-27"]
[3181,720041,"Study on Technical Requirements for a new secure platform for 3GPP applications","FS_NG_SP",1,"Rel-15","C6","2016-06-13","2017-09-12",1,"CP-160371",null,"Heiko Kruse","heiko.kruse@safrangroup.com","16/9/16: 0%->15. ¦5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet)¦5/6/17: FCD:12/16->09/20¦15/12/17: 70%->100",31.800999999999998,72,37,null,null,"2016-06-13","2017-12-15"]
[3185,590045,"Study on Enhanced Acoustic Test Specifications","FS_SEATS",1,"Rel-15","S4","2013-03-18","2017-12-12",1,"SP-130028","-","Knowles, Intel","Scott Isabelle (Knowles), David Isherwood (Intel)","SP#65 completion 09/14=>12/14. Moved to Rel-13. Dec.14: 30->35%, CD 12/14->03/15. Mar.15: CD: 06/16. 40%¦June2015: Compl:40%->45. . 15/4/16: moved from R 21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: FCD:06/17->12/17¦11/9/17: 80%->8",26.931000000000001,59,30,null,null,"2013-02-20","2017-12-15"]
[3188,730055,"Study on Management aspects of selected IoT-related features","FS_OAM_IOT",1,"Rel-15","S5","2016-09-19","2017-12-12",1,"SP-160611",null,"Cisco Systems / Yanover, Vladimir ",null,"6/10/16: 32.857 added¦1/12/16: 0%->5¦21/3/17: moved from Rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 5%->20¦11/9/17: 20%->30¦15/12/17: 30%->45¦16/3/18: 45%->100",32.856999999999999,73,37,null,null,"2016-09-19","2018-03-16"]
[3191,680054,"Study on Overload Control for Diameter Charging Applications","FS_DOCME_CH",1,"Rel-15","S5","2015-06-18","2017-12-15",1,"SP-170481",null,"GUO Wenjie, ZTE","guo.wenjie1@zte.com.cn","Aug2015: moved to Rel-14 (email CT and EG)¦07/09/15: 0%->5¦7/3/16: 5%->10¦13/6/16: FCD:03/16->09/16¦19/9/16: FCD: 09/16->06/17¦6/3/17: FCD:03/17->12/17¦21/3/17: moved from rel-14¦7/6/17: 10%->25¦8/6/17: WID:SP-150310->SP-170481¦11/9/17: 25%->3","New 32.869",68,35,null,null,"2015-06-26","2017-12-15"]
[3195,720047,"Study on Management and Orchestration Architecture of Next Generation Network and Service","FS_NGNS_MOA",1,"Rel-15","S5","2016-06-13","2017-12-12",1,"SP-160400",null,"Huawei Technologies, Zou Lan","zoulan@huawei.com","28/7/16: 28.800 added¦19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 10%->25¦11/9/17: 25%->30¦15/12/17: 30%->100","xy.abc; 28.800",72,37,null,null,"2016-06-13","2017-12-15"]
[3198,760060,"Study on Volume Based Charging Aspects for VoLTE ","FS_VBCLTE",1,"Rel-15","S5","2017-06-05","2018-06-14",1,"SP-170594",null,"Chen, Ai, China Mobile","chenai@chinamobile.com ","30/6/17: 32.848 added;¦11/9/17: 0%->5¦15/12/17: 5%->35¦16/3/18: 35%->45¦7/6/18: 45%->100","new; 32.848",76,39,null,null,"2017-06-05","2018-06-07"]
[3202,0,"--- RELEASE 14 ---","-",1,"Rel-14",null,"2014-12-12","2014-12-12",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3203,0,"Release 14 on Mission Critical","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A3206+1","v":3206},740022,"   Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",2,"Rel-14",null,"2016-06-13","2017-06-14",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379, 23.280, 23.281, 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[3210,740025,"         CT3 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3213,700028,"   Mission Critical Services Common Requirements ","MCImp-MCCoRe",2,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150822","SP-170407","Andrew Thiessen","andrew (at) its (dot) bldrdoc (dot) gov","2/3/16: FCD: 03/16->06/16. ES in SP-160104¦0->75%¦9/6/16: 75%->100","New 22.280",70,36,null,null,"2015-12-07","2016-06-09"]
[3216,670006,"      Study on Mission Critical Video over LTE","FS_MCVideo",3,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150048",null,"Villebrun, Emmanuelle (French MoI)","emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","1/4/15:TR number added¦June2015: Compl:0%->50¦07/09/15: 50%->70¦7/12/15: 70%->100","New 22.879",67,34,null,null,"2015-03-04","2015-12-07"]
[3220,740033,"      Stage 3 of MCVideo","MCImp-MCVIDEO-CT",3,"Rel-14","ct","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ",null,"24.581, 24.281 ",74,38,null,null,"2016-12-01","NA"]
[3223,740036,"         CT4 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","6/3/17: 0%->100","23.003, 23.335, 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[3227,700031,"      Stage 1 of MCData","MCImp-MCData",3,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100","New 22.282",70,36,null,null,"2015-12-07","2016-06-09"]
[3228,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[3231,740030,"         CT3 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C3","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","5/6/17: 0%->100","29.165, 29.213, 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3235,790052,"   UE Conformance Test Aspects - Mission Critical Improvements","MCImp-UEConTest",2,"Rel-14","R5","2018-03-15","2019-12-13",1,"RP-180527",null,"NIST",null,"tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements)¦to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).;; 25/9/20: 5%->100",null,79,40,null,null,"2018-03-27","2020-09-25"]
[3238,730010,"   CT3 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","2/12/16: 0%->20¦6/3/17: 20%->100","29.165, 29.212, 29.213, 29.214",73,37,null,null,"2016-09-16","2017-03-06"]
[3241,0,"Release 14 on V2X","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3245,740009,"   Security aspect of LTE support of V2X services","V2XLTE-Sec",2,"Rel-14","S3","2016-12-01","2017-06-15",1,"SP-160955",null,"Huawei, Marcus Wong","mwong@huawei.com","6/3/17: 0%->75¦7/6/17: 75%->100",33.185000000000002,74,38,null,null,"2016-12-01","2017-06-07"]
[3248,720290,"      Perf. part: LTE-based V2X Services","LTE_V2X-Perf",3,"Rel-14","R4","2016-06-15","2017-09-15",1,"RP-162519",null,"LG Electronics",null,"¦26/9/16: WID: RP-161298->RP-161894¦20/12/16: WID: RP-161894->RP-162519¦20/12/16: Stat Rep: ->RP-162519¦19/6/17: Compl:0%->75%¦19/9/17: Compl:75%->100%",null,72,37,null,null,"2016-07-01","2017-09-19"]
[3250,730026,"   CT aspects of V2X Services","V2X-CT",2,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3253,730029,"      CT4 aspects of V2X Services","V2X-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 29.388 added¦6/10/16: 29.389 added¦2/12/16: 0%->80¦6/3/17: 80%->100","23.003, 23.007, 23.008, 29.272; 29.388; 29.389",73,37,null,null,"2016-09-16","2017-03-06"]
[3256,670009,"      Study on Stage 1 of LTE support for V2X services","FS_V2XLTE_S1",3,"Rel-14","S1","2015-02-09","2015-02-09",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75¦7/12/15: 75%->100","New 22.885",67,34,null,null,"2015-12-07","2015-12-07"]
[3260,700061,"Support for V2V services based on LTE sidelink","LTE_SL_V2V",1,"Rel-14",null,"2015-12-15","2018-09-14",1,"RP-152293",null,"LG Electronics",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3263,730073,"   UE Conformance Test Aspects - Support for V2V services based on LTE sidelink","LTE_SL_V2V-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-172358",null,"Huawei",null,"¦20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ;; 11/10/20: 98%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3266,710024,"   Non-IP for Cellular IoT for EC-EGPRS ","NonIP_GPRS",2,"Rel-14","S2","2016-03-02","2016-06-15",1,"SP-160196",null,"Hans Ronneke, Ericsson","hans . Ronneke (a) ericsson . Com","9/6/16: 0%->50¦19/9/16: 50%->100","23.060, 23.682, 23.401?",71,36,null,null,"2016-03-02","2016-09-19"]
[3269,720069,"      CT3 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C3","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦20/9/16: 0%->100","29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007",72,37,null,null,"2016-03-02","2016-09-20"]
[3274,770063,"   UE Conformance Test Aspects - Further enhanced MTC for LTE","LTE_feMTC-UEConTest",2,"Rel-14","R5","2017-09-15","2018-09-14",1,"RP-192886",null,"Ericsson",null,"¦8/1/18: Compl:0%->6%¦27/3/18: Compl:6%->21%¦ ¦2¦26/3/19: WID:RP-180414->RP-190514; 26/6/19: WID:RP-190514->RP-190935; 14/1/20: WID:RP-190935->RP-192886; 26/3/20: 26%->100",null,77,39,null,null,"2017-09-19","2020-03-26"]
[3275,720093,"Enhancements of NB-IoT","NB_IOTenh",1,"Rel-14",null,"2016-06-15","2018-12-14",1,"RP-161324",null,"Huawei",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[3278,770061,"   UE Conformance Test Aspects - Enhancements of NB-IoT","NB_IOTenh-UEConTest",2,"Rel-14","R5","2017-09-15","2018-12-14",1,"RP-171781",null,"Huawei",null,"¦8/1/18: Compl:0%->5%27/3/18: Compl:5%->30%¦27/6/18: C; 11/10/20: 60%->100",null,77,39,null,null,"2017-09-19","2020-10-11"]
[3281,720081,"   Study on extended architecture support for Cellular Internet of Things","FS_CIoT_Ext",2,"Rel-14","S2","2016-06-17","2016-12-15",1,"SP-160505",null,"Intel : Puneet Jain","puneet.jain@intel.com","28/7/16: 23.730 added¦19/9/16: 0%->70¦1/12/16: FCD:03/17->12/16¦1/12/16: 70%->100",23.73,72,37,null,null,"2016-06-17","2016-12-01"]
[3285,740040,"      CT4 aspects of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","6/3/17: 0%->90¦5/6/17: 90%->100","23.008, 29.272, 29.002, 29.336, 29.128, 29.171, 29.172, 29.173",74,38,null,null,"2016-12-01","2017-06-05"]
[3288,730277,"   Perf. part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh-Perf",2,"Rel-14","R6","2018-03-15","2018-06-15",1,"RP-161806",null,"Nokia",null,"¦20/12/16: Compl:0%->20% ¦21/3/17: Compl:20%->80%¦ 19/6/17: Compl:80%->100%",null,73,37,null,null,"2016-09-26","2017-06-19"]
[3290,730183,"   Core part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands-Core",2,"Rel-14","R4","2016-09-15","2017-06-15",1,"RP-170139","RP-170970","Ericsson",null,"¦20/12/16: Compl:0%->99% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17;19/6/17: Compl:99%->100%19/6/17: Stat Rep: ->RP-170970",null,73,37,null,null,"2016-09-26","2017-06-19"]
[3296,730013,"   CT aspects of eDecor","eDecor-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3299,730016,"      CT6 aspects of eDecor","eDecor-CT",3,"Rel-14","C6","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100","31.102, 31.111",73,37,null,null,"2016-09-16","2017-06-05"]
[3300,740067,"   RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE",2,"Rel-14","R3","2016-12-15","2017-12-15",0.99,"RP-162543",null,"Ericsson",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[3303,760002,"   Stopped - GSM aspects of eDECOR","eDecor",2,"Rel-14","R6","2017-04-04","2017-06-15",1,"SP-160310",null,"Ericsson",null,"Verbal addition by Paolo U. 21/09/17: verbal deletion by Paolo","44.060, 44.018, 48.018",76,39,null,null,"2017-05-29","NA"]
[3306,740179,"Addition of bands 25 and 40 to LTE MTC cat.1","LTE_MTCe2_L1_cat1_B25_B40-Core",1,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162573",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3310,720002,"   CT aspects of EWE","EWE-CT",2,"Rel-14","ct","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com",null,null,72,37,null,null,"2016-06-13","NA"]
[3315,730003,"   CT aspects of ERP","ERP-CT",2,"Rel-14","ct","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3318,720019,"Phase 2 of the Support of Emergency services over WLAN","SEW2",1,"Rel-14",null,"2015-09-01","2017-03-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com",null,"new 23.771, 23.402, 23.167",72,37,null,null,"2015-04-01","2016-06-09"]
[3321,730017,"   CT aspects of SEW2","SEW2-CT",2,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","5/12/16: WID:CP-160476->CP-160694",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3324,730020,"      Stopped - CT6 aspects of SEW2","SEW2-CT",3,"Rel-14","C6","2016-12-14","2016-12-14",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","Deleted at CT6#82",31.102,73,37,null,null,"2016-09-16","2016-09-16"]
[3325,720076,"T-ADS supporting WLAN Access","TADS_WLAN",1,"Rel-14","S2","2016-03-15","2016-09-15",1,"SP-160488","SP-170519","Jiang Yi","jiangyi (at) chinamobile (dot) com","19/9/16: 0%->100","23.292, 23.221, 23.402",72,37,null,null,"2016-06-17","2016-09-19"]
[3328,0,"Release 14 on IMS","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3331,700021,"   Stage 2 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S2","2015-12-11","2016-06-10",1,"SP-150623",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","7/3/16: 0%->20¦9/6/16: 20%->100. FCD: 03/16->06/16","23.167, 23.401",68,35,null,null,"2015-12-07","2016-06-09"]
[3336,760084,"   UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI)","EIEI-UEConTest",2,"Rel-14","R5","2017-06-15","2018-03-15",1,"RP-171057",null,"Qualcomm",null,"¦19/9/17: Compl:0%->45%¦8/1/18: Compl:45%->80%¦27/3/18: Compl:80%->100%",null,76,39,null,null,"2017-06-16","2018-03-27"]
[3339,720034,"   CT aspects for PWDIMS","PWDIMS-CT",2,"Rel-14","ct","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,null,null,72,37,null,null,"2016-06-11","NA"]
[3343,630107,"   CT1 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C1","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728¦5/6/17: 0%->100","24.229, 24.323",63,32,null,null,"2014-01-29","2017-06-05"]
[3346,651203,"   (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497","ISAT",2,"Rel-14","C4-IETF","2014-09-12","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 25%->70; 26/6/19: 70%->100","draft-dawes-sipping-debug",65,33,null,null,"2014-09-02","2019-06-26"]
[3349,0,"Other Release 14 ","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3350,740017,"User Controlled Spoofed Call Treatment","SPECTRE",1,"Rel-14",null,"2016-08-23","2018-06-15",1,"SP-160898",null,"Greg Schumacher, Sprint",null,"1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898",null,73,37,null,null,"2016-09-19","2016-12-01"]
[3353,750037,"   (IETF) A SIP Response Code for Unwanted Calls (draft-ietf-sipcore-status-unwanted)","SPECTRE-CT_IETF",2,"Rel-14","C1-IETF","2017-03-14","2017-03-14",1,null,null,"Ericsson",null,"18/12/17: 20%->100; 9/4/21: RFC 8197 added;","RFC 8197",75,38,null,null,"2017-03-21","2021-04-09"]
[3357,720015,"   System Architecture Enhancements to eMBMS for TV Video Service","AE_enTV",2,"Rel-14",null,"2016-03-11","2016-12-15",1,"SP-160730",null,null,null,null,null,71,36,null,null,"2016-03-11","2016-06-09"]
[3361,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347, 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[3364,740051,"      CT3 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","6/3/17: 0%->80¦6/3/17: 80%->100",29.061,74,38,null,null,"2016-12-01","2017-03-06"]
[3368,670003,"Multimedia Priority Service Modifications","MPS_Mods",1,"Rel-14","S1","2015-03-11","2016-06-15",1,"SP-150043",null,"Ray P. Singh (Applied Communications Science)","rsingh@appcomsci.com","1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%¦07/09/15: 25%->40¦7/12/15: 40%->70¦2/3/16: 70%->80¦9/6/16: 80%->100",22.152999999999999,67,34,null,null,"2015-03-04","2016-06-09"]
[3371,730032,"   CT1 aspects of SIP Reason header extension","REAS_EXT",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160481",null,"Mohali, Marianne","marianne.mohali@orange.com","2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100",24.228999999999999,73,37,null,null,"2016-09-16","2017-06-05"]
[3374,690034,"Enhancements to User Location Reporting Support","eULRS",1,"Rel-14","S1","2015-09-09","2015-12-18",1,"SP-150540",null,null,null,"2/3/16: 0%->100",null,68,35,null,null,"2015-09-09","2016-03-02"]
[3375,730002,"Diameter Load Control Mechanism","DLoCMe",1,"Rel-14","ct","2014-12-03","2017-03-15",0.98,"CP-160645","CP-171049","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","5/12/16: WID:CP-160412->CP-160645",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3378,740058,"   (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583","DLoCMe",2,"Rel-14","C4-IETF","2016-12-02","2017-03-15",0.9,"CP-160645",null,null,null,"2/12/16: 0%->90",null,74,38,null,null,"2016-12-02","2016-12-02"]
[3383,740056,"      CT4 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.109, 29.128, 29.172, 29.173, 29.228, 29.229, 29.272, 29.273, 29.283, 29.328, 29.329, 29.336, 29.337, 29.338, 29.343, 29.344, 29.345",74,38,null,null,"2016-12-01","2017-03-06"]
[3386,720029,"   Overall aspects of MMCMH_Enh","MMCMH_Enh",2,"Rel-14","S4","2016-06-13","2017-03-10",1,"SP-160596",null,"Nikolai Leung","nleung@qti.qualcomm.com","19/9/16: WID:SP-160272->SP-160785¦19/9/16: 0%->50¦1/12/16: 50%->80¦1/12/16: FCD:12/16->03/17¦6/3/17: 80%->100","26.114, 26.980",72,37,null,null,"2016-06-11","2017-03-06"]
[3389,720066,"      CT3 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C3","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Acronym changed from \"MMCMH-CT\"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦6/3/17: 0%->100","29.162, 29.213, 29.214, 29.165",72,37,null,null,"2016-03-02","2017-03-06"]
[3393,710002,"Stopped - CT aspects of (or \"Enhancements of\") MTSI Extension on Multi-stream","MMCMH-CT",1,"Rel-14","ct","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT",null,71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3396,710030,"   deleted -CT4 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","23.333, 29.333, 23.334, 29.334, 29.238",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3399,720009,"   Control and User Plane Separation of EPC nodes","CUPS",2,"Rel-14","S2","2016-06-09","2016-09-15",1,"SP-160316",null,"Huawei, Mirko Schramm","mirko.schramm@huawei.com","19/9/16: 0%->80¦1/12/16: 80%->100","23.214, 23.002, 23.203, 23.401, 23.402",72,37,null,null,"2015-09-17","2016-12-01"]
[3403,690048,"OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM14",1,"Rel-14","S5","2015-03-12","2017-12-12",1,null,null,null,null,null,null,68,35,null,null,"2015-09-16","2015-09-16"]
[3404,680035,"   Management of mobile networks that include virtualized network functions","OAM14-MAMO_VNF",2,"Rel-14","S5","2015-06-15","2017-12-12",1,"SP-150362",null,"Jinglei Liu, China Mobile","liujinglei@chinamobile.com","June2015: WID:SP-150308->SP-150362",null,68,35,null,null,"2015-06-15","2015-06-18"]
[3408,690041,"      Performance management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-PM",3,"Rel-14","S5","2015-09-16","2017-12-12",1,"SP-160402",null,"Intel (Joey Chou, joey.chou@intel.com)","joey.chou@intel.com","5/10/15: 28.523¦28.522¦28.521¦28.520 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->30¦13/6/16: WID:SP-150401->SP-160402¦19/9/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->75¦7/6/17: 75%->90¦7/6/17: FCD:0","28.523; 28.522; 28.521; 28.520; 32.426, 32.409, 32.401",69,35,null,null,"2015-06-15","2017-09-11"]
[3411,670028,"   Study on OAM support for Licensed Shared Access (LSA)","FS_OAM_LSA",2,"Rel-14","S5","2015-03-12","2016-03-11",1,"SP-150056",null,"Nokia Networks, Anatoly Andrianov","anatoly<dot>andrianov<at>nokia<dot>com","June2015: Compl:0%->15¦07/09/15: 15%->70¦7/12/15: 70%->75¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14¦28/7/16: 28.303 added¦28/7/16: 28.302 added¦28/7/16: 28.301 added¦28/7/16: 33.250 added¦28/7/16: added;","28.303; 28.302; 28.301; ",67,34,null,null,"2015-03-12","2016-07-28"]
[3414,670004,"Enhancing Location Capabilities for Indoor and Outdoor Emergency Communications","ELIOT",1,"Rel-14","S1","2015-03-11","2015-12-15",1,"SP-150044","SP-170553","Greg Schumacher","Gregory.schumacher@sprint.com","1/4/15: rapporteur added, Impacted TS added¦June2015: Compl:0%->25¦07/09/15: 25%->80¦2/3/16: 80%->100","22.101, 22.071",67,34,null,null,"2015-03-04","2016-03-02"]
[3418,700033,"   PS Data Off Services","PS_Data_Off",2,"Rel-14","S1","2015-11-09","2016-03-15",1,"SP-150823",null,"Orange, Bruno Tossou","bruno.tossou@orange.com","2/3/16: 0%->100",22.03,70,36,null,null,"2015-12-07","2016-03-02"]
[3421,740041,"   Stage 3 of PS Data Off","PS_DATA_OFF-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[3424,740044,"      CT6 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/3/17: 0%->100","31.102, 31.103, 31.111",74,38,null,null,"2016-12-01","2017-03-07"]
[3426,710003,"SCC AS Restoration","SCCAS_RES",1,"Rel-14","C4","2016-03-02","2016-12-15",1,"CP-160118",null,"China Mobile, Hao Zhang, ","zhanghao@chinamobile.com","13/6/16: 0%->100",23.38,71,36,null,null,"2016-03-02","2016-06-13"]
[3429,680003,"   Study on enhancement to FMSS for Rel 14","FS_eFMSS",2,"Rel-14","S1","2015-05-11","2015-12-16",1,"SP-150280",null,"Lu Lu, China Mobile","lulu@chinamobile.com","7/12/15: 70%->100",22.808,68,35,null,null,"2015-06-09","2015-12-07"]
[3433,721005,"   S4 aspects of Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",2,"Rel-14","S4","2016-03-01","2016-12-01",1,"SP-160081",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100",26.222999999999999,72,37,null,null,"2016-03-01","2016-12-01"]
[3436,800104,"      (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8845 added;","RFC 8845",80,41,null,null,"2018-06-27","2021-04-09"]
[3439,800107,"      (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8846 added;","RFC 8846",80,41,null,null,"2018-06-27","2021-04-09"]
[3443,800111,"      (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",0.9,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8864 added;","RFC 8864",80,41,null,null,"2018-06-27","2021-04-09"]
[3445,710085,"New GPRS algorithms for EASE","EASE_ALGOs_SA3",1,"Rel-14","S3","2016-03-15","2016-06-15",1,"SP-160203",null,"Tim Evans, Vodafone",null,"Discussion whether it should be Rel-13. To be concluded at SA#72.¦13/6/16: 0%->60¦1/12/16: 60%->70¦6/3/17: 70%->100","55.241, 55.242, 55.243, 55.251, 55.252, 55.253",71,36,null,null,"2016-03-22","2017-03-06"]
[3448,690049,"   Study on LI in S8 Home Routing Architecture for VoLTE ","FS_LIV8",2,"Rel-14","S3","2015-09-17","2016-06-17",1,"SP-150461",null,"Greg Schumacher (SPRINT) Gregory ","Schumacher@sprint.com","7/12/15: 0%->45¦28/1/16: 33.827 added¦7/3/16: 45%->55¦19/9/16: 55%->65¦15/12/17: 65%->100",33.826999999999998,69,35,null,null,"2015-09-17","2017-12-15"]
[3451,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[3454,720020,"Improvements of awareness of user location change","AULC",1,"Rel-14",null,"2015-09-17","2017-06-09",1,"SP-160308","SP-170524","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-09-17","2016-06-09"]
[3458,730035,"      CT3 Aspect of AULC","AULC-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.212, 29.213",73,37,null,null,"2016-09-16","2017-03-06"]
[3461,720022,"Service Domain Centralization","SeDoC",1,"Rel-14","S2","2015-11-02","2016-09-19",1,"SP-160675",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[3464,720014,"Sponsored data connectivity improvements","SDCI",1,"Rel-14",null,"2015-11-02","2016-12-15",1,"SP-160309","SP-170523","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[3468,730038,"      CT3 Aspects of SDCI","SDCI-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.250 added¦2/12/16: 10%->30¦6/3/17: 30%->80¦5/6/17: 80%->100","29.212, 29.213, 29.214, 29.201, 29.250",73,37,null,null,"2016-09-16","2017-06-05"]
[3470,710018,"   SAES5 CS Fallback in EPS","SAES5-CSFB",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","11/6/16: 0%->5¦16/9/16: 5%->20¦2/12/16: 20%->70¦6/3/17: 70%->100","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",71,36,null,null,"2016-03-02","2017-03-06"]
[3473,720012,"Group based enhancements in the network capability exposure functions","GENCEF",1,"Rel-14","S2","2015-11-02","2016-12-16",1,"SP-160311","SP-170517","Samsung, Sung Hwan Won","sunghwan.won@samsung.com",null,null,70,36,null,null,"2015-12-07","2016-06-09"]
[3476,720084,"Robust Call Setup for VoLTE subscriber in LTE","RobVoLTE",1,"Rel-14",null,"2015-11-02","2018-09-14",0.99,"SP-160312",null,null,null,null,null,72,37,null,null,"2015-12-07","NA"]
[3479,730022,"   CT Aspects of RobVoLTE","RobVoLTE-CT",2,"Rel-14","C1","2016-09-16","2017-03-16",1,"CP-160478",null,"PATEL, Milan","Milan.Patel@huawei.com","2/12/16: 0%->80¦6/3/17: 80%->100","24.229, 24.292",73,37,null,null,"2016-09-16","2017-03-06"]
[3483,740010,"   RAN-Assisted Codec Adaptation in MTSI","LTE_VoLTE_ViLTE_enh-S4",2,"Rel-14","S4","2016-12-01","2017-06-09",1,"SP-160778","SP-170516","Ozgur Oyman, Intel","ozgur.oyman@intel.com","6/3/17: 0%->65¦6/3/17: FCD:03/17->06/17¦7/6/17: 65%->100",null,74,38,null,null,"2016-12-01","2017-06-07"]
[3486,720038,"   CT1 aspects of IOC_UE_conf","IOC_UE_conf",2,"Rel-14","C1","2016-06-13","2017-03-15",1,"CP-160828",null,"Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦16/9/16: 10%->20¦17/10/16: WID:CP-160296->CP-160374¦2/12/16: 20%->75¦6/3/17: 75%->100","24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.275",72,37,null,null,"2016-06-11","2017-03-06"]
[3490,710008,"   Resource Optimization for PS Domain Online","CH14-ROPOCH",2,"Rel-14","S5","2016-03-01","2017-06-09",1,"SP-160021",null,"Shrader, David(Ericsson)","david.shrader@ericsson.com","13/6/16: 0%->10. FCD:09/16->03/17¦19/9/16: FCD: 09/16->03/17¦19/9/16: 10%->20¦1/12/16: 20%->50¦6/3/17: 50%->80¦6/3/17: FCD:03/17->06/20¦7/6/17: 80%->100","32.251, 32.299",71,36,null,null,"2016-03-01","2017-06-07"]
[3491,740015,"   Charging for SMS via T4 ","CH14-SMST4",2,"Rel-14","S5","2016-12-01","2017-06-09",1,"SP-160840",null,"Nokia","Maryse <dot> Gardella <at> Nokia <dot> com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","32.274, 32.250 , 32.298, 32.299",74,38,null,null,"2016-12-01","2017-06-07"]
[3497,740021,"      CT3 Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160697",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","8/6/17: 0%->100",29.164999999999999,74,38,null,null,"2016-12-01","2017-06-08"]
[3498,700060,"Enhanced LAA for LTE","LTE_eLAA",1,"Rel-14",null,"2015-12-15","2018-09-14",1,"RP-152272",null,"Ericsson",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3501,730075,"   UE Conformance Test Aspects - Enhanced LAA for LTE","LTE_eLAA-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-171577",null,"Intel",null,"¦21/3/17: Compl:0%->5% ;19/6/17: Compl:5%->6%¦19/9/17: Compl 8/1/18: C2 ;; 11/10/20: 85%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3504,700063,"DTX/DRX enhancements in CELL_FACH","FACH_DTXDRX",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-152286",null,"Huawei",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3508,700277,"   Perf. part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06",null,70,36,null,null,"2016-01-01","2016-07-01"]
[3511,700178,"   Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3","LTE_1980_2170_REG3-Core",2,"Rel-14","R4","2015-12-15","2015-12-15",0,"RP-152238",null,"KT Corp.",null,null,null,70,36,null,null,"2016-01-01","2015-12-22"]
[3516,700179,"   Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Core",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378¦1/7/16: Compl:40%->100%;",36.857999999999997,70,36,null,null,"2016-01-01","2016-07-01"]
[3519,700080,"Multi-Band Base Station testing with three or more bands","MB_BS_test_3B",1,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-152205",null,"Alcatel-Lucent",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3522,700081,"Performance enhancements for high speed scenario in LTE","LTE_high_speed",1,"Rel-14","R4","2015-12-15","2018-09-14",0.99,"RP-152263",null,"NTT DOCOMO",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3523,700181,"   Core part: Performance enhancements for high speed scenario in LTE","LTE_high_speed-Core",2,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-160172","RP-162222","NTT DOCOMO",null,"22/3/16: Compl:0%->5%22/3/16: WID: RP-152263->RP-160172¦1/7/16: Compl:5%->25%26/9/16: Compl:25%->45%20/12/16: Compl:45%->100%20/12/16: Stat Rep: ->RP-162222",null,70,36,null,null,"2016-01-01","2016-12-20"]
[{"$f":"A3526+1","v":3526},710072,"Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2",1,"Rel-14","R2","2016-03-15","2017-12-15",0.99,"RP-160538",null,"Huawei",null,"follow-up WI of REL-13 WI UTRA_LTE_iPos_enh",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3530,710076,"Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE","LTE_MIMO_OTA",1,"Rel-14","R4","2016-03-15","2018-03-15",0.99,"RP-160603",null,"Intel",null,"follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3533,710077,"Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO",1,"Rel-14","R1","2016-03-15","2022-06-22",0.99,"RP-160623",null,"Samsung",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[3537,710078,"Further mobility enhancements in LTE","LTE_eMob",1,"Rel-14","R2","2016-03-15","2017-06-15",1,"RP-160636",null,"ZTE",null,"no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3541,710179,"   Core part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-162488","RP-170115","Ericsson",null,"1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->85%¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->21/3/17: Compl:85%->100%21/3/17: Stat Rep: ->RP-170115",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3544,710080,"L2 latency reduction techniques for LTE","LTE_LATRED_L2",1,"Rel-14","R2","2016-03-15","2018-03-15",0.99,"RP-160667",null,"Ericsson",null,"no Perf. part¦follow-up WI of SI FS_LTE_LATRED",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3547,710081,"eMBMS enhancements for LTE","MBMS_LTE_enh2",1,"Rel-14","R1","2016-03-15","2017-09-15",0.99,"RP-160675","RP-171628","Ericsson",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[3548,710181,"   Core part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Core",2,"Rel-14","R1","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"1/7/16: Compl:0%->10%1/7/16: CD:Tue 15/03/16->Wed 15/03/171/7/16: WID: RP-160675->RP-16129726/9/16: Compl:10%->55%¦20/12/16: Compl:55%->80%¦20/12/16: WID: RP-161297->RP-162231 ¦21/3/17: Compl:80%->90% ¦19/6/17: Compl:90 ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3551,710182,"   Core part: SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-Core",2,"Rel-14","R1","2016-03-15","2016-12-15",1,"RP-160935","RP-162137","Huawei",null,"1/7/16: Compl:0%->35%1/7/16: WID: RP-160676->RP-160935¦26/9/16: Compl:35%->55%¦20/12/16: Compl:55%->100%¦20/12/16: Stat Rep: -->RP-162137",null,71,36,null,null,"2016-03-22","2016-12-20"]
[3555,710184,"   Core part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Core",2,"Rel-14","R1","2016-03-15","2016-12-15",1,"RP-161019","RP-162504","MediaTek",null,"¦1/7/16: Compl:0%->40%¦1/7/16: WID: RP-160680->RP-16101926/9/16: Compl:40%->60%¦20/12/16: Compl:60%->100%¦20/12/16: Stat Rep: -->RP-162504",null,71,36,null,null,"2016-03-22","2016-12-20"]
[3558,720070,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc8",2,"Rel-14","C1","2016-06-14","2017-03-15",1,"CP-160294",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100¦16/9/16: 0%->30¦2/12/16: 30%->75¦6/3/17: 75%->100",null,72,37,null,null,"2014-12-04","2017-03-06"]
[3562,720094,"Multi-Carrier Enhancements for UMTS","UTRA_MCe",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-161259",null,"Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3566,720195,"   Core part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US-Core",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-162007",null,"Nokia",null,"26/9/16: Compl:0%->70%¦6/10/16: 36.744 added¦20/12/16: Compl:70%->100%¦",36.744,72,37,null,null,"2016-07-01","2016-12-20"]
[3569,720096,"LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2",1,"Rel-14","R4","2016-06-15","2017-03-15",1,"RP-161221",null,"Sprint",null,"follow-up WI of SI FS_LTE_B41_HPUE",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3572,730076,"   UE Conformance Test Aspects – LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-UEConTest",2,"Rel-14","R5","2016-09-15","2017-03-15",1,"RP-161789",null,"Sprint",null,"¦20/12/16: Compl:0%->65% 21/3/17: Compl:65%->100%",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3573,721002,"Dedicated Core Networks for GERAN","DECOR_GERAN",1,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161029",null,"Ericsson",null,"no Perf. part¦DECOR was a REL-13 SA2 feature",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3576,721103,"   Core part: Positioning Enhancements for GERAN","ePOS_GERAN-Core",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052","RP-170920","Ericsson",null,"26/9/16: Compl:0%->30%¦20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ¦19/6/17: Compl:80%->100%;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3579,660037,"   Study on KQIs for Service Experience","FS_KQISE",2,"Rel-14","S5","2014-12-03","2016-03-11",1,"SP-150676",null,"Li, Hui (hui.li(at)huawei.com)","hui.li(at)huawei.com","Mar 15: 0->5%¦June2015: Compl:0%->40¦07/09/15: 40%->50¦14/09/15: WID:SP-140784->SP-150405¦7/12/15: 50%->75¦7/12/15: WID:SP-150405->SP-150676 ¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14","32.8xy",66,34,null,null,"2014-12-04","2016-03-22"]
[3584,730180,"   Core part: Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID-Core",2,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161896","RP-170478","China Telecom",null,"¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3587,730284,"   Perf. part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL)","LTE_4Rx_AP_DL_CA-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-161897",null,"Ericsson",null,"¦20/12/16: Compl:0%->30%;21/3/17: Compl:30%->50%19/6/17: Compl:50%->90%¦19/9/17: Compl:90%->100%",null,73,37,null,null,"2016-09-26","2017-09-19"]
[3591,730085,"Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX",1,"Rel-14","R4","2016-09-15","2018-09-14",0.99,"RP-161898",null,"Qualcomm",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3594,760085,"   UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE","LTE_UE_cat_1RX-UEConTest",2,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-180263",null,"Qualcomm",null,"¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3595,730086,"Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP)","LTE_WLAN_eLWIP",1,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161929",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3598,710183,"   Core part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Core",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912","RP-171330","Intel",null,"¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3604,780052,"   (IETF) SDP Offer/Answer Clarifications for RTP/RTCP Multiplexing [RFC 5761 (was draft-ietf-avtcore-5761-update)]","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-09-15",1,null,null,null,null,null,null,78,40,null,null,"2017-12-18","NA"]
[3606,780054,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel) ","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-12-14",1,null,null,null,null,"22/3/18: 25%->100. was (IETF) BFCP floor control signalling over Data Channels (draft-schwarz-mmusic-bfcp-usage-data-channel). ; 9/4/21: RFC 8865 added;","RFC 8865",78,40,null,null,"2017-12-18","2021-04-09"]
[3609,870082,"   (IETF) IP Mobility Support for IPv4, Revised (draft-ietf-mip4-rfc3344bis) --> RFC 5944","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,null,null,87,44,null,null,"2020-04-23","NA"]
[3612,620362,"   TR on Security Assurance scheme for 3GPP network products","SCAS-SA3TR",2,"Rel-14","S3","2013-12-09","2016-12-15",1,"SP-150716","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","This TR contains results of the second WID objective. Dec.14: 75->85%¦June2015: Compl:85%->90¦7/12/15: 90%->92¦10/12/15: WID:SP-130718->SP-150716¦19/9/16: 92%->98. FCD set to 12.16 (was 03/16)¦6/10/16: 33.216 added¦1/12/16: 81%->100","New 33.916; 33.216",62,32,null,null,"2013-11-22","2016-12-01"]
[3616,709998,"Rel-14 LTE Carrier Aggregation","LTE_CA_Rel14",1,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[3619,690286,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3620,690087,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[3625,690288,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3627,700069,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL","LTE_CA_R14_5DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-151671",null,"Nokia Networks",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3631,700170,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-170123",null,"Qualcomm",null,"28/1/16: 36.714-02-01 added¦22/3/16: Compl:0%->20%¦22/3/16: WID: RP-152196->RP-160616¦1/7/16: Compl:20%->30%¦1/7/16: WI26/9/16: Compl:30%->50%¦20/12/16: Com 21/3/17: ","36.714-02-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3634,700171,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192¦1/7/16: Compl:20%->40%¦26/9/16: Compl:40%->60%¦20/12/16: C ¦21/3/17:","36.714-02-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3638,700272,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL-Perf",3,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,"¦1/7/16: Compl:0%->15%21/3/17: Compl:15%->100%",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3641,700273,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0,"RP-170128",null,"LG Electronics",null,"22/3/16: WID: RP-152246->RP-1601481/7/16: WID: RP-160148->RP-160748¦26/9/16: WID: RP-160748->RP-161487¦20/12/16: WID: RP-161487->RP-16203621/3/17:",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3644,700274,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"¦22/3/16: WID: RP-152249->RP-160614¦1/7/16: Compl:0%->38%¦1/7/16: WID: RP-160614->RP-16082126/9/16: Compl:38%->0%¦20/12/16: Compl:0%->95% ¦21/3/17: CD:Wed 1",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3646,700175,"      Core part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613¦1/7/16: Compl:60%->50%¦1/7/16: WID: RP-160613¦26/9/16: Compl:50%->44%¦20/12/16:21/3/1","36.714-00-00","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3649,700176,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170309",null,"Huawei",null,"28/1/16: 36.714-03-01 added;22/3/16: Compl:0%->15%22/3/16: WID: RP-152278->RP-1605821/7/16: Compl:15%->40%1/7/1626/9/16: Compl:40%->60%¦20/12/16: Compl:60%->80 21/3/1","36.714-03-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3652,0,"Release 14 Studies","-",1,"Rel-14","SP,RP,CP,GP","2014-09-17","2015-12-11",1,"-","-",null,"-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3656,610032,"Study on need for Multiple Access Point Names","FS_MAPN",1,"Rel-14","S1","2013-09-12","2015-06-19",1,"SP-130416",null,"Giesecke & Devrient","Ilario.macchi@gi-de.com","SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%¦June2015: Compl:90%->100",22.802,61,31,null,null,"2013-08-26","2015-06-15"]
[3659,640060,"Study on User Location Reporting Support enhancements","FS_eULRS",1,"Rel-14","S1","2014-06-19","2015-06-17",1,"SP-140402",null,"China Unicom","Zhuoyun Zhang ( zhangzy910@chinaunicom.cn)","SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%¦June2015: Compl:90%->100",22.899000000000001,64,33,null,null,"2014-05-29","2015-06-15"]
[3663,680057,"Study on High Power LTE UE for Band 41","FS_LTE_B41_HPUE",1,"Rel-14","R4","2015-06-15","2016-06-15",1,"RP-160092",null,"Sprint",null,"7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ¦22/3/16: Compl:10%->40%¦22/3/16: WID: RP-151104->RP-1600921/7/16: Compl",36.886000000000003,68,35,null,null,"2015-07-03","2016-07-01"]
[3666,700036,"Study on UICC power optimization for MTC","FS_UICC_MTC_OPT",1,"Rel-14","C6","2016-06-15","2016-12-15",1,"CP-150875",null,"Berionne, Michele","micheleb [at] qti [dot] qualcomm [dot] com","7/3/16: 0%->100¦5/6/17: 71%->100",31.97,70,36,null,null,"2015-12-07","2017-06-05"]
[3667,710013,"Study on Server and Network Assisted DASH for 3GPP","FS_SAND",1,"Rel-14","S4","2016-03-01","2016-12-15",1,"SP-160083",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100","TR26.957 ",71,36,null,null,"2016-03-01","2016-12-01"]
[3671,710059,"Study on LTE Advanced Carrier Aggregation of Band 3 and Band 39","FS_LTE_CA_B3_B39",1,"Rel-14","R4","2016-03-15","2017-03-15",1,"RP-161704",null,"ZTE",null,"intention to capture results in existing TR 36.714-02-01 ¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->50%¦20/12/16: Compl ¦21/3/17: Compl:8",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3674,670015,"Study on Determination of Completeness of Charging Information in IMS","FS_DCCHII",1,"Rel-14","S5","2015-03-05","2016-03-11",1,"SP-150106",null,"Jesske, Roland","r.jesske@telekom.de","11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request¦June2015: Compl:0%->7¦07/09/15: 7%->15¦7/12/15: 15%->60, FCD: 09/15->03/16¦7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14","32.xyz",67,34,null,null,"2015-03-05","2016-03-22"]
[3677,720027,"Study on MBMS Extensions for Provisioning and Content Ingestion","FS_xMBMS",1,"Rel-14","S4","2016-06-13","2017-03-10",1,"SP-160275",null,"Kyungmo Park, sk telecom","kyungmo.park@sk.com","28/7/16: 26.981 added¦19/9/16: 0%->30¦1/12/16: 30%->50¦1/12/16: FCD:12/16->03/17¦6/3/17: 50%->100",26.981000000000002,72,37,null,null,"2016-06-11","2017-03-06"]
[3681,700022,"Study on Stage 1 for New Services and Markets Technology Enablers","FS_SMARTER",1,"Rel-14","S1","2015-02-02","2016-06-10",1,"SP-150142",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com",null,"New 22.891",67,34,null,null,"2015-03-04","2015-09-07"]
[3684,700024,"   FS_SMARTER – Critical Communications","FS_SMARTER-CRIC",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150818",null,"Kanerva, Mikko","mikko.kanerva@nokia.com","2/3/16: 15%->60¦9/6/16: 60%->95¦7/6/17: 95%->100","New 22.862",70,36,null,null,"2015-12-07","2017-06-07"]
[3688,710062,"Study on New Radio (NR) Access Technology","FS_NR_newRAT",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-170379",null,"NTT DOCOMO",null,"includes RAN TR 38.801¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160671->RP-161214¦1/7/16: Release: Rel-15->Rel-14¦28/7/16: 38.802 added¦26/9/16: Compl:10%->20%¦26/9/16: WID: RP-161214->RP-161596. 2/12/16: Moved","38.801, 38.912; 38.802; 38.901; 38.805",71,36,null,null,"2016-03-22","2017-03-21"]
[3691,640142,"   Study on Application Architecture to support MCPTT","MCPTT",2,"Rel-13","S6","2014-06-23","2015-09-16",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435. Dec.14: 2->20%. Mar 15: WID: SP-140879->SP-150095. Mar15: 30%. Transferred to SA6. June 15: FCD shifted to Sept,WID updated¦June2015: Compl:24%->50¦June2015: Compl:50%->70. 3/8/15: Rapp","New 23.779",64,33,null,null,"2014-06-04","2015-09-07"]
[3692,670030,"   SA2 Study on Architecture Enhancements at the EPS and IMS Level to Support MCPTT","MCPTT",2,"Rel-13","S2","2015-03-13","2015-06-17",1,"SP-150356",null,"Randy Bloomfield (randy@its.bldrdoc.gov)","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164.¦June2015: Compl:0%->30, WID updated¦07/09/15: 30%->100, \"To be confirmed\" deleted, since SA2 has completed it.",null,67,34,null,null,"2015-03-13","2015-09-07"]
[3696,640143,"   Functional architecture and information flows to support MCPTT","MCPTT",2,"Rel-13","S6","2015-06-18","2015-12-11",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","June2015: added as per SP-150356¦June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID¦07/09/15: 15%->50¦07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15¦7/3/16: 85%->100","New 23.179",64,33,null,null,"2014-06-04","2016-03-07"]
[3699,690011,"   MCPTT protocol aspects","MCPTT-CT",2,"Rel-13","ct","2015-09-07","2016-06-30",0.96,"CP-150793",null,"Keith Drage, Alcatel-Lucent",null,"7/12/15: WID:CP-150587->CP-150793¦28/1/16: 24.384 added;",null,69,35,null,null,"2015-09-07","2016-01-28"]
[3703,690098,"         Floor Control – On Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->80¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 80%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.38,69,35,null,null,"2015-09-29","2016-12-05"]
[3706,691001,"         Group management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.381,69,35,null,null,"2015-09-29","2016-12-05"]
[3709,710033,"         Configuration management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Introduced from CT1 WP update in 03/16¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.384,71,36,null,null,"2016-03-07","2016-12-05"]
[3713,710034,"      (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",0.25,"CP-160817",null,"Ericsson","christer.holmberg@ericsson.com","5/12/16: WID:CP-160160->CP-160817","draft-holmberg-dispatch-mcptt-rp-namespace",71,36,null,null,"2016-03-07","2016-12-05"]
[3717,640062,"   Deleted: SA2 aspects for MCPTT","MCPTT",2,"Rel-13","S2","2015-03-13","2015-03-13",1,"SP-150356","-","Randy Bloomfield (randy@its.bldrdoc.gov)","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: transferred to SA6. Was 06/14 to 06/15. 6/15: WID updated","New 23.179",64,33,"SP-69",null,"2014-06-04","2015-06-18"]
[3720,670024,"MBMS Extensions and Profiling","MEPRO",1,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","1/4/15: TS number added¦14/09/15: WID:SP-150099->SP-150439","26.346, new 26.852",67,34,null,null,"2015-03-05","2015-09-14"]
[3721,670090,"   TR on Profiling and Extensions of MBMS","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100","new 26.852",67,34,null,null,"2015-04-08","2015-12-07"]
[3724,680047,"   Stage 1 fo Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-150463","S1-143304","General Dynamics","paul.piggin@gd-broadband.com","SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463","New 22.346",63,32,null,null,"2014-02-05","2015-09-14"]
[3728,700038,"      CT6 aspects for IOPS","IOPS-CT",3,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com","ES in CP-150837¦7/3/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-03-07"]
[3731,650019,"Flexible Mobile Service Steering","FMSS",1,"Rel-13","S1,S2","2014-09-15","2016-03-11",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS)",22.100999999999999,65,33,null,null,"2013-11-26","2014-08-28"]
[3734,660003,"   Flexible Mobile Service Steering - Stage 2","FMSS-SA2",2,"Rel-13","S2","2014-12-12","2015-06-17",1,"SP-140703",null,"Lu Lu, China Mobile","lulu@chinamobile.com","07/09/15: 0%->90¦07/09/15: 90%->100",null,66,34,null,null,"2014-12-03","2015-09-07"]
[3738,660013,"   Stage 1 for Application specific Congestion control for Data Communication","ACDC-ST1",2,"Rel-13","S1","2014-06-18","2014-09-17",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","Results from MCC Split of the SA1 feature into F+BB for stage 1",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[3742,670059,"   RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150512",null,"LG Electronics",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3745,570129,"   Stage 1 for User Plane Congestion management","UPCON-ST1",2,"Rel-13","S1","2012-09-12","2013-03-06",1,"SP-140631","-","KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101. 3/3/15: start date corrected (was Mar 12)",22.100999999999999,57,29,null,null,"2012-08-06","2015-03-03"]
[3746,580057,"   TR on Stage 2 for User Plane Congestion management","UPCON-SA2TR",2,"Rel-13","S2","2012-12-12","2015-03-18",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. TR 23.705v100 for Information. Dec.14: 87->98%. Mar15: 100%","new 23.705",58,30,null,null,"2012-11-13","2015-03-05"]
[3749,630119,"      Stage 2 for RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON-SA2",3,"Rel-13","S2","2014-03-07","2014-12-12",1,"SP-140434","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>S2-142850 (added impacted specs). Dec.14: 70->100% only if RAN agrees to standardize the FPI","23.060, 23.203, 23.401",63,32,null,null,"2014-03-04","2014-12-03"]
[3753,630020,"   Deleted - BB2: Application and Content Prioritization","UPCON-CONDEL",2,"Rel-13","S2","2014-03-07","2014-09-17",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Content specific UP prioritization (Video), Application specific UP prioritization","TBD",63,32,"SP-65","PCG-33","2014-03-04","2014-09-16"]
[3756,650128,"   TR on Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",2,"Rel-13","S4","2014-09-09","2015-09-16",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100","New 26.9xy",65,33,null,null,"2014-09-05","2015-12-07"]
[3759,710036,"   (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",0.9,null,null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90; 9/4/21: RFC 8849 added;","26.22; RFC 8849",71,36,null,null,"2016-03-07","2021-04-09"]
[3764,650021,"   RAN aspects of RAN Sharing Enhancements for LTE","RSE-RAN_LTE",2,"Rel-13","R3","2014-09-12","2015-12-15",1,"RP-141671","-","NEC","Siva.Vakeesar@emea.nec.com","Triggered by TR 36.856 Study on RAN aspects of RAN Sharing Enhancements for LTE (FS_RSE-RAN_LTE) & SA1 22.101 Stage 1","LTE",65,33,null,null,"2014-06-16","2014-10-05"]
[3767,630114,"   Stage 1 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-140630","S1-143303","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 completed. Updated WID SP-140286=>SP-140630",22.228000000000002,63,32,null,null,"2014-02-05","2014-09-16"]
[3768,640138,"   TR on Stage 2 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S2","2014-06-19","2015-03-18",1,"SP-140630","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 9->55%¦June2015: Compl:55%->85¦07/09/15: 85%->100","New 23.706",64,33,null,null,"2014-06-12","2015-09-07"]
[3771,650022,"   Security for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S3","2014-09-17","2015-09-30",1,"SP-140630","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%¦11/12/15: 15%->100","33.203, 33.328",65,33,null,null,"2014-09-04","2015-12-11"]
[3774,690015,"      CT1 aspects 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C1","2015-09-07","2015-12-18",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: 0%->100¦7/12/15: WID:CP-150498->CP-150790->CP-150767","24.371, 24.229",69,35,null,null,"2015-09-07","2015-12-07"]
[3778,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",0.75,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371, 24.229, 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[3780,870074,"      Deleted - (IETF) Oauth 2.0 Proof-of-Possession (PoP) Security Architecture (draft-ietf-oauth-pop-architecture) ","eWebRTCi-CT",3,"Rel-13","S3-IETF","2015-12-08","2016-06-16",1,null,null,null,null,"9/4/21: 25%->100",null,87,44,null,null,"2016-03-07","2021-04-09"]
[3785,650100,"   RAN aspects for improvements to CS/PS coordination in GERAN Shared Networks","CSPS_Coord_GERAN",2,"Rel-13","G2","2015-03-11","2016-05-12",1,"GP-150225",null,"Nicklas Johansson, Ericsson LM","Nicklas.Johansson@Ericsson.com","June2015: Compl:0%->35¦07/09/15: 35%->50, FCD:08/15->11/15¦7/12/15: 50%->95, FCD: 12/15->02/16. 02/03/16: FCD: 02/16->05/16¦13/6/16: 95%->100","48.008, 48.018",65,33,null,null,"2015-05-07","2016-06-13"]
[3789,640141,"   TR on Stage 2 for Enhancements to Proximity-based Services - Extensions","eProSe-Ext-SA2TR",2,"Rel-13","S2","2014-06-18","2015-03-13",1,"SP-150028","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:60%->90¦07/09/15: 90%->95¦07/09/15: 95%->100","New 23.713",64,33,null,null,"2014-06-17","2015-09-07"]
[3792,680007,"      CT1 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->40¦7/12/15: 40%->90. FCD -> 03/16, ES in CP-150724¦7/3/16: 90%->100",29.343,68,35,null,null,"2015-06-15","2016-03-07"]
[3793,680008,"      CT3 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->60¦8/3/16: 60%->100","23.003, 23.008, 29.272, 29.344, 29.345",68,35,null,null,"2015-06-15","2016-03-08"]
[3796,590035,"   Study on Security for Proximity-based Services","FS_ProSe_Sec",2,"Rel-13","S3","2013-03-18","2015-06-17",1,"SP-140629","-","Qualcomm","Adrian Escott (aescott@qti.qualcomm.com)","SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information. 4/3/15: 95%->70% (more topics to be included)¦June2015: Compl:70%->75¦7/12/15: 75%->95¦7/3/1",33.832999999999998,59,30,null,null,"2013-02-20","2016-12-01"]
[3799,640145,"   Stage 1 for voice over E-UTRAN Paging Policy Differentiation","voE_UTRA-N_PPD-SA1",2,"Rel-13","S1","2014-06-16","2014-06-18",1,"SP-140394","-","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#64 approved WID & completed","22.228, 22.278",64,33,null,null,"2014-05-29","2014-06-11"]
[3805,640047,"IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM",1,"Rel-13","S2","2014-06-18","2016-06-15",1,"SP-150250","-","Tricci So, ZTE","tso@zte.com.cn","06/15: WID: SP-140279->SP-150250","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[3807,640247,"   Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM-SA2",2,"Rel-13","S2","2014-06-23","2015-09-16",1,"SP-150250",null,"Tricci So, ZTE","tso@zte.com.cn","June2015: Compl:0%->65, WID: SP-140279->SP-150250¦07/09/15: 52%->100","23.402, New 23.203",64,33,null,null,"2014-05-30","2015-09-07"]
[3811,680021,"      CT3 aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",3,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150874",null,"680001Xingyue(Joy) Zhou, ZTECorporation. ES in 641","zhou.xingyue@zte.com.cn","07/09/15: 0%->40¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 40%->95¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 95%->100","29.212, 29.213, 29.214, 29.215",68,35,null,null,"2015-06-15","2016-03-07"]
[3814,640153,"   Stage 2 for Double Resource Reuse for Multiple Media Sessions","DRuMS-SA2",2,"Rel-13","S2","2014-03-14","2015-03-13",1,"SP-140393","-","Ericsson","George.Foti@ericsson.com","Dec.14: 49->95%. Mar15: 100%","23.203, 23.228",64,33,null,null,"2014-05-30","2015-03-05"]
[3817,660048,"      CT3 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson","Jan Holm","Mar.15: 65->95%¦June2015: Compl:95%->100","29.212, 29.213, 29.214, 29.215",66,34,null,null,"2014-12-09","2015-06-15"]
[3818,640056,"Lawful Interception in the 3GPP Rel-13","LI13",1,"Rel-13","S3","2014-06-18","2016-12-15",1,"SP-160043","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com","SP#65 updated WID SP-140400=>SP-140578. 2/4/15: WID SP-140815->SP-150111¦June2015: Compl:0%->10. WID: SP-150111->SP-150290¦14/09/15: WID:SP-150290->SP-150460¦7/12/15: 10%->15¦7/3/16: 13%->20¦7/3/16: WID:SP-150460->SP-160043¦19/9/16: 20%->60. FCD","33.106, 33.107, 33.108",64,33,null,null,"2014-06-11","2016-12-01"]
[3821,680031,"   SA4 aspects of Video enhancements by Region-Of-Interest information signalling","ROI",2,"Rel-13","S4","2014-06-18","2015-09-16",1,"SP-140219","-","Intel","ozgur.oyman@intel.com","Created by MCC as the structure of the Feature get expanded to include CT aspects¦June2015: Compl:40%->90, FCD: 06/15->09/15¦Aug2015: Compl:90%->95",26.114000000000001,64,33,null,null,"2015-06-15","2015-08-12"]
[3826,650026,"TV video profile","TVProf",1,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Mar. 15: 5->15%","-",65,33,null,null,"2014-09-05","2015-03-05"]
[3829,650027,"Enhanced LTE UE Delay test methods and requirements","E_LTE_UED",1,"Rel-13","S4","2014-09-09","2016-06-15",1,"SP-140482","-","Orange","stephane.ragot@orange.com","Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->50¦7/12/15: 50%->80, FCD: 12/15->03/16. ES in SP-150652¦7/3/16: FCD: 03/16->06/16¦11/6/16: 80%->100","26.131, 26.132",65,33,null,null,"2014-09-05","2016-06-11"]
[3832,670016,"   SA4 aspects of EVS in 3G Circuit-Switched networks","EVSoCS-S4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%¦Aug2015: 10%->20¦07/09/15: 20%->40¦7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103, 28.062, New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-03-07"]
[3836,670019,"      CT4 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","June2015: Compl:0%->95. FCD -> 03/16, ES in CP-150618¦7/3/16: 95%->100","23.153, 23.334, 29.002, 29.231, 29.232, 29.332, 29.334",67,34,null,null,"2015-03-04","2016-03-07"]
[3839,650031,"Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP)","eDASH",1,"Rel-13","S4","2014-09-09","2015-12-16",1,"SP-150448","-","Qualcomm, Huawei","Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com)","Triggered by Rel-12 Dec.14: 0->10%. Mar. 15: 15%¦June2015: Compl:15%->25. WID updated¦Aug2015: 25%->30¦07/09/15: 30%->60¦14/09/15: WID:SP-150211->SP-150448¦7/12/15: 60%->100","26.233, 26.234, 26.244, 26.247, 26.938, 26.346, 26.946",65,33,null,null,"2014-09-05","2015-12-07"]
[3842,650132,"   SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",2,"Rel-13","S4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65: WID SP-130670=>SP-140601 (moved from Rel12 incl. new TR to Rel-13). FCD 03/15=>06/15. St1 in TS 22.173. 12/14: 70->40%, CD: 06/15->09/15. 03/15: 50%. June 15: FCD: 09/15->12/15¦08/15: 60%¦09/15: 75%¦7/12. ES in SP-150658¦7/3/16: 90%->100",26.114000000000001,59,30,null,null,"2013-02-20","2016-03-07"]
[3843,660043,"   CT Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",2,"Rel-13","C3,C1,C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-09","2014-12-09"]
[3847,660050,"MTSI Extension on Multi-stream Multiparty","MMCMH",1,"Rel-13",null,"2014-12-12","2016-03-07",0.98,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Mar. 15: 0->10%. WID: SP-140738->SP-150097¦June2015: Compl:10%->30¦Aug2015: 30%->50, FCD: sep->Dec 2015¦07/09/15: 50%->60¦7/12/15: 60%->100¦10/12/15: WID:SP-150097->SP-150660. Might be moved to Rel-14 (see note in UID710002)","26.114, New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[3850,720062,"   (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","MMCMH",2,"Rel-13","S4-IETF","2015-12-07","2016-03-07",0.9,null,null,null,null,"Was (IETF) (draft-ietf-mmusic-sdp-simulcast); 23/4/20: 0%->90; 9/4/21: RFC 8853 added;","RFC 8853",72,37,null,null,"2016-06-13","2021-04-09"]
[3854,690038,"   (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) --> RFC 8627","VTRI_EXT",2,"Rel-13","S4-IETF","2014-12-12","2015-09-11",1,"SP-15047",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added; 23/4/20: 10%->100","26.114, draft-ietf-payload-flexible-fec-scheme",69,35,null,null,"2015-03-03","2020-04-23"]
[3857,560132,"   Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","SON-NM-CCO",2,"Rel-13","S5","2014-09-19","2015-12-11",1,"SP-140060","-","Ericsson","robert.petersen@ericsson.com","SP#64 work not started. Dec.14: 0->20, cd: 06/15->12/15. Mar 15: 20->30%¦June2015: Compl:30%->50¦07/09/15: 50%->60¦7/12/15: 60%->100","28.627, 28.628, 32.103, 32.422, 32.425, 32.442",56,29,null,null,"2012-04-18","2015-12-07"]
[3861,560235,"   Converged management Performance Management Interface Definitions","OAM-PMID",2,"Rel-13","S5","2012-06-20","2015-12-11",1,"SP-150678","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678","new TSs 32.863 ",56,29,null,null,"2012-05-14","2015-12-07"]
[3864,560236,"      WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface","WLAN-OAM-SA5ietf",3,"Rel-13","S5","2012-06-27","2015-06-17",1,"SP-140535","-","Intel","joey.chou@intel.com","SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified¦June2015: Compl:5%->20¦07/09/15: 20%->60¦7/12/15: 60%->100","new 28.403",56,29,null,null,"2012-06-12","2015-12-07"]
[3867,641000,"Rel-13 Charging","CH13",1,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-150307","-","-","-","CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150307","-",64,33,null,null,"2014-06-06","2015-06-18"]
[3868,640059,"   Inter-PLMN PS domain online charging","iPLMN-PS-OCH",2,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-140324","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations","Stage 2/3",64,33,null,null,"2014-06-06","2014-06-06"]
[3872,670025,"   Charging on enhancements for IMS Service Continuity","CHeISC",2,"Rel-13","S5","2015-03-05","2015-09-09",1,"SP-150055",null,"Gerald Goermer","Gerald <dot> Goermer <at> nsn <dot> com","06/15: 0->50%¦07/09/15: 50%->100. FCD: 12/15->09/15","32.260, 32.299, 32.298",67,34,null,null,"2015-03-05","2015-09-07"]
[3876,610105,"   CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C4","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15. Dec.14: 10->100","23.334, 29.334",61,31,null,null,"2013-08-10","2014-12-04"]
[3879,550017,"LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US",1,"Rel-13","R4,R2,R3","2012-03-05","2015-06-09",0.08,"RP-121397","-","LightSquared","masoud.olfat@lightsquared.com","RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14","LTE",55,28,null,null,"2012-02-23","2014-09-09"]
[3882,640019,"Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB_sig",1,"Rel-13","R3","2014-06-18","2015-09-15",1,"RP-141032","-","Samsung","sunghwan.won@samsung.com","Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015)","LTE",64,33,null,null,"2014-06-16","2014-06-23"]
[3886,640236,"   Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Perf",2,"Rel-13","R4","2014-06-18","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150106->RP-150705 29/09/15: Stat","36.101, 36.104, 36.133, 36.141, 36.307, 36.862",64,33,null,null,"2014-06-16","2016-01-01"]
[3889,650134,"   Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments","UTRA_LTE_SON_AAS-Core",2,"Rel-13","R3","2014-09-12","2015-06-15",1,"RP-141624","RP-150727","Nokia Networks","krzysztof.kordybach@nsn.com","CD:Tue 16/06/15->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141854 1st Apr 15: Compl:15%->25% 1st Apr 15: Stat Rep: RP-141854->RP-150110 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150110->RP-150727","36.300, 36.423, 36.413, 25.413",65,33,null,null,"2014-06-16","2015-06-18"]
[3893,660030,"Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",1,"Rel-13","C1","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[3894,660014,"   CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",2,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140813",null,"Ericsson",null,". 12/12:0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN","24.229, 24.302",66,34,null,null,"2014-12-04","2015-05-05"]
[3897,660041,"   CT1 aspects of P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",2,"Rel-13","C1","2014-12-03","2015-12-14",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","CT4->CT1. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:0%->10. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 10%->70¦7/12/15: 70%->100","24.302, 24.229, 24.244, 24.008",66,34,null,null,"2014-12-09","2015-12-07"]
[3901,680040,"   CT4 aspects of Mobile Equipment Identity signalling over WLAN","MEI_WLAN",2,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com","07/09/15: 0%->90¦7/12/15: 90%->100","29.273, 29.274, 29.275, 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[3904,670037,"   SAE Protocol Development (Stage 3) - Phase 4","SAES4",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms. 5/5/15: acronym changed from \"SAES4-CT1\"¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[3907,660034,"Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",1,"Rel-13","C1,C3","2014-12-03","2015-03-13",0.74,"CP-140928",null,"Orange",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[3911,660042,"Warning Status Report in EPS","WSR_EPS",1,"Rel-13","C4","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"5/5/15: acronym changed from \"WSR_EP\"¦7/12/15: WID:CP-140998->CP-150792",null,66,34,null,null,"2014-12-04","2015-12-07"]
[3914,660026,"Shared Data Update for Multiple Subscriber","SHARED_SubData_UPD",1,"Rel-13","C4","2014-12-03","2014-12-03",1,"CP-150013",null,"Huawei, Susan Shi","susan.shishufeng@huawei.com","Mar.15: 0->50%, WID: CP-140804->CP-150013¦June2015: Compl:50%->95¦07/09/15: 95%->100","29.328, 29.364",66,34,null,null,"2014-12-04","2015-09-07"]
[3918,670097,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C3","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","2/4/15: added, following CT3 chair's info that the WID also has a CT3 part¦June2015: Compl:0%->20¦07/09/15: 20%->40¦7/12/15: 40%->100",null,67,34,null,null,"2015-04-02","2015-12-07"]
[3919,670013,"Retry restriction for Improving System Efficiency","RISE",1,"Rel-13","C1","2015-03-04","2015-12-15",1,"CP-150495",null,"Huawei, Lin Shu","shulin@huawei.com","Continuation of Rel-12 SINE UID 620006. 5/5/15: acronym changed from \"RISE\"¦June2015: Compl:0%->10¦07/09/15: 10%->70¦14/09/15: WID:CP-150092->CP-150495¦7/12/15: 70%->100",null,67,34,null,null,"2015-03-04","2015-12-07"]
[3922,670021,"Continuation of the Overload Control for PCC based Diameter applications ","cDOCME_PCC",1,"Rel-13","C3","2015-03-04","2015-12-11",1,"CP-150194",null,"ZTE, Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","Relates to UID 580026 (Study on Diameter overload control mechanism)¦June2015: Compl:0%->100","29.212, 29.215, 29.219, 29.217",67,34,null,null,"2015-03-04","2015-06-15"]
[3926,680043,"   CT4 aspects of Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",2,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com","07/09/15: 0%->5¦7/12/15: 5%->70. FCD->03/16. ES in CP-150614¦7/3/16: 70%->100","23.334, 29.334, 29.238, 23.333, 29.333, 29.332, 29.232",68,35,null,null,"2015-06-15","2016-03-07"]
[3929,640051,"Enhanced CS Fallback (CSFB)","eCSFB",1,"Rel-13","S2,S3","2014-06-18","2015-03-13",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB)","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[3932,650024,"   Deleted - Security for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S3","2014-09-18","2014-09-18",1,"SP-140579","-","China Unicom","Feng Gao (gaofeng149@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579¦14/09/15: 0%->100. SA#69: deleted, since SA2 has stopped the work.",null,65,33,"SP-69",null,"2014-09-15","2015-09-14"]
[3936,590030,"Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA",1,"Rel-13","R4","2013-03-04","2016-09-15",1,"RP-130373","-","Huawei","ronnie.zhang@huawei.com","Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA)","UTRA, LTE, GERAN",59,30,null,null,"2013-02-26","2014-09-15"]
[3939,660074,"Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox",1,"Rel-13","R2","2014-12-15","2016-09-15",1,"RP-142311",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-15"]
[3941,660274,"   Perf. part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Perf",2,"Rel-13","R4","2014-12-15","2016-09-15",1,"RP-150441","RP-151337","Qualcomm","Qualcomm","1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Stat Rep: RP-150795->RP-151337¦1/1/16: CD¦22/3/16: Compl:0%->10%;26/9/16: Compl:85%->100%",null,66,34,null,null,"2015-01-12","2016-09-26"]
[3944,660077,"UE core requirements for uplink 64 QAM","LTE_UL64QAM",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-142222",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3947,660078,"Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS",1,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-142223",null,"China Telecom","China Telecom",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[3951,670055,"Dual Connectivity enhancements for LTE","LTE_dualC_enh",1,"Rel-13","R2","2015-03-16","2016-06-15",1,"RP-150490",null,"NTT DOCOMO",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3954,670056,"Multicarrier Load Distribution of UEs in LTE","LTE_MC_load",1,"Rel-13","R2","2015-03-16","2016-09-15",1,"RP-150491",null,"ZTE",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3957,670058,"LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio",1,"Rel-13","R2","2015-03-16","2018-09-14",0.99,"RP-150510",null,"Intel",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[3960,710070,"   UE Conformance Test Aspects - WLAN/3GPP Radio Level Integration and Interworking Enhancement Interworking","LTE_WLAN_radio-UEConTest",2,"Rel-13","R5","2016-03-15","2018-09-14",1,"RP-180942",null,"Intel",null,"testing REL-13 LTE_WLAN_radio-Core¦1/7/16: Compl:0%->5%¦20/21/3/17: Compl:20 ;27/3/18: ;¦26/3/19: 58%->100",null,71,36,null,null,"2016-03-22","2019-03-26"]
[3965,670261,"   Perf. part: LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-Perf",2,"Rel-13","R4","2000-01-03","2016-09-15",1,"RP-161237","RP-151265","Ericsson",null,"03/07/15: Compl:0%->15% 03/07/15: CD:Mon 02/10/00->Wed 15/06/16 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:15%->35% 29/09/15: Stat Rep: RP-150803->RP-15126522/3/16: Compl:60%-;26/9/16: Compl:90%->100%",null,67,34,null,null,"2015-04-01","2016-09-26"]
[3966,700066,"   UE Conformance Test Aspects - LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-UEConTest",2,"Rel-13","R5","2015-12-15","2017-09-15",1,"RP-160078",null,"Ericsson",null,"¦22/3/16: Compl:0%->10%¦1/7/16: Compl:10%->25%¦ 26/9/16: 21/3/17: Compl:60%->70 ;",null,70,36,null,null,"2016-01-01","2017-09-19"]
[3969,670262,"   Perf. part: AWS-Extension Band for LTE","LTE_AWS_EXT-Perf",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150800","RP-151343","Ericsson",null,"03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Stat Rep: RP-150796->RP-151343¦",null,67,34,null,null,"2015-04-01","2016-01-01"]
[3972,670163,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150602","RP-150536","Nokia Networks",null,"03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3976,670264,"   Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset-Perf",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425","RP-150536","Samsung",null,"03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[3979,680044,"Message interworking during PS to CS SRVCC ","mSRVCC",1,"Rel-13","C1","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com",null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[3981,680046,"   CT3 aspects of Message interworking during PS to CS SRVCC ","mSRVCC",2,"Rel-13","C3","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com","07/09/15: 0%->70¦7/12/15: 70%->100",29.292000000000002,68,35,null,null,"2015-06-15","2015-12-07"]
[3987,690023,"      CT4 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C4","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 0%->100","23.003, 23.008, 29.273, 29.274",69,35,null,null,"2015-09-07","2015-12-07"]
[3990,660010,"   MBMS Enhancements TR Phase","FS_MBMS_enh_TR",2,"Rel-13","S2","2014-12-03","2015-09-14",1,"SP-150516",null,"Nokia Networks, Curt Wong",null,"Acronym changed from \"MBMS_enh-SA2TR\". Mar15: 0->10%¦June2015: Compl:10%->50¦07/09/15: 50%->70. acronym changed from \"MBMS_enh\" to \"MBMS_enh_TR\"¦07/09/15: 70%->100¦14/09/15: WID:SP-140883->SP-150516","23.8xy",66,34,null,null,"2014-12-03","2015-09-14"]
[3991,690046,"   MBMS Enhancements","MBMS_enh_St2",2,"Rel-13","S2","2015-08-10","2015-09-16",1,"SP-150520",null,"Nokia Networks, Curt Wong",null,"SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_","23.246, 23.468",69,35,null,null,"2015-09-16","2015-10-14"]
[3994,700007,"      CT4 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C4","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,"29.274, 23.008, 29.230",70,36,null,null,"2015-12-07","2015-12-07"]
[3997,690026,"   CT3 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100","29.212, 29.213",69,35,null,null,"2015-09-07","2015-12-08"]
[4001,700010,"   CT4 aspects of DiaPri","DiaPri",2,"Rel-13","C4","2015-11-02","2016-03-11",1,"CP-150613",null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com","ES in CP-150622¦7/3/16: 70%->100","29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.338, 29.344, 29.345",70,36,null,null,"2015-12-07","2016-03-07"]
[4006,680060,"Licensed-Assisted Access using LTE","LTE_LAA",1,"Rel-13","R1","2015-06-15","2017-09-15",0.99,"RP-151045","-","Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4009,700067,"   UE Conformance Test Aspects - Licensed-Assisted Access using LTE","LTE_LAA-UEConTest",2,"Rel-13","R5","2015-12-15","2017-09-15",1,"RP-162376",null,"Motorola Mobility",null,"¦22/3/16: Compl:0%->5%1/7/16: Compl:5%->8%26/9/16: Compl:8%->15%¦20/21/3/17: Com ;",null,70,36,null,null,"2016-01-01","2017-09-19"]
[4012,680261,"   Perf. part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO-Perf",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151085","RP-151565","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Stat Rep: -->RP-151565 ¦1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->35%;26/9/16: Compl:70%->100%",null,68,35,null,null,"2015-07-03","2016-09-26"]
[4015,680162,"   Core part: L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-152184","RP-151238","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4016,680064,"Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM",1,"Rel-13","R2","2015-06-15","2016-09-15",1,"RP-151110","-","Huawei",null,"follow-up WI of REL-13 SI FS_LTE_SC_PTM",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4019,710069,"   UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161681","-","Huawei",null,"testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4022,680067,"RAN sharing enhancements for UMTS","RSE_UTRA_GUSH",1,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151086","-","Huawei",null,"no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4027,690062,"Network-Assisted Interference Cancellation and Suppression for UMTS","UTRA_NAICS",1,"Rel-13","R1","2015-09-15","2015-12-15",1,"RP-151577","-","Huawei",null,"no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS",null,69,35,null,null,"2015-09-29","NA"]
[4030,690164,"   Core part: Dual Carrier HSUPA Enhancements for UTRAN CS","DC_HSUPA_CS-Core",2,"Rel-13","R2","2015-09-15","2015-12-15",1,"RP-151780","-","Nokia Networks",null,"no Perf. part¦compare REL-13 WI HSUPA_DB_MC 1/1/16: Compl:0%->100% 1/1/16: WID: RP-151607->RP-151780",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4034,721000,"   UE Conformance Test Aspects – Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-161071",null,"Intel",null,"tested REL-13 WI: LTE_eMDT2-Core26/9/16: Com;21/3/17: Compl:5%->100%",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4037,690067,"Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh",1,"Rel-13","R2","2015-09-15","2017-03-15",1,"RP-151624","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh",null,69,35,null,null,"2015-09-29","NA"]
[4040,700011,"   CT aspects of Indoor Positionning","UTRA_LTE_iPos_enh-CT",2,"Rel-13","C4","2015-10-12","2015-12-07",1,"CP-150612",null,"Ericsson, Jesús de Gregorio","jesus.de.gregorio@ericsson.com",null,"29.171, 29.172, 29.230, 29.002",70,36,null,null,"2015-12-07","NA"]
[4041,700053,"      CT4 aspects of Indoor Positionning","UTRA_LTE_iPos_enh-CT",3,"Rel-13","C4","2015-10-12","2015-12-07",1,"CP-150612",null,"Ericsson, Jesús de Gregorio","jesus.de.gregorio@ericsson.com","8/12/15: 0%->100","29.171, 29.172, 29.230, 29.002",70,36,null,null,"2015-12-07","2015-12-08"]
[4044,680163,"   Core part: Power saving enhancements for UMTS","UTRA_SDATA_POWSAV-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-151998","RP-151291","Ericsson",null,"no Perf. part¦follow-up WI of SI FS_UTRA_SDATA 29/09/15: Compl:0%->25% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-151092->RP-151292 29/09/15: Stat Rep: -->RP-151291 29/09/15: Release: Rel-14->Rel-13 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4048,680273,"   Perf. part: 700MHz E-UTRA FDD Band for Arab Region","LTE_FDD_700_ARAB-Perf",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151042","RP-151207","Etisalat",null,"REL-independent from REL-9 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13 ",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4052,0,"Release 13 Features on Internet of Things (IoT)","-",1,"Rel-13","SP,RP,CP,GP","2013-09-12","2015-05-12",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4055,700016,"   Stage 2 of CIoT","CIoT",2,"Rel-13","S2","2015-10-05","2015-10-05",1,"SP-150844",null,"Intel, Puneet Jain","puneet.jain@intel.com","7/3/16: 0%->95","23.401, 23.682, 23.251",70,36,null,null,"2015-12-07","2016-03-07"]
[4059,700051,"      CT3 aspects of CIoT","CIoT-CT",3,"Rel-13","C3","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->90¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 90%->100","29.061, 29.212",70,36,null,null,"2015-12-07","2016-06-13"]
[4062,720042,"   Charging Aspects of CIoT","CIoT-CH",2,"Rel-13","S5","2016-05-12","2016-06-13",1,"SP-160395",null,"Gardella, Maryse (Nokia)","Gardella, Maryse (Nokia)","32.25x¦13/6/16: 0%->100","32.25x, 32.240, 32.251, 32.274, 32.299, 32.298, 32.297",72,37,null,null,"2016-06-13","2016-06-13"]
[4065,700257,"      Perf. part: Narrowband Internet of Things (IOT)","NB_IOT-Perf",3,"Rel-13","R4","2015-12-15","2016-12-15",1,"RP-162134",null,"Vodafone",null,"22/3/16: WID: RP-152284->RP-160656¦1/7/16: WID: RP-160656->RP-16093326/9/16: Compl:0%->60%26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦20/12/16: Compl:60%->100%¦20/12/16: WID: RP-160933->RP-162134",null,70,36,null,null,"2016-01-01","2016-12-20"]
[4066,720043,"   Management for NB-IoT","NB_IOT-OAM",2,"Rel-13","S5","2016-05-12","2016-06-15",1,"SP-160396",null,"Huawei, Kai ZHANG","kai.zhangkai@huawei.com","13/6/16: 0%->100","28.657, 28.658, 28.659, 32.425",72,37,null,null,"2016-06-13","2016-06-13"]
[4069,700003,"   Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things Core part","CIoT_EC_GSM-Core",2,"Rel-13","G1,G2","2015-09-25","2016-05-12",1,"GP-151039",null,"Marteen Sunberg, Ericsson","Marteen.Sunberg@Ericsson.com","7/12/15:created by MCC to distinguish core versus test parts. 2/3/16: FCD: 11/15->05/16, 40->90%¦13/6/16: 90%->100",null,70,36,null,null,"2015-09-07","2016-06-13"]
[4074,660008,"   Study on Extended DRX cycle for Power Consumption Optimization","FS_eDRX",2,"Rel-13","S2","2014-12-03","2015-12-11",1,"SP-140881",null,"Miguel Griot, Qualcomm ","mgriot@qti.qualcomm.com","No Ran aspects yet. GERAN in FS_uPoD.29/1: TS number added Mar15: 0->30%¦June2015: Compl:30%->95, Exc S granted in SP-150352¦07/09/15: 95%->100",23.77,66,34,null,null,"2014-12-03","2015-09-07"]
[4077,690020,"      CT1 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100","24.301, 24.008, 29.118",69,35,null,null,"2015-09-07","2016-03-07"]
[4080,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[4084,690001,"   Extended DRX (eDRX) for GSM","eDRX_GSM",2,"Rel-13","G2,G1","2015-08-28","2016-05-12",0.44,"GPC150624",null,"John Diachina, Ericsson LM","John.Diachina@Ericsson.com","07/09/15: 0%->40¦7/12/15: 40%->100","43.064, 44.018, 44.060, 45.008, 48.018, 43.022",69,35,null,null,"2015-08-12","2015-12-07"]
[4087,670027,"Optimizations to Support High Latency Communications","HLcom",1,"Rel-13","S2","2014-09-19","2015-12-16",1,"SP-150030",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com",null,"23.401, 23.060, 23.682",67,34,null,null,"2015-03-05","2015-03-05"]
[4088,650035,"   Study on Optimizations to support High Latency communications","FS_HLcom",2,"Rel-13","S2","2014-09-19","2015-06-17",1,"SP-140635","-","Ericsson","hans.ronneke@ericsson.com","Dec.14: 0->30%. Mar15: 70%¦June2015: Compl:70%->100","New 23.709",65,33,null,null,"2014-08-05","2015-06-15"]
[4094,710067,"   UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-UEConTest",2,"Rel-13","R5","2016-03-15","2017-09-15",1,"RP-171156",null,"Ericsson",null,"testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[4095,690045,"EGPRS Access Security Enhancements in relation to Cellular IoT","EASE_EC_GSM",1,"Rel-13","S3","2015-09-16","2016-03-11",1,"SP-150462",null,"Vesa Torvinen, Ericsson",null,"7/12/15: 0%->5¦28/1/16: 33.420 added¦7/3/16: 5%->80¦11/6/16: 80%->98¦19/9/16: 98%->99¦21/3/17: 99%->100->99%¦7/6/17: 99%->100","New 33.420",69,35,null,null,"2015-09-16","2017-06-07"]
[4099,640350,"   TR on Security for Group based Enhancements","GROUPE",2,"Rel-13","S3","2014-06-18","2015-06-12",1,"SP-140706","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. 3/3/15: 5->10%.¦June2015: Compl:10%->60¦11/12/15: 60%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[{"$f":"A4102+1","v":4102},680028,"      CT1 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->15¦7/12/15: 15%->100¦7/12/15: WID:CP-150240->CP-150816","24.008, 24.301",68,35,null,null,"2015-06-15","2015-12-07"]
[4105,640049,"Monitoring Enhancements","MONTE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140705","-","Intel","puneet.jain@intel.com","Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added;",32.277999999999999,64,33,null,null,"2014-05-30","2015-10-05"]
[4109,640449,"   Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[4112,680025,"      CT1 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->95¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 95%->100","24.301, 24.008",68,35,null,null,"2015-06-15","2015-12-07"]
[4115,640046,"Dedicated Core Networks","DECOR",1,"Rel-13","S2","2014-06-18","2016-03-11",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","06/15: WID: SP-140707-> SP-150249","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[4117,640246,"   Stage 2 for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-23","2015-03-18",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Mar15: 0->70%¦June2015: Compl:70%->100, WID: SP-140707-> SP-150249","23.060, 23.401, 23.236",64,33,null,null,"2014-05-30","2015-06-18"]
[4120,690013,"      CT4 aspects for Dedicated Core Networks CT aspects","DECOR-CT",3,"Rel-13","C4","2015-06-25","2016-03-11",1,"CP-150423",null,null,null,"7/12/15: 70%->90. FCD -> 03/16, ES CP-150617¦7/3/16: 90%->100","29.274, 29.060, 23.003, 29.272, 29.002, 29.305, 23.008, 29.230, 29.303, 23.007",69,35,null,null,"2015-09-07","2016-03-07"]
[4124,610130,"   TR on Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-06-18",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements)","New 22.853",61,31,null,null,"2013-08-26","2014-05-27"]
[4127,640148,"   TR for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S2","2014-06-18","2015-03-18",1,"SP-140704","-","Intel, Puneet Jain","puneet.jain@intel.com","Dec.14: 30->65%. Mar15: 75%¦June2015: Compl:75%->100","New 23.708",64,33,null,null,"2014-05-30","2015-06-15"]
[4130,640448,"   Security for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140704","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[4134,621000,"Rel-13 LTE Carrier Aggregation","LTE_CA_Rel13",1,"Rel-13","R4","2013-12-09","2018-12-14",0.95,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,62,32,null,null,"2012-12-14","2015-01-15"]
[4136,690180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4139,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4142,620123,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27","LTE_CA_B8_B27-Core",3,"Rel-13","R4","2013-12-09","2015-12-15",0.3,"RP-140120","RP-151131","KT","ilwhan.kim@kt.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101, 36.104, 36.133, generic 36.851",62,32,null,null,"2013-12-07","2015-09-29"]
[4145,620132,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27-Core",3,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","RP-151131","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Thu 18/06/15->Mon 15/06/15¦Compl:25%->25%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2015-09-29"]
[4149,630233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22-Perf",3,"Rel-13","R4","2014-03-11","2015-06-15",1,"RP-140094","RP-150536","Orange, Ericsson","erika.tejedor@ericsson.com","CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-141732->RP-150536","36.141, 36.307",63,32,null,null,"2014-03-10","2015-06-18"]
[4152,640222,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","RP-150536","U.S. Cellular","sebastian.thalanany@uscellular.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:0%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, 36.133, 36.141, 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[4156,640032,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140974","-","Huawei","leo.liuye@huawei.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4157,640132,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42-Core",3,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140974","RP-150536","Huawei","leo.liuye@huawei.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:30%->50%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:50%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-15","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-06-18"]
[4163,650138,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4164,650238,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4167,650239,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4170,650240,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141168","RP-151131","Ericsson","imadur.rahman@ericsson.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-1","36.141, 36.307",65,33,null,null,"2014-06-16","2016-01-01"]
[4174,650042,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141674","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4177,650043,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141336","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4181,650144,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->75% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:75%->100% 03/07/1","36.101, 36.104, New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4182,650244,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4188,650247,"      Perf. Part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_C_B42_3DL-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-151027","RP-150536","CATT","Yuexia Song (songyuexia@catt.cn)","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Stat ","36.141, 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4189,650049,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41",2,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141290","-","China Mobile","PAN, Qun (panqun@chinamobile.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4192,650051,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","-","Samsung","xutao.zhou@samsung.com","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4195,650053,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29","LTE_CA_B2_B5_B29",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141667","-","Huawei","SHAN Huiping (shanhuiping@huawei.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4199,660172,"      Core part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C-Core",3,"Rel-13","R1","2014-12-15","2015-12-15",1,"RP-151984","RP-151285","Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: Compl:10%->40% 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Compl:4",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4202,660080,"   HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142237",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-15"]
[4207,660281,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4210,660282,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4213,660283,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777","RP-151131","China Unicom","China Unicom","03/07/15: Compl:0%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4214,660084,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141791",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4217,660085,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42","LTE_CA_B21_B42_B42",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141792",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4221,660186,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150614","RP-151131","ZTE","ZTE","1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP-",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4224,660187,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4228,660288,"      Perf. Part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7_BWset-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141881","RP-150536","Ericsson","Ericsson","Acronym changed from LTE_CA_B3_B7_B7-Perf 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4232,660090,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141946",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4235,660091,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141947",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4238,660092,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141949",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4239,660192,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151261","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->95% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4242,660193,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->95% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4246,660294,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150719","RP-150536","Nokia Networks","Nokia Networks","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4249,660295,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4253,660097,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142206",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4257,660198,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-151071","RP-150536","Huawei","Huawei","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4260,660199,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150234","RP-150536","Huawei","Huawei","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4261,660299,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150234","RP-150536","Huawei","Huawei","1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4264,661200,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209","RP-151131","Huawei","Huawei","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4267,661201,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238","RP-150536","Intel","Intel","03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4270,661202,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28","LTE_CA_B3_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142244","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4275,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4278,661105,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150450","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4282,661206,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150452","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4285,661207,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150451","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4286,661008,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142203",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4289,661009,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4295,661011,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141975",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4297,661211,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4300,661212,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13","LTE_CA_2UL_R13-A3-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150409","RP-151131","Ericsson","Ericsson","1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4303,661213,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 18/12/18->Tue 15/12/15 1st Apr 15: Stat Rep: -->RP-150013 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150536->RP-151131 ¦",null,66,31,null,null,"2013-09-14","2016-01-01"]
[4307,670066,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150122",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4310,670067,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150123",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4311,670167,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150643","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4316,670069,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150125",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4318,670269,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4322,670071,"   Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4325,670072,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12","LTE_CA_B2_B7_B12",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150431",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4329,670173,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7-Core",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-1511311/1/16:22/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4332,670174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4335,670175,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12","LTE_CA_B2_B4_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150660","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4337,670076,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150074",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4340,670077,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150075",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4343,670078,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150434",null,"SK Telecom",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4347,670179,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4350,670180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4354,670281,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064","RP-151131","KDDI",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4357,670282,"      Perf. Part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13","LTE_CA_2UL_R13-A4-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150616","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[{"$f":"A4358+1","v":4358},670083,"   LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150479",null,"Nokia Corporation",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4362,670184,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246","RP-150536","Huawei",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4365,670185,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151177","RP-151131","CMCC",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4369,670286,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438","RP-151131","CATT",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4372,680277,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11","LTE_CA_B1_B8_B11-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150609","RP-151131","Softbank Mobile",null,"29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4375,680278,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32-Perf",3,"Rel-14","R4","2015-06-15","2016-03-15",0.9,"RP-150864","RP-151131","Ericsson",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->90%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4379,680080,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4383,680181,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","RP-151131","Nokia Networks",null,"29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-1511311/1/16: Compl:",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4386,680182,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","RP-151131","KDDI",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4387,680282,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","RP-151131","KDDI",null,"29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4390,680283,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151158","RP-151131","KDDI",null,"29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4394,680086,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4397,680087,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4400,680088,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4404,680189,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4408,680290,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4411,680291,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4412,680092,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4415,680093,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4419,680194,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[{"$f":"A4422+1","v":4422},680195,"      Core part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4425,680196,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4429,680297,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4433,681000,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4434,681100,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4437,681101,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4440,681102,"      Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4444,681203,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4447,681204,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","RP-151131","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4450,681205,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4455,680174,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","RP-151131","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4458,680176,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","RP-151131","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4459,680276,"      Perf. part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","RP-151131","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4462,680272,"      Perf. part: Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151037","RP-151242","Huawei",null,"29/09/15: Stat Rep: -->RP-151242 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4465,680184,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42","LTE_CA_B41_B41_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151562","RP-151131","ZTE",null,"29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131",null,68,35,null,null,"2015-08-12","2016-01-01"]
[4469,690273,"      Perf. part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4471,690174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4476,690076,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4480,690177,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 41, and Band 41 ","LTE_CA_B3_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151448","-","ZTE",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4483,690178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4484,690278,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4487,690279,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4490,690282,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,1,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4496,690284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4498,690185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4502,690289,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42","LTE_CA_B1_B3_B19_B42_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151159","-","NTT DOCOMO",null,null,"36.857-13",69,35,null,null,"2015-09-29","2016-01-01"]
[4505,690290,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4508,690291,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-160141","-","Telstra",null,"22/3/16: Compl:95%->100%;",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4509,690092,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151513","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4512,690093,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","NA"]
[4517,690294,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4520,690295,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12 ¦",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4523,710001,"(Small) Test Technical Enhancements and Improvements for Rel-13","TEI13_Test",1,"Rel-13","SP,CP,RP,GP","2013-09-18","2015-12-21",1,"-","PCG-31","-","-","Created upon demand of RAN5","-",61,31,null,null,"2015-01-12","2016-02-24"]
[4527,620012,"Study on Power saving for Machine-Type Communications (MTC) devices","FS_uPoD",1,"Rel-13","G2,G1","2014-08-12","2015-08-14",1,"GP-131136","-","China Mobile","Jing Han (hanjing@chinamobile.com)","GP#65 completion 02/15=>05/15. GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP). Dec.14: 30->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100",43.869,60,32,null,null,"2013-11-22","2015-09-30"]
[4530,670036,"Study on Battery Efficient Security for very low Throughput Machine Type Communication Devices","FS_BEST_MTC_Sec",1,"Rel-13","S3","2015-03-13","2015-12-11",1,"SP-150171",null,"Barry, Aguibou, VODAFONE Group Plc","Barry, Aguibou, VODAFONE Group Plc","TR number added¦June2015: Compl:0%->10¦7/12/15: 10%->50¦11/12/15: 50%->75¦7/3/16: 75%->95¦19/9/16: 95%->100¦6/10/16: 33.163 added;","32.863; 33.163",67,34,null,null,"2015-03-13","2016-10-06"]
[4533,610031,"Study on enhancements for Infrastructure based data Communication Between Devices","FS_eICBD",1,"Rel-13","S1","2013-09-14","2014-09-17",1,"SP-130418","S1-143309","KPN","toon.norp@tno.nl","SP#65 completed. TR 22.807v200 for Approval",22.806999999999999,61,31,null,null,"2013-08-26","2014-08-28"]
[4534,0,"Release 13 other Studies","-",1,"Rel-13","SP,R2","2013-09-12","2015-12-25",1,"-","-","-","-","-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4538,610033,"(SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO","FS_CSIPTO",1,"Rel-13","S1","2013-09-13","2014-06-18",1,"SP-130417","-","Intel","Eric.siow@intel.com","SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET",22.827999999999999,61,31,null,null,"2013-08-26","2014-12-12"]
[4542,520035,"Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group","FS_UMONC_sas",1,"Rel-13","S2","2011-06-08","2014-12-12",1,"SP-140403","-","China Telecom","Jinyan Li (lijy@ctbri.com.cn)","SP#64 revived. Added to the Title \"for Service, Application and Subscriber Group\", Changed Acronym: FS_UMONC=>FS_UMONC_sas",23.858000000000001,52,27,null,null,"2011-05-19","2014-06-19"]
[4545,520235,"   Deleted - SA5 part of Study on Usage Monitoring Control enhancement","-",2,"-","S5","2012-03-02","2012-09-12",1,"SP-120554","-","Huawei","Hui Cai (Sarah.Cai@huawei.com)","SP#57 stopped",32.857999999999997,52,27,"SP-57","PCG-29","2011-05-19","2012-08-30"]
[4548,610045,"Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function","FS_D_MLB_SON_OAM",1,"Rel-13","S5","2014-09-15","2016-06-13",1,"SP-130430","-","Cisco","Vladimir Yanover (vyanover@cisco.com)","SP#64 completion 06/14=>12/14. Dec.14: 20->25%, CD: 12/14->06/15¦June2015: Compl:25%->30¦7/12/15: 30%->45¦7/3/16: 45%->50¦13/6/16: 50%->100",32.86,61,31,null,null,"2013-09-09","2016-06-13"]
[4552,590010,"Study on Review of dedicated 3GPP UICC features","FS_Red_UCe",1,"Rel-13","C6","2013-03-13","2015-12-16",1,"CP-130168","-","BlackBerry","Adrian Buckley (abuckley@blackberry.com)","CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100%",31.901,59,30,null,null,"2013-02-20","2014-12-03"]
[4555,640017,"Study on MIMO OTA antenna test function for LTE","FS_LTE_MIMO_OTA_ATF",1,"Rel-13","R4","2013-03-18","2014-12-15",1,"RP-141325","RP-142045","Keysight","Moray_Rumney@keysight.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:60%->100%¦Stat Rep: RP-141124->RP-142045","36.509, new 37.978",64,33,null,null,"2014-06-16","2015-01-12"]
[4558,600020,"Study on Positioning enhancements for E-UTRA","FS_LCSenh_LTE",1,"Rel-13","R4","2012-05-01","2014-12-15",1,"RP-130680","RP-142224","Huawei","Jie Cui (cuijie@huawei.com)","WID: RP-140667->RP-130680¦Stat Rep: RP-140639->RP-142224. 3/3/15: R1 removed as 2nd responsible WG","LTE 36.855",60,31,null,null,"2013-06-17","2015-03-03"]
[4559,620045,"Study on Multi-RAT joint coordination","FS_MultiRAT_JC",1,"Rel-13","R4","2013-12-06","2015-06-15",1,"RP-150417","RP-150807","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","¦WID: RP-142043->RP-132086¦Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807","UTRA, LTE 37.870",62,32,null,null,"2013-11-27","2015-06-18"]
[4563,650015,"Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","FS_LTE_EBF_FDMIMO",1,"Rel-13","R1","2014-09-12","2015-06-15",1,"RP-150930","RP-150734","Nokia Networks (DL), Samsung (UL)","bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com","3/3/15: WID: RP-141831¦Stat Rep: -->RP-141822, impacted TR number added. 1st Apr 15: Compl:30%->45% 1st Apr 15: Stat Rep: RP-141822->RP-150346. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake) 03/07/15: Compl:45%->100% 03/07/15: WID: RP-141831->RP-1",36.896999999999998,65,33,null,null,"2014-09-15","2015-06-18"]
[4567,660063,"Study on possible additional configuration for LTE TDD","FS_LTE_TDD_add_config",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150652","RP-151283","NTT DOCOMO, Hideaki Takahashi","NTT DOCOMO","TR 36.825 rapporteur: CATT. TR number added. 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150151 03/07/15: Compl:5%->35% 03/07/15: WID: RP-142248->RP-150652 03/07/15: Stat Rep: RP-150151->RP-150805 29/09/15: Compl:35%->100% 29/09/15: Stat Rep: R",36.825000000000003,66,34,null,null,"2015-01-12","2015-09-29"]
[4570,660066,"Study on Support of single-cell point-to-multipoint transmission in LTE","FS_LTE_SC_PTM",1,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150177","RP-150695","Jeff GAO","gaoyongqiang@huawei.com","deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695",36.89,66,34,null,null,"2015-01-12","2015-06-18"]
[4573,660069,"Study on RAN sharing enhancements for UMTS","FS_RSE_UTRA_GUSH",1,"Rel-13","R3","2014-12-15","2015-06-15",1,"RP-150686","RP-150684","Huawei","Huawei","03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3)",25.756,66,34,null,null,"2015-01-12","2015-10-07"]
[4577,670040,"Study on regulatory aspects for flexible duplex for E-UTRAN","FS_LTE_flex_duplex_reg",1,"Rel-13","RP","2016-06-15","2016-12-15",1,"RP-150470","RP-151307","LG Electronics Inc.",null,"TR added 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: -->RP-150770 29/09/15: Compl:5%->100% 29/09/15: Stat Rep: RP-150770->RP-151307",36.881999999999998,67,34,null,null,"2015-04-01","2015-09-29"]
[4580,670087,"Study on Phase 1 of the Support of Emergency services over WLAN","FS_SEW",1,"Rel-13","S2","2015-03-12","2015-06-18",1,"SP-150251",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251","new 23.771",67,34,null,null,"2015-04-01","2015-06-18"]
[4584,680055,"Study on Network Assistance for Network Synchronization in LTE","FS_LTE_NW_SYNC",1,"Rel-14","R3","2015-06-15","2016-12-15",1,"RP-151252",null,"Huawei",null,"Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: WID: RP-151084->RP-151252 29/09/15: Stat Rep: -->RP-151240 22/3/16: Compl:60%->80%¦22/3/16: CD:Tue 15/03/16->Wed 15/06/16¦ ¦","New 36.898",68,35,null,null,"2015-07-03","2016-12-20"]
[4585,680056,"Study onLTE Advanced inter-band Carrier Aggregation of Band 20 and Band 28","FS_LTE_CA_B20_B28",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151515","RP-151231","TeliaSonera",null,"29/09/15: Compl:0%->20% 29/09/15: WID: RP-151101->RP-151515 29/09/15: Stat Rep: -->RP-151231 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4588,720087,"Study on multi-node testing for LAA","FS_LTE_LAA_multinode_test",1,"Rel-13","R4","2016-06-15","2017-06-15",1,"RP-162144",null,"Huawei",null,"coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672¦20/12/16: Compl:10%->30%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17¦20/12/16: WID: RP-161672->RP-162144¦21/3/17: CD:Wed 15/03/17->Thu 15/06/17;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[4592,490030,"SIPTO Service Continuity of IP Data Session","SIPTO_SC",1,"Rel-12","S1","2010-09-23","2011-09-21",1,"SP-100589","-","Vodafone","mona.mustapha@vodafone.com","SP#57 moved to Rel-12 (Reason: Stage 2 for requirements in TS 22.101 clause 4.3.5 have not been implemented in Rel-11). Linked to Rel-10 Local IP Access and Selected Internet IP Traffic Offload (LIPA_SIPTO)","Stage 1",49,25,null,null,"2010-09-01","2012-08-30"]
[4595,500131,"   Stage 1 for MOSAP","MOSAP-SA1",2,"Rel-12","S1","2010-12-16","2011-09-21",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#53 completed",22.277999999999999,50,26,null,null,"2010-11-29","2012-06-09"]
[4598,520027,"IMS Network-Independent Public User Identities","INIPUI",1,"Rel-12","S1","2011-06-08","2012-06-20",1,"SP-120425","-","Vodafone","mona.mustapha@vodafone.com","Triggered by Rel-11 TR 22.894 (FS_INIPUI)","Stage 1",52,27,null,null,"2011-05-19","2012-06-19"]
[4602,550024,"Advanced IP Interconnection of Services (IPXS) for national interconnect","IPXSNAT",1,"Rel-12","S1","2012-03-06","2012-09-12",1,"SP-120428","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051.","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[4605,550125,"   Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks","SSO_Int-SA1",2,"Rel-12","S1","2012-03-08","2012-09-12",1,"SP-120184","-","InterDigital","christopher.wallace@interdigital.com","SP#57 completed",22.100999999999999,55,28,null,null,"2012-02-22","2012-08-07"]
[4607,560119,"   Stage 1 for Explicit Communication Transfer Blind (ECT Blind) service interactions","ECTB-SA1",2,"Rel-12","S1","2012-06-18","2012-06-20",1,"SP-120301","-","Orange","philippe.lottin@orange.com","SP#56 new WID approved & work completed. Clarify the service interactions between ECT Blind and other MMTEL Supplementary Services",22.172999999999998,56,29,null,null,"2012-05-14","2012-06-08"]
[4610,580060,"Sequential Flexible Alerting","SEQ_FA",1,"Rel-12","S1","2012-12-10","2012-12-12",1,"SP-120895","-","Orange","bruno.tossou@orange-ftgroup.com","SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. 22/01: acronym modified","Stage 1",58,30,null,null,"2012-11-16","2015-01-22"]
[4613,580161,"   Stage 1 for Language and Modality Information for communications","LangInfo-SA1",2,"Rel-12","S1","2012-12-11","2013-03-06",1,"SP-130108","-","Orange","philippe.lottin@orange.com","SP#59 completed. Updated WID SP-120937=>SP-130108",22.228000000000002,58,30,null,null,"2012-11-16","2013-02-19"]
[4617,590141,"   Deleted - Stage 1 for Application and Service Access Control","ASAC-SA1del",2,"Rel-12","S1","2013-03-06","2013-06-19",1,"SP-130124","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster)",22.010999999999999,59,30,"SP-60","PCG-31","2013-02-19","2013-02-19"]
[4620,0,"SA1/SA2 Features","-",1,"Rel-12","SP,CP,RP","2013-05-17","2014-03-07",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[4623,500328,"   BB1: SIPTO at the Local Network","LIMONET-SIPTO",2,"Rel-12","S2","2010-10-22","2014-03-05",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#60 completed","23.060, 23.401",50,26,null,null,"2010-11-26","2013-06-06"]
[4626,530115,"         CT4 part of Stage 3 CN aspects of SIPTO at the Local Network","LIMONET-SIPTO-CT4",4,"Rel-12","C4","2011-09-24","2013-09-06",1,"CP-130274","-","Huawei","peter.schmitt@huawei.com","CP#61 completed","23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.303",53,27,null,null,"2011-08-27","2013-08-10"]
[4631,500228,"      Deleted - Stage 2 for stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network","LIMONET-LIPA-del1",3,"Rel-12","S2","2010-10-22","2012-12-12",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility)","23.060, 23.401",50,26,"SP-58","PCG-30","2010-11-26","2013-02-27"]
[4632,530016,"      Deleted - Stage 3 CN aspects of LIPA Mobility","LIMONET-LIPA-del2",3,"Rel-12","C1,C4","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","Stage 3",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[4635,510049,"Operator Policies for IP Interface Selection","OPIIS",1,"Rel-12","S2,C1","2011-03-23","2013-12-06",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network)","Stage 2/3",51,26,null,null,"2011-02-21","2013-02-27"]
[4638,600047,"   Stage 3 for Operator Policies for IP Interface Selection","OPIIS-CT",2,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130215","-","LG Electronics","Jaehyun Kim (jaehyun7.kim@lge.com)","CP#62 completed. Specify Inter-APN Routing Policies for selecting an IP interface to route IP flows among a choice of available interfacES in CP-150both 3GPP and non-3GPP accesses","24.302, 24.312",60,31,null,null,"2013-05-28","2013-11-18"]
[4642,590013,"   Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",2,"Rel-12","C1,C4","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS","Stage 3",59,30,null,null,"2013-02-16","2013-11-18"]
[4645,530042,"IMS-based Telepresence","IMS_TELEP",1,"Rel-12","S1,C1,C3,C4,IETF","2010-03-22","2014-12-09",0.93,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified","Stage 1/2/3",53,27,null,null,"2011-07-19","2012-06-08"]
[4647,580001,"   CT part for IMS Telepresence (Stage 2/3)","IMS_TELEP",2,"Rel-12","C1,C3,C4,IETF","2010-03-22","2014-12-09",0.93,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 updated WID CP-140196=>CP-140624. 2/4/15: acronym changed to IMS_TELEP","Stage 2/3",58,30,null,null,"2012-11-19","2015-04-02"]
[4653,641004,"      (IETF) Session Signaling for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-signaling) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",0.9,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-signaling); 9/4/21: RFC 8848 added;","draft-ietf-clue-signaling; RFC 8848",64,33,null,null,"2014-06-06","2021-04-09"]
[4656,610011,"      CT4 part of IMS Telepresence (Stage 2/3)","IMS_TELEP",3,"Rel-12","C4","2013-09-13","2014-12-09",1,"CP-140624","CP-140477","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140477. Mar.15: 0->100%. 2/4/15: acronym changed to IMS_TELEP","23.333, 29.333",61,31,null,null,"2013-08-11","2015-04-02"]
[4657,560020,"Group Communication System Enablers for LTE","GCSE_LTE",1,"Rel-12","S1,S2,S3,C3,C4,R3,C1","2012-06-18","2015-03-13",1,"SP-140433","-","Nokia Networks","Juergen.Merkel@nsn.com","Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety","Stage 1/2/3",56,29,null,null,"2012-05-14","2014-09-07"]
[4660,590038,"   Stage 2 for Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S2","2013-03-12","2014-09-16",1,"SP-140433","-","Nokia Networks","rainer.liebhart@nsn.com ","SP#65 completed. Updated WID SP-140113=>SP-140433. SP#63 TS 23.468v100 for 1-step Approval","New 23.468",59,30,null,null,"2013-02-21","2014-09-15"]
[4663,640010,"   CT aspects of Group Communication System Enablers for LTE","GCSE_LTE-CT",2,"Rel-12","C3,C4,C1","2014-06-13","2014-12-09",1,"CP-140559","-","Nokia Networks","thomas.belling@nsn.com","CP#65 updated WID CP-140452=>C3-143199 (added CT1 part)","Stage 3",64,33,null,null,"2014-06-10","2014-09-06"]
[4667,640037,"   Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM",2,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","-","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","-","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4670,560021,"   Stage 1 for Support for Interworking with M2M Service Enablement","MTCe-SIMSE",2,"Rel-12","S1","2012-06-18","2013-03-06",1,"SP-120436","-","KPN","toon.norp@tno.nl","SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer)",22.367999999999999,56,29,null,null,"2012-05-14","2013-02-19"]
[4672,560722,"   TR on Security aspects of Machine-Type Communications","MTCe-SA3TR",2,"Rel-12","S3","2009-12-10","2014-03-07",1,"SP-130327","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#63 completed. TR 33.868v100 for 1-step Approval. Was Rel-10 UID_460023 (Security for NIMTC). Was Rel-11 UID_490028 (TR on Security aspects of MTC). SP#56 activity transferred to Rel-12 Feature MTCe","New 33.868",56,29,null,null,"2012-08-16","2014-02-27"]
[{"$f":"A4678+1","v":4678},630101,"         CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement","MTCe-SDDTE-CT",4,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#65 completed. Updated WID CP-140272=>CP-140489","29.002, 29.336, 23.008, 29.337, 29.338, 29.230",63,32,null,null,"2014-01-29","2014-07-29"]
[4681,560322,"   BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",2,"Rel-12",null,"2012-06-18","2016-05-12",0.93,"SP-120442","-","Ericsson","peter.hedman@ericsson.com","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[4682,561622,"      TR on Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",3,"Rel-12","S2","2012-06-18","2013-12-11",1,"SP-120442","-","Ericsson","peter.hedman@ericsson.com ","SP#62 completed. TR 23.887v200 for Approval","New 23.887",56,29,null,null,"2012-04-13","2013-11-28"]
[4685,620107,"         CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT1",4,"Rel-12","C1","2013-12-06","2014-09-11",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","CP#65 completed","24.008, 24.301",62,32,null,null,"2013-11-18","2014-07-28"]
[4688,690068,"         UE Conformance Test Aspects - UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-UEConTest",4,"Rel-12","R5","2015-09-15","2016-03-15",1,"RP-151161","-","Ericsson",null,"tested: MTCe-UEPCOP was a REL-12 SA2 WI¦NAS over LTE and UTRA;1/1/16: Compl:0%->25%22/3/16: C",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4692,620043,"   RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN",2,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","-","ZTE","sergio.parolari@zte.com.cn","Triggered by TR 23.887 Machine Type and other mobile data applications Communications Enhancements (MTCe), TR 37.869 Study on Enhancements MTC and other Mobile Data Applications¦RAN aspects (FS_MTCe_RAN), Rel-11 TR 23.888 SIMTC","UTRA, LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[4697,670048,"   UE Conformance Test Aspects - Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2016-12-15",1,"RP-160069",null,"Ericsson",null,"03/07/15: Compl:0%->13% 03/07/15: WID: RP-150135->RP-150838 03/07/15: Stat Rep: ->RP-150833 29/09/15: Compl:13%->25% 29/09/15: Stat Rep: RP-150833->RP-151165 ¦1/1/16: Compl:25%->70% ¦1/1/16: CD:Tue 15/12/15->Tue 15/03/16 ",null,67,34,null,null,"2015-04-01","2016-12-20"]
[4700,560124,"   BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F",2,"Rel-12","S2,S5,C3,C1,C4","2012-06-20","2014-12-12",1,"SP-120275","-","Huawei","marco.spini@huawei.com","-","-",56,29,null,null,"2012-06-04","2013-01-08"]
[4703,610012,"      Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",3,"Rel-12","C3,C1,C4","2013-09-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","-","Stage 3",61,31,null,null,"2013-08-12","2014-04-16"]
[4706,620010,"         CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C4","2013-12-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed",29.273,62,32,null,null,"2013-11-19","2014-04-16"]
[4707,600042,"      Policy and Charging Enforcement Function (PCEF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3)","P4C-F-CH_P",3,"Rel-12","S5","2013-06-21","2014-09-17",1,"SP-130261","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#65 completed. Introduce Charging Characteristics in Convergent scenario, Include missing fixed user location information for NSWO ","Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299)",60,31,null,null,"2013-06-02","2014-08-26"]
[4710,560824,"      TR on Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI)","P4C-TI-SA2TR",3,"Rel-12","S2","2012-06-20","2013-06-19",1,"SP-120444","-","Alcatel-Lucent","konstantin.livanos@alcatel-lucent.com","SP#60 completed","new 23.839",56,29,null,null,"2012-06-04","2013-06-17"]
[4714,560524,"   Deleted - BB5: Policy and Charging Control for supporting Layer 2 traffic in fixed broadband access network (P4C-FL2)","P4C-FL2",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120279","-","Huawei","marco.spini@huawei.com","SP#58 stopped (at 0% completion)","23.139, 23.203, new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[4718,560125,"   TR on IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SATR",2,"Rel-12","S2,S1","2012-06-18","2013-06-19",1,"SP-120862","-","Deutsche Telekom","michele.zarri@telekom.com","SP#60 completed","new 23.897",56,29,null,null,"2012-05-11","2013-06-06"]
[4721,610107,"      CT1 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",3,"Rel-12","C1","2013-09-06","2014-12-09",1,"CP-140197","CP-140607","Deutsche Telekom","michael.kreipl@telekom.de","CP#65 completion 09/14=>12/14. Exception in CP-140607. Dec.14: 85->100%","23.218, 24.229, 24.525 (transfer of ETSI 182 025)",61,31,null,null,"2013-08-10","2014-12-04"]
[4725,560226,"   Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SA2",2,"Rel-12","S2","2012-06-22","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","23.402, 23.865",56,29,null,null,"2012-11-22","2013-11-28"]
[4728,570028,"Deleted - IMS Registration Control","IMS_RegCon",1,"Rel-12","S1,S2,C1,C4","2012-01-31","2013-12-11",1,"SP-120735","-","China Mobile","lulu@chinamobile.com","SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information)","Stage 1/2/3",57,29,"SP-62","PCG-32","2012-08-06","2013-12-10"]
[4731,600016,"   Deleted - CT aspects of IMS registration control","IMS_RegCon-CT",2,"Rel-12","C1,C4","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","Stage 2/3",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[4732,600116,"      Deleted - CT1 aspects of CT aspects of IMS registration control (Stage 2/3)","IMS_RegCon-CT1",3,"Rel-12","C1","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","23.218, 24.229",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[4735,580159,"   Stage 1 for Proximity-based Services","ProSe-SA1",2,"Rel-12","S1","2012-12-13","2013-06-19",1,"SP-140574","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#60 completed","22.115, 22.278",58,30,null,null,"2012-11-16","2014-09-15"]
[4739,651104,"   (IETF) Security for Proximity-based Services (ietf-avtcore-srtp-aes-gcm)","ProSe",2,"Rel-12","S3-IETF","2014-09-12","2014-12-09",1,"SP-140574","-","Atle Monrad","atle.monrad@ericsson.com","Submitted to IESG for publication¦7/3/16: 75%->100; 9/4/21: RFC 7714 added;","RFC 7714 (was ietf-avtcore-srtp-aes-gcm); RFC 7714",65,33,null,null,"2014-09-15","2021-04-09"]
[4743,630006,"   CT aspects of Proximity-based Services (Stage 3)","ProSe-CT",2,"Rel-12",null,"2014-03-05","2014-12-09",1,"CP-140290","-","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#64 updated WID CP-140194=>CP-140290","Stage 3",63,32,null,null,"2014-01-29","2014-03-03"]
[4746,630306,"      CT4 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C4","2014-03-05","2014-12-09",1,"CP-140290","CP-140484","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. TS 29.344/5v100 for 1-step Approval. Exception in CP-140484. Dec.14: 90->100","29.272, 23.008, 23.003, New TSs (29.344, 29.345)",63,32,null,null,"2014-01-29","2014-12-04"]
[4750,630230,"      Perf. part: LTE Device to Device Proximity Services","LTE_D2D_Prox-Perf",3,"Rel-12","R4","2014-03-11","2015-12-15",1,"RP-142043","RP-151276","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","¦CD:Sat 15/03/14->Sun 15/03/15¦Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:10%->25% 1st Apr 15: Stat Rep: RP-141894->RP-150094 03/07/15: Compl:25%->70% 03/07/15: Stat Rep: RP-150094->RP-150760 29/09/15: Compl:70%->95% 29/09/15: CD:Tue 15/09/15->","36.101, 36.133",63,32,null,null,"2014-03-10","2016-01-01"]
[4753,580162,"   Stage 1 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S1","2012-12-14","2013-06-19",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","SP#60 completed","22.101, 22.228",58,30,null,null,"2012-11-16","2013-09-09"]
[4756,631001,"   (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-overview)","IMS_WebRTC",2,"Rel-12","C1-IETF","2013-06-25","2014-12-12",0.9,"SP-130707","-","Uwe Rauschenbach","Uwe Rauschenbach","In WGLC. Mar15: responsible WG changed from S2-IETF; 23/4/20: 50%->90; 9/4/21: RFC 8825 added;","draft-ietf-rtcweb-overview; RFC 8825",63,32,null,null,"2014-02-10","2021-04-09"]
[4757,880055,"   (IETF) WebRTC Data Channel Establishment Protocol (draft-ietf-rtcweb-data-protocol)","IMS_WebRTC",2,"Rel-12","C1-IETF","2013-06-25","2014-12-12",0.9,"CP-140192",null,null,null,"9/4/21: RFC 8832 added;","RFC 8832",88,45,null,null,"2020-06-26","2021-04-09"]
[4760,630003,"   CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT",2,"Rel-12","C1,C4,IETF","2014-03-05","2019-03-07",0.97,"CP-140192","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","-","Stage 3",63,32,null,null,"2014-01-29","2014-09-06"]
[4765,641007,"      (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-stun-consent-freshness)","IMS_WebRTC-stun",3,"Rel-12","C1-IETF","2014-03-06","2014-12-09",1,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Mar15: Publication requested¦7/3/16: 50%->100; 9/4/21: RFC 7675 added;","draft-ietf-rtcweb-stun-consent-freshness; RFC 7675",64,33,null,null,"2014-06-06","2021-04-09"]
[4768,660031,"      Deleted - (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id)","IMS_WebRTC-holmb",3,"Rel-12","C1-IETF","2014-09-12","2014-12-09",1,"CP-140192",null,"christer.holmberg@ericsson.com",null,"7/3/16: 25%->100 since deleted (draft no longer needed). ","draft-holmberg-sipcore-auth-id",66,34,null,null,"2014-12-04","2016-03-07"]
[4771,580163,"   Stage 2 for Usage Monitoring Control PCC enhancement","UMONC",2,"Rel-12","S2","2012-12-13","2013-03-06",1,"SP-120928","-","ZTE","bi.yifeng@zte.com.cn ","SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System)",23.202999999999999,58,30,null,null,"2012-11-18","2013-02-27"]
[4775,600011,"   Charging for Application Based Charging","ABC-CT5",2,"Rel-12","S5","2013-06-19","2014-06-18",1,"SP-130328","-","Openet Telecom","alan.mcnamee@openet.com","SP#64 completed","32.240, 32.251, 32.296, 32.298, 32.299",60,31,null,null,"2013-05-29","2014-06-10"]
[4778,610138,"   Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-SA2",2,"Rel-12","S2","2013-09-11","2014-03-07",1,"SP-130391","-","ZTE","Tricci So (tso@zteusa.com)","SP#63 completed",23.402000000000001,61,31,null,null,"2013-07-25","2014-02-04"]
[4779,610009,"   Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",2,"Rel-12","C1,C4","2013-09-09","2014-12-09",1,"CP-130715","-","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#62 updated WID CP-130580=>CP-130715","Stage 3",61,31,null,null,"2013-08-10","2013-11-28"]
[4785,610040,"Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN",1,"Rel-12","S2,C3,C1,C4","2013-09-12","2014-09-11",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[4786,610140,"   Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-SA2",2,"Rel-12","S2","2013-09-12","2014-03-07",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","SP#63 completed","23.203, 23.228, 23.402",61,31,null,null,"2013-07-25","2014-02-04"]
[4790,620308,"      CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed","29.273, 29.274, 29.275, 29.328, 29.329",62,32,null,null,"2013-11-19","2014-07-28"]
[4793,650017,"   Charging aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CH",2,"Rel-12","S5","2014-09-15","2014-09-17",1,"SP-140541","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#65 New WID approved & completed. Introduction of Presence Reporting Areas for Charging","32.251, 32.298, 32.299",65,33,null,null,"2014-08-24","2014-09-10"]
[4796,630204,"      CT4 part of CT aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CT",3,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140093","-","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","CP#65 completed","23.008, 29.060, 29.274",63,32,null,null,"2014-01-29","2014-07-28"]
[4800,510354,"   TR on SA3 part for Security aspects of Public Warning System","PWS_Sec-SA3TR",2,"Rel-12","S3","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#65 completed. TR 33.969v100 for 1-step Approval. Former TR 33.869 changed to 33.969.","New 33.869 changed to 33.969",51,26,null,null,"2012-06-02","2014-09-04"]
[4803,510254,"   Deleted - Stage 2 for Security aspects of Public Warning System","PWS_Sec-del3",2,"Rel-12","S2","2011-03-23","2011-09-21",1,"SP-120434","-","ST-Ericsson","john.mattsson@ericsson.com","SP#53 work stopped as already done in previous releases",23.401,51,26,"SP-53","PCG-27","2012-06-02","2012-02-20"]
[{"$f":"A4806+1","v":4806},520031,"Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2)","Web_GBA",1,"Rel-12","S3","2011-06-08","2013-06-20",1,"SP-120890","-","Nokia","Silke.Holtmanns@nokia.com","SP#60 completed","33.220, 33.222, New 33.823",52,27,null,null,"2011-05-17","2013-07-01"]
[4808,560130,"   SA3 part of Extended IMS media plane security features (Stage 2)","eMEDIASEC-SA3",2,"Rel-12","S3","2012-06-20","2014-06-18",1,"SP-120447","-","Vodafone","Aguibou.Barry@vodafone.com","SP#64 completed",33.328000000000003,56,29,null,null,"2012-06-02","2014-06-10"]
[4811,600051,"      TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects","eMEDIASEC-CT",3,"Rel-12","C4","2012-12-13","2014-09-11",1,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completed. TR 29.828v200 for Approval. 2/4/15: acronym changed to eMEDIASEC-CT","New 29.828",58,30,null,null,"2012-11-14","2015-04-02"]
[4815,580007,"      CT1 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C1","2012-12-13","2014-09-11",1,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT","23.218, 24.147, 24.229, 24.247",58,30,null,null,"2012-11-14","2015-04-02"]
[4818,570032,"Lawful Interception in the 3GPP Rel-12","LI12",1,"Rel-12","S3","2012-09-17","2014-12-12",1,"SP-130650","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com","3/3/15: 75->100%","33.106, 33.107, 33.108",57,29,null,null,"2012-08-31","2015-03-03"]
[4822,620065,"Specification of the TUAK Algorithm Set","STAS",1,"Rel-12","S3","2013-12-09","2014-06-18",1,"SP-140814","-","Vodafone","aguibou.barry@vodafone.com","SP#64 completed. Triggered by SP-130602 LS from ETSI SAGE (TUAK as alternative to Milenage). 12/14: new TS added","New TSs: 35.231, 35.232, 35.233, 35.9nn, 35.9nn, 35.9nn",62,32,null,null,"2013-11-22","2014-12-12"]
[4825,470032,"   Stage 2/3 for Codec for Enhanced Voice Services","EVS_codec-SA4",2,"Rel-12","S4","2010-03-25","2014-12-12",1,"SP-140151","SP-140467","Huawei","lei.miao@huawei.com","SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). Dec.14: 90->95","26.114, New (26.441, 26.442, 26.443, 26.444, 26.445, 26.446, 26.447, 26.448, 26.449, 26.450, 26.451)",47,24,null,null,"2010-03-10","2015-06-26"]
[4827,650005,"   CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",2,"Rel-12","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140800","-","Nokia Networks","Jan.Kall@nsn.com","Stage 3¦WID: CP-140492-> CP-140800",null,65,33,null,null,"2014-07-29","2014-12-09"]
[4830,650305,"      CT3 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C3","2014-09-16","2014-12-09",1,"CP-140800","CP-140560","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800","29.163, 29.292",65,33,null,null,"2014-07-29","2014-12-09"]
[4833,560140,"   SA4 part of Coordination of Video Orientation","CVO-SA4",2,"Rel-12","S4","2012-06-07","2013-03-06",1,"SP-120228","-","Ericsson","frederic.gabin@ericsson.com","SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering","26.114, 26.141, 26.234, 26.346",56,29,null,null,"2012-06-07","2013-02-16"]
[4836,600206,"      CT1 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed",24.228999999999999,60,31,null,null,"2013-05-28","2013-11-18"]
[4840,570233,"   High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI, IMS Messaging and Presence","HEVC-SA4",2,"Rel-12","S4","2012-09-17","2014-06-18",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed","26.114, 26.140, 26.141, 26.234, 26.244, 26.247, 26.346",57,29,null,null,"2012-08-30","2014-04-16"]
[4843,580066,"IMS-based Streaming and Download Delivery Enhancements","IMS_SDE",1,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","Provide an extension of IMS based PSS and MBMS user services","-",58,30,null,null,"2012-11-12","2013-04-19"]
[4847,580167,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects","ART_LTE-NBWB",2,"Rel-12","S4","2012-12-12","2013-12-11",1,"SP-120771","-","Sony Mobile Communications","Peter.Isberg@sony.com","SP#62 completed","26.131, 26.132",58,30,null,null,"2012-11-12","2013-11-18"]
[4848,580267,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects","ART_LTE-UED",2,"Rel-12","S4","2012-12-12","2014-09-17",1,"SP-120770","-","AT&T, Orange","luisa.marchetto@att.com, stephane.ragot@orange.com","SP#65 completed","26.131, 26.132",58,30,null,null,"2012-11-12","2014-08-13"]
[4854,590243,"   MBMS operation on Demand","MI-MooD",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130026","SP-140471","Qualcomm","Charles Lo (clo@qti.qualcomm.com) ","SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 75->100",26.346,59,30,null,null,"2013-02-20","2015-03-05"]
[4855,590044,"End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI",1,"Rel-12","S4","2013-03-06","2015-09-14",1,"SP-140600","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040",26.114000000000001,59,30,null,null,"2013-02-20","2014-09-09"]
[4858,600107,"      CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C3","2013-06-21","2015-09-14",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","Dec.14: CD: 09/14->09/15. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","29.162, 29.163, 29.213, 29.214",60,31,null,null,"2013-05-29","2015-05-05"]
[4861,620066,"Video Coding Enhancements in IMS Messaging and Presence","VCEIMP",1,"Rel-12","S4","2013-12-11","2014-03-07",1,"SP-130579","-","Ericsson","frederic.gabin@ericsson.com","SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141",26.140999999999998,62,32,null,null,"2013-11-29","2014-01-29"]
[4865,560033,"      Multi-vendor Plug and Play eNB connection to the network","SON-NM-MUPPET",3,"Rel-12","S5","2011-09-21","2013-12-11",1,"SP-120777","-","NSN","anatoly.andrianov@nsn.com","SP#62 completed. TS 32.508v200 for Approval, TS 32.509v100 for 1-step Approval","32.501, New TSs (32.508, 32.509)",56,29,null,null,"2012-04-18","2013-11-27"]
[4868,560335,"      3GPP Fault Management Solution Profile for NGMN NGCOR","OAM-FMSP",3,"Rel-12","S5","2012-06-20","2013-06-19",1,"SP-120778","-","Ericsson","thomas.tovinger@ericsson.com","SP#60 completed. TS 28.390v200 for Approval","new 28.390",56,29,null,null,"2012-05-23","2013-06-13"]
[4873,620056,"      Alarm quality improvements","OAM-AMI-SA5",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130611","SP-140544","TeliaSonera","tommy.berggren@teliasonera.com","SP#65 completion 09/14=>12/14. Exception in SP-140544. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) . Dec.14: 50->100","32.111-1, 32.111-2, 32.111-6",62,32,null,null,"2013-11-28","2014-12-04"]
[4876,620057,"   OAM aspects of Network Sharing","OAM-SHARE",2,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. Triggered by Rel-12 TR 32.851 Study on OAM aspects of Network Sharing (FS_OAM_SHARE), Rel-6 Network Sharing (NTShar) UID_31018","Stage 1/2/3",62,32,null,null,"2013-11-28","2014-09-10"]
[4879,570037,"Rel-12 Charging","CH12",1,"Rel-12","S5","2012-12-12","2014-06-18",1,"-","-","-","-","CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI","-",57,29,null,null,"2012-09-19","2012-09-19"]
[4880,580051,"   Short Message Service - Service Center (SMS-SC) Offline Charging","SMS-SC-CH",2,"Rel-12","S5","2012-12-12","2014-03-10",1,"SP-140027","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027","32.240, 32.274, 32.297, 32.298, 32.299",58,30,null,null,"2012-11-20","2014-02-27"]
[4883,620058,"   Charging for IMS centralized service (ICS) control (Stage 2/3)","CHICS",2,"Rel-12","S5","2013-12-11","2014-06-18",1,"SP-130610","-","NSN","Gerald.Goermer@nsn.com","SP#64 completed. Align SA5 Charging specifications with Rel-8 Feature IMS Centralized Service control (ICSRA) and subsequent enhancements under TEIx (SA2 23.292 ICSRA Stage 2, CT3 29.292, CT1 24.607, 24.611)","32.250, 32.298",62,32,null,null,"2013-12-06","2014-06-10"]
[4887,530218,"   CT3 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C3","2011-09-24","2013-09-06",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#61 completed. 2/4/15: acronym changed to EMC_PC","29.163, 29.165",53,27,null,null,"2011-08-27","2015-04-02"]
[4890,580009,"Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD",1,"Rel-12","C1,C4,R3","2012-12-07","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality.","Stage 2/3",58,30,null,null,"2012-11-19","2013-09-04"]
[4894,590121,"      Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE","REP_WMD-RFR_PWS-Core",3,"Rel-12","R3","2013-03-04","2014-06-13",1,"RP-130398","RP-140637","one2many, Huawei","peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com)","RP#64 completed",36.412999999999997,59,30,null,null,"2013-02-26","2014-03-04"]
[4898,620017,"   Test part: Single Radio Voice Call Continuity (SRVCC) before ringing","bSRVCC-UEConTest",2,"Rel-12","R5","2013-12-06","2014-03-06",1,"RP-131919","RP-140422","NTT DOCOMO","Masahiro.Tamaoki.eu@nttdocomo.com","RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3)","34.229-1, 34.229-2, 36.523-1, 36.523-2 ",62,32,null,null,"2013-11-25","2013-12-14"]
[4901,601002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C1-IETF","2013-05-21","2014-12-09",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",60,31,null,null,"2013-06-10","2017-03-21"]
[4904,580015,"   CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6","IMSProtoc6",2,"Rel-12","C3","2014-06-06","2014-09-11",1,"CP-120905","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#65 completed. 4/2/15: acronym changed to IMSProtoc6","29.163, 29.165",58,30,null,null,"2012-11-19","2015-04-02"]
[4905,611001,"   (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C3-IETF","2013-09-06","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",61,31,null,null,"2013-08-23","2017-03-21"]
[4908,580018,"   CS Fallback in EPS - Phase 3","SAES3-CSFB",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[4912,580022,"   Stage 3 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C4","2012-12-10","2013-06-14",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#60 completed","29.328, 29.329, 29.364",58,30,null,null,"2012-11-19","2013-05-29"]
[4915,580123,"   Stage 3 for Diameter based interface between SGSN and SMS central functions","Dia_SGSN_SMS",2,"Rel-12","C4","2012-12-10","2013-12-06",1,"CP-130437","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#62 completed","29.002, 29.230, 29.272, 29.305, 29.336, 29.337, 29.338",58,30,null,null,"2012-11-20","2013-11-18"]
[4919,590112,"   CT4 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C4","2013-03-01","2013-12-06",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed","23.007, 23.008, 29.274",59,30,null,null,"2013-03-07","2013-11-18"]
[4923,590214,"   Stage 3 for Dual Radio VCC enhancements","eDRVCC",2,"Rel-12","C1,C3","2013-03-01","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed","Stage 3",59,30,null,null,"2013-02-19","2013-11-18"]
[4926,600009,"CT aspects of Signalling of Image Size (Stage 2/3)","SIS_CT",1,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[4929,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162, 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[4930,600010,"IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S)","ICS_IWE",1,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130352","-","Orange","marianne.mohali@orange.com ","CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS)",29.292000000000002,60,31,null,null,"2013-05-28","2013-11-19"]
[4933,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[4937,650002,"      CT3 part of Common for HSS & PCRF solutions","PCSCF_RES",3,"Rel-12","C3","2013-05-03","2014-12-09",1,"CP-140490","CP-140687","Huawei","susan.shishufeng@huawei.com","CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687","29.061, 29.165",65,33,null,null,"2013-08-10","2014-06-03"]
[4940,640114,"      CT1 part of HSS based solution","PCSCF_RES",3,"Rel-12","C1","2013-04-03","2014-12-09",1,"CP-140490","CP-140605","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100%",24.228999999999999,64,33,null,null,"2013-08-10","2014-12-04"]
[4944,610008,"Updating IMS to conform to RFC 6665 (Stage 3)","UP6665",1,"Rel-12","C1,C3","2013-09-09","2015-03-13",1,"CP-130717","-","BlackBerry","Andrew Allen (aallen@blackberry.com)","Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes","Stage 3",61,31,null,null,"2013-07-25","2013-09-09"]
[4948,670034,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-explicit-subscription)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100; 9/4/21: RFC 7614 added;","draft-ietf-sipcore-refer-explicit-subscription; RFC 7614",67,34,null,null,"2015-03-13","2021-04-09"]
[4951,620104,"   CT1 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C1","2013-12-06","2014-06-13",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#64 completed","24.229, 24.315",62,32,null,null,"2013-11-18","2014-05-26"]
[4952,620204,"   CT3 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C3","2013-12-09","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#65 completed",29.164999999999999,62,32,null,null,"2013-11-18","2014-08-01"]
[4955,630102,"   CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3)","ICEH248",2,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#65 completed","23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334",63,32,null,null,"2014-01-29","2014-07-28"]
[4958,630105,"   SA1 part of Transfer of ETSI business trunking specifications","IMS_Corp2",2,"Rel-12","S1","2014-03-05","2014-09-17",1,"SP-140170","S1-143300","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 completed. TS 22.519v200 for Approval","New 22.519 (ETSI 181 019)",63,32,null,null,"2014-03-06","2014-09-03"]
[4961,630108,"   CT4 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C4","2014-03-10","2014-12-09",1,"CP-140191","CP-140485","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140485. Dec.14: 0->100","23.334, 29.238, 29.334",63,32,null,null,"2014-01-29","2014-12-04"]
[4966,641010,"   (IETF) Diameter Overload Control Mechanisms (draft-ietf-dime-ovli)","DOCME",2,"Rel-12","C4-IETF","2014-06-13","2014-12-09",1,"CP-140273","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Mar15: In WGLC¦7/3/16: 50%->100; 9/4/21: RFC 7683 added;","draft-ietf-dime-ovli; RFC 7683",64,33,null,null,"2014-05-25","2021-04-09"]
[4969,640204,"   CT3 part of Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140285","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","CP#65 completed","29.163, 29.165, 29.292",64,33,null,null,"2014-04-07","2014-07-31"]
[4973,640207,"   CT3 part of Indication of NNI Routeing scenarios in SIP requests","NNI_RS",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","CP#65 completed","29.079, 29.165",64,33,null,null,"2014-04-07","2014-07-31"]
[4976,640011,"Overload Control for PCC based Diameter applications","DOCME-PCC",1,"Rel-12","C3,IETF","2014-06-13","2014-12-09",1,"CP-140405","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)","-",64,33,null,null,"2014-06-10","2014-06-16"]
[4977,640111,"   CT3 part of Overload Control for PCC based Diameter applications","DOCME-PCC",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140405","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#65 completed","29.212, 29.213, 29.214",64,33,null,null,"2014-06-10","2014-07-31"]
[4980,530002,"Introduction of ER-GSM band for GSM-R","RT_ERGSM",1,"Rel-12","G1,C1,G3new","2011-09-16","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios.","GERAN",51,27,null,null,"2011-09-06","2014-03-07"]
[4986,570202,"   CT part: Downlink Multi Carrier GERAN","DMCG",2,"Rel-12","C1","2012-09-10","2014-09-11",1,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","CP#65 completed",24.007999999999999,55,29,null,null,"2012-09-03","2014-07-28"]
[4988,590033,"Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS)","MSRD_VAMOS",1,"Rel-12","G1,G2,C1,G3new","2013-03-01","2014-11-21",1,"GP-130849","GP-140579","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","GP#63 completion 08/14=>11/14. Exception in GP-140579. Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002","GERAN",57,30,null,null,"2013-03-04","2014-08-29"]
[4991,590233,"   MSRD for VAMOS - MS Conformance Test","MSRD_VAMOS-Test",2,"Rel-12","G3new","2013-03-06","2014-11-21",1,"GP-130849","GP-140579","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 85->100","51.010-1, 51.010-2",57,30,null,null,"2013-03-04","2014-12-03"]
[4995,620314,"   CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3)","NewToN",2,"Rel-12","C1","2013-11-22","2014-12-09",1,"GP-131139","CP-140604","Ericsson","Mårten Sundberg","CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604. 3/3/15: 100% cpltd.",24.007999999999999,60,32,null,null,"2013-11-22","2015-03-03"]
[{"$f":"A4998+1","v":4998},570021,"Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3)","EHNB_enh3",1,"Rel-12","R3,R2","2012-09-12","2013-12-06",1,"RP-130741","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Triggered by FS_EHNB_enh (TR 37.803)","UTRA, LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[5001,590119,"   Core part: Support for BeiDou Navigation Satellite System (BDS) for UTRA","LCS_BDS-UTRA-Core",2,"Rel-12","R2,R3","2013-06-02","2014-03-06",1,"RP-130416","RP-131500","ZTE","Huang He (huang.he4@zte.com.cn)","RP#62 completed","25.305, 25.306, 25.331, 25.453, 25.413, 25.423, 25.433",59,30,null,null,"2013-02-26","2013-11-29"]
[5002,590219,"   Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA","LCS_BDS-UTRA-Perf",2,"Rel-12","R4","2013-03-07","2014-06-13",1,"RP-130416","RP-140714","ZTE","Ling Soonleh (soonleh.ling@zte.com.cn)","RP#64 completed. TS 25.173v100 for 1-step Approval","25.172 (FDD), new 25.173 (TDD)",59,30,null,null,"2013-02-26","2014-06-11"]
[5007,620111,"   GERAN2 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",2,"Rel-12","G2","2013-11-22","2014-08-29",1,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#63 completed","44.031, 49.031, 44.071, 48.031",60,32,null,null,"2013-11-22","2014-08-29"]
[5009,630009,"   Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new","LCS_BDS_GERAN-GERAN3new",2,"Rel-12","G3new","2014-03-01","2015-03-13",0.8,"GP-140244",null,"CATR","Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn","Dec.14: 25->80%, CD: 11/14->03/15","51010-1, 51.010-2, 51.010-7",61,32,null,null,"2014-03-01","2014-08-29"]
[5013,600219,"   Deleted - Perf. part: New Base Station specification structure","BSspec_struc-Perf",2,"Rel-12","R4","2013-06-20","2013-12-06",1,"RP-130851","RP-131514","Ericsson","johan.skold@ericsson.com","RP#62 stopped (at 0% completion)","25.113, 25.141, 25.142, 36.113, 36.141, 37.113, 37.141, 37.810, New 37.xyz (New RF test specification, New 37.xyw (ew EMC specification)",60,31,"RP-62","PCG-32","2013-06-17","2013-11-29"]
[5016,600221,"   Perf. part: L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-Perf",2,"Rel-12","R4","2013-06-17","2014-06-13",1,"RP-140092","RP-140633","Orange","olfa.benhaddada@orange.com","RP#64 completed","25.133, 25.141, 25.307, 25.327, 36.133, 36.141, 36.307, 37.141",60,31,null,null,"2013-06-17","2014-06-12"]
[5020,600127,"   Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON-Core",2,"Rel-12","R3","2013-06-18","2014-06-13",1,"RP-130831","RP-140745","China Telecom","Jinlian_wu@189.cn","RP#64 completed","36.300, 36.413",60,31,null,null,"2013-06-17","2014-06-12"]
[5023,620042,"Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon",1,"Rel-12","R4,R2","2013-12-15","2018-09-14",0.99,"RP-132061","-","Ericsson","christopher.callender@ericsson.com","-","UTRA, LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[5026,700064,"   UE Conformance Test Aspects - Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-UEConTest",2,"Rel-12","R5","2015-12-15","2018-09-14",1,"RP-171889",null,"Ericsson",null,"22/3/16: Compl:0%->4%1/7/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: Com 21/3/17: Compl ¦2 ;; 11/10/20: 35%->100",null,70,36,null,null,"2016-01-01","2020-10-11"]
[5028,620148,"   Core part: WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-Core",2,"Rel-12","R2","2013-12-06","2014-09-12",1,"RP-140981","RP-141310","Intel","sasha.sirotkin@intel.com","SP#65 completed","25.304, 25.306, 25.331, 36.304, 36.306, 36.331",62,32,null,null,"2013-12-09","2014-09-09"]
[5031,640106,"      CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3)","UTRA_LTE_WLAN_interw-CT",3,"Rel-12","C1","2014-09-09","2014-12-09",1,"CP-140623","CP-140720","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd.","24.008, 24.301, 24.302, 24.312",64,33,null,null,"2014-04-07","2015-03-03"]
[5034,551000,"Rel-12 LTE Carrier Aggregation","LTE_CA_Rel-12",1,"Rel-12","R4","2011-09-19","2016-12-15",1,"-","-","-","-","LTE_CA_Rel-12","LTE",58,30,null,null,"2012-12-14","2012-12-14"]
[5038,530029,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25",2,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","-","Sprint","George.Cummings@sprint.com","Intra-band NC","LTE",53,27,null,null,"2011-09-15","2013-06-07"]
[5041,550010,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL",2,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","-","SK Telecom","Seungpyo Hong","Inter-band 2UL","LTE",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[5045,550011,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","-","SK Telecom","haesung.park@sk.com","Intra-band NC","LTE",55,28,null,null,"2012-02-23","2012-02-23"]
[5048,560015,"   Deleted - LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1",2,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-130298","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Intra-band C ","LTE",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[5049,560115,"      Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1-Core",3,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-120826","RP-130549","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#60 stopped at 10% completion (rationale in RP-130670)","36.101, 36.104, 36.133, 36.141, 36.307, new 36.835",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[5053,560216,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4-Perf",3,"Rel-12","R4","2012-06-22","2013-09-06",1,"RP-131135","RP-131040","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed. Updated WID RP-130842=>RP-131135","36.101, 36.104, 36.133, 36.141, 36.307",56,29,null,null,"2012-06-13","2013-08-28"]
[5056,560217,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4-Perf",3,"Rel-12","R4","2012-06-22","2013-09-06",1,"RP-130175","RP-131376","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed","36.101, 36.104, 36.133, 36.141, 36.307",56,29,null,null,"2012-06-13","2013-08-28"]
[5060,570013,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[5063,570014,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130198","-","NTT DOCOMO","Kei ANDO","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[5066,570015,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39","LTE_CA_B38_B39",2,"Rel-12","R4","2012-09-11","2012-12-07",1,"RP-121178","-","China Mobile","Pan Qun (panqun@chinamobile.com)","Inter-band 1 UL","LTE",57,29,"RP-58","PCG-30","2012-09-03","2012-12-11"]
[5070,570116,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3-Core",3,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","RP-131029","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs)","36.101, 36.104, 36.133, new 36.833-1-03",57,29,null,null,"2012-09-03","2013-09-04"]
[5074,570218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Perf",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130181","RP-130516","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[5077,570226,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28","LTE_CA_B3_B28-Perf",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130189","RP-130530","eAccess","FukumotoShiro@eaccess.net","RP#60 completed","36.141, 36.307",57,29,null,null,"2012-09-03","2013-06-05"]
[5078,580032,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26",2,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[5081,580033,"   LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41",2,"Rel-12","R4","2012-12-10","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","Inter-band 2DL","LTE",58,30,null,null,"2012-12-10","2014-03-05"]
[5085,580134,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12-Core",3,"Rel-12","R4","2012-12-10","2014-09-12",1,"RP-140474","RP-141084","US Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.851",58,30,null,null,"2012-12-10","2014-09-08"]
[5088,580135,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","RP-131575","Ericsson","christian.bergljung@ericsson.com","RP#62 completed","36.101, 36.104, 36.133, new 36.833-2-07",58,30,null,null,"2012-12-10","2013-12-02"]
[5091,580136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-131679","RP-131567","NII Holdings","bill.shvodian@nii.com","RP#62 completed","36.101, 36.104, new 36.833-1-27",58,30,null,null,"2012-12-10","2013-12-06"]
[5095,590222,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Perf",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130524","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101, 36.104, 36.133, 36.141, 36.307",59,30,null,null,"2013-02-26","2013-02-26"]
[5099,590025,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26",2,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band 1 UL","LTE",59,30,"RP-62","PCG-32","2013-02-26","2013-02-26"]
[5100,590125,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Core",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131549","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.101, 36.104, 36.133, new generic 36.851",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[5103,590129,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141941","RP-141732","Huawei","Liu Ye (leo.liuye@huawei.com)","¦WID: RP-142043->RP-141941¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[5106,590128,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-130327","RP-141732","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[5110,590223,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-140853","RP-141732","Ericsson","christian.bergljung@ericsson.com ","¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5113,590231,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141967","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5116,590226,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.141, 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5121,600122,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL","LTE_CA_NC_2UL-Core",3,"Rel-12","R4","2013-06-18","2014-12-15",1,"RP-141962","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141962¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, 36.306, 36.331, New 36.833-4",60,31,null,null,"2013-06-17","2015-01-12"]
[5124,600223,"      Deleted - Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL-Perf",3,"Rel-12","R4","2013-06-20","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","RP#63 stopped (0% complete). ","36.101, 36.104, 36.133, 36.141, 36.307",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[5125,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[5128,600025,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band C CA","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[5131,600026,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23",2,"Rel-12","R4","2013-06-18","2014-06-13",1,"RP-131700","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2013-12-19"]
[5135,600128,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","RP-131705","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",60,31,null,null,"2013-06-05","2013-12-02"]
[5137,600029,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5142,600230,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5-Perf",3,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130675","RP-131010","AT&T","marc.grant@att.com","RP#61 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-05","2013-08-30"]
[5146,600032,"   Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131130","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[5149,600033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30",2,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[5150,600133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Core",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131697=>RP-141212","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5153,600134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30","LTE_CA_B4_B5_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141213","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131698=>RP-141213","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5156,600135,"      Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131133","RP-131598","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131653 discussion","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853 (3 Band CA with 1UL)",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[5160,600236,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[5162,600137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed. Updated RP-131684=>RP-141434","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-21"]
[5168,600139,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13","LTE_CA_B4_B4_B13-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141433","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed. Updated WID RP-131683=>RP-141433","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-21"]
[5171,610117,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28-Core",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","RP-131545","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#62 completed","36.101, 36.104, 36.307",61,31,null,null,"2013-09-07","2013-09-07"]
[5174,610118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Core",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131543","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101, 36.104, 36.133, new generic 36.851",61,31,null,null,"2013-09-07","2013-12-02"]
[5175,610218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Perf",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131705","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2013-12-02"]
[5178,610219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11","LTE_CA_B1_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131354","RP-140569","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#64 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2014-06-20"]
[5181,610220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","RP-141084","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#65 completed","36.141, 36.307",61,31,null,null,"2013-09-07","2014-09-08"]
[5187,610222,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL-Perf",3,"Rel-12","R4","2013-09-09","2015-03-13",1,"RP-142017","RP-150013","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","¦WID: RP-142043->RP-142017¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013",36.140999999999998,61,31,null,null,"2013-09-07","2015-04-01"]
[5189,610123,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2-Core",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","RP-140569","Ericsson","imadur.rahman@ericsson.com","RP#64 completed. TR 36.833-2-02v100 for 1-step Approval","36.101, 36.104, 36.133, New 36.833-2-02",61,31,null,null,"2013-09-07","2014-06-12"]
[5193,620218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5196,620219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-141803","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.133, 36.141",62,32,null,null,"2013-12-07","2015-01-12"]
[5199,620220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set","LTE_CA_B2_B4_BWset-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-131656","RP-140428","T-Mobile USA","nelson.ueng@t-mobile.com","RP#63 completed",36.307000000000002,62,32,null,null,"2013-12-07","2014-03-04"]
[5200,620021,"   LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","-","NII Holdings","bill.shvodian@nii.com","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5203,620022,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5208,620272,"      Perf. part:LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","RP#63 completed",36.140999999999998,62,32,null,null,"2013-12-09","2014-03-05"]
[5211,620224,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","RP-141084","KT","Ilwhan Kim (ilwhan.kim@kt.com)","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-22"]
[5214,620225,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed","36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-22"]
[5218,620027,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12","LTE_CA_B2_B4_B12",2,"Rel-12","R4","2013-12-09","2014-12-11",1,"RP-140189","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[5221,620028,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140190","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5224,620029,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12","LTE_CA_B2_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131654","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5225,620129,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12","LTE_CA_B2_B12_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131654","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.853",62,32,null,null,"2013-12-07","2014-09-08"]
[5229,620230,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101, 36.104, 36.133, 36.141, 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5233,620033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5236,620034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5239,620035,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5243,620137,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","RP-140569","CATT","Yuexia Song (songyuexia@catt.cn)","RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728","36.101, 36.104, 36.133, new 36.833-1-42",62,32,null,null,"2013-12-07","2014-06-12"]
[5246,620136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","RP-140569","Orange","Olfa BEN HADDADA","RP#64 completed","36.101, 36.307",62,32,null,null,"2013-12-07","2014-06-20"]
[5249,620138,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL-Core",3,"Rel-12","R4","2013-12-09","2014-09-11",1,"RP-140101","RP-141084","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101, 36.104, 36.133, 36.307, new 36.833-6-xy",62,32,null,null,"2013-12-07","2014-09-08"]
[5250,620238,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL-Perf",3,"Rel-12","R4","2013-12-09","2015-03-13",1,"RP-140101","RP-150013","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:60%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013",36.140999999999998,62,32,null,null,"2013-12-07","2015-04-01"]
[{"$f":"A5254+1","v":5254},620050,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5",2,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","-","SK Telecom","haesung.park@sk.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-09","2014-09-21"]
[5258,620151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-141017=>RP-141222","36.101, 36.104, 36.133, new generic 36.851 (2 Band CA with 1UL), 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5261,620152,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20","LTE_CA_B1_B7_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141223","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-140243=>RP-141223","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5264,620153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-141084->RP-141732","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL), 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2015-01-12"]
[5268,630023,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20_BWset",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140447","-","NSN","iwajlo.angelow@nsn.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5271,630124,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140448","RP-140569","NSN","iwajlo.angelow@nsn.com","RP#64 completed","36.101, 36.851",63,32,null,null,"2014-03-10","2014-06-20"]
[5275,630126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_","36.101, 36.104, 36.133, new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-03-10"]
[5276,630226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_","36.141, 36.307",63,32,null,null,"2014-03-10","2015-03-10"]
[5279,630227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.141, 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[5283,630029,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","-","China Mobile","Pan Qun (panqun@chinamobile.com)","Intra-band contig. CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5286,630035,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset",2,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[5289,630036,"   LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","-","Huawei","leo.liuye@huawei.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[5293,630137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141709","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed. Updated WID RP-140116=>RP-141709","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-22"]
[5296,630138,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141236","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","RP#65 completed. Updated WID RP-140117=>RP-141236","36.101, 36.104, 36.133, 36.141, 36.307, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-21"]
[5298,630045,"   Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140452","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[5301,640020,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4_Bwset2",2,"Rel-12","R4","2014-06-15","2014-09-12",1,"RP-140599","-","T-Mobile USA","nelson.ueng@T-Mobile.com","Inter-band CA 2DL. Mar 15: acronym changed from LTE_CA_B2_B4_Bwset_","LTE",64,33,null,null,"2014-06-16","2015-03-10"]
[5304,640121,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_Bwset-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","RP-141732","AT&T","marc.grant@att.com","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.101, 36.851",64,33,null,null,"2014-06-16","2015-01-12"]
[5308,640028,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","-","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5311,640029,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","-","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5314,640030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5317,640031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5322,650054,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Perf",3,"Rel-12","R4","2014-09-08","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 updated WID RP-140950=>RP-141127 (added Perf. Part). Completed.",36.307000000000002,65,33,null,null,"2014-09-21","2014-10-05"]
[5323,650010,"   LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28",2,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 2DL","LTE",65,33,null,null,"2014-03-10","2014-09-10"]
[5326,630034,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","-","Intel","xinrong.wang@intel.com ","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5329,630039,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5333,630140,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5336,630141,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5338,630042,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5344,630044,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141610","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5347,640023,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","-","Rogers Wireless","pavlo.nebesny@rci.rogers.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5348,640123,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, 36.307, generic 36.851 (2 Band CA with 1UL), generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5351,640124,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, 36.307, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5354,640126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41-Core",3,"Rel-12","R4","2014-06-16","2014-12-15",1,"RP-142301","RP-141732","China Mobile","PAN Qun (panqun@chinamobile.com)","¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5358,640233,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5363,650146,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.307, New 36.833-x-yz ",65,33,null,null,"2014-06-16","2015-01-12"]
[5366,650148,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41","LTE_CA_B39_B39_B41-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142302","RP-141732","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5369,650150,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","RP-141732","AT&T","marc.grant@att.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5372,650152,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Fri 11/12/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101, 36.104, 36.133, New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5373,650252,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141, 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5376,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[5379,570117,"   Core part: LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band-Core",2,"Rel-12","R4,R2","2012-09-12","2013-06-14",1,"RP-130843","RP-130569","AT&T","marc.grant@att.com","RP#60 completed. Updated WID RP-121419=>RP-130843","36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, new 36.846",57,29,null,null,"2012-09-03","2013-06-11"]
[5383,570119,"   Core part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Core",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-121414","RP-130567","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#60 completed. TR 36.840 v100 for 1-step Approval","36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new 36.840",57,29,null,null,"2012-09-03","2013-06-05"]
[5388,570220,"   Perf. part: Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh-Perf",2,"Rel-12","R4","2012-09-15","2014-12-15",1,"RP-121416","RP-142042","Alcatel-Lucent","ren.da@alcatel-lucent.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141378->RP-142042",36.100999999999999,57,29,null,null,"2012-09-03","2015-01-12"]
[5391,570125,"   Deleted - Core part: New Carrier Type for LTE","LTE_NCT-Core",2,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122028","RP-130984","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 20% completion","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.321, 36.331",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[5394,580127,"   Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Core",2,"Rel-12","R1,R2,R3,R4","2012-12-07","2014-06-13",1,"RP-121772","RP-140724","CATT","Zukang Shen (shenzukang@catt.cn)","RP#64 completed","36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423",58,30,null,null,"2012-09-03","2014-07-06"]
[5397,580029,"HetNet Mobility enhancements for LTE","HetNet_eMOB_LTE",1,"Rel-12","R2,R4","2012-04-13","2014-09-12",1,"RP-122007","-","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","Stage 3. Triggered by Rel-11 TR 36.839 Study on HetNet mobility enhancements for LTE (FS_HetNet_eMOB_LTE)","LTE",58,30,null,null,"2012-12-10","2014-09-09"]
[5398,580129,"   Core part: HetNet Mobility enhancements for LTE","HetNet_eMOB_LTE-Core",2,"Rel-12","R2,R4","2012-04-13","2014-09-12",1,"RP-122007","RP-141413","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","SP#65 completed","36.133, 36.304, 36.331",58,30,null,null,"2012-12-10","2014-09-09"]
[5401,580031,"8 Rx Antennas for LTE UL","LTE_UL_8Rx",1,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","-","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","WI has perf. part only (as change from 4Rx to 8Rx has no Core spec impact) ","LTE",58,30,null,null,"2012-09-03","2012-12-10"]
[5405,600213,"   Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD-Perf",2,"Rel-12","R4","2013-06-15","2014-12-15",1,"RP-140465","RP-141972","Nokia","lars.e.lindh@nokia.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141374->RP-141972","36.101, 36.104, 36.133",60,31,null,null,"2013-06-17","2015-01-12"]
[5409,650012,"   Test part: LTE Coverage Enhancements","Cov_Enh_LTE-UEConTest",2,"Rel-12","R5","2014-09-15","2015-06-15",1,"RP-141150","RP-150631","China Telecom","YANG Shan (yangshan@ctbri.com.cn)","¦Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631","36.508, 36.523-1, 36.523-2, 36.523-3",65,33,null,null,"2014-09-09","2015-06-18"]
[5412,620073,"   Perf. part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Wed 17/12/14->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821",36.133000000000003,62,32,null,null,"2013-12-18","2015-01-12"]
[5416,631000,"   SA2 part of Dual connectivity for LTE","LTE_SC_enh_dualC-S2",2,"Rel-12","S2","2014-03-19","2014-09-17",1,"-","-","-","-","SP#64 Three CRs agreed in SP-140262 (23.251CR0099, 23.401CR2658&CR2707). Dec.14:99->100%","23.251, 23.401",63,32,null,null,"2014-06-19","2014-12-03"]
[5419,620041,"E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2013-12-15","2017-06-15",1,"RP-141459","-","Huawei","Elean FAN (fanxiaoan@huawei.com)","Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041)","LTE",62,32,null,null,"2013-12-09","2014-09-15"]
[5422,680068,"   UE Conformance Test Aspects - E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-UEConTest",2,"Rel-12","R5","2015-06-15","2017-06-15",1,"RP-160414",null,"Huawei",null,"tested Core part: LTE_SC_enh_L1-Core 29/09/15: Compl:0%->10% 29/09/15: CD:Wed 15/06/16->Thu 15/12/16 29/09/15: Stat Rep: -->RP-151247¦1/1/16: Compl:10%->40%¦ ",null,68,35,null,null,"2015-07-03","2017-06-19"]
[5423,620047,"Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB",1,"Rel-12","R3,R1","2013-12-15","2014-12-12",1,"RP-140983","-","Samsung","Sung Hwan Won (sunghwan.won@samsung.com)","Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation).","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5426,630131,"   Core part: Smart Congestion Mitigation in E-UTRAN","SCM_LTE-Core",2,"Rel-12","R2","2014-03-06","2014-09-12",1,"RP-140434","RP-141292","LG Electronics","youngdae.lee@lge.com","RP#65 completed",36.331000000000003,63,32,null,null,"2014-03-10","2014-09-21"]
[5430,630032,"Positioning Enhancements for RF Pattern Matching in E-UTRA","LCS_LTE_RFPMT",1,"Rel-12","R3,R2","2014-04-25","2014-06-13",1,"RP-140177","-","Polaris Wireless","Gordon Scot (sgordon@polariswireless.com)","follow-up of TR 36.809 FS_LCS_LTE_RFPMT","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5434,630246,"   Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Perf",2,"Rel-12","R4","2014-03-11","2015-09-15",1,"RP-151297","RP-151296","MediaTek","Craig.Burnet@mediatek.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->25%¦Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862",36.100999999999999,63,32,null,null,"2014-03-10","2015-09-29"]
[5437,630147,"   Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO","LTE_SUMIMO_RX-Perf",2,"Rel-12","R4","2014-03-06","2015-03-13",1,"RP-140520","RP-150229","Huawei","Qian Cheng (Q.Cheng@Huawei.com)","CD:Fri 13/03/15->Sun 15/03/15¦Compl:50%->80%¦Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229",36.100999999999999,63,32,null,null,"2014-03-10","2015-04-01"]
[5441,580228,"   Perf. part: HSPA signalling enhancements for more efficient resource usage for LCR TDD","LCR_TDD_HSPA_sign_enh-Perf",2,"Rel-12","R4","2012-12-11","2013-09-06",1,"RP-121984","RP-130968","CATT","Yanping Xing (xingyanping@catt.cn)","RP#61 completed",25.102,58,30,null,null,"2012-12-10","2013-08-30"]
[5444,610025,"Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh",1,"Rel-12","R1,R2,R3,R4","2013-09-15","2016-06-15",1,"RP-140771","-","Qualcomm","arjunb@qti.qualcomm.com","Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2014-09-09"]
[5445,610125,"   Core part: Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh-Core",2,"Rel-12","R1,R2,R3,R4","2013-11-18","2014-09-12",1,"RP-140771","RP-141137","Qualcomm","arjunb@qti.qualcomm.com","RP#65 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433",61,31,null,null,"2013-09-07","2014-09-09"]
[5448,610026,"UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob",1,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","-","Huawei","Xudong Yang (yangxudong@huawei.com)","Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2013-09-07"]
[5451,620054,"UMTS Heterogeneous Networks enhancements","UTRA_HetNet_enh",1,"Rel-12","R1,R2,R3,R4","2013-12-06","2014-12-15",1,"RP-141701","-","Huawei","carmela.cozzo@huawei.com","Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet)¦the 1st part is addressed by UTRA_HetNet_mob UID_610026","UTRA",62,32,null,null,"2013-12-09","2014-09-15"]
[5456,620255,"   Perf. part: Enhanced Broadcast of System Information","UTRA_SIBenh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140131","RP-142080","Ericsson","martin.van.der.zee@ericsson.com","¦Stat Rep: RP-141230->RP-142080","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[5459,620249,"   Perf. part: Further Enhanced Uplink (EUL) enhancements","EDCH_enh-Perf",2,"Rel-12","R4","2013-12-15","2015-03-13",1,"RP-140127","RP-150062","Ericsson","mark.curran@ericsson.com","¦CD:Wed 18/03/15->Sun 15/03/15¦Stat Rep: RP-141684->RP-141860 1st Apr 15: Compl:75%->100% 1st Apr 15: Stat Rep: RP-141860->RP-150062","25.101, 25.104, 25.133, 25.141",62,32,null,null,"2013-12-09","2015-04-01"]
[5462,610001,"Test - (Small) Technical Enhancements and Improvements for Rel-12","TEI12_Test",1,"Rel-12","R5,G3new","2014-10-24","2015-12-11",1,"-","-","-","-","-","-",61,31,null,null,"2013-07-29","2013-07-29"]
[5466,490035,"Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int",1,"Rel-12","S1","2010-09-23","2012-03-07",1,"SP-100640","-","InterDigital","christopher.wallace@interdigital.com ","SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec)",22.895,49,25,null,null,"2010-08-31","2012-02-22"]
[5469,530044,"Study on Proximity-based Services","FS_ProSe",1,"Rel-12","S1","2011-09-22","2013-03-05",1,"SP-110638","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#59 completed",22.803000000000001,53,27,null,null,"2011-09-08","2013-02-19"]
[5470,540027,"Study on User Plane Congestion management","FS_UPCON",1,"Rel-12","S1","2011-12-14","2012-09-12",1,"SP-110819","-","KDDI","John Visser (jvisser@rogers.com)","SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits)",22.805,54,28,null,null,"2011-11-29","2012-08-07"]
[5476,570036,"   SA3 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S3","2012-09-12","2012-12-12",1,"SP-120622","-","China Mobile","Zhu Judy(zhuhongru@chinamobile.com)","SP#58 completed. TR 33.844 v100 for Information and Approval",33.844000000000001,57,29,null,null,"2012-09-11","2012-11-02"]
[5477,490036,"Study on Core Network Overload solutions","FS_CNO",1,"Rel-12","S2","2010-09-23","2013-12-11",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014)",23.843,49,25,null,null,"2010-08-31","2013-11-28"]
[5481,510061,"Study on S2a Mobility based On GTP and WLAN access to EPC","FS_SaMOG",1,"Rel-12","S2","2011-03-23","2013-09-11",1,"SP-120426","-","ZTE","Tricci So (tso@zteusa.com)","SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI",23.852,51,26,null,null,"2011-02-21","2013-07-25"]
[5484,410043,"Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",1,"Rel-12","S2,S1","2008-08-08","2012-12-12",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM)",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5487,560039,"Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces","FS_NBIFOM",1,"Rel-12","S2","2012-06-18","2013-03-06",1,"SP-120742","-","ZTE","Tricci So (tso@zteusa.com)","SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility)",23.861000000000001,56,29,"SP-59","PCG-30","2012-06-04","2013-02-27"]
[5491,570035,"Study on Security Assurance Methodology for 3GPP Network Elements","FS_SECAM",1,"Rel-12","S3","2012-09-13","2014-06-18",1,"SP-120654","-","Orange","loic.habermacher@orange.com","SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible)",33.805,57,29,null,null,"2012-08-31","2014-05-21"]
[5494,470050,"Study on version handling","FS_OAM_VH",1,"Rel-12","S5","2010-03-25","2012-12-12",1,"SP-100082","-","Ericsson","thomas.tovinger@ericsson.com","SP#58 completed",32.83,47,24,null,null,"2010-02-12","2012-11-21"]
[5497,560032,"Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","FS_SON_NM_CCO",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140028","-","Ericsson","robert.petersen@ericsson.com","SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060)",32.835999999999999,56,29,null,null,"2012-04-18","2014-08-25"]
[5499,580052,"Study on Alarm Management","FS_OAM_AM",1,"Rel-12","S5","2012-12-07","2013-09-11",1,"SP-120774","-","TeliaSonera","tommy.berggren@teliasonera.com","SP#61 completed",32.859000000000002,58,30,null,null,"2012-11-21","2013-09-04"]
[5502,590011,"Study on XML based access of AF to the PCRF","FS_XML_AF_PCRF",1,"Rel-12","C3","2013-03-01","2013-12-04",1,"CP-130167","-","Alcatel-Lucent","horst.brinkman@alcatel-lucent.com","CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications",29.817,59,30,null,null,"2013-02-16","2014-06-19"]
[5506,460001,"Study on GERAN improvements for Machine-Type Communications","FS_NIMTC_GERAN",1,"Rel-12","G1,G2","2010-05-24","2012-11-23",1,"GP-092418","-","Ericsson","paul.schliwa-bertling@ericsson.com","GP#56 completed. GP#44 approved WID",43.868000000000002,44,24,null,null,"2009-11-20","2012-11-23"]
[5509,500016,"Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN","FS_LCS_LTE_RFPMT",1,"Rel-12","R4","2010-12-10","2013-09-06",1,"RP-120885","RP-131082","Polaris Wireless","Scot Gordon (sgordon@polariswireless.com)","RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005","LTE 36.809",50,26,null,null,"2010-12-10","2013-08-28"]
[5513,580041,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects","FS_LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122032","RP-131618","Huawei","Elean Fan (fanxiaoan@huawei.com)","RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.872",58,30,null,null,"2012-12-10","2013-12-03"]
[5516,580042,"Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE","FS_LTE_3D_channel",1,"Rel-12","R1","2012-12-10","2014-09-12",1,"RP-141237","RP-141206","Nokia Networks","bishwarup.mondal@nsn.com","RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network","LTE 36.873",58,30,null,null,"2012-12-10","2014-09-21"]
[5518,590016,"Study on Expansion of LTE_FDD_1670_US to include 1670-1680MHz Band for LTE in the US","FS_LTE_FDD_1670_US",1,"Rel-13","R4","2013-03-01","2014-12-15",1,"RP-130202","RP-141815","LightSquared","masoud.olfat@lightsquared.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:80%->100%¦Stat Rep: RP-141453->RP-141815","LTE 36.844",59,30,null,null,"2013-02-26","2015-01-12"]
[5521,600015,"Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul ","FS_COMP_LTE_nibackhaul",1,"Rel-12","R1","2013-06-18","2013-12-06",1,"RP-130847","RP-131626","Samsung","Hyojin Lee (hyojin257.lee@samsung.com)","RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332)","LTE 36.874",60,31,null,null,"2013-06-17","2013-12-03"]
[5524,620044,"Study on RAN aspects of RAN Sharing Enhancements for LTE","FS_RSE-RAN_LTE",1,"Rel-12","R3","2013-12-06","2014-06-13",1,"RP-132116","RP-140746","NEC","Siva.Vakeesar@emea.nec.com","RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1)","LTE 36.856",62,32,null,null,"2013-11-27","2014-06-12"]
[5527,550021,"Study on Passive InterModulation (PIM) handling for UTRA and LTE Base Stations","FS_BS_PIM",1,"Rel-12","R4,G1","2012-03-05","2013-09-06",1,"RP-120268","RP-131076","Ericsson","johan.skold@ericsson.com","RP#61 completed (Conclusion: no spin-off WI). Linked to Rel-10 WI on Multi-standard radio Base Station RF requirements for non-contiguous spectrum deployments (MSR_NC) UID_480025","UTRA, LTE 37.808",55,28,null,null,"2012-02-23","2013-08-30"]
[5531,580049,"Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","FS_UTRA_LTE_1980_2170_REG1",1,"Rel-12","R4","2012-12-11","2014-09-12",1,"RP-140505","RP-141099","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1","UTRA, LTE 37.846",58,30,null,null,"2012-12-10","2014-09-22"]
[5534,570024,"Study on UMTS heterogeneous networks","FS_UTRA_HetNet",1,"Rel-12","R1,R2,R3","2012-06-12","2013-09-06",1,"RP-121436","RP-131606","Huawei","carmela.cozzo@huawei.com","RP#62 completed","UTRA 25.800",57,29,null,null,"2012-09-03","2013-12-02"]
[5538,580043,"Study on Further Enhanced Uplink (EUL) enhancements","FS_EDCH_enh",1,"Rel-12","R2,R1,R3","2012-12-10","2013-12-06",1,"RP-130347","RP-131608","Ericsson","alessandro.caverni@ericsson.com ","RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.)","UTRA 25.700",58,30,null,null,"2012-12-10","2013-12-02"]
[5539,600018,"Study on HNB Emergency Warning Area for UTRA","FS_HNB_warn_area",1,"Rel-12","R3","2013-06-18","2014-03-06",1,"RP-131258","RP-140129","Alcatel-Lucent, Ip.access","Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com ","RP#63 completed. TR 25.703 v100 for 1-step approval","UTRA 25.703",60,31,null,null,"2013-06-17","2014-02-26"]
[5545,530004,"   Stage 3 for Advanced IP Interconnection of Services","IPXS",2,"Rel-11","C1,C3","2011-09-13","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed","Stage 3",53,27,null,null,"2011-08-29","2011-08-29"]
[5546,530104,"      CT1 part of Stage 3 for Advanced IP Interconnection of Services","IPXS",3,"Rel-11","C1","2011-09-16","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed",24.228999999999999,53,27,null,null,"2011-08-29","2012-11-19"]
[5549,480130,"   Stage 1 for SIMTC","SIMTC",2,"Rel-11","S1","2010-06-10","2011-09-21",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#53 completed. SP#57 added MTC definitions in 21.905","22.368, 21.905 (MTC definitions)",48,25,null,null,"2010-05-28","2012-11-12"]
[5553,520221,"      On-line device trigger","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed","New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5556,520521,"      MSISDN-less / PS-Only","SIMTC-Reach",3,"Rel-11","S2","2011-06-13","2012-03-07",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#55 completed","23.060, 23.272, New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5559,530106,"      CT1 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","23.040, 24.008, 24.301, 24.341, 24.368",53,27,null,null,"2011-08-29","2015-01-22"]
[5564,530105,"      Deleted - Stage 2 CS aspects for SIMTC ","SIMTC-CS",3,"Rel-11","C4","2011-09-16","2012-09-06",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 stopped",23.012,53,27,"CP-57","PCG-29","2011-08-29","2012-08-13"]
[5567,530405,"         Deleted - CT6 part of Stage 3 CS aspects for SIMTC ","SIMTC-CS",4,"Rel-11","C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 stopped",31.102,53,27,"CP-57","PCG-29","2012-06-15","2012-08-13"]
[5570,560202,"      CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",3,"Rel-11","C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed. TS 29.338 v200 for Approval","23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New 29.338 ",56,29,null,null,"2012-04-23","2012-11-28"]
[5571,530009,"   RAN overload control for Machine-Type Communications","SIMTC-RAN_OC",2,"Rel-11","R2,R3,C1,C6","2011-09-16","2012-09-07",1,"RP-111373","-","Huawei","Jeff Gao (gaoyongqiang@huawei.com)","Stage 2,3. TSG#57 completed","UTRA, LTE",53,27,null,null,"2011-09-15","2012-09-06"]
[{"$f":"A5574+1","v":5574},530309,"         CT1 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",4,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#56 completed","23.122, 24.008, 24.301",53,27,null,null,"2011-08-29","2012-06-01"]
[5578,520022,"   Deleted - BB2: Stage 2 Signalling Optimizations of SIMTC","SIMTC-Sig",2,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped. SP#58 updated WID SP-110877=>SP-120848","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5581,530107,"      Deleted - Stage 3 (CS+PS) Signalling Optimizations of SIMTC","SIMTC-Sig",3,"Rel-11","C1,C6","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","CP#54 work stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2011-12-13"]
[5585,520123,"      Deleted - Charging Requirements (TS 22.368, 7.1.5)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5589,530108,"         Deleted - CT1 part of Stage 3 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",4,"Rel-11","C1","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","-","23.122, 24.008, 24.301, 24.368",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[5592,540119,"   Deleted - BB4: Secure Connection and Privacy of SIMTC","SIMTC-Sec",2,"Rel-11","S3","2011-06-08","2012-09-12",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#57 stopped (activity transferred to Rel-12 Feature MTCe under UID_560522)","TBD",52,27,"CP-57","PCG-29","2011-05-26","2012-11-12"]
[5595,480330,"   Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications","SIMTC",2,"Rel-11","S2","2010-06-10","2011-06-08",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#52 stopped","TBD",48,25,"SP-52","PCG-27","2010-05-28","2012-11-12"]
[5596,480430,"   Deleted - Stage 2 on Security part for System Improvements to Machine-Type Communications","SIMTC",2,"Rel-11","S3","2010-06-10","2011-06-08",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#52 stopped","TBD",48,25,"SP-52","PCG-27","2010-05-28","2012-11-12"]
[5599,520003,"   Stage 3 for USSD simulation service in IMS","USSI",2,"Rel-11","C1,C3","2011-06-03","2012-12-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228","-",52,27,null,null,"2011-05-18","2012-11-19"]
[5603,490131,"   Stage 1 for QoS Control Based on Subscriber Spending Limits","QoS_SSL",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-110519","-","Vodafone","mona.mustapha@vodafone.com","SP#53 completed. Use cases & service requirements to allow: 1) modification of QoS based on subscriber’s spending limits 2) enforcing of spending limits for roaming subscribers without having dedicated support in the visited network",22.114999999999998,49,25,null,null,"2010-09-02","2011-08-24"]
[5606,520004,"   CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3)","QoS_SSL-CT3",2,"Rel-11","C3","2011-06-03","2012-06-15",1,"CP-120203","-","Huawei","QiaoWeihua@huawei.com","CP#56 completed","29.212, 29.213, 29.214, 29.215, new 29.219",52,27,null,null,"2011-05-18","2012-04-20"]
[5610,490332,"   Deleted - Stage 2 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S2","2010-09-28","2012-03-07",1,"SP-110347","-","Vodafone","Susana.Sabater@vodafone.com ","SP#55 no normative work in SA2. Stage 2/3 to be done in under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021","None",49,25,"SP-55","PCG-28","2010-08-31","2012-03-05"]
[5614,530321,"      CT1 part of Stage 3 for Inclusion of Media Resource Broker","MRB",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed","24.229, 29.165",53,27,null,null,"2011-08-25","2012-08-14"]
[5617,500030,"Non Voice Emergency Services","NOVES",1,"Rel-11","S1,S2","2010-12-16","2012-03-07",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES)","-",50,26,null,null,"2010-11-29","2012-03-16"]
[5618,500130,"   Stage 1 for Non Voice Emergency Services","NOVES",2,"Rel-11","S1","2010-12-16","2011-09-21",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed",22.100999999999999,50,26,null,null,"2010-11-29","2011-08-24"]
[5621,510147,"   Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",2,"Rel-11","S1","2011-03-23","2011-09-21",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 completed ",22.228000000000002,51,26,null,null,"2011-02-21","2011-08-24"]
[5624,520128,"   Stage 1 for Anonymous Call Rejection in the CS domain","ACR_CS",2,"Rel-11","S1","2011-06-07","2011-06-08",1,"SP-110421","-","Alcatel-Lucent","Betsy.Covell@alcatel-lucent.com","SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013)","22.004, 22.081, 22.082, 22.085, 22.088",52,27,null,null,"2011-05-19","2011-09-19"]
[5628,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[5631,470023,"   Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2","2010-03-26","2012-06-20",1,"SP-120539","-","Ericsson","stefan.rommer@ericsson.com","SP#56 completed","23.203, new 23.139",47,24,null,null,"2009-12-06","2012-06-09"]
[5635,550005,"      TR on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface","BBAI_BBI-CT",3,"Rel-11","C4","2012-03-02","2012-06-15",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#56 completed","new 29.839",55,28,null,null,"2012-02-20","2012-06-14"]
[5639,530412,"      CT4 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C4","2011-09-16","2012-12-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#58 completed","23.008, 29.273, 29.274, new 29.139",53,27,null,null,"2011-08-29","2012-11-28"]
[5642,530013,"   Stage 3 BB II - Core Network impacts: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",2,"Rel-11","C3,C1,C4","2011-09-16","2012-09-07",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#57 completed","Stage 3",53,27,null,null,"2011-08-29","2012-06-14"]
[5643,530113,"      TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#56 completed ",24.82,53,27,null,null,"2011-08-29","2012-06-14"]
[5646,530413,"      CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C4","2011-09-16","2012-03-02",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#55 completed","23.008, 29.273",53,27,null,null,"2011-08-29","2012-08-13"]
[5649,530014,"   Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility ","-",2,"Rel-11","C3,C1,C4","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2012-03-06"]
[5652,530314,"      Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C3","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","29.212, 29.213, 29.215",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5657,500026,"Single Radio Video Call Continuity for 3G-CS","vSRVCC",1,"Rel-11","S2,C1,C3,C4","2010-10-15","2012-06-15",1,"SP-100704","-","Samsung","xiaowan.ke@samsung.com","CP#56 completed. Provide Single Radio VIDEO Call Continuity from E-UTRAN to UTRAN-CS based on the agreed architecture alternative in TR 23.886","-",50,26,null,null,"2010-11-26","2012-06-18"]
[5660,520105,"      CT1 aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",3,"Rel-11","C1","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","CP#56 completed","24.008, 24.237, 24.301",52,27,null,null,"2011-05-18","2012-06-06"]
[5664,500027,"   Stage 1 for Network-provided Location information for IMS","NWK-PL2IMS",2,"Rel-11","S1","2010-12-15","2011-09-21",1,"-","-","n/a","n/a","SP#53 completed",22.114999999999998,50,26,null,null,"2010-12-13","2011-09-21"]
[5667,490029,"   Charging for Network-provided Location information for IMS","NWK-PL2IMS_CH",2,"Rel-11","S5","2010-09-23","2012-09-12",1,"SP-110700","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#57 completed","Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299)",49,25,null,null,"2010-09-03","2012-09-05"]
[5668,550008,"   CT aspects of Network-provided Location information for IMS (Stage 3)","NWK-PL2IMS-CT",2,"Rel-11","C3,C4,C1","2012-03-02","2013-03-01",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","Stage 3. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","-",55,28,null,null,"2012-02-22","2015-03-03"]
[5671,550308,"      CT1 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C1","2012-03-02","2013-03-01",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","24.229, 24.292",55,28,null,null,"2012-02-22","2015-03-03"]
[5677,500133,"   Stage 2 for VPLMN Autonomous CSG Roaming","VCSG",2,"Rel-11","S2","2010-10-15","2011-12-14",1,"SP-100706","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#54 completed","23.002, 23.060, 23.401",50,26,null,null,"2010-11-26","2011-11-28"]
[5679,510048,"Data Identification in Access Network Discovery and Selection Function (ANDSF)","DIDA",1,"Rel-11","S2,C1","2011-03-23","2012-12-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions","Stage 2/3",51,26,null,null,"2011-02-21","2012-11-19"]
[5682,550003,"   CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3","DIDA-CT",2,"Rel-11","C1","2012-03-02","2012-12-07",1,"CP-120089","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#58 completed","24.302, 24.312",55,28,null,null,"2012-02-20","2013-01-21"]
[5686,540110,"      CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",3,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","CP#56 completed",29.273,54,28,null,null,"2011-11-23","2012-09-24"]
[5689,530101,"   Stage 2 for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC",2,"Rel-11","S2","2011-09-22","2012-06-20",1,"SP-110475","-","Orange","antoine.mouquet@orange-ftgroup.com ","SP#56 completed","23.216, 23.237",53,27,null,null,"2011-08-12","2012-06-18"]
[5692,530401,"      CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","29.165, 29.292",53,27,null,null,"2011-08-25","2012-08-14"]
[5693,530501,"      CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C4","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.003, 23.008, 29.002, 29.230, 29.272, 29.280, 29.303, 29.305, 29.328",53,27,null,null,"2011-08-25","2012-08-14"]
[5698,530046,"S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",1,"Rel-11","S2,C4,C1,C3,IETF","2011-09-22","2014-03-05",1,"SP-110642","-","ZTE","Chunhui Zhu (zhu.chunhui@zte.com.cn)","Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a)","Stage 2/3",53,27,null,null,"2011-08-12","2014-02-19"]
[5700,540011,"   CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",2,"Rel-11","C4,C1,C3,IETF","2011-12-02","2014-03-05",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","-","Stage 3",54,28,null,null,"2011-10-26","2011-11-23"]
[5704,540311,"      CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C3","2011-12-02","2012-06-15",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#56 completed","29.212, 29.213, 29.215",54,28,null,null,"2011-10-26","2012-06-01"]
[5707,540030,"   Charging for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CH",2,"Rel-11","S5","2011-12-14","2012-09-12",1,"SP-110886","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","Stage 2/3. SP#57 completed","32.240, 32.260, 32.298, 32.299",54,28,null,null,"2011-12-08","2012-09-05"]
[5711,560027,"IMS Overload Control","IOC",1,"Rel-11","S2,C1,C3,IETF","2012-06-18","2014-12-09",1,"SP-120273","-","Orange, China Mobile","Antoine MOUQUET, YU Qing","SP#57 Stage 2 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. Linked to UID_410041 Study on IMS Evolution (TR 23.812). Solutions from IETF SOC WG and existing 3GPP procedures to be re-used if possible & backward compatibility ensured","Stage 2/3",56,29,null,null,"2012-05-11","2012-07-24"]
[5714,570107,"      CT1 part of Stage 3 for IMS Overload Control","IOC",3,"Rel-11","C1","2012-09-05","2012-12-07",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","CP#58 completed",24.228999999999999,57,29,null,null,"2012-08-13","2012-11-20"]
[5717,571002,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","Submitted to IESG for publication. Dec14: 50->90%. Mar15: 100%. Impacted RFC updated (was draft-ietf-soc-overload-rate-control). Jun 15: RFC 7415 (was draft-ietf-soc-overload-rate-control)","RFC 7415",57,29,null,null,"2012-09-03","2015-03-10"]
[5719,520030,"Rel-11 Security small Enhancements","SEC11",1,"Rel-11","S3","2011-06-08","2012-09-12",1,"-","-","-","-","SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature","-",52,27,null,null,"2011-04-19","2012-08-16"]
[5722,440155,"   ZUC EEA3 and EIA3","EEA3_EIA3",2,"Rel-11","S3","2009-06-04","2011-12-14",1,"SP-090457","-","CATR","Yuan Qi (yuanqi@catr.cn)","SP#53 completed new EPS algorithms e.g. for China","33.401, New (35.221, 35.222, 35.223, 35.924)",44,23,null,null,"2009-05-18","2011-12-12"]
[5726,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[5729,540312,"      CT4 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",3,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",29.109000000000002,54,28,null,null,"2011-11-23","2012-08-14"]
[5732,530048,"Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements","EMM",1,"Rel-11","S4","2011-09-07","2013-03-06",1,"SP-120025","-","Qualcomm","Nikolai Leung (nleung@qualcomm.com)","Stage 3. SP#59 completed","26.140, 26.234, 26.247, New 26.951=>26.851",53,27,null,null,"2011-09-07","2013-02-16"]
[5736,560041,"Mobile 3D Video Coding","M3DV",1,"Rel-11","S4","2012-06-07","2012-09-12",1,"SP-120229","-","Orange","gilles.teniou@orange.com","SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905.","26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905",56,29,null,null,"2012-06-07","2012-08-20"]
[5739,510056,"      IRP framework enhancements to support Management of Converged Networks","OAM-FMC-IRP",3,"Rel-11","S5","2011-03-23","2013-03-07",1,"SP-120652","-","Nokia Siemens Networks, Ericsson","thomas.tovinger@ericsson.com, olaf.pollakowski@nsn.com","SP#59 completed. Triggered by SA5 Studies TR 32.833, 32.828, 32.831","32.101/103/150, new (28.620/621/622/623/624/625/626/627/628/629/631/632/633/651/652/653/654/655/656/657/658/659/661/662/663/671/672/673/674/675/676/701/702/703/704/705/706/707/708/709/731/732/733/734/735/736/751/752/753, 32.107/156/157/853/854",51,26,null,null,"2011-03-09","2012-12-05"]
[5740,510251,"   Rel-11 Performance Management","OAM11-PM",2,"Rel-11","S5","2011-03-23","2012-12-12",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2012-11-19"]
[5744,530049,"      Management of Carrier Aggregation for LTE","OAM-CA",3,"Rel-11","S5","2011-09-21","2012-12-12",1,"SP-120776","-","Nokia Siemens Networks, Ericsson","yizhi.yao@nsn.com, per.elmdahl@ericsson.com","SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA)",32.424999999999997,53,27,null,null,"2011-08-27","2012-11-20"]
[5747,530051,"      LTE Self-Organizing Networks (SON) coordination management","OAM-SON-LTE_COORD",3,"Rel-11","S5","2011-09-21","2013-03-06",1,"SP-110637","-","Huawei, Nokia Siemens Networks","kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com","SP#59 completed","LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766",53,27,null,null,"2011-08-27","2013-02-16"]
[5751,510060,"   Charging for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Data Bases","PEST-CH",2,"Rel-11","S5","2011-03-21","2011-09-21",1,"SP-110126","-","Ericsson","patrik.teppo@@ericsson.com","SP#53 completed. Stage 3","32.251, 32.298, 32.299",51,26,null,null,"2011-02-22","2011-08-26"]
[5754,510129,"   Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","S1","2010-10-27","2011-09-21",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","SP#53 completed under IPXS",22.114999999999998,51,26,null,null,"2011-02-22","2011-10-07"]
[5757,480011,"User Data Convergence - Data Model","UDC_DM",1,"Rel-11","C4,S1","2010-03-25","2012-09-07",1,"CP-110384","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#57 completed. SP#48 Stage 1 completed as Rel-10","-",48,25,null,null,"2010-05-26","2012-08-13"]
[5761,510004,"Definition of the UICC Application for Hosting Party Module","HPM_UICC",1,"Rel-11","C6","2011-03-18","2012-06-15",1,"CP-110289","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#56 completed","31.102, New 31.104",51,26,null,null,"2011-03-03","2012-09-25"]
[5765,581001,"   (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077)","eNR_EPC",2,"Rel-11","C4-IETF","2012-12-07","2013-12-06",1,"CP-120449","-","Lionel Morand","Lionel Morand","CP#62 completed","RFC 7077 (was draft-ietf-netext-update-notifications)",58,30,null,null,"2012-11-24","2013-11-28"]
[5768,520009,"Reference Location Information (Stage 3)","RLI",1,"Rel-11","C4,C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11)","-",52,27,null,null,"2011-05-18","2011-06-01"]
[5769,520109,"   CT4 part of Reference Location Information (Stage 3)","RLI",2,"Rel-11","C4","2011-06-03","2011-06-03",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#52 completed","23.008, 29.228, 29.328, 29.329",52,27,null,null,"2011-05-18","2011-06-02"]
[5772,520110,"   CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C1","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","23.218, 24.229, 24.930",52,27,null,null,"2011-05-18","2012-08-14"]
[5776,520210,"   CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C3","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","29.163, 29.165",52,27,null,null,"2011-05-18","2012-08-14"]
[5779,560008,"   Stage 2 for Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","S2","2012-06-18","2012-09-07",1,"-","-","-","-","SP#57 completed","23.060, 23.251",56,29,null,null,"2012-06-18","2012-08-31"]
[5782,550009,"      Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN","SIRIG",3,"Rel-11","C3","2012-03-02","2012-06-15",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","CP#56 stopped (SA2 decided NO CT3 impact)",29.212,55,28,"CP-56","PCG-29","2012-02-20","2012-04-20"]
[5786,530219,"   CS Fallback in EPS - Phase 2","SAES2-CSFB",2,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110639","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed","23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118",53,27,null,null,"2011-09-08","2012-08-14"]
[5790,540015,"Support of RFC 6140 in IMS","GINI",1,"Rel-11","C1","2011-12-02","2012-09-07",1,"CP-110760","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#57 completed. Stage 3. Support procedures and protocol extensions in RFC6140 \"Registration for Multiple Phone Numbers in SIP\" to IMS for complex UEs. Ensure co-existence with NGCN IP-PBX registration procedures already defined in IMS.",24.228999999999999,54,28,null,null,"2011-11-22","2012-08-14"]
[5791,540017,"Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",1,"Rel-11","C4,C3","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI.","Stage 3",54,28,null,null,"2011-10-26","2012-08-13"]
[5794,550007,"Inter-IMS Network to Network Interface (II-NNI) enhancements: SIP timers applicability (Stage 3)","NNI_timers",1,"Rel-11","C3","2012-03-02","2012-09-07",1,"CP-120082","-","Telecom Italia","antonio.ascolese@telecomitalia.it","CP#57 completed",29.164999999999999,55,28,null,null,"2012-02-22","2012-08-13"]
[5797,560007,"Generic IMS User Group Over Sh","GenUG_Sh",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120254","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",29.364000000000001,56,29,null,null,"2012-06-02","2012-08-13"]
[5801,570011,"Enhanced T.38 FAX support (Stage 3)","MMTel_T.38_FAX",1,"Rel-11","C3,C1,C4","2012-09-06","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed. Linked to Rel-8 Feature: IMS Multimedia Telephony Service (IMS-MMTel) UID_7038. SA1 added FAX stage 1 requirement only in Rel-10 under TEI10 to TS 22.173 (CR#0064)","-",57,29,null,null,"2012-08-13","2012-11-20"]
[5804,570311,"   CT4 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C4","2012-09-06","2012-09-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#57 completed",29.332000000000001,57,29,null,null,"2012-08-13","2012-11-20"]
[5807,540216,"   Deleted - CT4 part of Enhancement of the Protocols for SMS over SGs","PROTOC_SMS_SGs",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped (abandonned new TS 29.218 Diameter based protocols for SMS service over SGs)","29.305, new 29.218",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[5812,510301,"   CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","C1,C4","2011-06-03","2012-12-07",1,"CP-120563","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#58 completed","-",49,26,null,null,"2012-06-02","2012-11-19"]
[5815,560042,"   Stage 2 for Gateway Core Network Sharing for GERAN","Full_MOCN-GERAN-GWCN",2,"Rel-11","S2","2012-06-18","2013-03-06",1,"SP-120268","-","Vodafone","chris.pudney@vodafone.com","SP#59 completed. (23.251CR0062R2 as TEI11. TS 23.251 specifies both MOCN and GWCN for E-UTRAN and UTRAN, but GWCN is not yet supported on GERAN. Extend Full_MOCN-GERAN to also cover GWCN GERAN",23.251000000000001,56,29,null,null,"2012-06-04","2012-11-22"]
[5816,540003,"Medium range/local area requirements for multicarrier BTS","MRLA",1,"Rel-11","G1","2011-11-25","2012-11-23",1,"GP-111780","-","Ericsson","Eric Nordström","GP#56 completed. GP#52 approved WID","GERAN",52,28,null,null,"2011-11-25","2012-11-23"]
[5819,550023,"Domain Specific Access Control in GERAN","GDSAC",1,"Rel-11","G2","2012-03-05","2012-08-31",1,"GP-120452","-","Vodafone","chris.pudney@vodafone.com","GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001)","GERAN 44.018",53,28,null,null,"2012-04-18","2012-08-31"]
[5822,500220,"   Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Perf",2,"Rel-11","R4","2010-12-10","2012-03-02",1,"RP-111396","RP-120076","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[5826,530033,"Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2013-12-06",1,"RP-121204","-","MediaTek","Johan Johansson","Stage 2/3","UTRA, LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[5828,590001,"   Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-12-06",1,"RP-130172","RP-131447","NTT DoCoMo","masahiro.tamaoki.eu@nttdocomo.com","RP#62 completed","34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2013-08-13"]
[5833,530137,"   Core part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-Core",2,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-111383","RP-121558","Ericsson","johan.skold@ericsson.com","RP#58 completed. TR 37.809 v200 for Approval","25.104, 36.104, 37.104, new 37.809",53,27,null,null,"2011-09-15","2012-12-05"]
[5837,550115,"   Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Core",2,"Rel-11","R4,G1","2012-02-06","2012-12-07",1,"RP-120857","RP-121985","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#58 completed","25.104, 25.105, 36.104, 37.104, new 37.812",55,28,null,null,"2012-02-23","2012-12-05"]
[5840,560113,"   Core part: Further enhancements to H(e)NB mobility - Part 1","EHNB_enh1-Core",2,"Rel-11","R3,R2","2012-06-15","2012-12-07",1,"RP-121427","RP-121563","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#58 completed","25.413, 25.467, 25.469, 36.300, 36.413, 36.423",56,29,null,null,"2012-06-13","2012-11-27"]
[5841,560014,"Further enhancements to H(e)NB mobility - Part 2","EHNB_enh2",1,"Rel-11","R3,R2","2012-06-19","2012-12-07",1,"RP-121712","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2)","UTRA, LTE",56,29,null,null,"2012-06-13","2012-11-27"]
[5844,430111,"   Core part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Core",2,"Rel-11","R2,R1,R3,R4","2009-03-05","2013-06-12",1,"RP-131259","RP-130483","TruePosition","terri.brooks@trueposition.com","RP#60 completed","36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new (36.111, 36.456, 36.457, 36.458, 36.459)",43,22,null,null,"2009-03-06","2013-08-29"]
[5847,480126,"   Core part: Service continuity improvements for MBMS for LTE","MBMS_LTE_SC-Core",2,"Rel-11","R2,R3","2010-06-04","2012-09-07",1,"RP-120258","RP-121001","Huawei","David.Lecompte@huawei.com ","RP#57 completed","25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445",48,25,null,null,"2010-06-04","2012-09-06"]
[5853,510028,"New Band LTE Downlink FDD 716-728 MHz (Band 29, Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29)","LTE_DL_FDD700",1,"Rel-11","R4","2011-03-22","2012-12-07",1,"RP-110435","-","AT&T","marc.grant@att.com ","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[5855,510228,"   Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700-Perf",2,"Rel-11","R4","2011-03-29","2012-12-07",1,"RP-110435","RP-121605","AT&T","marc.grant@att.com ","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[5859,510032,"LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB",1,"Rel-11","R1,R2,R4,R5","2011-03-23","2013-03-01",1,"RP-120602","-","NII Holdings","bill.shvodian@nii.com","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-06-09"]
[5862,560010,"   Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-UEConTest",2,"Rel-11","R5","2012-06-18","2013-03-01",1,"RP-120603","RP-130045","NII Holdings","bill.shvodian@nii.com","RP#59 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1",56,29,null,null,"2012-06-06","2013-02-27"]
[5865,520217,"   Perf. part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Perf",2,"Rel-11","R4","2011-06-09","2012-06-15",1,"RP-110875","RP-120573","Ericsson","olav.queseth@ericsson.com","RP#56 completed","36.133, 36.141, 37.141",52,27,null,null,"2011-06-02","2012-06-09"]
[5866,560011,"   Test part: LTE for 700 MHz Digital Dividend","LTE_APAC700-UEConTest",2,"Rel-11","R5","2012-06-18","2013-06-14",1,"RP-120600","RP-130467","Ericsson","fredrik.sundstrom@ericsson.com","RP#60 completed","36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1",56,29,null,null,"2012-06-06","2013-06-03"]
[5869,520219,"   Perf. part: Relays for LTE (part 2)","LTE_Relay2-Perf",2,"Rel-11","R4","2009-12-04","2013-06-14",1,"RP-110914","RP-130487","Ericsson","christian.hoymann@ericsson.com ","RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213","36.133, new 36.117 (E-UTRA Relay conformance testing)",46,24,null,null,"2009-11-30","2013-06-04"]
[5872,530231,"   Perf. part: Signalling and Procedure for Interference Avoidance for in-device coexistence","SPIA_IDC_LTE-Perf",2,"Rel-11","R4","2011-09-20","2012-12-07",1,"RP-111356","RP-121574","China Mobile","Zhenping HU","RP#58 completed",36.133000000000003,53,27,null,null,"2011-09-15","2012-11-27"]
[5878,590004,"   Test part: Coordinated Multi-Point Operation for LTE","COMP_LTE-UEConTest",2,"Rel-11","R5","2013-03-15","2014-12-15",1,"RP-130376","RP-141782","Samsung","Stoyan.Baev@partner.samsung.com",null,"36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-01-29","2015-01-12"]
[5880,540125,"   Core part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-Core",2,"Rel-11","R1,R2,R4","2011-12-09","2012-12-07",1,"RP-120871","RP-121579","Alcatel-Lucent","sigen.ye@alcatel-lucent.com","RP#58 completed","36.101, 36.211, 36.212, 36.213, 36.331",54,28,null,null,"2011-12-07","2012-11-28"]
[5884,550112,"   Core part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-Core",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120362","RP-121581","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#58 completed. TR 36.837 v100 for Information and Approval","36.101, new 36.837",55,28,null,null,"2012-02-23","2012-12-05"]
[5887,550113,"   Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-Perf",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120382","RP-121582","Renesas Mobile","Timo Roman","RP#58 completed",36.100999999999999,55,28,null,null,"2012-02-23","2012-11-27"]
[5890,550114,"   Core part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-Core",2,"Rel-11","R4,R2,R3","2012-03-05","2012-09-07",1,"RP-120384","RP-121019","China Mobile","Xiaodong Shen","RP#57 completed","36.211, 36.213, 36.331, 36.423",55,28,null,null,"2012-02-23","2012-09-06"]
[5891,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508, 36.523-1, 36.523-2, 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[{"$f":"A5894+1","v":5894},510130,"      Core part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Core",3,"Rel-11","R1,R2,R4,R3","2011-03-22","2013-08-27",1,"RP-121999","RP-130059","Nokia","lars.e.lindh@nokia.com","RP#59 completed. New TR 36.823 v100 for Information and Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new 36.823",51,26,null,null,"2011-03-14","2013-02-27"]
[5899,480023,"      LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7",3,"Rel-11","R4","2010-12-10","2012-12-07",1,"RP-120830","-","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed. In Europe Band 3,7,20 are interesting for LTE and LTE-Advanced deployment. Different CA combinations for these bands are of high priority for Region 1","LTE",48,25,null,null,"2010-06-04","2012-09-04"]
[5902,500017,"      LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17",3,"Rel-11","R4","2010-12-10","2012-12-07",1,"RP-121458","-","AT&T","marc.grant@att.com ","Stage 3. RP#57 Core completed. RP#58 Perf completed","LTE",50,26,null,null,"2010-12-10","2012-11-26"]
[5905,500018,"      LTE Advanced Carrier Aggregation of Band 4 and Band 13","LTE_CA_B4_B13",3,"Rel-11","R4","2010-12-10","2012-12-07",1,"RP-120905","-","Ericsson","christian.bergljung@ericsson.com ","Stage 3. RP#57 Core completed. RP#58 Perf completed","LTE",50,26,null,null,"2010-12-10","2012-11-27"]
[5909,510122,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120877","RP-121592","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[5912,510123,"         Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","RP-121596","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[5915,510124,"         Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20-Core",4,"Rel-11","R4","2011-03-22","2012-09-07",1,"RP-120889","RP-121032","Huawei","Steven Chen","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[5916,510224,"         Perf. part: LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20-Perf",4,"Rel-11","R4","2011-03-25","2012-09-07",1,"RP-120889","RP-121033","Huawei","Steven Chen","RP#57 completed","36.133, 36.141",51,26,null,null,"2011-03-14","2012-09-04"]
[5920,510026,"      LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5",3,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110433","-","AT&T","marc.grant@att.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[5924,510127,"         Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17-Core",4,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110434","RP-121598","AT&T","marc.grant@att.com ","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.141, 36.307, new generic 36.850",51,26,null,null,"2011-03-14","2012-11-26"]
[5927,530123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120887","RP-121046","Vodafone","tim.frost@vodafone.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",53,27,null,null,"2011-09-15","2012-09-04"]
[5930,530124,"         Core part: LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-120888","RP-121600","Vodafone","Luis.Anaya@vodafone.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.307, new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[5934,530226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5-Perf",4,"Rel-11","R4","2011-09-21","2012-09-07",1,"RP-120899","RP-121043","SK Telecom","Haesung Park","RP#57 completed","36.133, 36.141",53,27,null,null,"2011-09-15","2012-09-04"]
[5937,530227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Perf",4,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-121152","RP-121591","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed","36.101, 36.104, 36.133, 36.141, 36.307",53,27,null,null,"2011-09-15","2012-11-27"]
[5940,540220,"         Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Perf",4,"Rel-11","R4","2011-12-15","2012-12-07",1,"RP-120898","RP-121603","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed",36.133000000000003,54,28,null,null,"2011-12-07","2012-12-04"]
[5941,540021,"      LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18",3,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-120892","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Stage 3. RP#57 completed","LTE",54,28,null,null,"2011-12-07","2012-09-04"]
[5945,540122,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Core",4,"Rel-11","R4,R2","2012-03-05","2012-09-07",1,"RP-120866","RP-120552","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101, 36.104, 36.133, 36.307, new generic 36.850",54,28,null,null,"2011-12-07","2012-06-15"]
[5949,540223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Perf",4,"Rel-11","R4","2011-12-13","2012-12-07",1,"RP-121173","RP-121055","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed","36.133, 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[5952,550218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Perf",4,"Rel-11","R4","2012-03-06","2012-12-07",1,"RP-121162","RP-121587","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed","36.133, 36.141",55,28,null,null,"2012-02-23","2012-11-27"]
[5955,520115,"         Core part: LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38-Core",4,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110862","RP-121060","Huawei","ronnie.zhang@huawei.com","RP#57 completed. TR 36.830 v100 for Information & Approval","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.833-1-38 [instead of 36.830]",52,27,null,null,"2011-06-02","2012-09-04"]
[5959,520216,"         Perf. part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Perf",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120127","Clearwire","michael.hart@clearwire.com","RP#55 completed","36.101, 36.104, 36.133, 36.141, 36.307",52,27,null,null,"2011-06-02","2012-02-23"]
[5962,530228,"         Perf. part: LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7-Perf",4,"Rel-11","R4","2011-09-20","2012-09-07",1,"RP-121193","RP-121063","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","RP#57 completed","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141",53,27,null,null,"2011-09-15","2012-09-04"]
[5966,500019,"Eight carrier HSDPA","8C_HSDPA",1,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-12-07",1,"RP-101419","-","Ericsson","johan.hultell@ericsson.com","Stage 3","UTRA",50,26,null,null,"2010-12-10","2012-09-04"]
[5967,500119,"   Core part: Eight carrier HSDPA","8C_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-06-15",1,"RP-101419","RP-120971","Ericsson","johan.hultell@ericsson.com","RP#57 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306",50,26,null,null,"2010-12-10","2012-09-04"]
[5970,500121,"   Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc-Perf",2,"Rel-11","R4","2010-12-10","2011-09-16",1,"RP-111244","RP-110996","China Mobile","Li Nan (linan@chinamobile.com)","RP#53 completed. TR 25.873v100 for Approval","25.102, new 25.873",50,26,null,null,"2010-12-10","2011-09-12"]
[5974,500222,"   Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop","HSPA_UL_TxDiv-CL-Perf",2,"Rel-11","R4","2010-12-14","2013-09-06",1,"RP-120367","RP-130477","Huawei","zongjie.wang@huawei.com","RP#61 completed","25.101, 25.104, 25.133, 25.141",50,26,null,null,"2010-12-10","2013-08-30"]
[5977,590008,"   Test part: Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv-UEConTest",2,"Rel-11","R5","2013-03-04","2014-06-13",1,"RP-130351","RP-140767","Qualcomm","Shubhang Vora (svora@qti.qualcomm.com)","RP#64 completed","34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",59,30,null,null,"2013-01-29","2014-06-10"]
[5980,510218,"   Perf. part: Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config-Perf",2,"Rel-11","R4","2011-03-24","2012-06-15",1,"RP-110308","RP-120475","Telus Communications","jorge.delrio@telus.com ","RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",51,26,null,null,"2011-03-14","2012-06-09"]
[5984,510020,"Further Enhancements to CELL_FACH","Cell_FACH_enh",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-18","2015-03-13",1,"RP-111321","-","Qualcomm","Ravi Agarwal","-","UTRA",51,26,null,null,"2011-03-14","2011-09-16"]
[5987,600004,"   Test part: Further Enhancements to CELL_FACH","Cell_FACH_enh-UEConTest",2,"Rel-11","R5","2013-06-15","2015-03-13",1,"RP-130644","RP-150132","Ericsson","leif.mattisson@ericsson.com","¦Stat Rep: RP-141164->RP-141770 1st Apr 15: Compl:92%->100% 1st Apr 15: Stat Rep: RP-141770->RP-150132","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 ",60,31,null,null,"2013-05-22","2015-04-01"]
[5989,530134,"   Core part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-Core",2,"Rel-11","R2,R1,R3,R4","2011-09-19","2012-12-07",1,"RP-111375","RP-121551","Nokia Siemens Networks","Alexander Sayenko","RP#58 completed","25.101, 25.104, 25.133, 25.211, 25.212, 25.214, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433",53,27,null,null,"2011-09-15","2012-11-27"]
[5992,530035,"Four Branch MIMO transmission for HSDPA","4Tx_HSDPA",1,"Rel-11","R1,R2,R3,R4","2011-09-19","2013-12-06",1,"RP-111393","-","Ericsson","johan.hultell@ericsson.com","Stage 3","UTRA",53,27,null,null,"2011-09-15","2012-11-27"]
[5995,540009,"MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA",1,"Rel-11","R1,R2,R3,R4","2011-12-09","2013-09-06",1,"RP-121794","-","Nokia Siemens Networks","Karri Ranta-aho","Specified UE and BS performance requirements for uplink MIMO together with QPSK and 16QAM modulations for E-DCH/HSUPA. 64QAM is for future releases","UTRA",54,28,null,null,"2011-12-07","2013-02-27"]
[5999,540124,"   Core part: HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC-Core",2,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","RP-120987","Ericsson","muhammad.kazmi@ericsson.com","RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101, 25.104, 25.141, 25.317 replaced by new 25.327",54,28,null,null,"2011-12-07","2012-09-04"]
[6002,480004,"(Small) Technical Enhancements and Improvements for Rel-11","TEI11",1,"Rel-11","SP,CP,RP,GP","2010-06-18","2012-09-20",1,"-","-","-","-","SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs#","-",48,25,null,null,"2009-06-02","2010-12-13"]
[6006,450047,"Study on IMS based Peer-to-Peer Content Distribution Services","FS_IMS_P2P",1,"Rel-11","S1,S2","2009-09-11","2010-06-10",1,"SP-090491","-","China Mobile","Li Gang (ligangyf@chinamobile.com)","SP#48 completed. 3/3/15: start date corrected (was 05/09)",22.905999999999999,45,23,null,null,"2009-09-21","2015-03-03"]
[6008,480033,"Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX","FS_VINE",1,"Rel-11","S1,S2","2010-09-23","2011-03-23",1,"SP-100411","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices",22.809000000000001,48,25,null,null,"2010-06-06","2011-06-06"]
[6013,460030,"Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","FS_rSRVCC",1,"Rel-11","S2","2009-12-10","2011-12-14",1,"SP-090806","-","Orange","delphin.barankanira@orange-ftgroup.com","SP#54 completed. Study on \"reverse direction\" from UTRAN/GERAN to E-UTRAN/HSPA (Rel-8 SRVCC was in the other direction E-UTRAN/HSPA to GERAN/UTRAN)",23.885000000000002,46,24,null,null,"2009-12-06","2012-03-04"]
[6014,510044,"Study on Roaming Architecture for Voice over IMS with Local Breakout","FS_RAVEL",1,"Rel-11","S2","2011-03-23","2011-12-14",1,"SP-110087","-","Deutsche Telekom","michele.zarri@telekom.com","SP#54 completed. Linked to Rel-11 OSCAR (Optimized Service Charging and Allocation of ResourcES in CP-150IMS whilst Roaming) UID_490032. Related to LBO/home routing decision",23.85,51,26,null,null,"2011-02-21","2011-11-28"]
[6017,520036,"Study on Mobile 3D Video Coding","FS_M3DVC",1,"Rel-11","S4","2011-06-08","2012-06-20",1,"SP-110310","-","Orange","gilles.teniou@orange-ftgroup.com","SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS",26.905000000000001,52,27,null,null,"2011-05-26","2012-08-20"]
[6020,510045,"Study on OAM aspects of inter-RAT Energy Saving","FS_OAM_ES_iRAT",1,"Rel-11","S5","2011-03-23","2011-12-14",1,"SP-110138","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES)",32.834000000000003,51,26,null,null,"2011-03-09","2012-04-02"]
[6024,470014,"Study on Coordinated Multi-Point operation for LTE","FS_CoMP_LTE",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101425","RP-111343","Samsung","bruno.clerckx@samsung.com","RP#53 completed","LTE 36.819",47,24,null,null,"2010-03-19","2011-05-27"]
[6027,510037,"Study on further Downlink MIMO enhancements for LTE-Advanced","FS_LTE_eDL_MIMO_enh",1,"Rel-11","R1","2011-03-18","2011-12-09",1,"RP-111366","RP-111550","Alcatel-Lucent","federico.boccardi@alcatel-lucent.com","RP#54 completed","LTE 36.871",51,26,null,null,"2011-03-21","2011-12-08"]
[6029,530053,"Study on LTE Coverage Enhancements","FS_Cov_Enh_LTE",1,"Rel-11","R1,R2","2011-09-19","2012-06-15",1,"RP-120225","RP-120589","China Telecom","Peng Chen (chenpeng@ctbri.com.cn)","RP#56 completed. TR 36.824 v200 for Approval","LTE 36.824",53,27,null,null,"2011-09-19","2012-06-09"]
[6035,500002,"Study on UE Application Layer Data Throughput Performance","FS_UE_App_Data_Perf",1,"Rel-11","R5,R4","2010-09-16","2011-09-16",1,"RP-101422","RP-111543","Spirent","ron.borsato@spirent.com","RP#54 completed","UTRA, LTE 37.901",50,26,null,null,"2010-12-08","2011-11-29"]
[6038,520018,"Study on UMTS/LTE in 900 MHz band (Japan, Korea)","FS_UTRA_LTE_900MHz",1,"Rel-11","R4","2011-06-07","2012-06-15",1,"RP-120617","RP-120580","NTT DoCoMo","Masahiro Fujii (fujiima@nttdocomo.co.jp)","RP#56 completed. Updated WID RP-111751=>RP-120617. TR 37.804 v100 for Information and Approval. Linked to Study on Interference analysis between 800~900 MHz bands UID_510038","UTRA, LTE 37.804",52,27,null,null,"2011-05-27","2012-06-06"]
[6039,500014,"Study on Uplink MIMO","FS_UTRA_UL_MIMO",1,"Rel-11","R1","2010-12-10","2011-09-16",1,"RP-101432","RP-111048","Qualcomm","Sharad Sambhwani","RP#53 completed (1-step Approval)","UTRA 25.871",50,26,null,null,"2010-12-08","2011-09-02"]
[6042,540026,"Study on HSPA feedback and signalling efficiency enhancements for LCR TDD","FS_LCRTDD_HSPAenh",1,"Rel-11","R1","2011-12-07","2012-09-07",1,"RP-111766","RP-121079","TD Tech","limei.wei@td-tech.com","RP#57 completed. TR 25.874 v100 for Information & Approval","UTRA 25.874",54,28,null,null,"2011-12-07","2012-06-09"]
[6045,390073,"Enhancements for Multimedia Priority Service","eMPS",1,"Rel-10","S1,S2,C4,C3,C1","2006-03-13","2011-03-18",1,"SP-080051","-","Telcordia","jgarraha@telcordia.com","CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044)","-",39,21,null,null,"2003-03-28","2011-03-01"]
[6049,460429,"      Stage 2 on eMPS for EPS Bearer Service","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002, 23.203, 23.221, 23.228, 23.272, 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[6054,490208,"      CT3 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","29.212, 29.213, 29.214",49,25,null,null,"2010-09-01","2011-03-01"]
[6057,410031,"   Stage 1 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-100863","-","KPN","toon.norp@tno.nl","SP#47 completed","22.011, New 22.368",41,21,null,null,"2008-09-15","2010-03-09"]
[6060,460023,"   Deleted - Security for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S3","2009-12-10","2010-09-23",1,"SP-100863","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#49 stopped (activity transferred to Rel-11 Feature SIMTC under UID_490028 \"TR on Security aspects of Machine-Type Communications\".","New 33.868",46,24,"SP-49","PCG-25","2009-09-21","2010-09-27"]
[6063,480105,"      CT1 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C1","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","23.122, 24.008, 24.301, New 24.368",48,25,null,null,"2010-05-26","2011-06-01"]
[6064,480205,"      Deleted - CT3 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C3","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 stopped (SA2 decided to move impact from CT3 to CT4). Updated WID CP-110147=>CP-110442 (no CT3 impact)","29.212, 29.213, 29.215",48,25,"CP-52","PCG-27","2010-05-26","2011-06-01"]
[6067,490003,"   GERAN part of Network Improvements for Machine-Type Communications (Stage 3)","NIMTC",2,"Rel-10","G2","2010-09-03","2011-09-02",1,"GP-101647","-","Vodafone, Ericsson","leo.patanapongpibul@vodafone.com, john.diachina@ericsson.com","GP#51 completed. GP#47 approved WID","44.018, 44.060",47,25,null,null,"2010-09-05","2011-09-05"]
[6071,430035,"Multi Access PDN Connectivity","MAPCON",1,"Rel-10","S2,C4,C1,C3","2009-03-13","2011-03-18",1,"SP-090659","-","Telecom Italia","ivano.guardini@telecomitalia.it","CP#51 completed. SP#49 Stage 2 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control)","-",43,22,null,null,"2009-03-05","2011-02-08"]
[6075,500204,"      CT1 aspects of Multi Access PDN Connectivity","MAPCON-St3",3,"Rel-10","C1","2010-12-10","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed","24.302, 24.312",50,26,null,null,"2010-10-25","2011-02-28"]
[6078,440152,"   Stage 1 - IMS Service Continuity – Inter Device Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","S1","2009-06-04","2010-03-25",1,"SP-090452","-","Huawei","Amar Deol (adeol@huawei.com)","SP#47 completed",22.228000000000002,44,23,null,null,"2009-05-25","2010-03-09"]
[6082,450030,"IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",1,"Rel-10","S1,S2,C3","2009-09-24","2010-09-17",1,"SP-090615","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM","-",45,23,null,null,"2009-09-08","2010-03-09"]
[6085,460017,"   Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",2,"Rel-10","C3","2009-12-04","2010-09-17",1,"CP-090859","-","Ericsson","Jan Holm","CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204",29.311,46,24,null,null,"2009-11-30","2010-09-01"]
[6088,470002,"   CT1 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#51 completed","24.173, 24.642",47,24,null,null,"2010-03-17","2011-02-14"]
[6089,480006,"   CT3 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C3","2010-06-04","2010-09-17",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#49 completed",29.164999999999999,48,25,null,null,"2010-05-26","2010-09-01"]
[6092,450036,"   TR on Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S2","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#51 completed. TR 23.829 for Approval","New 23.829",45,23,null,null,"2009-09-08","2010-12-01"]
[6096,450238,"   Stage 2/3 for Local IP Access","LIPA",2,"Rel-10","S2,C4,C1","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","-","-",45,23,null,null,"2009-09-08","2010-09-06"]
[6100,480208,"         CT1 part of Stage 3 for Local IP Access","LIPA",4,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","24.008, 24.301",48,25,null,null,"2010-05-26","2011-02-28"]
[6103,480007,"      Stage 3 for SIPTO for macro networks","SIPTO",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","-",48,25,null,null,"2010-05-26","2011-03-08"]
[6107,450042,"   Stage 1 for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S1","2009-09-24","2009-12-10",1,"SP-100089","-","Qualcomm","David Williams (dwilliam@qualcomm.com)","SP#46 completed",22.277999999999999,45,23,null,null,"2009-09-08","2010-10-01"]
[6110,480009,"   Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",2,"Rel-10","C1,C3","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","Stage 3",48,25,null,null,"2010-05-26","2010-12-09"]
[6113,450044,"Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",1,"Rel-10","S2,S4,C4,C3,C1,IETF","2009-07-15","2012-09-07",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#52 completed. Triggered by Rel-9 UID_440013 Vocoder rate adaptation for LTE","UTRA, LTE",45,23,null,null,"2009-09-08","2011-05-23"]
[6114,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[6117,490038,"   SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S4","2010-09-23","2011-03-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#51 completed",26.114000000000001,49,25,null,null,"2010-09-14","2011-02-18"]
[6121,490207,"      CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed","29.162, 29.163, 29.213, 29.235, 29.292",49,25,null,null,"2010-09-01","2011-05-17"]
[6125,420034,"   IMS aspects of Architecture for Home NodeB","EHNB-IMS",2,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080799","-","Alcatel-Lucent","Nicolas Drevon","SP#47 completed. Chosen solution has no normative impacts","New 23.832",42,22,null,null,"2008-12-09","2010-02-26"]
[6128,460128,"   Stage 2 for Optimal Media Routing","OMR",2,"Rel-10","S2","2010-03-25","2010-03-25",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","SP#47 completed",23.228000000000002,46,24,null,null,"2009-12-06","2010-02-26"]
[6132,480310,"      Deleted - CT4 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134","-",48,25,"CP-51","PCG-26","2010-05-26","2011-03-10"]
[6135,470027,"   Stage 1 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","S1","2010-03-25","2010-03-25",1,"SP-100170","-","Deutsche Telekom, T-Mobile","Kurt Bischinger","SP#47 completed","22.101 CR#0343",47,24,null,null,"2010-03-10","2010-03-23"]
[6136,470028,"   Stage 2 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","SP#49 completed",23.167000000000002,47,24,null,null,"2010-03-10","2010-09-06"]
[6139,480137,"   Stage 2 for S2b Mobility based on GTP","SMOG",2,"Rel-10","S2","2010-06-10","2010-09-23",1,"SP-100357","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#49 completed","23.002, 23.203, 23.402",48,25,null,null,"2010-06-06","2010-09-06"]
[6142,490209,"      CT3 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed","29.212, 29.213, 29.215",49,25,null,null,"2010-09-01","2011-03-18"]
[6147,470029,"Lawful Interception in the 3GPP Rel-10","LI10",1,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106 (LI requirements), 33.107 (LI architecture and functions), 33.108 (Handover interface for LI)",47,24,null,null,"2010-02-23","2011-03-12"]
[{"$f":"A6150+1","v":6150},470329,"   LI for EPS enhancements","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6153,470629,"   LI for H(e)NB also with Local IP Access and Selected IP Traffic Offload (LIPA, SIPTO)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106, 33.107, 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6157,470034,"HTTP-based Streaming and Download Services","HTTP_SDS",1,"Rel-10","S4,IETF","2010-03-25","2011-09-21",1,"SP-100032","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#52 completed. Work to enhance UID_430038 Rel-9 PSS and MBMS extensions","-",47,24,null,null,"2010-03-10","2011-05-26"]
[6160,480040,"PSS and MBMS enhancements","MBS_Enh",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100305","-","Ericsson","Markus.Kampmann@ericsson.com","SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). ","26.234, 26.346",48,25,null,null,"2010-05-28","2011-03-02"]
[6161,480041,"Enhancements and Addition of Audio Tests to 26.131 and 26.132","EAAT",1,"Rel-10","S4","2010-06-10","2011-06-08",1,"SP-100306","-","Vodafone","ramin.afchar@vodafone.com","SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec","26.131, 26.132",48,25,null,null,"2010-05-28","2011-05-17"]
[6167,470036,"      Deleted - Service Oriented Architecture (SOA) for IRP continuation from Rel-9","OAM-SOA-IRP",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100076","-","Nokia Siemens Networks, Ericsson","Jörg Schmidt (J.Schmidt@NSN.com), edwin.tse@ericsson.com","SP#51 work stopped (Reason: lack of progress). Continuation of Rel-9 UID_440065 SOA for IRP (covering SOA Architecture & SOA-supporting Solution Set) to address SOA conforming Registration & Discovery capabilities","32.101, 32.150",47,24,"SP-51","PCG-26","2010-03-08","2011-03-09"]
[6168,480042,"      IRP Overview, Profiles & Usage Guide","OAM-NIM-IRP_OPU",3,"Rel-10","S5","2010-06-10","2011-06-08",1,"SP-110277","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@NSN.com)","SP#52 completed. Updated WID SP-100777=>SP-110277","new 32.103",48,25,null,null,"2010-05-26","2011-06-06"]
[6172,460035,"      SON Self-optimization management continuation","LTE-SON-OAM_SO",3,"Rel-10","S5","2009-12-10","2011-06-08",1,"SP-110130","-","Huawei","Lan Zou (zlan@huawei.com)","SP#52 completed. Cont'd Rel-9 SON self-optimization management UID_390007","32.425, 32.521, 32.522, 32.526, 32.762, 32.766",46,24,null,null,"2009-12-01","2011-05-13"]
[6175,470038,"   Rel-10 Subscription Management (SuM) evolution","OAM10-SuM",2,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100086","-","Ericsson","leo.yang@ericsson.com","SP#51 completed","32.172, 32.175, 32.176",47,24,null,null,"2010-03-23","2011-03-09"]
[6179,470042,"      Management of UE based network performance measurements","OAM-PM-UE",3,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"SP-100612","-","Huawei, Nokia Siemens Networks, Ericsson","Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com","SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE)","-",47,24,null,null,"2010-02-12","2011-03-22"]
[6182,470043,"      3G HNB and LTE HeNB Subsystem performance measurements","OAM-PM-HeNS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100081","-","China Mobile","Chen Gang (chengang@chinamobile.com)","SP#51 completed","32.582, 32.592, new (32.452, 32.453)",47,24,null,null,"2010-03-08","2011-03-09"]
[6185,470046,"Advice of Charge (AoC) service support enhancements","eAoC",1,"Rel-10","S5,C1","2010-03-25","2011-06-03",1,"SP-100080","-","Deutsche Telekom","matthias.seibel@telekom.de","CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work","-",47,24,null,null,"2010-03-23","2011-05-23"]
[6188,470003,"IMS Stage 3 IETF Protocol Alignment - phase 4","IMSProtoc4",1,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100099","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not","23.218, 24.229, 24.930",47,24,null,null,"2010-03-17","2011-02-28"]
[6190,480014,"Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications","II-NNI2",1,"Rel-10","C3","2010-06-04","2013-03-01",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI)","-",48,25,null,null,"2010-05-26","2013-02-21"]
[6193,561002,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6809)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2012-12-07",1,"CP-100326","-","christer.holmberg@ericsson.com","Christer Holmberg","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",56,29,null,null,"2012-04-20","2012-12-04"]
[6197,500003,"Dynamic view of SIP message for Inter-IMS Network to Network Interface (II-NNI) (Stage 3)","NNI_DV",1,"Rel-10","C3","2010-12-10","2011-06-03",1,"CP-100795","-","NTT","arai.kenjiro@lab.ntt.co.jp","CP#52 completed. Linked to CT3 Rel-10 Feature UID_480014 Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications (II-NNI2)",29.164999999999999,50,26,null,null,"2010-11-26","2011-05-17"]
[6200,500010,"Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3)","eSRVCC",1,"Rel-10","C1,C4,IETF","2010-12-10","2012-12-07",1,"CP-100881","-","China Mobile","Jiang Y (jiangyi@chinamobile.com)","Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049","-",50,26,null,null,"2010-10-25","2013-02-21"]
[6204,500011,"Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3)","aSRVCC",1,"Rel-10","C1,R5","2010-12-10","2013-03-01",1,"CP-110145","-","ZTE","li.shitao@zte.com.cn","Builds on Rel-8 UID_390057 (IMS-Cont) TS 23.216 Stage 2. Provide Stage 3 for SRVCC PS-CS transfer of a call in alerting phase. Stage 2 TEI10 in TS 23.237 (6.3.2.1.4c/d, 6.3.2.1.7a/b)","-",50,26,null,null,"2011-03-16","2011-05-23"]
[6207,500012,"PCRF failure and restoration","PCRF_FR",1,"Rel-10","C4,C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed. Triggered by CT3 TR 29.816 Study on Policy and Charging Rules Function (PCRF) failure and restoration (FS_PCRF-FR) UID_450013 ","Stage 2/3 work",50,26,null,null,"2010-10-25","2011-03-01"]
[6209,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212, 29.213, 29.214, 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[6212,510008,"EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated","EPC_NR",1,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110092","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014","Stage 2/3: 23.007, 29.274",51,26,null,null,"2011-02-22","2011-03-18"]
[6215,510010,"UICC access to IMS Specification","IMS-UICC-S",1,"Rel-10","C6,C1","2011-03-16","2011-06-03",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC","-",51,26,null,null,"2011-03-03","2011-05-18"]
[6218,550006,"Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features","USIM_R10_Test",1,"Rel-10","C6","2012-03-05","2013-12-03",1,"CP-120396","-","Gemalto","Denis.Praca@gemalto.com","CP#62 stopped (at 70% completion 06/13). Testing for New featurES in CP-150Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111","31.121, 31.124, New 31.ABC (Conformance Testing of specific features)",55,28,"CP-62","PCG-32","2012-02-22","2013-06-06"]
[6222,440023,"   Deleted - CT3 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C3","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT3 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[6225,480002,"Tightened Link Level Performance Requirements for Single Antenna MS","TIGHTER",1,"Rel-10","G1,G2,C1,G3new","2010-09-03","2013-03-01",1,"GP-101083","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#46 approved WID","GERAN",46,25,null,null,"2010-05-27","2013-03-16"]
[6229,490001,"Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",1,"Rel-10","G2,S2,C1","2010-05-21","2011-03-04",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method","GERAN",47,25,null,null,"2010-05-27","2011-03-04"]
[6230,490101,"   Stage 2 for Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",2,"Rel-10","S2","2010-05-21","2010-12-16",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","SP#50 completed",23.251000000000001,47,25,null,null,"2010-05-27","2010-11-30"]
[6236,380077,"1.28 Mcps TDD Repeater","RANimp-Repeaters1.28TDD",1,"Rel-10","R4","2007-12-04","2010-03-19",1,"RP-071003","RP-100039","RITT","qinyan@chinattl.com","RP#47 completed","UTRA 25.113, New 25.116, 25.153 (testing)",38,21,null,null,"2007-12-17","2010-03-09"]
[6237,450019,"1.28 Mcps TDD Multi-carrier HSUPA","TDD_MC_HSUPA",1,"Rel-10","R1,R2,R3,R4","2009-09-18","2010-12-10",1,"RP-090990","RP-101079","CATR","Aihui Song (songaihui@mail.ritt.com.cn)","RP#50 completed","UTRA 25.102, 25.105, 25.123, 25.221, 25.222, 25.223, 25.224, 25.225, 25.306, 25.319, 25.321, 25.331, 25.423, 25.427, 25.433",45,23,null,null,"2009-09-15","2010-12-03"]
[6240,460214,"   Perf. part: 1.28Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF-Perf",2,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","RP-101081","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. TR 25.968 v100 for Approval","25.142, new 25.968",46,24,null,null,"2009-11-30","2010-12-03"]
[6244,450027,"AGNSS Minimum Performance for UTRAN","AGNSSPerf_UTRAN",1,"Rel-10","R4,R5","2009-09-18","2011-09-16",1,"RP-100363","-","Thales","Michel.monnerat@thalesaleniaspace.com","RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures)","UTRA",45,23,null,null,"2009-09-15","2010-12-08"]
[6247,460005,"Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN","LCS_UMTS_RFPMT",1,"Rel-10","R2,R3","2009-12-04","2011-03-18",1,"RP-091427","RP-110048","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907)","UTRA",46,24,null,null,"2009-11-30","2011-03-11"]
[6250,460115,"   Core part: Four carrier HSDPA","4C_HSDPA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-03-18",1,"RP-100991","RP-110046","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#51 completed. RP#52 TR 25.864 v200 for Approval","25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306, new 25.864",46,24,null,null,"2009-11-30","2011-05-27"]
[6255,470213,"   Perf. part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-100168","RP-110521","TD Tech","dafei.wang@td-tech.com","RP#52 completed",25.102,47,24,null,null,"2010-03-19","2011-06-01"]
[6258,530039,"   Test part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-UEConTest",2,"Rel-10","R5","2011-09-19","2012-12-07",1,"RP-120599","RP-121529","Ericsson","leif.mattisson@ericsson.com","RP#58 completed","34.108, 34.123-1, 34.123-2, 34.123-3",53,27,null,null,"2011-09-09","2012-11-28"]
[6261,480221,"   Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Perf",2,"Rel-10","R4,R2","2010-06-04","2010-09-17",1,"RP-100657","RP-100759","AT&T","Vince Spatafora (vs5785@att.com)","RP#49 stopped (Reason: no need for Performance work)","25.101, 25.104, 25.141, 25.317",48,25,"RP-49","PCG-25","2010-06-03","2010-09-09"]
[6262,480022,"MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA",1,"Rel-10","R4,R5","2010-06-04","2012-03-02",1,"RP-100993","-","Qualcomm","Heechoon Lee","RP#52 completed. RP#49 updated WID RP-100687=>RP-100993 (changed Title: MIMO Testing in HSDPA => MIMO operation with non-MIMO coexistence in HSDPA)","UTRA",48,25,null,null,"2010-06-03","2011-03-14"]
[6265,510017,"   Test part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-UEConTest",2,"Rel-10","R5","2011-03-18","2012-03-02",1,"RP-110244","RP-120042","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#55 completed","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",51,26,null,null,"2011-03-10","2012-02-23"]
[6269,460207,"   Perf. part: Carrier Aggregation for LTE","LTE_CA-Perf",2,"Rel-10","R4","2009-12-04","2011-12-09",1,"RP-100661","RP-111452","Nokia","lars.e.lindh@nokia.com","RP#54 completed","36.101, 36.104, 36.133, 36.141, 37.141",46,24,null,null,"2009-11-30","2012-06-07"]
[6272,460108,"   Core part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-03-18",1,"RP-100196","RP-110067","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 36.807",46,24,null,null,"2009-11-30","2012-06-07"]
[6276,460109,"   Core part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-Core",2,"Rel-10","R1,R2,R4","2000-01-03","2001-06-29",1,"RP-100959","RP-110537","Huawei","Mattias.wennstrom@huawei.com","RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval","36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 (36.807, 36.817)",46,24,null,null,"2009-11-30","2012-06-07"]
[6280,460113,"   Core part: Relays for LTE","LTE_Relay-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-06-03",1,"RP-110911","RP-110540","Ericsson","christian.hoymann@ericsson.com","RP#52 completed. Updated WID RP-101417=>RP-101911 (contains only Core part completed in Rel-10). Open RAN4 Core & Perf parts moved to new Rel-11","36.201, 36.211, 36.212, 36.213, 36.300, 36.321, 36.323, 36.331, New RAN1 36.216",46,24,null,null,"2009-11-30","2012-06-14"]
[6283,500038,"   LTE Relay Nodes Security","LTE_Relay-Sec",2,"Rel-10","S3,C6","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","-","-",50,26,null,null,"2010-11-25","2011-02-14"]
[6284,500238,"      TR on LTE Relay Nodes Security","LTE_Relay-Sec",3,"Rel-10","S3","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","SP#51 completed",33.816000000000003,50,26,null,null,"2010-11-25","2011-02-14"]
[6287,510012,"   Core Network Impacts for Relay Nodes","LTE_Relay-CN",2,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110094","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","23.003, 23.008, 29.303, 29.230, 29.272",51,26,null,null,"2011-02-28","2011-03-08"]
[6290,470207,"   Perf. part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-Perf",2,"Rel-10","R4","2010-03-19","2012-06-15",1,"RP-100383","RP-120461","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#56 completed","36.101, 36.133",47,24,null,null,"2010-03-19","2012-06-05"]
[6294,470208,"   Perf. part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-Perf",2,"Rel-10","R4","2010-03-19","2010-09-17",1,"RP-101003","RP-100783","Clearwire","michael.hart@clearwire.com","RP#49 completed","36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new 36.812",47,24,null,null,"2010-03-19","2010-09-16"]
[6297,470109,"   Core part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-Core",2,"Rel-10","R4,R2","2010-03-19","2011-06-03",1,"RP-110775","RP-110545","DBSD","Mariam.Sorond@ico.com","RP#52 completed","25.101, 25.104, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new 36.811",47,24,null,null,"2010-03-19","2011-06-01"]
[6301,470110,"   Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Core",2,"Rel-10","R4,R2","2009-12-11","2010-12-10",1,"RP-101284","RP-101117","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#51 completed","25.101, 25.104, 25.141, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new RAN4 36.813",47,24,null,null,"2010-03-19","2011-03-17"]
[6305,470111,"   Core part: LTE Self Optimizing Networks (SON) enhancements","SONenh_LTE-Core",2,"Rel-10","R3,R2,R4","2010-03-19","2011-06-03",1,"RP-101004","RP-110547","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#52 completed (Stage 1,2,3) ","36.300, 36.331, 36.413, 36.423",47,24,null,null,"2010-03-19","2011-05-24"]
[6308,540008,"   Test part: Further enhancements to MBMS for LTE","MBMS_LTE_enh-UEConTest",2,"Rel-10","R5","2011-12-02","2012-03-02",1,"RP-111615","RP-120049","Huawei","Zhang Xin (suzanna.zhang@huawei.com)","RP#55 completed","36.508, 36.523-1, 36.523-2, 36.523-3",54,28,null,null,"2011-11-24","2012-02-23"]
[6309,380173,"UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",1,"Rel-10","R4,R2,R3,R5","2007-11-30","2013-06-14",1,"RP-091380","-","Ericsson","johan.skold@ericsson.com","-","UTRA, LTE",38,21,null,null,"2007-12-17","2013-06-03"]
[6312,420014,"   Conformance Test Aspects – UMTS 3500","RInImp-UEConTest_UMTS3500",2,"Rel-10","R5","2008-12-05","2012-06-15",1,"RP-110386","RP-120450","Ericsson","fredrik.sundstrom@ericsson.com","RP#56 completed","34.108, 34.121-1, 34.121-2",42,22,null,null,"2008-11-27","2012-06-05"]
[6315,530041,"   Test part: Minimization of Drive Tests for E-UTRAN","MDT_UMTSLTE-UEConTest",2,"Rel-10","R5","2011-09-19","2013-03-01",1,"RP-120598","RP-130036","Ericsson","leif.mattisson@ericsson.com","RP#59 completed. Testing for LTE only","LTE 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 ",53,27,null,null,"2011-09-06","2013-02-27"]
[6318,550002,"   Test part: HeNB Mobility Enhancements","HNB_HENB_mob_enh-UEConTest_LTE",2,"Rel-10","R5","2012-03-05","2012-12-07",1,"RP-120218","RP-121533","Qualcomm","Anjali Mishra (ajha@qualcom.com)","RP#58 completed","34.108, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3",55,28,null,null,"2012-02-23","2012-09-04"]
[6323,480025,"Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments","MSR_NC",1,"Rel-10","R4,G1","2010-06-04","2011-11-25",1,"RP-101402","-","Ericsson","johan.skold@ericsson.com","-","UTRA, LTE, GERAN",48,25,null,null,"2010-06-04","2011-09-12"]
[6326,490004,"   GERAN part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-GERAN",2,"Rel-10","G1","2010-09-03","2011-11-25",1,"GP-101618","-","Ericsson","mats.y.samuelsson@ericsson.com ","-","-",47,25,null,null,"2010-09-05","2011-05-21"]
[6330,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[6333,350014,"Deleted - Registration in Densely-populated area (RED)","RED",1,"Rel-10","S1","2007-03-12","2009-09-24",1,"SP-070133","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned","-",35,18,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6334,370030,"   Deleted - Stage 1 for RED","RED",2,"Rel-10","S1","2007-03-12","2007-03-15",1,"SP-070133","-","NTT DoCoMo","takakurat@s1.nttdocomo.co.jp","SP#35 completed. SP#46 work stopped/abandoned","22.101 CR#0207",37,19,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6337,380162,"   Deleted - Stage 1 for N3GtoNSP","N3GtoNSP",2,"Rel-10","S1","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",22.010999999999999,38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6343,460010,"Deleted - Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF",1,"Rel-10","R4,R5","2009-12-04","2011-06-03",1,"RP-091432","-","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions). Add new power classES in CP-150E-UTRAN UL to allow CPE type applications to be operated at higher max output power","LTE",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[6345,460210,"   Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-UEConTest",2,"Rel-10","R5","2009-12-04","2011-06-03",1,"RP-091432","RP-110504","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions)","36.521-1",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[6348,470006,"Deleted - Enhanced Interference Management for Home NodeBs","HNB_IM",1,"Rel-10","R3","2010-03-19","2010-09-17",1,"RP-100392","RP-100754","Qualcomm","Andrei Radulescu (aradules@qualcomm.com)","RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs","UTRA",47,24,"RP-49","PCG-25","2010-03-19","2010-09-09"]
[6352,370047,"   Use cases definition and service and system requirements","FS_EV_EPS-S1",2,"Rel-10","S1","2007-09-03","2008-12-11",1,"SP-070698","-","France Telecom","philippe.lottin@orange.com","SP#47 completed. TR 22.813-100 for Approval",22.812999999999999,37,19,null,null,"2007-10-04","2010-08-31"]
[6355,410039,"Study on Personal Broadcast Service","FS_PBS",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080504","-","ETRI","Jaihyung Cho","SP#47 completed",22.946999999999999,41,21,null,null,"2008-09-15","2010-03-09"]
[6358,370050,"Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media","FS_IMS_LBO_ORM",1,"Rel-10","S2","2007-10-01","2009-12-10",1,"SP-080556","-","Telecom Italia, BT","mario.madella@telecomitalia.it, victor.kueh@bt.com","SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011",23.893999999999998,37,19,null,null,"2007-10-02","2009-11-25"]
[6359,390055,"Study on Intra Domain Connection of RAN Nodes to Multiple CN Nodes","FS_IDC",1,"Rel-10","S2","2008-03-12","2010-03-25",1,"SP-080094","-","China Mobile","LIU HONG (liuhongyfw@chinamobile.com)","SP#47 completed. Concluded no further normative work expected. Linked to 23.236","23.924 (was 23.823)",39,21,null,null,"2007-12-20","2010-03-23"]
[6362,470049,"Study on S2b Mobility based on GTP","FS_SMOG",1,"Rel-10","S2","2010-03-25","2010-06-10",1,"SP-100169","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101",23.834,47,24,null,null,"2010-03-10","2010-06-07"]
[6368,460037,"Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model","FS_3GNRM_TMFSID",1,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-090759","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#51 completed",32.828000000000003,46,24,null,null,"2009-12-01","2011-03-09"]
[6370,480045,"Study on Alarm Correlation and Alarm Root Cause Analysis","FS_AC_ARCA",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100775","-","Ericsson","edwin.tse@ericsson.com","SP#51 completed",32.832000000000001,48,25,null,null,"2010-05-26","2011-03-09"]
[6373,480016,"Study on User Data Convergence (UDC) evolution ","FS_UDCe",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100296","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model",23.844999999999999,48,25,null,null,"2010-05-26","2011-02-28"]
[6377,470015,"Study on Potential solutions for energy saving for E-UTRAN","FS_Energy_LTE",1,"Rel-10","R3,R2","2010-02-02","2011-06-03",1,"RP-100674","RP-110597","China Mobile","Yang Ning (yangning@chinamobile.com)","RP#52 completed","LTE 36.927",47,24,null,null,"2010-03-19","2011-06-02"]
[6380,410042,"Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services","FS_eIMS_IBCF",1,"Rel-10","S2","2008-09-18","2010-12-15",1,"SP-090809","-","Starent Networks","Rajat Ghai (rghai@starentnetworks.com)","SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS)",23.847999999999999,41,21,"SP-50","PCG-26","2008-09-15","2010-12-13"]
[6383,0,"--- RELEASE 9 ---","-",1,"Rel-9","CP,GP,RP,SP","2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[6384,400035,"Enhanced Home NodeB / eNodeB","EHNB",1,"Rel-9","S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP","2008-06-05","2011-12-09",1,"SP-090214","-","T-Mobile","michael.kurz@t-mobile.at ","RP#54 Testing completed","UTRA, LTE",40,21,null,null,"2007-12-13","2011-11-29"]
[6389,450004,"   CT6 aspects - Support of Home NB and Home eNB enhancements","EHNB-CT6",2,"Rel-9","C6","2009-09-18","2010-03-19",1,"CP-090741","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#47 completed. Storing of CSG related data items on the USIM",31.102,45,23,null,null,"2009-07-09","2010-03-16"]
[6391,430012,"   3G HNB and LTE HeNB OAM&P Type 1 Interface","HNB_eHNB-OAM_Type1",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090208","-","Huawei","Zou Lan (zlan@huawei.com)","SP#47 completed","32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594)",43,22,null,null,"2009-03-09","2010-03-08"]
[6395,430025,"   Home NB and Home eNB enhancements - RAN3 aspects","EHNB-RAN3",2,"Rel-9","R3","2009-03-06","2009-12-04",1,"RP-090349","RP-091050","Alcatel-Lucent","Martin Warner (mw15@alcatel-lucent.com)","RP#46 completed (based on high priority items specified in RP-090995)","25.413, 25.467, 25.467, 25.468, 25.469, 25.469, 36.401, 36.413, New 25.444",43,22,null,null,"2009-03-10","2009-11-27"]
[6398,500023,"   Conformance Test Aspects – Home eNB enhancements","EHNB-LTE_UEConTest",2,"Rel-9","R5","2010-12-10","2011-09-16",1,"RP-101191","RP-110972","Qualcomm","Mrs Lena Chaponniere (lchaponn@qualcomm.com)","RP#53 completed","36.508, 36.523-1, 36.523-2, 36.523-3",50,26,null,null,"2010-12-10","2011-09-06"]
[6402,410011,"   CT4 aspects of VAS4SMS Interface and Signalling Flow","VAS4SMS",2,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090813","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed","new 23.142",41,21,null,null,"2008-09-11","2009-12-02"]
[6405,410024,"   Stage 1 for Definition of End-User Identity","EUI",2,"Rel-9","S1","2007-09-03","2008-12-11",1,"SP-090380","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905)",21.905000000000001,38,21,null,null,"2007-10-02","2009-06-11"]
[6408,440041,"   Stage 3 for IMS Customized Ringing Signal (CRS) Service","CRS",2,"Rel-9","C1","2009-05-29","2009-12-03",1,"CP-090444","-","China Mobile","wangzhao","CP#48 completed","24.173, new 24.183",44,23,null,null,"2009-05-13","2010-05-28"]
[6410,380058,"   Stage 1 for Public Warning System","PWS",2,"Rel-9","S1","2007-12-06","2008-12-11",1,"SP-070876","-","T-Mobile","Mark.Younge@t-mobile.com","SP#42 completed",22.268000000000001,38,21,null,null,"2007-12-13","2008-12-05"]
[6413,440031,"      CT4 aspects of Stage 3 for Public Warning System","PWS-St3",3,"Rel-9","C4","2009-05-30","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#46 completed",29.167999999999999,44,23,null,null,"2009-05-13","2009-12-03"]
[6417,400043,"   Stage 1 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","S1","2008-06-05","2008-06-05",1,"SP-080430","-","Vodafone","armin.toepfer@vodafone.com","SP#40 completed ",22.259,40,21,null,null,"2007-12-13","2008-12-05"]
[6420,400032,"Multi-Media Telephony Service enhancements","eMMTel",1,"Rel-9","S1,S5,C1","2008-06-05","2010-03-25",1,"SP-080503","-","France Telecom","philippe.lottin@orange.com","SP#47 completed","-",40,21,null,null,"2007-12-13","2008-12-05"]
[6423,430032,"   Support of Real-time Transfer of Tariff Information (RTTI) in IMS charging","IMSTSS-RTTI-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090306","-","Orange","Jean-Luc Garcia (jl.garcia@orange-ftgroup.com)","SP#47 completed. Linked to SA5 Rel-8 UID_380042 AoC support in IMS Charging (IMSTSS)","32.240, 32.280, 32.298, 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[6427,430103,"   Stage 2/3 for User Data Convergence (UDC) Technical Realization","UDC-CN",2,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","-","-",43,22,null,null,"2009-03-04","2010-03-09"]
[6430,440060,"   User Data Convergence (UDC) Modelling and Management","UDC-MMAN",2,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090309","-","T-Mobile, China Mobile, Ericsson","istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com","SP#48 completed","-",44,23,null,null,"2009-05-18","2010-05-26"]
[6431,440062,"      UDC – Framework for Model Handling and Management","UDC-MMAN-MFRM",3,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090311","-","T-Mobile","istvan.aba@t-mobile.at","SP#48 completed","32.172, new 32.181",44,23,null,null,"2009-05-18","2010-05-26"]
[6435,410134,"   Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","-","-",41,21,null,null,"2008-09-15","2012-07-20"]
[6438,410135,"   Stage 2/3 for IMS Centralized Services","IMS_SCC-ICS",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-","-",41,21,null,null,"2008-09-15","2009-06-02"]
[6442,420020,"Service Specific Access Control in EPS","SSAC",1,"Rel-9","S1,C1,R5","2008-12-11","2012-06-15",1,"SP-080882","-","NTT DoCoMo","Frederic Thepot (thepot@docomolab-euro.com)","CP#47 completed. Triggered by TR 22.986 Study on Service Specific Access Control in EPS. As EPS is a PS-Domain only system, Domain Specific Access Control (DSAC) doesn't apply, hence SSAC allows restriction of voice and non-voice calls separately","-",42,22,null,null,"2008-12-05","2010-03-04"]
[6445,520014,"   Conformance Test Aspects - Service Specific Access Control","SSAC_UEConTest",2,"Rel-9","R5","2011-06-07","2012-06-15",1,"RP-110765","RP-120447","NTT DoCoMo","Takao.Shimizu.rp@nttdocomo.com","RP#56 completed. Testing for Stage 3 for Service Specific Access Control in EPS (24.173, 27.007) UID_440040","34.229-1, 34.229-2, 34.229-3",52,27,null,null,"2011-05-23","2012-06-05"]
[6448,410037,"   Stage 2 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",2,"Rel-9","S2","2008-01-14","2009-06-04",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#44 completed","23.869, 23.060, 23.167, 23.203, 23.221, 23.228, 23.271, 23.401, 23.402",38,21,null,null,"2008-09-15","2009-06-01"]
[6452,480029,"      Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS_UEConTest",3,"Rel-9","R5","2010-06-04","2012-06-15",1,"RP-100567","RP-120445","Samsung","stoyan.baev@partner.samsung.com","RP#56 completed","34.108, 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2, 34.229-3, 36.508, 36.523-1, 36.523-2, 36.523-3",48,25,null,null,"2010-06-04","2012-06-05"]
[6456,470017,"   Conformance Test Aspects – Support for IMS Emergency Calls over LTE","IMS_EMER_LTE_UEConTest",2,"Rel-9","R5","2010-03-25","2010-12-10",1,"RP-100118","RP-101068","Ericsson","leif.mattisson@ericsson.com","RP#50 completed","36.508, 36.523-1, 36.523-2, 36.523-3",47,24,null,null,"2010-03-10","2010-12-08"]
[6457,410038,"   Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",2,"Rel-9","S2,C1,C4,C3,IETF","2008-09-18","2014-06-13",1,"SP-090099","-","China Mobile","Yu Qing (Yuqing@chinamobile.com)","CP#56 added IETF dependency","-",41,21,null,null,"2008-09-15","2009-03-05"]
[6460,440027,"         CT1 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","24.229, 24.237",44,23,null,null,"2009-05-13","2009-12-02"]
[6463,561003,"         (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254)","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C3-IETF","2012-04-20","2014-06-13",1,"CP-090882","-","Andrew Allen","Andrew Allen","CP#64 completed","RFC 7254 (was draft-montemurro-gsma-imei-urn)",56,29,null,null,"2012-04-20","2014-06-06"]
[6467,440020,"      CT4 aspects of Control Plane LCS in the EPC","LCS_EPS-CPS",3,"Rel-9","C4","2009-05-29","2010-03-19",1,"CP-090811","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","CP#47 completed (IANA registrations outstanding). Stage 3 SLs and SLg interfaces & transport of positioning messages between E-SMLC and MME in the scope of UID_420006 (Positioning Support for LTE)","24.080, 29.002, 29.272, 29.230, new 24.171, 29.171, 29.172, 29.173",44,23,null,null,"2009-05-13","2010-03-09"]
[{"$f":"A6470+1","v":6470},470018,"   Conformance Test Aspects – Positioning Support for LTE","LCS_LTE_UEConTest",2,"Rel-9","R5","2010-03-19","2012-03-02",1,"RP-111209","RP-120034","Qualcomm","Shubhang Vora (svoral@qualcomm.com)","RP#55 completed. RP#56 TS 37.571-4 v200 for Approval","36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5)",47,24,null,null,"2010-03-17","2012-06-06"]
[6473,420023,"   Security for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#46 completed",33.246000000000002,42,22,null,null,"2008-12-09","2009-12-09"]
[6477,430007,"   MBMS support in LTE","MBMS_LTE",2,"Rel-9","R2,R3,R4","2009-03-06","2010-03-19",1,"RP-091457","RP-100033","Huawei","arnaud.meylan@huawei.com","RP#47 completed","25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445",43,22,null,null,"2009-03-10","2010-03-16"]
[6481,450006,"   CT1 aspects of Access Network Discovery and Selection Function enhancements","eANDSF",2,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090742","-","Panasonic","benjamin.limck@sg.panasonic.com","CP#47 completed","24.302, 24.312",45,23,null,null,"2009-09-08","2010-03-02"]
[6482,430034,"Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",1,"Rel-9","S2,C4,C1","2009-03-13","2010-03-19",1,"SP-090098","-","Samsung","erik.guttman@partner.samsung.com","CP#47 completed. Continues Rel-8 SAES Stage 2 UID_320005. Stage 1 in 22.278 (EPS Service requirements)","-",43,22,null,null,"2009-03-05","2010-03-04"]
[6485,450008,"   CT1 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",2,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090515","-","Samsung","Surjyakanta Mohapatra (surjya.kanta@samsung.com)","CP#47 completed",24.302,45,23,null,null,"2009-03-05","2010-03-02"]
[6488,450051,"   SA4 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090653","-","Qualcomm","Nikolai Leung","SP#46 completed",26.114000000000001,45,23,null,null,"2009-05-28","2009-12-07"]
[6492,33025,"Access Security Enhancements","ACCSEC2",1,"Rel-9","S3","2007-07-02","2009-06-04",1,"SP-040865","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security)","33.102, 43.020",33,17,null,null,"2005-03-24","2010-08-06"]
[6495,410029,"   SA3 work on PUCI","PUCI",2,"Rel-9","S3","2008-09-18","2009-12-10",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#46 completed. No normative work done in Rel-9","New 33.937",41,21,null,null,"2008-09-15","2009-12-07"]
[6498,521007,"   (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3-IETF,C1-IETF,C3-IETF","2009-03-18","2012-09-14",1,"SP-090128","-","Peter Dawes","-","CP#57 completed, ietf-draft discontinued, documented within 3GPP","draft-dawes-dispatch-mediasec-parameter",52,27,null,null,"2011-06-20","2012-09-03"]
[6503,460021,"      CT3 aspects of IMS Media Plane Security","MEDIASEC_CORE",3,"Rel-9","C3","2009-12-04","2010-06-04",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#48 completed",29.161999999999999,46,24,null,null,"2009-12-02","2010-05-27"]
[6506,440054,"Extended Identity Management","GBA-IdM",1,"Rel-9","S3","2009-06-04","2009-12-10",1,"SP-090284","-","Nokia","Silke.Holtmanns@nokia.com","SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous)","New 33.924, CT4 29.109 (added service code)",44,23,null,null,"2009-05-18","2010-02-23"]
[6507,440056,"Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",1,"Rel-9","S3,IETF","2009-06-04","2012-12-07",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","Continuation of Rel-8 UID_390044 SAE security architecture. Covers gaps in backhaul security in SAE (also applicable to UTRAN and GERAN backhaul)","-",44,23,null,null,"2009-05-18","2012-11-24"]
[6510,440256,"   Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","C4","2009-06-04","2009-12-04",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","CP#46 completed. No impact on CT4 specs","-",44,23,"CP-46","PCG-24","2009-05-18","2009-11-25"]
[6513,440357,"   CT1 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C1","2009-06-04","2009-09-18",1,"SP-090287","-","Ericsson","Karl Norrman","CP#45 completed","24.008,44.064",44,23,null,null,"2009-05-18","2009-09-08"]
[6517,440257,"   Deleted - SA2 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090287","-","Ericsson","Karl Norrman","SP#45 work stopped/abandoned",23.06,44,23,"SP-45","PCG-23","2009-05-18","2009-09-07"]
[6519,430037,"Managing MTSI Media Adaptation","M3A",1,"Rel-9","S4","2009-03-12","2009-12-10",1,"SP-090021","-","Samsung","kyunghun.jung@samsung.com","SP#46 completed. Work extending Rel-8 UID_34041 MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size. Update speech/video adaptation algorithms used by network to control MTSI client terminal in congestion or poor transmission conditions.",26.114000000000001,43,22,null,null,"2009-02-02","2009-12-07"]
[6525,450048,"Distortion Measurement Test Methods and Requirements","DTMR",1,"Rel-9","S4","2009-09-24","2010-03-25",1,"SP-090575","-","Motorola","Stephen Kendall (wcsk01@motorola.com)","SP#47 completed","26.131, 26.132",45,23,null,null,"2009-09-21","2009-12-02"]
[6528,420031,"      Software Management for Network Elements","OAM9-NE_SWM",3,"Rel-9","S5","2008-12-11","2010-03-25",1,"SP-080756","-","Huawei, Nokia Siemens Networks","Bidipta Das (bidipta@huawei.com), Clemens Suerbaum (clemens.suerbaum@nsn.com)","SP#47 completed","32.531, 32.532, 32.533, new 32.537",42,22,null,null,"2008-12-03","2010-03-08"]
[6531,420032,"   Rel-9 Performance Management","OAM9-PM",2,"Rel-9","S5","2009-03-12","2010-06-10",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[6532,440059,"      Enhancement of UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-06-04","2009-12-10",1,"SP-090308","-","China Mobile","liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao","SP#46 completed",32.405000000000001,44,23,null,null,"2009-05-18","2009-12-01"]
[6535,430043,"   Rel-9 Self-Organizing Networks (SON) - OAM aspects","OAM9-SON",2,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","SP#43 umbrella BB created to host OAM WIs","-",43,22,null,null,"2009-03-09","2010-02-09"]
[6538,440058,"   Rel-9 Subscription Management (SuM) evolution","OAM9-SuM",2,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090307","-","Ericsson","frode.nergard@ericsson.com","SP#48 completed","32.140, 32.141, 32.152, 32.172, 32.175",44,23,null,null,"2009-05-18","2010-05-26"]
[6544,410008,"IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",1,"Rel-9","C4,C3","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","-",41,21,null,null,"2007-09-05","2009-07-29"]
[6546,410208,"   CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C3","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","29.162, 29.235",41,21,null,null,"2007-09-05","2009-11-25"]
[6550,440017,"Completion of IMS Restoration Procedures","eIMS_RP",1,"Rel-9","C3,C4,C1","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed. Continuation of Rel-8 Feature UID_400012 IMS Restoration Procedures","-",44,23,null,null,"2009-05-13","2010-04-01"]
[6553,460022,"   CT3 aspects of Completion of IMS Restoration Procedures","eIMS_RP",2,"Rel-9","C3","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed","29.061, 29.212, 29.213, 29.214, 29.215",46,24,null,null,"2009-05-13","2010-03-02"]
[6556,521009,"   (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7329)","IMSProtoc3",2,"Rel-9","C1-IETF","2009-05-29","2014-12-05",1,"CP-090491","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed","RFC 7329 (was draft-kaplan-insipid-session-id)",52,27,null,null,"2011-06-20","2014-09-03"]
[6557,531007,"   (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7044)","IMSProtoc3",2,"Rel-9","C1-IETF","2011-09-13","2014-03-07",1,"CP-090491","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#63 completed","RFC 7044 (was draft-ietf-sipcore-rfc4244bis)",53,27,null,null,"2011-09-13","2013-11-27"]
[6560,561004,"   (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7329)","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-09-12",1,"CP-090331","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 complete","RFC 7329 (was draft-kaplan-insipid-session-id)",56,29,null,null,"2012-04-20","2014-09-03"]
[6565,561009,"   Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2013-12-06",1,"CP-090331","-","Peter Dawes","peter.dawes@vodafone.com","CP#62 removed from Rel-8 to Rel-11. Not completed internet-draft","Rel-12 remains draft-dawes-sipping-debug",56,29,"SP-69",null,"2012-04-20","2013-11-27"]
[6568,450009,"PCC enhancements","PCC-Enh",1,"Rel-9","C3","2009-09-18","2009-12-04",1,"CP-090744","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#46 completed","29.212, 29.213, 29.215",45,23,null,null,"2009-03-05","2009-09-17"]
[6571,410023,"Rel-9 Improvements of the Radio Interface","RInImp9",1,"Rel-9","RP,GP","2008-09-12","2010-03-19",1,"-","-","-","-","RP#41 umbrella Feature created to host Rel-9 WIs","GERAN, UTRA, LTE",41,21,null,null,"2005-01-04","2010-03-16"]
[6575,420001,"      GERAN part of RF requirements for Multicarrier and Multi RAT BS","RInImp9-RFmulti-GERAN",3,"Rel-9","G1","2008-11-21","2009-11-20",1,"GP-081945","-","Ericsson","mats.y.samuelsson@ericsson.com","GP#44 Core spec completed. GP#40 WID approved","GERAN 45.005, 51.021",40,22,null,null,"2008-11-23","2009-11-20"]
[6578,430010,"   Performance requirement for LCR TDD with UE speeds up to 350 km/h","RInImp9-LCRTDD350",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-090258","RP-091035","CATT","Yuexia Song (songyuexia@catt.cn)","RP#46 completed","UTRA 25.102, 25.105, 25.142",43,22,null,null,"2009-02-27","2009-12-02"]
[6581,440007,"   Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe","RInImp-UEConTest-UMTSLTE800EU",2,"Rel-9","R5","2009-05-19","2010-09-17",1,"RP-090485","RP-100736","Ericsson","fredrik.sundstrom@ericsson.com","RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe","UTRA, LTE 34.108, 34.121-1, 34.121-2, 36.508, 36.521-1, 36.521-2, 36.521-3",44,23,null,null,"2009-05-18","2010-09-08"]
[6582,450017,"   Conformance Test Aspects – Extended UMTS/LTE 1500 MHz","UMTSLTE1500_UEConTest",2,"Rel-9","R5","2009-09-18","2010-06-04",1,"RP-091366","RP-100487","NTT DoCoMo","Nguyen Dung Dao (dao@nttdocomo.co.jp)","RP#48 completed","UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3",45,23,null,null,"2009-09-15","2010-06-01"]
[6586,430013,"Rel-9 RAN improvements","-",1,"Rel-9","RP","2009-03-06","2010-09-08",1,"-","-","-","-","RP#47 completed","UTRA",43,22,null,null,"2009-03-06","2010-09-08"]
[6590,430018,"   Transmit Antenna Array (TxAA) extension for non-MIMO UEs","RANimp-TxAA_nonMIMO",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090013","RP-091040","Nokia","Arto Lehti (arto.lehti@nokia.com)","RP#46 completed","25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433",43,22,null,null,"2009-03-06","2009-11-26"]
[6593,490019,"   Conformance Test Aspects – Combination of DC-HSDPA with MIMO","RANimp-DC_MIMO_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-101001","RP-110510","Ericsson","leif.mattisson@ericsson.com","UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO","UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-08","2011-05-18"]
[6596,420007,"LTE improvements","LTEimp",1,"Rel-9","R1,R2,R4,R5","2009-03-06","2011-06-03",1,"-","-","-","-","-","LTE",42,22,null,null,"2008-12-02","2009-01-21"]
[6600,420011,"Rel-9 Self-Organizing Networks (SON)","SON",1,"Rel-9","R3,R2","2009-03-06","2009-03-06",1,"RP-090162","RP-100038","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#47 completed","LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902",42,22,null,null,"2008-12-05","2010-03-10"]
[6603,38004,"   AGNSS Testing Procedures","AGNSSPTP-MStest",2,"Rel-9","G3new","2008-05-16","2011-05-20",1,"GP-092343","-","Thales","Michel.monnerat@thalesaleniaspace.com","GP#50 completed","51.010-1, new 51.010-7",38,20,null,null,"2008-05-19","2011-05-21"]
[6606,420004,"   Stage 3 for Voice services over Adaptive Multi-user channels on One Slot","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-03-04",1,"GP-081965","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#49 completed. GP#40 WID approved","24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058",40,22,null,null,"2008-11-23","2011-03-04"]
[6607,420005,"   VAMOS Radio Performance Requirements","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-05-20",1,"GP-081966","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#50 completed. GP#40 WID approved",45.005000000000003,40,22,null,null,"2008-11-23","2011-05-21"]
[6611,440102,"   GERAN part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre","CEBRO",2,"Rel-9","GP","2009-05-15","2010-03-05",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","GP#45 completed. GP#42 WID approved","new 48.049",42,23,null,null,"2009-05-18","2010-03-05"]
[6615,460002,"Test - (Small) Technical Enhancements and Improvements for Rel-9","TEI9_Test",1,"Rel-9","R5,G3new","2009-11-20","2010-12-24",1,"-","-","-","-","GP#44 created","-",44,24,null,null,"2009-11-25","2010-09-05"]
[6618,380071,"Deleted - Harmonization of Gq'/Rx for Common IMS","IMS_Comm_GqRx_Harm",1,"Rel-9","S2","2008-01-14","2009-03-12",1,"SP-070822","-","Alcatel-Lucent","geoffrey.cristallo@alcatel-lucent.be","SP#43 stopped. LS_out to TISPAN informs about stopping this activity ","23.822, 23.203",38,21,"SP-43","PCG-22","2007-10-02","2009-03-24"]
[6621,380086,"Deleted - Definition of 3GPP UICC services over the new high-speed interface","UICCHS",1,"Rel-9","C6","2010-03-19","2010-03-19",1,"CP-070837","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#47 work stopped/abandoned","31.xyz",38,21,"CP-47","PCG-24","2008-01-31","2009-11-25"]
[6625,390042,"   Deleted - SAE for generic support for non-3GPP accesses","SAES_Ph2",2,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[6628,0,"Release 9 Studies","-",1,"Rel-9","CP,RP,SP","2008-06-05","2008-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6629,400036,"Study on Service Specific Access Control in EPS","FS_SSAC",1,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080319","-","NTT DoCoMo","Shin-ichi Isobe (isobes@nttdocomo.co.jp)","SP#42 completed. Spin-off Feature UID_420020 (SSAC)",22.986000000000001,40,21,null,null,"2007-12-13","2010-08-31"]
[6632,320031,"Study on Service Continuity for Emergency Voice Calls","FS_VCCEm",1,"Rel-9","S2","2006-06-08","2009-03-12",1,"SP-080555","-","Nortel","Ricky Kaura (rkaura@nortel.com)","SP#43 completed",23.826000000000001,32,17,null,null,"2006-07-19","2009-02-24"]
[6636,390017,"Study on Self-healing of Self-Organizing Networks (SON)","FS_OAM-SON-SH",1,"Rel-9","S5","2008-02-22","2009-09-24",1,"SP-080076","-","ZTE","zhu.weihong@zte.com.cn","SP#45 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036)",32.823,39,21,null,null,"2007-05-28","2009-09-07"]
[6640,410016,"Study on 1.28 Mcps TDD Home NodeB","FS_RAN-HNBLCRTDD",1,"Rel-9","R4","2008-02-20","2009-12-04",1,"RP-080767","RP-091081","TD Tech","Li Rong (lirong@td-tech.com)","RP#46 completed",25.866,41,21,null,null,"2007-12-17","2009-12-03"]
[6643,430027,"Study on Enhanced Interference Management for HNBs","FS_eInterfMgmt_HNB",1,"Rel-9","R4","2009-03-06","2009-05-29",1,"RP-090361","RP-090429","Qualcomm","Farhad Meshkati (fmeshkat@qualcomm.com)","RP#44 completed. Linked to UID_420008 LTE FDD Home eNodeB RF Requirements. Spin-off RAN3 UID_440015 Study on Enhanced Interference Management Mechanisms for HNBs",25.966999999999999,43,22,null,null,"2009-03-10","2009-06-25"]
[6646,0,"--- RELEASE 8 ---","-",1,"Rel-8","CP,GP,RP,SP","2006-09-19","2010-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[6650,350024,"      Stage 2 for High level functions ","SAES-SA-HLF",3,"Rel-8","S2","2007-01-02","2008-06-02",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed","New 23.402",35,18,null,null,"2007-03-29","2010-07-28"]
[6653,340054,"      Stage 3 SAE impact on existing capabilities","SAES",3,"Rel-8","C3","2007-02-05","2008-12-05",1,"CP-080772","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#42 completed",29.061,34,18,null,null,"2006-07-19","2010-07-28"]
[6657,340022,"      Stage 3 PCC within SAE","SAES-St3-PCC",3,"Rel-8","C3","2007-02-05","2009-05-29",1,"CP-080576","-","Ericsson ","j.javier.pastor@ericsson.com","CP#44 completed","29.212, 29.213, 29.214, New 29.215",34,18,null,null,"2006-07-19","2010-07-28"]
[6658,340028,"      Stage 3 for SAE / LTE identities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",23.003,34,18,null,null,"2006-07-19","2010-07-28"]
[6661,340060,"      CT4 Stage 3 for protocol between EPCs","SAES-LTE",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[6665,350043,"      SAES-SA-FP_LTE with PMIP variant","SAES-SA-FP_LTE-IETF",3,"Rel-8","S2,C4","2007-01-02","2009-03-06",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","CP#43 completed","-",35,18,null,null,"2007-04-26","2010-07-28"]
[6668,410004,"         Mobile IPv4 (MIPv4) based Mobility protocols","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Motorola","Lewis Milton","CP#42 completed",29.279,41,21,null,null,"2006-07-19","2010-07-28"]
[6671,340053,"      Stage 3 for security aspects of LTE Access","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008, 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[6675,370008,"      Stage 2 for Interoperation between LTE and 2G/3G","EPSto2_3G",3,"Rel-8","S2","2007-02-05","2008-09-18",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#41 completed","23.401, 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[6678,390008,"      Stage 2 GPRS for EPC (23.060, etc.)","SAES-SA-FP_3GPP",3,"Rel-8","S2","2008-01-14","2008-09-18",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#41 completed",23.06,39,21,null,null,"2007-09-19","2010-07-28"]
[6680,380032,"      Stage 3 for EPC to UTRAN","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274, 29.275, 29.281",38,21,null,null,"2006-07-19","2010-07-28"]
[6683,360023,"      Stage 3 for Inter-system mobility between E-UTRAN and CDMA2000","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.301, 24.302",36,19,null,null,"2007-09-12","2010-07-28"]
[6686,350044,"      Stage 2 for Host-based Mobility aspects","SAES-SA-FP_n3GPP-HBMob",3,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed",23.402000000000001,35,18,null,null,"2007-04-26","2010-07-28"]
[6690,521012,"      (IETF) Stage 3 for Mobility management based on DSMIPv6 (RFC6275)","SAES-SA-FP_n3GPP",3,"Rel-8","C1-IETF","2007-02-05","2011-07-29",1,"CP-080493","-","-","-","SP#53/IETF#81 completed","RFC 6275 (was draft-ietf-mext-rfc3775bis)",52,27,null,null,"2011-06-20","2011-08-31"]
[6693,360019,"      Stage 2 for Optimized Dual-Radio Handover with WiMAX","SAES-SA-FP_n3GPP-OptWIMAX",3,"Rel-8","S2","2007-06-25","2008-06-05",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed",23.402000000000001,36,19,null,null,"2007-04-26","2010-07-28"]
[6697,360021,"      Stage 3 for Access to the EPC via non-3GPP access networks","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.302, 24.312",36,19,null,null,"2007-09-12","2010-07-28"]
[6699,340057,"      Stage 3 for Interfaces EPC - non-3GPP IP access ","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.273, 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[6704,350030,"   Single Radio Voice Call Continuity for 3GPP (SRVCC)","SAES-SRVCC",2,"Rel-8","S2,C1,C4","2007-01-02","2009-03-06",1,"SP-070949","-","Nokia Siemens Networks","curt.c.wong@nokia.com","CP#43 completed. SP#38 WID approved (extract from SAE WID SP-070817).","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6705,350130,"      Stage 2 for 2G/3G SRVCC","SAES-SRVCC",3,"Rel-8","S2","2007-01-02","2008-09-18",1,"SP-070949","-","Nokia Siemens Networks","curt.c.wong@nokia.com","SP#41 completed. SP#38 WID approved","New 23.216",35,18,null,null,"2007-03-29","2010-07-28"]
[6708,360020,"   Voice Call Continuity for CDMA2000 1X","SAES-VCC_1X",2,"Rel-8","S2","2007-06-25","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","-",36,19,null,null,"2007-03-29","2010-07-28"]
[6711,400001,"      Stage 2 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","SP#40 completed","New (23.272, 23.401)",40,21,null,null,"2007-03-29","2010-07-28"]
[6715,390010,"   EPC Data Definitions","EPC-OAM",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"-","-","-","-","SP#43 completed","-",39,21,null,null,"2005-06-17","2010-07-28"]
[6718,380038,"   EPC Charging","EPC-CH",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070736","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240, 32.296, 32.251, 32.252, 32.298, 32.299",38,21,null,null,"2005-06-17","2010-07-28"]
[6720,410007,"   InterWorking Function (IWF) between MAP based and Diameter based interfaces","SAES-MAP2Diam",2,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080644","-","Huawei","liming49985@huawei.com","CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam)","New 29.305",41,21,null,null,"2007-11-19","2010-07-28"]
[{"$f":"A6726+1","v":6726},390019,"   Issues for CT3 TR 29.804","SAES",2,"Rel-8","C3","2007-02-05","2008-09-12",1,"CP-080068","-","Ericsson ","j.javier.pastor@ericsson.com","CP#41 completed",29.803999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[6729,350032,"   Deleted (covered by 380064): SAE aspects of Emergency Calls","SAES-SA-EmCall",2,"Rel-8","S2","2008-03-03","2008-03-03",1,"-","-","Nokia Siemens Networks","-","SP#37 stopped","-",35,18,"SP-37",null,"2007-03-29","2009-03-24"]
[6730,340019,"   Deleted - CT aspects of SAES","SAES-St3",2,"Rel-8","C3,C1,C4","2007-09-04","2008-03-14",1,"CP-060674","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6733,350020,"      Deleted - CT3 aspects of SAES","SAES",3,"Rel-8","C3","2007-09-04","2007-09-04",1,"CP-060675","-","-","-","SP#37 stopped","-",35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[6737,340037,"   Deleted - Architecture enhancements for non-3GPP accesses","SAES-non_3GPP",2,"Rel-8","S2","2007-09-04","2007-09-04",1,"SP-060926","-","Motorola","Irfan.Ali@motorola.com","SP#34 stopped. Replaced by UID_350027 and its children",23.402000000000001,34,18,"SP-34",null,"2006-06-23","2009-03-24"]
[6740,450022,"Conformance Test Aspects – Mobility management based on DSMIPv6 (Dual-Stack Mobile IPv6)","DSMIPv6_UEConTest",1,"Rel-8","R5","2009-09-18","2010-09-17",1,"RP-090754","RP-100738","Qualcomm","Lena Chaponniere (lchaponn@qualcomm.com)","RP#49 completed. Testing for CT1's UID_360022 (24.303) under Rel-8 Feature SAES","36.508, 36.523-1, 36.523-2, 36.523-3",45,23,null,null,"2009-09-15","2010-09-09"]
[6745,400005,"      CT1 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-091046","-","Ericsson","Sean Schneyer","CP#46 completed","24.229, new (24.292, 24.286)",40,21,null,null,"2008-03-03","2009-12-07"]
[6748,521016,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7195)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2014-06-13",1,"CP-091046","-","Andrew Allen","-","CP#64 complete","RFC 7195 (was draft-ietf-mmusic-sdp-cs)",52,27,null,null,"2011-06-20","2014-06-06"]
[6751,400007,"      CT4 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-091046","-","Ericsson","Sean Schneyer","CP#42 completed","23.003, 29.232, 23.018, 29.002",40,21,null,null,"2008-03-03","2009-12-07"]
[6754,370059,"IMS Multimedia Telephony and Supplementary Services","IMSTSS",1,"Rel-8","S1,S5,C1,C3,C4,IETF","2007-05-02","2014-12-09",1,"-","-","-","-","SP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[6755,370060,"   General aspects of IMS Sup Services","IMSSS-Gal",2,"Rel-8","S1,C1,C3,C4","2007-09-03","2009-03-06",1,"SP-070691","-","Ericsson","Susana Sabater","CP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[6758,380002,"      Documentation of TISPAN R1 and R2 in CT3","REDOC_TIS-C3",3,"Rel-8","C3","2007-11-28","2009-03-06",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#43 completed","29.162, 29.163, 29.658",38,21,null,null,"2007-11-28","2009-12-07"]
[6762,380041,"      Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging","MMTel-CH",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-080848","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","CP#43 completed","32.275, 32.298/299",38,21,null,null,"2005-06-17","2009-02-23"]
[6766,521019,"      (IETF) Stage 3 CCBS_CCNR [RFC 6910 (was draft-ietf-bliss-call-completion)]","CCBS_CCNR",3,"Rel-8","C1-IETF,C3-IETF","2007-05-02","2013-06-14",1,"CP-080215","-","Roland Jesske","-","CP#60 completed","RFC 6910 (was draft-ietf-bliss-call-completion)",52,27,null,null,"2011-06-20","2013-06-10"]
[6769,390015,"      Stage 3 FA","FA",3,"Rel-8","C1","2008-01-30","2009-03-06",1,"CP-080219","-","Nortel","milanpa@nortel.com","CP#43 completed","24.239, 24.173",39,21,null,null,"2008-03-03","2009-02-20"]
[6773,380011,"      CT3 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C3","2007-11-30","2008-12-04",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#42 completed",29.163,38,21,null,null,"2007-11-14","2008-11-21"]
[6776,380042,"      Advice of Charge (AoC) support in IMS Charging","CH8_IMS",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070739","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240, 32.260, 32.296, 32.298, 32.299, new 32.280",38,21,null,null,"2005-06-17","2009-02-23"]
[6779,390051,"   Stage 2 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","23.002, 23.141, 23.203, 23.167, 23.228",39,21,null,null,"2008-03-03","2015-03-24"]
[6780,390052,"   Security CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#42 completed [issues addressed under UID_370078 (IMS-Sec)]. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","33.141, 33.203, 33.210",39,21,null,null,"2008-03-03","2015-03-24"]
[6783,390026,"      Stage 3 CIMS_3GPP2 (CT3)","REDOC_3GPP2",3,"Rel-8","C3","2008-03-07","2008-12-05",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","29.163, 29.212, 29.213, 29.214",39,21,null,null,"2008-03-03","2009-03-26"]
[6787,350009,"      Architecture aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","S2","2007-02-05","2007-12-06",1,"SP-070105","-","Cablelabs","Bernie McKibben (b.mckibben@cablelabs.com)","SP#38 completed",23.228000000000002,35,18,null,null,"2007-03-29","2008-05-27"]
[6791,350013,"      CT1,CT3 aspects of PktCbl-Interwork","PktCbl-Intw",3,"Rel-8","C1,C3","2007-03-26","2008-03-14",1,"CP-070575","-","Cablelabs","D.Hancock@CableLabs.com","CP#39 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-03-03"]
[6794,350006,"      CT1 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-05-27"]
[6798,390049,"   SA1 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S1","2008-03-12","2008-06-05",1,"SP-080095","-","Telecom Italia","-","SP#40 completed","-",39,21,null,null,"2007-06-22","2008-05-19"]
[6801,531002,"   (IETF) CT1 aspects of IMS_Corp (RFC 7316)","IMS_Corp",2,"Rel-8","C1-IETF","2011-06-29","2014-09-12",1,"CP-080220","-","Keith Drage","Keith Drage (drage@alcatel-lucent.com)","CP#65 completed","RFC 7316 (was draft-vanelburg-dispatch-private-network-ind)",53,27,null,null,"2011-07-29","2014-09-03"]
[6802,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228, 29.229, 23.003, 23.008, 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[6805,521021,"   Deleted - (IETF) Maintenance of TISPAN R2 (avasarala-dispatch-comm-div-notification)","MAINT_R2_IETF",2,"Rel-8","C1-IETF","2007-11-09","2014-06-13",1,"CP-080229","-","Andrew Allen","-","CP#64 Draft removed from 3GPP documentation","draft-avasarala-dispatch-comm-div-notification",52,27,"SP-69",null,"2011-06-20","2014-06-06"]
[6808,390056,"IMS Service Continuity","IMS-Cont",1,"Rel-8","S2,S1,C1","2008-03-12","2009-05-29",1,"SP-080092","-","LG Electronics","JaeSeung SONG (anthonys@lge.com)","CP#44 completed","-",39,21,null,null,"2007-10-02","2010-07-29"]
[6813,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203, 33.141, 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[6816,380012,"   CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication","NBA",2,"Rel-8","C1","2007-11-14","2009-03-06",1,"CP-070781","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed",24.228999999999999,39,21,null,null,"2007-11-19","2009-02-20"]
[6819,34146,"   SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",2,"Rel-8","S4,S3","2008-03-12","2008-03-12",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#43 completed","26.234, 26.346, 33.246, New 26.237",34,18,null,null,"2008-03-18","2011-06-30"]
[6823,7014,"   Stage 3 of MW-IMS","MIW-IMS-St3C3",2,"Rel-8","C3","2005-09-23","2007-11-30",1,"CP-070096","-","Vodafone","nico.gabriele@vodafone.com","Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021","29.863, 29.163",70,36,null,null,"2006-02-16","2008-08-05"]
[6826,360029,"IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",1,"Rel-8","C1,IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","-",36,19,null,null,"2007-09-05","2009-02-20"]
[6827,360129,"   CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",2,"Rel-8","C1","2007-06-22","2009-03-06",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","23.218, 24.229, 24.930",36,19,null,null,"2007-09-05","2009-02-20"]
[6830,521025,"   (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[6833,521026,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui)","RFC 7433",52,27,null,null,"2011-06-20","2015-03-10"]
[6838,380020,"   Stage 3 Overlap (CT3)","Overlap",2,"Rel-8","C3","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed",29.163,38,21,null,null,"2007-11-13","2008-11-25"]
[6841,380135,"   AS/MRFC Stage 2","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed",23.218,38,21,null,null,"2007-11-14","2012-01-10"]
[6844,400012,"IMS Restoration Procedures","IMS_RP",1,"Rel-8","C4,C1","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 ","-",40,21,null,null,"2007-03-29","2010-07-30"]
[6848,340030,"I-WLAN Network Selection Principle (NSP)","IWLANNSP",1,"Rel-8","S1,C1,C6","2007-06-14","2009-03-06",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","CP#43 completed","-",34,18,null,null,"2005-11-04","2009-02-25"]
[6851,390125,"   CT6 part of Stage 3 for I-WLAN NSP","IWLANNSP",2,"Rel-8","C6","2008-03-07","2008-12-11",1,"CP-080217","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","CP#42 completed","31.102, 31.111",39,21,null,null,"2008-03-07","2009-02-25"]
[6852,370049,"Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",1,"Rel-8","S2,C1","2007-09-14","2009-03-06",1,"SP-070701","-","Orange","xiaobao.chen@orange-ftgroup.com","CP#43 completed","-",37,19,null,null,"2005-11-04","2008-05-27"]
[6858,370019,"   VGCS/VBS and GPRS Interactions","EVA",2,"Rel-8","S1","2007-09-03","2008-03-21",1,"SP-070653","-","Huawei","Ling Liu","SP#39 completed","42.068, 42.069",37,19,null,null,"2007-10-02","2008-05-16"]
[6859,320019,"   CT1 aspects of EVA","EVA",2,"Rel-8","C1","2006-06-02","2009-09-18",1,"CP-060260","-","Nortel","milanpa@nortel.com","CP#45 completed","43.068, 44.068",32,17,null,null,"2006-06-21","2009-09-09"]
[6863,7012,"   Stage 1 for PNM","PNM",2,"Rel-8","S1","2005-07-11","2006-07-31",1,"SP-080327","-","Vodafone","armin.toepfer@vodafone.com","SP#31 completed",22.259,null,null,null,null,"2006-02-16","2008-06-04"]
[6866,350001,"      CT1 aspects of Stage 3 PNM","PNM",3,"Rel-8","C1","2007-03-26","2009-03-06",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#43 completed","24.259, 24.229",null,null,null,null,"2007-03-29","2009-02-20"]
[6870,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[6873,34042,"eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution","eCall_Phase2",1,"Rel-8","S4","2007-12-06","2009-09-24",1,"SP-070756","-","Airbiquity","lhong@airbiquity.com & rrobinson@airbiquity.com","SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData)","26.267, 26.268, 26.269, 26.967, 26.969",null,null,null,null,"2007-12-09","2010-08-02"]
[6876,380060,"IP Interconnection of Services ","IPinterc",1,"Rel-8","S1,S2,S5,C3","2006-08-16","2009-03-06",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#43 completed","-",38,21,null,null,"2007-12-13","2010-08-02"]
[6879,360024,"      Stage 2 for IMS_NNI","IMS_NNI",3,"Rel-8","S2","2007-06-22","2007-12-06",1,"SP-080554","-","Telecom Italia","Mario Madella (mario.madella@telecomitalia.it)","SP#38 completed","23.002, 23.228",null,null,null,null,"2007-06-22","2010-08-02"]
[6881,330011,"      Charging harmonization for NGN between 3GPP and ATIS-TMOC","FBI2-TISP2-CH",3,"Rel-8","S5","2006-09-28","2006-12-07",1,"SP-060545","-","Amdocs","yishai.brown@amdocs.com ","SP#34 completed",32.296999999999997,null,null,null,null,"2006-10-09","2008-03-03"]
[6884,360025,"Support of (G)MSC-S – (G)MSC-S Nc Interface based on the SIP-I protocol","SIP_Nc",1,"Rel-8","C4,C3","2007-09-14","2009-03-06",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#43 completed. Stage 1 in Feature UID_380060 (IPinterc). CP#40 updated WID CP-070517=>CP-080282","-",null,null,null,null,"2007-09-05","2008-05-28"]
[6888,360028,"   Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks","SIP_Nc-St3C3",2,"Rel-8","C3","2007-09-14","2009-03-06",1,"CP-080282","-","Nokia Siemens Networks","Thomas.Belling@nsn.com","CP#43 completed. CP#42 target 12/08=>03/09","29.235, 23.172, 23.202, 29.007, 29.163, 29.414",null,null,null,null,"2007-09-05","2009-02-19"]
[6891,380056,"   SA2 aspects of ETWS","ETWS",2,"Rel-8","S2","2008-01-14","2008-09-18",1,"SP-070815","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#41 completed","23.828, 23.401",38,21,null,null,"2007-12-13","2008-09-14"]
[6895,440011,"Conformance Test Aspects – UMTS Earthquake and Tsunami Warning System (ETWS) FDD","ETWS_UMTS_UEConTestFDD",1,"Rel-8","R5","2009-05-29","2010-03-12",1,"RP-090467","RP-100068","NTT DoCoMo","Makoto Ito (itohm@nttdocomo.co.jp)","RP#47 completed. Testing for Rel-8 ETWS UID_370051","34.108, 34.123-1, 34.123-2",44,23,null,null,"2009-05-28","2010-03-08"]
[6898,380259,"   CT6 aspects of ICE","ICE",2,"Rel-8","C6","2007-03-13","2009-03-06",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","CP#43 completed (ICE Graphics not in Rel-8 / not explicitly in SA1 WID either)",31.102,38,21,null,null,"2007-12-13","2010-09-06"]
[6900,340029,"Customized Alerting Tone (CAT) service","CAT",1,"Rel-8","S1,C1,C3,C4","2006-12-06","2009-09-18",1,"SP-070122","-","China Mobile","fenglingjuan@chinamobile.com","CP#45 completed","-",34,null,null,null,"2005-11-04","2010-08-02"]
[6903,390014,"   IMS CAT Supplementary Service","CAT-SS",2,"Rel-8","C1,C3","2008-03-12","2009-09-18",1,"CP-080496","-","Nortel","milanpa@nortel.com","-","-",39,21,null,null,"2008-03-03","2008-11-21"]
[6906,410010,"   CAT Service in 3GPP CS domain","CAT-3G_CS",2,"Rel-8","C4,C1","2008-09-12","2009-03-06",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","-","23.205, 23.231, 29.002",41,21,null,null,"2008-09-11","2012-01-11"]
[6910,350047,"   Stage 1 for MESSIW","MESSIW",2,"Rel-8","S1","2007-03-26","2007-03-26",1,"SP-070816","-","Huawei","ling.liu@huawei.com","SP#35 completed","22.105, 22.340",null,null,null,null,"2005-11-04","2008-03-22"]
[6913,400017,"   CT1 part of Stage 3 for MESSIW","MESSIW",2,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080773","-","Huawei","xupeili@huawei.com","CP#42 completed",24.228999999999999,40,21,null,null,"2006-07-19","2010-08-02"]
[6916,340012,"   CT1 part of Stage 3 for PRIOR","PRIOR_EMR",2,"Rel-8","C1","2006-12-01","2009-09-18",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#45 completed",24.228999999999999,34,null,null,null,"2006-12-18","2009-09-09"]
[6920,360004,"   OSA Stage 1 - Service Requirements","OSA8",2,"Rel-8","S1","2007-08-23","2008-03-12",1,"-","-","Orange, AePONA","Song Dong","SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A).",22.126999999999999,null,null,null,null,"2005-03-22","2010-08-30"]
[6921,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[6927,370016,"      Deleted - Identify communication format used by a particular application","-",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Ericsson","catherine.mulligan@ericsson.com","CP#40: Work moved to OMA","existing 29.199-xy",37,21,"CP-40","PCG-21","2007-09-13","2009-03-24"]
[6928,380047,"      Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6931,380050,"      Deleted - Subscriber event notification (22.127 CR 0087 S1-071836)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[6935,380054,"      Presence alignment with OMA and IETF (22.127 CR 0092 S1-071764)","OSA8-IMS",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-14/13",38,21,null,null,"2007-12-05","2009-01-19"]
[6938,390068,"      Mobility Emergency Location","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-06",39,21,null,null,"2008-03-26","2009-01-19"]
[6941,360032,"Paging Permission with Access Control (PPACR)","PPACR",1,"Rel-8","S1,C1","2007-06-12","2008-12-05",1,"SP-070501","-","NTT DoCoMo","Morita Takashi","CP#42 completed. Triggered by Study UID_330016 (PPAC).","-",null,null,null,null,"2007-10-16","2008-12-10"]
[6946,380070,"   Stage 1 for CHRGMPH","CHRGMPH-s1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-03-20"]
[6949,420019,"   Support of Closed Subscriber Group (CSG)","-",2,"Rel-8","C4","2008-12-05","2009-03-06",1,"-","-","CT#42","Hannu Hietalahti","CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG","29.002, 29.272, 23.008, 23.003",42,22,null,null,"2008-12-04","2009-02-23"]
[6952,390033,"UTRA HNB","HNB",1,"Rel-8","RP,S5","2008-03-07","2009-06-04",1,"-","-","-","-","SP#44 completed","-",39,21,null,null,"2005-01-04","2008-06-03"]
[6953,400053,"   Support of UTRA HNB","HNB-supp",2,"Rel-8","R2","2008-05-30","2009-03-06",1,"RP-080752","RP-090040","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#43 completed","25.304, 25.306, 25.331, new 25.367",40,21,null,null,"2008-06-03","2009-02-27"]
[6956,420037,"   3G Home NodeB OAM&P Type 1 Management Interface","HNB-3G_OAM",2,"Rel-8","S5","2008-12-11","2009-06-04",1,"SP-080708","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Complements work in BroadBand Forum","new (32.581, 32.582, 32.583, 32.584)",42,22,null,null,"2008-12-03","2009-05-18"]
[6960,390046,"Generic Bootstrapping Architecture Push Function","GBAPush",1,"Rel-8","S3,C1,C4","2008-03-12","2009-03-06",1,"SP-080133","-","Ericsson","Rolf Blom","CP#43 completed","-",39,21,null,null,"2008-03-22","2009-02-20"]
[6963,390346,"   CT4 part of GBAPush ","GBAPush",2,"Rel-8","C4","2008-03-12","2009-03-06",1,"CP-090112","-","Ericsson","Rolf Blom","CP#43 completed",29.109000000000002,39,21,null,null,"2008-03-22","2009-03-04"]
[6967,34041,"   MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size","MTSI_eMHI-DRASIS",2,"Rel-8","S4","2007-12-06","2009-03-12",1,"SP-080246","-","Qualcomm, Samsung","nleung@qualcomm.com & kyunghun.jung@samsung.com","SP#43 completed",26.114000000000001,null,null,null,null,"2007-12-09","2010-08-02"]
[6971,340063,"Rel-8 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM8",1,"Rel-8","S5,C1,C4,IETF","2007-06-07","2012-12-07",1,"-","-","-","-","OAM8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI",30.818000000000001,34,null,null,null,"2007-03-08","2010-08-02"]
[6974,35053,"      Advanced Alarming on Itf-N","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070492","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#40 completed","32.121, 32.122, 32.123",null,null,null,null,"2005-06-17","2008-06-04"]
[6975,35056,"      CN CS Bearer Transport Network (BTN) relative NRM","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070300","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#40 completed","32.632, 32.633, 32.635",null,null,null,null,"2005-06-17","2008-04-28"]
[6978,450052,"      Create missing specifications for IRP XML definitions","OAM8-NIM",3,"Rel-8","S5","2009-09-24","2009-12-04",1,"SP-090553","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x)","new (32.125, 32.355, 32.505, 32.535), 32.150, 32.153, 32.335 ",45,23,null,null,"2009-09-11","2009-12-01"]
[6981,35061,"      IP bearer network Performance measurement definitions","OAM8-PM",3,"Rel-8","S5","2007-06-07","2008-12-11",1,"SP-070301","-","China Mobile","lilianyuan@chinamobile.com","SP#42 completed","32.321, 32.322, 32.323, 32.325",null,null,null,null,"2005-06-17","2010-08-02"]
[6985,11067,"      CT1 part of Service Level Tracing in IMS","OAM8-Trace",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080315","-","Vodafone","peter.dawes@vodafone.com","CP#42 completed","24.323, 24.229",null,null,null,null,"2008-03-17","2010-08-02"]
[6988,400022,"      CT4 part of Service Level Tracing in IMS","OAM8-Trace",3,"Rel-8","C4","2008-03-07","2008-12-05",1,"CP-080315","-","Vodafone","peter.dawes@vodafone.com","CP#42 completed","29.228, 29.229",40,21,null,null,"2008-03-17","2010-08-02"]
[6992,350038,"   Online charging correlation","CH8",2,"Rel-8","S5","2006-03-16","2007-12-14",1,"SP-070077","-","Orange","Chahine, Rony ","SP#38 completed",32.295999999999999,null,null,null,null,"2008-03-17","2008-03-17"]
[6996,380024,"Conferencing enhancements for Mp interface","eMp",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed","-",null,21,null,null,"2007-11-19","2010-08-02"]
[6999,320014,"Contact Manager for 3GPP UICC applications","eUPHBOOK",1,"Rel-8","C6","2006-06-22","2008-12-05",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#42 completed. CP#40: WID updated CP-070622=>CP-080382. aka Enhanced USIM phonebook","-",null,null,null,null,"2006-01-24","2009-03-24"]
[7000,320015,"   Requirements for Contact Manager","eUPHBOOK-St1",2,"Rel-8","C6","2006-06-22","2007-12-21",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#38 completed",21.111000000000001,null,null,null,null,"2006-01-24","2008-05-29"]
[7003,320016,"   Deleted - Implementation of eUPHBOOK","eUPHBOOK-St23",2,"Rel-8","C6","2007-06-21","2007-06-21",1,"CP-060355","-","Giesecke & Devrient","Claus Dietze","SP#33 stopped",31.102,null,null,"SP-33",null,"2006-01-24","2009-03-24"]
[7006,330019,"   LTE – Radio Interface Layer 2 and 3 Protocol Aspect","LTE-L23",2,"Rel-8","R2","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Nokia Siemens Networks","benoist.sebire@nokia.com","RP#42 completed","36.302, 36.304, 36.306, 36.314, 36.321, 36.322, 36.323, 36.331, 25.302, 25.304, 25.331",null,null,null,null,"2006-03-21","2009-12-18"]
[7009,370046,"   LTE – FDD repeaters","LTE-Repeaters",2,"Rel-8","R4","2007-09-14","2009-03-06",1,"RP-070749","RP-090037","Powerwave Technologies, Andrew Wireless","ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com","RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report)","36.106, 36.143, 25.113",37,null,null,null,"2007-10-01","2010-03-16"]
[7014,390003,"      Key Performance Indicators (KPIs) for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080063","-","Ericsson ","ulf.hubinette@ericsson.com ","SP#43 completed","new (32.450, 32.451)",39,21,null,null,"2005-06-17","2009-02-23"]
[7017,390005,"      Self-Establishment of eNBs, including automated Software Management","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080849","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#42 completed","new (32.501, 32.502, 32.503, 32.531, 32.532, 32.533)",39,21,null,null,"2005-06-17","2010-03-22"]
[7021,25042,"   LTE – Terminal Radio Transmission and Reception Conformance Test Specifications","LTE-UEConTest_RF",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080601","RP-091059","Agilent","andrea_leonardi@agilent.com","RP#46 completed. RP#50 TR 36.903 v100 for Approval","36.521-1, 36.521-2, 36.521-3, new 36.903",null,null,null,null,"2009-06-02","2010-12-10"]
[7024,350035,"   UMTS 700 MHz FDD","RInImp8-UMTS700",2,"Rel-8","R4","2007-03-05","2008-05-30",1,"RP-070127","RP-080260","Nokia","Tuomo Saynajakangas","RP#40 completed","25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,null,null,"2004-09-27","2010-03-16"]
[7025,410018,"   UMTS 1880 MHz TDD","RInImp9-UMTS1880TDD",2,"Rel-8","R4","2008-09-12","2009-03-06",1,"RP-080757","RP-090044","CATT","Yuexia Song (songyuexia@catt.cn)","RP#43 completed","25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307",41,21,null,null,"2008-09-11","2009-03-10"]
[7028,370032,"   CS Voice Service over HSPA","RInImp8-CsHspa",2,"Rel-8","R2","2007-07-19","2008-03-07",1,"RP-070765","RP-080042","Nokia Siemens Networks","woonhee.hwang@nsn.com","RP#39 completed","25.323, 25.331, 25.322",37,null,null,null,"2007-10-02","2010-08-02"]
[7034,370035,"Rel-8 RAN improvements","-",1,"Rel-8","RP","2007-06-04","2009-05-29",1,"-","-","-","-","-","-",null,null,null,null,"2007-10-01","2010-02-09"]
[7036,370036,"   Improved L2 for uplink","RANimp-UplinkL2dataRates",2,"Rel-8","R2","2007-09-14","2008-05-30",1,"RP-070717","RP-080265","Ericsson","Janne.Peisa@ericsson.com","RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD","25.319, 25.301, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, 25.427",37,null,null,null,"2007-10-02","2010-08-03"]
[7039,370039,"   Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure","RANimp-SrnsReloc",2,"Rel-8","R3","2007-09-14","2008-09-12",1,"RP-070759","RP-080521","Nokia Siemens Networks","masatoshi.nakamata@nsn.com","RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution","25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.214, 25.133",37,null,null,null,"2007-10-01","2010-08-03"]
[7043,390028,"   Continuous Connectivity for packet data users for 1.28 Mcps TDD","RANimp-LCRCPC",2,"Rel-8","R1","2008-03-07","2009-05-29",1,"RP-080085","RP-090394","TD Tech","chenying@td-tech.com","RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.929, 25.308, 25.319",39,21,null,null,"2008-03-17","2010-08-03"]
[{"$f":"A7046+1","v":7046},400050,"   MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","RANimp-MIMOLCR",2,"Rel-8","R1,R4","2008-01-24","2009-05-29",1,"RP-080485","RP-090313","CATT","wangke@datangmobile.cn","RP#43 completed","25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.102, 25.105, 25.142",40,21,null,null,"2008-03-17","2010-08-03"]
[7049,410020,"   Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-UEConTest_64QamMimoHsdpa",2,"Rel-8","R5","2008-09-12","2009-12-04",1,"RP-080759","RP-091058","Ericsson","leif.mattisson@ericsson.com","RP#46 completed. Testing for UID_360013","34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2",41,21,null,null,"2008-06-03","2010-08-03"]
[7050,400056,"   Conformance Test Aspects – Improved L2 for uplink","RANimp-UEConTest_UplinkL2dataRates",2,"Rel-8","R5","2008-05-30","2009-09-18",1,"RP-080606","RP-090712","Ericsson","leif.mattisson@ericsson.com","RP#45 completed. Testing for UID_370036","34.108, 34.123-1, 34.123-2, 34.123-3",40,21,null,null,"2008-06-03","2010-08-03"]
[7055,430028,"   Conformance Test Aspects – Receiver Type3i","RANimp-UEConTest_ReceiverType3i",2,"Rel-8","R5","2009-03-06","2009-12-04",1,"RP-090010","RP-091066","Qualcomm","Ashok Kumar Narayanaswamy (anarayan@qualcomm.com)","RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD","34.108, 34.121-1, 34.121-2",43,22,null,null,"2009-03-10","2010-08-03"]
[7057,450024,"   Conformance Test Aspects – Continuous Connectivity for packet data users for 1.28 Mcps TDD","RANimp-UEConTest_CPCLCRTDD",2,"Rel-8","R5","2009-09-18","2010-09-17",1,"RP-090751","RP-100739","ZTE","huang.he4@zte.com.cn","RP#49 completed. Testing for UID_390028","34.108, 34.123-1, 34.123-2, 34.123-3",45,23,null,null,"2009-09-15","2010-09-09"]
[7061,440008,"Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast","MBSFN_IMB_UEConTest",1,"Rel-8","R5","2009-05-30","2010-03-19",1,"RP-090583","RP-100070","IPwireless","Phil Young (pyoung@ipwireless.com)","RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",44,23,null,null,"2009-05-21","2010-03-16"]
[7064,52583,"   G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G2","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","44.018, 44.060, 48.008, 48.018",null,null,null,null,"2006-09-13","2010-09-09"]
[7068,50587,"GAN Enhancements","GANENH",1,"Rel-8","GP","2007-05-15","2009-09-04",1,"GP-071484","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed. GP#43 completed Testing","-",null,null,null,null,"2007-09-06","2009-09-28"]
[7071,50591,"AoIP (A-interface over IP)","AoIP",1,"Rel-8","GP,S4,C4,C1,C3","2000-01-03","2008-12-11",1,"GP-081361","-","China Mobile, Ericsson","wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com","GP#40/TSG#42 completed . Triggered by TR 43.903 Study on A-interface over IP (AINTIP) UID_50589. ","-",null,21,null,null,"2008-02-26","2008-12-03"]
[7074,400024,"   Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",2,"Rel-8","C4,C1,C3","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722","-",40,21,null,null,"2007-09-19","2012-01-11"]
[7075,400324,"      CT4 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722","23.205, 23.153, 23.231, 29.232",40,21,null,null,"2007-09-19","2012-01-11"]
[7080,420038,"   Stage 1 for ANSS for LCS","ANSS",2,"Rel-8","S1","2008-12-11","2008-12-11",1,"-","-","-","-","SP#42 completed by 22.071 CR0077",22.071000000000002,42,22,null,null,"2008-12-08","2010-02-09"]
[7083,51149,"Conformance testing for the Latency Reductions feature","CTLATRED",1,"Rel-8","G1,G3new","2008-02-22","2010-03-05",1,"GP-080367","-","Ericsson","mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com","GP#45 completed","-",null,21,null,null,"2008-02-26","2010-03-05"]
[7086,53091,"MS conformance testing of changes introduced by WI \"Support of Packet-switched Handover for GERAN A/Gb mode\"","PSHCT-MStest",1,"Rel-8","G3new","2008-02-22","2008-11-21",1,"GP-080411","-","Rohde & Schwarz","Franz.Segerer@ROHDE-SCHWARZ.COM","GP#40 completed",51.01,null,21,null,null,"2008-02-26","2008-11-22"]
[7089,400025,"Test - (Small) Technical Enhancements and Improvements for Rel-8","TEI8_Test",1,"Rel-8","R5,G3new","2007-03-07","2010-12-24",1,"-","-","-","-","-","-",40,21,null,null,"2005-11-04","2010-12-07"]
[7093,330010,"Deleted - never approved- FBI Phase 2 ","FBI2",1,"Rel-8","S2","2007-09-28","2007-09-28",1,"-","-","Nokia Siemens Networks","-","SP#38 stopped","-",null,null,"SP-38",null,"2003-06-09","2009-03-24"]
[7096,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[7099,53092,"Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain","SCSAGBCT-MStest",1,"Rel-8","G3new","2008-02-25","2009-09-04",1,"GP-080330","-","Nokia","arsi.heino@nokia.com","GP#43 work stopped/abandoned (completion 0%)",51.01,null,21,"GP-43","PCG-23","2008-02-26","2009-09-07"]
[7101,7026,"Study on Customised Alerting Tone (CAT) Requirements","FS_CAT",1,"Rel-8","S1","2005-10-07","2006-09-14",1,"SP-060474","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","Spin-off Rel-8 Feature Customized Alerting Tone (CAT) Service UID_340029",22.981999999999999,null,null,null,null,"2005-11-04","2010-08-31"]
[7104,320024,"Study on Requirements of IMS Multimedia Conferencing","FS_IMSconf",1,"Rel-8","S1","2006-06-08","2007-09-12",1,"SP-060479","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","SP#37 completed. Spin-off New Feature UID_370026 Value-Added Services for Short Message Service (VAS4SMS)",22.948,null,null,null,null,"2006-06-23","2010-08-31"]
[7108,340034,"Study on Value Added Services for Short Message Service","FS_VAS4SMS",1,"Rel-8","S1","2006-12-06","2007-12-07",1,"SP-060786","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","SP#38 completed. Spin-off New Feature UID_370026 (VAS4SM)",22.942,34,null,null,null,"2006-10-06","2010-08-31"]
[7111,32085,"Study on 3GPP System Architecture Evolution","FS_SAE",1,"Rel-8","S2,S3","2004-12-03","2009-03-12",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#43 completed","-",null,null,null,null,"2005-01-31","2009-02-20"]
[7114,7024,"   Security study for Inter-access mobility between non-3GPP and 3GPP system","FS_SAE",2,"Rel-8","S3","2007-09-03","2009-03-12",1,"SP-070163","-","Nokia","dajiang.zhang@nokia.com","SP#43 completed","33.821, 33.822",null,null,null,null,"2006-02-21","2009-02-20"]
[7118,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[7121,380078,"Study on Architecture of IMS based Customized Alerting Tone (CAT)","FS_CAT-St2",1,"Rel-8","S2","2007-12-04","2008-09-18",1,"SP-070905","-","China Mobile","WANG, Jing (wangjing@chinamobilecom)","SP#41 completed as Rel-8",23.872,38,21,null,null,"2007-12-20","2008-09-23"]
[7122,380085,"Study on Home (e)NodeB Security","FS_HNB_Sec",1,"Rel-8","S3","2007-12-20","2009-03-12",1,"SP-070783","-","Huawei","yangyanmei@huawei.com","SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007)",33.82,38,21,null,null,"2007-12-20","2009-03-11"]
[7126,320006,"Study on Common Profile Storage (CPS) Framework of User Data for network services and management","OAM7-CPS",1,"Rel-8","S5","2006-07-03","2007-06-07",1,"SP-060263","-","T-Mobile","istvan.aba@t-mobile.at","SP#36 completed. Spin-off New Feature UID_400034 User Data Convergence (UDC)",32.808,null,null,null,null,"2006-05-22","2008-03-17"]
[7129,7048,"Study on AS-MRFC media server control protocol","MRFC",1,"Rel-8","C1","2006-03-22","2008-06-13",1,"CP-060180","-","Hewlett-Packard","mark.syrett@hp.com","CP#40 completed. Spin-off New Feature UID_380035 (MRFC_TS)",24.88,null,null,null,null,"2006-03-22","2008-05-13"]
[7133,380023,"Study on InterWorking Function between MAP based and Diameter based interfaces","FS_MAP2Diam",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-070760","-","Huawei","liming49985@huawei.com","CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005",29.805,38,21,null,null,"2007-11-19","2008-11-22"]
[7136,360016,"Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies","FS_RAN-LTEmob",1,"Rel-8","R4","2007-06-04","2007-12-03",1,"RP-070511","RP-070827","Motorola","hao.bi@Motorola.com","RP#38 completed",36.938000000000002,null,null,null,null,"2007-06-21","2008-06-26"]
[7139,50590,"Study on Multi-User Reusing-One-Slot ","MUROS",1,"Rel-8","GP","2007-11-16","2010-11-12",1,"GP-072033","-","Nokia Siemens Networks","juergen.hofmann@nsn.com","GP#48 completed as Rel-8. Spin-off implementation WI UID_420002 VAMOS (Voice services over Adaptive Multi-user channels on One Slot)",45.914000000000001,null,null,null,null,"2007-11-19","2010-11-30"]
[7143,380068,"Deleted - Study on Evaluation of LCS Control Plane Solution for EPS","FS_LCS_EPS",1,"Rel-8","S2","2008-01-14","2008-05-30",1,"SP-070819","-","SiRF","-","SP#40 spin-off Feature UID_400038 (LCS_CPS_EPS). SP#40 FS stopped",23.890999999999998,38,null,"SP-40","PCG-21","2007-10-02","2009-03-24"]
[7147,732097,"Identification of Communication Services in IMS","ServID",1,"Rel-7","S2,S1,C1,S5","2005-05-02","2007-09-14",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","WID approved SP#28. WID updated SP#32","-",null,null,null,null,"2005-06-22","2008-07-01"]
[7148,32106,"   TR on ServID","ServID",2,"Rel-7","S2","2005-05-02","2006-03-21",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-",23.815999999999999,null,null,null,null,"2005-07-01","2008-07-01"]
[7151,7035,"   Charging of ServID","ServID",2,"Rel-7","S5","2006-03-31","2007-09-14",1,"SP-060293","-","Orange","alain.bibas@orange-ft.com","-","32.260, 32.298, 32.299",null,null,null,null,"2006-03-20","2008-07-01"]
[7154,7010,"   Stage 1,2 of GRUU","GRUU",2,"Rel-7","S1,S2","2006-07-03","2006-09-29",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","SP#29 approved WID","22.228, 23.228, 23.218, 24.229",null,null,null,null,"2006-02-16","2008-07-01"]
[7158,7037,"   Stage 3 of MTSI","MTSI",2,"Rel-7","C1","2006-03-10","2007-06-14",1,"CP-060257","-","Ericsson","christer.holmberg@ericsson.com","-",24.172999999999998,null,null,null,null,"2006-03-22","2008-06-25"]
[7161,690071,"   UE Conformance Test Aspects – Multimedia Telephony Services for IMS (MTSI) over WLAN","MTSI_WLAN-UEConTest",2,"Rel-7","R5","2015-09-15","2016-12-15",1,"RP-151770",null,"Ericsson",null,"tested: REL-7 WI MTSI¦1/1/16: Compl:0%->5%1/1/16: WID: RP-151334->RP-15177022/3/16: Compl:5%->10% ",null,69,35,null,null,"2015-09-29","2016-12-20"]
[7164,377001,"TISPAN requirements for Multimedia Telephony with PSTN/ISDN simulation services","TMMTEL7",1,"Rel-7","S1","2007-09-18","2007-12-06",1,"SP-070568","-","-","-","-","22.273 (EI 181 002 maintenance)",37,null,null,null,"2008-01-10","2008-01-10"]
[7168,380072,"   SA1,SA2 part of Maintenance of TISPAN release 1 common IMS","IMS_Comm_Mtce7",2,"Rel-7","S2,S1","2007-07-02","2007-12-06",1,"SP-080501","-","BT, Ericsson","Dick Knight, Raymond Forbes","SP#38 completed","22.173, 22.273, 22.401, 23.406, 23.417, 23.508, 23.509, 23.511",38,21,null,null,"2007-10-02","2010-07-29"]
[7172,32046,"   Study on Stage 2 for IMS-level solution","EMC1",2,"Rel-7","S2","2003-02-26","2005-09-16",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2003-03-27","2005-12-22"]
[7173,32080,"   Study on Stage 2 for GPRS-level solution","EMC1",2,"Rel-7","S2","2004-10-14","2005-12-08",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2004-10-14","2005-12-22"]
[7176,1653,"   Emergency Call Enhancements for IP& PS Based Calls – stage 3","EMC1",2,"Rel-7","C1,C4,IETF","2006-01-09","2011-12-09",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","-",null,null,null,null,"2000-08-08","2005-12-22"]
[7179,13028,"      Deleted - CT3 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C3","2006-05-08","2006-09-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","Cancelled for Rel-7 and there is no corresponding Rel-8 WI",29.163,null,null,"CP-33",null,"2000-04-19","2008-07-01"]
[7183,11065,"IMS Support of Conferencing","IMSconf",1,"Rel-7","C1","2005-11-04","2007-03-15",1,"CP-070120","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#35 revised WID","24.147, 24.229",null,null,null,null,"2005-12-22","2008-07-01"]
[7186,31057,"   Stage 1 on Session Continuity","WLAN2",2,"Rel-7","S1","2004-01-05","2004-06-11",1,"-","-","-","-","Acronym changed from \"WLAN2, WLAN-SC\"",22.234000000000002,null,null,null,null,"2004-06-17","2015-03-24"]
[7189,32111,"   WLAN-PNA - Stage 2","WLANPNA-st2",2,"Rel-7","S2","2005-10-10","2006-06-23",1,"SP-050489","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Approved at SP#29","23.234, 33.234",null,null,null,null,"2005-12-20","2006-05-31"]
[7194,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[7197,14028,"   Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking","WLANQOS",2,"Rel-7","C4","2006-09-22","2007-03-09",1,"CP-060418","-","Huawei","zhang.peng@huawei.com","CP#33 approved WID","29.234, 23.008",null,null,null,null,"2006-10-11","2008-07-18"]
[7198,340005,"   Stage 3 CT1 on support of QoS over 3GPP/WLAN Interworking","WLANQOS",2,"Rel-7","C1","2006-09-04","2006-11-30",1,"CP-060418","-","Huawei","zhang.peng@huawei.com","CP#33 approved WID",24.234000000000002,34,null,null,null,"2006-11-29","2008-07-18"]
[7201,50558,"   LCS Enhancements related to Location-Based Services","LCS3-LBS",2,"Rel-7","GP","2005-01-03","2007-08-31",1,"GP-050265","-","SiRF","kjudge@sirf.com","-","43.059, 44.031, 48.008, 49.031",null,null,null,null,"2005-02-01","2008-07-02"]
[7204,20012,"   Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications","LCS3-UEPos-UTDOA",2,"Rel-7","R2","2004-09-15","2007-12-17",1,"RP-040387","RP-070797","TruePosition","Robert Gross (rgross@polariswireless.com)","-","25.305, 25.453, new 25.111",null,null,null,null,"2004-09-27","2008-07-02"]
[7208,340007,"      Stage 2 for LCS architecture for I-WLAN","LCS3-IWLAN",3,"Rel-7","S2","2006-10-23","2007-03-02",1,"SP-060818","-","LG Electronics","dhshim@lge.com ; phede@lge.com","-","23.234, 23.271, 23.167",34,null,null,null,"2006-02-16","2011-08-15"]
[7210,31084,"MBMS Enhancements","MBMSE",1,"Rel-7","S1,R1,C3","2005-07-11","2007-11-30",1,"SP-050389","-","China Mobile","liuhongyfw@chinamobile.com","-","-",null,null,null,null,"2005-06-20","2008-06-25"]
[7216,400058,"MBMS - UE Conformance Testing","MBMSE_UEConTest",1,"Rel-7","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Linked to Rel-7 Feature UID_31084 (MBMSE)","-",40,21,null,null,"2008-03-11","2009-04-01"]
[7219,400060,"   Conformance Test Aspects – MBSFN for FDD","MBMSE-UEConTest_RANPhysFDD",2,"Rel-7","R5","2008-05-30","2009-12-04",1,"RP-080336","RP-091214","Huawei","Xiang Li (trica_li@huawei.com)","RP#46 completed","34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3",40,21,null,null,"2008-06-03","2009-11-26"]
[7222,50551,"   Stage 1/2 for Towards AGNSS Concept","AGNSS",2,"Rel-7","S1,S2","2007-02-16","2007-02-16",1,"SP-040681","-","Alcatel","richard.couty@space.alcatel.fr","-","22.071, 23.271",null,null,null,null,"2012-05-21","2012-05-21"]
[7223,50548,"   Towards AGNSS Concept","AGNSS-GP",2,"Rel-7","GP","2004-06-28","2007-08-31",1,"GP-042677","-","Alcatel","richard.couty@space.alcatel.fr","GP#36 completed","43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031",null,null,null,null,"2004-08-30","2012-05-21"]
[7226,31048,"Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM","USSD-USIM",1,"Rel-7","S1,C6","2004-03-05","2005-08-12",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","-",null,null,null,null,"2004-06-08","2008-09-10"]
[7229,31063,"Combinational Services ","CSICS",1,"Rel-7","S1,S2,C1,S4","2005-01-17","2006-03-06",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-","-",null,null,null,null,"2004-12-17","2008-07-02"]
[7235,31066,"   Stage 1 for CAMEL Trunk Triggers","TTCAMEL",2,"Rel-7","S1","2004-12-17","2005-12-05",1,"SP-040743","-","Nortel","Amar Deol (deola@nortelnetworks.com)","-",22.077999999999999,null,null,null,null,"2004-12-17","2008-07-18"]
[7237,31088,"IMS Service Brokering enhancements","ISB",1,"Rel-7","S1","2005-12-07","2006-03-13",1,"SP-050830","-","Telcordia","jbakker@telcordia.com","No CR submitted in rel-8 (according to CR database). ",22.228000000000002,null,null,null,null,"2005-11-04","2008-03-25"]
[7241,11056,"   Architecture and protocol aspects ","EVGCS",2,"Rel-7","C1,C4","2004-08-27","2007-06-15",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-","43.068, 44.068",null,null,null,null,"2005-09-14","2006-03-09"]
[7244,752076,"   GERAN2 aspects of EVGCS","EVGCS",2,"Rel-7","G2","2004-08-27","2007-02-16",1,"GP-071855","-","Siemens","kenneth.isaacs@roke.co.uk","-","-",75,38,null,null,"2004-10-15","2007-03-08"]
[7247,32090,"   Stage 2 modifications for VGCS improvements","IVGCS",2,"Rel-7","C1","2005-12-01","2007-03-14",1,"NP-050141","-","T-Mobile","kurt.bischinger@t-mobile.at","-",43.067999999999998,null,null,null,null,"2005-03-22","2007-03-08"]
[7248,11057,"   Protocol aspects ","IVGCS",2,"Rel-7","C1","2005-12-01","2007-03-15",1,"NP-050141","-","T-Mobile","Dieter Jacobsohn","Previous name (before CT32) was Architecture and protocol aspects",44.067999999999998,null,null,null,null,"2005-09-14","2006-05-31"]
[7251,31071,"Open Service Access (OSA) Rel-7 ","OSA7",1,"Rel-7","S1,C5","2005-03-15","2007-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-","-",null,null,null,null,"2005-03-22","2005-09-15"]
[7256,15039,"   Rel-7 OSA Stage 2/3 enhancements","OSA7",2,"Rel-7","C5","2006-04-28","2007-06-08",1,"CP-070200","-","AePONA","damian.oneill@aepona.com","CP#34 updated WID CP-060607=>CP-070200","29.198/9, 23.198",null,null,null,null,"2005-12-14","2012-07-26"]
[7259,7020,"      Parlay X Application driven QoS Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2007-03-09",1,"CP-070200","-","BT","-","-","29.199-17, 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[7262,340003,"      Parlay-X Multimedia Multicast Control Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","ETRI","-","-","29.199-20, 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[7266,32089,"   Deleted - TR on different possible architectures","SDoUE-FS",2,"Rel-7","S2","2005-03-21","2005-12-16",1,"SP-050182","-","Vodafone","Gavin.Wong@vodafone.com","Moved from FS section Feb 06. Abandoned at SP-30","23.805 abandonned at SP-30; descendant C1 24.305",null,null,"SP-30",null,"2005-06-07","2008-07-17"]
[7269,320012,"   Stage 1 of NSP","NSP-TS",2,"Rel-7","S1","2006-03-15","2006-12-06",1,"SP-060220","-","O2","chris.friel@O2.com","-","22.101, 22.011, 23.122, 24.008, 25.304, 31.102, 45.008",null,null,null,null,"2006-07-17","2008-04-15"]
[7272,32064,"Access Class Barring and Overload Protection","ACBOP",1,"Rel-7","S2,C1","2004-03-15","2006-09-08",1,"SP-040338","-","Vodafone","chris.pudney@vodafone.com","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[7273,32065,"   TR on Stage 2","ACBOP",2,"Rel-7","S2","2004-03-15","2005-03-31",1,"SP-040338","-","NTT DoCoMo","Jean-Jacques Davidian (davidian@docomo.fr)","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[7277,50117,"   Deleted - Extra ACBOP information in GERAN","ACBOP",2,"Rel-7","GP","2006-09-08","2006-09-08",1,"-","-","-","-","-",44.018000000000001,null,null,"RP-33",null,"2004-04-14","2006-07-20"]
[7281,11050,"      Protocol impact of FBI for TISPAN R1","-",3,"Rel-7","S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","-",null,null,null,null,"2004-09-03","2006-02-16"]
[7284,13025,"         CT3 aspects of FBI for TISPAN R1","-",4,"Rel-7","C3","2003-11-05","2006-12-08",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","29.163, 29.209",null,null,null,null,"2004-09-03","2006-10-12"]
[7287,7002,"   PacketCable Related aspects","FBI-PCBL",2,"Rel-7","S2,S5,C1","2006-02-01","2007-03-14",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","-","-",null,null,null,null,"2006-02-16","2006-02-16"]
[7291,32081,"Support of SMS over generic 3GPP IP access","SMSIP",1,"Rel-7","S2,C4,C1","2004-10-14","2007-06-14",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID (removed MMS)","-",null,null,null,null,"2004-10-14","2008-07-18"]
[7294,310001,"   Stage 3 for SMSIP","SMSIP-St3",2,"Rel-7","C4,C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","-",null,null,null,null,"2006-04-13","2008-07-15"]
[7297,32082,"Evolution of Policy Control and Charging","PCC",1,"Rel-7","S2,S5,C3,C1","2004-10-14","2007-11-30",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID adding SA5 charging. 23.125 will be discontinued from Rel-7.","-",null,null,null,null,"2004-10-14","2008-07-18"]
[7298,32102,"   Deleted - TR for PCC","-",2,"Rel-7","S2","2004-10-14","2005-12-29",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-30: S2 has no intention for TR completion",23.803000000000001,null,null,"SP-33",null,"2005-07-01","2008-07-18"]
[{"$f":"A7302+1","v":7302},13029,"   Gx reference point for Policy and Charging Control","PCC-Gx",2,"Rel-7","C3","2005-12-02","2007-11-30",1,"CP-060434","-","Siemens","Thomas.Belling@nsn.com","-","29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208)",null,null,null,null,"2005-12-13","2008-07-18"]
[7306,32091,"Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC",1,"Rel-7","S2,S1,S5,C1,C4","2004-12-31","2007-06-15",1,"SP-060292","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","WID approved SP#27¦updated SP#28¦updated SP#32","-",null,null,null,null,"2005-06-07","2008-07-21"]
[7309,32105,"   Stage 2 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S2","2005-09-06","2006-09-08",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",23.206,null,null,null,null,"2005-07-01","2008-07-21"]
[7312,11066,"      CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C1","2006-02-01","2007-06-15",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-","24.206, 24.216",null,null,null,null,"2005-10-04","2008-07-21"]
[7316,320002,"   Deleted - Study on Stage 2 for One Tunnel solution","OPTUNEL-Study",2,"Rel-7","S2","2006-03-27","2006-09-15",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","TR for Info SP-33. SP-34: S2 Report intention to discontinue TR",23.809000000000001,null,null,"SP-34",null,"2004-08-30","2008-07-15"]
[7319,320029,"CSI Terminating Session handling","CSItermS",1,"Rel-7","S2,C1","2006-06-08","2007-06-15",1,"SP-060437","-","Samsung","Osok Song","Triggered by the abandoned Study UID_32117 ","-",null,null,null,null,"2006-07-19","2008-07-17"]
[7320,340014,"   Stage 2 of CStermS","-",2,"Rel-7","S2","2006-06-08","2007-03-02",1,"SP-060437","-","Samsung","Osok Song","-",23.279,34,null,null,null,"2007-01-05","2008-07-17"]
[7323,33022,"Liberty Alliance and 3GPP Security Interworking","LibSec",1,"Rel-7","S3","2005-03-10","2006-11-30",1,"SP-050145","-","Nokia","Silke.Holtmanns@nokia.com","WID approved SP#27.",33.979999999999997,null,null,null,null,"2005-03-24","2008-07-16"]
[7327,33028,"Key establishment between a UICC and a terminal","KeyEstUTerm",1,"Rel-7","S3","2005-12-07","2006-09-28",1,"SP-050780","-","Gemalto","mireille.pauliac@gemplus.com","-",33.11,null,null,null,null,"2005-12-12","2008-01-10"]
[7331,732032,"   2G GBA: 2G SIM usage in 3GPP GAA framework","SEC7-2GGBA",2,"Rel-7","S3","2005-09-12","2005-12-05",1,"SP-050576","-","Nokia","Silke.Holtmanns@nokia.com","-","33.920, 33.220",null,null,null,null,"2005-11-04","2008-07-16"]
[7334,310004,"      SA3 aspects of SEC7-NDS-TCAPsec","SEC7-NDS-TCAPsec-SA3",3,"Rel-7","S3","2005-09-12","2006-03-10",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-",33.204000000000001,null,null,null,null,"2005-11-04","2008-07-16"]
[7337,7043,"Interoperability between VGCS/VBS and A/Gb flexibility","VGCSFlex",1,"Rel-7","C1,C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","Voice Group Call Service","-",null,null,null,null,"2006-03-22","2008-07-21"]
[7341,13022,"DIAMETER on the PDG Wi interface","DIAMWi",1,"Rel-7","C3","2004-09-10","2006-12-08",1,"CP-060432","-","Vodafone","Nico.Gabriele@vodafone.com","-",29.161000000000001,null,null,null,null,"2005-01-18","2008-07-15"]
[7344,14012,"Mp (MRFC - MRFP) interface","Mp",1,"Rel-7","C4,C1","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-","-",null,null,null,null,"2003-01-13","2008-07-15"]
[7348,14021,"   Stage 3 for Mp (MRFC - MRFP) interface","Mp-St3c4",2,"Rel-7","C4","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-",29.332999999999998,null,null,null,null,"2003-01-13","2008-07-15"]
[7349,340016,"Routeing of MT-SMS via the HPLMN","SMSviaH",1,"Rel-7","C4,C1","2006-12-01","2007-03-09",1,"CP-070032","-","Vodafone","Nick.Russell@vodafone.com","WID approved in CP#34","23.040, 29.002",34,null,null,null,"2005-10-07","2007-09-12"]
[7352,440042,"Rel-7 (U)SIM API Testing (TS 31.213)","USIM_API_Test",1,"Rel-7","C6","2009-05-30","2010-03-19",1,"CP-090450","-","Sagem Orga","gerrit.hartbrod@sagem-orga.com","CP#47 completed. Update of Rel-6 (U)SIM API for Java Card Testing UID_43007 under Rel-6 UICC/USIM enhancements and interworking UID_1800",31.213000000000001,44,23,null,null,"2009-05-29","2010-03-09"]
[7356,34034,"3G-324M Video Telephony Call Setup Times Improvements","VTCSTI",1,"Rel-7","S4","2005-06-08","2006-09-27",1,"SP-050404","-","Vodafone","edward.hall@vodafone.co.uk","-",26.911000000000001,null,null,null,null,"2005-06-16","2006-11-29"]
[7359,34036,"End-to-End Multimedia Services Performance Metrics","E2EMSPM",1,"Rel-7","S4","2005-09-28","2007-03-15",1,"SP-050433","-","China Mobile","zhangyanyf@chinamobile.com","-",26.943999999999999,null,null,null,null,"2005-10-04","2007-03-08"]
[7363,35044,"      Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050302","-","Motorola","-","-","32.731/2/3/5, 32.631/2/3/5",null,null,null,null,"2005-06-17","2007-03-29"]
[{"$f":"A7366+1","v":7366},35048,"      Delta synchronization between IRP Manager and IRP Agent (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050306","-","Siemens","-","-","32.391/2/3/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[7369,35052,"      Partial suspension of Itf-N during maintenance/testing (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050310","-","Siemens","-","-","32.381/2/3/5",null,null,null,null,"2005-06-17","2007-06-22"]
[7371,35055,"      Deleted - Rules for Vendor Specific Extensions","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050313","-","Siemens","-","Request to TSG#35 to STOP the WI","32.62n; For n = 1 to 5",null,null,"SP-35",null,"2005-06-17","2007-03-29"]
[7374,35072,"      UTRAN radio channel power monitoring","-",3,"Rel-7","S5","2006-02-13","2007-03-15",1,"SP-050733","-","China Mobile","-","-","32.405, 32.64n; For n = 1 to 5",null,null,null,null,"2005-11-24","2007-03-29"]
[7377,35057,"      Performance measurements definition for CN CS","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050315","-","China Mobile","-","-","32.407, 32.408",null,null,null,null,"2005-06-17","2007-03-29"]
[7381,35069,"      Performance measurements definition for IMS","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050631","-","China Mobile","-","-","32.404,32.409,32.437, 32.632/3/4/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[7384,35040,"      End-to-end Service Level tracing for IMS","-",3,"Rel-7","S5","2005-11-11","2007-03-15",1,"SP-050627","-","Vodafone","-","07/2005: OMA (Stage 1), Stage 2/3 SA5, CT1/3/4","32.101, 32.421, 32.422, 32.423",null,null,"SP-31",null,"2005-03-02","2007-03-29"]
[7388,35070,"      Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management","-",3,"Rel-7","S5","2005-09-02","2006-12-15",1,"SP-050629","-","Nokia","-","-","32.421,32.422,32.423. 3 new 32.4x1,2,3",null,null,"SP-33",null,"2005-03-02","2007-03-29"]
[7390,320008,"   Alternate Charged Party (ACP) for IMS","CH7-IMS-ACP",2,"Rel-7","S5","2006-05-22","2007-06-14",1,"SP-060442","-","Lucent","njmazzarella@alcatel-lucent.com","-","32.240, 32.260, 32.298, 32.299",null,null,null,null,"2006-05-22","2007-06-22"]
[7395,23008,"   MIMO - Iub/Iur Protocol Aspects","MIMO-IurIub",2,"Rel-7","R3","2003-03-14","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037","-",null,null,null,null,"2003-03-27","2008-06-24"]
[7396,24008,"   MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing","MIMO-RF",2,"Rel-7","R4","2003-12-12","2007-09-17",1,"RP-030192","RP-070531","Alcatel-Lucent","ngm@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070531","-",null,null,null,null,"2003-03-27","2008-06-24"]
[7399,20028,"Rel-7 Improvements of the Radio Interface","-",1,"Rel-7","RP,GP","2004-09-15","2007-06-04",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2005-01-04","2008-06-25"]
[7402,20021,"   UMTS 2.6 GHz","RInImp-UMTS2600",2,"Rel-7","R4","2004-09-15","2005-06-14",1,"RP-040397","RP-050184","Nokia","jussi.numminen@nokia.com","RP#28 completed","25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121",null,null,null,null,"2004-09-27","2010-07-27"]
[7406,20024,"   UE Antenna Performance Evaluation Method and Requirements","RInImp-UEAnt",2,"Rel-7","R4,GP","2004-12-15","2007-06-04",1,"RP-050122","RP-070281","TeliaSonera","Christian.Bergljung@TeliaSonera.com","RP#36 completed","25.101, new (25.914, 25.963)",null,null,null,null,"2005-01-04","2010-07-27"]
[7409,20048,"      Additional minimum UE performance requirement for DL physical channels in support of DCH/HS-DSCH operation based on type 1 enhanced receiver (RX-Diversity)","RInImp-RxDiv-DCH",3,"Rel-7","R4","2005-09-15","2006-06-14",1,"RP-060185","RP-060235","Cingular","Marc Grant","RP#32 completed",25.100999999999999,null,null,null,null,"2005-10-05","2010-07-27"]
[7411,7029,"      Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-EDCH",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060184","RP-060679","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[7417,25013,"   Conformance Test Aspects – Improved Performance of HSDPA Receiver type 3","RInImp-HSPerf-Type3_Test",2,"Rel-7","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","RP#34 completed","34.121, 34.108",null,null,null,null,"2006-03-21","2006-03-21"]
[7420,25028,"   Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz","RInImp-UEConTest_UMTS1721Ext",2,"Rel-7","R5","2006-12-01","2007-06-01",1,"RP-060676","RP-070312","Motorola","carolyn.taylor@motorola.com","RP#36 completed","34.108, 34.121-1, 34.121-2",null,null,null,null,"2006-09-20","2007-06-11"]
[7421,25039,"   Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-UEConTest_RxDivEDCH",2,"Rel-7","R5","2007-06-01","2007-12-07",1,"RP-070414","RP-070810","Motorola","carolyn.taylor@motorola.com","RP#38 completed","-",null,null,null,null,"2006-09-20","2007-09-11"]
[7424,20026,"   Optimization of channelisation code utilisation for 1.28 Mcps TDD","RANimp-RABSE-CodOptLCRTDD",2,"Rel-7","R1","2004-12-15","2006-12-15",1,"RP-040552","RP-060682","UTStarcom","Ka Leong Lo (kaleong.lo@UTSTAR.COM)","RP#34 completed","-",null,null,null,null,"2005-01-04","2010-07-27"]
[7428,20046,"   Continuous connectivity for packet data users","RANimp-CPC",2,"Rel-7","R1","2005-03-14","2007-03-15",1,"RP-050870","RP-070033","Siemens","Joern.Krause@siemens.com ","RP#35 completed","25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133",null,null,null,null,"2005-10-05","2010-07-27"]
[7431,330009,"   Enhanced CELL_FACH State in FDD","RANimp-EnhState",2,"Rel-7","R2","2006-09-25","2007-06-04",1,"RP-070245","RP-070286","Nokia","juho.pirskanen@nokia.com","RP#36 completed","25.308, 25.304, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425,",null,null,null,null,"2006-10-06","2010-07-27"]
[7436,20166,"      RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs)","-",3,"Rel-7","R3","2006-06-02","2007-03-16",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[7439,25021,"   Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink","RANimp-UEConTest_EDCHTDH",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060484","RP-080536","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7442,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7445,20014,"7.68 Mcps TDD option","VHCRTDD",1,"Rel-7","R1,R2,R3,R4,R5","2004-09-15","2007-09-14",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","-",null,null,null,null,"2004-09-27","2010-07-27"]
[7446,20015,"   VHCRTDD: Stage 2","VHCRTDD-Stage2",2,"Rel-7","R1","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed",25.202000000000002,null,null,null,null,"2004-09-27","2010-07-27"]
[7449,20018,"   VHCRTDD: UTRAN Iub/Iur Protocol Aspects","VHCRTDD-IurIub",2,"Rel-7","R3","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Peter Legg (plegg@ipwireless.com)","RP#31 completed","25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435",null,null,null,null,"2004-09-27","2010-07-27"]
[7453,20036,"   EDCHTDD: Stage 2","EDCHTDD-Stage2",2,"Rel-7","R2","2005-03-15","2006-06-15",1,"-","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7457,20040,"   EDCHTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","EDCHTDD-RF",2,"Rel-7","R4","2005-03-15","2006-09-15",1,"-","RP-060462","IPwireless","Shin Horng Wong (shwong@ipwireless.com)","RP#33 completed","25.102, 25.105, 25.123, 25.142",null,null,null,null,"2005-03-15","2010-07-27"]
[7460,20057,"   1.28 Mcps TDD Enhanced Uplink: Layer 2 and 3 Protocol Aspects","LCRTDD-EDCH-L23",2,"Rel-7","R2","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Haiyang Quan","RP#35 completed","25.301, 25.302, 25.306, 25.321, 25.331",null,null,null,null,"2006-03-21","2010-07-27"]
[7464,490016,"Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD","LCRTDD_MB_MF_UEConTest",1,"Rel-7","R5","2010-09-17","2011-09-16",1,"RP-100805","RP-110968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD.","UTRA 34.108, 34.123-1, 34.123-2, 34.123-3",49,25,null,null,"2010-09-08","2011-09-06"]
[7467,51138,"   Inclusion of the 698 – 746 MHz band into GERAN core specifications","GSM710-core",2,"Rel-7","G1","2005-01-03","2005-06-30",1,"-","-","-","-","Completed","24.008, 43.022, 44.018, 44.118, 45, 001, 45.005, ",null,null,null,null,"2005-09-12","2005-09-15"]
[7468,53184,"   Aspects of GSM710","GSM-710-test",2,"Rel-7","G1,G3new","2005-08-31","2006-06-30",1,"-","-","-","-","-","-",null,null,null,null,"2005-09-12","2006-07-20"]
[7471,50564,"Support of Conversational Services in A/Gb mode via the PS domain","SCSAGB",1,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-061501","-","Ericsson","gunnar.hedby@ericsson.com","Originally started Nov. 2003 as GP-030443","-",null,null,null,null,"2005-04-21","2007-05-29"]
[7474,52144,"   Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode","SCSAGB-RLCNP",2,"Rel-7","G2","2006-06-30","2006-11-17",1,"GP-061503","-","Ericsson","gunnar.hedby@ericsson.com","-","43.955, 43.064, 44.060, 45.001, 45.002, 45.003, 45.005, 45.010, 51.010, 51.021",null,null,null,null,"2006-07-05","2008-01-10"]
[7478,50566,"   Changes to core specification","TGSM810-Core",2,"Rel-7","GP","2005-04-08","2005-09-02",1,"GP-050946","-","Huawei","chende@huawei.com","-","45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060",null,null,null,null,"2005-04-21","2005-09-15"]
[7482,55093,"   GERAN2 part of Handover of dedicated and shared resources while in Dual Transfer Mode","HODSRDTM-G2",2,"Rel-7","G2","2005-04-08","2006-06-30",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","GP#30 completed","43.055, 44.018, 44.060",null,null,null,null,"2005-04-21","2006-07-17"]
[7485,50569,"Mobile Station Receive Diversity (DARP Phase II)","MSRD2",1,"Rel-7","GP","2005-11-11","2007-11-16",1,"GP-061491","-","Nokia","kent.pedersen@nokia.com","GP#36 completed","-",null,null,null,null,"2005-11-21","2008-05-19"]
[7489,50570,"   MS conformance test of DARP Phase II (MSRD)","MSRD2-Msconf",2,"Rel-7","GP","2005-11-11","2007-11-16",1,"GP-060114","-","Nokia","kent.pedersen@nokia.com","GP#36 completed",51.01,null,null,null,null,"2005-11-21","2007-09-12"]
[7492,52142,"   Downlink Dual Carrier Stage 3","GDCDL-Stage3",2,"Rel-7","G1","2006-01-20","2007-08-31",1,"GP-060485","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#35 completed","24.008, 44.018, 44.060, 45.001, 45.002, 45.005, 45.008",null,null,null,null,"2006-01-24","2009-04-01"]
[7493,53086,"   Downlink Dual Carrier – MS Conformance Test ","GDCDL-MStest",2,"Rel-7","G3new","2006-01-20","2009-09-04",1,"GP-060486","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#43 completed",51.01,null,null,null,null,"2006-01-24","2009-09-07"]
[7496,52145,"   Improved Ack/Nack reporting","LATRED-ACKNAR",2,"Rel-7","G2","2006-06-30","2007-08-31",1,"GP-061520","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021",null,null,null,null,"2006-07-05","2008-12-15"]
[7499,50584,"Higher Uplink performance for GERAN Evolution ","HUGE",1,"Rel-7","GP","2006-09-08","2011-05-20",1,"GP-071083","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#39 completed","-",null,null,null,null,"2006-09-13","2010-07-26"]
[7504,51143,"   BTS Conformance Test for HUGE","HUGE-BTStest",2,"Rel-7","G1","2006-09-08","2009-09-04",1,"GP-061907","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#43 completed",51.021000000000001,null,null,null,null,"2006-09-13","2009-09-07"]
[7507,51144,"   Stage 2 for REDHOT","REDHOT-Stage2",2,"Rel-7","G1","2006-11-17","2007-08-31",1,"GP-062489","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#35 completed","43.055, 43.064",null,null,null,null,"2006-11-20","2008-12-15"]
[7510,53088,"   MS Conformance Tests for REDHOT","REDHOT-Mstest",2,"Rel-7","G3new","2006-11-17","2011-05-20",1,"GP-062491","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#50 completed",51.01,null,null,null,null,"2006-11-20","2011-05-21"]
[7514,32114,"   Deleted - IMS aspects to support IMS Emergency sessions","-",2,"Rel-7","S2","2006-06-23","2006-06-23",1,"SP-050604","-","Nokia","curt.c.wong@nokia.com","Approved at SP#29","23.867, 23.abc, 23.060, 23.002, 23.271",null,null,"SP-30",null,"2005-03-22","2005-12-22"]
[7517,32019,"   Deleted - Stage 2","-",2,"Rel-7","S2","2006-01-06","2006-01-06",1,"-","-","-","-","DAB - Not yet required in SA2 as it exists in previous releases","-",null,null,"SP-26",null,"2002-03-25","2004-12-06"]
[7518,11035,"   Deleted - Stage 3 for IMS Local services","-",2,"Rel-7","C1","2006-01-06","2006-01-06",1,"-","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,"SP-25",null,"2003-01-13","2004-09-09"]
[7524,31082,"Study on Multimedia Telephony Capabilities for IMS","MITE",1,"Rel-7","S1","2005-07-11","2006-07-31",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","Spin-off Feature UID_7038 (MTSI)",22.972999999999999,null,null,null,null,"2005-04-21","2008-07-01"]
[7525,31050,"Study on Behaviour of Multi system UEs","BMSU",1,"Rel-7","S1","2004-06-28","2005-12-15",1,"SP-050502","-","Qualcomm","dwilliams@qualcomm.com","-",22.936,null,null,null,null,"2004-08-30","2008-06-27"]
[7529,31073,"Study on Network Selection Principles","NetSel",1,"Rel-7","S1","2005-03-15","2005-12-08",1,"SP-050227","-","O2","chris.friel@O2.com","Spin-off Feature Network selection enhancements (NSP-CR) UID_7041",22.811,null,null,null,null,"2005-03-22","2008-06-27"]
[7532,32073,"Study on Enhancement of E2E QoS","QoS7",1,"Rel-7","S2","2004-06-28","2005-09-15",1,"SP-040326","-","Huawei","Robert Jaksa","-",23.802,null,null,null,null,"2004-08-30","2008-06-30"]
[7536,7034,"Study on Bandwidth Saving at Nb Interface with IP transport","BSNbIP",1,"Rel-7","C3","2006-03-10","2007-03-09",1,"CP-060438","-","Siemens","Thomas.Belling@siemens.com","Moved to FS at CT32 (in line with slides)",29.814,null,null,null,null,"2006-03-20","2010-07-27"]
[7539,7050,"Study on using M2PA in 3GPP network ","FS-M2PA",1,"Rel-7","C4","2006-03-22","2007-06-08",1,"CP-060698","-","China Mobile","zhaoyuyi@chinamobile.com","-",29.800999999999998,null,null,null,null,"2006-03-22","2008-07-01"]
[7542,330003,"   CT3 aspects of NcSIP","-",2,"Rel-7","C3","2006-05-15","2007-09-14",1,"CP-070034","-","Ericsson","ragnar.huslende@ericsson.com","-",29.802,null,null,null,null,"2006-09-21","2008-07-01"]
[7545,20041,"Study on UTRA Tower Mounted Amplifier (FDD)","RANFS-TMA",1,"Rel-7","R4","2005-06-15","2006-03-14",1,"RP-050387","RP-060035","Ericsson","Klas.Sjerling@ericsson.com","RP#31 (Mar 2006) completed. SR in RP-060035",25.818000000000001,null,null,null,null,"2005-06-20","2010-07-27"]
[7547,20051,"Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN","RANFS-MBMSImp",1,"Rel-7","R2","2005-12-15","2006-12-15",1,"RP-050746","RP-060692","LG Electronics","leego@lge.com","RP#34 completed",25.905000000000001,null,null,null,null,"2005-12-15","2012-07-26"]
[7550,20065,"Study on Scope of future FDD HSPA Evolution","RANFS-HSPAEvo",1,"Rel-7","RP","2006-03-15","2007-09-17",1,"RP-060217","RP-070533","Cingular","Don Zelmer (dz1069@att.com)","RP#37 (Sep 2007) completed. SR in RP-070533",25.998999999999999,null,null,null,null,"2006-03-21","2008-06-23"]
[7554,31054,"Deleted - Study on IMS with real time services deployment","IRTSD",1,"Rel-7","S1","2004-06-28","2005-09-12",1,"SP-040465","-","-","-","-","-",null,null,"SP-30",null,"2004-08-30","2008-06-27"]
[7557,732028,"Deleted - IMS security extensions (covered by UID33027)","IMS-SE",1,"Rel-7","S3","2005-12-08","2005-12-08",1,"SP-050395","-","Ericsson","Bengt.Sahlin@ericsson.com","-","-",null,null,"SP-30",null,"2005-06-20","2005-12-22"]
[7561,32076,"Deleted - Study on Stage 2 (IMS services using CS bearers)","IRTSD-IMSCS",1,"Rel-7","S2","2004-06-28","2005-09-12",1,"SP-040479","-","Nortel","Mark Watson","SP-30: S2 has no intention for TR completion",23.899000000000001,null,null,"SP-30",null,"2004-08-30","2008-06-26"]
[7564,32112,"Deleted - Study on IMS enhancements and optimizations for real time communication.","IMS-RT",1,"Rel-7","S2","2005-10-10","2007-06-01",1,"SP-050492","-","Ericsson","stephen.terrill@ericsson.com","abandoned at 65%",23.818000000000001,null,null,"SP-35",null,"2006-02-16","2007-06-22"]
[7567,35045,"Deleted - Study on IRP usage scenarios","OAM-Study",1,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050303","-","Lucent","-","-","32.8xy",null,null,"SP-32",null,"2005-06-17","2007-03-29"]
[7570,0,"--- RELEASE 6 ---","-",1,"Rel-6","NP,GP,RP,SP,TP","2002-06-28","2005-12-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7572,20032,"   Improved support of IMS Realtime Services using HSDPA/EDCH","RInImp-IMSRealTime",2,"Rel-6","R2","2005-03-15","2005-12-14",1,"-","-","Cingular","Don Zelmer (dz1069@att.com)","-","-",null,null,null,null,"2005-06-20","2006-01-13"]
[7575,1476,"      FDD Base station classification","-",3,"Rel-6","R4","2000-08-14","2002-12-04",1,"-","-","Nokia","antti.toskala@nokia.com","-","25.104, 25.141",null,null,null,null,"2000-07-26","2004-07-08"]
[7579,25010,"   Conformance Test Aspects – UMTS 1.7/2.1 GHz Band","RInImp-UMTS1721_Test",2,"Rel-6","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","TS34.121, TS34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[7582,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7586,23007,"   FS of the improved access to UE measurement data for CRNC to support TDD RRM","RANimp-RRMopt-FSUEMsD",2,"Rel-6","R3","2002-12-06","2003-12-18",1,"-","-","Interdigital","jim.miller@interdigital.com","-","25.801, 25.423",null,null,null,null,"2003-02-13","2004-10-21"]
[7589,21003,"   FS for the analysis of OFDM for UTRAN enhancement","RInImp-FSOFDM",2,"Rel-6","R1","2002-06-10","2004-06-14",1,"-","-","Nortel","Sarah Boumendil","-",25.891999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7591,21005,"   FS on Analysis on Higher Chip Rates for UTRA TDD evolutions","RInImp-FSVHCRTDD",2,"Rel-6","R1","2002-09-06","2004-09-14",1,"-","-","IPWireless","mbeale@ipwireless.com","Study finished at RP#25",25.895,null,null,null,null,"2003-10-02","2004-10-13"]
[7594,24005,"   FS on UE antenna efficiency test methods performance requirements (2)","RInImp-UEAnTM2",2,"Rel-6","R4","2002-03-08","2002-09-06",1,"-","-","Allgon","Alf Ahlström (alf.ahlstrom@pwav.com)","The RInImp-UEAnTM FS was re-opened at TSG RP#15 upon request from WG4","-",null,null,null,null,"2002-05-30","2004-07-08"]
[7597,20004,"   FDD Enhanced Uplink - Stage 2","EDCH-Stage2",2,"Rel-6","R2","2004-03-15","2004-12-14",1,"-","-","-","-","-",25.309000000000001,null,null,null,null,"2004-03-21","2005-01-13"]
[7601,20008,"   FDD Enhanced Uplink - RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","EDCH-RF",2,"Rel-6","R4","2004-03-15","2004-06-24",1,"-","-","Ericsson","thomas.unshelm@ericsson.com","-","25.101, 25.104, 25.133, 25.141",null,null,null,null,"2004-03-18","2006-01-13"]
[7604,624,"   RAB support enhancement","-",2,"Rel-6","R2","2003-03-14","2005-03-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","building block without particular end date",25.861999999999998,null,null,null,null,"2000-03-31","2005-01-13"]
[7607,20013,"      HS-DPCCH ACK/NACK Enhancement","RANimp-RABSE-ACKNACK",3,"Rel-6","R1","2004-09-15","2004-12-14",1,"-","-","Nokia","Jussi Kähtävä (juha.mikola@nokia.com)","Approved at RP#25 as RP-040390","25.212, 25.214, 24.331, 25.433",null,null,null,null,"2004-09-27","2005-03-25"]
[7611,23012,"   Rel-6 RRM optimization for Iur and Iub","RANimp-RRMopt-UEMsD",2,"Rel-6","R3","2003-09-19","2004-03-12",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2003-03-27","2004-07-08"]
[7612,23014,"      Improved access to UE measurement data for CRNC to support TDD RRM","-",3,"Rel-6","R3","2003-09-19","2004-03-12",1,"-","-","Interdigital","jim.miller@interdigital.com","-",25.422999999999998,null,null,"RP-22",null,"2003-10-02","2005-01-13"]
[7618,32024,"   Improvement on Le interface","-",2,"Rel-6","S2,OMA","2002-06-17","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-05-21"]
[7619,32051,"      Stage 2 for Improvement on Le interface","-",3,"Rel-6","S2","2002-06-17","2003-09-22",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[{"$f":"A7622+1","v":7622},32047,"      Stage 2 for Enhanced support for anonymity and user privacy","-",3,"Rel-6","S2","2002-07-08","2003-06-27",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[7626,32055,"      Stage 3 - definition of RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7629,32056,"      OMA Stage 3 for Location Services support for IMS public identities - impacts MLP, RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7632,14015,"      Stage 3 for UE-CN signalling","-",3,"Rel-6","N4","2003-10-09","2004-08-31",1,"SP-030127","-","Nokia","-","Current stage 3 fullfills stage 2","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7637,22002,"      Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods","LCS2-UEpos-FSBlank",3,"Rel-6","R2","2002-07-01","2003-09-19",1,"-","-","Cambridge Positioning Systems","david.bartlett@cursor-system.com","RP#38 Work stopped","new 25.894",null,null,"RP-38",null,"2002-06-21","2012-05-21"]
[7640,1571,"Rel-6 Security enhancements","SEC16",1,"Rel-6","S3","2001-01-03","2004-11-26",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID. Acronym changed from \"SEC1, Rel-6\"","-",null,null,null,null,"2000-04-09","2015-03-24"]
[7641,2026,"   Enhanced HE control of security (including positive authentication reporting)","-",2,"Rel-6","S3","2001-01-03","2003-09-25",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID S3-000490 (Enhanced home control of security by HE)",33.101999999999997,null,null,null,null,"2000-09-22","2011-08-08"]
[7644,33007,"         Rel-6 IP network layer security (NDS/IP)","SEC1-NDS-IP",4,"Rel-6","S3","2002-06-17","2003-09-25",1,"SP-000420","-","-","-","SP#9 approved WID S3-000626 (Access security for IP-based services)",33.21,null,null,null,null,"2002-11-08","2011-08-08"]
[7647,33020,"Network Domain Security; MAP application layer security (NDS/MAPsec)","MAPSEC",1,"Rel-6","S3","2004-07-06","2004-12-29",1,"SP-040280","-","Vodafone","Peter.Howard@vodafone.com","SP#19 approved WID. Marked as closed 12/2008 (was marked 20% complete)",33.200000000000003,null,null,null,null,"2003-07-25","2011-08-08"]
[7651,31025,"   IMS Group Management","IMSGM",2,"Rel-6","S1","2002-03-14","2004-12-08",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7654,11036,"      Stage 3 for IMS Group management (e.g. chat)","-",3,"Rel-6","N1","2002-12-13","2004-12-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Depends on CN decision on CPCP in Rel-6. Complete, if unresolved IETF dependencies are dropped (-> LS to CN plenary)","-",null,null,null,null,"2003-01-13","2005-03-25"]
[7658,31022,"   IMS Messaging","IMSM",2,"Rel-6","S1","2002-03-14","2005-12-30",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2004-09-08"]
[7662,32700,"      Stage 2 for IMS Messaging","-",3,"Rel-6","S2","2002-11-04","2004-08-31",1,"-","-","-","-","-",23.228000000000002,null,null,null,null,"2002-09-26","2004-09-08"]
[7665,11040,"   Additional SIP Capabilities support not covered by Rel-5","-",2,"Rel-6","N1","2002-11-11","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[7666,32041,"      Stage 2 for add SIP cap (e.g. forking)","-",3,"Rel-6","S2","2002-11-11","2004-02-20",1,"-","-","-","-","-",23.228000000000002,null,null,null,null,"2003-02-27","2004-03-12"]
[7669,11041,"   Review additional SIP Capabilities against IMS","-",2,"Rel-6","N1","2002-12-13","2004-09-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2003-01-13","2005-03-25"]
[7672,13005,"      Interworking for IPv6 to IPv4","-",3,"Rel-6","N3","2000-08-28","2004-12-08",1,"-","-","-","-","-",29.163,null,null,null,null,"2002-02-28","2005-03-09"]
[7676,14001,"   Mn interface (IM-MGW to MGCF) enhancements (CN4 Part)","IMS-CCR-Mn",2,"Rel-6","N4","2001-08-07","2004-09-01",1,"-","-","-","-","TISPAN issue is open","-",null,null,null,null,"2001-10-08","2005-03-09"]
[7679,31042,"   IMS Subscription and access scenarios","-",2,"Rel-6","S1","2002-12-16","2003-06-13",1,"-","-","TeliaSonera","FRANK, Robert","-",22.8,null,null,null,null,"2003-03-28","2010-08-31"]
[7683,32063,"3GPP Enablers for services like Push to Talk over Cellular (PoC)","PoC",1,"Rel-6","S2,S4,S5","2003-09-08","2005-06-09",1,"SP-030384","-","Ericsson","Shabnam Sultana","-","-",null,null,null,null,"2003-10-15","2004-07-08"]
[7687,35036,"   PoC charging","PoC-CH",2,"Rel-6","S5","2004-09-27","2005-06-09",1,"SP-050032","-","Siemens","Gerald.Goermer@nsn.com","SP#28 06/2005 completed",32.271999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[7690,32028,"   Stage 2 for Interoperability","-",2,"Rel-6","S2","2002-09-16","2003-09-30",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2",23.864000000000001,null,null,null,null,"2002-11-08","2004-07-08"]
[7691,32061,"   Stage 2 for commonality","-",2,"Rel-6","S2","2002-09-16","2003-09-19",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","-",23.864000000000001,null,null,null,null,"2003-09-15","2004-07-08"]
[7694,31004,"   Stage 1 for Support of Push Services","-",2,"Rel-6","S1","2001-01-03","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2003-07-04"]
[7697,42010,"   Definition of service requirements for MMS6","MMS6-SR",2,"Rel-6","S1","2002-11-15","2003-12-19",1,"-","-","-","-","-",22.14,null,null,null,null,"2002-09-26","2004-03-12"]
[7700,42012,"   OMA dependencies","-",2,"Rel-6","OMA","2003-08-15","2005-04-29",1,"-","-","-","-","-","OMA specs",null,null,null,null,"2002-09-26","2005-03-25"]
[7705,42005,"Rel-6 MExE enhancements","MEXE6",1,"Rel-6","T2","2002-03-08","2003-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-21","2002-03-21"]
[7709,2499,"Presence Capability","PRESNC",1,"Rel-6","S1,S2,S3,S4,N1,N3,N4,OMA","2001-03-19","2005-12-07",1,"SP-010064","-","Motorola","Mark Cataldo","merged \"Presence Service Enhancements\" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date","-",null,null,null,null,"2001-03-30","2004-09-08"]
[7712,2503,"   Stage 3 for Presence Capability","-",2,"Rel-6","N1,N4","2002-04-01","2004-12-08",1,"NP-040492","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Dependency to 2 IETF drafts, no known work at the moment","New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328)",null,null,null,null,"2001-03-30","2011-08-09"]
[7715,2504,"   Security aspects of Presence Capability","-",2,"Rel-6","S3","2002-08-26","2002-12-12",1,"SP-020514","-","Ericsson","krister.boman@erv.ericsson.se","SP#17 approved WID S3-020429","-",null,null,null,null,"2001-03-30","2011-08-09"]
[7716,60003,"   SIMPLE Presence","-",2,"Rel-6","OMA","2004-01-01","2005-03-31",1,"SP-040232","-","-","OMA-LIAISON@mail.openmobilealliance.org","SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables","-",null,null,null,null,"2004-06-08","2011-08-09"]
[7719,50080,"      Requirements for the support of conversational services","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[7725,50063,"Flexible Layer One for GERAN","FLOGER",1,"Rel-6","GP,S3","2000-01-03","2004-06-25",1,"GP-021018","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2003-09-16"]
[7727,50065,"      Technical Report on Realisation of a Flexible Layer One","-",3,"Rel-6","GP","2002-04-19","2004-02-06",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7730,51004,"      Channel Coding in 45.003 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[7734,52072,"   Signalling and protocol support for a Flexible Layer One","FLOGER-SigPro",2,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-12-06"]
[7737,52075,"   Security for a Flexible Layer One","FLOGER-SecFLO",2,"Rel-6","S3,G2","2002-04-19","2003-08-29",1,"GP-021021","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-01-14"]
[7740,55078,"      Deleted at TSG #27 - MS Test in 51.010","-",3,"Rel-6","G4,G5","2004-02-06","2004-02-06",1,"-","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-22",null,"2002-05-23","2005-03-09"]
[7741,55079,"   Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE","FLOGER-BTSconf",2,"Rel-6","G3new","2004-02-06","2004-02-06",1,"GP-021023","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-27",null,"2002-05-23","2005-03-09"]
[7746,32002,"   Stage 2 for Multimedia Broadcast and Multicast Service","-",2,"Rel-6","S2","2001-09-24","2004-03-17",1,"SP-010516","-","-","-","-","-",null,null,null,null,"2001-09-19","2012-07-26"]
[7748,32703,"      Stage 2 MBMS Specification Work","-",3,"Rel-6","S2","2002-08-19","2004-03-17",1,"-","-","-","-","-",23.245999999999999,null,null,null,null,"2002-09-26","2012-07-26"]
[7752,35038,"   MBMS Charging","MBMS-CH",2,"Rel-6","S5","2005-01-11","2005-06-09",1,"SP-040779","-","-","-","SP#28 completed",32.273000000000003,null,null,null,null,"2004-10-29","2012-07-26"]
[7755,34026,"      Definition of MBMS user services, media codecs, formats and transport/application protocols using MBMS","MBMS-TSMBMS",3,"Rel-6","S4","2003-06-12","2006-03-16",1,"SP-030674","-","Nokia","igor.curcio@nokia.com","-","26.346, 26.936, 26.946",null,null,null,null,"2003-07-04","2012-07-26"]
[7759,25024,"   MBMS UE Conformance Testing","MBMS-UEConTest",2,"Rel-6","R5,T1","2006-03-10","2008-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2006-09-22","2012-07-26"]
[7762,25023,"      Signalling Conformance Test Aspects – MBMS for LCR TDD","MBMS-UEConTest_SIGTDL",3,"Rel-6","R5,T1","2006-09-20","2007-12-07",1,"-","-","Datang","zhaojian@datangmobile.cn","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2012-07-26"]
[7765,50085,"   Support of MBMS in GERAN","MBMS-GERAN",2,"Rel-6","GP,G2,G3new","2001-08-30","2005-01-28",1,"GP-022566","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7767,52085,"      MBMS Re-synchronisation at cell change","-",3,"Rel-6","G2","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7770,50100,"      MBMS Resynchronization at cell change","-",3,"Rel-6","GP","2001-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7774,50090,"      GERAN specific changes to the Iu-ps interface for MBMS","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[7777,53081,"      MBMS-GERAN - MS conformance tests","-",3,"Rel-6","G3new","2002-01-25","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[7780,31007,"   Speech Enabled Services Based on Distributed Speech Recognition (DSR)","DSR",2,"Rel-6","S1","2001-10-08","2002-03-15",1,"SP-010581","-","Qualcomm","Dwilliams@qualcomm.com","-","22.977, 22.941, 23.207, 22.243",null,null,null,null,"2001-10-09","2004-03-12"]
[7784,11021,"   Deleted - SES codec negotiation at Session Description Protocol (SDP)","-",2,"Rel-6","N1","2003-06-04","2003-06-04",1,"-","-","-","-","Abandoned NP-23","-",null,null,"NP-23",null,"2004-10-20","2004-10-21"]
[7787,32008,"   Stage 2 - Architecture","-",2,"Rel-6","S2","2002-01-28","2003-06-06",1,"SP-020539","-","Nokia","harri.o.koskinen@nokia.com","-",23.24,null,null,null,null,"2001-10-09","2004-03-12"]
[7788,42002,"   Stage 2 - Data Description Method","-",2,"Rel-6","N4","2002-12-05","2005-03-03",1,"TP-020275","-","T-Mobile","kurt.bischinger@t-mobile.at","TR approved in CN#26",23.241,null,null,null,null,"2001-10-09","2005-03-09"]
[7792,31011,"   Requirements for Digital Rights Management","-",2,"Rel-6","S1","2001-10-08","2002-06-13",1,"-","-","Openwave","nicholas.wood@openwave.com","-","-",null,null,null,null,"2001-10-11","2003-07-04"]
[7795,33001,"   Security for Digital Rights Management","-",2,"Rel-6","OMA","2002-06-17","2003-03-03",1,"-","-","-","-","SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17","-",null,null,null,null,"2001-10-11","2005-03-25"]
[7799,31035,"   Stage 1 for WLAN-UMTS Interworking Rel-6","WLAN-TS",2,"Rel-6","S1","2003-01-06","2004-06-11",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","-","22.101, 22.105",null,null,null,null,"2003-01-13","2004-06-08"]
[7802,14013,"   Stage 3 - CN4 aspects","WLAN-IW",2,"Rel-6","N4","2003-05-23","2004-09-01",1,"NP-030490","-","Nokia","raquel.rodriguez@nokia.com","WID approved at CN#19","29.234, 29.061",null,null,null,null,"2003-03-27","2005-03-09"]
[7805,11047,"   Stage 3 for scenario 3","-",2,"Rel-6","N1","2003-05-23","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-06-08","2005-03-09"]
[7809,31016,"   Feasibility Study on Priority Service","PRIOR-FS",2,"Rel-6","S1","2002-06-14","2002-06-14",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-",22.95,null,null,null,null,"2002-02-27","2010-08-31"]
[7812,31018,"Network Sharing ","NTShar",1,"Rel-6","S1,S2,N1,R2,R5","2003-01-20","2006-03-10",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","-",null,null,null,null,"2002-02-27","2009-11-10"]
[7813,31019,"   Technical Report on Network Sharing ","NTShar-TR",2,"Rel-6","S1","2003-01-20","2003-12-19",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-",22.951000000000001,null,null,null,null,"2002-02-27","2009-11-10"]
[7817,22004,"   Enhancement of the support of network sharing in the UTRAN","NTShar-UTRANEnh",2,"Rel-6","R2","2003-09-19","2003-09-19",1,"-","-","TeliaSonera","Anders.Dahlen@TeliaSonera.com","-","25.401, 25.413, 25.331, 25.304",null,null,null,null,"2003-10-02","2005-01-13"]
[7820,32017,"   FS on Dynamic Policy control enhancements for end-to-end QoS","-",2,"Rel-6","S2","2002-07-15","2004-04-23",1,"SP-020540","-","Nortel","Claire Mousset","-","23.917 withdrawn (Contenall in 23.207)",null,null,null,null,"2002-01-24","2004-07-08"]
[7824,32705,"   Stage 1 of Subscriber certificates","-",2,"Rel-6","S3","2002-02-25","2002-09-12",1,"SP-010622","-","Nokia","valtteri.niemi@nokia.com","-","New (33.220, 33.221, 33.222, 33.246, 33.919)",null,null,null,null,"2002-09-26","2010-06-07"]
[7827,11049,"   Stage 3 Ua & Ub interfaces","-",2,"Rel-6","N1","2003-11-03","2004-12-08",1,"-","-","Nokia","-","-",24.109000000000002,null,null,null,null,"2004-03-01","2009-11-10"]
[7830,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[7834,15029,"   TS on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2002-10-31","2004-03-26",1,"-","-","-","-","N5#26: Split WI into TS & TR.","29.198-14",null,null,null,null,"2003-01-13","2005-01-13"]
[7838,60008,"   OMA potential overlaps with 3GPP OSA Stage 3 (Web services)","-",2,"Rel-6","OMA","2003-12-18","2004-09-16",1,"-","-","-","-","TSG#25 Approved CN5 29.199 Parlay X Web services. Ongoing 3GPP/OMA co-ordination to avoid OMA producing conflicting/OVERLAPING specs (NP-040283/SP-040493).","-",null,null,null,null,"2004-06-08","2005-03-25"]
[7839,15037,"   Deleted - TR on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2004-09-17","2004-09-17",1,"-","-","-","-","N5#26:TR Completion 09/04¦consistent with CN1 delayed Rel-6 completion.","-",null,null,"NP-24",null,"2004-10-20","2004-10-21"]
[7842,51102,"      Changes to core specs","-",3,"Rel-6","G1","2002-11-15","2002-12-20",1,"GP-022073","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2003-02-13"]
[7845,50130,"Seamless support of streaming services in A/Gb mode","SSStrea",1,"Rel-6","GP,S3","2000-01-03","2005-06-17",1,"GP-022561","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2004-01-14"]
[7849,51134,"      Performance of NACC","-",3,"Rel-6","G1","2000-01-03","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7852,52131,"   Reduction of service interruption times and packet loss during mobility procedures","-",2,"Rel-6","G2","2003-06-27","2005-06-17",1,"GP-022563","-","Vodafone","José Luis Carrizo Martínez","Completed at GERP#17","-",null,null,null,null,"2002-09-26","2003-09-16"]
[7855,52135,"      PS Handover (within GERAN and between GERAN and UTRAN)","-",3,"Rel-6","G2","2003-06-27","2005-06-17",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[7859,33013,"   GERAN A/Gb mode security enhancements","-",2,"Rel-6","S3","2002-09-26","2005-01-28",1,"SP-030107","-","Vodafone","peter.howard@vodafone.com","SP#19 approved WID",33.101999999999997,null,null,null,null,"2003-01-15","2011-08-08"]
[7863,35011,"   Principles, high level Requirements and Architecture","-",2,"Rel-6","S5","2002-09-12","2004-09-16",1,"SP-040767","-","Motorola","-","SP#25 09/2004 completed","32.101, 32.102",null,null,null,null,"2002-11-08","2006-01-13"]
[7864,35012,"   Performance Management","-",2,"Rel-6","S5","2002-09-12","2004-12-16",1,"SP-040782","-","Nortel","-","SP#26 12/2004 completed","32.401, 32.403, 52.402, 32.411, 32.412, 32.413, 32.432, 32.435, 32.436",null,null,null,null,"2002-11-08","2006-01-13"]
[7867,35022,"      Subscriber and UE trace management","-",3,"Rel-6","S5","2002-09-20","2004-12-16",1,"-","-","Nokia","kari.t.ronka@nokia.com","SP#26 12/2004 completed","32.421, 32.422, 32.423, 52.008",null,null,null,null,"2003-10-03","2006-01-13"]
[7870,35016,"Rel-6 Charging Management","CH",1,"Rel-6","S5,S2,N3","2002-11-21","2005-06-09",1,"SP-040773","-","T-Mobile","karl-heinz.nenner@t-mobile.de","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[7874,35026,"   Diameter charging applications","-",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.298999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[7877,35017,"   Charging Management for Bearer level","CH-BC",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"SP-030048","-","Nokia","Benni ALEXANDER ","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[7880,35031,"      CDR transfer","-",3,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.295000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[7885,13020,"      Gx interface for flow based charging","-",3,"Rel-6","N3","2004-02-02","2004-12-08",1,"NP-040245","-","Nokia","juha.a.rasanen@nokia.com","-",29.21,null,null,null,null,"2004-05-20","2005-03-09"]
[7888,1802,"   UICC API","USAT1-API",2,"Rel-6","T3","2002-03-20","2005-03-10",1,"-","-","-","-","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan","-",null,null,null,null,"2000-09-14","2001-03-12"]
[7889,43001,"      Rel-6 Java API Test specification","-",3,"Rel-6","T3","2002-03-20","2002-06-10",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-","-",null,null,null,null,"2002-05-30","2010-02-09"]
[7892,43003,"      Deleted - Java API Test specification (TS 43.019 Rel-5)","-",3,"Rel-6","T3","2002-05-30","2003-06-09",1,"TP-020122","-","Microelectrónica Española","Mario Pérez ","MOVED to Rel-5 WP","-",null,null,"TP-20",null,"2002-09-26","2010-02-09"]
[7895,502032,"         Specification of C SIM API","-",4,"Rel-6","T3","2000-09-25","2002-09-27",1,"TP-000155","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2000-04-09","2010-02-09"]
[7899,31039,"   Stage 1 for Packet Switched Streaming Services Rel-6","-",2,"Rel-6","S1","2002-11-18","2003-03-17",1,"SP-020685","-","Ericsson","-","2nd resp SA4",22.233000000000001,null,null,null,null,"2003-03-14","2009-11-13"]
[7901,34023,"AMR-WB extension for high audio quality","AMRWB+",1,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-030083","-","Nokia","janne.m.vainio@nokia.com","TR tbc by Sept. 05","26.290, 26.304, 26.273, 26.274, 26.412, 26.936",null,null,null,null,"2002-11-28","2006-01-13"]
[7907,32060,"Study on Bandwidth and resource savings in CS networks","BARS",1,"Rel-6","S2","2003-06-01","2004-06-16",1,"SP-030308","-","-","-","-",23.977,null,null,null,null,"2003-07-23","2004-07-08"]
[7910,50602,"      Multiple TBF Concept paper","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2003-09-16"]
[7913,50605,"   Deleted - Multiple TBF in A/Gb mode – MS testing","MULTBF-Testing",2,"Rel-6","G3new","2005-01-28","2005-01-28",1,"GP-022098","-","Ericsson","gunnar.mildh@era.ericsson.se","-","-",null,null,"GP-27",null,"2003-07-31","2005-03-09"]
[7914,50096,"Alignment between the test-regimes for GERAN capable MS","ALTERE",1,"Rel-6","G3new","2003-08-29","2005-09-02",0.99,"GP-032236","-","Ericsson","anthony.toubassi@sonyericsson.com ","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[7917,50445,"Addition of U-TDOA in the PS domain ","UTDOAPS",1,"Rel-6","GP","2003-06-27","2004-11-12",1,"GP-032774","-","TruePosition","Bob Gross, Rhys Robinson (rlgross@trueposition.com)","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7921,50104,"      Performance requirements in 45.005 for DARP for GMSK modulated voice services","DARP-GMSK-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7926,50115,"   DARP Capability signalling","DARP-CAPSIG",2,"Rel-6","GP","2003-11-21","2004-11-12",1,"GP-041970","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[7928,50109,"Reduction of PS service interruption in Dual Transfer Mode","PSintDTM",1,"Rel-6","G2","2003-11-21","2005-06-24",1,"GP-032548","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[7932,50113,"   Deleted - MS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfMS",2,"Rel-6","G3new","2004-06-25","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2008-12-12"]
[7935,31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[7938,32072,"   Deleted - Stage 2 description on Redial","-",2,"Rel-6","S2","2004-05-03","2004-12-16",1,"SP-040331","-","Vodafone","chris.pudney@vodafone.com","-","-",null,null,"SP-26",null,"2004-05-20","2005-03-09"]
[7939,11053,"   Switching between voice and video call - Redial solution","-",2,"Rel-6","N1","2005-01-03","2005-06-17",1,"SP-040331","-","Vodafone","-","-","23.009, 24.008",null,null,null,null,"2005-04-20","2005-06-02"]
[{"$f":"A7942+1","v":7942},13024,"Reorganisation of CS Data Specifications","CSData",1,"Rel-6","N3","2004-11-19","2004-12-08",1,"NP-040563","-","Siemens","Thomas.Belling@nsn.com","Created at TSG#27 as 100 % complete","23.910, 29.007, New 23.202",null,null,null,null,"2005-03-02","2005-03-09"]
[7947,50556,"   MS Conformance Test for GAAI","GAAI-CT",2,"Rel-6","GP","2004-08-27","2006-01-20",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)","-",null,null,null,null,"2004-10-15","2008-12-12"]
[7950,50561,"   PS handover for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-PSHO",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051162","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-PSH","-",null,null,null,null,"2005-04-20","2006-01-13"]
[7953,33021,"Study on Security for early IMS","SEC-IMS",1,"Rel-6","S3","2004-10-01","2005-03-28",1,"SP-040691","-","Vodafone","Peter.Howard@vodafone.com","SP#24 approved WID. SP#46 withdrawn TR 33.978 from Rel-8 onwards",33.978000000000002,null,null,null,null,"2003-07-25","2011-08-09"]
[7957,50563,"Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials","-",1,"Rel-6","GP,G2","2005-08-25","2005-09-02",1,"GP-041837","-","Siemens","kenneth.isaacs@roke.co.uk","GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials","44.018, 44.068, 48.008",null,null,"GP-26",null,"2005-04-20","2005-04-21"]
[7960,50502,"   Deleted - Stage 2","SCSAGB-Stage2",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030445","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[7963,50505,"   Deleted - replaced by 50561 - PS Handover","SCSAGB-PSH",2,"Rel-6","GP,N1","2003-11-24","2004-02-19",1,"GP-030448","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Started","-",null,null,"GP-18",null,"2003-02-13","2010-03-02"]
[7964,50506,"   Deleted SCSAGB-FLO - Modifications to FLO","-",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030449","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"RP-29",null,"2003-02-13","2010-03-02"]
[7968,2455,"Feasibility study on SS7 signalling transportation in the core network with SCCP-User Adaptation (SUA)","FS_SS7IP",1,"Rel-5","N4","2001-03-12","2001-12-21",1,"NP-010460","-","-","-","-",29.902999999999999,null,null,null,null,"2001-03-12","2001-12-12"]
[7972,2479,"   Iub/Iur protocol aspects - for High Speed Downlink Packet Access","HSDPA-IubIur",2,"Rel-5","R3","2001-04-02","2002-03-29",1,"RP-010262","-","Motorola","Mike Diesen","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[7975,25012,"   Conformance Testing of HCR TDD HSDPA","HSDPA_HCRTDD_Test",2,"Rel-5","R5","2006-03-10","2007-03-09",1,"-","-","IPWireless","drichards@ipwireless.com","-","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2010-06-16"]
[7978,1477,"      TDD Base station classification","RInImp-BSClass-TDD",3,"Rel-5","R4","2000-08-14","2002-03-08",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-07-26","2002-06-21"]
[7982,1221,"   FS on USTS","RInImp-USTS",2,"Rel-5","R1","2000-08-14","2001-12-21",1,"-","-","SK Telecom","D. Kim","-","-",null,null,null,null,"2000-04-26","2002-02-28"]
[7985,2493,"   FS on mitigating the effect of CPICH interference at the UE","RInImp-CPICH_Intf",2,"Rel-5","R4","2001-03-19","2002-03-08",1,"-","-","Intel","shimon.moshavi@INTEL.COM","-","-",null,null,null,null,"2001-03-27","2002-03-01"]
[7986,1839,"   Deleted - Conformance Test Spec. improvements in Radio Interface","-",2,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2001-10-11"]
[7989,500009,"Rel-5 RAN improvements","-",1,"Rel-5","RP","2001-03-16","2007-03-09",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2002-06-21"]
[7993,23002,"      FS Introduction of direct transport bearers between SRNC and Node-B","RAN-imp-RRMopt-DTB",3,"Rel-5","R3","2001-06-15","2002-06-04",1,"-","-","Ericsson","Risto Sepponen","FS was closed and introduction of WI not agreed at RAN #16 ","-",null,null,null,null,"2001-09-19","2002-11-08"]
[7997,2490,"   FS Improvement of Radio Resource Management across RNS and RNS/PSS","RANimp-ImpRRM",2,"Rel-5","R3","2001-03-16","2001-12-21",1,"-","-","Nokia","antti.toskala@nokia.com","FS was closed and WI was introduced at RAN #14 ","-",null,null,null,null,"2001-03-20","2002-11-08"]
[8000,25005,"   Testing of ROHC performance","RANimp-RABSE5_Test",2,"Rel-5","R5","2005-09-09","2007-03-09",1,"-","-","Nokia","jarkko.hellsten@nokia.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[8003,2472,"   Node B Synchronisation for 1.28 Mcps TDD","RANimp-NBSLCR",2,"Rel-5","R1","2001-03-16","2002-03-29",1,"-","-","CATT","Jinling HU","-","-",null,null,null,null,"2001-03-20","2002-03-25"]
[8007,23004,"UTRAN Sharing in Connected Mode","NETSHARE",1,"Rel-5","R3","2001-12-03","2002-09-03",1,"-","-","Ericsson ","Martin Israelsson","Formerly 'Shared Network support in connected mode', renamed at RAN #16.","-",null,null,null,null,"2002-03-21","2002-11-08"]
[8010,1633,"      Stage 1 for Call control and roaming to support IMS in UMTS","-",3,"Rel-5","S1","2000-02-21","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Issues include e.g.: Roaming requirements, Requirements on supplementary services, Interworking requirements",22.228000000000002,null,null,null,null,"2000-08-08","2001-03-30"]
[8014,1998,"         IMS signalling flows","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228000000000002,24.228000000000002,null,null,null,null,"2000-08-25","2003-03-14"]
[8015,1278,"         IMS stage 3","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228999999999999,24.228999999999999,null,null,null,null,"2000-04-19","2003-03-14"]
[8018,10004,"      Main IETF dependencies","-",3,"Rel-5","NP","2000-01-03","2002-06-14",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-01-25","2003-03-28"]
[8022,2524,"         IETF: RFC 3323 (SIP extensions for caller identity and privacy)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[8025,11001,"         IETF: RFC editor Queue (refer method)","-",4,"Rel-5","N1","2000-11-24","2002-06-07",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8028,11005,"         IETF: RFC 3266 (IPv6 support within SDP)","-",4,"Rel-5","N1","2000-01-03","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8032,1290,"         Addressing","-",4,"Rel-5","S2","2000-10-09","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2000-04-01"]
[8035,2530,"         Service Examples (Work stopped)","IMS-Sex",4,"Rel-5","S1","2001-04-17","2002-06-14",1,"-","-","Motorola","Mark Cataldo","-",22.928000000000001,null,null,null,null,"2001-05-28","2003-07-25"]
[8037,1298,"   Access Security for IMS","IMS-ASEC",2,"Rel-5","S3,T3","2001-10-08","2002-06-28",1,"SP-010323","-","Ericsson","krister.boman@emw.ericsson.se","-","-",null,null,null,null,"2000-04-18","2011-08-08"]
[8040,2574,"   Security Aspects of Requirement for Network Configuration Independence","SEC1-NCI",2,"Rel-5","S3","2001-07-02","2001-12-28",1,"SP-010324","-","AT&T Wireless","hugh.shieh@attws.com","Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C",33.203000000000003,null,null,null,null,"2001-06-09","2011-08-08"]
[8043,2036,"   Multimedia codecs and protocols for conversational PS services","IMS-CODEC",2,"Rel-5","S4","2000-07-26","2002-09-27",1,"SP-000398","-","Toshiba, Nokia","B. Aronson (Toshiba), pasi.s.ojala@nokia.com","-","26.235, 26.236",null,null,null,null,"2000-09-27","2003-03-27"]
[8047,11025,"      IETF: RFC 3310 (HTTP Digest Authentication using AKA)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8050,32004,"      Stage 2 for SIP message compression","-",3,"Rel-5","S2","2001-09-24","2001-10-26",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2001-11-24"]
[8054,14997,"      Mp interface (MRFC - MRFP) enhancements","-",3,"Rel-5","N4","2001-03-14","2002-03-08",1,"-","-","-","-","[DAB 08-03-02] - No work required in CN4","-",null,null,null,null,"2001-10-08","2002-05-30"]
[8057,14003,"      Dx interface (I-CSCF to SLF)","-",3,"Rel-5","N4","2001-03-14","2002-06-07",1,"-","-","-","-","CN4#11 30/11/01: No inputs received in CN4","-",null,null,null,null,"2001-10-08","2002-05-30"]
[8060,14006,"      Sh interface (HSS to AS)","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","CN4#11 30/11/01: No inputs received in CN4","-",null,null,null,null,"2001-10-11","2002-05-30"]
[8062,11020,"      Gm interface (UE to CSCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[8065,11029,"      Mk interface (BGCF to BGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[8068,12001,"      Stage2 work 'general'","-",3,"Rel-5","N2","2001-04-16","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2001-10-08","2003-01-13"]
[8072,14004,"      Deleted - SDM issues for CAMEL control of IMS","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"NP-17",null,"2001-10-08","2008-12-12"]
[8075,32006,"      Charging Implications of IMS architecture","-",3,"Rel-5","S2","2001-08-06","2001-11-16",1,"SP-010519","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-02-28"]
[8079,11011,"      IETF: draft-ietf-aaa-diameter - should be CN4","-",3,"Rel-5","NP","2000-11-24","2002-06-07",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)","-",null,null,null,null,"2001-10-08","2008-12-12"]
[8081,1844,"   Conformance Test Aspects - Provisioning of IMS","IMS-TEST",2,"Rel-5","T1","2002-03-18","2002-12-27",1,"-","-","-","-","The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008","-",null,null,null,null,"2000-09-14","2008-12-12"]
[8086,34002,"   Stage 1 for Extended Transparent End-to-End PS Streaming Service","-",2,"Rel-5","S1","2002-11-18","2003-03-17",1,"SP-010392","-","Vodafone","stephen.wolak@vodafone.com","2nd resp SA4",22.233000000000001,null,null,null,null,"2001-06-28","2002-03-25"]
[8087,31032,"      Interaction with other services","-",3,"Rel-5","S1","2002-11-18","2003-03-17",1,"-","-","Vodafone","stephen.wolak@vodafone.com","2nd resp SA4. Marked as closed 12/2008 (was marked 65% complete)",22.233000000000001,null,null,null,null,"2003-01-13","2008-12-12"]
[8090,501637,"Rel-5 Open Service Access (OSA) enhancements","OSA1",1,"Rel-5","S1,S3","1999-04-27","2002-12-20",1,"SP-000216","-","Siemens","joerg.swetina@neclab.eu","-","22.127, 23.127, 29.198-x, 29.998-x",null,null,null,null,"2000-08-08","2003-07-25"]
[8094,15002,"      Stages 2 and 3 for Multimedia Call Control","-",3,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-04",null,null,null,null,"2002-02-28","2002-06-21"]
[8097,15007,"   Call Control Service Mapping; Multiparty Call Control SIP - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.998-04-4",null,null,null,null,"2002-02-28","2002-06-21"]
[8100,2121,"      Stage 1 for OSA Security","-",3,"Rel-5","S1","2000-07-11","2001-11-09",1,"-","-","Siemens","Manfred.leitgeb@siemens.at","-",22.126999999999999,null,null,null,null,"2000-11-22","2002-02-28"]
[8102,1422,"      security related SCF(s) definition","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2002-06-21"]
[8108,15005,"   Policy Management - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-13",null,null,null,null,"2002-02-28","2002-09-26"]
[8111,1787,"      Stage 1 for LCS - OSA interfaces","-",3,"Rel-5","S1","2000-09-11","2000-12-08",1,"-","-","Siemens","joerg.swetina@neclab.eu","-",22.126999999999999,null,null,null,null,"2000-04-19","2002-05-30"]
[8112,2124,"      Stage 2 for LCS - OSA interfaces","-",3,"Rel-5","S2","2000-12-11","2000-12-11",1,"-","-","Ericsson","Christophe GOURRAUD","az 24/05/01: Rel4 completion 90->100%.",23.126999999999999,null,null,null,null,"2000-11-22","2001-06-06"]
[8115,1433,"   Retrieval of Terminal capabilities","OSA2-TC",2,"Rel-5","S2","2000-07-11","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2003-07-25"]
[8119,1638,"CAMEL phase 4","CAMEL4",1,"Rel-5","S1","2000-04-17","2002-09-06",1,"NP-020486","-","Nokia","keijo.palviainen@nokia.com","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[8122,2013,"   Mid call procedure for MO and MT calls ","CAMEL4-MCP",2,"Rel-5","N2","2000-07-17","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-05-30"]
[8127,2458,"   Provision of location information of called subscriber","CAMEL4-LOCB",2,"Rel-5","N2","2001-03-02","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-02-28"]
[8130,2516,"   GPRS Any Time Interrogation","CAMEL4-ATI",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[8133,2464,"Rel-5 MExE enhancements","MEXE5",1,"Rel-5","T2","2001-03-26","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-13"]
[8136,62,"   Specification ","-",2,"Rel-5","S4","2000-01-01","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2003-03-27"]
[8137,31005,"      Stage 1 for Wideband Telephony Service - AMR","-",3,"Rel-5","S1","2001-10-01","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-03-01"]
[8140,1460,"         General Description for Wideband Telephony Service - AMR","-",4,"Rel-5","S4","2000-02-07","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[8144,67,"      Codec issues","-",3,"Rel-5","S4","2000-01-03","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[8148,34007,"         TFO AMR-WB","AMRWB-TFO",4,"Rel-5","S4","2001-12-18","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-09-26"]
[8151,34009,"         Interworking with fixed broadband networks","-",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[8155,76,"         Terminal Acoustic Characteristics ","-",4,"Rel-5","S4","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2000-04-01"]
[8158,34004,"   Floating-point ANSI-C code for the AMR-WB speech codec","AMRWB-FP",2,"Rel-5","S4","2001-09-25","2002-03-14",1,"SP-010459","-","Nokia","janne.m.vainio@nokia.com","-",26.204000000000001,null,null,null,null,"2001-10-08","2002-02-28"]
[8159,80,"   Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR","GAMRWB",2,"Rel-5","GP","2000-01-03","2002-06-28",1,"GP-000453","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-07-31"]
[8162,2267,"      Signalling for Iu","-",3,"Rel-5","GP","2000-01-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8165,2269,"   Deleted - GERAN MS conformance test for AMR-WB","-",2,"Rel-5","GP","2000-01-03","2003-12-19",1,"GP-000454","-","-","-","Not started 02/2003. Marked as stopped 12/2008","-",null,null,"SP-69",null,"2001-02-01","2008-12-12"]
[8169,2573,"   Terminal local model enhancements","TLM5",2,"Rel-5","T2","2001-05-14","2002-03-20",1,"TP-010224","-","-","-","-",23.227,null,null,null,null,"2000-09-14","2003-03-27"]
[8173,2125,"      Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning","LCS-INTF",3,"Rel-5","R2","2001-01-15","2001-10-12",1,"RP-010414","-","Qualcomm","Kirk Burroughs","RP#13 completed","-",null,null,null,null,"2000-11-27","2002-01-24"]
[8176,1538,"      Stage 2 for Event based and Periodic LCS","-",3,"Rel-5","S2","2000-11-06","2001-01-26",1,"-","-","-","-","Marked as closed 12/2008 (was marked 51% complete)","-",null,null,null,null,"2000-07-28","2008-12-12"]
[8180,2438,"      Gb interface support for LCS","-",3,"Rel-5","GP","2000-04-03","2001-08-31",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8183,2442,"   Location Services for GERAN in Iu Mode","-",2,"Rel-5","S2,G1,G2,R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8184,2443,"      GERAN LCS Stage 2","-",3,"Rel-5","S2,G1,G2","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8187,2446,"      Iur-g interface support for LCS","-",3,"Rel-5","G1,G2","2002-01-23","2002-04-19",1,"GP-011926","-","Nokia","Margaret Livingston","FFS","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8190,2449,"      Stage 3 for Location Services for GERAN in Iu Mode","-",3,"Rel-5","G1,G2,R2,R3","2002-03-25","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8195,55071,"      Deleted - LCS BTS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2008-12-12"]
[{"$f":"A8198+1","v":8198},2434,"   LCS interoperability aspects to GERAN (LCS-GERAN)","-",2,"Rel-5","GP,S5","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[8202,521,"   New security aspects of LCS","LCS1-SEC",2,"Rel-5","S3,S2","2000-04-14","2001-12-28",1,"SP-000421","-","Nokia","valtteri.niemi@nokia.com","SP#9 updated WID S3-000609 (Location services security)","23.271, 43.059",null,null,null,null,"2000-04-19","2012-05-21"]
[8205,501571,"Rel-5 Security enhancements (SEC1)","-",1,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","Added BB UE authentication and rapporteur added. TO BE DELETED","-",null,null,null,null,"2000-04-09","2011-08-08"]
[8208,1577,"      Deleted - Control plane protection in core network (e.g., GTP, CAP, MAP/IP, provided by IPsec) ","-",3,"Rel-5","S3","2000-05-12","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-04-18","2008-12-12"]
[8209,1578,"         Deleted - Main aspects of User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","S3","2000-05-12","2001-06-21",1,"-","-","-","-","TO BE DELETED. Marked as stopped 12/2008","-",null,null,"SP-12",null,"2000-04-09","2008-12-12"]
[8215,2244,"   Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","S2","2001-01-03","2001-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2000-12-13","2001-09-19"]
[8216,20000,"   Stage 3: RAN node selecting CN node","-",2,"Rel-5","R3","2001-09-24","2002-03-22",1,"-","-","Vodafone","Brendan.McWilliams@gb.vodafone.co.uk","Not identified","-",null,null,null,null,"2001-09-19","2002-03-01"]
[8220,51068,"      Stage 2 (changes to )","-",3,"Rel-5","G1","2002-02-08","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8223,52077,"      48.016 Use of Gb interface concepts when a network applies IDNNS","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","Closed, accept changes for Gb over IP","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8227,2322,"      Deleted - Definition of a new A/Ater interface Transport Layer option based on the Iu Interface Transport Layer","-",3,"Rel-5","GP","2001-04-06","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8230,35002,"   Rel-5 Principles, high level Requirements and Architecture","-",2,"Rel-5","S5","2001-09-17","2002-06-28",1,"SP-010461","-","Motorola","-","-","32.101, 32.102",null,null,null,null,"2000-04-26","2002-06-21"]
[8233,35001,"   Rel-5 Network Infrastructure Management ","-",2,"Rel-5","S5","2001-09-21","2002-09-12",1,"SP-010461","-","Ericsson","thomas.tovinger@ericsson.com","-","32.6xy, 32.3xy",null,null,null,null,"2001-10-08","2002-11-08"]
[8236,2395,"   RLC protocol enhancement (SDU Discard)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8238,2398,"   Usage of ECSD Concept","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8241,2401,"   RLC PDU formats","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8245,2414,"      Identification of GERAN requirements on Iu ps","-",3,"Rel-5","GP,R3","2000-09-01","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-05-21"]
[8248,2417,"   Evolution of Iu cs","GERUEV2-IuCS",2,"Rel-5","GP,R3","2000-06-29","2002-06-28",1,"GP-000430","-","Lucent","Krishna Balachandran","Lucent, Ericsson, AWS, Nortel","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8252,2557,"   E2E QoSConcept and Architecture","-",2,"Rel-5","S2","2001-01-03","2001-09-07",1,"-","-","-","-","-",23.207000000000001,null,null,null,null,"2001-06-08","2001-11-24"]
[8255,2569,"Rel-5 Messaging enhancements","MESS5",1,"Rel-5","T2","2001-06-15","2003-03-31",1,"-","-","-","-","support of UAProf, so this in my opinion is 100% complete","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8257,31000,"      Definition of service requirements for MESS5-MMS","MESS5-SR",3,"Rel-5","S1","2001-06-15","2002-03-15",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",22.14,null,null,null,null,"2001-07-04","2003-07-25"]
[8260,34018,"      MMS formats and codecs for MESS5-MMS","-",3,"Rel-5","S4","2001-12-03","2002-03-15",1,"-","-","-","-","-",26.14,null,null,null,null,"2002-01-24","2002-02-28"]
[8263,42001,"      Technical realization of Enhanced Messaging Service (EMS) enhancements","-",3,"Rel-5","T2","2001-06-15","2002-03-08",1,"-","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-",23.04,null,null,null,null,"2001-07-04","2002-02-28"]
[8267,14502,"      Stage 2 - 23.060 change - Definition of Inter BSC NACC","-",3,"Rel-5","N4,S2","2001-09-03","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8270,50003,"      Stage 3 (changes to TS 48.018)","-",3,"Rel-5","GP","2001-11-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8273,50035,"   Deleted - GERAN MS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012750","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[8277,50061,"      Concept","-",3,"Rel-5","GP","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8278,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8282,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8283,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8284,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8285,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[8286,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[8287,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[8288,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8289,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[8290,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[8291,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[8292,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[8293,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[8294,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[8295,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[8296,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8297,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[8298,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[8299,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[8300,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[8301,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8302,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8303,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8304,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8305,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[8306,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8307,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8308,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8309,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8310,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8311,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8312,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8313,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8314,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8315,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8316,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8317,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8318,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8319,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8320,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8321,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8322,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8323,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8324,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8325,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[{"$f":"A8326+1","v":8326},50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8327,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8328,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8329,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8330,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8331,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8332,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8333,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8334,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8335,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8336,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8337,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8338,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8339,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8340,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8341,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8342,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8343,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8344,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8345,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8346,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8347,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8348,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8349,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8350,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8351,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8352,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8353,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8354,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8355,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8356,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8357,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8358,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8359,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8360,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8361,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8362,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8363,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8364,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8365,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8366,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8367,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8368,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8369,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8370,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8371,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8372,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8373,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8374,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8375,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8376,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8377,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8378,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8379,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8380,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8381,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8382,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[8383,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[8384,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8385,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8386,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8387,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8388,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8389,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[{"$f":"A8390+1","v":8390},1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8391,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8392,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8393,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8394,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8395,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8396,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8397,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8398,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8399,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8400,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8401,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8402,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8403,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8404,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[8405,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8406,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8407,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8408,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8409,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8410,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8411,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8412,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8413,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8414,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8415,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8416,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8417,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8418,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8419,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8420,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8421,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8422,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8423,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8424,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8425,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8426,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8427,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8428,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8429,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8430,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8431,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8432,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8433,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8434,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8435,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8436,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8437,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8438,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8439,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8440,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8441,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8442,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8443,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8444,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8445,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8446,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[8447,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8448,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8449,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8450,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8451,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8452,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8453,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[{"$f":"A8454+1","v":8454},1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8455,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8456,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8457,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8458,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8459,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8460,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8461,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8462,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8463,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8464,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8465,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8466,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8467,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8468,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[8469,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8470,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8471,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8472,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8473,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8474,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8475,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8476,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8477,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8478,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8479,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8480,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8481,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8482,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8483,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8484,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8485,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8486,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8487,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8488,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8489,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8490,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8491,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8492,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8493,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8494,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8495,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8496,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8497,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8498,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8499,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8500,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8501,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8502,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8503,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8504,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8505,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8506,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8507,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8508,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8509,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8510,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[8511,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[8512,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[8513,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8514,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[8515,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8516,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[8517,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[{"$f":"A8518+1","v":8518},1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8519,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[8520,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[8521,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8522,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8523,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8524,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8525,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8526,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8527,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8528,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8529,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8530,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[8531,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8532,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[8533,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[8534,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[8535,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[8536,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[8537,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8538,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[8539,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[8540,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[8541,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[8542,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[8543,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[8544,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8545,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8546,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[8547,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[8548,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[8549,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[8550,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[8551,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8552,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[8553,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8554,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8555,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8556,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[8557,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[8558,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[8559,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8560,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8561,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[8562,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[8563,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[8564,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8565,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[8566,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8567,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[8568,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8569,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[8570,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8571,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8572,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[8573,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[8574,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[8575,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8576,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[8577,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[8578,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8579,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[8580,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[8581,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[{"$f":"A8582+1","v":8582},2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[8583,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[8584,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[8585,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[8586,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[8587,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[8588,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[8589,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[8590,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[8591,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[8592,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[8593,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[8594,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[8595,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8596,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[8597,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8598,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8599,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[8600,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[8601,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[8602,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[8603,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[8604,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8605,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[8606,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8607,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[8608,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[8609,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8610,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8611,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[8612,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[8613,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[8614,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[8615,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[8616,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[8617,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[8618,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[8619,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8620,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8621,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[8622,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8623,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8624,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[8625,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[8626,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8627,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8628,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[8629,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8630,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8631,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8632,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8633,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8634,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8635,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[8636,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[8637,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8638,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8639,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8640,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[8641,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[8642,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[8643,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8644,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[8645,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[{"$f":"A8646+1","v":8646},60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[8647,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[8648,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8649,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[8650,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[8651,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8652,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8653,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[8654,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[8655,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[8656,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[8657,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[8658,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[8659,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[8660,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8661,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8662,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[8663,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[8664,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8665,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[8666,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[8667,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[8668,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[8669,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[8670,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[8671,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[8672,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[8673,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[8674,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[8675,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8676,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8677,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8678,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[8679,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[8680,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[8681,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8682,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8683,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[8684,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[8685,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8686,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[8687,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8688,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[8689,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[8690,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[8691,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8692,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[8693,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8694,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[8695,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[8696,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[8697,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[8698,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[8699,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[8700,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[8701,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[8702,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8703,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8704,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8705,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8706,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[8707,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8708,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8709,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A8710+1","v":8710},60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[8711,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[8712,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[8713,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[8714,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[8715,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8716,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[8717,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[8718,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[8719,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8720,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8721,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8722,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8723,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[8724,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8725,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[8726,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8727,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[8728,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[8729,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8730,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8731,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[8732,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8733,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8734,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8735,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8736,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8737,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[8738,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[8739,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[8740,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[8741,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8742,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[8743,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[8744,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[8745,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8746,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[8747,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8748,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8749,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[8750,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[8751,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[8752,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[8753,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8754,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[8755,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[8756,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8757,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[8758,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8759,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8760,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[8761,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[8762,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8763,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[8764,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[8765,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[8766,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[8767,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[8768,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[8769,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8770,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[8771,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[8772,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[8773,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[{"$f":"A8774+1","v":8774},60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[8775,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[8776,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[8777,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[8778,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[8779,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[8780,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[8781,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]