{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp","index":0,"n_rows":9065,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version January 8th 2025",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[2,0,"Temporary Post TSG#106 version - includes WIDs approved at SA and CT#106 BUT NOT YET FROM RAN#106",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[3,0,"Next key milestones: Rel-19 St.3: Sept.25",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 20 ---","-",1,"Rel-20",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[6,1050110,"Study on 6G Use Cases and Service Requirements ","FS_6G-REQ",1,"Rel-20","S1","2024-09-04","2025-03-03",0,"SP-241391",null,"Xiaonan Shi, China Mobile","shixiaonan@chinamobile.com",null,null,105,53,null,null,"2024-09-04","NA"]
[{"$f":"A7+1","v":7},1030042,"Study on satellite access - Phase 4 ","FS_5GSAT_Ph4",1,"Rel-20","S1","2024-04-02","2025-03-03",0.6,"SP-241824",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","13/6/24: 0%->30; 4/9/24: 30%->60; 8/1/25: WID:SP-240495->SP-241824",22.887,103,52,null,null,"2024-03-13","2025-01-08"]
[{"$f":"A8+1","v":8},1060071,"Satellite access - Phase 4 ","5GSAT_Ph4",1,"Rel-20","S1","2024-12-05","2025-03-03",0,"SP-241822",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ",null,22.260999999999999,null,null,null,null,"2024-12-05","NA"]
[9,1030043,"Study on FRMCS Phase 6 ","FS_FRMCS_Ph6",1,"Rel-20","S1","2024-03-13","2025-03-03",0.4,"SP-241392",null,"Nikolopoulou, Vassiliki, UIC, ","nikolopoulou@uic.org ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 26/9/24: WID:SP-240199->SP-241392; 26/9/24: FCD:09/09/2024->/25",22.989000000000001,103,52,null,null,"2024-03-13","2024-09-26"]
[10,1030044,"Study on Energy Efficiency as Service Criteria Phase 2 ","FS_EnergyServ_Ph2",1,"Rel-20","S1","2024-04-02","2025-03-03",0.55000000000000004,"SP-240494",null,"Laurent-WalterGoix, Nokia ","laurent-walter.goix@NOKIA.COM ","13/6/24: 0%->25; 4/9/24: 25%->55",22.882999999999999,103,52,null,null,"2024-03-13","2024-09-04"]
[11,1050105,"Indirect Network Sharing on Satellite Access Network ","INS_SAT",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241393",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[12,1050106,"Indirect Network Sharing Phase 2 ","NetShare_Ph2",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241147",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[13,1050107,"Resident Phase 2 ","Resident_Ph2",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241149",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[14,1050108,"Combined QoS configuration and monitoring ","CombQoS",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241150",null,"Yansheng Liu, ZTE ","liu.yansheng@zte.com.cn ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[15,1050109,"Legacy Residential Gateway Supporting 5G LAN-type Service ","LegacyRG_5GLAN",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241151",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[16,1050111,"Exposure for Virtual Network information and capability ","VNExposure",1,"Rel-20","S1","2024-09-04","2024-09-09",1,"SP-241153",null,"Pengtai Qin, China Mobile ","qinpengtai@chinamobile.com ",null,22.260999999999999,105,53,null,null,"2024-09-04","NA"]
[17,1060070,"Vehicle-Mounted Relays Phase3 ","VMR_Ph3",1,"Rel-20","S1","2024-12-05","2024-12-12",1,"SP-241821",null,"Qing Wan, CATT, ","wanqing1@cictmobile.com ","; 5/12/24: 0%->100",22.260999999999999,null,null,null,null,"2024-12-05","2024-12-05"]
[18,1060072,"MPS support in 3GPP system with satellite ","MPS_Sat",1,"Rel-20","S1","2024-12-05","2024-12-12",1,"SP-241823",null,"Singh, Ray, Peraton Labs, ","rsingh@peratonlabs.com ","; 5/12/24: 0%->100",22.152999999999999,null,null,null,null,"2024-12-05","2024-12-05"]
[19,1040011,"Lawful Interception Rel-20 ","LI20",1,"Rel-20","S3LI","2024-06-12","2027-03-03",0,"SP-241012",null,"Koen Jaspers, PIDS, ","k.b.jaspers@minjenv.nl ",null,"33.107; 33.108; 33.126; 33.127; 33.128; 33.928 ",104,53,null,null,"2024-06-12","NA"]
[20,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[21,0,"Rel-19 Energy Efficiency, Energy Saving","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[22,1020060,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19",null,"2022-06-02","2025-09-09",0.77,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[23,960019,"   Study on Energy Efficiency as service criteria ","FS_EnergyServ",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.882000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[24,1000033,"   Stage 1 of Energy Efficiency as Service Criteria ","EnergyServ",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[25,1040018,"   Charging Aspects for Energy Efficiency of 5G ","EnergySys_CH",2,"Rel-19","S5","2024-06-12","2025-06-06",0.45,"SP-241003",null,"YiMeng, DENG, Huawei, ","dengyimeng@huawei.com ","; 4/9/24: 0%->45","32.240; 28.201; 28.202; 32.291; 32.298 ",104,53,null,null,"2024-06-12","2024-09-04"]
[26,1010029,"   Study on Energy Efficiency and Energy Saving","FS_EnergySys",2,"Rel-19","S2","2023-09-09","2024-06-06",1,"SP-231391",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","SP-231192; 23.700-66; 28.880",101,51,null,null,"2023-09-20","2024-09-04"]
[27,1050112,"   (WA) Energy Efficiency and Energy Saving ","EnergySys",2,"Rel-19","S2","2024-09-04","2024-12-12",0.7,"SP-241388",null,"Primary Rapporteur: Jungshin Park (Samsung) ","shin02.park@samsung.com ","; 5/12/24: 0%->70","23.501; 23.502; 23.503 ",105,53,null,null,"2024-09-04","2024-12-05"]
[28,1020021,"   Study on energy efficiency and energy saving aspects of 5G networks and services ","FS_Energy_OAM_Ph3",2,"Rel-19","S5","2023-12-08","2024-12-12",1,"SP-241568",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com","4/1/24: 28.866 added;; 14/3/24: 0%->10; 13/6/24: 10%->25; 4/9/24: 25%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-231723->SP-241568",28.866,102,52,null,null,"2023-12-07","2025-01-08"]
[29,1030038,"   Study on security aspects of energy saving in 5G ","FS_Energy_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.9,"SP-240512",null,"Bo Bjerrum ","bo.bjerrum@nokia.com ","3/4/24: 33.766 added;; 13/6/24: 0%->30; 5/9/24: 30%->70; 5/12/24: 70%->90",33.765999999999998,103,52,null,null,"2024-03-14","2024-12-05"]
[30,1060007,"   Energy efficiency and energy saving aspects of 5G networks and services ","Energy_OAM_Ph3",2,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241940",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com ",null,"28.310; 28.622; 28.623; 28.541; 28.554; 28.104 ",null,null,null,null,"2024-12-05","NA"]
[31,1020095,"Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh",1,"Rel-19",null,"2023-12-13","2025-03-03",0.26,"RP-242354",null,"Ericsson ",null,"2/4/24: WID:RP-234065->RP-240170; 23/7/24: WID:RP-240170->RP-241650; 26/9/24: WID:RP-241650->RP-242354",null,102,52,null,null,"2024-01-02","2024-09-26"]
[32,1021095,"   Core part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.6,"RP-242354","RP-242498","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->35%; Stat Re",null,102,52,null,null,"2024-01-02","2024-12-06"]
[33,1022095,"   Perf. part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-242354","RP-242498","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241182->RP-241866; ; 6/12/24: FCD:03/03",null,102,52,null,null,"2024-01-02","2024-12-06"]
[34,1030004,"Study on Media enerGy consumption exposuRE and EvaluatioN framework ","FS_MediaEnergyGREEN",1,"Rel-19","S4","2024-04-02","2025-03-03",0.6,"SP-240481",null,"Julien Lemotheux, Orange, ","julien.lemotheux@orange.com ","14/5/24: 26.942 added;; 13/6/24: 0%->15; 4/9/24: 15%->30; 5/12/24: 30%->60",26.942,103,52,null,null,"2024-03-13","2024-12-05"]
[35,1020094,"Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS",1,"Rel-19",null,"2023-12-13","2025-03-03",0.24,"RP-241824",null,"vivo ",null,"2/4/24: WID:RP-234056->RP-240801; 26/9/24: WID:RP-240801->RP-241824; 26/9/24: 38.774 added;",38.774000000000001,102,52,null,null,"2024-01-02","2024-09-26"]
[36,1021094,"   Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.55000000000000004,"RP-240801","RP-242619","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Compl:8%->20%; Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->30%; Stat Rep: RP-241039->RP-24",null,102,52,null,null,"2024-01-02","2024-12-06"]
[37,1022094,"   Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240801","RP-242619","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241039->RP-241822; ; 6/12/24: FCD:03/03/2025->03/03/2026; ",null,102,52,null,null,"2024-01-02","2024-12-06"]
[38,0,"Rel-19 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[39,1040084,"Study on 3GPP AI/ML Consistency Alignment","FS_AIML_CAL",1,"Rel-19","SP","2024-06-20","2025-06-06",0,"SP-241368",null,"Johannes Achter, Magenta",null,"26/9/24: WID:SP-240970->SP-241368",null,104,53,null,null,"2024-06-20","2024-09-26"]
[40,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95","22.875; 22.876",95,48,null,null,"2022-03-10","2023-09-06"]
[41,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-19","S4","2022-03-12","2025-06-06",0.82,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50; 14/3/24: 50%->60; 14/...","26.927; 26.847",95,48,null,null,"2022-03-10","2024-12-05"]
[42,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80; 8/12/23: 80%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[43,1050047,"Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",1,"Rel-19","S2","2024-06-12","2025-09-09",0.39,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ",null,"23.288; 23.501; 23.502; 23.503; 23.273 ",105,53,null,null,"2024-06-12","NA"]
[44,1040033,"   Stage 2 of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19","S2","2024-06-12","2024-12-12",0.85,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ","; 4/9/24: 0%->15; 5/12/24: 15%->85","23.288; 23.501; 23.502; 23.503; 23.273 ",104,53,null,null,"2024-06-12","2024-12-05"]
[45,1050014,"   CT aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19","C3","2024-09-09","2025-09-09",0.38,"CP-242247",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,null,105,53,null,null,"2024-06-12","NA"]
[46,1050048,"      CT3 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C3","2024-09-09","2025-09-09",0.25,"CP-242247",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,null,105,53,null,null,"2024-06-12","NA"]
[47,1050049,"      CT4 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C4","2024-09-09","2025-09-09",0.5,"CP-242247",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,null,105,53,null,null,"2024-06-12","NA"]
[48,1060059,"   Security aspects of Core Network Enhanced Support for AIML ","AIML_CN_SEC",2,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241957",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ",null,33.500999999999998,null,null,null,null,"2024-12-05","NA"]
[49,1050044,"Application enablement for AI/ML services ","AIML_App",1,"Rel-19","S6","2024-07-16","2025-09-09",0.27,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ",null,"23.436; 23.434; 23.558 ",105,53,null,null,"2024-06-12","NA"]
[50,1040075,"   Stage 2 of Application enablement for AI/ML services ","AIML_App",2,"Rel-19","S6","2024-07-16","2024-12-12",1,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ","; 4/9/24: 0%->40; 26/9/24: 23.482 added;; 5/12/24: 40%->100","23.436; 23.434; 23.558 ; 23.482",104,53,null,null,"2024-06-12","2024-12-05"]
[51,1050024,"   CT aspects of Application enablement for AI/ML services ","AIML_App",2,"Rel-19","C1","2024-09-09","2025-09-09",0.12,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,"24.559, 29.549, 29.558, 24.559, 29.549, 29.558",105,53,null,"x","2024-06-12","NA"]
[52,1050045,"      CT1 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C1","2024-09-09","2025-09-09",0.2,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com","; 26/9/24: 24.560 added;",null,105,53,null,"x","2024-06-12","2024-09-26"]
[53,1050046,"      CT3 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C3","2024-09-09","2025-09-09",0.05,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,null,105,53,null,"x","2024-06-12","NA"]
[54,1060011,"AI/ML management phase 2 ","AIML_MGT_Ph2",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241944",null,"Hassan Al-Kanani (NEC)","Hassan.Alkanani@EMEA.NEC.COM",null,"28.105; 28.552; 28.554; 28.541 ",null,null,null,null,"2024-12-05","NA"]
[55,1020068,"Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","FS_AIML_CN",1,"Rel-19","S2","2024-01-04","2024-06-06",1,"SP-241936",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com) ","14/3/24: 0%->25; 13/6/24: 25%->100; 26/9/24: WID:SP-231800->SP-241383; 8/1/25: WID:SP-241383->SP-241936",null,102,52,null,null,"2024-01-03","2025-01-08"]
[56,1030035,"Study on security aspects of Core Network Enhanced Support for AIML ","FS_AIML_CN_SEC",1,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240509",null,"Chang Liu, ","liuchangyjy@chinamobile.com ","3/4/24: 33.784 added;; 13/6/24: 0%->35; 5/9/24: 35%->60; 5/12/24: 60%->100",33.783999999999999,103,52,null,null,"2024-03-14","2024-12-05"]
[57,1020007,"Study on AI/ML management - phase 2 ","FS_AIML_MGT_Ph2",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-241567",null,"Yizhi Yao (Intel) ","yizhi.yao@intel.com ","13/6/24: 0%->19; 16/7/24: WID:SP-231780->SP-240965; 4/9/24: 19%->55; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: 28.858 added;; 5/12/24: 55%->100; 8/1/25: WID:SP-240965->SP-241567",28.858000000000001,102,52,null,null,"2023-12-07","2025-01-08"]
[58,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","2023-09-07","2024-09-09",1,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","8/12/23: 0%->35; 4/1/24: 23.700-82 added;; 14/3/24: 35%->55; 13/6/24: 55%->95; 4/9/24: 95%->100","23.700-82",101,51,null,null,"2023-09-07","2024-09-04"]
[59,1020083,"Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","FS_NR_AIML_NGRAN_enh",1,"Rel-19","R3","2023-12-13","2024-09-24",1,"RP-240323","RP-241791","ZTE ",null,"14/3/24: FCD:06/06/2024->/24; 2/4/24: WID:RP-234054->RP-240323; 3/4/24: 38.743 added;; 13/6/24: Compl:0%->80%; Stat Rep: ->RP-241097; ; 4/9/24: FCD:09/09/2024->24/09/2024; Compl:80%->100%; Stat Rep: RP-241097->RP-241791; ",38.743000000000002,102,52,null,null,"2024-01-02","2024-09-04"]
[60,1020084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR ","FS_NR_AIML_Mob",1,"Rel-19","R2","2019-03-07","2025-09-09",0.5,"RP-242393","RP-242797","Zhongda Du, OPPO","duzhongda@oppo.com","14/3/24: FCD:28/05/2021->12/12/2024; Stat Rep: ->RP-240083; Rapporteur: Oppo->Zhongda Du, OPPO; Rap eMail: ->duzhongda@oppo.com; ; 2/4/24: WID:RP-234055->RP-240082; 3/4/24: 38.744 added;; 4/9/24: FCD:12/12/2024->25/09/2024; Compl:0%->38%; Stat Rep: RP-...",38.744,102,52,null,null,"2024-01-02","2024-12-06"]
[61,1020093,"Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air",1,"Rel-19",null,"2023-12-13","2025-03-03",0.24,"RP-242399",null,"Qualcomm ",null,"2/4/24: WID:RP-234039->RP-240774; 26/9/24: WID:RP-240774->RP-242399",null,102,52,null,null,"2024-01-02","2024-09-26"]
[62,1021093,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.55000000000000004,"RP-242399","RP-242559","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsso...",null,102,52,null,null,"2024-01-02","2024-12-06"]
[63,1022093,"   Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-242399","RP-242559","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com; ; 13/6/...",null,102,52,null,null,"2024-01-02","2024-12-06"]
[64,1050124,"Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh",1,"Rel-19","R3","2024-09-09","2025-09-09",0.3,"RP-242385",null,"ZTE ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[65,1051124,"   Core part: Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh-Core",2,"Rel-19","R3","2024-09-09","2025-09-09",0.3,"RP-242385","RP-242503","ZTE ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-242503; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[66,0,"Rel-19 Ambient power-enabled Internet of Things ","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[67,1020055,"Ambient power-enabled Internet of Things ","AmbientIoT",1,"Rel-19",null,"2022-03-10","2024-12-12",0.96,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[68,950004,"   Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.84,95,48,null,null,"2022-03-10","2023-12-08"]
[69,1020071,"   Study on Architecture support of Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S2","2024-01-04","2024-12-12",0.9,"SP-240969",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","14/3/24: 0%->25; 13/6/24: 25%->65; 16/7/24: WID:SP-231803->SP-240969; 4/9/24: 65%->80; 5/12/24: 80%->90",null,102,52,null,null,"2024-01-03","2024-12-05"]
[70,1020030,"   Stage 1 of Ambient power-enabled Internet of Things ","AmbientIoT",2,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[71,1020085,"Study on solutions for Ambient IoT (Internet of Things) in NR ","FS_Ambient_IoT_solutions",1,"Rel-19","R1","2023-12-13","2024-12-12",0.99,"RP-240826","RP-242965","Xiaodong Shen, CMCC","shenxiaodong@chinamobile.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240155; Rapporteur: CMCC->Xiaodong Shen, CMCC; Rap eMail: ->shenxiaodong@chinamobile.com; ; 2/4/24: WID:RP-234058->RP-240826; 3/4/24: 38.769 added;; 13/6/24: Compl:8%->40%; Stat Rep: RP-240155->RP-241206; ; 4/9/24: FC",38.768999999999998,102,52,null,null,"2024-01-02","2024-12-06"]
[{"$f":"A72+1","v":72},1030031,"Study on Security Aspect of Ambient IoT Services in 5G ","FS_Ambient_IoT_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",0.55000000000000004,"SP-240506",null,"Marcus Wong, ","marcus.wong@oppo.com ","3/4/24: 33.713 added;; 13/6/24: 0%->30; 5/9/24: 30%->35; 5/12/24: 35%->55",33.713000000000001,103,52,null,null,"2024-03-14","2024-12-05"]
[73,0,"See also IoT_NTN_Ph3 under Satellite/NTN ","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[74,0,"Rel-19 Internet of Things, RedCap, MTC","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[75,1040133,"NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE",1,"Rel-19","R4","2024-06-06","2025-06-06",0.5,"RP-241997",null,"China Telecom ",null,"26/9/24: WID:RP-241665->RP-241997",null,104,53,null,null,"2024-07-23","2024-09-26"]
[76,1041133,"   Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE-Core",2,"Rel-19","R4","2024-06-06","2025-06-06",0.5,"RP-241997","RP-242859","China Telecom ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241998; ; 6/12/24: Compl:20%->50%; Stat Rep: RP-241998->RP-242859; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[77,1050123,"Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD",1,"Rel-19","R1","2024-09-09","2026-03-03",0.08,"RP-242415",null,"Iridium ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[78,1051123,"   Core part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Core",2,"Rel-19","R1","2024-09-09","2025-09-09",0.2,"RP-242415","RP-242652","Iridium ",null,"6/12/24: Compl:0%->20%; Stat Rep: ->RP-242652; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[79,1052123,"   Perf. part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Perf",2,"Rel-19","R4","2024-09-09","2026-03-03",0,"RP-242415","RP-242652","Iridium ",null,"6/12/24: Stat Rep: ->RP-242652; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[80,1060008,"Management Aspects of RedCap features ","NR_RedCap_OAM",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241941",null,"Zhen Xing (China Unicom)","xingz12@chinaunicom.cn ",null,"28.540; 28.541; 28.552; 28.554 ",null,null,null,null,"2024-12-05","NA"]
[81,0,"Rel-19 Satellite (5GSAT), NTN","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[82,1020058,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19",null,"2022-06-02","2025-09-09",0.48,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[83,960016,"   Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[84,1000024,"   Stage 1 of Satellite access Phase 3 ","5GSAT_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-12-08"]
[85,1010033,"   Study on Integration of satellite components in the 5G architecture Phase 3","FS_5GSAT_Ph3_ARCH",2,"Rel-19","S2","2023-09-20","2024-06-06",1,"SP-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","23.700-29; 28.874",101,51,null,null,"2023-09-20","2024-09-04"]
[86,1020053,"   Study on application enablement for Satellite access enabled 5G Services ","FS_5GSAT_Ph3_App",2,"Rel-19","S6","2024-01-03","2024-09-09",1,"SP-240296",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","8/12/23: 0%->5; 14/3/24: 0%->25; 2/4/24: WID:SP-231738->SP-240296; 3/4/24: 23.700-01 added;; 13/6/24: 25%->60; 4/9/24: 60%->100","23.700-01",102,52,null,null,"2023-12-07","2024-09-04"]
[87,1040027,"   Integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3-ARC",2,"Rel-19","S2","2024-06-12","2024-12-12",0.65,"SP-241386",null,"Hucheng Wang (CATT) ","wanghucheng@catt.cn","4/9/24: 0%->15; 26/9/24: WID:SP-240986->SP-241386; 5/12/24: 15%->65","23.501; 23.502; 23.503; 23.682; 23.228; 23.401 ",104,53,null,null,"2024-06-12","2024-12-05"]
[88,1040077,"   Application enablement for satellite access Phase 3 ","5GSAT_Ph3_App",2,"Rel-19","S6","2024-07-16","2024-12-12",0.75,"SP-241690",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 4/9/24: 0%->5; 5/12/24: 5%->75; 8/1/25: WID:SP-241010->SP-241690","23.558; 23.434; 23.289 ",104,53,null,null,"2024-06-12","2025-01-08"]
[89,1060023,"   CT aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",2,"Rel-19","C3","2024-12-02","2025-09-09",0.01,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,"x","2024-06-12","2024-09-04"]
[90,1060032,"      CT1 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C1","2024-12-02","2025-09-09",0,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,"x","2024-06-12","2024-09-04"]
[91,1060033,"      CT3 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C3","2024-12-02","2025-09-09",0.05,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,"x","2024-06-12","2024-09-04"]
[92,1050019,"   CT aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",2,"Rel-19","C1","2024-09-09","2025-09-09",0.1,"CP-242103",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[93,1050041,"      CT1 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C1","2024-09-09","2025-09-09",0.1,"CP-242103",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[94,1050042,"      CT3 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C3","2024-09-09","2025-09-09",0.1,"CP-242103",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[95,1050043,"      CT4 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C4","2024-09-09","2025-09-09",0.1,"CP-242103",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[96,1060016,"Management Aspects of NTN Phase 2 ","NTN_OAM_Ph2",1,"Rel-19","S5","2024-12-05","2025-06-06",0,"SP-241949",null,"MingRui Sun (China Unicom)","sunmr19@chinaunicom.cn",null,"28.541; 28.552; 28.554; 28.658; 28.662; 28.540; 28.530 ",null,null,null,null,"2024-12-05","NA"]
[97,1020044,"Study on Security Aspects of 5G Satellite Access Phase 3 ","FS_5GSAT_Ph3_SEC",1,"Rel-19","S3","2024-01-04","2024-12-12",0.85,"SP-240232",null,"Zhou Wei ","zhouwei@catt.cn ","No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;; 14/3/24: 0%->10; 2/4/24: WID:SP-231790->SP-240232; 13/6/24: 10%->65; 5/9/24: 65%->75; 5/12/24: 75%->85","33.700-29",102,52,null,null,"2023-12-07","2024-12-05"]
[98,1060065,"Security Aspects of 5G Satellite Access Phase 3 ","5GSAT_Ph3_SEC",1,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241780",null,"Wei Zhou, CATT ","zhouwei@catt.cn ",null,33.401000000000003,null,null,null,null,"2024-12-05","NA"]
[99,1040014,"Study on charging aspects of satellite access Phase 3 ","FS_5GSAT_Ph3_CH",1,"Rel-19","S5","2024-06-12","2025-03-03",0.75,"SP-240980",null,"Yingying Liu, CATT, ","liuyingying@cictmobile.com ","13/6/24: 0%->10; 4/9/24: 10%->40; 26/9/24: 28.846 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25",28.846,104,53,null,null,"2024-06-12","2024-12-05"]
[100,1020097,"Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3",1,"Rel-19",null,"2023-12-13","2025-03-03",0.24,"RP-241789",null,"Thales ",null,"2/4/24: WID:RP-234078->RP-240775; 23/7/24: WID:RP-240775->RP-241667; 26/9/24: WID:RP-241667->RP-241789",null,102,52,null,null,"2024-01-02","2024-09-26"]
[101,1021097,"   Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.55000000000000004,"RP-240775","RP-242462","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->45%",null,102,52,null,null,"2024-01-02","2024-12-06"]
[102,1022097,"   Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240775","RP-242462","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240923->RP-241742; ; 6/12/24: ",null,102,52,null,null,"2024-01-02","2024-12-06"]
[103,1020096,"Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE)","IoT_NTN_Ph3",1,"Rel-19",null,"2023-12-13","2025-03-03",0.23,"RP-242397",null,"Mediatek ",null,"2/4/24: WID:RP-234077->RP-240776; 23/7/24: WID:RP-240776->RP-241624; 26/9/24: WID:RP-241624->RP-242397",null,102,52,null,null,"2024-01-02","2024-09-26"]
[104,1021096,"   Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.5,"RP-242397","RP-242996","Mediatek ",null,"13/6/24: Compl:0%->15%; Stat Rep: ->RP-241356; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241356->RP-242050; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:30%->50%; Stat Rep: RP-242050->RP-242996; ",null,102,52,null,null,"2024-01-02","2024-12-06"]
[105,1032087,"   Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-242397","RP-242996","Mediatek ",null,"13/6/24: FCD:03/03/2026->12/12/2025; Stat Rep: ->RP-241356; ; 4/9/24: FCD:12/12/2025->26/03/2025; Stat Rep: RP-241356->RP-242050; ; 6/12/24: Stat Rep: RP-242050->RP-242996; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[106,1030076,"Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob",1,"Rel-19","R2","2024-03-03","2024-09-09",0.96,"RP-240924",null,"Thales ",null,"23/7/24: WID:RP-240846->RP-240924",null,103,52,null,null,"2024-04-02","2024-07-23"]
[107,1031076,"   Core part: Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob-Core",2,"Rel-19","R2","2024-03-03","2025-09-09",0.96,"RP-240846","RP-242463","Thales ",null,"13/6/24: Compl:0%->70%; Stat Rep: ->RP-240925; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:70%->95%; WID: RP-240924->RP-240846; Stat Rep: RP-240925->RP-241741; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:95%->96%; Stat Rep: RP-241741->RP-242463; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[108,1030086,"Enhanced requirements and test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh",1,"Rel-19","R4","2024-03-03","2025-03-03",0.39,"RP-241985",null,"Samsung ",null,"23/7/24: WID:RP-240857->RP-241281; 26/9/24: WID:RP-241281->RP-241985",null,103,52,null,null,"2024-04-02","2024-09-26"]
[109,1031086,"   Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.5,"RP-241985","RP-242592","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->16%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:16%->50%; Stat Rep: RP-241984->RP-242592; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[110,1032086,"   Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0.3,"RP-241985","RP-242592","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->10%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:10%->30%; Stat Rep: RP-241984->RP-242592; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[111,1040129,"Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband",1,"Rel-19","R4","2024-06-06","2025-06-06",0.21,"RP-241885",null,"Qualcomm ",null,"26/9/24: WID:RP-241661->RP-241885",null,104,53,null,null,"2024-07-23","2024-09-26"]
[112,1041129,"   Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.5,"RP-241885","RP-242615","Qualcomm ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241884; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; Stat Rep: RP-241884->RP-242615; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[113,1042129,"   Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Perf",2,"Rel-19","R4","2024-06-06","2025-06-06",0,"RP-241885","RP-242615","Qualcomm ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241884; ; 6/12/24: Stat Rep: RP-241884->RP-242615; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[114,1040130,"Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band",1,"Rel-19","R4","2024-06-06","2025-06-06",0.21,"RP-242062",null,"Mediatek ",null,"26/9/24: WID:RP-241662->RP-242062",null,104,53,null,null,"2024-07-23","2024-09-26"]
[115,1041130,"   Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.5,"RP-242062","RP-242999","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-242061; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[116,1042130,"   Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Perf",2,"Rel-19","R4","2024-06-06","2025-06-06",0,"RP-242062","RP-242999","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-242061; ; 6/12/24: WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[117,1040135,"Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands",1,"Rel-19","R4","2024-06-06","2025-03-03",0.13,"RP-241690",null,"Intelsat ",null,null,null,104,53,null,null,"2024-07-23","NA"]
[118,1041135,"   Core part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.3,"RP-241690","RP-242946","Intelsat ",null,"4/9/24: FCD:09/09/2025->24/09/2024; Compl:0%->15%; Stat Rep: ->RP-241788; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241788->RP-242946; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[119,1042135,"   Perf. part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Perf",2,"Rel-19","R4","2024-06-06","2026-03-03",0,"RP-241690","RP-242946","Intelsat ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-241788; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241788->RP-242946; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[120,1040134,"New NR NTN bands to support Extended L-band and combined MSS L-band and Extended L-band ranges ","NR_NTN_combinedLband",1,"Rel-19","R4","2024-06-06","2025-06-06",0.15,"RP-241856",null,"Inmarsat ",null,"26/9/24: WID:RP-241689->RP-241856",null,104,53,null,null,"2024-07-23","2024-09-26"]
[121,1041134,"   Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.35,"RP-241856","RP-242601","Inmarsat ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->15%; Stat Rep: ->RP-241782; ; 6/12/24: Compl:15%->35%; Stat Rep: RP-241782->RP-242601; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[122,1042134,"   Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Perf",2,"Rel-19","R4","2024-06-06","2025-06-06",0,"RP-241856","RP-242601","Inmarsat ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241782; ; 6/12/24: Stat Rep: RP-241782->RP-242601; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[123,1050127,"Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands",1,"Rel-19","R4","2024-09-09","2025-03-03",0.64,"RP-242373",null,"SoftBank ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[124,1051127,"   Core part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Core",2,"Rel-19","R4","2024-09-09","2025-03-03",0.99,"RP-242373","RP-242890","SoftBank ",null,"6/12/24: FCD:12/12/2024->03/03/2025; Compl:0%->99%; Stat Rep: ->RP-242890; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[125,1052127,"   Perf. part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Perf",2,"Rel-19","R4","2024-09-09","2024-12-12",0,"RP-242373",null,"SoftBank ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[126,0,"Rel-19 XR (eXtended Reality), Metaverse","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[127,1020056,"Localized Mobile Metaverse Services ","Metaverse",1,"Rel-19",null,"2022-03-10","2025-09-09",0.61,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[128,950005,"   Study on Localized Mobile Metaverse Services ","FS_Metaverse",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100",22.856000000000002,95,48,null,null,"2022-03-10","2023-12-08"]
[129,1000028,"   Stage 1 of Localized Mobile Metaverse Services ","Metaverse",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"2023-06-08","2023-12-08"]
[130,1040076,"   Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19","S6","2024-07-16","2024-12-12",0.8,"SP-241390",null,"Shah, Sapan, Samsung ","<sapan.shah@samsung.com> ","; 4/9/24: 0%->25; 26/9/24: WID:SP-241009->SP-241390; 26/9/24: 23.437 added;; 5/12/24: 25%->80","23.434; 23.542; 23.558; 23.436 ; 23.437",104,53,null,null,"2024-06-12","2024-12-05"]
[131,1020052,"   Study on application enablement for Localized Mobile Metaverse Services ","FS_Metaverse_App",2,"Rel-19","S6","2024-01-03","2024-09-09",1,"SP-231806",null,"Shah, Sapan, Samsung ","sapan.shah@samsung.com ","8/12/23: 0%->10; 14/3/24: 0%->30; 3/4/24: 23.700-21 added;; 13/6/24: 30%->70; 4/9/24: 70%->100","23.700-21",102,52,null,null,"2023-12-07","2024-09-04"]
[132,1030039,"   Study on security aspects of 5G Mobile Metaverse services ","FS_Metaverse_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.7,"SP-240508",null,"Rohini Rajendran, ","r.rohini@samsung.com ","3/4/24: 33.721 added;; 13/6/24: 0%->20; 5/9/24: 20%->50; 5/12/24: 50%->70",33.720999999999997,103,52,null,null,"2024-03-14","2024-12-05"]
[133,1050025,"   CT aspects of Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19","C3","2024-09-09","2025-09-09",0.1,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,"24.583, 24.545, 29.549",105,53,null,"x","2024-06-12","NA"]
[134,1050060,"      CT1 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C1","2024-09-09","2025-09-09",0.15,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com","; 26/9/24: 24.437 added;",null,105,53,null,"x","2024-06-12","2024-09-26"]
[135,1050061,"      CT3 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C3","2024-09-09","2025-09-09",0.05,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,null,105,53,null,"x","2024-06-12","NA"]
[{"$f":"A136+1","v":136},1060060,"   Security aspects of 5G Mobile Metaverse services ","Metaverse_Sec",2,"Rel-19","S3","2024-12-05","2025-03-03",0,"SP-241775",null,"Rohini Rajendran, r.rohini@samsung.com ","Lihui Xiong, xionglihui@oppo.com ",null,33.433999999999997,null,null,null,null,"2024-12-05","NA"]
[137,1060034,"Extended Reality and Media",null,1,"Rel-19",null,"2023-03-16","2025-09-09",0.44,null,null,null,null,null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[138,990052,"   Supporting UE Mobility for XR Services ","XRMobility",2,"Rel-19","S1","2023-03-16","2023-06-06",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-09-06"]
[139,1010032,"   Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",2,"Rel-19","S2","2024-01-03","2024-09-09",1,"SP-231671",null,"Primary Rapporteur: Devaki Chandramouli (Nokia) ","devaki.chandramouli@nokia.com. ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13; 14/3/24: 0%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100","23.700-70",101,51,null,null,"2023-09-20","2024-09-04"]
[140,1040032,"   Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19","S2","2024-06-12","2024-12-12",0.65,"SP-241385",null,"Georgios Gkellas (Nokia), ","Georgios.Gkellas@nokia.com. ","; 4/9/24: 0%->5; 26/9/24: WID:SP-240990->SP-241322; 26/9/24: WID:SP-241322->SP-241385; 5/12/24: 5%->65","23.501; 23.502; 23.503; 23.316 ",104,53,null,null,"2024-06-12","2024-12-05"]
[141,1060027,"   CT aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19","C3","2024-12-02","2025-09-09",0.13,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,"24.501, 29.122, 29.508, 29.512, 29.514, 29.522, 29.513, 29.561, 29.281, 29.244, 29.502, 29.564, 29.571",104,53,null,null,"2024-06-12","2024-09-26"]
[142,1060035,"      CT1 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C1","2024-12-02","2025-09-09",0,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[143,1060036,"      CT3 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C3","2024-12-02","2025-09-09",0.2,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[144,1060037,"      CT4 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C4","2024-12-02","2025-09-09",0.2,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[145,1020051,"   Study on Application enabler for XR Services ","FS_XRApp",2,"Rel-19","S6","2024-01-03","2024-12-12",1,"SP-2315739",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","8/12/23: 0%->10; 14/3/24: 0%->20; 3/4/24: 23.700-23 added;; 13/6/24: 20%->65; 4/9/24: 65%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-23",102,52,null,null,"2023-12-07","2024-12-05"]
[146,1040074,"   Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19","S6","2024-07-16","2024-12-12",0.9,"SP-241207",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 4/9/24: 0%->15; 26/9/24: WID:SP-241007->SP-241207; 5/12/24: 15%->90","23.433; 23.558 ",104,53,null,null,"2024-06-12","2024-12-05"]
[147,1060024,"   CT aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19","C3","2024-12-02","2025-09-09",0.02,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,"24.543, 24.548, 29.548, 29.549, 29.558",104,53,null,null,"2024-06-12","2024-09-26"]
[148,1060038,"      CT1 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C1","2024-12-02","2025-09-09",0,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[149,1060039,"      CT3 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C3","2024-12-02","2025-09-09",0.05,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"2024-06-12","2024-09-26"]
[150,1020098,"XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3",1,"Rel-19",null,"2023-12-13","2025-03-03",0.24,"RP-241771",null,"Nokia ",null,"2/4/24: WID:RP-234080->RP-240791; 26/9/24: WID:RP-240791->RP-241771",null,102,52,null,null,"2024-01-02","2024-09-26"]
[151,1021098,"   Core part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.55000000000000004,"RP-240791","RP-242517","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Compl:0%->2%; Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Compl:2%->18%; Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:18%->30%; Stat Rep: RP-240",null,102,52,null,null,"2024-01-02","2024-12-06"]
[152,1022098,"   Perf. part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-240791","RP-242517","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240927->RP-241770; ; 6/12/24: FCD:03/03/2025->03",null,102,52,null,null,"2024-01-02","2024-12-06"]
[153,1030045,"Indirect Network Sharing ",null,1,"Rel-19",null,"2022-03-10","2025-09-09",0.82,null,null,null,null,null,null,103,52,null,null,"2024-03-13","NA"]
[154,950006,"   Study on Network Sharing Aspects ","FS_NetShare",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100",22.850999999999999,95,48,null,null,"2022-03-10","2023-09-06"]
[155,1000029,"   (Stage 1 of) Indirect Network Sharing ","NetShare",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100",22.260999999999999,100,51,null,null,"2023-06-08","2023-09-06"]
[156,1030011,"   (Stage 2 of) Indirect Network Sharing ","TEI19_NetShare",2,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240488",null,"Xing, Tianqi, China Unicom, ","xingtq@chinaunicom.cn ","; 13/6/24: FCD:12/12/2024->06/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[157,1040019,"   Charging enhancement for indirect network sharing ","NetShare_CH",2,"Rel-19","S5","2024-06-12","2024-12-12",1,"SP-241004",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ","; 5/12/24: 0%->100","32.240; 32.255; 32.256 ",104,53,null,null,"2024-06-12","2024-12-05"]
[158,1050004,"   CT aspects of indirect network sharing ","TEI19_NetShare",2,"Rel-19","C4","2024-09-09","2025-09-09",0.57999999999999996,"CP-242024",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[159,1050074,"      CT1 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C1","2024-09-09","2025-09-09",0.75,"CP-242024",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[160,1050075,"      CT4 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C4","2024-09-09","2025-09-09",0.4,"CP-242024",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[161,1060017,"Management of Network Sharing Phase 3 ??","NetShare_OAM_Ph3",1,"Rel-19","S5","2024-12-05","2025-06-06",0,"SP-241950",null,"ZhaoNing Wang (China Unicom)","wangzn18@chinaunicom.cn",null,"28.552; 32.130; 28.541 ",null,null,null,null,"2024-12-05","NA"]
[162,1030046,"Roaming Value-Added Services ",null,1,"Rel-19",null,"2022-06-02","2025-06-06",0.96,null,null,null,null,null,null,103,52,null,null,"2024-03-13","NA"]
[163,960015,"   Study on roaming value added services ","FS_RVAS",2,"Rel-19","S1","2022-06-02","2022-12-12",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100",22.876999999999999,96,49,null,null,"2022-06-02","2022-12-10"]
[164,990051,"   Roaming Value-Added Services ","RVAS",2,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100",22.260999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[165,1030013,"   Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240119",null,"Qian Chen, Ericsson, ","qian.xb.chen@ericsson.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[166,1050002,"   CT aspects of Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19","C4","2024-09-09","2025-06-06",0.95,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[167,1050087,"      CT3 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C3","2024-09-09","2025-06-06",0.9,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[168,1050088,"      CT4 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C4","2024-09-09","2025-06-06",0.99,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[169,0,"Rel-19 user plane","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[170,1050037,"Study on immersive Real-Time Communication for WebRTC, Phase 2 ","FS_iRTCW_Ph2",1,"Rel-19","S4","2024-09-09","2025-06-06",0.15,"SP-241374",null,"Hakju Ryan Lee, Samsung Electronics, CO., LTD, ","hakju00.lee@samsung.com ","5/12/24: 0%->15",null,105,53,null,null,"2024-06-12","2024-12-05"]
[171,1050113,"Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 ","ATIAS_Ph2",1,"Rel-19","S4","2024-09-09","2025-09-09",0,"SP-241314",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ",null,"26.259; 26.260; 26.261 ",105,53,null,null,"2024-06-12","NA"]
[172,1060022,"Diverse audio Capturing System for UEs ","DaCAS",1,"Rel-19","S4","2024-12-05","2025-09-09",0,"SP-241962",null,"Wang Bin, Xiaomi Technology ","wangbin23@xiaomi.com ",null,26.533000000000001,null,null,null,null,"2024-12-05","NA"]
[173,1040022,"Study on Spatial Computing for AR Services ","FS_ARSpatial",1,"Rel-19","S4","2024-06-06","2025-06-06",0.25,"SP-240927",null,"Hamza, Ahmed, InterDigital Canada ","<Ahmed.Hamza@InterDigital.com> ","4/9/24: 0%->10; 26/9/24: 26.819 added;; 5/12/24: 10%->25",26.818999999999999,104,53,null,null,"2024-06-12","2024-12-05"]
[174,1040021,"EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 ","IVAS_Codec_Ph2",1,"Rel-19","S4","2024-06-06","2025-09-09",0.2,"SP-241000",null,"Su, Huan-yu, Huawei Technologies Co Ltd., ","su.huanyu@huawei.com ","; 4/9/24: 0%->5; 5/12/24: 5%->20; 5/12/24: FCD:06/06/2025->/25","26.114; 26.117; 26.119; 26.249; 26.250; 26.252; 26.253; 26.258; 26.997 ",104,53,null,null,"2024-06-12","2024-12-05"]
[175,1040020,"Study on Haptics in 5G Media Services ","FS_HapticsMedia",1,"Rel-19","S4","2024-06-12","2025-03-03",0.6,"SP-241121",null,"Gaëlle Martin-Cocher, InterDigital ","(Gaelle.Martin-Cocher@InterDigital.com) ","4/9/24: WID:SP-240979->SP-241121; acron.: FS_HapticsMed-> FS_HapticsMedia; 4/9/24: 0%->15; 26/9/24: 26.854 added;; 5/12/24: 15%->60",26.853999999999999,104,53,null,null,"2024-06-12","2024-12-05"]
[176,1050097,"UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",1,"Rel-19","S2","2024-01-04","2025-09-09",0.76,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"2024-06-12","NA"]
[177,1020003,"   Study on UPF enhancement for Exposure And SBA Phase 2 ","FS_UPEAS_Ph2",2,"Rel-19","S2","2024-01-04","2024-06-06",1,"SP-231795",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","14/3/24: 0%->45; 13/6/24: 45%->100",null,102,52,null,null,"2024-01-03","2024-06-13"]
[178,1040035,"   Stage 2 of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 4/9/24: 0%->65; 5/12/24: 65%->100","23.501; 23.502; 23.503 ",104,53,null,null,"2024-06-12","2024-12-05"]
[179,1050001,"   CT aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","C4","2024-09-09","2025-09-09",0.65,"CP-242245",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[180,1050098,"      CT3 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C3","2024-09-09","2025-09-09",0.6,"CP-242245",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[181,1050099,"      CT4 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C4","2024-09-09","2025-09-09",0.7,"CP-242245",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"2024-06-12","NA"]
[182,1030002,"Video Operating Points - Harmonization and Stereo MV-HEVC ","VOPS",1,"Rel-19","S4","2024-03-13","2025-06-06",0.45,"SP-240060",null,"Waqar Zia ","waqar_zia (at) apple.com ","14/5/24: 26.265 added;; 13/6/24: 0%->15; 4/9/24: 15%->20; 4/9/24: 20%->; 5/12/24: 20%->45; 5/12/24: FCD:03/03/2025->/25",26.265000000000001,103,52,null,null,"2024-03-13","2024-12-05"]
[183,1030003,"Split rendering over IMS ","SR_IMS",1,"Rel-19","S4","2024-04-02","2025-06-06",0.45,"SP-240492",null,"He, Shane, Nokia Corporation ","shane.he@nokia.com ","; 14/5/24: 26.567 added;; 13/6/24: 0%->10; 4/9/24: 10%->25; 5/12/24: 25%->45; 5/12/24: FCD:03/03/2025->/25","26.264 ; 26.567",103,52,null,null,"2024-03-13","2024-12-05"]
[184,1030005,"Study on Media Messaging ","FS_MeMe",1,"Rel-19","S4","2024-04-02","2025-03-03",0.6,"SP-240477",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","13/6/24: 0%->10; 13/6/24: FCD:12/12/2024->/25; 4/9/24: 10%->30; 5/12/24: 30%->60",null,103,52,null,null,"2024-03-13","2024-12-05"]
[185,1030006,"Study on Advanced Media Delivery ","FS_AMD",1,"Rel-19","S4","2024-04-02","2024-12-12",0.75,"SP-241011",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-240478->SP-241011; 4/9/24: 15%->30; 5/12/24: 30%->75","26.802; 26.804 ",103,52,null,null,"2024-03-13","2024-12-05"]
[186,1060069,"Stage 2 for Advanced Media Delivery ","AMD-ARCH-MED",1,"Rel-19","S4","2024-12-05","2025-03-03",0,"SP-241963",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ",null,"26.501; 26.502 ",null,null,null,null,"2024-12-05","NA"]
[187,1030007,"Study of 5G Real-time Transport Protocol Configurations, Phase 2 ","FS_5G_RTP_Ph2",1,"Rel-19","S4","2024-04-02","2024-12-12",1,"SP-240482",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","14/5/24: 26.822 added;; 13/6/24: 0%->40; 4/9/24: 40%->65; 5/12/24: 65%->100",26.821999999999999,103,52,null,null,"2024-03-13","2024-12-05"]
[188,1060021,"5G Real-time Transport Protocol Configurations, Phase 2 ","5G_RTP_Ph2",1,"Rel-19","S4","2024-12-05","2025-09-09",0,"SP-241961",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ",null,"26.522; 26.510; 26.113 ",null,null,null,null,"2024-12-05","NA"]
[189,1030008,"Study on Beyond 2D Video ","FS_Beyond2D",1,"Rel-19","S4","2024-04-02","2025-06-06",0.28000000000000003,"SP-240479",null,"Jiayi Xu, ","xujiayi@chinamobile.com ","14/5/24: 26.956 added;; 13/6/24: 0%->10; 4/9/24: 10%->17; 5/12/24: 17%->28",26.956,103,52,null,null,"2024-03-13","2024-12-05"]
[190,1030009,"Study on Audio Codec APIs ","FS_ACAPI",1,"Rel-19","S4","2024-04-02","2025-06-06",0.2,null,null,"Stefan Döhla ","(stefan DOT doehla AT iis DOT fraunhofer DOT de) ","14/5/24: 26.858 added;; 13/6/24: 0%->10; 5/12/24: 10%->20; 5/12/24: FCD:03/03/2025->/25",26.858000000000001,103,52,null,null,"2024-03-13","2024-12-05"]
[191,0,"Rel-19 Verticals and Non Public Network","-",1,"Rel-19",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[192,1050034,"Study on Service Enabler Architecture Layer (SEAL) Phase 4","FS_SEAL_Ph4",1,"Rel-19","S6","2024-09-04","2025-03-03",0.2,"SP-241375",null,"Yang, Yanmei, Huawei Technologies Co.,Ltd. ","yangyanmei@huawei.com","5/12/24: 0%->20",null,105,53,null,null,"2024-09-04","2024-12-05"]
[193,1060040,"Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",1,"Rel-19","S6","2024-01-04","2025-09-09",0.46,"SP-241381",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ",null,23.222000000000001,105,53,null,null,"2024-09-04","NA"]
[194,1020062,"   Study on CAPIF Phase 3 ","FS_CAPIF_Ph3",2,"Rel-19","S6","2024-01-04","2024-12-12",1,"SP-231741",null,"Preciado Rojas, Diego, Nokia ","diego.preciado_rojas@nokia.com ","14/3/24: 0%->20; 3/4/24: 23.700-22 added;; 13/6/24: 20%->55; 4/9/24: 55%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-22",102,52,null,null,"2024-01-03","2024-12-05"]
[195,1050035,"   Stage 2 of Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",2,"Rel-19","S6","2024-09-04","2024-12-12",0,"SP-241694",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ","; 8/1/25: WID:SP-241381->SP-241694",23.222000000000001,105,53,null,null,"2024-09-04","2025-01-08"]
[196,1060026,"   CT aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",2,"Rel-19","C3","2024-12-02","2025-09-09",0,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,29.222000000000001,105,53,null,null,"2024-09-04","NA"]
[197,1060041,"      CT3 aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",3,"Rel-19","C3","2024-12-02","2025-09-09",0,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,29.222000000000001,105,53,null,null,"2024-09-04","NA"]
[198,1040025,"   Study on security aspects of CAPIF Phase 3 ","FS_CAPIF_Ph3-sec",2,"Rel-19","S3","2024-06-12","2024-12-12",0.6,"SP-240654",null,"Henry Leung ( Xiaomi) ","lianghaoran@xiaomi.com ","5/9/24: 0%->20; 26/9/24: 33.700-22 added;; 5/12/24: 20%->60","33.700-22",104,53,null,null,"2024-06-12","2024-12-05"]
[199,1060061,"   Security aspects of CAPIF Phase3 ","CAPIF_Ph3_sec",2,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241776",null,"1st rapporteur: Henry Leung (Xiaomi), ","lianghaoran@xiaomi.com ",null,33.122,null,null,null,null,"2024-12-05","NA"]
[{"$f":"A200+1","v":200},1040015,"   Study on Charging Aspects of CAPIF ","FS_CAPIF_Ph2_CH",2,"Rel-19","S5","2024-06-12","2024-12-12",0.75,"SP-240981",null,"João Rodrigues, Nokia, ","joao.a.rodrigues@nokia.com ","13/6/24: 0%->15; 4/9/24: 15%->35; 26/9/24: 28.849 added;; 5/12/24: 35%->75",28.849,104,53,null,null,"2024-06-12","2024-12-05"]
[201,1060009,"Enhanced OAM for management service exposure to external consumers through CAPIF ","MExpo",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241942",null,"Winnie Nakimuli (Nokia) ","winnie.nakimuli@nokia.com",null,null,null,null,null,null,"2024-12-05","NA"]
[202,1000027,"Non-Public Network (NPN) security considerations ","SecNPN",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,22.260999999999999,100,51,null,null,"2023-06-08","NA"]
[203,1020039,"Study on security for PLMN hosting a NPN ","PLMNNPN_SEC",1,"Rel-19","S3","2024-01-03","2024-09-09",0.95,"SP-231786",null,"Jun Shen","shenjun6@chinatelecom.cn","4/1/24: 33.757 added;; 14/3/24: 0%->25; 13/6/24: 25%->70; 5/9/24: 70%->75; 5/12/24: 75%->95",33.756999999999998,102,52,null,null,"2023-12-07","2024-12-05"]
[204,1060067,"Security for PLMN hosting a NPN ","PLMNNPN",1,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241782",null,"Jun Shen ","shenjun6@chinatelecom.cn ",null,33.500999999999998,null,null,null,null,"2024-12-05","NA"]
[205,1050080,"ProSe support in NPN ","TEI19_ProSe_NPN",1,"Rel-19","S2","2024-03-13","2025-09-09",0.68,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"2024-03-13","2024-06-13"]
[206,1030016,"   Stage 2 of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"2024-03-13","2024-06-13"]
[207,1050021,"   CT aspects of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19","C1","2024-09-09","2025-09-09",0.66,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,"x","2024-03-13","2024-06-13"]
[208,1050081,"      CT1 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C1","2024-09-09","2025-09-09",0.7,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,"x","2024-03-13","2024-06-13"]
[209,1060042,"      CT3 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C3","2024-09-09","2025-09-09",1,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,"x","2024-03-13","2024-06-13"]
[210,1050082,"      CT4 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C4","2024-09-09","2025-09-09",0.95,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,"x","2024-03-13","2024-06-13"]
[211,1050083,"      CT6 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C6","2024-09-09","2025-09-09",0,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,"x","2024-03-13","2024-06-13"]
[212,1040009,"Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.3,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,"24.558, 24.559, 24.549, 29.116, 29.122, 29.222, 29.255, 29.257, 29.343, 29.435, 29.486, 29.522, 29.538, 29.548, 29.549, 29.558, 29.583",101,51,null,"x","2023-09-06","2023-09-06"]
[213,1040060,"   CT1 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[214,1040061,"   CT3 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C3","2024-06-17","2025-09-09",0.4,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[215,0,"Rel-19 Radio: NR-only, band-related",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[216,1040127,"Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz",1,"Rel-19","R4","2024-06-06","2024-12-12",0.99,"RP-242120",null,"MidWave Wireless ",null,"26/9/24: WID:RP-241648->RP-242120",null,104,53,null,null,"2024-07-23","2024-09-26"]
[217,1041127,"   Core part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.99,"RP-241648","RP-242494","MidWave Wireless ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[218,1042127,"   Perf. part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Perf",2,"Rel-19","R4","2024-06-06","2025-03-03",0.99,"RP-241648","RP-242494","MidWave Wireless ",null,"4/9/24: FCD:03/03/2025->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[219,1040131,"Introduction of NR bands n87 and n88 ","NR_bands_n87_n88",1,"Rel-19","R4","2024-06-06","2025-03-03",0.66,"RP-242338",null,"Nokia ",null,"26/9/24: WID:RP-241663->RP-242338",null,104,53,null,null,"2024-07-23","2024-09-26"]
[220,1041131,"   Core part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.66,"RP-242338","RP-242500","Nokia ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[221,1042131,"   Perf. part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Perf",2,"Rel-19","R4","2024-06-06","2025-03-03",0.66,"RP-242338","RP-242500","Nokia ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[222,1040132,"Introduction of NR band n68 ","NR_band_n68",1,"Rel-19","R4","2024-06-06","2024-12-12",0.6,"RP-241664",null,"Ericsson ",null,null,null,104,53,null,null,"2024-07-23","NA"]
[223,1041132,"   Core part: Introduction of NR band n68 ","NR_band_n68-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.6,"RP-241664","RP-242605","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[224,1042132,"   Perf. part: Introduction of NR band n68 ","NR_band_n68-Perf",2,"Rel-19","R4","2024-06-06","2025-03-03",0.6,"RP-241664","RP-242605","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[225,1040121,"Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.35,"RP-241922",null,"ZTE ",null,"26/9/24: WID:RP-241677->RP-241922",null,104,53,null,null,"2024-07-23","2024-09-26"]
[226,1041121,"   Core part: Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.35,"RP-241922","RP-242573","ZTE ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241923; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->35%; Stat Rep: RP-241923->RP-242573; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[227,1040120,"Rel-19 NR CA/DC for x bands DL with y bands UL (x<7, y<3) and SUL/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.34,"RP-241833",null,"Ericsson ",null,"26/9/24: WID:RP-241674->RP-241833",null,104,53,null,null,"2024-07-23","2024-09-26"]
[228,1041120,"   Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.34,"RP-241833","RP-242753","Ericsson ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->20%; Stat Rep: ->RP-241832; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->34%; Stat Rep: RP-241832->RP-242753; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[229,1050120,"Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2",1,"Rel-19","R1","2024-09-09","2025-06-06",0.4,"RP-242408",null,"Lenovo ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[230,1051120,"   Core part: Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2-Core",2,"Rel-19","R1","2024-09-09","2025-06-06",0.4,"RP-242408","RP-242903","Lenovo ",null,"6/12/24: FCD:09/09/2025->06/06/2025; Compl:0%->40%; Stat Rep: ->RP-242903; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[231,0,"Rel-19 Radio: NR-only, topics other than band",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[232,1050126,"mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect",1,"Rel-19","R4","2024-09-09","2025-06-06",0.4,"RP-242371",null,"China Unicom ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[233,1051126,"   Core part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Core",2,"Rel-19","R4","2024-09-09","2025-06-06",0.4,"RP-242371","RP-242612","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[234,1052126,"   Perf. part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Perf",2,"Rel-19","R4","2024-09-09","2025-06-06",0.4,"RP-242371","RP-242612","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[235,1040100,"Study on spatial channel model for demodulation performance requirements for NR ","FS_NR_demod_SCM",1,"Rel-19","R4","2024-06-06","2025-06-06",0.4,"RP-241610","RP-242465","Nokia ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->15%; Stat Rep: ->RP-241844; ; 26/9/24: WID:RP-241610->RP-241848; 26/9/24: 38.753 added;; 6/12/24: Compl:15%->40%; WID: RP-241848->RP-241610; Stat Rep: RP-241844->RP-242465; ",38.753,104,53,null,null,"2024-07-23","2024-12-06"]
[236,1040101,"Study on NR FR1 DL fragmented carriers ","FS_NR_FR1_DL_Frag_Carrier",1,"Rel-19","R4","2024-06-06","2025-06-06",0.25,"RP-242404","RP-243001","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242054; ; 26/9/24: WID:RP-241669->RP-242404; 26/9/24: 38.755 added;; 6/12/24: Compl:5%->25%; Stat Rep: RP-242054->RP-243001; ",38.755000000000003,104,53,null,null,"2024-07-23","2024-12-06"]
[237,1020081,"Study on channel modelling enhancements for 7-24GHz for NR ","FS_NR_7_24GHz_CHmod",1,"Rel-19","R1","2023-12-13","2025-06-06",0.6,"RP-234018","RP-242541","LEE Daewon, Intel Corporation","daewon.lee@intel.com","14/3/24: Stat Rep: ->RP-240265; Rapporteur: Intel->LEE Daewon, Intel Corporation; Rap eMail: ->daewon.lee@intel.com; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240265->RP-241099; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:15%->35%; Stat Rep: RP-241099->RP-24",null,102,52,null,null,"2024-01-02","2024-12-06"]
[238,1050125,"Additional topological enhancements for NR ","NR_WAB_5GFemto",1,"Rel-19","R3","2024-09-09","2025-09-09",0.3,"RP-242395",null,"NTT DOCOMO ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[239,1051125,"   Core part: Additional topological enhancements for NR ","NR_WAB_5GFemto-Core",2,"Rel-19","R3","2024-09-09","2025-09-09",0.3,"RP-242395","RP-243006","NTT DOCOMO ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-243006; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[240,1020082,"Study on additional topological enhancements for NR ","FS_NR_WAB_5GFemto",1,"Rel-19","R3","2024-09-09","2025-09-09",1,"RP-241264","RP-241963","Min, Tianyang, NTT DOCOMO","tianyang.min.ex@nttdocomo.com","14/3/24: FCD:28/05/2021->09/09/2024; Stat Rep: ->RP-240320; Rapporteur: NTT DOCOMO->Min, Tianyang, NTT DOCOMO; Rap eMail: ->tianyang.min.ex@nttdocomo.com; ; 2/4/24: WID:RP-234041->RP-240319; 3/4/24: 38.799 added;; 13/6/24: Compl:0%->70%; Stat Rep: RP-2...",38.798999999999999,102,52,null,null,"2024-01-02","2024-09-26"]
[241,1030084,"NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS",1,"Rel-19",null,"2024-03-03","2024-09-09",0,"RP-240840",null,"OPPO ",null,null,null,103,52,null,null,"2024-04-02","NA"]
[242,1031084,"   Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS-Core",2,"Rel-19","R4","2024-03-03","2024-03-04",0,"RP-240840","RP-242789","OPPO ",null,"14/5/24: 38.787 added;; 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241152; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->25%; Stat Rep: RP-241152->RP-241843; ; 6/12/24: FCD:09/09/2024->04/03/2024; Compl:25%->0%; Stat Rep: RP-241843->RP-242789; ",38.786999999999999,103,52,null,null,"2024-04-02","2024-12-06"]
[243,1040114,"NR sidelink multi-hop relay ","NR_SL_relay_multihop",1,"Rel-19","R2","2024-06-06","2024-09-09",0.4,"RP-242349",null,"LG Electronics ",null,"26/9/24: WID:RP-241609->RP-242349",null,104,53,null,null,"2024-07-23","2024-09-26"]
[244,1041114,"   Core part: NR sidelink multi-hop relay ","NR_SL_relay_multihop-Core",2,"Rel-19","R2","2024-06-06","2025-09-09",0.4,"RP-242349","RP-242529","LG Electronics ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241750; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->40%; Stat Rep: RP-241750->RP-242529; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[245,1020089,"NR MIMO Phase 5 ","NR_MIMO_Ph5",1,"Rel-19",null,"2023-12-13","2025-03-03",0.31,"RP-242394",null,"Samsung ",null,"2/4/24: WID:RP-234007->RP-240087; 26/9/24: WID:RP-240087->RP-242394",null,102,52,null,null,"2024-01-02","2024-09-26"]
[246,1021089,"   Core part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.7,"RP-242394","RP-242522","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Compl:0%->15%; Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: Compl:15%->35%; WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl",null,102,52,null,null,"2024-01-02","2024-12-06"]
[247,1022089,"   Perf. part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-242394","RP-242522","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:03/03/2026->26/03/2025; WID: RP-234007->RP-240087; Stat Rep:",null,102,52,null,null,"2024-01-02","2024-12-06"]
[248,1020090,"Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo",1,"Rel-19",null,"2023-12-13","2025-03-03",0.24,"RP-241614",null,"Huawei ",null,"2/4/24: WID:RP-234035->RP-240789; 23/7/24: WID:RP-240789->RP-241614",null,102,52,null,null,"2024-01-02","2024-07-23"]
[249,1021090,"   Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Core",2,"Rel-19","R1","2023-12-13","2025-09-09",0.55000000000000004,"RP-241614","RP-242877","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Compl:7%->18%; Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:09/09/",null,102,52,null,null,"2024-01-02","2024-12-06"]
[250,1022090,"   Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-241614","RP-242877","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: R",null,102,52,null,null,"2024-01-02","2024-12-06"]
[251,1020091,"NR mobility enhancements Phase 4 ","NR_Mob_Ph4",1,"Rel-19",null,"2023-12-13","2025-03-03",0.19,"RP-242356",null,"Apple ",null,"2/4/24: WID:RP-234036->RP-240299; 23/7/24: WID:RP-240299->RP-241515; 26/9/24: WID:RP-241515->RP-242356",null,102,52,null,null,"2024-01-02","2024-09-26"]
[252,1021091,"   Core part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Core",2,"Rel-19","R2","2023-12-13","2025-09-09",0.5,"RP-242356","RP-242790","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Compl:0%->5%; Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->20%; Stat Rep: RP-241514->RP-241915;",null,102,52,null,null,"2024-01-02","2024-12-06"]
[253,1022091,"   Perf. part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Perf",2,"Rel-19","R4","2023-12-13","2026-03-03",0,"RP-242356","RP-242790","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241514->RP-241915; ; 6/12/24: FCD:03/03/2025->0",null,102,52,null,null,"2024-01-02","2024-12-06"]
[254,1040023,"   Security aspects of NR mobility enhancement Phase 4 ","NR_Mob_Ph4_Sec",2,"Rel-19","S3","2024-07-16","2025-03-03",0,"SP-240652",null,"Rajavelsamy R ","rajvel@samsung.com ",null,33.500999999999998,104,53,null,null,"2024-07-16","NA"]
[255,1020092,"Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4",1,"Rel-19",null,"2023-12-13","2024-09-09",0.5,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"2024-01-02","NA"]
[256,1021092,"   Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4-Core",2,"Rel-19","R3","2023-12-13","2025-09-09",0.5,"RP-234038","RP-242835","Xufei Dong, China Unicom","dongxf37@chinaunicom.cn","14/3/24: Stat Rep: ->RP-240118; Rapporteur: China Unicom->Xufei Dong, China Unicom; Rap eMail: ->dongxf37@chinaunicom.cn; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240118->RP-241081; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241081->",null,102,52,null,null,"2024-01-02","2024-12-06"]
[257,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-19","RP","2017-12-15","2024-03-03",1,"RP-234033","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R...","37.890; 37.107",78,40,null,null,"2018-01-08","2024-04-02"]
[258,1030074,"Study on NR FR2 OTA (Over the Air) testing Phase 3 ","FS_NR_FR2_OTA_Ph3",1,"Rel-19","R4","2024-03-03","2025-09-09",0.9,"RP-242400","RP-242832","Qualcomm ",null,"13/6/24: Compl:0%->30%; Stat Rep: SI ->RP-241157; ; 23/7/24: WID:RP-240856->RP-241158; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:30%->70%; Stat Rep: RP-241157->RP-241845; ; 26/9/24: WID:RP-241158->RP-242400; 26/9/24: 38.771 added;; 6/12/24: FCD:09/09/2024",38.771000000000001,103,52,null,null,"2024-04-02","2024-12-06"]
[259,1030075,"Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz ","FS_NR_IMT_4400_7125_14800MHz",1,"Rel-19","R4","2019-03-07","2025-03-03",0.95,"RP-241326","RP-242943","Ericsson ",null,"14/5/24: 38.922 added;; 23/7/24: WID:RP-240787->RP-241326; 4/9/24: FCD:09/03/2021->24/12/2024; Compl:0%->50%; Stat Rep: SI ->RP-241840; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:50%->95%; Stat Rep: RP-241840->RP-242943; ",38.921999999999997,103,52,null,null,"2024-04-02","2024-12-06"]
[260,1030078,"NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo",1,"Rel-19",null,"2024-03-03","2025-03-03",0.19,"RP-242010",null,"ZTE ",null,"23/7/24: WID:RP-240829->RP-241284; 26/9/24: WID:RP-241284->RP-242010",null,103,52,null,null,"2024-04-02","2024-09-26"]
[261,1031078,"   Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.3,"RP-242010","RP-242831","ZTE ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241285; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241285->RP-242011; ; 26/9/24: 38.908 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->30%; Stat Rep: RP-242011->RP-242831; ",38.908000000000001,103,52,null,null,"2024-04-02","2024-12-06"]
[262,1032078,"   Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0.1,"RP-242010","RP-242831","ZTE ",null,"13/6/24: Stat Rep: ->RP-241285; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241285->RP-242011; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->10%; Stat Rep: RP-242011->RP-242831; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[263,1030079,"NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5",1,"Rel-19",null,"2024-03-03","2025-03-03",0.26,"RP-242380",null,"Apple ",null,"26/9/24: WID:RP-240830->RP-242380",null,103,52,null,null,"2024-04-02","2024-09-26"]
[{"$f":"A264+1","v":264},1031079,"   Core part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.6,"RP-242380","RP-242569","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241268; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->25%; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->60%; Stat Rep: RP-241971->RP-242569; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[265,1032079,"   Perf. part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-242380","RP-242569","Apple ",null,"13/6/24: Stat Rep: ->RP-241268; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241971->RP-242569; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[266,1030080,"NR demodulation performance Phase 5 ","NR_demod_Ph5",1,"Rel-19",null,"2024-03-03","2024-09-09",0.43,"RP-241297",null,"China Telecom ",null,"23/7/24: WID:RP-240831->RP-241297",null,103,52,null,null,"2024-04-02","2024-07-23"]
[267,1032080,"   Perf. part: NR demodulation performance Phase 5 ","NR_demod_Ph5-Perf",2,"Rel-19","R4","2024-03-03","2025-09-09",0.43,"RP-241297","RP-242855","China Telecom ",null,"13/6/24: FCD:03/03/2026->09/09/2025; Stat Rep: ->RP-241296; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->14%; Stat Rep: RP-241296->RP-241996; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:14%->43%; Stat Rep: RP-241996->RP-242855; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[268,1030081,"NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2",1,"Rel-19","R4","2024-03-03","2025-06-06",0.25,"RP-241622",null,"Intel ",null,"23/7/24: WID:RP-240832->RP-241622",null,103,52,null,null,"2024-04-02","2024-07-23"]
[269,1031081,"   Core part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Core",2,"Rel-19","R4","2024-03-03","2025-03-03",0.99,"RP-241622","RP-243146","Intel ",null,"13/6/24: Compl:0%->25%; Stat Rep: ->RP-241496; ; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:25%->70%; Stat Rep: RP-241496->RP-242031; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:73%->99%; Stat Rep: RP-242031->RP-243146; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[270,1032081,"   Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Perf",2,"Rel-19","R4","2024-03-03","2025-06-06",0,"RP-241622","RP-243146","Intel ",null,"13/6/24: Stat Rep: ->RP-241496; ; 6/12/24: Stat Rep: RP-241496->RP-243146; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[271,1030083,"Enhancements for Air-to-ground network for NR ","NR_ATG_enh",1,"Rel-19",null,"2024-03-03","2025-03-03",0.24,"RP-242381",null,"CMCC ",null,"23/7/24: WID:RP-240839->RP-241213; 26/9/24: WID:RP-241213->RP-242381",null,103,52,null,null,"2024-04-02","2024-09-26"]
[272,1031083,"   Core part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.55000000000000004,"RP-242381","RP-242960","CMCC ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241214; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->25%; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->55%; Stat Rep: RP-241933->RP-242960; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[273,1032083,"   Perf. part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-242381","RP-242960","CMCC ",null,"13/6/24: Stat Rep: ->RP-241214; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241933->RP-242960; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[274,1040123,"Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.3,"RP-242003",null,"China Telecom ",null,"26/9/24: WID:RP-241679->RP-242003",null,104,53,null,null,"2024-07-23","2024-09-26"]
[275,1041123,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.3,"RP-242003","RP-242866","China Telecom ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242004; ; 26/9/24: 38.794 added;; 26/9/24: 38.746 added;; 26/9/24: 38.750 added;; 26/9/24: 38.792 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->30%; Stat Rep: RP-242004->RP-24286","38.794; 38.746; 38.750; 38.792",104,53,null,null,"2024-07-23","2024-12-06"]
[276,1040124,"Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.3,"RP-241932",null,"CMCC ",null,"26/9/24: WID:RP-241680->RP-241932",null,104,53,null,null,"2024-07-23","2024-09-26"]
[277,1041124,"   Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA Ues, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.3,"RP-241932","RP-242959","CMCC ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241931; ; 26/9/24: 38.795 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241931->RP-242959; ",38.795000000000002,104,53,null,null,"2024-07-23","2024-12-06"]
[278,1040128,"Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW",1,"Rel-19","R4","2024-06-06","2024-12-12",0.99,"RP-241930",null,"CMCC ",null,"26/9/24: WID:RP-241660->RP-241930",null,104,53,null,null,"2024-07-23","2024-09-26"]
[279,1041128,"   Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW-Core",2,"Rel-19","R4","2024-06-06","2024-12-12",0.99,"RP-241930","RP-242957","CMCC ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->20%; Stat Rep: ->RP-241929; ; 6/12/24: Compl:20%->99%; Stat Rep: RP-241929->RP-242957; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[280,0,"Rel-19 Radio: NR and LTE","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[281,1040118,"Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.2,"RP-241672",null,"China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ",null,104,53,null,null,"2024-07-23","NA"]
[282,1041118,"   Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.2,"RP-241672","RP-242860","China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241999; ; 26/9/24: 37.887 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->20%; Stat Rep: RP-241999->RP-2428",37.887,104,53,null,null,"2024-07-23","2024-12-06"]
[283,1040126,"Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs",1,"Rel-19","R4","2024-06-06","2024-09-09",0.15,"RP-242402",null,"Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 26/9/24: WID:RP-241684->RP-242402",null,104,53,null,null,"2024-07-23","2024-09-26"]
[284,1041126,"   Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.15,"RP-242402","RP-242603","Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->5%; WID: RP-241684->RP-231684; Stat Rep: ->RP-241757; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:5%->15%; Stat Rep: RP-241757->RP-242603; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[285,1040122,"Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.3,"RP-242341",null,"China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 26/9/24: WID:RP-241678->RP-242341",null,104,53,null,null,"2024-07-23","2024-09-26"]
[286,1041122,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.3,"RP-242341","RP-242610","China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-242019; ; 26/9/24: 37.898 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-242019-",37.898000000000003,104,53,null,null,"2024-07-23","2024-12-06"]
[287,1040125,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx",1,"Rel-19","R4","2024-06-06","2024-09-09",0.5,"RP-242088",null,"Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 26/9/24: WID:RP-241682->RP-242088",null,104,53,null,null,"2024-07-23","2024-09-26"]
[288,1041125,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.5,"RP-242088","RP-243015","Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242087; ; 26/9/24: 38.793 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Comp",38.792999999999999,104,53,null,null,"2024-07-23","2024-12-06"]
[289,1040119,"Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR",1,"Rel-19","R4","2024-06-06","2024-09-09",0.15,"RP-241786",null,"Nokia ",null,"26/9/24: WID:RP-241673->RP-241786",null,104,53,null,null,"2024-07-23","2024-09-26"]
[290,1041119,"   Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.15,"RP-241786","RP-242535","Nokia ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241785; ; 26/9/24: 37.719-11-11 added;; 26/9/24: 37.719-21-11 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->15%; Stat Rep: RP-241785->RP-242535; ","37.719-11-10; 37.719-11-11; 37.719-21-11",104,53,null,null,"2024-07-23","2024-12-06"]
[291,1030077,"UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4",1,"Rel-19","R4","2024-03-03","2025-03-03",0.33,"RP-241656",null,"Huawei ",null,"23/7/24: WID:RP-240828->RP-241656",null,103,52,null,null,"2024-04-02","2024-07-23"]
[292,1031077,"   Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.5,"RP-241656","RP-243011","Huawei ",null,"13/6/24: Compl:0%->20%; Stat Rep: ->RP-241236; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->35%; Stat Rep: RP-241236->RP-242084; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->50%; Stat Rep: RP-242084->RP-243011; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[293,1032077,"   Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0.2,"RP-241656","RP-243011","Huawei ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->15%; Stat Rep: ->RP-242084; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:15%->20%; Stat Rep: RP-242084->RP-243011; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[294,1030082,"Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2",1,"Rel-19","R4","2024-03-03","2025-03-03",0.19,"RP-242083",null,"KDDI ",null,"26/9/24: WID:RP-240838->RP-242083",null,103,52,null,null,"2024-04-02","2024-09-26"]
[295,1031082,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.45,"RP-242083","RP-242842","KDDI ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->35%; Stat Rep: ->RP-242079; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->45%; Stat Rep: RP-242079->RP-242842; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[296,1032082,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0,"RP-242083","RP-242842","KDDI ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-242079; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-242079->RP-242842; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[297,1030085,"FR1 TRP, TRS and MIMO OTA testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3",1,"Rel-19","R4","2024-03-03","2025-03-03",0.34,"RP-241623",null,"Vivo ",null,"23/7/24: WID:RP-240841->RP-241623",null,103,52,null,null,"2024-04-02","2024-07-23"]
[298,1031085,"   Core part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Core",2,"Rel-19","R4","2024-03-03","2025-09-09",0.45,"RP-241623","RP-242623","Vivo ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241043; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241043->RP-241828; ; 26/9/24: 38.762 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->45%; Stat Rep: RP-241828->RP-242623; ",38.762,103,52,null,null,"2024-04-02","2024-12-06"]
[299,1032085,"   Perf. Part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Perf",2,"Rel-19","R4","2024-03-03","2026-03-03",0.25,"RP-241623","RP-242623","Vivo ",null,"13/6/24: Stat Rep: ->RP-241043; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241043->RP-241828; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->25%; Stat Rep: RP-241828->RP-242623; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[300,0,"Rel-19 Radio: LTE","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[301,1040117,"Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN",1,"Rel-19","R4","2024-06-06","2025-03-03",0.99,"RP-241739",null,"Novamint ",null,"; 26/9/24: WID:RP-241649->RP-241739",null,104,53,null,null,"2024-07-23","2024-09-26"]
[302,1041117,"   Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Core",2,"Rel-19","R4","2024-06-06","2025-03-03",0.99,"RP-241739","RP-242460","Novamint ",null,"; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; Stat Rep: ->RP-241738; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->99%; Stat Rep: RP-241738->RP-242460; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[303,1042117,"   Perf.part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Perf",2,"Rel-19","R4","2024-06-06","2025-03-03",0.99,"RP-241739","RP-242460","Novamint ",null,"; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: ->RP-241738; ; 6/12/24: Compl:0%->99%; Stat Rep: RP-241738->RP-242460; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[304,1040116,"Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19",1,"Rel-19","R4","2024-06-06","2024-09-09",0.1,"RP-241681",null,"Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ",null,104,53,null,null,"2024-07-23","NA"]
[305,1041116,"   Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.1,"RP-242086","RP-242499","Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241814; ; 26/9/24: 36.767 added;; 6/12/24: FCD:09/09/2024->09/09/2025; WID: RP-241681->RP-242086; Stat Rep: RP-241814->RP-242499; ",36.767000000000003,104,53,null,null,"2024-07-23","2024-12-06"]
[306,1040115,"Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL",1,"Rel-19","R4","2024-06-06","2025-06-06",0.31,"RP-242086",null,"Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 26/9/24: WID:RP-241676->RP-242086",null,104,53,null,null,"2024-07-23","2024-09-26"]
[307,1041115,"   Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL-Core",2,"Rel-19","R4","2024-06-06","2025-09-09",0.31,"RP-242086","RP-243013","Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 4/9/24: FCD:09/09/2025->24/06/2025; Compl:0%->10%; Stat Rep: ->RP-242085; ; 26/9/24: 36.719-01-01 added;; 6/12/24: FCD:06/06/2025->09/09/2025; Compl:10%->31%; Stat Rep: RP-2420","36.719-01-01",104,53,null,null,"2024-07-23","2024-12-06"]
[308,0,"Rel-19 other topics","-",1,"Rel-19",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[309,1060056,"Study on 3GPP Cryptographic Inventory ","FS_CryptoInv",1,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241955",null,"Stawros Orkopoulos","stawros.orkopoulos@nokia.com",null,null,null,null,null,null,"2024-12-05","NA"]
[310,1060068,"Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",1,"Rel-19","S6","2024-12-05","2024-12-12",0,"SP-241695",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ",null,23.436,null,null,null,null,"2024-12-05","NA"]
[311,1060028,"MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",1,"Rel-19","S2","2024-12-05","2024-12-12",0,"SP-241498",null,"Rohit Abhishek (AT&T) ","ra503n@att.com ",null,"23.502; 23.501 ",null,null,null,null,"2024-12-05","NA"]
[312,1060030,"Network Controlled Network Slice Selection ","TEI19_SliceSel",1,"Rel-19","S2","2024-12-05","2024-12-12",0,"SP-241502",null,"Saito, Koji, KDDI ","kj-saitou_at_kddi_dot_com ",null,"23.501; 23.502; 23.503 ",null,null,null,null,"2024-12-05","NA"]
[313,1060031,"PRU Usage Extension supported by Core Network ","TEI19_PRUE",1,"Rel-19","S2","2024-12-05","2024-12-12",0,"SP-241504",null,"Hou, Yunjing, CATT ","houyunjing@catt.cn ",null,null,null,null,null,null,"2024-12-05","NA"]
[314,1040012,"CHF Segmentation ","CHFSeg",1,"Rel-19","S5","2024-06-12","2025-03-03",0.55000000000000004,"SP-241001",null,"Cetinkaya Egemen Kemal,Verizon ","(egemen.cetinkaya@verizon.com) ","; 4/9/24: 5%->25; 5/12/24: 25%->55","32.290; 32.291 ",104,53,null,null,"2024-06-12","2024-12-05"]
[315,1050121,"Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR",1,"Rel-19","R2","2024-09-09","2025-09-09",0.35,"RP-242413",null,"CAICT ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[316,1051121,"   Core part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Core",2,"Rel-19","R2","2024-09-09","2025-09-09",0.7,"RP-242413","RP-242580","CAICT ",null,"6/12/24: FCD:06/06/2025->09/09/2025; Compl:0%->70%; Stat Rep: ->RP-242580; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[317,1052121,"   Perf. part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Perf",2,"Rel-19","R4","2024-09-09","2025-09-09",0,"RP-242413","RP-242580","CAICT ",null,"6/12/24: Stat Rep: ->RP-242580; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[318,1050122,"Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE",1,"Rel-19","R2","2024-09-09","2025-09-09",0.21,"RP-242414",null,"Reliance Jio ",null,null,null,105,53,null,null,"2024-09-26","NA"]
[319,1051122,"   Core part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Core",2,"Rel-19","R2","2024-09-09","2025-06-06",0.5,"RP-242414","RP-243246","Reliance Jio ",null,"6/12/24: Compl:0%->50%; Stat Rep: ->RP-243246; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[320,1052122,"   Perf. part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Perf",2,"Rel-19","R4","2024-09-09","2025-09-09",0,"RP-242414","RP-243246","Reliance Jio ",null,"6/12/24: Stat Rep: ->RP-243246; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[321,1050033,"Data management regarding subscriptions and reporting ","Data_SREP",1,"Rel-19","S5","2024-09-04","2025-09-09",0,"SP-241380",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ",null,"28.537; 28.550; 28.532; 32.421; 32.422; 32.423; 28.404; 28.405; 28.622; 28.623 ",105,53,null,null,"2024-09-04","NA"]
[322,1040071,"Study on MC services support on IOPS mode of operation for 5G ","FS_Generic_IOPS",1,"Rel-19","S6","2024-07-16","2024-12-12",1,"SP-241017",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","4/9/24: 0%->40; 26/9/24: 23.700-09 added;; 5/12/24: 40%->100; 5/12/24: FCD:06/06/2025->12/24; 5/12/24: 40%->100","23.700-09",104,53,null,null,"2024-06-12","2024-12-05"]
[323,1050036,"MC services for generic support on IOPS mode of operation","Generic_IOPS",1,"Rel-19","S6","2024-09-04","2024-12-12",0.65,"SP-241382",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","; 5/12/24: 0%->100; 5/12/24: 100%->65",23.18,105,53,null,null,"2024-09-04","2024-12-05"]
[324,1050114,"Monitoring of signalling traffic in 5G ","MonSTra",1,"Rel-19","S1","2024-05-06","2024-12-12",0.28000000000000003,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100",22.260999999999999,105,53,null,null,"2024-06-12","2024-06-12"]
[325,1040082,"   Stage 1 for MonSta","MonSTra",2,"Rel-19","S1","2024-05-06","2024-06-06",1,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100",22.260999999999999,104,53,null,null,"2024-06-12","2024-06-12"]
[326,1050028,"   Security for MonStra ","MonStra-Sec",2,"Rel-19","S3","2024-09-04","2024-12-12",0,"SP-241376",null,"Vodafone, Susana Sabater","susana.sabatr@vodafone.com",null,33.500999999999998,105,53,null,null,"2024-09-04","NA"]
[327,1060012,"   Management for MonStra ","Monstra-OAM",2,"Rel-19","S5","2024-12-05","2024-12-12",0.8,"SP-241945",null,"Susana Sabater (Vodafone)","susana.sabater@vodafone.com","5/12/24: 0%->80",null,null,null,null,null,"2024-12-05","2024-12-05"]
[{"$f":"A328+1","v":328},1040036,"Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",1,"Rel-19","S2","2024-01-04","2025-09-09",0.69,"SP-241284",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","; 26/9/24: WID:SP-240996->SP-241284","23.501; 23.502; 23.548; 23.503 ",104,53,null,null,"2024-06-12","2024-09-26"]
[329,1020004,"   Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","FS_eEDGE_5GC_Ph3",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-240962",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 16/7/24: WID:SP-231796->SP-240962; 4/9/24: 90%->100",null,102,52,null,null,"2024-01-03","2024-09-04"]
[330,1030036,"   Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","FS_EDGE_Ph3",2,"Rel-19","S3","2024-04-02","2024-12-12",0.95,"SP-240510",null,"Ge Yao, ","yaog9@chinaunicom.cn ","3/4/24: 33.749 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->95",33.749000000000002,103,52,null,null,"2024-03-14","2024-12-05"]
[331,1060064,"   Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","EDGE_Ph3",2,"Rel-19","S3","2024-12-05","2025-03-03",0,"SP-241959",null,"TBD ",null,null,"33.501; 33.558 ",null,null,null,null,"2024-12-05","NA"]
[332,1050050,"   Stage 2 of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","S2","2024-06-12","2024-12-12",0.97,"SP-241505",null,"Meghashree Dattatri Kedalagudde (Intel); ","meghashree.dattatri.kedalagudde@intel.com","; 4/9/24: 0%->30; 5/12/24: 30%->97; 8/1/25: WID:SP-240996->SP-241505 (Rapp change)","23.501; 23.502; 23.548; 23.503 ",105,53,null,null,"2024-06-12","2025-01-08"]
[333,1050006,"   CT aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","C4","2024-09-09","2025-09-09",0.5,"CP-243049",null,"Luetzenkirchen, Thomas (Intel)","thomas.luetzenkirchen@intel.com",null,"29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591",105,53,null,"x","2024-06-12","NA"]
[334,1050051,"      CT3 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C3","2024-09-09","2025-09-09",0.6,"CP-243049",null,"Luetzenkirchen, Thomas (Intel)","thomas.luetzenkirchen@intel.com",null,null,105,53,null,"x","2024-06-12","NA"]
[335,1050052,"      CT4 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C4","2024-09-09","2025-09-09",0.4,"CP-243049",null,"Luetzenkirchen, Thomas (Intel)","thomas.luetzenkirchen@intel.com",null,null,105,53,null,"x","2024-06-12","NA"]
[336,1050056,"Multi-Access (ATSSS_Ph4) ","MASSS",1,"Rel-19","S2","2024-01-04","2025-09-09",0.56999999999999995,"SP-240994",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"2024-06-12","NA"]
[337,1020070,"   Study on Multi-Access (DualSteer and ATSSS_Ph4) ","FS_MASSS",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-240467",null,"Krisztian Kiss (Apple) ","krisztian@apple.com ","14/3/24: 0%->30; 2/4/24: WID:SP-231802->SP-240467; 2/4/24: FCD:09/09/2024->/24; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 30%->70; 4/9/24: 70%->100",null,102,52,null,null,"2024-01-03","2024-09-04"]
[338,1030037,"   Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) ","FS_MASSS_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240511",null,"Kolekar, Abhijeet (Intel) ","abhijeet.kolekar@intel.com ","3/4/24: 33.754 added;; 13/6/24: 0%->45; 5/9/24: 45%->95; 5/12/24: 95%->100",33.753999999999998,103,52,null,null,"2024-03-14","2024-12-05"]
[339,1040034,"   Stage 2 of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-241331",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ","; 4/9/24: 0%->50; 26/9/24: WID:SP-240994->SP-241331; 5/12/24: 50%->100","23.501; 23.502; 23.503 ",104,53,null,null,"2024-06-12","2024-12-05"]
[340,1050020,"   CT aspects of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","C1","2024-09-09","2025-09-09",0.3,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,"24.193, 24.501, 29.512, 29.244, 29.571",105,53,null,"x","2024-06-12","NA"]
[341,1050057,"      CT1 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C1","2024-09-09","2025-09-09",0.3,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","2024-06-12","NA"]
[342,1050058,"      CT3 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C3","2024-09-09","2025-09-09",0.2,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","2024-06-12","NA"]
[343,1050059,"      CT4 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C4","2024-09-09","2025-09-09",0.4,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","2024-06-12","NA"]
[344,1050066,"System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",1,"Rel-19","S2","2023-09-20","2025-09-09",0.41,"SP-240985",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985","23.228; 23.502 ",105,53,null,null,"2024-06-12","2024-07-16"]
[345,1010030,"   Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",2,"Rel-19","S2","2023-09-20","2024-09-09",1,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15; 14/3/24: 15%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->95; 5/12/24: 95%->100","23.700-77",101,51,null,null,"2023-09-20","2024-12-05"]
[346,1040016,"   Study on Charging aspects of next generation real time communication services phase 2 ","FS_NG_RTC_Ph2_CH",2,"Rel-19","S5","2024-06-12","2025-03-03",0.75,"SP-240982",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","13/6/24: 0%->10; 4/9/24: 10%->45; 26/9/24: 28.851 added;; 5/12/24: 45%->75; 5/12/24: FCD:12/12/2024->/25",28.850999999999999,104,53,null,null,"2024-06-12","2024-12-05"]
[347,1040026,"   Stage 2 of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","S2","2024-06-12","2024-12-12",0.7,"SP-241384",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985; 4/9/24: 0%->10; 26/9/24: WID:SP-240985->SP-241384; 5/12/24: 10%->70","23.228; 23.502 ",104,53,null,null,"2024-06-12","2024-12-05"]
[348,1050022,"   CT aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","C1","2024-09-09","2025-09-09",0.16,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"2024-06-12","2024-07-16"]
[349,1050067,"      CT1 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C1","2024-09-09","2025-09-09",0.2,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"2024-06-12","2024-07-16"]
[350,1050068,"      CT3 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C3","2024-09-09","2025-09-09",0.15,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"2024-06-12","2024-07-16"]
[351,1050069,"      CT4 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C4","2024-09-09","2025-09-09",0.3,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"2024-06-12","2024-07-16"]
[352,1050070,"      CT6 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C6","2024-09-09","2025-09-09",0,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"2024-06-12","2024-07-16"]
[353,1050078,"On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",1,"Rel-19","S2","2024-04-02","2025-09-09",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ",null,"23.502; 23.273 ",103,52,null,null,"2024-03-13","NA"]
[354,1030010,"   Stage 2 of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","S2","2024-04-02","2024-12-12",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 4/9/24: 0%->100","23.502; 23.273 ",103,52,null,null,"2024-03-13","2024-09-04"]
[355,1050003,"   CT aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","C4","2024-09-09","2025-09-09",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"2024-03-13","NA"]
[356,1050079,"      CT4 aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",3,"Rel-19","C4","2024-09-09","2025-09-09",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"2024-03-13","NA"]
[357,1030012,"Minimize the Number of Policy Associations ","TEI19_MINPA",1,"Rel-19","S2","2024-06-17","2025-03-03",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ",null,"23.502; 23.501; 23.503 ",103,52,null,null,"2024-03-13","NA"]
[358,1040078,"   Stage 2 of Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","S2","2024-06-17","2025-03-03",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ","13/6/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-06-13"]
[359,1040004,"   CT Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","C4","2024-06-17","2025-03-03",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"TS 29.503,TS 29.507,TS 29.513,TS 29.518,TS 29.525",101,51,null,null,"2023-09-06","2023-09-06"]
[360,1040052,"      CT3 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C3","2024-06-17","2025-03-03",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[361,1040053,"      CT4 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C4","2024-06-17","2025-03-03",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[362,1050089,"Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",1,"Rel-19","S2","2024-03-13","2024-12-12",0.99,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"2024-03-13","2024-06-13"]
[363,1030014,"   Stage 2 of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19","S2","2024-03-13","2024-06-06",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"2024-03-13","2024-06-13"]
[364,1050011,"   CT aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19","C3","2024-09-09","2024-12-12",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[365,1050090,"      CT3 aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",3,"Rel-19","C3","2024-09-09","2024-12-12",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[366,1030015,"Enhancing Parameter Provisioning with static UE IP address and UP security policy ","TEI19_IP_SP_EXP",1,"Rel-19","S2","2023-12-26","2025-06-06",0.97,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"2024-03-13","NA"]
[367,1040079,"   Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","S2","2023-12-26","2024-12-12",1,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 4/9/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-09-04"]
[368,1040007,"   CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","C3","2024-06-17","2025-06-06",0.95,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.522,29.503,29.522",101,51,null,"x","2023-09-06","2023-09-06"]
[369,1040056,"      CT3 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C3","2024-06-17","2025-06-06",0.9,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[370,1040057,"      CT4 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C4","2024-06-17","2025-06-06",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[371,1030017,"Multiple Location Procedure for Emergency LCS Routing ","TEI19_MLR4RTR",1,"Rel-19","S2","2024-03-13","2024-12-12",1,"SP-240123",null,"Simon Cai (Nokia Shanghai-Bell)Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","; 5/12/24: 0%->100",23.273,103,52,null,null,"2024-03-13","2024-12-05"]
[372,1030018,"Roaming traffic offloading via session breakout in HPLMN ","TEI19_HSBO",1,"Rel-19","S2","2024-04-02","2024-12-12",1,"SP-240491",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 5/12/24: 0%->100",23.501000000000001,103,52,null,null,"2024-03-13","2024-12-05"]
[373,1060043,"Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",1,"Rel-19","S2","2024-03-13","2025-03-03",0.99,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ",null,23.273,103,52,null,null,"2024-03-13","NA"]
[374,1030019,"   Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","S2","2024-03-13","2024-12-12",1,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ","; 5/12/24: 0%->100",23.273,103,52,null,null,"2024-03-13","2024-12-05"]
[375,1060004,"   CT aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","C4","2024-12-02","2025-03-03",0.99,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"29.515, 29.518, 29.572",103,52,null,"x","2024-03-13","NA"]
[376,1060044,"      CT4 aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",3,"Rel-19","C4","2024-12-02","2025-03-03",0.95,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,103,52,null,"x","2024-03-13","NA"]
[377,1050084,"QoS monitoring enhancement ","TEI19_QME",1,"Rel-19","S2","2024-04-02","2025-06-06",0.39,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-07-16"]
[378,1030020,"   Stage 2 of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-07-16"]
[379,1050012,"   CT aspects of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19","C3","2024-09-09","2025-06-06",0.31,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.122, 29.502, 29.512, 29.514, 29.522, 29.565",103,52,null,"x","2024-03-13","2024-07-16"]
[380,1050085,"      CT3 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C3","2024-09-09","2025-06-06",0.85,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,"x","2024-03-13","2024-07-16"]
[381,1050086,"      CT4 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C4","2024-09-09","2025-06-06",0.9,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,"x","2024-03-13","2024-07-16"]
[382,1060045,"Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",1,"Rel-19","S2","2024-03-13","2024-12-12",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100",null,103,52,null,null,"2024-03-13","2024-09-04"]
[383,1030021,"   Stage 2 of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19","S2","2024-03-13","2024-12-12",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100",23.401,103,52,null,null,"2024-03-13","2024-09-04"]
[384,1060001,"   CT aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19","C4","2024-12-02","2024-12-12",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,"29.272, 29.274, 29.230, 23.008 ",103,52,null,null,"2024-03-13","2024-09-04"]
[385,1060046,"      CT4 aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",3,"Rel-19","C4","2024-12-02","2024-12-12",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,null,103,52,null,null,"2024-03-13","2024-09-04"]
[386,1030022,"Providing per-subscriber VLAN instructions from UDM and DN-AAA ","TEI19_VLANSUB",1,"Rel-19","S2","2023-12-26","2025-06-06",0.8,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"2024-03-13","NA"]
[387,1040080,"   Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","S2","2023-12-26","2024-12-12",1,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 5/12/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-12-05"]
[388,1040006,"   CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","C3","2024-06-17","2025-06-06",0.7,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.561,29.503,29.561",101,51,null,null,"2023-09-06","2023-09-06"]
[389,1040054,"      CT3 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C3","2024-06-17","2025-06-06",0.5,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[390,1040055,"      CT4 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C4","2024-06-17","2025-06-06",0.9,"CP-241072",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[391,1050076,"NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",1,"Rel-19","S2","2024-04-02","2025-09-09",0.83,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[{"$f":"A392+1","v":392},1030023,"   Stage 2 of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19","S2","2024-04-02","2024-06-06",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"2024-03-13","2024-06-13"]
[393,1050005,"   CT aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19","C4","2024-09-09","2025-09-09",0.8,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[394,1050077,"      CT4 aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",3,"Rel-19","C4","2024-09-09","2025-09-09",0.8,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"2024-03-13","2024-06-13"]
[395,1020057,"Integrated Sensing and Communication ","Sensing",1,"Rel-19",null,"2022-03-10","2023-12-12",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[396,950003,"   Study on Integrated Sensing and Communication ","FS_Sensing",2,"Rel-19","S1","2022-03-10","2023-09-09",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",22.837,95,48,null,null,"2022-03-10","2023-09-06"]
[397,1000026,"   Stage 1 of Integrated Sensing and Communication ","Sensing",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"2023-06-08","2023-12-08"]
[398,1020086,"Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR",1,"Rel-19","R1","2023-12-13","2025-06-06",0.55000000000000004,"RP-242348","RP-242804","Yingyang Li, Jerome Vogedes, Xiaomi, AT&T","liyingyang@xiaomi.com, jerome.vogedes@att.com","14/3/24: Compl:0%->6%; Stat Rep: ->RP-240114; Rapporteur: Xiaomi->Yingyang Li, Jerome Vogedes, Xiaomi, AT&T; Rap eMail: ->liyingyang@xiaomi.com, jerome.vogedes@att.com; ; 2/4/24: WID:RP-234069->RP-240799; 13/6/24: Compl:6%->22%; Stat Rep: RP-240114->RP...",null,102,52,null,null,"2024-01-02","2024-12-06"]
[399,1020059,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19",null,"2022-06-02","2025-09-09",0.8,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[400,960017,"   Study on (Stage 1 of) UAV Phase 3 ","FS_UAV_Ph3",2,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-09-06"]
[401,1020069,"   Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM ","FS_UAS_Ph3",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-231801",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 4/9/24: 90%->100",null,102,52,null,null,"2024-01-03","2024-09-04"]
[402,1000032,"   Stage 1 of Uncrewed Aerial System Phase 3 ","UAS_Ph3",2,"Rel-19","S1","2023-06-08","2023-12-12",1,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"2023-06-08","2023-12-08"]
[403,1040037,"   (Stage 2 of) UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","S2","2024-06-12","2024-12-12",0.99,"SP-241287",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","; 4/9/24: 0%->65; 26/9/24: WID:SP-240997->SP-241287; 5/12/24: 65%->99","23.256; 23.288; 23.503; 23.502; 23.401 ",104,53,null,null,"2024-06-12","2024-12-05"]
[404,1050013,"   CT aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","C3","2024-09-09","2025-09-09",0.55000000000000004,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,"24.501, 24.301, 27.007, 29.122, 29.255, 29.256, 29.503, 29.518, 29.520, 29.522",105,53,null,"x","2024-06-12","NA"]
[405,1050091,"      CT1 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C1","2024-09-09","2025-09-09",0.75,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","2024-06-12","NA"]
[406,1050092,"      CT3 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C3","2024-09-09","2025-09-09",0.5,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","2024-06-12","NA"]
[407,1060047,"      CT4 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C4","2024-09-09","2025-09-09",0.4,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","2024-06-12","NA"]
[408,1060058,"   Security of Uncrewed Aerial System Phase 3 ","UAS_Ph3_Sec",2,"Rel-19","S3","2024-12-05","2025-03-03",0,"SP-241773",null,"Markus Hanhisalo, Ericsson ","markus.hanhisalo@ericsson.com ",null,33.256,null,null,null,null,"2024-12-05","NA"]
[409,1010008,"   Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",2,"Rel-19","S6","2023-09-07","2024-12-12",1,"SP-240741",null,"Roy, Michel, InterDigital ","michel.roy@interdigital.com","; 8/12/23: 0%->20; 14/3/24: 20%->40; 13/6/24: 40%->60; 16/7/24: WID:SP-230991->SP-240741; 4/9/24: 60%->75; 5/12/24: 75%->100","23.255; 23.434 ",101,51,null,null,"2023-09-07","2024-12-05"]
[410,1040043,"   CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",2,"Rel-19","C1","2024-06-17","2025-09-09",0.8,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[411,1040069,"      CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C1","2024-06-17","2025-09-09",0.8,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[412,1040070,"      CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C3","2024-06-17","2025-09-09",0.8,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[413,1030033,"   UAS security enhancements ","FS_UAS_Ph3_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240504",null,"Markus Hanhisalo, ","markus.hanhisalo@ericsson.com ","3/4/24: 33.759 added;; 13/6/24: 0%->50; 5/12/24: 50%->100",33.759,103,52,null,null,"2024-03-14","2024-12-05"]
[414,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","2022-06-02","2023-09-09",1,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.841000000000001,96,49,null,null,"2022-06-02","2023-12-08"]
[415,1040017,"Study on Charging aspects of Uncrewed Aerial Systems ","FS_UAS_CH",1,"Rel-19","S5","2024-06-12","2025-03-03",0.75,"SP-240983",null,"Jia Dong, China Mobile, ","dongjia@chinamobile.com ","4/9/24: 0%->40; 26/9/24: 28.853 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25",28.853000000000002,104,53,null,null,"2024-06-12","2024-12-05"]
[416,1020031,"Upper layer traffic steering and switching over dual 3GPP access ","DualSteer",1,"Rel-19","S1","2023-12-07","2023-12-12",0.95,"SP-231412",null,"Pica Francesco, Qualcomm ","fpica<at>qti.qualcomm.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"2023-12-07","2023-12-08"]
[417,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[418,1060048,"5G NR Femto","5G_Femto",1,"Rel-19","S2","2024-01-04","2025-09-09",0.7,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327","23.501; 23.502 ",104,53,null,null,"2024-06-12","2024-09-26"]
[419,1020002,"   Study on System aspects of 5G NR Femto ","FS_5G_Femto",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-231797",null,"Malla Reddy Sama (NTT DOCOMO) ","sama@docomolab-euro.com ","14/3/24: 0%->40; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->90; 4/9/24: 90%->100; 4/9/24: 100%->",null,102,52,null,null,"2024-01-03","2024-09-04"]
[420,1040028,"   System aspects of 5G NR Femto ","5G_Femto",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327; 5/12/24: 30%->100","23.501; 23.502 ",104,53,null,null,"2024-06-12","2024-12-05"]
[421,1060002,"   CT aspects of 5G NR Femto","5G_Femto",2,"Rel-19","C4","2024-12-12","2025-09-09",0.56999999999999995,"CP-243018",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,"29.244, 29.502, 29.503, 29.504, 29.505, 29.522, 29.571",104,53,null,null,"2024-06-12","2024-09-26"]
[422,1060049,"      CT3 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C3","2024-12-12","2025-09-09",0.75,"CP-243018",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,"29.244, 29.502, 29.503, 29.504, 29.505, 29.522, 29.571",104,53,null,null,"2024-06-12","2024-09-26"]
[423,1060050,"      CT4 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C4","2024-12-12","2025-09-09",0.4,"CP-243018",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,"29.244, 29.502, 29.503, 29.504, 29.505, 29.522, 29.571",104,53,null,null,"2024-06-12","2024-09-26"]
[424,1030028,"   Study on security aspects of 5G NR Femto Document for: Approval ","FS_5G_Femto_Sec",2,"Rel-19","S3","2024-04-02","2024-12-12",0.98,"SP-240505",null,"Peilin LIU (ZTE) ","liu.peilin@zte.com.cn , ","3/4/24: 33.745 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->98",33.744999999999997,103,52,null,null,"2024-03-14","2024-12-05"]
[425,1060062,"   Security aspects of 5G NR Femto ","5G_Femto_Sec",2,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241958",null,"Liu,Peilin liu.peilin@zte.com.cn ","Song,Hua songhua@chinamobile.com ",null,null,null,null,null,null,"2024-12-05","NA"]
[426,1050115,"Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",1,"Rel-19","S1","2024-01-04","2025-09-09",0.45,"SP-231037",null,"Hugh Shieh (AT&T) ","hs6220@att.com ",null,null,102,52,null,null,"2023-09-06","2023-09-06"]
[427,1020066,"   Study on Proximity-based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-231798",null,"Hugh Shieh (AT&T) ","hs6220@att.com ","14/3/24: 0%->45; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100",null,102,52,null,null,"2024-01-03","2024-09-04"]
[428,1040030,"   Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-240988",null,"Nassima Toumi (KPN N.V.)","nassima.toumi@tno.nl","; 4/9/24: 0%->70; 5/12/24: 70%->100",23.303999999999998,104,53,null,null,"2024-06-12","2024-12-05"]
[429,1050023,"   CT aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19","C1","2024-09-09","2025-09-09",0.43,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com","; 26/9/24: WID:CP-242108->SP-241290","24.554, 24.555, 24.501, 24.587, 29.519, 29.522, 29.525, 29.503, 29.504, 29.518, 29.510, 29.555, 29.559, 29.571, 31.102",105,53,null,"x","2024-06-12","2024-09-26"]
[430,1050038,"      CT1 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C1","2024-09-09","2025-09-09",0.4,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,"x","2024-06-12","NA"]
[431,1050116,"      CT3 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C3","2024-09-09","2025-09-09",0.6,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,null,null,null,"x","2024-06-12","NA"]
[432,1050039,"      CT4 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C4","2024-09-09","2025-09-09",0.7,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,"x","2024-06-12","NA"]
[433,1050040,"      CT6 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C6","2024-09-09","2025-09-09",0,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,"x","2024-06-12","NA"]
[434,1060057,"   Security Aspects of Proximity Based Services in 5GS Phase 3 ","5G_ProSe_Sec_Ph3",2,"Rel-19","S3","2024-12-05","2025-03-03",0,"SP-241956",null,"Primary Rapporteur: Ao Lei (Huawei) ","leiao@huawei.com ",null,33.503,null,null,null,null,"2024-12-05","NA"]
[435,1050030,"   Charging for 5G ProSe Ph3 ","5G_ProSe_Ph3_CH",2,"Rel-19","S5","2024-09-04","2025-09-09",0,"SP-241377",null,"Xiaoqian Jia (China Telecom)","jiaxq1@chinatelecom.cn ",null,"32.277; 32.291; 32.298 ",105,53,null,null,"2024-09-04","NA"]
[436,1030034,"Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3_SEC",1,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240513",null,"Lei, Ao (Huawei) ","leiao@huawei.com ","3/4/24: 33.743 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->100",33.743000000000002,103,52,null,null,"2024-03-14","2024-12-05"]
[437,1050100,"Vehicle Mounted Relays Phase 2 ","VMR_Ph2",1,"Rel-19","S2","2024-01-04","2025-06-06",0.83,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ",null,"23.501; 23.502; 23.273 ",105,53,null,null,"2024-06-12","NA"]
[438,1020067,"   Study on Vehicle Mounted Relays Phase 2 ","FS_VMR_Ph2",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-240493",null,"Primary Rapporteur: Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","14/3/24: 0%->40; 2/4/24: WID:SP-231799->SP-240493; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->95; 5/12/24: 95%->100",null,102,52,null,null,"2024-01-03","2024-12-05"]
[439,1040031,"   Stage 2 of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","; 4/9/24: 0%->40; 5/12/24: 40%->100","23.501; 23.502; 23.273 ",104,53,null,null,"2024-06-12","2024-12-05"]
[440,1050026,"   CT aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19","C1","2024-09-09","2025-06-06",0.7,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"2024-06-12","NA"]
[441,1050101,"      CT1 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C1","2024-09-09","2025-06-06",0.7,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"2024-06-12","NA"]
[442,1050102,"      CT4 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C4","2024-09-09","2025-06-06",0.7,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"2024-06-12","NA"]
[443,1050093,"Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",1,"Rel-19","S2","2024-01-04","2025-09-09",0.46,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com",null,null,105,53,null,null,"2024-06-20","NA"]
[444,1020063,"   Study on User Identities and Authentication Architecture ","FS_UIA_ARC",2,"Rel-19","S2","2024-01-04","2024-09-09",1,"SP-231804",null,"Michael Starsinic, Interdigital ","Michael.Starsinic@Interdigital.com ","14/3/24: 0%->35; 14/3/24: 23.700-32 added;; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 35%->90; 4/9/24: 90%->93; 5/12/24: 93%->100","23.700-32",102,52,null,null,"2024-01-03","2024-12-05"]
[445,1040085,"   Stage 2 of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19","S2","2024-06-20","2024-12-12",0.9,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com","4/9/24: 0%->15; 5/12/24: 15%->90",null,104,53,null,null,"2024-06-20","2024-12-05"]
[446,1050009,"   CT aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19","C4","2024-09-09","2025-09-09",0.27,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"2024-06-20","NA"]
[447,1050094,"      CT1 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C1","2024-09-09","2025-09-09",0.1,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"2024-06-20","NA"]
[448,1050095,"      CT3 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C3","2024-09-09","2025-09-09",0.6,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"2024-06-20","NA"]
[449,1050096,"      CT4 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C4","2024-09-09","2025-09-09",0.1,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"2024-06-20","NA"]
[450,1030032,"Study on security aspects of User Identities and Authentication ","FS_UIA_Sec",1,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240507",null,"Samir Ferdi, ","Samir.Ferdi@InterDigital.com ","3/4/24: 33.700-32 added;; 13/6/24: 0%->35; 5/9/24: 35%->65; 5/12/24: 65%->100","33.700-32",103,52,null,null,"2024-03-14","2024-12-05"]
[451,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","2022-03-10","2023-12-12",1,"SP-241693",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100; 8/1/25: WID:SP-220437->SP-241693",22.989000000000001,95,48,null,null,"2022-03-10","2025-01-08"]
[452,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","2023-06-08","2025-09-09",0.64,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50; 8/12/23: 50%->100","22.280; 22.179; 22.289; 22.261 ",100,51,null,null,"2023-06-08","2023-12-08"]
[453,1000038,"   Stage 2 of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","S6","2023-06-08","2024-12-12",1,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10; 8/12/23: 10%->30; 14/3/24: 30%->40. 14/5/24: acronym: enh4FRMCS ->FRMCS_Ph5 ; 13/6/24: 40%->55; 4/9/24: 55%->70; 5/12/24: 70%->100","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2024-12-05"]
[454,1050018,"   CT aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","C1","2024-09-09","2025-09-09",0.1,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"2023-06-08","2024-06-13"]
[455,1050103,"      CT1 aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",3,"Rel-19","C1","2024-09-09","2025-09-09",0.1,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"2023-06-08","2024-06-13"]
[{"$f":"A456+1","v":456},850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","2019-09-19","2022-09-08",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"2019-09-13","2022-09-09"]
[457,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","2022-06-02","2023-12-12",1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.916,96,49,null,null,"2022-06-02","2023-12-08"]
[458,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","2023-06-08","2024-12-12",0.4,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65",22.847999999999999,99,50,null,null,"2023-03-16","2023-12-08"]
[459,1030041,"Interconnect of SNPN ","ISN",1,"Rel-19","S1","2024-03-13","2024-03-29",1,"SP-240194",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 14/3/24: 0%->100",22.260999999999999,103,52,null,null,"2024-03-13","2024-03-14"]
[460,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100",22.103999999999999,99,50,null,null,"2023-03-16","2023-03-17"]
[461,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","2023-02-02","2023-03-03",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100",22.010999999999999,99,50,null,null,"2023-03-16","2023-08-09"]
[462,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[463,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","2023-05-22","2023-06-06",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,51,null,null,"2023-06-08","2023-06-08"]
[464,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[465,1040083,"MPS for Messaging services ","MPS4msg",1,"Rel-19",null,"2022-09-01","2025-09-09",0.79,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[466,970042,"   (stage 1 of) MPS for Messaging services ","MPS4msg",2,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[467,1040029,"   (stage 2 of) MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","S2","2024-06-12","2024-12-12",1,"SP-240987",null,"Robert Streijl (Peraton Labs), ","rstreijl@peratonlabs.com ","; 4/9/24: 0%->80; 5/12/24: 80%->100","23.401; 23.203; 23.501; 23.502; 23.503; 23.682; 23.204; 23.272; 23.228 ",104,53,null,null,"2024-06-12","2024-12-05"]
[468,1010031,"   Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",2,"Rel-19","S2","2024-01-03","2024-06-06",1,"SP-231197",null,"Robert Streijl (Peraton Labs) ","rstreijl@peratonlabs.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20; 14/3/24: 0%->70; 13/6/24: 70%->100; 4/9/24: 99%->100","23.700-75",101,51,null,null,"2023-09-20","2024-09-04"]
[469,1050007,"   CT aspects of MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","C4","2024-09-09","2025-09-09",0.72,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,"23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272, 29.336, 29.338, 24.501, 29.503, 29.513, 29.514, 29.518, 29.522, 29.562, 29.577, 23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272,",105,53,null,"x","2024-06-12","NA"]
[470,1050063,"      CT1 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C1","2024-09-09","2025-09-09",0.7,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,"x","2024-06-12","NA"]
[471,1050064,"      CT3 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C3","2024-09-09","2025-09-09",0.75,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,"x","2024-06-12","NA"]
[472,1050065,"      CT4 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C4","2024-09-09","2025-09-09",0.7,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,"x","2024-06-12","NA"]
[473,1050104,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","2022-09-01","2024-12-12",0.83,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[474,1050029,"   Study on MINT support in EPS for 5G-only national roaming UE","FS_MINT_Ph2",2,"Rel-19","C1","2024-09-09","2024-12-12",0.8,"CP-242249",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,97,49,null,null,"2022-09-09","2022-09-09"]
[475,970041,"   Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",2,"Rel-19","S1","2022-09-01","2022-09-19",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"2022-09-09","2022-09-09"]
[476,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","2022-12-09","2022-12-20",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100",22.260999999999999,98,50,null,null,"2022-12-09","2022-12-10"]
[477,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","2023-08-21","2023-09-09",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"2023-09-06","2023-09-06"]
[478,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","2022-12-13","2024-12-12",1,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45; 14/3/24: 45%->70; 13/6/24: 70%->85; 4/9/24: 85%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",26.933,98,50,null,null,"2022-12-09","2024-12-05"]
[479,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","2023-06-08","2024-12-12",1,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100; 5/12/24: FCD:09/09/2024->12/24","23.222 ; 23.700-92",100,51,null,null,"2023-06-08","2024-12-05"]
[480,1040073,"Application enablement aspects for MMTel ","MMTel_App",1,"Rel-19","S6","2024-07-16","2024-12-12",0.6,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60",23.792000000000002,104,53,null,null,"2024-06-12","2024-12-05"]
[481,1050053,"Enhanced application layer support for location services ","eLSAPP",1,"Rel-19","S6","2023-06-08","2025-09-09",0.76,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,"23.434; 23.436 ",105,53,null,null,"2024-06-12","NA"]
[482,1000035,"   Study on enhanced application layer support for location services ","FS_eLSAPP",2,"Rel-19","S6","2023-06-08","2024-09-09",1,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25; 14/3/24: 25%->40; 2/4/24: WID:SP-230778->SP-240295; 2/4/24: FCD:05/06/2024->/24; 13/6/24: 40%->85; 13/6/24: WID:SP-240295->SP-230778; 4/9/24: 85%->100","23.434 ; 23.700-72",100,51,null,null,"2023-06-08","2024-09-04"]
[483,1040072,"   Stage 2 of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19","S6","2024-06-12","2024-12-12",1,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 4/9/24: 0%->30; 5/12/24: 30%->100","23.434; 23.436 ",104,53,null,null,"2024-06-12","2024-12-05"]
[484,1050015,"   CT aspects of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19","C3","2024-09-09","2025-09-09",0.55000000000000004,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[485,1050054,"      CT1 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C1","2024-09-09","2025-09-09",0.5,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[486,1050055,"      CT3 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C3","2024-09-09","2025-09-09",0.6,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"2024-06-12","NA"]
[487,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","2023-06-08","2024-12-12",1,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5; 8/12/23: 5%->40; 14/3/24: 40%->90; 13/6/24: 90%->90; 4/9/24: 90%->100","23.280; 23.379; 23.281; 23.282 ",100,51,null,null,"2023-06-08","2024-09-04"]
[488,1060051,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19","S6","2023-06-08","2025-06-06",0.68,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50",null,100,51,null,null,"2023-06-08","2024-09-04"]
[489,1000037,"   5GMSG Service phase 3 ","5GMARCH_Ph3",2,"Rel-19","S6","2023-06-08","2024-12-12",1,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50; 5/12/24: 50%->100; 5/12/24: FCD:09/09/2024->12/24",null,100,51,null,null,"2023-06-08","2024-12-05"]
[490,1060019,"   CT aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",2,"Rel-19","C1","2024-12-02","2025-06-06",0,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"2023-06-08","2024-09-04"]
[491,1060052,"      CT1 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C1","2024-12-02","2025-06-06",0,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"2023-06-08","2024-09-04"]
[492,1060053,"      CT3 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C3","2024-12-02","2025-06-06",0,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"2023-06-08","2024-09-04"]
[493,1030030,"   Security aspects for MSGin5G Service Phase 3 ","5GMARCH_SEC_Ph3",2,"Rel-19","S3","2024-04-02","2024-12-12",1,"SP-240516",null,"Xiaoting Huang, ","huangxiaoting@chinamobile.com ","; 13/6/24: 0%->70; 5/9/24: 70%->100",33.500999999999998,103,52,null,null,"2024-03-14","2024-09-05"]
[494,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","2023-06-08","2024-12-12",1,"SP-241691",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30; 14/3/24: 30%->40; 13/6/24: 40%->60; 4/9/24: 60%->75; 5/12/24: 75%->100; 8/1/25: WID:SP-230988->SP-241691","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,51,null,null,"2023-06-08","2025-01-08"]
[495,1050071,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19","S6","2023-09-07","2025-09-09",0.74,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70",null,101,51,null,null,"2023-09-07","2024-06-13"]
[496,1010006,"   Stage 2 of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","S6","2023-09-07","2024-12-12",1,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100",null,101,51,null,null,"2023-09-07","2024-12-05"]
[497,1050017,"   CT aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","C1","2024-09-09","2025-09-09",0.56999999999999995,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.543, 24.548, 29.548, 29.549",101,51,null,"x","2023-09-07","2024-06-13"]
[498,1050072,"      CT1 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C1","2024-09-09","2025-09-09",0.35,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,"x","2023-09-07","2024-06-13"]
[499,1050073,"      CT3 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C3","2024-09-09","2025-09-09",0.8,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,"x","2023-09-07","2024-06-13"]
[500,1040081,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19",null,"2023-09-07","2025-09-09",0.59,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35",23.558,101,51,null,null,"2023-09-07","2024-03-14"]
[501,1010007,"   Stage 2 of enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",2,"Rel-19","S6","2023-09-07","2024-12-12",1,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35; 13/6/24: 35%->80; 4/9/24: 80%->85; 5/12/24: 85%->100",23.558,101,51,null,null,"2023-09-07","2024-12-05"]
[502,1040008,"   CT aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",2,"Rel-19","C3","2024-06-17","2025-06-06",0.38,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com",null,"24.558,29.558",101,51,null,null,"2023-09-06","2023-09-06"]
[503,1040058,"      CT1 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C1","2024-06-17","2025-09-09",0.25,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: FCD:06/06/2025->/25",null,101,51,null,null,"2023-09-06","2024-07-16"]
[504,1040059,"      CT3 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C3","2024-06-17","2025-09-09",0.5,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: 0%->100",null,101,51,null,null,"2023-09-06","2024-07-16"]
[505,0,"Rel-19 miscellaneous Security",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[506,1030029,"Security Assurance Specification for maintenance of 5G features ","SCAS_5G_Maint",1,"Rel-19","S3","2024-04-02","2025-03-03",1,"SP-240515",null,"Rong Wu (Huawei) ","raina.wu@huawei.com ","5/9/24: 0%->50; 5/12/24: 50%->100",null,103,52,null,null,"2024-03-14","2024-12-05"]
[507,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","2023-09-06","2024-09-09",0.8,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 8/12/23: 0%->10; 3/4/24: 33.530 added;; 13/6/24: 10%->50; 5/9/24: 50%->60; 5/12/24: 60%->80","33.926 ; 33.530",101,51,null,null,"2023-09-06","2024-12-05"]
[508,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","2023-09-06","2024-09-09",1,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in","8/12/23: 0%->10; 4/1/24: 33.529 added;; 14/3/24: 10%->40; 13/6/24: 40%->70; 5/9/24: 70%->40; 5/9/24: 40%->100; 5/12/24: 100%->100",33.529000000000003,101,51,null,null,"2023-09-06","2024-12-05"]
[509,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","2023-09-06","2024-03-03",1,"SP-240476",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ","8/12/23: 0%->10; 4/1/24: 35.248 added;; 14/3/24: 10%->100; 2/4/24: WID:SP-231159->SP-240476","35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240",101,51,null,null,"2023-09-06","2024-04-02"]
[510,1020036,"Addition of Milenage-256 algorithm ","Milenage_256",1,"Rel-19","S3","2024-01-03","2024-12-12",1,"SP-241087",null,"Mireille Pauliac ","mireille.pauliac@thalesgroup.com ","4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;; 14/3/24: 0%->5; 5/9/24: 5%->65; 26/9/24: WID:SP-231792->SP-241087; 5/12/24: 65%->100","35.237; 35.236; 35.235; 35.234",102,52,null,null,"2023-12-07","2024-12-05"]
[511,1020041,"Study on enabling a cryptographic algorithm transition to 256-bits ","FS_CAT256",1,"Rel-19","S3","2024-01-03","2024-12-12",1,"SP-231788",null,"Yuto Nakano ","yt-nakano@kddi.com ","4/1/24: 33.700-41 added;; 14/3/24: 0%->10; 13/6/24: 10%->90; 5/9/24: 90%->100","33.700-41",102,52,null,null,"2023-12-07","2024-09-05"]
[512,1020034,"Study on enablers for Zero Trust Security ","FS_eZTS",1,"Rel-19","S3","2024-01-03","2024-12-12",0.95,"SP-231784",null,"Sheeba Backia Mary Baskaran ","smary@lenovo.com ","4/1/24: 33.794 added;; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->75; 5/12/24: 75%->95",33.793999999999997,102,52,null,null,"2023-12-07","2024-12-05"]
[513,1020035,"Mission critical security enhancements for release 19 ","MCXSec4",1,"Rel-19","S3","2024-01-04","2024-12-12",0.9,"SP-231783",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 14/3/24: 0%->10; 5/9/24: 10%->50; 5/12/24: 50%->90",33.18,102,52,null,null,"2023-12-07","2024-12-05"]
[514,1020038,"Study on the security support for the Next Generation Real Time Communication services phase 2 ","FS_NG_RTC_SEC_Ph2",1,"Rel-19","S3","2024-01-03","2024-12-12",0.8,"SP-240233",null,"Vlasios Tsiatsis ","vlasios.tsiatsis@ericsson.com ","4/1/24: 33.790 added;; 14/3/24: 0%->17; 2/4/24: WID:SP-231785->SP-240233; 13/6/24: 17%->40; 5/9/24: 40%->60; 5/12/24: 60%->80",33.79,102,52,null,null,"2023-12-07","2024-12-05"]
[515,1060063,"Security support for the Next Generation Real Time Communication services Phase 2 ","NG_RTC_SEC_Ph2",1,"Rel-19","S3","2024-12-05","2025-03-03",0,"SP-241778",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ",null,33.203000000000003,null,null,null,null,"2024-12-05","NA"]
[516,1020040,"Study of ACME for Automated Certificate Management in SBA ","FS_ACME_SBA",1,"Rel-19","S3","2024-01-03","2024-12-12",1,"SP-231787",null,"Charles Eckel ","eckelcu(at)cisco.com ","4/1/24: 33.776 added;; 14/3/24: 0%->15; 13/6/24: 15%->45; 13/6/24: FCD:06/06/2024->12/24; 5/9/24: 45%->55; 5/12/24: 55%->100",33.776000000000003,102,52,null,null,"2023-12-07","2024-12-05"]
[517,1060066,"Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) ","ACME_SBA",1,"Rel-19","S3","2024-12-05","2025-06-06",0,"SP-241960",null,"Charles Eckel (Cisco)","eckelcu(at)cisco.com",null,33.31,null,null,null,null,"2024-12-05","NA"]
[518,1020042,"3GPP profiles for cryptographic algorithms and security protocols ","CryptoSP",1,"Rel-19","S3","2024-01-03","2024-12-12",1,"SP-231793",null,"Mohsin Khan A ","mohsin.a.khan@ericsson.com ","; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->80; 5/12/24: 80%->100","33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 ",102,52,null,null,"2023-12-07","2024-12-05"]
[519,1020043,"Study on mitigations against bidding down attacks ","FS_MiBiDA",1,"Rel-19","S3","2024-01-03","2024-12-12",1,"SP-231789",null,"Noamen Ben Henda ","noamen.ben.henda@huawei.com ","4/1/24: 33.701 added;; 14/3/24: 0%->20; 13/6/24: 20%->85; 13/6/24: FCD:05/06/2024->12/24; 5/9/24: 85%->100",33.701000000000001,102,52,null,null,"2023-12-07","2024-09-05"]
[{"$f":"A520+1","v":520},1060054,"Mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",1,"Rel-19","S3","2024-01-03","2025-09-09",0.11,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088",33.500999999999998,104,53,null,null,"2024-06-12","2024-09-26"]
[521,1020045,"   Study on Security for mobility over non-3GPP access to avoid full primary authentication ","FS_Non3GPPMob_Sec",2,"Rel-19","S3","2024-01-03","2024-12-12",0.25,"SP-231791",null,"Saurabh Khare, Nokia ","Saurabh.Khare@nokia.com ","4/1/24: 33.702 added;; 14/3/24: 0%->25",33.701999999999998,102,52,null,null,"2023-12-07","2024-03-14"]
[522,1040024,"   Security for mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",2,"Rel-19","S3","2024-06-12","2024-12-12",0,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088",33.500999999999998,104,53,null,null,"2024-06-12","2024-09-26"]
[523,1060020,"   CT aspects of security for mobility over non-3GPP access to avoid full primary authentication","Non3GPPMob_Sec",2,"Rel-19","C1","2024-12-02","2025-09-09",0,"CP-243269",null,"Nassar, Mohamed Amin, Nokia","mohamed.a.nassar@nokia.com",null,24.501999999999999,104,53,null,null,"2024-06-12","2024-09-26"]
[524,0,"Rel-19 miscellaneous OAM&charging",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[525,1060006,"Service Based Management Architecture enhancement phase 3 ","SBMA_Ph3",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241939",null,"Kai Zhang (Huawei)","kai.zhangkai@huawei.com",null,"32.156; 28.532; 28.533; 28.537; 28.622; 28.623; 28.530; 28.550; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.552; 28.554; 28.558; 32.130; 28.313; 28.314; 28.623; 28.310; 28.530; 28.531; 28.111; 28.550; 28.621; 28.623; 32.421; 32.422; 28.404; 28.405;",null,null,null,null,"2024-12-05","NA"]
[526,1020019,"Study on Management Data Analytics (MDA) Phase 3 ","FS_eMDAS_Ph3",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-241157",null,"Brendan T Hassett (Huawei) ","brendan.t.hassett@huawei.com ","13/6/24: 0%->70; 16/7/24: WID:SP-231726->SP-240968; 4/9/24: 70%->90; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: WID:SP-240968->SP-241157; 5/12/24: 90%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[527,1060014,"Management Data Analytics phase 3 ","eMDAS_Ph3",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241947",null,"Brendan T Hassett (Huawei)","brendan.t.hassett@huawei.com",null,28.103999999999999,null,null,null,null,"2024-12-05","NA"]
[528,1020008,"Study on intent driven management services for mobile network phase 3 ","FS_IDMS_MN_Ph3",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231737",null,"Ruiyue Xu (Huawei) ","xuruiyue@huawei.com ","14/3/24: 0%->5; 13/6/24: 5%->70; 4/9/24: 70%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[529,1060013,"Intent driven management services for mobile network phase 3 ","IDMS_MN_Ph3",1,"Rel-19","S5","2024-12-05","2025-06-06",0,"SP-241946",null,"Ruiyue Xu (Huawei)","xuruiyue@huawei.com",null,28.312000000000001,null,null,null,null,"2024-12-05","NA"]
[530,1020009,"Study on closed control loop management ","FS_CCLM",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231735",null,"Deepanshu Gautam (Samsung) ","deepanshu.g@samsung.com ","14/3/24: 0%->5; 13/6/24: 5%->40; 4/9/24: 40%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[531,1020018,"Study on management aspects of Network Digital Twin ","FS_NDT",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231727",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com ","4/1/24: 28.915 added;; 14/3/24: 0%->5; 13/6/24: 5%->65; 13/6/24: WID:SP-231428->SP-231727; 4/9/24: 65%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100",28.914999999999999,102,52,null,null,"2023-12-07","2024-12-05"]
[532,1060005,"Management aspects of Network Digital Twins ","NDT",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241938",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com",null,null,null,null,null,null,"2024-12-05","NA"]
[533,1020010,"Study on Cloud Aspects of Management and Orchestration ","FS_Cloud_OAM",1,"Rel-19","S5","2024-01-03","2024-12-12",0.9,"SP-241566",null,"Guangjing Cao (CMCC)","caoguangjing@chinamobile.com","14/3/24: 0%->2; 13/6/24: 2%->40; 4/9/24: 40%->80; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 80%->90; 8/1/25: WID:SP-231781->SP-241566 (rapp changed)",null,102,52,null,null,"2023-12-07","2025-01-08"]
[534,1020016,"Study on Enablers for Security Monitoring ","FS_SECM",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231736",null,"Clifton Fernandes (Nokia) ","clifton.fernandes@nokia.com ","4/1/24: 28.870 added;; 4/9/24: 0%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",28.87,102,52,null,null,"2023-12-07","2024-12-05"]
[535,1020011,"Study on Service Based Management Architecture enhancement phase 3 ","FS_SBMA_Ph3",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-241569",null,"Kai Zhang (Huawei) ","kai.zhangkai@huawei.com ","13/6/24: 0%->45; 4/9/24: 45%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100; 8/1/25: WID:SP-231725->SP-241569",null,102,52,null,null,"2023-12-07","2025-01-08"]
[536,1020033,"Study on Management of planned configurations ","FS_PlanM",1,"Rel-19","S5","2024-01-04","2024-09-09",1,"SP-231721",null,"Olaf Pollakowski (Nokia) ","olaf.pollakowski@nokia.com ","4/1/24: 28.872 added;; 13/6/24: 0%->60; 4/9/24: 60%->100",28.872,102,52,null,null,"2024-01-03","2024-09-04"]
[537,1050032,"Management of planned configurations ","PlanM",1,"Rel-19","S5","2024-09-04","2025-09-09",0.6,"SP-241379",null,"Olaf Pollakowski (Nokia)","olaf.pollakowski@nokia.com","26/9/24: 28.572 added;; 5/12/24: 0%->60",28.571999999999999,105,53,null,null,"2024-09-04","2024-12-05"]
[538,1060010,"Closed Control Loop Management ","CCLM",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241943",null,"Deepanshu Gautam (Samsung)","deepanshu.g@samsung.com",null,"28.535; 28.536; 28.622; 32.161 ",null,null,null,null,"2024-12-05","NA"]
[539,1020025,"Data management phase 2 ","MADCOL_Ph2",1,"Rel-19","S5","2024-01-03","2025-06-06",0.88,"SP-240877",null,"Sivaramakrishnan Swaminathan (Nokia) ","sivaramakrishnan.swaminathan@nokia.com ","; 13/6/24: 0%->50; 16/7/24: WID:SP-231746->SP-240877; 4/9/24: 50%->80; 5/12/24: 80%->88","28.622; 28.623 ",102,52,null,null,"2023-12-07","2024-12-05"]
[540,1020012,"Study on data management regarding subscriptions and reporting ","FS_Data_SREP",1,"Rel-19","S5","2024-01-03","2024-09-09",1,"SP-231732",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","13/6/24: 0%->60; 4/9/24: 60%->100",null,102,52,null,null,"2023-12-07","2024-09-04"]
[541,1020026,"5G performance measurements and KPIs phase 4 ","PM_KPI_5G_Ph4",1,"Rel-19","S5","2024-01-03","2025-06-06",0.65,"SP-241155",null,"Ruan bang qiu","ruan.bangqiu@zte.com.cn","; 13/6/24: 0%->20; 4/9/24: 20%->30; Rapporteur update: Xiebaoguo->Ruan bang qiu (ruan.bangqiu@zte.com.cn); 26/9/24: WID:SP-231747->SP-241155; 5/12/24: 30%->65","28.552; 32.425; 28.554; 28.532; 28.550; 28.abc ",102,52,null,null,"2023-12-07","2024-12-05"]
[542,1020027,"5G Advanced NRM features phase 3 ","AdNRM_Ph3",1,"Rel-19","S5","2024-01-03","2025-06-06",0.6,"SP-241565",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-231745->SP-240875; 4/9/24: 15%->30; 5/12/24: 30%->60; 8/1/25: WID:SP-240875->SP-241565","28.540; 28.541; 28.622; 28.623 ",102,52,null,null,"2023-12-07","2025-01-08"]
[543,1020028,"Subscriber and Equipment Trace and QoE collection management ","TraceQoE_OAM",1,"Rel-19","S5","2024-01-03","2025-06-06",0.75,"SP-231748",null,"Zu Qiang (Ericsson) ","zu.qiang@ericsson.com ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 5/12/24: 40%->75","32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 ",102,52,null,null,"2023-12-07","2024-12-05"]
[544,1020013,"Study on Management Aspects of NTN Phase 2 ","FS_NTN_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231733",null,"MingRui Sun (China Unicom) ","sunmr19@chinaunicom.cn ","13/6/24: 0%->65; 4/9/24: 65%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[545,1020014,"Study on management of IAB nodes ","FS_NR_mobile_IAB_OAM",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231729",null,"JunFeng Wang (Ericsson) ","junfeng.a.wang@ericsson.com ","13/6/24: 0%->40; 13/6/24: FCD:09/09/2024->12/24; 4/9/24: 40%->90; 5/12/24: 90%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[546,1060015,"Management of IAB nodes ","NR_MOBILE_IAB_OAM",1,"Rel-19","S5","2024-12-05","2025-09-09",0,"SP-241948",null,"JunFeng Wang (Ericsson)","junfeng.a.wang@ericsson.com",null,"28.541; 28.540; 28.531; 28.314; 28.315 ",null,null,null,null,"2024-12-05","NA"]
[547,1020017,"Study on management aspects of RedCap feature ","FS_NR_RedCap_OAM",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-231734",null,"Zhen Xing (China Unicom) ","xingz12@chinaunicom.cn ","13/6/24: 0%->50; 4/9/24: 50%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[548,1020020,"Study on Enhancement of Management Aspects related to NWDAF Phase 2 ","FS_NWDAF_OAM_Ph2",1,"Rel-19","S5","2024-01-03","2024-09-09",1,"SP-231724",null,"Primary Rapporteur: Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","13/6/24: 0%->75; 4/9/24: 75%->100",null,102,52,null,null,"2023-12-07","2024-09-04"]
[549,1050031,"Enhancement of Management Aspects Related of NWDAF Phase 2 ","NWDAF_OAM_Ph2",1,"Rel-19","S5","2024-09-04","2025-06-06",0.6,"SP-241378",null,"Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","; 5/12/24: 0%->60","28.552; 28.541 ",105,53,null,null,"2024-09-04","2024-12-05"]
[550,1020015,"Study on Management of Network Sharing Phase3 ","FS_NetShare_OAM_Ph3",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-240966",null,"ZhaoNing Wang (China Unicom) ","wangzn18@chinaunicom.cn ","13/6/24: 0%->50; 16/7/24: WID:SP-231731->SP-240966; 4/9/24: 50%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"2023-12-07","2024-12-05"]
[551,1020022,"Study on Enhanced OAM for management exposure to external consumers ","FS_MExpo",1,"Rel-19","S5","2024-01-03","2024-12-12",1,"SP-241570",null,"Srilakshmi Srinivasaraju (Nokia)","srilakshmi.s@nokia.com","14/3/24: 0%->5; 13/6/24: 5%->50; 16/7/24: WID:SP-231728->SP-240967; 4/9/24: 50%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-240967->SP-241570",null,102,52,null,null,"2023-12-07","2025-01-08"]
[552,0,"Rel-19 other",null,1,"Rel-19",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2023-12-07","NA"]
[553,1060055,"Reducing Information Exposure over SBI ","RedInfExp_SBI",1,"Rel-19","C4","2023-06-07","2025-09-09",0.43,"CP-243019",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;",null,100,51,null,null,"2023-06-07","2023-06-30"]
[554,1000001,"   Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",2,"Rel-19","C4","2023-06-07","2023-12-12",1,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;",29.856999999999999,100,51,null,null,"2023-06-07","2023-06-30"]
[555,1060003,"   Reducing Information Exposure over SBI ","RedInfExp_SBI",2,"Rel-19","C4","2024-12-02","2025-09-09",0.05,"CP-243308",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;","29.510, 29.500",100,51,null,"x","2023-06-07","2023-06-30"]
[556,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-19","C4","2022-08-25","2024-03-03",1,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,null,"2022-06-03","2023-09-21"]
[557,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-19","S4","2023-06-08","2024-09-09",1,"SP-241389",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->3/3/25; Rel-18->Rel-19; 13/6/24: 30%->; 4/9/24: 30%->100; 4/9/24: FCD:03/03/2025->09/24; 4/9/24: WID:SP-230539->SP-241120 ; 26/9/24: WID:SP-...","26.955 ; 26.855",100,51,null,null,"2023-06-08","2024-09-26"]
[558,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-19","S4","2023-06-08","2025-03-03",0.6,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->12/24; ; Rel-18->Rel-19; 13/6/24: 30%->50; 4/9/24: 50%->55; 5/12/24: 55%->60; 5/12/24: FCD:12/12/2024->/25",26.812999999999999,100,51,null,null,"2023-06-08","2024-12-05"]
[559,1040001,"Service Based Interface Protocol Improvements Release 19","SBIProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.3,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[560,1040050,"   CT3 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0.4,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[561,1040051,"   CT4 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C4","2024-06-17","2025-09-09",0.2,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[562,1040003,"Subscriber Data Migration","SUBDMIG",1,"Rel-19","C4","2024-06-17","2024-12-12",0.8,"CP-241023",null,"Jesus de Gregorio, Ericsson","Jesus de Gregorio, jesus.de.gregorio@ericsson.com",null,"23.527,29.503,29.504,29.510,29.571",101,51,null,null,"2023-09-06","2023-09-06"]
[563,1050010,"Rel-19 Enhancements of Network Automation Enablers","eNetAE19",1,"Rel-19","C3","2024-06-17","2025-09-09",0.4,"CP-243078",null,"Xuefei Zhang (Huawei)","summer.xuefei@huawei.com",null,"29.508, 29.517, 29.520, 29.522, 29.552, 29.574, 29.575, 29.576, 29.591",101,51,null,null,"2023-09-06","2024-09-26"]
[564,1040005,"Study on Protocol for AI Data Collection from UPF","FS_PAIDC_UPF",1,"Rel-19","C4","2024-06-17","2025-03-03",0.4,"CP-241025",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[565,1040039,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.3,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[566,1040062,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[567,1040063,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0.4,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[568,1040041,"Protocol enhancements for Mission Critical Services","MCProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.2,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[569,1040064,"   CT1 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[570,1040065,"   CT3 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C3","2024-06-17","2025-09-09",0.4,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[571,1040066,"   CT4 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C4","2024-06-17","2025-09-09",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[572,1040042,"Enhancement of controlling RAT utilization","ECRATU",1,"Rel-19",null,"2024-06-17","2025-09-09",0.63,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,"24.301, 24.501, 23.122, 29.272, 29.503",101,51,null,"x","2023-09-06","2023-09-06"]
[573,1040067,"   CT1 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C1","2024-06-17","2025-09-09",0.75,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[574,1040068,"   CT4 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C4","2024-06-17","2025-09-09",0.5,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,"x","2023-09-06","2023-09-06"]
[575,1040045,"Enhanced Mission Critical Location Management","enhMCLoc",1,"Rel-19","C1","2024-06-17","2025-09-09",0.3,"CP-241288",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281,24.282,24.283,24.379,24.481,24.482,24.483,24.484,29.379",101,51,null,null,"2023-09-06","2023-09-06"]
[576,1050027,"Alignment of eCall over IMS with CEN","eCallCEN",1,"Rel-19","C1","2024-09-09","2025-03-03",0.85,"CP-242254",null,"Osama Lotfallah, Qualcomm Incorporated","osamal@qti.qualcomm.com",null,null,101,51,null,null,"2023-09-06","2023-09-06"]
[577,1060025,"Rel-19 Enhancements of UE Policy","UEP19",1,"Rel-19","C3","2024-12-02","2025-09-09",0.25,"CP-243073",null,"Susana Fernández, Ericsson","Susana.fernandez@ericsson.com",null,"29.525, 29.523, 29.519, 29.522, 29.513",101,51,null,null,"2023-09-06","2023-09-06"]
[578,1060018,"NAS layer overhead reduction for data transfer using CP CIoT","NORDAT_CP",1,"Rel-19","C1","2024-12-02","2025-09-09",0,"CP-243270",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"24.301, 24.007",101,51,null,null,"2023-09-06","2023-09-06"]
[579,1040044,"Stage-3 5GS NAS protocol development 18 ","5GProtoc19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.2,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","2023-06-06"]
[580,1040046,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc19",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","NA"]
[581,1040047,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc19-non3GPP",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"2022-06-03","NA"]
[582,1040040,"Stage-3 SAE Protocol Development ","SAES19",1,"Rel-19",null,"2024-06-17","2025-09-09",0.2,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","2023-06-06"]
[583,1040048,"   Stage-3 SAE Protocol Development general","SAES19",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","NA"]
[{"$f":"A584+1","v":584},1040049,"   Stage-3 SAE Protocol Development non 3GPP","SAES19-non3GPP",2,"Rel-19","C1","2024-06-17","2025-09-09",0.2,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"2022-06-03","NA"]
[585,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","2023-03-24","2024-09-09",0.15,"SP-230242",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater; 5/9/24: 0%->10; 5/12/24: 10%->15","33.107; 33.108; 33.126; 33.127; 33.128 ",97,49,null,null,"2022-09-11","2024-12-05"]
[586,1040010,"Lawful Interception Guidance Rel-19 ","LI19_Guide",1,"Rel-19","S3LI","2024-07-16","2025-03-03",0.52,"SP-240562",null,"Nag Rao, Nokia, ","nagaraja.rao@nokia.com ","5/12/24: 0%->52",null,104,53,null,null,"2024-07-16","2024-12-05"]
[587,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"2022-09-09","2022-12-12",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[588,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[589,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[590,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"2021-06-11","2023-12-12",1,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[591,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","2021-06-11","2021-06-18",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[592,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"2021-12-19","2022-12-10"]
[593,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[594,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","2023-06-06"]
[595,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"2022-09-11","NA"]
[596,1020024,"Charging aspects of Satellite Backhaul in 5GS ","5GSATB_CH",1,"Rel-18","S5","2023-12-07","2024-03-03",1,"SP-240266",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","SP-231707 shows UID 1020023 but this duplicates with SP-231706, so changed here to 1020024.; 15/3/24: 0%->100; 2/4/24: WID:SP-231707->SP-240266","32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 ",102,52,null,null,"2023-12-07","2024-04-02"]
[597,1020029,"Management aspects of 5G system supporting satellite backhaul ","5GSATB_OAM",1,"Rel-18","S5","2023-12-07","2024-03-03",1,"SP-231708",null,"Wen Qi, China Telecom ","qiw@chinatelecom.cn ","; 14/3/24: 0%->100","28.541; 28.552 ",102,52,null,null,"2024-01-03","2024-03-14"]
[598,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[599,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"2021-12-19","2022-12-10"]
[600,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"2022-12-09","2024-03-03",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","NA"]
[601,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"2022-12-09","2023-06-08"]
[602,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[603,990056,"   deleted - CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","; 15/3/24: 0%->100","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"2022-12-09","2024-03-15"]
[604,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","2023-09-07","2024-03-03",1,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","; 8/12/23: 0%->35; 14/3/24: 35%->100","32.255; 32.256; 32.291; 32.298 ",101,51,null,null,"2023-09-07","2024-03-14"]
[605,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"2021-12-13","2025-12-12",0.81,"RP-240779",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ...",null,94,48,null,null,"2022-01-06","2024-04-02"]
[606,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2024-06-06",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"2022-01-06","2024-06-13"]
[607,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[608,1050130,"   UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects ","NR_NTN_enh_plus_CT-UEConTest",2,"Rel-18","R5","2024-09-09","2025-12-12",0.06,"RP-242024","RP-242899","Qualcomm ",null,"6/12/24: Compl:0%->6%; Stat Rep: ->RP-242899; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[609,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"2021-12-13","2024-12-12",0.84,"RP-241351",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073; 23/7/24: WID:RP-234073->RP-241351",null,94,48,null,null,"2022-01-06","2024-07-23"]
[610,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-241351","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[611,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","2022-03-07","2024-06-06",1,"RP-241351","RP-241350","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"2022-06-04","2024-06-13"]
[612,1030073,"   UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects ","IoT_NTN_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.47,"RP-241949","RP-242979","CMCC ",null,"13/6/24: Compl:0%->16%; WID: RP-240784->RP-240144; Stat Rep: ->RP-241198; ; 23/7/24: WID:RP-240144->RP-241197; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:16%->27%; Stat Rep: RP-241198->RP-241950; ; 26/9/24: WID:RP-241197->RP-241949; 6/12/24: FCD:12/12/2024",null,103,52,null,null,"2024-04-02","2024-12-06"]
[613,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-234043",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043",38.741,98,50,null,null,"2023-01-09","2024-01-02"]
[614,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[615,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[616,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"2022-09-11","2023-09-07"]
[617,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","2022-06-02","2023-06-06",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"2022-06-02","2023-06-08"]
[618,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","2022-06-01","2022-06-15",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"2022-07-12","NA"]
[619,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","2022-06-01","2023-12-12",1,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100",22.844000000000001,98,50,null,null,"2022-12-09","2023-12-08"]
[620,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647",null,"Thales ",null,"6/10/23: WID:RP-231499->RP-232647",null,100,51,null,null,"2023-06-29","2023-10-06"]
[621,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","2023-06-07","2023-09-08",1,"RP-232647","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,51,null,null,"2023-06-29","2023-09-21"]
[622,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","2023-03-03","2025-06-06",0.98,"RP-240741",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856; 2/4/24: WID:RP-233856->RP-240741",null,99,50,null,null,"2023-03-29","2024-04-02"]
[623,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","2023-03-03","2024-03-03",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"2023-03-29","2024-04-02"]
[624,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","2023-03-03","2024-06-06",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12...",null,99,50,null,null,"2023-03-29","2024-07-23"]
[625,1040110,"   UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-UEConTest",2,"Rel-18","R5","2024-06-06","2025-06-06",0.95,"RP-241355","RP-242993","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242049; ; 6/12/24: Compl:5%->95%; Stat Rep: RP-242049->RP-242993; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[626,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","2023-03-03","2025-03-03",0.99,"RP-241353",null,"MediaTek ",null,"2/1/24: WID:RP-230792->RP-234060; 2/4/24: WID:RP-234060->RP-240451; 23/7/24: WID:RP-240451->RP-241353",null,99,50,null,null,"2023-03-29","2024-07-23"]
[627,991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2...",36.764000000000003,99,50,null,null,"2023-03-29","2024-06-13"]
[628,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","2023-03-06","2024-06-06",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ...",null,99,50,null,null,"2023-03-29","2024-06-13"]
[629,1040109,"   UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-UEConTest",2,"Rel-18","R5","2024-06-06","2024-12-12",0.99,"RP-241354","RP-242991","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->95%; Stat Rep: ->RP-242048; ; 6/12/24: FCD:03/03/2025->12/12/2024; Compl:95%->99%; Stat Rep: RP-242048->RP-242991; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[630,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"2022-03-15","2024-03-03",1,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437; 23/7/24: 99%->100",null,95,48,null,null,"2022-04-05","2024-07-23"]
[631,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"2022-04-05","2023-01-09"]
[632,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...",36.180999999999997,95,48,null,null,"2022-04-05","2023-06-07"]
[633,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","2022-12-13","2024-03-03",1,"RP-240147","RP-240146","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"2023-01-09","2024-04-02"]
[634,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[635,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[636,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"2020-06-25","2021-09-13"]
[637,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[638,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[639,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"2021-12-19","2023-03-15"]
[640,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[641,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-06"]
[642,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","2023-06-09"]
[643,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"2022-12-09","NA"]
[644,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"2021-12-13","2024-03-03",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"2022-12-09","NA"]
[645,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"2021-12-13","2023-03-31"]
[646,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100",23.542000000000002,98,50,null,null,"2022-12-09","2023-06-08"]
[647,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%",27.007000000000001,99,50,null,null,"2022-12-09","2023-06-06"]
[{"$f":"A648+1","v":648},990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","2023-03-13","2024-03-15",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"2022-12-09","2023-06-09"]
[649,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.881999999999998,96,49,null,null,"2022-06-02","2023-06-08"]
[650,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","2021-06-11","2022-06-09",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"2021-06-11","2023-06-08"]
[651,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[652,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[653,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232672","RP-233067","Xueming Pan, vivo","panxueming@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...",38.869,94,48,null,null,"2022-01-06","2023-12-08"]
[654,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"2021-12-12","2024-12-12",0.85,"RP-233637",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637",null,97,49,null,null,"2022-09-23","2024-01-02"]
[655,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"2022-09-23","2023-12-08"]
[656,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","2022-09-13","2024-06-06",1,"RP-233637","RP-241124","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"2022-09-23","2024-07-23"]
[657,940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","2021-12-12","2022-09-09",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...; 23",38.865000000000002,94,48,null,null,"2022-01-06","2022-09-23"]
[658,1030062,"   UE Conformance - Enhanced support of reduced capability NR devices plus CT1 aspects ","NR_redcap_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.53,"RP-240920","RP-242486","China Unicom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240919; ; 23/7/24: WID:RP-240054->RP-240920; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-240919->RP-241883; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->53%; Stat Rep: RP-241883->RP-242486; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[659,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"2021-12-19","2022-12-10"]
[660,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"2022-12-15","2023-12-13",1,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[661,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added;","23.501; 23.502 ; 28.876",97,49,null,null,"2022-12-10","2024-01-04"]
[662,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","2022-12-15","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[663,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"2022-09-11","NA"]
[664,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894",null,"Ericsson",null,"2/1/24: WID:RP-230743->RP-232894",null,99,50,null,null,"2023-04-07","2024-01-02"]
[665,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232894","RP-232xyz","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[666,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"2021-12-13","2025-12-12",0.84,"RP-234009",null,"Huawei ",null,"2/1/24: WID:RP-223540->RP-234009",null,98,50,null,null,"2023-01-09","2024-01-02"]
[667,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","2022-12-13","2023-12-12",1,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[668,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","2022-12-14","2024-06-06",1,"RP-234009","RP-241239","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/...",null,98,50,null,null,"2023-01-09","2024-07-23"]
[669,1030067,"   UE Conformance - Network energy savings for NR ","Netw_Energy_NR-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.54,"RP-240291","RP-243092","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241378; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->24%; Stat Rep: RP-241378->RP-242075; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:24%->54%; Stat Rep: RP-242075->RP-243092; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[670,940080,"   Study on network energy savings for NR","FS_Netw_Energy_NR",2,"Rel-18","R1","2021-12-13","2022-12-01",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...",38.863999999999997,94,48,null,null,"2022-01-06","2023-03-29"]
[671,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[672,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ",23.256,99,50,null,null,"2022-12-09","NA"]
[673,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"2021-12-19","2023-03-15"]
[674,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100",23.256,98,50,null,null,"2022-12-09","2023-06-08"]
[675,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100",33.890999999999998,96,49,null,null,"2022-06-02","2023-03-17"]
[676,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100",33.256,99,50,null,null,"2023-03-16","2023-09-07"]
[677,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"2022-12-09","2023-06-06"]
[678,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-09"]
[679,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","2023-06-06"]
[680,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"2022-12-09","NA"]
[681,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","2021-09-13","2022-12-12",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"2021-09-13","2022-12-11"]
[682,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,97,49,null,null,"2022-09-11","NA"]
[683,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100",23.254999999999999,97,49,null,null,"2022-12-11","2023-06-08"]
[684,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-06"]
[685,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,null,"2022-09-11","2023-06-09"]
[686,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386",null,94,48,null,null,"2022-01-06","2024-01-02"]
[687,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233386","RP-233385","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[688,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389",null,"Nokia ",null,"2/1/24: WID:RP-230783->RP-233389",null,99,50,null,null,"2023-03-29","2024-01-02"]
[689,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","2023-03-03","2023-12-12",1,"RP-233389","RP-233388","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[690,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[691,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"2020-06-25","2025-03-03",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[692,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"2020-06-25","2021-06-11"]
[693,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[694,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"2021-12-19","2023-03-15"]
[695,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"2022-12-09","2023-06-08"]
[696,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100",33.893000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[697,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100",33.533000000000001,99,50,null,null,"2023-03-16","2023-09-07"]
[698,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"2022-12-09","2023-06-06"]
[699,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 16/7/24: 99%->100","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"2022-12-09","2024-07-16"]
[700,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%; 4/1/24: 29.586 added;","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586",99,50,null,null,"2022-12-09","2024-01-04"]
[701,1040013,"   Charging Aspects of Ranging and Sidelink Positioning","Ranging_SL_CH",2,"Rel-18","S5","2024-05-06","2025-03-03",1,"SP-241002",null,"Zhiwei Mo, China Telecom, ","mozw@chinatelecom.cn ","; 4/9/24: 20%->50; 5/12/24: 50%->100","32.240; 32.290; 32.271; 32.291; 32.298 ",104,53,null,null,"2024-06-13","2024-12-05"]
[702,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 70%->100",28.844999999999999,100,51,null,null,"2023-06-08","2024-03-14"]
[703,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"2022-09-30","2024-03-03",1,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[704,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"2021-12-19","2022-12-10"]
[705,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","2022-09-30","2023-06-06",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100",23.273,97,49,null,null,"2022-09-11","2023-06-08"]
[706,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%",23.273,97,49,null,null,"2022-09-11","2023-06-06"]
[707,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[708,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65",23.273,97,49,null,null,"2022-09-11","2023-06-09"]
[709,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"2022-12-13","2026-06-05",0.75,"RP-241186",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382; 2/4/24: WID:RP-233382->RP-240778; 23/7/24: WID:RP-240778->RP-241186",null,98,50,null,null,"2023-01-09","2024-07-23"]
[710,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","2022-12-13","2025-03-24",1,"RP-241186","RP-241919","Debdeep Chatterjee","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...",38.354999999999997,98,50,null,null,"2023-01-09","2024-09-04"]
[711,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","2022-12-15","2024-12-12",0.99,"RP-241186","RP-242766","Debdeep Chatterjee","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"2023-01-09","2024-12-06"]
[{"$f":"A712+1","v":712},1040107,"   UE Conformance - Expanded and improved NR positioning ","NR_pos_enh2-UEConTest",2,"Rel-18","R5","2024-06-06","2026-06-05",0.06,"RP-241342","RP-243121","CATT ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-242124; ; 26/9/24: WID:RP-241342->RP-242125; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->6%; WID: RP-242125->RP-241342; Stat Rep: RP-242124->RP-243121; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[713,940081,"   Study on expanded and improved NR positioning","FS_NR_pos_enh2",2,"Rel-18","R1","2022-12-13","2024-06-06",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...",38.859000000000002,94,48,null,null,"2022-01-06","2023-01-09"]
[714,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-232789",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789",null,94,48,null,null,"2022-01-06","2024-01-02"]
[715,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...",38.786000000000001,94,48,null,null,"2022-01-06","2023-12-08"]
[716,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-232789","RP-240928","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[717,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"2021-12-13","2024-12-12",0.89,"RP-232972",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972",null,94,48,null,null,"2022-01-06","2024-01-02"]
[718,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[719,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-223501","RP-241088","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[720,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","2022-06-15","2025-03-03",0.7,"RP-221447","RP-243118","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"2022-07-12","2024-12-06"]
[721,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"2021-12-13","2024-12-12",0.74,"RP-234010",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010",null,94,48,null,null,"2022-01-06","2024-01-02"]
[722,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-234010","RP-232887","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[723,1040103,"   UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR ","NR_MT_SDT-UEConTest",2,"Rel-18","R5","2024-06-06","2025-12-12",0.4,"RP-241127","RP-242496","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->10%; Stat Rep: ->RP-241914; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:10%->40%; Stat Rep: RP-241914->RP-242496; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[724,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","2021-12-20","2023-03-10",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 14/3/24: 95%->100","23.700-33",95,48,null,null,"2021-12-19","2024-03-14"]
[725,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"2021-12-19","2022-12-10"]
[726,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","2022-03-10","2023-03-10",1,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"2022-03-10","2023-06-08"]
[727,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"2022-09-27","2023-12-12",1,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","NA"]
[728,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","2022-09-27","2023-06-06",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-10-19","2023-06-08"]
[729,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[730,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-09"]
[731,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","2023-06-06"]
[732,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","2022-12-16","2023-12-12",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"2022-10-19","NA"]
[733,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90; 8/12/23: 90%->95; 15/3/24: 95%->100",33.503,99,50,null,null,"2023-03-16","2024-03-15"]
[734,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"2021-06-11","2024-03-03",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,23.434000000000001,99,50,null,null,"2022-12-09","NA"]
[735,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","2021-06-11","2022-09-12",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"2021-06-11","2022-12-11"]
[736,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100",23.434000000000001,98,50,null,null,"2022-12-09","2023-06-08"]
[737,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-06"]
[738,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"2022-12-09","2023-06-09"]
[739,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[740,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[741,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[742,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-18","S6","2023-09-07","2024-09-09",1,"SP-241692",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ","8/12/23: 0%->20; 4/1/24: 23.946 added;; 14/3/24: 20%->55; 13/6/24: 55%->80; 4/9/24: 80%->90; 5/12/24: 90%->100; 8/1/25: WID:SP-231161->SP-241692 (change Rel-19->Rel-18)",23.946000000000002,101,51,null,null,"2023-09-07","2025-01-08"]
[743,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-01-09"]
[744,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"2021-12-19","2023-03-15"]
[745,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","2022-09-23","2023-03-03",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","2023-06-08"]
[746,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[747,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[748,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"2022-09-23","2023-06-06"]
[749,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","2021-09-10","2023-03-03",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"2021-09-10","2023-06-30"]
[750,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"2021-12-10","2023-09-09",1,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,23.434000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[751,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","2021-12-12","2023-06-06",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...",23.434000000000001,94,48,null,null,"2022-12-11","2023-06-08"]
[752,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","2021-12-12","2022-12-12",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-06"]
[753,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","2021-12-10","2022-12-09",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"2021-12-10","2023-06-09"]
[754,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.433999999999997,99,50,null,null,"2023-03-16","2024-03-15"]
[755,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"2021-09-13","2024-03-03",1,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"2022-09-11","2022-09-23"]
[756,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"2021-09-13","2022-12-11"]
[757,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"2022-12-11","2023-06-08"]
[758,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[759,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"2022-09-11","2023-06-09"]
[760,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","2023-06-08","2023-09-09",1,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ","; 15/3/24: 0%->100",33.433999999999997,100,51,null,null,"2023-06-08","2024-03-15"]
[761,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","2021-03-18","2021-06-11",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"2021-03-18","2021-06-11"]
[762,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","2020-09-01","2020-09-17",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"2020-09-11","NA"]
[763,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"2022-06-02","2023-09-09",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"2022-06-02","2022-12-11"]
[764,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"2023-03-16","2023-06-08"]
[765,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.884,96,49,null,null,"2022-06-02","2023-06-08"]
[766,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50; 8/12/23: 50%->85; 15/3/24: 85%->100",33.122,99,50,null,null,"2023-03-16","2024-03-15"]
[767,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","2023-03-16","2023-09-09",1,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,29.222000000000001,99,50,null,null,"2023-03-16","2023-06-08"]
[768,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"2020-06-25","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"2021-06-11","NA"]
[769,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","2020-06-25","2021-06-11",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"2020-06-25","2021-09-13"]
[770,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"2021-06-11","2021-12-10"]
[771,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100",28.902000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[772,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"2021-06-11","2022-12-11"]
[773,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"2022-06-03","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"2022-06-03","2023-06-30"]
[774,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","2022-06-06","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->",24.558,96,49,null,null,"2022-06-03","2023-06-09"]
[775,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","2022-06-03","2024-03-03",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"2022-06-03","2023-06-06"]
[{"$f":"A776+1","v":776},980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","2022-12-09","2023-12-12",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100",28.843,98,50,null,null,"2022-12-09","2023-09-07"]
[777,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ","; 8/12/23: 0%->80; 14/3/24: 80%->100","32.240; 32.290 ",101,51,null,null,"2023-09-06","2024-03-14"]
[778,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[779,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","2022-06-02","2022-06-10",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100",22.100999999999999,96,49,null,null,"2022-06-02","2022-09-12"]
[780,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100",33.18,94,48,null,null,"2021-12-10","2023-06-08"]
[781,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"2021-12-10","2024-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-03-17"]
[782,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","2021-12-10","2023-03-03",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"2021-12-10","2023-06-08"]
[783,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-240297",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,51,null,null,"2023-06-07","2023-06-30"]
[784,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","NA"]
[785,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","2020-06-25","2021-09-20",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"2020-06-26","2021-09-13"]
[786,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","2021-09-10","2022-06-10",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"2021-09-10","2022-09-12"]
[787,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,null,"2021-09-10","2022-09-12"]
[788,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"2019-03-07","2023-12-12",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"2021-09-10","2022-06-04"]
[789,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","2019-03-07","2022-03-11",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100",23.289000000000001,93,47,null,null,"2021-09-10","2022-12-11"]
[790,970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","2022-09-13","2023-12-12",1,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"2022-09-05","2023-06-06"]
[791,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"2019-03-07","2023-12-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"2021-12-10","2022-06-04"]
[792,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","2019-03-07","2022-09-12",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22",23.289000000000001,94,48,null,null,"2021-12-10","2022-09-12"]
[793,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","2022-09-13","2023-12-12",1,"CP-233210",null,"Mengdi Ji, Huawei","jimengdi@huawei.com, ","3/24: rapporteur changed (was weihaitao@huawei.com)","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"2022-09-05","NA"]
[794,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","2022-09-12","2023-03-03",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%",33.503,97,49,101,null,"2022-09-11","2023-06-08"]
[795,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[796,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","2021-09-10","2021-09-20",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"2021-09-10","2021-12-10"]
[797,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","2022-12-09","2024-03-03",0.99,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[798,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","2022-12-09","2023-06-06",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"2022-12-09","2023-06-08"]
[799,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","2023-09-09","2024-03-03",1,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"2022-12-09","2023-06-08"]
[800,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","2019-09-19","2021-12-10",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"2019-09-13","2021-09-13"]
[801,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","2021-12-13","2023-03-03",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"2021-12-13","2023-06-08"]
[802,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","2021-12-13","2022-12-12",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"2021-12-13","2023-03-17"]
[803,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","2018-06-06","2022-06-10",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"2018-06-06","2022-06-04"]
[804,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[805,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"2019-12-06","2021-12-10",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"2021-06-11","2022-07-13"]
[806,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","2019-12-06","2021-06-11",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"2019-12-06","2022-06-21"]
[807,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"2021-06-11","2022-06-21"]
[808,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-221348","RP-233132","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...",38.843000000000004,94,48,null,null,"2022-01-06","2023-12-08"]
[809,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[810,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","2022-06-21","2023-03-03",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100",33.898000000000003,96,49,null,null,"2022-06-21","2023-09-07"]
[811,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220071",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"2021-12-19","2022-12-10"]
[812,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2024-01-03"]
[813,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"2022-12-09","2023-06-06"]
[814,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"2022-12-09","2023-06-06"]
[815,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"2021-12-13","2023-12-12",0.8,"RP-233441",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441",null,94,48,null,null,"2022-01-06","2024-01-02"]
[816,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",0.8,"RP-233441","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"2022-01-06","2023-09-21"]
[817,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100",33.877000000000002,96,49,null,null,"2022-06-02","2023-09-07"]
[818,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100",28.908000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[819,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","2023-03-17","2024-03-03",1,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35; 14/3/24: 35%->100; 14/3/24: FCD:12/12/2023->/24","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"2023-03-17","2024-03-14"]
[820,1020023,"NEF Charging enhancement to support AI/ML in 5GS ","AIMLsysNEF_CH",1,"Rel-18","S5","2023-12-07","2023-12-12",1,"SP-231706",null,"Alla Goldner, OPPO ","v-alla.goldner@oppo.com ","; 14/3/24: 0%->100; 14/3/24: 100%->100","32.254; 32.291 ",102,52,null,null,"2023-12-07","2024-03-14"]
[821,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[822,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-232993",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993",null,94,48,null,null,"2022-01-06","2024-01-02"]
[823,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-232993","RP-232992","Rui Zhou, CATT","zhourui@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[824,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","NA"]
[825,940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"2021-12-19","2022-12-10"]
[826,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"2022-12-09","2023-06-08"]
[827,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024. 03/24: rapporteur changed (was giorgi.gulbani@huawei.com)",null,99,50,null,null,"2022-12-09","2023-06-30"]
[828,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 9/6/23: 15%->40",null,99,50,null,null,"2022-12-09","2023-06-09"]
[829,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,null,"2022-12-09","2023-06-06"]
[830,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","2023-06-08","2023-09-09",1,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"2023-06-08","2024-03-15"]
[831,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100",33.883000000000003,96,49,null,null,"2022-06-02","2023-06-08"]
[832,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"2021-06-15","2025-12-12",0.66,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"2021-07-02","2023-01-09"]
[833,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","2021-06-15","2023-09-08",1,"RP-232590","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",36.792000000000002,92,47,null,null,"2021-07-02","2023-10-06"]
[834,1050131,"   UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast ","LTE_terr_bcast_bands_part2-UEConTest",2,"Rel-18","R5","2024-09-09","2025-12-12",0.05,"RP-242026","RP-242900","Qualcomm ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242900; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[835,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"2023-03-03","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[836,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024",31.102,92,47,null,null,"2021-07-02","2023-06-06"]
[837,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","2023-03-03","2023-03-03",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"2021-07-02","2023-01-09"]
[838,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[839,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[{"$f":"A840+1","v":840},0,"Rel-18 Slice","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[841,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","2021-03-12","2022-09-22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"2021-04-07","2022-09-23"]
[842,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[843,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"2021-03-18","NA"]
[844,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","2020-06-25","2021-03-17",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"2020-06-25","2021-06-11"]
[845,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-06-11"]
[846,1000023,"   Stopped – CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[847,1000044,"   Stopped – CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[848,1000045,"   Stopped – CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"2023-06-07","NA"]
[849,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","NA"]
[850,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"2021-12-19","2022-12-10"]
[851,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90; 15/3/24: 90%->100",33.886000000000003,96,49,null,null,"2022-06-02","2024-03-15"]
[852,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-06-08"]
[853,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[854,990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-09"]
[855,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"2022-12-09","2023-06-06"]
[856,1030024,"   Network Slice Replacement charging ","eNS_Ph3_CH",2,"Rel-18","S5","2024-02-02","2024-03-03",1,"SP-240475",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com) ","; 2/4/24: 0%->100","32.255; 32.256; 32.291; 32.298 ",103,52,null,null,"2024-03-14","2024-04-02"]
[857,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793",null,"ZTE ",null,"2/1/24: WID:RP-230787->RP-232793",null,99,50,null,null,"2023-03-29","2024-01-02"]
[858,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232793","RP-232866","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[859,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[860,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","2022-03-10","2023-12-12",1,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12/23",28.835999999999999,95,48,null,null,"2022-03-10","2023-12-08"]
[861,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added;","28.312 ; 28.914",99,50,null,null,"2023-03-16","2024-01-04"]
[862,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","2021-03-18","2021-12-10",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"2021-03-18","2022-06-04"]
[863,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","2022-06-15","2023-12-12",1,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100",26.940999999999999,96,49,null,null,"2022-06-03","2023-12-08"]
[864,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","2021-12-10","2022-03-11",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"2021-12-10","2022-06-04"]
[865,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","2021-03-18","2022-09-12",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"2021-03-18","2022-12-11"]
[866,1020049,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18",null,"2022-06-02","2024-03-15",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[867,960013,"   (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement","NSCALE",2,"Rel-18","S6","2022-06-02","2023-03-03",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"2022-06-02","2023-06-08"]
[868,1020050,"   CT1 aspects of NSCALE","NSCALE",2,"Rel-18","C1","2022-06-02","2024-03-15",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,24.548999999999999,96,49,null,null,"2022-06-02","2023-06-08"]
[869,1020006,"   CT3 aspects of NSCALE","NSCALE",2,"Rel-18","C3","2022-06-02","2024-03-15",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.222, 29.520, 29.522, 29.549",96,49,null,null,"2022-06-02","2023-06-08"]
[870,1020046,"   CT4 aspects of NSCALE","NSCALE",2,"Rel-18","C4","2022-06-02","2024-03-15",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,29.536000000000001,96,49,null,null,"2022-06-02","2023-06-08"]
[871,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","2022-06-03","2023-09-09",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"2022-06-03","2022-07-13"]
[872,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","2021-01-12","2023-03-03",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"2021-01-12","2023-03-17"]
[873,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-231448",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448; 14/3/24: 75%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"2022-12-09","2024-03-14"]
[874,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","2023-06-30","2024-03-03",1,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;",31.105,100,51,null,null,"2023-06-30","2023-09-21"]
[875,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[876,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"2021-12-13","2024-12-12",0.82,"RP-232778",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778",null,98,50,null,null,"2023-01-09","2024-01-02"]
[877,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","2022-12-13","2023-12-12",1,"RP-223502","RP-232779","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"2023-01-09","2023-12-08"]
[878,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","2021-12-13","2023-03-03",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...",38.835000000000001,94,48,null,null,"2022-01-06","2023-03-17"]
[879,1030063,"   UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects ","NR_XR_enh_plus_CT1-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.6,"RP-241588","RP-242607","Nokia ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240936; ; 23/7/24: WID:RP-240088->RP-241588; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->40%; Stat Rep: RP-240936->RP-241790; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:40%->60%; Stat Rep: RP-241790->RP-242607; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[880,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"2022-12-09","NA"]
[881,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"2021-12-19","2022-12-10"]
[882,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"2022-12-09","2023-09-07"]
[883,1030048,"   CT1 aspects of XRM","XRM",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196; 2/4/24: 0%->98","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2024-04-02"]
[884,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[885,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"2022-12-09","2023-06-06"]
[886,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","2022-03-10","2024-03-03",1,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...",26.93,95,48,null,null,"2022-03-10","2024-03-14"]
[887,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","2022-03-15","2024-06-06",1,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60; 14/3/24: FCD:03/03/2024->/...",26.113,95,48,null,null,"2022-03-10","2024-06-13"]
[888,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","2022-03-10","2023-06-06",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"2022-03-10","2023-06-08"]
[889,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","2022-03-10","2024-03-03",1,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024; 14/3/24: 80%->","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"2022-03-10","2024-03-14"]
[890,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","2022-06-03","2024-06-06",1,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1...",26.263999999999999,96,49,null,null,"2022-06-03","2024-06-13"]
[891,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","2022-06-03","2023-06-06",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"2022-06-03","2023-06-08"]
[892,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","2022-06-03","2024-03-03",1,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...",26.521999999999998,96,49,null,null,"2022-06-03","2024-03-14"]
[893,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","2019-03-07","2024-06-06",1,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/...","26.260; new",83,42,null,null,"2019-03-14","2024-06-13"]
[894,1030047,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18",null,"2017-09-08","2024-06-06",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2023-12-08"]
[895,770024,"   EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",2,"Rel-18","S4","2017-09-08","2024-06-06",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"2017-09-08","2024-06-13"]
[896,1030025,"   CT3 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C3","2024-03-03","2024-06-06",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"2017-09-08","2023-12-08"]
[897,1030001,"   CT4 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C4","2024-03-03","2024-06-06",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"2017-09-08","2023-12-08"]
[898,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","2023-03-16","2024-06-06",1,"SP-231291",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291; 14/3/24: 25%->35; 14/3/24: FCD:03/03/2024->/24; 3/4/24: 26.249 added; 26.996 added;; 13/6/24: 35%","26.119 ; 26.566; 26.866; 26.865; 26.249; 26.996",99,50,null,null,"2023-03-16","2024-06-13"]
[899,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","2022-06-03","2024-06-06",1,"SP-231291",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%...",26.565000000000001,96,49,null,null,"2022-06-03","2024-06-13"]
[900,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","2022-06-03","2024-03-03",1,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65; 14/3/24: 65%->100",26.812000000000001,96,49,null,null,"2022-06-03","2024-03-14"]
[901,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","2022-06-03","2022-12-08",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"2022-06-03","2022-12-11"]
[902,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[903,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","2020-06-25","2021-12-10",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"2020-06-25","2021-12-10"]
[{"$f":"A904+1","v":904},880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","2020-06-25","2021-09-16",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"2020-06-26","2022-03-12"]
[905,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"2022-03-03","2023-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-03-10","2022-09-12"]
[906,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","2022-03-03","2022-12-12",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"2022-12-11","2023-06-08"]
[907,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2023-06-06"]
[908,980071,"   deleted - CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","2/4/24: deleted at 100%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"2022-03-10","2024-04-02"]
[909,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","2020-12-04","2021-12-10",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"2020-12-04","2022-06-21"]
[910,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","2021-09-13","2022-09-12",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"2021-09-13","2022-12-11"]
[911,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"2022-09-09","2024-03-03",1,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"2022-09-11","NA"]
[912,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","2022-09-09","2023-06-06",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"2022-12-11","2023-06-08"]
[913,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","2023-06-30"]
[914,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"2022-09-11","NA"]
[915,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"2022-09-12","2024-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[916,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"2022-09-11","2023-03-22"]
[917,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,51,null,null,"2023-06-07","NA"]
[918,1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,51,null,null,"2023-06-07","NA"]
[919,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"2022-03-15","2024-12-12",0.8,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"2022-04-05","2022-09-23"]
[920,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","2022-03-15","2023-09-22",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[921,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","2022-03-16","2024-06-06",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[922,1030071,"   UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.38,"RP-240371","RP-242595","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241278; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->36%; Stat Rep: RP-241278->RP-241981; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:36%->38%; Stat Rep: RP-241981->RP-242595; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[923,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[924,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"2019-09-19","2025-12-12",0.89,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"2021-06-11","NA"]
[925,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","2019-09-19","2021-09-08",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"2019-09-13","2021-09-13"]
[926,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","2021-06-11","2021-12-10",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"2021-06-11","2021-09-13"]
[927,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","2021-12-20","2023-03-03",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"2021-12-19","2023-03-16"]
[928,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[929,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,null,"2022-09-11","2023-06-06"]
[930,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,null,"2022-09-11","NA"]
[931,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"2022-09-11","2024-01-04"]
[932,1030027,"   CT6 aspects of NG_RTC","NG_RTC",2,"Rel-18","C6","2023-03-13","2024-03-03",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"2022-09-11","2024-01-04"]
[933,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","2022-06-02","2023-06-06",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100",33.89,96,49,null,null,"2022-06-02","2023-06-08"]
[934,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","; 15/3/24: 0%->100",33.328000000000003,99,50,null,null,"2023-03-16","2024-03-15"]
[935,1050133,"   UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) ","NG_RTC_IMS_dataCH-UEConTest",2,"Rel-18","R5","2024-09-09","2025-12-12",0.05,"RP-242078","RP-243093","Huawei ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-243093; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[936,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.260; 32.255; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2024-03-14"]
[937,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[938,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"2021-12-19","2022-12-10"]
[939,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[940,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[941,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-09"]
[942,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"2022-09-11","2023-06-06"]
[943,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"2021-12-19","2023-03-15"]
[944,1060029,"ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E",1,"Rel-19","S2","2024-12-05","2024-12-12",0,"SP-241500",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ",null,23.501999999999999,null,null,null,null,"2024-12-05","NA"]
[945,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"2022-09-12","2024-03-03",1,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2022-12-10"]
[946,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[947,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-06"]
[948,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","2023-04-18","2024-03-03",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"2022-09-11","2023-06-09"]
[949,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"2020-12-04","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[950,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","2020-12-04","2021-06-11",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"2020-12-04","2021-12-10"]
[951,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[952,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[953,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"2022-09-11","2022-09-12"]
[954,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","2022-09-09","2023-03-03",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"2022-12-11","2023-06-08"]
[955,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","2022-12-15","2023-12-12",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[956,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","2022-12-15","2023-12-12",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"2022-09-11","2023-06-06"]
[957,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","2022-06-02","2023-12-12",1,"SP-220990",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156; 15/3/24: 65%->98; 13/6/24: 98%->100; 13/6/24: WID:SP-231156->S",23.957999999999998,96,49,null,null,"2022-06-02","2024-06-13"]
[958,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","2021-06-11","2022-06-10",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"2021-06-11","2022-12-11"]
[959,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"2021-12-20","2024-06-06",1,null,null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2022-12-11","NA"]
[960,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"2021-12-19","2022-03-12"]
[961,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"2021-12-19","2022-12-10"]
[962,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90; 15/3/24: 90%->100",33.738999999999997,95,48,null,null,"2022-03-10","2024-03-15"]
[963,970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","2022-09-23","2023-06-06",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[964,1040038,"   CT1 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C1","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[965,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2023-06-09"]
[966,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","2022-12-16","2024-06-06",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%; 16/7/24: WID:CP-233026->CP-241027","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"2022-09-11","2024-07-16"]
[967,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95; 15/3/24: 95%->100","33.558; 33.501 ",99,50,null,null,"2023-03-16","2024-03-15"]
[{"$f":"A968+1","v":968},0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[969,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"2020-09-16","2021-09-08",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"2021-06-11","NA"]
[970,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","2020-09-16","2021-06-11",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"2020-09-10","2021-09-13"]
[971,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","2021-06-11","2021-09-08",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[972,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"2021-12-13","2025-12-12",0.87,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2022-12-10"]
[973,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"2021-12-19","2023-03-15"]
[974,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"2022-09-11","2023-06-08"]
[975,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99; 15/3/24: 99%->100",33.857999999999997,96,49,null,null,"2022-06-02","2024-03-15"]
[976,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90; 14/3/24: 90%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-14"]
[977,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-30"]
[978,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","2022-12-15","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-09"]
[979,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"2022-09-11","2023-06-06"]
[980,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100",28.827999999999999,94,48,null,null,"2021-12-13","2023-03-17"]
[981,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65; 14/3/24: 65%->100","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"2023-03-16","2024-03-14"]
[982,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","2023-03-06","2023-12-12",1,"RP-233569","RP-233567","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"2023-04-07","2024-01-02"]
[983,1040106,"   UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects ","eNPN_Ph2-NGRAN_plus_CT1-UEConTest",2,"Rel-18","R5","2024-06-06","2025-12-12",0.05,"RP-241307","RP-242870","China Telecom ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242870; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[984,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[985,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"2019-05-31","2023-03-15"]
[986,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"2022-09-09","2024-06-06",1,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-23","NA"]
[987,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[988,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","2022-12-16","2024-06-06",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192; 23/7/24: WID:CP-240080->CP-241076","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2024-07-23"]
[989,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","2022-12-16","2024-06-06",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[990,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","2022-12-16","2024-06-06",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"2022-09-23","2023-06-06"]
[991,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"2022-09-12","2023-12-12",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-03-22"]
[992,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","2022-09-12","2023-06-06",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"2022-09-11","2023-06-08"]
[993,1000040,"   CT3 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,51,null,null,"2023-06-07","NA"]
[994,1020048,"   CT4 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C4","2023-06-07","2023-12-12",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",102,52,null,null,"2023-06-07","NA"]
[995,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"2019-03-07","2023-12-13",1,"CP_233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"2022-03-10","NA"]
[996,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","2019-03-07","2023-12-12",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"2022-09-07","2023-06-06"]
[997,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","2019-03-11","2023-12-12",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,29.518000000000001,97,49,null,null,"2022-09-07","NA"]
[998,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"2019-03-07","2024-03-03",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-01-09"]
[999,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"2021-12-19","2022-09-12"]
[1000,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","2019-03-07","2019-03-07",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-03-15"]
[1001,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[1002,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[1003,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"2021-12-20","2023-09-09",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,97,49,null,null,"2022-09-11","NA"]
[1004,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102",23.501999999999999,97,49,null,null,"2022-09-11","2023-03-16"]
[1005,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[1006,1020047,"   CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C4","2021-12-20","2023-09-09",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"2022-09-11","2023-06-06"]
[1007,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1008,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","2023-06-08","2024-03-03",1,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65; 14/3/24: 65%->100","26.955 ; 26.966",100,51,null,null,"2023-06-08","2024-03-14"]
[1009,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","2021-12-13","2022-12-12",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"2021-12-13","2022-12-11"]
[1010,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","2022-06-02","2024-03-03",1,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65; 14/3/24: 65%->100","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"2022-06-03","2024-03-14"]
[1011,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","2022-12-09","2023-03-03",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"2022-12-09","2023-03-17"]
[1012,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","2022-06-02","2023-06-06",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100",26.501000000000001,96,49,null,null,"2022-06-03","2023-06-08"]
[1013,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","2022-12-12","2024-03-03",1,"SP-231709",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709; 14/3/24: 75%->100; 3/4/24: 26.982 added;","26.114 ; 26.982",98,50,null,null,"2022-12-09","2024-04-03"]
[1014,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","2020-03-25","2023-09-09",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...",26.925000000000001,87,44,null,null,"2019-12-06","2023-09-07"]
[1015,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","2023-06-08","2024-03-03",1,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40; 14/3/24: 40%->100","26.140; 26.141 ; 26.143",100,51,null,null,"2023-06-08","2024-03-14"]
[1016,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","2023-06-08","2024-06-06",1,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55; 14/3/24: 55%->75; 14/3/24: FCD:03/03/2024->/24; 13/6/24: 75%->100","26.512; 26.247; 26.517; 26.532 ; 26.510",100,51,null,null,"2023-06-08","2024-06-13"]
[1017,0,"Rel-18 Other topics","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1018,1030040,"AKMA service disabling in roaming ","AKMA_Disable",1,"Rel-18","S3","2024-02-02","2024-03-03",1,"SP-240246",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","15/3/24: 0%->100",null,103,52,null,null,"2024-03-14","2024-03-15"]
[1019,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[1020,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"2017-06-03","2023-03-15"]
[1021,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100",33.887,96,49,null,null,"2022-06-02","2023-06-08"]
[1022,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-09","2023-06-08"]
[1023,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-30"]
[1024,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-09"]
[1025,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","2022-12-15","2024-03-03",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[1026,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-15"]
[1027,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.255; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2024-03-14"]
[1028,980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"2022-09-09","2023-12-12",1,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-23","NA"]
[1029,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-12","2023-06-08"]
[1030,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","NA"]
[1031,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","2022-12-15","2023-12-12",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"2022-09-23","2023-06-06"]
[{"$f":"A1032+1","v":1032},970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","2022-09-23","2024-03-03",1,"SP-240267",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 87%->100; 2/4/24: WID:SP-220981->SP-240267","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"2022-09-11","2024-04-02"]
[1033,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"2021-12-13","2024-03-03",1,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"2022-09-11","2022-12-11"]
[1034,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","2021-12-13","2022-09-12",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"2021-12-13","2022-12-11"]
[1035,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","2022-09-12","2023-06-06",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"2022-09-11","2023-06-08"]
[1036,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","2022-09-12","2024-03-03",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"2022-09-11","2023-06-06"]
[1037,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","2022-09-12","2024-03-03",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5",29.548999999999999,97,49,null,null,"2022-09-11","2023-06-09"]
[1038,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","2021-12-20","2022-09-12",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"2021-12-19","2022-06-04"]
[1039,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"2022-09-08","2023-09-09",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[1040,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[1041,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[1042,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","2023-06-09"]
[1043,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","2022-12-16","2023-09-09",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"2022-09-11","NA"]
[1044,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[1045,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","2022-09-09","2023-06-06",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[1046,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[1047,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","2021-12-20","2023-12-12",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"2022-09-11","2023-06-06"]
[1048,940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"2021-12-19","2022-12-10"]
[1049,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"2021-12-19","2023-03-15"]
[1050,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"2022-09-08","2024-03-03",0.77,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","NA"]
[1051,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","2022-09-08","2023-06-06",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-12-10","2023-06-08"]
[1052,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[1053,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","2022-12-16","2024-03-03",0.25,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[1054,1020064,"      (IETF) CT3 part of DetNet (draft-ietf-detnet-yang)","DetNet",3,"Rel-18","C3-IETF","2022-12-16","2024-03-03",0.25,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","2/4/24: 100%->25","29.513, 29.565",97,49,null,null,"2022-09-11","2024-04-02"]
[1055,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"2022-09-11","2023-06-06"]
[1056,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,97,49,null,null,"2022-09-11","NA"]
[1057,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100",23.273,97,49,null,null,"2022-12-10","2022-12-10"]
[1058,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","2022-12-16","2023-06-06",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"2022-09-11","2023-06-06"]
[1059,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"2022-09-08","2023-06-06",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[1060,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"2022-12-10","2023-03-22"]
[1061,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","2022-12-15","2023-06-06",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"2022-09-11","2023-06-06"]
[1062,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"2022-09-08","2023-12-12",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-09-11","NA"]
[1063,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","2022-09-08","2023-03-03",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"2022-12-10","2023-03-22"]
[1064,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","2023-06-06"]
[1065,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[1066,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"2022-09-11","NA"]
[1067,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"2022-09-08","2024-03-03",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"2022-09-11","NA"]
[1068,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","2022-09-08","2022-12-12",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"2022-12-10","2022-12-10"]
[1069,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-06"]
[1070,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","2023-06-09"]
[1071,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","2022-12-16","2024-03-03",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"2022-09-11","NA"]
[1072,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"2022-03-10","2023-12-12",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70",23.553999999999998,95,48,null,null,"2022-03-10","2022-12-11"]
[1073,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","2022-03-10","2023-03-03",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100",23.553999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[1074,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","2023-03-13","2023-12-15",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-06"]
[1075,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","2023-03-13","2023-12-15",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"2022-03-10","2023-06-09"]
[1076,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","2023-02-02","2023-03-03",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100",33.500999999999998,99,50,null,null,"2023-03-16","2023-06-08"]
[1077,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"2020-06-25","2024-03-03",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"2021-03-18","NA"]
[1078,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","2020-06-25","2021-03-12",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"2020-06-25","2021-06-11"]
[1079,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"2021-12-19","2023-03-15"]
[1080,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","2021-03-18","2021-09-10",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1081,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","2022-09-12","2023-03-03",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"2022-09-11","2023-06-08"]
[1082,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-30"]
[1083,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","2022-12-16","2024-03-03",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"2022-09-11","2023-06-06"]
[1084,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","2022-12-16","2023-12-12",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"2022-09-11","2023-06-30"]
[1085,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772",28.832000000000001,95,48,null,null,"2022-03-10","2023-06-30"]
[1086,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","2021-12-13","2022-09-22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",38.878999999999998,94,48,null,null,"2022-01-06","2022-09-23"]
[1087,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863",null,"Nokia ",null,"2/1/24: WID:RP-230754->RP-232863",null,99,50,null,null,"2023-03-29","2024-01-02"]
[1088,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","2023-03-03","2023-12-12",1,"RP-232863","RP-232864","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; ",null,99,50,null,null,"2023-03-29","2023-12-08"]
[1089,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"2020-09-16","2024-03-03",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"2021-09-10","NA"]
[1090,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","2020-09-16","2021-09-08",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"2020-09-10","2021-09-13"]
[1091,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"2021-09-10","2021-12-14"]
[1092,980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added;","23.501; 23.502; 23.503; 23.273 ; 28.875",98,50,null,null,"2022-12-09","2024-01-04"]
[1093,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","2023-03-13","2024-03-03",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[1094,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"2022-12-09","2023-06-06"]
[1095,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"2021-12-19","2022-12-10"]
[{"$f":"A1096+1","v":1096},941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-240104",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320; 2/4/24: WID:RP-2",null,94,48,null,null,"2022-01-06","2024-04-02"]
[1097,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[1098,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","2021-12-15","2024-06-06",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[1099,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"2021-12-13","2023-12-12",1,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"2022-01-06","2023-01-09"]
[1100,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","2021-12-13","2023-12-12",1,"RP-223488","RP-233603","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1101,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-231432",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432",28.863,94,48,null,null,"2021-12-13","2024-01-03"]
[1102,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-231440",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440; 14/3/24: 99%->100",null,95,48,null,null,"2022-03-10","2024-03-14"]
[1103,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"2021-09-10","2024-03-03",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"2021-09-10","2022-01-07"]
[1104,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","2021-09-10","2021-12-10",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"2021-09-10","2021-12-10"]
[1105,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","2021-12-20","2023-06-06",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"2021-12-19","2023-06-08"]
[1106,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[1107,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[1108,1030049,"   CT6 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"2023-06-07","NA"]
[1109,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"2021-01-01","2023-12-12",1,"RP-233438",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1110,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","2021-01-01","2023-12-12",1,"RP-233438","RP-233437","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1111,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-233438","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"2022-04-05","2023-10-06"]
[1112,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","2021-12-10","2024-03-03",1,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 90%->100","28.313; ; 28.317",94,48,null,null,"2021-12-10","2024-03-14"]
[1113,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","2020-12-04","2021-03-12",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-04","2020-12-05"]
[1114,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","2021-03-18","2021-03-25",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"2021-03-18","2021-03-19"]
[1115,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","2022-09-16","2024-03-01",0.99,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"2021-06-11","2021-12-10"]
[1116,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","2022-12-16","2023-06-06",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"2022-09-19","2023-06-06"]
[1117,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","2022-09-16","2022-09-16",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,31.102,97,49,null,null,"2022-09-19","NA"]
[1118,1010052,"   UE Conformance - Signal level Enhanced Network Selection ","SENSE-UEContest",2,"Rel-18","R5","2023-09-09","2024-03-01",1,"RP-233770","RP-240288","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770; 14/3/24: FCD:05/06/2024->01/03/2024; Compl:5%->100%; Stat Rep: RP-233769->RP-",null,101,51,null,null,"2023-10-06","2024-03-14"]
[1119,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","2021-12-10","2023-03-03",1,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75; 15/3/24: 75%->100","33.527; 33.927; 33.936",94,48,null,null,"2021-12-10","2024-03-15"]
[1120,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30; 15/3/24: 30%->100","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"2022-03-10","2024-03-15"]
[1121,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100",33.892000000000003,96,49,null,null,"2022-06-02","2023-09-07"]
[1122,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","2018-09-06","2022-12-09",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ; ","New",81,41,null,null,"2018-09-06","2023-06-08"]
[1123,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","2022-06-02","2022-12-12",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"2022-06-02","2023-09-07"]
[1124,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","2023-06-06"]
[1125,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[1126,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"2022-06-03","NA"]
[1127,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","2023-06-06"]
[1128,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[1129,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[1130,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"2022-06-03","NA"]
[1131,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"2022-06-03","2024-03-03",1,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2022-06-20"]
[1132,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","2022-06-03","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[1133,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","2022-06-06","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-09"]
[1134,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","2022-06-03","2024-03-03",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"2022-06-03","2023-06-06"]
[1135,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","2022-06-03","2022-12-08",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"2022-06-03","2022-06-20"]
[1136,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,null,"2022-06-03","2022-06-20"]
[1137,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-06"]
[1138,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"2022-09-07","2023-06-09"]
[1139,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","2022-03-07","2024-03-03",1,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,null,"2022-06-03","2023-06-06"]
[1140,1050016,"UE conformance test for NB-IoT/eMTC Non-Terrestrial Networks in EPS","IoT_SAT_UEConTest",1,"Rel-18","C6","2024-09-09","2025-09-09",1,"CP-242075",null,"Daiwei Zhou, MediaTek Inc","daiwei.zhou@mediatek.com",null,null,96,49,null,"x","2022-06-03","2023-06-06"]
[1141,1050008,"Test method of GBA_U Based APIs","TEST_GBA_U_APIs",1,"Rel-18","C6","2024-09-09","2025-06-06",1,"CP-242028",null,"Huo Weijing(China Mobile)","huoweijing@chinamobile.com",null,null,96,49,null,"x","2022-06-03","2023-06-06"]
[1142,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","2022-12-15","2023-12-12",1,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"2022-06-03","2023-06-06"]
[1143,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","2023-03-13","2023-12-15",1,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"2022-06-03","2023-06-06"]
[1144,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,51,null,null,"2023-09-20","NA"]
[1145,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",22.260999999999999,101,51,null,null,"2023-09-20","NA"]
[1146,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","2023-08-08","2023-09-09",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100",33.500999999999998,101,51,null,null,"2023-09-20","2023-12-08"]
[1147,1020001,"NRF API enhancements to avoid signalling and storing of redundant data","NRFe",1,"Rel-18","C4","2023-12-12","2024-03-15",1,"CP-233025",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com",null,"29.510, 29.571, 29.504",96,49,null,null,"2022-06-03","2023-06-06"]
[1148,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1149,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95; 15/3/24: 95%->100","33.926 ; 33.537",95,48,null,null,"2022-03-10","2024-03-15"]
[1150,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","2023-03-16","2023-12-12",1,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23; 15/3/24: 40%->100","33.926 ; 33.528",99,50,null,null,"2023-03-16","2024-03-15"]
[1151,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2023-09-07"]
[1152,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","2022-12-09","2023-09-09",1,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23; 15/3/24: 80%->100","33.535; 33.220; 33.222 ",98,50,null,null,"2022-12-09","2024-03-15"]
[1153,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99; 15/3/24: 99%->100","33.926 ; 33.742; 33.523",95,48,null,null,"2022-03-10","2024-03-15"]
[1154,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","2022-03-10","2024-03-03",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 15/3/24: 99%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2024-03-15"]
[1155,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"2022-03-10","2023-03-17"]
[1156,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","2022-12-09","2023-06-06",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"2022-12-09","2023-09-07"]
[1157,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","2023-09-09","2024-03-03",1,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"2022-12-09","NA"]
[1158,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","2022-03-10","2022-12-12",1,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.737000000000002,95,48,null,null,"2022-03-10","2024-03-15"]
[1159,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.534999999999997,99,50,null,null,"2023-03-16","2024-03-15"]
[{"$f":"A1160+1","v":1160},940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","2021-12-13","2023-03-03",1,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80; 15/3/24: 80%->100",33.869999999999997,94,48,null,null,"2021-12-13","2024-03-15"]
[1161,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","2018-12-13","2022-12-09",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%-> ; ",null,82,42,null,null,"2018-12-06","2023-09-07"]
[1162,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100",33.893999999999998,96,49,null,null,"2022-06-02","2023-09-07"]
[1163,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","2022-06-02","2023-03-03",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100",33.896000000000001,96,49,null,null,"2022-06-02","2023-03-17"]
[1164,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","2023-05-01","2023-06-06",1,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"2023-06-08","2024-03-15"]
[1165,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","2023-09-06","2024-03-03",1,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 8/12/23: 0%->10; 15/3/24: 10%->100",33.926000000000002,101,51,null,null,"2023-09-06","2024-03-15"]
[1166,0,"Rel-18 NR-only: topics other than band","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1167,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"2022-03-15","2024-12-12",0.79,"RP-241292",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586; 23/7/24: WID:RP-233586->RP-241292",null,95,48,null,null,"2022-04-05","2024-07-23"]
[1168,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","2023-06-07","2023-12-12",1,"RP-241292","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; ",null,100,51,null,null,"2023-06-29","2023-12-08"]
[1169,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-241292","RP-241293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...",38.878,95,48,null,null,"2022-04-05","2024-06-13"]
[1170,1040105,"   UE Conformance - NR demodulation performance evolution ","NR_demod_enh3-UEConTest",2,"Rel-18","R5","2024-06-06","2025-12-12",0.41,"RP-241298","RP-242854","China Telecom ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->8%; Stat Rep: ->RP-241995; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:8%->41%; Stat Rep: RP-241995->RP-242854; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1171,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025",null,"Ericsson",null,"2/1/24: WID:RP-230813->RP-234025",null,99,50,null,null,"2023-04-07","2024-01-02"]
[1172,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","2023-03-06","2024-03-01",0.95,"RP-234025","RP-233392","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50%->",null,99,50,null,null,"2023-04-07","2023-12-08"]
[1173,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"2022-12-13","2025-06-06",0.86,"RP-240251",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004; 2/4/24: WID:RP-234004->RP-240251",null,98,50,null,null,"2023-01-09","2024-04-02"]
[1174,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2024-03-14"]
[1175,981242,"   Stopped - Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"2023-01-09","2024-04-02"]
[1176,1040102,"   UE Conformance - 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-UEConTest",2,"Rel-18","R5","2024-06-06","2025-06-06",0.52,"RP-241093","RP-242810","ZTE ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->13%; Stat Rep: ->RP-241772; ; 6/12/24: Compl:13%->52%; Stat Rep: RP-241772->RP-242810; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1177,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"2022-09-12","2025-06-06",0.72,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"2022-10-19","2023-01-09"]
[1178,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","2022-09-12","2023-12-12",1,"RP-223499","RP-233448","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...",38.895000000000003,97,49,null,null,"2022-10-19","2023-12-08"]
[1179,970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","2022-09-13","2023-12-12",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"2022-10-19","2022-12-09"]
[1180,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",1,"RP-241199","RP-241200","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ; 14/3/24: FCD:05/...",null,100,51,null,null,"2023-06-29","2024-07-23"]
[1181,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"2022-09-12","2024-12-12",0.75,"RP-241314",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031; 2/4/24: WID:RP-233031->RP-240120; 23/7/24: WID:RP-240120->RP-241314",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1182,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...",38.896000000000001,97,49,null,null,"2022-10-19","2024-06-13"]
[1183,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"2022-10-19","2024-06-13"]
[1184,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",0.31,"RP-232774","RP-242484","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774; 14/3/24: FCD:05/06/2024->12/12/2024; Compl:...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1185,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-241254",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975; 2/4/24: WID:RP-233975->RP-240428; 23/7/24: WID:RP-240428->RP-241254",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1186,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241254","RP-241253","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....",38.896999999999998,97,49,null,null,"2022-10-19","2024-06-13"]
[1187,970287,"   Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","2022-09-13","2024-03-01",1,"RP-240428","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,102,null,"2022-10-19","2024-01-02"]
[1188,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-241302",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561; 2/4/24: WID:RP-233561->RP-240763; 23/7/24: WID:RP-240763->RP-241302",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1189,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...",38.899000000000001,97,49,null,null,"2022-10-19","2024-06-13"]
[1190,970289,"   Stopped: Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","2022-09-12","2022-09-12",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1191,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-241317",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017; 2/4/24: WID:RP-234017->RP-240123; 23/7/24: WID:RP-240123->RP-241317",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1192,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241317","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...",38.85,97,49,null,null,"2022-10-19","2024-06-13"]
[1193,970290,"   Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","2022-09-12","2024-03-01",1,"RP-240123","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,102,null,"2022-10-19","2024-06-13"]
[1194,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"2022-09-08","2024-03-01",1,"RP-232952",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952",null,97,49,null,null,"2022-09-23","2024-01-02"]
[1195,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","2022-09-08","2024-03-01",1,"RP-232952","RP-240275","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"2022-09-23","2024-03-14"]
[1196,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","2022-09-08","2025-06-06",0.91,"RP-240736",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742; 2/4/24: WID:RP-233742->RP-240736",38.761000000000003,97,49,null,null,"2022-09-23","2024-04-02"]
[1197,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","2022-09-08","2023-12-12",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1198,970281,"   Perf. Part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1199,1040112,"   UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs ","NR_MIMO_OTA_enh-UEConTest",2,"Rel-18","R5","2024-06-06","2025-06-06",0.65,"RP-241504","RP-242479","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->45%; ; 6/12/24: Compl:45%->65%; Stat Rep: ->RP-242479; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1200,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"2022-12-13","2024-03-01",1,"RP-240796",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446; 2/4/24: WID:RP-233446->RP-240796",null,98,50,null,null,"2023-01-09","2024-04-02"]
[1201,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240796","RP-240159","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"2023-01-09","2024-03-14"]
[1202,981247,"   Stopped - Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","2022-12-13","2024-03-01",1,"RP-240796","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"2023-01-09","2024-04-02"]
[1203,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"2021-12-13","2024-12-12",0.85,"RP-234027",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1204,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","2021-12-13","2023-12-12",1,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1205,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","2021-12-15","2024-06-06",1,"RP-233963","RP-240063","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1206,1030060,"   UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 ","NR_FR1_lessthan_5MHz_BW-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.46,"RP-240044","RP-242457","Nokia ",null,"13/6/24: Compl:0%->22%; Stat Rep: ->RP-240908; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:22%->43%; Stat Rep: RP-240908->RP-241737; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:43%->46%; Stat Rep: RP-241737->RP-242457; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1207,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"2021-12-13","2024-06-06",1,"RP-232957",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1208,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1209,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-232957","RP-241174","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1210,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"2021-12-13","2024-12-12",0.96,"RP-234012",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1211,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[1212,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1213,1030070,"   UE Conformance - Multi-carrier enhancements for NR ","NR_MC_enh-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.87,"RP-240346","RP-242852","China Telecom ",null,"13/6/24: Compl:0%->18%; Stat Rep: ->RP-241301; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:18%->80%; Stat Rep: RP-241301->RP-242000; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:80%->87%; Stat Rep: RP-242000->RP-242852; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1214,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"2021-12-13","2024-12-12",0.8,"RP-241295",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558; 23/7/24: WID:RP-233558->RP-241295",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1215,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-241295","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1216,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-241295","RP-241294","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1217,1030069,"   UE Conformance - Further NR coverage enhancements ","NR_cov_enh2-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.28999999999999998,"RP-240345","RP-242851","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241300; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-241300->RP-241992; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->29%; Stat Rep: RP-241992->RP-242851; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1218,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"2021-12-13","2024-12-12",0.82,"RP-233028",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1219,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1220,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","2021-12-15","2024-06-06",1,"RP-233028","RP-241282","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"2022-01-06","2024-07-23"]
[1221,1030072,"   UE Conformance - NR MIMO evolution for downlink and uplink ","NR_MIMO_evo_DL_UL-UEConTest",2,"Rel-18","R5","2024-03-03","2025-12-12",0.37,"RP-240372","RP-242596","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241279; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->19%; Stat Rep: RP-241279->RP-241982; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:19%->37%; Stat Rep: RP-241982->RP-242596; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1222,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","2021-12-13","2023-12-12",1,"RP-223041","RP-233435","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...",38.857999999999997,94,48,null,null,"2022-01-06","2023-12-08"]
[1223,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"2022-09-08","2024-06-06",1,"RP-232886",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886",null,97,49,null,null,"2022-09-23","2024-01-02"]
[{"$f":"A1224+1","v":1224},970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","2022-09-08","2023-12-12",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"2022-09-23","2024-06-13"]
[1225,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","2022-09-12","2024-06-06",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"2022-09-23","2024-07-23"]
[1226,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","2022-09-08","2024-06-06",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%->10",38.866999999999997,94,48,null,null,"2022-01-06","2022-09-23"]
[1227,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"2021-12-13","2024-12-12",0.85,"RP-233970",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1228,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","2021-12-13","2024-03-01",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[1229,940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","2021-12-15","2024-06-06",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"2022-01-06","2024-06-13"]
[1230,1040108,"   UE Conformance - Further NR mobility enhancements ","NR_Mob_enh2-UEConTest",2,"Rel-18","R5","2024-06-06","2025-12-12",0.4,"RP-241348","RP-242990","Mediatek ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->20%; Stat Rep: ->RP-242047; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:20%->40%; Stat Rep: RP-242047->RP-242990; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1231,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"2021-12-13","2026-06-05",0.59,"RP-233485",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1232,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233485","RP-233484","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1233,1040104,"   UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC ","NR_IDC_enh-UEConTest",2,"Rel-18","R5","2024-06-06","2026-06-05",0.18,"RP-241195","RP-242978","CMCC ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-241948; ; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->18%; Stat Rep: RP-241948->RP-242978; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1234,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-233976",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1235,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1236,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1237,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"2022-03-15","2025-06-06",0.9,"RP-240732",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023; 2/4/24: WID:RP-234023->RP-240732",null,95,48,null,null,"2022-04-05","2024-04-02"]
[1238,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"2022-04-05","2024-03-14"]
[1239,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","2022-03-16","2024-03-01",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"2022-04-05","2024-03-14"]
[1240,1020087,"   UE Conformance - Air-to-ground network for NR ","NR_ATG-UEConTest",2,"Rel-18","R5","2023-12-13","2025-06-06",0.64,"RP-233412","RP-242977","Dan SONG, CMCC","songdan@chinamobile.com","14/3/24: Compl:0%->50%; Stat Rep: ->RP-240148; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 2/4/24: WID:RP-233412->RP-240750. corrected: Rel-19->Rel-18; 13/6/24: WID: RP-240750->RP-233412; Stat Rep: RP-240148->RP-241201; ; ...",null,102,52,null,null,"2024-01-02","2024-12-06"]
[1241,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"2022-03-15","2025-03-03",0.88,"RP-240940",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791; 23/7/24: WID:RP-232791->RP-240940",null,95,48,null,null,"2022-04-05","2024-07-23"]
[1242,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...",38.890999999999998,95,48,null,null,"2022-04-05","2024-06-13"]
[1243,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1244,1030065,"   UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-UEConTest",2,"Rel-18","R5","2024-03-03","2025-03-03",0.4,"RP-240125","RP-242600","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241175; ; 4/9/24: FCD:03/03/2025->25/03/2025; Compl:5%->15%; Stat Rep: RP-241175->RP-242219; ; 6/12/24: Compl:15%->40%; Stat Rep: RP-242219->RP-242600; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1245,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"2022-03-15","2023-11-30",0.75,"RP-241534","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"2022-04-05","2024-07-23"]
[1246,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...",38.750999999999998,95,48,null,null,"2022-04-05","2024-06-13"]
[1247,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1248,1040113,"   UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-UEConTest",2,"Rel-18","R5","2024-06-06","2025-12-12",0.09,"RP-241653","RP-242898","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->5%; Stat Rep: ->RP-242040; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:5%->9%; Stat Rep: RP-242040->RP-242898; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1249,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"2022-03-15","2024-06-06",1,"RP-233496",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1250,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1251,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","2022-03-17","2024-06-06",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1252,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"2022-03-15","2025-06-06",0.84,"RP-233186",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1253,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...",38.881,95,48,null,null,"2022-04-05","2023-12-08"]
[1254,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-232366","RP-241240","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1255,1030066,"   UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 ","NR_ENDC_RF_FR1_enh2-UEConTest",2,"Rel-18","R5","2024-03-03","2025-06-06",0.34,"RP-240290","RP-243091","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241377; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->12%; Stat Rep: RP-241377->RP-242074; ; 6/12/24: Compl:12%->34%; Stat Rep: RP-242074->RP-243091; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1256,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"2022-03-15","2023-12-12",0.97,"RP-233513",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1257,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",0.95,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1258,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","2022-03-16","2023-12-12",1,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"2022-04-05","2024-04-02"]
[1259,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"2022-03-15","2025-12-12",0.78,"RP-234021",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021",null,95,48,null,null,"2022-04-05","2024-01-02"]
[1260,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1261,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","2022-03-15","2024-06-06",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"2022-04-05","2024-06-13"]
[1262,1050132,"   UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-UEConTest",2,"Rel-18","R5","2024-09-09","2025-12-12",0.1,"RP-242046","RP-242994","Mediatek ",null,"6/12/24: Compl:0%->10%; Stat Rep: ->RP-242994; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[1263,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","2021-12-13","2025-06-06",0.94,"RP-233071",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071",null,94,48,null,null,"2022-01-06","2024-01-02"]
[1264,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","2021-12-13","2023-12-12",1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"2022-01-06","2023-12-08"]
[1265,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","2022-03-15","2024-06-06",1,"RP-231461","RP-241045","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"2022-06-04","2024-06-13"]
[1266,1030061,"   UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR ","NR_DualTxRx_MUSIM-UEConTest",2,"Rel-18","R5","2024-03-03","2025-06-06",0.72,"RP-240045","RP-242471","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240909; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->14%; Stat Rep: RP-240909->RP-241957; ; 6/12/24: Compl:14%->72%; Stat Rep: RP-241957->RP-242471; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1267,0,"Rel-18 NR-only: band related","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1268,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","2023-03-06","2023-12-12",0.99,"RP-233245",null,"Vodafone",null,"6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245",null,99,50,null,null,"2023-04-07","2024-01-02"]
[1269,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"2023-04-07","2023-12-08"]
[1270,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630; ;",null,99,50,null,null,"2023-04-07","2023-12-08"]
[1271,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","2023-03-06","2024-06-06",0.99,"RP-233999",null,"Vodafone",null,"6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999",null,99,50,null,null,"2023-04-07","2024-01-02"]
[1272,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ; 14/...",null,99,50,null,null,"2023-04-07","2024-06-13"]
[1273,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","2023-03-08","2024-06-06",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039...",null,99,50,null,null,"2023-04-07","2024-06-13"]
[1274,1010055,"Introduction of NR bands n31 and n72 ","NR_bands_n31_n72",1,"Rel-18","R4","2023-09-09","2023-12-12",0.99,"RP-233950",null,"Nokia ",null,"2/1/24: WID:RP-232691->RP-233950",null,101,51,null,null,"2023-10-06","2024-01-02"]
[1275,1011055,"   Core part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Core",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[1276,1012055,"   Perf. part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Perf",2,"Rel-18","R4","2023-09-09","2023-12-12",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"2023-10-06","2023-12-08"]
[1277,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991",null,"CATT",null,"6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991",null,99,50,null,null,"2023-04-07","2024-01-02"]
[1278,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-233005","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; ",null,99,50,null,null,"2023-04-07","2023-12-08"]
[1279,991246,"   Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","2023-03-06","2023-12-12",1,"RP-233991","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102",null,99,50,102,null,"2023-04-07","2024-01-02"]
[1280,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"2023-01-09","2023-03-29"]
[1281,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1282,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1283,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"2022-12-13","2023-12-12",0.25,"RP-234044",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1284,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Ra",null,98,50,null,null,"2023-01-09","2023-09-21"]
[1285,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eolbr",null,98,50,null,null,"2023-01-09","2023-09-21"]
[1286,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241222",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920; 2/4/24: WID:RP-232920->RP-240761; 23/7/24: WID:RP-240761->RP-241222",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1287,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241222","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"2022-08-03","2024-06-13"]
[{"$f":"A1288+1","v":1288},961210,"   Stopped - Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240761","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1289,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241089",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231; 2/4/24: WID:RP-233231->RP-240166; 23/7/24: WID:RP-240166->RP-241089",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1290,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1291,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","2022-06-16","2024-06-06",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1292,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"2022-06-16","2023-12-12",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[1293,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"2022-08-03","NA"]
[1294,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241140",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990; 2/4/24: WID:RP-233990->RP-240238; 23/7/24: WID:RP-240238->RP-241140",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1295,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1296,961207,"   Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,102,null,"2022-08-03","2024-06-13"]
[1297,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241327",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696; 2/4/24: WID:RP-233696->RP-240501; 23/7/24: WID:RP-240501->RP-241327",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1298,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1299,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1300,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"2022-06-15","2023-03-03",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"2022-08-03","2023-03-29"]
[1301,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...",38.892000000000003,96,49,null,null,"2022-08-03","2023-03-17"]
[1302,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","2022-06-15","2023-03-03",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"2022-08-03","2023-03-17"]
[1303,960098,"Stopped - Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"2022-06-16","2023-12-12",1,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1304,960198,"   Stopped - Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#102...",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1305,960298,"   Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","2022-06-16","2023-12-12",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23: S",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1306,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"2022-06-15","2024-12-12",0.9,"RP-240422",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040; 2/4/24: WID:RP-234040->RP-240422",null,96,49,null,null,"2022-08-03","2024-04-02"]
[1307,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240422","RP-240421","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"2022-08-03","2024-03-14"]
[1308,960295,"   stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240422","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23: F",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1309,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2025-06-06",0.74,"RP-232772","RP-242485","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772; 14/3/24: FCD:05/06/2024->12/12/2024; Stat ...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1310,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"2022-06-15","2023-06-06",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"2022-08-03","2023-03-29"]
[1311,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","2022-06-15","2023-06-06",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"2022-08-03","2023-06-07"]
[1312,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","2022-06-15","2023-06-06",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"2022-08-03","2023-03-31"]
[1313,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"2022-03-15","2023-12-12",1,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1314,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1315,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","2022-03-15","2022-12-01",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"2022-04-05","2023-01-09"]
[1316,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","2023-03-03","2023-12-12",1,"RP-232783","RP-232784","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP...",null,99,50,null,null,"2023-03-29","2024-01-02"]
[1317,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","2022-06-15","2023-03-03",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualcomm-",38.893000000000001,96,49,null,null,"2022-07-12","2023-03-31"]
[1318,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2024-12-12",0.99,"RP-240287","RP-243088","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1319,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1320,1010053,"Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC",1,"Rel-18","R4","2023-09-09","2024-06-06",1,"RP-241149",null,"Oppo ",null,"2/1/24: WID:RP-232674->RP-232941; 2/4/24: WID:RP-232941->RP-240307; 23/7/24: WID:RP-240307->RP-241149",null,101,51,null,null,"2023-10-06","2024-07-23"]
[1321,1011053,"   Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2023-09-09","2024-06-06",1,"RP-241149","RP-241150","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;; 14/3/24: FCD:01/03/2024->06/06/2024; Compl:30%->70%; Stat Rep: RP-232940->RP...",38.880000000000003,101,51,null,null,"2023-10-06","2024-06-13"]
[1322,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"2022-09-12","2024-06-06",1,"RP-241144",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977; 2/4/24: WID:RP-233977->RP-240241; 23/7/24: WID:RP-240241->RP-241144",null,97,49,null,null,"2022-10-19","2024-07-23"]
[1323,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","2022-09-12","2024-06-06",1,"RP-241144","RP-241143","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...",38.898000000000003,97,49,null,null,"2022-10-19","2024-06-13"]
[1324,970288,"   Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","2022-09-12","2023-12-12",1,"RP-241144","RP-240240","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,102,null,"2022-10-19","2024-07-23"]
[1325,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.8,"RP-231199","RP-242867","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ; 14/3...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1326,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"2022-06-15","2024-12-12",0.99,"RP-240941",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180; 2/4/24: WID:RP-233180->RP-240361; 23/7/24: WID:RP-240361->RP-240941",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1327,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-240941","RP-240942","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....",37.829000000000001,96,49,null,null,"2022-08-03","2024-06-13"]
[1328,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","2023-06-08","2024-12-12",0.99,"RP-242372","RP-242836","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ; 14/3/24:...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1329,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","2023-06-08","2025-06-06",0.76,"RP-240285","RP-243087","Chunying GU, Huawei Technologies. Co., Ltd.","guchunying@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ; 14/3/24: ...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[1330,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-234046",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1331,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-234046","RP-232937","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%; S",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1332,1020088,"UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest",1,"Rel-18","R5","2023-12-13","2025-06-06",0.77,"RP-233771","RP-243090","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240289; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; 2/4/24: corrected: rel-19->Rel-18; 13/6/24: Compl:7%->26%; Stat Rep: RP-240289->RP-241376; ; 4/9/24: FCD:06/06/2025->25/06/2025;",null,102,52,null,null,"2024-01-02","2024-12-06"]
[1333,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"2022-09-08","2024-09-09",1,"RP-241251",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002; 2/4/24: WID:RP-234002->RP-240425; 23/7/24: WID:RP-240425->RP-241251",null,97,49,null,null,"2022-09-23","2024-07-23"]
[1334,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","2022-09-08","2024-06-06",1,"RP-241251","RP-241250","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",38.893999999999998,97,49,null,null,"2022-09-23","2024-06-13"]
[1335,970284,"   Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","2022-09-08","2024-03-01",1,"RP-240425","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,102,null,"2022-09-23","2024-01-02"]
[1336,1030068,"   UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-UEConTest",2,"Rel-18","R5","2024-03-03","2024-09-24",1,"RP-242077","RP-242076","Huawei ",null,"13/6/24: Compl:0%->58%; Stat Rep: ->RP-241379; ; 4/9/24: FCD:06/06/2025->24/09/2024; Compl:58%->100%; Stat Rep: RP-241379->RP-242076; ; 26/9/24: WID:RP-240292->RP-242077",null,103,52,null,null,"2024-04-02","2024-09-26"]
[1337,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"2022-09-08","2025-06-06",0.87,"RP-234064",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064",null,97,49,null,null,"2022-09-23","2024-01-02"]
[1338,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","2022-09-08","2024-12-23",1,"RP-234064","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...",38.869999999999997,97,49,null,null,"2022-09-23","2024-09-04"]
[1339,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","2022-09-12","2024-09-24",1,"RP-242327","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"2022-09-23","2024-09-26"]
[1340,1040111,"   UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-UEConTest",2,"Rel-18","R5","2024-06-06","2025-06-06",0.3,"RP-241503","RP-242480","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-241899; ; 6/12/24: Compl:5%->30%; Stat Rep: RP-241899->RP-242480; ",null,104,53,null,null,"2024-07-23","2024-12-06"]
[1341,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241248",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197; 2/4/24: WID:RP-233197->RP-240420; 23/7/24: WID:RP-240420->RP-241248",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1342,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"2022-08-03","2024-06-13"]
[1343,961209,"   Stopped - Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1344,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241233",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242; 2/4/24: WID:RP-233242->RP-240482; 23/7/24: WID:RP-240482->RP-241233",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1345,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"2022-08-03","2024-06-13"]
[1346,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","2022-06-16","2024-06-06",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1347,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"2022-06-15","2024-06-06",0.87,"RP-241274",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989; 2/4/24: WID:RP-233989->RP-240374; 23/7/24: WID:RP-240374->RP-241274",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1348,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1349,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",0.7,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1350,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241052",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488; 2/4/24: WID:RP-233488->RP-240758; 23/7/24: WID:RP-240758->RP-241052",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1351,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"2022-08-03","2024-06-13"]
[{"$f":"A1352+1","v":1352},961203,"   Stopped - Perf. Part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1353,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241245",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987; 2/4/24: WID:RP-233987->RP-240417; 23/7/24: WID:RP-240417->RP-241245",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1354,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241245","RP-241244","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"2022-08-03","2024-06-13"]
[1355,961204,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-241245","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1356,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241166",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988; 2/4/24: WID:RP-233988->RP-240384; 23/7/24: WID:RP-240384->RP-241166",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1357,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241166","RP-241165","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1358,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-241166","RP-240382","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"2022-08-03","2024-03-14"]
[1359,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241225",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923; 2/4/24: WID:RP-232923->RP-240760; 23/7/24: WID:RP-240760->RP-241225",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1360,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241225","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2024-06-13"]
[1361,961206,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240760","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1362,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"2022-06-15","2023-12-12",1,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"2022-08-03","2023-03-29"]
[1363,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Compl:5",37.878,96,49,null,null,"2022-08-03","2023-12-08"]
[1364,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"2022-08-03","2023-12-08"]
[1365,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"2022-06-15","2025-12-12",0.9,"RP-233588",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588",null,96,49,null,null,"2022-08-03","2024-01-02"]
[1366,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...",37.877000000000002,96,49,null,null,"2022-08-03","2023-12-08"]
[1367,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","2022-06-15","2023-12-12",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"2022-08-03","2023-12-08"]
[1368,1050129,"   UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-UEConTest",2,"Rel-18","R5","2024-09-09","2025-12-12",0.67,"RP-242001","RP-242853","China Telecom ",null,"6/12/24: Compl:0%->67%; Stat Rep: ->RP-242853; ",null,105,53,null,null,"2024-09-26","2024-12-06"]
[1369,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"2019-03-07","2019-03-07",0,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1370,1010054,"High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14",1,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946",null,"AT&T ",null,"2/1/24: WID:RP-232676->RP-232946",null,101,51,null,null,"2023-10-06","2024-01-02"]
[1371,1011054,"   Core part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Core",2,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;; 14/3/24: Compl:50%->100%; Stat Rep: RP-232945->RP-240075; List of Impacted TS & TR up",36.770000000000003,101,51,null,null,"2023-10-06","2024-03-14"]
[1372,1012054,"   Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Perf",2,"Rel-18","R4","2023-09-09","2024-03-01",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 14/3/24: Compl:80%->100%; Stat Rep: RP-232945->RP-240075; ",null,101,51,null,null,"2023-10-06","2024-03-14"]
[1373,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"2022-12-13","2023-12-12",1,"RP-232892",null,"Ericsson ",null,"2/1/24: WID:RP-222824->RP-232892",null,98,50,null,null,"2023-01-09","2024-01-02"]
[1374,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1375,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","2022-12-13","2023-12-12",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"2023-01-09","2023-12-08"]
[1376,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"2022-12-12","2025-03-03",0.73,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"2023-01-09","2023-03-29"]
[1377,981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","2022-12-12","2023-06-06",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"2023-01-09","2023-06-29"]
[1378,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","2022-12-12","2023-06-06",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1379,1030064,"   UE Conformance - Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-UEConTest",2,"Rel-18","R5","2024-03-03","2025-03-03",0.85,"RP-240096","RP-242838","Nokia ",null,"13/6/24: Compl:0%->85%; Stat Rep: ->RP-240915; ; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: RP-240915->RP-241747; ; 6/12/24: Stat Rep: RP-241747->RP-242838; ",null,103,52,null,null,"2024-04-02","2024-12-06"]
[1380,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"2022-12-12","2023-03-03",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"2023-01-09","2023-03-29"]
[1381,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","2022-12-12","2023-03-03",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"2023-01-09","2023-03-17"]
[1382,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"2022-06-15","2024-06-06",1,"RP-241242",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927; 2/4/24: WID:RP-233927->RP-240414; 23/7/24: WID:RP-240414->RP-241242",null,96,49,null,null,"2022-08-03","2024-07-23"]
[1383,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","2022-06-15","2024-06-06",1,"RP-241242","RP-241241","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"2022-08-03","2024-06-13"]
[1384,960299,"   Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","2022-06-15","2024-03-01",1,"RP-240414","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24: St",null,96,49,102,null,"2022-08-03","2024-01-02"]
[1385,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"2022-08-03","NA"]
[1386,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","2022-06-15","2022-12-22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"2022-08-03","2023-01-09"]
[1387,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"2023-03-29","NA"]
[1388,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[1389,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","2023-03-03","2023-12-12",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"2023-03-29","2023-06-07"]
[1390,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"2017-12-15","2017-12-15",0.34,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1391,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","2023-03-03","2023-09-08",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23: FC",null,99,50,null,null,"2023-03-29","2023-09-21"]
[1392,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","2023-03-03","2023-12-12",1,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100",37.911000000000001,99,50,null,null,"2023-03-29","2024-01-02"]
[1393,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","2022-09-08","2023-09-08",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...",38.847999999999999,97,49,null,null,"2022-09-23","2023-10-06"]
[1394,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-231468","RP-233234","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...",38.845999999999997,95,48,null,null,"2022-04-05","2023-12-08"]
[1395,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","2022-03-15","2023-12-12",1,"RP-233171","RP-233170","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"2022-04-05","2024-01-02"]
[1396,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","2022-03-15","2023-06-06",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...",38.877000000000002,95,48,null,null,"2022-04-05","2023-06-07"]
[1397,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","2022-03-03","2023-03-03",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...",38.872,95,48,null,null,"2022-04-05","2023-03-17"]
[1398,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","2019-09-19","2022-06-22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"2019-10-08","2022-07-12"]
[1399,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","2020-09-17","2023-03-03",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"2020-09-25","2023-03-17"]
[1400,0,"Rel-18 Network automation","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1401,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"2021-12-20","2024-03-03",1,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"2022-12-09","2022-12-10"]
[1402,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","2021-12-20","2022-12-12",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"2021-12-19","2022-12-10"]
[1403,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","2022-03-10","2023-03-03",1,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.738,95,48,null,null,"2022-03-10","2024-03-15"]
[1404,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65; 15/3/24: 65%->100",33.500999999999998,99,50,null,null,"2023-03-16","2024-03-15"]
[1405,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","2022-12-09","2023-06-06",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"2022-12-09","2023-06-08"]
[1406,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","2023-03-13","2024-03-03",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[1407,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","2023-03-13","2024-03-03",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"2022-12-09","2023-06-06"]
[1408,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","2022-12-15","2024-03-03",1,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"2022-06-03","2023-06-06"]
[1409,0,"Rel-18 other Studies","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1410,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","2019-12-06","2021-12-10",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"2019-12-06","2021-12-10"]
[1411,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","2022-06-02","2023-09-09",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"2022-06-20","2023-06-30"]
[1412,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1413,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","2023-06-30","2024-03-03",1,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30; 8/12/23: 30%->95; 14/3/24: 95%->100","28.531; 28.533; 28.526 ",100,51,null,null,"2023-06-30","2024-03-14"]
[1414,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","2023-05-01","2023-06-06",1,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ","; 8/12/23: 0%->100","32.240; 32.255; 32.256; 32.291; 32.298 ",100,51,null,null,"2023-06-08","2023-12-08"]
[1415,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;; 14/3/24: 60%->100","28.552; 28.554; 28.622 ; 28.318; 28.879",100,51,null,null,"2023-06-08","2024-03-14"]
[{"$f":"A1416+1","v":1416},980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024; 14/3/24: 55%->100",28.84,98,50,null,null,"2022-12-09","2024-03-14"]
[1417,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","2022-12-12","2024-03-03",1,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90; 14/3/24: 90%->100","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"2022-12-09","2024-03-14"]
[1418,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","2021-12-10","2023-12-12",1,"SP-211441",null,"Cornily Jean-Michel, Huawei","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"2021-12-10","2023-12-08"]
[1419,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","2021-12-10","2022-12-09",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"2021-12-10","2023-09-07"]
[1420,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"2022-06-02","2022-12-11"]
[1421,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","2022-06-02","2024-03-03",1,"SP-240271",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;; 14/3...","28.552; 32.425; 28.554; 28.550 ; 28.558",96,49,null,null,"2022-06-02","2024-04-02"]
[1422,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","2020-03-25","2023-12-12",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"2019-12-06","2023-06-08"]
[1423,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024; 14/3/24: 70%->","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"2022-03-10","2024-03-14"]
[1424,890016,"Study on access control for management service ","FS_MNSAC",1,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"2020-09-11","2021-09-13"]
[1425,930010,"Access control for management service ","MSAC",1,"Rel-18","S5","2021-09-10","2024-03-03",1,"SP-231711",null,"Clifton Fernandes, Nokia ","Clifton.fernandes@nokia.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP...",28.318999999999999,93,47,null,null,"2021-09-10","2024-03-14"]
[1426,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","2021-09-10","2023-12-12",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"2021-12-10","2023-09-07"]
[1427,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","2020-09-16","2022-03-10",1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100",null,89,45,null,null,"2020-09-10","2023-12-08"]
[1428,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","2021-03-18","2022-03-11",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"2021-03-18","2022-06-04"]
[1429,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","2021-03-18","2023-06-06",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23","New ",91,46,null,null,"2021-03-18","2023-06-08"]
[1430,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-231443",null,"Zhang Kai, Huawei ","kai.zhangkai@huawei.com","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;; 14/3/24: 55%->100","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871",99,50,null,null,"2023-03-16","2024-03-14"]
[1431,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100",28.864000000000001,94,48,null,null,"2021-12-13","2023-06-08"]
[1432,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added;","28.541; 28.552; 28.554 ; 28.877",99,50,null,null,"2023-03-16","2024-01-04"]
[1433,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","2021-12-13","2023-03-03",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100",28.907,94,48,null,null,"2021-12-13","2023-03-17"]
[1434,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100",28.913,94,48,null,null,"2021-12-13","2023-06-08"]
[1435,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-240269",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92; 14/3/...",28.864999999999998,94,48,null,null,"2021-12-13","2024-04-02"]
[1436,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","2021-12-13","2024-03-03",1,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80; 14/3/24: 80%->100",28.908999999999999,94,48,null,null,"2021-12-13","2024-03-14"]
[1437,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","2021-12-13","2023-12-12",1,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100",28.91,94,48,null,null,"2021-12-13","2023-12-08"]
[1438,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","2021-12-13","2023-06-06",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100",28.911999999999999,94,48,null,null,"2021-12-13","2023-06-08"]
[1439,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774",28.831,95,48,null,null,"2022-03-10","2023-06-30"]
[1440,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",28.902999999999999,95,48,null,null,"2022-03-10","2023-06-08"]
[1441,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","2022-03-10","2023-03-03",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->",28.832999999999998,95,48,null,null,"2022-03-10","2023-06-08"]
[1442,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100","28.541; 28.552; 28.554 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1443,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added;","28.834; 28.869",95,48,null,null,"2022-03-10","2024-01-04"]
[1444,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added;","28.835; 28.878",95,48,null,null,"2022-03-10","2024-01-04"]
[1445,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30; 8/12/23: 30%->60; 14/3/24: 60%->100","32.130; 28.541; 28.552 ",100,51,null,null,"2023-06-08","2024-03-14"]
[1446,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","2022-03-10","2023-06-06",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773",28.837,95,48,null,null,"2022-03-10","2023-06-30"]
[1447,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","2022-03-10","2024-03-03",1,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65; 14/3/24: 65%->100",28.83,95,48,null,null,"2022-03-10","2024-03-14"]
[1448,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","2022-06-02","2022-12-12",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"2022-06-02","2023-06-08"]
[1449,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","2021-06-11","2023-12-12",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"2021-06-11","2023-12-08"]
[1450,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","2023-03-16","2023-09-09",1,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 8/12/23: 0%->100","32.240; 32.290 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1451,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","2021-06-11","2023-09-09",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"2021-06-11","2023-09-07"]
[1452,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,51,null,null,"2023-09-06","2024-03-14"]
[1453,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","2022-09-12","2023-03-10",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"2022-09-11","2023-03-17"]
[1454,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","2022-09-12","2024-03-03",1,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;; 14/3/24: 80%->100","; 28.842; 28.873",97,49,null,null,"2022-09-11","2024-03-14"]
[1455,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","2022-09-12","2023-12-12",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100",28.838999999999999,97,49,null,null,"2022-09-11","2023-09-07"]
[1456,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","2023-09-06","2024-03-03",1,"SP-240268",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;; 8/12/23: 0%->60; 14/3/24: 60%->100; 2/4/24: WID:SP-231151->SP-240268","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,51,null,null,"2023-09-06","2024-04-02"]
[1457,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80; 14/3/24: 80%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"2023-03-16","2024-03-14"]
[1458,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","2023-03-16","2023-12-12",1,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30; 8/12/23: 30%->100","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"2023-03-16","2023-12-08"]
[1459,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","2023-03-16","2024-03-03",1,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 65%->100","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"2023-03-16","2024-03-14"]
[1460,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1461,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","2021-06-11","2023-03-03",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...",33.875999999999998,92,47,null,null,"2021-06-11","2023-06-08"]
[1462,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","2023-03-16","2023-09-09",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100",33.31,99,50,null,null,"2023-03-16","2023-09-07"]
[1463,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","2022-12-09","2023-03-03",1,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.500999999999998,98,50,null,null,"2022-12-09","2024-03-15"]
[1464,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","NA"]
[1465,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"2022-06-03","2023-06-06"]
[1466,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","2022-06-03","2023-12-12",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"2022-06-03","2023-06-09"]
[1467,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","2022-06-03","2023-03-03",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"2022-06-03","2022-07-13"]
[1468,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","2023-06-07","2024-03-03",1,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,51,null,null,"2023-06-07","2023-06-30"]
[1469,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","2023-12-12","2023-12-12",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"2018-06-06","2021-09-13"]
[1470,0,"Rel-18 other aspects","-",1,"Rel-18",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1471,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"2021-03-12","2023-03-03",0,null,null,null,null,null,null,92,47,null,null,"2015-06-15","2015-06-15"]
[1472,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","2021-03-12","2023-09-09",0.96,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;; 5/9/24: 20%->90; 5/12/24: 90%->96","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"2021-06-11","2024-12-05"]
[1473,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"2019-03-07","2019-03-07",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"2022-03-13","NA"]
[1474,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","2022-01-05","2023-03-16",1,null,null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"2023-06-08","2023-06-08"]
[1475,1040002,"Update of conformance test specifications to Rel-18","UEConTest_R18",1,"Rel-18","C6","2023-06-29","2025-06-06",0.2,"CP-241022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,null,92,47,null,null,"2021-08-12","NA"]
[1476,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1477,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1478,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"2019-03-07","2019-12-12",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1479,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[{"$f":"A1480+1","v":1480},840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"2019-05-31","2020-06-26"]
[1481,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","2019-06-06","2021-03-12",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"2019-05-31","2021-03-19"]
[1482,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"2020-06-12","2022-06-10",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","NA"]
[1483,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"2020-12-03","2022-03-12"]
[1484,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1485,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"2021-03-18","2022-06-20"]
[1486,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1487,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1488,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1489,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"2020-06-25","2022-06-04"]
[1490,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1491,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","2018-06-06","2019-06-12",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"2018-06-06","2019-09-13"]
[1492,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1493,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","2021-03-18","2022-06-10",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"2021-03-18","2022-06-04"]
[1494,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","2019-03-07","2021-06-11",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"2018-12-06","2021-09-13"]
[1495,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","2019-06-06","2020-03-12",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"2019-05-31","2022-03-22"]
[1496,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","2020-12-04","2021-12-10",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"2020-12-04","2022-03-12"]
[1497,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1498,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1499,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-06-28"]
[1500,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"2019-05-31","2020-09-13"]
[1501,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"2020-09-25","2022-06-04"]
[1502,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"2019-05-31","2020-06-25"]
[1503,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"2019-09-13","NA"]
[1504,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"2018-09-06","2019-09-13"]
[1505,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","2019-09-19","2019-12-12",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1506,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"2019-05-31","2020-12-05"]
[1507,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","2020-03-25","2021-09-08",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"2019-05-31","2021-12-10"]
[1508,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"2021-03-18","2021-06-11"]
[1509,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"2021-03-18","2022-06-20"]
[1510,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"2021-03-18","2022-03-12"]
[1511,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"2021-03-18","2022-06-20"]
[1512,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"2019-03-07","2024-12-12",0.99,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"2021-01-06","2021-04-07"]
[1513,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1514,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","2020-12-14","2022-03-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[1515,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-09-22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"2021-01-06","2022-09-23"]
[1516,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","2022-09-08","2024-12-12",0.99,"RP-222384","RP-243119","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"2022-09-23","2024-12-06"]
[1517,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"2019-05-31","NA"]
[1518,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","2018-09-06","2019-09-13",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"2018-09-06","2019-12-06"]
[1519,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1520,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1521,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"2018-09-06","2019-12-13",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"2019-05-31","NA"]
[1522,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","2018-09-06","2019-12-13",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[1523,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"2019-05-31","2019-12-06"]
[1524,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","2018-12-06","2020-12-15",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"2018-12-06","2020-12-05"]
[1525,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","2018-12-06","2021-03-12",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"2018-12-06","2021-03-21"]
[1526,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"2020-12-04","2021-03-21"]
[1527,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","2020-12-04","2021-06-11",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"2020-12-04","2021-07-02"]
[1528,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1529,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"2021-06-11","2022-03-12"]
[1530,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100",33.853999999999999,88,45,null,null,"2020-06-25","2023-03-31"]
[1531,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"2018-09-06","2024-12-12",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"2018-09-06","NA"]
[1532,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","2018-09-06","2018-12-14",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"2018-09-06","2018-12-04"]
[1533,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"2020-12-03","2021-12-10"]
[1534,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1535,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1536,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"2021-03-18","2022-03-12"]
[1537,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1538,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","2021-06-11","2022-03-11",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"2021-06-11","2022-03-12"]
[1539,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","2023-03-03","2024-12-12",1,"RP-241591","RP-241126","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ; 14/3/24: FCD:12/12/2023->12/12/2024; Compl:40%->95%; ...",null,99,50,null,null,"2023-03-29","2024-07-23"]
[1540,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1541,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","NA"]
[1542,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","2018-06-06","2018-09-14",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[1543,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","2018-06-06","2020-06-25",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"2018-06-06","2020-06-26"]
[{"$f":"A1544+1","v":1544},860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","2019-12-06","2021-09-08",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"2019-12-06","2021-12-10"]
[1545,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2021-06-11"]
[1546,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-06-04"]
[1547,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","2020-09-16","2021-09-10",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1548,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"2020-09-12","2022-03-12"]
[1549,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","2021-09-13","2022-03-11",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"2020-09-12","2022-06-04"]
[1550,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"2019-12-16","2024-12-12",0.95,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"2020-01-14","2022-04-05"]
[1551,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","2019-12-16","2022-06-06",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"2020-01-14","2023-03-17"]
[1552,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","2019-12-16","2023-03-03",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[1553,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2025-06-06",0.86,"RP-221241","RP-242897","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"2022-07-12","2024-12-06"]
[1554,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2021-06-15","2024-03-01",0.99,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"2021-07-02","NA"]
[1555,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","2021-06-15","2022-06-22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"2021-07-02","2022-06-20"]
[1556,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-233250","RP-240442","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"2022-07-12","2024-03-14"]
[1557,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"2021-09-10","2022-03-12"]
[1558,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"2022-03-12","2022-06-20"]
[1559,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1560,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-03-12"]
[1561,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","2021-12-13","2022-03-15",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"2022-03-12","2022-06-04"]
[1562,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","2019-03-07","2021-03-12",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"2019-03-14","2021-03-21"]
[1563,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","2019-12-16","2021-06-15",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"2020-01-14","2021-07-02"]
[1564,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1565,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"2019-09-13","2021-06-11"]
[1566,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","2020-06-12","2021-06-11",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"2020-06-25","2021-06-11"]
[1567,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","2021-06-11","2021-06-18",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-03-24"]
[1568,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"2020-12-03","NA"]
[1569,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"2020-12-03","2021-09-13"]
[1570,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1571,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1572,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1573,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1574,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1575,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"2019-03-07","2022-09-22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1576,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","2021-12-21","2022-03-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1577,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","2019-03-07","2022-09-22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1578,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"2019-12-16","2024-12-12",0.99,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1579,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1580,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","2019-12-16","2022-12-21",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...; 9/",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1581,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","2022-06-15","2024-12-12",0.99,"RP-221238","RP-242497","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"2022-07-12","2024-12-06"]
[1582,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"2019-12-16","2023-12-12",1,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1583,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"2020-01-14","2022-12-09"]
[1584,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","2020-06-15","2022-12-01",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...; 9/",null,86,44,null,null,"2020-09-25","2022-12-09"]
[1585,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221416","RP-232885","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1586,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[1587,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"2019-12-16","2025-03-03",0.79,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"2020-01-14","2021-01-06"]
[1588,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","2019-12-16","2022-03-11",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1589,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...; 23",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1590,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2025-03-03",0.4,"RP-221448","RP-243117","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"2022-07-12","2024-12-06"]
[1591,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","2019-12-16","2020-09-15",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[1592,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","2019-06-06","2020-06-12",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"2019-05-31","2022-03-22"]
[1593,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-02-10"]
[1594,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"2020-09-11","2021-06-11"]
[1595,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1596,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1597,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1598,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"2021-03-18","NA"]
[1599,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"2019-09-13","2021-03-19"]
[1600,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","2021-03-18","2021-09-08",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"2021-03-18","2021-12-10"]
[1601,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1602,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"2021-06-11","2022-03-22"]
[1603,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"2021-06-11","2022-06-04"]
[1604,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1605,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","2021-06-15","2023-09-22",0.99,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"2021-07-02","2021-09-29"]
[1606,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"2021-07-02","2022-03-22"]
[1607,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","2021-06-15","2022-03-11",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"2021-07-02","2022-03-22"]
[{"$f":"A1608+1","v":1608},940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","2021-12-13","2023-09-22",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"2022-01-06","2023-09-06"]
[1609,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"2019-12-16","2024-09-09",1,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"2020-01-14","2021-09-29"]
[1610,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1611,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","2019-12-16","2022-12-01",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"2020-01-14","2023-01-09"]
[1612,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-24",1,"RP-241983","RP-241980","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"2022-07-12","2024-09-26"]
[1613,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"2020-01-14","2021-07-02"]
[1614,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","2019-12-16","2022-03-22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1615,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"2019-12-16","2024-03-01",1,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1616,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","2019-12-16","2022-03-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1617,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"2020-01-14","2022-09-23"]
[1618,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-01",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"2020-07-28","2023-01-09"]
[1619,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-233247","RP-233246","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"2022-07-12","2024-04-02"]
[1620,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"2019-12-16","2024-06-06",1,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"2020-01-14","2020-07-28"]
[1621,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1622,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","2019-12-16","2022-09-22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1623,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","2023-03-03","2024-06-06",1,"RP-233764","RP-241372","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ; 8/12/23: FCD:03/03/2024->01/03/2024; Compl:46%->94%; Stat Rep: RP-232355->RP-233763; ; 2/1/24: WID...",null,99,50,null,null,"2023-03-29","2024-06-13"]
[1624,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"2019-03-11","2022-09-22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"2020-01-14","2022-07-12"]
[1625,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","2019-12-16","2022-06-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1626,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","2019-12-16","2022-09-22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"2020-01-14","2022-09-09"]
[1627,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","2019-03-11","2021-12-10",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"2019-03-14","2022-03-12"]
[1628,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"2019-12-16","2022-03-09",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"2020-01-14","2022-01-21"]
[1629,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-09",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1630,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"2020-09-15","2024-09-09",1,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126 ; ",null,89,45,null,null,"2020-10-11","2022-07-12"]
[1631,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","2021-12-14","2022-06-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"2022-03-22","2022-06-20"]
[1632,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"2020-10-11","2022-09-09"]
[1633,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-24",1,"RP-241994","RP-241993","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"2022-07-12","2024-09-26"]
[1634,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"2020-09-15","2023-12-12",1,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1635,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1636,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1637,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","2022-06-15","2023-12-12",1,"RP-221240","RP-233873","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"2022-07-12","2023-12-08"]
[1638,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"2020-09-15","2022-09-22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1639,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1640,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1641,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"2020-09-15","2023-06-06",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1642,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1643,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1644,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[1645,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"2020-09-15","2024-03-01",1,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366 ; ",38.850999999999999,89,45,null,null,"2020-10-11","2022-07-12"]
[1646,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","2020-09-15","2022-06-22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1647,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1648,970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",1,"RP-240751","RP-240092","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"2022-09-23","2024-04-02"]
[1649,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"2020-09-15","2024-12-12",0.85,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"2020-10-11","2021-04-07"]
[1650,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1651,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1652,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","2022-06-15","2025-06-06",0.68,"RP-221402","RP-242594","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"2022-07-12","2024-12-06"]
[1653,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"2020-09-15","2024-06-06",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"2020-10-11","2022-01-06"]
[1654,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation;",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1655,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1656,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","2022-12-14","2024-06-06",1,"RP-223246","RP-241346","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ; 8/12/23: FCD:03/03/2024...",null,98,50,null,null,"2023-01-09","2024-06-13"]
[1657,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"2020-09-15","2024-03-01",1,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"2020-10-11","2022-04-05"]
[1658,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","2020-09-15","2022-03-22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"2020-10-11","2022-06-20"]
[1659,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","2020-09-15","2022-09-22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"2020-10-11","2022-09-09"]
[1660,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","2022-06-15","2024-03-01",1,"RP-221848","RP-240280","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"2022-07-12","2024-03-14"]
[1661,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","2021-12-13","2022-09-22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"2022-01-06","2022-04-05"]
[1662,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1663,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","2021-12-13","2022-03-11",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"2022-01-06","2022-03-22"]
[1664,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","2022-06-15","2022-09-22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"2022-07-12","2022-09-23"]
[1665,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1666,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"2019-12-16","2022-03-22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1667,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","2019-12-16","2022-03-22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:65%",null,86,44,null,null,"2020-01-14","2022-06-20"]
[1668,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1669,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"2019-12-06","2022-06-21"]
[1670,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","2019-09-19","2020-09-14",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"2019-09-13","2020-09-13"]
[1671,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","2020-06-12","2021-12-10",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"2020-06-26","2021-12-13"]
[{"$f":"A1672+1","v":1672},0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1673,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"2019-05-31","2021-06-11"]
[1674,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","2018-09-14","2020-03-12",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"2018-09-14","2020-12-05"]
[1675,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"2020-06-25","2022-03-12"]
[1676,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","2019-09-19","2020-03-12",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"2019-09-13","2020-03-26"]
[1677,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"2019-03-07","2024-03-03",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1678,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"2019-03-14","2021-03-19"]
[1679,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","2020-12-03","2021-09-10",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-06-04"]
[1680,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"2021-06-11","2022-06-04"]
[1681,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"2021-06-11","2022-06-20"]
[1682,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"2021-06-11","2022-06-20"]
[1683,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","2021-06-11","2022-03-11",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"2022-06-20","NA"]
[1684,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"2021-06-11","2022-06-04"]
[1685,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-231712",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30; 8/12/23: 30%->65; 3/1/24: WID:SP-230623->SP-231712; 14/3/24: 65%->100","32.240; 32.255; 32.298; 32.291; 33.279; 33.290",100,51,null,null,"2023-06-08","2024-03-14"]
[1686,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","2019-09-02","2019-12-12",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"2019-09-13","2019-12-06"]
[1687,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1688,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","2019-12-16","2023-12-12",0.99,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"2020-01-14","2022-04-05"]
[1689,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","2019-12-16","2022-03-11",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"2020-01-14","2022-03-22"]
[1690,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","2022-03-15","2023-12-12",1,"RP-220423","RP-233760","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"2022-04-05","2023-12-08"]
[1691,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"2020-09-11","2021-03-21"]
[1692,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"2020-09-11","2021-06-11"]
[1693,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1694,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"2019-12-06","2022-03-11",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"2019-12-06","2020-09-13"]
[1695,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"2019-12-06","2021-06-11"]
[1696,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","2020-06-17","2022-03-11",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"2020-09-25","2022-06-04"]
[1697,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","2018-12-13","2022-03-11",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"2018-12-07","2022-06-04"]
[1698,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","2020-09-16","2021-09-08",1,null,null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"2020-09-25","2021-09-13"]
[1699,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1700,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"2019-03-07","2022-06-07",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"2019-12-06","2020-03-26"]
[1701,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","2019-03-07","2019-12-05",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"2019-03-14","2020-03-26"]
[1702,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","2019-12-06","2021-06-15",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"2019-12-06","2021-06-11"]
[1703,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"2020-12-05","2021-06-11"]
[1704,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","2020-12-07","2022-03-11",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"2020-12-05","2022-06-04"]
[1705,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","2020-12-07","2022-03-11",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1706,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","2020-12-07","2022-06-07",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"2022-06-20","2022-08-03"]
[1707,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"2019-03-14","2020-12-05"]
[1708,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"2020-12-03","2022-03-11",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1709,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1710,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"2021-03-18","2021-09-10"]
[1711,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"2021-03-18","2022-06-04"]
[1712,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"2021-03-18","2022-03-12"]
[1713,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"2021-03-18","2022-06-04"]
[1714,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","2021-06-11","2021-12-10",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"2021-06-11","2022-03-12"]
[1715,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","2021-06-11","2022-03-11",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"2021-06-11","2022-06-04"]
[1716,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"2020-06-25","2022-03-12"]
[1717,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","2021-12-10","2022-06-10",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"2021-12-10","2022-06-04"]
[1718,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"2021-09-10","2022-03-22"]
[1719,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","2020-06-25","2021-12-10",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"2020-06-26","2022-06-21"]
[1720,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","2021-09-10","2022-03-11",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"2021-09-10","2022-06-04"]
[1721,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","2020-03-25","2021-09-08",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"2019-12-06","2021-09-13"]
[1722,0,"Rel-17 Slicing","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1723,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"2021-06-11","2022-04-28"]
[1724,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"2021-06-11","2022-06-20"]
[1725,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1726,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","2021-06-11","2022-03-11",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1727,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1728,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"2019-09-19","2023-06-06",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1729,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","2019-09-19","2021-03-12",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"2019-09-13","2021-03-19"]
[1730,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-22"]
[1731,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","2021-03-18","2023-06-06",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"2021-03-18","2021-10-01"]
[1732,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"2021-03-18","2022-03-12"]
[1733,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"2021-03-18","2022-06-04"]
[1734,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"2021-03-18","2022-03-12"]
[1735,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","2022-03-15","2023-06-06",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"2022-04-05","2023-06-07"]
[{"$f":"A1736+1","v":1736},911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","2019-03-07","2023-09-22",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"2021-04-07","2022-07-12"]
[1737,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","2021-03-12","2022-06-22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[1738,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","2022-06-15","2023-09-22",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17...; ",null,96,49,null,null,"2022-07-12","2023-09-06"]
[1739,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","2022-06-03","2022-06-20",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-03","2022-06-04"]
[1740,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","2019-03-07","2019-03-07",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"2022-06-20","2022-08-03"]
[1741,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","2019-12-06","2021-12-10",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"2019-12-06","2021-12-13"]
[1742,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","2022-03-10","2022-03-11",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"2022-03-10","2022-03-12"]
[1743,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1744,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","NA"]
[1745,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","2019-03-07","2019-09-06",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"2019-03-14","2019-12-06"]
[1746,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1747,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"2018-12-06","2021-09-13"]
[1748,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1749,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"2021-03-18","2021-09-10"]
[1750,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1751,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-18","2022-03-12"]
[1752,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"2020-12-04","2021-09-13"]
[1753,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"2019-12-09","2023-09-22",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"2020-06-10","2022-01-06"]
[1754,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","2019-12-09","2022-03-22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"2020-06-10","2022-06-20"]
[1755,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","2022-03-15","2023-09-22",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"2022-04-05","2023-09-06"]
[1756,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1757,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"2019-06-06","2021-12-10",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1758,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","2019-06-06","2020-12-11",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"2019-05-31","2021-06-11"]
[1759,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"2020-09-10","2022-03-12"]
[1760,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1761,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"2020-09-11","2021-06-11"]
[1762,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","2020-09-16","2021-06-15",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"2020-09-11","2021-12-13"]
[1763,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"2021-09-10","NA"]
[1764,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"2021-09-10","2022-06-04"]
[1765,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"2021-09-10","2022-03-12"]
[1766,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","2021-09-29","2024-06-06",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"2021-09-29","NA"]
[1767,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"2021-09-29","2022-03-12"]
[1768,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"2021-09-29","2022-06-04"]
[1769,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","2023-06-08","2024-06-06",1,"RP-230873","RP-240910","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ; 14/3/24: FCD:03/03/2024->06/06/2024; Compl:5%->74%; Stat Rep: RP-231826->RP-240115; ; ...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1770,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"2020-09-25","2021-06-11"]
[1771,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","2020-09-16","2022-06-09",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.866999999999997,89,45,null,null,"2020-09-25","2023-03-31"]
[1772,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.500999999999998,93,47,null,null,"2021-09-10","2023-03-31"]
[1773,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"2021-03-18","2021-12-13"]
[1774,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","2021-12-13","2024-03-01",0.99,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"2022-01-06","2023-03-29"]
[1775,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","2021-12-13","2022-03-22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"2022-01-06","2022-06-04"]
[1776,970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","2022-09-08","2024-03-01",1,"RP-240048","RP-240047","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"2022-09-23","2024-04-02"]
[1777,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"2021-03-18","2021-06-11"]
[1778,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","2021-06-12","2021-06-12",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"2021-08-12","2022-03-11"]
[1779,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"2021-03-18","2022-03-11",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2021-09-13"]
[1780,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","2021-03-18","2021-12-10",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1781,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"2021-12-10","2022-06-04"]
[1782,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"2021-12-10","2022-03-12"]
[1783,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1784,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->",33.534999999999997,92,47,null,null,"2021-06-11","2022-09-12"]
[1785,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","2021-06-11","2022-06-10",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"2021-06-11","2022-06-04"]
[1786,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"2022-03-10","2022-06-04"]
[1787,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","2020-12-07","2020-12-18",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"2020-12-05","2020-12-05"]
[1788,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1789,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"2019-03-07","2021-09-10",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1790,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","2019-05-09","2019-06-06",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[1791,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"2020-12-05","2021-03-21"]
[1792,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1793,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","2019-03-07","2021-09-10",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"2022-09-07","2022-09-23"]
[1794,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","2020-12-04","2021-12-10",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"2020-12-04","2021-12-13"]
[1795,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"2020-12-04","2022-03-11",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"2020-12-04","2021-03-21"]
[1796,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","2020-12-04","2021-06-15",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"2020-12-04","2021-09-13"]
[1797,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"2021-06-11","2022-06-04"]
[1798,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","2021-06-11","2022-03-11",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100",29.548999999999999,92,47,null,null,"2021-06-11","2022-06-04"]
[1799,940018,"   Security for eSEAL ","eSEAL",2,"Rel-17","S3","2021-12-10","2021-12-10",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100",33.433999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[{"$f":"A1800+1","v":1800},900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"2019-03-07","2024-06-06",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"2020-12-03","NA"]
[1801,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","2019-03-07","2020-12-15",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"2019-06-26","2021-03-19"]
[1802,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","2020-12-03","2021-06-11",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"2020-12-03","2021-09-13"]
[1803,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1804,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"2021-03-18","2022-06-04"]
[1805,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"2021-03-18","2021-12-13"]
[1806,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"2021-03-18","2022-03-12"]
[1807,1010050,"   UE Conformance - ATSSS_Ph2","ATSSS_Ph2-UEConTest",2,"Rel-17","R5","2023-09-11","2024-06-06",1,"RP-240912","RP-240911","China Telecom ",null,"13/6/24: FCD:09/09/2024->06/06/2024; Compl:0%->100%; Stat Rep: ->RP-240911; ; 23/7/24: WID:RP-231827->RP-240912",null,101,51,null,null,"2023-10-06","2024-07-23"]
[1808,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"2019-06-06","2022-03-11",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"2020-12-03","NA"]
[1809,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","2019-06-06","2020-12-15",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"2019-05-31","2021-03-19"]
[1810,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","2020-09-16","2022-03-11",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22",33.866,89,45,null,null,"2020-09-10","2022-03-12"]
[1811,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"2020-12-03","2021-12-10"]
[1812,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"2021-03-19","2021-06-11"]
[1813,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"2021-03-19","2022-06-04"]
[1814,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1815,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","2021-09-10","2021-12-10",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100",33.500999999999998,93,47,null,null,"2021-09-10","2022-03-12"]
[1816,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"2019-03-07","2022-06-10",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"2020-12-03","NA"]
[1817,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","2019-03-07","2021-03-12",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"2019-03-14","2021-12-10"]
[1818,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","2020-12-03","2021-09-08",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"2020-12-03","2022-03-12"]
[1819,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"2021-03-18","2022-07-13"]
[1820,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"2021-03-18","2022-06-04"]
[1821,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100",29.556999999999999,91,46,null,null,"2021-03-18","2022-03-12"]
[1822,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90",29.559000000000001,91,46,null,null,"2021-03-18","2022-06-04"]
[1823,920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","2021-03-18","2022-03-11",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"2021-03-18","2022-06-04"]
[1824,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","2020-09-16","2021-12-10",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"2020-09-10","2022-06-21"]
[1825,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","2021-12-10","2022-06-10",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1826,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","2020-06-12","2022-06-10",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ",33.847000000000001,88,45,null,null,"2020-06-25","2022-06-04"]
[1827,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","2021-09-10","2022-06-09",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"2021-09-10","2023-03-31"]
[1828,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"2021-04-07","2021-09-29"]
[1829,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","2021-03-12","2022-03-22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, huan",38.350999999999999,91,46,null,null,"2021-04-07","2022-06-20"]
[1830,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[1831,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"2019-09-19","2022-03-11",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"2019-09-13","2020-06-26"]
[1832,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","2019-09-19","2020-06-12",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"2019-09-13","2022-03-12"]
[1833,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"2020-09-11","2020-09-25"]
[1834,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100",24.501000000000001,89,45,null,null,"2020-09-11","2022-03-12"]
[1835,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"2020-09-11","2022-03-12"]
[1836,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"2020-09-11","2022-03-12"]
[1837,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","2020-09-17","2024-09-09",0.99,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"2020-09-25","2021-09-29"]
[1838,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","2020-09-17","2022-03-11",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[1839,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","2022-06-15","2024-09-24",1,"RP-242005","RP-242006","Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm","gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222942; Rapporteur: ChinaTelecom->Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm; Rap eMail: ->gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com; 17/3/23: FCD:30/11/202.....",null,96,49,null,null,"2022-07-12","2024-09-26"]
[1840,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"2017-12-15","2022-03-11",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"2019-05-31","NA"]
[1841,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","2017-12-15","2019-09-12",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"2017-12-15","2020-08-17"]
[1842,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","2019-09-19","2020-06-12",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,96,null,"2019-09-13","2022-03-22"]
[1843,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"2019-05-31","2019-12-06"]
[1844,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","2020-03-25","2021-06-11",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"2020-03-25","2022-03-12"]
[1845,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"2020-06-26","NA"]
[1846,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1847,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1848,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1849,890011,"Mission critical security enhancements phase 2 ","MCXSec2",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200879",null,"Woodward, Tim, Motorola Solutions, Inc, ","tim.woodward@motorolasolutions.com ","; 12/9/20: FCD:12/03/2021->06/21; 12/9/20: 0%->10; 25/9/20: WID:SP-200718->SP-200879; 5/12/20: 10%->100; 19/3/21: 100%->25; 11/6/21: 25%->80; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 80%->82; 13/12/21: 82%->100",33.18,89,45,null,null,"2020-09-11","2021-12-13"]
[1850,890070,"PAP/CHAP protocols usage in 5GS ","PAP_CHAP",1,"Rel-17","ct","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 29.561 ; 12/3/22: 99%->100",null,89,45,null,null,"2020-09-25","2022-03-12"]
[1851,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","2020-09-16","2021-09-10",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1852,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","2020-09-16","2021-03-12",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"2020-09-25","2021-06-11"]
[1853,890001,"Service-based support for SMS in 5GC ","SMS_SBI",1,"Rel-17",null,"2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","25/9/20: WID:CP-202028->CP-202242; 10/9/21: WID:CP-202242->CP-212023",null,89,45,null,null,"2020-09-11","2021-09-10"]
[1854,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"2020-09-11","2022-03-12"]
[1855,890029,"   CT4 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->15; 21/3/21: 15%->25; 11/6/21: 25%->35; 13/9/21: FCD:Wed 08/09/->03/22; 13/9/21: 35%->40; 1/10/21: 23.540 added;; 13/12/21: 40%->45; 12/3/22: 45%->65; 22/3/22: 29.577 added;; 22/3/22: 29.579 added;; 22/3/22: ; ","29.503; 29.540; 29.571; 23.540; 29.577; 29.579; 29.578",89,45,null,null,"2020-09-11","2022-08-03"]
[1856,840048,"Enhanced Relays for Energy eFficiency and Extensive Coverage ","REFEC",1,"Rel-17",null,"2018-09-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1857,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","2018-09-06","2019-06-14",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100",22.866,81,41,null,null,"2018-09-06","2019-12-06"]
[1858,840034,"   Stage 1 of REFEC","REFEC",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-190307",null,"Norp, Toon, KPN ","toon.norp@tno.nl ","13/9/19: 0%->90; 6/12/19: 90%->100",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-06"]
[1859,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"2018-06-06","2019-12-12",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"2019-05-31","NA"]
[1860,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","2018-06-06","2019-03-14",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100",22.841999999999999,80,41,null,null,"2018-06-06","2019-05-31"]
[1861,840030,"   Stage 1 of NCIS","NCIS",2,"Rel-17","S1","2019-06-06","2019-12-12",1,"SP-191039",null,"Ning YANG, oppo ","yangning@oppo.com ","13/9/19: 0%->85; 6/12/19: 80%->100; 12/12/19: WID:SP-190303->SP-191039",22.260999999999999,84,43,null,null,"2019-05-31","2019-12-12"]
[1862,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","2019-06-06","2021-06-11",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"2019-05-31","2021-06-11"]
[1863,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","2020-09-16","2021-06-11",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"2020-09-10","2021-06-11"]
[{"$f":"A1864+1","v":1864},880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"2019-09-02","2020-12-11",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1865,850041,"   Stage 1 of MuDE","MuDE",2,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1866,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","2020-06-25","2020-12-11",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"2020-06-26","2021-06-11"]
[1867,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"2020-06-26","2021-09-10"]
[1868,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1869,880014,"   CT4 aspects of BEPoP","BEPoP",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->45; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 45%->55; 13/12/21: 55%->80; 12/3/22: 80%->100",29.82,88,45,null,null,"2020-06-26","2022-03-12"]
[1870,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","2020-06-25","2021-09-10",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"2020-06-25","2021-12-13"]
[1871,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","2019-06-06","2020-09-11",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100",23.18,84,43,null,null,"2019-05-31","2020-12-05"]
[1872,840016,"Stopped - Supporting Flexible Local Area Data Network ","FLADN",1,"Rel-17","S2","2019-06-06","2020-09-11",1,"SP-190563",null,"LG Electronics, Hyunsook Kim ","hyuns.kim@lge.com ","21/1/22: stopped at 0%; 21/1/22: 0%->100","23.501; 23.502 ",84,43,95,null,"2019-05-31","2022-01-21"]
[1873,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","2018-12-13","2022-03-11",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"2019-03-14","2022-03-12"]
[1874,860012,"Handsets Featuring Non-Traditional Earpieces","HaNTE",1,"Rel-17","S4","2019-12-06","2022-03-11",1,"SP-190989",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com","25/3/20: 0%->5; 20/4/20: FCD:12/03/2020->09/20. Study in Rel-16; 10/6/20: 5%->25; 26/6/20: 25%->25; 12/9/20: 25%->35; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 35%->35; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 35%->50; 21/3/21: FCD:12/03/2021->09/21; 11 ","26.131; 26.132; 26.801",86,44,null,null,"2019-12-06","2022-03-12"]
[1875,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-03-12"]
[1876,920008,"   Stage 2 of EVEX","EVEX",2,"Rel-17","S4","2021-06-11","2022-06-10",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"2021-06-11","2022-06-04"]
[1877,960021,"   Stage 3 (CT3) of EVEX","EVEX",2,"Rel-17","C3","2022-06-01","2022-06-10",1,"CP-222128",null,"Waqar Zia, Qualcomm Incorporated","wzia@qti.qualcomm.com",null,"29.522; 29.517; 29.591",96,49,null,null,"2022-05-30","NA"]
[1878,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","2021-06-11","2021-09-08",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"2021-06-11","2021-12-13"]
[1879,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"2021-06-11","2022-03-12"]
[1880,920011,"8K Television over 5G ","8K_TV_5G",1,"Rel-17","S4","2021-06-11","2022-03-11",1,"SP-210381",null,"Thomas Stockhammer ","tsto@qti.qualcomm.com ","; 13/9/21: 0%->40; 13/12/21: 40%->60; 12/3/22: 60%->100","26.955;26.925;26.511;26.116 ",92,47,null,null,"2021-06-11","2022-03-12"]
[1881,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","2019-03-07","2019-03-21",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"2017-12-15","2019-03-14"]
[1882,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","2019-09-02","2019-09-19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"2019-09-13","2019-09-13"]
[1883,880049,"Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON",1,"Rel-17",null,"2019-09-02","2023-03-03",1,"CP-210148",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 13/6/21: WID:SP-190941->CP-210148",22.260999999999999,85,43,null,null,"2019-09-13","2021-06-13"]
[1884,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","2019-09-02","2021-06-18",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100",22.260999999999999,85,43,null,null,"2019-09-13","2022-03-11"]
[1885,880022,"   Stage 3 (CT1) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 21/3/21: 5%->35; 11/6/21: 35%->50; 13/9/21: 50%->70; 13/9/21: FCD:Fri 18/06/->03/22; 13/12/21: 70%->92; 12/3/22: 92%->100",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1886,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"2020-06-26","2022-03-12"]
[1887,920061,"   Stage 3 (CT6) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C6","2020-06-25","2022-03-11",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/9/21: 0%->70; 13/9/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100; 4/6/22: 100 ",null,92,47,null,null,"2020-06-26","2022-06-04"]
[1888,970073,"   UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode ","eCPSOR_CON-UEConTest",2,"Rel-17","R5","2022-09-08","2023-03-03",1,"RP-222255","RP-230359","Masahiro Takano, NTT DOCOMO, INC","masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->80%; Stat Rep: ->RP-223159; Rapporteur: NTT DOCOMO->Masahiro Takano, NTT DOCOMO, INC; Rap eMail: ->masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com; 17/3/23: FCD:09/09/2023->03/03/2023; Compl:80%->100%; ...",null,97,49,null,null,"2022-09-23","2023-03-17"]
[1889,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2020-12-05"]
[1890,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","2019-09-19","2021-12-10",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2019-09-13","2021-12-13"]
[1891,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","2021-03-18","2022-03-11",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"2021-03-18","2022-03-12"]
[1892,910047,"   Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",2,"Rel-17","S3","2018-06-06","2022-03-11",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 24/3/22: 0%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"2021-03-19","2022-03-24"]
[1893,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"2019-03-07","2022-03-11",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"2019-09-13","NA"]
[1894,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","2019-03-07","2019-09-05",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[1895,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","2019-09-13","2019-12-12",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"2019-09-13","2019-12-06"]
[1896,920062,"   Stage 2 of MINT","MINT",2,"Rel-17","S2","2021-08-12","2021-12-10",1,"SP-210582",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","13/9/21: 0%->50; 10/12/21: 50%->90; 12/3/22: 90%->98; 4/6/22: 98%->100","23.501; 23.502 ",92,47,null,null,"2021-08-12","2022-06-04"]
[1897,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","2020-12-07","2021-03-12",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"2020-12-05","2021-09-13"]
[1898,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","NA"]
[1899,930049,"      CT1 aspects of MINT","MINT",3,"Rel-17","C1","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 13/12/21: 0%->50; 12/3/22: 50%->85; 4/6/22: 85%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1900,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-20"]
[1901,930048,"      CT6 aspects of MINT","MINT",3,"Rel-17","C6","2021-09-29","2022-03-11",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->100; 4/6/22: 100%->100","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"2021-09-29","2022-06-04"]
[1902,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","2022-03-10","2022-03-11",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100",33.500999999999998,95,48,null,null,"2022-03-10","2022-03-22"]
[1903,860008,"IMS emergency support for Stand-alone Non-Public Network (SNPN)","IESNPN",1,"Rel-17","S1","2019-12-06","2019-12-13",1,"SP-191038",null,"Wong, Curt; ","curt.wong@charter.com ","6/12/19: 0%->100","22.101; 22.261; 22.228 ",86,44,null,null,"2019-12-06","2019-12-06"]
[1904,870023,"Management of non-public networks (NPN)","OAM_NPN",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200189",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 13/9/20: 0%->5; 5/12/20: 5%->15; 21/3/21: 15%->35; 11/6/21: 35%->50; 11/6/21: FCD:Wed 16/06/->12/21; 13/9/21: 50%->70; 13/12/21: 70%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->100","28.541; 28.531; 28.533; 28.552; 28.554 ",87,44,null,null,"2019-12-06","2022-03-12"]
[1905,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","2019-12-06","2021-06-11",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"2019-12-06","2021-12-13"]
[1906,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"2020-03-25","2020-06-26"]
[1907,890013,"   eSCAS_5G for Network Slice-Specific Authentication and Authorization Function (NSSAAF) ","SCAS_5G_NSSAAF",2,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200720",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 9/4/21: 40%->60; 11/6/21: 60%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->100","33.926; 33.326",89,45,null,null,"2020-09-11","2021-09-13"]
[1908,870017,"   eSCAS_5G for Non-3GPP InterWorking Function","SCAS_5G_N3IWF",2,"Rel-17","S3","2020-03-25","2021-12-10",1,"SP-200146",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","26/6/20: 0%->10; 19/3/21: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->20; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 20%->100","33.926; 33.520",87,44,null,null,"2020-03-25","2021-12-13"]
[1909,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","2020-03-25","2022-06-10",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"2020-03-25","2022-06-04"]
[1910,870019,"   eSCAS_5G for Service Communication Proxy","SCAS_5G_SECOP",2,"Rel-17","S3","2020-03-25","2022-06-09",1,"SP-200148",null,"Wei Lu, Nokia","wei.lu@nokia-sbell.com","26/6/20: 0%->10; 12/9/20: 10%->20; 19/3/21: FCD:17/03/2021->06/21; 9/4/21: 20%->60; 11/6/21: 60%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 70%->95; 12/3/22: 95%->95; 12/3/22: FCD:10/12/2021->06/22; 31/3/23: 95%->100","33.522; 33.926",87,44,null,null,"2020-03-25","2023-03-31"]
[1911,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","2020-06-12","2021-12-10",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"2020-06-25","2021-09-13"]
[1912,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2020-06-28"]
[1913,870016,"   Stage 2 aspects of enh3MCPTT","enh3MCPTT",2,"Rel-17","S6","2020-03-25","2021-06-15",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 10/2/21: FCD:17/09/2020->06/21; 21/3/21: 45%->60; 11/6/21: 60%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-06-11"]
[1914,900039,"   Stage 3 aspects of enh3MCPTT","enh3MCPTT-CT",2,"Rel-17","C1","2020-09-14","2021-09-08",1,"CP-202188",null,null,null,"; 28/6/20: 0%->20; 13/9/20: 20%->35; 5/12/20: 35%->45; 5/12/20: 0%->45; 11/6/21: 45%->48; 13/12/21: 48%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"2019-12-06","2021-12-13"]
[1915,880020,"Protocol enhancements for Mission Critical Services ","MCProtoc17",1,"Rel-17","C1","2020-09-25","2022-03-11",1,"CP-202193",null,"AXELL, Jörgen ","jorgen.axell@ericsson.com ","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 13/9/20: 0%->10; 25/9/20: WID:CP-201164->CP-202193; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/12/21: 70%-> ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1916,1050128,"UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 ","MCProtoc17_enh3MCPTT_eMCData3_MCOver5GS-UEConTest",1,"Rel-17","R5","2024-09-09","2025-12-12",0.16,"RP-241755","RP-242642","Ericsson ",null,"6/12/24: Compl:0%->16%; Stat Rep: ->RP-242642; ",null,null,null,null,null,"2024-09-26","2024-12-06"]
[1917,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","2019-06-06","2021-12-10",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"2019-05-31","2022-03-12"]
[1918,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","2018-12-13","2021-03-12",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"2018-12-06","2021-06-11"]
[1919,890012,"Enhancements to User Plane Integrity Protection Support in 5GS ","eUPIP_SEC",1,"Rel-17","S3","2020-09-16","2021-03-12",1,"SP-200719",null,"Anand Palanigounder, Qualcomm Incorporated ","apg@qti.qualcomm.com ","; 5/12/20: 0%->80; 5/12/20: FCD:17/12/2020->03/20; 19/3/21: 80%->100",33.500999999999998,89,45,null,null,"2020-09-11","2021-03-19"]
[1920,950040,"Non-Seamless WLAN offload in 5GS ","NSWO_5G",1,"Rel-17","S3","2021-05-25","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ",null,33.500999999999998,95,48,null,null,"2021-12-10","NA"]
[1921,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","2021-05-25","2021-09-08",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"2021-05-25","2022-06-04"]
[1922,940011,"   Security aspects of NSWO","NSWO_5G",2,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211358",null,"Ranganathan Mavureddi Dhanasekaran, Nokia ","ranganathan.mavureddi_dhanasekaran@nokia-bell-labs.com ","; 12/3/22: FCD:12/12/2021->3/22; 12/3/22: 0%->100",33.500999999999998,94,48,null,null,"2021-12-10","2022-03-12"]
[1923,950041,"   CT1 aspects of NSWO","NSWO_5G",2,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 22/3/22: 0%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-03-22"]
[1924,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1925,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","2022-03-10","2022-03-11",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"2022-03-10","2022-06-04"]
[1926,990122,"Lawful Interception Rel-17 ","LI17",1,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[1927,860025,"   Lawful Interception Rel-17 general aspects","LI17",2,"Rel-17","S3","2019-12-10","2022-06-10",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"2019-12-06","2022-06-04"]
[{"$f":"A1928+1","v":1928},990120,"   (IETF) PASSporT Extension for Rich Call Data (draft-ietf-stir-passport-rcd)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1929,990121,"   (IETF) Messaging Use Cases and Extensions for STIR (draft-ietf-stir-messaging)","LI17",2,"Rel-17","S3-IETF","2019-12-10","2022-06-10",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"2023-03-17","NA"]
[1930,850047,"(Small) Technical Enhancements and Improvements for Rel-17","TEI17",1,"Rel-17",null,"2020-03-11","2022-03-11",1,null,null,null,null,null,null,85,43,null,null,"2015-06-15","2015-06-15"]
[1931,940047,"   IMS Optimization for HSS Group ID in an SBA environment (St. 2)","TEI17_IMSGID",2,"Rel-17","S2","2020-03-11","2022-03-11",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1932,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"2020-06-10","2021-03-19"]
[1933,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","2020-03-11","2022-03-11",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100",24.228999999999999,94,48,null,null,"2021-12-10","2022-03-12"]
[1934,910044,"   Same PCF Selection For AMF and SMF ","TEI17_SPSFAS",2,"Rel-17",null,"2020-03-25","2021-09-08",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ",null,null,88,45,null,null,"2020-06-25","NA"]
[1935,880016,"      Stage 2 for TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200447",null,"Heng, Nie, China Telecom ","nieheng@chinatelecom.cn ","23.501, 23.502 ; 19/3/21: 0%->100",null,88,45,null,null,"2020-06-25","2021-03-19"]
[1936,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"2021-03-18","NA"]
[1937,910045,"         CT3 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C3","2021-03-18","2021-09-08",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->98; 11/6/21: FCD:Fri 11/06/->09/21; 11/6/21: WID:CP-210071->CP-211184; 13/9/21: 98%->100",29.513000000000002,91,46,null,null,"2021-03-18","2021-09-13"]
[1938,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","2021-03-18","2021-06-11",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"2021-03-18","2021-09-13"]
[1939,930036,"   System enhancement for Redundant PDU Session ","TEI17_SE_RPS",2,"Rel-17",null,"2020-03-25","2022-03-11",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1940,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"2020-06-25","2021-06-11"]
[1941,930001,"      CT aspects of TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","ct","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ",null,"24.501; 24.526; 27.007; 29.513; 29.525; 29.561; 29.502 ",93,47,null,null,"2021-09-10","NA"]
[1942,930037,"         CT1 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C1","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","24.501; 24.526; 27.007",93,47,null,null,"2021-09-10","2021-12-13"]
[1943,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"2021-09-10","2022-03-12"]
[1944,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","2021-09-10","2022-03-11",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100",29.501999999999999,93,47,null,null,"2021-09-10","2021-12-13"]
[1945,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"2020-03-25","2021-09-10",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1946,870004,"      Stage 2 for TEI17_SAPES","TEI17_SAPES",3,"Rel-17","S2","2020-03-25","2020-06-12",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ","19/3/21: 0%->100","23.228; 23.167",87,44,null,null,"2020-06-10","2021-03-19"]
[1947,910020,"      CT aspects on TEI17_SAPES","TEI17_SAPES",3,"Rel-17","ct","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ",null,"24.229; 29.165 ",91,46,null,null,"2021-03-19","NA"]
[1948,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1949,910080,"         CT3 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"2021-03-19","2021-06-11"]
[1950,910081,"   Dynamically Changing AM Policies in the 5GC ","TEI17_DCAMP",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,null,null,87,44,null,null,"2020-06-10","NA"]
[1951,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"2020-06-10","2021-03-19"]
[1952,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1953,910082,"         CT3 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: 0%->30; 13/9/21: 30%->50; 13/12/21: 50%->75; 12/3/22: 75%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1954,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1955,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"2020-06-10","2021-03-19"]
[1956,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"2020-03-11","2022-03-11",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"2020-06-10","NA"]
[1957,870007,"      Stage 2 for TEI17_GEM ","TEI17_GEM",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com","11/6/21: 0%->100",23.681999999999999,87,44,null,null,"2020-06-10","2021-06-11"]
[1958,910010,"      CT aspects on TEI17_GEM ","TEI17_GEM",3,"Rel-17","ct","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: WID:CP-210185->CP-211195; 10/9/21: WID:CP-211195->CP-212165","29.122 29.336 ",91,46,null,null,"2021-03-19","2021-09-10"]
[1959,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1960,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","2021-03-19","2022-03-11",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"2021-03-19","2022-03-12"]
[1961,920041,"   Support of different slices over different Non 3GPP access ","TEI17_N3SLICE",2,"Rel-17",null,"2020-03-11","2021-06-18",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1962,870008,"      Stage 2 for TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200456",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","19/3/21: 0%->100","23.501; 23.502 ",87,44,null,null,"2020-06-10","2021-03-19"]
[1963,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-10-01"]
[1964,920001,"      CT4 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C4","2021-06-11","2021-06-18",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"2021-06-11","2021-06-11"]
[1965,910087,"   N7/N40 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",2,"Rel-17",null,"2020-03-11","2021-09-10",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ",null,null,87,44,null,null,"2020-06-10","NA"]
[1966,870009,"      Stage 2 for TEI17_NIESGU","TEI17_NIESGU",3,"Rel-17","S2","2020-03-11","2020-06-25",1,"SP-200457",null,"Aihua, Li, China Mobile ","liaihua@ chinamobile.com ","11/6/21: 0%->100","23.060; 23.401; 23.503; 23.203 ",87,44,null,null,"2020-06-10","2021-06-11"]
[1967,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","2020-09-16","2021-09-08",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[1968,910011,"      CT3 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C3","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->90; 11/6/21: WID:CP-210186->CP-211194; 13/9/21: 90%->100","29.512; 29.513 ",91,46,null,null,"2021-03-19","2021-09-13"]
[1969,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","2021-03-19","2021-09-10",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"2021-03-19","2021-09-13"]
[1970,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","2021-12-10","2022-03-22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"2022-04-21","NA"]
[1971,880019,"Stage-3 5GS NAS protocol development 17 ","5GProtoc17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","NA"]
[1972,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"2020-06-26","2022-03-12"]
[1973,880045,"   Stage-3 5GS NAS protocol development 17 non-IETF aspects","5GProtoc17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","1/10/21: 0%->70; 23/9/22: 70%->100","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",88,45,null,null,"2020-06-26","2022-09-23"]
[1974,880021,"Stage-3 SAE Protocol Development ","SAES17",1,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1975,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1976,880047,"   Stage-3 SAE Protocol Development CSFB aspects","SAES17-CSFB",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1977,880048,"   Stage-3 SAE Protocol Development non 3GPP aspects","SAES17-non3GPP",2,"Rel-17","C1","2020-06-25","2021-09-20",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","22/3/22: 0%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",88,45,null,null,"2020-06-26","2022-03-22"]
[1978,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","2020-06-25","2024-06-06",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"2020-06-26","2021-03-21"]
[1979,880023,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C1","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 20%->40; 13/9/21: 40%->60; 13/12/21: 60%->80; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 80%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1980,911035,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","11/6/21: 0%->60; 13/9/21: 60%->70; 13/12/21: 70%->85; 12/3/22: 85%->100; 12/3/22: FCD:10/09/2021->3/22","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; 13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20",88,45,null,null,"2020-06-26","2022-03-12"]
[1981,1000055,"   STOPPED - UE Conformance - IMS Data Channel ","IMSProtoc17_dataCH-UEContest",2,"Rel-17","R5","2023-06-07","2024-06-06",1,"RP-240283","RP-241373","Zhaobing Yang, Huawei Technologies. Co., Ltd","yangzhaobing@huawei.com","6/9/23: FCD:12/12/2023->22/09/2023; Compl:0%->5%; Stat Rep: ->RP-232356; Rapporteur: HiSilicon->Zhaobing Yang, Huawei Technologies. Co., Ltd; Rap eMail: ->yangzhaobing@hisilicon.com; ; 6/10/23: WID:RP-231246->RP-232357; 8/12/23: FCD:22/09/2023->09/09/2...",null,100,51,null,null,"2023-06-29","2024-06-13"]
[1982,880032,"Packet Flow Description (PFD) management enhancement ","pfdManEnh",1,"Rel-17","C3","2020-06-25","2021-06-11",1,"CP-210183",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","13/9/20: 0%->25; 5/12/20: 25%->60; 21/3/21: 60%->98; 21/3/21: FCD:11/12/2020->06/21; 21/3/21: WID:CP-201208->CP-210183; 11/6/21: 98%->100","29.251; 29.551 ",88,45,null,null,"2020-06-26","2021-06-11"]
[1983,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"2020-06-26","NA"]
[1984,880053,"   CT3 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C3","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->15; 5/12/20: 15%->30; 21/3/21: 30%->50; 11/6/21: 50%->65; 11/6/21: WID:CP-201075->CP-211088; 13/9/21: 65%->75; 13/12/21: 75%->85; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 85%->100","29.507; 29.508; 29.512; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.551; 29.554; 29.554; 29.591; 29.594; 29.122; 29.222; 29.486; 29.517; 29.549; 29.675; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1985,880054,"   CT4 aspects of SBIProtoc17","SBIProtoc17",2,"Rel-17","C4","2020-06-25","2022-03-11",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","13/9/20: 0%->10; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 30%->50; 13/9/21: 50%->60; 13/12/21: 60%->80; 13/12/21: FCD:Mon 20/09/->03/22; 12/3/22: 80%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.531; 29.540; 29.541; 29.542; 29.544; 29.550; 29.562; 29.563; 29.571; 29.572; 29.573; 29.598; ",88,45,null,null,"2020-06-26","2022-03-12"]
[1986,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","2020-12-07","2022-03-11",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"2020-12-05","2022-03-12"]
[1987,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"2021-12-10","2022-03-12"]
[1988,970052,"   CT3 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C3","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1989,970053,"   CT4 aspects of ReP_UDR","ReP_UDR",2,"Rel-17","C4","2019-03-07","2022-03-18",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ",null,"23.527; 29.503; 29.505; 29.510; 29.519 ",97,49,null,null,"2022-09-07","NA"]
[1990,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","2021-12-10","2022-06-10",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"2021-12-10","2022-06-04"]
[1991,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","2021-12-10","2022-03-11",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"2021-12-10","2022-03-12"]
[{"$f":"A1992+1","v":1992},820009,"Study on authentication enhancements in 5GS","FS_AUTH_ENH",1,"Rel-17","S3","2018-12-13","2021-12-10",1,"SP-190713",null,"Tsiatsis, Vlasios, ","vlasios.tsiatsis@ericsson.com ","07/19: Rel corrected, was wrongly allocated to Rel-17¦20/3/19: 0%->5; 13/9/19: 5%->15; 13/9/19: FCD:19/09/2019->12/20; 19/9/19: WID:S3-183745->SP-190713; 6/12/19: 15%->40; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/202 ","new",82,42,null,null,"2018-12-06","2022-03-12"]
[1993,940012,"Authentication enhancements in 5GS ","AUTH_ENH",1,"Rel-17","S3","2021-12-10","2022-03-11",1,"SP-211360",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 24/3/22: 0%->100",33.101999999999997,94,48,null,null,"2021-12-10","2022-03-24"]
[1994,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","2022-03-10","2022-03-11",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"2022-03-10","2022-03-12"]
[1995,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","2022-03-10","2022-03-11",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"2022-03-10","2022-06-20"]
[1996,990004,"Update of conformance test specifications to Rel-17","UEConTest_R17",1,"Rel-17","C6","2021-06-14","2024-06-06",1,"CP-230022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com","Tests eV2XARC_Ph2;eCPSOR_CON;5G_ProSe;5GSAT_ARCH-CT;ING_5GS;MINT;NSWO_5G;ARCH_NR_REDCAP;IoT_SAT_ARCH_EPS","31.121; 31.124",92,47,null,null,"2021-08-12","NA"]
[1997,0,"Rel-17 Management-only Features","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[1998,900021,"Management Aspects of 5G Network Sharing ","MANS",1,"Rel-17","S5","2020-12-04","2022-03-11",1,"SP-201080",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","32.130; 28.541; 28.552; 28.554 ; 21/3/21: 0%->20; 11/6/21: 20%->25; 13/9/21: 25%->30; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 30%->60; 12/3/22: 60%->100",null,90,46,null,null,"2020-12-04","2022-03-12"]
[1999,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","2021-06-11","2021-12-10",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"2021-06-11","2021-12-13"]
[2000,910030,"File Management ","FIMA",1,"Rel-17","S5","2021-03-18","2022-03-11",1,"SP-210135",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 11/6/21: 0%->25; 13/9/21: 25%->60; 13/12/21: 60%->75; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 75%->100","28.537; 28.622; 28.623; 28.532 ",91,46,null,null,"2021-03-18","2022-03-12"]
[2004,880028,"Management data collection control and discovery ","MADCOL",1,"Rel-17","S5","2020-06-25","2022-03-11",1,"SP-200465",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","28.533; 28.532; 28.622; 28.623 ; 5/12/20: 0%->5; 21/3/21: 5%->25; 11/6/21: 25%->30; 13/9/21: 30%->35; 13/9/21: FCD:Wed 22/09/->03/22; 13/12/21: 35%->40; 12/3/22: 40%->45; 4/6/22: 45%->100",null,88,45,null,null,"2020-06-26","2022-06-04"]
[2007,810027,"Intent driven management service for mobile network","IDMS_MN",1,"Rel-17","S5","2018-09-06","2022-03-11",1,"SP-180899",null,"Zou Lan, Huawei ","zoulan@huawei.com","7/12/18: 0%->20¦14/3/19: 20%->30; 31/5/19: 30%->35; 13/9/19: 35%->45; 13/9/19: FCD:14/06/2019->03/20; 26/3/20: 45%->55; 26/3/20: FCD:12/03/2020->03/21; Rel-16->Rel-17; 13/9/20: FCD:12/03/2021->09/21; 5/12/20: 55%->65; 21/3/21: 65%->70; 11/6/21: FCD:Wed ","New",81,41,null,null,"2018-09-06","2022-06-04"]
[2009,860024,"Network policy managementfor 5G mobile networks ","NPM",1,"Rel-17","S5","2019-12-06","2022-03-11",1,"SP-191211",null,"China Mobile Shasha Guo ","guoshasha@chinamobile.com ","; 13/9/20: 0%->55; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 55%->60; 21/3/21: 60%->65; 21/3/21: FCD:11/06/2021->03/22. 9/4/21: corrected from Rel-16 to Rel-17; 11/6/21: 65%->75; 13/9/21: 75%->78; 13/12/21: 78%->100","28.532; 28.541 ",86,44,null,null,"2019-12-06","2021-12-13"]
[2015,870025,"Management of MDT enhancement in 5G ","e_5GMDT",1,"Rel-17","S5","2020-03-25","2022-03-11",1,"SP-200191",null,"Ayani, Zhulia, Ericsson ","zhulia.Ayani@ericsson.com ","; 13/9/20: 0%->20; 5/12/20: 20%->50; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 50%->70; 21/3/21: FCD:11/06/2021->12/21; 11/6/21: 70%->75; 13/9/21: 75%->85; 13/12/21: 85%->95; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 95%->100","32.421; 32.422; 32.423; 28.622; 28.623; 28.523 ",87,44,null,null,"2019-12-06","2022-03-12"]
[2018,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","2022-03-10","2022-06-10",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"2022-03-10","2022-06-04"]
[2019,0,"Rel-17 Other NR-only improvements","-",1,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[2022,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","2021-01-01","2022-03-22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"2021-04-07","2022-06-20"]
[2027,1000056,"   UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL ","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-UEConTest",2,"Rel-17","R5","2023-06-08","2025-06-06",0.09,"RP-231247","RP-243085","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->9%; Stat Rep: ->RP-232358; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232358->RP-233766; ; 14/3/24: ...",null,100,51,null,null,"2023-06-29","2024-12-06"]
[2030,911210,"   Perf. part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Perf",2,"Rel-17","R4","2021-03-12","2022-09-22",1,"RP-222269","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TS 38.1yy ; 22/3/22: Compl:0%->20%; 22/3/22: CD:08/09/2022->12/09/2022 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com s...; 23",null,91,46,null,null,"2021-04-07","2022-09-23"]
[2035,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","2021-09-17","2022-12-01",1,"RP-211979","RP-223061","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...; 9/12/22: FCD:23/03/2023->01/12/2022; Compl:84%->100%; Stat R...",null,93,47,null,null,"2021-09-29","2023-01-09"]
[2038,911213,"   Perf. part: NR_UE_PC2_n34","NR_UE_PC2_n34-Perf",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-07-02"]
[2041,911114,"   Core part: NR_UE_PC2_n39","NR_UE_PC2_n39-Core",2,"Rel-17","R4","2021-03-12","2021-09-08",1,"RP-210845",null,"CMCC ",null,"; 29/9/21: 0%->100",null,91,46,null,null,"2021-04-07","2021-09-29"]
[2044,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"2021-03-12","2021-09-08",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"2021-04-07","NA"]
[2048,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","2021-03-12","2022-03-11",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"2021-04-07","2022-04-05"]
[2049,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","2022-06-15","2023-06-06",1,"RP-221449","RP-230395","Huiying ZHANG, CATT","zhanghuiying@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%->33%; Stat Rep: ->RP-223139; Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn; 17/3/23: Compl:33%->67%; Stat Rep: RP-223139->RP-230395; ;...",null,96,49,null,null,"2022-07-12","2023-06-07"]
[2053,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"2020-07-28","2022-06-20"]
[2057,870164,"   Core part: NR_FR2_FWA_Bn257_Bn258","NR_FR2_FWA_Bn257_Bn258-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 7/4/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-04-07"]
[2060,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2064,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-09-29"]
[2067,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","2020-03-19","2022-03-21",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"2020-07-28","2021-09-13"]
[2070,860036,"   Study on on NR coverage enhancements","FS_NR_cov_enh",2,"Rel-17","R1","2019-03-07","2020-06-03",1,"RP-200861",null,"China Telecom",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193240->RP-200861; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[2072,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","2020-12-14","2022-12-21",1,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...; 9/",null,90,46,null,null,"2021-01-06","2023-01-09"]
[2075,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","2019-12-16","2020-06-15",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-04-07"]
[2079,930018,"   Architecture Enhancement for NR Reduced Capability Devices ","ARCH_NR_REDCAP",2,"Rel-17","S2","2021-09-10","2021-12-10",1,"SP-211100",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 10/12/21: 0%->100","23.501; 23.502 ",93,47,null,null,"2021-09-10","2021-12-10"]
[2083,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","2021-12-10","2022-03-11",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"2022-01-07","2022-06-04"]
[2086,900164,"   Core part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Core",2,"Rel-17","R4","2020-12-14","2022-06-22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: Compl:0%->70%; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"2021-01-06","2022-06-20"]
[2090,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"2020-12-14","2024-03-01",1,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;",37.866999999999997,90,46,null,null,"2021-01-06","2021-07-02"]
[2092,900268,"   Perf. part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Perf",2,"Rel-17","R4","2020-12-14","2022-03-11",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI ; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478; 13/9/21: Stat Rep: ->RP-211833 ; ",null,90,46,null,null,"2021-01-06","2022-03-22"]
[2095,900169,"   Core part: HPUE_PC1_5_n77_n78","HPUE_PC1_5_n77_n78-Core",2,"Rel-17","R4","2020-12-14","2021-09-21",1,"RP-202912","RP-212049","Qualcomm ",null,"no Perf. part ; 13/9/21: Compl:0%->100% ; 29/9/21: 100%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[2098,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","2020-12-14","2022-03-22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"2021-01-06","2022-06-20"]
[2101,930156,"   Core part: Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-Core",2,"Rel-17","R4","2021-09-17","2022-06-22",1,"RP-221302","RP-221588","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","no Perf. Part ; 22/3/22: Compl:0%->75%; … 20/6/22: WID: RP-212622->RP-221302; Stat Rep: RP-220514->RP-221588; Rapporteur: Qualcomm->Gene Fong, Qualcomm Incorporated; Rap eMail: ->gfong@qti.qualcomm.com; ",null,93,47,null,null,"2021-09-29","2022-06-20"]
[2106,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","2022-06-15","2022-12-01",1,"RP-221417","RP-222802","Heng Pan, Puloli","heng.pan@puloli.com","9/9/22: Comp...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:72%->100%; Stat Rep: ->RP-222802; Rapporteur: Puloli->Heng Pan, Puloli; Rap eMail: ->heng.pan@puloli.com; 9/1/23: 100%->100",null,96,49,null,null,"2022-07-12","2023-01-09"]
[2109,930258,"   Perf. part: High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD-Perf",2,"Rel-17","R4","2021-09-17","2022-03-11",1,"RP-212892","RP-220381","China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD ; ",null,93,47,null,null,"2021-09-29","2022-03-22"]
[2112,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"2016-06-09","2016-06-09",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"2014-08-29","2014-08-29"]
[2114,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A2120+1","v":2120},881006,"NR iterbCA/Dual Connectivity for 2 bands DL with x bands UL (x=1,2)","NR_CADC_R17_2BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221250",null,"ZTE",null,"25/9/20: WID:RP-200672->RP-201539; 6/1/21: WID:RP-201539->RP-202199; 7/4/21: WID:RP-202199->RP-210495; 2/7/21: WID:RP-210495->RP-211058; 29/9/21: WID:RP-211058->RP-212511; 6/1/22: WID:RP-212511->RP-212887; 5/4/22: WID:RP-212887->RP-220144; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2121,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2127,881108,"   Core part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2128,881208,"   Perf. part: NR_CADC_R17_3BDL_2BUL","NR_CADC_R17_3BDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221253","RP-221254","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2132,881010,"NR iterbCA/Dual connectivity for DL 4 bands and 2UL bands","NR_CADC_R17_4BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221396",null,"Samsung",null,"25/9/20: WID:RP-200869->RP-201640; 6/1/21: WID:RP-201640->RP-202544; 7/4/21: WID:RP-202544->RP-210802; 2/7/21: WID:RP-210802->RP-211194; 29/9/21: WID:RP-211194->RP-212110; 6/1/22: WID:RP-212110->RP-213111; 5/4/22: WID:RP-213111->RP-220676; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2135,881011,"NR iterbCA for 5 bands DL with x bands UL (x=1, 2)","NR_CADC_R17_5BDL_xBUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221510",null,"Huawei",null,"25/9/20: WID:RP-201027->RP-201724; 6/1/21: WID:RP-201724->RP-202609; 7/4/21: WID:RP-202609->RP-210561; 2/7/21: WID:RP-210561->RP-211373; 29/9/21: WID:RP-211373->RP-212176; 6/1/22: WID:RP-212176->RP-213129; 5/4/22: WID:RP-213129->RP-220692; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2140,890254,"   Perf. part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","2020-09-17","2022-06-22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI ; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211131->RP-202102 RP-202373 RP-210476 RP-211131; 13/9/21: Stat Rep: ->RP-211832; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: WID: RP-213649->RP‑213649; 22/3/22: Stat Rep: RP-211832- ; ",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2143,920072,"LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39",1,"Rel-17","R4","2019-03-07","2019-03-07",1,null,"RP-211995","CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 13/9/21: Compl:0%->100% ; ",null,92,47,null,null,"2021-07-02","2021-09-13"]
[2146,920073,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM",1,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795",null,"Nokia ",null,"this is not a basket WI ; 29/9/21: WID:RP-211571->RP-212533; 6/1/22: WID:RP-212533->RP-213106; 5/4/22: WID:RP-213106->RP-220767; 12/7/22: WID:RP-220767->RP-221795",null,92,47,null,null,"2021-07-02","2022-07-12"]
[2147,920173,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Core",2,"Rel-17","R4","2021-06-15","2022-06-22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; …; 7/1/22: 37.828 and 37.828 added;; 22/3/22: Compl:0%->50% ; 20/6/22: Compl:50%->100%; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail...","37.828; 37.828",92,47,null,null,"2021-07-02","2022-06-20"]
[2153,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17","R4","2021-03-25","2021-03-25",0.99,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"2021-04-09","2022-06-20"]
[2154,930259,"   Stopped - Perf. Part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Perf",2,"Rel-17","R4","2021-03-25","2021-03-25",0.99,"RP-220709",null,"Huawei, HiSilicon ",null,"4/6/22: Stopped at 70%. This Perf. part is not needed",null,93,47,96,null,"2022-03-13","2022-06-04"]
[2158,930051,"   UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR-UEConTest",2,"Rel-17","R5","2021-09-17","2024-09-24",1,"RP-230082","RP-242229","Kuba KOLODZIEJ, Ericsson","Kuba[dot]kolodziej[at]ericsson[dot]com","tested: REL-17 WI ENDC_PC2_R17_xLTE_yNR ; 22/3/22: Compl:0%->5%; 22/3/22: CD:15/12/2022->12/12/2022; 22/3/22 6/6/22: CD:12/12/2022->22/12/2022 ; ; 20/6/22: Rapporteur: Ericsson->Leif MATTISSON, Ericsson; Rap eMail: ->Leif[dot]mattisson[at]ericsson[d...",null,93,47,null,null,"2021-09-29","2024-09-04"]
[2162,890052,"Rel-17 Dual Connectivity (DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) ","DC_R17_5BLTE_1BNR_6DL2UL",1,"Rel-17",null,"2020-09-17","2022-03-11",1,"RP-220672",null,"Samsung ",null,"basket WI; TR 37.717-51-11 ; 6/1/21: WID:RP-201642->RP-202540; 7/4/21: WID:RP-202540->RP-210801; 2/7/21: WID:RP-210801->RP-211195; 6/1/22: WID:RP-211195->RP-213112; 5/4/22: WID:RP-213112->RP-220672",null,89,45,null,null,"2020-09-25","2022-04-05"]
[2166,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[2169,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"2020-07-28","2022-06-20"]
[2172,880194,"   Core part: ENDC_UE_PC2_R17_NR_TDD","ENDC_UE_PC2_R17_NR_TDD-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221227","RP-221228","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","; 13/9/21: Compl:0%->40%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211852; 22/3/2 20/6/22: Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2175,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"2020-07-28","NA"]
[2177,880096,"LTE/NR spectrum sharing in Band 40/n40","DSS_LTE_B40_NR_Bn40",1,"Rel-17",null,"2020-06-17","2020-09-15",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: WID:RP-201362->RP-202084",null,88,45,null,null,"2020-07-28","2020-09-25"]
[2181,880198,"   Core part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: Compl:0%->75%; ; 22/3/22: Compl:75%->90%; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[{"$f":"A2184+1","v":2184},880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2188,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2192,881002,"Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R17_xBLTE_2BNR_yDL2UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221182",null,"LG Electronics",null,"25/9/20: WID:RP-201372->RP-201477; 6/1/21: WID:RP-201477->RP-202292; 7/4/21: WID:RP-202292->RP-210202; 2/7/21: WID:RP-210202->RP-211043; 29/9/21: WID:RP-211043->RP-211750; 6/1/22: WID:RP-211750->RP-212876; 5/4/22: WID:RP-212876->RP-220302; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2195,881003,"Dual Connectivity (DC) of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL)","DC_R17_xBLTE_yBNR_3DL3UL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221232",null,"ZTE",null,"25/9/20: WID:RP-201373->RP-201710; 6/1/21: WID:RP-201710->RP-202192; 7/4/21: WID:RP-202192->RP-210344; 2/7/21: WID:RP-210344->RP-211054; 29/9/21: WID:RP-211054->RP-211803; 6/1/22: WID:RP-211803->RP-212883; 5/4/22: WID:RP-212883->RP-220202; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2197,881203,"   Perf. part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2200,881204,"   Perf. part: DC_R17_xBLTE_3BNR_yDL2UL","DC_R17_xBLTE_3BNR_yDL2UL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221235","RP-221236","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","6/6/22: Compl:0%->100%; ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2203,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2206,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"2021-03-12","2022-09-22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"2021-04-07","2022-07-12"]
[2211,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","2021-03-12","2022-03-11",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"2021-04-07","2022-03-22"]
[2214,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","2019-12-16","2023-03-03",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"2020-01-14","2023-03-17"]
[2218,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[2219,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","2020-03-25","2020-09-15",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"2020-01-14","2021-01-06"]
[2225,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","2020-03-19","2021-03-19",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-04-07"]
[2226,890050,"Introduction of 6GHz NR licensed bands ","NR_6GHz",1,"Rel-17","R4","2020-09-17","2022-09-22",1,"RP-221504",null,"Huawei ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202114->RP-202844; 6/1/22: WID:RP-202844->RP-213696; 5/4/22: WID:RP-213696->RP-220686; 12/7/22: WID:RP-220686->RP-221504",null,89,45,null,null,"2020-09-25","2022-07-12"]
[2232,890051,"Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU",1,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604",null,"Nokia ",null,"missing target dates to be updated ; 6/1/21: WID:RP-202116->RP-202592; 7/4/21: WID:RP-202592->RP-210762; 29/9/21: WID:RP-210762->RP-212625; 6/1/22: WID:RP-212625->RP-213604",null,89,45,null,null,"2020-09-25","2022-01-06"]
[2234,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","2020-09-17","2022-03-11",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"2020-09-25","2022-03-22"]
[2237,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[2240,900266,"   Perf. part: Introduction of NR band n85 ","NR_n85-Perf",2,"Rel-17","R4","2020-12-14","2021-06-11",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-07-02"]
[2245,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[{"$f":"A2248+1","v":2248},880186,"   Core part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Core",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[2249,880286,"   Perf. part: NR_SUL_band_2300_2400MHz","NR_SUL_band_2300_2400MHz-Perf",2,"Rel-17","R4","2020-06-22","2020-12-15",1,"RP-201364",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"2020-07-28","2021-01-06"]
[2254,880079,"Additional LTE bands for UE categories M1/M2/NB1/NB2","LTE_bands_R17_M1_M2_NB1_NB2",1,"Rel-17",null,"2020-06-08","2022-06-22",1,"RP-220816",null,"Ericsson",null,"25/9/20: WID:RP-200804->RP-201646; 29/9/21: WID:RP-201646->RP-211857; 6/1/22: WID:RP-211857->RP-212906; 5/4/22: WID:RP-212906->RP-220816",null,88,45,null,null,"2020-07-28","2022-04-05"]
[2256,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","2020-06-08","2022-06-22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2260,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","2021-06-15","2021-12-15",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"2021-07-02","2022-01-06"]
[2263,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2267,880288,"   Stopped - Perf. part: LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-220713","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","6/1/21: stopped at 0%; 22/3/22: Compl:100%->10%; 22/3/22: CD:15/09/2021->10/06/2022 ; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,96,null,"2020-07-28","2022-06-20"]
[2271,880090,"LTE iterbCA for 2 bands DL with 2 bands UL","LTE_CA_R17_2BDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221528",null,"Huawei",null,"25/9/20: WID:RP-201246->RP-201732; 7/4/21: WID:RP-201732->RP-210542; 2/7/21: WID:RP-210542->RP-211390; 29/9/21: WID:RP-211390->RP-212194; 5/4/22: WID:RP-212194->RP-220718; 12/7/22: WID:RP-220718->RP-221528",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2274,880091,"LTE iterbCA for x bands DL (x= 3, 4, 5) with 2 bands UL","LTE_CA_R17_xBDL_2BUL",1,"Rel-17",null,"2020-06-22","2022-06-22",1,"RP-221188",null,"LG",null,"25/9/20: WID:RP-201247->RP-201475; 6/1/21: WID:RP-201475->RP-202289; 7/4/21: WID:RP-202289->RP-210200; 2/7/21: WID:RP-210200->RP-211041; 29/9/21: WID:RP-211041->RP-211748; 6/1/22: WID:RP-211748->RP-212874; 5/4/22: WID:RP-212874->RP-220295; 12/7/22: WID:RP",null,88,45,null,null,"2020-07-28","2022-07-12"]
[2276,880291,"   Perf. part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Perf",2,"Rel-17","R4","2020-06-22","2022-06-22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[2279,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","2020-09-16","2021-12-10",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"2020-09-10","2022-03-12"]
[2282,820010,"Study on Long Term Key Update Process (LTKUP) Detailed solutions","FS_LTKUP_Detail",1,"Rel-17","S3","2018-12-13","2020-03-12",1,"SP-181038",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->60¦20/3/19: 0%->60; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 60%->100",null,82,42,null,null,"2018-12-06","2020-06-26"]
[2286,870015,"Study on Streaming Architecture extensions For Edge processing ","FS_EMSA",1,"Rel-17","S4","2020-03-25","2021-06-11",1,"SP-200056",null,"Bouazizi, Imed, Qualcomm ","bouazizi@qti.qualcomm.com ","10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100",null,87,44,null,null,"2019-12-06","2021-06-11"]
[2289,911032,"Study on enhanced IMS to 5GC Integration Phase 2 ","FS_eIMS5G2",1,"Rel-17","ct","2020-09-25","2022-03-11",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15","23.700-10",88,45,null,null,"2020-06-26","2021-03-21"]
[2293,890002,"Study on Port Number Allocation Alternatives for New 3GPP Interfaces ","FS_PortAl",1,"Rel-17","C4","2020-09-16","2022-03-11",1,"CP-220391",null,"Giorgi Gulbani, Huawei","giorgi.gulbani@huawei.com ","13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->85; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 85%->100; 22/3/22: WID:CP-202243->CP-220391",null,89,45,null,null,"2020-09-11","2022-03-22"]
[2297,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","2020-06-22","2022-03-11",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"2020-07-28","2022-04-05"]
[2300,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","2020-12-14","2021-09-08",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"2021-01-06","2021-09-29"]
[2302,840021,"Stopped - Study on the Usage of User Identifiers in the 5G System ","FS_UUI5",1,"Rel-17","S2","2019-06-06","2020-06-12",1,"SP-190450",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; 21/1/22: stopped at 0%; 21/1/22: 0%->100","New ; 23.700-094; ",84,43,95,null,"2019-05-31","2022-01-21"]
[2305,880004,"Stopped - Study on security aspects of the Disaggregated gNB Architecture ","FS_disagg_gNB_Sec",1,"Rel-17","S3","2020-06-25","2021-03-12",1,"SP-200349",null,"Sen XU, China Telecom ","xusen@chinatelecom.cn ","12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100. 13/7/22: marked as stopped (was already at 100%!) as per e-mail from Mirko on 02/06/22 14.03",33.840000000000003,88,45,95,null,"2020-06-25","2021-03-19"]
[2308,0,"Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC)","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2311,810036,"   Study on the security of URLLC for 5GS ","FS_5G_URLLC_SEC",2,"Rel-16","S3","2018-09-06","2019-06-12",1,"SP-180910",null,"Rong Wu, Huawei Technologies","Raina.wu@huawei.com","7/12/18: 0%->20¦20/3/19: FCD:019->06/19¦20/3/19: 20%->65; 31/5/19: 65%->80; 13/9/19: 80%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[2316,840060,"      CT3 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","29.512; 29.513; 29.514; 29.522; 29.508",84,43,null,null,"2019-05-31","2020-03-26"]
[2320,780030,"   Stopped - Study on EPC support for Mobility with Low Latency Communication","FS_LLC_Mob",2,"Rel-16","S2","2017-12-15","2018-09-14",1,"SP-171069",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395","new 23.739",78,40,84,null,"2017-12-15","2018-06-07"]
[2323,800095,"   Study on physical layer enhancements for NR UR Low Latency Cases","FS_NR_L1enh_URLLC",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181477",null,"Huawei",null,"TR 38.8xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2324,830174,"   Core part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-190726",null,"Huawei",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2328,810060,"   Study on channel modeling for indoor industrial scenarios","FS_IIIOT_CM",2,"Rel-16","R1","2018-09-14","2019-09-13",1,"RP-182138",null,"Ericsson",null,"8/10/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-10-08"]
[2331,880067,"   UE Conformance Test Aspects – Support of NR Industrial Internet of Things (IoT)","NR_IioT-UEConTest",2,"Rel-16","R5","2020-06-22","2022-03-11",1,"RP-200757","RP-220623","CMCC",null,"8/10/20: 0%->5; 8/4/21: 5%->68; 2/7/21: 68%->77; 13/9/21: Compl:77%->95%; 13/9/21: C ; 29/9/21: WID:RP-200757->RP-211786; 6/1/22: WID:RP-211786->RP-212943; ",null,88,45,null,null,"2020-07-28","2022-03-22"]
[2337,820017,"   Stage 2 of Vertical_LAN","Vertical_LAN",2,"Rel-16","S2","2018-12-13","2019-06-24",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","14/3/19: 0%->43; 31/5/19: 43%->90; 13/9/19: 90%->97; 6/12/19: 97%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-12-06"]
[2339,840027,"   Security for Vertical_LAN ","Vertical_LAN_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190352",null,"Jerichow, Anja, Nokia ","anja.jerichow@nokia.com ","13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100",33.500999999999998,84,43,null,null,"2019-05-31","2020-06-26"]
[2342,830036,"      CT3 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-201174",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174","29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061",83,42,null,null,"2018-12-06","2020-06-26"]
[2346,850019,"   Security aspects of SEAL","SEAL",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190901",null,"Rajavelsamy Rajadurai (Samsung) ","rajvel@samsung.com ","; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[2350,820067,"NR-based access to unlicensed spectrum","NR_unlic",1,"Rel-16","R1","2017-03-15","2019-12-15",0.97,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 26/6/19: WID:RP-190706->RP-191575; 14/1/20: WID:RP-191575->RP-192926; 25/9/20: WID:RP-192926->RP-201834",null,82,42,null,null,"2019-01-16","2020-09-25"]
[2353,820267,"   Perf. part: NR-based access to unlicensed spectrum","NR_unlic-Perf",2,"Rel-16","R4","2018-12-15","2019-12-15",1,"RP-201834",null,"Qualcomm",null,"26/3/19: WID:RP-182878->RP-190706; 2/7/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-07-02"]
[2354,911003,"   UE Conformance Test Aspects - NR-based access to unlicensed spectrum ","NR_unlic-UEConTest",2,"Rel-16","R5","2021-03-12","2025-03-03",0.94,"RP-210708","RP-242896","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","tested: REL-16 WI NR_unlic-Core ; 2/7/21: 0%->5 ; ; 6/6/22: Compl:18%->20% 20/6/22: Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com ; 9/...; 9/12/22: FCD:22/12/2022->01/06/2023; Compl:25%->28%; Stat Re...",null,91,46,null,null,"2021-04-07","2024-12-06"]
[2359,0,"Cellular IoT support and evolution ","-",1,"Rel-16",null,"2016-06-18","2016-06-18",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2362,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[2365,830039,"      CT3 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->15; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 15%->40; 6/12/19: 40%->65; 6/12/19: WID:CP-111237->CP-193147; 26/3/20: 65%->90; 26/6/20: 90%->100","29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514",83,42,null,null,"2018-12-06","2020-06-26"]
[2368,850014,"   Security of 5G_CIoT","5G_CIoT",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190897",null,"Henrik Normann, Ericsson ","henrik.normann@ericsson.com ","6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[2372,800183,"   Core part: Additional MTC enhancements for LTE","LTE_eMTC5-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[{"$f":"A2376+1","v":2376},800284,"   Perf. part: Additional enhancements for NB-IoT","NB_IOTenh3-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"26/3/19: WID:RP-182902->RP-190757; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[2379,810014,"   Message Service Within the 5G System requirements ","MSGin5G",2,"Rel-16","S1","2018-09-06","2018-12-14",1,"SP-180920",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","4/12/18: 0%->100","22.262; 22.261",81,41,null,null,"2018-09-06","2021-06-11"]
[2381,790002,"Study on Improvement of V2X Service Handling ","FS_V2XIMP",1,"Rel-16","S1","2018-03-15","2018-06-14",1,"SP-180247",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100",22.885999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[2384,780025,"   Study on V2XAPP","FS_V2XAPP",2,"Rel-16","S6","2017-12-15","2018-09-14",1,"SP-171071",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","16/3/18: 0%->45¦14/6/18: 45%->75¦10/9/18: 75%->95¦7/12/18: 95%->100",null,78,40,null,null,"2017-12-15","2018-12-07"]
[2388,840076,"      CT3 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->60; 26/3/20: 60%->100","29.122; 29.116",84,43,null,null,"2019-05-31","2020-03-26"]
[2391,760043,"   Study on eV2XARC","FS_eV2XARC",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180733","SP-170412","LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","11/9/17: 0%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170379->SP 170590¦16/3/18: 20%->25¦7/6/18: 25%->35¦10/9/18: 35%->58¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP 170590->SP-180733¦7/12/18: 58%->88¦14/3/19: 88%->95; 31/5/19: 95%->100",23.786000000000001,76,39,null,null,"2017-06-03","2019-05-31"]
[2394,840079,"      CT1 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.501; 24.301; 27.007",84,43,null,null,"2019-05-31","2020-09-13"]
[2399,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2402,830078,"5G V2X with NR sidelink","5G_V2X_NRSL",1,"Rel-16","R1","2019-03-01","2024-12-12",0.9,"RP-200129",null,"LG Electronics",null,"26/6/19: WID:RP-190766->RP-190984; 8/10/19: WID:RP-190984->RP-191723; 26/3/20: WID:RP-191723->RP-200129",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2403,830178,"   Core part: 5G V2X with NR sidelink","5G_V2X_NRSL-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-200129",null,"LG Electronics",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2407,800013,"5G positioning services","5G_HYPOS",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ",null,22.260999999999999,80,41,null,null,"2018-06-06","NA"]
[2410,830102,"Enhancement to the 5GC LoCation Services","5G_eLCS",1,"Rel-16",null,"2017-12-15","2020-06-12",1,"SP-181119",null,"Ming Ai, CATT","aiming@catt.cn",null,"23.501; 23.502",83,42,null,null,"2018-12-06","NA"]
[2414,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[2416,830045,"      CT3 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85","29.522; 29.122",83,42,null,null,"2018-12-06","2020-06-26"]
[2421,830073,"   Study on local NR positioning in NG-RAN","FS_NR_local_pos",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-191774",null,"CMCC",null,"8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100",38.856000000000002,83,42,null,null,"2019-03-26","2020-01-14"]
[2425,0,"UE radio capability signalling optimization","-",1,"Rel-16",null,"2018-06-06","2018-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2429,840003,"   CT aspects of RACS","RACS",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","17/9/19: WID:CP-191061->CP-192207; 25/3/20: WID:CP-192207->CP-200058",null,84,43,null,null,"2019-05-31","2020-03-25"]
[2430,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[2433,830079,"Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN",1,"Rel-16","R2","2018-06-15","2023-03-03",0.99,"RP-200164",null,"MediaTek",null,"26/3/20: WID:RP-190657->RP-200164",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2436,880073,"   UE Conformance Test Aspects - Optimisations on UE radio capability signalling - NR/E-UTRA Aspects","RACS-UEConTest",2,"Rel-16","R5","2020-03-19","2023-03-03",1,"RP-201152","RP-230098","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 7/4/21: WID:RP-201153->RP-210714; 8/4/21: 5%->25; 8/4/21: FCD:19/03/2021->09/21; 2/7/21: 25%->50; 22/3/22: ; 5/4/22: WID:RP-210714->RP-220434 ; 9/12/22: Acronym:RACS-UEConTest->NG_RAN_PRN_Vertical_LAN-UEConTest; FCD:22/12/2022->01/03...",null,88,45,null,null,"2020-07-28","2023-03-17"]
[2442,830009,"   CT aspects of eNA","eNA",2,"Rel-16","ct","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","3/6/19: WID:CP-190194->CP-191111; 17/9/19: WID:CP-191111->CP-192259",null,83,42,null,null,"2018-12-06","2019-09-17"]
[2444,830049,"      CT4 aspects of eNA","eNA",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100","29.244; 29.510; 29.518; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-03-26"]
[2447,800031,"Study on the security of the Wireless and Wireline Convergence for the 5G system architecture","FS_5WWC_SEC",1,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180438",null,"He Li, Huawei Technologies","LIHE2@HUAWEI.COM","6/8/18: 33.807 added;¦10/9/18: 0%->5¦7/12/18: 5%->30¦20/3/19: 30%->60¦20/3/19: FCD:019->09/19; 31/5/19: 60%->75; 8/10/19: 75%->100","New; 33.807",80,41,null,null,"2018-06-06","2019-10-08"]
[2451,829911,"      CT1 aspects of 5WWC","5WWC",3,"Rel-16","C1","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100","24.501; 24.502; 24.526",82,42,null,null,"2018-12-06","2020-06-30"]
[2455,860019,"   Charging Aspect for 5WWC ","5WWC",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191188",null,"ZHU, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","32.240; 32.255; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-06-28"]
[2456,830082,"   NG interface usage for WWC","5WWC-NG_interface",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190772",null,"Huawei",null,null,null,83,42,null,null,"2019-03-26","NA"]
[2459,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[2464,830051,"Enhancements to Functional architecture and information flows for Mission Critical Data","eMCData2",1,"Rel-16","S6","2018-06-06","2020-03-12",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40",null,83,42,null,null,"2018-06-06","2018-12-07"]
[2467,850051,"MCData File Distribution support over xMB","MC_XMB",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,85,43,null,null,"2018-09-06","2019-05-31"]
[2470,810011,"Protocol enhancements for Mission Critical Services","MCProtoc16",1,"Rel-16","C1","2018-09-06","2019-12-20",1,"CP-182110",null,"AXELL, Jörgen","jorgen.axell@ericsson.com","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->80; 6/12/19: 80%->90; 26/3/20: 90%->100","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980",81,41,null,null,"2018-09-06","2020-03-26"]
[2474,800020,"   Stage 2 of MBMS APIs for MC Services","MBMSAPI_MCS",2,"Rel-16","S6","2018-06-06","2019-03-14",1,"SP-180380",null,"Ling Zhang, TD Tech Ltd.","zhangling@td-tech.com","6/8/18: 23.479 added;¦10/9/18: 0%->15¦7/12/18: 15%->65¦14/3/19: 65%->90; 31/5/19: 90%->100","New; 23.479",80,41,null,null,"2018-06-06","2019-05-31"]
[2477,850059,"   CT4 aspects of eNAPIs","eNAPIs",2,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: 0%->80; 26/3/20: 80%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[2481,800016,"Stage 3 for MC Communication Interworking with Land Mobile Radio Systems","MCCI_CT",1,"Rel-16","C1","2018-06-06","2019-09-12",1,"CP-190203",null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com","10/9/18: 5%->15¦7/12/18: 15%->45¦10/12/18: FCD:12/18->06/19¦10/12/18: WID:CP-181187->CP-183247. 06/03/19: both name and acronym changed (was MCCI3)¦14/3/19: 45%->60¦18/3/19: WID:CP-183248->CP-190203¦18/3/19: FCD:019->09/19; 31/5/19: 60%->70; 13/9/19: 7 ","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482",80,41,null,null,"2018-06-06","2020-03-26"]
[2482,800032,"Mission Critical Services Security Enhancements","MCXSec",1,"Rel-16","S3","2018-06-06","2020-06-11",1,"SP-180596",null,"Woodward, Tim, Motorola Solutions, Inc",null,"10/9/18: 0%->40¦7/12/18: 40%->50¦20/3/19: FCD:019->09/19¦20/3/19: 50%->0; 31/5/19: 0%->45; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 45%->55; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 55%->75; 26/6/20: 75%->80; 12/9/20: FCD:12/03/2020->06/20; 9/4/21: 80% ",33.18,80,41,null,null,"2018-06-06","2021-04-09"]
[2486,810012,"   CT aspects of enhancements of Public Warning System ","ePWS",2,"Rel-16","ct","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155",null,81,41,null,null,"2018-09-06","2019-06-03"]
[2489,810048,"      deleted- CT4 aspects of ePWS (Possible impacts)","ePWS",3,"Rel-16","C4","2018-09-06","2019-12-13",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155; 16/9/19: 0%->100",29.167999999999999,81,41,null,null,"2018-09-06","2019-09-16"]
[2493,760004,"   Stage 1 of MONASTERY2","MONASTERY2",2,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","16/3/18: 35%->55¦7/6/18: 55%->70¦7/6/18: FCD:06/18->12/18¦10/9/18: 70%->75¦4/12/18: 75%->100","New 22.289; 22.280; 22.281; 22.282; 22.179",76,39,null,null,"2017-06-03","2018-12-04"]
[2496,840072,"      CT1 aspects of MONASTERY2 ","MONASTERY2",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-193143",null,"Gkatzikis, Lazaros (Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/19: 0%->10; 6/12/19: 10%->50; 26/3/20: 50%->65; 26/6/20: 65%->100","24.379 ; 24.281 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.581; 24.582",84,43,null,null,"2019-05-31","2020-06-26"]
[2499,840192,"   Core part: NR support for high speed train scenario","NR_HST-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-191788",null,"CMCC",null,"28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[{"$f":"A2504+1","v":2504},800051,"   Stage 1 of MARCOM","MARCOM",2,"Rel-16","S1","2018-06-06","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com","10/9/18: 0%->70¦4/12/18: 70%->95¦14/3/19: 95%->100","22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","2019-03-14"]
[2507,740001,"   Study on eLSTR","FS_eLESTR",2,"Rel-16","S1","2016-12-01","2018-03-15",1,"SP-160960",null,"China Telecommunications, XIA Xu","xiaxu@ctbri.com.cn","2/3/17: 0%->20¦7/6/17: 20%->50¦11/9/17: 50%->70¦15/12/17: 70%->75¦15/12/17: FCD:09/17->03/18¦16/3/18: 75%->100",22.832999999999998,74,38,null,null,"2016-12-01","2018-03-16"]
[2508,800054,"   Stage 1 of eLSTR","eLSTR",2,"Rel-16","S1","2018-05-08","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn","15/6/18: FCD:06/18->09/18¦10/9/18: 90%->100","22.278; 22.115",80,41,null,null,"2018-06-06","2018-09-10"]
[2512,760039,"Study on 5G enhanced Mobile Broadband Media Distribution","FS_5GMedia_Distribution",1,"Rel-16","S4","2017-06-05","2018-09-14",1,"SP-170334",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd., ","i (dot) Bouazizi (at) Samsung (dot) com ","11/9/17: 0%->10¦15/12/17: FCD:03/18->06/20¦15/12/17: 10%->25¦16/3/18: 25%->60¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->75; 26/6/20: 75%->100; 25/9/20: 26.998 added;","26.8xx; 26.998",76,39,null,null,"2017-06-03","2020-09-25"]
[2515,810040,"Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",1,"Rel-16","S4","2017-06-05","2019-12-12",1,"SP-180663",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[2519,820001,"EVS Floating-point Conformance for Non Bit-Exact ","EVS_FCNBE",1,"Rel-16","S4","2018-06-06","2019-12-12",1,"SP-180983",null,"Fabrice, Plante, Intel ","fabrice.m.plante@intel.om ","¦7/3/19: 0%->25¦7/3/19: 0%->25¦7/3/19: 0%->25. CANNOT CHANGE STARTING DATE… Real one: Thu 06/12/18; 31/5/19: 25%->50; 13/9/19: 50%->80; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 80%->100",26.443999999999999,82,42,null,null,"2018-06-06","2019-12-06"]
[2521,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2527,810010,"   CT aspects of Multi-device and multi-identity","MuD",2,"Rel-16","ct","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","9/12/19: WID:CP-182227->CP-193273; 25/3/20: WID:CP-193273->CP-200148",null,81,41,null,null,"2018-06-06","2020-03-25"]
[2530,0,"Slicing","-",1,"Rel-16",null,"2017-09-08","2017-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2534,830011,"   CT aspects of eNS","eNS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","2/7/20: WID:CP-190196->CP-201161",null,83,42,null,null,"2018-12-06","2020-07-02"]
[2535,830052,"      CT1 aspects of eNS","eNS",3,"Rel-16","C1","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","13/9/19: 0%->40; 6/12/19: 40%->85; 26/3/20: 85%->95; 26/6/20: 95%->97; 13/9/20: 97%->100",24.501000000000001,83,42,null,null,"2018-12-06","2020-09-13"]
[2538,810034,"   Study on Security aspects of Enhancement of Network Slicing","FS_eNS_SEC",2,"Rel-16","S3","2018-09-06","2020-03-12",1,"SP-180692",null,null,"Suresh.p.nair@nokia.com","7/12/18: 0%->15¦20/3/19: 15%->65¦20/3/19: FCD:019->06/19; 31/5/19: 65%->75; 13/9/19: FCD:12/06/2019->12/20; 13/9/19: 75%->80; 6/12/19: 80%->85; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 85%->100","New",81,41,null,null,"2018-09-06","2020-06-26"]
[2542,770005,"   Study on Business Role Models for Network Slicing ","FS_BMNS",2,"Rel-16","S1","2017-09-08","2018-09-14",1,"SP-180169",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100","New; 22.830",77,39,null,null,"2017-09-08","2018-12-04"]
[2547,850029,"   KPI reporting ","5G_SLICE_ePA-KPI",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190881",null,"ZHU, Weihong, ZTE Corporation ","zhu.weihong@zte.com.cn ","; 26/3/20: 0%->100","28.550; 28.554; 28.622; 28.532 ",85,43,null,null,"2019-09-13","2020-03-26"]
[2549,0,"Other cross-TSG Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2553,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[2556,830012,"   CT aspects of PARLOS","PARLOS",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2560,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[2561,860015,"   Security Aspects of PARLOS ","PARLOS",2,"Rel-16","S3","2019-12-06","2019-12-13",1,"SP-191126",null,"Schumacher, Greg, Sprint ","Gregory.schumacher@sprint.com ","; 6/12/19: 0%->100",33.401000000000003,86,44,null,null,"2019-12-06","2019-12-06"]
[2564,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[2569,820044,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture","ATSSS",1,"Rel-16",null,"2017-06-05","2023-06-06",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com",null,"23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","NA"]
[2572,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[2575,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[2578,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[2583,820008,"   Security aspects of single radio voice continuity from 5GS to UTRAN ","5GS_UTRAN_SEC",2,"Rel-16","S3","2018-12-13","2019-06-12",1,"SP-190703",null,"Feng Gao, China Unicom ","gaofeng149@chinaunicom.cn ","20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703","33.501; 33.401; 33.220",82,42,null,null,"2018-12-13","2019-09-20"]
[2586,830270,"      Perf. part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-200151",null,"China Unicom",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2587,890046,"      UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G ","SRVCC_NR_to_UMTS-UEConTest",3,"Rel-16","R5","2020-09-17","2021-12-10",1,"RP-210400",null,"China Unicom ",null,"tested: REL-16 WI SRVCC_NR_to_UMTS-Core ; 7/4/21: WID:RP-201794->RP-210400; 8/4/21: 0%->31; 8/4/21: FCD:08/09/2021->09/21; 2/7/21: FCD:Fri 10/09/->12/21; 2/7/21: 31%->85; 6/1/22: 85%->100",null,89,45,null,null,"2020-09-25","2022-01-06"]
[2591,840059,"      CT4 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100","29.303; 29.503; 29.504; 29.505; 29.518; 29.274",84,43,null,null,"2019-05-31","2020-03-26"]
[2595,790007,"   Study on Enhancements to the Service-Based 5G System Architecture","FS_eSBA",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180231",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","7/6/18: 0%->15¦6/8/18: 23.742 added;¦10/9/18: 15%->60¦7/12/18: 60%->100","23.xxx; 23.742",79,40,null,null,"2018-03-15","2018-12-07"]
[2598,830060,"      CT3 aspects of 5G_eSBA","5G_eSBA",3,"Rel-16","C3","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com","6/12/19: 0%->30; 26/3/20: 30%->100","29.507; 29.508; 29.513; 29.512; 29.514; 29.519; 29.520; 29.521; 29.523; 29.525; 29.551; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[2601,780029,"Study on Enhanced IMS to 5GC Integration","FS_eIMS5G",1,"Rel-16","S2","2017-12-15","2019-06-14",1,"SP-180736",null,"Joul, Chris, T-Mobile USA","chris <dot> joul <at> t-mobile <dot> com","16/3/18: 0%->20¦7/6/18: 20%->40¦10/9/18: FCD:09/18->06/19¦2/10/18: WID:SP-171052->SP-180736¦14/3/19: 40%->70; 6/12/19: 70%->100","new 23.794",78,40,null,null,"2017-12-15","2019-12-06"]
[2604,840006,"   CT aspects of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","16/9/19: WID:CP-191065->CP-192023",null,84,43,null,null,"2019-05-31","2019-09-16"]
[2609,830181,"   Core part: Private Network Support for NG-RAN","NG_RAN_PRN-Core",2,"Rel-16","R3","2019-03-01","2020-02-28",1,"RP-200122",null,"China Telecom",null,"26/6/19: WID:RP-190729->RP-191563; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2610,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-21",1,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com 9/9/22: Compl:89%->97%; 29/3/23: 97%->10",null,88,45,null,null,"2020-07-28","2023-03-29"]
[2613,810001,"   Stage 2 of E2E_DELAY","E2E_DELAY",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180662",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->75¦7/3/19: 75%->85¦7/3/19: FCD:03/19->06/19; 31/5/19: 85%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-05-31"]
[2617,830068,"      CT4 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100","23.334; 29.334; 29.238; 23.333; 29.333",83,42,null,null,"2018-09-06","2019-05-31"]
[2621,850008,"   CT aspects of eCAPIF ","eCAPIF",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192254",null,"Narendranath Durga, Tangudu (Samsung) ","n.tangudu {@]samsung.com ","; 6/12/19: 0%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",29.222000000000001,85,43,null,null,"2019-09-13","2020-06-26"]
[2624,830029,"   Stage 2 of UDICOM","UDICOM",2,"Rel-16","S2","2019-03-14","2019-06-14",1,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ","6/6/19: 0%->100; 26/6/19: 23.632 added;","23.501; 23.502; 23.228; 23.632",83,42,null,null,"2019-03-14","2019-06-26"]
[2626,910008,"UICC-terminal interface testing for UEs with non-removable UICCs ","nrUICC_UEConTest",1,"Rel-16","C6","2021-03-18","2022-03-10",1,"CP-210285",null,"Marquordt, Arne, COMPRION GmbH ","amarquordt@comprion.com ",null,"TS 31.121,TS 31.124,TS 31.127",91,46,null,null,"2021-03-18","2023-06-06"]
[{"$f":"A2632+1","v":2632},860258,"   Perf. part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2635,860259,"   Perf. part: Addition of wider channel bandwidth in NR band n65","NR_n65_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200306",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2639,830275,"   Perf. part: UE Power Saving in NR","NR_UE_pow_sav-Perf",2,"Rel-16","R4","2019-03-01","2020-09-15",1,"RP-200494",null,"CATT",null,"7/4/21: 0%->100",null,83,42,null,null,"2019-03-26","2021-04-07"]
[2640,800072,"Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 26/6/19: WID:RP-1907 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2643,800057,"NR intra-band Carrier Aggregation",null,1,"Rel-16",null,"2018-06-15","2019-12-13",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2647,800074,"   Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦16/1/19: WID:RP-180817->RP-182501¦26/3/19: WID:RP-182501->RP-190494; 26/6/19: WID:RP-190494->RP-191565; 8/10/19: WID:RP-191565->RP-191822; 14/1/20: WID:RP-191822->RP-192615; 26/3/20: WID:RP-192615->RP-200168; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2652,830095,"   Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200918",null,"CATT",null,"26/6/19: WID:RP-190692->RP-191153; 8/10/19: WID:RP-191153->RP-192245; 14/1/20: WID:RP-192245->RP-193206; 26/3/20: WID:RP-193206->RP-200238; 28/7/20: WID:RP-200238->RP-200918",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2655,830096,"   Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL",2,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"26/6/19: WID:RP-190693->RP-191566; 8/10/19: WID:RP-191566->RP-191824; 14/1/20: WID:RP-191824->RP-192617; 26/3/20: WID:RP-192617->RP-200171; 28/7/20: WID:RP-200171->RP-200673",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2658,831000,"New bands for New Radio",null,1,"Rel-16","R4","2018-06-15","2022-12-01",0.99,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[2661,800177,"      Core part: Band 65 for New Radio","NR_band_n65-Core",3,"Rel-16","R4","2018-06-15","2018-12-14",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2663,820073,"   Introduction of NR band n18","NR_n18",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-191556",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: WID:RP-190173->RP-191556",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2666,820077,"   Introduction of NR band n48","NR_n48",2,"Rel-16","R4","2018-12-13","2019-05-31",1,"RP-190908",null,"US Cellular",null,"26/6/19: WID:RP-182865->RP-190908",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2669,830090,"   Introduction of NR band n14","NR_n14",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190965",null,"AT&T",null,"26/6/19: WID:RP-190165->RP-190965",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2674,830291,"      Perf. part: Introduction of NR band n30","NR_n30-Perf",3,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190166",null,"AT&T",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2677,830297,"      Perf. part: Introduction of NR band n259","NR_n259-Perf",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2681,840097,"   Introduction of NR supplementary DL band n29","NR_n29",2,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: WID:RP-191474->RP-192236",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2683,840297,"      Perf. part: Introduction of NR supplementary DL band n29","NR_n29-Perf",3,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: 0%->100",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2688,860156,"      Core part: Introduction of band n53","NR_n53-Core",3,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2689,860256,"      Perf. part: Introduction of band n53","NR_n53-Perf",3,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2692,830187,"      Core part: RF requirements for NR FR1","NR_RF_FR1-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-193266",null,"Huawei",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[{"$f":"A2696+1","v":2696},830188,"      Core part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200124",null,"China Telecom",null,"8/10/19: 38.883 added;; 28/7/20: 0%->100",38.883000000000003,83,42,null,null,"2019-03-26","2020-07-28"]
[2700,830189,"      Core part: NR RF requirement enhancements for FR2","NR_RF_FR2_req_enh-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200668",null,"Nokia",null,"8/10/19: 38.831 added;; 25/9/20: 0%->100",38.831000000000003,83,42,null,null,"2019-03-26","2020-09-25"]
[2703,830092,"   Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5","NR_SUL_UL_n5",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2705,830292,"      Perf. part: Introduction of an NR SUL band with same uplink frequency range as NR band n5","NR_SUL_UL_n5-Perf",3,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2711,850063,"   Addition of further channel bandwidths in NR band 38","NR_n38_BW2",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192513",null,"Ericsson",null,"13/6/21: WID:RP-192215->RP-192513",null,85,43,null,null,"2019-10-08","2021-06-13"]
[2714,820075,"   Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 26/6/19: WID:RP-190174->RP-191569; 8/10/19: WID:RP-191569->RP-191681",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2715,820175,"      Core part: Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2718,820176,"      Core part: Adding wider channel bandwidths in NR band n50","NR_n50_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2723,850165,"      Core part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2726,850166,"      Core part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2729,850169,"      Core part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[2731,850070,"   Addition of asymmetric channel bandwidth for NR band n66","NR_n66_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-200265",null,"Huawei",null,"no Perf. Part; 14/1/20: WID:RP-192276->RP-192808; 26/3/20: WID:RP-192808->RP-200265",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2737,800087,"NR mobility enhancements","NR_Mob_enh",1,"Rel-16","R2","2018-06-15","2022-09-22",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 8/10/19: WID:RP-190489->RP-192277; 14/1/20: WID:RP-192277->RP-192534",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2740,880068,"   UE Conformance Test Aspects - NR Mobility Enhancements","NR_Mob_enh-UEConTest",2,"Rel-16","R5","2020-06-22","2022-09-22",1,"RP-221481","RP-221480","Zhaobing Yang, Huawei Technologies. Co., Ltd.","yangzhaobing @hisilicon.com","8/10/20: 0%->5; 8/4/21: 5%->35; 22 6/6/22: CD:10 ; 20/6/22: Rapporteur: Huawei->Zhaobing Yang, Huawei Technologies. Co., Ltd.; Rap eMail: ->yangzhaobing @hisilicon.com12/7/22: WID:RP-200893->RP-2214819/9/22: Compl:97%->100%9/9/22: ...",null,88,45,null,null,"2020-07-28","2022-09-09"]
[2744,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-22",1,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[2745,840091,"SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR","NR_SON_MDT",1,"Rel-16","R3","2019-06-17","2022-06-22",1,"RP-191594",null,"CMCC",null,"no Perf. part; impact on SA2, SA5, CT4?; TR 38.314",null,84,43,null,null,"2019-06-26","NA"]
[2749,850030,"Self-Organizing Networks (SON) for 5G networks ","SON_5G",1,"Rel-16","S5","2019-09-19","2020-09-14",1,"SP-200763",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/19: 0%->80; 8/10/19: 28.544 added;; 8/10/19: 28.313 added;; 28/6/20: 80%->75; 13/9/20: 75%->100; 13/9/20: WID:SP-190785->SP-200763; 13/9/20: FCD:12/03/2020->09/20","28.552; 28.545 ; 28.544; 28.313",85,43,null,null,"2019-09-13","2020-09-13"]
[2752,840293,"   Perf. part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Perf",2,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"2/7/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-07-02"]
[2757,840195,"   Core part: NR RRM enhancement","NR_RRM_enh-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201883",null,"Intel",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[{"$f":"A2760+1","v":2760},840096,"Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 8/10/19: WID:RP-191196->RP-191814; 14/1/20: WID:RP-191814->RP-192447; 26/3/20: WID:RP-192447->RP-200103; 28/7/20: WID:RP-200103->RP-200658",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2763,840098,"Addition of wider channel bandwidth in NR band n1","NR_n1_BW",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-192009",null,"Ericsson",null,"8/10/19: WID:RP-191595->RP-192009",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2766,840099,"Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-191606",null,"Huawei",null,"no Perf. part",null,84,43,null,null,"2019-06-26","NA"]
[2768,841000,"Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2771,841001,"Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[2775,841102,"   Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-Core",2,"Rel-16","R4","2019-07-31","2020-03-12",0,"RP-192093",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093",null,84,43,null,null,"2019-07-31","2019-10-08"]
[2779,0,"Release 16 Features impacting both LTE and NR","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2782,860055,"High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","ENDC_UE_PC2_FDD_TDD",1,"Rel-16","R4","2019-12-16","2021-12-17",1,"RP-193244",null,"China Unicom",null,"affects: LTE, NR. no Perf. part",null,86,44,null,null,"2020-02-18","NA"]
[2786,860157,"   Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 28/7/20: 0%->100; 25/9/20: 37.716-41-22 added;","37.716-41-22",86,44,null,null,"2020-01-14","2020-09-25"]
[2788,860060,"LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 26/3/20: WID:RP-193213->RP-200234; 28/7/20: WID:RP-200234->RP-201359; 25/9/20: WID:RP-201359->RP-201858",null,86,44,null,null,"2020-01-14","2020-09-25"]
[2791,800188,"   Core part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements","LTE_NR_DC_CA_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[2794,820079,"High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD",1,"Rel-16","R4","2018-12-13","2020-03-18",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2797,820279,"   Perf. part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-Perf",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[2801,820080,"LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex",1,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191588",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: WID:RP-190175->RP-191588",null,82,42,null,null,"2019-03-26","2019-06-26"]
[2805,920068,"   UE Conformance Test Aspects - 29 dBm UE Power Class for LTE Band 41 and NR Band n41 ","LTE_NR_B41_Bn41_PC29dBm-UEConTest",2,"Rel-16","R5","2021-06-15","2022-12-01",1,"RP-211443","RP-223059","Dan SONG, CMCC, T-Mobile","songdan@chinamobile.com","tested: REL-17 WI LTE_NR_B41_Bn41_PC29dBm-Core ; 5/4/22: WID:RP-211443->RP-220124 6/6/22: C ; 20/6/22: Stat Rep: R5-222679->RP-221180 / R5-222679; Rapporteur: T-Mobile USA->Scott Probasco, Dan SONG, T-Mobile, CMCC; Rap eMail: ->scott.probasco@t-mobile....",null,92,47,null,null,"2021-07-02","2023-01-09"]
[2808,800166,"      Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦26/3/19: WID:RP-182567->RP-190705; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2810,800067,"   Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦TR 37.716-02-01¦16/1/19: WID:RP-181357->RP-182557¦26/3/19: WID:RP-182557->RP-190379; 26/6/19: WID:RP-190379->RP-191124; 8/10/19: WID:RP-191124->RP-192087; 14/1/20: WID:RP-192087->RP-192815; 26/3/20: WID:RP-192815->RP-200271; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2816,800069,"   Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦16/1/19: WID:RP-181001->RP-182534¦26/3/19: WID:RP-182534->RP-190294; 26/6/19: WID:RP-190294->RP-191205; 8/10/19: WID:RP-191205->RP-191728; 14/1/20: WID:RP-191728->RP-192768; 26/3/20: WID:RP-192768->RP-200134; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2817,800169,"      Core part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2820,800170,"      Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2823,800171,"      Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2828,790257,"   Perf. part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Perf",2,"Rel-16","R4","2018-03-15","2018-12-14",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦16/1/19: 0%->100",null,79,40,null,null,"2018-03-27","2019-01-16"]
[2831,800060,"   Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦TR 36.716-01-01¦16/1/19: WID:RP-180806->SP-182255¦26/3/19: WID:RP-182255->RP-190157; 26/6/19: WID:RP-190157->RP-191193; 8/10/19: WID:RP-191193->RP-191811; 14/1/20: WID:RP-191811->RP-192444; 26/3/20: WID:RP-192444->RP-200100; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2836,800261,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2839,800262,"      Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182553->; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2842,800263,"      Perf. part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201238",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2843,800064,"   Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2849,810061,"   UE Conformance Test Aspects – Rel-16 LTE CA configurations","LTE_CA_R16-UEConTest",2,"Rel-16","R5","2018-09-14","2022-12-21",7.0000000000000007E-2,"RP-182648","RP-222098","Leif MATTISSON","Leif[dot]mattisson[at]ericsson[dot]com","16/1/19: WID:RP-181605->RP-182648; 8/10/20: 0%->7; 8/10/20: FCD:19/06/2020->12/20; 8/4/21: 7%->7; 8/4/21: FCD:11/12/2020->09/21; 2/7/21: 7%->; 2/7/21: FCD:Wed 08/09/->03/22; 20/6/22: FCD:11/03/2022->22/12/2022; WID: RP-182648->RP-171886; Stat Rep: ->RP...",null,81,41,null,null,"2018-09-25","2022-09-09"]
[2850,830076,"LTE-based 5G terrestrial broadcast","LTE_terr_bcast",1,"Rel-16","R1","2018-06-15","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"8/10/19: WID:RP-190732->RP-191924; 8/10/19: 36.276 added;; 14/1/20: WID:RP-191924->RP-193050","36.276; 36.476",83,42,null,null,"2019-03-26","2020-01-14"]
[2854,830094,"Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72",1,"Rel-16","R4","2019-03-01","2020-09-11",1,"RP-191285",null,"Nokia",null,"26/6/19: WID:RP-190665->RP-191285",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2858,800056,"Additional LTE bands",null,1,"Rel-16",null,"2018-06-15","2021-09-21",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2862,900052,"      UE Conformance Test Aspects - Additional LTE bands for UE category M1 and/or NB1 in Rel-16 ","LTE_bands_R16_M1_NB1-UEConTest",3,"Rel-16","R5","2020-12-14","2021-09-08",1,"RP-202522",null,"Ericsson ",null,"tested: REL-16 WI LTE_bands_R16_M1_NB1-Core ; 8/4/21: 0%->26; 2/7/21: 26%->80",null,90,46,null,null,"2021-01-06","2021-07-02"]
[2865,900053,"      UE Conformance Test Aspects - Additional LTE bands for UE category M2 and/or NB2 in Rel-16 ","LTE_bands_R16_M2_NB2-UEConTest",3,"Rel-16","R5","2020-12-14","2021-09-08",1,"RP-202523",null,"Ericsson ",null,"tested: REL-16 WI LTE_bands_R16_M2_NB2-Core ; 8/4/21: 0%->33; 2/7/21: 33%->59",null,90,46,null,null,"2021-01-06","2021-07-02"]
[2868,800279,"   Perf. part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2871,800282,"   Perf. part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Perf",2,"Rel-16","R4","2018-06-15","2019-06-14",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2873,800086,"DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE",1,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"16/1/19: WID:RP-181485->RP-182901; 14/1/20: WID:RP-182901->RP-192766",null,80,41,null,null,"2018-06-27","2020-01-14"]
[2876,820071,"Transfer of Iuant interface specifications from 25-series to 37-series","Iuant_transfer",1,"Rel-16","R3","2018-12-13","2019-03-18",1,"RP-190160",null,"Huawei",null,"administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs¦no Perf .",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2880,800089,"Even further mobility enhancement in E-UTRAN","LTE_feMob",1,"Rel-16","R2","2018-06-15","2022-06-22",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 26/6/19: WID:RP-190272->RP-190921; 26/3/20: WID:RP-190921->RP-200148",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2884,820078,"410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe","LTE410_Europe_PPDR",1,"Rel-16","R4","2018-12-13","2020-12-17",1,"RP-191287",null,"Nokia",null,"26/6/19: WID:RP-182898->RP-191287",null,82,42,null,null,"2019-01-16","2019-06-26"]
[{"$f":"A2888+1","v":2888},850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2891,0,"All other Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2893,880009,"User Plane Integrity Protection ","UPIP_SEC",1,"Rel-16","S3","2020-06-12","2020-06-25",1,"SP-200656",null,"Tim Evans, Vodafone Group ","tim.evans1@vodafone.com ","33.501; 33.401 ; 26/6/20: 0%->100; 25/9/20: WID:SP-200354->SP-200656",null,88,45,null,null,"2020-06-25","2020-09-25"]
[2896,830186,"   Core part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Core",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2899,810021,"   Stage 2 of VBCLTE","VBCLTE",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50; 13/9/19: 50%->55; 13/9/19: FCD:14/06/2019->12/20; 6/12/19: 55%->100","32.251; 32.260; 32.298; 32.299",81,41,null,null,"2018-09-06","2019-12-06"]
[2903,820070,"Integrated access and backhaul for NR","NR_IAB",1,"Rel-16",null,"2017-03-15","2020-06-12",1,"RP-210442",null,"Qualcomm",null,"follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 26/6/19: WID:RP-190712->RP-191558; 8/10/19: WID:RP-191558->RP-192188; 14/1/20: WID:RP-192188->RP-193226; 26/3/20: WID:RP-193226->RP-200084; 28/7/20: WID:RP-200084->RP-200840; 25/9/2 ",38.808999999999997,82,42,null,null,"2019-01-16","2021-04-07"]
[2906,850060,"      Stage 2 of IABARC","IABARC",3,"Rel-16","S2","2019-09-19","2019-12-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33; 6/12/19: 33%->100","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-12-06"]
[2910,820270,"   Perf. Part: NR_IAB","NR_IAB-Perf",2,"Rel-16","R4","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added;; 2/7/21: 0%->100","38.809; 38.176-1; 38.176-2",82,42,null,null,"2019-01-16","2021-07-02"]
[2914,820028,"Enhancement of 5G PCC related services ","en5GPccSer",1,"Rel-16","C3","2018-12-13","2019-12-19",1,"CP-183246",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","¦14/3/19: 0%->10; 31/5/19: 10%->60; 13/9/19: 60%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 ",82,42,null,null,"2018-12-07","2020-03-26"]
[2915,810023,"Energy efficiency of 5G","EE_5G",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-191193",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com ","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->45; 13/9/19: 45%->70; 12/12/19: WID:SP-180819->SP-191193; 12/12/19: FCD:13/12/2019->03/20; 26/3/20: 70%->95; 28/6/20: 95%->100","28.540; 28.541; 28.552; 28.554",81,41,null,null,"2018-09-06","2020-06-28"]
[2921,800030,"   Stage 2 of xBDT","xBDT",2,"Rel-16","S2","2019-03-07","2019-12-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com","31/5/19: 0%->100","23.501; 23.502; 23.503",80,41,null,null,"2018-06-06","2019-05-31"]
[2922,840014,"   CT aspects of xBDT","xBDT",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","17/9/19: WID:CP-191113->CP-192182",null,84,43,null,null,"2019-05-31","2019-09-17"]
[2925,850057,"      CT4 aspects of xBDT","xBDT",3,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","26/3/20: 0%->100",null,85,43,null,null,"2019-05-31","2020-03-26"]
[2928,800046,"Shared Data Handling on Nudm and Nudr","Shared_Data",1,"Rel-16","C4","2018-06-06","2018-12-14",1,"CP-181136",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com","10/9/18: 0%->90¦10/12/18: 90%->100","29.503; 29.505; 29.504",80,41,null,null,"2018-06-06","2018-12-10"]
[2933,760058,"Management of QoE measurement collection","QOED",1,"Rel-16","S5","2017-06-05","2019-12-12",1,"SP-181069",null,"Petersen, Robert, Ericsson","robert <dot> petersen <at>ericsson<dot>ericsson","30/6/17: 28.309 added;¦30/6/17: 28.308 added;¦30/6/17: 28.307 added;¦30/6/17: 28.406 added;¦11/9/17: 0%->5¦15/12/17: 5%->15¦16/3/18: 15%->25¦7/6/18: FCD:06/18->12/18. 16/6/16: moved from Rel-15¦10/9/18: 25%->30¦7/12/18: 30%->40¦13/12/18: FCD: ; 31/5/ ","32.101; 32.103; 6 new TS; 28.309; 28.308; 28.307; 28.406; 28.405; 28.404",76,39,null,null,"2017-06-07","2020-09-13"]
[2936,810024,"OAM aspects of LTE and WLAN integration","OAM_LTE_WLAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180820",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","7/12/18: 0%->50¦14/3/19: 50%->100","32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659",81,41,null,null,"2018-09-06","2019-03-14"]
[2941,820033,"Network Exposure Charging in 5G System Architecture ","5GS_Ph1_NEFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181070",null,"Tornkvist, Robert, Ericsson ","robert(dot)tornkvist(at)Ericsson(dot)com ","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100","32.240; 32.254; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-12-06"]
[2944,820005,"Lawful Interception Rel-16 ","LI16",1,"Rel-16","S3LI","2018-12-13","2021-06-11",1,"SP-181210",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ","31/5/19: 0%->15; 13/9/19: 15%->40; 6/12/19: 40%->55; 25/3/20: 55%->60; 25/3/20: FCD:19/12/2019->03/20; 26/6/20: FCD:13/03/2020->09/20; 26/6/20: 60%->85; 12/9/20: 85%->92; 5/12/20: 92%->97; 19/3/21: 97%->99; 19/3/21: FCD:15/09/2020->06/21; 11/6/21: 99%- ","33.107; 33.108; 33.126; 33.127; 33.128 ",82,42,null,null,"2018-12-07","2021-06-11"]
[2945,820038,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 30/6/20: 99%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",82,42,null,null,"2018-12-07","2020-06-30"]
[2948,870078,"   (IETF) Location Source Parameter for the SIP Geolocation Header Field (draft-ietf-sipcore-locparam)","5GProtoc16",2,"Rel-16","C1-IETF","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 30/6/20: 90%->100; 9/4/21: RFC 8787 added;","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ; RFC 8787",87,44,null,null,"2018-12-07","2021-04-09"]
[2954,820047,"   Stage-3 SAE Protocol Development for Rel16 for CS Fallback in EPS","SAES16-CSFB",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[2956,840018,"S6b Optional for ePDG connected to 5GS ","5GS_S6b_Optional",1,"Rel-16","S2","2019-05-09","2019-06-06",1,"SP-190447",null,"Irfan Ali, Cisco ","irfaali at cisco dot com ","6/6/19: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[2959,840053,"   CT4 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","31/5/19: 0%->10; 6/12/19: 10%->90; 26/3/20: 90%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.531; 29.540; 29.518; 29.571; 29.572; 29.573",84,43,null,null,"2019-05-31","2020-06-26"]
[2963,850025,"Network Slice Performance and Analytics Charging in 5G System ","5GS_NSPACH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190780",null,"Chen Shan, Huawei ","chenshan@huawei.com ","8/10/19: 28.201 added;; 6/12/19: 0%->15; 26/3/20: 15%->30; 28/6/20: 30%->60; 13/9/20: 60%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.201",85,43,null,null,"2019-09-13","2020-09-13"]
[2967,850033,"Network Slice Management Charging in 5G System ","5GS_NSMCH",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190788",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 8/10/19: 28.202 added;; 6/12/19: 0%->5; 28/6/20: 5%->50; 13/9/20: 50%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.202",85,43,null,null,"2019-09-13","2020-09-13"]
[2970,800044,"   Study on Load and Overload Control of 5GC Service Based Interfaces","FS_LOLC",2,"Rel-16","C4","2018-06-06","2019-06-14",1,"CP-181195",null,"Sridhar Bhaskaran (Huawei)","sridhar.bhaskaran@huawei.com","6/8/18: 22.943 added;¦10/9/18: 0%->5¦10/12/18: 5%->25¦14/3/19: 25%->50; 31/5/19: 50%->90; 6/12/19: 90%->100","New; 22.943",80,41,null,null,"2018-06-06","2019-12-06"]
[2971,850052,"   Deleted: C3 aspects of LOLC (TBD)","LOLC",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","2/7/20: deleted, put at 100% (was at 0)","TBD",85,43,null,null,"2019-09-13","NA"]
[2976,830026,"Integration of ONAP and 3GPP 5G management framework","ONAP3GPP",1,"Rel-16","S5","2019-03-07","2020-03-12",1,"SP-190139",null,"SMITH David K., AT&T ","DS9930@att.com","31/5/19: 0%->10; 13/9/19: 10%->25; 13/9/19: FCD:05/03/2020->03/20; 26/3/20: 25%->100","28.540; 28.622; 28.623; 28.532",83,42,null,null,"2019-03-14","2020-03-26"]
[2978,860017,"3GPP profiles for cryptographic algorithms and security protocols ","CryptPr",1,"Rel-16","S3","2019-12-06","2020-03-12",1,"SP-191129",null,"Christine Jost, Ericsson ","christine.jost@ericsson.com ","; 25/3/20: 0%->100","33.210; 33.310; 33.501 ",86,44,null,null,"2019-12-06","2020-03-25"]
[2982,860001,"Nudsf Service Based Interface ","NUDSF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193270",null,"Askerup, Anders, Hewlett Packard Enterprise, ","Anders.Askerup@hpe.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.510; 29.500 ",86,44,null,null,"2019-12-06","2020-07-02"]
[2985,860004,"Video enhancement of IMS CAT/CRS/announcement services ","eIMSVideo",1,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193149",null,"Hongxia Hao, Huawei ","haohongxia@huawei.com ","; 26/3/20: 0%->33; 26/6/20: 33%->100","24.182; 24.183; 24.628 ",86,44,null,null,"2019-12-06","2020-06-26"]
[2989,960003,"UE Conformance Test Aspects Release 16 ","UEConTest_R16",1,"Rel-16","C6","2022-06-03","2023-09-09",1,"CP-221184",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","20/6/22: FCD:12/06/2023->09/20; 6/6/23: Compl:90%->98%","31.121; 31.124 ",96,49,null,null,"2022-06-03","2023-06-06"]
[2993,0,"Release 16 Studies with no corresponding Feature","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2996,790014,"Study on security aspects of single radio voice continuity from 5G to UTRAN","FS_5G_UTRAN_SEC",1,"Rel-16","S3","2018-03-15","2019-03-15",1,"SP-180209",null,"Feng Gao, China Unicom","gaofeng149@chinaunicom.cn","27/3/18: 33.856 added;¦7/6/18: 0%->50¦10/9/18: 50%->79¦7/12/18: 79%->100",33.856000000000002,79,40,null,null,"2018-03-15","2018-12-07"]
[2998,780001,"Study on User Plane Protocol in 5GC","FS_UPPS",1,"Rel-16","C4","2017-12-15","2019-06-14",1,"CP-182052",null,"Satoru Matsushima, SoftBank Corp","satoru.matsushima@g.softbank.co.jp","16/3/18: 0%->5¦2/10/18: WID:CP-173160->CP-182052¦2/10/18: FCD:09/18->06/19¦14/3/19: 20%->70; 31/5/19: 70%->90; 14/1/20: 90%->100",29.891999999999999,78,40,null,null,"2017-12-15","2020-01-14"]
[3001,800093,"Study on remote interference management for NR","FS_NR_RIM",1,"Rel-16","R1","2018-06-15","2018-12-14",1,"RP-181430",null,"CMCC",null,"TR 38.8xx¦see follow-up REL-16 WI NR_CLI_RIM¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[3004,801002,"Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR","FS_NR_2RX_vehUE",1,"Rel-16","R4","2018-06-01","2018-12-14",1,"RP-181467",null,"Samsung",null,"TR 38.8XX¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[3007,810033,"Stopped - Study of KDF negotiation for 5G System Security","FS_5GS_KDF",1,"Rel-16","S3","2018-09-06","2019-06-14",1,"SP-180691",null,"Ahmad Muhanna ","ahmad.muhanna@huawei.com","7/12/18: 0%->55¦20/3/19: 55%->100","New",81,41,84,null,"2018-09-06","2019-03-20"]
[3012,830072,"Study on enhancement for disaggregated gNB architecture","FS_enh_disagg_gNB",1,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-191975",null,"China Telecom",null,"26/6/19: WID:RP-190702->RP-191481; 8/10/19: WID:RP-191481->RP-191975; 8/10/19: 38.823 added;; 14/1/20: 0%->100",38.823,83,42,null,null,"2019-03-26","2020-01-14"]
[{"$f":"A3016+1","v":3016},770003,"Study on enhancements to IMS for new real time communication services","FS_enIMS",1,"Rel-16","S1","2017-09-08","2017-12-15",1,"SP-170703",null,"China Mobile, Hui Cai ","caihui at chinamobile dot com","11/9/17: 0%->20¦15/12/17: 22.823 added;¦15/12/17: 20%->75¦16/3/18: 75%->100; 25/9/20: 26.998 added;","New; 22.823; 26.998",77,39,null,null,"2017-09-08","2020-09-25"]
[3019,780031,"Study on integration of ONAP DCAE and 3GPP management architecture ","FS_ONAPDCAE",1,"Rel-16","S5","2017-12-15","2019-03-15",1,"SP-181074",null,"ORANGE (Jean-Michel Cornily","jeanmichel.cornily@orange.com","16/3/18: 0%->10¦27/3/18: 28.900 added;¦7/6/18: 10%->20¦7/6/18: FCD:09/18->03/19¦15/6/18: WID:SP-170948->SP-180389¦10/9/18: 20%->35¦7/12/18: 35%->80¦14/12/18: WID:SP-180389->SP-181074¦14/3/19: 80%->100",28.9,78,40,null,null,"2017-12-15","2019-03-14"]
[3020,800039,"Study on management aspects of edge computing","FS_MAN_EC",1,"Rel-16","S5","2018-06-06","2019-03-14",1,"SP-180390",null,"Joey Chou, Intel","joey<dot>chou<at>intel<dot>com","6/8/18: 28.803 added;¦10/9/18: 0%->10¦7/12/18: 10%->20¦14/3/19: 20%->50; 31/5/19: 50%->65; 13/9/19: 65%->100","New; 28.803",80,41,null,null,"2018-06-06","2019-09-13"]
[3024,820037,"Study on non-file-based trace reporting ","FS_OAM_RTT",1,"Rel-16","S5","2018-12-06","2019-06-12",1,"SP-181076",null,"Andrianov, Anatoly, Nokia ","anatoly.andrianov@nokia.com ","13/9/19: 0%->100",null,82,42,null,null,"2018-12-07","2019-09-13"]
[3027,760045,"Stopped - Study on encrypted traffic detection ","FS_ENTRADE",1,"Rel-16","S2","2017-06-05","2019-06-12",1,"SP-181111",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn","¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: WID:SP-170381->SP-170934¦16/3/18: 0%->20¦7/6/18: 20%->70¦14/12/18: FCD:09/18->06/19. Name changed; 22/3/22: stopped at 70% (\"deprioritised\"in SA2 language)","new 23.787",76,39,84,null,"2017-06-03","2022-03-22"]
[3030,0,"Release 15 Features on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3033,720005,"   (Stage 1 of 5G) New Services and Markets Technology Enablers","SMARTER",2,"Rel-15","S1","2016-06-09","2017-03-15",1,"SP-160364",null,"Li, Alice","alice.li@vodafone.com","Resulting from FS_SMARTER¦19/9/16: 0%->55¦6/10/16: 22.261 added¦1/12/16: FCD:09/16->03/20¦1/12/16: 55%->75¦2/3/17: 75%->90¦7/6/17: 90%->100",22.260999999999999,72,37,null,null,"2016-06-09","2017-06-07"]
[3038,750026,"      Studies on CT1 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15",null,"2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","18/12/17: WID:CP-172034->CP-173161","23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-12-18"]
[3042,770045,"         Study on 5G Non-3GPP access networks","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 15%->55¦15/12/17: 55%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[3046,780008,"      CT1 aspects of 5G System - Phase 1 (normative work)","5GS_Ph1-CT",3,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-09-08"]
[3049,780011,"         5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->35¦16/3/18: 35%->85¦7/6/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[3050,780012,"         5G Non-3GPP access networks","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->95¦10/9/18: 95%->100",null,77,39,null,null,"2017-03-03","2018-09-10"]
[3053,780015,"         5G Network slicing","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[3059,790043,"      CT6 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15","C6","2018-03-16","2018-06-14",1,"CP-183243",null,"Landais, Bruno (Nokia)","Bruno.Landais at nokia.com","5/6/17: 0%->5¦11/9/17: 5%->25¦15/12/17: 25%->45¦16/3/18: 45%->50¦16/3/18: 0%->20¦7/6/18: 20%->90¦10/9/18: 90%->95. 10/9/18: 95->100 as per CT81 discussions¦10/12/18: 100%->95¦11/12/18: 95%->100","23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303",75,38,null,null,"2017-03-03","2018-12-11"]
[3061,760029,"   IMS impact due to 5GS IP-CAN","5GS_Ph1-IMSo5G",2,"Rel-15","ct","2017-09-04","2018-06-15",1,"CP-180094",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","8/9/17: WID:CP-171103->CP-172033¦FCD: 12/17->06/18¦19/3/18: WID:CP-172033->CP-180094",null,76,39,null,null,"2017-06-02","2018-03-19"]
[3064,770019,"      CT4 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C4","2017-09-04","2018-06-15",1,"CP-180094",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","23.008; 29.228; 29.229; 29.328; 29.329; 23.003",77,39,null,null,"2017-03-03","2018-06-07"]
[3068,800040,"   Charging for IMS over 5G System Architecture Phase 1","5GS_Ph1_IMSCH",2,"Rel-15","S5","2018-05-07","2018-06-15",1,"SP-180391",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.240; 32.260; 32.299; 32.298",80,41,null,null,"2018-06-06","2018-06-07"]
[3072,750036,"   SA3 aspects of EDCE5","EDCE5",2,"Rel-15","S3","2017-03-02","2017-09-14",1,"SP-170233",null,"Adrian Escott, Qualcomm Incorporated",null,"7/6/17: 0%->60¦11/9/17: 60%->70¦15/12/17: 70%->100",null,75,38,null,null,"2017-03-02","2017-12-15"]
[3075,760069,"      CT3 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C3","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com",null,"29.212; 29.213; 29.214; 29.215; 29.201",76,39,null,null,"2017-06-05","NA"]
[3076,760070,"      CT4 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C4","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","11/9/17: 0%->50¦15/12/17: 50%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",76,39,null,null,"2017-06-05","2017-12-15"]
[3081,750072,"LTE connectivity to 5G-CN","LTE_5GCN_connect",1,"Rel-15","R2","2017-03-15","2018-12-20",1,"RP-171432",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-170840->RP-171432",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3084,760087,"UE Conformance Test Aspects - 5G system with NR and LTE","5GS_NR_LTE-UEConTest",1,"Rel-15","R5","2017-06-15","2021-12-14",0.87,"RP-211228",null,"Ericsson",null,"¦19/9/17: Compl:0%->2%¦15/12/17: impacted specs add¦15/12/17: 38.508-2 added;¦ ;; 8/10/19: WID:RP-181206->RP-192123; 8/10/19: 34.229-5 added;; 24/4/20: FCD:14/12/2018->12/20; 24/4/20: 15%->69; 8/10/20: 69%->79; 8/10/20: FCD:15/12/2020->12/20; 7/4/21: W ","38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2; 34.229-5",76,39,null,null,"2017-06-16","2021-07-02"]
[3087,720003,"   Study on Enhancement of 3GPP support for V2X services","FS_eV2X",2,"Rel-15","S1","2016-06-09","2016-12-15",1,"SP-160370",null,"LG Electronics, SungDuck Chun","sungduck.chun@lge.com","19/9/16: 30%->70¦6/10/16: 22.886 added¦1/12/16: 70%->95¦2/3/17: 95%->100",22.885999999999999,72,37,null,null,"2016-06-09","2017-03-02"]
[3090,750175,"   Core part: V2X new band combinations for LTE","LTE_V2X_CA_bands-Core",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-180328",null,"LG Electronics",null,"no Perf. part¦19/6/17: Compl:0%->20%¦19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->50%¦27/3/18: Compl:50%->70%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3095,0,"Release 15 Features on Ultra/Highly Reliable Low Latency Communication","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3098,750161,"   Core part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-181259","RP-180693","Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: Compl:0%->10%¦8/1/18: WID: RP-171489->RP-172845¦27/3/18: Compl:10%->30%¦27/6/18: Compl:30%->99%¦27/6/18: CD:Fri 15",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3101,720057,"Study on MC system migration and interconnect between MCPTT systems","FS_MCSMI",1,"Rel-15","S6","2016-06-13","2017-06-12",1,"SP-160880",null,"Chater-Lea, David",null,"28/7/16: 23.781 added¦19/9/16: WID:SP-160340->SP-160526¦FCD: 09/16->12/16¦19/9/16: 0%->40¦1/12/16: WID:SP-160526->SP-160880¦1/12/16: 40%->48¦9/12/16: FCD:12/16->06/17, Rel-14->Rel-15¦3/3/17: 48%->60¦7/6/17: 60%->100","New 23.781",72,37,null,null,"2016-09-16","2017-06-07"]
[3103,720083,"Study on MC Security Enhancements","FS_MC_Sec",1,"Rel-15","S3","2016-06-17","2018-03-15",1,"SP-170416",null,"Haigh, Peter, CESG","peter.haigh@cesg.gsi.gov.uk ","28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17","33.xxx; 33.280; 39.880",72,37,null,null,"2016-06-17","2018-03-16"]
[3106,750021,"Enhancements to MCPTT functional architecture and information flows ","enhMCPTT",1,"Rel-15",null,"2017-03-03","2018-06-15",1,"SP-170248",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->25","23.280 + 23.379",75,38,null,null,"2017-03-03","2017-06-07"]
[3110,770010,"   Stage 2 of eMCData","eMCData",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170462",null,"David Freeman, Home Office","david@dnf-consulting.co.uk","21/3/17: impacted TS/TR added¦7/6/17: 0%->10¦8/6/17: WID:SP-170249->SP-170462¦11/9/17: 10%->15¦15/12/17: 15%->100","23.280 + 23.282",75,38,null,null,"2017-03-03","2017-12-15"]
[3112,760048,"Enhancements to MC Video Functional architecture and information flows","eMCVideo",1,"Rel-15",null,"2017-06-05","2018-06-15",1,"SP-170401",null,"Niranth Amogh, Huawei Telecommunications (India","namogh@huawei.com","7/6/17: 0%->10","23.280; 23.281",76,39,null,null,"2017-06-03","2017-06-07"]
[3117,770016,"      CT6 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C6","2017-12-05","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","10/9/18: 0%->100","31.102; 31.103",77,39,null,null,"2017-06-03","2018-09-10"]
[3121,800017,"   Stage 3 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","C1","2018-04-09","2018-06-07",1,"CP-183105",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","12/6/18: 10%->30¦10/9/18: 30%->70¦7/12/18: 70%->100","24.281; 24.282; 24.379; 24.380; 24.581; 24.380",80,41,null,null,"2018-06-06","2018-12-10"]
[3124,890042,"UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo ","MCenhUEConTest",1,"Rel-15","R5","2020-09-17","2022-06-22",1,"RP-212956","RP-221332","KAHN, Jason, NIST (U.S. Department of Commerce)","jason.kahn@nist.gov","tested: REL-15 SA/CT WIs enhMCPTT, eMCVideo, eMCData, MBMS_Mcservices, MCSMI, MCProtoc15, MCOver ; 8/4/21: 0%->16; 2/7/21: 16%->33; 13/9/21: Compl:33%->40%; 13/9/21: CD:Fri 17/12/21->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211764; 6/1/22: WID:RP-201487- ; ",null,89,45,null,null,"2020-09-25","2022-06-20"]
[3125,0,"Release 15 Features on MTC-IoT","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3129,750159,"   Core part: Even further enhanced MTC for LTE","LTE_eMTC4-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",1,"RP-172811","RP-181213","Ericsson",null,"WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦19/6/17: Compl:0%- 19/9/ 8/1 2 ;¦16/1/19: 97%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3132,750066,"Further NB-IoT enhancements","NB_IOTenh2",1,"Rel-15","R1","2017-03-15","2021-09-08",0.98,"RP-182389",null,"Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦14/9/17: WID:RP-170852->RP-171428",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3138,740003,"   Stage 1 of ProSe_WLAN_DD","ProSe_WLAN_DD",2,"Rel-15","S1","2016-11-15","2016-12-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[3140,760026,"   Stage 3 of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",2,"Rel-15","ct","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","18/12/17: WID:CP-171102->CP-173084",null,76,39,null,null,"2017-06-02","2017-12-18"]
[3143,780045,"   Charging of ProSe_WLAN_DD","ProSe_WLAN_DD-CH",2,"Rel-15","S5","2017-12-15","2018-03-15",1,"SP-170947",null,"Yizhi Yao, Intel Corporation ","yizhi.yao@intel.com","15/12/17: 0%->40¦16/3/18: 40%->100","32.277; 32.298; 32.299",74,38,null,null,"2016-12-01","2018-03-16"]
[3147,760022,"   CT aspects of VoWLAN","VoWLAN-CT",2,"Rel-15","ct","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: WID:CP-171101->CP-181083",null,76,39,null,null,"2017-06-02","2018-06-07"]
[3151,0,"Release 15 Features on Virtual Reality (VR)","-",1,"Rel-15",null,"2016-03-01","2016-03-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3152,710014,"Study on Virtual Reality","FS_VR",1,"Rel-15","S4","2016-03-01","2017-09-12",1,"SP-160084",null,"Gilles TENIOU, Orange","gilles.teniou@orange.com","11/6/16: 0%->10¦19/9/16: 10%->40, FCD: 12/16->03/17¦1/12/16: FCD:03/17->06/17¦1/12/16: 40%->35¦14/12/16: 35%->45¦14/12/16: FCD:06/17->09/17¦6/3/17: 45%->55¦7/6/17: 55%->70¦11/9/17: 70%->100",26.917999999999999,71,36,null,null,"2016-03-01","2017-09-11"]
[3155,770023,"Addition of HDR to TV Video Profiles","HDR",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170610",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->100","26.116; 26.346; 26.234; 26.247; 26.244",77,39,null,null,"2017-09-08","2017-12-15"]
[3160,790018,"Charging aspects of WLAN access in EPC","WAEPC_CH",1,"Rel-15","S5","2018-03-15","2018-06-15",1,"SP-180078",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.251; 32.260; 32.299; 32.298",79,40,null,null,"2018-03-15","2018-06-07"]
[3163,790025,"SRVCC for terminating call in pre-alerting phase","bSRVCC_MT",1,"Rel-15",null,"2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com",null,null,79,40,null,null,"2018-03-16","NA"]
[3166,790035,"Increasing the number of EPS bearers","INOBEAR",1,"Rel-15",null,"2018-03-16","2018-06-15",1,"SP-171044",null,"Andy.Bennett, Samsung","a <dot> bennett <at> Samsung.com",null,"23.401; 23.167",78,40,null,null,"2017-12-15","NA"]
[3169,790037,"      CT1 aspects of INOBEAR","INOBEAR-CT",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com","7/6/18: 0%->100","24.301; 24.007",79,40,null,null,"2017-12-15","2018-06-07"]
[3173,780019,"Remote UE access via relay UE","REAR",1,"Rel-15",null,"2016-03-01","2018-06-15",1,"SP-160511",null,"Huawei, Laurence Meriau","laurence.meriau@huawei.com","Previously known as \"wearable devices\"¦9/6/16: 0%->100¦9/6/16: WID:SP-160231->SP-160371","22.278; 22.115",71,36,null,null,"2016-03-11","2016-06-09"]
[3177,780046,"Enhanced VoLTE performance","eVoLP",1,"Rel-15",null,"2016-12-01","2018-06-15",1,null,null,null,null,null,null,78,40,null,null,"2017-12-15","NA"]
[3178,780026,"   Stage 2 of eVoLP","eVoLP",2,"Rel-15","S2","2017-10-12","2017-12-15",1,"SP-170935",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com",null,"23.401; 23.203",78,40,null,null,"2017-12-15","NA"]
[3181,780043,"      CT4 aspects of EvoLP","eVoLP-CT",3,"Rel-15","C4","2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com","7/6/18: 0%->100",29.274000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[3186,740008,"   Study on unlicensed spectrum offloading system enhancements","FS_USOS",2,"Rel-15","S2","2016-12-01","2017-06-15",1,"SP-160835",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100",23.728999999999999,74,38,null,null,"2016-12-01","2017-09-11"]
[3189,770001,"   Stage 3 of USOS","USOS-CT",2,"Rel-15","C4","2017-09-08","2018-03-15",1,"CP-172028",null,"Lena Chaponniere, Qualcomm Incorporated","lguellec@qti.qualcomm.com","15/12/17: acronym corrected to USOS-CT as per the approved WID¦18/12/17: 0%->60¦16/3/18: 60%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",77,39,null,null,"2016-03-01","2018-03-16"]
[3192,750024,"   Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) ","FS_FRMCS_ARCH",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170269",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com ","21/3/17: added impacted TR¦7/6/17: 0%->10¦11/9/17: 10%->50¦15/12/17: 50%->100","new 23.790",75,38,null,null,"2017-03-03","2017-12-15"]
[3195,790031,"   Stage 3 of MONASTERY","MONASTERY",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","10/9/18: WID:CP-180097->CP-182202",null,79,40,null,null,"2018-03-16","2018-09-10"]
[3200,760030,"PS Data Off Phase 2 ","PS_DATA_OFF2",1,"Rel-15",null,"2017-03-02","2018-06-14",1,"SP-170246",null,"Murhammer, Leopold, Deutsche Telekom AG","leopold.murhammer@t-mobile.at",null,null,75,38,null,null,"2017-03-02","NA"]
[3203,760032,"      CT1 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C1","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","24.008; 24.301; 27.007; 24.229; 24.368; 24.167; 24.173; 24.275; 24.341; 24.390; 24.391",76,39,null,null,"2017-06-02","2018-06-07"]
[3204,760033,"      CT4 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->100","29.272; 29.274; 29.328; 29.329; 29.228; 29.229; 23.008",76,39,null,null,"2017-06-02","2017-12-15"]
[{"$f":"A3208+1","v":3208},780006,"   Stage 3 of NAPS","NAPS-CT",2,"Rel-15","C3","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90. 18/12/17: WID corrected¦18/12/17: WID:CP-171143 ->CP-173112","29.336; 29.128; 29.230",78,40,null,null,"2017-06-02","2017-12-18"]
[3211,770032,"   Security aspects of NAPS","NAPS-Sec",2,"Rel-15","S3","2017-09-08","2018-03-16",1,"SP-170635",null,"Zhao, Xuwen, Huawei","zhaoxuwen@huawei.com ","15/12/17: 0%->60¦16/3/18: 60%->100",33.186999999999998,77,39,null,null,"2017-09-08","2018-03-16"]
[3215,770041,"   Stage 2 of CAPIF","CAPIF",2,"Rel-15","S6","2017-09-08","2017-12-15",1,"SP-170798",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","15/12/17: 0%->95¦16/3/18: 95%->100","New",77,39,null,null,"2017-09-08","2018-03-16"]
[3217,780024,"   Security aspects of CAPIF","CAPIF-Sec",2,"Rel-15","S3","2017-12-15","2018-06-14",1,"SP-171051",null,"Rajavelsamy Rajadurai, Samsung","rajvel{@]samsung.com ","16/3/18: 0%->40¦7/6/18: 40%->100",null,78,40,null,null,"2017-12-15","2018-06-07"]
[3223,780037,"   Network Resource Model (NRM) for 5G networks and network slicing","NETSLICE-5GNRM",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180812",null,"Nokia (Jing Ping","jing.ping@nokia-sbell.com","16/3/18: 0%->25¦7/6/18: 25%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170956->SP-180812","28.657; 28.658; 28.659; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-10-02"]
[3226,780040,"   5G Trace management","NETSLICE-5GTRACE",2,"Rel-15","S5","2017-12-15","2018-06-07",1,"SP-170959",null,"Nokia (Anatoly Andrianov","anatoly.andrianov@nokia.com","7/6/18: 0%->100","32.421; 32.422; 32.423; 32.441; 32.442; 32.446",78,40,null,null,"2017-12-15","2018-06-07"]
[3229,810043,"      CT4 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C4","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274",81,41,null,null,"2018-09-06","2018-09-10"]
[3230,780041,"   Fault Supervision for 5G networks and network slicing","NETSLICE-FS5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180817",null,"Zhu Weihong, ZTE","zhu.weihong@zte.com.cn","16/3/18: 0%->20¦7/6/18: 20%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170961->SP-180817",28.545000000000002,78,40,null,null,"2017-12-15","2018-10-02"]
[3234,780018,"      CT1 aspects of FS_PC_VBC","FS_PC_VBC",3,"Rel-15","C1","2016-12-01","2017-12-15",1,"CP-172135",null,"Huang, Zhenning, China Mobile","huangzhenning <at> chinamobile <dot> com","15/12/17: 0%->100",29.827000000000002,74,38,null,null,"2016-12-01","2017-12-15"]
[3238,770034,"Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management","OAM_SON_AAS",1,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170658",null,"Nokia (Weixing Wang)","weixing.wang@nokia-sbell.com","15/12/17: 0%->80¦10/9/18: 80%->100","28.627; 28.628; 28.629; 28.658; 28.659",77,39,null,null,"2017-09-08","2018-09-10"]
[3243,760012,"Enhanced Calling Name Service","eCNAM",1,"Rel-15",null,"2016-09-15","2018-03-14",1,"SP-160548",null,"Hala Mowafy, Ericsson",null,"1/12/16: 0%->100",22.172999999999998,73,37,null,null,"2016-09-19","2016-12-01"]
[3245,760013,"   CT aspects of eCNAM","eCNAM-CT",2,"Rel-15","ct","2017-06-02","2018-03-14",1,"CP-171181",null,"Mowafy, Hala. Ericsson","hala.mowafy@ericsson.com",null,null,76,39,null,null,"2017-06-02","NA"]
[3249,760016,"Stage-3 SAE Protocol Development - Phase 6","SAES6",1,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","NA"]
[3252,760019,"   SAE Protocol Development (Stage 3) - Phase 6","SAES6",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,null,null,"14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100",null,72,37,null,null,"2015-03-24","2018-06-07"]
[3256,760008,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",1,"Rel-15","ct","2017-06-02","2020-04-23",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com",null,null,76,39,null,null,"2016-06-11","NA"]
[3257,760009,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C1","2017-06-02","2018-06-13",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com","14/9/17: 0%->40¦15/12/17: 40%->60¦16/3/18: 60%->80¦7/6/18: 80%->100","23.218; 24.229; 24.930",76,39,null,null,"2014-12-04","2018-06-07"]
[3260,780048,"      (IETF) P-Visited-Network header updated (was: draft-jesske-update-p-visited-network )","IMSProtoc9",3,"Rel-15","C1-IETF","2017-06-02","2018-06-15",1,null,null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","27/6/18: 0%->100",null,78,40,null,null,"2017-12-18","2018-06-27"]
[3265,750013,"   Normative work on Lawful Interception Rel-15","LI15",2,"Rel-15","S3LI","2017-03-02","2019-03-12",1,"SP-170839",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","12/7/17: 0%->5¦15/12/17: 5%->10¦10/9/18: 17%->40¦7/12/18: FCD:12/18->03/19¦7/12/18: 40%->75¦20/3/19: 75%->80; 31/5/19: 80%->100",null,75,38,null,null,"2016-07-27","2019-05-31"]
[3268,760055,"Control and monitoring of Power, Energy and Environmental (PEE) parameters in Radio Access Networks (RAN)","PEE_CMON",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170479",null,"Jean-Michel CORNILY, ORANGE",null,"30/6/17: 28.306 added;¦30/6/17: 28.305 added;¦30/6/17: 28.304 added;¦11/9/17: 0%->20¦15/12/17: 20%->80¦16/3/18: 80%->100","New TSs; 52.402; 32.405; 32.425; 32.101; 32.103; 28.306; 28.305; 28.304",76,39,null,null,"2017-06-03","2018-03-16"]
[3271,760182,"   Core part: Simplified HS-SCCH for UMTS","UTRA_simple_HSSCCH-Core",2,"Rel-15","R6","2017-06-15","2017-12-15",1,"RP-172720","RP-172306","Ericsson",null,"11/9/17: 0%->85¦15/12/17: 85%->100¦8/1/18: WID: RP-171443->RP-172720¦",null,76,39,null,null,"2017-06-16","2018-01-08"]
[3275,780032,"REST Solution Sets","REST_SS",1,"Rel-15",null,"2016-09-19","2019-09-16",1,"SP-170950",null,null,null,null,null,78,41,null,null,"2017-12-15","NA"]
[3278,800114,"   deleted - (IETF) JSON Schema: A Media Type for Describing JSON Documents (draft-handrews-json-schema)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",1,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com","16/7/24: 0%->100",null,80,41,null,null,"2018-07-10","2024-07-16"]
[3282,790029,"   CT1 aspects of eSPECTRE","eSPECTRE",2,"Rel-15","C1","2018-03-15","2018-06-14",1,"CP-180096",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","16/3/18: 0%->5; 7/6/18: 5%->50; 10/9/18: 50%->100",24.228999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[3283,800101,"   (IETF) PASSporT SHAKEN Extension (draft-ietf-stir-passport-shaken)--> RFC 8588","eSPECTRE",2,"Rel-15","C1-IETF","2018-06-14","2018-09-14",1,null,null,"Axell, Jörgen, Ericsson",null,"23/4/20: 25%->100",null,80,41,null,null,"2018-06-27","2020-04-23"]
[3287,800102,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (draft-ietf-tls-tls13)","TEI15",2,"Rel-15","S3-IETF","2017-03-17","2018-06-15",1,null,null,null,null,"26/6/19: 25%->100; 9/4/21: RFC 8446 added;","RFC 8446",80,41,null,null,"2018-06-27","2021-04-09"]
[3291,770167,"   Core part: UL data compression in LTE ","LTE_UDC-Core",2,"Rel-15","R2","2000-01-03","2018-09-14",0.99,"RP-180914","RP-180912","CATT",null,"¦8/1/18: Compl:0%->70%¦8/1/18: CD:Mon 03/01/00->Thu 15/03/18¦27/3/18: Compl:70%->99%27/3/1 ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18;",null,77,39,null,null,"2017-09-19","2018-06-27"]
[3294,770168,"   Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Core",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"15/12/17: 36.715-04 added;¦8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%;","36.715-04",77,39,null,null,"2017-09-19","2018-03-27"]
[3297,770169,"   Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-Core",2,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-180262",null,"Ericsson",null,"¦8/1/18: Compl:0%->99%27/3/18: WID: RP-172077->RP-180262¦27/6/18: Compl:99%->100%",null,77,39,null,null,"2017-09-19","2018-06-27"]
[3300,770070,"Additional LTE bands for UE category M2 and/or NB2 in Rel-15","LTE_bands_R15_M2_NB2",1,"Rel-15","R4","2017-09-15","2018-12-14",1,"RP-172078",null,"Ericsson",null,null,null,77,39,null,null,"2017-09-19","NA"]
[3305,710073,"Stopped - Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON",1,"Rel-15",null,"2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459",null,71,36,80,null,"2016-03-22","2017-09-14"]
[3306,710173,"   Stopped - Core part: Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON-Core",2,"Rel-15","R2","2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/12/16->Wed 15/03/17¦1/7/16: WID: RP-160540->RP-16093726/9/16: Compl:10%->30%¦20/12/16: Compl:30%->75%¦20/12/16: Stat Rep: --> 21/3/17: Compl:75%->79% 21/3/17: CD:W ¦27/6/",null,71,36,80,null,"2016-03-22","2018-06-27"]
[3309,740046,"      Stopped - CT1 aspects of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",3,"Rel-15","C1","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->25¦11/9/17: 25%->0","24.008; 24.301; 29.118; 24.368; 27.007",74,38,80,null,"2016-12-01","2017-09-11"]
[3313,710174,"   Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA-Core",2,"Rel-15","R4","2016-03-15","2017-12-15",1,"RP-171745","RP-172345","Huawei",null,"follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/1726/9/16: Compl:5%->10% 20/12/16: Compl:10%->20%21/3/17: Compl:20%->40% ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3317,720291,"   Perf. part: Shortened TTI and processing time for LTE","LTE_sTTIandPT-Perf",2,"Rel-15","R4","2016-09-14","2018-09-14",1,"RP-171468",null,"Ericsson",null,"¦26/9/16: WID: RP-161299->RP-161922¦20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113¦19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%¦27/6/18: Compl:33%->60%¦26/3/19: 60%->100",null,72,37,null,null,"2016-07-01","2019-03-26"]
[3320,740172,"   Core part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-162514",null,"Airbus",null,"21/3/17: Compl:0%->10%¦19/6/17: Compl:10%->75%¦19/9/17: Compl:75%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3322,770065,"   UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72)","LTE450_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180528",null,"Airbus",null,"¦8/1/18: Compl:0%->77%¦27/3/18: Compl:77%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3328,740175,"   Core part: FDD operating band in the L-band for LTE","LTE_FDD_L_Band-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171403",null,"NTT DOCOMO",null,"21/3/17: Compl:0%->50%¦19/6/17: Compl:50%->99%¦19/9/17: Compl:99%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3331,740076,"LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext",1,"Rel-15",null,"2016-12-15","2017-09-15",1,"RP-162556",null,"Qualcomm",null,"21/3/17: 36.934 added;¦21/3/17: 36.753 added;","36.934; 36.753",74,38,null,null,"2016-12-20","2017-03-21"]
[3332,740176,"   Core part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"21/3/17: Compl:0%->20%19/6/17: Compl:20%->50%;19/9/17: Compl:50%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3335,740177,"   Core part: Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-Core",2,"Rel-15","R4","2016-12-15","2017-12-15",1,"RP-172295",null,"Sprint",null,"21/3/17: Compl:0%->5%¦19/6/17: Compl:5%->50%¦19/9/17: Compl:50%->90%¦8/1/18: Compl:90%->100%;",null,74,38,null,null,"2016-12-20","2018-01-08"]
[3339,740080,"TDD operating band in the L-band for LTE","LTE_TDD_L_Band",1,"Rel-15",null,"2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: 36.753 added;¦14/9/17: WID:RP-162557->RP-170304",36.753,74,38,null,null,"2016-12-20","2017-09-14"]
[3343,750160,"   Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-180584","RP-180318","Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75¦19/6/17: Compl:0%->70%¦19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%¦27/3/18: Compl:90%->99%¦27/3/18: CD:Thu 15/03/18->Fri ¦27/6/18: CD:Fri",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3348,750064,"Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL",1,"Rel-15","R1","2016-09-14","2018-12-14",0.99,"RP-171067",null,"Huawei",null,"14/9/17: WID:RP-170838->RP-171067",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3350,750264,"   Perf. part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL-Perf",2,"Rel-15","R4","2016-09-14","2018-12-14",1,"RP-171740",null,"Huawei",null,"¦19/6/17: CD:Sat 15/12/18->Fri 15/06/18¦19/6/17: WID: RP-170838->RP-171067 19/9/17: WID: RP-171067->RP-17173827/3/18: Compl:0%->25%¦27/6/18: Compl:25%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3354,750069,"Further video enhancements for LTE","LTE_ViLTE_enh2",1,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170781",null,"CMCC",null,"no Perf. part¦compare REL-14 WI LTE_VoLTE_ViLTE_enh",null,75,38,null,null,"2017-03-21","2017-03-21"]
[3357,750170,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170956","RP-172192","China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core¦19/6/17: Compl:0%->25%¦19/6/17: WID: RP- 19/9/17: Compl:25%->45%¦8/1/18: Compl:45%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3361,750271,"   Perf. part: Enhancing LTE CA Utilization","LTE_euCA-Perf",2,"Rel-15","R4","2017-09-13","2018-12-14",1,"RP-180561",null,"Nokia",null,"16/3/18: FCD:12/17->12/18¦27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:0%->20%¦26/3/19: 20%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[3362,820066,"   UE Conformance Test Aspects - Enhancing LTE CA Utilization","LTE_euCA-UEConTest",2,"Rel-15","R5","2018-12-15","2021-09-08",1,"RP-182619",null,"Nokia",null,"tested: REL-15 WI LTE_euCA-Core; 8/10/20: 0%->35; 8/10/20: FCD:15/12/2019->12/20; 8/4/21: 0%->56; 8/4/21: FCD:12/12/2020->09/20; 2/7/21: 0%->82; 29/9/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-09-29"]
[3365,750273,"   Perf. part: 450 MHz Band for LTE in Region 3","LTE450_Reg3-Perf",2,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170952",null,"China Unicom",null,"¦19/6/17: WID: RP-170159->RP-170952¦8/1/18: Compl:0%->100%",null,75,38,null,null,"2017-03-21","2018-01-08"]
[3370,770060,"   UE Conformance Test Aspects - US 600 MHz Band for LTE (Band 71)","LTE600_US-UEConTest",2,"Rel-15","R5","2017-09-15","2017-12-15",1,"RP-172195",null,"Dish Network",null,"¦8/1/18: Compl:0%->100%¦",null,77,39,null,null,"2017-09-19","2018-01-08"]
[3373,750276,"   Perf. part: LAA/eLAA for the CBRS 3.5GHz band in the United States","LTE_3550_CBRS_US_LAA-Perf",2,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-172626",null,"AT&T",null,"compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2¦19/6/17: C Acronym changed, was \"LTE_TDD_3550_CBRS_US_LAA-Perf\";",null,75,38,null,null,"2017-03-21","2018-01-08"]
[3377,760098,"Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40",1,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3380,760199,"   Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171755",null,"Huawei",null,"19/9/17: Compl:0%->10%¦ 15/12/17: 36.760 added;¦8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%¦27/6/18: Comp",36.76,76,39,null,null,"2017-06-16","2018-06-27"]
[3383,761100,"   Core part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Core",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"12/7/17: 36.758 added;19/9/17: Compl:0%->10%¦ 8/1/18: Compl:10%->70%27/3/18: Compl:70%->100%;",36.758000000000003,76,39,null,null,"2017-06-16","2018-03-27"]
[3385,761001,"UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM",1,"Rel-15","R4","2017-06-15","2018-12-14",0.93,"RP-171408",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3388,780068,"Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN",1,"Rel-15","R2","2017-12-15","2019-12-15",0.98,"RP-172820",null,"CMCC",null,"MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3392,750042,"   Study on enhanced LTE Support for Aerial Vehicles","FS_LTE_Aerial",2,"Rel-15","R2","2017-03-15","2017-12-15",1,"RP-171050",null,"NTT DOCOMO",null,"TR 36.7XX19/6/17: Compl:0%->15%¦30/6/17: 36.777 added;¦19/9/17: Compl:15%->30%¦8/1/18: Compl:30%->100%",36.777000000000001,75,38,null,null,"2017-03-21","2018-01-08"]
[3396,780171,"   Core part: Separation of CP and UP for Split Option 2 of NR","NR_CPUP_Split-Core",2,"Rel-15","R3","2017-12-15","2018-06-15",1,"RP-180326","RP-181149","Ericsson",null,"follow-up WI of REL-15 SI FS_NR_CPUP_Split¦introduction of E1 interface. 30/1/18: acronym updated27/3/18: Compl:0%->30%27/3/18: WID: RP-172831->RP-180326¦27/6/18: Compl:30%->100%¦27/6/18: Stat Rep: ->RP-181149",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3399,780272,"   Perf. part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-180960",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL¦27/6/18: Compl:0%->30%¦26/3/19: 30%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3403,780074,"LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172839",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3405,780274,"   Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-181442",null,"Qualcomm",null,"basket CA WI27/3/18: CD:Sat 15/12/18->Fri 15/06/18 ¦27/6/18: Compl:0%->50%;¦16/1/19: 50%->100",null,78,40,null,null,"2018-01-08","2019-01-16"]
[3410,760090,"LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170962",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3411,760190,"   Core part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180800",null,"Ericsson",null,"12/7/17: 36.715-00-00 added;¦19/9/17: Compl:0%->25% 8/1/18: Compl:25%->70%;27/3/18: Compl:70%->67%¦ ¦27/6/18: Compl:67%->100%;","36.715-00-00",76,39,null,null,"2017-06-16","2018-06-27"]
[3414,760191,"   Core part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-181013",null,"Qualcomm",null,"12/7/17: 36.715-02-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->30%¦27/3/18: Compl:30%->40%¦ ¦27/6/18: Compl:40%->100%;","36.715-02-01",76,39,null,null,"2017-06-16","2018-06-27"]
[3419,760093,"LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170963",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3422,760094,"LTE Advanced inter-band CA Rel-15 for 5DL/1UL","LTE_CA_R15_5DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171466",null,"Nokia",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3425,760095,"LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171127",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3427,760295,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180957",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3433,580137,"   Stopped - Core part: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements","LTE_UTRA_TRP_TRS-Core",2,"Rel-15","R4","2012-12-15","2017-12-15",0.85,"RP-172035",null,"Nokia","petri.j.vasenkari@nokia.com","¦CD:Wed 18/03/15->Sun 15/03/15¦Rel-12->Rel-13¦Stat Rep: RP-141158->RP-141973 1st Apr 15: Compl:35%->40% 1st Apr 15: Stat Rep: RP-141973->RP-150104 03/07/15: Stat Rep: RP-150104->RP-150615 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150615->RP-15","25.144; New 37.144",58,30,80,null,"2012-12-10","2018-01-08"]
[3436,790153,"   Core part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Core",2,"Rel-15","R6","2018-03-15","2018-09-14",0.8,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;",null,79,40,null,null,"2018-03-27","2018-06-27"]
[3440,801203,"   Perf. Part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5","LTE_CA_R15_xDL3UL-Perf",2,"Rel-15","R4","2018-05-15","2018-05-15",1,"RP-181311",null,"KDDI",null,"Perf. Part was introduced and completed at RAN #80",null,80,41,null,null,"2018-06-27","NA"]
[3441,790055,"Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72",1,"Rel-15","R4","2018-03-15","2018-12-14",1,"RP-180178",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;",null,79,40,null,null,"2018-03-27","NA"]
[3445,0,"Release 15 Studies on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3448,750040,"Study on NR to support non-terrestrial networks","FS_NR_nonterr_nw",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171450",null,"Thales",null,"TR 38.8XX19/6/17: Compl:0%->25%19/6/17: CD:Fri 15/12/17->Thu 15/03/1819/6/17: WID: RP-170717->RP-171450¦30/6/17: 38.811 added;¦19/9/17: Compl:25%->40%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/18¦27/3/18: Compl:40%->45%¦27/6/18: Compl:4",38.811,75,38,null,null,"2017-03-21","2018-06-27"]
[3453,730070,"Study on interference cancellation receiver for LTE BS","FS_LTE_IC_BS",1,"Rel-15","R4","2016-09-15","2017-06-15",1,"RP-161485",null,"China Telecom",null,"6/10/16: 36.766 added¦20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%¦19/6/17: Compl:65%->100%",36.765999999999998,73,37,null,null,"2016-09-26","2017-06-19"]
[3456,0,"Other Release 15 Studies","-",1,"Rel-15",null,"2017-09-08","2018-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3459,710049,"Study on Energy Efficiency Aspects of 3GPP Standards","FS_ENEFF",1,"Rel-15","SP","2016-03-11","2017-06-09",1,"SP-160224","_SP-170533","Orange, Xiaobao Chen","xiaobao.chen@orange.com","28/7/16: 21.866 added;¦9/6/17: FCD:12/16->9/6/17 (Rel-14->Rel-15)¦0%->100",21.866,71,36,null,null,"2016-03-11","2017-06-09"]
[3462,710032,"Study on Enhanced Isolated E-UTRAN Operation for Public Safety","FS_IOPS_LB",1,"Rel-15","S2","2016-03-07","2016-12-15",1,"SP-160171",null,"Antoine Mouquet, Orange","antoine.mouquet@orange.com","9/6/16: 0%->6¦28/7/16: 23.798 added¦1/12/16: FCD:09/16->12/16¦1/12/16: 6%->15. 7/12/16: Moved from Rel-14 according to SP-160806.¦6/3/17: 15%->50¦7/6/17: 50%->100",23.797999999999998,71,36,null,null,"2016-03-07","2017-06-07"]
[3466,750041,"Study on scheduling enhancements with CA for UMTS","FS_UTRA_CA_sched_enh",1,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171065",null,"Huawei",null,"TR 25.7XX¦19/6/17: Compl:0%->100%¦ 12/7/17: 25.708 added;",25.707999999999998,75,38,null,null,"2017-03-21","2017-07-12"]
[3467,750050,"Study on Architecture Evolution for E-UTRAN","FS_LTE_arch_evo",1,"Rel-15","R3","2017-03-15","2018-03-15",1,"RP-172707",null,"China Unicom",null,"TR 36.8XX¦12/7/17: 36.756 added;19/9/17: Compl:0%->40%¦15/12/17: 37.876 added;¦8/1/18: Compl:40%->827/3/18: Compl:85%->100%","36.756; 37.876",75,38,null,null,"2017-03-21","2018-03-27"]
[3471,730055,"Study on Management aspects of selected IoT-related features","FS_OAM_IOT",1,"Rel-15","S5","2016-09-19","2017-12-12",1,"SP-160611",null,"Cisco Systems / Yanover, Vladimir ",null,"6/10/16: 32.857 added¦1/12/16: 0%->5¦21/3/17: moved from Rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 5%->20¦11/9/17: 20%->30¦15/12/17: 30%->45¦16/3/18: 45%->100",32.856999999999999,73,37,null,null,"2016-09-19","2018-03-16"]
[3475,730053,"Study on forward compatibility for 3GPP Diameter Charging Applications","FS_FWDCA",1,"Rel-15","S5","2016-09-19","2017-06-15",1,"SP-160608",null,"Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","6/10/16: 32.870 added¦1/12/16: 0%->10¦21/3/17: moved from rel-14¦11/9/17: 10%->40¦15/12/17: 40%->100",32.869999999999997,73,37,null,null,"2016-09-19","2017-12-15"]
[3478,720047,"Study on Management and Orchestration Architecture of Next Generation Network and Service","FS_NGNS_MOA",1,"Rel-15","S5","2016-06-13","2017-12-12",1,"SP-160400",null,"Huawei Technologies, Zou Lan","zoulan@huawei.com","28/7/16: 28.800 added¦19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 10%->25¦11/9/17: 25%->30¦15/12/17: 30%->100","xy.abc; 28.800",72,37,null,null,"2016-06-13","2017-12-15"]
[3482,710015,"STOPPED - Study on UE characteristics and performance for Video","FS_UE_VTPerf",1,"Rel-15","S4","2016-03-01","2017-06-15",1,"SP-160085",null,"Stéphane PROUST, Orange","stephane.proust@orange.com","11/6/16: 0%->10¦19/9/16: 10%->30, FCD: 12/16->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: Stopped, so 30%->100",26.931999999999999,71,36,80,null,"2016-03-01","2017-06-07"]
[3485,0,"--- RELEASE 14 ---","-",1,"Rel-14",null,"2014-12-12","2014-12-12",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3488,700029,"   Mission Critical Push to Talk over LTE Realignment ","MCImp-MCPTTR",2,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150821","SP-170406","Andrew Thiessen","andrew (at) its (dot) bldrdoc (dot) gov","2/3/16: FCD: 03/16->06/16. ES in SP-160102¦0->75%¦9/6/16: 75%->100",22.178999999999998,70,36,null,null,"2015-12-07","2016-06-09"]
[3490,720056,"      Stage 2 of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379; 23.280; 23.281; 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[3493,740025,"         CT3 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100","29.165; 29.213; 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3497,720055,"   Common functional architecture to support mission critical services","MCImp-MC_ARCH",2,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160489",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","28/7/16: 23.280 added¦19/9/16: 0%->40¦1/12/16: 40%->95¦3/3/17: 95%->100","23.280; 23.379; 23.281; 23.282; 23.280",72,37,null,null,"2016-06-13","2017-03-03"]
[3501,720051,"      Stage 2 for MCVideo","MCImp-MCVideo",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160491",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","28/7/16: 23.281 added¦19/9/16: 0%->25¦1/12/16: 25%->95¦3/3/17: 95%->100","23.281; 23.280; 23.379; 23.282; 23.281",72,37,null,null,"2016-06-13","2017-03-03"]
[3504,740034,"         CT1 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C1","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","6/3/17: 0%->25¦5/6/17: 25%->90¦14/9/17: 90%->100","24.381; 24.382; 24.383; 24.384",74,38,null,null,"2016-12-01","2017-09-14"]
[3508,720054,"   Mission Critical Data over LTE ","MCImp-MCData",2,"Rel-14",null,"2015-04-14","2017-06-14",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100",null,70,36,null,null,"2015-12-07","2016-07-28"]
[3510,700031,"      Stage 1 of MCData","MCImp-MCData",3,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100","New 22.282",70,36,null,null,"2015-12-07","2016-06-09"]
[3513,740029,"         CT1 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C1","2016-12-01","2017-06-14",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","6/3/17: 0%->10¦5/6/17: 10%->65¦5/6/17: 65%->90¦14/9/17: 90%->96¦15/12/17: 96%->100","24.381; 24.382; 24.383; 24.384",74,38,null,null,"2016-12-01","2017-12-15"]
[3516,740032,"         CT6 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C6","2016-12-01","2017-06-14",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","No work identified.","31.102; 31.103",74,38,null,null,"2016-12-01","2017-06-05"]
[3519,730008,"Protocol enhancements for MCPTT over LTE","MCPTTProtoc1",1,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","This Feature is a stage-3 only feature that fixes/enhances MCPTT protocol level (not visible from stage2). Not to be confused with Rel-14 MCPTT Stage 3.",null,73,37,null,null,"2016-09-16","2016-09-16"]
[3524,0,"Release 14 on V2X","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3527,720011,"   Architecture enhancements for LTE support of V2X services","V2XARC",2,"Rel-14","S2","2016-06-09","2016-12-15",1,"SP-160317",null,"LG Electronics, LaeYoung Kim","laeyoung.kim@lge.com","28/7/16: 23.285 added¦19/9/16: 0%->85¦1/12/16: FCD:09/16->12/16¦1/12/16: 85%->100",23.285,72,37,null,null,"2016-06-09","2016-12-01"]
[3530,720190,"      Core part: LTE-based V2X Services","LTE_V2X-Core",3,"Rel-14","R1","2016-06-15","2017-03-15",1,"RP-162519","RP-170237","LG Electronics",null,"follow-up WI of REL-14 SI FS_LTE_V2X26/9/16: Compl:0%->15%26/9/16: WID: RP-161298->RP-161894¦6/10/16: 36.786 added¦6/10/16: added¦20/12/16: Compl:15%->75% 21/3/17: Compl:75%->100%","36.786; ",72,37,null,null,"2016-07-01","2017-03-21"]
[3532,760086,"      UE Conformance Test Aspects - Support for LTE-based V2X Services","LTE_V2X-UEConTest",3,"Rel-14","R5","2017-06-15","2018-12-14",1,"RP-192556",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->40%¦ 27/3/18: Compl:40%->55%; 14/1/20: WID:RP-172356->RP-192556; 14/1/20: 65%->100",null,76,39,null,null,"2017-06-16","2020-01-14"]
[3538,700019,"   Study on LTE support for V2X services","FS_V2XLTE",2,"Rel-14",null,"2015-02-09","2016-06-17",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75","New 22.885",67,34,null,null,"2015-03-04","2015-09-07"]
[3539,670009,"      Study on Stage 1 of LTE support for V2X services","FS_V2XLTE_S1",3,"Rel-14","S1","2015-02-09","2015-02-09",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75¦7/12/15: 75%->100","New 22.885",67,34,null,null,"2015-12-07","2015-12-07"]
[3545,700261,"   Perf. part: Support for V2V services based on LTE sidelink","LTE_SL_V2V-Perf",2,"Rel-14","R4","2015-12-15","2017-06-15",1,"RP-161603",null,"LG Electronics",null,"22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-16127226/9/16: WID: RP-161272->RP-161603¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:80%->100%",null,70,36,null,null,"2016-01-01","2017-06-19"]
[3546,730073,"   UE Conformance Test Aspects - Support for V2V services based on LTE sidelink","LTE_SL_V2V-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-172358",null,"Huawei",null,"¦20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ;; 11/10/20: 98%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3550,710025,"   CT aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",2,"Rel-14",null,"2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293",null,71,36,null,null,"2016-03-02","2016-06-11"]
[3553,710027,"      CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦2/12/16: 65%->100","29.060; 29.274; 29.002; 29.303; 23.008; 29.128; 29.272; 23.007",71,36,null,null,"2016-03-02","2016-12-02"]
[3558,720093,"Enhancements of NB-IoT","NB_IOTenh",1,"Rel-14",null,"2016-06-15","2018-12-14",1,"RP-161324",null,"Huawei",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[3561,770061,"   UE Conformance Test Aspects - Enhancements of NB-IoT","NB_IOTenh-UEConTest",2,"Rel-14","R5","2017-09-15","2018-12-14",1,"RP-171781",null,"Huawei",null,"¦8/1/18: Compl:0%->5%27/3/18: Compl:5%->30%¦27/6/18: C; 11/10/20: 60%->100",null,77,39,null,null,"2017-09-19","2020-10-11"]
[3564,720081,"   Study on extended architecture support for Cellular Internet of Things","FS_CIoT_Ext",2,"Rel-14","S2","2016-06-17","2016-12-15",1,"SP-160505",null,"Intel : Puneet Jain","puneet.jain@intel.com","28/7/16: 23.730 added¦19/9/16: 0%->70¦1/12/16: FCD:03/17->12/16¦1/12/16: 70%->100",23.73,72,37,null,null,"2016-06-17","2016-12-01"]
[3567,740039,"      CT1 aspects of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",3,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","6/3/17: 0%->50¦5/6/17: 50%->100","24.301; 24.008",74,38,null,null,"2016-12-01","2017-06-05"]
[3569,730077,"Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh",1,"Rel-14","R6","2016-09-15","2018-06-15",1,"RP-161806",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3572,730083,"New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands",1,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-161890",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3576,720006,"Enhancements of Dedicated Core Networks selection mechanism","eDecor",1,"Rel-14",null,"2015-09-17","2017-12-15",1,"SP-160310","SP-170537","Roland Gustafsson","Roland.Gustafsson@ericsson.com","7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95",23.710999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[3580,730014,"      CT1 aspects of eDecor","eDecor-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100","24.301; 24.008; 24.368",73,37,null,null,"2016-09-16","2017-06-05"]
[3584,740167,"      Core part: RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE-Core",3,"Rel-14","R3","2016-12-15","2017-03-15",1,"RP-162543","RP-170547","Ericsson",null,"21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3587,740078,"Addition of band 25 and 26 to LTE MTC cat.0","LC_MTC_LTE_cat0_B25_B26",1,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162572",null,"Sprint",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[3589,740179,"Addition of bands 25 and 40 to LTE MTC cat.1","LTE_MTCe2_L1_cat1_B25_B40-Core",1,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162573",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[{"$f":"A3592+1","v":3592},700039,"   Stage 2 of EWE","EWE",2,"Rel-14","S2","2015-11-02","2016-06-17",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002; 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[3595,720033,"      CT4 aspects of EWE","EWE-CT",3,"Rel-14","C4","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com","2/12/16: 0%->100",29.273,72,37,null,null,"2016-06-13","2016-12-02"]
[3599,730045,"      CT1 aspects of ERP","ERP-CT",3,"Rel-14","C1","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com","2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100",24.302,73,37,null,null,"2016-09-16","2017-06-05"]
[3602,690033,"   Study on Phase 2 of the Support of Emergency services over WLAN","FS_SEW2",2,"Rel-14","S2","2015-09-01","2016-06-16",1,"SP-160173",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251¦7/12/15: 0%->30, FCD: 12/15->06/16¦7/3/16: 30%->75¦7/3/16: WID:SP-150251->SP-160173¦9/6/16: 75%->100","new 23.771",67,34,null,null,"2015-04-01","2016-06-09"]
[3606,730019,"      CT4 aspects of SEW2","SEW2-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 0%->100","23.003; 29.272; 29.273; 29.274; 29.328",73,37,null,null,"2016-09-16","2016-12-02"]
[3610,710175,"   Core part: Enhanced LTE-WLAN Aggregation (LWA)","LTE_WLAN_aggr-Core",2,"Rel-14","R2","2016-03-15","2017-03-15",1,"RP-160923","RP-170330","Intel",null,"follow-up WI of REL-13 WI LTE_WLAN_radio¦no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923¦26/9/16: Compl:25%->45%¦20/12/16: Compl:45%->75%¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:75%->100% ¦21/3/17",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3613,680004,"   Stage 1 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S1","2015-05-11","2015-06-19",1,"SP-150275",null,"Kurt Bischinger",null,null,22.100999999999999,68,35,null,null,"2015-06-09","2015-06-09"]
[3615,710020,"   CT aspects of evolution to and interworking with eCall in IMS","EIEI-CT",2,"Rel-14",null,"2016-03-02","2016-09-15",1,"CP-160053",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,null,71,36,null,null,"2016-03-02","2016-03-02"]
[3618,710022,"      CT6 aspects of evolution to and interworking with eCall in IMS","EIEI-CT",3,"Rel-14","C6","2016-03-02","2016-09-15",1,"CP-160053",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","16/9/16: 0%->100",31.102,71,36,null,null,"2016-03-02","2016-09-16"]
[3621,670012,"   Stage 1 for PWDIMS","PWDIMS",2,"Rel-14","S1","2015-03-11","2015-03-13",1,"SP-150041",null,"Peter Bleckert (Ericsson)",null,"1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100%",22.172999999999998,67,34,null,null,"2015-03-04","2015-07-31"]
[3624,720036,"      CT3 aspects for PWDIMS","PWDIMS-CT",3,"Rel-14","C3","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,"5/6/17: 0%->100",29.292000000000002,72,37,null,null,"2016-06-11","2017-06-05"]
[3629,651203,"   (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497","ISAT",2,"Rel-14","C4-IETF","2014-09-12","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 25%->70; 26/6/19: 70%->100","draft-dawes-sipping-debug",65,33,null,null,"2014-09-02","2019-06-26"]
[3632,0,"Other Release 14 ","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3636,750037,"   (IETF) A SIP Response Code for Unwanted Calls (draft-ietf-sipcore-status-unwanted)","SPECTRE-CT_IETF",2,"Rel-14","C1-IETF","2017-03-14","2017-03-14",1,null,null,"Ericsson",null,"18/12/17: 20%->100; 9/4/21: RFC 8197 added;","RFC 8197",75,38,null,null,"2017-03-21","2021-04-09"]
[3637,780049,"   (IETF) Authenticated Identity Management in SIP (draft-ietf-stir-rfc4474bis)","SPECTRE-CT_IETF2",2,"Rel-14","C1-IETF","2017-06-15","2018-06-15",1,null,null,"Christer Holmberg","christer.holmberg@ericsson.com","22/3/18: 0%->100; 9/4/21: RFC 8224 added;","RFC 8224",78,40,null,null,"2017-12-18","2021-04-09"]
[3643,730052,"   Mobile Network Interface for MBMS Delivery of Media and TV services","AE_enTV-MI_MTV",2,"Rel-14","S4","2016-08-22","2016-12-09",1,"SP-160731",null,"Thorsten Lohmar","Thorsten.lohmar@ericsson.com","06/10/16: Acronym: SA_enTV-MI_MTV -> AE_enTV-MI_MTV¦1/12/16: FCD:09/16->2/16¦1/12/16: 0%->50¦8/12/16: 50%->100",26.346,73,37,null,null,"2016-09-19","2016-12-08"]
[3644,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347; 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[3650,700054,"MBMS Transport Protocol and APIs","TRAPI",1,"Rel-14","S4","2015-12-11","2017-03-15",1,"SP-150851",null,"Samsung, Imed Bouazizi","i.bouazizi@samsung.com","28/1/16: 26.347 added¦7/3/16: 0%->20¦11/6/16: 20%->35¦19/9/16: 35%->60. FCD: 09/16->03/17¦1/12/16: 60%->70¦6/3/17: 70%->100","26.346; 26.852; New TS; 26.347",70,36,null,null,"2015-12-11","2017-03-06"]
[3652,721004,"Lawful Interception Rel-14","LI14",1,"Rel-14","S3LI","2016-06-15","2017-12-15",1,"SP-170038",null,"Koen JASPERS, PIDS",null,"1/12/16: 0%->10¦2/3/17: WID:SP-160375->SP-1570038¦3/3/17: 8%->15¦6/3/17: 15%->20¦9/3/17: WID:SP-1570038->SP-170038¦7/6/17: 20%->50¦11/9/17: 50%->80¦15/12/17: 80%->100",null,72,37,null,null,"2016-07-27","2017-12-15"]
[3655,780050,"   (IETF) ISUP Cause Location Parameter for the SIP Reason Header Field (draft-ietf-sipcore-reason-q850-loc) --> RFC 8606","REAS_EXT",2,"Rel-14","C1-IETF","2017-06-15","2018-06-14",1,null,null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","23/4/20: 50%->100",null,78,40,null,null,"2017-12-18","2020-04-23"]
[3658,730002,"Diameter Load Control Mechanism","DLoCMe",1,"Rel-14","ct","2014-12-03","2017-03-15",1,"CP-160645","CP-171049","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","5/12/16: WID:CP-160412->CP-160645",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3663,740012,"Diameter Base Protocol Specification Update","DBPU",1,"Rel-14",null,"2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[3666,740056,"      CT4 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.109; 29.128; 29.172; 29.173; 29.228; 29.229; 29.272; 29.273; 29.283; 29.328; 29.329; 29.336; 29.337; 29.338; 29.343; 29.344; 29.345",74,38,null,null,"2016-12-01","2017-03-06"]
[3667,740013,"   Charging aspects for Diameter Base Protocol Specification Update","DBPU-CH",2,"Rel-14","S5","2016-12-01","2017-03-10",1,"SP-160837",null,"Nokia","Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","6/3/17: 0%->100","32.240; 32.251; 32.260; 32.270; 32.271; 32.272; 32.273; 32.274; 32.275; 32.278; 32.280; 32.295; 32.296; 32.297; 32.299",74,38,null,null,"2016-12-01","2017-03-06"]
[3672,720066,"      CT3 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C3","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Acronym changed from \"MMCMH-CT\"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦6/3/17: 0%->100","29.162; 29.213; 29.214; 29.165",72,37,null,null,"2016-03-02","2017-03-06"]
[3674,750038,"      (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","MMCMH_Enh-CT",3,"Rel-14","C1-IETF","2017-03-21","2017-03-21",1,null,null,"Ericsson","tomas.frankkila@ericsson.com","23/4/20: 50%->90; 9/4/21: RFC 8853 added;","RFC 8853",75,38,null,null,"2017-03-21","2021-04-09"]
[3678,710029,"   deleted -CT3 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C3","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","29.162; 29.213; 29.214; 29.165",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3681,690052,"   Study on Control and User Plane Separation of EPC nodes","FS_CUPS",2,"Rel-14","S2","2015-09-17","2016-06-17",1,"SP-150519",null,"Huawei, Mirko Schramm","mirko.schramm@huawei.com","7/12/15: 0%->20¦7/3/16: 20%->40¦9/6/16: 40%->100",23.713999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[3685,730040,"      CT4 aspects for CUPS","CUPS-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com","2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100","23.007; 29.274; 29.281; 29.303; 23.008",73,37,null,null,"2016-09-16","2017-06-05"]
[3689,690039,"      Configuration Management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-CM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160401",null,"ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn)","zhu.weihong@zte.com.cn","5/10/15: 28.513¦28.512¦28.511¦28.510 added¦7/12/15: 0%->15¦7/3/16: 15%->20¦13/6/16: 20%->30¦19/9/16: 30%->50¦1/12/16: 50%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%->100","28.513; 28.512; 28.511; 28.510; 28.621; 28.622; 28.623; 28.704; 28.707",69,35,null,null,"2015-06-15","2017-06-07"]
[3692,690042,"      Lifecycle management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-LCM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160427",null,"Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks","anatoly.andrianov@nokia.com","5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%-","28.525; 28.526; 28.527; 28.528; 28.704; 28.705; 28.706; 28.707; 28.708; 28.709",69,35,null,null,"2015-06-15","2017-06-07"]
[3694,670028,"   Study on OAM support for Licensed Shared Access (LSA)","FS_OAM_LSA",2,"Rel-14","S5","2015-03-12","2016-03-11",1,"SP-150056",null,"Nokia Networks, Anatoly Andrianov","anatoly<dot>andrianov<at>nokia<dot>com","June2015: Compl:0%->15¦07/09/15: 15%->70¦7/12/15: 70%->75¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14¦28/7/16: 28.303 added¦28/7/16: 28.302 added¦28/7/16: 28.301 added¦28/7/16: 33.250 added¦28/7/16: added;","28.303; 28.302; 28.301; ",67,34,null,null,"2015-03-12","2016-07-28"]
[3697,670004,"Enhancing Location Capabilities for Indoor and Outdoor Emergency Communications","ELIOT",1,"Rel-14","S1","2015-03-11","2015-12-15",1,"SP-150044","SP-170553","Greg Schumacher","Gregory.schumacher@sprint.com","1/4/15: rapporteur added, Impacted TS added¦June2015: Compl:0%->25¦07/09/15: 25%->80¦2/3/16: 80%->100","22.101; 22.071",67,34,null,null,"2015-03-04","2016-03-02"]
[3700,720080,"PS Data Off Services","PS_Data_Off",1,"Rel-14",null,"2015-11-09","2017-06-09",1,"SP-150823","SP-170708","Orange, Bruno Tossou","bruno.tossou@orange.com","2/3/16: 0%->100",22.03,70,36,null,null,"2015-12-07","2016-03-02"]
[3704,740041,"   Stage 3 of PS Data Off","PS_DATA_OFF-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,null,null,"2016-12-01","NA"]
[3707,740044,"      CT6 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/3/17: 0%->100","31.102; 31.103; 31.111",74,38,null,null,"2016-12-01","2017-03-07"]
[3712,680003,"   Study on enhancement to FMSS for Rel 14","FS_eFMSS",2,"Rel-14","S1","2015-05-11","2015-12-16",1,"SP-150280",null,"Lu Lu, China Mobile","lulu@chinamobile.com","7/12/15: 70%->100",22.808,68,35,null,null,"2015-06-09","2015-12-07"]
[3715,710010,"Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",1,"Rel-14",null,"2016-03-01","2016-12-01",1,"SP-160081","SP-170515","Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10",26.222999999999999,71,36,null,null,"2016-03-01","2016-06-11"]
[3716,721005,"   S4 aspects of Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",2,"Rel-14","S4","2016-03-01","2016-12-01",1,"SP-160081",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100",26.222999999999999,72,37,null,null,"2016-03-01","2016-12-01"]
[{"$f":"A3720+1","v":3720},800105,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8850 added;","RFC 8850",80,41,null,null,"2018-06-27","2021-04-09"]
[3723,800108,"      (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8847 added;","RFC 8847",80,41,null,null,"2018-06-27","2021-04-09"]
[3726,800111,"      (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8864 added;","RFC 8864",80,41,null,null,"2018-06-27","2021-04-09"]
[3729,710048,"S8 Home Routing Architecture for VoLTE","V8",1,"Rel-14",null,"2015-06-18","2017-06-09",1,"SP-160315","SP-170522",null,null,"Umbrella, created by MCC to group SA2 and SA3 activities",null,71,36,null,null,"2016-03-11","2016-03-11"]
[3734,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[3738,690050,"   Study on improvement of awareness of user location change","FS_AULC",2,"Rel-14","S2","2015-09-17","2016-06-17",1,"SP-150517",null,"Yang Xu","xuyang49@chinaunicom.cn","7/12/15: 0%->40¦7/3/16: 40%->70¦9/6/16: 70%->100",23.71,69,35,null,null,"2015-09-17","2016-06-09"]
[3742,730036,"      CT4 Aspect of AULC","AULC-CT",3,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->95¦6/3/17: 95%->100",29.274000000000001,73,37,null,null,"2016-09-16","2017-03-06"]
[3745,700040,"   Study on Service Domain Centralization","FS_SeDoC",2,"Rel-14","S2","2015-11-02","2016-09-15",1,"SP-160306",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com","Comes back from previous release¦28/1/16: 23.719 added¦7/3/16: 0%->30¦7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70¦11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16¦1/12/16: 70%->100",23.719000000000001,70,36,null,null,"2015-12-07","2016-12-01"]
[3746,730044,"   Service Domain Centralization","SeDoC",2,"Rel-14","S2","2016-08-16","2016-09-19",1,"SP-160675",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com","19/9/16: 0%->100","23.292; 23.167",73,37,null,null,"2016-09-19","2016-09-19"]
[3749,720024,"   Sponsored data connectivity improvements","SDCI",2,"Rel-14","S2","2016-06-13","2016-09-15",1,"SP-160309",null,"Yang Xu","xuyang49@chinaunicom.cn","19/9/16: 0%->100","23.203; 23.682",72,37,null,null,"2015-12-07","2016-09-19"]
[3755,720073,"   SAE Protocol Development (Stage 3) - Phase 5","SAES5",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,null,null,"Added following CT1's chair e-mail 14/06/16¦16/9/16: 0%->20¦2/12/16: 20%->85¦6/3/17: 85%->100",null,72,37,null,null,"2015-03-24","2017-03-06"]
[3757,700043,"   Study on group based enhancements in the network capability exposure functions","FS_GENCEF",2,"Rel-14","S2","2015-11-02","2016-06-10",1,"SP-160311",null,"Samsung, Sung Hwan Won","sunghwan.won@samsung.com","28/1/16: 23.773 added¦28/1/16: 23.742 added¦7/3/16: 0%->10¦9/6/16: 10%->100","23.xyz; 23.773; 23.742",70,36,null,null,"2015-12-07","2016-06-09"]
[3760,700044,"   Study on Robust Call Setup for VoLTE subscriber in LTE","FS_RobVoLTE",2,"Rel-14","S2","2015-11-02","2016-06-10",1,"SP-150632",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com","28/1/16: 23.750 added¦7/3/16: 0%->20¦9/6/16: 20%->100","23.8xx; 23.750",70,36,null,null,"2015-12-07","2016-06-09"]
[3764,730178,"      Core part: Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh-Core",3,"Rel-14","R2","2016-09-15","2017-03-15",1,"RP-161856","RP-170323","CMCC",null,"¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170323",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3768,720037,"Improved operator control using new UE configuration parameters","IOC_UE_conf",1,"Rel-14",null,"2016-06-13","2017-03-15",1,"CP-160828","CP-171176","Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦17/10/16: WID:CP-160296->CP-160374¦5/12/16: WID:CP-160374->CP-160828","24.167; 24.229; 24.301; 24.302; 24.312; 24.341; 24.368; 24.607; 24.623; 24.XXX; 24.YYY",72,37,null,null,"2016-06-11","2016-12-05"]
[3771,720001,"Shared Subscription Data Update","eSDU",1,"Rel-14","C4","2016-06-13","2016-12-15",1,"CP-160644","CP-171050","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","13/6/16: 0%->25¦2/12/16: 25%->100¦5/12/16: WID:CP-160243->CP-160644","29.272; 29.002; 29.305; 29.230",72,37,null,null,"2016-06-13","2016-12-05"]
[3772,710012,"Rel-14 Charging","CH14",1,"Rel-14","S5","2016-03-01","2017-06-09",1,"SP-160021",null,null,null,"Umbrella Feature",null,71,36,null,null,"2016-03-01","2016-03-01"]
[3777,720045,"   Determination of Completeness of Charging Information in IMS","CH14-DCCII",2,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160398","SP-170344","Jesske, Roland (Deutsche Telekom)",null,"19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦7/6/17: 10%->100","32.240; 32.260; 32.298; 32.299",72,37,null,null,"2016-06-13","2017-06-07"]
[3780,740021,"      CT3 Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160697",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","8/6/17: 0%->100",29.164999999999999,74,38,null,null,"2016-12-01","2017-06-08"]
[3783,700260,"   Perf. part: Enhanced LAA for LTE","LTE_eLAA-Perf",2,"Rel-14","R4","2015-12-15","2017-09-15",1,"RP-162235",null,"Ericsson",null,"22/3/16: WID: RP-152272->RP-160407¦1/7/16: WID: RP-160407->RP-16088126/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160881->RP-161832¦20/12/16: WID: RP-161832->RP-162235;21/3/17: Compl:0%->33%¦19/6/17: Compl:33%->50%¦ ;",null,70,36,null,null,"2016-01-01","2017-09-19"]
[3786,700162,"   Core part: RRC optimization for UMTS","UTRA_RRCopt-Core",2,"Rel-14","R2","2015-12-15","2016-09-15",1,"RP-160287","RP-172758","Ericsson",null,"22/3/16: Compl:0%->8%¦ 1/7/16: Compl:8%->70%26/9/16: Compl:70%->100%¦8/1/18: Stat Rep: ->RP-172758",null,70,36,null,null,"2016-01-01","2018-01-08"]
[3790,700177,"   Core part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Core",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"¦22/3/16: Compl:0%->60%¦1/7/16: Compl:60%->100%¦1/7/16: CD:Th",36.749000000000002,70,36,null,null,"2016-01-01","2016-07-01"]
[3794,700178,"   Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3","LTE_1980_2170_REG3-Core",2,"Rel-14","R4","2015-12-15","2015-12-15",0,"RP-152238",null,"KT Corp.",null,null,null,70,36,null,null,"2016-01-01","2015-12-22"]
[3797,760083,"   UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs-UEConTest",2,"Rel-14","R5","2017-06-15","2017-09-15",1,"RP-170931",null,"Dish Network",null,"¦19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[3799,700179,"   Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Core",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378¦1/7/16: Compl:40%->100%;",36.857999999999997,70,36,null,null,"2016-01-01","2016-07-01"]
[3802,700080,"Multi-Band Base Station testing with three or more bands","MB_BS_test_3B",1,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-152205",null,"Alcatel-Lucent",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3806,700181,"   Core part: Performance enhancements for high speed scenario in LTE","LTE_high_speed-Core",2,"Rel-14","R4","2015-12-15","2016-12-15",1,"RP-160172","RP-162222","NTT DOCOMO",null,"22/3/16: Compl:0%->5%22/3/16: WID: RP-152263->RP-160172¦1/7/16: Compl:5%->25%26/9/16: Compl:25%->45%20/12/16: Compl:45%->100%20/12/16: Stat Rep: ->RP-162222",null,70,36,null,null,"2016-01-01","2016-12-20"]
[3809,710072,"Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2",1,"Rel-14","R2","2016-03-15","2017-12-15",1,"RP-160538",null,"Huawei",null,"follow-up WI of REL-13 WI UTRA_LTE_iPos_enh",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3812,750053,"   UE Conformance Test Aspects - RAT Independent Further Indoor Positioning Enhancements for LTE","LTE_iPos_enh2_RI-UEConTest",2,"Rel-14","R5","2017-03-15","2017-12-15",1,"RP-172317",null,"NextNav",null,"tested: REL-14 UTRA_LTE_iPos_enh2-Core (but only RAT independent aspects for LTE);¦ ;",null,75,38,null,null,"2017-03-21","2018-01-08"]
[3817,710177,"   Core part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160623","RP-170173","Samsung",null,"¦1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->80%¦20/12/16: Stat Rep: -->¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170173",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3820,710078,"Further mobility enhancements in LTE","LTE_eMob",1,"Rel-14","R2","2016-03-15","2017-06-15",1,"RP-160636",null,"ZTE",null,"no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[3821,710178,"   Core part: Further mobility enhancements in LTE","LTE_eMob-Core",2,"Rel-14","R2","2016-03-15","2017-03-15",1,"RP-162503","RP-170369","ZTE",null,"no Perf. part¦1/7/16: Compl:0%->25%¦1/7/16: WID: RP-160636->RP-160921¦26/9/16: Compl:25%->50%¦20/12/16: Compl:50%->90%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/1721/3/17: Compl:90%->100%¦21/3/17: St",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3825,710279,"   Perf. part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-162488",null,"Ericsson",null,"¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->;21/3/17: Compl:0%->20%19/6/17: Compl:20%->75%¦19/9/17: Compl:75%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3828,710180,"   Core part: L2 latency reduction techniques for LTE","LTE_LATRED_L2-Core",2,"Rel-14","R2","2016-03-15","2016-09-15",1,"RP-160667","RP-172559","Ericsson",null,"no Perf. part¦follow-up WI of SI FS_LTE_LATRED¦1/7/16: Compl:0%->80%¦26/9/16: Compl:80%->100%8/1/18: Stat Rep: -->RP-172559",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3832,710281,"   Perf. part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3834,710182,"   Core part: SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-Core",2,"Rel-14","R1","2016-03-15","2016-12-15",1,"RP-160935","RP-162137","Huawei",null,"1/7/16: Compl:0%->35%1/7/16: WID: RP-160676->RP-160935¦26/9/16: Compl:35%->55%¦20/12/16: Compl:55%->100%¦20/12/16: Stat Rep: -->RP-162137",null,71,36,null,null,"2016-03-22","2016-12-20"]
[3839,710284,"   Perf. part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-161019",null,"MediaTek",null,"1/7/16: WID: RP-160680->RP-161019¦26/9/16: CD:Fri 15/09/17->Thu 15/06/17¦20/12/16: Stat Rep: --> ¦21/3/17: Compl:0%->25%19/6/17: Compl:25%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3843,800112,"   (IETF) Session Description Protocol (SDP) Offer/Answer Considerations for Datagram Transport Layer Security (DTLS) and Transport Layer Security (TLS) (draft-ietf-mmusic-dtls-sdp)","IMSProtoc8",2,"Rel-14","C1-IETF","2016-06-14","2017-03-15",1,"CP-160294",null,"Alcatel-Lucent","Keith Drage","23/4/20: 25%->90; 9/4/21: RFC 8842 added;; 16/7/24: 90%->100","RFC 8842",80,41,null,null,"2018-06-27","2024-07-16"]
[3847,720194,"   Core part: Multi-Carrier Enhancements for UMTS","UTRA_MCe-Core",2,"Rel-14","R2","2016-06-15","2016-12-15",1,"RP-162453","RP-162129","Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe¦26/9/16: Compl:0%->35%¦20/12/16: Compl:35%->100%;",null,72,37,null,null,"2016-07-01","2016-12-20"]
[{"$f":"A3848+1","v":3848},720095,"Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US",1,"Rel-14","R4","2016-06-15","2017-06-15",1,"RP-161219",null,"Nokia",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[3851,740069,"   UE Conformance Test Aspects – Citizens Broadband Radio Service (CBRS) 3.5GHz Band for LTE in the United States (Band 48)","LTE_TDD_3550_CBRS_US-UEConTest",2,"Rel-14","R5","2016-12-15","2017-06-15",1,"RP-162254",null,"Nokia",null,"21/3/17: Compl:0%->60% ¦ 19/6/17: Compl:60%->100%",null,74,38,null,null,"2016-12-20","2017-06-19"]
[3854,720296,"   Perf. part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[3860,721203,"   Perf. part: Positioning Enhancements for GERAN","ePOS_GERAN-Perf",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052",null,"Ericsson",null,"¦20/12/16: Compl:0%->50% ¦21/3/17: Compl:50%->80%¦19/6/17: Compl:80%->100%¦",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3862,660037,"   Study on KQIs for Service Experience","FS_KQISE",2,"Rel-14","S5","2014-12-03","2016-03-11",1,"SP-150676",null,"Li, Hui (hui.li(at)huawei.com)","hui.li(at)huawei.com","Mar 15: 0->5%¦June2015: Compl:0%->40¦07/09/15: 40%->50¦14/09/15: WID:SP-140784->SP-150405¦7/12/15: 50%->75¦7/12/15: WID:SP-150405->SP-150676 ¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14","32.8xy",66,34,null,null,"2014-12-04","2016-03-22"]
[3865,730080,"Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID",1,"Rel-14","R3","2016-03-15","2017-03-15",1,"RP-161896",null,"China Telecom",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3869,730184,"   Core part: 4 receiver (RX) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL)","LTE_4Rx_AP_DL_CA-Core",2,"Rel-14","R4","2016-09-15","2016-12-15",1,"RP-161897","RP-162059","Ericsson",null,"¦20/12/16: Compl:0%->100%¦20/12/16: Stat Rep: ->RP-162059",null,73,37,null,null,"2016-09-26","2016-12-20"]
[3873,750058,"      UE Conformance Test Aspects - 4 Rx antenna ports with CA for LTE DL","LTE_4Rx_AP_DL_CA-UEConTest",3,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170704",null,"Ericsson",null,"tested: REL-14 LTE_4Rx_AP_DL_CA-Core¦19/6/17: C 1 8/1/18: C 27/3/ ;¦26/3/19: 90%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[3874,730085,"Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX",1,"Rel-14","R4","2016-09-15","2018-09-14",1,"RP-161898",null,"Qualcomm",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3877,760085,"   UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE","LTE_UE_cat_1RX-UEConTest",2,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-180263",null,"Qualcomm",null,"¦19/9/17: Compl:0%->5%¦8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%;; 11/10/20: 80%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3882,710283,"   Perf. part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912",null,"Intel",null,"1/7/16: WID: RP-160678->RP-1609121/7/16: Release: Rel-15->Rel-14¦20/12/16: Stat Rep: -->¦20/12/16: Release: Rel-15->Rel-14 21/3/17: Compl:0%->20% 21/3/17: Release: Rel19/6/17: Compl:20%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3885,780051,"Miscellaneous IETF dependencies","TEI14_IETF",1,"Rel-14",null,"2017-03-15","2020-06-05",1,null,null,null,null,"Created upon demand of RAN5",null,78,40,null,null,"2017-12-18","NA"]
[3888,780053,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel)","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-12-14",1,null,null,null,null,"was (IETF) T.140 Text Conversation over Data Channels (draft-schwarz-mmusic-t140-usage-data-channel); 9/4/21: RFC 8865 added;","RFC 8865",78,40,null,null,"2017-12-18","2021-04-09"]
[3891,870069,"   (IETF) Indicating Exclusive Support of RTP/RTCP Multiplexing using SDP (draft-ietf-mmusic-mux-exclusive) ","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,"9/4/21: RFC 8858 added;","RFC 8858",87,44,null,null,"2020-04-23","2021-04-09"]
[3896,620262,"   Security Assurance Specification for 3GPP network product classes","SCAS-SA3",2,"Rel-14","S3","2013-12-13","2017-06-15",1,"SP-150716","-","China Mobile","Judy Zhu (zhuhongru@chinamobile.com)","June2015: 0%->5¦7/12/15: 5%->72.¦10/12/15: WID:SP-130718->SP-150716¦7/3/16: 72%->75¦28/7/16: 33.250 added¦19/9/16: 75%->90. FCD set to 12.16 (was 03/16). 6/3/17: moved from Rel-14.¦15/2/18: moved back to Rel-14¦6/8/18: 33.515 added;","New 33.116; 33.117; 33.250; 22.511; 22.512; 22.513; 22.514; 33.515",62,32,null,null,"2013-11-22","2018-08-06"]
[3899,709998,"Rel-14 LTE Carrier Aggregation","LTE_CA_Rel14",1,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[3900,690086,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[3904,690187,"      Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12-Core",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3907,690188,"      Core part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12-Core",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[3911,700169,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL","LTE_CA_R14_5DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170143",null,"Nokia Networks",null,"28/1/16: 36.714-05-01 added¦22/3/16: Compl:0%->15%¦22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%¦26/9/16: Compl:40%->60%¦20/12/16: Compl ¦21/3/17","36.714-05-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3914,700170,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-170123",null,"Qualcomm",null,"28/1/16: 36.714-02-01 added¦22/3/16: Compl:0%->20%¦22/3/16: WID: RP-152196->RP-160616¦1/7/16: Compl:20%->30%¦1/7/16: WI26/9/16: Compl:30%->50%¦20/12/16: Com 21/3/17: ","36.714-02-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3917,700171,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192¦1/7/16: Compl:20%->40%¦26/9/16: Compl:40%->60%¦20/12/16: C ¦21/3/17:","36.714-02-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3922,700073,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.48,"RP-152246",null,"LG Electronics",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3925,700074,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-152249",null,"Ericsson",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[3926,700174,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%¦26/9/16: Compl:38%->74%¦20/12/16: Compl:74%->9521/3/1","36.714-04-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3930,700275,"      Perf. part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"¦22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-16082226/9/16: WID: RP-160822->RP-161473¦20/12/16: Compl:50%->64% 21/3/17: Compl:64%->",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3933,700276,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170309",null,"Huawei",null,"22/3/16: WID: RP-152278->RP-160582¦1/7/16: WID: RP-160582->RP-160945¦26/9/16: WID: RP-160945->RP-161674¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->90%;",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[3937,700058,"Study on Scenarios and Requirements for Next Generation Access Technologies","FS_NG_SReq",1,"Rel-14","RP","2015-12-15","2016-12-15",1,"RP-160811",null,"CMCC",null,"22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%¦14/12/16: FCD:09/16->12/16¦14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re","38.xxx",70,36,null,null,"2016-01-01","2016-12-20"]
[3939,610032,"Study on need for Multiple Access Point Names","FS_MAPN",1,"Rel-14","S1","2013-09-12","2015-06-19",1,"SP-130416",null,"Giesecke & Devrient","Ilario.macchi@gi-de.com","SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%¦June2015: Compl:90%->100",22.802,61,31,null,null,"2013-08-26","2015-06-15"]
[3945,670041,"Study on Latency reduction techniques for LTE","FS_LTE_LATRED",1,"Rel-14","R2","2015-03-16","2016-06-15",1,"RP-150465",null,"Ericsson",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%;",36.881,67,34,null,null,"2015-04-01","2016-07-01"]
[3948,720085,"Stopped - Study on SON for eCoMP for LTE","delFS_LTE_SON_eCOMP",1,"Rel-14","R3","2016-06-14","2016-06-16",1,"RP-161181",null,"Nokia",null,"26/9/16: Compl:0%->10%. 1/12/16: Deleted: 720085 was allocated twice: to FS_LTE_SON-ECOMP (now in 720063) and to ROBVOLTE (now in 720301)","23.228; 23.237",72,37,80,null,"2015-12-07","2016-09-26"]
[3952,710057,"Study on enhancement of VoLTE","FS_LTE_eVoLTE",1,"Rel-14","R2","2016-03-15","2016-09-15",1,"RP-160902","-","CMCC",null,"1/7/16: Compl:0%->75%1/7/16: WI¦28/7/16: 36.750 added¦26/9/16: Compl:75%->100%",36.75,71,36,null,null,"2016-03-22","2016-09-26"]
[3953,710058,"Study on HSPA and LTE Joint Operation","FS_UTRA_LTE_JOP",1,"Rel-14","R3","2016-03-15","2016-12-15",1,"RP-160571",null,"China Unicom",null,"¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦","New 37.805",71,36,null,null,"2016-03-22","2016-12-20"]
[3956,710061,"Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","FS_feCOMP_LTE",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160954",null,"Intel",null,"¦1/7/16: Compl:0%->15%¦26/9/16: Compl:15%->30%¦20/12/16: Compl:30%->80%21/3/17: Compl:80%->100%",null,71,36,null,null,"2016-03-22","2017-03-21"]
[3960,720027,"Study on MBMS Extensions for Provisioning and Content Ingestion","FS_xMBMS",1,"Rel-14","S4","2016-06-13","2017-03-10",1,"SP-160275",null,"Kyungmo Park, sk telecom","kyungmo.park@sk.com","28/7/16: 26.981 added¦19/9/16: 0%->30¦1/12/16: 30%->50¦1/12/16: FCD:12/16->03/17¦6/3/17: 50%->100",26.981000000000002,72,37,null,null,"2016-06-11","2017-03-06"]
[3965,670008,"   General aspects of FS_SMARTER SA1","FS_SMARTER",2,"Rel-14","S1","2015-02-02","2016-02-12",1,"SP-150142",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","7/12/15: 60%->85¦2/3/16: 85%->95¦7/6/17: 95%->100","New 22.891",67,34,null,null,"2015-03-04","2017-06-07"]
[3967,700024,"   FS_SMARTER – Critical Communications","FS_SMARTER-CRIC",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150818",null,"Kanerva, Mikko","mikko.kanerva@nokia.com","2/3/16: 15%->60¦9/6/16: 60%->95¦7/6/17: 95%->100","New 22.862",70,36,null,null,"2015-12-07","2017-06-07"]
[3971,710062,"Study on New Radio (NR) Access Technology","FS_NR_newRAT",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-170379",null,"NTT DOCOMO",null,"includes RAN TR 38.801¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160671->RP-161214¦1/7/16: Release: Rel-15->Rel-14¦28/7/16: 38.802 added¦26/9/16: Compl:10%->20%¦26/9/16: WID: RP-161214->RP-161596. 2/12/16: Moved","38.801; 38.912; 38.802; 38.901; 38.805",71,36,null,null,"2016-03-22","2017-03-21"]
[3974,640142,"   Study on Application Architecture to support MCPTT","MCPTT",2,"Rel-13","S6","2014-06-23","2015-09-16",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435. Dec.14: 2->20%. Mar 15: WID: SP-140879->SP-150095. Mar15: 30%. Transferred to SA6. June 15: FCD shifted to Sept,WID updated¦June2015: Compl:24%->50¦June2015: Compl:50%->70. 3/8/15: Rapp","New 23.779",64,33,null,null,"2014-06-04","2015-09-07"]
[3978,620164,"   Stage 1 for MCPTT","MCPTT",2,"Rel-13","S1","2013-12-11","2014-12-12",1,"SP-150356","SP-140502","NIST","david.cypher@nist.gov","SP#65 completion 09/14=>12/14. Exception in SP-140502. TS 22.179v100 for Information. Completed. Mar 15: WID: SP-140879->SP-150164. 6/15: WID updated","New 22.179",62,32,null,null,"2013-11-26","2015-06-18"]
[3979,640143,"   Functional architecture and information flows to support MCPTT","MCPTT",2,"Rel-13","S6","2015-06-18","2015-12-11",1,"SP-150356","-","Yannick Lair","yannick.lair@lge.com","June2015: added as per SP-150356¦June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID¦07/09/15: 15%->50¦07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15¦7/3/16: 85%->100","New 23.179",64,33,null,null,"2014-06-04","2016-03-07"]
[3982,690011,"   MCPTT protocol aspects","MCPTT-CT",2,"Rel-13","ct","2015-09-07","2016-06-30",1,"CP-150793",null,"Keith Drage, Alcatel-Lucent",null,"7/12/15: WID:CP-150587->CP-150793¦28/1/16: 24.384 added;",null,69,35,null,null,"2015-09-07","2016-01-28"]
[3987,690099,"         Floor Control – Off Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->85¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 85%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.38,69,35,null,null,"2015-09-29","2016-12-05"]
[3990,691002,"         Identity management","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.382000000000001,69,35,null,null,"2015-09-29","2016-12-05"]
[3993,690028,"      CT3 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-160817",null,"Alcatel-Lucent, Keith Drage","keith.drage@alcatel-lucent.com","7/12/15: 0%->70¦7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150643¦7/3/16: 70%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",29.164999999999999,69,35,null,null,"2015-09-07","2016-12-05"]
[3996,710034,"      (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",1,"CP-160817",null,"Ericsson","christer.holmberg@ericsson.com","5/12/16: WID:CP-160160->CP-160817","draft-holmberg-dispatch-mcptt-rp-namespace",71,36,null,null,"2016-03-07","2016-12-05"]
[4001,670031,"   Deleted (duplicated): Application Architecture to support MCPTT","MCPTT",2,"Rel-13","S6","2015-03-13","2015-03-13",1,"SP-150356",null,"U.S. Department of Commerce","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated. 7/15: removed since duplicates 640143 and 660054 (only 640143 is kept)",null,67,34,"SP-69",null,"2015-03-13","2015-07-31"]
[4004,670090,"   TR on Profiling and Extensions of MBMS","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100","new 26.852",67,34,null,null,"2015-04-08","2015-12-07"]
[4005,670091,"   Specification of MBMS Extensions and Profiling","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100",26.346,67,34,null,null,"2015-04-08","2015-12-07"]
[4009,690047,"   Security aspects for Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S3","2015-09-16","2015-12-30",1,"SP-150463",null,"General Dynamics","paul.piggin@gd-ms.uk","07/09/15: 0%->100¦11/12/15: 0%->100",33.401000000000003,63,32,null,null,"2014-02-05","2015-12-11"]
[4013,650018,"Enhanced Calling Information Presentation","ECIP",1,"Rel-13","S1","2014-09-15","2015-12-16",1,"SP-140513","S1-143311","China Mobile","LI Xiaofan (lixiaofan@chinamobile.com","SP#65 approved WID & completed. Triggered by Rel-13 TR 22.810. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067. 31/07/15: 100%","22.182 (CAT); 22.183 (CRS) ",62,32,null,null,"2013-11-26","2015-07-31"]
[4016,660002,"   Flexible Mobile Service Steering TR Phase","FMSS-SA2TR",2,"Rel-13","S2","2014-12-12","2015-06-17",1,"SP-140703",null,"Lu Lu, China Mobile","lulu@chinamobile.com","3/3: TR number added.Mar15: 15->20%¦June2015: Compl:20%->85¦07/09/15: 85%->100",23.718,66,34,null,null,"2014-12-03","2015-09-07"]
[4018,690024,"   CT3 Aspect of Flexible Mobile Service Steering","FMSS-CT",2,"Rel-13","C3","2015-09-09","2016-03-11",1,"CP-150799",null,"ZTE,Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100","29.abc; 29.212; 29.213",69,35,null,null,"2015-09-09","2016-03-07"]
[4024,660239,"      CT6 part of Stage 3 for Application specific Congestion control for Data Communication","ACDC-CT",3,"Rel-13","C6","2014-12-04","2016-03-11",1,"CP-150282",null,"Kim, Jaehyun, LGE","jaehyun7.kim@lge.com","Presented at CT#66. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282. 12/15: FCD -> 03/16, ES in CP-150838¦7/3/16: 0%->100",31.102,66,34,null,null,"2015-05-05","2016-03-07"]
[4027,570029,"User Plane Congestion management","UPCON",1,"Rel-13","S1,S2,C3,C4","2012-09-12","2015-03-18",1,"SP-140631","-","KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON)","Stage 1/2/3",57,29,null,null,"2012-08-06","2014-09-16"]
[4028,570129,"   Stage 1 for User Plane Congestion management","UPCON-ST1",2,"Rel-13","S1","2012-09-12","2013-03-06",1,"SP-140631","-","KDDI","Eriko Yoshida (er-yoshida@kddi.com)","SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101. 3/3/15: start date corrected (was Mar 12)",22.100999999999999,57,29,null,null,"2012-08-06","2015-03-03"]
[4031,630019,"   BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON",2,"Rel-13","S2","2014-03-07","2015-03-13",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control","-",63,32,null,null,"2014-03-04","2014-09-16"]
[4035,650207,"         CT4 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C4","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->20¦WID: CP-140734->CP-140929. Mar. 15: 50%¦June2015: Compl:50%->90. WID: CP-140929-> CP-150365.¦07/09/15: 90%->100","23.003; 29.303; New 29.405 (UPCON over Nq)",65,33,null,null,"2014-07-29","2015-09-07"]
[4039,650128,"   TR on Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",2,"Rel-13","S4","2014-09-09","2015-09-16",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100","New 26.9xy",65,33,null,null,"2014-09-05","2015-12-07"]
[4042,710036,"   (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",1,null,null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90; 9/4/21: RFC 8849 added;","26.22; RFC 8849",71,36,null,null,"2016-03-07","2021-04-09"]
[4044,710038,"   (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",1,null,null,"Ericsson","tomas.frankkila@ericsson.com","23/4/20: 60%->90; 9/4/21: RFC 8853 added;","26.114; 26.223; RFC 8853",71,36,null,null,"2016-03-07","2021-04-09"]
[4050,630114,"   Stage 1 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-140630","S1-143303","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 completed. Updated WID SP-140286=>SP-140630",22.228000000000002,63,32,null,null,"2014-02-05","2014-09-16"]
[4053,650122,"   TR on Security for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S3","2014-09-17","2015-09-30",1,"SP-140630","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%, TR number added. 3/3/15: 30%.¦June2015: Compl:30%->75¦11/12/15: 54%->100¦11/12/15: 100%->100","New 33.872 ",65,33,null,null,"2014-09-04","2015-12-11"]
[4057,690015,"      CT1 aspects 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C1","2015-09-07","2015-12-18",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: 0%->100¦7/12/15: WID:CP-150498->CP-150790->CP-150767","24.371; 24.229",69,35,null,null,"2015-09-07","2015-12-07"]
[4058,690029,"      CT3 aspects for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150644¦7/3/16: 0%->100",29.213999999999999,69,35,null,null,"2015-09-07","2016-03-07"]
[4061,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371; 24.229; 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[4065,630016,"Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks","CSPS_Coord",1,"Rel-13","S2","2014-03-07","2016-05-12",1,"SP-140168","-","Ericsson","roland.gustafsson@ericsson.com","Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios","Stage 2",63,32,null,null,"2014-02-05","2014-03-04"]
[4070,640140,"   Stage 1 for Enhancements to Proximity-based Services","eProSe-SA1",2,"Rel-13","S1","2014-06-19","2014-09-17",1,"SP-140386","-","Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced.","22.115; 22.278",64,33,null,null,"2014-05-27","2014-09-03"]
[4073,650023,"   Security for Enhancements to Proximity-based Services - Extensions","eProSe-Ext-SA3",2,"Rel-13","S3","2014-09-19","2016-03-11",1,"SP-150028","-","Qualcomm","Adrian Escott (aescott@qti.qualcomm.com)","SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA3t->eProSe-Ext-SA3. Mar15: WID: SP-140573 ->SP-150028¦7/12/15: 0%->75¦10/12/15: FCD ->03/16, ES in SP-150714¦7/3/16: 75%->100",33.302999999999997,65,33,null,null,"2014-09-04","2016-03-07"]
[4076,680008,"      CT3 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->60¦8/3/16: 60%->100","23.003; 23.008; 29.272; 29.344; 29.345",68,35,null,null,"2015-06-15","2016-03-08"]
[4079,590035,"   Study on Security for Proximity-based Services","FS_ProSe_Sec",2,"Rel-13","S3","2013-03-18","2015-06-17",1,"SP-140629","-","Qualcomm","Adrian Escott (aescott@qti.qualcomm.com)","SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information. 4/3/15: 95%->70% (more topics to be included)¦June2015: Compl:70%->75¦7/12/15: 75%->95¦7/3/1",33.832999999999998,59,30,null,null,"2013-02-20","2016-12-01"]
[4081,640045,"voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD",1,"Rel-13","S1,S2,C4,C1,C3","2014-06-16","2014-12-12",1,"SP-140394","-","Alcatel-Lucent","(betsy.covell@alcatel-lucent.com)","-","Stage 1/2",64,33,null,null,"2014-05-29","2014-06-11"]
[4084,650003,"   CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",2,"Rel-13","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Stage 3","Stage 3",65,33,null,null,"2014-07-29","2014-07-29"]
[4087,650303,"      CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Mar.15: 0->100%",29.061,65,33,null,null,"2014-07-29","2015-03-04"]
[4092,680019,"   CT aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation","zhou.xingyue@zte.com.cn","14/09/15: WID:CP-150285->CP-150497¦7/12/15: WID:CP-150497->CP-150791->874",24.161000000000001,68,35,null,null,"2015-06-15","2015-12-07"]
[4095,680022,"      CT4 aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation","zhou.xingyue@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 20%->100¦7/12/15: WID:CP-150497->CP-150791->874","29.274; 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[4099,660047,"      CT1 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,"5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100","24.229; 24.615; 24.610; 24.605",66,34,null,null,"2014-12-09","2015-09-07"]
[4101,640056,"Lawful Interception in the 3GPP Rel-13","LI13",1,"Rel-13","S3","2014-06-18","2016-12-15",1,"SP-160043","-","PIDS, Alcatel-Lucent","Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com","SP#65 updated WID SP-140400=>SP-140578. 2/4/15: WID SP-140815->SP-150111¦June2015: Compl:0%->10. WID: SP-150111->SP-150290¦14/09/15: WID:SP-150290->SP-150460¦7/12/15: 10%->15¦7/3/16: 13%->20¦7/3/16: WID:SP-150460->SP-160043¦19/9/16: 20%->60. FCD","33.106; 33.107; 33.108",64,33,null,null,"2014-06-11","2016-12-01"]
[4106,680032,"      CT1 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->50¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 50%->100",24.228999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[4107,680033,"      CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->10¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 10%->100",29.161999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[4110,650126,"   TR on TV video profile","TVProf-SA4TR",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16¦7/3/16: 85%->100","New 26.9xy; ES in SP-150650",65,33,null,null,"2014-09-05","2016-03-07"]
[4114,650030,"Support of EVS in 3G Circuit-Switched networks","EVSoCS",1,"Rel-13","S4,C4,C1,C3,R1,R2,R3","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Provide CS support of EVS to enhance voice quality in CS services over UTRAN (3G WCDMA). Dec.14: 0->5%¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103; 28.062; New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-01-28"]
[4118,670018,"      CT3 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C3","2015-03-04","2016-03-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","June2015: Compl:0%->10¦07/09/15: 10%->15¦7/12/15: 15%->90. FCD -> 03/16, ES in CP-150638¦7/3/16: 90%->100","29.163; 29.414; 29.415",67,34,null,null,"2015-03-04","2016-03-07"]
[4121,660173,"      Core part: Support of EVS over UTRAN CS","EVSoCS_UTRAN-Core",3,"Rel-13","R2,R1,R3","2015-06-16","2015-12-15",1,"RP-142282","RP-151282","Francesco Pica - Qualcomm Incorporated ","fpica@qti.qualcomm.com","Rapporteur details and involved WGs updated 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150128. 5/5/15: 0->10% 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150128->RP-150759 29/09/15: Compl:25%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4123,650032,"QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",1,"Rel-13","S4,C3,C1,C4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040","-",59,30,null,null,"2013-02-20","2014-09-20"]
[4129,660046,"      CT4 Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",3,"Rel-13","C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,"FCD -> 03/16, ES in CP-150620¦7/3/16: 0%->100","23.333; 23.334; 29.238; 29.332; 29.333; 29.334",66,34,null,null,"2014-12-09","2016-03-07"]
[4132,710043,"   (IETF) RTP Stream Pause and Resume (RFC 7728)","MMCMH",2,"Rel-13","S4-IETF","2015-12-07","2016-03-07",1,"SP-150660",null,"Ericsson","tomas.frankkila@ericsson.com","02/2016: published as RFC 7728","(IETF) RTP Stream Pause and Resume (RFC 7728)",71,36,null,null,"2014-12-12","2016-03-07"]
[4133,720062,"   (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast)","MMCMH",2,"Rel-13","S4-IETF","2015-12-07","2016-03-07",1,null,null,null,null,"Was (IETF) (draft-ietf-mmusic-sdp-simulcast); 23/4/20: 0%->90; 9/4/21: RFC 8853 added;","RFC 8853",72,37,null,null,"2016-06-13","2021-04-09"]
[4136,660251,"   Specification on Video Telephony Robustness Improvements","VTRI_EXT",2,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","3/3/15: created to distinguish TR and TS tasks¦June2015: Compl:10%->40¦Aug2015: 40%->95¦07/09/15: 95%->100","26.922 (new); 26.114",66,34,null,null,"2015-03-03","2015-09-07"]
[4141,560034,"   Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",2,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0","-",56,29,null,null,"2012-05-14","2014-09-01"]
[4144,560235,"   Converged management Performance Management Interface Definitions","OAM-PMID",2,"Rel-13","S5","2012-06-20","2015-12-11",1,"SP-150678","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30¦June2015: Compl:30%->60¦07/09/15: 60%->80¦7/12/15: 80%->100¦7/12/15: WID:SP-140613->SP-150678","new TSs 32.863 ",56,29,null,null,"2012-05-14","2015-12-07"]
[4149,660055,"   Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement","MBSFN_MDT",2,"Rel-13","S5","2014-12-12","2014-12-12",1,"SP-140786",null,"Padma Sudarsan (Alcatel-Lucent) ","padma.sudarsan<AT>alcatel-lucent<DOT>com","Mar 15: 0->15%¦June2015: Compl:15%->100","32.421; 32.422; 32.423; 32.441; 32.442; 32.446",66,34,null,null,"2014-12-12","2015-06-15"]
[4152,640159,"      TR on Inter-PLMN PS domain online charging","iPLMN-PS-OCH",3,"Rel-13","S5","2014-06-19","2015-06-17",1,"SP-140324","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Dec.14: 10->25%. Mar15: 20->60%. 06/15: 100%¦7/12/15: 100%->100","New 32.843",64,33,null,null,"2014-06-06","2015-12-07"]
[4155,670025,"   Charging on enhancements for IMS Service Continuity","CHeISC",2,"Rel-13","S5","2015-03-05","2015-09-09",1,"SP-150055",null,"Gerald Goermer","Gerald <dot> Goermer <at> nsn <dot> com","06/15: 0->50%¦07/09/15: 50%->100. FCD: 12/15->09/15","32.260; 32.299; 32.298",67,34,null,null,"2015-03-05","2015-09-07"]
[4158,610005,"Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS","RTCP_MUX",1,"Rel-13","C4,C1,C3","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Stage 2/3","Stage 2/3",61,31,null,null,"2013-08-10","2014-09-03"]
[4162,550017,"LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US",1,"Rel-13","R4,R2,R3","2012-03-05","2015-06-09",0.08,"RP-121397","-","LightSquared","masoud.olfat@lightsquared.com","RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14","LTE",55,28,null,null,"2012-02-23","2014-09-09"]
[4163,550117,"   Core part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US-Core",2,"Rel-13","R4,R2,R3","2013-08-06","2015-03-10",0.15,"RP-121397","RP-141452","LightSquared","masoud.olfat@lightsquared.com","RP#65 completion 03/15=>06/15. On hold till 12/2014","25.101; 25.104; 25.113; 25.133; 25.306; 25.307; 25.331; 25.461; 25.466; 34.124; 36.101; 36.104; 36.113; 36.124; 36.133; 36.307; new 36.832",55,28,null,null,"2012-02-23","2014-09-09"]
[4167,640036,"2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1",1,"Rel-13","R4","2014-06-17","2016-09-15",1,"RP-141710","-","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","Triggered by TR 37.846 Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) FS_UTRA_LTE_1980_2170_REG1","LTE",64,33,null,null,"2014-06-16","2014-09-22"]
[4171,650034,"Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments","UTRA_LTE_SON_AAS",1,"Rel-13","R3,G2","2014-09-12","2015-06-15",1,"RP-141624","-","Nokia Networks","krzysztof.kordybach@nsn.com","Triggered by TR 37.822 Study on Next-Generation SON for UTRA and LTE (FS_UTRA_LTE_NG_SON)","LTE",65,33,null,null,"2014-06-16","2014-09-16"]
[4174,660022,"   Stage 2 of Usage Monitoring Control PCC Extension","eUMONC-SA2",2,"Rel-13","S2","2014-12-03","2015-06-16",1,"SP-140709",null,"China Telecom, Jinyan Li","lijy@ctbri.com.cn","June2015: Compl:6%->100. Verbal indication from SA2 chair",23.202999999999999,66,34,null,null,"2014-12-03","2015-06-15"]
[4178,660023,"   CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",2,"Rel-13","C4","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,"Mar.15: 0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN","29.274; 29.275",66,34,null,null,"2014-12-04","2015-05-05"]
[4181,660040,"   CT4 aspects of P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",2,"Rel-13","C4","2014-12-03","2015-12-11",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","Dec.14: 0->5%. Mar.15: 5->100%. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:100%->75. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 75%->85¦7/12/15: 85%->100","New 29.8xy; 23.380; 29.273; 29.274; 29.275; 23.008",66,34,null,null,"2014-12-09","2015-12-07"]
[4184,680040,"   CT4 aspects of Mobile Equipment Identity signalling over WLAN","MEI_WLAN",2,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com","07/09/15: 0%->90¦7/12/15: 90%->100","29.273; 29.274; 29.275; 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[4186,660016,"Stage-3 SAE Protocol Development - Phase 4","SAES4",1,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms","23.12; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118",66,34,null,null,"2014-12-04","2015-03-24"]
[4189,670039,"   SAE for support for non-3GPP accesses - Phase 4","SAES4-non3GPP",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->50¦7/12/15: 50%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[4193,660021,"   CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",2,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140928",null,"Orange",null,"Mar.15: 80->90%. WID changed from INNB_IW-CT3¦June2015: Compl:0%->98¦07/09/15: 98%->99¦7/12/15: 99%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[4197,660026,"Shared Data Update for Multiple Subscriber","SHARED_SubData_UPD",1,"Rel-13","C4","2014-12-03","2014-12-03",1,"CP-150013",null,"Huawei, Susan Shi","susan.shishufeng@huawei.com","Mar.15: 0->50%, WID: CP-140804->CP-150013¦June2015: Compl:50%->95¦07/09/15: 95%->100","29.328; 29.364",66,34,null,null,"2014-12-04","2015-09-07"]
[4200,720059,"   (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C1","2016-06-13","2017-06-20",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage",null,"draft-ietf-mmusic-dtls-sdp; draft-ietf-mmusic-4572-update",66,34,null,null,"2014-12-04","2015-12-07"]
[4204,670001,"   CT4 Aspect of H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",2,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du. ES in 639","duxiaoning@chinamobile.com","June2015: Compl:0%->10¦07/09/15: 10%->20¦7/12/15: 20%->90¦7/3/16: 90%->100",23.334,67,34,null,null,"2015-03-04","2016-03-07"]
[4206,670026,"Review of dedicated 3GPP UICC features","Red_UCe",1,"Rel-13","C6","2015-03-09","2015-12-11",1,"CP-150152",null,"Blackberry, Adrian Buckley","abuckley@blackberry.com","Results from the homonymous Study¦June2015: Compl:0%->60¦07/09/15: 60%->75¦7/3/16: 75%->100","31.102; 31.111; 31.121; 31.124",67,34,null,null,"2015-03-09","2016-03-07"]
[4209,680043,"   CT4 aspects of Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",2,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com","07/09/15: 0%->5¦7/12/15: 5%->70. FCD->03/16. ES in CP-150614¦7/3/16: 70%->100","23.334; 29.334; 29.238; 23.333; 29.333; 29.332; 29.232",68,35,null,null,"2015-06-15","2016-03-07"]
[4212,640051,"Enhanced CS Fallback (CSFB)","eCSFB",1,"Rel-13","S2,S3","2014-06-18","2015-03-13",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB)","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[4215,650024,"   Deleted - Security for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S3","2014-09-18","2014-09-18",1,"SP-140579","-","China Unicom","Feng Gao (gaofeng149@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579¦14/09/15: 0%->100. SA#69: deleted, since SA2 has stopped the work.",null,65,33,"SP-69",null,"2014-09-15","2015-09-14"]
[4219,590030,"Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA",1,"Rel-13","R4","2013-03-04","2016-09-15",1,"RP-130373","-","Huawei","ronnie.zhang@huawei.com","Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA)","UTRA; LTE; GERAN",59,30,null,null,"2013-02-26","2014-09-15"]
[4223,660174,"   Core part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Core",2,"Rel-13","R2,R1,R3","2015-08-14","2016-03-15",1,"RP-150441","RP-151337","Qualcomm Incorporated, Shailesh Patil","patil@qti.qualcomm.com ","Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4226,660176,"   Core part: Radiated requirements for the verification of multi-antenna reception performance of UEs","UTRA_LTE_MIMO_OTA-Core",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-160344","RP-151573","Intel","Intel","1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142221->RP-150261 1st Apr 15: Stat Rep: ->RP-150260 03/07/15: Compl:5%->15% 03/07/15: Stat Rep: RP-150260->RP-150746 29/09/15: Compl:15%->25% 29/09/15: WID: RP-150261->RP-151574 29/09/15: Stat Rep: RP-15074",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4228,660177,"   Core part: UE core requirements for uplink 64 QAM","LTE_UL64QAM-Core",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150691","RP-151244","Huawei","Huawei","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150232 03/07/15: Compl:10%->90% 03/07/15: WID: RP-142222->RP-150691 03/07/15: Stat Rep: RP-150232->RP-150688 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150688->RP-151244",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4234,670055,"Dual Connectivity enhancements for LTE","LTE_dualC_enh",1,"Rel-13","R2","2015-03-16","2016-06-15",1,"RP-150490",null,"NTT DOCOMO",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4235,670155,"   Core part: Dual Connectivity enhancements for LTE","LTE_dualC_enh-Core",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-151739","RP-151330","NTT DOCOMO",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150744 29/09/15: Compl:25%->55% 29/09/15: Stat Rep: RP-150744->RP-151330 1/1/16: Compl:55%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4238,670156,"   Core part: Multicarrier Load Distribution of UEs in LTE","LTE_MC_load-Core",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-152181","RP-151190","ZTE",null,"03/07/15: Compl:0%->40% 03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: Compl:40%->55% 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-151190 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4241,670158,"   Core part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Core",2,"Rel-13","R2","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081, 07/08/15: impacted TSs added 29/09/15: Compl:30%->35% 29/09/15: Stat Rep: RP-151081->RP-151563;","36.461; 36.462; 36.463; 36.464; 36.465; 36.622; 36.623; 36.624; 36.625; 36.360",67,34,null,null,"2015-04-01","2016-03-22"]
[4246,670061,"LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL",1,"Rel-13","R4","2000-01-03","2017-09-15",1,"RP-150427",null,"Ericsson",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4249,700066,"   UE Conformance Test Aspects - LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-UEConTest",2,"Rel-13","R5","2015-12-15","2017-09-15",1,"RP-160078",null,"Ericsson",null,"¦22/3/16: Compl:0%->10%¦1/7/16: Compl:10%->25%¦ 26/9/16: 21/3/17: Compl:60%->70 ;",null,70,36,null,null,"2016-01-01","2017-09-19"]
[4254,670063,"Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset",1,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150171",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4257,670064,"Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset",1,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425",null,"Samsung",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4260,670054,"Multiflow Enhancements for UTRA","HSDPA_MFTX_enh",1,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-150288",null,"Nokia","alexander.sayenko@nokia.com",null,null,67,34,null,null,"2015-05-05","2015-05-05"]
[4261,670154,"   Core part: Multiflow Enhancements for UTRA","HSDPA_MFTX_enh-Core",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-151021","RP-151302","Nokia","alexander.sayenko@nokia.com","03/07/15: Compl:0%->80% 03/07/15: WID: RP-150288->RP-151021 03/07/15: Stat Rep: ->RP-150827 29/09/15: Compl:80%->100% 29/09/15: Stat Rep: RP-150827->RP-151302",null,67,34,null,null,"2015-05-05","2015-09-29"]
[4267,690009,"   CT aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",2,"Rel-13","ct","2015-09-07","2016-03-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com",null,null,69,35,null,null,"2015-09-07","2015-09-14"]
[4268,690022,"      CT1 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 60%->95. FCD -> 03/16, ES in CP-150729¦7/3/16: 95%->100","24.302; 24.229",69,35,null,null,"2015-09-07","2016-03-07"]
[4272,660009,"MBMS Enhancements","MBMS_enh",1,"Rel-13","S2","2014-12-03","2015-12-07",1,"SP-150516",null,"Nokia Networks, Curt Wong",null,". 3/3: WID tdoc number updated¦14/09/15: WID:SP-140883->SP-150516",null,66,34,null,null,"2014-12-03","2015-09-14"]
[4276,700035,"      CT3 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C3","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,"8/12/15: 0%->100","29.061; 29.468",70,36,null,null,"2015-12-07","2015-12-08"]
[4280,690026,"   CT3 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100","29.212; 29.213",69,35,null,null,"2015-09-07","2015-12-08"]
[4283,700009,"   CT3 aspects of DiaPri","DiaPri",2,"Rel-13","C3","2015-11-02","2016-03-11",1,"CP-150613",null,"Intel, Vivek Gupta",null,"ES in CP-150645¦7/3/16: 65%->100","29.153; 29.154; 29.201; 29.212; 29.213; 29.214; 29.215; 29.217; 29.219",70,36,null,null,"2015-12-07","2016-03-07"]
[4286,680059,"Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC",1,"Rel-13","R1","2015-06-15","2016-03-15",1,"RP-151044","-","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4289,680060,"Licensed-Assisted Access using LTE","LTE_LAA",1,"Rel-13","R1","2015-06-15","2017-09-15",0.99,"RP-151045","-","Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4291,680260,"   Perf. part: Licensed-Assisted Access using LTE","LTE_LAA-Perf",2,"Rel-13","R4","2015-06-15","2016-12-15",1,"RP-151045",null,"Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Stat Rep: -->RP-15139022/3/16: Compl:0%->33%¦1/7/16: Compl:3¦26/9/16: Compl:50%->90%¦20/12/16: Compl:90%->100%¦20/12/16: Stat Rep: RP-151390->",null,68,35,null,null,"2015-07-03","2016-12-20"]
[4294,680161,"   Core part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO-Core",2,"Rel-13","R1","2015-06-15","2015-12-15",1,"RP-151085","RP-151565","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-151565 1/1/16: Compl:25%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4298,680162,"   Core part: L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-152184","RP-151238","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4302,710069,"   UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161681","-","Huawei",null,"testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4306,680167,"   Core part: RAN sharing enhancements for UMTS","RSE_UTRA_GUSH-Core",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151251","RP-151239","Huawei",null,"no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE¦29/09/15: Compl:0%->30% 29/09/15: WID: RP-151086->RP-151251 29/09/15: Stat Rep: -->RP-151239 ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4309,750051,"   UE Conformance Test Aspects - Interference Mitigation for Downlink Control Channels of LTE","LTE_IM_DLCCH-UEConTest",2,"Rel-13","R5","2017-03-15","2018-09-14",1,"RP-180176",null,"Intel",null,"tested: REL-13 LTE_IM_DLCCH-Perf (note: WI had no Core part);19/6/171 8/1/18: C 27/3/18 ;¦26/3/19: 84%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[4311,690162,"   Core part: Network-Assisted Interference Cancellation and Suppression for UMTS","UTRA_NAICS-Core",2,"Rel-13","R1","2015-09-15","2015-12-15",1,"RP-151879","-","Huawei",null,"no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS ¦1/1/16: Compl:0%->100% ¦1/1/16: WID: RP-151577->RP-151879",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4314,690065,"Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2",1,"Rel-13","R2","2015-03-16","2017-03-15",1,"RP-151611","-","CMCC",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_eMDT2",null,69,35,null,null,"2015-09-29","NA"]
[4317,721000,"   UE Conformance Test Aspects – Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-161071",null,"Intel",null,"tested REL-13 WI: LTE_eMDT2-Core26/9/16: Com;21/3/17: Compl:5%->100%",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4320,690067,"Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh",1,"Rel-13","R2","2015-09-15","2017-03-15",1,"RP-151624","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh",null,69,35,null,null,"2015-09-29","NA"]
[4325,720099,"   UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS","UTRA_LTE_iPos_enh-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-170233",null,"NextNav",null,"tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl:",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4328,700256,"   Perf. Part: Power saving enhancements for UMTS","UTRA_SDATA_POWSAV-Perf",2,"Rel-13","R4","2015-12-15","2016-03-15",1,"RP-151998",null,"Ericsson",null,"¦22/3/16: Compl:0%->100%",null,70,36,null,null,"2016-01-01","2016-03-22"]
[4332,680075,"European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150861","-","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it",null,68,35,null,null,"2015-07-03","2015-07-03"]
[4333,680175,"   Core part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20-Core",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151228","RP-151232","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it. Aug 15: TR numb added 29/09/15: Compl:0%->80% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13",36.895000000000003,68,35,null,null,"2015-07-03","2016-01-01"]
[4339,700046,"   Security Aspects of CIoT (aka NB-IoT)","CIoT",2,"Rel-13","S3","2015-11-02","2016-06-10",1,"SP-150844",null,"Tim Evans, Vodafone",null,"7/3/16: 0%->39¦19/9/16: 39%->100",33.401000000000003,70,36,null,null,"2015-12-07","2016-09-19"]
[4340,700013,"   CT aspects of CIoT","CIoT-CT",2,"Rel-13","C1","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","11/6/16: WID:CP-150795->CP-160292",null,70,36,null,null,"2015-12-07","2016-06-11"]
[4343,700015,"      CT4 aspects of CIoT","CIoT-CT",3,"Rel-13","C4","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->65¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 65%->100","29.272; 29.274; 23.008; 23.007; 29.128; 29.275; 29.230; 29.336; 29.281; 29.002; 29.303",70,36,null,null,"2015-12-07","2016-06-13"]
[4346,690063,"   RAN aspects of CIoT aka Narrowband Internet of Things (IOT)","NB_IOT",2,"Rel-13","R1","2015-09-15","2016-12-15",1,"RP-151621","-","Vodafone",null,"no Perf. part¦note: WI only stays in REL-13 because of PCG decision",null,69,35,null,null,"2015-09-29","NA"]
[4351,690006,"Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things","CIoT_EC_GSM",1,"Rel-13","G1,G2","2015-09-25","2016-09-15",0.69,"GP-151039",null,"Marteen Sunberg, Ericsson","Marteen.Sunberg@Ericsson.com","7/12/15: 0%->60",null,69,35,null,null,"2015-09-07","2015-12-07"]
[4354,721201,"   Perf. Part: Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things","CIoT_EC_GSM-Perf",2,"Rel-13","R6","2016-06-15","2016-09-15",1,"RP-160929",null,"Ericsson",null,"related to GERAN REL-13 WI CIoT_EC_GSM-Core26/9/16: Compl:0%->100%",null,72,37,null,null,"2016-07-01","2016-09-26"]
[4359,690010,"   CT aspects of extended DRX cycle","eDRX-CT",2,"Rel-13","ct","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541",null,69,35,null,null,"2015-09-07","2015-09-14"]
[4362,690021,"      CT4 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C4","2015-09-07","2015-12-17",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 40%->100¦8/12/15: 100%->95¦8/3/16: 95%->100",29.212,69,35,null,null,"2015-09-07","2016-03-08"]
[4363,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[4366,710071,"   UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE","LTE_extDRX-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-160602","-","Qualcomm",null,"testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT;",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4372,680005,"   Optimizations to Support High Latency Communications","HLcom",2,"Rel-13","S2","2015-03-05","2015-06-15",1,"SP-150252",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com","June 2015: created by MCC as a result of the split of the one-line Feature into a several-lines Feature (now Stage 2 and Stage 3 aspects)¦June2015: Compl:0%->100. WID: SP-150030->SP-150252","23.401; 23.060; 23.682",67,34,null,null,"2015-06-15","2015-06-18"]
[4374,650033,"Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1",1,"Rel-13","R1,R4,R2","2014-09-12","2017-09-15",1,"RP-141660","-","Ericsson","johan.bergman@ericsson.com","Triggered by Rel-12 TR 36.888 Study on Provision of low-cost MTC UEs based on LTE (FS_LC_MTC_LTE) and Low cost & enhanced coverage MTC UE for LTE (LC_MTC_UE)","LTE",65,33,null,null,"2014-06-16","2014-10-05"]
[4377,710067,"   UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-UEConTest",2,"Rel-13","R5","2016-03-15","2017-09-15",1,"RP-171156",null,"Ericsson",null,"testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[4381,640250,"   Stage 2 for Group based Enhancements","GROUPE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140706","-","Huawei","ZhangWanqiang@huawei.com","Mar15: 0->20%¦June2015: Compl:20%->100","23.682; TBD",64,33,null,null,"2014-05-30","2015-06-15"]
[4385,680028,"      CT1 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->15¦7/12/15: 15%->100¦7/12/15: WID:CP-150240->CP-150816","24.008; 24.301",68,35,null,null,"2015-06-15","2015-12-07"]
[4388,640049,"Monitoring Enhancements","MONTE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140705","-","Intel","puneet.jain@intel.com","Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added;",32.277999999999999,64,33,null,null,"2014-05-30","2015-10-05"]
[4389,640149,"   TR for Monitoring Enhancements","MONTE",2,"Rel-13","S2","2014-09-17","2015-06-17",1,"SP-140705","-","Intel, Puneet Jain","puneet.jain@intel.com","Dec.14: 25->85%. Mar15: 100%","New 23.789",64,33,null,null,"2014-05-30","2015-10-05"]
[4394,680011,"   Monitoring Enhancements CT aspects","MONTE-CT",2,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","14/09/15: WID:CP-150396->CP-150422",null,68,35,null,null,"2015-06-15","2015-09-14"]
[4396,680026,"      CT3 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->100¦14/09/15: WID:CP-150396->CP-150422","29.214; 29.213; 29.201",68,35,null,null,"2015-06-15","2015-09-14"]
[4400,640246,"   Stage 2 for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-23","2015-03-18",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Mar15: 0->70%¦June2015: Compl:70%->100, WID: SP-140707-> SP-150249","23.060; 23.401; 23.236",64,33,null,null,"2014-05-30","2015-06-18"]
[4403,690013,"      CT4 aspects for Dedicated Core Networks CT aspects","DECOR-CT",3,"Rel-13","C4","2015-06-25","2016-03-11",1,"CP-150423",null,null,null,"7/12/15: 70%->90. FCD -> 03/16, ES CP-150617¦7/3/16: 90%->100","29.274; 29.060; 23.003; 29.272; 29.002; 29.305; 23.008; 29.230; 29.303; 23.007",69,35,null,null,"2015-09-07","2016-03-07"]
[4407,610130,"   TR on Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-06-18",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements)","New 22.853",61,31,null,null,"2013-08-26","2014-05-27"]
[4411,640248,"   Stage 2 for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140704","-","Intel, Puneet Jain","puneet.jain@intel.com","-¦June2015: Compl:0%->100","23.682; 33.187",64,33,null,null,"2014-05-30","2015-06-15"]
[4414,680001,"   CT aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","14/09/15: WID:CP-150402->CP-150487->CP-150576",null,68,35,null,null,"2015-06-15","2015-09-14"]
[4416,680024,"      CT4 aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","07/09/15: 0%->40¦14/09/15: WID:CP-150402->CP-150487->CP-150576¦7/12/15: 40%->100","29.201; 29.336; 29.230; 29.272; 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[4419,690180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4422,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4425,620123,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27","LTE_CA_B8_B27-Core",3,"Rel-13","R4","2013-12-09","2015-12-15",0.3,"RP-140120","RP-151131","KT","ilwhan.kim@kt.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:10%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053","36.101; 36.104; 36.133; generic 36.851",62,32,null,null,"2013-12-07","2015-09-29"]
[4430,630033,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22",2,"Rel-13","R4","2014-03-06","2015-06-15",1,"RP-140094","-","Orange, Ericsson","erika.tejedor@ericsson.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4434,640122,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12-Core",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","RP-150536","U.S. Cellular","sebastian.thalanany@uscellular.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->40%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:40%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; 36.141; 36.307; generic new Rel-13 TR36.8xy [similar to Rel-12 36.853 (3 Band CA with 1UL)]",64,33,null,null,"2014-06-16","2015-06-18"]
[4437,640125,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8-Core",3,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-150874","RP-150536","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:60%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.133; generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-06-18"]
[4438,640225,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-150874","RP-150536","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536",36.307000000000002,64,33,null,null,"2014-06-16","2015-06-18"]
[4442,650037,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38","LTE_CA_B3_B38",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141129","-","Nokia Networks","iwajlo.angelow@nsn.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4445,650038,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","-","Huawei","alf.ahlstrom@huawei.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4451,650040,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40",2,"Rel-13","R4","2014-09-12","2015-12-15",1,"RP-141168","-","Ericsson","imadur.rahman@ericsson.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4453,650240,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40","LTE_CA_B20_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141168","RP-151131","Ericsson","imadur.rahman@ericsson.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-1","36.141; 36.307",65,33,null,null,"2014-06-16","2016-01-01"]
[4456,650241,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","RP-151131","KT","ilwhan.kim@kt.com","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->70%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1","36.141; 36.307",65,33,null,null,"2014-06-16","2016-01-01"]
[4460,650043,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141336","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4464,650144,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->75% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:75%->100% 03/07/1","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4467,650145,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Core",3,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4468,650245,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4473,650149,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141845","RP-150536","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4476,650151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4479,650153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29","LTE_CA_B2_B5_B29-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141667","RP-150536","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Fri 11/12/15->Mon 15/06/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xy (inter-band CA 2DL/1UL (introduce CA_B5-B29); New 36.8xz (inter-band CA 3DL/1UL)",65,33,null,null,"2014-06-16","2015-06-18"]
[4482,660172,"      Core part: LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C-Core",3,"Rel-13","R1","2014-12-15","2015-12-15",1,"RP-151984","RP-151285","Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: Compl:10%->40% 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Compl:4",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4486,660180,"      Core part: HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151852","RP-151281","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Compl:10%->40% 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150761->RP-151281¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4490,660281,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4493,660282,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4494,660083,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777",null,"China Unicom","China Unicom",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4499,660284,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150639","RP-151131","NTT DOCOMO","NTT DOCOMO","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4502,660285,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42","LTE_CA_B21_B42_B42-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150640","RP-150536","NTT DOCOMO","NTT DOCOMO","03/07/15: Compl:0%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4505,660286,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150614","RP-151131","ZTE","ZTE","1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP-",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4508,660287,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4513,660189,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28","LTE_CA_B7_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141882","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4516,660190,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151258","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4519,660191,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151259","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4521,660092,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141949",null,"KT","KT",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4524,660093,"   LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4528,660194,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150719","RP-150536","Nokia Networks","Nokia Networks","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4530,660095,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28",2,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193",null,"Softbank Mobile","Softbank Mobile",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4535,660296,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131;",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4539,660098,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142207",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4542,660099,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142208",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4543,660199,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150234","RP-150536","Huawei","Huawei","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4547,661200,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209","RP-151131","Huawei","Huawei","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4550,661201,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238","RP-150536","Intel","Intel","03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4556,661203,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150449","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4558,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4561,661105,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150450","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4565,661206,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150452","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4569,661008,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142203",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4570,661108,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150453","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4573,661109,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4578,661011,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-141975",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4581,661012,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13","LTE_CA_2UL_R13-A3",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142010",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4584,661013,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4587,670065,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150121",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4591,670166,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150642","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4595,670267,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150643","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4596,670068,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42","LTE_CA_B3_B19_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150124",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4600,670169,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4603,670170,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4607,670271,"      Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4610,670272,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12","LTE_CA_B2_B7_B12-Perf",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150431","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 122/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4613,670273,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7-Perf",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 1/1/1¦22/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4618,670175,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12","LTE_CA_B2_B4_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150660","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4621,670176,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150659","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4622,670276,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150659","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4626,670078,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150434",null,"SK Telecom",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4629,670079,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4633,670180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4635,670081,"   LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064",null,"KDDI",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4641,670083,"   LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150479",null,"Nokia Corporation",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4644,670084,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246",null,"Huawei",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4647,670085,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150437",null,"CMCC",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4648,670185,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151177","RP-151131","CMCC",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4652,670286,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438","RP-151131","CATT",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4656,680078,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32",2,"Rel-13","R4","2015-06-15","2016-03-15",0.9,"RP-150864","-","Ericsson",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4661,680279,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","RP-151131","Huawei",null,"29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4663,680180,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","RP-151131","Huawei",null,"29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4667,680281,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","RP-151131","Nokia Networks",null,"29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-151131¦1/1/16: Comp",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4670,680282,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","RP-151131","KDDI",null,"29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4674,680085,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","-","Rogers Communications",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4675,680185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","RP-151131","Rogers Communications",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4678,680186,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4683,680088,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4686,680089,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4689,680090,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4693,680191,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4696,680192,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4700,680293,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4701,680094,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4705,680195,"      Core part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4709,680296,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4712,680297,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4715,680298,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4718,681200,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4723,681102,"      Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4724,681202,"      Perf. part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4727,681203,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4731,681005,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","-","Intel",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4735,681106,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_NC_B42_4DL-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151102","RP-151131","Huawei",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4738,680174,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","RP-151131","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4740,680076,"   Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","-","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4746,710068,"      UE Conformance Test Aspects - Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China-UEConTest",3,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161679","-","Huawei",null,"testing REL-13 LTE_TDD_1447MHz_China-Core¦1/7/16: C¦",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4749,680284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42","LTE_CA_B41_B41_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151562","RP-151131","ZTE",null,"29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131",null,68,35,null,null,"2015-08-12","2016-01-01"]
[4753,690074,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4754,690174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4757,690175,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40","LTE_CA_B5_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151200","-","ZTE",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4761,690276,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4766,690178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4768,690079,"   LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4772,690182,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,"¦1/1",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4775,690183,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40","LTE_CA_B3_B28_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151363","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4779,690284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4780,690085,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4783,690089,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42","LTE_CA_B1_B3_B19_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151159","-","NTT DOCOMO",null,null,"36.857-13",69,35,null,null,"2015-09-29","NA"]
[4788,690290,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4791,690291,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-160141","-","Telstra",null,"22/3/16: Compl:95%->100%;",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4795,690093,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","NA"]
[4798,690094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case¦5/10/15: 36.899-13 added;","36.899-13",69,35,null,null,"2015-09-29","2015-10-05"]
[4801,690095,"   Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12",null,69,35,null,null,"2015-09-29","NA"]
[4803,690295,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12 ¦",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4806,710001,"(Small) Test Technical Enhancements and Improvements for Rel-13","TEI13_Test",1,"Rel-13","SP,CP,RP,GP","2013-09-18","2015-12-21",1,"-","PCG-31","-","-","Created upon demand of RAN5","-",61,31,null,null,"2015-01-12","2016-02-24"]
[4810,620012,"Study on Power saving for Machine-Type Communications (MTC) devices","FS_uPoD",1,"Rel-13","G2,G1","2014-08-12","2015-08-14",1,"GP-131136","-","China Mobile","Jing Han (hanjing@chinamobile.com)","GP#65 completion 02/15=>05/15. GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP). Dec.14: 30->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100",43.869,60,32,null,null,"2013-11-22","2015-09-30"]
[4814,650013,"Study on Small data transmission enhancements for UMTS","FS_UTRA_SDATA",1,"Rel-13","R1,R3","2014-09-16","2015-06-15",1,"RP-141861","RP-150843","Ericsson","gerardo.agni.medina.acosta@ericsson.com","3/3/15: WID: RP-141861¦Stat Rep: -->RP-141859. Impacted TR number added. 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141859->RP-150196 03/07/15: Compl:55%->100% 03/07/15: Stat Rep: RP-150196->RP-150843",25.704999999999998,65,33,null,null,"2014-09-15","2015-06-18"]
[4817,0,"Release 13 other Studies","-",1,"Rel-13","SP,R2","2013-09-12","2015-12-25",1,"-","-","-","-","-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4821,610033,"(SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO","FS_CSIPTO",1,"Rel-13","S1","2013-09-13","2014-06-18",1,"SP-130417","-","Intel","Eric.siow@intel.com","SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET",22.827999999999999,61,31,null,null,"2013-08-26","2014-12-12"]
[4823,620070,"Study on Enhanced Calling Information Presentation","FS_ECIP",1,"Rel-13","S1","2013-12-13","2014-09-17",1,"SP-130598","S1-143311","China Mobile","LI Xiaofan (lixiaofan@chinamobile.com","SP#65 completed. TR 22.810v200 for Approval. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067",22.81,62,32,null,null,"2013-11-26","2014-08-28"]
[4828,520235,"   Deleted - SA5 part of Study on Usage Monitoring Control enhancement","-",2,"-","S5","2012-03-02","2012-09-12",1,"SP-120554","-","Huawei","Hui Cai (Sarah.Cai@huawei.com)","SP#57 stopped",32.857999999999997,52,27,"SP-57","PCG-29","2011-05-19","2012-08-30"]
[4829,500034,"Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int_Sec",1,"Rel-13","S3","2010-12-28","2015-06-12",1,"SP-150368","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%¦June2015: Compl:65%->100¦June2015: WID:SP-140576->SP-150368",33.895000000000003,50,26,null,null,"2010-11-25","2015-06-18"]
[4832,620059,"Study on Application and Partitioning of Itf-N","FS_OAM_AP_Itf-N",1,"Rel-13","S5","2013-12-17","2015-09-11",1,"SP-130681","-","China Mobile","Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com)","-Dec.14: 15->30%, CD: 12/14->09/15¦June2015: Compl:30%->60¦07/09/15: 60%->100","32.861 ",62,32,null,null,"2013-11-28","2015-09-07"]
[4837,590034,"Study on Downlink MIMO","FS_DOMIMO",1,"Rel-13","G1,G2","2014-08-14","2016-05-12",1,"GP-130288","-","Nokia Networks","juergen.hofmann@nokia.com","GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID. Dec.14: 50->65%, CD: 02/15->05/15. 7/9/15: FCD: 11/15->02/16¦2/3/16: 65%->75, FCD: 02/16->05/16¦11/9/17: 75%->100","45.8xy",57,30,null,null,"2013-03-04","2017-09-11"]
[4840,570022,"Study on LTE FDD in the bands 1980-2010 MHz and 2170-2200 MHz","FS_LTE_1980_2170_Korea",1,"Rel-13","R4","2012-09-11","2015-12-15",1,"RP-151855","RP-151274","KT","Chungwoo HWANG (cwhwang@kt.com)","CD:Thu 11/12/14->Sun 15/03/15¦Compl:85%->90%¦Stat Rep: RP-141153->RP-141851 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141154->RP-150119 1st Apr 15: Stat Rep: RP-141851->RP-150120 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: S","LTE 36.861",57,29,null,null,"2012-09-03","2016-01-01"]
[4843,640016,"Study on Advanced Wireless Services (AWS) - Extension band for LTE","FS_LTE_AWS_EXT",1,"Rel-13","R4","2013-12-16","2014-12-15",1,"RP-141037","RP-141968","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141429->RP-141968. 5/5/15: 2nd TR number added (to be clarified why two TR for a same topic)","36.849; 36.869",64,33,null,null,"2014-06-16","2015-05-05"]
[4845,650014,"Study on Downlink enhancements for UMTS","FS_UTRA_EDL",1,"Rel-13","R2,R1","2014-09-12","2015-06-15",1,"RP-150224","RP-150681","Huawei","jun.chen@huawei.com","WID: RP-141901¦Stat Rep: -->RP-142233 1st Apr 15: Compl:40%->80% 1st Apr 15: WID: RP-141901->RP-150224 1st Apr 15: Stat Rep: RP-142233->RP-150223. 5/5/15: R4 replaced by R1 (correction mistake) 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150223->","UTRA 25.706",65,33,null,null,"2014-09-15","2015-06-18"]
[4851,660064,"Study on Network-Assisted Interference Cancellation and Suppression for UMTS","FS_UTRA_NAICS",1,"Rel-13","R1","2014-12-15","2015-09-15",1,"RP-150174","RP-151235","Huawei","Huawei","TS number added 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-142250->RP-150174 1st Apr 15: Stat Rep: ->RP-150175. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake) 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150175->RP-150679 29/09/15: Compl:65%-",25.765999999999998,66,34,null,null,"2015-01-12","2015-09-29"]
[4854,660067,"Study on Extension of Dual Connectivity in E-UTRAN","FS_LTE_dualC_ext",1,"Rel-13","R3","2014-12-15","2015-06-15",1,"RP-150170","RP-150849","Samsung","Samsung","1st Apr 15: WID: RP-142257->RP-150170 1st Apr 15: Stat Rep: ->RP-150163 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150163->RP-150849. 7/10/15: responsible group corrected (R4->R3)",36.875,66,34,null,null,"2015-01-12","2015-10-07"]
[4858,660071,"Study on performance enhancements for high speed scenario in LTE","FS_LTE_high_speed",1,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150159","RP-151313","NTTDoCoMo","NTTDoCoMo","TR Rapporteur is Huawei 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142307->RP-150159 1st Apr 15: Stat Rep: ->RP-150517 03/07/15: Compl:5%->40% 03/07/15: Stat Rep: RP-150517->RP-150793 29/09/15: Compl:40%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4859,660061,"Study on Enhanced Multiuser Transmissions and Network","FS_MUIC_LTE",1,"Rel-13","R1","2014-12-12","2015-12-11",0,"RP-142315",null,"Pei-Kai Liao","pk.liao@mediatek.com","TR added",36.890999999999998,67,34,null,null,"2014-12-12","2015-01-29"]
[4863,670087,"Study on Phase 1 of the Support of Emergency services over WLAN","FS_SEW",1,"Rel-13","S2","2015-03-12","2015-06-18",1,"SP-150251",null,"Laurent Thiebaut, Alcatel Lucent","Laurent.thiebaut@alcatel-lucent.com ","June2015: Compl:0%->100, SP-150151->SP-150251","new 23.771",67,34,null,null,"2015-04-01","2015-06-18"]
[4866,680018,"Study on S6a/S6d Shared Data Update","FS_eSDU",1,"Rel-13","C4","2015-06-15","2015-12-11",1,"CP-150400",null,"Ulrich Wiehe, Nokia Networks","ulrich.wiehe@nokia.com","07/09/15: 0%->20¦7/12/15: 20%->100","New 29.813",68,35,null,null,"2015-06-15","2015-12-07"]
[4871,720087,"Study on multi-node testing for LAA","FS_LTE_LAA_multinode_test",1,"Rel-13","R4","2016-06-15","2017-06-15",1,"RP-162144",null,"Huawei",null,"coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672¦20/12/16: Compl:10%->30%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17¦20/12/16: WID: RP-161672->RP-162144¦21/3/17: CD:Wed 15/03/17->Thu 15/06/17;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[4874,0,"Stage 1 - ONLY Features","-",1,"Rel-12","SP,CP","2011-09-27","2014-03-05",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[4877,500031,"Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers","MOSAP",1,"Rel-12","S1,S2","2010-12-16","2013-12-11",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#58 Stage 2 stopped (TR only, no normative work done)","Stage 1",50,26,null,null,"2010-11-29","2012-11-22"]
[4880,520026,"   Deleted - Stage 2 for MOSAP","MOSAP-SA2Del",2,"Rel-12","S2","2011-06-14","2012-12-12",1,"SP-120427","-","Intel","chang.hong.shan@intel.com","SP#58 stopped (no normative work done)","TBD",52,27,"SP-58","PCG-30","2011-05-26","2012-11-22"]
[4882,520127,"   Stage 1 for IMS Network-Independent Public User Identities","INIPUI-SA1",2,"Rel-12","S1","2011-06-08","2012-06-20",1,"SP-120425","-","Vodafone","mona.mustapha@vodafone.com","SP#56 re-completed. Updated WID SP-110381=>SP-120425 (Re-opened & moved to Rel-12 by adding new reqs & removing reqs from Rel-11). SP#53 Rel-11 Stage 1 completed","22.115; 22.228",52,27,null,null,"2011-05-19","2012-06-19"]
[4885,550024,"Advanced IP Interconnection of Services (IPXS) for national interconnect","IPXSNAT",1,"Rel-12","S1","2012-03-06","2012-09-12",1,"SP-120428","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051.","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[4889,560019,"Explicit Communication Transfer Blind (ECT Blind) service interactions","ECTB",1,"Rel-12","S1","2012-06-18","2012-06-20",1,"SP-120301","-","Orange","philippe.lottin@orange.com","SP#56 WID approved & Stage 1 completed","Stage 1",56,29,null,null,"2012-05-14","2012-06-08"]
[4893,580060,"Sequential Flexible Alerting","SEQ_FA",1,"Rel-12","S1","2012-12-10","2012-12-12",1,"SP-120895","-","Orange","bruno.tossou@orange-ftgroup.com","SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. 22/01: acronym modified","Stage 1",58,30,null,null,"2012-11-16","2015-01-22"]
[4896,580161,"   Stage 1 for Language and Modality Information for communications","LangInfo-SA1",2,"Rel-12","S1","2012-12-11","2013-03-06",1,"SP-130108","-","Orange","philippe.lottin@orange.com","SP#59 completed. Updated WID SP-120937=>SP-130108",22.228000000000002,58,30,null,null,"2012-11-16","2013-02-19"]
[4900,590141,"   Deleted - Stage 1 for Application and Service Access Control","ASAC-SA1del",2,"Rel-12","S1","2013-03-06","2013-06-19",1,"SP-130124","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster)",22.010999999999999,59,30,"SP-60","PCG-31","2013-02-19","2013-02-19"]
[4902,590142,"   Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode","PMOC-SA1",2,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130111","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#59 completed",22.010999999999999,59,30,null,null,"2013-02-19","2013-02-19"]
[4905,500128,"   TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network","LIMONET-SA3",2,"Rel-12","S2","2010-10-15","2013-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#59 completed. TR 23.859 v100 for Information and Approval","new 23.859",50,26,null,null,"2010-11-26","2013-02-27"]
[4908,530015,"      Stage 3 CN aspects of SIPTO at the Local Network","LIMONET-SIPTO",3,"Rel-12","C4,C1","2011-09-24","2014-03-05",1,"CP-130274","-","Huawei","peter.schmitt@huawei.com","CP#63 completed","Stage 3",53,27,null,null,"2011-08-27","2014-01-29"]
[4911,590020,"   RAN aspects for SIPTO at the Local Network","LIMONET-RAN",2,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","-","Huawei","zheng.zhou@huawei.com","-","UTRA; LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[4915,530016,"      Deleted - Stage 3 CN aspects of LIPA Mobility","LIMONET-LIPA-del2",3,"Rel-12","C1,C4","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","Stage 3",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[4919,510149,"   TR on Stage 2 for Operator Policies for IP Interface Selection","OPIIS",2,"Rel-12","S2","2011-03-23","2012-12-12",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","SP#58 completed","new 23.853",51,26,null,null,"2011-02-21","2012-12-10"]
[4922,520029,"Short Message Service (SMS) submit and delivery without MSISDN in IMS","SMSMI",1,"Rel-12","S2,C1,C4","2011-06-08","2013-12-06",1,"SP-120321","-","Nokia Siemens Networks","curt.wong@nsn.com","Linked to Rel-7 SMSIP (Support of SMS over generic 3GPP IP access), Rel-11 SIMTC, Rel-12 TR 22.988 SA1 Study on alternatives to E.164 for MTC","Stage 2/3",52,27,null,null,"2011-05-26","2013-11-18"]
[4926,590113,"      CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",3,"Rel-12","C1","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed","23.040; 24.341",59,30,null,null,"2013-02-16","2013-11-18"]
[4928,530042,"IMS-based Telepresence","IMS_TELEP",1,"Rel-12","S1,C1,C3,C4,IETF","2010-03-22","2014-12-09",1,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified","Stage 1/2/3",53,27,null,null,"2011-07-19","2012-06-08"]
[4931,580002,"      TR on CT part of IMS Telepresence (Stage 2/3)","IMS_TELEP",3,"Rel-12","C1","2012-12-07","2014-06-13",1,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#64 completed. 2/4/15: acronym changed to IMS_TELEP","New 24.803",58,30,null,null,"2012-11-19","2015-04-02"]
[4934,641002,"      (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",1,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-framework ); 9/4/21: RFC 8845 added;","draft-ietf-clue-framework; RFC 8845",64,33,null,null,"2014-06-06","2021-04-09"]
[4937,641005,"      (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",1,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-data-model-schema); 9/4/21: RFC 8846 added;","draft-ietf-clue-data-model-schema; RFC 8846",64,33,null,null,"2014-06-06","2021-04-09"]
[4942,590037,"   TR on Architecture enhancements to support Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S2","2013-03-07","2014-03-07",1,"SP-140433","-","Nokia Networks","rainer.liebhart@nsn.com ","SP#63 completed. TR 23.768v200 for Approval","New 23.768",59,30,null,null,"2013-02-21","2014-09-07"]
[4945,610035,"   Security for Group Communication System Enablers for LTE (Stage 2)","GCSE_LTE",2,"Rel-12","S3","2013-09-13","2014-06-18",1,"SP-140433","-","Nokia Networks","anja.jerichow@nsn.com","SP#64 completed",33.246000000000002,61,31,null,null,"2013-09-03","2014-09-07"]
[4949,650008,"      CT1 part of Group Communication System Enablers for LTE","GCSE_LTE-CT",3,"Rel-12","C1","2014-09-12","2014-12-09",1,"CP-140559","CP-140614","Nokia Networks","thomas.belling@nsn.com","CP#65 updated WID CP-140452=>CP-140559 (added CT1 part). Exception in CP-140614. Dec.14: 90->100%",24.300999999999998,65,33,null,null,"2014-07-30","2014-12-04"]
[4950,640037,"   Group Call eMBMS congestion management for LTE","GCSE_LTE-MBMS_CM",2,"Rel-12","R3","2014-06-16","2015-03-13",1,"RP-141035","-","Alcatel-Lucent","hakon.helmers@alcatel-lucent.com","-","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4956,560522,"   Security and Privacy aspects for Machine-Type and other mobile data applications Communications enhancements (Stage 2)","MTCe-SA3",2,"Rel-12","S3","2012-06-22","2014-03-07",1,"SP-130327","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#63 completed. TS 33.187v100 for 1-step Approval","New 33.187",56,29,null,null,"2012-06-02","2014-02-27"]
[4957,560122,"   BB1: Small Data and Device Triggering Enhancements (SDDTE)","MTCe-SDDTE",2,"Rel-12","S2,C4,C3","2012-06-18","2014-09-11",1,"SP-120450","-","Intel","puneet.jain@intel.com ","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[4963,560222,"   Deleted - BB2: Monitoring Enhancements (MONTE)","MTCe-MONTE",2,"Rel-12","S2","2012-06-18","2012-12-12",1,"SP-120438","-","Intel","puneet.jain@intel.com ","SP#58 stopped (at 20% completion)",23.681999999999999,56,29,"SP-58","PCG-30","2012-04-13","2012-12-14"]
[4964,560322,"   BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",2,"Rel-12",null,"2012-06-18","2016-05-12",0.93,"SP-120442","-","Ericsson","peter.hedman@ericsson.com","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[4968,620107,"         CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT1",4,"Rel-12","C1","2013-12-06","2014-09-11",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","CP#65 completed","24.008; 24.301",62,32,null,null,"2013-11-18","2014-07-28"]
[4971,690068,"         UE Conformance Test Aspects - UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-UEConTest",4,"Rel-12","R5","2015-09-15","2016-03-15",1,"RP-151161","-","Ericsson",null,"tested: MTCe-UEPCOP was a REL-12 SA2 WI¦NAS over LTE and UTRA;1/1/16: Compl:0%->25%22/3/16: C",null,69,35,null,null,"2015-09-29","2016-03-22"]
[4976,620143,"      Core part: RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN-Core",3,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","RP-141096","ZTE","sergio.parolari@zte.com.cn","RP#65 completed","25.300; 25.304; 25.413; 36.300; 36.304; 36.413; 36.423",62,32,null,null,"2013-12-07","2014-09-15"]
[4979,600212,"   Perf. part: Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE-Perf",2,"Rel-12","R4","2013-06-15","2015-06-15",1,"RP-150940","RP-150915","Vodafone","eric.bouton@vodafone.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141221->RP-142024 1st Apr 15: Compl:65%->90% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-142024->RP-150149 03/07/15: Compl:90%->100% 03/07/15: WID: RP-14052","36.101; 36.104; 36.133",60,31,null,null,"2013-06-17","2015-06-18"]
[4982,570031,"   Stage 1 for Policy and Charging Support for Fixed Mobile Convergence","P4C-FMC",2,"Rel-12","S1","2012-09-10","2012-09-12",1,"SP-120542","-","Huawei","amar.deol@huawei.com","SP#57 completed",22.277999999999999,57,29,null,null,"2012-08-06","2013-01-08"]
[4985,562124,"      Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F-SA2",3,"Rel-12","S2","2012-06-20","2013-12-11",1,"SP-120275","-","Huawei","marco.spini@huawei.com","SP#62 completed","23.139; 23.203",56,29,null,null,"2012-06-04","2013-11-28"]
[4987,610112,"         CT3 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C3","2013-09-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed","29.212; 29.213; 29.215; 29.219",61,31,null,null,"2013-08-12","2014-04-16"]
[4990,600042,"      Policy and Charging Enforcement Function (PCEF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3)","P4C-F-CH_P",3,"Rel-12","S5","2013-06-21","2014-09-17",1,"SP-130261","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#65 completed. Introduce Charging Characteristics in Convergent scenario, Include missing fixed user location information for NSWO ","Stage 2 (32.240; 32.251); Stage 3 (32.298; 32.299)",60,31,null,null,"2013-06-02","2014-08-26"]
[4994,562224,"      Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI)","P4C-TI-SA2",3,"Rel-12","S2","2012-06-20","2013-06-19",1,"SP-120444","-","Alcatel-Lucent","konstantin.livanos@alcatel-lucent.com","SP#60 completed","23.139; 23.203",56,29,null,null,"2012-06-04","2013-06-06"]
[4998,560624,"   Deleted - BB6: Policy and Charging Control for 3GPP UEs connected to fixed broadband access networks via S2a reference point for EPC routed traffic in convergence (P4C-TC)","P4C-TC",2,"Rel-12","S2","2012-06-20","2012-12-12",1,"SP-120280","-","ZTE","Tricci So (tso@zteusa.com)","SP#58 stopped (at 30% completion)","23.139; 23.203; new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[5002,560225,"   Stage 2 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA2",2,"Rel-12","S2","2012-06-25","2013-06-19",1,"SP-120862","-","Deutsche Telekom","michele.zarri@telekom.com","SP#60 completed",23.228000000000002,56,29,null,null,"2012-05-11","2013-06-06"]
[5005,610207,"      CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",3,"Rel-12","C3","2013-09-06","2014-06-11",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","CP#64 completed",29.164999999999999,61,31,null,null,"2013-08-10","2014-04-16"]
[5007,560126,"   TR on Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SATR",2,"Rel-12","S2,S1","2012-06-18","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","New 23.865",56,29,null,null,"2012-05-11","2013-11-28"]
[5010,620005,"   CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3)","WLAN_NS-CT",2,"Rel-12","C1","2013-12-06","2014-12-09",1,"CP-130712","CP-140622","Qualcomm","Amer Catovic, amerc@qualcomm.com","CP#65 completion 09/14=>12/14. CP#65 exception CP-140622. Dec.14: 95->100%","24.302; 24.312",62,32,null,null,"2013-11-19","2014-12-04"]
[5013,580056,"   Deleted - Stage 2 for IMS Registration Control","IMS_RegCon-del2",2,"Rel-12","S2","2012-12-13","2013-12-11",1,"SP-120735","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 stopped at 50% completion",23.228000000000002,58,30,"SP-62","PCG-32","2012-11-13","2013-12-10"]
[5017,580059,"Proximity-based Services","ProSe",1,"Rel-12",null,"2012-12-13","2017-06-15",1,"SP-140574","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044","Stage 1/2",58,30,null,null,"2012-11-16","2014-09-15"]
[5020,580359,"   Stage 2 for Proximity-based Services","ProSe-SA2",2,"Rel-12","S2","2012-12-19","2014-06-18",1,"SP-140574","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval","New 23.303",58,30,null,null,"2012-11-16","2014-09-15"]
[5024,640139,"      Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use","ProSe-CH-SA5TR",3,"Rel-12","S5","2014-06-19","2014-12-12",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100%","New 32.844",64,33,null,null,"2014-06-06","2014-12-12"]
[5028,630206,"      CT3 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C3","2014-03-05","2014-12-09",1,"CP-140290","CP-140568","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. TS 29.343v100 for 1-step Approval. Exception in CP-140568. Dec.14: 90->100","New 29.343",63,32,null,null,"2014-01-29","2014-12-04"]
[5029,630306,"      CT4 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C4","2014-03-05","2014-12-09",1,"CP-140290","CP-140484","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. TS 29.344/5v100 for 1-step Approval. Exception in CP-140484. Dec.14: 90->100","29.272; 23.008; 23.003; New TSs (29.344; 29.345)",63,32,null,null,"2014-01-29","2014-12-04"]
[5035,580062,"Web Real Time Communication access to IMS","IMS_WebRTC",1,"Rel-12","S1,S2,S3","2012-12-14","2019-03-07",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed.","Stage 1/2",58,30,null,null,"2012-11-16","2013-09-09"]
[5036,580162,"   Stage 1 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S1","2012-12-14","2013-06-19",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","SP#60 completed","22.101; 22.228",58,30,null,null,"2012-11-16","2013-09-09"]
[5039,631001,"   (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-overview)","IMS_WebRTC",2,"Rel-12","C1-IETF","2013-06-25","2014-12-12",1,"SP-130707","-","Uwe Rauschenbach","Uwe Rauschenbach","In WGLC. Mar15: responsible WG changed from S2-IETF; 23/4/20: 50%->90; 9/4/21: RFC 8825 added;","draft-ietf-rtcweb-overview; RFC 8825",63,32,null,null,"2014-02-10","2021-04-09"]
[5042,610036,"   Security for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S3","2013-09-12","2014-06-18",1,"SP-130707","-","Ericsson","oscar.ohlsson@ericsson.com","SP#64 completed","33.203; 33.328",61,31,null,null,"2013-09-03","2014-06-09"]
[5047,641006,"      (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-data-channel)","IMS_WebRTC-data",3,"Rel-12","C1-IETF","2014-03-06","2014-12-09",1,"CP-140192","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Submitted to IESG for publication. Mar15: In RFC-Editors queue; 9/4/21: RFC 8831 added;","draft-ietf-rtcweb-data-channel; RFC 8831",64,33,null,null,"2014-06-06","2021-04-09"]
[5050,870067,"       (IETF) Third-Party Token-based Authentication and Authorization for Session Initiation Protocol (SIP) (draft-ietf-sipcore-sip-token-authnz)","IMS_WebRTC-yusef",3,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,null,null,null,null,"9/4/21: RFC 8898 added;","RFC 8898",87,44,null,null,"2014-09-02","2021-04-09"]
[5055,600048,"   CT3 aspects of Usage Monitoring Control PCC enhancement (Stage 3)","UMONC-CT3",2,"Rel-12","C3","2013-06-14","2013-09-06",1,"CP-130396","-","ZTE","zhou.xiaoyun@zte.com.cn","CP#61 completed. 2/4/15: acronym changed to \"UMONC-CT3\"","29.212; 29.214; 29.215",60,31,null,null,"2013-05-29","2015-04-02"]
[5058,600011,"   Charging for Application Based Charging","ABC-CT5",2,"Rel-12","S5","2013-06-19","2014-06-18",1,"SP-130328","-","Openet Telecom","alan.mcnamee@openet.com","SP#64 completed","32.240; 32.251; 32.296; 32.298; 32.299",60,31,null,null,"2013-05-29","2014-06-10"]
[5061,610138,"   Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-SA2",2,"Rel-12","S2","2013-09-11","2014-03-07",1,"SP-130391","-","ZTE","Tricci So (tso@zteusa.com)","SP#63 completed",23.402000000000001,61,31,null,null,"2013-07-25","2014-02-04"]
[5062,610009,"   Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",2,"Rel-12","C1,C4","2013-09-09","2014-12-09",1,"CP-130715","-","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#62 updated WID CP-130580=>CP-130715","Stage 3",61,31,null,null,"2013-08-10","2013-11-28"]
[5068,610040,"Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN",1,"Rel-12","S2,C3,C1,C4","2013-09-12","2014-09-11",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[5070,620008,"   CT aspects of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case (Stage 3)","NETLOC_TWAN-CT",2,"Rel-12","C3,C1,C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","-","Stage 3",62,32,null,null,"2013-11-19","2013-11-19"]
[5073,620308,"      CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed","29.273; 29.274; 29.275; 29.328; 29.329",62,32,null,null,"2013-11-19","2014-07-28"]
[5076,650017,"   Charging aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CH",2,"Rel-12","S5","2014-09-15","2014-09-17",1,"SP-140541","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#65 New WID approved & completed. Introduction of Presence Reporting Areas for Charging","32.251; 32.298; 32.299",65,33,null,null,"2014-08-24","2014-09-10"]
[5081,510054,"Security aspects of Public Warning System","PWS_Sec",1,"Rel-12","S3,S1","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","-","-",51,26,null,null,"2012-06-02","2014-06-09"]
[5084,511354,"   Deleted - SA3 part for Security aspects of Public Warning System","PWS_Sec-del1",2,"Rel-12","S3","2011-03-30","2014-06-18",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#64 stopped","New 33.269",51,26,"SP-64","PCG-33","2012-06-02","2014-06-09"]
[5085,510154,"   Deleted - Stage 1 for Security aspects of Public Warning System","PWS_Sec-del2",2,"Rel-12","S1","2011-03-23","2012-06-20",1,"SP-120434","-","ST-Ericsson","john.mattsson@ericsson.com","Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. ",22.268000000000001,51,26,"SP-56","PCG-29","2012-06-02","2012-06-26"]
[5090,560030,"Extended IMS media plane security features","eMEDIASEC",1,"Rel-12","S3,C4,C1,C3,IETF","2012-06-20","2014-12-09",1,"SP-120447","-","Vodafone","Aguibou.Barry@vodafone.com","Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC)","Stage 2/3",56,29,null,null,"2012-06-02","2013-02-19"]
[5092,611003,"   (IETF) SA3 part of Extended IMS media plane security features (RFC 7345)","eMEDIASECSA3IETF",2,"Rel-12","S3-IETF","2012-06-20","2014-09-12",1,"SP-120447","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","SP#65 completed","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",61,31,null,null,"2013-09-23","2014-09-02"]
[5096,621001,"      (IETF) CT4 part of Extended IMS media plane security features (RFC 7345)","eMEDIASEC-CT",3,"Rel-12","C4-IETF","2012-12-18","2014-09-11",1,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",62,32,null,null,"2013-11-27","2015-04-02"]
[5099,621002,"      (IETF) CT1 part of Extended IMS media plane security features (RFC 7345)","eMEDIASEC-CT",3,"Rel-12","C1-IETF","2014-03-06","2014-09-11",1,"CP-130597","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",62,32,null,null,"2013-11-27","2015-04-02"]
[5103,580164,"   SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3)","TURAN-SA3",2,"Rel-12","S3","2012-12-13","2014-06-18",1,"SP-130245","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#64 completed","33.203; 33.402",58,30,null,null,"2012-11-12","2014-06-09"]
[5107,470031,"   Stage 1 for Codec for Enhanced Voice Services","EVS_codec-SA1",2,"Rel-12","S1","2010-03-25","2010-03-25",1,"SP-140007","-","Huawei","lei.miao@huawei.com","SP#47 completed",22.172999999999998,47,24,null,null,"2010-03-10","2010-03-22"]
[5110,650005,"   CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",2,"Rel-12","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140800","-","Nokia Networks","Jan.Kall@nsn.com","Stage 3¦WID: CP-140492-> CP-140800",null,65,33,null,null,"2014-07-29","2014-12-09"]
[5112,650205,"      CT1 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C1","2014-09-16","2014-12-09",1,"CP-140800","CP-140618","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140618. Dec.14: 0->100%¦WID: CP-140492-> CP-140800",24.228999999999999,65,33,null,null,"2014-07-29","2014-12-09"]
[5115,560040,"Coordination of Video Orientation","CVO",1,"Rel-12","S4,C4,C1,C3","2012-06-07","2013-12-06",1,"SP-120228","-","Ericsson","frederic.gabin@ericsson.com","CP#62 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering","-",56,29,null,null,"2012-06-07","2013-11-19"]
[5118,600106,"      CT4 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C4","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","23.333; 23.334; 29.238; 29.332; 29.333; 29.334",60,31,null,null,"2013-05-28","2014-01-29"]
[5122,570133,"   TR on Evaluation of High Efficiency Video Coding for 3GPP Services","HEVC-SA4TR",2,"Rel-12","S4","2012-09-12","2014-06-19",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed. TR 26.906v200 for Approval","New 26.906",57,29,null,null,"2012-08-30","2014-04-16"]
[5125,580065,"Mobile stereoscopic 3D services extensions","M3DV_Ext",1,"Rel-12","S4","2012-12-12","2013-09-11",1,"SP-120768","-","Huawei","lukasz.kondrad@huawei.com","SP#61 completed. Related to Rel-11 Study On Mobile 3D Video Coding (FS_M3DVC) TR 26.905 and Rel-11 Mobile 3D Video Coding (M3DVC)","26.114; 26.245; 26.247; 26.430",58,30,null,null,"2012-11-12","2013-07-24"]
[5130,580167,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects","ART_LTE-NBWB",2,"Rel-12","S4","2012-12-12","2013-12-11",1,"SP-120771","-","Sony Mobile Communications","Peter.Isberg@sony.com","SP#62 completed","26.131; 26.132",58,30,null,null,"2012-11-12","2013-11-18"]
[5133,590043,"MBMS Improvements","MI",1,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130024","SP-140471","Ericsson","eric.turcotte@ericsson.com","Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description",null,59,30,null,null,"2013-02-20","2014-09-05"]
[5134,590343,"   TR on Enhanced MBMS Operation","MI-EMOTR",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.848v100 for Information. Dec.14: 85->100. ","New 26.848",59,30,null,null,"2013-02-20","2015-03-05"]
[5138,590044,"End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI",1,"Rel-12","S4","2013-03-06","2015-09-14",1,"SP-140600","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040",26.114000000000001,59,30,null,null,"2013-02-20","2014-09-09"]
[5141,600107,"      CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C3","2013-06-21","2015-09-14",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","Dec.14: CD: 09/14->09/15. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","29.162; 29.163; 29.213; 29.214",60,31,null,null,"2013-05-29","2015-05-05"]
[5144,620066,"Video Coding Enhancements in IMS Messaging and Presence","VCEIMP",1,"Rel-12","S4","2013-12-11","2014-03-07",1,"SP-130579","-","Ericsson","frederic.gabin@ericsson.com","SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141",26.140999999999998,62,32,null,null,"2013-11-29","2014-01-29"]
[5147,560131,"   Rel-12 Self-Organizing Networks (SON) - OAM aspects","OAM12-SON",2,"Rel-12","S5","2011-09-21","2013-12-11",1,"-","-","-","-","OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI","-",56,29,null,null,"2012-04-18","2012-11-19"]
[5152,530050,"   Network Management for 3GPP Interworking WLAN","OAM-IWLAN",2,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140542","-","China Mobile","Chengang@chinamobile.com, lijian@chinamobile.com","SP#65 updated WID SP-120779=>SP-140542 (removed parts on CN and non-3GPP access). Discontinue I-WLAN spec.","-",53,27,null,null,"2011-08-27","2014-09-10"]
[5156,620056,"      Alarm quality improvements","OAM-AMI-SA5",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130611","SP-140544","TeliaSonera","tommy.berggren@teliasonera.com","SP#65 completion 09/14=>12/14. Exception in SP-140544. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) . Dec.14: 50->100","32.111-1; 32.111-2; 32.111-6",62,32,null,null,"2013-11-28","2014-12-04"]
[5160,620157,"      OAM aspects of Network Sharing - Concepts and high-level requirements","OAM-SHARE-SA5c",3,"Rel-12","S5","2013-12-11","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. LM 80->100","new 32.130",62,32,null,null,"2013-11-28","2014-12-04"]
[5163,580051,"   Short Message Service - Service Center (SMS-SC) Offline Charging","SMS-SC-CH",2,"Rel-12","S5","2012-12-12","2014-03-07",1,"SP-140027","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027","32.240; 32.274; 32.297; 32.298; 32.299",58,30,null,null,"2012-11-20","2014-02-27"]
[5164,610041,"   Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3)","CHIPS",2,"Rel-12","S5","2013-09-12","2014-06-18",1,"SP-130642","-","Ericsson","david.shrader@ericsson.com","SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS","32.251; 32.298; 32.299",61,31,null,null,"2013-09-04","2015-12-07"]
[5167,530018,"IMS Emergency PSAP Callback (Stage 3)","EMC_PC",1,"Rel-12","C1,C3,IETF","2011-09-21","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls","Stage 3",53,27,null,null,"2011-08-27","2013-11-18"]
[5173,580009,"Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD",1,"Rel-12","C1,C4,R3","2012-12-07","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality.","Stage 2/3",58,30,null,null,"2012-11-19","2013-09-04"]
[5175,580011,"   CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD-CT4",2,"Rel-12","C4","2012-12-10","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","CP#64 completed","23.007; 29.168",58,30,null,null,"2012-11-19","2014-05-25"]
[5178,580012,"Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3)","bSRVCC",1,"Rel-12","C1,C3,R5","2012-12-07","2014-03-06",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12","GERAN; UTRA; LTE",58,30,null,null,"2012-11-19","2013-06-10"]
[5182,580013,"IMS Stage 3 IETF Protocol Alignment - phase 6","IMSProtoc6",1,"Rel-12","C1,C3,IETF","2012-12-07","2014-12-09",1,"CP-120905","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","-","Stage 3",58,30,null,null,"2012-11-19","2012-12-06"]
[5186,660038,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id)","IMSProtoc6",2,"Rel-12","C1-IETF","2014-09-12","2014-12-09",1,"CP-120905",null,"christer.holmberg@ericsson.com",null,"work in progress. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 25%->100; 9/4/21: RFC 7989 added;","draft-ietf-insipid-session-id; RFC 7989",65,34,null,null,"2014-12-04","2021-04-09"]
[5189,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[5190,580017,"   SAE Protocol Development (Stage 3) - Phase 3","SAES3-CT1",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[5195,580022,"   Stage 3 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C4","2012-12-10","2013-06-14",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#60 completed","29.328; 29.329; 29.364",58,30,null,null,"2012-11-19","2013-05-29"]
[5198,580123,"   Stage 3 for Diameter based interface between SGSN and SMS central functions","Dia_SGSN_SMS",2,"Rel-12","C4","2012-12-10","2013-12-06",1,"CP-130437","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#62 completed","29.002; 29.230; 29.272; 29.305; 29.336; 29.337; 29.338",58,30,null,null,"2012-11-20","2013-11-18"]
[5201,590012,"eMBMS restoration procedures","eMBMS_Rest",1,"Rel-12","C4,C3","2013-03-01","2014-09-11",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed. Linked to Rel-9 MBMS support in EPS (MBMS_EPS). Rel-10 CT Features EPC Node Restoration with/out Idle mode Signalling Reduction (ISR) activated (EPC_NR/EPC_NR_ISR)","Stage 3",59,30,null,null,"2013-03-07","2013-11-18"]
[5204,590014,"Dual Radio VCC enhancements (Stage 2/3)","eDRVCC",1,"Rel-12","C1,C3.S2","2012-09-19","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed. Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). Stage 3 linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056 (Stage 2 in TS 23.237). 2/4/15: acronym changed to eDRVCC","Stage 2/3",59,30,null,null,"2013-02-16","2013-11-18"]
[5209,600009,"CT aspects of Signalling of Image Size (Stage 2/3)","SIS_CT",1,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[5212,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162; 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[5215,610004,"Proxy Call Session Control Function (P-CSCF) restoration enhancements (Stage 2/3)","PCSCF_RES",1,"Rel-12","C4,C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 updated WID CP-140443=>CP-140490. Based TR 29.806, solutions B and D are selected for standardization. Dec.14: 95->100","Stage 2/3",61,31,null,null,"2013-08-10","2014-12-04"]
[5217,640999,"   Common for HSS & PCRF solutions","PCSCF_RES",2,"Rel-12","C4,C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[5220,650002,"      CT3 part of Common for HSS & PCRF solutions","PCSCF_RES",3,"Rel-12","C3","2013-05-03","2014-12-09",1,"CP-140490","CP-140687","Huawei","susan.shishufeng@huawei.com","CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687","29.061; 29.165",65,33,null,null,"2013-08-10","2014-06-03"]
[5224,640997,"   PCRF based solution","PCSCF_RES",2,"Rel-12","C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Huawei","susan.shishufeng@huawei.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[5227,610008,"Updating IMS to conform to RFC 6665 (Stage 3)","UP6665",1,"Rel-12","C1,C3","2013-09-09","2015-03-13",1,"CP-130717","-","BlackBerry","Andrew Allen (aallen@blackberry.com)","Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes","Stage 3",61,31,null,null,"2013-07-25","2013-09-09"]
[5230,670033,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-clarifications)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date; 9/4/21: RFC 7647 added;","draft-ietf-sipcore-refer-clarification; RFC 7647",67,34,null,null,"2015-03-13","2021-04-09"]
[5235,620204,"   CT3 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C3","2013-12-09","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#65 completed",29.164999999999999,62,32,null,null,"2013-11-18","2014-08-01"]
[5238,630102,"   CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3)","ICEH248",2,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#65 completed","23.333; 23.334; 29.232; 29.238; 29.332; 29.333; 29.334",63,32,null,null,"2014-01-29","2014-07-28"]
[5239,630202,"   CT3 part of ICE impacts on IMS H.248 profiles (Stage 2)","ICEH248",2,"Rel-12","C3","2014-03-05","2014-06-13",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#64 completed","29.162; 29.163; 29.292",63,32,null,null,"2014-01-29","2014-06-03"]
[5243,630008,"Support of ALT-C attribute","ALTC",1,"Rel-12","C4,C1,C3","2014-03-10","2014-12-09",1,"CP-140191","-","Orange","lionel.morand@orange.com","SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network.","-",63,32,null,null,"2014-01-29","2014-03-03"]
[5246,630308,"   CT3 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C3","2014-03-10","2014-12-09",1,"CP-140191","CP-140563","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140563. Dec.14: 0->100",29.161999999999999,63,32,null,null,"2014-01-29","2014-12-04"]
[5250,640004,"Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",1,"Rel-12","C1,C3","2014-06-13","2014-12-09",1,"CP-140285","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases.","-",64,33,null,null,"2014-04-07","2014-04-07"]
[5252,640204,"   CT3 part of Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140285","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","CP#65 completed","29.163; 29.165; 29.292",64,33,null,null,"2014-04-07","2014-07-31"]
[5257,640008,"Unstructured Supplementary Service Data (USSD) method selection (Stage 3)","USSD_MS",1,"Rel-12","C1","2014-06-11","2014-06-13",1,"CP-140450","-","Ericsson","ivo.sedlacek@ericsson.com","CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain)","24.173; 24.390; New 24.391",64,33,null,null,"2014-04-07","2014-06-12"]
[5261,641011,"   (IETF) Overload Control for PCC based Diameter applications","DOCME-PCC",2,"Rel-12","C3-IETF","2014-06-13","2014-12-09",1,"CP-140405","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress¦7/3/16: 50%->100","draft-ietf-dime-ovli",64,33,null,null,"2014-06-10","2016-03-07"]
[5265,610016,"   Test part: Introduction of ER-GSM band for GSM-R","RT_ERGSM",2,"Rel-12","G3new","2013-09-02","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","GP#61 completed","51.010; 51.021",59,31,null,null,"2013-09-04","2014-03-07"]
[5266,530202,"   CT1 part of Introduction of ER-GSM band for GSM-R","RT_ERGSM",2,"Rel-12","C1","2011-09-28","2013-12-06",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","CP#62 completed. Added ERGSM capability indication (24.008 CR#2469R1)",24.007999999999999,53,27,null,null,"2011-09-06","2013-11-19"]
[5269,570202,"   CT part: Downlink Multi Carrier GERAN","DMCG",2,"Rel-12","C1","2012-09-10","2014-09-11",1,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","CP#65 completed",24.007999999999999,55,29,null,null,"2012-09-03","2014-07-28"]
[5272,590333,"   CT1 introduction of MS capability support for MS supporting MSRD for VAMOS","MSRD_VAMOS",2,"Rel-12","C1","2013-03-01","2013-12-06",1,"GP-130849","-","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","CP#62 completed",24.007999999999999,57,30,null,null,"2013-03-04","2014-08-29"]
[5278,620314,"   CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3)","NewToN",2,"Rel-12","C1","2013-11-22","2014-12-09",1,"GP-131139","CP-140604","Ericsson","Mårten Sundberg","CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604. 3/3/15: 100% cpltd.",24.007999999999999,60,32,null,null,"2013-11-22","2015-03-03"]
[5280,550116,"   Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS","HSPA_LTE_measRP_MIMO-Perf",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-120368","RP-131507","Vodafone","luis.anaya@vodafone.com","RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI)","new 37.977",55,28,null,null,"2012-02-23","2013-08-30"]
[5283,590019,"Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE","LCS_BDS",1,"Rel-12","R2,R3,R4,R5","2013-03-04","2015-06-15",1,"RP-130416","-","CATR","Ying Du (duying1@catr.cn)","BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2","UTRA; LTE",59,30,null,null,"2013-02-26","2013-03-05"]
[5287,590419,"   Perf. part: Support for BeiDou Navigation Satellite System (BDS) for LTE","LCS_BDS-LTE-Perf",2,"Rel-12","R4","2013-03-07","2014-06-13",1,"RP-130416","RP-140713","ZTE","Ling Soonleh (soonleh.ling@zte.com.cn)","RP#64 completed",36.170999999999999,59,30,null,null,"2013-02-26","2014-06-12"]
[5291,620211,"   GERAN1 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",2,"Rel-12","G1","2013-11-22","2014-08-29",1,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#63 completed","43.059; 45.005",60,32,null,null,"2013-11-22","2014-08-29"]
[5292,630009,"   Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new","LCS_BDS_GERAN-GERAN3new",2,"Rel-12","G3new","2014-03-01","2015-03-13",0.8,"GP-140244",null,"CATR","Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn","Dec.14: 25->80%, CD: 11/14->03/15","51010-1; 51.010-2; 51.010-7",61,32,null,null,"2014-03-01","2014-08-29"]
[5295,600119,"   Deleted - Core part: New Base Station specification structure","BSspec_struc-Core",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-130851","RP-131513","Ericsson","johan.skold@ericsson.com","RP#62 stopped (at 20% completion)","25.104; 25.105; 36.104; 37.104; 37.810; New 37.811 (New BS specification structure); New 37.xya (New RF core specification)",60,31,"RP-62","PCG-32","2013-06-17","2013-11-29"]
[5300,670047,"   UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-UEConTest",2,"Rel-12","R5","2015-03-16","2015-12-15",1,"RP-150835","RP-151163","Ericsson",null,"03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163¦1/1/16",null,67,34,null,null,"2015-04-01","2016-01-01"]
[5303,600127,"   Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON-Core",2,"Rel-12","R3","2013-06-18","2014-06-13",1,"RP-130831","RP-140745","China Telecom","Jinlian_wu@189.cn","RP#64 completed","36.300; 36.413",60,31,null,null,"2013-06-17","2014-06-12"]
[5306,620042,"Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon",1,"Rel-12","R4,R2","2013-12-15","2018-09-14",0.99,"RP-132061","-","Ericsson","christopher.callender@ericsson.com","-","UTRA; LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[5309,700064,"   UE Conformance Test Aspects - Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-UEConTest",2,"Rel-12","R5","2015-12-15","2018-09-14",1,"RP-171889",null,"Ericsson",null,"22/3/16: Compl:0%->4%1/7/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: Com 21/3/17: Compl ¦2 ;; 11/10/20: 35%->100",null,70,36,null,null,"2016-01-01","2020-10-11"]
[5314,640106,"      CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3)","UTRA_LTE_WLAN_interw-CT",3,"Rel-12","C1","2014-09-09","2014-12-09",1,"CP-140623","CP-140720","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd.","24.008; 24.301; 24.302; 24.312",64,33,null,null,"2014-04-07","2015-03-03"]
[5317,551000,"Rel-12 LTE Carrier Aggregation","LTE_CA_Rel-12",1,"Rel-12","R4","2011-09-19","2016-12-15",1,"-","-","-","-","LTE_CA_Rel-12","LTE",58,30,null,null,"2012-12-14","2012-12-14"]
[5318,530025,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7",2,"Rel-12","R4","2011-09-19","2014-09-12",1,"RP-141487","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band CA 2DL","LTE",53,27,null,null,"2011-09-15","2013-12-07"]
[5322,530129,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25-Core",3,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","RP-130563","Sprint","George.Cummings@sprint.com","RP#60 completed. TR 36.841 for 1-step Approval","36.101; 36.104; 36.133; new 36.833-2-25",53,27,null,null,"2011-09-15","2013-06-07"]
[5325,550110,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL-Core",3,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","RP-130098","SK Telecom","Seungpyo Hong","RP#59 stopped (covered by new WI LTE_CA_2UL-A4)","36.101; 36.104; 36.133; 36.307; new generic 36.851",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[5329,550111,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3-Core",3,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","RP-131573","SK Telecom","haesung.park@sk.com","RP#62 completed","36.101; 36.104; 36.133; new 36.833-2-03",55,28,null,null,"2012-02-23","2013-12-02"]
[5331,560015,"   Deleted - LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1",2,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-130298","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Intra-band C ","LTE",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[5337,560017,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4",2,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-130175","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band 1 UL","LTE",56,29,null,null,"2012-06-13","2012-09-07"]
[5340,570012,"   LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29",2,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","-","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-03"]
[5343,570013,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[5344,570113,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26-Core",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","RP-130527","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#60 completed. Updated WID RP-130199=>RP-130658","36.101; 36.104; 36.133; 36.307; new generic 36.851",57,29,null,null,"2012-09-03","2013-06-07"]
[5348,570214,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19-Perf",3,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130198","RP-130526","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141; 36.307",57,29,null,null,"2012-09-03","2013-06-08"]
[5351,570215,"      Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39","LTE_CA_B38_B39-Perf",3,"Rel-12","R4","2012-09-11","2012-12-07",1,"RP-121178","RP-121625","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#58 stopped at 0% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41)","36.133; 36.141",57,29,"RP-58","PCG-30","2012-09-03","2012-12-11"]
[5355,570018,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8",2,"Rel-12","R4","2012-02-02","2013-06-14",1,"RP-130181","-","Softbank Mobile","Kenichi Kihara","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-11-28"]
[5357,570218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Perf",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130181","RP-130516","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.141; 36.307",57,29,null,null,"2012-09-03","2013-06-04"]
[5363,580232,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26-Perf",3,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","RP-131006","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.141; 36.307",58,30,null,null,"2012-12-10","2013-08-28"]
[5366,580233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41-Perf",3,"Rel-12","R4","2012-12-14","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#63 completed","36.133; 36.141",58,30,null,null,"2012-12-10","2014-03-05"]
[5370,580035,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","-","Ericsson","christian.bergljung@ericsson.com","Intra-band NC","LTE",58,30,null,null,"2012-12-10","2013-02-28"]
[5371,580135,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-130813","RP-131575","Ericsson","christian.bergljung@ericsson.com","RP#62 completed","36.101; 36.104; 36.133; new 36.833-2-07",58,30,null,null,"2012-12-10","2013-12-02"]
[5374,580136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-131679","RP-131567","NII Holdings","bill.shvodian@nii.com","RP#62 completed","36.101; 36.104; new 36.833-1-27",58,30,null,null,"2012-12-10","2013-12-06"]
[5378,590222,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Perf",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130524","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101; 36.104; 36.133; 36.141; 36.307",59,30,null,null,"2013-02-26","2013-02-26"]
[5383,590125,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Core",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131549","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.101; 36.104; 36.133; new generic 36.851",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[5385,590029,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140475","-","Huawei","Liu Ye (leo.liuye@huawei.com)","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[5389,590128,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-130327","RP-141732","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[5392,590123,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140853","RP-141732","Ericsson","christian.bergljung@ericsson.com ","¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[5396,590231,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141967","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5397,590026,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-141195","-","NTT DOCOMO","kei.andou.ye@nttdocomo.com","Inter-band CA 2UL. RP#65 updated WID RP-131146=>RP-141195. Changed Rapp Renesas=>Broadcom=>NTT DOCOMO","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[5400,590027,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39",2,"Rel-12","R4","2013-03-04","2014-03-06",1,"RP-131171","-","China Mobile","Li Nan (linan@chinamobile.com)","Intra-band C 2DL/2UL","LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[5405,600023,"   Deleted -LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL",2,"Rel-12","R4","2013-06-19","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","Intra-band NC 2UL","LTE",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[5408,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[5411,600025,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band C CA","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[5414,600026,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23",2,"Rel-12","R4","2013-06-18","2014-06-13",1,"RP-131700","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2013-12-19"]
[5419,600228,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131159","RP-131706","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.141; 36.307",60,31,null,null,"2013-06-05","2013-12-02"]
[5420,600029,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5423,600030,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130675","-","AT&T","marc.grant@att.com","Inter-band 2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5427,600131,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30-Core",3,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. TR 36.853v200 for Approval","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5431,600232,"      Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131130","RP-131591","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131652 discussion","36.101; 36.104; 36.133; 36.141; 36.307",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[5434,600233,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[5436,600134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30","LTE_CA_B4_B5_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141213","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131698=>RP-141213","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5442,600136,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131699=>RP- 141215","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5445,600137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed. Updated RP-131684=>RP-141434","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-21"]
[5446,600237,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101; 36.133; 36.141; 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[5449,600238,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141435","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed","36.101; 36.133; 36.141; 36.307",60,31,null,null,"2013-06-17","2014-09-21"]
[5453,610017,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","-","Huawei","Liehai Liu (liuliehai@huawei.com)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[5457,610118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Core",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131543","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101; 36.104; 36.133; new generic 36.851",61,31,null,null,"2013-09-07","2013-12-02"]
[5462,610020,"   LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11",2,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","-","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","Inter-band CA 2DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[5464,610220,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","RP-141084","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#65 completed","36.141; 36.307",61,31,null,null,"2013-09-07","2014-09-08"]
[5468,610022,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL",2,"Rel-12","R4","2013-09-09","2015-03-13",1,"RP-140100","-","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","Intra-band contig. CA 3DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[5471,610023,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2",2,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","-","Ericsson","imadur.rahman@ericsson.com","Intra-band non-contig. CA 2DL","LTE",61,31,null,null,"2013-09-07","2013-09-07"]
[5475,620118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.101; 36.104; 36.133; new generic 36.851",62,32,null,null,"2013-12-07","2014-09-08"]
[5476,620218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","RP-141084","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","RP#65 completed","36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5479,620219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28-Perf",3,"Rel-12","R4","2013-12-12","2014-12-15",1,"RP-141803","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.133; 36.141",62,32,null,null,"2013-12-07","2015-01-12"]
[5484,620121,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed","36.101; 36.104; 36.133; new generic 36.851",62,32,null,null,"2013-12-07","2014-06-20"]
[5487,620122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27-Core",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#63 completed. Updated WID RP-131752=>RP-140119","36.101; 36.104; 36.133; 36.307; New generic 36.851",62,32,null,null,"2013-12-07","2014-03-13"]
[5491,620272,"      Perf. part:LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","RP#63 completed",36.140999999999998,62,32,null,null,"2013-12-09","2014-03-05"]
[5494,620224,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","RP-141084","KT","Ilwhan Kim (ilwhan.kim@kt.com)","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-22"]
[5497,620225,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed","36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-22"]
[5499,620126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5502,620127,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12","LTE_CA_B2_B4_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140189","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-30"]
[5505,620128,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140190","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5510,620030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5513,620031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20","LTE_CA_B3_B7_B20",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141224","-","Vodafone","luis.anaya@vodafone.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-21"]
[5517,620133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","RP-141084","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5519,620034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5524,620235,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5525,620037,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","-","CATT","Yuexia Song (songyuexia@catt.cn)","Intra-band contig. CA 2DL/2UL","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5528,620036,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","-","Orange","Olfa BEN HADDADA","Intra-band contig. CA 2DL/2UL","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5532,620138,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL-Core",3,"Rel-12","R4","2013-12-09","2014-09-11",1,"RP-140101","RP-141084","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101; 36.104; 36.133; 36.307; new 36.833-6-xy",62,32,null,null,"2013-12-07","2014-09-08"]
[5536,620239,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","RP-140569","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#64 completed","36.141; 36.307",62,32,null,null,"2013-12-07","2014-06-12"]
[5539,620250,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Perf",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.141; 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[5541,620151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed. Updated WID RP-141017=>RP-141222","36.101; 36.104; 36.133; new generic 36.851 (2 Band CA with 1UL); 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5547,620153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL); 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2015-01-12"]
[5550,630122,"      Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700_B29_BWset-Core",3,"Rel-12","R4","2014-03-03","2014-03-06",1,"RP-140084","RP-140428","AT&T","marc.grant@att.com","RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected","36.101; 36.307",63,32,null,null,"2014-03-10","2014-03-12"]
[5551,630023,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20_BWset",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140447","-","NSN","iwajlo.angelow@nsn.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5554,630124,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140448","RP-140569","NSN","iwajlo.angelow@nsn.com","RP#64 completed","36.101; 36.851",63,32,null,null,"2014-03-10","2014-06-20"]
[5559,630226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_","36.141; 36.307",63,32,null,null,"2014-03-10","2015-03-10"]
[5562,630227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.141; 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[5567,630129,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","RP-140569","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#64 completed. Updated WID RP-140453=>RP-140948","36.101; 36.104; 36.133; New 36.833-5-40",63,32,null,null,"2014-03-10","2014-06-20"]
[5570,630135,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset-Core",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed. Updated WID RP-140987=>RP-141235 (removed Perf. Part)","36.101; generic 36.850",63,32,null,null,"2014-03-10","2014-09-21"]
[5573,630136,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","RP-141084","Huawei","leo.liuye@huawei.com","RP#65 completed","36.101; 36.104; 36.851",63,32,null,null,"2014-03-10","2014-09-08"]
[{"$f":"A5576+1","v":5576},630137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141709","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed. Updated WID RP-140116=>RP-141709","36.101; 36.104; 36.133; 36.141; 36.307; generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-22"]
[5580,630238,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141236","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[5581,630045,"   Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140452","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[5585,640120,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4_BWset2-Core",3,"Rel-12","R4","2014-06-15","2014-09-12",1,"RP-140599","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","Dec 14: Prev CD:Fri 12/09/14¦Prev %:100%, title changed. Mar 15: Acronym changed to LTE_CA_B2_B4_BWset2-Core_","36.101; 36.851",64,33,null,null,"2014-06-16","2015-03-10"]
[5589,640027,"   E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","-","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","LTE","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5592,640128,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2014-09-08"]
[5596,640229,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141; 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5599,640230,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","RP-150013","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","CD:Thu 11/12/14->Tue 15/03/16¦Compl:50%->70%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: CD:Tue 15/03/16->Sun 15/03/15 1st Apr 15: Stat Rep: RP-141732->RP-150013","36.141; 36.307",64,33,null,null,"2014-06-16","2015-04-01"]
[5602,640231,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","RP-141084","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","RP#65 completed","36.141; 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5604,640135,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated WID RP-140950=>RP-141127",36.100999999999999,64,33,null,null,"2014-06-16","2014-09-08"]
[5607,650110,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28-Core",3,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#65 WID approved & completed. Triggered by revised Rel-13 WID RP-140451=>RP-141610 (take out B18_B28 for Rel-12 from the Rel-13 B1_B18_B28)","36.101; 36.104; 36.133",65,33,null,null,"2014-03-10","2014-09-10"]
[5611,630234,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5615,630040,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5618,630041,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","-","Intel","xinrong.wang@intel.com ","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5622,630142,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5624,630043,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26","LTE_CA_B1_B3_B26",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140194","-","China Telecom","Zhao Dong (zhaodong@ctbri.com.cn)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5627,630044,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141610","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5630,640023,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","-","Rogers Wireless","pavlo.nebesny@rci.rogers.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5633,640024,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","-","Rogers Wireless","pavlo.nebesny@rci.rogers.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5638,640226,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142301","RP-141732","China Mobile","PAN Qun (panqun@chinamobile.com)","¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5641,640233,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5644,640234,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5646,650146,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.307; New 36.833-x-yz ",65,33,null,null,"2014-06-16","2015-01-12"]
[5652,650150,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","RP-141732","AT&T","marc.grant@att.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5653,650250,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29","LTE_CA_B2_B2_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141448","RP-141732","AT&T","marc.grant@att.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5656,650252,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5659,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[5664,640002,"   Test Part: LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band-UEConTest",2,"Rel-12","R5","2014-06-15","2014-12-15",1,"RP-140643","RP-141773","Ericsson","fredrik.sundstrom@ericsson.com","¦Stat Rep: RP-141166->RP-141773","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1",64,33,null,null,"2014-05-28","2015-01-12"]
[5667,570219,"   Perf. part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Perf",2,"Rel-12","R4","2012-09-13","2013-09-06",1,"RP-121414","RP-131070","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#61 completed","36.133; 36.141; 37.141",57,29,null,null,"2012-09-03","2013-08-30"]
[5672,670045,"   UE Conformance Test Aspects - Further DL MIMO Enhancement for LTE-Advanced","LTE_eDL_MIMO_enh-UEConTest",2,"Rel-12","R5","2015-03-16","2016-03-15",1,"RP-150071","RP-151189","ZTE",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150606 29/09/15: Compl:10%->70% 29/09/15: Stat Rep: RP-150606->RP-1511891/1/16: Compl:70%->75%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[5675,570225,"   Deleted - Perf. part: New Carrier Type for LTE","LTE_NCT-Perf",2,"Rel-12","R4","2012-09-17","2013-09-06",1,"RP-122028","RP-130985","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 0% completion","36.101; 36.104; 36.133; 36.141",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[5678,580227,"   Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Perf",2,"Rel-12","R4","2012-12-15","2015-09-15",1,"RP-121772","RP-151447","CATT","Zukang Shen (shenzukang@catt.cn)","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141342->RP-141948 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141948->RP-150154 03/07/15: Compl:55%->95% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150","36.101; 36.104; 36.133; 36.141",58,30,null,null,"2012-09-03","2015-09-29"]
[5679,690072,"   UE Conformance Test Aspects - Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-UEConTest",2,"Rel-12","R5","2015-09-15","2018-03-15",1,"RP-151398",null,"CATT",null,"tested: REL-12 WI LTE_TDD_eIMTA-Core;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15% 21/3/ 19 827/3/",null,69,35,null,null,"2015-09-29","2018-03-27"]
[5685,580231,"   Perf. part: 8 Rx Antennas for LTE UL","LTE_UL_8Rx-Perf",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","RP-131523","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","RP#62 completed","36.104; 36.141",58,30,null,null,"2012-09-03","2013-11-29"]
[5686,600013,"LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD",1,"Rel-12","R1,R2,R4","2013-04-12","2014-12-15",1,"RP-140465","-","Nokia","lars.e.lindh@nokia.com","-","LTE",60,31,null,null,"2013-06-17","2014-03-13"]
[5690,600114,"   Core part: LTE Coverage Enhancements","Cov_Enh_LTE-Core",2,"Rel-12","R1,R2,R4","2013-03-01","2014-06-13",1,"RP-130833","RP-140683","China Telecom","Xiaoming She (shexm@ctbri.com.cn)","RP#64 completed","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.300; 36.321; 36.331",60,31,null,null,"2013-06-17","2014-06-12"]
[5694,610124,"   Core part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Core",2,"Rel-12","R2,R1,R3,R4","2013-09-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Thu 18/06/15->Mon 15/06/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821","36.133; 36.214; 36.300; 36.304; 36.306; 36.331; 36.413; 36.423; 37.320",61,31,null,null,"2013-09-07","2015-01-12"]
[5698,620240,"   Perf. part: Dual Connectivity for LTE","LTE_SC_enh_dualC-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141797","RP-150791","NTT DOCOMO","kunihiko.teshima.hg@nttdocomo.com","¦Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791","36.101; 36.104; 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[5701,680070,"   UE Conformance Test Aspects - Dual connectivity for LTE","LTE_SC_enh_dualC-UEConTest",2,"Rel-12","R5","2015-06-15","2017-09-15",1,"RP-150840",null,"Ericsson",null,"tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16¦ ;",null,68,35,null,null,"2015-07-03","2017-09-19"]
[{"$f":"A5704+1","v":5704},620241,"   Perf. part: E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141459","RP-150690","Huawei","Elean FAN (fanxiaoan@huawei.com)","¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-","36.101; 36.104; 36.133; 36.141",62,32,null,null,"2013-12-09","2015-06-18"]
[5707,620147,"   Core part: Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB-Core",2,"Rel-12","R3,R1","2013-12-15","2014-12-12",1,"RP-140983","RP-141804","Samsung","Sung Hwan Won (sunghwan.won@samsung.com)","CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-140597->RP-141804","36.300; 36.423",62,32,null,null,"2013-12-07","2015-01-12"]
[5709,630131,"   Core part: Smart Congestion Mitigation in E-UTRAN","SCM_LTE-Core",2,"Rel-12","R2","2014-03-06","2014-09-12",1,"RP-140434","RP-141292","LG Electronics","youngdae.lee@lge.com","RP#65 completed",36.331000000000003,63,32,null,null,"2014-03-10","2014-09-21"]
[5713,630032,"Positioning Enhancements for RF Pattern Matching in E-UTRA","LCS_LTE_RFPMT",1,"Rel-12","R3,R2","2014-04-25","2014-06-13",1,"RP-140177","-","Polaris Wireless","Gordon Scot (sgordon@polariswireless.com)","follow-up of TR 36.809 FS_LCS_LTE_RFPMT","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5716,630146,"   Core part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Core",2,"Rel-12","R1,R2,R4,R3","2014-07-11","2014-12-15",1,"RP-141634","RP-141866","MediaTek","Craig.Burnet@mediatek.com","CD:Mon 08/12/14->Mon 15/12/14¦Compl:95%->100%¦Stat Rep: RP-141621->RP-141866","36.211; 36.213; 36.300; 36.331; 36.423",63,32,null,null,"2014-03-10","2015-01-12"]
[5720,630147,"   Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO","LTE_SUMIMO_RX-Perf",2,"Rel-12","R4","2014-03-06","2015-03-13",1,"RP-140520","RP-150229","Huawei","Qian Cheng (Q.Cheng@Huawei.com)","CD:Fri 13/03/15->Sun 15/03/15¦Compl:50%->80%¦Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229",36.100999999999999,63,32,null,null,"2014-03-10","2015-04-01"]
[5724,580228,"   Perf. part: HSPA signalling enhancements for more efficient resource usage for LCR TDD","LCR_TDD_HSPA_sign_enh-Perf",2,"Rel-12","R4","2012-12-11","2013-09-06",1,"RP-121984","RP-130968","CATT","Yanping Xing (xingyanping@catt.cn)","RP#61 completed",25.102,58,30,null,null,"2012-12-10","2013-08-30"]
[5727,610025,"Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh",1,"Rel-12","R1,R2,R3,R4","2013-09-15","2016-06-15",1,"RP-140771","-","Qualcomm","arjunb@qti.qualcomm.com","Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2014-09-09"]
[5729,610225,"   Perf. part: Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh-Perf",2,"Rel-12","R4","2013-09-15","2014-12-15",1,"RP-140771","RP-141970","Qualcomm","arjunb@qti.qualcomm.com","¦Stat Rep: RP-141137->RP-141970","25.101; 25.104; 25.133",61,31,null,null,"2013-09-07","2015-01-12"]
[5732,610126,"   Core part: UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob-Core",2,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","RP-140636","Huawei","Xudong Yang (yangxudong@huawei.com)","RP#64 completed. TS 25.300v100 for 1-step Approval","25.101; 25.104; 25.133; 25.141; 25.304; 25.306; 25.331; 25.433; new 25.300",61,31,null,null,"2013-09-07","2014-06-12"]
[5735,620154,"   Core part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Core",2,"Rel-12","R1","2013-12-06","2014-09-12",1,"RP-141701","RP-141702","Huawei","carmela.cozzo@huawei.com","RP#65 completed. Updated WID RP-140463=>RP-141701","25.101; 25.211; 25.212; 25.213; 25.214; 25.300; 25.302; 25.306; 25.308; 25.319; 25.331; 25.423; 25.433",62,32,null,null,"2013-12-09","2014-09-15"]
[5738,620155,"   Core part: Enhanced Broadcast of System Information","UTRA_SIBenh-Core",2,"Rel-12","R2,R1,R3,R4","2013-12-06","2014-09-12",1,"RP-140131","RP-141230","Ericsson","martin.van.der.zee@ericsson.com","RP#65 completed","25.211; 25.212 ; 25.213; 25.214; 25.301; 25.302; 25.304; 25.306; 25.321; 25.331; 25.433",62,32,null,null,"2013-12-09","2014-09-15"]
[5743,560018,"(Small) Technical Enhancements and Improvements for Rel-12","TEI12",1,"Rel-12","SP,CP,RP,GP","2012-12-25","2014-09-16",1,"-","-","-","-","-","-",56,29,null,null,"2012-07-13","2013-12-06"]
[5746,0,"Release 12 Studies","-",1,"Rel-12","SP,CP,GP,RP","2013-08-05","2014-09-16",0.8,"-","-","-","-","-","-","-","-",null,null,"2011-09-08","2011-09-15"]
[5750,500035,"Study on Continuity of Data Sessions to Local Networks","FS_CSN",1,"Rel-12","S1","2010-12-16","2011-12-14",1,"SP-100885","-","NEC","joerg.swetina@neclab.eu","SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC)",22.896000000000001,50,26,null,null,"2010-11-25","2011-11-29"]
[5751,500036,"Study on non-MTC Mobile Data Applications Impacts","FS_MODAI",1,"Rel-12","S1","2010-12-16","2011-12-14",1,"SP-100889","-","Huawei, China Mobile","Amar Deol (adeol@huawei.com), Gang Li","SP#54 completed. Linked to UID_490036 SA2 Rel-11 TR 23.843 Study on Core Network Overload solutions (FS_CNO)",22.800999999999998,50,26,null,null,"2010-11-25","2011-11-29"]
[5757,490134,"   SA1 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S1","2010-09-23","2011-09-21",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#53 completed",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-08"]
[5758,490234,"   SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S2","2010-09-23","2012-06-20",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#56 completed. TR 23.844v100 for Information and Approval",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-14"]
[5764,510061,"Study on S2a Mobility based On GTP and WLAN access to EPC","FS_SaMOG",1,"Rel-12","S2","2011-03-23","2013-09-11",1,"SP-120426","-","ZTE","Tricci So (tso@zteusa.com)","SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI",23.852,51,26,null,null,"2011-02-21","2013-07-25"]
[5766,560038,"Study on Application Based Charging","FS_ABC",1,"Rel-12","S2","2012-06-18","2013-03-06",1,"SP-120271","-","Allot","Alla Goldner (agoldner@allot.com)","SP#59 completed. Linked to Rel-11 Feature UID_500032 Service Awareness and Privacy Policies (SAPP)",23.8,56,29,null,null,"2012-06-04","2013-02-27"]
[5769,410243,"   SA2 part of Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",2,"Rel-12","S2","2008-09-18","2012-12-12",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","SP#43 TR 23.861v100 for Information. SP#56 Rel-9 TR 23.861v130 renamed & progressed under new Study FS_NBIFOM. SP#58 completed the FS_MAPIM part of TR 23.861 (TR continued under FS_NBIFOM).",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5772,530047,"Deleted - Study on Firewall traversal (Stage 2)","FS_Fire",1,"Rel-12","S3","2011-06-17","2014-09-17",1,"SP-120849","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#65 stopped. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043",33.83,53,27,"SP-65","PCG-33","2011-07-19","2014-05-21"]
[5777,470050,"Study on version handling","FS_OAM_VH",1,"Rel-12","S5","2010-03-25","2012-12-12",1,"SP-100082","-","Ericsson","thomas.tovinger@ericsson.com","SP#58 completed",32.83,47,24,null,null,"2010-02-12","2012-11-21"]
[5780,560032,"Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","FS_SON_NM_CCO",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140028","-","Ericsson","robert.petersen@ericsson.com","SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060)",32.835999999999999,56,29,null,null,"2012-04-18","2014-08-25"]
[5781,560336,"Study on WLAN management","FS_WLAN_OAM",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-150408","-","Intel","joey.chou@intel.com","SP#65 revised WID SP-130042=>SP-140536 (split into Rel-12 Study & Rel-13 normative WI). Changed Title from \"TR on WLAN impacts to Type-2 management interface to the 3GPP Network Manager\". TR 32.841v200 for Approval. Completed¦14/09/15: WID:SP-140536->","28.680; 28.681; 28.682; 28.683; 28.403",56,29,null,null,"2012-06-12","2015-09-14"]
[5786,610010,"Study on Technical aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks","FS_REVOLTE_IMS",1,"Rel-12","C3","2013-09-09","2014-12-09",1,"CP-130774","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","CP#65 completion 09/14=>12/14. CP#64 TR 29.949v100 for Information.Dec.14:95->100",29.949000000000002,61,31,null,null,"2013-08-10","2014-12-04"]
[5788,620002,"Study on Shared Data Update for Multiple Subscribers","FS_SHARED_SubData_UPD",1,"Rel-12","C4","2013-12-06","2014-12-09",1,"CP-130809","-","Huawei","Susan Shi (susan.shishufeng@huawei.com)","CP#65 TR 29.854v200 for Approval. Completion 09/14=>12/14. Dec.14: 80->85%. Mar.15: 100%",29.853999999999999,62,32,null,null,"2013-11-19","2015-03-04"]
[5792,500016,"Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN","FS_LCS_LTE_RFPMT",1,"Rel-12","R4","2010-12-10","2013-09-06",1,"RP-120885","RP-131082","Polaris Wireless","Scot Gordon (sgordon@polariswireless.com)","RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005","LTE 36.809",50,26,null,null,"2010-12-10","2013-08-28"]
[5795,570023,"Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN","FS_LTE_SC_enh_req",1,"Rel-12","RP","2012-09-11","2012-12-07",1,"RP-121418","RP-121651","China Mobile","Hai TANG (tanghai@chinamobile.com)","RP#58 completed. TR 36.932 v100 for Information and Approval","LTE 36.932",57,29,null,null,"2012-09-03","2012-12-06"]
[5799,580042,"Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE","FS_LTE_3D_channel",1,"Rel-12","R1","2012-12-10","2014-09-12",1,"RP-141237","RP-141206","Nokia Networks","bishwarup.mondal@nsn.com","RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network","LTE 36.873",58,30,null,null,"2012-12-10","2014-09-21"]
[5803,590018,"Study on Network-Assisted Interference Cancellation and Suppression for LTE","FS_LTE_NAICS",1,"Rel-12","R1,R4","2013-03-08","2014-03-06",1,"RP-130404","RP-132108","MediaTek","jeff.zhuang@mediatek.com","RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work","LTE 36.866",59,30,null,null,"2013-02-26","2014-03-14"]
[5806,610029,"Study on Smart Congestion Mitigation in E-UTRAN","FS_SCM_LTE",1,"Rel-12","R2","2013-09-09","2014-03-06",1,"RP-132092","RP-140102","LG Electronics","youngdae.lee@lge.com","RP#63 completed","LTE 36.848",61,31,null,null,"2013-09-07","2014-03-14"]
[5807,620044,"Study on RAN aspects of RAN Sharing Enhancements for LTE","FS_RSE-RAN_LTE",1,"Rel-12","R3","2013-12-06","2014-06-13",1,"RP-132116","RP-140746","NEC","Siva.Vakeesar@emea.nec.com","RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1)","LTE 36.856",62,32,null,null,"2013-11-27","2014-06-12"]
[5812,580047,"Study on RAN Enhancements for UMTS/HSPA and LTE Interworking","FS_HSPA_LTE_interworking",1,"Rel-12","R3","2012-12-10","2013-12-06",1,"RP-122036","RP-131612","China Unicom","Meng Zhang (zhangmeng68@chinaunicom.cn)","RP#62 completed. TR 37.852v100 for Information & Approval","UTRA; LTE 37.852",58,30,null,null,"2012-12-10","2013-12-03"]
[5814,580049,"Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","FS_UTRA_LTE_1980_2170_REG1",1,"Rel-12","R4","2012-12-11","2014-09-12",1,"RP-140505","RP-141099","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1","UTRA; LTE 37.846",58,30,null,null,"2012-12-10","2014-09-22"]
[5818,580039,"Study on Scalable UMTS FDD bandwidth","FS_UTRA_SCAL",1,"Rel-12","R1,R4","2012-12-10","2013-12-06",1,"RP-130221","RP-132035","China Unicom","Han Xiao (hanxiao91@chinaunicom.cn)","RP#62 completed. TR 25.701v200 for Approval","UTRA 25.701",58,30,null,null,"2012-12-10","2013-12-18"]
[5821,580043,"Study on Further Enhanced Uplink (EUL) enhancements","FS_EDCH_enh",1,"Rel-12","R2,R1,R3","2012-12-10","2013-12-06",1,"RP-130347","RP-131608","Ericsson","alessandro.caverni@ericsson.com ","RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.)","UTRA 25.700",58,30,null,null,"2012-12-10","2013-12-02"]
[5825,470051,"Advanced IP Interconnection of Services","IPXS",1,"Rel-11","S1,S2,C1,C3","2010-03-25","2012-09-12",1,"SP-100876","-","Telefónica","chris.friel@O2.com","CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS)","-",47,24,null,null,"2002-03-05","2012-11-19"]
[5829,530104,"      CT1 part of Stage 3 for Advanced IP Interconnection of Services","IPXS",3,"Rel-11","C1","2011-09-16","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed",24.228999999999999,53,27,null,null,"2011-08-29","2012-11-19"]
[{"$f":"A5832+1","v":5832},480130,"   Stage 1 for SIMTC","SIMTC",2,"Rel-11","S1","2010-06-10","2011-09-21",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#53 completed. SP#57 added MTC definitions in 21.905","22.368; 21.905 (MTC definitions)",48,25,null,null,"2010-05-28","2012-11-12"]
[5834,520021,"   BB1: Stage 2 Reachability Aspects of SIMTC","SIMTC-Reach",2,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682)","23.221; New 23.368",52,27,null,null,"2011-05-26","2012-11-12"]
[5837,520321,"      MTC Addressing","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 completed","23.221; New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5840,540014,"      MTC related interfaces and functional entities to support above features (MTCsp, etc.)","SIMTC-Reach",3,"Rel-11","S2","2011-12-14","2012-03-07",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#55 completed","New 23.682",54,28,null,null,"2011-11-25","2012-11-12"]
[5843,530206,"      CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","29.061; New 29.368",53,27,null,null,"2011-08-29","2015-01-22"]
[5848,530205,"      Stage 3 CS aspects for SIMTC ","SIMTC-CS",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed","Stage 3",53,27,null,null,"2012-06-15","2012-08-13"]
[5852,560102,"      CT1 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",3,"Rel-11","C1","2012-06-15","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed","23.040; 24.008; 24.011; 24.301; 29.018; 29.118",56,29,null,null,"2012-04-23","2012-08-14"]
[5855,530109,"      Core part: RAN overload control for Machine-Type Communications","SIMTC-RAN_OC-Core",3,"Rel-11","R2,R3","2011-09-19","2012-09-07",1,"RP-111373","-","Huawei","Jeff Gao (gaoyongqiang@huawei.com)","RP#57 completed","25.304; 25.331; 25.413; 36.304; 36.331; 36.413",53,27,null,null,"2011-09-15","2012-09-06"]
[5856,530209,"      Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 3",53,27,null,null,"2011-08-29","2012-08-24"]
[5860,540019,"   BB5: Charging of SIMTC (Stage 2/3)","SIMTC-CH",2,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-120848","-","Ericsson","patrik.teppo@ericsson.com","SP#58 completed","32.240; 32.251; 32.298; 32.299",54,28,null,null,"2011-10-24","2012-11-19"]
[5863,520222,"      Deleted - Small Data Transmissions (TS 22.368, 7.2.5)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5869,520223,"      Deleted - Lower Power Consumption (TS 22.368, 7.1.1)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[5871,530008,"      Deleted - Stage 3 (CS+PS) CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",3,"Rel-11","C1,C6","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","CP#54 work stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2011-12-13"]
[5874,490028,"   Deleted - TR on Security aspects of Machine-Type Communications","-",2,"Rel-11","S3","2009-12-10","2012-06-20",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","Was Rel-10 UID_460023 (Security for NIMTC). SP#56 stopped (activity transferred to Rel-12 Feature MTCe under UID_560722). ","New 33.868",49,25,"SP-56","PCG-29","2010-09-18","2012-11-12"]
[5878,480330,"   Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications","SIMTC",2,"Rel-11","S2","2010-06-10","2011-06-08",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#52 stopped","TBD",48,25,"SP-52","PCG-27","2010-05-28","2012-11-12"]
[5882,520003,"   Stage 3 for USSD simulation service in IMS","USSI",2,"Rel-11","C1,C3","2011-06-03","2012-12-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228","-",52,27,null,null,"2011-05-18","2012-11-19"]
[5885,490031,"QoS Control Based on Subscriber Spending Limits","QoS_SSL",1,"Rel-11","S1,S2,S5,C3","2010-09-23","2012-06-20",1,"SP-110519","-","Vodafone","mona.mustapha@vodafone.com","TSG#56 completed","-",49,25,null,null,"2010-09-02","2012-06-14"]
[5886,490131,"   Stage 1 for QoS Control Based on Subscriber Spending Limits","QoS_SSL",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-110519","-","Vodafone","mona.mustapha@vodafone.com","SP#53 completed. Use cases & service requirements to allow: 1) modification of QoS based on subscriber’s spending limits 2) enforcing of spending limits for roaming subscribers without having dedicated support in the visited network",22.114999999999998,49,25,null,null,"2010-09-02","2011-08-24"]
[5891,490132,"   TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S2","2010-09-23","2012-03-07",1,"SP-110347","-","Vodafone","Susana.Sabater@vodafone.com ","SP#55 completed","new 23.849",49,25,null,null,"2010-08-31","2012-03-05"]
[5894,530021,"Inclusion of Media Resource Broker (Stage 2/3)","MRB",1,"Rel-11","C1,C3,IETF","2011-09-16","2013-06-14",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032","Stage 2/3",53,27,null,null,"2011-08-25","2012-06-06"]
[5897,530321,"      CT1 part of Stage 3 for Inclusion of Media Resource Broker","MRB",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed","24.229; 29.165",53,27,null,null,"2011-08-25","2012-08-14"]
[5900,500030,"Non Voice Emergency Services","NOVES",1,"Rel-11","S1,S2","2010-12-16","2012-03-07",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES)","-",50,26,null,null,"2010-11-29","2012-03-16"]
[5904,510147,"   Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",2,"Rel-11","S1","2011-03-23","2011-09-21",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 completed ",22.228000000000002,51,26,null,null,"2011-02-21","2011-08-24"]
[5908,530011,"   Core Network aspects of Anonymous Call Rejection in the CS domain","ACR_CS-CN",2,"Rel-11","C4,C3","2011-09-14","2011-12-02",1,"CP-110587","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#54 completed","Stage 2/3",53,27,null,null,"2011-08-27","2011-08-27"]
[5911,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[5913,470022,"   TR on Stage 2 for BBAI","BBAI",2,"Rel-11","S2","2010-03-26","2012-06-20",1,"SP-120539","-","Ericsson","marco.spini@huawei.com","TR 23.839 not Approved in Rel-11¦progressed in Rel-12 under P4C-TI (UID_560824)","new 23.839",47,24,null,null,"2012-04-13","2013-04-15"]
[5916,530012,"   Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",2,"Rel-11","C1,C3,C4","2011-09-16","2012-12-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#58 completed","Stage 3",53,27,null,null,"2011-08-29","2012-11-17"]
[5920,530212,"      CT1 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#57 completed","24.229; new 24.139",53,27,null,null,"2011-08-29","2012-09-05"]
[5923,490026,"   Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CTofldS1",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-120419","-","Ericsson","Olle.Eriksson@ericsson.com","SP#53 completed. 22/01: acronym modified",22.277999999999999,49,25,null,null,"2010-09-01","2015-01-22"]
[5926,530113,"      TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#56 completed ",24.82,53,27,null,null,"2011-08-29","2012-06-14"]
[5931,470025,"   Deleted - Stage 2 BB III: BBF convergence and network based mobility ","-",2,"Rel-11","S2","2010-09-28","2012-03-07",1,"SP-120539","-","Huawei","marco.spini@huawei.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#55 stopped","23.203; 23.401; 23.402; 23.139",47,24,"SP-55","PCG-28","2009-12-06","2012-08-30"]
[5934,530214,"      Deleted - CT1 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C1","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","TBD",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5935,530314,"      Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C3","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","29.212; 29.213; 29.215",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[5939,480235,"   Stage 2 on SRVCC for eMPS","eMPS_SRVCC",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#54 completed","23.216; 23.237",48,25,null,null,"2010-06-06","2012-03-04"]
[5942,520005,"   CN aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",2,"Rel-11","C1,C3,C4","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","Stage 3. CP#56 completed","-",52,27,null,null,"2011-05-18","2012-06-06"]
[5946,480038,"Network-provided Location information for IMS (NETLOC)","NWK-PL2IMS",1,"Rel-11","S2,S1,S5,C3,C4,C1","2010-06-10","2013-03-01",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging.","-",48,25,null,null,"2010-06-06","2012-11-13"]
[5948,480138,"   TR on Stage 2 for Network-provided Location information for IMS","NWK-PL2IMS",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","SP#54 completed","new 23.842",48,25,null,null,"2010-06-06","2011-12-06"]
[5953,550208,"      CT4 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C4","2012-03-02","2012-06-15",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","23.008; 29.002; 29.060; 29.230; 29.272; 29.274; 29.305; 29.328; 29.329",55,28,null,null,"2012-02-22","2015-03-03"]
[5957,500232,"   Stage 2 for Service Awareness and Privacy Policies","SAPP",2,"Rel-11","S2","2010-10-15","2011-09-21",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","SP#53 completed",23.202999999999999,50,26,null,null,"2010-11-26","2011-08-12"]
[{"$f":"A5960+1","v":5960},500133,"   Stage 2 for VPLMN Autonomous CSG Roaming","VCSG",2,"Rel-11","S2","2010-10-15","2011-12-14",1,"SP-100706","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#54 completed","23.002; 23.060; 23.401",50,26,null,null,"2010-11-26","2011-11-28"]
[5961,530017,"   CT aspects of VPLMN Autonomous CSG Roaming","VCSG-St3",2,"Rel-11","C4","2011-12-07","2011-12-07",1,"CP-120196","-","ZTE","Fei Lu (lu.fei1@zte.com.cn)","CP#57 completed","23.003; 23.007; 23.008; 23.012; 29.002; 29.230; 29.272",53,27,null,null,"2011-08-27","2012-08-13"]
[5965,550003,"   CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3","DIDA-CT",2,"Rel-11","C1","2012-03-02","2012-12-07",1,"CP-120089","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#58 completed","24.302; 24.312",55,28,null,null,"2012-02-20","2013-01-21"]
[5968,540010,"   CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","Stage 3. CP#56 completed","Stage 3",54,28,null,null,"2011-11-23","2012-09-24"]
[5974,530301,"      CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.009; 24.008; 24.229; 24.237; 24.292; 24.301",53,27,null,null,"2011-08-25","2012-08-14"]
[5976,530501,"      CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C4","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.003; 23.008; 29.002; 29.230; 29.272; 29.280; 29.303; 29.305; 29.328",53,27,null,null,"2011-08-25","2012-08-14"]
[5979,530801,"      Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-RAN_UTRA-Core",3,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-111334","RP-121553","Huawei","liwei.qiu@huawei.com","RP#58 completed","25.331; 25.401; 25.413",53,27,null,null,"2011-08-25","2012-11-27"]
[5983,540011,"   CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",2,"Rel-11","C4,C1,C3,IETF","2011-12-02","2014-03-05",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","-","Stage 3",54,28,null,null,"2011-10-26","2011-11-23"]
[5987,540311,"      CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C3","2011-12-02","2012-06-15",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#56 completed","29.212; 29.213; 29.215",54,28,null,null,"2011-10-26","2012-06-01"]
[5988,540029,"Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",1,"Rel-11","S2,S5,C1,C3","2011-11-28","2012-12-07",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","CP#58 completed. Triggered by Rel-11 TR 23.850 Study on Roaming Architecture for Voice over IMS with Local Breakout (FS_RAVEL). GSMA CPWP LS_in S5-102806 asked 3GPP SA5 to check if CS voice charging principles also apply to voice over IMS","Stage 2/3",54,28,null,null,"2011-10-25","2012-11-20"]
[5991,550004,"   CT aspects of Roaming Architecture for Voice over IMS with Local Breakout (Stage 3)","RAVEL-CT",2,"Rel-11","C1,C3","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","Stage 3",55,28,null,null,"2012-02-20","2012-11-20"]
[5996,570007,"   Stage 3 for IMS Overload Control","IOC",2,"Rel-11","C1,C3,IETF","2012-09-05","2014-12-09",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","-","-",57,29,null,null,"2012-08-13","2012-11-20"]
[5999,571001,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control)","RFC 7339",57,29,null,null,"2012-09-03","2015-03-10"]
[6002,520030,"Rel-11 Security small Enhancements","SEC11",1,"Rel-11","S3","2011-06-08","2012-09-12",1,"-","-","-","-","SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature","-",52,27,null,null,"2011-04-19","2012-08-16"]
[6005,440155,"   ZUC EEA3 and EIA3","EEA3_EIA3",2,"Rel-11","S3","2009-06-04","2011-12-14",1,"SP-090457","-","CATR","Yuan Qi (yuanqi@catr.cn)","SP#53 completed new EPS algorithms e.g. for China","33.401; New (35.221; 35.222; 35.223; 35.924)",44,23,null,null,"2009-05-18","2011-12-12"]
[6009,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[6013,540412,"      CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",3,"Rel-11","C1","2011-12-05","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",24.109000000000002,54,28,null,null,"2011-11-23","2012-08-14"]
[6014,520033,"Extensions of Acoustic Test Specifications in TS 26.131 and TS 26.132","Ext_ATS",1,"Rel-11","S4","2011-06-08","2012-09-12",1,"SP-110309","-","Orange, Qualcomm","stephane.ragot@orange-ftgroup.com, Andre Schevciw (aschevci@qualcomm.com)","SP#57 completed","26.131; 26.132",52,27,null,null,"2011-05-26","2012-08-20"]
[6018,530348,"   IMS-based PSS and MBMS Streaming Synchronization Enhancements","EMM-IPME",2,"Rel-11","S4","2011-09-07","2012-09-12",1,"SP-120025","-","InterDigital Communications","hang.liu@interdigital.com","SP#58 completed","26.237; new 26.951=>26.851",53,27,null,null,"2011-09-07","2012-12-11"]
[6021,510151,"   Rel-11 Network Infrastructure Management","OAM11-NIM",2,"Rel-11","S5","2011-03-23","2013-03-06",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2011-02-22"]
[6025,510058,"      Enhanced Management of UE based network performance measurements","OAM-ePM-UE",3,"Rel-11","S5","2011-03-23","2012-12-12",1,"SP-110135","-","Huawei, Ericsson, Nokia Siemens Networks","Zou Lan (zlan@huawei.com), ulf.hubinette@ericsson.com, gyula.bodog@nsn.com","SP#58 completed","32.421; 32.422; 32.423; 32.441; 32.442; 32.446",51,26,null,null,"2011-02-22","2012-11-21"]
[6028,510351,"   Rel-11 Self-Organizing Networks (SON) - OAM aspects","OAM11-SON",2,"Rel-11","S5","2011-03-23","2013-03-06",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2011-02-22"]
[6031,540031,"      Inter-RAT Energy Saving Management","OAM-IRAT-ESM",3,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-110701","-","Nokia Siemens Networks, Huawei","clemens.suerbaum@nsn.com, xiahaitao@huawei.com","SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs","32.405; 32.551; 32.522; 32.526; 32.642; 32.646; 32.762; 32.766",54,28,null,null,"2011-11-22","2012-11-19"]
[6036,510029,"Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",1,"Rel-11","S5,S1,C1","2010-10-27","2012-06-15",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115","-",51,26,null,null,"2011-02-22","2012-06-01"]
[6039,520006,"   Stage 3 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","C1","2011-06-07","2012-06-15",1,"CP-110440","-","Deutsche Telekom","martin.huelsemann@telekom.de]","CP#56 completed",24.228999999999999,52,27,null,null,"2011-05-23","2012-06-01"]
[6040,480011,"User Data Convergence - Data Model","UDC_DM",1,"Rel-11","C4,S1","2010-03-25","2012-09-07",1,"CP-110384","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#57 completed. SP#48 Stage 1 completed as Rel-10","-",48,25,null,null,"2010-05-26","2012-08-13"]
[6044,510004,"Definition of the UICC Application for Hosting Party Module","HPM_UICC",1,"Rel-11","C6","2011-03-18","2012-06-15",1,"CP-110289","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#56 completed","31.102; New 31.104",51,26,null,null,"2011-03-03","2012-09-25"]
[6047,520108,"   CT4 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C4","2011-06-03","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed","23.007; 23.008; 23.018; 29.274; 29.275",52,27,null,null,"2011-05-18","2012-11-20"]
[6051,520009,"Reference Location Information (Stage 3)","RLI",1,"Rel-11","C4,C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11)","-",52,27,null,null,"2011-05-18","2011-06-01"]
[6053,520209,"   CT1 part of Reference Location Information (Stage 3)","RLI",2,"Rel-11","C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed",24.228999999999999,52,27,null,null,"2011-05-18","2011-06-01"]
[6059,520210,"   CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5","IMSProtoc5",2,"Rel-11","C3","2011-06-07","2012-09-07",1,"CP-110437","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#57 completed","29.163; 29.165",52,27,null,null,"2011-05-18","2012-08-14"]
[6062,560008,"   Stage 2 for Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","S2","2012-06-18","2012-09-07",1,"-","-","-","-","SP#57 completed","23.060; 23.251",56,29,null,null,"2012-06-18","2012-08-31"]
[6066,530103,"   GERAN2 part of Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","G2","2011-09-19","2012-08-31",1,"GP-111876","-","China Mobile, Huawei","Juan Deng, Yang Zhao","GP#55 completed. GP#51 approved WID",48.018000000000001,51,27,null,null,"2011-09-06","2012-08-31"]
[6067,530019,"SAE Protocol Development - Phase 2","SAES2",1,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110639","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","-",53,27,null,null,"2011-08-27","2012-08-14"]
[6070,530020,"GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3)","RT_VGCS_Red",1,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069)","Stage 2/3",53,27,null,null,"2011-08-27","2012-08-14"]
[6074,540017,"Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",1,"Rel-11","C4,C3","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI.","Stage 3",54,28,null,null,"2011-10-26","2012-08-13"]
[6079,560006,"PS Additional Number (Stage 3)","PSAN",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120253","-","Deutsche Telekom","Yvette.koza@t-mobile.at","CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact)","23.003; 23.008; 29.002; 29.272; 29.230",56,29,null,null,"2012-04-23","2012-08-13"]
[6081,570010,"IMS Operator Determined Call Barring","IODB",1,"Rel-11","C1,C4","2012-09-07","2013-06-14",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","LS_in C4-121615 GSMA IREG RILTE concluded that TS 22.041 clause 5.4 Stage 1 requirements are not covered by stage 3 specifications","-",57,29,null,null,"2012-08-13","2012-09-06"]
[6085,570111,"   CT3 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C3","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",29.163,57,29,null,null,"2012-08-13","2012-11-20"]
[{"$f":"A6088+1","v":6088},540016,"Deleted - Enhancement of the Protocols for SMS over SGs (Stage 3)","PROTOC_SMS_SGs",1,"Rel-11","C4,C1","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped. Reason: Protocols for SMS over SGs is replaced by the SIMTC SMS in MME solution (as solution not only for MTC user but for general subscribers)","Stage 3",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[6092,510001,"Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",1,"Rel-11","G2,S2,C1","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001","GERAN",49,26,null,null,"2011-03-04","2013-05-17"]
[6093,510101,"   GERAN part of Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","G2","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID","44.018; 44.060; 45.002; 45.008; 48.008; 48.018",49,26,null,null,"2011-03-04","2013-05-17"]
[6096,510401,"      CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C1","2011-06-03","2012-12-07",1,"CP-120563","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#58 completed",24.007999999999999,49,26,null,null,"2011-03-04","2012-11-19"]
[6101,540203,"   Perf. part: Medium range/local area requirements for multicarrier BTS","MRLA-Perf",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111782","-","Ericsson","Eric Nordström","Test spec. GP#56 completed. GP#52 approved WID",51.021000000000001,52,28,null,null,"2011-11-25","2012-11-23"]
[6104,500120,"   Core part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Core",2,"Rel-11","R4,R2,R3","2010-12-10","2012-03-02",1,"RP-111396","RP-120075","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.331; 37.104; 37.113; 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[6107,530030,"Further Self Optimizing Networks (SON) enhancements","SONenh2_LTE_UTRA",1,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-120314","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","Stage 1/2/3","UTRA; LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[6111,590001,"   Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-12-06",1,"RP-130172","RP-131447","NTT DoCoMo","masahiro.tamaoki.eu@nttdocomo.com","RP#62 completed","34.108; 34.109; 34.123-1; 34.123-2; 34.123-3; 36.508; 36.509; 36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-01-29","2013-08-13"]
[6114,570001,"   GERAN part: Network Energy Saving for E-UTRAN","-",2,"Rel-11","GP","2012-08-27","2012-08-31",1,"GP-121178","-","Alcatel-Lucent","marguerite.woch@alcatel-lucent.com","GP#55 approved WID and completed. Stage 3. ChangES in CP-150RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature","48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)]",55,29,null,null,"2012-09-01","2012-09-01"]
[6118,540002,"   GERAN part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-GERAN",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111779","-","Ericsson","Eric Nordström","GP#56 completed. GP#52 approved WID","45.005; 51.021",52,28,null,null,"2011-11-25","2012-11-23"]
[6119,550015,"RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF",1,"Rel-11","R4,G1","2012-02-06","2014-03-06",1,"RP-120857","-","Huawei","Liu Ye (leo.liuye@huawei.com)","-","UTRA; LTE; GERAN",55,28,null,null,"2012-02-23","2012-09-04"]
[6123,560113,"   Core part: Further enhancements to H(e)NB mobility - Part 1","EHNB_enh1-Core",2,"Rel-11","R3,R2","2012-06-15","2012-12-07",1,"RP-121427","RP-121563","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#58 completed","25.413; 25.467; 25.469; 36.300; 36.413; 36.423",56,29,null,null,"2012-06-13","2012-11-27"]
[6127,430111,"   Core part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Core",2,"Rel-11","R2,R1,R3,R4","2009-03-05","2013-06-12",1,"RP-131259","RP-130483","TruePosition","terri.brooks@trueposition.com","RP#60 completed","36.214; 36.300; 36.305; 36.401; 36.413; 36.455; new (36.111; 36.456; 36.457; 36.458; 36.459)",43,22,null,null,"2009-03-06","2013-08-29"]
[6130,480126,"   Core part: Service continuity improvements for MBMS for LTE","MBMS_LTE_SC-Core",2,"Rel-11","R2,R3","2010-06-04","2012-09-07",1,"RP-120258","RP-121001","Huawei","David.Lecompte@huawei.com ","RP#57 completed","25.446; 36.300; 36.304; 36.321; 36.322; 36.323; 36.331; 36.440; 36.441; 36.442; 36.443; 36.444; 36.445",48,25,null,null,"2010-06-04","2012-09-06"]
[6133,510121,"   Core part: Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE-Core",2,"Rel-11","R1,R2,R3,R4","2011-03-22","2012-12-07",1,"RP-120860","RP-121986","China Mobile","ShenXiaodong@chinamobile.com","RP#58 completed","36.101; 36.133; 36.201; 36.211; 36.212; 36.213; 36.214; 36.300; 36.304; 36.321; 36.331; 36.413; 36.423",51,26,null,null,"2011-03-14","2012-12-05"]
[6136,510028,"New Band LTE Downlink FDD 716-728 MHz (Band 29, Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29)","LTE_DL_FDD700",1,"Rel-11","R4","2011-03-22","2012-12-07",1,"RP-110435","-","AT&T","marc.grant@att.com ","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[6141,590003,"   Test part: LTE RAN Enhancements for Diverse Data Applications","LTE_eDDA-UEConTest",2,"Rel-11","R5","2013-03-04","2013-09-06",1,"RP-130338","RP-130946","BlackBerry","Enikő Sokondár (esokondar@rim.com)","RP#61 completed","36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-02-26","2013-08-28"]
[6142,510032,"LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB",1,"Rel-11","R1,R2,R4,R5","2011-03-23","2013-03-01",1,"RP-120602","-","NII Holdings","bill.shvodian@nii.com","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-06-09"]
[6145,560010,"   Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-UEConTest",2,"Rel-11","R5","2012-06-18","2013-03-01",1,"RP-120603","RP-130045","NII Holdings","bill.shvodian@nii.com","RP#59 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1",56,29,null,null,"2012-06-06","2013-02-27"]
[6149,560011,"   Test part: LTE for 700 MHz Digital Dividend","LTE_APAC700-UEConTest",2,"Rel-11","R5","2012-06-18","2013-06-14",1,"RP-120600","RP-130467","Ericsson","fredrik.sundstrom@ericsson.com","RP#60 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1",56,29,null,null,"2012-06-06","2013-06-03"]
[6153,530031,"Signalling and Procedure for Interference Avoidance for in-device coexistence","SPIA_IDC_LTE",1,"Rel-11","R2,R4","2011-09-19","2012-12-07",1,"RP-111355","-","China Mobile","Zhenping HU","Stage 2/3","LTE",53,27,null,null,"2011-09-15","2012-11-27"]
[6156,530032,"Coordinated Multi-Point Operation for LTE","COMP_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-09-19","2014-12-15",1,"RP-111365","-","Huawei, Samsung","Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com","Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE)","LTE",53,27,null,null,"2011-09-15","2011-09-15"]
[6158,530232,"   Perf. part: Coordinated Multi-Point Operation for LTE – Uplink","COMP_LTE_UL-Perf",2,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-111365","RP-121576","Huawei","Xinwei Zhi (zhixinwei@huawei.com)","RP#58 completed","36.101; 36.104; 36.133; 36.141",53,27,null,null,"2011-09-15","2012-11-27"]
[6164,540225,"   Perf. part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-Perf",2,"Rel-11","R4","2011-12-16","2014-06-13",1,"RP-120871","RP-140651","Alcatel-Lucent","teck.hu@alcatel-lucent.com","RP#64 completed","36.101; 36.104; 36.133; 36.141",54,28,null,null,"2011-12-07","2014-06-11"]
[6167,550112,"   Core part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-Core",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120362","RP-121581","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#58 completed. TR 36.837 v100 for Information and Approval","36.101; new 36.837",55,28,null,null,"2012-02-23","2012-12-05"]
[6171,600002,"   Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-UEConTest",2,"Rel-11","R5","2013-06-18","2014-09-12",1,"RP-140491","RP-141602","Broadcom","jarkko.hellsten@kolumbus.fi","RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101","36.508; 36.521-1; 36.521-2; New 36.904",60,31,null,null,"2013-05-22","2014-09-07"]
[6172,550014,"Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe",1,"Rel-11","R4,R2,R3,R5","2012-03-05","2013-06-14",1,"RP-120384","-","China Mobile","Xiaodong Shen","Stage 3. Exists already for 1UL a WI LTE_CA_B3_B5","LTE",55,28,null,null,"2012-02-23","2012-02-28"]
[6175,580158,"Rel-11 LTE Carrier Aggregation","LTE_CA_Rel-11",1,"Rel-11","R1,R2,R3,R4,R5","2010-12-10","2014-12-12",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[6179,600003,"      Test part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-UEConTest",3,"Rel-11","R5","2013-06-18","2014-09-12",1,"RP-140619","RP-141443","Microsoft","jussi.kuusisto@microsoft.com","SP#65 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",60,31,null,null,"2013-05-22","2014-09-09"]
[6184,480223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-120830","RP-121023","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed","36.133; 36.141",48,25,null,null,"2010-06-04","2012-09-04"]
[6187,500217,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-121458","RP-121595","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",50,26,null,null,"2010-12-10","2012-11-26"]
[6190,500218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 13","LTE_CA_B4_B13-Perf",4,"Rel-11","R4","2010-12-21","2012-12-07",1,"RP-120905","RP-121594","Ericsson","christian.bergljung@ericsson.com ","RP#58 completed","36.101; 36.133; 36.141",50,26,null,null,"2010-12-10","2012-11-27"]
[6193,510222,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12-Perf",4,"Rel-11","R4","2011-03-29","2012-12-07",1,"RP-120877","RP-121593","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","RP#58 completed","36.133; 36.141",51,26,null,null,"2011-03-14","2012-11-27"]
[6195,510123,"         Core part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","RP-121596","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[6198,510124,"         Core part: LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20-Core",4,"Rel-11","R4","2011-03-22","2012-09-07",1,"RP-120889","RP-121032","Huawei","Steven Chen","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[6201,510125,"         Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17-Core",4,"Rel-11","R4","2011-03-23","2012-09-07",1,"RP-110432","RP-121034","AT&T","marc.grant@att.com ","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[6206,510027,"      LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17",3,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110434","-","AT&T","marc.grant@att.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[6209,530023,"      LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120887","-","Vodafone","tim.frost@vodafone.com","Stage 3. RP#57 completed","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[6213,530124,"         Core part: LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-120888","RP-121600","Vodafone","Luis.Anaya@vodafone.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.307; new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[6215,530026,"      LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5",3,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120899","-","SK Telecom","Haesung Park","Stage 3. RP#57 completed","LTE",53,27,null,null,"2011-09-15","2012-09-04"]
[6220,530227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Perf",4,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-121152","RP-121591","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed","36.101; 36.104; 36.133; 36.141; 36.307",53,27,null,null,"2011-09-15","2012-11-27"]
[6221,540020,"      LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18",3,"Rel-11","R4,R2","2011-12-09","2012-12-07",1,"RP-120898","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Stage 3. RP#58 completed","LTE",54,28,null,null,"2011-12-07","2012-12-04"]
[6224,540021,"      LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18",3,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-120892","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Stage 3. RP#57 completed","LTE",54,28,null,null,"2011-12-07","2012-09-04"]
[6228,540122,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Core",4,"Rel-11","R4,R2","2012-03-05","2012-09-07",1,"RP-120866","RP-120552","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",54,28,null,null,"2011-12-07","2012-06-15"]
[6232,540223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Perf",4,"Rel-11","R4","2011-12-13","2012-12-07",1,"RP-121173","RP-121055","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed","36.133; 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[6235,550218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Perf",4,"Rel-11","R4","2012-03-06","2012-12-07",1,"RP-121162","RP-121587","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed","36.133; 36.141",55,28,null,null,"2012-02-23","2012-11-27"]
[6239,520215,"         Perf. part: LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38-Perf",4,"Rel-11","R4","2011-06-08","2012-09-07",1,"RP-110862","RP-121061","Huawei","ronnie.zhang@huawei.com","RP#57 completed","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; 37.141",52,27,null,null,"2011-06-02","2012-09-04"]
[6241,520116,"         Core part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Core",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120126","Clearwire","michael.hart@clearwire.com","RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; new 36.833-1-41 [instead of 36.827]",52,27,null,null,"2011-06-02","2012-02-23"]
[6246,450016,"UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest",1,"Rel-11","R4,R5","2009-09-18","2016-09-15",1,"RP-111381","-","CATR","Guo Lin (guolin@emcite.com)","-","UTRA",45,23,null,null,"2009-09-15","2011-09-17"]
[6247,450116,"   Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest-Core",2,"Rel-11","R4","2009-09-18","2011-12-09",1,"RP-111381","RP-111456","CATR","Guo Lin (guolin@emcite.com)","RP#54 completed","25.144; 25.914; 34.114",45,23,null,null,"2009-09-15","2011-11-29"]
[6250,500119,"   Core part: Eight carrier HSDPA","8C_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-06-15",1,"RP-101419","RP-120971","Ericsson","johan.hultell@ericsson.com","RP#57 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.331; 25.423; 25.433; 26.306",50,26,null,null,"2010-12-10","2012-09-04"]
[6255,500022,"Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv",1,"Rel-11","R1,R4,R2,R3,R5","2010-12-10","2014-06-13",1,"RP-120367","-","Huawei","zongjie.wang@huawei.com","Stage 2/3","UTRA",50,26,null,null,"2010-12-10","2012-02-28"]
[6258,500322,"   Core part: Uplink Transmit Diversity for HSPA - Open Loop","HSPA_UL_TxDiv-OL-Core",2,"Rel-11","R4,R1,R2,R3","2010-12-10","2012-12-07",1,"RP-120367","RP-121544","Huawei","zongjie.wang@huawei.com","RP#58 completed","25.101; 25.133; 25.306; 25.319; 25.321; 25.331; 25.423; 25.433",50,26,null,null,"2010-12-10","2012-11-28"]
[6261,510018,"Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config",1,"Rel-11","R4,R2","2011-03-22","2012-06-15",1,"RP-110308","-","Telus Communications","jorge.delrio@telus.com ","-","UTRA",51,26,null,null,"2011-03-14","2011-06-01"]
[6263,510218,"   Perf. part: Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config-Perf",2,"Rel-11","R4","2011-03-24","2012-06-15",1,"RP-110308","RP-120475","Telus Communications","jorge.delrio@telus.com ","RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",51,26,null,null,"2011-03-14","2012-06-09"]
[6269,510220,"   Perf. part: Further Enhancements to CELL_FACH","Cell_FACH_enh-Perf",2,"Rel-11","R4","2011-03-24","2013-12-06",1,"RP-111321","RP-131459","Qualcomm","Heechoon Lee (heechoon@qti.qualcomm.com)","RP#62 completed","25.101; 25.104; 25.133; 25.141",51,26,null,null,"2011-03-14","2013-11-29"]
[6272,530134,"   Core part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-Core",2,"Rel-11","R2,R1,R3,R4","2011-09-19","2012-12-07",1,"RP-111375","RP-121551","Nokia Siemens Networks","Alexander Sayenko","RP#58 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.214; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433",53,27,null,null,"2011-09-15","2012-11-27"]
[6276,530135,"   Core part: Four Branch MIMO transmission for HSDPA","4Tx_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2011-09-19","2012-12-07",1,"RP-111393","RP-121549","Ericsson","johan.hultell@ericsson.com","RP#58 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.331; 25.423; 25.433; 26.306",53,27,null,null,"2011-09-15","2012-11-27"]
[6277,530235,"   Perf. part: Four Branch MIMO transmission for HSDPA","4Tx_HSDPA-Perf",2,"Rel-11","R4","2011-09-21","2013-12-06",1,"RP-111393","RP-131460","Ericsson","johan.hultell@ericsson.com","RP#62 completed","25.101; 25.104; 25.133; 25.141",53,27,null,null,"2011-09-15","2013-11-29"]
[6281,540024,"HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC",1,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","-","Ericsson","muhammad.kazmi@ericsson.com","Stage 3","UTRA",54,28,null,null,"2011-12-07","2012-09-04"]
[6284,620015,"Split TTCN Test Models for IMS testing in TS 34.229-3","IMS-CCR_Test2",1,"Rel-11","R5","2013-12-09","2014-09-12",1,"RP-140440","RP-141155","Spirent","richard.catmur@spirent.com","SP#65 completed. TS 34.229-4 for Approval. Split out of old TS 34.229-3 a new TS 34.229-4","34.229-3; New 34.229-4",62,32,null,null,"2013-11-25","2014-09-09"]
[6289,450047,"Study on IMS based Peer-to-Peer Content Distribution Services","FS_IMS_P2P",1,"Rel-11","S1,S2","2009-09-11","2010-06-10",1,"SP-090491","-","China Mobile","Li Gang (ligangyf@chinamobile.com)","SP#48 completed. 3/3/15: start date corrected (was 05/09)",22.905999999999999,45,23,null,null,"2009-09-21","2015-03-03"]
[6292,490033,"Study on IMS Network-Independent Public User Identities","FS_INIPUI",1,"Rel-11","S1","2010-09-23","2011-06-08",1,"SP-100652","-","Vodafone","mona.mustapha@vodafone.com","SP#52 completed",22.893999999999998,49,25,null,null,"2010-09-21","2011-05-18"]
[6295,440048,"Study on IPv6 Migration","FS_IP6M",1,"Rel-11","S2","2009-06-04","2011-06-08",1,"SP-090362","-","China Mobile","Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com)","SP#52 completed",23.975000000000001,44,23,null,null,"2009-05-31","2011-05-26"]
[6298,380084,"Study on UTRAN key management enhancements","FS_UKM",1,"Rel-11","S3","2007-12-20","2012-03-07",1,"SP-090283","-","Ericsson","karl.norrman@ericsson.com","SP#55 completed",33.859000000000002,38,21,null,null,"2007-12-20","2012-11-20"]
[6300,520036,"Study on Mobile 3D Video Coding","FS_M3DVC",1,"Rel-11","S4","2011-06-08","2012-06-20",1,"SP-110310","-","Orange","gilles.teniou@orange-ftgroup.com","SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS",26.905000000000001,52,27,null,null,"2011-05-26","2012-08-20"]
[6303,510045,"Study on OAM aspects of inter-RAT Energy Saving","FS_OAM_ES_iRAT",1,"Rel-11","S5","2011-03-23","2011-12-14",1,"SP-110138","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES)",32.834000000000003,51,26,null,null,"2011-03-09","2012-04-02"]
[6307,470014,"Study on Coordinated Multi-Point operation for LTE","FS_CoMP_LTE",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101425","RP-111343","Samsung","bruno.clerckx@samsung.com","RP#53 completed","LTE 36.819",47,24,null,null,"2010-03-19","2011-05-27"]
[6311,510039,"Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","FS_LTE_TDD_eIMTA",1,"Rel-11","R1,R4","2011-03-22","2012-06-15",1,"RP-110450","RP-120587","CATT","Zukang Shen (shenzukang@catt.cn)","RP#56 completed. TR 36.828 for Information and Approval","LTE 36.828",51,26,null,null,"2011-03-21","2012-06-09"]
[6314,550022,"Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology","FS_LTE_OTA",1,"Rel-11","R4","2012-03-05","2012-09-07",1,"RP-120412","RP-121083","CATR","Xudong An (anxudong@emcite.com)","RP#57 completed","LTE 25.914; New 37.902",55,28,null,null,"2012-02-23","2012-09-03"]
[6318,500002,"Study on UE Application Layer Data Throughput Performance","FS_UE_App_Data_Perf",1,"Rel-11","R5,R4","2010-09-16","2011-09-16",1,"RP-101422","RP-111543","Spirent","ron.borsato@spirent.com","RP#54 completed","UTRA; LTE 37.901",50,26,null,null,"2010-12-08","2011-11-29"]
[6320,510038,"Study on Interference analysis between 800~900 MHz bands","FS_B800_B900_Interf_LTE",1,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-111752","RP-120586","LG Uplus","Koo Yeon Sang (yskoo@lguplus.co.kr)","RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 ","UTRA; LTE impac37.804",51,26,null,null,"2011-03-21","2012-06-06"]
[6323,500015,"Study on HSDPA Multipoint Transmission","FS_HSDPA_MP_TX",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101439","RP-111049","Nokia Siemens Networks","karri.ranta-aho@nsn.com ","RP#53 completed","UTRA 25.872",50,26,null,null,"2010-12-08","2011-09-09"]
[6326,510035,"Deleted - Study on Enhanced Uplink Transmission for LTE","FS_eUL_TX_LTE",1,"Rel-11","R1","2011-03-22","2012-06-15",1,"RP-120259","RP-120585","Huawei","Yongxing Zhou","RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it","LTE 36.8xy",51,26,"RP-56","PCG-29","2011-03-21","2012-06-18"]
[6329,390074,"   Stage 1 on enhancements for Multimedia Priority Service","ePRIOR-St1",2,"Rel-10","S1","2006-03-13","2008-06-05",1,"SP-080051","-","Telcordia","jgarraha@telcordia.com","22/01: acronym modified","22.153; 22.278",39,21,null,null,"2003-03-28","2015-01-22"]
[6333,460529,"      Stage 2 on eMPS for IMS Aspects","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002; 23.203; 23.221; 23.228; 23.272; 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[6337,490208,"      CT3 part on Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","29.212; 29.213; 29.214",49,25,null,null,"2010-09-01","2011-03-01"]
[6340,410031,"   Stage 1 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-100863","-","KPN","toon.norp@tno.nl","SP#47 completed","22.011; New 22.368",41,21,null,null,"2008-09-15","2010-03-09"]
[6342,490037,"   Stage 2 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S2","2010-08-30","2010-09-23",1,"SP-100863","-","Samsung","erik.guttman@partner.samsung.com","SP#49 completed","23.060; 23.236; 23.401",45,23,null,null,"2009-09-21","2010-12-13"]
[6348,480305,"      CT4 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C4","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","23.003; 23.008; 29.002; 29.060; 29.230; 29.272; 29.274; 29.275; 29.282",48,25,null,null,"2010-05-26","2011-06-01"]
[6349,510005,"      CT6 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C6","2011-03-18","2011-06-03",1,"-","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#52 completed",31.102,51,26,null,null,"2011-03-10","2011-05-18"]
[6352,490024,"   RAN mechanisms to avoid CN overload due to Machine-Type Communications","NIMTC-RAN_overload",2,"Rel-10","R2,R3","2010-09-17","2011-03-18",1,"RP-101026","RP-110063","Huawei","Jeff Gao (gaoyq@huawei.com)","RP#51 completed","UTRA; LTE 25.331; 25.413; 36.331; 36.413",49,25,null,null,"2010-09-20","2011-03-14"]
[6355,430135,"   Stage 2 for Multi Access PDN Connectivity","MAPCON",2,"Rel-10","S2","2009-03-13","2010-09-23",1,"SP-090659","-","Telecom Italia","ivano.guardini@telecomitalia.it","SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control)","23.237; 23.401; 23.402",43,22,null,null,"2010-10-25","2010-10-25"]
[6360,440052,"IMS Service Continuity – Inter Device Transfer enhancements","IMS_SC_eIDT",1,"Rel-10","S1,S2,C1,IETF","2009-06-04","2012-12-07",1,"SP-090452","-","Huawei","Amar Deol (adeol@huawei.com)","CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements","-",44,23,null,null,"2009-05-25","2010-03-09"]
[6363,470001,"   Stage 3 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-110285","-","Huawei","georg.mayer@huawei.com ","CP#51 completed. WID updated CP-100334=>CP-110285","24.216; 24.229; 24.237; new (24.837; 24.337)",47,24,null,null,"2010-03-17","2011-03-17"]
[6368,460017,"   Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",2,"Rel-10","C3","2009-12-04","2010-09-17",1,"CP-090859","-","Ericsson","Jan Holm","CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204",29.311,46,24,null,null,"2009-11-30","2010-09-01"]
[6371,470002,"   CT1 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#51 completed","24.173; 24.642",47,24,null,null,"2010-03-17","2011-02-14"]
[6374,450037,"   Stage 1 for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-110131","-","Huawei, China Mobile","Amar Deol (adeolf@huawei.com), Gang Li (ligangyf@chinamobile.com)","SP#47 completed","22.101; 22.220",45,23,null,null,"2009-09-08","2010-03-09"]
[6375,450036,"   TR on Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S2","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#51 completed. TR 23.829 for Approval","New 23.829",45,23,null,null,"2009-09-08","2010-12-01"]
[6381,480008,"      Stage 3 for Local IP Access","LIPA",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","-",48,25,null,null,"2010-05-26","2010-05-26"]
[6382,480108,"         CT4 part of Stage 3 for Local IP Access","LIPA",4,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","23.008; 23.015; 29.002; 29.060; 29.272; 29.274; 29.281; 29.303",48,25,null,null,"2010-05-26","2010-11-30"]
[6386,480007,"      Stage 3 for SIPTO for macro networks","SIPTO",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","-",48,25,null,null,"2010-05-26","2011-03-08"]
[6389,450041,"IP Flow Mobility and seamless WLAN offload","IFOM",1,"Rel-10","S2,S1,S5,C1,C3","2009-09-24","2011-03-23",1,"SP-100089","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#51 completed. Triggered by Rel-10 TR 23.861 (UID_410043 Study on Multi Access PDN connectivity and IP flow mobility - MAPIM)","-",45,23,null,null,"2009-09-08","2011-03-10"]
[6394,480109,"      CT1 part of Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",3,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","24.008; 24.301; 24.302; 24.303; 24.312; 24.327",48,25,null,null,"2010-05-26","2011-02-28"]
[6397,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[6400,490038,"   SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S4","2010-09-23","2011-03-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#51 completed",26.114000000000001,49,25,null,null,"2010-09-14","2011-02-18"]
[6403,531006,"      (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3-IETF,C4-IETF","2009-07-15","2012-09-07",1,"CP-100702","-","Lionel Morand","-","CP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",53,27,null,null,"2011-08-31","2012-09-03"]
[6405,490307,"      CT1 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C1","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed",24.228999999999999,49,25,null,null,"2010-09-01","2011-05-23"]
[{"$f":"A6408+1","v":6408},420034,"   IMS aspects of Architecture for Home NodeB","EHNB-IMS",2,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080799","-","Alcatel-Lucent","Nicolas Drevon","SP#47 completed. Chosen solution has no normative impacts","New 23.832",42,22,null,null,"2008-12-09","2010-02-26"]
[6412,480010,"   Stage 3 for Optimal Media Routing","OMR",2,"Rel-10","C3,C1,C4","2010-06-04","2011-06-03",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134","-",48,25,null,null,"2010-05-26","2011-03-10"]
[6416,500013,"   Charging for Optimal Media Routing","OMR",2,"Rel-10","S5","2010-12-16","2011-06-08",1,"SP-100772","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#52 completed. Stage 3: Linked to CT3 TS 29.079 OMR within the IMS¦Stage 3 (UID_480110)","32.260; 32.298; 32.299",50,26,null,null,"2010-11-27","2011-05-16"]
[6420,500005,"   Stage 3 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-100880","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","CP#52 completed",24.228999999999999,50,26,null,null,"2010-10-25","2011-05-23"]
[6423,490009,"   Stage 3 for S2b Mobility based on GTP","SMOG-St3",2,"Rel-10","C4,C3,C1","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 Stage 3 completed","-",49,25,null,null,"2010-09-01","2011-03-18"]
[6425,490209,"      CT3 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C3","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed","29.212; 29.213; 29.215",49,25,null,null,"2010-09-01","2011-03-18"]
[6428,500106,"   Stage 2 for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST",2,"Rel-10","S2","2010-10-12","2010-10-12",1,"SP-110196","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#51 updated WID SP-100702=>SP-110196. SP#49 work completed as SA2 CRs approved under TEI10 (SP-10557)","23.002; 23.203",50,26,null,null,"2010-11-26","2011-03-19"]
[6431,470129,"   LI for CAT (Customer Alerting Tones)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6435,470529,"   LI for MEDIASEC (IMS Media security)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6438,470829,"   LI for LCLS (Local Call Local Switch)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6442,521002,"   (IETF) HTTP-based Streaming and Download Services in 3GPP","HTTP_SDS",2,"Rel-10","S4-IETF","2010-03-25","2011-09-21",1,"SP-100032","-","-","-","SP#53/IETF#81: Draft not included in 3GPP documentation. Dec.14: IETF RFC added","RFC 6381 (was draft-gellens-mime-bucket-bis)",52,27,null,null,"2011-06-20","2014-12-04"]
[6446,460031,"Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM10",1,"Rel-10","S5,C4","2009-12-10","2011-09-21",1,"-","-","-","-","OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI",30.82,46,24,null,null,"2009-12-01","2011-08-26"]
[6447,460032,"   Rel-10 Network Infrastructure Management","OAM10-NIM",2,"Rel-10","S5","2009-12-10","2011-09-21",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[6453,510042,"      Inventory Management Network Resource Model enhancements","OAM-IM-NMR",3,"Rel-10","S5","2011-03-23","2011-06-08",1,"SP-110141","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items","32.690; 32.691; 32.692; 32.696",51,26,null,null,"2011-03-09","2011-05-16"]
[6454,460034,"   Rel-10 Self-Organizing Networks (SON) - OAM aspects","OAM10-SON",2,"Rel-10","S5","2009-12-10","2011-06-08",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[6457,470037,"      OAM aspects of Energy Saving in Radio Networks","OAM-ES",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-110128","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management¦Energy Savings Management (FS_OAM_ESM) UID_430044","32.425; 32.522; 32.526; 32.626; 32.762; 32.766; new 32.551",47,24,null,null,"2010-02-12","2011-03-17"]
[6460,470040,"      Key Performance Indicators (KPIs) for IMS","OAM-PM-KPI_IMS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100083","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#51 completed","new 32.454",47,24,null,null,"2010-02-12","2011-03-09"]
[6465,470043,"      3G HNB and LTE HeNB Subsystem performance measurements","OAM-PM-HeNS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100081","-","China Mobile","Chen Gang (chengang@chinamobile.com)","SP#51 completed","32.582; 32.592; new (32.452; 32.453)",47,24,null,null,"2010-03-08","2011-03-09"]
[6468,470046,"Advice of Charge (AoC) service support enhancements","eAoC",1,"Rel-10","S5,C1","2010-03-25","2011-06-03",1,"SP-100080","-","Deutsche Telekom","matthias.seibel@telekom.de","CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work","-",47,24,null,null,"2010-03-23","2011-05-23"]
[6473,480014,"Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications","II-NNI2",1,"Rel-10","C3","2010-06-04","2013-03-01",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI)","-",48,25,null,null,"2010-05-26","2013-02-21"]
[6476,561002,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6809)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2012-12-07",1,"CP-100326","-","christer.holmberg@ericsson.com","Christer Holmberg","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",56,29,null,null,"2012-04-20","2012-12-04"]
[6477,480013,"AT Commands for IMS-configuration","AT_IMS",1,"Rel-10","C1","2010-06-04","2011-03-18",1,"CP-100376","-","Ericsson","atle.monrad@ericsson.com","CP#51 completed. Specify 1) IMS-related AT-commands to configure MT and 2) IMS-related unsolicited response codes from MT to present to end-user",27.007000000000001,48,25,null,null,"2010-05-29","2011-02-14"]
[6480,500003,"Dynamic view of SIP message for Inter-IMS Network to Network Interface (II-NNI) (Stage 3)","NNI_DV",1,"Rel-10","C3","2010-12-10","2011-06-03",1,"CP-100795","-","NTT","arai.kenjiro@lab.ntt.co.jp","CP#52 completed. Linked to CT3 Rel-10 Feature UID_480014 Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications (II-NNI2)",29.164999999999999,50,26,null,null,"2010-11-26","2011-05-17"]
[6486,521003,"   (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809)","eSRVCC",2,"Rel-10","C1-IETF","2010-12-10","2012-12-07",1,"CP-100881","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",52,27,null,null,"2011-06-20","2013-02-21"]
[6488,500111,"   CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3)","aSRVCC",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-110145","-","ZTE","li.shitao@zte.com.cn","CP#52 completed","24.008; 24.237",50,26,null,null,"2011-03-16","2011-05-23"]
[6491,500112,"   CT4 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C4","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 2 23.007; Stage 3 29.230",50,26,null,null,"2010-10-25","2011-03-01"]
[6495,510008,"EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated","EPC_NR",1,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110092","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014","Stage 2/3: 23.007; 29.274",51,26,null,null,"2011-02-22","2011-03-18"]
[6499,510110,"   CT6 part of UICC access to IMS Specification","IMS-UICC-S",2,"Rel-10","C6","2011-03-16","2011-03-18",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed","31.102; 31.103; 31.111",51,26,null,null,"2011-03-03","2011-03-10"]
[6502,440021,"CN aspects of Local Call Local Switch","LCLS-CN",1,"Rel-10","C4","2009-05-29","2011-03-18",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","GERAN Stage 2/3",44,23,null,null,"2009-05-13","2010-12-09"]
[6503,440022,"   TR on CN aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C4","2009-05-29","2010-09-16",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#49 completed","new 23.889",44,23,null,null,"2009-05-13","2010-12-09"]
[6508,480002,"Tightened Link Level Performance Requirements for Single Antenna MS","TIGHTER",1,"Rel-10","G1,G2,C1,G3new","2010-09-03","2013-03-01",1,"GP-101083","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#46 approved WID","GERAN",46,25,null,null,"2010-05-27","2013-03-16"]
[6510,480202,"   TIGHTER Performance Requirements","TIGHTER",2,"Rel-10","G1,G2","2010-09-03","2011-05-20",1,"GP-101084","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#50 completed","45.005; 45.015",46,25,null,null,"2010-05-27","2011-05-21"]
[6514,490201,"   CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",2,"Rel-10","C1","2010-05-21","2010-12-10",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#50 completed","24.008 CR#1644",47,25,null,null,"2010-05-27","2011-03-04"]
[6517,490102,"   GERAN part for Enhancements of Iur-g interface (Stage 2/3)","eIurg-GERAN",2,"Rel-10","G2","2010-09-03","2011-03-04",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#49 completed. GP#48 updated WID GP-101659=>GP-101758 (restricting the scope to GERAN BSC and TD-SCDMA RNC only). GP#47 approved WID","43.130; 48.008",47,25,null,null,"2010-09-05","2011-03-04"]
[6521,460014,"1.28 Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF",1,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","-","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866)","UTRA",46,24,null,null,"2009-11-30","2010-12-03"]
[6525,470112,"   Core part: MU-MIMO for 1.28Mcps TDD","MUMIMO_LCR_TDD-Core",2,"Rel-10","R1,R2,R3","2010-03-19","2010-12-10",1,"RP-100347","RP-101085","CATT","Yanping Xing (xingyanping@datangmobile.cn)","RP#50 completed","25.221; 25.222; 25.224; 25.306; 25.308; 25.319; 25.331; 25.423; 25.425; 25.433; 25.435",47,24,null,null,"2010-03-19","2010-12-03"]
[6528,450127,"   AGNSS Minimum Performance Specification Development","AGNSSPerf_UTRAN",2,"Rel-10","R4","2009-09-18","2010-12-10",1,"RP-100363","RP-101078","Thales","Michel.monnerat@thalesaleniaspace.com","RP#50 completed","new 25.172",45,23,null,null,"2009-09-15","2010-12-08"]
[6530,460005,"Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN","LCS_UMTS_RFPMT",1,"Rel-10","R2,R3","2009-12-04","2011-03-18",1,"RP-091427","RP-110048","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907)","UTRA",46,24,null,null,"2009-11-30","2011-03-11"]
[6533,460115,"   Core part: Four carrier HSDPA","4C_HSDPA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-03-18",1,"RP-100991","RP-110046","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#51 completed. RP#52 TR 25.864 v200 for Approval","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.331; 25.423; 25.433; 26.306; new 25.864",46,24,null,null,"2009-11-30","2011-05-27"]
[{"$f":"A6536+1","v":6536},470013,"Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD",1,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-100168","-","TD Tech","dafei.wang@td-tech.com","Stage 3. RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2011-06-01"]
[6540,480120,"   Core part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-Core",2,"Rel-10","R3,R2","2010-06-04","2011-06-03",1,"RP-100688","RP-110522","ZTE","Zhai.hengxing@zte.com.cn","RP#52 completed","25.331; 25.413; 25.423; new 25.484 (Stage 2)",48,25,null,null,"2010-06-03","2011-05-31"]
[6543,480121,"   Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100657","RP-110523","AT&T","Vince Spatafora (vs5785@att.com)","RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",48,25,null,null,"2010-06-03","2011-05-24"]
[6548,510017,"   Test part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-UEConTest",2,"Rel-10","R5","2011-03-18","2012-03-02",1,"RP-110244","RP-120042","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#55 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",51,26,null,null,"2011-03-10","2012-02-23"]
[6551,460107,"   Core part: Carrier Aggregation for LTE","LTE_CA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-06-03",1,"RP-100661","RP-110535","Nokia","lars.e.lindh@nokia.com","RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.300; 36.302; 36.306; 36.321; 36.331; 36.413; 36.423; 37.104; new RAN4 (36.807; 36.808)",46,24,null,null,"2009-11-30","2012-06-07"]
[6552,460207,"   Perf. part: Carrier Aggregation for LTE","LTE_CA-Perf",2,"Rel-10","R4","2009-12-04","2011-12-09",1,"RP-100661","RP-111452","Nokia","lars.e.lindh@nokia.com","RP#54 completed","36.101; 36.104; 36.133; 36.141; 37.141",46,24,null,null,"2009-11-30","2012-06-07"]
[6556,460208,"   Perf. part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Perf",2,"Rel-10","R4","2009-12-04","2012-03-02",1,"RP-091429","RP-120053","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#55 completed","36.101; 36.104; 36.133; 36.141",46,24,null,null,"2009-11-30","2012-02-23"]
[6559,460109,"   Core part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-Core",2,"Rel-10","R1,R2,R4","2000-01-03","2001-06-29",1,"RP-100959","RP-110537","Huawei","Mattias.wennstrom@huawei.com","RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval","36.101; 36.104; 36.133; 36.201; 36.211; 36.212; 36.213; 36.300; 36.306; 36.321; 36.331; new RAN4 (36.807; 36.817)",46,24,null,null,"2009-11-30","2012-06-07"]
[6562,460013,"Relays for LTE","LTE_Relay",1,"Rel-10","R1,R2,R4,S2,S3,C4,C6","2009-12-04","2011-06-08",1,"RP-110911","-","Ericsson","christian.hoymann@ericsson.com","RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11)","LTE",46,24,null,null,"2009-11-30","2011-02-14"]
[6565,520020,"   Stage 2 for Relays for LTE","LTE_Relay",2,"Rel-10","S2","2011-06-06","2011-06-08",1,"-","-","Vodafone","chris.pudney@vodafone.com","SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview",23.401,52,27,null,null,"2011-06-06","2011-06-06"]
[6570,510012,"   Core Network Impacts for Relay Nodes","LTE_Relay-CN",2,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110094","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","23.003; 23.008; 29.303; 29.230; 29.272",51,26,null,null,"2011-02-28","2011-03-08"]
[6574,550001,"   Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-UEConTest",2,"Rel-10","R5","2012-03-05","2014-06-13",1,"RP-120217","RP-140766","Qualcomm","Anjali Mishra (ajha@qualcomm.com)","RP#64 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",55,28,null,null,"2012-02-23","2014-06-10"]
[6578,480019,"   UE conformance test part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-UEConTest",2,"Rel-10","R5","2010-06-04","2010-12-10",1,"RP-100615","RP-101071","Clearwire","michael.hart@clearwire.com","RP#50 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",48,25,null,null,"2010-06-01","2010-12-03"]
[6581,470209,"   Perf. part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-110775","RP-110546","DBSD","Mariam.Sorond@ico.com","RP#52 completed","36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.811",47,24,null,null,"2010-03-19","2011-06-01"]
[6582,520012,"   Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-06-07","2011-12-09",1,"RP-110623","RP-111444","DBSD","Mariam.Sorond@ico.com","RP#54 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",52,27,null,null,"2011-05-23","2011-11-29"]
[6585,470210,"   Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-101284","RP-110548","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#52 completed","34.121-1; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.521-1; 36.813",47,24,null,null,"2010-03-19","2011-05-24"]
[6591,540008,"   Test part: Further enhancements to MBMS for LTE","MBMS_LTE_enh-UEConTest",2,"Rel-10","R5","2011-12-02","2012-03-02",1,"RP-111615","RP-120049","Huawei","Zhang Xin (suzanna.zhang@huawei.com)","RP#55 completed","36.508; 36.523-1; 36.523-2; 36.523-3",54,28,null,null,"2011-11-24","2012-02-23"]
[6593,380073,"   Core part: UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",2,"Rel-10","R4,R2,R3","2007-11-30","2011-09-16",1,"RP-091380","RP-110987","Ericsson","johan.skold@ericsson.com","RP#53 completed. TR 37.801v200 for Approval","25.101; 25.104; 25.113; 25.133; 25.141; 25.307; 25.307; 25.331; 25.461; 25.463; 34.124; 36.101; 36.104; 36.113; 36.141; 36.331; new 37.801",38,21,null,null,"2007-12-17","2011-09-09"]
[6596,460003,"Minimization of Drive Tests for E-UTRAN and UTRAN","MDT_UMTSLTE",1,"Rel-10","R2,R4,R3,R5","2009-12-04","2013-03-01",1,"RP-100360","-","Nokia Siemens Networks","malgorzata.tomala@nsn.com","Triggered by UID_430021 TR 36.805 (Study on Minimization of drive-tests in NGN)","UTRA; LTE",46,24,null,null,"2009-11-30","2013-02-27"]
[{"$f":"A6600+1","v":6600},470105,"   Core part: HNB and HeNB Mobility Enhancements","HNB_HENB_mob_enh-Core",2,"Rel-10","R3,R2","2010-03-19","2011-03-18",1,"RP-110183","RP-110058","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#51 completed","25.413; 25.467; 25.469; 36.300; 36.413; 36.423; new 25.471",47,24,null,null,"2010-03-19","2011-03-11"]
[6604,480224,"   Perf. part: Expanded 1900 MHz Band for UTRA and LTE","E1900-Perf",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100676","RP-110530","Sprint","nick.j.baustert@sprint.com","RP#52 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.331; new 36.818",48,25,null,null,"2010-06-04","2011-05-24"]
[6607,480125,"   Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-Core",2,"Rel-10","R4","2010-06-04","2011-06-03",1,"RP-101402","RP-110531","Ericsson","johan.skold@ericsson.com","RP#52 completed","25.104; 36.104; 37.104; new 37.802",48,25,null,null,"2010-06-04","2011-06-01"]
[6608,480225,"   Perf. part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-Perf",2,"Rel-10","R4","2010-06-04","2011-09-16",1,"RP-101402","RP-110988","Ericsson","johan.skold@ericsson.com","RP#53 completed","25.141; 36.141; 37.141; 37.802",48,25,null,null,"2010-06-04","2011-09-12"]
[6613,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[6616,350014,"Deleted - Registration in Densely-populated area (RED)","RED",1,"Rel-10","S1","2007-03-12","2009-09-24",1,"SP-070133","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned","-",35,18,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6619,380062,"Deleted - Network Selection for non-3GPP Access","N3GtoNSP",1,"Rel-10","S1,C6","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned","-",38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6622,420025,"Deleted - GTP-based S8 chaining","GTPchaining",1,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080798","-","Huawei","Haining Wang (wanghaining@huawei.com)","SP#47 work stopped (depending on ongoing related CT4 work). Stage 1 in UID_320022 Rel-8 Requirements for evolution of the 3GPP system architecture (AIPN-SAE): 22.278, 22.011, 22.246","-",42,22,"SP-47","PCG-24","2008-12-05","2010-03-07"]
[6627,460110,"   Deleted - Core part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-Core",2,"Rel-10","R4","2009-12-04","2011-06-03",1,"RP-091432","RP-110539","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped at 55% (lack of contributions)",36.100999999999999,46,24,"RP-52","PCG-27","2009-11-30","2011-03-16"]
[6630,460112,"   Deleted - Core part: Latency reductions for LTE","LTE_LATRED-Core",2,"Rel-10","R2,R1","2009-12-04","2010-12-10",1,"RP-091449","RP-101112","Ericsson","henrik.enbuske@ericsson.com","RP#50 work stopped (RP-101266)","36.213; 36.300; 36.306; 36.321; 36.331",46,24,"RP-50","PCG-26","2009-11-30","2010-12-08"]
[6633,0,"Release 10 Studies","-",1,"Rel-10","CP,GP,RP,SP","2009-03-12","2009-03-12",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[6635,370047,"   Use cases definition and service and system requirements","FS_EV_EPS-S1",2,"Rel-10","S1","2007-09-03","2008-12-11",1,"SP-070698","-","France Telecom","philippe.lottin@orange.com","SP#47 completed. TR 22.813-100 for Approval",22.812999999999999,37,19,null,null,"2007-10-04","2010-08-31"]
[6638,410039,"Study on Personal Broadcast Service","FS_PBS",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080504","-","ETRI","Jaihyung Cho","SP#47 completed",22.946999999999999,41,21,null,null,"2008-09-15","2010-03-09"]
[6642,390055,"Study on Intra Domain Connection of RAN Nodes to Multiple CN Nodes","FS_IDC",1,"Rel-10","S2","2008-03-12","2010-03-25",1,"SP-080094","-","China Mobile","LIU HONG (liuhongyfw@chinamobile.com)","SP#47 completed. Concluded no further normative work expected. Linked to 23.236","23.924 (was 23.823)",39,21,null,null,"2007-12-20","2010-03-23"]
[6644,470048,"Study on Single Radio Video Call Continuity for 3G-CS","FS_vSRVCC",1,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100168","-","Samsung","Haris Zisimopoulos (haris.z@samsung.com)","SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user",23.885999999999999,47,24,null,null,"2010-03-10","2010-09-15"]
[6649,430044,"Study on Telecommunication Management; Energy Savings Management","FS_OAM_ESM",1,"Rel-10","S5","2009-03-12","2010-03-25",1,"SP-090048","-","Orange, Vodafone","Jean-Michel Cornilly (Orange)","SP#47 completed. Study result might impact Feature UID_420011 Self Organising Networks (SON)",32.826000000000001,43,22,null,null,"2009-02-23","2010-03-08"]
[6653,480045,"Study on Alarm Correlation and Alarm Root Cause Analysis","FS_AC_ARCA",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100775","-","Ericsson","edwin.tse@ericsson.com","SP#51 completed",32.832000000000001,48,25,null,null,"2010-05-26","2011-03-09"]
[6656,480016,"Study on User Data Convergence (UDC) evolution ","FS_UDCe",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100296","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model",23.844999999999999,48,25,null,null,"2010-05-26","2011-02-28"]
[6657,480017,"Study on UICC access to IMS","FS_IMS-UICC",1,"Rel-10","C6","2010-06-04","2011-03-18",1,"CP-100424","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#51 completed",31.827999999999999,48,25,null,null,"2010-05-26","2011-03-03"]
[6661,470016,"Study on Improvements of distributed antenna for 1.28Mcps TDD","FS_distr_ant_LCR_TDD",1,"Rel-10","R1,R2,R3","2010-03-05","2010-12-10",1,"RP-100178","RP-101287","ZTE","huang.he4@zte.com.cn","RP#50 completed. TR 25.865 v101 for Approval","UTRA 25.865",47,24,null,null,"2010-03-19","2010-12-07"]
[{"$f":"A6664+1","v":6664},440050,"Deleted - Study on EPC Charging enhancement","FS_EPCcharg",1,"Rel-10","S5","2009-06-04","2010-03-25",1,"SP-090318","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#47 work stopped. Issue covered by Rel-10 UID_460039 Charging for LIPA_SIPTO and UID_4700xy Charging for IFOM ","-",44,23,"SP-47","PCG-24","2009-05-18","2009-07-06"]
[6668,400047,"   Stage 1 for EHNB","EHNB",2,"Rel-9","S1","2008-06-05","2009-06-04",1,"SP-080791","-","T-Mobile","michael.kurz@t-mobile.at ","CP#49 the SA1-reqs are moving. CT1 will align when the work in SA1 is clear. (was SP#44 completed.) ","22.220; 22.011",40,21,null,null,"2007-12-13","2010-09-06"]
[6670,420035,"   Security aspects of Enhanced Home NodeB / eNodeB","EHNB-Sec",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080879","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#46 completed","New 33.320",42,22,null,null,"2008-12-09","2009-12-07"]
[6675,440066,"   3G HNB and LTE HeNB OAM&P Type 2 Interface","HNB_eHNB-OAM_Type2",2,"Rel-9","S5","2009-05-15","2010-03-25",1,"SP-090315","-","Ericsson","edwin.tse@ericsson.com","SP#47 completed","New (32.571; 32.572)",44,23,null,null,"2009-05-18","2010-03-08"]
[6679,430026,"   Home NB and Home eNB enhancements - RAN2 aspects","EHNB-RAN2",2,"Rel-9","R2","2009-03-06","2010-03-19",1,"RP-091392","RP-100037","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#47 completed","25.304; 25.331; 25.367; 36.300; 36.304; 36.331",43,22,null,null,"2009-03-10","2010-03-16"]
[6683,370026,"Value-Added Services for Short Message Service","VAS4SMS",1,"Rel-9","S1,C4,C1","2007-09-10","2009-12-04",1,"SP-070572","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed","-",37,19,null,null,"2007-10-02","2009-11-16"]
[6684,370126,"   Stage 1 for VAS4SMS","VAS4SMS",2,"Rel-9","S1","2007-09-10","2008-03-12",1,"SP-070572","-","China Mobile","Wu Bin (wubin@chinamobile.com)","SP#39 completed. SP#43 Feature moved to Rel-9","new 22.142",37,19,null,null,"2007-10-02","2009-03-04"]
[6687,370027,"Definition of End-User Identity","EUI",1,"Rel-9","S1","2007-09-03","2008-12-11",1,"SP-090380","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905)","-",37,19,null,null,"2007-10-02","2010-08-05"]
[6690,410025,"   Stage 1 for Customized Ringing Signal","CRS",2,"Rel-9","S1","2007-12-06","2008-12-11",1,"SP-080502","-","SK Telecom, China Mobile","Donghee Shim (SK Telecom), Jianping Zheng (China Mobile)","SP#42 completed. ","22.173; new 22.183",38,21,null,null,"2007-12-13","2008-12-05"]
[6696,440031,"      CT4 aspects of Stage 3 for Public Warning System","PWS-St3",3,"Rel-9","C4","2009-05-30","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#46 completed",29.167999999999999,44,23,null,null,"2009-05-13","2009-12-03"]
[6698,540005,"   Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE","PWS-RAN_UEConTest",2,"Rel-9","R5","2011-12-02","2012-12-07",1,"RP-111564","RP-121525","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#58 completed","36.508; 36.523-1; 36.523-2; 36.523-3",54,28,null,null,"2011-11-24","2012-12-04"]
[6701,430002,"   Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-06","2009-12-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#46 completed",23.259,43,22,null,null,"2009-03-05","2009-11-16"]
[6705,430031,"   Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services)","eMMTel-SS-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090196","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#47 completed","32.275; 32.298; 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[6709,400046,"   Stage 1 for User Data Convergence (UDC)","UDC",2,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080448","-","Nokia Siemens Networks","juergen.merkel@nsn.com ","SP#42 completed","22.101; new 22.985",40,21,null,null,"2007-12-13","2010-08-31"]
[6710,430103,"   Stage 2/3 for User Data Convergence (UDC) Technical Realization","UDC-CN",2,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","-","-",43,22,null,null,"2009-03-04","2010-03-09"]
[6713,440060,"   User Data Convergence (UDC) Modelling and Management","UDC-MMAN",2,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090309","-","T-Mobile, China Mobile, Ericsson","istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com","SP#48 completed","-",44,23,null,null,"2009-05-18","2010-05-26"]
[6718,410134,"   Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","-","-",41,21,null,null,"2008-09-15","2012-07-20"]
[6721,410135,"   Stage 2/3 for IMS Centralized Services","IMS_SCC-ICS",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-","-",41,21,null,null,"2008-09-15","2009-06-02"]
[6724,430004,"   Stage 3 - IMS Centralized Services support via I1 interface","IMS_SCC-ICS_I1",2,"Rel-9","C1","2009-03-06","2010-03-19",1,"CP-090640","-","Huawei","Lili Yang(kadyyang@huawei.com)","CP#47 completed","24.237; 24.292; new 24.294",43,22,null,null,"2009-03-05","2010-03-02"]
[6727,440040,"   Stage 3 for Service Specific Access Control in EPS","SSAC",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090885","-","NTT DoCoMo","Hideyuki Yamashita (yamashitahi@s1.nttdocomo.co.jp)","CP#47 completed","24.173; 27.007",44,23,null,null,"2009-05-13","2010-03-02"]
[6732,420022,"   Security aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS-Sec",2,"Rel-9","S3","2008-12-12","2010-06-10",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#48 completed","33.401; 33.402",42,22,null,null,"2008-12-09","2010-05-05"]
[6735,480029,"      Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS_UEConTest",3,"Rel-9","R5","2010-06-04","2012-06-15",1,"RP-100567","RP-120445","Samsung","stoyan.baev@partner.samsung.com","RP#56 completed","34.108; 34.123-1; 34.123-2; 34.123-3; 34.229-1; 34.229-2; 34.229-3; 36.508; 36.523-1; 36.523-2; 36.523-3",48,25,null,null,"2010-06-04","2012-06-05"]
[6736,440037,"      CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC3",3,"Rel-9","C3","2009-05-29","2009-09-18",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#45 completed","29.212; 29.213; 29.214; 29.215",44,23,null,null,"2009-05-13","2009-09-09"]
[6740,410038,"   Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",2,"Rel-9","S2,C1,C4,C3,IETF","2008-09-18","2014-06-13",1,"SP-090099","-","China Mobile","Yu Qing (Yuqing@chinamobile.com)","CP#56 added IETF dependency","-",41,21,null,null,"2008-09-15","2009-03-05"]
[6743,440027,"         CT1 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","24.229; 24.237",44,23,null,null,"2009-05-13","2009-12-02"]
[6747,430006,"LCS for LTE and EPS","LCS_LTE_EPS",1,"Rel-9","S2,C1,C4,R2,R1,R3,R4,R5","2008-06-05","2012-03-02",1,"-","-","-","-","-","LTE",43,22,null,null,"2009-02-18","2010-03-16"]
[6749,400048,"      Stage 2 for LCS Control Plane Solution for EPS","LCS_EPS-CPS",3,"Rel-9","S2","2008-06-05","2009-06-04",1,"SP-080445","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","SP#44 completed","23.891; 23.271; 23.401; 23.402",40,21,null,null,"2007-12-13","2009-06-01"]
[6755,400040,"   Stage 2 for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S2","2008-06-05","2009-06-04",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#44 completed",23.245999999999999,40,21,null,null,"2007-12-13","2009-06-01"]
[6758,440025,"   CT4 aspects of MBMS support in EPS (Stage 3)","MBMS_EPS",2,"Rel-9","C4","2009-05-29","2009-12-04",1,"CP-090325","-","China Mobile, ZTE","wangjingyf@chinamobile.com, lu.fei1@zte.com.cn","CP#46 completed","29.274; 29.281; 23.007; 23.008",44,23,null,null,"2009-05-13","2009-11-16"]
[6761,500024,"   Conformance Test Aspects – MBMS support in LTE","MBMS_LTE-UEConTest",2,"Rel-9","R5","2010-12-10","2011-12-09",1,"RP-101245","RP-111437","Huawei","Zhang Xin (zhangxin0208@huawei.com)","RP#54 completed","36.508; 36.521-1; 36.521-2; 36.523-1; 36.523-2; 36.523-3",50,26,null,null,"2010-12-10","2011-11-29"]
[6762,420024,"Access Network Discovery and Selection Function enhancements","eANDSF",1,"Rel-9","S2,C1","2008-12-11","2010-03-19",1,"SP-080887","-","Motorola","Apostolis Salkintzis (salki@motorola.com)","CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8","22.278; SA3 33.402 CR#0055",42,22,null,null,"2008-12-05","2010-03-04"]
[6766,430134,"   Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",2,"Rel-9","S2","2009-03-13","2009-06-04",1,"SP-090098","-","Samsung","erik.guttman@partner.samsung.com","SP#44 completed","23.060; 23.203; 23.401; 23.402",43,22,null,null,"2009-03-05","2009-09-08"]
[6769,450049,"System aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",1,"Rel-9","S2,S4,C1,C3,R2,IETF","2007-05-07","2012-09-12",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE","LTE",45,23,null,null,"2009-05-28","2012-09-03"]
[6775,33025,"Access Security Enhancements","ACCSEC2",1,"Rel-9","S3","2007-07-02","2009-06-04",1,"SP-040865","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security)","33.102; 43.020",33,17,null,null,"2005-03-24","2010-08-06"]
[6777,410028,"   Stage 1 for PUCI","PUCI",2,"Rel-9","S1","2008-09-18","2008-12-11",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#42 completed",22.228000000000002,41,21,null,null,"2008-09-15","2008-12-05"]
[6781,521007,"   (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security","MEDIASEC",2,"Rel-9","S3-IETF,C1-IETF,C3-IETF","2009-03-18","2012-09-14",1,"SP-090128","-","Peter Dawes","-","CP#57 completed, ietf-draft discontinued, documented within 3GPP","draft-dawes-dispatch-mediasec-parameter",52,27,null,null,"2011-06-20","2012-09-03"]
[6784,450010,"      CT1 aspects of IMS Media Plane Security","MEDIASEC_CORE",3,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#47 completed","23.218; 24.229",45,23,null,null,"2009-02-11","2010-03-02"]
[6788,420039,"   SA3 part of eGBAPush (Generic push layer)","eGBAPush",2,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#47 completed","New 33.224",39,21,null,null,"2008-03-22","2010-02-23"]
[6789,440054,"Extended Identity Management","GBA-IdM",1,"Rel-9","S3","2009-06-04","2009-12-10",1,"SP-090284","-","Nokia","Silke.Holtmanns@nokia.com","SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous)","New 33.924; CT4 29.109 (added service code)",44,23,null,null,"2009-05-18","2010-02-23"]
[{"$f":"A6792+1","v":6792},521008,"   (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3-IETF","2009-06-04","2012-12-07",1,"SP-090286","-","Bengt Sahlin","-","CP#58 completed","RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols)",52,27,null,null,"2011-06-20","2012-11-24"]
[6797,440457,"   CT4 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C4","2009-06-04","2009-12-10",1,"SP-090287","-","Ericsson","Karl Norrman","CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060","-",44,23,null,null,"2009-05-18","2009-11-16"]
[6800,440257,"   Deleted - SA2 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090287","-","Ericsson","Karl Norrman","SP#45 work stopped/abandoned",23.06,44,23,"SP-45","PCG-23","2009-05-18","2009-09-07"]
[6803,440046,"PSS and MBMS Aspects","PMA",1,"Rel-9","S4","2009-03-12","2010-03-25",1,"SP-090261","-","Ericsson, Nokia","Clinton.Priddle@ericsson.com, imed.bouazizi@nokia.com","Umbrella WI","-",44,23,null,null,"2009-05-31","2010-03-08"]
[6807,440051,"Syndicated Feed Reception within 3GPP environments","SFR",1,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090260","-","Ericsson","Thorsten.Lohmar@ericsson.com","SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD.","New 26.150",44,23,null,null,"2009-05-31","2009-12-07"]
[6810,420030,"   Rel-9 Network Infrastructure Management","OAM9-NIM",2,"Rel-9","S5","2008-12-11","2010-03-25",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[6814,420032,"   Rel-9 Performance Management","OAM9-PM",2,"Rel-9","S5","2009-03-12","2010-06-10",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[6815,440059,"      Enhancement of UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-06-04","2009-12-10",1,"SP-090308","-","China Mobile","liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao","SP#46 completed",32.405000000000001,44,23,null,null,"2009-05-18","2009-12-01"]
[6818,430043,"   Rel-9 Self-Organizing Networks (SON) - OAM aspects","OAM9-SON",2,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","SP#43 umbrella BB created to host OAM WIs","-",43,22,null,null,"2009-03-09","2010-02-09"]
[6823,440068,"Rel-9 Charging Management small Enhancements","CH9",1,"Rel-9","S5","2009-06-04","2010-03-25",1,"-","-","-","-","CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,44,23,null,null,"2009-05-19","2010-03-08"]
[6826,400010,"   CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications","CS-IBCF",2,"Rel-9","C4","2008-05-30","2009-12-04",1,"CP-090073","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#46 completed","23.231; 29.232; new 29.238",40,21,null,null,"2007-09-05","2009-11-25"]
[6829,410208,"   CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C3","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","29.162; 29.235",41,21,null,null,"2007-09-05","2009-11-25"]
[6832,420017,"   Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service","eCAT-SS",2,"Rel-9","C1","2008-12-05","2010-06-04",1,"CP-080796","-","China Mobile","Jiang Yi","CP#48 completed",24.181999999999999,42,22,null,null,"2008-12-04","2010-05-28"]
[6837,440039,"IMS Stage 3 IETF Protocol Alignment - phase 3","IMSProtoc3",1,"Rel-9","C1,IETF","2009-05-29","2014-12-05",1,"CP-090491","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","-",44,23,null,null,"2009-05-13","2010-03-02"]
[6838,440139,"   CT1 aspects of IMS Stage 3 - IETF Protocol Alignment - phase 3","IMSProtoc3",2,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090491","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","23.218; 24.229; 24.930",44,23,null,null,"2009-05-13","2010-03-02"]
[6841,440070,"Operational description of the Inter-IMS Network to Network Interface (II-NNI)","II-NNI",1,"Rel-9","C3,IETF","2009-05-29","2014-12-09",1,"CP-090331","-","Orange","sebastien.daudet@orange-ftgroup.com","-","-",44,23,null,null,"2009-05-29","2013-02-28"]
[6845,561006,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100","draft-ietf-salud-alert-info-urns",56,29,null,null,"2012-04-20","2016-03-07"]
[6849,591002,"   Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface (avasarala-dispatch-comm-div-notification)","II-NNI",2,"Rel-9","C3-IETF","2013-03-01","2014-06-13",1,"CP-090331","-","Andrew Allen","Andrew Allen","CP#64 Draft removed from 3GPP documentation","draft-avasarala-dispatch-comm-div-notification",59,30,"SP-69",null,"2013-02-21","2014-06-06"]
[6852,460004,"3GPP IMS Conferencing Management Object (MO)","IMS_ConfMO",1,"Rel-9","C1","2009-12-03","2009-12-04",1,"-","-","-","-","CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2)","New 24.166",46,24,null,null,"2009-12-08","2010-02-09"]
[6854,410023,"Rel-9 Improvements of the Radio Interface","RInImp9",1,"Rel-9","RP,GP","2008-09-12","2010-03-19",1,"-","-","-","-","RP#41 umbrella Feature created to host Rel-9 WIs","GERAN; UTRA; LTE",41,21,null,null,"2005-01-04","2010-03-16"]
[6860,430009,"   UMTS/LTE 800 MHz for Europe","RInImp9-UMTSLTE800EU",2,"Rel-9","R4,R2,R3","2009-03-06","2009-03-06",1,"RP-090156","RP-100028","Ericsson","olav.queseth@ericsson.com","RP#47 completed","UTRA; LTE 25.101; 25.104; 25.113; 25.133; 25.141; 34.124; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; new 36.810; 25.306; 25.307; 25.331; 36.331; 25.461; 25.466",43,22,null,null,"2009-02-26","2010-03-16"]
[6863,440006,"Rel-9 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-9","R5","2009-05-19","2010-09-17",1,"-","-","-","-","-","UTRA; LTE",44,23,null,null,"2009-05-18","2009-05-28"]
[6864,440007,"   Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe","RInImp-UEConTest-UMTSLTE800EU",2,"Rel-9","R5","2009-05-19","2010-09-17",1,"RP-090485","RP-100736","Ericsson","fredrik.sundstrom@ericsson.com","RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe","UTRA; LTE 34.108; 34.121-1; 34.121-2; 36.508; 36.521-1; 36.521-2; 36.521-3",44,23,null,null,"2009-05-18","2010-09-08"]
[6867,470019,"   Conformance Test Aspects – Performance requirement for LCR TDD with UE speeds up to 350 km/h","RInImp9-LCRTDD350_UEConTest",2,"Rel-9","R5","2010-03-19","2010-06-04",1,"RP-100167","RP-100496","CATT","Xiaozhong Chen (chexiaozhong@datangmobile.cn)","RP#48 completed. Testing for UID_430010 Performance requirement for LCR TDD with UE speeds up to 350 km/h","UTRA 34.122",47,24,null,null,"2010-03-17","2010-06-01"]
[6871,430015,"   Support for different bands for Dual-Cell HSDPA","RANimp-MultiBand_DC_HSDPA",2,"Rel-9","R4,R2,R3","2009-03-06","2009-03-06",1,"RP-090973","RP-091038","Nokia Siemens Networks","Tuomo Säynäjäkangas (tuomo.saynajakangas@nsn.com)","RP#46 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.133; 25.306; 25.308; 25.331; 25.423; 25.433; new 25.317 replaced by new 25.327",43,22,null,null,"2009-03-06","2009-11-26"]
[6875,490025,"Rel-9 RAN improvements - UE Conformance Testing","-",1,"Rel-9","R5","2010-09-17","2012-12-07",1,"-","-","-","-","-","-",49,25,null,null,"2010-09-08","2010-09-20"]
[6880,430019,"   LTE Pico NodeB RF Requirements","LTEimp-Pico_eNB-RF",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-091155","RP-091045","Huawei","Liyan Yin (yinliyan@huawei.com)","RP#46 completed","36.104; 36.141; new 36.931",43,22,null,null,"2009-02-27","2010-02-08"]
[6882,490018,"   UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD","LTEimp-eDL_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-100868","RP-110509","China Mobile","Shanpeng Xiao (xiaoshanpeng@chinamobile.com)","RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE)","36.508; 36.521-1; 36.521-2",49,25,null,null,"2010-09-09","2011-05-18"]
[6886,38004,"   AGNSS Testing Procedures","AGNSSPTP-MStest",2,"Rel-9","G3new","2008-05-16","2011-05-20",1,"GP-092343","-","Thales","Michel.monnerat@thalesaleniaspace.com","GP#50 completed","51.010-1; new 51.010-7",38,20,null,null,"2008-05-19","2011-05-21"]
[6889,420004,"   Stage 3 for Voice services over Adaptive Multi-user channels on One Slot","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-03-04",1,"GP-081965","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#49 completed. GP#40 WID approved","24.008; 44.018; 45.002; 45.003; 45.004; 45.008; 48.008; 48.058",40,22,null,null,"2008-11-23","2011-03-04"]
[6893,440002,"Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC)","CEBRO",1,"Rel-9","GP,C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed. GP#45 completed. GP#42 WID approved","-",42,23,null,null,"2009-05-18","2010-03-05"]
[6894,440102,"   GERAN part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre","CEBRO",2,"Rel-9","GP","2009-05-15","2010-03-05",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","GP#45 completed. GP#42 WID approved","new 48.049",42,23,null,null,"2009-05-18","2010-03-05"]
[6897,420099,"(Small) Technical Enhancements and Improvements for Rel-9","TEI9",1,"Rel-9","SP,CP,RP,GP","2008-09-15","2009-12-10",1,"-","-","-","-","SP#46 completed","-",42,22,null,null,"2005-11-04","2009-11-25"]
[6902,380081,"Deleted - Support of WiMAX - LTE Mobility","WiMAX_LTE_Mobility",1,"Rel-9","R2","2008-06-06","2009-12-25",1,"RP-070511","-","Samsung","-","RP#39: No agreed WID","36.306; 36.331; 36.413; 36.300; 36.214; 36.133; 36.304",38,21,"SP-39","PCG-21","2007-12-17","2009-03-24"]
[6905,390040,"Deleted - SAES Enhancements (non RAN aspects)","SAES_Ph2",1,"Rel-9","S2","2007-06-25","2008-12-08",1,"-","-","Nokia Siemens Networks","-","SP#39 created to host Rel-9 Wis. BUT no agreed WID","-",39,20,"SP-39","PCG-21","2005-01-31","2009-03-24"]
[6909,390043,"      Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX","SAES_Ph2",3,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-04-26","2009-03-24"]
[6912,400036,"Study on Service Specific Access Control in EPS","FS_SSAC",1,"Rel-9","S1","2008-06-05","2008-12-11",1,"SP-080319","-","NTT DoCoMo","Shin-ichi Isobe (isobes@nttdocomo.co.jp)","SP#42 completed. Spin-off Feature UID_420020 (SSAC)",22.986000000000001,40,21,null,null,"2007-12-13","2010-08-31"]
[6915,320031,"Study on Service Continuity for Emergency Voice Calls","FS_VCCEm",1,"Rel-9","S2","2006-06-08","2009-03-12",1,"SP-080555","-","Nortel","Ricky Kaura (rkaura@nortel.com)","SP#43 completed",23.826000000000001,32,17,null,null,"2006-07-19","2009-02-24"]
[6917,360006,"Study on System Maintenance over Itf-N","FS_OAM-Maint-Itf-N",1,"Rel-9","S5","2007-06-07","2009-09-24",1,"SP-070306","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#45 completed",32.822000000000003,36,19,null,null,"2007-05-28","2009-09-07"]
[{"$f":"A6920+1","v":6920},400029,"Study on Service Oriented Architecture (SOA) for IRP","FS_OAM_SOA_IRP",1,"Rel-9","S5","2008-06-05","2009-06-04",1,"SP-080281","-","Ericsson","edwin.tse@ericsson.com","SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP",32.823999999999998,40,21,null,null,"2007-05-28","2009-06-02"]
[6924,420012,"Study on E-UTRAN Mobility Evaluation and Enhancement","FS_EUTRAN_mob",1,"Rel-9","R1","2008-12-05","2009-05-29",1,"RP-081137","RP-090426","Qualcomm","Rajat Prakash (rprakash@qualcomm.com)","RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed)","none",42,22,null,null,"2008-12-04","2009-05-20"]
[6928,320026,"Deleted - Study on Protection against SMS and MMS spam","FS_CPSMal",1,"Rel-9","S3","2006-06-08","2009-09-24",1,"SP-060446","-","Orange","eric.gauthier@orange.ch","SP#45 work stopped/abandoned","33.9xx",32,17,"SP-45","PCG-23","2006-06-23","2009-09-21"]
[6931,320022,"   Requirements for evolution of the 3GPP system architecture ","AIPN-SAE",2,"Rel-8","S1","2006-06-08","2007-12-12",1,"SP-080132","-","T-Mobile","michael.kurz@t-mobile.at ","SP#38 completed","22.011; 22.246; New 22.278",32,17,null,null,"2006-06-23","2010-07-28"]
[6935,340051,"      Stage 3 (CT1) for SAE impact on services, network functions and capabilities","SAES",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.229; 27.007; New 24.305",34,18,null,null,"2006-07-19","2010-07-28"]
[6937,340062,"      Stage 3 (CT4) of SAE impact on existing capabilities","SAES",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","New (29.274; 29.275)",34,18,null,null,"2006-07-19","2010-07-28"]
[6942,370017,"      Unified guidelines for Diameter usage within 3GPP","SAES-DIAM",3,"Rel-8","C3","2007-09-21","2008-12-05",1,"CP-080055","-","Huawei","Javier Gonzalez Gallego","CP#42 completed","New 29.909",37,19,null,null,"2007-09-25","2010-07-28"]
[6943,350025,"   SAE for LTE access ","SAES-LTE",2,"Rel-8","S2,C1,C3,C4","2007-01-02","2009-03-06",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6946,370006,"         Stage 2 for SAES-SA-FP_LTE with GTP variant","SAES-SA-FP_LTE-GTP-St2",4,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","23.401; 23.060; 23.002; 23.246; 23.203; 23.107; 23.234; 23.271",37,19,null,null,"2007-09-19","2010-07-28"]
[6951,410004,"         Mobile IPv4 (MIPv4) based Mobility protocols","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Motorola","Lewis Milton","CP#42 completed",29.279,41,21,null,null,"2006-07-19","2010-07-28"]
[6954,340053,"      Stage 3 for security aspects of LTE Access","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008; 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[6957,350026,"   SAE for Interoperation between LTE and legacy cellular PS accesses","SAES-SA-FP_3GPP",2,"Rel-8","S2,C1,C4","2007-02-05","2009-03-06",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6959,380031,"      Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008; 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[6965,370009,"      Stage 2 for Interoperation between LTE and CDMA2000","EPStoC2k",3,"Rel-8","S2","2007-06-18","2008-09-18",1,"SP-080132","-","Motorola, Vodafone","Irfan.Ali@motorola.com, chris.pudney@vodafone.com","SP#41 completed (except: Handover of multiple PDNs=>Rel-9)","23.401; 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[6968,350027,"   SAE for support for non-3GPP accesses ","SAES-SA-FP_n3GPP",2,"Rel-8","S2,S3,C1,C4,IETF","2007-01-02","2012-06-15",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037","-",35,18,null,null,"2007-03-29","2010-07-28"]
[6969,350044,"      Stage 2 for Host-based Mobility aspects","SAES-SA-FP_n3GPP-HBMob",3,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed",23.402000000000001,35,18,null,null,"2007-04-26","2010-07-28"]
[6972,521011,"      (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt)","SAES-SA-FP_n3GPP",3,"Rel-8","C1-IETF","2007-02-05","2012-06-15",1,"CP-080493","-","Mark Jones","-","CP#56 completed; 9/4/21: RFC 6610 added;","RFC 6610 (was draft-ietf-mip6-hiopt); RFC 6610",52,27,null,null,"2011-06-20","2021-04-09"]
[6977,390045,"      Stage 2 Security aspects for non-3GPP Access","SAES-SA-FP_n3GPP",3,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080132","-","Nokia Siemens Networks","marc.blommaert.ext@nsn.com","SP#42 completed","33.402; 33.210; 33.310",39,21,null,null,"2008-03-19","2010-07-28"]
[6980,360021,"      Stage 3 for Access to the EPC via non-3GPP access networks","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.302; 24.312",36,19,null,null,"2007-09-12","2010-07-28"]
[6985,340059,"      Stage 3 for EPC - AAA interface","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[6988,350130,"      Stage 2 for 2G/3G SRVCC","SAES-SRVCC",3,"Rel-8","S2","2007-01-02","2008-09-18",1,"SP-070949","-","Nokia Siemens Networks","curt.c.wong@nokia.com","SP#41 completed. SP#38 WID approved","New 23.216",35,18,null,null,"2007-03-29","2010-07-28"]
[6991,360020,"   Voice Call Continuity for CDMA2000 1X","SAES-VCC_1X",2,"Rel-8","S2","2007-06-25","2008-06-05",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","SP#40 completed","-",36,19,null,null,"2007-03-29","2010-07-28"]
[6994,400001,"      Stage 2 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","SP#40 completed","New (23.272; 23.401)",40,21,null,null,"2007-03-29","2010-07-28"]
[6998,390010,"   EPC Data Definitions","EPC-OAM",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"-","-","-","-","SP#43 completed","-",39,21,null,null,"2005-06-17","2010-07-28"]
[6999,380037,"      EPC Network Resource Model (NRM) Integration Reference Point (IRP)","EPC-OAM",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070737","-","Huawei","WANG, Xuelong","SP#43 completed","New (32.751; 32.752; 32.753; 32.755)",38,21,null,null,"2005-06-17","2009-02-23"]
[7003,410007,"   InterWorking Function (IWF) between MAP based and Diameter based interfaces","SAES-MAP2Diam",2,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080644","-","Huawei","liming49985@huawei.com","CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam)","New 29.305",41,21,null,null,"2007-11-19","2010-07-28"]
[7007,490015,"      Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS)","SAES-ISIM_IMS_Test",3,"Rel-8","C6","2010-09-17","2011-06-03",1,"CP-100602","-","Comprion","Udo Willenbrink (uwillenbrink@comprion.com )","CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229).","31.121; 31.124; New 31.134",49,25,null,null,"2010-09-06","2011-05-18"]
[7010,390020,"   Deleted - Issues for CT4 TR 29.803","SAES",2,"Rel-8","C4","2007-01-04","2008-09-12",1,"CP-080068","-","Huawei","-","CP#41 Work stopped and continued in Normative specifications",29.803000000000001,39,21,"CP-41","PCG-21","2006-07-19","2009-03-24"]
[7014,350019,"      Deleted - CT1 aspects of SAES","SAES-St3",3,"Rel-8","C1","2007-09-04","2007-09-04",1,"CP-060674","-","-","-","SP#37 stopped","-",35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[7017,350021,"      Deleted - CT4 aspects of SAES","SAES",3,"Rel-8","C4","2007-09-04","2007-09-04",1,"CP-060676","-","-","-","SP#37 stopped",29.803000000000001,35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[7020,340037,"   Deleted - Architecture enhancements for non-3GPP accesses","SAES-non_3GPP",2,"Rel-8","S2","2007-09-04","2007-09-04",1,"SP-060926","-","Motorola","Irfan.Ali@motorola.com","SP#34 stopped. Replaced by UID_350027 and its children",23.402000000000001,34,18,"SP-34",null,"2006-06-23","2009-03-24"]
[7022,350023,"   Deleted - SA aspects of System Architecture Evolution","SAES-SA",2,"Rel-8","S2","2006-04-12","2007-10-01",1,"-","-","-","-","SP#34 stopped","-",35,18,"SP-34",null,"2007-03-29","2009-03-24"]
[7025,380039,"   Stage 1 for ICS Requirement and Architecture","ICSRA",2,"Rel-8","S1","2007-09-03","2008-03-12",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","SP#39 completed",22.100999999999999,38,21,null,null,"2007-10-02","2008-07-23"]
[7029,521014,"      (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2014-12-09",1,"CP-091046","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[7033,400006,"      CT3 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-091046","-","Mavenir","Brett Wallis ( brett@mavenir.com)","CP#43 completed","new 29.292",40,21,null,null,"2008-03-03","2009-12-07"]
[7036,400105,"      Deleted - Stage 3 for ICSRA – I1 interface","ICSRA",3,"Rel-8","C1","2008-05-30","2008-09-12",1,"CP-080492","-","Huawei","xupeili@huawei.com","CP#41 work stopped",24.292999999999999,40,21,"CP-41","PCG-21","2008-03-03","2009-12-02"]
[7040,380001,"      Documentation of TISPAN R1 and R2 in CT1","REDOC_TIS-C1",3,"Rel-8","C1","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","24.141; 24.147; 24.173; 24.229; 24.247; 24.341; 24.604; 24.605; 24.606; 24.607; 24.608; 24.610; 24.611; 24.616; 24.623; 24.628; 24.629; 24.647; 24.654",38,21,null,null,"2007-11-28","2008-08-01"]
[7042,380003,"      Documentation of TISPAN R1 and R2 in CT4","REDOC_TIS-C4",3,"Rel-8","C4","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","29.228; 29.229",38,21,null,null,"2007-11-28","2008-09-01"]
[7045,380041,"      Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging","MMTel-CH",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-080848","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","CP#43 completed","32.275; 32.298/299",38,21,null,null,"2005-06-17","2009-02-23"]
[{"$f":"A7048+1","v":7048},380008,"      CT3 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C3","2007-05-02","2008-12-05",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#42 completed",29.163,38,21,null,null,"2007-11-14","2012-01-11"]
[7051,390059,"      Stage 1 FA","FA",3,"Rel-8","S1","2008-01-30","2008-06-05",1,"-","-","Telecom Italia","-","SP#40 completed ",22.172999999999998,39,21,null,null,"2008-03-03","2008-09-18"]
[7056,380011,"      CT3 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C3","2007-11-30","2008-12-04",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#42 completed",29.163,38,21,null,null,"2007-11-14","2008-11-21"]
[7059,380042,"      Advice of Charge (AoC) support in IMS Charging","CH8_IMS",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070739","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240; 32.260; 32.296; 32.298; 32.299; new 32.280",38,21,null,null,"2005-06-17","2009-02-23"]
[7062,390051,"   Stage 2 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","23.002; 23.141; 23.203; 23.167; 23.228",39,21,null,null,"2008-03-03","2015-03-24"]
[7064,390113,"   Stage 3 CIMS_3GPP2","REDOC_3GPP2",2,"Rel-8","C1,C3,C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","-","-",39,21,null,null,"2008-03-03","2008-12-04"]
[7070,350009,"      Architecture aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","S2","2007-02-05","2007-12-06",1,"SP-070105","-","Cablelabs","Bernie McKibben (b.mckibben@cablelabs.com)","SP#38 completed",23.228000000000002,35,18,null,null,"2007-03-29","2008-05-27"]
[7071,350010,"      CT1 aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070122","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed","-",35,18,null,null,"2007-03-29","2008-05-13"]
[7077,350006,"      CT1 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-05-27"]
[7078,380029,"      CT3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C3","2007-03-26","2007-11-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#38 completed",29.163,38,21,null,null,"2007-03-29","2008-03-07"]
[7082,360014,"   SA2 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S2","2007-06-22","2008-09-18",1,"SP-080095","-","Orange","Delphin Barankanira","no Stage 2 impacts",23.228000000000002,36,19,null,null,"2007-06-22","2010-07-29"]
[7085,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228; 29.229; 23.003; 23.008; 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[7090,380044,"   Maintenance of TISPAN release 2 common IMS","IMS_Comm_Mtce8",2,"Rel-8","S2","2007-07-02","2007-12-06",1,"SP-070916","-","Telecom Italia","antonio.ascolese@telecomitalia.it","SP#38 completed","23.506; 23.507.23.517; 23.521",38,21,null,null,"2007-10-02","2010-07-29"]
[7093,390057,"   Stage 2 IMS Service Continuity","IMS-Cont",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080092","-","LG Electronics","JaeSeung SONG (anthonys@lge.com)","SP#40 completed","23.237; 23.292",39,21,null,null,"2007-10-02","2008-05-27"]
[7096,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203; 33.141; 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[7099,380012,"   CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication","NBA",2,"Rel-8","C1","2007-11-14","2009-03-06",1,"CP-070781","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed",24.228999999999999,39,21,null,null,"2007-11-19","2009-02-20"]
[7101,34046,"IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",1,"Rel-8","S4,S3,IETF","2008-03-12","2011-09-21",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#39 WID approved","-",34,18,null,null,"2008-03-18","2011-06-30"]
[7104,713024,"Multimedia interworking between IMS and CS networks","MIW-IMS",1,"Rel-8","C3,C4","2005-09-23","2008-12-05",1,"CP-070729","-","Vodafone","nico.gabriele@vodafone.com","CP#42 completed","-",71,36,null,null,"2005-10-03","2008-12-10"]
[7108,380022,"   Mn interface (MGCF – IM MGW)","MIW-IMS-St3C4",2,"Rel-8","C4","2007-11-21","2008-12-05",1,"CP-070729","-","Vodafone","Christer.Holmberg@ericsson.com","CP#42 completed",29.332000000000001,38,21,null,null,"2007-11-21","2008-11-22"]
[{"$f":"A7112+1","v":7112},521024,"   (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2012-06-15",1,"CP-080794","-","Keith Drage","-","CP#56 completed","RFC 6544 (was draft-ietf-mmusic-ice-tcp)",52,27,null,null,"2011-06-20","2012-04-20"]
[7116,521026,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui)","RFC 7433",52,27,null,null,"2011-06-20","2015-03-10"]
[7119,380018,"Support of Overlap signalling","Overlap",1,"Rel-8","C3,C1,C4","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed","-",38,21,null,null,"2007-11-13","2009-02-20"]
[7122,380120,"   Stage 3 Overlap (CT4)","Overlap",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#42 completed","29.228; 29.229",38,21,null,null,"2007-11-13","2008-11-22"]
[7125,380235,"   AS/MRFC Stage 3","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed","24.229; 24.147; 24.247",38,21,null,null,"2007-11-14","2012-01-10"]
[7127,400012,"IMS Restoration Procedures","IMS_RP",1,"Rel-8","C4,C1","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 ","-",40,21,null,null,"2007-03-29","2010-07-30"]
[7131,340030,"I-WLAN Network Selection Principle (NSP)","IWLANNSP",1,"Rel-8","S1,C1,C6","2007-06-14","2009-03-06",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","CP#43 completed","-",34,18,null,null,"2005-11-04","2009-02-25"]
[7134,390125,"   CT6 part of Stage 3 for I-WLAN NSP","IWLANNSP",2,"Rel-8","C6","2008-03-07","2008-12-11",1,"CP-080217","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","CP#42 completed","31.102; 31.111",39,21,null,null,"2008-03-07","2009-02-25"]
[7138,460006,"Conformance Test Aspects – Mobility between 3GPP WLAN Interworking and 3GPP Systems","IWLAN_Mob_UEConTest",1,"Rel-8","R5","2009-12-04","2010-09-17",1,"RP-091349","RP-100740","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","RP#49 completed. Testing for Rel-8 UID_400013 CT1 aspects of mobility between 3GPP WLAN Interworking and 3GPP Systems (24.327)","34.108; 34.123-1; 34.123-2; 34.123-3",46,24,null,null,"2009-11-30","2010-09-09"]
[7142,320019,"   CT1 aspects of EVA","EVA",2,"Rel-8","C1","2006-06-02","2009-09-18",1,"CP-060260","-","Nortel","milanpa@nortel.com","CP#45 completed","43.068; 44.068",32,17,null,null,"2006-06-21","2009-09-09"]
[7145,31081,"Personal Network Management","PNM",1,"Rel-8","S1,C1,S3","2005-07-11","2009-03-06",1,"SP-080327","-","Vodafone","armin.toepfer@vodafone.com","CP#43 completed","-",null,null,null,null,"2005-04-21","2009-03-24"]
[7147,350050,"   Stage 2 for PNM","PNM",2,"Rel-8","C1","2007-03-26","2008-12-05",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#42 completed",23.259,null,null,null,null,"2007-05-04","2008-11-21"]
[7150,350002,"      Deleted - CT4 aspects of Stage 3 PNM","PNM",3,"Rel-8","C4","2007-03-26","2008-12-05",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#42 no impact on CT4 specs","-",null,null,"CP-42",null,"2007-03-29","2010-07-30"]
[7153,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[7156,34042,"eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution","eCall_Phase2",1,"Rel-8","S4","2007-12-06","2009-09-24",1,"SP-070756","-","Airbiquity","lhong@airbiquity.com & rrobinson@airbiquity.com","SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData)","26.267; 26.268; 26.269; 26.967; 26.969",null,null,null,null,"2007-12-09","2010-08-02"]
[7161,7005,"   System enhancements for interconnection interfaces between two IMSs","IMS_NNI",2,"Rel-8","S2,S5,C3","2006-08-16","2009-03-06",1,"SP-080554","-","Telecom Italia","Mario Madella (mario.madella@telecomitalia.it)","CP#43 completed","-",null,null,null,null,"2006-02-16","2010-08-02"]
[7164,330011,"      Charging harmonization for NGN between 3GPP and ATIS-TMOC","FBI2-TISP2-CH",3,"Rel-8","S5","2006-09-28","2006-12-07",1,"SP-060545","-","Amdocs","yishai.brown@amdocs.com ","SP#34 completed",32.296999999999997,null,null,null,null,"2006-10-09","2008-03-03"]
[7168,410002,"   Stage 1 for SIP_Nc (covered by Feature IPinterc)","SIP_Nc",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-070871","-","Telefónica O2","chris.friel@O2.com","22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc)","22.101; 22.228",41,21,null,null,"2007-12-13","2008-03-20"]
[7169,360026,"   SIP-I based circuit-switched core network; Stage 2","SIP_Nc-St2",2,"Rel-8","C4","2007-09-14","2008-12-05",1,"CP-080282","-","Vodafone","David.Hutton@vodafone.com","CP#42 completed","23.231; 23.153; 23.205",null,null,null,null,"2007-09-05","2008-11-22"]
[7175,400015,"   CT1 aspects of ETWS","ETWS",2,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080951","-","NTT DoCoMo","yamashitahi@s1.nttdocomo.co.jp","CP#42 completed",23.041,40,21,null,null,"2007-12-13","2010-08-02"]
[{"$f":"A7176+1","v":7176},410021,"   CT4 aspects of ETWS","ETWS",2,"Rel-8","C4","2008-09-26","2008-12-05",1,"CP-080951","-","NTT DoCoMo","yamashitahi@s1.nttdocomo.co.jp","CP#42 completed",29.167999999999999,40,21,null,null,"2007-12-13","2010-08-02"]
[7182,330006,"Local Charging Zone Requirements","LCZR",1,"Rel-8","S1","2006-09-28","2008-03-12",1,"SP-060482","-","China Mobile","liuhongyfw@chinamobile.com","SP#39 Stage 1 completed",22.114999999999998,null,null,null,null,"2006-10-06","2008-03-25"]
[7184,370028,"   Stage 1 for CAT","CAT",2,"Rel-8","S1","2006-12-06","2007-09-20",1,"SP-070122","-","China Mobile","fenglingjuan@chinamobile.com","-",22.181999999999999,37,null,null,null,"2007-10-02","2008-09-10"]
[7187,390114,"      IMS CAT SS","CAT-SS",3,"Rel-8","C1","2008-04-21","2008-12-04",1,"CP-080496","-","Nortel","milanpa@nortel.com","CP#42 completed",24.181999999999999,39,21,null,null,"2008-03-03","2008-11-21"]
[7190,410110,"      CT4 part of CAT Service in 3GPP CS domain","CAT-3G_CS",3,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","CP#43 completed. Triggered by Study UID_360031 (TR 29.882) ","23.205; 23.231; 29.002",41,21,null,null,"2008-09-11","2012-01-11"]
[7195,400016,"   CT3 part of Stage 3 for MESSIW","MESSIW",2,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-080773","-","Huawei","xupeili@huawei.com","CP#43 completed",29.311,40,21,null,null,"2006-07-19","2009-02-19"]
[7198,320023,"   Service Requirements for PRIOR","PRIOR_EMR",2,"Rel-8","S1","2006-06-08","2007-12-06",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","SP#38 completed","New 22.153",32,null,null,null,"2003-03-28","2008-06-03"]
[7199,340012,"   CT1 part of Stage 3 for PRIOR","PRIOR_EMR",2,"Rel-8","C1","2006-12-01","2009-09-18",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#45 completed",24.228999999999999,34,null,null,null,"2006-12-18","2009-09-09"]
[7204,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[7206,370012,"      Deleted - Ensure Parlay-X composable with identity management frameworks, in particular Liberty Alliance","-",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Ericsson","catherine.mulligan@ericsson.com","CP#40: Work moved to OMA","existing 29.199-xy",37,21,"CP-40","PCG-21","2007-09-13","2009-03-24"]
[7210,370016,"      Deleted - Identify communication format used by a particular application","-",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Ericsson","catherine.mulligan@ericsson.com","CP#40: Work moved to OMA","existing 29.199-xy",37,21,"CP-40","PCG-21","2007-09-13","2009-03-24"]
[7213,380049,"      Deleted - Topology Hiding (22.127 CR 0086 S1-071838)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7217,380053,"      Deleted - API usage accounting (22.127 CR 0090 S1-071792)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7221,390068,"      Mobility Emergency Location","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-06",39,21,null,null,"2008-03-26","2009-01-19"]
[7224,360032,"Paging Permission with Access Control (PPACR)","PPACR",1,"Rel-8","S1,C1","2007-06-12","2008-12-05",1,"SP-070501","-","NTT DoCoMo","Morita Takashi","CP#42 completed. Triggered by Study UID_330016 (PPAC).","-",null,null,null,null,"2007-10-16","2008-12-10"]
[7226,380017,"   Stage 3 for PPACR (CT1)","PPACR-CT1",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070783","-","NTT DoCoMo","-","CP#42 completed","24.008; 23.122; 24.301",38,21,null,null,"2007-11-14","2008-11-21"]
[7229,380070,"   Stage 1 for CHRGMPH","CHRGMPH-s1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-03-20"]
[7232,420019,"   Support of Closed Subscriber Group (CSG)","-",2,"Rel-8","C4","2008-12-05","2009-03-06",1,"-","-","CT#42","Hannu Hietalahti","CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG","29.002; 29.272; 23.008; 23.003",42,22,null,null,"2008-12-04","2009-02-23"]
[7236,400053,"   Support of UTRA HNB","HNB-supp",2,"Rel-8","R2","2008-05-30","2009-03-06",1,"RP-080752","RP-090040","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#43 completed","25.304; 25.306; 25.331; new 25.367",40,21,null,null,"2008-06-03","2009-02-27"]
[7239,420037,"   3G Home NodeB OAM&P Type 1 Management Interface","HNB-3G_OAM",2,"Rel-8","S5","2008-12-11","2009-06-04",1,"SP-080708","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Complements work in BroadBand Forum","new (32.581; 32.582; 32.583; 32.584)",42,22,null,null,"2008-12-03","2009-05-18"]
[7243,390046,"Generic Bootstrapping Architecture Push Function","GBAPush",1,"Rel-8","S3,C1,C4","2008-03-12","2009-03-06",1,"SP-080133","-","Ericsson","Rolf Blom","CP#43 completed","-",39,21,null,null,"2008-03-22","2009-02-20"]
[7247,34045,"Requirements and Test methods for Wideband Terminals","RETEM_WB_T",1,"Rel-8","S4","2008-03-12","2008-12-11",1,"SP-080004","-","FT, Ericsson","stephane.ragot@orange-ftgroup.com, wanqing.shi@sonyericsson.com","SP#42 completed. SP#39 WID approved. ","26.131; 26.132",null,null,null,null,"2008-03-18","2008-11-21"]
[7248,34043,"Extending PSS and MBMS User Services for optimized Mobile TV","PSS_MBMS_OMTV",1,"Rel-8","S4","2007-12-06","2008-12-11",1,"SP-070757","-","Ericsson","thorsten.lohmar@ericsson.com","SP#42 completed. SP#38 WID approved. ","26.234; 26.346; 26.946",null,null,null,null,"2007-12-09","2008-11-21"]
[7252,400020,"   CT4 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#43 completed",29.332000000000001,40,21,null,null,"2007-12-09","2009-02-20"]
[7255,340064,"   Rel-8 Network Infrastructure Management","OAM8-NIM",2,"Rel-8","S5","2007-06-07","2009-12-04",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[7258,35056,"      CN CS Bearer Transport Network (BTN) relative NRM","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070300","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#40 completed","32.632; 32.633; 32.635",null,null,null,null,"2005-06-17","2008-04-28"]
[7261,450052,"      Create missing specifications for IRP XML definitions","OAM8-NIM",3,"Rel-8","S5","2009-09-24","2009-12-04",1,"SP-090553","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x)","new (32.125; 32.355; 32.505; 32.535); 32.150; 32.153; 32.335 ",45,23,null,null,"2009-09-11","2009-12-01"]
[7266,360002,"      Key Performance Indicators (KPIs) for UMTS and GSM","OAM8-PM",3,"Rel-8","S5","2007-06-07","2009-03-12",1,"SP-070299","-","China Mobile","Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com)","SP#43 completed",32.409999999999997,null,null,null,null,"2007-05-28","2009-02-23"]
[7270,531003,"      Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event)","OAM8-Trace",3,"Rel-8","C1-IETF","2008-03-07","2011-12-09",1,"CP-080315","-","Peter Dawes","peter.dawes@vodafone.com","CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100","draft-dawes-sipping-debug-event",53,27,null,null,"2011-07-29","2021-04-09"]
[7273,870081,"   (IETF) A Two-Way Active Measurement Protocol (TWAMP) (draft-ietf-ippm-twamp) --> RFC 5357","OAM8",2,"Rel-8","S5-IETF","2008-03-07","2010-09-06",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[7274,350016,"Rel-8 Charging Management small Enhancements","CH8",1,"Rel-8","S5","2006-03-16","2008-12-11",1,"-","-","-","-","CH8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI",30.818000000000001,null,null,null,null,"2006-05-22","2009-03-24"]
[7278,380046,"   Deleted - WLAN Offline Charging","CH8",2,"Rel-8","S5","2008-01-07","2008-12-11",1,"SP-070750","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#42 stopped","32.252; 32.298; 32.299",38,21,"SP-42","PCG-22","2005-06-17","2009-03-24"]
[7281,380026,"   Stage 3 for eMp","eMp",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed",29.332999999999998,38,21,null,null,"2007-11-19","2010-08-02"]
[7287,20068,"Rel-8 LTE – 3G Long Term Evolution - Evolved Packet System RAN part","LTE",1,"Rel-8","RP,S5","2006-09-25","2009-03-12",1,"RP-080747","RP-080741","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","RP#43 completed. Role model for SAE/LTE system wide project management by SA2 in SP-060166","LTE 36.300; 36.938",null,null,null,null,"2006-06-21","2009-12-18"]
[7289,330019,"   LTE – Radio Interface Layer 2 and 3 Protocol Aspect","LTE-L23",2,"Rel-8","R2","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Nokia Siemens Networks","benoist.sebire@nokia.com","RP#42 completed","36.302; 36.304; 36.306; 36.314; 36.321; 36.322; 36.323; 36.331; 25.302; 25.304; 25.331",null,null,null,null,"2006-03-21","2009-12-18"]
[7292,370046,"   LTE – FDD repeaters","LTE-Repeaters",2,"Rel-8","R4","2007-09-14","2009-03-06",1,"RP-070749","RP-090037","Powerwave Technologies, Andrew Wireless","ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com","RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report)","36.106; 36.143; 25.113",37,null,null,null,"2007-10-01","2010-03-16"]
[7296,390002,"      Performance measurements for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080062","-","Motorola, Huawei","Yizhi Yao (yzyao@motorola.com)","SP#43 completed","new 32.425",39,21,null,null,"2005-06-17","2010-07-29"]
[7300,390005,"      Self-Establishment of eNBs, including automated Software Management","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080849","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#42 completed","new (32.501; 32.502; 32.503; 32.531; 32.532; 32.533)",39,21,null,null,"2005-06-17","2010-03-22"]
[7303,25041,"   3G LTE – Terminal Protocol Conformance Test Specifications","LTE-UEConTest_SIG",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080647","RP-091060","NEC, Motorola","david.lecompte@nectech.fr, Jacob.John@motorola.com","RP#46 completed","36.521-1; 36.521-2; 36.508; 36.509; 36.523-1; 36.523-2; 36.523-3",null,null,null,null,"2006-03-21","2009-11-27"]
[{"$f":"A7304+1","v":7304},25042,"   LTE – Terminal Radio Transmission and Reception Conformance Test Specifications","LTE-UEConTest_RF",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080601","RP-091059","Agilent","andrea_leonardi@agilent.com","RP#46 completed. RP#50 TR 36.903 v100 for Approval","36.521-1; 36.521-2; 36.521-3; new 36.903",null,null,null,null,"2009-06-02","2010-12-10"]
[7309,380074,"   UMTS 2300 MHz TDD LCR","RInImp8-UMTS2300TDD",2,"Rel-8","R4","2007-12-17","2008-09-12",1,"RP-071016","RP-080517","CATT","Yuexia Song (songyuexia@catt.cn)","RP#41 completed. RP#47 abandoned draft 25.828","25.102; 25.105; 25.113; 25.123; 25.142; 34.124; 25.306; 25.331; 34.122",38,21,null,null,"2007-12-17","2010-08-02"]
[7312,370033,"   Performance requirements for 15 code reception with 16QAM/QPSK (FDD)","RInImp8-Hsdpa15codes",2,"Rel-8","R4","2007-06-11","2008-03-07",1,"RP-070745","RP-080043","Vodafone","tim.frost@vodafone.com","RP#39 completed",25.100999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[7315,25050,"   Conformance Test Aspects – CS Voice Service over HSPA","RInImp8-CsHspa_UEConTest",2,"Rel-8","R5","2007-06-01","2008-09-12",1,"RP-080160","RP-080542","Huawei","baoyi@huawei.com","RP#41 completed","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2008-03-11","2008-09-09"]
[7318,360013,"   Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-64QamMimoHsdpa",2,"Rel-8","R1","2007-06-04","2008-09-12",1,"RP-070500","RP-080518","Ericsson","Johan.Bergman@ericsson.com","RP#41 completed","25.308; 25.211; 25.212; 25.213; 25.306; 25.331; 25.433; 25.435; 25.423; 25.425; 25.101; 25.104; 25.141",null,null,null,null,"2007-06-21","2010-08-03"]
[7322,370039,"   Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure","RANimp-SrnsReloc",2,"Rel-8","R3","2007-09-14","2008-09-12",1,"RP-070759","RP-080521","Nokia Siemens Networks","masatoshi.nakamata@nsn.com","RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution","25.306; 25.308; 25.321; 25.331; 25.423; 25.433; 25.214; 25.133",37,null,null,null,"2007-10-01","2010-08-03"]
[7326,390028,"   Continuous Connectivity for packet data users for 1.28 Mcps TDD","RANimp-LCRCPC",2,"Rel-8","R1","2008-03-07","2009-05-29",1,"RP-080085","RP-090394","TD Tech","chenying@td-tech.com","RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.929; 25.308; 25.319",39,21,null,null,"2008-03-17","2010-08-03"]
[7329,400050,"   MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","RANimp-MIMOLCR",2,"Rel-8","R1,R4","2008-01-24","2009-05-29",1,"RP-080485","RP-090313","CATT","wangke@datangmobile.cn","RP#43 completed","25.201; 25.221; 25.222; 25.223; 25.224; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433; 25.102; 25.105; 25.142",40,21,null,null,"2008-03-17","2010-08-03"]
[7331,25126,"Rel-8 RAN improvements - UE Conformance Testing","-",1,"Rel-8","R5","2008-05-30","2010-09-17",1,"-","-","-","-","Linked to Feature UID_20029 (RANimp) ","-",null,null,null,null,"2006-09-22","2008-06-01"]
[7334,440010,"   Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates","RANimp-UEConTest_ImprovedL2LCRTDD",2,"Rel-8","R5","2009-05-29","2010-09-17",1,"RP-090491","RP-100737","CATT","Xiaozhong Chen (chenxiaozhong@datangmobile.cn)","RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink","34.108; 34.123-1; 34.123-2; 34.123-3",44,23,null,null,"2009-05-20","2010-09-09"]
[7338,430028,"   Conformance Test Aspects – Receiver Type3i","RANimp-UEConTest_ReceiverType3i",2,"Rel-8","R5","2009-03-06","2009-12-04",1,"RP-090010","RP-091066","Qualcomm","Ashok Kumar Narayanaswamy (anarayan@qualcomm.com)","RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD","34.108; 34.121-1; 34.121-2",43,22,null,null,"2009-03-10","2010-08-03"]
[7341,450025,"   Conformance Test Aspects – MIMO for 1.28 Mcps TDD","RANimp-UEConTest_MIMOLCRTDD",2,"Rel-8","R5","2009-09-18","2010-06-04",1,"RP-100120","RP-100660","ZTE","huang.chun2@zte.com.cn","PR#48 completed. Testing for UID_400050","34.108; 34.122; 34.123-1; 34.123-2; 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[7344,440008,"Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast","MBSFN_IMB_UEConTest",1,"Rel-8","R5","2009-05-30","2010-03-19",1,"RP-090583","RP-100070","IPwireless","Phil Young (pyoung@ipwireless.com)","RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008","34.108; 34.122; 34.123-1; 34.123-2; 34.123-3",44,23,null,null,"2009-05-21","2010-03-16"]
[7349,54583,"   Testing for GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G3new","2006-09-08","2011-11-25",1,"GP-061757","-","Renesas Mobile","deepa.kamath@renesasmobile.com","GP#52 completed",51.01,null,null,null,null,"2006-09-13","2011-11-25"]
[7352,50588,"   Update to GAN specifications","GANENH-SPEC",2,"Rel-8","GP","2007-08-31","2008-02-22",1,"GP-071560","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed","43.318; 44.318",null,null,null,null,"2007-09-06","2008-05-19"]
[7353,53089,"   Update TS 51.010 Mobile Station (MS) Conformance Specification for GAN Enhancements","GANENH-MStest",2,"Rel-8","G3new","2007-05-15","2009-09-04",1,"GP-071563","-","T-Mobile","mohammed.versi@t-mobile.com","GP#43 completed",51.01,null,null,null,null,"2007-09-06","2009-09-07"]
[7357,400024,"   Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",2,"Rel-8","C4,C1,C3","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722","-",40,21,null,null,"2007-09-19","2012-01-11"]
[7360,400224,"      CT3 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C3","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722",29.007000000000001,40,21,null,null,"2007-09-19","2012-01-11"]
[7364,38101,"   GERAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS","ANSS",2,"Rel-8","G2","2008-05-16","2008-11-21",1,"GP-081784","-","Qualcomm","Mungal Dhanda","GP#40 completed","43.059; 44.031; 49.031; 44.071; 48.031; 51.010",null,null,null,null,"2008-05-19","2008-12-03"]
[7366,51149,"Conformance testing for the Latency Reductions feature","CTLATRED",1,"Rel-8","G1,G3new","2008-02-22","2010-03-05",1,"GP-080367","-","Ericsson","mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com","GP#45 completed","-",null,21,null,null,"2008-02-26","2010-03-05"]
[7371,521029,"(IETF) (Small) Technical Enhancements and Improvements for Rel-8","TEI8_IETF",1,"Rel-8","C1-IETF","2007-01-01","2012-09-07",1,"-","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#57 completed","RFC 6714 (was draft-ietf-simple-msrp-cema)",52,27,null,null,"2011-06-20","2012-09-03"]
[7375,340032,"Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN","LCS4_IWLAN",1,"Rel-8","S2","2007-09-28","2007-09-28",1,"SP-060818","-","LG Electronics","dhshim@lge.com","SP#35 stopped","23.234; 23.271; 23.167",34,null,"SP-35",null,"2006-03-22","2009-03-24"]
[7379,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[7380,400123,"   Deleted - Contact Manager for 3GPP UICC applications test specifications","eUPHBOOK-Test",2,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion","Udo Willenbrink (uwillenbrink@comprion.com )","CP#47 work stopped/abandoned","31.320 (external interface for communication with the ME)",40,21,"CP-47","PCG-24","2008-11-24","2010-09-06"]
[7383,0,"Release 8 Studies","-",1,"Rel-8","CP,GP,RP,SP","2005-10-07","2005-10-07",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[7386,31089,"Study on Network Composition","FS_NetComp",1,"Rel-8","S1","2005-12-07","2007-12-12",1,"SP-060478","-","Nokia Siemens Networks","joerg.swetina@neclab.eu","SP#38 completed",22.98,null,null,null,null,"2005-12-12","2008-03-24"]
[7392,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[7394,32085,"Study on 3GPP System Architecture Evolution","FS_SAE",1,"Rel-8","S2,S3","2004-12-03","2009-03-12",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#43 completed","-",null,null,null,null,"2005-01-31","2009-02-20"]
[7397,7024,"   Security study for Inter-access mobility between non-3GPP and 3GPP system","FS_SAE",2,"Rel-8","S3","2007-09-03","2009-03-12",1,"SP-070163","-","Nokia","dajiang.zhang@nokia.com","SP#43 completed","33.821; 33.822",null,null,null,null,"2006-02-21","2009-02-20"]
[7401,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[7405,380085,"Study on Home (e)NodeB Security","FS_HNB_Sec",1,"Rel-8","S3","2007-12-20","2009-03-12",1,"SP-070783","-","Huawei","yangyanmei@huawei.com","SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007)",33.82,38,21,null,null,"2007-12-20","2009-03-11"]
[7406,360015,"Study on Transferring of emergency call data – in-band modem solution","eCALLIBMS",1,"Rel-8","S4","2006-12-07","2007-12-12",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2)",26.966999999999999,null,null,null,null,"2006-12-10","2008-05-16"]
[7409,320006,"Study on Common Profile Storage (CPS) Framework of User Data for network services and management","OAM7-CPS",1,"Rel-8","S5","2006-07-03","2007-06-07",1,"SP-060263","-","T-Mobile","istvan.aba@t-mobile.at","SP#36 completed. Spin-off New Feature UID_400034 User Data Convergence (UDC)",32.808,null,null,null,null,"2006-05-22","2008-03-17"]
[7414,360030,"Study on IMS Application Server Service Data Descriptions for AS interoperability","FS_IMS_ASIO",1,"Rel-8","C4","2007-09-14","2008-09-12",1,"CP-070685","-","Alcatel-Lucent","Jean-Jacques Trottin","CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO)",29.864000000000001,null,null,null,null,"2007-09-05","2008-09-11"]
[7417,370041,"Study on Scope of future HSPA Evolution for 1.28 Mcps TDD","FS_RAN-LCRTDDHSPAEvo",1,"Rel-8","R1","2007-09-14","2008-05-30",1,"RP-070748","RP-080290","RITT","Xu Fei","RP#40 completed",25.824000000000002,37,null,null,null,"2007-06-21","2008-06-12"]
[7420,350039,"Study on 3G Home NodeB/eNodeB","FS_RAN-HNBeNB",1,"Rel-8","R4","2007-03-05","2008-05-30",1,"RP-070257","RP-080289","Motorola","howard.thomas@motorola.com","RP#40 completed",25.82,null,null,null,null,"2007-03-29","2008-06-26"]
[7424,350017,"Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems","FS_SM3GWLAN",1,"Rel-8","S2","2007-03-20","2008-09-18",1,"SP-070106","-","Orange","-","SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327.","withdrawn 23.827",null,null,"SP-41","PCG-21","2007-03-29","2008-09-17"]
[7427,380080,"Deleted - Study on HS-PDSCH serving cell change enhancements","FS_RAN-HSPDSCH",1,"Rel-8","R4","2007-12-17","2008-03-07",1,"RP-071044","RP-080070","Qualcomm","-","RP#39 stopped (no TR produced). Spin-off HS-DSCH Serving Cell Change Enhancements (UID_39003)","none",38,21,"RP-39","PCG-21","2007-12-17","2008-06-26"]
[7431,32106,"   TR on ServID","ServID",2,"Rel-7","S2","2005-05-02","2006-03-21",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-",23.815999999999999,null,null,null,null,"2005-07-01","2008-07-01"]
[{"$f":"A7432+1","v":7432},32107,"   Stage 1,2 of ServID","ServID",2,"Rel-7","S1,S2","2005-11-11","2006-05-31",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-","22.228; 23.228; 23.203",null,null,null,null,"2005-07-01","2008-07-01"]
[7436,7009,"   Deleted - TR on GRUU","GRUU",2,"Rel-7","S2","2005-11-14","2006-09-14",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","Abandoned","-",null,null,"SP-32",null,"2006-02-16","2008-07-01"]
[7439,7038,"Multimedia Telephony Service for IMS","MTSI",1,"Rel-7","S1,C1,S4","2006-02-01","2017-03-15",1,"SP-060224","-","Ericsson","peter.bleckert@ericsson.com","-","-",69,35,null,null,"2006-03-02","2008-06-25"]
[7443,690069,"   UE Conformance Test Aspects - Multimedia Telephony Services for IMS (MTSI) over fixed access","MTSI_FIXED_ACCESS-UEConTest",2,"Rel-7","R5","2015-09-15","2017-03-15",1,"RP-151257",null,"Telecom Italia",null,"tested: REL-7 SA/CT WI MTSI;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15%1/7/16: Compl:15%->30% ¦21/",null,69,35,null,null,"2015-09-29","2017-03-21"]
[7446,350147,"Multimedia Telephony Service for IMS (MTSI) - UE Conformance Testing","MTSI-UEConTest",1,"Rel-7","R5","2007-09-19","2009-03-12",1,"RP-080605","RP-090056","Ericsson, Motorola","Leif.Mattisson@ericsson.com, Jacob.John@motorola.com","RP#43 completed. Linked UID_7038 (MTSI)","34.123-1; 34.123-2; 34.123-3; 34.229-1; 34.229-2",null,null,null,null,"2006-03-21","2009-02-24"]
[7449,387002,"   SA1 aspects of MCIMSTR1","MCIMSTR1-S1",2,"Rel-7","S1","2007-09-18","2007-12-06",1,"SP-070915","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","-","22.173; 22.273",38,21,null,null,"2008-01-10","2008-11-04"]
[7454,1314,"   Service Requirements for IP-based emergency calls","EMC1",2,"Rel-7","S1","2000-09-18","2004-06-25",1,"SP-050604","-","Siemens","Rainer Liebhart","-",22.100999999999999,null,null,null,null,"2000-04-19","2004-06-08"]
[7457,32100,"   Stage 2 Specification Phase - IMS-level","EMC1",2,"Rel-7","S2","2005-09-05","2006-06-09",1,"SP-050604","-","Siemens","Rainer Liebhart","-","23.060; 23.167; 23.203; 23.221; 23.228; 23.234; 23.271; 23.406",null,null,null,null,"2004-10-14","2006-09-19"]
[7458,32101,"   Deleted - Stage 2 Specification Phase - GPRS-level","EMC1",2,"Rel-7","S2","2007-03-02","2007-03-02",1,"SP-050604","-","Siemens","Rainer Liebhart","-","-",null,null,"SP-32",null,"2004-10-14","2007-06-22"]
[7462,13028,"      Deleted - CT3 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C3","2006-05-08","2006-09-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","Cancelled for Rel-7 and there is no corresponding Rel-8 WI",29.163,null,null,"CP-33",null,"2000-04-19","2008-07-01"]
[7465,14026,"      CT4 PS domain aspects to support IMS Emergency sessions","EMC1-GPRSc4",3,"Rel-7","C4","2006-01-09","2007-06-01",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-",29.06,null,null,null,null,"2000-08-08","2007-05-29"]
[7469,31057,"   Stage 1 on Session Continuity","WLAN2",2,"Rel-7","S1","2004-01-05","2004-06-11",1,"-","-","-","-","Acronym changed from \"WLAN2, WLAN-SC\"",22.234000000000002,null,null,null,null,"2004-06-17","2015-03-24"]
[7471,32110,"WLAN Interworking – Private Network access from WLAN 3GPP IP Access","WLANPNA",1,"Rel-7","S2,C1,C3,C4","2005-10-10","2006-09-26",1,"SP-050489","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2003-03-28","2005-10-07"]
[7477,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[7480,14028,"   Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking","WLANQOS",2,"Rel-7","C4","2006-09-22","2007-03-09",1,"CP-060418","-","Huawei","zhang.peng@huawei.com","CP#33 approved WID","29.234; 23.008",null,null,null,null,"2006-10-11","2008-07-18"]
[7484,50558,"   LCS Enhancements related to Location-Based Services","LCS3-LBS",2,"Rel-7","GP","2005-01-03","2007-08-31",1,"GP-050265","-","SiRF","kjudge@sirf.com","-","43.059; 44.031; 48.008; 49.031",null,null,null,null,"2005-02-01","2008-07-02"]
[7485,14025,"   CT4 aspects for LCS UEPos-LBS","LCS3-UEPos-LBS",2,"Rel-7","C4","2006-01-02","2006-12-01",1,"CP-050240","-","SiRF","brodilitz@sirf.com","-","24.030; 24.080; 29.002",null,null,null,null,"2005-06-20","2008-07-02"]
[7488,31052,"   LCS for 3GPP Interworking WLAN","LCS3-IWLAN",2,"Rel-7","S1,S2","2004-06-28","2007-03-02",1,"SP-060291","-","Telcordia","Mike Loushine","-","-",null,null,null,null,"2004-08-30","2010-08-31"]
[7492,20030,"   Deleted - UE positioning Rel-7","LCS3-UEpos",2,"Rel-7","RP","2004-09-15","2007-12-17",1,"-","-","-","-","-","-",null,null,"RP-38",null,"2005-01-04","2008-06-25"]
[7497,350022,"   MBMS Low Chip Rate TDD Physical Layer Enhancement","MBMSE-RANPhysLCRTDD",2,"Rel-7","R1","2007-03-16","2007-09-10",1,"RP-070253","RP-070292","RITT","Lin Hui","-","25.346; 25.221; 25.222; 25.223; 25.224; 25.306; 25.331; 25.402; 25.433; 25.102; 25.105; 25.123",null,null,null,null,"2007-04-02","2008-06-25"]
[7499,400058,"MBMS - UE Conformance Testing","MBMSE_UEConTest",1,"Rel-7","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Linked to Rel-7 Feature UID_31084 (MBMSE)","-",40,21,null,null,"2008-03-11","2009-04-01"]
[7503,34038,"MBMS User Service Extensions","MBMSUSE",1,"Rel-7","S4","2005-12-07","2007-06-07",1,"SP-050838","-","Ericsson","Thorsten.Lohmar@ericsson.com","-","26.346; 26.946",null,null,null,null,"2005-12-13","2007-05-29"]
[7506,50548,"   Towards AGNSS Concept","AGNSS-GP",2,"Rel-7","GP","2004-06-28","2007-08-31",1,"GP-042677","-","Alcatel","richard.couty@space.alcatel.fr","GP#36 completed","43.030; 43.059; 44.031; 44.035; 44.071; 48.008; 48.018; 48.031; 49.031",null,null,null,null,"2004-08-30","2012-05-21"]
[7510,31060,"   Stage 1 for USSD message delivery and transfer to USIM","USSD-USIM",2,"Rel-7","S1","2004-03-18","2004-10-15",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-",22.09,null,null,null,null,"2004-06-08","2008-09-10"]
[7511,43008,"   Alignment with requirements regarding USSD usage","USSD-USIM",2,"Rel-7","C6","2004-03-05","2005-08-12",1,"TP-040069","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","31.111; 31.115; 31.130",null,null,null,null,"2004-09-02","2011-09-01"]
[7514,32084,"   Stage 2 for CSICS","CSICS",2,"Rel-7","S2","2005-01-17","2005-07-15",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-",23.279,null,null,null,null,"2005-06-07","2008-07-02"]
[7519,14017,"   CAMEL Trunk Originated Trigger Detection Points","CamelR7",2,"Rel-7","C4","2004-12-17","2005-12-05",1,"NP-040550","-","Nortel","David Hutton (dhutton@nortel.com)","-","-",null,null,null,null,"2004-12-17","2008-07-18"]
[7522,11045,"Enhancements of VGCS for public authority officials","EVGCS",1,"Rel-7","S1,C1,C4,G2","2004-08-27","2007-06-15",1,"SP-040304","-","-","-","Moved from Rel-6 UID_50563 Enhancements of VGCS in public networks for communication of public authority officials","43.068; 44.068; 24.008; 29.002",75,38,null,null,"2004-09-03","2006-07-17"]
[7525,11062,"      CT1 aspects of EVGCS","EVGCS",3,"Rel-7","C1","2004-08-27","2007-06-15",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-","43.068; 44.068; 24.008",null,null,null,null,"2005-09-14","2007-09-12"]
[7528,11055,"Improvements of VGCS for parallel use of services","IVGCS",1,"Rel-7","S1","2005-03-15","2007-03-15",1,"SP-070167","-","-","-","Voice Group Call Service","-",null,null,null,null,"2005-03-02","2007-03-26"]
[7533,14023,"      Deleted - CT4 aspects of IVGCS","IVGCS-St3-c4",3,"Rel-7","C4","2007-03-09","2007-03-09",1,"NP-050141","-","T-mobile","-","CT4#33 stage 2 solution is still open. ",29.001999999999999,null,null,"CP-35",null,"2005-09-14","2007-03-29"]
[7536,31072,"      Service Requirements for OSA Service Broker","OSA7",3,"Rel-7","S1","2005-03-15","2005-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-",22.126999999999999,null,null,null,null,"2005-03-22","2006-02-16"]
[7537,43011,"      Stage 2 OSA API Service Brokering","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","AePONA","damian.oneill@aepona.com","-",23.198,null,null,null,null,"2005-03-22","2012-07-26"]
[7541,7019,"      Parlay X Geocoding Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-16; 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[7545,340003,"      Parlay-X Multimedia Multicast Control Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","ETRI","-","-","29.199-20; 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[7548,32088,"   Stage 1 of SDoUE","SDoUE-CR",2,"Rel-7","S1","2005-01-24","2006-12-08",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06",22.010999999999999,null,null,null,null,"2004-08-30","2008-07-17"]
[7551,7041,"Network selection enhancements (NSP)","NSP",1,"Rel-7","S1","2006-03-15","2007-06-15",1,"SP-060220","-","O2","chris.friel@O2.com","-","-",null,null,null,null,"2005-11-04","2006-03-22"]
[7554,25048,"Network selection enhancements (NSP) - UE Conformance Testing","NSP-CR_UEConTest",1,"Rel-7","R5","2007-06-01","2008-12-05",1,"RP-080135","RP-080819","Nokia","jarkko.hellsten@nokia.com","RP#42 completed. Testing for Feature UID_7041 (NSP-CR)","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-03-21","2008-12-09"]
[7559,20009,"   Deleted - Extra ACBOP information in RAN","ACBOP",2,"Rel-7","RP","2004-03-15","2004-03-15",1,"-","-","-","-","-",25.331,null,null,"RP-25",null,"2004-04-14","2004-10-13"]
[{"$f":"A7560+1","v":7560},50117,"   Deleted - Extra ACBOP information in GERAN","ACBOP",2,"Rel-7","GP","2006-09-08","2006-09-08",1,"-","-","-","-","-",44.018000000000001,null,null,"RP-33",null,"2004-04-14","2006-07-20"]
[7563,32075,"      Stage 2 of FBI for TISPAN R1","-",3,"Rel-7","S2","2004-10-14","2006-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2006-05-31"]
[7567,13025,"         CT3 aspects of FBI for TISPAN R1","-",4,"Rel-7","C3","2003-11-05","2006-12-08",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","29.163; 29.209",null,null,null,null,"2004-09-03","2006-10-12"]
[7571,7003,"      Stage 1,2 of FBI for PacketCable","-",3,"Rel-7","S2","2006-02-01","2006-12-15",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","-","22.228; 23.228",null,null,null,null,"2006-02-16","2006-09-19"]
[7574,32081,"Support of SMS over generic 3GPP IP access","SMSIP",1,"Rel-7","S2,C4,C1","2004-10-14","2007-06-14",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID (removed MMS)","-",null,null,null,null,"2004-10-14","2008-07-18"]
[7576,32095,"   Stage 2 for SMSIP","-",2,"Rel-7","S2","2005-06-08","2006-09-15",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID",23.204000000000001,null,null,null,null,"2005-06-07","2008-07-15"]
[7582,32103,"   Stage 2 for PCC","-",2,"Rel-7","S2","2005-07-04","2006-09-15",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.",23.202999999999999,null,null,null,null,"2005-07-01","2008-07-18"]
[7585,13029,"   Gx reference point for Policy and Charging Control","PCC-Gx",2,"Rel-7","C3","2005-12-02","2007-11-30",1,"CP-060434","-","Siemens","Thomas.Belling@nsn.com","-","29.212 (not progressed to Rel-7: 29.210; 29.207; 29.208)",null,null,null,null,"2005-12-13","2008-07-18"]
[7589,32091,"Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC",1,"Rel-7","S2,S1,S5,C1,C4","2004-12-31","2007-06-15",1,"SP-060292","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","WID approved SP#27¦updated SP#28¦updated SP#32","-",null,null,null,null,"2005-06-07","2008-07-21"]
[7590,32104,"   TR for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S2","2004-12-31","2005-12-08",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",23.806000000000001,null,null,null,null,"2005-07-01","2008-07-21"]
[7593,35079,"   SA5 Charging for Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC-CH",2,"Rel-7","S5","2006-03-17","2007-06-14",1,"SP-060292","-","Orange","alain.bibas@orange-ft.com","03/2006 SP#31 WID approved","32.250; 32.260",null,null,null,null,"2006-03-20","2008-07-21"]
[7597,13032,"      Deleted - CT3 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C3","2006-11-02","2006-11-02",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-",29.163,null,null,"CP-33",null,"2005-10-04","2008-07-21"]
[7602,320029,"CSI Terminating Session handling","CSItermS",1,"Rel-7","S2,C1","2006-06-08","2007-06-15",1,"SP-060437","-","Samsung","Osok Song","Triggered by the abandoned Study UID_32117 ","-",null,null,null,null,"2006-07-19","2008-07-17"]
[7605,340011,"   Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling","-",2,"Rel-7","C1","2007-03-09","2007-03-09",1,"CP-060647","-","Samsung","chenho.chin@samsung.com","CP-34 approved WID ","24.229; 24.179; 24.279",34,null,"CP-34",null,"2006-12-18","2008-07-17"]
[7608,33024,"Development of UEA2 and UIA2","AlgUEA2",1,"Rel-7","S3","2004-12-01","2005-12-09",1,"SP-040864","-","TeliaSonera","per.christoffersson@teliasonera.com","WID approved SP#26, Dependant on Funding Availability. ","35.919; 35.215; 35.216; 35.217; 35.218",null,null,null,null,"2005-03-24","2008-07-16"]
[7611,330008,"NDS Authentication Framework Extension for Transport Layer Security","NDSAFTLS",1,"Rel-7","S3","2006-09-28","2006-12-06",1,"SP-060507","-","Nokia","tiina.s.koskinen@nokia.com","TLS profile is moved to Rel-8",33.31,null,null,null,null,"2006-10-06","2008-07-16"]
[7613,732031,"   HTTPS connection between a UICC and a NAF","SEC7-HSUN",2,"Rel-7","S3,C1","2005-09-12","2005-09-12",1,"SP-050573","-","Gemalto","JSeif@axalto.com, mireille.pauliac@gemplus.com","-","33.918; 33.222; 24.109",null,null,null,null,"2005-11-04","2008-07-16"]
[7616,32034,"   SS7 TCAP security Gateway","SEC7-NDS-TCAPsec",2,"Rel-7","S3,C4","2005-09-12","2006-08-14",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-","-",null,null,null,null,"2005-11-04","2008-07-16"]
[7619,711052,"IMS Stage 3 IETF Protocol Alignment","IMSProtoc",1,"Rel-7","C1","2004-12-10","2007-03-14",1,"CP-060101","-","-","-","TR 24.930: Signalling flows for the session setup in the IM CN subsystem based on Session Initiation Protocol (SIP)",24.93,71,36,null,null,"2005-01-05","2007-05-29"]
[{"$f":"A7624+1","v":7624},13022,"DIAMETER on the PDG Wi interface","DIAMWi",1,"Rel-7","C3","2004-09-10","2006-12-08",1,"CP-060432","-","Vodafone","Nico.Gabriele@vodafone.com","-",29.161000000000001,null,null,null,null,"2005-01-18","2008-07-15"]
[7627,14012,"Mp (MRFC - MRFP) interface","Mp",1,"Rel-7","C4,C1","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-","-",null,null,null,null,"2003-01-13","2008-07-15"]
[7631,14021,"   Stage 3 for Mp (MRFC - MRFP) interface","Mp-St3c4",2,"Rel-7","C4","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-",29.332999999999998,null,null,null,null,"2003-01-13","2008-07-15"]
[7633,350003,"Mobile Termination whilst the MS is moving to another MSC","MTmovMS",1,"Rel-7","C4","2007-03-09","2007-05-31",1,"CP-070334","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","-","23.008; 23.012; 23.018; 23.078; 23.079; 29.002",null,null,null,null,"2007-03-29","2007-05-29"]
[7638,34032,"Dynamic and Interactive Multimedia Scenes","DIMS",1,"Rel-7","S4","2005-03-15","2007-06-07",1,"SP-050195","-","Streamezzo","gaelle.martin-cocher@streamezzo.com","-","26.140; 26.142; 26.234; 26.244; 23.346",null,null,null,null,"2005-03-21","2007-05-29"]
[7639,34034,"3G-324M Video Telephony Call Setup Times Improvements","VTCSTI",1,"Rel-7","S4","2005-06-08","2006-09-27",1,"SP-050404","-","Vodafone","edward.hall@vodafone.co.uk","-",26.911000000000001,null,null,null,null,"2005-06-16","2006-11-29"]
[7642,34036,"End-to-End Multimedia Services Performance Metrics","E2EMSPM",1,"Rel-7","S4","2005-09-28","2007-03-15",1,"SP-050433","-","China Mobile","zhangyanyf@chinamobile.com","-",26.943999999999999,null,null,null,null,"2005-10-04","2007-03-08"]
[7646,35044,"      Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050302","-","Motorola","-","-","32.731/2/3/5; 32.631/2/3/5",null,null,null,null,"2005-06-17","2007-03-29"]
[7650,35049,"      Subscription Management (SuM) IRP Solution Sets","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-060739","-","Ericsson ","-","-","32.307/317/607/667/665; 32.101; 32.175",null,null,null,null,"2005-06-17","2007-03-29"]
[7653,35054,"      Deleted - Management of Legacy Equipment","-",3,"Rel-7","S5","2005-09-02","2006-12-15",1,"SP-050312","-","Siemens","-","Request to TSG#35 to STOP the WI","new 32.xxx",null,null,"SP-35",null,"2005-06-17","2007-03-29"]
[7655,35064,"      Backward and Forward Compatibility of IRP systems","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050630","-","Ericsson ","-","-",32.154000000000003,null,null,null,null,"2005-09-16","2007-06-22"]
[7661,35058,"      Enhancement UTRAN performance measurements definition","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050316","-","China Mobile","-","-",32.405000000000001,null,null,null,null,"2005-06-17","2007-06-22"]
[7664,35069,"      Performance measurements definition for IMS","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050631","-","China Mobile","-","-","32.404.32.409.32.437; 32.632/3/4/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[7665,35073,"      HSDPA performance measurements","-",3,"Rel-7","S5","2006-02-13","2007-06-14",1,"SP-060379","-","China Mobile","-","-",32.405000000000001,null,null,null,null,"2005-11-24","2007-06-22"]
[7668,35062,"      Trace record content for UTRAN TDD","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050628","-","Nokia","-","-","32.421; 32.422; 32.423",null,null,null,null,"2005-03-02","2007-03-29"]
[7673,320008,"   Alternate Charged Party (ACP) for IMS","CH7-IMS-ACP",2,"Rel-7","S5","2006-05-22","2007-06-14",1,"SP-060442","-","Lucent","njmazzarella@alcatel-lucent.com","-","32.240; 32.260; 32.298; 32.299",null,null,null,null,"2006-05-22","2007-06-22"]
[7676,21006,"   MIMO - Physical layer","MIMO-Phys",2,"Rel-7","R1","2003-09-12","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037","25.211; 25.212; 25.213; 25.214; 25.215; 25.221",null,null,null,null,"2003-03-27","2008-06-24"]
[7681,25037,"      Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD","MIMO-UEConTest_FDD",3,"Rel-7","R5","2007-03-09","2008-03-07",1,"-","-","Qualcomm","svora@qualcomm.com","-","34.108; 34.109; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-20","2010-06-16"]
[7684,20067,"   UMTS 2.6 GHz 7.68 Mcps TDD","RInImp-UMTS26VHCRTDD",2,"Rel-7","R4","2006-06-15","2006-09-15",1,"RP-060349","RP-060451","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#33 completed","25.102; 25.105; 25.123; 25.113; 25.142; 34.124",null,null,null,null,"2006-06-21","2010-07-27"]
[7687,20027,"   UMTS 900 MHz","RInImp-UMTS900",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040541","RP-050662","Nortel","Yannick Li (yli@nortelnetworks.com)","RP#30 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.331; 25.942; 25.306; 25.307; 34.121",null,null,null,null,"2005-01-04","2010-07-27"]
[7690,20045,"   Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2)","RInImp-HSPerf-Type3",2,"Rel-7","R4","2005-03-15","2005-03-15",1,"RP-050362","RP-060015","Cingular","Marc Grant","RP#27 completed",25.100999999999999,null,null,null,null,"2005-06-20","2010-07-27"]
[7694,7029,"      Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-EDCH",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060184","RP-060679","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[7695,20049,"   Deleted Improved support of gaming over HSDPA/EDCH","RInImp-Gaming",2,"Rel-7","R2","2005-12-15","2006-12-15",1,"-","RP-060680","Cingular","Don Zelmer (dz1069@att.com)","RP#34 stopped. SR in RP-060680","-",null,null,"RP-34",null,"2005-12-15","2010-07-27"]
[7699,25008,"   UE Conformance Test for UMTS 900 MHz (band VIII)","RInImp-UMTS900_Test",2,"Rel-7","R5","2005-11-11","2006-06-02",1,"-","-","Qualcomm","hanye@qualcomm.com","RP#32 completed","34.108; 34.121",null,null,null,null,"2002-02-28","2006-03-21"]
[7702,25015,"   UE conformance testing for FDD Inter-Band Operation","RInImp-InterBand_Test",2,"Rel-7","R5","2006-06-02","2006-12-01",1,"-","-","NEC, Motorola","Jacob.John@motorola.com","RP#34 completed","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-03-21","2006-12-01"]
[7707,20026,"   Optimization of channelisation code utilisation for 1.28 Mcps TDD","RANimp-RABSE-CodOptLCRTDD",2,"Rel-7","R1","2004-12-15","2006-12-15",1,"RP-040552","RP-060682","UTStarcom","Ka Leong Lo (kaleong.lo@UTSTAR.COM)","RP#34 completed","-",null,null,null,null,"2005-01-04","2010-07-27"]
[7710,20033,"   UE Performance Requirements for MBMS (TDD)","MBMS-RAN-RF-TDD",2,"Rel-7","R4","2005-03-15","2006-06-15",1,"RP-050156","RP-060477","IPwireless","shwong@ipwireless.com","RP#32 completed","25.102; 25.123",null,null,null,null,"2005-03-15","2010-07-27"]
[7713,7031,"   7.68 Mcps TDD Enhanced Uplink","RANimp-VHCRTDD-EDCH",2,"Rel-7","R1","2006-03-15","2006-12-15",1,"RP-060119","RP-060684","IPwireless","nanderson@ipwireless.com","RP#34 completed","25.201; 25.202; 25.221; 25.222; 25.223; 25.224; 25.225; 25.331; 23.321; 25.306; 25.302; 25.401; 25.420; 25.423; 25.427; 25.433; 25.102; 25.105; 25.142",null,null,null,null,"2006-03-21","2010-07-27"]
[7716,340039,"   Improved L2 support for high data rates","RANimp-L2DataRates",2,"Rel-7","R2","2006-12-15","2007-06-04",1,"RP-070242","RP-070289","Ericsson","Janne.Peisa@ericsson.com","RP#36 completed","25.301; 25.308.25.306; 25.321; 25.322; 25.331; 25.433; 25.435; 25.423; 25.425; 25.999",null,null,null,null,"2006-10-06","2010-07-27"]
[7718,20066,"   Interface to control Tower Mounted Amplifiers (TMAs)","RANImp-TMA",2,"Rel-7","R3,S5","2006-06-02","2007-06-15",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[7721,25026,"Rel-7 RAN improvements - UE Conformance Testing","-",1,"Rel-7","R5","2006-09-20","2009-09-18",1,"-","-","-","-","Linked to Feature UID_20029 (RANimp) ","-",null,null,null,null,"2006-09-22","2010-07-27"]
[7725,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7729,20015,"   VHCRTDD: Stage 2","VHCRTDD-Stage2",2,"Rel-7","R1","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed",25.202000000000002,null,null,null,null,"2004-09-27","2010-07-27"]
[7732,20018,"   VHCRTDD: UTRAN Iub/Iur Protocol Aspects","VHCRTDD-IurIub",2,"Rel-7","R3","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Peter Legg (plegg@ipwireless.com)","RP#31 completed","25.401; 25.420; 25.423; 25.425; 25.427; 25.430; 25.433; 25.435",null,null,null,null,"2004-09-27","2010-07-27"]
[7736,20036,"   EDCHTDD: Stage 2","EDCHTDD-Stage2",2,"Rel-7","R2","2005-03-15","2006-06-15",1,"-","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7738,20038,"   EDCHTDD: Layer 2 and 3 Protocol Aspects","EDCHTDD-L23",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"-","RP-060462","IPwireless","drichards@ipwireless.com","RP#33 completed","25.301; 25.302; 25.306; 25.321; 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[7741,20055,"1.28 Mcps TDD Enhanced Uplink","LCRTDD-EDCH",1,"Rel-7","R1,R2,R3,R4,R5","2006-03-15","2008-09-12",1,"RP-060202","RP-070296","CATT","Haijing Hu","RP#35 completed","-",null,null,null,null,"2006-03-21","2010-07-27"]
[7744,20058,"   1.28 Mcps TDD Enhanced Uplink: UTRAN Iub/Iur Protocol Aspects","LCRTDD-EDCH-IubIur",2,"Rel-7","R3","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Yincheng Zhang","RP#35 completed","25.401; 25.420; 25.423; 25.425; 25.427; 25.430; 25.433; 25.435",null,null,null,null,"2006-03-21","2010-07-27"]
[7747,490016,"Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD","LCRTDD_MB_MF_UEConTest",1,"Rel-7","R5","2010-09-17","2011-09-16",1,"RP-100805","RP-110968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD.","UTRA 34.108; 34.123-1; 34.123-2; 34.123-3",49,25,null,null,"2010-09-08","2011-09-06"]
[7751,53184,"   Aspects of GSM710","GSM-710-test",2,"Rel-7","G1,G3new","2005-08-31","2006-06-30",1,"-","-","-","-","-","-",null,null,null,null,"2005-09-12","2006-07-20"]
[7755,52143,"   Minimise the transfer delay between the SGSN and the MS","SCSAGB-MTD",2,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-061501","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,null,null,"2006-05-03","2008-01-10"]
[7758,52138,"   Deleted- Radio Channel Support","SCSAGB-RCHS",2,"Rel-7","G2","2006-07-17","2006-07-17",1,"GP-051166","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,"SP-32",null,"2005-04-21","2006-05-11"]
[7760,50565,"Addition of new frequency band to GSM (T-GSM810)","TGSM810",1,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-050945","-","Huawei","chende@huawei.com","-","45.005; 45.050; 24.008; 45.008; 45.001; 43.022; 43.030; 44.018; 44.060; 51.010-1; 51.021",null,null,null,null,"2005-04-21","2007-05-29"]
[7766,55095,"   Deleted - MS Conformance Testing","HODSRDTM-MStest",2,"Rel-7","G3new","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","Stopped, no work done. 12/2008 Marked as stopped (\"deleted\")","51-010",null,null,"GP-32",null,"2005-11-21","2008-12-15"]
[7767,53083,"   Deleted - BTS conformance testing","HODSRDTM-BTStest",2,"Rel-7","G1","2005-04-08","2006-11-17",1,"GP-050979","-","Nokia","rami.vaittinen@nokia.com","Stopped, no work done. 12/2008 Marked as stopped (\"deleted\")",51.026000000000003,null,null,"GP-32",null,"2005-04-21","2008-12-15"]
[7770,50572,"   Capability signalling of Mobile Station Receive Diversity, DARP Phase II","MSRD2-CapSig",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060116","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",24.007999999999999,null,null,null,null,"2005-11-21","2007-03-08"]
[7773,50579,"Downlink Dual Carrier","GDCDL",1,"Rel-7","GP","2006-01-20","2009-09-04",1,"GP-061331","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#35 completed","-",null,null,null,null,"2006-01-24","2009-04-01"]
[7778,50582,"Latency Reductions","LATRED",1,"Rel-7","GP","2006-06-30","2007-08-31",1,"GP-061519","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001; 45.002; 45.003; 45.005; 45.010; 43.055; 43.064; 44.060; 51.010-1; 51.021",null,null,null,null,"2006-07-05","2007-09-12"]
[7781,52147,"PS Handover between GERAN/UTRAN mode and GAN Mode","GUGAN",1,"Rel-7","G2","2006-06-30","2007-02-16",1,"GP-061349","-","Ericsson","John.Diachina@Ericsson.com","GP#33 completed","43.318; 44.318; 43.129; 25.306; 24.008; 44.060; 25.331; 51.010",null,null,null,null,"2006-07-05","2008-12-15"]
[7786,51142,"   Performance requirements for HUGE","HUGE-Perfreq",2,"Rel-7","G1","2006-09-08","2008-08-29",1,"GP-061905","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#39 completed",45.005000000000003,null,null,null,null,"2006-09-13","2008-12-15"]
[7789,50121,"REduced symbol Duration, Higher Order modulation and Turbo coding (RED HOT) for downlink","REDHOT",1,"Rel-7","GP","2006-11-17","2011-05-20",1,"GP-071080","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#38 completed","-",null,null,null,null,"2006-11-20","2008-12-15"]
[7792,51146,"   BTS Conformance Tests for REDHOT","REDHOT-BTStest",2,"Rel-7","G1","2006-11-17","2009-05-15",1,"GP-062492","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#42 completed",51.021000000000001,null,null,null,null,"2006-11-20","2009-05-18"]
[7793,53088,"   MS Conformance Tests for REDHOT","REDHOT-Mstest",2,"Rel-7","G3new","2006-11-17","2011-05-20",1,"GP-062491","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#50 completed",51.01,null,null,null,null,"2006-11-20","2011-05-21"]
[7799,32005,"Deleted - IMS Local services","IMSLocal",1,"Rel-7","S2","2006-01-06","2006-01-06",0.99,"-","-","-","-","-",23.228000000000002,null,null,"SP-28",null,"2001-10-08","2002-05-30"]
[7800,32019,"   Deleted - Stage 2","-",2,"Rel-7","S2","2006-01-06","2006-01-06",1,"-","-","-","-","DAB - Not yet required in SA2 as it exists in previous releases","-",null,null,"SP-26",null,"2002-03-25","2004-12-06"]
[7804,14018,"Deleted: Generic User Profile Phase 2","-",1,"Rel-7","C4","2005-08-08","2006-06-30",1,"-","-","-","-","Created at TSG#27 by A. Sultan because of the move to Rel-7 of \"Common Objects\". ","-",null,null,"SP-27",null,"2005-03-09","2005-03-09"]
[7808,31050,"Study on Behaviour of Multi system UEs","BMSU",1,"Rel-7","S1","2004-06-28","2005-12-15",1,"SP-050502","-","Qualcomm","dwilliams@qualcomm.com","-",22.936,null,null,null,null,"2004-08-30","2008-06-27"]
[7812,31073,"Study on Network Selection Principles","NetSel",1,"Rel-7","S1","2005-03-15","2005-12-08",1,"SP-050227","-","O2","chris.friel@O2.com","Spin-off Feature Network selection enhancements (NSP-CR) UID_7041",22.811,null,null,null,null,"2005-03-22","2008-06-27"]
[7815,32073,"Study on Enhancement of E2E QoS","QoS7",1,"Rel-7","S2","2004-06-28","2005-09-15",1,"SP-040326","-","Huawei","Robert Jaksa","-",23.802,null,null,null,null,"2004-08-30","2008-06-30"]
[7818,35068,"Study on IRP Information Model","OAM7-NIM-IM",1,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050611","-","Motorola","trevor.pirt@motorola.com ","SP#35 completed",32.81,null,null,null,null,"2005-09-16","2010-07-27"]
[7821,7025,"Feasibility Study on the TCAPsec Gateway concept","FS_SEC7-TCAP",1,"Rel-7","C4","2005-10-28","2006-03-10",1,"CP-050687","-","Siemens","Ulrich.wiehe@gksag.de","TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway",29.8,null,null,null,null,"2005-10-07","2008-07-01"]
[7823,320018,"Study on Support of (G)MSC-S - (G)MSC-S Nc Interface based on the SIP-I protocol","NcSIP",1,"Rel-7","C4,C3","2006-05-15","2007-09-14",1,"CP-070034","-","Vodafone","david.hutton@vodafone.com","-",29.802,null,null,null,null,"2006-06-21","2008-07-01"]
[7826,20023,"Study on Evolved UTRA and UTRAN","RANFS-Evo",1,"Rel-7","RP","2004-12-15","2006-09-15",1,"RP-040461","RP-060472","NTT DoCoMo","nakamurata@NTTDOCOMO.CO.JP","RP#33 (Sep 2006) completed. SR in RP-060472",25.911999999999999,null,null,null,null,"2005-01-04","2008-06-23"]
[7830,20051,"Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN","RANFS-MBMSImp",1,"Rel-7","R2","2005-12-15","2006-12-15",1,"RP-050746","RP-060692","LG Electronics","leego@lge.com","RP#34 completed",25.905000000000001,null,null,null,null,"2005-12-15","2012-07-26"]
[7834,330013,"Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met","FSUEPow",1,"Rel-7","R4","2007-06-22","2007-06-22",1,"RP-060641","RP-070534","Nokia","Chris.callender@nokia.com, tiina.s.koskinen@nokia.com","RP#37 (Sep 2007) completed. SR in RP-070534",25.905999999999999,null,null,null,null,"2006-10-06","2008-06-23"]
[7838,31077,"Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN)","PNPAN",1,"Rel-7","S1","2005-12-08","2005-12-08",1,"SP-050386","-","Vodafone","armin.toepfer@vodafone.com","-","-",null,null,"SP-30",null,"2005-04-21","2005-12-22"]
[7841,32029,"Deleted - Study on applicability of GALILEO for LCS","Galileo",1,"Rel-7","S2","2005-06-30","2005-06-30",1,"SP-020541","-","-","-","-","-",null,null,"SP-25",null,"2002-11-08","2004-09-08"]
[7843,50095,"   Deleted - GERAN review of the TR","-",2,"Rel-7","GP","2005-06-30","2005-06-30",1,"-","-","-","-","-","-",null,null,"SP-26",null,"2003-07-23","2004-12-06"]
[7846,32098,"   Deleted - Study on enhancement of radio performance for VoIMS","-",2,"Rel-7","S2","2006-07-21","2006-07-21",1,"SP-050351","-","Nortel","Laurence Lautier (lautierl@nortel.com)","WID approved SP#28. SA2#52 stopped",23.806999999999999,null,null,"SP-32",null,"2005-06-22","2006-05-31"]
[7849,34040,"Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) ","-",1,"Rel-7","S4","2007-06-22","2007-06-22",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP-38 stopped",26.966999999999999,null,null,"SP-38",null,"2006-12-10","2007-06-22"]
[7853,0,"--- RELEASE 6 ---","-",1,"Rel-6","NP,GP,RP,SP,TP","2002-06-28","2005-12-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[7856,24006,"   Improving Receiver Performance Requirements for the FDD UE","RInImp-UERecPerf",2,"Rel-6","R4","2002-03-08","2003-09-19",1,"-","-","Intel","shimon.moshavi@INTEL.COM","-",25.100999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7860,24009,"   DS-CDMA introduction in the 800 MHz band","RInImp-UMTS800",2,"Rel-6","R4","2003-03-14","2003-12-12",1,"-","-","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","Introduction of UMTS800 in 25.307","25.101, 25.104, 25.133, 25.141, 25.307, 25.331",null,null,null,null,"2003-10-02","2009-07-09"]
[7864,20011,"      Improved Minimum Performance Requirements for HSDPA UE categories 7 and 8","RInImp-HSPerf-10code",3,"Rel-6","R4","2004-09-15","2006-06-09",1,"-","-","Nokia","jussi.numminen@nokia.com","Approved at RP#25 as RP-040375",25.100999999999999,null,null,null,null,"2004-09-27","2006-01-13"]
[7865,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[7871,21000,"   FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD","RInImp-IfIsMLCR",2,"Rel-6","R1","2001-12-14","2003-09-19",1,"-","-","Samsung","Li Xiao Qiang (xqli@samsung.co.kr)","-",25.888000000000002,null,null,null,null,"2003-10-02","2004-07-08"]
[7872,21003,"   FS for the analysis of OFDM for UTRAN enhancement","RInImp-FSOFDM",2,"Rel-6","R1","2002-06-10","2004-06-14",1,"-","-","Nortel","Sarah Boumendil","-",25.891999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7875,24011,"   FS on Low Output Powers for general purpose FDD BSs","RInImp-FSLoPw",2,"Rel-6","R3","2003-06-13","2004-03-12",1,"-","-","Telefónica","Ana Burgos (burgos_a@tsm.es)","-",25.806999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[7878,23006,"   Deleted - FS on the evolution of the UTRAN architecture","RANimp-FSEvo",2,"Rel-6","R3","2002-09-09","2004-12-14",1,"-","-","Nokia","woonhee.hwang@nsn.com, Antti.Toskala@nokia.com","Study Closed, work will continue within the FS on evolved UTRA and UTRAN","-",null,null,"RP-26",null,"2002-09-16","2005-01-13"]
[7883,20007,"   FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects","EDCH-IurIub",2,"Rel-6","R3","2004-03-15","2005-03-14",1,"-","-","Nortel","Saso Stojanovski","-","25.401, 25.420, 25.423, 25.430, 25.433",null,null,null,null,"2004-03-18","2005-03-25"]
[7886,9,"Rel-6 RAN improvements","-",1,"Rel-6","RP,S5","2002-09-09","2005-03-14",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2000-03-31","2004-07-08"]
[7891,23009,"      Deleted - Iu enhancements for IMS support in RAN","RANimp-RABSE-IuEnhIMS",3,"Rel-6","R3","2003-03-14","2004-06-03",1,"-","-","Nortel","Philippe.Godin@nortelnetworks.com","Closed RP#24 due to the lack of progress","-",null,null,"RP-24",null,"2003-03-27","2006-01-13"]
[7894,23012,"   Rel-6 RRM optimization for Iur and Iub","RANimp-RRMopt-UEMsD",2,"Rel-6","R3","2003-09-19","2004-03-12",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2003-03-27","2004-07-08"]
[7895,23014,"      Improved access to UE measurement data for CRNC to support TDD RRM","-",3,"Rel-6","R3","2003-09-19","2004-03-12",1,"-","-","Interdigital","jim.miller@interdigital.com","-",25.422999999999998,null,null,"RP-22",null,"2003-10-02","2005-01-13"]
[7898,35023,"      OAM&P impacts","RANimp-TiltAnt-OAM",3,"Rel-6","S5","2004-02-27","2004-09-16",1,"S5-048270","-","Vodafone","Adrian.Neal@vodafone.com","SP#25 09/2004 completed","32.804, 32.64x",null,null,null,null,"2004-03-30","2006-01-13"]
[7904,32001,"   Enhanced support for anonymity and user privacy","-",2,"Rel-6","S2,OMA","2002-07-08","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2001-09-19","2012-05-21"]
[7906,32054,"      Stage 3 - impacts MLP and RLP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7909,32055,"      Stage 3 - definition of RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[7913,32026,"   New area event for location service triggering reports","-",2,"Rel-6","S2,N4,OMA","2002-06-03","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-05-21"]
[7917,20001,"   UE positioning for Location Services enhancements 2","LCS2-UEpos",2,"Rel-6","R2,R4,R5","2001-01-15","2004-09-14",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-16","2012-05-21"]
[7920,22002,"      Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods","LCS2-UEpos-FSBlank",3,"Rel-6","R2","2002-07-01","2003-09-19",1,"-","-","Cambridge Positioning Systems","david.bartlett@cursor-system.com","RP#38 Work stopped","new 25.894",null,null,"RP-38",null,"2002-06-21","2012-05-21"]
[7921,2457,"      Deleted - UE positioning enhancements - other methods","LCS2-UEpos-enh",3,"Rel-6","R2","2003-09-26","2003-09-26",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","RP#24 Work stopped","-",null,null,"RP-24",null,"2004-10-19","2012-05-21"]
[7926,33006,"      Rel-6 Network Domain Security","SEC1-NDS",3,"Rel-6","S3","2002-06-17","2003-09-25",1,"SP-000420","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#9 approved WID S3-000606 (Network Domain Security)","33.102, 33.103, 33.105",null,null,null,null,"2002-11-08","2011-08-08"]
[7928,33017,"   Network Domain Security; Authentication Framework (NDS/AF)","SEC1-NDS-AF",2,"Rel-6","S3","2002-02-15","2004-02-13",1,"SP-030108","-","Nokia","tommi.viitanen@nokia.com","SP#19 approved WID",33.81,null,null,null,null,"2003-03-27","2011-08-08"]
[7932,14014,"   Enhancements to the Cx and Sh interfaces","IMS2-CCR",2,"Rel-6","N4","2003-06-06","2004-08-31",1,"NP-030229","-","-","-","Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done.","-",null,null,null,null,"2003-06-09","2005-03-25"]
[7935,31026,"      Stage 1 - TS on IMS group management","-",3,"Rel-6","S1","2002-03-14","2002-12-09",1,"-","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2003-12-07"]
[7939,32037,"      Stage 2 for IMS Conferencing","-",3,"Rel-6","S2","2002-11-04","2003-12-31",1,"-","-","-","-","-",23.228000000000002,null,null,null,null,"2003-02-27","2004-03-12"]
[7943,31034,"      Stage 1 22.340","IMSM-TS",3,"Rel-6","S1","2002-11-11","2002-12-11",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-",22.34,null,null,null,null,"2003-01-13","2010-09-07"]
[7946,11039,"      Stage 3 for IMS Messaging","-",3,"Rel-6","N1","2002-12-13","2004-12-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2003-01-13","2005-03-25"]
[7948,11040,"   Additional SIP Capabilities support not covered by Rel-5","-",2,"Rel-6","N1","2002-11-11","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[7951,11052,"      Procedured associated with IMS-ALG","-",3,"Rel-6","N1","2004-09-06","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2005-04-20","2005-06-02"]
[7954,13004,"      Interworking for 3GPP_SIP and IETF_SIP","-",3,"Rel-6","N3","2000-08-28","2003-06-13",1,"-","-","Siemens","Thomas.Belling@nsn.com","[DAB - 20.08.03] - CN Part of TR Complete @ CN#20","New 29.962",null,null,null,null,"2002-02-28","2003-09-15"]
[7957,11017,"      stage 3 of interworking with non-IMS IP networks","-",3,"Rel-6","N1","2001-03-14","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2004-09-08"]
[7962,31042,"   IMS Subscription and access scenarios","-",2,"Rel-6","S1","2002-12-16","2003-06-13",1,"-","-","TeliaSonera","FRANK, Robert","-",22.8,null,null,null,null,"2003-03-28","2010-08-31"]
[7966,32063,"3GPP Enablers for services like Push to Talk over Cellular (PoC)","PoC",1,"Rel-6","S2,S4,S5","2003-09-08","2005-06-09",1,"SP-030384","-","Ericsson","Shabnam Sultana","-","-",null,null,null,null,"2003-10-15","2004-07-08"]
[7969,34029,"   Selection of one or more PoC codec(s) for PoC","-",2,"Rel-6","S4","2004-09-13","2004-12-16",1,"-","-","-","-","Completed","26.235, 26.236",null,null,null,null,"2004-10-01","2004-12-06"]
[7970,35036,"   PoC charging","PoC-CH",2,"Rel-6","S5","2004-09-27","2005-06-09",1,"SP-050032","-","Siemens","Gerald.Goermer@nsn.com","SP#28 06/2005 completed",32.271999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[7974,32061,"   Stage 2 for commonality","-",2,"Rel-6","S2","2002-09-16","2003-09-19",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","-",23.864000000000001,null,null,null,null,"2003-09-15","2004-07-08"]
[7977,31004,"   Stage 1 for Support of Push Services","-",2,"Rel-6","S1","2001-01-03","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2003-07-04"]
[7980,42010,"   Definition of service requirements for MMS6","MMS6-SR",2,"Rel-6","S1","2002-11-15","2003-12-19",1,"-","-","-","-","-",22.14,null,null,null,null,"2002-09-26","2004-03-12"]
[7983,42012,"   OMA dependencies","-",2,"Rel-6","OMA","2003-08-15","2005-04-29",1,"-","-","-","-","-","OMA specs",null,null,null,null,"2002-09-26","2005-03-25"]
[7988,42005,"Rel-6 MExE enhancements","MEXE6",1,"Rel-6","T2","2002-03-08","2003-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-21","2002-03-21"]
[7992,2499,"Presence Capability","PRESNC",1,"Rel-6","S1,S2,S3,S4,N1,N3,N4,OMA","2001-03-19","2005-12-07",1,"SP-010064","-","Motorola","Mark Cataldo","merged \"Presence Service Enhancements\" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date","-",null,null,null,null,"2001-03-30","2004-09-08"]
[7996,13018,"   Stage 3 (CN3 Part Pk interface)","-",2,"Rel-6","N3","2002-04-01","2005-03-11",1,"NP-040492","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","29.061, 29.161",null,null,null,null,"2004-06-08","2011-08-09"]
[7999,60003,"   SIMPLE Presence","-",2,"Rel-6","OMA","2004-01-01","2005-03-31",1,"SP-040232","-","-","OMA-LIAISON@mail.openmobilealliance.org","SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables","-",null,null,null,null,"2004-06-08","2011-08-09"]
[8000,50056,"Enhanced A/Gb feasibility study","AGbEnFS",1,"Rel-6","GP","2002-08-30","2002-11-08",1,"GP-022565","-","Vodafone","jose-luis.carrizo@vodafone.co.uk","-","None",null,null,null,null,"2002-05-23","2009-11-18"]
[8003,50084,"      Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2003-01-13","2009-11-18"]
[8009,50064,"   Realisation of a Flexible Layer One","FLOGER-Real",2,"Rel-6","GP","2000-01-03","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[8011,51002,"      Architecture in 45.001 and 43.051","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8014,51005,"      Performance Requirements in 45.005 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2000-01-03","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8018,52073,"      Modifications to RLC/MAC in 44.060 and 44.160","-",3,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[8022,55077,"   Deleted - GERAN MS Conformance test for the Flexible Layer One - DELETE","FLOGER-Msconf",2,"Rel-6","G4,G5","2004-02-06","2004-02-06",1,"GP-021022","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-27",null,"2002-05-23","2005-03-09"]
[8025,53080,"      Deleted at TGS #27 - BTS Test in 51.021 - DELETE","-",3,"Rel-6","G3new","2004-02-06","2004-02-06",1,"-","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-22",null,"2002-09-26","2005-03-09"]
[8026,50041,"Uplink TDOA feasibility study","TDOAF",1,"Rel-6","GP","2001-11-30","2002-06-28",1,"GP-012794","-","TruePosition","Bob Gross (rlgross@trueposition.com)","-",45.811,null,null,null,null,"2001-12-10","2003-04-24"]
[8031,32703,"      Stage 2 MBMS Specification Work","-",3,"Rel-6","S2","2002-08-19","2004-03-17",1,"-","-","-","-","-",23.245999999999999,null,null,null,null,"2002-09-26","2012-07-26"]
[8034,33008,"   Security aspects of MBMS","-",2,"Rel-6","S3","2002-07-01","2005-03-18",1,"SP-020514","-",3,"adrian.escott@three.co.uk","SP#17 approved WID S3-020433","New 33.246 ",null,null,null,null,"2002-11-08","2012-07-26"]
[8037,31044,"      Stage 1 for MBMS User Services","-",3,"Rel-6","S1","2003-05-13","2004-04-01",1,"-","-","-","-","-",22.245999999999999,null,null,null,null,"2001-03-30","2012-07-26"]
[8040,20022,"      Introduction of MBMS in RAN (physical & upper layers, access network interfaces)","-",3,"Rel-6","R2","2002-01-01","2004-12-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","25.346, 25.304, 25.321, 25.322, 25.323",null,null,null,null,"2004-09-27","2012-07-26"]
[8045,25023,"      Signalling Conformance Test Aspects – MBMS for LCR TDD","MBMS-UEConTest_SIGTDL",3,"Rel-6","R5,T1","2006-09-20","2007-12-07",1,"-","-","Datang","zhaojian@datangmobile.cn","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2012-07-26"]
[8048,50085,"   Support of MBMS in GERAN","MBMS-GERAN",2,"Rel-6","GP,G2,G3new","2001-08-30","2005-01-28",1,"GP-022566","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8051,50098,"      Simultaneous support of MBMS services","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8053,50100,"      MBMS Resynchronization at cell change","-",3,"Rel-6","GP","2001-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8056,50089,"      MBMS Changes to the Gb interface","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8060,53081,"      MBMS-GERAN - MS conformance tests","-",3,"Rel-6","G3new","2002-01-25","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8062,31006,"Speech Recognition and Speech Enabled Services","SRSES",1,"Rel-6","S1,S2,S4,OMA","2001-10-08","2005-12-30",1,"SP-010572","-","-","-","-","-",null,null,null,null,"2001-10-09","2004-09-08"]
[8067,11021,"   Deleted - SES codec negotiation at Session Description Protocol (SDP)","-",2,"Rel-6","N1","2003-06-04","2003-06-04",1,"-","-","-","-","Abandoned NP-23","-",null,null,"NP-23",null,"2004-10-20","2004-10-21"]
[8071,42002,"   Stage 2 - Data Description Method","-",2,"Rel-6","N4","2002-12-05","2005-03-03",1,"TP-020275","-","T-Mobile","kurt.bischinger@t-mobile.at","TR approved in CN#26",23.241,null,null,null,null,"2001-10-09","2005-03-09"]
[8074,31010,"Digital Rights Management","DRM",1,"Rel-6","S1,OMA","2001-10-08","2004-05-28",1,"SP-010577","-","-","-","Foreseen start and completion dates introduced by MCC (no indication at all on the WID)","-",null,null,null,null,"2001-10-11","2001-10-11"]
[8075,31011,"   Requirements for Digital Rights Management","-",2,"Rel-6","S1","2001-10-08","2002-06-13",1,"-","-","Openwave","nicholas.wood@openwave.com","-","-",null,null,null,null,"2001-10-11","2003-07-04"]
[8079,31037,"   Deleted - Monitoring of Stages 2 and 3 progress (actual work to be done by OMA)","-",2,"Rel-6","S1","2003-03-21","2003-03-21",1,"-","-","-","-","Replaced by UID 60005 and 60006","-",null,null,"SP-19",null,"2003-01-15","2004-09-08"]
[8082,31035,"   Stage 1 for WLAN-UMTS Interworking Rel-6","WLAN-TS",2,"Rel-6","S1","2003-01-06","2004-06-11",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","-","22.101, 22.105",null,null,null,null,"2003-01-13","2004-06-08"]
[8088,11047,"   Stage 3 for scenario 3","-",2,"Rel-6","N1","2003-05-23","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-06-08","2005-03-09"]
[8090,43010,"   USIM enhancements for WLAN Interworking","-",2,"Rel-6","T3","2003-09-05","2005-03-04",1,"TP-030185","-","Axalto","Jabellan@axalto.com","-",31.102,null,null,null,null,"2004-12-06","2011-09-01"]
[8093,31017,"   Stage 1 - Requirements for Priority Service","PRIOR-SR",2,"Rel-6","S1","2002-05-30","2003-09-17",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-","-",null,null,null,null,"2002-02-27","2010-08-31"]
[8097,31038,"   Stage 1 - CRs to implement Network Sharing","NTSharCR",2,"Rel-6","S1","2003-01-20","2003-12-19",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","22.011, 22.101, 22.115, 22.129",null,null,null,null,"2003-03-14","2009-11-10"]
[8101,25004,"   Conformance Test Aspects – Network Sharing","NTShar-UTRANEnh_Test",2,"Rel-6","R5","2005-03-11","2006-03-10",1,"-","-","TeliaSonera","Niklas.Wiren@TeliaSonera.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[8102,32016,"QoS Improvements","QoS1",1,"Rel-6","S2,N3","2002-07-15","2004-12-08",1,"SP-010719","-","Nokia","-","-","23.107, 23.207, 23.221",null,null,null,null,"2002-01-24","2002-01-24"]
[8105,13016,"   Gq interface specification for Dynamic Policy control enhancements – Stage 3","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"NP-030198","-","Nokia","Anna.Sillanpaai@nokia.com","[DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004","29.207, 29.208, 29.209",null,null,null,null,"2003-10-13","2005-03-09"]
[8110,11049,"   Stage 3 Ua & Ub interfaces","-",2,"Rel-6","N1","2003-11-03","2004-12-08",1,"-","-","Nokia","-","-",24.109000000000002,null,null,null,null,"2004-03-01","2009-11-10"]
[8113,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[8116,15028,"   Policy management extensions","-",2,"Rel-6","N5","2002-10-31","2003-12-12",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-01-13","2005-01-13"]
[8119,15033,"   Introduction of migration support mechanism","-",2,"Rel-6","N5","2002-10-31","2003-12-10",1,"-","-","-","-","-","29.198, 29.998",null,null,null,null,"2003-03-27","2005-01-13"]
[8123,50401,"Addition of frequency bands to GSM (TAPS)","TAPS",1,"Rel-6","GP","2002-06-28","2005-01-28",1,"GP-022072","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2005-03-09"]
[8127,54103,"      Deleted - 51.010-1 Add testing","-",3,"Rel-6","G4","2002-06-28","2005-01-28",1,"GP-022074","-","Nokia","Torben Themsen","-","-",null,null,"GP-23",null,"2002-07-31","2005-03-09"]
[8128,50130,"Seamless support of streaming services in A/Gb mode","SSStrea",1,"Rel-6","GP,S3","2000-01-03","2005-06-17",1,"GP-022561","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2004-01-14"]
[8131,51132,"   Performance study of cell change mechanisms","-",2,"Rel-6","G1","2000-01-03","2003-08-29",1,"GP-022562","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[{"$f":"A8136+1","v":8136},52133,"      optimizations of existing mechanisms/procedures","-",3,"Rel-6","G2","2003-06-27","2003-11-21",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[8139,52136,"      Dependency to other features of Reduction of service interruption times and packet loss during mobility procedures","-",3,"Rel-6","G2","2003-06-27","2003-11-21",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[8142,33013,"   GERAN A/Gb mode security enhancements","-",2,"Rel-6","S3","2002-09-26","2005-01-28",1,"SP-030107","-","Vodafone","peter.howard@vodafone.com","SP#19 approved WID",33.101999999999997,null,null,null,null,"2003-01-15","2011-08-08"]
[8145,35010,"Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM6",1,"Rel-6","S5","2002-09-12","2005-03-11",1,"SP-040766","-","-","-","SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4.","-",null,null,null,null,"2002-11-08","2005-01-13"]
[8150,35022,"      Subscriber and UE trace management","-",3,"Rel-6","S5","2002-09-20","2004-12-16",1,"-","-","Nokia","kari.t.ronka@nokia.com","SP#26 12/2004 completed","32.421, 32.422, 32.423, 52.008",null,null,null,null,"2003-10-03","2006-01-13"]
[8153,35016,"Rel-6 Charging Management","CH",1,"Rel-6","S5,S2,N3","2002-11-21","2005-06-09",1,"SP-040773","-","T-Mobile","karl-heinz.nenner@t-mobile.de","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[8154,35037,"   Charging architecture and principles","-",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.24,null,null,null,null,"2004-10-29","2006-01-13"]
[8158,35027,"   Online Charging System (OCS) architecture study","-",2,"Rel-6","S5","2003-03-21","2003-09-18",1,"-","-","-","-","SP#21 09/2003 completed",32.814999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[8161,35029,"      CS domain charging","-",3,"Rel-6","S5","2003-03-21","2004-03-18",1,"-","-","-","-","SP#23 03/2004 completed",32.25,null,null,null,null,"2004-10-29","2006-01-13"]
[8165,32030,"   Overall architectural aspects of IP flow based bearer level charging","CH-FBC",2,"Rel-6","S2,N3","2002-11-21","2005-03-11",1,"SP-040041","-","-","-","-",23.125,null,null,null,null,"2003-01-15","2004-07-08"]
[8167,32070,"      Study on providing policy control with FBC","-",3,"Rel-6","S2","2004-02-02","2004-07-30",1,"-","-","-","-","-","-",null,null,null,null,"2004-05-20","2004-10-21"]
[8173,43006,"      2G/3G Java Card™ API based applet interworking","-",3,"Rel-6","T3","2003-03-17","2004-03-05",1,"TP-030031","-","Oberthur Card Systems","Stéphane Andrau","-","-",null,null,null,null,"2003-09-08","2005-01-19"]
[8176,43004,"   Rel-6 USIM toolkit enhancements","USAT1-API-MULTOS",2,"Rel-6","T3","2000-09-25","2005-03-04",1,"-","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2002-11-29","2005-01-19"]
[8179,502033,"         Test specification for C SIM API","-",4,"Rel-6","T3","2001-01-01","2001-09-28",1,"TP-000155","-","Aspects Software","Neil Livingston","-","-",null,null,null,null,"2000-09-14","2010-02-09"]
[8180,43009,"      USIM application toolkit Conformance Test Specification for Mobile Equipments ","-",3,"Rel-6","T3","2003-12-05","2005-03-04",1,"TP-030259","-","Gemplus","Eric.laffont@gemplus.com","-",31.123999999999999,null,null,null,null,"2004-12-06","2005-06-02"]
[8184,34023,"AMR-WB extension for high audio quality","AMRWB+",1,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-030083","-","Nokia","janne.m.vainio@nokia.com","TR tbc by Sept. 05","26.290, 26.304, 26.273, 26.274, 26.412, 26.936",null,null,null,null,"2002-11-28","2006-01-13"]
[8188,12006,"Enhancement of dialled service for CAMEL","EDCAMEL",1,"Rel-6","S1,N2,N4","2003-03-28","2003-12-31",1,"SP-020818","-","Samsung","craig.bishop@samsung.com","-",22.077999999999999,null,null,null,null,"2003-03-14","2009-11-13"]
[8193,50602,"      Multiple TBF Concept paper","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2003-09-16"]
[8195,50604,"      Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2004-12-06"]
[8199,50444,"Addition of U-TDOA in the CS domain ","UTDOACS",1,"Rel-6","GP","2003-11-21","2004-04-23",1,"GP-032773","-","TruePosition","Bob Gross, Rhys Robinson (rlgross@trueposition.com)","Completed, except for potential LMU performance specs","-",null,null,null,null,"2003-12-01","2004-03-12"]
[8202,50102,"   DARP test scenarios","DARP-TS",2,"Rel-6","GP","2003-11-21","2004-08-27",1,"GP-041967","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8206,50106,"   DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE",2,"Rel-6","GP","2004-02-06","2004-11-12",1,"GP-041969","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2005-03-09"]
[8207,50107,"      Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8210,50116,"   GERAN MS Conformance test for DARP","ARP-ConfTest",2,"Rel-6","G3new","2004-08-27","2005-09-02",1,"GP-041971","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[8215,50113,"   Deleted - MS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfMS",2,"Rel-6","G3new","2004-06-25","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2008-12-12"]
[8218,31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[8221,32072,"   Deleted - Stage 2 description on Redial","-",2,"Rel-6","S2","2004-05-03","2004-12-16",1,"SP-040331","-","Vodafone","chris.pudney@vodafone.com","-","-",null,null,"SP-26",null,"2004-05-20","2005-03-09"]
[8225,13024,"Reorganisation of CS Data Specifications","CSData",1,"Rel-6","N3","2004-11-19","2004-12-08",1,"NP-040563","-","Siemens","Thomas.Belling@nsn.com","Created at TSG#27 as 100 % complete","23.910, 29.007, New 23.202",null,null,null,null,"2005-03-02","2005-03-09"]
[8228,50554,"   GAAI – Stage 2","GAAI-Stage2",2,"Rel-6","GP","2004-08-27","2005-04-08",1,"-","-","Ericsson","jari.vikberg@ericsson.com","-",43.317999999999998,null,null,null,null,"2004-10-15","2005-03-25"]
[8232,50560,"   Stage 2 for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-Stage2",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051161","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-Stage2",43.128999999999998,null,null,null,null,"2005-04-20","2006-01-13"]
[8233,50561,"   PS handover for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-PSHO",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051162","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-PSH","-",null,null,null,null,"2005-04-20","2006-01-13"]
[8237,60111,"(Small) Technical Enhancements and Improvements for Rel-6","TEI6",1,"Rel-6","SP,CP,RP,GP","2006-06-02","2006-06-02",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 6 CR not related to any feature and with very limited impact on the system. Moved in from Stoyan/Testing WP","-",null,null,null,null,"2006-09-21","2008-05-06"]
[8241,50500,"Deleted SCSAGB - Support of Conversational Services in A/Gb mode via the PS domain","-",1,"Rel-6","GP,N1","2003-11-21","2004-02-19",1,"GP-030443","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","-","-",null,null,"GP-18",null,"2003-02-13","2010-03-02"]
[8244,50503,"   Deleted - Radio Channel Support","SCSAGB-RCS",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030446","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[8247,50506,"   Deleted SCSAGB-FLO - Modifications to FLO","-",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030449","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"RP-29",null,"2003-02-13","2010-03-02"]
[8250,625,"IP transport in the UTRAN","ETRAN-IPtrans",1,"Rel-5","R3","2000-07-17","2002-03-29",1,"-","-","Alcatel","Nicolas Drevon","-","-",null,null,null,null,"2000-03-31","2001-12-12"]
[8255,2479,"   Iub/Iur protocol aspects - for High Speed Downlink Packet Access","HSDPA-IubIur",2,"Rel-5","R3","2001-04-02","2002-03-29",1,"RP-010262","-","Motorola","Mike Diesen","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[8256,2480,"   RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","HSDPA-RF",2,"Rel-5","R4","2001-04-09","2003-06-06",1,"RP-010262","-","Motorola","Howard Benn","-","-",null,null,null,null,"2001-03-20","2003-03-27"]
[8259,501216,"Rel-5 Improvements of Radio Interface","-",1,"Rel-5","RP","2000-08-14","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8263,2469,"   Enhancement on the DSCH hard split mode","RInImp-DSCHhsp",2,"Rel-5","R1","2001-03-16","2002-03-29",1,"-","-","Samsung","Jaeyoel KIM","-","-",null,null,null,null,"2001-03-20","2002-03-25"]
[8267,2494,"   FS on the re-introduction of the downlink SIR measurement","RInImp-SIR",2,"Rel-5","R4","2001-03-12","2001-12-14",1,"-","-","Ericsson","Torgny.Palenius@ericsson.com","-","-",null,null,null,null,"2001-03-27","2001-11-29"]
[8270,2210,"      Deleted - Testing improvement of inter-frequency and inter-system measurement","-",3,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8272,500009,"Rel-5 RAN improvements","-",1,"Rel-5","RP","2001-03-16","2007-03-09",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2002-06-21"]
[8278,2489,"   Separation of resource reservation and radio link activation","RANimp-SepRR",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[8281,2491,"   Re-arrangements of Iub transport bearers","RANimp-TTPS",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[8282,22000,"   RAB support enhancement for Rel-5 ","RANimp-RABSE5",2,"Rel-5","R2","2001-04-02","2002-06-28",1,"-","-","Nokia","Juha Mikola","RFC 3095 context relocation","-",null,null,null,null,"2002-05-30","2002-06-21"]
[8285,21002,"   Support of Site Selection Diversity Transmission in UTRAN","RANimp-SSDT",2,"Rel-5","R1","2001-12-14","2002-06-04",1,"-","-","NEC","-","RP-020356","-",null,null,null,null,"2002-02-28","2002-06-21"]
[8289,41010,"      Deleted - General changes to TS34.121 and TS34.122 corresponding to release 5","RANimp-test,TEI5",3,"Rel-5","T1","2003-03-03","2004-03-01",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121, 34.122",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8293,1633,"      Stage 1 for Call control and roaming to support IMS in UMTS","-",3,"Rel-5","S1","2000-02-21","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Issues include e.g.: Roaming requirements, Requirements on supplementary services, Interworking requirements",22.228000000000002,null,null,null,null,"2000-08-08","2001-03-30"]
[8298,1278,"         IMS stage 3","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228999999999999,24.228999999999999,null,null,null,null,"2000-04-19","2003-03-14"]
[8300,25006,"      Conformance Test Aspects – IMS Call Control","IMS-CCR_Test",3,"Rel-5","R5","2005-03-11","2006-12-01",1,"-","-","Motorola","Jacob.John@motorola.com","-","34.108, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2002-02-28","2010-06-16"]
[8304,2522,"         IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[8307,11000,"         IETF: RFC 3265 (specific event notification)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8311,11005,"         IETF: RFC 3266 (IPv6 support within SDP)","-",4,"Rel-5","N1","2000-01-03","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8312,11022,"         IETF: RFC 3311 (The Update method)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8315,1290,"         Addressing","-",4,"Rel-5","S2","2000-10-09","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2000-04-01"]
[8320,1298,"   Access Security for IMS","IMS-ASEC",2,"Rel-5","S3,T3","2001-10-08","2002-06-28",1,"SP-010323","-","Ericsson","krister.boman@emw.ericsson.se","-","-",null,null,null,null,"2000-04-18","2011-08-08"]
[8323,2574,"   Security Aspects of Requirement for Network Configuration Independence","SEC1-NCI",2,"Rel-5","S3","2001-07-02","2001-12-28",1,"SP-010324","-","AT&T Wireless","hugh.shieh@attws.com","Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C",33.203000000000003,null,null,null,null,"2001-06-09","2011-08-08"]
[8327,2039,"      Codecs","-",3,"Rel-5","S4","2000-07-26","2002-03-14",1,"SP-000398","-","-","-","-","26.235, 26.236",null,null,null,null,"2000-09-28","2002-03-25"]
[8330,11025,"      IETF: RFC 3310 (HTTP Digest Authentication using AKA)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8333,32004,"      Stage 2 for SIP message compression","-",3,"Rel-5","S2","2001-09-24","2001-10-26",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2001-11-24"]
[8335,10001,"   Stage 3 description of IMS interfaces","-",2,"Rel-5","NP","2001-03-14","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-01-24"]
[8338,11016,"      Mw interface (CSCF to P-CSCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8342,11019,"      ISC (IMS Service Control) Interface","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-05-30"]
[8346,11027,"      Mi interface (CSCF to BGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[8349,1310,"   Support of VHE/OSA by entities and protocols of the IMS (e.g. CSCF)","IMS-ONOSA",2,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2002-06-21"]
[8353,12003,"      Stage2 work 'Si interface'","-",3,"Rel-5","N2","2002-01-07","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2002-01-24","2003-01-13"]
[8355,14004,"      Deleted - SDM issues for CAMEL control of IMS","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"NP-17",null,"2001-10-08","2008-12-12"]
[8360,34012,"      Billing, accounting and call detail record aspects","-",3,"Rel-5","S5","2001-09-27","2002-09-12",1,"SP-010631","-","T-Mobile","Karl-Heinz.Nenner@T-MOBILE.DE","-",32.225000000000001,null,null,null,null,"2001-10-09","2002-11-08"]
[8361,10002,"   Other IETF dependencies","-",2,"Rel-5","NP","2000-11-24","2002-06-07",1,"-","-","-","-","Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined)","-",null,null,null,null,"2001-10-11","2002-03-25"]
[8364,1844,"   Conformance Test Aspects - Provisioning of IMS","IMS-TEST",2,"Rel-5","T1","2002-03-18","2002-12-27",1,"-","-","-","-","The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008","-",null,null,null,null,"2000-09-14","2008-12-12"]
[8369,34002,"   Stage 1 for Extended Transparent End-to-End PS Streaming Service","-",2,"Rel-5","S1","2002-11-18","2003-03-17",1,"SP-010392","-","Vodafone","stephen.wolak@vodafone.com","2nd resp SA4",22.233000000000001,null,null,null,null,"2001-06-28","2002-03-25"]
[8372,34019,"   RTP usage model","-",2,"Rel-5","S4","2002-01-03","2002-12-06",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)",26.937000000000001,null,null,null,null,"2002-03-25","2008-12-12"]
[8375,1429,"   OSA APIs for Multimedia Call Control","OSA1-CSCF",2,"Rel-5","S2","2000-07-11","2002-06-07",1,"-","-","-","-","For Rel5 even if completed by March","-",null,null,null,null,"2000-04-19","2002-01-24"]
[8377,15002,"      Stages 2 and 3 for Multimedia Call Control","-",3,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-04",null,null,null,null,"2002-02-28","2002-06-21"]
[8383,2121,"      Stage 1 for OSA Security","-",3,"Rel-5","S1","2000-07-11","2001-11-09",1,"-","-","Siemens","Manfred.leitgeb@siemens.at","-",22.126999999999999,null,null,null,null,"2000-11-22","2002-02-28"]
[8386,1423,"      OSA changes required from supporting platforms, e.g. gsmSCF, HLR ","-",3,"Rel-5","S3","2000-09-11","2000-12-14",1,"SP-000302","-","BT, Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[8390,1529,"      Stages 2 and 3 for Interactions OSA - e-commerce","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-07-28","2002-06-21"]
[8391,15005,"   Policy Management - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-13",null,null,null,null,"2002-02-28","2002-09-26"]
[8395,2124,"      Stage 2 for LCS - OSA interfaces","-",3,"Rel-5","S2","2000-12-11","2000-12-11",1,"-","-","Ericsson","Christophe GOURRAUD","az 24/05/01: Rel4 completion 90->100%.",23.126999999999999,null,null,null,null,"2000-11-22","2001-06-06"]
[8398,1433,"   Retrieval of Terminal capabilities","OSA2-TC",2,"Rel-5","S2","2000-07-11","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2003-07-25"]
[8403,1461,"   Service requirements","-",2,"Rel-5","S1","2000-04-17","2002-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[8406,2014,"   Interactions with Optimal Routing","CAMEL4-IOR",2,"Rel-5","N2","2000-07-17","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[8409,2460,"   Notification of GPRS mobility management to CSE","CAMEL4-NMM",2,"Rel-5","N2","2001-03-02","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-05-30"]
[8412,2515,"   Location information during an ongoing call (Handover DP)","CAMEL4-HODP",2,"Rel-5","N2","2001-05-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[8414,2599,"   Transfer of IMEI (with SW version) to CSE (CAMEL4-ATI)","-",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2002-03-25","2002-05-30"]
[8417,2466,"   MExE Rel-5 Improvements and Investigations","MEXE5-ENHANC",2,"Rel-5","T2","2001-03-26","2002-03-08",1,"TP-010071","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2002-03-21"]
[8421,32007,"      Stage 2 for Wideband Telephony Service - AMR","-",3,"Rel-5","S4","2000-01-03","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-02-28"]
[8425,1656,"      N1 Aspects for Wideband Telephony Service - AMR","-",3,"Rel-5","N1","2001-09-21","2001-12-21",1,"-","-","-","-","Some of N1 tasks: Indication of supported codecs by the MS, Bearer cap negociation, codec indication to MS","-",null,null,null,null,"2000-08-08","2002-09-26"]
[8428,1627,"         Codec qualification","-",4,"Rel-5","S4","2000-02-02","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[8432,890,"         Other codec issues (verif., characterization)","-",4,"Rel-5","S4","2000-09-29","2002-06-07",1,"-","-","-","-","ANSI C-Code , Test Sequences, Speech Transcoding Functions, Error Concealment of lost frames, Source Controlled Bit-Rate Operation, Voice Activity Detector, Frame Structure ",26.975999999999999,null,null,null,null,"2000-04-05","2003-01-13"]
[8435,34010,"         Tones and announcements","-",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[8438,76,"         Terminal Acoustic Characteristics ","-",4,"Rel-5","S4","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2000-04-01"]
[8440,1629,"            Test specification for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-02-01","2000-04-12",1,"-","-","-","-","-",26.132000000000001,null,null,null,null,"2000-08-08","2001-03-20"]
[8443,50298,"      Channel coding in 45.003 for Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR","-",3,"Rel-5","GP","2000-01-03","2002-04-05",1,"-","-","-","-","50098 -> 50298","-",null,null,null,null,"2001-02-01","2008-05-06"]
[8447,50000,"      Link Adaptation in 45.009","-",3,"Rel-5","GP","2001-03-26","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-07-31"]
[8451,1826,"Rel-5 Terminal interfaces","TLM5",1,"Rel-5","T2","2001-05-14","2002-03-20",1,"-","-","-","-","Acronym changed from \"TI, TLMN5\"","-",null,null,null,null,"2000-09-14","2015-03-24"]
[8454,1600,"   UE positioning for Rel-5 Location Services enhancements","LCS1-Uepos",2,"Rel-5","R2","2001-01-15","2002-03-29",1,"-","-","-","-","Acronym changed from \"LCS1-Uepos, Rel-5\"","-",null,null,null,null,"2000-07-26","2015-03-24"]
[8458,1641,"      Stage 1 for Event based and Periodic LCS","-",3,"Rel-5","S1","2000-05-22","2000-11-17",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","Evaluate Event based and Periodic LCS to be included in R00, corresponding Stage 1 description",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8460,1179,"      Impact on MAP","-",3,"Rel-5","N4","2002-03-15","2002-06-07",1,"-","-","-","-","Possible impact on UTRAN of LCS quality level request","-",null,null,null,null,"2000-04-19","2002-05-30"]
[8463,2438,"      Gb interface support for LCS","-",3,"Rel-5","GP","2000-04-03","2001-08-31",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8466,2442,"   Location Services for GERAN in Iu Mode","-",2,"Rel-5","S2,G1,G2,R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8469,2445,"      Iu-cs interface support for LCS","-",3,"Rel-5","R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8474,50068,"   GERAN MS Conformance test for LCS","LCS-GERAN-MSconf",2,"Rel-5","GP","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","-","-",null,null,null,null,"2002-05-23","2012-05-21"]
[8477,50069,"   Deleted - GERAN BTS Conformance test for LCS","LCS-GERAN-BTSconf",2,"Rel-5","GP","2002-06-03","2003-06-27",1,"GP-000459","-","-","-","Not started 02/3003. Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2012-05-21"]
[8481,2434,"   LCS interoperability aspects to GERAN (LCS-GERAN)","-",2,"Rel-5","GP,S5","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[8482,2435,"      Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN","-",3,"Rel-5","GP,S2,S5,R2,R3,G2,G1","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[8488,501571,"Rel-5 Security enhancements (SEC1)","-",1,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","Added BB UE authentication and rapporteur added. TO BE DELETED","-",null,null,null,null,"2000-04-09","2011-08-08"]
[8489,1576,"   Rel-5 Network Domain Security (SEC1-NDS)","-",2,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000420","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE","New 33.200 (exisalso for Rel-4)",null,null,null,null,"2000-04-18","2011-08-08"]
[8495,1581,"         Deleted -Main aspects of User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","S3","2000-02-21","2001-06-21",1,"-","-","-","-","-","-",null,null,"SP-12",null,"2000-04-09","2002-11-08"]
[8496,1582,"         Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","N4","2001-09-14","2002-06-28",1,"-","-","-","-","14/02/2002 requirements are not clear/not receivedMarked as closed 12/2008 (was marked 95 complete)","-",null,null,"NP-16",null,"2000-04-09","2008-12-12"]
[8500,2248,"   N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","N1","2001-09-17","2002-06-28",1,"NP-010693","-","-","-","-","24.008 and check 29.018",null,null,null,null,"2000-12-13","2002-09-26"]
[8503,51068,"      Stage 2 (changes to )","-",3,"Rel-5","G1","2002-02-08","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8508,2320,"Deleted - GERAN improvements 3 (new transport layer on interface A)","GEIMP3",1,"Rel-5","GP","2001-04-06","2002-12-20",1,"GP-010909","-","-","-","Terminated - not standardized. Marked as stopped 12/2008","-",null,null,"SP-69",null,"2001-02-01","2008-12-12"]
[8511,2323,"      Deleted - Adaptation of the Layer 3 BSSMAP procedures as required","-",3,"Rel-5","GP","2001-04-06","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8514,35003,"   Rel-5 Performance Management","-",2,"Rel-5","S5","2001-09-17","2002-09-12",1,"SP-010631","-","Nortel","-","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2002-11-08"]
[8517,2392,"GERAN enhancements for streaming services 1 (RLC enhancements)","-",1,"Rel-5","GP","2000-11-06","2002-06-28",1,"GP-010429","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8519,2395,"   RLC protocol enhancement (SDU Discard)","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8522,2399,"   Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD)","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8526,2412,"GERAN/UTRAN interface evolution 1 (evolution of Iu PS)","GERUEV1",1,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"GP-010481","-","SBC","Marc Grant","SBC, Motorola, Nokia, Ericsson, Nortel","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8530,2416,"GERAN/UTRAN interface evolution 2 (evolution of Iu CS)","GERUEV2",1,"Rel-5","GP,R3","2000-06-29","2002-06-28",1,"GP-010417","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8534,2556,"End to End QoS for PS Domain including IMS","E2EQoS",1,"Rel-5","S2,S5,N3","2000-08-28","2002-06-28",1,"SP-010343","-","Ericsson","Johnson.oyama@era.ericcson.se","Acronym changed from \"E2EQoS, Rel-5\"","-",null,null,null,null,"2001-06-08","2015-03-24"]
[8537,2559,"   QoS Management (Provisioning and Monitoring)","E2EQoS-OAM",2,"Rel-5","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-11-08"]
[8539,2571,"   Rel-5 Multimedia Messaging (MMS) enhancements","MESS5-MMS",2,"Rel-5","T2","2001-06-15","2003-03-31",1,"TP-010130","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2000-09-14","2003-03-27"]
[8542,42008,"      WAP Forum dependency: MM1 stage 3","-",3,"Rel-5","T2","2001-06-15","2003-03-31",1,"-","-","-","-","Marked as closed 12/2008 (was marked 80% complete)","-",null,null,null,null,"2002-05-30","2008-12-12"]
[8545,31001,"      Definition of service requirements for Enhanced Messaging Service (EMS) enhancements","-",3,"Rel-5","S1","2001-06-15","2001-09-14",1,"-","-","Ericsson","Alan.Baldwin@EML.ERICSSON.SE","-","-",null,null,null,null,"2001-07-04","2002-02-28"]
[8549,32502,"      Stage 2 - Concept","-",3,"Rel-5","N4,S2","2001-09-03","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8552,50002,"   Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface","GERNACC-Gbmod",2,"Rel-5","GP","2001-11-30","2002-06-28",1,"GP-012314","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8556,50035,"   Deleted - GERAN MS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012750","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[8560,50061,"      Concept","-",3,"Rel-5","GP","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8561,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8565,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8566,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8567,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8568,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[8569,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[8570,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[8571,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8572,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[8573,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[8574,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[8575,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[8576,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[8577,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[8578,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[8579,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8580,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[8581,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[8582,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[8583,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[{"$f":"A8584+1","v":8584},50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8585,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8586,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8587,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8588,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[8589,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8590,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8591,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8592,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8593,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8594,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8595,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8596,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8597,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8598,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8599,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8600,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8601,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8602,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8603,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8604,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8605,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8606,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8607,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8608,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8609,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8610,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8611,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8612,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8613,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8614,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8615,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8616,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8617,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8618,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8619,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8620,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8621,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8622,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8623,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8624,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8625,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8626,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8627,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8628,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8629,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8630,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8631,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8632,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8633,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8634,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8635,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8636,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8637,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8638,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8639,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8640,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8641,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8642,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8643,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8644,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8645,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8646,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8647,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[{"$f":"A8648+1","v":8648},2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8649,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8650,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8651,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8652,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8653,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8654,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8655,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8656,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8657,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8658,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8659,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8660,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8661,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8662,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8663,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8664,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8665,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[8666,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[8667,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8668,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8669,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8670,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8671,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8672,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8673,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8674,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8675,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8676,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8677,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8678,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8679,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8680,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8681,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8682,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8683,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8684,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8685,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8686,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8687,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[8688,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8689,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8690,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8691,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8692,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8693,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8694,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8695,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8696,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8697,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8698,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8699,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8700,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8701,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8702,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8703,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8704,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8705,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8706,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8707,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8708,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8709,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8710,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8711,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[{"$f":"A8712+1","v":8712},2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8713,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8714,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8715,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8716,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8717,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8718,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8719,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8720,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8721,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8722,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8723,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8724,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8725,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8726,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8727,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8728,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8729,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[8730,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8731,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8732,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8733,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8734,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8735,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8736,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[8737,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8738,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8739,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8740,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8741,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8742,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8743,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8744,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8745,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8746,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8747,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8748,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8749,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8750,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8751,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[8752,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8753,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8754,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8755,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8756,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8757,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8758,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8759,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8760,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8761,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8762,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8763,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8764,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8765,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8766,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8767,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8768,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8769,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8770,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8771,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8772,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8773,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8774,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8775,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[{"$f":"A8776+1","v":8776},50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8777,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8778,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8779,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8780,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8781,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8782,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8783,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8784,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8785,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8786,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8787,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8788,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8789,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8790,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8791,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8792,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8793,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[8794,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[8795,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[8796,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8797,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[8798,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8799,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[8800,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[8801,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8802,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[8803,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[8804,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8805,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8806,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8807,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8808,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8809,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8810,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8811,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8812,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8813,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[8814,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8815,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[8816,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[8817,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[8818,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[8819,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[8820,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8821,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[8822,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[8823,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[8824,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[8825,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[8826,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[8827,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8828,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8829,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[8830,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[8831,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[8832,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[8833,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[8834,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8835,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[8836,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8837,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8838,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8839,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[{"$f":"A8840+1","v":8840},1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[8841,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[8842,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8843,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8844,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[8845,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[8846,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[8847,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8848,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[8849,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8850,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[8851,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[8852,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[8853,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8854,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[8855,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[8856,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[8857,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[8858,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8859,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[8860,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[8861,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[8862,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[8863,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[8864,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[8865,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[8866,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[8867,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[8868,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[8869,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[8870,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[8871,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[8872,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[8873,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[8874,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[8875,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[8876,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[8877,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[8878,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8879,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[8880,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8881,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8882,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[8883,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[8884,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[8885,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[8886,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[8887,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8888,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[8889,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8890,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[8891,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[8892,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8893,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[8894,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[8895,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[8896,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[8897,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[8898,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[8899,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[8900,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[8901,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[8902,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[8903,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A8904+1","v":8904},60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[8905,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8906,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8907,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[8908,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[8909,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[8910,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[8911,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[8912,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8913,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8914,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8915,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8916,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[8917,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8918,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[8919,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[8920,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8921,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8922,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8923,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[8924,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[8925,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[8926,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[8927,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[8928,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8929,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[8930,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[8931,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[8932,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[8933,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[8934,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[8935,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8936,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[8937,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[8938,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[8939,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[8940,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[8941,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[8942,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[8943,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8944,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[8945,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[8946,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[8947,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8948,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[8949,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[8950,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[8951,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[8952,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[8953,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[8954,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[8955,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[8956,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[8957,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[8958,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[8959,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8960,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8961,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[8962,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[8963,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[8964,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[8965,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[8966,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[8967,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[{"$f":"A8968+1","v":8968},60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8969,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[8970,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8971,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[8972,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[8973,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[8974,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[8975,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[8976,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[8977,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[8978,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[8979,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[8980,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[8981,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[8982,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[8983,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[8984,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[8985,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[8986,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8987,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[8988,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[8989,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[8990,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8991,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[8992,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[8993,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[8994,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[8995,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[8996,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[8997,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[8998,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[8999,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[9000,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[9001,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[9002,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9003,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9004,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9005,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9006,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[9007,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9008,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[9009,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9010,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[9011,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[9012,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9013,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9014,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9015,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9016,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9017,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9018,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9019,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9020,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9021,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[9022,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[9023,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[9024,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9025,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[9026,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9027,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[9028,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9029,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[9030,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9031,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A9032+1","v":9032},60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[9033,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[9034,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[9035,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[9036,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9037,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[9038,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[9039,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9040,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9041,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9042,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9043,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9044,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[9045,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[9046,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[9047,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[9048,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[9049,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[9050,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[9051,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[9052,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[9053,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[9054,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[9055,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[9056,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[9057,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[9058,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[9059,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[9060,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[9061,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[9062,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[9063,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[9064,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]